# SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	Changes have been made to Section 670 of the Special Provisions.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 1.5 mm.

2.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

3.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	Cross Sections

c.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

d.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

e.	Standard Specifications for Highway Construction 1998 Metric. ($25.00)

f.	High Strain Dynamic Pile Testing and Analyses Test Pile Program, PP 30” o.d. and 48” o.d., Delmag D46-32, Resurrection River, Seward, AK, January 24-28, 2002.

g.	Geophysical Investigation-Resurrection River Bridges, January 2001.

4.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

5.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

6.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for you to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the

STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS. Add the following:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed. (06/25/99)M 68

#### Special Provisions

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the .075 mm  screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11on minus 75 mm  material. (11/29/01)R1M98

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this Subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, fax, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, fax number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or fax prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (2/1/00)R171M98

# SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modifications

103-1.01 CONSIDERATION OF BIDS.  Add the following after item 9.:

In addition to the circumstances described above, you may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State. (10/28/99) M 84

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”.(06/25/99)M 69

# Special Provisions

Add the following Subsection:

103-1.10. Escrow of Bid Documentation. Furnish a legible copy of your bid documentation and an affidavit, as instructed in writing by the Contracting Officer. Bid documentation consists of written documentation of all quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and other information used to prepare your bid for this project.

Obtain and furnish the same level of bid documentation, for each subcontractor with a subcontract exceeding $200,000, regardless of tier.

Meet the following requirements:

- Submitting Bid Documentation. Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number. Deliver the sealed container to the Department-designated document depository for safekeeping.

- Affidavit. Submit directly to the Contracting Officer the completed and certified affidavit located at the end of this Subsection, attesting that:

- the affiant has examined the bid documentation and that it includes all documents used to prepare the bid,

- the sealed container contains all bid documentation submitted,

- the escrow materials were relied on to prepare the bid, and

- should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

- Duration and Use. The bid documentation will remain in escrow, without access by either party, until one of the following occurs:

- There is a dispute related to Change Order. With a neutral observer present, both parties will have joint access to review and copy the files.

- The Contractor files a written claim or initiates Contract-related litigation against the Department. With a neutral observer present, both parties will have joint access to review and copy the files.

- The Contractor completes the Contract and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed. Such action is sufficient grounds for the Contractor to obtain the release and custody of the escrow documentation.

- Failure to Provide Bid Documentation. Refusal or failure to provide your bid documentation or affidavit renders your bid nonresponsive. Failure or refusal to provide Subcontractor bid documentation, will result in subcontract disapproval.

- Confidentiality of Bid Documentation. Materials held in escrow are your property. Except as otherwise provided herein, the escrow materials cannot be released without your approval. The original escrow materials are returned to you once any litigation is concluded, outstanding claims are resolved, and the final release is executed.

- Cost and Escrow Instruction. The Department pays to store all escrowed materials and instructs the depository regarding escrow.

- Payment. Include within the overall Contract bid price all costs to comply with this subsection.

# (02/12/02) S 86

# THIS PAGE INTENTIONALLY LEFT BLANK

#### SECTION 105

# CONTROL OF WORK

### Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, you shall furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

#### Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: Request locates from all the utilities having facilities in the area. Use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

AT&T Alascom, Inc. City of Seward GCI TelAlaska, Inc.

Call the following utilities and agencies directly:

DOT/PF Maintenance and Operations	235-5217

The City of Seward, Engineering Department	(907) 224-4050

State (DOT&PF) Street Light & Storm Drain (Kenai)	269-0783

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination.  You shall bear the expense for any changes or additional relocation requested for your convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

You shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if you are required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of your two (2) week work plan, or not required by the contract.

The utility shall give you, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies, through the Engineer, fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit you, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific coordination requirements for the specific utilities are included below:

Alaska Railroad Corporation (ARRC): Coordinate with ARRC (265-2456) for working near the railroad tracks and building the detour road between Resurrection River bridges. Section 643, Traffic Maintenance, contains the Railroad schedule specifics. Avoid damaging and disrupting the existing railroad facilities.

City of Seward (COS): COS has existing aerial and underground facilities located within this project. Notify COS (907) 224-4050 to establish a point of contact and coordination. The following is a list of the COS facilities that will require relocation.

- Due to the proposed detour road for building the Resurrection bridges, the streetlight at “C” Station 5+449 near Airport Road required relocation. You will relocate the overhead facilities crossing Seward Highway with a new pole and a street light as a bid item under the project contract.

- The aerial crossing at “C” Station 6+155 required relocation due to the widening of Seward Highway to accommodate a right turn lane at the Nash Road intersection. You will install a new pole with down guy and anchor as a bid item under the project contract.

- The clearance of the aerial electrical facilities over the Metco’s driveway will be reduced by the higher profile grade of the new driveway. You will install a temporary pole at Station 5+868 left in line with existing poles GL27 and GL28 as shown on the UE plan sheet.

You will perform the relocation, the installation of the temporary pole, and the retirement of the existing facilities for the City of Seward under the 681 bid items established under the project contract. The City of Seward will provide inspection and/or engineering services to monitor the installation and retirement of its facilities. Notify COS at least fifteen (15) days prior to the start of this project. You shall bear the expense for any restoration to the facilities due to the damages caused by your operation.

GCI Cable Inc. (GCI): GCI has existing aerial and underground facilities within the project limits that are in conflict with the proposed roadway and bridges. Notify GCI at (907) 868-8581 to establish a point of contact and coordination.

The existing GCI underground cable crossing the Seward Highway near the Resurrection Bridge No: 3 at approximate Station 5+985 will require relocation due to the proposed new bridge foundation at this area.

The overhead clearance of the existing GCI facilities at Metco driveway would be impacted due to the raising of the roadway grade. Attach the GCI facilities to the temporary pole (installed under Bid Item 681(28)) for the clearance prior to constructing the proposed Metco driveway. Install a conduit system from Station 5+400 to 6+018 along the east (right) side of the highway (some areas in the joint trench with TelAlaska conduits). Once GCI has accepted the installation by you, GCI will have fifteen (15) calendar days to install and splice its cables that will include a crossing under railroad tracks.

TelAlaska, Inc. (TAI): TAI has existing aerial and underground facilities within the project limits that are in conflict with the proposed Seward Highway project. Notify TAI at (907) 563-2003 to establish a point of contact and coordination. The following is a list of TAI facilities that will require relocation.

- The existing aerial and underground TAI cables at both ends of the Resurrection Bridge No: 1, 2 and 3 will require relocation due to the footing of the proposed new bridge and the proposed detour road for this project. TAI will install a manhole (MH28) at Station 5+400 and a manhole (MH31) at 6+175. TAI will temporarily relocate its facilities from manhole (MH28) to manhole (MH31) along the existing railroad to accommodate the detour road during the construction of the bridges. TAI also install two underground conduits crossing the Seward Highway. It will take twenty-five (25) calendar days for TAI to relocate its temporary facilities and install two bore crossings at this location.

- Coordinate with TAI to ensure all temporary cables have been moved and/or installed prior to constructing the detour road and temporary bridges. Ensure that all the surveying and staking were completed prior to TAI relocating its facilities.

- Install two 100 mm conduits (in some areas joint trench with GCI) and two manholes under bid Item 680(5). Coordinate with TAI when connecting the conduits to the manholes MH28 at 5+400 and MH31 at 6+175. TAI will install its cables inside the conduits and manholes that are installed by you. It will take twenty (20) calendar days for TAI to install its facilities once TAI accepts the conduits and manholes you install.

105-1.12 LOAD RESTRICTIONS. Add the following: The Department requires you to have overload and oversize permits to transport the prestressed concrete girders on the State’s roadway system. Unless otherwise permitted by the overload permit officer, any permit will be subject to the following limitations:

Maximum Single Axle Load	13,610 kg (30,005 lbs.)

Maximum Tandem Axle Load	22,680 kg (50,001 lbs.)

Maximum Triple Axle Load	31,750 kg (69,997 lbs.)

Maximum Four Axle Load	40,820 kg (89,993 lbs.)

Minimum Spacing of Axle Group	6.1 m (20 ft) center to center axle groups

# Minimum Spacing Within Group			1.2 m (3.9 ft) center to center axles

Maximum Vehicle Speed on any Structure	5 km/h (3.1 mph)

The maximum axle loads tabulated above are applicable to hauling equipment with fixed axles only; variable load suspension (VLS) axles shall not be considered part of an axle group for purposes of this specification.

The Department will not permit you to haul girders on one tractor to traveling backwards on public roads or streets for one-way travel distances totaling more than 16 kilometers.

Vehicles shall cross structures at a constant speed with the load centered on roadway and no shifting of gears. When crossing structures and the load exceeds 36,290 kg, a walking flagman shall precede the vehicle.

This overload allowance shall not apply to the transportation of construction materials other than precast prestressed concrete girders.

All overload permits are subject to seasonal load restrictions.

Routing shall be as prescribed by the Permit Officer. The Permit Officer may be contacted at (800) 478-7636 or (907) 345-7636.

Submit to the Engineer for review, alternate axle configurations and loading which may reduce the overload movement restrictions.  (01/08/97)R103M98

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve you from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract. (02/06/02)R237M98

### Standard Modifications

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Delete this Subsection in its entirety and substitute the following:

Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

- The act, event, or condition the claim is based on.

- The Contract provisions which apply to the claim and provide relief.

- The item or items of Contract work affected and how they are affected.

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

- A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630.  (03/26/01) M 101

##### Special Provisions

Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

# SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials which remain in place at your convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject you to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (08/31/99)S 13

106-1.02  LOCAL MATERIAL SOURCES.  Add the following under Item 2. Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to their beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (05/01/02)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following:

When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T 27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 224

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO TP 53

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T 166/T 275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

(07/26/01)S 87

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

#### Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If you discover cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by your operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Add the following: The Department has received the following permits on your behalf which are located in Appendix A:

1.	Department of Natural Resources Tideland Permit, Permit No. ADL 228297, dated July 18, 2002, expires July 14, 2005.

2.	Department of Fish and Game, Fish Habitat Permit FG 02-II-0544, issued July 18, 2002, expires December 31, 2004.

3.	Department of Fish and Game, Fish Habitat Permit FG 02-II-0546, issued July 17, 2002, expires December 31, 2004.

4.	Department of Fish and Game, Fish Habitat Permit FG 02-II-0547, issued July 17, 2002, expires December 31, 2004.

5.	Department of Fish and Game, Fish Habitat Permit FG 02-II-0543, issued July 23, 2002, expires December 31, 2004.

6.	Department of the Army Permit, Permit No. 4-2002-0118, Resurrection River 29, issued August 28, 2002, expires August 31, 2005.

- Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion and Pollution Control for requirements for this permit. (5/21/01)R7M98

# Add the following:  Obtain a Right-Of-Way Construction Permit from the Kenai Peninsula Borough prior to commencing work within the Borough’s ROW. Contact Borough inspector Gary Davis at 907-262-4427.

# 107-1.08 RAILWAY-HIGHWAY PROVISIONS. Delete this Subsection in its entirety and substitute the following:

# SECTION 1.  DEFINITION OF TERMS

ARRC	Alaska Railroad Corporation, P.O. Box 107500, Anchorage, AK 99510-7500.

ARRC Property	All lands owned or withdrawn for the use of the ARRC, including the ARRC's track right-of-way and communications pole line right-of-way.

Chief Engineer	The person employed by the ARRC as head of its Engineering Department or Branch, or his/her authorized representative.

Contractor	Any agent of the Permittee, including Contractors or subcontractors employed to construct, reconstruct, operate and/or maintain the Facility.  The term "Contractor" shall be synonymous with the term "Permittee" when the Permittee performs the construction, reconstruction, operation and/or maintenance of the Facility with its own personnel.

Director, Real Estate	The person authorized by the ARRC to execute contractual real estate agreements on behalf of the ARRC.

Facility 	Any improvements owned by the Permittee/Contractor which are to be placed on ARRC property in accordance with written permission executed by ARRC and Permittee.

Roadway Worker	Any employee of a railroad, or of a contractor to a railroad, whose duties include inspection, construction, maintenance, or repair of railroad track, bridges, roadway, signal and communication systems, electric traction systems, roadway facilities, or roadway machinery on or near track or with the potential of fouling a track.

Telecommunications Supervisor	The person employed by the ARRC as head of its Telecommunications Department or Branch, or his/her authorized representative.

Permittee/Contractor	The person, company or governmental agency to whom the right to enter upon ARRC Property was given in the form of written permit or contract executed by the ARRC and Permittee/Contractor.

Trackwork	All work on the line from the top of subgrade to the top of rail, including geotextile, when required.

Track Materials	All hardware, excluding signals and controllers, associated with the running of a railroad.

# SECTION 2.  GENERAL REQUIREMENTS

- 2.1	All construction, reconstruction, operation, and maintenance on ARRC Property shall be performed in compliance with these Standard Specifications for Work on Railroad Property, including all revisions thereto.

2.2	Failure to comply with these Standard Specifications for Work on Railroad Property shall result in the demand of ARRC to suspend all work on ARRC Property.

2.3	All work on or about ARRC Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with approved ARRC practices, and as specified herein.  ARRC traffic and property shall be protected at all times.

2.4	The safety and continuity of the operation of the traffic of ARRC shall be of first importance and shall be at all times protected and safeguarded.  The Permittee/Contractor and its subcontractors shall be required to perform and arrange their work accordingly.  Whenever, in the opinion of the Chief Engineer or his or her representatives, the work or its performance may affect or involve the safety of ARRC's facilities and/or operation of its railroad, the method of doing such work shall first be submitted by the Permittee/Contractor to the Chief Engineer for his/her approval, without which it shall not be commenced or prosecuted.  The approval of the Chief Engineer, when given, shall not be considered as a release from responsibility or liability for any damage which ARRC may suffer, or for which it may be liable, as a result of the acts or omissions of the Permittee/Contractor, its subcontractors or employees.

2.5	Whenever, in the opinion of the Chief Engineer, the construction may cause a hazard to the safe operation of ARRC, ARRC may, in its discretion, place at the site of the work the required number of qualified employees to protect its operations.  The providing of such employees and such other precautions as may be taken shall not relieve the Permittee/Contractor and its subcontractors from liability for the payment of damages caused by their operations.  ARRC shall be the sole judge of the necessity for, and as to the number and classification of employees required. The Permittee/Contractor shall reimburse ARRC for the cost and expense incurred in providing such employees.

## SECTION 3.  SAFETY REQUIREMENTS

3.1	The safety of personnel, property, rail operations, and the public is of paramount importance in the prosecution of any work on ARRC Property.  The Permittee/Contractor shall comply with all Federal, State and local governmental regulations (e.g. OSHA, NESC, etc.) applicable to the construction, installation, or maintenance of any Facility.

As reinforcement and in furtherance of overall safety measures to be observed by Permittee/Contractor (and not by way of limitation), the following special safety rules shall be followed while working on ARRC Property. Further railroad safety information may be obtained from the ARRC Safety Office at 907-265-2440.  Safety information is also available on the ARRC website at www.akrr.com.

3.2.	ARRC flag protection is required before any activity can occur on or near a railroad operating facility such as a track, yard, bridge or shop building.  For subsidiary work, such as surveying or inspection, an ARRC furnished flagman will provide a safety briefing prior to the commencement of the work   For any activity involving a disturbance or potential disturbance to the track, track embankment, or any railroad facility, ARRC may require the Permittee/Contractor to submit a specific Railroad Safety Plan prior to startup.   Projects that involve activities that cross the tracks or are longitudinal to the tracks will require a specific Railroad Safety Plan and a one-hour ARRC provided training course for Permittee/Contractor’s project supervisors prior to the initiation of work on ARRC Property.  Specific information on Railroad Safety Plans may be obtained from the ARRC Safety Office at 907-265-2440.

3.3	The Permittee/Contractor shall arrange for ARRC flag protection when performing any work within 6 m (20’) of any track.  All work within 6 m (20’) of the track shall cease when a train passes and all Permittee/Contractor employees shall maintain a distance of at least 6 m (20’) from the track until the train has safely passed.  In addition, any work that could come within 6 m (20’) of the track will cease when a train passes.  For example, crane or pile driving activities shall stop when trains pass when the maximum boom and suspended load radius can come within 6 m (20’) of the tracks.  Pile driving shall not be done when trains are passing the work site.  Vehicles and other construction equipment shall not be operated or parked closer than 6 m (20’) from any track without ARRC flag protection.

3.4	In the event Permittee/Contractor will be performing construction or other activities on or in close proximity to a railroad track, the Permittee/Contractor shall be responsible for compliance with applicable Federal Railroad Administration’s Roadway Worker Protection (“RWP”) regulations (49 CFR 214, Subpart C) if its employees qualify as “Roadway Workers”.  Under 49 CFR 214, Subpart C, railroad contractors are responsible for the training of their employees on these regulations.  All RWP related Work shall be conducted in strict compliance with the RWP safety standards set forth in 49 CFR 214, Subpart C and the Permittee/Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards prior to beginning any RWP related Work.

3.5	In the event Permittee/Contractor will be performing construction or other activities on a railroad bridge, the provisions of 49 CFR 214 regarding bridge worker safety shall apply.  All bridge related work shall be conducted in strict compliance with the bridge worker safety standards set forth in 49 CFR 214 and the Permittee/Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards prior to beginning any bridge related work.

SECTION 4.  INSURANCE REQUIREMENTS

4.1       The Permittee/Contractor shall procure and maintain at all times while performing work on ARRC Property, and be covered by the types of insurance with the minimum limits as specified in Section 4.4.

4.2	Each policy specified in Section 4.4 shall be:  (1) endorsed to include ARRC as an additional named insured with respect to the performance of the work; (2) endorsed whereby the insurance company will notify ARRC of any material change, cancellation, non-renewal or expiration of the insurance policy in writing not less than thirty (30) days prior to the effective date; (3) endorsed with a waiver of subrogation rights in favor of ARRC; and (4) endorsed with the Alaska Suit Endorsement.

- 4.3	Prior to commencement of any work on ARRC Property, the Permittee/Contractor shall deliver to ARRC certificate(s) of insurance showing evidence of the insurance required in Section 4.4.

4.4	Alaska Railroad Corporation Minimum Insurance Requirements.

a.	Commercial General Liability insurance with limits not less than $5,000,000 per occurrence and $5,000,000 aggregate for Bodily Injury and Property Damage, including coverage for Premises and Operations Liability, Products and Completed Operations Liability, Contractual Liability, and Broad Form Property Damage Liability. Coverage shall not contain any exclusions of Explosion, Collapse, Underground, or Rail Operations.

b.	Automobile Liability insurance on all owned, non-owned, hired and rented vehicles with limits of liability of not less than $5,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

c.	Worker's Compensation insurance in accordance with the statutory coverage required by the State of Alaska and, where applicable, insurance in compliance with any other statutory obligations, whether State or Federal, pertaining to the compensation of injured employees assigned to the Work, including but not limited to Voluntary Compensation, Federal Longshoremen and Harbor Workers Act, Maritime and the Outer Continental Shelf's Land Act and the Federal Employers Liability Act.

d.	If any part of the work to be performed on ARRC Property is located in close proximity to a railroad track, then the Permittee/Contractor shall also obtain Railroad Protective Liability insurance (Alaska Railroad Corporation as named insured) with limits of liability of not less than $5,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

# SECTION 5.  NOTICE

- 5.1	A pre-construction meeting shall be held with ARRC's Chief Engineer and representatives of the Permittee/Contractor and subcontractors prior to the commencement of any work on ARRC Property by the Permittee/Contractor or its subcontractors.

- 5.2	The Permittee/Contractor shall give written notice to the Chief Engineer not less than ten (10) days in advance of the commencement of any construction, reconstruction or major maintenance activity on ARRC Property, in order that the necessary arrangements may be made for the protection of ARRC's operations.  This notice shall include a description of the proposed work on ARRC Property, schedule of work, and the names of any Permittee/Contractor's subcontractor who may also be working on ARRC Property.

# SECTION 6.  FLAG PROTECTION AND PROTECTION OF ARRC TRAFFIC

- 6.1	Whenever ARRC flag protection is required, it will be provided by ARRC at Permittee/Contractor's expense.  ARRC flag protection is to insure the safe movement of trains and other rail traffic and shall be done in strict accordance with the ARRC rules on flagging.  A minimum of 48 hours prior notice is required for ARRC to provide flag protection.

- 6.2	ARRC will, during the progress of the work, utilize as many qualified flag people as in the opinion of the ARRC may be required for the adequate protection of ARRC traffic.  All expense for providing such flagpersons shall be paid by the Permittee/Contractor to ARRC.

- 6.3	The Permittee/Contractor shall arrange with ARRC to keep itself informed on the time of arrival of all trains and shall stop any of Permittee/Contractor's operations which might be or cause a hazard to the safe passage of the train past the site of the work from ten (10) minutes before the expected arrival of the train until it has safely passed.

6.4	Track outages will only be approved in exceptional cases for limited duration’s.  The only outage of the main track will be for installation of the crossings.  Track outages will be:

- Scheduled 30 days in advance

- No more than 12 hours

- Only on Saturday nights

- With 48 hours notice, ARRC may delay the outage by one week.

Prior to a proposed track outage, the Permittee/Contractor shall submit a closure plan to ARRC.  The plan will describe the work to be accomplished, the equipment, manpower and other resources required, and the work schedule.  Once approved by ARRC, the Permittee/Contractor shall follow the plan.  ARRC reserves the right to assume control of the work to reestablish rail service if the schedule is not met.  Permittee/Contractor shall bear all costs and damages which may result from failure to meet the closure schedule, in addition to the train delay charges provided for herein.

- SECTION 7.  TRAIN DELAYS

7.1	All work on ARRC Property shall be conducted in such a manner as to prevent delays to trains or other rail traffic operated by ARRC.  The ARRC will provide a weekly forecast of train traffic and the ARRC flagmen will provide daily updates of anticipated train traffic.  Under no circumstances will the ARRC be liable in any way for delays to your work created by any changes or deviations from anticipated train schedules.

- ANTICIPATED WORK WINDOWS DURING CONSTRUCTION

- ARRC Track Maintenance Work Window: Section and summer work crews may need access into the work area to perform routine track maintenance work and scheduled summer major track replacement work.  The routine track work is performed as necessary for the safe passage of trains.  Railroad on-track equipment also travels through the project as needed.

- Train Traffic: The track through the project is very active.  The approximate number of trains in a 24 hour period is as follows:

- Summer Season - (May 11 to September 17) Approximate Daily Trains

- 4 Passenger Trains

- 2 Freight Trains, up to 6 per week

- 2 Coal Trains, up to 6 per week

- 1 Work Train

- Shoulder and Off Season - (April 10 to May 11 and September 18 to May)  Approximate Daily Trains

- 2 Freight Trains, up to 4 per week

- 2 Coal Trains, approximately every other day

- 1 Work Train, up to 6 per week

- ARRC also charters passenger trains, which may run on any day.

- Tracks out of Service: The work shall be planned to minimize track service outages.

- Prior to track outages, submit a closure plan to the Railroad.  The plan shall establish the work to be accomplished, the equipment, manpower and other resources required, and schedule.  Once agreed to by the Railroad, you shall follow the plan.  The Railroad reserves the right to assume control of the work to reestablish rail service if the schedule is not met.  You will bear all costs and damages, which may result from failure to meet the closure schedule, in addition to the train delay charges provided for in the contract.

- 7.2	Should any of the Permittee/Contractor's or its subcontractor's actions or activities cause delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Permittee/Contractor by ARRC.

- Passenger trains each:		$50 per minute of delay, 60-minute minimum charge.

- All other rail traffic:	$50 per minute for each delay over five minutes, 30 	minute minimum charge.

- Rail barges, or other

- connecting carrier vessels:	No charge for delays of one hour or less; $1,000 per hour for each hour or any part of an hour thereafter with a 	minimum charge of $6,000.

- 7.3	Delay time will be taken from the train sheet in ARRC’s Dispatcher's Office, Anchorage (907-265-2504) for all delays and such train sheet shall be the official document by which the length of time a train is delayed will be determined.  If another crew is needed to relieve the original crew, the charge shall also apply to the second crew.  If such delay causes a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by said train sheet.

# SECTION 8.  PROTECTION OF ARRC COMMUNICATION LINES

- 8.1	All work on ARRC Property shall be conducted in such a manner as to protect ARRC's communication facilities at all times from outages resulting directly or indirectly from the Permittee/Contractor's or its subcontractor's operations.

- 8.2	Should any of the Permittee/Contractor or its subcontractor's operations cause outages to said communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Permittee/Contractor:

- Open wire communication circuits:	$1.00 per minute per circuit

- Communication cable:	$1.00 per minute per cable

- 8.3	A minimum charge of $250.00 will be made for each outage plus the total repair costs.  The outage time shall be that as established by ARRC's Test Board, Anchorage.

- 8.4	There shall be no equipment operated or excavation made within 4.6 m (15’) of any ARRC communication pole guy, anchor, or other communications apparatus unless authorized in advance by the Telecommunications Supervisor.

# SECTION 9.  ROAD CROSSINGS

- 9.1	Whenever automatic railroad crossing signals are in the work area, these signals must remain in operating condition at all times.  If, as a result of the Permittee/Contractor's or subcontractor's activities the signals become inoperable, the crossing shall be continuously flag protected until the signals are again operable.  See Section 6 for flagging specifications.

- 9.2	When regular railroad crossings are used as haul routes inside or outside the work area, flagpersons shall be provided by the Permittee/Contractor for said crossings in all situations at the discretion of the ARRC.

- 9.3	Temporary road crossings may be installed provided the Permittee/Contractor has acquired from ARRC a temporary road crossing permit for said crossing.

- 9.4	The temporary road crossing shall be constructed to the length and the standards specified in the temporary road crossing permit.  All protective signs required by ARRC shall be provided and properly maintained by the Permittee/Contractor.  The temporary road crossing shall be installed under ARRC flag protection in accordance with Section 6 of these specifications.

- 9.5	The flange ways of all road crossings used by the Permittee/Contractor or its subcontractor as haul routes or temporary road crossings shall be kept clean and free of gravel at all times and shall otherwise be maintained to the satisfaction of the Chief Engineer.

- 9.6	When a temporary road crossing is in use, ARRC flag protection shall be provided at all times.  See Section 6 for specifications.

- 9.7	When a temporary or private road crossing is not in use, the Permittee/Contractor shall provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

- 9.8	When not in use during the winter season, the temporary road crossing shall be removed.  Upon completion of the work or termination of the crossing permit, the temporary crossing shall be removed and the area restored to its original condition.

- 9.9	The Permittee/Contractor agrees that all others using the private road crossing, except ARRC and its employees, shall be considered agents of the Permittee/Contractor.

- 9.10	Sight Triangles at road crossings shall be maintained by Permittee/Contractor free of vegetation and other obstructions to vision in accordance with the table entitled "Sight Triangle Distance" attached and as otherwise established and revised from time to time by ARRC.

- 9.11	Temporary public road crossings must be included in a traffic control plan submitted by the Permittee/Contractor to Alaska Department of Transportation (ADOT) for review and approval prior to constructing the crossing.

- SECTION 10.  POWER AND COMMUNICATION LINES

- 10.1	All power and communication lines shall be designed and constructed in accordance with the current edition of the National Electric Safety Code (NESC).

- 10.2	Underground power and communication lines shall be installed in accordance with Section 11 of these specifications.  Whenever an underground power or communication line crosses underneath a track, a casing pipe shall be installed for carrying such lines.

- 10.3	The minimum clearance above the top of rail of ARRC track shall be in accordance with the handbook referenced in Section 11.1, plus 0.15 meter (6”) to allow for future grade raises.

- 10.4	The minimum clearance above ARRC communication lines shall be in accordance with the handbook referenced in Section 11.1.

- 10.5	Additional lines may not be added, or the characteristics of the line(s) changed without the prior written approval of ARRC's Director, Real Estate or Chief Engineer.

- 10.6	Wires shall be strung across ARRC tracks only when ARRC flag protection is provided in accordance with Section 6 of these specifications.

- 10.7	No wires shall be strung across ARRC's communications lines without first receiving prior written approval from ARRC's Telecommunication Supervisor, and such work must be accomplished only at a time and in a manner prescribed by said Telecommunication Supervisor.

- SECTION 11.  UNDERGROUND UTILITIES

- 11.1	All underground utilities, including culverts, pipelines, and underground power and communication lines, on ARRC Property shall conform to the current American Railway Engineering Association (AREA) / American Railroad Engineering and Maintenance-of-way Association (AREMA) Specifications.

- 11.2	Unless the Chief Engineer authorizes another method in advance and in writing, all underground utilities shall be installed under tracks and roads by boring, jacking or tunneling.

- 11.3	Boring, jacking or tunneling shall be done under ARRC tracks only when ARRC flag protection is provided in accordance with Section 6 of these specifications.

- 11.4	The proposed plan for boring, jacking or tunneling shall be approved by the Chief Engineer prior to commencing the operation.

- 11.5	All boring, jacking or tunneling headings shall be continuously protected against any loss of ground material by shoring and/or cribbing as necessary.

- SECTION 12.  OPEN TRENCHING

- 12.1	Only when authorized in advance and in writing by ARRC shall any portion of the track be removed to allow trenching for installation of the Facility.

- 12.2	If allowed to open trench, the track may be removed from service only at the time authorized by the Chief Engineer and shall be restored to service within the time period specified by the Chief Engineer.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in accordance with Section 7 of these specifications, whichever is greater, and shall be collected from the Permittee/Contractor.

- 12.3	All track work shall be accomplished by qualified track persons.

- 12.4	Only that portion of the track structure necessary to excavate, stockpile and install the Facility shall be removed.  All track material removed shall be handled, stockpiled and relayed in a manner to avoid damage.  Any material that is damaged shall be replaced by the Permittee/Contractor at its own expense.

- 12.5	The backfill of the trench under the track and in the road bed prism shall be of the same type of material as taken out, except the top 0.6 m (2’) shall be clean pit run gravel.  Backfilling and compaction shall be in 0.3 meter (1’) lifts with a compaction of 95% of maximum density in the area affecting the road bed prism.

- 12.6	The ballast used in replacing the track shall be equal in depth and quality as that which was removed.  The track shall be relayed and brought to original grade in accordance with standard ARRC practices.  The track shall be resurfaced as often as necessary for a period of 12 months after completion of construction to remove any settlement that may have occurred.

- SECTION 13.  EXCAVATIONS

- 13.1	Unless authorized in advance and in writing by ARRC, the top of any excavation shall not be within 6 m (20’) of the centerline of any track.

- 13.2	No water shall be allowed to stand in open excavations in the track area.

- 13.3	Bridging and shoring shall be adequate to safely carry ARRC traffic and the decision of the Chief Engineer pertaining to same shall be final.

- 13.4	All open excavations shall be continuously protected by flags, flares, barricades or watchpersons, as directed by ARRC.

- 13.5	No excavation shall be left open more than three days, unless authorized by the Chief Engineer.

- 13.6	ARRC embankments and cut slopes shall not be disturbed any more than necessary to accommodate the construction and shall be left in a stabilized condition.

- 13.7	ARRC ditches, culverts and roadways shall be kept clean and free of rock, gravel, construction debris and equipment at all times.

- SECTION 14.  ARRC INSPECTIONS

- 14.1	ARRC may furnish an inspector during the periods of construction on ARRC Property.  The ARRC inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary.  The ARRC inspector will work directly with the representative of the Permittee /Contractor and the decision of the ARRC inspector in matters pertaining to ARRC operations and safety shall be final.  In the event more than one shift is worked, an ARRC inspector will be required for each shift.  Presence or absence of an ARRC inspector shall not relieve the Permittee /Contractor of liability for damage done to property of ARRC, or the property of ARRC lessees or permittees having installations on ARRC Property.  All ARRC cost and expense for furnishing said inspector(s) shall be collected from the Permittee /Contractor.

- SECTION 15.  USE OF EXPLOSIVES

- 15.1	The use of explosives shall be done in compliance with all applicable Federal, State and local laws and ordinances regarding same.

- 15.2	No blasting of any kind will be permitted unless the Permittee/Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, ARRC flag protection in accordance with Section 6 of these specifications shall be provided on each side of the blast area by the Permittee/Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

- SECTION 16.  SNOW REMOVAL

- 16.1	Snow removal operations shall be conducted in such a manner as to not place snow (1) upon the tracks of ARRC; (2) where it interferes with the normal operation of the automatic crossing signals; (3) impairs the visibility of either highway or rail traffic at the crossing.

- 16.2	Snow removal operations shall be conducted in accordance with Section 3 of these specifications.

- SECTION 17.  CLEAN-UP

- 17.1	At all times, all work and activities on ARRC Property shall be accomplished in such a manner as to keep the ARRC Property in a neat, orderly and safe condition satisfactory to ARRC.

- 17.2	Upon completion of Permittee/Contractor’s work, all equipment and unused materials shall be removed and the ARRC Property shall be left in a neat and clean condition satisfactory to ARRC.

- 17.3	Should the Permittee/Contractor or its subcontractor fail to comply with Section 17.1 and 17.2 above, ARRC may perform the required clean-up.  All ARRC costs and expenses for performing this work shall be collected from the Permittee /Contractor.

- 107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If you require water for any construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (05/29/02)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following before the last paragraph: When construction activities meet any of the following conditions, advise the appropriate owning Utility(s) in writing at least 24 hours in advance of work.

1.	Operations anticipated being within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 3 m of an overhead electrical line.

- The notice shall indicate the location and duration of the work.  Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m of an overhead line.  Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services. (7/30/99)R170M98

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

##### Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.  (01/22/02)S 80

SECTION 108

PROSECUTION AND PROGRESS

# Standard Modifications

108-1.01 SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4. and add the following to Item 5.:

Ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts. (10/28/99) M 70

#### Special Provisions

108-1.03 PROSECUTION IN PROGRESS. Add the following under item no. 1:  Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department. (4/22/99)R250M98

Delete Item 5 of the first paragraph and substitute the following:

- The submittals identified under Subsection 641-1.03, Submittals. (01/31/02)R160M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by you to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date. (2/15/01)R242M98

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modifications

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1. Labor: Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work. (5/31/00)M90

Replace subparagraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e. (02/08/01)M71

#### Special Provisions

Under item 3, Equipment, change the first sentence to read … “Rental Rate Blue Book for Construction Equipment”, published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA, 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (01/27/00)R14

#### Standard Modifications

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. You will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a sub-subcontractor. (02/08/01)M71

Special Provisions

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from you, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.  (02/04/02)R137A

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska, at a location acceptable to the Engineer. (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. You or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if you submit less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, you shall submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If a DBE replacement is approved by the Engineer, you shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that you cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- You have not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If you are unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with you. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from you for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and your subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, you will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by you to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- You will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of your operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, you shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of you, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. You must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to you, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall you take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, you shall immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that you cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	You are not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of you; and

- You are unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. You will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. You will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If you fail to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If you fail to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of you from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 202

#### REMOVAL OF STRUCTURES AND OBSTRUCTIONS

##### Special Provisions

202-1.01 DESCRIPTION.  Add the following:

This work includes the complete removal of the three existing Resurrection River Bridges (Bridge Numbers 596, 597 and 598) and portions of the Clear Creek, Salmon Creek and Bear Creek Bridges (Bridge Numbers. 599, 600 and 601) as shown on the Plans.  The existing Resurrection River Bridge No. 1 (Bridge No. 596) is a 61.8m long by 10.36m wide two-lane bridge. The existing Resurrection River Bridge No. 2 (Bridge No. 597) is a 46.3m long by 10.36m wide two-lane bridge. The existing Resurrection River Bridge No. 3 (Bridge No. 598) is a 55.4m long by 10.36m wide two-lane bridge.  The superstructures of all three Resurrection River bridges are constructed of steel girders with concrete decks.  The existing substructures consist of concrete cap beams on steel H-piles and concrete-filled pipe piles.  The original construction plans for all six bridges are available at the Central Region Plans Room.

This work also includes removal and disposal of existing asphalt pavement and membrane for the Salmon and Bear Creek Bridges.

Add the following: This work also consists of pavement planing as specified in this Section. (02/28/01)R143M98

202-3.03 REMOVAL OF BRIDGES, CULVERTS AND OTHER DRAINAGE STRUCTURES. Add the following: This work includes demolishing three (3) existing bridges that span the Resurrection River.  Remove and dispose of the following elements of these bridges:

1.	cast-in-place concrete deck,

2.	stay-in-place forms,

3.	bridge rail,

4.	top portions of the concrete abutment and wingwall,

5.	expansion devices, and

6.	miscellaneous hardware

7.	other items designated by the Engineer

Bridges 596, 597, and 598 have Nelson Studs. Bridge decks and other concrete bridge pieces shall be disposed of in accordance with Subsection 202-3.05.

Deck sections shall be removed in such a manner that damage is not done to the supporting structural steel members. Repair at your own expense any damage to structural steel due to his removal operations.

The use of explosives to remove portions of the existing bridge is not prohibited, provided that you shall be responsible for repairing any resulting damage to those portions of the structure that are to remain in place to the satisfaction of the Engineer and at no additional cost to the State, and provided that debris or other material from blasting operations does not damage fish or fish habitat or endanger the public. If you elect to use any explosives for concrete removal, a detailed plan shall be submitted to the Engineer for analysis 2 weeks prior to commencing any blasting activities. The receipt for analysis by the Engineer of your plan does not constitute approval for implementation nor the accuracy of its implementation.

On structural steel which is to be reused, concrete shall be removed to bare metal over at least 50 percent of the contact surface, and shall be removed to within 5 mm of the steel surface elsewhere. Any concrete which does not adhere tightly to the steel shall be removed. In areas where studs or cover plates are to be welded, concrete and other deleterious matter shall be totally removed from the steel surface.

The existing lateral bracing shall be removed, modified and reinstalled as shown on the Plans and in accordance with Section 504. When the existing lateral bracing is removed, you shall provide other temporary bracing during construction of the new truss members. A detailed plan for temporary lateral bracing shall be submitted to the Engineer for approval 2 weeks prior to removal of existing lateral bracing.

Where new concrete is to be cast against surfaces of existing backwalls or wingwalls, the existing surfaces shall be roughened to expose coarse aggregate.

Provide the detailed plans for pollution containment and prevention measures to be used at each bridge site where any part of the bridge is being removed.  Submit these plans as part of the SWPPP called for in Section 641.

It is known to the State of Alaska that elements of Bridge Nos. 596, 597, 598 and 599 contain lead-based paint.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 150 mm.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.  (3/29/01)R84M98

Add the following Subsections:

202-3.06 PAVEMENT PLANING. Remove existing asphalt concrete pavement by cold planing at locations shown on the Plans. The surface of the pavement after planing shall be uniformly rough grooved or ridged.

If you choose not to substitute the planed material (RAM) for Aggregate Base Course in accordance with Subsection 301-2.01, or incorporate it into the structural prism of the road as directed by the Engineer, then dispose of it in an acceptable manner outside the project limits in accordance with Subsection 202-3.05, Removal of Pavement, Sidewalks and Curbs. Obtain written consent from the property owner if disposing of it on private land.  Obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt. ADEC permitting officer in Anchorage may be contacted at 269-7590.

During the planing operation, sweep the streets with mechanical sweepers equipped with vacuum and water sprinkling devices to control dust and remove all loosened material from the planed areas. The removal operation shall follow within 15 m of the planing machine.

Do not allow traffic to travel on surfaces that have an abrupt longitudinal planed edge greater than 50 mm. In the event that it is necessary to route traffic across such edges, an asphalt concrete transition 0.6 m in width shall be placed adjacent to the edge and to all gutters.

- Maintain a tolerance of less than 7 mm between adjacent passes by the planer.

Remove existing asphalt concrete pavement overlay from gutters adjacent to the area being planed.

The existing curb and gutter not designated for removal shall not be damaged or disturbed. Any damage caused by the planing operation shall be removed and replaced by you at your expense.

The planing machine shall be specifically designed for the removal of bituminous pavement without the addition of heat. The cutting drum shall be a minimum of 1.5 m wide and shall be equipped with cutting teeth placed in a variable lacing pattern to produce the desired finish.

The planing machine shall have the following capabilities:

1.	operating speeds from 0 to 12 m per minute,

2.	self propelled,

3.	able to spray water at the cutting drum to minimize dust,

4.	able to remove material next to the gutter,

5.	designed so that the operator can at all times observe the planing operation without leaving the controls,

6.	longitudinal grade controls that are automatically actuated by a ski that is at least  9 m on each side of the planning machine to control the depth and cross slope of the planed surface, and

7.	able to cut up to 76 mm without producing fumes or smoke.

Provide a smaller machine to trim areas that are inaccessible to the larger machine at manholes, valve covers, curb returns, and intersections.

202-3.07 SALVAGING. Notify the Engineer, five (5) days prior to removing manholes and inlets. Upon excavation, the Engineer will physically identify those manholes, inlets or portions thereof to be salvaged.  All manholes, inlets or portions thereof so designated will be delivered to the Department of Transportation Maintenance Yard located in Seward.  All remaining items removed become your property.  (8/30/00)R258M98

202-4.01 METHOD OF MEASUREMENT.  Add the following:

202(15).  By the square meter of pavement planed as shown in the Plans

.

202-5.01 BASIS OF PAYMENT. Add the following:

Item 202(1).  Payment will include all labor, equipment and materials necessary to remove and dispose of the cast-in-place concrete deck, stay-in-place forms, bridge rail, expansion devices, portions of abutment and wingwalls and miscellaneous hardware as shown on the Plans and as accepted by the Engineer. These bridge elements shall become your property.

Removal, Modifications and reinstallation of lateral bracing, including temporary bracing, will be paid under Item 503(1) Reinforcing Steel. (2/2/00)R108M98

Removal and disposal of asphalt pavement and membrane for the Salmon and Bear Creek Bridges is subsidiary.

After the third paragraph, add the following:

Item 202(15).  At the contract price per unit specified.  Payment is full compensation for mechanical sweepers during planing operations, removal of pavement from the gutter and stockpile of planed material per sub section 202-3.06.  (2/28/01)R143M98

Payment will be made under:

| # Pay Item | # Pay Unit |
| --- | --- |
| 202(15) Pavement Planing | Square Meter |

SECTION 203

EXCAVATION AND EMBANKMENT

# Special Provisions

Add the following Subsection:

203-2.07 DITCH LINE/SUBGRADE BLASTING.  Where rock is encountered in ditches and below the subgrade, drill and blast to the depth shown in the Plans or as directed by the Engineer to fracture the rock foundation.  Space these holes closer than production holes and load the holes lighter.  Stem appropriately to minimize rifling.  Use this procedure to provide a stable draining interlock between the embankment material and the rock surface.  Provide a backhoe or other equipment to enable the Engineer to verify the effectiveness of the blasting.  Adjust the hole pattern and loading if the procedure fails to fracture the underlying rock 1.1 m below the Selected Material, Type A layer.

203-3.01 GENERAL. Add the following to the sixth paragraph: Prior to obliterating the existing driveway, remove the existing pavement and dispose in accordance with Subsection 202-3.05, Removal of Pavement, Sidewalks and Curbs.

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.  (03/14/02)R23M98

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  Compact embankment material designated as “Foundation Fill” on the Plans to not less than 98% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5. (03/14/02)R193M98

Add the following: Compact all embankment within 15 m of the bridge abutments for Resurrection River 1, 2, and 3 full width to not less than 100 percent of the maximum density.   Compact all embankment within 6 m of the bridge abutments for Salmon, Clear, and Bear Creek full width to not less than 100 percent of the maximum density.  All material used within these zones shall be graded to pass the 75-millimeter sieve.

203-5.01 METHOD OF MEASUREMENT.  Add the following:  Ditch Line/Subgrade Blasting will not be measured.

Item 203(9B). Per each driveway obliterated and accepted by the Engineer.

203-5.01 BASIS OF PAYMENT. Add the following: Grading and placement of material used within 15 m of the bridge abutments for Resurrection River 1, 2, and 3 and within 6 m of the bridge abutments for Salmon, Clear, and Bear Creek will not be paid for directly, but is subsidiary to Item 203(6A) Borrow, Type A.  (2/1/00)R113M98

Ditch Line/Subgrade Blasting is subsidiary to Item 203(3), Unclassified Excavation.

Item 203(9B).  At the contract unit price for the number of driveways obliterated and approved by the Engineer.   Payment shall be full compensation for all materials, labor and incidentals required to obliterate the driveways identified in the Plans.

Payment shall be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 203(9B) Obliteration of Driveway | Each |

SECTION 205

EXCAVATION, BACKFILL AND FOUNDATION

FILL FOR STRUCTURES

# Special Provisions

205-3.01 EXCAVATION. Add the following:

4.	Removal of Abandoned Subgrade.  Remove all existing subgrade material between the abutments of the Resurrection River Bridge No. 2 (Bridge No. 597) down to the elevation shown on the Plans.

205-3.03 BACKFILL. Add the following: All backfill placed within 0.3 m of a structural unit shall be graded to pass the 75 mm sieve.  Grade embankment such that the slopes do not exceed 1V:2H on the Clear Creek bridge approaches being widened for the pathway.

205-5.01 BASIS OF PAYMENT. Add the following: Grading and placement of material used within 0.3 m of structural units will be subsidiary to Item 203(6A) Borrow, Type A.  (7/24/95)R154M

Add the following:  Excavation done within the limits of riprap placement will be paid for under Section 611.

Add the following Section:	SECTION 240

RAILROAD

240-1.01 GENERAL.  You are responsible for all railroad trackwork and construction items associated with this project to the limits shown.  Construct all work on ARRC property in strict accordance with the requirements contained in Section 107-1.08 RAILWAY PROVISIONS of these specifications.  Unless otherwise specified, all track materials and work methods shall comply with the applicable standards contained herein.

240-1.02 SUMMARY OF WORK.  The work involved in this project consists of, but is not necessarily limited to, the following activities:

1.	Remove existing track to the excavation limits shown.

2.	Install new track as specified on the Plans for the trackwork area.

3.	Surface main line tracks and raise to design line and grade.

4.	Install temporary and permanent grade crossings.

240-1.03 DEFINITIONS.

- ARRC. Alaska Railroad Corporation.

- AREA and AREMA.  American Railway Engineering Association and its successor organization, American Railway Engineering and  Maintenance-of-way Association.

- W.C.L.I.B. West Coast Lumberman’s Inspection Bureau.

- FRA.  Federal Railroad Administration.

240-1.04 REFERENCED STANDARDS.

- ARRC  Standard Plans, Ballast and Trackwork.

- AREA/AREMA Manual for Railway Engineering–Fixed Properties.

- AREA/AREMA Portfolio of Trackwork Plans.

All standards listed in each section of these specifications, but referenced thereafter by a basic designation only i.e. AREA/AREMA, form a part of the specifications to the extent indicated by the reference.  The most recent edition of the standard at the time of advertising shall apply.

240-1.05 REFERENCED DRAWINGS.  Alaska Rail Road Standard Drawings shown sheet A1 of the Plans.

240-1.06 STORAGE.  The Engineer shall designate areas for storage facilities.

240-1.07 CLEAN-UP.  Clean up and leave the job site in a neat condition at the end of each days work shift.  Clean the entire work area to the satisfaction  of the Engineer before calling for a final inspection.

240-1.08 SURVEYING  Furnish all surveying work necessary for the performance of this project.

240-1.09 OWNERSHIP  All tracks and crossing materials replaced by new materials will become your property.

Add the following Section:

SECTION 241

RAILROAD BALLAST

241-1.01 DESCRIPTION. This work shall consist of furnishing, placing, tamping and shaping railroad ballast and surfacing and lining new and existing track and turnout, in conformance with the lines, grades and thickness’ shown on the Plans.

241-2.01   MATERIALS.  Subballast shall consist of material meeting the minimum requirements of Section 301, Aggregate Base Course, Type C-1.  Prepared ballast shall be crushed shot rock or crushed pit-run rock, size no. 4A, composed of hard, strong and durable particles, free from injurious amounts of deleterious substances and conforming to the following test standards:

TEST	TEST PROCEDURE	TEST STANDARD

Gradation Tests:

Sampling Aggregates	ASTM D 75

ASTM C 702

Sieves with Square Openings	ASTM E 11

Sieve Analysis	ASTM C 136	See table below

Materials Finer Than No. 200	ASTM C 117	See table below

Material Quality Tests:

Bulk Specific Gravity	ASTM C 127	 2.60 min.

Absorption	ASTM C 127	0.5% max.

Magnesium Sulfate Soundness	ASTM C 88

(Five Cycles)	1.0% max.

Clay Lumps & Friable Particles	ASTM C 142	0.5% max.

Flat and/or Elongated Particles	USACE CRD-C119	5.0% max.

Degradation (LA Abrasion)	ASTM C 535	 35% max.

Mill Abrasion	see description below	   9% max.

Abrasion Number	see description below	    55 max.

Fractured Particles	see description below	 80% min.

TYPE 4A

BALLAST GRADATIONS

| Sieve Size | ### Percent Passing |
| --- | --- |
| 63 mm (2-1/2") | 100 |
| 50 mm (2") | 90-100 |
| 37.5 mm (1-1/2") | 60-95 |
| 25 mm (1") | 10-35 |
| 19 mm (3/4") | 0-10 |
| 9.5 mm (3/8") | 0-3 |
| 0.075 mm (No. 200) | 0-0.3 |

MILL ABRASION TEST DESCRIPTION

A representative sample is obtained and sized using the current ASTM Methods of Test.  From the coarse aggregate, split a representative portion into a sample consisting of 1.5 kg (3.3 lb.) passing the 37.5 mm (1-1/2”) sieve and retained on the 25 mm (1”) sieve plus 1.5 kg (3.3 lb.) passing the 25 mm (1”) sieve and retained on the 19 mm (3/4”) sieve.  The sample shall be washed and oven dried in accordance with the Los Angeles abrasion procedure.  The sample will then be placed in a 3.79 liter (1 gallon) 229 mm (9”) external diameter porcelain ball mill pot, along with 2.99 kg (6.6 lb.) of distilled water.  The mill shall be rotated at 33 rpm for a total of 10,000 revolutions (five hours).  The sample shall then be wash-sieved through a 0.075 mm (No. 200) sieve and oven dried before weighing.  Mill abrasion shall be calculated as a percentage loss in weight by the following formula:

Mill Abrasion = (Loss in Weight / Original Weight) x 100

ABRASION NUMBER

The Abrasion Number is a number calculated with the results of the Los Angeles Abrasion Test and the Mill Abrasion Test given in this specification.  The Abrasion Number shall be calculated by the following formula:

Abrasion Number = LA Abrasion Number + (5 x Mill Abrasion Number)

#### FRACTURED PARTICLES TEST

A representative sample is obtained and sized using current ASTM methods of Test. From each coarse aggregate fraction representing five percent or more of the submitted sample, split a representative portion into samples of within 10 percent of the weight specified below:

| Sieve Passing | Sieve Retaining | Mass in Kilograms (Lbs.) +/- 10 percent |
| --- | --- | --- |
| 63 mm (2 ½") | 50 mm (2") | 5.90 (13.00) |
| 50 mm (2") | 37.5 mm (1 ½") | 5.31 (11.70) |
| 37.5 mm (1 ½") | 25 mm (1") | 2.06 (4.55) |
| 25 mm (1") | 19 mm (3/4") | 0.59 (1.30) |
| 19 mm (3/4") | 12.5 mm (½") | 0.18 (0.39) |
| 9.5 mm (3/8") | 4.75 mm (No. 4) | 0.06 (0.13) |

Each sample shall then be separated into fractured and non-fractured particles according to the following criteria:

A fractured particle shall be a particle with three or more fractured faces.  Each of the fractured faces on the fractured particle must have a freshly exposed rock surface with a maximum dimension of at least one third the maximum particle dimension and a minimum dimension of at least one quarter of the maximum particle dimension.  The included angle formed by the intersection of the average planes of adjoining fractured faces must be less than 135 degrees for each of the faces to be considered as separate fractured faces.

For example, a particle just retained on the 50 mm (2”) screen (i.e. particle size = 50 mm (2”)) must have at a minimum:

1.	a freshly exposed maximum face of between 17 mm (2/3”) and 50 mm (2”) and

2.	a second freshly exposed face with a minimum dimension of 12.5 mm (1/2”), and

3.	a third freshly exposed face ranging in dimension between the other two.

The angle formed between any two of these faces must not exceed 135 degrees.

Particles which do not meet the above criterion will be classified as non fractured faces.

The fractured particles for each sample will be calculated as a percentage by the following formula:

Fractured Particles = Weight of fractured particles x 100

Original Weight

You shall engage the service of a qualified Professional Engineer registered in the State of Alaska to oversee performance of the referenced test in the rock source and the processed ballast. All sampling and testing shall be done either by the Professional Engineer himself or by a qualified and experienced technician working under the direction of the Professional Engineer. The person sampling and testing must be WAQTC certified.  Samples of processed ballast shall be taken directly off the belt to minimize segregation and contamination. Material quality tests shall be done by a testing laboratory selected by you and approved by the ARRC.

The frequency of tests shall be as follows:

1.	Pre-Manufacturing Tests: Prior to production of ballast, submit whole and crushed samples of the proposed source rock along with test reports that verify that they conform to the Specifications.

2.	Start-up Manufacturing Test: When ballast manufacturing begins another full battery of tests shall be run to verify that the ballast manufactured conforms to the specifications.

3.	Periodic Full Testing: Whenever the nature of the source rock changes significantly, such that conformance with  specifications is in doubt, above tests shall be redone as appropriate to verify conformance and the results submitted for approval.

4.	Periodic Gradation Testing: The gradation tests and visual monitoring of degree of fracture shall be performed during manufacturing on every 750 m3 (1,000 CY) of ballast that is produced, but at least daily. A complete fractured particle test shall be run on every 3,750 m3 (5,000 CY) of ballast manufactured.

All test reports shall be submitted to the State for approval. The Professional Engineer shall verify that all test reports are accurate and shall indicate whether or not they conform to these specifications. Any tests that fail to conform shall be brought to the immediate attention of the State's Project Engineer and immediate steps shall be taken to bring manufacturing into conformance.

#### CONSTRUCTION REQUIREMENTS

241-3.01   GENERAL. Manufacture, handle, stockpile and deliver the ballast in such a manner that it is kept clean and free from segregation.  Stockpiling ballast over firm stable base areas.  Stockpile ballast in horizontal layers to minimize segregation.  Do not dump over the sides of the stockpile.  Keep construction machinery and other vehicles from traveling over the top of the stockpile as much as possible.  Keep ballast dumped on subgrade prior to track or turnout construction free from material tracked in by construction equipment.  Uniformly distribute ballast dumped on skeleton track and turnouts during the dumping operation to minimize the carrying or regulating required to provide the designed ballast section.

241-3.02   BALLAST HANDLING.  Keep ballast clean and free from segregation during handling and placing operations.  Submit your plan for handling and placing ballast.  This plan shall include the following:

- source,

- type of equipment to be used,

- location of stockpiles,

- method of distribution.

241-3.03  PLACEMENT OF INITIAL BALLAST.  At your option, an initial layer, or layers, of ballast may be uniformly distributed over the finished sub-ballast and compacted before tie distribution. Limit the initial layer of ballast to a total compacted depth that will establish the track surface at least 50 mm (2”) below final grade. Subgrade fouled or disturbed by your operations shall be repaired by you at no additional cost to State.

- 1.	Each lift of ballast within the initial layers shall be uniformly spread and compacted with not less than two passes of a vibratory compactor with the following characteristics:

- Gross mass (weight)		2,268 kg (5,000 lbs.) minimum

- Drum width			1,448 mm (57”) minimum

- Drum diameter		1,016 mm (40”) minimum

Each compacted lift within the initial layers shall not exceed a depth of 100 mm (4”).

2.	The vibratory compactor shall be capable of applying a dynamic load of not less than 80 kN (18,000 lbs.) at a frequency between 1,100 to 2,000 vibrations per minute. The compacting equipment you select is subject to inspection and acceptance by the Engineer.

241-3.04   SURFACING OF TRACK.  Place the ballast within the limits shown on the Plans with equipment that will not damage the cross ties or the spiking and anchoring holding capacity.

1.	Use vibratory squeeze-type tampers to compact the ballast after final vertical track alignment has been achieved.  Maintain tools to the manufacturer's specifications.  Pack ballast tightly under and around the tie from a point 450 mm (18”) inside each rail on both sides of the tie to the ends of the tie.  Do not compact ballast around the center of the tie between the above limits.

2.	Prepare a detailed tamping procedure specification covering tamping equipment methods for the Engineer's review and approval. The specification shall include a complete description of equipment to be used and variables that can be adjusted such as:

- Number of insertions of tamping tools per tie.

- Number of passes of tamping machine.

- Depth of penetration.

After tamping is complete, regulate ballast to the design section and remove all ballast from the top of cross ties, tie plates and base of rail.  Prepare a detailed raising, aligning, tamping and regulating procedure for the Engineer's review and approval.

241-4.01  METHOD OF MEASUREMENT. Subballast and ballast required to install the modular crossing will not be measured.

241-5.01  BASIS OF PAYMENT.  Subballast and ballast required to install the modular crossing is subsidiary to Item 245(1) and no separate payment shall be made.

# SECTION 242

# TRACKWORK

242-1.01   DESCRIPTION.   This work consists of furnishing and constructing skeleton track to the alignment and limits shown on the Plans.  This work will also include removal of existing track and crossing materials at the proposed road crossings.

242-2.01   MATERIALS.   Purchase and deliver all track material to construct skeleton track. The material shall conform to the current AREA/AREMA "Manual for Railway Engineering" and as detailed in this specification.

1.	New Standard Carbon Rail: Rail shall be 115# RE Rail Section and conform to the latest revision of the AREA/AREMA Manual, Chapter 4, Rail Specifications for steel rail and the ARRC Standard Plan 3.1. Rail shall be drilled at both ends. Rail shall be end hardened, 24.4 m (80’) in length per AREA/AREMA Chapter 4, paragraph 2.1.11.

2.	New High Strength Rail: Rail shall be 115# RE Rail Section and have a Brinell Hardness range of 341-388. Rail may be either head hardened or fully heat treated and conform to the latest revision of the AREA/AREMA Manual, Chapter 4, Rail Specifications for steel rail and the ARRC Standard Plan 3.1. Rail shall be drilled at both ends for 6-hole joint bars. Rail shall be 24.4 m (80’) in length per AREA/AREMA Chapter 4, paragraph 2.1.11.

3.	Track Spikes: Use Pandrol screws or approved screws.

4.	Rail Anchors: Use Pandrol clips or approved rail anchors.

5.	Tie Plates: Use Pandrol plates or approved plates.

6.	Angle Joint Bars: Angle joint bars shall be new 900 mm (36") headfree, standard toeless, 6 holes for 115# rail with hole spacing to fit rail drilling per ARRC plan 5.12. Joint bars shall be quenched or medium carbon steel, rolled steel only, heat #16. Hole diameter shall be 31.75 mm (1-1/4").

7.	Track Bolts, Nuts & Washers: Bolts and nuts shall be new and manufactured in accordance with AREA/AREMA Section 4.1.15. Bolts shall be of the appropriate size for the bolt hole of the rail and bar and sufficient length for a full nut, lockwasher and 1 ½ threads exposed after tightening, but not to exceed a 25 mm (1") exposure after tightening. Lockwashers shall be new per ARRC Plan No. 7 and sized for the bolt diameter.

8.	Cross Ties: Cross ties shall be treated 175 mm x 225 mm x 2.59 m (7” x 9” x 8’-6”) per ARRC Standard Plan 1.13.  Cross ties shall be manufactured in accordance with AREA/AREMA Manual for Railway Engineering, Chapter 3; W.C.L.I.B. Grading Rules #17, paragraph 192b; and this specification.  Hardwood ties shall be used.

- Timber: Cross ties shall be sawn from sound, straight live timber, free from any defect that might impair durability and/or strength. Multiples or combinations will not be accepted. Cross ties shall be cut square at the ends and have all bark that impairs treatablility entirely removed.

b.	Stump Pull: Stump pulls will be graded the same as holes or splits in the end of a tie. Cross ties with a stump pull that goes into the interior more than 127 mm (5") will be rejected.

c.	Wane: Cross ties shall have a minimum 203 mm (8 in.) face. Minimum face specifications apply to the entire length of the cross tie. All wane shall be free of bark.

d.	Knots: A knot exceeding in diameter 1/4 of the width of the surface on which it appears will be rejected if it occurs in the rail bearing area. Outside the rail bearing area, knots will be accepted up to a diameter of 1/3 of the surface on which they appear. A cluster of knots will be judged as being a large knot in damaging effect. Rail bearing area shall be defined as 508 mm (20") to 1,016 mm (40") from center of tie.

e.	Cross Grain: Any cross tie with cross grain exceeding one in fifteen will be rejected.

f.	Straightness: A cross tie will be considered straight when (1) a straight line along the top from middle of one end to middle of the other end is not closer than 76 mm (3") from either side of tie, and (2) when a straight line along a side from middle on one end to the middle of the other end is everywhere more than 63.5 mm (2 ½") from top or bottom of the tie.

g.	Bark: Any cross tie containing more than a minimal amount of ingrown bark will be rejected.

h.	Saw Kerf: A saw kerf is not required.

i.	Mill of Manufacture Certification: A mill certification is required indicating that inspections have been performed and that the product is in conformance with specifications. The mill certification must also indicate the species of wood. All ties which pass the inspection will be clearly marked and identified as ARRC ties; unmarked ties will not be accepted.

j.	Treatment: All treatment shall meet the specifications of the American Wood Preservers Association Standards Book C6 and the following guidelines. A treatment report shall be accurately completed for all charges and at a minimum shall contain the following:

i 	Charge number

ii	Date

iii	Wood species and size

iv	Total retort time in hours

v	Conditioning time in hours

vi	Pressing time in hours

vii	Retention in kg per cubic meter

viii	Average penetration to be shown for oak

ix	Initial air time, if applicable

x	Gauge readings and times

xi	Treating operator's signature

xii	Seasoned condition (dry or green), if green show moisture content.

xiii	Final Vacuum

xiv	Wright of solution at 38° C (100° F)

xv	Work tank number and cylinder number

The preservative shall consist of a mixture of 50 percent by volume of creosote oil and 50 percent by volume of residuum oil, 50/50 coal tar

solution may also be used. Final readings shall be entered on the treating report. Treating reports and charts shall become a permanent record maintained by the treating company with open access to ARRC personnel.

- Care of Treated Wood: Extreme care shall be used in handling treated cross ties to avoid damage to the edges of the timbers or breaking through the treated portions and exposing untreated wood. The use of peavies, cant hooks, pickaroons, long hooks or pointed tools shall be such as not to break through the treated portion of the wood. If damage during handling which could potentially impair the longevity of material service life, this material shall then be retreated at the vendor's expense. All cost associated with retreatment, including oil, shall be the responsibility of the vendor.

l.	Boring: All cross ties shall be bored and adzed in conformance to the ARRC Standard Tie Boring and Adzing Plan 1.13. Adzing may be deleted if vendor will certify that ties furnished will be flat and provide a uniform bearing surface for the tie plates.

m.	Anti-splitting Devices: All hardwood cross ties shall have steel multi-nail anti-splitting end plates in accordance with AREA/AREMA Manual of Railway Engineering, Chapter 3, Section 1.8 titled "Ties and Wood Preservation", Section 1.9.2.3 titled "Nail Plates", and Section 1.10.3 titled "Nail Plates".

n.	Species:   Acceptable hardwood species are Red Oak, White Oak, Hickory, Black Walnut, Gum, Beech, Ash, White Heart Sycamore, Hackberry and Hard Maple.

242-3.01   CONSTRUCTION REQUIREMENTS.   Perform track construction in accordance with the ARRC Standards, AREA/AREMA Manual for Railway Engineering and as specified herein.  The scope of construction includes, but is not limited to, unloading and distribution of track material, distribution and spacing of cross ties, laying, bolting and spiking rail, field welding of joint rail, placing rail anchors, raising, aligning and tamping track, and shaping ballast to the design section.

Employ construction procedures and methods that keep the railroad sub-ballast and ballast sections from becoming rutted or disturbed.  Immediately stop any operation that causes damage and institute alternate construction methods that do not cause damage.

All existing track material removed will become your property. Remove these materials from the ARRC right-of way.

242-3.02   TRACK ALIGNMENT AND GEOMETRY.   Construct the track to the alignment and profile indicated, or as adjusted by the Engineer, within the tolerances specified. Designate right or left rail, while facing in the direction of increasing stationing, to control the grade of all tangent tracks on a contract-wide basis.  Use profile grade rail for low rail on curves.  Use line rail on high rail on curves.

Maintain track centers between main line and future mainline at 4.572 m (15’-0”) within the project area.

242-3.03   TOLERANCES.   Deviations from indicated gauge, cross level, horizontal line, profile grade, and tie spacing shall conform to the following requirements:

1.	Gage: Shall be 1,435 mm (4’-8 ½”) plus or minus 3 mm (1/8”).

2.	Cross Level and Superelevation: Shall be plus or minus 3 mm (1/8”) from level on tangent or design superelevation on curve.

3.	Deviation from Horizontal Alignment: Plus or minus 6 mm (¼”) in a 19 m (62’) chord. Plus or minus 13 mm (½”) total except in road crossings where total deviation shall be plus or minus 6 mm (¼”).

4.	Deviation from Profile Grade: Shall not exceed plus or minus 6 mm (¼”) in 19 m (62’) chord or a total of plus or minus 13 mm (½”).

5.	Tie Spacing: Distance between centerline on adjacent ties shall be 495 mm (19 ½”) and not vary more than plus or minus 25 mm (1”) from the indicated spacing, with the additional requirements that 48 ties shall be installed per 23.8 m (78’) of track.

242-3.04   CROSS TIE DISTRIBUTION.   After receiving the cross ties from the supplier, transport them to the work area in accordance with the AREA/AREMA "Handling of Ties from the Tree into the Track".   Place ties on a smooth, compacted surface as specified herein, space as shown within the specified tolerances, and lay them normal to the centerline of track with heartwood face down. Line the ends of ties uniformly on the right side of track when facing increased stationing.

242-3.05  TIE PLATES AND SCREWS.  Attach tie plates to the cross ties with line and hold-down screws to the indicated patterns. You may pre-plate cross ties prior to distribution. If you choose to pre-plate the cross ties, furnish any additional material required at no added cost to Owner. Use a jig to compensate for fabrication tolerances to achieve track gage tolerances.

242-3.06  RAIL LAYING   Use standard carbon rail on all tangent track and curves up to four degrees. Use high strength rail on curved track over four degrees and through the crossings.  Lay rail in accordance with the details and the following procedures:

1.	Rail Distribution; Distribute rails along the roadbed with the head of the rail up and in such a manner that will prevent damage to them.  Do not drop rails from the sides of railcars or trucks.

2.	Rail Laying: Clean the base of the rail and surface of the tie and tie plate prior to laying.  Lay the rails one at a time without bumping or striking. Bring rail ends squarely together against the expansion shims and bolt completely before spiking.  Lay rails so that the joints in opposite rails are staggered not less than 6 m (20’) apart, plus or minus 610 mm (24”) with the following exception.  Closer joints may be required at turnouts or roadway crossings. Use less than standard length rails to space the joints on curves.  Do not use rails shorter than 4.6 m (15’). Lay or weld rail so that no joints are in grade crossings.

3.	Rail Cutting and Drilling: Cut rails square and clean using rail saws. Use an exact template for precisely marking, center punching and drilling holes for complete bolting of cut rail.  Do not mark or drill through joint bars. Debur all holes. Do not drill new holes between two previously drilled holes.  Do not burn or cut rails or bolt holes by means of an acetylene torch. Bevel and harden all cut rail ends at the head to conform to AREA/AREMA "Manual Specifications for Steel Rails", Supplementary Requirement S1.

4.	Rail Joints: Wire bush the fishing surface of the rails and joint-bars to remove rust before assembly. Use expansion shims between the ends of adjacent rails to allow for rail expansion. Use the following table to determine the proper expansion allowance.  Refer to AREMA chapter 5, paragraph 5.3.1 for shim thickness to use for 12 m (39’) rail.

| Rail Temperature °C (°F) | Shim Thickness in mm (inches) for 23.8 m-24.4 m (78’- 80’) rail |
| --- | --- |
| Below 2 (35) | 8 (5/16) |
| 2 to 8 (35-47) | 6.4 (1/4) |
| 9 to 15 (48-60) | 4.8 (3/16) |
| 16 to23 (61-73) | 3.2 (1/8) |
| 24 to 30 (74-85) | 1.6 (1/16) |
| Over 30 (Over 85) | None |

Use proportionate shim thickness for shorter lengths of rail.  Determine the temperature of the rails by the use of an AREA standard rail thermometer, placed on the base of the rails close to the web on the side shaded from the sun. Allow sufficient time to accurately record the temperature. Take care to assure that shims are not squeezed or damaged during installation of shims or rails. Remove shims from between rail ends as soon as the bolts have been tightened and the rail anchors applied. Install all track bolts when the rail is laid and tightened before spiking.

Tighten to a “final bolt tension” of 89 to 133 kN (20,000 and 30,000 lbs.).  Tighten the bolts once, at the time of rail installation. Check and adjust the final tension just prior to final acceptance per AREMA chapter 5, paragraph 5.5.2.

5.	Rail Anchoring: Use Pandrol clips or approved rail anchors.

242-4.01 METHOD OF MEASUREMENT. Railroad Trackwork will not be measured.

Trackwork Removal will not be measured.

242-5.01 BASIS OF PAYMENT. If you call for flagmen and, through no fault of the Department or the Railroad, the flagmen are not needed, payment shall be deducted from monies due you. Other flagging, required by your operation, shall be paid for by you.

All traffic control measures required will be paid for separately under their respective pay items.

Trackwork will not be paid for separately but will be subsidiary to Item 245(1).

All required grading and shaping of existing track embankment shall be subsidiary to Item 245(1).

Delete Section 617 in its entirety and add the following Section:

### SECTION 245

# GRADE CROSSINGS

245-1.01  DESCRIPTION. This work consists of furnishing and constructing a concrete modular crossing to the alignment and location shown on the Plans.  Installation of the modular crossing to the design grade lines will require the removal of existing main line to permit excavation of unsuitable subgrade and ballast and complete tie renewal within the limits shown.  Perform all trackwork associated with the crossing replacement. All trackwork shall be in accordance with Section 242 of the specifications and shall be scheduled with the ARRC through the Engineer.  No portion of the existing track structure shall be removed prior to the approval of the Engineer which must be requested in writing 7 calendar days in advance of the work.

245-2.01  MATERIALS. Furnish and deliver all new material required to construct the grade crossings. The material shall conform to the current AREA/AREMA specifications and as detailed in this specification.  All standard track material shall conform to Section 242 of these specifications.

- Modular Crossing Panels:  Crossing panels shall be modular reinforced concrete panels specifically designed for railroad crossing applications.  The particular manufacturer shall be regularly engaged in the fabrication of railroad crossing materials and the product must be approved, in writing, by the Engineer.  Panels will be screwed to the ties with ARRC approved lag screws.  Manufacturers of reinforced concrete modular panels shall be one of the following or approved equal:

Century Concrete Crossings		800-527-5232

Omni Grade Crossing Systems		800-203-8034

American Concrete Products Co.		402-331-5775

KSA					412-227-2396

Premier Concrete RR Crossings		800-425-5556

Omega Industries, Inc.			360-694-3221

Magnum Manufacturing Corp.		801-785-9700

Submit the manufacturer’s specifications for reinforced concrete crossing panels to the Engineer for approval.

- Cross Ties:  Cross ties shall be new hardwood as specified in Section 242 except length shall be adjusted to meet installation requirements of modular crossing manufacturer.

- Geotextile Fabric:  Geotextile fabric shall be non woven fabric meeting the requirements of AREMA Chapter 1 and shall be heavy class.  Fabric specifications and sample shall be submitted for review prior to purchase and installation.

- Ballast:  Construction and placement of ballast shall conform to Section 241 of these specifications.

- Sub-ballast:  Construction and placement of sub-ballast shall conform to Section 241 of these specifications.

##### CONSTRUCTION REQUIREMENTS

245-3.01  GENERAL. Perform grade crossing construction in accordance with ARRC standards, AREA/AREMA Manual Part 8 and as specified in this document.  The scope of construction includes but is not limited to, unloading and distribution of crossing materials and installation on prepared subgrade and sub-ballast sections.

# The ARRC track at the Nash Road crossing can be closed for construction as follows:

1) 	Closure will be scheduled in late September or October for a period not to exceed 36 hours.  A closure may be accommodated during another time period, if agreed upon and coordinated with the ARRC’s Chief Engineer.

2) 	Start of the closure will depend on arrival and departure of the last train through the Nash Road area for that day.  When the last train goes over the crossing, the closure will begin.

3) 	The ARRC can reasonably project these train operations 48 hours in advance.

4) 	If train schedules do not permit the start of a closure, then the closure will be delayed to the following week.  You will be expected to be ready for the closure.  The crossing reconstruction must be substantially completed in one closure.

Subsequent closures of up to 8 hours will be granted around train schedules to complete the crossing.

245-3.02  EXCAVATION.  The construction of the grade crossings will require the excavation of the existing and future mainline to the bottom of unsuitable material at the locations shown in the Plans.

245-3.03 TEMPORARY CROSSING.

1.	Provide flagmen in all situations at the discretion of the ARRC when regular railroad crossing are used as haul routes inside or outside the permit area.

2.	You may install a temporary road crossing provided you acquire a temporary road crossing permit from the ARRC prior to installation.

Construct the temporary crossing to the standards specified in the temporary crossing permit.  Provide and maintain all protective signs required by the ARRC.  Provide railroad flag protection at all times in accordance with Subsection 107-1.08, Section 6 when a temporary railroad crossing is in use.  Remove the temporary crossing unless specifically allowed in the temporary crossing permit when not in use during the winter season.  Upon completion of the work, or termination of the temporary crossing permit, remove the temporary railroad crossing and restore the area to its original condition.

3.	Keep the flange ways of all road crossing used by you or subcontractors as haul routes, or temporary road crossings, free of gravel at all times.  Maintain road crossings to the satisfaction of the Railroad’s Chief Engineer.

4.	Provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing when temporary or private road crossings are not in use.

245-3.04  MODULAR CROSSINGS.  Construct modular crossings in accordance with ARRC Standards shown in standard drawing “Modular Crossing” except that the minimum excavation limits for the Nash Road crossing shall be 9.1 m (30’) from the edge of roadway pavement.  Construct all modular crossings with Pandrol Plates, Pandrol Clips and approved screws or equal.  Use geotextile fabric that conforms to Subsection 245-2.01.

Raise the Nash Road crossing 100 mm (4”) or as directed by the ARRC Chief Engineer.

245-3.05    RAIL.  Use unjointed 52 kg RE rail within the road crossing and for at least 6 m on either side of the crossing as specified in Section 242-2.01.

245-4.01   METHOD OF MEASUREMENT.

Item 245(1). Will not be measured.

245-5.01  BASIS OF PAYMENT.

Item 245(1). At the contract price of lump sum price.  Payment shall be full compensation for all labor, materials and equipment necessary to complete the required work as specified in this section.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 245(1) Modular Crossing | Lump Sum |

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1. (10/1/91)R116

Add the following after the first paragraph: At your option, recycled asphalt material (RAM) may be substituted for aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 0.300 mm | 5-34 |
| 0.150 mm | 3-22 |
| 0.075 mm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

(2/28/01)R176M98

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface. (9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(2/28/01)R176M98

SECTION 401

ASPHALT CONCRETE PAVEMENT

# Special Provisions

401-2.01  Composition Of Mixture - Job Mix Design.  Add the following to the first paragraph after ATM T-17: (version 01/93).

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

401-2.03  Asphalt Materials. Change the last sentence of the first paragraph to read: When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following.

Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

401-3.09  Preparation Of Aggregates.  In the first paragraph, delete AASHTO T-110 and substitute the following: WAQTC TM 6.

401-3.14  Joints.  Delete the last paragraph.  Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one 150 mm diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

401-3.15  Surface Tolerance.  Add the following: The Engineer will measure the smoothness of the top lift of the pavement in all of the driving lanes with an inertial profiler before final acceptance of the project.  Remove and replace or grind any portion of the pavement having a Prl greater than 230 mm/km in a 160 m segment.

Use a milling machine equipped with a triple-scroll micromill head for grinding bumps.

After completion of the corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, or within 8 m of bridge abutments or matches with existing pavement.  Smoothness will be measured in the left wheel path of each lane and reported as profilograph results (Prl) filtered with a 5 mm blanking band.  The Prl will be reported as a job average for all measured lanes, calculated to the nearest mm per km.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: All costs associated with the patching of defective areas shall be borne by you

401-4.01  Method Of Measurement.  Under Asphalt Cement, 1., add to the end of the second sentence: “... ,or WAQTC FOP for AASHTO TP 53.”

Add the following paragraph to this subsection: Longitudinal joints.  By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

401-4.02  Acceptance Sampling And Testing.  Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken from the windrow, at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC  TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.  Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.

One 150 mm diameter core is required for acceptance density testing only.  Acceptance density testing will be according to WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph, No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following: Longitudinal joint densities less than 91 percent of MSG, as defined is Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with Subsection 401-3.15 will be calculated and applied.  The adjustment shall be applied under Item 401(6), Asphalt Price Adjustment.  Calculate the smoothness price adjustment as follows:

##### SPA% • PAB • quantity

Smoothness Price Adjustment ($) = 									                                         				       100

Where;		SPA% = Smoothness Price Adjustment Percentage = 6.65 – 0.0532 • Prl

Prl = measured pavement smoothness (mm/km)

PAB = Price Adjustment Base = $41.00/Megagram

SECTION 501

STRUCTURAL CONCRETE

# Special Provisions

501-1.01 DESCRIPTION.  Add the following: This work also consists of the following:

- Drilling into portions of an existing bridge as shown on the Plans or as described in the Special Provisions.

Where portions of a bridge are to be chipped or removed, perform the chipping and removal operations without damaging any portions of the structure that are to remain in place.  Repair all damage to existing concrete, that is to remain in place, to a condition equal to that existing prior to the beginning of the chipping or removal operations.

Before beginning concrete removal operations involving the removal of a portion of a monolithic concrete element, make a saw cut approximately 25 mm deep to a true line along the limits of removal on all faces of the element that will be visible in the completed work.  Do not damage or otherwise contact longitudinal reinforcement, transverse reinforcement, or prestressing steel strands when saw cutting through reinforced and prestressed concrete members.  Field verify the locations of reinforcement prior to saw cutting.  Provide results of the field survey to the Engineer prior to saw cutting.

- Patching drilled and saw cut holes in concrete decks with concrete.

- Installing blockouts for utilities and drainage work as indicated on the Plans and as directed by the Engineer.

- Repairing delaminations in the existing concrete deck.  The delaminations are approximately 0.2 square meters in area.  Repair all delaminations as shown on the Plans and as directed by the Engineer.

- Removing existing joint material and installing a Silicone Joint Sealer across the entire expansion joint at both ends of the bridge.

501-2.01 MATERIALS.  Add the following:

| Metal Pipe | Section 707 |
| --- | --- |

Use threaded ferrule inserts that will accept an NC threaded rod and can resist a tensile load of at least 9 kN.  Furnish the threaded inserts in a stainless steel finish.  Submit complete details of the threaded inserts to be used for approval.

501-3.01 PROPORTIONING.  Under 1.  Determining Proportions and Batch Weights., delete the first sentence and substitute the following: Submit a mix design developed in accordance with ACI 211 and ACI 301, Section 4 to the Engineer for approval.  (7/6/99)R37M98

501-3.07 PLACING CONCRETE.  Add the following to item 8. Forming Construction Joints:

Only make construction joints at locations shown on the Plans, unless otherwise approved by the Engineer.

Clean all construction joints of surface laitance, curing compounds and other foreign materials before placing fresh concrete against the surface of the joint.  Clean all construction joints using abrasive blast methods to the extent that clean aggregate is exposed.  Flush all construction joints with water and allow them to dry to a surface dry condition immediately prior to placing concrete.

When existing structures are to be modified, clean and flush all construction joints between new and existing concrete as specified above.  When a roughened concrete surface is shown on the Plans, roughen the existing concrete surface to a full amplitude of approximately 6 mm by abrasive blasting or mechanical equipment.

Do not discharge pulverized concrete and waste sand from abrasive blasting into streams.  Properly dispose of the pulverized concrete and waste sand from abrasive blasting.

Drill holes in existing concrete by methods that do not shatter or damage the concrete adjacent to the holes when joining new construction to existing concrete by means of reinforcing steel dowels bonded by an epoxy cartridge system.

Concrete drilling consists of drilling holes of various diameters through reinforced and prestressed concrete bridge members, as shown on the Plans and in conformance with the requirements in these Special Provisions.

Do not damage or otherwise contact longitudinal reinforcement, transverse reinforcement, or prestressing steel strands when drilling through reinforced and prestressed concrete members.  Field verify the locations of reinforcement prior to drilling holes.  Provide results of the field survey to the Engineer prior to drilling holes.

Holes in which longitudinal or transverse reinforcement is encountered during drilling before the specified depth is attained shall be rejected.  Drill a new hole, which does not strike reinforcement, adjacent to the rejected hole to the depth shown on the Plans.  With the approval of the Engineer, holes may be cored through reinforcing steel to the correct depth.  Fill all rejected holes with grout.

Do not core holes in the decks of precast, prestressed girders.

Place the bonding material and anchor bolts into clean and dry holes.

Use an epoxy cartridge system that consists of the following:

1.  	A two-component epoxy bonding material that is contained in a cartridge having two separate chambers

2. 	An applicator that is a special dispensing gun having a replaceable static mixing nozzle.

Use an epoxy cartridge system appropriate for the service temperature and ambient concrete temperature at the time of installation.

Epoxy cartridge systems are subject to the approval of the Engineer.  Use epoxy cartridge systems that meet the requirements of the Acceptance Criteria for Adhesive Anchors in Concrete and Masonry Elements, AC58, dated July 2000, by the ICBO Evaluation Service, Inc.  Meet the suitability requirements for creep, in-service temperature, dampness, freezing and thawing, and seismic qualification of these acceptance criteria.  Approval of epoxy cartridge systems is contingent upon you submitting to the Engineer one sample of each type of epoxy cartridge system, manufacturer's installation instructions, and certified results of tests, either by a private testing laboratory or the manufacturer, indicating compliance with the above requirements.

The following products have been found to substantially meet these requirements and are conditionally approved for use on this project

| Conditionally Acceptable Manufacturer | Model of Epoxy Cartridge System | Manufacturer’s Phone Number |
| --- | --- | --- |
| Simpson Strong - Tie | SET Models SET22 and SET56 (Model # designates volume of cartridge in fluid ounces) | 1-510-460-9912 1-630-543-2797 |
| Covert Operations | CIA Gel 7000 | 1-800-827-7229 |
| Adhesive Technology (Division of US Anchor Corp.) | Anchor-it HS-200 | 1-800-262-4748 |
| ITW Ramset / Redhead | Epcon Ceramic 6 | 1-800-368-9724 |
| Hilti | HSE 2421 | 1-907-344-8351 |

Do not use the above conditionally approved products when:

- Temperature of concrete exceeds 40° C.

- There is a likelihood of fire.

- Coated bars, rods or bolts are specified unless the embedment depth is increased by 50%.

- The concrete temperature is below 5° C.

Provide epoxy cartridges that are clearly and permanently marked with the manufacturer's name, model number of epoxy cartridge system, manufacturing date, and lot number.  Provide the manufacturer's recommended installation procedures, minimum cure time, and such warning or precautions concerning the contents as may be required by State or Federal Laws and Regulations for each carton of epoxy cartridges.

Provide a Certificate of Compliance as provided in Section 106-1.05, "Certification of Compliance," of the Standard Specifications with each shipment of the epoxy cartridge system, regardless of which epoxy product is furnished.  Provide certificates which state that the material complies with the Specifications and with the data submitted in obtaining acceptance.

Drill holes to the diameters and depths as recommended by the manufacturer and sufficient to develop the ultimate strength of the steel dowel.

After bonding, support all dowels as necessary to prevent movement during curing.  Do not disturb the dowels until the epoxy has cured the minimum time specified by the manufacturer.  Dowels that are improperly bonded, as determined by the Engineer, will be rejected.  Drill new holes and place new securely bonded dowels at your expense.

Water for core drilling operations shall meet the requirements of Section 712-2.01, “Water”.  If water is to be taken from a lake, stream, or other natural water body containing fish, and the pump intake hose is less than 50 mm in diameter, immerse the intake in a 18.9 liter (5 gallon) bucket perforated with 2.38 mm (3/32”) holes.  For larger pumps, use a box with screen openings no more than 1 mm.

Do not permit unfiltered water from core drilling operations to fall on public traffic, to flow across shoulders or lanes occupied by public traffic, or to flow into gutters, other drainage facilities, or streams.  Wastewater from coring must be contained and filtered before being discharged into any stream, such that the wastewater meets the standards given in the General Permit.

501-4.01 METHOD OF MEASUREMENT. Add the following:

Item 501(7). By the square meter of area shown in the Plans for repair, completed and accepted by the Engineer.

Item 501(8). By the actual number of dowels installed, completed and accepted by the Engineer.

The following shall not be measured:

- Drains and blockouts required for drainage and utilities

- Portions of bridge to be chipped or removed

- Silicone joint sealer

- Metal service pipe placed at the abutments of Bridge No. 596, 597 and 598

501-5.01 BASIS OF PAYMENT.  Add the following:  The cost of repairing existing concrete damaged by your operation is at your expense.  Drilling or coring done by you that is not shown on the Plans shall not be paid for under this contract.

The cost of drilling new holes and placing new securely bonded dowels is at your expense if the Engineer determines that you improperly bond any dowels.

Labor, materials, and incidentals required to do the following are subsidiary to Item 501(1):

- Chipping concrete

- Drains and blockouts required for drainage and utilities

Labor, materials and incidentals required to do the following are subsidiary to Item 501(2):

:

- Installing utility hanger bracket assemblies (including threaded inserts, rods, flatbars, spacers, nuts and washers) on Clear Creek Bridge No. 599

- Silicone joint sealer

- Metal service pipe placed at the abutments of Bridge No. 596, 597 and 598

Item 501(7). At the contract unit price for the area accepted by the Engineer.  Payment shall include all materials, labor and incidentals required to complete the work as shown in the Plans and in accordance with the Specifications.

Item 501(8).  At the contract unit price for each dowel completed and accepted by the Engineer.  Payment includes all materials, labor and incidentals required to complete the work in accordance with the Plans and Specifications.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 501(7) Concrete Bridge Deck Repair | Square Meter |
| 501(8) Drill and Bond Dowels | Each |

SECTION 502

PRESTRESSED CONCRETE STRUCTURES

Standard Modifications

502-1.01 DESCRIPTION. Add the following:  This work also consists of furnishing and installing utility hanger bracket assemblies as shown in the Plans.

Note,

502-2.01 MATERIALS. In the second paragraph, delete the words “as determined by ASTM C 271”and substitute “as determined by ASTM D 3575, Suffix W, Method B”.

Special Provisions

Add the following:  Use threaded ferrule inserts that will accept an NC threaded rod and can resist a tensile load of at least 9 kN.  Furnish the threaded inserts in a stainless steel finish.  Submit complete details of the threaded inserts to be used for approval.

Standard Modifications

502-3.01 PRESTRESSING METHODS. Delete the last four paragraphs. (02/08/01)M93

502-3.06 PLACING. In the third paragraph, replace the words “place the grout” with “place grout conforming to Subsection 701-2.03 and”. (02/08/01)M 94

##### Special Provisions

502-4.01 METHOD OF MEASUREMENT.  Add the following:  No measurement shall be made for furnishing and installing utility hanger bracket assemblies (including threaded inserts, rods, flatbars, spacers, nuts and washers).

502-5.01 BASIS OF PAYMENT. Add the following:  Furnishing and installing utility hanger bracket assemblies (including threaded inserts, rods, flatbars, spacers, nuts and washers) are subsidiary to Items 502(1A) through 502(1D).

- SECTION 503

- REINFORCING STEEL

- Special Provisions

- 503-3.05 SPLICING.  Add the following to the first paragraph:  Unless otherwise shown on the Plans, do not lap splice more than 50% of the bars at one section.  Do not lap splice two adjacent bars at one section.  Stagger adjacent lap splices no less than 100% of the required lap splice length.

- Add the following to the second paragraph:  Use welded splices of reinforcing bars only if detailed in the Plans or if authorized by the Engineer in writing.

- Add the following:  Where shown on the Plans or otherwise approved by the Engineer, splice bars using mechanical bar couplers capable of resisting at least 125% of the specified yield strength of the bar in tension and compression.  Do not splice two adjacent bars at one section.  Unless shown otherwise on the Plans, stagger mechanical splices in adjacent bars at least 760 mm.  Submit complete details of the method, materials, and equipment to be used during the mechanical splicing to the Engineer for approval.  Submit laboratory tests results that verify the required splicing system properties.

- Use mechanical end anchorages that conform to ASTM A 970M where shown on the Plans or approved by the Engineer.

- SECTION 504

- STEEL STRUCTURES

## Special Provisions

504-3.02 ERECTION. Delete the second paragraph of Item 4. Method and Equipment and substitute the following:

Follow handling and erection procedures so as to avoid inducing critical buckling stresses in the girder flanges, webs and other components.

504-4.01 METHOD OF MEASUREMENT.

Under Item 2, “Kilogram,” change lettered sub-item designations “4, d, and e” to “d, e, and f” respectively.

(3/31/00)R253M98

SECTION 505

PILING

##### Special Provisions

505-1.01  DESCRIPTION.  Add the following:  The Engineer shall perform high-strain dynamic testing on the steel pipe pile at one pier, and optionally at an abutment, on each of the three Resurrection River Bridges, Bridge Number 596, 597 and 598. After performing the test pile program as described below, the Engineer shall establish the installation and construction control criteria for Bridge Number 596, 597 and 598 which shall then be applied to the service piles. Drive all test piles, and service piles, for Bridge Number 596, 597, 598, 599, 600 and 601 to at least the minimum tip elevations shown on the Plans.

There will be no high-strain dynamic testing performed on the piles for Clear Creek, Bridge Number 599, Salmon Creek, Bridge Number 600 and Bear Creek, Bridge Number 601.

Item 505(5) shall include any excavation or backfill within the steel pipe pile shell required before filling the shell with concrete to the elevations shown on the Plans.  Item 505(5) shall not include any work required to install reinforcing steel or place concrete in the steel pile shell.

Practical refusal is defined as Pile Refusal in Section 505-4.01, numbered paragraph 8 of these Special Provisions.

505-3.01  TEST PILES.  Add the following:  There shall be high-strain dynamic testing performed on piles at Bridge Number 596, 597 and 598. Drive a test pile at Pier 2 of each bridge, and if required by the Engineer, drive a test pile at an abutment.  Dynamic measurements will be taken by the Engineer during the driving and re-strike testing of the test piles.

Resurrection River Bridges (Br. No. 596, 597 and 598)

Test Site	Test Pile Type	Requirements

Abutment 1or 3               	Plumb	Pile test may be required

Pier 2	Plumb	 Pile test is required

The initial pile driven at each test location shall be a test pile.  If the immediate results from the high strain dynamic testing on the test pile are acceptable to the Engineer, you may drive the remaining piles in that foundation unit. Further dynamic pile tests may be required on other piles or at other test sites if in the opinion of the Engineer, performance of the hammer-pile-soil system changes from that of the test pile program.  For the dynamic testing of the piles, provide the Engineer reasonable and safe means of access to the test piles for attaching instruments after the pile is placed in the leads.  It is estimated that the Engineer will need approximately 4 (four) hours maximum to set up and install the dynamic test equipment.  The Engineer will furnish the equipment, materials, and labor necessary for drilling holes in the test piles for mounting the testing instruments.  The testing instruments will be attached near the top of the pile with bolts placed through drilled and threaded holes.

If necessary, you shall furnish electric power for the setup and use of the high-strain dynamic test equipment.  The power supply at the outlet shall be at least 10 amps, 115 volt, 55-60 cycles, AC only.  Delays resulting from installation of the high-strain testing equipment shall not be a basis for a claim.

The test piles shall remain as part of the permanent structure after testing, analysis, and recommendations are completed.

The test pile program with high-strain dynamic testing shall consist of the following tasks:

- Submit the necessary pile driving equipment information as shown on the Pile Driving Equipment Data Form to the Engineer for the test pile program at least 28 calendar days prior to driving the first test pile.  The Engineer will provide the Pile Driving Equipment Data Form.  You shall attend a meeting with the Engineer to evaluate and discuss the pile test program at least 14 calendar days prior to driving the first test pile.  Give the Engineer at least 7 calendar days advance notice of the date a test pile will be driven.

- The Engineer shall perform an initial wave equation analysis based on subsurface conditions, pile capacity, and pile type.

- Drive the test piles as specified above and to the tip elevations shown on the Plans, and to criteria established by the initial wave equation analysis.  Dynamic pile testing will be performed for the total length of each test pile.  If an obstruction is encountered during driving of the test pile, that pile will not be considered a test pile and the next pile driven at the test site shall be designated as a test pile as directed by the Engineer.  Perform this dynamic pile testing in accordance with ASTM D 4945-96.

- The Engineer shall evaluate the test pile at each test site by re-striking the test piles a minimum of 48 hours after completion of driving the test piles to the specified tip elevation.  You shall perform the re-strike of the test piles with simultaneous testing by the Engineer using the pile dynamic analyzer.

The re-strike testing procedure shall be performed with a warmed up hammer, the energy or fuel setting adjusted to the maximum position and shall consist of striking the test pile with 60 consecutive blows or until the pile penetrates an additional 75 mm, whichever comes first.  In the event the pile movement is less than 25 mm during the re-strike, the re-strike may be terminated after 25 blows, or even fewer blows if the pile is at practical refusal.

505-3.03  PILE BEARING VALUES.  Delete this Subsection in its entirety and substitute the following:  Drive all piles to a depth at which they will satisfy the required ultimate bearing capacity. The required ultimate bearing capacity for all the piles, at all of the bridges on this project is the ultimate pile load as indicated in the Structural Foundation Engineering Report and on the bridge plans. The Engineer shall determine the pile driving criteria for the bridges on this project using a Wave Equation analysis and on Bridge Numbers 596, 597 and 598, results from the high-strain dynamic testing. Use the “GRLWEAP” Wave Equation computer program on this project using the GRLWEAP industry standard hammer input data and as required, data from the high-strain dynamic testing. Determination of the ultimate bearing capacity of production piles may include re-strike testing as described above and as directed by the Engineer.

505-3.05  MINIMUM PENETRATION.  Add the following:  Furnish piles of sufficient length to be driven to 1) the minimum tip elevation, 2) to meet the driving criteria as specified herein and 3) to provide the required cut-off elevation.  Calculate pile lengths from the design cut-off elevation to the minimum tip elevation.  You shall increase the pile lengths given to provide for fresh heading and for such additional pile lengths as may be necessary to suit their method of operation at your own expense.  The Resurrection River Bridges, Bridge Number 596, 597 and 598 sites, contains cobbles, boulders, riprap and remnants of old bridge foundations damaged in the 1964 earthquake.

    - DRIVING PILES.  Replace the third paragraph with the following:

Drive all piles as shown on the Plans or as ordered in writing.  Place exposed pile bents within 13 mm of the plan position at cut-off elevation and within 75 mm of the plan position at the original ground line elevation.  Place abutment piles within 25 mm of the plan position at the cut-off elevation.

Add the following:  All of your pile driving equipment shall be subject to approval by the Engineer.  You may use vibratory drivers for initial pile placement of the steel pipe piles.  The piles shall not penetrate more than 10 meters when a vibratory driver is used for initial pile placement.  Equip all pile driving systems with a hammer cushion of appropriate thickness to prevent damage to the hammer or pile and to provide uniform driving performance.   Use hammer cushions made of durable, manufactured materials in accordance with the hammer manufacturers guidelines.  Do not use wood, wire rope, and asbestos hammer cushions.  Inspect the hammer cushion in the presence of the Engineer prior to beginning pile driving operations and after every 100 hours of pile driving.  Replace cushions with a reduction in cushion thickness exceeding 25% of the original thickness before driving is permitted to continue.

Size the pile driving equipment such that the piles can be 1) driven to the required ultimate bearing capacity without damage to the piles, 2) have compressive driving stresses as indicated by the high-strain dynamic testing and the wave equation analysis not exceeding 90% of the pile yield stress and 3) with a penetration resistance of 120 blows per 0.305 meter or less as determined by the production driving wave equation analyses. Approval of the pile driving equipment by the Engineer will be based on the high-strain dynamic testing, the wave equation and the Engineer's recommendations.

Drive all service piles to at least the minimum tip elevation shown in the Foundation Engineering Report and the bridge plans, or to a tip elevation based on the high-strain dynamic test results and the Engineer's recommendations.  Adequate pile penetration will be considered to be obtained when the wave equation and as applicable, the specified high-strain dynamic testing criteria is achieved.  The Engineer shall establish the tip elevation for piles not achieving the required ultimate bearing capacity within these limits.

After the test piles are driven and during the service pile driving operations, you shall use the approved driving system to install the service piles.  No variations in the driving system shall be permitted without the Engineer's written approval.  Any change in the driving system will only be considered after you have submitted a revised Pile Driving Equipment Data Form for a revised wave equation analysis by the Engineer, and the analysis indicates an acceptable result.  Approval of any change in your driving system may be contingent upon obtaining satisfactory results from additional high strain dynamic tests.  You will be notified of the acceptance or rejection of the revised driving system within 7 calendar days of the Engineer's receipt of the requested change.  The time required for submission, review, and approval of a revised driving system shall not constitute the basis for a contract time extension.

The Engineer reserves the right to require dynamic monitoring in addition to those previously specified if your pile driving equipment does not show to be working properly or in accordance with these specifications, or if pile design modifications are ordered by the Engineer.  The Engineer shall perform all dynamic monitoring.  If changes in the approved driving system are requested by you, the additional high-strain dynamic testing shall be performed at your expense.

There is a possibility of encountering difficult driving conditions due to large cobbles, boulders, riprap and remnants of old bridge foundations damaged in the 1964 earthquake. Where such obstructions are encountered and result in pile refusal above the minimum pile tip elevation, removal of such obstructions, when required by the Engineer, shall be classified as Special Pipe Pile Excavation.

505-4.01	METHOD OF MEASUREMENT.  Add the following to numbered paragraph 1:

- Piles not achieving the required ultimate bearing capacity within 1.6 meters below the minimum pile tip elevation shown on the Plans shall be driven to a penetration established by the Engineer.  Requirement to drive the piles more than 1.6 meters deeper than the minimum pile tip elevations shown on the Plans shall be at the written direction of the Engineer.  For depths up to 4.6 meters below the minimum pile tip elevations, the contract bid price for piling shall be applied.  For depths beyond 4.6 meters below the estimated pile tip elevations, the pile unit costs shall be determined on a time and materials basis in accordance with Section 109, Paragraph 1.05, of the Standard Specifications.

Replace the first sentence of the second paragraph under Item 2. Drive Piles with the following:

#### This covers all items related to pile work that are not included in Item 1. Furnish Piles, including but not limited to: equipment movements, pile splices, cutoffs, templates, crane or work platforms, pile cleanout, jetting or drilling to specified depths, and other fixed or variable items.

Delete numbered paragraph 5 and substitute the following:

- Load Tests.  The specified high-strain dynamic load tests on this project will not be measured for payment.  The number of high-strain dynamic load tests to be paid for shall be the number of additional tests, not specified, but required by the Engineer.  This unit price per load test shall provide payment to you for their work required to assist the Engineer in performing additional high-strain dynamic testing, if required.  The six (6) specified high-strain dynamic load tests on this project will not be paid for directly, but will be subsidiary to Item 505(6), Structural Steel Piles, Driven.

Replace Item 6 with the following:

6.	Splices.  The number of piles driven deeper than 1.5 m below the estimated tip elevations.  All other splices shall be considered subsidiary.

Add the following:

- Special Pile Excavation: Removal of unusual obstructions causing pile refusal above the specified minimum pile tip elevations, when required by the Engineer, shall be classified as Special Pipe Pile Excavation.  This work will be measured on a time and materials basis in accordance with Section 109, Paragraph 1.05, of the Standard Specifications.  Pile refusal is defined as the condition reached during pile driving which results in a bearing pile driven by a impact hammer having a negligible rate of penetration per blow (such as when a pile tip reaches an impenetrable bottom such as a rock or a bedrock formation), or when the effective transferred energy (ram stroke, rate in blows per minute and rate in blows per 0.3 meter of a properly maintained, operating and efficient impact hammer blow is no longer sufficient to advance the pile tip.

505-5.01	BASIS OF PAYMENT.  Add the following:  The reinforcing steel to be used in the piling shall be measured and paid as Item 503(1), Reinforcing Steel.  Concrete fill used in the piling shall be measured and paid as Item 505(1), Class A Concrete.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 505(12) Pile Splice | Each |
| 505(13) Dynamic Test Pile | Each |
| 505(14) Special Pipe Pile Excavation | Contingent Sum |

SECTION 507

BRIDGE RAILING

Special Provisions

507-1.01  DESCRIPTION.  Add the following: This work consists of the removal and disposal of the existing bridge rail and transitions and installation of the new bridge rail and transitions shown on the plans.  Remove and dispose of existing bridge rail and transitions in accordance with Subsection 606-3.07

507-3.01  CONSTRUCTION REQUIREMENTS.  Add the following: Roughen deck surface and top of wing wall where new curb concrete is to be placed.

507-4.01  METHOD OF MEASUREMENT.  Add the following to Item 2. after “concrete rail section”: “including the wingwall corbel”

Add the following: Item 4.  Remove and dispose of existing bridge rail and transitions.

507-5.01 BASIS OF PAYMENT.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 507(1A) Retrofit Steel Bridge Railing | Meter |

SECTION 508

#### WATERPROOFING MEMBRANE

Special Provisions

508-3.01 APPLICATION OF MEMBRANE WATERPROOFING. Add the following to Item 2. Preparation of Concrete Deck:

g.	Completely remove the existing asphalt and membrane.

508-4.01 METHOD OF MEASUREMENT.  Delete Item 1 and substitute the following:

1.	Membrane.  By the square meter of area approved by the Engineer.

508-5.01 BASIS OF PAYMENT. Delete Item 1 and substitute the following:

1.	Membrane.  At the contract unit price for the area approved by the Engineer.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 508(1A) Waterproofing Membrane | Square Meter |

- SECTION 513

- field painting of steel structures

Special Provisions

513-1.01  DESCRIPTION.  Add the following: The limits of the cleaning and painting includes all superstructure steel for the Clear Creek bridge. Perform the painting work after widening of the concrete deck.

The existing bridge was originally constructed in 1967. The original paint system consists of a lead-based prime coat, a lead-based intermediate coat and an aluminum based top coat.  The underlying steel surface is believed to have been wheelabrated in the shop to remove loose mill scale and rust.  The existing amount of intact mill scale underlying the coating system is unknown.

Add the following Section:	SECTION 515

# CABLE-TIED CONCRETE BLOCK MAT SYSTEM

Special Provisions

515-1.01  DESCRIPTION.  This work consists of designing, constructing, and supplying all labor, equipment, and materials required for an articulating cable-tied precast concrete block mat system, including anchors, geotextile, and grout in accordance with the lines, grades, and dimensions shown on the Contract Documents and as specified herein.  This system consists of cable-tied concrete block mats placed side by side and clamped together to provide one homogeneous erosion protection system.

515-2.01  MATERIALS.  Meet the following requirements for the Cable-tied Concrete Block Mat System:

Concrete:	The minimum required concrete strength is 28 MPa at 28 days.  Use concrete mix recommended by manufacturer and approved by the Engineer.  Use materials that conform with the following:

Portland Cement:	Subsection 701-2.01

Fine aggregate:	Subsection 703-2.01

Coarse aggregate:	Subsection 703-2.02

Cables:	Use stainless steel 1X19-strand, 9.52 mm diameter, high strength, Type 316 that conforms to the current ASTM A 368 or equivalent.

Geotextile:	Use a needle punched nonwoven fabric.  Use materials that conform to Subsection 729-2.02 Subsurface Drainage, Class 2.

Clamps:	Use stainless steel clamps recommended by manufacturer.

Anchors:	Use anchor system recommended by manufacturer.

Grout:	Use materials that conform to Section 701 Hydraulic Cement.

Bedding Material:	Meet AASHTO M 80, Class A.  Gradation:  AASHTO M 43, size No. 68.

# DESIGN AND CONSTRUCTION REQUIREMENTS

515-3.01  SUBMITTALS.  Prepare and submit drawings according to Subsection 105-1.02.  Show the following as applicable:

1.	Design and show the details for constructing a precast articulating cable-tied concrete block mat system for the locations shown on the Contract Documents.

2.	Furnish design calculations

3.	Precisely describe all proposed materials and furnish manufacturer’s certificates of compliance for the concrete blocks, geotextile, cable, anchors, and cable fittings and connectors prior to the start of mat fabrication.

4.	Furnish shop drawings for the fabrication of the cable-tied concrete block mats and any recommendations, if applicable, 14 days prior to assembly of the mats.

515-3.02  DESIGN.  Use Factor-of-Safety methodology described in Publication FHWA-NHI-01-003, HEC-23 Bridge Scour and Stream Instability Countermeasures.  Design cable-tied concrete block mats to a minimum safety factor of 1.5.  Use a closed cell concrete block.  Perform analysis based upon the stability of the mat due to gravity forces alone, neglecting forces which may be due to cabling, mechanical anchorage, contact with adjacent blocks, or other restraints not attributable to gravity based forces.  Account for a 13 mm block projection.  See Subsection 515-3.03 for design hydraulic parameters.  Design for the most critical/stringent situation.

515-3.03  DESIGN HYDRAULIC PARAMETERS.  Base all calculations on the following hydraulic parameters for Bridge No. 599 Clear Creek:

Channel Slope:	0.23%

##### Side Slope:	Streambed: Horizontal, Bank Slopes: up to 1.5 H:1V

Discharge:	8.2 m3/s (290 cfs)

Velocity:	2.7 m/s (9 ft/s)

Depth:	1.6 m (5.3 ft)

Hydraulic Radius:	1.55 m (5.1 ft)

Bed Shear:	13.86 kg/m2 (2.84 psf)

515-3.04  CLOSED CELL CONCRETE BLOCKS.  Provide blocks sound and free of defects that would interfere with the proper placing of the mats or impair the strength or permanence of the construction.  Surface cracks incidental to the usual methods of manufacture, or surface chipping resulting from customary methods of handling in shipment and delivery, shall not be deemed grounds for rejection.

Cracks exceeding 7 mm in width and/or 25 mm in depth shall be deemed grounds for rejection.

Chipping resulting in a weight loss exceeding 10% of the average weight of the blocks shall be deemed grounds for rejection.

Repair blocks rejected at the project location with structural grout at no expense to the State.

515-3.05  FOUNDATION PREPARATION.  Remove all rocks greater than 75 mm, vegetation, and debris from the existing surface within the defined limits for the cable-tied concrete block mat.  If cable-tied concrete block mat placement conflicts with existing abandoned piles, remove portion of piles in conflict.  Grade surface to a smooth plane reasonably free of mounds, dips, or windrows.  Compaction is not required.

515-3.06  GEOTEXTILE.  During all periods of shipment and storage, protect the geotextile from direct sunlight, ultraviolet rays, and temperatures greater the 60 °C.  Place geotextile on the prepared surface so that the upstream strip of fabric overlaps on top of the downstream strip.  Overlap longitudinal and traverse joints a minimum of 600 mm.  Do not place geotextile fabric within 2000 mm of the side and bottom edges of the cable-tied concrete block mat.

515-3.07  CABLE-TIED CONCRETE BLOCK MAT PLACEMENT.  Due to the limited height under the bridge, it is anticipated that you will pull the cable concrete block mats into place.  Place mats from the downstream end of the bridge to the upstream end.  Abut adjacent mats with less than a 50 mm gap.  Entrench and bury at least two blocks on the upstream edge of the mat system into the ground.  Backfill trenches flush with the top of the non-trenched blocks.  Submit placement method plan for approval.

515-4.01  METHOD OF MEASUREMENT.

Item 515(1). By the square meter of Cable-tied Concrete Block Mat accepted by the Engineer.

515-5.01  BASIS OF PAYMENT.

Item 515(1).  At the contract unit price for the area accepted by the Engineer.  Payment shall include full compensation for all labor, materials and incidentals required to install the system in accordance with the Plans and Specifications.

Grade preparation, slope work, geotextile, anchors, grout, and bedding material are subsidiary.

Removal of piles will be paid for under Pay Item 202(1) Removal of Structures and Obstructions.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 515(1) Cable-tied Concrete Block Mat System | Square Meter |

SECTION 603

CULVERTS AND STORM DRAINS

# Special Provisions

603-1.01 DESCRIPTION. Add the following: This work shall also consist of installing culvert marker posts. (09/10/02)R42M

Standard Modifications

603-2.01 MATERIALS. In the second paragraph, delete “(900 mm maximum diameter)”.

In the fourth paragraph, delete the last sentence.

Special Provisions

Add the following: Culvert marker posts shall meet the requirements of Subsection 730-2.05 Flexible Delineator Posts. The color shall be blue with no other markings. The 65 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm. (09/10/02)R42M

Standard Modifications

603-3.03 JOINING PIPE.

2. Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.” (02/08/01)M95

Add the following Subsection:

603-3.06 CULVERT MARKER POSTS. Culvert marker posts shall be installed on the approach side of storm drain outfalls 750 mm and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. 1070 mm of post shall remain above the ground after driving. (09/10/02)R42M

603-4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

(09/10/02)R42M

SECTION 606

GUARDRAIL

# Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers. Use flexible markers with an over all length of 1,800 mm. The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag that provides approximately 129 cm2 of surface area. Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:		FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:		(218) 745-5095

Fax:		(218) 745-4990

E-mail:		www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

(05/29/02)R45aM98

# Standard Modifications

606-3.01  GENERAL.  Add  the following:   Treat field cuts to timber posts and blocks according to AWPA standard M 4.  (10/19/98)M 67

606-3.05 TERMINAL SECTIONS.  Delete the fourth paragraph (flexible markers) in its entirety and substitute the following:

Attach flexible markers, in a vertical position, to the last post of each guardrail terminal using two pipe bracket holders spaced 300 mm apart. Attach to wooden guardrail posts with wood screws and to steel guardrail posts with hex bolts. (03/14/00) M 88

Special Provisions

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following: Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 15 m of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.  (05/29/02)R45aM98

606-3.07 REMOVAL AND DISPOSAL OF GUARDRAIL. Delete the last sentence and substitute the following: Notify the Engineer, five (5) days prior to removing guard rail for disposal.  At that time, the Engineer will physically identify portions of guardrail to be salvaged.  All guardrail and associated hardware so designated will be delivered to the Department of Transportation Maintenance Yard located in Seward.  All remaining items removed become your property.  (9/8/00)R259M98

606-3.09 FLEXIBLE MARKERS. Add the following Subsection: For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION. Add the following Subsection: After shaping the slopes and staking all proposed guardrail locations, notify the Engineer to field verify the beginning and ends. The Engineer will approve the staked location of the guardrail before installation. The Engineer may determine that additional guardrail is necessary, and comply without delay. (05/29/02)R45aM98

### Standard Modifications

606-4.01 METHOD OF MEASUREMENT. Delete the second to the last paragraph and substitute the following:

Guardrail/Bridge Rail Connection. Per each, installed in place. Each connection includes all brackets, beam sections, transition pieces, and all posts and associated hardware required to connect the guardrail section to a bridge rail according to the Plans and the Special Provisions.

(10/19/98)M 66

SECTION 607

FENCES

Special Provisions

607-1.01 DESCRIPTION. Add the following:  This work also includes installing pedestrian guardrail.  This consists of prefabricated metal rail panels constructed from welded steel tube and perforated plate, welded steel tube posts, and all necessary stainless steel hardware required for installation.

Add the following Subsection:

607-1.02 SUBMITTALS. Provide submittals for all metal fabrications and supplementary structural items as follows:

- Shop Drawings:  Metal fabrications including welding and fabrication information.

- Specific instructions for all phases of installation including hole size, fasteners, preparation, placement procedures and instructions for safe handling of anchoring systems.

- Sample of powder coat finishes (100 mm x 100 mm min. each color) to be approved prior to submittal of Guardrail Panel and Post as per Item 4 below.

- One complete “Type B” guardrail panel and one guardrail post prior to manufacture of the remaining pedestrian guardrail.

607-2.01 MATERIALS.  	***DELETED TEXT***

Add the following:

##### Pedestrian Guardrail steel railing 	Section 722

Standard Modifications

607-3.01 CONSTRUCTION REQUIREMENTS.  In the ninth paragraph, change “minimum” to “maximum”. (06/25/99)M 73

Special Provisions      	***DELETED TEXT***

Add the following:    Install pedestrian guardrail as shown on the Plans and according to these Specifications.

- Fabrication:

  - Finish exposed surfaces smooth and uniform.  The guardrail shall be free of warps, kinks, dents, scrapes and other damage.

  - Fabricate horizontal elements perpendicular to vertical elements.  Construct vertical elements such that they will be plumb when installed.

  - Drill metalwork as required for attaching hardware or other materials.

  - Fabricate perforated steel plates with a border along the outer edge.  The width of the border shall be between 12 mm and 25 mm.   The border width shall be the same for all panels.  Ensure that no partial perforations are exposed along the edges of the plates.  The perforated plates for panels B and C shall have identical symmetry and location of perforations.  Fabricate the perforated plate for panel E identical to panels B and C except panel E is to be shortened on the left hand edge.  Perforations for panels A and D shall be symmetrical along a vertical mirror line to the adjacent panels B or C.

  - Round sharp edges to small uniform radii.  Grind burrs, jagged edges and surface defects smooth.  Flame cutting is not permitted.

  - Package and clearly tag parts and assemblies in a manner that will protect them from damage and facilitate identification and field assembly.

- Assembly:

  - Fabricate as shown on Plans.

  - It is the fabricator’s responsibility to ensure that measurements as shown on Plans match the dimensioning required for field installation within tolerances given.

  - Weld connections and grind exposed welds smooth.

  - Use fasteners as shown or scheduled.

  - Grind cut edges smooth and straight.  Remove all fins and ensure smooth surface with no sharp edges on perforated plate.

- Finish:   Refer to the Plans for colors of finish.  Apply powder coating using the following seven step process to provide an acceptable finish:

  - Abrasive blast to SSPC10, with a surface profile of no greater than 0.038 mm.

  - Iron phosphate treat to etch surfaces and remove foreign material

  - Rinse with clear water

  - Non-chrome seal rinse

  - Oven dry surfaces prior to powder coating

  - Apply a powder coat base of zinc rich epoxy primer electrostatically and partially cure.

  - Apply the final surface finish of TGIC polyester powder electrostatically to a thickness of 0.038 mm and bake to properly cure.

Use polyester material meeting AAMA 605.2 performance standards for powder coating.

Use material that conforms to the following:

Chemical Type:	Polyester

Particle Size:	30-60 microns average

Specific Gravity:	1.2-1.7

Cure Cycle:	204°C-10 min. Peak Metal Temperature (TGIC)

204°C-15 min. Peak Metal Temperature (Poyurethane)

Gloss @ 60°:	Available from 30° - 90+°

Film thickness: 	0.038 mm

Mechanical Specifications ASTM # or AAMA 605.2

Dry Adhesion:	D 3359 7.4.1.1	100% 5b Pass

Wet Adhesion:	             7.4.1.2	100% 5b Pass

Boiling Water Adhesion:	             7.4.1.3	100% 5b Pass

Hardness:	 D 3363 7.3.1.2H	Pass

Impact, Direct:	 D 2794-67 7.5.1	Up to 18 N•m Pass

Reverse:	 D 2795-67 7.5.1 	Up to 18 N•m Pass

Abrasion Resistance:	 D 968 7.6.1 Coefficient	28 Pass

Chemical Resistance  AAMA 605.2

Muriatic Acid, 15 min.:	No effect

Mortar Resistance, 24 Hr.:	No effect

Nitric Acid Resistance, 30 min.:	Less than DE2 Color Change

Corrosion Resistance ASTM # or AAMA 605.2

Humidity D 2247 7.8.1, 3000 Hr.: 	Rated “8” Few Blisters

Salt Spray B 117 7.8.2,  3000 Hr.:	Less than 1.6 mm Creepage

- Welding:

  - Meet requirements of ANSI/AWS D1.1 for techniques of welding employed, appearance, quality of welds made, and the methods of correcting defective work.

  - Meet visual acceptance standards of ANSI/AWS D1.1, paragraph 6.9. Grind welds smooth to required size and ensure they are free of putty, pits, pinholes and debris.

  - Complete welding before applying finish.

  - Provide continuous welds unless shown otherwise.

- Installation:

  - General:  Install metal fabrications plumb or level, accurately fitted, free from distortion or defects.

Install manufactured products in accordance with manufacturer’s recommendations.

Allow for erection loads, and for sufficient temporary bracing to maintain true alignment until completion of erection and installation of permanent attachments.

Obtain Engineer’s acceptance prior to site cutting or making adjustments not scheduled.

Construct railing to the line and grade shown on the Plans.  Ensure that the rail does not reflect any unevenness of the bridge structure.

  - Erection Tolerances:  Correct variations from horizontal alignment with Guardrail Post adjustment mechanisms and natural rubber washers for panel attachment mechanism (matching washers shown on the Plans).  Total correction utilizing natural rubber washers shall not exceed 8 mm (including thickness of natural rubber washer required for expansion).

Vertical variation from plumb or correct elevation should be corrected via the post leveling plate and should not vary more than 2 mm from plumb or correct elevation.

It is the fabricator’s responsibility to ensure that measurements as shown on the Plans match

607-4.01 METHOD OF MEASUREMENT. Add the following:

Pedestrian Guardrail.  By the meter measured along the top of the rail.

607-5.01 BASIS OF PAYMENT.  Add the following:

Class W concrete for post footings is subsidiary.

Payment for Item 607(7) shall be at the contract unit price for the amount of rail shown in the Bid Schedule.  Payment shall be full compensation for all labor, material and equipment necessary to fabricate and install the pedestrian guardrail per these Specifications and as shown in the Plans.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 607(7) Pedestrian Guardrail | Meter |

THIS PAGE INTENTIONALLY LEFT BLANK.

#### SECTION 608

- SIDEWALKS

Special Provisions

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

2.  Asphalt Sidewalk and Asphalt Pathway

###### Asphalt Cement, PG52-28	Subsection 702-2.01

Aggregate, Type III	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, N, min.	4450

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

608-5.01 BASIS OF PAYMENT. Add the following: Asphalt cement for asphalt sidewalk will not be paid for separately, but will be subsidiary to item 608(2), Asphalt Sidewalk.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively. (2/1/00)R47M98

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

- Notify the Engineer five (5) days prior to beginning sign salvage activities. At that time, the Engineer will physically identify those signs to be salvaged.  For each sign so designated, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner.  Deliver sign panels, posts and hardware to the State Maintenance Yard located in Seward.  Do not deliver salvaged materials until they have been inspected and approved by the Engineer.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose of). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 mm below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(05/16/01)R50M98

#### SECTION 618

SEEDING

# Special Provisions

618-1.01 DESCRIPTION. Add the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. Provide a living ground cover on all slopes as soon as possible.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION. Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  All seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION. Add the following: Apply seed, mulch and fertilizer as follows per hectare (ha). Apply seed and mulch in one application if using the hydraulic method. Apply all fertilizer with the hydraulic method.

| Seed Mix | Component | Ingredients | Application Rate (per ha) |
| --- | --- | --- | --- |
| Type A | Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 24.5 kg 19.5 kg 5.0 kg Total = 49.0 kg |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 2240 kg 2800 kg |
|  | Fertilizer | 20-20-10 | 586 kg |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright)  is commercially unavailable.  If this substitution is made, apply at the  same application rate.

618-4.01 METHOD OF MEASUREMENT. Add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT. The work described under subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(03/05/02)R52M98

SECTION 620

TOPSOIL

Special Provisions

620-2.01 MATERIALS. Delete this subsection in its entirety and substitute the following: Topsoil shall conform to the requirements of Section 726. Class of topsoil shall be as shown on the Plans.

620-4.01 METHOD OF MEASUREMENT. Add the following: Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(9/11/96)R53

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

# Special Provisions

639-1.01 DESCRIPTION. Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS. Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION. Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. By the number of driveways and approaches constructed as shown on the Plans or as directed. Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule. The contract unit price for driveways and approaches shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.(05/09/02)R58M98

Payment will be made under:

| ## Pay Item | Pay Unit |
| --- | --- |
| 639(6) Approach | Each |

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modifications

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

- ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and included in the project plans and specifications. It serves as a resource for bid estimation and a framework from which you develop the project SWPPP.

- Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan). Your detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI. Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.

- NOT. Notice of Termination of coverage under the NPDES General Permit.

- NPDES General Permit. The General Permit for Stormwater Discharges from Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires a SWPPP prior to ground-disturbing activities for the project.

- SWPPP (Storm Water Pollution Prevention Plan).Your plan for erosion and sediment control and storm water management under the NPDES General Permit. The SWPPP is developed by you and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS. Submit 3 copies each of your SWPPP and HMCP for approval no less than 5 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days. Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP must be signed by you and the Engineer in accordance with the NPDES General Permit.

Submit your signed NOI (use EPA Form 3510-9) to the Engineer no later than 10 working days before you intend to commence ground-disturbing activities.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP. Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing over 2 hectares. The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private. The plan must also incorporate all the requirements of the Project permits.

Have the SWPPP prepared under the direction of and sealed by a professional engineer currently registered in the State of Alaska. Include all requirements of the NPDES General Permit.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities. Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-3.01 CONSTRUCTION REQUIREMENTS.

Do not begin ground-disturbing work until you are notified by the Engineer that 48 hours have passed since the NOIs were mailed to the EPA and DEC.

Post at the construction site, the

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	name and phone number of your local contact person, and

3.	location of a SWPPP available for viewing by the public.

Comply with all requirements of the NPDES General Permit, implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms. Perform all fueling operations in a safe and environmentally responsible manner. Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections. Prior to start of construction conduct a joint on-site inspection with the Engineer and the professional engineer who stamped the SWPPP to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

a.	During construction, inspect the following at least once every 7 calendar days and within 24 hours of the end of a storm event exceeding 13 mm in 24 hours (as recorded at or near the project site).

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections. During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 13 mm or greater. Monthly inspection requirements may be waived by the Engineer until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports. Prepare and submit, within 3 calendar days of each inspection, a report with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) of personnel making the inspection.

c.	The date of the inspection.

d.	Observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

f.	Incidents of non-compliance.

Where a report does not identify any incidents of non-compliance, include certification that the facility is in compliance with the SWPPP and NPDES General Permit. Sign the report in accordance with Part VI. Standard Permit Conditions of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP.

Retain copies of the SWPPP, and all other records required by the NPDES General Permit, for at least 3 years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

1.	storm event or other circumstance that threatens water quality, and

2.	inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within 7 days.

Stabilize all areas disturbed after the seeding deadline within 7 calendar days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT (use EPA Form 3510-7) to the Engineer

1.	when the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

2.	when the construction activity Operator (as defined in the NPDES General Permit) has changed.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

- pursue work required by the approved SWPPP,

- respond to inspection recommendations and/or deficiencies in the SWPPP, or

- implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01 METHOD OF MEASUREMENT. Items 641(1) and 641(3) will not be measured for payment.

Items 641(2) and (4) will be measured as specified in the Contract or Directive authorizing the work.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1) and (2) or items 641(1), (3), and (4)

1.	Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract to install and maintain all temporary erosion, sedimentation, and pollution control measures.

3.	Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain temporary erosion, sedimentation, and pollution control measures in accordance with the original approved SWPPP and HMCP.

4.	Item 641(4) Temporary Erosion and Pollution Control Amendments. At the prices specified in the Directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures. All work paid under this Item shall be shown as amendments to the original approved SWPPP or HMCP.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.

(08/15/01)M78

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 641(1) Erosion and Pollution Control Administration | Lump Sum |
| 641(2) Temporary Erosion and Pollution Control | Contingent Sum |
| 641(3) Temporary Erosion and Pollution Control | Lump Sum |
| 641(4) Temporary Erosion and Pollution Control Amendments | Contingent Sum |
| 641(5) Silt Fence | Meter |

# SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642 1.01 DESCRIPTION.  Add the following:  This work also consists of performing a cross section survey of the deck surface and girder cambers of the Clear Creek bridge.

CONSTRUCTION REQUIREMENTS

642-3.01 GENERAL. Add the following after Item 10 on page 355: Prior to any work from Sta. “C” 10+440.000 to Sta. “C” 10+720.000 and from Sta. “C” 11+480 to Sta. “C” 13+704.380 (EOP), stake and reference the construction centerline. Reference the existing centerline at 25 m intervals on tangents, and 12.5 meter intervals on curves, super elevations, transitions and cross-slopes. The reference stake shall be a minimum of 25 mm x 50 mm by 0.6 m and be offset 1.2 to 2.4 m from the shoulder on the right side of the roadway.  They shall show the offset distance to centerline and the station from the beginning of the project.  Ensure that the stakes are visible from the roadway by clearing as necessary.

Install a reference sign every 150 m within all project segments. These reference signs shall meet the following requirements:

1.	mounted a minimum of 1.5 m above the shoulder,

2.	located a minimum of 3 m from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 125 mm high black lettering on an orange background.

Reference the beginning and ending points of the no-passing zones in a separate field book.

Provide centerline and shoulder profiles extending 90 m beyond the limits of the pavement removal and dig-out areas. The Engineer may require such adjustments to the planned roadway grades. This shall not be considered extra work. Provide this profile information to the Engineer (electronically in Excel format) immediately upon its completion, along with checked computations on all level loops, but in no case later than 7 calendar days before slope staking. (09/20/02)R61M98

Delete the seventh paragraph.

Add the following: Perform a cross section survey of the deck surface and girder cambers of the existing bridge prior to the removal of the concrete bridge deck.  Record the profile and cross-slope of the concrete deck surface.  Take elevations at 3.05 m intervals along the centerline and left and right edges of roadway for the Clear Creek bridge.

Submit the survey results in a report.  Provide three (3) copies of the report to the Engineer.  Include plan sheets depicting the profile of the centerline, left and right edges of roadway and existing girder camber for each girder for the Clear Creek bridge.  Include plan sheets depicting the cross-slope of the deck surface and pathway surface for each 3.05 m interval. Also tabulate grade data for each 3.05 m interval.

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

- Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work.  (3/31/00)R252M98

642-4.01 METHOD OF MEASUREMENT.  Add the following:  Clearing required for stake visibility shall not be measured.

Item 642(13).  No measurement of quantities will be made.

642-5.01 BASIS OF PAYMENT. Add the following:  Clearing required for stake visibility is subsidiary to Item 642(1) and no separate payment shall be made. (09/20/02)R61M98

Item 642(13). At the contract lump sum price.  Payment shall include all material, labor and incidentals required to perform the work as described in the Specifications.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 642(13) Bridge Survey | Lump Sum |

SECTION 643

#### TRAFFIC MAINTENANCE

# Special Provisions

643-1.01 Description.  Add the following:  This work also consists of constructing temporary detour bridge(s) to maintain traffic during the removal and replacement of the Resurrection River Bridges.  This work also consists of providing temporary traffic control during bridge widening and bridge rail replacement at the Clear, Bear and Salmon Creek Crossings.

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: You may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations. (09/10/02)R222M98

## Standard Modifications

643-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM and ASDS.

a.	Construction Signs: Use regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or on an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 1.2 m X 1.2 m traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 2.4 m long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section. Use yellow reflectors or tape if you use barriers at centerline. Use white reflectors or tape if you use barriers on the roadway shoulder.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 710 mm high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08,

b.	Preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or

c.	Temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use approved temporary crash cushions conforming to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. Do not use permanent crash cushions as temporary crash cushions. Use sand or water filled crash cushions only when the forecasted temperature during their use is above 5 oC.

11.	Sequential Arrow Panels. Use Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs. Use truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following features:

- Message sign panel large enough to display 3 lines of 229 mm high characters.

- Eight character display per message line.

- Fully programmable message module.

- The capacity to create, preview, and display new messages and message sequences.

- A waterproof, lockable cover for the controller keyboard.

- An operator’s manual, a service manual, and a wiring diagram.

- Quick release attachments on the display panel cover.

- Variable flash and sequence rates.

- Manual and automatic dimming capabilities on lamp bulb matrix models.

- Locate the bottom of the sign panel at least 2.1 m above the pavement.

- Operate with a battery pack a minimum of 2 hours under full load.

13.	Plastic Safety Fence. Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	“Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 12 mm thick for areas continuously supported by subgrade. Use plywood at least 25 mm thick for areas that are not continuously supported.

b.	Do not use unsupported 25 mm plywood longer than 750 mm.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 25 mm.

d.	Use a method that will withstand 40 km/h wind velocities to hold temporary surfacing in place.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

- Flagger Paddles. Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. (9/29/00)M 91

## Special Provisions

Add the following:

17.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

(09/10/02)R222M98

## Standard Modifications

Add the following Subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Category | ## Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://safety.fhwa.dot.gov/roadside/know/workzone/index.htm).

Submit documentation of compliance to the Engineer before using devices on the project. (9/29/00) M91

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, you shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity. (11/29/01)R222M98

Add the following: During bridge rail replacement, completely remove the existing bridge rail and replace with new bridge rail on one side of the bridge before removing any rail on the opposite side of the bridge.  Maintain two lanes of traffic across the bridge at all times.

Standard Modifications

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.  (06/25/99)M 80

## Special Provisions

Add the following:  You may maintain traffic on a continuous gravel surface for 3,048 m (measured along the centerline) at any one time.

643-3.04 TRAFFIC CONTROL DEVICES.  Delete the first sentence of the eighth paragraph and substitute the following:  All items paid under this Section shall remain your property unless stated otherwise.

Add the following to 1. Embankments.:  Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.:  Remove all obstructions greater than 100 mm above the nominal foreslope grade at the end of each continuous work shift.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following items:

10.	ET-2000  LET.  The price listed in the Traffic Control Rate Schedule shall be full compensation for furnishing, installing, maintaining during construction, removing and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

11	Resurrection River Crossings.  Maintain two lanes of traffic at the Resurrection River Bridge Nos. 1, 2 and 3 (Bridge Nos. 596, 597 and 598) using stage construction and temporary detour bridges.  This will require maintaining traffic at all times unless other restriction to traffic are addressed through the approved Traffic Control Plan.

Construct the temporary detour bridges and approaches entirely within the right-of-way.

Acquire all permits necessary to construct, maintain and remove the temporary detour bridges.

Use detour bridges that conform to the following requirements:

- Design the detour to support HS20-44 live loads with no overstress, or your maximum construction equipment or vehicle load with an overstress less than 25 percent, whichever is greater.

- Provide the minimum clear roadway width shown on the Plans.  Pave the clear roadway width.  The maximum width of the temporary bridge is not to exceed the 12.2 m out to out shown in the Plans.

- Provide an approved Jersey-type precast concrete barrier or equivalent traffic protection device along the edges of the temporary bridges with crashworthy end treatments or connection to guardrail.

- In constructing the detour, use materials that conform to the requirements of the applicable specifications.

- Provide sufficient waterways to allow passage of the maximum flow expected during the construction period.

- Have no fill material below ordinary high water.

- Post load limits for the detour.

- Conform to the AASHTO Standard Specifications for Highway Bridges, 16th Edition with the latest interim’s.

- A Professional Engineer registered in Alaska must design the temporary bridges and any related structures.

Submit design calculations, independent design check calculations, plans and installation procedure for approval.  A Professional Engineer registered in the State of Alaska must stamp all plans and design calculation cover sheets for the temporary detour bridges.

Submit plans of the proposed temporary detour bridges and approaches, including a rehabilitation plan for the removal of the temporary bridges, to the Engineer at least thirty (30) days prior to the anticipated date of installation of the temporary crossings.  Begin no work on the detour without written approval of the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Friday from 1500 hours to Sunday 2200 hours

2.	1500 hours the day before to 0300 hours the day after the Seward Silver Salmon Derby.

3.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

Lane restrictions, if allowed shall be conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 0.4 kilometers of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 20 minute stopped delay, 80 vehicles, or 0.8 kilometers of traffic detained, will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  Make every effort not to delay school buses through the construction work zone.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

643-4.01 METHOD OF MEASUREMENT. Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement shall be made for providing a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

Delete Item 13 and substitute the following:

13.	Temporary Guardrail.  By the meter, including end treatments, as shown on an approved TCP or in the Plans.

Add the following:

14.	Temporary bridges. Temporary bridges will not be measured for payment.

643-5.01 BASIS OF PAYMENT.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET 2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.

Add the following:  The Engineer does not require a change order/directive for Item 643(25) Traffic Control. (01/29/02)R222M98

Payment for Item 643(27) includes all labor, equipment, materials, and incidentals necessary to install, maintain, remove and salvage the temporary guardrail.  Deliver the salvaged temporary guardrail to the Department of Transportation and Public Facilities maintenance yard in Seward.

Add the following:

Payment for Item 643(29) includes all labor, equipment and materials necessary to install, maintain, and remove the temporary bridge and approaches accepted by the Engineer.  All temporary bridge elements shall become your property upon completion of the contract.  Excavation, backfill and embankment required for the temporary crossing will be paid for under their respective items.

Compensation for payment and contract time extensions will not be permitted for delays resulting from inadequate calculations, plans or installation procedures for the temporary detour bridges.

Delete item 643(15) and substitute the following:

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15) Flagging | Contingent Sum |
| 643(29A) Temporary Bridge (Bridge # 596) | Lump Sum |
| 643(29B) Temporary Bridge (Bridge # 597) | Lump Sum |
| 643(29C) Temporary Bridge (Bridge # 598) | Lump Sum |

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions.

644-2.01 FIELD OFFICE. Delete this subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15. The following office requirements shall be met:

1.	A minimum of 250 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of twelve (12) electrical outlets.

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Five (5) telephone service lines available at the office location.

8.	If a part of your building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 1600 m of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY. Delete sub-item g on page 380 and substitute the following:

g.	1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

- Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

644-2.05 VEHICLES.  Delete the first sentence in the first paragraph and substitute the following: Furnish and maintain five (5) full-size four-wheel drive pickup(s) or sport utility vehicle(s) for exclusive use of the Department throughout the project.

Add the following: Equip vehicles used by the Department with CB radios and yellow rotating beacons wired into the vehicle’s system with a dash mounted switch easily accessible to the vehicle operator.

You are responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use. The Department is responsible for damage to any vehicle caused by its own negligent operation. The Department will provide non-owned auto liability insurance providing third party liability coverage for any accident during the Department’s operation and use.

644-3.01 METHOD OF MEASUREMENT. Delete subparagraph “vehicles” and substitute the following:

Vehicle. Per each vehicle provided. If a replacement vehicle is necessary, no additional measurement for payment will be made. (01/28/02)R245M98

644-4.01 BASIS OF PAYMENT. . In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators.”

(06/25/99)M 81

Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory. (9/28/00)R63M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 644(7) Vehicle | Each |

Add the following Section:	SECTION 645

TRAINING PROGRAM

#### Special Provisions

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, you shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "green pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless you can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to you where the apprentices/trainees are concurrently employed on the project and you do one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, you shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by you, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

You may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by you and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by you.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in your judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and you employ that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  You must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03 Subcontracts.  In the event you subcontract a portion of the work, you shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with you; compliance or non-compliance with these provisions rests with you and sanctions and/or damages, if any, shall be applied to you in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  You will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to your submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of you, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, you will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds you may receive, unless such other funding sources specifically prohibit you from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to you if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where you have failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, you will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.  (10/29/91)S 16

Payment will be made under:

| # Pay Item | Pay Unit |
| --- | --- |
| 645(1) Training Program, 3 Trainees/Apprentices | Labor Hour |

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.   The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.   60-Day Preliminary Schedule.

(3/12/01)R261M98

Add the following Section: 	SECTION 647

EQUIPMENT RENTAL

##### Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and your operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to your supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for your responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, you shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by you shall be, and shall remain during the work hereunder, employees solely of you.

Furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by you and involved in the performance of the work. Also, you shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by your representative at the end of each shift, and a copy will be provided to your representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1), Wide Pad Dozer, 48 kW Minimum will be paid on a contingent sum basis at the rate of $125/hour.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle you to any extra compensation. (11/12/98)R15M98

Payment will be made under:

| # Pay Item | # Pay Unit |
| --- | --- |
| 647(1) Wide Pad Dozer, 48 kW Minimum | Contingent Sum |

# SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS.  Delete item number 1 that follows the first paragraph, and add the following:  The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-1.05 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS. Delete this Subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned in accordance with the following specifications.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When you begin work, the Engineer will notify you and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility. Therefore, before starting work on the project, you should inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with you. If you begin work before providing the Engineer with an inventory, you waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, and photoelectric controls operate the lighting systems. The State will pay for all electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin repair work on all systems within one hour of notification by the Engineer. If you do not complete the repairs, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due you.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day you retire the original circuit.

Relocate or replace lighting standards whenever you reduce their clearance from the traveled way to less than 1.8 m.

When no longer required, salvage all original and Department provided equipment in accordance with the Plans and subsection 660-3.21, Salvaging or Reusing Electrical Equipment, and remove all other materials used in the temporary systems from the project.

660-1.05(B) TEMPORARY ELECTROLIERS.

Existing electroliers, that are part of a lighting system to be modified and are scheduled to remain, shall be operational at all times except as permitted for system Modifications.  Electroliers that are scheduled to be replaced shall have permanent electroliers installed and be operational from September 15 through May 1.  If you are unable to install the permanent electorliers for operation during this time period, temporary electroliers shall be installed at no additional cost to the Department.

Submit a plan for each temporary electrolier system to the Engineer for his review and approval before implementing it. Allow at least two weeks for review.  Along roadways, choose one of the following options for your temporary lighting plan:

- When one is included, use the temporary lighting plan detailed in the Plans.

- On roadways with existing lighting, provide new foundations and install poles and mast arms sized to keep the existing luminaires in its existing positions horizontally and vertically over the roadway.  In this case, no lighting design is required.

- Design your own temporary lighting system using your choice of luminaires, including the luminaires of the permanent lighting system. Use a layout pattern, offset, mounting height, and luminaire spacing that provide a light distribution that conforms to AASHTO’s “An Informational Guide for Roadway Lighting” illuminance method of design.  Design the system for the roadway’s functional class as specified in the Department’s Annual Traffic Volume Report.

Furnish and install all materials and miscellaneous hardware required to provide a functional lighting system, including foundations and electrical load centers. All materials shall conform to the requirements of the Plans and Specifications, except branch conductors may be triplex aluminum with messenger cable if they are installed overhead.  Install branch conductors in underground electrical conduit when overhead conductor clearances do not conform to the National Electrical Safety Code (NESC).  Size the branch conductors to provide the minimum voltage the ballast manufacturer recommends at the most remote luminaire.

Use any of the following poles.

1.	Existing light poles found within the project limits scheduled to be salvaged.

2.	Poles from the permanent lighting system.

3.	The following new or used poles that you furnish, provided they maintain a minimum 9 m difference in elevation between a luminaire and the edge of traveled way beneath it.  Provide certification on the merchantability of the used poles.

a.	ANSI Class 4 wood poles.  Install them outside the clear zone during winter shutdown. To determine the clear zone, see subsection 1130.02 of the Alaska DOT/PF Highway Preconstruction Manual.

b.	Steel, aluminum, or fiberglass poles that meet design criteria for 130 kilometer per hour wind speeds according to AASHTO’s “Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals”.

Furnish all temporary electroliers, in service at any time from October 1 through May 15 and located within the clear zone, with an approved yielding type base. Approved yielding bases consist of FHWA approved slip bases, transformer bases, or frangible couplings. Install wood poles and all other fixed base poles outside the clear zone or behind guardrail or portable concrete barrier that protects against another hazard.

Install temporary electroliers, in service at any time from May 15 through September and located within the clear zone, with approved yielding bases or with fixed bases shielded by 9 m of barrier and an FHWA approved end treatment.  Provide 0.6 m of clearance between the barrier and pole. Replace fixed base poles that are located within the clear zone and which will remain in service after October 1 with yielding base poles at no expense to the State.

Use any of the following load centers to energize the temporary lighting systems. Provide all work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

1.	Permanent load centers installed in their plan location.

2.	Existing load centers scheduled to remain intact until completion of the project. You may relocate and reuse existing load centers only if they are approved.

3.	Approved temporary load centers with photoelectric controlled lighting circuits.  Provide a temporary load center when you retire an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "Suitable for use as service equipment".

660-2.01 EXCAVATING AND BACKFILLING. In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

Add the following after the fourth paragraph: Backfill the first 150 mm lift with material free of rocks exceeding a 25 mm maximum dimension.

660-2.03 FOUNDATIONS.  Add the following:  Use cast-in-drilled-hole foundations for electrolier foundations.  The use of piles for electrolier foundations is not permitted on this project.

660-2.04 POLES, STEEL PEDESTALS AND POSTS. Add the following:  Furnish back-up calculations stamped by a registered professional engineer.

Relocate existing standards per the Plans in a manner that maintains their existing condition. Replace standards damaged or destroyed by your operations at your expense. When you relocate galvanized standards with rusted or scarred surface areas, repair these areas in accordance with subsection 660-2.15, Galvanizing.

Welding design, fabrication and inspection shall be in accordance with the latest edition of the AWS D1.1, Structural Welding Code- Steel

- Circumferential Welded Splices

- 100% of Complete Joint Penetration (CJP) welds by ultrasonic examination (UT)

- Longitudinal Seam Welds

- 100% of CJP welds by ultrasonic examination (UT)

- 25% of all Partial Joint Penetration (PJP) welds of longitudinal seams by magnetic particle examination (MT)

- Base Connection Welds

- Inspect 100% of all base connection welds shall be inspected

- CJP welds shall be inspected by UT

- Fillet welds shall be inspected by MT

- At least 14 calendar days before welding, submit the welding plan and mill certification reports for all steel to the Engineer for approval.  Do not begin welding until these items have been returned approved in writing by the Engineer.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS)

- Procedure Qualification Record (PQR)

- Welder Performance Qualification Record (WPQR)

- Visual Inspection Form

- Report of Nondestructive Examination (NDE) of Welds in accordance with Annex K of the latest edition of AWS D1.1

- Your Quality Control (QC) manager with documentation of qualifications

- NDE personnel qualification records

- Furnish all Quality Control inspection necessary to ensure that the materials meet the requirements of the contract documents and that workmanship meets the requirements of AWS D1.1.

- Correct all deficiencies in materials and workmanship revealed by inspection in accordance with AWS D1.1 without additional compensation.

- Furnish all completed QC inspection documents to the QA representative as designated by the State.

660-2.05 CONDUIT. Add the following: The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid.  The Engineer will not allow trenching after you pave the final asphalt course.

660-2.06 JUNCTION BOXES. Delete the second paragraph and substitute the following: Only use pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the Plans.  All junction box lids shall be cast iron.

660-2.08 CONDUCTORS.  Add the following after the second paragraph:

Provide the following markings on the outer coverings of conductors and cables on intervals of 0.6 m or less: manufacturer, the number of conductors or pairs in cables, conductor size, 600V, the conductor or cable type and environmental conditions for which the conductor or cables are listed, and the symbol of an approved independent testing laboratory.

Delete item 2. Power Conductors and Cables and add the following:

- Power Conductors. For individual conductors, install general-purpose building wire manufactured according to UL Standard 44, ICEA publication S-66-524, and NEMA Publication No. WC7.  Furnish conductors insulated with cross-linked polyethylene listed as type XHHW-2 and rated for 600 volts AC operation.

Use size 10 AWG wire for illumination tap conductors.  In an electrolier, the illumination tap conductors run from the fused disconnect kit to the ballast in the luminaire. Furnish conductors with black, red, or white colored insulation as required to identify the two phase and neutral conductors, respectively.

If conductors in controller cabinets carry the full signal load circuit, use size 10 AWG or larger conductors.  Use orange colored conductors from the flash transfer relay to program emergency flashing operation.

- Illumination Cables. For cables that consist of three size 6 or 8 AWG conductors, furnish power cables that feature three conductors, each insulated with cross-linked polyethylene, and a black, low density, high molecular weight polyethylene jacket.  Use insulated conductors listed as type XHHW-2.  Furnish these cables with one black, one white, and one red colored conductor and no grounding conductor. Use cables rated for 600 volts AC operation.

Use insulated conductors that meet the requirements of ICEA publication S-66-524 and UL Standard 44.  The jacket shall also meet the requirements of ICEA publication S-66-524.

- Power Cables. For cables that consist of three size 4 AWG and larger conductors, furnish tray cables that feature three conductors, each insulated with cross-linked polyethylene that meets the requirements of XHHW-2, and a PVC jacket.  Furnish these cables without an integral grounding conductor. Use cables manufactured according to UL Standard 1277, ICEA publication S-95-658, and NEMA Publication No. WC70.  Provide cables listed for direct burial and resistance to sunlight and rated for 600 volts AC operation.

Furnish these cables with black conductor insulation with one printed number (1, 2, or 3) identifying each conductor.

Renumber items 3 and 5 as items 5 and 7, respectively.

660-2.09 WIRING. Delete the first paragraph and add the following: Install illumination cables without splices, except when adding an electrolier to the midst of a circuit. In addition, do not splice conductors within cabinets, poles, signal heads, and luminaires.

Crimp spade type terminals onto all conductors that attach to terminal blocks. When reusing cabinets, replace terminal blocks that lack enough terminals. Make the wiring within cabinets neat, and cable conductors together with self-clinching nylon ties.

660-2.10 FUSED SPLICE CONNECTORS. Delete the 4th paragraph in its entirety and replace with the following:  Use fuses that are 10 ampere, midget (10 mm x 40 mm) ferrule type with fast acting current limiting (KTK type) design.

Add the following: Retrofit reused poles with new tap wires, and fused disconnect kits.

660-2.11 BONDING AND GROUNDING. Add the following to the second paragraph:  The bare grounding conductor shall be separate from other cables in the conduits.  All system grounding connections shall be made in the junction boxes.

Add the following after the second paragraph:  All hardware, including grounding bushings, ground rods, and ground rod clamps shall be UL listed. Furnish threaded type grounding bushings that are made of malleable iron or steel and feature a zinc or galvanized finish.  Bushings shall also feature an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Where wire is pulled and reinstalled in existing conduits, the bare No. 8 AWG copper wire shall also be installed. Where conduits are installed for future conductors, the above-mentioned copper wire may be omitted. (3/30/00)R215M98

660-3.16 LUMINAIRES. Add the following: Furnish high-pressure sodium lamps with a rated life of 24,000 hours based on 10 hours per start.  Provide magnetic regulator ballasts for all luminaires.

Furnish luminaires that

- Are UL 1572 listed for use in wet locations.

- Include a terminal block for terminating the illumination tap conductors.

- Feature an easily removed hinged door or tray used exclusively for mounting the ballast.

- Provide the illumination levels and uniformity specified (or better) in the arrangements listed on the plans when calculated according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 1983.

- Include a lamp-starting aid that plugs into a socket for easy replacement.

- Feature a wire way that meets NEC requirements for installing three #10 AWG conductors with type XHHW-2 insulation between the pole and a terminal block located in the luminaire.

- Are free of substances (such as paint) that affect photometric performance.

Furnish the Engineer with the manufacturer’s current electronic photometric data in Illuminating Engineering Society (I.E.S.) format to verify illumination levels and uniformity ratios.

Luminaire Type Definitions:

MC-3:	Mast arm Mounted Medium Cutoff, Type 3 as defined by the Illuminating Engineering Society (I.E.S.).

SC-5:	Short Cutoff, Type 5 as defined by the I.E.S.

Offset:	Pole top mounted luminaires designed to be offset between 6 and 15 m from the edge of traveled way and angled between 30 and 50 degrees from the horizontal.

660-3.21 SALVAGING OR REUSING ELECTRICAL EQUIPMENT. Add the following: Transport all electrical and lighting equipment, if any, from the project to the State Maintenance Yard located south of Soldotna. Allow maintenance personnel to select the equipment they would like to salvage, and dispose of all remaining equipment. Contact the Kenai Peninsula District Superintendent; Carl High, or Brian Gabriel, Electrician, at (907) 262-2199; provide one-week notice of your intent to deliver salvaged materials.

660-5.01 BASIS OF PAYMENT. Add the following: The lump sum prices paid for the items included in the Contract includes full compensation for all work involved in furnishing and installing, assembling, modifying, and removing the components of the systems shown on the Plans. This includes: clearing, completing all excavation to install foundations, conduits, and junction boxes, backfilling and compacting trenches, removing and replacing improvements, installing sumps under junction boxes, and pulling conductors. The lump sum prices paid also include full compensation for all work specified in the Standard Specifications and Special Provisions. This includes: getting all materials approved; preparing as-built Plans, maintaining the electrical systems, adjusting junction boxes to grade, making all splices, labeling all conductors, completing all tests, and delivering salvaged electrical equipment.

Add the following Section:

#### SECTION 669

#### AUTOMATED TRAFFIC RECORDERS

Special Provisions

669-1.01  DESCRIPTION. This work shall consist of furnishing and installing two automated traffic recorder stations.

An Automated Traffic Recorder (ATR) station is a vehicle detection system and may contain a traffic volume counter, an Automated Vehicle Classifier (AVC), a Weigh-In-Motion (WIM) system and/or other equipment.  ATRs are operated and maintained by personnel of the Highway Data Section (HDS); main office located at 2200 E. 42nd Ave., Anchorage, phone (907) 269-0876.

The simplest form of ATR is an Intermittent Volume Recorder (IVR), which consists of inductive loop sensors connected to a traffic counter.  In each traffic lane, an inductive loop is buried beneath the pavement.  Lead wires run from the sensors to a type CBA1 cabinet located at the side of the road. At the type CBA1 cabinet, the lead wires connect to the traffic counter. Traffic volume information is collected by a portable, battery-operated traffic counter that detects passage of vehicles and stores the data for later retrieval.

The locations of traffic detection sensors and cabinets, shown on the Plans are approximate and the Engineer shall establish the exact locations in the field.

A general description of the Automated Traffic Recorders on the project is as follows:

H1: Seward Highway Station 10+640, IVR, 2 lane vehicle sensor array with 1 Presence Loop per lane, 12m left offset CBA1 cabinet without electrical and without telephone service.

Supply and install the CBA1 cabinet, Junction Boxes, Conduit, IVR traffic counter and loop presence sensors as shown on the Plans.  Install Inductive Loop Presence Sensors beneath the new pavement by burial as shown on the Plans.

H2: Seward Highway Station 12+195, IVR, 2 lane vehicle sensor array with 1 Presence Loop per lane, 12m left offset CBA1 cabinet without electrical and without telephone service.

Supply and install the CBA1 cabinet, Junction Boxes, Conduit, IVR traffic counter and loop presence sensors as shown on the Plans.  Install Inductive Loop Presence Sensors beneath the new pavement by burial as shown on the Plans.

669-1.02  REGULATIONS AND CODE.  All materials and workmanship shall conform to the standards of the Underwriter's Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturer's Association, where applicable.

669-2.01  MATERIALS.  All materials provided shall be new, unless otherwise stated, and shall meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with subsection 660-2.09, Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable.  All wires and cables must be home run labeled in each junction box and cabinet; for example, W1SLA (for wire) and GaSLA (for cable) as shown on the Plans.

2.	Conduit.  All conduit shall be in accordance with subsection 660-2.05, Conduit. All conduit, except for PVC conduit forming the inductive loops, shall be galvanized rigid metal. All grounding bushings shall be plastic-sleeved to minimize the potential for  insulation damage during wire pulls.

3.	Junction Boxes.  All junction boxes shall be in accordance with subsection 660-2.06, Junction Boxes.  The covers of all junction boxes used for loops or sensor wires shall be labeled 'TRAFFIC'.  The covers of all junction boxes used to provide electrical service to ATR installations shall be labeled 'ELECTRIC’. .  Junction boxes for 120V/240V electrical service shall be kept completely separate from junction boxes containing loop or sensor wiring

4.	Terminal Blocks.  All terminal blocks shall have nickel, silver or cadmium plated brass binder-head screw terminals.  Terminal blocks shall be a barrier type, rated 600 VAC at 20 Amps, sized for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips.

5.	Presence Loops.  All presence loops shall be in accordance with subsection 660-2.08, Conductors.  Conductors used for detector presence loops shall be UL listed as IMSA specification #51-5-1984 single conductor PVC nylon with tube jacket, type THHN, #14 AWG.

Multiple pair loop lead-in cable shall consist of twisted pairs of 18AWG stranded tinned copper wire.  Each twisted pair shall have its own 20AWG tinned copper drain wire.  An aluminum foil shield shall surround each individual bundle of twisted pair and drain wire.  Multiple pair loop lead-in cable shall have an overall PVC or PE outer jacket.

- Style CBA1 Cabinets.  All cabinets shall meet or exceed a NEMA Type 3R rating.  Style CBA1 cabinets shall meet the following requirements:

- Cabinet Dimensions.  Unless otherwise shown on the Plans, the cabinet shall be 518-mm high, 440-mm wide, and 412-mm deep.

- Cabinet Construction. The cabinet and hinged door shall be constructed from sheet aluminum alloy, and shall be unpainted with a smooth exterior finish.  All welds shall be neatly formed and free of irregularities.  All inside and outside edges of the cabinet shall be free of burrs.  Cabinet shall be provided with aluminum mounting plate as shown on the Plans.

- Shelf.  An adjustable equipment shelf shall be mounted inside of the cabinet.  The adjustable equipment shelf shall be supported on both sides and located 75 mm upwards from the bottom of the cabinet.  The adjustable equipment shelf shall be constructed from 5052-H32 or better sheet aluminum alloy with a minimum thickness of 3.15 mm.

- Pavement. Pavement materials shall meet the following requirements:

- Asphalt Pavement. Materials used for asphalt pavement shall conform to Section 401, Asphalt Concrete Pavement for Asphalt Concrete, Type I and shall be approved by the Engineer.

669-3.01 CONSTRUCTION REQUIREMENTS.

- Wiring.

- Referenced Requirements. All wiring shall be installed in accordance with subsection 660-2.09, Wiring.

- Termination. At junction boxes, unused pairs shall be terminated within splices.  At cabinets, unused pairs shall be terminated to a terminal block.  At terminal blocks, all conductors, including unused spares, shall terminate and be soldered to "spade" type terminal lugs.

- Relief. All wiring shall have at least 0.6 m of slack cable in each junction box and at least 1.8 m of slack cable available in the equipment cabinet prior to the terminal block.

- Labeling. All wiring shall be labeled in all junction boxes and at all terminal blocks.

- Conduit.

- Referenced Requirements. All conduit shall be installed in accordance with subsection 660-2.05, Conduit, or as indicated on the Plans.

- Pull Cords. Nylon pull cords shall be left in all conduits larger than 25 mm and in all spare conduits.

- Bushings. Plastic or plastic-sleeved bushings shall be in place before wire pulls are performed.

- Junction Boxes.

- Referenced Requirements. All junction boxes shall be installed in accordance with subsection 660-2.06, Junction Boxes, or as indicated on the Plans.

- Voltage Limitation. Junction boxes used for ATR installations shall not contain any wiring of systems at or greater than 24 V or conduits carrying wiring of systems at or greater than 24 V.

- Terminal Blocks.

- Terminal Block Placement. Terminal blocks within cabinets shall be mounted so that all terminals are easily accessible from the front of the cabinet.

- Labeling. All terminal blocks and wire pairs shall be clearly labeled on the block.

- Termination. All conductors, including unused spares, shall terminate and be soldered to "spade" type terminal lugs

- Presence Loops.

- Referenced Requirements. All presence loops shall be installed and constructed in accordance with subsection 660-3.08, Installation Details, unless otherwise specified on the Plans.

- Placement Design Adherence. The Plans are not schematics; installation of the presence loops shall closely conform to the location and layout of conduit runs shown in the Plans.

- Presence Loop Dimensions. Unless otherwise noted, presence loops shall be formed of four turns of wire, and shall be 1.83 m square with plus-or-minus 25mm (± 25mm) tolerance.

- Lead-in Conduit. All lead-in conduit from edge of pavement to the presence loops shall be straight and perpendicular to the center line of the road.

- Presence Loop Alignment. Presence detector loops shall be centered in the traffic lane plus-or-minus 25mm (± 25mm) tolerance.

- Presence Loops in Asphalt.

- Presence Loops In Existing Asphalt. All presence loops installed through existing asphalt pavement shall be installed using full-lane-width cuts a minimum of 2.43m in length.  Inductive loops shall be centered in the 2.43m cut and spaced a minimum distance of  0.3 m from the edge of the cut. All edges of the cuts shall be heated and tack-coated during patching to ensure full adhesion. All full-width patches shall be rolled sufficiently to ensure compaction equal or better than the existing asphalt, and to prevent edge ridges or settling of the patch from 'telegraphing' through the final lift asphalt.

Compaction tests shall be required at the discretion of the Project Engineer.

- Presence Loops In New Asphalt. All loops installed in new asphalt paving shall be installed immediately prior to final paving of the particular section of road. Installation of loops after final lift paving shall not be permitted.

- Cabinets.

- Cabinet Placement and Orientation. All Cabinets shall be installed out of the clear zone and with the doors facing away from the road.

- Conduit Entry. All conduits entries for any above-ground enclosure shall be made through the bottom of the enclosure.  No conduit runs shall be cut through the sides or top of any above-ground enclosure.

- Style CBA1 Cabinets.

- Mounting. The Style CBA1 cabinets shall be mounted on a 63mm perforated steel tube and supported with a sleeved concrete foundation as shown on the Plans.

- Terminal Blocks. Terminal blocks in CBA1 cabinets shall be mounted vertically as shown on the Plans.

- Asphalt Pavement Smoothness: There shall be no transverse seams, joints or roughness within 15.24 m of any inductive loops placed in asphalt pavement section. The finished surface of the asphalt shall be tested with a straightedge 3 m long. The surface shall not vary more than 6 mm from the lower edge of the straightedge within 15.24 m of all sensors at the ATR installations. At the discretion of the Engineer, a profilograph equipped with a chart recorder shall be run along each wheelpath of each lane. The profilograph will be supplied by the Highway Data Section and shall be operated by your personnel.  Each profilogram shall extend 15.24 m beyond either end of the ATR installation. The asphalt surface as recorded by the chart recorder shall not vary more than 6 mm in 3 m of distance.

- Field Inspection. Before installation of conduit, wiring, inductive loops or cabinets, you shall notify the Engineer. Notification shall be given in writing, a minimum of 3 working days prior to installation (excluding Saturday, Sunday and State or Federal Holidays).  The Engineer shall be present to approve the installation prior to final burial or encasement. Any unacceptable installations shall be corrected and re-inspected for completeness prior to burial or encasement. Any burial or encasement without approval by the Engineer shall be uncovered, removed, and/or replaced at your expense. Any expense or delay in the project scheduling will be the responsibility of you.

669-3.02 ACCEPTANCE TESTING. Perform acceptance testing on all ATR installations.

- General Tests. You shall perform tests for the ATR installations in accordance with subsection 660-3.08, Installation Details.

669-3.05 DELIVERABLES. All deliverables shall be submitted to the Engineer prior to final approval of the work or as otherwise called for herein.

- Materials Submittal.

- Format and Contents. Provide a Materials Submittal of proposed equipment and materials for the ATR installations.  The Materials Submittal shall consist of three collated copies of an equipment and materials portfolio.  Each identical portfolio shall contain information of sufficient detail to determine the suitability of the equipment and materials proposed.

- Table of Contents. Each portfolio shall include a table of contents listing each item's intended uses, item description, product name, manufacturer, model or part number and reference to associated information within the portfolio.

- Reference Drawings. The Materials Submittal shall include a detailed shop drawing of each equipment cabinet showing the location of all mounted components.

- Delivery Interval. The Materials Submittal shall be delivered for review and approval of the Engineer within thirty days following award of the contract.

- Liability. The State of Alaska will not be liable for any materials purchased, labor performed, equipment used or delay to the work before all equipment and materials have been reviewed and approved.

- As-Built Plans.

- Prepare four complete sets of as-built plans which will be current with the construction. These as-built plans shall detail all construction changes made to the ATR design and include the following information on the appropriate sheets:

- location and depth of all inductive loops, piezo sensors, conduit runs and scales.

- locations of all equipment cabinets and junction boxes.

- station and offset of all junction boxes

- Three sets of as-built plans shall be presented to the Engineer, and one set shall be affixed to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation in a waterproof, clear plastic holder.

- Redlines of full size construction plans will be acceptable as-builts.

- Photographs.

- Provide photographic prints, 35 mm negatives and Kodak PictureCD format CDROMs documenting all sensor installations.

- Photographs, negatives and CDROMs shall be delivered organized in one or more white colored, D-ring style, 3 ring binders with clear insert overlays on fronts and spines. Photographs and negatives will be mounted in archival quality polypropylene pocketed sheets. CDROMs will be placed in CD storage sheets inside the binders.

- The photographs shall be 127 mm x 178 mm color prints.

- Each photograph shall be labeled with the identification of its subject. ATR station and device designation as indicated on the Plans will be used as identification whenever possible (example: H1 - W1NLA ).  Labels will be photographed with the subject and will be rendered large enough to be read with the unaided eye.

- The photographs shall show the inductive loops and conduit in place prior to covering with gravel and pavement for asphalt pavement sites, or prior to covering with epoxy compound for concrete pavement sites. The photographs shall include:

- two or more overall views of each ATR installation showing placement of the inductive loops.

- one or more views of each loop showing the loop and the conduit to the nearest junction box

- Test Results. Written or printed copies of the final results of all tests, signed by you, shall be provided to the Engineer prior to acceptance of the Automated Traffic Recorder Installation. Tests will be conducted in accordance with subsection 660-3.08, Installation Details.

- Manuals. Provide the Engineer all installation, repair and operation manuals for all Automated Traffic Recording equipment, telemetry equipment, dataloggers, and environmental sensors.

- Materials.

- Provide the Engineer any ATR equipment, sensors, and all epoxy grout remaining after installation.

- You shall palletize the Deliverable Materials.

- You shall group the contents of each pallet by like items.

- You shall attach to each pallet a sealed plastic pouch containing complete copies of all Material Safety Data Sheets that apply to the contents of that pallet.

- You shall provide an itemized list of all Deliverable Materials. For each item, the list shall detail:

- Item description: including nature of the item, brand name, manufacturer name, model number, type number and serial number.

- Item condition

- Item quantity

- You shall provide complete copies of all Material Safety Data Sheets that apply to the Deliverable Materials. You shall attach these Material Safety Data Sheets after the last page of the Deliverable Materials list.

669-4.01 METHOD OF MEASUREMENT. The quantity to be paid for will be the actual number of completed and accepted Automated Traffic Recorder Installations as shown on the Plans or as directed by the Engineer.

669-5.01 BASIS OF PAYMENT. The contract unit bid price for all Automated Traffic Recorder installations shall be full compensation for furnishing all equipment, labor and materials necessary to complete the work as specified, with the following exceptions:

1.	Backfill materials required will be paid for under their respective pay items.

2.	Asphalt required will be paid for under a separate pay item.

Excavation, as-built plans and acceptance testing required for these installations will not be paid for separately, but will be subsidiary to the Automated Traffic Recorder Installations.

All Type IA J-Boxes, 27 mm rigid conduit, and 53 mm rigid conduit associated with the Automated Traffic Recorders are subsidiary to the 669 items. Traffic Control required to install Automated Traffic Recorders is paid for under 643 items.

WITHHOLDING.  To ensure full compliance under this section, twenty percent (20%) of the amount for Item 669(1) shall be withheld until all deliverables have been provided to the Engineer and approved by the highway data section in writing.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 669(1) Automated Traffic Recorders H1, H2 | Lump Sum |

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Delete Item 4 in its entirety and substitute the following:

4. Methyl Methacrylate Pavement Markings.  Apply Methyl Methacrylate markings with truck-mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.  Provide the manufacturer’s installation instructions for the Methyl Methacrylate markings at least 15 days prior to application.  Retain a copy of the instructions for use on the project.

A manufacturer’s representative shall be present on the first day of striping and any additional days as required by the Engineer.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in liters.

Perform a film test strip at the beginning of each striping shift and when there is a change in asphalt type.   In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion.

Apply glass beads as specified in Subsection 712-2.18. Use a minimum drop on rate of 580 g/m2 for transverse type markings.  Apply glass beads for Type V sprayed material by double bead gun, one gun directly in front of the spray unit and another directly behind.

Remove contaminants such as curing agents, surface oils or existing pavement marking materials prior to applying the new pavement markings. Then, thoroughly clean and dry the roadway surface immediately prior to applying Methyl Methacrylate pavement markings.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 60 mils (1.5 mm).

#### METHYL METHACRYLATE PAVEMENT MARKING

#### YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 | Inlaid Markings2 |
| --- | --- | --- |
| ##### Longitudinal Type3 ##### (Center and Edge lines) | 2.3 mm | 5.8 mm |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 3.0 mm | 5.8 mm |
| Neutral Area (Diagonals, Chevrons) | 1.5 mm | Do not inlay these markings |

1. Measure Type V spray without glass beads.  Tolerance is ±0.1 mm.  Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 150 mm x 300 mm flat sheet of 2 mm thick aluminum placed in the path of the striping guns.

2. Cut the inlaid slots to a depth of  6.35 mm.  Do not over fill the slots.

3.  Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 1.5 mm per application pass.

Non-Inlaid Markings

New asphalt pavement:  Apply interim non-inlaid Longitudinal and Transverse Type markings at 0.75 mm.

Unless directed otherwise by the Engineer, apply the final 1.5 mm of the Longitudinal Type markings once the asphalt has cured for the duration listed below.

Stone Mastic Asphalt Concrete	30 days

All others				15 days

Apply the final Transverse and Neutral Area markings as shown in the application table at this time.  Multiple application passes are required for Transverse Type markings.

Existing asphalt pavement:  Apply markings according to the Yield Thickness Table.  Longitudinal Type markings will require multiple application passes.

Inlaid Markings

Apply markings in the milled groves after all millings have been removed. The extruded Methyl Methacrylate may be installed at the final yield thickness at the Engineer’s discretion.

670-3.04 PAINT REMOVAL. Change the title of this subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.05 PRELIMIINARY SPOTTING. Add the following:  Prior to striping operations, the Engineer will review the passing/no passing zones shown on the Plans.  The Engineer shall modify the zones in accordance with Chapter #3 of the ATM if needed.  There shall be no adjustment to the lump sum price as a result of this review.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width in any 15m longitudinal run from the plan quantity.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 4:

5.	Liter Basis:  The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in liters.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B).  No separate payment shall be made for furnishing and maintaining the MMAMS.

(08/21/02)R246

Payment will be made under:

| #### Pay Item | #### Pay Unit |
| --- | --- |
| 670(10B) Methyl Methacrylate Pavement Markings | Liter |

# Add the following Section 	SECTION 680

## CONDUITS AND MANHOLES INSTALLATION FOR TELPHONE

# Special Provisions

680-1.01 DESCRIPTION.  This work consists of furnishing and installing a conduit system with manholes in accordance with the Specifications and the  “UT” plan sheets.

This work includes installing 100 mm (4”) Schedule. 40 PVC conduits and installing 1.8 m by 1.8 m, by 1.8 m (72”x72”x72”) Manholes. This work includes furnishing labor, material (except the two manholes supplied by TelAlaska as stated in 680-2.01), devices, and all appurtenances required to install, support, secure and provide a complete system for supporting and protecting the Telecommunication cables.

This work also includes providing two sets of redlined as-built drawings in accordance with the conditions prescribed herein. TAI representatives will inspect and accept this work through the Engineer.

For the purpose of these specifications, “TAI” shall mean TelAlaska Inc., which owns and operates underground and overhead facilities along the existing highway through the length of the project.

Coordinate with TAI to ensure that all existing cables have been temporarily relocated prior to start of work on the temporary detour road and bridges. You are responsible for all surveying and staking of the detour road prior to TAI working on the temporary relocation in the area.

680-1.02  CODES AND STANDARDS.  Furnish conduit materials and devices in accordance with the applicable standard of ANSI, ASTM, NEMA,UL, AND ALL LOCAL CODES AND PERMITS. Install conduit components in accordance with applicable requirements of the NEC.  If there are conflicts between the codes/standards listed above and these Specifications, these Specifications shall govern. Ensure all materials, devices, and practices are in accordance with the applicable requirements of the Federal “ Occupational Safety and Health Standards.”

680-2.01 MATERIALS.  Provide Schedule 40 PVC or high-density polyethylene (HDPE) conduits with a minimum wall thickness in accordance Table 2 of ASTM D 3035 [DR-13.5 (0.333-inch)].

Leave 6.35 mm (0.025”) Greenlee Polyline #430/21481 pull cords or Omni glide pull line rated at 226.8 kg (500 lb) in all the conduits. TAI must approve all plastic end plugs prior to installation.

TAI will furnish the two 1.8 m by 1.8 m, by 1.8 m Manholes, manhole rings, grates and covers as required. These materials will be available at TAI’s Cable Yard on Nash Road near Rabbit Run. Coordinate with Mr. Robbie Nash at Tel: (907) 224-5224 to arrange for a pickup time between 8:00 am and 5:00 pm from Monday to Friday. You are responsible for providing the applicable equipment to load the manholes onto your delivery truck. You shall sign for the two manholes at the time of receipt and are responsible for storing and safekeeping.

Provide all Schedule 40 100 mm (4”) PVC conduits, miscellaneous tools, hardware, devices, material and all other appurtenances required to construct and install the conduit system that are not furnished by TAI.

680-3.01 GENERAL CONSTRUCTION REQUIREMENTS. TAI through the Engineer, reserves the right to suspend the conduit system installation, at any time that you fail to meet the requirements set forth herein, until such time that you make the necessary corrections. Suspension of work will not entitle you an extension of time for the completion of the project, and will not entitle you extra payment for costs incurred.

You are responsible for locating, shoring and protecting all property in the vicinity of the project. You are responsible for establishing the location of each facility by calling for field locates in accordance with Subsection 105-1.06, Cooperation with Utilities.

680-3.02 GENERAL INSTALLATION REQUIREMENTS. Grade the trench bottom smooth. Native materials may be utilized for the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07,Selected Material.  Native backfill material shall be placed in layers and compacted as directed by the Engineer and in accordance with Section 680-3.07 Backfill and Compaction.

Dispose of waste excavation in accordance with Subsection 680-3.06, Disposal of waste Excavation.

Maintain a minimum clearance of 300 mm where the conduit passes above or below an underground utility line.

Plug the end of the conduit and mark with an EMS marker. Remove all foreign materials, earth, sand, and gravel from the conduit. You and the Engineer shall measure the wall-to-wall distance of the installed conduit, and record that measurement onto the drawings provided by the Engineer.

680-3.03 CONDUIT INSTALLATION. The scope of work for installing 100 mm (4”) Schedule. 40 PVC or HDPE (if applicable) conduits as shown in the “UT” plan sheets includes the following:

- Install two 100 mm (4”) Schedule 40 PVC conduits along the eastside of Seward Highway from MH28 at “C” Station 5+400 to MH31 at Station 6+175. Install the two conduits from Station 5+457 to 6+175 in the same trench as the GCI conduits (see GCI’s Trench Detail for Item 684(1)). Attach these two 100 mm conduits to the designated diaphragms of the Resurrection River bridges using hangers as shown in the bridge plans. The conduit is located along the right edge of the proposed pathway as shown on the “UT” plan sheets.

- Install one 100 mm Schedule 40 PVC conduit attached to the eastside of the bridges at the Clear Creek, the Salmon Creek, and the Bear Creek.  Place both ends of the conduit outside the pathway.

Furnish all materials (except the materials furnished by TAI as stated in Section 680-2.01 Material), devices, labors, and all appurtenances required for the proper installation of the conduit system.

You have the option to install the conduit system by trenching or plowing for the entire project.

All HDPE conduits (if applicable) shall be one continuous piece from pedestal to pedestal or from manhole to manhole. All cuts, joints, and placements shall meet the manufacture’s requirements and be acceptable to TAI’s inspector or the Engineer.

Maintain a minimum clearance of 300 mm where the conduit passes above or below an underground utility line. Place the conduit at the exact grade or depth shown in the “UT” plan sheets. Keep all HDPE (if applicable) conduits away from sunlight as required to prevent curvature and deterioration due to the thermal expansion and ultraviolet degradation. Do not install defective conduit.  Remove all defective conduit from the work site immediately.

Excavate trenches to provide a cover of at least 1.2 m over the conduit; formation including top protection should be employed unless otherwise approved by the TAI representative or the Engineer.

Level the trench bed to provide an even base prior to installing conduit.  In some cases, it may be necessary to provide sand or fine earth to establish an even base.  The TAI representative or the Engineer shall determine whether a concrete base is required if upon excavation, the trench bed appears incapable of firmly supporting the conduit.

Keep backfill next to the conduit free from stones or other material that might damage the conduit or conduit joints. Do not include large boulders in any part of the backfill.  Use extreme care while tamping the backfill at the sides of conduit to avoid damage to the joints or shifts in the conduit structure. Backfill and tamp alongside the conduit in maximum layer thicknesses of 50 mm until the backfill reaches the top of the conduit.  Use PVC Glue at all joints.

Clean and test the conduit system in accordance with Section 680-3.04 Testing of Conduit prior to TAI installing their facilities inside the conduit.   Plug each end of the conduit and mark with an EMS marker. Place Greenlee Polyline #430/21481 pull cord or Omni glide pull line inside the conduits. You and the TAI inspector or the Engineer shall measure the wall-to-wall distance of the installed conduit, and record all measurements onto the drawings provided by the Engineer.

Maintain a complete and accurate record of conduit offsets and sequential conduit distances and supply the Engineer with a complete log within five (5) days after the installation of the conduits.

680-3.04 TESTING OF CONDUIT.   Clean and test the conduit after installation and compaction of the backfill embankment.  The minimum cover is 1.22 m.  Plug the ends of conduit which is not used or tested immediately.  Notify TAI at least five (5) calendar days in advance of the testing any conduit.  Coordinate with TAI so that their inspector will be on site during conduit testing.

You must be able to pass a rigid mandrel through the conduit as a clearance test.  The mandrel must be longer than 300 mm (12”) with a diameter of at least 75 mm (3”).  The acceptance of the conduit installation is based on, but not limited to, the above requirements.

680-3.05  INSTALLATION OF MANHOLE. Install two 1.8 m by 1.8 m by 1.8 m (72” x 72” x 72”) manholes in the specially built 2 m by 3 m “Manhole Landing” on the eastside of the pathway as shown on the “UT” plan sheets. You are responsible for the installation, pickup, delivery, repair, and maintenance of these manholes until their installation is accepted by TAI’s inspector.

Excavate enough material to accommodate the outside dimensions of the manhole plus a minimum clearance of 300 mm on every side of the structure.  Provide a minimum of 300 mm of base material at the bottom of the excavation to insure uniform distribution of soil pressure.  Compact and grade the base material level at the elevation shown in the “UT” plan sheets. Excavate all unsuitable material to a depth of 0.30 m below the designed grade of all manholes.  Backfill the excavated bedding with Selected Material, Type A or Aggregate Base Course, Type D-1 as required for the manhole installation and compact to 95 percent of the maximum density.

Use flexible butyl-mastic joint compound between joints of the manholes and along the walls of the grooves.  Prime and seal the frames and covers with primer and gasket sealant (RAMNEK).  Install two 2.44 m (8’) ground rods, one on each end of the manhole excavation, driven from the base level down or at the direction of the TAI inspector. Then, connect the ground rods to the manhole ground wire leaving a 1.83 m (6’) loop of that same wire inside the manhole. Set the manhole frame and cover to the designed finish grade.

Install the manhole (MH29) at “C” Station 5+575 with the center set at 10.74 m right, and manhole (MH30) at Station 5+880 with the center set at 11.2 m right in the designated “Manhole Landing” area or as directed by the TAI inspector. Field verify the locations with the Engineer and TAI inspector for the exact locations and elevations of the manholes, frames, and covers.

The following table summarizes the conduit and manhole installations:

Utilities Conduit Installation Summary

| Sheet | From Sta./Pedestal | To Sta. /Pedestal | Conduit Unit | 680(1) | 680(5) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| UT 1-5 | “C” 5+400 Rt. | “C” 6+175 Rt. | 2 | 1550 |  | Install 2 conduits along the east side of Seward Hwy. From Resurrection River Bridge 1 to Bridge 3 |
| F7 | “C” 7+165 | “C” 7+191 | 1 | 26 |  | Install 1 conduit on the east side of Clear Ck. Bridge. Place both ends of the conduit outside of the pathway. |
| F8 | “C” 10+543 | “C” 10+580 | 1 | 37 |  | Install 1 conduit on the east side of Salmon Ck. Bridge. Place both ends of the conduit outside of the pathway. |
| F10 | “C” 11+579 | “C” 11+595 | 1 | 16 |  | Install 1 conduit on the east side of Bear Ck. Bridge. Place both ends of the conduit outside of the pathway. |
| UT-1 | “C” 5+575, 10.74 m Rt. |  |  |  | 1 | Install 1 1.8 m x 1.8 m x 1.8 m manhole (MH29) |
| UT-3 | “C” 5+880, 11.2 m Rt. |  |  |  | 1 | Install 1 1.8 m x 1.8 m x 1.8 m manhole (MH30) |
|  |  |  |  | 1629 | 2 |  |

680-3.06 DISPOSAL OF WASTE EXCAVATION.  The Engineer shall approve all waste disposals within the project limits. Feather waste disposal areas into the surrounding grounds with no noticeable break or discernible variation, and match the existing drainage patterns.

680-3.07 BACKFILL AND COMPACTION.  Backfill in accordance to Section 203, Excavation and Embankment. Place backfill for conduit installation crossing under roadway or railroad in 200 mm lifts, and compact to 95 percent of the maximum density.

You may backfill areas where large quantities of water are evident with 50 mm to 150 mm lifts of oversized coarse rock over a layer of geotextile fabric.  In areas outside the railroad embankment slope limits, the Engineer shall decide the compaction efforts.  All backfill material shall meet or exceed the requirements of Selected Material, Type A.  The Engineer shall conduct random soil compaction tests at various depths and locations.

680-3.08 SURVEYING AND STAKING.   The proposed conduit alignment is located under the right edge of the pathway as shown in the “UT” plan sheets. The Engineer must approve any changes to the alignment.

680-3.09 BRIDGE HANGER AND ATTACHMENT.  Install bridge hangers and attachment for the placement of the 100 mm (4”) conduit under the new bridge as shown on the bridge plans.  Install bridge hangers every 3.66 m (12’) at the inserts provided.  GCI will supply all the bridge hangers for all the bridges in Phase I of this project.  GCI will charge the Department for all the hangers furnished as needed.  Furnish labor, other materials and devices as required to attach the conduit to the bridge.

680-3.10 CONCRETE BASE/SLURRY.   A concrete base and/or slurry is required in areas where the trench bed is incapable of supporting the conduit firmly.  The concrete mixture shall contain a minimum of 5 ¼ standard 42.68 kg sacks of cement per cubic meter (4 standard 94 lb sacks of cement per cubic yard) of concrete. Place the concrete slurry when the air temperature is 0° C (32° F) or above. Propose alternate methods to ensure an adequate curing temperature will be met if the air temperature is below 0° C (32° F).  These methods are subject to approval by the Engineer and may include using concrete additives, additional cement, warming blankets, and others.

680-3.11 SAND BEDDING.  Where existing material is determined unsuitable for bedding the conduits and manholes by the TAI inspector, provide bedding sand meeting the following requirements:

Sieve Size	Present Passing by Weight

6.25 mm (¼”)	100 %

0.075 mm (No. 200)	0 – 6 %

680-4.01 METHOD OF MEASUREMENT.   All surveying and staking required for the 680 Items will be measured as indicated in Section 642.

Item 680(1). By the meter of conduit installed and accepted by the Engineer.  The TAI representative and the Engineer shall measure the horizontal distance of conduit installed.

Item 680(2). No measurement will be made.

Item 680(5).  By each unit installed and accepted by the Engineer.

680-5.01 BASIS OF PAYMENT.   If unsuitable material is encountered and excavated below the conduit elevation, Selected Material, Type A material used for the backfill will be paid under Item 203(6A) Borrow, Type A.

Item 680(1). At the contract unit price for the length of conduit accepted by the Engineer.  Payment shall be full compensation for all labor, equipment, tools, materials and incidentals necessary to install the complete conduit system in accordance with the Specifications and “UT” plan sheets.

This includes, but is not limited to, the following:

- All excavating, trenching, backfilling, compacting, and placing end caps, EMS markers, marker tape, Greenlee Polyline/Omni glide pull line, and tracer wire for the purpose of installing the conduit.

- The complete installation and attachment of the conduit under the new bridge.

Item 680(2).  At the contract lump sum price.  Payment is full compensation for all labor and materials required for establishing two sets of As-Built plans with redlined drawings of the final location of the conduits.

Item 680(5).  At the contract unit price for the number of units accepted by the Engineer.  Payment includes full compensation for all labor, materials, and incidentals required to complete the work as described in the Specifications and shown in the “UT” plan sheets.

This includes, but is not limited to, the following:

- Sand bedding and concrete base/slurry material when needed for the purpose of bedding support

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 680(1) 100 mm Conduit Installation (Telephone) | Meter |
| 680(2) Telephone As-Builts | Lump Sum |
| 680(5) 1.8 m x 1.8 m x 1.8m Manhole Installation | Each |

# Add the following Section 	SECTION 681

ELECTRICAL FACILITIES RELOCATION/RETIREMENT COMPLETE

# Special Provisions

681-1.01 DESCRIPTION.  This work consists of furnishing and installing all the electrical facilities that are required for the relocation, furnishing all labor and appurtenances required to retire all the existing electrical facilities that are impacted by this project. Perform this work in accordance with the Specifications (see Appendix “E” for additional specifications), the staking information and electrical design in the “UE” plan sheets.

This work includes installing an aerial crossing with distribution poles, street lighting systems, a temporary pole inline with the existing overhead facilities, and all items required for the complete relocation and retirement of the electrical facilities.  This work also includes furnishing labor, material, devices, and all appurtenances required to install, support, secure and provide a complete system for supporting and protecting the electrical facilities. The work also includes all appurtenances, parts, and items that are listed in the Appendix “E” Electrical Facilities Relocation.

Provide two sets of redlined as-built drawings in accordance with the conditions prescribed herein. This work shall be inspected and accepted by the representatives of the City of Seward through the Engineer.

For the purpose of these specifications, “COS” shall mean City of Seward, which owns and operates underground and overhead facilities along the existing highway throughout the length of the project.

681-3.01 GENERAL CONSTRUCTION REQUIREMENTS. COS, through the Engineer, reserves the right to suspend the work at any time that you fail to meet the requirements set forth herein, until such time as you make the necessary corrections. Suspension of work will not entitle you an extension of time for the completion of the project, and will not entitle you extra payment for costs incurred.

Solicit bids from the list of qualified electrical contractors approved by COS to perform this electrical facilities relocation work. You are responsible for contacting COS for the list of the qualified electrical contractors.

You are responsible for locating, shoring and protecting all property, real and personal, in the vicinity of the project. You are responsible for establishing the location of each facility by calling for field locates in accordance with Subsection 105-1.06, Cooperation with Utilities.

681-3.02 GUY POLES AND STREETLIGHTS.  Install a streetlight with a 40/3 pole for the aerial crossing of Seward Highway at Station 5+430 right. The work at this location includes a 250W HPS street light (S. L. 2), 45.7 m (150’) of No. 6 DPX conductor, and all the hardware required for the complete installation of a street light system. It also includes retiring an existing street light (S. L. 1), a 35/3 pole, 29 m (95’) of No. 6 DPX conductor, and all the hardware attached to the existing street light system at Station 5+446.

Install a 45/3 guy pole (G.P.2), 36.6 m (120’) of guy wire crossing over the Seward Highway at Station 6+153, anchor, down guy, and all the hardware for the complete installation.  This work also includes retiring an existing 40/2 guy pole (G. P.1), 30.5 m (100’) of guy wire, down guy, anchor and all the existing hardware.

The detailed specifications and scope of work for the above tasks are found in Appendix E, “UE” plan sheet, and the Staking Sheet.

681-3.03 INSTALLATION OF TEMPORARY POLE AND FACILITIES ATTACHMENT.  Install a new temporary Class 70-1 pole (GL27A) for raising the clearance over the Metco driveway at Station 5+868, 17.0 m left.  Attach COS electrical facilities and GCI television facilities to the temporary pole.

The detailed specifications and scope of work for the above tasks are found in Appendix E, “UE” plan sheet, and the Staking Sheet.

681-3.04 SURVEYING AND STAKING.   Place the guy pole, temporary pole, street light and anchor in accordance with the design as shown in the “UE” plans and Staking Sheet.  The COS inspector and/or the Engineer must approve any changes to the location. You are responsible for scheduling a physical check of all staked facilities with COS prior to installation.

681-3.05 AS-BUILT DRAWINGS.  Submit two (2) sets of final red-lined as-built drawings to COS, through the Engineer, prior to final acceptance of the systems.  Maintain an accurate record of the facilities on the prints.  Include all references to the highway centerline, railroad track centerline, and/or existing landmarks in the records.  As-built drawings must be certified and stamped by a licensed surveyor registered in the State of Alaska.

681-3.06 CITY OF SEWARD  INSPECTION.   COS may at any time have access to the project site for the purpose of inspection. Notify COS at least fifteen (15) calendar days prior to the start of this project.  COS will conduct a final inspection within ten (10) calendar days after you have informed them in writing, through the Engineer, that the electrical facilities relocation and retirement has been completed.  Accomplish the incomplete items (punch list), as noted in final inspection report, within ten (10) calendar days of the final inspection.

681-4.01 METHOD OF MEASUREMENT.   All surveying and staking required for the 681 Items will be measured as per Section 642.

Items 681(15) through 681(28). No measurement will be made.

681-5.01 BASIS OF PAYMENT.

Item 681(15).  At the contract lump sum price.  Payment shall be full compensation for establishing two (2) sets of As-Built plans with redlined drawings of the final location of the installed facilities.

Items 681(26A) through 681(27B).  At the contract lump sum price.  Payment shall be full compensation for all labor, equipment, tools, materials and incidentals necessary to complete the electrical facilities relocation and retirement.  All work must be approved by the Engineer. All retired facilities will become your property.

Item 681(28).  At the contract lump sum price.  Payment includes full compensation for all labor and hardware required for the complete installation of the temporary pole and attachment as shown on the “UE” plan sheet and Staking Sheet.

This includes, but is not limited to, the following:

- Attaching the COS and GCI facilities to the temporary pole is subsidiary to Item 681(28).

The Standard Drawings and list of materials required to perform the work for the Street Light System Installation and Retirement, Guy Pole Facilities Installation and Retirement, and the Temporary Pole Facilities Installation are located in Appendix E.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 681(15) Electrical As-Builts | Lump Sum |
| 681(26A) Street Light System Installation Complete | Lump Sum |
| 681(26B) Street Light System Retirement Complete | Lump Sum |
| 681(27A) Guy Pole Facilities Installation Complete | Lump Sum |
| 681(27B) Guy Pole Facilities Retirement Complete | Lump Sum |
| 681(28) Temporary Pole Installation Complete | Lump Sum |

# Add the following Section 	SECTION 684

## CONDUITS AND VAULTS INSTALLATION FOR TELEVISION

# Special Provisions

684-1.01 DESCRIPTION.  This work consists of furnishing and installing a conduit system with inner ducts and vaults in accordance with the Specifications and the plans as shown in the “UTV” plan sheets.

The work includes installing 100 mm (4”) Schedule 40 PVC conduits, 32 mm (1.25”) high-density polyethylene (HDPE) inner ducts, and two 1.200 m by 0.750 m by 0.900 m (48”x 30”x 36”) vaults, and placing GCI aerial facilities on the temporary pole. This work also includes furnishing labor, material (except the materials furnished by GCI as listed in Subsection 684-2.01), devices, and all appurtenances required to install, support, secure and provide a complete system for supporting and protecting the Television cables.

Provide two sets of redlined as-built drawings in accordance with the conditions prescribed herein. This work shall be inspected and accepted by the representatives of the GCI Cable Inc. through the Engineer.

The overhead clearance of the existing GCI cable at Metco driveway will be impacted due to the raising of the roadway grade. You shall initially attach the existing facilities to the proposed temporary pole (installed under Item 681) for overhead clearance prior to constructing the proposed Metco driveway. Install the conduit system from Station 5+400 to 6+187. This work includes installing the bridge hangers to provide attachment of the conduits at the bridge diaphragm of the proposed new bridges.

For the purpose of these specifications, “GCI” shall mean GCI Cable Inc., which owns and operates underground facilities along the existing highway through the length of the project.

684-1.02  CODES AND STANDARDS.  Conduit materials and devices furnished shall be in accordance with the applicable standards of ANSI, ASTM, NEMA,UL, and all local codes and permits. Install the conduit components in accordance with applicable requirements of the NEC.  In case of conflict between the requirements of any of the above referenced codes and standards, and the requirements of these Specifications, the latter shall govern. All materials, devices, and practices shall be in accordance with the applicable requirements of the Federal “ Occupational Safety and Health Standards.”

684-2.01 MATERIALS.  Provide Schedule 40 PVC or HDPE conduits with a minimum wall thickness in accordance Table 2 of ASTM D 3035 [DR-13.5 (.333-inch)].

Furnish sand bedding, and all other materials that are needed to install the conduit system, except the materials furnished by GCI.

GCI will furnish the following materials:

- Two 1.200 m by 0.750 m by 0.900 m (48”x 30”x 36”) vaults

- The required amount of 100 mm (4”) Schedule 40 PVC conduits

- The required length of 32 mm (1.25”) HDPE inner ducts.

- The copper tracer or No. 6 wire

- EMS markers

- End plugs

- Polypropylene pull rope with 680.4 kg (1,500 lb.) tensile strength

- Cable warning tapes

- End bells

- 18-hole cable racks

- Butyl-mastic joint compound

- Gasket sealant (RAMNEK)

- Bridge hangers

- 100 mm (4”) fiberglass conduit

- Fiberglass expansion joint

Coordinate with GCI  (868-8581) at least 48 hours in advance to arrange for delivery from GCI.  You shall sign for materials at the time of receipt and shall be responsible for storing and safekeeping after the pick up from GCI. The GCI warehouse foremen will be available for issuing the requested materials between 1:00 PM to 4:00 PM daily except Saturday, Sundays and GCI holidays. If you pick up materials at times other than normal GCI working hours, you will be billed for the labor time plus a 25 percent overhead charge by GCI.

684-3.01 GENERAL CONSTRUCTION REQUIREMENTS. GCI through the Engineer, reserves the right to suspend the conduit system installation any time you fail to meet the requirements set forth herein, until you make the necessary corrections.  Suspension of work shall not entitle you an extension of time for the completion of the project, and shall not entitle you extra payment for costs incurred.

You are responsible for locating, shoring and protecting of all property (real and personal), in the vicinity of the project. You are responsible for establishing the location of each facility by calling for field locates in accordance with Subsection 105-1.06, Cooperation with Utilities.

You have the option to install the conduit system by trenching or boring for the highway and railroad crossings.

684-3.02 GENERAL INSTALLATION REQUIREMENTS.  Construct the trench so it has a smooth bottom.  Sand bedding around the conduit, as shown on the “UTV” plan, is needed.  You may use native materials for the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07,Selected Material.  Place native backfill material in layers and compact as directed by the Engineer and in accordance with Subsection 684-3.07 Backfill and Compaction.

Dispose of waste excavation in accordance with Subsection 684-3.06, Disposal of waste Excavation.

Maintain a minimum clearance of 300 mm where the conduit passes above or below an underground utility line.

Plug the end of the conduit and mark with an EMS marker. Remove all foreign materials, earth, sand, and gravel from the conduit. You and the Engineer shall measure the wall-to-wall distance of the installed conduit, and record that measurement onto the drawings provided by the Engineer.

684-3.03 CONDUIT AND INNER DUCT INSTALLATION. The scope of work for installing the 100 mm (4”) PVC conduits and 32 mm (1.25”) HDPE inner ducts as shown in the “UTV” plan sheets includes the following:

- Place the 100 mm (4”) Schedule 40 PVC conduit with one cluster of three 32 mm (1.25”) HDPE inner ducts inside along the east side of highway from the existing pole at Station 5+455 left to the existing pole at Station 6+203 left (with underground crossing the highway at Station 5+457, 5+912 and 6+187). From Station 5+457 to Station 6+175 GCI’s 100 mm conduit will be installed in the same trench with the two Telalaska conduits  (see Trench Detail in the “UTV” plan).

- Install a 100 mm fiberglass conduit with attachments to the hangers at all three Resurrection River bridges. Fiberglass conduit will be furnished by GCI.

- Trench or bore across the Seward Highway at Station 5+457, 5+912 and Station 6+187 to install the conduits and inner ducts.

- Continue installing the conduits parallel to the highway from the vault at Station 6+006, 16.0 m right southward to Station 5+980, 16.0 m right.  Continue installing by “field fit” as directed by the GCI inspector from Station 5+980 to the existing GCI CC AMP pedestal at the right side of railroad track near Station 5+980.  Some hand digging under the railroad tracks may be required.

- Place bridge hangers at the designated bridge bays for all the conduit installation at the bridges of Resurrection River (1,2,3), Clear Creek, Salmon Creek, and Bear Creek.

- Place fiberglass conduit in the bridge hangers at the inner bay of the three Resurrection River bridges.

Furnish all materials (except the materials furnished by GCI as listed in Section 684-2.01), devices, labors, and all appurtenances required for the proper installation of the conduit system together with the inner ducts and vaults.

Coordinate with GCI to arrange proper timing for GCI to install its pedestals and load center as shown on “UTV” plan.

Install all HDPE conduits as one continuous piece from vault to vault or pedestal. All cuts, joints, and placements must meet the manufacture’s requirements and be acceptable to the GCI inspector and the Engineer.   Provide sand bedding in accordance with the “UTV” plan if needed.

Maintain a minimum clearance of 300 mm where the conduit passes above or below any underground utility line.  Place the conduit at least 1,200 mm below the road surface and ditch bottom when crossing the DOT&PF’s road and ditch prisms.  Shade all HDPE conduits from the sunlight as required to prevent curvature and deterioration due to the thermal expansion and ultraviolet degradation. Do not install defective conduit.  Remove defective conduit immediately from the site of work.

Construct the trench to obtain a minimum cover of 1,200 mm over the conduit and formation (including top protection where employed) unless otherwise approved by the GCI inspector.

Level the trench bed and provide sand bedding to establish an even base for supporting the conduits.

Do not include large boulders in any part of the backfill.  Use extreme care while tamping the backfill at the sides of conduit to avoid damage to the joints or shifts in the conduit structure. Backfill and tamp alongside the conduit in maximum layer thicknesses of 50 mm until the backfill reaches the top of the conduit.

Clean and test the conduit and inner duct system in accordance with Section 684-3.04 Testing of Conduit and Inner Duct prior to GCI installing their facilities inside the conduit.   Plug each end of the conduit and mark with an EMS marker. Place polypropylene pull rope (provided by GCI) inside the ducts. You and the GCI inspector or the Engineer shall measure the wall-to-wall distance of the installed conduit, and record all measurements onto the drawings provided by the Engineer.

Maintain a complete and accurate record of conduit offsets, depths, and sequential conduit distances. Supply the Engineer with a complete log of sequential distances on a per reel basis within five (5) days after the installation of each reel of conduit.

The following table summarizes GCI facility installations:

GCI Facilities Installation Summary

| Sheet | From Station | To Station | Unit | 684(1) | 684(4) | 684(5) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| UTV 7-15 | 5+400 | 6+203 | 1 | 950 |  |  | Install a 100 mm PVC conduit. Include three road crossings (Sta. 5+457, 5+926 & 6+203) |
| UTV 7-15 | 5+400 | 6+203 | 3 |  | 2850 |  | Install three runs of 32 mm (1.25”) innerduct (HDPE) inside the above mentioned 100 mm conduit. |
| UTV 6-8 | 6+060 | 20.8 m |  |  |  | 1 | Install one 1.2 m x 0.75 m x 0.9 m (48” x 30” x 36”) vault. |
| UTV 6-8 | 6+187 | 18 m |  |  |  | 1 | Install one 1.2 m x 0.75 m x 0.9 m (48” x 30” x 36”) vault. |
|  |  |  |  | 950 | 2850 | 2 |  |

684-3.04 TESTING OF CONDUIT AND INNER DUCT.  Clean and test the conduit upon completion of installation and compaction of the backfill embankment.  Provide a minimum cover of 1.22 m above the conduit.  Plug the ends of conduit which are not used or tested immediately. Notify GCI at least five (5) calendar days in advance of any testing.  Coordinate with GCI so that the inspector from GCI will be on site during the testing of the conduit.

You must be able to pass a rigid mandrel through the conduit as a clearance test.  The mandrel must be longer than 300 mm (12”) with a diameter of at least 75 mm (3”).  The acceptance of the conduit installation is based on, but not limited to, the above requirements.

684-3.05 INSTALLATION OF VAULT.  Install two 1.2 m by 0.750 m by 0.900 m (48”x 30”x 36”) vaults as shown on the “UTV” plans. You are responsible for the cost of transportation, installation, repair, and maintenance of the subject vaults until the GCI inspector has accepted the vaults installations.

Excavate enough to accommodate the outside dimensions of the vault plus a minimum of 300 mm clearance on every side of the structure.  Prior to setting, provide a minimum of 300 mm of base (sand bedding) material at the bottom of the excavation to insure uniform distribution of soil pressure.  Compact and grade level the base (sand bedding) material at the elevations shown in the “UTV” plan. Excavate all unsuitable material to a depth of 0.3 m below the designed grade of all vaults.  Backfill the excavated trench with Selected Material, Type A or Aggregate Base Course, Type D-1 as required for the vault installation and compact to 95 percent of the maximum density.

Use flexible butyl-mastic joint compound between joints of the vaults and along the walls of the grooves.

Conduct field verification with the Engineer and GCI inspector for the exact locations and elevations of the vaults, frames, and covers. Prime and seal the frames and covers with primer and gasket sealant (RAMNEK). The vault frame and cover shall be set to the designed finish grade.

Install one vault each at Station 6+006, 18 m right and Station 6+187, 20.8 m right or as directed by GCI inspector.

684-3.06 DISPOSAL OF WASTE EXCAVATION.  The Engineer shall approve all waste disposal within the project limits. Feather waste disposal areas into the surrounding ground with no noticeable break or discernible variation while matching the existing drainage patterns.

684-3.07 BACKFILL AND COMPACTION.  Backfill in accordance to Section 203, Excavation and Embankment.  Backfill conduit installations crossing under roadways or railroads in 200 mm lifts and compact to 95 percent of the maximum density.

You may backfill areas where large quantities of water are evident with 50 mm to 150 mm lifts of oversized coarse rock over a layer of geotextile fabric.  In areas outside the railroad embankment slope limits, the Engineer shall decide the compaction efforts.  All backfill material shall meet or exceed the requirements of Selected Material, Type A.  The Engineer shall conduct random soil compaction tests at various depths and locations.

684-3.08 SURVEYING AND STAKING.    Conduit alignment shall be in accordance with the design as shown in the “UTV” plan sheets.  The Engineer must approve any changes to the alignment.

684-3.09 BRIDGE HANGERS:  Install bridge hangers along the east side of the three Resurrection River bridges, the Salmon Creek bridge, the Clear Creek bridge, and the Bear Creek bridge. GCI will furnish all the hangers for all the utilities to attach their facilities to the bridge. Install a bridge hanger on a 3.66 m (12’) spacing interval.

684-3.10 TEMPORARY POLE AND ATTACHMENT: Attach existing GCI facilities to the proposed temporary pole (GL27A) at Station 5+868 near the Metco driveway.

684-4.01 METHOD OF MEASUREMENT.   All surveying and staking required for the 684 Items will be measured as per Section 642.

Item 684(1). By the meter of conduit installed and accepted by the Engineer.  The GCI representative and the Engineer shall measure the horizontal distance of conduit installed.

Item 684(4).  By the meter of inner ducts installed and accepted by the Engineer.

Item 684(5).  By each unit installed and accepted by the Engineer.

Item 684(2).  No measurement will be made.

684-5.01 BASIS OF PAYMENT.  All surveying and staking required for the 684 items shall be paid for under Item 642(2), Construction Surveying.

If unsuitable material is encountered and be excavated below the conduit elevation, Selected Material, Type A used for the backfill will be paid under Item 203(6A) Borrow, Type A

Installing the proposed temporary pole (GL27A) at Station 5+868 near the Metco driveway shall be paid for under Item 681(28) for the City of Seward’s facilities. Attaching the GCI facilities to the temporary pole is subsidiary to Item 681(28) and no extra payment shall be made.

Items 684(1) and 684(4).  At the contract unit price per meter as described in Subsection 684-4.01.  Payment shall be full compensation for all labor, equipment, tools, materials and incidentals necessary to install the complete conduit/inner duct system approved by the Engineer.

This includes, but is not limited to, the following:

- All excavating, trenching, backfilling, sand bedding (material and labor), compacting, placing end caps, EMS markers, pull rope, and copper tracer wire (or #6 wire) for the purpose of installing the conduit.

- The complete installation of bridge hangers and attachment of conduits to the bridges.

- Installing the 100 mm fiberglass conduit with attachments to all three Resurrection River bridges

- Hand digging required under the railroad tracks near Station 5+980.

- Placing fiberglass conduit in the bridge hangers at the inner bay of the three Resurrection River bridges.

Item 684(2).  At the contract lump sum price.  Payment shall be full compensation for all labor, materials, and incidentals required for establishing two sets of As-Built plans with redlined drawings of the final location of the conduits.

Item 684(5).  At the contract unit price per each unit installed and accepted by the Engineer.  Payment shall be full compensation for all labor, materials, and incidentals required to install the vaults as detailed in the Plans and Specifications.  The labor and material required to construct sand bedding for installing vaults is subsidiary to Item 684(5) and no additional payment shall be made.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 684(1) 100 mm Conduit Installation (Television) | Meter |
| 684(2) Cable TV As-Builts | Lump Sum |
| 684(4) 32 mm Inner Duct Installation | Meter |
| 684(5) 1,200 mm x 750 mm x 900 mm Vault Installation | Each |

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENTS. Add the following: Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T 53 and ASTM D 5801 assigned to each grade.

Performance Graded Asphalt Cement

Property	Standard	PG 52-28	PG 58-28	PG 64-28

Softening Point	AASHTO T 53	(none)	49oC	52oC

Toughness (min)	ASTM D 5801	(none)	12.4 N-m	12.4 N-m

Tenacity (min)	ASTM D 5801	(none)	8.5 N-m	8.5 N-m

(9/18/00)R244M98

SECTION 703

AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

Standard Modifications

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material. (06/25/99)M 82

- SECTION 705

- joint materials

705-2.02  JOINT SEALER.  Delete Item 1. and substitute the following:

- Silicone joint sealer.  Use one of the following:

##### Roadware Ureaseal

Dow Corning XJS Expansion Joint Sealant

Watson Bowman Two Part Silicone Joint Sealant

Or approved equal.

Install according to manufacturer’s recommendation.

# SECTION 706

# CONCRETE AND PLASTIC PIPE

Standard Modifications

706-2.07 CORRUGATED POLYETHYLENE PIPE. Replace “Type S” with “Type S or Type D”.

(02/08/01)M 97

SECTION 710

FENCE AND GUARDRAIL

# Special Provisions

### Delete Item 710-2.03 CHAIN LINK FABRIC in its entirety and replace with the following:

710-2.03 CHAIN LINK FENCE.  Chain link fabric, posts, rails, ties, bands, rods, and fittings and hardware conform to AASHTO M181, Type I.  Posts and rails are Grade 1.  Chain link fabric is 9 gage with 50mm-mesh size.

710-2.11 GUARDRAIL TERMINALS. Add the following:

Use the ET-2000 LET.

The current guardrail end terminal drawings approved by the Department are as follows:

# Drawing	Original	Latest

# Number	Date	Revision	Comments

# ET-2000 LET Metric	SS 155M	7/18/00	None	11.4 m, 7 tube, Plus head

# English	SS 155	5/18/00	None	37.5’, 7 tube, Plus head

# (01/22/02)R249

SECTION 712

MISCELLANEOUS

##### Special Provisions

712-2.14 PREFORMED PAVEMENT MARKINGS. Add the following to paragraph A. under Item 1., General Requirements: The preformed ribbon shall consist of one solid piece of required width and length. In solid stripe areas, the tape length shall, where possible, be a minimum of 30 m. (7/15/96)R79M

712-2.17 METHYLMETHACRYLATE PAVEMENT MARKINGS. Add the following subsection:

2.	Performance Properties: Add the following:

k.	Adhesion: 	To Portland Cement, minimum 13.8 MPa, to asphalt, dependent on tensile failure of the substrate.

(09/04/01)R221M98

- SECTION 715

- STEEL FOR PILES

Special Provisions

Delete this Section in its entirety and replace with the following:

715-2.01 SCOPE.  Steel and fabrication of Structural Steel Piles.

715-2.02 GENERAL REQUIREMENTS.

Use rolled shape piling that matches the shape description shown on the Plans.

Use cylindrical steel piles, as shown on the Plans, fabricated according to American Petroleum Institute (API) Specification 2B using the structural steel specified on the Plans, or API 5L Grade X52 PSL2 with the following requirements:

- Do not use spiral welds.

715-2.03 CERTIFICATION.  Furnish 4 copies of a certified mill test report covering chemical and physical tests conducted on the steel to the Department for each heat number of metal included in the shipment.

# Section 722

# Bridge Railing

722-2.01 Bridge Railing.

Delete and replace with the following:

| Steel tube rail elements | ASTM A500, Grade B |
| --- | --- |
| Steel Thrie Beam elements | AASHTO M180 |
| Posts | ASTM A36M |
| Machine bolts, cap screws, nuts and washers | ASTM A307M |
| High strength bolts, nuts and washers | AASHTO M164 and Subsection 716-2.03 |
| Anchor studs | AASHTO M169, Grade 1015 or 1020 |
| Shims, plates and sleeves | ASTM A36M |
| Galvanize steel portions of railing after fabrication | Meet AASHTO M111 or M232, whichever is applicable. |
| Stainless steel bolts, nuts and washers | ASTM F 593, Alloy Group 1, Condition SH |

## SECTION 724

#### SEED

# Special Provisions

724-2-02. MATERIALS. Delete this Subsection in its entirety and substitute the following:

Meet applicable requirements of the State of Alaska Seed Regulations, 11 AAC 34, Article 1 and Article 4.

Furnish “certified seed” or 4 signed copies of a report certifying that each lot of seed has been tested by an approved laboratory within 9 months of date of application. Include: name and address of laboratory, date of test, lot number for each kind of seed, and results of test as to name, percentages of purity and germination, and percentage of weed content for each kind of seed furnished.

Meet or exceed the percentages of sproutable seed specified in Table 724-1.

TABLE 724-1

Seed Requirements

| SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(03/05/02)R52M98

SECTION 726

TOPSOIL

#### Special Provisions

726-2.01 TOPSOIL. Replace Item No. 3 with the following:

TABLE 726-1

TOPSOIL REQUIREMENTS

| REQUIREMENT | CLASS A | CLASS B |
| --- | --- | --- |
| Sieve Designation | Percent Passing by Weight |  |
| 75 mm | - | 100 |
| 12.5 mm | 100 | - |
| 4.75 mm | 95-100 | 75-100 |
| 1.18 mm | 64-90 | 50-95 |
| .075 mm | 30-60 | 20-80 |
| Organic Content* | 10% - 40% | 5% minimum |
| Limestone | 3.4 Mg/hectare | - |

*   Determined by loss on ignition of oven dried sample in accordance with ALASKA FOP for AASHTO T 267

(12/05/01)R139M98

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01 EMBANKMENT SEPARATION AND REINFORCEMENT.  Under 1. Separation, replace ‘(medium survivability)’ with: ‘(Class 3)’.  Under 2. Reinforcement, replace ‘Separation (high survivability)’ with: ‘Stabilization’.

729-2.02 SUBSURFACE DRAINAGE AND EROSION CONTROL.  Under 2. Erosion control, replace ‘Meet AASHTO M 288 for Erosion Control’ with: ‘Meet AASHTO M 288 for Permanent Erosion Control’.

729-2.04 SEDIMENT CONTROL.  Replace ‘Meet AASHTO M 288 for Sediment Control’ with: ‘Meet AASHTO M 288 for Temporary Silt Fence’.  (2/28/00)R229M98

SECTION 730

SIGN MATERIALS

# Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

(2/29/00)R81M

Standard Modifications

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”. (06/25/99)M 83

Special Provisions

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(2/29/00)R81M

APPENDIX A

#### PERMITS

AND

EROSION AND SEDIMENT CONTROL PLAN

AND

TEMPORARY CONSTRUCTION PERMITS

APPENDIX B

#### CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST

# APPENDIX D

CUSTOM SIGN SHOP DRAWINGS

# APPENDIX E

ELECTRICAL FACILITIES RELOCATION