PART 4

STANDARD MODIFICATIONS

And SPECIAL PROVISIONS

for the

STATE OF ALASKA

STANDARD SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2002

# SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

c.	The Standard Specifications for Highway Construction 2002 USC units may be viewed or downloaded at no charge from the Statewide Design and Engineering Service Division’s external website.

d.	Geotechnical data comprised of test boring logs and grain size classifications.

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

4.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

5.	The Materials Certification List (MCL) has been included in Appendix B.  This list is provided for you to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

6.	The US Environmental Protection Agency (EPA) issued a new NPDES General Permit for Storm Water Discharges from Construction Activities Effective July 1, 2003 to July 1, 2008.  You will be required to comply with the provisions of the new General Permit.

SECTION 101

DEFINITIONS AND TERMS

101-1.03.DEFINITIONS.Add the following definition:

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the No. 200 screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 3 inch material. (11/29/01)R1USC

SECTION 103

# AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.06 INSURANCE REQUIREMENTS. Delete this Subsection in its entirety and substitute the following:  The Contractor shall provide evidence of insurance with an insurance carrier or carriers satisfactory to the Department covering injury to persons and property suffered by the State of Alaska or by a third party as a result of operations under this contract by the Contractor or by any subcontractor. The Contractor's insurance shall provide protection against injuries to all employees of the Contractor and the employees of any subcontractor engaged in work under this Contract. All insurance policies (a) shall comply with AS 21 and (b) shall be issued by insurers that (i) are licensed to transact the business of insurance in the State of Alaska under AS 21 and (ii) have a financial rating acceptable to the Department. The Contractor shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.

Where specific limits and coverages are shown, it is understood that they shall be the minimum acceptable. The requirements of this subsection shall not limit the Contractor’s indemnity responsibility under Subsection 107-1.13. Additional insurance requirements specific to this contract are contained in the Special Provisions, when applicable.

The Contractor shall maintain the following policies of insurance with the specified minimum coverages and limits in force at all times during the performance of the Contract:

- Workers' Compensation: as required by AS 23.30.045, for all employees of the Contractor engaged in work under this Contract. The Contractor shall be responsible for Workers' Compensation Insurance for any subcontractor who performs work under this Contract. The coverage shall include:

- Waiver of subrogation against the state and Employer's Liability Protection at $500,000 each accident/$500,000 each disease;

- “Other States” endorsement if the Contractor directly utilizes labor outside of the State of Alaska;

- United States Longshore and Harbor Workers’ Act Endorsement, whenever the work involves activity over or about navigable water; and

- Maritime Employer’s Liability (Jones Act) Endorsement with a minimum limit of $1,000,000, whenever the work involves activity form or on a vessel on navigable water.

- Commercial General Liability: on an occurrence policy form covering all operations with combined single limits not less than:

- $1,000,000 Each Occurrence;

- $1,000,000 Personal Injury;

- $2,000,000 General Aggregate; and

- $2,000,000 Products-Completed Operations Aggregate.

- Automobile Liability: covering all vehicles used in Contract work, with combined single limits not less than $1,000,000 each occurrence.

- Umbrella Coverage: for Contract amounts over $5,000,000 not less than $5,000,000 umbrella or excess liability. Umbrella or excess policy shall include products liability completed operations coverage and may be subject to $5,000,000 aggregate limits. Further, the umbrella or excess policy shall contain a clause stating that it takes effect (drops down) in the event the primary limits are impaired or exhausted.

- The State of Alaska shall be named as an additional insured on policies required by paragraphs 2 thru 4 above. All of the above insurance coverages shall be considered to be primary and non-contributory to any other insurance carried by the State of Alaska, whether through self-insurance or otherwise.

In any contract or agreement with subcontractors performing work, the Contractor shall require that all indemnities and waivers of subrogation it obtains, and any stipulation to be named as an additional insured it obtains, shall also be extended to waive rights of subrogation against the State of Alaska and to add the State of Alaska as an additional named indemnitee and as an additional insured.

The apparent low bidder shall furnish evidence of insurance to the Department before award of the Contract. The evidence shall be issued to the Department and shall be either a certificate of insurance or the policy declaration page with all required endorsements attached and must:

- Denote the type, amount, and class of operations covered;

- Show the effective (and retroactive) dates of the policy;

- Show the expiration date of the policy;

- Include all required endorsements; and

- Be executed by the carrier's representative.

When a certificate of insurance is furnished, it shall contain the following statement:

“This is to certify that the policies described herein comply with all aspects of the insurance requirements of (Project Name and Number). The insurance carrier agrees that it shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.”

The Department’s acceptance of deficient evidence of insurance does not constitute a waiver of Contract requirements.

Failure to maintain the specified insurance or to provide substitute insurance if an insurance carrier becomes insolvent, is placed in receivership, declares bankruptcy, or cancels a policy may be grounds for withholding Contract payments until substitute insurance is obtained, and may, in the Department's discretion, be grounds for declaring the Contractor in default. (05/06/03)R271USC02

SECTION 105

# CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: Request locates from all the utilities having facilities in the area.  Use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska Communications Systems (ACS) Anchorage Water & Wastewater Utility (AWWU) Chugach Electric Association, Inc. (CEA) ENSTAR Natural Gas Company (ENSTAR) GCI Cable, Inc. (GCI) Municipal Light & Power (ML&P) DOT&PF Maintenance and Operations DOT&PF Street Light & Storm Drain

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility-specific sections.  Cooperate with these utilities and coordinate the schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility-specific coordination.  You shall bear the expense for any changes or additional relocation requested for your convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

You shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if you are required to provide the surveying as part of the contract and/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of your two (2) week work plan, or not required by the contract.

The utility shall give you, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit you, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific coordination requirements for the specific utilities are included below.

(4/1/03)R3M98

UTILITY FACILITY PROTECTION.  Throughout the project area, protect all facilities while working around and under existing and newly constructed utilities.  Implement suitable construction methods and traffic control plans and ensure all utility facilities are protected until project completion.  Coordinate with utility companies to verify which, if any, facilities have been abandoned in place.

Prior to exposing utilities, provide the owning utility companies, through the Engineer, a proposed method of shoring the facilities and schedule for the work required. The utility company will review and approve the proposal prior to construction around the facilities. When working near live electrical facilities, comply with all laws and regulations and adhere to the requirements of Section 107-1.16, and Chugach Electric Association’s “Electrical Facility Clearance Requirements for Construction or Maintenance Near Electrical Facilities.”

When working near natural gas pipes, comply with all laws and regulations and adhere to ENSTAR’s “Safety Requirements for Excavation Adjacent to Natural Gas Pipelines.”

Replace sand bedding around all utilities where bedding is disturbed or removed by the excavation.

ANCHORAGE WATER AND WASTEWATER UTILITY (AWWU)

AWWU owns a water main that crosses the alignment near Station 161+10, which you will decommission and fill with sand slurry.  You will construct a new water main near Station 153+20 to replace the decommissioned link.

AWWU owns a sanitary sewer main that crosses the alignment near Station 164+45, which you will reconstruct in place.  You will replace the existing Asbestos Concrete (AC) sanitary sewer pipe with Ductile Iron Pipe (DIP) in the vicinity of the new retaining wall.

Construct the improvements to AWWU facilities as shown on the Plans and as provided in these Specifications.  See Sections 626, 627, and Appendix A.

Schedule and coordinate pre-construction and post-construction inspections of AWWU facilities in the project area.  Call Brian Baus at AWWU (564-2765) to coordinate the inspections and other work for this project.  At least fifteen (15) calendar days prior to beginning construction, notify the AWWU point of contact in writing. At least three (3) calendar days prior to pre-construction and post-construction inspections, notify the AWWU point of contact in writing.  Immediately provide copies of all the written notices to the Engineer.

Furnish traffic control and personnel to assist AWWU in locating facilities, performing inspections, and any work required to correct deficiencies noted during the inspections.  The Engineer, AWWU, and you shall witness the condition and location of each AWWU facility anticipated to be impacted by the project.  You will have no claim that AWWU facilities were deficient prior to construction except for deficiencies specifically listed in the record of the pre-construction inspection.  If pre-construction deficiencies are noted, supply traffic control and allow AWWU access to correct those deficiencies.

Protect and maintain all AWWU facilities impacted by the project in operable condition during all phases of construction.  If at any time after the pre-construction inspection, AWWU finds that you have damaged or rendered any of their facilities inoperable, you will be required to repair the damage at your expense.

Following construction, the Engineer, AWWU, and you shall verify the condition of each AWWU facility within the project limits.  Correct any deficiencies noted during the post-construction inspection.  All deficiencies shall be corrected at your expense except those deficiencies that were specifically noted in the pre-construction inspection record and were not to be corrected as a part of this contract.

# UTILITY TRENCHES

Coordinate with the Engineer to schedule construction of ENSTAR, CEA, ACS and GCI facilities.  The utility facilities are to be constructed prior to retaining wall construction at each location where utility construction will occur.

Excavate and backfill trenches for utility relocation under the proposed pathway as shown on the drawings and as described below.  If you choose to place the selected material backfill in the utility trenches prior to completion of the utility relocation to facilitate your operations, take all precautions necessary to assure the selected material is not contaminated during subsequent operations.  Coordinate with each utility and provide excavation backfill and compaction for their installation under the proposed pathway and retaining wall.

You will be responsible for final backfill and compaction of all selected material.  Coordinate with each utility company for the placement of safety marker tape in the backfill.

ENSTAR NATURAL GAS COMPANY (ENSTAR)

ENSTAR owns and operates an underground natural gas system located throughout the project area.  Some of ENSTAR’s facilities must be relocated to resolve conflicts with this project.

Call ENSTAR at 264-3740 to establish a point of contact and coordinate with ENSTAR as required.  ENSTAR will decommission gas pipes as needed to facilitate excavation.  Excavate as shown on the drawings, and then allow ENSTAR access to complete gas pipe relocation prior to beginning retaining wall construction.  Provide ENSTAR with written notice 15 calendar days in advance of commencing the work.

Coordinate with ENSTAR and provide traffic control, erosion and pollution control, and access to the work site.  You will be responsible for final backfill and compaction and final trim work in the work areas you share with ENSTAR.

To facilitate excavation for the retaining wall and pathway, ENSTAR will require 24 calendar days to complete the work required, including:

- Relocating their service to Lot 19 (Station 158+85) and Lot 26, Brink Subdivision (Station 164+30) from Muldoon Road to Brink Drive.

- Decommissioning the existing 2-inch steel pipe located in the easement area between Lots 21 and 22, Brink Subdivision, (Station 161+00).

- Decommissioning the existing 3-inch plastic main that parallels the proposed retaining wall from Station 153+60 to 169+00.  (Baseline Station 11+00 to 26+40).  ENSTAR will establish a temporary connection between the existing 2-inch steel main located in the easement between Lots 1 and 10 of Brink Subdivision (Station 155+15, Baseline Station 12+60) and the existing main near 20th Avenue (Station 153+55, Baseline Station 11+00).

When the work described above is completed, excavation can begin.  Following excavation and prior to retaining wall construction, coordinate with ENSTAR to allow them to complete the relocation work.  ENSTAR will:

- Construct a new 4-inch plastic main under the proposed pathway at the locations shown on the drawings.  Provide excavation, backfill and compaction.

- Construct a new link at Station 155+15 (Baseline Station 12+60) between the existing 2-inch steel main and the new 4-inch main shown on the drawings.  Provide final trim work including topsoil, plantings, seed, etc.

- Construct a new link between the existing 2-inch steel main on the north side of Parkway Drive (Station 157+10, Baseline Station 14+50) and the relocated main paralleling the retaining wall.  Provide final trim work including grading, paving, topsoil, seed, etc.

ENSTAR will require a total of 14 calendar days to complete the work in coordination with your excavation and backfill.  Coordinate with the Engineer to schedule ENSTAR into each work location.

- ENSTAR will require 4 calendar days to complete the work between 20th Avenue and Parkway Drive  (Baseline Station 11+00 to 14+50).

- ENSTAR will require 3 calendar days to complete the work between Parkway Drive and Island Drive (Baseline Station 14+50 to 22+60).

- ENSTAR will require 7 calendar days to complete the work between Island Drive and 16th Avenue (Baseline Station 22+60 to 26+40).

Provide a written notice to ENSTAR 7 calendar days in advance of when each work area will be available.

ENSTAR will perform a cathodic-protection sweep after the underground work on the project is complete, but prior to paving.  Notify ENSTAR 4 calendar days before the sweep is to be performed.  Allow ENSTAR one (1) calendar day to perform the sweep.  If the final sweep detects a ground fault, allow ENSTAR a minimum of 2 calendar days to make the required repairs.

ENSTAR reserves the right to excavate to determine if there has been any damage to its facilities. ENSTAR will bill you for the cost of repair if ENSTAR determines the fault was the result of your operations.

JOINT RELOCATION OF OVERHEAD UTILITIES

Joint-use poles are located on the east side of Muldoon Road from Station 155~ to Station 166~; Right.  Chugach Electric Association, Inc. (CEA), Alaska Communications Systems (ACS) and GCI Cable, Inc. (GCI) all have cables mounted on the joint-use poles.

The joint-use poles fall within the area of the proposed retaining wall and will require relocation.  Existing poles located near Stations 155+11; 156+27, 158+45, 159+56, 160+93, 162+36, 163+88, and 166+00 will be retired.  The facilities will be reconstructed underground in three phases.

Phase 1.

The first phase will complete the following:

Beginning in the easement near Station 155+00 (Baseline Station 12+60), the underground facilities will be located in the easement immediately east of the ROW line.  The alignment will cross under the proposed retaining wall on each side of Parkway Drive and continue north to the easement between Lots 11 and 19, Brink Subdivision (Station 158+40, Baseline Station 15+85).

Near Station 160+95 (Baseline Station 18+33), the underground facilities will be located in an easement between Lots 21 and 22 Brink Subdivision, which extends from Muldoon Road to Brink Drive.  Along Brink Drive the underground cable alignment proceeds north to an easement across Lot 27, Brink Subdivision.  At the north side of Lot 27, the alignment rises up an existing pole to connect to existing overhead facilities.

The construction sequencing requires that all new facilities (underground, primary and services) in the Phase 1 area be installed and energized prior to the start of excavation for the retaining wall.  The first phase must be completed in order to retire the existing overhead utilities.

During Phase 1, GCI will temporarily relocate some of their facilities above ground in innerduct between Baseline Station 15+85 and 18+33.  The facilities will be located in the temporary construction permit area until the joint trench is constructed under the proposed pathway during Phase 2.  Protect the temporary facilities during your operations in the area.

CEA, ACS and GCI will require a total of 24 calendar days to complete their work prior to retiring the existing overhead utilities.

Phase 2.

Phase 2 will construct underground facilities that will cross under the proposed retaining wall in two locations: Station 158+40, (Baseline Station 15+93) and Station 160+95 (Baseline Station 18+33).

A joint-use duct bank will be constructed under the proposed pathway between J-Box 0121 (Station 158+40 50’ Right) and PM 0730 (Station 160+95 150’ Right.)  CEA will install two 4-inch PVC (for CEA) and two 2-inch HDPE conduits (one each for ACS and GCI separated by labels) in the joint-utility trench.

Excavate the joint-utility trench (shown on the “Utility Relocation Schematic” on Sheet B1) and coordinate with CEA for the installation of the duct bank.  During the completion of this work, CEA will also trench and backfill through the easement between Lots 21 and 22 Brink Subdivision.

CEA will require a total of 7 calendar days to complete the duct bank.  Provide written notice to CEA 7 calendar days in advance of when the work area will be available.

Backfill and compact the joint-utility trench following the installation of the duct bank.

Phase 3.

CEA, ACS and GCI will all be active participants in Phase 3. ACS and GCI will install their facilities after CEA completes their conduit installation.

Coordinate with ACS and provide adequate work areas and a minimum of seven (7) calendar days to perform their relocation works.  Coordinate with GCI and provide adequate work areas and a minimum of seven (7) calendar days to perform their relocation works.

Coordination.

Allow each utility access to the work area to complete the installation.

When CEA, ACS, or GCI are working in the area of the pathway or the retaining wall, coordinate with each utility as necessary and provide traffic control, erosion and pollution control, and access to the work site.  You will be responsible for final backfill and compaction and final trim work in the work areas you share with the utilities.

To establish a point of contact and coordinate the work in Phases 1, 2 & 3, call CEA at 762-4635.  ACS and GCI will also work in the area during Phase 3.  Allow each utility access to the work area to complete their installation.  To establish points of contact and coordinate the work call ACS at 564-1691 and GCI at 868-8581 or 522-9400.

Provide a 15-calendar day written notice for commencement of the work and for each time there is a break in the project scheduling.

105-1.07 COOPERATION BETWEEN CONTRACTORS. Add the following: The following projects may or will be under construction concurrently with this project:

Muldoon Road Landscaping & Pedestrian Improvements, Phase II

DOT Project No. 56516

Design Project Manager:  Gerry Kintz, P.E

Project Status: Begin Construction Spring 2004

Project Engineer: Not yet assigned

Contractor:

Creekside Town Center Road Improvement

MOA Project No. 02-012

Design Project Manager:  Jerry Hansen

Project Status:  Begin Construction July 2004

Project Engineer:  Not yet assigned

Contractor:

Coordinate traffic control, construction, and material hauling operations with the prime contractor of each above project so as to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contract.  (2/1/00)R175M98 -LA

105-1.13 MAINTENANCE DURING CONSTRUCTION. Add the following: Inspect and clean all storm drain sumps and petroleum separator manholes during the construction season and prior to winter shutdowns. This inspection and maintenance of the storm drain system will not be paid for directly but will be subsidiary to work paid for under Sections 603 and 604. (2/1/00)R4M98

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Plant Establishment and Maintenance; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve you from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve you of any obligations under the Contract. (05/28/03)R237USC02

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

# CONTROL OF MATERIAL

Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials which remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.  (08/31/99)S 13

106-1.03 TESTING AND ACCEPTANCE.  Add the following:

When the specifications refer to the following test methods, use the corresponding test method shown.

| REPLACE TEST METHOD: | WITH TEST METHOD: |
| --- | --- |
| ATM 203 | Alaska FOP for AASHTO T 267 |
| WAQTC FOP for AASHTO T 89/T 90 | WAQTC FOP for AASHTO T 89 WAQTC FOP for AASHTO T 90 |
| WAQTC FOP for AASHTO T 180 | WAQTC FOP for AASHTO T 99/T 180 and WAQTC TM 9 |
| WAQTC FOP for AASHTO T 224 | Same |
| ATM 212 | ATM T-12 |
| WAQTC FOP for AASHTO T 310 | WAQTC TM 7 |
| WAQTC FOP for AASHTO T 27/T 11 | Same |
| WAQTC TM 1 | Same |
| ATM 306 | ATM T-9 |
| ATM 313 | ATM T-13 |
| WAQTC TM 4 | Same |
| WAQTC FOP for AASHTO T 308 | WAQTC FOP for AASHTO TP 53 |
| WAQTC TM 6 | Same |
| WAQTC FOP for AASHTO T 30 | Same |
| WAQTC FOP for AASHTO T 209 | Same |
| WAQTC FOP for AASHTO T 166/T 275 | Same |
| WAQTC TM 8 | Same |
| ATM 412 | None |
| ATM 414 | ATM T-14 |
| ATM 417 | ATM T-17 |
| WAQTC TM 2 | Same |
| WAQTC FOP for AASHTO T 309 | WAQTC TM 10 |
| WAQTC FOP for AASHTO T 119 | Same |
| WAQTC FOP for AASHTO T 121 | Same |
| WAQTC FOP for AASHTO T 152 | Same |
| WAQTC FOP for AASHTO T 23 | Same |
| ATM 520 | ATM T-30 |

(09/04/02)B01

SECTION 107

# LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If you discover cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by your operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Add the following: The Department has received the following permits on your behalf:

1.	Alaska Department of Environmental Conservation Storm Water Discharge 
Non-Objection Letter, dated May 6th, 2003, and attached in Appendix C.

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  MOA will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from you.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If you require water for any construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (05/29/02)R7M98 - LA

107-1.13 RESPONSIBILITY FOR DAMAGE CLAIMS. Delete this Subsection in its entirety and substitute the following:   The Contractor shall indemnify, hold harmless and defend the State of Alaska and its agents and employees from any and all claims or actions for injuries or damages whatsoever sustained by any person or property that arise from or relate to, directly or indirectly, the Contractor's performance of the Contract, however, this provision has no effect if, but only if, the sole proximate cause of the injury or damage is the Department’s negligence. This Contract does not create a third party benefit in the public or any member of the public, nor does it authorize any person or entity not a party to this Contract to maintain a suit based on this Contract or any term or provision of the Contract, whether for personal injuries, property damage or any other claim or cause of action.   (05/06/03)R271USC02

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following after the last paragraph: When construction activities meet any of the following conditions, advise the appropriate owning Utility(s) in writing at least 24 hours in advance of work.

1.	Operations anticipated being within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services. (10/23/02)R170USC02

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

# Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.  (08/13/98)S 80

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1. A progress schedule.  and substitute the following:

1.  A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order in which the work will be carried out and the contemplated dates on which the Contractor and subcontractors will start and finish each of the salient features of the work, including any scheduled periods of shutdown.  Indicate any anticipated periods of multiple-shift work in the CPM Schedule.  If revisions to the proposed CPM Schedule are required, make them promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to your schedule, or upon request of the Engineer. (12/13/02)R261M98

Delete Item 5 of the first paragraph and substitute the following:

- The submittals identified under Subsection 641-1.03, Submittals.

(01/31/02)R160M98

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.05 COMPENSATION FOR EXTRA WORK.   Delete the first sentence of the second paragraph of sub-item a. of item 3 and substitute the following:  The regular hourly rental rate is the adjusted monthly rate for the basic equipment plus the adjusted monthly rate for applicable attachments, both divided by 176, and multiplied by the area adjustment factor specified on the adjustment maps for the Alaska - South Region.  (10/23/02)R14USC02

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

Add the following section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following:

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84USC -LA

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-3.02 EMBANKMENT CONSTRUCTION.

Add the following: Where the plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.  (11/05/02)R23USC02

203-3.03 COMPACTION WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP FOR AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the No. 200 sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the No. 4 sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus No. 4 material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the ¾ inch sieve with the plus ¾ inch material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5. (11/05/02)R193USC02

203-5.01 BASIS OF PAYMENT.  Delete pay items 203(1) through 203(4).  All excavation is subsidiary to the pay item to be constructed where the excavation is required.  Change Pay Items (6) to read:  Borrow, Type A.  Borrow, Type A shall be comprised of Selected Material, Type A as defined in Subsection 703-2.07.  Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

203 (6A)	Borrow, Type A	Ton

## SECTION 204

STRUCTURE EXCAVATION FOR CONDUIT AND MINOR STRUCTURES

## Special Provisions

204-2.01 MATERIALS.  Add the following:  All bedding material for water and sewer pipe construction shall conform to 	AWWU specifications for Class "C" Bedding as follows:

# Cumulative % Passing

Sieve Size			by Weight

2 in				100

½ in				40-100

#4				20-75

#10				12-60

#40				2-30

#200				0-6

In addition to the grading limits listed above, the fraction of material passing the #200 sieve shall not be greater than six percent of that fraction passing the #4 sieve.

204-5.01 BASIS OF PAYMENT.

Delete the last paragraph and substitute the following:  Any backfill or bedding material required whose source is other than project excavation will be paid for at the contract unit price for Borrow, Type A.

SECTION 205

EXCAVATION, BACKFILL AND FOUNDATION FILL FOR STRUCTURES

# Special Provisions

205-3.03 BACKFILL. Add the following:

Construct Unit Drainage Fill and Infill Soil in accordance with the modular block retaining wall manufacturer’s published recommendations and the approved submittal for modular block retaining walls.

Unit Drainage Fill shall be as defined in Section 703, Aggregates of these special provisions.  Infill Soil shall be as defined in Section 703, Aggregates of these special provisions.

205-4.01 METHOD OF MEASUREMENT. Add the following:

Item 205(6) Infill Soil will be measured by weighing.

205-5.01 BASIS OF PAYMENT. Add the following:

Preparing the retaining wall foundation, the Unit Drainage Fill and the retaining wall leveling pad are subsidiary to Section 511, Modular Block Retaining Walls.

Delete pay item 205(1) Excavation for Structures.  All excavation for structures is subsidiary to pay item 511(3) Modular Block Retaining Walls.

Delete pay item 205(3) Foundation Fill.  Payment for this work shall be made under Pay Item 203(6A) Borrow, Type A.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

205 (6)	Infill Soil	Ton

## SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-2.01 MATERIALS. Add the following after the first sentence: If no gradation type is specified in the bid schedule the base course material gradation shall conform to the requirements for Grading D-1. (11/05/02)R116USC02

Add the following after the first sentence: At your option, recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5-inch sieve and 95-100 percent by weight passing the 1-inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 40,000 pounds. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.  (11/05/02)R176USC02

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-1.01 DESCRIPTION. Add the following: This work shall also consist of construction of architectural precast concrete wall caps and pilaster caps as shown on the plans.

Add the following subsections:

501-1.02 QUALITY ASSURANCE.

Precast Concrete Fabricator Qualifications: Firm shall have a minimum of five (5) years experience in producing units similar to those required for this Project, with sufficient production capacity to produce and deliver required units without causing delay in Work.  The Fabricating plant shall be certified by one of the following:

    - Architectural Precast Association (APA)

    - Precast/Prestressed Concrete Institute (PCI), Group A1

    - Firms not certified by APA or PCI shall submit a written Quality Assurance/Quality Control program for approval.

- Production Samples:  Before fabrication, provide three, 8-inch long wall cap unit samples for approval of appearance.  The wall cap sample will serve as both the sample for the wall caps and pilaster caps.

501-1.03 FINISHES.

Precast Concrete elements shall match the approved samples.  All exposed surfaces on each cap shall be a smooth, steel trowel or steel form finish.  Form lines shall be invisible except at corners or angle points.  No form lines may be larger than 1/8”.  All surfaces shall be free from pockets, sand streaks, honeycomb, or bugholes greater than ¼” in diameter.

The color shall be uniform on all units and shall be white or gray.  If necessary to maintain color consistency, white cement shall be used.

Discard all units that are warped, cracked, broken, spalled, stained, discolored, or otherwise defective unless repairs are approved by the Engineer and meet specified requirements.

501-2.01 MATERIALS. Add the following:

Reinforcing steel in pilaster caps shall conform to the requirements of Section 503.

Reinforcement for precast concrete wall caps shall be fibrillated polypropylene fibers, ¾” to 1-1/2” long, mixed in the concrete at 1.5 pounds per cubic yard.  The fibers shall meet the requirements of ASTM C-1116, Type III, Section 4.1.3, "Synthetic Fiber Reinforced Concrete or Shotcrete".

Graffiti protection treatments shall conform to the requirements of Section 514.

501-3.01 PROPORTIONING.  Under 1.  Contractor Mix Design., delete the first sentence of the second paragraph and substitute the following: Submit a mix design developed in accordance with ACI 211 and ACI 301, Section 4 to the Engineer for approval. (11/05/02)R37USC02

501-4.01 METHOD OF MEASUREMENT. Replace with the following: Precast concrete elements will be measured for payment as described in Section 511 Modular Block Retaining Walls.

501-5.01 BASIS OF PAYMENT. Replace with the following: Payment for precast concrete elements will be made as described in Section 511 Modular Block Retaining Walls.  No separate payment will be made.

Replace Section 511 with the following section:

Section 511

Modular Block Retaining Walls

Special Provisions

511-1.01 DESCRIPTION. The Modular Block Retaining Walls shall be constructed at the locations shown on the plans as provided in these specifications.  The following is the list of acceptable modular block systems for this project:

Keystone Retaining Wall Systems	“Pyramid”

Keystone Retaining Wall Systems Inc.	The Reinforced Earth Company

444 West 78th  Street	20381 Lake Forest Drive, Suite B-2

Minneapolis, Minnesota 55435	Lake Forest, CA 92630

1-800-747-8971	(949) 587-3060

Mesa Retaining Wall Systems

Tensar Earth Technologies, Inc.

5883 Glenridge Drive, Suite 200

Atlanta GA 30328

1-800-836-7271

Use only one system for the entire project.

511-1.02 APPEARANCE STANDARDS.

Mock-Ups

Based on mock-ups you will prepare, the Department may choose tri-planar/radius or straight-faced blocks or a combination of the two for this project.

Construct two (2) mock-ups for Department review and approval.  Each mock-up shall be at least four (4) courses high.  Each mock-up shall include a prototype pilaster and at least two (2) blocks on each side of the pilaster.

Construct Mock-up #1 entirely of straight-plane blocks.  Construct Mock-up #2 with straight-plane blocks in the pilaster and tri-plane/radius blocks in the wall face.  Provide at least one (1) pilaster cap and four (4) wall caps and install the wall caps on each mock-up for the Department’s evaluation.

Construct the pilaster using the exact details you will use for the entire project.  The Department will review the pilaster details you propose in the mock-ups and may require you to correct any pilaster construction details as required to meet project requirements.  Revise the pilaster details as required to attain the Department’s approval of the mock-up.  You will be required to provide detailed information about where and how mortar and adhesives would be placed, however, the actual placement of mortar and adhesives will not required for the mock-ups.

The approved mock-up shall serve as the prototype for the entire project.

# Appearance of Constructed Walls

The wall shall present the appearance of a running bond pattern.  The color and texture of the blocks shall be as chosen by the Engineer following the Contractor’s submittal and mock-up construction.  The blocks shall be arranged so that all exposed surfaces whether on the front, sides, or back, match the standard block face in shape, texture, and color.

Wall caps shall be provided in conformance to the details shown on the drawings.  Precast concrete wall caps and pilaster caps are intended to provide a color contrast, reveal, and finished appearance at the top of walls.  The precast concrete portion of the wall caps shall be sized to provide a one-inch (1”) overhang in all directions.  Pilaster caps shall be two (2”) inches larger than the pilaster in all directions.

Curvilinear alignment, pilasters, and terraces are required as shown on the drawings.  Pilasters shall be provided in the locations shown.  Pilaster dimensions shall extend at least three (3”) inches beyond face of wall, and at least one (1”) inch behind the back of the wall cap.  Pilasters may not extend more than four (4”) inches beyond the face of the wall.  All pilasters shall be constructed using the same details and at the same dimensions as the pilaster in the approved mock-up.

# Modular Block Units

The color of the wall shall be as selected by the Engineer.  Surfaces of modular blocks shall be split face, sculptured rock face, or approved faux stone.

The minimum allowable modular block unit length is sixteen (16”) inches. The maximum allowable modular block unit length is twenty-four (24”) inches.  The minimum allowable block height is six (6”) inches.  The maximum allowable block height is twelve (12”) inches.  The design wall batter cannot exceed one (1) degree.

# Precast Concrete Cap Elements

Precast wall caps and pilaster caps shall be constructed as detailed on the drawings.  The standard length for precast concrete wall caps shall be the standard modular block length.  The thickness of precast concrete wall caps shall be a nominal four (4”) inches.  The appearance of Precast Concrete Cap elements shall be as described in Section 501 Structural Concrete.

511-1.03 REFERENCE STANDARDS.

Engineering Design

- Design Manual for Segmental Retaining Walls, 2nd edition, National Concrete Masonry Association. (NCMA)

- NCMA TEK 2-4 - Specifications for Segmental Retaining Wall Units.

- NCMA SRWU-1 - Determination of Connection Strength between Geosynthetics and Segmental Concrete Units.

- NCMA SRWU-2 - Determination of Shear Strength between Segmental Concrete Units.

### Modular Block Retaining Wall Units

#### ASTM C 140 - Sampling and Testing Concrete Masonry Units

#### ASTM C 1262 - Evaluating the Freeze - Thaw Durability of Manufactured Concrete Masonry Units and Related Concrete Units.

#### ASTM C 1372 – Standard Specification for Segmental Retaining Wall Units

### Geogrid

#### ASTM D 4595 - Test Method for Tensile Properties of Geotextiles by the Wide-Width Strip Method.

#### ASTM D 5262 - Test Method for Evaluating the Unconfined Creep Behavior of Geosynthetics.

#### ASTM D 6637 - Test Method for Determining Tensile Properties of Geogrids by the Single or Multi-Rib Tensile Method.

#### ASTM D 6638 - Test Method for Determining Connection Strength Between Geogrid and Segmental Concrete Units.

#### ASTM D 6706 - Test Method for Measuring Geosynthetic Pullout Resistance in Soil.

- Geosynthetic Research Institute (GRI)

  - GG1	Standard Test Method for Geogrid Rib Tensile Strength

  - GG2	Standard Test Method for Geogrid Junction Strength

  - GG3	Standard Test Method for Tension Creep Testing of Geogrids

  - GG4	Standard Practice for Determination of the Long Term Design Strength of Geogrids

  - GG5	Standard Practice for Evaluating Geogrid Pullout Behavior

### Soils

#### Infill Soil – Section 205 Excavation, Backfill and Foundation Fill for Structures

#### Foundation – Section 205 Excavation, Backfill and Foundation Fill for Structures

#### Unit Drainage Fill – Section 205 Excavation, Backfill and Foundation Fill for Structures

#### Leveling Pad – Section 301 Aggregate Base and Surface Course (if crushed stone leveling pads are used)

#### ASTM D G51 - Soil pH

### Concrete

#### Wall and Pilaster Caps – Section 501 Structural Concrete

#### Leveling Pad – Section 501 Structural Concrete (if concrete leveling pads are used)

### Drainage Pipe

### Section 605 Underdrains

### Where specifications and reference documents conflict, the Engineer shall make the final determination of applicable document.

511-1.04 SUBMITTALS.

### In addition to other submittals described in other sections of these specifications, submit the following information for approval a minimum of thirty (30) days prior to starting construction of the segmental retaining wall.

General

Demonstrate that the modular block units, adhesive(s), geogrid, unit drainage fill, and infill soil are compatible with each other and together these materials will meet the requirements of the plans, specifications, and the structure design.

Provide the engineer with two (2) copies of the design manual and four (4) copies of the installation manual as published by the geogrid and modular block manufacturers.

Modular Blocks

### If necessary, supplement the manufacturer’s guide(s) to demonstrate that the product you will supply will meet the requirements for curve radii, batter, and pilaster construction.

Submit Modular Block samples for approval of colors, textures and shapes.

Submit manufacturer’s certifications for modular block units including: dimension tolerances, unit weight, compressive strength, freeze/thaw protection, inter-unit mechanical interlock shear strength, and the connection strength between the modular blocks and the geogrid.

### Submit documentation for approval for the adhesive(s) to be used.  You may use a different adhesive for the caps than the adhesive used to construct the pilaster.  The submittal shall demonstrate that the adhesives meet the Modular Block Manufacturer’s specifications and recommendations and that the adhesives are suitable for the application shown on the drawings.  Weather restrictions shall be included.  The submittal shall also demonstrate that the uncured adhesive will not have an adverse effect where it comes into contact with the geogrid.

### To be approved the submittal shall document that, once properly applied and cured, the adhesives will be suitable for local temperature extremes, applications below grade, and occasional exposure to ground water.

Geogrid

Submit manufacturer’s certifications for geogrid including:

- Documentation of manufacturing quality control.

- Testing and documentation required to establish the Soil Interaction Coefficient, (CI), and the Coefficient of Direct Sliding (CDS).

- Detailed test data including tensile strength (ASTM D 4595 or ASTM D 6637), creep potential (ASTM D 5262), site damage and durability (GRI GG-4), pullout resistance (ASTM D 6706) and connection strength (ADTM D 6638).  You shall complete all testing and documentation required to establish the design value of the long-term allow tensile load (Ta), and submit the result to the Engineer for approval.  The submittal shall include specific evaluation documenting the relationship between the actual infill soil the Contractor will supply for this project and the geogrid to be used.

Retaining Wall Design Submittal - Except as provided in the subsection entitled Pre-Approved Engineering Design presented on the following page, provide four (4) sets of stamped construction drawings and detailed design calculations, completed and sealed by an Engineer who is registered as a Civil Engineer in the State of Alaska.  A detailed explanation of the design properties for the geogrids shall be submitted with the design.  Allow the Engineer three (3) weeks to review the working drawings and calculations.

Your Engineer will perform at least the following tasks:

- Produce sealed construction drawings and detailed design calculations, completed in accordance with the design requirements outlined in the plan set and these specifications.

#### Review the site soil and geometric conditions to ensure the designed wall is compatible with the site prior to construction.

#### Inspect the site conditions, materials incorporated into the retaining wall, and the construction practices used during the construction.

#### Provide a letter after completion, certifying the design meets the requirements of this specification, the design was compatible with the site and the wall was constructed according to the design.

Design Requirements –

- The engineering designs, techniques, and material evaluations shall be in accordance with the Manufacturer's Design Manual, and/or the NCMA Design manual.

- The design batter cannot exceed one (1) degree.

- The minimum embedment shall be the wall height (H) divided by 10.

- The maximum backslope is 2H:1V for infill soil and retained soil.   The design may recognize the load characteristics of the actual slope -- a “broken back slope” (slope that levels off within the distance of 2*H behind the wall) may be used in calculations at the specific locations where the slope condition is known to apply.

- The actual backslope may be used for walls A and I.

- No additional surcharge loading beyond the weight of the backslopes is required.

Meet or exceed the Safety Factor values established in the NCMA design manual.

Pre-Approved Engineering Design –

You may construct the design presented in the plan set without separate stamped engineering drawings subject to all the conditions listed below:

##### Submittals

You must submit all items listed in Subsection 511-1.05 Submittals except the “Retaining Wall Design Submittal.”

##### Materials

All materials shall conform to the plans and Subsection 511-2.01 Materials.  In order to adopt the design shown in the plan set without a separate engineering seal and certification, the following additional requirements must also be met:

# Modular Block Units

- Modular block units, including infill soil, shall weigh a minimum of 114 pounds per square foot of wall face.

- The inter-unit shear strength of mechanical interlock between units shall be a minimum of 600 pounds per linear foot (plf).

- The connection strength between the modular block units and the geogrid shall be a minimum of 600 plf.

# Structural Geogrid

In order to adopt the design shown in the plan set without a separate engineering seal and certification, you shall submit testing certifications described in Subsection 511-1.05 Submittals for the values of long-term allowable tensile strength (Ta) Coefficient of Interaction (CI), and Coefficient of Direct Sliding (CDS) based on the infill soil and geogrid materials you will use and construction methods you will employ.

- The minimum Ta required to adopt the design shown in the plan set is 1250 plf, as Ta is defined in Subsection 511-2.01 Materials.

- The Coefficient of Direct Sliding (CDS) shall be a minimum of 0.95.

- The Coefficient of Interaction (CI) value shall be a minimum of 0.85.

##### Construction

All construction shall conform to Subsection 511-3.01 Construction.  In order to adopt the design shown in the plan set without a separate engineering seal and certification, the following additional requirements must also be met:

- You must comply with all construction requirements of the “Design Manual for Segmental Retaining Walls, 2nd Edition” published by the National Concrete Masonry Association. (NCMA)

- You must follow all recommendations of both the geogrid and modular block wall manufacturers. Geogrid overlap requirements at curves shall comply with NCMA details or manufacturer’s recommendations whichever is the most stringent.

    - ALTERNATE RETAINING WALL SYSTEMS

If you wish to substitute an alternative retaining wall system (i.e. other Mechanically – Stabilized Earth retaining wall systems, cast-in-place concrete walls, or wall systems using tie-backs, ground anchors etc.), you may submit a Value Engineering Proposal in accordance with Subsection 104-1.06 Value Engineering Proposals By contractor.

511-1.07 DELIVERY, STORAGE, AND HANDLING.

All units shall be handled, stored, and shipped in such a manner to protect them from chipping, discoloration, cracks, and fractures. Check materials upon delivery to assure that specified type and grade of materials have been received and proper color and texture of the modular block units have been received.  Prevent excessive mud, wet concrete, epoxies, and like materials that may affix themselves from coming in contact with materials.  Store and handle materials in accordance with manufacturer's recommendations.

Rejection: Units shall be rejected because of failure to meet any of the requirements specified above.  In addition, any of the following defects shall be sufficient cause for rejection:

- Defects caused by faulty casting.

- Defects indicating honeycombed or open-texture concrete.

- Cracked or severely chipped units.

- Unreasonable color variation, staining, or calcification on front face of unit.

Protect materials from damage. Carefully inspect all reinforcing and attachment devices to ensure they are true to size and free from defects that may impair strength and durability.

Do not incorporate damaged or defective materials into the retaining wall.

511-2.01 MATERIALS.

Modular Concrete Retaining Wall Units

Architectural Requirements are as listed in Subsection 511-1.02 Appearance Standards.  Modular block units shall be capable of being constructed at the curve radii shown on the drawings using standard details published by the manufacturer.

Modular concrete materials shall conform to the requirements of ASTM C1372 - Standard Specifications for Segmental Retaining Wall Units.	Modular block units shall have a minimum 28-day compressive strength of 4000 psi.  The concrete in modular block units shall have adequate freeze/thaw protection and meet the requirements of ASTM C 1262.  The maximum absorption rate shall be six (6%) percent.

The dimensions of the modular block units shall have a maximum tolerance of one-eighth (1/8”) inch (not including rough split face) for each dimension.  All units shall be free from cracks or other defects that would interfere with the proper placing of the unit or significantly impair the strength or permanence of the construction.  Exposed surfaces of units shall be free of chips, cracks or other imperfections when viewed from a distance of ten (10’) feet under diffused lighting.

Modular block units shall lock together vertically.  In addition to core fill and friction, there shall be a mechanical interlock between units.  Shear connectors shall consist of a non-degrading polymer or galvanized steel and shall be made for the express use with the modular block units supplied.  Shear connectors shall be suitable for cold weather applications. Shear connectors shall be capable of holding the geogrid in the proper design position during grid pre-tensioning and backfilling.

Modular Block Adhesives

Adhesives shall comply with the Modular Block manufacturer’s specifications and recommendations.  The adhesive for bonding the caps may be a different product than the adhesive used to construct the pilasters.

### Select adhesives with suitable weather restrictions such that the local weather will not adversely affect proper application and curing of the adhesives.  Once properly applied and cured the adhesives shall be suitable for local temperature extremes, applications below grade, and occasional exposure to ground water.

Precast Concrete Elements

Precast concrete elements shall comply with the requirements for Class W concrete as specified in Section 501 Structural Concrete.  Reinforcing for Precast Wall Caps shall be as specified in Section 501 Structural Concrete as described in these special provisions.  Reinforcing for Precast Pilaster Caps shall be as specified in Section 503 Reinforcing Steel.

## Geogrid Reinforcement at Obstructions

### Structural steel elements and galvanizing shall be as specified in Section 716 Structural Steel.

# Geosynthetic Reinforcement

Where “Geogrid” appears in the plan set or specifications, these “Geosynthetic Reinforcement” specifications shall apply.

Geosynthetic Reinforcements shall consist of high-tenacity geogrids or geotextiles manufactured for soil reinforcement applications.  The location of the reinforcing geosynthetic shall be as shown on the plans.  The design properties of the reinforcement shall be determined according to the procedures outlined in this specification and the NCMA Design Manual for Segmental Retaining Walls.  Detailed test data shall be submitted as described in Subsection 511-1.05 Submittals.

Included with the raw test data shall be a report that will show that the proposed geosynthetic reinforcements meet all of the design requirements.  At a minimum, the following is required:

  - Documentation of Manufacturing Quality Control.  The geogrid manufacturer shall have a manufacturing quality control program that includes QC testing by an independent laboratory.  The QC testing shall include:

Tensile Strength Testing

Melt Flow Index (HDPE)

Molecular Weight (Polyester)

  - Testing and documentation required to establish the Soil Interaction Coefficient, (CI), and the Coefficient of Direct Sliding (CDS).  CI values shall be determined per GRI:GG5 at a maximum 0.75 inch displacement.

  - Detailed test data including tensile strength (ASTM D 4595 or ASTM D 6637), creep potential (ASTM D 5262), site damage and durability (GRI GG-4) and pullout resistance (ASTM D 6706) and connection strength (ADTM D 6638).  You shall complete all testing and documentation required to establish the design value of the long-term allow tensile load (Ta).  Ta is defined as follows:

Ta = Tult / (RFCR*RFD*RFID*FSunc)

Ta shall be evaluated based on a 75-year design life.

Tult, Short Term Ultimate Tensile Strength

Tult is based on the minimum average roll values (MARV)

RFCR, Reduction Factor for Long Term Tension Creep

RFCR shall be determined from 10,000-hour creep testing performed in accordance with ASTM D5262. RFCR = 1.60 minimum.

RFD, Reduction Factor for Durability

RFD shall be determined from polymer-specific durability testing covering the range of expected soil environments. RFD = 1.10 minimum.

RFID, Reduction Factor for Installation Damage

RFID shall be determined from product specific construction damage testing performed in accordance with GRI-GG4.  Test results shall be provided for each product to be used with project specific or more severe soil type.  RFID = 1.10 minimum.

FSunc, Factor of Safety for Uncertainties

FSunc shall be 1.5.

In no case shall the product RFCR*RFD*RFID be less than 2.0.

The maximum design tensile load of the geogrid shall not exceed the laboratory-tested ultimate strength of the geogrid/facing unit connection as limited by the "Hinge Height" divided by a factor of safety of 1.5. The connection strength testing and computation procedures shall be in accordance with NCMA SRWU-1 Test Method for Determining Connection Strength of SRW.

# Drainage Pipe

Drainage pipe shall conform to the requirements of Section 605 Underdrains.

# Unit Drainage Fill Material

Unit drainage fill shall comply with the requirements of Table 703-7 of these special provisions.

Infill Soil

Infill soil shall comply with the requirements of Subsection 703-2.07 of these special provisions.

- A smaller maximum aggregate size may be required in order to match the RFID, as defined above.  It is your responsibility to match the selection of geogrid and maximum aggregate size as necessary to maintain the required values for allowable tensile strength (Ta), Soil Interaction Coefficient (CI), and the Coefficient of Direct Sliding (CDS).  Submit testing documentation for Ta, CI, and CDS to the Engineer.

# Leveling Pad Material

If the Contractor elects to use crushed stone, the Leveling Pad Material shall conform to the requirements of Aggregate Base Course, Type D-1.  If the Contractor elects to use unreinforced concrete, the Leveling Pad Material shall conform to the requirements for Class W concrete as specified in Section 501 Structural Concrete.

# Foundation Material

Foundation material shall consist of undisturbed native material.  Where the native material is disturbed, it shall be removed and replaced with Borrow, Type A installed in accordance with Section 205, Excavation, Backfill and Foundation Fill for Structures.

511-3.01  CONSTRUCTION.

Foundation Preparation

The foundation for the modular block retaining wall structure shall be graded level for the width  shown on the plans or shop drawings.  Any foundation soils found to be unsuitable shall be removed and replaced with backfill in accordance with Section 205, Excavation, Backfill and Foundation Fill for Structures.

## Leveling Pad

#### The minimum thickness of the leveling pad shall be six (6”) inches.  At the Contractor’s option, the leveling pad material may be crushed stone compacted as required by Section 301 Aggregate Base and Surface Course, or unreinforced concrete meeting the requirements for Class W concrete as specified in Section 501 Structural Concrete.

#### Installing Drainage System

### The drainage pipe shall be placed behind the leveling pad, or lower course of facing units as shown on the plans or as directed by the Engineer. The pipe shall be laid at a minimum gradient of two (2%) percent unless otherwise approved by the Engineer.  Route pipes to inlets as shown on the drawings.

Wall Erection

A field representative from the proprietary modular block wall system being used shall be available during the erection of the wall.  The services of the representative shall be at no additional cost to the Department.

## Modular Block Retaining Wall Units

Install modular block units according to the modular block manufacturers recommendations and specifications.  Place modular block units so that their final position is battered in the near vertical (one degree or less) position.

Construction Tolerances

The following tolerances are the maximum allowable deviation from the planned construction:

- Vertical Control: Deviation shall be limited to one-quarter (1/4” ) inch over a ten (10’) foot distance.  Total deviation shall not exceed three (3”) inches total

- Horizontal Control: Deviation shall be limited to one-quarter (1/4” ) inch over a ten (10’) foot distance.  Total deviation shall not exceed three (3”) inches total

- Rotation: final wall batter may vary between one-half (0.5) and two (2.0) degrees.

- Bulging: Deviation shall be limited to one (1”) inch over a ten (10’) foot distance (not counting variations in split-face surfaces).

## Unit Drainage Fill

One (1) cubic foot, minimum, of drainage fill shall be used for each square foot of wall face.  Place unit drainage fill in lifts a maximum of eight (8”) inches thick.  Fill within the cores of, between, and behind each unit.  Compact to the manufacturer’s specifications.

## Geogrid Reinforcement at Obstructions

### Construct the reinforcement in accordance with the details shown in the plans and the recommendations of the geogrid manufacturer.

## Infill Soil and Geogrid

### Place infill soil in the locations shown on the plans as described below.  Complete all backfill operations according to the modular block manufacturers recommendations and specifications.

### Place infill soil in such a manner as to avoid any damage or disturbances of the wall materials or misalignment of the facing panels.  Remove and replace any wall materials that become damaged during any backfill placement and correct any misalignment or distortion of the masonry block units at your expense.

Do not operate ride-on mechanical compaction equipment closer than three (3’) feet from the back of the modular block units during the placement of Unit Drainage Fill, Infill Soil, or Retained Soil.  Compact within three (3’) feet of the back face of the wall facing using a lightweight mechanical tamper, roller or vibratory system.

Compact infill soil to 95 percent of the maximum density as determined by Alaska Test Method T-12 or AASHTO T 180.  The maximum lift thickness after compaction shall not exceed eight (8”) inches.  Decrease the lift thickness if necessary to obtain the specified density.  Field density will be determined using Alaska Test Method T-3 or T-11 by the Engineer.

The Engineer shall take a minimum of one density test after every three levels of blocks are placed.  Soil tests shall be taken no closer than three (3’) feet from the back surface of the masonry modular block units.

At the specified elevations, place geogrid, as described below. Place the infill soil and compact level with the top of the wall modules at the specified geogrid elevations prior to placing the geogrid.  Take care to ensure that the geogrid lays flat and taut during placement of the infill soil.  This is best achieved by placing fill on top of the geogrid near the wall fascia and spreading toward the back of the infill soil zone.

### Do not operate tracked construction equipment directly on top of the geogrid until a minimum thickness of six (6”) inches of fill has been placed.  Rubber-tired equipment may drive on top of the geogrid at slow speeds but should exercise care not to stop suddenly or make sharp turns.

### Place pre-cut sections of geogrid horizontally at each specified elevations.  Assure that the longitudinal axis is perpendicular to the wall face (i.e. machine direction).  Connect the geogrid to the wall facing units as specified by the manufacturer.  Take care to ensure that the wall modules are swept clean and that the geogrid is in complete contact with the top and bottom faces of the adjacent wall modules.  Carefully place the next course of wall modules on top of the lower modules to ensure that no pieces of concrete are chipped off and become lodged between unit layers.

### Pull the geogrid taut away from the wall modules during placement of infill soil.  Alternatively, suitable anchoring pins or staples can be used to ensure that there are no wrinkles or slackness prior to placement of the infill soil.  The geogrid shall lay perfectly flat when pulled back perpendicular to the back of the wall fascia.

## Finishing Wall

### Construct pilasters and caps as shown on the drawings.  Secure cap units to the top of the wall with the approved adhesive as specified by the modular block manufacturer according to the drawings and the manufacturer’s recommendations.

### Finish grading above the wall to direct surface run off water away from the segmental retaining wall. Place topsoil as required to restrict the rate of water infiltration into the retaining wall structure.

At the end of each day's operation, the Contractor shall slope the last level of backfill away from the wall to rapidly direct water runoff away from the wall face.  In addition, the Contractor shall not allow surface runoff from adjacent areas to enter the wall construction site.

511-4.01 METHOD OF MEASUREMENT.

The face of the walls will be measured for payment by the square foot.  For the purposes of payment, the face of the walls is defined as the block surface or wall cap surface opposite the retained earth.  By this definition, the face of the walls does not include any top, bottom, back, or side surfaces.

The length measurement will be recorded along the modular blocks below the wall caps and will include the face width of the pilasters and vertical portions of the wall cap. Wall cap overhangs will not be measured for payment.  The length measured for payment will not include any surface perpendicular to the face of the wall.

The height measurement shall be vertical, not parallel to the batter angle.  Measurement shall take place prior to backfill.  The wall below grade will be measured for payment.  The height measurement will be recorded from the top of the leveling pad to the top of the wall cap.  Neither the pilaster cap nor the area of the pilasters above the wall cap will be measured for payment.

If the Engineer determines that the wall embedment or wall height exceeds both the dimensions shown on the plans or working drawings and the height of wall needed to match the backslope requirements at a specific location, the wall area that exceeds the requirements may be deducted from the area measured for payment.

511-5.01 BASIS OF PAYMENT.

Payment for Modular Block Retaining Walls will be full compensation for all labor, tools, equipment and materials required to complete the walls in accordance with the plans, working drawings, specifications, manufacturer’s recommendations, and the directions of the Engineer.

The pay item for Modular Block Retaining Walls will include modular block units, precast concrete wall caps, pilasters, pilaster caps, geogrid, shear connectors, adhesives, geogrid reinforcement at obstructions, and all other appurtenances required to construct a complete modular block earth reinforcement system.

The following items are subsidiary to the pay item for Modular Block Retaining Walls: all excavation required to construct the retaining walls, preparing the retaining wall foundations, leveling pads, and unit drainage fill material.  Also, preparing submittals and mock-ups will be subsidiary, and there shall be no increase in the bid price based on the color, texture, or block shape selected by the Engineer during the mock-up review and approval process.

Clearing and grubbing will be compensated as described in Section 201, Clearing and Grubbing.  Selected material required for foundation preparation will be compensated as described in Section 203, Excavation and Embankment. Infill soil will be compensated as described in Section 205, Excavation, Backfill, and Foundation Fill for Major Structures.  Graffiti protection will be compensated under Section 514, Concrete Surface Treatments.  Drainage pipe will be compensated as described in Section 605, Underdrains.

Payment will be made under:

Pay Item No.	Pay Item 	Pay Unit

511(3)	Modular Block Retaining Walls	Square Foot

Add the following Section:

SECTION 514

CONCRETE SURFACE TREATMENTS

Special Provisions

514-1.01  DESCRIPTION.  This work consists of installing graffiti protection on all modular block retaining walls and precast concrete wall elements.

    - MATERIALS.

Use a two-step graffiti protection system designed specifically for this use.  The system shall consist of a single component clear acrylic base coat covered by a clear urethane finish coat.  This material is not a sealer or vapor barrier and no appreciable discoloration is allowed.

Trained personnel shall apply the material according to the manufacturer’s recommendations.

    - GRAFFITI PROTECTION.  Let all concrete surfaces set at least 28 days before applying any coatings.  Apply the base coat with a roller or sprayer in accordance with the manufacturer’s recommendations.  Apply two coats of the finish coat after the base coat has cured for 72 hours.  Apply appropriate masking as required.

514-4.01  METHOD OF MEASUREMENT.  Measure graffiti protection by the square foot of surface area designated by the Engineer.

514-5.01 BASIS OF PAYMENT.  Payment for grafitti protection will be full compensation for all labor, equipment and materials required to complete the work in accordance with the Plans and specifications.

Payment will be made under:

Pay Item No.	Pay Item 	Pay Unit

514(2)	Grafitti Protection	Square Foot

(2/28/01)R41usc-LA

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-3.01 CONSTRUCTION REQUIREMENTS.

Add the following: Tap the proposed ductile iron sanitary sewer pipe into existing manhole in the same location as the existing sanitary sewer pipe to be replaced.  Repair the invert of the manhole as described in Appendix A, Municipality of Anchorage Standard Specifications, MASS Section 50.05, Connections to Existing Manholes.

Tap the proposed storm drain pipe into the existing inlet by cleanly cutting a hole by approved means at the invert elevation given on the plans.  The hole shall be two (2”) inches larger than the outside diameter of the new pipe. Then, grout the connection with non-shrinking cement mortar.

Connect the proposed four (4”) inch underdrains to the existing inlets by cleanly cutting a hole by approved means into each inlet at the locations shown on the plans.  Establish the invert elevation   at five one-hundredths of a foot (0.05’) above the outlet pipe. The hole shall be two (2”) inches larger than the outside diameter of the four-inch (4”) underdrain pipe.  Grout the connection with non-shrinking cement mortar.

Change “In walkways and bike paths, set the manhole frame flush with the finish surface.” to:  “In sidewalks and pathways, set the manhole frame approximately one-quarter (1/4”) inch, and no more than three-eighths (3/8”) inch, below the finished surface.”

604-5.01 BASIS OF PAYMENT. Add the following: Frames, grates and lids are subsidiary to the drainage structure.

Delete Items 604(1) Storm Sewer Manhole and add the following new pay items:

Pay Item No.	Pay Item	Pay Unit

604(1A)	Storm Drain Manhole, Type 1	Each

604(9)	4 Inch Underdrain Connection to Existing Inlet	Each

(9/1/00)R43 –LA

SECTION 608

SIDEWALKS

### Special Provisions

608-1.01 description. Add the following: This work also consists of constructing asphalt pathways in conformance with the Plans.

608-2.01 MATERIALS. In paragraph number 2 Asphalt Sidewalk and Asphalt Pathway, change the asphalt cement from AC-5 to PG52-28.

608-3.03 CURB RAMPS. Delete the second sentence of this Subsection.

- Add following Subsections:

608-3.04 ASPHALT PATHWAY. Construct asphalt pathway in accordance with subsection 608-3.02 Asphalt Sidewalks.

608-4.01 METHOD OF MEASUREMENT. Add the following:

Asphalt Pathway. By the ton of asphalt concrete in accordance with Section 109, Measurement and Payment. Asphalt cement will not be measured for payment.

Delete the Curb Ramp item and substitute the following:

Curb Ramp.  By each installation, complete in place, including construction of the ramp runs, flares, composite detectable warning tiles and landings necessary to provide a single street-level access.

608-5.01 BASIS OF PAYMENT.  Add the following:  Backing curb will be subsidiary to Item 608(6), Curb Ramp.  The composite detectable warning tiles are subsidiary to item 608(6) Curb Ramp.

Asphalt cement for Asphalt Pathway will not be paid for separately, but will be subsidiary to their respective pay items.  Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

- Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

- 608(7)	Asphalt Pathway	Ton

(2/1/00)R47USC and  (06/11/02)R256USC – LA

SECTION 609

CURBING

Special Provisions

609-3.02 CAST-IN-PLACE CONCRETE CURBING.  Add the following to the sixth paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than two (2”) inches.  (11/6/02)R202USC02

609-4.01 METHOD OF MEASUREMENT. Delete the Backing Curb item and replace with the following:

Base Curb and Planter Curb. By the linear foot along the front face of the curb.

Add the following:

Special forming or shaping of Curb and Gutter at curb ramps and driveways is subsidiary to Curb and Gutter, and will not be measured for separate payment.

609-5.01 BASIS OF PAYMENT.  Delete item 609(2) and replace with the following:

- Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

- 609(2)	Curb and Gutter, Type 1	Linear Foot

- 609(2A)	Base Curb	Linear Foot

- 609(2B)	Planter Curb	Linear Foot

SECTION 610

DITCH LINING

Special Provisions

610-5.01 BASIS OF PAYMENT.  Delete item 610(3) and replace with the following:

- Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

- 610(3A)	Ditch Lining	Linear Foot

SECTION 618

# SEEDING

Special Provisions

618-1.01 DESCRIPTION.  Delete this subsection and substitute the following:  All new or disturbed slopes that are not within planting beds, and any other areas directed by the Engineer shall be overlaid with topsoil and seeded with seed mix. This work shall consist of grading the soil, followed by the application of seed, slope stabilizer, fertilizer and rolling.  It is intended to provide a living ground cover as soon as possible on all exposed areas.

618-3.01 SOIL PREPARATION.  Add the following:  Apply seeding as detailed below immediately after the shaping of the slopes.  Cover all areas to be seeded with topsoil in accordance with Section 620. Grade with a scarifying slope board or rake.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete raking as soon as topsoil is placed.  You may round the top and bottom of the slopes to create a pleasing appearance, but do not disrupt drainage flow lines.  The performance of this work is subsidiary to seeding and will not be paid for directly.

618-3.02 SEEDING SEASONS.  Add the following:  If seeding can not be done prior to August 15th then a dormant seeding application of the seed mix shall be performed after the first frost or October 1st whichever occurs last.  The dormant seeding application may be performed after the closing of contract time as indicated in subsection 105-1.15, Contract Completion.

618-3.03 APPLICATION.  Add the following to the first paragraph:  For all seeded areas, fertilizer shall be applied by the hydraulic method with the application rates as shown in the following table.

Item	Application Rate (per 1000 square feet)

Seed Mix 	1.5 lbs.

Fertilizer (20-20-10)	10.5 lbs.

Soil Stabilizer	**

# **  Add Mulch per Section 619 Soil Stabilization.  Apply Seed Mix before or during application of Bonded Fiber Matrix.

Take extra precautions when applying seed mixtures.  Do not apply seed mix within planting beds.  Provide equipment capable of detailing the areas around the planting beds without overspray onto surfaces not intended for seed (planting beds, walls, lights, fences, sidewalks, etc.)  If overspray does occur, wash those surfaces and remove seed mix from planting beds within 24 hours.

618-3.04 MAINTENANCE OF SEEDED AREAS.  Add the following:  The Maintenance Period for all seeded areas shall be 60 days from the time of the acceptance of the seeding.

A reapplication of fertilizer with water shall be applied between May 1 and September 15 of the following season at a rate of one-half the initial application to all areas that have received seed, as shown on the Contract Drawings.  Notify the Engineer in writing two days prior to the application of fertilizer.  Allow the Engineer ample time for verification of fertilizer application during the maintenance period.

Ensure that the seeded areas stay moist during germination and seedling establishment [as defined by the plants attaining a height of approximately two (2”) inches, and show signs of vigorous growth].  Be prepared to water the seeded areas two to three (2-3) times per day until seedlings have become established.

Water should saturate the first inch of soil, but should not cause soil erosion or wash seed away.  The Engineer will conduct inspections during the germination period following application of seed, to verify the application of adequate amounts of water.  Should inspections reveal that an adequate amount of moisture is not being applied to the seeded areas, the Engineer will notify you that immediate applications of water are needed.  Failure to apply water as requested will result in a restart of the 60-day maintenance period beginning the day of proper application of moisture.  No additional compensation will be allowed for additional applications of water.

If you fail to apply adequate moisture during the germination period for five (5) consecutive days, or after two (2) notices of watering requirements without immediate response, the Engineer may declare the seeding unacceptable.  You will be required to reseed areas that have not been kept moist.  Once adequate water is applied, the Engineer shall restart the 60-day maintenance period beginning the day of proper application of moisture or reseeding.

618-5.01 BASIS OF PAYMENT.  Add the following:  Fertilizer, and mulch, as described above, including any required reseeding will not be paid for directly but will be subsidiary to seeding.

The work described under Subsection 618-3.01 Soil Preparation will not be paid for directly but will be subsidiary to seeding.

Water required for the hydraulic method of application will not be paid for separately, but will be subsidiary to seeding.

Pay Item No.	Pay Item	Pay Unit

618 (1A)	Seeding (Type A)	Acre

SECTION 619

# SOIL STABILIZATION

Special Provisions

619-1.01 DESCRIPTION.  Add the following:  All new or disturbed slopes that are seeded shall use a slope stabilizer comprised of a bonded fiber matrix.

619-2.01 MATERIALS.  Add the following:  The bonded fiber matrix shall conform to the special provisions of Section 727-2.04 of these specifications.

619-3.03 APPLICATION.  Add the following:

The bonded fiber matrix shall be applied while climatic conditions are dry.  Surface coverage thickness shall be 1/8 to 1/4 inch after application.  There shall be no bare spots.   For all seeded areas, bonded fiber matrix shall be applied by the hydraulic method using conventional hydraulic seeding equipment with mechanical application with the application rates as shown in the following table.

Item	Application Rate (per 1000 square feet)

Bonded fiber matrix 				70 lbs

619-3.03 MAINTENANCE AND REPAIR. Add the following: Hydraulically applied soil stabilization matting shall be maintained and repaired in accordance with the manufacturer's written recommendations and Subsection 618-3.04, Plant Establishment and Maintenance, or as directed by the Engineer.

619-4.01 METHOD OF MEASUREMENT. Add the following: Item 619(3).By the square yard measured along the ground for the area designated in the Plans or as directed by the Engineer.

619-5.01 BASIS OF PAYMENT.  Add the following:  Water required for the application will not be paid for separately, but will be subsidiary to the bonded fiber matrix.

Pay Item No.	Pay Item	Pay Unit

619 (7)	Bonded Fiber Matrix	Square Yard

There shall be no adjustment to price in the event that weather, soil conditions or other conditions preclude the use of bonded fiber matrix.

SECTION 620

TOPSOIL

# Special Provisions

620-2.01 MATERIALS. Delete paragraph and substitute the following:  Topsoil shall be as modified in Section 726.

Root barrier shall be as specified in Section 729.

620-3.01 PLACING.  Delete paragraph in its entirety and substitute the following:  For all areas shown on the Contract Drawings, or as directed by the Engineer that are to be seeded, topsoil shall be evenly spread on the designated areas to a minimum depth after settlement of four inches.  Settlement shall be achieved by rolling the topsoil with a water-filled drum approved by the Engineer.

Grade topsoil with a scarifying slope board or rake.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete the grading as soon as topsoil is placed.  You may round the top and bottom of the slopes to facilitate working the slope and to create a pleasing appearance, but drainage flow lines shall not be disrupted.

Do not place topsoil when the site or the topsoil itself is in a condition detrimental to the work.  Keep all roadways, pathways and wall surfaces clean of topsoil during hauling and spreading operations.

620-4.01 METHOD OF MEASUREMENT.  Add the following:  Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.  Root barrier will not be measured for payment.

620-5.01 BASIS OF PAYMENT.  Add the following:  Root Barrier is subsidiary to Topsoil pay items.  Limestone, if required, is subsidiary to Topsoil pay items.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

620(1A)	Topsoil, 4” Depth	Square Yard

620(1B)	Topsoil, 12” Depth	Square Yard

620(1C)	Topsoil, 18” Depth	Square Yard

## SECTION 621

## PLANTING TREES AND SHRUBS

Special Provisions

621-1.01 DESCRIPTION.   Add the following: This work shall also include preparation of planting beds, furnishing and installing shredded bark mulch as shown on plans.

621-2.01 PLANT STOCK.  Add the following:  Variety and species shall be as scheduled on the Contract Drawings.  Trees and shrubs are not to be bare root.

1. 	Nursery Stock.

b.	Delete paragraph in its entirety and substitute the following: Container-grown plants shall be healthy, vigorous, well rooted and established in the container in which they are furnished.  Root mass shall retain its shape and hold together when removed from the container without being root-bound.

Add the following:

c.  Perennials shall have been growing for at least one year and exhibit strong root growth pattern within containers.  Perennial roots shall be visible and thriving when plant is pulled out of its container for inspection.  Weeds, grasses and foreign materials shall be completely removed from the containers of all plants.  Complete removal includes removal of all related roots.  Perennials shall be easily identifiable through thick healthy leaf growth.  Dormant plants will not be accepted.

d.	Coniferous trees shall not come from or have the appearance of trees from Christmas tree farms.  Coniferous trees that appear to be too heavily pruned, sheared, or that have their bottom branches removed, or that do not have acceptable root balls shall be rejected.   The Engineer shall be the sole judge of the plant material.

6.	Inspection.

a.	 Delete Paragraph (a) and substitute the following:

Notify the Engineer ten (10) working days prior to planting, and make available for inspection all plant materials to be used for this project, either in the nursery or collection fields, before plants are dug. Submit to the Engineer certification of species and varieties, size, quantities, and condition, for all materials obtained from suppliers, thirty (30) working days prior to final placement, before plant materials will be accepted.

621-2.03 LIMESTONE.  Add the following:  Apply limestone at a rate determined by the Engineer, as described in Subsection 726-1, and based on the soil analysis tests you provide for the topsoil used for this project.

621-2.04 MULCH.   Add the following sentence:  Mulch shall be shredded bark mulch and shall be placed as shown on plans.

CONSTRUCTION REQUIREMENTS

621-3.02 ADVANCE PREPARATION AND CLEANUP. Add the following:  Prior to final placement of all plant materials, after planting pits have been filled with topsoil, mark with flags, or by other means, the locations where trees and shrubs are to be installed. The marked locations shall be reviewed and approved by the Engineer prior to planting. Notify the Engineer four (4) working days prior to plant location inspection.

621-3.03 PLANTING.

1.	Plant Season.

Delete item 1.  Plant Season, and substitute the following:

1.	Plant Season.

a.	Locally grown:  When native species of locally grown trees and shrubs are furnished for the project, they shall be planted between June 1 and September 15. Trees and shrubs shall be fully leafed-out prior to planting.

b.	Imported and Nursery Grown: When plants are shipped in from out-of-state, or have been container grown in a nursery for at least one year, handling shall be in accordance with nursery recommendations.  Plants imported from out-of-state shall be planted between May 15 and August 1.

2.	Delete item 2.  Excavation, and substitute the following:

Prepare Planting Bed.

a.	Planting beds must be completely prepared prior to placement of plants.  Planting bed preparation includes excavation to depth as shown on plans, loosening of sub-grade soils and placement of topsoil.  Planting beds shall be prepared no more than five (5) days prior to planting.

b.	Prior to excavation of planting areas, ascertain the location of all utilities so that proper precautions may be taken not to disturb or damage any subsurface improvements.  Should obstructions or conflicts be found, promptly notify the Engineer.  Prepare a revised plan that avoids conflicts with the Utility and meets the intent of the original plan to the extent possible.  Submit the revised plan for the Engineer’s approval prior to construction of the planting bed.

c.	Excavate planting beds for trees and shrubs to the depth as shown on plans.  Remove all excess excavated material from the site and disposed according to specifications.

d.	Planting beds with only perennials may be excavated to a depth of 12 inches.  All excavation is to be removed from the site and disposed according to specifications.

e.	Once excavated, sub-grade shall not be compacted.  Heavy equipment shall not be use within planting beds.

f.	Soak planting beds with water.  Allow to drain completely. Place topsoil.  Water planting beds to moisten topsoil. Allow water to absorb in throughout planting bed.  Topsoil backfill shall be moist but not wet, during planting.  Do not plant until topsoil has no signs of excess water including pools, puddles, inability to compact or muddiness.   Notify Engineer if planting beds are not draining properly.

g.	Dig planting holes within the planting bed.  Firmly tamp the base of the planting hole to assure plants will not settle to lower than their proper planting depth.  Water planting holes prior to planting if soil appears dry or if planting bed has not been planted within 24 hours of initial watering.

3.	Pruning.  Delete the last two sentences of paragraph (b.) in their entirety.

- Placing Plants.  Delete Paragraph (b) and substitute the following:

b.	Balled and burlapped plants, plants in wire baskets or containers shall be handled by the earth ball, container, or basket and not by the plant itself.  Wire baskets, and burlap shall be clipped and laid flat on the bottom of the planting pit as indicated on the Contract Drawings.  Containers shall be removed from the site.  The Engineer may reject any plants whose rootballs collapse during planting.

7.	Wrapping.  Delete this paragraph in its entirety, and substitute the following:

Plant materials shall not be wrapped.

Add the following:

- Quality Control.  Do not install plants that do not meet standards, and remove all plants deemed unacceptable from the site.

You will be responsible for quality control.  However, the Engineer may monitor your quality control efforts and may:

  - Inspect plant materials prior to installation.

  - Be on site to approve planting conditions and be present for initial planting.

  - Inspect plants during season.

Inspect trees prior to installation to assure they meet the requirements under this section including that they meet ANSI, are disease free, free of wounds, broken branches, missing or double leaders, co-dominant trunks or other defects.

The Department may, at its own discretion, retain the services of an arborist certified by the International Society of Arboriculture or American Nursery Association. If pruning is required, the Engineer will notify you, and you will complete the required pruning under the direct supervision of the Arborist.

Provide the Engineer with four working days advance written notification of all proposed work so the Engineer or Arborist can review all plant materials and their installation.  The Arborist will report directly to the Engineer.  The Engineer will notify you of any deficiencies noted.  You will remain responsible for the acceptability and continued health of plant materials regardless of the presence or absence of the Engineer or an Arborist.

621-3.04 PERIOD OF ESTABLISHMENT.  Delete this subsection and substitute the following:

Scope

The work during the Plant Establishment Period (PEP) includes all maintenance activities required by Subsection 621-3.07 Maintenance for all planting beds, trees, shrubs, and perennials.

Time

The PEP will begin after all planting is complete and approved by the Engineer, or after the Engineer approves the maintenance schedule, whichever is the latest date.  The PEP shall extend for one calendar year.

If maintenance activities are not being performed according to the approved maintenance schedule, the Engineer may extend the PEP.  If the Engineer chooses to extend the PEP, a week will be added to the PEP for each week of non-performance of maintenance activities.  At the Department’s sole discretion, payment may be deducted for non-performance of the maintenance required by the approved maintenance schedule rather than extending the PEP.

Completion

The PEP will expire only if all maintenance has been completed as required by the approved maintenance schedule for the full term of the PEP in a manner acceptable to the Engineer.

621-3.05 CLEANUP.  Add the following:  Planted and seeded areas shall be kept clean of litter and garbage during the growing season.

621-3.06 PLANT REPLACEMENTS.  Add the following:  Plants shall be replaced following the same details and specifications in the original Contract Documents.  Plants that are dead or dying shall be replaced within 48 hours of notification, May through September.  Plants dead at the end of the growing season shall be replaced at the beginning of the following season.

If damaged plants are not replaced as required, the Engineer may replace or have replaced the damaged items and deduct the cost of said repair or replacement work from remaining payments.

621-3.07 MAINTENANCE.  Add the following:

Maintenance Schedule

Submit a project-specific maintenance schedule [based on the anticipated beginning of the Plant Establishment Period (PEP)] to the Engineer for approval prior to plant installation.  To be approved, the maintenance schedule must address all efforts required by these specifications.

In addition to describing the weekly maintenance routine, the maintenance schedule shall also identify specific dates for less-frequent activities such as pruning, and applying anti-desiccants, fertilizer, and pesticides.

Scope

Maintenance shall begin as soon as each plant is installed and continue in accordance with these specifications for the full term of the PEP.  Maintenance includes:

- The care of all trees, shrubs, perennials, and seeded areas with activities such as watering, disease control, pruning, fertilizing, and weeding;

- Replacement of plants as required; and

- Repair or replacement of related elements such as stakes or mulch.

As a minimum, the following maintenance activities shall be performed:

a.	Mowing.

Seeded areas shall not be mowed.

b.	Watering.

Deep water the root balls of all trees and shrubs on a regular basis.  Deep watering shall provide water penetration through the root zone to a depth of the planting pits with a minimum of runoff.  Rain will not be considered as a substitute for deep watering unless permitted by the Engineer.  Deep water all evergreen plants just prior to freeze-up in order to minimize over-wintering desiccation.  Apply anti-desiccants to conifers as approved by the Engineer.  Application shall occur while the Engineer is present.  Notify the Engineer in writing 4 working days prior to applying anti-desiccants.  Written notice shall state the time and location of application if times differ from the maintenance schedule.

c.	Disease Control.

Apply pesticides, insecticides, or other disease-control methods as necessary to maintain plant health.  Permission of the Engineer and appropriate permits for the application of insecticides from the Alaska Department of Environmental Conservation must be obtained prior to the application of any regulated products.

d.	Pruning.

Prune all plant materials, with appropriate pruning techniques, to remove dead or dying wood and to improve the shape and or vigor of the plants.  Cuts shall not be painted. Pruning of flowering trees shall be scheduled to occur right after flowers drop off or decay.  Damaged trees or those that constitute health or safety hazards shall be pruned as directed by the Engineer at any time of the year.  Do not prune evergreens without the Engineer’s approval.

e.	Fertilizer.

Fertilizer shall be applied to all trees, shrubs, and ground covers in the spring of the following year, prior to June 15 at the rates shown in Table 621-1.  The fertilizer shall be applied as per manufacturer’s recommendations and thoroughly watered into the ground.   Notify the Engineer in writing 4 working days prior to applying any fertilizers.  Written notice shall state the time and location of fertilizer application if times differ from the maintenance schedule.

TABLE 621-1

MAINTENANCE FERTILIZER SCHEDULE

Plant Type			Fertilizer	Application Rate

Coniferous Trees		16-16-16	1 /4 lbs. for each 3” caliper

Deciduous Trees		8-32-16	1 lbs. for each 1-inch caliper

Shrubs and Ground Cover	16-16-16	15 lbs. per 1000 square feet

f.	Weeding.

Keep all planting beds in a weed-free condition during planting and throughout the PEP.  Weeding shall be accomplished on a weekly basis and as requested by the Engineer.  Weeding shall begin immediately after each plant is installed and continue through the PEP.  Weeds include grasses and other undesirable plants within planting beds.

Schedule joint inspections with the Engineer for the end of each growing season to review conditions and to make adjustments to required maintenance.

Schedule a joint inspection with the Engineer at the end of the PEP.  Correct all deficiencies noted during the inspection to the satisfaction of the Engineer.

621-4.01 METHOD OF MEASUREMENT. Delete this subsection and substitute the following:

The quantity of trees and shrubs and ground covers to be paid for shall be the actual number of plants, alive and healthy at the time of final inspection.

621-5.01 BASIS OF PAYMENT.  Add the following:

The quantity of all plant materials accepted in place will be paid for at 70% of the Contract price, per unit of measurement for each pay item.  Payment of the remaining 30% will be made after all deficiencies noted during the inspection at the end of the Plant Establishment Period have been corrected and accepted by the Engineer.

Shredded bark mulch, disposal of unsuitable and surplus material, preparing the maintenance schedule, the maintenance required during the Plant Establishment Period, and the correction of deficiencies at the end of the Plant Establishment Period are subsidiary to planting pay items.

Pay Item No.	Pay Item	Pay Unit

621 (1A)	Trees: Birch (Betula papriferai), 18’ tall, clump	Each

621 (1B)	Trees: Crabapple (Malus Snowdrift), 2-inch caliper	Each

621 (1C)	Trees: Spruce- Green (Picea pungens), 5-feet tall	Each

621 (2A)	Shrubs: Lilac (Syringa vulgaris ‘Night’), 48-inches tall	Each

621 (2B)	Shrubs: Dwarf Lilac (Syringa meyeri’Palibin’), 18-inches tall	Each

621(2C)	Shrubs: Spirea (Spirea Goldflame), 24-inches tall	Each

621(2D)	Shrubs: Rose – Purple leafed (Rosa rubrifolia), 24-inches tall	Each

621(5A)	Ground Covers: Iris (Iris setosa),	Each

SP 5 container

621(5B)	Ground Covers: Lily (Hemerocallis ‘Stella d Oro’),	Each

SP 5 container

SECTION 626

SANITARY SEWER SYSTEM

# Special Provisions

626-1.01 DESCRIPTION. Add the following:  The work includes all efforts described in this Section and in Appendix A, Anchorage Water and Wastewater Utility Supplementary Specifications. Appendix A includes portions of Chapter 50 of the Municipality of Anchorage Standard Specifications (MASS), and amendments to MASS.  The specifications are joined in the following manner:

- Section 626 shall govern regarding all measurement and payment provisions.  All MASS measurement and payment provisions are deleted.

- The Department’s specifications shall govern on all matters related to excavation, backfill, concrete, and surveying.  All references in MASS Chapter 50 that refer to other Chapters of MASS are deleted.

- Where the two specifications are in conflict regarding materials or construction, the MASS amendments and those portions of MASS that have not been deleted from the text shown in Appendix A shall govern.

The work also includes all coordination with the Engineer and AWWU required, including all efforts described in Section 105, Control of Work.

626-2.01 MATERIALS. Delete this Section and substitute the following:

Use materials that conform to the requirements of the specifications attached in Appendix A, Anchorage Water and Wastewater Utility Supplementary Specifications.

626-3.01 CONSTRUCTION. Delete this Section and substitute the following:

Construction shall be completed in accordance with the specifications attached in Appendix A, Anchorage Water and Wastewater Utility Supplementary Specifications.

626-3.02 TESTING. Delete this Section and substitute the following:

Testing shall be completed in accordance with the specifications attached in Appendix A, Anchorage Water and Wastewater Utility Supplementary Specifications.

Add the following:

626-3.03 ASBESTOS CEMENT (AC) PIPE.

Properly handle and dispose of AC pipe in accordance with applicable Federal and State regulations.  Federal regulations governing removal and disposal of asbestos are NESHAP 40 CFR, Part 61, Subpart M; and ASHA 29 CFR 1910.  Alaska Department of Environmental Conservation requirements include, but are not limited to 18 AAC 50, Air Quality Control Regulations; and 18 AAC 60, Solid Waste Management Regulations.  Alaska Department of Labor’s governing regulations include, but are not limited to Occupational Safety and Health Standard, Subchapter 04.0103: Asbestos; 8 AAC 61.600.790 Article 8; and Alaska Workers Right to Know, AS 18.60. The Contractor may abandon AC pipe in place only in strict accordance with regulations.

626-5.01  BASIS OF PAYMENT.

Add the following:  All labor, equipment, materials and coordination required to complete the following work is subsidiary to pay item 626(1-8):

- All costs (except for traffic control, which will be measured for payment as described in Section 643) for pre-construction, construction, and post-construction inspections.

- Abandoning existing pipe and handling/disposing of Asbestos Cement pipe.

- Verifying, in the field, the exact location of connection points, and the exact location of utilities and other obstacles.  Costs incurred for pipe removal and realignment due to improper verification methods shall be borne by the Contractor.

- Connecting pipes and manholes to existing pipes as shown on the drawings.

- Maintaining sewage flow.

- All temporary and permanent fittings of any kind required for the proposed construction or for connecting new pipes to existing pipes, including transition couplings and any other required appurtenance.

- Polyethylene encasement.

- Fittings and all other appurtenances shown in detail drawings.

- All costs involved in testing and acceptance of sanitary sewer systems.

- Preparing submittals and record documents meeting AWWU requirements.

- Shoring and protection of existing utility poles, pad-mounted equipment, pedestals, carriers, cables, conductors, conduits and j-boxes and/or electroliers for sanitary sewer construction.

Delete Pay Item 626(1) and add the following Pay Item:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

626 (1-8)	8” Ductile Iron Sanitary Sewer Conduit, Class 50 	Linear Foot

SECTION 627

WATER SYSTEM

# Special Provisions

627-1.01 DESCRIPTION. Add the following before the first paragraph: For purposes of these specifications, Water Utility shall mean Anchorage Water and Wastewater Utility.

It is the intent of this contract that the Contractor shall maintain water service to all current customers in the project area during the entire period of construction activities. If a temporary water system is necessary to maintain service, the work in this section will also consist of the construction, installation, maintenance and removal of a temporary water system.

The work includes all efforts described in this Section and in Appendix A, Anchorage Water and Wastewater Utility Supplementary Specifications. Appendix A includes portions of Chapter 60 of the Municipality of Anchorage Standard Specifications (MASS), and amendments to MASS.  The specifications are joined in the following manner:

- Section 627 shall govern regarding all measurement and payment provisions.  All MASS measurement and payment provisions are deleted.

- The Department’s specifications shall govern on all matters related to excavation, backfill, concrete, and surveying.  All references in MASS Chapter 60 that refer to other Chapters of MASS are deleted.

- Where the two specifications are in conflict regarding materials or construction, the MASS amendments and those portions of MASS that have not been deleted from the text shown in Appendix A shall govern.

The work also includes all coordination with the Engineer and AWWU required, including all efforts described in Section 105, Control of Work.

The work also includes retaining AWWU to complete a live tap on an existing water main, including all coordination with AWWU, payment to AWWU for all their labor and materials, and providing excavation and trench shoring as needed for AWWU personnel to complete the live tap.  The work also includes trench backfill following the live tap.

627-2.01 MATERIALS. Delete all items except “Bedding and Backfill” and substitute the following:  Use materials that conform to the requirements of the specifications attached in Appendix A, Anchorage Water and Wastewater Utility Supplementary Specifications.

627-3.06 TESTING WATER SYSTEM. Delete this Section and substitute the following:

Testing shall be completed in accordance with the specifications attached in Appendix A, Anchorage Water and Wastewater Utility Supplementary Specifications.

627-3.07 DISINFECTION. Delete this Section and substitute the following:

Disinfection shall be completed in accordance with the specifications attached in Appendix A, Anchorage Water and Wastewater Utility Supplementary Specifications.

    - METHOD OF MEASUREMENT.  Add the following:

- Temporary Water System.  No measurement of quantities will be made.

- Abandon Existing Water Main.  No measurement of quantities will be made.

    - BASIS OF PAYMENT.

Add the following:

All labor, equipment, materials and coordination required to complete the following work is subsidiary to pay item 627(1-12) and 627(23):

- All costs (except for traffic control, which will be measured for payment as described in Section 643) for pre-construction, construction, and post-construction inspections.

- All costs for providing a Temporary Water System, including all coordination, permits, materials, labor, and equipment required to maintain existing water distribution system flows and/or to provide temporary water service.

- Abandoning existing pipe and valves, filling the existing pipe with sand slurry, and handling and disposing of Asbestos Cement pipe.

- Verifying, in the field, the exact location of connection points, and the exact location of utilities and other obstacles.  Costs incurred for pipe removal and realignment due to improper verification methods shall be borne by the Contractor.

- Connecting new pipes to existing pipes as shown on the drawings.

- All temporary and permanent fittings of any kind required for the proposed construction or for connecting new pipes to existing pipes, including bends, plugs, couplings, tees, crosses, reducers, transition couplings, and any other required appurtenance.

- Thrust blocks, pipe joint restraints and polyethylene encasement.

- Fittings and all other appurtenances shown in detail drawings.

- Cleaning, disinfecting, flushing; hydrostatic testing, continuity testing, and coordinating water supply as required for each operation.

- Preparing submittals and record documents meeting AWWU requirements.

- Shoring/protection of existing utility poles, pad-mounted equipment, pedestals, carriers, cables, conductors, conduits, j-boxes and electroliers for water main construction.

Payment for 627(23), Abandon Existing Water Main, will be full compensation for all labor, equipment, and materials required to excavate, decommission the existing water main in accordance with the Plans, and reconstruct the street.  Payment for removal and replacement of pavement and curb and gutter will be made under item numbers 202(2), 202(9), 608(7), and 609(2).  If the Engineer directs replacement of materials encountered during trench excavation, payment for importing selected material will be made under item 203(6A).  Disposal of existing trench material will be paid for as extra work.

Payment for 627(36), 10-inch x 8-inch Water Main Live Tap, will be full compensation for all coordination with AWWU, all labor and equipment to excavate, protect and expose the existing water main, all trench shoring required by OSHA standards and AWWU, and all handling of pipe materials and equipment as required by AWWU for AWWU forces to complete the Live Tap in accordance with the Plans.  Payment for removal and replacement of pavement and curb and gutter will be made under item numbers 202(2), 202(9), 608(7), and 609(2).  If the Engineer directs replacement of materials encountered during trench excavation, payment for importing selected material will be made under item 203(6A).  Disposal of existing trench material will be paid for as extra work.

Delete Pay item 627(1).  Add the following Pay Items:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

627(1-12)	12” Ductile Iron Water Conduit, Class 52	Linear Foot

627(23)	Abandon Existing Water Main	Lump Sum

627(36)	10-inch x 8-inch Water Main Live Tap	Lump Sum

SECTION 634

GEOGRID SOIL REINFORCEMENT

# Special Provisions

    - MATERIALS. Delete this subsection.  Geogrid materials shall conform to the requirements of Section 511, Modular Block Retaining Walls.

634-4.01	METHOD OF MEASUREMENT.  Delete this subsection.

634-5.01	BASIS OF PAYMENT.  Delete Pay item 634(1).  Geogrid is subsidiary to the work in Section 511, Modular Block Retaining Walls.

SECTION 639

DRIVEWAYS

# Special Provisions

639-3.01 CONSTRUCTION. Add the following: complete all work on private property inside the limits of each temporary construction permit, and in full accordance with the terms of each temporary construction permit.

639-4.01 METHOD OF MEASUREMENT. Delete this section and replace with the following:

Driveways and approaches will not be measured for payment.  Reconstruction of driveways and approaches shall be subsidiary to the construction of the adjacent pathway.

SECTION 641

# EROSION, SEDIMENT, AND POLLUTION CONTROL

Special Provisions

641-1.02 DEFINITIONS. Add the following to item 2. ESCP (Erosion and Sediment Control Plan).  Refer to Appendix E for the Erosion and Sediment Control Plan (ESCP).

641-1.03 SUBMITTALS. Replace the first sentence of the second paragraph with the following:  The Department will review the above submittals 14 calendar days before the Preconstruction Conference.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  Delete the first paragraph and substitute the following:  Follow the format presented in the Alaska Storm Water Pollution Plan Guide, for projects disturbing 1 acre or more.  Each Plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.  Each SWPPP shall meet the requirements of the following two paragraphs.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Delete the first paragraph and substitute the following:  Prepare a HMCP for each of the SWPPP’s as required in 641-2.01 for the handling, storage, cleanup and disposal of petroleum products and other hazardous substances (see 40 CFR 177 and 302 for a listing of hazardous materials).  Each HMCP shall meet the requirements of the following five paragraphs.  (06/03/03)R272USC02

641-3.01 CONSTRUCTION REQUIREMENTS.  Delete the first sentence and substitute the following:  Do not begin ground-disturbing work until you receive authorization from the Engineer.  To obtain authorization, submit evidence to the Engineer that the EPA has acknowledged receipt of the NOI and DEC has acknowledged receipt of the NOI and approved your SWPPP.

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-3.01 GENERAL.  Delete item 10 and substitute the following:

- Cross sections at retaining wall locations.  Provide the Engineer cross section data, taken at 25-foot intervals, 10 days prior to ordering retaining wall materials.  At that time, the Engineer will verify the plan quantity and make any necessary adjustments to the wall size, design or configuration.

- All other surveying and staking necessary to complete the project.

(11/18/02)R255USC

642-3.03 MONUMENTS. Delete the second sentence of the first paragraph and substitute the following:  Reference all property markers/corners, monuments or accessories which may be disturbed or buried during construction.  Prepare and record Monument Record Forms in the appropriate Recorder’s Office prior to disturbing monuments.  Monument Record Forms may be obtained from the Engineer.  Reestablish monuments in their original position prior to the completion of the Project.  Then, prepare and file a Monument Record Form for each reestablished monument. (05/16/03)R269USC

642-5.01 BASIS OF PAYMENT.  Add the following after the first paragraph: Where the bid item for Reference Existing Monument does not appear in the bid schedule, all work necessary to reference existing monuments and prepare and file Monument Record Forms is subsidiary to Item 642(1) Construction Surveying.  Five percent of the contract lump sum bid price for Item 642(1) will be withheld until the Monument Record Forms are prepared and recorded in the local Recorder’s Office.  Where the bid item for Reference Existing Monument does appear in the bid schedule, all work associated with preparing and recording the Monument Record Forms is subsidiary to Item 642(9) Reference Existing Monument.  You will not receive any payment for Item 642(9) until the Monument Record Forms are prepared and recorded in the local Recorder’s Office. (05/16/03)R269USC

SECTION 643

TRAFFIC MAINTENANCE

# Special Provisions

643-2.01 MATERIALS. Add the following:

17.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

643-3.03 PUBLIC NOTICES. Add the following Organizations: Federation of Community Councils, Scenic Foothills Community Council, Northeast Community Council, and Pulse Newspapers.

643-3.04 TRAFFIC CONTROL DEVICES.  Delete the first sentence of the eight paragraph and substitute the following:  All items paid under this Section remain your property except:

Permanent construction signs shown on Sheet K1 will remain the property of the Department.  At the end of your project, cover the permanent construction signs entirely with metal or plywood sheeting as required to protect the signs until the next construction season.

Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift unless otherwise shown on an approved Traffic Control Plan.

Add the following to 3. Fixed Objects.: At the end of each continuous work shift remove all obstructions greater than 4 inches above the nominal foreslope grading.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, and maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER.  Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full, unimpeded use by the public.  Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING.  Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic except as listed below.  The following restrictions will be allowed:

Weekend Closure:

You will be allowed one weekend closure for the intersection of Muldoon Road and 20th Avenue from 2000 hours Friday to 0600 hours Monday to accomplish the water main crossing.  Schedule an inspection of the existing illumination conduit crossing to be reused near Station 155+50 so that replacement conduit can be placed with the water relocation if necessary.  If you believe replacement conduit is required, notify the Engineer for verification and then complete the necessary electrical work during the water main crossing.

Restriction to a Single Northbound Lane:

You will be allowed to restrict northbound traffic to a single lane, except from 0630 hours to 0930 hours and from 1500 hours to 1830 hours,

Monday through Friday.

Closure of the Eastern-Most Northbound Lane, Station 146+42 to 168+90:

A continuous lane closure is shown on the drawings that would close the center continuous two-way left-turn lane and detour northbound traffic on Muldoon Road to the west to make use of the center lane for northbound traffic.  You may use this detour on a continuous basis as long as you are prosecuting the work in the area of that detour on a continuous (6-7 day per week) basis.  You may close the Parkway Drive/Muldoon Road intersection for the duration of the detour.

If you suspend your work for more than 2 days, remove the detour and restore full traffic in its original configuration unless ACS, GCI, CEA, or ENSTAR is actively using the area to relocate utilities.

Add the following:

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  Make every effort not to delay school buses through the construction work zone.

643-3.09 INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following:  Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer. (05/13/03)R222USC02

Add the following Subsection:

643-3.10 PUBLIC INFORMATIONAL PROGRAM. Provide a Public Information (PI) professional to accomplish the work outlined in this Subsection. The PI person shall have a minimum of five (5) years demonstrated professional experience in performing similar informational campaigns involving multi-media, i.e.: television, radio, newspaper and public presentations. S/he shall be responsible for all aspects of this service including coordination; public interaction; preparing graphics; developing mailing lists; supplying updated information; and all labor, equipment, postage, and materials to provide this service. Logos, reports, software, visual aids, graphics and work products developed for this Project shall become the property of the Department, and delivered to the Engineer at the end of the work. The PI professional's office shall be equipped with a facsimile machine.

This professional shall be responsible for the following tasks for the PI Program:

- Mail-outs. Design and distribute three informational mail-outs/flyers each construction season, which will be approved by the Engineer. The mail-outs shall contain most or all of the following:

a.	a brief description and map of the Project,

b.	the Contractor's anticipated construction schedule,

c.	a narrative of the possible delays to the traveling public through the Project,

d.	detailed traffic information such as intersection, lane and/or sidewalk closures, their corresponding detours, and their effective dates,

e.	locations of temporary bus stops,

f.	a description of possible impacts to abutting property accessing the Project,

g.	a listing of locations where current Project information may be obtained,

h.	date and times of Open House meeting as required by the Engineer,

i.	the Contractor's 24-hour message number and office telephone number, and

j.	the Engineer's Project office telephone number, e-mail address, and the web site address containing Project updates, schedules and general narrative information.

The last mail-out shall also contain a questionnaire to aid in preparing the final Report required under Item 5 below.

The mail-outs shall be sent to all addresses within one city block on either side of the Project corridor, and shall be addressed to both the owner of record and the current tenant. It shall be distributed at the following times:

a.	two weeks before construction begins,

b.	at the approximate one-third point of construction season, and

c.	at the approximate two-thirds point of construction season.

2.	Weekly Notices. Write and submit weekly Public Information Notices that identify road closures, restrictions to traffic, and detours. Areas of potential traffic delay shall be emphasized and alternative routes noted. Coordinate this effort with the Engineer and the Department's NAVIGATOR Informational Program. Telephone numbers for further information, and the date and time for the next scheduled public open house meeting shall be provided. The Engineer will approve the Notices. Hand carry or fax the Notices to the local news broadcasting media, emergency services, public service organizations and the major retailers near the Project corridor.

Notices shall also be distributed to the following local officials and transportation organizations, including but not necessarily limited to:

Alaska Carriers Association

Alaska Trucking Association

Alaska State Troopers

Anchorage Police Department

Anchorage Fire Department

Anchorage School District

People Mover Transit Authorities

Local Emergency Medical Services

US Postal Service

The Notices shall be submitted at the following times:

a.	one week prior to the beginning of construction,

b.	on Wednesday of each week during construction, and

c.	prior to any major change or disruption to traffic or local access.

Additionally, the PI professional shall notify business and residents that front the Project or scheduled road closures of driveway, curb or sidewalk reconstruction, or any other work affecting them. Property owners within the work segment shall receive the Notices a minimum of one week prior to the commencement of the work within their segment. Lastly, provide daily information to those media who do non-paid public service road reports or announcements, and/or "Eye-in-the-Sky" commuter road reporting.

3.	Public Open House Meetings.  Prepare presentations for the Engineer's Open House Meetings, and for each of the Community Councils that represent areas affected this Project. The Community Council meetings attended shall be the last regularly scheduled meetings prior to the beginning of construction.  Presentation size graphics shall be used to help explain the Project to the general public.

The PI professional shall be the Contractor's representative and spokesman able to speak for him. The PI professional shall be available to attend additional public meetings, up to five, as requested by the Engineer.

4.	Other Agency Coordination.  Coordinate with the Anchorage People Mover Transit Department (343-8294) to take advantage of programs which will help decrease traffic through this Project, such as Park-and-Ride with express bus service, Ride Share, and the car pooling program. Also coordinate any major detours and closures with emergency service providers (police, fire, and ambulance), Anchorage School District bus operators, postal service, and the People Mover.

5.	Final Report.  Before project completion, submit a Report evaluating the Public Informational Program as detailed under this Subsection. The Report shall include an outline of the program, an analysis of the program's effectiveness, and suggestions on how to improve the program's effectiveness, economy, and usefulness on future projects.

6.	Project Progress Meetings.  Attend all scheduled or special Project meetings between the Contractor and the Engineer at the field office.

7.	Web Page.  Generate an INTERNET web site for the Project containing Project updates, schedules and general narrative information. Add links to the Department's NAVIGATOR Home Page (www.dot.state.ak.us/navigator.html). Update the site weekly.  (05/01/03)R102M98

643-4.01 METHOD OF MEASUREMENT.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.  (05/13/03)R222USC02

Providing mail-outs, notices, displays for open house and public meetings, and providing weekly notices with updates will not be measured for payment. (05/01/03)R102M98

643-5.01 BASIS OF PAYMENT.  Add the following:  The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

Payment for Item 643(31) will be made on a contingent sum basis for work completed and accepted by the Engineer.  (05/01/03)R102M98

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $2.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Foot Foot Foot Each | $0.30 $0.65 $0.07 $40.00 |

The Engineer will pay for Item 643(15), Flagging on a contingent sum basis at the rate of $36.00/hour. The Engineer does not require a change order/directive for the flagging pay item.  Flagging associated with Change Order work will be paid at the prices agreed to in the Change Order, or on a time and materials basis in accordance with Subsection 109-1.05. (05/14/03)R222USC02

Delete Item 643(15) and substitute the following:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15) Flagging | Contingent Sum |
| 643(31) Public Informational Program | Contingent Sum |

Add the following Section:

# SECTION 645

TRAINING PROGRAM

Special Provision

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 OBJECTIVE.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "yellow pages" of this document.

645-3.01 GENERAL.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless you can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to you where the apprentices/trainees are concurrently employed on the project and you do one or more of the following: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by you, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by you.  Training program approval by the Department for use under this Section is on a project-by-project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in your judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and you employ that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  You must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts.  In the event you subcontract a portion of the work, you shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with you; compliance or non-compliance with these provisions rests with you and sanctions and/or damages, if any, shall be applied to you in accordance with Subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  You will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section prior to your submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at your discretion, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, you will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds you may receive, unless such other funding sources specifically prohibit you from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to you if you fail to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where you have failed, by the end of the project, to provide the required number of hours of training and have failed to submit acceptable good faith efforts documentation which establishes why you were unable to do so, you will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

(10/29/91) S16

Payment will be made under:

###### Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program, 1 Trainee/Apprentice	Labor Hour

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this Subsection in its entirety and replace with the following:  Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  If revisions are required, make them promptly.   The finalized CPM Schedule must be completed and accepted prior to commencement of any work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.   60-Day Preliminary Schedule.

Delete the first sentence of item 3. Schedule Updates.  and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly, or as deemed necessary by the Engineer.

(12/13/02)R261M98

Add the following Section:

SECTION 647

# EQUIPMENT RENTAL

Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and your operations shall be in accordance with the Engineer's instructions at all times. The Engineer’s instructions shall be to your supervisory personnel only, not to the operators or laborers. In no case shall the Engineer’s instructions be construed as making the Department liable for your responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by you shall be, and shall remain during the work hereunder, solely your employees.

Furnish, without direct compensation, a job superintendent or your representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by you and involved in the performance of the work. Also, furnish without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by your representative at the end of each shift, and a copy will be provided to your representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(2), Wide Pad Dozer, 65 HP Minimum will be paid on an hour basis at the rate shown on the bid schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher horsepower than specified will not entitle you to any extra compensation.

(11/12/98)R15USC

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 647(2) Wide Pad Dozer, 65 HP Minimum | Hour |

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-4.01 METHOD OF MEASUREMENT.  Add the following:

The work under pay item 660(18) Adjust Junction Box will be measured by each junction box of any size adjusted to match the final grade, complete and accepted in place.

643-5.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

660(18)	 Adjust Junction Box	Each

Add the following Section:

SECTION 662

SIGNAL INTERCONNECT

Special Provisions

662-1.01 DESCRIPTION. This item consists of all work required to furnish and install signal interconnect in conduit as shown on the plans and along the route indicated, or as directed by the Engineer.

662-2.01 MATERIALS. These specifications and Section 660, Signals and Lighting, shall apply. The interconnect cable shall be a 25 pair #19 telephone cable conforming to REA Specification PE-39. The interconnect cable shall be installed in a two (2”) inch galvanized rigid metal conduit.

Completed splices shall be encapsulated in waterproof re-enterable type cases. Acceptable splicing materials are listed in the REA Bulletin 344-2 entitled "Lists of Materials Acceptable for use on Telephone Systems of REA Borrowers".

All materials shall be submitted for review and approval per the requirements of subsection 660-1.03, Equipment List(s) and Drawings.

662-3.01 CONSTRUCTION REQUIREMENTS. The signal interconnect is comprised of cable, conduit, junction boxes, other necessary hardware required to complete the item, cable splicing, and the termination of conductors on terminal blocks.

Install junction boxes at all abrupt changes in conduit alignment and on a maximum spacing of 250 feet. An abrupt change is defined as an angle point or curve with a delta angle greater than 45 degrees. All signal interconnect splices shall be made in Type II or III junction boxes, and completed in accordance with REA PC-2 for splicing telephone cables. Make splices in the locations shown on the drawings.  Splices in the interconnect cable will be kept to an absolute minimum, and approved by the Engineer beforehand.

662-4.01 METHOD OF MEASUREMENT. Signal interconnect modifications will be measured complete and in place as accepted by the Engineer.

662-5.01 BASIS OF PAYMENT. The contract unit price for signal interconnect modifications will be full compensation for furnishing all materials, labor, and equipment required to complete the work as specified and shown on the plans.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

662(2)	Signal Interconnect Modifications	Lump Sum

SECTION 703

AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 |  |  |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| ## No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

(2/28/00)R117USC

703-2.07 SELECTED MATERIAL. Add the following:

- Infill Soil, shall consist of Selected Material, Type A.  The maximum particle size shall be limited to ¾ inch unless tests have been performed to evaluate potential installation damage strength reduction (RFID) for the geosynthetic reinforcement.  Refer to Section 511 Modular Block Retaining Walls.

If you use steel reinforcement to support the retaining wall, the infill soil shall meet the following:

| Property | Criteria | Test Method |
| --- | --- | --- |
| Resistivity | > 3000 ohm-cm | AASHTO T-288-91 |
| pH | >5<10 | AASHTO T-289-91 |
| Cholorides | < 100 PPM | AASHTO T-291-91 |
| Sulfates | < 200 PPM | AASHTO T-290-91 |
| Organic Content | 1% Max. | AASHTO T-267-86 |

If you use geosynthetic reinforcement to support the retaining wall, the electrochemical criteria may vary depending on the polymer.  Include documentation of standards and testing requirements in the retaining wall submittal.  At a minimum, the pH shall be greater than 4.5 and less than 9.

703-2.10 POROUS BACKFILL MATERIAL.  Delete Table 703-7 and substitute the following:

TABLE 703-7

REQUIREMENTS FOR GRADING FOR UNIT DRAINAGE FILL MATERIAL

| Sieve Designation | Percent Passing By Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 75-100 |
| No. 4 | 0-10 |
| ## No. 50 | 0-5 |

# SECTION 706

# CONCRETE AND PLASTIC PIPE

Special Provisions

Delete  706-2.06 PLASTIC PIPE FOR SANITARY SEWERS.  Replace all material specifications for Sanitary Sewers with material specifications included in the AWWU specifications attached in Appendix A.

(04/01) -LA

# SECTION 724

SEED

# Special Provisions

Delete Table 724-1 in its entirety and substitute the following:

TABLE 724-1

SEED REQUIREMENTS

Seed Mix:  (Application Rate:  4 lbs./1000s.f.)

PROPORTION

NAME	BY WEIGHT	PURITY	GERMINATION

Bering Hairgrass

(Deschampsia beringensis)	50%	95%	90%

Arctared Fescue

(Festuca rubra)			30%		95%			90%

Nootka Lupine

(Lupinus nootkaensis)	20%	95%	70%

SECTION 726

TOPSOIL

Special Provisions

726-2.01 TOPSOIL.  Replace item (2.) with the following:

2.	Topsoil shall contain not less than 15 percent and no greater than 25 percent organic matter by dry weight as determined by ATM T-6.

Delete the gradation table in the third paragraph and substitute the following:

Sieve Designation	Percent Passing (by Weight)

10	100

20	 90

100 	 50

Delete last sentence in second paragraph and substitute the following:

The Contractor shall submit to the Engineer, 10 working days prior to final placement, a soil analysis for particle size, nutrient content and organic content, before any topsoil shall be accepted for this project.  The Engineer may test the topsoil at any time to verify compliance with the topsoil analysis.  If the supplied topsoil does not meet specifications in this Section, the Contractor shall supply new topsoil of a quality required to meet the section standards.

Delete the fertilizer requirements (not the limestone requirements) as stated in this subsection and substitute the following:

Nitrogen	21 – 35 PPM

Phosphoric Acid	11 - 20 PPM

Potassium		76 - 150 PPM

TABLE 726-1

LIMESTONE REQUIREMENTS

Add the following:

Limestone shall be incorporated into the topsoil at a sufficient rate to attain a pH of between 6.0 and 7.0.

Add the following Subsection:

SECTION 727

## SOIL STABILIZATION MATERIAL

Special Provisions

727-2.01 MULCH.

Add the following:

3.	Shredded Bark Mulch.

Shredded bark mulch, to be placed throughout planting beds of all newly planted trees and shrubs.  Shredded bark mulch shall consist of aged spruce, fir, hemlock, birch, or aspen wood and bark that is aged at least one year and has a deep, dark brown color.  Mulch shall be comprised of a minimum of 70% bark and shall conform to the following gradation:

Screen Designation	Percent, By Loose Volume

1 inch	70

Shredded bark mulch shall not contain resin, tannin, or other compounds in quantities that are detrimental to plant growth.  It shall be reasonably free of sawdust, dirt, and twigs.  Mulch shall not contain foreign matter or refuse and shall have the characteristic to be spread evenly so as to form a uniform consistent mat that inhibits weed growth and that will not blow or wash away.  Shredded bark mulch shall be spread evenly in all planting beds at three-inch depth.

4.	Bonded Fiber Matrix.

Bonded fiber matrix to be applied using hydraulic methods and placed on all seeded areas shall have a moisture content of 9-15% by weight and shall be composed of refined wood fiber (90% by weight) and blended hydrocolloid-based binder (10% by weight).  The bonded fiber matrix shall have a natural color and shall be able to hold over ten times its own weight in water.  It shall decompose to carbon dioxide and water and shall form a water resistant matrix that retains soil moisture, enhances seed germination, holds soil on virtually all slopes and soil types and absorbs rainfall evenly.

727-2.04 HYDRO MATTING. Provide a hydraulically applied system of long strand fibers joined together by a high-strength adhesive to create a continuous three-dimensional blanket that adheres to the soil surface to form a bonded fiber matrix. Apply the system to the soil as a viscous mixture, which upon drying, creates a high strength, porous and erosion resistant mat. Upon drying, the matrix shall not inhibit the germination and growth of plants beneath the layer. The matrix shall retain its form despite rewetting.

(11/06/02)R223USC

SECTION 729

## GEOTEXTILES

Special Provisions

Add the following:

729-2.05 ROOT CONTROL FABRIC.  Furnish a landscape fabric whose purpose is to prevent structural damage due to root penetration.  The fabric shall provide both physical and chemical barrier zone to restrict vegetative root growth.

1.	ASTM Referenced standards: D-5261 Test Method for Measuring Mass per Unit Area of Geotextiles; D-4632 test Method for Grab Breaking Load and Elongation of Geotextiles; D-4833 Test Method for Index Puncture Resistance of Geotextiles, Geomembranes and Related Products; D-4533 Test method for Trapezoid Tear Strength of Geotextiles; D-4491 Test Method for Water Permeability of Geotextiles by Permittivity; D-4751 Test Method for Determining the Apparent Opening Size of a Geotextile; D-4355 Test Method for Deterioration of Geotextiles from Exposure to Ultraviolet Light and Water.

2.	EPA Standards EPA CG Water Solubility 1500 and EPA CG Vapor Pressure 1600

3.	Fibers of root control barrier shall consist of long chain synthetic polyolefins (at least 95% by weight) and a UV stabilizer.  The fibers shall be formed into a stable network such that the filaments or yarns retain their dimensional stability relative to each other.

4.		Product major composition and ingredients shall include active chemical Trifluralin and inert ingredient 100% Spunbonded polypropylene, polyethylene and carbon.