PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

# SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	Three active eagle nests are known to exist within the project limits.  See drawings and section 107-1.01 of the Special Provisions for details.

2.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

3.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

- Quantity Computations

b.	Cross Sections

- Geotechnical Report, "Unalaska Airport Beach Road, Project No. RS-0310(4)/58242, Central Region, April 1994".

d.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

e.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

- Standard Specifications for Highway Construction 1998 Metric. ($25.00)

- Documentation for Determination of No Adverse Effect, April 2001

- Unalaska Airport Beach Road, As Built, 1994

- Unalaska Airport Beach Road Construction Photos, 1995

4.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

5.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

6.	The Materials Certification List (MCL) has been included in Appendix A. This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

SECTION 101

DEFINITIONS AND TERMS

Standard Modification

101-1.03 DEFINITIONS. Add the following:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed.

## (06/25/99)M 68

Special Provisions

101-1.03 DEFINITIONS. Add the following definition:

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the 0.075 mm  screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75 mm  material. (11/29/01)R1M98

SECTION 102

## BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (2/1/00)R171M98

# SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modification

103-1.01 CONSIDERATION OF BIDS.  Add the following after item 9.:

In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State.

(10/28/99) M 84

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”.

(06/25/99)M 69

SECTION 105

## CONTROL OF WORK

### Standard Modification

105-1.02 PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, the Contractor shall furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. The following utilities are known to have facilities in the area:

- City of Unalaska Department of Public Works & Utilities (Water, Sewer, & Electric Utility) (907) 581-1260

- Interior Telephone Company (Telephone, Fiber Optic, and Cable Television)

1-800-478-3127

- Alyeska Seafoods (Seafood Outfall Lines)  (907) 581-1211

- Royal Aleutian Seafood’s (Seafood Outfall Line) (907) 581-1671

5.	Unisea Inc. (Seafood Outfall Line) (907) 581-1258

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

(5/31/01)R3M98

Specific coordination requirements for the specific utilities are included below for this contract:

Interior Telephone Company & Eyecom. (ITC & Eyecom) have existing underground Telecommunications and Cable Televisions facilities located within this project.  No relocation of ITC & Eyecom facilities is anticipated for this project-planned improvements.  The Contractor shall be required to shore the existing ITC & Eyecom facilities to facilitate the storm-drain installation. The contractor shall notify ITC & Eyecom at 907-563-2003 to establish a point of contact and determine were to send the written notice fifteen (15) calendar days prior to starting the storm-drain excavation in the locations listed below.  The Contractor shall furnish a copy of the written notice to the utility, to engineer.  Below is a list of locations that the contractor shall be required to shore the existing ITC & Eyecom facilities.

UNDERGROUND FACILITIES

| Under Drain Station | Type of Facility | Shoring Required |
| --- | --- | --- |
| 1. 7+197 | 4-100mm PVC conduits & Contents | Yes |
| 2. 7+260 | 4-100mm PVC conduits & Contents | Yes |
| 3. 7+297 | 1-100mm PVC conduit & Contents | Yes |

The Contractor shall provide a shoring plan to ITC & Eyecom for review and approval for each of the locations listed above prior to starting the storm-drain excavation in the above locations. The Contractor shall allow ITC& Eyecom five (5) calendar days to review and approve the shoring plan. The Contractor shall allow ITC & Eyecom personal free access to the locations listed above to inspect the backfill operation around the ITC & Eyecom facilities.

OUTFALL LINES

There are three existing outfall lines that are located within this project’s limits. The outfall lines are owned and operated by Alyeska Seafood’s, Royal Aleutian, and Unisea Inc.  Relocation of the seafood processor outfall lines is not anticipated for the project.  Below is the approximate outfall line road crossings locations.

| Location/Station | Type of Facility | Owners Name |
| --- | --- | --- |
| 1. 2+478 | 1-400mm Outfall line | Unisea Inc. |
| 2. 3+762 | 2-HDPE Outfall lines (1-250mm & 1-400mm ) | Alyeska Seafood’s & Royal Aleutian Seafood’s |

105-1.07 COOPERATION BETWEEN CONTRACTORS. Add the following: The following projects will be under construction concurrently with this project:

Airport Safety Improvements

City Dock Expansion

City of Unalaska City Streets

Ulatka Drive Improvements

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects so as to minimize impact on the travelling public, and to minimize conflicts with the work being performed under the other contract.  (2/1/00)R175M98

105-1.12 LOAD RESTRICTIONS.  All overload permits are subject to seasonal load restrictions.

Routing shall be as prescribed by the Permit Officer.  The Permit Officer may be contacted at (800) 478-7636 or (907) 345-7636.

Alternate axle configurations and loading which may reduce the overload movement restrictions and conditions may be submitted to the Engineer for review.

(01/08/97)R103m

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Plant Establishment and Maintenance; and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract. (02/06/02)R237M98

### Standard Modification

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Delete this Subsection in its entirety and substitute the following:  Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

- The act, event, or condition the claim is based on.

- The Contract provisions which apply to the claim and provide relief.

- The item or items of Contract work affected and how they are affected.

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630.

(03/26/01) M 101

Special Provisions

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

## CONTROL OF MATERIAL

Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.  (08/31/99)S 13

106-1.02 LOCAL MATERIAL SOURCES.

Under Item 2. Inspection and Acceptance, add the following:

In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (5/7/01)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following: When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 224

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO TP 53

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T166/T275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

(7/26/01) S87

SECTION 107

## LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01 LAWS TO BE OBSERVED. Add the following:

Eagle Nest Restrictions

Active bald eagle nests are located at approximately stations 2+174, 35 meters left of centerline 2+800, 30 meters right of centerline, and 4+458, 50 meters right of centerline.  To avoid violations of the Bald Eagle Protection Act, the following measures must be observed:

In order to permit eagles to initiate nesting, operations shall not take place within 100 m of the nest from March 1 to May 31.  This period shall continue to August 31 if the nest contains a nesting pair of eagles. If the nest is not occupied by May 31, activities may proceed provided the nest and nest support are not jeopardized.

It is possible to conduct operations during the restricted time periods, even if the nest contains a pair of nesting eagles.  To do so, notify the Engineer 2 weeks prior to beginning activities.  Procure the services of an eagle monitor as specified under Section 651, Eagle Monitoring.  The eagle monitor shall observe the nest and determine whether operations cause a disturbance to the nesting eagles.  The eagle monitor shall work independently of the Contractor’s operation and have reporting authority to the Engineer.  If any evidence of disturbance is observed, operations will be stopped or modified to comply with the Bald Eagle Protection Act as directed by the Engineer.

It is expected that the eagles will be disturbed less later in the summer than they will be early in the summer.  Consequently, it is recommended that the work shown in the vicinity of the eagle nests be executed late in the summer, after the other work is completed.

If additional nests are discovered within the vicinity of the project site, the U.S. Fish and Wildlife Service must be notified immediately by calling (907) 260-2809 or (907) 271-2780, prior to any construction activities, for further site evaluation. (2/28/00)R51M

107-1.02 PERMITS, LICENSES AND TAXES. Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineation’s of any site outside the project limits or not previously permitted, impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

107-1.07 ARCHAEOLOGICAL AND HISTORICAL DISCOVERIES. In the first sentence, insert the words “or historic” after “prehistoric”.

In the first sentence, insert the words “at that location” after “operations”.

Delete the last sentence.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following: If the Contractor requires water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

(5/21/01)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following before the last paragraph: Where the Contractor's activities meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15 feet) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.(7/30/99) R170M98

Add the following subsections:

107-1.21 PERMITS. Add the following:  It is the Contractor’s responsibility to obtain all permits required for actions not permitted previously by ADOT&PF.  The Contractor is responsible for complying with all permit stipulations, conditions and/or terms.  Agencies to contact for permit information may include, but is not limited to, the U.S. Army Corps of Engineers, the Environmental Protection Agency, the U.S. Fish and Wildlife Service, the Alaska Department of Fish and Game, the Alaska Department of Environmental Conservation, the Alaska Department of Natural Resources, and local or regional governments.  The Contractor shall provide timely notification of such actions and permit acquisitions as may be required by federal, state, regional, and local authorities.  The Contractor shall provide copies of all permits, and applicable Federal and State notifications to the Project Engineer.

107-1.22 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

# Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(01/22/02)S 80

## SECTION 108

## PROSECUTION AND PROGRESS

# Standard Modification

108-1.01 SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4. and add the following to Item 5.:

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts.

(10/28/99)M70

Special Provisions

108-1.03 PROSECUTION IN PROGRESS. Add the following under item no. 1:  Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department. (4/22/99)R250M98

Delete Items 5 of the first paragraph and substitute the following:

5.	The submittals identified under subsection 641-1.03, Submittals.

(5/16/00)R160M98

108-1.04 LIMITATION OF OPERATIONS.  Add the following:  Complete all work designated on Typical Sections III, V, and VI on or before September 30, 2002. Within each station range of Typical Sections V and VI, the Asphalt Concrete, Type II, Class B shall be complete and accepted for traffic within seven days of commencing existing pavement removal.

No existing pavement shall be removed from station ranges designated on Typical Sections I, II, and IV in the year 2002.  Asphalt Concrete, Type IV, Class B shall not be placed prior to May 15, 2003 or after September 1, 2003.

(ANH, 05/29/02)

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date. (2/15/01)R242M98

SECTION 109

## MEASUREMENT AND PAYMENT

Standard Modification

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1. Labor:

Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work.

(5/31/00) M90

1. 	Labor. Replace sub-paragraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e.

Delete item 5. and substitute the following:

# 5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor. (02/08/01) M71

Special Provisions

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (1/27/00)R14

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount. (09/05/01)R137

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Unalaska/Dutch Harbor, Alaska, at a location acceptable to the Engineer. (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The Engineer makes the determination of CUF after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the Department reduces the quantity of work of a bid item involving a DBE firm, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If the Engineer approves a DBE replacement, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form

25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The DBE Liaison Officer will make the decision on reconsideration.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control

of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

4.	DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-3.03 REMOVAL OF BRIDGES, CULVERTS AND OTHER DRAINAGE STRUCTURES. Add the following after the second paragraph: Remove, dispose or salvage sanitary sewer manholes designated for removal by the plans or as directed by the Engineer.

Remove manhole frame and cover, dustpan, adjusting rings and cone section or reducing slab for existing sanitary sewer manholes designated for removal by the Plans or by the Engineer. Plug all conduits intersecting the manhole and fill the remaining barrel sections of the abandoned manholes with material meeting the requirements of selected material, Type C and compact it to the satisfaction of the Engineer.

Carefully remove and deliver salvaged materials to a site identified by the Engineer. Provide a disposal site for non-salvageable and unwanted materials.

All existing manhole frames, covers, dustpans, adjusting rings, cone sections and reducing slabs removed but not reinstalled under these Special Provisions shall become the property of the Contractor.  Materials may be reused if they are undamaged, of satisfactory quality and approved by the Engineer.  No materials are reused or reinstalled until they have been thoroughly cleaned by the Contractor and inspected by the Engineer.  (2/2/00)R18M98

Delete the fourth paragraph and replace with the following:  Remove drainage structures designated for removal in their entirety.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following:

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84M98

Remove existing pavement in areas of distress, cold patches or potholes as shown on the drawings or as directed by the Engineer. Sawcutting is required when the resulting joint will not be overlayed and when directed by the Engineer. The pavement shall be removed to a distance of 300 mm beyond the limits of excavation. Pavement that is removed shall be replaced with Asphalt Concrete as shown on the plans in accordance with the requirements of Section 401, Asphalt Concrete Pavement. (2/28/01)R257M98

Prior to removing curb and gutter designated for replacement, survey the existing curb and gutter at the same intervals dictated for staking curb and gutter construction. Install replacement curb and gutter at the same line and grade as the existing curb and gutter, except as noted otherwise and as necessary to assure positive drainage toward drainage structures.  (ANH, 04/22/02)

Add the following subsections:

202-3.06 SALVAGING. Notify the Engineer, five (5) days prior to removing manholes and inlets. Upon excavation, the Engineer will physically identify those manholes, inlets or portions thereof to be salvaged.  All manholes, inlets or portions thereof so designated will be delivered to the City of Unalaska Department of Public Works Maintenance Yard located at 1035 E. Broadway Avenue.  All remaining items removed become the property of the Contractor. (8/30/00)R258M98

202-5.01  BASIS OF PAYMENT.  Add the following:  Sawcutting and other methods of pavement cuts, if required, will not be paid for directly, but will be subsidiary to Item 202(2), Removal of Pavement.

Activities associated with pipes to be abandoned in place are subsidiary to Removal of Culvert Pipe and will not be measured for payment.

SECTION 203

#### EXCAVATION AND EMBANKMENT

Special Provisions

203-2.05 BORROW. Add the following: Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.

Add the following subsection:

203-2.07 TRENCH BLASTING.  Drill, load, and shoot a series of line holes along the pipe trench.  This is to be used in areas where normal excavation equipment and effort cannot accomplish the excavation.  “Normal excavation equipment and effort” is defined as that level of power and effort as is attainable from a 235 Caterpillar Backhoe or equivalent.

This work shall only be performed where directed by the Engineer.

Prior to drilling, furnish a blast plan to the Engineer showing pattern and depth of drill holes, type and amount of explosives used, loading pattern and sequence of firing.  All dynamite handling shall be performed by a properly insured, certified, and licensed person as required by State statutes.

Coordinate with the utility companies prior to blasting to shutdown utilities during blasting.

203-3.01 GENERAL CONSTRUCTION REQUIREMENTS.   Add the following:

Finishing and Protection of Subgrade.  Some of the native subgrade soils are sensitive to moisture and disturbance.  After the subgrade elevations have been reached, the Contractor shall conduct his operations to minimize the potential for “pumping” the subgrade soils.   Do not unnecessarily load the subgrade soils until the specified pavement structure materials are placed.  Surface and subsurface water shall also be controlled to prevent entry into the excavation and percolation into the subgrade.  All “pumping “ subgrade soils resulting from negligent construction operations shall be excavated and replaced with soils compacted to the requirements of Subsection 203-3.03 at the Contractor’s expense. 		(ANH 02/08/02)

After the subgrade has been substantially completed, the full width shall be conditioned by removing any soft or other unstable material.  Except where sensitive soils are present, the resulting areas and all other low areas, holes or depressions shall be brought to grade with  material compacted to the requirements of subsection 203-3.03 or 3.04 as appropriate.   Except where sensitive soils are present, scarifying, blading, rolling and other methods shall be performed to provide a thoroughly compacted subgrade shaped to the lines and grades shown on the plans.  (CM/ANH, 02/08/02)

No subbase, or surface course shall be placed on the subgrade until the subgrade has been approved by the Engineer.

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

On page 88, in the third paragraph, replace the first sentence with the following: When the excavated material consists predominantly of rock fragments or boulders too large to be placed in 200 mm layers, the Engineer may permit a maximum rock size of 450 mm to be placed in the embankment in layers not exceeding 600 mm.

Standard Modifications

203-3.02 EMBANKMENT CONSTRUCTION. In the 12th paragraph, first sentence, delete the words “from excavation”.

In the 12th paragraph, third sentence, insert the words “from excavation” after “wasted rock”.

(02/08/01) M 92

Special Provisions

203-3.02 EMBANKMENT CONSTRUCTION. Add the following: Where the plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work. (3/14/02)R23M98

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5.

(03/14/02)R193M98

203-3.04 COMPACTION OF EMBANKMENTS NOT CONSTRUCTED WITH MOISTURE AND DENSITY CONTROL. Delete this subsection and replace with the following: Except in rock fills and the first layer of fills over swampy ground or other sensitive soils, deposit embankment materials in layers not exceeding 200 mm in thickness before compaction.	(ANH, 02/08/02)

Delete the second and third paragraphs and substitute the following:  In areas of subgrade excavation without sensitive soils the subgrade shall be compacted with a vibratory roller having a minimum static weight of 10,900 kg until the roller drum rebounds back off the subgrade.  Do not cover any lift by another lift until compaction has been completed. (CM/ANH, 02)

203-4.01 METHOD OF MEASUREMENT. Add the following:  Item 203(11), Trench Blasting will be measured by the meter along the centerline of the trench.

203-5.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

203(11)	Trench Blasting	Meter

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

### Special Provisions

204-1.01 DESCRIPTION.  Add the following to the first paragraph: This work also includes excavating, shoring as required, dewatering as required, backfilling, compacting, final trimming, disposing of excess and unusable materials as required, and other earthwork incidentals for the construction of water lines, sanitary sewers, and all water and sanitary sewer appurtenances.

204-2.01 MATERIALS.  In the first paragraph, replace Selected Material, Type A, with Subbase, Grading B, except as noted otherwise.

Add the following paragraph after the first paragraph: The requirements of the previous paragraph shall apply to water lines, sanitary sewer lines, sanitary sewer vaults, and electrical conduits except as noted below.  The following shall be bedded and backfilled to 150 mm above the pipe or conduit in import material:

- 25 mm copper water lines.

- 50 mm and 75 mm HDPE sanitary pressure sewers.

- DIP water lines at sanitary sewer and storm drain crossings.

- Sanitary sewer vault electrical conduits.

- 50 mm HDPE lighting conduit

Import bedding material and import backfill material to 150 mm above the pipe or conduit shall meet the requirements for Subbase, Grading B, as specified in Subsection 703-2.09.  50mm HDPE (Scada system) conduit not under the proposed pathway shall be bedded in Aggregate Base Course, Type D-1.

    - CONSTRUCTION REQUIREMENTS.  Add the following : Water and sanitary sewer pipe and structure trenches shall be dewatered as necessary so that no standing water is present in the trench during pipe laying or structure installation operations.

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1. (10/1/91)R116

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

# CONSTRUCTION REQUIREMENTS

401-2.01 Composition Of Mixture - Job Mix Design.  Add the following to the first paragraph after ATM T-17: (version 01/93).

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

Table 401-1 Asphalt Concrete Mix Design Requirements,  In the Table under Voids In the Mineral Aggregate, delete Type II and replace with: Type II and Type IV.

401-2.02 AGGREGATES.  Change the first sentence to read:   Screen aggregates into a minimum of three crushed stockpiles (course, intermediate, and fine).  Stockpile blend sand (if required) in a separate pile.

401-2.03 ASPHALT Materials.  Change the last sentence of the first paragraph to read:  When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following:  Asphalt cement may be conditionally accepted at the source. Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during loading for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

3.	Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

401-307 PREPARATION OF EXISTING SURFACE.  Add the following to the end of the second paragraph:  A light tack coat shall also be applied over the first layer of a two layer pavement system. (CM, 01/29.02)

401-3.09  Preparation Of Aggregates.  In the first paragraph, delete AASHTO T-110 and substitute the following: WAQTC TM 6.

401-3.12 PLACING AND SPREADING.  Add the following: Place the asphalt concrete mixture in lifts no greater than 75 mm.  (ANH, 02/11/02)

Add the following at the end of this sub-section:  The paving speed shall be paced to match the delivery rate of asphalt concrete to the site.  Sufficient trucks shall be used to maintain a uniform paving rate without excessive delays between trucks.  In no case shall the paver hopper be emptied between trucks.	(CM, 01/29/02)

401-3.13 COMPACTION.  Add the following after the first paragraph:  Joints shall be compacted from the “hot” mat side with approximately 150 mm overlap onto the “cold” mat.  Subsequent compaction shall then begin from the low side and proceed back towards the joint.

Sufficient rollers shall be furnished to handle the output of the plant.  Rolling shall continue until all roller marks are eliminated, the surface is of uniform texture and true to grade and cross section, and the required field density is obtained.

To prevent adhesion of the mixture to the roller, the wheels/drums shall be kept properly moistened, but excessive water will not be permitted.  In areas not accessible to the roller, the mixture shall be thoroughly compacted with hot hand tampers or vibratory plate compactors.  Do not leave rollers or other equipment standing on pavement that has not cooled sufficiently to prevent indentation.

(CM, 01/29/02)

    - Joints. Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.

Cut one core, 150 mm minimum diameter, centered on the longitudinal joint at each location where the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.

Delete the last paragraph and substitute the following, Cut back all mat edges of the top asphalt layer that were not confined during placing and compaction before placing the adjacent asphalt concrete mat that will complete a joint.  Cut back the mat 150mm from the unconfined edge.  Cut a neat vertical edge, consistently true in longitudinal alignment.  Remove the loose, cut portion of the joint, sweep all loose material with a power broom, and then apply a tack coat prior to constructing the adjacent mat of asphalt concrete.  No pay quantity deduction will be made for material removed during joint construction.

If the average of all the project joint densities is less than 91.0% of the MSG, the Contractor shall seal all the joints on the project with a sealer system approved by the Engineer, at no expense of money or time to the State prior to paint striping.

401-3.15 SURFACE TOLERANCE. Delete this subsection in its entirety.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01  Method Of Measurement.  Under Asphalt Cement, 1., add to the end of the second sentence: “... ,or WAQTC FOP for AASHTO TP 53.”

Add the following paragraph to this subsection: Longitudinal joints.  By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

401-4.02 Acceptance Sampling And Testing.  Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken from the windrow, at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC  TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined in accordance with  WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined in accordance with  WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One minimum diameter 150 mm core is required for acceptance density testing only.  Acceptance density testing will be in accordance with WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

At the end of the subsection, Delete “PAB = Price Adjustment Base = $33.00/Mg”, Substitute, “PAB = Price Adjustment Base = $55.00/Mg”

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph, No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following: No payment will be made for placement or removal of Temporary Pavement.

Evaluate the project average density as defined in Subsection 401-3.14, Joints, in the following manner:

- If less than 91.0% of the MSG,

- The Contractor shall repair all of the asphalt joints on the project at
his expense with an approved asphalt joint sealing method as per
401-3.14, Joints.

- A disincentive = $3.28 / lineal meter of paved joint for the entire
project x (Project Average Joint Density – 91.0) shall be assessed as
a price adjustment and applied in 401(6) Asphalt Price Adjustment.

- If greater than 91.0% of the MSG,

- An incentive  = $0.82 / lineal meter of paved joint for the entire project x (Project Average Joint Density – 91.0) will be paid as an incentive and applied in 401(6) Asphalt Price Adjustment.

(11/29/01)R199M98

Except for Subbase, Grading B, no separate payment will be made for the pothole and centerline joint repair shown on Typical Section V, or base course excavation placed on shoulders, these items of work will be subsidiary to the asphalt pay items.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

401(1B)	Asphalt Concrete, Type II; Class B	Megagram

401(1D)	Asphalt Concrete, Type III; Class B	Megagram

401(1F)	Asphalt Concrete, Type IV; Class B	Megagram

#### SECTION 603

CULVERTS AND STORM DRAINS

Special Provisions

603-1.01  DESCRIPTION.  Add the following:  This work shall also consist of installing culvert marker posts, and utility conduits.

603-2.01 MATERIALS.  Add the following to the second paragraph: New pipe being installed in existing manholes shall have the same outside diameter as the pipe being replaced, except as noted otherwise.

Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts.  The color shall be blue with no other markings.  The 65 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm.

Standard Modifications

603-2.01 MATERIALS. In the second paragraph, delete “(900 mm maximum diameter)”.

603-3.03 JOINING PIPE.

2.	Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.”

(02/08/01)M 95

Special Provisions

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 750 mm and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. 1070 mm of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

(5/31/96)R42M

#### SECTION 604

#### MANHOLES AND INLETS

Special Provisions

604-2.01 MATERIALS.  Add the following: Scupper Drain shall be Neenah model R-4006 or equivalent.

604-3.01 CONSTRUCTION REQUIREMENTS. Add the following :  For the purposes of these specifications, “Sewer Utility” shall mean City of Unalaska, Department of Public Works & Department of Public Utilities at (907) 581-1260.

It shall be the Contractor’s responsibility to protect and maintain all sewer manholes and sewer cleanouts in an operable condition during all phases of construction. In conjunction with working around and /or adjusting the sewer manholes or cleanouts the Contractor shall exercise due care. Prior to commencement of work by the Contractor, the Sewer Utility shall check and correct deficiencies, which may exist in any sewer manholes or sewer cleanouts. The Engineer, Contractor and Sewer Utility representatives shall witness the condition and location of each sewer manhole and sewer cleanout.  Failure to participate in this inspection shall result in the contractor forfeiting all right to claim that the Sewer Utility facilities were damaged prior to his beginning work.

Notice that the Contractor is ready for the above walk through inspection shall be given to the Sewer Utility in writing a minimum of two (2) calendar days prior to starting construction.  The Contractor shall furnish a copy of the written notice to the Engineer.

It shall be the Contractor’s responsibility to protect and maintain all sewer manholes and sewer cleanouts in an operable condition during all phases of construction. If at any time after the inspection as outlined above, and before final acceptance, the Sewer Utility finds a sewer manhole or sewer cleanout inoperable by the Contractor, the Contractor shall repair the damage at his expense.

The Contractor shall be responsible for the furnishing of traffic control and personal to assist the Sewer Utility while locating and performing the pre-construction and post construction inspections. The Contractor shall schedule a final field review with the Sewer Utility and the Engineer upon completion of the sewer and sewer cleanout adjustments.

Add the following after the third sentence: Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway shall have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 25 mm of concrete or asphalt, as applicable.

On page 260, in the third full paragraph referencing adjusting existing manholes and inlets, insert the word:  cleanout, after the word:  manhole.

On page 260, third from the bottom paragraph, add the following:  Items not reused shall be salvaged and delivered to the City Maintenance Yard.

Add the following: When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the plans and 50 mm larger than the outside diameter of the new pipe. Then, grout joint with non-shrinking cement mortar.

All new curb inlet structures shall have a 75 mm formed hole approximately 0.6 m below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation. Keep the openings functional. This may require temporary dikes, RMC extensions, etc., as necessary. Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install them before concrete hardens.

Reference in this subsection to reconstructing or adjusting manholes or inlets shall also apply to catch basins.

604-4.01 METHOD OF MEASUREMENT. Add the following: Frames, grates and lids will not be measured for payment.

604-5.01 BASIS OF PAYMENT. Add the following: Frames, grates and lids are subsidiary to the drainage structure.    Elbow, geotextile, porous backfill material and pipe extension shown on the scupper drain detail are subsidiary to Item 604(22), Scupper Drain.

Adjustment of cleanout frames and covers shall be paid for under 604(4), Adjust Existing Manholes.

Delete Item 604(1) Storm Sewer Manhole, and add the following pay items:

Pay Item No.	Pay Item	Pay Unit

604(1A)	Storm Drain Manhole, Type I	Each

604(1B)	Storm Drain Manhole, Type II	Each

604(13C) 	Reconstruct Existing Inlet	Each

604(22)	Scupper Drain	Each

(9/1/00)R43M98

SECTION 605

UNDERDRAINS

Special Provisions

605-2.01 MATERIALS.  Add the following:  Pea Gravel material shall meet the following gradation requirements:

| SIEVE, mm | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 9.5 | 100 |
| 4.75 | 0-5 |

605-3.01 PIPE INSTALLATION.  First paragraph, delete the last sentence.

Third paragraph, delete the first sentence and substitute the following: For perforated pipe less than 300 mm in diameter, place perforated pipe with the perforations down. For perforated pipe greater than or equal to 300 mm in diameter, place perforated pipe with the perforations up.

Delete the fourth paragraph and substitute the following: “After pipe installation has been inspected and approved, place and compact backfill with the materials and to the dimensions shown on the plans.

605-3.02 UNDERDRAIN OUTLETS. Delete the paragraph and substitute the following: “Connect underdrain outlets to existing or proposed drainage structures as shown on the plans.

605-5.01 BASIS OF PAYMENT.  Add the following:  Pea Gravel  will not be paid for directly, but will be subsidiary to Item 605(6-150), 150mm Perforated Corrugated Polyethylene Pipe for Underdrain, unless noted otherwise on the plans.

SECTION 606

GUARDRAIL

Special Provisions

606-1.01 DESCRIPTION.  Add the following:  This work also consists of reconstructing individual guardrail items.

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers. Use flexible markers with an over all length of 1,800 mm. The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag that provides approximately 129 cm2 of surface area. Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

| Model FF2 | Nordic Fiberglass, Inc. P.O. Box 27 Highway 75 South Warren, MN 56762 | (218) 745-5095 phone (218) 745-4990 fax www.nordicfiberglass.com |
| --- | --- | --- |

If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following: Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 15 meters of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

Add the following subsections:

606-3.09 FLEXIBLE MARKERS. For each extruder terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer. The flexible markers shall have a minimum of 530 millimeters of marker extending above the top of the guardrail. The reflective tape shall face the nearest oncoming traffic.

606-3.10 LENGTH OF NEED VERIFICATION. After shaping the slopes and staking all proposed guardrail locations, the Contractor shall notify the Engineer to field verify the beginning and ends. The Engineer will approve the staked location of the guardrail before installation. The Engineer may determine that additional guardrail is necessary, and the Contractor shall comply without delay.

(10/01/01)R45aM98

606-3.11 RECONSTRUCTING GUARDRAIL. Existing guardrail will be inspected, and as determined by the Engineer, damaged items shall be replaced with new as directed.  All removed items become the property of the Contractor and shall be disposed off the project.

Existing BCT End Terminal cables determined loose, shall be unbolted and tensioned, as directed by the Engineer.

606-4.01 METHOD OF MEASUREMENT.  Add the following: Item 606(23), Reconstructing Guardrail, will be measured by the number of units of each item shown in the Guardrail Rate Schedule, that are replaced, accepted and in place.

606-5.01 BASIS OF PAYMENT.  Add the following: Payment for Item 606(23), Reconstructing Guardrail, will be made for the pay unit of accepted item replaced times the unit rate value contained in the Guardrail Rate Schedule below:

#### GUARDRAIL RATE SCHEDULE

| Guardrail Item | Pay Unit | Unit Rate |
| --- | --- | --- |
| Steel Posts | Each | $ 200.00 |
| W-Beam Rail Segment | Each | $ 400.00 |
| Standard W-Beam End Section | Each | $ 100.00 |
| Tension BCT End Terminal Cables | Each | $ 100.00 |

The bid schedule will reflect a contingent sum amount to provide adequate guardrail reconstruction for the project.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

606(23)	Reconstructing Guardrail	Contingent Sum

SECTION 608

SIDEWALKS

Special Provisions

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

- 2.	Asphalt Sidewalk and Asphalt Pathway:  As specified for Asphalt Concrete, Type IV, Class B.

608-3.03 SIDEWALK RAMPS. Delete this subsection and substitute the following:

608-3.03 CURB RAMPS. Construct curb ramps according to the details and locations shown on the Plans.  Install composite detectable warning tiles such as Armor Tile Cast-In-Place In-Line Tactile Panels, manufactured by Engineered Plastics, Inc., or approved tactile warning bumps as shown in the details on the drawings.  (06/11/02, ANH)

Follow the construction requirements of Subsection 608-3.01.  Give the surface a coarse broom finish. (05/14/01)R256M98

608-4.01 METHOD OF MEASUREMENT. Delete the fourth item “Sidewalk Ramp” and substitute the following:

Curb Ramp. By each installation, complete in place, including ramp runs, flares, backing curb and landing necessary to provide a single street-level access. (05/14/01)R256M98

Standard Modification

608-4.01 METHOD OF MEASUREMENT.  In both the first and second paragraphs, after “finished surface” insert “, including ramps”.

(06/25/99) M 74

Special Provisions

608-4.01 METHOD OF MEASUREMENT. Add the following:  Asphalt cement for Asphalt Sidewalks, will not be measured for payment.

Additional asphalt pavement used for matching existing surfaces such as paved parking lots behind a new sidewalk/pathway will be measured and paid under this Section.

608-5.01 BASIS OF PAYMENT.  Add the following: Asphalt cement for Asphalt Sidewalk will not be paid for separately, but will be subsidiary to the pay item.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.  (2/1/00) R47M98

Concrete, tactile warning bumps, and backing curb will be subsidiary to Item 608(6), Curb Ramp. (06/11/02, ANH)

Delete Item 608(6), Sidewalk Ramp, and substitute the following pay item:

Pay Item No.	Pay Item	Pay Unit

608(6)	Curb Ramp	Each

(05/14/01)R256M98

#### SECTION 609

#### CURBING

#### Special Provisions

609-3.02 CAST-IN-PLACE CONCRETE CURBING. Add the following to the fifth paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than 50 mm.  (2/1/00)R202M98

609-3.05 CURB RAMPS. Delete this Subsection in its entirety.

Standard Modifications

609-4.01 METHOD OF MEASUREMENT.  In the first paragraph, after “drainage structures” insert “or ramps”.  (06/25/99) M 75

Special Provisions

609-4.01 METHOD OF MEASUREMENT.  Delete the second paragraph.

Add the following: Valley gutter will be measured along the flow line as shown on the detail drawing. The associated concrete apron will not be measured for payment.

609-5.01 BASIS OF PAYMENT. Add the following: Concrete valley gutter apron will not be paid for separately, but will be considered subsidiary to Item 609(2), Curb and Gutter, Type 1.

Delete Pay Item 609(3), Curb Ramp.  (05/14/01)R256M98

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

- Notify the Engineer five (5) days prior to beginning sign salvage activities. At that time, the Engineer will physically identify those signs to be salvaged.  For each sign so designated, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner. Deliver sign panels, posts and hardware to the local State Maintenance Yard.  Do not deliver salvaged materials until they have been inspected and approved by the Engineer.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing signs and sign post foundations, or work required to abandon the signpost foundations in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(05/16/01)R50M98

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION. Delete this subsection and substitute the following: All new or disturbed areas shown on the Plans and any other areas identified by the Engineer within the project limits shall be seeded. Track the soil and apply seed, mulch, fertilizer and water. As soon as possible provide a living ground cover on all slopes.

This work shall consist of ground preparation, hydraulic application or hand broadcasting of the seed, finishing work including raking seed into the soil, fertilizing and limestone application in conformance with the Plans and Specifications.

Standard Modifications

618-2.01 MATERIALS. Delete this subsection and substitute the following: Use materials that conform to the Special Provisions and the following:

Seed 	Section 724

Fertilizer (20-20-10)	Section 725

(02/08/01) M99

Special Provisions

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

Standard Modifications

Replace subsection 618-3.01 with the following:

618-3.01 SOIL PREPARATION. Clear all areas to be seeded of stones 100 mm in diameter and larger and of all weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the seeding operation, growth of grass, or subsequent maintenance of the grass-covered areas.

Make areas to be seeded reasonably free of ruts, holes, and humps.

Roughen the surface slightly by means of dozer-tracking or other approved method.

(02/08/01) M99

Special Provisions

618-3.01 SOIL PREPARATION. Add the following: Seed shall be applied immediately after the ground has been prepared and approved by the Engineer. Protect prepared base from damage and prevent erosion if seeding season limitations prohibit application of seed.

618-3.02 SEEDING SEASONS.  Add the following: Application of seed shall be performed between May 15 and August 15.

Standard Modifications

618-3.03 APPLICATION. Replace Items 1 and 2 with the following:

Use any of the following methods:

1.	Hydraulic Method.

a.	Furnish and place a slurry made of seed, fertilizer, water, and other components as required by the Special Provisions.

b.	Use hydraulic seeding equipment that will maintain a continuous agitation and apply a homogeneous mixture through a spray nozzle. The pump must produce enough pressure to maintain a continuous, nonfluctuating spray that will reach the extremities of the seeding area with the pump unit located on the roadbed. Provide enough hose to reach areas not practical to seed from the nozzle unit situated on the roadbed.

c.	If mulch material is required, it may be added to the water slurry in the hydraulic seeder after adding the proportionate amounts of seed and fertilizer. Add seed to the slurry mixture no more than 30 minutes before application.

d.	Mix the slurry and apply it evenly.

2.	Dry Methods.

a.	Use mechanical spreaders, seed drills, landscape seeders, aircraft, cultipacker seeders, fertilizer spreaders, or other approved mechanical spreading equipment when seed and fertilizer are to be applied in dry form.

- Spread fertilizer separately at the specified rate.

(02/08/01) M99

Special Provisions

618-3.03 APPLICATION METHOD. Add the following: Apply seed, mulch and fertilizer as follows per hectare (ha). Apply seed and mulch in one application if using the hydraulic method. Apply all fertilizer with the hydraulic method.

| Item | Ingredients | Application Rate (per ha) |
| --- | --- | --- |
| Seed Mix | Alpine Kentucky Bluegrass Red Fescue Nortran Tufted Hairgrass Bering Hairgrass Annual Ryegrass | 12 kg 12 kg 12 kg 9.6 kg 2.4 kg 48 kg |
| Mulch | See below: |  |
| <3:1 |  | 2241 kg |
| >3:1 to 2:1 | add tackifier | 2805 kg |
| Fertilizer | low-release 20-20-10 | 585 kg |

Each species of seed shall be supplied separately and not as mixtures.  Mark each container with the weight and with the manufacturer’s guaranteed analysis of the contents showing the percentage for each ingredient contained therein.

Standard Modifications

Replace subsection 618-3.04 with the following:

618-3.04 Plant Establishment AND MAINTENANCE. Protect seeded areas against traffic and erosion.

Promptly repair surfaces that are gullied or otherwise damaged following seeding by regrading, reseeding, and remulching as needed.

Water and maintain seeded areas in a satisfactory condition until final inspection and acceptance of the work. Use equipment that can water all seeded areas without damaging the seed bed.

Reseed any areas not showing evidence of satisfactory growth within 3 weeks of seeding. (02/08/01) M99

Special Provisions

618-3.04 Plant Establishment AND MAINTENANCE  Add the following to the third paragraph: Water seeded areas as required for proper germination and growth.

Add the following:

Fertilizing.  Fertilizer shall be reapplied once between May 15 and June 15 at a rate of one-half the initial application to all areas during the maintenance period.

- Watering during establishment.  Contractor shall ensure that the seeded areas stay moist during germination and seedling establishment (as defined by the grass plants

- attaining a height of approximately 75mm).  The Contractor shall be prepared to water the seeded areas 3 times a day if weather conditions warrant it, until seedlings have become established.

- If the Contractor fails to apply adequate moisture during the germination period for 4 consecutive days, or after 2 notices without immediate response, the Engineer may declare all affected seeding unacceptable.  The Contractor will be required to reseed areas that have not been kept moist.

Maintenance period. The maintenance period shall be one full growing season following acceptance. One full growing season shall be defined as the period between May 1 and September 30 for the purpose of this Contract. Partial growing seasons will not be counted against the one full growing season requirement.

Upon request by the Engineer, the Contractor shall repair any damaged areas during the maintenance period.

Add the following:

    - FERTILIZER. Fertilizer shall be delivered in moisture-proof containers marked with weight and manufacturer’s guaranteed analysis showing proportions of the chemical ingredients of nitrogen, phosphoric acid, and potassium within a tolerance of +/- 2 percent. A slow release fertilizer 5-3-1 (N-P-K) shall be used for all seeding applications.  Fertilizer shall be applied at a rate determined by the Engineer, as described in Section 618-3.03, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.

618-4.01 METHOD OF MEASUREMENT.  Replace the second paragraph with the following: Seeding shall be measured by the kilogram. Measurement by the kilogram shall be the number of kilograms of seed Dry Measure accepted in place. Water shall be measured by the Kiloliter.

The amount of mulch, tackifier, and fertilizer in this work, including any required reseeding, will be subsidiary to seeding and shall not be measured separately for payment.

The work described under subsection 618-3.01 Soil Preparation shall not be measured but will be subsidiary to seeding.

Delete the last paragraph.

618-5.01 BASIS OF PAYMENT. Add the following: Partial payments shall be made at 40% upon seeding, 30% at the end of the first growing season in which seeding is done (first season’s maintenance) and 30% upon final acceptance.

The amounts of mulch, fertilizer, and water for application used in this work, including any required reseeding, are subsidiary to seeding.

Maintenance for seeded areas shall be subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(8/28/01)R52M98

SECTION 626

SANITARY SEWER SYSTEM

### Special Provisions

626-1.01 DESCRIPTION. Add the following: This work also includes the installation of new sewer services, adjustment of existing sewer services, and abandonment and installation of replacement sewer services.

For purposes of these specifications, “Sewer Utility” shall mean City of Unalaska, Department of Public Works & Department of Public Utilities at (907) 581-1260.

The Contractor shall also provide as-builts in accordance with the conditions prescribed herein.

626-2.01  MATERIALS.  Delete the first sentence and replace with the following: Use materials that conform to the following subsections, except where shown otherwise on the service detail drawings.

626-3.01 CONSTRUCTION REQUIREMENTS.  Add the following: Use the same diameter as the existing service when replacement is necessary, or the diameter as directed by the Engineer.

Remove all exposed portions of services to be abandoned and cap the end of the service nearest the main.

Give at least 24 hours’ notice to the Owning utility and impacted residentsbefore interrupting sewer service to any area.  Restore disrupted sewer service as soon as possible, or make temporary service connections.  Use hoses or other suitable methods.

If your operations cause service interruptions, you are responsible for all damages.

Add the following subsection:

626-3.03 AS-BUILT DRAWINGS.  The Contractor shall complete and accurately record all deviations, deletions, additions, and alterations, to correctly depict sanitary sewer lines and appurtenances, and existing utilities, as actually installed, on a clean set of blueline plans dedicated solely to keeping of this as-built information.  When sanitary sewer construction is complete, the Contractor shall certify the accuracy of the sanitary sewer as-builts in writing, and deliver them to the Engineer.

626-4.01 METHOD OF MEASUREMENT.  Add the following:  As-builts will not be measured for payment.

Item 626(2) Sewer Service, will be measured for each service completed and accepted.

626-5.01 BASIS OF PAYMENT.  In the third paragraph, delete the words “and service fittings”.

Add the following:  As-builts will not be paid for directly, but will be sudsidiary to Item 626(2), Sewer Service.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

626(2)	Sewer Service	Each

SECTION 627

WATER SYSTEM

### Special Provisions

627-1.01 DESCRIPTION.  Add the following: For purposes of these specifications, “Water Utility” shall mean City of Unalaska, Department of Public Works & Department of Public Utilities at (907) 581-1260.

The Contractor shall also provide as-builts in accordance with the conditions prescribed herein.

In conjunction with working around and/or adjusting the Water Utility water valves, the Contractor shall exercise due care.  Prior to commencement of work by the Contractor, the Water Utility shall check and correct deficiencies which may exist in any valve or valve box. The Engineer and Contractor shall witness the condition and location of each valve or valve box. Failure to participate in the inspection by the Contractor will result in his forfeiting all rights to deny damages at a later date during the course of the work. Notice that the Contractor is ready for the above inspection shall be in writing to the Water Utility and shall be submitted giving at least 48 hours notice. The Contractor shall furnish a copy of the notice to the Engineer.

It shall be the Contractor’s responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction. If at any time after the inspection as outlined above, and before final acceptance, the Water Utility finds a valve or valve box inoperable, the Contractor shall repair it at his own expense.

Item 627(8), Water Service, when used, shall apply to all water services, including fire services.

627-2.01 MATERIALS.  Delete the first sentence and replace with the following: Use materials that conform to the following subsections, except where shown otherwise on the service detail drawings.

Materials for water service connections, shall match existing pipe materials.

627-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following: Work includes adjustment of existing services and abandonment and installation of replacement services as necessary to resolve conflicts.  This work also includes installation of new services as shown on the drawings or as directed by the Engineer.

Use the same diameter as the existing service when replacement is necessary, or install the diameter as directed by the Engineer.

Abandoned water services shall be turned off at the corp stop and any exposed service pipe shall be removed.

627-3.05 VALVE BOXES. Add the following : It shall be the Contractor’s responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction.  In conjunction with working around and/or adjusting the Water Utility water valves, the Contractor shall exercise due care.  Prior to commencement of work by the Contractor, the Water Utility shall check and correct deficiencies, which may exist in any valve or valve box. The Engineer, Contractor and Water Utility representatives shall witness the condition and location of each valve or valve box. Failure to participate in the inspection by the Contractor will result in his forfeiting all rights to deny damages at a later date during the course of the work. Notice that the Contractor is ready for the above walk through inspection shall be in writing to the Water Utility and shall be submitted giving at least two (2) Calendar days notice. The Contractor shall furnish a copy of the notice to the Engineer.

It shall be the Contractor’s responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction. If at any time after the inspection as outlined above, and before final acceptance, the Water Utility finds a valve or valve box damaged or rendered inoperable by the Contractor, the Contractor shall repair it at his own expense.

The Contractor shall be responsible for the furnishing of traffic and personal to assist the Water Utility while locating and performing the pre-construction and post construction inspections. The Contractor shall schedule a final field review with the Water Utility and the Engineer upon completion of the valve box adjustments.

Add the following subsection:

627-3.08 AS-BUILT DRAWINGS.  A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed. This as-built information shall be recorded on a print of the plans affected and on the applicable pages of the specifications with supplementary notes. This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed. Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When the water system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance of the system by the Water Utility.

Final as-built drawings shall be submitted in electronic “AutoCad 2000” format and shall also include two “hard” copies printed on 24” X 36” paper, minimum 50 scale. They shall be submitted within 60 days of the notice of substantial completion.  These drawings shall include swing ties (two each) to all valves, tees, fittings, and buried appurtenances (ARV’s, Blow-offs, etc.).  All pipe lengths shall be shown on the drawing.  If stationing is used in lieu of pipe lengths, then the stationing shall be of the actual in place pipe and not of ROW centerline.  Only clean drawings will be permitted.  No marked up design drawings will be accepted.

627-4.01 METHOD OF MEASUREMENT.  Delete Item 4., Water Service Connection, and replace with the following:

4.	Water Service. By the number of water services and fire services installed, including installation of a gate valve with service box, all fittings and materials required, thrust blocks, curb stop, valve box, service pipe and connection to a new or existing water main with a service saddle, tapped coupling or corporation stop, other items as referenced in the Relocate Fire Service or Water Service details, and as shown on the plans.

Add the following:  As-builts will not be measured for payment.  Multiple adjustments required for items in 627(10) Adjustment of Valve Box will be paid for as a single adjustment.

627-5.01 BASIS OF PAYMENT.  Add the following to the third paragraph:  Corp stops, key boxes, thaw wires, and other items shown on the details are subsidiary to Water Service.

Add the following:  As-builts will not be paid for directly, but will be subsidiary to Item 627(8), Water Service.

Delete pay item 627(8), Water Service Connection, and substitute the following pay item:

Pay Item No.	Pay Item	Pay Unit

627(8)	Water Service	Each

SECTION 635

INSULATION BOARD

### Special Provisions

635-2.01 MATERIALS.

Insulation Boards.  Add the following sentences:  Insulation for freeze protection of existing and new water lines and sanitary sewers shall meet the following criteria.  Individual board thickness shall be 50.8 mm.  R-value shall be 0.0315 K-sq. m/W-mm minimum per ASTM C177/C518.  Compressive strength shall be 414-kPa minimum per ASTM D1621.  Water absorption shall be 0.10% by volume per ASTM C272.  Submit manufacturer’s literature for insulation board for the Engineer’s review and approval.

Delete “Sand Blanket.  Subsection 703-2.12.”, Add, “Aggregate Base Course, Type D-1. Subsection 703-2.03”.

635-3.01 CONSTRUCTION REQUIREMENTS. Delete the last sentence of the first paragraph and substitute “Place a Aggregate Base Course, Type D-1 leveling course at least 50mm thick.”

Add the following paragraphs after the second paragraph: If no insulation is shown on the drawings, but the separation between the drainage facilities and existing water and sewer facilities is less than the following, then provide 50mm of insulation between them.

Water	0.6m
Pressure or Gravity Sewer	0.45m

Third paragraph, delete the words, “sand blanket material”, replace with, “Aggregate Base Course, Type D-1”.

635-4.01 METHOD OF MEASUREMENT.  Add the following after the first paragraph: For insulation installed for freeze protection of existing and new water and sanitary sewer facilities, by the square meter of 50 mm nominal thickness of insulation board in place.

Delete the sentence, “Sand blanket material is subsidiary.”, and replace with “Aggregate Base Course, Type D-1 material is subsidiary.”

635-5.01 BASIS OF PAYMENT.  Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

635(2)	Insulation Board	Square Meter

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01 DESCRIPTION. Add the following: This work also includes the construction of public approaches at locations shown on the plans.

639-2.01 METHOD OF MEASUREMENT. Add the following: By the number of public approaches constructed as shown on the Plans, or as directed.

Driveways and Public Approaches will be measured for payment only if work is performed outside of the back of curb or projected edge of pavement of Airport Beach Road.  (ANH, 04/23/02)

639-3.01 BASIS OF PAYMENT. Add the following: Materials required to construct approaches will be paid for separately under the respective items listed in the bid schedule.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

639(3)	Public Approach	Each

639(4)	Driveway	Each

(12/14/99)R58M98

# SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modification

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

# SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

Special Provisions

641-1.01 DESCRIPTION. This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

- ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and included in the project plans and specifications. It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS. Submit 3 copies each of your SWPPP and HMCP for approval no less than 5 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days. Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP. Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing 2 hectares or less. The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private. The plan must also incorporate all the requirements of the Project permits.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities. Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-3.01 CONSTRUCTION REQUIREMENTS.  Do not begin ground-disturbing work until you receive written approval of the SWPPP and HMCP.

Post at the construction site, the

1.	name and phone number of your local contact person, and

2.	location of a SWPPP available for viewing by the public.

Implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms. Perform all fueling operations in a safe and environmentally responsible manner. Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

- storm event or other circumstance that threatens water quality, and

2.	inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within 7 days.

Stabilize all areas disturbed after the seeding deadline within 7 calendar days of the temporary or permanent cessation of ground-disturbing activities.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

- pursue work required by the approved SWPPP,

- respond to inspection recommendations and/or deficiencies in the SWPPP, or,

- implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01 METHOD OF MEASUREMENT. Items 641(1) and 641(3) will not be measured for payment.

Items 641(2) and (4) will be measured as specified in the Contract or Directive authorizing the work.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1) and (2) or items 641(1), (3), and (4)

1.	Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract to install and maintain all temporary erosion, sedimentation, and pollution control measures.

3.	Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain temporary erosion, sedimentation, and pollution control measures in accordance with the original approved SWPPP and HMCP.

4.	Item 641(4) Temporary Erosion and Pollution Control Amendments. At the prices specified in the Directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures. All work paid under this Item shall be shown as amendments to the original approved SWPPP or HMCP.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution	Lump Sum

Control Administration

641(2)	Temporary Erosion and Pollution Control	Contingent Sum

641(3)	Temporary Erosion and Pollution Control	Lump Sum

641(4)	Temporary Erosion and Pollution	Contingent Sum

Control Amendments

(08/15/01)S81

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Standard Modification

642-3.01 GENERAL.  Delete the seventh paragraph.

(06/25/99)M 79

Special Provisions

Ninth paragraph, Add the following to the end of “2.”: “Cross section beginning and end of each Typical Section IV segment prior to pavement removal.  Cross section intermediate stations as required to define, superelevation, superelevation transition, and edge of pavement change.

Add the following to the end of this sub-section:  Place and maintain survey lathes labled with the station every 50 meters along the road alignment, 3 meters off the right edge of pavement.  Also mark the ground surface with a paint mark so replacement lathes can be easily set.  (ANH/CM, 05/13/02)

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work.

(3/31/00) R252M98

642-5.01 BASIS OF PAYMENT Add the following:  Lathes placed at 50 meter intervals shall be subsidiary to item 642(1), Construction Surveying.  (ANH, 05/13/02)

SECTION 643

#### TRAFFIC MAINTENANCE

Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6-meter lateral separation between the non-street legal vehicles and the motoring public. The Traffic Control plan shall specify the traffic control devices required for these operations.

The TCP requires monthly meetings to be attended by the Project Engineer and Contractor’s Project Superintendent.  (ANH, 02/11/02)

Special Provisions

643-2.01 MATERIALS.  Add the following:

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials. (01/29/02)R222M98

Standard Modifications

Add the following subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Category | ## Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site.  (http://www.fhwa.dot.gov/.)

Submit documentation of compliance to the Engineer before using devices on the project.

(09/29/00) M91

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following after the first sentence of the second paragraph: Provide temporary bridges as required to maintain continuous access to all residences, businesses, and public facilities.

Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Delete the last paragraph of and substitute the following: The Contractor shall maintain a 2.4 meter minimum width pedistrian route through the construction area.  The pedestrian route shall be located within the right-of-way, or area of a temporary construction permit.  The pedestrian route shall be separated from construction activity by a pedestrian fence.

Standard Modification

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.  (06/25/99)M 80

Special Provisions

Add the following:  Do not allow traffic queues to sit on bridges.

643-3.03 PUBLIC NOTICE.  Add the following:  Write and submit weekly notices that identify road closures, restrictions to traffic, and detours. Areas of potential traffic delay shall be emphasized and alternative routes noted.  Prepare and conduct monthly meetings with the public.  Public meeting announcements should be made in the prior week’s public notice.  Coordinate this effort with the Engineer.

Hand carry or fax the notices to the local news broadcasting media (including KO8IW, Channel 8), emergency services, public service organizations and the major retailers near the Project corridor.

643-3.04 TRAFFIC CONTROL DEVICES.  Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: Remove all obstructions greater than 100 mm above the nominal foreslope grade at the end of each continuous work shift

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

- Power Brooming.  The Contractor shall use a power broom capable of ejecting all loose material to the shoulder of the road.  The Contractor shall remove all loose material from all pave portions of the roadway and haul routes open to the public.  This includes sections of roadway off the project where the Contractor’s operations have deposited loose material.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. . Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer, do not restrict traffic during the times listed below.

Monday through Friday, 6:00 a.m. to 8:00 a.m. and 4:00 p.m. to 6:00 p.m.

Lane restrictions, if allowed shall be conducted so that no more than a 5 minute accumulated stopped delay, 20 vehicles, or 0.2 kilometers of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 10 minute stopped delay, 40 vehicles, or 0.4 kilometers of traffic detained, will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.  Traffic queue will not be allowed on bridges.

The Contractor shall obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  The Contractor shall make every effort not to delay school buses through the construction work zone.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

Add the following subsection:

643-3.11 PORTABLE TRAFFIC SIGNAL.  The Contractor shall submit the traffic control system that he intends to use for alternating one-way traffic control at the Preconstruction Conference.  The submittal shall include a TCP and the make of the signal equipment and operations manuals as well as any field wiring that may be needed to make the unit or units function as specified.  Traffic signals shall be capable to fully operate for 24 hours on emergency battery power. The Contractor shall also submit a contingency plan on how he intends to handle traffic if the equipment should malfunction.  The Department will not be liable for any material purchased, labor performed, equipment used or delay to the work before all materials and TCPs have been reviewed and approved.

Signals shall be installed and operated in accordance with the requirements of Part IV Signals of the Alaska Traffic Manual.  The traffic signals shall be 300-mm R-Y-G displays with backplates and visors.  Signal faces, detectors and control equipment shall be kept in good operating condition at all times.  The Engineer shall approve signal timing.

The minimum mounting height to the bottom of the signal shall be 3 meters above the roadway surface.  If the signal is suspended over the traveled portion of the roadway, the minimum height to the bottom of the signal shall be 5.3 meters with a maximum height of 5.8 meters above the roadway surface.

The horizontal and vertical alignment of the roadway may require adjustment in the location of the advance warning signs (the distances shown are minimums).  The vertical alignment of the roadway may require adjustments in the height of the signal heads.  Signs shall not block the visibility of the traffic signals.

Type C steady burn warning lights shall be installed on all drums, barricades and vertical panels during hours of darkness.

The traffic signal control equipment shall have the following minimum control capability:

- A fixed green interval adjustable from 0 to 60 seconds in 1-second increments.

- A 3-second, minimum, yellow change interval shall follow each green interval.

- An all-red clearance interval shall follow each yellow change interval.  The all-red clearance interval shall permit a vehicle to travel the length of the one-way lane before a green indication is shown to the opposing traffic.  The all-red interval shall be adjustable from 0 to 420 seconds in 1-second intervals.

- A means of operating in a semi-actuated mode.  A means of detection shall be furnished at each end of the alternating one-lane route to detect the presence of vehicles.

- A means of protecting against green-green; yellow-green; yellow-yellow conflicts.  If conflict is detected, the signals shall go into flashing mode of operation with flashing red signal displays at each end of the one-lane section.

- Cable or radio may interconnect one-way lane control that requires sets of signals to be coordinated, so that they are operated from a s single manual or automatic control.

The following control equipment shall be capable of functioning in each of the following modes:

- The traffic signals shall rest in red awaiting the arrival of a vehicle at either end of the one-lane section.  When the vehicle is detected, the signal shall change to green for the detected vehicle.  A minimum selectable green shall time out, followed by a 3-second minimum yellow change interval.  The yellow change interval shall be followed by a selectable all-red interval after which the signal system shall again resume its rest in red mode until the next vehicle is detected.

- The traffic signal upon termination of a selectable minimum green interval for up-hill traffic shall rest in green for up-hill traffic.  When a vehicle arrives at the other end of the one-lane section, the signal for up-hill traffic shall time the 3 second minimum yellow change interval followed by a selectable all-red clearance interval.  After completion of the all-red interval, a selectable minimum green interval shall be given to the downhill traffic.  The 3-second minimum yellow change interval and the selectable all-red clearance interval shall follow the green interval.  The unit will again time out the selectable up-hill green interval and rest in green awaiting the arrival of the next downhill vehicle.

- The traffic signal operates in a pre-timed mode where the signal times out a selectable green for up-hill traffic followed by a 3 second minimum yellow change interval followed by a selectable all-red clearance interval.  It will then time out a selectable green for the downhill traffic followed by a 3 second minimum yellow change interval followed by a selectable all-red clearance interval then repeat the same operation.

The contractor may work the signals manually during his normal working hours.

The contractor shall submit a detailed plan of how he will operate the units during this time for review and consideration by the Engineer.  No payment for the operator during manual operation of the units will be made.

643-4.01 METHOD OF MEASUREMENT. Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide monthly public notices.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

- Portable Traffic Signal.  By the lump sum.

643-5.01 BASIS OF PAYMENT. Add the following:  The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 CET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.  (01/29/02) R222M98

Payment for Item 643(29) Portable Traffic Signal will include all material and labor required to install and maintain the Portable Traffic Signal.

No separate payment will be made for detours.  All work necessary to construct, maintain, demolish, and dispose of detours will be subsidiary to Item 643(2), Traffic Maintenance.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

643(29)	Portable Traffic Signal 	Lump Sum

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE. Delete the third, fifth, and seventh sentences of the first paragraph and the second paragraph in this subsection and substitute the following: Meet the following office requirements:

1.	A minimum of 100 square meters of floor area. Divide the office area so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area. A minimum of 15 square meters of window area and adequate ventilation.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	A minimum of four electrical outlets.

4.	Adequate parking for a minimum of 15 vehicles, with one disability parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

5.	Provide attached indoor plumbing with sanitary lavatory facilities and potable drinking water.

6.	Three (3) telephone service lines available at the office location, with 1 dedicated internet service.

7.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

8.	Located on Amaknak Island, within 2 kilometers of the project.

- Provide one move in and one move out for state office furniture and equipment.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

Standard Modification

644-2.01 FIELD OFFICE.  In the third paragraph, change “the final inspection” to “project completion”. (06/25/99)M 81

Special Provisions

644-2.02 FIELD LABORATORY. Delete sub-item g on page 380 and substitute the following:

g.	1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

- Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

644-2.05 VEHICLES.  Delete first sentence in the first paragraph and substitute the following: Furnish and maintain four (4) full-size four-wheel drive pickup(s) or sport utility vehicle(s) for exclusive use of the Department throughout the project.

Add the following: Equip vehicles used by the Department with CB radios and  yellow rotating beacons wired into the vehicle’s system with a dash mounted switch easily accessible to the vehicle operator.

The Contractor is responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use. The Department is responsible for damage to any vehicle caused by its own negligence during operation. The Department will provide non-owned auto liability insurance providing third party liability coverage for any accident during the Department’s operation and use.

644-3.01 METHOD OF MEASUREMENT. Delete subparagraph “vehicles” and substitute the following:

Vehicle. Per each vehicle provided. If a replacement vehicle is necessary, no additional measurement for payment will be made. (01/28/02)R245M98

Standard Modifications

644-4.01 BASIS OF PAYMENT. In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators, “.  (06/25/99)M 81

Special Provisions

644-4.01 BASIS OF PAYMENT. Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

Delete subparagraph “vehicles” and substitute the following:

Vehicle. Per each vehicle provided. If a replacement vehicle is necessary, no additional measurement for payment will be made.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

644(8)	Vehicle				Each

(01/28/02) R245M98

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval. The CPM shall clearly address the interim completion provisions of 108-1.04.  The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.   60-Day Preliminary Schedule.

(3/12/01)R261M98

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

Special Provisions

647-1.01 DESCRIPTION. Furnish construction equipment, operated, fueled and maintained, on a rental basis.  This equipment is for use in construction of extra or unanticipated work, only at the direction of the Engineer. The definition of construction equipment is that equipment actually used for performing the items of work specified. The definition shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

Accomplish this work under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. The Department will not be liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. Furnish, operate, maintain, service and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. Use skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth must meet minimum requirements. Furnish the number of pieces of each equipment that the Engineer considers necessary for economical and expeditious performance of the work. Use only the equipment that the Engineer directs.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturers’ specifications. Do not alter equipment to achieve the minimum rating. Replace equipment when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Fully operate all equipment. This includes the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Use competent and experienced equipment operators capable of operating the equipment to its capacity. All personnel are employees solely of the Contractor.

Provide a job superintendent or Contractor’s representative together with such other needed personnel for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and material. Furnish without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. Perform work in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer. Commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. Record time to the nearest one-quarter hour for each item of equipment listed in the bid schedule, during which equipment is actively engaged in construction of the project. Also, record the serial number and brief description of each item of equipment listed in the bid schedule. Record each day's activity on a separate sheet or sheets. A Contractor’s representative shall verify the data and sign at the end of each shift. Provide a copy to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work, on the designated areas, in accordance with the instruction of the Engineer. The pay time will not include idle periods, or time spent oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. The Engineer will not authorize payment for travel time to or from the project.

647-5.01 BASIS OF PAYMENT. This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(2)	Wide Pad Dozer, 48 kW Minimum	Hour

(11/12/98)R15M98

Add the following Section:

SECTION 651

EAGLE MONITORING

Special Provisions

651-1.01 DESCRIPTION. This work shall consist of engaging a Professional Services Contractor to provide a monitor to observe eagle activity at nests in order to comply with this section and Section 107.

651-2.01 MATERIALS. A video camera with a minimum 10 power zoom lens shall be used to monitor and record nest activity.

651-3.01 GENERAL REQUIREMENTS. The monitor shall work directly for the contract manager of the professional services contract.  He shall be trained by the Professional Services Contract Manager or another qualified representative in the techniques of monitoring and observing eagles. The Professional Services Contract Manager will be responsible for preparing an eagle monitoring plan in conjunction with the Contractors work plan when it involves work within the restricted area or any timing restriction period.

The Professional Services Contract Manager shall meet one of the following criteria.

1. 	Have a bachelor of science degree in biology, environmental science or ecology and be presently working in that profession.

2. 	Have 2 years experience monitoring and observing eagles or other birds of prey or studying their habitat.

The on-site eagle monitor shall be an employee of the Professional Services Contract Manager and shall be at least 18 years of age and physically able to perform all aspects of work.

651-4.01 METHOD OF MEASUREMENT.  Item 651(1), Eagle Monitoring will be measured in the manner specified in the directive authorizing the work.

651-5.01 BASIS OF PAYMENT. Payment for Item 651(1), Eagle Monitoring will be full compensation to accomplish the work, as specified in the authorizing directive.  Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

651(1)	Eagle Monitoring	Contingent Sum

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS.  Delete item number 1 that follows the first paragraph, and add the following:  The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-1.05 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS. Delete this subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned in accordance with the following specifications.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When you begin work, the Engineer will notify you and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility. Therefore, before starting work on the project, you should inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with you. If you begin work before providing the Engineer with an inventory, you waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, and photoelectric controls operate the lighting systems. The State will pay for all electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin repair work on all systems within one hour of notification by the Engineer. If you do not complete the repairs, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due you. When you work on a traffic signal system, print a record of all work performed in the diary found in each controller cabinet. Make sure each entry includes:

1.	The dates and times you began and completed your work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to periods during normal working hours as specified in Section 643, Traffic Maintenance. During the shutdowns, use flag persons to control traffic. Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day you retire the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever you reduce their clearance from the traveled way to less than 1.8 meters.

During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches in accordance with the following:

1.	For overhead signals, maintain 5.3 m to 5.8 m of clearance between the traveled way and the bottom of each signal.

2.	For side mounted signals, maintain 2.7 m to 3.4 m of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	Check the horizontal angle to the side mounted far right signal from the center of the farthest left through lane at the stop bar. When the angle exceeds 20 degrees, move this signal to an overhead location. With two or more through lanes, center one signal head over each lane. With one through lane and protected-permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane, otherwise install the relocated signal 2.4 meters to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 2.1 m to 2.7 m between the traveled way and the bottom of each pedestrian signal.

7.	Aim all signal heads in accordance with subsection 660-3.08, Installation Details.

When no longer required, salvage all original and Department provided equipment in accordance with the plans and subsection 660-3.21, Salvaging or Reusing Electrical Equipment, and remove all other materials used in the temporary systems from the project.

660-1.08 DEFINITIONS.  Under Item 1. Electrolier, add the following after the word ballast: ,foundation.

660-2.01 EXCAVATING AND BACKFILLING. In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

Add the following after the fourth paragraph: Backfill the first 150 mm lift with material free of rocks exceeding a 25 mm maximum dimension.

660-2.05 CONDUIT. Add the following: The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid.  After  new pavement has been placed, trenching will not be allowed.

Change the first sentence in paragraph number 1 to reference UL-651B.   (ANH, 05/06)

660-2.06 JUNCTION BOXES. Delete the second paragraph and substitute the following: Only use pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the plans.  All junction box lids shall be cast iron.

Add the following subsection:

660-2.17 EMS DISKS.  Install electronic marker system locator disks at the end of each conduit run where junction boxes are not specified, including runs terminating for the winter shutdown of construction.  Use water locators for scada conduit and electric locators for lighting conduit.

Use 3M Scotch Mark, Marker Locator, EMS II Series or equal.

660-3.16 LUMINAIRES.  Add the following:  Provide a luminaire that produce IES Medium Cutoff Type II light distribution with a 250 watt high pressure sodium lamp with a rated life of 24,000 hours and a magnetic –regulator ballast.

660-4.01 METHOD OF MEASUREMENT.  Add the following: Measurement for conduit will be along the horizontal projection of the conduit from center of junction box to center of junction box.  Measurement for junction box will be by the unit completed and accepted in final position.  Illumination cable is to be provided  by the City of Unalaska at a later time and is not included, however pull strings are to be installed subsidiary to conduit.

Item 660(13), Electrolier.  By each complete unit installed and ready operation after the City connects power.

660-5.01 BASIS OF PAYMENT.  Add the following:  Excavation, bedding and backfill for conduits and junction boxes shall be considered incidental to the installation of the respective items.  EMS disks will be considered subsidiary to 660(20) 50mm HDPE Conduit.

Item 660(3), Highway Lighting System Complete, is for work on East Point and Ballyhoo Roads. The other lighting system improvements are paid for under other 
items.

Delete Pay Item 660(13) Relocate Electrolier, and add the following pay items:

Pay Item No.	Pay Item	Pay Unit

660(13)	Electrolier	Each

660(20)	50mm HDPE Conduit	Meter

660(29)	Type 1A Junction Box	Each

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Delete Item 4 in its entirety and substitute the following:

4. Methyl Methacrylate Pavement Markings.  Apply Methyl Methacrylate markings with truck-mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.  Provide the manufacturer’s installation instructions for the Methyl Methacrylate markings at least 15 days prior to application.  Retain a copy of the instructions for use on the project.

A manufacturer’s representative shall be present on the first day of striping and any additional days as required by the Engineer.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in liters.

Perform a film test strip at the beginning of each striping shift and when there is a change in asphalt type.   In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion.

Apply glass beads as specified in Subsection 712-2.18. Use a minimum drop on rate of 580 g/m2 for transverse type markings.  Apply glass beads for Type V sprayed material by double bead gun, one gun directly in front of the spray unit and another directly behind.

Remove contaminants such as curing agents, surface oils or existing pavement marking materials prior to applying the new pavement markings. Then, thoroughly clean and dry the roadway surface immediately prior to applying Methyl Methacrylate pavement markings.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 1.5 mm.

#### METHYL METHACRYLATE PAVEMENT MARKING

#### YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 |
| --- | --- |
| ##### Longitudinal Type3 ##### (Center and Edge lines) | 2.3 mm |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 3.0 mm |
| Neutral Area (Diagonals, Chevrons) | 1.5 mm |

1. Measure Type V spray without glass beads.  Tolerance is ±0.1 mm.  Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 150 mm x 300 mm flat sheet of 2 mm thick aluminum placed in the path of the striping guns.

2. not used

3.  Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 1.5 mm per application pass.

Non-Inlaid Markings

New asphalt pavement:  Apply interim non-inlaid Longitudinal and Transverse Type markings at 0.75 mm.

Unless directed otherwise by the Engineer, apply the final 1.5 mm of the Longitudinal Type markings once the asphalt has cured for the duration listed below.

Stone Mastic Asphalt Concrete		30 days

All others 	15 days

Apply the final Transverse and Neutral Area markings as shown in the application table at this time.  Multiple application passes are required for Transverse Type markings.

Existing asphalt pavement:  Apply markings according to the Yield Thickness Table.  Longitudinal Type markings will require multiple application passes.

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the removal requirement. Do not use any method utilizing burning with an open flame for removing pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width for any 15 m longitudinal run from the width shown in the Plans.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 4:

5.	Liter Basis:  The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in liters.  The Department will limit the final quantity of 115% of the Plan quantity.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B).  No separate payment shall be made for furnishing and maintaining the MMAMS.

(08/21/02)R246

The Department will pay the contract unit price for the volume of Methyl Methacrylate accepted by the Engineer up to a maximum of 115% of the quantity shown in the Plans.  All Methyl Methacrylate material over-runs above 115% of the plan quantity shall be paid for by the Contractor at no expense to the Department.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10B)	Methyl Methacrylate Pavement Markings	Liter

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENTS. Add the following sentence:  Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T-53 and ASTM D5801 assigned to each grade.

Performance Graded Asphalt Cement

PG 52-28	PG 58-28	PG 64-28

Softening Point	(none)	49C	52C

AASHTO T-53

Toughness min.	(none)	12.4 N-m	12.4 N-m

ASTM D5801

Tenacity min.		(none)	8.5 N-m	8.5 N-m

ASTM D5801

(9/18/00) R244M98

SECTION 703

AGGREGATES

Special Provisions

Add the following subsection:

703-1.01 AGGREGATES. All aggregates specified in this section shall be derived from granitic rock.

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Coarse Aggregate, in the table, change Percent of Wear to 50 max., and Degradation Value to 45 min.

Under Percent Fracture, delete 80 min. (single face), and replace with 90 min. (two face).

Add the following to Table 703-3:

| SIEVE, mm | GRADATION |
| --- | --- |
|  | Type IV |
| 25 mm | - |
| 19 mm | 100 |
| 12.5 mm | 85-100 |
| 9.5 mm | 75-85 |
| 4.75 mm | 55-65 |
| 2.36 mm | 42-50 |
| 1.18 mm | 32-42 |
| 0.600 mm | 23-35 |
| 0.300 mm | 15-22 |
| 0.150 mm | 6-16 |
| 0.075 mm | 4-8 |

Standard Modifications

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total." (06/25/99)M 82

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material. (06/25/99)M 82

Special Provisions

703-2.09 SUBBASE. First paragraph, add the following to the requirement: Percentage Fracture of Grading B, WAQTC TM 1, 90% two face

Delete Table 703-6, and substitute the following:

Table 703-6

REQUIREMENTS FOR GRADING FOR SUBBASE

PERCENT PASSING BY WEIGHT

|  | #### GRADING |  |
| --- | --- | --- |
| #### SIEVE, mm | A | B |
| 100 | 100 | - |
| 50 | 85-100 | 100 |
| 4.75 | 20-55 | 20-55 |
| 0.075 | 0-6 | 0-4 |

SECTION 706

CONCRETE & PLASTIC PIPE

Standard Modifications

706-2.06 PLASTIC PIPE FOR SANITARY SEWERS. Replace “Type S” with “Type S or Type D”. (02/08/01)M 97

### Special Provisions

706-2.06 PLASTIC PIPE FOR SANITARY SEWERS.  Add the following at the end of this sub-section:

High Density Polyethylene (HDPE) SDR11, ASTM D3350 (Cell Classification 345434C)

HDPE fittings shall meet the same requirements as HDPE pipe.

HDPE pipe furnished with arctic insulation and 215 mm OD HDPE jacket shall meet the following additional requirements.  Heat trace channel shall be HDPE rectangular, 25.4 mm by 38.1 mm by 1.6 mm thick.  Arctic insulation shall be poured polyurethane foam, minimum density = 45 kg/cu m, minimum compressive strength = 240 kPa, maximum thermal conductivity K = 0.023 W/sq. m-K.  Exposed ends of arctic insulation shall be sealed with an elastomeric coating acceptable to the Engineer.  Arctic insulated HDPE pipe shall be fabricated in accordance with the most current specifications of the US Public Health Service for Alaska projects.

Submit manufacturer’s literature for HDPE pipe and fittings, HDPE jacket, heat trace channel, arctic insulation, and elastomeric coating, and insulation joint kit for the Engineer’s review and comment.

Standard Modifications

706-2.07 CORRUGATED POLYETHYLENE PIPE.  For culverts replace “Type S” with “Type S or Type D”. (02/08/01)M 97

For underdrains, replace “AASHTO M252” with “AASHTO M252 for 75 –250 mm pipe diameters, AASHTO M294, Type SP for 300 – 1200 mm pipe diameters.

SECTION 707

METAL PIPE

### Special Provisions

707-2.01 CORRUGATED STEEL PIPE, PIPE ARCHES, AND UNDERDRAINS. Add the following: Corrugated steel pipe used in underdrains/subdrains shall be Type III.

    - WATER CONDUIT.  Delete the following:

Ductile iron	FSS WW-P-421D

Add the following:

### Ductile iron pipe (DIP)			Class 52 rubber gasketed bell-and-spigot joint pipe per AWWA C-151, with cement mortar lining per AWWA C-104

DIP mechanical joint fittings	2400 kPa pressure rating short body per AWWA C110, with cement mortar lining per AWWA C-104

DIP mechanical joint retainer glands	1720 kPa pressure rating, UL listed, ASTM A536-80, multiple thrust-restraint wedge design with twist-off nuts for correct torquing, “EBAA Megalug” or Engineer accepted equal

DIP standard rubber gaskets	AWWA C111

DIP field lock gaskets	1720 kPa pressure rating, UL listed, rubber with multiple vulcanized stainless steel locking segments, all subject to Engineer’s acceptance

Tapping sleeves for DIP	1380 kPa pressure rating, ductile iron ANSI Class 150 flange, 304 stainless steel shell, branch neck, armors, lifter bars, lugs, test plug assembly, bolts, and nuts, two rows of 16 mm teflon-coated NC bolts and heavy hex nuts with plastic lubricating washers, virgin SBR wrap-around pipe gasket per ASTM D 2000 MAA 410Z-90 (Z = 45 Durometer), virgin SBR flange gasket per ASTM D 2000 MAB 710-90 glued to flange face, “Romac SST” or Engineer accepted equal

Steel casing pipe for railroad crossing	New ASTM A252 Grade 2, 241,000 kPa minimum yield stress, 762-mm diameter, 11.9-mm minimum wall thickness.

Carrier pipe casing spacers	Two piece centering-type, 711 mm outside diameter, constructed to fit 335 mm actual diameter DIP (300 mm nominal diameter), 200 mm minimum length, 304 stainless steel band, risers, nuts, bolts, and washers, 2.3 mm minimum thickness EDPM band liner, at least 4 each 50 mm wide glass filled polymer plastic runners, designed to support the buoyant force of empty carrier pipe that is completely submerged in water with a safety factor of 2 against damage to the spacer (assuming spacers at 2.4 m on center)

Submit manufacturer’s literature for ductile iron pipe, fittings, and appurtenances, tapping sleeves, steel casing pipe, and casing spacers for the Engineer’s review and comment.  Submit design calculations for casing spacer buoyant force resistance, stamped and signed by an Alaska Professional Engineer, for the Engineer’s review and comment.

Add the following new subsection:

707-2.07 SEWER CONDUIT.

### Ductile iron pipe (DIP)				Class 52 rubber gasketed bell-and-spigot joint pipe per AWWA C-151, with cement mortar lining per AWWA C-104, all sewer services shall be cast iron conforming to ASTM A-74.

Sewer Gaskets						Gaskets shall perform to ASTM C-564

DIP mechanical joint fittings 	2400 kPa pressure rating short body mechanical joint per AWWA C110, with cement mortaring per AWWA C-104

DIP standard rubber gaskets 	AWWA C111

Submit manufacturer’s literature for ductile iron pipe, fittings, and appurtenances for the Engineer’s review and comment.

SECTION 710

FENCE AND GUARDRAIL

# Special Provisions

710-2.11 GUARDRAIL TERMINALS. Add the following: Use the ET-2000 LET.

The current guardrail end terminal drawings approved by the Department are as follows:

# Drawing	Original	Latest

# Number	Date	Revision	Comments

# ET-2000 LET (Metric)	SS 155M	7/18/00	None	11.4 m, 7 tube,

# Plus head

# ET-2000 LET (English)	SS 155	5/18/00	None	37.5 ft, 7 tube,

# Plus head

(01/22/02)R249

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.09 CORPORATION STOPS AND CURB STOPS.  Delete in its entirety.

712-2.10 GATE VALVES.  Delete the second and third paragraphs and substitute the following: Ductile iron body resilient seat valves, with rubber-encapsulated wedges, manufactured in accordance with the requirements of AWWA C515, with 1720 kPa maximum rated working pressure.  Valves shall be non-rising stem type with a triple O-ring stem seals.  Valves shall have a 50.8-mm square nut, and shall open counterclockwise.  Valves shall be coated inside and outside with fusion bonded epoxy.  Valves shall be UL-listed.  Valves shall have mechanical joint ends, except that hot tap valves shall have flange-by-mechanical joint.  Flanged valve ends shall be ANSI Class 150 drilling. Gate valves shall be “Mueller”, “American Flow Control”, or Engineer accepted equal.   Valve ends shall be restrained using “EBAA Iron Meg-a-lugs”, “Mueller Aquagrip” or approved equal. Submit manufacturer’s literature for the Engineer’s review and comment.

712-2.11 VALVE SERVICE BOXES.  Delete the second, third, and fourth paragraphs in their entirety.

712-2.12	HYDRANTS.  In the second sentence of the first paragraph, delete the words “125 mm”, and substitute the following words: “133 mm”

Insert the following paragraphs at the end of this subsection:  All hydrants shall be L-base single pumper type with 150-mm mechanical joint base connections.  All hydrant main valves shall open counterclockwise.  Hydrant main valves shall be of the compression type, where water pressure holds the main valve closed, permitting easy maintenance or repair of the entire barrel assembly from above the ground without the need of a water shut-off.

All fire hydrants shall be furnished with a breakaway traffic flange, which allows both barrel and stem to break clean upon impact from any angle.  Traffic flange design must be such that repair and replacement can be accomplished above ground.

All hydrants shall be draining (drain plug removed).

Operating and nozzle nuts shall be pentagon shaped with 38.1 mm point-to-flat measurements.

Hose nozzle threading shall be in conformance with NFPA #194 for National (America) Standard Fire Hose Coupling Screw Threads.

All hydrants shall be furnished with chains that attach hose and pumper connection caps to hydrant bodies.

Fire hydrants shall be “Mueller Centurian”, or “American Darling B-62-B” only. Submit manufacturer’s literature for fire hydrants for the Engineer’s review and comment.

Add the following Subsection:

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.

2.	Performance Properties: Add the following:

k.	Adhesion: 	To Portland Cement, minimum 13.8 MPa, to asphalt, dependent on tensile failure of the substrate.

(09/04/01)R221M98

SECTION 724

SEED

Special Provisions

724-2-02. MATERIALS. Delete this Subsection in its entirety and substitute the following:  Meet applicable requirements of the State of Alaska Seed Regulations, 11 AAC 34, Article 1 and Article 4.

Furnish “certified seed” or 4 signed copies of a report certifying that each lot of seed has been tested by an approved laboratory within 9 months of date of application. Include: name and address of laboratory, date of test, lot number for each kind of seed, and results of test as to name, percentages of purity and germination, and percentage of weed content for each kind of seed furnished.

Meet or exceed the percentages of sproutable seed specified in Table 724-1.

# TABLE 724-1

Seed Requirements

| SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

- Sproutable Seed is the mathematical product of Germination and Purity.

(03/05/02)R52M98

SECTION 729

GEOTEXTILES

Standard Modifications

729-2.01 Embankment Separation and Reinforcement.  Under 1. Separation, replace (medium survivability) with (Class 3).  Under 2.  Reinforcement, replace Separation (high survivability) with Stabilization.

729-2.02 Subsurface Drainage and Erosion Control.  Under 2. Erosion control, replace 0.1 sec-1 with 0.5 sec -1.

729-2.04 Sediment Control.  Replace Meet AASHTO M 288 for Sediment Control with  Meet AASHTO M 288 for Temporary Silt Fence.

(2/8/01) M98

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Standard Modification

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.

(06/25/99)M 83

Special Provisions

Add the following:

6.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(2/29/00)R81M

APPENDIX A

MATERIALS CERTIFICATION LIST

APPENDIX B

EROSION AND SEDIMENTATION CONTROL PLAN

#### APPENDIX C

CONSTRUCTION SURVEY REQUIREMENTS

#### APPENDIX D

TEMPORARY CONSTRUCTION PERMITS