PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

CAMPBELL CREEK TRAIL, PHASE II

INTERNATIONAL AIRPORT ROAD TO LAKE OTIS

CM-0001(263)/55801

PM&E 96018

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publication, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

d.	Standard Specifications for Highway Construction 1998 Metric. ($25.00)

e.	Geotechnical Report Titled “Campbell Creek Greenbelt Bike Trail”, Anchorage, Alaska, January 1998 by Shannon & Wilson, Inc.

3.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

4.	New DBE Program Requirements

ADOT&PF will fully implement new program elements of its USDOT-approved Disadvantaged Business Enterprise (DBE) Program on August 1, 2000.  Key elements of the new DBE Program are:

A newly revised DBE Program specification, Section 120;

All bidder’s are required to register annually with the ADOT&PF Civil Rights Office;

Apparent low bidder’s will be required to submit a written commitment with each DBE firm proposed for subcontracting; and

Prime Contractors will be required to report to the ADOT&PF Civil Rights Office payments made to DBE firms on a monthly basis.

All information required may be reported on forms available from the ADOT&PF Civil Rights Office or the Regional Contract Compliance Officer.  These forms will also be available soon on the ADOT&PF Civil Rights Office web page in ADOBE Acrobat downloadable format at

www.dot.state.ak.us/external/state_wide/dbe/dbe.html

Any questions about these new provisions may be directed to the Civil Rights Office at 1(800)770-6236 or 269-0851.

5.	The Materials Certification List (MCL) has been included in Appendix D.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

TABLE OF CONTENTS

Section 101 Definitions and Terms	1

Section 102 Bidding Requirements And Conditions	2

Section 103 Award and Execution of Contract	3

Section 105 Control of Work	4

Section 106 Control of Material	8

Section 107 Legal Relations and Responsibility to Public	11

Section 108 Prosecution And Progress	14

Section 109 Measurement and Payment	15

Section 120 Disadvantaged Business Enterprise (DBE) Program	17

Section 202 Removal of Structures And Obstructions	28

Section 203 Excavation And Embankment	30

Section 301 Aggregate Base Course	32

Section 501 Structural Concrete	34

Section 504 Steel Structures	36

Section 511 Modular Block Retaining Walls	39

Section 514 Concrete Surface Treatments	43

Section 603 Culverts And Storm Drains	45

Section 607 Fences	46

Section 608 Sidewalks	49

Section 609 Curbing	51

Section 615 Standard Signs	52

Section 618 Seeding	53

Section 619 Soil Stabilization	57

Section 620 Topsoil	58

Section 621 Planting Trees and Shrubs	59

Section 627 Water System	68

Section 640 Mobilization and Demobilization	72

Section 641 Erosion, Sediment, and Pollution Control	73

Section 642 Construction Surveying and Monuments	80

Section 643 Traffic Maintenance	81

Section 644 Services to be Furnished by the Contractor	88

Section 646 CPM Scheduling	90

Section 647 Equipment Rental	91

Section 650 Site Amenities	94

Section 652 Creek Restoration	104

Section 660 Signals And Lighting	107

Section 661 Load Centers	113

Section 670 Traffic Markings	114

Section 702 Asphalt Materials	116

Section 703 Aggregates	117

Section 708 Paints	119

Section 712 Miscellaneous	121

Section 716 Structural Steel	122

Section 722 Bridge Railing	123

Section 724 Seed	124

Section 726 Topsoil	126

Section 727 Soil Stabilization Material	127

Section 730 Sign Materials	129

Appendix A	Permits
Appendix B	Erosion And Sediment Control Plan
Appendix C	Construction Surveying Requirements
Appendix D	Materials Certification List

Section 101
Definitions and Terms

Standard Modification

101-1.03 DEFINITIONS. Add the following definition:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed.

(06/25/99)M68

Special Provisions

Add the following definition:

NON-FROST SUSCEPTIBLE MATERIAL.. Material that contains 6 percent or less passing the 0.075 mm  screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75 mm  material.

(11/29/01)R1M98

Section 102
Bidding Requirements And Conditions

Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form.

(2/1/00)R171M98

Section 103
Award and Execution of Contract

Standard Modification

103-1.01 CONSIDERATION OF BIDS. Add the following after item 9:  In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State.

(10/28/99) M 84

Standard Modification

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”.

(06/25/99)M 69

Section 105
Control of Work

Standard Modification

105-1.02 PLANS AND WORKING DRAWINGS. Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, the Contractor shall furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: Request locates from all the utilities having facilities in the area. Use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska Communication Systems Alaska Fiberstar Alaska Native Hospital Anchorage Water and Wastewater Utility AT&T Alascom, Inc. Chugach Electric Association ENSTAR Natural Gas, Inc. GCI Marathon Oil Corporation Municipal Light & Power PTI Communications, Inc. Phillips Petroleum Signature Flight Support SOA-DOT/PF Anchorage M&O TelAlaska, Inc. Tesoro Petroleum Co. Unocal Oil & Gas

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination .  You shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

You shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

1.	Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

2.	Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies, through the Engineer, fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

105-1.07 COOPERATION BETWEEN CONTRACTORS. Add the following: The following project will be under construction concurrently with this project:

Campbell Creek Trail Connection to Tudor Road Crossing (TEA-0001(137) / 52520)

Owner:	 MOA Department of Public Works

Contractor:	Wilder Construction

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above project so as to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contract.

(2/1/00)R175M98

105-1.13 MAINTENANCE DURING CONSTRUCTION. Add the following: Inspect and clean all storm drain sumps and petroleum separator manholes during the construction season and prior to winter shutdowns. This inspection and maintenance of the storm drain system will not be paid for directly but will be subsidiary to work paid for under Sections 603 and 604.

(2/1/00)R4M98

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract.

(02/06/02)R237M98

Standard Modification

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Delete this Subsection in its entirety and substitute the following:

Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any  dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish    the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

1.	The act, event, or condition the claim is based on.

2.	The Contract provisions which apply to the claim and provide relief.

3.	The item or items of Contract work affected and how they are affected.

4.	The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract   provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver  of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and  AS 36.30.630.

(03/26/01) M 101

Special Provisions

Add the following: Any appeal to the Superior Court under AS 36.30.685 must be filed in the Third Judicial District, in Anchorage.

(03/21/01)R93

Section 106
Control of Material

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials which remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

(08/31/99)S13

106-1.02 LOCAL MATERIAL SOURCES. Add the following under Item 2. Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to their beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

1.	Site specific health and safety risks.

2.	Recognition and avoidance of hazards.

3.	Restricted areas.

4.	Warning and evacuation signals.

5.	Other special safety procedures.

6.	Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.

(05/01/02)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following:

When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T 27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 224

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO TP 53

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T 166/T 275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

(07/26/01)S 87  (03/08/02)klj

Section 107
Legal Relations and Responsibility to Public

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If you discover cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by your operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Add the following: The Municipality has received the following permits on the Contractor’s behalf that are contained in Appendix A:

1.	U.S. Army Corps of Engineers Section 404 Permit

2.	Municipality of Anchorage Flood Hazard Permit

3.	Alaska Department of Fish and Game (ADFG) Title 16 Permit

4.	State of Alaska, Division of Governmental Coordination, Final Consistency Determination

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from you.

Work within Campbell Creek covered by the AFG Title 16 permit is restricted to the period between May 15 and July 15.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If you require water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

(05/29/02)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following before the last paragraph: When construction activities meet any of the following conditions, advise the appropriate owning Utility(s) in writing at least 24 hours in advance of work.

1.	Operations anticipated being within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services

(7/30/99)R170M98

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120
Training Program	Section 645
Federal EEO Bid Conditions	Form 25A-301
EEO-1 Certification	Form 25A-304
DBE Subcontractable Items	Form 25A-324
ADOT&PF Training Program Request	Form 25A-310
Training Utilization Report	Form 25A-311
Contact Report	Form 25A-321A
DBE Utilization Report	Form 25A-325C
Summary of Good Faith Effort Documentation	Form 25A-332A
Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(01/22/02)S 80

Section 108
Prosecution And Progress

Standard Modification

108-1.01 SUBLETTING OF CONTRACT. Delete the last paragraph under Item 4. and add the following to Item 5:

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts.

(10/28/99) M 70

Special Provisions

108-1.03 PROSECUTION AND PROGRESS. Add the following under item no. 1: Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

(4/22/99)R250M98

Delete Item 5 of the first paragraph and substitute the following:

5.	The submittals identified under subsection 641-1.03, Submittals.

(01/31/02)R160M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

1.	those instances where the Engineer orders suspension of the work for unsafe conditions,

2.	for failure by the Contractor to carry out contractual provisions, or

3.	for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.

(2/15/01)R242M98

Section 109
Measurement and Payment

Standard Modification

109-1.05 COMPENSATION FOR EXTRA WORK.

Under item 1. Labor:

Delete: “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work.

(5/31/00)M90

1.	Labor. Replace subparagraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e.

(02/08/01)M71

Special Provision

Under item 3, Equipment, change the first sentence to read: … “Rental Rate Blue Book for Construction Equipment”, published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA, 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.

(1/27/00)R14

Standard Modification

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor.

(02/08/01)M71

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

Add the following section:

Section 120
Disadvantaged Business Enterprise (DBE) Program

Standard Modification

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

1.	Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

a.	that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

b.	whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

c.	has been certified by the Department in accordance with 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer. A DBE certified by the Department in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

d.	fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

2.	Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

a.	Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

1)	A description of the work that each DBE will perform;

2)	The dollar amount of participation by the DBE firm;

3)	Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

4)	Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

b.	DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

3.	Phase III - Construction.

a.	Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

b.	DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

c.	DBE Replacement. If a DBE replacement is approved by the Engineer, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

1)	The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

2)	If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

d.	DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

1.	Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

a.	Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

b.	If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

c.	Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

d.	Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

e..	Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

f.	Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

g.	Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

h.	Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

i.	Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

2.	Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

a.	The decision on reconsideration will be made by the DBE Liaison Officer.

b.	The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

c.	The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

d.	The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

1.	Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

a.	regular dealer;
b.	manufacturer;
c.	broker; 
d.	subcontractor; 
e.	joint-venture; or
f.	prime contractor.

2.	Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

a.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

b.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

c.	The DBE is certified in the appropriate category at the time of

1)	the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

2)	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

d.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

e.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

f.	The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

1)	The work performed will be necessary and useful work required for the execution of the Contract.

2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

3)	The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

4)	The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

5)	The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

6)	All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

7)	The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

g.	On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

a.	withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

b.	continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

1)	increasing the participation of other DBEs on the project;

2)	documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

2)	by a combination of the above.

4.	DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06.

(11/17/00)S 33

Section 202
Removal of Structures And Obstructions

Special Provisions

202-1.01 DESCRIPTION. Add the following: This work shall also include relocation of cluster mail boxes on concrete pads foundations, as shown on the Plans.

202-2.01 MATERIALS. Add the following after “Item 4. Reflectors”:

5.	Concrete. Class A as described in Section 501.

6.	Reinforcing Steel. Section 503.

7.	Grout. Subsection 705-2.04

Cluster mail box mounting bolts and template will be provided by the USPS.

202-3.01 GENERAL. Add the following: The construction of mail box installations shall use new posts and mail boxes. Mail boxes shall be United States Postal Service approved, either traditional or contemporary design, having a minimum length of 530 mm, minimum width of 200 mm and minimum height of 270 mm. Existing posts and foundations shall be removed with remaining holes backfilled to the level of surrounding ground. (4/18/00)R74M98

202-3.02 MAIL BOXES. Add the following: Remove existing cluster mail boxes and associated concrete pad foundations.  If cluster mail box cannot be immediately relocated to the new location it must be set on a concrete pad foundation at an approved temporary location.  Set cluster mail box in permanent location on concrete pad foundation

Contractor shall coordinate relocation (temporary and permanent) of cluster mail box with the United States Postal Service Lake Otis Station.  Contact Deiter Jackson at 563-9578 at least 72 hours prior to relocation of cluster mail box.

If the cluster mail box is damaged during relocation the Contractor shall repair or replace the mail box, as directed by the Engineer.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 150 mm.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84M98

202-5.01 BASIS OF PAYMENT. Add the following after the third paragraph:

Item 202(12A) Relocate Cluster Mail Boxes.  Payment is full compensation for removal of cluster mail box, removal of existing concrete pad foundation, concrete disposal, temporary mail box installation, concrete pad foundation, reinforcing steel, all mounting hardware and installation of relocated cluster mail box.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

202(12A)	Relocate Cluster Mail Boxes	Each

Section 203
Excavation And Embankment

Special Provisions

203-3.01 GENERAL. Add the following:  Obliteration of Trail D includes all grading operations necessary to incorporate the existing trail into the new trail and surroundings in order to provide a pleasing appearance from the new trail.  Fill ditches not required for drainage and grade to the approximate original contour of the ground.  Obliterate trail where indicated on the Plans in association with Item 202(2) Removal of Pavement.

This work shall also consist of pathway linear grading, as shown on the Plans.

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.

(03/14/02)R23M98

Add the following: All references to “roadway” shall also refer to “pathway”.

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP FOR AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5.

(03/14/02)R193M98

Add the following: Compact all embankment within 6 meters of a bridge abutment full width to not less than 100 percent of the maximum density. All material used within this zone shall be graded to pass the 75-millimeter sieve.

(2/1/00)R113M98

203-4.01 METHOD OF MEASUREMENT. Add the following after Item 5:

6.	Item 203(25). Pathway Linear Grading will be measured for payment .by the kilometer

Add the following after item “4.” following “No measurement will be made for:”

5.	obliteration of trail

203-5.01 BASIS OF PAYMENT. Add the following: Grading and placement of material used within 6 meters of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(6A) Borrow, Type A.

(2/1/00)R113M98

Add the following:

Obliteration of trail will be subsidiary to Item 202(2) Removal of Pavement.

Payment for Item 203(25) Pathway Linear Grading will be full compensation for furnishing all equipment, labor, tools and incidentals to provide removal of organics, preparation, excavation and shaping necessary to complete the work.  Haul, if required, will not be paid for directly, but will be subsidiary to Item 203(25) Pathway Linear Grading.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

203(25)	Pathway Linear Grading	Kilometer

Section 301
Aggregate Base Course

Special Provisions

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1.

(10/1/91)R116

301-2.01 MATERIALS. Add the following after the first paragraph: At the Contractor's option, recycled asphalt material (RAM) may be substituted for aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 0.300 mm | 5-34 |
| 0.150 mm | 3-22 |
| 0.075 mm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

(2/28/01)R176M98

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.

(9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Delete this section and substitute the following:  Spread and shape the material to the required grade and section.  The following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

Maintain the surface of each layer during the compaction operations in such manner that a uniform texture is produced and the aggregates firmly keyed.

The finished surface will be tested using a 3-m straightedge at selected locations.  The variance of the surface from the testing edge of the straightedge between two contacts with the surface shall not exceed 10mm.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for crushed aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(2/28/01)R176M98

Section 501
Structural Concrete

Special Provisions

501-1.01 DESCRIPTION. Add the following: This work shall also consist of construction of cast-in-place concrete retaining walls and concrete pile caps, as shown on the Plans.

Excavation and backfill required for the cast-in-place retaining walls shall be in accordance with Section 205.

501-2.01 MATERIALS. Add the following: Reinforcing steel shall conform to the requirements of Section 503.

Concrete surface treatments shall conform to the requirements of Section 514.

501-3.01 PROPORTIONING. Under 1. Determining Proportions and Batch Weights., delete the first sentence and substitute the following: Submit a mix design developed in accordance with ACI 211 and 301, Section 4 to the Engineer for approval.

(7/6/99)R37M98

501-4.01 METHOD OF MEASUREMENT. Delete the fourth paragraph.

Add the following: Reinforcing steel and other items included in the cast-in-place concrete retaining wall will be subsidiary to Item 501(15) Cast-In-Place Concrete Retaining Walls.

Reinforcing steel and other items included in the cast-in-place concrete pile caps will be subsidiary to Item 504(6) Elevated Trail.

501-5.01 BASIS OF PAYMENT. Add the following: Payment for cast-in-place concrete retaining walls will be made under Item 501(15) Cast-In-Place Concrete Retaining Walls.

Payment for Item 501(15) Cast-in-Place Concrete Retaining Walls will be full compensation for all labor, equipment and materials required for construction of the wall, complete and in place. Structural excavation, temporary shoring, reinforcing steel, insulation board, aesthetic fascia, and graffiti protection required for cast-in-place walls will not be paid for separately, but will be subsidiary to Item 501(15) Cast-in-Place Concrete Retaining Walls.

Payment for cast-in-place concrete pile caps will be made under Item 504(6) Elevated Trail.  Payment for cast-in-place concrete pile caps will be full compensation for all labor, equipment and materials required for construction of cast-in-place concrete pile caps, complete and in place. Structural excavation, temporary shoring, and reinforcing steel required for cast-in-place concrete pile caps will not be paid for separately, but will be subsidiary to Item 504(6) Elevated Trail.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

501(15)	Cast-In-Place Concrete Retaining Walls	Lump Sum

Section 504
Steel Structures

Special Provisions

504-1.01 DESCRIPTION. Add the following paragraph: This work also consists of constructing an Elevated Trail along the South bank of Campbell Creek, under the International Airport Road bridge North of Juneau Street, as shown on the Plans.

504-3.01 FABRICATION. Add the following Paragraphs to Item 2:

Fabricate architecturally exposed structural steel with exposed surfaces smooth, square, and free of surface blemishes, including pitting, rust and scale seam marks, roller marks, rolled trade names, and roughness.

Remove blemishes by filling, grinding, or by welding and grinding, prior to cleaning, treating, and shop priming.

Comply with fabrication requirements, including tolerance limits, of AISC's "Code of Standard Practice for Steel Buildings and Bridges" for architecturally exposed structural steel.

Replace Item 8, Paragraph 1 with: When welding, conform to AASHTO/AWS D1.1.

Add the following Items:

9.	Source Quality Control: The Contractor shall engage an independent testing and inspecting agency to perform fabrication and quality control inspection.  This shall include shop inspections and tests and preparation of test reports.  Testing agency will conduct and interpret tests and state in each report whether test specimens comply with or deviate from requirements.  Provide testing agency with access to places where structural steel Work is being fabricated or produced so required inspection and testing can be accomplished.  Correct deficiencies in or remove and replace structural steel that inspections and test reports indicate do not comply with specified requirements.  Additional testing, at Contractor's expense, will be performed to determine compliance of corrected Work with specified requirements.

In addition to visual inspection, shop-welded connections will be inspected and tested according to AWS D1.1 and the inspection procedures listed below, at testing agency's option.

Liquid Penetrant Inspection: ASTM E 165.

Magnetic Particle Inspection:  ASTM E 709; performed on root pass and on finished weld.  Cracks or zones of incomplete fusion or penetration will not be accepted.

Radiographic Inspection:  ASTM E 94 and ASTM E 142; minimum quality level "2-2T."

Ultrasonic Inspection:  ASTM E 164.

10.	Wood Decking: Wood decking shall be attached as follows:

Planks shall have maximum 6 mm gaps between adjacent planks at time of acceptance.  Planks shall be continuous across the structure. No splicing will be allowed. Every plank must be attached at each end and to interior supports with at least one fastener or as shown on the drawings.  Fasteners are to be galvanized A307 bolts.  Hex-head bolts, with a steel plank hold down, to be used at the ends of planks.  Carriage bolts are to be used as interior connection fasteners when required.  Power actuated fasteners will not be allowed.  Planks are to be drilled prior to installation of bolts.

504-3.02 ERECTION. Add the following paragraphs to Item 1:

Before erection proceeds, and with the steel erector present, verify elevations of concrete and steel bearing surfaces and locations of anchorages for compliance with requirements.

Do not proceed with erection until unsatisfactory conditions have been corrected.

Add the following item:

10.	Field Quality Control: The Contractor shall engage an independent testing and inspecting agency to perform field inspections and tests and to prepare test reports.  Testing agency will conduct and interpret tests and state in each report whether tested Work complies with or deviates from requirements.  Correct deficiencies in or remove and replace structural steel that inspections and test reports indicate do not comply with specified requirements.  Additional testing, at Contractor's expense, will be performed to determine compliance of corrected Work with specified requirements.  The Owner’s inspecting agency will furnish verification and quality assurance inspection.

Field-bolted connections will be tested and inspected according to RCSC's "Specification for Structural Joints Using ASTM A 325 or A 490 Bolts".

In addition to visual inspection, field-welded connections will be inspected and tested according to AWS D1.1 and the inspection procedures listed below, at testing agency's option.

Liquid Penetrant Inspection:  ASTM E 165.

Magnetic Particle Inspection:  ASTM E 709; performed on root pass and on finished weld.  Cracks or zones of incomplete fusion or penetration will not be accepted.

Radiographic Inspection:  ASTM E 94 and ASTM E 142; minimum quality level "2-2T."

Ultrasonic Inspection:  ASTM E 164.

504-3.03 PAINTING. Replace the first sentence of paragraph 13 of Item 3d with: For metal primer, coat shall be 76-127 microns.  Intermediate coat shall be 101-152 microns. Top coat shall be 76-101 microns.  All measurements shall be dry film thickness.

504-4.01 METHOD OF MEASUREMENT.

Under Item 2, “Kilogram,” change lettered sub-item designations “4, d, and e” to “d, e, and f” respectively.

(3/31/00)R253M98

Structural steel, wood decking and other items included in Item 504(6) Elevated Trail will not be measured.  Furnishing and driving elevated trail piling will be measured separately under Item 505(5) Furnish Structural Steel Piles and Item 505(6) Drive Structural Steel Piles respectively.

504-5.01 BASIS OF PAYMENT.

Payment for Item 504(6) Elevated Trail will be full compensation for all labor, equipment and materials required for construction of the elevated trail, complete and in place.  Structural excavation and temporary shoring required for the elevated trail will not be paid for separately, but will be subsidiary to Item 504(6) Elevated Trail.  Furnishing and driving elevated trail piling will be paid for under Item 505(5) Furnish Structural Steel Piles and Item 505(6) Drive Structural Steel Piles respectively.

Add the following Pay Items:

Pay Item No.	Pay Item 	Pay Unit

504(6)	Elevated Trail	Lump Sum

Add the following Section

Section 511
Modular Block Retaining Walls

Special Provisions

511-1.01 DESCRIPTION. The Modular Block Retaining Walls shall be constructed at the locations shown on the plans and as provided in these specifications.  The Modular Block Retaining Walls to be constructed shall consist of a precast modular masonry product specifically engineered for the retention of earth. The modular units shall be a gravity system and shall lock together vertically by pins.  The pins shall also be connected to geogrid reinforcement where indicated in the Plans.

The Contractor shall submit a modular block system for approval.  The submittal for the  modular block retaining wall shall include complete working drawings for the wall system in accordance with the provisions in Subsection 105-1.02 of the Standard Specifications.  The Contractor shall verify the existing ground elevations and conditions at the site before preparing the final working drawings.  Said working drawings shall contain all information required for the proper construction of the system and any required revisions or additions to drainage or other facilities. The working drawings shall be supplemented with calculations for the particular installation.  Said working drawings and calculations shall demonstrate the internal stability as well as the external stability of the modular block retaining wall and shall be signed and sealed by an Engineer who is registered as a Civil Engineer in the State of Alaska.  The Contractor shall allow the Engineer 3 weeks to review the working drawings and calculations after a complete set of working drawings and calculations are submitted by the Contractor.

Heights, lengths, and depths of Modular Block Retaining Wall systems may vary somewhat from the Plans, but begin and end of wall locations and top of wall elevations shall not be less than those shown on the Plans.  Modular Block Retaining Wall shall battered at 1H to 8V.

The height and length to be used for any system shall be the minimum for the system that will effectively retain the earth behind the structure for the loading conditions, profile, or slope lines shown on the plans or on the approved working drawings.  In addition, if the plans show limiting parameters for the systems, the system selected shall conform to those parameters.

The construction of the Modular Block Retaining Wall system shall conform to the details shown on the plans and shall be constructed in accordance with the manufacturer’s instructions.  The supplier shall provide technical assistance and training to the Contractor.  The Contractor shall provide evidence of prior installation experience with the specific product being used.

511-2.01 MATERIALS. Materials furnished for the Modular Block Retaining Walls shall conform to the following:

GENERAL. The Contractor shall make his own arrangements to purchase and/or manufacture the pre-cast modular block units, attachment devices, and all other necessary components as shown on the Plans.  Materials not conforming to the Plans or specifications, shall not be used without written consent from the Engineer.

1.	Modular Block Units. The units shall be precast in conformance with the manufacturer's requirements and the following additions:

a.	Handling, Storage and Shipping: All units shall be handled, stored, and shipped in such a manner as to protect them from chipping, discoloration, cracks, and fractures.

b.	Rejection: Units shall be rejected because of failure to meet any of the requirements specified above. In addition, any of the following defects shall be sufficient cause for rejection.

1)	Defects caused by faulty casting.

2)	Defects indicating honeycombed or open texture concrete.

3)	Cracked or severely chipped units.

4)	Unreasonable color variation on front face of unit.

c.	Color: Block color shall be buff. Contractor shall submit samples of colors for approval by the Project Landscape Architect.

2.	Soil Reinforcing and Attachment Devices. All reinforcing and attachment devices shall be carefully inspected to insure they are true to size and free from defects that may impair strength and durability. The geogrid shall meet the requirements of AASHTO Standard Specifications for Highway Bridges, latest Edition, and per the modular block unit suppliers design recommendations.

3.	Backfill Materials. All backfill materials for modular block retaining walls shall conform to requirements for Selected Material, Type A, as set forth in Subsection 703-2.07 Selected Material.

CONSTRUCTION REQUIREMENTS

511-3.01 EXCAVATION AND FOUNDATION. Excavation and preparation of the foundation shall be in conformance with Section 205, Excavation, Backfill and Foundation Fill for Structures.

Foundation Preparation. The foundation for the modular block retaining wall structure shall be graded level for a width as shown on the plans.  Prior to wall erection, the foundation backfill shall be compacted to meet the requirements of Section 301.  Any foundation soils found to be unsuitable shall be removed and replaced with backfill as per Section 205.

511-3.02 WALL ERECTION. A field representative from the proprietary modular block wall system being used shall be available during the erection of the wall.  The Services of the representative shall be at no additional cost to the Department.

Precast masonry block units shall be placed so that their final position is battered at 1H to 8V, as shown in the Plans.  The masonry block units shall be placed in successive horizontal lifts in the sequence shown on the working drawings as backfill placement proceeds.  While placing backfill material behind the first course of masonry block units, place backfill material at the front of the units. Remove all excess backfill material from the top surface of all masonry block units prior to placement of the next course of masonry block units.

Backfill Placement. Backfill placement shall closely follow erection of each course of masonry blocks.  Backfill shall be placed in such a manner as to avoid any damage or disturbances of the wall materials or misalignment of the facing panels.  Any wall materials which become damaged during backfill placement shall be removed and replaced at the Contractor's expense.  Any misalignment or distortion of the masonry block units due to placement of backfill outside the limits of this specification shall be corrected by the Contractor .

Backfill shall be compacted to 95 percent of the maximum density as determined by Alaska Test Method T-12 or AASHTO T 180.  The maximum lift thickness after compaction shall not exceed 200mm.  The Contractor shall decrease this lift thickness, if necessary to obtain the specified density.  Field density will be determined using Alaska Test Method T-3 or T-11 by the Engineer.

Compaction within 900mm of the back face of the wall facing shall be achieved by using a plate compactor.

A minimum of one density test shall be taken by the Engineer after every three levels of blocks are placed.

At the end of each day's operation, the Contractor shall slope the last level of backfill away from the wall to rapidly direct water runoff away from the wall face.  In addition, the Contractor shall not allow surface runoff from adjacent areas to enter the wall construction site.

511-3.03 COORDINATION. After construction staking the Modular Block Retaining Wall excavation limits, but at least 48 hours prior to beginning construction of the retaining wall, the Contractor shall contact Lori Schanche of MOA PM&E at 343-8368 to schedule a field review with the Municipal Horticulturalist.  The horticulturalist shall determine if any existing trees behind the proposed retaining wall require removal or trimming.  All remaining trees shall be pruned of branches within 2.75 meters above the trail grade.

511-401 METHOD OF MEASUREMENT. Modular Block Retaining Walls will be measured by the square meter of wall face measured along the face of the wall, and including that part of wall which is below grade as indicated on the plans.  Measurement shall take place prior to fill of backfill.  Measurement shall be by vertical face, not parallel to batter angle.

511-5.01 BASIS OF PAYMENT. The contract price paid per square meter of wall face for Modular Block Retaining Walls shall include full compensation for furnishing all labor, materials, tools, equipment, and incidentals and for doing all work involved in constructing the earth retaining structure; including tree removal, tree pruning, precast masonry blocks, random backfill soil, excavation, aggregate base course leveling pad, and all parts of or appurtenances to the modular block earth reinforcement system, complete in place, as shown on the Plans, as provided in the Standard Specifications, Standard Modifications and these Special Provisions, and as directed by the Engineer.

Payment will be made under:

Pay Item No.	Pay Item 	Pay Unit

511(3)	Modular Block Retaining Walls	Square Meter

Add the following Section:

Section 514
Concrete Surface Treatments

Special Provisions

514-1.01 DESCRIPTION. This work consists of providing an aesthetic fascia on all precast and cast-in-place concrete walls.  Use form liners on all cast-in-place concrete retaining walls.  Install graffiti protection on all walls and surfaces designated on the Plans.

514-2.01 MATERIALS. Provide standard reusable, non-porous form liners conforming to the following requirements:

Concrete Pattern: Where indicated on the Plans, Contractor shall provide a textured and patterned finish to vertical cast-in-place concrete retaining wall surfaces.  Surface shall be formed to provide a staggered board pattern with coarse wood grain texture finish.  Finish shall provide random offset of individual boards with variations of between 6mm and 19mm.  Board texture shall provide distinctly visible wood grain finish.  This pattern shall match that used for Campbell Creek Trail Connection to Tudor Road Crossing (TEA-0001(137) / 52520).  Contractor shall provide one meter by one meter sample of the proposed finished surface for Engineer’s approval.  The approved panel shall be used for comparison and acceptance of all other textured vertical concrete.

Use a two-step graffiti protection system designed specifically for this use.  The system shall consist of a single component clear acrylic base coat covered by a clear urethane finish coat.  This material is not a sealer or vapor barrier and no appreciable discoloration is allowed.

Trained personnel shall apply the material according to the manufacturer’s recommendations.

CONSTRUCTION REQUIREMENTS

514-3.01 AESTHETIC FASCIA. Use form liners on all retaining wall forms which have exposed surfaces.  The wall dimensions and concrete quantities provided on the Plans are minimum and do not include allowances for the thickness of the form liners and must be accounted for by the Contractor.

The liners will cover the majority of the form with a minimum of 50 mm and a maximum of 300 mm between the edge of liner and the finished top of the wall, pathway or original ground grade at the bottom, and edge or expansion joints of the wall on the sides.  The Engineer shall approve the liner placement on the form prior to the concrete pour.

514-3.02 GRAFFITI PROTECTION. Let all concrete surfaces set at least 28 days before applying any coatings.  Apply the base coat with a roller or sprayer in accordance with the manufacturer’s recommendations.  Apply two coats of the finish coat after the base coat has cured for 72 hours.  Apply appropriate masking as required.

514-4.01 METHOD OF MEASUREMENT. Aesthetic fascia and graffiti protection will not be measured.

514-5.01 BASIS OF PAYMENT.  Payment for all labor, equipment, and materials to furnish and install aesthetic fascia and graffiti protection shall be subsidiary to Item 501(15) Cast-In-Place Concrete Retaining Walls.

Section 603
Culverts And Storm Drains

Standard Modifications

603-3.03 JOINING PIPE.

2. Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.”

(02/08/01)M95

Section 607
Fences

Special Provisions

607-1.01 DESCRIPTION. Add the following: The work under this section includes but is not limited to all labor, materials, transportation, testing, maintenance, and service necessary to furnish and install the Decorative Fence as shown on the Plans and specified herein.

607-1.02 SUBMITTALS. Add the following:

The following submittals for the decorative fence shall be provided by the Contractor for the Engineer’s review and approval.  The Contractor will not be allowed to begin decorative fence construction until all submittal requirements are satisfied and found acceptable to the engineer.  Changes or deviations from the approved submittals must be re-submitted for approval.  No adjustments in contract time will be allowed due to incomplete submittals.  At least 15 working days prior to initiating the work, the Contractor shall submit to the Engineer:

1.	Shop drawings of decorative fence panels and posts clearly showing all materials, finishes, connections, joining methods, location of installation and field measurements for construction of ornamental fence.  Approved shop drawings shall become the basis for acceptance of Work.

2.	After shop drawing approval, Contractor shall provide a full size sample panel that will serve as the basis of quality control for metal fabrication.  This panel shall be unfinished and available for review at an Anchorage location.  All subsequent panels shall meet the fabrication standard established by the approved sample.

3.	Contractor shall furnish color chips from standard RAL color chart for approval by the Engineer.

607-2.01 MATERIALS. Add the following:

Concrete	Section 501
Paint	Section 650, Section 708 as modified
Structural Steel	Section 716
Bridge railing	Section 722 as modified

All weather wood post material and preservative shall be as specified in Subsection 650-2.01 Materials – Wood Posts & Fixed Wood Bollards.

607-2.02 CONTRACTOR QUALIFICATIONS. Add the following:

Qualifications for Contractors constructing the decorative fence shall include the following:

1.	Not less than five years of continuous experience in the fabrication of similar products.

2.	All welding shall be performed by welders currently certified by the American Welding Society (AWS).

3.	Comply with “Code for Welding in Building Construction” of the American Welding Society, latest edition.

607-2.04 PRODUCT DELIVERY AND STORAGE. Add the following:  All steel fabrications and material shall be stored on skids above the ground.  The storage area shall be kept clean and properly drained.  Keep all materials dry during delivery.  Protect exposure to weather and contact with damp or wet surfaces.

607-3.01 CONSTRUCTION REQUIREMENTS. In the ninth paragraph, change “minimum” to “maximum”.

(06/25/99)M73

Add the following: Decorative fence panels shall be assembled in shop or factory.  Welds shall be neat and clean made by the gas metal arc method.  All flush welds shall be ground smooth.  Holes for attachment shall be predrilled prior to painting.

Contractor shall layout decorative fence in accordance with the Plans and approved Shop drawings.  Contractor shall investigate site for any grade changes, surface irregularities, and obstructions prior to installation and modify panels as necessary to accommodate grade changes.  Discrepancies between Plans and field conditions shall be addressed to the Engineer to approve proposed modifications.

All weather wood posts shall be plumb and level erected and evenly spaced with allowable tolerances for panel installation.  Footings and other components shall be installed to provide a continuous top surface at uniform height above the trail or to change grade and follow side slope grade where fence diverts from trail (down or up side slopes).

Paint, treatment and color for all weather wood posts shall meet the requirements of Subsection 650-3.01 Finishes, General (for wood posts).

Panel and top rail painting shall be polyester powder coating and meet the requirements of Section 708.  Polyester powder coat color shall match the existing trail bridge located west of Piper Street in the Campbell Creek Greenbelt.

Polyester powder coating application shall be prepared through a five step process to provide an acceptable finish:

a.	Rinsing and cleaning with clear water

b.	Phosphate treating to etch surfaces

c.	Re-rinsing with clear water

d.	Oven drying surfaces prior to powder coating

e.	Application of polyester powder by the electrostatic spray process to a thickness of 2.5mils.  The metal shall be oven heated at 232C for 14 minutes.

Add the following subsection:

607-3.02 CLEANUP. Add the following: Any abrasions to factory coatings and finishes shall be thoroughly cleaned.  Powder coated surfaces shall be reprimed and touched up with paint of the same color and quality used in the factory.  Drop cloths shall be laid under and around items to protect ground surfaces.  Excess materials and rubbish shall be removed from job site and disposed of off-site upon completion of Work.  The work area shall be clean and left in an acceptable condition.

607-4.01 METHOD OF MEASUREMENT. Add the following: The Decorative Fence shall be measured per lineal meter installed, outside of post to outside of post, complete in place.

607-5.01 BASIS OF PAYMENT. Add the following: Decorative Fence at the contract unit price per pay unit as shown below.  This price will be full compensation for furnishing materials, all labor, equipment, and incidentals necessary to complete these items.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

607(10)	Decorative Fence	Meter

Section 608
Sidewalks

Special Provision

608-1.01 DESCRIPTION. Add the following: This work also consists of constructing asphalt pathway(s) in conformance with the plans.

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

2.	Asphalt Sidewalk and Asphalt Pathway

Asphalt Cement, PG52-28	Subsection 702-2.01
Aggregate, Type II	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, N, min.	4450
Percent Voids, Total Mix	2-5
Compaction, Blows/side	50

608-3.03 SIDEWALK RAMPS. Delete this Subsection and substitute the following:

608-3.03 CURB RAMPS. Construct curb ramps according to the details and locations shown on the Plans.

Follow the construction requirements of Subsection 608-3.01.  Give the surface a coarse broom finish.

(06/11/02)R256M98

608-3.04 ASPHALT PATHWAY. Construct asphalt pathway in accordance with subsection 608-3.02 Asphalt Sidewalks.

608-4.01 METHOD OF MEASUREMENT.

Standard Modification

In both the first and second paragraphs, after “finished surface” insert “, including ramps”.

(06/25/99)M 74

Special Provisions

Delete the fourth item “Sidewalk Ramp” and substitute the following:

Curb Ramp. By each installation, complete in place, including construction of the ramp runs, flares, composite detectable warning tiles, backing curb, curb and gutter and landings necessary to provide a single street-level access.

(06/11/02)R256M98

Add the following:

Asphalt Pathway. Shall be measured by the Megagram in accordance with Section 109, Measurement and Payment.  Asphalt cement and anti-stripping additive will not be measured for payment.

608-5.01 BASIS OF PAYMENT. Add the following: Backing curb, will be subsidiary to Item 608(6), Curb Ramp.

The composite detectable warning tiles are subsidiary to Item 608(6) Curb Ramp.

(06/11/02)R256M98

Curb and gutter replaced with curb ramp installations will not be paid for separately, but will be subsidiary to Item 608(6) Curb Ramp

Asphalt cement and anti-stripping additive for Asphalt Pathway will not be paid for separately, but will be subsidiary to Item 608(7) Asphalt Pathway.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

Delete Item 608(6), Sidewalk Ramp, and substitute the following pay item:

Pay Item No.	Pay Item	Pay Unit

608(6)	Curb Ramp	Each

608(7)	Asphalt Pathway	Megagram

Section 609
Curbing

Special Provisions

609-3.02 CAST-IN-PLACE CONCRETE CURBING. Add the following to the fifth paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than 50 mm.

(2/1/00)R202M98

609-3.05 CURB RAMPS. Delete this Subsection in its entirety.

609-4.01 METHOD OF MEASUREMENT. Delete the second paragraph.

609-5.01 BASIS OF PAYMENT. Delete Pay Item 609(3), Curb Ramp.

(06/11/02)R256M98

Section 615
Standard Signs

Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

7.	Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose of). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(6/8/00)R50M98

Section 618
Seeding

Special Provisions

618-1.01 DESCRIPTION. Delete this subsection in its entirety and substitute the following: All new or disturbed areas, as a result of this project, shown on the Plans and any other areas identified by the Engineer, within the project limits shall be seeded.

This work shall consist of topsoil preparation, hydraulic application or hand broadcasting of the seed, finishing work including raking seed into the soil, fertilizing and limestone application in conformance with the Plans and Specifications.  Provide a living ground cover on all slopes as soon as possible.

618-2.01 MATERIALS. Add the following to the list of materials:

Schedule A	Subsection 724-2.02, Table 724-1
Schedule B	Subsection 724-2.02, Table 724-2
Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following:  Seed shall be applied in accordance with subsection 618-3.03 immediately after the topsoil base preparation has been completed in accordance with Section 620, and approved by the Engineer.  Protect prepared base from damage and prevent erosion if seeding season limitations prohibit application of seed.  Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope.  Areas to be seeded shall receive 100 mm depth of topsoil after settlement, as described in Section 620.  Complete slope preparation as soon as topsoil is placed on the slopes.  Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.l

618-3.02 SEEDING SEASONS.  Add the following: Application of Schedules A and B shall be performed between May 15 and August 15.  The Contractor shall submit request for extension of seeding season in writing and provide appropriate guarantee for remedy if seeding proves to be unsuccessful.

Application of Schedule A and B may be performed after the closing of contract time as indicated in subsection 105-1.15, Contract Completion.

Seed germination and establishment shall occur in the same growing season as seeding for Schedules A and B.

Submit a schedule indicating dates for accomplishing work for this section including watering and maintenance.  Provide for periodic up-dating and adequate notice for inspections, observations, and testing dates.

618-3.03 APPLICATION.  Add the following as subparagraph e.) to subsection 1.) Hydraulic Method: Seed, mulch and fertilizer for seeding shall be applied adhering to the application rates shown in the following table.

| Seed Mix | Component | Ingredients | Application Rate (48.8Kg/ha) |
| --- | --- | --- | --- |
| Type A | Seed | “Alyeska” Polargrass “Arctared” Red Fescue “Norcoast” Bering Hairgrass American Sloughgrass Smooth Brome Cotton Grass Water Sedge Beaked Sedge | 4.8 kg 14.6 kg 9.8 kg 4.8 kg 7.2 kg 2.5 kg 2.5 kg 2.5 kg Total = 48.8 kg |
|  | Soil Stabilizer Slope 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 2240 kg 2800 kg |
|  | Fertilizer | 16-16-16 | 586 kg |
| Seed Mix | Component | Ingredients | Application Rate (48.8Kg/ha) |
| Type B | Seed | “Arctared” Red Fescue Tufted Hairgrass “Alyeska” Polargrass American Sloughgrass Alpine Bluegrass “Gruening” | 19.7 kg 14.6 kg 2.5 kg 4.8 kg 7.2 kg Total = 48.8 kg |
|  | Soil Stabilizer Slope 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 1710 kg 2240 kg |
|  | Fertilizer | 16-16-16 | 586 kg |

The Contractor shall not remove the required tags from the seed bags until told to do so by the Engineer.

Upon the engineer’s approval, Nortan Tufted Hairgrass may be used as a substitute for Bering Hairgrass if Bering Hairgrass is commercially unavailable.  Substitute Bering Hairgrass with Nortan Tufted Hairgrass at the same application rate.

The Contractor shall submit to the Engineer an analysis of the seed mix (Schedules A and B) 10 days prior to application, showing percentage of seed mix, year of production, net weight, date of packaging, and location of packaging.  All seed containers or bags shall be sealed when coming on site.  Seed containers or bags already opened will not be accepted.  Contractor shall open seed containers or bags in the presence of Engineer, and submit the seed tag to the before application commences.

Provide fresh cleaned seed of the latest crop meeting the minimum purity and germination requirement.

Upon the Engineer’s approval, Bearing Hairgrass may be used as a substitute for Nortran Tufted Hairgrass if Bearing Hairgrass is commercially unavailable.  Substitute Nortran Tufted Hairgrass with Bearing Hairgrass at the same application rate.

Item	Application Rate (per ha)

Schedule A, B	Section 724 as modified
Mulch	1710 kg
Fertilizer (16-16-16)	586 kg

618-3.04 MAINTENANCE OF SEEDED AREAS.  Delete second paragraph and replace with the following: Water seeded areas as required for proper germination and growth.

Add the following:

Fertilizing.  Fertilizer shall be reapplied with water twice between May 31 and September 1 at a rate of one-half the initial application to all areas that received Schedules A and B as shown on Plans during the maintenance period.

Watering during establishment.  Contractor shall ensure that the seeded areas stay moist during germination and seedling establishment (as defined by the grass plants attaining a height of approximately 75mm).  The Contractor shall be prepared to water the seeded areas 3 times a day if weather conditions warrant it, until seedlings have become established.

If the Contractor fails to apply adequate moisture during the germination period for 4 consecutive days, or after 2 notices without immediate response, the Engineer may declare all affected seeding unacceptable.  The Contractor will be required to reseed areas that have not been kept moist.

Mowing. Schedules A and B shall not be mowed.

Maintenance period. The maintenance period for Schedule A and B shall be one full growing season following their acceptance. One full growing season shall be defined as the period between May 1 and September 30 for the purpose of this Contract. Partial growing seasons will not be counted against the one full growing season requirement.

The Contractor shall repair any damage to seeded areas within their respective maintenance periods upon request by the Engineer.

618-4.01 METHOD OF MEASUREMENT.  Delete full paragraph and substitute the following:  Seeding with Schedules A and B shall be measured by the kilogram.  Measurement by the kilogram shall be the number of kilograms of seed (Dry Measure) for Schedule A and B accepted in place.

The amount of mulch, fertilizer, limestone and water in this work, including any required reseeding, will be subsidiary to Pay Items 618(2A-2B) and shall not be measured separately for payment.

The work described under subsection 618-3.01 Soil Preparation shall not be measured but will be subsidiary to Items 618(2A-2B).

Water required for establishment of seed will be measured by the kiloliter using calibrated tanks or distributors, accurate water meters, or by weighing.  The conversion factor of 1.00 kilogram per liter will be used to convert weights to kiloliters.

Maintenance of seeded areas will not be measured separately, but shall be subsidiary to Items 618(2A-2B).

618-5.01 BASIS OF PAYMENT. Add the following:  Partial payments of up to 70% of full amount may be authorized for seeded areas at the time of acceptance.  The balance shall be paid at the completion of the maintenance period.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

618(2A)	Seeding – Schedule A	Kilogram

618(2B)	Seeding – Schedule B	Kilogram

Section 619
Soil Stabilization

Special Provisions

619-1.01 DESCRIPTION. Delete paragraph in its entirety and substitute the following:  This work consists of furnishing and installing matting for erosion control on slopes, as shown on the Plans or as directed by the Engineer.

619-2.01 MATERIALS. Delete the second subsection reference and substitute the following:

Matting	Subsection 727-2.02, as modified

619-3.02 APPLICATION. Delete paragraph in its entirety and substitute the following:  Matting shall be installed per manufacturer’s specifications.

Section 620
Topsoil

Special Provisions

620-1.01 DESCRIPTION. Delete paragraph in its entirety and substitute the following:  This work consists of furnishing and placing topsoil for seed areas and in planting beds at the locations shown on the Plans or as directed by the Engineer.

620-3.01 PLACING.  Delete paragraph in its entirety and substitute the following:

Topsoil shall be evenly spread to a minimum depth of 100 mm after settlement on all areas to be seeded with Schedule A or B, as described in Section 618.  Settlement shall be achieved by rolling the topsoil with a water-filled drum approved by the Engineer.

All slopes to be seeded with the ratio of 1V:4H or steeper shall be prepared by a method approved by the Engineer to result in indentations perpendicular to the fall of the slope. Complete as soon as topsoil is placed on the slopes.  The Contractor shall round the top and bottom of the slopes to create a pleasing appearance. Drainage flow lines shall not be disrupted. All equipment performing the placement of 100mm topsoil, or other operations for this project shall be kept clear of wetland areas.  If access into wetlands is required, it shall be done only after approved by the Engineer and shall be performed under close supervision.

Topsoil shall not be placed in heavy rainfall, snowfall, when the soil is frozen or during other conditions detrimental to the work.  Contractor shall keep all roadway surfaces clean of topsoil during hauling and spreading operations.

620-4.01 METHOD OF MEASUREMENT. Add the following: Track walking shall be subsidiary to Item 620(1A) Topsoil Class A, 100 mm Depth.  Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1A) Topsoil Class A, 100mm Depth.  Topsoil for planting beds and any work required to shape or work planting beds shall be considered subsidiary to Item 620(1A) Topsoil Class A, 100 mm Depth, and shall not be measured separately.

620-5.01 BASIS OF PAYMENT.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

620(1)	Topsoil, 100 mm Depth	Square Meter

Section 621
Planting Trees and Shrubs

Special Provisions

621-1.01 DESCRIPTION. Delete this subsection in its entirety and substitute the following: This work shall consist of collecting, furnishing, planting and maintaining trees, shrubs and other plants as shown and scheduled on the Plans.  This work also includes preparation of planting bed areas including furnishing and installing shredded bark mulch.

621-2.01 PLANT STOCK. Delete this subsection in its entirety and substitute the following:  All plants shall be locally grown and shall be true to type and name in accordance with the current edition of Standardized Plant Names, American Joint Committee on Horticultural Nomenclature, except that plant species which are scheduled, but not included in the current edition of Standardized Plant Names, shall be certified by a botanist.  Each bundle, flat, or plant if not bundled, shall be labeled with the scientific name.

Variety and species shall be as scheduled on the Plans.  All trees and shrubs shall be typical of the species or variety and shall, unless otherwise specified, conform to the American Standard for Nursery Stock (ANSI-Z 60.1-1996) of the American Association of Nurserymen (AAN) for type and grade.  Plant stock having severely damaged bark or trunks, broken leaders or main branches, severed main roots, or evidence of disease or injurious insects will be rejected.  Bare root trees and shrubs will also be rejected.

1.	Nursery Stock.

a.	Trees and shrubs furnished from a nursery shall have a fibrous compact root system suitable for the various species and sizes called for on the plans.

b.	Container-grown plants shall be healthy, vigorous, well rooted and established in the container in which they are furnished.  Root mass shall retain its shape and hold together when removed from the container without being root-bound.

2.	Collected Stock.  Field collected plant material shall be plants growing under natural conditions in soils, and in locations the same as the areas where the collected plants will be transplanted. All plants shall be root pruned with sharp instruments prior to being dug and removed from their existing locations.  The root system of collected material shall be at least one third larger than those specified for nursery-grown material.  All heights of field-collected plants shall conform to ANSI Z60.1. The Contractor shall obtain any permits required for collection of plants from natural areas.  The Contractor shall assure material does not dry out during the entire transplanting process.  If material must be stored on site, it shall be heeled in, shaded, and kept moist throughout the root zone to assure it does not dry out.

Willow bundles shall be composed of a mix of willow cuttings from at least two of the following species, with no one species comprising more than 75% of the material used. Material of a single species shall be collected from at least two sources to ensure genetically diverse stock.  Sources shall be located on the western slope of the Talkeetna or Chugach Mountains within 160 road kilometers of the project site.

Feltleaf willow (Salix alaxensis)

Sitka willow (Salix sitchensis)

Barclay willow (Salix barclayii)

Undergreen willow (Salix commutata)

Pacific willow (Salix lasiandra)

Willow cuttings shall be collected prior to leaf out or by April 15 from local sources.  Willow and cottonwood cuttings shall be collected and stored prior to placement in one of two manners.

For cuttings collected before March 15, cuttings and finished bundles shall be stored at -18ºC to -7ºC, wrapped tightly in plastic to retard desiccation of the stems.  Several shovels of clean snow shall be placed on the cuttings, inside the plastic wrap before freezing.  Cut materials shall be wrapped and frozen within four hours of cutting and shall remain frozen until placement.

For cuttings collected between March 15 and April 15, cuttings and finished bundles shall be wrapped loosely in plastic after cutting or constructing and refrigerated at 0ºC to 2ºC until used at the job site.  Cuttings shall not be unrefrigerated for more than four hours after cutting and prior to placement.  Cuttings shall be monitored weekly during storage for mold.  The Engineer will not allow the use of any moldy cuttings or bundles in construction of this project.

Willow stems collected for willow bundles shall be approximately 8 mm to 25 mm diameter and 1.2 m to 2.5 m long.  Buds must be present on the cuttings.  Avoid flower buds (pussy willows).  Cuttings shall be harvested with shearing tools.  No chainsaws shall be used. Willow cuttings shall be kept as noted above until placement.

Stakes shall be pointed 50mm x 50mm x 406mm wooden or willow cuttings.

3.	Balled and Burlapped Plants.

a.	The diameter and depths of balls on balled and burlapped Trees and Shrubs shall be in accordance with ANSI-Z60.1-1996.

b.	All balled and burlapped Trees and Shrubs shall be furnished with a firm ball of earth from the original and undisturbed soil in which the plant was growing.  The ball shall be wrapped with burlap or similar approved material and tightly laced to hold the ball firm and intact.  Any balled and burlapped designated plant material arriving at the planting site with broken or loose balls or of manufactured earth will be rejected.

c.	All plants found to be rootbound by the determination of the Engineer will be rejected.

4.	Substitutions. No substitutions of plant stock will be permitted without written approval of the Engineer.  Request for substitutions for Trees and Shrubs shall be submitted in writing six (6) months prior to installation.

5.	Storage and Packing. All plant material shall be handled and packed in accordance with good nursery practices as required by soil and climatic conditions.  Plants that show signs of improper storage or handling will be rejected.

6.	Inspection.

a.	All planting stock shall be available for inspection in the nursery or collection field before it is dug.  The contractor shall furnish complete and detailed information concerning the source of supply for all plant materials not less than 10 days in advance of digging operations.

b.	Final inspection and acceptance for size of ball or roots, color, absence of defects, and for other requirements will be made at the planting site by the Engineer prior to placing the plants in their permanent positions.

Plant material installed prior to acceptance by the Engineer will be removed, inspected and reinstalled if found acceptable.  If found to be unacceptable, Contractor shall furnish new material, allow inspection, and then install.

621-2.02 FERTILIZER.  Add the following: Fertilizer shall be delivered in moisture-proof containers marked with weight and manufacturer’s guaranteed analysis showing proportions of the chemical ingredients of nitrogen, phosphoric acid, and potassium within a tolerance of +/- 2 percent. A slow release fertilizer 8-32-16 (N-P-K) shall be used with all plant materials early in the first full growing season following installation.  Fertilizer for topsoil installation shall be applied at a rate determined by the Engineer, as described in Section 726, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.  Fertilizer shall be well-watered in immediately after application.

621-2.03 LIMESTONE. Add the following: Limestone shall be applied at a rate determined by the Engineer, as described in Subsection 726, in Table 726-1, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.

621-2.04 MULCH. Replace with the following: Mulch shall be shredded bark mulch.  It shall consist of shredded bark and wood.  Maximum length of any individual components shall be 50mm and a minimum of 75% of the mulch shall pass through a 25mm sieve.  Mulch shall be free of growth or germination-inhibiting ingredients.  The bark mulch shall have the characteristics of retaining moisture, forming a mat not susceptible to spreading by wind or rain, and providing a good growth medium for plants.  Shredded bark may contain up to 50% shredded wood material.  Wood chips are not acceptable.  Bark shall be aged for one-year minimum prior to installation.  The mulch shall not contain resin, tannin, or other compounds in quantities that are detrimental to plant life.  Mulch shall be spread evenly in all planting beds, to a depth of 75mm, as shown on Plans.

621-2.06 STAKES. Add the following:  Stakes shall be installed as shown on Plans.

Add the following subsections:

621-2.08 PLASTIC LANDSCAPE EDGING. Plastic edging shall be 10.16 mm wide heavy-duty polyethylene edging. Install per manufacturer’s specifications, straight, level and secure.

621-2.09 BOULDERS. Boulders shall be placed as shown on the Plans.  The design intent for the boulders is to provide rich form and texture as an integral element in the landscape design.  Their selection and placement shall emphasize their natural beauty and form.  The selection of boulders shall be approved by the Engineer prior to transporting them to the site.  Boulders that were damaged or defaced prior to installation will be rejected on site at the option of the Engineer.  Boulders shall be uniform in color and character with distinct faces and edges.

1.	Boulder Type B:  Boulders shall be minimum 1200mm and maximum 1500mm at their longest dimension.  Their shortest dimension shall be a minimum 900mm.

621-3.02 ADVANCE PREPARATION AND CLEANUP. Add the following:  Areas that receive group plantings shall be laid out as shown on Plans.  Contractor shall mark these areas individually with flags, or other approved methods to delineate planting areas.  Engineer shall approve the shape, size, location and general layout of planting areas before the work may proceed.

Contractor shall stake or mark with other approved methods the location of individual trees within each planting area for approval by the Engineer.

621-3.03 PLANTING. Delete Items 1 and 2 and substitute the following:

1.	Plant Season.

a.	Locally grown: When native species of locally grown trees and shrubs are furnished for the project, they shall be planted between June 1 and September 15.  Trees and shrubs shall be fully leafed-out prior to planting.

b.	Imported and Nursery grown: When plants are shipped in from out of state, or have been container grown in a nursery for at least one year, handling shall be in accordance with nursery recommendations.  Plants imported from out of state shall be planted between May 15 and September 1.

2.	Excavation.

a.	Topsoil shall be kept separate from subsoil and shall be rendered loose and friable.  Any material detrimental to plant growth shall be separated and disposed at approved locations.

b.	Planting pits for trees and shrubs shall be in accordance with the details shown on the Plans.

Delete paragraphs (c.) and (d.)

3.	Pruning. Delete the last two sentences of paragraph b in their entirety.

5.	Placing Plants.

Add the following to paragraph a.: Trees and Shrubs shall be planted as shown on the Plans and as directed on site by the Engineer.

Delete paragraph b. and substitute the following: Balled and burlapped plants, plants in wire baskets or containers shall be handled by the earth ball, container, or basket and not by the plant itself.  Wire baskets, and burlap shall be clipped and laid flat on the bottom of the planting pit as indicated on the Plans.  Containers shall be removed from the site.  The Engineer may reject any plants whose rootballs collapse during planting.

Add the following paragraph: Constructed willow bundles shall conform to dimensions and materials noted as shown on the Plans. Willow bundles shall be prepared and placed as follows:

1.	Construct willow bundles with cuttings pointing in both directions.  Tightly tie willow cuttings together to create a 150-mm diameter bundle.  Tie at 300-mm intervals using untreated hemp twine.

2.	Prepare bundles the same day as the stems are removed from cold storage.  Once prepared, keep the bundles shaded, cool and moist until buried.

3.	Dig a trench into the placed and compacted topsoil to accept the bundle.

4.	Bury the willow bundles until only 8 mm of the bundle is above the soil.  Firmly tamp topsoil into the spaces between the individual cuttings.

5.	After placement but before final burial bundles shall be staked every 450 mm.  Stakes shall be pounded vertically through the center of the bundle and adjacent to where the bundles are tied.  The top 25 mm to 50 mm of the stake shall be left above the bundle.  After staking the bundle shall be buried as noted above.

7.	Wrapping. Delete this paragraph in its entirety.

8.	Staking and Guying. Delete paragraphs a, b, and c in their entirety and add the following:  Contractor shall stake trees as shown on Plans and as directed by the Engineer.  The stakes and wire shall be maintained during construction and the establishment period to prevent damage to the trees.  All stakes and wire shall be removed at the end of the period of establishment.

Add the following subsection:

9.	Certified Arborist.  The Contractor shall retain the services of an arborist certified by the International Society of Arboriculture or the American Association of Nurserymen whose experience and qualifications are acceptable to the Engineer.  The arborist’s resume shall be submitted at least 10 calendar days before the delivery of plant material.  The certified arborist shall oversee quality assurance of trees, their installation and shall inspect trees for health and vigor.  Specifically, the arborist shall carry out the following:

The certified arborist shall inspect plants for health and vigor prior to installation, to assure the requirements of Section 621-2.01 for plant stock, including that the materials are disease free, free of wounds, broken branches, double leaders, co-dominant trunks, or other defects.  Plants that do not meet the standards will be rejected prior to installation.  The certified arborist shall also be responsible for the following:

a.	Inspect the tree planting process to assure that planting techniques meet the specifications of the Contract documents and match standard industry practices.

b.	Inspect the plantings after installation is complete to assure that they are ready to be accepted by the Engineer and ready for the maintenance schedule to begin.

c.	Inspect plantings twice during the growing season during Plant Establishment Period for any needed maintenance, such as watering, pruning, or removal of dead, dying, or untreatable diseased trees.

d.	After acceptance, the arborist shall inspect the trees at least twice during the growing season each year of the Plant Establishment period for any needed maintenance, such as watering, pruning, removal of dead, dying or untreatable diseased trees.

621-3.04 PERIOD OF ESTABLISHMENT. Delete the last sentence and substitute the following: The period of establishment for trees and shrubs shall extend for one complete growing season. One full growing season shall be defined as the period between May 1 and September 30 for the purpose of this Contract.  The work under Section 621 will only be accepted as fully complete for period of establishment requirement purposes, no partial acceptance will be given.  The one full growing season period of establishment starts on May 1st after the acceptance of the work as complete.  Partial growing seasons will not be counted against the one full growing season requirement.

621-3.05 CLEANUP. Add the following: Planted trees, shrubs, and seeded areas shall be kept clean of litter and garbage during the growing season.

621-3.06 PLANT REPLACEMENTS. Delete the last sentence and substitute the following:  Plants shall be replaced following the same details and specifications as used in the original plans. Plants which are dead or dying shall be replaced immediately during the months of June through September.  Plants dead at the end of the growing season shall be replaced at the beginning of the following season.

621-3.07 MAINTENANCE. Delete the paragraph and substitute with the following:  Maintenance includes the care of all Trees and Shrubs during the period of establishment, including the non-growing season.  Specific work includes watering, pruning, weeding, pest control, and protection of planted areas.  At the beginning and end of each growing season, the Engineer and Contractor shall undertake a joint inspection to review conditions and document any changes in maintenance or acceptance of plantings.

1.	Watering. The Contractor shall water all trees and shrubs using the quick coupler system to maintain the plants in a healthy, vigorous growing condition.  The root zone of plants shall be kept moist at all times.

During the germination period for seeded areas (14-21 days), the seed bed shall be kept moist at all times.  To achieve this goal, it may be required to water seeded areas twice daily, depending upon weather conditions during the germination period. Care should be given to apply water at such a rate so as to not erode or wash away seed.  Inspections will be conducted by the Engineer during the germination period following application of seed to verify the application of adequate amounts of water.

Should inspections reveal that an adequate amount of moisture is not being applied to the seeded areas, the Engineer will place the contractor on notice that immediate applications of water be applied and failure to do so will result in a restart of the 60 day maintenance period beginning the day of proper application of moisture.  No additional compensation will be allowed the Contractor for additional applications of water.

If the Contractor continues to fail to apply adequate moisture during the germination period for 5 consecutive days, the Engineer may declare the seeding unacceptable.  The Contractor will be required to reseed areas that have not been kept moist.  Once adequate water is applied the Engineer shall restart the 60-day maintenance period beginning the day of proper application of moisture or reseeding.

2.	Disease Control. The Contractor shall apply pesticides, insecticides, or other disease-control methods as necessary to maintain plant health.  Permission of the Engineer and appropriate permits for the application of insecticides from the Alaska Department of Environmental Conservation must be obtained prior to the application of any regulated products.

3.	Pruning. Prune all plant materials, with appropriate pruning techniques, to remove dead or dying wood and to improve the shape and or vigor of the plants.  Cuts shall not be painted. Pruning of flowering trees shall be scheduled to occur immediately after flowers drop off or decay.  Damaged trees or those that constitute health or safety hazards shall be pruned as directed by the Engineer at any time of the year.  Evergreens are not to be pruned without the approval of the Engineer.

4.	Fertilizing. Trees and Shrubs shall receive an application of fertilizer in accordance with Section 621-2.02 Fertilizer.  The application shall occur between May 15 and June 15 of each growing season following planting.  The fertilizer tablets shall be placed near the root zone in accordance with the fertilizer manufacturer’s instructions.  Fertilizer shall be well-watered in immediately after application.  The Contractor shall notify the Engineer in writing 4 working days prior to applying any fertilizers.  Written notice shall state the time and location of fertilizer application.

TABLE 621-1
MAINTENANCE FERTILIZER SCHEDULE

Plant Type	Fertilizer	Application Rate

Coniferous Trees	8-32-16	34.2 grams per square meter
Deciduous Trees	8-32-16	500 g for each 25 mm of Caliper
Shrubs and Ground Cover	8-32-16	7 grams per square meter.

621-3.08 BOULDERS. Bury base of boulder 100-150mm below finish grade or as directed by the Engineer.

621-4.01 METHOD OF MEASUREMENT. Delete this entire subsection and substitute the following: Measurement of new or transplanted Trees, Shrubs and Perennials, Pay Items 621(1A – 1C) and 621(2A-2F) shall be by the actual number planted and maintained in accordance with the Plans and Specifications, and as accepted by the Engineer.  Furnishing and installing shredded bark mulch, landscape fabric, additional topsoil backfill mix, staking and guying, arborist review, fertilizing, disposal of unsuitable and surplus material, water for maintenance used, and all work required during the one full growing season period of establishment shall not be paid for separately, but shall be subsidiary to Pay Items 621(1A – 1C) and 621(2A-2F).

Measurement of Item 621(8B) Boulder (Type B, 1200 mm) shall be made for each boulder installed.

Measurement of Item 621(9) Willow Bundles shall be by meter in place.

621-5.01 BASIS OF PAYMENT.  Delete second sentence.  Add the following: Partial payments of up to 70% of full amount may be authorized for Items 621(1A –1C) and 621(2A-2F) at the time of acceptance. The balance shall be paid at the completion of the period of establishment.

The accepted quantities will be paid for at the contract price, per unit of measurement, for all labor material and equipment required to furnish and install the pay items listed below and appearing in the bid schedule.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

621(1A)	Tree (Picea glauca – 1800mm Ht.)	Each

621(1B)	Tree (Picea pungens – 1800mm Ht.)	Each

621(1C)	Tree (Prunus maackii - 40mm Cal.)	Each

621(2A)	Shrub (Pinus mugho “Slowmound” – 600mm Ht.)	Each

621(2B)	Shrub (Rosa rugosa – 600mm Ht.)	Each

621(2C)	Shrub (Rosa acicularis – 450mm Ht.)	Each

621(2D)	Shrub (Alnus crispa – 450mm Ht.)	Each

621(2E)	Perennial (Iris setosa – 400mm Ht.)	Each

621(2F)	Perennial (Dicentra spectabilis – 400mm Ht.)	Each

621(8B)	Boulder (Type B, 1200mm)	Each

621(9)	Furnishing and Planting Willow Bundles	Meter

Section 627
Water System

Special Provisions

627-1.01 DESCRIPTION. Add the following: For purposes of these Special Provisions, “AWWU” shall mean the Anchorage Water and Wastewater Utility, Engineering Division, Project Management Section at (907) 564-2785.  AWWU shall be responsible for providing any live-taps required and also final adjustment of fire hydrants.

Work on existing facilities by the Department’s Contractor that will require coordination with AWWU includes the relocation of two (2) fire hydrants, adjustment of one (1) valve box and the adjustment of four (4) sanitary sewer manholes, as shown on the Plans.

This work shall include the coordination, installation, testing, flushing and chlorination or hand cleaning of water systems for acceptance by AWWU.  The Contractor shall also provide as-builts in accordance with the conditions prescribed herein.

627-2.01 MATERIALS. Add the following: All materials used in the construction or adjustment of the Water System shall conform to the Drawings and the 1994 edition of the Municipality of Anchorage Standard Specifications (M.A.S.S.), Division 60.00, and Sections 70.08 and 70.09.

All water main and fire hydrant laterals shall be Class 52, Ductile Iron Pipe unless otherwise noted.  All Ductile Iron and Cast Iron pipe, fittings, and valves installed shall be wrapped with a layer of polyethylene encasement material 8 mm thick and conforming to the latest editions of the ANSI/AWWA A21.5/C105.  The polyethylene encasement shall be installed in strict compliance with the methods described in the latest editions of ANSI/AWWA A21.5/C105 and Ductile Iron Pipe Research Association’s “A Guide For The Installation Of Ductile Iron Pipe.”

CONSTRUCTION REQUIREMENTS

627-3.01 GENERAL. Add the following before the first paragraph: AWWU, through the Engineer, reserves the right to suspend the water system installation at any time if the Contractor fails to meet the requirements set forth herein.  Work will be suspended until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

In those areas where the presence of existing abandoned pipe causes a conflict with new or existing utilities or facilities, the pipe may be removed as a subsidiary item of construction.  All abandoned materials removed and not reused shall become the property of the Contractor, unless specifically addressed otherwise in the contract.

Delete the fifth paragraph and substitute the following:  Prior to removing or disrupting service to fire hydrants, the Contractor shall contact the Anchorage Fire Department, Chief Dispatcher at 267-4950 and Deputy Fire Chief at 267-4935 at least 48 hours in advance of any construction.

Delete the sixth paragraph and substitute the following:  The Contractor shall provide 72 hours written notice to the Engineer, the Anchorage Fire Department, and affected property owners/businesses prior to anticipated mainline flow interruptions.  It shall be the Contractor’s responsibility to coordinate “turn-off” and “turn-on” with the Engineer.

Restore disrupted water service as soon as possible, or make temporary service connections.  Use hoses or other suitable methods.  Any temporary system must be approved by ADEC.

Add the following to the eighth paragraph: Concrete thrust blocks or thrust restraint of the type shown on the plans shall be installed where the pipe line terminates or changes alignment, utilizes a tee, cross, bend, reducer, or similar fitting.  Either poured-in-place or precast thrust blocks are acceptable if the minimum base area is sufficient as shown on the plans.  Concrete for the thrust blocks shall be Class A.  If the Contractor elects to use poured-in-place thrust blocks, all pipe and fittings exposed to concrete shall be double wrapped with 8-mil polyethylene, prior to placement of the concrete.  Poured-in-place thrust blocks shall be cured a minimum of 7 days prior to the application of any hydrostatic loads.

627-3.03 FIRE HYDRANTS. Delete this subsection in its entirety and substitute the following:

Fire Hydrant Relocation. The Contractor shall disconnect the existing fire hydrant assembly at the main and install it at the location shown on the Plans.  The Contractor shall provide a minimum 48-hour advance notification to AWWU for scheduling any live-taps.  The Contractor shall furnish and install a plug w/thrust restraint at existing main location.  An AWWU inspector shall be present during all disconnections and installations of fire hydrants.  The Contractor shall install the gate valve with valve box and the proper length of leg section to provide the desired offset of the fire hydrant from the centerline.  The Contractor shall furnish new ductile iron pipe material for the hydrant leg section.  New fire hydrant legs shall be installed level.  The fire hydrant barrel shall be installed plumb, and the drain plug shall not be removed prior to installation.  The Contractor shall verify that all drain plugs are in place and tightened before acceptance.

Work shall be in conformance with the requirements defined in the 1994 edition of the Municipality of Anchorage Standard Specifications (M.A.S.S.), Section 60.04, and M.A.S.S. Standard Details 60-5, 60-6, and 60-8 with the following exceptions:

1.	All references to tie backs and tie rods shall be replaced with restrained joints.  Tie back rods and/or tie back rod and shackle assemblies will not be acceptable as restrained joints or restraining system for fittings or valves.  Joint restraint shall be EBAA Iron “MEGALUG” or Romac Industries “GripRings”, or equal.

2.	The dimension on M.A.S.S. Standard Detail 60-8, from the vertical face of the fire hydrant to the center of the guard post, shall be increased from 600mm to 900mm.

Fire hydrants will be adjusted to final grade by the AWWU Operations and Maintenance Division.  Contractor shall provide AWWU with a minimum of 72 hours notice, excluding non working days, to coordinate fire hydrant adjustment.  Contractor shall be responsible for access to the hydrant location and all trench excavation, dewatering, shoring, backfill and compaction operations prior to, during, and after the fire hydrants are adjusted by AWWU personnel.

The Contractor shall paint in 50mm black lettered stencils, the direction and distances to the nearest 30mm the distance to the valve box on the face of the fire hydrant directly below the bonnet flange.

627-3.04 VALVES. Add the following: Valves shall be installed where shown on the plans. The interiors of all valves shall be cleaned of all foreign matter before installation.  If the valve is at the end of the line, it shall be plugged prior to backfilling.  The valve shall be inspected by a representative of AWWU, in the open and closed positions to ascertain that all parts are in good working condition.

627-3.05 VALVE BOXES. Add the following:

Adjustment of Valve Box: All construction shall conform to the requirements defined in the 1994 edition of the Municipality of Anchorage Standard Specifications (M.A.S.S.), Sections 60.03 and 70.08, and M.A.S.S. Standard Detail 60-4.  All locations where adjustment of valve box is required shall be excavated to the top of the valve.  Extreme care must be exercised when working around existing AWWU water valves and mains.  Visual inspection of the work by an AWWU inspector shall be required. The Contractor will be responsible for coordination of inspection with AWWU.  Provide a minimum 24 hours notice.

Add the following Subsections:

627-3.08 SALVAGEABLE MATERIALS. Unless specifically addressed otherwise in these special provisions, all existing water valves, tees, bends, or conduit (including ductile iron pipe) removed but not reinstalled and declared “salvageable materials” shall become the property of the Contractor.

627-3.09 FINAL ACCEPTANCE. It shall be the Contractor’s responsibility to protect and maintain all valves, valve boxes, and fire hydrants in an operable condition during all phases of construction.

Prior to construction activities, the Contractor shall schedule a field inspection with AWWU and the Engineer to witness and document the condition of the existing valves, valve boxes, and fire hydrants to insure they are in working order.  Cleaning or repair to the valves or valve boxes prior to adjustment will be accomplished by AWWU at no cost to the Contractor.

Failure of the Contractor to schedule and participate in the valve, valve box, and fire hydrant inspection shall result in the Contractor forfeiting all rights to claim that the valves were damaged prior to Contactor construction activity.

If AWWU finds a valve, valve box, or fire hydrant damaged or otherwise rendered inoperable at any time after the inspection as described above, the Contractor shall repair the damage at his expense.

The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a pre-final inspection of the project.  This inspection will be performed in the presence of the Engineer, AWWU, and the Contractor.  Copies of a list of deficiencies, if any, indicated by this inspection will be furnished to the Contractor for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and an acceptance inspection will be performed.

627-4.01 METHOD OF MEASUREMENT. Add the following to  2. Fire Hydrant Adjustment: Coordination and payment for AWWU hydrant vertical adjustment is subsidiary.

Section 640
Mobilization and Demobilization

Standard Modification

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

Section 641
Erosion, Sediment, and Pollution Control

Special Provisions

641-1.01 DESCRIPTION. This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02 DEFINITIONS.

1.	BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

2.	ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and included in the project plans and specifications. It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

3.	Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

4.	HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

5.	NOI. Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.

6.	NOT. Notice of Termination of coverage under the NPDES General Permit.

7.	NPDES General Permit. The General Permit for Stormwater Discharges from Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires a SWPPP prior to ground-disturbing activities for the project.

8.	SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS. Submit 3 copies each of your SWPPP and HMCP for approval no less than 5 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days. Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP must be signed by you and the Engineer in accordance with the NPDES General Permit.

Submit your signed NOI (use EPA Form 3510-9) to the Engineer no later than 10 working days before you intend to commence ground-disturbing activities.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP. Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing over 2 hectares. The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private. The plan must also incorporate all the requirements of the Project permits.

Have the SWPPP prepared under the direction of and sealed by a professional engineer currently registered in the State of Alaska. Include all requirements of the NPDES General Permit.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities. Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641 3.01 CONSTRUCTION REQUIREMENTS.

Do not begin ground-disturbing work until you are notified by the Engineer that 48 hours have passed since the NOIs were mailed to the EPA and DEC.

Post at the construction site, the

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	name and phone number of your local contact person, and

3.	location of a SWPPP available for viewing by the public.

Comply with all requirements of the NPDES General Permit, implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms. Perform all fueling operations in a safe and environmentally responsible manner. Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections. Prior to start of construction conduct a joint on-site inspection with the Engineer and the professional engineer who stamped the SWPPP to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

a.	During construction, inspect the following at least once every 7 calendar days and within 24 hours of the end of a storm event exceeding 13 mm in 24 hours (as recorded at or near the project site).

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections. During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 13 mm or greater. Monthly inspection requirements may be waived by the Engineer until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports. Prepare and submit, within 3 calendar days of each inspection, a report with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) of personnel making the inspection.

c.	The date of the inspection.

d.	Observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

f.	Incidents of non-compliance.

Where a report does not identify any incidents of non-compliance, include certification that the facility is in compliance with the SWPPP and NPDES General Permit. Sign the report in accordance with Part VI. Standard Permit Conditions of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP.

Retain copies of the SWPPP, and all other records required by the NPDES General Permit, for at least 3 years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

1.	storm event or other circumstance that threatens water quality, and

2.	inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within 7 days.

Stabilize all areas disturbed after the seeding deadline within 7 calendar days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT (use EPA Form 3510-7) to the Engineer

1.	when the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

2.	when the construction activity Operator (as defined in the NPDES General Permit) has changed.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

1.	pursue work required by the approved SWPPP,

2.	respond to inspection recommendations and/or deficiencies in the SWPPP, or

3.	implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01 METHOD OF MEASUREMENT. Items 641(1) and 641(3) will not be measured for payment.

Items 641(2) and (4) will be measured as specified in the Contract or Directive authorizing the work.

Item 641(5) Silt Fence will be measured by the Meter installed complete and in place.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1) and (2) or items 641(1), (3), and (4)

1.	Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract to install and maintain all temporary erosion, sedimentation, and pollution control measures.

3.	Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain temporary erosion, sedimentation, and pollution control measures in accordance with the original approved SWPPP and HMCP.

4.	Item 641(4) Temporary Erosion and Pollution Control Amendments. At the prices specified in the Directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures. All work paid under this Item shall be shown as amendments to the original approved SWPPP or HMCP.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution Control Administration	Lump Sum

641(2)	Temporary Erosion and Pollution Control	Contingent Sum

641(3)	Temporary Erosion and Pollution Control	Lump Sum

641(4)	Temporary Erosion and Pollution Control Amendments	Contingent Sum

641(5)	Silt Fence	Meter

(08/15/01)M78

Section 642
Construction Surveying and Monuments

Special Provisions

642-3.01 GENERAL. Delete the seventh paragraph.

(3/31/00)R252M98

642-3.01 GENERAL. Delete item number 10 after the heading “Perform the following:” and substitute the following:

10.	Necessary cross sections at retaining wall locations.  Cross section data shall be taken at 5.0 meter intervals and given to the Engineer 10 days prior to ordering retaining wall materials.  At that time, the Engineer will verify the plan quantity and make any necessary adjustments to the wall size, design or configuration.

11.	All other surveying and staking necessary to complete the project.

(5/8/00)R255M98

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

1.	Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work.

(3/31/00)R252M98

Section 643
Traffic Maintenance

Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan.  Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.

643-2.01 MATERIALS. Add the following:

17.	Flexible Markers. Refer to subsection 606-2.01 Materials.

(01/29/02)R222M98

Standard Modifications

Add the following Subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Category | Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed Category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements.  Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://www.fhwa.dot.gov/.)

Submit documentation of compliance to the Engineer before using devices on the project.

(09/29/00)M91

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Standard Modification

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. In the fourth paragraph, third sentence, change “crossings” to “closures”.

(06/25/99)M 80

Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES. Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: Remove all obstructions greater than 100 mm above the nominal foreslope grade at the end of each continuous work shift.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1
ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

Add the following:

1.	Monday through Friday 6:00 am to 8:00 am and 4:00 pm to 6:30pm.

2.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

Lane restrictions, if allowed shall be conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 0.4 kilometers of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 20 minute stopped delay, 80 vehicles, or 0.8 kilometers of traffic detained, will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Add the following:

For construction adjacent to Waldron Park, the Contractor shall coordinate construction activities with the Boys and Girls Club of Anchorage director of athletics, Tony Lopez at 249-5449 a minimum of 72 hours ahead of construction activity.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

(01/29/02)R222M98

643-4.01 METHOD OF MEASUREMENT. Add the following: Providing mail-outs, notices, displays for open house and public meetings, and providing weekly notices with updates will not be measured for payment.

(8/13/99)R102M98

Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following:

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion/ET 2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.

(01/29/02)R222M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

Section 644
Services to be Furnished by the Contractor

Special Provisions

644-2.01 FIELD OFFICE. Delete this subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15. The following office requirements shall be met:

1.	A minimum of 100 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Three (3) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 1600 meters of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

Add the following:

7.	Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

8.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

644-4.01 BASIS OF PAYMENT. In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators.”

(06/25/99)M 81

Section 646
CPM Scheduling

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.   The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.   60-Day Preliminary Schedule.

(3/12/01)R261M98

Section 647
Equipment Rental

Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1), Wide Pad Dozer, 48 kW Minimum will be paid on a contingent sum basis at the rate of $125/hour.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)	Wide Pad Dozer, 48 kW Minimum	Contingent Sum

(11/12/98)R15M98

Add the following Section:

Section 650
Site Amenities

Special Provision

650-1.01 DESCRIPTION. This work shall consist of furnishing, constructing and placing Benches, Trash Receptacles, Scenic Overlook & Boardwalk, Fixed Wood Bollards, Removable Steel Bollards, Interpretive Displays, Location Pylons w/ Trail Map Signs, Bicycle Racks and Wood Park Sign in conformance with the Plans and Special Provisions.

650-1.02 APPLICABLE ACCESSIBILITY STANDARD. Americans with Disabilities Act (ADA) Accessibility Guidelines for Buildings and Facilities.

650-1.03 SUBMITTALS. Conform to Subsection 106-1.01.

The following submittals shall be provided by the Contractor for the Engineer’s review and approval.  The Contractor will not be allowed to begin construction until all submittal requirements are satisfied and found acceptable to the engineer.  Changes or deviations from the approved submittals must be re-submitted for approval.  No adjustments in contract time will be allowed due to incomplete submittals.  At least 15 working days prior to initiating the work, the Contractor shall submit to the engineer:

1.	Manufacturer’s installation instructions and product data if used

2.	Shop drawings showing all connections and dimensions

3.	Samples of vinyl print mounted behind a single piece of non-glare acrylic

650-1.04 QUALIFICATIONS.

A.	Qualifications of Installers:

1.	All welding shall be performed by welders currently certified by the American Welding Society (AWS).

B.	Codes and Standards: Comply with "Code for Welding in Building Construction" of the American Welding Society, latest edition.

C.	The Printer/Producer of interpretive panels shall be able to demonstrate a minimum of 3 years of production and fabrication of graphic products intended for use in an outdoor environment.  The Printer/Producer must provide samples of previous work.  The samples shall be vinyl prints mounted behind a single piece of non-glare acrylic.  Samples provided by the Contractor will be used as the standard against which the panels for this project will be judged for acceptance.  The samples must be accepted before beginning work on the interpretive panels.

650-2.01 MATERIALS.

All equipment for submission of "or equals" must match quality and function of specified equipment.  If the "or equal" equipment occupies a different footprint, the Contractor is responsible for the redesign and submittal of shop drawings of the areas as well as any increase in costs, as calculated by the Engineer.

The following products or approved equals shall be installed where indicated on Project Drawings.  Materials substituted as "or approved equal," must be similar with same characteristics, and functions as materials specified or Contractor will assume responsibility for all related costs of construction.  The Contractor shall notify the Engineer at least 72 hours prior to picking up materials.

1.	Bench. shall be one of the following or approved equal:

a.	Arcata series, 1.9 meter backed bench, with arms, polysite seating, embedded footing by Landscape Forms (Rep: Hartman Ltd - 206-842-1846), Steelsites Series Model NRB-6, 1.8 meter backed bench with armrests, in ground mounting by Victor Stanley, Inc (Rep: Division 10 - 907-345-1633), Plaza Series Model PL-2, 1.8 meter backed bench with armrests, embedded footing by FairWeather Site Furnishings (1-800-323-1798)

2.	Trash Receptacle. shall be one of the following or approved equal:

a.	Scarborough, vertical strap, top opening, black liner, embedded footing by Landscape Forms (Rep: Hartman Ltd - 206-842-1846), Ironsites S-42, standard lid, holds 121L. can, embedded pedestal mount, by Victor Stanley Inc. (Rep: Division 10 - 907-345-1633), Model TR-12, flat top, embedded footing by FairWeather Site Furnishings (1-800-323-1798).

3.	Scenic Overlook and Boardwalk.

a.	Wood for Scenic Overlook and Boardwalk. Shall be as shown on the Plans.  Wood shall be all weather wood.  Wood species shall be Douglas Fir, Western Hemlock or Hem-Fir unless otherwise specified.

i.	Dimensional. Dimensional lumber and timbers are shown on the plans in nominal dimensions, i.e.; 50 mm x100 mm, indicating surfaced four sides (S4S) or planed material.  Use classification for light framing shall be Construction Grade.  Manufacturing classification shall be Dressed (Surfaced) Lumber.  Size classification shall be Nominal Size Designations of Boards, Dimension, and Timbers.

b.	Preservative for Scenic Overlook and Boardwalk.

i.	Above Ground Wood Preservative. Brown preservative with active ingredient of 6.411 kilograms per cubic meter alkaline copper quat treatment.  Color shall be per Subsection 650-3.01 and Section 708 or as approved by the Engineer.  Finish with 2 coats non-gloss wood finish.

ii.	End Cut Preservative for Treated Wood. Per wood treatment manufacturer’s recommendations.  Color to match preservative pressure treatment color.

c.	Grating for Scenic Overlook and Boardwalk. Grating shall be as specified in Section 712-2.16 Fiberglass Grating

d.	Piling for Scenic Overlook and Boardwalk. Piling shall be 100mm Schedule 40 pipe meeting the requirements of Section 715.

4.	Wood Posts & Fixed Wood Bollards.

a.	General. Wood Posts and Fixed Wood Bollards shall be as shown on the Plans.  Wood for posts and Fixed Wood Bollards shall be all weather wood.  Wood species shall be Douglas Fir, Western Hemlock or Hem-Fir unless otherwise specified.

i.	Dimensional. Dimensional lumber and timbers are shown on the plans in nominal dimensions, i.e.; 50 mm x100 mm, indicating surfaced four sides (S4S) or planed material.  Use classification for light framing shall be Construction Grade.  Manufacturing classification shall be Dressed (Surfaced) Lumber.  Size classification shall be Nominal Size Designations of Boards, Dimension, and Timbers.

ii.	Rough Cut. Unless otherwise indicated, rough cut lumber and timbers are shown on the plans in actual dimensions, e.g.; 50 mm x100 mm, indicating rough cut material. Use classification shall be Structural Lumber, No. 2 Grade or Better. Manufacturing classification shall be Rough Lumber.  Size classification shall be Rough Dry Sizes.

b.	Preservative.

i.	Above Ground Wood Preservative. Brown preservative with active ingredient of minimum 6.411 kilograms per cubic meter alkaline copper quat treatment.  Color shall be per Section 708 or as approved by the Engineer.

ii.	Below Ground Wood Preservative. Preservative with active ingredient of minimum 9.617 kilograms per cubic meter alkaline copper quat treatment.

iii.	End Cut Preservative for Treated Wood. Per wood treatment manufacturer’s recommendations.  Color to match preservative pressure treatment color.

5.	Removable Steel Bollard. shall be as detailed on the Plans and as specified under General materials for Steel, Galvanizing and Fasteners.

6.	Interpretive Display.

a.	Interpretive Materials. shall be color products printed on continuous, full-size premium cast vinyl, mounted behind a single piece of non-glare Acrylic and installed in the frame and support structure shown on the Plans.  The graphic product shall be printed using an electrostatic, 4-color digital process with ultraviolet durable inks, not less than 300 dots per inch.  The graphic product shall be an ultraviolet (UV)-stable product with inks guaranteed as color-true after exposure to sunlight for a period of not less than 5 years in vertical exposure.  Colors shall be as provided by the Department’s Representative.  The Department’s Representative will coordinate color-correction with the Contractor’s printer.  The Department’s Representative must approve the colors in writing prior to final printing.  After printing, the Contractor shall have the products mounted behind a single piece of non-glare Acrylic.  The panels must be water and air-tight.

b.	Interpretive Display Graphic Information. shall be available from the Department’s Representative in electronic format.  Product is a Quark Xpress file.  Contractor is responsible for coordinating with the fabricator of the panels including the production of the graphics and being mounted behind a single piece of non-glare Acrylic.

c.	Polycarbonate protective cover for Interpretive Display Panels. Polycarbonate protective cover shall be UV and abrasion-resistant vertical glazing.

d.	Plywood for Interpretive Display. Plywood shall be marine grade plywood with fill finish.  Exposed surfaces shall be painted per Section 708.

e.	Wood Posts for Interpretive Display. shall be as specified under Wood Posts and Fixed Wood Bollards.

7.	Location Pylon. shall be as detailed on the Plans and as specified under Wood Posts and Fixed Wood Bollards.

8.	Trail Map Signs for Location Pylon.

a.	Substrate for Trail Map Signs. Substrate shall be 0.080 aluminum, alloy 5058 H38, treated with chromate conversion coating conforming to ASTM B 449 as described in Section 730

b.	Facing for Trail Map Signs. Premium cast vinyl, rated by the manufacturer for a minimum effective performance lifespan of 5 years in vertical exposure.

c.	Copy for Trail Map Signs. Lettering and artwork to be produced using one or more of the following methods deemed most suitable for crisp and efficient reproduction of original artwork:

i.	Cut vinyl:  computer-driven automated plotters, preferred method for all vector-based graphics and text over 19mm in height.

ii.	Digital Printing:  computer-driven digital imaging device used to fine-detail graphics and small text directly to premium cast vinyl substrate.  To be rated by the manufacturer for a minimum performance lifespan of 5 years in vertical exposure.

iii.	Screen printing:  image transfer to premium cast vinyl using vinyl specific inks and a 230 mesh screen (typical).  Inks must adhere to premium cast vinyl substrate and be rated by the manufacturer for a minimum performance lifespan of 5 years in vertical exposure.

d.	Digital files for Trail Map Signs. (including all graphics and text) will be provided by the Department’s Representative in Adobe Illustrator format (.ai)

9.	Bicycle Rack. shall be one of the following or approved equal:

a.	SRE / G-7 Loop Style Bike Rack, 60 mm O.D. Pipe, 157 mm long, holds 7 bikes, standard embedded post mount, Hot-Dip Galvanized, by Pilot Rock Park Equipment (1-800-762-5002), Model FSC-LBR7P High Style Bike Rack by Upbeat, Incorporated (1-800-325-3047), TB 7-E-G Thunderbolt Series by Creative Pipe (1-800-644-8467).

10.	Wood Park Sign. Shall use a section of glu-lam beam material as detailed on the Plans and finished as described in Section 708 Paints.  Wood Park Sign posts shall be as described under 4. Wood Posts & Fixed Wood Bollards, of Subsection 650-2.01 Materials.

11.	Concrete, General. An approved, pre-mixed sacked concrete conforming to Section 501, Class W.

12.	Backfill, General. Selected Material, Type A conforming to Subsection 703-2.07.

13.	Steel, General. Unless otherwise specifically permitted, all steel shall conform to ASTM Specification A36 (Standard Specification for Carbon Structural Steel), and shall be clean new stock, free from rust and pitting.  Tube steel shall conform to ASTM A500.

14.	Galvanizing, General. Conform to AASHTO M111/ASTM A123 (Standard Specification for Zinc [Hot-Dip Galvanized] Coatings on Iron and Steel Products), or AASHTO M232/ASTM A153 (Standard Specification for Zinc Coating [Hot-Dip] on Iron and Steel Hardware).

15.	Fasteners, General. Commercial quality and type of nails and screws as required to securely hold all members in place in accordance with National Design Specifications.  Nails shall be hot dipped galvanized.  All other fasteners shall be corrosion resistant.  Fasteners in pressure treated wood shall be hot dipped galvanized.  Nails and wood screws below grade in pressure treated wood shall be stainless steel.

16.	Paint, General. Shall be as specified in Subsection 650-3.01 Finishes, General and Section 708 Paints.

650-3.01 CONSTRUCTION REQUIREMENTS.  Locations shown on the Plans for Site Amenities are approximate.  The Engineer will field locate Site Amenities at the time of construction.

Finishes, General. Unless otherwise specified, schedule finishes as follows:

| Treatment and Coating Schedule |  |  |  |
| --- | --- | --- | --- |
| Item | Treatment | Finish | Color |
| Fixed Wood Bollard, Wood Fence Posts, Wood Sign Posts, and Location Pylons | Below Ground Wood Preservative | Oil stain | Russet Brown |
| Park Sign Posts | Below ground wood preservative | Oil stain | Russet Brown |
| Bench Post, Trash Receptacle, Steel Railing, and Decorative Fence Panels & Top Rails, Interpretive Display Frames and mounts. | Steel | Polyester powder coat | Turquoise Blue RAL Color 5018 |
| Elevated Trail | Steel | 3 Part Epoxy System | Turquoise Blue RAL Color 5018 |
| Scenic Overlook & Boardwalk railings, toe boards, railing posts and other visible wood components | Above ground wood preservative | Exterior non-gloss | Cedar tone |
| Scenic Overlook & Boardwalk headers and joists | Below ground wood preservative | Oil stain | Cedar tone |
| Light Poles | Steel | Polyester Powder Coat | Sherwin Williams SW6179 Artichoke |

1.	Paint shall be delivered in sealed containers with labels legible and intact.  Remove dirt, grease, oil and other construction debris prior to painting.  Insure that surfaces to be painted are even, smooth, sound, clean, dry, and free from defects affecting proper application.  Metal surfaces to receive paint shall be corrosion free.  Apply per manufacturer's recommendations.  Apply paint material evenly without runs, sags, or other defects.  Work each coat into the material being coated at an average rate of coverage recommended by the manufacturer.  Cover surfaces completely to provide uniform color and appearance.  Remove all paint, stain, or other finish material where it has spilled or spattered.

2.	Polyester powder coating application shall be prepared through a five step process to provide an acceptable finish:

a.	Steel shot blasting

b.	Phosphate conversion coating, rinsing and sealer coating

c.	Preheating steel surfaces

d.	Application of polyester powder by the electrostatic spray process

e.	Oven curing at 400 degrees F for 10 minutes for a thickness of 8-10 mils

Benches, Trash Receptacles, and Bicycle Racks.

1.	Installation of benches, trash receptacles, and bike racks shall comply with Manufacturer’s specifications for in-ground mount and shall be in locations as shown on the Plans.  Contractor is responsible for acquiring manufacturer’s specifications and submitting for review and approval.

2.	Excavation and backfill for in-ground mounts shall conform to the requirements of Section 204 and the details on the Plans.

Scenic Overlook & Boardwalk.

1.	Construction and installation of Scenic Overlooks and Boardwalks shall be as shown on the Plans.

2.	Pile driving shall conform to the requirements of Section 505(6)

Fixed Wood Bollard.

1.	Installation of fixed wood bollards shall be as shown on the Plans.

2.	Excavation and backfill for fixed wood bollards shall conform to the requirements of Section 204 and the details on the Plans.

Removable Steel Bollard.

1.	Installation of Removable Steel Bollards shall be as shown on the Plans.

2.	Excavation and backfill for removable steel bollards shall conform to the requirements of Section 204 and the details on the Plans.

3.	All welding shall be in accordance with “Code for Welding in Building Construction” of the most current American Welding Society D1.1.

Interpretive Display.

1.	Installation of Interpretive Displays shall be as shown on the Plans.

2.	All welding shall be in accordance with “Code for Welding in Building Construction” of the most current American Welding Society D1.1.

3.	Excavation and backfill for wood posts shall conform to the requirements of Section 204 and the details on the Plans.

4.	Wood Posts for Interpretive Displays shall be installed as per the Plans.  Wood posts shall be plumb and level erected and evenly spaced with allowable tolerances for panel installation.  Posts shall be installed to provide a continuous level top surface at the same elevation.

Location Pylon

1.	Installation of Location Pylons shall be as shown on the Plans.

2.	Excavation and backfill for Location Pylons shall conform to the requirements of Section 204 and the details on the Plans.

Trail Map Signs for Location Pylon.

1.	Installation of Trail Map Signs shall be as shown on the Plans.

Wood Park Sign.

1.	Installation of Wood Park Sign shall be as shown on the Plans.

650-4.01 METHOD OF MEASUREMENT.

Measurement of Benches, Trash Receptacles and Bicycle Racks shall be by individual unit, measured by the actual number complete-in-place and accepted.  Excavation and embankment for Benches, Trash Receptacles and Bicycle Racks outside the limits shown on the Plans will be measured for payment only if said activity is directed by the Engineer.  Excavation and backfill required for Benches, Trash Receptacles and Bicycle Racks will not be measured for payment.

Measurement of Interpretive Displays shall be by the actual number of Interpretative Displays complete-in-place and accepted.  Excavation and embankment for Interpretative Panels outside the limits shown on the Plans will be measured for payment only if said activity is directed by the Engineer.  Excavation and backfill required for Interpretative Displays will not be measured for payment.

Installation of Map Trail Signs shall be measured by individual count of Trail Map Signs complete-in-place.

Measurement of Fixed Wood Bollards, Removable Steel Bollards, Wood Park Signs and Location Pylons will be by the individual unit complete and in place.  Sign material installed on Item 650(41) Location Pylon will be measured under Section 615.  Excavation and backfill for Scenic Overlook & Boardwalk, Fixed Wood Bollards, Removable Steel Bollards, Wood Park Signs and Location Pylons will not be measured.  Piling for Item 650(13) Scenic Overlook and Boardwalk shall be subsidiary to this Item.  Concrete for Pay Item 650(20) Removable Steel Bollard will not be measured.

There shall be no measurement of Scenic Overlook & Boardwalk.

650-5.01 BASIS OF PAYMENT. The accepted quantity of Benches, Trash Receptacles and Bicycle Racks, and Interpretive Displays will be paid for at the contract unit price per unit of measurement for the type specified completed in place, and listed below excluding all clearing, grubbing, topsoil, and aggregate base course which shall be paid for separately at contract unit prices.

No separate payment shall be made for Trail Map Signs for Location Pylons.  Payment shall be included under Section 615 Standard Signs.

The accepted quantity of Fixed Wood Bollards, Removable Steel Bollards, Wood Park Signs and Location Pylons will be paid for at the contract unit price per unit of measurement for the type specified, completed in place.

Scenic Overlooks & Boardwalks shall be paid at the contract lump sum price.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

650(3)	Bench	Each

650(7A)	Trash Receptacle	Each

650(13)	Scenic Overlook & Boardwalk	Lump Sum

650(19)	Fixed Wood Bollard	Each

650(20)	Removable Steel Bollard	Each

650(38)	Wood Park Sign	Each

650(40)	Interpretive Display	Each

650(41)	Location Pylon	Each

650(50)	Bicycle Rack	Each

Add the following Section:

Section 652
Creek Restoration

Special Provisions

652-1.01 DESCRIPTION. The work under this section consists of supplying all materials, labor, equipment, supplies, handling, and storage to construct a root wad revetment, as shown on the Plans.  This work also includes constructing, maintaining and restoring to original condition a creek access corridor.

652-1.02 CONTRACTOR QUALIFICATIONS. The Contractor’s stream restoration supervisor shall have a minimum of 3 years experience performing creek restoration work.  Contractor’s stream restoration supervisor must have completed a minimum of four (4) projects performing creek bank restoration in Alaska.  The Contractor shall supply evidence of compliance with these requirements before beginning creek restoration work.  The Contractor responsible for creek restoration shall attend the project Pre-Construction meeting.

The Contractor shall expect 2 site visits from public regulatory agency personnel during the course of the work.  The Contractor shall anticipate a 1 hour delay for each visit.  Any delay caused by these site visits shall be considered subsidiary to Item 652(2) Root Wad Revetment.

652-1.03 CREEK ACCESS. Creek access for restoration work shall be from International Airport Road.  A temporary access permit has been provided for the Contractor to allow access across private property adjacent to International Airport Road.  See Appendix A – Parcel P-3 for permit.  Contractor shall access the private property crossing through the existing fence gate at this location.  Contractor shall coordinate access with the property owner.  This gate shall remain locked at all times and only be opened for the Contractor to enter or leave the temporary access drive.  Any clearing within the creekside greenbelt shall be the minimum required for stream access drive construction.  The Contractor shall provide a creek access plan to the Engineer for approval prior to clearing the creek access and constructing the temporary drive.  After approval of the stream access plan the Contractor shall stake the limits of clearing for the stream access within the temporary construction easement and the greenbelt for approval by the Engineer and stream restoration supervisor.  Contractor shall provide and install a fence gate across the temporary creek access drive for the existing fence located at the east edge of Tract B-1, Campbell Creek Commercial Park Subdivision, as shown on the temporary access permit.  After completion of creek restoration work the temporary creek access drive shall be removed and the area returned as nearly as possible to its original condition.  The fence gate installed for the temporary creek access drive shall be removed and the fence shall be restored to original condition.

652-2.01 MATERIALS. Use materials that conform to the following:

1.	Selected Material, Type A. As described in Section 703 Aggregates.

2.	Selected Material, Type D. As described in Section 703 Aggregates, as modified.

3.	Logs. Logs shall conform to the dimensions shown on the plans.  Header and footer logs and root wads shall be sound (not rotted or hollow) and be either birch (Betula papyrifera), spruce (Picea glauca or Picea sichensis), or hemlock (Tsuga hetrophylla or Tsuga mertensiana).  Log ends shall be cut clean and square and branches shall be trimmed to within 75 mm of the trunk.  Log collection shall be the responsibility of the Contractor.  All logs shall be staged at a Contractor-supplied yard prior to construction and are subject to approval of the Engineer.

4.	Boulders. Boulders shall conform to the dimensions shown on the Plans and shall meet the requirements of Riprap, Subsection 611-2.01.  Rounded boulders may not be used.  All boulders shall be staged at a Contractor-supplied yard prior to construction and are subject to approval of the Engineer.

5.	Rebar. Rebar shall conform to the dimensions shown on the drawings and shall be ASTM A615, Grade 60, deformed.

6.	Topsoil. As described in Section 726 Topsoil Aggregates, as modified.

7.	Willow Bundle. As described in Section 621 Planting Trees and Shrubs, as modified.

8.	Coir Log. As described in Section 727 Soil Stabilization Material, as modified.

9.	Coir Log Fabric Wrap. As described in Section 727 Soil Stabilization Material, as modified.

10.	Seed. As described in Section 724 Seed, as modified.

CONSTRUCTION REQUIREMENTS

652-3.01 ROOT WAD REVETMENT. Construction shall be as shown on the Plans.  All construction shall be in accordance with the permits issued for this project.  All work shall be done in non-flowing waters isolated from Campbell Creek with jersey barriers or similar structures as approved by the Engineer placed continuously from above the upper limits of construction to below the lower limits of construction.  Silt fence shall be installed between the work area and the jersey barriers.

Water may be pumped from the work area at the option and expense of the Contractor.  This step is not required if the Contractor can perform his operations within permit requirements without pumping.  If water is pumped from the construction site, it shall be discharged to uplands and shall not cause erosion or damage to the ground as it flows away from the pumping operation.  The Contractor shall submit a plan for this diversion to the Engineer for review prior to beginning work.

Logs, root wads, and boulders shall be stockpiled for inspection by the Engineer before construction begins.  Materials shall be organized by size prior to construction.  Larger logs shall be used for footer logs, larger root wads and rocks shall be used in the middle portion of the curve.  Backfill shall be Type D classified fill or an organic free unclassified material approved by the Engineer.  Backfill shall be placed in maximum of 450 mm lifts and compacted by a minimum of four passes of a small bulldozer.  Willow bundles and coir fiber rolls with fabric wrap shall be placed as shown on the Drawings and as described in Section 621 of these Special Provisions.  Installation of any topsoil as shown on the drawings shall be as described in Section 620 Topsoil.  Root wad revetment backfill material above the level of the bottom of Campbell Creek shall meet the requirements of Select Material, Type D or other suitable organic-free material approved by the Engineer.  Below the level of the bottom of Campbell Creek backfill material shall be Select Material, Type A.  Topsoil shall be used to bring the installation area to finish grade if insufficient salvaged organic material is not available.

652-4.01 METHOD OF MEASUREMENT.

652(2) Root Wad Revetment. By the meter for the completed installed root wad revetment.  Furnishing, collecting, transporting, and placing the individual logs, root wads, boulders, Select Material, Type A, and coir logs in soil fabric wrap shall be included in the per meter payment for the completed installed revetment.  Pay limits shall be as shown on the Plans.

Work and materials required for the temporary creek access shall not be measured.

652-5.01 METHOD OF PAYMENT. Payment for Item 652(2) Root Wad Revetment shall include full payment for creek access construction, maintenance and restoration, jersey barriers used to divert flow, dewatering (if provided), excavation, placement of logs, root wads, boulders, and coir logs in soil fabric wrap, disposal of surplus material, site grading, salvaging topsoil and all other items subsidiary to construction of Item 652(2) Root Wad Revetment.

Work and materials required for the temporary creek access shall be subsidiary to Item 652(2) Root Wad Revetment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

652(2)	Root Wad Revetment	Meter

Section 660
Signals And Lighting

Special Provisions

660-1.01 DESCRIPTION. Replace the first paragraph with: This work consists of the furnishing and installation of all necessary labor and equipment to provide a fully functioning multi-use trail illumination system. This work shall consist of furnishing and installing, modifying, removing or salvaging one or more trail or roadway lighting systems including load centers, luminaires, poles, foundations, junction boxes, conduit and appurtenances all as required by the plans and as specified.

660-1.02 REGULATIONS AND CODE. Add the following to the second paragraph after the last sentence: Completed assemblies made up of materials and individual components shall also be Listed or Labeled.

Add the following paragraph: The Contractor shall be responsible for obtaining all permits and inspections as required by the MOA, Building Safety Division Policy 006 Electrical Inspections Within Rights of Way.

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS. Delete item number 1 that follows the first paragraph, and add the following:  The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.  Paint color chips shall be submitted and approved prior to acceptance of poles and lamps.

Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-1.05 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS. Delete this subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned in accordance with the following specifications.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When you begin work, the Engineer will notify you and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility. Therefore, before starting work on the project, you should inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with you. If you begin work before providing the Engineer with an inventory, you waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, and photoelectric controls operate the lighting systems. The State will pay for all electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin repair work on all systems within one hour of notification by the Engineer. If you do not complete the repairs, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due you. When you work on a traffic signal system, print a record of all work performed in the diary found in each controller cabinet. Make sure each entry includes

1.	The dates and times you began and completed your work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to periods during normal working hours as specified in Section 643, Traffic Maintenance. During the shutdowns, use flag persons to control traffic. Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day you retire the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever you reduce their clearance from the traveled way is less than 1.8 meters.

During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches in accordance with the following:

1.	For overhead signals, maintain 5.3 m to 5.8 m of clearance between the traveled way and the bottom of each signal.

2.	For side mounted signals, maintain 2.7 m to 3.4 m of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	Check the horizontal angle to the side mounted far right signal from the center of the farthest left through lane at the stop bar. When the angle exceeds 20 degrees, move this signal to an overhead location. With two or more through lanes, center one signal head over each lane. With one through lane and protected-permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane, otherwise install the relocated signal 2.4 meters to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 2.1 m to 2.7 m between the traveled way and the bottom of each pedestrian signal.

7.	Aim all signal heads in accordance with subsection 660-3.08, Installation Details.

When no longer required, salvage all original and Department provided equipment in accordance with the plans and subsection 660-3.21, Salvaging or Reusing Electrical Equipment, and remove all other materials used in the temporary systems from the project.

660-2.01 EXCAVATING AND BACKFILLING. In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

Add the following after the fourth paragraph: Backfill the first 150 mm lift with material free of rocks exceeding a 25 mm maximum dimension.

660-2.04 POLES, STEEL PEDESTALS AND POSTS. Delete the first paragraph and replace with the following: All trail lighting poles shall be designed in accordance with the requirements of the current “Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals,” as published by the American Association of State Highway and Transportation Officials, for 160 km/h wind velocity, with 1.3 gust factor.  The subject standards shall be designed to support the luminaires as shown on the drawings.   The poles shall be designed to be suitable for direct bury applications.

Add the following paragraphs: Relocate existing standards per the plans in a manner that maintains their existing condition. Replace standards damaged or destroyed by your operations at your own expense. When you relocate galvanized standards with rusted or scarred surface areas, repair these areas in accordance with subsection 660-2.15, Galvanizing.

During backfill and compaction, all direct buried poles shall be held plumb.

660-2.05 CONDUIT. Add the following: The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid.  After you pave the final asphalt course, however, the Engineer will not allow trenching.

Delete item 1 after the first paragraph and replace with the following: For conduit runs between trail lighting luminaire junction boxes, electrical conductors that are pre-installed in HDPE conduit will be allowed.  Conduit runs between junction boxes and load centers or luminaire poles, and any above grade conduit shall be galvanized rigid.  Risers into junction boxes shall all be galvanized rigid.  Provide galvanized rigid elbows and transition couplings for HDPE conduit.

660-2.06 JUNCTION BOXES. Delete the second paragraph and substitute the following: Only use pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the plans.  All junction box lids shall be cast iron.

660-2.08 CONDUCTORS. Add the following to item 2 “Power Conductors and Cables:” Furnish cables consisting of three #8 AWG conductors with conductor insulation colored black, white, and red. Furnish cables with three conductors larger than #8 AWG with conductor insulation colored black, white, and red, or with all black conductor insulation with printed numbers identifying each conductor per ICEA method 4.

660-2.09 WIRING. Delete the first paragraph and add the following: Install signal cables with no splices in them. Install illumination cables without splices, except when adding an electrolier to the midst of a circuit. In addition, do not splice conductors within cabinets, junction boxes, signal heads, and luminaires.

Crimp spade type terminals onto all conductors that attach to terminal blocks. When reusing cabinets, replace terminal blocks that lack enough terminals. Make the wiring within cabinets neat, and cable conductors together with self-clinching nylon ties.

660-2.10 FUSED SPLICE CONNECTORS.

Add the following: Retrofit reused poles with new tap wires, and fused disconnect kits.

660-2.11 BONDING AND GROUNDING. Add the following after the first paragraph: Install a 19 mm by 3.0 m copper clad ground rod under “P” type controller cabinet foundations.

Add the following after the second paragraph:

All hardware, including insulated throat grounding bushings, ground rods, and ground rod clamps shall be UL listed. Grounding bushings shall be the threaded type.

Where wire is pulled and reinstalled in existing conduits, the bare No. 8 AWG copper wire shall also be installed. Where conduits are installed for future conductors, the above mentioned copper wire may be omitted. (3/30/00)R215M98

660-3.16 LUMINAIRES. Add the following: Furnish high-pressure sodium lamps with a rated life of 24,000 hours based on 10 hours per start.

The luminaire manufacturer shall furnish light fixtures free of substances (such as paint) that affect luminaire photometric performance.

Furnish luminaires with a wire way that meets National Electrical Code requirements to install three #10 AWG conductors with type XHHW insulation from the pole to a terminal block located in the luminaire.

Furnish luminaires that provide the uniformity specified (or better) in the arrangements listed on the plans.  Use a lighting program that calculates illumination levels according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 1983.  Furnish the Engineer with the manufacturer’s current electronic photometric data in Illuminating Engineering Society (I.E.S.) format to verify illumination levels and uniformity ratios.  If electronic data is unavailable, derive the illumination level at the dimmest point by straight-line interpolation between the isolux lines on the manufacturer’s current published photometric data charts. To calculate the uniformity ratio, divide the average illumination level by the illumination at the dimmest point.

Luminaire Type Definitions:

Q:	Mast-arm mount with Type V, Quadrate distribution.

660-3.21 SALVAGING OR REUSING ELECTRICAL EQUIPMENT. Add the following: Transport all signal equipment, if any, from the project to the Municipality of Anchorage, Traffic Signal Electronics Shop. Allow maintenance personnel to select the equipment they would like to salvage, and dispose of all remaining equipment. Contact the Municipality of Anchorage, Traffic Signal Electronics Shop; provide one-week notice of your intent to deliver salvaged materials.

660-5.01 BASIS OF PAYMENT. Add the following: The lump sum prices paid for the items included in the Contract includes full compensation for all work involved in furnishing and installing, assembling, modifying, and removing the components of the systems shown on the plans. This includes: completing all excavation to install poles, conduits, and junction boxes, backfilling and compacting trenches, removing and replacing improvements, installing sumps under junction boxes, and pulling conductors. The lump sum prices paid also include full compensation for all work specified in the Standard Specifications and Special Provisions. This includes: getting all materials approved; preparing as-built plans, maintaining the electrical systems, adjusting junction boxes to grade, making all splices, labeling all conductors, completing all tests, and delivering salvaged electrical equipment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

660(28)	Trail Lighting System Complete	Lump Sum

Section 661
Load Centers

661-2.01 MATERIALS. Add the following paragraphs:

Load center ‘A’ shall contain a seven-day programmable timer that is active when the timer selector switch is in the “ON” position. The timer shall be a double pole single throw, 40A, 277V rated contactor. Powered by a self-starting synchronous motor, capable if being set for different ON-OFF times each day of the week. Removable ON-OFF trippers shall make possible a minimum ON period of one hour and a minimum of two hours between OFF operation and the next ON. The 7-day timer shall have a spring driven reserve sufficient to operate the time switch contacts for at least 24 hours after a power failure. On restoration of power, time switch shall transfer to synchronous motor drive and automatically rewind reserve.

Trail lighting system load centers shall contain a multi-pole, two-position control switch to provide selection of photocell/timer operation.  Switch positions shall be labeled “ON”, “BYPASS”.  In the “ON” position of the switch, The timer will be in series with the photocell such that the trail lights will only illuminate when called for by both the timer and the photocell. In the “BYPASS” position of the switch, the timer will be removed form the circuit and the lights will be operated by the photocell control.

The switch and timer shall be located inside the load center, accessible only through one of the lockable doors.

Section 670
Traffic Markings

Special Provisions

670 3.01 CONSTRUCTION REQUIREMENTS. Under item 4 Methyl Methacrylate Pavement Markings, delete the last sentence in the first paragraph and substitute the following: Do not apply striping to the new asphalt until the asphalt has cured for the duration listed below and at the Engineer’s discretion.

Stone Mastic Asphalt Concrete	30 days

All others				15 days

Under item 4 Methyl Methacrylate Pavement Markings. , delete the second paragraph and substitute the following: Apply Methyl Methacrylate marking material with truck mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in liters.

Add the following under item 4. before the third paragraph:  A film test strip will be required at the beginning of each striping shift, and when there is a change in the asphalt type. In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion. (09/04/01)R221M98

Under item 4. Methyl Methacrylate Pavement Markings.  delete the first sentence in the fifth paragraph and substitute the following:  Apply markings for lane lines, edge lines, and center lines at a yield thickness of 2.3 mm (1 liter will yield a 2.3 mm thick stripe 100 mm wide by 4.348 m in length).

670 3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

2.	Width of Stripe. The width shall not vary more than 6 mm in width in any 15 m longitudinal run from the Plan quantity.

670-4.01 METHOD OF MEASUREMENT. Add the following after Item 4:

5.	Liter Basis: The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in liters.  The Department will limit the final quantity to 115% of the Plan quantity.

670-5.01 BASIS OF PAYMENT. Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B) and no separate payment shall be made.

Add the following: The Department will pay the contract unit price for the volume of Methyl Methacrylate accepted by the Engineer up to a maximum of 115% of the quantity shown in the Plans.  All Methyl Methacrylate material over-runs above 115% of the plan quantity shall be paid for by the Contractor at no expense to the Department.

(06/05/02)R246m98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10B)	Methyl Methacrylate Pavement Markings	Liter

Section 702
Asphalt Materials

Special Provisions.

702-2.01 ASPHALT CEMENTS. Add the following: Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T-53 and ASTM D5801 assigned to each grade.

Performance Graded Asphalt Cement

Property	Standard	PG 52-28	PG 58-28	PG 64-28

Softening Point	AASHTO T-53	(none)	49oC	52oC

Toughness (min)	ASTM D5801	(none)	12.4 N-m	12.4 N-m

Tenacity (min)	ASTM D5801	(none)	8.5 N-m	8.5 N-m

(9/18/00)R244M98

Section 703
Aggregates

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE
Percent Passing By Weight

| Sieve Designation | Grading D-1 |
| --- | --- |
| 37.5 mm |  |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 50-79 |
| 4.75 mm | 35-58 |
| 2.36 mm | 20-47 |
| 0.600 mm | 10-26 |
| 0.300 mm | 6-19 |
| 0.075 mm | 0-6 |

(2/28/00)R117M98

Standard Modification

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material.

(06/25/99)M 82

Add the following subparagraph:

4.	Selected Material, Type D. shall consist of sand, gravel and rock and shall contain no muck, peat, frozen material, roots, sod or other organic or deleterious matter.  The maximum rock size shall be 200mm with a maximum of 20% by weight passing a 0.075mm sieve.

Section 708
Paints

Special Provisions

708-1.01 General Requirements. Add the following paragraph: This special provision covers all steel structures associated with this trail unless such structures are hot dip galvanized (except for fasteners), temporary structures or otherwise exempted in writing.  Also included are all wood items.  In particular, items to be painted includes, but is not necessarily limited to, all metal components and fasteners for elevated trail, metal fence components and fasteners, interpretive panel frame and supports, park signs, location pylons, bollards, and scenic overlook and boardwalk.

708-2.01 PAINT FOR STEEL. Replace the first three items with the following:

1.	Prime Coat: Sherwin Williams Zinc Clad IV, Tnemec Tneme-Zinc 90-97 or approved equal zinc rich epoxy primer.

2.	Intermediate Coat: Sherwin Williams Recoatable Epoxy Primer (B67 Series), Tnemec S.T. Typoxy N27 or approved equal.

3.	Top Coat: Sherwin Williams Hi-Solids Polyurethane (B65-300 Series), Tnemec Eudura Shield II 1075 or approved equal.  Top coat color shall match existing Campbell Creek Trail bridge near Piper Street.

Add the following:

4.	Polyester Powder Coat: Shall be TGIC Polyester powder coat, RAL #5018 Turquoise Blue, or approved equal meeting US Federal Standards. Material shall be as follows:

Chemical Type:	Polyester
Particle Size:	30-60 microns average
Specific Gravity:	1.2-1.7
Cure Cycle:	400F-10MINS Peak Metal Temperature (TGIC)

Gloss @ 60 Degree:	Available from 20-80+ Degrees

Theoretical Coverage:	110-160 square feet per pound at 1 mil film Thickness:	2mils primer     4 mils top coat for fence & light

poles

2mils primer 6-8 mils for furniture

708-2.02 PAINT FOR TIMBER. Replace Paragraph with: For all wood except Wood Park Sign glu-lam beam and Scenic Overlook & Boardwalk, coating shall be alkyd flat stain Color Shield 4000 #63-138 Russet by Preservative Paint Company; Russet by Pittsburg Paint Company; or Olympic Russet by PPG Architectural Finishes, Inc.  Scenic Overlook & Boardwalk finish coat shall be oil based, cedar toned exterior non-gloss wood finish.

Park sign gluelam beam shall be stained with light brown stain and coated with clear exterior polyurethane.  Letters shall be painted with gloss black exterior paint.

Section 712
Miscellaneous

Special Provisions

Add the following Subsection:

712-2.16 FIBERGLASS GRATING. Grating used on the elevated trail shall be pultruded vinyl ester resin (VEFR) equal to Safe-T-Span I-4015 as manufactured by Fibergrate Composite Structures Inc., 38mm I-4000 custom grating by Morrison Molded Fiberglass Co. (MMFG) or approved equal.

Grating shall be manufactured from thermally cured pultruded structural load and tie bar components using a UV resistant synthetic veil on all exposed surfaces. The grating shall be provided with a recessed tie bar design and a grit top surface for maximum skid resistance.

The grating shall be an assembled and bonded notched tie bar system to provide both a mechanical and bonded intersection. Center to center spacing of load rails shall be 25.4mm. Open space between load bars shall be 10.16mm. Approximate weight shall be 0.84 kg per square meter.  Submit shop drawings for approval.

Section 716
Structural Steel

Special Provisions

716-2.03 HIGH TENSILE STRENGTH BOLTS. Add the following paragraphs:

4.	Bolt, Nut and Washer Finish: Hot-dip Zinc Coating, ASTM A153, Class C.

Section 722
Bridge Railing

Special Provisions

722-2.02 FENCE.

Steel tubing	ASTM A500, Grade B

Steel Post and cap	ASTM A500, Grade B

Steel Bar and plate	ASTM A500, Grade B

Section 724
Seed

Special Provision

724-2.01 DESCRIPTION. Add the following:

The Contractor shall submit to the Owner’s Representative, 10 working days prior to application, a certification tag for the seed mix in this Contract, depicting species, proportion by weight, percent purity, and percent germination.  The certification tag shall come from the specified seed mix and be removed from the unopened bags in the presence of the Owner’s Representative. Tags from bags already opened before coming on-site will not be accepted.

724-2.02 MATERIALS. Delete Table 724-1 in its entirety and substitute the following tables:

TABLE 724-1
SEED REQUIREMENTS

Schedule A – Riparian Seed Mix (Application Rate: 48.8 kg/ha)

GERMINATION	GERMINATION

NAME	PERIOD	PURITY	RATE	RATE/HECTARE

“Alyeska” Polargrass

(Arctagrostis latifolia “Alyeska”)	14 days	95%	94%	4.8 kg

“Arctared” Red Fescue

(Festuca rubra “Arctared”)	14 days 	95%	85%	14.6 kg

“Norcoast” Bering Hairgrass

(Deschampsia beringenis “Norcoast”) 14 days 	85%	90%	9.8 kg

American Sloughgrass

(Beckmania syzigachne)	14 days	95%	95%	4.8 kg

Smooth Brome

(Bromus inermis var. Manchar)	14 days 	75%	80%	7.2 kg

Cotton Grass

(Eriophorum spp.)	14 days	75%	80%	2.5 kg

Water Sedge

(Carex aquatilis)	14 days	85%	80%	2.5 kg

Beaked Sedge

(Carex rostrata)	14 days	85%	80%	2.5 kg

TABLE 724-2

SEED REQUIREMENTS

Schedule B – Unmowed Seed Mix (Application Rate: 48.8 kg/ha)

GERMINATION	GERMINATION

NAME	PERIOD	PURITY	RATE	RATE/HECTARE

“Arctared” Red Fescue

(Festuca rubra “Arctared”)	14 days 	95%	85%	19.7 kg

Tufted Hairgrass

(Deschampsia caespitosa)	14 days	90%	75%	14.6 kg

American Sloughgrass

(Beckmania syzigachne)	14 days	95%	95%	7.3 kg

Alpine Bluegrass ‘Gruening’

(Poa alpina ‘Gruening’)	14 days 	95%	95%	7.2 kg

Section 726
Topsoil

Special Provisions

726-2.01 TOPSOIL. Replace item (2.) with the following:

2.	Topsoil shall contain not less than 5 percent and no greater than 15 percent organic matter by dry weight as determined by ASTM T-6.

Delete the gradation table in the third paragraph and substitute the following:

Sieve Size	Percent Passing (by Weight)

12.5 mm	100
4.75 mm	95-100
1.18 mm	64-90
0.075 mm	30-60
Organic Content	5%-15%

Delete last sentence in second paragraph and substitute the following:

The Contractor shall submit to the Engineer, 10 working days prior to final placement, a soil analysis for particle size, nutrient content and organic content, before any topsoil shall be accepted for this project.  The Engineer may test the topsoil at any time to verify compliance with the topsoil analysis.  If the supplied topsoil does not meet specifications in this section, the Contractor shall supply new topsoil of a quality required to meet the section standards.

Delete the fertilizer requirements (not the limestone requirements) as stated in this subsection and substitute the following:

Nitrogen	50 – 75 kg per hectare
Phosphoric Acid	112 – 165 kg per hectare
Potassium	121 – 200 kg per hectare

Section 727
Soil Stabilization Material

Special Provisions

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

1.	Virgin/Recycled Wood Fiber, Paper Cellulose Fiber Mulch, or Blended Wood-Paper Mulch.

Mulch shall consist of specially prepared wood fiber processed to contain no growth or germination inhibiting factors. The mulch shall be manufactured and processed in such a manner that the fibers will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry. The mulch shall be of a texture such that it can be applied uniformly to the soil surface. Mulch shall not create a hard crust upon drying and it shall have moisture absorption and retention properties as well as the ability to hold grass seed in contact with the soil.

The mulch shall be shipped in packages of uniform weight (plus or minus 5%) bearing the name of the manufacturer and the air-dry weight content.

The mulch shall be dyed a suitable color to facilitate inspection of the placement of the material.

A commercial tackifier shall be used on all seeded areas where mulch is applied. The amount added will be as recommended by the manufacturer.

727-2.02 MATTING.

2.	Jute Mesh Fabric:  Delete Subsection in its entirety and replace with the following:

1. 	Matting shall be a pervious fabric of yarn of unbleached and undid jute fibers woven into a uniform pattern with distinct and measurable openings.

2. 	Matting shall be totally biodegradable within 2 years after placement, capable of absorbing more than 5 times its weight in water and suitable for protecting slopes as steep as 1 horizontal to 1 vertical.

3. 	Edges of the cloth shall be salvaged to prevent the outer yarn from pulling away from the cloth.  Matting shall meet the mechanical and physical properties listed below:

| Matting Property (1) | Test Method | Value |
| --- | --- | --- |
| Dry Tensile Strength, Warp, N. | ASTM D-4632 | 1335 min. |
| Wet Tensile Strength, Warp, N. | ASTM D-4632 | 556 min. |
| Tensile Elongation, Warp, % | ASTM D-4632 | 10 |
| Strands per Meter, Warp | ASTM D-3775 | 62 |
| Strands per Meter, Weft | ASTM D-3775 | 45 |
| Yarn Count per Width, Warp | n/a | 78 min. |
| Yarn Count per Width, Weft | n/a | 42 min. |
| Matting Property (1) | Test Method | Value |
| Mass per Unit Area, g/sq. m | ASTM D-3776 | 475 |
| Opening Area, % | COE CW 002215 | 60 to 65 |
| Water Velocity, ft./sec, (1.5H:1V slope) | n/a | 2.44 m/sec min. |

Notes:

1. 	Minimum Average Roll Values.

2. 	Erosion control matting manufacturer shall provide a letter certifying that its erosion control matting meets the specified requirements.

Add the following Subsection:

727-2.04 COIR LOG. Log material shall consist of the following:

Fiber:	100% mattress grade coconut (coir) fiber, 7.44 kg per meter minimum.

Netting:	100% coconut (coir) fiber yarn, mesh opening approximately 50 mm, mesh tied at junctions, tensile strength per yarn 244 N dry, 178 N kg wet.

Description:	Manufactured from 100% coconut (coir) fiber, the log shall be a machine fabricated cylinder, encased in 100% coconut (coir) fiber netting.  Fiber shall be packed tightly into netting.  Netting mesh shall have mesh junctions tied to prevent misalignment.  Use only coir logs specifically for stream bank reclamation.

Section 730
Sign Materials

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

(2/29/00)R81M

Standard Modification

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.

(06/25/99)M 83

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(2/29/00)R81M

Appendix A
Permits

Appendix B
Erosion And Sediment Control Plan

Appendix C 
Construction Surveying Requirements

Appendix D
Materials Certification List