PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004 STANDARD SPECIFICATIONS

# SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	Funding for this project is contingent upon approval of the Capital Budget

2.	This project has an Illumination Price Adjustment item.  See subsection 660-3.09 of these Special Provisions.

3.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

4.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective June 2004.

b.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements.

- Standard Specifications for Highway Construction 2004.  ($25.00)

- Alaska Test Methods Manual (Lab & Field), 2004 Edition.  ($25.00)

- 1)	High Tower Phase II Foundations and Geotechnical Report

  - Design computations – Quantites

3)	Current ROW Plats.

5.	Utility agreements pertaining to the disposition of utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

6.	The Department has an approved environmental document addressing concerns and commitments, and  it is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

7.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

SECTION 101

DEFINITIONS AND TERMS

## Special Provisions

101-1.03 DEFINITIONS.  Add the following definition:

NON-FROST SUSCEPTIBLE.  Material that contains 6 percent or less passing the No. 200 screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 3 inch material.  (11/29/01)R1M98

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Special Provision

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent

SECTION 105

CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES.  Add the following:  Request locates from the utilities having facilities in the area.  Use the locate Call Center for the following utilities:

Locate Call Center Local 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar Anchorage School District ACS Alyeska Cable AT&T Alascom, Inc. Anchorage Water & Waste Water Utility Chugach Electric Association DOT Street Lights, State of Alaska Enstar Natural Gas GCI Communications Marathon Oil Corporation Matanuska Electric Association Matanuska Telephone Association MFS Technologies, inc. Municipality of Anchorage Municipal Light & Power Phillips Petroleum

Call the following utilities and agencies directly:

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

The Contractor shall bear the responsibility for changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in subsection 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required before utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

- Under Item 642(3) Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.  (05/31/01)R3M98

Specific coordination requirements for specific utilities are included below:

The Contractor shall be required to give each utility 15 calendar days advanced written notice of relocation work to begin.

1.	Chugach Electric Association, Inc. (CEA).  CEA has existing buried and overhead primary secondary circuits within the Minnesota Drive (MD), Seward Highway/Huffman Road (SH/HR) corridors.  Some of these facilities are located within easements outside of the highway right-of-way (ROW) and others are located within the MD and SH/HR rights-of-way.  None of CEA's facilities require relocation.  Before CEA starts any load center service installation work the Contractor shall install the new load center; the Department of Labor and Workforce Development (ADOL) shall inspect and accept (tag) the new load center.

CEA will disconnect service to existing load center "F" near the new load center designated "RASPBERRY" that will replace load center "F".  CEA will extend the disconnected service to serve the new load center "RASPBERRY".  Load center RASPBERRY will be located at Raspberry Road Station R 90+75, 70-feet left.

CEA will extend service to new load center designated "W100TH" at Minnesota Drive and West 100th Avenue.  Load Center W100TH will be located at Minnesota Bypass Station M1 204+40, 206-feet left.

CEA will extend service to new load center "HUFFMAN" at Seward Highway and Huffman Road.  Load Center HUFFMAN will be located at New Seward Highway S0 529+11, 290-feet right.

CEA will extend service to new load center "TURPIN" at the junction of Glenn Highway and Turpin Road.  Load Center TURPIN will be located at Glenn Highway Station GL 132+93, 256 feet right.

The Contractor shall notify CEA by telephone or in writing at least 14 calendar days before the load center installations and inspection will be complete, to arrange for CEA’s service connection work and allow 15 calendar days for service connection work to be completed.

The CEA contact is Michael Tullius, Supervising Engineer - Distribution Improvements Design, who can be reached by telephone (907) 762-4610 and by US Mail at P.O. Box 196300, Anchorage AK 99519-6300.

2.  	Matanuska Electric Association (MEA).  MEA has existing buried and overhead primary and secondary circuits within the Glenn Highway (GH) corridor.  Some of these facilities are located within easements outside of the highway right-of-way (ROW) and others are within the Glenn Highway corridor.  None of MEA’s facilities require relocation.  Before MEA starts load center service installation work the Contractor shall install the new load centers; the Department of Labor and Workforce Development (ADOL) will inspect and accept (tag) the new load centers.

MEA will disconnect service to existing load centers near the new load centers designated "EAGLE-1" and "EAGLE-2" replacing the disconnected load centers.  MEA will extend the disconnected services to serve the new load centers.

Load Center "EAGLE-1" will be located at Station GH 261+24, 362 feet left.

Load Center "EAGLE-2" will be located at Station GH 275+55, 189 feet left.

The Contractor shall notify MEA by Fax at least 14 calendar days before the load centers installation and inspection will be complete, to arrange for MEA’s service connection work and allow 15 calendar days for service connection work to be completed.

The MEA contact is Jim Hartley, Real Estate & Properties Officer, who can be reached by telephone (907) 689-9200 and by facsimile at (907) 689-9630.

3.	Municipal Light & Power.  (ML&P).  ML&P has existing buried and overhead primary and secondary circuits within the Muldoon Road (MR) and Glenn Highway (GH) Corridors.  Some of these facilities are located within easements outside of the highway right-of-way (ROW) and others are within the ROW.  None of ML&P’s facilities require relocation.  Before ML&P starts any load center service installation work the Contractor shall install the new load center; the Department of Labor and Workforce Development (ADOL) will inspect and accept (tag) the new load center.

ML&P will disconnect service to existing load center-D located at GL 132+40, approximately 142 feet right.

In addition ML&P will extend new service to load center designated "OILWELL".  Load Center "OILWELL" will be located at Muldoon Road Station M 110+05, 90-feet right.

Load Center "BOUNDRY" located at Muldoon Road Station M 92+60, 94 feet left.  Load Center "BONIFACE" located at B 110+10, 60 feet right will be reused and may be de-energized and reenergized as required by contacting ML&P 4 calendar days before the date it is to be de-energized or reenergized.

The service request for new load center "OILWELL" has been submitted to ML&P.

The Contractor shall request the service to the existing load center ”TURPIN” located at Glenn Highway station GL 132+40, 142 feet right to be disconnected by ML&P, a minimum of 7 calendar days before the disconnection is required.  (Note: the new load center ”TURPIN” located at Glenn Highway Station GL 132+85, 260 feet right will be served by Chugach Electric Association).

The Contractor shall request electrical service from ML&P for load center “OILWELL” a minimum of 30 calendar days before the service connect is required.  Notify ML&P by telephone or in writing at least 14 calendar days before the load centers installation and inspection will be complete, to arrange for ML&P’s service connection work and allow 15 calendar days for service connection work to be completed.

The ML&P contact is Kevin Flemming, Line Extension Coordinator, who can be reached by telephone (907) 263-5212 and by facsimile at (907) 263-5804.

105-1.15 PROJECT COMPLETION.  Delete the last paragraph and substitute the following:  When physical work and cleanup provided for under the Contract is found to be complete, except for work specified under subsection 618-3.04, Maintenance of Seeded Areas; and subsection 621-3.04, Period of Establishment; subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve the Contractor of obligations under the Contract.  (02/06/02)R237M98

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION.  Modify the first paragraph, Item 4., after: “DOLWD” add: and State Department of Revenue.

105-1.17 CLAIMS.  Add the following Add the following:  Appeals to the superior court under AS 36.30.685 must be filed in the third judicial district.  (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, before award of the contract.

Steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States.  The definition of “manufacturing process” is smelting or subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting or other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrape, pig iron, and processed, pelletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.  (02/07/05)S 13

106-1.02 LOCAL MATERIAL SOURCES.  Add the following under Item 2. Inspection and Acceptance:  In compliance with 30CFR46.11, have the Operator of the sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for the Engineer’s personnel (non-miners) before their beginning operations in the surface mine.  Offer the training at each surface mine that the Contractor will be using to supply processed aggregates.  A competent person must provide the training according to the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (05/01/02)R262M98

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

# Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES.  Add the following:  Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in according to the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of site outside the project limits or not previously permitted, affected by the Contractor’s operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using site outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Provide information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from the Contractor.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following:  If water for a construction purpose is required from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.  (05/29/02)R7M98

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and

Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

# Training Utilization Report		Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, noncompliance with these requirements is grounds for withholding of progress payments.  (01/22/02)S 80

SECTION 108

PROSECUTION AND PROGRESS

## Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1.  A progress schedule, and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order in which the work will be carried out and the contemplated dates on which the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple-shift work in the CPM Schedule.  If revisions to the proposed CPM Schedule are required, make them promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the Contractor’s schedule, or upon request of the Engineer.  Use the schedule for coordination and monitoring of work under the contract including activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.  (12/13/02)R261M98

Add the following to the second paragraph:  Provide the Engineer with written documentation showing that the poles have been ordered within two weeks after the shop drawings have been approved and returned to the Contractor by the Department.

SECTION 109

MEASUREMENT AND PAYMENT

## Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Under subtitle Electronic Computerized Weighing System item (1) add the following to the end of the first sentence:  “, CD, or a USB device.”

109-1.05 COMPENSATION FOR EXTRA WORK.  Delete the first sentence of the second paragraph of sub-item a. of item 3. equipment, and substitute the following:  The regular hourly rental rate is the adjusted monthly rate for the basic equipment plus the adjusted monthly rate for applicable attachments, both divided by 176, and multiplied by the area adjustment factor specified on the adjustment maps for the Alaska - South Region.  (10/23/02)R14USC02

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of subsection 105-1.16.

###### Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract.  Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.  The following definitions will apply.

- Broker.  A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF).  The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment.  The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself.  To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work.  Other relevant factors will be considered.  The determination of CUF is made by the Engineer after evaluating the way in which the work performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE).  An enterprise which is a for profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department according to 49 CFR, Part 26.

- DBE Key Employee.  Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts.  Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer.  A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification.  For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report.  Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer.  A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a

regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount.  A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document of the required Good Faith Efforts under subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid.  Each bidder must register with the Civil Rights Office annually according to §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award.  The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment.  Written commitments from DBEs to be used on the project.  The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report.  Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation.  Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal.  If accepted by the Department, this lower DBE utilization

becomes the new DBE Utilization Goal.  If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer.  At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work.  The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in subcontract, purchase order or service agreement with that DBE.

- DBE Replacement.  If the Engineer approves a DBE replacement, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended according to subsection 120-3.02.

- DBE Utilization Goal.  The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that cannot be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document of the following actions constitutes insufficient Good Faith Effort.

- Consideration of subcontractable items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) before bid opening.  It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder cannot achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to active DBEs listed for a given region in the Department's most current DBE Directory at least seven calendar days before bid opening.  The bidder must give the DBEs no less than five days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor.  Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- The bidder may reject non-competitive DBE quotes.  Allegations of non-competitive DBE quotes must be documented and verifiable.  A DBE quote that is more than 10.0% higher than the accepted non DBE quote will be deemed non-competitive, provided the DBE and non DBE subcontractor quotes are for the exact same work or service.  Bidders must have a non DBE subcontractor quote for comparison purposes.  Such evidence shall be provided in support of the bidder’s allegation.  Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non DBE subcontractor and payments received by the non DBE subcontractor during the execution of the Contract shall be consistent with the non DBE's accepted quote.  This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding.  Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration.  Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration.  The bidder must exercise such an opportunity within three calendar days of notification it has failed to meet the requirements of this subsection.  As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The DBE Liaison Officer will make the decision on reconsideration.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder.  The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work.  Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer according to this Section.  CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function.  In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO before submitting a bid to a contractor for DBE trucking.  The DBE trucking firm must demonstrate that it owns trucks (proof of title and/or registration) to be credited for work and that operators are employed by the DBE trucking firm.  A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker.

(This does not affect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work will be performed with the DBE’s own equipment.  Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department.  The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska.

Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- Subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control business administration, accounting, billing, and payment transactions.  The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, according to AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE.  Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal.  The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF.  Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE.  Under no circumstances shall the Contractor take action against the DBE firm until the Engineer has made a final determination.  The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE.  In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended according to items c through h of subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that cannot be replaced.

120-4.01 METHOD OF MEASUREMENT.  The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials according to 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.  This shall include DBE trucking firms certified as a subcontractor and not a broker.  Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value.  The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department.  The DBE joint venture partner will be responsible for performing of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.

Unsatisfactory work may result in disqualification of the Contractor from future bidding under subsection 102-1.13 and withholding of progress payments consistent with subsection 109-1.06.  (11/17/00)S 33

# SECTION 501

# Structural Concrete

Special Provisions

501-1.01 DESCRIPTION. Add the following: This work shall also consist of construction of cast-in-place concrete retaining walls and concrete pile caps, as shown on the Plans.  This work will also include the construction of a cast-in-place concrete headwall, as shown on the Plans.

Excavation and backfill required for the cast-in-place retaining walls shall done according to Section 205.

501-2.01 MATERIALS. Add the following: Reinforcing steel shall conform to the requirements of Section 503.

Concrete surface treatments shall conform to the requirements of Section 514.

501-3.01 PROPORTIONING. Under 1. Determining Proportions and Batch Weights., delete the first sentence and substitute the following: Submit a mix design developed in accordance with ACI 211 and 301, Section 4 to the Engineer for approval.

(7/6/99)R37M98

501-4.01 METHOD OF MEASUREMENT. Delete the fourth paragraph.

Add the following:

Square Yard.  By the square yard of wall face.  The vertical height of each section measured on the outer face from the bottom of the lowermost face elemet to the top of the wall.  Reinforcing steel and other items included in the cast-in-place concrete retaining wall will be subsidiary to Item 501(15) Cast-In-Place Concrete Retaining Walls.

501-5.01 BASIS OF PAYMENT. Add the following: Payment for cast-in-place concrete retaining walls will be made under Item 501(15) Cast-In-Place Concrete Retaining Walls.

Payment for Item 501(15) Cast-in-Place Concrete Retaining Walls will be full compensation for labor, equipment and materials required for construction of the wall, complete and in place.  Structural excavation, temporary shoring, reinforcing steel, insulation board, aesthetic fascia, and graffiti protection required for cast-in-place walls will not be paid for separately, but will be subsidiary to Item 501(15) Cast-in-Place Concrete Retaining Walls.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

501(15)	Cast-In-Place Concrete Retaining Walls	Square Yard

SECTION 504

## STEEL STRUCTURES

## CONSTRUCTION REQUIREMENTS

Special Provision

504-3.01 FABRICATION.  In subsection 8, Welding, replace item e in the second paragraph with the following: e.	Name and qualifications of NDE technicians.

504-3.02 ERECTION.  Add the following:

10.	Defects Repair.  From the results of the weld inspection of existing high tower 69, the Engineer will order one of three options:  reuse the pole as is, repair and reuse the pole, or replace the pole.  If ordered, repair defects directed by the Engineer according to the following Defects Repair procedure.

  - Grind out defective welds and cracks one-inch beyond the ends of the defect or crack.

  - Complete welding according to sub-subsection 504-3.01.8, Welding.  Use filler metals compatible with the metals used to fabricate the pole, which are listed in the following summary:

    - Top tube section	ASTM A595, Grade A

    - All other tube sections	ASTM A572, Grade 65

    - Hand hole frame	ASTM A572, Grade 65

    - Pole base plate	ASTM A572, Grade 42

    - Winch support plate	ASTM A36

    - Pole top tenon plate	ASTM A36

    - Pole top tenon	C.D.S. tubing with 36 ksi yield

  - Grind the filler metal smooth and flush with the adjoining pole surface.

  - Inspect welds according to sub-subsection 504-3.01.  8, Welding.

  - Repair the damage to the hot dip galvanized finish according to subsection 660-301.8.

  - Repair the damage to the painted finish using a paint that matches the existing pole color and is compatible with the existing powder coated finish.

504-4.01 METHOD OF MEASUREMENT.  Add the following:  The Engineer will measure Item 504(14), Defects Repair, on a time and materials basis according to subsection 109-1.05.

504-5.01 BASIS OF PAYMENT.  Add the following:  Payment for Pay Item 504(14), Defects Repair, provides full compensation for completing work ordered by the Engineer according to these special provisions.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

504(14)	Defects Repair	Contingent Sum

SECTION 505

PILING

Special Provisions

505-3.03 PILE Bearing Values.  Delete the first paragraph of this section and substitute the following:  Drive piles, except piles for lighting standards, to the required ultimate bearing capacity.  For lighting standards, install piles of sufficient length to cut the pile at the required cut off elevation and to provide the minimum installed length shown on the Plans.

505-3.09 Driving Piles.  Add the following:  In many cases, the Contractor may need to pre bore, spud, use a larger pile driving hammer, and excavate inside the pile in addition to normal pile driving techniques.  Sites for the lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

Submit a pile driving plan to the Engineer, for approval, at least 14 calendar days before driving the first steel pipe pile.  At a minimum, the pile driving plan shall consist of the following:

a.  	pile driving hammer, or hammers, to be used,

b.  	alternate techniques planned for pile installation, and

c.  	equipment used for the pile driving operation.

When the Contractor cannot achieve the minimum installed length shown on the Plans, install the pile tip to an elevation established by the Engineer.

505-4.01 Method of Measurement.

Add the following to the second paragraph:

Do not measure piles for lighting standards for payment.

505-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:  Include costs of furnishing and installing piles for lighting standards in Item 660(3) Highway Lighting System Complete.

# SECTION 606

# GUARDRAIL

# Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers.  Use flexible markers with an over length of 72 inches.  The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag that provides approximately 20 square inches of surface area.  Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval before ordering the markers.  (05/29/02)R45aM98

606-3.05 TERMINAL SECTIONS.  Replace the first sentence of the second paragraph with the following:  Conform to these Specifications and the Standard Drawings with the following exception.  Modify Standard drawing G-20.10 to only allow an offset of 1.5 foot maximum ET-2000 or 2 feet for LET-2001.  (07/14/03)R266M98

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL.  Add the following:  Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within seven calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.  (05/29/02)R45aM98

606-3.07 REMOVAL AND DISPOSAL OF GUARDRAIL.  Delete the last sentence and substitute the following:  Notify the Engineer, 5 days before removing guardrail for disposal.  The Engineer will identify portions of guardrail to be salvaged.  Guardrail and associated hardware designated will be delivered to the Department of Transportation Maintenance Yard located at 5300 E. Tudor Road (338-1466) in Anchorage.  Remaining guardrail removed shall become property of the Contractor.

Add the following subsection:

606-3.09 FLEXIBLE MARKERS.  For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION.  Add the following subsection:  After shaping the slopes and staking proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer before installation.  The Engineer may determine that additional guardrail is necessary, and comply without delay.

(05/29/02)R45aM98

606-5.01 BASIS OF PAYMENT.    Add the following:  Installation of downstream end anchorages  installed according to Standard Drawing G-13.00 is subsidiary to 606 items.

# SECTION 618

# SEEDING

# Special Provisions

618-1.01 DESCRIPTION.  Add the following:  Topsoil and seed new or disturbed slopes and other areas directed by the Engineer.  Track the soil and apply seed, mulch  ***deleted*** and water.  Provide a living ground cover on slopes as soon as possible.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Mulch	subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following:  Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes.  Cover slopes to be seeded with topsoil in according to Section 620.  Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete slope preparation as soon as topsoil is placed on the slopes.  Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  Seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION.  Add the following:  Apply seed and mulch ***deleted*** as follows per acre.  Apply seed and mulch in one application if using the hydraulic method.  ***deleted***

| Seed Mix | Component | Ingredients | Application Rate (per ha) |
| --- | --- | --- | --- |
| Type A | Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.40 lbs. 0.40 lbs. 0.20 lbs. 0.30 lbs. Total = 1.00 lbs. |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
|  | ***deleted*** | ***deleted*** | ***deleted*** |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

Delete Section 641 in its entirety and replace with the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

Standard Modification

641-1.01 DESCRIPTION.  Plan, provide, inspect, and maintain control of erosion, sedimentation, water pollution, and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices).  A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands.  BMPs include temporary or permanent structural and non-structural devices and practices.  The Department describes common BMPs in its Alaska Storm Water Pollution Prevention Plan Guide, June 2004.

- ESCP (Erosion and Sediment Control Plan).  The general plan for control of project-related erosion and sedimentation.  The ESCP normally consists of a general narrative and a map or site plan.  It is developed by the Department and included in the project plans and specifications.  It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization.  A point in time when ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional.  The stabilized site is protected from erosive forces of raindrop impact and water flow.  Typically, unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70 percent cover density) or equivalent permanent stabilization measures such as riprap, gabions, or geotextiles.

- HMCP (Hazardous Material Control Plan).  The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI.  Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.  Use EPA Form 3510-9.(Revised 6/03).

- NOT.  Notice of Termination of coverage under the NPDES General Permit.  Use EPA Form 3510-13.  (Revised 6/03).

- NPDES General Permit.  The Storm Water General Permit for Large and Small Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES).  It requires an approved SWPPP and NOIs listed as active status by the EPA before ground disturbing activities for the project.

- SPCC Plan (Spill Prevention, Control and Countermeasure).  The Contractor’s detailed plan for oil spill prevention and control measures that meets the requirements of 40 CFR 112.

- SWPPP (Storm Water Pollution Prevention Plan).  The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit.  The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project.  The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS.  For projects that disturb one acre or more of ground submit three copies each of the SWPPP and HMCP to the Engineer for approval.  Submit one copy of the SPCC Plan (if required under subsection 641-2.03) to the Engineer.  Sign submittals.  Deliver these documents to the Engineer no less than five calendar days before the preconstruction conference.

The Department will review the SWPPP and HMCP submittals within 14 calendar days.  Submittals will be returned to the Contractor as either requiring modification unless approved by the Department.  Besides a copy of the Contractor’s NOI, the approved SWPPP must contain a certification and be signed by an authorized representative according to the Standard Permit Conditions of the NPDES General Permit Part 8, Appendix G.  Notification must be received in writing from the Department that the SWPPP has been approved before submitting the original NOI to EPA.  NOIs can be submitted by Certified mail or through EPA’s electronic NOI system (eNOI).

For regular U.S. Mail delivery:			For Overnight/Express mail delivery:

EPA Storm Water Notice Processing Center		EPA Storm Water Notice Processing Center

Mail Code 4203M		Room 7420

U.S. EPA		U.S. EPA

1200 Pennsylvania Avenue, NW		1201 Constitutional Avenue, NW

Washington, D.C.  20460		Washington, D.C.  20004

For electronic mail, the Contractor must register online with EPA at: http://cfpub.epa.gov/npdes/stormwater/enoi.cfm.  This website has instructions and guidance on how to set up and use the eNOI system.

Whether submitting the NOI electronically or by mail, do not begin ground-disturbing activities until the Engineer has issued a written statement that the EPA has listed the Contractor’s NOI and the Department’s NOI as active.

The Department will submit the approved SWPPP to ADEC that will include both the Contractor and Department NOIs.

The active status NOIs, approved SWPPP, approved HMCP, and submitted SPCC Plan (when required) become the basis of the work required for the project’s erosion, sediment, and pollution control.

Once the Department has determined the site has achieved final stabilization, the Engineer will provide written notification that the NOT may be submitted to EPA with a copy to the Engineer.  The Department will transmit the Department’s NOT to the EPA.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  For projects that disturb one acre or more of ground, prepare a Storm Water Pollution Prevention Plan.  Use the Department's ESCP to develop a SWPPP based on scheduling, equipment, and use of alternative BMPs. Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, October 2003.  The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address site-specific controls and management plan for the construction site as well as for material sites, waste disposal sites, haul roads, and other affected areas, public or private.  The plan must also incorporate the requirements of the project permits.

Specify the line of authority and designate a field representative for implementing SWPPP compliance.  Designate one representative for each subcontractor who performs earth disturbing activities or who installs and maintains erosion and sediment control measures.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances.  (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities.  Detail a plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where storage, fueling and maintenance activities will take place, describe the maintenance activities, and list controls to prevent the accidental spillage of oil, petroleum products and other hazardous materials.

Detail procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by accidental spills.  Detail a plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate a field representative for spill response and one representative for each subcontractor.

641-2.03 SPILL PREVENTION, CONTROL, AND COUNTERMEASURE (SPCC) PLAN REQUIREMENTS. Prepare and implement a SPCC Plan that is certified by a licensed Professional Engineer, when required by 40 CFR 112, including:

- When oil spills may reach navigable waters; and

- Total above ground oil storage capacity is greater than 1,320 gallons.

Comply with 40 CFR 112 and address the following issues in the SPCC Plan:

- Operating procedures that prevent oil spills;

- Control measures installed to prevent a spill from reaching navigable waters; and

- Countermeasures to contain, clean up, and mitigate the effects of an oil spill.

641-3.01 CONSTRUCTION REQUIREMENTS.  Do not begin ground-disturbing work until the Engineer provides written notice that both the Contractor’s and the Department’s NOIs have been listed as active and that ground disturbing work can begin.

Post at the construction site:

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	Name and phone number of the local contact person, and

3.	Location of a SWPPP available for viewing by the public.

Comply with requirements of the approved HMCP, the submitted SPCC Plan, and state and federal regulations that pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms.  Perform fueling operations in a safe and environmentally responsible manner.  Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.  Report oil spills as required by federal, state, and local law, and as described in the SPCC Plan.

Comply with requirements of the NPDES General Permit, implement temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.  Maintain temporary and permanent erosion and sediment control measures in effective operating condition.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections.  Before the start of construction, conduct a joint on-site inspection with the Engineer and the Contractor’s field representative to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

  - During construction, inspect the following at least once every seven days and within 24 hours of the end of a storm exceeding 1/2 inch in 24 hours (as recorded at or near the project site):

(1)	Disturbed areas that have not been finally stabilized

(2)	Areas used for storage of erodible materials that are exposed to precipitation

(3)	Sediment and erosion control measures

(4)	Locations where vehicles enter or exit the site

b.	Before winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections.  During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 1/2 inch or greater.  The Engineer may waive monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports.  Prepare and submit, within three working days of each inspection, a report on state Form 25D-100, with the following information:

a.	A summary of the scope of the inspection

b.	Name(s) of personnel making the inspection

c.	The date of the inspection

d.	Observations relating to the implementation of the SWPPP

e.	Any actions taken as the result of the inspection

f.	Incidents of non-compliance

Where a report does not identify incidents of non-compliance, certify that the facility complies with the SWPPP and NPDES General Permit.  The Contractor and the Engineer will sign the report according to the Standard Permit Conditions of the NPDES General Permit, Part 8, Appendix G.  Include reports as an appendix to the SWPPP.

Retain copies of the SWPPP, and other records required by the NPDES General Permit, for at least three years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP to correct problems identified because of:

1.	Storm or other circumstance that threatens water quality, and

2.	Inspection that identifies existing or potential problems.

Submit SWPPP amendments to the Engineer within seven days following the storm or inspection.  Detail additional emergency measures required and taken, to include additional or modified measures.  If modifications to existing measures are necessary, complete implementation within seven days.

Stabilize areas disturbed after the seeding deadline within seven days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT to EPA and the Engineer:

1.	When the Engineer has acknowledged in written form that the project site (including material sources, disposal sites, etc.) has been finally stabilized and storm water discharges from construction activities authorized by this permit have ceased, or

2.	When the construction activity operator (as defined in the NPDES General Permit) has changed. and the Engineer provides written notification that the Contractor’s responsibilities with respect to compliance with the NPDES GP on the project have ceased.

If the Contractor fails to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend earthwork operations and withhold monies due on current estimates for such earthwork items until the work is coordinated in a satisfactory manner.

If the following is not done:

1.	Pursue work required by the approved SWPPP,

2.	Respond to inspection recommendations and/or deficiencies in the SWPPP, or

3.	Implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from the progress payments.

641-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Items 641(2) and (4) will be measured as specified in the contract or directive authorizing the work.

641-5.01 BASIS OF PAYMENT.  The Bid Schedule will include either items 641(1) and (2) or items 641(1), (3), and (4).

1.	Item 641(1) Erosion and Pollution Control Administration.  At the contract lump sum price for administration of work under this section.  Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting, and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control.  At the prices specified in the contract to install and maintain temporary erosion, sedimentation, and pollution control measures.

3.	Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain temporary erosion, sedimentation, and pollution control measures under the original approved SWPPP and HMCP.

4.	Item 641(4) Temporary Erosion and Pollution Control Amendments.  At the prices specified in the directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures.  Work paid under this item will be shown as amendments to the original approved SWPPP or HMCP.

Temporary erosion and pollution control measures that are required at Contractor furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to the Contractor’s negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for the Contractor’s convenience, at the Contractor’s expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule. (02/19/04)E09

Payment will be made under:

641-5.01 BASIS OF PAYMENT.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1) 	Erosion and Pollution Control Administration 	Lump Sum

641(2) 	Temporary Erosion and Pollution Control 	Contingent Sum

641(3) 	Temporary Erosion and Pollution Control 	Lump Sum

641(4) 	Temporary Erosion and Pollution Control Amendments 	Contingent Sum

(02/19/04)E09

SECTION 643

TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following:  The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  Movements of oversize and overweight vehicles in or near traffic within the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 feet lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.  (01/29/02)R222M98

643-2.01 MATERIALS.

Add the following:

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.  (01/29/02)R222M98

Standard Modification

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:

Immediately notify the Engineer of traffic related accident that occurs within the project limits as becoming aware of the accident.  E10(2/5/04)

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.  (01/29/02)R222M98

Standard Modifications

643-3.04 TRAFFIC CONTROL DEVICES.

In the sixth paragraph, delete the words “ATTSA” and replace with “ATSSA”

Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES.  Add the following to  1. Embankments:  Close trenches and excavations at the end of each continuous work shift.

Add the following to  3. Fixed Objects:  At the end of each continuous work shift remove obstructions greater than 4 inches above the nominal fore slope grading.

Add the following:

9.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, and maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER.  Add the following after the second sentence:  In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following:  Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices.  The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public.  Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

# ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING.  Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Monday thru Thursday from 0600 hours to 0800 hours.

2.	Monday thru Thursday from 1600 hours to 1800 hours.

3.	Friday from 1500 hours to 2200 hours.

4.	Sunday from 1200 hours to 2200 hours.

5.	Around holidays:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

Obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  Make every effort not to delay school buses through the construction work zone.

643-3.09 INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following:  Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer.

- Add the following new subsection:

643-3.10 LIGHTING OF NIGHT WORK

Illuminate the night work areas specified in Table 643-2 to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

| Table 643-2 Night Work Illumination Level and Area of Coverage |  |  |  |  |
| --- | --- | --- | --- | --- |
| Type of Work/ Equipment | Lighting Configuration | Minimum lllumination (footcandles) | Area of Illumination |  |
|  |  |  | Length (along road) | Width (across road) |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least 2 machine-mounted balloon lights with a total wattage of at least 4000 watts. Provide additional lights or wattage to meet illumination and area requirements. | 5 | 15' beyond front and back of machine | 15’ beyond both sides of machine |
|  |  | 1 | 30' beyond front and back of machine | 30’ beyond both sides of machine |
| Rolling, pavement sweeping | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. | 5 | 20' beyond front and back of roller | Not specified |
| Flagging | One light plant with 4 - 1000 watt metal halide lamps illuminating the flagger located within 50' of flagger. Orient to avoid creating glare for drivers. | Not specified | Not specified | Not specified |
| Truck Crossings (meaning where haul vehicles cross or enter a road): | One light plant with 4 - 1000 watt metal halide lamps located in a manner that will illuminate haul vehicles approaching the crossing. Orient to avoid creating glare for drivers. If it is not possible to illuminate both the flagger and haul vehicles at flagger controlled crossings, provide an additional light plant of the same type. | Not specified | Not specified | Not specified |
| 1) with roads with ADTs over 10,000 or |  |  |  |  |
| 2) that are controlled by portable signals or flaggers |  |  |  |  |

When Table 643-2 gives the option of balloon lights or light plants, use balloon lights where possible – they provide uniform light with minimal glare.

The Engineer may verify illuminance levels and uniformity at any time using a handheld light meter.

Install lighting in a manner that minimizes glare for motorists, workers, and annoyance or discomfort for residents living along the roadway.  Locate, aim, louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to meet required illuminance levels or provides lighting that creates unacceptable glare at any time, the Contractor shall cease nighttime operations in that area until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare

and to provide the required illuminance.  Locate mounting brackets and fixtures so they don’t interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibration.

Ground, trailer, and equipment-mounted light towers shall be sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer-mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Ensure that trailer or equipment mounted light towers do not exceed the height of overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting.  Furnish each side of non-street legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.

Existing street and highway lighting do not eliminate the need for the Contractor to provide lighting.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of emergency flares for use in the event of emergency or unanticipated situations.

Provide NCHRP 350 compliant breakaway bases for post-mounted electroliers located within the clear zone.

Standard Modification

- Add the following new subsection:

643-3.11. HIGH VISIBILITY CLOTHING.  Ensure workers within project limits wear an outer visible surface or layer that complies with the following requirements:

1.	Tops.

Wear fluorescent vests, jackets, or coverall tops conforming to Class 2 at all times.  Class 2 requires at least 775 square inches of conforming fluorescent red-orange background material and at least 201 square inches of conforming retroreflective striping.  Retroreflective striping shall be fluorescent yellow-green combined-performance material.

The vest, jacket, or coverall top shall have two over the shoulder combined-performance retroreflective stripes, and at least one 360 degree horizontal combined-performance retroreflective stripe around the torso.  Jackets and coverall tops shall have two horizontal combined-performance retroreflective bands on each sleeve; one above and one below the elbow.

2.	Bottoms.

Wear fluorescent red-orange Class E pants or coverall bottoms during nighttime work (sunset to sunrise).  Flaggers shall wear fluorescent red-orange Class E pants or Class E coverall bottoms at all times.  Furnish each garment with two 2-inch wide combined-performance fluorescent yellow-green retroreflective horizontal stripes on each leg.

3.	Raingear.

Raingear tops and bottoms, when worn as the outer visible surface or layer, shall conform to the requirements listed above in (1) Tops and (2) Bottoms.

- Exceptions.

When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility clothing.

- Standard.

High visibility garments shall conform to the requirements of ANSI 107-1999 as well as this specification.  Class 2 and Class E garment requirements are defined in that standard. Retroreflective material must also qualify as combined-performance fluorescent material.

- Labeling.

Garments shall be labeled in conformance with Section 10.2 of ANSI-107-1999.

- Condition.

Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.

643-4.01 METHOD OF MEASUREMENT.  Add the following:  No measurement required to provide a 24 hour toll free (1-800-###-####) "hotline road report" telephone with a recorded message, and weekly notices with daily updates.  Work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.  (01/29/02)R222M98

643-5.01 BASIS OF PAYMENT.  Add the following:

- Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items. R276USC04(11/29/04)

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $2.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Foot Foot Each Each | $0.30 $0.65 $0.75 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $36.00/hour.  The Engineer does not require a change order/directive for the flagging pay item.  (11/18/02)R222M98

Add the following:  Payment for high visibility clothing for workers is subsidiary to other items.  (12/02/03)E07

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete the third, fifth, and seventh sentences of the first paragraph and the second paragraph in this subsection and substitute the following:  Meet the following office requirements:

1.	A minimum of 1000 square feet of floor area.  Divide the office area so that it contains an office room separated by a closable door.  The office room shall have a minimum of 40 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	A minimum of two electrical outlets.

4.	Adequate parking for a minimum of 5 vehicles, with one disability parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

5.	Provide attached indoor plumbing with sanitary lavatory facilities and potable drinking water.

6.	Three telephone lines available at the project location.

7.	Located within 5 miles of the project.

8.	Provide one move in and one move out for state office furniture and equipment.

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Delete this subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.  The finalized CPM schedule must be completed and accepted before work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete item 2.  60-Day Preliminary Schedule.

Delete the first sentence of item 3.  Schedule Updates.  and substitute the following:  Hold job site progress meetings with the Engineer for updating the CPM Schedule.  Meet with the Engineer monthly, or as deemed necessary by the Engineer.  (12/13/02)R261M98

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

Special Provisions

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall be according to the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment on the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary, for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the engineer may direct.

Equipment shall be in first-class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacture's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISON PERSONNEL.  Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, state, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS.  The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop the operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas according to the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT.  Payment for Item 647(1) Wide Pad Dozer, 65 hp Minimum will be paid on a contingent sum basis at the rate of $125/hour on a per hour basis at the rate shown on the bid schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)				Wide Pad Dozer, 65 hp Minimum     		Contingent Sum

(11/12/98)R15M98

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-2.01 MATERIALS.  Delete the requirement for “Steel Pipe Pile” and substitute the following:

Steel Pipe Pile	ASTM 252, Grade 3, seamless or Electric resistance welded single longitudinal seam

1.	Equipment List(s) and Drawings. Delete item a in its entirety and substitute the following:

a.	Materials on the Approved Products List: The Approved Products List does not apply to the 660 items.  Provide catalog cuts of materials to the Engineer for review and approval.

2.	As-Built Plans.  Add the following:

The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL  Delete items 3 through 8 in their entirety and substitute the following:

- Excavating and Backfilling. Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors.  Complete this work according to the requirements of Section 643.  Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountered during excavation.

Excavate trenches wide enough to install the number of conduits specified side by side, to provide clearances of at least 2½ inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches, and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for six inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit.  Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

Dispose of, according to subsection 203-3.01, excavated materials that remain after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in subsection 703-2.07.

Dewater excavations immediately before and during embedding and backfilling operations.  Backfill excavations with materials that meet the following requirements:

a.	Around formed foundations and the tops of pipe pile foundations, use material that meets the requirements of Selected Material, Type A,

b.	Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift in which it is located, reusing excavated materials if it meets the requirements of the applicable lift,

c.	In other locations, embed conduits, and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

d.	Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material gleaned free of rocks exceeding a one inch maximum dimension.  Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within six feet of paved surfaces and around foundations, backfill in uniform layers no more than six inches deep and compact each layer according to subsection 203-3.04.  In other locations, compaction may be as approved by the Engineer.

- Welding.  Complete welding according to subsection 504-3.01.8. Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval.  The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes, which were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface.  For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole.  Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole.  Grind the welds smooth and flush with the adjoining pole and disk surfaces.  Repair the damaged finish according to subsection 660-3.01.8.

- Removing and Replacing Improvements.  Complete the following work at the Contractor’s expense.

- Remove improvements that need to be removed to complete the work detailed in the Plans.

- Reconstruct with new materials the nonreusable improvements removed to complete the work, the repairs that are not covered by other items in the Contract.

- Replace with new materials the reusable items damaged by the Contractor, which are specified for reuse.

- Reconstruct with new materials improvements damaged or removed by the Contractor, which do not conflict with the work and are not scheduled for removal.

Nonreusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings.  Reusable improvements include the items that were made before they were installed.  However, the Contractor may not reuse crushed aggregate base material as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska Standard Specifications for Highway Construction (SSHC), and leave the work in a satisfactory and serviceable condition.  In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If a portion of sidewalk or curb and gutter is removed, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install four inches of compacted topsoil.  Match the top of the topsoil with the bottom of the vegetative mat.  Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621.  Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

- Salvaging or Reusing Electrical Equipment. When the Plans include existing electrical systems, salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, service equipment, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for reuse in a new location.

A controller assembly includes the cabinet and equipment contained in the cabinet before Contract award, including bus interface units, controller unit, phase selectors, load switches, flasher unit, detector amplifiers, and conflict monitor unit.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer.  Note the location and condition of the materials.  When finding material specified for reuse in an unserviceable condition, the Engineer will

determine whether to repair it or replace it with new material, which will be paid for as extra work under subsection 109-1.05.  Retain a copy of the inventory and give the original documents to the Engineer.

Remove, store, and deliver salvaged equipment not scheduled to remain in service without damaging it.  Replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.  Deliver removed equipment not scheduled for reuse to the Anchorage District Maintenance Station.  Notify Jerry Reed, the district superintendent, at 338-1432 or Ed Caress at 338-1436 one week before the planned delivery date.

Remove other materials from the highway right-of-way, including conduits, junction boxes, conductors, and foundations.  Raze the tops of foundations abandoned in place according to subsection 660-3.02.  Fill the holes left by removing junction boxes and foundations with selected material type A and compact them as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned with a credit taken by the Department.  Remove the ends of abandoned conduits from the junction boxes that will remain in service.

When reusing the existing and State furnished equipment specified, complete the following work at the Contractor’s expense:

- For relocated poles, install new foundations of the type specified and furnish new nuts, bolts, washers, and conduits needed to complete the installations.

- For reused electroliers, including those electroliers that will remain on their foundations, install new illumination tap wires and fused disconnect kits.

- Clean reused signal heads and luminaires inside and out.

- Install new lamps in luminaires and new light emitting diode optical units in the signal heads.

- For relocated signal heads, furnish and install the mounting brackets needed to complete the installations.

- For reused poles, repair the holes that were made to mount equipment according to subsection 660-3.01.4. Welding.

- For equipment with damaged finishes, including welded hole repairs, provide a new finish on the equipment according to subsection 660-3.01.8.

- Adjust reused junction boxes and the conduit ends in them to the new grade according to subsections 660-3.04 and 660-3.03, respectively.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to subsection 660-2.01.1.

- Field Tests.  Electrical circuits must pass the following tests before the Engineer will accept the work for payment.  Perform these tests in the presence of the Engineer, and document the results of each test on a per circuit basis.  Retain a copy of test results and give the original documents to the Engineer.  Furnish equipment needed to perform these tests.

Replace or repair at the Contractor’s expense, and in an approved manner, faulty materials and work revealed by these tests.  After making repairs, repeat tests on the repaired circuit and continue this process until circuits have passed required tests.  The Department reserves the right to have circuits retested, and to use the retest results to accept or reject individual circuits.

- Grounds. Before completing the circuitry and functional tests, physically examine conduits ends, junction box lids, load centers, and the foundations for signal posts and poles, lighting poles, and controller cabinets to ensure the grounding system required by subsections 660-3.06 and 661-3.01 has been installed and splices and connections are mechanically firm.

- Continuity.  Test each loop detector circuit for continuity at the roadside junction box before splicing the loop detector to the lead-in cable.  Each loop detector must have a resistance less than 0.5 ohms.

After splicing the loop detectors to the lead-in cables, test each pair at the controller or detector cabinet.  Each pair must have a value less than 5 ohms for single pair lead-in cables and 10 ohms for multi-pair lead-in cables.  The continuity test ohm reading at the cabinet must be greater than the ohm reading measured for the loop detector at the junction box.

- Insulation Resistance Test.  Perform a conductor insulation (megohm) test on conductors.  Complete the test between each conductor and ground and between the conductors in each cable.  Disconnect lamps and magnetometer sensing probes before completing the megohm test.

After splicing the loops to the lead-in cables, measure each pair in the lead-in cables at the controller or detector cabinet between one conductor and the cabinet ground rod.  Insulation shall measure a minimum resistance of 100 megohms or the minimum specified by the manufacturer, measured at 500 volts DC.

- Inductance Test.  Measure each detector loop and lead-in cable system at the controller or detector cabinet.  The inductance must be in the range of 50 to 500 microhenries.

- Circuit. Energize every signal indication circuit with lamps installed before installing the load switches.

- Functional. Perform the following tests on each signal and lighting system after the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity, and circuitry.

  - For each new traffic signal system, complete at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory

operation.  The Engineer may decide to omit the flashing portion of the test for modified signal systems and for new signals that replaced existing signals that remained in operation during the construction phase.

If the Engineer omits flashing operation and the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for five days with continuous, satisfactory operation.

Begin the signal functional tests between 9:00 a.m. and 2:00 p.m. on any day, except a Friday, Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Before each system turn-on, aim signal faces according to subsection 660-3.08 and ensure equipment specified in the Plans is installed and operable, including: pedestrian signals and push buttons; signal backplates and visors; vehicle detectors; highway lighting; and regulatory, warning, and guide signs.

  - Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5 day operational test using the photocell.

  - Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

  - Perform a continuous 5 day burning test on each pedestrian overpass and underpass lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system functions normally when power is returned.

8.	Repairing Damaged Finishes. Examine new, reused, and State furnished equipment for damage to its finish before putting the equipment into service.  Repair the damaged finishes found according to the following:

a.	Galvanized.  Repair damaged areas more than 12 inches away from welds and slip fit areas, by applying a minimum 7.8 mils of zinc based alloy applied according to ASTM A780.

If the damaged areas are within 12 inches of welds and slip fit areas, make the repair by applying a minimum 7.8 mils of zinc rich paint applied according to ASTM A780.

b.	Painted.  Repair damage to painted finishes according to the following

(1)	Wash the equipment with a stiff bristle brush using a solution containing two tablespoons of heavy duty detergent powder per gallon of water.  After rinsing, wire brush surfaces to remove poorly bonded paint, rust, scale, corrosion, grease, or dirt.  Remove dust or residue remaining after wire brushing before priming.

(2)	Factory or shop cleaning methods may be used for metals if equal to the methods specified herein.

(3)	Immediately after cleaning, coat bare metal with pre-treatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

(4)	Give signal equipment, excluding standards, a spot finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

(5)	Give nongalvanized standards 2 spot finish coats on newly primed areas.

Paint coats may be applied either by hand brushing or by approved spraying machines.  Perform the work in a neat and workmanlike manner. The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint spraying machine prove unacceptable.

Add the following new item 9:

9.	Regulations and Code. Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the authority having jurisdiction.

660-3.02 FOUNDATIONS.

1.	Cast-in-Place Foundations. Delete item k and add the following new items k and l:

k.	Install the bottoms of the bottom leveling nuts in a level plane within one inch of the top of foundations.  Generously lubricate the bearing surface and internal threads of top nuts with beeswax and tighten the top nuts according to the anchor bolt tightening procedure included in the subsection 660-3.08 item 6. High Tower Lighting System Installation.

l.	Attach a 4 AWG, bare, solid copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector or cadweld to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled 4 AWG, bare, solid copper wire as the grounding electrode.  Route the conductor to protrude near the top, center of the foundations.  Slide a minimum six inch long, non-metallic, protective sleeve over the conductor.  Allow one inch of the sleeve and 24 inches of conductor to protrude from the foundations.

2.	Pile Foundations. Add the following new item g:

g.	Use no more than one splice per foundation.  Locate the splice at least seven feet from the top of pile.

Add the following:

4.	High Tower Foundations.  Furnish pipe piles that conform to ASTM A252 grade 3 and feature the diameter, minimum length and wall thickness shown on the Plans.  Furnish seamless piles or piles with a single longitudinal seam that is electric resistance welded.

Complete welding according to subsection 504-3.01.8 Welding.  Submit a shop drawing of the work with the welding plan.  Furnish Quality Control inspection to ensure materials and workmanship meet contract requirements.  Visually inspect (VT) 100% of each weld and inspect 100% of full penetration welds by ultrasonic NDE (UT).

Furnish anchor bolts that conform to ASTM F1554, grade 55, and meet the supplementary Charpy V-Notch requirements listed in subsection S4 of the specification.  Furnish each anchor bolt with three nuts and two washers.

Secure the anchor bolts to ensure they do not move during concrete placement.  Replace, with no additional compensation, concrete pile caps with anchor bolts that do not match the base plate of the pole or are out of plumb.  The Department will not allow modification of the anchor bolts or base plate to get the base plate set on the leveling nuts.

660-3.03 CONDUIT.  Delete this subsection in its entirety and substitute the following.  Install electrical conductors in conduits, except for overhead wiring, wiring inside poles, and when otherwise specified. Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits.  Install conduits of the sizes specified along the routes detailed on the Plans.  When routing is not shown, route conduits as directed by the Engineer.

- Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

- Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches.  Excavate, bed conduits, and backfill trenches according to subsection 660-3.01.3, Excavating and Backfilling.

- Install conduit(s) under paved roadways and approaches that will not be overlaid by jacking them under pavements up to 30 feet wide and by boring or drilling methods under pavements greater than 30 feet wide.

- Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs.  To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box.

- Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box.  Extend the ends a minimum of 2 inches beyond the inside wall of the box.

- Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs.  Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors.  Cover the holes with a wrap of approved filter cloth secured with two self clinching nylon cable ties.

- Keep conduits clean at all times.  Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends.

- At the low points of conduit runs, install sumps containing a minimum 2 cubic feet of coarse concrete aggregate material that conforms to subsection 703-2.02.  Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

- Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary.  Install additional drains and aggregate sumps at the low spots.

- Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 2½  inches around two inch conduits and at least 2 inches around conduits larger than 2 inches.

- Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit.  Cut the same number of threads as found on the factory threaded ends.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.  Do not use slip joints or pieces of running thread pipe.

- Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

- When standard couplings cannot be used to join conduit components, use approved threaded unions.

- Bury a continuous strip of 4 mils thick, six inch wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a red background.

- If encountering obstructions during jacking or drilling operations, obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 1-¼ to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

- When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

- In foundations, install 90 degree elbows and conduits of the size and quantity shown on the Plans.  Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

- Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct-sealing compound.

- Install expansion fittings in conduits that cross expansion joints.

- Install a polypropylene pull rope with a minimum 200 pound tensile strength in future use or spare conduits, and reinstall the plugs.  Double back at least two feet of pull rope into both ends of each conduit.

- Conduits larger than specified may be installed. If used, it must be for the entire length of the run.  Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

- Clean existing conduits that will remain in service using a heavy duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch.  Clean the conduits before pulling in new cables and after removing cables specified to be removed or replaced as follows:

- When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

- Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

- When modifing existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit.  When extending existing conduits, add no more than 90 degrees of horizontal bend to the extension.

- When install a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

- When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

- Remove the ends of abandoned conduits from junction boxes that will remain in service.

Replace subsection 660-3.04 with the following:

660-3.04 JUNCTION BOXES.  Install pre-cast reinforced concrete junction boxes of the types specified with cast iron lids.  For junction boxes that contain traffic signal conductors, furnish lids with the word TRAFFIC cast into them.  For junction boxes that contain lighting conductors exclusively, furnish lids with the word LIGHTING cast into them.

When shown, install junction boxes at the station and offset locations specified.  When lateral locations are not specified, install junction boxes eight feet from the face of curb or edge of pavement.  If the eight feet offset falls:

- In a pedestrian facility separated less than seven feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility. When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

- In a pedestrian facility separated at least seven feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

- Outside the right of way, install the boxes just inside the right of way line.

- In a raised median, install junction boxes near the center of the median.

- In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

- Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least five feet back from the face of rail.

- On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing type 1A junction boxes in driveways and in locations subject to use by heavy trucks.  When shown near the ends of medians, install junction boxes at least ten feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.

Limit the distance between adjacent junction boxes to the following dimensions:

- 400 feet for conduits that contain signal interconnect cable only.

- 300 feet for conduits that exclusively contain two loop lead-in cables or a single cable other than signal interconnect.

- 190 feet for conduits that contain more cables than those listed in the two preceding limitations.

- If the three preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work, otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria.  In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes one inch below finished grade.  In seeded areas, install the tops of junction boxes to two inches below the seeded surface.

Bond junction box lids to an equipment-grounding conductor according to subsection 660-3.06.  Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box.  Drains shall consist of coarse aggregate for concrete that conforms to subsection 703-2.02.  Minimum drain dimensions include an 18 inch depth and a length and width equal to those of the junction box it drains.  Compact the aggregate material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker that consists of an antenna encapsulated in a 4 inch diameter red polyethylene ball.  Furnish markers that conform to the American Public Works Association standards for locating power.  Markers shall respond to locator devices up to 5 feet away, work at all temperatures, and contain no internal power source.

660-3.05 WIRING.  Delete the second paragraph in its entirety and substitute the following:

Do not pull conductors into conduits until the following conditions are met:

  - The prescribed clearances around conduit ends are provided,

  - Crushed rock sumps are installed under junction boxes,

  - Conduit ends protrude above the bottom of junction boxes within the prescribed range,

  - New conduits are free of materials that became lodged in them during the completion of the work,

  - Reused conduits are cleaned according to subsection 660-3.03,

  - Junction boxes are set to grade, and

  - Grounding bushings are installed on the ends of metallic conduits.

Delete item 3 in its entirety and substitute the following:

3.	Pull, as a unit, the conductors specified to be installed into clean conduits, leaving existing conductors that will remain in service in place.

Delete items 11 and 12 in their entirety and substitute the following:

11.	Encapsulate illumination cable splices in rigid 2 piece plastic molds filled with an insulating and sealing epoxy resin.  Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin.  Furnish molds rated for 600 volts AC operation and feature fill and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

12.	Encapsulate loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with reenterable polyurethane electrical insulating and sealing compound.  Furnish splice kits rated for 1000 volts AC operation and direct burial.

Provide reuseable four piece molds that are held together with stainless steel hose clamps. Two pieces form a cylinder and two flexible end caps seal the ends and allow the conductor entry.  Use molds with dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Insert a loose woven polyester web that allows a full ¼ inch of insulating compound to flow between the splice and the inside of the mold.  Fill the PVC molds with re-enterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is non-corrosive to copper, and does not support fungi or mold growth.

Add the following:

18.	Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

19.	Whenever conductors cannot be terminated in circuit breakers due to their size, splice a piece of 8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet.  Limit the length of the #8 AWG conductor to five-feet.

Replace subsection 660-3.06 with the following:

660-3.06 BONDING AND GROUNDING.  Bond and ground branch circuits according to the NEC and the following requirements.  Make non-current carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor.  Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install grounding bushings with insulated throats on the ends of metallic conduits.

Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size 8 AWG conductors, except in those conduits that contain circuit conductors larger than 8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12-inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installing or removing conductors from existing conduits, retrofit them with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross-sectional area equal to an 8 AWG conductor.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.  Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the 4 AWG grounding electrode conductor using irreversible compression connectors at Portland cement concrete foundations.  For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a four feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the hand hole of each pole.

Bond slip-base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the hand hole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a ¾” by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

Replace subsection 660-3.08 with the following:

660-3.08 SIGNAL AND LIGHTING INSTALLATION REQUIREMENTS.  Install signal and lighting equipment according to the details shown on the Plans and the following:

Determine the shaft lengths and signal mast arm connector plate locations on poles to meet the plan mounting heights of luminaires and traffic signal heads.

Remove burrs and sharp edges from the inside and outside of holes before passing conductors through the walls of posts, poles, mast arms, signal heads, and other equipment.

Furnish work to install foundations for relocated poles, including: conduit, excavation, reinforcing steel, class A concrete, anchor bolts, nuts, and washers.

Orient photoelectric control units mounted on top of poles to face the north sky.

To install photoelectric controls on top of electroliers, use a pole top adapter manufactured to fit over the end of poles, General Electric model PTA-PECTL or approved equal.

To install photoelectric controls on signal poles, wood poles and on Type 1 and 1A Load Centers, use a receptacle manufactured to fit the end of a rigid metal conduit, General Electric model MB-PECTL or approved equal.  On signal poles, attach a short nipple to the rain cap using a Myers hub sealed with silicone.

1.	Electrolier.  Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm.  After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

2.	Wood Pole.  Place the poles in the ground to at least six feet deep.

After setting each pole in the ground, backfill the space around the pole with selected earth or sand, free of rocks four-inches and larger, or deleterious material.  Place in layers approximately four-inches thick and thoroughly compact with mechanical tampers.

Furnish poles that provide a minimum vertical clearance of 21 feet between the pavement and low point of overhead conductor.

3.	Signal Pole.  Install signal poles with the centerline of the pole plumb.  Install a metal skirt that fits around the anchor bolts and between the top of the foundation and bottom of the base plate.  Secure the skirt with stainless sheet metal screws.

4.	Signal Head Mounting.  Keep signal indications fully and securely covered with a white or light brown material until the signals go into operation.

Furnish elbow pipe fittings, post top adapters without a terminal compartment, and elevator plumbizers with integral serrated contacts that feature 72 teeth.

For signal faces installed on the sides of poles, furnish signal frames that consist of watertight assemblies of 1½-inch nominal diameter standard steel pipe, malleable iron or brass pipe fittings, and bronze terminal compartments.  Furnish signal frames that conceal the conductors within the framework.

Furnish vehicular signal frames with a minimum horizontal dimension between the center of the terminal compartment and the axis of the adjacent signal face of 22 inches in side mounted frames and 11 inches in post top installations.

Furnish terminal compartment with a terminal block containing 12 poles, each with two screw-type terminals.  Each terminal must accommodate at least three 14 AWG conductors. Provide terminal compartments with a rain-tight door that provide ready access to the terminal block.

Securely attach terminal compartments on the side of poles according to Standard Drawing T-30.  Install vertical pipe members plumb.

When installing 5-section vertically stacked signal heads on the sides of poles, secure the vertical pipe to the pole using a steel conduit hanger mounted six inches below the top horizontal pipe.

Aim through-phase vehicular signal faces at a point located a distance from the face as shown in Table 660-2.  If two through-signal faces are not visible from this point at a height of 42 inches above finished grade, consult the Engineer for corrective measures.

Orient pedestrian signal faces at the center of the crosswalk on the opposite side of the street.

# TABLE 660-2

# THROUGH-SIGNAL AIMING POINT

| 85th Percentile Speed (mph) | Minimum Visibility Distance (feet) |
| --- | --- |
| 20 | 175 |
| 25 | 215 |
| 30 | 270 |
| 35 | 325 |
| 40 | 390 |
| 45 | 460 |
| 50 | 540 |
| 55 | 625 |
| 60 | 715 |

Install framed signals on post-tops using post top adapters with terminal compartments, except one-way signal heads, may be installed on slip-fitters without a terminal compartment.  Provide post top adapters with no terminal compartment made of cast-iron.  Furnish post top adapters that fit over a four-inch nominal standard pipe and feature two rows of cadmium plated steel setscrews, with three screws in each row.

Provide signal heads that will be mounted on mast arms or pipe tenons with a ferrous or bronze elevator plumbizers.

With two-piece mast arms, do not install signal heads within 12-inches on either side of the slip type field splice.

Install side-mount pedestrian signals using a 2-piece, hinge connected, cast aluminum bracket that mounts directly between the pole and the side of the signal head housing.  The bracket must properly fit round poles four inches and greater in outside diameter and allow a minimum rotation of 15 degrees when mounted on a four inch pole.  The bracket shall feature a rain-tight terminal compartment and include a 12-position terminal block.  Installed, the bracket shall take less than three inches of space between the head and pole.

5.	Pedestrian Push Button.  Install the push button and sign on the crosswalk side of the pole.  Install indicator lights when specified.

Install R10-4B (R or L) push button signs above each push button.  Furnish signs with the arrow pointing in the direction of the appropriate crosswalk.  When channel is used for mounting push button signs, tap the top and bottom sign bolts into the pole.  Install R10-101 stickers, The Meaning of Pedestrian Signals, immediately above and between the R10-4B signs, when two pedestrian push buttons are installed on a pole.

6.	High Tower Lighting System.  Assemble high tower poles according to the installation instructions furnished by the manufacturer.  If assembling the poles using another technique, furnish a plan stamped by a registered professional engineer to the Engineer for approval.  Furnish timbers required to assemble the pole, regardless of the method of assembly.

Position the pole during assembly to avoid moving the pole on the ground when lifting the pole to install it on its foundation.  When conditions around a foundation preclude assembling the pole on site, assemble the pole as close as possible to the foundation and move the pole into position for installation on its foundation.  Before moving a pole, submit a plan stamped by a register professional engineer for moving poles without damage to the Engineer for approval.

Install the lowering system including masthead assembly, luminaire ring, winch assembly, and cables as instructed by the manufacturer’s on site representative.

Install and level the luminaires according to the manufacturer’s written installation instructions.

Furnish the Engineer an instruction sheet from the manufacturer for orienting reflectors in luminaires that provide an asymmetrical light distribution.  Adjust the luminaire reflectors on each pole according to this sheet until they are oriented in the same direction and distribute light according to the pattern shown on the illumination sheets.

Use steel templates to accurately locate and hold the anchor rods plumb and in proper alignment during concrete placement.  Leave this template in place for at least 24 hours after completing concrete placement.  The Engineer will reject foundations with anchor rods that are out-of-position or more than 1:40 out-of-plumb.  The Department does not allow bending of anchor rods to plumb the ends or to move them into position, or altering a pole’s base plate to match the anchor bolts.

Tighten the nuts that secure high tower lighting poles to concrete foundations according to the following procedure.  Use nuts that conform to ASTM Specification A 194 or A 563 of the grade, surface finish, and style for two-inch diameter anchor rods that conform to ASTM F 1554, Grade 55.  Washers shall conform to ASTM F 436 Type 1.

Thread nuts onto the anchor rods to within one inch above the top of the concrete base and adjust them downward, if necessary, to provide a minimum ¼ inch projection of the rod above the top of the top nut in the tightened position.  Adjust nuts until their tops form a level plane.  Install one washer on top of leveling nuts and, after setting the pole on these washers, install one washer under top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Apply beeswax to the top nut bearing face and top nut internal threads before threading it onto the anchor rod.  Tighten top nuts to a “snug” condition.  Use a click-type torque wrench to apply 600 foot-pounds of torque to the “snug” top nuts.  Torque the top nuts in the following crisscross pattern.

After torquing the top nuts, use a hydraulic wrench to rotate top nuts an additional one third (120o) turn, while preventing the leveling nuts from turning.  Use the crisscross pattern shown above.

7.	Underpass Lighting System.  Mount the fixture as detailed on the drawings so that the axis of the lamp is perpendicular to the axis of the underpass.

8.	Flashing Beacon.  When installing flashing beacons adjacent to or in conjunction with a traffic signal system, install the flasher control in the controller cabinet.

Replace subsection 660-3.09 with the following:

660-3.09 MAINTAINING TEMPORARY AND EXISTING ELECTRICAL SYSTEMS.  This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract.  The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.  Temporary electrical services shall be underground.

If the electrical system is not maintained as specified herein, the Engineer will reduce the payments under Item 660(22), Illumination Price Adjustment.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference.  Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility.  Therefore, before starting work on the project, inventory the condition of the existing equipment and document damaged and defective equipment, the Engineer will inspect with the Contractor.  If beginning work before providing the Engineer with an inventory, the Contractor will waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems.  The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems.  The State will pay for electricity used to operate the systems, if the public benefits from their operation.  Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer.  If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times beginning and completing work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions are allowed in subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than six feet.

During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches according to the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 17.5 feet to 21.5 feet of clearance between the traveled way and the bottom of each signal.  For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain nine feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	When the horizontal angle to the side mounted far right signal exceeds 20o, relocate this signal to an overhead location.  Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

i.	With two or more through lanes, center one signal head over each lane.

ii.	With one through lane and protected-permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

iii.	Otherwise, install the relocated signal eight feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain seven to nine feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in subsection 660-3.08, Signal and Lighting Structures.

When no longer required, salvage original and Department provided equipment according to the Plans and item 6.  Salvaging or Reusing Electrical Equipment found in subsection 660-3.01, and remove other materials used in the temporary systems from the project.

Add the following subsections:

660-3.09(B) TEMPORARY ELECTROLIERS.  When the contract includes Item 643(40), Temporary Electrolier, install temporary electroliers at the following locations:

1.	Along roadway segments that are illuminated when beginning work and of the following conditions apply:

a.	Traffic maintained on the subgrade, portions of the new pavement structure, or on the existing pavement.

b.	Permanent light system cannot be made operational beforehand.

c.	When, because of grading operations, a vehicle with a four-inch ground clearance and five feet between the tires would snag on the existing foundations, or the tops of the existing foundations are more than eight inches below the grade of the surrounding embankment.

2.	At locations specified by the Engineer, including

a.	Along detours and diversions, and

b.	Along traveled ways that transition from one typical section to another, and

3.	At temporary traffic signals.

4.	At the locations shown in the Plans.

North of the Turnagain Arm of Cook Inlet, the Department will not require lighting from midnight June 7 to midnight July 5.  Make temporary electroliers operational by sunset on the day replacing or retiring the existing system, or open a roadway and/or detour to traffic.

Submit a plan for each temporary electrolier system to the Engineer for review and approval before implementing it.  Allow at least two weeks for review.  Provide temporary electroliers on the far right side of approaches at signalized intersections.  Installation of luminaires and mast arms on the signal poles maybe allowed when they do not conflict with other overhead utilities.  Along roadways, choose one of the following options for temporary lighting plan

1.	When one is included, use the temporary lighting plan detailed in the Plans.

2.	On roadways with existing lighting, provide new foundations and install poles and mast arms sized to keep the existing luminaires in their existing positions horizontally and vertically over the roadway.  In this case, no lighting design is required.

3.	Design temporary lighting system using specified types of luminaires, including the luminaires of the permanent lighting system.  Use a layout pattern, mounting height, and luminaire offset and spacing that provide a light distribution that conforms to AASHTO’s “An Informational Guide for Roadway Lighting” luminance or illuminance methods of design.  Design the system for the roadway’s functional class as specified in the Department’s Annual Traffic Volume Report.

Furnish and install materials and miscellaneous hardware required to provide a functional lighting system, including foundations, branch circuitry, and electrical load centers.  Size the branch conductors to provide a maximum 5% voltage drop at the most remote luminaire.  Materials shall conform to the Specifications.  The illumination cables maybe buried directly provided the cables are listed for direct burial.

Use the following poles.

1.	Existing light poles found within the project limits and scheduled to be salvaged.

2.	Poles from the permanent lighting system.

3.	The following new poles that the Contractor furnishes provided 30 feet difference in elevation between a luminaire and the edge of traveled way is maintained beneath it.

a.	ANSI Class 4 wood poles.  Install outside the clear zone during winter shutdown.  To determine the clear zone, see subsection 1130.02 of the Alaska DOT/PF Highway Preconstruction Manual.

b.	Steel, aluminum, or fiberglass poles that meet design criteria for 80 mph wind speeds according to AASHTO’s 1994 edition of the “Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals”.

c.	Poles that are part of the temporary signal systems.

Furnish temporary electroliers, in service from October 1 through May 15 and located within the clear zone, with an approved yielding type base.  Approved yielding bases consist of FHWA approved slip bases, transformer bases, or frangible couplings.  Install wood poles and other fixed base poles outside the clear zone or behind guardrail or portable concrete barrier that protects against another hazard.

Install temporary electroliers, in service from May 15 through September and located within the clear zone, with approved yielding bases or with fixed bases shielded by 30 feet of barrier and an FHWA approved end treatment.  Provide two-feet of clearance between the barrier and pole.  Consider the costs of furnishing the barrier and an end treatment a subsidiary obligation of Item 660(8), Temporary Electrolier.  Replace fixed base poles that are located within the clear zone and that will remain in service after October 1 with yielding base poles at no expense to the State.

Use the following load centers to energize the temporary lighting and signal systems.  Provide work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

1.	Permanent load centers installed in Plan location.

2.	Existing load centers scheduled to remain intact until completion of the project.  Relocate and reuse existing load centers only if they are approved.

3.	Approved temporary load centers with photoelectrical controlled lighting circuits.  Provide a temporary load center when retiring an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "Suitable for use as service equipment".

660-3.11 HIGH TOWER LOWERING AND LIFTING PLAN SUBMITTAL, REQUIREMENTS AND REVIEW.

- Submit a High Tower Lowering and Lifting Plan as developed by a Consultant at the preconstruction conference.  Attach a resume and a description of the required Consultant qualifications to the Plan.  Submit the Plan to the Division of Labor Standards and Safety, Occupation Safety and Health, of the Alaska Department of Labor for comments.

The Department will have 10 days to review, comment, and accept the first Plan submittal, and 5 days on each subsequent submittal, until the Plan is found to be acceptable.  The Department’s allotted time to review the Plan starts when both the Plan and the Traffic Control Plan according to Section 643 Traffic Maintenance has been submitted.

- The Consultant’s Plan, services, and activities shall follow the guidelines and requirements of ANSI A10.33-1992, American National Standard Construction and Demolition Operations – Safety and Health Program Requirements for Multi-Employer Projects, approved February 6, 1992 and published by the National Safety Council.  This specification does not modify Section 107 of the Standard Specifications for Highway Construction metric edition.  The Consultant shall use ANSI A10.33 for performance of the required tasks.  The Contractor is not required to use or follow ANSI A10.33 for construction operations.

- The scope of work for the application of ANSI A10.33 is the lowering and lifting of the high tower structures.  The Consultant will follow the guidelines of the following sections as found in ANSI A10.33:

3.4.1 Evaluation of Contractor Safety and Health Programs to determine their appropriateness to the specific job site and work to be performed;

3.4.2 Monitoring and documenting the implementation of Safety and Health Programs;

3.7    Special Safety and Health Plan.

5.3    Corrective Action.

7.      Construction Process Plan

8.      Pre-Work Planning

The Project Safety and Health Program and Construction Process Plan as described within ANSI A10.33 as applied to the lowering and lifting of the high tower structure should be considered the same as the Plan.  The Consultant is not the same as the Senior Contractor Supervisor as defined within ANSI A10.33.  The Contractor will provide the Consultant access to the construction sites.

- At a minimum, the information included in the Plan provided shall include:

- a list and the configuration of equipment, tools and material to be used;

- a sketch of each site or the crane set-up where one sketch may represent multiple sites that are similar;

- manpower and manpower qualifications;

- a description of the method and sequencing of the lowering and lifting procedure;

- documentation of crane certification as required by law;

- the necessary equipment and work force to provide a backup system to prevent the fall of a high tower structure should there be a failure of primary lowering and lifting equipment.

- More than one process Plan may be necessary to address differing site conditions from site to site.  Possible Plan differences may include differing site restrictions such as the available working area, differing terrain, highway and ramp slopes, guardrail, highway traffic and nearby private development.

- The high tower pole sections shall be manufactured without picking holes.  Coordinate with the pole manufacturer for load picking points.

- The Plan will need to be coordinated with the Traffic Control Plan at high tower pole sites.  The final Traffic Control Plan approved by the Engineer may have an impact on the Plan.

660-3.12 HIGH TOWER LOWERING AND LIFTING PLAN CONSULTANT QUALIFICATIONS.  The Consultant is to be a Certified Safety Professional (CSP) as certified by the Board of Certified Safety Professionals, with specific knowledge and experience in the lowering and lifting industry, crane and sling operations and safety, fall protection, and knowledge of State and Federal Occupational Safety and Health Standards and applicable regulations.  The Consultant will also demonstrate education in the field of safety, a minimum of 4 years of experience and practice in crane lowering and lifting in cold regions, and a list of 5 prior and similar projects.  The Plan may require the services and certification of a Professional Engineer registered to practice in the State of Alaska, as per ANSI A10.33 Section 3.9 Critical Structures and Complex Processes, and will be dependent on the scope of the lift and weights involved.

660-3.13 IMPLEMENTATION OF THE HIGH TOWER LOWERING AND LIFTING PLAN.

- Ten days before the first lowering event, the Contractor will schedule a meeting and have the Consultant conduct a training session with the Contractor and the Engineer present, to review and explain the accepted Plan.  The Contractor’s and subcontractor’s construction personnel that will be in the field performing the work are also to be present.  The approved Traffic Control Plan will also be reviewed.

- During the first lowering event and again with the first lifting event, the consultant shall conduct a field inspection of the operation and procedure being used by the Contractor, establish compliance with the Plan, to be followed within 3 days by a written report and certify that the Plan is being incorporated.  The report will indicate discrepancies and deviations from the Plan that were found, and the corrective action to be incorporated.  This is the same as ANSI A10.33, Section 3.7, Special Safety and Health Plan and Section 5.3 Corrective Action.

- There are to be 2 additional field inspections and reports by the consultant during the progress of the work:  2 of a lowering activity and 2 of a lifting activity.  These inspections and reports are the same as ANSI A10.33, Section 3.8 Monthly Status Reports, and replaces the monthly requirement.  This brings the total required field inspections to 3 each of lowering and lifting, for a total of 6 inspections and reports.  The fifth and sixth inspection will be considered as the last and final inspections and reports.

660-3.14 HIGH TOWER LOWERING AND LIFTING CORRECTIVE MEASURES BY THE CONTRACTOR.  The Contractor will implement corrective measures.  The Consultant will conduct a follow up inspection and provide a written report on how discrepancies were corrected.

Replace subsection 660-4.01 with the following:

660-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

Item 660(9), Bored Casing.  By the foot measured along a line that connects the centers of the junction boxes located at each end of the bored casing.

Add the following:

Item 660(14A), Temporary Illumination.  Will not be measured.

Item 660(15), Electrolier & Foundation.  By each complete unit installed and accepted.

Item 660(22), Illumination Price Adjustment.  By the mile for each roadway with all or part of its illumination system inoperative.  A divided roadway is considered one roadway.  Ramps are considered a separate roadway.  The Engineer will measure each unlit section less than one mile long as one mile.

Item 660(23), High Tower Electrolier & Foundation.  By each complete unit installed and accepted.

Item 660(24C), 2 inch Polyethylene Conduit.  By the foot along the centerline of pipe complete in place, backfilled, and accepted.

Item 660(24D), 3 inch Polyethylene Conduit.  By the foot along the centerline length of pipe complete in place, backfilled, and accepted.

Item 660(29), Type 1A Junction Box.  By each complete unit installed and accepted.

Item 660(30), Type 2 Junction Box.  By each complete unit installed and accepted.

Item 660(41), High Tower Lowering and Lifting Plan.  Will not be measured.

Item 660(42), High Tower Pole & Foundation Removal.  By each complete unit, removed.

660(43), High Tower Inspection.  Will not be measured.

660(44), High Tower Luminaire Shields.  Will not be measured.

Delete this subsection in its entirety and substitute the following:

660-5.01 BASIS OF PAYMENT.  Sign removal and reinstallation required to install foundations, conduits, and junction boxes is subsidiary.  Minor conduit routing changes as directed are subsidiary to existing contract pay items.  Concrete required to complete the foundations is subsidiary.  If no item for Bored Casing is included in the bid schedule, boring is subsidiary to other items of work.

The amount bid for an item shall includes full compensation for excavation, bedding, and backfill required to install the components shown in the Plans.  Dewatering excavations is a subsidiary obligation of completing the excavation work.

The Engineer will pay for the disposal of surplus and unusable excavation and for imported backfill and bedding material at their respective contract unit prices, or as extra work if the contract does not include these items.

The costs of repairing damage to finishes on new equipment are a subsidiary obligation.

Include payment for removing the existing illumination cables that served the high tower poles removed in other items of work.

The price bid for Item 660(14A) Temporary Illumination, shall include full compensation for furnishing and installing materials needed to form an operational lighting system and for removing materials after making high tower 69 or its replacement operational.

In Item 660(15) Electrolier and Foundation, include payment for installing the two inch conduit and illumination cable between the electrolier and the adjacent junction box and for completing splices.

In Item 660(22) Illumination Price Adjustment, the Engineer will deduct $1275.00 per day from the payments due for each mile of roadway with existing lighting systems that is not kept fully operational.

In Item 660(23) High Tower Electrolier and Foundation, include payment for completing the work to:

- Install the three inch rigid metal conduit and illumination cable between the high tower pole and the adjacent junction box.

- Install the number of luminaires specified, regardless of the quantity.

In Items 660(24C) 2-Inch Polyethylene Conduit, and Item 660(24D) 3 Inch Polyethylene Conduit, include payment for completing the work to:

- Install the illumination cables specified, regardless of the size or quantity of cables.

- Install bare grounding conductors equal in size to the largest ungrounded line conductor contained in the conduit.

Items 660(29) Type 1A Junction Box, and 660(30) Type 2 Junction Box, will be paid at the contract unit price for each unit installed and accepted.

Item 660(41) High Tower Lowering and Lifting Plan will be paid at the lump sum price.  The costs for additional work by the Consultant to report on and describe corrective measures, to participate in correcting the discrepancies, and to provide a written report back to the Engineer on corrective activities, will be considered incidental to this item.

Item 660(42) High Tower Pole and Foundation Removal will be paid for at the contract unit price.  This price includes costs associated with the removal and disposal of the poles and foundations.

The bid price for item 660(43) High Tower Inspection, shall include full compensation for

- Removing high tower 69 from its foundation.

- Disassembling the pole to complete the visual inspection of the holes and radiographic testing of the longitudinal welds.

- Furnishing timbers to support the disassembled pole.

- Completing the weld inspection specified.

- Generating a report summarizing the condition of high tower 69.

- Repairing the pole’s finish that was removed to complete the ultrasonic and magnetic particle inspections with zinc rich and matching colored paints.

- Complete reassembly of the pole and lowering device.

- Reinstalling high tower 69 on its foundation and making it operational.

From 660(44) High Tower Luminaire Shields, the Engineer will pay the Contractor to furnish and install luminaire shields fabricated by the luminaire manufacturer, including the costs of designing the shields, if necessary.  The Engineer will pay for the costs of the surveying required to design the shields using Item 642(3) Three Person Survey Party.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

660(14A) 	Temporary Illumination	Lump Sum

660(15) 	Electrolier & Foundation	Each

660(22) 	Illumination Price Adjustment 	Contingent Sum

660(23) 	High Tower Electrolier & Foundation 	Each

660(24C) 	2 inch Polyethylene Conduit	Foot

660(24D) 	3 inch Polyethylene Conduit	Foot

660(29) 	Type 1A Junction Box 	Each

660(30)	Type 2 Junction Box 	Each

660(41)	High Tower Lowering and Lifting Plan 	Lump Sum

660(42) 	High Tower Pole & Foundation Removal 	Each

660(43)	High Tower Inspection	Lump Sum

660(44)	High Tower Luminaire Shields	Contingent Sum

SECTION 661

# ELECTRICAL LOAD CENTERS

Special Provisions

Add the following subsection:

661-1.03 EQUIPMENT LIST (S) AND DRAWINGS.  Within 30 days following award of the contract, submit 4 collated copies of a portfolio of equipment and material to be installed.  The Department will review these for approval.  The portfolio(s) shall consist of a table of contents which includes each item’s intended use(s) and the following:

1.	For materials on the Approved Products List: a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

2.	For materials not on the Approved Products List:  catalog cuts that include the manufacturer’s name, type of product, size, model number, conformance specifications, and supplemented by other data as may be required, including manufacturer’s maintenance and operations manuals, or sample articles.

This information may be included in the portfolio for 660 items.

The Department will not be liable for material purchased, labor performed, equipment used, or delay to the work before equipment and materials have been reviewed and approved.

661-2.01 MATERIALS.  Add the following to the paragraph titled Meters: Furnish meter sockets and landing pads rated for 200 ampere services.

661-5.01 BASIS OF PAYMENT.  Add the following: Payment of fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be considered incidental to the Section 661 items.

SECTION 710

FENCE AND GUARDRAIL

# Special Provisions

710-2.03 CHAIN LINK FABRIC. Change Class D coating to Class C coating. (9/13/04)R273usc04

710-2.11 GUARDRAIL TERMINALS.  Add the following:

Use the ET-2000 LET.

The current guardrail end terminal drawings approved by the Department are as follows:

# Drawing	Original	Latest

# Number	Date	Revision	Comments

# ET-2000 LET	English	SS 155	5/18/00	None	37.5’, 7 tube, Plus head

## (01/22/02)R24

## SECTION 740

### SIGNALS AND LIGHTING MATERIALS

Special Provisions

Replace subsection 740-2.02 with the following:

740-2.02 SIGNAL AND LIGHTING POLES.  Design and fabricate highway lighting and traffic signal structures with pole shaft lengths to 55 feet long to conform to the 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions.  For the design and fabrication of high tower poles, see subsection 740-2.04.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations.  Submit the stamped drawings and calculations for each pole to the Engineer for approval.  Design for stresses on the completed structure with hardware in place.

1.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole and mast arm, including:  design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

2.	On the stamped shop drawings, provide design wind speed and the details for building the poles and mast arms, including:  materials specifications, slip fit joint dimensions, pole component dimensions, welds that will be made, and the welding inspection that will be done.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

Design poles for 100 mph winds with a 1.3 gust factor.

Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 feet above the base of the pole.

Fabricate signal and lighting structures from tapered steel tubes with a round or 16 sided cross section.  Orient hand holes located near the base of poles to face down-stream of traffic flow.

Furnish poles and mast arms up to 40 feet long in one piece.  Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice.  For slip type joints, provide a minimum overlap of two feet or 1.5 times the inside diameter of the female section whichever is larger.

With two piece mast arms, locate the slip type field splice at least one foot away from the plan location of signal heads and signs.

Fabricate tubes with walls up to ½ inch thick from the prequalified base metals listed in AWS D1.1 and which feature maximum yield strengths of 70,000 psi.  Fabricate elements greater than ½ inch thick from steel that conforms to ASTM A 709 and meets the Fracture Critical Impact Test requirements for zone 3.  The Department will not accept structures that contain or are made with laminated steel elements.

Fabricate each tube from no more than 2 pieces of steel.  When using 2 pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from two inch nominal schedule 40 pipe that conforms to ASTM A 53 Grade B.

Fabricate 10 feet long signal posts from 11 US Standard Gage sheet steel.  Fabricate each post with a minimum inside diameter of five inches at the base plate.  Use a 3½ inch long piece of four inch nominal schedule 40 pipe that conforms to ASTM A 53 Grade B as a post top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms.  To add lift points, weld them at least 12 inches away from welds on the outside of female segments and on the inside of male segments.  Before shipment, remove added lift points, grind the area smooth with the base metal, and hot stick repair the finish according to subsection 660-3.01.8.a.

Hot-dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications.  Completely submerge pole and mast arm segments in one dip in a kettle of concentrated zinc ammonium chloride flux solution heated to 130 oF, then completely submerge in one dip in a separate kettle of prime western grade zinc heated to approximately 825 oF.  Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove excess zinc from drip lines and points and the surfaces of tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

1.	Not fabricated according to these specifications or the approved shop drawings,

2.	Bowed with sweeps exceeding ¾ inch throughout the length of the pole, mast arm, or segment, if furnishing a two-piece pole or mast arm,

3.	Out of round.  Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed two percent of the dimension specified on the shop drawings.

Fabricate pile cap adapters from Grade 3 pipe pile that conforms to ASTM 252 and from steel plate that conforms to ASTM A 709 Grade 50.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Fabricate the anchor plate to match the base plate of the lighting standard.

Perform welding to conform to subsection 504-3.01 8.  Welding and the following:

1.	Make welds continuous.

2.	Use partial joint penetration (PJP) welds in longitudinal seams.  PJP welds must provide at least 60% penetration.

3.	Use CJP groove welds to connect base plates to tubes with walls 5/16 inch thick and thicker. When CJP groove welds are used, the designer may use additional fillet welds when deemed necessary.

4.	Use socket-type joints with two fillet welds to connect base plates to tubes with walls less than 5/16 of an inch thick.

5.	On steels 5/16 of an inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

6.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.  In steels less than 1/8 inch thick, complete the tests according to AWS D1.3.

7.	Only visually inspect welds made on luminaire mast arms.

Finish poles and mast arms to conform to the following requirements.  Before they are galvanized, neatly round the following features to the radius specified

1.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both edges,

2.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on other exposed edges,

3.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus six inches do two things: grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces, and

4.	Grind exposed welds flush with the base metal, except fillet welds and seam welds on top of mast arms.  Grinding seam welds on multi-sided poles is not required, except in slip type joints.

Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1.  The measurements shown are for illustration purposes only.  Use tags large enough to include required information using ¼ inch high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text.  Secure the tags with two 1/8 inch blind rivets at the base of poles and the under side of mast arms.  If furnishing a two-piece signal mast arm with slip type joint, mark both pieces with the same message.

# TABLE 740-1

#### POLE MARKINGS

| Note: Italic type indicates additional Tag Markings if poles have 2 luminaire or 2 signal mast arms. |  |  |
| --- | --- | --- |
|  | MEASUREMENTS | TAG MARKINGS |
| Signal Poles |  |  |
| a) Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| b) Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| c) Pole height | 36 ft. | PH 36 |
| d) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| e) Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| f) Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| a) Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| b) Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| a) Mast arm length | 40 ft. | SMA 40 |
| b) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| c) Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| d) Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| a) Mast arm length | 18 ft. | LMA 18 |
| b) Pole number (if unique arm design) |  | P 4 |

740-2.03 WOOD POLES.  Replace the last sentence with the following: For wood poles that are not to be painted after fabrication, furnish treated wood poles that meet Section 714.

Replace subsection 740-2.04 with the following:

740-2.04 HIGH TOWER POLES.  Design and fabricate high tower lighting poles to conform to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations.  Submit the stamped drawings and calculations for each pole to the Engineer for approval.  Design for stresses on the completed structure with hardware in place.

1.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole, including:  design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

2.	On the stamped shop drawings, provide the criteria to which the poles are designed and the details for building the poles, including:  materials specifications, slip fit joint dimensions, dimensions of the tube segments and other components, the total weight of each segment, the welds that will be made, and the welding inspection that will be done.

The pole manufacturer shall submit a pole installation plan that details the work required to assemble each pole, the locations of timber supports during and after pole assembly.  Submit this plan with the stamped plans and calculations.

Submit the mill certifications for steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

Design high tower poles for a 50-year design life and the basic wind speed shown in the 2001 AASHTO Standard Specifications for Structural Supports or for 100 mph, whichever is greater.  Use a gust effect factor of 1.14.

For fatigue design, use fatigue category I importance factors for lighting poles, and design poles that taper less than 0.14 inches of diameter per foot to resist the effects of vortex shedding.

Furnish poles fabricated from tapered steel tubes with a round, 16 sided, or 12 sided cross section.  Use no more than four tapered-tube segments with slip type field splices to form each pole.  For the slip type joints, provide a minimum overlap of 24 inches or 1.5 times the inside diameter of the female section whichever is larger.

Furnish poles that allow the luminaire ring to descend within five feet of the base plate.

Design poles to support a load that consists of the lowering device and ten luminaires equipped with light shields.  Use the following values for these components.

Component	Effective Projected Area	Weight

One lowering device	8.6 ft2	309 lbs

Ten luminaires	21.5 ft2	617 lbs

Ten light shields	30.0 ft2	22 lbs

Provide a reinforced rectangular hand hole that provides an opening large enough to install the winch assembly.

Provide a detachable door over the hand hole frame including hinges, nuts to fasten the door to the frame, and a neoprene gasket to provide a watertight seal around the frame.  Provide for a locking mechanism for the hand hole door.

Fabricate the base plate to match the bolt circle diameter and the quantity and size of anchor bolts of the foundation detailed on the Plans.  The anchor bolts conform to ASTM F 1554, Grade 55 with Supplemental Impact Test Requirements of Section S4.  The distance from bottom of the leveling nut to the top of the concrete of the anchor bolts will not exceed one inch.

Install a hook to the left of the hand hole for storing the winch control cable away from the top of the foundation.  Provide a one-inch wide hook that features rounded edges, a 1½ inch radius, and three inches between the low point and free end of the hook.

Fabricate tubes with walls up to ½ inch thick from the prequalified base metals listed in AWS D1.1 and which feature maximum yield strengths of 70,000-psi.  Fabricate elements greater than ½ inch thick from steel that conforms to ASTM A 709 and meets the Fracture Critical Impact Test requirements for zone 3.

Fabricate each tube from no more than 2 pieces of steel.  When using 2 pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent segments to form continuous straight seams from the base to the top of the pole.  The Department will not accept poles and mast arms made with laminated steel elements.

The Department does not allow holes made for lifting purposes in the ends of tubular segments.  To add lift points, weld them at least 12 inches away from welds on the outside of female segments and on the inside of male segments.  Before shipment, remove added lift points, grind the area smooth with the base metal, and hot stick repair the finish according to subsection 660-3.01.8.a.

Provide the mounting brackets needed to install the luminaire-ring lowering device, including the winch assembly, associated hardware, and the masthead assembly.

Around the top of each pole, provide a stabilizer system that prevents the luminaire ring from swinging freely when the top of the ring is within 24 inches of being fully docked in the masthead fitting.  The stabilizer system shall consist of at least three crooked-F shaped brackets located symmetrically around each pole.  The brackets shall form a tapered bottom section and a parallel top section that restricts ring movement.  Bolt each bracket to two channels welded to the pole shaft. With the Eagle lowering device, locate the brackets between the wheels that line the luminaire ring. Design and fabricate the brackets from stainless steel tubing to withstand the load and wind speed used to design the poles.  The installed brackets shall just fit through a circle two inches smaller in diameter than the inside diameter of the luminaire ring.

Perform welding to conform to subsection 504-3.01 8.  Welding and the following:

1.	Make welds continuous.

2.	Use CJP groove welds on longitudinal seams within six inches of CJP circumferential welds.

3.	In the ends of those segments that form a slip type joint, provide CJP longitudinal seam welds at least 12 inches longer than the length of the joint.

4.	Use CJP groove welds to connect base plates to tubes with walls 5/16 inch thick and thicker. When CJP groove welds are used, the designer may use additional fillet welds when deemed necessary.

5.	Use socket-type joints with two fillet welds to connect the pole top plates to tubes with walls less than 5/16 inch thick.

6.	Use partial joint penetration (PJP) welds in longitudinal seams between the segments of CJP welds.  PJP welds must provide at least 60% penetration.

7.	Use PJP and fillet welds to attach hand hole frames to the tube.

8.	On steels 5/16 inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

9.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.

Weld tags on the ends of segments that form slip type joints to facilitate field assembly.  Locate the tags to ensure segment alignment when the tags are aligned.  Attach the tags at least 12 inches away from the slip type joint.  Include the shop drawing number to which the poles are fabricated and pole length on the tag.

Finish poles to meet the following requirements.  Before they are galvanized, neatly round the following features to the radius specified

1.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both edges,

2.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on other exposed edges,

3.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus six inches do two things: grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces, and

4.	Grind exposed welds flush with the base metal, except fillet welds and seam welds on top of mast arms.  Grinding seam welds on multi-sided poles is not required, except in slip type joints.

The Department will reject poles containing segments that

1.	Are not fabricated according to these specifications and the approved shop drawings,

2.	Are bowed with sweeps exceeding ¾ inch throughout the length of the segment,

3.	Are out of round.  Segments are out of round when the diameters of round members or the dimension across the flats of multi-sided members exceed two percent of the dimension specified on the shop drawings.

4.	Do not provide the minimum overlap of 24 inches or 1.5 times the inside diameter of the female section, whichever is larger, in the slip type field splices when the pole is assembled.

Hot-dip galvanize pole segments and attachments to meet AASHTO M 111 and these specifications.  Completely submerge pole segments in one dip in a kettle of concentrated zinc ammonium chloride flux solution heated to 130 oF, then completely submerge in one dip in a separate kettle of prime western grade zinc heated to approximately 825 oF.  Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove excess zinc from drip lines and points and the surfaces of tube ends that form slip type joints to provide a smooth finish.

Delete this subsection in its entirety and substitute the following:

740-2.06 ELECTRICAL CONDUIT.

1.	Rigid Metallic Conduit.  Use UL Standard UL-6 galvanized conduit and fittings that are rigid metal type and manufactured of mild steel according to ANSI Standard C80.1.

2.	Rigid Nonmetallic Conduit.  For loop detectors, use UL Standard UL-651 Schedule 80 rigid polyvinyl chloride (PVC) conduit.  Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL 651 B.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle.  Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline.  The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it.  The movements include:  axial expansion or contraction to ¾ inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to ¾ inch.  The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

Replace subsection 740-2.18 with the following:

740-2.18 ROADWAY LUMINAIRES.  Furnish luminaires that meet the following specifications and provide the light distributions specified.  When luminaire performance criteria are specified, luminaires shall also:

- Meet or exceed the minimum initial light levels indicated.

- Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified:  luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 2000.

Furnish each luminaire with a high pressure sodium lamp of the wattage specified and matching ballast with an input voltage equal to circuit voltage.  Furnish lamps that feature a rated life of 24,000 hours based on 10 hours per start and ballasts that conform to subsection 740-2.21.

Install luminaires that feature:

1.	Corrosion-resistant enclosures with gray paint finish and space for the ballast.

2.	Third party certification for use in wet locations.

3.	Glass lenses, unless polycarbonate resin refractors are specified.

4.	Terminal blocks for attaching the illumination tap conductors.

5.	Aluminum reflectors with an ALZAK or ALGLAS finish.

6.	Optical components free of substances that affect photometric performance, e.g. paint.

7.	Housings cast with no provision for a photoelectric control receptacle.

8.	Airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components.  Gasket material must withstand the temperatures involved and be securely held in place.

9.	Plug-in starting aids in fixtures with lamps up to 400 watts.

Cobrahead luminaires shall also include:

- An easily removed hinged door used exclusively for mounting the ballast.

- A second door that frames the lens, hinges on the house side, and fastens on the street side with an automatic type latch.

- Four-bolt mounting brackets that fit two-inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit two inch nominal diameter standard pipe and feature a wireway meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

High tower luminaires shall also include:

1.	1,000 watt, high pressure sodium lamps that provide 140,000 minimum initial lumens.

2.	A side entry four-bolt mounting bracket designed for two inch nominal diameter pipe with provision for leveling the luminaire.

3.	A die cast aluminum housing attached to the mounting bracket, which provides a weather tight enclosure for the ballast and terminal block and is readily removable without removing the luminaire from the bracket arm.

4.	A cover and reflector that readily detaches from the mounting bracket without removing the luminaire from the bracket arm.

5.	Double fused 480-volt ballasts with fuses sized by the luminaire manufacturer.

6.	A hinged lens compatible with add on light shields.

7.	A stainless steel lamp clamp to prevent lamps from loosening, which is separate from the socket.

When the Plans specify shielding areas from illumination, install light shields on luminaires on high tower poles whose templates touch the shielded areas.  Provide shields that limit light levels to 0.1 footcandle or less at the right of way line.  Whenever stock shields fail to limit light levels to the 0.1 footcandle level, hire the luminaire manufacturer to custom design and fabricate shields.  If the first generation of custom fabricated shields fail to limit light levels to the 0.1 footcandle level, the Engineer may waive the 0.1 footcandle requirement.

740-2.20 ILLUMINATION CONTROL.  Replace the third paragraph with the following: Furnish units for illuminated signs that have a “turn-on” level of between 20 and 25 footcandles.  (“Turn-on” level specified above corresponds to a switching level of approximately 40 to 50 footcandles measured in the horizontal plane.)  "Turn-off" level must not exceed 3 times “turn-on” level.

Delete item 2.

740-2.21 BALLASTS.  Replace the first paragraph with the following: Include ballasts for high intensity discharge lamps rated for the voltages and lamp types specified.  Furnish ballasts with starting currents less than operating currents.

Replace the forth and fifth paragraph with the following: For luminaires equipped with 1000 watt high pressure sodium lamps, furnish auto-regulator ballasts that provide a maximum 30% lamp regulation spread, a minimum 35% voltage dip tolerance, and with nominal line and lamp voltages regulate lamp output to within 5% of the ballast design center.

For soffit luminaires, furnish ballasts with mounting brackets and terminal blocks for primary connections.  Furnish flush mounted luminaires with the lamp sockets preconnected to the secondary.  With suspended luminaires, furnish ballasts with terminal blocks for both primary and secondary connections.

Replace subsection 740-2.22 with the following:

740-2.22 HIGH TOWER LUMINAIRE LOWERING SYSTEM.  Furnish an integral luminaire lowering device that is compatible with the high tower design and consists of a head frame assembly, luminaire ring assembly, and winch assembly complete with electric motor.

Provide a technician employed by the lowering device manufacturer, who has a minimum three years experience installing the lowering device, to

1.	Teach each crew that assembles the lowering device how to complete the work on the first pole,

2.	Oversee the assembly work on the next three poles or until the technician can assure the Engineer the crew can correctly assemble the lowering devices,

3.	Teach each crew how to initially adjust each lowering device on the first pole installed,

4.	Oversee the adjustment work on the next three installed poles or until the technician can assure the Engineer the crew can correctly adjust the lowering devices,

5.	Come back to teach each new crew how to assemble and adjust the lowering system components, if the installation crews change, and

6.	Make intermediate and final adjustments to lowering devices installed under the contract at three, six, and twelve month intervals after the State has accepted the high tower poles.

Furnish a complete service manual with instructions on installation, operation, and maintenance for each lowering device, winch assembly, and power drive system furnished on the project.

Install one of the following high mast lowering devices wired for a single circuit, rated 480 VAC single-phase, on each high tower pole shown on the Plans.  Furnish power cords with four #8 AWG conductors.

Furnish each luminaire ring assembly with guide cones (Millerbernd) or tapered positioning pins (Eagle) painted a safety orange color for their full length.  Use a two component, water borne epoxy paint with gloss finish that applies to galvanized steel and provides a tough, abrasion resistant coating rated for exterior use.  Complete work according to the paint manufacturer’s written instructions, including: preparing the surfaces and tinting, mixing, and applying the paint.

Manufacturer	Model No.	Options to be furnished

Eagle High Mast Lighting Co.	ELC-XX-GV	Hot dip galvanized masthead assembly and transition plate, and integral motor

Millerbernd Manufacturing	SSLD-2	Integral winch and motor assembly

Manufacturers shall meet third party certification.

The Plans will indicate the number of luminaires on each pole, each pole’s height, and whether FAA approved obstruction lights are required.

#### APPENDIX A

EROSION & SEDIMENT CONTROL

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST