PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

STANDARD SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2002 (USC)

OLD GLENN HIGHWAY

NORTH EAGLE RIVER TO FIRE LAKE

STP-0558 (5) / 56221

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements.

d.	The Standard Specifications for Highway Construction 2002 USC units may be viewed or downloaded at no charge from the Statewide Design and Engineering Service Division’s external website.

e.	Geotechnical Report Titled Geotechnical Report Stations 187-220 North Eagle River Access to Fire Lake Old Glenn Highway Rehabilitation North Eagle River to Peter’s Creek, Alaska, dated March 2003.

3	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

4	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

5.	The Materials Certification List (MCL) has been included in Appendix D.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

TABLE OF CONTENTS

Section 101 Definitions and Terms	1

Section 102 Bidding Requirements and Conditions	2

Section 103 Award and Execution of Contract	3

Section 105 Control of Work	6

Section 106 Control of Material	12

Section 107 Legal Relations and Responsibility to Public	15

Section 108 Prosecution and Progress	18

Section 109 Measurement and Payment	19

Section 120 Disadvantaged Business Enterprise (DBE) Program	20

Section 201 Clearing and Grubing	30

Section 202 Removal of Structures and Obstructions	31

Section 203 Excavation and Embankment	33

Section 301 Aggregate Base Course	35

Section 306 Asphalt Treated Base Course	37

Section 310 Recycled Asphalt Pavement Base Course	40

Section 407 Stone Mastic Asphalt Concrete Pavement	42

Section 603 Culverts and Storm Drains	61

Section 604 Manholes and Inlets	63

Section 608 Sidewalks	64

Section 609 Curbing	67

Section 615 Standard Signs	68

Section 616 Thaw Pipe and Thaw Wires	69

Section 618 Seeding	70

Section 620 Topsoil	72

Section 635 Insulation Board	73

Section 639 Approaches	75

Section 642 Construction Surveying and Monuments	76

Section 643 Traffic Maintenance	77

Section 644 Services to be Furnished by the Contractor	81

Section 645 Training Program	83

Section 646 CPM Scheduling	87

Section 647 Equipment Rental	88

Section 660 Signals and Lighting	90

Section 670 Traffic Markings	100

Section 703 Aggregates	103

Section 712 Miscellaneous	105

Section 724 Seed	106

Section 726 Topsoil	107

Section 730 Sign Materials	108

Section 740 Signals and Lighting Materials	109

Appendix A	Permits / Temporary Construction Permits
Appendix B	Erosion and Sediment Control Plan
Appendix C	Construction Surveying Requirements
Appendix D	Materials Certification List
Appendix E	Sign Details
Appendix F	Utility Company Requirements

Section 101
Definitions and Terms

Special Provisions

101-1.03 DEFINITIONS. Add the following definition:

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the No. 200 screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11on minus 3 inch material.

(11/29/01)R1USC

Section 102
Bidding Requirements and Conditions

Special Provisions

102-1.10 ADDENDA REQUIREMENTS. Delete this Subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form.

(10/23/02)R171USC02

Section 103
Award and Execution of Contract

Special Provisions

103-1.06 INSURANCE REQUIREMENTS. Delete this Subsection in its entirety and substitute the following: The Contractor shall provide evidence of insurance with an insurance carrier or carriers satisfactory to the Department covering injury to persons and property suffered by the State of Alaska or by a third party as a result of operations under this contract by the Contractor or by any subcontractor. The Contractor's insurance shall provide protection against injuries to all employees of the Contractor and the employees of any subcontractor engaged in work under this Contract. All insurance policies (a) shall comply with AS 21 and (b) shall be issued by insurers that (i) are licensed to transact the business of insurance in the State of Alaska under AS 21 and (ii) have a financial rating acceptable to the Department. The Contractor shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.

Where specific limits and coverages are shown, it is understood that they shall be the minimum acceptable. The requirements of this subsection shall not limit the Contractor’s indemnity responsibility under Subsection 107-1.13. Additional insurance requirements specific to this contract are contained in the Special Provisions, when applicable.

The Contractor shall maintain the following policies of insurance with the specified minimum coverages and limits in force at all times during the performance of the Contract:

1.	Workers' Compensation: as required by AS 23.30.045, for all employees of the Contractor engaged in work under this Contract. The Contractor shall be responsible for Workers' Compensation Insurance for any subcontractor who performs work under this Contract. The coverage shall include:

a.	Waiver of subrogation against the state and Employer's Liability Protection at $500,000 each accident/$500,000 each disease;

b.	“Other States” endorsement if the Contractor directly utilizes labor outside of the State of Alaska;

c.	United States Longshore and Harbor Workers’ Act Endorsement, whenever the work involves activity over or about navigable water; and

d.	Maritime Employer’s Liability (Jones Act) Endorsement with a minimum limit of $1,000,000, whenever the work involves activity form or on a vessel on navigable water.

2.	Commercial General Liability: on an occurrence policy form covering all operations with combined single limits not less than:

a.	$1,000,000 Each Occurrence;

b.	$1,000,000 Personal Injury;

c.	$2,000,000 General Aggregate; and

d.	$2,000,000 Products-Completed Operations Aggregate.

3.	Automobile Liability: covering all vehicles used in Contract work, with combined single limits not less than $1,000,000 each occurrence.

4.	Umbrella Coverage: for Contract amounts over $5,000,000 not less than $5,000,000 umbrella or excess liability. Umbrella or excess policy shall include products liability completed operations coverage and may be subject to $5,000,000 aggregate limits. Further, the umbrella or excess policy shall contain a clause stating that it takes effect (drops down) in the event the primary limits are impaired or exhausted.

The State of Alaska shall be named as an additional insured on policies required by paragraphs 2 thru 4 above. All of the above insurance coverages shall be considered to be primary and non-contributory to any other insurance carried by the State of Alaska, whether through self-insurance or otherwise.

In any contract or agreement with subcontractors performing work, the Contractor shall require that all indemnities and waivers of subrogation it obtains, and any stipulation to be named as an additional insured it obtains, shall also be extended to waive rights of subrogation against the State of Alaska and to add the State of Alaska as an additional named indemnitee and as an additional insured.

The apparent low bidder shall furnish evidence of insurance to the Department before award of the Contract. The evidence shall be issued to the Department and shall be either a certificate of insurance or the policy declaration page with all required endorsements attached and must:

1.	Denote the type, amount, and class of operations covered;

2.	Show the effective (and retroactive) dates of the policy;

3.	Show the expiration date of the policy;

4.	Include all required endorsements; and

5.	Be executed by the carrier's representative.

When a certificate of insurance is furnished, it shall contain the following statement:

“This is to certify that the policies described herein comply with all aspects of the insurance requirements of (Project Name and Number). The insurance carrier agrees that it shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.”

The Department’s acceptance of deficient evidence of insurance does not constitute a waiver of Contract requirements.

Failure to maintain the specified insurance or to provide substitute insurance if an insurance carrier becomes insolvent, is placed in receivership, declares bankruptcy, or cancels a policy may be grounds for withholding Contract payments until substitute insurance is obtained, and may, in the Department's discretion, be grounds for declaring the Contractor in default.

(05/06/03)R271USC02

Section 105
Control of Work

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following:

The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar Alaska Native Hospital Anchorage Water & Wastewater Utility AT&T Alascom, Inc. Chugach Electric Association Digline - Boise loan to AK ENSTAR Natural Gas, Inc. GCI Marathon Oil Corporation Matanuska Electric Association Matanuska Telephone Association PTI Communications, Inc. ACS of the Northland Phillips Petroleum Rogers Cable Systems of AK, Inc. Signature Flight Support SOA-DOT/PF Anchorage M&O TelAlaska, Inc. Tesoro Petroleum Co. Unocal Oil & Gas

The Contractor shall call the following utilities and agencies directly:

DOT/PF Maintenance and Operations	235-5217

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the Plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

1.	Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

2.	Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific coordination requirements for the specific utilities are included below:

(05/31/01)R3M98

The Contractor will be required to provide each utility fifteen (15) calendar days advance written notice of any relocation work to begin.

1.	MATANUSKA ELECTRIC ASSOCIATION (MEA): MEA has existing buried and overhead primary circuits running within the Old Glenn Highway (OGH) corridor. Some of these facilities are located in easements outside the highway right-of-way; others are located within the right-of-way. MEA will be relocating facilities located west of the OGH near the intersection of North Eagle River Access Road. A primary underground feed crosses the OGH near Station 190+90.  This crossing includes a second cable installed by Tab Electric in the same trench. The contractor is expected to work around this crossing.

The primary underground crossing for MEA provides a feed to a 3∅ junction box located at approximately Station 190+58, 90 feet left. A service line runs from the J-box to a single phase pad mount transformer located beside the J-box. The 1∅ service provides power to AWWU facilities located near Station 188+75, 110 feet left.  Another service line extended from the J-box west to a portable sales office located outside the right-of-way. MEA will relocate the single-phase transformer approximately 70 feet further west to a location just outside the Old Glenn Highway right of way and will replace the underground service to the AWWU load center.  MEA will abandon underground cable in place, including the temporary service (cable and corflo) to the portable sales office.  Materials abandoned in place may be removed by the Contractor if desired and if the Contractor has verified the status (active or abandoned) of facilities. MEA’s relocation work is required because of a conflict between underground facilities and the proposed pathway construction. The relocation work will need to be coordinated with the Contractor’s work in this area.  The Contractor shall notify MEA by fax with at least 14 calendar days lead time to arrange the start of MEA’s relocation work and shall allow 15 working days for MEA to complete the work.

Additional work to be performed by MEA includes providing service to two new load centers proposed at Station 208+32.4, 101 RT and Station 208+37.1, 101 RT.  The Contractor shall notify MEA by fax with at least 14 calendar days lead time to arrange the start of MEA’s service connection work and shall allow 15 working days to complete.

The MEA contact is Sterling Larson at (907) 761-9281.  The MEA fax number for written notification is (907) 761-9339.

2.	ENSTAR NATURAL GAS COMPANY (ENSTAR): Enstar relocation work will be conducted within the Old Glenn Highway project limits and will need to be coordinated with the Contractor’s work. An existing 4” Steel transmission pipeline is in conflict with the proposed storm drain improvements and with excavation limits throughout the project, right of centerline.  This line will be abandoned from North Eagle River Access Road north through the project limits.  The Department’s contractor will be required to work around the existing 4” steel transmission line until the installation is ready to be abandoned.  Enstar requires 25 calendar days to prepare for abandoning the transmission line within the project limits.

Conflicts with Enstar’s 4” steel distribution gas line occur from Station 202+33 to the end of project, right of centerline. This 4” line will be abandoned and replaced with a 6” plastic line in a new alignment within the State right-of-way to the east of the proposed road improvements.  The 6” plastic gas line will reconnect to the 4” steel distribution main north of West Lake Ridge Drive, at approximately Station 220+90, 17 feet right.  New service connections will be installed from the new 6” distribution main, crossing the Old Glenn Highway near Station 205+54 (connecting to existing ~ 23’ right) and near Station 211+50. Enstar requires 25 calendar days to complete relocation of distribution facilities within the project limits.

The Contractor shall allow Enstar 50 consecutive days to complete the overall relocation work, including work within the project limits and work outside the project limits that is required to enable them to abandon both transmission and distribution facilities within the project area. Enstar will provide written notice to the Contractor through the Department when this line has been abandoned.

Enstar will not be responsible for any facilities that are abandoned in place. Any further disposal, if required, will be the responsibility of the Contractor and shall be paid for under Item 202(16) Removal of Gas Pipe.

Prior to commencement of construction Enstar Natural Gas Company will perform a cathodic protection sweep to verify that the system is in working order. Problems found at that time will be the responsibility of the Utility. A second sweep will be performed after all underground work has been completed, but prior to paving. The Contractor shall, in writing, give the utility four (4) calendar days notice to proceed and shall allow one (1) day for each sweep to be performed. Should either sweep detect a ground fault, the Contractor shall allow the utility time to repair the fault. If the ground fault is determined to be caused by the Contractor’s actions, the cost of repair shall be charged to the Contractor by the Utility.

When working near Enstar Natural Gas facilities, the Contractor shall adhere to the requirements set forth in “Safety Requirements for Excavation Adjacent to Natural Gas Pipelines”, attached to these specifications in Appendix F.

Enstar’s contact is Steve Cooper at (907) 264-3712.

3.	MATANUSKA TELEPHONE ASSOCIATION (MTA): Conflicts exist with MTA lines within the project limits.  MTA will be relocating telecommunications facilities.

North of the North Eagle River Access Road, a duct system will be relocated due to conflicts with the proposed bike path near Station 11+70.  An existing 6-24 direct bury will be abandoned in place at this location and a new feed for the nearby AWWU intertie facility will be installed. The Contractor shall allow MTA 7 calendar days to complete work in this location.

Additional conflicts exist within the Old Glenn Highway right-of-way from approximately Station 207+30 to 209+50, right, near cut slope limits.  The existing fiber optic cable will be lowered as required within the same alignment. The Contractor shall allow 7 calendar days to work with MTA in this location. The Contractor’s work includes providing slope stakes to determine the extent of backslope excavation in proximity to MTA’s fiber optic cable. Once staked, MTA will determine how much of the fiber optic cable is affected and will lower that portion in conflict with excavation limits.

Along the west side of the Old Glenn Highway right-of-way, a 600 pair cable will be abandoned in place from approximately Sta. 208+50 continuing to the end of project. MTA will install new underground facilities five (5’) feet inside the west right-of-way line from approximately Sta. 213+00 to the end of project.  The new facilities include multi-denominational (600, 100 and 300) line pair within conduit.  MTA will bore around existing power poles (near Station 215+35 and 217+28, left) to avoid undermining the poles and guy anchors for electric and/or cable television facilities located on the poles. The Contractor shall allow MTA 21 calendar days to complete work in this location.

The MTA relocation work will be conducted within the Old Glenn Highway project limits and will need to be coordinated with the Contractor’s work.  The Contractor shall provide notification to MTA with at least 14 calendar days lead time before the start of MTA relocation work and shall allow MTA 35 calendar days to complete their work.

MTA contact is Ed Powell at (907) 761-2534.

4.	ANCHORAGE WATER AND WASTEWATER UTILITY (AWWU): Adjustments will be made to existing AWWU facilities and insulation will be installed to protect two existing sewer mains and one existing water main. This work will be performed by the Department’s Contractor.

A preconstruction inspection of existing facilities shall be scheduled with AWWU and the Engineer to witness and document the condition of existing valves and valve boxes prior to adjustment.  The Contractor shall provide AWWU 48 hours advance written notice of the scheduled field inspection and provide the Engineer with a copy.

AWWU shall locate and inspect the existing valve and valve box to insure it is in working order.  Cleaning or repair to the valve or valve box prior to adjustment will be accomplished by AWWU at no cost to the Contractor.  Failure of the Contractor to schedule and participate in the valve and valve box inspection shall result in the Contractor forfeiting all rights to claim that the valves were damaged prior to construction.

If AWWU finds a valve or valve box damaged or otherwise rendered inoperable at any time after the inspection as described above, the Contractor shall repair the damage at his expense.

The Contractor shall schedule a final field review with AWWU and the Engineer upon completion of the valve box and manhole adjustments.

The Department’s Contractor will be responsible for the furnishing of traffic control and personnel to assist AWWU while locating and performing the pre-construction and post-construction inspections.

AWWU will be relocating a 4” force sewer main crossing the Old Glenn Highway near Station 199+93 and connecting to the existing 24” sewer main approximately 60 feet right.  AWWU will complete this relocation prior to May 15, 2003.  Coordination by the Department’s Contractor with AWWU will be required.  The AWWU contact is Brian Baus at 564-2765.

105-1.07 COOPERATION BETWEEN CONTRACTORS. Add the following: The following projects may be under construction concurrently with this project:

1.	Eagle River Urban Rehabilitation – STP-0558(4) / 53834

Owner: ADOT&PF

Contractor: Quality Asphalt Paving

Telephone: 522-2211

2.	Fire Eagle Condominiums

Owner: Eklutna Corporation

Contractor: McLin Contractors

Telephone: 562-1294

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above project so as to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contract.

(2/1/00)R175M98

105-1.13 MAINTENANCE DURING CONSTRUCTION. Add the following: Inspect and clean all storm drain sumps and petroleum separator manholes during the construction season and prior to winter shutdowns. This inspection and maintenance of the storm drain system will not be paid for directly but will be subsidiary to work paid for under Sections 603 and 604.

(2/1/00)R4M98

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract.

(02/06/02)R237M98

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Add the following: Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district.

(3/21/01)R93

Section 106
Control of Material

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials which remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

(08/31/99)S 13

106-1.02 LOCAL MATERIAL SOURCES. Add the following under Item 2. Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of the sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) before beginning any operations in your surface mine.  Offer the training at each surface mine that will be used to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

a.	Site specific health and safety risks.

b.	Recognition and avoidance of hazards.

c.	Restricted areas.

d.	Warning and evacuation signals.

e.	Other special safety procedures.

f.	Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.

(05/01/02)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following:

When the specifications refer to the following test methods, use the corresponding test method shown.

| REPLACE TEST METHOD: | WITH TEST METHOD: |
| --- | --- |
| ATM 203 | Alaska FOP for AASHTO T 267 |
| WAQTC FOP for AASHTO T 89/T 90 | WAQTC FOP for AASHTO T 89 WAQTC FOP for AASHTO T 90 |
| WAQTC FOP for AASHTO T 180 | WAQTC FOP for AASHTO T 99/T 180 and WAQTC TM 9 |
| WAQTC FOP for AASHTO T 224 | Same |
| ATM 212 | ATM T-12 |
| WAQTC FOP for AASHTO T 310 | WAQTC TM 7 |
| WAQTC FOP for AASHTO T 27/T 11 | Same |
| WAQTC TM 1 | Same |
| ATM 306 | ATM T-9 |
| ATM 313 | ATM T-13 |
| WAQTC TM 4 | Same |
| WAQTC FOP for AASHTO T 308 | WAQTC FOP for AASHTO TP 53 |
| WAQTC TM 6 | Same |
| WAQTC FOP for AASHTO T 30 | Same |
| WAQTC FOP for AASHTO T 209 | Same |
| WAQTC FOP for AASHTO T 166/T 275 | Same |
| WAQTC TM 8 | Same |
| ATM 412 | None |
| ATM 414 | ATM T-14 |
| ATM 417 | ATM T-17 |
| WAQTC TM 2 | Same |
| WAQTC FOP for AASHTO T 309 | WAQTC TM 10 |
| WAQTC FOP for AASHTO T 119 | Same |
| WAQTC FOP for AASHTO T 121 | Same |
| WAQTC FOP for AASHTO T 152 | Same |
| WAQTC FOP for AASHTO T 23 | Same |
| ATM 520 | ATM T-30 |

(09/04/02)B01

Section 107
Legal Relations and Responsibility to Public

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If you discover cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by your operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from you.

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES. Change the first sentence to the following: When your operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, such as shell heaps, land or sea mammal bones or tusks, or other items of historical significance, cease operations immediately and notify the Engineer.  Nighttime construction activities will require a Municipality of Anchorage noise permit which you must obtain.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If you require water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

(05/29/02)R7M98

107-1.13 RESPONSIBILITY FOR DAMAGE CLAIMS. Delete this Subsection in its entirety and substitute the following: The Contractor shall indemnify, hold harmless and defend the State of Alaska and its agents and employees from any and all claims or actions for injuries or damages whatsoever sustained by any person or property that arise from or relate to, directly or indirectly, the Contractor's performance of the Contract, however, this provision has no effect if, but only if, the sole proximate cause of the injury or damage is the Department’s negligence. This Contract does not create a third party benefit in the public or any member of the public, nor does it authorize any person or entity not a party to this Contract to maintain a suit based on this Contract or any term or provision of the Contract, whether for personal injuries, property damage or any other claim or cause of action.

(05/06/03)R271USC02

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following after the last paragraph: When construction activities meet any of the following conditions, advise the appropriate owning Utility(s) in writing at least 24 hours in advance of work.

1.	Operations anticipated being within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(10/23/02)R170USC02

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120
Training Program	Section 645
Federal EEO Bid Conditions	Form 25A-301
EEO-1 Certification	Form 25A-304
DBE Subcontractable Items	Form 25A-324
ADOT&PF Training Program Request	Form 25A-310
Training Utilization Report	Form 25A-311
Contact Report	Form 25A-321A
DBE Utilization Report	Form 25A-325C
Summary of Good Faith Effort Documentation	Form 25A-332A
Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(08/13/98)S 80

Section 108
Prosecution and Progress

Special Provisions

108-1.03 PROSECUTION AND PROGRESS. Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1. A progress schedule.  and substitute the following:

1. A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order in which the work will be carried out and the contemplated dates on which the Contractor and subcontractors will start and finish each of the salient features of the work, including any scheduled periods of shutdown.  Indicate any anticipated periods of multiple-shift work in the CPM Schedule.  If revisions to the proposed CPM Schedule are required, make them promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to your schedule, or upon request of the Engineer.

(12/13/02)R261M98

Add the following under item no. 1: Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

(4/22/99)R250M98

Delete Item 5 of the first paragraph and substitute the following:

5.	The submittals identified under subsection 641-1.03, Submittals.

(01/31/02)R160M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 3rd paragraph under item 2 “Suspension and Extension of Contract Time,” and substitute the following:

Contract time shall continue through the suspension of work in the following conditions:

●	those instances where the Engineer orders suspension of the work for unsafe conditions,

●	for failure by the Contractor to carry out contractual provisions, or

●	for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.

(10/23/02)R242USC02

Section 109
Measurement and Payment

Special Provision

109-1.05 COMPENSATION FOR EXTRA WORK.

Delete the first sentence of the second paragraph of sub-item a. of item 3 and substitute the following: The regular hourly rental rate is the adjusted monthly rate for the basic equipment plus the adjusted monthly rate for applicable attachments, both divided by 176, and multiplied by the area adjustment factor specified on the adjustment maps for the Alaska - South Region.

(10/23/02)R14USC02

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

Add the following Section:

Section 120
Disadvantaged Business Enterprise (DBE) Program

Standard Modification

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

1.	Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

a.	that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

b.	whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

c.	has been certified by the Department in accordance with 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer. A DBE certified by the Department in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

d.	fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

2.	Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

a.	Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

1)	A description of the work that each DBE will perform;

2)	The dollar amount of participation by the DBE firm;

3)	Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

4)	Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

b.	DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

3.	Phase III - Construction.

a.	Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

b.	DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

c.	DBE Replacement. If a DBE replacement is approved by the Engineer, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

1)	The Contractor has not committed any discriminatory practice in its exercise of good business judgment to replace a DBE.

2)	If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

d.	DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

1.	Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

a.	Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

b.	If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

c.	Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

d.	Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

e.	Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

f.	Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

g.	Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

h.	Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

i.	Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

a.	The decision on reconsideration will be made by the DBE Liaison Officer.

b.	The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

c.	The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

d.	The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

1.	Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

a.	regular dealer;
b.	manufacturer;
c.	broker; 
d.	subcontractor; 
e.	joint-venture; or
f.	prime contractor.

2.	Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

a.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

b.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

c.	The DBE is certified in the appropriate category at the time of

1)	the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

2)	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

d.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

e.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

f.	The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

1)	The work performed will be necessary and useful work required for the execution of the Contract.

2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

3)	The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

4)	The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

5)	The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

6)	All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

7)	The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

g.	On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

a.	withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

b.	continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

1)	increasing the participation of other DBEs on the project;

2)	documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

3)	by a combination of the above.

4.	DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06.

(11/17/00)S33

Section 201
Clearing and Grubing

Special Provisions

201-3.04 HAND CLEARING. Delete this Subsection in its entirety and substitute the following:

Cut and dispose of all trees less than 4” in diameter, down timber, stubs, brush, bushes and debris from all areas designated, with minimal disturbance to grass and/or moss cover.  Do not use equipment on wheels or tracks in areas designated as had clearing except as stated below.

Where approved by the Engineer, you may use a mechanical brush cutter.

Cut stumps flush with the ground.

201-4.01 METHOD OF MEASUREMENT.  Replace Item 1 with the following:

1.	Acre.  The area acceptably cleared and/or grubbed, measured horizontally.  Only areas shown on the Plans or staked for clearing and/or grubbing will be measured.

Existing roadways, lakes, ponds, stream beds or other areas not covered by trees or brush will not be included for measurement.  Other areas that do not require clearing and/or grubbing will be so staked.

(01/27/03)R270USC02

Section 202
Removal of Structures and Obstructions

Special Provisions

202-1.01 DESCRIPTION. Add the following: This work also consists of cutting and abandoning segments of existing culvert pipe as detailed in the Plans.

This work also includes removal of gas pipe.

202-3.04 REMOVAL OF PIPE. Add the following: Where indicated on the Plans, existing culvert pipe shall be shortened by cutting and removing specified length(s).  The remaining culvert pipe shall be abandoned in place.  No portion of abandoned culvert pipe shall protrude into new sidewalk, pathway or roadway embankment.

During project construction, Enstar Natural Gas Company will abandon existing gas pipelines.  Follow the procedures given in Subsection 105-1.06 Cooperation with Utilities, when working around gas pipelines until they have been abandoned.  Once the pipelines are abandoned, remove all those abandoned within the right-of-way that are in conflict with the work and dispose of all pipes outside of the project limits.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Remove and stockpile all existing and temporary asphalt pavement for reuse as Item 301(1) Aggregate Base Course, Item 306(1) ATB or Recycled asphalt pavement base course as specified in Section 310.

Asphalt material not used as specified above shall be removed from the project and stockpiled at the Municipality of Anchorage gravel pit located along the Eagle River Correctional Frontage Road near the Hiland Overpass.  Contact Scott Schnell, MOA Supervisor for Eagle River/Chugiak area @ 694-3487 to coordinate acceptance of material and desired location of stockpile.  Material not acceptable to the maintenance chief will be disposed of in an acceptable manner.

Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 6 inches.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84USC

202-3.07 SALVAGING. Notify the Engineer, five (5) days prior to removing manholes and inlets. Upon excavation, the Engineer will physically identify those manholes, inlets or portions thereof to be salvaged.  All manholes, inlets or portions thereof so designated will be delivered to the Department of Transportation Maintenance Yard located in Anchorage.  All remaining items removed become your property.

(8/30/00)R258M98

202-4.01 METHOD OF MEASUREMENT. Add the following: Existing culverts to be abandoned shall be measured by the linear foot under Item 202(4) Removal of Culvert Pipe.

Add the following: Existing culverts to be abandoned shall be paid under Item 202(4) Removal of Culvert Pipe.

Removal of gas pipe will be measured by the linear foot under Item 202(16) Removal of Gas Pipe.

202-5.01 BASIS OF PAYMENT. Add the following: Removal of gas pipe will be paid on a linear foot basis for all gas pipe that is removed and disposed of, regardless of size or material.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 202(16) Removal of Gas Pipe | Linear Foot |

Section 203
Excavation and Embankment

Special Provisions

203-3.01 GENERAL. Add the following: Obliteration of Pathway includes all grading operations necessary to incorporate the existing pathway into the new sidewalk and surroundings in order to provide a pleasing appearance from the new trail and adjacent highway.  Prior to obliterating the existing pathway, remove the existing pavement and dispose in accordance with Subsection 202-3.05, Removal of Pavement, Sidewalks and Curbs.  Fill ditches not required for drainage and grade to the approximate original contour of the ground.  Obliterated pathway areas may be used to waste excess roadway excavation as approved by the Engineer.  Where obliteration operations enter decorative landscaping areas the restoration efforts shall include matching the topsoil, seeding, mulch, etc. as approved by the Engineer.

203-3.02 EMBANKMENT CONSTRUCTION. On page 63, delete the first sentence of the  tenth paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding  8 inches in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by  1 foot and transversely by 10 feet.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.

The surface of Selected Material, Type D, shall be compacted by coverage of the Contractor's placement equipment to provide a smooth and firm slope. The surface of Selected Material, Type D shall be free of surface irregularities, rutting, slope breaks or unconsolidated material.

(11/05/02)R23USC02

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL. Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP FOR AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the No. 200 sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the No. 4 sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus No. 4 material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the ¾ inch sieve with the plus ¾ inch material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5.

(11/05/02)R193USC02

203-4.01 METHOD OF MEASUREMENT. Add the following after Item 5:

6.	Item 203(9D) Obliteration of Pathway.  Will be measured by the square yard of existing paved pathway removed outside of cut/fill staking limits.

203-5.01 BASIS OF PAYMENT. Add the following: If deep peat excavation in the vicinity of Sta. 200+00 to 202+00 requires mechanical stabilization or shoring of the sanitary sewer and/or excavation slopes this will be paid as extra work under Subsection 109-1.05.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 203(9D) Obliteration of Pathway | Square Yard |

Section 301
Aggregate Base Course

Special Provisions

301-2.01 MATERIALS. Add the following after the first sentence: If no gradation type is specified in the bid schedule the base course material gradation shall conform to the requirements for Grading D-1.

(11/05/02)R116USC02

Add the following after the first sentence: At your option, recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| No. 4 | 28-78 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

(11/05/02)R176USC02

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.

(9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 40,000 pounds. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to  80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(11/05/02)R176USC02

Section 306
Asphalt Treated Base Course

Special Provisions

306-2.01 MATERIALS. Replace this Subsection and with the following:

1.	Aggregate. Conform to Subsection 703-2.04. Combine aggregates from processed existing pavement and crushed for asphalt concrete mix before testing.

2.	Asphalt. The total residual asphalt cement may be a combination of PG 52-28 and the asphalt binder in the existing asphalt or only PG 52-28.  Documentation and conformance is only required for PG 52-28.  Provide a manufacture’s certificate of compliance, in accordance with Subsection 106-1.05, test results of applicable quality requirements of Section 702 before you ship the material.

3.	Anti-Strip. As required by the approved Job Mix Design.

4.	Processed Asphalt Pavement (PAP). Process existing pavement removed under Subsection 202-3.05 so all the material passes the 1.5 inch sieve.  Stockpile the material separately from the Asphalt Concrete Aggregates.  Perform one gradation and one asphalt content test for every 1000 tons of PAP or a minimum of ten sets of tests which ever is greater.  From these samples, ten samples shall be split and submitted to the State Materials lab.

306-3.01 COMPOSITION OF MIXES. Replace this Subsection with the following:  If you choose to use recycled materials, submit process control data of the PAP and of the asphalt concrete aggregates supporting your proposed job mix design gradations.  The residual asphalt cement of the mix shall target 5.0 percent of total mix weight.

At least 15 calendar days prior to the production, submit the following to the Engineer:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile and PAP. The proposed mix gradation must meet the requirements of Table 703-3, Type II Submit gradation and asphalt content process control data of PAP for the Job Mix Design.

2.	Provide representative samples of each of the aggregates in the blend.  Sample sizes: 45 kilograms of each intermediate and/or coarse aggregate, 90 kilograms of fine aggregate, 10 kilograms of blend sand, and 90 kilograms of PAP.

3.	A minimum of three 4-liter samples of asphalt cement proposed for use in the mixture, including the name of the product, the manufacturer, test results as required in Section 702, manufacturer’s certificate of compliance in accordance with Section 106, and a temperature viscosity curve for the asphalt cement.

4.	A 0.25-liter sample of the anti-strip additive proposed, including the name of product, manufacturer, and manufacturer’s data sheet, and current Materials safety Data Sheet (MSDS).

The Job Mix Design will be performed using ATM T-17 and shall meet the requirements of Type II, Class B in Table 401-1, Asphalt Concrete Mix Design Requirements. PAP may be used in the mixture. The design minimum residual asphalt content (PAP residual plus PG 52-28) is 5.0 percent by weight of total mix and with  ¼ percent anti-strip by weight of PG 52-28. The Job Mix Design will specify the design aggregate gradation, gradation of virgin aggregate blend, percent of residual asphalt cement, percentage of PAP, and mixing and compaction temperatures ranges.

Submit changes in the Job Mix design warranted by changes in the source of asphalt cement, the source of aggregates, aggregate quality, aggregate gradations, or blend ratios, in the same manner as the original submittal.  A new Job Mix Design will only apply to asphalt concrete mixture produced after your submittal of the new aggregate gradation.

Approved Job Mix Designs will have the full tolerances shown in Table 401-2 applied and will not be limited to the broad band listed in table 703-3.  Tolerances for the largest sieve specified will be plus 0% and minus 1%.

306-3.02 WEATHER LIMITATIONS. Delete this Subsection and substitute the requirements of Subsection 401-3.01.

306-3.03 STOCKPILING. Delete this Subsection in its entirety.

306-3.04 EQUIPMENT. Add the following: Apply the requirements of Subsection 401-3.02 to all equipment.

306-3.06 PREPARATION OF AGGREGATE. Substitute the requirements of Subsection 401-3.09.

306-3.08 SPREADING AND FINISHING. Substitute the requirements of Subsection 401-3.12.

306-3.09 COMPACTION. Substitute the requirements of Subsection 401-3.13.

Add the following:

306-3.12 PATCHING DEFECTIVE AREAS. Remove any ATB that becomes contaminated with foreign material, is segregated, or is in any way determined to be defective.  Do not skin patch. Remove defective materials for the full thickness of the course.  Cut the pavement so that all edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees. Coat edges with a tack coat conforming to Section 402 and allow to cure.  Place and compact fresh ATB to grade and smoothness requirements.

306-3.13 PREPARATION OF EXISTING SURFACE. Prepare existing surfaces in conformance with the Plans and Specifications. Clean existing paved surfaces of loose material.

Prior to placing the asphalt concrete mixture, uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material meeting Section 402.

Allow prime coat to cure and emulsion tack coat to break before placement of asphalt concrete mixture on these surfaces.

306-3.14 TEMPORARY STORAGE. Silo type storage bins may be used, provided that the characteristics of the mixture are not altered. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness, or stiffness of the mixture are causes for rejection.

306-4.01 METHOD OF MEASUREMENT.  Change the second paragraph to read:

Asphalt Cement. Will not be measured for payment, the cost of the asphalt cement will be subsidiary to Item 306(1).

Change the third paragarph to read:

Antistrip Additive. Will not be measured for payment, the cost of the antistrip additive will be subsidiary to Item 306(1).

Add the following:

306-4.02 ACCEPTANCE SAMPLING AND TESTING. Sample and test Asphalt Treated Base at 1000 ton intervals for acceptance.  The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project.  The Engineer shall perform acceptance sampling and testing.  The Engineer will make the results of the acceptance testing available to you within seven working days from the date of sampling.  Sample the blended virgin aggregate at the cold feed.  You may select the sample location of mix to determine the asphalt content.  Sample the blended virgin aggregate at the cold feed. The Contractor may select the mix sample location to determine the asphalt content.

Within 24 hours of final rolling, cut one 6 inch diameter core, full depth, from the finished mat to determine density.  Neatly cut the sample using a core drill at the randomly selected location marked by the Engineer.  Use a core extractor to prevent damage to the core.  Do not cut a sample over a bridge deck.

Apply Tolerances shown in Table 401-2 to all test results to determine compliance with mix design.

The Engineer shall test for density, gradation, and asphalt content as specified in Subsection 401-4.02.

306-5.01 BASIS OF PAYMENT. Add the following: Asphalt cement and anti-strip shall not be paid separately but shall be subsidiary to and included in the Asphalt Treated Base contract price.

Patching defective areas shall be subsidiary to Item 306(1).

Add the following Section:

Section 310
Recycled Asphalt Pavement Base Course

Special Provisions

310-1.01 DESCRIPTION. At the Contractor’s option, a layer of up to 1.5” of recycled asphalt pavement base course may be used to level the surface of Select Material, Type A within the roadway limits before placement of Item 306(1) ATB.  The use of recycled asphalt pavement base course shall not reduce the thickness requirements of the Select Material, Type A layer as specified in the Plans.

310-2.01 MATERIALS. Recycled asphalt pavement base course shall be produced from asphalt pavement that has been crushed and processed and shall meet the following requirements:

1.	Recycled asphalt pavement base course shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall be determined in accordance with WAQTC FOP for AASHTO T 30 and shall meet the following grading specifications:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| No. 4 | 28-78 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the recycled asphalt pavement base course as determined by ATM T-16, WAQTC FOP for AASHTO T 164, or WAQTC FOP for AASHTO TP 53.

CONSTRUCTION REQUIREMENTS

310-3.01 PLACING. The recycled asphalt pavement base course shall be placed and uniformly spread on the approved grade in one layer. Any material that becomes segregated shall be remixed before compaction occurs. Maintain the roadway surface to drain freely at all times.

310-3.02 SHAPING & COMPACTION. The amount of compactive effort required shall be determined by the control strip method using a vibratory compactor with a minimum dynamic force of 40,000 pounds. The control strip shall be evaluated with the use of a nuclear density gauge to establish a roller pattern. The location of the control strip will be designated by the Engineer.

You are responsible for the development of the control strip. Adequate water shall be added to facilitate compaction of the recycled asphalt pavement base course. Select a minimum of two test sites on the control strip and take 15 second (minimum) readings with the nuclear densometer at each test site for every roller pass over the test site. Rolling shall continue until there is less than a 1 lb/ft3 increase in unit weight in the averaged density readings per roller pass. A copy of the density readings developing the control strip will be supplied to the Engineer. The Engineer will obtain ten random nuclear density readings on the completed control strip. A density standard for the project will be determined by averaging the ten readings. Compaction requirements will be 98% of the density standard.

After the recycled asphalt pavement base course layer has received the appropriate compaction with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Pneumatic roller tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

310-3.03 SURFACE TOLERANCE. The finished surface shall not show any variances in excess of ½ inch when tested with a 10 foot straight edge. Areas which are out of tolerance must be corrected by methods approved by the Engineer.

310-4.01 METHOD OF MEASUREMENT. Recycled asphalt pavement base course shall not be measured.

310-5.01 BASIS OF PAYMENT. Recycled asphalt pavement base course shall be subsidiary to Item 306(1) ATB.

Add the following Section:

Section 407
Stone Mastic Asphalt Concrete Pavement

Special Provisions

407-1.01 DESCRIPTION. This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the Stone Mastic Asphalt (SMA) Concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thicknesses shown on the Plans.

407-2.01 COMPOSITION OF STONE MASTIC ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN. Stone Mastic Asphalt Concrete mixture shall be composed of aggregate, asphalt cement, and required additives combined within the limits specified in the contract.

Provide a Stone Mastic Asphalt Concrete mixture that meets the Stone Mastic Asphalt Concrete mix design requirements of Table 407-1.

Submit the following to the Engineer at least 15 calendar days prior to the production of Stone Mastic Asphalt Concrete mixture:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-9, Stone Mastic Asphalt Concrete Aggregate.  Stone Mastic Asphalt Concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended.  Sample sizes: 100 pounds of each intermediate and/or coarse aggregate, 200 pounds of fine aggregate, 22 pounds of blend sand and/or mineral filler.

3.	A minimum of three 1 gallon samples of the asphalt cement proposed for use in the mixture.  Include name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a temperature/viscosity curve for the asphalt cement.

4.	A minimum ½ pint sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

5.	A minimum 5.5 pound sample of the stabilizing additive (cellulose or polyolefin) proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 407-2.05 and manufacturer’s certificate of compliance with Section 407-2.05.

The Engineer will then evaluate the material and the proposed gradation using ATM T-17 (version 01/93) and the mix design requirements of Table 407-1 to establish the Job Mix Design.  Approved Job Mix Designs will become a part of the contract and will specify the target value for asphalt cement content, additives, and the allowable mixing temperature range.  Up to10 working days will be required to determine the Job Mix Design after receipt of all items specified above.

TABLE 407-1
STONE MASTIC ASPHALT CONCRETE
MIX DESIGN REQUIREMENTS

| Design Parameters | Requirement |
| --- | --- |
| Stability, pounds, min. | 1000 |
| Flow, 0.25 inch | 0.3- 0.6 |
| Voids in total mix, percent | 3-5 |
| Compaction, number of blows each side of test specimen | 50 |
| Dust-asphalt ratio (the percent of material passing the No. 200 sieve divided by the percent of asphalt, by weight of mix) | 0.6-1.4 |
| Voids in the mineral aggregate (VMA), min. Voids In Coarse Aggregate (VCA) Of The Mix, % | 17.0 Less Than VCA Of The Coarse Aggregate As Determined By AASHTO T 19 |
| Minimum Asphalt Cement Content % | 6.2 |

Approved Job Mix Designs will have the full tolerances shown in Table 407-4 applied and will not be limited to the broad band listed in Table 703-9.  Tolerances will not be applied to the largest sieve specified.

Submit changes in the Job Mix Design warranted by failure to meet the requirements of Table 407-1, changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio in the same manner as the original submittal.  A new Job Mix Design will only apply to Stone Mastic Asphalt Concrete mixture produced after submittal of the changes.

All mix designs after a Job Mix Design has been approved will be assessed a fixed fee of $1,500.00 each.

407-2.02 AGGREGATES. Aggregates shall be of the type specified in the contract and shall conform to the requirements of Subsection 703-2.13.

407-2.03 ASPHALT MATERIALS. Provide the grade of asphalt cement specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702.  When not specified, the grade of asphalt cement shall be PG 58-28.

Asphalt cement may be conditionally accepted at the source. Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

1.	Manufacturers certificate of compliance, Subsection 106-1.05.

2.	Conformance test results of the batch, Section 702.

3.	Manufacturer shall also certify:

a.	Date and Time of loading

b.	Batch number and storage tank

c.	Type, grade, temperature, and quantity of materials loaded

d.	Type and percent of anti-strip added

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at  275 degrees Fahrenheit) of the asphalt cement used on the project changes from the viscosity of the asphalt supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended until a new Job Mix Design is submitted and approved.

407-2.04 ANTI-STRIP ADDITIVES. Use anti-strip agents in the proportions determined by ATM T-14 and included in the approved Job Mix Design.  At least 70 percent of the aggregate shall remain coated when tested in accordance with ATM T-14.

407-2.05 STABILIZING ADDITIVES. Use cellulose or polyolefin stabilizing additives.  The dosage rate for cellulose is 0.3 percent by weight of the total mix.  The dosage rate for polyolefin is 0.4 percent by weight of the total mix.  The allowable tolerance per ton shall not exceed 10 percent of the required weight of the stabilizing additive.

The cellulose stabilizing additive shall conform to the properties shown in Table 407-2. The polyolefin stabilizing additive shall conform to the properties shown in Table 407-3.

TABLE 407-2
CELLULOSE STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Sieve Analysis: Method A - Alpine Sieve Analysis(1): Fiber Length Percent passing No. 100 sieve Method B - Mesh Screen Analysis(2): Fiber Length Percent passing No. 20 sieve Percent passing No. 40sieve Percent passing No. 140sieve | ¼ inch(max) 60-80 0.035-0.06 inch(avg) 75-95 55-75 10-30 |
| Ash Content(3) | 20% non-volatiles (max) |
| pH(4) | 7.5 +/-1.0 |
| Oil Absorption(5) | 5.0 +/-1.0 times fiber weight |
| Moisture Content(6) | < 5% |
| Bulk Density(7) | 1.25- 2.50 lb/ft3 |

Notes:

(1)	Method A - Alpine Sieve Analysis. This test is performed using an Alpine Air Jet Sieve (Type 200 LS).  A representative 75 grain sample of fiber is sieved for 14 minutes at a controlled vacuum of 1.8 feet (+/-3 inches) of water.  The portion remaining on the screen is weighed.

(2)	Method B - Mesh Screen Analysis. This test is performed using No. 20, No. 40, No. 60, No. 100, and No. 140 sieves, nylon brushes and a shaker.  A representative 150 grain sample of fiber is sieved, using a shaker and two nylon brushes on each screen.  The amount retained on each sieve is weighed and the percentage passing calculated.

(3)	Ash Content. A representative 30-50 grain sample of fiber is placed in a tared crucible and heated between  1000 and  1200 F for not less than two hours.  The crucible and ash are cooled in a desiccator and reweighed.

(4)	pH Test. Seventy-five grains of fiber is added to ¼ pint of distilled water, stirred and let sit for 30 minutes.  The pH is determined with a probe calibrated with pH 7.0 buffer.

(5)	Oil Absorption Test. Seventy-five grains of fiber is accurately weighed and suspended in an excess of mineral spirits for not less than five minutes to ensure total saturation.  It is then placed in a screen mesh strainer (approximately  0.0008 square inch hole size) and shaken on a wrist action shaker for ten minutes (approximately 1 ¼ inch motion at 240 shakes/minute).  The shaken mass is then transferred without touching, to a tared container and weighed.  Results are reported as the amount (number of times its own weight) the fibers are able to absorb.

(6)	Moisture Content. One-hundred-fifty grains of fiber is weighed and placed in a 250 F forced air oven for two hours.  The sample is then reweighed immediately upon removal from the oven.

(7)	Bulk Density. Fluff fiber with air or Hobart Mixer, weigh out 385 grains of fiber, place in 0.2 pint cylinder, tap cylinder and measure volume.

TABLE 407-3
POLYOLEFIN STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Chemical Property | Ethylene, Propylene, Butane 1, Terpolymer, double bond free with no other functional group. |
| Specific Gravity | 0.86 |
| Size | Approx. 0.1 inch dia. by 0.1 inch length |
| Softening Point | 200 F |

407-2.06 PROCESS QUALITY CONTROL. Sample and test materials for process QC of the Stone Mastic Asphalt Concrete mixture in accordance with Subsection 106-1.03.

Failure to perform process QC forfeits the Contractor's right to retests as provided for in Subsection 407-4.02.

CONSTRUCTION REQUIREMENTS

407-3.01 WEATHER LIMITATIONS. Do not place Stone Mastic Asphalt Concrete mixture when it is raining or when rain is imminent, on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture.  Do not place Stone Mastic Asphalt Concrete mixture unless the surface temperature is 50 degrees F or warmer, or after August 15 of any year.

407-3.02 EQUIPMENT. Use equipment in good working order and free of asphalt concrete mix buildup.  Make all equipment available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

407-3.03 BITUMINOUS MIXING PLANTS. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the data to the Engineer at least one day prior to Stone Mastic Asphalt Concrete production.  Maintain a current Air Quality Permit issued by the State Of Alaska.

Provide a scalping screen on the asphalt plant to prevent oversize material or debris from being incorporated into the Stone Mastic Asphalt Concrete mixture.  Provide aggregate and asphalt cement sampling locations meeting OSHA safety requirements.

Do not use proportioning (batch) scales for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

407-3.04 HAULING EQUIPMENT. Haul Stone Mastic Asphalt Concrete mixture in trucks with tight, clean, smooth metal beds thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department's Approved Products List.  Do not use any petroleum product (e.g. diesel or fuel oil) as an asphalt release agent.  If truck beds are not satisfactorily cleaned, the Engineer may direct operations to cease.  The Engineer will not allow the operations to resume until measures are in place to insure proper cleaning of hauling units.  Hauling units will be restricted to end dumps only.

Belly dumps will not be allowed as hauling units unless a plan is developed and approved by the Engineer that ensures the following items are satisfactorily adhered to:

1.	Tracking of asphalt material on the haul route, both on and off the project, shall be eliminated or cleaned.

2.	Truck beds shall be cleaned and build up of material not allowed.

3.	Pavement mat temperature behind the screed shall be optimum for compaction.

If the above items are not performed to the Engineer’s satisfaction, the use of belly dumps will be terminated.

Cover the Stone Mastic Asphalt Concrete mixture with a secured watertight canvas cover extending at least 1 foot over the sides and end of the truck bed when required by the Engineer.

407-3.05 ASPHALT PAVERS. Use self-propelled asphalt pavers equipped with a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a mobile string-line (ski) at least 30 feet in length, or other approved grade follower to automatically actuate the paver screed control system. Use grade control on either  a) both the high and low sides or b) grade control on the high side and slope control on the low side.

Equip asphalt pavers with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip receiving hoppers with a distribution system to place the Stone Mastic Asphalt Concrete mixture uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the Stone Mastic Asphalt Concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Place auger extensions within 1.5 feet of the screed extension on both sides, or per written manufacturer’s recommendations.

The use of a pickup machine to transfer Stone Mastic Asphalt Concrete mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collecting the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any detrimental effects are observed.

407-3.06 ROLLERS. Supply a minimum of three rollers weighing a minimum of 12 tons each to compact the Stone Mastic Asphalt Concrete mixture to the required density while maintaining the pace of the paving operations.  Rollers shall be of the static steel wheel or vibratory steel wheel type.  The roller drums shall be a minimum of 7 feet wide.  Use self-propelled rollers specifically designed to compact hot asphalt concrete mixtures and capable of reversing without backlash.  The use of equipment that results in crushing of the aggregate, or pick-up of the Stone Mastic Asphalt Concrete mixture will not be permitted.

407-3.07 PREPARATION OF EXISTING SURFACE. Prepare existing surfaces in conformance with the Plans and specifications.  Clean existing paved surfaces of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

After completion of planing of a section of the roadway, the Engineer shall inspect that section for areas of distress or failure.  Areas requiring repair shall have the remaining pavement removed, and the distressed area shall be excavated to the depth and limits directed by the Engineer.  Backfill the excavated area with aggregate base course material in conformance with the requirements of Section 301, asphalt concrete leveling course, or with Stone Mastic Asphalt Concrete as directed by the Engineer.

Prior to placing Stone Mastic Asphalt Concrete mixture, uniformly coat pavement surfaces and contact surfaces of curbing, gutters, manholes, and other structures with tack coat material conforming to Section 402.

407-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of the asphalt cement to the mixer at a uniform temperature, within the Job Mix Design mixing temperature range.

407-3.09 PREPARATION OF AGGREGATES. Provide adequate dry storage for the mineral filler and stabilizing additive.  Dry the aggregate for Stone Mastic Asphalt Concrete so the moisture content of the Stone Mastic Asphalt Concrete mixture, sampled from the windrow, the end of the auger, or from behind the screed prior to compaction, is less than 0.5% (by total weight of mix) as determined by WAQTC TM 6.

Heat the aggregate for Stone Mastic Asphalt Concrete to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Stone Mastic Asphalt Concrete mixture in which soot or fuel is present is considered unacceptable per Subsection 105-1.11.

407-3.10 MIXING. Uniformly combine the aggregate, asphalt cement, additives, and stabilizing additives in the amounts required by the Job Mix Design.  Mix the materials such that a complete and uniform coating of the aggregate is obtained.

1.	For batch plants.  Add the stabilizing additive through a separate inlet directly into the weigh hopper above the pugmill.  Time the addition of the stabilizing additive to occur during the hot aggregate charging of the hopper.  Provide adequate dry mixing time to ensure proper blending of the aggregate and fiber stabilizer.

2.	For drum mix plants.  Add cellulose stabilizing additive into the drum mixer at the same point the asphalt cement is added.  Add polyolefin-stabilizing additive directly into the drum mixer through the RAP inlet.  Do not use polyolefin stabilizing additive in a drum mix plant without a RAP inlet.  Operate the drum mixer to ensure complete blending of the stabilizing additive into the mix.

Dry mix Stone Mastic Asphalt Concrete with cellulose stabilizing additive a minimum of 15 seconds, and wet mix a minimum of 40 seconds.  Dry mix Stone Mastic Asphalt Concrete with polyolefin a minimum of 4 seconds, and wet mix a minimum of 30 seconds.  In batch plants, place the dry aggregate in motion immediately prior to the addition of asphalt cement.  Use a wet mixing time adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

Mix the Stone Mastic Asphalt Concrete within the temperature range determined by the Job Mix Design.

Proportion the mineral filler into the mixture uniformly and in the desired quantities.  Provide appropriate equipment for accurately proportioning the relatively large amounts of mineral filler required for a Stone Mastic Asphalt Concrete mixture.

407-3.11 TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Temporary storing or holding Stone Mastic Asphalt Concrete mixture in silo type storage bins is permitted provided that the characteristics of the Stone Mastic Asphalt Concrete mixture are not altered.  Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Dispose of rejected Stone Mastic Asphalt Concrete mixture at no cost to the Department.

407-3.12 SPREADING AND PLACING. Submit a Paving Plan for the Engineer's review a minimum of five working days prior to initiating paving operations.  The plan shall consist of, but not be limited to the following:

1.	Paving schedule to include sequence of operations.

2.	Operational details to include:

a.	Plant operating capacity and target production rate.  Process control testing frequency for gradation, moisture, asphalt cement content, and compaction.

b.	Number and capacity of trucks, cycle time, and delivery rate.

c.	The manufacturer and model of the paver and pickup machine, to include information on grade followers, sensors, operating speed and production rate of the pavers.

d.	Number, type, weight, and operating speed of rollers.

e.	Location and method of constructing longitudinal and transverse joints.

f.	Construction plan for paving intersections and driveways.

Place Stone Mastic Asphalt Concrete mixture upon an approved surface, spread and strike off and compact to the required compacted thickness.  Spread and compact in one layer if the total thickness is 3 inches or less.  Use asphalt pavers to distribute the Stone Mastic Asphalt Concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 407-3.14.

Use hand tools to spread, rake, and lute the Stone Mastic Asphalt Concrete mixture in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.  In such areas, compact the Stone Mastic Asphalt Concrete mixture to the required compacted thickness.

Any Stone Mastic Asphalt Concrete mixture that is contaminated or segregated will be rejected.

Pave adjacent traffic lanes to the same elevation within 24 hours when the section of roadway being paved is open to traffic unless prevented by weather or other factors beyond control.  Place approved material against the outside pavement edge when the drop-off exceeds2 inches.

When multiple lifts are specified in the contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted.

Do not pave against new concrete curb until it has cured for at least 72 hours.

407-3.13 COMPACTION. Immediately after spreading, thoroughly and uniformly compact the Stone Mastic Asphalt Concrete mixture by rolling.

Roll with a minimum of three steel wheel rollers of a minimum weight of 12 tons each.  Adjust rolling procedures to provide the specified pavement density.  Operate rollers at a uniform speed not to exceed 3 miles/hour and with the drive roller nearest the paver.  Roll until all roller marks are eliminated and the specified pavement density has been obtained.

Prevent adhesion of mixture to the rollers by moistening the wheels with water mixed with detergent or other approved material.  Replace rollers showing evidence of excessive pick-up.

Stop rolling operations once sufficient in-place density has been achieved.  Where migration of asphalt cement and filler to the compacted pavement surface has occurred, remove and replace with fresh Stone Mastic Asphalt Concrete mixture.

The target value for density will be 94% of the maximum specific gravity (MSG) as determined in accordance with WAQTC FOP FOR AASHTO T 209.  For the first lot of Stone Mastic Asphalt Concrete, the Job Mix Design will determine the MSG.  For additional lots, the MSG will be determined by the sample from the first sublot of the lot.  Acceptance testing for field density will be determined in accordance with WAQTC FOP FOR AASHTO T 166/T 275 except that a 6 inch diameter core is required.  (Acceptance testing for field density of leveling course will not be done.)

Grade with rakes and lutes and compact with mechanical tampers areas not accessible to rollers.  Use a trench roller in depressed areas to achieve the required compaction.

Remove any Stone Mastic Asphalt Concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective and replace with fresh Stone Mastic Asphalt Concrete mixture and compact to conform with surrounding areas.  Remove and replace any area showing an excess or deficiency of asphalt cement.

Do not leave rollers, other equipment, or vehicles standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

407-3.14 JOINTS. Minimize the number of joints and construct to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.

The minimum specification for longitudinal joint density will be 91 percent of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP FOR AASHTO T 166/T 275.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Remove full depth improperly formed joints resulting in surface irregularities, replace with fresh Stone Mastic Asphalt Concrete mixture, and thoroughly compact.  Do not roll joints after the material has cooled below 150 degrees Fahrenheit.  All pavement removal shall be precut to a neat line with a power driven saw.

Apply a tack coat of asphalt cement or asphalt emulsion on all cold joints and allow to break prior to placing any fresh Stone Mastic Asphalt Concrete mixture against the joint.  Apply the tack coat just prior to paving.

Form transverse joints by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints between 15-25 degrees.

Offset longitudinal joints in one layer from those in the layer immediately below by at least6 inches.  Align the joints in the top layer at the centerline or lane lines.  Where pre-formed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

407-3.15 SURFACE TOLERANCE. The surface of the Stone Mastic Asphalt Concrete will be measured after final rolling at selected locations using a 15 foot straightedge.  Correct variations of the surface greater than 0.2 inches from the testing edge of the straightedge between any two contacts.

The smoothness of the Stone Mastic Asphalt Concrete Pavement in all driving lanes will be measured by the Engineer with a California-type profilograph within 15 days after mainline paving is completed and all defects are corrected.  No measurements will be taken in turn lanes, lane transitions, or within 25 feet of bridge abutments or matches with an existing pavement.  The profilograph results (PrI) will be reduced within the 15 day period and a price adjustment will be calculated in accordance with Subsection 407-5.01.  Furnish any required traffic control devices or flagging in accordance with Section 643.

407-3.16 PATCHING DEFECTIVE AREAS. Remove any Stone Mastic Asphalt Concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective.  Skin patching is not permitted.  Remove defective materials for the full thickness of the course.  Cut the pavement so that all edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with tack coat conforming to Section 402 and allow to cure.  Place and compact fresh Stone Mastic Asphalt Concrete mixture in sufficient quantity so that the finished surface conforms to grade and smoothness requirements.  Compact the Stone Mastic Asphalt Concrete mixture to the density specified.  No payment shall be made for material replacing defective material.  All costs associated with patching defective areas shall be borne by the Contractor.

407-3.17 TEST SECTION. Place a minimum of 300 tons of Stone Mastic Asphalt Concrete mixture in a test section at a location approved by the Engineer 5 days prior to proceeding with Stone Mastic Asphalt Concrete paving.  The test section is used to adjust the Job Mix Design asphalt cement content and also to familiarize the Contractor's personnel with the laydown and compaction of Stone Mastic Asphalt Concrete mixture.

Stone Mastic Asphalt Concrete mixture placed in the test strip that meets specifications will be measured and paid for at contract prices.  No payment will be made for mixture that does not meet specifications.  If the test strip is placed within the project limits and does not meet specifications, it shall be removed at the Contractor's expense.

407-4.01 METHOD OF MEASUREMENT. Stone Mastic Asphalt Concrete mixture will be measured by the ton in accordance with Section 109.  The weight used shall be the tons  used in the accepted pavement and no deduction will be made for the weight of asphalt cement material, anti-stripping agent or any other additive used in the mixture.

A price adjustment, when applicable, will be made based on a quality level analysis under Subsection 407-4.03.

Asphalt cement will be measured by the ton based on the weight of asphalt cement calculated using the percent of asphalt cement for each sublot as determined by WAQTC TM 4, or WAQTC FOP FOR AASHTO TP 53.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If the asphalt cement content is determined by WAQTC TM 4, the percent of asphalt cement for each sublot will be reduced by 0.4 percent for Stone Mastic Asphalt Concrete containing polyolefin.  If the asphalt cement content is determined by WAQTC FOP FOR AASHTO TP 53, the percent of asphalt cement for each sublot will be reduced by 0.4 percent for Stone Mastic Asphalt Concrete containing polyolefin, and by 0.3 percent for Stone Mastic Asphalt Concrete containing cellulose.

The Engineer may direct at any time that tankers be weighed before and after unloading in his presence.  If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

No payment will be made for any asphalt cement in excess of 0.4 percent above the optimum asphalt cement content specified in the Job Mix Design.

Any leftover, waste, or diversion will be computed in a manner to be determined by the Engineer.  The weight of asphalt cement in waste Stone Mastic Asphalt Concrete will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Longitudinal joints will be measured by the foot.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

407-4.02 ACCEPTANCE SAMPLING AND TESTING. The quantity of  Stone Mastic Asphalt Concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance.  The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project.  The Engineer shall perform acceptance sampling and testing.  The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection.  If the project has more than one lot and less than eight additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot will include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,000 tons and 5,000 tons, the contract quantity will be considered one lot.  The lot will be divided into 5 equal sublots and randomly sampled for asphalt cement content, density and gradation in accordance with this subsection.  The Engineer shall select one sample for every 1,000 tons of mix, or majority portion thereof, for testing.  If the test result(s) conform to the specification limits, the lot will be accepted and the weight of asphalt cement for the lot will be calculated from the average of the asphalt cement content tests performed.  If only one asphalt cement content test is performed, the weight of asphalt cement for the lot will be calculated from that one test result.  If any of the test results fail to conform to specification limits, the remaining samples will be tested and the lot evaluated for price adjustment in accordance with subsection 407-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 1,000 tons, Stone Mastic Asphalt Concrete pavement shall be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the Stone Mastic Asphalt Concrete mixture to the specified depth and finished surface requirements and tolerances.  Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 150 degrees F prior to completing compaction, or is any other way defective shall be removed and replaced with fresh Stone Mastic Asphalt Concrete mixture.  Removal and replacement of defective pavement shall be at no additional cost to the Department.

Samples taken for the determination of asphalt cement content will be taken from behind the screed prior to initial compaction.  Asphalt cement content will be determined by WAQTC TM 4, or WAQTC FOP FOR AASHTO TP 53 with the exception that the moisture content will be determined by WAQTC TM 6.

Samples taken for the determination of aggregate gradation will be from the same location as samples taken for asphalt cement content.  Aggregate gradation will be determined in accordance with WAQTC FOP FOR AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP FOR AASHTO TP 53) has burned off the asphalt cement.

Cut a full-depth core sample with a diameter of 6 inches from the finished lift from each sublot within 24 hours of final rolling.  The core sample will be used for density acceptance testing in accordance with WAQTC FOP FOR AASHTO T 166/T 275.  Neatly cut the core sample with a core drill at the randomly selected location marked by the Engineer.  Use a core extractor to prevent damage to the cores while removing.  Do not cut core samples from Stone Mastic Asphalt Concrete mats on bridge decks.  Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

Backfill all voids left by sampling with fresh Stone Mastic Asphalt Concrete mixture and compact within 24 hours of sampling.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

Samples will be evaluated for acceptance in accordance with Subsection 407-4.03.

A retest of any sample outside the limits specified in Table 407-4 may be requested.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  Verbal requests with the written request to be delivered after the specified 7 days will not be accepted.  The sample(s) for retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s).  The Engineer will mark the sample location for the retest.  Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s).  The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample will be allowed.

407-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The following method of price adjustment will be applied to Stone Mastic Asphalt Concrete mixture when the contract quantity equals or exceeds 5,000 tons except as defined in Subsection 407-4.02.  The longitudinal joint density price adjustment will apply when Stone Mastic Asphalt Concrete quantities are equal to or greater than 1,000 tons.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis Method as specified in Subsection 106-1.03 to determine the estimated percent of a lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results.  Outlier test results shall not be included in the price adjustment calculations.  If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment.  The density test result for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s).  Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0 percent and a contractor's risk of 5.0 percent unless otherwise specified.  AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100 percent pay.  The Contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained.  The maximum pay factor obtainable is 1.05.  The maximum pay factor for the largest sieve size specification for gradation shall be 1.00.  The price adjustment is based on the lowest of two pay factors.  The first factor is a composite pay factor for Stone Mastic Asphalt Concrete mixture that includes gradation and asphalt cement content.  The second factor is a separate pay factor for density.

A lot containing non-specification material (less than 1.00 pay factor) may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing non-specification material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11.

The Engineer can reject material that appears to be defective based on visual inspection.  Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis.  Procedures for computation of composite pay factors are as follows:

1.	Eliminate test results found to be outliers by SP-7 (Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ  =  summation of

x=Σxn

x  =  individual test value to xn

n  =  total number of test values

x is rounded to the nearest tenth for density and all sieve sizes except the No.200 sieve.  x is rounded to the nearest hundredth for asphalt content and the No. 200 sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)  =  summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2  =  square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest 0.01 for density and all sieve sizes except the No.200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt content and the No. 200 sieve.

If the computed sample standard deviation (s) is less than 0.001, then use s = 0.20 for density and all sieve sizes except the No. 200 sieve.  Use s = 0.020 for the No. 200 sieve and asphalt cement content.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL).  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances  in Table 407-4.  The tolerances for the largest sieve specified will be plus 0% and minus 1%.  The TV is the specification value defined by the Job Mix Design.  The TV for density is 94 percent of the maximum specific gravity (MSG).  The LSL  for density is 92 percent of MSG and the USL is 96%.

4.	Compute the upper quality index (QU):

Where:	USL = Upper Specification Limit

QU=USL-xs

QU is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

Where:	LSL = Lower Specification Limit

QL=x-LSLs

QL is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit that corresponds to a given QU) from Table 106-1.  For negative values of QU, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

7.	Determine PL (percent within the lower specification limit that corresponds to a given QL) from Table 106-1.  For negative values of QL, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

8.	Determine the Quality Level (QL), the total percent within specification limits, for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from step 8, determine the lot Pay Factor for Density (DPF), and gradation and asphalt cement content pay factors (PF) from Table 106-2.

10.	Calculate the lot Stone Mastic Asphalt Concrete mixture Composite Pay Factor (CPF) for asphalt cement content and gradation using the following formula:

Round the Composite Pay Factor (CPF) to the nearest hundredth.

CPF=[f19mm(PF19mm)+f12.5mm(PF12.5mm)+.......fac(PFac)]Σf

Table 407-5 is used to determine the weight factor (f) for each sieve size and asphalt  cement content.

Table 407-4
LOWER SPECIFICATION LIMIT (LSL) and
UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV-5.0 | TV+5.0 |
| 1/2 inch sieve | TV-5.0 | TV+5.0 |
| 3/8 inch sieve | TV-5.0 | TV+5.0 |
| No. 4 sieve | TV-4.0 | TV+4.0 |
| No. 8 sieve | TV-4.0 | TV+4.0 |
| No.16 sieve | TV-4.0 | TV+4.0 |
| No. 30 sieve | TV-4.0 | TV+4.0 |
| No.50 sieve | TV-3.0 | TV+3.0 |
| No.100 sieve | TV-3.0 | TV+3.0 |
| No. 200 sieve | TV-2.0 | TV+2.0 |
| Asphalt % | TV-0.40 | TV+0.40 |
| Density | 92% | 96% |

Table 407-5
WEIGHT FACTORS

| Sieve Designation | Factor (f) |
| --- | --- |
| 3/4 inch sieve | 3 |
| 1/2 inch sieve | 5 |
| 3/8 inch sieve | 6 |
| No. 4 sieve | 10 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No.30 sieve | 4 |
| No. 50 sieve | 6 |
| No.100 sieve | 8 |
| No. 200 sieve | 10 |
| Asphalt % | 40 |

407-5.01 BASIS OF PAYMENT. The accepted quantity will be paid for at the contract unit price for the pay items listed below, complete in place.

Anti-strip additives will be subsidiary to Item 407(1), Stone Mastic Asphalt Concrete.

Stabilizing additives will be subsidiary to Item 407(1), Stone Mastic Asphalt Concrete.

A change order/directive is not required for Anti-Strip Additive or Asphalt Price Adjustment pay items.  The approved Job Mix Design will initiate Item 407(3), Anti-Strip Additive at the prescribed rate and the Notice to Proceed shall constitute the notice required to initiate Item 407(4), Asphalt Price Adjustment.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot, fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 407-2.01, and fees accrued for failure to cut cores and/or backfill voids left by sampling in the allotted time as outlined in Subsection 407-4.02.  The Asphalt Price Adjustment will be algebraically added to the Contractor's payment for Stone Mastic Asphalt Concrete.  Individual lot price adjustments will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (tons  in lot) x (PAB)

PAB = Price Adjustment Base = $60/Ton

* Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest    value.

Longitudinal joint densities less than 91 percent of MSG as defined in Subsection 407-3.14 will be measured in accordance with Subsection 407-4.01 and assessed a price adjustment of $ 0.30 per  foot.  The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with Subsection 407-3.15 will be calculated and applied in accordance with Table 407-6.  The adjustment will be applied under Item 407(4), Asphalt Price Adjustment.

TABLE 407-6

| Average Profile Index (PrI) (Inches per Lane Mile) | Adjustment to payment for Stone Mastic Asphalt Concrete |
| --- | --- |
| 0 to 3.9 | Add $5,000 multiplied by ( 4.0-PrI) |
| 4.0 to 6.0 | No adjustment |
| 6.1 and greater | Deduct $5,000 multiplied by (PrI- 6.0) but not to exceed $10,000. |

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 407(1) Stone Mastic Asphalt Concrete | Ton |
| 407(2) Asphalt Cement, Grade 58-28 | Ton |
| 407(4) Asphalt Price Adjustment | Contingent Sum |

(08/19/02)R163USC

Section 603
Culverts and Storm Drains

Special Provisions

603-1.01 DESCRIPTION. Add the following:

This work also consists of installation of perforated storm drain pipe as detailed on the Plans.

This work shall also consist of installing culvert marker posts.

This work also includes installation of culvert inlet trash grates where indicated on the Plans.

603-2.01 MATERIALS. Add the following:

Perforated Corrugated Polyethylene Pipe	Subsection 7.06-2.07

Corrugated Steel Pipe for Underdrain	Subsection 7.07-2.01

Corrugated Aluminum Pipe for Underdrain	Subsection 7.07-2.03

Culvert marker posts shall meet the requirements of subsection 730-2.05 Flexible Delineator Posts. The color shall be blue with no other markings. The 2.5 inch by 6 foot post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

Culvert inlet trash grates shall be cast material or fabricated from steel and galvanized as approved by the Engineer.

603-3.02 LAYING PIPE. Add the following: Place perforated storm drain pipe with the perforations up.

Add the following Subsection:

603-3.06 CULVERT MARKER POSTS. Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two (42) inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT. Add the following:

Perforated Pipes for Storm Drains.  By the linear foot in place along the invert, from center to center of structures.  No deduction will be made for length through inlets, catch basins, or manholes.

Culvert marker posts will not be measured for payment.

Culvert inlet trash grates shall not be measured.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

(09/10/02)R42 USC

Installation of culvert trash grates will be subsidiary to pipe items.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 603(33-24) 24 Inch Perforated Pipe | Linear Foot |

Section 604
Manholes and Inlets

Special Provisions

604-2.01 MATERIALS. Add the following: Grates for curb inlet catch basins shall have “vaned” slots , be certified as bicycle-safe by the manufacturer, and meet the requirements of the applicable standard drawing.

604-3.01 CONSTRUCTION REQUIREMENTS. Add the following after the third sentence: Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 1 inch of concrete or asphalt, as applicable.

Under the heading “Reconstruct existing manhole by using one or more of the following methods,” add the following:

8.	Salvage existing frame and grate, remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab (reducing slab without an access hole).  Salvaged frame and grate shall be delivered to the local DOT maintenance station.

Add the following: When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the plans and 2 inches larger than the outside diameter of the new pipe. Then, grout joint with non-shrinking cement mortar.

All curb inlet structures shall have a 3 inch formed hole approximately 2 feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation. Keep the openings functional. This may require temporary dikes, RMC extensions, etc., as necessary. Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install them before concrete hardens.

604-4.01 METHOD OF MEASUREMENT. Add the following: Frames, grates and lids will not be measured for payment.

604-5.01 BASIS OF PAYMENT. Add the following: Frames, grates and lids are subsidiary to the drainage structure.

(11/05/02)R43USC02

Delete Item 604(1) Storm Sewer Manhole and add the following new Pay Item:

| Pay Item | Pay Unit |
| --- | --- |
| 604(1A) Storm Drain Manhole, Type I | Each |

Section 608
Sidewalks

Special Provisions

608-1.01 DESCRIPTION. Add the following: This work also consists of constructing asphalt pathway(s) in conformance with the Plans.  Asphalt sidewalk will be used for paving medians, bus pull-outs and approaches.

This work also consists of providing equipment, materials and labor necessary to install cast-in-place Patterned Concrete.  Patterned Concrete shall be imprinted concrete as shown on the Plans.

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

2.  Asphalt Sidewalk and Asphalt Pathway

Asphalt Cement, PG52-28	Subsection 702-2.01
Aggregate, Type III	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, pounds, min.	1000
Percent Voids, Total Mix	2-5
Compaction, Blows/side	50

Add the following:

Patterned Concrete shall conform to Section 501, Structural Concrete, Class A, except that Subsection 501-3.02 Batching is modified as follows:

Under item 3. Aggregates, delete the third paragraph.

Add the following: For Patterned Concrete, concrete shall be Class A with the following modification:

1.	Air Entrainment - 7 percent. Air entraining agents complying with ASTM C 260 may be used.

2.	Imprint the Patterned Concrete using one of the following imprinting systems and patterns:

a.	“Flagstone” pattern, Bomanite, John-Wayne Construction Co., Anchorage, Alaska; (907-344-3511)

b.	“California Fieldstone” pattern, Stampcrete, Stampcrete International, Ltd. 325 commerce Blvd., Liverpool NY 13088, (800-233-3298); web site: stampcrete.com

c.	“Flagstone” pattern, Design-Crete by Symons Corporation, 200 E. Touhy Avenue, Des Plaines, Il, 60018; (847-298-3200)

608-3.01 CONCRETE SIDEWALKS. Delete the fifth paragraph and substitute the following: Expansion joints shall be placed along all structures and about all features that project into, through., or against the concrete.  An expansion joint shall be constructed at the intersection of the sidewalks; between curbs and sidewalks (except parallel curb); and at the beginning and end of curb returns.  Expansion joint material shall conform to the requirements of AASHTO M-33.  This material shall extend the full width of the structure and shall be cut to such dimensions that the base of the expansion joint shall extend to the subgrade and the top shall be depressed not less than ¼ inch nor more than ½ inch below the finished surface of the concrete.  The material shall be of one (1) piece in the vertical dimension and shall be securely  fastened in a vertical position to the existing concrete face against which fresh concrete is to be placed.  After the concrete has set, the expansion joints shall be filled flush to the finish concrete surface with joint sealer.  Before sealing, the joint shall be cleaned of all dirt, gravel, concrete mortar, and other extraneous material.  Sealing shall be done in a neat workmanlike manner.

Contraction joints: Transverse contraction joints, cut to a depth of 1 inch, prior to the final set of the concrete, shall be tooled in the sidewalks at intervals of 5 feet, and at 10 foot intervals in the curb and gutter.  Where the sidewalk adjoins the curb (parallel to it) contraction joints in the sidewalk and curb shall be made to match where practicable.

Add the following: Contractor shall provide a 4 foot by 1.2 foot sample of the proposed finish for approval by the Engineer prior to beginning Patterned Concrete work.  All other Patterned Concrete shall match the approved panel.

Final groove dimensions in the stamped pattern shall be no deeper than ¼ inch and no wider than ½ inch.  Patterned Concrete shall be placed in such a fashion that a uniform appearance and texture will be maintained along the length of the sidewalk.  Any significant difference in texture, pattern or appearance between two adjacent concrete panels, or from the sample panel, will result in the removal and replacement of concrete panels by the Contractor at no additional cost.

608-3.03 CURB RAMPS. Delete the second sentence of this Subsection.

Add the following Subsections:

608-3.04 ASPHALT PATHWAY. Construct asphalt pathway in accordance with Subsection 608-3.02, Asphalt Sidewalks.

608-3.05 PATTERNED CONCRETE. In addition to meeting the requirements of Section 501, the Patterned Concrete shall include all excavation, compaction, steel reinforcement, dowels, construction, and expansion joint materials, patterned concrete and incidental work required to complete work per the plans.  The Patterned Concrete shall be installed prior to asphalt paving.

Protection of Patterned Concrete. When asphalt paving, observe the following requirements:

Do not place the asphalt pavement until the concrete has cured enough to prevent damage from the paving operation.

When crossing over the concrete surface with vibratory rollers, turn the vibrator off.

Place, spread, and roll the asphalt so that the concrete will not be damaged.

Cover the concrete surface with kraft paper or other approved material, suitable to withstand high asphalt temperatures and vehicle traffic to protect the concrete surface from contaminants.

Prior to final acceptance, the Contractor shall repair all damaged concrete and clean all surface contamination at his expense, to the satisfaction and approval by the Engineer.

608-4.01 METHOD OF MEASUREMENT.

Delete the Curb Ramp item and substitute the following:

Curb Ramp. By each installation, complete in place, including construction of the ramp runs, flares, composite detectable warning tiles and landings necessary to provide a single street-level access.

Add the following:

Asphalt Pathway. Will be measured by the ton in accordance with Section 109, Measurement and Payment.  Asphalt cement and anti-stripping additive will not be measured for payment.

Patterned Concrete. Will be measured by the square yards of finished surface.

608-5.01 BASIS OF PAYMENT. Add the following:

The composite detectable warning tiles are subsidiary to item 608(6) Curb Ramp.

(06/11/02)R256USC

Add the following: Asphalt cement for Asphalt Pathway will not be paid for separately, but will be subsidiary to Item 608(7) Asphalt Pathway.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

(2/1/00)R47USC

Payment for Patterned Concrete will be full compensation for all work to complete the item.  No separate payment will be made for surface preparation, or the test panel, these items will be considered subsidiary to Item 608(17B) Patterned Concrete.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 608(7) Asphalt Pathway | Ton |
| 608(17B) Patterned Concrete | Square Yard |

Section 609
Curbing

Special Provisions

609-3.02 CAST-IN-PLACE CONCRETE CURBING. Add the following to the sixth paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than 2 inches.

(11/06/02)R202USC02

Section 615
Standard Signs

Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit shop drawings for all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete the sixth sentence of the first paragraph of item 7 and substitute the following:

Deliver sign panels, posts and hardware to the State Maintenance Yard located in Anchorage.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in Subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(11/16/02)R50USC02

Section 616
Thaw Pipe and Thaw Wires

Special Provisions

616-2.02 THAW WIRE. Under Item 3 “Controls,” add the following:

d.	Use a spring wound mechanical line voltage timer.  Contacts close during timer period.  Contact rating 20 amps inductive at 120 volts.  Time period is 12 hours without hold.  Intermatic PFGH or equivalent.

(08/28/00)R216USC

Section 618
Seeding

Special Provisions

618-1.01 DESCRIPTION. Add the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer.  Track the soil and apply seed, mulch, fertilizer and water.  Provide a living ground cover on all slopes as soon as possible.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION. Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS. Add the following:  All seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION. Add the following: Apply seed, mulch and fertilizer as follows per acre. Apply seed and mulch in one application if using the hydraulic method. Apply all fertilizer with the hydraulic method.

| Seed Mix | Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- | --- |
| Type A | Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
|  | Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, at the same application rate.

618-4.01 METHOD OF MEASUREMENT. Add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT. Add the following: The work described under Subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(11/06/02)R52USC

Section 620
Topsoil

Special Provisions

620-2.01 MATERIALS. Delete paragraph and substitute the following:  Topsoil shall conform to the requirements of Section 726.  Topsoil shall be Class B.

620-3.01 PLACING. Delete paragraph in its entirety and substitute the following:

For all areas shown on the Plans, or as directed by the Engineer that are to be seeded (as described in Section 618), topsoil shall be evenly spread on the designated areas to a minimum depth after settlement of 4 inches.  Settlement shall be achieved by rolling the topsoil with a water-filled drum approved by the Engineer.

Grade topsoil with a scarifying slope board or rake.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete the grading as soon as topsoil is placed.  The resultant indentations shall be perpendicular to the fall of the slope.  The Contractor may round the top and bottom of the slopes to facilitate working the slope and to create a pleasing appearance, but drainage flow lines shall not be disrupted.

Do not place topsoil when the site or the topsoil itself is in a condition detrimental to the work.  Keep all roadway surfaces clean of topsoil during hauling and spreading operations.

620-4.01 METHOD OF MEASUREMENT. Add the following: Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1B) Topsoil, Class B.

(9/11/96)R53

620-5.01 BASIS OF PAYMENT.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 620(1B) Topsoil, Class B | Square Yard |

Section 635
Insulation Board

Special Provision

635-2.01 MATERIALS. Delete this section in its entirety and substitute the following:

Use materials that conform to the following:

Insulation Boards. AASHTO M 230, except that the extrusion is not required.  The insulation board shall be rigid, homogeneous and conform to the following:

Property	Test Method	Value

Compressive Strength,
minimum at yield or 5% strain	ASTM D 1621	60 psi

Density,
minimum	ASTM D 1622	3 lb/ft3

Water Absorption,
maximum percent by volume	ASTM C 272	10%

Thermal Resistance,
Minimum R Value at 75°F,
°F-Ft2-Hr/BTU	ASTM C 177	As specified in Plans

Sand Blanket. Subsection 703-2.12.

635-3.01 CONSTRUCTION REQUIREMENTS. Add the following:

Equipment shall not be allowed on insulation with less than twelve (12) inches of cover (sand bedding and select material, type A).  Use of dump trucks over insulation shall require a minimum of eighteen (18) inches of cover.

Applied loads over insulation from equipment, including compactors, shall be limited to less than the following elastic-limit stresses:

Expanded Polystyrene Insulation Board	4,000 pounds per square foot

Extruded Polystyrene Insulation Board	3,300 pounds per square foot

635-4.01 METHOD OF MEASUREMENT. Delete this Subsection in its entirety and substitute the following: By the cubic foot of insulation board, in place based on the nominal dimensions or the materials, or by the square foot of insulation board with the required “R” value in its final position, including transitions, regardless of thickness, complete and accepted.

Sand blanket material is subsidiary.

635-5.01 BASIS OF PAYMENT.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 635(2) Insulation Board | Square Foot |

(8/23/00)R57USC

Delete this Section in its entirety and substitute the following:

Section 639
Approaches

Special Provisions

639-1.01 DESCRIPTION. Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS. Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION. Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. By the number of driveways and approaches constructed as shown on the Plans or as directed. Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT. At the contract unit price shown in the bid schedule. The contract unit price for driveways and approaches shall be full compensation for furnishing  equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.

(05/09/02)R58M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 639(2) Commercial Driveway | Each |
| 639(3) Public Approach | Each |

Section 642
Construction Surveying and Monuments

Special Provisions

642-3.01 GENERAL. Add the following item after Item 10:

11.	Measure and document the actual intersection sight distance triangles at all public intersections.  List the actual sight distance available up to 600 feet.  Note locations with greater than 600 feet of sight distance as “600+”.  Measure sight distance triangles are shown in Figure 1190-1 of the Highway Preconstruction Manual by setting up an instrument at the driver’s eye location.  Certify and record the results on standard “letter” size paper and provide it to the Engineer at least 2 weeks prior to submitting shop drawings for permanent signing. Provide an additional copy to the Regional Traffic Engineer.

(3/12/03)R269USC

642-3.03 MONUMENTS. Delete the second sentence of the first paragraph and substitute the following:  Reference all property markers/corners, monuments or accessories which may be disturbed or buried during construction.  Prepare and record Monument Record Forms in the appropriate Recorder’s Office prior to disturbing monuments.  Monument Record Forms may be obtained from the Engineer.  Reestablish monuments in their original position prior to the completion of the Project.

(3/12/03)R269USC

642-5.01 BASIS OF PAYMENT. Add the following after the first paragraph: You will not receive any payment for Item 642(9), Reference Existing Monument until the Monument Record Forms are recorded in the local Recorder’s Office. (3/12/03)R269USC

(3/12/03)R269USC

Section 643
Traffic Maintenance

Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: You may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum12 foot lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.

643-2.01 MATERIALS. Add the following:

17.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Add the following: You may maintain traffic on a continuous gravel surface for 1,000 feet.

643-3.03 PUBLIC NOTICE. Add the following: Since this project will impact commuters, all project information (road closures, lane restrictions) shall be submitted for inclusion in the Anchorage Daily News (NAVIGATOR) and Pulse Newspapers.  Notification shall also be sent to the Federation of Community Councils.

643-3.04 TRAFFIC CONTROL DEVICES. Delete the first sentence of the eighth paragraph and substitute the following: All items paid under this Section remain your property unless stated otherwise.

Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: Remove all obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT &PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Monday through Friday from 6:00 am to 8:00 am and 4:00 pm to 6:30 pm.

2.	Bear Paw Festival Parade - 2003 (tentatively scheduled July 12, 2003).  At least one month prior to this date, the Contractor shall contact the Chugiak-Eagle River Chamber of Commerce at 694-4702 to verify the date and time of the parade.

Weekend Road Closures

Weekend is defined as Friday 9:00 pm to Monday 5:00 am.  The road closures shall be scheduled so that the side street entrances along the Old Glenn Highway are maintained to local traffic.

In the event the Contractor has performed substantial completion of the work activities the roadway shall be reopened.  The Project Engineer shall have sole determination of the reopening of the roadway.  The road closures shall be completed by August 1, 2003.

1.	The Contractor will be allowed two (2) road closures for cross pipe installation.

2.	The Contractor will be allowed one road closure for the electrical and paving operations required at the intersection of North Eagle River Access and the Old Glenn Highway.  The Northbound eastside Old Glenn Highway lane shall be maintained for access into Spenard Builders/Fred Meyer.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

643-4.01 METHOD OF MEASUREMENT. Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following:

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $2.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Foot Foot Foot Each | $0.30 $0.65 $0.07 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $36.00/hour. The Engineer does not require a change order/directive for the flagging pay item.

(11/18/02)R222USC02

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15)Flagging | Contingent Sum |

Section 644
Services to be Furnished by the Contractor

Special Provisions

644-2.01 FIELD OFFICE. Delete this Subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15. The following office requirements shall be met:

1.	A minimum of 1,000 square feet of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Four (4) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY. Delete sub-item g of item 2 and substitute the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

7.	Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

8.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

(11/19/02)R63USC

Add the following Section:

Section 645
Training Program

Special Provision

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "green pages" of this document.

645-3.01 General.  The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03 Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

(10/29/91)S 16

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 645(1) Training Program, 1 Trainees/Apprentices | Labor Hour |

Section 646
CPM Scheduling

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this Subsection in its entirety and replace with the following: Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  If revisions are required, make them promptly.  The finalized CPM Schedule must be completed and accepted prior to commencement of any work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.  60-Day Preliminary Schedule.

Delete the first sentence of item 3. Schedule Updates. and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly, or as deemed necessary by the Engineer.

(12/13/02)R261M98

Add the following Section:

Section 647
Equipment Rental

Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1), Wide Pad Dozer, 65 HP Minimum will be paid on a contingent sum basis at the rate of $125/hour on a per hour basis at the rate shown on the bid schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

(11/12/98)R15USC

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 647(1) Wide Pad Dozer, 65 HP Minimum | Contingent Sum |

Section 660
Signals and Lighting

Special Provisions

660-2.01 MATERIALS. 1. Equipment List(s) and Drawings.  Delete item (a) that follows the first paragraph and add the following: The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

2. As-Built Plans.  Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.  You will also submit two additional sets of electrical as-built plans to the Engineer.  The Engineer shall deliver one set of electrical as-built plans to MOA Signal Electronics Shop and the other set to MOA Street Light Maintenance.

660-3.01 GENERAL. 6. Salvaging or Reusing Electrical Equipment. Delete the first paragraph and replace with the following:  Salvage and deliver existing electrical equipment undamaged, including signal equipment, luminaires, lighting standards, signal poles and mast arms, service equipment, and junction box lids to the State Maintenance Yard at 5300 east Tudor Road in Anchorage, Alaska. Notify Mike Knowles, Electrician, or Jerry Reed at 338-1466 one-week before your planned delivery date.  All salvaged LED modules and controller assemblies will be delivered to the MOA Signal Electronics Warehouse at 5923 Rowan Street in Anchorage.  Contact MOA Signal Electronics Foreman at 343-8355 one week before anticipated delivery to schedule delivery.

660-3.02 FOUNDATIONS.  1.  Cast-in-Place Foundations.  In subparagraph f, revise the second sentence to read: Before you place the form or reinforcing steel cage, remove all loose material to ensure the foundation rests on firm, undisturbed ground.

In the second sentence of subparagraph i, delete “prior to grouting” and add, ”before you attach the galvanized skirt.”

In the first sentence of subparagraphs j and k, delete “concrete pile caps” and add, ”foundations.”

Add the following new subparagraph l (lowercase L).  Attach a 4 AWG, bare, solid copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector or cadweld to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled 4 AWG, bare, solid copper wire as the grounding electrode.  Route the conductor to protrude near the top, center of the foundations. Slide a minimum 6-inch long, non-metallic, protective sleeve over the conductor. Allow one inch of the sleeve and 4 feet of conductor to protrude from the foundations.

Add the following new subparagraph m. CIDH foundations installed in the peat excavation segment, between Sta. 199+50 and 203+50 RT, may require extension of the foundation beyond the depth shown on the Plans.  If peat is left in place adjacent to the roadway subgrade, at depths less than 8 feet from the final surface elevation, the CIDH foundation shall be extended to at least 1 foot below the peat excavation limits within the roadway subgrade at this location.

2. Pile Foundations. Delete subparagraphs a. through f. and substitute the following:

Pile foundations will not be used.

660-3.03 CONDUIT. Revise subparagraph 6, to read: Install rigid metal conduit under pavements that will not be overlaid by jacking them under pavements up to 30 feet wide and under pavements greater than 30 feet wide by boring or drilling methods.

In subparagraph 8, delete “non-metallic”

Delete subparagraph 9, and add the following: 9.  Position conduit ends in junction boxes to provide clearances of at least 2-1/2 inches around all 2-inch conduits and at least 2-inches around all three inch conduits.

Add the following to subparagraph 11, Provide enough clearance between conduits, including protective sleeves, to ensure you can install grounding bushings on all conduits.

660-3.05 WIRING. Delete subparagraph 11 and add the following: Encapsulate illumination cable splices in rigid 2-piece plastic molds filled with an insulating and sealing epoxy resin. Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin. Furnish molds rated for 600 volts AC operation and feature fill and vent funnels for epoxy resin. Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and which will not sustain combustion.

Delete subparagraph 12 and renumber the paragraph that follows subparagraph 11 to 12.  Also revise the first sentence of new subparagraph 12 to read: Encapsulate all loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with re-enterable polyurethane electrical insulating and sealing compound.

Add the following new subparagraph: 18.  Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

Add the following new subparagraph: 19.  Whenever you can not terminate the conductors specified in the Plans in circuit breakers due to their size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing. Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductor to 5 feet.

660 3.06 BONDING AND GROUNDING. Delete this subsection and add the following: Bond and ground all branch circuits according to the NEC and the following requirements. Make all non-current carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor. Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install threaded-type grounding bushings made of malleable iron or steel with a zinc or galvanized finish on the ends of all metallic conduits. Use bushings with an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Install a bare stranded copper wire for the equipment grounding conductor in all conduits, except those conduits you install for future use. Install size 8 AWG conductors, except in those conduits that contain circuit conductors larger than 8 AWG. In this case, install a conductor equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit all existing spare conduits that will contain new cables exclusively with new grounding bushings. When the Plans require you to install or remove conductors from existing conduits, retrofit them with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross-sectional area equal to an 8 AWG conductor.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.  Replace all missing or damaged conduit and junction box lid bonding jumpers.

When you install signal poles and other poles with fixed bases, attach one grounding conductor to the grounding lug located in the hand hole of each pole.  Join the other required grounding conductors together using irreversible compression type connectors.

When you install lighting standards and other poles with breakaway or slip bases, run a four feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the hand hole of each pole.  With pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector. With concrete foundations, join the equipment grounding conductor from the conduits to the 4 AWG grounding electrode conductor using an irreversible compression connector.

Bond slip-base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the hand hole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a ¾ inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

660-3.08 SIGNAL AND LIGHTING STRUCTURES. 4. Signal Head Mounting. Add the following: When you side-mount 5-section vertically stacked signal heads on poles, install a steel conduit hanger six inches below the upper horizontal framework pipe and secure the vertical framework pipe to the pole.

660-3.09 MAINTAINING TEMPORARY AND EXISTING ELECTRICAL SYSTEMS. Delete this subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If you fail to maintain the electrical systems as specified herein, the Engineer will adjust payments to you according to subsection 643-3.06, Traffic Price Adjustment.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When you begin work, the Engineer will notify you and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility. Therefore, before starting work on the project, you should inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with you. If you begin work before providing the Engineer with an inventory, you waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, all components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems. The State will pay for all electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer. If you do not complete the work, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due you.

When you work on a traffic signal system, print a record of all work performed in the diary found in each controller cabinet. Make sure each entry includes

1.	The dates and times you began and completed your work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing. During shutdowns, use flag persons to control traffic. Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day you retire the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever you reduce their clearance from the traveled way to less than six feet.

During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches in accordance with the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 17.5 feet to 21.5 feet of clearance between the traveled way and the bottom of each signal. For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain nine feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	When the horizontal angle to the side mounted far right signal exceeds 20o, relocate this signal to an overhead location. Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

•	With two or more through lanes, center one signal head over each lane.

•	With one through lane and protected-permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

•	Otherwise, install the relocated signal eight feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain seven feet to nine feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim all signal heads according to Table 660-2 found in subsection 660-3.08, Signal and Lighting Structures.

When no longer required, salvage all original and Department provided equipment according to the plans and item 6 Salvaging or Reusing Electrical Equipment found in subsection 660-3.01, and remove all other materials used in the temporary systems from the project.

Add the following Subsection:

660-3.09(A) TEMPORARY SIGNAL SYSTEMS. Provide temporary traffic signals at the intersections listed in the plans or special provisions. Move traffic through these intersections at all times with fully functional traffic signals, except during shutdowns to change from one system to another. The Engineer will limit temporary signal system shutdowns to the times when traffic restrictions are allowed in Section 643, Traffic Maintenance. During these shutdowns, use flag-control to control the flow of traffic.

Submit a plan for each temporary signal system to the Engineer for approval before implementation. Include the same number of signal heads, signal phases, pedestrian pushbuttons, etc. found in the signal system being replaced or modified in the plan, plus the following details.

1.	A scale drawing of the intersection that includes all lanes, their widths, and auxiliary lane pocket lengths.

2.	The location of all signal poles, controller cabinet, and the load center that will feed the temporary signal system.

3.	The location, sizes, and type of each signal head.

Temporary signal systems may consist of any combination of the existing systems, relocated components of the existing systems, guyed wood poles, and parts of the permanent signal system.  Provide load centers as required in subsection 660-3.09(B), Temporary Electroliers.

Furnish and install all materials and miscellaneous hardware required for a functional traffic signal system.  Furnish all signal faces with back plates and visors. Use temporary controller equipment compatible with equipment used in the Central Region.  All materials shall conform to the plans and specifications, except you may

1.	Install temporary controller assemblies on Type III junction boxes.

2.	Suspend traffic signals from messenger cables provided you mount them with standard span wire hangers and secure them with a second cable to prevent misalignment in a wind.  Leave sufficient signal cable slack at each pole to provide for drip loops and to allow realignment of each signal head.

3.	Use a minimum of two circuits to energize the signals of each phase that include two or more signal faces. The Engineer will allow splices only at the terminal blocks in the signal faces.

Whenever temporary signals include a span wire attached to a permanent signal pole, install a guy on the permanent pole and provide protective collars to prevent chafe damage. Exclude poles with breakaway bases in span wire supported signal systems.

Maintain fully actuated traffic signals during the normal course of construction by installing loop detectors or a video detection system.  During winter shutdown, provide loop detectors in the signal systems according to Section 6.080 of Chapter 6 of the Municipality of Anchorage’s Design Criteria Manual.

Add the following Subsection:

660-3.09(B) TEMPORARY ELECTROLIERS.  When the contract includes Item 660(14), Temporary Electrolier, install temporary electroliers at the following locations.  North of Turnagain Arm of Cook Inlet, the Department will not require lighting from midnight June 7 to midnight July 5.

1.	Along all roadway segments that are illuminated when you begin work and all of the following conditions apply

A.	You maintain traffic on the subgrade, portions of the new pavement structure, or on the existing pavement.

B.	When you cannot make the permanent lighting system operational beforehand.

C.	When, as a result of your grading operations, a vehicle with a four-inch ground clearance and five-feet between the tires would snag on the existing foundations, or the tops of the existing foundations are buried no more than eight inches in the new embankment.

2.	At all locations specified by the Engineer, including

A.	Along detours and diversions, and

B.	Along traveled ways that transition from one typical section to another, and

3.	At all temporary traffic signals.

4.	At the locations shown in the Plans.

Make temporary electroliers operational by sunset on the day you replace or retire the existing system, or open a roadway and/or detour to traffic.

Submit a plan for each temporary electrolier system to the Engineer for his review and approval before implementing it. Allow at least two weeks for review. Provide temporary electroliers on the far right side of all approaches at signalized intersections.  You may install luminaires and mast arms on the signal poles when they do not conflict with other overhead utilities.  Along roadways, choose one of the following options for your temporary lighting plan

1.	When one is included, use the temporary lighting plan detailed in the Plans.

2.	On roadways with existing lighting, provide new foundations and install poles and mast arms sized to keep the existing luminaires in their existing positions horizontally and vertically over the roadway.  In this case, no lighting design is required.

3.	Design your own temporary lighting system using your choice of luminaires, including the luminaires of the permanent lighting system. Use a layout pattern, mounting height, and luminaire offset and spacing that provide a light distribution that conforms to AASHTO’s “An Informational Guide for Roadway Lighting” illuminance method of design.  Design the system for the roadway’s functional class as specified in the Department’s Annual Traffic Volume Report.

Furnish and install all materials and miscellaneous hardware required to provide a functional lighting system, including foundations, branch circuitry, and electrical load centers.  Size the branch conductors to provide a maximum 5% voltage drop at the most remote luminaire.  All materials shall conform to the Specifications.  You may directly bury the illumination cables provided the cables are listed for direct burial.

Use any of the following poles.

1.	Existing light poles found within the project limits and scheduled to be salvaged.

2.	Poles from the permanent lighting system.

3.	The following new poles that you furnish, provided they maintain a minimum 30-feet difference in elevation between a luminaire and the edge of traveled way beneath it.

a.	ANSI Class 4 wood poles.  Install them outside the clear zone during winter shutdown. To determine the clear zone, see subsection 1130.02 of the Alaska DOT/PF Highway Preconstruction Manual.

b.	Steel, aluminum, or fiberglass poles that meet design criteria for 80 mile per hour wind speeds according to AASHTO’s 1994 edition of the “Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals”.

c.	Poles that are part of the temporary signal systems.

Furnish all temporary electroliers, in service at any time from October 1 through May 15 and located within the clear zone, with an approved yielding type base. Approved yielding bases consist of FHWA approved slip bases, transformer bases, or frangible couplings. Install wood poles and all other fixed base poles outside the clear zone or behind guardrail or portable concrete barrier that protects against another hazard.

Install temporary electroliers, in service at any time from May 15 through September and located within the clear zone, with approved yielding bases or with fixed bases shielded by 30 feet of barrier and an FHWA approved end treatment.  Provide two feet of clearance between the barrier and pole. Consider the costs of furnishing the barrier and an end treatment a subsidiary obligation of Item 660(8), Temporary Electrolier.  Replace fixed base poles that are located within the clear zone and which will remain in service after October 1 with yielding base poles at no expense to the State.

Use any of the following load centers to energize the temporary lighting and signal systems. Provide all work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

1.	Permanent load centers installed in their plan location.

2.	Existing load centers scheduled to remain intact until completion of the project. You may relocate and reuse existing load centers only if they are approved.

3.	Approved temporary load centers with photoelectrical controlled lighting circuits.  Provide a temporary load center when you retire an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "Suitable for use as service equipment".

660-3.11 SIGNAL SYSTEM TIMING AND ADJUSTMENTS. Add the following subsection: The Engineer will use Municipality of Anchorage (MOA) signal maintenance personnel for certain work inside controller cabinets. Before they arrive to terminate conductors, ensure you have attached terminal connectors to all conductor ends and labeled all paired loop detector conductors and cables as specified in Subsection 660-3.05, Wiring.  On projects outside the MOA, send controller equipment to the MOA for testing and complete all work specified inside controller cabinets.

Controller Cabinet Preparation. Ship the traffic controller cabinet(s) and equipment to the Municipality of Anchorage Traffic Signal Electronics Shop at 3650 E. Tudor Road, Building C.  They will inspect cabinet wiring, burn in signal equipment, customize cabinets for desired operation, and test the equipment according to Subsection 660-3.07, Shop Tests.

1.	Loop Detector Wiring. Municipality of Anchorage Traffic Signal Maintenance (MOA Signal Maintenance) will test and connect all paired loop detector conductors to the terminal blocks.

2.	Control Cable Wiring. When you modify an operational signal system or controller assembly, MOA Signal Maintenance will connect all control cables within the controller cabinet to the terminal blocks.

3.	Timing Adjustments. During construction, MOA Signal Maintenance may adjust the system and intersection operational timing to accommodate project conditions.

4.	Interconnect Wiring. MOA Signal Maintenance will test and connect all interconnect wiring to the terminal blocks.

660-4.01 METHOD OF MEASUREMENT. Add the following:

Item 660(14), Temporary Electrolier. By each electrolier furnished, installed and maintained as directed by the Engineer.

660 5.01 BASIS OF PAYMENT. Add the following: The Engineer will pay Item 660(26), Signal System Timing and Adjustments, based on paid receipts plus 15 percent for authorized work performed by the Municipality of Anchorage. A directive will not be required to initiate payment for work performed under Item 660(26). Pay all costs of the Municipality re-testing equipment that fails to comply with the Plans and Specifications.

Payment for Item 660(14), the Engineer will pay Temporary Electrolier on a contingent sum basis at the unit price of $1,000/each. The Engineer does not require a change order/directive for this item.

The unit price paid for each temporary electrolier includes full compensation for all work involved in getting your plan and materials approved, and moving, furnishing, assembling, installing, and making each temporary electrolier operational. The price also includes full compensation for installing a foundation (including extended foundations), removing and replacing improvements, installing conductors (in electrical conduit or by direct bury only), maintaining the electrical system, installing temporary electrical load centers when load centers are unavailable for use, and removing the temporary electrolier and its foundation when it is no longer needed.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 660(3) Highway Lighting System Complete on Old Glenn Highway | Lump Sum |
| 660(8) Temporary Lighting System Complete on Old Glenn Highway | Lump Sum |
| 660(17) Traffic Signal System Modifications at Old Glenn Hwy / North Eagle River Access Rd | Lump Sum |
| 660(26) Signal System Timing and Adjustments | Contingent Sum |

Section 670
Traffic Markings

Special Provisions

670 3.01 CONSTRUCTION REQUIREMENTS. Delete Item 4 in its entirety and substitute the following:

4. Methyl Methacrylate Pavement Markings. Apply Methyl Methacrylate markings with truck-mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.  Provide the manufacturer’s installation instructions for the Methyl Methacrylate markings at least 15 days prior to application.  Retain a copy of the instructions for use on the project.

A manufacturer’s representative shall be present on the first day of striping and any additional days as required by the Engineer.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in gallons or liters.

Perform a film test strip at the beginning of each striping shift and when there is a change in asphalt type.   In addition, measure out one (1) gallon liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion.

Apply glass beads as specified in Subsection 712-2.18. Use a minimum drop on rate of 1 lb/yd2 (580 g/m2) for transverse type markings.  Apply glass beads for Type V sprayed material by double bead gun, one gun directly in front of the spray unit and another directly behind.

Remove contaminants such as curing agents, surface oils or existing pavement marking materials prior to applying the new pavement markings. Then, thoroughly clean and dry the roadway surface immediately prior to applying Methyl Methacrylate pavement markings.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 60 mils (1.5 mm).

METHYL METHACRYLATE PAVEMENT MARKING

YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 | Inlaid Markings2 |
| --- | --- | --- |
| Longitudinal Type3 (Center and Edge lines) | 90 mils (2.3 mm) | 230 mils (5.8 mm) |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 120 mils (3.0 mm) | 230 mils (5.8 mm) |
| Neutral Area (Diagonals, Chevrons) | 60 mils (1.5 mm) | Do not inlay these markings |

1. Measure Type V spray without glass beads.  Tolerance is ±4 mils (±0.1 mm).  Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 6” x 12” (150 mm x 300 mm) flat sheet of 80 mils (2 mm) thick aluminum placed in the path of the striping guns.

2. Cut the inlaid slots to a depth of 250 mils (6.35 mm).  Do not over fill the slots.

3. Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 60 mils (1.5 mm) per application pass.

Non-Inlaid Markings

New asphalt pavement: Apply interim non-inlaid Longitudinal and Transverse Type markings at 30 mils (0.75 mm).

Unless directed otherwise by the Engineer, apply the final 60 mils (1.5 mm) of the Longitudinal Type markings once the asphalt has cured for the duration listed below.

Stone Mastic Asphalt Concrete	30 days

All others	15 days

Apply the final Transverse and Neutral Area markings as shown in the application table at this time.  Multiple application passes are required for Transverse Type markings.

Existing asphalt pavement: Apply markings according to the Yield Thickness Table.  Longitudinal Type markings will require multiple application passes.

Inlaid Markings

Apply markings in the milled groves after all millings have been removed. The extruded Methyl Methacrylate may be installed at the final yield thickness at the Engineer’s discretion.

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the removal requirement. Do not use any method utilizing burning with an open flame for removing pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

2.	Width of Stripe. The width shall not vary more than ¼” (6 mm) in width in any 50’ (15m) longitudinal run from the width shown in the Plans.

670-4.01 METHOD OF MEASUREMENT. Add the following after Item 4:

5.	Gallon Liter Basis:  The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in gallons liters.

6.	Foot Meter Basis:  Item 670(10D), Milling for Inlayed Markings will be measured by the linear foot meter of 4 inch 100 mm wide slot ground into the pavement at the depth specified in the Yield Thickness Table and accepted by the Engineer.

670-5.01 BASIS OF PAYMENT. Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B) and 670(10C).  No separate payment shall be made for furnishing and maintaining the MMAMS.

Add the following: Item 670(10D), Milling for Inlayed Markings shall be paid at the contract unit price for the quantity shown in the Bid Schedule.  Payment includes all costs associated with this item, including the removal of millings.

(12/4/02)R246

Section 703
Aggregates

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 |  |  |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| ## No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

(2/28/00)R117USC

703-2.13 AGGREGATE FOR STONE MASTIC ASPHALT PAVEMENT

Coarse Aggregate (retained on the No. 4 sieve).  Coarse aggregate shall be free from clay balls, vegetative matter or other deleterious matter and consist of sound, tough, durable rock of uniform quality not coated with dirt or other finely divided mineral matter.  Crush stone or cobbles to such a degree that all faces are fractured and meet the following requirements:

Property	Test Method	Requirement

Percent of Wear	AASHTO T 96	30 max.

Degradation	ATM T-13	30 min.

Percent Sodium Sulfate Loss	AASHTO T 104	9   max. (5 cycles)

Percent Fracture	WAQTC TM 1

All Faces		75 min.

Thin & Elongated Particles	ATM T-9

3 to 1		20% max.

5 to 1		5%   max.

Absorption	AASHTO T 85	2%   max.

Nordic Abrasion		12.0 max.

Fine Aggregate (passing the No. 4 sieve).  Consist entirely of 100 percent crushed aggregate and be non-plastic as determined by WAQTC FOP for AASHTO T 90.  Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Mineral Filler. Meet AASHTO M 17.  Use rock dust from the aggregate crushing operation or crushed limestone free of agglomerations and sufficiently dry to flow freely.

Blended Aggregate. Blend the aggregate fractions to meet the grading requirements of Table 703-9 as determined by WAQTC FOP for AASHTO T 27/T 11.

TABLE 703-9
STONE MASTIC ASPHALT CONCRETE AGGREGATE

Percent Passing by Weight

Sieve Designation	Requirement

¾ inch	100

½ inch	76-85

3/8 inch	<60

No. 4	20-27

No. 8	14-20

No. 200	8-11

(08/19/02)R164USC

Section 712
Miscellaneous

Special Provisions

712-2.06 FRAMES, GRATES, COVERS AND LADDER RUNGS. Add the following:

Ductile iron castings	ASTM A536 for grade 60-401.

(2/22/00)R78M98

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS. Add the following Subsection:

2.	Performance Properties: Add the following:

k.     Adhesion:	To Portland Cement, minimum 2000 psi to asphalt, dependent on tensile failure of the substrate.

(12/04/02)R246USC

Section 724
Seed

Special Provisions

724-2-02. MATERIALS. Delete Table 724-1 and substitute the following:

TABLE 724-1

SEED REQUIREMENTS

| SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(11/06/02)R52USC

Section 726
Topsoil

Special Provisions

726-2.01 TOPSOIL. Delete table 726-1 and replace Item No. 3 with the following:

TABLE 726-1
TOPSOIL REQUIREMENTS

| REQUIREMENT | CLASS A | CLASS B |
| --- | --- | --- |
| Sieve Designation | Percent Passing by Weight |  |
| 3 inch | - | 100 |
| ½ inch | 100 | - |
| No. 4 | 95-100 | 75-100 |
| No.16 | 64-90 | 50-95 |
| No. 200 | 30-60 | 20-80 |
| Organic Content* | 10% - 40% | 5% minimum |
| Limestone | 1.5 Ton/Acre | - |

*   Determined by loss on ignition of oven dried sample in accordance with ALASKA FOP for AASHTO T 267

(12/05/01)R139USC

Section 730
Sign Materials

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

6.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(12/04/02) R81USC

Section 740
Signals and Lighting Materials

Special Provisions

740-2.02 SIGNAL AND LIGHTING STRUCTURES. Add the following after the fifth paragraph: Furnish all poles and mast arms with a round or 16-sided cross section.  Fabricate all elements greater than ½-inch thick from steels that conform to ASTM A 709 and meet the Fracture Critical Impact Test requirements for zone 3.

Delete the sixth paragraph and add the following: Fabricate poles less than 15 feet long from 4-inch pipe, or from No. 11 or thicker US Standard Gage steel with a post top made from 4-inch pipe.  Use schedule 40 pipe that conforms to ASTM A 53, A 513, or A 618. Construct pedestrian push button posts of 2-1/2 inch nominal diameter schedule 40 pipe that conforms to ASTM A 53.

Delete the seventh paragraph and add the following: Fabricate poles 15 feet or longer and all mast arm from tapered steel tubes that taper at a minimum rate of 0.14-inches of diameter per foot of length.  Fabricate tubes with walls up to ½-inch thick from the prequalified base metals listed in AWS D1.1 and which feature maximum yield strengths of 70,000-psi.

Add the following to the eighth paragraph: The Department will not accept poles and mast arms that are made with laminated steel elements.

Delete the fourteenth paragraph and add the following: Perform all welding to conform to Subsection 504-3.01 8. Welding and the following:

Delete the last two sentences in subparagraph 4 that follow the fourteenth paragraph.

Add the following to subparagraph 5 that follow the fourteenth paragraph. Inspect 100% of all fillet welds by MT.

740-2.11 CONTROLLER CABINET.

1.	STANDARD FEATURES

c.	Cabinet Wiring. Add the following to (1): Furnish all controller cabinets wired to accommodate five 4-channel inductive loop detector units and two 2-channel inductive loop detector units.

740-2.12 STANDARD AUXILIARY EQUIPMENT.

3.	Conflict Monitors. Add the following:

d.	Whenever the Plans or Special Provisions call for a Traffic Management Communication System, supply conflict monitors with an RS-232 serial port that allows the monitor to download information through an external dial-up multi-port modem or to a personal computer using the Microsoft Windows NT operating system.

740-2.13 SPECIAL AUXILIARY EQUIPMENT. Add the following:

6.	Opticom Priority Control System. Install the following components of the 3M Company’s Opticom Priority Control System according to 3M’s written installation instructions at the signalized intersections listed on the plans.

Install the quantity of model 711, 721, and 722 optical detectors on the signal pole mast arms shown on the Plans. Before you install the detectors, gain approval of their final lateral location from the Engineer. See the Plans for installation details.

Install Model 138 Optical detector lead-in cable between the end of each signal mast arm and the controller cabinet. Furnish enough slack in these cables for them to extend 2-feet beyond the end of each signal mast arm and to leave 10-feet of slack in the controller cabinet.  Seal both ends of each lead-in cable with mastic lined, heat shrink tubing end caps.

Before you attach the conductors to the optical detectors, strip the insulation for the conductors and attach all four conductors to ground in the controller cabinet. Attach the signal cable to the confirmation light.  The Municipality of Anchorage Signal Maintenance Section (MOA Signal Maintenance) will tie down the conductors in the controller cabinet under Item 660(26), Signal Timings and Adjustments.

Furnish each controller cabinet with a Model 754 phase selector, a Model 760 card rack, and an Opticom Panel Assembly, U.S. Traffic Corporation part number 103303.  The panel assembly interfaces the card rack to the controller cabinet.  Furnish new controller assemblies with these parts installed by the controller assembly manufacturer.  To retrofit existing controller assemblies, deliver the parts to MOA Signal Maintenance, who will install the parts under Item 660(26), Signal Timings and Adjustments.

7.	Traffic Logging System.  For each traffic signal controller(new and existing), furnish, and others will install in the controller cabinet, a stand-alone unit that collects, time stamps, and stores data in an unattended manner.  The traffic logging system shall conform to the following:

a.	Operation. The unit shall accept a new operating program, operational parameters, and the date and time stamp from a personal computer, downloaded through an RS-232 cable. The use of replaceable proms to change the operational program is unacceptable. Data collection shall be automatic and not require an operator to reset or start operation.

In the event of a power interruption, data collection shall automatically restart at the proper time. Other than the current sample being collected, the unit shall not lose stored data because of the power interruption. At power-up or at the restoration of power after an outage, the unit shall log the date and time at the start of data collection.

The unit shall maintain the operating program, data storage, and date/time for a minimum of 5 years from when power is removed from the unit. The internal program/data size shall be a minimum of 32,000 bytes.

b.	Input Interface. The unit shall have a minimum of 28 inputs.  Furnish all new and existing controller cabinet with a loose Detector Systems TLS-1-C1 interface cable only to connect the unit to the output of the loop detector units.  The Municipality of Anchorage’s Signal Maintenance Section will install the interface cable in the controller cabinets under Item 660(26), Signal System Timing and Adjustments. Do not furnish new controller cabinets with a built-in interface panel.

c.	Output Interface. Furnish all units with an RS-232 serial port that allows a user to download and upload directly between the unit and a personal computer using the Microsoft Windows NT operating system or the external dial-up multi-port modem.

d.	Software. Supply Microsoft Windows NT compatible software and user manuals with the unit that provides the operator an interface to the hardware. Furnish menu driven software that allows an operator to: 1) download to initialize the unit with its operating program and data collection parameters, 2) upload information from the unit (both stored data and real-time data) and 3) transfer a data file to a text file.

The operating program shall provide for month, day, day-of-week, hour, minute, and second information and allow sampling periods of 5, 15, 30, and 60 minutes.

740-2.14 VEHICULAR SIGNAL HEADS.

1.	Conventional Signal Heads.  Delete the first paragraph and replace with the following:  Use LED optical units for red and green indications.  Use incandescent optical units for yellow indications except on mast arm mounted flashing beacons which will be LED optical units and conform to subsection b. of this section.

APPENDIX A

PERMITS / TEMPORARY CONSTRUCTION PERMITS

APPENDIX B

EROSION AND SEDIMENT CONTROL PLAN (ESCP)

APPENDIX C

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX D

MATERIALS CERTIFICATION LIST

APPENDIX E

SIGN DETAILS

APPENDIX F

UTILITY COMPANY REQUIREMENTS

APPENDIX G

ENSTAR NATURAL GAS COMPANY CONSTRUCTION REQUIREMENTS