PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2002 STANDARD SPECIFICATIONS

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

- Alaska Department of Transportation and Public Facilities publication, Alaska Storm Water Pollution Prevention Plan Guide.

- Utility agreements pertaining to the disposition of utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

3.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

4.	There are interim completion dates required.  See subsections 108-1.07 and 407-3.01.

SECTION 101

DEFINITIONS AND TERMS

## Special Provisions

101-1.03 DEFINITIONS. Add the following definition:

NON-FROST SUSCEPTIBLE MATERIAL. Material that contains 6 percent or less passing the No. 200 screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11on minus 3 inch material. (11/29/01)R1USC

SECTION 105

CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from the utilities having facilities in the area.  The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Anchorage Communications Systems (ACS) Anchorage Water & Wastewater Utilities (AWWU) Chugach Electric Association (CEA) Enstar Natural Gas GCI Communications Municipal Light and Power SOA-DOT/PF Anchorage M&O

The Contractor shall call the following utilities and agencies directly:

DOT/PF Maintenance and Operations	269-5700

State (DOT&PF) Street Light & Storm Drain	269-0783

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen- (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen- (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.  (05/31/01)R3M98

Specific coordination requirements for the specific utilities are included below:

Anchorage Water & Wastewater Utility (AWWU): AWWU has existing water valves and sanitary sewer manholes located with this project’s limits.  It shall be the contractor’s responsibility to protect and maintain valves and valve boxes in an operable condition during all phases of construction.

Before the Contractor starting work, AWWU shall check and correct deficiencies that may exist in any AWWU facilities.  The Engineer, Contractor, AWWU representatives shall witness the

condition and location of each AWWU facility.  Failure to participate in this inspection shall result in the forfeiture of the entire Contractor’s right to claim that the AWWU facilities were damaged before beginning the Contractor’s work.

The Contractor shall notify AWWU  (564-2725 or 564-2765) to establish a point of contact and coordination.  The Contractor shall submit a written notice to AWWU Field Service section, a minimum of two calendar days, to schedule for the above walk through inspection.  Submit a copy of the written notice to the Engineer.  The Contractor shall notify AWWU at least fifteen (15) days before the start of this project.

If, at any time, after the preconstruction inspection, AWWU finds any of their facilities damaged or rendered inoperable by the Contractor, the Contractor shall repair the damage at the Contractor’s expense.

The Contractor shall be responsible for the furnishing of traffic control and personnel to assist AWWU while locating and performing the Preconstruction and post construction inspection.  The Contractor shall schedule a final field review with AWWU and the Engineer upon completion of the valve and manhole adjustments.

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:  The following state owned projects will be under construction concurrently with this project:

Project		Central Region Highway.  Data Equipment, 02; MGS-000S (405) / 55585.

Wilder

11301 Lang Street

Anchorage, Alaska 99515

Project.	High Tower Illumination Mast Replacement, NH-000S(387)/54964.

Arctic Electric

PO Box 230508

Anchorage, Alaska 99523

Project:	New Seward Highway at Dimond Interchange Capacity Improvement, 53569 / IM-000S(290) and O’Malley Road and Potter Drive Resurfacing STP-0512(6)/54182

Project:	Dowling Road Old Seward Highway to Lake Otis Parkway, NH-0532(4)/59599

Both projects are being constructed by:

QAP

240 W. 68th Avenue

Anchorage, AK 99518

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above project to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contract.

(2/1/00)R175M98

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

Steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (08/31/99)S 13

106-1.03 TESTING AND ACCEPTANCE.  Add the following:

When the specifications refer to the following test methods, use the corresponding test method shown.

| REPLACE TEST METHOD: | WITH TEST METHOD: |
| --- | --- |
| ATM 203 | Alaska FOP for AASHTO T 267 |
| WAQTC FOP for AASHTO T 89/T 90 | WAQTC FOP for AASHTO T 89 WAQTC FOP for AASHTO T 90 |
| WAQTC FOP for AASHTO T 180 | WAQTC FOP for AASHTO T 99/T 180 and WAQTC TM 9 |
| WAQTC FOP for AASHTO T 224 | Same |
| ATM 212 | ATM T-12 |
| WAQTC FOP for AASHTO T 310 | WAQTC TM 7 |
| WAQTC FOP for AASHTO T 27/T 11 | Same |
| WAQTC TM 1 | Same |
| ATM 306 | ATM T-9 |
| ATM 313 | ATM T-13 |
| WAQTC TM 4 | Same |
| WAQTC FOP for AASHTO T 308 | WAQTC FOP for AASHTO TP 53 |
| WAQTC TM 6 | Same |
| WAQTC FOP for AASHTO T 30 | Same |
| WAQTC FOP for AASHTO T 209 | Same |
| WAQTC FOP for AASHTO T 166/T 275 | Same |
| WAQTC TM 8 | Same |
| ATM 412 | None |
| ATM 414 | ATM T-14 |
| ATM 417 | ATM T-17 |
| WAQTC TM 2 | Same |
| WAQTC FOP for AASHTO T 309 | WAQTC TM 10 |
| WAQTC FOP for AASHTO T 119 | Same |
| WAQTC FOP for AASHTO T 121 | Same |
| WAQTC FOP for AASHTO T 152 | Same |
| WAQTC FOP for AASHTO T 23 | Same |
| ATM 520 | ATM T-30 |

(09/04/02)B01

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

## Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: The Contractor shall obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

The Contractor shall provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual, of any site outside the project limits or not previously permitted.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

The Contractor shall provide a copy to the Engineer, of permits or clearances received before Contractor's use of any site outside the project limits.  Additionally, the Contractor shall provide the Engineer a written statement that the Contractor has obtained necessary permits or clearances. The Contractor shall also provide a written statement to the Engineer listing agencies or offices contacted that responded that required no additional action from the Contractor.

Provide necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

The Contractor shall obtain an Endangered and Threatened Species Clearance from the U.S. Fish and Wildlife Service for sites being used outside the project limits.

No permits were obtained for this project.  The Contractor is required to obtain a Municipal Noise Permit if the Contractor plans to work between 10 pm and 7 am.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following: If the Contractor requires water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (05/29/02)R7M

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.

Add the following before the last paragraph: Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated being within 10 feet of an overhead electrical line.

2.	Operations anticipated being within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(10/23/02)R170USC02

Add the following subsections:

107-1.22 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program			Section 120

Training Program							Section 645

Federal EEO Bid Conditions						Form 25A301

EEO-1 Certification							Form 25A304

DBE Subcontractable Items						Form 25A324

ADOT&PF Training Program Request				Form 25A310

Training Utilization Report						Form 25A311

Contact Report							Form 25A321A

DBE Utilization Report						Form 25A325C

Summary of Good Faith Effort Documentation			Form 25A332A

Required Contract Provisions, Federal-Aid Contracts		Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(9/11/01)S80

SECTION 108

PROSECUTION AND PROGRESS

## Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1.  A progress schedule.  and substitute the following:

1.  	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order in which the work will be carried out and the contemplated dates on which the Contractor and subcontractors will start and finish each of the salient features of the work, including any scheduled periods of shutdown.  Indicate any anticipated periods of multiple-shift work in the CPM Schedule.  If revisions to the proposed CPM Schedule are required, make them promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.  (12/13/02)R261M98

108-1.03 PROSECUTION IN PROGRESS.  Add the following under item no. 1: Use the schedule for coordination and monitoring of work under the contract including the activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.  (4/22/99)R250M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 3nd paragraph under item 2 “Suspension and Extension of Contract Time,” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date. (10/23/02)R242M98

108-1.07 FAILURE TO COMPLETE ON TIME. Add the following:

Interim Completion Work:  If work north of O’Malley Road is not completed before September 30, 2003 the Contractor shall be assessed 50 % of the liquidated damages listed in Table 108-1.

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.05 COMPENSATION FOR EXTRA WORK.  Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.  (1/27/00)R14

109-1.06 PROGRESS PAYMENTS.  Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from subsequent progress payments.  The Engineer, upon receipt of current schedules from the Contractor, will release this amount.  (09/05/01)R137

Add the following section:

## SECTION 120

## DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its

performance of the work. Other relevant factors will be considered. The Engineer makes the determination of CUF after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If the Engineer approves a DBE replacement, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document the following actions constitutes insufficient Good Faith Effort.

- Consideration of subcontractable items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days before bid opening.  The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- The bidder may reject non-competitive DBE quotes. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The DBE Liaison Officer will make the decision on reconsideration.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith

efforts to do so.  If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns trucks (proof of title and/or registration) to be credited for work and that operators are employed by the DBE trucking firm.  A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- Unless the Engineer’s approval is given before subletting, use the same unit of measure as contained in the Bid Schedule for subcontract work, with the exception of truck hauling.

- The DBE will control business administration, accounting, billing, and payment transactions.  The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.

Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION.  Add the following: This work also consists of pavement planing, cleaning, filling or sealing cracks as specified in this section.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS. Add the following:  Removed pavement and millings from Pavement Planing shall become property of the Contractor.

Add the following Subsection:

202-3.06 PAVEMENT PLANING.  Remove existing asphalt concrete pavement by cold planing at locations shown on the plans.  The surface of the pavement after planing shall be uniformly rough grooved or ridged.

Remove planed material from the project immediately after planing.  If the Contractor chooses not to reuse the asphalt material, it shall become the property of the Municipality of Anchorage (MOA).  The Contractor shall deliver and stockpile unused asphalt material to the Municipal Street Maintenance Facility (also known as “Kloep Station”), located at 5701 Northwood Drive, Anchorage, Alaska.  The delivered asphalt shall be fee of objectionable material (concrete and steel) and shall consist of pieces no larger than 1 square yard maximum area dimension.  The Contractor shall coordinate, 48-hours in advance, the location of he placement and the time of delivery, with the Kloep Station management.  (Dan Southard 343-8102).

Keep the rotomilled material free from base course and other deleterious material.

Remove existing asphalt concrete pavement overlay from gutters adjacent to the area being planed.

The existing curb and gutter not designated for removal shall not be damaged or disturbed.  Any damage caused by the planing operation shall be removed and replaced by the Contractor at his expense.

During the planing operation, the Contractor shall concurrently sweep the highway with mechanical sweepers equipped with vacuum and water sprinkling devices to control dust and remove loosened material from the planed areas.

The Contractor shall not allow traffic to travel on surfaces that have an abrupt longitudinal planed edge greater than 2 inches.  In the event that it is necessary to route traffic across such edges, an asphalt concrete transition 2 feet wide shall be placed adjacent to the edge and to gutters.

Maintain a vertical tolerance of 1/8 inch between adjacent passes with the planer.

The planing machine shall be specifically designed for the removal of bituminous pavement without the addition of heat.  The cutting drum shall be a minimum of 5 feet wide and shall be equipped with cutting teeth placed in a variable-lacing pattern to produce the desired finish.

The planing machine shall have the following capabilities:

1.	operating speeds from 0 to 40 feet per minute,

2.	self propelled,

3.	able to spray water at the cutting drum to minimize dust,

4.	able to remove material next to the gutter,

5.	designed so that the operator can at all times observe the planing operation without leaving the controls,

6.	adjustable as to slope and depth,

7.	longitudinal grade control automatically actuated by the use of two 30 foot skis, (use on both sides of the machine) and

8.	able to cut up to 3 inches without producing fumes or smoke.

The Contractor shall provide a smaller machine to trim areas that are inaccessible to the larger machine at manholes, valve covers, curb returns, and intersections.  (2/28/01)R143USC

After completing pavement planning, clean and fill or seal cracks in the pavement surface.  Cleaning of cracks and application of sealant shall be done according to the manufacturer's recommendations.  Cracks greater than 1 inch (+1 inch) in width shall be cleaned of loose material to full depth then filled using Asphalt Concrete Pavement, Type IV, Class B, tamped in place.

202-5.01 BASIS OF PAYMENT.  Add the following:  Replace any loop detectors damaged by the planing operation according to Section 660.  Damaged loop detectors that are encountered within the planing depth specified on the plans shall be measured and paid as Item 660(11) Traffic Loop.  The Contractor shall replace other loops damaged by the planing operation without compensation.

Cleaning, filling or sealing cracks in the pavement surface is subsidiary to Item 202(15) Pavement Planing.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

202(15)	Pavement Planing	Square Yard

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

Special Provisions

301-2.01 MATERIALS.  Replace the first sentence with the following:  Use aggregate that conforms to subsection 703-2.03 for gradation D-1.

Add the following after the first paragraph:  At the Contractor’s option recycled asphalt material (RAM) may be substituted for crushed aggregate base course, inch for inch, if RAM is crushed or processed to 100 percent by weight passing the 11/2 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

301-3.03 SHAPING AND COMPACTION.  Add the following:  Compact base course material placed against the outside pavement edge at the roadway shoulder to the satisfaction of the Engineer.  Field densities will not be performed.

301-5.01 BASIS OF PAYMENT.  Add the following***deleted***

SECTION 401

## ASPHALT CONCRETE PAVEMENT

## Special Provisions

401-2.01 COMPOSITION Of Mixture - Job Mix Design. Add the following to the first paragraph after ATM T-17: (version 01/93).

Add the following: No testing is required for the preleveling material.  The Engineer will inspect and accept this material.

In table 401-1 under Voids in the Mineral Aggregate (VMA), %, min. change “Type III” to “Type III, IV”.

401-2.03 ASPHALT Materials.  Delete the second paragraph and substitute the following.

Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

d.	Type and percent of anti-strip added.

CONSTRUCTION REQUIREMENTS

401-3.07 PREPARATION OF EXISTING SURFACE. Add the following:

Planing breakthrough areas shall be patched to match the planed surface with Asphalt Concrete Pavement, Type II or Type IV, and be paid for as leveling course material.  Contractor shall notify the Engineer of any pavement areas that might be considered thin or unstable.

Contact surfaces of curbing, gutters, manholes, and other structures shall be coated with a thin, uniform coating of tack coat material conforming to Section 402 prior to the asphalt mixture being placed.

Surfaces that have received a prime coat or tack coat, shall be allowed to cure, prior to placement of asphalt concrete pavement.

401-3.13 COMPACTION.  Add the following to the first paragraph: Use pneumatic tire rollers to compact Preleveling Asphalt Concrete, Type IV, Class B.

401-3.15 SURFACE TOLERANCES.  Add the following before the first paragraph: Before placing Asphalt Concrete pavement, the rutted pavement sections that have been Preleveled with Asphalt Concrete, Type IV, Class B shall be tested after rolling at selected locations using a 10 foot straightedge.  Correct variations from the testing edge, between any two contacts, of more than 3/16 inch.  The preleveling material shall be no greater than 1/2 inch higher than the existing pavement at the edges.

401-4.01 METHOD OF MEASUREMENT.  Add the following: Item 401(9) will be measured by the lane station.  A lane station is defined as 12 feet wide containing two ruts 100 feet long.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: Costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.02 ACCEPTANCE Sampling And Testing.  Replace the last sentence of the seventh paragraph with the following: Use WAQTC TM 4 or AASHTO T 308 to determine the asphalt cement content.  Determine the moisture content with WAQTC TM 6.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 1,000 tons.

401-5.01 BASIS OF PAYMENT.  Add the following: The anti-stripping additive and asphalt cement required for preleveling the highway shall be subsidiary to Item 401(9), Asphalt Concrete, Type IV, Class B.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

401(9)	Asphalt Concrete, 	Lane Station

Type IV, Class B

(10/24/02)R199USC

Add the following Section:

# SECTION 407

# STONE MASTIC ASPHALT CONCRETE PAVEMENT

# Special Provisions

407-1.01 DESCRIPTION.  This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the Stone Mastic Asphalt (SMA) Concrete mixture on a previously prepared surface, as specified in the contract and in conformance with the lines, grades and thickness shown on the plans.

407-2.01 COMPOSITION OF STONE MASTIC ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN.  Stone Mastic Asphalt Concrete mixture shall be composed of aggregate, asphalt cement, and required additives combined within the limits specified in the contract.

Provide a Stone Mastic Asphalt Concrete mixture that meets the Stone Mastic Asphalt Concrete mix design requirements of Table 407-1.

Submit the following to the Engineer at least 15 working days prior to the production of Stone Mastic Asphalt Concrete mixture:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-9, Stone Mastic Asphalt Concrete Aggregate.  Stone Mastic Asphalt Concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended.  Total sample size of 500 pounds proportioned to the Job Mix Design blend.

3.	A minimum of five gallons, in one-gallon metal containers, of the asphalt cement proposed for use in the mixture.  Include name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a recommended mixing temperature.

4.	A minimum one-pint sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

5.	A minimum 5 pound sample of the cellulose stabilizing additive proposed for use in the mixture, including name of product, manufacture, test results as required in Section 407-2.05 and manufactures certificate of compliance with Section 407-2.05.

The Engineer will then evaluate the material and the proposed gradation using the Superpave Gyratory Compactor, AASHTO PP 41, and the mix design requirements of Table 407-1 to establish the Job Mix Design.  Approved Job Mix Designs will become a part of the contract and will specify the target value for asphalt cement content, additives, and the allowable mixing temperature range.  Up to12 working days will be required to determine the Job Mix Design after receipt of items specified above.

TABLE 407-1

STONE MASTIC ASPHALT CONCRETE

MIX DESIGN REQUIREMENTS

| Design Parameters | Requirement Standard Material |
| --- | --- |
| Voids in total mix, percent | 4 |
| Compaction, Gyration Ndesign | 100 |
| Dust-asphalt ratio (the percent of material passing the No. 200 sieve divided by the percent of effective asphalt cement, by weight of mix) | 0.6-1.6 |
| Voids in the mineral aggregate (VMA), min. | 18.0 |
| Voids in Coarse Aggregate (VCA) Of The Mix, % | Less Than VCA Of The Coarse Aggregate As Determined By AASHTO T 19 |
| Rut Index, mm, maximum. | 3 |
| Minimum Asphalt Cement Content, % | 6.2 |

Approved Job Mix Designs will have the full tolerances shown in Table 407-4 applied and will not be limited to the broad band listed in Table 703-9.  Tolerances will not be applied to the largest sieve specified.

Submit changes in the Job Mix Design warranted by failure to meet the requirements of Table 407-1, changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio in the same manner as the original submittal.  A new Job Mix Design will only apply to Stone Mastic Asphalt Concrete mixture produced after submittal of the changes.

Mix designs after a Job Mix Design has been approved will be assessed a fixed fee of $3,500.00 each.

407-2.02 AGGREGATES.  Aggregates shall be of the type specified in the contract and shall conform to the requirements of Subsection 703-2.13.  Use a minimum of three stockpiles for crushed Stone Mastic Asphalt Concrete aggregate (coarse, intermediate, and fine).

407-2.03 ASPHALT MATERIALS.  Provide the grade of asphalt cement specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702.  When not specified, the grade of asphalt cement shall be PG 58-28.

Asphalt cement may be conditionally accepted at the source source by providing a manufacture's certificate of compliance in accordance with Subsection 106-1.05, and test results of the applicable quality requirements of Section 702 before the material is shipped.

Shipping documents shall include the following:

1.	Manufacturers certificate of compliance, Subsection 106-1.05

2.	Conformance test results of the batch, Section 702.

3.	Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

407-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM T-14 and included in the approved Job Mix Design.  At least 70 percent of the aggregate shall remain coated when tested in accordance with ATM T-14.

407-2.05 STABILIZING ADDITIVES.  Use cellulose stabilizing additive.  The dosage rate for cellulose is 0.3 percent by weight of the total mix.  The allowable tolerance per ton shall not exceed ± 10 percent of the required weight of the stabilizing additive.

Cellulose stabilizing additive shall conform to the properties shown in Table 407-2.

TABLE 407-2

CELLULOSE STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Sieve Analysis: Method A - Alpine Sieve Analysis (1): Fiber Length Percent passing No. 100 sieve Method B - Mesh Screen Analysis(2): Fiber Length Percent passing No. 20 sieve Percent passing No. 40 sieve Percent passing No. 140 sieve | 0.25 in. (max) 60-80 0.035-0.060 in. (avg.) 75-95 55-75 10-30 |
| Ash Content (3) | 20% non-volatiles (max) |
| pH (4) | 7.5 +/-1.0 |
| Oil Absorption (5) | 5.0 +/-1.0 times fiber weight |
| Moisture Content (6) | < 5% |
| Bulk Density (7) | 1.25-2.50 lbs/ft3 |

Notes:

(1)	Method A - Alpine Sieve Analysis.  This test is performed using an Alpine Air Jet Sieve (Type 200 LS).  A representative 5 gram sample of fiber is sieved for 14 minutes at a controlled vacuum of 22 inches (+/- 3 inches) of water.  The portion remaining on the screen is weighed.

(2)	Method B - Mesh Screen Analysis.  This test is performed using No. 20, 40, 60, 80, 100, and 140 sieves, nylon brushes and a shaker.  A representative 10 gram sample of fiber is sieved, using a shaker and two nylon brushes on each screen.  The amount retained on each sieve is weighed and the percentage passing calculated.

(3)	Ash Content.  A representative 2-3 gram sample of fiber is placed in a tared crucible and heated between 1100 and 1200 F for not less than two hours.  The crucible and ash are cooled in a desiccator and reweighed.

(4)	pH Test.  5 grams of fiber is added to 100 ml of distilled water, stirred and let sit for 30 minutes.  The pH is determined with a probe calibrated with pH 7.0 buffer.

(5)	Oil Absorption Test.  5 grams of fiber is accurately weighed and suspended in an excess of mineral spirits for not less than five minutes to ensure total saturation.  It is then placed in a screen mesh strainer (approximately 0.5 square millimeter hole size) and shaken on a wrist action shaker for ten minutes (approximately 1.25inch motion at 240 shakes/minute).  The shaken mass is then transferred without touching, to a tared container and weighed.  Results are reported as the amount (number of times its own weight) the fibers are able to absorb.

(6)	Moisture Content.  10 grams of fiber is weighed and placed in a 250 F forced air oven for two hours.  The sample is then reweighed immediately upon removal from the oven.

(7)	Bulk Density.  Fluff fiber with air or Hobart Mixer, weigh out 25 grams of fiber, place in 100 ml cylinder, tap cylinder and measure volume.

407-2.06 PROCESS QUALITY CONTROL.  Sample and test materials for process QC of the Stone Mastic Asphalt Concrete mixture in accordance with Subsection 106-1.03.

Failure to perform process QC forfeits the Contractor's right to retests as provided for in Subsection 407-4.02.

CONSTRUCTION REQUIREMENTS

407-3.01 WEATHER LIMITATIONS.  Do not place Stone Mastic Asphalt Concrete mixture when it is raining or when rain is imminent, on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture.  Do not place Stone Mastic Asphalt Concrete mixture after August 15 of any year.

407-3.02 EQUIPMENT.  Use equipment in good working order and free of asphalt concrete mix buildup.  Make equipment available for inspection and demonstration of operation 24 hours before placement of asphalt concrete mix.

407-3.03 BITUMINOUS MIXING PLANTS.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the data to the Engineer at least one day prior to Stone Mastic Asphalt Concrete production.    Maintain a current Air Quality Permit issued by the State Of Alaska.

Provide a scalping screen on the asphalt plant to prevent oversize material or debris from being incorporated into the Stone Mastic Asphalt Concrete mixture.  Provide aggregate and asphalt cement sampling locations meeting OSHA safety requirements.

Do not mix Stone Mastic Asphalt Concrete mixtures produced from different plants.

Do not use proportioning (batch) scales for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

407-3.04 HAULING EQUIPMENT.  Haul Stone Mastic Asphalt Concrete mixture in trucks with tight, clean, smooth metal beds thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent.  Do not use any petroleum product (e.g. diesel or fuel oil) as an asphalt release agent

Cover the Stone Mastic Asphalt Concrete mixture with a secured watertight canvas cover extending at least one foot over the sides and ends of the truck bed.

407-3.05 ASPHALT PAVERS.   Use self-propelled asphalt pavers equipped with a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a mobile string-line (ski) at least 30 feet in length, or other approved grade follower to automatically actuate the paver screed control system. Use grade control on either a) both the high and low sides or b) grade control on the high side and slope control on the low side.

Equip asphalt pavers with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip receiving hoppers with a distribution system to place the Stone Mastic Asphalt Concrete mixture uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the Stone Mastic Asphalt Concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Place auger extensions within 1.5 feet of the screed extension on both sides, or per written manufacturer’s recommendations.

The use of a pickup machine to transfer Stone Mastic Asphalt Concrete mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of

collecting the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any detrimental effects are observed.

407-3.06 ROLLERS.  Supply a minimum of three rollers weighing a minimum of 12 tons each to compact the Stone Mastic Asphalt Concrete mixture to the required density while maintaining the pace of the paving operations.  Rollers shall be of the static steel wheel or vibratory steel wheel type. Use self-propelled rollers specifically designed to compact hot asphalt concrete mixtures and capable of reversing without backlash.  The use of equipment that results in crushing of the aggregate, or pick-up of the Stone Mastic Asphalt Concrete mixture will not be permitted.

Follow the paving plan established for the project.

407-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces in conformance with the plans and specifications.  Clean existing paved surfaces of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

After completion of planing of a section of the roadway, the Engineer shall inspect that section for areas of distress or failure.  Areas requiring repair shall have the remaining pavement removed, and the distressed area shall be excavated to the depth and limits directed by the Engineer.  Backfill the excavated area with crushed aggregate base course material in conformance with the requirements of Section 301, asphalt concrete leveling course, or with Stone Mastic Asphalt Concrete as directed by the Engineer.

Prior to placing Stone Mastic Asphalt Concrete mixture, uniformly coat pavement surfaces and contact surfaces of curbing, gutters, manholes, and other structures with tack coat material conforming to Section 402.

407-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of the asphalt cement to the mixer at a uniform temperature, within the Job Mix Design mixing temperature range.

407-3.09 PREPARATION OF AGGREGATES.    Provide adequate dry storage for the mineral filler and stabilizing additive.  Dry the aggregate for Stone Mastic Asphalt Concrete so the moisture content of the Stone Mastic Asphalt Concrete mixture, sampled from behind the screed prior to compaction, is less than 0.5% (by total weight of mix) as determined by WAQTC TM 6.

Heat the aggregate for Stone Mastic Asphalt Concrete to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Stone Mastic Asphalt Concrete mixture in which soot or fuel is present is considered unacceptable per Subsection 105-1.11.

407-3.10 MIXING.  Uniformly combine the aggregate, asphalt cement, additives, and stabilizing additives in the amounts required by the Job Mix Design.  Mix the materials such that a complete and uniform coating of the aggregate is obtained.

1.	For batch plants.  Add the stabilizing additive through a separate inlet directly into the weigh hopper above the pugmill.  Time the addition of the stabilizing additive to occur during the hot aggregate charging of the hopper.  Provide adequate dry mixing time to ensure proper blending of the aggregate and fiber stabilizer.

2.	For drum mix plants.  Add cellulose stabilizing additive into the drum mixer at the same point the asphalt cement is added.   Operate the drum mixer to ensure complete blending of the stabilizing additive into the mix.

Dry mix Stone Mastic Asphalt Concrete with cellulose stabilizing additive a minimum of 15 seconds, and wet mix a minimum of 40 seconds.  In batch plants, place the dry aggregate in motion immediately before the addition of asphalt cement.  Use a wet mixing time adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

Mix the Stone Mastic Asphalt Concrete within the temperature range determined by the Job Mix Design.

Proportion the mineral filler into the mixture uniformly and in the desired quantities.  Provide appropriate equipment for accurately proportioning the relatively large amounts of mineral filler required for a Stone Mastic Asphalt Concrete mixture.

407-3.11 TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Temporary storing or holding Stone Mastic Asphalt Concrete mixture in silo type storage bins is permitted provided that the characteristics of the Stone Mastic Asphalt Concrete mixture are not altered.  Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Dispose of rejected Stone Mastic Asphalt Concrete mixture at no cost to the Department.

407-3.12 SPREADING AND PLACING.  Submit a Paving Plan for the Engineer's review a minimum of five working days prior to initiating paving operations.  The plan shall consist of, but not be limited to the following:

1.	Paving schedule to include sequence of operations.

2.	Operational details to include:

a.	Plant operating capacity and target production rate.  Process control testing frequency for gradation, moisture, asphalt cement content, and compaction.

b.	Number and capacity of trucks, cycle time, and delivery rate.

c.	The manufacturer and model of the paver and pickup machine, to include information on grade followers, sensors, operating speed and production rate of the pavers.

d.	Number, type, and weight of rollers, and number of impacts per foot.

e.	Location and method of constructing longitudinal and transverse joints.

f.	Construction plan for paving intersections and driveways.

Place Stone Mastic Asphalt Concrete mixture upon an approved surface, spread and strike off and compact to the required compacted thickness.  Spread and compact in one layer if the total thickness is 3 inches or less.  Use asphalt pavers to distribute the Stone Mastic Asphalt Concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 407-3.14.

Use hand tools to spread, rake, and lute the Stone Mastic Asphalt Concrete mixture in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.  In such areas, compact the Stone Mastic Asphalt Concrete mixture to the required compacted thickness.

Any Stone Mastic Asphalt Concrete mixture that is contaminated or segregated will be rejected.

Pave adjacent traffic lanes to the same elevation within 24 hours when the section of roadway being paved is open to traffic unless prevented by weather or other factors beyond control.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

When multiple lifts are specified in the contract, do not place the final lift until lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted.

Do not pave against new concrete curb until it has cured for at least 72 hours.

407-3.13 COMPACTION.  Immediately after spreading, thoroughly and uniformly compact the Stone Mastic Asphalt Concrete mixture by rolling.

Roll with a minimum of three steel wheel rollers of a minimum weight of 12 tons each.  Follow the paving plan established for the project to provide the specified pavement density. Rollers with vibratory engaged may be used for a maximum of three passes.  Operate rollers at a uniform speed to obtain no less than 10-12 impacts per foot with the drive roller nearest the paver.  Set rollers for high frequency and low amplitude.  Verify roller settings in the presence of the Engineer.  Roll until roller marks are eliminated and the specified pavement density has been obtained.

Prevent adhesion of mixture to the rollers by moistening the wheels with water mixed with detergent or other approved material.  Replace rollers showing evidence of excessive pick-up.

Stop rolling operations once sufficient in-place density has been achieved.  Where migration of asphalt cement and filler to the compacted pavement surface has occurred, remove and replace with fresh Stone Mastic Asphalt Concrete mixture.

The target value for density will be 94% of the maximum specific gravity (MSG) as determined in accordance with WAQTC FOP for AASHTO T 209.  For the first lot of Stone Mastic Asphalt Concrete, the Job Mix Design will determine the MSG.  For additional lots, the MSG will be determined by the sample from the first sublot of the lot.  Acceptance testing for field density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.  (Acceptance testing for field density of leveling course will not be done.)

Grade with rakes and lutes and compact with mechanical tampers areas not accessible to rollers.  Use a trench roller in depressed areas to achieve the required compaction.

Remove any Stone Mastic Asphalt Concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective and replace with fresh Stone Mastic Asphalt Concrete mixture and compact to conform to surrounding areas.  Remove and replace any area showing an excess or deficiency of asphalt cement.

Do not leave rollers, other equipment, or vehicles standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

407-3.14 JOINTS.  Minimize the number of joints and construct to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.

The minimum specification for longitudinal joint density will be 91 percent of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.

If the average joint density for any lot is less than 91.0% MSG, immediately change and improve the method used for joint construction

If the average joint density of a lot is less than 91.0% MSG, seal the joints constructed in that lot with a joint sealing method approved by the Engineer.

No additional cost or contract time will be paid to repair or seal joints.  Seal or repair joints before paint striping.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Remove full depth improperly formed joints resulting in surface irregularities, replace with fresh Stone Mastic Asphalt Concrete mixture, and thoroughly compact.  Do not roll joints after the material has cooled below 150 degrees Fahrenheit.  Pavement removal shall be precut to a neat line with a power driven saw.

Apply a tack coat of asphalt cement or asphalt emulsion on cold joints and allow to break before placing any fresh Stone Mastic Asphalt Concrete mixture against the joint.  Apply the tack coat just prior to paving.

Form transverse joints by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints between 15-25 degrees.

Offset longitudinal joints in one layer from those in the layer immediately below by at least 6 inches.  Align the joints in the top layer at the centerline or lane lines.  Where pre-formed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

407-3.15 SURFACE TOLERANCE.  The surface of the Stone Mastic Asphalt Concrete will be measured after final rolling at selected locations using a 15 foot straightedge.  Correct variations of the surface greater than 0.25 inches from the testing edge of the straightedge between any two contacts.

The Engineer mill measure the surface smoothness of the top lift of the asphalt in the driving lanes with an inertial profiler before final acceptance of the project.  Remove and replace or grind any portion of final pavement surface having a smoothness Profile Index (PrI) greater than 15.0 inches per mile in a 0.10 mile segment.  PrI will be calculated using a0.2 inch/mile blanking band.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, within 25 feet of bridge abutments, or within 25 feet of exiting pavement that requires difficult matching.

407-3.16 PATCHING DEFECTIVE AREAS.  Remove any Stone Mastic Asphalt Concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective.  Skin patching is not permitted.  Remove defective materials for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with tack coat conforming to Section 402 and allow to cure.  Place and compact fresh Stone Mastic Asphalt Concrete mixture in sufficient quantity so that the finished surface conforms to grade and smoothness requirements.  Compact the Stone Mastic Asphalt Concrete mixture to the density specified.  No payment shall be made for material replacing defective material.  Costs associated with patching defective areas shall be borne by the Contractor.

407-3.17 TEST SECTION.  Place a minimum of 300 tons of Stone Mastic Asphalt Concrete mixture in a test section at a location approved by the Engineer at least 5 days prior to proceeding with Stone Mastic Asphalt Concrete paving. Use an underlying grade or pavement structure similar to project conditions for the test section Use the test section to verify plant calibration and compaction characteristics of the Stone Mastic Asphalt Concrete mixture.  Use the same equipment that will be used for the project.

Stone Mastic Asphalt Concrete mixture placed in the test strip that duplicates mix design parameters and meets specifications will be measured and paid for at contract prices.  No payment will be made for mixture that does not duplicate the mix design and meet specifications.  If the test strip is placed

within the project limits and does not duplicate the mix design and not meet specifications, it shall be removed at the Contractor's expense.  Additional test sections will continue to be placed until all criteria are meet.

407-4.01 METHOD OF MEASUREMENT.  Stone Mastic Asphalt Concrete mixture will be measured by the ton in accordance with Section 109.  The weight used shall be the tons used in the accepted pavement and no deduction will be made for the weight of asphalt cement material, anti-stripping agent or any other additive used in the mixture.

A price adjustment, when applicable, will be made based on a quality level analysis under Subsection 407-4.03.

Asphalt cement will be measured by the ton based on the weight of asphalt cement calculated using the percent of asphalt cement for each sublot as determined by WAQTC TM 4.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.

The Engineer may direct at any time that tankers be weighed before and after unloading in his presence.  If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

No payment will be made for any asphalt cement in excess of 0.4 percent above the optimum asphalt cement content specified in the Job Mix Design.

Any leftover, waste, or diversion will be computed in a manner to be determined by the Engineer.  The weight of asphalt cement in waste Stone Mastic Asphalt Concrete will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Longitudinal joints will be measured by the foot.  *** deleted****

407-4.02 ACCEPTANCE SAMPLING AND TESTING.  The quantity of Stone Mastic Asphalt Concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance.  The Department has the exclusive right and responsibility for determining the acceptability of materials incorporated into the project.  The Engineer shall perform acceptance sampling and testing.  The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection.  If the project has more than one lot and less than eight additional sublots have been

sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot will include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 4,999 tons, the contract quantity will be considered one lot.  The lot will be divided into 10 equal sublots and randomly sampled for asphalt cement content, density and gradation in accordance with this subsection except that retests will not be allowed.  The lot will be evaluated for price adjustment in accordance with subsection 407-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 1,500 tons, Stone Mastic Asphalt Concrete pavement shall be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the Stone Mastic Asphalt Concrete mixture to the specified depth and finished surface requirements and tolerances.  Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 150 degrees F before completing compaction, or is any other way defective shall be removed and replaced with fresh Stone Mastic Asphalt Concrete mixture.  Removal and replacement of defective pavement shall be at no additional cost to the Department.

Asphalt cement content will be determined from Stone Mastic Asphalt concrete mixture samples in accordance with WAQTC TM 4.  Aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.  Stone Mastic Asphalt Concrete mixture samples will be taken from behind the screed before compaction.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.

Cut full depth core samples from the finished lift for density acceptance testing in accordance with WAQTC FOP for AASHTO T 166/T 275 within 24 hours of final rolling.  Neatly cut 6-inch minimum diameter core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the cores while removing.  Do not cut samples from Stone Mastic Asphalt Concrete mats on bridge decks.  Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 407(5), Asphalt Price Adjustment.

Backfill voids left by sampling with fresh Stone Mastic Asphalt Concrete mixture and compact within 24 hours of sampling.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 407(5), Asphalt Price Adjustment.

Samples will be evaluated for acceptance in accordance with Subsection 407-4.03.

A retest of any sample outside the limits specified in Table 407-4 may be requested.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  Verbal requests with the written request to be delivered after the specified 7 days will not be accepted.  The sample(s) for density retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s).  The Engineer will mark the sample location for the retest.  Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s).  The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample will be allowed.

Remove and replace at no additional expense to the Department any sublot represented by a test or retest that meets or exceeds any of the rejection limits in Table 407-4.  The Engineer will determine the limits of the material represented by the sublot.

407-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  The following method of price adjustment will be applied to Stone Mastic Asphalt Concrete mixture when the contract quantity equals or exceeds 5,000 tons except as defined in Subsection 407-4.02.  The longitudinal joint density price adjustment will apply when Stone Mastic Asphalt Concrete quantities are equal to or greater than 1,000 tons.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis Method as specified in Subsection 106-1.03 to determine the estimated percent of a lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results.  Outlier test results shall not be included in the price adjustment calculations.  If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment.  The density test result for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s).  Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0 percent and a contractor's risk of 5.0 percent unless otherwise specified.  AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100 percent pay.  The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained.  The maximum pay factor obtainable is 1.05.  The maximum pay factor for the largest sieve size specification for gradation shall be 1.00.  The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for Stone Mastic Asphalt Concrete mixture that includes gradation and asphalt cement content.  The second factor is a separate pay factor for density.

A lot containing non-specification material (less than 1.00 pay factor) may be accepted at an adjusted price provided the pay factor is at least 0.75 and the Engineer does not identify isolated defects.  A lot containing non-specification material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11.

The Engineer can reject material that appears to be defective based on visual inspection.  Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis.  Procedures for computation of composite pay factors are as follows:

1.	Eliminate test results found to be outliers by SP-7 (Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ  =  summation of

x=Σxn

x  =  individual test value to xn

n  =  total number of test values

x is rounded to the nearest tenth for density and all sieve sizes except the No.200 sieve.  x is rounded to the nearest hundredth for asphalt content and the No.200 sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)  =  summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2  =  square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest 0.01 for density and all sieve sizes except the No.200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt content and the No.200 sieve.

If the computed sample standard deviation (s) is less than 0.001, then use s = 0.20 for density and all sieve sizes except the No.200 sieve.  Use s = 0.020 for the No.200 sieve and asphalt cement content.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL).  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 407-4.  The tolerances for the largest sieve specified will be plus 0% and minus 1%.  The TV is the specification value defined by the Job Mix Design.  The TV for density is 94 percent of the maximum specific gravity (MSG).  The LSL for density is 92 percent of MSG and the USL is 96%.

4.	Compute the upper quality index (QU):

Where:	USL = Upper Specification Limit

QU=USL-xs

QU is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

Where:	LSL = Lower Specification Limit

QL=x-LSLs

QL is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit which corresponds to a given QU) from Table 106-1.  For negative values of QU, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

7.	Determine PL (percent within the lower specification limit which corresponds to a given QL) from Table 106-1.  For negative values of QL, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

8.	Determine the Quality Level (QL), the total percent within specification limits, for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

- Using the Quality Levels from step 8, determine the lot Pay Factor for Density (DPF), and gradation and asphalt cement content pay factors (PF) from Table 106-2.

10.	Calculate the lot Stone Mastic Asphalt Concrete mixture Composite Pay Factor (CPF) for asphalt cement content and gradation using the following formula:

Round the Composite Pay Factor (CPF) to the nearest hundredth.

CPF=[f34} }  \(  { ital PF}  rSub { size 8{3/4)+f12} }  \(  { ital PF}  rSub { size 8{1/2)+.......fac(PFac)]Σf

Table 407-5 is used to determine the weight factor (f) for each sieve size and asphalt cement content.

Table 407-4

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL | Rejection Limits |
| --- | --- | --- | --- |
| ¾ inch sieve | TV-4.0 | TV+4.0 | TV + 6.0 |
| ½ inch sieve | TV-4.0 | TV+4.0 | TV + 6.0 |
| 3/8 inch sieve | TV-4.0 | TV+4.0 | TV + 6.0 |
| # 4 sieve | TV-4.0 | TV+4.0 | TV + 5.0 |
| # 8 sieve | TV-4.0 | TV+4.0 | TV + 5.0 |
| # 200 sieve | TV-2.0 | TV+2.0 | TV + 3.0 |
| Asphalt % | TV-0.40 | TV+0.40 | TV + 0.5 |
| Density | 92% | 96% | 91% or 98% |

Table 407-5

WEIGHT FACTORS

| Sieve Designation | Factor (f) |
| --- | --- |
| ¾ inch sieve | 2 |
| ½ inch sieve | 10 |
| 3/8 inch sieve | 10 |
| # 4 sieve | 10 |
| # 8 sieve | 8 |
| # 200 sieve | 20 |
| Asphalt % | 40 |

407-5.01 BASIS OF PAYMENT.  The accepted quantity will be paid for at the contract unit price for the pay items listed below, complete in place.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $4.95 per 0.25 percent additive per ton of asphalt cement.

Stabilizing additives will be subsidiary to Item 407(1), Stone Mastic Asphalt Concrete.

A change order/directive is not required for anti-stripping additive or Asphalt price adjustment pay items.  The approved Job Mix Design will initiate Item 407(4), Anti-Stripping Additive at the prescribed rate and the Notice to Proceed shall constitute the notice required to initiate Item 407(5), Asphalt Price Adjustment.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot, fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 407-2.01, and fees accrued for failure to cut cores and/or backfill voids left by sampling in the allotted time as outlined in Subsection 407-4.02.  The Asphalt Price Adjustment will be algebraically added to the Contractor's

payment for Stone Mastic Asphalt Concrete.  Individual lot price adjustments will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (Tons in lot) x (PAB)

PAB = Price Adjustment Base   $60.75/ Tons

* Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest    value.

Calculate a separate price adjustment based on the average of all the required joint densities taken on the project.  Determine the incentive / disincentive as follows and apply under Item 407 (5), Asphalt Price Adjustment.

- If the average joint density is greater than 91%, apply the following incentive:  Incentive = ($0.25 per lineal foot)x(lineal feet of paved joint for the entire project)x (project average joint density % - 91%).

- If the average joint density is less than 91%, apply the following disincentive:  Disincentive = ($1.00 per lineal foot)x(lineal feet of paved joint for the entire project)x(project average joint density % - 91%).

Calculate and apply a separate asphalt Smoothness Price Adjustment as measured according to subsection 407-3.15.  Calculate the smoothness price adjustment as follows;

Smoothness Price Adjustment ($) = SA x  PAB x  PQ

If PQ is less than 1500 tons,	SA = 0

If PQ is 1500 to 5000 tons, 	SA = 0.1333- 0.01666 (PrI)

If PQ is 5000 + tons,		SA = 0.0666- 0.0083 (PrI)

SA = Smoothness Adjustment factor

PrI = Profile Index pavement smoothness (inches/mile)

PAB = Price Adjustment Base, 407-4.03

PQ =  final pay quantity of 407(1) in tons

Apply smoothness price adjustment as an incentive/disincentive under Item 407(5) Asphalt Price Adjustment.

*** deleted ****

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

407(1)	Stone Mastic Asphalt Concrete	Ton

*** deleted ***

407(2A)	Asphalt Cement, Grade ____	Ton

407(2B)	Asphalt Cement, Grade ____  	Ton

407(4)	Anti-Stripping Additive	  Contingent Sum

407(5)	Asphalt Price Adjustment	  Contingent Sum

(08/19/02)R163USC

Add the following Section:

SECTION 408

ASPHALT CONCRETE PAVEMENT

408-1.01 DESCRIPTION.  This work consists of constructing one or more courses of plant mixed hot asphalt on an approved surface, as specified and in conformance with the lines, grades and thickness shown on the plans.  Superpave mix design procedures will be used to design the mix.

408-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN.  The Job Mix Design will be developed using Asphalt Institute’s SP-2 and also meet the requirements of Table 408-1 and Table 408-2 and SP-2 TABLE 5.2.  Evaluation of moisture sensitivity by AASHTO T 283 will not be part of the mix design process

TABLE 408-1

Asphalt Concrete Mix Design Requirements

| Design ESALs, millions | As shown on front Plan Sheet |
| --- | --- |
| Nom. Max Aggr. Size, inch | 3/4 |
| Rut Index, max. | 3 |

Asphalt concrete mixtures shall be composed of aggregate, asphalt cement, and required

additives combined within the limits for the type and class of asphalt concrete specified in the contract.

At least 15 calendar days before the production of this asphalt concrete pavement mixture, the Contractor shall submit the following to the Engineer.

- A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile.  The proposed Job Mix Design gradation must meet the requirements of Table 408-2

- Representative samples from each of the stockpiles replicating the weight proportions of the proposed blend ratios, for a total sample weight of 350 pounds.

- A minimum of five 1-gallon samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, and test results as required in Subsection 702-2.01.  This shall also include a manufacturer’s certificate of compliance in accordance with Subsection 106-1.05, a temperature viscosity curve, specific gravity of the asphalt binder, the recommended mixing temperature, and a Materials Safety Data Sheet (MSDS).

- A sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

From this material, the Engineer will develop the Job Mix Design using procedures in SP-2.  Approved Job Mix Designs will become a part of the contract.  Up to15 working days may be required to determine the Job Mix Design after receipt of items specified above.  Do not produce any asphalt concrete mix for payment until the Job Mix Design is approved.

Approved Job Mix Design become part of the contract and will specify the target values for gradation, the target values for asphalt cement content, and the maximum specific gravity (MSG) of the mix.  Tolerances in Table 408-3 apply for acceptance testing and will not be applied to the largest sieve specified.

Changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation changes from Job Mix, or blend ratio requires a new Job Mix Design.  The Contractor must provide submittals and materials to create a new job mix design.  Approved changes to the mix design may be only initialized after a lot is competed using the previous mix design.

The Contractor will be assessed a mix design fee of $3,600.00 for each mix design subsequent to the first approved Job Mix Design for each Type of Asphalt Concrete specified.

## Table 408-2

Design Aggregate JMF Control Points

| # Sieve Size |  | # Nominal Maximum Sieve Size Percent Passing By Weight |  |  |
| --- | --- | --- | --- | --- |
|  | ## 3/4” |  | ## 1/2” | ## 3/8” |
| 1” | 100 |  |  |  |
| ¾” | 90-100 |  | 100 |  |
| ½” | 65-75 |  | 90-100 | 100 |
| 3/8” | 48-60 |  |  | 90-100 |
| No. 4 | 30-40 |  |  |  |
| No.8 | 20-30 |  | 28-58 | 32-67 |
| No.200 | 3-8 |  | 3-8 | 3-8 |

Boundaries of Aggregate Restricted Zone

| # Sieve Size |  | # Nominal Maximum Sieve Size Percent Passing By Weight |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 3/4” |  |  | 1/2” |  | 3/8” |  |
|  | Min. % |  | Max. % | Min. % | Max. % | Min. % | Max. % |
| No 8 | 34.6 |  | 34.6 | 39.1 | 39.1 | 47.2 | 47.2 |
| No. 16 | 22.3 |  | 28.3 | 25.6 | 31.6 | 31.6 | 37.6 |
| No. 30 | 16.7 |  | 20.7 | 19.1 | 23.1 | 23.5 | 27.5 |
| No. 50 | 13.7 |  | 13.7 | 15.5 | 15.5 | 18.7 | 18.7 |

Note:  The Contractor’s proposed aggregate blend proportions shall fall between the aggregate control points, shown in Table 408-1, and will plot below the lower boundary line of the restricted zone as defined above.

408-2.02 AGGREGATES.  Conform to subsection 703-2.13.  Remove all natural fines passing a #4 (4.75 mm) sieve before crushing aggregates for asphalt concrete mixtures.  Divide the crushed aggregate into a minimum of 3 stockpiles; coarse, intermediate, and fine.  Additional stockpiles may be required for some material sources to create a Design Aggregate Structure that meets the volumetric requirements of the mix design procedures.

408-2.03 ASPHALT MATERIALS.  Conform to Subsection 702-2.01, Use PG 58-28 asphalt cement, no binder adjustment will be made for traffic load rate.  Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 before shipping.  Storage tanks used for the batch shall be noted on the test report.  Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project.  A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket.  The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

1.	Manufacturers certificate of compliance, Subsection 106-1.05

2.	Conformance test results of the batch, Section 702.

3.	Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

408-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM T-14 and included in the approved Job Mix Design.  At least 70 percent of the aggregate shall remain coated when tested in accordance with ATM T-14.  Anti-stripping additive shall be furnished in the minimum amount of 0.25 percent per ton of asphalt cement.

408-2.05 QUALITY CONTROL.  It is expressly understood that the Contractor is solely responsible for the sampling and testing of material for quality control of the asphalt concrete mixture in accordance with Subsection 106-1.03.

Failure to perform quality control forfeits the Contractor's right to retest as provided for in Subsection 408-4.02.

A paving and plant control plan shall be submitted at least 3 working days before the pre-paving meeting.  The paving and plant control plan shall address sequence of operations, joint construction and sealing, outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the asphalt concrete mixture.  The plan shall also include a proposed testing frequency for gradation, asphalt cement content and compaction and shall include temperatures for bituminous mixture and materials.  The pre-paving meeting shall be held on-site with the Project Engineer at least 2 days before paving begins, and shall include the project superintendent, the paving foreman, the asphalt plant operator, and the Contractor's quality control supervisor.

CONSTRUCTION REQUIREMENTS

408-3.01 WEATHER LIMITATIONS.  Do not place the asphalt concrete mixture on a dry non-yielding roadbed, when the frozen base material, or when free water is present on the road surface, or when weather conditions prevent proper handling, or finishing of the mix.  Do not place asphalt concrete mixture unless the road surface temperature is 40 F and rising.

408-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of asphalt concrete mixture buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of asphalt concrete mix.

408-3.03 BITUMINOUS MIXING PLANTS.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the data to the Engineer at least one day before production.  Maintain a current Air Quality Permit issued by the State Of Alaska.

Provide a scalping screen on the asphalt plant to prevent oversize material or debris from being incorporated into the mixture.  Provide aggregate and asphalt cement sampling locations meeting OSHA safety requirements.

Do not use proportioning (batch) scales for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

408-3.04 HAULING EQUIPMENT.  Haul asphalt mixtures in trucks having tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department’s Approved Products List.  Do not use diesel fuel or fuel oil as an asphalt release agent.

Cover the asphalt mixture in the haul vehicle, when required.

408-3.05 ASPHALT PAVERS.  Use self-propelled asphalt pavers having a heated vibratory screed, with grade and cross slope controlled using automatic grade and slope control devices.  Use a paver screed control system that is automatically actuated by the use of an erected string line, mobile string line (ski) on the high side of the paver at least 30 feet in length, or other approved grade follower.  Use grade control on either a) both the high and low sides or b) grade control on the high side and slope control on the low side.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture.  Provide heaters and vibrators on the main screed and screed extensions.  Maintain auger extensions within 1.5 feet of the screed extension on both sides.

408-3.06 ROLLERS.  Use a sufficient number of static, vibratory steel wheel, and pneumatic-tire rollers having adequate weight to compact the mixture to the required density while maintaining the pace of the paving operations.  Use self propelled rollers capable of reversing without backlash, specifically designed to compact hot asphalt concrete mixtures.

Pneumatic-rollers are required and shall be fully skirted, have a minimum operating weight per tire of at least 3,000 pounds, inflated to 90 psi minimum.

408-3.07 PREPARATION OF EXISTING SURFACE.  Prepare the existing surfaces in conformance with the plans and specifications.  Existing paved surfaces shall be cleaned of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

Contact surfaces of curbing, gutters, manholes, sawcut pavement, and other structures shall be coated with a uniform coating of tack coat material conforming to Section 402 before the asphalt concrete mixture being placed.

Asphalt concrete mixture shall not be placed upon a non-cured prime or non-broken tack coat.

408-3.08 PREPARATION OF ASPHALT.  A continuous supply of asphalt cement shall be supplied to the mixer at a uniform temperature, within the allowable mixing temperature range noted in the approved mix design.

408-3.09 PREPARATION OF AGGREGATES.  The aggregate for the asphalt concrete mixture shall be heated and dried to a temperature compatible with the mix requirements specified.

The burner on the dryer shall be properly adjusted to avoid damage to the aggregate and to avoid the presence of unburned fuel on the aggregate.  Any asphalt concrete mixture in which soot or fuel is present is unacceptable in accordance with Subsection 105-1.11.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the asphalt concrete mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5% (by total weight of mix), as determined by WAQTC TM 6.

408-3.10 MIXING.  The aggregate, asphalt cement and additives shall be combined at the plant in the amounts required by the Job Mix Design and contract specifications.

The materials shall be mixed such that a complete and uniform coating of the aggregate is obtained.  For batch plants, dry aggregate shall be in motion before the addition of asphalt cement.  Wet mixing time shall be adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

The temperature of the asphalt concrete mixture at the time of the mixing shall be as determined by the Job Mix Design.

408-3.11 TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE.  Asphalt concrete mixture drawn from silo type storage bins shall conform to the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant.  Signs of visible segregation, heat loss, changes from the Job Mix

Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.  Asphalt concrete mixtures shall not be stored or transported by barges.

408-3.12 PLACING AND SPREADING.  Place the asphalt concrete mixture upon an approved surface, spread, strike off, and compacted to the required compacted thickness.  Use asphalt pavers to distribute the asphalt concrete mixture in lanes from the roadway crown outward and of such widths as to hold to a practical minimum the number of longitudinal joints required.  Use asphalt pavers to distribute asphalt concrete mixture for leveling course unless otherwise allowed.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor’s control, in order to prevent lane edge drop off.  Place approved material against the pavement edge when the outside pavement edge drop off exceeds 2 inches.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted.

Areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impractical, the mixture shall be spread, raked and luted by hand tools.  For such areas, the mixture shall be placed to the required compacted thickness.

When laying asphalt concrete mixtures, the paver shall be operated at uniform forward speeds consistent with the delivery of asphalt concrete mix to avoid unnecessary stopping and starting of the paver.  The Contractor shall continuously pave a single lane within a single work shift to avoid unnecessary starting and stopping of the paver.

Submit a Paving Plan for the Engineer's review a minimum of five working days before initiating paving operations.  The plan shall consist of, but not be limited to the following:

1.	Paving schedule to include sequence of operations.

2.	Operational details to include:

a.	Plant operating capacity and target production rate.  Process quality control testing frequency for gradation, moisture, asphalt cement content, and compaction.

b.	Number and capacity of trucks, cycle time, and delivery rate.

c.	The manufacturer and model of the paver and pickup machine, to include information on grade followers, sensors, operating speed and production rate of the pavers.

d.	Number, type, and weight of rollers, and number of impacts per foot.

e.	Location and method of constructing longitudinal and transverse joints.

- Construction plan for paving intersections and driveways.

- Traffic control plan during paving

- Striping plan

Schedule a pre-paving meeting on the jobsite, a minimum of 3 days before paving.

408-3.13 COMPACTION.  Immediately after spreading, thoroughly and uniformly compact the asphalt concrete mixture by rolling.

The target value for density is 94% of the maximum specific gravity (MSG), as determined by WAQTC FOP for AASHTO T 209.  For the first lot of each type of asphalt concrete pavement, use the MSG determined by the Job Mix Design.  For subsequent lots, use the MSG of the first sublot as a standard for the lot.

Acceptance testing for field density will be determined according to WAQTC FOP for AASHTO T 166 and T 275 from a 6” diameter core of the finished mat.

Use pneumatic-tire rollers to compact asphalt concrete pavements.

Rollers or other vehicles shall not be parked or left standing on any pavement that has not cooled to ambient temperature.

408-3.14 JOINTS.  Minimize the number of joints and construct to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.

The minimum specification for longitudinal joint density will be 91 percent of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the

longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  The Engineer will mark the core location, center the core over this mark on the joint “screed mark”.

Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.  If the average joint density in a lot is less than 91%, the Contractor will immediately change and improve the method used for joint construction.  If the average of all joint densities on the project is less than 91%, the Contractor shall also seal all the joints with an approved joint sealing method, according to manufacturers recommendations, at no expense of money or time to the State prior to paint striping.  If the Contractor elects to cut back a joint, there will be no deduction of pay quantity.

At the beginning and end of a project, when joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw, or ground out with a milling machine.

Apply tack coat of asphalt cement or asphalt emulsion to all cold joints and allow emulsions to break before placing any fresh asphalt concrete mixture against the joint.  Tack just before paving.

Form transverse joints by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Transverse joints shall not be perpendicular to centerline.

Offset longitudinal joints in one layer from those in the layer immediately below by at least 6”.  The joints shall be at centerline or lane lines.  Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset 2” to not more than 6” from the edge of the stripe.

408-3.15 SURFACE TOLERANCE.  The surface will be tested after final rolling at selected locations using a 16-foot straightedge.  The variation of the pavement surface from the testing edge of the straightedge shall not exceed 3/16 inch.  Then the Engineer will measure the surface smoothness of the top lift of the asphalt in all of the driving lanes with an inertial profiler before final acceptance of the project.  Remove and replace, or grind any portion of final pavement surface having smoothness Profile Index (PrI) greater than 15 inches per mile in a 0.1 mile segment.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, within 25 feet of bridge abutments, or within 25 feet of remaining existing pavement, or on roads with curb and gutters.

Smoothness will be measured in the left wheel path of each lane and reported as profilograph results (PrI) filtered with a 0.2 inch blanking band.  Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch per mile.

408-3.16 PATCHING DEFECTIVE AREAS.  Any asphalt concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective as determined by the Engineer shall be removed.  Patches shall be full-depth of the pavement thickness.  Defective materials shall be removed for the full thickness of the course.  The pavement shall be cut so that all edges are vertical, the longitudinal sides are parallel to the direction of traffic, and the tranverse ends are skewed at an angle to centerline.  Edges shall be coated with a tack coat of material conforming to Section 402 and allowed to break.  Fresh asphalt concrete mixture shall be placed, and compacted in accordance with Subsection 408-3.13 so that the finished surface will conform to grade and smoothness requirements.

408-4.01 METHOD OF MEASUREMENT.

ASPHALT CONCRETE.  The asphalt concrete mixture will be measured by the ton or by the square yard in accordance with Section 109.  The tons used will be the weight used in the accepted pavement and no deduction will be made for the weight of asphalt cement material and anti-stripping additive in the mixture.  A price adjustment, when applicable, will be made based on a quality level analysis under Subsection 408-4.03.

ASPHALT CEMENT.  The method of measurement to be used for asphalt cement will be the weight of asphalt cement calculated using the percent of asphalt cement for each sublot multiplied by the total tonnage represented by that lot.  WAQTC TM 4 will be used to determine percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.

No payment will be made for any asphalt cement that is more than 0.4% above the optimum asphalt content specified in the Job Mix Design.

LONGITUDINAL JOINTS.  Longitudinal joints on the top pavement surface will be measured by the foot.

408-4.02 ACCEPTANCE SAMPLING AND TESTING.  The quantity of each type of asphalt concrete mixture produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 ton.  The lot will be divided into sublots of 500 ton, each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 4,999 tons, the contract quantity will be considered one lot.  The lot will be divided into 10 equal sublots and randomly sampled for asphalt cement content, density and gradation in accordance with this subsection except that retests will not be allowed.  The lot will be evaluated for price adjustment in accordance with subsection 408-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 1,500 ton, asphalt concrete pavement will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the asphalt concrete pavement to the specified depth and finished surface requirements and tolerances.

Any area of finished surfacing that is visibly segregated, fails to meet surface tolerance, or density requirements, or is in any other way defective, shall be removed and replaced with new asphalt concrete pavement as per Subsection 105-1.11.  Removal and replacement of defective pavement shall be at no additional cost to the Department.

The Engineer will sample the mix for the determination of asphalt cement content and aggregate gradation from either behind the screed before initial compaction, or at the end of the auger, or from the windrow in front of the paver.  The sample location will be selected by the Contractor and documented at the pre-paving meeting.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested

Asphalt cement content will be determined from asphalt concrete mixture samples in accordance with WAQTC TM 4.  Aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

Cut 6” diameter full-depth core samples from the finished mat for density acceptance testing within 12 hours of final rolling for each sublot.  The Engineer will randomly select core locations and use WAQTC FOP for AASHTO T 166/T 275 to determine density.  Cut no samples from asphalt concrete mats on bridge decks.  All voids left by sampling shall be backfilled with new asphalt concrete mixture and compacted within 24 hours of sampling.

Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount for each will be subtracted under Item 408(3), Asphalt Price Adjustment.

A retest of any sample outside the limits specified may be requested.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  Verbal requests with the written request to be delivered after the specified 7 days will not be accepted.  The sample for density retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest.  The Engineer will mark the sample location for the retest. Failure to provide the sample for retesting within the specified period forfeits the right for a retest for the affected sample.  The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample will be allowed.

408-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  The following method of price adjustment will be applied to each type of Asphalt Concrete Pavement, for which the contract quantity equals or exceeds 5,000 ton, except as defined in Subsection 408-4.02.  The longitudinal joint density price adjustment will apply when Asphalt Concrete quantities are equal to or greater than 1,500 tons.

Before computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results shall not be included in the price adjustment calculations.  If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment.  The density test result for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s).  Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0 percent and a contractor's risk of 5.0 percent unless otherwise specified.  AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100 percent pay.  The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained.  The maximum pay factor obtainable is 1.05.  The maximum pay factor for the largest sieve size specification for gradation shall be 1.00.  The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for Stone Mastic Asphalt Concrete mixture, which includes gradation and asphalt cement content.  The second factor is a separate pay factor for density.

A lot containing non-specification material (less than 1.00 pay factor) may be accepted at an adjusted price provided the pay factor is at least 0.75 and the Engineer does not identify isolated defects.  A lot containing non-specification material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11.

The Engineer can reject material, which appears to be defective based on visual inspection.  Such rejected material shall not be used in the work.  No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis.  Procedures for computation of composite pay factors are as follows:

1.	Eliminate test results found to be outliers by SP-7 (Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ  =  summation of

x=Σxn

x  =  individual test value to xn

n  =  total number of test values

x is rounded to the nearest tenth for density and all sieve sizes except the 0.075 mm sieve.  x is rounded to the nearest hundredth for asphalt content and the 0.075 mm sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)  =  summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2  =  square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest 0.01 for density and all sieve sizes except the #200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt content and the #200 sieve.

If the computed sample standard deviation (s) is less than 0.001, then use s = 0.20 for density and all sieve sizes except the #200 sieve.  Use s = 0.020 for the #200 sieve and asphalt cement content.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL). For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 408-4.  The tolerances for the largest sieve specified will be plus 0% and minus 1%.  The TV is the specification value defined by the Job Mix Design.  The TV for density is 94 percent of the maximum specific gravity (MSG).  The LSL for density is 92 percent of MSG and the USL is 97%.

4.	Compute the upper quality index (QU):

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

Where:	LSL = Lower Specification Limit

QL=x-LSLs

QL is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit which corresponds to a given QU) from Table 106-1.  For negative values of QU, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

7.	Determine PL (percent within the lower specification limit which corresponds to a given QL) from Table 106-1.  For negative values of QL, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

8.	Determine the Quality Level (QL), the total percent within specification limits, for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from step 8, determine the lot Pay Factor for Density (DPF), and gradation and asphalt cement content pay factors (PF) from Table 106-2.

10.	Calculate the lot Asphalt Concrete mixture Composite Pay Factor (CPF) for asphalt cement content and gradation using the following formula:

Round the Composite Pay Factor (CPF) to the nearest hundredth.

CPF=[f19mm(PF19mm)+f12.5mm(PF12.5mm)+.......fac(PFac)]Σf

Table 408-5 is used to determine the weight factor (f) for each sieve size and asphalt cement content.

Table 408-4

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 1 Inch Sieve | TV-6.0% | TV+6.0% |
| ¾ Inch Sieve | TV-6.0% | TV+6.0% |
| ½ Inch Sieve | TV-6.0% | TV+6.0% |
| 3/8 Inch Sieve | TV-6.0% | TV+6.0% |
| No. 4 Sieve | TV-6.0% | TV+6.0% |
| No. 8 Sieve | TV-6.0% | TV+6.0% |
| No. 16 Sieve | TV-5.0% | TV+5.0% |
| No. 30 Sieve | TV-4.0% | TV+4.0% |
| No. 50 Sieve | TV-4.0% | TV+4.0% |
| No. 100 Sieve | TV-3.0% | TV+3.0% |
| No. 200 Sieve | TV-2.0% | TV+2.0% |
| Asphalt % | TV-0.40% | TV+0.40% |
| Density | 92% | 97% |

Table 408-5

WEIGHT FACTORS

| Gradation | Factor “f” |
| --- | --- |
| 1 Inch | 0 |
| ¾ Inch | 5 |
| ½ Inch | 10 |
| 3/8 Inch | 5 |
| No. 4 | 5 |
| No. 8 | 10 |
| No. 16 |  |
| No. 30 | 5 |
| No. 50 |  |
| No. 100 |  |
| No. 200 | 20 |
| Asphalt % | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* –1.00] x (Ton in lot) x (PAB)

* CPF or DPF, whichever is lower

PAB = Price Adjustment Base = $45/Ton

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot and will be algebraically added to the Contractor’s payment for Asphalt Concrete under Item 408(3) Price Adjustment.

408-5.01 BASIS OF PAYMENT.  The accepted quantity will be paid for at the adjusted contract unit price for the pay item listed below, complete in place.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot, and for fees accrued for failure to cut cores and/or backfill voids left by sampling in the allotted time as outlined in Subsection 408-4.02.

A separate price adjustment for longitudinal joint density based on the average of the joint densities taken on the project will be applied under Item 408(3), Asphalt Price Adjustment.  Calculate the average of the joint densities taken on the project and determine the incentive / disincentive as follows:

- If the average joint density is greater than 91%,  the Contractor will be paid an incentive calculated as follows:

Incentive = ($0.25 per lineal foot per 1% of density difference)x(lineal feet of paved joint for the entire project)x(project average joint density % - 91%).

- If the average joint density is less than 91%, the Contractor shall repair the asphalt joints on the project at his expense with an approved asphalt joint sealing method as per Subsection 408-3.14; and have a disincentive calculated as follows applied:

Disincentive = ($1.00 per lineal foot per 1% of density difference)x(lineal feet of paved joint for the entire project)x( project average joint density % - 91%).

Asphalt cement, anti-stripping additives, and tack coat will be subsidiary to the asphalt concrete pavement unless specified as pay items.

Additional Job Mix Design evaluations by the Department, as outlined in Subsection 408-2.01, will be subtracted from the Contractor’s payment.

A separate price adjustment for pavement smoothness will be calculated and applied in a separate asphalt Smoothness Price Adjustment as measured in accordance with subsection 408-3.15.

Calculate the smoothness price adjustment as follows;

Smoothness Price Adjustment ($) = SA x PAB x PQ

If PQ is less than 1500 tons, 	SA = 0

If PQ is 1500 to 5000 tons,   	SA = 0.1333 - 0.01666 (PrI)

If PQ is 5000+ tons,		SA = 0. 0666 – 0.0083 (PrI)

SA = Smoothness Adjustment factor

PrI = Profile Index, measured pavement smoothness (inches/mile)

PAB = Price Adjustment Base in 408-4.03

PQ = final pay quantity of 408(1) in tons

Apply smoothness price adjustment as an incentive/disincentive under Item 408(3), Asphalt Price Adjustment

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

## 408(1) 	Asphalt Concrete, Type V	Ton

## 408(2) 	Asphalt Cement, PG 58-28 	Ton

## 408(3) 	Asphalt Price Adjustment 	Contingent Sum

## SECTION 505

## PILING

Special Provisions

505-3.03 PILE Bearing Values.  Delete the first paragraph of this section and substitute the following: Drive piles, except piles for lighting standards, to the required ultimate bearing capacity.  For lighting standards, install piles of sufficient length to cut the pile at the required cut-off elevation and to provide the minimum installed length shown on the plans.

505-3.09 Driving Piles.  Add the following: In many cases, pre-boring, spuding, a larger pile-driving hammer, and excavating inside the pile may be required, in addition to normal pile driving techniques.  Sites for the lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

Submit a pile-driving plan to the Engineer, for approval, at least 14 calendar days before driving the first steel pipe pile.  At a minimum, the pile-driving plan shall consist of the

a.) pile driving hammer, or hammers, to be used,

b.) alternate techniques planned for pile installation, and

c.) equipment used for the pile driving operation.

When the minimum installed length shown on the contract plans can not be achieved, install the pile tip to an elevation established by the Engineer.

505-4.01 Method of Measurement.

Add the following to numbered paragraph 2:

Do not measure piles for lighting standards for payment.  Include costs of furnishing and installing piles in Item 660(3), Highway Lighting System Complete.

(03/12/02)R65M98

SECTION 508

WATERPROOFING MEMBRANE

Special Provisions

CONSTRUCTION REQUIREMENTS

508-3.01 APPLICATION OF MEMBRANE WATERPROOFING.  Replace 2 and 4 with the following:

2.	Preparation of Concrete Deck: Before applying membrane:

a.	Mill existing Asphalt Concrete off down to a bare deck.  It is not necessary to have the deck surface 100% free of Asphalt Concrete.

b.	Power sweep the deck to remove foreign materials such as dirt, dust, moisture, and loose concrete.

4.	Overlaying and Protection of Membrane.  When overlaying membrane, observe the following requirements:

- Apply tack coat.

b.	Place 1 inch thick leveling course of Asphalt Concrete Type IV, Class B over deck.

c.	Place the membrane according to manufacturer’s recommendations and according to item 3 of this subsection.

d.	Do not place the asphalt overlay until the membrane has cured enough to prevent damage from the overlaying operation.

e.	Place, spread, and roll the asphalt so that the membrane will not be damaged.

1)		If traffic is not to be allowed on the Asphalt Concrete over the membrane, place 1 inch of Asphalt Concrete, Type IV, Class B.

2)	If traffic is to be allowed on the Asphalt Concrete over the membrane, place a 1 ½ inch thick layer of Asphalt Concrete, Type IV, Class B.

f.		Do not operate vehicles except the asphalt paver and trucks used for hauling the asphalt overlay mix, on the membrane.

g.	Use only rubber tired or rubber-tracked paving machines over the membrane.

h.		Use only steel-wheeled rollers to compact the asphalt paving on the bridge decks.

i.	Do not use vibratory rollers with vibrator turned on.

j.	Apply tack coat.

k.	Place 2 or 1 ½ inches of final Stone Mastic Asphalt Concrete wearing surface for a total Asphalt Concrete thickness of 4 inches.

508-4.01 METHOD OF MEASUREMENT.  Add the following:

Each – The number of units as defined on the Plans.

508-5.01 BASIS OF PAYMENT.  Replace the last sentence with the following: Asphalt Concrete Pavement, Type IV, Class B, and required tack placed over the Waterproofing Membrane over the bridges shall be subsidiary to the Item 508(2) Waterproofing Membrane.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

508(2)	Waterproofing Membrane	Each

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-1.01 DESCRIPTION.  Add the following: This work consists of inspecting and cleaning the existing storm drain system.

604-3.01 CONSTRUCTION REQUIREMENTS.  Delete the sixteenth paragraph and substitute the following:  In roadways, set the manhole frame and cover to 3/8 inch plus or

## minus 1/8 inch below the finished pavement surface.  In walkways and bike paths, set the manhole frame flush with the surface.

Within 30 days of beginning other construction activities, the Contractor shall inspect and clean storm drain manholes, inlets, catch basins, sumps, mainlines, laterals and culverts.

Probe the manholes with a calibrated bar.  If 50% or more of the manhole sump is filled with the debris, remove the debris. Remove debris from catch basins and inlets regardless of the quantity of debris.  No more than 5%-10% of debris should remain.  Remove debris (sticks, plastic bags) blocking culvert inlets and outlets.  Record the date of inspection, the depth of sediments, and whether the manhole was cleaned or not in a grid map book provided by the Engineer.

The Contractor shall provide equipment that is capable of cleaning storm drains.  The equipment shall be inspected and accepted by the Engineer before use on this project.  The Contractor shall provide traffic control while cleaning storm drains.

The work shall include disposal of silt, trash, debris and other material removed from the system. This material may be disposed at the Municipality of Anchorage Hazardous Materials Waste Disposal site.

## 604-4.01 METHOD OF MEASUREMENT.  Add the following: Item 604(20) Clean Drainage System, will be measured in the manner specified in the directive authorizing the work.

604-5.01 BASIS OF PAYMENT.  Add the following:  604(20) Clean Drainage System, will be made on a time and materials basis in accordance with subsection 109-1.05, Compensation for Extra Work.  Traffic Control provided to clean storm drains will be paid under the 643 items.

Pay Item No.	Pay Item	Pay Unit

604(20)	Clean Drainage System	Contingent Sum

## SECTION 608

SIDEWALKS

Special Provisions

608-3.03 CURB RAMPS.  Replace the first sentence with the following:  Remove existing curb ramps and construct curb ramps according to the details and locations shown on the Plans.  Install composite detectable warning tiles such as Armor Tile Cast-In-Place In-Line Tactile Panels, manufactured by Engineered Plastics, Inc., or approved tactile warning bumps as shown in the details on the plans.

608-4.01 METHOD OF MEASUREMENT.  Replace Curb Ramp with the following:

Curb Ramp.  By each installation, complete in place, including removal of the existing curb ramp, construction of the ramp runs, flares, and landings necessary to provide a single street-level access.

608-5.01 BASIS OF PAYMENT.  Add the following: Concrete and tactile warning bumps used in the construction of curb ramps is subsidiary to item 608(6) Curb Ramp.

SECTION 615

## STANDARD SIGNS

Special Provisions

615-3.02 SIGN PLACEMENT AND INSTALLATION.  Add the following: Do not remove existing signs without authorization from the Engineer.

# SECTION 618

# SEEDING

# Special Provisions

618-1.01 DESCRIPTION.  Add the following: Topsoil and seed new or disturbed slopes and any other areas directed by the Engineer.  Track the soil and apply seed, mulch, fertilizer and water.  Provide a living ground cover on slopes as soon as possible.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes.  Cover slopes to be seeded with topsoil in accordance with Section 620.  Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete slope preparation as soon as topsoil is placed on the slopes.  Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  Seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION.  Add the following: Apply seed, mulch and fertilizer as follows per acre.  Apply seed and mulch in one application if using the hydraulic method.  Apply fertilizer with the hydraulic method.

| Seed Mix | Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- | --- |
| Type A | Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
|  | Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

618-4.01 METHOD OF MEASUREMENT.  Add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT.  The work described under subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(11/06/02)R52USC

SECTION 620

TOPSOIL

# Special Provisions

620-2.01 MATERIALS.  Add the following: Provide topsoil of the class specified on the Plans.

620-4.01 METHOD OF MEASUREMENT.  Add the following: Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.  (11/06/02)R53USC02

# SECTION 641

## EROSION, SEDIMENT, AND POLLUTION CONTROL

Special Provisions

641-1.02 DEFINITIONS.  Delete items No. 5, 6, and 7.

Replace item 8.  with the following:

- SWPPP (Storm Water Pollution Prevention Plan).  The Contractor’s plan for erosion and sediment control and storm water management.  The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project.  The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS.  Replace the first sentence in the second paragraph with the following: The Department will review the above submittals within 14 working days.

Delete the third and forth paragraph.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  Replace the second sentence with the following:  Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing 5 acres or less.

Delete the last paragraph.

641-3.01 CONSTRUCTION REQUIREMENTS.  Replace the first sentence with the following: Do not begin ground-disturbing work until the Contractor receives written approval of the SWPPP and HMCP.

Delete item 1.

Replace the 3rd paragraph with the following: Implement temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

###### Delete paragraph 6, items 1 through 3, and paragraph 7.

Delete the 12 paragraph and items 1 and 2.

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-3.03 MONUMENTS.  Replace the second sentence in the first paragraph with the following:  Reference property markers/corners, monuments, or accessories that may be disturbed or buried during construction, prepare and submit Monuments Record Forms before monument are disturbed and reestablish monuments in their original position before the completion of the project.

Replace the fourth paragraph with the following: The surveyor must complete and stamp a State of Alaska Land Survey Monument Record form for each Primary and secondary monument removed, installed, relocated, or replaced.  Record the required survey information, including section, township, and range.  Meet requirements for recording at the District Recorder’s Office in which the project is located for each record.  Deliver these forms to the Engineer before monument removal or disturbance and after resetting of disturbed monuments before project completion.  The Department will file original records as requires by current State Statutes using the information the Contractor provides.

642-5.01 BASIS OF PAYMENT.  Replace the last sentence of the first paragraph with the following: Payment for referencing is based on the Engineers acceptance of the Surveyors Monument Record Form.

## SECTION 643

## TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  Movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 foot lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations. (11/18/02)R222USC02

643-2.01 MATERIALS.  Add the following:

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.

(11/18/02)R222USC02

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity. (11/18/02)R222USC02

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following:  Pave lanes next to the median lanes first.  Pave lanes next to exit and entrance ramps last.  On lanes next to exit and entrance ramps place a temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge at entrance and exit ramps.  The roadway shall not be opened to traffic until slope wedge is in place.

643-3.04 TRAFFIC CONTROL DEVICES.  Add the following to 1. Embankments.: Close trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

- Power Brooming.  The Contractor shall use a power broom capable of ejecting loose material to the shoulder of the road.  The Contractor shall remove loose material from paved portions of the roadway and haul routes open to the public.  This includes sections of roadway off the project where the Contractor’s operations have deposited loose material.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT &PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic between 0600 hours to 2100 hours

The Contractor shall perform his operation so that the traveling public experiences no more than a 2 minute stopped delay, 40 vehicles, 2500 feet of traffic is detained, whichever occurs first, before releasing the detained motorists.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

The Contractor will be permitted to allow traffic to run on a milled surface only up to seven days.  At the end of a continuous work shift both lanes of traffic in the same direction shall be milled and striped.  No pavement lips along the centerline will be left after the work shift has ended.

The Contractor shall obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted as a TCP to the Engineer for approval before implementation of the school bus coordination plan.

To establish a smooth driving surface through the intersections, pave the entire length of the segment in a continuous operation.

Road closures and traffic control plans are subject to approval by the Department.  The following projects may be under construction concurrently with this project:

1.	Dowling Road, Old Seward Highway to Lake Otis Pkwy.  NH-0532 (4) / 59599.

2.	New Seward Hwy.  at Dimond Interchange Capacity Improvements; IM-000S (290) / 53569.

3.	Central Region Hwy.  Data Equipment, 02; MGS-000S (405) / 55585.

4.	High Tower Illumination Mast Replacement project will under construction concurrently with this project.  The contractor may coordinate with the High Tower Illumination Mast Replacement project for the use of frontage roads for detour routes.  In the event of conflicts the High Tower Illumination Replacement project shall have first right of the use of the detour routes.

Final approval of Traffic Control Plans may be affected by the construction activities on these projects.

643-3.09 INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Add the following Subsection:

643-3.10 PUBLIC INFORMATIONAL PROGRAM.  Provide a Public Information (PI) professional to accomplish the work outlined in this Subsection.  The PI person shall have a minimum of five (5) years demonstrated professional experience in performing similar informational campaigns involving multi-media, i.e.: television, radio, newspaper and public presentations.  S/he shall be responsible for all aspects of this service including coordination; public interaction; preparing graphics; developing mailing lists; supplying updated information; and labor, equipment, postage, and materials to provide this service.  Logos, reports, software, visual aids, graphics and work products developed for this Project shall become the property of the Department, and delivered to the Engineer at the end of the work.  The PI professional's office shall be equipped with a facsimile machine.

This professional shall be responsible for the following tasks for the PI Program:

A.	Mail-outs.  Design and distribute three informational mail-outs/flyers each construction season, which will be approved by the Engineer.  The mail-outs shall contain most or all of the following:

1.	a brief description and map of the Project,

2.	the Contractor's anticipated construction schedule,

3.	a narrative of the possible delays to the traveling public through the Project,

4.	detailed traffic information such as intersection, lane and/or sidewalk closures, their corresponding detours, and their effective dates,

5.	locations of temporary bus stops,

6.	a description of possible impacts to abutting property accessing the Project,

7.	a listing of locations where current Project information may be obtained,

8.	date and times of Open House meeting as required by the Engineer,

9.	the Contractor's 24-hour message number and office telephone number, and

10.	the Engineer's Project office telephone number, e-mail address, and the

web site address containing Project updates, schedules and general narrative information.

The last mail-out shall also contain a questionnaire to aid in preparing the final Report required under Item E below.

The mail-outs shall be sent to addresses within one city block on either side of the Project corridor, and shall be addressed to both the owner of record and the current tenant.  It shall be distributed at the following times:

a.	two weeks before construction begins,

b.	at the approximate one-third point of construction season, and

c.	at the approximate two-thirds point of construction season.

B.	Weekly Notices.  Write and submit weekly Public Information Notices that identify road closures, restrictions to traffic, and detours.  Areas of potential traffic delay shall be emphasized and alternative routes noted.  Coordinate this effort with the Engineer and the Department's NAVIGATOR Informational Program.  Telephone numbers for further information, and the date and time for the next scheduled public open house meeting shall be provided.  The Engineer will approve the Notices.  Hand carry or fax the Notices to the local news broadcasting media, emergency services, public service organizations and the major retailers near the Project corridor.

Notices shall also be distributed to the following local officials and transportation organizations, including but not necessarily limited to:

Alaska Carriers Association

Alaska Trucking Association

Alaska State Troopers

Anchorage Police Department

Anchorage Fire Department

Anchorage School District

People Mover Transit Authorities

Local Emergency Medical Services

US Postal Service

The Notices shall be submitted at the following times:

1.	one week before the beginning of construction,

2.	on Wednesday of each week during construction, and

3.	before any major change or disruption to traffic or local access.

Additionally, the PI professional shall notify business and residents that front the Project or scheduled road closures or of driveway, curb or sidewalk reconstruction, or any other work affecting them.  Property owners with the work segment shall receive the Notices a minimum of one week before the commencement of the work within their segment.  Lastly, provide daily information to those media who do non-paid public service road reports or announcements, and/or "Eye-in-the-Sky" commuter road reporting.

C.	Public Open House Meetings.  Prepare presentations for the Engineer's Open House Meetings, and for of each of the Community Councils that represent areas affected this Project.  The Community Council meetings attended shall be the last regularly scheduled meetings before the beginning of construction.  Presentation size graphics shall be used to help explain the Project to the general public.

The PI professional shall be the Contractor's representative and spokesman, able to speak for him.  The PI professional shall be available to attend additional public meetings, up to five, as requested by the Engineer.

D.	Other Agency Coordination.  Coordinate with the Anchorage People Mover Transit Department (343-8294) to take advantage of programs which will help decrease traffic through this Project, such as Park-and-Ride with express bus service, Ride Share, and the car pooling program.  Also coordinate any major

detours and closures with emergency service providers (police, fire, and ambulance), Anchorage School District bus operators, postal service, and the People Mover.

E.	Final Report.  Before Project completion, submit a Report evaluating the Public Informational Program as detailed under this Subsection.  The Report shall include an outline of the program, an analysis of the program's effectiveness, and suggestions on how to improve the program's effectiveness, economy, and usefulness on future projects.

F.	Project Progress Meetings.  Attend scheduled or special Project meetings between the Contractor and the Engineer at the field office.

G.	Web Page.  Generate an INTERNET web site for the Project containing Project updates, schedules and general narrative information.  Add links to the Department's NAVIGATOR Home Page (www.dot.state.ak.us/navigator.html).  Update the site weekly.

643-4.01 METHOD OF MEASUREMENT.  Page 281, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

Providing mail-outs, notices, displays for open house and public meetings, and providing weekly notices with updates will not be measured for payment.

643(33) Public Informational Program includes work under this item, including but not limited to providing the mailouts, notices, displays for open house and public meetings, and providing weekly notices with updates will not be measured for payment.

643-5.01 BASIS OF PAYMENT.  Add the following: The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour.  The Engineer does not require a change order/directive for the flagging pay item.  (11/18/02)R222USC02

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | 1000 Gallon | $20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Feet | $2.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Foot Foot Foot Each | $0.30 $0.65 $0.75 $40.00 |

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

643(33)	Public Informational Program	Lump Sum

#### SECTION 644

#### SERVICES TO BE FURNISHED BY THE CONTRACTOR

#### Special Provisions

644-2.01 FIELD OFFICE. Delete the third, fifth, and seventh sentences of the first paragraph and the second paragraph in this subsection and substitute the following: Meet the following office requirements:

1.	A minimum of 1,000 square feet of floor area. Divide the office area so that it contains an office room separated by a closable door. The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	A minimum of two electrical outlets.

4.	Adequate parking for a minimum of 10 vehicles, with one disability parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

5.	Provide attached indoor plumbing with sanitary lavatory facilities and potable drinking water.

6.	Three telephone lines available at the project location.

7.	Located in within 3 miles of the project.

8.	Provide one move in and one move out for state office furniture and equipment.

#### Special Provisions

644-4.01 BASIS OF PAYMENT. Add the following: The Engineer will not pay for electricity, propane and water supplied for the State provided portable asphalt lab separately.  Those items are subsidiary to Item 644(1) Field Office.

Add the following Section:

SECTION 645

## TRAINING PROGRAM

Special Provision

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts before the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "yellow pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Before award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith that substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved before contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the Contractor’s judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts.  In the event the Contractor subcontracts a portion of the work, the Contractor shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor according to subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed based on hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section before the Contractor’s submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the Contractor’s discretion, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibits the Contractor the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of training programs approved for the project.  No payment or partial payment will be made to the Contractor if the Contractor fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why the Contractor was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.  (10/29/91)S 16

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1) 	Training Program, __ Trainees/Apprentices 	Labor Hour

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE Delete this subsection in its entirety and replace with the following: Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  If revisions are required, make them promptly.  The finalized CPM Schedule must be completed and accepted before commencement of any work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete item 2.   60-Day Preliminary Schedule.  (3/12/01)R261M98

Delete the first sentence of item 3. Schedule Updates.  and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly, or as deemed necessary by the Engineer.

(12/13/02)R261M98

# SECTION 660

## SIGNALS AND LIGHTING

Special Provisions

660-2.01 MATERIALS.  1. Equipment List(s) and Drawings.  Delete item a that follows the first paragraph and add the following: The Approved Products List does not apply to the 660 items.  Provide catalog cuts of materials to the Engineer for review and approval.

2. As-Built Plans.  Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-3.01 GENERAL.  6. Salvaging or Reusing Electrical Equipment.  Add the following: Deliver junction box lids undamaged to the Municipality of Anchorage Signal Maintenance shop at 3650 E. Tudor Road, Building C in Anchorage, Alaska.  Notify Mike Sickler or William Sosnowski at 343-8355 one-week before the planned delivery date.  Dispose of other materials removed from the project.

660-3.02 FOUNDATIONS.  1.  Cast-in-Place Foundations.  In subparagraph f, revise the second sentence to read: Before placing the form or reinforcing steel cage, remove loose material to ensure the foundation rests on firm, undisturbed ground.

In the second sentence of subparagraph i, delete “prior to grouting” and add, ”before attaching the galvanized skirt.”

In the first sentence of subparagraphs j and k, delete “concrete pile caps” and add, ”foundations.”

Add the following new subparagraph l.  Attach a 4 AWG, bare, solid copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector or cadweld to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled 4 AWG, bare, solid copper wire as the grounding electrode.  Route the conductor to protrude near the top, center of the foundations.  Slide a minimum 6-inch long, non-metallic, protective sleeve over the conductor.  Allow one inch of the sleeve and two feet of conductor to protrude from the foundations.

2. Pile Foundations.  Add the following new subparagraph g.  Use no more than one splice per foundation.  Locate the splice at least seven feet from the top of pile.

660-3.03 CONDUIT.  Revise subparagraph 6, to read: Install rigid metal conduit under existing pavements that will not be overlaid by jacking them under pavements up to 30 feet wide and under existing pavements greater than 30 feet wide by boring or drilling methods.

In subparagraph 8, delete “non-metallic”

Delete subparagraph 9, and add the following:

9.	Position conduit ends in junction boxes to provide clearances of at least 2-1/2 inches around all 2-inch conduits and at least 2-inches around all conduits larger than two inch.

Add the following to subparagraph 11, Provide enough clearance between conduits, including protective sleeves, to ensure installation of grounding bushings on conduits.

660-3.05 WIRING. Delete subparagraph 11 and add the following: Encapsulate illumination cable splices in rigid 2-piece plastic molds filled with an insulating and sealing epoxy resin.  Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin.  Furnish molds rated for 600 volts AC operation and feature fill and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and which will not sustain combustion.

Delete subparagraph 12 and renumber the paragraph that follows subparagraph 11 to 12.  Also revise the first sentence of new subparagraph 12 to read: Encapsulate all loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with re-enterable polyurethane electrical insulating and sealing compound.

Add the following new subparagraph: 18.  Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

Add the following new subparagraph: 19.  Whenever the conductors can not be terminated as conductors specified in the Plans in circuit breakers due to their size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet.  Limit the length of the #8 AWG conductor to 5 feet.

660-3.06 BONDING AND GROUNDING.  Delete this subsection and add the following: Bond and ground branch circuits according to the NEC and the following requirements.  Make non-current carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor.  Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.  Where an authority having jurisdiction requires grounding conductors in metal poles, install a 10 AWG power conductor with green insulation and terminate it on the grounding lug in the luminaire.

Install threaded-type grounding bushings made of malleable iron or steel with a zinc or galvanized finish on the ends of metallic conduits.  Use bushings with an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size 8 AWG conductors, except in those conduits that contain circuit conductors larger than 8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installing or removing conductors from existing conduits, retrofit them with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross-sectional area equal to an 8 AWG conductor.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.  Replace missing or damaged conduit and junction box lid bonding jumpers.

At Portland cement concrete foundations, join the equipment grounding conductors from the conduits to the 4 AWG grounding electrode conductor using irreversible compression connectors.  With pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a four feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the hand hole of each pole.

Bond slip-base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the hand hole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a ¾ inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

660-3.08 SIGNAL AND LIGHTING STRUCTURES.  4. Signal Head Mounting.  Add the following:  When side-mounting the 5-section vertically stacked signal heads on poles, install a steel conduit hanger six inches below the upper horizontal framework pipe and secure the vertical framework pipe to the pole.

660-3.09 MAINTAINING TEMPORARY AND EXISTING ELECTRICAL SYSTEMS.  Delete this subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract.  The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If the Contractor fails to maintain the electrical systems as specified herein, the Engineer will adjust payments to the Contractor according to subsection 643-3.06, Traffic Price Adjustment.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities.  Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When the Contractor begins work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility.  Therefore, before starting work on the project, the Contractor should inventory the condition of the existing equipment and document damaged and defective equipment, which the Engineer will inspect with the Contractor.  If the Contractor begins work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems.  The State will pay for electricity used to operate the systems, if the public benefits from their operation.  Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer.  If the Contractor does not complete the work, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due the Contractor.

When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times the Contractor began and completed work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the original circuit is retired.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever the clearance from the traveled way is reduced to less than six feet.

During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches in accordance with the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 17.5 feet to 21.5 feet of clearance between the traveled way and the bottom of each signal.  For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain nine feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

- When the horizontal angle to the side mounted far right signal exceeds 20o, relocate this signal to an overhead location.  Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

  - With two or more through lanes, center one signal head over each lane.

  - With one through lane and protected-permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

  - Otherwise, install the relocated signal eight feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain seven feet to nine feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in subsection 660-3.08, Signal and Lighting Structures.

When no longer required, salvage original and Department provided equipment according to the plans and item 6 Salvaging or Reusing Electrical Equipment found in subsection 660-3.01, and remove other materials used in the temporary systems from the project.

660-3.11 SIGNAL SYSTEM TIMING AND ADJUSTMENTS.  Add the following subsection: The Engineer will use Municipality of Anchorage (MOA) signal maintenance personnel for certain work inside controller cabinets.  Before MOA personnel arrive to terminate conductors, the Contractor shall attach terminal connectors to conductor ends and labeled paired loop detector conductors and cables as specified in Subsection 660-3.05, Wiring.  On projects outside the MOA, send controller equipment to the MOA for testing and complete work specified inside controller cabinets.

Controller Cabinet Preparation.  Ship the traffic controller cabinet(s) and equipment to the Municipality of Anchorage Traffic Signal Electronics Shop at 3650 E. Tudor Road, Building C.  They will inspect cabinet wiring, burn in signal equipment, customize cabinets for desired operation, and test the equipment according to Subsection 660-3.07, Shop Tests.

- Loop Detector Wiring.  Municipality of Anchorage Traffic Signal Maintenance (MOA Signal Maintenance) will test and connect paired loop detector conductors to the terminal blocks.

- Control Cable Wiring.  When the Contractor modifies an operational signal system or controller assembly, MOA Signal Maintenance will connect control cables within the controller cabinet to the terminal blocks.

- Timing Adjustments.  During construction, MOA Signal Maintenance may adjust the system and intersection operational timing to accommodate project conditions.

- Interconnect Wiring.  MOA Signal Maintenance will test and connect interconnect wiring to the terminal blocks.

660-5.01 BASIS OF PAYMENT.  Add the following: The Engineer will pay Item 660(26), Signal System Timing and Adjustments, based on paid receipts plus 15 percent for authorized work performed by the Municipality of Anchorage.  A directive will not be required to initiate payment for work performed under Item 660(26).  Pay costs of the Municipality re-testing equipment that fails to comply with the Plans and Specifications.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

660(17)	Traffic Signal Modifications	Lump Sum

660(26)	Signal System Timing and Adjustments	Contingent Sum

SECTION 670

## TRAFFIC MARKINGS

## Special Provisions

670-1.01 DESCRIPTION.  Delete the first sentence and substitute the following: This work shall consist of placing Methyl Methacrylate Pavement Markings and Durable Pavement Markings as indicated on the Plans.

Durable pavement markings consist of either preformed marking tape or Methyl Methacrylate pavement markings at the Contractor’s option.  Once selected, only one durable pavement marking type shall be used throughout that section indicated on the Plans.

670-3.01 CONSTRUCTION REQUIREMENTS.  Under item 4 Methyl Methacrylate Pavement Markings, add the following:

- General.  Add the following:

(1)	The manufacturer’s representative shall have no affiliation with the Contractor.

(2) 	Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method of application.  Submit these certifications 15 days before beginning work.

(3)	 Install pavement markings using equipment certified by the marking material manufacturer that is designed and capable of properly mixing at the point and time of application.  Submit these certifications 15 days before beginning work

(4)	Waste material becomes the property of the Contractor.  This includes grindings and removed marking material.  Do not dispose of or store stripe removal wastes material or asphalt grindings on State property.  Dispose of waste material according to applicable State, Federal and local regulations.

- Preparation.  Delete the last sentence and replace with the following:

Apply first pass seven days after the final lift pavement.  Apply the final pass a minimum of thirty days after the initial pass or as directed by the Engineer.

- Application.  Delete first paragraph and replace with the following:

Match the new skip stripes to the pattern of existing markings on at least one end of the project.  Monitor the bead application to ensure proper bead embedment and density.  In spray applications ensure sinker beads uniformly penetrate the full thickness of the marking.  Apply marking materials by one or more of the following methods, appropriate to the pay item(s) in the bid schedule.  Apply markings at the thickness specified uniformly across their width and along their length.  At least two passes of equal thickness are required to obtain the thickness specified.  Place additional passes squarely on top of the first pass, within +/- 1/16 inch laterally and =/- 3 inches longitudinally.  The thickness specified is the minimum.

Add the following after (2)

(3)	Longitudinal Extruded Markings   Apply with certified extrusion equipment.  Uniformly apply top coat of beads with a mechanical dispenser.

- Longitudinal Inlaid Protected Markings   Apply with certified extrusion equipment.  Grind the slot to the correct depth, and in proper alignment, using a diamond edged grinder capable of grinding the slot to the specified depth and width in a single pass.  After grinding obtain approval before placing marking material.  Fill the slot edge-to-edge, making the line flat or slightly convex on top and to the specified width.  Uniformly apply top coat of beads with a mechanical dispenser

- Transverse Markings   Apply markings as shown.  Apply with certified spray or extrusion equipment.  Apply sinker beads as specified at minimum drop rate of 1 lb/yd2

- Legends Only/Arrows120mils.  .  Apply with certified spray equipment.  Apply sinker beads as specified at a minimum drop rate of 1 lb/yd2.

- Sampling.  Delete in it’s entirety and replace with the following:

Record the following readings, and the locations where they were taken, and submit them to the engineer within 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of pavement.

For inlay applications, record the depth of the slot every 300 feet during the grinding operation.

For other longitudinal applications, measure the thickness of the lines (above the pavement surface), at the time of application, every 300 feet.

Inspect the line initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with specification material.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 60 mils

#### METHYL METHACRYLATE PAVEMENT MARKING

#### YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 | Inlaid Markings2 |
| --- | --- | --- |
| ##### Longitudinal Type3 ##### (Center and Edge lines) | 90 mils | 60 mils |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 120 mils | 60 mils |
| Neutral Area (Diagonals, Chevrons) | 60 mils | 60 mils |

1. 	Measure Type V spray without glass beads.  Tolerance is ±4 mils.  Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 6” x 12” flat sheet of 80 mils thick aluminum placed in the path of the striping guns.

2. 	Cut the inlaid slots to a depth of 120 mils.  Do not over fill the slots.

3. 	Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 60 mils per application pass.

Non-Inlaid Markings

New asphalt pavement:  Apply interim non-inlaid Longitudinal and Transverse Type markings at 30 mils.

Add the following under item 4.  before the third paragraph: A film test stripe will be required at the beginning of each striping shift, and when there is a change in the asphalt type.  Additional film test stripes may be required at the Engineer’s discretion.  (7/28/99)R221M98

670-3.04 PAVEMENT MARKING REMOVAL.  Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement.  Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING.  Delete in its entirety and replace with the following:

1.	Length of Stripe.  +/- 2”

2.	Width of stripe.  + ¼ inch, - 1/16 inch

3.	Lane Width.   +/- 4 inches from the width shown on plans.

- Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

- Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

- All Stripes.  Keep the center of the stripe within 4 inches from the planed alignment.

- Double stripes.  +/- ¼ inch

- Thickness.  Minimum specified to a maximum of +15mils.

- Depth of Inlay Slot.  Minimum specified to a maximum of – 40 mils.

- Thickness of Protected Inlaid Marking Material.  Minimum specified to a maximum of  + 40 mils.

If it is determined that the material is being placed too thin, or otherwise not to specification, make immediate adjustments to correct the problem.

Durable pavement markings applied by any method will be unacceptable if:

  - The marking is not straight, not wide enough, or not trues to line.

  - The thickness of the line is not uniform or less than specified.

  - The top of the line is not smooth and uniform.

  - The material is uncured.

  - The material blackens or is inconsistent in color.

  - The inlay slot is not filled to the specified depth.

  - The inlay slot is not ground to the specified depth.

  - The edges of the markings are not clear-cut and free from overspray.

  - The reflective elements are not properly embedded.

  - The markings exhibit poor adhesion.

  - The retro-reflectivity of the markings is less than specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repair in a “patch-work” manner.  If more than one repair is required in a single 300-foot section, grind and repair the entire section.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 3:

4	Gallon Basis: The Engineer will measure the Methyl Methacrylate material used to form the pavement markings accepted by the Engineer in gallon.

Item 670(13), Durable Pavement Markings, Inlay will not be measured for payment.

Thickness will be measured from the top of the marking to the top of the wearing surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

There will be no separate or additional payment for the following:

- Over-runs of material caused by the variation of the gradation of the asphalt.

- Additional material required to achieve the thickness specified on open-graded pavement.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

Costs associated with the MMAMS are subsidiary to 670 items.  No separate payment shall be made for furnishing and maintaining the MMAMS.

Repair of any damaged pavement or surfacing caused by the pavement marking removal operation will not be paid for directly, but will be subsidiary to 670(13) Durable Pavement Markings, and work performed under Section 643.

Add the following:  Grooving pavement will be subsidiary to item 670(13) Durable Pavement Markings, Inlay.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

670(10B)	Methyl Methacrylate Pavement, Surface Applied	Gallon

670(13)	Durable Pavement Markings, Inlay	Lump Sum

## SECTION 703

## AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

## TABLE 703-2

## AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 |  |  |
| 1 inch | 70-100 | 100 | 100 |
| ¾ inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

Special Provisions

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.

Coarse Aggregate.  Add the following to the Table:

Percent Fracture for Type IV is 90% double face.

Add the following to Table 703-3.

SIEVE	GRADATION

Type IV

½”	100%

3/8”	80-95

#4	55-70

#8	35-50

#16	20-40

#30	15-30

#50	10-24

#100	5-15

#200	4-7

703-2.13 AGGREGATE FOR STONE MASTIC ASPHALT PAVEMENT

Coarse Aggregate (retained on the # 4 sieve).  Coarse aggregate shall be free from clay balls, vegetative matter or other deleterious matter and consist of sound, tough, durable rock of uniform quality not coated with dirt or other finely divided mineral matter.  Crush stone or cobbles to such a degree that all faces are fractured and meet the following requirements:

Property			Test Method		Requirement

Percent of Wear		AASHTO T 96	30 max.

Degradation			ATM T-13		30 min.

Percent Sodium Sulfate Loss	AASHTO T 104	9   max. (5 cycles)

Percent Fracture		WAQTC TM 1*

All Faces 					75 min.

*  Except that a Fractured Face is defined as the entire projected area when viewed normal to that face.

Flat & Elongated Particles	ATM 306

3 to 1						20% max.

5 to 1						5%   max.

Absorption			AASHTO T 85	2%   max.

Nordic Abrasion		ATM 312		12.0 max.

Fine Aggregate (passing the # 4 sieve).  Consist entirely of 100 percent crushed aggregate and be non-plastic as determined by WAQTC FOP for AASHTO T 90.  Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Property	Test Method			Requirement

#### Uncompacted Voids	AASHTOT304		45 min

#### Method A

Mineral Filler. Meet AASHTO M 17. Use rock dust from the aggregate crushing operation or crushed limestone free of agglomerations and sufficiently dry to flow freely.

Blend Aggregate. Blend the aggregate fractions to meet the grading requirements of Table 703-9 as determined by WAQTC FOP for AASHTO T 27/T 11.

TABLE 703-9

STONE MASTIC ASPHALT CONCRETE AGGREGATE

Percent Passing by Weight

Sieve Designation			Requirement

¾ inch			100

½ inch  			68-80

3/8 inch			 < 60

# 4 sieve			20-27

# 8 sieve			14-20

# 200 sieve			  8-11

(5/31/02)

703-2.15 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT (SUPERPAVE)

Coarse Aggregate.  (retained on #4 Sieve)  Remove all natural fines passing a #4 sieve before crushing aggregates for this asphalt concrete mixture.  Crush only aggregate that is free from clay balls, vegetative matter or other deleterious matter and consists of sound, tough, durable rock of uniform quality not coated with dirt or other finely divided mineral matter.  Meet the following requirements;

#### Property		Test Method		Requirement

Percent of Wear				AASHTO T 96		30 max.

Degradation					ATM T-13			30 min.

Percent Sodium Sulfate Loss			AASHTO T 104		9   max. (5 cycles)

Percent Fracture				WAQTC TM 1

Two Faces 			90 min.

Flat & Elongated Particles			ATM 306

3 to 1				20% max.

5 to 1				5%   max.

Absorption					AASHTO T 85		2%   max.

Nordic Abrasion				ATM 312			12.0 max.

Fine Aggregate (passing the #4 sieve).  Remove all natural fines passing a #4 sieve before crushing aggregates for this asphalt concrete mixture.  Consist entirely of aggregate produced from aggregate crushing process and be non-plastic as determined by WAQTC FOP for AASHTO T 90.  Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness and the following:

##### Property	Test Method	Requirement

Fine Aggregate Angularity	AASHTO T 304	45% min.

Method A

SECTION 710

FENCE AND GUARDRAIL

# Special Provisions

710-2.11 GUARDRAIL TERMINALS. Add the following:

Use the ET-2000 LET.

The current guardrail end terminal drawings approved by the Department are as follows:

# Drawing	Original	Latest

# Number	Date	Revision	Comments

# ET-2000 LET	Metric		SS 155M	7/18/00	None	11.4 m, 7 tube, Plus head

# English	SS 155	5/18/00	None	37.5’, 7 tube, Plus head

(01/22/02)R249

SECTION 712

## MISCELLANEOUS

## Special Provisions

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS. Add the following subsection:

2.	Performance Properties: Add the following:

k.	Adhesion: To Portland Cement, minimum 2,000 pounds per inch, to asphalt, dependent on tensile failure of the substrate.

(12/04/02)R246

## SECTION 740

### SIGNALS AND LIGHTING MATERIALS

Special Provisions

740-2.02 SIGNAL AND LIGHTING STRUCTURES.  Add the following after the fifth paragraph:  Furnish poles and mast arms with a round or 16-sided cross section.  Fabricate elements greater than ½-inch thick from steels that conform to ASTM A 709 and meet the Fracture Critical Impact Test requirements for zone 3.

Delete the sixth and seventh paragraphs and add the following: Fabricate posts, poles, and mast arms from tapered steel tubes that taper at a minimum rate of 0.14-inches of diameter per foot of length.  Fabricate tubes with walls up to ½-inch thick from the prequalified base metals listed in AWS D1.1 and which feature maximum yield strengths of 70,000-psi.

Fabricate 10 feet long signal posts from sheet steel that features a minimum thickness of 11 US Standard Gage.  Fabricate each post with a minimum five inch inside diameter at the base plate.  Use a three and one-half inch long piece of 4-inch schedule 40 pipe that conforms to ASTM A 53 as a post-top adapter

Add the following to the eighth paragraph: The Department will not accept poles and mast arms that are made with laminated steel elements.

Delete the twelfth paragraph and add the following: Fabricate pile cap adapters from steel piles that conform to API 5L X42 and from steel plate that conforms to ASTM A 709 Grade 50. Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Furnish the adapters hot dip galvanized according to ASTM A 123, except leave the beveled edge free of zinc.  Fabricate the anchor plate to match the base plate of the lighting standard.

Delete the fourteenth paragraph and add the following: Perform welding to conform to Subsection 504-3.01 8.  Welding and the following:

Delete the last two sentences in subparagraph 4 that follow the fourteenth paragraph.

Add the following to subparagraph 5 that follow the fourteenth paragraph.  Inspect 100% of fillet welds by MT.

740-2.13 SPECIAL AUXILIARY EQUIPMENT.  Add the following:

7.	Traffic Logging System.  Furnish, and others will install in the controller cabinet, nine stand-alone units that collect, time stamp, and store data in an unattended manner.  The traffic logging system shall conform to the following:

a.	Operation.  The unit shall accept a new operating program, operational parameters, and the date and time stamp from a personal computer, downloaded through an RS-232 cable.  The use of replaceable proms to change the operational program is unacceptable.  Data collection shall be automatic and not require an operator to reset or start operation.

In the event of a power interruption, data collection shall automatically restart at the proper time.  Other than the current sample being collected, the unit shall not lose stored data because of the power interruption.  At power-up or at the restoration of power after an outage, the unit shall log the date and time at the start of data collection.

The unit shall maintain the operating program, data storage, and date/time for a minimum of 5 years from when power is removed from the unit.  The internal program/data size shall be a minimum of 32,000 bytes.

b.	Input Interface.  The unit shall have a minimum of 28 inputs.  The Municipality of Anchorage’s Signal Maintenance Section will install the interface cable in the controller cabinets under Item 660(26), Signal System Timing and Adjustments.

c.	Output Interface.  Furnish units with an RS-232 serial port that allows a user to download and upload directly between the unit and a personal computer using the Microsoft Windows NT operating system or the external dial-up multi-port modem.

d.	Software.  Supply Microsoft Windows NT compatible software and user manuals with the unit that provides the operator an interface to the hardware.  Furnish menu driven software that allows an operator to: 1) download to initialize the unit with its operating program and data collection parameters, 2) upload information from the unit (both stored data and real-time data) and 3) transfer a data file to a text file.

The operating program shall provide for month, day, day-of-week, hour, minute, and second information and allow sampling periods of 5, 15, 30, and 60 minutes.

APPENDIX A

EROSION AND SEDIMENT CONTROL PLAN

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST

APPENDIX D

SIGN PANEL DETAILS