SPECIAL NOTICE TO BIDDERS

The following information is available at 4111 Aviation Avenue to assist in preparing your bids:

1

.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

- Quantity Computations

- Existing Pavement Core Information:  Old Glenn Highway at Palmer, MP 0-11.5 Pavement Recommendations Report (08/20/03)

- State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities, January 1997 and Alaska Storm Water Pollution Prevention Plan Guide, October 1, 2003.

- Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

- The Standard Specifications for Highway Construction 2002 USC units may be viewed or downloaded at no charge from the Statewide Design and Engineering Service Division’s external website.

- Alaska Test Methods Manual (Lab & Field), 2004 Edition.  ($25.00)

2.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

3.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

4.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for you to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

5.	The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retro reflectivity.  See Subsection 643-3.11, High Visibility Clothing for requirements.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the

STATE OF ALASKA

SPECIFICATIONS

for

HIGHWAY CONSTRUCTION

2002 STANDARD SPECIFICATIONS

SECTION 101

DEFINITIONS AND TERMS

## Special Provisions

101-1.03.DEFINITIONS.  Add the following definition:

NON-FROST SUSCEPTIBLE.  Material that contains 6 percent or less passing the No. 200 screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 3 inch material.  (11/29/01)R1USC

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.10 ADDENDA REQUIREMENTS.  Delete this Subsection in its entirety and substitute the following:  Addenda will be issued to the individual or company to whom bidding documents were issued.  Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone.  Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents.  It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids.  No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening.  If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form.  (10/23/02)R171USC02

-

# SECTION 103

# AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  CONSIDERATION OF BIDS.  Add the following:  In determination of the low bidder for state funded projects, a 5 percent bid preference will be given to Alaska bidders, as required under AS 36.30.170.  "Alaska bidder" means a person who:

(1)	holds a current Alaska business license;

(2)	submits a bid for goods, services, or construction under the name as appearing on the person's current Alaska business license;

(3)	has maintained a place of business within the state staffed by the bidder or an employee of the bidder for a period of six months immediately preceding the date of the bid;

(4)	is incorporated or qualified to do business under the laws of the state, is a sole proprietorship, and the proprietor is a resident of the state, is a limited liability company organized under AS 10.50 and all members are residents of the state, or is a partnership, and all partners are residents of the state; and

(5)	if a joint venture, is composed entirely of ventures that qualify under (1) through (4), above.

Except for timber, lumber and manufactured lumber products used in the construction project under AS 36.30.322(b), an Alaska products preference will be given as required under AS 36.30.326 - 36.30.332 when the bidder designates the use of Alaska products.  The bidder shall complete the Alaska Products Preference Worksheet, per its instructions, and submit it with his bid to indicate those Alaska products which are proposed for use.  If the successful bidder/contractor proposes to use an Alaska product and does not do so, a penalty will be assessed against the successful bidder/contractor in an amount equal to the product preference percentage granted to the successful bidder/contractor plus one percent multiplied by the total declared value of the Alaska products proposed but not used.  (05/12/89)S20

103-1.06 INSURANCE REQUIREMENTS.  Delete this Subsection in its entirety and substitute the following:  The Contractor shall provide evidence of insurance with an insurance carrier or carriers satisfactory to the Department covering injury to persons and property suffered by the State of Alaska or by a third party as a result of operations under this contract by the Contractor or by any subcontractor.  The Contractor's insurance shall provide protection against injuries to all employees of the Contractor and the employees of any subcontractor engaged in work under this Contract.  All insurance policies (a) shall comply with AS 21 and (b) shall be issued by insurers that (i) are licensed to transact the business of insurance in the State of Alaska under AS 21 and (ii) have a financial rating acceptable to the Department. The Contractor shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.

Where specific limits and coverages are shown, it is understood that they shall be the minimum acceptable. The requirements of this subsection shall not limit the Contractor’s indemnity responsibility under Subsection 107-1.13.  Additional insurance requirements specific to this contract are contained in the Special Provisions, when applicable.

The Contractor shall maintain the following policies of insurance with the specified minimum coverages and limits in force at all times during the performance of the Contract:

- Workers' Compensation:  as required by AS 23.30.045, for all employees of the Contractor engaged in work under this Contract.  The Contractor shall be responsible for Workers' Compensation Insurance for any subcontractor who performs work under this Contract.  The coverage shall include:

- Waiver of subrogation against the state and Employer's Liability Protection at $500,000 each accident/$500,000 each disease;

- “Other States” endorsement if the Contractor directly utilizes labor outside of the State of Alaska;

- United States Longshore and Harbor Workers’ Act Endorsement, whenever the work involves activity over or about navigable water; and

- Maritime Employer’s Liability (Jones Act) Endorsement with a minimum limit of $1,000,000, whenever the work involves activity form or on a vessel on navigable water.

- Commercial General Liability:  on an occurrence policy form covering all operations with combined single limits not less than:

- $1,000,000 Each Occurrence;

- $1,000,000 Personal Injury;

- $2,000,000 General Aggregate; and

- $2,000,000 Products-Completed Operations Aggregate.

- Automobile Liability:  covering all vehicles used in Contract work, with combined single limits not less than $1,000,000 each occurrence.

- Umbrella Coverage:  for Contract amounts over $5,000,000 not less than $5,000,000 umbrella or excess liability.  Umbrella or excess policy shall include products liability completed operations coverage and may be subject to $5,000,000 aggregate limits.  Further, the umbrella or excess policy shall contain a clause stating that it takes effect (drops down) in the event the primary limits are impaired or exhausted.

- The State of Alaska shall be named as an additional insured on policies required by paragraphs 2 thru 4 above. All of the above insurance coverages shall be considered to be primary and non-contributory to any other insurance carried by the State of Alaska, whether through self-insurance or otherwise.

In any contract or agreement with subcontractors performing work, the Contractor shall require that all indemnities and waivers of subrogation it obtains, and any stipulation to be named as an additional insured it obtains, shall also be extended to waive rights of subrogation against the State of Alaska and to add the State of Alaska as an additional named indemnitee and as an additional insured.

The apparent low bidder shall furnish evidence of insurance to the Department before award of the Contract.  The evidence shall be issued to the Department and shall be either a certificate of insurance or the policy declaration page with all required endorsements attached and must:

- Denote the type, amount, and class of operations covered;

- Show the effective (and retroactive) dates of the policy;

- Show the expiration date of the policy;

- Include all required endorsements; and

- Be executed by the carrier's representative.

When a certificate of insurance is furnished, it shall contain the following statement:

“This is to certify that the policies described herein comply with all aspects of the insurance requirements of (Project Name and Number).  The insurance carrier agrees that it shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.”

The Department’s acceptance of deficient evidence of insurance does not constitute a waiver of Contract requirements.

Failure to maintain the specified insurance or to provide substitute insurance if an insurance carrier becomes insolvent, is placed in receivership, declares bankruptcy, or cancels a policy may be grounds for withholding Contract payments until substitute insurance is obtained, and may, in the Department's discretion, be grounds for declaring the Contractor in default.  (05/06/03)R271USC02

SECTION 105

CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES.  Add the following:  Request locates from all the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities:

| ALASKA DIGLINE, INC. Anchorage Area………………… 278-3121 Statewide…………………….800-478-3121 Who will notify the following: |  |
| --- | --- |
| - ACS | - Matanuska Electric Assoc. |
| - Aircraft Service International Group | - Matanuska Telephone Assoc. |
| - Alaska Fiber Star | - MOA Street Maint. Dept. |
| - Alaska Native Medical Center | - Municipal Light & Power |
| - Alaska Railroad Corp. | - Phillips Alaska, Inc. |
| - Anchorage School District | - Telalaska |
| - Anchorage Water & Wastewater | Alyeska Cable |
| - AT&T Alascom | Eyecom, Inc. |
| - Chugach Electric Assoc. | Interior Telecom. |
| - City of Wasilla | Mukluk Telecom. |
| - ENSTAR Natural Gas | - Tesoro Alaska Pipeline |
| - GCI | - Unocal |
| Kanas | - United Utilities |
| - Homer Electric Assoc. | - Yukon Telephone |
| - Marathon Oil |  |

Call the following utilities and agencies directly:

DOT&PF Maintenance and Operations	(907) 269-0782

Alaska Railroad Corporation	(907) 265-2520

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for your convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if you are required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of your two (2) week work plan, or not required by the contract.

The utility shall give you, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit you, through the Engineer, from working near the utility’s facilities when the ground is frozen.  (04/01/03)R3M98

Specific coordination requirements for the specific utilities are included below:

MATANUSKA ELECTRIC ASSOCIATION (MEA).  The existing light pole at East Twin Peaks Road shall be relocated due to the proposed ditch grading.  Provide staking for the proposed ditch to determine an acceptable location for the light pole.  MEA will require two (2) calendar days to complete the relocation and removal of their light pole.

MEA’s existing poles G18 and G19 are in conflict with the proposed back slope cut between Station 411+00 Rt. and Station 423+00 Rt.  Pole G16 and pole G17 shall be relocated to accommodate the aerial clearance requirements for the attached aerial telephone cable.  Stake the proposed cut limits and clear the required area needed to accommodate the relocation of the poles.  MEA will be allowed seven (7) calendar days to relocate pole G18 and pole G19 and place new aerial conductor.  MTA will relocate their cable to new poles after MEA relocates the existing poles.  MEA will then be allowed two (2) calendar days to complete the retirement of the two poles.

At approximately Station 451+00 Lt. MEA will remove the existing transmission down guys closest to the roadway and install an overhead guy and guy pole on the left side of the road.  Distribution pole B141 will be relocated in order to install and maintain clearance with the overhead guy.  MEA will be allowed four (4) calendar days to complete the relocation of their facilities.

MATANUSKA TELEPHONE ASSOCIATION (MTA).  MEA’s existing poles G18 and G19 are in conflict with the proposed back slope cut between Station 411+00 Rt. and Station 423+00 Rt.  A MTA aerial telephone cable is attached to the pole line.  MTA will be allowed four (4) calendar days to relocate their aerial cable to the new poles after MEA has installed the new poles and relocated the conductor.

ENSTAR Natural Gas Company (ENSTAR).  ENSTAR owns the existing natural gas lines.  There are several locations for potential conflicts where ENSTAR’s lines cross the roadway and ditch.  Stake the proposed ditch to identify actual conflicts.  Approximate stations of the gas line crossings are as follows:

Station 513+00			Station 529+00

Station 515+00			Station 549+50

Station 521+50			Station 581+50

If adjustment is required, ENSTAR will be allowed two (2) calendar days at each location to complete the required adjustment.

Work around ENSTAR’s facilities shall adhere to the Safety Requirements for Excavation Adjacent to Natural Gas Pipelines as provided in Appendix E.

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:  The following project will be under construction concurrently with this project:

Project:  Eklutna Tailrace Fishing Access

Project Number:  75056-1

Owner:  Department of Natural Resources (907-269-8736)

Contractor:  To Be Determined

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above project to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contract.  (02/01/00)R175M98

-

105-1.15 PROJECT COMPLETION.  Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Plant Establishment and Maintenance; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve you from further maintenance responsibilities, except under Subsections 618-3.04, 621-3.04, 641-2.01, and 641-3.01, and will stop the count of contract time but will not relieve you of any obligations under the Contract.  (05/28/03)R237USC02

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following:  Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district.  (03/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01  SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  Add the following:  Pursuant to AS 36.15.050 and AS 36.30.322, agricultural/wood products harvested in Alaska shall be used in state funded projects whenever they are priced no more than seven percent above agricultural/wood products harvested outside the state and are of a like quality as compared with agricultural/wood products harvested outside the state.

Maintain records which establish the type and extent of agricultural/wood products utilized.  When such products are not utilized, document the efforts he made towards obtaining agricultural/wood products harvested in Alaska and include in this documentation a written statement that he contacted the manufacturers and suppliers identified on the Department of Commerce and Economic Development's list of suppliers of Alaska forest products concerning the availability of agricultural/wood products harvested in Alaska and, if available, the product prices.  Complete this documentation at a time determined by the Contracting Officer.

The Contractor's use of agricultural/wood products that fail to meet the requirements of this Subsection shall be removed and replaced in accordance with the last paragraph of Subsection 105-1.03, Conformity With Plans and Specifications.  (05/07/91)S18

106-1.02 LOCAL MATERIAL SOURCES.  Add the following under item 2. Inspection and Acceptance:  In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to their beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (05/01/02)R262M98

106-1.03 TESTING AND ACCEPTANCE.  Add the following:

When the specifications refer to the following test methods, use the corresponding test method shown.

| REPLACE TEST METHOD: | WITH TEST METHOD: |
| --- | --- |
| WAQTC FOP for AASHTO T 89/T 90 | WAQTC FOP for AASHTO T 89 and WAQTC FOP for AASHTO T 90 |
| WAQTC TM 1 | WAQTC FOP for AASHTO TP 61 |
| WAQTC TM 4 | ATM 405 |

(02/05/04)ES05

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

# Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES.  Add the following:  Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If you discover cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by your operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits.  Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained.  Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

The Department has received a Nationwide Permit #3 from the Department of the Army and it is included in Appendix A.

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from the Contractor.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following:  If you require water for any construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.  (05/29/02)R7M98

107-1.13 RESPONSIBILITY FOR DAMAGE CLAIMS.  Delete this Subsection in its entirety and substitute the following:  The Contractor shall indemnify, hold harmless and defend the State of Alaska and its agents and employees from any and all claims or actions for injuries or damages whatsoever sustained by any person or property that arise from or relate to, directly or indirectly, the Contractor's performance of the Contract, however, this provision has no effect if, but only if, the sole proximate cause of the injury or damage is the Department’s negligence.  This Contract does not create a third party benefit in the public or any member of the public, nor does it authorize any person or entity not a party to this Contract to maintain a suit based on this Contract or any term or provision of the Contract, whether for personal injuries, property damage or any other claim or cause of action.  (05/06/03)R271USC02

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following after the last paragraph:  When construction activities meet any of the following conditions, advise the appropriate owning Utility(s) in writing at least 24 hours in advance of work.

1.	Operations anticipated being within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services. (10/23/02)R170USC02

-

SECTION 108

PROSECUTION AND PROGRESS

## Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1. A progress schedule.  and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order in which the work will be carried out and the contemplated dates on which you and the subcontractors will start and finish each of the salient features of the work, including any scheduled periods of shutdown.  Indicate any anticipated periods of multiple-shift work in the CPM Schedule.  If revisions to the proposed CPM Schedule are required, make them promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to your schedule, or upon request of the Engineer.

(12/13/02)R261M98

Delete item 5 of the first paragraph and substitute the following:

- The submittals identified under Subsection 641-1.03, Submittals.

- (01/31/02)R160M98

108-1.06 DETERMINING AND EXTENDING CONTRACT TIME.  Delete the third paragraph under item 2 “Suspension and Extension of Contract Time,” and substitute the following:

Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.  (03/13/03)R242USC02

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.05 COMPENSATION FOR EXTRA WORK.  Delete the first sentence of the second paragraph of sub-item a. of item 3 and substitute the following:  The regular hourly rental rate is the adjusted monthly rate for the basic equipment plus the adjusted monthly rate for applicable attachments, both divided by 176, and multiplied by the area adjustment factor specified on the adjustment maps for the Alaska - South Region.  (10/23/02)R14USC02

109-1.06 PROGRESS PAYMENTS.  Add the following:  Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

#### Special Provisions

202-3.01 GENERAL.  Add the following:  The construction of mail box installations shall use new posts and mail boxes.  Mailboxes shall be United States Postal Service approved, either traditional or contemporary design, having a minimum length of 21 inches, minimum width of 8 inches and minimum height of 11 inches.  Existing posts and foundations shall be removed with remaining holes backfilled to the level of surrounding ground.  (04/18/00)R74USC

-

The mailbox turnouts shall be staked and constructed within the existing right-of-way.  The staked locations of the mailbox turnouts will be approved by the Engineer prior to construction.

Add the following:  This work also includes the removal of the shoulder berm around the base of the guardrail to establish shoulder grade as shown on the Plans.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 6 inches.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at (907) 269-7590.  (03/29/01)R84M98USC

Add the following Subsection:

202-3.06 REMOVAL OF SHOULDER BERM.  The Contractor shall remove the shoulder berm around the guardrail as shown on the Plans or as directed by the Engineer.  The Contractor shall keep the removed berm material out of any water bodies or wetland areas.

202-4.01 METHOD OF MEASUREMENT.  Add the following:

No measurement will be made for removing the shoulder berm around the guardrail.

202-5.01 BASIS OF PAYMENT.  Add the following:

Item 202(41).  The contract lump sum price paid for removal of shoulder berm around guardrail constitutes full compensation for furnishing all work required to complete the work specified.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 202(41) Removal of Shoulder Berm | Lump Sum |

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

-

203-3.03 EMBANKMENT CONSTRUCTION.  Delete the first sentence of the tenth paragraph and substitute the following:  Place roadway embankment of earth materials in horizontal layers not exceeding 8 inches in thickness measured before compaction.  Each layer of classified material shall have its joint offset from the joint below, longitudinally by 1 foot and transversely by 10 feet.

Where the plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements.  Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104, Scope of Work.  (11/05/02)R23USC02

-

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following:  Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP FOR AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the No. 200 sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the No. 4 sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus No. 4 material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 3/4 inch sieve with the plus 3/4 inch material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1 percent.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5.  (11/05/02)R193USC02

Compact embankment within 20 feet of a bridge abutment full width to not less than 100 percent of the maximum density.  Material used within this zone shall be graded to pass the 3-inch sieve.  (11/05/02)R113USC02

203-5.01 BASIS OF PAYMENT.  Add the following:  Removal and disposal of pavement removed from the digout areas and paved approaches are subsidiary to Item 203(3) and no separate payment shall be made.

No separate payment will be made for any clearing or grubbing or its disposal.  This work is subsidiary to 203 items.

Grading and placement of material used within 20 feet of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(6A), Borrow, Type A.  (11/05/02)R113USC02

-

-

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-2.01 MATERIALS.  Add the following after the first sentence:  If no gradation type is specified in the bid schedule the base course material gradation shall conform to the requirements for Grading D-1. (11/05/02)R116USC02

Add the following after the first sentence:  At your option, recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5-inch sieve and 95 to100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 to 5.0 percent by weight of the RAM.

301-3.03 SHAPING AND COMPACTION.  Add the following:  If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern.  The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

Compaction for areas where the Engineer determines aggregate base course is required to construct superelevations or guardrail heights it shall be by compactive efforts approved by the Engineer.

301-5.01 BASIS OF PAYMENT.  Add the following:  If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.  (11/05/02)R176USC02

SECTION 303

RECONDITIONING

Special Provisions

303-1.01 DESCRIPTION.  Add the following:  This work also consists of all excavation and shaping required to construct superelevations and maintain existing guardrail heights listed in Subsection 606-3.11.  Additional excavation, beyond the depth shown on the Plans, may be required in order to achieve the superelevations and guardrail heights.

303-5.01 BASIS OF PAYMENT.  Add the following:  Work required to construct superelevations and guardrail heights as detailed in Subsection 303-1.01 will not be paid for separately, but shall be subsidiary to Item 303(1), Reconditioning.

When the Engineer determines aggregate base course is required to construct superelevations or guardrail heights it will be paid for as required in Section 301.

(11/05/02)R254M98

SECTION 401

ASPHALT CONCRETE PAVEMENT

# Special Provisions

401-2.01 COMPOSITION ON MIXTURE – JOB MIX DESIGN.  Table 401-1, Voids in Mineral Aggregate (VMA), %, min., Change Type III to Type III, IV.

401-2.03  Asphalt CEMENT.  Delete the second paragraph and substitute the following.  Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping.  Storage tanks used for the batch shall be noted on the test report.  Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project.  A printed weight ticket of anti-strip shall be included with the asphalt cement delivery ticket.  The location where anti-strip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturer’s certificate of compliance, Subsection 106-1.05.

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading.

- Batch number and storage tank.

- Type, grade, temperature, and quantity of materials loaded.

- Type and percent of anti-strip added.

401-3.01 WEATHER LIMITATIONS.  Add the following second paragraph:  Place the top layer of paving or surface course between May 1 and August 15.  Place bottom and middle layers of asphalt, leveling courses, and treated bases according to the limitations of this Subsection.  (07/03/03)S90

401-3.03 ASPHALT MIXING PLANT.  Add the following to the end of the second paragraph.  Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve), to sample asphalt cement.

Standard Modification

401-3.13 COMPACTION.  Add the following to the end of the first paragraph:  Compact asphalt concrete mixture immediately after it is placed and spread, and as soon as it can be compacted without undue displacement, cracking or shoving.  Perform initial breakdown compaction while the asphalt concrete surface mixture temperature is greater than 235 degrees F and finish compaction before the surface temperature reaches 150 degrees F.  (07/03/03)E02

Special Provisions

401-3.13 COMPACTION.  Delete the third paragraph and substitute the following:  Acceptance testing for density will be determined by WAQTC FOP for AASHTO T 166/T 275 except that a 6 inch diameter core is required.  (Acceptance testing for density of leveling course or temporary pavement will not be required.)

401-3.14 Joints.  Delete the last paragraph and substitute the following:  Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91 percent MSG.  Cut one 6-inch diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.  The MSG will be determined in accordance with WAQTC FOP for AASHTO T 209.

If the average joint density for any lot is less than 91 percent MSG, immediately change and improve the method used for joint construction.  Seal all of the joints constructed in the lot with GSB-78 Mfg by Asphalt Systems or approved equal by the engineer.  Seal joint while asphalt is clean and free of moisture, dirt or debris.

No additional cost or contract time will be paid to repair or seal joints.  Seal or repair joints prior to paint striping.

Delete the last paragraph.

Standard Modification

Delete the heading of Subsection 401-3.15 and substitute the following:

401-3.15 SURFACE REQUIREMENTS AND TOLERANCE.

The finished surface of asphalt concrete paving shall match dimensions shown on the Plans for horizontal alignment and width, profile grade and elevation, crown slope, and paving thickness.  Water shall drain without puddles, across the pavement surface.  The surface shall be of uniform texture and without ridges, humps, depressions, and roller marks.  The surface shall be free of raveling, cracking, tearing, rutting, asphalt cement bleeding, and aggregate segregation.  The asphalt concrete mixture shall be free of foreign material, uncoated aggregate and oversize aggregate.

Any finished surface area that does not meet the requirements of this Subsection is deemed unacceptable as per Subsection 105-1.11.  The Engineer will determine whether the unacceptable asphalt concrete mixture shall either be corrected, or removed and replaced.  Submit correction methods to the Engineer for approval prior to correction work commencing.  (07/03/03)E02

Special Provisions

Add the following:  The Engineer will measure the surface smoothness of the top lift of the asphalt in all of the driving lanes with an inertial profiler before final acceptance of the project.  No measurements will be taken in turn lanes, lane transitions, within 25 feet of bridge abutments, lanes adjacent to curb and gutter, lanes with manholes, or within 25 feet of existing pavement.  The Contractor shall remove and replace, or grind any portion of final pavement surface having a smoothness Profile Index (PrI) greater than 15 inches/mile in a 0.10 mile segment. PrI will be calculated using a 0.2 inch/mile blanking band.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following:  All costs associated with the patching of defective areas shall be borne by the Contractor.

Standard Modification

Add the following Subsection:

401-3.17 TEMPERATURE REQUIREMENTS.  The Engineer may reject asphalt concrete mixture that is mixed, hauled, spread and placed, or compacted at a temperature outside the temperature range determined by either the Job Mix Design, by a control test strip, or by the Specifications.  Rejected asphalt concrete mixture is deemed unacceptable as per Subsection 105-1.11.  The Engineer will determine whether the unacceptable asphalt concrete mixture shall either be corrected, or removed and replaced.

At the Engineer’s discretion, the Contractor may be allowed to compact asphalt concrete mixture that is already placed and spread but is outside the temperature range.  If the compacted asphalt concrete mixture fails the Engineer’s tests for acceptance, it must be removed and replaced as per Subsection 105-1.11.  (07/03/03)E02

401-4.01 METHOD OF MEASUREMENT.  Add the following:

Longitudinal Joint.  By the linear foot of longitudinal asphalt joints in the top pavement surface.

Joint Density.  By the meter of longitudinal asphalt joints in the top pavement surface and the calculated joint density.  (07/03/03)S92

Standard Modification

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  Delete fifth and sixth paragraph and replace with the following:  For contract quantity of less than 1,500 tons (and for temporary pavement), asphalt concrete pavement will be accepted for payment when the following requirements are met:

1.	The Engineer approves a Job Mix Design.

2.	Asphalt concrete paving mixture complies with approved Job Mix Design.

3.	Final pavement thickness matches plans, and final density matches specifications.

4.	Final pavement surface meets requirements of Subsection 401-3.15.

The Engineer reserves the right to perform any testing required in order to determine acceptance.  If calibrated test equipment is not available, asphalt content of the mix may be determined by extraction in accordance with AASHTO T 164.  When testing is required in order to determine acceptance, at least two tests shall be taken for each approved mix design.

If asphalt concrete pavement fails to meet the requirements of this Subsection, the Engineer may determine a price reduction for asphalt as per Subsection 105-1.03; or the Engineer may direct you either to correct, or to remove and replace the unacceptable area as per Subsection 105-1.11.  (07/03/03)E02

Special Provisions

401-4.02 Acceptance Sampling And Testing.  Delete item 1. Asphalt Cement Content. and replace with the following:

1.	Asphalt Cement Content.  Samples taken for the determination of asphalt cement content will be taken at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

The Contractor shall sample asphalt cement from the asphalt cement supply line when requested, witnessed by the Engineer’s representative.  After purging residual asphalt from the sampling valve, take 3 one-quart samples (Department’s acceptance and referee samples, and Contractor’s retest sample).

Delete sub-items a. and b. of item 2. Aggregate Gradation. and replace with the following:

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates.  The dry batched aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Delete item 3. Density. and substitute the following:

3.	Density.  Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One (1) 6 inch diameter core is required for acceptance density testing only.  Acceptance density testing will be in accordance with WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  Delete second to last paragraph and replace with:  PAB = Price Adjustment Base = $42 per Ton.

Add the following:  Asphalt cement shall be randomly sampled and tested at a frequency of one sample taken for every 200 tons used.  No sampling and testing is required for projects having less than 100 tons of asphalt cement, but will be accepted based on shipping certification and supplier test results.  If the last project sample increment is less than 100 tons, it shall not be sampled and tested; but the asphalt quantity will be added to that of previous sample for pay evaluation.  If the last project sample increment is over 100 tons, it shall be sampled, tested, and evaluated separately.  Price adjustments for each sample will be assessed according to the Asphalt Binder Pay Reduction Table 401-4.

# TABLE 401-4

ASPHALT CEMENT PAY REDUCTION

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Specification | 0 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.1 | 0.25 | Reject or Engr Eval. |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | 1.00 to 1.11 |  | 0.99 to 0.88 |  |  |  | 0.87 to 0.71 | 0.70 to 0.50 | < 0.50 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 % |  | 1.001 to 1.092 |  |  |  | 1.093 to 1.184 | 1.185 to 1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 kPa |  | 2.199 to 1.816 |  |  |  | 1.815 to 1.432 | 1.431 to 1.048 | < 1.048 |
| Tests On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 kPa |  | 5001 to 5289 |  |  |  | 5290 to 5578 | 5579 to 5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 MPa |  | 301 to 338 |  |  |  | 339 to 388 | 389 to 450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 |  | 0.299 to 0.287 |  |  |  | 0.286 to 0.274 | 0.273 to 0.261 | < 0.261 |
| Direct Tension | > 1.0 % | > 1.0 % |  | 0.99 to 0.86 |  |  |  | 0.85 to 0.71 | 0.70 to 0.56 | < 0.56 |
| Tests on Original Binder |  |  |  |  |  |  |  |  |  |  |
| Toughness, in-lbs | > 110 | >93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity, in-lbs | > 75 | >63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |

# Asphalt Cement Price Adjustment for each sample = 5 x PAB x Qty x PRF

PAB = Price Adjustment Base

Qty = quantity of asphalt cement represented by asphalt cement sample

PRF = Pay Reduction Factor from Table 401-4

The total asphalt cement price adjustment is the sum of the sample price adjustments and is applied to Pay Item 401(6), Asphalt Price Adjustment.

Asphalt Binder Appeal Procedure.  Once notified of a failing asphalt cement sample, the Contractor has 21 days to issue a written appeal of the test results.  The appeal must be accompanied by all of the Contactor’s quality control test results and test results of a sample tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Department will review these test results provided by the Contractor and determine if the proposed price reduction will or will not remain in place.

If the Contractor challenges the Engineer’s decision, then the referee sample held by the Department will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  Their reported results will be binding on both the Department and the Contractor.  The Contractor shall pay for this testing if the sample fails.

401-4.04 EVALUATION OF PAVEMENT FOR SMOOTHNESS.  The Engineer will calculate and apply a separate asphalt Smoothness Price Adjustment for the top lift of pavement as measured in accordance with Subsection 401-3.15.  Calculate the smoothness price adjustment as follows:

1.	Smoothness Price Adjustment ($) = SF x PAB x PQ

If PQ is less than 1500 tons, 	SF = 0

If PQ is 1500 to 5000 tons,   	SF = 0.1166 – 0.0167 x (PrI)

If PQ is 5000+ tons,		SF = 0.0583 – 0.083 x (PrI)

SF= smoothness factor

PrI = final measured pavement smoothness (inches/mile)

PAB = Price Adjustment Base, see Subsection 401-4.03

PQ = final pay quantity of 401(1) in tons

Apply the smoothness price adjustment as an incentive/disincentive under Item 401(6), Asphalt Price Adjustment.

401-4.05 EVALUATION OF JOINTS FOR ACCEPTANCE.  Add the following:  The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 1,000 tons.

The Engineer will calculate an average of the required joint densities taken on the project.  Apply an incentive or disincentive price adjustment as part of Item 401(6), Asphalt Price Adjustment.

- If project average joint density is less than 91 percent MSG apply the following disincentives:

- The Contractor shall repair all of the asphalt joints on a project at the Contractor’s expense with an approved asphalt joint sealing method as per Subsection 401-3.14.

b.	Deduct = ($1.00 per lineal foot) x (lineal feet of paved joint for the entire project) x (91 % – Project Average Joint Density %) x 100

- If project average joint density is greater than 91 percent MSG apply the following incentive:

- Add = ($0.25 per lineal foot) x (lineal feet of paved joint for the entire project) x (Project Average Joint Density % – 91%) x 100                            (08/04/03)R199USC02

Standard Modification

401-5.01 BASIS OF PAYMENT.  Fourth paragraph, Item 1 delete “5000” and replace with:  1500.

(07/03/03)E02

# SECTION 508

WATERPROOFING MEMBRANE

# Special Provisions

508-1.01 DESCRIPTION.  Add the following:  Remove the existing asphalt concrete surface and membrane waterproofing on the Goat Creek Bridge (Bridge #0538).

508-3.01 APPLICATION OF MEMBRANE WATERPROOFING.  Add the following:

5.  Removing Existing Asphalt and Membrane Waterproofing.

- Remove existing asphalt concrete down to the base concrete bridge deck.  Do not employ removal methods that damage the concrete deck.

- Do not use a mechanical milling machine such as a reclaimer or planner.

- Recommend installation by half width construction.

- Prevent foreign material from entering the creek.

508-4.01 METHOD OF MEASUREMENT.  Add the following:

No measurement will be made for asphalt and membrane waterproofing removal.

508-5.01 BASIS OF PAYMENT.  Add the following:  Asphalt and membrane waterproofing removal will not be measured for payment but will be subsidiary to Item 508(1).

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 508(1) Waterproofing Membrane – Bridge #0538 | Lump Sum |

# SECTION 603

# CULVERTS AND STORM DRAINS

# Special Provisions

603-1.01 DESCRIPTION.  Add the following:  This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS.  Delete the second paragraph and substitute the following:

When Item 603(17-xx), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP) or Reinforced Concrete Pipe.  Corrugated Polyethylene Pipe is not allowed.  End Sections for Metal Pipe must be of the same material as the pipe.

Add the following: Culvert marker posts shall meet the requirements of Subsection 730-2.05, Flexible Delineator Posts. The color shall be blue with no other markings.  The 2.5-inch by 6-foot post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

Add the following Subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two (42) inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.  (08/27/03)R42USC

Grading of the embankment after pipe installation will be subsidiary to 603(17-xx) items.

SECTION 606

GUARDRAIL

# Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers.  Use flexible markers with an over all length of 72 inches.  The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag which provides approximately 20 square inches of surface area.  Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

  - If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

606-3.02 POSTS.  Delete the first two numbered items in this Subsection and substitute the following:  Exclusive of end treatments, use one type of post in each run of guardrail.

Delete the third paragraph titled “Set Posts as follows” and the numbered items below the third paragraph in that subsection, and replace with the following:

Set posts as follows:

- Set posts plumb, in the location and to the depth shown on the Plans or Standard Drawings.

- Choose an installation method that does not damage the post, adjacent pavement, structures, utility conduits, and final slopes.  Repair all damage to the satisfaction of the Engineer, or replace the damaged item, as per Subsection 105-1.11.  If the pavement becomes deformed after steel posts are driven, use hot mix to fill in the hole(s), use a mechanical compactor to grade pavement to conform with the design template.  This work will be incidental to Item 606(1).

- Set wood or steel posts in dug, drilled, or pre-punched holes.  Backfill and compact around posts with acceptable material, to firmly support the post laterally and vertically.  Compact under and around posts to the Engineer’s satisfaction.

Steel posts may also be set by ramming or driving if:

a.	The embankment aggregate is no larger than six inch; and

- Posts are not damaged during installation.

- In solid rock or in broken rock embankment, construct holes for posts, no ramming or driving in the rock will be allowed.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL.  Add the following:  Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within seven (7) calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.  (10/17/02)R45aUSC

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL.  Delete the last sentence and substitute the following:  Notify the Engineer a minimum of five (5) days prior to removing guardrail for disposal.  The Engineer will notify ADOT&PF M&O (907-338-1466) and have an M&O representative physically identify portions of guardrail to be salvaged.  Protect all items from damage during salvage and delivery.  Deliver all guardrail and associated hardware designated to be salvaged to the ADOT&PF Maintenance Yard located on Inner Springer Loop in Palmer.  Replace any items damaged by the Contractor at no additional cost to the Department.  All remaining items removed become the Contractor’s property.  (06/12/03)R259M98

Add the following Subsections:

606-3.09 FLEXIBLE MARKERS.  For each end terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking all proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine that additional guardrail is necessary and you shall comply without delay.  (10/17/02)R45aUSC

606-3.11 EXISTING GUARDRAIL.  After paving is complete, the Contractor shall measure the existing guardrail heights in the presence of the Engineer to verify if they are between 24 to 30 inches, measuring from the top of the rail to the finished shoulder surface below the rail.  The Contractor shall remove and replace the existing guardrail that does not meet the height requirement with new guardrail.

Existing guardrail that is damaged shall be removed and replaced with new guardrail.  The Contractor shall mark the damaged guardrail for the Engineer’s approval prior to removal and replacement.  The Contractor shall also remove and replace the existing guardrail the Engineer identifies as damaged.

606-5.01 BASIS OF PAYMENT.  Add the following:  No separate payment will be made for identifying damaged guardrail, or measuring guardrail height.  ***DELETED***  The work will be subsidiary to Item 606(1), W-Beam Guardrail.

--

-

-

SECTION 611

RIPRAP

# Special Provisions

611-5.01 BASIS OF PAYMENT.  Add the following:

No separate payment for furnishing and installing the geotextile, Erosion Control, Class I for the riprap downdrain will be made.  This work will be subsidiary to Item 611(2B), Riprap Class II.

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS.  Under item 1. delete the first sentence and substitute the following:  Unless Shop Drawings have been provided in the Contract, submit shop drawings for all signs requiring the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

The Contractor shall not order warning signs until curve advisory speeds have been field tested.

615-3.01 CONSTRUCTION REQUIREMENTS.  Under item 6. add the following:  Replace sign post, sign post base, and foundation as approved by the Engineer.

Delete the sixth sentence of the first paragraph of item 7 and substitute the following:

Deliver sign panels, posts, and hardware to the ADOT&PF Maintenance Yard located on Inner Springer Loop in Palmer.

615-3.02 SIGN PLACEMENT AND INSTALLATION.  Add the following:  Do not remove existing signs without authorization from the Engineer.  (11/06/02)R50USC02

615-4.01 METHOD OF MEASUREMENT.  Under “Standard Signs and Object Markers.” in fourth sentence delete:  “Actual areas for signs will be measured, except” and capitalize the remaining portion: “Octagons and round signs will be measured as rectangles.”  (07/03/03)E04

615-5.01 BASIS OF PAYMENT.  Delete the first sentence and substitute the following:  Sign posts, bases, mounting hardware, and concrete used for sign bases are subsidiary.

No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in Subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.  (11/06/02)R50USC02

-

-

-

SECTION 618

# SEEDING

# Special Provisions

618-1.01 DESCRIPTION.  Add the following:  Seed all new or disturbed slopes and any other areas directed by the Engineer.  Track the soil and apply seed, mulch, fertilizer, and water.  Provide a living ground cover on all slopes as soon as possible.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Mulch		Subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following:  Apply seed as detailed in Subsection 618-3.03 immediately after the shaping of the slopes.  Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer.  The resultant indentations shall be perpendicular to the fall of the slope.  Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  All seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION.  Add the following:  Apply seed, mulch and fertilizer as follows per acre.  Apply seed and mulch in one application if using the hydraulic method.  Apply all fertilizer with the hydraulic method.

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
| Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

618-4.01 METHOD OF MEASUREMENT.  Add the following:  The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT.  The work described under Subsection 618-3.01, Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(11/06/02)R52USC

SECTION 619

SOIL STABILIZATION

Special Provisions

619-1.01 DESCRIPTION.  Add the following:  This work also includes the furnishing, application and maintenance of jute matting.

619-2.01 MATERIALS.  Add the following:

Jute Matting		Subsection 727-2.02, item 2

619-4.01 METHOD OF MEASUREMENT.  Add the following:  Item 619(2A).  By the square yard measured along the ground for the area designated in the Plans or as directed by the Engineer.

619-5.01 BASIS OF PAYMENT.  Add the following:

Item 619(2A).  At the contract unit price for the area accepted by the Engineer.

Add the following pay item:

| Pay Item | Pay Unit |
| --- | --- |
| 619(2A) Jute Matting | Square Yard |

SECTION 619

SOIL STABILIZATION

Payment will be made under:

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

# Special Provisions

639-1.01 DESCRIPTION.  Construct residential, commercial, or public approaches at the locations shown in the Plans.

639-2.01 MATERIALS.  Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION.  Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed as shown on the Plans or as directed.  Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule.  The contract unit price for driveways and approaches shall be full compensation for furnishing equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.  (05/09/02)R58M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 639(6) Approach | Each |

Delete this Section in its entirety and substitute the following:

SECTION 641

# EROSION, SEDIMENT, AND POLLUTION CONTROL

Standard Modification

641-1.01 DESCRIPTION.  Plan, provide, inspect, and maintain control of erosion, sedimentation, water pollution, and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices).  A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands.  BMPs include temporary or permanent structural and non-structural devices and practices.  The Department describes common BMPs in its Alaska Storm Water Pollution Prevention Plan Guide, October 2003.

- ESCP (Erosion and Sediment Control Plan).  The general plan for control of project-related erosion and sedimentation.  The ESCP normally consists of a general narrative and a map or site plan.  It is developed by the Department and included in the project plans and specifications.  It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization.  A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional.  The stabilized site is protected from erosive forces of raindrop impact and water flow.  Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70 percent cover density) or equivalent permanent stabilization measures such as riprap, gabions, or geotextiles.

- HMCP (Hazardous Material Control Plan).  The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI.  Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.  Use EPA Form 3510-9 (Revised 6/03).

- NOT.  Notice of Termination of coverage under the NPDES General Permit.  Use EPA Form 3510-13 (Revised 6/03).

- NPDES General Permit.  The Storm Water General Permit for Large and Small Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES).  It requires an approved SWPPP and NOIs listed as active status by the EPA prior to ground-disturbing activities for the project.

- SPCC Plan (Spill Prevention, Control, and Countermeasure) Plan.  The Contractor’s detailed plan for oil spill prevention and control measures, that meets the requirements of 40 CFR 112.

- SWPPP (Storm Water Pollution Prevention Plan).  The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit.  The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project.  The approved SWPPP must contain a copy of the Contractor’s signed NOI.

641-1.03 SUBMITTALS.  For all projects that disturb one acre or more of ground submit three copies each of your SWPPP and HMCP to the Engineer for approval.  Submit one copy of your SPCC Plan (if required under Subsection 641-2.03) to the Engineer.  Sign all submittals.  Deliver these documents to the Engineer no less than five calendar days prior to the preconstruction conference.

The Department will review the SWPPP and HMCP submittals within 14 calendar days.  Submittals will be returned to you as either requiring modification unless approved by the Department.  Besides a copy of the Contractor’s NOI, the approved SWPPP must contain a certification and be signed by an authorized representative according to the Standard Permit Conditions of the NPDES General Permit Part 8, Appendix G.  You must receive written notification from the Department that your SWPPP has been approved before you submit your original NOI to EPA.  NOIs can be submitted by Certified mail or through EPA’s electronic NOI system (eNOI).

For regular U.S. Mail delivery:			For Overnight/Express mail delivery:

EPA Storm Water Notice Processing Center		EPA Storm Water Notice Processing Center

Mail Code 4203M		Room 7420

U.S. EPA		U.S. EPA

1200 Pennsylvania Avenue, NW		1201 Constitutional Avenue, NW

Washington, D.C.  20460		Washington, D.C.  20004

For electronic mail, the Contractor must register online with EPA at:  http://cfpub.epa.gov/npdes/stormwater/enoi.cfm.  This website has instructions and guidance on how to set up and use the eNOI system.

Whether submitting the NOI electronically or by mail, you may not begin ground-disturbing activities until the Engineer has issued you a written statement that the EPA has listed your NOI and the Department’s NOI as active.

The Department will submit the approved SWPPP to ADEC that will clued both the Contractor and Department NOIs.

The active status NOIs, approved SWPPP, approved HMCP, and submitted SPCC Plan (when required) become the basis of the work required for the project’s erosion, sediment, and pollution control.

Once the Department has determined the site has achieved final stabilization, the Engineer will provide written notification to you that your NOT may be submitted to EPA with a copy to the Engineer.  The Department will transmit the Department’s NOT to the EPA.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  For projects that disturb one acre or more of ground, you must prepare a Storm Water Pollution Prevention Plan.  Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMPs.  Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, October 2003.  The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private.  The plan must also incorporate all the requirements of the project permits.

Have the SWPPP prepared under the direction of and sealed by a professional engineer currently registered in the State of Alaska. Include all requirements of the NPDES General Permit.

Specify the line of authority and designate your field representative for implementing SWPPP compliance.  Designate one representative for each subcontractor who performs earth-disturbing activities or who install and maintain erosion and sediment control measures.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances.  (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities.  Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where storage, fueling, and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of oil, petroleum products, and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by accidental spills.  Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE (SPCC) PLAN REQUIREMENTS.  Prepare and implement a SPCC Plan that is certified by a licensed Professional Engineer, when required by 40 CFR 112, including:

- When oil spills may reach navigable waters; and

- Your total above ground oil storage capacity is greater than 1,320 gallons.

Comply with 40 CFR 112 and address the following issues in your SPCC Plan:

- Operating procedures that prevent oil spills;

- Control measures installed to prevent a spill from reaching navigable waters; and

- Countermeasures to contain, clean up, and mitigate the effects of an oil spill.

641-3.01 CONSTRUCTION REQUIREMENTS.  Do not begin ground-disturbing work until the Engineer provides you written notice that both your and the Department’s NOIs have been listed as active and that ground-disturbing work can begin.and DEC

Post at the construction site:

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	Name and phone number of your local contact person, and

3.	Location of a SWPPP available for viewing by the public.

Comply with all requirements of the approved HMCP, the submitted SPCC Plan, and all state and federal regulations that pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms.  Perform all fueling operations in a safe and environmentally responsible manner.  Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.  Report oil spills as required by federal, state and local law, and as described in your SPCC Plan.

Comply with all requirements of the NPDES General Permit, implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.  Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections.  Prior to start of construction, conduct a joint on-site inspection with the Engineer and the Contractor’s field representative to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

a.	During construction, inspect the following at least once every seven days and within 24 hours of the end of a storm exceeding 1/2 inch in 24 hours (as recorded at or near the project site):

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections.  During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 1/2 inch or greater.  The Engineer may waive monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports.  Prepare and submit, within three working days of each inspection, a report on state Form 25D-100, with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) of personnel making the inspection.

c.	The date of the inspection.

d.	Observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

f.	Incidents of non-compliance.

Where a report does not identify any incidents of non-compliance, certify that the facility is in compliance with the SWPPP and NPDES General Permit.  You and the Engineer will sign the report according to the Standard Permit Conditions of the NPDES General Permit, Part 8, Appendix G.  Include all reports as an appendix to the SWPPP.

Retain copies of the SWPPP and all other records required by the NPDES General Permit, for at least three years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP to correct problems identified as a result of any:

1.	Storm or other circumstance that threatens water quality, and

2.	Inspection that identifies existing or potential problems.

Submit SWPPP amendments to the Engineer within seven days following the storm or inspection.  Detail additional emergency measures required and taken, to include additional or modified measures.  If modifications to existing measures are necessary, complete implementation within seven days.

Stabilize all areas disturbed after the seeding deadline within seven days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT to EPA and a copy to the Engineer:

1.	When the Engineer has acknowledged to you in written form that the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

2.	When the construction activity operator (as defined in the NPDES General Permit) has changed and the Engineer provides written notification that your responsibilities with respect to compliance with the NPDES GP on the project have ceased.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

- Pursue work required by the approved SWPPP,

- Respond to inspection recommendations and/or deficiencies in the SWPPP, or

- Implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Items 641(2) and (4) will be measured as specified in the contract or directive authorizing the work.

641-5.01 BASIS OF PAYMENT.  The Bid Schedule will include either Items 641(1) and (2) or Items 641(1), (3), and (4).

1.	Item 641(1) Erosion and Pollution Control Administration.  At the contract lump sum price for administration of all work under this Section.  Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting, and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control.  At the prices specified in the contract to install and maintain temporary erosion, sedimentation, and pollution control measures.

3.	Item 641(3) Temporary Erosion and Pollution Control.  At the lump sum price shown on the bid schedule to install and maintain all temporary erosion, sedimentation, and pollution control measures under the original approved SWPPP and HMCP.

4.	Item 641(4) Temporary Erosion and Pollution Control Amendments.  At the prices specified in the directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures.  All work paid under this item will be shown as amendments to the original approved SWPPP or HMCP.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.  (02/19/04)E09

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 641(1) Erosion and Pollution Control Administration | Lump Sum |
| 641(2) Temporary Erosion and Pollution Control | Contingent Sum |
| 641(3) Temporary Erosion and Pollution Control | Lump Sum |
| 641(4) Temporary Erosion and Pollution Control Amendments | Contingent Sum |

-

-

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

#### Special Provisions

642-3.01 GENERAL.  Add the following after item 10:  Prior to any work on the project, stake and reference the construction centerline.  Reference the existing centerline at 100 foot on tangents and 50-foot intervals on curves from the beginning and ending of superelevation changes when the roadway is no longer at normal crown.  Also stake the beginning and ending of tapers of the edge of pavement.  The reference stake shall be a minimum of 1 inch by 2 inch by 2 feet and be offset 4 to 8 feet from the shoulder on the right side of the roadway.  They shall show the offset distance to centerline and the station from the beginning of the project.  Ensure the stakes are visible from the roadway by clearing as necessary.  Maintain staking until the final roadway striping is completed.

Install a reference sign every 500 feet.  These reference signs shall meet the following requirements:

1.	mounted a minimum of 5 feet above the shoulder,

2.	located a minimum of 10 feet from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 6 inch high black lettering on an orange background.

Compute design centerline profile to best fit the existing centerline profile and exiting guardrail requirements detailed in Subsection 606-3.11.  Prepare existing top of pavement cross-sections for horizontal curves and transitions with design superelevated pavement plotted on each section.  The Engineer may require adjustments to the roadway grades.  This shall not be considered extra work.  Provide this profile information to the Engineer (electronically in Excel format) immediately upon its completion, along with checked computations on all level loops, but in no case later than seven (7) calendar days before slope staking or blue topping.

11.	Measure and document the actual intersection sight distance triangles at all public intersections and driveways.  Measure this after all paving, guardrail, and other work affecting intersection sight distance has been completed.  List the actual sight distance available up to 650 feet.  Note locations with greater than 650 feet of sight distance as “650’+”.  Measure sight distance triangles as shown in the following figure by setting up an instrument at the driver’s eye location.  Provide the results in a table format as shown.  Include remarks in a “notes” column, relating any minor obstacles or observations which may assist in improving sight distance.  Certify and record the results on standard “letter” sized paper and provide two copies to the Engineer at least two (2) weeks prior to submitting shop drawings for permanent signing.  The Engineer will forward one (1) copy to the Regional Traffic Engineer.  The Regional Traffic Engineer’s office will take up to two (2) weeks to review and require any additional warning signs for intersections or driveways as needed.  (02/18/04)R269USC

# Intersection Sight Distance Survey Table

ROAD NAME:___________________________________________________

Stationing 	FROM:______________________________	DATE:_____________

TO:	_________________________________	Surveyor:____________________

| Public Approach or Estimated Driveway Station | Posted Speed Limit (Main Rd) | Sight Distance Back (Left) | Sight Distance Ahead (Right) | Remarks |
| --- | --- | --- | --- | --- |

Other Notes:

1.

2.

3.

Accepted By: _____________________________________________Date:    ______________

DOT/PF Project Engineer

Intersection Warning Signing

Review Checked By:_______________________________________ Date:   _______________

DOT/PF Regional Traffic Engineer

12.	Measure and document available passing sight distance along the roadway in both directions of travel.  Measure this after all paving, guardrail, and other work affecting intersection sight distance has been completed.  Use Table 642-1 to establish Minimum Passing Sight Distance.  Move forward alongside the centerline or edge of traveled way in order to spot check and discover locations where the Minimum Passing Sight Distance drops below what is required for 10 MPH over the posted speed limit.  Record the sight distance for each station location which falls below the posted speed limit plus 10 MPH.  Continue to record the sight distance for each station location until the sight distance drops below what is required for the posted speed limit.  Stations observed to exceed the values required for posted speed limit plus 10 MPH should be marked as “Pass” or “+”.  Stations observed to fall below the values required for the posted speed limit should be marked as “Fail” or “-”.

Measure on the roadway centerline, using a 3.5-foot object height (or “instrument height”) at 100-foot station marks looking ahead as far as possible towards a 3.5-foot target height.  Provide a list of each station result for each direction of travel along the centerline.  Certify and record the results on standard “letter” sized paper and provide two (2) copies to the Engineer at least two (2) weeks prior to laying out final pavement markings.

The Engineer will forward one (1) copy to the Regional Traffic Engineer.  Table 642-1 does not automatically ensure passing striping will be provided.  The Regional Traffic Engineer’s office will take up to two (2) weeks to review and approve pass/no-pass striping against operating speeds for the roadway prior to installation, using Table 642-1 and the Alaska Traffic Manual as a guide.  No-pass striping zones shall be at least 500 feet in length.  Passing striping shall be long enough to meet the distances in Table 642-1.  Passing striping will not extend into a segment of road without minimum sight distance.  (02/18/04)R61USC02

TABLE 642-1

PASSING SIGHT DISTANCE

| Operating Speed (mph) | Minimum Passing Sight Distance (ft) |
| --- | --- |
| 15 | 220 |
| 20 | 295 |
| 25 | 365 |
| 30 | 440 |
| 35 | 515 |
| 40 | 585 |
| 45 | 660 |
| 50 | 735 |
| 55 | 805 |
| 60 | 880 |
| 65 | 955 |

Passing Sight Distance Survey Table

ROAD NAME:___________________________________________________

Stationing 	FROM:______________________________	DATE:_____________

TO:	_________________________________	Surveyor:____________________

| Project Station | Posted Speed Limit | Direction of Travel | Sight Distance Ahead | Remarks |
| --- | --- | --- | --- | --- |

Other Notes:

1.

2.

3.

Accepted By: _____________________________________________Date:    ______________

DOT/PF Project Engineer

Passing Sight Distance

Review Checked By:_______________________________________Date:    _______________

DOT/PF Regional Traffic Engineer

642-3.03 MONUMENTS.  Delete the second sentence of the first paragraph and substitute the following:  Reference property markers/corners, monuments or accessories which may be disturbed or buried during construction.  Prepare and record Monument Record Forms in the appropriate Recorder’s Office before disturbing monuments.  Monument Record Forms may be obtained from the Engineer.  Reestablish monuments in their original position before the completion of the Project. Then, prepare and file a Monument Record Form for each reestablished monument.

642-4.01 METHOD OF MEASUREMENT.  Add the following:  Clearing required for stake visibility shall not be measured.  Maintenance of stakes will not be measured.

Item 642(15)  Intersection Sight Distance Measurement.  By each intersection measured, only after the certified and recorded results have been accepted by the Engineer.

Item 642(16)  Passing Sight Distance Measurement.  By the number of stations on the project measured separately along centerline, once for each direction, only after the certified and recorded results have been accepted by the Engineer.

642-5.01 BASIS OF PAYMENT.  Add the following after the first paragraph:  Where the bid item for Reference Existing Monument does not appear in the bid schedule, work necessary to reference existing monuments and prepare and file Monument Record Forms is subsidiary to Item 642(1) Construction Surveying.  Five (5) percent of the contract lump sum bid price for Item 642(1) will be withheld until the Monument Record Forms are prepared and recorded in the local Recorder’s Office.  Where the bid item for Reference Existing Monument does appear in the bid schedule, work associated with preparing and recording the Monument Record Forms is subsidiary to Item 642(9) Reference Existing Monument.  Payment will not be processed payment of Item 642(9) until the Monument Record Forms are prepared and recorded in the local Recorder’s Office.

Clearing required for stake visibility is subsidiary to Item 642(1) and no separate payment shall be made.

Add the following pay items:

R

| PAY ITEM | PAY UNIT |
| --- | --- |
| 642(15) Intersection Sight Distance Measurement | Each |
| 642(16) Passing Sight Distance Measurement | Station |

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following:  The Contractor may request a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project in writing.  If the waiver is approved, all movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan.  Maintain a minimum12 foot lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.  (07/02/03)R222USC02

Standard Modification

643–1.04 WORKSITE TRAFFIC SUPERVISOR.  Item 1. Qualifications, delete the last paragraph and replace it with the following:

Renew certification no less frequently than every four (4) years, and be able to show their certification anytime they are on the project.

Delete item 2.b. and replace it with the following:

b.	Physically inspect the condition and position of all traffic control devices used on the project at least once each day and once each night.  Ensure that traffic control devices work properly, are clean and visible, and conform to the approved TCP.  Complete and sign a detailed written report of each inspection on the form provided by the Engineer within 24 hours.

Delete item 2.h. and replace it with the following:

h.	Certify that all flaggers are certified as required by Subsection 643-3.04.4.  Submit a copy of all flagger certifications to the Engineer.  (07/03/03)E06

643-2.01 MATERIALS.  Add the following:

Add the following:

17.	Flexible Markers.  Refer to Subsection 606-2.01, Materials.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Add the following:  Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as you, an employee, or a subcontractor becomes aware of the accident.  (02/05/04)E10

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following: The Contractor may maintain traffic on a continuous gravel surface for four (4) miles or as directed by the Engineer.

643-3.04 TRAFFIC CONTROL DEVICES.  Delete the sixth paragraph and replace it with the following:

Use only traffic control devices that meet the requirements of the “Acceptable” category in ATTSA “Quality Standards for Work Zone Traffic Control Devices”.

Item 4. Flagging, delete the fourth paragraph and replace it with the following:

Renew flagger training and certification no less frequently than every four (4) years.  Flaggers must be able to show their flagger certification anytime they are on the project.

(07/03/03)E06

Special Provisions

Delete the first sentence of the eighth paragraph and substitute the following:  All items paid under this Section remain your property unless stated otherwise.

Add the following to 1. Embankments.:  Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.:  Remove all obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest ADOT &PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER.  Add the following after the second sentence:  In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following:  Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices.  The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public.  Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING.  Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

  - Monday through Friday from 0600 to 0800.

  - Monday through Thursday from 1630 to 1830.

  - Friday from 1630 to 2000.

  - Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

5.	During the Alaska State Fair (August 26, 2004 – September 6, 2004)

Lane restrictions, if allowed shall be conducted so that no more than a 5-minute accumulated stopped delay, 20 vehicles, or 1/8 mile (660 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 10-minute stopped delay, 40 vehicles, or 1/4 mile (1,320 feet) of traffic detained, will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following:  Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer.

643-3.11. HIGH VISIBILITY CLOTHING.  Ensure all workers within project limits wear an outer visible surface or layer that complies with the following requirements:

1.	Tops.  Wear fluorescent vests, jackets, or coverall tops conforming to Class 2 at all times.  Class 2 requires at least 775 square inches of conforming fluorescent red-orange background material and at least 201 square inches of conforming retroreflective striping.  Retroreflective striping shall be fluorescent yellow-green combined-performance material.

The vest, jacket, or coverall top shall have two over the shoulder combined-performance retroreflective stripes, and at least one 360-degree horizontal combined-performance retroreflective stripe around the torso.  Jackets and coverall tops shall have two horizontal combined-performance retroreflective bands on each sleeve; one above and one below the elbow.

2.	Bottoms.  Wear fluorescent red-orange Class E pants or coverall bottoms during nighttime work (sunset to sunrise).  Flaggers shall wear fluorescent red-orange Class E pants or Class E coverall bottoms at all times.  Furnish each garment with two 2-inch wide combined-performance fluorescent yellow-green retroreflective horizontal stripes on each leg.

3.	Raingear.  Raingear tops and bottoms, when worn as the outer visible surface or layer, shall conform to the requirements listed above in (1) Tops and (2) Bottoms.

- Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility clothing.

- Standard.  All high visibility garments shall conform to the requirements of ANSI 107-1999 as well as this specification.  Class 2 and Class E garment requirements are defined in that standard. All retroreflective material must also qualify as combined-performance fluorescent material.

- Labeling.  All garments shall be labeled in conformance with Section 10.2 of ANSI-107-1999.

- Condition.  Furnish and maintain all vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place a temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.  (07/02/03)R222USC02

643-4.01 METHOD OF MEASUREMENT.  Add the following:

Payment for high visibility clothing for workers is subsidiary to other items.  (12/02/03)E07

No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT.  Add the following:  The Engineer does not require a change order/directive for Item 643(25), Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $2.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Foot Foot Each Each | $0.30 $0.65 $0.75 $40.00 |

The Engineer will pay for Item 643(15), Flagging on a contingent sum basis at the rate of $36/hour.  The Engineer does not require a change order/directive for the flagging pay item.  Flagging associated with Change Order work will be paid at the prices agreed to in the Change Order, or on a time and materials basis in accordance with Subsection 109-1.05.  (07/02/03)R222USC02

Delete Item 643(15) and substitute the following:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15) Flagging | Contingent Sum |

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

#### Special Provisions

644-2.01 FIELD OFFICE.  Delete this Subsection in its entirety and substitute the following:  Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 600 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 40 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Four (4) telephone service lines available at the office location.

8.	If a part of your building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY.  Delete sub-item g and substitute the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

- Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

(11/19/02)R63USC

644-2.05 VEHICLES.  Delete the second  and third paragraphs and substitute the following:  Furnish three (3) full-size four-wheel drive pickups and one (1) sport utility vehicle for exclusive use of the Department throughout the project.  Provide vehicles less than 3 model years old, in good condition and with less than 36,000 miles on the odometer.

Furnish all fuels, maintenance and insurance.  If you are working after October 1, provide studded snow tires for all vehicles you provide for the Department’s use.  Equip vehicles used by the Department with CB radios and yellow lightbars wired into the vehicle’s electrical system with a dash mounted switch easily accessible to the vehicle operator.  Provide Code 3; Model 6005H (formerly PE 6200 LE) lightbars, or approved equal.  Approved equals shall have the following characteristics:

- Four (4) 55 watt rotators with amber filters

- 1200 flashes per minute

- Two diamond mirrors

- 55” in length

The Contractor is responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use.  The Department is responsible for damage to any vehicle caused by its own negligent during operation.

644-3.01 METHOD OF MEASUREMENT.  Delete the third paragraph and substitute the following:

Vehicle.  Per each vehicle provided.  If a replacement vehicle is necessary, no additional measurement will be made.  (02/03/03)R245USC

Delete Item 644(7) and substitute the following:

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 644(7) Vehicle | Each |

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Delete this Subsection in its entirety and replace with the following:  Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer fourteen (14) days to review the initial CPM Schedule.  If revisions are required, make them promptly.  The finalized CPM Schedule must be completed and accepted prior to commencement of any work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete item 2.  60-Day Preliminary Schedule.

Delete the first sentence of item 3.  Schedule Updates.  and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly, or as deemed necessary by the Engineer.  (12/13/02)R261M98

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

## Special Provisions

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors, and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and your operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to your supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for your responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL.  Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  All personnel furnished by you shall be, and shall remain during the work hereunder, employees solely of you.

Furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by you and involved in the performance of the work.  Also, furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS.  The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by your representative at the end of each shift, and a copy will be provided to your representative.

647-4.01 METHOD OF MEASUREMENT.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT.  Payment for Item 647(1) will be paid on a contingent sum basis at the rate of $125/hour.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher horsepower than specified will not entitle you to any extra compensation.  (11/12/98)R15USC

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 647(1) Wide Pad Dozer, 65-HP Minimum | Contingent Sum |

--

-

--

-

-

-

--

-

-

-

-

-

-

-

-

--

-----

--

---

------

-------

-------

-

-

-








-

-

--

---

----

---

-

-

--

-

-----

-

-

-

-

-

-

--

--

-

-

--

-

--

-

-

-

-

---

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS.

4.	Methyl Methacrylate Pavement Markings.

a.	General.  Add the following:

(1)	The Contractor shall have no affiliation with the manufacturer’s representative.

(2)	Install pavement markings using only striping installers certified by the manufacturer of the marking material for the specific striping material and application method.  Submit these certifications fifteen (15) days before beginning work.

(3)	Install pavement markings using equipment certified by the marking material manufacturer that is designed and capable of properly mixing at the point and time of application.  Submit these certifications fifteen (15) days before beginning work.

(4)	Waste material becomes the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store stripe removal wastes material or asphalt grindings on State property.  Dispose of waste material according to applicable State, Federal, and local regulations.

b.	Preparation.  Delete the last sentence and substitute the following:  Apply first pass markings seven (7) days after the final lift of pavement has been installed.  Apply the final pass a minimum of thirty (30) days after the initial pass or as directed by the Engineer.

c.	Application.  Delete the first paragraph and substitute the following:  Match the new skip stripes to the existing marking pattern on at least one end of the project.  Monitor the bead application to ensure proper bead embedment and density.  In spray applications ensure sinker beads uniformly penetrate the full thickness of the marking.  Apply marking material by one or more of the following methods, appropriate to the pay item(s) in the bid schedule.  Apply markings at the thickness specified uniformly across their width and along their length.  At least two passes of equal thickness are required to obtain the thickness specified.  Place additional passes squarely on top of the first pass, within ± 1/16 inch laterally and ± 3 inches longitudinally.  The thickness specified is the minimum.

Add the following sub-items:

- Longitudinal Extruded Markings.  Apply with certified extrusion equipment.  Uniformly apply top coat of beads with a mechanical dispenser.

- Longitudinal Inlaid Protected Markings.  Apply with certified extrusion equipment.  Grind the slot to the correct depth, and in proper alignment, using a diamond edged grinder capable of grinding the slot to the specified depth and width in a single pass.  After grinding, obtain approval before placing marking material.  Fill the slot edge-to-edge, making the line flat or slightly convex on top and to the specified width.  Uniformly apply top coat of beads with a mechanical dispenser.  The material depth shall be measured from the peaks created by the groves to the visible surface of the markings.

- Transverse Markings.  Apply markings as shown on the Plans.  Apply with certified spray or extrusion equipment.  Apply sinker beads as specified at a minimum drop rate of 1 lb/yd2.

- Legends Only/Arrows.  Apply with certified spray equipment.  Apply sinker beads as specified at a minimum drop rate of 1 lb/yd2.

d.	Sampling.  Delete in its entirety and substitute the following:  Record the following readings, and the locations where taken, and submit to the Engineer within 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

For inlay applications, record the depth of the slot every 300 feet during the grinding operation.

For other longitudinal applications, measure the thickness of the lines (above the pavement surface), at the time of application, every 300 feet.

Inspect the line initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 60 mils.

METHYL METHACRYLATE PAVEMENT MARKING

#### YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 | Inlaid Markings2 |
| --- | --- | --- |
| ##### Longitudinal Type3 ##### (Center and Edge lines) | 90 mils | 60 mils |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 120 mils | 60 mils |
| Neutral Area (Diagonals, Chevrons) | 60 mils | Do not inlay these markings |

1.	Measure Type V spray without glass beads.  Tolerance is ±4 mils.  Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 6-inch by 12-inch flat sheet of 80 mils thick aluminum placed in the path of the striping guns.

2.	Cut the inlaid slots to a depth of 250 mils.  Do not over fill the slots.

3.	Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 60 mils per application pass.

Non-Inlaid Markings

New asphalt pavement:  Apply interim non-inlaid Longitudinal and Transverse Type markings at 30 mils.

Apply the final Transverse and Neutral Area markings as shown in the application table.  Multiple application passes are required for Transverse Type markings.

Existing asphalt pavement:  Apply markings according to the Yield Thickness Table.  Longitudinal Type markings will require multiple application passes.

670-3.04 PAVEMENT MARKING REMOVAL.  Replace the first sentence of the second paragraph with the following:  Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement.  Painting over existing striping does not meet the removal requirement.  Do not use any method utilizing burning with an open flame for removing pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING.  Delete this Subsection in its entirety and replace with the following:

- Length of Stripe.  ± 2 inches

- Width of Stripe.  + 1/4 inch, - 1/16 inch

- Lane Width. ± 4 inches from the width shown in the Plans.

- Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

- Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

- Stripes.  Keep the center of the stripe within 4 inches from the planed alignment.

- Double Stripes.  ± 1/4 inch

- Thickness.  Minimum specified to a maximum of + 15 mils.

- Depth of Inlay Slot.  Minimum specified to a maximum of – 40 mils.

- Thickness of Protected Inlaid Marking Material.  Minimum specified to a maximum of + 40 mils.

If it is determined that the material is being placed too thin, or otherwise not to specification, make immediate adjustments to correct the problem.

Durable pavement markings applied by any method will be unacceptable if:

- The marking is not straight or wide enough.

- The thickness of the line is not uniform or less than specified.

- The top of the line is not smooth and uniform.

- The material is uncured.

- The material blackens or is inconsistent in color.

- The inlay slot is not ground to the specified depth.

- The inlay slot is not filled to the specified depth.

- The edge of the markings are not clear-cut and free from overspray.

- The reflective elements are not properly embedded.

- The markings exhibit poor adhesion.

- The retro-reflectivity of the markings is less than specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch-work” manner.  If more than one repair is required in a single 300 foot section, grind and repair the entire section.

-

SECTION 703

AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE.  Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 |  |  |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

(02/28/00)R117USC

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.14 PREFORMED PAVEMENT MARKINGS.  Add the following to paragraph Aa. under item 1., General Requirements:  The preformed ribbon shall consist of one solid piece of required width and length.  In solid stripe areas, the tape length shall, where possible, be a minimum of 100 feet.  (07/15/96)R79MUSC

Add the following Subsection:

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.

2.	Performance Properties:  Add the following:

k.	Adhesion:	To Portland Cement, minimum 2000 psi, to asphalt, dependent on tensile failure of the substrate.  (12/04/02)R246

SECTION 724

# SEED

# Special Provisions

724-2.02  MATERIALS.  Delete Table 724-1 and substitute the following:

TABLE 724-1

Seed Requirements

| SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(11/06/02)R52USC

SECTION 727

SOIL STABILIZATION MATERIAL

# Special Provisions

727-2.01 MULCH.  Delete numbered item 1. in its entirety and substitute the following:

1.	Virgin/Recycled Wood Fiber, Recycled Paper (“wood cellulose”) Mulch, or a Blend of Virgin/Recycled Wood Fiber with Recycled Paper Mulch.  Blended mulch may contain up to 50 percent recycled paper.  The mulch shall meet the following requirements:

a.	Contains no growth or germination inhibiting factors.

b.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form homogeneous slurry.

c.	Mulch can be applied uniformly on the soil surface.

d.	Will not create a hard crust upon drying and have moisture absorption and retention properties and the ability to hold grass seed in contact with the soil.

e.	Dyed a suitable color to facilitate inspection of its placement.

Ship the mulch material in packages of uniform weight (plus or minus 5 percent) and bear the name of the manufacturer and the air-dry weight content.

Use a commercial tackifier on all areas steeper than 3:1.  Use the amount recommended by the manufacturer.  (08/19/99)R206M98

SECTION 730

SIGN MATERIALS

# Special Provisions

730-2.04 SIGN POSTS.  Under item 1., Metal Pipe Posts, add the following to paragraph a.:  Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following items:

6.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch-thick walls.  0.4-inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized in accordance with 1.b. of this Subsection.  Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this Subsection.

7.	Square Non-Perforated Steel Tubes.

a.	Fabricate from 3/16-inch thick cold-rolled carbon steel sheets, commercial quality, to meet ASTM A 500, Grade B.  Form posts into a steel tube, roll to size, and weld in the corner.  Furnish with 7/16-inch diameter holes drilled or punched as necessary to permit mounting of the sign.

b.	Hot dip galvanize to meet AASHTO M 111 after fabrication.  When cutting metal posts after hot dip galvanizing, minimize damage to the zinc coating and protect all exposed surfaces by treating the exposed area.

c.	Repair galvanized surfaces that are abraded or damaged at any time after the application of the zinc coating to meet the applicable provisions of AASHTO M 36.

(08/04/03)R81USC

-

APPENDIX A

EROSION AND SEDIMENT CONTROL PLAN

AND

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST

APPENDIX D

ENSTAR’s SAFETY REQUIREMENTS

FOR EXCAVATION ADJACENT TO NATURAL GAS PIPELINES

APPENDIX E

CUSTOM SIGN SHOP DRAWINGS