ESCROW OF PROPOSAL DOCUMENTATION AFFIDAVIT

THE UNDERSIGNED HEREBY CERTIFIES THAT THE ESCROW OF PROPOSAL DOCUMENTATION CONTAINS ALL OF THE INFORMATION THAT WAS USED TO DEVELOP THE PROPOSAL AND THAT I HAVE PERSONALLY EXAMINED THESE CONTENTS AND THAT THE DOCUMENTATION IS CORRECT AND COMPLETE IN ACCORDANCE WITH SUBSECTION 102-1.17. SUBMITTAL BY THE CONTRACTOR OF A CLAIM, WHICH IS NOT CONSISTENT WITH THE CONTENTS OF THESE PROPOSAL PREPARATION DOCUMENTS, SHALL RESULT IN DENIAL OF THE CLAIM.

By:

Title:

Firm:

Date of Submission:

Project Number:

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004 STANDARD SPECIFICATIONS

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	Cross Sections

c.	State of Alaska Department of Transportation and Public Facilities publication, Alaska Storm Water Pollution Prevention Plan Guide.

d.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

e.	Standard Specifications for Highway Construction 2004. ($25.00)

f.	Alaska Test Methods Manual (Lab & Field), 2004 Edition. ($25.00)

2.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

3.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

4.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for the Contractor to determine which materials will require submittal to the project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority. 7.

5.	The Laborers’ Mechanics’ Minimum Rate of Pay contains information on remote sites and per diem.  The department of Labor has issued WHPL #197, which further clarifies this requirement.  See pay item 640(4).

6.	Based on guidance from the US Department of Transportation’s General Counsel, effective January 10, 2006 the Alaska Department of Transportation and Public Facilities implemented a Race Neutral Disadvantaged Business Enterprise (DBE) program by setting 0% project goals on all highway, mass transit and airport projects.  All forms and reports required under the existing DBE program will continue to be required under these 0% goal contracts.

Specifically, contractors must continue to report creditable DBE participation/payments on the Monthly Summary of Disadvantaged Business Enterprise Participation Form 25A-336. This will allow the Department to continue to accurately report DBE participation to the Federal Highway Administration, Federal Transit Administration and Federal Aviation Administration.

Contractors must also continue to provide opportunities for DBE firms to participate on highway, mass transit and airport projects as appropriate.  A 0% DBE participation goal does not relieve the contractor of the requirement to provide equal opportunity in subcontracting, supplies or other services offered by DBE firms.

Any questions about this notice may directed to Jon Dunham, Manager of the Civil Rights Office, 907 269 0850, jon_dunham@dot.state.ak.us

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS.  Replace the definitions of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.  E22(1/1/06)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.  Replace the second paragraph with the following:  The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development. E23(1/1/06)

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent. E18(6/30/04)

SECTION 105

## CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Delete the last paragraph of item 2.

Add the following after Item 4. e.:

f.	The Contractor shall bear the responsibility for changes in Contract scheduling that result in conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Add the following: The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar Alaska Native Hospital Anchorage Telephone Utility Alyeska Cable AT&T Alascom, Inc. Chugach Electric Association City of Wasilla DOT Street Lights, State of Alaska Enstar Natural Gas Eyecom TV/Interior Telephone GCI Communications Marathon Oil Matanuska Electric Association Matanuska Telephone Association MFS Technologies, inc. Mukluk Telephone Association Phillips Petroleum PTI

The Contractor shall call the following utilities and agencies directly:

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required before utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the contract and/or

- Under Item 642(3) Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s 2 week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking. (09/01/04)R3

    - LOAD RESTRICTIONS.

Add the following:  Overload and oversize permits are required to transport the prestressed concrete girder sections to the job site.  Routing and other permit requirements are prescribed by the Permit Office, (800) 478-7636 or (907) 345-7750.

Girder hauling methods where one tractor is required to travel backwards are not permitted on public roads or streets.

Overload permits are subject to seasonal load restrictions.

Axle configurations and loads are subject to individual analysis.

Standard Modification

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION.  Modify the first paragraph, Item 4., after: “DOLWD” add: and State Department of Revenue. E19(06/30/04)

Special Provision

105-1.17 CLAIMS. Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap, pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (02/07/05)S 13

Standard Modification

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a. delete text and replace with:  Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4.  When there is insufficient useable excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources.  Replace the first paragraph with the following:  The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

4.	d.	Available Sources.  Replace the second paragraph with the following:  When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

4.	e.	Excluded Material Sources.  Replace the paragraph with the following:  Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material sources or any portion of a material source, at any time after Contract award, that is determined by material testing to be unsuitable for use on the project.  E24(1/1/06)

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: The Contractor shall obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

The Contractor shall provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual, of any site outside the project limits or not previously permitted, impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

The Contractor shall provide a copy to the Engineer, of all permits or clearances received prior to Contractor's use of any site outside the project limits. Additionally, the Contractor shall provide the Engineer a written statement that the Contractor has obtained all necessary permits or clearances. The Contractor shall also provide a written statement to the Engineer listing agencies or offices contacted that responded that required no additional action from the Contractor.

The Contractor shall obtain an Endangered and Threatened Species Clearance from the U.S. Fish and Wildlife Service for sites being used outside the project limits.

The Department has received the following permits on the Contractor’s behalf and are attached in Appendix A.

1.	Alaska Department of Natural Resources Title 41 Fish Habitat Permit, Permit Number FH 05-V-0137.

2.	Kenai Peninsula Borough Conditional Use Permit, Permit Number KRC# 5547.

3.	US Army Corp. of Engineer’s (USACE) permit POA-2005-913-D.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following: If the Contractor requires water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (5/29/02)R7M

Add the following subsections:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program			Section 120

Training Program							Section 645

Federal EEO Bid Conditions						Form 25A301

EEO-1 Certification							Form 25A304

DBE Subcontractable Items						Form 25A324

ADOT&PF Training Program Request				Form 25A310

Training Utilization Report						Form 25A311

Contact Report							Form 25A321A

DBE Utilization Report						Form 25A325C

Summary of Good Faith Effort Documentation			Form 25A332A

Required Contract Provisions, Federal-Aid Contracts		Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(1/22/02)S80

SECTION 108

PROSECUTION AND PROGRESS

Special Provision

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1. A progress schedule.  and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple-shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.  (12/13/02)R261M98

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3, Equipment, part a. Hourly Rental Rates add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (2/24/05)R14

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. Upon receipt of current schedules, from the Contractor, the Engineer will release this retainage. (09/05/01)R137

Standard Modification

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of subsection 105-1.16. E11(06/30/04)

Special Provision

Add the following section:

## SECTION 120

## DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The Engineer makes the determination of CUF after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the Department reduces the quantity of work of a bid item involving a DBE firm, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If the Engineer approves a DBE replacement, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- The bidder may reject non-competitive DBE quotes. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The DBE Liaison Officer will make the decision on reconsideration.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- The same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained will sublet all subcontract work, with the exception of truck hauling.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with subsection 109-1.06. (11/07/00)S 33

SECTION 205

## EXCAVATION, BACKFILL AND

## FOUNDATION FILL FOR STRUCTURES

205-3.03 BACKFILL.  Add the following:  Backfill placed within 18 inches of a structural unit shall be graded to pass the 3 inch sieve.

205-5.01 BASIS OF PAYMENT.  Add the following:  Grading and placement of material used within 18 inches of structural units, or as shown on the Plans, will not be paid for directly, but will be subsidiary to Item 203(6A) Borrow, Type A.

Excavation for structures is paid for under Item 203(3) Unclassified Excavation.

## SECTION 206

## FILTER BLANKET

- Special Provision

- 206-5.01 BASIS OF PAYMENT.  Add the following:  Filter blanket for

riprap slope drains is subsidiary to Item 611(3) Riprap, Class 1.

Replace Section 401 with the following:

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provision

401-1.01 DESCRIPTION. Construct one or more layers of plant mixed hot asphalt concrete pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN. Meet the requirements of Table 401-1 for the Job Mix Design performed according to ATM 417.

TABLE 401-1

Asphalt Concrete Mix Design Requirements

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| Stability, pounds | 1800 min. | 1200 min. |
| Flow, 0.01 inch | 8-14 | 8-16 |
| Voids in Total Mix, % | 3-5 | 3-5 |
| Compaction, number of blows each side of test specimen | 75 | 50 |
| Percent Voids Filled with Asphalt (VFA) | 65-75 | 65-78 |
| Asphalt Content, min. % | 5.0 | 5.0 |
| Dust-asphalt ratio* | 0.6-1.4 | 0.6-1.4 |
| Voids in the Mineral Aggregate (VMA), %, min. |  |  |
| Type I Type II Type III, IV | 12.0 13.0 14.0 | 11.0 12.0 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt (calculated by weight of mix).

The approved Job Mix Design will specify the target values for gradation, the target value for asphalt cement content, the Maximum Specific Gravity (MSG) of the mix, the additives, and the allowable mixing temperature range.

Target values for gradation in the Job Mix Design must be within the broad band limits shown in Table 703-3, for the type of asphalt concrete pavement specified but asphalt concrete mixture will have the full tolerances in Table 401-2 applied for evaluation in accordance with 401-4.03 except the tolerances for the #200 sieve is limited by the broad band limits.

Do not produce asphalt concrete mixture for payment until the Engineer approves the Job Mix Design.  Do not mix asphalt concrete mixtures produced from different plants.

Use Asphalt Concrete Type II, Class B, minimum, for temporary pavement.

Submit the following to the Engineer at least 15 days before the production of asphalt concrete mixture:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each type of asphalt concrete pavement specified in the Contract.

2.	Representative samples of each aggregate (coarse and/or intermediate, fine, and natural blend material) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1 gallon samples of the asphalt cement proposed for use in the mixture.  Include name of product, manufacturer, test results of the applicable quality requirements of subsection 702-2.01, manufacturer's certificate of compliance according to subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will then evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate type and class of asphalt concrete pavement specified and establish the approved Job Mix Design that will become a part of the Contract.

No payment for asphalt concrete pavement for which a new Job Mix Design is required, will be made until the new Job Mix Design is approved.  Approved changes apply only to asphalt concrete mixture produced after the submittal of the changes.

Changes. Failure to achieve results conforming to Table 401-1 or changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio, will require a new Job Mix Design.  Submit changes and new samples in the same manner as the original submittal.

401-2.02 AGGREGATES. Conform to subsection 703-2.04.

Use a minimum of three stockpiles for crushed asphalt concrete aggregate (coarse, intermediate, and fine). Place blend material or natural fines in separate piles.

401-2.03 ASPHALT CEMENT.  Provide the grade of asphalt cement specified in the Contract meeting the applicable requirements of Section 702.  If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Document the storage tanks used for each batch on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket.  The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (106-1.05).

2.	Conformance test reports for the batch (Section 702).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design.  At least 70% of the aggregate must remain coated when tested according to ATM 414.

401-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the asphalt concrete mixture according to subsection 106-1.03.  Provide copies of these test results to the Engineer within 24 hours.

Failure to perform quality control forfeits the Contractor’s right to a retest under subsection 401-4.02.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the asphalt concrete mixture. Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS.  Do not place the asphalt concrete mixture on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or compaction of the mix.  Do not place asphalt concrete mixture unless the roadway surface temperature is 40 F or warmer.

401-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of asphalt concrete mixture buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of asphalt concrete mixture.

401-3.03 ASPHALT MIXING PLANT.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before asphalt concrete mixture production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the asphalt concrete mixture.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

401-3.04 HAULING EQUIPMENT.  Haul asphalt mixtures in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

Cover the asphalt concrete mixture in the hauling vehicle, when directed.

401-3.05 ASPHALT PAVERS.  Use selfpropelled pavers equipped with a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices.  Use a 30 foot minimum ski, or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture. Heat and vibrate screed extensions.  Place auger extensions within 20 inches of the screed extensions or according to written manufacturer’s recommendations.

Equip the paver with a means of preventing the segregation of the coarse aggregate particles from the remainder of the bituminous plant mix when that mix is carried from the paver hopper back to the paver augers.  The means and methods used shall be approved by the paver manufacturer and may consist of chain curtains, deflector plates, or other such devices and any combination of these.

The following specific requirements apply to the identified bituminous pavers:

1)	Blaw-Knox bituminous pavers shall be equipped with the Blaw-Knox Materials Management Kit (MMK).

2)	Cedarapids bituminous pavers must have been manufactured in 1989 or later.

3)	Caterpillar bituminous pavers shall be equipped with deflector plates as identified in the December 2000 Service Magazine – entitled: New Asphalt Deflector Kit {6630, 6631, 6640}.

The Contractor shall supply a Certificate of Compliance that verifies the required means and methods used to prevent bituminous paver segregation have been implemented.

The Engineer shall approve means and methods used to prevent bituminous paver segregation before the bituminous paver is used to place bituminous plant mix on the project.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers.  Operate rollers according to manufacturer's instructions.  Avoid crushing or fracturing of aggregate.  Use rollers designed to compact hot asphalt concrete mixtures and reverse without backlash.

Use fully skirted pneumatic-tire rollers with a minimum operating weight of 3000 pounds per tire.

401-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the asphalt concrete mixture, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC TM 6.

Heat the aggregate for the asphalt concrete mixture to a temperature specified in the mix design.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Asphalt concrete mixture containing soot or fuel is considered unacceptable according to subsection 105-1.11.

401-3.10 MIXING.  Combine the aggregate, asphalt cement and additives in the mixer in the amounts required by the Job Mix Design.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

Mix the asphalt concrete mixture within the temperature range determined by the Job Mix Design.

401-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, if the characteristics of the asphalt concrete mixture are not altered.  Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness, or stiffness of the mixture are causes for rejection.

401-3.12 PLACING AND SPREADING.  Place the asphalt concrete mixture upon the approved surface, spread, strike off, and adjust surface irregularities.  Use asphalt pavers to distribute asphalt concrete mixture, including leveling courses.  The maximum compacted lift thickness allowed is 3 inches.

Use hand tools to spread, rake, and lute the asphalt concrete mixture in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the dropoff exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland concrete curbing until it has cured for at least 72 hours.

401-3.13 COMPACTION.  Thoroughly and uniformly, compact the asphalt concrete mixture by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers. Use pneumatic tire rollers to compact Preleveling Asphalt Concrete, Type IV, Class B.

***deleted***

The target value for density is 94% of the maximum specific gravity (MSG), as determined by WAQTC FOP for AASHTO T 209.  For the first lot of each type of asphalt concrete pavement, the MSG will be determined by the Job Mix Design.  For additional lots, the MSG will be determined by the sample from the first sublot of each lot.

Acceptance testing for density will be performed in accordance with WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.  (Acceptance testing for density of leveling course or temporary pavement is not required.)

Do not leave rollers or other equipment standing on pavement that has not cooled sufficiently to prevent indentation.

401-3.14 JOINTS.  Minimize the number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.

Remove to full depth improperly formed joints resulting in surface irregularities.  Replace with new, and thoroughly compact.

Precut pavement removal to a neat line with a power saw or by other approved method.

Form transverse joints by saw cutting back on the previous run to expose the full depth of the course or use a removable bulkhead.  Skew transverse joints between 15-25 degrees.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

Seal the vertical edge of all longitudinal joints with Crafco 34524 Joint Adhesive or approved equal before paving against it.  Apply a 1/8 inch thick band of joint adhesive over the surface according to manufacturer’s recommendations.

For the top layer of asphalt concrete pavement, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

Seal the pavement surface 12 inches on each side of all the longitudinal joints while the pavement is clean, free of moisture, and before traffic marking with GSB-78 (from Asphalt Systems), or approved equal.

401-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge.  Correct variations from the testing edge, between any two contacts of more than 3/16 inch.

401-3.16 PATCHING DEFECTIVE AREAS.  Remove any asphalt concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way determined to be defective.  Do not skin patch.  Remove defective materials for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh asphalt concrete mixture according to subsection 401-3.13 to grade and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the Asphalt Concrete pay item.

401-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

Asphalt Concrete. By weighing, no deduction will be made for the weight of asphalt cement or anti-stripping additive, or by the area of final pavement surface.

Asphalt Price Adjustment. Calculated by quality level analysis under subsection 401-4.03.

Asphalt Cement. By the ton, as follows. Method 1 will be used for determining asphalt quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt content specified in the Job Mix Design.

1.	Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  Percent of asphalt cement will be determined by ATM 405 or WAQTC FOP for AASHTO T 308.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the Job Mix Design.

2.	Supplier's invoices minus waste, diversion and remnant. This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing asphalt concrete mixture for one project only.

The Engineer may direct, at any time, that tankers be weighed in the Engineers presence before and after unloading.  If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement.  The Engineer will determine the method.  The weight of asphalt cement in waste asphalt concrete mixture will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Temporary Pavement.  By weighing.  No deduction will be made for the weight of asphalt cement or anti-stripping additive.

Longitudinal Joint.  By the lineal foot of longitudinal joint.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The quantity of each type of asphalt concrete mixture produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons, each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 4,999 tons, the contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection.  Hot mix asphalt quantities of less than 300 tons remaining after dividing the lot into sublots will be included in the last sublot, hot mix asphalt quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to subsection 401-4.03 except as noted.

For contract quantity of less than 1,500 tons (and for temporary pavement), hot mix asphalt will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the hot mix asphalt to the specified depth and finished surface requirements and tolerances.  Remove and replace any hot mix asphalt that does not conform to the approved JMD.

A area of finished surfacing that is visibly segregated, fails to meet surface tolerance requirements is considered unacceptable according to subsection 105-1.11.

1. 	Asphalt Cement. Samples for the determination of asphalt cement content will be taken from the windrow either in front of the paver, or at the end of the auger, or behind the screed before the initial compaction.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2. 	Asphalt Cement Quality. The Contractor shall sample asphalt cement from the asphalt cement supply line when requested, witnessed by the Engineer’s representative.  After purging residual asphalt cement, take 3 one quart samples into wide mouth one quart metal containers.  Asphalt cement will be sampled for acceptance testing according to WAQTC FOP for AASHTO T 40 and tested for conformance to the specifications in Section 702.  Three separate samples will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing.

3.	Aggregate Gradation.

a.	Drum Mix Plants. Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device, from the stopped conveyor belt or from the same location as samples for the determination of asphalt cement content.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the asphalt concrete mixture.

b.	Batch Plants. Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

4.	Density. Cut full depth core samples from the finished asphalt concrete pavement within 24 hours after final rolling.  Neatly cut one 6 inch diameter core sample with a core drill from each sublot at the randomly selected location marked by the Engineer including locations having low cyclic density.  Use a core extractor to prevent damage to the core.  The Engineer will determine the density of the core samples according to WAQTC FOP for AASHTO T 166/T 275.  Do not core asphalt concrete pavement on bridge decks. Backfill and compact voids left by coring with new asphalt concrete mixture within 24 hours.

5.	Retesting.  A retest of a sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  The Engineer will mark the sample location for the density retest.  The original test results for gradation, asphalt cement content, or density will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed. Except for the first lot, gradation or asphalt cement content retesting of the sample from the first sublot of a lot will include retesting for the MSG.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The following method of price adjustment will be applied to each type of Asphalt Concrete Pavement for which the contract quantity equals or exceeds 1,500 tons, except as specified in subsection 401-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.  Asphalt cement content results will be reported to the nearest 0.1 percent.

The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for asphalt concrete mixture, which includes gradation and asphalt cement content.  The second factor is for density.

A lot containing asphalt concrete pavement with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing asphalt concrete pavement that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under subsection 105-1.11.

The Engineer will reject asphalt concrete mixture that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected mixture and tested if requested.  If test results are within specification limits, payment will be made for the mixture.  If a test results fails to meet specifications, no payment will be made and the cost of the testing will be subtracted under Item 401(6) Asphalt Price Adjustment.  Costs associated with removal and disposal of the rejected asphalt concrete mixture are subsidiary to the Asphalt Concrete pay item.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.  Cyclic low density will not be considered outliers.

If a sieve size on a gradation test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment.  The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

If the density test result is an outlier, the density test result will not be included in the price adjustment, however, the gradation and asphalt cement content results for that sublot will be included provided neither is an outlier.

Quality Level Analysis.  Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and a test results on material not incorporated into the work, are eliminated from the quality level analysis.

The arithmetic mean () of the remaining test results is determined:

Where:	= summation of

x = individual test value to xn

n = total number of test values

is rounded to the nearest tenth for density and all sieve sizes except the No. 200 sieve.   is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation(s), after the outliers have been excluded, is computed:

Where:	(x2)	=	sum of the squares of individual test values.

(x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200.  Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2.  The TV is the specification value specified in the approved Job Mix Design.  Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 for Quality Level Analysis purposes.  The TV for density is 94% of the maximum specific gravity (MSG), the LSL is 92% of MSG and the USL is 98%.

TABLE 401-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV-6.0 | TV+6.0 |
| 1/2 inch sieve | TV-6.0 | TV+6.0 |
| 3/8 inch sieve | TV-6.0 | TV+6.0 |
| No. 4 sieve | TV-6.0 | TV+6.0 |
| No. 8 sieve | TV-6.0 | TV+6.0 |
| No. 16 sieve | TV-5.0 | TV+5.0 |
| No. 30 sieve | TV-4.0 | TV+4.0 |
| No. 50 sieve | TV-4.0 | TV+4.0 |
| No. 100 sieve | TV-3.0 | TV+3.0 |
| No. 200 sieve1 | TV-2.0 | TV+2.0 |
| Asphalt % | TV-0.4 | TV+0.4 |
| Mat Density % | 92 | 98 |

Note 1.Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

4.	The Upper Quality Index (QU) is computed:	 QU

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	The Lower Quality Index (QL) is computed:	 QL

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined.  See subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined.  See subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor is determined for Density (DPF) and gradation and asphalt cement content pay factors (PF) from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

The CPF is rounded to the nearest hundredth.

Table 401-3 gives the weight factor (f) for each sieve size and asphalt cement content.

TABLE 401-3

WEIGHT FACTORS

| Gradation | Factor “f” |
| --- | --- |
| 3/4 inch sieve | 4 |
| 1/2 inch sieve | 5 |
| 3/8 inch sieve | 5 |
| No. 4 sieve | 4 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No. 30 sieve | 5 |
| No. 50 sieve | 5 |
| No. 100 sieve | 4 |
| No. 200 sieve | 20 |
| Asphalt % | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower.

PAB = Price Adjustment Base  = $84.20 per ton

401-4.04 EVALUATION OF ASPHALT CEMENT

Asphalt cement will be randomly sampled and tested every 200 tons and evaluated for price adjustment.  If the last sample increment is 100 tons or less, that quantity of asphalt cement will be added to the quantity represented by the previous sample and the total quantity will be evaluated for price adjustment.  If the last sample increment is greater than 100 tons, it will be sampled, tested and evaluated separately.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.

The total asphalt cement price adjustment is the sum of the individual sample price adjustments and will be subtracted under Item 401(6) Asphalt Price Adjustment.

Table 401-4

## ASPHALT CEMENT PAY REDUCTION FACTORS

## (Use the single, highest pay reduction factor)

|  | #### Spec | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 0 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.1 | 0.25 | Reject or Engr Eval |
| ##### Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | <3 Pa-s | <3 |  | >3 |  |  |  |  |  |  |
| Dynamic Shear | >1.00 kPa | >1.00 |  | 0.99-0.88 |  |  |  | 0.87-0.71 | 0.70-0.50 | <0.50 |
| Toughness | >110 in-lbs | >93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | <70.0 |
| Tenacity | >75 in-lbs | >63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | <48.0 |
| ##### Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | <1.00 % | <1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | >1.276 |
| Dynamic Shear | >2.20 kPa | >2.20 |  | 2.199-1.816 |  |  |  | 1.815-1.432 | 1.431-1.048 | <1.048 |
| ##### Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | <5000 kPa | <5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | >5867 |
| Creep Stiffness, S | <300 MPa | <300 |  | 301-338 |  |  |  | 339-388 | 389-450 | >450 |
| Creep Stiffness, m-value | >0.300 | >0.300 |  | 0.299-0.287 |  |  |  | 0.286-0.274 | 0.273-0.261 | <0.261 |
| Direct Tension | >1.0 % | >1.0 |  | 0.99-0.86 |  |  |  | 0.85-0.71 | 0.70-0.56 | <0.56 |

# Asphalt Cement Price Adjustment for each sample = 5 x PAB x Qty X PRF

PAB = Price Adjustment Base

Qty = Quantity of asphalt cement represented by asphalt cement sample

PRF = Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results and using ASTM D3244 determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test

result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor under Item 401(6) Asphalt Price Adjustment, shall pay the cost of testing the referee sample.

The total Asphalt Price Adjustment is the sum of all the price adjustments for each lot.

401-4.06 EVALUATION OF LONGITUDINAL JOINT DENSITY.  Longitudinal joint density price adjustments apply when asphalt concrete mixture quantities are equal to or greater than 1,500 tons.  An price adjustment will be based on the average of the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

Deduct = ($1.00 per lineal foot) x (lineal feet of paved joint for the entire project) x (91 % – Project Average Joint Density %) x 100    (Note: convert % to decimals in this equation)

2.	If project average joint density is greater than 91% MSG apply the following incentive:

Add = ($1.00 per lineal foot) x (lineal feet of paved joint for the entire project) x (Project Average Joint Density % – 91%) x 100        (Note: convert % to decimals in this equation)

The longitudinal joint price adjustment will be included in Item 401(6) Asphalt Price Adjustment.

401-5.01 BASIS OF PAYMENT.

The Engineer will assess a fee of $2,500.00 under Item 401(6) Asphalt Price Adjustment, for each mix design subsequent to the approved Job Mix Design for each Type and Class of Asphalt Concrete Pavement specified.

Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6) Asphalt Price Adjustment.

Anti-stripping additives are subsidiary to the asphalt concrete pavement unless specified as pay items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1) 	Asphalt Concrete, Type __; Class __ 	Ton

401(2) 	Asphalt Cement,  __ 	Ton

***deleted***

R199USC04(10/25/05)

## SECTION 501

# STRUCTURAL CONCRETE

501-1.01 DESCRIPTION.  Add the following:  “Construct utility conduits as shown on the Plans.”

    - MIXING.

3.   	Truck Mixing.  In the fourteenth paragraph, revise “30 seconds” to “30 minutes.”

Add the following paragraph before the last paragraph:

When carrying wash water on the truck mixer, carry it in a compartment separate from the one used for carrying or measuring the mixing water.  The Engineer will specify the amount of wash or flush water, when permissible, and may specify a “dry” drum if wash water is used without measurement or without supervision.

    - PLACING CONCRETE.

13.  Pipes, Conduits and Ducts.  Add the following:  Fill annulus around utility conduits at abutment backwalls with epoxy resin conforming to AASHTO M 235, Type III, Grade 3.

    - PRECAST CONCRETE MEMBERS.

2.  Manufacture.  Add the following to the second paragraph “Fabricate precast prestressed concrete members according to Section 502.”

    - METHOD OF MEASUREMENT.  Add the following:

“Each.  Installed in place.”

501-5.01 BASIS OF PAYMENT.  Delete the second paragraph and substitute the following:  Payment for reinforcing steel, prestressing steel, structural steel, hardware, elastomeric bearing pads, concrete, grout, epoxy resin adhesive, expanded polyethylene and other items included in or attached to precast concrete members is subsidiary to the Contract price for the member.

Delete the subsection Concrete Price Adjustment.

Add the following:  Utility conduits are subsidiary to concrete.

# SECTION 502

# PRESTRESSING CONCRETE

Add the following subsection:

502-1.02 ALTERNATE DESIGN.  The Contractor may submit an alternative design for prestressed girders for approval.  Substitutions and necessary modifications to other portions of the structure to accommodate the substituted girders, will be done without extra compensation and at no adjustment in unit prices or pay quantities.  Follow the AASHTO LRFD Bridge Design Specifications, 3rd Edition – 2004 (with latest interims), as modified in this specification, for alternate girder designs.  Have the alternate design sealed by a professional engineer registered in the State of Alaska.

Proportion alternate girder designs for zero tension stress at full service load after losses have occurred.  Do not use girder designs that use lightweight concrete.  Design girders to include a 50 psf dead load allowance for future paving.  When concrete deck slabs are cast integral with the girders, provide at least 2 ¼” inches of concrete cover above the top mat of deck slab reinforcing steel.  Cast in place deck slabs must provide at least 2 ½” inches of cover.  Where required, construct cast in place curb and sidewalks after erecting the girders.

502-3.02 FABRICATION

3.	 Tensioning.

In the fifth paragraph revise “80 percent” to “70 percent” and “(0.80 f’s)” to “(0.70 f’s)”.

4.	 Grouting.

Add the following:  Pressure placed on the grout shall not exceed 100 psi.

## SECTION 503

## REINFORCING STEEL

503-3.04 PLACING AND FASTENING.  In the second sentence of the first paragraph, insert “gage” after “16.”

Delete the period from the second sentence and delete the last sentence of the fifth paragraph and add the following “or weather, the minimum embedment is l ½ inches.”

503-3.05 SPLICING.  In the second sentence of the first paragraph, revise “No. 16” to “No. 11.”

Add the following:

4. Welded Lap Splice.  Meet ANSI/AWS D1.4.  Apply visual inspection to all welded lap splices.

Before welding, submit for approval a welding plan consisting of the following:

  - Contractor’s Quality Control Inspector qualifications

b.	Welding Procedure Specifications (WPS)

## c.	Welder Performance Qualification Records (WPQR) with documentation of current welder certification

## SECTION 504

## STEEL STRUCTURES

    - FABRICATION.

5.  	Bolt Holes.   In the third paragraph, revise “paragraph 5” to “paragraph 7.”

In the seventh paragraph, revise “paragraph 9” to “paragraph 11.”

In the eighth paragraph, revise “paragraph 9” to ”paragraph 11.”

- Bolted Connections, High-Strength Bolts.  In the second sentence of the first paragraph, revise “washers” to “no washers.”

Delete numbered item 8. and substitute the following:

- Welding.  Perform all welding and Nondestructive Examination (NDE) as shown on the Plans according to the requirements of AWS Structural Welding Code – Steel, D1.1: 2004.

Prior to welding, submit for approval a welding plan consisting of the following:

  - Contractor’s Quality Control Inspector qualifications

  - Welding Procedure Specifications (WPS)

  - Procedure Qualification Records (PQR), if applicable

  - Current welder certifications

  - Contractor’s Ultrasonic Testing (UT) Technician qualifications

Impact energy values for filler metals must not be less than that of the base metals to be joined, when tested at the same temperature as the base metal.

Perform all QC inspection necessary to ensure the material and workmanship satisfies the requirements of the contract documents.

Correct deficiencies in materials and workmanship revealed by either QC or Quality Assurance (QA) inspection without additional compensation.

Furnish completed QC inspection documents to the QA representative designated by the State.

SECTION 505

PILING

Special Provisions

- 505-1.01 DESCRIPTION.  Delete the second paragraph and substitute the following:

Furnish piles of sufficient length to be driven to the estimated pile tip elevation and the required ultimate bearing capacity as shown on the Plans.

Add the following: The Engineer will perform high strain dynamic pile testing at one abutment on Stariski  Creek (Bridge No. 667) and optionally at the other abutment.  After performing the test pile program as described below, the Engineer will establish the installation and construction control criteria for Bridge Number 667 which will be applied to the service piles.  Test piles and service piles for Bridge Number 667 will be driven at least to the estimated tip elevations shown on the plans.

505-3.01 TEST PILES.   Add the following: There will be high-strain dynamic testing performed on at least one pile (possibly two piles) at Bridge Number 667.  The Contractor will drive the test piles as described below:

Stariski Creek  (Br. No. 667)

Test Site                                    Test Pile Type                    Requirements

Abutment 1                                  H Pile / Plumb                Pile test is required

Abutment 2                                  H Pile / Plumb                Pile test may be required

The initial pile driven at each test location will be a test pile.  If the immediate results from the high strain dynamic testing on the test pile are acceptable to the Engineer, the Contractor may drive the remaining abutment piles.  Further dynamic pile tests may be required on other piles, or at other test sites if in the opinion of the Engineer, performance of the hammer-pile-soil system changes from that of the test pile program.  For the dynamic testing of the piles, the Contractor will provide the Engineer reasonable and safe means of access to the test piles for attaching instruments after the pile is placed in the leads.  It is estimated that the Engineer will need approximately 4 (four) hours maximum to set up and install the dynamic test equipment.  The Engineer will furnish the equipment, materials, and labor necessary for drilling holes in the test piles for mounting the testing instruments.  The testing instruments will be attached near the top of the pile with bolts placed through drilled and threaded holes.  If concrete filled pipe piles are to be used on this project, the drilled and threaded holes may have to be plugged after pile installation and testing, and before concrete is poured in to the pipe pile.  If necessary, the Contractor shall furnish electric power for the setup and use of the high-strain dynamic test equipment.  The power supply at the outlet shall be at least 10 amps, 115 volt, 55-60 cycles, AC only.  Delays resulting from installation of the high-strain testing equipment shall not be a basis for a claim.

The Engineer will use the pile dynamic test data to verify assumptions of the original wave equation analysis, and to confirm pile tip elevation, pile bearing capacity, hammer system efficiency, pile stresses during driving, soil resistance distribution on the pile, and pile integrity.  The test piles will remain as part of the permanent structure after testing, analysis, and recommendations are completed.

The high-strain dynamic test pile program for this bridges, will consist of the following tasks:

1.  	For the test pile program, at least 30 calendar days before driving the first test pile, the Contractor will submit to the Engineer the necessary pile driving equipment information as shown on the Pile Driving Equipment Data Form.  The Engineer will provide the Pile Driving Equipment Data Form.  A minimum of 14 calendar days prior to driving the first test pile, the Contractor shall attend a meeting with the Engineer to evaluate and discuss the pile test program.  The Contractor shall give the Engineer at least 7 calendar days advance notice that a test pile will be driven.

2.  	The Engineer shall perform an initial wave equation analysis based on subsurface conditions, pile capacity, and pile type.

3.  	The Contractor shall drive the test piles as specified above and to the tip elevations shown on the Plans, and to criteria established by the initial wave equation analysis.  Dynamic pile testing will be performed for the total length of each test pile.  If an obstruction is encountered during driving of the test pile, that pile will not be considered a test pile and the next pile driven at the test site shall be designated as a test pile as directed by the Engineer.  This dynamic pile testing shall be performed in accordance with ASTM D 4945-00.

4.  	The Engineer shall evaluate the test pile at each test site by re-striking the test piles a minimum of 48 hours after completion of driving the test piles to the specified tip elevation.  The Contractor shall perform the re-strike of the test piles with simultaneous testing by the Engineer using the pile dynamic analyzer.

The re-strike testing procedure shall be performed with a warmed up hammer, the energy or fuel setting adjusted to the maximum position and shall consist of striking the test pile with 60 consecutive blows or until the pile penetrates an additional 3 inches, whichever comes first.  In the event the pile movement is less than 1 inch during the re-strike, the re-strike may be terminated after 25 blows, or even fewer blows if the pile is at practical refusal.

505-3.03 PILE Bearing Values.  Delete this section in its entirety and substitute the following:  The required ultimate bearing capacity for the piles at the bridge on this project is the ultimate pile load as indicated on the bridge plans.  The Engineer shall determine the pile driving criteria for the bridge on this project using a Wave Equation analysis and results from the high-strain dynamic testing.  The Wave Equation computer program to be used on this project shall be the "GRLWEAP" program using the Contractor furnished hammer information, GRLWEAP industry standard hammer input data, and data from the high-strain dynamic testing.

- 505-3.05 Minimum Penetration.   Change “minimum desirable” to “estimated”.

Add the following: The Contractor shall furnish piles of sufficient length to be driven to the minimum tip elevation, to meet the driving criteria from the wave equation analysis and to provide the required cut-off elevation.  Pile lengths shall be calculated from the design cut-off elevation to the minimum tip elevation.  The Contractor shall at the Contractor’s expense, increase the pile lengths given to provide for fresh heading and for such additional pile lengths as may be necessary to suit their method of operation.

505-3.09 DRIVING Piles.  Delete the first and second paragraph and add the following: Pile driving equipment (hammer) used by the Contractor shall be subject to the approval of the Engineer.  The piles shall not penetrate more than 20 feet when a vibratory driver is used for initial pile placement.  Pile driving systems shall be equipped with an appropriate thickness of hammer cushion to prevent damage to the hammer or pile and to ensure uniform driving performance.  Hammer cushions shall be made of durable, manufactured materials, and provided according to the hammer manufacturers guidelines except that wood, wire rope, and asbestos hammer cushions shall not be used.  The hammer cushion shall be inspected in the presence of the Engineer before beginning pile driving and after 50 hours of pile driving on this project.

The pile driving equipment (hammer) shall be sized such that the piles can be driven to the required ultimate bearing capacity without damage to the piles and have compressive driving stresses as indicated by the high-strain dynamic testing and the wave equation analysis not

exceeding 90% of the pile yield stress.  Approval of the pile driving equipment by the Engineer will be based on the high-strain dynamic testing, the wave equation analysis, properly operating pile driving equipment and the Engineer's recommendations.

After the test piles are driven and during the service pile driving operations, the Contractor shall use the approved driving system to install the service piles.  No variations in the driving system will be permitted without the Engineer's written approval. A change in the driving system will only be considered after the Contractor has submitted a revised Pile Driving Equipment Data Form for a revised wave equation analysis by the Engineer, and the analysis indicates an acceptable result.  Approval of a change in the Contractor's driving system may be contingent upon obtaining satisfactory results from additional high strain dynamic tests.  The Contractor will be notified of the acceptance or rejection of the revised driving system within 7 calendar days of the Engineer's receipt of the requested change.  The time required for submission, review, and approval of a revised driving system shall not constitute the basis for a contract time extension.

If difficult pile driving conditions result in pile refusal above the estimated pile tip elevation due to rocks, cobbles, boulders or other subsurface impediment, the work involved in the removal of such impediments, when required by the Engineer, will be classified as Special Pile Excavation.  Pile refusal is defined as the condition encountered during pile driving which results in a pile driven by an impact hammer having a negligible rate of penetration per blow (such as when a pile tip reaches an impenetrable layer such as bedrock) and when the effective transferred energy of a properly maintained and properly operating impact hammer is no longer sufficient to advance the pile tip.  The subsurface impediment must be due the naturally occurring subsurface soil formation and conditions.

505-4.01 Method of Measurement.

Furnish Piles.: Add the following:  The Contractor will, at the Contractor’s expense, increase the specified pile lengths to provide for fresh heading and for such additional pile lengths as may be necessary to suit their method of operation.

Load Tests.   Add the following: The specified high-strain dynamic load tests on this project will not be measured for payment.  The number of high-strain dynamic load tests to be paid for shall be the number of additional tests required by the Engineer.  This unit price per load test shall provide payment to the Contractor for their work required to assist the Engineer in performing additional high-strain dynamic testing if required.

Add the following paragraph:

Special Pile Excavation:  Removal of unusual obstructions causing pile refusal above the specified minimum pile tip elevations, when required by the Engineer, shall be classified as Special Pile Excavation.  This work will be measured on a time and materials basis according to subsection 109-1.05 of the Standard Specifications.

505-5.01 Basis of Payment.  Add the following: The specified high-strain dynamic load tests at the bridges on this project will not be paid for directly, but will be subsidiary to Item 505(6) Drive Structural Steel Piles.

Driving shoes required to drive piles is subsidiary to Item 505(6) Drive Structural Steel Piles.

Pay Item No.	Pay Item	Pay Unit

505 (17)	Special Pile Excavation	Contingent Sum

## SECTION 507

## BRIDGE RAILING

507-3.01 CONSTRUCTION REQUIREMENTS. 1.  General. In the third sentence, replace “normal to grade” with “plumb.”

SECTION 610

DITCH LINING

Special Provision

610-2.01 MATERIALS.  Replace this subsection with the following:  Use stones that are sound and durable, are no larger than 4 inches in greatest dimension, and not more than 50% by weight passing a 3 inch sieve as determined by WAQTC FOP for AASHTO T 27/T11.

This page intentionally left blank.

SECTION 611

RIPRAP

Special Provision

611-1.01  DESCRIPTION.  Add the following:  Construct riprap slope drains.

611-2.01 MATERIALS.  Add the following:

5.	Class IIA	Consists of 90% Riprap, Class II combined with 10 percent Stream Backfill.  Refer to subsection 703-2.13 for Stream Backfill gradation.  This material is intended to inhibit subsurface stream flow through the voids provided by typical riprap installations by adding a silty sandy gravel to fill the voids.

611-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:  Fill Riprap voids with Stream Backfill.  Manual placement with hand tools and use of water may be required to adequately fill voids.  Stream Backfill material shall not inhibit stone to stone contact of the Class II riprap material.  The final surface of the Riprap, Class IIA shall receive a 4 inch layer of Stream Backfill that will be washed to form a uniform bed surface that is flush with the top of the riprap as shown on the Plans.  Wash water shall be handled according to applicable permits.

- 611-5.01 BASIS OF PAYMENT.  Add the following:  Payment for Item

611(3) includes excavation, backfill, pavement depression and filter blanket.

Furnishing and placing Stream Backfill material is subsidiary to Riprap, Class IIA.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

611(3)	Riprap, Class I	Lump Sum

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS. Under items 1 delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit shop drawings for signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

Standard Modification

615-2.01 MATERIALS.  Delete the first paragraph of Item 2, including subitems a., b., and c. and replace with:

2.	Sign Fabrication.  Use Type IV reflective sheeting (for lettering, symbols, borders, and background) on sheet aluminum panels for signs except the following:

a.	Orange Background Signs:  Use either Type II or Type III orange reflective sheeting or use Type VII or Type IX fluorescent orange reflective sheeting.  For temporary installations place reflective sheeting on sheet aluminum, plastic, or plywood panels.

b.	Railroad Crossbucks and Vertical Crossbuck Supports: Use white Type VIII or Type IX reflective sheeting for background of sign and strips.

- Non-Illuminated Overhead Signs with White Legends on Green Backgrounds:  Use Type IX reflective sheeting for legends and background.  Create the legend in one of the following ways:

(1)	Cut border and legend from white Type IX reflective sheeting and adhere to a green Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

- Fluorescent Yellow-Green School Area Signs:  Use Type VIII or Type IX reflective sheeting for background.

Add the following paragraph:

Reflective Sheeting Warranty.  Supply manufacturer’s warranty for reflective sheeting, including retention of fluorescent yellow-green (measured according to ASTM E 2301) for ten years according to the following criteria:

Minimum Fluorescent Luminance Factor 	YF: 20%

Minimum Total Luminance Factor		YT: 35%

The warranty shall stipulate that: If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness. E26(1/1/06)

SECTION 618

# SEEDING

# Special Provisions

618-1.01 DESCRIPTION. Add the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. Provide a living ground cover on all slopes as soon as possible.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.03 APPLICATION. Add the following: Apply seed, mulch and fertilizer as follows per acre. Apply seed and mulch in one application if using the hydraulic method. Apply all fertilizer with the hydraulic method.

| Seed Mix | Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- | --- |
| Type A | Seed | Bering Hairgrass (Norcoast) Red Fescue (Arctared) Annual Ryegrass (Lolium) Alpine Bluegrass (Grueining) | 0.4 lbs. 0.3 lbs. 0.1 lbs. 0.2 lbs. Total = 1.00 lbs. |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 45 lbs. 45-58 lbs. |
|  | Fertilizer | 20-20-10 | 12.0 lbs. |

The Contractor shall not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Bering Hairgrass if Bering Hairgrass is commercially unavailable.  Substitute Bering Hairgrass with Nortran Tufted Hairgrass at the same application rate.

618-4.01 METHOD OF MEASUREMENT. Delete the third paragraph and add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT. Add the following: The work described under subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(11/06/02)R52USC

SECTION 621

PLANTING TREES AND SHRUBS

621-1.01 DESCRIPTION.  Add the following:  This work consists of revegetation as shown on the Plans and in Alaska Corp. of Engineer’s (ACOE) Permit No. POA-2005-913D.   Conform to the lines, grades, depths, and typical cross sections shown on the Plans or as established.  Guidelines for this work may be found in “Streambank Revegetation and Protection, Guide for Alaska” revised 2005, Alaska Department of Fish and Game.

621-2.01 PLANT STOCK.  Add the following to item 2. Collected Stock:

The live rooted plants and dormant cuttings shall be collected under the supervision of a plant material consultant provided by the Contractor and approved by the Engineer.  The Contractor is responsible for locating, harvesting, and providing a controlled cold storage facility for plants and dormant cuttings.  At least one week before the harvest, the Contractor shall submit harvest site locations for site inspection and approval.

Woody plants acceptable for dormant cuttings and root plant transplanting are as follows:

Barclay Willow	(Salix Barclay)

Felt Leaf Willow	(Salix Alaensis)

Pacific Willow	(Salix Lasiandra)		(transplanting only)

Balsam Poplar 	(Populus Balsamnifera)	(transplanting only)

Cottonwood	(Populus Trichocarpa)		(transplanting only)

Sitka Alder	(Alnus Sinuate)		(transplanting only)

Thinleaf Alder	(Alnus Tenuifolia)		(transplanting only)

a.	Dormant Cuttings.  Dormant cuttings shall be harvested from living woody plants when the plants are not actively growing.  The cuttings shall be collected from the species specified unless the Engineer approves alternates. No invasive vines or plant materials shall be mixed with the cuttings.  Such material shall be left at the harvest site.

Live dormant cuttings shall be ½ to 2 inches in diameter, 3 to 4 feet long.   Live dormant cuttings shall be handled with care to avoid bark stripping and trunk

wood splitting.  Cuts shall be made 8 to 12 inches from the ground.  Cuts shall be made flat or at a blunt angle with pruning shears.  Cut the basal ends, not the growing tips to obtain the required length.

If cuttings are to be used for spring and early summer plantings, cuttings shall be collected during winter/early spring before leaves appear but no later than March 31.  For fall dormant plantings, collect cuttings in the late summer/early fall, after plants have gone dormant, after leaves change color, and have dropped.  Flower buds (“pussy willows”) are not acceptable.  These buds typically occur at the tips of branches produced during the last growing season.

1)	Binding.  Live dormant cuttings shall be bound together securely with twine or hoisting belts at the harvesting site for ease handling and for protection during transport.  Cutting shall be grouped and bound to stay together during handling.  Side branches shall be kept intact.  Growing tips shall be placed in the same direction.

2)	Identification.  The Contractor shall label live dormant cuttings.  Securely attach labels to the bundles and/or groups of cuttings, indicating plant species and the date collected.

3)	Transportation to Cold Storage.  Place cuttings in the transport vehicle in an orderly manner and cover for ease of handling to prevent damage or bruising and to prevent drying out.  The Contractor shall schedule cutting and deliver to the cold storage facility so that the materials can be processed the day they arrive.

4)	Inspection.  Upon arrival at the cold storage facility, labeled dormant cuttings shall be inspected by the Engineer for proper length, diameter, binding, labeling, and the presence of unapproved plant.

5)	Cold Storage.  Live dormant cuttings shall be stored in a secure refrigerated area.  If collection of dormant cuttings occurs while daytime temperatures remain below freezing, freeze not colder than 0F until planting.  If daytime temperatures are above freezing during collection, refrigerate cuttings at temperatures between 31F and 40F, with 60 to 70 percent humidity, until planting.

Place cuttings in ventilated plastic bags or a plastic cover.  Monitor temperature and humidity to prevent cuttings from drying out, sprouting, or getting mildew.  Do not plant cuttings having mold, are dried out, or have sprouted.

6)	Transportation to Work Site. Before use, soak cuttings in cool water for at least 24 hours before, but for no more than 4 days.  Cuttings shall be taken directly from the cold storage site to the planting site.    The Contractor shall deliver only plant material to be installed that day to the work site.  Do not return unplanted cuttings to cold storage.  Outside storage locations shall be shaded and protected from wind.  Protect cuttings from drying.

b.	Vegetative Mats.  On site willows and alders with intact root mass and soil matrix shall be salvaged as practicable and transplanted in the newly established floodplain area upstream of the new highway bridge.  Cut the root/soil mass as deeply as possible.  Individual vegetative mats shall be stored, until transplanted together with other salvaged mats in a single layer with mat edges butting against other mats.  Cuttings having mold or sprouted may not be used for planting.  Root mass and soil matrix shall be periodically watered to maintain a moist condition.  Planting may be supplemented with native nursery grown, bare root, or wild collected willow to achieve the required density.

621-3.03 PLANTING.  Add the following:

9.	Brush Layering.

Begin brush layering at the top surface of the riprap toe as shown on the Plans.

Place 15 rooted plants/dormant cuttings per foot slightly crisscrossed.  Place the roots of the transplants or the cut ends of the branches into the slope with the tips extending beyond the edge of the bench no more than ¼ the total plant/branch length.  Soak each layer with water before covering with soil.  Place a minimum of 6 to 8 inches of topsoil on top of the plant/cuttings and tamp into place.

Compact the soil layer over and around live dormant cuttings or rooted plants with hand tools and feet.

10.	Vegetative Mats.

Place mats of salvaged vegetation at 4 foot centers in the areas shown in the ACOE permit reclamation plan.

621-3.04 PERIOD OF ESTABLISHMENT.  Replace the first sentence with the following:  The establishment period shall extend for 1 complete growing season after the required planting is completed.

Add the following:

BRUSH LAYERING

By the end of the establishment period, at least 4 cuttings per foot, on average, for each individual layer shall be healthy and in a flourishing condition.  In no case shall 4 contiguous linear feet of a layer have less than this condition.  For areas not meeting this requirement, the Contractor shall replant the areas, without additional cost to the Department, using live staking techniques spaced at 6 inches along the layer or as directed by the Engineer.  Do not remove the dead cuttings.

The Contractor shall be responsible for replacing plants vandalized, stolen, or damaged during the establishment period.  Replacement shall be made as soon as weather conditions permit.  The quality of replacement plants shall be equal to, or better than, initially specified.

VEGETATIVE MATS

Planted woody shrubs, placed as transplanted salvaged vegetative mats or other supplied shrubs shall exhibit 70% survival at the end of the 1st complete growing season, and achieve 50% survival of woody species planted after the 2nd growing season.  If, after the 2nd year, 50% survival has not been attained, the Contractor shall replant woody shrubs.

Add the following subsections:

621-3.08 CHANNEL REALIGNMENT.  Excavate to the dimensions, lines and grades shown on the Plans.  Construct embankments with material from unclassified excavation, Riprap Class II, alluvial gravels, coir geotextile, and brush layering.  Backfill the existing stream channel with Borrow, Type A and revegetate as shown on the Plans.

621-5.01 BASIS OF PAYMENT.  Add the following:  Payment for Item 621(7) Revegetation includes

1)	excavating, hauling, placing material, and disposing material

2)	installing, and furnishing topsoil, soil/gravel mix in revegetation areas, and soil stabilization fabric (geotextile),

3)	harvesting, transporting, storing, and transplanting dormant cuttings, vegetative mats, and measures including watering, to aid in the survivability of the Revegetation.

4)	furnishing, and installing live rooted plants, Dormant cuttings, Vegetative mats, and Brush Layering

5)	Channel Realignment and revegetation of the existing channel a shown in the Plans.

6)	Grading and revegetation of temporary access roads into the work area.

Borrow required for backfilling the existing channel will be paid for under 203(6A) Borrow, type A.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

621(7)	Revegetation	Lump Sum

SECTION 622

REST AREA FACILITIES

Special Provisions

622-1.01 DESCRIPTION.  Add the following:

9.	Boardwalk

10.	Steel Stairs

11.	Aluminum stairway tread

Add the following subsections:

622-2.13 STEEL/FIBERGLASS BOARDWALK AND STAIRS.  Material shall be new and conform to the following:

A.	Structural Steel and Steel Members.  Structural steel shall conform to the requirements of ASTM ***deleted*** A 36  (for Carbon Structural Steel).

B.	Aluminum.  Extruded aluminum for pipe handrailing and aluminum for elbows shall meet ASTM B-429.

C.	Fiberglass Grating.  Shall be fiberglass vinyl ester resin.  Load bar depth shall be 1-1/2 inches and spaced 1 inch on center.  Grating open area shall be 40% minimum.  Color shall be dark gray.  Product similar to Fibergrate Fiberglass Grating, Model I 4015 Safe T-Span Pultruded Grating.  Fibergrate Composite Structures Inc.;  4285 Kellway Circle, Suite 224; Addison, TX 75001; Phone 800-527-4043 or www. Fibergrate.com.

Fiberglass grating hold down clips shall be M-clip, saddle type similar to Fibergrate MI-40 or approved equal.

Edge sealing kit shall be as specified by manufacturer.

D.	Lumber.  Lumber shall be surfaced four sides conforming to the following: Wood species Douglas Fir, Western Hemlock or Hem fir unless otherwise specified.

1.	Dimensional.  Dimensional lumber and timbers as shown on the Plans in nominal dimensions.  2x4 indicated surfaced for sides (S4S) or planed material.  Use classification for light framing shall be Construction Grade.  Use classification for structural joists and 	planks shall be No. 2 Grade or better.  Manufacturing classification shall be Dressed (Surfaced) Lumber.  Size classification shall be Nominal Size Designations of Boards, Dimension, and Timbers.

2.	Rough Cut.  Unless otherwise indicated, rough cut lumber and timbers are shown on the Plans in actual dimensions.  2 inch x 4 inch indicating rough cut material.  Use classification shall be Structural Lumber No. 2 Grade or better.  Manufacturing classification shall be Rough Lumber.  Size classification shall be Rough Dry Sizes.

E.	Preservative Pressure Treatment.  Shall conform to Section 714.  Pressure treat with preservative Ammonical Copper Quat – Type A,B,C, or D (ACQ-A,B,C, or D) or Copper Azole – Type A (CBA-A).  Treatment shall be as follows:

1.	Above Ground Applications.  Minimum retention shall be 0.40 pounds per cubic foot or to refusal.  Treated materials shall be uniformly brown in color and nonincised.  This type of treated lumber is commonly used for residential decks for above ground applications.  Incising may be used on 4x and thicker material to obtain minimum retentions.

2.	Ground Contract Applications.  Minimum retentions shall be 0.60 pounds per cubic foot.  Expose treated materials shall be pigmented uniformly brown in color by manufacturer.

F.	Fasteners.  Commercial quality and type of nails and screws as required to securely hold members in place according to the National Design Specifications.  Nails shall be hot dipped galvanized.  Other fasteners shall be corrosion resistant.  Fasteners in pressure treated wood shall be hot dipped galvanized.  Nails and wood screws below grade in pressure treated wood shall be stainless steel.

G.	Paint.

1.	Semitransparent Oil Stain.  Exterior alkyd based stain, color to match solid oil stain “Russet”.  Stains for pressure treated wood shall be recommended by manufacturer for use on pressure treated wood.

2.	Metal Primer Paint.  As recommended by enamel paint manufacturer.

3.	Enamel Paint.  Exterior alkyd base gloss enamel.  Color to match solid oil stain color.

622-2.14 ALUMINUM STAIRWAY TREAD.    Structural aluminum shall conform to the requirements of ANSI 6061-T6, 3003-H14, or 3003-H112.

Aluminum treads for stairway construction shall be serrated rectangular bar grating with a corrugated angle nosing.  Bearing bars shall be 1-3/4” x 3/16” with at 1-3/16” center to center spacing.

622-2.15 PILES.  Piles shall be galvanized schedule 40 pipe.  Galvanize according to subsection 505-3.13.

622-3.08 BOARDWALK AND STAIRWAY TREAD.  Submit show drawings for approval before construction of landings and stairs.  The Contractor shall stay within the Right of Way for the length of the boardwalk while constructing the boardwalk.  No equipment, access, or material storage is allowed outside of the Right of Way.  Revegetate and restore to original appearance or to the satisfaction of the Engineer any disturbed area.

Structural Steel.  Steel beams shall be set parallel to adjacent steel beams where the Plans call for straight alignments.  Steel beams shall be angled symmetrically between adjacent steel beams where the Plans call for turns on the boardwalk alignment.

Steel members serving as railing support posts shall be set plumb vertically.  Top of steel posts shall be constructed to the line and grades shown on the Plans.

Welding type and size shall be shown in the Plans and according to the standard practices of American Welding society D1.1.

Fiberglass Grating.  Follow manufacturer’s recommendations for installation and safety procedures.  Install fiberglass grating panels in full lengths and widths whenever possible.  Panel ends shall rest supported securely on top of steel beams.  Fasten fiberglass grating panels onto steel beams using saddle type hold down clips, as recommended by the manufacturer.  A minimum of 4 clips per panel, spaced a maximum of 48 inches shall be used.  Any cuts made shall be sealed by manufacture recommend or approve methods.

Lumber.  Store lumber a minimum of 6 inches above ground on framework or blocking and protected with waterproof covering allowing for adequate air circulation and ventilation.  Do not store materials in wet or damp conditions.

Horizontal railing shall be constructed to line and grades shown on the Plans.  Fasten onto steel posts as shown on the Plans.  Install top rail plate with the wood’s natural curvature facing downward.

Paint.  Delivered paint shall be in sealed and intact containers.  Remove dirt, grease, oil and other construction debris before painting.  Ensure that surfaces to be painted are even, smooth, sound, clean, dry and free from defects affecting proper application.  Metal surfaces to receive paint shall be corrosion free.  Apply according to manufacturer’s recommendations.  Apply paint material evenly without runs, sags, or other defects.  Work each coat into the material being coated at an average rate of coverage recommended by the manufacturer.  Cover surfaces completely to provide uniform color and appearance.  Remove paint, stain, or other finish material where it has spilled or spattered.

1.	Boardwalk and Stairway Tread – Steel.

a.	Fiberglass Grating.  Factory Finish, Dark Gray.

b.	Wood, Visible Surfaces.  Semi-Transparent Oil Stain.

c.	Above Ground Nongalvanized Metal.  Primer and Enamel Paint.

2.	Stairway Tread – Aluminum.

a.	Structural Aluminum.  No finish required.

b.	Stair Tread.  No finish required.

c.	Handrail and Posts.  No finish required.

3.	Barrier Rail.

a.	Wood.  Semitransparent Oil Stain

b.	Metal. Primer and Enamel paint.

622-3.08 ALUMINUM STAIRWAY TREAD.  Submit show drawings for approval before construction of landings and stairs.

622-4.01 METHOD OF MEASUREMENT.  Add the following:  Boardwalk will be measured by the linear foot along the centerline of the boardwalk constructed, completed, and accepted.

***deleted***

Aluminum Stairway Tread will be measured for each stair risers constructed, completed, and accepted.  Aluminum Stairway Tread includes the entire assembly of the stairway from the boardwalk to the bottom of the stairway, including the handrailing.

622-5.01 BASIS OF PAYMENT.  Add the following:  Item 622(17) Boardwalk includes labor, material, and equipment to construct and paint or stain the boardwalk.

***deleted***

Labor material and equipment required to construct the aluminum stairway tread, attached landing, and handrail will be subsidiary to Item 622(30B) Aluminum Stairway .

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

622(17)	Boardwalk	Linear Foot

***deleted***

622(30B)	Aluminum Stairway Tread	Each

SECTION 640

# MOBILIZATION AND DEMOBILIZATION

Standard Modification

640-1.01 DESCRIPTION. Add the following:

6.	Comply with the Alaska Department of Labor and Workforce Development (DOLWD) requirements for Worker Meals and Lodging, or Per Diem; as described in their July 25, 2005 memo WHPL #197 (A2) and the State Laborer’s and Mechanic’s Minimum Rates of Pay (current issue).

Ensure subcontractors comply with the DOLWD requirements.

Ensure facilities meet the Alaska Administrative Code 8 AAC 61.1010 and 8 AAC 61.1040 Occupational Safety and Health Standards, 18 AAC 31 Alaska Food Code, and U. S. Code of Federal Regulations 29 CFR Section 1910.142 Temporary Labor Camps.

Do not consider the cost of Meals and Lodging, or Per Diem in setting wages for the worker or in meeting wage requirements under AS 23.10.065 or AS 36.05.

640-4.01 METHOD OF MEASUREMENT.  Delete the numbered paragraph 3 and substitute the following:

3. 	The remaining balance of the amount bid for Mobilization and Demobilization will be paid after all submittals required under the Contract are received and approved.

Add the following:

4. 	Progress payments for Worker Meals and Lodging, or Per Diem will be computed as equivalent to the percentage, rounded to the nearest whole percent, of the original contract amount earned.

640-5.01 BASIS OF PAYMENT.  Add the following pay item:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

640(4)    	Worker Meals and Lodging, or Per Diem 	Lump Sum

E27(1/01/06)

# SECTION 641

## EROSION, SEDIMENT, AND POLLUTION CONTROL

Special Provisions

641-1.02 DEFINITIONS.  Delete items No. 5, 6, and 7.

Replace item 8.  with the following:

- SWPPP (Storm Water Pollution Prevention Plan).  The Contractor’s plan for erosion and sediment control and storm water management.  The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project.  The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS.  Replace the first sentence in the second paragraph with the following: The Department will review the above submittals within 14 working days.

Delete the third and forth paragraph.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  Replace the second sentence with the following:  Follow the format presented in the most current Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing 5 acres or less.

Delete the last paragraph.

641-3.01 CONSTRUCTION REQUIREMENTS.  Replace the first sentence with the following: Do not begin ground-disturbing work until the Contractor receives written approval of the SWPPP and HMCP.

Delete item 1.

Replace the 3rd paragraph with the following: Implement temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

###### Delete paragraph 6, items 1 through 3, and paragraph 7.

Delete the 12 paragraph and items 1 and 2.

641-5.01 BASIS OF PAYMENT.  Add the following:  Temporary stream diversions through the work zones for sediment control and fish passage shall be paid for under Item 641 (2).

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provision

642-3.01 GENERAL. Add the following to the third paragraph: Before beginning work on the project, stake and reference the construction centerline. Reference the existing centerline 100 foot on tangents, and 50 foot intervals on curves, super elevations, transitions and cross-slopes. The reference stake shall be a minimum of 1 inch x 2 inch by 2 foot and shall show the offset distance to centerline and the station from the beginning of the project.

SECTION 643

#### TRAFFIC MAINTENANCE

#### Special Provisions

643-1.03 TRAFFIC CONTROL PLAN.  Add the following: The Contractor may request in writing a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan.  A minimum 12 feet lateral separation shall be maintained between the nonstreet legal vehicles and the motoring public. The Traffic Control Plan shall specify the traffic control devices that will be required for these operations.

Standard Modifications

643-2.01 MATERIALS.  Under Item 16. Flagger Paddles, replace the last sentence with the following:  Use reflective sheeting that meets AASHTO M 268 Type VIII or IX.  Use background colors of fluorescent orange on one side and red on the other side. E28(1/1/06)

Special Provisions

643-2.01 MATERIALS.

Add the following:

- Flexible Markers.  Refer to subsection 606-2.01 Materials.

Standard Modifications

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Immediately notify the Engineer of a traffic related accident that occurs within the project limits as soon as becoming aware of the accident.  (01/01/06)E28

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following:

Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station an employee at the encroachment to assist pedestrians and bicyclists past the construction activity.

Standard Modification

643-3.04 TRAFFIC CONTROL DEVICES.  In the sixth paragraph and also in Item 4.b., delete: “ATTSA” and replace with:  ATSSA (American Traffic Safety Services Association). E28(1/01/06)

Special Provision

643-3.04 TRAFFIC CONTROL DEVICES.  Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

- Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

10.	Maintain traffic at the location of Stariski Creek Bridge No. 667 by providing a temporary detour bridge.  Maintain traffic continuously unless other restrictions to traffic are addressed through approved Traffic Control Plans.  Do not route traffic onto the Detour for a duration longer than four months.

Construct the temporary detour bridge and approaches at the upstream side of the existing alignment and entirely within the right-of-way.

The temporary detour bridge shall conform to the following requirements:

- Design the detour to support HS 25 - 44 live loads, construction equipment live loads and to provide a moment and shear operating rating as specified in item 2.  Follow the strength design method (load factor design) according to the AASHTO Standard Specifications for Highway Bridges, 17th edition – 2002, with latest interims.

- The moment and shear operating rating of the temporary detour bridge must be equal to or greater than HS 42.  Determine the operating rating using the load factor method according to the latest edition of the AASHTO Manual for Condition Evaluation of Bridges, 2nd edition with latest interims and the AASHTO Standard Specifications for Highway Bridges, 17th edition – 2002, with latest interims.

- Provide a clear roadway width of not less than 32 feet for a double lane bridge.

- Provide NCHRP Report 350 Test Level 3 (TL-3) bridge railing, transitions, guardrails and guardrail terminals (railing or barrier system).

- Construct the detour so that vehicular traffic will move safely through the construction zone.

- Provide a single span bridge with a minimum streambed width of 30 feet that passes the maximum flow expected during the construction period.   The design flow shall not be less than the five year flood, which the Department estimates to be 590 cubic feet/second (cfs).  Provide a low superstructure elevation of at least one foot above the maximum discharge elevation expected for proposed temporary bridge.

- Provide design calculations, operating rating calculations and plans for the detour and temporary detour bridge stamped by an Engineer registered in the State of Alaska.

h.	Once the new bridge is open to the traveling public, remove the detour, including the temporary bridge and approaches.  Grade the area to the existing contour and revegetate.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.   Add the following:  Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-5,000 | $30 |
| 5,001+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Add the following:

The Contractor shall not restrict traffic during the following times:

- Monday through Friday 0600 through 0800.

- Monday through Thursday 1600 to 1800.

3.	Friday from 1500 to 1700.

4.	Sunday from 12:00 (noon) to Sunday at 2400.

5.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1500. on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1500 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1500 on the day before the holiday to 1500 on the Monday after the holiday.

The Contractor shall make every effort not to delay school buses through the construction work zone.

Lane restrictions, if allowed, shall be conducted so that no more than a 5 minute accumulated stopped delay, 40 vehicles, or ¼ mile (1,320 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 10 minute stopped delay, 80 vehicles, or ½ mile (2,640 feet) of traffic detained, will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

The Contractor shall obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  The Contractor shall make every effort not to delay school buses through the construction work zone.

Standard Modification

- Add the following new subsection:

643-3.11. HIGH VISIBILITY CLOTHING.  Ensure workers within project limits wear an outer visible surface or layer that complies with the following requirements:

1.	Tops.

Wear fluorescent vests, jackets, or coverall tops at all times.  Furnish each vest, jacket, or coverall top with at least one 360 degree horizontal retroreflective band around the torso; and two vertical retroreflective bands that begin at the horizontal band or lower in front, reach over the shoulder, and end at the horizontal band or lower in back.  Furnish each jacket and coverall top with two horizontal retroreflective bands on each sleeve; one above and one below the elbow.

2.	Bottoms.

Wear fluorescent red-orange pants or coverall bottoms during nighttime work (sunset to sunrise).  Flaggers wear fluorescent orange-red pants or coverall bottoms at all times.  Furnish each pants or coverall bottom with two horizontal retroreflective bands on each leg.

- Raingear.

Raingear tops and bottoms, when worn as the outer visible surface or layer, shall conform to the requirements listed in this subsection 643-3.11.

- Exceptions.

When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility clothing.

- Standard.

High visibility garments shall conform to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

Retroreflective bands are made of material conforming to either:

a.	A 2 inch wide strip, fluorescent yellow-green color, made of retroreflective microprisms; or

b.	A 2 inch wide strip, silver color, made of retroreflective lenses bonded to a durable cloth backing; and on 2 long edges apply 1 inch wide strips, fluorescent yellow-green color, made of durable cloth material.  Total width of band is 4 inch.

- Labeling.

Garments shall be labeled according to Section 10.2 of ANSI/ISEA-107-2004; except garments may be labeled to conform to ANSI/ISEA 107-1999 until 1/1/08.

- Condition.

Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.  Maintain retroreflective material to Level 2 standards.  (1/01/06)E28

Special Provision

643-4.01 METHOD OF MEASUREMENT. Add the following: No measurement required to provide a 24 hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to 643 items.

16.	Detour and temporary bridge. By the lump sum.  No measurement shall be made.

Standard Modifications

643-5.01 BASIS OF PAYMENT. 	Add the following:  Payment for high visibility clothing for workers is subsidiary to other items.  (1/01/06)E28

Special Provision

643-5.01 BASIS OF PAYMENT. Add the following:

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $2.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |

Payment for Item 643(15) the Engineer will pay Flagging on a contingent sum basis at the rate of $38.00/hour. The Engineer does not require a change order/directive for the flagging pay item. Flagging associated with Change Order work will be paid at the prices according to subsection 109-1.05 Compensation for Extra Work.  (01/01/06)R222USC04

Payment for Item 643(20A) Detour and Temporary Bridge includes resources required to provide, install, maintain, repair and remove the detour and temporary bridge and approaches.  Excavation, backfill, geotextile, grading the area after removal to match existing or proposed contours and pavement are subsidiary.  Traffic Control for the Detour will be subsidiary to Item 643(20A).  Striping for the Detour will be subsidiary to item 643(20A).  Traffic maintenance and permanent construction signs will be subsidiary to Item 643(20A) Detour and Temporary Bridge.

Furnishing, placing, and removing temporary access roads, as shown on the UASACE Permit, to Revegetation areas and Channel Realignment is subsidiary to Item 643(20A) Detour and Temporary Bridge.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

643(20A) 	Detour and Temporary Bridge 	Lump Sum

(01/01/06) R222USC04

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE. Delete the third, fifth, and seventh sentences of the first paragraph and the second paragraph in this subsection and substitute the following: Meet the following office requirements:

1.	A minimum of 1000 square feet of floor area. Divide the office area so that it contains an office room separated by a closable door. The office room shall have a minimum of 40 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	A minimum of two electrical outlets.

4.	Adequate parking for a minimum of 5 vehicles, with one disability parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

5.	Provide attached indoor plumbing with sanitary lavatory facilities and potable drinking water.

6.	Three telephone lines available at the project location.

7.	Located within 5 miles of the project.

8.	Provide one move in and one move out for state office furniture and equipment.

644-2.05 VEHICLES.  Delete first sentence in the first paragraph and substitute the following: Furnish and maintain two full-size four-wheel drive pickup or sport utility vehicle for exclusive use of the Department throughout the project.

Add the following: Furnish all fuels, maintenance and insurance.   If work continues after October 1, provide studded snow tires for vehicles provided for the Department’s use.

Equip vehicles with CB radios and yellow lightbars wired into the vehicle’s electrical system with a dash mounted switch easily accessible to the vehicle operator.  Provide Code 3; Model 6005H (formerly PE 6200 LE) lightbars, or approved equal.  Approved equals shall have the following characteristics:

- Four (4) 55 watt rotators with amber filters

- 1200 flashes per minute

- Two diamond mirrors

- 55” in length

Delete the last sentence.

644-4.01 BASIS OF PAYMENT. Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

Delete subparagraph “vehicles” and substitute the following:

Vehicle.  Per each vehicle provided.  If a replacement vehicle is necessary, no additional measurement for payment will be made.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(8)	Vehicle	Each

Add the following Section:	SECTION 645

## TRAINING PROGRAM

### Special Provisions

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "yellow pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish before contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and one or more of the following occurs: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Conractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the Contractor’s judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  Submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts.  In the event  a portion of the work is subcontracted, the Engineer shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor according to subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section before the Contractor’s submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the Contractor’s discretion, graduates early and is employed as a journey worker according to the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of other training program funds the Contractor may receive, unless such other funding sources specifically prohibits the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Noncompliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of training programs approved for the project.  No payment or partial payment will be made if the Contractor fails to do the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why the Contractor was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.  (10/29/91)S16

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1) 	Training Program, __ Trainees/Apprentices 	Labor Hour

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE Delete this subsection in its entirety and replace with the following: Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  If revisions are required, make them promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete item 2.  60-Day Preliminary Schedule.

Delete the first sentence of item 3.  Schedule Updates.  and substitute the following:  Hold job site progress meetings weekly with the Engineer for updating the CPM Schedule.  Meet with the Engineer weekly, or as deemed necessary by the Engineer.

(12/13/02)R261M98

Add the following Section:

## SECTION 647

## EQUIPMENT RENTAL

Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall be according to the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL.  Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS.  The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT.  Payment for Item 647(1) Wide Pad Dozer, 65 hp Minimum will be paid on a contingent sum basis at the rate of $125/hour on a per hour basis at the rate shown on the bid schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)	Wide Pad Dozer, 65 hp Minimum	Contingent Sum

(08/24/05)R15USC

***deleted***

SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 |  |  |
| 1 inch | 70-100 | 100 | 100 |
| ¾ inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

(6/22/04)R117USC04

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT. Add the following:

|  |  | Type IIA, IV | Type I, IIB, III |
| --- | --- | --- | --- |
| LA Wear, % max | AASHTO T 96 | 45 | 45 |
| Degradation Value, min | ATM 313 | 30 | 30 |
| Sodium Sulfate Loss % max (5 cycles) | AASHTO T 104 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP61 | 90,2 face | 80, 1 face |
| Thin-Elongated Pieces, max % 1:5 1:3 | ATM 306 | 8 20 | 8 - |
| Nordic Abrasion, max.% | ATM 312 |  |  |
| Absorption, max. % | AASHTO T85 | 2.0 |  |

TABLE 703-3

BROAD BAND GRADATIONS FOR ASPHALT CONCRETE PAVEMENT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V, VH |
| 1 inch | 100 |  |  |  | 100 |
| ¾ inch | 80-90 | 100 |  |  | 90-100 |
| ½ inch | 60-84 | 75-90 | 100 | 100 | 65-75 |
| 3/8 inch | 48-78 | 60-84 | 80-90 | 80-95 | 48-60 |
| No. 4 | 28-63 | 33-70 | 44-81 | 55-70 | 30-40 |
| No. 8 | 14-55 | 19-56 | 26-70 | 35-50 | 20-30 |
| No. 16 | 9-44 | 10-44 | 16-59 | 20-40 | < 22 |
| No. 30 | 6-34 | 7-34 | 9-49 | 15-30 | < 17 |
| No. 50 | 5-24 | 5-24 | 6-36 | 10-24 | < 14 |
| No. 100 | 4-16 | 4-16 | 4-22 | 5-15 | < 12 |
| No. 200 | 3-8 | 3-8 | 3-8 | 3-8 | 3-8 |

## (10/25/05)R199usc04

Add the following subsection:

703-2.13 STREAM BACKFILL.  Hard, durable, rounded stone and gravel, earth and sand.  Do not use materials that break up when alternatively frozen and thawed, or wetted and dried.  Do not include muck, frozen material, roots, sod, or other deleterious matter.  Material shall be uniformly graded stone, gravel and sand with 100 percent passing the 4 inch and no more than10 percent passing the #40 sieve.  ***deleted***

## SECTION 709

# REINFORCING STEEL AND WIRE ROPE

Special Provision

709-2.01 REINFORCING STEEL.  Add the following to the list of materials:

Low-Alloy Deformed Steel Bars for Concrete Reinforcement ASTM A 706

Add the following:

ASTM A 615, Grade 60 reinforcing steel may be substituted for non-weldable reinforcing steel.

SECTION 710

FENCE AND GUARDRAIL

Special Provision

710-2.03 CHAIN LINK FABRIC. Change Class D coating to Class C coating. (9/13/04)R274usc04

Replace Section 720 with the following:

SECTION 720

ELASTOMERIC PADS

720-2.01 Meet AASHTO M251, with the following revisions:

3.	GENERAL REQUIREMENTS.  Add the following:

3.6 Meet the requirements of the low temperature shear test, paragraph 9.3, AASHTO M 251-02 (22nd edition 2002), for a condition temperature of –37C+or-0.5C.

- 4.1 Properties of the Elastomer.  Replace the first sentence with the

following:  Use elastomeric compound in the construction of the bearings containing only virgin natural polyisoprene (natural rubber) as the raw polymer.  Do not use neoprene.  Properties and requirements elsewhere in AASHTO M251 pertaining solely to polychloroprene (neoprene) do not apply.

Add the following:

Use elastomer compound classified as low temperature Grade 5 and meeting the requirements of paragraphs 8.11 and 8.12 of AASHTO M251-04 (25th edition 2005).

5. 	FABRICATION

Add the following:

5.5.  Fabricate pads over ¾ inch thick with alternating laminations of elastomer and steel reinforcements.  The outside laminations must be steel with a minimum elastomer cover as shown on the Plans.

## SECTION 722

## BRIDGE RAILING

722-2.01 BRIDGE RAILING.

Anchor studs.  Add the following: “and ASTM A400, Class R-2, HR 1030.”

SECTION 726

TOPSOIL

Special Provisions

Add the following subsection:

726-2.02 SOIL/GRAVEL.  Combine 50% Topsoil with 50% Stream Backfill.  Refer to subsection 703-2.13 for Stream Backfill gradation.

APPENDIX A

## PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST