SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available from the Department of Transportation and Public Facilities located at 4111 Aviation Avenue in Anchorage.  Information may be obtained as follows:

1.	Copies for review and reproduction information may be obtained from the Plans Room, (907) 266-1674, for the following:

a.	Computations.

b.	Cross Sections

2.	The following report is available upon request in the Plans Room, (907)  266-1674:

-	Geotechnical Report entitled "Glenn Highway, MP 35-54, Project No. 57121 and Glenn Highway, MP 54-56, Project No. 58124".

3.	Utility agreements pertaining to the disposition of the load centers on this project are available for review at the office of the Traffic, Safety and Utilities Engineer, (907) 266-1531.

4.	An environmental evaluation addressing concerns and environmental commitments has been approved and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 266-1737.

PART 4

STANDARD MODIFICATIONS AND SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS FOR HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.27  Holidays.  Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third Monday in January.

3.	President's Day - Third Monday in February.

(5/7/91)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  Qualification of Bidders.  Delete the second paragraph.  (5/12/89)

102-1.06  Preparation of Proposal.  Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

(5/7/91)

102-1.07  Non-Responsive Proposals.  Delete item 3. in its entirety and substitute the following:

3.	If the bidder adds any provisions reserving the right to accept or reject any award or to enter into a contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to the bidder at any one bid letting, as  provided in Subsection 102-1.06.  (5/7/91)

102-1.07  Non-Responsive Proposals.  Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)

102-1.12  Addenda Requirements.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  Consideration of Proposals.  Add the following:  The apparent low bidder shall, within 5 working days following the bid opening, submit either a list of all firms with which the prime Contractor intends to execute subcontracts for the performance of the contract or a statement that the bidder intends to perform the work without subcontractors.  The list shall include the following information for each proposed subcontractor:

1.	name,

2.	business address,

3.	Alaska business license number,

4.	Contractor's registration number,

5.	the work to be performed, and

6.	the approximate dollar amount of the work to be performed.

If the apparent low bidder fails to submit either a list of subcontractors or a statement that the bidder intends to perform the work without subcontractors, the apparent low bidder will be found not to be a responsible bidder and may be required to forfeit the bid security.  The Department will then consider the next lowest bidder for the award of the contract.

If the apparent low bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess  of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this Subsection.

If a contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department, or

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the contract with the bidder involving work for which the subcontractor was  listed,

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or

9.	is determined by the Contracting Officer not to be responsible.

(9/1/90)

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  Changes.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)

Special Provisions

104-1.02  Changes.  Delete the first three paragraphs and substitute the following:  The Engineer reserves the right to make, in writing, at any time during the work, such changes in quantities and such alterations in the work as are necessary to satisfactorily complete the project.  Such changes in quantities and alterations shall not invalidate the contract nor release the surety, and the Contractor agrees to perform the work as altered.

If the alterations or changes in quantities significantly change the character of the work under the contract, whether or not changed by any such different quantities or alterations, an adjustment, excluding loss of anticipated profits, will be made to the contract.  The basis for the adjustment shall be agreed upon prior to the performance of the work.  If a basis cannot be agreed upon, then an adjustment will be made either for or against the Contractor in such amount as the Engineer may determine to be fair and equitable.

If the alterations or changes in quantities do not significantly change the character of the work to be performed under the contract, the altered work will be paid for as provided elsewhere in the contract.

The term "significant change" shall be construed to apply only to the following circumstances:

1.	When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction, or

2.	When a major item of work, as defined elsewhere in the contract, is increased in excess of 125 percent or decreased below 75 percent of the original contract quantity.  Any allowance for an increase in quantity shall apply only to that portion in excess of 125 percent of original contract item quantity, or in case of a decrease below 75 percent, to the actual amount of work performed.

(4/13/89)

104-1.03  Differing Site Conditions.  Delete in its entirety and substitute the following:  During the progress of the work, if subsurface or latent physical conditions are encountered at the site differing materially from those indicated in the contract or if unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the work provided for  in  the  contract, are  encountered at the site, the

party discovering such conditions shall promptly notify the other party in writing of the specific differing conditions before they are disturbed and before the affected work is performed.

Upon written notification, the Engineer will investigate the conditions, and if he determines that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any work under the contract, an adjustment, excluding loss of anticipated profits, will be made and the contract modified in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment which results in a benefit to the Contractor will be allowed unless the Contractor has provided the required written notice.

(4/13/89)

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  Authority of the Engineer.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02, Changes.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime  contract and  by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)

Special Provisions

105-1.06  Cooperation With Utilities.  Add the following:  The Contractor shall request locates from all the Utilities having facilities in the area.  Their telephone numbers are as follows:

Matanuska Telephone Association, Inc.        745-3121

Matanuska Electric Association, Inc.     800-478-5150

DOT/PF Maintenance & Operations (Palmer)     266-1584

ENSTAR Natural Gas Company (Wasilla)         376-7979

Rogers Cablevision                           373-2288

City of Palmer                               745-3271

All existing utilities shall remain in service until the new utilities are installed and put into service.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Prior to the relocation of the utility's facilities, construction stakes by the Contractor in the areas of utility conflicts may be required.  The Utility requesting the stakes, through the Engineer, shall be given fifteen days advance notice when the area will be staked.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the Utilities may prohibit the Contractor, through the Engineer, from working near the Utility's facilities when the ground is frozen.

There are various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.  The following specific coordination requirements are indicated for each Utility:

1.	ENSTAR NATURAL GAS COMPANY.  When excavation adjacent to buried gas lines results in exposing and undercutting of the lines, the Contractor shall continuously support the exposed lines.  The method of support and length of line to be exposed shall be coordinated with Enstar.  Backfill over buried lines shall be accomplished such as to not damage the buried lines.

A cathodic protection area sweep is required after all underground work has been completed and before paving begins.  The sweep will take one day to perform and will require three working days notice to ENSTAR prior to performing the work.  If any underground contacts are detected, additional time will be required to perform repairs.

ENSTAR will adjust or relocate the existing natural gas facilities at several locations along and crossing the Glenn Highway to accommodate the road construction between Sta. "GH" 1640+25 and Sta. "GH" 1728+30.  ENSTAR will install new plastic gas line between Sta. "GH" 1699+00 and Sta. "GH" 1753+00 and along Fishhook-Willow Road. This will include several crossings of the Glenn Highway.

a.	Sta. "GH" 1433+01 to Sta. "GH" 1640+00.  The existing natural gas facilities in this area are within the project limits however they do not conflict with the road construction and no relocation is required.

b.	Sta. "GH" 1640+25.  The existing 4-inch plastic gas line crossing the highway will be lowered in place to 4 feet below the new drainage ditch (25-ft Lt to 55-ft Lt).  This gas line is between existing water and sanitary sewer crossings of the Glenn Highway.  During the reconstruction of the water and sewer the gas line will be exposed.  This includes the "dogleg" in the gas line located on the east side of the highway.  The Contractor shall notify ENSTAR's Wasilla office (ATTN: Steve Walker), in writing, at least fifteen days prior to the excavation for the water and sewer lines.

c.	Sta. "GH" 1644+50.  The existing 4-inch plastic gas line crossing the Glenn Highway on the north side of the Palmer-Wasilla Highway is in conflict with the storm drain construction in the northwest and northeast quadrants of the intersection.  The crossing will be relocated to Sta. "GH" 1644+60 to avoid this conflict.  The Contractor shall stake the locations of the storm drain facilities as well as traffic signal facilities in these areas so that ENSTAR can determine the exact location of the relocated gas line.  The Contractor shall notify ENSTAR, in writing, at least fifteen days in advance of the actual construction of the above-mentioned facilities.

d.	Sta. "GH" 1643+35 to Sta. "GH" 1650+00, 138-ft Left of R-O-W Centerline.  The existing 4-inch plastic gas line that crosses the Palmer-Wasilla Highway and runs along the west side of the Glenn Highway may require adjustment in order to maintain four feet of cover under the storm drain pipe.  The Contractor shall stake the storm drain facility and notify ENSTAR in writing at least fifteen days prior to storm drain construction in this area to allow for adjustment of this gas line, if required.

e.	Sta. "PW" 531+61.  A new 10-inch casing will be installed across the Palmer-Wasilla Highway at Sta. "PW" 531+61.  Since the casing must be installed four feet below the finished ditch elevation, the Contractor shall notify ENSTAR at least fifteen days prior to excavation in this area so that ENSTAR can install the new facility.

f.	Sta. "GH" 1673+30.  The existing 2-inch plastic gas line (in 3-inch steel casing) that crosses the Glenn Highway, then continues south to Hemmer Road, then west along the north side of Hemmer Road, is not in conflict with the road construction.  The Contractor shall exercise caution when working around this existing gas line.

g.	Sta. "GH" 1685+80.  The existing 2-inch plastic gas line crossing the Glenn Highway will be replaced with a 4-inch plastic gas line at this location.  Service provided from the existing gas line may be interrupted for not more than 12 daytime hours.  The existing gas line will be abandoned and the new gas line shall be installed during the backfill operation for the road cut.  The new gas line will be placed at an elevation to maintain four feet of cover under the finished road grade.  The Contractor shall notify ENSTAR, in writing, at least fifteen days prior to backfill to allow for scheduling of crews.

h.	Sta. "GH" 1689+50 to Sta. "GH" 1693+50.  The existing 4-inch plastic gas line along the east side of the Glenn Highway south of and up to W. Dolphin Avenue will be lowered as required to maintain four feet of cover under the new special ditch.  The Contractor shall slope stake this area and notify ENSTAR to allow for adjustments, if required.

i.	Sta. "GH" 1693+50 to Sta. "GH" 1699+00.  The existing 4-inch plastic gas line that continues along the east side of the Glenn Highway is not in conflict with the proposed construction.

j.	Sta. "GH" 1699+00 to Sta. "GH" 1702+05.  A new 2-inch plastic gas line will be connected to the existing 4-inch plastic gas line on the east side of the Glenn Highway at Sta. "GH" 1699+00 (W. Eagle Avenue).  The new gas line will cross the highway at this station (in a joint-use trench with Matanuska Telephone Association) and then continue northerly along the west side of the highway to Sta. "GH" 1702+05.  The new gas line will be installed five feet inside the right-of-way.

k.	Sta. "GH" 1709+05 to Sta. "GH" 1711+85.  A new 2-inch plastic gas line will be installed by ENSTAR along the west side of the Glenn Highway beginning at Sta. "GH" 1709+05.  It will continue north where it will connect to the two, 2-inch plastic gas lines that cross Marsh Road at Sta. "M" 29+55 ("GH" 1711+85).  The new gas line will be installed five feet inside the west right-of-way.  The Contractor shall notify ENSTAR, in writing, after excavation and at least fifteen days prior to backfill so that ENSTAR can install the new facility.

l.	Sta. "GH" 1712+00.  The existing 4-inch plastic gas line crossing the Glenn Highway on the north side of the Marsh Road intersection will be relocated to Sta. "GH" 1712+30.  The relocation is necessary to avoid conflict with the construction on the existing water line that runs east-west along Marsh Road, and also with the new culvert end section in the northwest quadrant of the intersection.  The new crossing will be installed (bore), by ENSTAR, four feet below the new finished grade elevation prior to the road construction so that the 4-inch plastic feeder gas line along the north side of Marsh Road can be abandoned to facilitate the water line reconstruction.

m.	Sta. "M" 25+00 to Sta. "M" 31+00.  An existing 4-inch plastic gas line that runs along the north side of Marsh Road is within the area of water line reconstruction.  It will also be in the new slope limits.  The gas line will be temporarily abandoned, then reinstalled, to facilitate the water line construction.  The Contractor shall notify ENSTAR, in writing, at least fifteen days prior to the excavation in this area to allow for scheduling of crews.  During the backfill operation the gas line will be reinstalled at an elevation that maintains four feet of cover under the new side slopes.

n.	Sta. "GH" 1712+00 to Sta. "GH" 1716+00.  The existing 4-inch plastic gas line along the west side of the Glenn Highway will be relocated  five feet inside the west right-of-way.  MTA will be located three feet inside the west right-of-way.  This relocation will keep the utilities as close to the slope limits as possible.  The Contractor shall slope stake this area and notify ENSTAR so that the limits of the gas line relocation can be determined.  In those areas requiring relocation the gas line will be installed prior to excavation at an elevation that will maintain four feet of cover under the new backslope.  This section of 4-inch pipeline and the previously-mentioned 4-inch pipeline along Marsh Road provide a looped feed to Cedar Hills Subdivision.  One of the two sections must be maintained at all times to provide flow from the east side of the Glenn Highway to Cedar Hills customers.

o.	Sta. "GH" 1716+00 to Sta. "GH" 1719+50.  The existing 4-inch plastic gas line along the west side of the Glenn Highway is not in conflict with the proposed road construction.  The Contractor shall exercise caution when working around this gas line.

p.	Sta. "GH" 1719+50 to Sta. "GH" 1723+50.  The existing 4-inch plastic gas line along the west side of the Glenn Highway between Sta. "GH" 1719+50 and Sta. "GH" 1723+50 is in conflict with the proposed road improvements.  ENSTAR will lower the gas line prior to excavation to an elevation that will maintain four feet of cover under the new backslope.  The Contractor shall stake the slope limits and shall notify ENSTAR, in writing, at least fifteen days prior to excavation in this area.

q.	Sta. "GH" 1723+50 to Sta. "GH" 1727+90.  The existing 4-inch plastic gas line along the west side of the Glenn Highway is not in conflict with the proposed road construction.  The Contractor shall exercise caution when working around this gas line.

r.	Sta. "GH" 1725+25.  The existing 2-inch plastic gas line that crosses the Glenn Highway approximately 300 feet south of Pioneer Parkway may require adjustment to maintain four feet of cover under the new ditches.  The Contractor shall notify ENSTAR, in writing, fifteen days prior to excavation in this area so that the required adjustments can be determined.

s.	Sta. "GH" 1729+04 to Sta. "GH" 1753+50.  A new 4-inch plastic gas line will enter the Glenn Highway right-of-way at Sta. "GH" 1729+04 and will continue north along the west side of the Glenn Highway staying five feet inside the west right-of-way and outside the new slope limits where possible.  The Contractor will slope stake so that ENSTAR can adjust the location of the new gas line to stay outside the slopes and maintain four feet of cover under the finished grade.  The new 4-inch gas line will terminate on the south side of FIshhook-Willow Road at approximate Sta. "GH" 1751+46.5.  A new 6-inch gas line will continue north, across Fishhook-Willow Road to Sta. "GH" 1753+50.  A spare 10-inch casing will be installed adjacent to this crossing.  New 2-inch crossings will be made from the west side to the east side of the highway at approximate Sta. "GH" 1736+70 and "GH" 1745+67.  The Contractor shall notify ENSTAR, in writing, at least fifteen days prior to backfill so that these crossings can be installed.  Between approximate Sta. "GH" 1735+50 and "GH" 1736+50 ENSTAR will install the new gas line outside of the existing water tower fence and four feet under the existing 12-inch underground drain pipe.

t.	Station "FH" 20+15 to Station "FH" 32+10.  A new 6-inch plastic gas line will connect to the Fishhook-Willow crossing outlined above and will run along the south side of Fishhook-Willow Road past the project limits to Werner Road.  The Contractor shall provide the necessary survey information for ENSTAR to determine the elevation and alignment of both the relocated and proposed facilities.  The Contractor shall provide fifteen days advance written notice to ENSTAR's Wasilla office to allow for scheduling of crews.

2.	MATANUSKA TELEPHONE ASSOCIATION, INC.  Matanuska Telephone Association, Inc. (MTA) will relocate conflicting aerial and underground telephone facilities along and crossing the Glenn Highway between M.P. 35 and 56 to accommodate the highway project.  The MTA relocation design is included in the plans as "UT" sheets.  The new facilities must be in place and operational prior to abandonment or retirement of existing facilities.

The Contractor shall provide MTA fifteen days advance written notice that relocation on the project is required.  Separate notification for the

coordination and installation of the following road crossings is also required:

"GH" 1699+00  (joint Enstar/MTA trench)

"GH" 1715+10

"GH" 1820+00

"GH" 1877+40  (Service to Wolf Country)

"GH" 1971+40

Access Road 12+25

Crossings in proposed cut sections will be installed after excavation and prior to fill.  Crossings in fill sections will be installed prior to placement of Selected Material, Type B.

a.	"GH" Sta. 1685+36 to 1735+43.  The existing underground and aerial telephone facilities along and crossing the Glenn Highway between Sta. 1685+36 and Sta. 1735+43 will be relocated to a new underground configuration adjacent to the east right-of-way line.

The installation of a new underground telephone cable along the north side of Marsh Road will be installed after placement of insulation board over the existing water line and prior to final slope construction.

b.	"GH" Sta. 1803+80 to 1823+12.  The existing underground telephone facilities along and crossing the Glenn Highway at Farm Loop Road will be relocated to allow for highway construction.  The Contractor is required to work around the existing underground cables until the new cables are installed and operational.

c.	"GH" Sta. 1871+00 to 1880+40.  Existing aerial services along and crossing the Glenn Highway between Collier Road and Rue Road will be relocated to a new underground cable to be installed adjacent to the northwest right-of-way line.

d.	"GH" Sta. 1903+00 to 1909+50.  The existing underground 25 pair cable along the left side of the Glenn Highway will be relocated along the northwest right-of-way line to accommodate proposed Glenn Highway slope limits and realignment of the Soapstone Road approach between Sta. 1903+00 and Sta. 1909+50.

e.	"GH" Sta. 1972+80.  MTA will install a new underground cable across the Glenn Highway at Sta. 1971+40 as replacement for the existing aerial crossing at Sta. 1972+80.

f.	Access Road Sta. 12+25.  MTA will install a new underground cable between existing poles at "GH" Sta. 2060+08, 177-ft right and Sta. 2061+70, 51-ft right to allow for construction of the proposed Access Road.

The existing underground cables between "GH" Sta. 2061+70 and Sta. 2068+00 will be relocated and adjusted to accommodate proposed Glenn Highway slope limits and the proposed Access Road approach.

3.	CITY OF PALMER (Water and Sewer)

Sewer.  A new 10-inch, Class 50 ductile iron sewer main will be constructed across the Glenn Highway at Sta. "GH" 1640+16.  The new crossing is for future expansion and will not be connected to the existing sanitary sewer collection system.

The existing 8-inch A.C. sewer main crossing the Glenn Highway at Sta. "GH" 1640+24 shall remain in service at all times.  Insulation board shall be placed one foot above the existing pipe as shown on the plans.

Water.  The existing 6-inch steel water line crossing the Glenn Highway at Sta. "GH" 1640+50 will be replaced with new 8-inch ductile iron pipe between approximately 146 left and 85 right.

The existing 6-inch steel water line adjacent to the Glenn Highway between Sta. "GH" 1640+50, 56 right and Sta. "GH" 1643+84, 56 right will be relocated to the east to approximately 85 right of centerline.

Insulation board will be placed one foot above the existing 8-inch ductile iron water line along Marsh Road and crossing the Glenn Highway at Sta. "GH" 1712+25.

The Contractor shall coordinate the installation of water and sewer crossings at Sta. "GH" 1640+16 and Sta. "GH" 1640+50 with Enstar Natural Gas and Matanuska Electric Association to allow for:

a.  	Adjustment of the existing gas crossing at Sta. "GH" 1640+33,

b.	Placement of two, 5-inch rigid metal electrical conduits across the Glenn Highway at Sta. "GH" 1640+10,

c.	Placement of protective conduit around an existing three-phase underground electrical conductors at approximately 125 feet right of centerline.

4.	MATANUSKA ELECTRIC ASSOCIATION.  Matanuska Electric Association (MEA) will be retiring the existing three phase overhead facility crossing the Glenn Highway at Sta. 1643+45, between "PW" Sta. 529+60, 35-ft Rt, and "EA" Sta. 102+20, 30-ft Rt.  The replacement facility will be installed underground with MEA installing two 5-inch rigid steel conduits (RSC) crossing the Glenn Highway at Sta. 1640+10.  This crossing will be installed in conjunction with the sewer line relocation.  MEA will install the conduits in the Contractor's trench during the backfill operation at an elevation 4 feet below finish grade.  MEA will require 2 weeks prior written notice for coordination of the crossing.

MEA must have the underground relocation complete and energized around the intersection prior to retiring the overhead facilities.

Prior to the water and sewer line relocations at approximate Sta. 1640+16 and Sta. 1640+47, MEA will uncover the existing three phase underground circuit and place protective conduit around the facility.  Temporary support of the conduit and cable will be required during excavation. The method of support will require MEA approval.  Any work within ten feet of this or any other MEA facility will require prior notification and coordination with the utility.

MEA's remaining relocation consists of poles, down guys or anchor relocations due to slope or alignment conflicts.  This work is detailed in the "UE" sheets of the contract.

5.	ROGERS CABLESYSTEMS OF ALASKA, INC.  Rogers Cable will be replacing their aerial facilities from Sta. 1699+20 Rt to 1735+60 Rt with new aerial cables attached to the existing or relocated Matanuska Electric Association poles.  The new cables must be in place and spliced over prior to retirement of the existing facilities.

At Sta. 1727+50 Rogers Cable will be installing an underground crossing of the Glenn Highway, with cable conduit.  This crossing will be installed in conjunction with the Contractor's excavation and backfill operation, with Rogers installing the conduit in the excavation at the maximum cut.  Rogers cable will require 2 weeks prior written notice for coordination of the installation.

Standard Modifications

105-1.12  Load Restrictions.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless otherwise allowed by an approved Traffic Control Plan.  (5/7/91)

Special Provisions

105-1.15  Project Completion.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work scheduled under Subsection 618-3.04, Maintenance of Seeded Areas and subsection 621-3.04, Period of Establishment, a letter of project completion will be issued by the Engineer.  (2/1/90)

105-1.17  Claims for Adjustment and Disputes.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (12/26/90)

Add the following:  Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/29/87)

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  Source of Supply and Quality Requirements.  Add the following:  All steel products which are to be incorporated into the work shall be produced in the United States except that minor amounts of steel products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel products into the project.

(11/9/84)

106-1.02  Local Material Sources.  Under Item 1. General, add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)

Add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement will be given to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01  Laws to be Observed.  Add the following:  Specific Equal Employment Opportunity Responsibilities of Federal-Aid Construction Contractors.

1.	General

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form 25D-55) and these Special Provisions which are imposed pursuant to Section 140 of Title 23, U.S.C., as established by Section 22 of the Federal-Aid Highway Act of 1968.  The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the equal employment opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State highway agencies and the Federal Government in carrying out equal employment opportunity obligations and in their review of his/her activities under the contract.

c.	The Contractor and all his/her subcontractors holding subcontracts not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of equal employment opportunity:  (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as Contractors and subcontractors.)  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.

2.	Equal Employment Opportunity Policy

The Contractor will accept as his operating policy the following statement which is designed to further the provision of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include:  employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprenticeship and/or on-the-job training.

3.	Equal Employment Opportunity Officer

The Contractor will designate and make known to the Engineer and equal employment opportunity officer (hereinafter referred to as the EEO Officer) who will have the responsibility for and must be capable of effectively administering and promoting an active Contractor program of equal employment opportunity and who must be assigned adequate authority and responsibility to do so.

4.	Dissemination of Policy

a.	All members of the Contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the Contractor's equal employment opportunity policy and contractual responsibilities  to  provide equal employment opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

(1)	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the Contractor's equal employment opportunity policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor's equal employment opportunity obligations within thirty days following their reporting for duty with the Contractor.

(3)	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the Contractor's procedures for locating and hiring minority group employees.

b.	In order to make the Contractor's equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

(1)	Notices and posters setting forth the Contractor's equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The Contractor's equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

5.	Recruitment

a.	When advertising for employees, the Contractor will include in all advertisements for employees the notation:  "An Equal Opportunity Employer."  All such advertisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority group applicants, including, but not limited to, State employment agencies, schools, colleges and minority group organizations.  To meet this requirement, the Contractor will, through his EEO Officer, identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority group applicants may be referred to the Contractor for employment consideration.

In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor's compliance with equal employment opportunity contract provisions.  (The U.S. Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or women, or obligates the Contractor to do the same, such implementation violates Executive Order 11246, as amended.)

c.	The Contractor will encourage his present employees to refer minority group applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures with regard to referring minority group applicants will be discussed with employees.

6.	Personnel Actions

Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The Contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The Contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with his obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the Contractor will inform every complainant of all of his avenues of appeal.

7.	Training and Promotion

a.	The Contractor will assist in locating, qualifying, and increasing the skills of minority group and women employees, and applicants for employment.

b.	Consistent with the Contractor's work force requirements and as permissible under Federal and State regulations, the Contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.  In the event the Training Special Provision is provided under this contract, this subparagraph will be superseded as indicated.

c.	The Contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.	The Contractor will periodically review the training and promotion potential of minority group and women employees and will encourage eligible employees to apply for such training and promotion.

8.	Unions

If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and female employees.  Actions by the Contractor either directly or through a Contractor's association acting as agent will include the procedures set forth below:

a.	The Contractor will use best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

b.	The Contractor will use best efforts to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The Contractor is to obtain information as to the referral practices and policies of the labor union except that the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the Contractor, the Contractor shall so certify to the State highway department and shall set forth what efforts have been made to obtain such information.

d.	In the event the union is unable to provide the Contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the Contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minority group persons and women.  (The U.S. Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer  minority  employees.)  In the event the union referral practice prevents the Contractor   from   meeting   the  obligations pursuant to Executive Order 11246, as amended, and these special provisions, such Contractor shall immediately notify the State highway agency.

9.	Subcontracting

a.	The Contractor will use his best efforts to solicit bids from and to utilize minority group subcontractors or subcontractors with meaningful minority group and female representation among their employees.  Contractors shall obtain lists of minority-owned construction firms from State highway agency personnel.

b.	The Contractor will use his best efforts to ensure subcontractor compliance with their equal employment opportunity obligations.

10.	Records and Reports

a.	The Contractor will keep such records as are necessary to determine compliance with the Contractor's equal employment opportunity obligations.  The records kept by the Contractor will be designed to indicate:

(1)	the number of minority and nonminority group members and women employed in each work classification on the project,

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to Contractors who rely in whole or in part on unions as a source of their work force),

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority group subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such records must be retained for a period of three years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the State highway agency and the Federal Highway Administration.

c.	The Contractor will submit an annual report to the State highway agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form PR 1391.  If on-the-job training is being required by "Training Special Provision", the Contractor will be required to furnish State of Alaska Form 25A312.

(4/8/83)

107-1.08  Railway-Highway Provisions.  Delete the second paragraph and add the following:

1.	Definition of Terms.

a.	Railroad's Manager of Telecommunications and Signaling - the person employed by the Railroad as head of its Telecommunications Department or his authorized representative.

b.	Railroad's Chief Engineer - the person employed by the Railroad as head of its Engineering Department or his authorized representative.

c.	Railroad's Contracting Officer - the person authorized by the Railroad to execute contractual agreements on behalf of the Railroad.

d.	Facility - any improvements owned by the Department which are to be placed on Railroad Property in accordance with a written permit executed by the Railroad and the Department.

e.	Permit Area - the space on Railroad property that is or will be occupied by the Facility plus reasonable working area and reasonable ingress and egress to the Facility.

f.	Railroad - the Alaska Railroad Corporation, P.O. Box 107500, Anchorage, Alaska  99510-7500.

g.	Railroad Property - all lands owned or withdrawn for the use of the Railroad, in and including the track right-of-way and communications pole right-of-way.

h.	Trackwork - all work on the line from the top of subgrade to the top of rail, including geotextile, when required.

i.	Track Materials - all hardware, excluding signals and controllers, associated with the running of a railroad.

2.	General Requirements.

a.	All construction, reconstruction, operation and maintenance on the Railroad Property shall be performed in compliance with these specifications.

b.	Failure to comply with these specifications  shall result in the suspension of all work on Railroad Property.  The Contractor shall comply immediately upon notification from the Department, either verbal or written.

c.	All negotiations between the Railroad and the Contractor shall be handled through the Department.

d.	All work on or about the Railroad Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with the approved Railroad practices, and as specified herein.  Railroad traffic and property shall be protected at all times.

e.	The safety and continuity of the operation of the railroad traffic shall be of first importance and shall be at all times protected and safeguarded.  The Contractor and his subcontractors shall perform and arrange their work accordingly.  The Railroad's Chief Engineer shall decide all matters involving the safety of Railroad facilities and the operation of it's railroad.  The approval of the Railroad's Chief Engineer, when given, shall not be considered as a release from responsibility or liability for any damage which the Railroad may suffer or for which it may be liable, as a result of the acts of the Contractor, his subcontractor or employees.

f.	Whenever in the opinion of the Railroad's Chief Engineer, the construction may cause a hazard to the safe operation of the Railroad, the Railroad may, at its discretion, place at the site of the work the required number of qualified employees to protect its operations.  The providing of such employees and such other precautions as may be taken shall not relieve the Contractor and his subcontractors from liability for the payment of damages caused by their operations.  The Railroad shall be the sole judge of necessity, as to the number and classification of employees required.  All Railroad cost and expense for providing such employees shall be collected from the Contractor, except for flagging which shall be paid for as described in Subsection 107-1.08.5.b.

g.	The Contractor shall be responsible for maintaining sight triangles at existing railroad crossings as well as at any temporary crossings within the project limits and at any railroad crossing outside the project limits that is designated and used as an alternate route for traffic.

3.	Insurance Requirements.

a.	The Contractor shall comply with all insurance requirements and conditions specified under Subsection 103-1.05, except that the following minimum limits shall apply for Comprehensive or General Liability Insurance:

Bodily Injury - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Property Damage - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Blanket Contractual

b.	Prior to commencement of work on Railroad Property, the Contractor shall provide evidence of Railroad Protective Liability insurance (Alaska Railroad and State of Alaska as insureds) with the following limits:

Bodily Injury - $2,000,000 per occurrence

Property Damage - $2,000,000 per occurrence

4.	Notice.

a.	The Contractor shall give written notice to the Department and the Railroad not less than 10 days in advance of the commencement of any construction, reconstruction or major maintenance activity on Railroad Property, in order that the necessary arrangements may be made for the protection of the Railroad's operation.  This notice shall include the proposed schedule of work, and the names of the subcontractors who may also be working on Railroad Property.

b.	A preconstruction meeting shall be held with the Railroad's Chief Engineer and representatives of the Department and Contractor prior to the commencement of any work on Railroad Property by the Contractor or his subcontractors.

5.	Flag Protection and Protection of Railroad Traffic.

a.	Whenever Railroad flag protection is required in the specifications, this flag protection shall be provided by person(s) authorized by the Railroad.  Each person so authorized shall have met the Railroad's qualifications for flagmen.  Railroad flag protection is to insure the safe movement of trains and other rail traffic and shall be done in strict accordance with the Railroad rules on flagging.

b.	The Contractor shall, during the progress of the work, furnish as many qualified flagmen, as in the opinion of the Railroad, may be required for the adequate protection of the Railroad traffic.  If Railroad employees are used as flagmen, all Railroad expenses for providing such flagmen shall be reimbursed by the Department, except for flagging as described in Subsections 107-1.08.8.b and c., in which case the Railroad expenses shall be paid by the Contractor.  If the Contractor calls for flagmen and, through no fault of the Department or the Railroad, the flagmen are not needed, payment shall be deducted from monies due the Contractor.

c.	Vehicles and other construction equipment shall not be parked or operated closer than 20 feet from centerline of any track without Railroad flag protection provided in accordance with Subsection 107-1.08.5.a.

d.	The Contractor shall arrange with the Railroad to keep himself informed of the time of arrival of all trains and shall entirely stop any of the operations which might be or cause a hazard to the safe passage of the train past the site of the work from 10 minutes before the expected arrival of the train until the train has passed.

6.	Train Delays.

a.	All work on Railroad property shall be conducted in such a manner as to prevent delays to trains or other rail traffic operated by the Railroad.

b.	Should any of the Contractor's or subcontractor's actions or activities cause delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

| Passenger Trains | $50 per minute for each delay. $3,000 minimum charge. |
| --- | --- |
| All other trains and rail traffic | $50 per minute for each delay over five minutes. $1,500 minimum charge. |
| Rail barges, train-ships or other connecting carrier vessels | No charge for delays of an hour or less. $1,000 per hour for each hour or any part of an hour thereafter, with a minimum charge of $6,000. |

c.	Delay time will be taken from the train sheet in the Railroad Dispatcher's Office, in Anchorage, (265-2649) for all delays and such train sheet shall be the official document by which the length of time a train is delayed will be determined.  If another crew is needed to relieve the original crew, the charge shall also apply to the second crew.  If such delay causes a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by said train sheet.

7.	Protection of Railroad Communication Lines.

a.	All work on Railroad Property shall be conducted in such a manner as to protect the Railroad's communications facilities at all times from outages resulting directly or indirectly from the Contractor's or his subcontractor's operations.

b.	Should any of the Contractor's, or his subcontractor's operations cause outages to said communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

| Open wire communication circuits | $1.00 per minute per circuit |
| --- | --- |
| Communication cable | $5.00 per minute per cable |

c.	A minimum charge of $250 will be made for each outage.  The outage time shall be that as established by the Railroad's Test Board, Anchorage.

d.	There shall be no equipment worked or excavation within 15 feet of any Railroad communication pole guy, anchor, or other communications apparatus unless authorized in advance by the Railroad's Manager of Telecommunications and Signaling.

8.	Railroad Crossings.

a.	Whenever automatic railroad crossing signals are in the permit area, these signals must remain in operating condition at all times.  If, as a result of the Contractor's activities on the facility, the signals become inoperable the crossing shall be continuously protected in accordance with Subsection 107-1.08.5. until the signals are again operable.

b.	When regular railroad crossings are used as haul routes inside or outside the permit area, flagmen shall be provided by the Contractor for said crossings in all situations at the discretion of the Railroad.

c.	Temporary road crossings may be installed, provided the Contractor has acquired from the Railroad a temporary road crossing permit for said crossing.

The temporary crossing shall be constructed to the standards specified in the temporary crossing permit.  All protective signs required by the Railroad shall be provided and properly maintained by the Contractor.  When a temporary railroad crossing is in use, Railroad flag protection shall be provided at all times in accordance with Subsection 107-1.08.5.  When not in use during the winter season, the temporary crossing shall be removed unless specifically allowed in the temporary crossing permit.  Upon completion of the work or termination of the temporary crossing permit, the temporary railroad crossing shall be removed and the area restored to its original condition.

d.	The flange ways of all road crossings used by the Contractor or subcontractor as haul routes or temporary road crossings shall be kept free of gravel at all times and shall otherwise be maintained to the satisfaction of the Railroad's Chief Engineer.

e.	When a temporary or private road crossing is not in use, the Contractor shall provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

9.	Power and Communication Lines.

a.	All power and communication lines shall be designed and constructed in accordance with National Electric Safety Code (NESC).

b.	Underground power and communication lines shall be installed in accordance with Subsection 107-1.08.10.  Whenever an underground power or communication line crosses underneath a track, a casing pipe shall be installed for carrying such lines.

c.	The minimum clearance above the top of a rail of the Railroad track shall be in accordance with the NESC, plus 6 inches to allow for future grade raises.

d.	The minimum clearance above the Railroad communication lines shall be in accordance with the NESC.

e.	Additional lines may not be added, or the characteristics of the line(s) changed without written approval of the Railroad's Contracting Officer.

f.	Wires shall be strung across the Railroad tracks only when Railroad flag protection is provided in accordance with Subsection 107-1.08.5.

g.	No wires shall be strung across the Railroad's communication lines without first receiving approval from the Railroad's Manager of Telecommunications and Signaling therefor, and such work must be accomplished only at a time and in a manner prescribed by said Manager of Telecommunications and Signaling.

10.	Underground Facilities.

a.	All underground utilities, including culverts, pipelines and underground power and communication lines, on Railroad property shall conform to the current AREA Specifications.

b.	Unless another method is authorized in advance and in writing by the Railroad's Chief Engineer, all underground facilities shall be installed under tracks and roads by boring, jacking or tunneling.

c.	Boring, jacking and tunneling shall be done under Railroad tracks only when Railroad flag protection is provided in accordance with Subsection 107-1.08.5.

d.	The proposed plan for boring, jacking or tunneling shall be approved by the Railroad's Chief Engineer prior to commencing the operation.

e.	All boring, jacking or tunneling headings shall be continuously protected against any loss of ground material by shoring or cribbing as necessary.

11.	Open Trenching.

a.	Only when authorized in advance and in writing by the Railroad's Chief Engineer shall any portion of the track be removed to allow trenching for installation of the facility.

b.	If allowed to open trench, the track may be removed from service only at the time authorized by the Railroad's Chief Engineer and shall be restored to service within the time period specified by the Railroad's Chief Engineer.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in accordance with Subsection 107-1.08.6., whichever is greater and shall be collected from the Contractor.

c.	All work on track materials shall be accomplished by qualified trackmen.

d.	Only that portion of the track structure necessary to excavate, stockpile and install the facility shall be removed.  All track material removed shall be handled, stockpiled, and relaid in a manner as to avoid damage.  Any material which is damaged shall be replaced by the Contractor at his own expense.

e.	The backfill of the trench under the track and in the roadbed prism shall be of the same type of material as taken out, except the top 2 feet shall be clean pit run gravel.  Backfilling and compaction in the area affecting the roadbed prism shall be in accordance with the requirements of Section 204, Structure Excavation for Conduits and Minor Structures.

f.	The ballast used in replacing the track shall be equal in depth and quality to that which was removed.  The track shall be relaid and brought to original grade in accordance with standard Railroad practices.

12.	Excavations.

a.	Unless authorized in advance and in writing by the Railroad, the top of any excavation shall not be within 20 feet of center line of any track.

b.	No water shall be allowed to stand in open excavations in the track area.

c.	Bridging and shoring shall be adequate to safely carry Railroad traffic and the decision of the Railroad pertaining to same shall be final.

d.	All open excavations shall be continuously protected by flags, barricades or watchmen, as directed by the Railroad.

e.	No excavation shall be left open more than three days, unless authorized by the Railroad's Chief Engineer.

f.	The Railroad embankment, and cut slopes, shall not be disturbed any more than necessary to accommodate the construction and shall be left in a stabilized condition.

g.	Railroad ditches, culverts and roadways shall be kept clean and free of rock, gravel, construction debris and equipment at all times.

13.	Railroad Inspectors.

a.	The Railroad may furnish an inspector during the periods of construction on Railroad Property.  The Railroad inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary.  The Railroad inspector will work directly with the representative of the Department and the decision of the Railroad inspector in matters pertaining to Railroad operations and safety shall be final.  In the event more than one shift is worked, a Railroad inspector will be required for each shift.  Presence or absence of a Railroad inspector shall not relieve the Contractor of liability for damage done to property of the Railroad, Railroad lessees or permittees having installations on Railroad Property.

14.	Use of Explosives.

a.	The use of explosives shall be done in compliance with all applicable Federal, State and local laws and ordinances regarding the same.

b.	No blasting of any kind will be permitted unless the Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, Railroad flag protection in accordance with Subsection 107-1.08.5., shall be provided on each side of the blast area by the Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

c.	The Contractor will notify the Alaska Railroad Inspector and the Engineer of the exact time of each blast at least two hours in advance.

15.	Snow Removal.

a.	Snow removal operations shall be conducted in such a manner as to not place snow (1) upon the tracks of the Railroad, (2) where it interferes with the normal operation of the automatic crossing signals, or (3) impairs the visibility of either highway or rail traffic  at the crossing.

b.	Snow removal operations shall be conducted in accordance with Subsection 107-1.08.5.

16.	Clean-Up.

a.	At all times, all work and activities on the Facility shall be accomplished in such a manner as to keep the Railroad Property in a neat and orderly condition satisfactory to the Railroad.

b.	Upon completion of work, all equipment and unused materials shall be removed and the Railroad property shall be left in a neat and clean condition satisfactory to the Railroad.

c.	Should the Contractor or subcontractor fail to comply with Subsections 107-1.08.16.a. and 16.b., the Railroad may perform the required clean-up.  All Railroad costs and expenses for performing this work shall be collected from the Contractor.

17.	Payment Guarantee.

a.	The Department shall withhold 10 percent of the contract price or $10,000.00, whichever is smaller, from the final payment to apply against damages or other direct costs which may be assessed by the Railroad as a result of the Contractor's operations.

b.	The amount withheld above shall not be released until after the Department has received a written statement from the Railroad's Contracting Officer agreeing to release the payment.

(5/7/91)

107-1.11  Protection and Restoration of Property and Landscape.  Add the following after the third paragraph:  The Contractor shall report immediately to the Engineer any hazardous material discovered, exposed, or released into the air, ground or water during construction of the project.  The Contractor shall also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery.  Hazardous materials include, but are not limited to, petroleum products, oils, solvents, paints and chemicals that are toxic, corrosive, explosive or flammable.  (5/7/91)

The Contractor shall not excavate, nor use for fill, any material containing hazardous substances or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected of containing hazardous substances or petroleum fuels.

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall  obtain a Temporary Water Use Permit from the 	Water Resource Manager and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2253.

Add the following:  The Contractor shall not use land from or restrict access to the following locations, or any other park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract:

1.	Kepler-Bradley State Recreational Site, Sta 1355 to Sta 1400 Lt.

2.	Patten Matanuska Agricultural Colony Farm, Sta 1535 Lt.

3.	Hecky (Kertulla) Homestead Barn, Sta 1606 Lt.

4.	Palmer Municipal Park, Sta. 1665 to Sta 1667 Rt.

5.	Puhl-Bacon Matanuska Agricultural Colony House, Sta 1686+50 to Sta 1692+25 Lt.

6.	Bailey-Estelle House and Barn, Sta 1702+25 to Sta 1709 Lt.

7.	Moose Creek Wayside/State Recreational Site, Sta 2011 to Sta 2030 Lt.

The Contractor shall do no work, stockpiling, staging, parking, nor trespassing in or around any watercourses.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

Excavation in the area located left of Sta. 1992 to Sta. 1998 may cause material to slough from the adjacent private property.  Any material sloughed from the adjacent property belongs to the property owner and shall be delivered to and stockpiled at a site designated by the Engineer.  Payment for delivering and stockpiling sloughed material will be made under Item 203(3), Unclassified Excavation.  If the sloughed material is hauled away or used as embankment, Borrow, Type A shall be substituted with no additional payment due the Contractor.

While working from Sta. 1630+00 to Sta. 1750+00, the Contractor shall observe the following noise restrictions:

1.	a maximum noise level of 80 dba (from 6:00 AM to 10:00 PM)

2.	a maximum noise level of 50 dba (from 10:00 PM to 6:00 AM)

Standard Modifications

107-1.13  Responsibility for Damage Claims.  In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries".  (5/12/89)

Special Provisions

107-1.15 Contractor's Responsibility for Work.  Add the following to the end of the first paragraph:  Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense.  (5/7/91)

Standard Modifications

107-1.16  Contractor's Responsibility For Utility Property And Services.  In the last sentence of the third paragraph delete: "by the local fire authority."  (5/12/89)

Special Provisions

107-1.16  Contractor's Responsibility for Utility Property and Services.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mislocates the facility in the field by more than 2.5-feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.

(9/1/89)

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  Subletting of Contract.  Add the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Driver's License.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	the owner-operator's right to control the manner in which the work is to be performed,

2. 	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3. 	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4. 	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each owner-operator.  The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.

(5/7/91)

108-1.03  Prosecution and Progress.  In the first paragraph, delete the words "At this time" and substitute:  "Five working days before the preconstruction conference".  (5/7/91)

Standard Modifications

108-1.03  Prosecution and Progress.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule". (5/12/89)

Special Provisions

108-1.03  Prosecution and Progress.  Add the following:  The construction of this project will be planned and recorded with a conventional Critical Path Method (CPM) schedule.  The schedule shall be used for coordination, monitoring, and payment of all work under the contract including all activity of subcontractors, vendors, and suppliers.

1.	Preparation of Initial Schedule.

At the preconstruction conference, the Contractor shall submit a detailed initial Progress Work Schedule in the activity-on-arrow format.  The schedule shall meet the requirements set forth below.

The construction time, for the entire project or any milestone shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed schedule are required, the Contractor shall do so promptly.  The schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements.

All activity-on-arrow diagrams shall include:

a.	Activity Nodes

b.	Activity Description

c.	Activity Duration

d.	Resources required for each of the project activities, including:

1)	labor, showing

-workdays per week

-holidays

-shifts per day

-hours per shift

2)	equipment, and

3)	materials.

The activity-on-arrow diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and approvals and fabrication and delivery activities.  All network "dummies" are to be shown on the diagram.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60 - Day Preliminary Schedule.

Before proceeding with any work on site, the Contractor shall have an acceptable 60-day preliminary schedule.  This schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include:

a.	mobilization,

b.	submittals,

c.	procurement, and

d.	construction.

No contract work may be pursued at the site without an accepted 60-day Preliminary Schedule or an accepted CPM schedule.

4.	Schedule Updates And Progress Payments.

Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the Progress Work Schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions.

The Contractor will revise activity-on-arrow diagrams for the following:

a.	resource availability,

b.	delay in completion of any critical activity,

c.	actual prosecution of the work which is, as determined by the Engineer, significantly different than that represented on the schedule, and,

d.	the addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

The principles involved and terms used in this section are as set forth in the Associated General Contractors of America publication, "The Use of CPM in Construction, A Manual for General Contractors and the Construction Industry", Copyright 1976.

In addition to the CPM Progress Work Schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail work activities, manpower involved by trade, work hours, equipment involved and the location of the work to be performed.

Preparation of the CPM work schedule and two week work plans will not be paid for directly, but will be subsidiary to Item 640(1) Mobilization and Demobilization.

(6/13/90)

108-1.04  Limitations of Operations.  Add the following:  The Contractor shall not begin construction on the following items of work prior to June 16, 1992:

1.	Widening of the Glenn Highway from Sta. 1433+00 to Sta. 1463+00.

2.	Construction of the Coal Haul Access Road and related railroad crossing work.

3.	All work on the Glenn Highway from Sta. 2045+00 to Sta. 2070+00, including the Wishbone Hill Coal Mine Access Road.

Quantities for the items of work indicated above are summarized on the plans as "Coal Mine Access Facilities Deletions".  The Engineer will notify the Contractor prior to June 15, 1992 if these items of work will be deleted in accordance with Subsection 104-1.02, Changes.

108-1.05  Character of Workmen, Methods and Equipment.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer. (2/1/90)

108-1.06  Determination and Extension of Contract Time.  Add the following:

4.	Suspensions of Work Ordered by the Engineer.  If the performance of all or any portion of the work is suspended or delayed by the Engineer in writing for an unreasonable period of time (not originally anticipated, customary, or inherent to the construction industry) and the Contractor believes that additional compensation and/or contract time is due as a result of such suspension or delay, the Contractor shall submit to the Engineer in writing, a request for adjustment within 7 calendar days of receipt of the notice to resume work.  The request shall set forth the reasons and support for such adjustment.

Upon receipt, the Engineer will evaluate the Contractor's request.  If the Engineer agrees that the cost and/or time required for the performance of the contract has increased as a result of such suspension and the suspension was caused by conditions beyond the control of and not the fault of the Contractor, its suppliers, or subcontractors at any approved tier, and not caused by weather, the Engineer will make an adjustment (excluding profit) and modify the contract in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment will be allowed unless the Contractor has submitted the request for adjustment within the time prescribed.

No contract adjustment will be allowed under this clause to the extent that performance would have been suspended or delayed by any other cause, or for which an adjustment is provided for or excluded under any other term or condition of this contract.

(4/13/89)

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  General.  Add the following:  When more than one variety of material or work item is specified for a single pay item number, letter or numeric suffixes will be included within the parenthesis to differentiate the types.  (9/1/89)

Standard Modifications

109-1.03 Scope of Payment.  Delete the last sentence of the fourth paragraph.  (5/7/91)

Special Provisions

109-1.04  Compensation for Altered Quantities.  In the third indented subparagraph, delete the following:    ", except that the total payment for the item shall not exceed 75 percent of the total amount bid for the item".  (4/13/89)

109-1.05  Compensation for Extra Work.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)

109-1.07  Payment For Materials on Hand.  Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project will be at a location acceptable to the Engineer.  (9/1/89)

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  Description.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  Interpretation.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  Essential Contract Provision.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  Definitions and Terms.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular Contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03 Item 3. for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a Contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  Utilization Goal.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement of

attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Utilization Goal in order to be eligible for award of this contract.

120-3.01  Determination of Compliance.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  Good Faith Effort.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE Credit.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least one of which must be working on this project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  Default of DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, all of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02, Good Faith Effort.

120-4.01  Method of Measurement.  The Contractor shall be entitled to count toward the DBE Utilization Goal those monies allowed by the Engineer in 120-3.03.04 as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100 percent.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60 percent of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  Basis of Payment.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01, Utilization Goal, until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per subsection 120-3.03, Item 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

Payment or Deduction will be made under:

Pay Item No.        Pay Item         Pay Unit

120(1)        DBE Adjustment   Contingent Sum

(5/5/89)

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01  Description.  Add the following:  This work shall also consist of the removal of fences at the locations designated on the plans.

202-2.01  General Construction Requirements.  Add the following:  The construction of mail box installations shall use new posts and mail boxes.  Existing newspaper delivery tubes shall be relocated to new posts.  Mail boxes shall be United States Postal Service approved, either traditional or contemporary design, having a minimum length of 21-inches, minimum width of 8-inches and minimum height of 10-1/2 inches.  Existing posts and foundations shall be removed with remaining holes backfilled to the level of surrounding ground.

202-2.02  Removal of Bridges, Culverts and Other Drainage Structures.  Add the following:  Frames and grates from inlets to be removed shall be salvaged and delivered to the State Maintenance Yard in Palmer.

202-2.04  Removal of Pavement, Sidewalks, Curbs, Etc.  Add the following:  Pavement removed may be used in the construction of the embankment, provided it is placed below the Selected Material, Type B layer and in the lower reaches of the slope flattening areas.  It shall be placed away from wetlands, and no closer than 300 feet to a stream.  The broken asphalt pieces shall be six inches or less in maximum dimension.

For disposal of removed asphalt not placed as embankment, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529.

202-3.01  Method of Measurement.  Add the following:  All pavement to be removed and disposed of under this contract will not be measured for payment but will be subsidiary to Pay Item 203(3), Unclassified Excavation.

Removal of existing concrete sidewalks at West Evergreen Avenue will not be measured for payment but will be subsidiary to Item 608(1), Concrete Sidewalk.

Removal of fence will be measured by the linear foot for the actual amount of fence taken down, disposed of or delivered to the owner, regardless of the type or height.

Newspaper tube installations will not be measured for payment but will be subsidiary to mail box installations.

202-4.01  Basis of Payment.  Add the following pay item:

Pay Item No.          Pay Item          Pay Unit

202(12)         Removal of Fence     Linear Foot

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01  Description.  Add the following:  This work shall also consist of grading special ditches as designated on the plans.

Standard Modifications

203-2.05  Borrow.  Add the following:  Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.  (5/12/89)

Special Provisions

203-3.01  General Construction Requirements.  Add the following to the fourth paragraph:  The Contractor shall allow the Engineer to obtain cubic yard vehicle measurements of the usable excavation obtained from Project No. 58124 (Sta 1949+76.11 to 2070+00) prior to placing the material in Project No. IR-0A1-5(5) (Sta 1340+10 to 1950+00).  This is necessary to determine the amount of Pay Item 203(3), Unclassified Excavation used on the Federal portion of the project.

Add the following to the fifth paragraph:  Existing pavement shall be removed and disposed of in accordance with subsection 202-2.04, Removal of Pavement, Sidewalks, Curbs, Etc., prior to obliteration of the underlying roadway.

203-3.02 Embankment Construction.  On page 97, delete the 5th paragraph and substitute the following:  All embankments shall be constructed with moisture and density control unless the Engineer determines that such controls are not feasible, in accordance with approved methods.  (5/7/91)

Delete the first sentence of the tenth paragraph, and substitute the following:  Roadway embankments shall be placed in horizontal layers not exceeding eight inches in thickness measured before compaction.  Each layer of classified material shall have its joint offset from the joint below, longitudinally by one foot and transversely by 20-feet.

Add the following:  Where the plans call for placement of selected material and excavation is required, the existing material may be left in place if tests determine that it will meet the appropriate selected material requirements.  Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104, Scope of Work.  (9/1/89)

203-5.01  Basis of Payment.  Add the following:  Obliteration of existing roads and driveways outside the slope limits, but within the right of way, will not be paid for directly, but will be subsidiary to Pay Item 203(3), Unclassified Excavation.  Grading of special ditches will not be paid for directly, but will be subsidiary to Item 203(3), Unclassified Excavation.

Any additional grading required at ends of the driveway culverts, storm drain pipes or roadway cross-culverts to obtain minimum cover will be subsidiary to Pay Item 203(3) Unclassified Excavation.

Standard Modifications

203-5.01  Basis of Payment.  Change Pay Items 203(5), (6) and (7) to read:  Borrow, Type _____.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01  Materials.  Add the following: Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material.  Native material shall be utilized for pipe bedding and backfill below or outside the pavement structure if the material meets the minimum requirements of Selected Material, Type C as specified in Subsection 703-2.07, Selected Material.  (9/1/89)

204-3.01  Construction Requirements.  Add the following to the third paragraph:  Native material used for pipe bedding and backfill outside the pavement structure shall be placed in layers and compacted as approved by the Engineer.

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-1.01  Description.  Add the following:  The aggregate surface course shall be used within the unpaved portion of all side streets, roads, and driveways requiring reconstruction to meet the proposed alignment and grade as shown on the plans.

301-2.01  Materials.  Delete the second sentence of the first paragraph and substitute the following:  The gradation of base course material shall conform to the requirements for Grading D-1.

Add the following:  Aggregate for the aggregate surface course shall conform to the following gradation requirements:

Sieve                Percent Passing by

Designation               Weight Grading

1 inch                      100

3/4 inch                     70-95

1/2 inch                     60-86

No. 4                       40-65

No. 40                      15-30

No. 200                      8-13

301-4.01  Method of Measurement.  Add the following:  The aggregate surface course will be measured by the ton in accordance with Section 109.

301-5.01  Basis of Payment.  Add the following:  Payment for the aggregate surface course will be made at the contract unit price, complete and accepted in place.

Payment will be made under:

Pay Item No.         Pay Item          Pay Unit

301(3)       Aggregate Surface        Ton

Course

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-2.01  Composition of Mixtures.  Add the following to the first paragraph after the first sentence:  The Contractor shall submit, in writing, the proposed ratios at which he plans to blend the various aggregate stockpiles in order to achieve the target gradation submitted.

Add the following to the tolerance table of the fourth paragraph:

Sieve Size          Tolerance

1/2 inch               + 7

No. 80                 + 4

Add the following after the tolerance table of the fourth paragraph:  The asphalt cement and aggregate submitted by the Contractor for Asphalt Concrete, Type IA Job Mix Design approval as tested according to Alaska T-17 shall conform to the following.  The asphalt content of the mix shall be expressed as a percentage of the total mix.

Marshall Stability, pounds, minimum     1500

Voids, Total Mix %                      3.0-5.0

Flow Value                              8-16

Compaction Blows per Side               75

Voids in Mineral Aggregate, %, min.     14.0

Dust-asphalt ratio (1)                  0.6-1.2

(1)	Dust-asphalt ratio is defined as the percent of material passing the No. 200 sieve divided by the percent of asphalt (calculated by weight of mix).

The Voids in mineral aggregate is calculated by the following formula:

GmbPs

Voids in mineral aggregate = 100 - (____)

Gsb

Where:

Gsb = bulk specific gravity of aggregate

Gmb = bulk specific gravity of compacted

mixture (ATM T-18), and

Ps = aggregate, percent by total weight of

mixture

The Contractor should be cautioned that addition of crushed fines may be required to meet the Voids in Mineral Aggregate requirement.

The Alaska Test Method T-17 section E.4.a shall be deleted and the following should be substituted:

a.	From the data curves, asphalt contents are determined which yield the following:

1.  Maximum Unit Weight

2.  Maximum Stability

3.  Voids Total Mix at 4 percent

Add the following:  The asphalt cement and aggregate for Asphalt Concrete, Type III shall conform to the following:

Marshall Stability, pounds, minimum		1000

Voids, Total Mix %						3-5

Compaction Blows per Side				50

401-2.04  Asphalt Materials.  Add the following:  AC-5 asphalt cement will be used for the new asphalt concrete pavement mix.

401-3.01 Weather Limitations.  Delete in its entirety and substitute the following:  The asphalt mixture shall not be placed on a wet surface, on a surface of which the temperature is less than that determined from the following table for the appropriate mat thickness, or when other conditions would prevent the proper handling or finishing of the mixture.

SURFACE TEMPERATURE LIMITATIONS

| Mat Thickness | Surface Temperature Degrees F, min. |
| --- | --- |
| 3 inches or greater | 40 |
| between 1 and 3 inches | 45 |
| 1 inch or less | 50 |

(5/7/91)

401-3.11  Spreading and Finishing.  Add the following:  When pavement marking tape for striping is required, the longitudinal joints on the final lift shall be offset 6-inches from the plan lane lines.  The Contractor shall submit a Paving Plan for the Engineer's approval before starting this work.  The Paving Plan shall be submitted to the Engineer one week prior to initiating the paving operation.  The Paving Plan shall include but not be limited to the following:

1.	Manuals for the paving machine and the rollers.

2.	Traffic Control Plan for the paving operations.

3.	Pavement widths to be placed.

4.	Traffic marking installation plan.

Asphalt concrete pavement over 3 inches in depth shall be spread and compacted in 2 layers of approximately equal thickness.  The final lift shall not be placed until the initial lift throughout continuous segments has been placed and accepted.  Final lift paving shall be continuous, where possible, to keep the number of transverse joints to a minimum.

Standard Modifications

401-3.12  Compaction.  In the second paragraph, delete the following:  "(94% at joints)".  (5/7/91)

Special Provisions

401-3.12  Compaction.  Add the following:  All rolling operations on Asphalt Concrete, Type III shall be accomplished with a pneumatic tire roller.

401-3.14  Pavement Samples.  Delete the third sentence of the first paragraph and substitute the following:  Each sample shall be one core, having a minimum diameter of 6-inches.

401-4.01 Method of Measurement.  Add the following numbered paragraph:

4.	Volume measurement determined by the use of a flow meter.  Asphalt cement quantities measured by the gallon shall be converted to tons in accordance with Subsection 109-1.02, Measurement of Quantities.  The flow meter shall correct the volume to gallons at 60 degrees F and shall be calibrated to 0.1 percent accuracy prior to production of hot asphalt pavement.  The flow meter shall be inspected and recalibrated as often as the Engineer deems necessary to assure its continued accuracy.

Waste will be computed based on the estimated tons of mix wasted and the percentage of asphalt added at the mixing plant, as determined by the Engineer.

(5/7/91)

401-4.02  Contract Price Adjustments. Add the following to the first paragraph:  Asphalt Concrete, Type III will not be subject to price adjustments.  The shoulders receiving rumble strips will not be subject to price adjustment for density.  (9/1/89)

Add the following to the sixth paragraph:  Sampling will be done in front of the screed just prior to final placement or from the mat prior to breakdown rolling.

Delete the seventh paragraph and substitute the following:  Sampling for determination of oil content will be from in front of the screed just prior to final placement or from the mat prior to breakdown rolling.

In the eighth paragraph, add the following:  On projects consisting of more than 5000 tons, density evaluation shall be as follows:

For the purpose of evaluating the density of the material, a lot will be represented by fifteen test values, three for each sublot.  A representative single density value for each sublot will be obtained by averaging the three sublot density test valves.  This representative density shall become the density value reported for the sublot and the value used to evaluate individual lots for acceptance and price adjustment.

In the ninth paragraph, delete the second sentence and substitute the following:  Prior to computing a reduction in price, the validity of the failing test results for asphalt content and gradation tests shall be ascertained in accordance with ATM T-19.  Tests for density compliance will not be subject to ATM T-19 and no retests will be allowed.

401-5.01  Basis of Payment.  Add the following:  Anti-stripping additives will be paid on a contingent sum basis at a rate of $3.75 per 0.25 percent additive per ton of asphalt cement.

SECTION 402

TACK COAT

Special Provisions

402-3.04  Dilution of Asphalt Material.  Add the following:  CSS-1 Emulsified Asphalt used for tack coat may be diluted not more than 50 percent water by weight or volume at the Engineer's direction.  The determination of this ratio shall be accomplished by weighing the distributor prior to adding water, by sticking the tank, or other means suitable to the Engineer.  Emulsified asphalt as manufactured is approximately 60 percent oil and 40 percent water.  Any required dilution is additional water.

402-3.05  Application of Asphalt Material.  Modify the application rate given in the first paragraph from "0.05 to 0.10 gallons" to "0.05 to 0.15 gallons".

Add the following Section:

SECTION 409

RUMBLE STRIP

Special Provisions

409-3.01  Construction Requirements.  This work shall consist of forming a series of pavement indentations along the edge of both shoulders.  These rumble strips shall be made after the breakdown rolling while the surface temperature of the mixture is a minimum of 180 degrees F and shall be accomplished in one pass of the roller.  Installation of the rumble strip prior to or following intermediate rolling shall be determined in the field and approved by the Engineer.

Rumble strips shall be placed perpendicular to centerline along both shoulders.  They shall not be placed on side streets, where the shoulder stripe is stopped, when the shoulder is less than four feet, or as directed by the Engineer.

The edges of the rumble strip indentations shall be neat, smooth and free of spalling, and shall be within the following tolerances:

Offset from outside edge 	  		+ 2-inches

shoulder stripes

Width of rumble strip				+ 2-inches

Spacing of indentations				+ 1-inch

Depth of indentations				+ 1/4-inch

Surface width of indentations			+ 1/4-inch

409-4.01  Method of Measurement.  Measurement of rumble strips shall be on a lump sum basis for rumble strips completed and accepted.  For rumble strips out of tolerance, the length out of tolerance will be divided by the total plan quantity of rumble strips and that proportion will be deducted from the lump sum amount.

409-5.01  Basis of Payment.  Payment for rumble strips shall include all equipment, material and labor necessary to complete the work.

Payment will be made under:

Pay Item No.           Pay Item          Pay Unit

409(10)            Rumble Strip        Lump Sum

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-1.01  Description.  Add the following:  This work shall also consist of construction of a  cast-in-place reinforced concrete roadway slab (Glenn Hwy, Sta 1942+06 to Sta 1944+94), which is to be used in conjunction with the Automated Traffic Recorder System (ATR/WIM site).

501-2.01  Materials.  Add the following:  Reinforcing steel to be used in the concrete roadway slab shall conform to the requirements of Section 503, Reinforcing Steel and shall be epoxy coated, grade 60 steel.

501-3.01  Proportioning.  Revise this subsection as follows:  In Table 501-1, Class of Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S and W concrete.  (9/1/89)

501-3.02  Batching.  Add the following to item No. 5, Batching:  Furnish the mix design number and a list of all ingredients, their individual weights, the moisture content of the various aggregates and the individual truck water meter reading when batched, for each truck load or batch of concrete supplied.  (5/7/91)

501-3.06  Placing Concrete.  Delete the last sentence of Item 2. Pumping Concrete and substitute the following:  Concrete samples for testing shall be taken at the discharge end of the pipe.  The Contractor shall provide the necessary samples of concrete at the direction of the Engineer or his representative.

Add the following:

16.	Concrete Pavement.  This work shall consist of constructing a pavement composed of air-entrained portland cement concrete, with reinforcement as specified, in accordance with these specifications and in reasonably close conformity with the lines, grades, thicknesses, and typical cross sections shown on the plans or established by the Engineer.

Preparation of Roadbed.  The roadbed shall be uniformly wet when the concrete is placed.

Stationary Side Form Construction.  The pavement may be constructed using stationary side form construction in areas inaccessible to paving equipment.  The Contractor will be permitted to perform the strike-off, consolidation, final floating and surface finishing by equipment, tools, means, labor and methods other than described below; provided however, that the work shall meet with the approval of the Engineer.

a.	The process of striking-off and consolidating the concrete shall include thorough vibration of the concrete uniformly throughout the mass as the concrete is being placed and until it is uniformly compacted, the work being done without causing segregation of material.

b.	The concrete shall be struck-off by means of templates or screeds of proper design and so manipulated as to shape the concrete to specified cross section between the forms, carrying a slight excess of concrete in front of the leading edge of templates or screeds at all times.

c.	Floating shall follow the vibrating and striking-off operations and shall provide transverse floating or other smoothing and finishing action which shall leave the surface to specified grade, cross section and surface evenness set forth in these specifications.

Sawed Contraction Joints.  These joints shall be created by sawing grooves in the surface of the concrete pavement of the width, depth and at the spacing and lines shown on the plans, with an approved concrete saw.  After each joint is sawed, the saw cut and adjacent concrete surface shall be thoroughly cleaned.

Sawing of the joints shall commence as soon as the concrete has hardened sufficiently to permit sawing without raveling, usually 4 to 24 hours.  All joints shall be sawed before uncontrolled shrinkage cracking takes place.  The sawing of any joint shall be omitted if a crack occurs at or near the joint location prior to the time of sawing.  Sawing shall be discontinued when a crack develops ahead of the saw.

501-3.07  Finishing Concrete Surfaces. Add the following:  Concrete pavement for the Automated Traffic Recorders shall be finished in accordance with Item 3, Concrete Decks, with the following additional requirements:

Surface Finish.  The pavement shall be given a final finish surface by texturing with metal tines to produce transverse grooves between 1/8 and 3/16 inch deep on 1/2 inch centers (approximately).

Surface Test.  As soon as the concrete has hardened sufficiently, the pavement surface shall be tested by the Contractor as directed by the Engineer with a 10-foot rolling straightedge provided by the Department.  The surface shall not vary more than 0.01 foot from the lower edge of the straightedge.

All high areas in the hardened surface in excess of 0.01 foot as indicated by testing shall be removed by abrasive means.  After grinding has been performed, the ground areas shall be provided with a uniform texture as described under Surface Finish.

All testing shall be made longitudinally for the full length of each traffic lane.  Each section shall be tested as early as possible in a longitudinal path at (a) transverse location(s) selected by the Engineer.

501-3.08  Curing Concrete. Add the following before Item 1., Water Curing:  Immediately after the finishing operations have been completed and as soon as marring of the concrete will not occur, the entire surface of the newly placed concrete pavement shall be covered and cured in accordance with one of the following methods:

Add the following to Item 1., Water Curing:  The mats shall be placed and weighted down in intimate contact with the surface of the concrete pavement and shall extend beyond the edges of the slab at least 2 feet. The mats shall be maintained wetted and in position for 72 hours.

Add the following Item:

3.	Polyethylene Sheeting.  The surface of the concrete pavement shall be entirely covered with polyethylene sheeting.  The sheeting shall be lapped at least 18 inches, placed, and weighted down in intimate contact with the surface covered.  The sheeting shall extend beyond the edges of the slab at least 2 feet.  The covering shall be maintained in position for 72 hours.

501-3.09  Backfilling and Opening to Traffic.  Add the following:  The concrete pavement shall not be opened to traffic until the concrete has attained a minimum compressive strength of 3000 pounds per square inch.  Prior opening to traffic, the pavement shall be cleaned and joint sealing completed.

501-5.01  Basis of Payment.  Add the following:  Payment for Class A Concrete will be full compensation for all required labor, form materials, Class A Concrete, epoxy coated reinforcing steel, smooth dowels and steel caps, expansion joint materials and filler sealant, and the cutting and sealing of all contraction joints to complete the concrete roadway slab in accordance with the plans.

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01  Description.  Add the following:  This work will include the epoxy-coating of appropriate reinforcing steel bars.

Standard Modifications

503-3.05  Splicing.  Delete the first and second paragraphs and substitute the following:  Lap splices for reinforcing bars shall be as shown on the plans or as directed.  (5/12/89)

Special Provisions

503-5.01  Basis of Payment.  Add the following:  If epoxy coating the reinforcing steel is required, it will be a subsidiary obligation and no separate payment will be made.

SECTION 504

STEEL STRUCTURES

Special Provisions

504-3.03  Painting.  Add the following to Item 1:  Preparing Metal Surfaces for Painting:

Metal Bin Walls:  These structures shall be primed and painted after they are installed in their final position.  Each structure shall be cleaned, roughened by abrasive blasting, primed and painted in a continuous operation.

Paint shall be spray applied only on thoroughly cleaned and dried surfaces during favorable weather.  Fabrication defects, such as weld imperfections, slivers, burrs, and jagged edges shall be ground smooth.  All surfaces to be painted shall be cleaned using a solvent wash in accordance with the Steel Structures Painting Council's specification SSPC-SP1, Solvent Cleaning.  Immediately thereafter, all surfaces to be painted shall be roughened by abrasive blasting using an abrasive no larger than a No. 30 mesh.  Galvanizing shall not be removed by this roughening.

Delete the first sentence of the first paragraph under Item 2. Schedule of Paint Coats for Metals, and substitute the following:  Except for metal bin walls, galvanized surfaces shall not be painted.

Delete the first sentence of the second paragraph under Item 2., and substitute the following:  Except for metal bin walls, the prime coat shall be applied in the shop.

Add the following to Item 2.  The paints used to protect the metal bin walls shall consist of a primer especially formulated for use on galvanized steel and an acrylic polyurethane topcoat.  The primer and top coat used shall be manufactured by the same company.  The primer shall be United Coatings Primer 376, or an approved equal meeting the following requirements:

a.	It shall be a zinc phosphate rich, two component epoxy primer formulated for superior adhesion to galvanized steel, aluminum, and other non-ferrous metals.

b.	Mixed together, at 75 degrees F and 50 percent relative humidity, it shall have a useable pot life of at least 24 hours and a dry time of 2 hours or less.

c.	The in service temperature limits shall be a minimum  minus 70 degrees F and at least 150 degrees F.

d.	The topcoat shall not lift the primer from the metal surface.

The topcoat shall be United Coatings' Marathon, with a satin finish, or an approved equal meeting the following requirements:

a.	It shall be a two component acrylic polyurethane with a satin finish.

b.	It shall be chemical and weather resistant, showing no effect from a 60 day exposure to acetic, hydrochloric, sulfuric, lactic, and formic acids, potassium and sodium hydroxides, distilled and salt waters, and common fertilizers, when tested in accordance with ASTM D543.  It shall also show no effect from a 30 day exposure to alcohol, xylol, gasoline, diesel, gasohol, and transmission fluid.

c.	It shall show no deleterious effects after 2000 hours of accelerated weathering, when tested per ASTM D822 and G23, in an Atlas Carbon Arc Weatherometer, Type EH.

d.	It shall have an excellent abrasion resistance, losing 10 milligrams or less material when tested per ASTM D4060 in a Taber Abraser Machine using CS-17 wheels with 1000 gram weights at 1000 revolutions.

e.	It shall show no cracking or breaks in a 180 degree bend over a 1/4 inch mandrel.

The topcoat shall be applied in two layers.  The color of each layer shall be a light beige, closely matching color chip number 36642 of the Federal Standard Specification No. 595a.

Add the following to Item 3. Painting Metal Surfaces.  b. Storage of Paint and Thinner:

Metal Bin Walls:  The components to the primer and topcoat shall have a minimum shelf life of one year, and be stored at temperatures between 50 degrees F and 100 degrees F.

Containers shall not be opened until they are to be used.  Containers that are opened and not immediately mixed shall be discarded and not used.

Add the following to Item 3.  c. Mixing and Thinning:

Metal Bin Walls:  The primer and topcoat paints shall be mixed using an air operated or explosion proof mixer only in accordance with the written recommendations of the manufacturer.

Add the following to Item 3.  d. Application of Paint:

Metal Bin Walls:  The clean and dry surfaces shall be primed upon completion of the roughening operation.  The spray applied prime coat shall be between 1.0 and 1.5 mils in thickness.  When the prime coat has dried, an intermediate coat of topcoat material shall be spray applied to a 1.0 to 1.5 mil thickness.  The topcoat may be spray applied at any stage of dryness of the intermediate coat.  However, if the intermediate coat becomes totally cured, then it shall be scuff sanded before applying the topcoat.  The thickness of the topcoat shall be between 2.0 and 3.0 mils.

Any skips, holidays, thin areas, or other deficiencies shall be corrected prior to applying the succeeding coat of paint.

Subject to approval by the Engineer of a detailed proposal, the Contractor may provide suitable enclosures to permit painting during inclement weather.  Provisions shall be included to artificially control conditions within these enclosures to within suitable limits for the painting and drying periods.  Payment for providing and maintaining these enclosures shall be included in the prices paid for the bin walls to be painted and no additional payment will be made.

The Contractor shall provide tarps, screens, or covers as necessary to prevent damage to any adjacent structures, property, or persons from the cleaning and painting operations.  Any paint overspray which results in an unsightly appearance on surfaces not designated to be painted shall be removed by the Contractor, at his expense, to the satisfaction of the Engineer.

SECTION 505

PILING

Special Provisions

505-1.01  Description.  Add the following:  This work shall consist of furnishing and installing temporary steel sheet piles in conformance with the plans and as specified herein.  Temporary shoring will be required behind Wall IB to stabilize the backslope during erection of Wall IB.  Excavation at Wall IB shall not proceed below the top elevation of the shoring as specified on the plans until the shoring is installed.  When Wall IB erection and backfill is complete, the shoring may be removed or left in place.

505-2.01  Materials.  Delete this subsection and substitute the following:  Sheet pile shoring shall meet the requirements listed below:

1.	The steel sheet piling material may be previously used material, such as rental type, but it shall be in a good or better condition as approved by the Engineer.

2.	The steel sheet piling material shall meet the following minimum structural specifications:

Area = 9.15 sq.in. per sheet pile

Weight = 31.0 lbs./l.f. of sheet pile

Section Modulus = 13.21 cu.in./foot of wall

Steel Grade = ASTM A-572, grade 50

3.	Cold-rolled steel sheet piling is an acceptable alternate.

4.	The integrity of the interlock shall be maintained when the sheet piles are installed.

The Contractor shall furnish documentation to the Engineer to verify that the above requirements are met.

505-3.03  Pile Bearing Values.  Add the following:  No bearing values are required for the sheet pile shoring.  The sheet piles shall be driven to the depths shown on the plans.

505-3.09  Driving Piles.  Add the following:  The sheet piles may be installed with a vibratory driver.

505-4.01  Method of Measurement.  Add the following to Item No. 7:  In determining the area of sheet piling, the horizontal measurement will be made along the alignment of the sheet piling without any allowance for the structural shapes of the separate sections of the sheet piling.

Delete the last paragraph in this subsection.

505-5.01  Basis of Payment.  Add the following pay item:

Pay Item No.              Pay Item             Pay Unit

505(12)          Sheet Pile Shoring        Square Foot

Add the following Section:

SECTION 510

STEEL BIN RETAINING WALLS

Special Provisions

510-1.01 Description.  This item shall consist of furnishing and constructing steel bin walls in reasonably close conformity with the lines, grades, and dimensions shown on the plans or as established by the Engineer.

General design criteria for the bin wall structure, such as location and elevations shall be as shown on the plans.  Design details for the wall shall conform to one of the following manufactured systems or an approved equivalent:

1.	"Steelbin Retaining Wall", as manufactured by the Syro Steel Company.  For information concerning purchase and delivery of Steel Bin Wall materials, contact:

Syro Steel Company

P.O. Box 99

Centerville, Utah  84014

Phone:  (801) 292-4461

2.	"Bin-Type Retaining Wall, Type 1", as manufactured by the Contech Construction Products Company.  For information concerning purchase and delivery of Steel Bin Wall materials, contact:

Contech Construction Products Inc.

1409 - 140th Place N.E., Suite 101

Bellevue, Washington  98007

Phone:  (206) 641-3328

The Contractor shall make his own arrangements to purchase or manufacture all of the necessary components.

510-1.02 Submittals.  The Contractor shall submit complete working drawings for the wall system in accordance with the provisions in Subsection 105-1.02, Plans and Working Drawings.  The working drawings shall contain all information required for the proper construction of the wall system.  The Contractor shall allow the Engineer two weeks to review the drawings after a complete set has been received.

The Contractor shall submit a Manufacturer's Certificate of Compliance in accordance with the provisions in Subsection 106-1.05, Certificate of Compliance, for all materials to be placed under Item 510(5), Steel Bin Walls.  Submittals shall also include Manufacturer's installation instructions for the application shown on the plans.

510-2.01 Materials.  The steel bin walls shall consist of a series of rectangular cells composed of galvanized steel members.  They shall conform to the materials requirements of ASTM A444.  Fasteners for the bin walls shall conform to ASTM A307 and shall be galvanized in accordance with ASTM A153.

510-3.01 Construction Requirements.

1.	Design details.  The plans show general details of the bin walls only.  The bin walls shall be of standard manufacture and the Contractor shall submit working drawings as specified above.

2.	Fabrication Requirements.  All bin members shall be fabricated so that members of the same nominal size shall be interchangeable.  Drilling, punching, or drifting bolt holes to correct defects in fabricating will not be permitted.  Any members twisted, bent, or with holes improperly located shall be replaced by the Contractor at his expense.

3.	Excavation and Backfill.  Excavation and backfill shall be performed in accordance with Section 205.

Temporary shoring will be required behind the bin walls to stabilize the backslope during erection of the bin walls.  The temporary shoring shall be installed as per the plans and as specified in Section 505.

4.	Finishing.  The bin walls shall be treated and painted in accordance with Subsection 504-3.03, Painting.

510-4.01 Method of Measurement.  Steel bin walls will be measured for payment by the square foot.  The measurement will be along the outer face for the height from the bottom of the base plate to the top of the top stringer and for a length measured from end to end of each section of wall.

510-5.01 Basis of Payment.  The contract price paid per square foot for steel bin walls shall include full compensation for furnishing all labor, materials, tools, equipment and incidentals, and for doing all the work involved in construction the bin walls, complete in place.

Excavation will be paid under Item 205(1), Excavation for Structures.  Backfill will be paid under Item 203(6A), Borrow, Type A.

Add the following pay item:

Pay Item No.            Pay Item               Pay Unit

510 (5)           Steel Bin Walls           Square Foot

SECTION 601

METAL FLUME DOWNDRAINS

Special Provisions

601-1.01  Description.  Add the following:  Work under this section shall also include furnishing and installing treated timber curb at locations shown on the plans.

601-2.01  Materials.  Add the following:  Treated timber curb shall consist of 2-inch by 8-inch treated lumber.  It shall be of a timber stress grade of 1200 psi or more in accordance with the American Institute of Timber Construction.  Timber shall be treated in accordance with Section 714, Preservatives and Preservative Treatment Processes for Wood Materials.

601-3.01  Construction Requirements.  Add the following:  This work shall consist of installation of new metal flume downdrain inlets to match the timber curb flow line, and attaching treated timber curb to steel guardrail posts as shown on the plans.

601-4.01  Method of Measurement.  Add the following:  Treated timber curb shall be measured by the number of linear foot of curb complete in place and accepted, and shall include all miscellaneous hardware and excavation necessary for the installation, completed and accepted by the Engineer.

601-5.01  Basis of Payment.  Add the following:  Metal flume downdrain inlet shall be subsidiary to Item 601(1), Metal Flume Downdrain.

Pay Item No.              Pay Item             Pay Unit

601(3)          Treated Timber Curb      Linear Foot

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-2.01  Materials.  Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05, Delineator Posts for Item 2., Flexible Posts.  The color shall be blue with no other markings.  The     3-3/4 inch by 72-inch post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9-inches.

603-3.06  Culvert Marker Posts.  Add the following subsection:  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30-inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or at the locations as directed by the Engineer.  42-inches of post shall remain above the ground after driving.

603-4.01  Method of Measurement.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01  Basis of Payment.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to the pipe item.

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-3.01  Construction Requirements.  Add the following:  Those manholes which by design must fall within the paved roadway surface shall be aligned such that the casting will not be in the wheel tracks of any driving lane, or the flow line of the gutter pan.

Standard drainage structure steps shall be cast during structure pour or installed before concrete hardens.

Where the plans indicate the top of manhole elevations, the Contractor shall field verify the exact elevations.  Rotating and adjusting manholes to the required location and grade shall be incidental to the cost of installing manholes.

When new pipe is installed in an existing manhole, a hole shall be cleanly cut at the invert elevation given on the plans and 2-inches larger than the outside diameter of the new pipe.  The joint shall then be grouted with non-shrinking cement mortar.  The downstream pipe in manholes shall be screened to prevent mortar or other debris from entering the system.

All curb inlet structures shall have a 3-inch formed hole approximately 2 feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  The Contractor shall be responsible for keeping the openings functional, which may require temporary dikes, RMC extensions, etc., as necessary.  These holes shall be filled with grout upon final paving.

Each precast concrete barrel section, precast concrete eccentric cone section, concrete adjusting ring, and manhole frame set, installed, reconstructed or relocated shall be sealed by use of a premolded plastic gasket pipe joint sealer manufactured in accordance with Federal Specifications SS-S-210A or AASHTO M-198.  Use and installation of premolded plastic gaskets for manhole construction shall be strictly in accordance with the manufacturer's printed instructions.  Gaskets shall be trimmed flush with the inside of the manhole.

Connections to existing sanitary sewer manholes will be allowed only after all portions of the Contractors work tributary to the connection point have been cleaned, flushed, tested and inspected.  Under certain conditions, connection prior to the completion of the system may be permitted subject to the Engineers written approval and the provision of suitable and adequate debris and sand traps and sumps upstream from the connection.

604-4.01   Method of Measurement.  Add the following:  Frames, grates and lids will not be measured for payment.

604-5.01  Basis of Payment.  Add the following: Frames, grates and lids are subsidiary to the drainage structure.

Delete Pay Item 604(1), Storm Sewer Manhole and Pay Item 604(6), Relocate Inlet and substitute the following:

Pay Item No.             Pay Item               Pay Unit

604(1)       Storm Drain Manhole, Type I        Each

604(6E)         Relocate Inlet, Type E          Each

SECTION 606

GUARDRAIL

Special Provisions

606-1.01  Description.  Add the following:  This work shall also consist of installing breakaway cable terminals, controlled release terminals, bridge rail retrofit, and concrete barriers at the locations shown on the plans.

606-3.01  Posts.  Add the following:  The foundation type for the Breakaway Cable Terminal Posts shall be the "steel post embedment-soil or concrete" option as shown on Standard Drawing G-18.  Posts for W-Beam Guardrail may be either wood or steel, but shall be of the same type throughout a run.

606-3.02  Rail Elements.  Add the following:  Guardrail elements shall be factory bent for all radii less than 75-feet.

606-3.04  Removal and Disposal of Existing Guardrail.  Delete in its entirety and substitute the following:  All posts, rail and hardware, including nuts, bolts, washers, etc., from the existing guardrail designated for removal shall be salvaged and delivered to the State Maintenance Yard in Palmer.

606-3.06  Concrete Barriers.  Add the following subsection:  Concrete barriers shall be constructed under the general requirements of Section 501, Structural Concrete.  Reinforcing steel shall be epoxy coated and shall conform to ASTM A-615, Grade 60.

The concrete barriers at Wall IB shall be dyed a light brown color acceptable to the Engineer.

606-3.07  Bridge Rail Retrofit.  Add the following subsection:  New bridge rail shall be installed in accordance with the details shown on the plans.  The existing bridge rail is to remain.

Installation of Bridge Rail Retrofit and approach/departure guardrail shall be complete on one side of the bridge prior to removal of the existing guardrail on the other side of the bridge.  Traffic shall not be allowed to cross the bridge being worked on without guardrail in place adjacent to the available travel lane.  Each bridge rail retrofit and its associated approach and departure guardrail will be treated as one guardrail segment per subsection 643-3.08, Construction Sequencing.

606-3.09  Length of Need Verification.  Add the following subsection:  After shaping the slopes and staking all proposed guardrail locations, the Contractor shall notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine that additional guardrail is necessary, and the Contractor shall comply without delay.  (3/17/86)

606-3.10  Controlled Release Terminal.  Add the following subsection:  Controlled Release Terminals shall conform to the requirements shown on the plans.

Standard Modifications

606-4.01 Method of Measurement.  Delete the last sentence of the first paragraph and substitute the following:  Double faced (and nested) installations will be measured by dividing the number of panels by two, before multiplying by the panel length.  Thrie beam transition pieces shall be measured by multiplying the number of panels by 6.25 feet and shall be paid for at the contract price for Thrie Beam Guardrail.  (5/12/89)

Special Provisions

606-4.01  Method of Measurement.  Delete the third paragraph and replace with the following:  Breakaway Cable Terminals will be measured per each installation which shall include anchor cable assembly, terminal posts, terminal end, and all associated hardware.  Rail elements, standard posts, and blocking for breakaway cable terminals shall be measured as Beam Type Guardrail.

Controlled Release Terminals will be measured per each installation which consists of all materials from the terminal end to and including the breakaway cable terminal anchor cable assembly, terminal posts and associated hardware.

Concrete Barriers will be measured by the linear foot.

Bridge Rail Retrofit at Moose Creek will not be measured for payment.

606-5.01  Basis of Payment.  Add the following:

Concrete barriers will be paid under Item 606(22), Concrete Barriers, regardless of type.

Add the following pay items:

Pay Item No.             Pay Item              Pay Unit

606(8)         Breakaway Cable Terminal       Each

606(9)       Controlled Release Terminal      Each

606(13)        Bridge Rail Retrofit at      Lump Sum

Moose Creek

606(22)           Concrete Barriers        Linear Foot

(9/1/89)

SECTION 607

FENCES

Special Provisions

607-1.01  Description.  Add the following to the last paragraph:  All the chain-link fence to be installed at the scenic viewpoint (approximate Sta 1772+00 Rt) shall have a 1-1/4 inch pipe top rail in lieu of the top tensioning wire.

607-3.01  Construction Requirements.  Add the following to the seventh paragraph:  The wire ends of the chain-link fences at the scenic viewpoint shall be finished using a knuckle selvage as shown on Standard Drawing F-01.

Add the following to the last paragraph:  For reconstructed fences, the posts and foundations shall be new materials.

Add the following:  All new barbed wire fences and gates between Sta. 1685+00 and Sta 1950+00 shall be installed prior to the removal of existing fences.

607-4.01  Method of Measurement.  Add the following:  Chain-link fence will be measured by the linear foot regardless of height.

Posts and foundations required for the reconstructed fences will not be measured for payment, but will be subsidiary to Item 607(4), Reconstructed Fence.

SECTION 608

SIDEWALKS

Special Provisions

608-1.01  Description.  Add the following:  This work also consists of construction of asphalt pathway and median paving as shown on the plans.

608-2.01  Materials.  Add the following:  AC-5 Asphalt Cement shall be used for the asphalt concrete pavement mix for asphalt pathways and medians and shall conform to the requirements of subsection 702-2.01, Asphalt Cements.  Asphalt concrete aggregate shall conform to Subsection 703-2.04, Aggregate for Plant Mix Asphalt Pavement, for Asphalt Concrete, Type III.

608-3.03  Asphalt Pathways and Medians.  Add the following subsection:  Asphalt pathways and medians shall be constructed in accordance with subsection 608-3.02, Asphalt Sidewalks.

608-4.01  Method of Measurement. Add the following:  Asphalt pathways and medians will be measured by the ton in accordance with Section 109, Measurement and Payment.  Asphalt cement will not be measured for payment.

608-5.01  Basis of Payment.  Add the following: Asphalt cement will not be paid for directly but will be subsidiary to Item 608(8), Asphalt Pathways and Medians.

Payment for Item 608(1), Concrete Sidewalk will include the removal of existing concrete sidewalks at West Evergreen Avenue.

Excavation and bed Course materials, as detailed on the plans, will be furnished, placed and paid under their respective bid items.

Add the following Pay Item:

Pay Item No.             Pay Item           Pay Unit

608(8)      Asphalt Pathways and Medians     Ton

SECTION 615

STANDARD SIGNS

Special Provisions

615-1.01  Description.  Add the following:  This work shall also include the relocation of an existing sign (Cedar Hills) and shrubs within the median of Pioneer Parkway, as shown on the plans.

615-2.01  Materials.  Add the following to the end of the first sentence of the fifth paragraph, "and the Alaska Traffic Manual."

Delete paragraphs 7 and 8 and substitute the following:  All metal sign posts other than perforated steel tubes and wide flange posts shall be equipped with slip bases, unless multi-directional breakaway load concentration couplings are called for on the plans.  Wide flange posts shall always be equipped with multi-directional breakaway load concentration couplings.  Structural aspects of design and materials for sign supports shall comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals.

Concrete for steel-reinforced slip base and breakaway base foundations shall be Class A, conforming to the requirements of Section 501, Structural Concrete.  Concrete for other sign foundations may be Class W.

(5/7/91)

Add the following:  For Item 615(15), Relocate Existing Sign and Shrubs, all materials shall be salvaged and reused.

615-3.01  Construction Requirements.  Add the following to the fifth paragraph:  The existing sign (Cedar Hills) to be relocated shall have the wooden posts placed in excavated holes to the same depths as the original condition.  The space around the posts shall be backfilled to finish ground with selected earth or sand, free of rocks or deleterious material, placed in layers approximately 6 to 12 inches thick, and thoroughly compacted.

Relocation of existing shrubs shall conform to the requirements of Subsection 621-3.03, Item 4., Transplanting.  If the relocated shrubs are not transplanted within 24 hours after removal, they shall be properly stored in accordance with Subsection 621-3.01, Temporary Storage.

Add the following after the sixth paragraph:  Salvaged sign panels shall be delivered to the State Maintenance Yard at Palmer.

615-3.02  Sign Placement and Installation:  Add the following:  All existing signs shall not be removed until the new signs have been installed.  If necessary, they may be temporarily relocated to a location approved by the Engineer.  They shall be maintained until they are no longer needed.

The signs shall be removed from posts and mounting brackets.  All posts and foundations shall be removed to at least a 1-foot depth below finish grade.

The quantity of existing signs to be removed shall not exceed the quantity of new signs to be constructed by this Contract.

615-4.01  Method of Measurement.  Add the following:  Item 615(15), Relocate Existing Sign and Shrubs will not be measured for payment.

615-5.01  Basis of Payment.  Add the following:  Maintaining existing signs until they are no longer needed and temporary relocation of existing signs will not be paid for directly, but will be subsidiary to Item 615(1), Standard Signs.

Item 615(15), Relocate Existing Sign and Shrubs will be paid on a lump sum basis and will include all work necessary to salvage and relocate the wooden sign (Cedar Hills) and shrubs.  Replacement of any damaged materials will not be paid for directly but will be subsidiary to this item.

Add the following pay item:

Pay Item No.              Pay Item               Pay Unit

615(15)     Relocate Existing Sign & Shrubs    Lump Sum

SECTION 617

RAILROAD CROSSINGS

Special Provisions

617-2.01  Materials.  Add the following:

5.	Geotextile.  Railroad Ballast Geotextile shall conform to the requirements of Subsection 729-2.01, Embankment Separation and Reinforcement.

617-3.01 Construction Requirements.  Under Item 1.c. after "appurtenances...", add the following:  "outside the crossing work limits shown on the plans...".

Delete Item 4. Railroad Crossing and substitute the following:

4.	Railroad Crossing.  Construction of railroad crossings shall take place within the limits of each crossing and shall consist of the following items of work:

a.	Furnish all materials required for the project including rail, ties, ballast, geotextile, tie plates, spikes, joint bars, bolts, rail anchors, temporary crossing timbers, and modular crossing materials.  Ballast required for track raises to match the new crossing elevation shall be furnished and delivered to the job site in a ARRC hopper car.

b.	Removal of the existing crossing surface, i.e., planks, asphalt, or modular pads.

c.	Removal of the track panel, i.e., rails, ties, and all associated hardware after disconnection by the Alaska Railroad.

d.	Excavation of the crossing in accordance with the typical sections shown on the plans.

e.	Furnishing and installing new geotextile as shown on the plans.

f.	Backfilling with new ballast to the plan grade.

g.	Re-installation of the track.

h.	Furnishing and installing a temporary wood crossing surface.

i.	Construction or reconstruction of the roadway approaches to the crossing after reconnection of the new track panel by the Alaska Railroad.

j.	Removal of the temporary wood crossing surface after three passes of rail traffic over the crossing.

k.	Furnishing and installing a new modular crossing surface.

l.	Completion of roadway approach surfacing, to include paving.

Coordination of the crossing reconstruction shall be arranged through the Chief Engineer of the Alaska Railroad by the Engineer.

Add the following:  Unless otherwise approved by the Engineer and with approval of the ARRC the following coordination sequence of construction shall be required for installation of the railroad crossings:

1.	The Contractor shall construct the track panel as shown on the project plans.  The centerline of the crossing will be marked on the rail panel.  The tie spacing will be in accordance with the crossing pad manufacturer's recommendations.  This work must be approved by the ARRC inspector prior to the scheduling of the crossing rebuild.  The rail anchors must be compatible with the crossing pads.

2.	The ARRC will make the necessary rail cuts in the existing track to facilitate the removal of the existing track panel through the crossing area.

3.	The ARRC will raise the existing track outside of the crossing prior to the rebuild.

4.	The Contractor shall supply the ballast for the grade raise to the site in a ARRC hopper car.

5.	The ARRC will disconnect the section of track to be removed by the Contractor.

6.	The Contractor shall remove the existing crossing materials and track materials.  The crossing materials may be removed prior to the track closure if arranged with the ARRC foreman in charge.  All salvaged track materials will become the property of the Contractor.

7.	The Contractor shall excavate to the dimensions shown on the project plans.

8.	The Contractor shall install geotextile and place ballast below design bottom of tie.

9.	The Contractor shall place the prebuilt track panel in place.

10.	The ARRC will connect the new track panel to the existing track.

11.	The Contractor shall place crib ballast as directed by the ARRC foreman in charge.

12.	The ARRC will raise, line, and tamp the track.

13.	The Contractor shall install geotextile and temporary wood plank crossing and perform necessary road work for a temporary highway crossing.  The temporary crossing shall remain in place a minimum of three passes by a train.

14.	The Contractor shall remove the temporary roadway surface and wood crossing.

15.	The ARRC will make the final raise, line and tamp the crossing.

16.	The Contractor shall install the modular crossing in conformity with the manufacturer's recommendations.

17.	The Contractor shall complete the match of the roadway approach surfaces to top of pavement prior to opening the roadway to highway traffic.

SECTION 618

SEEDING

Special Provisions

618-1.01  Description.  Delete this subsection and substitute the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded.  This work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

Seeding, Type 2A (wildflowers) shall be applied from Sta. 1340+10 to Sta. 1671+21.  Seeding, Type 2B (erosion control) shall be applied from Sta. 1671+21 to Sta. 2070+00.

618-2.01  Materials.  Add the following to the list of material specifications:

Mulch                      Section 727-2.01

618-3.01  Soil Preparation.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be covered with topsoil in accordance with Section 620, and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as topsoil is placed on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach onto the wetlands.  The performance of this work is incidental to seeding and will not be paid for directly.

618-3.03  Application Method.  In the first sentence of subparagraph b. under numbered paragraph 1., Hydraulic Method, delete the following:  "Item 619(1),".

Add the following:  Seed, mulch and fertilizer shall be applied as shown in the following tables for each seed mix type per 1,000 square feet.  If the hydraulic method for seed and mulch is used, it shall be made in one application.  The mulch rate shown is a minimum, and may be increased in accordance with the manufacturers recommendations.  All fertilizer shall be applied by the hydraulic method.

SEED MIX TYPE 2A (wildflowers)

Application

Ingredients                        Rate Lbs/MSF

Kentucky Bluegrass (Nugget)              0.20 lb.

Red Fescue (Arctared)                    0.10 lb.

Annual Ryegrass (Lolium)                 0.30 lb.

Alsike or Dutch White Clover             0.20 lb.

Wildflower mix*                          0.20 lb

TOTAL= 1.00 lb/MSF

*  Wildflower mix shall consist of the following species of seed:

Ox Eye or Shasta Daisy (Chrysanthemum Leucantheumum)  	Columbine (Aquilegia Caerulea)

Jacob's Ladder (Polemonium pulcherrium)

Lupine (Lupinus nootkaensis or arcticus)

Milk Vetch (Astragalus spp.)

Yarrow (Achillea millefolium)

Iceland Poppy (Papaver Nudicaule)

The wildflower mixture proportions may vary with seed availability;  however, the percentage of each species by weight shall not be less than 5 percent nor greater than 30 percent.

SEED MIX TYPE 2B (erosion control)

Application

Ingredients                        Rate Lbs/MSF

Bering Hairgrass (Norcoast)              0.30 lb.

Red Fescue (Arctared)                    0.30 lb.

Kentucky Bluegrass (Nugget)              0.20 lb.

Annual Ryegrass (Lolium)                 0.20 lb.

TOTAL= 1.00 lb/MSF

Mulch                                    35.0 lbs.

Fertilizer (20-20-10)                    12.0 lbs.

The Contractor shall not remove the required tags from the grass or wildflower seed bags.

618-3.04  Maintenance of Seeded Areas.  Add the following:  A reapplication of fertilizer shall be applied with water to areas using seed mix Type 2B between May 1 and September 15 of the year following seeding at a rate of one-half the initial application.

618-4.01  Method of Measurement.  Delete the second and third sentences of the second paragraph and substitute the following:  Seeding by the pound will be the number of pounds of seed (dry measure) accepted in place.  The amount of mulch and fertilizer used in this work, including any required reseeding, will be subsidiary to seeding and will not be measured separately for payment.

Delete the last paragraph.

618-5.01  Basis of Payment.  Add the following:  Fertilizer and mulch as well as any required reseeding as described above, will not be paid for directly, but will be subsidiary to the seeding item.

Delete pay item 618(2) and substitute the following:

Pay Item No.             Pay Item              Pay Unit

618(2A)           Seeding, Type 2A             Pound

618(2B)           Seeding, Type 2B             Pound

SECTION 619

SOIL STABILIZATION

Special Provisions

619-1.01  Description.  Add the following:  This work will consist of all required labor and materials to cover all embankment and cut slopes steeper than 2:1.

SECTION 620

TOPSOIL

Special Provisions

620-2.01  Materials.  Add the following:   Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

620-4.01  Method of Measurement.  Add the following:  Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(6/1/90)

SECTION 621

PLANTING TREES, SHRUBS AND VINES

Special Provisions

621-2.02  Fertilizer.  Add the following:  For the Cottonwood, Spruce and Birch trees, the chemical proportions of the fertilizer shall be 8-32-16 (Nitrogen-Phosphoric Acid-Potassium).

621-3.03  Planting.  Add the following to Item 6., Backfilling:  For the Cottonwood, Spruce and Birch trees, fertilizer shall be added to the backfill mix at a rate of 3 ounces per inch diameter of tree.

SECTION 626

SANITARY SEWER SYSTEMS

Special Provisions

626-1.01  Description.  Add the following:  For the purposes of these Special Provisions the "City of Palmer" shall mean the City of Palmer Public Works Department at (907) 745-3271.  This work shall include the installation and testing of sanitary sewer systems for acceptance by the City of Palmer.  The Contractor shall also provide as-built drawings in accordance with the conditions prescribed herein.

626-3.01  Construction Requirements.  Delete the words "or flexible connection" from the third paragraph.

Delete the seventh paragraph and add the following:  Where sewer conduit constructed under this contract approaches within 10 feet horizontal clearance and is above or less than 3 feet below an existing or a new water main, the sewer conduit shall be constructed with cast iron or ductile iron pipe for a distance of 10 feet perpendicular to and on each side of the water main.  The Contractor shall stagger the joints for the sanitary sewer conduit such that no joint shall be closer than 9 feet from the centerline crossing of the water and sewer conduits.  In addition, the vertical separation between the water and sewer conduits shall be 18 inches minimum, outside of pipe to outside of pipe.

Add the following:

Required Clearance from Water Mains.  When it is necessary to construct a water conduit crossing below a sewer conduit or within a vertical distance of 3 feet above the sewer conduit (less than 24 inches diameter), and the sewer main is not cast or ductile iron, and provided no joint is within 3 feet horizontally of the crossing or where the Engineer may direct, the sewer conduit shall be encased in a minimum thickness of 4 inches of concrete for a distance of 10 feet perpendicular to and on each side of the water conduit.

Wire fabric or other types of wire mesh, approved by the Engineer, shall be placed around the sewer prior to encasement with concrete to minimize cracking.  Construction of concrete encasement shall be in accordance with the applicable details on the plans.

Ductile iron encasement may be substituted for concrete when approved by the Engineer.

Suspension of Work.  The City of Palmer through the Engineer reserves the right to suspend the sanitary sewer installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections. Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

For non-emergency service interruption and suspension of service, the Contractor shall notify affected customers 7 days in advance of the scheduled suspension of service.  For emergency suspension of service, the Contractor shall provide such notice as is reasonably practicable under the circumstances.  The notification provided shall be done by leaving a door hanger at each premise notifying the customer of the date and times the suspension of service will be in effect.  Emergency suspension of service requires no notification.

If construction or excavation require the removal of any existing privately owned facilities on the provided sewer easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed 2 weeks.

Sanitary Sewer Conduit.  The outside of all ductile iron and cast iron pipe, fittings and other appurtenances used in sewer conduit construction shall be encased with one layer of 8-mil thick (0.2 mm) polyethylene film.  The polyethylene encasement shall be installed using any the following three methods:

Method A.

1.	Cut  polyethylene  tube  to  a length approximately 2-feet longer than the length of the pipe section.  Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

2.	Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

3.	After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube.  Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place.  Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up the slack width to make a snug, but not tight fit along the barrel of the pipe, securing the fold at quarter points.

4.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method B.

1.	Cut  polyethylene  tube  to  a  length approximately one foot shorter than that of the pipe section.  Slip the tube around the pipe, centering it to provide six inches of bare pipe at each end.  Take up the slack width at the top of the pipe to make a snug, but not tight, fit along the barrel of the pipe, securing the fold at quarter points; secure the ends as described in Method A.

2.	Before making up a joint, slip a three foot length of polyethylene tube over the end of the preceding pipe section, bunching it accordion-fashion lengthwise.  After completing the joint, pull the three foot length of polyethylene over the joint, overlapping the polyethylene previously installed on each adjacent section of pipe by at least one foot; make each end snug and secure as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method C.

1.	Cut polyethylene sheet to a length approximately two feet longer than that of the pipe section.  Center the cut length to provide a one foot overlap on each adjacent pipe section, bunching it until it clears the pipe ends.  Wrap the polyethylene around the pipe so that it circumferentially overlaps the top quadrant of the pipe.  Secure the cut edge of polyethylene sheet at intervals of approximately three feet.

2.	Lower the wrapped pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at joints to facilitate installation of the polyethylene.  After completing the joint, make the overlap and secure the ends as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Remove or Abandoned-in-Place Sanitary Sewer Conduit.  Any existing sanitary sewer conduits, or appurtenances designated on the plans or directed by the Engineer to be abandoned-in-place or removed shall be accomplished as an incidental item of construction.  Whenever or wherever an existing sanitary sewer conduit is abandoned-in-place, the Contractor shall empty the pipe of all waste, fill the pipe with sand and plug the ends.  Asbestos concrete pipe may be either crushed or removed.  In the event of cracked or crushed lines, the Contractor shall excavate to the next joint of pipe and install the plug.  Existing sanitary sewer conduit and all other contaminated material to be removed shall be disposed of at the Municipality of Anchorage Sanitary Land Fill at the Hiland Drive Interchange.  There will be no separate payment for disposal of the contaminated material at the land fill.

Manhole Cover Location.  All existing manhole assemblies shall be rotated to provide the location as indicated on the plans.  The Contractor shall rotate the existing cone or reducing slab, and barrel sections in the direction shown and in accordance with Subsection 604-3.01, Construction Requirements.  The manhole base section containing the pipe carrier (inverts) shall remain in place.  These manholes are being rotated away from the driving lanes and the proposed gutter flow line.

Verification of Existing Utilities.  At a sufficient distance prior to encountering a known obstacle or pipe or tying into an existing pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled.

The cost incurred for removal and realignment of backfilled pipe sections due to improper verification methods shall be borne by the Contractor.

626-3.02  Testing.  Delete in its entirety and substitute the following:  The Contractor shall clean and flush all sanitary sewer pipe installed prior to testing and final inspection.  He shall notify the Engineer 48 hours in advance (two working days) prior to any test.  The Engineer and the City of Palmer shall be present during all tests.  Two hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or canceled.

The Contractor shall furnish all tools, equipment, and labor necessary to complete the tests and shall verify from his own observations, or preliminary tests, that each line conforms with this specification before requesting the City of Palmer to observe and record the actual leakage.

The Engineer may require the Contractor to repair obvious leaks even though the total length of the test section falls within the maximum allowable leakage of the test used.

No test section shall exceed 1000 linear feet, unless approved by the City of Palmer in writing.

All sanitary sewer pipe installed shall be subject to either an infiltration test or an exfiltration test.  In those areas where, in the opinion of the City of Palmer, the water table is high enough to subject the pipe to a satisfactory infiltration test, it is not anticipated that an exfiltration test shall be required.  In checking leakage, there will be no allowance made for external hydrostatic head.  Where in the opinion of the City of Palmer the water table is not high enough to provide a satisfactory infiltration test, an exfiltration test shall be required.

The type of test, either infiltration or exfiltration, shall be determined by the City of Palmer.  The Contractor shall have the option of choosing only one method (air or water) of testing for each section tested.  All testing shall be considered a subsidiary obligation under this Contract and extra payment will not be allowed for this portion of work.

All wyes, tees, or ends of side sewer stubs and service connections shall be plugged or capped, and the plug or cap shall be securely fastened to withstand the internal test pressures.  Such plugs or caps shall be readily removable and their removal shall provide a socket suitable for extending the lateral connection.

The lengths of service connections shall be included in the computations to determine allowable leakage for the test section.

Infiltration Test.  Infiltration testing may be allowed at the City of Palmer's option when the natural ground water table is six feet above the crown of the higher end of the test section.  The maximum allowable limit for infiltration shall not exceed the rate of 50 gallons per inch diameter per mile per 24 hours.

Exfiltration Test (Using Water).  On completion of a section of sanitary sewer between manholes, or otherwise, the ends of all pipe shall be plugged, including service connections, and the pipe subjected to hydrostatic pressure.  Generally all testing is to be conducted after backfilling, prior to resurfacing, and after service connections are made.

A minimum head of six feet of water above the crown at the upper end of the test section shall be maintained for a period of four hours, during which time it will be presumed that full absorption of the pipe body has taken place and thereafter for a further period of one hour for the actual test of leakage.  During this one hour period the measured loss shall not exceed the rate of 50 gallons per inch diameter per mile per 24 hours.

Infiltration or exfiltration in greater amounts than the above listed leakage rates will be cause for rejection of the sanitary sewer and all repairs necessary to meet these requirements and retesting shall be at the expense of the Contractor.  If it is apparent that the leakage test results between any two manholes is not satisfactory, then the City of Palmer may require subsequent tests to establish the more exact location of the leakage areas.  Any section of sanitary sewer that does not meet the above requirements shall be rejected and the Contractor, at his own expense, shall make the necessary repairs to assure compliance.

Exfiltration Test (Using Air).  The Contractor shall furnish all facilities and personnel for conducting the test under the observation of the City of Palmer.  The equipment and personnel shall be subject to their approval.  The Contractor may desire to make an air test prior to backfilling for his own purpose.  However, the acceptance air test shall be made after backfilling has been completed, and compacted.

Immediately following the pipe cleaning, the pipe installation shall be tested with low pressure air.  Air shall be slowly supplied to the plugged pipe installation until the internal air pressure reaches 4.0 pounds per square inch greater than the average back pressure of any ground water that may submerge the conduit.  At least two minutes shall be allowed for temperature stabilization before proceeding further.

The pipeline shall be considered acceptable when tested at an average pressure of 4.0 psi greater than the average back pressure of any ground water that may submerge the pipe, if:

The total rate of air loss from any section tested in its entirety between manholes or between manhole and cleanout structures does not exceed 2.0 cubic feet per minute, or the following table may be used as a guideline for a satisfactory test by air for pipe sizes shown:

Pipe Diameter              Allowable Pressure Drop

in Ten (10) Minutes

8-inches                         2.7 psi

10-inches                         2.1 psi

12-inches                         1.8 psi

16-inches                         1.4 psi

18-inches                         1.2 psi

24-inches                         0.9 psi

48-inches                         0.5 psi

Pressure gauges shall be incremented in not more than 1/2 pound increments for accurate tests.

If the pipe installation fails to meet test requirements, the Contractor shall determine at his own expense the source of leakage, and he shall repair (if the extent and type of repairs proposed by the Contractor are acceptable to the Engineer) or replace all defective materials or workmanship. The completed pipe installation shall meet the requirements of this test or the alternative water exfiltration test before being considered acceptable.

Safety braces shall be required to hold plugs in place and to prevent the sudden release of the compressed air.  Due to the large forces exerted by an escaping plug during the testing of the pipe, workmen shall not be allowed in the manholes in which plugs have been placed, while tests are being conducted.  The Contractors testing equipment shall be arranged in such a manner that a  pressure relief device will prohibit the pressure in the pipeline from exceeding 10 psi.

Check of Line and Grade.  After backfilling and cleaning, but before final acceptance, all sanitary sewer mains, excluding service connections, may be checked for line and grade by closed circuit television.  A full circle of light must be seen and no pipe misplaced in line or grade.  Any excess deviation shall be corrected by the Contractor at his expense prior to final acceptance of the pipe line.

The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a semi-final inspection of the project.  This inspection will be performed in the presence of the Engineer, the City of Palmer, and the Contractor.  Copies of a list of deficiencies, if any, indicated by the inspection will be furnished to the Contractor by the Engineer for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and at that time an acceptance inspection will be performed.

The Contractor shall take precautions to allow no sewage to enter the new sewer conduit until it has been inspected, tested and accepted for operation and maintenance by the City of Palmer.  Any deviations shall require written approval.  The new sewer line may be tested and inspected in incremental runs, manhole to manhole.

626-3.03  As-Builts of Plans and Working Drawings.  Add the following subsection:  A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as it is actually installed.  This as-built information shall be recorded on a print of the plans affected, and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed.  Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When this sanitary sewer system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance by the owning Utility.

626-5.01  Basis of Payment.  Add the following:  The unit bid price for the sanitary sewer conduit will include all necessary excavation to the plan grade, shoring as required, and backfill with native materials outside the normal lines of the pavement structure.

No separate payment for providing pumping of effluent during construction will be made but will be considered incidental to the sewer improvement.

Payment for sewer manholes will be made under Item 604(2), Sanitary Sewer Manhole, Type A.

Payment for adjusting existing sewer manhole will be made under Item 604(4), Adjust Existing Manhole.

Payment for insulation board will be made under Item 635(2), Insulation Board.

Add the following pay item:

Pay Item No.           Pay Item               Pay Unit

626(10)       Sanitary Sewer As-Builts        Lump Sum

SECTION 627

WATER SYSTEM

Special Provisions

627-1.01  Description.  Add the following:  For purposes of these Special Provisions, the "City of Palmer" shall mean the City of Palmer Public Works Department at (907) 745-3271.  This work shall include the installation, testing, flushing, and chlorination or hand cleaning of water systems for acceptance by the City of Palmer.  The Contractor shall also provide as-builts in accordance with the conditions prescribed herein.

In conjunction with working around and/or adjusting the City of Palmer water valves, the Contractor shall exercise due care.  Prior to commencement of work by the Contractor, the City of Palmer shall check and correct deficiencies which may exist in any valve or valve box.  The Engineer and Contractor shall witness the condition and location of each valve or valve box.  Failure to partake in the inspection by the Contractor will result in his forfeiting all rights to deny damages at a later date during the course of the work.  Notice that the Contractor is ready for the above inspection shall be in writing to the City of Palmer and shall be submitted giving at least 48 hours notice.  The Contractor shall furnish a copy of the notice to the Engineer.

It shall be the Contractors responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction.  If at any time after the inspection as outlined above the City of Palmer finds a valve or valve box damaged or rendered inoperable by the Contractor, the Contractor shall repair them at his own expense.

627-3.01  General Construction Requirements.  Add the following before the first paragraph:  The City of Palmer through the Engineer reserves the right to suspend the water system installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

The Contractor shall furnish to the Engineer complete installation drawings for the project prior to fabrication.  All restrained joint areas shall be detailed to include fittings, piping and deflection points.  The Contractor shall provide design calculations, prepared and sealed by a licensed professional engineer, registered in the State of Alaska, for all restrained joint areas to assure adequacy, ability to resist longitudinal forces and compliance with the Contract Documents.

If construction or excavation require the removal of any existing privately owned facilities on the provided water easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed 2 weeks.

The Contractor shall maintain uninterrupted water service to the McDonalds restaurant during regular business hours.

Add the following to the third sentence of the third paragraph:  "or so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled."

Add the words "and incidental" between the words "subsidiary" and "item" in the fourth paragraph.

Delete the fifth, sixth and seventh paragraphs and substitute the following:  Prior to removing or disrupting service to fire hydrants, the Contractor shall provide written notice to the Palmer Fire Department at least 48 hours in advance of the work, with a copy to the Engineer.

Additionally, the Contractor shall notify all affected property owners, the Engineer, and the City of Palmer 48 hours prior to interruption of any water service.  The Contractor shall provide temporary service to all those property owners with disrupted water service if the interruption exceeds 12 hours.

The Contractor shall provide any necessary fittings, valves, temporary connections or appurtenances necessary in order to maintain the water distribution system.  Any costs involved in service changeovers and providing temporary water service shall be subsidiary.  The Contractor shall be responsible for all damages incidental to interruption of service that may be due to his operations.

Prior to water system installation, the Contractor shall submit to the Engineer a detailed plan for the installation of the new water systems and for removal/abandonment of existing water systems that are to be removed or abandoned for review prior to commencement of work.  The plan shall be of sufficient detail to clearly indicate the proposed work sequence, schedules, and disruption of water service.

Add the following to the eighth paragraph:  Concrete thrust blocks or tie back rods of the type shown on the plans shall be installed where the pipe line terminates or changes alignment, utilizing a tee, cross, bend, reducer, or similar fitting.  Either poured-in-place or precast thrust blocks are acceptable if the minimum base area is sufficient as shown on the plans.  Concrete for the thrust blocks shall be Class A.  If the Contractor elects to use poured-in-place thrust blocks, all pipe and fittings exposed to concrete shall be double wrapped with 4-mil Visqueen or equal, prior to placement of the concrete.  Poured-in-place thrust blocks shall be cured a minimum of 7 days prior to the application of any hydraulic loads.

Add the following:

Abandon Existing Pipe.  Existing pipe shown to be abandoned shall be abandoned-in-place as an incidental item of construction.   Pipe abandoned-in-place shall be filled with a sand or cement slurry and the ends plugged or shall be crushed and backfilled as directed by the Engineer.  In those areas that the presence of existing pipe causes a conflict with new or existing utilities or facilities the pipe may be removed as an incidental item of construction.  All abandoned materials removed and not reused shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.

Disconnect and Reconnect Water Service.  In the course of construction, the Contractor will encounter water service pipe requiring disconnection from mains to be abandoned or removed, and reconnection to new water conduit facilities. The Contractor shall disconnect the existing water service, replace the service from the new main to the property line and reconnect the on-property portion of the service.  This item of work shall include all materials, excavation, disconnection, installation, reconnection, bedding, backfill, and mechanical compaction for completed services in-place.  Existing 3/4-inch services shall be replaced with 1-inch services from the main to the property line and shall have a 1-inch to 3/4-inch reducer installed at the property line reconnection point.  All service lines 2-inches and smaller shall be constructed of seamless, soft-drawn, Type "K" copper.  All service lines larger than 2-inches shall be constructed of ductile iron pipe, with two 3/4-inch tie rods installed on each service line from the main to the property line.  Connection to the water conduit of service lines larger than 2-inches shall be accomplished by the City of Palmer connection crews, for which a minimum of 48 hours notice shall be provided prior to the required time of connection.

Rights In and Use of Materials Found on the Work Site.  Unless specifically addressed otherwise in these special provisions, all existing water valves, tees, bends, and conduit (including ductile iron pipe) removed but not reinstalled, and declared "salvageable materials" shall become the property of the Contractor.

Final Acceptance.  The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a pre-final inspection of the project. This inspection will be performed in the presence of the Engineer, the City of Palmer, and the Contractor. Copies of a list of deficiencies, if any, indicated by this inspection will be furnished to the Contractor for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and an acceptance inspection will be performed.

627-3.02  Installation of Conduit.  Add the following to the second paragraph:  However, at a sufficient distance prior to encountering a known obstacle or tying into an existing pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled. The costs incurred for removal  and realignment of backfilled conduit sections due to improper verification methods shall be borne by the Contractor.

Delete the eighth paragraph and substitute the following:  Deflections from a straight line or grade, as required by vertical curves, horizontal curves, or offsets shall not exceed 50 percent of the manufacturer's recommended maximum deflection.  If the alignment requires deflection in excess of the above limitations, the Contractor shall furnish special bends to provide angular deflections within the limits allowable.  Wherever possible, the Contractor shall achieve the desired deflection by taking advantage of reduced deflections over multiple joints.  Short-radius curves and closures shall be formed by shorter lengths of pipe, bevels, or fabricated specials.

A maximum 0.2-foot deviation from design alignment and elevation will be allowed.  Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed.  All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the pipe and not by blocking or wedging up.

The Contractor shall have survey instruments such as transit and level for transferring alignment and grades from offset hubs.  He shall also have in his employ a person who is qualified to use such instruments and who shall have the responsibility of placing and maintaining such construction guides.  The Contractor shall furnish to the Engineer a copy of the surveyor's record notes for the newly-installed conduit and appurtenances.  The practice of placing backfill over a section of conduit to provide a platform for the instruments shall be subject to the approval of the Engineer.

Conduit that has the grade or joint disturbed after laying shall be taken up and relaid.  Water shall be kept out of the trench until the jointing is completed

Add the following:

Conduit Joints.  Conduit that has the grade or joint disturbed after laying shall be taken up and relaid.  Water shall be kept out of the trench until the jointing is completed.

The Contractor has the option of using either mechanical or push-on joints for conduit installed in trenches, except in those areas where restrained joints are required.  All joints shall conform to the requirements of AWWA C-600.

The Contractor will be required to use mechanical joints on all fire hydrant leads.  The Engineer may check any or all mechanical joints to assure proper torque as specified by the manufacturer.

Two electrical continuity straps shall be installed on each side joint for pipes less than 12-inches in diameter.  Straps are to be welded to a clean, dry surface.  All welds and uncoated surfaces shall be coated with a coal tar pitch to the satisfaction of the Engineer.

Conduit Wrap:  The outside of all ductile iron and cast iron pipe, fittings, valves and other appurtenances used in water line construction  shall be encased with one (1) layer of 8-mil thick (0.2 mm) polyethylene film.  The polyethylene encasement shall be installed using any the following three methods:

Method A.

1.	Cut  polyethylene  tube  to  a  length approximately 2-feet longer than the length of the pipe section.  Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

2.	Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

3.	After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube.  Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place.  Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up the slack width to make a snug, but not fit along the barrel of the pipe, securing the field at quarter points.

4.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method B.

1.	Cut  polyethylene  tube  to  a  length approximately 1-ft shorter than that of the pipe section.  Slip the tube around the pipe, centering it to provide 6-inch of bare pipe at each end.  Take up the slack width at the top of the pipe to make a snug, but not tight, fit along the barrel of the pipe, securing the fold at quarter points; secure the ends as described in Method A.

2.	Before making up a joint, slip a 3-ft length of polyethylene tube over the end of the preceding pipe section, bunching it accordion-fashion lengthwise.  After completing the joint, pull the 3-ft length of polyethylene over the joint, overlapping the polyethylene previously installed on each adjacent section of pipe by at least 1-ft; make each end snug and secure as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method C.

1.	Cut polyethylene sheet to a length approximately 2-ft longer than that of the pipe section.  Center the cut length to provide a 1-ft overlap on each adjacent pipe section, bunching it until it clears the pipe ends.  Wrap the polyethylene around the pipe so that it  circumferentially overlaps the top

quadrant of the pipe.  Secure the cut edge of polyethylene sheet at intervals of approximately 3-ft.

2.	Lower the wrapped pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at joints to facilitate installation of the polyethylene.  After completing the joint, make the overlap and secure the ends as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Thrust Restraint.  Concrete thrust blocks, tie back rods or restrained joints of the type shown on the plans, or specified herein, shall be installed where the pipe line changes alignment utilizing a tee, cross, bend, or similar fitting.

Conduit ends left for future connections shall be plugged or capped and anchored as shown on the plans, or as directed by the Engineer.

627-3.04.  Add the following:  Valves shall be installed where shown on the plans.  Valves shall have the interiors cleaned of all foreign matter before installation.  If the valve is at the end of the line, it shall be plugged prior to backfilling.  The valve shall be inspected by the City of Palmer's representative, in the open and closed positions to ascertain that all parts are in good working condition.

627-3.05.  Delete the first paragraph and substitute the following:  Valve boxes shall be installed over the valves as shown on the plans, with base section centered over the operating nut of the valve and resting on well compacted backfill.  Top section shall be so set as to allow equal movement above and below finished grade, final elevation to be 1/4-inch below finished grade of pavement unless otherwise directed.  Top of base section shall be approximately on line with nut at top of valve stem, and the entire assembly shall be plumb.

Add the following after the second paragraph:  In areas where running sand is encountered, provisions shall be made to restrict sand from entering the bottom section of the valve box.

The Contractor shall expose all valve boxes for pre-final and final inspection.  After final inspection of the valves located in unpaved areas, sawdust shall be poured directly over the valve box lid and covered with gravel to facilitate location in the future.

627-3.06  Testing Water System.  Delete in its entirety and substitute the following:  The Contractor shall notify the Engineer in writing 48 hours in advance (two working days) prior to any test.  The City of Palmer and the Engineer shall be present during all tests.  Two (2) hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or canceled.

1.	Flushing.  All flushing shall be coordinated with the City of Palmer.  All newly-laid water conduit, except the 30-inch line, shall be "open-bore" flushed to remove any foreign matter to the satisfaction of the City of Palmer.  A detailed plan for cleaning of the lines shall be submitted to the Engineer for review and approval prior to commencement of work.

"Open-bore" flushing shall be accomplished prior to hydrostatic testing and disinfection at all extremities including all stubouts and dead-ends. The Contractor shall furnish, install and remove all fittings and conduit necessary to perform the flushing.  Under no circumstances will "open-bore" flushing through hydrants or reduced outlets be permitted.

All flushing of newly-installed conduit shall be accomplished between the hours of 1:00 AM and 6:00 AM, unless otherwise authorized by the City of Palmer.  Flushing shall be considered incidental to this work and no separate payment shall be made.

2.	Hydrostatic Testing.  A hydrostatic test shall be conducted on all newly-constructed water conduit, fire hydrant leads and stub-outs after "open-bore" flushing in the presence of the Engineer and the City of Palmer in accordance with the requirements of AWWA C-600 unless hereinafter modified. The Contractor, at his option, may either use a pressure test or a leakage test.

The Contractor shall furnish all necessary assistance, equipment, labor, materials and supplies (except the test pressure gauge) necessary to complete the test to the satisfaction of the City of Palmer.  The Contractor shall suitably valve off or plug the outlet to the existing or previously-tested water main at this expense, prior to making the required hydrostatic test.

Prior to testing, all air shall be expelled from the conduit. If permanent air vents are not located at all high points, the Contractor shall, at his expense, install corporation cocks at such points so the air can be expelled as the conduit is slowly filled with water.

Where any section is provided with poured-in-place concrete thrust blocks for fittings or hydrants, the hydrostatic test shall not be made until at least 7 days after installation of the thrust blocks unless otherwise approved by the Engineer.

No hydrostatic test section shall exceed 1000-feet unless approved by the City of Palmer in writing. All main line valves, fire hydrant auxiliary valves, fire hydrant main valves and plugs shall be tested.  All intermediate valves within the section being tested will be fully closed and reopened as directed by the Engineer during the actual test. Only static pressure will be allowed on the opposite side of the end valves of the section being tested.

All hydrostatic testing will be performed through test copper. Use of fire hydrants and service connections for testing will not be allowed.

The hydrostatic pressure shall be a minimum of 150 psi, and the duration of each hydrostatic pressure test shall be 30-minutes. After the required test pressure has been reached, the pumping will be terminated. If the pressure remains constant for 30-minutes without the aid of a pump, that section of the conduit will not be subjected to any further hydrostatic tests.

If a hydrostatic pressure test fails on any section, the Contractor has the option to perform a leakage test on that section.  The City of Palmer will furnish the test gauge and measuring device, and the Contractor shall furnish all other necessary assistance, equipment, labor, material and supplies to conduct the test.

Leakage for a newly-installed conduit is determined by the following formula:

L = (ND) P0.5  where:

7400

L = Allowable leakage in

gallons per hour

N = Summation of mechanical

and push-on joints in

length of pipe tested

D = Diameter of conduit in

inches

P = Test pressure in pounds

per square inch

The duration of each leakage test shall be 2 hours and during the test, the conduit shall be subjected to the constant test pressure as defined above. The test pump shall be valved to insure that constant test pressure is maintained throughout the test and all excess water will be returned to a storage tank.  If the pressure decreases below the required test pressure during the 2-hour period, the preceding portion of that test shall be declared void.

Cracked or defective conduit, gaskets, mechanical joints, fittings, valves or hydrants discovered as a consequence of the hydrostatic tests shall be removed and replaced with sound material at the Contractor's expense. The test shall then be repeated until the results are satisfactory.

In the instance where connection is made to a presently installed water conduit a new valve shall be installed on the connection.  The Contractor shall suitably seal off the outlet leading to the presently installed conduit prior to making the field tests.

3.	Continuity Tests.  The Contractor shall perform electrical conductivity tests on all mains less than 12-inches in the presence of the Engineer and the City of Palmer.  The Contractor shall maintain a circuit of 600 amperes DC current for a period of 15-minutes.  Input current shall not exceed 10 percent of the return circuit.  All equipment necessary to maintain the circuit shall be supplied by the Contractor.

All continuity tests will be through wires brought to the surface or through 3/4-inch, minimum, copper pipe connected to the main.  The use of fire hydrants and valves, as substitutes for wires will not be accepted.  All wires brought to the surface to complete the continuity test shall be removed to a depth of 2-feet below finished street grade upon completion of the tests.

627-3.07  Disinfection of Waterlines.  Delete paragraphs 1 thru 4 and add the following:  This subsection applies to the disinfection of all portions of the water system, including all valves and stops and any portion of the existing connection system that might have become contaminated during construction activities.  Disinfection shall be accomplished after completion of pressure and/or leakage tests in compliance with AWWA C-601, Disinfecting Water Mains.

Chlorine shall be used for disinfection, and shall be applied only by one of the following methods:  (1) liquid chlorine gas and water mixture, (2) direct chlorine gas feed, or (3) calcium hypochlorite and water mixture. Calcium hypochlorite shall be comparable to commercial products known as HTH, Perchloren or Machochlor. The chlorinating agent shall be applied at the beginning of the section adjacent to the feeder connection, insuring treatment of the entire line. Water shall be fed slowly into the new conduit with chlorine applied in amounts to produce a dosage of forty (40) ppm to fifty (50) ppm. Application of the chlorine solution shall continue until the required dosage is evident at all extremities of the newly-laid conduit.

Chlorine gas-water mixture shall be applied by means of a solution-feed chlorinating device. Chlorine gas shall be fed directly from a chlorine cylinder equipped with a suitable device for regulating the rate of flow and effective diffusion of gas within the conduit. Calcium hypochlorite shall be injected or pumped into the water conduit. During the chlorination process, all intermediate valves and accessories shall be manipulated so that the strong chlorine solution in the conduit being treated will not flow back into the conduit supplying the water. Hydrostatic testing of water conduit containing the chlorine mixture will not be allowed.

A residual of not less than five (5) ppm chlorine shall be produced in all parts of the water conduit and retained for a minimum period of 24 hours, after which it shall be flushed from the conduit at its extremities until the replacement water tests are equal chemically and bacteriologically to those of the permanent source of supply.  In no instance will a water conduit be chlorinated before "open-bore" flushing.

CHLORINATION

Conduit Diameter      Dosage (oz. per 100 feet)

6-inch                     1.35 oz

8-inch                     2.75 oz

10-inch                     4.30 oz

12-inch                     6.19 oz

16-inch                    11.00 oz

The above table is to be used as a guide for chlorinating mains by the calcium hypochlorite and water mixture method. The given dosage per 100 feet results in a chlorine solution of forty (40) to fifty (50) ppm.  This dosage takes into account that Contractors most frequently use granular HTH, which is 65 percent pure.  If another chlorinating agent is used, the dosage must be adjusted.  Caution should be exercised against producing too high a concentration of chlorine in the conduit.

After completion of all testing, all test and air vent copper pipe shall be removed and the corporation cock closed at the main in the presence of the Engineer and the City of Palmer.

627-3.08  As-Builts of Plans and Working Drawings.  Add the following subsection:  A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed.  This as-built information shall be recorded on a print of the plans affected and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed.  Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When the water system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance of the system by the owning Utility.

627-4.01  Method of Measurement.  Delete Subparagraph 1 and 5 in their entirety and substitute the following:

1.	Water Conduit.  Measurement for water conduit with appurtenances shall be per linear foot of horizontal distance of the various sizes and classes furnished and installed as set forth in the Bid Schedule.  Measurement will be from station to station as staked in the field and as shown on the plans, except where the grade exceeds 25 percent, in which case measurement will be by actual conduit length.  Fittings, tees, reducers, crosses, bends, couplings, etc., for water conduit shall be included in the linear foot cost of the water main.

5.	Valves, Valve Boxes and Markers.  The quantity to be paid shall be the actual number of valves, including boxes and marker posts, of each class and size furnished, installed, and accepted.

Add the following:

6.	Disconnect and Reconnect Water Services.  The quantity to be paid shall be the actual number of services of each size disconnected  from  the  old main and reconnected to the new main.

7.	Remove Water Valve.  The quantity to be paid shall be the actual number of valves removed from the  old main.

627-5.01  Basis of Payment.  Add the following: Payment for Item 627(1-8), 8-inch Ductile Iron Water Conduit, Class 52, will include all necessary excavation to plan grade, shoring as required, and backfill of native materials outside the normal lines of the roadway pavement structure.  Removal of 223 feet of existing 6-inch steel water line, and removal of the valve box at Sta. "GH" 1643+42, 57-ft Right, will not be paid for directly, but will be subsidiary to Item 627(1-8), 8-inch Ductile Iron Water Conduit, Class 52.

Payment for insulation board will be made under Item 635(2), Insulation Board.

Add the following Pay Items:

Pay Item No.            Pay Item                 Pay Unit

627(13-__)    Disconnect/Reconnect ___-inch      Each

Water Service

627(15)          Remove Water Valve              Each

627(20)         Water Line As-Builts           Lump Sum

SECTION 630

GEOTEXTILE FOR EMBANKMENT SEPARATION

AND REINFORCEMENT

Special Provisions

Delete this Section in its entirety and substitute the following:

630-1.01  Description.  Prepare surfaces and furnish and place geotextiles for embankment separation and/or reinforcement as shown on the plans or as directed.

630-2.01  Materials.  Geotextile material and thread used in joining geotextiles by sewing shall conform to Subsection 729-2.01, Embankment Separation and Reinforcement.

630-3.01  Construction.

1.	Surface Preparation.  Prepare surface by removal of stumps, boulders and other sharp objects, and dewatering any areas as necessary.  Fill holes and large ruts with material as shown on the plans or as approved.  Material used to fill ruts and holes will be paid for at the unit price for the class of material used.  Removal of stumps, boulders, sharp objects and dewatering, if necessary, will be considered subsidiary to this item.

2.	Fabric Laying.  Unroll fabric (geotextile) directly onto the prepared surface.  Stretch fabric to remove any creases or wrinkles.  Keep fabric taut during placement and spreading of cover material.

Lay fabric parallel to the direction of the material spread.  When laid on horizontal curves, it shall be placed in segment lengths not exceeding those listed in Table 630-1, with butt ends cut to match and sewn or overlapped.  When laid on tangents, the fabric shall be straightened and butt ends sewn or overlapped.

TABLE 630-1

GEOTEXTILE PLACEMENT ON CURVES

| Degree of Curve | Maximum Segment Length (feet) |
| --- | --- |
| 1 | 125 |
| 2 | 90 |
| 3 | 75 |
| 4 | 65 |
| 5 | 55 |
| 6 | 50 |

c.	Fabric Joining.  Join fabric by sewing or overlapping.  Bonding or other attachment methods may be used, subject to the approval of the Engineer.  If sewn, all seams shall be sewn by butterfly or J-seams and develop a minimum of 85 percent of the specified geotextile strength.  Seams shall be sewn with a double-thread chain-lock stitch.  The seam shall be 1-1/2 inches (+1/4 inch) from the outside edge of the fabric.  If seams are to be overlapped, adjacent sections of fabric shall be overlapped a minimum of three feet unless otherwise shown on the plans.

4.	Material Placing and Spreading.  During placing and spreading, a minimum depth of 1 foot shall be maintained at all times between the fabric and the wheels or tracks of the construction equipment.  Spread the material in the direction of the fabric overlap.  Maintain a proper overlap and fabric continuity.  If sewn or bonded seams are used, place the cover material and spread in only one direction for the entire length of the geotextile.  On weak subgrades, spread the cover material simultaneously with dumping to minimize the potential of a localized subgrade failure.

Construction equipment shall not make sudden stops, starts, or turns on the cover material.  Use a smooth drum roller to achieve the specified density.

5.	Geotextile Repair.  If fabric used for separation should be torn for any reason, the cover material shall be cleaned from the torn area and new fabric shall be overlapped a minimum of three foot around the edges of the torn area.  The patch shall remain in place when material is placed over the affected area.

6.	Shipping and Handling.  Protect fabric from direct sunlight, ultraviolet rays, temperatures greater than 140 degrees F, moisture, and contamination from mud, dirt, dust, and debris.  Label or tag each roll to provide product identification.  Geotextiles will be rejected if at the time cover material is placed they have been removed from protective wrapping for more than five days, or if they have detrimental defects or damage which  cannot be repaired in the field.

630-4.01  Method of Measurement.  Geotextile will be measured in final position by the square yard, determined by multiplying plan neat line width by the measured length parallel to installation centerline along the ground surface, for installations acceptably completed.  No allowance will be made for overlap, whether at joints or patches.  No payment will be made for geotextile placed beyond the limits shown on the plans unless placed at the prior, written direction of the Engineer.

630-5.01  Basis of Payment.  Payment will be made at the contract unit price per square yard.  This price shall be full compensation for furnishing all materials, surface preparation, delivering and laying the fabric and for all labor, equipment, tools and incidentals necessary to complete this item.

Payment will be made under:

Pay Item No.             Pay Item              Pay Unit

630(1)         Geotextile, Separation     Square Yard

(7/15/91)

SECTION 635

INSULATION BOARD

Special Provisions

635-1.01  Description.  Add the following:  Insulation will be placed between a storm drain and a sanitary sewer or water line when the separation is less than 3-feet.  Insulation will also be placed in areas where ground cover, over waterlines or sanitary sewer line, is reduced to 10 feet or less.

635-2.01  Materials.  Add the following:  The insulation board shall be rigid, homogeneous, and essentially unicellular, and shall conform to the following:

Property                  Test Method        Value

Compression Strength,

psi, minimum at yield          AASHTO M-230        35

or 5 percent compression

Water Absorption,

maximum percent                AASHTO M-230       0.25

by volume

Thermal Resistance, min.

R-Value at 75F                ASTM C-177          17

F-SF-Hr/BTU

635-4.01  Method of Measurement.  Delete and add the following: The quantity to be paid will be the number of square feet of insulation board, including transitions, regardless of thickness, complete and accepted.

635-5.01  Basis of Payment. Add the following pay item:

Pay Item No.        Pay Item          Pay Unit

635(2)       Insulation Board     Square Foot

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01  Description.  Add the following:  This work includes the construction of public approaches at locations shown on the plans.

639-2.01  Method of Measurement.  Add the following:  Public approaches will be measured per each constructed as shown on the plans, or as directed.

639-3.01  Basis of Payment.  Add the following:  Payment for public approaches will be full compensation for furnishing all equipment and labor necessary to complete the work as indicated.  Materials required to construct driveways will be paid for separately under the respective items listed in the bid schedule.

Add the following pay item:

Pay Item No.        Pay Item          Pay Unit

639(3)        Public Approaches      Each

Delete the last paragraph and substitute the following:  The contract unit price for driveways and public approaches will be full compensation for furnishing all  equipment and labor necessary to complete the work as specified.  Materials required to construct driveways and public approaches will be paid for separately under their respective items listed in the bid schedule.

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-2.01  Method of Measurement.  Delete item 3. and substitute the following:

3.	When the letter of project completion has been issued and the Contractor has made all the required submittals the remaining balance of the amount for this item will be paid.  (5/7/91)

640-3.01  Basis of Payment.  Add the following:  Preparation of the CPM work schedule and two week work plans in accordance with Section 108, will not be paid for directly, but will be subsidiary to Item 640(1) Mobilization and Demobilization.

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

Special Provisions

641-2.01  Construction Requirements.  Add the following:  The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water.  The temporary erosion and pollution control plan shall address the measures the Contractor shall implement in the containment, cleanup, and disposal of such substances as well as the methods to be utilized for disposing of waste oil or other hazardous substances generated by construction equipment or activities.  The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.  The plan shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

641-2.02  Best Management Practices.  Add the following subsection:  Erosion and sediment control measures are more easily accomplished if construction operations are properly scheduled.  Operations should be planned, when possible, for that time of year when potential for erosion is low.

There are a number of factors to consider and operations to schedule in the development of an acceptable temporary erosion and pollution control plan.  These include, but are not necessarily limited to the following:

1.	Clearing by cutting, slashing and disposing of the trees and other debris.

2.	Installation of temporary erosion and sediment control measures on the downhill side of the construction work area before building the embankment or excavating a slope.

3.	Construction of temporary drainage ditches to convey off-site drainage through the work area and diversion of the flow before excavating for the permanent drainage structure.

4.	Installation of all erosion and sediment control measures at the toe of embankment and excavation operations.  Silt fences are a structural method for providing temporary erosion and sediment control.

5.	Construction of the embankment in horizontal lifts, providing protection from erosion by temporarily or permanently mulching and seeding the slopes in vertical increments, preferably of no more than 10-feet.  Keep the top of the work area shaped and compacted so that surface water will run off without causing serious erosion should a storm occur.  At the  end of each  day's work or before a storm, berms and temporary downdrains must be constructed to control the release of on-site drainage.

6.	Excavation operations performed in the same manner as the embankment operation with the exception of slope drains and compaction.  This operation will release on-site drainage at a point where appropriate control measures have been installed.  The excavated slope must be finished as it is constructed and incrementally protected and seeded.

7.	Shaping and compacting the surface of the embankment or cut when the area reaches subgrade elevation.  Control surface runoff by berms and ditches and release through temporary pipes or ditches.  Detain sediment-laden runoff and trap sediment before releasing runoff from the construction area.

8.	Inspection and maintenance of each erosion and sediment control measure should be performed after each significant storm.  Silt fences should be inspected periodically for damage, such as tearing by wind, animals or equipment, and for the amount of sediment which has accumulated.  Removal of the sediment is generally necessary when it reaches half the height of the silt fence.    In situations

where access is available, machinery can be used; otherwise it must be removed manually.  The key elements to remember are:

a.	The sediment deposits should be removed when heavy rain or high water is anticipated.

b.	The sediment removed should be placed in an area where there is little danger of erosion.

(7/1/90)

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  Description.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix A.

642-3.01  Construction Requirements.  Add the following to the third paragraph:  Work under this item shall also include the referencing of the existing centerline from Sta 1340+10 to Sta 1626+85 for the purpose of asphalt yield control.  This referencing will be done at every even (100-ft) station from Sta. 1340+10.  The reference stake will show centerline offset and station.  Reference to the "Establishment of Point-of-Rotation" shown on the plans shall also be included under Item 642(1), Construction Surveying.

Add the following:

12.	The Contractor's survey crews shall comply with approved traffic control plans.  Crews shall coordinate their activities with the project's Worksite Traffic Supervisor.

642-4.01  Method of Measurement.  Add the following:  Pay Item 642(2), Three Person Survey Party, shall be used only for extra, additional, or unanticipated work made necessary by changes in the project as directed.

642-5.01  Basis of Payment.  Add the following:  If staking for extra, additional or unanticipated work as stated above is performed by a two person survey party, payment will be made at 75 percent of the unit price for Item 642(2), Three Person Survey Party.  If a single person is required for additional office computations or there is work requiring only one person, payment will be made at 32 percent of the unit price for Item 642(2).

(5/7/91)

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  Traffic Control Plan.  Add the following to the third paragraph:  All TCP's submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

643-1.04 Construction Phasing Plan.  Revise the first sentence to read as follows:  A Construction Phasing Plan shall be submitted at least five working days prior to the preconstruction conference for approval by the Engineer and shall consist of the following:  (5/7/91)

Delete Items 2. and 3. and substitute the following:

2.	Division of the Construction Sequencing Plan into steps.  A plan for each step shall show the work areas and traffic routing consistent with the Progress Schedule.  Changes shall be submitted to the Engineer for approval 30 days in advance of their proposed implementation.

3.	TCP's corresponding to each step of the Construction Sequencing Plan in accordance with Subsection 643-1.02, Traffic Control Plan.

643-2.01  Materials.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8-feet.

Delete numbered paragraph 8. in its entirety and substitute the following:

8.	Work Zone Pavement Markings.  Work zone pavement markings shall be either paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08, preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.  The markings shall be applied in accordance with Section 670, Traffic Markings, and the manufacturer's recommendations.

(5/7/91)

643-3.02  Roadway Characteristics During Construction.  Add the following to the first paragraph:  The maximum spacing between channelizing devices in a taper should be approximately equal in feet to the speed limit.

Delete the second paragraph.

643-3.03  Public Notice.  Add the following:  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of commencing construction, resuming construction after seasonal suspension, or any scheduled delay or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure.  Advertisements shall be published in the following newspapers:

1.	Anchorage Daily News

2.	Anchorage Times

3.	Frontiersman

4.	Valley Sun

The Contractor shall indicate on the ad order a first preference for the local news section, and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.  Advertisements shall be promptly canceled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

The Contractor shall notify the owners of businesses and residences that front on the Glenn Highway or are located on dead end streets accessing the Glenn Highway, of any scheduled road closure or of curb and driveway reconstructions affecting them.  The notices (flyers) shall contain the project name, a map, detailed traffic control information, effective dates, and the Contractor's name and telephone number.  The property owners shall receive the notices a minimum of 3 days prior to the scheduled work.

643-3.04  Traffic Control Devices.    Under Item 1., Embankments, change the reference from "Annual Average Daily Traffic (AADT)" to read "Average Daily Traffic (ADT)".

Add the following to Item 1., Embankments:  Barrier reflectors shall be mounted on the face of barrier adjacent to traffic on 50-foot centers and shall be a minimum height of 18 inches above the surface of the roadway.

Delete numbered paragraph 4. in its entirety and substitute the following:

4.	Work Zone Pavement Markings.  Pavement Markings shall be in place before opening a paved roadway to public traffic for longer than one continuous work shift.

Temporary Pavement Markings shall be installed and maintained on all new and overlay Hot Asphalt Concrete Pavements, Seal Coats and Surface Treatments;  whenever existing pavement markings for centerline or lane lines have been obliterated or worn off;  and until final pavement markings (covered under Section 670) can be placed on the final pavement surface.  Temporary Pavement Markings are also required on temporary pavements, detours, and interim paving lifts.

Temporary Pavement Markings shall consist of marking the work zone in accordance with this subsection, the traffic control plans, and Parts III and VI of the Alaska Traffic Manual.

Conflicting pavement markings shall be removed in accordance with Subsection 670-3.04, Paint Removal.  Construction shall be staged so that no traffic is routed over conflicting markings.

Sections of existing roadway that will be opened to traffic during the winter shall be marked at the same location as the existing lines and markings unless shown otherwise on the plans, an approved traffic control plan, or as directed by the Engineer.

Short-term operations.  The following exceptions to Part III of the Alaska Traffic Manual are allowed for Temporary Pavement Markings which will be in place for less than two weeks:

a.	Passing Zones.

Broken line pavement markings shall conform to Table 643-1, Short-Term Markings In Safe Passing  Areas.   This  applies  to both white lane lines for traffic moving in the same direction and yellow center lines for two or three lane two-way roadways when it is safe to pass.

Only temporary raised pavement markers conforming to Subsection 712-2.16 shall be used for short-term markings on seal coat and surface treatment pavements.  The markers shall be installed prior to the application of the asphalt surface material and cover coat and in accordance with Table 643-2.

On multicourse surface treatments the temporary raised pavement markers shall be installed following the full width application of the first layer of cover coat.  The markers shall be installed on each day's completed surface before the pilot car operations are removed and unescorted traffic is allowed on the surface treatment.

If the temporary raised pavement markers cannot be adequately secured to the first course of the cover coat material with the marker's flexible bituminous adhesive, the Contractor shall secure them to the surface with two nails and washers, of the appropriate length and area, so the nails do not pull through the foot of the marker.

After application of the asphalt and cover coat material, the vinyl protective cover shall be removed to expose the retroreflective surfaces of the marker.  Temporary markers shall be installed so that the foot of the marker unit is facing the direction of the approaching distributor.

Final pavement markings shall not be placed until the seal coat or surface treatment has been opened to traffic for at least 14 days.  Final pavement markings shall be applied within 10 days of the completion of the final sweeping or brooming of the mainline seal coat or surface treatment.  Seal coat and surface treatment pavements are exempt from the two week requirement stated in short-term operations.

SHORT-TERM MARKINGS

TABLE 643-1

_______________________________________________________

|               |    LENGTH OF      |      SKIP         |

|  MARKING      |    MARKINGS       |     SPACING       |

|  MATERIAL     | NORMAL  | SEVERE* | NORMAL  | SEVERE* |

|               |CURVATURE|CURVATURE|CURVATURE|CURVATURE|

|               |         |         |         |         |

|  REMOVABLE    |         |         |         |         |

|  PREFORMED    |  4 feet |  2 feet | 36 feet | 18 feet |

|MARKING TAPE   |         |         |         |         |

|               |         |         |                   |

|               |         |         |         |         |

|  TEMPORARY    | 2 units | 2 units |         |         |

|RAISED PAVEMENT|         |         |         |         |

|    MARKERS    | 3 feet  | 2 feet  | 34 feet | 18 feet |

|               |on center|on center|         |_________|

*Severe Curvature:  When the degree of curvature is 5 or greater or when it is necessary for motorists to reduce their speed at least 15 miles per hour below the 85th percentile speed.

TABLE 643-2

_______________________________________________________

|               |    LENGTH OF      |      SKIP         |

|   MARKING     |    MARKINGS       |     SPACING       |

|   MATERIAL    |  NORMAL | SEVERE* |  NORMAL | SEVERE* |

|               |CURVATURE|CURVATURE|CURVATURE|CURVATURE|

|               |         |         |         |         |

|   REMOVABLE   |         |         |         |         |

|   PREFORMED   | 2 feet  | 1 foot  | 38 feet | 19 feet |

| MARKING TAPE  |         |         |         |         |

|               |         |         |         |         |

|               |         |         |         |         |

|   TEMPORARY   | 1 unit  | 1 unit  |         |         |

|RAISED PAVEMENT|         |         |         |         |

|    MARKERS    | 40 feet | 20 feet | ------  | ------  |

|               |on center|on center|         |_________|

* Severe Curvature:  When the degree of curvature is 5 or greater or when it is necessary for motorists to reduce their speed at least 15 miles per hour below the 85th percentile speed.

b.	No-passing zones.  No passing zones, as detailed in Section 3B-3 to 3B-5 of the Alaska Traffic Manual, shall be identified with R4-1, (DO NOT PASS) and R4-2, (PASS WITH CARE) signs and short-term temporary pavement markings.  The signs shall be supplemented with two 18 inch by 18 inch, minimum size, fluorescent red-orange flags mounted above the signs.  The signs shall be mounted so that the bottom of the sign is at least 5 feet above the adjacent roadway.

(1)	Sections of roadway with an Average Daily Traffic (ADT) of less than 2000 vehicles per day, seal coats, and surface treatment pavements shall be marked with temporary pavement markings conforming to Table 643-2.

(2)	Sections of roadway with an ADT of 2000 vehicles per day or greater, shall have broken centerline markings conforming to Table 643-1 and no-passing markings consisting of a continuous 4-inch strip of removable preformed marking tape or temporary raised pavement markers placed on 5-foot centers and the broken center line markings are not required.

c.	Other Markings.  It will not be necessary to install arrows, legend, stop lines, crosswalks, or right edge line markings.  Railroad crossing markings should be considered for areas that have sight restrictions or high accident experience.  Left edge lines will not be required unless they will be the only markings on the paved surface, such as ramps.  All other types of markings are required.  These include channelizing lines and gore area outlines.

The Contractor shall maintain all Temporary Pavement Markings for their intended life without additional compensation for any reapplication that may be required.  There will be no additional compensation to upgrade short-term Temporary Pavement Markings to long term Temporary Pavement Markings when the final pavement markings cannot be placed within the two week time period.

Only temporary raised pavement markers or removable preformed retroreflective marking tape shall be used as Temporary Pavement Markings on the final pavement surface.  They shall be completely removed and disposed of in conjunction with the placement of the final markings.  Final pavement markings shall be in place before work is suspended for the winter.

Temporary Pavement Markings may not be required for construction activities that will be completed within one continuous work shift if the roadway is adequately delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.  The Engineer shall determine the need for the Temporary Pavement Markings for these conditions.

(5/7/91)

643-3.07  Maintenance of Traffic During Suspension of Work.  Add the following to the first paragraph:  Prior to winter shutdown, roadways under construction shall be completed to final lift pavement with permanent pavement markings and signing in place.  All work on the Glenn Highway from Sta. 1661+75 to Sta. 1791+00 shall be completed prior to the 1992 winter shutdown.

643-3.08  Construction Sequencing.  Delete this subsection in its entirety, and substitute the following:  A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes, stops traffic, or causes the 85th percentile speed to fall more than 10 mph below the posted speed limit.  An approved Traffic Control Plan is required before any restriction to traffic is implemented.  No restrictions to traffic will be allowed during the following times:

1	Monday through Friday from 6:00 AM to 7:00 AM, from B.O.P. to Fishhook Willow Road.

2.	Monday through Friday from 5:00 PM to 7:00 PM, from B.O.P. to Fishhook Willow Road.

3.	Around any holiday as described below:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above  stipulations apply from 3:00 PM on the Friday before the holiday to 3:00 AM on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 3:00 PM on the Tuesday before the holiday to 3:00 AM on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 3:00 PM on the day before the holiday to 3:00 AM on the Monday after the holiday.

5.	During the Alaska State Fair, after 5:00 PM, from B.O.P. to Outer Springer Loop at Sta. 1587+94.

The Glenn Highway shall have one lane open to through traffic between approximate Sta. 1699+00 to Sta. 1752+00 between the hours of 7:00 AM and 7:00 PM.

Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 5 calendar days after removal.  When no construction activity is taking place on a guardrail segment which is partially constructed it shall be protected with Type II barricades spaced on 50 foot centers.  Breakaway cable terminals and controlled release terminals partially constructed shall be protected with a minimum of 5 Type II barricades each.

At the Moose Creek Bridge, guardrail located within 50 feet of the bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

A portable concrete barrier will be required if an excavation or fill area, as described in Subsection 643-3.04(1), exists within 16 feet from the edge of a traveled way for gravel roadways, and 26 feet from the edge of a traveled way for paved roadways.

643-4.01  Method of Measurement.  Delete the second sentence of the first paragraph under Item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this contract.  Permanent Construction Signing will not be measured for payment, but will include all permanent construction signs, as detailed on the plans, that are installed, accepted and maintained during the life of this contract.

Delete the last sentence of the first paragraph under Item 3. and replace with the following:  The quantities to be paid for shall be the number of hours or days that the setups are installed, accepted and maintained in place during the life of this contract.

Delete Item 6. in its entirety and substitute the following:

6.	Temporary Pavement Markings will be measured by the single stripe station.  A single stripe is a marking or a temporary raised pavement marker four inches in width.  Wider striping will be measured as multiples of four inches.  Centerline gaps will not be deducted from measurements.  Installation of any word and symbol markings as well as the removal of the Temporary Pavement Markings will not be measured separately but will be subsidiary to this item.  The No-Passing Zone signing, as described in Subsection 643-3.04, 4., b., will not be measured separately but will be subsidiary to this item.

Delete paragraph 7., Seasonal Pavement Markings in its entirety.

643-5.01  Basis of Payment.  In the second paragraph, delete Item 1., Seasonal Pavement Markings .

In the fourth paragraph, delete Pay Item No 643(14), Seasonal Pavement Markings.

Change the pay unit for item 643(11), Portable Concrete Barrier, from "Each" to "Linear Foot".

Add the following:  Barrier reflectors will not be paid for directly, but will be subsidiary to Pay Item 643(11), Portable Concrete Barrier.

Add the following pay item:

Pay Item No.             Pay Item                Pay Unit

643(24)     Permanent Construction Signing    Lump Sum

SECTION 644

SERVICES TO BE FURNISHED

BY THE CONTRACTOR

Special Provisions

644-2.01  Field Office.  Delete this subsection in its entirety and substitute the following:  The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks prior to commencing work through 30 days after the Engineer issues a letter of project completion.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 150 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles.

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within five miles of the project.

644-2.02  Field Laboratory.  Delete the sixth sentence of the first paragraph and substitute the following:  The water supply shall consist of a 500-gallon capacity tank with a pressure pump or a commercial pressurized system.

Modify the second paragraph to include the following:  The lab slab shall be 8 x 10-feet, and installed within an enclosed structure with an exhaust fan.

Add the following:  The Contractor shall supply electricity with an adequate supply of 110-volt, 60-cycle current, 100-lb. propane bottle, and a 500-gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location as designated by the Engineer.

Electricity, propane and water supplied for the State provided portable asphalt lab will not be measured for payment, but will be subsidiary to Item 644(2), Field Laboratory.

(9/1/89)

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  Description.  This Training Special Provision is in implementation of 23 U.S. Code 140(a).

As part of the Contractor's equal employment opportunity affirmative action program, the Contractor shall provide on-the-job training aimed at developing full journeymen in the type of trade or job classification involved.  The number of trainees to be trained under this contract is four.

645-2.01  Objective.  Training and upgrading of minorities and women toward journeyman status is a primary objective of this program.  Accordingly, the Contractor shall make every effort to enroll minority trainees and women to the extent that such persons are available within a reasonable area of recruitment and will be responsible for documenting such efforts in order to demonstrate compliance with this Training Special Provision.  This training commitment is not intended, and shall not be used, to discriminate against any applicant for training, whether a member of a minority group or not.

645-3.01  General.  The Contractor shall determine the distribution of the required number of trainees among the various work classifications based on his needs and the availability of journeymen within a reasonable area of recruitment.

It is the intention of these provisions that training is to be provided in the construction crafts rather than clerk-typists or secretarial-type positions.  Training is permissible in lower level management positions such as office engineers, estimators, timekeepers, etc., where the training is oriented toward construction applications.  Training in the laborer classification may be permitted provided that significant and meaningful training is provided and approved.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Reimbursement for offsite training indicated above may only be made to the Contractor where he does one or more of the following and the trainees are concurrently employed on a Federal-aid project; contributes to the cost of the training, provides the instruction to the trainee or pays the trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit his training proposal for approval, indicating the number of trainees to be trained in each selected classification and the training program to be used.  Furthermore, the Contractor shall specify the starting time for training in each of the classifications.  To this end, completed certification forms, appropriate to the classifications selected, shall be submitted for each trainee.

1.	Trainees in apprenticeship programs currently approved by the U.S. Department of Labor shall be entered on Form 25A311 "Contractor's FHWA Apprenticeship Certification."

2.	Trainees not in approved apprenticeship programs, including laborers and teamsters, shall be entered on Form 25A310 "Contractor's FHWA OJT Certification."  These trainees shall receive at least 500 hours training on the project.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor and approved by the Department.  The Department shall approve any program which will reasonably qualify the trainee for journeyman status in his classification by the end of the overall training program, and which conforms to the Contractor's equal employment obligations.  Existing approved programs shall be  considered  acceptable  except  in  those cases

where the Department has determined that the program is not being administered in a manner consistent with the equal employment obligations stipulated in Federal-Aid provisions.

It is normally expected that a trainee will begin his training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist in his work classification or until he has completed his training program.  It is not required that all trainees be on board for the entire length of the contract.  A Contractor will have fulfilled his responsibilities under this Training Special Provision if he has provided acceptable training to the number of trainees specified.

If, in the judgement of the Contractor, a trainee becomes proficient enough to qualify as a journeyman before the end of the prescribed training period, and the Contractor so employs such trainee, the individual training program will be considered completed.

The Contractor shall furnish each trainee a copy of the program he will follow during training on the project, and with a certification showing the type and length of training satisfactorily completed.  No employee shall be employed as a trainee in any classification in which he has successfully completed a training course leading to journeyman status, or in which he has been employed as a journeyman.

The Contractor shall advise all employees and applicants for employment of available training programs and entrance requirements for each.

The Contractor shall periodically review the training and promotion potential of minority group and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each trainee.

645-3.02  Wages.  Trainees will be paid at least 60 percent of the appropriate minimum journeyman's rate specified in the contract for the first half of the training period, 75 percent for the third quarter of the training period, and 90 percent for the last quarter of the training period, unless apprentices or trainees in an approved existing program are enrolled as trainees on this project.  In that case, the appropriate rates approved by the U.S. Departments of Labor or Transportation in connection with the existing program shall apply to all trainees being trained for the same classification who are covered by this Training Special Provision.

645-3.03  Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the trainees are to be trained by the subcontractor.  Any such subcontracts shall include the appropriate training provisions and pay item.  However, primary responsibility for meeting the training requirements imposed remains with the Contractor.

645-4.01  Method of Measurement.  The Contractor will be credited for each approved trainee employed by him on the project and reimbursed on the basis of man-hours worked, as listed in the certified payrolls.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  Basis of Payment.  Payment will be made at the contract unit price for each accepted man-hour of training performed.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment may be made for training persons in excess of the number specified herein, when approved by the Engineer.

Payment will be made following completion of each approved training program for the project.  No payment will be made to the Contractor if he fails to provide the required training or fails to hire the trainee as a journeyman upon completion of the program, and if such actions indicate a lack of good faith in meeting these requirements.

Payment will be made under:

Pay Item No.          Pay Item          Pay Unit

645(1)          Training Program      Man-Hour

(8/1/88)

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.01  Description.  Add the following:  Item 660(22), Optically Activated Preemptive Traffic Control System, shall consist of furnishing and installing the 3M Opticom Priority Control System for the Glenn Highway and Arctic Avenue Traffic Signal System.  The Contractor shall furnish and install two optical detectors, their lead in cables, a detector coupling unit, a phase selector, and its harness assembly as detailed on the Plans.  The Contractor shall also furnish and deliver to the Matanuska Susitna Borough School District seven (7) low priority optical emitter assemblies complete with installation and maintenance manuals.

660-1.02  Regulations and Code.  Add the following:  Underground conduit fill and bending shall conform to the National Electric Code.

660-1.05  Maintaining Existing and Temporary Electrical and Signal Systems.  Delete this subsection in its entirety and add the following:  The Contractor shall provide all work required to maintain the existing and temporary:  traffic signal, highway lighting, flashing beacon, and sign illumination systems.  They shall be kept in effective operation during the progress of the work, except when shutdown is permitted to allow for alterations or final removal of the systems.  Systems shall be considered in effective operation when there are no damaged, inoperative, or malfunctioning components, and they operate as designed.  The State will pay for all electricity required for the operation of the systems, if they are in effective operation and the public benefits from their operation.  Replacement equipment shall be compatible with existing equipment used in the Region.

During the various phases of construction, the Contractor shall shift the signal heads as required so they are aligned both horizontally and vertically with the approaches in accordance with the following:

1.	For a signal mounted overhead, the height above the travelled way to the bottom of the signal shall be at least 17.5 to no more than 19.0-feet.

2.	For a side mounted signal, the height above the travelled way to the bottom of the signal shall be at least 9 to no more than 11-feet.

3.	An overhead signal controlling a single lane shall be in line with the center of the lane.

4.	The overhead signal controlling two lanes and each of the two overhead signals controlling three lanes shall be in line with the stripe separating the lanes.

5.	If, when the travelled way is moved, the side mounted far right signal head is located such that the horizontal angle to it from the center of the farthest left through lane at the stop bar exceeds 20 degrees, then it shall be moved to an overhead location.  If there are two or three through lanes, then all overhead signal heads shall be realigned so that one is centered over each lane.  If there is one through lane, then the former side mounted signal head shall be located 8 feet to the right of the existing overhead signal.

6.	For a pedestrian signal, the height above the travelled way to the bottom of the signal shall be at least 7 to no more than 9 feet.

7.	All signal heads shall be aimed so they conform with Subsection 660-4.01, Installation Details.

Signal system shutdowns shall be limited to periods during normal working hours as specified in Section 643, Traffic Maintenance, during which flag control shall be used.  Lighting system shutdowns shall not interfere with the regular lighting schedule.  Local traffic enforcement and maintenance agencies shall be notified prior to any shutdown of a traffic signal system.

When the Contractor begins work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include repair or any damage prior to the date of the transfer of maintenance responsibility.  Therefore, before commencing work on the project, the Contractor should inventory the condition of the existing equipment and present written documentation of all damaged, inoperative, and malfunctioning electrical equipment.  This equipment shall be inspected jointly by the Engineer and the Contractor.  If the Contractor begins work before he provides the Engineer with an inventory, he waives the right to claim extra compensation when any component is later found to be damaged, inoperative, or malfunctioning.

At the Preconstruction Conference  the Contractor shall furnish the Engineer with the name and phone number of the person responsible for maintaining existing and temporary electrical facilities.  This person shall be available at all times until the date of Acceptance for Traffic and Maintenance and have access to all labor, materials, and equipment required to complete any repair.

Repair work on traffic signals shall begin within one hour of notification.  If repairs are not completed as required, then the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due the Contractor.  The Contractor shall maintain a hand printed record of all work performed on the signal system in the diary found in each controller cabinet.  Each entry shall include the following:

1.	The date(s) and time(s) the changes or maintenance operations began and were completed, and the names of the crew members completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the changes or performing maintenance.

The Contractor shall ascertain the location of existing conduit runs, buried cables, junction boxes, and all underground utilities before using equipment that may damage such facilities or interfere with any system.

Where roadways are to remain open to traffic and existing lighting systems are to be modified, the Contractor shall energize the modified circuit by sunset on the same day he retires the original circuit.

Where an existing system is being modified, work not shown on the plans or specified in the Special Provisions which the Engineer determines is necessary to keep all or any part of the existing system in effective operation will be paid for as extra work as provided in Subsection 109-1.05, Compensation for Extra Work.

When no longer required, the Contractor shall salvage all original and Department provided equipment in accordance with the plans and Subsection 660-6.07, Salvaging Electric Equipment, and remove all other materials used in the temporary systems from the project.

660-1.05(A)  Temporary Signal Systems.  Add the following subsection;  The Contractor shall provide temporary signalization at the intersections of Arctic Avenue at Glenn Highway, and Palmer-Wasilla Highway at Glenn Highway.  At no time shall the intersections operate in an unsignalized mode, except for shutdown due to change over from the existing system to a temporary system, and from the temporary system to a permanent system.

A plan for each temporary signal system shall be submitted to and approved by the Engineer prior to implementation.  The temporary signal plan shall equal or exceed the system being replaced or modified.  That is, the plan shall not downgrade the number of signal heads, signal phases, pedestrian push-button, etc.  The temporary signal system plan shall also include the layout of the temporary intersection.  The complete plan shall include intersection geometrics, lane widths and auxiliary lane pocket lengths.

The Contractor shall furnish and install all materials and miscellaneous hardware required to provide a functional traffic signal system.  All materials shall conform to the requirements of the plans and specifications.  Temporary equipment shall be compatible with existing equipment used in the Central Region.  Load centers shall be provided as required in Subsection 660-1.05(B), Temporary Illumination Systems.

The temporary signal system may consist of:  the existing systems, relocations of the component parts, guyed wood poles, or any portion of the permanent signal system.  Traffic signals may be suspended from messenger cables provided they are mounted by standard span wire hangers and secured with a second cable to prevent misalignment in a wind.  All signal faces shall be equipped with backplates and visors.  The signal faces of each phase with two or more faces shall be energized using two circuits, with each circuit wired with an IMSA 20-1 signal cable; splices shall be made only at the terminal blocks in the signal faces.  Sufficient signal cable slack shall be left at each pole to provide for drip loops and to allow realignment of each signal head.  Temporary controller assemblies may be mounted on Type III junction boxes while work is completed on the permanent systems.

Whenever a pole of the permanent signal system is included in a span wire signal system, the Contractor shall guy the pole and provide protective collars to prevent chafe damage.  Poles with breakaway bases shall not be included in a span wire supported signal system.

Unless otherwise specified, no vehicle detection will be required in the temporary systems during the construction season after the existing loops are removed during normal construction.  At that time, the controller will revert to the pre-timed mode.  However, prior to the Department's acceptance of the signalized intersections for winter maintenance, vehicle detection shall be installed and working to the same extent as it was in the original and temporary signal systems prior to their removal.

660-1.05(B)  Temporary Illumination Systems.  Add the following subsection:  The Contractor shall provide illumination at all locations with preexisting lighting, and at all intersections where temporary traffic signalization is specified to be provided.  This work shall be provided during the life of the contract on all roadways open to traffic within the project limits.  The temporary lighting systems shall be operational by sunset on the same day the replaced system is retired, or the roadway is opened to traffic.

A plan for each temporary lighting system shall be submitted to and approved by the Engineer prior to implementation.  The temporary lighting plan shall equal or exceed the system(s) being replaced or modified, and at intersections, consist of a luminaire located on the far right for each through street approach and installed adjacent to the through street radius returns.  The through street is the street with the vehicular right-of-way; both streets shall be considered through at signalized intersections and four-way stops.

The Contractor shall furnish and install all materials and miscellaneous hardware required to provide a functional lighting system, including electrical load centers.  All materials shall conform to the requirements of the plans and specifications, except that the branch conductors may be triplex aluminum with messenger cable if they are installed overhead.  Illumination conductors shall be sized so the voltage at the most remote luminaire is not less than the minimum required for the ballast, as recommended by the manufacturer.  The Contractor shall install intermediate conductor and supports to energize luminaires at locations without electrical service.  Luminaires used in the system may be the existing fixtures or new fixtures with a light distribution compatible with the proposed lighting configuration.

The temporary lighting systems may consist of any of the following lighting pole types, or combinations thereof, provided the luminaires have a minimum 30 feet mounting height.  Mounting height is the difference in elevation between the luminaire refractor and the edge of travelled way at the same station.  The existing poles may be reused if they are not utility owned.  Any pole of the permanent lighting and temporary signal systems, and any Contractor supplied poles may be used in the temporary lighting system(s).  Contractor supplied poles may be wood, and shall meet AASHTO design criteria for 80 miles per hour wind.  All poles, except traffic signal poles, installed within the clear zone shall be provided with FHWA approved: slip bases, transformer bases, or frangible couplings.

The load centers to power the temporary lighting and signal systems may be the permanent installations, the existing installations, or temporary installations.  The existing load centers may be used only if they are scheduled to remain intact until completion of the project, and reused only if they are approved.  The Contractor shall provide approved temporary load centers with photoelectrically controlled lighting circuits, whenever no load center is available for use or when an existing load center that is not approved is retired due to conflict with the work.  An approved load center is any load center UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "suitable for use as service equipment".  The Contractor shall provide all work to modify these load centers as required to provide functional temporary lighting and signal systems and to install them, completing all work in accordance with the NEC.

660-2.03  Foundations.  Delete the first sentence of the last paragraph and substitute the following:  All existing foundations for poles that are removed or relocated shall be removed entirely unless otherwise directed by the Engineer to avoid damaging utilities or surface features.  Any damage to utilities or surface features caused by the Contractor shall be replaced or repaired at his expense.

Delete the tenth paragraph.

660-2.04  Poles, Steel Pedestals and Posts.  Add the following:  All poles and mast arms shall be designed for 100 MPH wind speeds with gusts and mastarms to 130 MPH.

The Contractor shall relocate existing standards per the plans in a manner that maintains the existing condition.  The Contractor will be required to replace, at his expense, standards which are damaged or destroyed by his operations.  Relocated galvanized standards with rusted or scarred surface areas shall be repaired and re-coated in accordance with Subsection 660-2.14, Galvanizing.  Repair and re-coating of rusted or scarred surface areas less than or equal to 10 percent of each standard's total surface area shall be subsidiary to other work of Section 660 and not measured or paid for directly.

660-2.05  Conduit.  Add the following:  Trenching to install conduits across roadways with an existing paved surface will be allowed.

660-2.08.  Add the following to subsection 3.  The optical detector lead in cable shall be a 3 conductor number 20 AWG cable and be the 3M Opticom brand Model 138 detector cable.

Standard Modifications

660-2.09(A)  Wiring.  In the seventh paragraph,  insert "and feeder" between "signal" and "conductors".

(5/7/91)

Special Provisions

660-2.10  Bonding and Grounding.  Add the following after the first paragraph:  All hardware, including insulated throat grounding bushings, ground rods, and ground rod clamps shall be UL listed.

660-3.04  Special Auxiliary Equipment.  Add the following:

7.	The following equipment that comprise the Opticom Priority Control System shall conform to the Opticom Model Number indicated.  The low priority emitter assemblies shall be provided with 3M Opticom brand visible light filters.

Optical detectors				205

Quad detector coupling unit		161

Phase selector					168J

Phase selector harness assembly	168J-4

Low priority emitter assemblies	195

Visible light filters			199

The phase selector and coupling units shall be installed in the controller cabinet.

Standard Modifications

660-4.01  Installation Details.  In numbered paragraphs 7 and 9, under "Loops", change "660-2.08" to read "660-2.09(A), Wiring".  (5/7/91)

660-5.02  Backplates.  In the last paragraph, change "660-2.16" to read "660-2.15, Painting".  (5/7/91)

Special Provisions

660-6.01  Luminaires.  Add the following paragraph:  No paint may be applied to the reflecting surface of luminaire reflectors.

Luminaires to be used shall provide the specified uniformities or better in the configurations listed in the table below.  Uniformity is defined as the average maintained illumination level divided by the maintained illumination at the dimmest point.  Uniformity shall be calculated using the manufacturer's current published photometric charts.  Uncorrected illumination values shall be derived by straight line interpolation between lines of the isofootcandle curves.  Computations shall be done assuming luminaires are located on one side of the roadway only.

Lum   Road   Mtg  Spacing  Lum  Uniformity  Initial

Type  Width  Ht           Offset            Foot-

Candles

MC-3    40'   40'    220'     0      2.7:1    1.2

Offset  36'   50'    200'   -30'     3.0:1    1.4

Luminaire Type Definitions:

MC-3	Mastarm Mounted Medium Cutoff, Type 3 as defined by the Illuminating Engineering Society (I.E.S.).

Offset:	Pole top mounted luminaires designed to be offset between 20 and 50 feet from the edge of traveled way and angled between 30 and 50 degrees from the horizontal.

660-6.07  Salvaging Electrical Equipment.  Add the following to the first paragraph:  Controller assemblies shall be salvaged and delivered to the State Maintenance Yard at 5820 East Tudor Road in Anchorage.  All other salvaged equipment shall be delivered to the State Maintenance Yard at 289 Inner Springer Loop in Palmer.

Delete the fourth paragraph and substitute the following: The following existing items not being reused shall become the property of the Contractor and be disposed of as indicated.  Items that are to be removed shall be removed from the highway right of way.

1.	Junction boxes (not including lids), conductors, and post and controller assembly foundations shall be removed.

2.	Conduits and vehicle detectors may be abandoned in place provided any section of metallic conduit located within two radial feet of any new conduit is removed.

3.	Traffic signal pole and electroller foundations may be abandoned in place provided the tops of the foundations, reinforcing steel, anchor bolts, and conduits are removed to a depth of not less than one foot below roadway subgrade, sidewalk, or unimproved ground, whichever applies.

660-7.01  Basis of Payment.  In the first paragraph, modify line eleven to read: "...involved in furnishing and installing, modifying, maintaining and ...".

Add the following pay items:

Pay Item No.             Pay Item               Pay Unit

660(22)      Optically Activated Preemptive   Lump Sum

Traffic Control System

SECTION 661

ELECTRICAL LOAD CENTERS

Special Provisions

661-1.02  Equipment List(s) and Drawings.  Add the following subsection:  The Contractor shall submit for review and approval, within 30 days following award of the contract, 8 collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s) and the following:

1.	For materials on the Approved Products List:  a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

2.	For materials not on the Approved Products List:  catalog cuts that include the manufacturer's name, type of product, size, model number, conformance specifications, and supplemented by other data as may be required, including manufacturer's maintenance and operations manuals, or sample articles.

The Department will not be liable for any material purchased, labor performed, equipment used, or delay to the work before all equipment and materials have been reviewed and approved.

661-2.01  Materials.  Add the following:  Type 1 load center cabinets shall be constructed similar to the section and elevations shown in the plans, and conform to the following requirements.  Slight variation in the dimensions is allowable, except in the anchor bolt template.

1.	The cabinet shall be constructed of zinc-coated A60 finish sheet steel per ASTM A525 with no external screws, bolts, or nuts.  The components shall have the following minimum thickness as measured by the United States Standard Gauge:  the exterior shell No. 12 gauge, the interior doors and panels No. 14 gauge, and the interior covers No. 16 gauge.

2.	The components shall be painted with a 2-part urethane paint undercoating inside and out.  The final finish shall be a 2-part urethane paint, standard white for removable panels and non-gloss silver-gray, closely matching Color No. 36622 of Federal Standard Specification No. 5950 for the enclosure.

3.	The service entrance section shall be isolated from the main load section and distribution load section by non-removable metal barriers, and shall be equipped with landing lugs for termination of service conductors.

4.	The cabinet shall be provided with internal mounting brackets sized for 1/2-inch anchor bolts for use with a standard mounting base assembly.

5.	All doors shall be equipped with continuous stainless steel pin hinges, coin latches and hasp for padlock.  The meter section door shall have a clear polycarbonate resin window, 0.187" minimum thickness, with a minimum size of 10.0-inch x 10.0-inch, which shall be sealed with silicone.

6.	Each completed load center assembly shall be provided with an exterior name plate, safety labels, interior identification labels, wiring diagram, and installation instructions.

7.	When two type 1 load centers are to be installed adjacent to one another, furnish one cabinet with the load distribution section located on the left side.

When required, type 2 and 3 load center cabinets shall be sized and wired to serve the combination of highway lighting, traffic signal and thaw wire circuits shown in the plans.  Each cabinet shall be a single box, subdivided to form compartments as required, and constructed of formed and welded, code gauge steel, finished with gray baked enamel, electro-deposited on cleaned phosphatized steel and suitable for surface mounting.  A hinged lockable door with hasp shall be installed over each compartment.

The wiring configuration for each load center type shall be in accordance with the wiring diagram indicated on the load center detail sheet.  Circuit breaker ratings shall be as shown in the load center summary for each location.  Dead panels shall be indelibly labeled with the circuit number and the direction of the circuit run from the load center.

When the load centers are ready to be energized, the Contractor shall request and coordinate an electrical inspection of the load centers from the local authority having jurisdiction, allowing at least 5 working days before the inspection is needed.  The Contractor shall be present during the inspection to assist in accessing the cabinets and to answer questions.  The Contractor shall correct the deficiencies noted in each load center.

Payment of any fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be considered incidental to the Section 661 items.  (9/1/89)

Add the following Section:

SECTION 663

ADVANCE WARNING SIGN AND FLASHER ASSEMBLY

Special Provisions

663-1.01  Description.  Work under this section consists of furnishing all labor, materials, and equipment required to install and make operational an active advance warning flasher assembly at the location shown on the plans.  The assembly includes the following items:

1.	A double cantilever arm sign support and foundation.  See the plans and Standard Drawing S-41 for details of these structures.

2.	An internally illuminated sign capable of flash operation with the legend "PREPARE TO STOP" (referred to hereafter as THE SIGN).

3.	Mounting brackets and all required hardware for attaching THE SIGN to the sign support.  See the double beam sign mounting details on Standard Drawing S-21 for details of this hardware.

4.	Two single section 12-inch amber signal heads mounted with mast arm type plumbizers on 2-inch pipe tenons, and provided with backplates and visors.

5.	A 36-inch by 36-inch W3-3 sign with symbolized signal ahead legend.

6.	A photoelectric control mounted on top of the sign support.

7.	All required conduit, conductors, and junction boxes.

8.	All incidentals required to furnish a functional assembly.

The display of THE SIGN and two signal heads shall be energized by a two circuit flasher located in the controller cabinet.  THE SIGN and the inboard signal head shall be wired to one circuit, and the outboard signal head shall be wired to the other.  They shall begin wigwagging 5.7 seconds before the end of the southbound Glenn Highway green vehicular interval, and shall continue flashing until the beginning of the same interval.  The signal heads and THE SIGN shall be off during all other times.

663-2.01  Materials.  Materials shall conform to this section and the applicable subsections of Section 660.

THE SIGN shall be either of the following or an approved equal:

1.	An ELECTRO-DELTA model "ES-48".

2.	A NU-ART model "Extinguishable Message Sign".

It shall be illuminated by two 8-feet long very high output fluorescent lamps, and the legend "PREPARE TO STOP" shall consist of two lines of 10-inch series E capital lettering.

Operation of the assembly shall be achieved by means of four conductors from the controller cabinet.  Two conductors shall provide 120 volt power (AC+ and AC-) to THE SIGN which energize the photoelectric control, and filament transformers.  The other two conductors shall provide the AC+ pulses from the two circuit flasher, one of which energizes a 0.5 KVA 120/480 volt boosting transformer (which in turn energizes the ballasts) and one of the signal heads.

The photoelectric control shall be connected to relay controlled dimming devices, which reduce the intensity of the assembly's nighttime light output.  The dimming circuitry shall be located in THE SIGN.  THE SIGN's nighttime message shall be approximately 1/35 of its daytime intensity.

The entire flash interval of THE SIGN shall be full intensity, and shall not flicker during both day and night time operation down to a temperature of minus 40 degrees fahrenheit.

The sign structure shall be designed and fabricated to withstand an AASHTO 100 MPH wind speed with a 1.3 gust factor.  In addition, the centerline of the pole shall not deflect more than three inches from vertical at the top of the pole when loaded as shown on the plans.

663-3.01  Construction Requirements.  All work shall conform to the applicable subsections of Section 660.

The pole shall be installed so the legend of THE SIGN is level to drivers approaching it.

663-3.02  Field Tests.  The active advance warning flasher system shall be tested in accordance with subsection 660-2.13, Field Tests.  The functional test shall consist of not less than 5 days of continuous satisfactory operation.

663-4.01  Method of Measurement.  Item 663(1) is a lump sum item, and no measurement of quantities will be made.

663-5.01  Basis of Payment.  The lump sum bid price paid for this item will be full compensation for furnishing all labor, materials, equipment, and incidentals required to install and make operational the Active Advance Warning Flasher assembly.  It also includes full compensation for all necessary excavation and backfill, restoration of improvements damaged during construction, and for completing all required tests.

Payment for furnishing and installing the W3-3 signal ahead sign will be made under Item 615(1), Standard Signs.

Payment for furnishing and installing the controller cabinet will be included under Item 660 (1), Traffic Signal System Complete.

Payment will be made under:

Pay Item No.             Pay Item              Pay Unit

663 (1)     Active Advance Warning Flasher   Lump Sum

at Glenn Hwy/W. Arctic Ave.

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDER STATIONS

Special Provisions

669-1.01  Description.  This work shall consist of furnishing and installing traffic count stations for the automated collection of traffic data on an intermittent or permanent basis.  The Automated Traffic Recorder (ATR) station is a vehicle detection system.

The ATR station can be a combination of detection, electronics and software and is defined as a system.  Four types of systems are defined as follows:

1.	Each Intermittent ATR station will include the following parts:

a.	inductive loops detectors for detecting the presence of vehicles, and

b.	underground conduit, junction boxes, cabinet, and wiring as specified in the plans.

2.	Each Traffic Volume Count System specified herein shall consist of the following parts:

a.	inductive loop detectors for detecting the presence of vehicles,

b.	electronics for collecting and storing data obtained from the sensors,

c.	communications capabilities (e.g. modem and cabling) for transmitting the data to IBM PC compatible computers located both in the Highway Data Office in Anchorage, Alaska, and portable laptop computers carried to the equipment site by State personnel, and

d.	underground conduit, junction boxes, cabinet, modem, electrical and telephone service as specified.

3.	Each Automated Vehicle Classification System (AVC) specified herein shall consist of the following parts:

a.	Inductive loop detectors and piezoelectric sensors for detecting vehicle presence and counting axles and measuring axle spacing,

b.	electronics for collecting, analyzing and temporarily storing the data obtained from the sensors,

c.	communications capabilities (e.g. modem, remotely controllable code operated switch and cabling) for transmitting the data to IBM PC compatible computers located both in the Highway Data Office in Anchorage, Alaska, and portable laptop computers carried to the equipment site by State personnel, and

d.	underground conduit, junction boxes, cabinet, electrical and telephone service as specified.

4.	Each Weigh In Motion (WIM) System specified herein shall consist of the following parts:

a.	Inductive loop detectors and piezoelectric or bending plate sensors for detecting vehicle presence and counting axles and measuring axle spacing and weight,

b.	electronics for collecting, analyzing and temporarily storing the data obtained from the sensors,

c.	communications capabilities (e.g. modem, remotely controllable code operated switch and cabling) for transmitting the data to IBM PC compatible computers located both in the Highway Data Office in Anchorage, Alaska, and portable laptop computers carried to the equipment site by State personnel,

d.	underground conduit, junction boxes, cabinet, electrical and telephone service as specified,

e.	modification to the pavement section at the WIM installation to provide a smooth approach to and adequate mounting foundation for the axle weight sensors, and

f.	a gravel pad for installation of the equipment cabinet and off-street parking for calibration and service vehicles.

The locations of traffic detection, and cabinets, shown on the plans are approximate and the exact locations shall be established in the field by the Engineer.

Concrete pavement work shall consist of furnishing and placing Portland cement concrete for concrete road section at Weigh In Motion (WIM) Installation site in conformance with section 501 or as established on the plans.

General description of the Automated Traffic Recorders are as follows:

Assembly H1 -	A  permanent traffic volume count system and permanent AVC system, with a four inductive loop configuration, two piezoelectric sensors and electrical and telephone service  to be installed by the Contractor.  Traffic volume electronics, automated vehicle classification electronics, telephone modem, remotely controllable code operated switch will be supplied by the department and installed and commissioned by the Contractor.

Assembly H2 -	A two loop configuration, intermittent ATR without electrical, telephone, or electronics.

Assembly H3 -	A two loop configuration, intermittent ATR without electrical, telephone, or electronics.

Assembly H4 -	A two loop configuration, intermittent ATR without electrical, telephone, or electronics.

Assembly H5 -	A two loop configuration, intermittent ATR without electrical, telephone, or electronics.

Assembly H6 -	A two loop configuration, intermittent ATR without electrical, telephone, or electronics.

Assembly H7 -	A two loop configuration, intermittent ATR without electrical, telephone, or electronics.

Assembly H8 -	A two loop configuration, intermittent ATR without electrical, telephone, or electronics.

Assembly H9 -	A permanent traffic volume count system, permanent AVC system and permanent WIM system. Includes a ten inductive loop configuration, two piezoelectric cable axle sensors for vehicle classification, two lanes of bending plate WIM sensors, electrical and telephone service to be installed by the Contractor.  The WIM electronics,  traffic volume electronics, AVC electronics, telephone modem and remotely controllable code operated switch will be supplied by the department, and installed and commissioned by the Contractor.  This assembly will require a 288 foot section of portland cement concrete pavement.

Assembly H10 -	A two loop configuration, intermittent ATR without electrical, telephone, or electronics.

669-1.02  Regulation and Code.  All materials and workmanship shall conform to the standards of the Underwriters Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturers Association, where applicable.

669-2.01 Materials.  All materials provided for the work shall be new, unless otherwise stated, and shall meet the following requirements:

1.	WIRING.  All wiring shall be in accordance with Subsection 660-2.09(A), Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable.

2.	Conduit.  All conduit shall be in accordance with Subsection 660-2.05, Conduit.  Nylon pull cords shall be left in all two inch conduit.

3.	Junction Boxes.  All junction boxes shall be in accordance with Subsection 660-2.06, Junction Boxes.  Junction boxes used for ATR installations shall not contain any conduit with 440 voltage.

4.	Terminal Blocks.  All terminal blocks shall be provided with nickel, silver or cadmium plated brass binder head screw terminals.  All terminal block which are installed in junction boxes shall be waterproof and resistant to corrosion.  Terminal blocks shall be a barrier type, 600vac @ 20 amps, capacity for 12-18 AWG wire with removable shorting bars in each positions and with integral type marking strips.  All conductors shall be terminated to a terminal block.

5.	Inductive Loops.  All inductive loops shall be in accordance with Subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be UL listed as Type RHW/USE/XLP 12AWG 600V rating.

Loop lead-in cable homerun shall consist of a twisted pair 18AWG stranded tinned copper wire with polyethylene insulation, covered with an aluminum foil shield, stranded copper drain wire, and PE outer jacket conforming to IMSA specification 50-2.

Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, and aluminum shield and overall PVC or PE jacket.

6.	Cabinets.  All style 3 cabinets shall be in accordance with Subsection 660-3.05, Controller Cabinets. All cabinets shall be aluminum and include a thermostatically controlled heater and exhaust (cooling) fan, switched light, 3 shelves, Corbin locks, Grount Fault Interrupt (GFI) circuit breakers, dual sets of four 110 volt receptacles mounted per the plans, and terminal blocks mounted on the walls adjacent to the door. All cabinets shall have a NEMA 3R specification.  All style 1 and style 2 cabinets shall be installed as indicated on the plans.

7.	Concrete Pavement.  Materials used for concrete pavement shall conform to section 501-2.01, Materials.

8.	Modems.  All modems shall meet or exceed the following specifications:

a.	300, 1200, or 2400 baud selectable

b.	Automatic Answer Mode

c.	Hayes 2400 compatible

d.	pulse or touch-tone dialing

e.	Full or Half-duplex operation

f.	External switches for COM port 1-4 selection

g.	Compatible with CCITT V.22, Bell 103, and Bell 212A modem specifications.

h.	Meets FCC Part 15, FCC Part 68 regulations for direct connection to telephone lines.

9.	Remotely Controllable Code Operated Switch.  All code operated switches shall meet or exceed the following specifications:

a.	minimum four addressable ports

b. 	Speed: 110 to 19,200 bps, each port individually setable

c.	Flow Control: Hardware X-ON/X-OFF

d.	Data Format: 7 or 8 data bits; odd, even, or no parity

e.	Connectors: DB25s (female); DTE/DCE strap-setable

f.	Power: 115 VAC, 60 Hz, 5 watts

Suggested Model:  GS-SW540A (available from Black Box Corporation) or approved equal.

10.	Traffic Volume Counters.  Permanent traffic volume counters shall be GK brand units available from Capital Enterprise & Engineering Corp., P.O. Box 12688, Salem OR 97309, phone (503) 363-9290.  Permanent traffic volume counters shall include:

a.	GK model 6000 TC

b.	2 each loop cards

c.	Communications card

d.	Rechargeable battery

e.	64KB data module

f.	Battery charger

g.	Connective cable

h.	Modem cable

i.	User manual

11.	Automated Vehicle Classification (AVC) Counters and Sensors.  AVC counters and piezoelectric axle sensors shall be PAT brand C100S available from PAT Equipment Corporation, Inc., 1665 Orchard Drive, Chambersburg, PA 17201, phone (717) 263-7655. AVC counters and sensors shall include:

a.	PAT model C100S

b.	Loop card(s)

c.	Communications card

d.	Loop cable(s)

e.	Power cable

f.	Axle detector cable

g.	Modem cable

h.	User manual

i.	Rechargeable battery

j.	Battery charger

k.	Piezo axle sensor (1 per lane)

l.	Epoxy with hardener for each piezo axle sensor.

12.	Weigh In Motion (WIM) Counters.  WIM electronics and sensors shall be International Road Dynamics (IRD) brand bending plate WIM equipment available from Internation Road Dynamics, 702 43rd Street East, Saskatoon, Saskatchewan S7K 3T9 Canada, phone (306) 934-6777.  WIM electronics and sensors shall include:

a.	IRD Bending plate WIM basic unit, including 386 computer, 110 volt power supply, monitor, keyboard, 3.5" floppy drive, 40Mb hard disk drive, and DOS software

b.	Loop cards

c.	Loop cables

d.	Bending plate cards

e.	Bending plate cables

f.	Dynax axle detector cards

g.	Dynax axle detector cables

h.	Modem cable

i.	User Manuals

j.	IRD WIM software

k.	Bending plate slab scale with frame and installation hardware (2 for each lane)

l.	Epoxy with grout and hardener for each bending plate slab scale

m.	Dynax axle detector (1 per lane)

n.	Epoxy with hardener for each Dynax axle sensor.

13.	Cabinet Load Panel.  See plan drawings for details.  All circuit breakers shall be of the ground fault interrupt (GFI) type, UL listed equipment.

669-3.01 Construction Requirements

1.	Wiring.  All wiring shall be installed in accordance with Subsection 660-2.09(A), Wiring. All unused pairs shall be terminated within splices, at cabinets unused pairs shall be terminated to a terminal block and labeled.

2.	Conduit.  All conduit shall be installed in accordance with Subsection 660-2.05, Conduit or as indicated on the plans.

3.	Junction Boxes.  All junction boxes shall be installed in  accordance with Subsection 660-2.06, Junction Boxes or as indicated on the plans.

4.	Terminal Blocks.  All terminal blocks and wire pairs shall be clearly labeled on the block.  Terminal blocks within cabinets shall be mounted so that all terminals are easily accessible from the front of the cabinet.  By convention, wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block. All conductors shall terminate and be soldered to "spade" type terminal lugs.

5.	Inductive Loops.  All inductive loops shall be installed and constructed in accordance with Subsection 660-4.01, Installation Details, unless otherwise specified on the plans.

All inductive loops shall be wound in the same direction with the starting lead marked "S" per section 660-2.09(A).

All inductive loops shall be formed of four turns of wire, and shall be six feet square with plus-or-minus one inch tolerance.  All inductive loops in a lane shall be located sixteen feet from leading edge to leading edge, with plus-or-minus one inch tolerance.  All inductive loops located in adjacent lanes shall be aligned within plus-or-minus one inch tolerance.

All lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the center line of the road.  Lead-in wires for each loop shall be in separate conduits to the first junction box, and shall be separated by a minimum of 6 inches.

All loops shall be installed immediately prior to final paving of the particular section of road.  There shall be no transverse seams, joints or roughness within 50 feet of any inductive loops.

6.	Cabinets.  All style 3 control cabinets shall be installed according to Subsection 660-4.01, Installation Details.  All style 1 and 2 cabinets shall be install as indicated in the plans.

7.	Concrete Pavement.  Construction of concrete pavement shall be in accordance with Subsection 501-3.01 through 501-3.10.

8.	Piezoelectric Sensors for AVC.  All permanent piezoelectric sensors shall be installed per AVC equipment manufacturer's recommendations.  All coaxial cables shall be run to the equipment cabinet without splices and terminated on the specified terminal block, with at least six feet of slack cable available in the equipment cabinet prior to the terminal block.  Acceptance testing shall be performed by the Contractor to ensure compliance with Section 669-3.02 Acceptance Testing.

9.	Bending Plate Axle Weight Sensors and Electronics for WIM.  All permanent bending plate axle sensors shall be installed per WIM equipment manufacturer's recommendations.  A manufacturer's representative shall be present to supervise installation of the bending plate sensors and to commission the WIM equipment as a complete and fully functioning system.  All cables shall be run to the equipment cabinet with no more than one splice per cable and terminated on the specified terminal block, with at least two feet of slack cable in each junction box and at least six feet of slack cable available in the equipment cabinet prior to the terminal block.  Acceptance testing shall be performed by the Contractor to ensure compliance with Section 669-3.02 Acceptance Testing.

10.	Coordination.  The Contractor shall coordinate with the local telephone and electrical utility for additional installation requirements for telephone and electrical service installations.

669-3.02 Acceptance Testing.  The Contractor shall perform acceptance testing on all ATR installations.

1.	General Tests.  All ATR installations shall have tests conducted in accordance with Subsection 660-4.01, Installation Details.

2.	AVC Acceptance Tests.  In addition to the General Tests, Acceptance Tests shall be performed by the contractor on all automated vehicle classification installations.  Acceptance tests shall be performed to demonstrate that the AVC system performs at or above the required accuracy.

a.	Accuracy Requirements -  The accuracy of Automated Vehicle Classifiers is such that, if good lane discipline is maintained:

*	not more than plus or minus ten percent (+ 10 %) of the total vehicles in FHWA class one through class three (1 thru 3) and

*	not more than plus or minus five percent (+ 5 %) of the total vehicles in FHWA class four through class thirteen (4 thru 13)

are classified in the wrong bin when compared with a concurrent manual classification count.

b.	The AVC Acceptance Test shall consist of an hour-by-hour and summary comparison of a manual classification count with the output of the permanent AVC.  A manual vehicle classification count shall be performed for sixteen consecutive hours (16 hrs) at the AVC site.  During that 16 hour period, a minimum of five (5) vehicles in an individual vehicle type bin is required in order to be included in the final comparison.

c.	The difference between the number of vehicles in each type bin as observed manually and as recorded by the AVC system shall be computed.  If more than the allowed percentages as listed above are classified in the wrong bin when compared with a concurrent manual classification count, the AVC equipment shall be recalibrated and the test performed again until the system meets the required accuracy.

3.	WIM Acceptance Tests.  In addition to the General Tests, Acceptance Tests shall be performed by the contractor on all weigh in motion installations after Calibration of the WIM system has been performed.  Acceptance tests shall be performed to demonstrate that the WIM system performs at or above the required accuracy.

a.	Acceptance Tests shall consist of three vehicles which will make ten passes over the WIM sensors in each lane at speeds varying from 15 to 70 miles per hour.

b.	The three test vehicles shall consist of a five axle, eighteen wheel single trailer vehicle (FHWA Class 9), a three axle, ten wheel single unit vehicle (FHWA Class 6), and a two axle, six wheel single unit vehicle (FHWA Class 5).  All three test vehicles shall be fully loaded with non-shifting material to near legal weight limits.

c.	All tires on all three test vehicles shall be inflated to recommended preassures.

d.	The gross weight of the vehicles and the weight of each axle group shall be determined by weighing on a certified static scale at a scalehouse operated by the State of Alaska Department of Commerce, Division of Weights and Measures.  An axle group is defined as any two axles whose midpoints are within eight feet of each other.  For the test vehicles, the Class 9 single trailer vehicle has three axle groups, while the Class 6 and Class 5 each have two axle groups.

d.	The difference in value or error between the weight of each axle group or vehicle gross weight shall be computed as follows:

d = 100[(W - R) / R]

where

d =	difference between WIM value and reference value

W =	WIM value, or weight as measured by the WIM system

R = Reference value, or weight as measured by a static scale

e.	The Accuracy requirements for the WIM equipment consist of a maximum error of plus or minus twelve percent with a ninty-four percent confidence interval (i.e. + 12% with 94% confidence) for axle group weights, and a maximum error of plus or minus ten percent with a ninty-four percent confidence interval (i.e. + 10% with 94% confidence) for gross vehicle weights.

For each test vehicle, no more than two of the axle group weights measured by the WIM system can differ from the axle group weights as measured at the scalehouse by more than twelve percent.  Similarly, for each test vehicle, no more than two of the gross vehicle weights measured by the WIM system can differ from the gross vehicle weights as measured at the scalehouse by more than ten percent.

f.	Errors, or differences between the weights as measured by the WIM and weights as measured at the scalehouse, shall be calculated on ten consecutive passes of each of the three test vehicles at various speeds.  If more than the maximum number of errors is observed, the equipment shall be recalibrated and the Acceptance test performed again until the system meets the accuracy specifications.

669-3.05  Deliverables.  All deliverables shall be submitted to the Engineer prior to final approval of the work or as otherwise called for herein.

1.	Equipment List(s) and Drawings.  The Contractor shall submit for review and approval within thirty days following award of the contract, three collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s), and a description that includes product name, manufacturer, model or part number.

The Department will not be liable for any materials purchased, labor performed, equipment used or delay to the work before all equipment and materials have been reviewed and approved.

2.	As-Built Plans.  The Contractor shall prepare four complete sets of as-built plans which will be kept current with the construction.  These as-built plans shall detail all  construction changes made to the plans and also include the following information on the appropriate sheets:

a.	the location and depth of all inductive loops and conduit runs, and,

b.	the station and offset of all junction boxes.

Redlines of full size construction plans will be acceptable.

Three sets of as-built plans shall be presented to the Engineer, and one set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation.

3.	Test Results.  Written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Engineer prior to acceptance of the Automated Traffic Recorder Installation.  Tests will be conducted in accordance with Subsection 660-4.01, Installation Details.

Written (computer printout) results and copies of the electronic data files collected during performance of the WIM System acceptance test shall submitted to the Project Engineer prior to acceptance of completion of the WIM system.

669-4.01  Method of Measurement.  The quantity to be paid for will be the actual number of completed and accepted Automated Traffic Recorder installations as shown on the plans or as directed by the Engineer.

The Class A concrete required for concrete pavement will not be measured for payment.

As-Built plans will not be measured for payment.

669-5.01  Basis of Payment.  The contract unit bid price per each Automated Traffic Recorder installation shall be full compensation for furnishing all equipment, labor and materials necessary to complete the work as specified, with the following exceptions:

1.	The cost for installation of electrical load centers shall be paid for under Pay Item 661(2), Load Center, Type 2.

2.	Excavation required for these installations will be paid for under Section 203.

3.	Backfill materials required will be paid for under their respective pay items.

4.	Class A concrete will be paid under Item 501(1), Class A Concrete.

As-built plans and acceptance testing will not be paid for separately, but will be subsidiary to the Automated Traffic Recorder installations.

Payment will be made under:

Pay Item No.           Pay Item                Pay Unit

669(1-__)   Automated Traffic Recorders-__    Lump Sum

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01  Description.  Delete the first sentence and substitute the following:  This work shall consist of furnishing and placing preformed pavement markings.

Standard Modifications

670-3.01  Construction Requirements.  In the last paragraph under Item 2., insert "pneumatic" immediately before "roller".  (5/12/89)

670-3.05 Preliminary Spotting.  Add the following:  Lines and markings to be replaced at their existing locations shall be referenced by the Contractor at his expense, prior to performing any work that may disturb them.

SECTION 702

ASPHALT MATERIALS

Standard Modifications

702-2.04  Storage And Application Temperatures.  In Table 702-1, change storage temperatures for ACs from "340 Max" to "325 Max".  (5/12/89)

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  Fine Aggregate For Concrete.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

703-2.02  Coarse Aggregate For Concrete.  In the first sentence, insert ", class B," after "AASHTO M 80".

703-2.03  Aggregate for Base.  Add the following to the list under the first paragraph:

Plastic Index     AASHTO T-90     6 max.

(5/7/91)

Special Provisions

703-2.03  Aggregate for Base.  Delete Table 703-2, Aggregate for Untreated Base, and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing by Weight

Sieve Designation               Grading D-1

1-1/2 inch                      ---

1 inch                      100

3/4 inch                     70-100

3/8 inch                     50-79

No. 4                       35-58

No. 8                       20-47

No. 40                       8-23

No. 200                      0-6

703-2.04  Aggregate for Plant Mix Asphalt Pavement.  In the second paragraph, after Fine Aggregate, delete the remainder of the sentence after "thereof" and add the following:

The fine aggregate will meet the following requirements:

Plastic Index     AASHTO T-90     4 max.

Sodium Sulfate    AASHTO T-104   15 percent max.

Soundness Loss

Add the following to Table 703-3, Asphalt Concrete Aggregate:

Asphalt Concrete

Sieve Designation                   Type IA

1-inch                           100

3/4-inch                          75-95

1/2-inch                          52-86

3/8-inch                          41-80

No. 4                            21-66

No. 10                           10-58

No. 40                            5-38

No. 80                            4-23

No. 200                           3-10

703-2.07  Selected Material.  Add the following to Item 1., Selected Material, Type A:  It shall have 30 to 55 percent by weight of particles passing the No. 4 sieve.

SECTION 707

METAL PIPE

Special Provisions

707-2.05  Water Conduit.  Delete in its entirety and add the following:

1.	Applicable Standards for Water Conduit.  The most recent revision for the following standards for the American Society for Testing and Materials (ASTM), the American Association for State Highway and Transportation Officials (AASHTO), the American Standards Association (ASA), and the American Water Works Association (AWWA) are hereby made a part of these specifications:

ANSI/AWWA C-104/A21.4-85		Cement Mortar Lining  for Ductile Iron Pipe and Fittings for Water.

ANSI/AWWA C-105/A21.5-88		Polyethylene Encasement Ductile Iron Piping For Water and Other Liquids.

ANSI/AWWA C-110/A21.10-87	Ductile Iron and Gray Iron Fittings, 3-Inch Through 48-Inch, For Water And Other Liquids.

ANSI/AWWA C-111/A21.11-85	Rubber Gasket Joints for Ductile Iron and Gray Iron Pressure Pipe and Fittings.

ANSI/AWWA C-115/A21.15-88	Flanged Ductile Iron Pipe with Threaded Flanges.

ANSI/AWWA C-150/A21.50-81	Thickness Design of Ductile Iron Pipe.

ANSI/AWWA C-151/A21.51-81	Ductile Iron Pipe, Centrifugally Cast in Metal Molds Or Sand Lined Molds, For Water Or Other Liquids.

2.	Ductile Iron Pipe and Fittings.

a.	Pipe.  Ductile iron pipe shall conform to AWWA C-151, with cement mortar lining meeting the requirements of AWWA C-104.  Class 52 ductile iron pipe shall be used for water conduit between 3 and 16-inches in diameter unless otherwise indicated on the plans.

b.	Fittings.  All fittings shall be a minimum 250 psi pressure rating, mechanical joint or all bell, either lined or unlined, either cast iron or ductile iron, unless otherwise indicated on the plans or in these special provisions.  All fittings shall meet the requirements of AWWA C-110.

Rubber gasket joints for ductile iron pipe and fittings shall conform to AWWA C-111.

c.	Piping Joints and Connections.

Joint Tie Rods.  Tie rods shall be all-thread black iron or mild steel and shall be located symmetrically around the perimeter of the pipe, using anchoring lugs of standard manufacture for attachment where required.  Tie rods shall be 3/4-inch diameter on pipe 16-inches and less.  There shall be 2 rods on pipes 12-inches and less and 4 each on pipes 14-inches to 16-inches in diameter.

707-2.06  Service Pipe.  Delete in its entirety and

add the following:

Pipe.  Ductile iron pipe or soft drawn seamless copper type "K" shall be used for all water service pipe.  Galvanized pipe, asbestos-cement pipe and the use of lead-tipped gaskets shall be prohibited.

Key Box, Valve Box.  The key box shall provide clear and unobstructed access to a valve or curb stop to enable the AWWU operation of the valve or curb stop.  Key boxes or valve boxes shall be furnished and installed in accordance with Subsection 627-3.05, Valve Boxes and Subsection 712-2.11, Valve Service Boxes.  AWWU key boxes shall not be in contact with a natural gas main or service line.

707-2.07  Sewer Conduit.  Add the following subsection:

1.	Applicable Standards for Sewer Conduit.  The most recent revision for the following standards for the American Society for Testing and Materials (ASTM), the American Association for State Highway and Transportation Officials (AASHTO), the American Standards Association (ASA), and the American Water Works Association (AWWA) are hereby made a part of these specifications:

ANSI/AWWA C104/A21.4		Cement Mortar lining for ductile-iron pipe and fittings for water

ANSI/AWWA C105/A21.5    		Polyethylene encasement for ductile-iron piping for water and other liquids

ANSI/AWWA C110/A21.10		Ductile-iron and gray-iron fittings, 3 in. through 48 in., for water and other liquids

ANSI/AWWA C111/A21.11		Rubber-gasket joints for ductile-iron and gray-iron pressure pipe and fittings

ABSI/AWWA C150/A21.50		Thickness design of ductile-iron pipe

ANSI/AWWA C151/A21.51		Ductile-iron pipe, centrifugally cast in metal molds or sand-lined molds, for water or other liquids

2.	Ductile Iron Pipe and Fittings.

a.	Pipe.  Ductile iron pipe shall conform to  ANSI/AWWA C151/A21.51, with cement mortar lining meeting the requirements of ANSI/AWWA C104/A21.4.  Class 50 ductile iron pipe shall be used unless otherwise required.

b.	Fittings.  All fittings shall be a minimum 250 psi pressure rating, mechanical joint or all bell, either lined or unlined, either cast iron or ductile iron, unless otherwise indicated on the plans or in these Special Provisions.  All fittings shall conform to the requirements of ANSI/AWWA C110/A21.10.

Rubber gasket joints for ductile iron pipe and fittings shall conform to ANSI/AWWA C111/A21.11.

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.05  Precast Concrete Units.  Add the following after the first paragraph:  Sanitary sewer manholes shall also conform to the requirements of the details shown on the Plans.  Cones shall be Type (b), eccentric, unless otherwise approved.

Each precast concrete barrel section shall be set upon and sealed with pre-molded plastic gasket as manufactured by K.T. Snyder Co., Ram-Nek Gasket Division, 2100 Travis Street, Houston, Texas or equal.

712-2.06  Frames, Grates, Covers and Ladder Rungs.  Add the following:  Ductile iron castings shall conform to the requirements of ASTM A536 for grade 60-4018.  (9/1/89)

712-2.09  Corporation Stops and Curb Stops.  Add the following:  Use Mueller Corporation Stop No. 15000 or equal for 3/4-inch and 1-inch service pipe connections.  Use Mueller Curb Stop No. H15214 or equal for 3/4-inch and 1-inch, copper to copper connections.  Rod to be attached to curb stop with no. 6 gauge copper wire.

Use Mueller Corporation Stop No. 15025 or equal for 1-1/2-inch and 2-inch service pipe connections.  Use Mueller Curb Stop No. H15214 Ori-Seal or equal for 1-1/2 inch and 2 inch connections.  Mueller Service Clamp or equal with two straps shall be used on all pipe.  Rod to be attached to curb stop with no. 6 gauge copper wire.

712-2.10  Gate Valves.  Delete this subsection in its entirety and substitute the following:

1.	Gate Valves.  Gate valves shall be iron body, fully  bronze mounted, double disc, parallel seat valves as manufactured in accordance with the requirements of AWWA C500 "Gate Valves for Ordinary Water Works Service".  All valves shall be nonrising stem type with an O-ring seal and a 2-inch square operating nut, and shall open counterclockwise.  Valves shall have mechanical joint ends.

712-2.11  Valve Service Boxes.  Delete in its entirety and substitute the following:

1.	Valve Boxes.  Valve boxes, whether installed for mainline valves or curb stops, shall be cast iron of sliding, adjustable-height type with round or oval bottom hood sections to fit over the top of the valve.  The top section shall be recessed to receive a close fitting "eared" lid with the word "WATER" or "SEWER cast into it. Internal diameter of the smallest section shall not be less than 5-inches.  The minimum thickness of the metal shall not be less than 5/16-inch.  Castings shall be smooth and the workmanship shall be acceptable to the Engineer.

Valve boxes shall be sufficient length for the pipe cover depth shown on the profile drawings and in accordance with the details shown on the plans.

2.	Markers.  Valve boxes shall be marked with a marker consisting of 2-1/2 inch O.D. galvanized steel pipe sections, 7-feet in length, with 3-feet buried in the ground.  Markers shall be shop painted "Caterpillar Yellow" and stenciled with 2-inch black numerals, showing the appropriate references.  Markers shall be located on the nearest property line, due north, south, east or west of the valve at a maximum distance of 50-feet, unless otherwise directed by the Engineer.  Markers shall carry the notation "VB (feet)(direction)".  Markers will not be required where valve boxes are located in paved areas.

712-2.14  Preformed Pavement Markings.  Add the following to paragraph A., under Item 1., General Requirements:  The preformed ribbon shall consist of one solid piece of required width and length.  In solid stripe areas, the tape length shall, where possible, be a minimum of 100 feet.

712-2.15  Temporary Raised Pavement Markers.  Add the following:  The temporary raised pavement markers shall be installed utilizing an approved raised pavement marker flexible bituminous adhesive.

The color of the raised pavement markers shall conform to the color of the marking for which they supplement, substitute, or serve as a positioning guide.

712-2.16  Temporary Raised Pavement Markers for Short-Term Operations, Seal Coats, and Surface Treatments.  Add the following subsection:  The marker shall consist of an L-shaped polyurethane body with retroreflective tape on the top vertical section and with a self-adhesive base.  Both faces of the yellow marker and one face of the white marker shall be reflectorized.  The marker body shall be made from 0.060 inch minimum thick polyurethane; the vertical leg shall be approximately 2 inches high by 4 inches wide and the base approximately 1-1/8 inches wide.  The polyurethane body shall conform to Table 712-1.

The adhesive shall be factory-applied to the marker base, and made of a pressure-sensitive material, a minimum 1/8 inch thick and 3/4 inch wide, with release paper.

Where chip seals, slurry seals or tack coats are to be utilized after placement of the temporary raised pavement markers, the markers shall come with a protective cover made of clear flexible polyvinyl chloride.

The reflective tape shall be metalized polycarbonate microprism retroreflective material with acrylic backing or equal, a minimum 0.25 inch wide by 4 inches long, and provide the minimum optical performance shown in Table 712-2, for an observation angle of 0.2 degrees.

TABLE 712-1

| PROPERTY | RESULT | ASTM TEST METHOD |
| --- | --- | --- |
| Specific Gravity (minimum) | 1.19 | D 792 |
| Hardness | 80A | D 2240 |
| Tensile Strength (min, psi) | 4600 | D 412 |
| Ultimate Elongation (minimum, percent) | 330 | D 412 |
| Modulus at 300 percent (minimum, psi) | 1000 | D 412 |
| Stiffness @-20 degrees F (min, psi) @+72 degrees F (min, psi) | 1700 900 | D 1053 D 1053 |
| Compression Set 22 hrs at 70 degrees C (maximum, percent) | 65 | D 395 |
| Taber Abrasion CS17 wheel wt loss (mg/1000 cycles) | 3 | --- |

TABLE 712-2

| HORIZONTAL ENTRANCE ANGLE | SPECIFIC INTENSITY * White Yellow |  |
| --- | --- | --- |
| 0 degrees | 3.5 | 3.0 |
| 30 degrees | 2.7 | 1.7 |

* Candelas per footcandle of illumination at the reflector on a plane perpendicular to the incident light.

(5/7/91)

SECTION 724

SEED

Special Provisions

724-2.02  Materials.   Add the following to Table 724-1:

| Seed Type | Germination Period | Percent Purity | Percent Germination | Percent Sproutable Seed |
| --- | --- | --- | --- | --- |
| Bering Hairgrass (Norcoast) | 14 days | 95 | 75 | 71 |
| Columbine (Aquilegia Caerulea) | N/A | 85 | 70 | 65 |
| Jacob's Ladder (Polemonium Pulcherrium) | N/A | 85 | 70 | 65 |
| Lupine (Lupinus nootkaensis or arcticus) | N/A | 85 | 70 | 65 |
| Milk Vetch (Astragalus spp.) | N/A | 85 | 70 | 65 |
| Yarrow (Achillea Millefolium) | N/A | 98 | 80 | 78 |
| Shasta or Ox Eye Daisy (Chrysanthemum Leucanthemum) | N/A | 96 | 88 | 84 |

SECTION 726

TOPSOIL

Standard Modifications

726-2.01  Topsoil.  In the second paragraph, change "not less than 1%" to read "not less than 3%".  (5/12/89)

SECTION 729

GEOTEXTILES

Standard Modifications

Delete this Section in its entirety and substitute the following:

729-2.01  Embankment Separation.

1.	Fibers used in the manufacturer of geotextiles, and the threads used in joining geotextiles by sewing, shall consist of long chain synthetic polymers, composed of at least 85 percent by weight polyolefins, or polyesters.  The geotextile shall be formed into a stable network such that the filaments or yarns retain their relative position to each other.  Both the geotextile and threads shall be resistant to chemical attack, mildew, and rot.

2.	Nonwoven geotextile may be formed by the needle-punched, spun-bonded or heat-bonded process.

3.	Woven geotextile shall be woven into a uniform pattern with distinct and measurable openings.  Edges of the cloth shall be selvaged to prevent the outer yarn from pulling away from the cloth.  The fabric shall be free from detrimental defects.

4.	The geotextile supplied shall meet the requirements listed in Table 729-1 for the type specified.

5.	The Contractor shall submit certification that the geotextile supplied meets the above requirements before it is used on the project.

Table 729-1

GEOTEXTILE REQUIREMENTS FOR

EMBANKMENT SEPARATION

| Geotextile Property | Test Method (ASTM) | Separation |  |
| --- | --- | --- | --- |
| Grab Elongation, % at breaking load | D-4632 | <50 | >50 |
| Grab Tensile Load, lbs, min. | D-4632 | 175 | 105 |
| Burst Strength, psi, min. | D-3786 | N/A | N/A |
| Trapezoid Tearing Strength, lbs, min. | D-4533 | 50 | 40 |
| Puncture Resistance, lbs, min. | D-4833 | 70 | 40 |
| Water Permittivity, 1/sec, min. | D-4491 | 0.04 | 0.30 |
| Apparent Opening Size, mm, max. | D-4751 | 0.30 | 0.21 |
| UV Degradation at 500 hour exposure, % strength retained | D-4355 | 70 | 70 |
| Geotextile Acceptance, Pass or Fail | D-4759 | Pass | Pass |

NOTES:                                                   1.	Separation geotextile supplied may have either less than, or greater than 50% elongation measured at breaking load in the Grab Tensile Test (ASTM D-4632).

2.	Geotextile Property Values = Minimum average roll values at a 95% confidence level in the weaker principal direction.

3.	0.21 mm = US Standard Sieve Size 70.

4.	0.30 mm = US Standard Sieve Size 50.

(5/7/91)

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04  Sign Posts. Delete Item 4., "Multi-directional Breakaway Load Concentration Coupler Base Assemblies and Coupler Hinge Plate", and substitute the following:

4.	Wide Flange Posts.

a.	Steel for wide flange posts shall conform to AASHTO M 183.

b.	Post sizes shall be as designated on the plans.

c.	Posts shall be hot dip galvanized in a manner conforming to AASHTO M 111 after fabrication.  Any cutting of metal posts after hot dip galvanizing shall be accomplished with minimum damage to the zinc coating and all exposed surfaces shall be protected by treating the exposed area in the same manner as if it were abraded or damaged.

d.	Galvanized surfaces that are abraded or damaged at any time after the application of the zinc coating shall be repaired in accordance with the applicable provisions of AASHTO M 36.

(5/7/91)

Add the following Section:

SECTION 740

RAILROAD TRACKWORK MATERIALS

Special Provisions

740-1.01  Description.  This work shall consist of furnishing and placing ballast in reasonable conformance with the plans.

740-2.01  Ballast.  Prepared ballast shall be crushed stone, or crushed gravel composed of hard, strong and durable particles, free from injurious amounts of deleterious substances and conforming to these specifications.

Deleterious substances shall not be present in prepared ballast in excess of the following amounts:

|  | Percent By Weight | Test Method |
| --- | --- | --- |
| Material finer than No. 200 sieve | 1.0% | ATM T-7 |
| Soft and Friable Pieces | 5.0% | AASHTO T-112 |

The percentage of wear of prepared ballast when tested in accordance with AASHTO T-96 shall not be greater than 45 percent in 500 revolutions.  The soundness of prepared ballast shall be such that when tested in the sodium sulfate soundness test AASHTO T-104, the weighted average loss shall not be in excess of 12 percent after five cycles.

Prepared ballast shall conform to the following requirements for grading.

| Sieve Designation | Percent Passing by Weight |
| --- | --- |
| 2 inch | 100 |
| 1-1/2 inch | 90-100 |
| 1 inch | 30-65 |
| 3/4 inch | 10-25 |
| 1/2 inch | 0-15 |
| No. 4 | 0-5 |
| Crushed Particles | Not less than 21% |

The grading of prepared ballast shall be determined in accordance with ATM T-7.  The percentage of crushed particles (fracture faces) in the prepared ballast shall be determined by ATM T-4.

740-3.01  Construction Requirements.  Ballast shall be placed at the locations shown on the plans in strict accordance with accepted railroad practice.

740-4.01  Method of Measurement.  Ballast will not be measured for payment.

740-5.01  Basis of Payment.  Payment for Ballast will not be made separately but will be subsidiary to Item 617(1), Railroad Crossing.

APPENDIX A

CONSTRUCTION SURVEYING REQUIREMENTS