- SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

1.	Publications.  The following are available from the Plans Room:

a.	Standard Specifications for Highway Construction, 2004 Edition ($25.00).

b.	Alaska Test Methods Manual (Lab & Field), 2012 Edition ($25.00). Available online at:

http://www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/pop_testman.shtml

c.	Alaska Storm Water Pollution Prevention Plan Guide, February 2012.

d.	Completion Documents (Quantity Computations, Material Reference, and Photo Log)

e.	Geotechnical Report, Kipnuk Boardwalk Improvements, Phase II, Golder and Associates Inc, December 2011.

f.	Erosion, Sediment Control Plan (ESCP), Kipnuk Boardwalk Improvements Phase II, CRW Engineering Group, LLC, December 2011.

g.	Structure Conflict Notebook, Kipnuk Boardwalk Improvements Phase II, CRW Engineering Group, LLC, January 2012

h.	Private Utility Conflict Notebook, CRW Engineering Group, LLC, February 2012

2.	Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix 	C	.

3.	Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

4.	Laborers Mechanics Minimum Rate of Pay.  The current Laborers Mechanics Minimum Rate of Pay contains information on remote sites and per diem.  The Department of Labor has issued WHPL #197, which further clarifies this requirement.  See pay item 640(4).

- 5.	Section 120, Disadvantaged Business Enterprise (DBE) Program.  Effective for FHWA funded projects advertised on or after March 5, 2012, there is a revised Statewide Special Provision for Section 120 DBE Program, revised DBE forms, and other revised construction contract forms.  Contractors are encouraged to review the construction contract forms and the revised Statewide Special Provision for Section 120 DBE Program which includes changes to timelines for submission of the DBE Utilization Report and DBE Good Faith Effort documentation, if applicable.  See also the revised Required Documents form, 25D-4A.

- Any questions about this notice may be directed to Grace San Miguel Morfield, Manager of the Civil Rights Office, (907) 269-0850, or email grace.sanmiguel-morfield@alaska.gov.

- 6.	DBE Program Waiver - Central Region Projects.  The US DOT Waiver for the DBE Program has been implemented on Central Region Projects since August 1, 2011.  The DBE Program Waiver approved by USDOT addresses the issue identified in the Department's Disparity Study which found that DBE firms that are owned by Non-Minority Women were participating on the Department's construction contracts and subcontracts on an equal basis similar to other non-DBE contractors and non-DBE subcontractors for Central Region only.

- As a result, DBE contract goals cannot be met through the use of female Caucasian owned DBEs.  This Waiver does not affect DBE project goals for airports or transit projects anywhere in Alaska, and does not apply to professional service agreements or highway construction projects in Northern or Southeast Regions.

- The decision to continue or discontinue the use of the Waiver will be made on an annual basis.

- Any questions about this notice may be directed to Grace San Miguel Morfield, Manager of the Civil Rights Office, (907) 269-0854, or email Grace.sanmiguel-morfield@alaska.gov.

7.	Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0650.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

8.	High Visibility Clothing.  The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retroreflectivity.  See subsection 643-3.11.

PART 4

STANDARD MODIFICATIONS

AND

SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004

EDITION

05-23-12

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS.

PLANS.  Delete Text of PLANS and replace with:

The Department’s Contract drawings, profiles, typical cross sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.

E32-012707

Insert the following definition after RESPONSIVE BID:

RETAINAGE.  A percentage of a payment established in advance under a contract or subcontract to be withheld from progress payment due on the contract or subcontract.  Payment or a percentage of payment withheld for unsatisfactory performance is not retainage.

E101-030512

Add the following definition:

QUALIFIED PRODUCTS LIST.  A list of companies and products that the Department has found conforms to the SSHC.

E36-012707

Replace the definitions of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.

E22-010106

- SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.

Replace the second paragraph with the following:

The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development.

E23-010106

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid must be signed by a corporate officer,” add: “or agent”.

E18-063004

Special Provision

Add the following Subsection 102-1.14:

102-1.14 MANDATORY POST-AWARD CONFERENCE. There will be a mandatory post-award conference held in Kipnuk prior to the Contractor beginning work. The Contractor is required to attend the post-award conference. All costs incurred by the Contractor to attend this conference, including air transportation, are at the Contractor’s expense. The Department will schedule the post-award conference and notify the Contractor at least 7 days prior to the conference date. The Department is not liable for delays or rescheduling of the post-award conference due to unforeseen circumstances. The proposed agenda for the conference is attached as Appendix E and identifies information the Contractor will be required to present.

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modifications

Delete Subsection 103-1.05 and replace with the following:

103-1.05 PERFORMANCE AND PAYMENT BONDS.  The successful bidder shall furnish all required Performance and Payment Bonds on forms provided by the Department for the sums specified in the Contract.  If no sum is specified, the successful bidder shall comply with AS 36.25.010.  The Surety on each bond may be any corporation or partnership authorized to do business in the state as an insurer under AS 21.09 or two individual sureties approved by the Contracting Officer.

If individual sureties are used, two individual sureties must each provide the Department with security assets located in Alaska equal to the penal amount of each bond.  Any costs incurred by the Contractor and the individual Surety are subsidiary and shall be borne by the Contractor or the individual Surety.  In no event will the Department be liable for these Costs.

Individual sureties shall provide security by one, or a combination, of the following methods:

1.	Escrow Account, with a federally insured financial institution, in the name of the Department.  Acceptable securities include, but are not limited to, cash, treasury notes, bearer instruments having a specific value, or money market certificates.

2.	Irrevocable letters of credit, with a financial institution approved by the Contracting Officer.

3.	Cashier’s or certified check, made payable to the State of Alaska issued by financial institutions approved by the Contracting Officer.

These bonds and security assets, as applicable, shall remain in effect for 12 months after the date of final payment or, if longer, until all obligations and liens under this Contract are satisfied, including, but not limited to, obligations under Subsection 107-1.19.

The Department may, in its discretion, notify the bonding company or Surety of any potential default or liability.

The Contractor shall substitute, within five working days, another bond or surety acceptable to the Department if an individual Surety or the Surety on any bond furnished in connection with the Contract:

1.	Becomes insolvent or is declared bankrupt;

2.	Loses its right to do business in any state affecting the work;

3.	Ceases to meet Contract requirements;

4.	Fails to furnish reports of financial condition upon request; or

5.	Otherwise becomes unacceptable to the Department.

When approved by the Contracting Officer, the Contractor may replace:

1.	An individual surety with a corporate surety; or

2.	Posted collateral with substitute collateral.

Failure to maintain the specified bonds or to provide substitute bonds when required under this section may be grounds for withholding contract payments until substitute bonding is obtained, and may, in the Department’s discretion, be grounds for declaring the Contractor in default.

E65-022309

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.01 INTENT OF CONTRACT.  Add to the end of this subsection:

The Contractor is responsible for the means, methods, techniques, sequence, or procedures of construction, safety, quality control, and to perform or furnish the work in accordance with the Contract documents.

E58-072808

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  In the third paragraph delete: "(24"x36")" and replace with: “(22"x34")”.

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS.  In the first sentence of the first paragraph after: "Work performed and materials furnished shall conform to the Plans and Specifications" add: “and approved Working Drawings”.

In the first sentence of the second paragraph after: "All work or material not conforming to the Plans and Specifications" add: “and approved Working Drawings”.

E33-012707

Special Provisions

105-1.06 UTILITIES.  Add the following:

Request locates from the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities.

ALASKA DIGLINE, INC.

Locate Call Centers: Anchorage 278-3121 Statewide (800) 478-3121

Call Centers will notify the following: General Communications, Inc. (GCI) United Utilities, Inc. (UNITED)

Call the following utilities and agencies directly:

Kipnuk Light Plant (Electric Utility)	(907) 896-5427

Kugkaktlik Ltd (Village Corporation)	(907) 896-5414

Native Village of Kipnuk (Water & Sewer)	(907) 896-5575

Lower Kuskokwim School District (Fuel)	(907) 896-5011

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent's phone number for this project.

Utilities Relocated by Others.

Some utilities will be relocated by others concurrently with construction of this project.  The Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.  For utilities being relocated, the Contractor will:

1.	include utility work on the Construction Phasing Plan and Progress Schedule.

2.	provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work.  Identify all utility companies performing ground disturbing activity in the Storm Water pollution Prevention Plan (SWPPP).  Refer to Section 641 for further information.

3.	provide traffic control and flagging as requested.  Payment will be made under Section 643, Traffic Maintenance.

4	provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

·	Control for utility relocation - either ROW or Centerline staking with Station information,

·	Slope staking,

·	Proposed utility facilities and appurtenances.

Payment will be made as follows:

a.	Subsidiary to Pay Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642(3) Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

Work done by utility owner(s) is as follows:

United Utilities, Inc (UUI): UUI owns and operates overhead telecommunication facilities within the project limits.  United Utility, Inc. facilities cannot be relocated until KLP stub poles and anchors are placed.  Once stub poles and anchors are placed, allow time and access for UUI to install, retire , relocate, and/or adjust facilities as noted:

- UUI will remove existing guy wires and install new overhead guy wires form existing poles, to new KLP stub poles and provide anchors at the following ten (10) locations:

  - Station 130+72

  - Station 701+22

  - Station 706+72

  - Station 710+35

  - Station 1700+65

  - Station 2010+27

  - Station 2305+95

  - Station 2600+91

  - Station 3203+90

  - Station 3600+38

Allow UUI one (1) calendar day per installation for a total of ten (10) calendar days to complete this relocation.

- Provide UUI a minimum of 15 calendar days, written notice following installation of the new pole at station 2002+41 and prior to removal of the existing pole to allow UUI to connect their system to the new pole.  UUI will relocate the existing 50 pair and guy wire.  Additional 50 pair may need to be spliced into existing to provide necessary length.  UUI will also install a downguy from the new pole to the provided anchor.

Allow UUI three (3) calendar days to complete this relocation.

- In order to provide 9.5 feet of clearance between services and the proposed boardwalk, UUI shall raise the existing telecommunications riser on the buildings at stations:

  - Station 2302+45

  - Station 3300+24

  - Station 3600+40

Allow UUI one (1) calendar day to raise each riser, for a total of three (3) calendar days to complete this relocation.

See Section 681 for UUI contact information.

Kipnuk Light Plant:  Work includes relocation of existing electrical wire at one location on the project.  Work will be coordinated with Contractor’s efforts to relocate electrical poles and wires throughout project.  Allow time for Kipnuk Light Plant to relocate facility as noted.

Existing overhead electrical wire does not currently have adequate vertical clearance and will need to be raised at Station 1703+30.

Inspection of the Electrical construction will be provided by Kipnuk Light Plant.  Contact Sam Carl at 907-896-5427 to provide schedule and access for electrical inspection.

Privately Owned Utilities: Work includes relocation of existing electrical wires, guy wires, and satellite cable wires throughout project.

Existing overhead electrical service wires do not have adequate vertical clearance or do not meet other electrical code requirements and will need to be removed or relocated in the following locations:

| - Station 701+75 | - Station 3005+15 |
| --- | --- |
| - Station 702+78 | - Station 3104+99 |
| - Station 707+17 | - Station 3202+60 |
| - Station 709+23 | - Station 3202+65 |
| - Station 810+92 | - Station 3302+60 |
| - Station 2602+44 | - Station 3305+56 |
| - Station 2603+10 | - Station 3400+83 |
| - Station 3001+99 | - Station 3500+18 |
| - Station 3003+06 | - Station 3600+70 |

Existing overhead satellite cable wires do not currently, or will not after boardwalk construction, have adequate vertical clearance and will need to be removed or relocated in the following locations:

| - Station 3003+66 | - Station 706+30 |
| --- | --- |
| - Station 3203+87 | - Station 3104+28 |

Existing guy wires supporting UHF antennas do not have adequate horizontal clearance from proposed boardwalk and will need to be removed or relocated in the following locations:

- Station 1700+90

- Station 3600+34

57181-120111

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:

The following projects may be under construction concurrently with this project.

| Project Name: | Project No.: |
| --- | --- |
| Kipnuk Airport Relocation – Phase II | 57796 |
| LKSD Kipnuk K-12 Renovation/Addition |  |
| Kipnuk Light and Power High Penetration Wind Diesel Power and Heat |  |
| Kipnuk Honey Bucket Lagoon Closure | KIP S12SCW |

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

57181-120111

Standard Modifications

105-1.13 MAINTENANCE DURING CONSTRUCTION.  Add the following at the end of this subsection:

Costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various Contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer's opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance.  The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance.  If the Contractor fails to take corrective action within the specified time, the Engineer may:

1.	Suspend the work until corrective maintenance is completed;

2.	Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

3.	Employ others for corrective maintenance and deduct the cost from the Contract amount.

E33-012707

105-1.15 PROJECT COMPLETION.  In the second paragraph, second sentence, delete:

“Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

In the third paragraph, first sentence, delete:

“Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

E59-072808

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION.  Modify the first paragraph, Item 4. after: “DOLWD” add: and State Department of Revenue.

E19-063004

Special Provisions

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following:

Appeals to the superior court under AS 36.30.685 must be filed in the Third Judicial District.

CR93-032101

Standard Modification

Add the following Subsection 105-1.18:

105-1.18 RESERVED FOR WARRANTIES.

E33-012707

SECTION 106

CONTROL OF MATERIAL

Standard Modification

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  In fifth paragraph, in two places remove the text. “Approved Products List” and replace with:  Qualified Products List.

E36-012707

Special Provision

Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and submit a completed Material Origin Certificate, Form 25D-60, before award of the Contract.

Steel and iron products, which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the Project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating process must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap pig iron, and processed, pelletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

CR13-020705

Standard Modifications

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a. delete text and replace with:  Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4.  When there is insufficient, Useable Excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources.  Replace the first paragraph with the following:

The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

d.	Available Sources.  Replace the second paragraph with the following:

When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

e.	Excluded Material Sources.  Replace the paragraph with the following:

Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material source or any portion of a material source, at any time after Contract Award that is determined by material testing to be unsuitable for use on the Project.

E24-010106

Add new Subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE.  The Contractor shall complete a Submittal Register, and shall submit to the Engineer on forms provided by the Department.  The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified Project document.  The Contractor shall fill it out sequentially by bid Item and allow at least three spaces between bid items.  The Submittal Register shall list working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation, and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items.  If the number of copies of a submittal is not otherwise specified, three copies shall be required.  On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet.  The Contractor may use forms provided by the Department of a similar form of the Contractor’s choice as approved by the Department.  The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received.  The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed.  The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections.  The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department.  The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract Item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract Item.

When material invoices, freight bills, and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); Project name and number where material will be incorporated, manufacturer, product number, quantity and cost.

Add the following Subsection 106-1.09:

106-1.09 RESERVED.

E34-012707

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.  Under “The Department will:” Add No. 3:

- The Department has received the following permits on the Contractor’s behalf:

a.	Wetlands Fill Permit – Department of the Army, U.S. Army Engineer District, Alaska, Permit No. POA-2011-1193, Kuguklik River, dated March 14, 2012.  A copy is contained in Appendix B.

b.	Temporary Construction Easement – Native Village of Kipnuk, dated March 7, 2012.  A copy is contained in Appendix D.

Under “The Contractor shall:” Add the following:

9.	Provide information to comply with the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

10.	Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also, provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

57181-041312

Standard Modification

107-1.05 FEDERAL AID PROVISIONS.  Add the following:

Form 25D-55H Required Contract Provisions for Federal-Aid (FHWA) Construction Contracts.  The FHWA no longer requires the Contractor to fill out FHWA Form 47, Statement of Materials and Labor Used By Contractors on Highway Construction Involving Federal Funds.  Section VI Records of Materials, Supplies and Labor of Form 25D-55H is no longer applicable to highway construction contracts.

Title VI Requirements.  During the performance of this Contract, the Contractor, for itself, its assignees, and successors in interest (hereinafter referred to as the "Contractor") agrees as follows:

(1)	Compliance with Regulations:  The Contractor shall comply with the Regulation relative to nondiscrimination in Federally-assisted programs of the Department of Transportation (hereinafter, "DOT") title 49, Code of Federal Regulations, Part 21, and the Federal Highway Administration (hereinafter "FHWA") Title 23, Code of Federal Regulations, Part 200 as they may be amended from time to time, (hereinafter referred to as the Regulations), which are herein incorporated by reference and made a part of this Contract.

(2)	Nondiscrimination:  The Contractor, with regard to the work performed by it during the contract, shall not discriminate on the grounds of race, color, or national origin, sex, age, and disability/handicap in the selection and retention of subcontractors, including procurements of materials and leases of equipment.  The Contractor shall not participate either directly or indirectly in the discrimination prohibited by 49 CFR, Section 21.5 of the regulations, including employment practices when the Contract covers a program set forth in Appendix B of the Regulations.

(3)	Solicitation for Subcontractors, Including Procurements of Materials and Equipment:  In all solicitations either by competitive bidding or negotiation made by the Contractor for work to be performed under a subcontract, including procurements of materials or leases of equipment, each potential subcontractor or supplier shall be notified by the Contractor of the Contractor's obligations under this Contract and the Regulations relative to nondiscrimination on the grounds of race, color, or national origin, sex, age, and disability/handicap.

(4)	Information and Reports:  The Contractor shall provide all information and reports required by the Regulations or directives issued pursuant thereto, and shall permit access to its books, records, accounts, other sources of information, and its facilities as may be determined by the DOT&PF or the FHWA to be pertinent to ascertain compliance with such Regulations, orders and instructions.  Where any information required of a Contractor is in the exclusive possession of another who fails or refuses to furnish this information the Contractor shall so certify to the DOT&PF, or the FHWA as appropriate, and shall set forth what efforts it has made to obtain the information.

(5)	Sanctions for Noncompliance:  In the event of the Contractor's noncompliance with the nondiscrimination provisions of this Contract, the DOT&PF shall impose such contract sanctions as it or the FHWA may determine to be appropriate, including, but not limited to:

(a)	withholding of payments to the Contractor under the Contract until the Contractor complies, and/or

(b)	cancellation, termination, or suspension of the Contract, in whole or in part.

(6)	Incorporation of Provisions:  The Contractor shall include the provisions of paragraphs (1) through (6) in every subcontract, including procurements of materials and leases of equipment, unless exempt by the Regulations, or directives issued pursuant thereto.

The Contractor shall take such action with respect to any subcontract or procurement as the DOT&PF or the FHWA may direct as a means of enforcing such provisions including sanctions for non-compliance:  Provided, however, that in the event a Contractor becomes involved in, or is threatened with, litigation with a subcontractor or supplier as a result of such direction, the Contractor may request the DOT&PF to enter into such litigation to protect the interests of the DOT&PF, and, in addition, the Contractor may request the United states to enter into such litigation to protect the interests of the United States.

E67-101509

Special Provision

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Change the first sentence to the following:  When operations encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

CR7-033012

Standard Modification

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following paragraphs:

7.	Restoring Areas.  Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed.  The original condition of an area shall be determined as follows:

Before beginning operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition.  After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs.  Before demobilization, the Contractor shall repair damages attributed to its operations.  The Contractor agrees that costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

8.	Material Disposal Sites.  Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result there from, together with permits required by law for such dumping.  A copy of permission, waiver of claims, and permits shall be filed with the Engineer before beginning work on private property.  The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.

E35-012707

Special Provisions

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following:

If water is required for a construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

CR7-033012

Spectacled Eiders, Steller Eiders, and Short Tailed Albatross are listed by the US Fish and Wildlife Service as threated or endangered species that could be encountered in the Kipnuk Region.  A survey for of the project area looking for Spectacled Eiders shall be conducted by the Contractor prior to construction activities occurring during breeding season.  Breeding season is typically mid-May through late July, but the Contractor is responsible for performing the survey at all times that Spectacled Eiders are breeding.  Surveys should focus on pond shorelines and small islands, the preferred nest sites for spectacled eiders.  If Spectacled Eider nests are found, work must stop in that area and FWS must be contacted.

The surveyed project area shall, at a minimum, include all areas within 200 meters (656 feet) of proposed construction activities.

57181-120111

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity Disadvantaged Business Enterprise and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A 301

EEO-1 Certification	Form 25A 304

ADOT&PF Training Program Request	Form 25A 310

Training Utilization Report	Form 25A 311

Contact Report	Form 25A 321A

DBE Subcontractable Items	Form 25A 324

DBE Utilization Report	Form 25A 325C

Summary of Good Faith Effort Documentation	Form 25A 332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D 55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

S80-012202

SECTION 108

PROSECUTION AND PROGRESS

Standard Modification

Delete Subsection 108-1.01 in its entirety and replace with the following:

108-1.01 SUBCONTRACTING OF CONTRACT.  The Contractor shall submit a Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or any subcontractor subcontracts, sells, transfers, assigns, or otherwise disposes of the Contract or any portion of the Contract.  The Department has authority to review subcontracts and to deny permission to subcontract work.  The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

The Contractor shall perform, with the Contractor's own organization, work amounting to at least 30 percent of the difference between the original Contract price and the price of designated Specialty Items.  For the purpose of this Subsection, work is defined as the dollar value of the services, equipment, materials, and manufactured products furnished under the Contract.  The Engineer will determine the value of the subcontracts based on Contract unit prices or upon reasonable value, if entire items are not subcontracted.

The Department's consent to the subcontracting, sale, transfer, assignment, or disposal of all or a part of the Contract shall not relieve the Contractor and the Surety of responsibility for fulfillment of the Contract or for liability under bonds regardless of the terms of the transfer or sublet approvals.

1.	The Contractor shall ensure that for all subcontracts (agreements):

a.	The Department is furnished with one completed Contractor Self Certification, Form 25D-042, for each subcontract;

b.	The subcontractors have submitted a Bidder Registration; Form 25D-6;

c.	The required prompt payment provisions of AS 36.90.210 are included in all subcontracts;

d.	A clause is included requiring the Contractor to pay the subcontractor for satisfactory performance according to AS 36.90.210 and within eight (8) working days after receiving payment for which the subcontractor is to be paid.

e.	A clause is included requiring the Contractor to pay the subcontractor interest, according to AS 45.45.100(a), for the period beginning the day after the required payment date and ending on the day payment of the amount due is made;

f.	A clause is included requiring the Contractor to pay the subcontractor all retainage due under the subcontract, within eight (8) working days after final payment is received from the Department, or after the notice period under AS 36.25.020(b) expires, whichever is later;

g.	A clause is included requiring the Contractor to pay interest on retainage, according to AS 36.90.250 and AS 45.45.101(a);

h.	Other required items listed in Form 25D-042 are included in the subcontracts;

i.	The subcontractors pay current prevailing rate of wages as per Subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for all work performed on the project; and

j.	Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

2.	The Contractor shall ensure that for all lower tier subcontracts (agreements between subcontractors and lower tier subcontractors):

a.	The required prompt payment provisions of AS 36.90.210 are included in all lower tier subcontracts;

b.	A clause is included requiring the subcontractor to pay the lower tier subcontractor for satisfactory performance according to AS 36.90.210, and within eight (8) working days after receiving payment from which the subcontractor is to be paid;

c.	A clause is included requiring the subcontractor to pay the lower tier subcontractor interest, according to AS 45.45.010(a), for the period beginning the day after the required payment date and ending on the day payment of the amount due is made;

d.	A clause is included requiring the subcontractor to pay the lower tier subcontractor all retainage due under the subcontract, within eight (8) working days after final payment is received, or after the notice period under AS 36.25.020(b) expires, whichever is later;

e.	A clause is included requiring the subcontractor to pay the lower tier subcontractor interest on retainage, according to AS 36.90.250 and AS 45.45.101(a);

f.	Other required items listed in Form 25D-042 are included in the lower tier subcontracts;

g.	The lower tier subcontractors pay current prevailing rate of wages as per Subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for all work performed on the project; and

h.	Upon receipt of a receipt for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

3.	The following will be considered as subcontracting, unless performed by the Contractor:

a.	Roadside Production.  Roadside production of crushed stone, gravel, and other materials with portable or semi-portable crushing, screening, or washing plants set up or reopened in the vicinity of the project to supply materials for the project, including borrow pits used exclusively or nearly exclusively for the project.

b.	Temporary Plants.  Production of aggregate mix, concrete mix, asphalt mix, other materials, or fabricated items from temporary batching plants, temporary mixing plants, or temporary factories that are set up or reopened in the vicinity of the project to supply materials exclusively or nearly exclusively for the project.

c.	Hauling.  Hauling from the project to roadside production, temporary plants, or commercial plants, from roadside production or temporary plants to the project, from roadside production or temporary plants to commercial plants, and all other hauling not specifically excluded in this subsection.

d.	Other Contractors.  All other contractors working on the project site under contract with the Contractor are considered subcontractors unless specifically excluded in this subsection.

4.	The following will not be considered as subcontracting, but the Contractor shall comply with the prompt payment provisions AS 36.90:

a.	Commercial Plants.  The purchase of sand, gravel, crushed stone, crushed slag, batched concrete aggregates, ready-mixed concrete, asphalt paving mix, and any other materials or fabrication produced at and furnished from established and recognized commercial plants that sell to both public and private purchasers.

b.	Hauling.  Delivery of materials from a commercial plant to a different commercial plant, and delivery from a commercial plant to the project site by vehicles owned and operated by the commercial plants or by commercial freight companies that have a contract with the commercial plant.  Commercial freight companies are trucking or hauling companies that deliver multiple types of materials to multiple clients, both public and private, on an established route, and on a recurrent basis.

c.	Contractors' General Business.  Work within permanent home offices, branch plants, fabrication plants, tool yards, and other establishments that are part of a contractor's or subcontractor's general business operations.

5.	Owner-Operators.  Hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor or approved subcontractor is not considered subcontracting for purposes of AS 36.30.115.

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in contracts with owner-operators.

The Contractor shall collect and maintain at the project site current and valid copies of the following to prove that each trucker listed is a bona fide owner-operator.

a.	Alaska Driver's License with appropriate CDL class and endorsements;

b.	Business license for trucking with supporting documents that list the driver as the business owner or corporate officer;

c.	Documents showing the driver's ownership interest in the truck, including copies of:

(1)	Truck registration; and

(2)	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of these records for a period of at least three years after final acceptance of the project.

Owner-operators must qualify as independent contractors under the current Alaska Department of Labor's criteria.  Owner-operators may be required to show:

a.	The owner-operator's right to control the manner in which the work is to be performed;

b.	The owner-operator's opportunity for profit or loss depending upon their managerial skill;

c.	The owner-operator's investment in equipment or materials required for their task, or the employment of helpers;

d.	Whether the service rendered requires a special skill;

e.	The degree of permanence of the working relationship; and

f.	Whether the service rendered is an integral part of the owner-operator's business.

The status of owner-operators is subject to evaluation throughout the project period.  If the criteria for an independent contractor are not met, the Contractor shall submit amended payrolls listing the driver as an employee subject to all labor provisions of the Contract.

The Contractor shall issue each owner-operator a placard in a form approved by the Engineer that identifies both the truck driver and the vehicle.  The placard shall be prominently displayed on the vehicle so that it is visible to scale operators and inspectors.

Notwithstanding the Department's definitions of contracting and subcontracting, the Contractor shall be responsible for determining and complying with all federal and state laws and regulations regarding contracting, subcontracting, and payment of wages.  The Contractor shall promptly pay any fines or penalties assessed for violations of those laws and regulations, and shall promptly comply with the directives of any government agency having jurisdiction over those matters.

E102-030512

Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:

Submit the following at the Preconstruction Conference:

Delete the last sentence of the first paragraph in No. 1.  A progress schedule, and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.

CR261-121302

108-1.04 LIMITATION OF OPERATIONS.  Add the following paragraphs:

Existing boardwalk shall be replaced with new constructed boardwalk within 7 calendar days of the date from when it was removed.  Upon approval of the Engineer, Contractor may provide a temporary access route around removed boardwalk when more than 7 days is required between existing boardwalk removal and new boardwalk construction.  Contractor shall submit proposed method and surfacing for temporary access routing for Engineer’s approval.  In no case shall time between existing boardwalk removal and new boardwalk construction exceed 28 days.

Contractor shall limit working hours to between 7:00 AM and 7:00 PM each day.

57181-120111

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Under subtitle Electronic Computerized Weighing System Item (1) add the following to the end of the first sentence:

", CD, or a USB device."

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.  Under Item 3. Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

CR14-043105

Standard Modification

Delete Subsection 109-1.06 in its entirety and replace with the following:

109-1.06 PROGRESS PAYMENTS.  The Department will make monthly progress payments to the Contractor based on estimates of the value of work performed and materials on hand under Subsection 109-1.07.  At the Departments discretion, a progress payment may be made twice monthly if the value of the estimate exceeds $10,000.

Contractor's failure to pay subcontractors or subcontractor's failure to pay lower tier subcontractors, according to prompt payment provisions required under Subsection 108-1.01 is considered unsatisfactory performance.

The Department will not withhold payment as retainage but may withhold payment for unsatisfactory performance.  If satisfactory progress is being made and subcontractors are paid according to Subsection 108-1.01 and AS 36.90.210, the Engineer will authorize 100 percent payment for the estimated value of work accomplished, less any authorized deductions.

If the Engineer finds that satisfactory progress is not being made or payment for satisfactory work by a subcontractor or lower tier subcontractor is not paid according to Subsection 108-1.01, the Engineer may withhold up to 100 percent of the total amount earned from subsequent progress payments.  The Engineer may withhold up to 200 percent of the estimated cost to complete final punch list items for unsatisfactory performance until those items are complete.  The Engineer will notify the Contractor in writing within eight (8) working days of a request for a progress payment of the reasons why part or all of the payment is being withheld for unsatisfactory performance and what actions may be taken by the Contractor to receive full payment.

Payments of withheld amounts will be made in accordance with AS 36.90.200.  No interest will be paid to the Contractor for amounts withheld for unsatisfactory performance except if the Department fails to pay the amount withheld within twenty one (21) calendar days after the Contractor satisfactorily completes the remedial actions identified by the Engineer, as provided in AS 36.90.200(e).

The Contractor shall pay interest on retainage withheld from subcontractors, and at an interest rate according to AS 36.90.250 and AS 45.45.010(a).

E103-030512

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of Subsection 105-1.16.

E11-063004

Special Provisions

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, the opportunity to participate fairly with other contractors in the performance of contracts financed with federal funds.  The Contractor and subcontractors shall not discriminate on the basis of race, color, national origin, or sex in the performance of this Contract.  The Contractor will carry out applicable requirements of 49 CFR Part 26 in the award and administration of US DOT assisted contracts.

120-1.02 INTERPRETATION.  This Section implements the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this Section is a material breach of contract, which may result in contract termination or other remedy as DOT&PF deems appropriate.  Failure to comply with this Section is justification for debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.

1.	Administrative Reconsideration.  A process by which the low bidder may request reconsideration when the Department determines the Good Faith Effort (GFE) requirements have not been met.

2.	Broker.  A certified DBE for the delivery of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary to complete the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and ensuring that the materials meet specifications before credit will be given.

3.	Civil Rights Office. The Department's Civil Rights Office.

4.	Contract Compliance Officer.  Individual within the Civil Rights Office with the authority to administer the Department's compliance programs.

5.	Disadvantaged Business Enterprise.  A Disadvantage Business Enterprise which is a for-profit small business concern that is certified in accordance with 49 CFR, Part 26 and listed in the Alaska DBE Directory.

6.	DBE Key Employee.  A permanent, year-round employee of the DBE and whose name is on file with the Civil Rights Office as a key employee.  A key employee may act as an on-site representative when the owner is not on-site.

7.	DBE Utilization Goal.  The percent of work to be performed by certified DBEs.  The goal is established by the Department and specified in the Contract.

8.	DBE Officer.  Individual designated in writing as a representative of the Contractor concerning DBE issues.

9.	Manufacturer.  A DBE certified in a supply category that changes the shape, form, or composition of original material in some way.  The DBE must provide that material to the general public or the construction industry at large on a regular basis.

10.	Race Conscious Participation.  DBE participation used to meet a specified DBE Utilization Goal.

11.	Race Neutral Participation.  DBE participation that is in excess of the specified DBE Utilization Goal.

12.	Regular Dealer.  A DBE certified in a supply category who operates in a manner consistent with industry practice and who:

a.	maintain an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally fabricate (assemble large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

d.	a person may be a regular dealer in such bulk items as petroleum products, steel, cement, gravel, stone, or asphalt without owning, operating, or maintaining a place of business, if the person both owns and operates distribution equipment for the products.  Any supplementing of regular dealers' own distribution equipment shall be by a long-term lease agreement and not on an ad hoc or contract-by-contract basis.

120-2.01 MEETING THE DBE UTILIZATION GOAL.  A DBE's proposed work may be used to demonstrate the successful bidder's ability to meet the DBE Utilization Goal before Contract award.  The DBE must be certified in a category covering the Commercially Useful Function to be performed at the time of listing on Form 25A-325C (DBE Utilization Report).

A bidder may meet the DBE Utilization Goal through (1) the participation of certified DBE firms, or (2) documentation of required Good Faith Effort (Subsection 120-3.01), or (3) a combination of participation and Good Faith Effort to be eligible for Contract award.

DBE participation on contingent sum items will count as RACE Neutral DBE participation and not towards fulfilling a minimum DBE Utilization Goal, which is RACE Conscious DBE participation.

120-3.01 DETERMINATION OF COMPLIANCE.

1.	Phase I-Bid.  All DBE Good Faith Efforts must be completed prior to bid opening.

2.	Phase II-Award.  The apparent low bidder shall submit evidence of DBE commitment(s) within five working days after receipt of written notification by the Department of the successful low bid.  The apparent low bidder may not supplement its DBE efforts after opening, nor may offer new or additional DBE participation after submitting the DBE Utilization Report (Form 25A-325C).

a.	Written DBE Commitment:  Complete Form 25A-326 for each DBE subcontractor.

b.	DBE Utilization Report.  Submit a completed DBE Utilization Report Form 25A-325C listing certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation.  Submit a completed Summary of Good Faith Effort Documentation Form 25A-332A (with attachments) and contact Report Form 25A-321A if the DBE Utilization Goal is not demonstrated on Form 25A-325C.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and cannot document the minimum required Good Faith Effort (as specified below), the Contracting Officer will determine the bidder to be not responsible.

120-3.02 GOOD FAITH EFFORTS (GFE).

1.	Good Faith Effort Criteria.  When a bidder fails to meet DBE Utilization Goals, the Civil Rights Office will use the following criteria to judge whether they have demonstrated sufficient Good Faith Effort to be eligible for award of the Contract.

a.	Consider All Subcontractable Items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items with an established DBE goal as identified on Form 25A-324, before bid opening.  It is the bidder's responsibility to facilitate DBE participation by making the work listed on the subcontractable items list available to DBE firms.

If the bidder cannot achieve the DBE Utilization Goal, then the bidder may also consider other items not listed that could be subcontracted to DBEs.

b.	Initial DBE Notification.  All DBEs listed in the Department's current DBE Directory that have a "Yes" Under Required GFE Contact and "Yes" under the specific Work Area (Region) must be contacted at least seven calendar days prior to bid opening.  DBEs certified to perform work items identified on Form 25A-324 must be contacted to solicit their interest.  Each contact with a DBE firm will be logged on a Contact Report, Form 25A-321A.

The bidder must give DBEs at least five calendar days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs will be consistently applied.

The only acceptable methods of initial and follow up notification are:

1)	By fax with a confirmation receipt of successful transmission to the DBE's fax number listed in the DBE Directory.  A fax transmission without receipt of successful transmission is unsatisfactory.

2)	By email with a confirmation of successful receipt by DBE's email address listed in the DBE Directory.  Email without confirmation of successful receipt is unsatisfactory.

3)	By U.S. Mail to the DBE's address listed in the DBE Directory with a return receipt requested.  Letters mailed without a return receipt signed by the DBE or DBE Key employee are unsatisfactory.  Delivery confirmation with evidence of successful delivery is an acceptable substitute for Return Receipt.

4)	By telephone solicitation with a record of the date and time of the telephone call made to the DBE's telephone number listed in the DBE Directory.  Telephone solicitation without a record of date and time is unsatisfactory.

c.	Non-Competitive DBE Quotes.  DBE quotes more than 10 percent higher than an accepted non-DBE quote will be deemed non-competitive, provided they are for the exact same work or service.

All evidence in support on a non-competitive bid determination must be provided at the time of the Good Faith Effort submittal.  When a DBE quote is rejected as being non-competitive, the work must be performed by the non-DBE subcontractor whose quote was used to provide the basis of the determination.  Payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the accepted quote.  This does not preclude increases due to change documents issued by the Department.

d.	Assistance To DBEs.  Contractors must provide DBEs with:

1)	Information about bonding or insurance required by the bidder.

2)	Information about securing equipment, supplies, materials, or related assistance or services.

3)	Adequate information about the requirements of the Contract regarding the specific item work or service sought from the DBE.

e.	Follow-up DBE Notifications.  Contact the DBEs to determine if they will be bidding.  For acceptable forms of notification and required documentation see 120-3.02, subsection 1.b items 1 through 4.

Failure to submit a bid by the deadline is evidence of the DBE's lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report, Form 25-321A.

f.	Good Faith Effort Evaluation.  Subsections (a) through (e) must be completed for a Good Faith Effort based submission to be considered.  Failure to perform and document actions contained in subsection (a) through (e) constitutes insufficient Good Faith Effort.  After submitting a Good Faith Effort, bidders may only clarify efforts taken before opening.  No new efforts or additional DBE participation is permitted after opening.

2.	Administrative Reconsideration.  49 CFR Part 26.53(d) provides an opportunity for administrative reconsideration when the Department determines that Good Faith Effort is insufficient.  This opportunity must be exercised within three working days of notification that Good Faith Efforts were unsatisfactory.  For reconsideration, the bidder must provide written documentation or argument concerning efforts to meet the DBE Utilization Goal.  No new or additional contact information may be provided.  Only contact information the bidder provided in support of its initial request for a Good Faith Effort determination by the Civil Rights Office may be presented to support the request for administrative reconsideration.

The process for an Administrative Reconsideration is as follows:

a.	The bidder will have the opportunity to meet with the DBE Liaison Officer in person to discuss the issue.  If so desired, the bidder must be ready to meet with the DBE Liaison Officer within four working days of receipt of notice that it failed to meet the requirements of this subsection.

b.	The DBE Liaison Officer will render a written decision and provide notification to the bidder within four working days after the meeting.  The written decision will explain the basis for finding.

c.	The finding of the DBE Liaison Officer cannot be appealed to the U.S. DOT.

3.	Phase III-Construction.

a.	DBE Creditable Work.  The Commercially Useful Function work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report, Form 25A-325C, shall be included in any subcontract, purchase order of service agreement with that DBE.

b.	DBE replacement.  The Contractor shall submit a written request to replace a DBE to the Engineer.  If approved, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  If the Engineer and the Civil rights Office agree that the criteria of Subsection 120-3.04 have been met, the DBE may be replaced by the Contractor with a non-DBE subcontractor.

c.	DBE Utilization Goal Adjustment.  The DBE Utilization Goal will be adjusted only if a DBE replacement is approved by the Engineer, and only to the extent the Contractor cannot obtain another DBE subcontractor to perform the work.

120-3.03 COMMERCIALLY USEFUL FUNCTION.

1.	Creditable Work.  Measuring the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable Commercially Useful Function work on this project.  This is determined by the Engineer in accordance with this Section.

Commercially Useful Function is limited to:

a.	Prime Contractors;

b.	Subcontractors;

c.	Manufacturers;

d.	Regular Dealers;

e.	Brokers; or

f.	Joint Ventures

2.	Determination of Commercially Useful Function.  In order for the Commercially Useful Function work of the DBE to be credited toward the goal, the Contractor will ensure that the DBE is certified in the appropriate category at the time of the submittal of the subcontract, or the issuance of a purchase order or service agreement.  Subcontracts, purchase orders and service agreements shall be consistent with written DBE commitment.

a.	The Commercially Useful Function performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, a regular dealer, or manufacturer of the product provided to this project.

b.	The following factors will be used in determining whether a DBE trucking company is performing a Commercially Useful Function:

1)	The DBE must be responsible for the management and supervision of the entire trucking operation for which it is responsible on a particular contract, and there cannot be a contrived arrangement for the purpose of meeting DBE goals.

2)	The DBE must itself own and operate at least one fully licensed, insured, and operational truck used on the Contract.

3)	The DBE receives credit for the total value of the transportation services it provides on the Contract using trucks it owns, insures, and operates using drivers it employs.

4)	The DBE may lease trucks from another DBE firm, including an owner-operator who is certified as a DBE.  The DBE who leases trucks from another DBE receives credit for the total value of the transportation services the lessee DBE provides on the Contract.

5)	The DBE may also lease trucks from a non-DBE firm, including from an owner-operator.  The DBE who leases trucks from a non-DBE is entitled to credit for the total value of transportation services provided by non-DBE lessees not to exceed the value of transportation services provided by DBE-owned trucks on the Contract.  Additional participation by non-DBE lessees receives credit only for the fee or commission it receives as a result of the lease arrangement.

6)	A lease must indicate the DBE has exclusive use of and control over the truck.  This does not preclude the leased truck from working for others during the term of the lease with the consent of the DBE, so long as the lease gives the DBE absolute priority for use of the leased truck.  Leased trucks must display the name and identification number of the DBE.

c.	The Contractor will receive credit for the Commercially Useful Function performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding Commercially Useful Function and potential DBE credit.

d.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the Commercially Useful Function criteria may be credited toward the DBE Utilization Goal.

e.	DBE work shall conform to the following requirements to be a Commercially Useful Function:

1)	It will be necessary and useful work required for the execution of the Contract.

2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

3)	It will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work will be performed with the DBE's own equipment.  Either the DBE owner of DBE On-Site Representative will be at the work site and responsible for the work.

4)	The manner in which the work is sublet or performed will conform to standard industry practice within Alaska, as determined by the Department.  The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

5)	The cost of the goods and services will be reasonable and competitive with the cost of goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling their delivery and fully responsible for ensuring that they meet specifications.  The cost of materials purchased from the Contractor or its affiliates is not creditable.

6)	Subcontract work, with the exception of truck hauling, shall be sublet by the same unit of measure as is contained in the Bid Schedule unless approved in advance by the Engineer.

7)	The DBE will control all business administration, accounting, billing and payment transactions.  The Contractor cannot perform these functions for the DBE.

In accordance with AS 36.30.420(b), the Engineer may inspect the offices of the DBE and audit their records to assure compliance.

3.	Rebuttal of a Finding of No Commercially Useful Function.  Consistent with the provisions of 49 CFR, Part §26.55(c)(4)&(5), before the Engineer makes a final finding that no Commercially Useful Function has been performed by a DBE, the Engineer will coordinate transmittal of the presumptive finding through the Civil Rights Office to the Contractor, who will in-turn, notify the DBE.  The Contractor will provide the DBE the opportunity to provide rebuttal information.  The Contractor shall present the information to the Engineer.

The Engineer, together with the Civil Rights Office, will make a final determination on whether the DBE is performing a Commercially Useful Function.  Under no circumstances will the Contractor take any action with respect to the DBE until the final determination is made.  The Engineer's decisions on Commercially Useful Function matters are subject to review by the Department, but are not administratively appealable to the US DOT.

4.	Monthly Required Reporting.  On a monthly basis, the Contractor shall submit the Monthly Summary of Disadvantaged Business Enterprise Participation, Form 25A-336, to the Civil Rights Office.  Reports are due by the 15th of the following month.  Also attach copies of canceled checks or bank statements that identify payer, payee, and amount of transfer to verify payment information shown on the form.

5.	Removal of DBE Certification.  Should a DBE performing a Commercially Useful Function lose its DBE certification during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

The Contractor must still meet the DBE Utilization Goal by expending Good Faith Effort (Subsection 120-3.03, 2.) and either:

a.	Withdrawing the subcontract, purchase order or service agreement from the decertified DBE to replace it with a currently certified DBE for that same work or service; or

b.	Continuing with the subcontract, purchase order or service agreement with the decertified firm and finding other work not already committed to DBEs in an amount that meets the DBE Utilization Goal.

120-3.04 TERMINATION OF A DBE SUBCONTRACT.  In accordance with 49 CFR 26.53(f)(1) the Contractor shall not terminate a DBE subcontractor without the written consent of the DBE Liaison Officer.  This includes, but is not limited to, instances in which the Contractor seeks to perform work originally designated for a DBE subcontractor with its own forces or those of an affiliate, a non-DBE firm, or with another DBE firm.  The Contractor must give the DBE subcontractor written notice of an approved subcontract termination.

120-3.05 DEFAULT OF DBE.  If a DBE defaults on their obligation for any reason, the Contractor shall take immediate steps to retain the services of other DBEs to perform the defaulted work.  If the Contractor cannot obtain replacement DBE participation, the DBE Utilization Goal will not be adjusted.  However, the Engineer may consider the following criteria as satisfying that portion of DBE participation that cannot be replaced:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.03 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities for DBEs.

If a DBE firm defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding it.

120-4.01 DETERMINING DBE CREDIT.  The Contractor is entitle to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for Commercially Useful Function work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the Commercially Useful Function of a DBE prime contractor is 100 percent of the monies actually paid to the DBE under the Contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the Commercially Useful Function of a subcontractor is 100 percent of the monies actually paid to the DBE under the subcontract for creditable work and materials.

3.	Credit for the Commercially Useful Function of a subcontractor performing hauling/transportation is 100 percent of the monies actually paid to the DBE under the subcontractor for creditable work for those firms certified in the 100 percent credit category.  Leasing trucks from another DBE firm also qualifies for credit and must conform to the provisions of 49 CFR 26.55(d).  Credit for the Commercially Useful Function of a subcontractor performing hauling/transportation is 5 percent of the monies actually paid to the DBE under the subcontract for creditable work for those firms certified in the 5 percent credit category.

4.	Credit for the Commercially Useful Function of a manufacturer is 100 percent of the monies paid to the DBE for the creditable materials manufactured.

5.	Credit for the Commercially Useful Function of a regular dealer of a creditable material, product, or supply is 60 percent of its value.  The value is the actual cost paid to the DBE not to exceed the bid price for such item.

6.	Credit for the Commercially Useful Function of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the procurement contract for the creditable item.

7.	Credit for the Commercially Useful Function of a broker performed by a DBE certified in a bonding or insurance category is limited to a reasonable brokerage fee, not to exceed 5 percent of the premium cost.

8.	Credit for the Commercially Useful Function of a joint venture (JV) either as the prime contractor or as a subcontractor may not exceed the percent of the DBE's participation in the JV agreement, as certified by the Civil Rights Office.  The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 ACHIEVEMENT OF DBE GOALS.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A-325C as scheduled or fails to submit proof of payment, requested documentation, or otherwise cooperate with a DBE review or investigation, the Department will consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Effort to replace a DBE, regardless of fault (except for Subsection 120-3.05 item 3), the Department will also consider this unsatisfactory work.  Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06.

S97-030512

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-3.01 GENERAL.

Replace the first sentence with the following:

Clearing and grubbing are not anticipated on this project except in very limited localized areas where it is necessary to remove existing tundra vegetation to provide a level surface for timber sleepers.  Do not remove the existing tundra vegetation mat unless approved by the Engineer.  The vegetation mat shall be left intact wherever possible.

See Section 107-1.11 Protection and Restoration of Property and Landscape for migratory bird survey requirements that must occur prior to commencing construction activities.

57181-100111

Add the following:

The Contractor shall perform the work necessary to preserve and/or restore land monuments and property corners from damage.  A land monument or property corner that is disturbed shall be restored according to Section 642 at the Contractor’s expense.  An undisturbed area five feet in diameter may be left around existing monuments and property corners.  A list of land monuments and property corners is shown on the Right of Way maps.

CR107-061004

201-3.01 GENERAL.  Add the following:

Clearing and grubbing is not permitted within the migratory bird window of May 1 to July 15; except as permitted by Federal, State and local laws and approved by the Engineer.

CR2011-033012

201-4.01 METHOD OF MEASUREMENT

Delete this Subsection in its entirety and replace it with the following:

Clearing and grubbing will not be measured for payment.

201-5.01 BASIS OF PAYMENT

Delete this Subsection in its entirety and replace it with the following:

All work shall be subsidiary to Section 506 Items.

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION.  Add the following:

This work shall also include the removal of private electrical or telephone utilities, gas pipe, removal of storage tanks (either fuel or septic) and the removal and salvage of existing boardwalk and boardwalk materials.  The boardwalk shall be salvaged in sections not to exceed 10-feet in length or individual usable boards.

57181 – 120111

202-3.01 GENERAL.  Add the following:

The removal of buildings, foundations, and structures shall include removal of utility lines, staircases, railings, radio towers, satellite dishes, fuel storage tanks, wooden boardwalk, wooden piling, and other attached appurtenances as shown or indicated on the drawings.

Buildings being removed may contain asbestos.  Take special handling measures when removing this material.

Remove septic or fuel tanks according to the Department of Environmental Conservation (DEC) regulation.

All structure conflicts identified in the Structure Conflict Report  by CRW Engineering Group, LLC are intended to be removed or permitted by the Village.  If advance removal of such structure conflicts is required, coordinate with Engineer for reset location.  This work will be paid on a time and materials basis according to subsection 109-1.05 Compensation for Extra Work.

All privately owned utilities as identified in Section 105-1.06 are intended to be removed by utility owners.  If advance removal of such utility conflicts is required, coordinate with the Engineer for approval to remove utility.  This work will be paid on a time and materials basis according to subsection 109-1.05 Compensation for Extra Work.

Existing boardwalk designated to be removed shall be salvaged in sections not to exceed 10-feet in length or individual useable boards.  Salvaged sections and boards shall be neatly stacked and safely stored outside of the existing landfill fencing as shown on the Plans or in an area specified by the Engineer.  The salvaged materials shall become the property of the Native Village of Kipnuk.  Material not designated or fit for salvage shall be disposed of in the community landfill.  Obtain written permission from the Engineer prior to removing any existing boardwalks that are not shown on the Plans as designated to be removed.  Wooden piling supporting elevated boardwalk designated for removal shall be cut off at or below existing summertime grade.  See subsection 108-1.04, Limitation of Operations for restrictions on removing existing boardwalk.

57181-120111

202-4.01 METHOD OF MEASUREMENT.  Add the following:

Item 202(38).  Linear Foot.  Payment shall be made per linear foot of boardwalk removed measured along the centerline of the boardwalk, regardless of the boardwalk width.

Item 202(39), Contingent Sum.  Payment shall be made on time and materials basis according to subsection 109-1.05 Compensation for Extra Work.

57181-120111

202-5.01 BASIS OF PAYMENT.  Add the following:

Acquiring a solid waste disposal permit from DEC is subsidiary to 202 Pay Items.

CR2021-010610

Add the following:

Item 202(38).  At the Contract Unit price for the actual length of boardwalk removed and salvaged  and delivered to the designated location, regardless of the type, width, or foundation type.  Payment includes full compensation for labor and materials required to perform this work.

Payment will be made under.

Pay Item No.	Pay Item	Pay Unit

202(38)	Remove and Salvage Existing Boardwalk	Linear Foot

202(39)	Remove and Reset Structure or Remove Private Utility	Contingent Sum

57181-100111

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provision

204-1.01 DESCRIPTION.	  Add the following:

A minor structure includes boardwalk supports and foundations where installed adjacent to existing roads, trails and other earthen embankments.

57181 - 120111

Standard Modifications

204-3.01 CONSTRUCTION REQUIREMENTS.  In the first sentence of paragraph four, delete:

“bedding and”

E37-012707

Special Provisions

204-5.01 BASIS OF PAYMENT.  Delete in its entirety and replace with the following:

Excavation and backfill is subsidiary to Section 506 Items.

57181-100111

SECTION 504

STEEL STRUCTURES

Special Provisions

504-2.01 MATERIALS.

Add the following:

Stainless Steel Fasteners:

Stainless steel bolts, nuts and washers shall provide AISI 316 stainless steel and shall conform to ASTM A193, B8M Class 1 and ASTM A194, 8M.

Delete Subsection 504-3.03 in its entirety and replace it with the following:

504-3.03 FINISH.

Perform work in accordance with safety regulations and guidelines of Federal, State and local agencies having jurisdiction.  Provide surface preparation and finishes in a controlled, suitable shop environment.

Provide finish surfaces of members exposed in final structure free of markings, burrs, and other defects.  Clean foreign matter, slag and weld splatter from steel members after fabrication is complete.  Complete welding before applying finish.

Surface Preparation:

- Blast clean steel after fabrication in accordance with SSPC-SP 10, Near-White Blast Cleaning.

- Galvanized steel surfaces to be painted shall be pre-cleaned with acid etched with 1 part commercial muriatic acid reduced by 2 parts water by volume (giving an approximate 10 percent solution of hydrochloric acid).  Preparation shall produce a “grit sandpaper” surface profile for anchoring top coats.

Shop-fabricated steel components shall be hot-dipped galvanized after fabrication in accordance with Section 716-2.07, to a minimum zinc coating thickness of 2.0 oz./sf.  The finish for manufactured connectors for wood construction shall be in accordance with Section 713-2.04.

Field Touch-Up Preparation:

- Clean new steel surfaces in accordance with SSPC-SP1.

- Wire brush cleaning (SSPC-SP2), power tool cleaning (SSPC-SP3), or commercial blast cleaning (SSPC-SP6) shall be required as necessary to remove all rust before field touch-up.

- Zinc shall have contact with bare metal to provide galvanic protection.

Field Finish Repairs:  Touch-up metal that has been hot dipped galvanized with zinc spray in accordance with ASTM A780.

57181-120111

SECTION 505

PILING

Special Provisions

505-1.01 DESCRIPTION.  Add the following:

Furnish and install helical piles and helical anchors, as detailed in the Plans, including connection details.

Add the following:

Helical piles may also be referred to as Helical piers on the Plans or specifications.  No differentiation between the two terms shall be made.

Helical piles refer to the piling that supports the Type A elevated boardwalk and sign posts as shown in the Plans.  Helical anchors refer to the anchors that are installed to tie down Type A and B At-Grade boardwalk.  However, for the purposes of these specifications, installation requirements that relate to helical piles shall also relate to helical anchors unless specifically noted otherwise.

Add the following Subsection:

505–1.02 CONTRACTOR QUALIFICATIONS

Helical pile installer shall be trained and certified by helical pile manufacturer in proper methods of installation of helical piles.  The Contractor shall provide copies of certificates for on-site personnel materially involved in helical pile installation.

Add the following Subsection:

505-1.03 SUBMITTALS AND SUBSTITUTIONS.  Conform to Subsection 106-1.01.

505-2.01 MATERIALS.  Add the following:

Wire Rope			Section 709

505-3.03 PILE BEARING VALUES.  Add the following:

Drill helical piles to the minimum torques specified on the Plans.

505-3.09 DRIVING PILES. Add the following:

Contractor shall maintain records of installation for each pile installed and provide copies of records to Engineer with 24-hours after each installation is complete.  Record shall include, at a minimum, the following information:

- Name of installer.

- Date and time of installation

- Type of installation equipment (name and model)

- Location of pile (station and offset)

- Pile type and configuration (steel shape, steel type, number and location of splices , etc…)

- Duration of installation.

- Total length of installed pile.

- Cut-off elevation

- Inclination of pile.

- Field Installation Data (blows per foot, etc..)

- Rated load capacity

- Comments pertaining to interruptions, obstructions, or other relevant observations or information.

Add the following subsections:

505-3.14 DRILLING HELICAL PILES AND ANCHORS.

Contractor shall maintain records of installation for each helical pile installed and provide copies of records to Engineer with 24-hours after each installation is complete.  Record shall include, at a minimum, the following information:

- Name of installer.

- Date and time of installation

- Type of installation equipment (name and model)

- Type of torque indicator used (name and model)

- Location of helical pile (station and offset)

- Helical pile type and configuration (number and size of helix plates, number and type of extensions, etc…)

- Duration of installation.

- Total length of installed pile.

- Cut-off elevation

- Inclination of pile.

- Installation torque at intervals as indicated on the Plans

- Rated load capacity

- Comments pertaining to interruptions, obstructions, or other relevant observations or information.

Piles shall be drilled using a rotary type, hydraulic power driven torque motor with clockwise and counter-clockwise rotation capabilities.  The torque motor shall be capable of continuous adjustment to revolutions per minute (RPM’s) during installation.  Percussion drilling equipment shall not be permitted.  The torque motor shall have torque capacity 15% greater than the torsional strength rating of the central steel shaft to be installed.

Equipment used to install helical piles shall be capable of applying adequate down pressure and torque simultaneously to suit project soil conditions and load requirements.  Piles may be installed in locations with frozen or hard soil.  The equipment shall be capable of continuous position adjustment to maintain proper helical pile alignment.

A torque indicator shall be used during helical pile installation.  The torque indicator may be an integral part of the installation equipment or externally mounted in-line with the installation tooling.  The torque indicator shall be capable of providing continuous measurement of applied torque throughout the installation and shall be capable of torque measurements in increments of at least 500 ft-lbs.  The torque indicator shall be calibrated prior to beginning work by an approved testing facility or on-site in the presence of the Engineer.  Contractor shall submit on-site calibration procedures for Engineer’s approval.  The torque indicator shall be recalibrated upon request of the Engineer if the accuracy of the torque measurements is in doubt.

Helical piles shall be installed plumb at the locations shown on the Plans.  The helical pile sections shall be engaged and advanced into the soil in a smooth, continuous manner at a rate of rotation of 5 to 20 RPM’s or as specified by the pile manufacturer.  Extension sections shall be provided to obtain the required minimum installation depth and torque as shown on the Plans.  Connect sections together as specified by the pile manufacturer.  Down pressure shall be applied in a controlled manner to uniformly advance the helical pile sections so that the pile helix continuously advances into the ground along a plane matching the pitch of the helix.   The rate of rotation and magnitude of down pressure shall be adjusted for different soil conditions and depths.   Any piles where the helix does not advance along a plane matching the helix pitch (i.e. when a hole is “shaved” through hard or frozen ground) shall be rejected.

The torque as measured during the installation shall not exceed the torsional strength rating of the central steel shaft.  The minimum installation torque and minimum installation depth criteria as shown on the Plans shall be achieved prior to terminating the helical pile installation.  Pre-drilling may be needed to avoid exceeding the torsional strength rating of the helical pile shaft when permafrost or relatively unyielding soils are encountered.  Pre-drilling shall be performed using an approved bit that produces a hole with a diameter no larger than that of the helical pile shaft.  Piles that are broken or damaged during pile installation, found to be defective or improperly positioned shall be replaced by the Contractor at no additional cost to the Owner.

If the helical pile is refused or deflected by a subsurface obstruction, installation shall be terminated and the pile removed.  The Engineer shall be notified immediately.  The obstruction shall be removed, if feasible, and the helical pile re-installed.  If the obstruction cannot be removed, the helical pile shall be installed at an adjacent location, subject to review and approval of the Engineer.

If the required installation torque has been achieved and the installed depth meets or exceeds the required installation depth, the Contractor shall cut the extension of the pile shaft to the correct elevation above ground.  The Contractor shall not reverse (back-out) a helical pile to facilitate positioning the top of a pile extension to the required elevation.

Maximum variation from true location at ground surface shall be 1/2-inch after installation is completed.   Maximum variation from plumb shall be 1/2-inch inch per 10 feet, non-cumulative.

Helical piles installed with an annular separation greater than ½-inch but less than 1-inch between the riser shaft and the soil require backfilling and densification with a sand and potable water slurry. The slurry shall be an unfrozen mineral sand mixed with potable water to a fully saturated state. The slurry shall be placed in fully thawed state in the annular space in nominal 12 inch lifts and hand-densified. Hand densification shall be conducted until the slurry no longer settles within the annular space and the slurry is dense and firm. Hand densification may include rod tamping, vibrating the helical anchor riser shaft, ground surface vibration adjacent to the helical pile riser or other means developed by the contractor. The Engineer shall approve the slurry, slurry placement, and densification methods proposed by the Contractor prior to use.

If a separation greater than 1-inch is present between the helical pile riser and the soil, the Engineer must be notified and, at no additional cost to the Owner, special annular space backfill methods may be required or the helical pile removed and relocated or replaced with a larger riser shaft diameter unit.

Connect helical anchors to at-grade boardwalk with galvanized steel wire rope and secure as shown on Plans.

505-4.01 METHOD OF MEASUREMENT. Add the following:

Furnish and Drill Piles: The number of helical piles drilled in place to the minimum torque and depth as shown on the Plans and extending above grade to the required above ground elevation in the completed structure and conforming to the Contract.

Furnish and Drill Piles (Additional Depth):  The sum of the in-place lengths of helical piles in the completed structure in excess of the minimum depth as shown on the Plans and conforming to the Contract, measured along the centerline of helical piles from the tip of pile to the intersection with the minimum depth below grade.

Furnish and Drill At-Grade Boardwalk Anchor: The number of helical piles drilled in place to the minimum depth as shown on the Plans and extending to the required elevation near the ground surface as shown in the Plans and connected to the foundation supports of at-grade boardwalk.

Furnish and Drill Sign Post Foundation: The number of helical piles drilled in place to the minimum depth as shown on the Plans and extending above grade and supporting a sign post.

505-5.01 BASIS OF PAYMENT.  Delete the first two paragraphs and replace them with the following:

Furnish Piles The contract price includes Type B Elevated Boardwalk pile materials delivered to the site; pile crew time, including payroll and administrative additives; and equipment rental for the driving crane, leads and hammer. It also includes pile caps, connections and fasteners to connect piling to Type B Elevated Boardwalk.  All other costs associated with pile work are paid under Drive Piles.

Drive Piles. The contract price includes all items related to Type B Elevated Boardwalk pile work that are not included in Furnish Piles, including but not limited to: equipment movements, pile splices, cutoffs, templates, crane or work platforms, pile cleanout, jetting or drilling to specified depths, reinforcing steel, concrete fill, and other fixed or variable items. This pay item is independent of pile length and, therefore, will not change with variations from estimated pile tip elevations. No adjustment in the contract unit price for Drive Piles will be made as a result of revisions ordered to the pile tip elevations.  This pay item includes all work to connect piles to Type B Elevated Boardwalk.

Add the following:

Furnish and Drill Piles:  The contract price includes all items related to pile work necessary to provide helical piles complete and in place to the minimum depth as shown or specified in the Plans.  This work includes but is not limited to pile materials delivered to the site; pile crew time, including payroll and administrative additives; and equipment rental for installation equipment, equipment movements, helical pile extensions, equipment work platforms, installation of helical pile to minimum depth, and other fixed or variable items.  This pay item includes the portion of helical pile extending above ground regardless of length and, therefore, will not change with variations in the above grade height of elevated boardwalk.  This pay item includes all pile caps, connection fasteners and other ancillary materials necessary.

Furnish and Drill Piles (Additional Depth):  The contract price includes all items related to pile work necessary to provide helical piles below the minimum depth specified on the Plans complete and in place.  Additional depth will only be paid for when minimum torque requirements as shown on the Plans cannot be achieved at or above minimum specified depth and when previously authorized by the Engineer.  This work includes but is not limited to pile materials (helical pile extensions) delivered to the site; pile crew time, including payroll and administrative additives’ and equipment rental for installation equipment, equipment movements, equipment work platforms,  installation of helical pile below minimum depth, and other fixed or variable items.

Furnish and Drill At-Grade Boardwalk Anchor:  The contract price includes all items related to pile work necessary to provide at-grade boardwalk helical anchors complete and in place to the minimum depth as shown or specified in the Plans.  This work includes but is not limited to anchor materials delivered to site; anchor  crew time, including payroll and administrative additives; and equipment rental for installation equipment, equipment movements, helical anchor extensions, equipment work platforms, installation of helical anchor to minimum depth, and other fixed or variable items.  This pay item includes all wire rope and connectors necessary to connect helical anchors to at-grade boardwalk,  This pay items also includes all work required to drill, tap, or swage boardwalk and anchor shaft as necessary to make connections.

Furnish and Drill Sign Post Foundation:  The contract price includes all items related to pile work necessary to provide helical piles complete and in place to provide sign post foundations to the minimum depth as shown or specified in the Plans.  This work includes but is not limited to pile materials delivered to site; pile crew time, including payroll and administrative additives; and equipment rental for installation equipment, equipment movements, helical pile extensions, equipment work platforms, installation of helical pile to minimum depth, and other fixed or variable items.  This pay item includes the portion of helical pile extending above grade regardless of length and, therefore, will not change with variations in the above grade cut of height of the anchor.

Payment will be made under:

Pay Item No. 	Pay Item	Pay Unit

505(12)	Furnish and Drill Piles	Each

505(13)	Furnish and Drill Piles (Additional Depth) 	Linear Foot

505(14)	Furnish and Drill At-Grade Boardwalk Anchor	Each

505(15)	Furnish and Drill Sign Post Foundation	Each

57181 - 120111

SECTION 506

TIMBER STRUCTURES

506-1.01 	DESCRIPTION.  Add the following:  This work shall consist of furnishing materials and labor for the construction of a boardwalk system in conformance with the Plans and Specifications.  The description is as follows:

Construct primary transportation system in Kipnuk, Alaska.  This work consists of furnishing and constructing boardwalk (all types), railing, access ramps, transitions between elevated and at-grade boardwalks, snow machine crossings, and intersection wings as shown and described in the Plans and Specifications.

506-1.02		SUBMITTALS AND SUBSTITUTIONS.  Conform to Subsection 106-1.01.

506-2.01 MATERIALS.  Delete the paragraph beginning with “Bolts, Screws and Drive Spikes” and replace it with the following:

Bolts, Screws, and Fasteners.    Conform to Section 713.

Add the following:

Boardwalk Lumber, Timber, Glue-Laminated and Plywood Materials.  Conform to Section 713.

Steel Connectors for Wood Construction.  Conform to Section 713.

Transitions to Existing Grade.  Molded High Load Capacity (HLC) Grating shall be constructed of fiberglass reinforced plastic grating.  Grating shall have load bearing beams oriented in the direction of boardwalk travel with minimum thickness of 0.43-inches.  Beams and cross members shall have minimum height of 1.5-inches.  Grating shall be designed to support vehicular loads with varying support spacing depending on load.

Wire Rope & Welded Wire Fabric: Wire rope and welded wire fabric shall be in accordance with Section 709.

Sealant for Wood:   An approved sealant material shall be used to fill cavities in wood cribbing used for foundation shimming.  The sealant shall be single-component elastoplastic, containing polycarbon and polycarbonate materials which seals on contact through water and oil.  The materials shall be workable from 40°F to 90°F and applied to materials surface temperature with minimum and maximum ranges of -50°F to +200°F.  The sealant shall have a vertical & horizontal slump between the ranges of 10,000 psi to 12,000 psi per ASTM C920.

Steel Fabrications:  Steel fabrications, including transition ramp substructure, shall be fabricated as shown on the Plans and in accordance with Section 504 Steel Fabrications.

506-3.01 	GENERAL.  Delete the first paragraph and replace it with the following:  Locate boardwalk as shown on Plans or as directed by the Engineer.  All boardwalk shall be constructed within existing rights-of-way.  Contractor shall employ competent carpenters for all wood construction work.  Workmanship on all metal parts must conform to specified requirements.

506-3.02 TREATED TIMBER. Delete this Section and replace it with the following:

Fabricate lumber and timber (including all cutting, shaping, and boring) before treatment.  Handle lumber and timber carefully without dropping, breaking the outer fibers, bruising, or penetrating the surface with tools.  Use of damaged lumber and timber shall not be allowed.  Store lumber and timber on-site in the dry, above the ground and on wood dunnage.  Protect lumber from damage and weathering during shipping, storage and installation.

Before final placement of timber and driving of lag screws and bolts, treat all field cuts, holes and other modifications with an approved copper naphthenate wood preservative product according to American Wood Preservers’ Association (AWPA) M4, Standard for the Care of Preservative-Treated Wood Products.

506-3.04 HOLES FOR BOLTS, DOWELS, RODS, AND LAG SCREWS. Delete this Section and replace it with the following:

Bore holes for machine bolts and thru bolts 1/32 to 1/16 inches wider than the bolt.  Bore holes for lag screws with a bit not larger than the body of the screw at the root of the thread.

506-3.05 BOLTS AND WASHERS. Delete this Section and replace it with the following:

Use washers of the type and size specified in the Plans to protect the wood from bolt heads and nuts.

506-3.06 COUNTERSINKING. Delete this Section and replace it with the following:

Countersink bolts where smooth faces are required.  Paint recesses formed for countersinking with wood preservative product.

Add the following:

506-3.14 	BOARDWALK.  Boardwalk is intended for use primarily by all-terrain vehicles (ATVs).  The boardwalk shall be constructed in accordance with the Plans.  Timber supports and beams shall be constructed level and stable.  Decking shall be installed perpendicular to timber supports and beams and shall be level or sloped according to the Plans.  Members shall be fastened together in accordance with the Plans.

506-3.15 	RAILING.  Construct in accordance with Plans.

506-3.16 	TRANSITION RAMPS & STEEL FABRICATIONS.  Construct in accordance with Plans and Section 504 Steel Structures.

506-4.01 	METHOD OF MEASUREMENT. Delete in its entirety and substitute the following:

Boardwalk (Elevated and At-Grade, All Types).  The length of boardwalk, measured in place, along the centerline.  The Pay Item shall include all fasteners, connectors, and other ancillary materials as necessary for construction and shown on the Plans.  Where two boardwalks intersect, measurement will be along one boardwalk centerline only (primary boardwalk).  Measurement of secondary boardwalk will begin at outside edge of primary boardwalk.  Boardwalk measurement does not include transition ramps between at-grade boardwalk and elevated boardwalk.

Boardwalk Transition Ramps shall be measured per each unit installed to transition between elevated boardwalk and at-grade boardwalk as shown on the Plans and accepted in place.

Boardwalk Transition to Silt Road shall be measured per each unit installed and accepted in place.  End Transitions to Silt Road and Side Transitions to Silt Road shall both be measured as Boardwalk Transition to Silt Road.

Boardwalk Snow Machine Crossings shall be measured per each unit installed and accepted in place.

Boardwalk Leveling Timbers.  Boardwalk Leveling Timbers shall be measured per thousand board feet for completed and accepted in place and include all fasteners and other ancillary material required for construction as shown on the Plans.    One board foot is equal to 144 cubic inches of timber.  Board feet will be calculated by multiplying the nominal board dimensions in inches by the actual length of the board in inches and dividing by 144.  Waste material and timber not installed as leveling sleepers shall not be measured for payment.

Boardwalk Intersection Connections.  Boardwalk Intersection Connections shall be measured as per set of two (2) intersection connection wings at boardwalk intersections including all foundation materials and supports necessary for construction.  Intersections at elevated boardwalk shall include railing as shown on the Plans.  A tee intersection would be counted as one (1) Boardwalk Intersection Connection.  A intersection crossing (four legs) would have two (2) Boardwalk Intersection Connections.   Locations requiring only one wing at the intersection will be measured as a complete intersection.   Work includes furnishing all materials labor for all preparation, erection, and installation of the aforementioned items complete and in place.

Elevated Boardwalk Barrier will be measured per each barrier installed as shown on the Plans and accepted in place.

End of Boardwalk Transition will be measured per each transition from boardwalk to existing ground surface as shown on the Plans and accepted in place.

Limits between adjacent pay items shall be as indicated on the Plans.

Temporary access required where boardwalk has been removed shall not be measured for and shall be subsidiary to Section 506 Items.

506-5.01 BASIS OF PAYMENT.  Add the following pay items:

Pay Item No. 	Pay Item	Pay Unit

506(5)	Boardwalk, At-Grade (Type A)	Linear Foot

506 (6)	Boardwalk, At-Grade (Type B)	Linear Foot

506 (7)	Boardwalk, Elevated (Type A)	Linear Foot

506(8)	Boardwalk, Elevated (Type B)	Linear Foot

506(9)	Boardwalk Transition Ramp	Each

506(10)	Boardwalk Transition to Silt Road	Each

506(11)	Boardwalk Leveling Timbers	MBM

506(12)	Boardwalk Snow Machine Crossing	Each

506(13)	Boardwalk Intersection Connection	Each

506(14)	Elevated Boardwalk Barrier	Each

506(15)	End of Boardwalk Transition	Each

57181 -120111

- SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS.  Delete first paragraph of Item 2. Including subitems a., b., c., and replace with:

2.	Sign Fabrication.	Use Type IV reflective sheeting (for lettering symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

(1)	For temporary installations, the reflective sheeting may be placed on aluminum, plastic, or plywood sheet panels.

(2)	For flexible signs, (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Fluorescent Yellow Green School Area Signs.  Use Type VIII or Type IX reflective sheeting for background.

Reflective Sheeting Warranty.  Supply manufacturer’s warranty for reflective sheeting including retention of fluorescent yellow green (measured according to ASTM E 2301) for ten years according to the following criteria:

	Minimum Fluorescent Luminance Factor:	YF = 20%

	Minimum Total Luminance Factor:			YT = 35%

The warranty shall stipulate:  If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

CR615-061708

615-5.01 BASIS OF PAYMENT.  Add the following:

OM2-1V signs shown on elevated boardwalk railing shall be considered incidental to the project and shall not be measured for payment.

Helical piles necessary for sign post installation shall be paid for under Pay Item 505(15)

57181-120111

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION.  Add the following:  Seed new or disturbed slopes and other areas as directed by the Engineer.  Apply seed, fertilizer, and water.  Provide a living ground cover on slopes as soon as possible.

57181-120111

CONSTRUCTION REQUIREMENTS

618-3.01 SOIL PREPARATION.  Delete the fourth paragraph and replace with the following:

Roughen the surface to be seeded by grooving the soil in a uniform pattern that is perpendicular to the fall of the slope.  Use one or more of the following grooving methods with associated equipment before the application of seed:

1.	Manual raking with landscaping rakes; or

2.	Mechanical raking with a scarifying slope board.  Form one inch wide grooves spaced no more than six inches apart.

Rounding the top and bottom of slopes to facilitate raking and to create a pleasant appearance is acceptable, but disrupting drainage flow lines is not.

57181-120111

618-3.02 SEEDING SEASONS.  Replace the 1st sentence with the following:  Seed disturbed areas after permanent cessation of ground disturbing activities in that area, within the time period specified in the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) Construction General Permit (CGP) for Alaska, Section 4.4 Final Stabilization, and Section 641 Erosion, Sediment, and Pollution Control.

Seed between May 15 and August 15, or obtain written approval from the Engineer to seed at a different date.

CR6183-101711

618-3.03 APPLICATION.  Delete the first three sentences and replace with:  Seed, seeding, reseeding includes the application of seed, fertilizer and when specified or included in the Alaska Department of Natural Resources (ADNR) Revegetation Manual for Alaska, mulch.

Apply seed mix, fertilizer, and mulch at the rate specified.  If the seed mix, fertilizer and mulch are not included in the Plans or Specifications, including their application rates, use the recommendations of the ADNR and the Revegetation Manual for Alaska.

Do not seed areas of bedrock, plant beds, and areas indicated in the plans as “no seeding.”

Special Provisions

618-3.03 APPLICATION.  Add the following:  Apply seed, mulch, and fertilizer as follows.

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | ‘Nortran’ Tufted hairgrass ‘Arctared’ Red Fescue | 0.60 lbs. 0.40 lbs. Total = 1.00 lbs |
| Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

CR6181-101711

57181-120111

Replace Subsection 3.04 with the following:

618-3.04 MAINTENANCE.  Maintain seeded areas in a satisfactory condition for the term of the Contract, including warranty obligations.

Maintenance includes but is not limited to:

1.	Protecting seeded areas against traffic by approved warning signs or barricades and against erosion.

2.	Repairing surfaces gullied or otherwise damaged following seeding.  Fill and reseed erosion gullies over 4 inches deep, Subsection 618-3.01 & 3.03.  Fill the entire erosion gully to surrounding grade, including the portions less than 4 inches deep.  Reseed repaired areas.

3.	Reseeding areas not showing evidence of satisfactory growth within 3 weeks of seeding and after repairs are complete.  Reseed bare patches of soil more than 10 square feet in area.  Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.

4.	Watering seeded areas for growth of vegetative cover.  If in the opinion of the Engineer, too little or too much water is being applied, adjust the amount of water as directed.

Add Subsections 618-3.05:

618-3.05 ACCEPTANCE.  The Engineer will perform a visual inspection of the vegetative mat considering each station and each side of the road a separate area.  Acceptance of the vegetative mat requires a minimum of 70% cover density in the inspection area, gullies repaired and reseeded, and no bare patches of soil more than 10 square feet in area.

Repair/reseed areas that are not accepted.

Add Subsection 618-3.06:

618-3.06 PERIOD OF ESTABLISHMENT.  For each area accepted, the establishment period extends one complete growing season following the date of acceptance.  Employ all possible means to preserve/maintain the new vegetative mat in a healthy and vigorous condition to ensure successful establishment.  Maintain the vegetative mat, according to Subsection 618-3.04, to not less than the requirements for acceptance, Subsection 618-3.05.

618-4.01 METHOD OF MEASUREMENT.  Delete the 3rd paragraph, "Seeding by the Pound," and replace with:

Seeding by the Pound. By the weight of dry seed acceptably seeded and maintained.

Add the following:

M Gal is equal to 1000 gallons.

618-5.01 BASIS OF PAYMENT.  Delete the 1st sentence:  "Mulching will be paid for under Section 619".

Delete paragraphs beginning: “Seeding by the Acre” and “Seeding by the Pound” and replace with:

Seeding by the Acre.  Pay Item 618(1), Seeding:  Payment is for established vegetative mat.  Surface preparation and materials (seed, fertilizer, and the water required for all hydraulic applications) are subsidiary.  Maintenance including:  1. Protection, 2. Repairs, 3. Reseeding, is also subsidiary.  Repairs and reseeding include, but are not limited to:  fill, surface preparation, seed, fertilizer, and the water required for hydraulic application.

Seeding by the Pound.  Pay Item 618(2), Seeding:  Payment is for established vegetative mat.  Sufrace preparation and materials (seed, fertilizer, and the water required for all hydraulic applications) are subsidiary.  Maintenance including:  1. Protection, 2. Repairs, 3. Reseeding, is also subsidiary.  Repairs and reseeding include, but are not limited to:  fill, surface preparation, seed, fertilizer, and the water required for hydraulic application.

Add new pay description:

Water for Seeding.

	Water for hydraulic application is subsidiary to Pay Items 618(1) and 618(2), and includes, but is not limited to:  the initial application of seed and fertilizer and the reapplication for repairs and reseeding.

	Water applied for growth of vegetative mat (Subsection 618-3.04.4 Watering), for the term of the Contract, including warranty obligations, is paid under Pay Item 618(3).

57181-120111

SECTION 622

REST AREA FACILITIES

Special Provisions

Add the following:

622-3.08	TREATED TIMBER CURB

Treated timber curbs shall be installed at locations where the decking of the constructed boardwalk has an elevation higher than 18-inches above final grade adjacent to the boardwalk.  Except for locations where curbing is specifically called for in the Plans, actual installed locations requiring curbing will be determined in the field by the Engineer after construction of typical at-grade boardwalk section.  Where required, Contractor may be directed to install curbing on one or both sides of the boardwalk.

57181-120111

SECTION 634

GEOGRID SOIL REINFORCEMENT

Special Provisions

634-2.01 MATERIALS.  Add the following:

Rigid Geogrid:

- Dark Gray to Black Polyethylene.

- Geogrid shall be supplied in modular units that can be interlocked together to provide ground cover below timber supports.

- Geogrid cells shall be open to allow vegetation to grow through and around mats.

- Manufacturer: Geoblock 2 Porous Pavement System by Presto Products Company, Perfo-SD Interlocking Ground Reinforcement Tiles by Perfo-UK or approved equal.

634-3.02 SURFACE PREPARATION. Add the following:

- Tundra:  Install rigid geogrid directly on tundra mat.  Level large hummocks as necessary to provide a level and stable surface.   Minimize tundra disturbance.

634-3.03 GEOGRID PLACEMENT. Add the following:

- Tundra:  Place rigid geogrid as shown on the drawings.  Install in complete panels.

634-4.01 MEATHOD OF MEASUREMENT. Delte this subsection in its entirety and replace it with the following:

At the contract lump sum price for all work related to furnishing and installing rigid geogrid.

634-5.01 BASIS OF PAYMENT.  Add the following:

Materials used to fill ruts and holes and the work to level hummocks to make level surface for geogrid is subsidiary to the Rigid Geogrid pay item.

Progress payments for lump sum price of Rigid Geogrid shall be based on percentage of overall project installed complete and accepted in place as determined by the Engineer.

Payment will be made under:

Pay Item No. 	Pay Item	Pay Unit

634(2)	Rigid Geogrid	Lump Sum

57181-120111

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01 DESCRIPTION.  Add the following:

Construct Boardwalk Tie-Ins as shown on the Plans.  Reconstruct 5-feet, or to right-of-way if less than 5-feet, of existing boardwalk to transition between existing and new boardwalk grades.

Construct Special Residential Access at locations and as shown on the plans.  Special Residential Access include relocation and reconstruction of existing decking, railing, stairways, doorways and other related items as shown or indicated on the Plans.

639.2.01 MATERIALS. Delete the first sentence and replace it with the following:

Use materials that conform to Section 506 and as shown on the Plans.

639-3.01 CONSTRUCTION.   Add the following:

Construct Boardwalk Tie-Ins and Special Residential Accesses as shown on Plans.  Contractor shall provide temporary access within 24-hours of blocking access to existing boardwalk or residences.  Temporary access shall be approved by the Engineer and shall meet requirements of ADA and IBC and shall remain in place until permanent access is constructed.

639-4.01 METHOD OF MEASUREMENT.  Add the following:

Boardwalk Tie-Ins shall be measured for payment per each tie-in constructed as shown on the Plans or as directed.  Where an existing boardwalk crosses a proposed boardwalk and tie-ins are required on both sides of the proposed boardwalk, two (2) tie-ins will be measured.  Materials used for construction of the tie-in (timbers, fasteners, etc...) shall not be measured separately for payment and shall be considered subsidiary.

Special Residential Access will be measured for payment per each location where special access is required as indicated on the Plans.  The per each measurement shall include all decking, railing, stairways, fasteners and other materials as necessary to provide a complete and functional access way to the residence as shown on the Plans.  Demolition, removal and disposal of existing decking and stairways is subsidiary to the Special Residential Access pay item.

639-5.01 BASIS OF PAYMENT.  Add the following pay items:

Payment will be made under:

Pay Item No. 	Pay Item	Pay Unit

639(3)	Boardwalk Tie-In	Each

639(4)	Special Residential Access	Each

57181-120111

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modification

640-1.01 DESCRIPTION.  Add the following:

6.	Comply with the Alaska Department of Labor and Workforce Development (DOLWD) requirements for Worker Meals and Lodging, or Per Diem; as described in their September 1, 2009 memo WHPL #197 (A3) and the State Laborer’s and Mechanic’s Minimum Rates of Pay (current issue). On Federal-aid projects, PL 109-59, 119 STAT. 1233, Sec. 1409(c) also applies.

Ensure subcontractors comply with the Federal and State DOLWD requirements.

Ensure facilities meet the Alaska Administrative Code 8 AAC 61.1010 and 8 AAC 61.1040 Occupational Safety and Health Standards, 18 AAC 31 Alaska Food Code, and U.S. Code of Federal Regulations 29 CFR Section 1910.142 Temporary Labor Camps.

Do not consider the cost of Meals and Lodging, or Per Diem in setting wages for the worker or in meeting wage requirements under AS 23.10.065 or AS 36.05.

640-4.01 METHOD OF MEASUREMENT.  Delete the numbered paragraph 3 and substitute the following:

3.	The remaining balance of the amount bid for Mobilization and Demobilization will be paid after all submittals required under the Contract are received and approved.

Add the following:

4.	Progress payments for Worker Meals and Lodging, or Per Diem will be computed as equivalent to the percentage, rounded to the nearest whole percent, of the original Contract amount earned.

640-5.01 BASIS OF PAYMENT.  Add the following Pay Item:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

640(4)	Worker Meals and Lodging, or Per Diem	Lump Sum

E89-052810

- Special Provision

- Replace Section 641 with the following:

- SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION.

Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this section and applicable local, state, and federal requirements, including the Construction General Permit.

641-1.02 DEFINITIONS.

These definitions apply only to Section 641.

Active Treatment System Operator. The Contractor’s qualified representative who is responsible for maintaining and operating an active treatment system (as defined in the CGP) for storm water runoff.

Alaska Certified Erosion and Sediment Control Lead (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years.

Alaska Department of Environmental Conservation (ADEC). The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

Alaska Pollutant Discharge Elimination System (APDES). A system administered by ADEC that issues and tracks permits for storm water discharges.

Best Management Practices (BMPs). Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or minimize the discharge of pollutants to waters of the United States. BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leaks, sludge or waste disposal, or drainage from material storage.

Clean Water Act (CWA). Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

Consent Decree. The decree entered by the United States District Court for the District of Alaska on September 21, 2010, regarding compliance with the CWA and implementation of the CGP, to which the United States and the Department are parties.

Construction Activity. Physical activity by the Contractor, Subcontractor, or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. Construction Activity includes soil disturbing activities (e.g. clearing, grubbing, grading, excavating); and establishment of construction materials or equipment storage or maintenance areas (e.g. material piles, borrow area, concrete truck chute washdown, fueling); and industrial activities that may discharge storm water and are directly related to the construction process (e.g. concrete or asphalt batch plants).

Construction General Permit (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by ADEC. It authorizes stormwater discharges provided permit conditions and water quality standards are met.

Corp of Engineers Permit (COE Permit). A U.S. Army Corp of Engineers Permit for construction in waters of the US. Such permit may be issued under Section 10 of the Rivers and Harbors Act of 1899, or Section 404 of the Clean Water Act.

Electronic Notice of Intent (eNOI). The electronic Notice of Intent submitted to ADEC, to obtain coverage under the CGP.

Electronic Notice of Termination (eNOT). The electronic Notice of Termination submitted to ADEC, to end coverage under the CGP.

Environmental Protection Agency (EPA). A federal agency charged to protect human health and the environment.

Erosion and Sediment Control Plan (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

Final Stabilization. Is defined in this section as it is defined in the CGP.

Hazardous Material Control Plan (HMCP). The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

Inspection. An inspection required by the CGP or the SWPPP, usually performed together by the Contractor’s SWPPP Manager and Department’s Stormwater Inspector.

Municipal Separate Storm Sewer System (MS4) Permit. An ADEC storm water discharge permit issued to certain local governments and other public bodies, for operation of storm water conveyances and drainage systems. See CGP for further definition.

Multi-Sector General Permit (MSGP). The Alaska Pollutant Discharge Elimination System General Permit for storm water discharges associated with industrial activity.

Operator(s). The party or co-parties associated with a regulated activity that has responsibility to obtain permit coverage under the CGP.  ”Operator” for the purpose of the CGP and in the context of storm water associated with construction activity, means any party associated with a construction project that meets either of the following two criteria:

1.	The party has operational control over construction plans and specifications, including the ability to make modifications to those plans and specifications; or

2.	The party has day to day operational control of those activities at a project which are necessary to ensure compliance with a SWPPP for the site or other permit conditions (e.g. they are authorized to direct workers at a site to carry out activities required by the SWPPP or comply with other permit conditions).

Pollutant. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

Project Zone. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Department by the Contract and are directly related to the Contract.

Material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

Records. Any record, report, information, document, or photograph required to be created or maintained pursuant to the requirements of the Consent Decree, the CGP, the CGP storm water requirements of the Clean Water Act; and applicable local, state, and federal laws and regulations regarding document preservation.

Spill Prevention, Control, and Countermeasure Plan (SPCC Plan). The Contractor’s detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

Spill Response Field Representative. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

Storm Event. A rainfall event that produces more than 0.5 inch of precipitation in 24 hours and that is separated from the previous storm event by at least 3 days of dry weather.

Storm Water Pollution Prevention Plan (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project Zone, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but is not limited to, amendments, records of activities, inspection schedules, and reports, qualifications of key personnel, and all other documentation, required by the CGP and this specification, and other applicable local, state, and federal laws and regulations.

Storm Water Pollution Prevention Plan Two (SWPPP2). The Contractor’s detailed project specific plan to comply with CGP or MSGP requirements, for Contractor construction-related activities outside the Project Zone.

Subcontractor Spill Response Coordinator. The subcontractor’s representative with authority and responsibility for coordinating the subcontractor’s activities in compliance with the HMCP and SPCC Plan.

Subcontractor SWPPP Coordinator. The subcontractor’s representative with authority to direct the subcontractor’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the subcontractor’s compliance with the SWPPP.

Superintendent. The Contractor’s duly authorized representative in responsible charge of the work.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

SWPPP Amendment. A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP Manager. The Contractor’s qualified representative who conducts Inspections, updates SWPPP records, and has authority to suspend work and to implement corrective actions required for CGP compliance.

SWPPP Preparer. The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

Utility Spill Response Coordinator. The Utility’s representative with authority and responsibility for coordinating the Utility’s activities in compliance with the HMCP and SPCC Plan.

Utility SWPPP Coordinator. The Utility’s representative with authority to direct the Utility’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the Utility’s compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS.

For plans listed in Subsection 108-1.03.5 (SWPPP and HMCP) use the Contractor submission and Department review deadlines identified in Subsection 641-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1.	Storm Water Pollution Prevention Plan. Submit an electronic copy and three hard copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize and bind the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14 day review period will restart when the contractor submits an electronic copy and three hard copies of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved by the Department, the Contractor must sign and certify the approved SWPPP. See Item 4 for further SWPPP submittal requirements.

2.	Hazardous Material Control Plan.  Submit an electronic copy and three hard copies of the HMCP, as an appendix to the SWPPP, to the Engineer for approval. The HMCP submittal and review timeline, and signature requirements are the same as the SWPPP.

3.	Spill Prevention, Control, and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and three signed hard copies of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

4.	CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. Do not use the SWPPP for Construction Activities outside the Project Zone where the Department is not an operator.  Use a SWPPP2 for Construction Activities outside the Project Zone.

After Department approval of the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to ADEC for coverage under the Construction General Permit (CGP). Submit a copy of the signed eNOI and ADEC’s written acknowledgement (by letter or other document), to the Engineer as soon as practicable and no later than three days after filing eNOI or receiving a written response.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to ADEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and ADEC’s written acknowledgment (by letter or other document), for inclusion in the SWPPP.

Before Construction Activities occur, transmit to the Engineer an electronic copy of the approved and certified SWPPP, with signed Delegations of Signature Authorities, SWPPP Certifications, both permittee’s signed eNOIs and ADEC’s written acknowledgement.

5.	Ending CGP Coverage. Submit an eNOT to ADEC within 30 days after the Engineer has determined the conditions listed in Subsection 641-3.01.6 have been met. Submit a copy of the signed eNOT and ADEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response.

6.	ADEC SWPPP Review. When CGP Part 2.1.3, requires ADEC SWPPP review:

a.	Transmit a copy of the Department-approved SWPPP to ADEC using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation; and

c.	Retain a copy of delivery receipt confirmation in the SWPPP.

7.	Local Government SWPPP Review. When local government or the CGP Part 2.1.4, requires local government review:

a.	Transmit a copy of the Department-approved SWPPP and other information as required to local government, with the required fee.  Use delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation;

c.	Transmit a copy of any comments by the local government to the Engineer within seven days of receipt;

d.	Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven days of receipt of the comments;

e.	Include a copy of local government SWPPP review letter in the SWPPP; and

f.	File a notification with local government that the project is ending.

8.	Modifying Contractor’s eNOI. When required by The CGP Part 2.7, modify your eNOI to update or correct information. Reasons for modification include a change in start or end dates, small changes in number of acres to be disturbed, change in decision to use or not use treatment chemicals, or change in location of SWPPP Records.

The Contractor must submit an eNOT and then submit a new eNOI instead of an eNOI modification when: the operator has changed, the original eNOI indicates disturbed area less than five acres and the project will disturb more than five acres, or a project over five disturbed acres grows by more than 50%.

641-1.04 PERSONNEL QUALIFICATIONS.

Provide documentation in the SWPPP that the individuals serving in these positions meet the personnel qualifications.

The SWPPP Preparer must meet at least one of the following qualifications:

a.	Current certification as a Certified Professional in Erosion and Sediment Control (CPESC);

b.	Current certification as AK-CESCL, and at least two years experience in erosion and sediment control, as a SWPPP Manager or SWPPP writer, or equivalent. Provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement; or

c.	Professional Engineer registered in the State of Alaska with current certification as AK-CESCL.

For Projects disturbing more than 20 acres, the SWPPP Preparer must also have completed a SWPPP Preparation course.

The Superintendent must meet the following qualifications:

a.	Current certification as AK-CESCL; and

b.	Duly authorized representative, as defined in the CGP, Appendix A, Part 1.12.3.

The SWPPP Manager must have current certification as AK-CESCL and must meet the CGP experience, training, and authority requirements identified for the Storm Water Lead and Storm Water Inspector positions as defined in the CGP, Appendix C, Qualified Person.

The Active Treatment System (ATS) operator must have current certification as AK-CESCL, and be knowledgeable in the principals and practices of treatment systems in general, and the operation of the project-specific ATS. The ATS operator must have at least three months field experience with ATS, or completion of an ATS manufacturer’s training course, or completion of system operator's certification course.

The Department accepts people having any of the following certificates as equivalent to AK-CESCL, if the certificates are current according to the sponsoring organization’s policies:

a.	CPESC, Certified Professional in Erosion and Sediment Control; or

b.	CISEC, Certified Inspector in Sediment and Erosion Control.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT. The eNOI and eNOT must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12.2. Signature and certification authority for the eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports. Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Superintendent position is responsible for signing and certifying the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI and eNOT.

The Engineer will provide the Department’s delegation Form 25D-107, which the Contractor must include in the SWPPP.

3.	Subcontractor Certification. Subcontractors must certify that they have read and will abide by the CGP and the conditions of the project SWPPP.

4.	Signatures and Initials. Handwrite signatures or initials on CGP documents and SWPPP forms, wherever a signature or initial is required.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

1.	The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

2.	The Contractor is responsible for permitting and permit compliance outside the Project Zone. The Contractor has sole responsibility for compliance with ADEC, COE and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

3.	An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.3) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

4.	The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas outside the Project Zone;

b.	For Construction Activity and Support Activities outside the Project Zone; and

c.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY.

Relocation Coverage. A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06.  The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work.  Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

1.	SWPPP Preparer and Pre-Construction Site Visit.

Use a SWPPP Preparer to develop the SWPPP and associated documents, according to the requirements of the CGP and COE permit. The SWPPP Preparer must put their name, qualifications (including the expiration date of any certifications), title and company name in the SWPPP.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least seven days notice of the site visit, so that the Department may participate.

During the pre-construction inspection, the SWPPP Preparer must identify, or if a draft of the SWPPP has already been prepared verify that the SWPPP fully addresses and describes:

- Opportunities to phase construction activities;

- Appropriate BMPs and their sequencing; and

- Sediment controls that must be installed prior to beginning Construction Activities.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, including the names of attendees and the date.

2.	Developing the SWPPP.

Use the Department’s ESCP, Environmental commitments, and other Contract documents as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.

Develop the SWPPP with sections and appendices, according to the current DOT&PF SWPPP template. Include information required by the Contract and the CGP.

Obtain the following forms after they have been completed by the Department and include them in the SWPPP:

	SWPPP Delegation of Signature Authority – DOT&PF (25D-107)

	SWPPP Certification for DOT&PF (25D-109)

	SWPPP Delayed Action Item Report (25D-113)

Use the following Department forms for recording information in the SWPPP:

	SWPPP Amendment Log (25D-114)

	SWPPP Certification for Contractor (25D-111)

	SWPPP Construction Site Inspection Report (25D-100)

	SWPPP Corrective Action Log (25D-112)

	SWPPP Daily Record of Rainfall (25D-115)

	SWPPP Delegation of Signature Authority – Contractor (25D-108)

	SWPPP Grading and Stabilization Activities Log (25D-110)

	SWPPP Pre-Construction Site Visit (25D-106)

	SWPPP Project Staff Tracking (25D-127)

	SWPPP Subcontractor Certification (25D-105)

	SWPPP Training Log (25D-125)

SWPPP Template and Forms are available online at:

http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix.

3.	SWPPP Considerations and Contents.

The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone. Construction activity outside the Project Zone must have permit coverage, using a separate SWPPP2, and separate Contractor Inspections.

The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity, and identify the areas:

a.	Over which each operator has operational control; and

b.	Where the Department and Contractor are co-operators.

For work outside the Project Zone, the SWPPP must identify the entity that has stormwater permit coverage, the operator, and the areas that are:

a.	Dedicated to the Project and where the Department is not an operator; and

b.	Not dedicated to the project, but used for the project.

Develop the SWPPP according to the requirements of the CGP and this specification. Account for the Contractor’s construction methods and phasing. Identify the amount of mean annual precipitation.

Comply with the CGP Part 1.4 .2 Allowable Non-Storm Water Discharges. List locations where authorized non-storm water will be used, including the types of water that will be used on-site.

Include the Department’s Antidegradation Analysis in the SWPPP if storm water from the Project Zone discharges into receiving water that is considered high quality water and that constitutes an outstanding national resource, according to CGP Part 2.1.5.

There are special requirements in the CGP Part 3.2, for storm water discharges into an impaired water body, and they may include monitoring of storm water discharges. For Projects meeting the permit criteria, the Department will initiate a monitoring program for the storm water within the Project Zone, and will provide the required information and reports for inclusion in the SWPPP. The Contractor is responsible for monitoring and reporting outside the Project Zone.

Preserve natural topsoil unless infeasible. Delineate the site according to CGP Part 4.1.  Use stakes, flags, or silt fence, etc. to identifying areas where land disturbing activities will occur and areas that will be left undisturbed. Minimize the amount of soil exposed during Construction activity according to CGP Part 4.1.2.

Comply with CGP Part 4.3, requirements for dewatering for trenches and excavations.

The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed.

Describe methods and time limits, to initiate temporary or permanent soil stabilization. For areas with mean annual precipitation of:

a.	40 inches or less, initiate stabilization as soon as practicable and within 14 days; or

b.	Greater than 40 inches, initiate stabilization as soon as practicable and within seven days.

Within seven days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete.

Include in the “Stabilize Soils” section of the SWPPP, a description of how you will minimize the amount of disturbed and unstabilized ground in the fall season. Identify anticipated dates of fall freeze-up and spring thaw. Describe how you will stabilize areas when it is close to or past the seasonal time of snow cover or frozen conditions, and before the first seasonal thaw. Include a plan for final stabilization.

Plans for Active Treatment Systems must be submitted to DEC for review at least 14 days prior to their use and the Operator of the ATS identified in the SWPPP. Any use of treatment chemicals must be identified on the NOI.

The SWPPP must provide designated areas for equipment and wheel washing, equipment fueling and maintenance, chemical storage, staging or material storage, waste or disposal sites, concrete washouts, paint and stucco washouts, and sanitary toilets. These activities must be done in designated areas that are located, to the extent practicable, away from drain inlets, conveyance channels, and waters of the US. No discharges are allowed from concrete washout, paint and stucco washout; or from release oils, curing compounds, fuels, oils, soaps, and solvents. Equipment and wheel washing water that doesn’t contain detergent may be discharged on-site if it is treated before discharge.

Design temporary BMPs for a 2 year 24 hour precipitation amount. Describe BMPs in the SWPPP and in SWPPP Amendments, including source controls, sediment controls, discharge points, and temporary and permanent stabilization measures. Describe the design, placement, installation, and maintenance of each BMP, using words, and drawings as appropriate. Describe the design capacity of sediment basins (including sediment ponds and traps). Provide a citation to the BMP Manual or publication used as a source for the BMP, including the title of the BMP Manual or publication, the author (individual or agency), and date of publication. If no published source was used to select or design a BMP, then the SWPPP or SWPPP amendment must state that “No BMP manual or publication was used for this design.”

Describe the sequence and timing of activities that disturb soils and of BMP implementation and removal. Phase earth disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization quickly. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities.

Identify the inspection frequency in the SWPPP:

•	For areas where the mean annual precipitation is 15 inches or less, inspect at least once every 14 days during construction and within 24 hours of the end of a storm event that resulted in a discharge.

•	For areas where the mean annual precipitation is between 15 to 40 inches, inspect once every seven days.

•	For areas where the mean annual precipitation is 40 inches or greater, inspect twice every seven days.

Linear Project Inspections, described in CGP Part 6.5, are not applicable to this project.

The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, COE permit, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities which were not included in the Department’s permitting and consultation.

The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the Consent Decree, CGP and this specification. See Subsection 641-3.03 for more information.

4.	Recording Personnel and Contact Information in the SWPPP.

Identify the SWPPP Manager as the Storm Water Lead and Storm Water Inspector positions in the SWPPP. Document the SWPPP Manager’s responsibilities in Section 2.0 Storm Water Contacts, of the SWPPP template and:

a.	Identify that the SWPPP Manager does not have authority to sign inspection reports (unless the SWPPP Manager is also the designated project Superintendent).

b.	Identify that the SWPPP Manager cannot prepare the SWPPP unless the SWPPP Manager meets the Contract requirements for the SWPPP Preparer.

Include in the SWPPP, Records of the AK-CESCL cards or certificates for the Superintendent and SWPPP Manager, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced permanently or temporarily, by an acting Superintendent or acting SWPPP Manager, record in the SWPPP (use Form 25D-127) the names of the replacement personnel, the date of the replacement. For temporary personnel record their beginning and ending dates.

Provide 24 hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24 hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, Records of the AK-CESCL cards or certificates of ATS operators. Record the names of ATS operators and their beginning and ending dates, on Form 25D-127.

The Department will provide Records of AK-CESCL cards or certificates for the Project Engineer, Stormwater Inspectors, and Monitoring Person (if applicable), and names and dates they are acting in that position. Include the Department’s Records in the SWPPP Appendix.   Include the department’s Storm Water Inspector and Storm Water Monitoring Person (if applicable) in section 2.0 of the SWPPP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.

Prepare the HMCP for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

Designate a Contractor’s Spill Response Field Representative with 24 hour contact information. Designate a Subcontractor Spill Response Coordinator for each subcontractor. The Superintendent and Contractor’s Spill Response Field Representative must have 24 hour contact information for each Subcontractor Spill Response Coordinator and the Utility Spill Response Coordinator.

List and give the location and estimated quantities of hazardous materials (Including materials or substances listed in 40 CFR 117 and 302, and petroleum products) to be used or stored on the Project. Hazardous materials must be stored in covered storage areas.  Include secondary containment for all hazardous material storage areas.

Identify the locations where fueling and maintenance activities will take place, describe the activities, and list controls to prevent the accidental spillage of petroleum products and other hazardous materials. Controls include placing absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc). Spill response materials must be stored in sufficient quantity at each work location, appropriate to the hazards associated with that site.

Describe procedures for containment and cleanup of hazardous materials.  Describe a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Describe a plan for dealing with contaminated soil and water encountered during construction. Clean up spills or contaminated surfaces immediately.

Describe methods of disposing of waste petroleum products and other hazardous materials generated by the Project, including routine maintenance.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Describe methods of complying with the requirements of AS 46.04.010-900, Oil and Hazardous Substances Pollution Control, and 18 AAC 75. Include contact information for reporting hazardous materials and petroleum product spills to the Project Engineer and reporting to federal, state, and local agencies.

641-2.03 SPILL PREVENTION, CONTROL, AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.

Prepare and implement an SPCC Plan when required by 40 CFR 112; when both of the following conditions are present on the Project:

a.	Oil or petroleum products from a spill may reach navigable waters (as defined in 40 CFR 112); and

b.	Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons).

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project. The Superintendent shall sign and certify the SWPPP, Inspection Reports, and other reports required by the CGP, except the NOI and NOT. The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP submitted under Subsection 641-1.03.1, Inspection Reports, and other reports required by the CGP.

The Superintendent may assign certain duties to the SWPPP Manager those duties may include:

a.	Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

b.	Ensuring the control of erosion, sedimentation, or discharge of pollutants;

c.	Directing and overseeing installation, maintenance, and removal of BMPs;

d.	Performing Inspections; and

e.	Updating the SWPPP including adding amendments and forms.

When Bid Item 641(7) is part of the Contract, the SWPPP Manager must be available at all times to administer SWPPP requirements, and be physically present within the Project Zone or the project office, for at least eight hours per day when construction activities are occurring.

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of this Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, environmental commitments, and historic preservation commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS.

Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

Use the temporary seed mixture specified by special provision, or use annual rye grass if no temporary seed mix is specified.

Use soil stabilization material as specified in Section 727.

Use silt fences as specified in Section 729.

Use straw that is certified as free of noxious weed by the United States Department of Agriculture, Natural Resources Conservation Service, Local Soil, and Water Conservative District. Alaska Weed Free Forage Certification Program must be used when available. Hay may not be substituted for straw.

Use Oregon Scientific RGR126 wireless rain gauge with temperature, or Taylor 2751 Digital Wireless Rain Gauge with Thermometer, or approved equivalent.

641-2.06 CONTRACTOR REQUIREMENTS.

The Contractor must be familiar with the requirements of the CGP and Consent Decree because Contractor’s employees will be conducting duties that relate to compliance with the CGP and the Consent Decree. A copy of the Consent Decree is available on the Department’s Statewide Environmental Office web page.

641-3.01 CONSTRUCTION REQUIREMENTS.

Comply with the SWPPP and the requirements of the CGP.

1.	Before Construction Activity may Begin.

The following actions must be completed before Construction Activity begins:

a.	The SWPPP Preparer must visit the Project, the visit must be documented in the SWPPP, and the SWPPP must be developed (or amended) with findings from the visit;

b.	The SWPPP must be approved by the Engineer;

c.	The Contractor must be authorized to begin by the Engineer;

d.	The Project eNOIs for the Department and for the Contractor, as well as any other eNOIs if there are additional operators, must be listed as Active Status on the ADEC website;

e.	The Department approved SWPPP must be submitted to ADEC and Local Government (when required); and

f.	The Contractor has transmitted to the Engineer an electronic copy of the approved SWPPP.

You may begin Winter Construction activity according to CGP Part 4.10.3, provided actions a through c above is completed before winter construction activity begins.

Post notices containing the following information:

a.	Copy of all eNOIs related to this project;

b.	Name and 24 hour phone number of SWPPP Manager; and

c.	Location of the SWPPP.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes.

Install an outdoor rain gauge in per manufacturer’s guidance in a readily accessible location on the Project.

Delineate the site for both land disturbing activities and areas that will be left undisturbed. Install sediment controls and other BMPs that must be placed prior to the initiation of Construction Activity.

2.	During Construction.

Before subcontractors or utility companies begin soil disturbing activities, provide to them copies of applicable portions of the SWPPP, and require them to sign a SWPPP Subcontractor Certification, Form 25D-105. Include SWPPP Subcontractor Certifications as an appendix to the SWPPP. Ensure subcontractors and utility companies understand and comply with the SWPPP and the CGP. Inform subcontractors and utility companies of SWPPP amendments that affect them in a timely manner. Coordinate with subcontractors and utility companies doing work in the Project Zone so BMPs, including temporary and permanent stabilization are installed, maintained, and protected from damage.

Provide on-going training to employees and subcontractors, on control measures at the site and applicable storm water pollution prevention procedures. Training must be specific to the installation, maintenance, protection, and removal of control measures. Training must be given at a frequency that will be adequate to ensure proper implementation and protection of control measures, and no less frequently than once a month during construction activity. Document on the SWPPP Training Log. Form 25D-125, the dates, and attendees to these trainings. Include the SWPPP Training Log as an appendix to the SWPPP.

Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

Comply with Subsection 107-1.11 Protection and Restoration of Property and Landscape. Concrete washout must be fully contained.

Fuel the equipment in designated areas. Place absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

Comply with requirements of the HMCP and SPCC Plan, and all local, state, and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

Keep the SWPPP and HMCP current (refer to Subsection 641-2.01.3, SWPPP Considerations and Contents).

3.	Pollutant and Hazardous Materials Reporting Requirements.

If there has been an incident of non-compliance with the CGP that may endanger health or the environment, immediately report the incident to ADEC according to the CGP, Appendix A, Part 3.0. Notify the Engineer immediately and to the extent possible coordinate reports to ADEC with the Engineer.

The report must include:

a.	A description of the noncompliance and its causes;

b.	The exact dates and times of noncompliance;

c.	If not yet corrected the anticipated time the project will be brought back into compliance; and

d.	The corrective action taken or planned to reduce, eliminate and prevent reoccurrence.

If there has been an incident of non-compliance with COE Permits, then notify the Engineer immediately of the non-compliance.

Report spills of petroleum products or other hazardous materials to the Engineer and other agencies as required by law. Use the HMCP and SPCC Plan (if available) for contact information to report spills to regulatory agencies.

4.	Corrective Action and Maintenance of BMPs.

Implement maintenance as required by the CGP, SWPPP, and manufacturer’s specifications, whichever is more restrictive.

Implement corrective action:

a.	If an incident of non-compliance with the SWPPP or CGP is identified;

b.	If an Inspection or the Engineer identifies the SWPPP or any part of the SWPPP is ineffective in preventing erosion, sedimentation or the discharge of pollutants;

c.	If a required BMP was not installed according to the SWPPP schedule or phasing, or was installed incorrectly, or was not installed according to the CGP Part 4.0;

d.	If a BMP is not operating as intended, has not been maintained in an effective operation condition, or is unable to effectively perform the intended function;

e.	If a prohibited discharge of pollutants, as specified in CGP Part 4.6, is occurring or will occur; or

f.	If there is accumulation of sediment or other pollutants, that is in or near any storm water conveyance channels, or that may enter a discharge point or storm sewer system. If there is accumulation of sediment or other pollutants that is being tracked outside the project zone.

Implement corrective actions so that they comply with the following time requirements:

a.	For conditions that are easily remedied (i.e. removal of tracked sediment, maintenance of control measure, or spill clean-up), initiate corrective action within 24 hours and complete as soon as possible;

b.	For all other conditions, meet both requirements:

(1)	Corrective action is completed in time to protect water quality; and

(2)	Corrective action is completed no later than the Complete-by-Date that was entered in an Inspection Report (see Subsection 641-3.03.2 for more information).

If a corrective action is not implemented within the time requirements of this section, document the situation in the SWPPP, notify the Engineer, and implement corrective action as soon as possible.

If a corrective action could affect a subcontractor, notify the subcontractor within three days of taking the corrective action. Require in your written subcontract, that subcontractors must notify the Contractor within 24 hours of becoming aware of a condition that requires a corrective action.

5.	Stabilization.

Stabilization may be accomplished using temporary or permanent measures. Initiate stabilization of disturbed soils, erodible stockpiles, disposal sites, and of erodible aggregate layers so that all of the following conditions are satisfied:

a.	As soon as practicable;

b.	As soon as necessary to avoid erosion, sedimentation, or the discharge of pollutants; and

c.	As identified in the SWPPP.

Land may be disturbed and stabilized multiple times during a project. Coordinate work to minimize the amount of disturbed soil at any one time. Do not disturb more soil than you can stabilize with the resources available.

Temporarily stabilize from wind and water erosion portions of disturbed soils, portions of stockpiles, and portions of disposal sites, that are not in active construction. Temporary stabilization measures may require a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, non-erodible cover,  dust palliatives, or other approved methods.

When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community, the hydro-seeder must be located at the project.

Before applying temporary or permanent seeding, prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover. Apply seed and maintain seeded areas. Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

Apply permanent seed according to Sections 618 and 724, within the time periods allowed by the CGP and the contract, at locations where seeding is indicated on the plans and after land-disturbing activity is permanently ceased.

When installing a culvert or other drainage structure where stream bypass is not used, install temporary or permanent stabilization concurrently or immediately after placing the culvert or drainage structure in a manner that complies with the SWPPP, applicable project permits and prevents discharge of pollutants. Install temporary and permanent stabilization:

a.	At the culvert or drainage structure inlet and outlet; and

b.	In the areas upstream and downstream, that may be disturbed by the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure.

Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install permanent stabilization:

a.	At the inlet and outlet of the culvert, drainage structure, or bridge;

b.	In the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge; and

c.	Under the bridge.

Within seven days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete.

6.	Ending CGP Coverage and BMP Maintenance.

The Engineer will determine the date that all the following conditions for ending CGP coverage have been met within the Project Zone:

a.	Land disturbing activities have ceased;

b.	Final Stabilization has been achieved (including at Department furnished material sources, disposal sites, staging areas, equipment areas, etc.); and

c.	Temporary BMPs have been removed.

After the Engineer has determined the conditions for ending CGP coverage have been met, the Department will:

a.	Send written notice to the Contractor with the date that the conditions were met;

b.	Submit an eNOT to ADEC; and

c.	Provide a copy of the eNOT and ADEC’s acknowledgement letter to the Contractor.

The Contractor is responsible for ending permit coverage within the Project Zone, by submitting an eNOT to ADEC within 30 days of meeting the conditions for ending CGP coverage. The Contractor is responsible for BMP maintenance and SWPPP updates until permit coverage is ended.

If the Contractor’s CGP eNOI acreage includes Support Activities and any other areas where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must amend the SWPPP and separate SWPPP2(s), to indicate the Department’s CGP coverage has ended, and the Department is no longer an Operator within the Project Zone.

The Contractor must indicate in the SWPPP the areas that have reached Final Stabilization, and the dates land disturbing activities ended and Final Stabilization was achieved. The Contractor must submit an eNOT to ADEC, and insert copies of the Department’s and the Contractor’s eNOTs with ADEC’s acknowledgement letters in the appendix of the SWPPP.

The Contractor must submit a copy of each signed eNOT and ADEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response.

The Contractor is responsible for coordinating local government inspections of work and ending permit coverage with local government. See Subsection 641-1.03.5 for more information.

7.	Transmit final SWPPP.

Transmit one copy of the final SWPPP, including all amendments, appendices, and maps, to the Engineer; when the project eNOTs are filed, or within 30 days of the Department’s eNOT being filed, whichever is sooner. Transmittal must be by both electronic and hard copy.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.

The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP and the Consent Decree. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP, and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown.  Update on-site postings if records are relocated during winter shutdown. Provide the Department with copies of all Records.

Retain Records and a copy of the SWPPP, for at least three years after the date of eNOT. If EPA or ADEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the retention period expires, retain the SWPPP and all Records related to the SWPPP and CGP until at least three years after EPA and/or ADEC has determined all issues related to the investigation  are settled.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them.  See CGP Parts 5.10, 6.6 and 9.4.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.

Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP.  Update SWPPP Corrective Action Log, SWPPP Amendment Log, SWPPP Grading and Stabilization Activities Log, and SWPPP Daily Record of Rainfall forms. For active projects, update the Records daily.

1.	Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s Stormwater Inspector jointly, unless impracticable. For this paragraph, “impracticable” means when both inspectors must fly to a remote area in the winter or when one inspector is sick or unable to travel to the site due to weather.  When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within three days of the Inspection date and document the date of the report transmittal.

2.	Inspection Reports.

Use only the DOT&PF SWPPP Construction Site Inspection Report, Form 25D-100 to record Inspections. Changes or revisions to Form 25D-100 are not permitted; except for adding or deleting data fields that list: Location of Discharge Points and Site Specific BMPs. Complete all fields included on the Inspection Report form; do not leave any field blank.

Unless otherwise directed by the Engineer, insert a Complete-by-Date for each corrective action listed that complies with:

a.	In time to protect water quality;

b.	less than seven calendar days after the date the inspection was performed; and

c.	before the next scheduled inspection.

Provide a copy of the completed, unsigned Inspection Report to the Engineer by noon on the day following the inspection.

The Superintendent must review, correct errors, and sign and certify the Inspection Report, within three days of the date of Inspection. The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. Deliver the signed and certified Inspection Report to the Engineer on the same day the Superintendent signs it.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days.

The Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

If subsequent corrections to the certified Inspection Report are needed, document the corrections in an addendum that addresses only the omitted or erroneous portions of the original Inspection Report. The Superintendent and the Engineer must both sign and certify the addendum.

3.	Inspection before Seasonal Suspension of Work.

Conduct an Inspection before seasonal suspension of work to confirm BMPs are installed and functioning according to the requirements of the SWPPP and CGP.

4.	Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

Inspection frequency may be reduced to at least one Inspection every 30 days if approved by the Engineer and the entire site is temporarily stabilized.

When work is suspended due to freezing conditions, the Engineer may suspend inspection requirements after fourteen days of freezing conditions if:

a.	Soil disturbing activities are suspended; and

b.	Soil stabilizing activities are suspended.

Inspections must resume according to the normal inspection schedule identified in the SWPPP, at least 21 days before anticipated spring thaw.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall during seasonal suspension of work.  If so, resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in runoff.  Resume recording land disturbance and stabilization activities on the Grading and Stabilization Activities Log when Construction Activity resumes.

5.	Stabilization before Seasonal Thaw.

Construction Activities within the Project Zone must be stabilized with appropriate BMPs prior to seasonal thaw. Seasonal thaw is the annual (first) recurrence of snow and ice melting after a prolonged period of freezing conditions.

6.	Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion.

7.	Items and Areas to Inspect.

Conduct Inspections of the areas required by the CGP and SWPPP.

8.	SWPPP Amendments and SWPPP Amendment Log.

The Superintendent and the SWPPP Manager are the only persons authorized to amend the SWPPP and update the SWPPP Amendment Log, Form 25D-114. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

a.	Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

b.	If an Inspection identifies that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

c.	Whenever an Inspection identifies a problem that requires additional or modified BMPs

d.	Whenever a BMP is modified during construction or a BMP not shown in the original SWPPP is added;

e.	If the Inspection frequency is modified (note beginning and ending dates); or

f.	When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01.4.

Do not record removal of BMPs as amendments to the SWPPP. See Subsection 641-3.03.9 for documenting removal of BMPs.

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than seven days following identification of the need for an amendment.  Every SWPPP Amendment must be signed and dated. Cross-reference the amendment number with the Corrective Action Log or SWPPP page number, as applicable. When a BMP is modified or added, describe the BMP according to Subsection 641-2.01.3.

Keep the SWPPP Amendment Log current. Prior to performing each scheduled Inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log as an appendix to the SWPPP.

9.	Site Maps.

Document the installation, routine maintenance, and removal of BMPs by making notes on the SWPPP Site Maps. Include the date and the recording person’s initials by these notes. Identify areas where Construction Activities begin, areas where Construction Activities temporarily or permanently cease, and areas that are temporarily or permanently stabilized.

10.	Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112. Document the need for corrective action within 24 hours of either:

a.	Identification during an inspection; or

b.	Discovery by the Department’s or Contractor’s staff, a subcontractor, or a regulatory agency inspector.

Modification or replacement of a BMP, installation of a new BMP not shown in the original SWPPP, or overdue maintenance (after sediment accumulated in sediment basins (including sediment traps and ponds) exceeds 50% of design capacity; or after sediment accumulates to more than half the above ground height on silt fences, check dams, or berms) is a corrective action and must be documented on the Corrective Action Log. Do not record removal of BMPs on the Corrective Action Log.

Within 24 hours of discovery, update the Corrective Action Log with the date of discovery and proposed corrective action. If discovered during an inspection, update log with inspection date and proposed corrective actions noted on the Inspection Report.

After the corrective action has been accomplished, note in the Corrective Action Log the action taken and if a SWPPP amendment was needed. Date and initial the entry.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log as an appendix to the SWPPP.

11.	Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection. Keep the Grading and Stabilization Activities Log organized and completed to demonstrate compliance with the CGP Part 4.4.

Keep the Grading and Stabilization Activities Log as an appendix to the SWPPP.

12.	Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled Inspection.  Keep the Daily Record of Rainfall as an appendix to the SWPPP.

641-3.04 FAILURE TO PERFORM WORK.

The Engineer has authority to suspend work and withhold monies, for an incident of non-compliance with the CGP, Consent Decree, or SWPPP, that may endanger health or the environment or for failure to perform work related to this Section 641. If the suspension is to protect workers, the public, or the environment from imminent harm, the Engineer may orally order the suspension of work. Following an oral order of suspension, the Engineer will promptly give written notice of suspension. In other circumstances, the Engineer will give the Contractor written notice of suspension before suspension of work. A notice of suspension will state the defects or reasons for a suspension, the corrective actions required to stop suspension, and the time allowed to complete corrective actions.

If the Contractor fails to take the corrective action within the specified time, the Engineer may:

a.	Suspend the work until corrective action is completed;

b.	Withhold monies due the Contractor until corrective action is completed;

c.	Assess damages or equitable adjustments against the Contract Amount; and

d.	Employ others to perform the corrective action and deduct the cost from the Contract amount.

Reasons for the Engineer to take action under this section include, but are not limited to, the Contractor’s failure to:

a.	Obtain appropriate permits before Construction Activities occur;

b.	Perform SWPPP Administration;

c.	Perform timely Inspections;

d.	Update the SWPPP;

e.	Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms to the Engineer;

f.	Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

g.	Perform duties according to the requirements of this Section 641; or

h.	Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control.

No additional Contract time or additional compensation will be allowed due to delays caused by the Engineer’s suspension of work under this subsection.

641-3.05 ACCESS TO WORK.

The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies. See CGP Part 6.6.

641-4.01 METHOD OF MEASUREMENT.

Section 109 and as follows:

Item 641(1), 641(3) and 641(7), are lump sum.

Items 641(2), 641(4) and 641(5), will be measured on a contingent sum basis as specified by the Directive authorizing the work.

Item 641(6) will be measured on a contingent sum basis with withholding determined by the Department.

TABLE 641-1 BMP VALUES - (Reserved)

Liquidated Damages assessed according to Table 641-2 are not an adjustment to the Contract amount. These damages charges are related to Contract performance but are billed by the Department independent of the Contract amount. An amount equal to the Liquidated Damages may be withheld for unsatisfactory performance, from payment due under the Contract, until the Contractor remits payment for billed Liquidated Damages.

TABLE 641-2 Version B

EROSION, SEDIMENT, AND POLLUTION CONTROL – LIQUIDATED DAMAGES

| Code | Specification Subsection Number and Description | Deductable Dollars | Cumulative Deductable Dollars |
| --- | --- | --- | --- |
| A | 641-1.04 Failure to have a qualified (AK-CESCL or equivalent) Superintendent or SWPPP Manager | Calculated in Code B or F |  |
| B | Failure to meet SWPPP requirements of: - 641-2.01.1 Name of SWPPP Preparer and Date of Pre-Construction Inspection - Not Applicable - 641-3.03.8 Sign and Date SWPPP amendments with qualified person. 641-2.01.4 SWPPP Include approving person’s name and AK-CESCL expiration date. (4) 641-3.02 Records maintained at project and made available for review | $750 per omission |  |
| C | 641-2.01.3 and 641-303.8 Failure to either reference a BMP manual or publication, or state that no BMP manual or publication was used | $250 per omission |  |
| D | 641-3.03.5 Failure to stabilize a Project prior to Seasonal Thaw | $5,000 per Project per year |  |
| E | 641-2.01.1 Failure to conduct pre-construction inspections before Construction Activities | $2,000 per Project |  |
| F | 641-3.03. Failure to conduct and record CGP Inspections 641-3.03.1 Personnel conducting Inspections and Frequency 641-3.03.2 Inspection Reports, use Form 25D-100, completed with all required information according to the Consent Decree paragraph 7.c, parts (1) through (11) | $750 per Inspection |  |
| G | 641-3.01.4 Failure to timely accomplish BMP maintenance and/or repairs, In effect until BMP maintenance and/or repairs is completed. | $500 per Project per day | Not to exceed $250,000 per year for all projects |
| H | 641-3.01.3 Failure to provide to the Engineer and ADEC a timely oral endangerment report of violations or for a deficient oral endangerment report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| I | 641-3.01.3 Failure to provide to the Engineer and ADEC a timely written endangerment report of violations or for a deficient written endangerment report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| J | 641-3.04 Failure to comply with the most restrictive requirements of the CGP, approved SWPPP, or Section 641, except as listed above | $750 per occurrence for the first day of noncompliance | Additional $750 for every day the deficiency remains uncorrected |

641-5.01 BASIS OF PAYMENT.

See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

Item 641(1) Erosion, Sediment, and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and Record keeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Item 641(2) Temporary Erosion, Sediment, and Pollution Control. At the contingent sum prices specified for all labor, supervision, material, equipment, and incidentals to install, maintain, remove, and dispose of approved temporary erosion, sedimentation, and pollution control BMPs required to implement the SWPPP and SPCC Plan.

Item 641(6) Withholding. The Engineer may withhold an amount equal to Liquidated Damages, assessed according to Section 641, from payment due the Contractor. Liquidated Damages for violations of the Contract, CWA, CGP, or Consent Decree are determined by the Engineer according to Table 641-2. The Engineer may withhold payment due the Contractors until the Contractor pays the Liquidated Damages to the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Subsidiary Items. Temporary erosion, sediment, and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641(1) Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641.

This work includes but is not limited to:

a.	Dewatering;

b.	Shoring;

c.	Bailing;

d.	Permanent seeding;

e.	Installation and removal of temporary work pads;

f.	Temporary accesses;

g.	Temporary drainage pipes and structures;

h.	Diversion channels;

i.	Settling impoundment; and

j.	Filtration.

Permanent erosion, sediment, and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense. Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion, Sediment, and Pollution Control Administration	Lump Sum

641(2)	Temporary Erosion, Sediment, and Pollution Control	Contingent Sum

641(6)	Withholding	Contingent Sum

CR641-041312

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-3.01 GENERAL.  Add No. 11:

11.	Before work on the project starts, stake and reference the existing centerline on the right side of the boardwalk alignment.  Stake the existing centerline on tangents at 50 ft.  Stake sign locations at proper offset.  Stakes shall be a minimum of 1" x 2" x 2'-0" and be offset 4 to 8 ft from the edge of boardwalk on the right side of the boardwalk.  Extend lath stakes a minimum of 2 ft above ground.  Show the offset distance to centerline and the station from the beginning of the project.  Maintain staking until the final boardwalk construction is completed.  Staking accuracy work requires an electronic distance measuring instrument (DMI) be installed in the Contractor's vehicle.  Calibrate the DMI to boardwalk alignments as stationed in the Plans before beginning work.  Record the calibration and staking information in the field book.

57181 -120111

Standard Modifications

642-3.04 OFFICE ENGINEERING.  Delete third sentence and replace with:

Perform the work by, or under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor or a Professional Engineer.

E53-050107

- SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION.  Add the following:

Additional work:

	Illuminate construction activities listed in Table 643-3, Night Work Illumination Level, and Area of Coverage, during hours of night work on boardwalk open to the public inside the project limits.

57181-100111

643-1.02 DEFINITIONS. Add the following paragraphs after paragraph titled “Construction Phasing Plan”:

Balloon Light:  Light surrounding’s by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The top half of the balloon enclosure shall be constructed of an opaque material.

Night Work:  Work occurring between sunset and sunrise on all days.

Add the following paragraph after paragraph titled “Traffic Control Zone”:

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following:

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

Add the following:

643-1.04 WORKSITE SUPERVISOR.

1.	Qualifications. Replace with the following:

Qualifications.  The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements.  The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, your proposed operations, and certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this Section.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

CR6432-110410

2.	Duties.  Add the following:

I.	Supervise lighting of Night Work.

ES14-031506

Add No. 3:

3.	Authority.	The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-2.01 MATERIALS.

13.	Plastic Safety Fence.  Replace a., b., and c. with the following:

a.	"Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306.  Phone (800) 428-8185.

b.	"Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108.  Phone (800) 648-7916.

c.	"Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104.  Phone (800) 662-6338.

CR6432-110410

Add No. 18:

18.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

CR6431-032611

Standard Modification

Replace Subsection 643-2.02 CRASHWORTHINESS with the following:

643-2.02 CRASHWORTHINESS.  Submit documentation, by the method indicated, that the following devices comply with the requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or Manual for Assessing Safety Hardware (MASH), Test Level 3 on the given schedule.

Submit documentation of compliance to the Engineer before installing devices on the project.

| Work Zone Traffic Control Device Compliance with NCHRP 350 or MASH |  |  |
| --- | --- | --- |
| Category | Devices | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | Manufacturer's Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in category 1 | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |
| 3 | Truck mounted attenuators, redirective and nondirective temporary crash cushions | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |
|  | Portable concrete barriers | FHWA acceptance letter specifying the Test Level required in the Plans or Specifications. |

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3.  This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

| Device | Composition | Weight | Height |
| --- | --- | --- | --- |
| Cones | Rubber | 20 lb. | 36 in. |
|  | Plastic | 20 lb. | 48 in. |
| Candles | Rubber | 13 lb. | 36 in. |
|  | Plastic | 13 lb. | 36 in. |
| Drums | Hi Density Plastic | 77 lb. | 36 in. |
|  | Lo Density Plastic | 77 lb. | 36 in. |
| Delineators | Plastic or Fiberglass | N/A | 48 in. |

E77-100410

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as you, an employee, or a subcontractor becomes aware of the accident.

E90-100410

Standard Modification

Replace Subsection 643-3.03 PUBLIC NOTICE with the following:

643-3.03 PUBLIC NOTICE.  Make sure the Worksite Traffic Supervisor gives a minimum of 3 days notice before major changes, delays, or boardwalk closures to local tribal officials and transportation organizations, including but not necessarily limited to:

	Kipnuk Tribal Office

	Health Clinic

	Water & Sewer Haul Operators

- Lower Kuskokwim School District

Provide notice as required by utility companies before repairing or replacing a utility.

57181-092211

643-3.04 TRAFFIC CONTROL DEVICES.  Replace paragraphs 6 and 7 with the following:

Use only traffic control devices that meet the requirements of the "Acceptable" category in the American Traffic Safety Services Association (ATSSA) "Quality Guidelines for Temporary Traffic Control Devices" and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project.  Stock repair parts for each Temporary Crash Cushion used on the project.  Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware.  All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the Plans, Specifications, and approved TCPs until permanent roadside safety hardware is installed.  All temporary roadside safety hardware shall meet NCHRP 350 or MASH, Test Level 3 unless otherwise noted.

CR6432-110410

643-3.05 AUTHORITY OF THE ENGINEER.  Replace the first sentence with:

When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice.  A written notice will follow the oral notice according to Subsection 105-1.01, Authority of the Engineer.

Add the following after the second sentence:

In no case shall this time exceed 24 hours.

CR6431-032611

643-3.06 TRAFFIC PRICE ADJUSTMENT.

Delete the third paragraph and replace it with the following:

Adjustment Rates are listed in Table 643-1.  These rates are liquidated damages which represent boardwalk user costs.  The Engineer will use the rate shown regardless of the amount of impacted traffic on the boardwalk.

Add the following after the 3rd paragraph:

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, Adjustment Rates, for the time the boardwalk or pedestrian facility is in an unacceptable condition.

Replace Table 643-1 with the following:

TABLE 643-1

ADJUSTMENT RATES

Dollars/Minute of Delay

$2

Add the following Subsection 643-3.10:

643-3.10 LIGHTING OF NIGHT WORK.  Illuminate the night work areas specified in Table 643-3, Night Work Illumination Level, and Area of Coverage, to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

TABLE 643-3

NIGHT WORK ILLUMINATION LEVEL AND AREA OF COVERAGE

| Type of Work/Equipment | Lighting Configuration |
| --- | --- |
| Installation of Helical Piles, H-Piles and Boardwalk construction | At least one balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the boardwalk beyond the flagger and the other on the left side of the boardwalk in front of the flagger. |

Use balloon lighting as the main light sources.  Do not use floodlights without prior approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents.  Locate, aim louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to provide the lighting equipment specified in Table 643-3 or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operations that require illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they do not interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibrations.

Ensure ground, trailer, and equipment mounted light towers are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-3.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of at least 20 emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Provide NCHRP 350-compliant breakaway bases for post mounted electroliers located within the clear zone.

57181-120111

Standard Modification

Add the following Subsection 643-3.11:

643-3.11 HIGH VISIBILITY GARMENTS.  Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise).  Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottoms at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to requirements in this Subsection, 643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

7.	Condition.  Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.  Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic Pay Items.

E90-100410

643-4.01 METHOD OF MEASUREMENT.

2.	Traffic Control Device Items.  Replace the second sentence with the following:

Special Construction signs are measured by the total area of legend bearing sign panel, as determined under Subsection 615-4.01 and compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-4.

57181-100111

643-5.01 BASIS OF PAYMENT.

- Flagging and Pilot Car.  Add the following:

The Engineer will pay for Item 643(15) Flagging on a Contingent Sum basis at the rate of $50.00/hr.  The Engineer does not require a change order or directive for the flagging pay item.  Flagging associated with Change Order work will be paid at prices according to Subsection 109-1.05 Compensation for Extra Work.

11.	Traffic Control.  Add the following:

The Engineer does not require a change order/directive for Pay Item 643(25), Traffic Control.

57181-120111

Standard Modification

Add No. 16:

16.	Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items.

ES14-031506

Add No. 17:

17.	High Visibility Garments.  Payment for high visibility garments for workers is subsidiary to other Pay Items.

TABLE 643-4

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $28.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Watering | M-Gallon | $25.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |

Replace Pay Item 643(15) with the following:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

CR6431-032611

- SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:

Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

6.	Provide engineering communication services to the field office, Subsection 644-2.08.

7.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

8.	Located within 3 miles of the project.

9.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

10.	Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

57181-120111

Standard Modification

644-2.05 VEHICLES.

Add the following:

Utility Vehicle (UTV).

Model Year	Three or less model years old

Good Condition

Body:	All original parts, straight, no rust, broken plastic or fiberglass, minor dings, chips, working head and tail lights

Frame:	Original factory condition, (Includes roll cage and bumpers)

Mechanical & Elec	Condition would not preclude manufacture warranty coverage

(actual warranty coverage is not required)

Tires/Rims	All purpose tires, less than 1/3 tread wear, straight rims

Seating	Side-by-side, buckets or bench, 2 person seating

Engine & Electrical

Type		4-cycle gas, liquid cooled, electronic fuel injection

Displacement	450 cc minimum, 20 hp minimum

Fuel Capacity	6 gallons, minimum

Ignition Type	Solid state 12V – electronic, keyed

Drive System

4WD	On-demand true four-wheel drive system

Front/Rear Differential	Auto-locking, 4 wheel shaft drive

Transmission	Automatic, dual range forward/reverse

Transaxle	Two speed

Brakes	Front/rear hydraulic disk

Park Brake	Mechanical, hand operated

Suspension

Front	Independent with Struts

Rear	Independent with coil over shock

Occupant Protective Sys (OPS)	Tubular overhead structure, passenger grab handles

Seat Belts	3-point seat belts

Certification	ROPS standards (Rollover Protective Structure)

All Weather Cab	Enclosed with hard top, storage glove box

Sound Rating@ Op Ear	87-90 dB

Tires	Dia. 25x, 14 psi max (fully loaded), all purpose

Wheelbase/Tread Centers	1.75 maximum, 12 inch min ground clearance

Towing Capacity	1300 lb, include hitch, ball mount and ball

Payload Capacity	1400 lbs

Cargo Box	Steel, 43L x 46W x 9D, 10 cu ft, 400 lb min, hinged tailgate,

cargo restraint system

Safety Lights	Safety Lights	Vertically extended operable rotating amber beacon or

strobe light.  SAE Spec. Class 1 or 2, J845 – 360 Rotating Lights or J1318 Flashing Strobe Lights.  Mount beacon to be visible at eye level at all times inside a 60 ft radius about the equipment, day or night.

Manufacturers:	Whelen Engineering Company,	Public Safety Equipment (PSE),

Federal Signal,	Or Approved Equal

UTV(s) meeting these specifications include, but are not limited to:

Polaris	Ranger 4x4	Kawasaki	Mule 4010 4x4

Honda	Big Red	John Deere	Gator HPX 4x4, or

Yamaha	Rhino 700	Approved Equal

Typical vehicle requirements including but not limited to: fuel, preventative maintenance, maintenance, and insurance apply to the UTV.

Submittal:  Submit the UTV vehicle and accessory specifications including photos of the UTV to the Engineer and receive approval prior to providing the vehicle for use.

CR644UTV-033111

Standard Modifications

Add the following new subsection:

644-2.06 STORAGE CONTAINER.  Furnish, transport, and maintain a weather tight, lockable, steel enclosed 20 foot long X 8 foot wide X 8 foot high wooden floored container for the storage of the Department’s materials, supplies and testing equipment (but not nuclear equipment). Provide twenty equally spaced fastening points on the interior walls that are capable of securing the Department’s contents.  Door opening dimensions of the storage container shall be greater than 60 square feet.  Supply necessary equipment to lift and move container with minimal disturbance to the Department’s contents.  The container shall not be moved by skidding or hook lift.  The Contractor shall be listed as the shipper on documents listing and acknowledging receipt of the Department’s goods for shipment.

Deliver an empty and clean container to the Regional Materials Laboratory, or location acceptable to the Engineer, three weeks before transporting to the project site.  Allow 7 days for the Department to load the container.  Transport the loaded container to the project site.  Set up container at a location approved by the Engineer prior to commencing construction work.

1.	Provide electrical service and other facilities as follows:

a.	Electrical current, 120V (ac), 60 cycle on a 24 hour a day basis.

b.	Wiring system to support a 20 amp user load demand.

c.	2 GFI protected outlets conveniently spaced on the interior walls.

d.	Four 100 watt incandescent or eight 40 watt fluorescent lights located for maximum illumination.

e.	Provide a stairway with railing, built to meet the International Building Code, if there is more than 12-inch difference in floor entry and existing ground elevation.

Return the container to the Regional Materials Laboratory or location acceptable to the Engineer, upon project completion.  Allow 7 days for the Department to unload the container.  The storage container remains your property after completing the work.

E44-012707

Add the following subsection:

644-2.07 ENGINEERING COMMUNICATION.  Engineering Communications, minimum service includes:

a.	Three phone/facsimile lines (different phone numbers for each line)

b.	High speed internet service with modem (DSL or Cable)

CR644FOCOM-080511

644-3.01 METHOD OF MEASUREMENT. Delete the third paragraph and substitute the following:

Vehicle (UTV). For each vehicle provided. If a replacement vehicle is necessary, no additional measurement will be made.

CR644UTV-033111

Standard Modification

Add the following Pay Item:

Storage Container.  By the number of storage containers specified, to including components, installed and accepted as completed units and ready for materials and equipment storage.

E44-012707

644-4.01 BASIS OF PAYMENT.  Add the following:

Pay Item 644(9B) Vehicle (UTV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(9B)	Vehicle (UTV)	Each

CR644UTV-033111

Add the following:

Pay Item 644(10) Engineering Communications.  Usage services including long distance calls made by State personnel and the Internet service provider will be paid by the State.  Payment for communication usage services shall be based on paid receipts to the service provider plus 15%.

Connection fees (initial connection) local calls, providing equipment and disconnection are subsidiary to Pay Item 644(1) Field Office and as such are paid by the Contractor.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(10)	Engineering Communications	Contingent Sum

CR644FOCOM-080511

Standard Modifications

Add the following Pay Items:

Lump Sum Items. Payment for lump sum items will be made as follows:

1.	A percentage of the lump sum amount, to be determined by the Engineer, will be paid as full compensation for furnishing the facility at the site.

2.	The balance of the lump sum amount will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, providing all utilities, and for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Storage Container.  At the Contract unit price to including labor, materials, tools, equipment and supplies required to deliver the storage shed to the regional office for loading, to deliver it to the project office, to install it before beginning construction, to maintain it for the duration of the project, to remove the shed and electrical service after project completion, to deliver it to the regional office for unloading, and to remove the storage shed.  Electrical service and utility costs are subsidiary to this item.

Add to Pay Items:

Pay Item No.	Pay Item	Pay Unit

644(14)	Storage Container	Each

E44-012707

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this Subsection with the following:

Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete No. 2.

2.	60-Day Preliminary Schedule.

Delete the first sentence of No. 3. Schedule Updates.  and substitute the following:

Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

CR261-121302

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Raised Markers as shown on the Plans and as directed.

670-2.01 MATERIALS. Add the following:

Raised Markers shall be White Raised Pavement Markers in accordance with the following:

- High-Impact plastic housing conforming to ASTM D788 Grade 8.

- Dual white prismatic reflective lenses.

- Minimum 3.25 square inches of reflective area per side.

- Manufacturer: Hy-Viz Incorporated, or approved equal.

670-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:

5.	Raised Markers:

a.	Install as shown on the Plans.

670-5.01 BASIS OF PAYMENT.  Add the following:

All work related to furnishing and installing Raised Markers, including hardware, shall subsidiary to Section 506 Pay Items Boardwalk At-Grade, Types A & B and Boardwalk, Elevated Types A & B.

57181-120111

Special Provisions

Add the following new Section:

SECTION 671

SPEED HUMPS

671-1.01 DESCRIPTION.

Furnish, locate and install speed humps as shown on the Plans and as directed.

671-2.01 MATERIALS.

Speed humps shall be made of molded rubber material to the dimensions shown on the plans.  Humps shall be modular in form so field cutting to match required dimensions is not required.  End cap transitions shall be installed at boardwalk edges.  Humps shall have molded high visibility yellow warning strips.  Speed hump sections shall utilize tongue and groove type system to connect individual sections.

Speed humps shall be 2-ft Traffic Calming Speed Hump as manufactured by Speed Bumps and Humps, or approved equal.

671-3.01 CONSTRUCTION REQUIREMENTS.

Follow manufacturer’s recommended instruction when installing speed humps.  Install humps at locations shown in the plans.  Use minimum 4-inch long 3/8-inch diameter lag screws to secure humps to boardwalk.  Fasteners shall be in accordance with Section 506.

670-4.01 METHOD OF MEASUREMENT.

Rubber Speed Humps shall be measured per each speed hump location installed and accepted in place in accordance with the Plans.  One speed hump location consists of two center units and 2 end cap units installed across the boardwalk as shown on the Plans.  Three additional speed humps (2 center units and 2 end cap units for each speed hump) shall be provided to community for future installation.  Speed humps provided to community will be measured the same as if installed.

670-5.01 BASIS OF PAYMENT.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

671(1)	Rubber Speed Hump	Each

57181-100111

Add the following Section:

- SECTION 681

ELECTRICAL

681-1.01 DESCRIPTION.

All work performed on electrical facilities and assemblies located outside of structures shall be performed in accordance with these specifications and consist of the tasks listed on the plans and specified herein.

Furnish and install and/or modify one or more electrical service risers as specified and shown on the plans.  Electrical service risers are located at the structure being served by the electrical utility.

Furnish and install and/or modify one or more service drop as specified and shown on the plans.   Electrical service drops are located at the utility pole providing service to a structure.

Relocate existing pole as shown on the plans.

Remove existing and set new guys and helical pile anchors as shown on the plans.

681-1.02 RELATED SECTIONS.  (Reserved)

681-1.03 REFERENCES.

- Code of Federal Regulations (CFR)	http://ecfr.gpoaccess.gov

- Title 7: Agriculture.  Part 1728-Electric Standards and Specifications for Materials and Construction

- United States Department of Agriculture (USDA)

a.	Rural Development Utilities Programs

- LIST OF MATERIALS Acceptable for Use on Systems of USDA Rural Development Electrification Borrowers. 	http://www.rurdev.usda.gov/SupportDocuments/lom110707.pdf

- Bulletin 1728F-700	http://www.usda.gov/rus/electric/regs/FRversionF-700.pdf

- Bulletin 1728F-804 	http://www.rurdev.usda.gov/SupportDocuments/UEP_Bulletin_1728F-804.pdf

- National Electrical Code (NEC)

- National Electrical Safety Code (NESC)

- Underwriters Laboratories (UL)

681-1.04 SUBMITTALS.

1.	Equipment List(s) and Drawings.  Within 30 days after the Contract award, submit 3 collated copies of a portfolio of equipment and materials proposed for installation to the Department for review and approval.  Include a table of contents in the portfolio(s) that includes each item's intended use(s) and the following:

- Catalog cuts that include the manufacturer's name, type of product, size, model number, conformance specifications, and other data as may be required, including manufacturer's maintenance and operations manuals, or sample articles.

- Incidental materials incorporated into the work (such as roof jacks, guy wires, nuts, ties, bolts, washers, etc.) must meet all applicable specifications and be installed per all manufacturer's recommendations. Certification is not needed unless required by the Special Provisions or requested by the Engineer.

- See 681-1.03.a.1 for the web address for the RUS equipment list.

2.	As-builts.  Provide as-builts of each complete installation to the Engineer.  Provide a printed and e-copy to the Engineer; include a printed copy and e-copy for each utility and the Department.

681-2.01 MATERIALS.

Use materials that conform to the NEC (materials listed or labeled by an agency acceptable to the State of Alaska Department of Labor Mechanical Inspections Division (i.e.: U/L, FM, ETL, CSA-US)), NESC and the USDA Rural Development Utilities Program.

Conductors	Stranded copper, Type XHHW-2 or RHW insulation

Service drop cable, duplex and triplex AL, AWG per

Conduit	Rigid galvanized steel conduit meeting UL standard UL-6 Galvanized Metal	Galvanize steel materials according to Section 716-2.07

Repair	AASHTO M 36

Primary Cable	ACSR #2 AWG

New Pole 	Class 5, 40’

Stub Pole	Class 5, treated

Support Components	Galvanized components as required per RUS guide drawings.

Helical Pile	See Section 550 for specification requirements.

681-3.01 CONSTRUCTION REQUIREMENTS.

Provide installations as shown on the drawings, noted in the specifications and according to the requirements of the Rural Development Utilities Program including the codes and standards referenced in the program documents and in the project specifications.

- Utilities.  Coordinate all work with the electrical and telephone utilities. Contact Sam Carl, Kipnuk Light Plant Manager, @ 907-896-5427 to coordinate inspection and power outages.  Contact Aaron Dygas, OSP Construction Manager UUI, @ 907-529-8112 to coordinate telephone. UUI will be relocating telephone services.

- Planned Power Outage.

  - Request, from utility(s), each outage 24 hrs before the planned event.

  - Notify users, in the affected area, 24 hrs before the planned event.

  - Utility personnel are required to be in attendance to restore power, in case of an emergency.

- Qualifications.  All work on the services performed per this specification under this contract shall be performed by State of Alaska licensed journeymen electricians or Linemen (depending on work) under the supervision of an Alaska licensed Electrical Administrator in accordance with the latest legally adopted version of the National Electrical Code or National Electrical Safety Code as amended.

- Demolition.  Provide demolition of existing materials, where shown in plans and included in the specifications, and when required for item installation.  Where not shown in the plans notify the engineer and receive written approval prior to beginning demolition.

- Service Riser.  Where shown in the drawings adjust service riser to raise service to minimum 12’ height above proposed boardwalk. Shall include all demolition, installation of new riser, weatherhead, riser cables, supports, roof jack, guy cable and shackles and will be considered complete only after required service drop elevation at the boardwalk is verified and installation inspected and approved by the Engineer and local Utility and service has been declared ready for energization. Actual energization is outside the control of the Contractor and is not a criteria for completion. All other material and tasks required to provide an acceptable riser, complete shall be considered incidental to the work.

- Service Drop. Shall include all demolition, installation of new riser, weatherhead, riser cables, supports, roof jack, guy cable and shackles and will be considered complete only after required service drop elevation at the boardwalk is verified and installation inspected and approved by the Engineer and local Utility and service has been declared ready for energization. Actual energization is outside the control of the Contractor and is not a criteria for completion. All other material and tasks required to provide an acceptable service drop adjustment, complete, shall be considered incidental to the work.

- Pole.

  - New Pole. Shall include all demolition and backfill, installation of new pole complete, including guy and helical pile anchors as necessary (up to 2), relocating the existing service drops, transformer, taps and primary cutout fuse and re-serving all of the electrical services and will be considered complete only after inspected and approved by the Engineer and local Utility and service has been declared ready for energization. Actual energization is outside the control of the Contractor and is not a criteria for completion. All existing material scheduled for demolition and deemed salvageable by the local utility shall be returned to the local Utility. New pole is a subsidiary to “Pole” pay item.

  - Retire Pole. Shall include all demolition and backfill, disposal of existing pole complete, including removal of guy and anchor and will be considered complete only after inspected and approved by the Engineer and/or local Utility. Existing pole shall not be retired until telephone utility has completed it relocation efforts. Coordination with the telephone utility by the contractor is required. Retire pole is a subsidiary to “Pole” pay item.

- Stub Pole.  Where shown in the drawings, provide stub pole to ensure proper clearance for guys. Shall include all demolition of the existing guys and anchor and installation of hardware, guy cable(s), helical pile anchor, stub pole and guy warning sheath as shown on the plans to provide overhead transmission line bracing, complete.

- Verification and Inspection.  Notify the Engineer when the installation of each item is complete.  The Engineer will inspect the item installation, including elevation of the service riser and drop at the boardwalk.  The local utilities will also inspect each installation.  The Engineer and utilities will provide written approval of the installation or require corrections to be made.  Make corrections to the installation and request inspection until the installation is approved by the Engineer.  The utilities will declare the service is ready to be energized as part of their written approval.

681-4.01 METHOD OF MEASUREMENT.  Section 109.

681-5.01 BASIS OF PAYMENT.

Includes all work (labor and materials) to provide complete installation of each pay item.  Complete installation requires the Engineer and the local utilities to inspect the installations, the Engineer and utilities to provide written approval of the installations and the utilities to declare service is ready to be energized.

Incidental to each Pay Item, when required for a complete installation of each item, both labor and materials are: demolition, salvage, relocating, supports (temporary and permanent), roof jacks, weatherheads, guys and sheaths, anchors, shackles, and other.  In addition, incidental is: the work required to provide adequate clearances for service drops and to clear obstructions presented by service poles, guys, and boardwalks (new and existing) and other obstructions, to provide complete installations.  As-builts and shipping are also incidental to the complete installation of each item.  All necessary surveying for pole and anchor locations shall also be considered subsidiary to construction contract.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

681(27A)	Pole	Each

681(27B)	Stub Pole	Each

681(34)	Service Riser	Each

681(44)	Service Drop	Each

57181-013012

Special Provisions

Add the following Section:

SECTION 690

EROSION, SEDIMENT AND POLLUTION CONTROL - MEASURES

690-1.01 DESCRIPTION.  Furnish, install, and maintain measures, countermeasures and associated materials as part of BMP(s) to prevent, control and contain erosion, erosion materials, sediments and pollution contaminates, on and off project site.

Measures:

	Permanent Measures – include, the materials, hardware, equipment, and labor required for installation and maintenance of erosion, sediment, and pollution control material(s).

	Temporary Measures - include, in addition to the requirements of Permanent Measures, removal and disposal of the erosion, sediment, and pollution control material(s).

Related Specifications:

Erosion, Sediment and Pollution Control	Section 641

Silt Fence	Section 633

Seeding	Section 618

Soil Stabilization	Section 619

690-2.01 MATERIALS.

Erosion Sediment and Pollution Control – Materials	Section 744

Others as specified in related Sections.

CONSTRUCTION REQUIREMENTS

690-3.01 GENERAL.  BMP(s) may include individual or a combination of measures and countermeasures, including but not limited to temporary seeding, mulch, matting, staples, stabilizing emulsions, blankets and mats, soil binders, non-erodible cover, dustless sweeping, dust palliatives.   Refer to Subsection 690-1.01, Related Specifications, for measures not included here.

690-3.02 MATERIAL STORAGE AND PROTECTION.  General:  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment and as follows:

Fiber Rolls.  Additionally, protect fiber rolls from:  precipitation, extended ultraviolet radiant including sunlight, chemicals that are strong acids or other, flames including welding sparks, excess temperatures, and any other environmental conditions that may damage the physical property value of the rolls.

690-3.03 FABRICATION.

Sandbags:  Sand bags shall measure 15 inches by 30 inches.  Use prayer type seams with a minimum of two rows of stitching using a Federal Stitch Type 401 Chain Stitch.  Place approximately 1.0 cubic foot of Select Material, Type B, in each sandbag sack.  Close the open end of the sandbag, after filling, with 2 cinch ties or as recommended by the manufacturer of the sandbag material.

690-3.04 PLACEMENT AND INSTALLATION.  Place and install where shown and detailed in the Plans and Specifications including Section 641, and as recommended by the manufacturer, directed by the Engineer and as follows:

Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Confirm application of temporary seeding with the Engineer.

Prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetation cover.  Maintain seeded areas.  Refer to Section 620 for further surface/topsoil preparation requirements.

Reseed where water quality standards are being exceeded as a result of insufficient vegetative cover.  Review with Engineer prior to reseeding.

Refer to Section 618 for further information.

690-3.05 MAINTENANCE.  Maintain the integrity of the erosion, sediment and pollution control measures for the duration of the project.  Inspect as required by the APDES CGP and SWPPP and correct any deficiencies immediately.  Remove and dispose of temporary measures including trapped sediment contaminants off project at approved locations. Materials manufactured as biodegradable may be left in place when approved by the Engineer.

690-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Fiber Rolls / Compost Sock: By length, measured along the centerline of the fiber roll, complete in place.

Silt Fence:  Section 633.

Seeding:  Section 618.

Stabilization:  Section 619.

690–5.01 BASIS OF PAYMENT.  Section 641.

Except:

Item 690(1) Fiber Rolls/Compost Sock, includes materials, hardware, equipment and labor required for installation and maintenance.

Payment will be made under:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 690(1) | Fiber Roll/Compost Sock | Linear Foot |

CR690-081210

SECTION 709

REINFORCING STEEL & WIRE ROPE

Special Provision

709–2.01  REINFORCING STEEL.  Add the following:

Steel Welded Wire Fabric, Galvanized, for Boardwalk Railing:

- 8GA Welded Wire (0.1644-inch diameter, W2.1xW2.1)

- Wire Spacing Size: 2-inches by 2-inches.

- Galvanized after welding.

- Dimension and Mechanical Properties: ASTM A82 and A496

Staples for Welded Wire Fabric: All staples shall be of9 gauge class 3 galvanized steel or heavier with a minimum length of 2-inches.  Staples shall be barbed and include cutting points.

709-2.02 WIRE ROPE OR WIRE CABLE.  Delete this Section in its entirety and replace it with the following:

Wire rope shall be ¼-inch diameter galvanized aircraft cable in accordance with the following:

- Performance Standard and Dimensions:  Federal Specification MIL-DTL-83420M

- Material:  Drawn galvanized high carbon steel per Federal Specification MIL-DTL-83420M

- Working Load Limit:  1,400 lbs.

- Minimum Breaking Strength:  7,000 lbs.

Wire rope clips shall be ¼-inch  malleable steel in accordance with the following:

- Material and Mechanical Properties:  Federal Specification FF-C-450D Type I Class 2.

- Saddle Hardness:  HRB 83 maximum.

- Thread Requirements:  Nut Fit, Threads are acceptable when torque tested per FF-C-450D

- Coating:

  - U-Bolt and Nuts:  Fe/Zn3A per ASTM F1941.

  - Saddle: Hot dipped galvanized per ASTM A153 or F2329.

SECTION 713

STRUCTURAL TIMBER, LUMBER, AND PILING

Special Provision

Delete Section 713 in its entirety and replace it with the following:

713-2.01 LUMBER AND TIMBER.

- Wood species shall be Douglas Fir-Larch, unless otherwise specified.    In accordance with Western Wood Products Association (WWPA) and West Coast Lumber Inspection Bureau (WCLIB) grading rules, all boardwalk lumber and timber material shall be visually graded No. 1, except for guardrail 4x12 timbers, which shall be visually graded No. 1 and Better.  Design strength values shall equal those listed for this species and grade in the 2005 edition of the American Wood Council National Design Specification, Design Values for Wood Construction-NDS Supplement.

- Lumber and timber sizes are shown on the Plans in nominal dimensions, i.e.; 2x4, 3x12, etc., indicating surfaced four sides (S4S) or planed material.  Manufacturing classification shall be S4S Dressed (Surfaced) Lumber.  Size classification shall be nominal size designations of lumber and timber in accordance with PS-20, U.S. Department of Commerce Voluntary Product Standard for American Softwood Lumber.

- All timber and lumber members shall be grade-stamped to indicate lumber grading agency, mill number, wood species and grade and moisture content at the time of surfacing.

- All lumber, plywood, and timber shall be preservative-treated and conform to Section 714 and the Plans.

713-2.02 GLUE-LAMINATED (GLULAM) BEAMS.

- Glulam beams shall provide Douglas Fir-Douglas Fir (DF/DF) outer laminations on top and bottom, combination grade 24F-V4, in accordance with AITC 117, Standard Specification for Structural Glued Laminated Timber of Softwood Species, with the following minimum strength characteristics:

Fbx = 2,400 psi

Ft = 1,100 psi

Fvx = 265 psi

Ex = 1,800,000 psi

- Wet-use laminate adhesives shall be provided with the manufacturing of glulam beams in accordance with ASTM D2559.

- Glue Laminated Manufacturer's Qualifications:  The manufacturer shall be an AITC licensed firm, qualified to issue the AITC "Quality Inspection" mark.

- Quality Marks:  Mark each member with a "Quality Inspected" Mark indicating conformance with AITC 117.  Place mark on member surface which will not be exposed in the completed Work.

- Glulam beam dimensions shall conform to AITC 113, Standard for Dimensions of Structural Glued Laminated Timber.

- Glulam beams shall be preservative-treated and conform to Section 714 and the Plans.

713-2.03 PLYWOOD.

- Plywood shall be American Plywood Association (APA)-rated Marine Grade in accordance with PS-1, U.S. Department of Commerce Voluntary Product Standard for Structural Plywood, and the thicknesses and dimensions shown on the Plans.

- Each plywood panel shall be provided with the APA quality trademark conforming to PS-1, indicating the panel grade (i.e. “Marine Grade”), veneer grade of face and back plies, minimum species of outer plies, exposure durability classification, plywood thickness and the PS-1 standard mark.

713-2.04 STEEL CONNECTORS FOR WOOD CONSTRUCTION.

- General:  All steel connectors for wood construction shall be installed with barrier membrane in accordance this section to prevent all their surfaces from contacting preservative-treated wood.

- Manufactured steel connectors:

  - Manufactured steel connectors shall be fabricated from steel sheet in accordance with ASTM A36, ASTM A653 or ASTM A1011.

  - Corrosion Protection:  All steel connectors shall be hot-dipped galvanized in accordance with ASTM A653, or be manufactured from stainless steel sheet in accordance with ASTM A240 or ASTM A480.  Hot-dipped galvanized (HDG) connectors having a thickness of 16 gauge or less shall provide a G90 coating, and connectors having a thickness of 14 gauge or thicker shall provide a minimum zinc coating weight of 2.0 oz./sf.  Where connectors are required to have special galvanized thickness, such as with Simpson Strong-Tie “Z-max”, such connectors shall provide a G185 (1.85 oz./sf) coating.

  - Fasteners used with galvanized steel connectors shall be hot-dipped galvanized per ASTM A153, or be a galvanized or equivalent protective-coated product that is provided by the connector manufacturer for specific use with the connectors, such as Simpson Strong-Tie SD or SDS screws, or approved equal.  Fasteners used with stainless steel connectors shall be Type 316L stainless steel.

  - Manufactured steel connectors shall be as manufactured by Simpson Strong-Tie Company, Inc., USP Structural Connectors (United Steel Products Company), or approved equal.

- Shop-fabricated connectors:

  - Shop-fabricated connectors shall be made from steel plate or shapes in accordance with ASTM A36.

  - Shop-fabricated connectors shall be hot-dipped galvanized after fabrication in accordance with Section 716-2.07, to a minimum zinc coating thickness of 2.0 oz./sf.

- Fasteners:  Type, size and length as indicated in the Plans.

  - Bolts, Nuts and Washers for wood-to-steel and wood-to-wood connections:  conform to ASTM A307 with dimensions conforming to ANSI/ASME Standard B18.2.1.  Nuts shall conform to ASTM A563, grade matching bolt material.  Washers shall conform to ASTM F436.  Bolts shall be installed with a minimum of one nut and two washers, unless otherwise noted.  Bolts, nut and washers shall be hot-dipped galvanized in accordance with ASTM A153.

  - Lag Screws: conform to AISI 1006 to 1022 steel with dimensions conforming to ANSI/ASME Standard B18.2.1.  Bending yield strength of steel shall be minimum 45,000 psi for nominal diameters greater than or equal to 3/8 inches.  Tensile strength shall be minimum 60,000 psi.  Bolts, nut and washers shall be hot-dipped galvanized in accordance with ASTM A153.

  - Wood Screws: self-tapping steel screws meeting SAE J78, with dimensions conforming to ANSI/ASME Standard B18.6.1.  Bending yield strength of steel shall be minimum 80,000 psi for No. 9, 10 and 12 wood screw sizes. Wood screws shall be Type 304 or 316 stainless steel or bronze-ceramic-coated for specific use with ACQ or CA-C preservative-treated wood in exterior, wet environments.

  - Nails and Staples:  conform to ASTM F-1667.  Nails shall be common type and hot-dipped galvanized.  Staples shall be hot-dipped galvanized.

- Barrier Membrane:  Membrane barrier material shall be cross-laminated HDPE having a minimum thickness of 25 mils and specifically manufactured for the purpose of providing separation between steel components and wood treated with copper-based preservatives such as ACQ and CA-C.  The membrane barrier material shall have rubberized asphalt adhesive with a paper release liner.

57181-10112

SECTION 714

PRESERVATIVES FOR TIMBER

Special Provision

Delete Section 714 in its entirety and replace it with the following:

714-2.01 Apply preservative to all timber that is exposed to weather, water, or soil.  Meet the following:

- Timber: Use the preservatives and treatment processes of AASHTO M133 and Best Management Practices for the Use of Treated Wood in Aquatic Environments (BMPs), published by the Western Wood Preservers Institute, 601 Main Street, Suite 405, Vancouver, WA 98660 (Phone: 800-279-9663).  Use Copper Azole Type C with a retention of preservative in accordance with General Notes in the Plans.  Kiln dry to an average moisture content of 19% after treatment.

- Glued-Laminated Timber.  Use Copper Napthenate with a retention of preservative in accordance with General Notes in the Plans.  Pressure treat by empty-cell process after gluing, in accordance with AWPA Standards C1 and C3.

When oil-borne preservatives are used, treat all lumber and timber, including glued-laminated members, by the empty-cell process.

57181-100111

SECTION 715

STEEL FOR PILES

Special Provision

715-2.02 GENERAL REQUIREMENTS.  Add the following:

1.d.		Meet ASTM A 36 for steel H-Piles, size as shown on the Plans.

- Helical piles:

  - Steel pipe, outer diameter size and wall thickness as shown on the Plans, conforming to ASTM A500, Grade C, and providing a minimum tensile strength of 62 ksi and a minimum yield strength of 50 ksi.  For each pile, the pipe extension below the bottom helix shall be provided with a 45-degree mitered end.

  - Helices shall be hot-rolled steel conforming to ASTM A1018, Grade 55, Class 1, having a 0.5-inch thickness, a 3-inch pitch, a minimum tensile strength of 65 ksi and a minimum yield strength of 55 ksi.  Dimensions and number of helices shall be as shown on the Plans.   Helices shall be factory-welded to pipe sections using a continuous fillet weld on both sides of the helix-to-pipe connection.  Leading edge of helices shall be sharpened to minimize soil disturbance during installation.

  - Helical pile couplings shall be integral to or welded to the pipe shaft, and comprised of ASTM A958, Grade SC, steel square shaft with rounded corners, having a 40 ksi minimum yield strength and an 80 ksi minimum ultimate strength, or approved equal coupling arrangement.  Each coupling shall provide two perpendicular, transverse 0.875-inch diameter ASTM A325 hex head bolts with ASTM A563 jam nuts and ASME B18. 22.1 washers.

  - Helical pile assemblies shall provide a minimum ultimate torque capacity of 15,000 ft-lbs.

  - Helical pile assemblies shall be manufactured in accordance with ICC-ES AC358 Acceptance Criteria for Helical Foundation Systems and Devices.

  - After fabrication, all helical pile surfaces shall be hot dipped galvanized in accordance with ASTM A123 and ASTM A153.

- Helical Anchors:

  - Solid steel square shaft, size as shown on the Plans, conforming to ASTM A576, Grade 1530M, and providing a minimum ultimate torque capacity of 7,000 ft-lbs, a minimum tensile strength of 120 ksi and a minimum yield strength of 90 ksi.

  - Helices: same as provided for helical piles.

  - Helical anchor shafts shall provide integrally-forged sockets that receive a square shaft of the same size, each with a transverse hole to join lead or extension sections with a bolt and nut. Each coupling shall provide a transverse 0.75-inch diameter ASTM A325 hex head bolt with ASTM A563 jam nut and ASME B18. 22.1 washer.

  - Helical pile assemblies shall provide a minimum ultimate torque capacity of 7,000 ft-lbs.

  - Helical pile assemblies shall be manufactured in accordance with ICC-ES AC358 Acceptance Criteria for Helical Foundation Systems and Devices.

  - After fabrication, all helical pile surfaces shall be hot dipped galvanized in accordance with ASTM A123 and ASTM A153.

57181-120111

SECTION 724

SEED

Special Provision

724-2.02 MATERIALS.

Delete Table 724-1 and replace with the following:

TABLE 724-1

SEED REQUIREMENTS

| Species | Sproutable Seed, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

*Sproutable Seed is the mathematical product of Germination and Purity.

CR7241-101711

SECTION 730

SIGN MATERIALS

Standard Modification

Delete Subsection 730-2.01 SHEET ALUMINUM and replace with the following:

730-2.01 SHEET ALUMINUM.  Use alloy 6061-T6, 5052-H36, 5052-H38, or recycled aluminum meeting alloy 3105, as specified in ASTM B 209.  Meet the thickness of aluminum sheet designated on the Plans.  Verify alloy and temper designation by mill certification.

Before January 1, 2011, treat the aluminum base metal sheets with chromate conversion coating for aluminum to meet ASTM B449, Class 2.

After January 1, 2011, treat the aluminum base metal sheets with a rinsed non-hexavalent chromium conversion coating for aluminum and aluminum alloys that meets ASTM B 921, class one.  Handle the cleaned and coated base metal only by a mechanical device or by operators wearing clean cotton or rubber gloves.  After cleaning and coating operations, protect the panels at all times from contact or exposure to greases, oils, dust, or other contaminants.

Make each sign panel a continuous sheet for all lengths 72 inches or less in the horizontal direction.  Use no more than one vertical splice for signs up to 144 inches in length and 48 inches or less in height.

Meet the panel dimensions specified with a tolerance of 1/16 inch.  Furnish metal panels that are cut to size and shape and free of buckles, warp, dents, cockles, burrs, and any other defects resulting from fabrication.  Complete all possible fabrication, including shearing, cutting, and punching of holes prior to the base metal preparation.

E86-041210

Special Provision

730-2.04 SIGN POSTS.

Add No. 7:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to ASTM A500, Grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

CR81-062204

Special Provisions

Add the following Section:

SECTION 744

EROSION, SEDIMENT, AND POLLUTION CONTROL - MATERIAL

744-2.01 MATERIAL.

1.	Fiber Roll:  (commonly called straw wattle)

a.	Comprised of UV-degradable plastic netting or 100 percent biodegradable material.

b.	Filled with straw, flax, rice, coconut fiber material or composted material.

c.	Staking shall be made of 100 percent biodegradable materials.

Provide the Engineer certification stating the name of the manufacturer, product name, style number, chemical composition of the fiber, netting, and certification of the weed-free status from the manufacturer.  Furnish a sample to the Engineer seven days before the scheduled installation.

2.	Compost Filter Sock:

a.	Compost filter material shall have the following parameters:

pH	5.0 – 8.5

Moisture Content	30 – 60% wet weight basis

Organic Matter Content	25 – 65% dry weight basis

Particle Size	3 in. 100% passing

1 in. 90 – 100% passing

0.75 in. 70-100% passing

0.25 in. 30-75% passing

Maximum particle size length of 6 in.

57181-120111

INDEX

Standard Modification

INDEX Remove the text. “Approved Products List” and replace with: Qualified Products List

E36-012707

APPENDIX A

CONSTRUCTION SURVEY REQUIREMENTS

APPENDIX B

ENVIRONMENTAL PERMITS

APPENDIX C

MATERIAL CERTIFICATION LIST

APPENDIX D

TEMPORARY CONSTRUCTION EASEMENTS

APPENDIX E

MANDATORY POST-AWARD CONFERENCE