SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available from the Department of Transportation and Public Facilities located at 4111 Aviation Avenue in Anchorage.  Information may be obtained as follows:

1.	Copies for review and reproduction information may be obtained from the Plans Room, (907) 266-1798, for the following:

a.	Computations

b.	Cross Sections

c.	Boring logs and laboratory testing information for test holes drilled at retaining walls and major excavation areas.

2.	Utility agreements pertaining to the disposition of the load centers on this project are available for review at the office of the Traffic, Safety and Utilities Engineer, (907) 266-1531.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS

FOR HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Special Provisions

101-1.27  Holidays.  Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third 		Monday in January.

3.	President's Day - Third Monday in February.

(11/6/89)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  Qualification of Bidders.  Delete the second paragraph.  (5/12/89)

Special Provisions

102-1.01  Qualification of Bidders.  Add the following:  The bidder, by signing the proposal and under penalty of perjury under the laws of the United States, certifies that, except as may be noted on the proposal, the bidding firm or any person associated therewith is not currently under suspension, debarment, voluntary exclusion, or determination of ineligibility by any federal agency; has not been suspended, debarred, voluntarily excluded or determined ineligible by any federal agency within the past 3 years; does not have a proposed debarment pending; and has not been indicted, convicted, or had a civil judgement rendered against (it) by a court of competent jurisdiction in any matter involving fraud or official misconduct within the past 3 years.

Exceptions to the above shall be noted by the bidder on the proposal or on an attachment thereto.

Exceptions will not necessarily result in denial of award, but will be considered in determining bidder responsibility.  For any exception noted, indicate to whom it applies, initiating agency, and dates of action.  Providing false information may result in criminal prosecution or administrative sanctions.

(3/18/88)

Special Provisions

102-1.06   Preparation of Proposal.  Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

102-1.07  Non-Responsive Proposals. Delete numbered subsection 3. in its entirety and substitute the following:

3.	 If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a limit on the maximum gross amount of awards acceptable to any one bidder at any one bid letting, provided that any selection of awards will be made by the Department.  (2/7/89)

Standard Modifications

102-1.07  Non-Responsive Proposals. Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)

102-1.12  Addenda Requirements.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  Consideration of Proposals.  Add the following:  The apparent low bidder shall, within 5 working days following the bid opening, submit either a list of all firms with which the prime Contractor intends to execute subcontracts for the performance of the contract or a statement that the bidder intends to perform the work without subcontractors.  The list shall include the following information for each proposed subcontractor:

1.	name,

2.	business address,

3.	Alaska business license number

4.	Contractor's registration number,

5.	the work to be performed, and

6.	the approximate dollar amount of the work to be performed.

If the apparent low bidder fails to submit either a list of subcontractors or a statement that the bidder intends to perform the work without subcontractors, the apparent low bidder will be found not to be a responsible bidder and may be required to forfeit the bid security.  The Department will then consider the next lowest bidder for the award of the contract.

If the apparent low bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess  of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this Subsection.

If a contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department; or

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18;

2.	files for bankruptcy or becomes insolvent;

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith;

4.	fails to obtain bonding;

5.	fails to obtain insurance acceptable to the Department;

6.	fails to perform the contract with the bidder involving work for which the subcontractor was  listed;

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements;

8.	refuses to agree or abide with the bidder's labor agreement; or

9.	is determined by the Contracting Officer not to be responsible.  (7/1/90)

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  Changes.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)

Special Provisions

104-1.02  Changes.  Delete the first three paragraphs and substitute the following:  The Engineer reserves the right to make, in writing, at any time during the work, such changes in quantities and such alterations in the work as are necessary to satisfactorily complete the project.  Such changes in quantities and alterations shall not invalidate the contract nor release the surety, and the Contractor agrees to perform the work as altered.

If the alterations or changes in quantities significantly change the character of the work under the contract, whether or not changed by any such different quantities or alterations, an adjustment, excluding loss of anticipated profits, will be made to the contract.  The basis for the adjustment shall be agreed upon prior to the performance of the work.  If a basis cannot be agreed upon, then an adjustment will be made either for or against the Contractor in such amount as the Engineer may determine to be fair and equitable.

If the alterations or changes in quantities do not significantly change the character of the work to be performed under the contract, the altered work will be paid for as provided elsewhere in the contract.

The term "significant change" shall be construed to apply only to the following circumstances:

1.	When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction, or

2.	When a major item of work, as defined elsewhere in the contract, is increased in excess of 125 percent or decreased below 75 percent of the original contract quantity.  Any allowance for an increase in quantity shall apply only to that portion in excess of 125 percent of original contract item quantity, or in case of a decrease below 75 percent, to the actual amount of work performed.

(4/13/89)

104-1.03  Differing Site Conditions.  Delete in its entirety and substitute the following:  During the progress of the work, if subsurface or latent physical conditions are encountered at the site differing materially from those indicated in the contract or if unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the work provided for in the contract, are encountered at the site, the party discovering such conditions shall promptly notify the other party in writing of the specific differing conditions before they are disturbed and before the affected work is performed.

Upon written notification, the Engineer will investigate the conditions, and if he determines that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any work under the contract, an adjustment, excluding loss of anticipated profits, will be made and the contract modified in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment which results in a benefit to the Contractor will be allowed unless the Contractor has provided the required written notice.

(4/13/89)

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  Authority of the Engineer.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02, Changes.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)

Special Provisions

105-1.05  Cooperation by Contractor.  Add the following:  The Contractor's office shall be equipped with a facsimile machine.  The cost of obtaining, maintaining and operating the machine will be subsidiary to the contract.

105-1.06   Cooperation With Utilities.  Add the following:  The Contractor shall request locates from all

the Utilities having facilities in the area.  Their telephone numbers are as follows:

Anchorage Telephone Utility               278-3121

Anchorage Water and Wastewater Utility    278-3121

Chugach Electric Association              278-3121

DOT/PF Maintenance & Operations           333-2411

ENSTAR Natural Gas Company                278-3121

Prime Cable Television                    278-3121

Municipal Traffic Operations              278-3121

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Prior to the relocation of the utility's facilities, construction stakes by the Contractor in the areas of utility conflicts may be required.  The Utility requesting the stakes, through the Engineer, shall be given two (2) weeks advance notice when the area will be staked.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the Utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

Electrical Cable Damage

If a cable is damaged and requires splicing, the first will be repaired by the Utility with the party causing the damage paying the repair costs.

If the cable is damaged a second time, the cable will be replaced between junction points.  The party causing the damage shall pay for replacing the cable.

ANCHORAGE TELEPHONE UTILITY

Anchorage Telephone Utility will be installing  conduit crossings of Tudor Road in conjunction with this project at the following locations:

Sta 152+95 (Lake Otis)	1 6-way duct

Sta 33+50 (Cambridge)	4 4-way PVC

The Contractor shall coordinate the installation of the conduit crossings with ATU after excavation and prior to backfill.  Two (2) weeks advance written notice from the Contractor to ATU is required for crew scheduling.

ANCHORAGE WATER AND WASTEWATER UTILITY

All AWWU relocation and construction is a part of the construction contract.  Refer to Sections 626 and 627 for water and sewer specifications and coordination.

Construction of sanitary sewer service to the new Anchorage School District Save II High School must be completed and accepted by AWWU by June 30, 1991 in order to meet the building occupancy date of July, 1991.  The Contractor is reminded that as-builts required per subsection 626-3.03 are a precondition to acceptance of the improvements by AWWU.

CHUGACH ELECTRIC ASSOCIATION

CEA will be relocating the existing underground facilities along and crossing Tudor Road to accommodate the required grade lowering between Sta 283+00 and 298+00.

CEA will abandon the existing 1-phase crossings of Tudor Road at Sta 288+15 and 291+70, and the 3-phase crossing of Kingston Drive prior to May 1, 1991.  To accomplish this a new 3-phase feeder will be installed along the north side of Tudor Road in the existing utility easement between approximate Sta 285+00 and 288+00.  The new feeder will replace service supplied by the existing 1-phase primary crossings and allow for abandonment.  The Contractor shall give CEA two (2) weeks advance written notice to proceed and shall allow one (1) week to complete the abandonment.

After  excavation of  Tudor Road  and  Kingston Drive and prior to fill   the   Contractor   shall  allow  CEA  to install   a   new    3-phase    feeder    circuit   along  the   north  side

of Tudor Road between Sta 283+75 and 297+05.  The new conductor will be placed between the new curb and pathway.

The Contractor will install a new 2-inch rigid steel conduit crossing Tudor Road at Sta 292+90 in accordance with the plans and specifications.

Upon completion of the crossing the Contractor will allow CEA access to install new conductor in the crossing.

ENSTAR NATURAL GAS COMPANY

Enstar will adjust and relocate the Natural Gas Facilities along and crossing Tudor Road to accommodate construction of the retaining wall between Sta 179+34 and 184+88, and the grade lowering between Sta 283+00 and 298+00.

Enstar will replace the existing six (6) inch steel crossing Tudor Road Sta 284+90 and lower the existing three (3)-inch steel crossing Baxter Road at Tudor Road.  The existing 2-inch plastic along the south side of Tudor Road between Sta 286+00 and 295+00 will be lowered in place as required to eliminate conflicts with slope limits.  Existing 2-inch distribution mains and services in conflict with the grade lowering of Kingston Drive will be replaced.

The existing 4-inch plastic along the south side of Tudor between Piper and Gruman may be abandoned to allow for excavation for the proposed retaining wall between Tudor Sta 179+34 and 184+88.  After excavation, the Contractor shall allow Enstar to place a new 4-inch plastic main below the new sidewalk.  The existing 4-inch main can only be abandoned between May 15th and August 31st.  At all other times the Contractor will be required to work around the main during wall excavation and construction.

The Contractor shall provide fifteen (15) days advance written notice to proceed to Enstar to allow for scheduling of crews.

A cathodic protection area sweep is required after all underground work has been completed and before paving begins.  The sweep will take one (1) day to perform and will require three (3) working days notice to Enstar prior to performing the work.  If any underground contacts are detected, additional time will be required to perform repairs.

PRIME CABLE

Prime Cable will relocate its facilities along the north side of Tudor Road between Sta 283+00 and 298+00 to accommodate the required grade lowering.

To allow for excavation of Kingston Drive a temporary aerial crossing will be constructed.  The Contractor shall set the required poles in accordance with the plans and specifications, Section 684.  Prime cable will accomplish the aerial crossing and abandonment of the existing underground.  Prime Cable requires five (5) days advance written notice to proceed after the poles have been set, and will require one (1) day to complete the crossing.

After excavation and prior to fill, the Contractor shall allow Prime cable to install the new cable between approximate Sta 288+00 and 290+80.

105-1.12  Load Restrictions.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless allowed for use by an approved Traffic Control Plan.  (2/7/89)

105-1.15  Project Completion.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work scheduled under Subsection 618-3.04, Maintenance of Seeded Areas, a letter of project completion will be issued by the Engineer.  (2/1/90)

Standard Modifications

105-1.17  Claims for Adjustment and Disputes.  Add the following after the ninth paragraph:  The Contractor shall certify that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and

belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (5/12/89)

Special Provisions

105-1.17  Claims for Adjustment and Disputes.  Add the following:  Legal actions will be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/29/87)

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  Source of Supply and Quality Requirements.  Add the following:  All steel products which are to be incorporated into the work shall be produced in the United States except that minor amounts of steel products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract cost, or $2500, whichever is greater.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel products into the project.

(11/9/84)

106-1.02  Local Material Sources.  Under Item 1. General, add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)

Add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement will be given to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01  Laws to be Observed.  Add the following:  Specific Equal Employment Opportunity Responsibilities of Federal-Aid Construction Contractors.

1.	General

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form 25D-55) and these Special Provisions which are imposed pursuant to Section 140 of Title 23, U.S.C., as established by Section 22 of the Federal-Aid Highway Act of 1968.  The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the equal employment opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State highway agencies and the Federal Government in carrying out equal employment opportunity obligations and in their review of his/her activities under the contract.

c.	The Contractor and all his/her subcontractors holding subcontracts not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of equal employment opportunity:  (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as Contractors and subcontractors.)  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.

2.	Equal Employment Opportunity Policy

The Contractor will accept as his operating policy the following statement which is designed to further the provision of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include:  employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprentice-ship and/or on-the-job training.

3.	Equal Employment Opportunity Officer

The Contractor will designate and make known to the Engineer and equal employment opportunity officer (hereinafter referred to as the EEO Officer) who will have the responsibility for and must be capable of effectively administering and promoting an active Contractor program of equal employment opportunity and who must be assigned adequate authority and responsibility to do so.

4.	Dissemination of Policy

a.	All members of the Contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the Contractor's equal employment opportunity policy and contractual responsibilities to provide equal employment opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

(1)	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the Contractor's equal employment opportunity policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor's equal employment opportunity obligations within thirty days following their reporting for duty with the Contractor.

(3)	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the Contractor's procedures for locating and hiring minority group employees.

b.	In order to make the Contractor's equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

(1)	Notices and posters setting forth the Contractor's equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The Contractor's equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

5.	Recruitment

a.	When advertising for employees, the Contractor will include in all advertisements for employees the notation:  "An Equal Opportunity Employer."  All such adver-tisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority group applicants, including, but not limited to, State employment agencies, schools, colleges and minority group organizations.  To meet this requirement, the Contractor will, through his EEO Officer, identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority group applicants may be referred to the Contractor for employment consideration.

In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor's compliance with equal employment opportunity contract provisions.  (The U.S. Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or women, or obligates the Contractor to do the same, such implementation violates Executive Order 11246, as amended.)

c.	The Contractor will encourage his present employees to refer minority group applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures with regard to referring minority group applicants will be discussed with employees.

6.	Personnel Actions

Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The Contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The Contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with his obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the Contractor will inform every complainant of all of his avenues of appeal.

7.	Training and Promotion

a.	The Contractor will assist in locating, qualifying, and increasing the skills of minority group and women employees, and applicants for employment.

b.	Consistent with the Contractor's work force requirements and as permissible under Federal and State regulations, the Contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.  In the event the Training Special Provision is provided under this contract, this subparagraph will be superseded as indicated.

c.	The Contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.	The Contractor will periodically review the training and promotion potential of minority group and women employees and will encourage eligible employees to apply for such training and promotion.

8.	Unions

If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and female employees.  Actions by the Contractor either directly or through a Contractor's association acting as agent will include the procedures set forth below:

a.	The Contractor will use best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

b.	The Contractor will use best efforts to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The Contractor is to obtain information as to the referral practices and policies of the labor union except that the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the Contractor, the Contractor shall so certify to the State highway department and shall set forth what efforts have been made to obtain such information.

d.	In the event the union is unable to provide the Contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the Contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minority group persons and women.  (The U.S. Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees.)  In the event the union referral practice prevents the Contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such Contractor shall immediately notify the State highway agency.

9.	Subcontracting

a.	The Contractor will use his best efforts to solicit bids from and to utilize minority group subcontractors or subcontractors with meaningful minority group and female representation among their employees.  Contractors shall obtain lists of minority-owned construction firms from State highway agency personnel.

b.	The Contractor will use his best efforts to ensure subcontractor compliance with their equal employment opportunity obligations.

10.	Records and Reports

a.	The Contractor will keep such records as are necessary to determine compliance with the Contractor's equal employment opportunity obligations.  The records kept by the Contractor will be designed to indicate:

(1)	the number of minority and nonminority group members and women employed in each work classification on the project,

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to Contractors who rely in whole or in part on unions as a source of their work force),

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority group subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such records must be retained for a period of three years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the State highway agency and the Federal Highway Administration.

c.	The Contractor will submit an annual report to the State highway agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form PR 1391.  If on-the-job training is being required by "Training Special Provision", the Contractor will be required to furnish State of Alaska Form 25A312.

(4/8/83)

107-1.11  Protection and Restoration of Property and Landscape.  Add the following to the third paragraph:  When working near designated wetlands the  Contractor shall place no fill nor operate equipment outside the slope limits.

The Contractor shall not excavate, nor use for fill, any material containing hazardous substances or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected of containing hazardous substances or petroleum fuels.  Hazardous substances are any element, compound, mixture, solution or substance designated pursuant to the Comprehensive Environmental Response, Compensation, and Liability Act of 1980 (CERCLA).  Hazardous substances include any hazardous wastes having the characteristics of ignitability, corrosivity, reactivity, or extraction procedure toxicity.

Add the following:  The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any significant historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.

The Contractor shall do no work, stockpiling, staging, parking, nor trespassing in or around any watercourse or wetlands unless permitted by the contract.  There shall be no operation of equipment beyond the finished toe of the existing slope in areas with adjacent wetlands.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

Standard Modifications

107-1.13  Responsibility for Damage Claims.  In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries".  (5/12/89)

107-1.16  Contractor's Responsibility For Utility Property And Services.  In the last sentence of the third paragraph delete: "by the local fire authority."  (5/12/89)

Special Provisions

107-1.16  Contractor's Responsibility for Utility Property and Service.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mislocates the facility in the field by more than 2.5-feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.  (9/1/89)

107-1.21  Permits.  Add the following Subsection:  The following permit has been received on the Contractor's behalf by the Department:

1.	Municipality of Anchorage Noise Permit.  The permit authorizes sound levels to 95 dBA to occur throughout the night from May 1, 1991 through October 31, 1991.

The permit obtained by the Department is attached to these specifications as Appendix A.  The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor's responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer.  The Engineer will then decide if a permit modification is necessary.

(9/1/89)

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  Subletting of Contract.  Delete the third paragraph on page 56 and substitute the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Driver's License.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	the owner-operator's right to control the manner in which the work is to be performed,

2.	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3.	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4.	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each truck driver that identifies the truck driver as either an employee or owner-operator.  The placard for owner-operators shall identify both the truck driver and the vehicle.  The placard shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.  (9/1/89)

Standard Modifications

108-1.03  Prosecution and Progress.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule". (5/12/89)

Special Provisions

108-1.03  Prosecution and Progress.  Add the following:  The construction of this project will be planned and recorded with a conventional Critical Path Method (CPM) schedule.  The schedule shall be used for coordination, monitoring, and payment of all work under the contract including all activity of subcontractors, vendors, and suppliers.

1.	Preparation of Initial Schedule.  At the preconstruction conference, the Contractor shall submit a detailed initial Progress Work Schedule in the activity-on-arrow format.  The schedule shall meet the requirements set forth below.

The construction time, for the entire project or any milestone shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed schedule are required, the Contractor shall do so promptly.  The schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements.	All activity-on-arrow diagrams shall include:

a.	Activity Nodes

b.	Activity Description

c.	Activity Duration

d.	Resources required for each of the project activities, including:

1.	labor, showing

-workdays per week

-holidays

-shifts per day

-hours per shift

2.	equipment, including the number of units of each type of equipment, and

3.	materials

The activity-on-arrow diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and approvals and fabrication and delivery activities.  All network "dummies" are to be shown on the diagram.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60 - Day Preliminary Schedule.  Before proceeding with any work on site, the Contractor shall have an acceptable 60-day preliminary schedule.  This schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include:

a.	mobilization,

b.	submittals,

c.	procurement, and

d.	construction.

No contract work may be pursued at the site without an accepted 60-day Preliminary Schedule or an accepted CPM schedule.

4.	Schedule Updates And Progress Payments.  Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the Progress Work Schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions.

The Contractor will revise activity-on-arrow diagrams for the following:

a.	resource availability;

b.	delay in completion of any critical activity;

c.	actual prosecution of the work which is, as determined by the Engineer, significantly different than that represented on the schedule; and,

d.	the addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

The principles involved and terms used in this subsection are as set forth in the Associated General Contractors of America publication, "The Use of CPM in Construction, A Manual for General Contractors and the Construction Industry", Copyright 1976.

In addition to the CPM Progress Work Schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail work activities, manpower involved by trade, work hours, equipment involved and the location of the work to be performed.

After approval of the Progress Schedule, and during the life of this project, the Contractor shall make available a spokesperson knowledgeable in the proposed construction operation.  State representatives may be attending meetings, community council meetings, throughout the Region, and it is expected that the spokesperson will accompany them to assist by briefly describing, and answering questions about the Contractor's work and time schedules.   The spokesperson will also be required to accompany the Engineer to residents and businesses abutting Tudor Road, when disputes or problems arise that require mediation between the public and the project.  The spokesperson must be able to speak for the Contractor and commit the Contractor to courses of action when needed to resolve problems.

Preparation of the CPM work schedule, two week work plans and providing a spokesperson will not be paid for directly, but will be subsidiary to Item 640(1) Mobilization and Demobilization.  (6/13/90)

108-1.04  Limitation of Operations.  Add the following:  The Contractor shall not commence any removal operations prior to May 1, 1991.  The Contractor shall adhere to Subsection 643-3.08 Construction Sequencing for further construction activity restrictions.

108-1.05  Character of Workmen, Methods and Equipment.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer. (2/1/90)

The following restrictions shall be followed for the night work authorized under the noise permit:

1.	The Contractor shall not use "Jake" brakes.

2.	Engine generators shall be placed in noise reduction cabinets.

3.	Vibrating rather than impacting jack hammers shall be used.

4.	Plywood barriers shall be constructed at jack hammer sites to attenuate noise levels.

108-1.06  Determination and Extension of Contract Time. Add the following:

4.	Suspensions of Work Ordered by the Engineer.  If the performance of all or any portion of the work is suspended or delayed by the Engineer in writing for an unreasonable period of time (not originally anticipated, customary, or inherent to the construction industry) and the Contractor believes that additional compensation and/or contract time is due as a result of such suspension or delay, the Contractor shall submit to the Engineer in writing, a request for adjustment within 7 calendar days of receipt of the notice to resume work.  The request shall set forth the reasons and support for such adjustment.

Upon receipt, the Engineer will evaluate the Contractor's request.  If the Engineer agrees that the cost and/or time required for the performance of the contract has increased as a result of such suspension and the suspension was caused by conditions beyond the control of and not the fault of the Contractor, its suppliers, or subcontractors at any approved tier, and not caused by weather, the Engineer will make an adjustment (excluding profit) and modify the contract in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment will be allowed unless the Contractor has submitted the request for adjustment within the time prescribed.

No contract adjustment will be allowed under this clause to the extent that performance would have been suspended or delayed by any other cause, or for which an adjustment is provided for or excluded under any other term or condition of this contract.

(4/13/89)

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  General.  Add the following:  When more than one variety of material or work item is specified for a single pay item number, letter or numeric suffixes will be included within the parenthesis to differentiate the types.  (9/1/89)

109-1.04  Compensation for Altered Quantities.  In the third indented subparagraph, delete the following:  ", except that the total payment for the item shall not exceed 75 percent of the total amount bid for the item".  (4/13/89)

109-1.05  Compensation for Extra Work.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)

109-1.07  Payment For Materials on Hand.  Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Anchorage, Alaska only.  (9/1/89)

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  Description.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  Interpretation.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  Essential Contract Provision.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  Definitions and Terms.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular Contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03 Item 3. for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a Contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  Utilization Goal.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Goal in order to be eligible for award of this contract.

120-3.01  Determination of Compliance.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  Good Faith Effort.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE Credit.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that ALL of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least one of which must be working on this project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  Default of DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, ALL of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02, Good Faith Effort.

120-4.01  Method of Measurement.  The Contractor shall be entitled to count toward the DBE Goal those monies allowed by the Engineer in 120-3.03.04 as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100 percent.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60 percent of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  Basis of Payment.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01, Utilization Goal, until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per subsection 120-3.03, Item 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

Payment or Deduction will be made under:

Pay Item No.        Pay Item         Pay Unit

120(1)        DBE Adjustment   Contingent Sum

(5/5/89)

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-2.01  General.  Add the following:  No burning or burying of cleared materials will be allowed on the project.

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-2.02  General.  Add the following:  All fences designated by the Engineer shall be carefully removed to the Right-of-Way limit, or to the end of the span beyond the Right-of-Way limit.  These materials belong to the property owners, and shall be salvaged and stacked neatly in their yards.  After construction of any noise barrier or fence, the fencing gaps behind the property line shall be filled using portions of the salvaged fencing in accordance with Section 607, Fences for reconstructed fences.

202-2.03  Removal of Pipe.  Delete this subsection and substitute the following:  When the Bid Schedule contains an item for the removal of culvert, sanitary sewer, or water pipe, the pipe to be removed will become the property of the Contractor.

202-2.05  Cold Planing.  Add the following Subsection:  The Contractor shall remove existing asphalt concrete pavement by cold planing at locations shown on the plans.  The surface of the pavement after planing shall be uniformly rough grooved or ridged.

The Contractor shall remove all planed material from the project immediately after planing.  Disposal areas shall be outside the project limits.  The Contractor shall obtain written consent of the property owner.  The Contractor shall also obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529.

Areas that have been planed shall be repaved within 24 hours after completion of planing unless prevented by weather or other factors beyond the Contractor's control.  If existing pavement not designated for removal is broken or otherwise damaged by the planing operation it shall be repaired by the Contractor at his expense.  During the cold planing operation, the Contractor shall sweep the streets with mechanical sweepers equipped with vacuum and  water sprinkling devices to control dust and remove all loosened material from the planed areas.  The removal operation shall follow within 50 feet of the cold planing machine.

The Contractor shall not allow traffic to travel on surfaces that have an abrupt longitudinal cold planed edge greater than 2 inches.  In the event that it is necessary to route traffic across such edges, an asphalt concrete transition 2 feet in width shall  be placed adjacent to the edge and to all gutters.

A tolerance of 1/8-inch shall be maintained by the cold planer between adjacent passes.

The cold planing machine shall be specifically designed for the removal of bituminous pavement without the addition of heat.  The cutting drum shall be a minimum of 60 inches wide and shall be equipped with cutting teeth placed in a variable lacing pattern to produce the desired finish.

The cold planing machine shall have the capability of being operated at speeds from 0 to 40 feet per minute.  It shall be self propelled and have the capability of spraying water at the cutting drum to minimize dust.  The machine shall be capable of removing the material next to the gutter.  It shall be designed so that the operator can at all times observe the planing operation without leaving the controls.  The machine shall be adjustable as to slope and depth.  It shall be capable of cutting up to 3 inches without producing fumes or smoke.

The Contractor shall provide a smaller machine to trim areas that are inaccessible to the larger machine at manholes, valve covers, curb returns, and intersections.

202-4.01  Basis of Payment.  Add the following:  Mechanical sweepers required for the cold planing operation will be paid for under Item 643(17), Street Sweeping.

Pay Item No.       Pay Item          Pay Unit

202(12)     Removal of Fence      Linear Foot

202(15)    Pavement Planing      Square yard-inch

202(17)    Removal of Water Pipe   Linear Foot

The payment for pavement planing in transition areas where planing depth varies, will be paid for as if the entire transition was of the larger thickness.

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01  Description.  Add the following:  Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

Standard Modifications

203-2.05  Borrow.  Add the following:  Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.  (5/12/89)

Special Provisions

203-4.01  Method of Measurement.  Add the following:  No deduction from the excavation quantities will be made for pavement removed under Item 202(2), Removal of Pavement. (9/1/89)

Add the following:  Measurement of ditch linear grading, whether flat bottom or "V" ditch, will be measured for payment by the linear foot along the center of the ditch for each ditch so designated, constructed and accepted by the Engineer.

Standard Modifications

203-5.01  Basis of Payment.  Change Pay Items 203(5), (6) and (7) to read:  Borrow, Type _____.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)

Special Provisions

203-5.01  Basis of Payment  Add the following:  Ditch linear grading will be paid by the linear foot; and payment so made will be full compensation for furnishing all equipment, labor, tools and incidentals to provide the preparation, excavating and shaping necessary to complete the work.

Payment will be made under:

Pay Item No.        Pay Item              Pay Unit

203(25)    Ditch Linear Grading     Linear Foot

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01  Materials.  Add the following:  Bedding and backfill materials within the structural section shall meet the requirements for the applicable lift of material.  Native material shall be utilized for pipe bedding and backfill below or outside the structural section if the material meets the minimum requirements of Selected Material, Type C as specified in Subsection 703-2.07, Selected Material.  Pipe bedding shall also pass a 3-inch sieve.  (9/1/89)

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01  Materials.  Delete the second sentence and substitute the following:  The gradation of base course material shall conform to Table 703-2, Grading D-1.

301-3.01  Placing.  Add the following:  Base course material used for the sidewalk or pathway shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.  (9/1/89)

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-2.01  Composition of Mixtures.  Add the following to the first paragraph after the first sentence:  The Contractor shall submit, in writing, the proposed ratios at which he plans to blend the various aggregate stockpiles in order to achieve the target gradation submitted.

Add the following to the tolerance table of the fourth paragraph:

Sieve Size          Tolerance

1/2 inch               + 8

No. 80                 + 4

Add the following after the tolerance table of the fourth paragraph:  The asphalt cement and aggregate submitted by the Contractor for Asphalt Concrete, Type IA Job Mix Design approval as tested according to Alaska T-17 shall conform to the following.

Marshall Stability, pounds, minimum    1500

Voids, Total Mix %                      3-5

Flow Value                              8-16

Compaction Blows per Side                75

Voids in Mineral Aggregate, %, min.     14.0

The Voids in mineral aggregate is calculated by the following formula:

GmbPs

Voids in mineral aggregate = 100 - (____)

Gsb

Where:

Gsb = bulk specific gravity of aggregate

Gmb = bulk specific gravity of compacted

mixture (ATM T-18), and

Ps = aggregate, percent by total weight of

mixture

The Contractor should be cautioned that addition

of crushed fines may be required to meet the Voids in

Mineral Aggregate requirement.

The Alaska Test Method T-17 section E.4.a shall be deleted and the following should be substituted:

a.	From the data curves, asphalt contents are determined which yield the following:

1.  Maximum Unit Weight

2.  Maximum Stability

3.  Voids Total Mix at 4 percent

Add the following:  Temporary pavement may, at the Contractor's option, be Asphalt Concrete, Type III, as detailed on Table 703-3 in Subsection 703-2.04, Aggregate for Plant Mix Asphalt Pavement.

401-2.04  Asphalt Materials.  Add the following:  AC-5 asphalt cement will be used for the new asphalt concrete pavement mix.

401-3.06  Preparation of Existing Surface.  Add the following:  After cold planing of a section of the roadway has been completed that section shall be inspected by the Engineer for areas of distress or failure.  Areas requiring repair shall have the remaining pavement removed, and the distressed area shall be excavated to the depth and limits directed by the Engineer.  The excavated area shall be backfilled, as directed by the Engineer with base material in conformance with the requirements of Section 301 or with Asphalt Concrete, Type IA.

Prior to the placement of pavement, all new construction directly adjacent to and within the area to be paved shall be completed.  This includes curb and gutter, storm drainage construction, traffic signal improvements, loop detectors, illumination, utility adjustments, manhole and valve adjustments, and other similar items of work that may be required.

401-3.09  Mixing.  Delete the second and third sentences of the second paragraph in their entirety.

401-3.11  Spreading and Finishing.  Add the following:  When pavement marking tape for striping is required, the longitudinal joints on the final lift shall be offset 12-inches from the plan lane lines.  The Contractor shall submit a Paving Plan for the Engineer's approval before starting this work.  The Paving Plan shall be submitted to the Engineer one week prior to initiating the paving operation.  The Paving Plan shall include but not be limited to the following:

1.	Manuals for the paving machine and the rollers.

2.	Traffic Control Plan for the paving operations.

3.	Traffic marking installation plan.

Asphalt concrete pavement over 3 inches in depth shall be spread and compacted in 2 layers.  The final lift in each defined project segment shall not be placed until all other mainline pavement throughout that segment has been placed and accepted, and all adjacent curb has been poured and cured for 7 days.  Final lift paving shall be progressive between the segments, and continuous within each segment whenever possible.  This final lift shall produce a 2-inch compacted depth.

401-3.12  Compaction.  In the second paragraph, delete from the first sentence: "...(94% at joints)...".

401-3.14  Pavement Samples.  Delete the third paragraph and substitute the following:  Each sample shall be one core, having a minimum diameter of 6-inches.

401-4.01  Method of Measurement.  Add the following:  Temporary pavement will be measured by the ton in accordance with Section 109.

401-4.02  Contract Price Adjustments. In the fifth paragraph, delete the last sentence.

In the eighth paragraph, add the following:  On projects consisting of more than 5000 tons, density evaluation shall be as follows:

For the purpose of evaluating the density of the material, a lot will be represented by fifteen test values three for each sublot.  A representative single density value for each sublot will be obtained by averaging the three sublot density test values.  This representative density shall become the density value reported for the sublot and the value used to evaluate individual lots for acceptance and price adjustment.

In the ninth paragraph, delete the second sentence and substitute the following:  Prior to computing a reduction in price, the validity of the failing test results for asphalt content and gradation tests shall be ascertained in accordance with ATM T-19.  Tests for density compliance will not be subject to ATM T-19 and no retests will be allowed.

401-5.01  Basis of Payment.  Add the following:  Anti-stripping additives will be paid on a contingent sum basis at a rate of $3.75 per 0.25 percent additive per ton of asphalt cement.

The labor material and equipment required for preparation of the existing surface prior to paving as described under Subsection 401-3.06, Preparation of Existing Surface, will be paid for separately under the respective items listed in the bid schedule.

Temporary pavement will be paid by the ton when placed as approved by the Engineer.  No payment will be made for the asphalt cement or anti-stripping additive, nor will price adjustments apply to this item.  Removal of temporary pavement will be paid under pay item 202(2), Removal of Pavement.

Add the following pay item:

Pay Item No.             Pay Item              Pay Unit

401(6)           Temporary Pavement           Ton

SECTION 402

TACK COAT

Special Provisions

402-3.04  Dilution of Asphalt Material.  Add the following:  CSS-1 Emulsified Asphalt used for tack coat may be diluted not more than 50 percent water by weight or volume at the Engineer's direction.  The determination of this ratio shall be accomplished by weighing the distributor prior to adding water, by sticking the tank, or other means suitable to the Engineer.  Emulsified asphalt as manufactured is approximately 60 percent oil and 40 percent water.  Any required dilution is additional water.

402-3.05  Application of Asphalt Material.  Modify the application rate given in the first paragraph from "0.05 to 0.10 gallons" to "0.05 to 0.15 gallons".

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-1.01 Description.  Add the following:  This work shall also consist of construction of cast-in-place retaining walls and precast concrete wall panels as shown on the plans.

501-2.01  Materials.  Add the following:  Reinforcing steel shall conform to the requirements of Section 503, Reinforcing Steel.

501-3.01  Proportioning.  Revise this subsection as follows:  In Table 501-1, Class A Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S and W concrete.  (9/1/89)

501-3.02  Batching.  Add the following to Item No. 5, Batching:  The Contractor shall furnish the Engineer with a list of all ingredients, their individual weights and the moisture content of the various aggregates, and the individual truck water meter reading when batched, for each truck load or batch of concrete supplied.  (9/1/89)

501-3.03  Backfill.  Add the following:  Where weepholes are shown on the plans for cast-in-place retaining walls, not less than one cubic foot of filter material securely tied in a burlap bag, or an acceptable substitute, shall be placed in the backfill at each hole.  The bag of filter material shall extend at least 0.5 feet above the hole.

501-3.11  Precast Concrete Wall Panels.  Add the following subsection:  Precast concrete wall panels shall be handled, stored, and installed in such a manner that there is no damage to any portion of the panel, including the facia.

501-4.01  Method of Measurement.  Delete the fourth paragraph and substitute the following:  Structural excavation required and the reinforcing steel utilized in the retaining walls will be subsidiary to the cast-in-place walls or precast wall panels.

Add the following:  The quantity of panels to be paid will be the actual square foot face area of all precast concrete wall panels accepted in place.  Cast-in-place retaining walls will be measured by the cubic yard of concrete placed.

501-5.01  Basis of Payment.  Add the following:  The aesthetic facia and anti-graffiti protection for the cast-in-place retaining walls and precast concrete wall panels will be paid under Items 510(1), Aesthetic Facia, and 510(2), Graffiti Protection, respectively.

Precast concrete wall panels will be paid for at the contract price per square foot and shall be full compensation for all material, labor, and equipment to cast and erect the panels.

Payment for Cast-in-Place Retaining Walls shall be full compensation for all excavation; furnishing and placing all temporary shoring; furnishing and placing all reinforcing steel; furnishing, hauling and mixing all concrete materials; placing, curing and finishing all concrete; all grouting; furnishing and placing porous backfill behind weepholes; furnishing and placing expansion joint material; and for all labor, tools, equipment and incidentals necessary for a complete retaining wall.

Add the following Pay Items:

Pay Item No.            Pay Item               Pay Item

501(8)     Precast Concrete Wall Panels   Square Foot

501(9)     Cast-in-Place Retaining Walls   Cubic Yard

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01  Description.  Add the following:  This work will include the epoxy-coating of appropriate reinforcing steel bars.  All reinforcing in the exposed vertical face of a retaining wall facing the roadway, and as noted on the plans shall be epoxy-coated.

503-5.01  Basis of Payment.  Add the following:  If epoxy coating the reinforcing steel is required, it will be a subsidiary obligation and no separate payment will be made.

SECTION 505

PILING

Special Provisions

505-2.01  Materials.  Add the following:

Retaining Wall 179+34-184+88        PZ22

Stay-in-Place Sheet Pile

The steel sheet piling shall be of the continuous interlock type and shall be furnished with suitable connecting and corner pieces if applicable.

505-3.09  Driving Piles.  Add the following:  The steel sheet piling shall be driven and cut off as specified under Section 505-3.11, Cutting Off Piles.  The steel sheet piling shall be driven with an impact pile driver that has a driving force of 12,000 - 24,000 foot-pounds.

The steel sheet piling shall be driven with equipment and by methods designed to minimize noise and disruption to any surrounding inhabitants, and to not cause damage or distress to nearby existing structures.  All sheet pile installation shall be conducted between 9:00 a.m. and 6:00 p.m.  No sheet pile installation shall be performed on Sundays or holidays.

505-3.15  Sheet Pile Stay-in-Place Forms.  Add the following subsection:  The stay-in-place sheet pile at the back of the concrete retaining wall acts as a form wall because of the existing structures near the retaining walls and the steep embankment.  The Contractor shall use extreme caution when installing the sheet pile.

505-4.01  Method of Measurement.  Delete the last paragraph and substitute the following:  In determining the area of sheet piling, the horizontal measurement will be made along the alignment of the sheet piling without any allowance for the structural shapes of the separate sections of the sheet piling.

SECTION 507

BRIDGE RAILING

Special Provisions

507-1.01  Description.  Add the following:  This work shall also consist of modifying the existing bridge rail expansion joints installed on the New Seward Highway Bridge, approximate Sta 112+00 to 114+25.

507-2.01  Materials.  Add the following to Item 1:  Bolts shall be A325.  Bolts, nuts, and washers shall be galvanized.

507-3.01  Construction Requirements.  Add the following:  All holes and disturbed surfaces caused by modifying the expansion joints shall be cold galvanized.  Expansion joint thru-bolts shall not be torqued more than 20 foot pounds to allow for joint movement.

507-4.01  Method of Measurement.  Add the following:  Measurement for payment to modify the bridge rail expansion joint shall be the actual number of expansion joint fittings modified.

507-5.01  Basis of Payment.  Add the following Pay Item:

Pay Item No.          Pay Item            Pay Unit

507(5)        Modify Bridge Rail          Each

Expansion Joint

Add the following Section:

SECTION 510

CONCRETE SURFACE TREATMENTS

Special Provisions

510-1.01  Description.  This work consists of providing an aesthetic facia on all cast-in-place and precast concrete walls.  All concrete retaining walls shall use form liners.  In addition, all walls and surfaces designated on the plans shall be protected with a sealer to prevent unwanted graffiti.

510-2.01  Materials. Contractor shall provide standard reusable, non-porous form liners conforming to the pattern for Burke Form Liner No. BG 312, Waterfall.

Anti-graffiti protection shall be a two step system designed specifically for this use consisting of a single component clear acrylic base coat over which a clear urethane finish coat are applied.  This material is not a sealer or vapor barrier.  No appreciable discoloration will be allowed.  The Contractor should be aware that these materials require special precautions, and shall be applied by trained personnel.

510-3.01  Aesthetic Facia.  Form liners shall be used in all retaining wall forms which have exposed surfaces.  The wall dimensions and concrete quantities provided on the plans are minimum and do not include allowances for the thickness of the form liners which must be accounted for by the Contractor.  The liners will cover the majority of the form with a minimum of 2-inches and a maximum of 12-inches between the edge of liner and the finished top of the wall, pathway or original ground grade at the bottom, and edge or expansion joints of the wall on the sides.  The Engineer shall approve the liner placement on the form prior to the concrete pour.

510-3.02  Graffiti Protection.  All concrete surfaces shall have set at least 28 days before any coatings are used.  The base coat shall be applied with a roller or sprayer in accordance with the manufacturers recommendations.  After 72 hours, two coats of the finish coat shall be applied.  Appropriate masking may be required.

510-4.01  Method of Measurement.  Aesthetic facia will be measured by the square foot.

Anti-graffiti protection shall be measured by the square foot of surface area.

510-5.01  Basis of Payment.

Payment will be made under:

Pay Item No.          Pay Item            Pay Unit

510(1)          Aesthetic Facia      Square Foot

510(2)       Graffiti Protection     Square Foot

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-2.01  Materials.  Add the following:  Corrugated Steel Pipe shall be AASHTO M36, Type I, unless otherwise specified on the plans.  The maximum height of cover for all pipes shall be 20 feet.

603-5.01  Basis of Payment.  Delete the last paragraph and substitute the following:  The unit bid prices will include all necessary excavation to the plan grade, and backfill with native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 203(1), Common Excavation.  Backfill and bedding to replace unsuitable material will be paid under Item 203(6), Borrow, Type A.

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-3.01  Construction Requirements.  Add the following to the fifth paragraph referencing the reconstruction of manholes:

5.	The work necessary to rotate the cone or reducing slab to align the manhole or inlet casting as detailed on the plans.  To align the access stairs, the Contractor will have the option of rotating the barrel sections or installing new steps.

Add the following:  Those manholes which by design must fall within the paved roadway surface shall be aligned such that the casting will not be in the wheel tracks of any driving lane, or the flow line of the gutter pan.

When new pipe is installed in an existing manhole, a hole shall be cleanly cut by approved means at the invert elevation given on the plans and 2-inches larger than the outside diameter of the new pipe.  The joint shall then be grouted with non-shrinking cement mortar.

Standard drainage structure steps shall be cast during structure pour or installed before concrete hardens.

Where the plans indicate the top of manhole elevations, the Contractor shall field verify the exact elevations.  Adjusting structures to the required grade will be subsidiary to the cost of installing, reconstructing or relocating manholes and inlets.

Any frames, grates, lids or reducing cones that are damaged during the relocation or reconstruction of an existing drainage structure shall be replaced at the expense of the Contractor.

Each precast concrete barrel section, precast concrete eccentric cone section, concrete adjusting ring, and manhole frame set, installed, reconstructed or relocated shall be sealed by use of a premolded plastic gasket pipe joint sealer manufactured in accordance with Federal Specifications SS-S-210A or AASHTO M-198.  Use and installation of premolded plastic gaskets for manhole construction shall be strictly in accordance with the manufacturer's printed instructions.  Gaskets shall be trimmed on the inside of the manhole to prevent the excess gasket material from entering the sanitary sewer lines.

Item 604(10), Adjusting Existing Inlet shall consist of raising the frame one foot or less and not requiring reconstruction of the inlet box.

604-4.01  Method of Measurement.  Add the following:  Frames, grates and lids will not be measured for payment unless otherwise noted.

Rotating barrel sections or installing new steps to align the manhole or inlet casting will not be measured for payment.

Each manhole required to be adjusted shall be measured for payment only once, when adjusted to final grade.  All other adjustments for intermediate construction activities shall be subsidiary to those activities.

604-5.01  Basis of Payment.  Add the following:  Frames, grates and lids are subsidiary to the drainage structure.

Delete Pay Item 604(1), Storm Sewer Manhole and Add the following Pay Items:

Pay Item No.          Pay Item            Pay Unit

604(1)    Storm Drain Manhole, Type __    Each

604(10)     Adjust Existing Inlet         Each

Delete the last paragraph and substitute the following:  Excavation and backfill necessary for manholes and inlets will be subsidiary to the cost of the drainage structure.

SECTION 606

GUARDRAIL

Standard Modifications

606-4.01  Method of Measurement.  Delete the last sentence of the first paragraph and substitute the following:  Double faced (and nested) installations will be measured by dividing the number of panels by two, before multiplying by the panel length.  Thrie beam transition pieces shall be measured by multiplying the number of panels by 6.25 feet and shall be paid for at the contract price for Thrie Beam Guardrail.  (5/12/89)

Special Provision

606-4.01  Method of Measurement.  Add the following:  Thrie beam transition bracket will not be measured separately for payment, but will be subsidiary to Item 606(2), Thrie Beam Guardrail.

SECTION 607

FENCES

Special Provisions

607-1.01  Description.  Add the following:  Work under this Section shall also include construction of wood fences to be built at the locations and to the dimensions indicated on the plans or as directed by the Engineer.

607-2.01  Materials.  Add the following:  The timber for the wood fence shall be as follows:

Posts         Douglas Fir-Larch              No. 2

Stringers     Douglas Fir-Larch              No. 2

Cedar Boards  Western Red Cedar     1-inch nominal

(rough sawn both sides)    thickness

The posts and stringers shall be treated in accordance with Section 714, Preservatives and Preservative Treatment Processes for Wood Materials.  Any field cutting of post ends shall require an application of pentachlorophenol.  All cedar boards shall be coated with a creosote based stain or 20 percent polyurethane base semi-transparent stain to be applied at a rate of one (1) gallon per 100 square feet.  The stain shall be Red Cedar in color, as approved by the Engineer.  The stain shall be furnished by a manufacturer and a manufacturers certificate attesting to the quality of the stain shall accompany the shipment.  The Contractor should be aware that some preservatives require application by trained personnel.

607-4.01  Method of Measurement.  Add the following:  The fence pay item will be measured by the linear foot.

607-5.01  Basis of Payment.  Add the following Pay Item:

Pay Item No.          Pay Item            Pay Unit

607(8)               Fence           Linear Foot

SECTION 608

SIDEWALKS

Special Provisions

608-1.01  Description.  Add the following:  This work also consists of construction of asphalt median and asphalt driveway paving in reasonably close conformity with the plans.

Bus shelter pads shall be placed at those bus stops indicated on the plans or as directed by the Engineer.

Concrete sidewalk or asphalt sidewalk shall include the paved apron around pedestrian push-buttons and fire hydrants, and the approach to the bus stop shelter pads.

Concrete utiliwalk lids shall be adjusted as indicated on the plans.

608-2.01  Materials.  Add the following:  AC-5 Asphalt Cement shall be used for the asphalt concrete pavement mix for sidewalks, driveways, and medians and shall conform to Subsection 702-2.01, Asphalt Cements.  Asphalt concrete aggregate shall conform to Subsection 703-2.04, Aggregate for Plant Mix Asphalt Pavement, for Asphalt Concrete, Type III.

Treated plywood shall conform to the requirements of Section 713, Structural Timber, Lumber and Piling and Section 714, Preservatives and Preservative Treated Processes for Wood Materials.  Joint sealant shall conform to Section 705-2.02, Joint Sealer.

608-3.01  Concrete Sidewalks.  Delete the sixth paragraph, and substitute the following:

Joints.  Transverse expansion joints shall be filled with 1/4-inch thick premolded expansion joint filler and shall be placed at intervals not to exceed 30-feet.  The sidewalk shall be divided into sections by contraction joints formed by a jointing tool or other acceptable method.  These contraction joints shall be placed every 10-feet and shall extend into the concrete at least one third of the depth and shall be approximately 1/8-inch wide.

608-3.03  Asphalt Sidewalks, Driveways and Medians.  Add the following Subsection:  Asphalt sidewalks, driveways and medians shall be constructed in accordance with Subsection 608-3.02, Asphalt Sidewalks.

608-3.04  Adjust Utiliwalk Lids.  Add the following Subsection:  Utiliwalk lids shall be adjusted as indicated on the plans.  A 1/2-inch bead of joint sealer shall be applied to the utiliwalk bearing surfaces and a 1-inch thick piece of treated plywood shall be seated with uniform pressure into the sealer.  No more than 100 feet of utiliwalk shall be opened at any time.  The utiliwalk shall be completely closed at the end of each day.  Contractor shall replace all lids that are damaged or broken during adjustment.

608-4.01  Method of Measurement.  Add the following:  Asphalt cement utilized in asphalt sidewalks, driveways, and medians will not be measured separately.

Additional asphalt pavement used for matching existing surfaces such as paved parking lots behind a new sidewalk will be measured and paid as Pay Item 608(6), Asphalt Sidewalks, Driveways and Medians.

Bus stop shelter pads will be measured by each unit installed and accepted by the Engineer.

Adjust utiliwalk lids will be measured by the linear foot of lids adjusted and approved by the Engineer.

No deduction from measurement of concrete sidewalk or asphalt sidewalk, driveway and medians will be made for curb ramps.

608-5.01  Basis of Payment.  Add the following:  Asphalt sidewalk, driveway, and medians will be paid by the ton of asphalt mixture, complete in place.  Excavation and bed course materials will be furnished, placed, and paid under their respective bid items.

Add the following Pay Items:

Pay Item No.           Pay Item           Pay Unit

608(6)         Asphalt Sidewalk,         Ton

Driveway, and Median

608(7)       Bus Stop Shelter Pads      Each

608(8)       Adjust Utiliwalk Lids  Linear Foot

SECTION 609

CURBING

Special Provisions

609-3.01  Cast-in-Place Concrete Curbing.  Add the following:  Where Control (line and grade) for new curb is based on the existing curb, the Contractor shall adjust his curb forms to remove apparent irregularities before placing the concrete.  Forms or stringline shall be approved by the Engineer prior to placing concrete.  Reference Section 642, Construction Surveying and Appendix B, Construction Surveying Requirements For Surveying Requirements.

SECTION 615

STANDARD SIGNS

Special Provisions

615-1.01  Description.  Add the following:  Work under this section shall also consist of furnishing sign panels, sign posts and sign foundations at the locations shown on the plans.

615-2.01  Materials.  Add the following to the end of the first sentence of the fifth paragraph, "and the Alaska Traffic Manual."

Delete the first sentence of the seventh paragraph and substitute the following:  All metal sign posts other than perforated steel tubes and wide flange posts shall be equipped with slip bases, unless multi-directional breakaway load concentration couplings are called for on the plans.  Wide flange posts shall always be equipped with multi-directional breakaway load concentration couplings.

615-3.01  Construction Requirements.  Add the following to the sixth paragraph:  Salvaged signs shall be delivered to the State Maintenance Yard, 5700 Tudor Road, Anchorage, Alaska.

The salvaged sign panels shall be removed from posts and mounting brackets.  All posts and foundations shall be removed to at least a 1-foot depth below finish grade.

615-3.02  Sign Placement and Installation:.  Add the following:  Existing signs shall not be removed until the new signs have been installed.  If necessary, they may be temporarily relocated to a location approved by the Engineer.  They shall be maintained until they are no longer needed.

615-4.01  Method of Measurement.  Add the following:  New sign panels, sign posts, and sign foundations will be installed, measured and paid under separate items.

New sign panels shall consist of furnishing all labor, equipment, and materials required to install new sign panels at the locations shown on the plans.

New sign posts shall consist of furnishing and installing or replacing pipes or perforated steel tubes at the locations shown.

New sign foundations shall consist of furnishing all labor, equipment, and materials required to install post foundations in accordance with Standard Drawings S-30 and S-34 at the locations shown on the plans.

When an all new sign assembly is called for on the plans, each component of work required to complete the installation will be paid for under their respective items, i.e. sign panel, post, or foundation.

615-5.01  Basis of Payment.  Add the following:  Maintaining existing signs until they are no longer needed and temporary relocation of existing signs will not be paid for directly, but will be subsidiary to other 615 signs.

Payment for sign panels, sign posts and sign foundations will be made for each panel, post or foundation complete in place and accepted.

Payment will be made under:

Pay Item No.           Pay Item           Pay Unit

615(8)            Sign Panels       Square Foot

615(9)            Sign Posts             Each

615(10)         Sign Foundations         Each

SECTION 618

SEEDING

Special Provisions

618-1.01  Description.  Delete this subsection and substitute the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded.  This work shall consist of tracking the soil, followed by the application

of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01  Materials.  Add the following to the list of material specifications:

Mulch                      Section 727-2.01

618-3.01  Soil Preparation.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be covered with topsoil in accordance with Section 620, and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as topsoil is placed on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach onto the wetlands.  The performance of this work is incidental to seeding and will not be paid for directly.

618-3.03  Application Method.  In the first sentence of subparagraph b. under numbered paragraph 1., Hydraulic Method, delete the following:  "Item 619(1),".

Add the following:  Seed, mulch and fertilizer shall be applied as shown in the following table per 1,000 square feet.  If the hydraulic method for seed and mulch is used, it shall be made in one application.  The mulch rate shown is a minimum, and may be increased in accordance with the manufacturers recommendations.  All fertilizer shall be applied by the hydraulic method.

Application

Item           Ingredients           Rate Lbs/MSF

Seed Mix    Kentucky Bluegrass (Nugget)    0.75 lb.

Red Fescue (Arctared)          0.25 lb.

TOTAL       1.00 lbs/MSF

Mulch                                         35.0 lbs.

Fertilizer     20-20-10                       12.0 lbs.

The Contractor shall not remove the required tags from the seed bags.

618-3.04  Maintenance of Seeded Areas.  Add the following:  A reapplication of fertilizer shall be applied with water between May 1 and September 15 of the year following seeding at a rate of one-half the initial application.

618-4.01  Method of Measurement.  Delete the second paragraph and substitute the following:  Seeding by the pound will be the number of pounds of seed (Dry Measure) accepted in place.  The amount of mulch and fertilizer used in this work, including any required reseeding will be subsidiary to seeding and will not be measured separately for payment.

Delete the last paragraph.

618-5.01  Basis of Payment.  Add the following:  Fertilizer and mulch as described above, will not be paid for directly, but will be subsidiary to Item 618(2) Seeding. Topsoil shall be paid under Item 620(1), Topsoil.

(6/1/90)

SECTION 620

TOPSOIL

Special Provisions

620-2.01  Materials.  Add the following:   Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

620-4.01  Method of Measurement.  Add the following:  Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(6/1/90)

SECTION 626

SANITARY SEWER SYSTEMS

Special Provisions

626-1.01  Description.  Add the following:  For the purposes of these Special Provisions "AWWU" shall mean the Anchorage Water and Wastewater Utility, Engineering Construction Section at (907) 564-2785.  This work shall include the installation and testing of sanitary sewer systems for acceptance by AWWU.  The Contractor shall also provide as-built drawings in accordance with the conditions prescribed herein.

626-2.01 Materials.  Delete this Subsection in its entirety and substitute the following:

Materials shall conform to the following:

1.	Sanitary Sewer Conduit

Ductile Iron Waterline          707-2.05

2.	Service Pipe

Ductile Iron                    707-2.05

626-3.01  Construction Requirements.  Delete the words "or flexible connection" from the third paragraph.

Delete the seventh paragraph and add the following:  Where sewer conduit constructed under this contract approaches within 10 feet horizontal clearance and is above or less than 3 feet below an existing or a new watermain, the sewer conduit shall be constructed with cast iron or ductile iron pipe for a distance of 10 feet perpendicular to and on each side of the watermain.  The Contractor shall stagger the joints for the sanitary sewer conduit such that no joint shall be closer than 9 feet from the centerline crossing of the water and sewer conduits.  In addition, the vertical separation between the water and sewer conduits shall be 18 inches minimum, outside of pipe to outside of pipe.

Add the following:

Required Clearance from Water Mains.  When it is necessary to construct a water conduit crossing below a sewer conduit or within a vertical distance of 3 feet above the sewer conduit (less than 24 inches diameter), and the sewer main is not cast or ductile iron, and provided no joint is within 3 feet horizontally of the crossing or where the Engineer may direct, the sewer conduit shall be encased in a minimum thickness of 4 inches of concrete for a distance of 10 feet perpendicular to and on each side of the water conduit.

Wire fabric or other types of wire mesh, approved by the Engineer, shall be placed around the sewer prior to encasement with concrete to minimize cracking.  Construction of concrete encasement shall be in accordance with the applicable details on the plans.

Ductile iron encasement may be substituted for concrete when approved by the Engineer.

Relocate Existing Water Main.  Where an existing water main crosses the location of the proposed sanitary sewer at an elevation to interfere with the construction of the sewer, the water main shall be raised or lowered sufficiently to permit 18 inches minimum clearance from the sewer.  The Contractor may employ either of the following methods for raising or lowering a water main.  He may raise or lower lengths of the water main as necessary on either side of the proposed sewer to allow the main to pass under or over the sewer, providing the deflection at any joint does not exceed one-half of the pipe manufacturer's recommendations, or the water main may be raised or lowered using 4 pipe bends not to exceed 22 degrees.  In special cases only, and when approved by the Engineer in advance, 45 degree bends may be used.  The method of lowering and materials to be used shall be approved by the Engineer prior to commencing work.  The Contractor shall give 48 hours notice to the Engineer, prior to any planned water shut-off.

Water lines 2 inches in diameter and smaller shall not be construed as water mains.  Any necessary lowering of water lines 2 inches and smaller shall be included under the conditions set forth in the Special Provisions for the moving and relocation of utilities occupying space within the area of construction.  With the approval of the Engineer, the Contractor may lower water lines 2 inches in diameter and smaller, but separate payment shall not be made for such lowering.  The cost shall be incidental to other sanitary sewer items.

Temporary Sewer Service.  Where it is necessary to disrupt sanitary sewer service, affected property owners, renters and business shall be given 48 hours notice of the disruption.  Temporary sewer service shall be provided when a disruption in service will exceed eight (8) hours in any 24 hour period.

Suspension of Work.  AWWU through the Engineer reserves the right to suspend the sanitary sewer installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

Connections to Existing Manholes.  Connections to existing manholes shall be made in an accurate and smooth manner, shall be tight and have smooth flow surfaces and curves.  The invert shall be brought into the existing manhole at the elevation shown on the drawings.  An expanding type grout (jet set or equal) shall be used in connecting sewer pipe to existing manhole.  The downstream pipe in existing manholes shall be screened to prevent entry of mortar or other debris from entering the system.

Where a connection is made to an existing sanitary sewer manhole, the base shall be broken out if necessary to form a smooth channel in accordance with the construction requirements of a new manhole.  Connections to existing sanitary sewer manholes will be allowed only after all portions of the Contractor's Work tributary to the connection point has been cleaned and flushed, inspected and tested.  Under certain conditions, connections prior to the completion of the system may be permitted subject to the Engineer's prior written approval and the provision of suitable and adequate debris and sand traps and sumps upstream from the connection.

Sanitary Sewer Conduit.  The outside of all ductile iron and cast iron pipe, fittings and other appurtenances used in sewer conduit construction shall be encased with one (1) layer of 8-mil thick (0.2mm) polyethylene film.  The polyethylene encasement shall be installed using any of the following three methods:

Method A.

1.	Cut polyethylene tube to a length approximately 2-feet longer than the length of the pipe section.  Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

2.	Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

3.	After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube.  Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place.  Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up

the slack width to make a snug, but not tight fit along the barrel of the pipe, securing the fold at quarter points.

4.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method B.

1.	Cut polyethylene tube to a length approximately 1-ft shorter than that of the pipe section.  Slip the tube around the pipe, centering it to provide 6-inch of bare pipe at each end.  Take up the slack width at the top of the pipe to make a snug, but not tight, fit along the barrel of the pipe, securing the fold at quarter points; secure the ends as described in Method A.

2.	Before making up a joint, slip a 3-ft length of polyethylene tube over the end of the preceding pipe section, bunching it accordion-fashion lengthwise.  After completing the joint, pull the 3-ft length of polyethylene previously installed on each adjacent section of pipe by at least 1-ft; make each end snug and secure as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method C.

1.	Cut polyethylene sheet to a length approximately 2-ft longer than that of the pipe section.  Center the cut length to provide a 1-ft overlap on each adjacent pipe section, bunching it until it clears the pipe ends.  Wrap the polyethylene around the pipe so that

it circumferentially overlaps the top quadrant of the pipe.  Secure the cut edge of polyethylene sheet at intervals of approximately 3-ft.

2.	Lower the wrapped pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at joints to facilitate installation of the polyethylene.  After completing the joint, make the overlap and secure the ends as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Bedding of Sanitary Sewer Conduit.  All sewer conduit shall be bedded in material conforming to the requirements of Selected Material, Type A, and shall also pass the 2-inch sieve.

Removed or Abandoned-in-Place Sanitary Sewer Conduit.  Any existing sanitary sewer conduits, or appurtenances designated on the plans or directed by the Engineer to be abandoned-in-place shall be accomplished as an incidental item of construction.  Whenever or wherever an existing sanitary sewer conduit is abandoned-in-place, the Contractor shall empty the pipe of all waste, fill the pipe with sand and plug the ends.  Asbestos concrete pipe shall be either crushed or removed.  In the event of cracked or crushed lines, the Contractor shall excavate to the next joint of pipe and install the plug.  Existing sanitary sewer conduit and all other contaminated material to be removed shall be disposed of at the Municipality of Anchorage Sanitary Land Fill at the Hiland Drive Interchange.  There will be no separate payment for disposal of the contaminated material at the land fill.

Disconnect and Reconnect Sanitary Sewer Service Connections.  In the course of construction, the Contractor will encounter sanitary sewer service connections.  The Contractor shall disconnect at the main those sanitary sewer service lines identified on the plans for removal, and remove upstream portions of the service line.  This item of work shall include all materials, excavation, backfill, mechanical compaction, disconnection, reconnection and appurtenant materials installation.  Reconnection includes installation of new Sewer Service including appurtenant fittings, cleanouts if required, and taps.  Minimum slope for new sewer service shall be 1/4 inch per foot.  Sewer services shall be rejoined to existing services where cover is 5.5 feet or more and all sewer service lines insulated where less than 8-foot cover.  All required fittings for sanitary sewer service connections shall be ductile iron, "Ty-seal" cast iron or equivalent unless otherwise noted on the plans or directed by the Engineer.

Verification of Existing Utilities.  At a sufficient distance prior to encountering a known obstacle or pipe or tying into an existing pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled.

The cost incurred for removal and realignment of backfilled pipe sections due to improper verification methods shall be borne by the Contractor.

626-3.02  Testing.  Delete in its entirety and substitute the following:  The Contractor shall clean and flush all sanitary sewer pipe installed prior to testing and final inspection.  He shall notify the Engineer 48 hours in advance (two working days) prior to any test.  The Engineer and AWWU shall be present during all tests.  Two (2) hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or cancelled.

The Contractor shall furnish all tools, equipment, and labor necessary to complete the tests and shall verify from his own observations, or preliminary tests, that each line conforms with this specification before requesting AWWU to observe and record the actual leakage.

If the pipe installation fails to meet test requirements, the Contractor shall determine at his own expense the source of leakage, and he shall repair (if the extent and type of repairs proposed by the Contractor are acceptable) or replace all defective materials or

workmanship.  The completed pipe installation shall meet the requirements of this Section before being considered acceptable.

The Engineer may require the Contractor to repair obvious leaks even though the total length of the test section falls within the maximum allowable leakage of the test used.

No test section shall exceed 1000 lineal feet, unless approved by AWWU in writing.

All gravity sanitary sewer pipe installed shall be subject to either an infiltration test or an exfiltration test.  In those areas where, in the opinion of AWWU, the water table is high enough to subject the pipe to a satisfactory infiltration test, it is not anticipated that an exfiltration test shall be required.  In checking leakage, there will be no allowance made for external hydrostatic head.  Where in the opinion of AWWU the water table is not high enough to provide a satisfactory infiltration test, an exfiltration test shall be required.

The type of test, either infiltration or exfiltration, shall be determined by AWWU.  The Contractor shall have the option of choosing only one method (air or water) of testing for each section tested.  All testing shall be considered a subsidiary obligation under this Contract and extra payment will not be allowed for this portion of work.

All wyes, tees, or ends of side sewer stubs and service connections shall be plugged or capped, and the plug or cap shall be securely fastened to withstand the internal test pressures.  Such plugs or caps shall be readily removable and their removal shall provide a socket suitable for extending the lateral connection.

Infiltration Test.  Infiltration testing may be allowed at AWWU's option when the natural ground water table is 6-feet above the crown of the higher end of the test section.  The maximum allowable limit for infiltration shall not exceed the rate of 50 gallons per inch diameter per mile per 24 hours.

Exfiltration Test  (Using Water).  On completion of a section of sanitary sewer between manholes, or otherwise, the ends of all pipe shall be plugged, including service connections, and the pipe subjected to hydrostatic pressure.  Generally all testing is to be conducted after backfilling, prior to resurfacing, and after service connections are made.

A minimum head of 6-feet of water above the crown at the upper end of the test section shall be maintained for a period of 4 hours, during which time it will be presumed that full absorption of the pipe body has taken place and thereafter for a further period of 1 hour for the actual test of leakage.  During this 1 hour period the measured loss shall not exceed the rate of 50 gallons per inch diameter per mile per 24 hours.

Exfiltration Test (Using Air).  The Contractor shall furnish all facilities and personnel for conducting the test under the observation of AWWU.  The equipment and personnel shall be subject to their approval.  The Contractor may desire to make an air test prior to backfilling for his own purpose.  However, the acceptance air test shall be made after backfilling has been completed, and compacted.

Immediately following the pipe cleaning, the pipe installation shall be tested with low pressure air.  Air shall be slowly supplied to the plugged pipe installation until the internal air pressure reaches 4.0 pounds per square inch greater than the average back pressure of any ground water that may submerge the conduit.  At least 2 minutes shall be allowed for temperature stabilization before proceeding further.

The pipeline shall be considered acceptable when tested at an average pressure of 4.0 psi greater than the average back pressure of any ground water that may submerge the pipe, if:

The total rate of air loss from any section tested in its entirety between manholes or between manhole and cleanout structures does not exceed 2.0 cubic feet per minute, or the following table may be used as a guideline for satisfactory test by air for pipe sizes shown:

Pipe Diameter              Allowable Pressure Drop

in Ten (10) Minutes

8-inches                         2.7 psi

Pressure gauges shall be incremented in not more than 1/2 pound increments for accurate tests.

Safety braces shall be required to hold plugs in place and to prevent the sudden release of the compressed air.  Due to the large forces exerted by an escaping plug during the testing of the pipe, workmen shall not be allowed in the manholes in which plugs have been placed while tests are being conducted.  The Contractors testing equipment shall be arranged in such a manner that a pressure relief device will prohibit the pressure in the pipeline from exceeding 10 psi.

Check of Line and Grade.  After backfilling and cleaning, but before final acceptance, all sanitary sewer mains, excluding service connections, may be checked for line and grade by closed circuit television.  A full circle of light must be seen and no pipe misplaced in line or grade.  Any excess deviation shall be corrected by the Contractor at his expense prior to final acceptance of the pipe line.

The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a semi-final inspection of the project.  This inspection will be performed in the presence of the Engineer, AWWU, and the Contractor.  Copies of a list of deficiencies, if any, indicated by the inspection will be furnished to the Contractor by the Engineer for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and at that time an acceptance inspection will be performed.

The Contractor shall take precautions to allow no sewage to enter the new sewer conduit until it has been inspected, tested and accepted for operation and maintenance by AWWU.  Any deviations shall require written approval.  The new sewer line may be tested and inspected in incremental runs, manhole to manhole.

626-3.03  As-Builts of Plans and Working Drawings.  Add the following subsection:  A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as it is actually installed.  This as-built information shall be recorded on a print of the plans affected, and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed.  Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When this sanitary sewer system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance by the owning Utility.

626-4.01  Method of Measurement.  Add the following:  Sanitary sewer pipes abandoned-in-place will not be measured for payment.

Disconnect and reconnect sewer service connection will be measured as units complete in place including disconnection from the existing sewer main and reconnection to the new sewer main.

626-5.01  Basis of Payment.  Delete the last sentence of the first paragraph and add the following:  The unit bid prices will include all necessary excavation to the plan grade, and backfill with native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 203(1), Common Excavation.  Backfill and bedding to replace unsuitable material will be paid under Item 203(6), Borrow, Type A.

No separate payment for providing temporary sewer service or providing pumping of effluent during construction will be made but will be considered incidental to the sewer improvement.

Mechanical plugs - will be considered incidental to the sewer improvement.

No separate payment for connecting to existing manholes will be made but will be considered incidental to the sewer improvement.

Payment for sewer manholes will be made under Item 604(2), Sanitary Sewer Manhole.

Add the following pay items:

Pay Item No.          Pay Item            Pay Unit

626(2)      Disconnect and Reconnect

Sewer Service           Each

626(3)      Sanitary Sewer As-Builts    Lump Sum

SECTION 627

WATER SYSTEM

Special Provisions

627-1.01  Description.  Add the following:  For purposes of these Special Provisions, AWWU shall mean the Anchorage Water and Wastewater Utility Engineering Construction Section at (907) 564-2785.  This work shall include the installation, testing, flushing, and chlorination or hand cleaning of water systems for acceptance by AWWU.  The Contractor shall also provide as-builts in accordance with the conditions prescribed herein.

In conjunction with working around and/or adjusting the AWWU water valves, the Contractor shall exercise due care.  Prior to commencement of work by the Contractor, AWWU shall check and correct deficiencies which may exist in any valve or valve box.  The Engineer and Contractor shall witness the condition and location of each valve or valve box.  Failure to partake in the inspection by the Contractor will result in his forfeiting all rights to deny damages at a later date during the course of the work.  Notice that the Contractor is ready for the above inspection shall be in writing to AWWU and shall be submitted giving at least 48 hours notice.  The Contractor shall furnish a copy of the notice to the Engineer.

It shall be the Contractors responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction.  If at any time after the inspection as outlined above

AWWU finds a valve or valve box damaged or rendered inoperable by the Contractor, the Contractor shall repair them at his own expense.

627-3.01  General Construction Requirements.  Add the following before the first paragraph:  AWWU through the Engineer reserves the right to suspend the water system installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary correction.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

The Contractor shall furnish to the Engineer complete installation drawings for the project prior to fabrication.  All restrained joint areas shall be detailed to include fittings, piping and deflection points.  The Contractor shall provide design calculations, prepared and sealed by a licensed professional engineer, registered in the State of Alaska, for all restrained joint areas to assure adequacy, ability to resist longitudinal forces and compliance with the Contract Documents.

If construction or excavation require the removal of any existing privately owned facilities on the provided water easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed 2 weeks.

Add the following to the third sentence of the third paragraph:  "or so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled."

Delete the fifth, sixth and seventh paragraphs and substitute the following:  Prior to removing or disrupting service to fire hydrants, the Contractor shall contact the Anchorage Fire Department, Chief Dispatcher at 267-4950 and Deputy Fire Chief at 267-4935 at least 48 hours in advance of any construction.

Additionally, the Contractor shall notify all affected property owners, the Engineer, and AWWU 48 hours prior to interruption of any water service.  The Contractor shall provide temporary service to all those property owners with disrupted water service if the interruption exceeds 8 hours.

Prior to water system installation, the Contractor shall submit to the Engineer a detailed plan for the installation of the new water systems and for removal/abandonment of existing water systems that are to be removed or abandoned for review prior to commencement of work.  The plan shall be of sufficient detail to clearly indicate the proposed work sequence, schedules, and disruption of water service.  This plan shall also be reviewed and approved by AWWU Treatment Division prior to construction.  This work shall be done on weekends or at night to limit disruption of service.  AWWU Treatment Division can be contacted at 338-3870.

The Contractor may shut down the water supply to perform construction.  The Contractor shall notify AWWU 30 days prior to the anticipated date of system shutdown and again 48 hours prior to the exact date of system shutdown.  If for any reason the system shutdown exceeds the time requirement as established by AWWU below, the Contractor shall provide for alternate water supply with sufficient pressure to provide for fire and full service flows.  If alternate supply is required, this work shall not entitle the Contractor to extra payment for the costs incurred.

AWWU SHUTDOWN REQUIREMENTS

1.	36" pipeline west of new valve at approximately Sta 287+86.

24 HOURS

2.	36" pipeline east of new valve at approximately Sta 287+86

96 HOURS

3.	8" pipeline on Kingston

8 HOURS

The Contractor shall provide any necessary fittings, valves, temporary connections or appurtenances necessary

in order to maintain the water distribution system.  Any costs involved in service changeovers and providing temporary water service shall be subsidiary.  The Contractor shall be responsible for all damages incidental to interruption of service that may be due to his operations.

Add the following to the eighth paragraph:  Concrete thrust blocks or tie back rods of the type shown on the plans shall be installed where the pipe line terminates or changes alignment, utilizes a tee, cross, bend, reducer, or similar fitting.  Either poured-in-place or precast thrust blocks are acceptable if the minimum base area is sufficient as shown on the plans.  Concrete for the thrust blocks shall be Class A.  If the Contractor elects to use poured-in-place thrust blocks, all pipe and fittings exposed to concrete shall be double wrapped with 4-mil Visqueen or equal, prior to placement of the concrete.  Poured-in-place thrust blocks shall be cured a minimum of 7 days prior to the application of any hydraulic loads.

Add the following:

Disconnect Water Service.  In the course of construction, the Contractor will encounter water service pipe requiring disconnection from mains.  The Contractor shall disconnect the existing water service, as required by AWWU and to the satisfaction of the Engineer.  This item of work shall include all materials, excavation, disconnection, backfill, and mechanical compaction for completed services in-place.

Water Service Connection.  This item of work shall include all materials, excavation, installation, bedding, backfill, and mechanical compaction for completed water service connections.  The water service connection includes a new corp stop at the water main, new continuous water service line to the curb stop and a new curb stop and key box at the property line.  This work will also include all necessary work and materials necessary to adjust or replace the existing on property water service between the key box and building being served in the areas where the existing ground surface has been lowered as part of this contract.  The intent is that the water service be reconstructed so that a minimum of 10 feet of cover remains over it after all surface regrading and contouring required by this contract is completed.  All service lines 2 inches and smaller shall be constructed of seamless, soft drawn, Type "K" copper.  All service lines larger than 2 inches shall be constructed of ductile iron pipe, with two-3/4 inch tie rods installed on each service line from the main to the property line.  For connection of service lines larger than 2 inches, a minimum of 48 hours shall be provided prior to the required time of completion.  Splices of copper service line are not allowed between the corp stop at the water main and the curb stop at the property line.  Splices, if necessary, on property will be made using flanged fittings.

Rights In and Use of Materials Found on the Work Site.  Unless specifically addressed otherwise in these special provisions, all existing water valves, tees, bends, and conduit (including ductile iron pipe) removed but not reinstalled, and declared "salvageable materials" shall become the property of the Contractor.

Final Acceptance.  The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a pre-final inspection of the project.  This inspection will be performed in the presence of the Engineer, AWWU and the Contractor.  Copies of a list of deficiencies, if any, indicated by this inspection will be furnished to the Contractor for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and an acceptance inspection will be performed.

627-3.02  Installation of Conduit.  Add the following to the second paragraph:  However, at a sufficient distance prior to encountering a known obstacle or tying into an existing pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled.  The costs incurred for removal and realignment of backfilled conduit sections due to improper verification methods shall be borne by the Contractor.

Delete the eighth paragraph and substitute the following:  Deflections from a straight line or grade, as required by vertical curves, horizontal curves, or offsets shall not exceed 50 percent of the manufacturer's recommended maximum deflection.  If the alignment requires deflection in excess of the above limitations, the Contractor shall furnish special bends to provide angular delections within the limits allowable.  Wherever possible, the Contractor shall achieve the desired deflection by taking advantage of reduced deflections over multiple joints.  Short-radius curves and closures shall be formed by shorter lengths of pipe, bevels, or fabricated specials.

A maximum 0.2-foot deviation from design alignment and elevation will be allowed.  Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed.  All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the pipe and not by blocking or wedging up.

The Contractor shall have survey instruments such as transit and level for transferring alignment and grades from offset hubs.  He shall also have in his employ a person who is qualified to use such instruments and who shall have the responsibility of placing and maintaining such construction guides.  The Contractor shall furnish to the Engineer a copy of the surveyor's record notes for the newly-installed conduit and appurtenances.  The practice of placing backfill over a section of conduit to provide a platform for the instruments shall be subject to the approval of the Engineer.

Conduit that has the grade or joint disturbed after laying shall be taken up and relaid.  Water shall be kept out of the trench until the jointing is completed

Add the following:

Conduit Joints.  Conduit that has the grade or joint disturbed after laying shall be taken up and relaid.  Water shall be kept out of the trench until the jointing is completed.

The Contractor has the option of using either mechanical or push-on joints for conduit installed in trenches, except in those areas where restrained joints are required.  All joints shall conform to the requirements of AWWA C-600.

The Contractor will be required to use mechanical joints on all fire hydrant leads.  The Engineer may check any or all mechanical joints to assure proper torque as specified by the manufacturer.

Two electrical continuity straps shall be installed on each side joint for pipes less than 12-inches in diameter.  Straps are to be welded to a clean, dry surface.  All welds and uncoated surfaces shall be coated with a coal tar pitch to the satisfaction of the Engineer.

Conduit Wrap:  The outside of all ductile iron and cast iron pipe, fittings, valves and other appurtenances used in water line construction  shall be encased with one (1) layer of 8-mil thick (0.2mm) polyethylene film.  The polyethylene encasement shall be installed using any the following three methods:

Method A.

1.	Cut  polyethylene  tube  to  a  length approximately 2-feet longer than the length of the pipe section.  Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

2.	Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

3.	After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube.  Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place.  Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up the slack width to make a snug, but not fit along the barrel of the pipe, securing the field at quarter points.

4.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open,

wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method B.

1.	Cut  polyethylene  tube  to  a  length approximately 1-ft shorter than that of the pipe section.  Slip the tube around the pipe, centering it to provide 6-inch of bare pipe at each end.  Take up the slack width at the top of the pipe to make a snug, but not tight, fit along the barrel of the pipe, securing the fold at quarter points; secure the ends as described in Method A.

2.	Before making up a joint, slip a 3-ft length of polyethylene tube over the end of the preceding pipe section, bunching it accordion-fashion lengthwise.  After completing the joint, pull the 3-ft length of polyethylene over the joint, overlapping the polyethylene previously installed on each adjacent section of pipe by at least 1-ft; make each end snug and secure as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method C.

1.	Cut polyethylene sheet to a length approximately 2-ft longer than that of the pipe section.  Center the cut length to provide a 1-ft overlap on each adjacent pipe section, bunching it until it clears the pipe ends.  Wrap the polyethylene around the pipe so that it circumferentially overlaps the top quadrant of the pipe.  Secure the cut edge of polyethylene sheet at intervals of approximately 3-ft.

2.	Lower the wrapped pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at joints to facilitate installation of the polyethylene.  After completing the joint, make the overlap and secure the ends as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Thrust Restraint.  Concrete thrust blocks, tie back rods or restrained joints of the type shown on the plans, or specified herein, shall be installed where the pipe line changes alignment utilizing a tee, cross, bend, or similar fitting.

Conduit ends left for future connections shall be plugged or capped and anchored as shown on the plans, or as directed by the Engineer.

Relocate Existing Water Main.  Where an existing water main crosses the location of the proposed sanitary sewer at an elevation to interfere with the construction of the sewer, the water main shall be raised or lowered sufficiently to permit 18 inches minimum clearance from the sewer.  The Contractor may employ either of the following methods for raising or lowering a water main.  He may raise or lower lengths of the water main as necessary on either side of the proposed sewer to allow the main to pass under or over the sewer, providing the deflection at any joint does not exceed one-half of the pipe manufacturer's recommendations, or the water main may be raised or lowered using a pipe bends not to exceed 22 degrees.  In special cases only, and when approved by the Engineer in advance, 45 degrees bends may be used.  The method of lowering and materials to be used shall be approved by the Engineer prior to commencing work.  The Contractor shall give 48 hours notice to the Engineer, prior to any planned water shut-off.

Water lines 2-inches in diameter and smaller shall not be construed as water mains.  Any necessary lowering of water lines 2-inches and smaller shall be included under the conditions set forth in these Special Provisions for the moving and relocation of utilities occupying space within the area of construction.  With the approval of the Engineer, the Contractor may lower water lines 2-inches in diameter and smaller, but separate payment shall not be made for such lowering.  The cost shall be included under Pay Item 204(1), Structure Excavation for Conduits and Minor Structures.

627-3.05.  Delete the first paragraph and substitute the following:  Valve boxes shall be installed over the valves as shown on the plans, with base section centered over the operating nut of the valve and resting on well compacted backfill.  Top section shall be so set as to allow equal movement above and below finished grade, final elevation to be 1/4-inch below finished grade of pavement unless otherwise directed.  Top of base section shall be approximately on line with nut at top of valve stem, and the entire assembly shall be plumb.

Add the following after the second paragraph:  In areas where running sand is encountered, provisions shall be made to restrict sand from entering the bottom section of the valve box.

The Contractor shall expose all valve boxes for pre-final and final inspection.  After final inspection of the valves located in unpaved areas, sawdust shall be poured directly over the valve box lid and covered with gravel to facilitate location in the future.

627-3.06  Testing Water System.  Delete in its entirety and substitute the following:  The Contractor shall notify the Engineer in writing 48 hours in advance (two working days) prior to any test.  AWWU and the Engineer shall be present during all tests.  Two (2) hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or cancelled.

1.	Flushing.  All flushing shall be coordinated with AWWU.  All newly-laid water conduit shall be "open-bore" flushed to remove any foreign matter to the satisfaction of AWWU.  A detailed plan for cleaning of the lines shall be submitted to the Engineer for review and approval prior to commencement of work.

"Open-bore" flushing shall be accomplished prior to 	hydrostatic testing and disinfection at all extremities including all stubouts and dead-ends. The Contractor shall furnish, install and remove all fittings and conduit necessary to perform the flushing.  Under no circumstances will "open-bore" flushing through hydrants or reduced outlets be permitted.

All flushing of newly-installed conduit shall be accomplished between the hours of 1:00 AM and 6:00 AM, unless otherwise authorized by AWWU.  Flushing shall be considered incidental to this work and no separate payment shall be made.

2.	Hydrostatic Testing.  A hydrostatic test shall be conducted on all newly-constructed water conduit, fire hydrant leads and stub-outs after "open-bore" flushing in the presence of the Engineer and AWWU in accordance with the requirements of AWWA C-600 unless hereinafter modified. The Contractor, at his option, may either use a pressure test or a leakage test.

The Contractor shall furnish all necessary assistance, equipment, labor, materials and supplies (except the test pressure gauge) necessary to complete the test to the satisfaction of AWWU.  The Contractor shall suitably valve off or plug the outlet to the existing or previously-tested water main at this expense, prior to making the required hydrostatic test.

Prior to testing, all air shall be expelled from the conduit. If permanent air vents are not located at all high points, the Contractor shall, at his expense, install corporation stops at such points so the air can be expelled as the conduit is slowly filled with water.

Where any section is provided with poured-in-place concrete thrust blocks for fittings or hydrants, the hydrostatic test shall not be made until at least 7 days after installation of the thrust blocks unless otherwise approved by the Engineer.

No hydrostatic test section shall exceed 1000-feet unless approved by AWWU in writing. All main line valves, fire hydrant auxiliary valves, fire hydrant main valves and plugs shall be tested.  All intermediate valves within the section being tested will be fully closed and reopened as directed by the Engineer during the actual test. Only static pressure will be allowed on the opposite side of the end valves of the section being tested.

All hydrostatic testing will be performed through test copper. Use of fire hydrants and service connections for testing will not be allowed.

The hydrostatic pressure shall be a minimum of 150 psi, and the duration of each hydrostatic pressure test shall be 30-minutes. After the required test pressure has been reached, the pumping will be terminated. If the pressure remains constant for 30-minutes without the aid of a pump, that section of the conduit will not be subjected to any further hydrostatic tests.

If a hydrostatic pressure test fails on any section, the Contractor has the option to perform a leakage test on that section.  AWWU will furnish the test gauge and measuring device, and the Contractor shall furnish all other necessary assistance, equipment, labor, material and supplies to conduct the test.

Leakage for a newly-installed conduit is determined by the following formula:

L = (ND) P0.5  where:

7400

L = Allowable leakage in

gallons per hour

N = Summation of mechanical

and push-on joints in

length of pipe tested

D = Diameter of conduit in

inches

P = Test pressure in pounds

per square inch

The duration of each leakage test shall be 2 hours and during the test, the conduit shall be subjected to the constant test pressure as defined above. The test pump shall be valved to insure that constant test pressure is maintained throughout the test and all excess water will be returned to a storage tank.  If the pressure decreases below the required test pressure during the 2-hour period, the preceding portion of that test shall be declared void.

Cracked or defective conduit, gaskets, mechanical joints, fittings, valves or hydrants discovered as a consequence of the hydrostatic tests shall be removed and replaced with sound material at the Contractor's expense. The test shall then be repeated until the results are satisfactory.

In the instance where connection is made to a presently installed water conduit a new valve shall be installed on the connection.  The Contractor shall suitably seal off the outlet leading to the presently installed conduit prior to making the field tests.

3.	Continuity Tests.  The Contractor shall perform electrical conductivity tests on all mains less than 12-inches in the presence of the Engineer and AWWU.  The Contractor shall maintain a circuit of 600 amperes DC current for a period of 15-minutes.  Return current shall be at least 90 percent of the input current.  All equipment necessary to maintain the circuit shall be supplied by the Contractor.

All continuity tests will be through wires brought to the surface or through 3/4-inch, minimum, copper pipe connected to the main.  The use of fire hydrants and valves, as substitutes for wires will not be accepted.  All wires brought to the surface to complete the continuity test shall be removed to a depth of 2-feet below finished street grade upon completion of the tests.

627-3.07  Disinfection of Waterlines.  Delete paragraphs 1 thru 4 and add the following:  This subsection applies to the disinfection of all portions of the water system, including all valves and stops and any portion of the existing connection system that might have become contaminated during construction activities.  Disinfection shall be accomplished after completion of pressure and/or leakage tests in compliance with AWWA C-601, Disinfecting Water Mains.

Chlorine shall be used for disinfection, and shall be applied only by one of the following methods:  (1) liquid chlorine gas and water mixture, (2) direct chlorine gas feed, or (3) calcium hypochlorite and water mixture. Calcium hypochlorite shall be comparable to commercial products known as HTH, Perchloren or Machochlor. The chlorinating agent shall be applied at the beginning of the section adjacent to the feeder connection, insuring treatment of the entire line. Water shall be fed slowly into the new conduit with chlorine applied in amounts to produce a dosage of forty (40) ppm to fifty (50) ppm. Application of the chlorine solution shall continue until the required dosage is evident at all extremities of the newly-laid conduit.

Chlorine gas-water mixture shall be applied by means of a solution-feed chlorinating device. Chlorine gas shall be fed directly from a chlorine cylinder equipped with a suitable device for regulating the rate of flow and effective diffusion of gas within the conduit. Calcium hypochlorite shall be injected or pumped into the water conduit. During the chlorination process, all intermediate valves and accessories shall be manipulated so that the strong chlorine solution in the conduit being treated will not flow back into the conduit supplying the water. Hydrostatic testing of water conduit containing the chlorine mixture will not be allowed.

A residual of not less than five (5) ppm chlorine shall be produced in all parts of the water conduit and retained for a minimum period of 24 hours, after which it shall be flushed from the conduit at its extremities until the replacement water tests are equal chemically and bacteriologically to those of the permanent source of supply.  In no instance will a water conduit be chlorinated before "open-bore" flushing.

CHLORINATION

Conduit Diameter      Dosage (oz. per 100 feet)

8-inch                     2.75 oz

36-inch                    45.00 oz

The above table is to be used as a guide for chlorinating mains by the calcium hypochlorite and water mixture method. The given dosage per 100 feet results in a chlorine solution of forty (40) to fifty (50) ppm.  This dosage takes into account that Contractors most frequently use granular HTH, which is 65 percent pure.  If another chlorinating agent is used, the dosage must be adjusted.  Caution should be exercised against producing too high a concentration of chlorine in the conduit.

After completion of all testing, all test and air vent copper pipe shall be removed and the corporation cock closed at the main in the presence of the Engineer and AWWU.

627-3.08  As-Builts of Plans and Working Drawings.  Add the following subsection:  A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed.  This as-built information shall be recorded on a print of the plans affected and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed.  Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When each water system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance of the system by AWWU.

627-4.01  Method of Measurement.  Delete Subparagraph 1 and 5 in their entirety and substitute the following:

1.	Water Conduit.  Measurement for water conduit with appurtenances will be per linear foot of horizontal distance of the various sizes and classes furnished and installed as set forth in the Bid Schedule.  Measurement will be from station to station as staked in the field and as shown on the plans, except where the grade exceeds 25 percent, in which case measurement will be by actual conduit length.  Fittings, tees, reducers, crosses, bends, couplings, etc., for water conduit shall be included in the linear foot cost of the water main.

5.	Valves, Valve Boxes and Markers.  The quantity to be paid will be the actual number of valves, including boxes and marker posts, of each class and size furnished, installed, and accepted, or adjusted.

Each valve box required to be adjusted shall be measured only once, when adjusted to final grade.  All other adjustments for intermediate construction activities shall be subsidiary to those activities.

Add the following:

6.	Disconnect and Reconnect Water Service.  The quantity to be paid will be the actual number of services of each size disconnected from the old main and reconnected to a main.

627-5.01  Basis of Payment.  Delete the second paragraph and substitute the following:  The unit bid prices will include all necessary excavation to plan grade, and backfill of native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 203(1), Common Excavation.  Backfill to replace unsuitable material will be paid under Item 203(6), Borrow, Type A.

Add the following Pay Items:

Pay Item No.             Pay Item            Pay Unit

627(11)        Disconnect and Reconnect      Each

Water Service

627(12)            Install 36 inch           Each

Butterfly Valve

627(13)         Water Line As-Builts       Lump Sum

SECTION 630

GEOTEXTILE FOR EMBANKMENT SEPARATION

AND REINFORCEMENT

Special Provisions

Delete this Section in its entirety and substitute the following:

630-1.01  Description.  This work shall consist of preparing surfaces and furnishing and placing geotextiles for embankment separation and/or reinforcement as shown in the plans or as directed by the Engineer.

630-2.01  Materials.  Geotextile material and thread used in joining geotextiles by sewing shall conform to the requirements of Subsection 729-2.01.

630-3.01  Construction.

1.	Surface Preparation.  Before placing the fabric (geotextile), the surface on which fabric is to be placed shall be prepared by removal of all stumps, boulders and other sharp objects.  All holes and large ruts shall be filled with material as shown on the plans or as approved by the Engineer.  Material used to fill ruts and holes will be paid for at the unit price for the class material used as shown on the plans or as approved by the Engineer.  Removal of stumps, boulders and sharp objects will be considered incidental to this item.

2.	Fabric Laying.  Fabric shall be unrolled directly onto the prepared surface.  The geotextile shall be stretched to remove any creases or wrinkles.  Thereafter, it shall be kept taut by pinning or random placement of cover material, and the constant attention of laborers during the cover material placement and spreading.

a.	Separation.  Fabric for embankment separation shall be laid parallel to the direction of the material spread.  When laid along horizontal curves, it shall be placed in segment lengths not exceeding those listed in Table 630-1, with butt ends cut to match and sewn or overlapped.  When laid along tangents, the fabric shall be placed in 200 ft. maximum segments, straightened, and butt ends sewn or overlapped.

b.	Reinforcement.  The fabric for embankment reinforcement shall be laid perpendicular to the roadway center line.  Segments shall be joined by sewing or an approved bonding or attachment process.

c.	Joining.  Fabric shall be joined with adjacent pieces of fabric by sewing, or overlapping.  Joining by bonding or other attachment methods may be used, subject to the approval of the Engineer.  If sewn, all seams shall be sewn by butterfly or J-seams and develop a minimum of 85 percent of the specified geotextile strength.  Seams shall be sewn with a double thread chain-lock stitch.  The seam shall be 1-1/2 inches (+1/4 inch) from the outside edge of the fabric.  If seams are to be overlapped, adjacent sections of fabric shall be overlapped a minimum of three feet unless otherwise shown on the plans.  Fabric used for reinforcement shall not be joined by overlapping.

TABLE 630-1

GEOTEXTILE PLACEMENT ON CURVES

Degree of Curve       Maximum Segment Length (Ft.)

1						125

2						 90

3						 75

4						 65

5						 55

6						 50

3.	Material Placing and Spreading.  Following placement of the fabric on the prepared surface, material of the type shown on the plans shall be end dumped on the previously spread fabric or ground adjacent to the fabric and carefully pushed or spread onto the fabric by a dozer or other machinery.  A minimum depth of 1 foot or depth shown on the plans shall be maintained at all times between the fabric and the wheels or tracks of the construction equipment.  At no time shall equipment operate on the unprotected fabric.  The material shall be spread in the direction of the fabric overlap.  Special care shall be given to maintain a proper overlap and fabric continuity.  If sewn or bonded seams are used, the cover material shall be placed and spread in only one longitudinal direction for the entire length of the geotextile.  On weak subgrades the cover material shall be spread simultaneously with dumping to minimize the potential of a localized subgrade failure.  Construction equipment shall not make sudden stops, starts, or turns on the cover material.  A smooth drum roller shall be used to achieve the specified density.  Any ruts occurring

during construction shall be filled with additional cover material and compacted to the specified density.

4.	Geotextile Repair.  If fabric used for separation should be torn for any reason, the cover material shall be cleaned from the torn area and it shall be overlain with fabric with a minimum three foot overlap around the edges of the torn area.  Care shall be taken that the patch remains in place when material is placed over the affected area.

Repair of fabric used for reinforcement shall be as described under Item 2.C., Joining.

5.	Shipping and Handling.  During shipment and storage, geotextiles shall be continuously protected from direct sunlight, ultraviolet rays, temperatures greater than 140 degrees F, moisture and contamination from mud, dirt, dust, and debris.  Each roll shall be labeled or tagged to provide product identification sufficient for field identification as well as inventory and quality control purposes.  Geotextiles will be rejected if at the time cover material is placed they have been removed from protective wrapping for more than five days, or if they have defects, tears, puncture, flaws, deterioration, contamination, creases or wrinkles caused by manufacturing and/or packaging which cannot be removed in the field, or if they have been damaged from any cause.

630-4.01  Method of Measurement.  Geotextile will be measured in final position by the square yard, determined by multiplying plan neat line width by the measured length parallel to installation centerline along the ground surface, for installations acceptably completed.  No allowance will be made for overlap, whether at joints or patches.  No payment will be made for geotextile placed beyond the limits shown on the plans unless placed at the prior, written direction of the Engineer.

630-5.01  Basis of Payment.  Payment will be made at the contract unit price per square yard.  This price shall be full compensation for furnishing all materials, surface preparation, delivering and laying the fabric and for all labor, equipment, tools and incidentals necessary to complete this item.

Payment will be under:

Pay Item No.             Pay Item              Pay Unit

630(1)         Geotextile, Separation    Square Yard

630(2)        Geotextile, Reinforcement   Square Yard

SECTION 639

DRIVEWAYS

Special Provisions

639-3.01  Basis of Payment.  Add the following:  Payment for all driveways, regardless of type, will be made under the following:

Pay Item No.        Pay Item          Pay Unit

639(4)           Driveways           Each

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-3.01  Basis of Payment.  Add the following:  Preparation of the CPM work schedule, two week work plans and providing a spokesperson for meetings in accordance with Section 108, will not be paid for directly, but will be subsidiary to Item 640(1) Mobilization and Demobilization.

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01  Description.  Add the following: Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of Subsection 107-1.11, Protection and Restoration of Property and Landscape.  Additional silt fencing may be required at other sites as directed by the Engineer.

641-1.03  Materials.  Add the following subsection:  The silt fence filtration material shall meet the following minimum requirements:

Property                        Test Method       Value

Equivalent Opening Size (EOS)

U.S. Standard Sieve             COE CW02215       30-100

Mullen Burst Strength           ASTM D-3786       200 psi

The silt fence support framework shall be finished 4 x 4-inch wood, 3-inch diameter wood, #6 rebar with PVC sleeves, or other posts capable of supporting the installation, as approved by the Engineer.

The mesh support shall be WWF 6x6 W1xW1 or as approved by the Engineer.

641-2.01  Construction Requirements.  Add the following:  The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other  substances hazardous to the land and water.  The temporary erosion and pollution control plan shall address the measures the Contractor shall implement in the containment, cleanup, and disposal of such substances as well as the methods to be utilized for disposing of waste oil or other hazardous substances generated by construction equipment or activities.  The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous

substance containment and cleanup activities.  The plan shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

The silt fence shall be installed as detailed on the plans.  Top of silt fence will be a minimum of one foot above Ordinary High Water where fence is installed in a waterbody.  Upon completion of work in the waterbody, the area behind the fence shall be allowed to settle the suspended material for a minimum of 2 days before the silt fence is removed.

Top of silt fence will be a minimum of two feet above ground surface where fence is installed in wetlands.  The silt fence shall not be removed until adequate vegetative growth insures no further erosion of the slopes.

The silt fence shall be removed and disposed of off the project upon completion of construction at those sites.  The fabric shall be cut off at ground level and the wire and posts shall be removed.  The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands.  If a sediment height in excess of four inches above ground remains, the sediment shall be spread on the roadway side of the fence location and seeded immediately in accordance with Section 618, Seeding.

641-2.02  Best Management Practices.  Add the following subsection:  The following factors shall be utilized by the Contractor in the development of the erosion and sediment control measures which are more easily accomplished if construction operations are properly scheduled.  Operations should be planned, when possible, for that time of year when potential for erosion is low.

1.	Clearing by cutting, slashing and disposing of the trees and other debris.

2.	Installation of temporary erosion and sediment control measures on the downhill side of the construction work area before building the embankment or excavating a slope.

3.	Construction of temporary drainage ditches to convey off-site drainage through the work area and diversion of the flow before excavating for the permanent drainage structure.

4.	Installation of all erosion and sediment control measures at the toe of embankment and excavation operations.  Silt fences are a structural method for providing temporary erosion and sediment control.

5.	Construction of the embankment in horizontal lifts, providing protection from erosion by temporarily or permanently mulching and seeding the slopes in vertical increments, preferably of no more than 10-feet.  The top of the work area should be shaped and compacted so that surface water will run off without causing serious erosion should a storm occur.  At the end of each day's work or before a storm, berms and temporary downdrains must be constructed to control the release of on-site drainage.

6.	Excavation operations performed in the same manner as the embankment operation with the exception of slope drains and compaction.  This operation will release on-site drainage at a point where appropriate control measures have been installed.  The excavated slope must be finished as it is constructed and incrementally protected and seeded.

7.	Shaping and compacting of the embankment surface  or cut when the area reaches subgrade elevation.  Surface runoff should be controlled by berms and ditches and release through temporary pipes or ditches.  Detain sediment-laden runoff and trap sediment before releasing runoff from the construction area.

8.	Inspection and maintenance of each erosion and sediment control measure should be performed after each significant storm.  Silt fences should be inspected periodically for damage, such as tearing by wind, animals or equipment, and for the amount of sediment which has accumulated.  Removal of the sediment is generally necessary when it reaches half the height of the silt fence.  In situations where

access is available, machinery can be used; otherwise it must be removed manually.  The key elements to remember are:

a.	The sediment deposits should be removed when heavy rain or high water is anticipated.

b.	The sediment removed should be placed in an area where there is little danger of erosion.

641-3.01  Method of Measurement.  Add the following:  Silt fence will be measured by the linear foot along the top of the fence.

641-4.01  Basis of Payment.  Add the following:  Payment for Item 641(2), Silt Fence, will be full compensation for all labor, equipment and materials required to furnish, install, maintain and remove the silt fence in accordance with these specifications.

Payment will be made under:

Pay Item No.              Pay Item             Pay Unit

641(2)                Silt Fence         Linear Foot

(7/1/90)

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  Description.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix B.

642-3.01  Construction Requirements.  Add the following:  Where new curb is to be constructed at a specified location or elevation relative to the existing curb, the Contractor shall reference the existing curb by setting surveyed reference points prior to removal of the curb.  In addition to setting reference points, the Contractor shall as-build the existing curb to obtain the elevation and location information necessary to stake the new curb if reference points are disturbed or damaged.  The frequency of surveyed reference points and as-built survey data shall be in accordance with the Department's "Construction Surveying Requirements".

642-4.01  Method of Measurement.  Add the following:  Pay Item 642(2), Three Person Survey Party, shall be used only for extra, additional, or unanticipated work made necessary by changes in the project as directed by the Engineer.  The quantities shown on the Bid Schedule for this item are for bidding purposes only, and the actual quantity in the field may vary as directed.  It is not intended to cover survey costs due to minor overruns (10 percent or less) in items which require staking of individual installations such as culverts, guardrail, approaches, signs and drainage structures, etc.

642-5.01  Basis of Payment.  Add the following:  If staking for extra, additional or unanticipated work as stated above is performed by a two person survey party, payment will be made at seventy-five (75) percent of the bid amount per hour for Item 642(2), Three Person Survey Party.  If a single person is required for additional office computations or there is work requiring only one person, payment will be made at thirty-two (32) percent of the bid amount per hour for  item 642(2).

(9/1/89)

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  Traffic Control Plan.  Add the following to the third paragraph:  All TCP's submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Safety Supervisor.

Add the following:  The Contractor should be aware that his traffic control plan may require traffic signal timing or re-timing adjustments.  This adjustment work will be done by the Municipality of Anchorage.  It is estimated that approximately four hours per week per signalized intersection at a cost of $50/hour for regular time and $100/hour for overtime will be required.  Payment for this work will be a subsidiary obligation of the Contractor under Section 660, Signals and Lighting.

643-1.03a   Public Relations Program.  Add the following subsection:  The Contractor shall provide a Public Relations (PR) professional, with a minimum of five years experience in Public Relations acceptable to the Department, to accomplish the work outlined in this subsection.  The PR person(s) shall be responsible for all aspects of this service including coordination; providing graphics and verbal commentary; supplying daily updated information; and all labor, equipment, postage, and materials to provide this service.   Logos, reports, software, visual aids, graphics and work products developed for this project shall become the property of the Department.  The PR person's office shall be equipped with a facsimile machine.

This Public Relations professional shall be responsible for the following tasks:

1.	Public Meetings.  Prepare a project description  for presentation at meetings of each of the five Community Councils which represent areas affected by this project.  The meetings attended shall be the last regularly scheduled meetings prior to the beginning of construction.  Presentation size graphics shall be used to help explain the project to the general public.  A question and answer period following the presentation should be anticipated.

The PR person(s) shall be the Contractor's representative and spokesman, able to speak for the Contractor and commit the Contractor to courses of action when needed to resolve problems.

The PR person(s) shall be available to attend an additional ten public meetings, as requested by the Department.

2.	Road Information Reports.  Provide for regularly scheduled (30 second) Road Information Reports (RIR) to air each evening, Sunday through Friday, between 5:45 PM and 6:30 PM, on a major local television station during the local evening news.  The RIR's shall run from the beginning of construction until winter shutdown or project acceptance.

The RIR's shall include a visual graphic display and a verbal commentary explaining routes affected by construction.  Areas of potential traffic delay shall be emphasized and alternate routes noted.  Telephone numbers for further information shall be provided.  The presentation and graphics shall be approved by the Engineer.

A sponsor(s) may be obtained for the RIR, however, the sponsor(s) must be approved by the Department.  The sponsor's advertisement time shall be outside the 30 seconds required for road reporting.

3.	Mailouts.  Design and distribute three mailouts which shall be approved by the Engineer.  The mailouts shall contain:

a.	a map of the project,

b.	the construction schedule,

c.	the Contractor's project office phone number,

d.	the Engineer's project office phone number,

e.	a 24-hour contact phone number for Contractor,

f.	a 24-hour contact phone number for Engineer,

g.	a listing of locations where current project  information may be obtained, (i.e., PR Office)

h.	broadcast schedule information,

i.	a description of impacts to abutting property accessing Tudor Road,

j.	an outline of the impacts to the travelling public on Tudor Road,

The last mailout shall also contain a questionnaire to aid in preparing the final report required under Item 6 below.

The three mailouts shall be sent to all addresses which are within one city block on either side of Tudor Road within the project limits and shall be distributed at the following times:

a.	two weeks before construction begins,

b.	at the approximate one-third point of construction completion, and

c.	at the approximate two-thirds point of construction completion.

Determine the cost of providing the mailouts as information distributed in the Municipality's utility bills.  This cost information shall be submitted to the Engineer within two weeks following issuance of the Notice to Proceed.

4.	Weekly Notices.  Write and submit weekly Public Information Notices that identify road closures, restrictions to traffic, and detours.  These notices shall be in a format approved by the Engineer and shall contain the broadcast schedules for the RIR's and telephone numbers for additional information.  The Notices shall be distributed to the list of local media, emergency services and public service organizations provided by the Department.  Notices shall be submitted at the following times:

a.	one week prior to the beginning of construction,

b.	on Wednesday of each week during construction, and

c.	prior to any major change or disruption to traffic or local access.

Provide daily information to those media which do non-paid public service road reports or eye in the sky road reporting.

5.	Other Agency Coordination.  Coordinate with the Anchorage People Mover Transit System and Ride Share to take advantage of programs which will help decrease traffic on Tudor Road, such as Park and Ride with express bus service, Ride Share, and Car Pooling.  Coordinate with emergency service providers (police and fire) and school bus operators.

6.	Final Report.  Before project completion, submit a report evaluating the Public Relations Program as detailed under this subsection.  This report shall include an outline of the program, an analysis of the program's effectiveness, and suggestions on how to improve the program's effectiveness, economy, and usefulness on future projects.

643-1.04  Construction Phasing Plan.  Add the following:

1.	General.  Rehabilitation of Tudor Road includes three types of work:  Replacement of curbs, cold planing and overlay of existing asphalt, and addition or extension of turn lanes.  Replacement of curb requires closing the adjacent lane during construction.  Cold planing and overlaying the asphalt requires closing the lanes affected plus one adjacent lane and will progress from the center of the road toward the outside.  Adding right turn lanes will also require closing the adjacent lane.

Two control strategies are required for this project.  One strategy will close off an entire section or one direction of a roadway during reconstruction.  The second strategy will maintain 2 way traffic on the section under construction.  The first method (closing the section under construction) shall apply to areas of signalized intersections and raised medians.

The Contractor must complete all work requiring traffic restrictions between Minnesota Drive and C Street (Work Segments 1, 2, 3 and 13) by the end of the 1991 construction season.

The Contractor must complete all work in Work Segments 16 and 17 by the end of the 1991 construction season.  This is to avoid conflicts with the Northern Lights and Benson Boulevards Rehabilitation project.

Scheduling construction of Tudor Road shall be coordinated with other construction projects in the area.  The Municipality of Anchorage may be constructing any or all of the following projects during the 1991 construction season:

Wilson Street

MacInnes Street

36th Avenue from Spenard Road to Arctic Blvd.

Lake Otis Pkwy. from 68th Ave. to Abbott Road

ADOT&PF is planning on beginning the reconstruction Northern Lights Boulevard and Benson Boulevard from Minnesota Drive to Lake Otis Parkway late in the 1991 construction season and completing construction in the 1992 construction season.

During the course of work, traffic conditions may change or problems may develop that require changes to the Traffic Control Plan (TCP).  The Contractor shall respond and make field changes as the Engineer directs.

2.	Hours of Work:

Night Work shall mean from 8:00 PM to 6:00 AM Monday through Sunday.  The Contractor shall comply with the conditions and restrictions of the noise permit.

Weekend Work shall mean from 10:00 PM Friday to 6:00 AM Monday.  Memorial Day and Labor Day are included in the weekend.  The Contractor shall comply with the conditions and restrictions of the noise permit.

Peak Hours shall mean the following:

Eastbound -	4:00 PM to 8:00 PM, Monday through     Friday.

Westbound -	7:00 AM to 10:00 AM, Monday through   Friday.

Independence Day (July 4), Memorial Day and Labor 	Day are not included in Peak Hours.

3.	Closing Section of Road:  Unless otherwise indicated in the individual Work Segments, road closures shall be used during the pavement removal, planing and paving of signalized intersections and sections of road that have raised medians.  Closures of the major intersections and certain other sections as shown in the TCP shall be done on weekends and/or during the night unless otherwise specified on the TCP.

4.	Maintaining 2-way Traffic:  In certain portion of the work, 2-way traffic shall be maintained through the work zone.  The minimum lane width allowed shall be 11 feet measured from face of curb and 10 feet without curb.

Where curb is being replaced, the adjacent traffic lane shall be closed.  When this occurs, the traffic shall be either merged into one lane around the work zone or if the center median is flush, the median shall be used as the second lane around the work zone.  In certain areas where the center median is raised, curb work shall be scheduled for off peak hours.

5.	Work Segments:

Intersections:  Signalized intersections have raised medians protecting the left turn lanes on Tudor Road.  The approach lanes adjacent to the raised medians will, unless otherwise indicated in the individual Work Segments, be paved at the same time the intersection is closed for construction.

The following signalized intersections shall be reconstructed on weekends and/or at night.  Signal detection shall be fully operational and all traffic lanes paved and opened for traffic by the end of the weekend or end of the night work shift.

Arctic Blvd.     Work Segment #13.   46+00 to 48+75

Old Sew. Hwy.    Work Segment #14    98+00 to 10+25

Lake Otis Pkwy.  Work Segment #15    145+00 to 155+00

Bragaw Street    Work Segment #16    200+00 to 211+00

Boniface Pkwy.   Work Segment #17    245+00 to 266+50

Baxter Road      Work Segment #18    281+00 to 285+00

The remaining intersections shall be paved in conjunction with paving Tudor Road.

Minnesota Drive to Arctic Boulevard:

Work Segment #1.  BOP to 46+00

During excavation, planing, and paving, Tudor Road shall be closed and detoured as shown in the TCP.  Due to potential detour conflicts between eastbound through traffic and westbound detour traffic, work shall be scheduled and performed so that the westbound closure and detour occurs while the eastbound closure and detour is in effect.

During curb replacement the adjacent lane shall be closed.  Only one traffic lane in each direction shall be closed at the same time.

Work hours will not be limited.

Arctic Boulevard to C Street:

Work Segment #2.  Sta. 48+75 to 57+00.

During curb replacement the adjacent lane shall be closed.  Only one traffic lane in each direction may be closed at the same time.

During median paving, only one adjacent traffic lane shall be closed.

During planing and paving of the traffic lanes, Tudor Road shall be closed and detoured as shown in the TCP.  Only one direction of traffic shall be closed at a time.

Work hours will not be limited.

C Street to Old Seward Highway:

Work Segment #3.  Sta. 74+50 to 98+00.

During curb replacement, the adjacent lane shall be closed.  Only one traffic lane in each direction shall be closed at the same time.

During median paving, only one adjacent traffic lane shall be closed.

During planing and paving of the traffic lanes, Tudor Road shall be closed and detoured as shown in the TCP.  Only one direction of traffic shall be closed at a time.

Work hours will not be limited.

Old Seward Hwy. to New Seward Hwy. SB Offramp:

Work Segment #4.  Sta. 101+25 to 110+00.

During curb replacement and median paving, one adjacent lane may be closed.  Only one traffic lane in each direction shall be closed at the same time.

During excavation, planing and paving of the traffic lanes, Tudor Road shall be closed and detoured as shown in the TCP.  Due to potential conflicts between eastbound through traffic and westbound detour traffic, work shall be scheduled and

performed so that the westbound closure and detour occurs while the eastbound closure and detour is in effect.

Operations requiring closure of a traffic lane shall be performed at night or on weekends.  Operations requiring closure of Tudor Road shall be done at night and/or on weekends.

New Seward Hwy. to Eau Claire Place:

Work Segment #5.  Sta 110+00 to 120+00.

During curb replacement and median paving, one adjacent lane may be closed.  Only one traffic lane in each direction shall be closed at the same time.

During excavation, planing and paving of the traffic lanes, Tudor Road shall be closed and detoured as shown in the TCP.  Only one direction of traffic shall be closed at a time.

Operations requiring closure of one or more traffic lanes in the same direction shall be performed at night and/or on weekends.

Eau Claire Place to Lake Otis Parkway:

Work Segment #6.  Sta. 120+00 to 145+00.

This segment of road is from the east end of the median at Eau Claire Place to the west end of the median prior to Lake Otis Parkway.

During curb replacement, the adjacent lane shall be closed.  Since the median is flush, it shall be used as a detour for the closed traffic lane in accordance with the TCP.  Two traffic lanes in each direction shall be maintained during curb replacement.

During planing and paving of the median, one adjacent traffic lane shall be closed.  During planing and paving of the traffic lanes, the adjacent median or if not adjacent to the median, then the adjacent traffic lane shall be closed.

At least one traffic lane shall be maintained in each direction at all times.  Operations that do not maintain two (2) traffic lanes in each direction shall be performed on weekends and/or at night.

The culverts at approximate station 141+00 may be installed during the Lake Otis intersection closure.

Lake Otis Parkway to Folker Street:

Work Segment #7.  Sta. 155+00 to 170+00.

This segment of road is from just east of Lake Otis Parkway to approximately 200 feet east of the east end of the new median at Folker Street.

During curb construction and replacement and median paving, the adjacent lane shall be closed.  Only one traffic lane in each direction shall be closed at the same time.  During median paving only one adjacent lane shall be closed.

During planing and paving of the traffic lanes, Tudor Road shall be closed and detoured as shown in the TCP.  Only one direction of traffic shall be closed at a time.

Operations requiring closure of a traffic lane shall be performed at night or on weekends.  Operations requiring closure of Tudor Road shall be done at night and/or on weekends.

Folker Street to Baxter

Work Segment #7A.   Sta. 170+00 to 200+00.

Work Segment #8.  Sta. 211+00 to 245+50.

Work Segment #9.  Sta. 266+50 to 281+00.

During curb replacement the adjacent lane shall be closed.  Since the median is flush, it shall be used as a detour for the closed traffic lane in accordance with the TCP.  Two (2) traffic lanes in each direction shall be maintained during curb replacement.  The area of Work Segment #7A between station 190+00 and 195+00 where there is a raised median, the adjacent lane may be closed during curb replacement.

During planing and paving of the flush median, one adjacent traffic lane shall be closed.

During planing and paving of the traffic lanes, the adjacent flush median or if not adjacent to the median, then the adjacent traffic lane shall be closed.

During planing and paving of the traffic lanes in Work Segment #7A adjacent to the raised median, traffic shall be routed around the median.  One lane of traffic in each direction shall be maintained.  Excavation, subbase reconstruction and paving from Sta 181+00 to 184+00 shall be scheduled for the same period of time as either the Lake Otis or Bragaw intersections (Work Segment 15 and 16) are closed.  Excavation, subbase reconstruction and paving from Sta. 215+00 to 220+00 and Sta 231+00 to 234+00 shall be scheduled for the same period of time as either the Bragaw or Boniface intersection (Work Segment 16 or 17) is closed.

During excavation and construction of the additional eastbound lane near Boniface Parkway, the adjacent traffic lane may be closed.

At least one traffic lane shall be maintained in each direction at all times.  Operations that do not maintain two (2) traffic lanes in each direction shall be performed on weekends and/or at night.  Construction of the median curb for the Boniface Parkway intersection shall be scheduled and coordinated so that this can be accomplished.

Baxter to Kingston:

Work Segment #10.  Sta 285+00 to 298+25.

During regrading of this section of road, one (1) lane of traffic shall be maintained in each direction at all times.  Traffic lanes shall be surfaced and maintained with temporary asphalt pavement.  Traffic lanes shall be 12 feet wide.

During construction of the 36-inch water line, this segment of road may be closed in accordance with the TCP for 72 hours.  Closure shall be scheduled to start at 8:00 PM on a Friday and run to 8:00 PM the following Monday.

Upon completion of the first course of permanent asphalt pavement, two (2) traffic lanes shall be reestablished and maintained in each direction.

During paving of the final course of permanent pavement in the median, one adjacent traffic lane shall be closed.  During paving of the inside traffic lane, the adjacent median shall be closed and used for the work zone.  During paving of other traffic lanes, one adjacent traffic lane shall be closed.  Two (2) traffic lanes shall be maintained in each direction during peak hours and one (1) traffic lane in each direction shall be maintained during off peak hours.

Kingston to Patterson:

Work Segment #11.  Sta. 298+25 to 312+00.

Since traffic on this segment of road will be affected by traffic restrictions during work on Work Segment #10, the Contractor shall coordinate his work and traffic restrictions to correspond with the Work Segment #10 traffic restrictions.  This does not relieve the Contractor of his responsibility for maintaining local traffic.

Work not performed during the above referenced 3 day period shall proceed as follows:

During curb replacement, the adjacent lane shall be closed.  Since the median is flush, it shall be used as a detour for the closed traffic lane in accordance with the TCP.  Two (2) traffic lanes shall be maintained in each direction during curb replacement.

During planing and paving of the inside traffic lane, the adjacent median shall be closed and used for the work zone.  During paving of other traffic lanes, one adjacent traffic lane shall be closed.  Two (2) traffic lanes shall be maintained in each direction during peak hours and one (1) traffic lane in each direction shall be maintained during off peak hours.

Patterson to East 36th Avenue:

Work Segment #12.   Sta. 312+00 to EOP.

Since traffic on this segment of road will be affected by traffic restrictions during work on Work Segment #10, the Contractor shall coordinate his work and traffic restrictions to correspond with the Work Segment #10 traffic restrictions.  This does not relieve the Contractor of his responsibility for maintaining local traffic.

Work not performed during the above referenced 3 day period shall proceed as follows:

During curb replacement, the adjacent lane shall be closed.  Since the median is flush, it shall be used as a detour for the closed traffic lane accordance with the TCP.  Two (2) traffic lanes shall be maintained in each direction during curb replacement.

During planing and paving of the inside traffic lane, the adjacent median shall be closed and used for the work zone.  During paving of other traffic lanes, one adjacent traffic lane shall be closed.  Two (2) traffic lanes shall be maintained in each direction during peak hours and one (1) traffic lane in each direction shall be maintained during off peak hours.

During planing and paving of the traffic lanes adjacent to the raised median at 36th Avenue, Tudor Road shall be closed and traffic detoured via East 36th Avenue and Patterson Street.  This work shall be done during the 3 day closure period for Work Segment #10.

643-2.01  Materials.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8-feet.

Delete paragraph 8. in its entirety and substitute the following:

8.	Work Zone Pavement Markings.  Work zone pavement markings shall be either paint conforming to Section 708, Paints, and Subsection 712-2.14,  Preformed Pavement Markings (removable or non-removable) or temporary raised pavement markers conforming to Section 712, Miscellaneous.  The markings shall be applied in accordance with Section 670, Traffic Markings, and the manufacturer's recommendations.

Add the following:

12.	Portable Changeable Message Board Signs.  Portable changeable message board signs shall be truck or trailer mounted with a self-contained power supply for the sign and shall have the following features:

a.	Message sign panel size of 5 ft - 8 in by 7 ft - 5 in, minimum, with a capacity for a three line message.

b.	Eight character display per message line.

c.	Message modules containing at least 36 different preprogrammed messages (three line displays) to be selected by the Engineer.

d.	The capacity to create, preview, and display new messages and message sequences.

e.	A waterproof, lockable cover for the controller keyboard.

f.	An operator's manual, a service manual, and wiring diagram.

g.	Quick release attachments on display panel cover.

h.	Variable flash and sequence rates.

i.	Manual and automatic dimming capability on lamp bulb matrix models.

j.	The ability to mount at least 7 feet above the pavement to the bottom of the message sign panel.

k.	The capacity to operate with a battery pack for 2 hours under full load.

643-3.03  Public Notice.  Add the following:  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of the start of construction and any scheduled delay, or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure.  Advertisements shall encourage the use of the People Mover Bus System and/or car pooling, and shall be published in the following newspapers:

1.  Anchorage Daily News

2.  Anchorage Times

The Contractor shall indicated on the ad order a first preference for the local news section, and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, time and television station on which Road Information Reports are aired (RIR's) and provide the Contractor's name and a "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.  Advertisements shall be promptly cancelled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

The Contractor shall advertise in the newspaper continuously for one (1) week prior to closure of Work Segment 10 (Baxter Road to Kingston Drive).  Advertisement shall be one-quarter (1/4) page and shall clearly show detours.  The advertisement shall explain how long the road will be closed and in addition, how long the road will be restricted to single lane traffic in each direction.

The Contractor shall notify business and residents that front on Tudor Road, or are located on dead end streets accessing Tudor Road, of any scheduled road closure or of curb and driveway reconstructions affecting them.  The notices (flyers) shall contain the project name, a map, detailed traffic information (i.e. detours), effective dates, and shall provide the Contractor's name and telephone number.  The property owners shall receive the notices (flyers) a minimum of three days prior to the scheduled work.

643-3.04  Traffic Control Devices.

Delete paragraph 4. in its entirety and substitute the following:

4.	Work Zone Pavement Markings.  Work Zone Pavement Markings shall be installed in accordance with the Alaska Traffic Manual and shall consist of either Permanent Pavement Markings or Temporary Pavement Markings.

Permanent or Temporary Pavement Markings shall be placed before opening the traveled way to public traffic on all new and overlay Hot Asphalt Concrete

Pavement projects, or whenever pavement delineation has been obliterated or worn off (centerline or lane lines).

Conflicting pavement markings shall be removed in accordance with Section 670, Traffic Markings.  Removal shall be by burning, grinding, sandblasting or other approved method.  Painting over existing striping does not meet the requirement for removal.  Construction shall be staged so that no traffic is routed over conflicting markings.

All Permanent Pavement Markings shall be completed before work is suspended for the winter or a period of time in excess of three weeks.  They shall be applied at the same location as the existing lines and markings unless shown otherwise on the plans, an approved traffic control plan or directed by the Engineer.  Lines and markings to be replaced at their existing locations shall be referenced by the Contractor, at his expense, prior to performing any work that may disturb them.

Temporary Pavement Markings shall consist of marking the work zone in accordance with this subsection, the traffic control plans, and Parts III and VI of the Alaska Traffic Manual.

All interim paving lifts that will be opened to traffic more than three weeks before the final pavement surface is applied, temporary pavements, and detours shall be marked as though a permanent condition existed before being opened to public traffic.  No exceptions to the requirements of the Alaska Traffic Manual for Permanent Pavement Markings will be allowed.

The Contractor shall maintain all Temporary Pavement Markings for their intended life without additional compensation for any reapplication that may be required.

Temporary Pavement Markings will be required for short-term operations.  Short-term operations are those that will last longer than one continuous work shift and will continue for a time period not to exceed two weeks following the completion of the mainline paving.  Temporary Pavement Markings for short-term operations shall conform to the requirements of the Alaska Traffic Manual for permanent markings with the following exceptions:

a.	Broken line pavement markings shall conform to the following Table 643-1A, Short-Term Markings In Safe Passing Areas.  This applies to  both white lane lines for traffic moving in the same direction, and yellow center lines for two or three lane two-way roadways when it is safe to pass.

b.	No-passing zones shall be identified with R4-1, (DO NOT PASS) and R4-2,(PASS WITH CARE) signs and temporary raised pavement markers conforming to the following Table 643-1B, Short-Term Markings in No Passing Areas, until permanent no-passing markings can be placed.  The signs shall be supplemented with two 18 inch by 18 inch, minimum size, fluorescent red-orange flags mounted above the signs.  The signs shall be mounted so that the bottom of the sign is at least 5 feet above the adjacent roadway.  This method of marking no passing areas may be used with Annual Average Daily Traffic (AADT) up to 2000 vehicles per day.

c.	It will not be necessary to install arrows, legend, stop lines, crosswalks, or right edge line markings.  Railroad crossing markings should be considered for areas that have sight restrictions or high accident experience.  Left edge lines will not be required unless they will be the only markings on the paved surface, such as ramps.  All other types of markings are required.  These include channelizing lines and gore area outlines.

Temporary Pavement Markings may not be required for construction activities that will be completed within one continuous work shift if the roadway is adequately delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.  The Engineer shall be the judge as to the need for the Temporary Pavement Markings for these conditions.

TABLE 643-1A

SHORT-TERM MARKINGS IN SAFE PASSING AREAS

┌──────────────────┬──────────────────────┬────────────────────┐

│                  │     LENGTH OF        │     SKIP           │

│    MARKING       │     MARKINGS         │     SPACING        │

│    MATERIAL      │  NORMAL  │  SEVERE*  │ NORMAL  │  SEVERE* │

│                  │ CURVATURE│ CURVATURE │CURVATURE│ CURVATURE│

│                  │          │           │         │          │

│    REMOVABLE     │          │           │         │          │

│PRESSURE SENSITIVE│  4 feet  │  2 feet   │ 36 feet │  18 feet │

│  MARKING TAPE    │          │           │         │          │

│                  │          │           │         │          │

│                  │          │           │         │          │

│    TEMPORARY     │ 2 units  │ 2 units   │         │          │

│ RAISED PAVEMENT  │ 4 feet   │ 2 feet    │ 36 feet │  18 feet │

│     MARKERS      │ on center│ on center │         │          │

└──────────────────┴──────────┴───────────┴─────────┴──────────┘

Severe Curvature:	When the degree of curvature is 5 or greater or when it is necessary for the motorist to reduce their speed 15 miles per hour below the 85th percentile speed.

TABLE 643-1B

SHORT-TERM MARKINGS IN NO PASSING AREAS

┌───────────────────┬────────────────────┬────────────────────┐

│ MARKING MATERIAL  │  NORMAL CURVATURE  │  SEVERE* CURVATURE │

│                   │                    │                    │

│                   │                    │                    │

│ TEMPORARY RAISED  │        1 UNIT      │        1 UNIT      │

│ PAVEMENT MARKERS  │  40 FOOT ON CENTER │  20 FOOT ON CENTER │

└───────────────────┴────────────────────┴────────────────────┘

*Severe Curvature:	When the degree of curvature is 5 or greater or when it is necessary for the motorist to reduce their speed 15 mile per hour below the 85th percentile speed.

Add the following:

9.	Portable Changeable Message Board Signs.  These signs shall be used on the four approaches to an intersection for one week prior to the closure of that intersection to notify the travelling public of the upcoming closure.  These signs may also be used in other applications as directed by the Engineer.

643-3.06  Traffic Price Adjustment.  Delete the table at the end of this Subsection, and substitute the following:

$1500 per lane-hour of delay.

Add the following:  When a Work Segment is not completed or not opened for traffic within the time listed below for Time of Completion or Time of Closure, the Contractor will have payment for this contract reduced under Item 643(23), Traffic Price Adjustment.

Time of Completion listed below will start at the time of the first traffic restriction, lane restriction or detour in accordance with the approved TCP and run continuous until the Work Segment is open for continuous full traffic.  In determining whether a Work Segment is open to continuous full traffic, it must have all work requiring lane restriction, including but not limited to, curb, asphalt, pavement markings, signing and lighting completed.

Time of Closure listed below will start at the time the first full traffic closure to through traffic in either direction is implemented and run continuous until through traffic is restored to the roadway.

Lane restrictions not allowed by the TCP, such as during peak hours when not allowed or during the day when only night time work or weekend work is allowed or during the week when only weekend restrictions are allowed, will be assessed the standard Traffic Price Adjustment, Item 643(23) at the rate of $1500 per lane-hour of delay.

┌─────────────────────────────────────────────┬───────────┬─────────┐

│                                             │  TIME OF  │ TIME OF │

│              WORK SEGMENT                   │COMPLETION │ CLOSURE │

│                                             │  (days)   │  (days) │

│#1  Minnesota Dr. to Arctic Blvd (eastbound) │    20     │   13    │

│#1  Minnesota Dr. to Arctic Blvd. (westbound)│    19     │    5    │

│#2  Arctic Blvd. to C St.                    │    21     │    6    │

│#3  C St. to Old Seward Hwy.                 │    24     │    6    │

│#4  Old Seward Hwy to New Seward Hwy         │    16     │    0    │

│#5  New Seward Hwy to Eau Claire Pl.         │    16     │    0    │

│#6  Eau Claire Pl. to Lake Otis Pkwy.        │    22     │    0    │

│#7  Lake Otis Pkwy. to Folker St.            │    20     │    0    │

│#7A Folker St. to Bragaw St.                 │    24     │    0    │

│#8  Bragaw St. to Boniface Pkwy.             │    24     │    0    │

│#9  Boniface Pkwy. to Baxter Rd.             │    24     │    0    │

│#10 Baxter Rd. to Kingston Dr.               │    60     │    3    │

│#11 Kingston Dr. to Patterson St.            │    16     │    0    │

│#12 Patterson St. to E. 36th Ave.            │    14     │    0    │

└─────────────────────────────────────────────┴───────────┴─────────┘

Unless otherwise indicated, closure times shown for a Work Segment are the combined time for east and westbound closures.

In addition to the time allowed in the above table for time of completion, an additional eighty (80) hours of time are provided as a contingency that can be used for lane restrictions outside the time period allowed for time of completion in the above table.  This eighty (80) hours will be applied solely and completely at the discretion of the Engineer.  This 80 hours can not be used to extend the Contract Time of the Contract or Closure time listed in the above table for any Work Segment.

643-3.08  Construction Sequencing.  Add the following:  The TCP for certain Work Segments provides for detouring of traffic during specific phases of the work.  If two (2) or more work segments have detours that conflict or could adversely impact each other, the Contractor shall schedule his operations and work schedule so conflicts do not occur.  Closures or detours for some work segments compliment work in other work segments by providing a detour that would not otherwise be available.  The Contractor shall schedule his work to take advantage of these situations (compliments) when possible to reduce impact to the motoring public.  The following table shows where conflicts and compliments could occur.  It is based on the TCP included as part of these plans and specifications.

Some Work Segments shown above as compliments may require modification of their detours in order to work together.

Construction sequencing for the major intersections to be excavated and backfilled with new base is anticipated to be as follows:

1.	Earthwork and first course of asphalt

a.	Close intersection in accordance with the TCP.

b.	Excavate to subgrade.

c.	Construct subbase.

d.	Install base course.

e.	Install detectors, conduits and other underground facilities.

f.	Place 1st lift of permanent asphalt and temporary striping.

g.	Open intersection for full traffic by end of allowed closure.

2.	Install curbs.

a.	Close outside traffic lanes in accordance with the TCP.

b.	Install curb and ramps.

c.	Protect curb during curing with Type II barricades.

3.	Install final course of asphalt.

a.	After appropriate curing of the curb, close intersection on a weekend or in accordance with the TCP.

b.	Fill all areas or gaps between the curb and asphalt where the 1st course of asphalt is not continuous to the curb.  These areas shall be filled flush to the top of the 1st asphalt course and compacted to required density.

c.	Pave the top (final) course of asphalt.

d.	Open the intersection for full traffic by the end of allowed closure period.

Intersections that require pavement resurfacing (asphalt removal and repaving) but do not require reconstruction of the subbase can be sequenced as follows:

1.	Install Curbs.

a.	Schedule and close outside traffic lanes in accordance with the TCP.

b.	Remove existing curb.  This may require removal of an area of the asphalt adjacent to the curb.  In no case will removal of asphalt wider than 1-foot from the existing curb be allowed.

c.	Prepare base for new curb.

d.	Install new curb.

e.	Protect curb with Type II barriers during curing.

f.	Open traffic lanes for traffic by the end of allowed closure period.

2.	Install detectors, conduits and miscellaneous buried utility crossings.

a.	Schedule and install detectors, conduits, and other buried appurtenances during the time the intersection is closed for pavement resurfacing.

b.	If the amount of work required to install detectors, conduits and miscellaneous buried utility crossings exceeds the time available during the intersections closure, the work can be scheduled and completed prior to closing the intersection for paving.

3.	Pavement removal and resurfacing.

a.	Schedule and close intersection in accordance with the TCP.

b.	Remove asphalt.

c.	Install underground facilities.

d.	Prepare surface for paving.

e.	Adjust utilities to grade.

f.	Pave intersection.

The Contractor may modify the above sequencing plan.  Any modifications to the sequencing or any new sequencing plan shall be submitted for approval of the Engineer.  The Contractor shall allow 1 week for review of any sequencing or each subsequent correction.  Changes in the work sequencing resulting from unforseen circumstances may be allowed during construction provided 48 hours are allowed for review and the changes are approved by the Engineer.

643-4.01  Method of Measurement.  Add the following to Item 1:  Permanent Construction Signing will be measured by the calendar day and shall consist of furnishing all labor, tools, equipment, signs, sign supports, and incidentals necessary to install and remove the Permanent Construction Signing Plan detailed on the Plans.  The quantity to be paid for shall be the number of calendar days the Construction Signing Plan is installed, accepted and maintained in place.

Delete the second sentence of the first paragraph under Item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this contract.

Delete the fourth sentence of the first paragraph under Item 2.

Delete the last sentence of the first paragraph under Item 3. and replace with the following:  The quantities to be paid for shall be the number of hours or days that the setups are installed, accepted and maintained in place during the life of this contract.

Delete paragraph 6 and substitute the following:

6.	Temporary Pavement Markings will be measured by the single stripe station.  A single stripe is a marking or a temporary raised pavement marker four inches in width.  Wider striping will be measured as multiples of four inches.  Centerline gaps will not be deducted from measurements.  Installation of any word and symbol markings as well as the removal of the temporary pavement markings will not be measured separately but will be subsidiary to this item.  The No-Passing Zone signing, as described in Subsection 643-3.04, 4.  Work Zone Pavement Markings, will not be measured separately but will be subsidiary to this item.

Delete paragraph 7., Seasonal Pavement Markings in its entirety.

Add the following:  Pay Item 643(24), Portable Changeable Message Board Mobilization will not be measured for payment.

Pay Item 643(25), Portable Changeable Message Board Signs will be measured by the calendar day for each sign used as approved by the Engineer.

Pay Item 643(26), Public Relations will be not be measured for payment.

643-5.01  Basis of Payment.  Delete paragraph 1,  Seasonal Pavement Markings under the second paragraph.

Delete Pay Item 643(14), Seasonal Pavement Markings.

Add the following:  Payment for Pay Item 643(24), Portable Changeable Message Board Mobilization will be full compensation for all labor, equipment, and materials required to mobilize four portable message board signs to the project.  The signs will become the property of the Contractor upon completion of the project.

Payment for Pay Item 643(25), Portable Changeable Message Board Signs will be full compensation for all labor, equipment, and materials to provide, move, maintain, program, and operate a portable message board sign on the project.

Payment for Pay Item 643(26), Public Relations will be full compensation for all labor, equipment, materials, and reports required to furnish public relation services as detailed in subsection 643-1.03a, Public Relations.  If mailouts are distributed in the Municipality utility bills, the cost of providing this additional service will be paid by Change Order as an extra cost.

Add the following pay items:

Pay Item No.		     Pay Item	           	Pay Unit

643(24)	  Portable Changeable Message	     Lump Sum

Board Mobilization

643(25)	  Portable Changeable Message      Calendar

Board Sign				  Day

643(26)		 Public Relations			Lump Sum

SECTION 644

SERVICES TO BE FURNISHED

BY THE CONTRACTOR

Special Provisions

644-2.01  Field Office.  Revise this subsection to read:  The project office shall have a minimum 2,000 square feet of floor area, 250 square feet of window area, a thermostatically controlled interior heating system, and attached indoor plumbing and lavatory facilities.  The office area shall be divided so that it contains a minimum of three (3) each office rooms separated by closable doors.  Each office room shall have a minimum of 350 square feet of floor area.  There shall be adequate parking for a minimum of 25 vehicles.  The office shall be located within one (1) mile of the project and be made available for occupancy within 10 days of the receipt of Notice-to-Proceed through 30 days after final acceptance.

(9/1/89)

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  Description.  This Training Special Provision is in implementation of 23 U.S. Code 140(a).

As part of the Contractor's equal employment opportunity affirmative action program, the Contractor shall provide on-the-job training aimed at developing full journeymen in the type of trade or job classification involved.  The number of trainees to be trained under this contract is one.

645-2.01  Objective.  Training and upgrading of minorities and women toward journeyman status is a primary objective of this program.  Accordingly, the Contractor shall make every effort to enroll minority trainees and women to the extent that such persons are available within a reasonable area of recruitment and will be responsible for documenting such efforts in order to demonstrate compliance with this Training Special Provision.  This training commitment is not intended, and shall not be used, to discriminate against any applicant for training, whether a member of a minority group or not.

645-3.01  General.  The Contractor shall determine the distribution of the required number of trainees among the various work classifications based on his needs and the availability of journeymen within a reasonable area of recruitment.

It is the intention of these provisions that training is to be provided in the construction crafts rather than clerk-typists or secretarial-type positions.  Training is permissible in lower level management positions such as office engineers, estimators, timekeepers, etc., where the training is oriented toward construction applications.  Training in the laborer classification may be permitted provided that significant and meaningful training is provided and approved.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Reimbursement for offsite training indicated above may only be made to the Contractor where he does one or more of the following and the trainees are concurrently employed on a Federal-aid project; contributes to the cost of the training, provides the instruction to the trainee or pays the trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit his training proposal for approval, indicating the number of trainees to be trained in each selected classification and the training program to be used.  Furthermore, the Contractor shall specify the starting time for training in each of the classifications.  To this end, completed certification forms, appropriate to the classifications selected, shall be submitted for each trainee.

1.	Trainees in apprenticeship programs currently approved by the U.S. Department of Labor shall be entered on Form 25A311 "Contractor's FHWA Apprenticeship Certification."

2.	Trainees not in approved apprenticeship programs, including laborers and teamsters, shall be entered on Form 25A310 "Contractor's FHWA OJT Certification."  These trainees shall receive at least 500 hours training on the project.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor and approved by the Department.  The Department shall approve any program which will reasonably qualify the trainee for journeyman status in his classification by the end of the overall training program, and which conforms to the Contractor's equal employment obligations.  Existing approved programs shall be considered acceptable except in those cases where the Department has determined that the program is not being administered in a manner consistent with the equal employment obligations stipulated in Federal-Aid provisions.

It is normally expected that a trainee will begin his training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist in his work classification or until he has completed his training program.  It is not required that all trainees be on board for the entire length of the contract.  A Contractor will have fulfilled his responsibilities under this Training Special Provision if he has provided acceptable training to the number of trainees specified.

If, in the judgement of the Contractor, a trainee becomes proficient enough to qualify as a journeyman before the end of the prescribed training period, and the Contractor so employs such trainee, the individual training program will be considered completed.

The Contractor shall furnish each trainee a copy of the program he will follow during training on the project, and with a certification showing the type and length of training satisfactorily completed.  No employee shall be employed as a trainee in any classification in which he has successfully completed a training course leading to journeyman status, or in which he has been employed as a journeyman.

The Contractor shall advise all employees and applicants for employment of available training programs and entrance requirements for each.

The Contractor shall periodically review the training and promotion potential of minority group and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each trainee.

645-3.02  Wages.  Trainees will be paid at least 60 percent of the appropriate minimum journeyman's rate specified in the contract for the first half of the training period, 75 percent for the third quarter of the training period, and 90 percent for the last quarter of the training period, unless apprentices or trainees in an approved existing program are enrolled as trainees on this project.  In that case, the appropriate rates approved by the U.S. Departments of Labor or Transportation in connection with the existing program shall apply to all trainees being trained for the same classification who are covered by this Training Special Provision.

645-3.03  Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the trainees are to be trained by the subcontractor.  Any such subcontracts shall include the appropriate training provisions and pay item.  However, primary responsibility for meeting the training requirements imposed remains with the Contractor.

645-4.01  Method of Measurement.  The Contractor will be credited for each approved trainee employed by him on the project and reimbursed on the basis of man-hours worked, as listed in the certified payrolls.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  Basis of Payment.  Payment will be made at the contract unit price for each accepted man-hour of training performed.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment may be made for training persons in excess of the number specified herein, when approved by the Engineer.

Payment will be made following completion of each approved training program for the project.  No payment will be made to the Contractor if he fails to provide the required training or fails to hire the trainee as a journeyman upon completion of the program, and if such actions indicate a lack of good faith in meeting these requirements.

Payment will be made under:

Pay Item No.          Pay Item          Pay Unit

645(1)          Training Program      Man-Hour

(8/1/88)

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.01  Description.  Add the following:  This work shall also include furnishing and installing new traffic detector loops, adjustment of junction boxes, relocating light standards, and replacement of side mounted traffic signals.

660-1.02  Regulations and Code.  Add the following:  Underground conduit fill and bending shall conform to the National Electric Code.

660-1.05  Maintaining Existing and Temporary Electrical Systems.  Add the following to paragraph 7:  Relocated lighting shall be in operation as soon as practical and in no case later than when the final configuration of the roadway or lane construction requiring the lighting relocation is opened to traffic.

Add the following:  Contractor shall maintain the existing illumination system for all segments of road until the new system is complete and ready for activation, except where existing electroliers conflict with new construction or where new luminaire heads are installed on existing electroliers.  No segment of the road may be without highway illumination for over 72 hours.  Where light standards are required to be relocated the Contractor has the option of installing a temporary lighting system.  Intersection illumination shall be maintained at all periods of darkness (defined as sundown to sunrise).  The Contractor shall schedule and stage his work to fulfill these requirements.

The Contractor shall provide temporary signalization at the intersections as required.  At no time shall any of these intersections operate in an unsignalized mode, except for shutdown due to change over from the existing system to a temporary system, and from the temporary system to a permanent system.

A plan for each temporary signal system shall be submitted to and approved by the Engineer prior to implementation.  The temporary signal plan shall equal or exceed the system being replaced or modified.  That is, the plan shall not downgrade the number of signal heads, signal phases, pedestrian push-button, etc.

The Contractor shall furnish and install all materials and miscellaneous hardware required to provide a functional traffic signal system.  All materials shall conform to the requirements of the plans and specifications.  Temporary equipment shall be compatible with existing equipment used in the Central Region.  Existing load centers shall be used.

The temporary signal system may consist of:  the existing systems, relocations of the component parts, guyed wood poles, or any portion of the permanent signal system.  Traffic signals may be suspended from messenger cables provided they are mounted by standard span wire hangers and secured with a second cable to prevent misalignment in a wind.  All signal faces shall be equipped with backplates and visors.  The signal faces of each phase with two or more faces shall be energized using two circuits, with each circuit wired with an IMSA 20-1 signal cable; splices shall be made only at the terminal blocks in the signal faces.  Sufficient signal cable slack shall be left at each pole to provide for drip loops and to allow realignment of each signal head.  Temporary controller assemblies may be mounted on Type III junction boxes while work is completed on the permanent systems.

Vehicle detection is required and shall remain operational for the temporary and permanent signal systems until no longer practical due to excavation of detector loops.  At that time, the controller will revert to the pre-timed mode.  However, prior to the Department's acceptance of the signalized intersections for winter maintenance, vehicle detection shall be installed and working to the same extent as it was in the original and temporary signal systems prior to their removal.

Existing signal heads and traffic signs may require temporary covering or removal in case of conflicting traffic flow.

Temporary signal heads may be mounted on the existing mast arms to facilitate changes in traffic patterns.  The Contractor shall be careful not to overload existing poles and mast arms.

660-1.06  Scheduling of Work.  Add the following subsection:  Don McAllen (786-8355), with the Municipality of Anchorage (MOA) shall be contacted by the Contractor at least 24 hours prior to the cutting of any signal interconnect cable.  A representative of the MOA shall be on site during the cutting and splicing of this cable.  The Contractor shall have all materials needed for this splice and conduit tie-in on site prior to the cutting.  After cutting, the work associated with the installation of the additional conduit and splicing of the cable shall be completed as quickly as possible.  The Contractor shall not leave the site until this cable is spliced, in working order and accepted by MOA.

660-2.01  Excavating and Backfilling.  Delete the third paragraph in its entirety and substitute the following:  Only excavation within the structural section shall be backfilled in conformance with the provisions of Subsection 204-3.01.

660-2.03  Foundations.  Add the following:  Foundations for existing lighting that is being relocated may be reused.  If the Contractor elects to re-use an existing foundation, it shall be installed the same as for corrugated steel pipe forms.  Signal foundations shall not be re-used.  Contractor shall be responsible for re-plumbing light poles that lilt do to foundation settlement.

660-2.04  Poles, Steel Pedestals and Posts.  Delete the third paragraph.

Add the following:  All poles and mast arms shall be designed for 100 MPH wind speeds with gusts to 130 MPH.

The Contractor shall relocate existing standards per the plans in a manner that maintains the existing condition.  The Contractor will be required to replace, at his expense, standards which are damaged or destroyed by his operations.  Relocated galvanized standards with rusted or scarred areas shall be repaired and re-coated in accordance with Subsection 660-2.14.  Repair and re-coating of rusted or scarred areas less than or equal to 10 percent of each standard's total area shall be subsidiary to other work of Section 660 and not measured or paid for directly.

660-2.05  Conduit.  Add the following:  Trenching to install conduits across roadways with an existing paved surface will be allowed.  No trenching of new final course asphalt will be allowed.  No trenching of existing asphalt not scheduled for removal or overlay will be allowed.

660-2.09(A)  Wiring.  Add the following after the second paragraph:  Interconnect splices shall be made by the Municipality of Anchorage.  The Contractor shall label the interconnect cable and neatly store five feet of the cable within the terminal facility as shown on the drawings.

Add the following between the words "signal" and  "conductors" in the seventh paragraph:  ..."and feeder"...

Add the following after the tenth paragraph:  The Municipality of Anchorage (MOA) shall perform terminal strip connections and channel assignments for all new detector lead in cable.  The Contractor shall label the lead-in cable and neatly store ten feet of cable within the controller cabinet.

Add the following:  All new and existing relocated signals shall be wired by the Contractor.  Where several existing or relocated signal heads were served with one cable, and are modified by the plans to be replaced with individual cables, the Contractor shall modify terminal strip within the controller cabinet accordingly.

660-2.10  Bonding and Grounding.  Add the following after the first paragraph:  All hardware, including insulated throat grounding bushings, ground rods, and ground rod clamps shall be Underwriter's Laboratory listed.

660-4.01  Installation Details.  Under loops, numbered paragraphs 7 and 9, change "660-2.08" to read "660-2.09(A)".

Add the following after Item 9:

10.	The Contractor must make sawcuts to make loop installations in existing pavement.  Detection loops within 11 feet of another loop in the existing pavement shall have all existing pavement between the loops sawcut and removed, then repaved continuously.  All traffic markings removed as a result of loop installation in existing pavement shall be replaced with painted traffic markings to the original alignment and messages.  All work shall be subsidiary to Item 660(11) Traffic Detector Loops.

Add the following:  Relocated Equipment.  All existing signal heads and backplates, pedestrian signals, pedestrian push buttons, and mounting apparatus designated by the plans to be relocated shall be painted in accordance with Subsection 660-2.15, and shall be dark olive green.  Colors integral to the equipment need no paint.

Equipment that is re-wired but not relocated shall require no painting unless ordered by the Engineer and will constitute extra work with payment as provided under Subsection 109-1.05.

The Contractor shall clean the lenses and re-lamp the signals that are designated by the plans to be rewired or relocated.

660-5.02  Backplates.  In the last paragraph, change "660-2.16" to read "660-2.15".

660-5.03  Signal Head Mounting.  Add the following:  Signal heads that are designated for field location shall be field drilled, holes prepared and painted, and mounted on the mast arm with Astro-brackets by Pelco Products, Inc. or approved equal.

Relocated and new signals designated to be side mounted on poles shall reuse existing terminal compartments and brackets.  Existing terminal compartments brackets must be modified in alignment or length to accommodate new side-mount signals.

All relocated mountings shall be painted in accordance with Subsection 660-2.15(2).

660-6.07  Salvaging Electrical Equipment.  Add the following to the first paragraph:  All equipment to be salvaged shall be delivered to the State Maintenance yard at 5700 E. Tudor Road, Anchorage.

Delete the first sentence of the fourth paragraph and substitute the following:  Unless otherwise specified, junction boxes (not including lids), underground conduit, conductors, foundations and detectors not to be used in the new system, shall become the property of the Contractor and shall be removed from the highway right-of-way.  Junction box lids shall be salvaged.

660-6.09  Method of Measurement.  Add the following subsection:  The Traffic Signal System Complete shall be measured by the lump sum for individual intersections.  It shall include all work associated with the Traffic Signal System including, but not limited to the traffic signals, highway lighting system, detector loops, and signal interconnect cable, as shown on the plans.

Each traffic detector loop that is located at an intersection that does not have a pay item for traffic signal system complete shall be measured individually.  The conduit, cable, and junction boxes necessary for each loop detector will not be measured separately.

Each junction box required to be adjusted shall be measured for payment only once, when adjusted to final grade.  All other adjustment for intermediate construction activities shall be subsidiary to those activities.

Each light standard required to be relocated shall be measured individually when complete and functioning.  The necessary conduit, cable, and junction boxes will not be measured separately.

Each sidemounted traffic signal head required to be replaced will be measured individually.

660-7.01  Basis of Payment.  Add the following: Payment for each traffic detector loop shall be full compensation for furnishing all labor, material, tools, equipment, and incidentals for a complete and functioning traffic detector loop.

Payment for the adjustment of Junction Boxes shall be full compensation for adjusting a Junction Box to final grade as required in Section 660-2.06.

Payment for relocating light standards will be full compensation for furnishing all labor, material, tools, equipment, and incidentals to remove and re-install a complete and functioning lighting system.  Temporary lighting systems shall be subsidiary to relocating light standards.

Payment for the replacement of sidemounted traffic signals will be full compensation for furnishing all labor, material, tools, equipment and incidentals to remove a sidemounted traffic signal head and replace it with a new sidemounted signal head complete and functioning.

Payment for traffic signal timing or re-timing adjustments performed by the Municipality of Anchorage will be a subsidiary obligation to the appropriate 660 item.

Add the following Pay Items:

Pay Item No.          Pay Item               Pay Unit

660(11)       Traffic Detector Loop          Each

660(12)     Adjustment of Junction Box       Each

660(14)       Relocate Light Standard        Each

660(15)     Replace Traffic Signal Head      Each

SECTION 661

ELECTRICAL LOAD CENTERS

Special Provisions

661-1.02  Equipment List(s) and Drawings.  Add the following subsection:  The Contractor shall submit for review and approval, within 30 days following award of the contract, 8 collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s) and the following:

1.	For materials on the Approved Products List:  a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

2.	For materials not on the Approved Products List:  catalog cuts that include the manufacturer's name, type of product, size, model number, conformance specifications, and supplemented by other data as may be required, including manufacturer's maintenance and operations manuals, or sample articles.

This information may be included in the portfolio for 660 items.

The Department will not be liable for any material purchased, labor performed, equipment used, or delay to the work before all equipment and materials have been reviewed and approved.

661-2.01  Materials.  Add the following:  Type 1 load center cabinets shall be constructed similar to the section and elevations shown in the plans, and conform to the following requirements.  Slight variation in the dimensions is allowable, except in the anchor bolt template.

1.	The cabinet shall be constructed of zinc-coated A60 finish sheet steel per ASTM A525 with no external screws, bolts, or nuts.  The components shall have the following minimum thickness as measured by the United States Standard Gauge:  the exterior shell No. 12 gauge, the interior doors and panels No. 14 gauge, and the interior covers No. 16 gauge.

2.	The components shall be painted with a 2-part urethane paint undercoating inside and out.  The final finish shall be a 2-part urethane paint, standard white for removable panels and non-gloss silver-gray, closely matching Color No. 36622 of Federal Standard Specification No. 5950 for the enclosure.

3.	The service entrance section shall be isolated from the main load section and distribution load section by non-removable metal barriers, and shall be equipped with landing lugs for termination of service conductors.

4.	The cabinet shall be provided with internal mounting brackets sized for 1/2-inch anchor bolts for use with a standard mounting base assembly.

5.	All doors shall be equipped with continuous stainless steel pin hinges, coin latches and hasp for padlock.  The meter section door shall have a clear polycarbonate resin window, 0.187" minimum thickness, with a minimum size of 10.0-inch x 10.0-inch, which shall be sealed with silicone.

6.	Each completed load center assembly shall be provided with an exterior name plate, safety labels, interior identification labels, wiring diagram, and installation instructions.

7.	When two type 1 load centers are to be installed adjacent to one another, furnish one cabinet with the load distribution section located on the left side.

When required, type 2 and 3 load center cabinets shall be sized and wired to serve the combination of highway lighting, traffic signal and thaw wire circuits shown in the plans.  Each cabinet shall be a single box, subdivided to form compartments as required, and constructed of formed and welded, code gauge steel, finished with gray baked enamel, electro-deposited on cleaned phosphatized steel and suitable for surface mounting.  A hinged lockable door with hasp shall be installed over each compartment.

The wiring configuration for each load center type shall be in accordance with the wiring diagram indicated on the load center detail sheet.  Circuit breaker ratings shall be as shown in the load center summary for each location.  Dead panels shall be indelibly labeled with the circuit number and the direction of the circuit run from the load center.

When the load centers are ready to be energized, the Contractor shall request and coordinate an electrical inspection of the load centers from the local authority having jurisdiction, allowing at least 5 working days before the inspection is needed.  The Contractor shall be present during the inspection to assist in accessing the cabinets and to answer questions.  The Contractor shall correct the deficiencies noted in each load center.

Payment of any fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be considered incidental to the Section 661 items.  (9/1/89)

All breakers shall have an ampere interrupting capacity (A.I.C.) of 20,000 or greater, unless the Contractor can show that a direct short across the serving transformer would result in a lower current.

661-3.01  Construction Requirements.  Delete the third paragraph in its entirety and substitute the following:  The Contractor shall install a rigid metal conduit at the location and depth as shown on the plans, threaded, capped and extended 12-inches from the face of the load center base.  The terminus shall be marked with a 2-inch by 4-inch by 4-foot stake.

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDER STATIONS

Special Provisions

669-1.01  Description.  This work shall consist of furnishing and installing traffic count stations for the automated collection of traffic data on an intermittent basis.  The Automated Traffic Recorder (ATR) station is a vehicle detection system.  Each intermittent volume count system specified herein shall consist of the following parts:

Inductive loop detectors for detecting the presence of vehicles, underground conduit, junction boxes, wiring, cabinet, and other items required to construct an operational system as specified.

The locations of traffic detection and cabinets shown on the plans are approximate and the exact locations shall be established in the field by the Engineer after consultation with the Department's Highway Data Section.

Concrete pavement work shall consist of furnishing and placing portland cement concrete for the concrete road section at the Weight In Motion (WIM) Installation site in conformance with Section 501, Structural Concrete, or as established in the plans.

General descriptions of the Automated Traffic Recorders included in the Tudor Road project are as follows:

Assembly H1--A four loop configuration, intermittent ATR without electrical or telephone service.

Assembly H2--A four loop configuration, intermittent ATR without electrical or telephone service.

Assembly H3--A twenty loop configuration, permanent ATR with electrical and telephone service.

Assembly H4--A two loop configuration, intermittent ATR without electrical or telephone service.

Assembly H5--A two loop configuration, intermittent ATR without electrical or telephone service.

Assembly H6--A four loop configuration, intermittent ATR without electrical or telephone service.

Assembly H7--A four loop configuration, intermittent ATR without electrical or telephone service.

Assembly H8--A twelve loop configuration, permanent ATR with electrical and telephone service.

Assembly H9--A four loop configuration intermittent ATR without electrical or telephone service.

Assembly H10--A twenty loop configuration, permanent ATR with electrical and telephone service.  This assembly will require a 288 foot section of Highway to be concrete and the inductive loops will be installed by the saw cut method.

Assembly H11--A five loop configuration, intermittent ATR without electrical or telephone service.

669-1.02  Regulations and Code.  All materials and workmanship shall conform to the standards of the Underwriters Laboratories, Inc., and the National Electrical Safety Code, and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturers Association, where applicable.

669-2.01  Materials.  All materials provided for the work shall be new, unless otherwise stated, and must meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with Subsection 660-2.09(A), Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable.

2.	Conduit.  All conduit shall be in accordance with Subsection 660-2.05, Conduit.  Nylon pull cords shall be left in all two inch conduit.

3.	Junction Boxes.  All junction boxes shall be in accordance with Subsection 660-2.06, Junction Boxes.  Junction boxes used for ATR installations shall not contain any conductors carrying a voltage over 50 volts.

4.	Terminal Blocks.  All terminal blocks shall be provided with nickel, silver or cadmium plated brass binder head screw terminals.  Terminal blocks shall be a barrier type, 600vac @ 20amps, capacity for 12-18 AWG wire.  All terminal blocks shall have removable shorting bars in each position and have integral type marking strips.  All conductors shall be terminated and labeled to a terminal block.

All terminal blocks mounted in junction boxes shall be waterproofed with a re-enterable type sealant and encapsulated in a rigid, two piece, snap together plastic mold.

5.	Inductive Loops.  All inductive loops shall be in accordance with Subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be UL listed as Type RHW/USE/XLP 12AWG 600V rating.

Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, and aluminum shield and overall PVC or PE jacket conforming to IMSA specification 50-2.

6.	Cabinets.  All style 3 cabinets shall be in accordance with Subsection 660-3.05, Controller Cabinets.  All cabinets shall be aluminum and painted.  All cabinets shall have a NEMA 3R specification.  All style 1 and 2 cabinets shall be installed as indicated on the plans.

7.	Concrete Pavement.  Materials used for concrete pavement shall conform to Section 501-2.01, Materials.

669-3.01  Construction Requirements.

1.	Wiring.  All wiring shall be installed in accordance with Subsection 660-2.09(A), Wiring.  All unused pairs shall be terminated within splices, at cabinets unused pairs shall be terminated at a terminal block and labeled "SPARE".

2.	Conduit.  All conduit shall be installed in accordance with Subsection 660-2.05, Conduit or as indicated on the plans.

3.	Junction Boxes.  All junction boxes shall be installed in accordance with Subsection 660-2.06, Junction Boxes or as indicated on the plans.

4.	Terminal Blocks.  All terminal blocks and wire pairs shall be clearly labeled on the block.  Terminal blocks within cabinets shall be permanently mounted so that all terminals are easily accessible from the front of the cabinet.  By convention, wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block.

Re-enterable splice kits containing terminal blocks in junction boxes shall be placed with the long dimension horizontal, and firmly mounted within six inches of the top of the box.  All conductors shall terminate and be soldered to "spade" type terminal lugs.

5.	Inductive Loops.  All inductive loops shall be installed and constructed in accordance with Subsection 660-4.01, Installation Details, Loops, unless otherwise specified in the plans.

All inductive loops shall be formed of four turns of wire, and shall be six feet square with plus-or-minus one inch tolerance.  All inductive loops shall be centered in the indicated traffic lane.  All inductive loops within a lane shall be located sixteen feet from leading edge to leading edge, with plus-or-minus one inch tolerance.  Inductive loops located in parallel lanes shall be within  one inch of being directly adjacent to each other.

Loops shall not be cut into final lift asphalt pavement.

All lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the center line of the road.

6.	Cabinets.  All style 3 cabinets shall be installed according to Subsection 660-4.01, Installation Details.  All style 1 and 2 cabinets shall be installed as indicated on the plans.

7.	Concrete Pavement.  Construction of concrete pavement shall be in accordance with Section 501-3.01 through 501-3.10.

All reinforcement steel shall be placed five inches (5") below concrete surface.

a.	Surface Treatment

(1)	Grinding Procedure and Tolerance.  Grind each traffic lane continuously for a minimum of 288 feet,at a vertical tolerance of 1/10 inch per 10 feet along the travel lane without any repeating waviness or unevenness.

(2)	Induction Loops.  Induction Loop saw cuts shall be made after the grinding operation.

669-3.05  Deliverables.

1.	Equipment List(s) and Drawings.  The Contractor shall submit for review and approval, within thirty days following award of the contract, nine collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s), and a description that includes product name, manufacturer, model or part number.

2.	As-Built Plans.  The Contractor shall prepare four complete sets of as-built plans which will be kept current with the construction.  These as-built plans shall detail all construction changes made to the plans and also include the following information on the appropriate sheets the location and depth of all inductive loops and conduit runs, and the station and offset of all junction boxes.

Two sets of as-built plans shall be presented to the Project Engineer for distribution to the Highway Data Section (HDS), and one set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet door at the appropriate Automated Traffic Recorder installation.

3.	Tests Results.  Two written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Project Engineer prior to acceptance of the Automated Traffic Recorder installation.  Distribution shall be:

1-Technical Services

2-Highway Data Section

1-Cabinet (in plastic holder with As-builts)

669-4.01  Method of Measurement.  The quantity to be paid for will be the actual number of completed and accepted Automated Traffic Recorder installations as shown on the plans or as directed by the Engineer.

The Class A concrete required for concrete pavement will not be measured for payment.

As-built plans will not be measured for payment, but the lump sum price will be paid under pay item 669(2), Traffic Recorder As-Builts.

669-5.01  Basis of Payment.  The contract unit bid price per each Automated Traffic Recorder installation shall be full compensation for providing all equipment, labor and materials necessary to complete the work as specified.  This includes the cutting and patching of existing asphalt, where necessary.

Class A concrete will be paid under Item 501(1), Class A Concrete.

Excavation and other modifications required for this installation shall be paid under their respective pay item numbers.

Payment will be made under:

Pay Item No.         Pay Item             Pay Unit

669(1-__)       Automated Traffic       Lump Sum

Recorder at Station ______

669(2)     Traffic Recorder As-Builts   Lump Sum

SECTION 670

TRAFFIC MARKINGS

Standard Modifications

670-3.01  Construction Requirements.  In the last paragraph under Item 2., insert "pneumatic" immediately before "roller".  (5/12/89)

Special Provisions

670-3.04  Paint Removal.  Change title of subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following:  Existing pavement markings shall be removed to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement.  Painting over existing striping does not meet the requirement for removal.  Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

Add the following Section:

SECTION 681

ELECTRICAL POWER RELOCATION

Special Provisions

681-1.01  Description.  The Contractor shall be responsible for furnishing all labor, equipment and materials necessary to install electrical duct bank and pad.  The electrical duct bank will consist of multiple conduits of the number shown on the plans.  The Utility will supply and pull the electrical power cable.

The Contractor doing this work shall be licensed as an electrical Contractor by the State of Alaska.  His work will be closely inspected by Chugach Electric Association (Chugach) with their instructions relayed to the Contractor through the Engineer.  The Chugach representative will be assigned for the entire underground installation, and no work shall proceed without him on site.  The Contractor shall advise Chugach in writing at least 24 hours in advance of his actual duct system work indicating both location and time.

681-2.01  Materials.  RSC conduit and preformed RSC elbows shall be manufactured of mild steel with a galvanized coating.  Conduit locator plates shall be supplied by the Contractor and be standard materials for locating the ends of buried conduits.  Concrete pad dimensions and installation details shall conform to CEA SUM1 specification.  Ground rod installation shall conform to CEA SUG7 specification.

681-2.02  Applicable Standards and Codes.  In order to resolve any questions on safety regulations, installation practices, and testing procedures, the Contractor shall consult and make himself familiar with the applicable parts of the current editions of the following standards and codes:

1.	Alaska State Safety Code

2.	Arctic and Subarctic Construction - Utilities,  US Army Corps of Engineers

3.	CEA Safety Code

4.	National Electrical Code

5.	National Electrical Safety Code

6.	National Electrical Manufacturers Association

7.	Occupational Safety Health Act

8.	Underwriters Laboratories.

All equipment and material furnished under this Section shall conform to the latest applicable specifications and rules of the National Electrical Manufacturers Association, American Standards Association, American Institute of Electrical Engineers and the Federal Specifications cited hereinafter.  As appropriate, all materials used shall be listed on the latest "List of Material Acceptable for Use on Systems of REA Electrification Borrowers", and approved for this electrical system by Chugach.

All materials furnished shall be standard equipment and be of the manufacturer's latest design.  These materials shall be new, and not used, manufacturer's seconds or rejects.  Where two or more units of the same class of material are required, they shall be like products of the same manufacturer.

681-2.03  Verification of Dimensions.  The exactness of dimensions given on any Chugach drawing issued is not guaranteed, and therefore the Contractor shall field verify the accuracy of all dimensions.  In all cases of interrelation with other work, he shall verify in the field all the dimensions relating to the contiguous work.  Any errors due to the Contractor's failure to verify shall be rectified promptly at the Contractors cost.

The specifications and drawings supplement each other and together constitute one complete set of specifications and drawings, so that any work exhibited in one and not in the other shall be executed just as if it had been set forth in both.  It is understood and agreed that the work shall be performed and completed according to the true spirit, meaning and intent of the specifications and drawings.  It is incumbent on the Contractor that he shall furnish all work complete, and that the work be satisfactory in all respects.

681-3.01  General Construction Requirements.  Chugach through the Engineer reserves the right to suspend work on the electrical duct bank installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspension of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

The electrical duct bank shall be installed to result in the maximum degree of reliability and maintenance-free operation.  Kinked ducts, inadequately supported, protected or swabbed ducts, and ducts that are carelessly jointed are not reliable and therefore unacceptable.  Any section of this electrical duct system that is not acceptable will be removed and replaced in accordance with these Special Provisions.

All conduit shall be stored to prevent damage or contamination prior to installation.  Conduit shall not be stored directly on the ground or floor.  They shall be kept clean and dry as possible and free from damaging or deteriorating elements.

If construction or excavation require the removal of any existing privately owned facilities on the provided electrical easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed 2 weeks.

A program of cleanup operations shall be carried out on a continuous basis throughout the progress of construction, and the site shall be left neat and clean.  All equipment, devices and structures shall be inspected after all work of construction and installation has been completed, and any damage shall be repaired or replaced as directed.

681-3.02  Surveying and Staking.  The electrical duct system and pad shall be located and staked by the Contractor at the elevations indicated on the plans.  It shall be his responsibility to schedule a physical inspection of all line and grade prior to placing any ducts.  The Contractor may at that time propose any changes or clarifications that he feels desirable.  These changes, if approved, will be made and recorded by Chugach.  No changes shall be made by the Contractor without prior written approval of the Engineer and Chugach.  Once work commences, the Contractor, the Engineer, and Chugach will meet at the end of each week to review the work to date and plan the following week's work.

All duct system shall be constructed to within an allowable vertical tolerance of 0.1-foot, and a horizontal tolerance of 0.2-foot from the indicated plan location.

681-3.03  Trench and Pad Excavation and Backfill.  All existing underground utilities shall be identified and located, and proper care taken not to damage them.  It shall be the Contractors responsibility to establish the location of each facility by calling for a field locate in accordance with Subsection 105-1.06, Cooperation with Utilities.

The excavation shall be dug in such a manner as to provide a foundation of undisturbed or compacted non-frost susceptible material on which to install the pad and electrical duct bank.  Trench depth shall be shown on the plans, and as staked in the field.  Trenches shall be of the necessary width that will allow compaction equipment to be utilized, and for proper laying of structures or conduit and the banks shall be sloped so as to conform to the prevailing safety requirements.

The trenches shall be maintained in a safe manner at all times to protect workers from cave-ins.  Appropriate shoring shall be employed to assure safety of workers while working in trenches.  Barriers and warning signs shall be employed to protect the public and employees from falling into trenches where such trenches are in areas vulnerable to these accidents.  Vehicles and excavation equipment must not cross over or run near trenches that could cause potential cave-ins.  Construction shall be arranged so the trenches will be left open for the shortest practical time to avoid creating a hazard, and to minimize the likelihood of trench collapse due to other construction activity, rain, and accumulation of water in the trench, etc.  All temporary bridging utilized by the Contractor will be inspected and approved prior to installation.  This does not relieve the Contractor of responsibility for providing bridging of sufficient size and strength.  Any bridging open to public traffic will provide a smooth driving joint.

The Contractor shall not begin excavation of the trench until all personnel, materials and equipment are present to complete the work in the most expedient manner.  Not more than 400 feet of trench shall be open in advance of the installation unless authorized in writing by the Engineer.  There shall be not more than 100 feet of open trench at the end of the work day, unless approved by the Engineer.

The routing of the duct bank shall be as shown on the plans unless the conditions encountered are such that changes are necessary to accomplish the work.  In the event that rock or other obstructions are encountered during the trenching operation so the ducts or pad cannot be installed, the Contractor shall inform the Engineer on the nature and extent of the difficulty encountered for his review and verification.  The Engineer, with the approval of Chugach, will determine whether the duct is to be rerouted, trenched in the rock, or advise on another suitable change.

All excavation shall be inspected and approved by the Engineer before duct bank installation is started.  Trench Acceptance and Conduit Installation shall be filled out by Chugach and signed by the electrical subcontractor after approval of each stage.  Failure to complete these forms will result in the rejection of the work.  The Contractor shall provide 24 hour written notification to Chugach when a section of the duct system is ready for an acceptable inspection and a time for this inspection shall be mutually agreed upon.  Failure by Chugach to attend the prearranged inspection shall not relieve the Contractor of the requirement to have the section accepted by Chugach.

All frost susceptible material below the specified trench depth shall be removed to a depth of 2-feet; all peat shall be removed to non-organic material below the ducts.  Backfill to the electrical duct grade, if necessary, will be with material meeting the requirements of Select Material, Type A deposited in layers not exceeding 8-inches, and each lift shall be compacted to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankment with Moisture and Density Control.

The bottom of the trench must be transversely level and compacted to provide a uniform support for ducts.  Care shall be exercised to minimize the likelihood of waterflow since this may cause trench damage and

reduction in trench depth.  When this occurs, the trench must be cleared to the required depth before installing the ducts.

The soil compaction of the trenches and pad foundations shall be randomly tested at various depths by the Engineer.

681-3.04  Conduits.  The RSC conduit, conduit bushings, and conduit caps shall be supplied by the Contractor and used for roadway crossings.

Fittings - After the conduit joints have been securely tightened, a 12-inch section of heat shrink tube shall be centered on each joint.

Only tools designed for the particular operation shall be used.  Tools shall be kept in good condition, and worn or broken tools shall be removed from the job immediately.

All conduit shall be field bent to follow the trench line and grade with a minimum radius of 25-feet.  All bends will be per the manufacturers recommendations.  The minimum allowable bending radius for equipment entrances is 48-inches.  Preformed sweeps and preformed elbows with bending radii less than 48 inches will not be allowed.  The material for all preformed elbows of 45 degrees will be RSC conduit.  All bends will be approved by the Engineer.

Duct Finishing - After completion of backfilling and compaction the electrical duct systems will be mandrilled, brushed, and swabbed.  The steel mandrill brush shall be 1 1/2 inches in diameter.  If the duct will not accept the mandrill, it will be removed and replaced at no additional expense.  All mandrilling must be done in the presence of the Engineer and Chugach.  All conduit entrances and exits shall then be sealed and plugged.

A polyethylene or polypropylene pull rope, with a minimum breaking strength of 200 pounds, shall be left in each conduit with a 3-foot length of rope projecting from the conduit at each substructure and securely tied.  When a conduit plug is used, the rope shall be securely tied to it in a manner approved by the Engineer.  All pull ropes shall be new and unspliced.

681-3.05  Electrical Duct Bank Installation.  The electrical duct bank on this project will be comprised of multiple RSC conduits of the configuration shown on the plans.  The conduits for the primary distribution circuit will be direct bury as noted on the plans.

It shall be the Contractor's responsibility, with the Engineer's approval, to determine the most expedient method to complete the required electrical duct bank installation.  All work across the roadway shall be accomplished in accordance with Section 115, Traffic Control.

681-3.07  Cable Pulling.  The Utility shall install and splice the electric power cable.

681-4.01  Method of Measurement.  The electrical conduit crossing will not be measured for payment.

681-5.01  Basis of Payment.  Payment will be full compensation for all labor, equipment and materials necessary to complete this work.

The unit bid price will include all necessary excavation to plan grade, and backfill of native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 203(1), Common Excavation.  Backfill to replace unsuitable material will be paid under Item 203(6) Borrow, Type A.

Payment will be made under:

Pay Item No.          Pay Item                Pay Unit

681(16)        Conduit Crossing at          Lump Sum

Station 292+90

Add the following Section

SECTION 684

CABLE TELEVISION RELOCATION

Special Provisions

684-1.01  Description.  The Contractor shall be responsible for furnishing all labor, equipment and materials necessary to install two (2) each poles required for the construction of a temporary aerial feeder circuit across Kingston Drive.  The poles will be retired when the final underground system is accepted and functioning.

The materials and work will be inspected and accepted by an inspector for Prime Cable, with instructions relayed to the Contractor through the Engineer.

684-2.01  Materials.  The Contractor shall furnish 35 foot Class 5 (35/5) poles as required, in good condition, acceptable to the Prime Cable inspector.

684-2.02  Applicable Standards and Code.  In order to resolve any questions concerning installation practices the Contractor shall consult and make himself familiar with the applicable parts of the current additions of the following standards and codes:

1.	Alaska State Safety Code

2.	National Electric Code

3.	National Electric Safety Code

684-3.01  General Construction Requirements.  Prime Cable through the Engineer reserves the right to suspend pole installation at any time the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspension of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

If construction or excavation require the removal of any existing privately owned facilities on the provided easements, the Contractor shall be responsible for coordinating with the owner(s) and for reestablishing lawns, driveways, parking lots, fences, etc. at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period exceed two (2) weeks.

A program of cleanup operations shall be carried out on a continuous basis throughout the progress of construction and the site shall be left neat and clean.  All equipment, devices and structures shall be inspected after all work of construction and installation has been completed, and any damage shall be repaired or replaced as directed.

684-3.02  Pole Removal.  After installation of the permanent underground Prime Cable feeder circuit has been installed across Kingston Drive and has become operational, Prime Cable will remove the temporary aerial feeder cable from poles at Tudor Road Sta 289+45, 75 feet left and 290+25, 75 feet left  The Contractor will then extract the poles.  No part of the poles will be left in the ground.  The resulting voids shall be backfilled and compacted in accordance with Section 203.  All pole material removed shall become the property of the Contractor.

684-3.03  Wood Pole Installation.  The Contractor shall set the poles at a minimum of six feet deep and at a one foot rake against the direction of pull.  Pole backfill shall be thoroughly tamped the full depth.  Excess soil shall be banked around the pole.

The approximate location of the poles to be set are given below:

Station            Offset

289+45         75 Feet Left

290+25         75 Feet Left

684-4.01  Method of Measurement.  Set 35/5 pole shall be measured by each pole, and shall include the necessary staking, excavation, backfill and compaction.

Utility pole removal shall be measured by each pole withdrawn, backfilled, compacted and clean-up as required.

684-5.01  Basis of Payment.  Payment will be full compensation for all labor, equipment and materials necessary to complete this work.

Payment will be made under:

Pay Item No.          Pay Item           Pay Unit

684(3)         Set 35-Foot Pole         Each

684(4)       Utility Pole Removal       Each

SECTION 702

ASPHALT MATERIALS

Standard Modifications

702-2.04  Storage And Application Temperatures.  In Table 702-1, change storage temperatures for ACs from "340 Max" to "325 Max".  (5/12/89)

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  Fine Aggregate For Concrete.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

703-2.02  Coarse Aggregate For Concrete.  In the first sentence, insert ", class B," after "AASHTO M 80".  (5/12/89)

Special Provisions

703-2.03  Aggregate for Base.  Add to the requirements:

Plastic Index     AASHTO T-90     6 max.

Standard Modifications

703-2.04  Aggregate For Plant Mix Asphalt Pavement.  Add the following to the end of the second paragraph:  ", including S1.1, Sulfate Soundness Test."

(5/12/89)

Special Provisions

703-2.04  Aggregate for Plant Mix Asphalt Pavement.  In the third paragraph, after Fine Aggregate, delete the remainder of the sentence after "thereof" and add the following:

The fine aggregate will meet the following requirements:

Plastic Index     AASHTO T-90     4 max.

Sodium Sulfate    AASHTO T-104   15 percent max.

Soundness Loss

Add the following to Table 703-3, Asphalt Concrete Aggregate:

Asphalt Concrete

Sieve Designation                   Type IA

1-inch                           100

3/4-inch                          80-95

1/2-inch                          60-90

3/8-inch                          50-82

No. 4                            30-70

No. 10                           14-59

No. 40                            7-40

No. 80                            6-25

No. 200                            3-8

703-2.07  Selected Material.  Add the following to Item 1., Selected Material, Type A:  It shall have 30 to 70 percent by weight of particles passing the No. 4 sieve.

(9/1/89)

SECTION 707

METAL PIPE

Special Provisions

707-2.06  Service Pipe.  Delete in its entirety and substitute the following:

Pipe.  Ductile iron pipe or soft drawn seamless copper type "K" shall be used for all water service pipe.  Galvanized pipe, asbestos-cement pipe and the use of lead-tipped gaskets shall be prohibited.

Key Box, Valve Box.  The key box shall provide clear and unobstructed access to a valve or curb stop to enable the AWWU operation of the valve or curb stop.  Key boxes or valve boxes shall be furnished and installed in accordance with Subsection 627-3.05, Valve Boxes and Subsection 712-2.11, Valve Service Boxes.  AWWU key boxes shall not be in contact with a natural gas main or service line.

707-2.07  Sewer Conduit.  Add the following subsection:

1.	Applicable Standards for Sewer Conduit.  The most recent revision for the following standards for the American Society for Testing and Materials (ASTM), the American Association for State Highway and Transportation Officials (AASHTO), the American

Standards Association (ASA), and the American Water Works Association (AWWA) are hereby made a part of these specifications:

ANSI/AWWA C104/A21.4	Cement Mortar lining for ductile-iron pipe and fittings for water

ANSI/AWWA C105/A21.5	Polyethylene encasement for ductile-iron piping for water and other liquids

ANSI/AWWA C110/A21.10	Ductile-iron and gray-iron fittings, 3 in. through 48 in., for water and other liquids

ANSI/AWWA C111/A21.11	Rubber-gasket joints for ductile-iron and gray-iron pressure pipe and fittings

ANSI/AWWA C115/A21.15	Flanged ductile-iron pipe with threaded flanges

ANSI/AWWA C150/A21.50	Thickness design of ductile-iron pipe

ANSI/AWWA C151/A21.51	Ductile-iron pipe, centrifugally cast in metal molds or sandlined molds, for water or other liquids

ANSI/AWWA C-600-87		Installation of ductile-iron water mains and their appurtenances

2.	Ductile Iron Pipe and Fittings.

a.	Pipe.  Ductile iron pipe shall conform to ANSI/AWWA C151/A21.51, with cement mortar lining meeting the requirements of ANSI/AWWA C104/A21.4.  Class 52 ductile iron pipe shall be used for sewer force main conduit between 3 and 16-inches in diameter unless otherwise indicated on the plans.  Class 50 ductile iron pipe shall be used for gravity sewer main conduit between 8 and 24-inches in diameter unless otherwise indicated on the plans.

b.	Fittings.  All fittings shall be a minimum 250 psi pressure rating, either lined or unlined, either cast iron or ductile iron, unless otherwise indicated on the plans or in these Special Provisions.  All fittings shall conform to the requirements of ANSI/AWWA C110/A21.10.

Rubber gasket joints for ductile iron pipe and fittings shall conform to ANSI/AWWA C111/A21.11.

(9/1/89)

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.14  Preformed Pavement Markings.  Add the following to paragraph A. under Item 1., General Requirements:  The preformed ribbon shall consist of one solid piece of required width and length.  In solid stripe areas, the tape length shall, where possible, be a minimum of 100 feet.

712-2.15  Temporary Raised Pavement Markers.  Add the following:  The temporary raised pavement markers shall be installed utilizing an approved raised pavement marker flexible bituminous adhesive.

The color of the raised pavement markers shall conform to the color of the marking for which they serve as a positioning guide, or for which they supplement, or substitute.

SECTION 714

PRESERVATIVES AND PRESERVATIVE TREATMENT

PROCESSES FOR WOOD MATERIALS

Special Provisions

714-2.01.  Add the following:  The following preservative treatments with corresponding retention values are allowed for the particular material being treated.

Preservative    Retention

Material      Standard      Treatment         Value

Fence Posts   AWPA C5       Creosote	       10 pcf

Pentachlorophenol    0.50 pcf

ACC            0.50 pcf

ACA            0.40 pcf

ACZA           0.40 pcf

CCA            0.40 pcf

Plywood       AWPA C9      Creosote            10 pcf

Pentachlorophenol    0.50 pcf

ACZA           0.40 pcf

CCA            0.40 pcf

SECTION 726

TOPSOIL

Standard Modifications

726-2.01  Topsoil.  In the second paragraph, change "not less than 1%" to read "not less than 3%".  (5/12/89)

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01  Embankment Separation and Reinforcement.  Delete this Subsection and Table 729-1 on page 575 in their entirety and substitute the following:

1.	Fibers used in the manufacture of geotextiles, and the threads used in joining geotextiles by sewing, shall consist of long chain synthetic polymers, composed of at least 85% by weight polyolefins, or polyesters.  The geotextile shall be formed into a stable network such that the filaments or yarns retain their relative position to each other.  Both the geotextile and threads shall be resistant to chemical attach, mildew, and rot.

2.	Nonwoven geotextile may be formed by the needle-punched, spun-bonded or heat-bonded process.

3.	Woven geotextile shall be woven into a uniform pattern with distinct and measurable openings.  Edges of the cloth shall be selvaged to prevent the outer yarn from pulling away from the cloth.  The fabric shall be free from defects.

4.	The geotextile supplied shall meet the requirements listed in Table 729-1 for the type specified.

5.	The Contractor shall submit certification that the geotextile supplied meets the above requirements before it is used on the project.

Table 729-1

GEOTEXTILE REQUIREMENTS FOR

EMBANKMENT SEPARATION AND REINFORCEMENT

┌─────────────────────────────┬────────────┬───────────────┐

│                      Test   │            │               │

│Geotextile            Method │            │               │

│Property              (ASTM) │ Separation │ Reinforcement │

│                             │            │               │

│Grab Elongation,      D-4632 │  <50   >50 │    30 max.    │

│% @ Breaking Load            │            │               │

│                             │            │               │

│Grab Tensile          D-4632 │  175   105 │     180       │

│Load, lbs., min.             │            │               │

│                             │            │               │

│Bursting Strength     D-3786 │  N/A   N/A │     290       │

│psi., min.                   │            │               │

│                             │            │               │

│Trapezoid Tearing     D-4533 │   50    40 │      65       │

│Strength, lbs., min.         │            │               │

│                             │            │               │

│Puncture Resistance   D-4833 │   70    40 │      75       │

│lbs., min.                   │            │               │

│                             │            │               │

│Water Permittivity,   D-4491 │ 0.04   0.3 │               │

│1/sec., min.                 │            │     0.02      │

│                             │            │               │

│Apparent Opening      D-4751 │  0.3  0.21 │     0.85      │

│Size, mm., max.              │            │               │

│                             │            │               │

│Ultraviolet           D-4355 │   70    70 │      70       │

│Degradation @ 500            │            │               │

│hour exposure, %             │            │               │

│Strength Retained            │            │               │

│                             │            │               │

│Acceptance, Pass      D-4759 │ Pass   Pass│     Pass      │

│or Fail                      │            │               │

└─────────────────────────────┴────────────┴──────────────┴┘

NOTES:

1.	Separation geotextile supplied may have either less than, or greater than 50% elongation measured at breaking load in the Grab Tensile Test (ASTM D-4632).

2.	Geotextile Property Values = Minimum average roll values at a 95% confidence level in the weaker principal direction.

3.	0.21 mm. = US Standard Sieve Size 70.

4.	0.3 mm. = US Standard Sieve Size 50.

5.	0.85 mm. = US Standard Sieve Size 20.

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04  Sign Post.  Under Item 1., Metal Pipe Posts, add the following to paragraph a:  Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the plans with 3/16 inch thick walls.  7/16 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural  tubing and W shape beams shall be hot dip galvanized in accordance with 1.b of this subsection.  Damaged and abraded tubes and beams shall be repaired in accordance with 1.c of this subsection.

(9/1/89)

APPENDIX A

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS