SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available from the Department of Transportation and Public Facilities located at 4111 Aviation Avenue in Anchorage.  Information may be obtained as follows:

1.	Copies for review and reproduction information are available in the Plans Room, (907) 266-1674 for the following:

- Computations

- Cross Sections

2.	The following reports are available in the Plans Room, (907) 266-1674, upon request:

-	"Glenn Highway Erosion Control, Mile Post 61 to 78, Hydraulics Report, April 15, 1991".

-	"Glenn Highway Erosion Control, Geotechnical Information".

3.	An environmental evaluation addressing concerns and environmental commitments is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 266-1737.

PART 4

STANDARD MODIFICATIONS AND SPECIAL PROVISIONS

to the

STATE OF ALASKA 1988 STANDARD SPECIFICATIONS

FOR HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.27  Holidays.   Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third Monday in January

3.	President's Day - Third Monday in February

(5/7/91)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  Qualification of Bidders.  Delete the second paragraph.  (5/12/89)

102-1.06 Preparation of Proposal.  Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

(5/7/91)

102-1.07   Non-Responsive Proposals.  Delete item 3 in its entirety and substitute the following:

3. 	If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to the bidder at any one bid letting, as provided in Subsection 102-1.06.  (5/7/91)

102-1.07  Non-Responsive Proposals.  Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)

102-1.12  Addenda Requirements.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  Consideration of Proposals.  Add the following:  The apparent low bidder shall, within 5 working days following the bid opening, submit either a list of all firms with which the prime contractor intends to execute subcontracts for the performance of the contract  or a  statement  that  the  bidder  intends  to

perform the work without subcontractors.  The list shall include the following information for each proposed subcontractor:

1.	name,

2.	business address,

3.	Alaska business license number,

4.	Contractor's registration number,

5.	work to be performed, and,

6.	approximate dollar amount of the work to be performed.

If the apparent low bidder fails to submit either a list of subcontractors or a statement that the bidder intends to perform the work without subcontractors, the apparent low bidder will be found not to be a responsible bidder and may be required to forfeit the bid security.  The Department will then consider the next lowest bidder for the award of the contract.

If the apparent low bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess  of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this Subsection.

If a contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department, or,

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the contract with the bidder involving work for which the subcontractor was  listed,

7.	must be replaced in order for the prime contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or,

9.	is determined by the Contracting Officer not to be responsible.

(12/26/90)

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  Changes.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)

Special Provisions

104-1.02  Changes.  Delete the first three paragraphs and substitute the following:  The Engineer reserves the right to make, in writing, at any time during the work, such changes in quantities and such alterations in the work as are necessary to satisfactorily complete the project.  Such changes in quantities and alterations shall not invalidate the contract nor release the surety, and the Contractor agrees to perform the work as altered.

If the alterations or changes in quantities significantly change the character of the work under the contract, whether or not changed by any such different quantities or alterations, an adjustment, excluding loss of anticipated profits, will be made to the contract.  The basis for the adjustment shall be agreed upon prior to the performance of the work.  If a basis cannot be agreed upon, then an adjustment will be made either for or against the Contractor in such amount as the Engineer may determine to be fair and equitable.

If the alterations or changes in quantities do not significantly change the character of the work to be performed under the contract, the altered work will be paid for as provided elsewhere in the contract.

The term "significant change" shall be construed to apply only to the following circumstances:

1.	When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction, or

2.	When a major item of work, as defined elsewhere in the contract, is increased in excess of 125 percent or decreased below 75 percent of the original contract quantity.  Any allowance for an increase in quantity shall apply only to that portion in excess of 125 percent of original contract item quantity, or in case of a decrease below 75 percent, to the actual amount of work performed.

(4/13/89)

104-1.03  Differing Site Conditions.  Delete in its entirety and substitute the following:  During the progress of the work, if subsurface or latent physical conditions are encountered at the site differing materially from those indicated in the contract or if unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the work provided for in the contract, are encountered at the site, the party discovering such conditions shall promptly notify the other party in writing of the specific differing conditions before they are disturbed and before the affected work is performed.

Upon written notification, the Engineer will investigate the conditions, and if he determines that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any work under the contract, an adjustment, excluding loss of anticipated profits, will be made and the contract modified in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment which results in a benefit to the Contractor will be allowed unless the Contractor has provided the required written notice.

(4/13/89)

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  Authority of the Engineer.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)

Special Provisions

105-1.06  Cooperation With Utilities.  Add the following:  The Contractor shall request locates from all the Utilities having facilities in the area.  Their telephone numbers are as follows:

DOT/PF Maintenance & Operations		745-2159

Matanuska Electric Association, Inc.	745-3231

Matanuska Telephone Association, Inc.	745-3121

There are various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project if necessary.

The Contractor is required to work around all utility facilities, throughout the project unless advised by the utility that the facility is abandoned in place.

If an electrical cable is damaged and requires splicing, it will be repaired by the Utility with the party causing the damage paying the repair costs.	If the cable is damaged a second time, the cable will be replaced between junction points.  The party causing the damage will pay for replacing the cable.

Standard Modifications

105-1.12  Load Restrictions.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless otherwise allowed by an approved Traffic Control Plan.  (5/7/91)

Special Provisions

105-1.15  Project Completion.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work scheduled under Subsection 618-3.04, Maintenance of Seeded Areas, a letter of project completion will be issued by the Engineer.

105-1.17  Claims for Adjustment and Disputes.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (2/1/91)

Add the following:  Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/29/87)

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  Source of Supply and Quality Requirements.  Add the following:  All steel products which are to be incorporated into the work shall be produced in the United States except that minor amounts of steel products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel products into the project.  (11/9/84)

106-1.02  Local Material Sources.  General.  Add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)

Add the following:  Prior to placing or removing any material in/from a location other than that designated below, that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement will be given to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)

Add the following to Item 3., Designated Sources:  The following material site is available for use in obtaining Riprap on this project.

M.S. 42-2-001-1	King Mountain Area Quarry Site      located between Sta 1471+00 and Sta 1493+50, Glenn Highway

This material site is located within the highway right-of-way, which is 150 feet left of centerline.  The site is 2200 feet long, with a total area of approximately 5.1 acres.

The following guidelines pertain to the development and use of this site for Riprap materials extraction for the subject project.  All work necessary to develop and operate this site for the production of riprap;  including, the removal and disposal of timber, overburden, reject materials;  providing site facilities; protecting and restoring adjacent property; and site rehabilitation, will not be paid for directly but will be subsidiary to the Riprap pay items.

a.	DEVELOPMENT OF SITE.  Contractor shall develop the site to eliminate or minimize unauthorized uses, including dumping of waste, discharge of firearms, and unauthorized removal of materials.  Prior to use of the site, the Contractor shall submit a mining plan containing the following:

1)  A sketch map showing the site boundaries, the working boundaries, development stages, proposed access, temporary and final stockpile locations, location of site facilities, and approximate contours before and after excavation including site drainage measures.  Section and profile drawings should be used as appropriate.

2)  An accompanying narrative describing methods of operation, length and times of operation (day, month, year and working hours), and rehabilitation measures.

b.	PROTECTION AND RESTORATION OF ADJACENT PROPERTY.  Property located outside the highway right-of-way along this segment of road is designated a "scenic corridor".  No access to this property will be allowed for any purpose.

The Contractor shall conduct his operations to minimize damage to the roadway adjacent to the blasting area.  Any damage done to the roadway shall be restored by the Contractor, at his own expense, to a condition similar or equal to that existing before such damage occurred.

c.	TIMBER.  All trees, snags, and other woody material cut in connection with clearing of overburden shall be removed from the site and disposed.

d.	OVERBURDEN.  Overburden shall be cleared only to the extent necessary to provide specific project quantities and stripped overburden shall be removed from the site and disposed.

e.	REJECT MATERIALS.  Material not meeting the requirements of Riprap Type II or Type III shall be removed from the site and disposed, unless specifically allowed by the Engineer to remain in a stockpile at the site.

f.	SLOPES.  The site shall be excavated leaving cut slopes no steeper than 1/4 horizontal to 1 vertical.

g.	SITE FACILITIES.

1)  The Contractor shall provide portable sanitation facilities.  The Contractor may also install a trailer or mobile home for an office or night watchman's use.  If a trailer or mobile home is provided, provisions must be made for sanitary waste and garbage disposal.  If the Contractor constructs any camp on the land, such location shall be indicated on the mining plan and approved by the Engineer, and the Engineer shall have authority to require that said camp be kept in a neat and sanitary condition.  The Contractor may leave equipment on the site until completion of project utilization with the understanding that the Department does not accept any responsibility for theft or damage.

2)  No garbage or trash generated during site use shall be buried or disposed of within the site.

3)  Petroleum product storage tanks shall be surrounded by berms of sufficient volume to contain 150 percent of the total volume of the tank and have an impervious liner within the berm and under the tank.  Measures shall be taken during equipment servicing to prevent any petroleum products from spilling on the ground.  Said storage tanks and liner shall be removed and the containment berm shall be graded to conform with the site floor upon completion of the project.

4)  No construction materials shall be stored on the site unless directly associated with the site operation or production of riprap on this project.

h.	EMISSIONS.  Emissions from motors, equipment, and installations shall meet the air quality standards of the United States Public Health Service and the State of Alaska.

i.	EXPLOSIVES.  No blasting material, blasting caps, and related materials may be stored on site.  Personnel engaged in blasting activities shall be licensed by the State for these purposes and shall observe all applicable laws and regulations.  Storage and handling of explosives shall be in accordance with Subsection 107-1.10, Use of Explosives.

j.	HAZARDS.  The site shall be operated in a manner that is not hazardous to humans or to wildlife.

k.	USE OF MATERIALS.  Controlled blasting techniques, as described herein, shall be used for forming the rock cut slopes.  Controlled blasting refers to the controlled use of explosives and blasting accessories in carefully spaced and aligned drill holes to produce a free surface or shear plane in the rock along the specified excavation backslope.  The controlled blasting technique covered by this specification is presplitting (preshearing), and is used to minimize damage to the rock backslope to help insure long-term stability.

1)  General Requirements.  The Engineer shall, at all times, have the authority to prohibit or halt the Contractor's blasting operations if it is apparent that through the methods being employed, the required results are not being obtained or the safety and convenience of the travelling public is being jeopardized.

Blasting shall be limited to daylight hours.

The Contractor shall observe the entire blast area for 20 minutes following a blast to guard against rock fall before commencing work in the cut.

All rock on the cut face that is loose, hanging, or which creates a potentially dangerous situation shall be removed or stabilized, to the Engineer's satisfaction, during or upon completion of the excavation in each lift.  Drilling of the next lift will not be allowed until this work has been completed.

If in-place stabilization is required, as determined by the Engineer, rock bolting or other Engineer approved stabilization techniques shall be used.  Stabilization necessitated, in the opinion of the Engineer, by the rock geology, will be paid for at the appropriate unit price or by force account in accordance with subsection 109-1.05.  Stabilization necessitated, in the opinion of the Engineer, by the Contractor's blasting operations, shall be performed at the Contractor's expense.

2)  Blasting Plan Submittal.  Two weeks prior to any drilling or blasting, the Contractor shall submit a blasting plan to the Engineer for review.  The blasting plan shall contain the full details of the drilling and blasting, controls the Contractor proposes to use for the controlled and production blasting, and traffic control through the blasting area.  The blasting plan shall contain the following minimum information:

- Station limits of proposed shot.

- Plan and section views of proposed drill pattern including free face, burden, blasthole spacing, blasthole diameters, and blasthole angles.

- Loading diagram showing type and amount of explosives, primers, initiators and location and depth of stemming.

- Initiation sequence of blastholes including delay times and delay system.

- Time of day and day of week for proposed shot.

- Road closure Traffic Control Plan.

The blasting plan submittal is for quality control and record keeping purposes.  Review of the blast plan by the Engineer will not relieve the Contractor of his responsibility for the accuracy and adequacy of the plan when implemented in the field.

3)  Presplitting.	All presplitting shall be performed in accordance with the following requirements:

The presplit drill holes shall be not less that 2.5 inches and not more the 3 inches in diameter.

The Contractor shall control his drilling operations by the use of proper equipment and technique to insure that no hole shall deviate from the plane of the planned slope by more than 9 inches either parallel or normal to the slope.

Before placing charges, the contractor shall determine that the hole is free of obstructions for its entire depth.  All necessary precautions shall be exercised so that the placing of the charges will not cause caving of material from the walls of the holes.

Drill hole conditions may vary from dry to filled with water.  The Contractor will be required to use whatever type(s) of explosives and/or blasting accessories necessary to accomplish the specified results.

Bulk ammonium nitrate and fuel oil (ANFO) shall not be allowed to be loaded in the presplit holes.

Only standard explosives manufactured especially for presplitting shall be used in presplit holes, unless otherwise approved by the Engineer.

Continuous column cartridge type of explosives used with detonating cord shall be assembled and affixed to the detonating cord in accordance with the explosive manufacturer's instructions, a copy of which shall be furnished to the Engineer.

The upper portion of all presplit holes, from the top most charge to the hole collar, shall be stemmed.  Stemming materials, shall be sand or other dry angular granular material, all of which passes a 3/8-inch sieve.

As long as equally satisfactory presplit slopes are obtained, the Contractor, at his option, may either presplit the slope face before drilling for production blasting or may presplit the slope face and production blast at the same time, provided that the presplitting drill holes are fired first.  If required to reduce  ground  vibrations or noise, presplit holes may be delayed, providing the hole to hole delay is no more than 25 milliseconds.

4)  Production Blasting.  All production blasting shall be preformed in accordance with the following general requirements:

A line of buffer holes shall be drilled on a parallel plane adjacent to the presplit holes.  Buffer hole diameters shall be between 2.5 and 3 inches.  The line of buffer holes shall be drilled approximately 3 feet out from the presplit line and spaced 3 to 5 feet center to center.  The explosive loads in these holes shall not exceed fifty percent of the average explosive load that could be placed in the nearest production holes.  Detonation of the buffer holes shall be on a delay sequence toward a free face and shall follow detonation of the production holes.

Production blast holes shall not be drilled closer than 6 feet to the controlled blast line, unless approved by the Engineer.  Production holes shall not exceed 6 inches in diameter, unless approved by the Engineer.  Detonation of production holes shall be on a delay sequence toward a free face.

It is the Contractor's responsibility to take all necessary precautions in the production blasting so as to minimize blast damage to the rock backslope.

5)  Flyrock Control.  Before the firing of any blast in areas where flying rock may result in personal injury or unacceptable damage to property or the work, the rock to be blasted shall be covered with approved blasting mats, soil, or other equally serviceable material, to prevent flyrock.

6)  Horizontal Drain Holes.  Drain holes to relieve water conditions in rock backslopes may be required.  If needed, they shall be 3 inches in diameter and lengths shall not exceed 40 feet.  Location and slope of horizontal drains will depend on conditions encountered but will not exceed the limits of the equipment in use on the project for presplitting or production holes.  Holes shall be flushed with water upon completion to remove drill fines.

l.	REHABILITATION.  Upon completion of the site excavation and prior to vacating the site, the Contractor shall smooth out the pit floor to conform to the surrounding topography.  Measures shall be taken to ensure adequate site draining.  A final pit inspection will be done by the Engineer after completion of operations and prior to the removal of equipment to ensure compliance with the appropriate stipulations.  The Engineer shall be notified by the Contractor at least 21 days prior to the scheduled removal of rehabilitation equipment from the site in order that an inspection can be performed.

m.	SITE CLEAN-UP.  All site clean-up shall be performed and all Contractor's equipment shall be removed from the site within 30 calendar days following the completion of Riprap removal from this site.

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01  Laws to be Observed.  Add the following:  Specific Equal Employment Opportunity Responsibilities of Federal-Aid Construction Contractors.

1.	General

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form 25D-55) and these Special Provisions which are imposed pursuant to Section 140 of Title 23, U.S.C., as established by Section 22 of the Federal-Aid Highway Act of 1968.  The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the equal employment opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State highway agencies and the Federal Government in carrying out equal employment opportunity obligations and in their review of his/her activities under the contract.

c.	The Contractor and all his/her subcontractors holding subcontracts not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of equal employment opportunity:  (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as Contractors and subcontractors.)  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.

2.	Equal Employment Opportunity Policy

The Contractor will accept as his operating policy the following statement which is designed to further the provision of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include:  employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprentice-ship and/or on-the-job training.

3.	Equal Employment Opportunity Officer

The Contractor will designate and make known to the Engineer an equal employment opportunity officer (hereinafter referred to as the EEO Officer) who will have the responsibility for and must be capable of effectively administering and promoting an active Contractor program of equal employment opportunity and who must be assigned adequate authority and responsibility to do so.

4.	Dissemination of Policy

a.	All members of the Contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the Contractor's equal employment opportunity policy and contractual responsibilities to provide equal employment opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

(1)	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the Contractor's equal employment opportunity policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor's equal employment opportunity obligations within thirty days following their reporting for duty with the Contractor.

(3)	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the Contractor's procedures for locating and hiring minority group employees.

b.	In order to make the Contractor's equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

(1)	Notices and posters setting forth the Contractor's equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The Contractor's equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

5.	Recruitment

a.	When advertising for employees, the Contractor will include in all advertisements for employees the notation:  "An Equal Opportunity Employer."  All such advertisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority group applicants, including, but not limited to, State employment agencies, schools, colleges and minority group organizations.  To meet this requirement, the Contractor will, through his EEO Officer, identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority group applicants may be referred to the Contractor for employment consideration.

In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor's compliance with equal employment opportunity contract provisions.  (The U.S. Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or women, or obligates the Contractor to do the same, such implementation violates Executive Order 11246, as amended.)

c.	The Contractor will encourage his present employees to refer minority group applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures with regard to referring minority group applicants will be discussed with employees.

6.	Personnel Actions

Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The Contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The Contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with his obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the Contractor will inform every complainant of all of his avenues of appeal.

7.	Training and Promotion

a.	The Contractor will assist in locating, qualifying, and increasing the skills of minority group and women employees, and applicants for employment.

b.	Consistent with the Contractor's work force requirements and as permissible under Federal and State regulations, the Contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.  In the event the Training Special Provision is provided under this contract, this subparagraph will be superseded as indicated.

c.	The Contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.	The Contractor will periodically review the training and promotion potential of minority group and women employees and will encourage eligible employees to apply for such training and promotion.

8.	Unions

If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and female employees.  Actions by the Contractor either directly or through a contractor's association acting as agent will include the procedures set forth below:

a.	The Contractor will use best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

b.	The Contractor will use best efforts to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The Contractor is to obtain information as to the referral practices and policies of the labor union except that the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the Contractor, the Contractor shall so certify to the State highway department and shall set forth what efforts have been made to obtain such information.

d.	In the event the union is unable to provide the Contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the Contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minority group persons and women.  (The U.S. Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees.)  In the event the union referral practice prevents the Contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such Contractor shall immediately notify the State highway agency.

9.	Subcontracting

a.	The Contractor will use his best efforts to solicit bids from and to utilize minority group subcontractors or subcontractors with meaningful minority group and female representation among their employees.  Contractors shall obtain lists of minority-owned construction firms from State highway agency personnel.

b.	The Contractor will use his best efforts to ensure subcontractor compliance with their equal employment opportunity obligations.

10.	Records and Reports

a.	The Contractor will keep such records as are necessary to determine compliance with the Contractor's equal employment opportunity obligations.  The records kept by the Contractor will be designed to indicate:

(1)	the number of minority and nonminority group members and women employed in each work classification on the project,

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to Contractors who rely in whole or in part on unions as a source of their work force),

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority group subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such records must be retained for a period of three years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the State highway agency and the Federal Highway Administration.

c.	The Contractors will submit an annual report to the State highway agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form PR 1391.  If on-the-job training is being required by "Training Special Provision", the Contractor will be required to furnish State of Alaska Form 25A312.

(4/8/83)

107-1.11  Protection and Restoration of Property and Landscape.  Add the following after the third paragraph:  The Contractor shall report immediately to the Engineer any hazardous material discovered, exposed, or released into the air, ground or water during construction of the project.  The Contractor shall also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery.  Hazardous materials include, but are not limited to, petroleum products, oils, solvents, paints and chemicals that are toxic, corrosive, explosive or flammable.  (5/7/91)

The Contractor shall not excavate, nor use for fill, any material containing hazardous substances or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected of containing hazardous substances or petroleum fuels.

Add the following after Item 10.:

11. 	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2253.

Add the following:  The Contractor shall not use land from any  park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.

The Contractor shall do no work, trespass, stockpiling, staging, or parking in or around any watercourse except for that work permitted in the Matanuska River that is specified by the Contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

(8/1/90)

Standard Modifications

107-1.13  Responsibility for Damage Claims.  In the

first sentence, change "claims or actions for injuries"

to read "claims, actions or liabilities for injuries". (5/12/89)

Special Provisions

107-1.15 Contractor's Responsibility for Work.  Add the following to the end of the first paragraph:  Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense.  (5/7/91)

Standard Modifications

107-1.16  Contractor's Responsibility For Utility Property And Services.  In the last sentence of the third paragraph delete: "by the local fire authority."  (5/12/89)

Special Provisions

107-1.16   Contractor's Responsibility for Utility Property and Service.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mislocates the facility in the field by more than 2.5-feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.

(9/1/89)

107-1.21  Permits.  Add the following Subsection:  The following permits and authorizations have been received on the Contractor's behalf by the Department:

1.	Department of Fish and Game Title 16 Permit No. FG 91-II-0422, dated August 1, 1991.

2.	Department of the Army, Corps of Engineers, Nationwide Permit No. 23, dated December 12, 1990.

The permits obtained by the Department are attached to these specifications as Appendix A.  The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor's responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer.  The Engineer will then decide if a permit modification is necessary.  The Engineer will have copies of the permits posted in the project office.

(9/1/89)

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  Subletting of Contract.  Add the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Driver's License.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	the owner-operator's right to control the manner in which the work is to be performed,

2. 	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3. 	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4. 	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each owner-operator.  The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.

(5/7/91)

108-1.03  Prosecution and Progress.  In the first paragraph, delete the words "At this time" and substitute:  "Five working days before the preconstruction conference".  (5/7/91)

Standard Modifications

108-1.03  Prosecution and Progress.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule". (5/12/89)

Special Provisions

108-1.03  Prosecution and Progress.   Add the following:  The Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail work activities, manpower involved by trade, work hours, equipment involved and the location of the work to be performed.

Preparation of the two week work plans will not be paid for directly, but will be subsidiary to Item 640(1) Mobilization and Demobilization (6/13/90)

108-1.05   Character of Workmen, Methods and Equipment.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer. (9/1/89)

108-1.06  Determination and Extension of Contract Time.  Add the following:

4.	Suspensions of Work Ordered by the Engineer.  If the performance of all or any portion of the work is suspended or delayed by the Engineer in writing for an unreasonable period of time (not originally anticipated, customary, or inherent to the construction industry) and the Contractor believes that additional compensation and/or contract time is due as a result of such suspension or delay, the Contractor shall submit to the Engineer in writing, a request for adjustment within 7 calendar days of receipt of the notice to resume work.  The request shall set forth the reasons and support for such adjustment.

Upon receipt, the Engineer will evaluate the Contractor's request.  If the Engineer agrees that the cost and/or time required for the performance of the contract has increased as a result of such suspension and the suspension was caused by conditions beyond the control of and not the fault of the Contractor, its suppliers, or subcontractors at any approved tier, and not caused by weather, the Engineer will make an adjustment (excluding profit) and modify the contract in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment will be allowed unless the Contractor has submitted the request for adjustment within the time prescribed.

No contract adjustment will be allowed under this clause to the extent that performance would have been suspended or delayed by any other cause, or for which an adjustment is provided for or excluded under any other term or condition of this contract.  (4/13/89)

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  General.  Add the following:  When more than one variety of material or work item is specified for a single pay item number, letter or numeric suffixes will be included within the parenthesis to differentiate the types.  (9/1/89)

Standard Modifications

109-1.03 Scope of Payment.  Delete the last sentence of the fourth paragraph.  (5/7/91)

Special Provisions

109-1.04  Compensation for Altered Quantities.  In the third indented subparagraph, delete the following: ", except that the total payment for the item shall not exceed 75 percent of the total amount bid for the item".  (4/13/89)

109-1.05  Compensation for Extra Work.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)

109-1.07  Payment  For Materials on Hand.   Add the following:  Stockpiled materials for payment in storage facilities off the project shall be in a location acceptable to the Engineer. (12/26/90)

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  Description.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49,  Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  Interpretation.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  Essential Contract Provision.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  Definitions and Terms.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03.3 for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  Utilization Goal.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Utilization Goal in order to be eligible for award of this contract.

120-3.01  Determination of Compliance.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  Good Faith Effort.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE Credit.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least one of which must be working on this project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  Default of DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02 Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, ALL of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02 Good Faith Effort.

120-4.01  Method of Measurement.  The Contractor shall be entitled to count toward the DBE Utilization Goal those monies allowed by the Engineer in 120-3.03.04 as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE

firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization Goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under 120-5.01.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100%.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60% of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  Basis of Payment.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01 until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per Subsection 120-3.03, 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

Payment or Deduction will be made under:

Pay Item No.        Pay Item         Pay Unit

120(1)        DBE Adjustment   Contingent Sum

(5/5/89)

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-2.04  Removal of Pavement, Sidewalks, Curbs, Etc.  Add the following:  For disposal of removed asphalt concrete, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529, extension 246.

SECTION 203

EXCAVATION AND EMBANKMENT

Standard Modifications

203-2.05  Borrow.  Add the following:  Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.  (5/12/89)

Special Provisions

203-3.01  General Construction Requirements.  Add the following to the fifth paragraph:  Existing pavement shall be removed and disposed of in accordance with subsection 202-2.04, Removal of Pavement, Sidewalks, Curbs, Etc., prior to obliteration of the underlying roadway.

Standard Modifications

203-3.02 Embankment Construction.  On page 97, delete the 5th paragraph and substitute the following:  All embankments shall be constructed with moisture and density control unless the Engineer determines that such controls are not feasible, in accordance with approved methods.  (5/7/91)

Special Provisions

203-4.01  Method of Measurement.  Add the following:  No deduction from the excavation quantities will be made for pavement removed under Item 202(2), Removal of Pavement.

Standard Modifications

203-5.01  Basis of Payment.  Change Pay items 203(5), (6) and (7) to read:  Borrow, Type _____.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01  Materials.  Delete the last two sentences of the first paragraph and substitute the following:  The gradation of base course material for use under asphalt concrete pavement shall be Type D-1.  The gradation of base course material for use as a surface course for the unpaved portions of the roadway shoulders shall be Type E-1.

301-5.01  Basis of Payment.  Add the following:  Payment for base course material will be made under Item 301(1), Crushed Aggregate Base Course, regardless of the gradation type used.

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provision

401-2.01  Composition of Mixtures.  Add the following to the first paragraph after the first sentence:  The Contractor shall submit, in writing, the proposed ratios at which he plans to blend the various aggregate stockpiles in order to achieve the target gradation submitted.

Add the following to the tolerance table of the fourth paragraph:

Sieve Size          Tolerance

1/2 inch               + 7

No. 80                 + 4

Add the following after the tolerance table of the fourth paragraph:  The asphalt cement and aggregate submitted by the Contractor for Asphalt Concrete, Type II, Job Mix Design approval as tested according to Alaska T-17 shall conform to the following.  The asphalt content of the mix will be expressed as a percentage of the total mix.

Marshall Stability, pounds, minimum		1200

Voids, Total Mix %						3-5

Flow Value							8-16

Compaction Blows per Side				50

Voids in Mineral Aggregate, %, min.          14.0

Dust-asphalt ratio (1)					0.6-1.2

(1)	Dust-asphalt ratio is defined as the percent of material passing the No. 200 sieve divided by the percent of asphalt (calculated by weight of mix).

The Voids in mineral aggregate is calculated by the following formula:

GmbPs

Voids in mineral aggregate = 100 - (____)

Gsb

Where:

Gsb = bulk specific gravity of aggregate

Gmb = bulk specific gravity of compacted

mixture (ATM T-18), and

Ps = aggregate, percent by total weight of

mixture

The Contractor should be cautioned that addition of crushed fines may be required to meet the Voids in Mineral Aggregate requirement.

The Alaska Test Method T-17 section E.4.a shall be deleted and the following should be substituted:

a.	From the data curves, asphalt contents are determined which yield the following:

1.  Maximum Unit Weight

2.  Maximum Stability

3.  Voids Total Mix at 4 percent

401-2.04  Asphalt Materials.  Add the following:  AC-5 asphalt cement will be used for the Asphalt Concrete, Type II pavement mix.

401-3.01 Weather Limitations.  Delete in its entirety and substitute the following:  The asphalt mixture shall not be placed on a wet surface, on a surface of which the temperature is less than that determined from the following table for the appropriate mat thickness, or when other conditions would prevent the proper handling or finishing of the mixture.

SURFACE TEMPERATURE LIMITATIONS

| Mat Thickness | Surface Temperature Degrees F, min. |
| --- | --- |
| 3 inches or greater | 40 |
| between 1 and 3 inches | 45 |
| 1 inch or less | 50 |

(5/7/91)

401-3.11  Spreading and Finishing.  Add the following to the third paragraph:  Asphalt concrete pavement shall be spread and compacted in one layer. Paving shall be continuous, where possible, to keep the number of transverse joints to a minimum.

401-3.12  Compaction.  Delete this subsection in its  entirety and substitute the following:  Compaction by Coverage.  Initial rolling shall be done with a steelwheeled tandem roller and/or a suitable pneumatic tired roller.  Initial rolling shall be completed while the mat temperature is above 225 degrees F.

Following the initial rolling, at least three coverages of the pavement shall be completed with a pneumatic tired roller.  Final rolling shall be completed with a 10 ton minimum weight steelwheeled tandem roller and shall continue until roller marks and further compacting are not evident in the pavement and the finished surface conforms to Section 401-3.15, Surface Tolerances.  All rolling shall be completed while the mat temperature is above 180 degrees F.

401-4.01 Method of Measurement.  Delete this subsection in its entirety and substitute the following:  Asphalt concrete will be measured by the ton in accordance with Section 109, Measurement and Payment.  Asphalt cement and anti-stripping additive will not be measured for payment.

401-4.02  Contract Price Adjustments.  Delete this subsection in its entirety and substitute the following:  Work accomplished under this item shall be accepted for payment based on the Engineer's approval of a Job Mix design, and the placement and consolidation of the pavement to both the specified depth, and the finished surfacing requirements and tolerances.

Any area of finished surfacing that is segregated, fails to meet the surface tolerance requirements, cools below 180 degrees prior to completing compaction, or is in any other way defective shall be removed and replaced with fresh hot mix.  Removal and replacement of defective pavement shall be at no additional cost to the Department.

401-5.01  Basis of Payment.  Add the following to the second paragraph:  Asphalt cement and anti-stripping additive will not be paid for directly but will be subsidiary to Item 401(9), Asphalt Concrete, Type II.

Add the following pay item:

Pay Item No.               Pay Item              Pay Unit

401(9)         Asphalt Concrete, Type II        Ton

SECTION 606

GUARDRAIL

Special Provisions

606-1.01  Description.  Add the following:  This work shall also consist of installing breakaway cable terminals at the locations shown on the plans.

606-3.01 Posts.  Add the following:  The foundation type for the Breakaway Cable Terminal Posts shall be the "steel post embedment-soil or concrete" option as shown on Standard Drawing G-18.

606-3.02  Rail Elements.  Add the following:  Guardrail elements shall be factory bent for all radii less than 75-feet.

606-3.08  Length of Need Verification.  Add the following subsection:  After shaping the slopes and staking all proposed guardrail locations, the Contractor shall notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine that additional guardrail is necessary, and the Contractor shall comply without delay.  (3/17/86)

606-4.01  Method of Measurement.  Delete the third paragraph and replace with the following:  Breakaway Cable Terminals shall be measured per each installation which shall include anchor cable assembly, terminal posts, terminal end, and all associated hardware.  Rail elements, standard posts, and blocking for breakaway cable terminals shall be measured as Beam Type Guardrail.

606-5.01  Basis of Payment.  Add the following pay items:

Pay Item No.            Pay Item            Pay Unit

606(8)       Breakaway Cable Terminal      Each

(9/1/89)

SECTION 618

SEEDING

Special Provisions

618-1.01   Description.  Delete this subsection and substitute the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded.  This work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01  Materials.  Add the following to the list of material specifications:

Mulch                       Section 727-2.01

618-3.01  Soil Preparation.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be covered with topsoil in accordance with Section 620, and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as topsoil is placed on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach onto the wetlands.  The performance of this work is subsidiary to seeding and will not be paid for directly.

618-3.03  Application.  In the first sentence of subparagraph b., under numbered paragraph 1., Hydraulic Method, delete the following:  "Item 619(1),".

Add the following:  Seed, mulch and fertilizer shall be applied as shown in the following table per 1,000 square feet.  If the hydraulic method for seed and mulch is used, it shall be made in one application.  The mulch rate shown is a minimum, and may be increased in accordance with the manufacturers recommendations.  All fertilizer shall be applied by the hydraulic method.

Application

Item              Ingredients           Rate Lbs/MSF

Rural Seed     Bering Hairgrass (Norcoast)    0.60 lb.

Mix            Red Fescue (Arctared)          0.30 lb.

Annual Ryegrass (Lolium)       0.10 lb.

Alsike or Dutch White Clover   0.05 lb.

Baby Blue Eyes (Nemophila

Menzeisii)                0.05 lb.

Sun Flower (Helianthus Annus)  0.05 lb.

Ox Eye Daisy (Chrysanthemum

Leucanthemum)             0.03 lb.

Iceland Poppy (Papaver

Nudicaule)                0.03 lb.

TOTAL =    1.21 lbs/MSF

Mulch                                         35.0 lbs.

Fertilizer     20-20-10                       12.0 lbs.

The Contractor shall not remove the required tags from the seed bags.

618-4.01  Method of Measurement.  Delete the second paragraph and substitute the following:  Seeding by the pound will be the number of pounds of seed (dry measure) accepted in place.  The amount of mulch and fertilizer used in this work, including any required reseeding, will be subsidiary to seeding and will not be measured separately for payment.

618-5.01  Basis of Payment.  Add the following:   Fertilizer, and mulch, as described above, will not be paid for directly, but will be subsidiary to Item 618(2) Seeding.

(6/1/90)

SECTION 620

TOPSOIL

Special Provisions

620-2.01  Materials.  Add the following:  Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

620-5.01  Basis of Payment.  Add the following:  Addition of limestone, if required, will be subsidiary to Item 620(1) Topsoil.

(6/1/90)

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-2.01  Method of Measurement.  Delete item 3. and substitute the following:

3.	When the letter of project completion has been issued and the Contractor has made all the required submittals the remaining balance of the amount for this item will be paid.  (5/7/91)

640-3.01  Basis of Payment.  Add the following:  Preparation of the two week work plans in accordance with Section 108, will not be paid for directly, but will be subsidiary to Item 640(1) Mobilization and Demobilization.

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01  Description.  Add the following:  Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of Subsection 107-1.11, Protection and Restoration of Property and Landscape.  Additional silt fencing may be required at any upland site as directed by the Engineer.

641-1.03  Materials.  Add the following subsection:  The silt fence filtration material shall meet the requirements shown in Table 729-4 in Section 729, Geotextiles.

The silt fence support framework shall be finished 4 x 4-inch wood, 3-inch diameter wood, #6 rebar with PVC sleeves, iron pipe or other posts capable of supporting the installation, as approved by the Engineer.

The mesh support shall be WWF 6x6 W1xW1 or as approved by the Engineer.

641-2.01 Construction Requirements.  Add the following:  The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water.  The temporary erosion and pollution control plan shall address the measures the Contractor shall implement in the containment, cleanup, and disposal of such substances as well as the methods to be utilized for disposing of waste oil or other hazardous substances generated by construction equipment or activities.  The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.  The plan shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

The Contractor shall immediately notify the Engineer of any construction related discharge of oil and/or other substances hazardous to the land or water.  Should any suspected hazardous substance be discovered during construction, work which would disturb the substance shall stop and the Engineer immediately notified.

The silt fence shall be installed as detailed on the plans.  Upon completion of work in the waterbody, the area behind the fence shall be allowed to settle the suspended material for a minimum of two (2) days before the silt fence is removed.

The silt fence shall not be removed until adequate vegetative growth insures no further erosion of the slopes.  The silt fence designated for removal on the plans shall be removed and disposed of off the project upon completion of construction at those sites.  The fabric shall be cut off at ground level and the wire and posts shall be removed.  The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands.  If a sediment height in excess of four inches above ground remains, the sediment shall be spread on the roadway side of the fence location and seeded immediately in accordance with Section 618, Seeding.

641-2.02  Best Management Practices.  Add the following subsection:  Erosion and sediment control measures are more easily accomplished if construction operations are properly scheduled.  Operations should be planned, when possible, for that time of year when potential for erosion is low.

There are a number of factors to consider and operations to schedule in the development of an acceptable temporary erosion and pollution control plan.  These include, but are not necessarily limited to the following:

1.	Clearing by cutting, slashing and disposing of the trees and other debris.

2.	Installation of temporary erosion and sediment control measures on the downhill side of the construction work area before building the embankment or excavating a slope.

3.	Construction of temporary drainage ditches to convey off-site drainage through the work area and diversion of the flow before excavating for the permanent drainage structure.

4.	Installation of all erosion and sediment control measures at the toe of embankment and excavation operations.  Silt fences are a structural method for providing temporary erosion and sediment control.

5.	Construction of the embankment in horizontal lifts, providing protection from erosion by temporarily or permanently mulching and seeding the slopes in vertical increments, preferably of no more than 10-feet.  The top of the work area should be shaped and compacted so that surface water will run off without causing serious erosion should a storm occur.  At the end of each day's work or before a storm, berms and temporary downdrains must be constructed to control the release of on-site drainage.

6.	Excavation operations performed in the same manner as the embankment operation with the exception of slope drains and compaction.  This operation will release on-site drainage at a point where appropriate control measures have been installed.  The excavated slope must be finished as it is constructed and incrementally protected and seeded.

7.	Shaping and compacting the surface of the embankment surface or cut when the area reaches subgrade elevation.  Surface runoff should be controlled by berms and ditches and release through temporary pipes or ditches.  Detain sediment-laden runoff and trap sediment before releasing runoff from the construction area.

8.	Inspection and maintenance of each erosion and sediment control measure should be performed after each significant storm.  Silt fences should be inspected periodically for damage, such as tearing by wind, animals or equipment, and for the amount of sediment which has accumulated.  Removal of the sediment is generally necessary when it reaches half the height of the silt fence.  In situations where access is available, machinery can be used; otherwise it must be removed manually.  The key elements to remember are:

a.	The sediment deposits should be removed when heavy rain or high water is anticipated.

b.	The sediment removed should be placed in an area where there is little danger of erosion.

641-3.01  Method of Measurement.  Add the following:  Silt fence will be measured by the linear foot along the top of the fence.

641-4.01  Basis of Payment.  Add the following:  Payment for item 641(2), Silt Fence, will be full compensation for all labor, equipment and materials required to furnish, install, maintain and remove the silt fence in accordance with these specifications.

Payment will be made under:

Pay Item No.		Pay Item		Pay Unit

641(2)          Silt Fence     Linear Foot

(6/1/90)

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01   Description.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix B.

642-3.01  Construction Requirements.  Add the following to the third paragraph:  The Contractor shall perform all staking necessary for Material Site M.S. 42-2-001-1.

Add the following:

12.	The Contractor's survey crews shall comply with approved traffic control plans.  Crews shall coordinate their activities with the project's Worksite Traffic Supervisor.

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  Traffic Control Plan.  Add the following to the third paragraph:  All TCP's submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

643-1.04 Construction Phasing Plan.  Revise the first sentence to read as follows:  A Construction Phasing Plan shall be submitted at least five working days prior to the preconstruction conference for approval by the Engineer and shall consist of the following:  (5/7/91)

643-2.01  Materials.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8-feet.

643-3.02  Roadway Characteristics During Construction.  Delete the second paragraph in its entirety.  (5/7/91)

643-3.03  Public Notice.  Add the following:  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of 1 week in advance of commencing construction, resuming construction after seasonal suspension of work, or any scheduled delay, or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure.  Advertisements shall be published in the following newspapers:

1.	Anchorage Times,

2	Anchorage Daily News,

3	Frontiersman, and

4.	Valley Sun.

The Contractor shall indicate on the ad order a first preference for the local news section, and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a telephone number for the public to access a pre-recorded message with current roadway status.  Advertisements shall be promptly canceled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

643-3.04  Traffic Control Devices.  Under Item 1., Embankments, change the reference from "Annual Average Daily Traffic, (AADT)" to read "Average Daily Traffic (ADT).

643-3.08  Construction Sequencing.  Delete this subsection in its entirety and substitute the following:  Throughout the duration of the project, the existing roadway configuration shall be maintained i.e., the number of lanes and shoulders and their respective widths.  Approved Traffic Control Plans are required for any restrictions to traffic.

Road closures will be allowed from approximate Sta 1471+00 to Sta 1493+50 for blasting of rock at Material Site No. 42-2-001-1, and subsequent clean-up.  These road closures shall be limited to periods of three hours per day and shall be scheduled for no impact to passage of school buses and postal carriers.

Paved roadways to be reconstructed may be left unpaved during construction for a period not to exceed 14 calendar days.  They shall not be left unpaved during winter shutdown.

643-4.01  Method of Measurement.  Delete the second sentence of the first paragraph under Item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this contract.

643-5.01  Basis of Payment.  Add the following pay item:

Pay Item No.          Pay Item              Pay Unit

643(24)      Permanent Construction       Lump Sum

Signing

SECTION 644

SERVICES TO BE FURNISHED

BY THE CONTRACTOR

Special Provisions

644-2.01  Field Office.  Delete this subsection in its entirety and substitute the following:  The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work through 30 days after the Engineer issues a letter of project completion.  The following office requirements shall be met:

1.	A minimum of 500 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 350 square feet of floor space.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 6 vehicles.

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within five miles of the project.

644-2.08  Water Testing.  Add the following subsection:  Prior to initiating work around the Matanuska River, the Contractor will be required to retain an independent test laboratory to test water samples taken by the Engineer.  These samples shall be tested for quality, color, turbidity and suspended solids, in accordance with EPA standards, and the results shall be transmitted directly to the Engineer.

During construction, samples shall be tested at intervals as directed by the Engineer (ie: hourly,  daily or weekly) depending on the adjacent operation.  After completion of the work  final samples shall be tested.

644-3.01  Method of Measurement.  Add the following: Water testing will be reimbursed based on paid receipts for the authorized tests.

644-4.01  Basis of Payment.  Add the following: Payment for water testing will be made on the receipts for authorized tests plus 15 percent, and will be considered full compensation for all labor, equipment and materials required to have tests performed.

Payment will be made under:

Pay Item No.         Pay Item          Pay Unit

644(7)         Water Testing     Contingent Sum

(9/1/89)

SECTION 670

TRAFFIC MARKINGS

Standard Modifications

670-3.01  Construction Requirements.  In the last paragraph under Item 2., insert "pneumatic" immediately before "roller".  (5/12/89)

Special Provisions

670-3.05  Preliminary Spotting.  Add the following:  Lines and markings to be replaced at their existing locations shall be referenced by the Contractor, at his expense, prior to performing any work that may disturb them.

SECTION 702

ASPHALT MATERIALS

Standard Modifications

702-2.04  Storage And Application Temperatures.  In Table 702-1, change storage temperatures for ACs from "340 Max" to "325 Max".  (5/12/89)

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  Fine Aggregate for Concrete.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0 (5/12/89)

703-2.02  Coarse Aggregate for Concrete.  In the first sentence, insert ", class B," after "AASHTO M 80".  (5/12/89)

703-2.03 Aggregate for Base.  Add the following to the list under the first paragraph:

Plastic Index      AASHTO T-90        6 max

(5/7/91)

Special Provisions

Delete Table 703-2 Aggregate for Untreated Base, and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing by Weight

Sieve Designation		Grading D-1		Grading E-1

1 inch                100              100

3/4 inch               70-100           70-95

1/2 inch                ---             60-86

3/8 inch               50-79             ---

No. 4                 35-58            40-65

No. 8                 20-47             ---

No. 40                 8-23            15-30

No. 200                0-6              8-13

703-2.04  Aggregate for Plant Mix Asphalt Pavement.  In the second paragraph, after Fine Aggregate, delete the remainder of the sentence after "thereof" and add the following:  The fine aggregate will meet the following requirements:

Plastic Index       AASHTO T-90         4 max.

Sodium Sulfate      AASHTO T-104     15 percent max.

Soundness Loss

Modify Table 703-3, Asphalt Concrete Aggregate to read as follows:

Asphalt Concrete

Sieve Designation                   Type II

3/4-inch                           100

1/2-inch                          82-100

3/8-inch                          68-90

No. 4                            50-79

No. 10                           36-67

No. 40                           17-44

No. 80                            9-29

No. 200                           3-10

703-2.07  Selected Material.   Add the following to Item 1., Selected Material, Type A:  It shall have 30 to 55 percent by weight of particles passing the No. 4 sieve.  (9/1/89)

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.14  Preformed Pavement Markings.  Add the following to paragraph A. under Item 1., General Requirements:  The preformed ribbon shall consist of one solid piece of required width and length.  In solid stripe areas, the tape length shall, where possible, be a minimum of 100 feet.

SECTION 724

SEED

Special Provisions

724-2.02  Materials.  Add the following to Table 724-1:

| Seed Type | Germination Period | Percent Purity | Percent Germination | Percent Sproutable Seed |
| --- | --- | --- | --- | --- |
| Bering Hairgrass | 14 days | 95 | 75 | 71 |
| Baby Blue Eyes (Nemophila Menzeisii) | 14 days | 99 | 79 | 78 |
| Sun Flower (Helianthus Annus) | 21 days | 99 | 80 | 79 |
| Ox Eye Daisy (Chrysanthemum Leucanthemum) | 14 days | 96 | 88 | 84 |

SECTION 726

TOPSOIL

Standard Modifications

726-2.01  Topsoil.  In the second paragraph, change "not less than 1%" to read "not less than 3%".  (5/12/89)

SECTION 729

GEOTEXTILES

Special Provisions

729-2.04 Temporary Silt Fence.  Add the following subsection:  The geotextile supplied shall meet the physical and mechanical properties listed in Table 729-4.

Table 729-4

GEOTEXTILE REQUIREMENTS FOR TEMPORARY SILT FENCE

┌─────────────────┬────────────┬───────────────┬──────────────┐

│	Geotextile     │    Test    │     Fence     │     Self-    │

│  Property       │   Method   │   Supported   │   supported  │

│                 │   (ASTM)   │  Requirements │  Requirements│

├─────────────────┼────────────┼───────────────┼──────────────┤

│  Grab Tensile   │   D-4632   │       90      │      90      │

│  Strength,      │            │               │              │

│  lb., min.      │            │               │              │

│                 │            │               │              │

│  Elongation     │            │               │              │

│  at 50%         │            │               │              │

│  minimum        │   D-4632   │      N/A      │      50      │

│  Tensile        │            │               │              │

│  Strength,      │            │               │              │

│  (45 lb.),      │            │               │              │

│  % max.         │            │               │              │

│                 │            │               │              │

│  Water          │            │               │              │

│  Permittivity   │   D-4491   │      0.01     │     0.01     │

│  1/sec., min.   │            │               │              │

│                 │            │               │              │

│  Apparent       │            │               │              │

│  Opening Size,  │   D-4751   │      0.84     │     0.84     │

│  mm., max.      │            │               │              │

│                 │            │               │              │

│  Ultraviolet    │            │               │              │

│  Degradation @  │            │               │              │

│  500 hour       │   D-4355   │        70     │       70     │

│  exposure, %    │            │               │              │

│  Strength       │            │               │              │

│  Retained, min. │            │               │              │

│                 │            │               │              │

│  Geotextile     │            │               │              │

│  Acceptance,    │   D-4759   │       Pass    │      Pass    │

│  Pass or Fail   │            │               │              │

└─────────────────┴────────────┴───────────────┴──────────────┘

Notes:

1.	Geotextile Property Value = Minimum average roll values 95% confidence level in the weaker principal direction.

2.	0.85 mm. = U.S. Standard Sieve Size 20

APPENDIX A

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS