SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	Copies for review of the following are available in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Design Computations

b.	Cross Sections

Copies of the above documents may be obtained from Ridgways Reprographics, 6000 Arctic Boulevard, Anchorage, Alaska  99518, (907) 561-1555, at the Contractor's cost.

2.	The following reports are available upon request:

a.	Geotechnical Report, Unalaska Airport Beach Road,

b.	Storm Water Manual (Price $20.00), and

c.	Laboratory Manual of Alaska Test Methods and Standard Practices (Price $20.00).

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Traffic, Safety and Utilities Engineer, (907) 266-1531.

4.	An environmental document addressing concerns and environmental commitments has been approved and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 266-1508.

5.	This contract contains a newly-developed asphalt concrete pavement specification (Section 401).  Due to changes in materials testing procedures and requirements, the following new items are incorporated by reference in this specification.

a.	Alaska Test Method T-17, Rev. 06/93, Standard Method of Test for Determining Bituminous Mix Design by the Marshall Method.

Alaska Test Method T-17 is the mix design method and also includes criteria which must be met for the class of mix specified in the bid schedule.

b.	Alaska Standard Practice SP-9, Rev. 07/93, Standard Practice for Abbreviated Testing Procedures to Monitor Process Control of Coarse and Fine Aggregate Gradations.

Standard practice SP-9 contains test methods for contractor process control as well as a minimum testing frequency, and a list of typical field laboratory equipment to be furnished by the Contractor.

6.	Corrective Action Plan for Soil Excavated During the Unalaska Airport Beach Road Project, Unalaska, Alaska, prepared by Dowl Engineers, January 1994.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS FOR HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.27  HOLIDAYS.  Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third Monday in January

3.	President's Day - Third Monday in February

(5/7/91)M30

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  QUALIFICATION OF BIDDERS.  Delete the second paragraph.  (5/12/89)M1

102-1.06  PREPARATION OF PROPOSAL.  Replace the second paragraph with the following:  The bidder shall specify a unit price, in figures, for each pay item for which a quantity is given and shall also show the products of the respective unit prices and quantities written in figures in the column provided for that purpose and the total amount of the proposal obtained by adding the amounts of the several items.  All the figures shall be in ink or typed.  In the event of a discrepancy between unit bid prices and extensions, the unit bid price shall govern.  Any changes shall be initialed by the person signing the proposal.  (7/2/93)M58

Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply when the bidder has added the following statement to the Proposal Form for at least one of the projects being bid:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

102-1.07  NON-RESPONSIVE PROPOSALS.  Delete item 3. in its entirety and substitute the following:

3.	If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to the bidder at any one bid letting, as provided in Subsection 102-1.06, Preparation of Proposal.

(6/6/94)M31

Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)M2

102-1.12  ADDENDA REQUIREMENTS.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)M3

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  CONSIDERATION OF PROPOSALS.  Add the following:  The apparent low bidder shall submit a completed Subcontractor List, form 25D-5(C), within 5 working days following receipt of written notification by the Department.

If a bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess  of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this subsection.

If a contract is awarded to a bidder who violates this subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department, or,

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the contract with the bidder involving work for which the subcontractor was listed,

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or,

9.	is determined by the Contracting Officer not to be responsible.

(4/1/93)R82

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  CHANGES.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)M5

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  AUTHORITY OF THE ENGINEER.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02, Changes.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)M6

Special Provisions

105-1.02  PLANS AND WORKING DRAWINGS.  Replace the second sentence of the second paragraph with the following:  No work shall be performed until working drawings for such work, or changes thereto, are approved.

Replace the second sentence of the fourth paragraph with the following:  The Contractor shall indicate on the working drawings all deviations from the plans and specifications and shall also itemize and explain all deviations in the letter of transmittal.

(7/2/93)S62

105-1.06  COOPERATION WITH UTILITIES.  Add the following:  The Contractor shall request locates from all the Utilities having facilities in the area.  Their telephone numbers are as follows:

Unalaska, Director of Public Works (Power, Sewer, Water)	581-1260

Interior Telephone (Telephone, Television)		349-2400

DOT/PF Maintenance & Operations	581-1786

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

Prior to the relocation of the utility's facilities, construction staking may be required.  The Contractor shall give the Utility 2 weeks advance notice as to when the staking will be available and maintain the stakes until the utility relocation is completed.  Payment for this staking will be as follows:

1.	If, as part of the contract, the Contractor is required to provide staking in the area needed by the Utility, this work will be subsidiary to Item 642(1), Construction Surveying.

2.	If construction staking or right-of-way staking is required by the Utility in advance of the Contractor's normal schedule, the Utility will request the staking, through the Engineer, two (2) weeks prior to the time the staking is required for the Utility to start their relocation.  This staking will be paid under Item 642(2), Three Person Survey Party.

3.	If right-of-way staking is required by the Utility, and staking the right-of-way is not a part of the contract, the Utility will request the staking, through the Engineer, two (2) weeks prior to the time the staking is required for the Utility to start their relocation.  This staking will be paid under Item 642(2), Three Person Survey Party.

(4/21/94)R3

The following specific coordination requirements shall be met:

Interior Telephone Company (ITC).  Interior Telephone Company will perform the following work on their existing system located within the project limits.  The Contractor shall provide ITC with 15 days advance notice of when work will occur in each of the following areas.

| STATION | WORK DESCRIPTION | DURATION |
| --- | --- | --- |
| 24+20 to 33+40 24+20 to 33+50 27+73 27+75 33+40 to 44+15 33+50 109+00 to 112+50 139+94 142+80 to 154+15 148+60 148+66 154+15 | Install 400 and 600 pair telephone cables in conduit, 2-5 feet within R/W. Install ¾ and ½ inch television cables in conduit, 2-5 feet within R/W. Install buried telephone road crossing. Install buried television road crossing. Install 600 pair telephone cable in conduit, 2-5 feet within R/W. Install buried television road crossing. Install ½ inch television cable in conduit, 2-5 feet within R/W. Raise existing pedestal, 20 feet right. Install 150 pair telephone cable in existing conduit on right. Install a ¾ inch television cable in existing conduit on right. Install buried telephone road crossing. Install buried television road crossing. Install buried main television trunk line road crossing. | 7 days 7 days 1 day 1 day 7 days 1 day 2 days 1 day 8 days 1 day 1 day 1 day |

This work shall be coordinated with the Contractor's Traffic Control Plan.

City of Unalaska, Electric.  The City of Unalaska will perform the following work on their existing system located within the project limits.  The Contractor shall provide the City with a 15 day advance notice of when work will occur in each of the following areas:

| STATION | WORK DESCRIPTION | DURATION |
| --- | --- | --- |
| 21+15 to 28+70 21+15 to 24+30 27+85 28+70 to 33+40 29+35 LT 31+00 LT to 31+25 RT 31+25 LT to 33+40 RT 51+95 LT 52+30, 30' LT | Install 1/0 and 4/0 electrical cables in duct between existing vaults. Install 1/0 electrical cable in duct between existing vault and cross road to existing switch cabinet. Install buried electrical cables and duct road crossings. Install 1/0 and 4/0 electrical cables in duct between existing vaults. Remove pole. Install 1/0 cable in duct road crossing. Install 1/0 cable in duct road crossing. Remove electrical vault. Install new vault, 1/0 and 3/0 cable in conduit. | 10 days 3 days 2 days 10 days 1 day 2 days 3 days 1 day 4 days |

This work shall be coordinated with the Contractor's Traffic Control Plan.

Standard Modifications

105-1.12  LOAD RESTRICTIONS.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless otherwise allowed by an approved Traffic Control Plan.  (5/7/91)M32

Special Provisions

105-1.13  MAINTENANCE DURING CONSTRUCTION.  Add the following:  During the construction season and prior to winter shutdowns, the Contractor shall inspect and clean all storm drain sumps and petroleum separator manholes.  This inspection and maintenance of the storm drain system will not be paid for directly but will be subsidiary to work paid for under Sections 603 and 604.  (7/24/91)R4

Standard Modifications

105-1.15  PROJECT COMPLETION.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas, and Subsection 621-3.04, Period of Establishment, a letter of project completion will be issued by the   Engineer.  (7/2/93)M7

105-1.17  CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (7/2/93)M8

Special Provisions

105-1.17  CLAIMS FOR ADJUSTMENT AND DISPUTES.  Replace the first sentence of the eighth paragraph with the following:  If the claim is not resolved by agreement within 30 days of its receipt, the Engineer will issue a written decision to the Contractor.  (7/2/93)S71

Add the following:  Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (8/5/93)R93

SECTION 106

CONTROL OF MATERIALS

Special Provisions

106-1.01  SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  Add the following:  All steel and iron products which are incorporated into the work and the action of applying a coating to a covered product (i.e., steel and iron) shall be manufactured in the United States except that minor amounts of products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater.  Coating includes epoxy coating, galvanizing, painting, and any other coating that protects or enhances the value of a material subject to the requirements of this paragraph.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the  project.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel or iron products into the project.

(7/2/93)S13

106-1.02  LOCAL MATERIAL SOURCES.  Under item 1. General, add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)S32

Add the following after the first paragraph:  The Contractor is responsible for the sampling and testing of materials for process quality control, including screening, crushing, blending, and stockpiling of aggregates, production and laydown of aggregate courses or aggregate mixtures, and monitoring of compaction.  Process control tests shall be documented and shall be available for review by the Engineer.

The Contractor shall provide a field laboratory for process control testing.  The contractor-furnished laboratory shall be fully furnished with appropriate testing equipment and shall be shared with the Engineer for concurrent process control testing.  The contractor-furnished laboratory is in addition to and separate from the field laboratory which is specified under Section 644 for acceptance testing by the Engineer.

A Crushing Control Plan shall be submitted at least 15 working days prior to the beginning of crushing operations.  The plan shall include a proposed testing frequency for aggregate gradation and a description of the process control testing location, staffing, and equipment.  Abbreviated testing for process control of gradation shall be in accordance with Alaska Standard Practice SP-9.  Such sampling and testing will be coordinated with the Department and split samples are to be provided to the Department.

(2/1/94)S74A

Add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement shall be provided to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)R5

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.11  PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following to the third paragraph:  When working near designated wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits.

The Contractor shall report immediately to the Engineer any hazardous material discovered, exposed, or released into the air, ground, or water during construction of the project.  The Contractor shall also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery.  Hazardous materials include, but are not limited to, petroleum products, oils, solvents, paints, and chemicals that are toxic, corrosive, explosive, or flammable.  (5/7/91)S47

Add the following after Item 10:

11. 	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2575.

Add the following: The Contractor shall not excavate, nor use for fill, any material at any site suspected of or found to contain hazardous materials or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected of or found to contain hazardous materials or petroleum fuels.

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.  If the Contractor chooses to pursue permit modifications, such modifications shall be requested through the Engineer.

The Contractor shall do no work, stockpiling, staging, parking nor trespassing in or around any watercourses except for that work permitted by the Contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

(5/27/92)R7

Standard Modifications

107-1.13  RESPONSIBILITY FOR DAMAGE CLAIMS.  In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries".  (5/12/89)M9

Special Provisions

107-1.15 CONTRACTOR'S RESPONSIBILITY FOR WORK.  Add the following to the end of the first paragraph:  Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense.  (5/7/91)S48

Standard Modifications

107-1.16  CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICES.  In the last sentence of the third paragraph delete:  "by the local fire authority."  (5/12/89)M10

Special Provisions

107-1.16  CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	the utility mislocates the facility in the field by more than 5 (five) feet horizontally for non-frozen soil conditions, or

2.	when the location or existence of the buried facility is unknown by the utility.

Add the following:  Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 5 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work to be performed.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will not be paid for separately, but will be subsidiary to the item(s) of work being performed requiring these services.

(4/21/94)R170

107-1.21  PERMITS.  Add the following subsection:  The following permits have been received on the Contractor's behalf by the Department:

1.	Department of the Army, Corps of Engineers Permit No. M-910363, Unalaska Bay 14.

2.	Department of the Army, Corps of Engineers Nationwide 13, No. 9–940121.

The Contractor shall provide the information necessary to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge stormwater from the construction site.  Requirements for this permit are given under Section 641, Erosion and Pollution Control.

The permits obtained by the Department are attached to these specifications as Appendix A.  The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor's responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer.  The Engineer will then decide if a permit modification is necessary.  The Engineer will have copies of the permits posted in the project office.

(9/10/92)R9A

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  SUBLETTING OF CONTRACT.  Delete the second paragraph.  (6/6/94)S68

108-1.01  SUBLETTING OF CONTRACT.  Delete the third paragraph on page 56 and substitute the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Commercial Driver's License, with the appropriate endorsements for the class of vehicle to be operated,

2.	business license for trucking together with supporting documents that list the driver as the business owner or corporate officer,

3.	documents showing the driver's ownership interest in the truck including:

a.	truck registration, and

b.	lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	The owner-operator's right to control the manner in which the work is to be performed,

2. 	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3. 	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4. 	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each owner-operator.  The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.

(5/7/91)S49

Standard Modifications

108-1.03  PROSECUTION AND PROGRESS.  In Item 1. insert: ", in a format acceptable to the Engineer," immediately after the words: "a progress schedule".  (5/12/89)M11

Special Provisions

108-1.03  PROSECUTION AND PROGRESS.  In the first paragraph, delete the words "At this time" and substitute:  "Five working days before the preconstruction conference".  (5/7/91)S50

Delete Item 5., and substitute the following:

5.	A plan for erosion and pollution control, as required under  Subsection 641-1.02, Submittals.  (9/21/92)R160

108-1.05  CHARACTER OF WORKMEN, METHODS AND EQUIPMENT.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer.  (9/1/89)R13

Standard Modifications

108-1.07  FAILURE TO COMPLETE ON TIME.  Replace the third sentence of the first paragraph with the following:  The amount of these deductions is to reimburse the Department for estimated additional contract administration expenses incurred as a result of the Contractor's failure to complete the work within the time specified.

Replace Table 108-1 with the following:

TABLE 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Original Contract Amount |  |  |
| --- | --- | --- |
| From More Than | To and Including | Daily Charge |
| $ 0 | $ 100,000 | $ 300 |
| 100,000 | 500,000 | 550 |
| 500,000 | 1,000,000 | 750 |
| 1,000,000 | 2,000,000 | 1,000 |
| 2,000,000 | 5,000,000 | 1,500 |
| 5,000,000 | 10,000,000 | 2,500 |
| 10,000,000 | - | 3,000 |

(7/2/93)M49

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  GENERAL.  Add the following:  When more than one type of material or work is specified for a pay item, letter or numeric suffixes, included within the parenthesis following the pay item number, will differentiate the types.  (7/2/93)S63

109-1.02  MEASUREMENT OF QUANTITIES.  Add the following after the eighth paragraph:  The Contractor shall furnish competent scale operators to weigh all materials measured and paid for on a weight basis.

Scale operators shall operate the scale(s) and keep records as directed by the Engineer.  All records shall be given to the Engineer as directed.  No weigh tickets shall be issued to vehicles which are not in compliance with the requirements of 105-1.12 LOAD RESTRICTIONS.

The weigh ticket shall accompany the load and be given to the ticket taker at the delivery location.  Each sheet of the sequential transaction printer log shall be signed and dated by the scale operators prior to the end of each shift or as directed by the Engineer.  Scale operators will acknowledge, by signature on a form prepared by the Engineer prior to weighing loads, that their signature on the sequential transaction log indicates their certification that all entries are true and correct.

The Engineer may, if he determines it to be necessary, designate previously weighed vehicles to be reweighed in his presence to verify the weight of the materials being purchased.  This may include empty or loaded vehicles as the Engineer may designate.

No direct payment will be made for furnishing scale operator(s), equipment, and incidentals required, but the costs thereof will be considered a subsidiary obligation.

Add the following:

TABLE 109-1

| CONVERSION TO THE SI INTERNATIONAL SYSTEM OF UNITS* |  |  |
| --- | --- | --- |
| To convert from | to | Multiply by |
| mile (US Statute) | meter (m) | 1,609.347 |
| foot | meter (m) | 0.3048 |
| foot (US survey) | meter (m) | 1200/3937 |
| inch | meter (m) | 0.0254 |
| square foot | square meter (m2) | 0.09290304 |
| square yard | square meter (m2) | 0.8361274 |
| acre (US Survey) | square meter (m2) | 4,046.873 |
| cubic foot | cubic meter (m3) | 0.02831685 |
| cubic yard | cubic meter (m3) | 0.7645549 |
| gallon (US liquid) | cubic meter (m3) | 0.003785412 |
| M. Gal. | cubic meter (m3) | 3.785412 |
| pound (lb avoirdupois) | kilogram (kg) | 0.45359237 |
| ton (short, 2000 lb) | kilogram (kg) | 907.1847 |
| pound-force (lbf) | newton (N) | 4.448222 |
| footcandle | lux (lx) | 10.76391 |
| degree Fahrenheit | degree Celsius (C) | tC=(tF-32)/1.8 |

* From ASTM publication E380-89a, Standard Practice for Use of the International System of Units (SI) The Modernized Metric System.

Standard Modifications

109-1.03 SCOPE OF PAYMENT.  Delete the last sentence of the fourth paragraph.  (5/7/91)M33

Special Provisions

109-1.03  SCOPE OF PAYMENT.  Add the following:  No payment will be made for any material delivered in a vehicle which is not in compliance with the requirements of 105-1.12 LOAD RESTRICTIONS and 644-2.06 SCALES.

109-1.05  COMPENSATION FOR EXTRA WORK.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)R14

109-1.06  PROGRESS PAYMENTS.  Add the following:  Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  This retainage will be released by the Engineer upon receipt of current schedules from the Contractor.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  This retainage will be released by the Engineer upon satisfactory completion of the requirements of the permit.

109-1.07  PAYMENT FOR MATERIAL ON HAND.  Add the following:  Materials shall be physically separated from the other materials stored at the storage location.  Materials shall be clearly labeled with the project name and number.  Materials shall be stored in accordance with the manufacturer's published recommendations.  A copy of any such recommendations shall be provided to the Engineer.

Should storage conditions become unsatisfactory, any payments made for the materials will be classified as unearned.  If the Contractor has not earned sufficient funds to cover the cost of a deduction on the next progress payment, a request for repayment will be sent to the Contractor.  The Contractor agrees to repay the Department within 30 days from the date of a request to refund payment when the storage conditions have become unsatisfactory .  Unsatisfactory storage conditions include, but are not limited to:

1.	Storage not in accordance with the manufacturer's recommendations.

2.	Commingling or storage of other materials where any element of doubt exists as to which materials belong in which lot.

3.	Unsatisfactory labeling of materials.

4.	Any liens filed on the materials for storage or transport, or by the supplier or manufacturer of the material.

5.	Change of the storage locations without obtaining approval of the Engineer prior to the relocation.

6.	Damage to all or part of the materials by fire, theft, or other peril.

Should labor, travel, or any other costs be incurred for inspection off the limits of the project, the Contractor shall reimburse the Department for these costs.

The Contractor releases and discharges the Department from any liability arising out of, or in any way related to, the payment for materials on hand and/or to the storage or transport of these materials.  The Contractor is responsible for damages or delays which may relate to the storage or transport of the materials.

Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project will be only at a location acceptable to the Engineer.  (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 23, with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds. The Contractor shall not, nor shall subcontractors or others associated with this contract discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 23, in compliance with the Federal Highway Administration's DBE Program guidelines and the Department's federally approved DBE Program.

120-1.03  ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS36.30.640(4).

120-1.04  DEFINITIONS AND TERMS

1.	Broker.  A DBE that arranges for the delivery or provision of creditable materials, supplies, equipment, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF).  The execution of a contract or a distinct element of work or service under a contract by the DBE actually performing, controlling, managing, and supervising the work involved with its own equipment and employees within its certified category.  The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the contract.

3.	Disadvantaged Business Enterprise (DBE).  A firm certified by the State of Alaska, Department of Transportation and Public Facilities, in accordance with 49 CFR, Part 23, or one granted that status under the Alaska Native Claims Settlement Act, 1991 Amendments and certified by the Department for participation in the Department's DBE program.

4.	Good Faith Efforts.  The affirmative action measures that shall be taken by a contractor to meet the DBE Program objectives and goals for this project.

5.	Manufacturer.  A DBE certified in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

6.	Original DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the contract bid schedule before approval of the Revised DBE Utilization Goal.

7.	Regular Dealer.  A DBE certified in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project,

b.	keeps an inventory in an amount appropriate for the type of work using that product, and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis.

8.	Revised DBE Utilization Goal.  The DBE Utilization as submitted by the contractor and approved by the Department for this project on Form 25A325C.  The Revised DBE Utilization Goal may be equal to, greater than, or less than the Original DBE Utilization Goal, if approved.  Once approved, this Revised goal becomes the minimum required DBE participation during the execution of the contract.

120-2.01  UTILIZATION GOAL.  The Original DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total basic bid amount.  In order for the work of the DBE to be credited towards meeting the Original DBE Utilization Goal at time of contract award, the DBE must be certified by the Department in a category covering the CUF to be performed at the time of listing on the "DBE Utilization Report" (Form 25A325C).

A bidder shall demonstrate the ability to meet the Original DBE Utilization Goal or perform and document all of the required Good  Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this contract.

120-3.01  DETERMINATION OF COMPLIANCE

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder shall demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of receipt of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the contractor submits less DBE utilization on Form 25A325C than is required to meet the Original DBE Utilization Goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (25A321A) shall be submitted.  If accepted by the Department, this lower DBE utilization becomes the Revised DBE Utilization Goal.

If the bidder cannot demonstrate the ability to meet the Original DBE Utilization Goal, failure to document the minimum required Good Faith Efforts will result in the bid being declared nonresponsive.

c.	Where the bidder submits more DBE utilization on Form 25A325C than is required by the Original DBE Utilization Goal, this higher DBE utilization, if accepted by the Department, becomes the Revised DBE Utilization Goal.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.  Prior written request by the Contractor and approval from the Engineer is required for the replacement of a DBE for any reason.  If DBE replacement is approved, the Contractor is obligated to replace the DBE with another DBE for the same work in order to still meet the Revised DBE Utilization Goal.  If the Contractor cannot find a replacement DBE, the Contractor shall document the required Good Faith Efforts stipulated in Subsection 120-3.02 for the items of work to have been performed by the replaced DBE in order to have the Revised DBE Utilization Goal reduced.

120-3.02  GOOD FAITH EFFORT.  The Contracting Officer will use all of the following criteria to judge if the bidder, who has not met  the Original DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.  Failure by the Contractor to perform and document any of the following actions 1-7 constitutes insufficient Good Faith Effort.

1.	Consideration of all subcontractable items.  The Contractor shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department prior to bid opening (see Form 25A324).

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification at least 10 calendar days prior to bid opening to all DBEs listed in the Department's most current DBE Directory certified to perform those work items identified in Form 25A324 of the bidder's/Contractor's interest in securing the DBE's participation in the execution of the work.  Each contact with the DBE shall be logged on a "Contact Report" (Form 25A321A).

4.	Request for DBE participation on specific items of work or services.  Allegations of non-competitive DBE quotes must be documented and verifiable.  A DBE quote that is more than 10.0% higher than the accepted non-DBE quote shall be deemed non-competitive, provided the DBE and non-DBE quotes are for the exact same work or service.  Where the Contractor rejects a DBE quote as being non-competitive under this condition, the work performed and payments received by the non-DBE during the execution of the contract shall be consistent with the non-DBE's accepted quote.  This does not preclude increases as a result of Change documents issued by the Department.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about the requirements of the contract regarding the specific item of work or service sought from the DBE.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether or not they were interested in bidding.  Documentation of follow-up contacts shall be logged on the "Contact Report" (Form 25A321A).

Items 4. through 7. will be utilized to evaluate any request from the Contractor for a reduction in the Revised DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

120-3.03  COMMERCIALLY USEFUL FUNCTION (CUF).  Measurement of attainment of the Revised DBE Utilization Goal shall be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.

CUF is limited to that of a:

a.	regular dealer,

b.	manufacturer,

c.	broker,

d.	subcontractor

e.	joint-venture, or

f.	prime contractor.

In order for the CUF work of the DBE to be credited toward the goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE shall be certified in the appropriate category at the time of:

a.	the Engineer's approval of the DBE subcontract; and

b.	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

2.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

3.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted within that category to the CUF of a broker.  (This does not effect the CUF of that same firm, when performing work as a subcontractor and certified in another category such as embankment or excavation which could include the hauling of materials for that work.)

4.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

5.	Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the Revised DBE Utilization Goal.

6.	Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm shall not be credited toward the Revised DBE Utilization Goal.  The Contractor must still meet the Revised DBE Utilization Goal by either:

a.	Withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items 4-7) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01, or

b.	Continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out and DBEs in an amount to meet the Revised DBE Utilization Goal through either

1)	subcontractor substitution (Subsection 103-1.01),

2)	increasing the participation of other DBEs on the project,

3)	documenting Good Faith Efforts (Subsection 120-3.02, items 4-7),

4)	or by a combination of the above.

7.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the Revised DBE Utilization Goal.

8.	The Engineer shall consider the following criteria when determining what CUF is being performed by the DBE:

a.	The work performed shall be necessary and useful work required for the execution of the contract.

b.	The scope of work shall be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

c.	The work shall be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE, with the exception allowed under (d) below.  Either the DBE owner or an on-site DBE representative, DBE superintendent, or DBE foreman shall be responsible for the work at the site.  All such DBE representatives must be designated as a key employee in the DBE's certification records with the Department prior to DBE subcontract award.

d.	The DBE shall use their own employees and equipment for the execution of the work.  An exception to this requirement may be permitted where the DBE must perform  a specialty task or where the work is in a remote area.  In such instance, the DBE may temporarily augment its project workforce with another contractor's equipment and employees (not to include supervision) in order to perform the work, if the Department considers this normal practice performed by non-DBE contractors, within the Alaskan construction industry.

On any project, this practice shall not involve more than 33.3% of the DBE's subcontract value.  Also, the Contractor shall submit a request in writing from the DBE and secure the Department's approval for such arrangement prior to commencement of the DBE's subcontract work involved.  Exclusive of this arrangement, the DBE's project work force shall be regular DBE employees.

In all instances, the DBE shall be responsible for its payroll and labor compliance requirements concerning all workers under its control.  DBE leases and payments for equipment must be documented; Contractor withholding or retainage for DBE labor and equipment usage is not permissible.  Two-party checks to individuals are not permissible.

e.	The manner in which the work is sublet or performed shall conform to standard, statewide industry practice within Alaska, as defined by the Department.  The work or provision of goods or services shall have a market outside of the DBE program (must be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed a superfluous step in the contracting or purchasing process and no DBE credit will be allowed.

There shall be no DBE credit for lower-tier non-DBE subcontract work, unless the Department defines this lower-tier subcontracting as standard, statewide industry practice within Alaska.

f.	The cost of the goods and services shall be reasonable and competitive with the cost of these goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

g.	All subcontract work, with the exception of truck hauling, shall be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE shall control all business administration, accounting, billing, and payment transactions (this requirement does not preclude the two-party check allowance described under i., below).  The prime contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

i.	Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE.

Two-party checks may be issued by the Contractor on an occasional basis to the DBE and another business for work or services performed under the contract; however, the Engineer shall be notified in writing in advance.  DBE credit will not be given for these two-party payments, if issued on a routine basis or issued to an extent greater than that offered by the prime to non-DBEs on the project.

j.	A DBE trucking firm certified and performing work in the transportation/hauling category shall have a supervisor on-site at all times in charge of the dispatching of trucks and the hauling of materials before any DBE credit may be credited.  The DBE supervisor must be regularly employed by the DBE and designated as a key employee in the DBE's certification records with the Department prior to prime contract award.

9.	The Contractor shall provide proof (canceled checks or bank statements that identify payor, payee, and amount of transfer) of the actual monies paid for the qualifying work, goods and services provided by DBEs.

10.	If the quantity of work of a bid item which involves a DBE is reduced by the Department, the Original and Revised DBE Utilization Goals on Form 25A325C are reduced proportionately.

120-3.04  DEFAULT OF DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs  to perform the defaulted work.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the Revised DBE Utilization Goal if, in the opinion of the Engineer, both of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with items 4 through 7 of Subsection 120-3.02 GOOD FAITH EFFORT for the defaulted work.

The Revised DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01  METHOD OF MEASUREMENT.  The Contractor shall be entitled to count toward the Revised DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer.   The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for work performed by a DBE prime contractor is 100%, not to exceed the Original DBE Utilization Goal.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value.  The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee shall not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee shall not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable  brokerage fee.  The brokerage fee shall not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department.  The DBE joint venture partner shall be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01  BASIS OF PAYMENT.  Meeting the Revised DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive or potential disincentive.

If the Contractor fails to meet the Revised DBE Utilization Goal, payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50% of the difference between the Revised DBE Utilization Goal expressed in dollars and the total creditable DBE participation as determined by the Engineer.

If and only after the Original DBE Utilization Goal established on Form 25A325C in terms of dollars has been met, the Contractor may be eligible for an incentive payment based upon the following calculation:

10% of the total dollar amount of CUF work performed by DBE subcontractors not needed in the calculation to meet the Original DBE Utilization Goal; except that the total incentive paid to the Contractor will not exceed 2% of the total basic bid amount at time of original contract award or $100,000, whichever is less.

Payment of the incentive will be made on the final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the Department within 30 days of being billed for the amount due.

A Change Order is not required for DBE Adjustment.  The Notice To Proceed shall constitute the notice required to initiate DBE Adjustment.

Payment or Deduction will be made under:

Pay Item No.	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent  Sum

(6/6/94)S33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01   DESCRIPTION.   Add the following:  This work shall also consist of the removal of boulder piles and placement of the rock as designated on the plans and as specified.

202-2.02   GENERAL.   Add the following:  At the locations shown on the plans, all boulders, rock, and concrete rubble pieces shall be removed from the existing piles and placed as bank protection.  Boulders and concrete rubble pieces must be individually placed from the toe of slope upward in accordance with the Corp of Engineers permit No. M-910363, Unalaska Bay 14, and as directed by the Engineer.  The Contractor shall utilize a backhoe, crane, or other methods to lower the material and arrange uniformly.  Pushing the material over the embankment is prohibited.

202-4.01   BASIS OF PAYMENT.   Add the following:  The removal and placement of boulders will not be paid for separately but will be included in the lump sum payment for Item 202(1), Removal of Structures and Obstructions.

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01  DESCRIPTION.  Add the following:  Stripping surface course shall consist of removal of the top 4 inch layer of the existing roadway under the proposed structural section.

Standard Modifications

203-2.05  BORROW.  Add the following:  Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.  (5/12/89)M12

203-2.06  CONTROLLED BLASTING.  Delete this subsection in its entirety and substitute the following:  Controlled blasting techniques, as described herein, shall be used for forming all highway rock cut slopes greater than 10 feet in height at the locations shown on the plans.

Description.  Controlled blasting refers to the controlled use of explosives and blasting accessories in carefully spaced and aligned drill holes to produce a free surface or shear plane in the rock along the specified excavation backslope.  The purpose of controlled blasting is to minimize damage to the rock backslope to help insure long term stability.

Use of Explosives.  All blasting operations, including the storage and handling of explosives and blasting agents, shall be performed in accordance with the applicable provisions of the Standard Specifications and all other pertinent Federal, State and local regulations.

Product Specifications.  All blasting caps and all explosives used on the project shall be one year or less in age.

To ensure the accuracy of firing times of blasting caps, each cap period shall come from one lot number.  Mixing of lot numbers for any one cap period is prohibited.

No blasting product shall be brought to the job site if the date codes are missing.

Blasting Plan Submittal.  A minimum of two weeks prior to commencing drilling and blasting operations, or at any time the Contractor proposes to change the drilling and blasting methods, the Contractor shall submit a "Blasting Plan" to the Engineer for review.  The blasting plan shall contain the full details of the drilling and blasting patterns and controls the Contractor proposes to use for both the controlled and production blasting.  The blasting plan shall contain the following minimum information:

1.	Station limits of proposed shot.

2.	Plan and section views of proposed drill pattern including free face, burden, blasthole spacing, blasthole diameters, blasthole angles, lift height and subdrill depth.

3.	Loading diagram showing type and amount of explosives, primers, initiators and location and depth of stemming.

The blasting plan submittal is for quality control and record keeping purposes.  Review of the blast plan by the Engineer shall not relieve the Contractor of his responsibility for the accuracy and adequacy of the plan when implemented in the field.

Scaling and Stabilization.  All rock on the cut face that is loose, hanging or which creates a potentially dangerous situation shall be removed or stabilized to the Engineer's satisfaction during or upon completion of the excavation in each lift.  Drilling of the next lift will not be allowed until this work has been completed.

The slopes shall be scaled throughout the length of the contract and at such frequency as required to remove all hazardous loose rock or overhangs.  The slopes shall be hand scaled using a suitable standard steel mine scaling rod.  Subject to the Engineer's approval, other methods such as machine scaling, hydraulic splitters or light blasting may be used in lieu of, or to supplement, hand scaling.

Material outside the planned neat line which appears unstable and constitutes a potential rockfall hazard in the opinion of the Engineer shall be excavated and removed.  Such material shall be used in the construction of embankment or disposed of as directed by the Engineer.

Safety.  The Contractor shall observe the entire blast area for a minimum of 5 minutes following a blast to guard against rock fall before commencing work in the cut.

Controlled Blasting (Presplitting or Preshearing).  All presplitting shall be performed in accordance with the following requirements:

All drilling equipment used to drill the presplit holes shall have mechanical devices affixed to that equipment to accurately determine the angle at which the drill steel enters the rock.  Presplit hole drilling will not be permitted if these devices are either missing or inoperative.

The length of presplit holes for any individual lift shall not exceed 40 feet unless authorized by the Engineer.

When the cut height will require more than one lift, a maximum 2 foot offset between lifts shall be permitted to allow for drill equipment clearances.  The Contractor shall begin the control blast hole drilling at a point which will

allow for necessary offsets and shall adjust, at the start of lower lifts, to compensate for any drill hole drift which may have occurred in the upper lifts.  Payment for the additional excavation volume resulting from the allowed 2 foot offsets shall be at the contract unit price for rock excavation.

Drilling 2 feet below the ditch bottom will be allowed to facilitate removal of the toe berm.

Drill hole conditions may vary from dry to filled with water.  The Contractor will be required to use whatever type(s) of explosives and/or blasting accessories necessary to accomplish the specified results.

Bulk ammonium nitrate and fuel oil (ANFO) shall not be used in the presplit holes.

Only standard explosives manufactured specifically for presplitting shall be used in presplit holes, unless otherwise approved by the Engineer.

If fractional portions of standard explosive cartridges are used, they shall be firmly affixed to the detonating cord in such a manner that the cartridges will not slip down the detonating cord nor bridge across the hole.  Spacing of fractional cartridges along the length of the detonating cord shall not exceed 30 inches center to center and shall be adjusted to give the desired result.

The upper portion of all presplit holes, from the top most charge to the hole collar, shall be stemmed.  Stemming materials, shall be sand or other dry, angular and granular material, all of which passes a 3/8 inch sieve.

Production Blasting.  All production blasting shall be performed in accordance with the following general requirements.

A line of buffer holes shall be drilled on a parallel plane adjacent to the presplit holes.  The line of buffer holes shall be drilled approximately 3 feet out from the presplit line and spaced 3 to 5 feet center to center.  The explosive loads in these holes shall not exceed fifty percent of the average explosive load that could be placed in the nearest production holes.  Detonation of the buffer holes shall be on a delay sequence toward a free face and shall follow detonation of the production holes.

Production blast holes shall not be drilled closer than 6 feet to the controlled blast line, unless approved by the Engineer.  The bottom of the production holes shall not be lower than the bottom of the controlled blast holes, except in the production drilling for the bottom lift.  For the drilling of the bottom lift, subdrilling to a minimum of 6.5 feet below finished grade shall be allowed.  Production holes shall not exceed 6 inches in diameter, unless approved by the Engineer.  Detonation of production holes shall be on a delay sequence toward a free face.  Stemming material used in production holes shall be sand or other dry angular granular material, all of which passes a 3/8 inch sieve.

Fluff Blasting.  Fluff blasting shall consist of drilling and shooting the  rock area to a depth of at least 3 feet beneath the finish grade resulting in a fractured or broken rock foundation.

203-3.02  EMBANKMENT CONSTRUCTION.  On page 97, delete the fifth paragraph and substitute the following:  All embankments shall be constructed with moisture and density control unless the Engineer determines that such controls are not feasible.  (5/7/91)M35

Special Provisions

203-3.02   EMBANKMENT CONSTRUCTION.  Replace paragraphs 11 and 12 with the following:  When the excavated material consists predominantly of rock fragments or boulders too large to be placed in 8 inch layers, the Contractor shall process the material as required to reduce it to a suitable size for incorporation into the embankment as Selected Material Type, B.  Any material that the Contractor disposes of, unless excess to embankment requirements, shall be replaced with borrow at the Contractor's expense.

203-3.03  CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete the second paragraph and substitute the following:  Embankment material shall be compacted to not less than 95 percent of the maximum density.  Maximum densities will be determined by AASHTO T 180 in conjunction with AASHTO T 224 or ATM T-12.  In place field densities will be determined by ATM T-3 or ATM T-11.

Add the following:  All embankment within 20 feet of a bridge abutment shall be compacted full width to not less than 100 percent of the maximum density.  All material used within this zone shall be graded to pass the 3-inch sieve.

203-3.04   COMPACTION OF EMBANKMENTS NOT CONSTRUCTED WITH MOISTURE AND DENSITY CONTROL.  Replace the first paragraph with the following:  Except for the first layer of fills over swampy ground, embankment materials shall be deposited in layers not exceeding 8 inches in -thickness before compaction.

203-3.05  CONTAMINATED MATERIAL TESTING.  Add the following subsection:  This work shall consist of testing soils for contaminants.  All work shall be performed under the supervision of a Professional Hazardous Waste Firm and in accordance with the following:

1.	Monitoring Excavation for Contaminated Soil.  A Professional Hazardous Waste Firm shall be provided by the Contractor.  This firm shall be in responsible charge of monitoring excavation activities and assuring contaminated soils encountered during construction are disposed of according to appropriate regulatory requirements.

2.	Professional Hazardous Waste Firm.  The firm shall have a current Alaska Department of Environmental Conservation (ADEC) approved Quality Assurance Program Plan (QAPP).  All work shall be in accordance with the procedures detailed in the QAPP and a project specific testing plan approved by ADEC.  The firm shall perform the following duties:

a.	Field monitor and direct all activities related to working within known or suspected contaminated areas.

b.	Prior to any work in the known contaminated areas, submit for the Engineer's approval an ADEC approved:

1)  	Site specific Quality Assurance Project Plan (QAPP).  This plan shall detail how the firm will identify and screen contaminants in the field, transport contaminated materials to the temporary disposal site and remediation location, identify the need for additional temporary stockpile locations, and detail the analytical methods to be used for determining the degree of contaminants in the excavated soil.

2)	Temporary Soil Stockpile Plan.  This plan shall identify where and how potentially contaminated soil would be stockpiled on-site until quantitative analyses are accomplished.  In addition, this plan shall detail what quantitative tests will be done, and how sampling of the material will be conducted.

c.	Characterize any contamination discovered during construction by techniques including, but not limited to, test pits, hand borings, and soil borings.

d.	Test the contamination levels in the soils and determine if the soils can be disposed of as unclassified excavation.

e.	Prepare closure reports required by ADEC regulations, and maintain "chain-of-custody" paperwork concerning the disposal of the contaminated soil.

3.	Worker Health and Safety.  Prior to the excavation of any soils identified as contaminated, the Contractor shall assure that all personnel working in the area of the potential contamination have received the State of Alaska, Department of Labor, Health and Safety Training.  The Contractor shall provide the Engineer with a list of all personnel that will be working within the area identified as being contaminated.

The Contractor shall perform all work according to a site health and safety plan which meets ADEC and OSHA requirements.

The Contractor shall notify all personnel and subcontractors prior to their beginning work at the site that they will be working in an area identified as being potentially contaminated.

203-3.06   EXCAVATION OF CONTAMINATED MATERIAL.  Add the following subsection:  This work shall consist of removing and disposing of fuel contaminated soils encountered during construction.  Disposal of fuel contaminated soils shall be at a location approved by the Engineer.

1.	Determining Limits of Contaminated Soil.  The exact limits of potential contaminated soil within the excavation can not be determined until the material is exposed.  Once exposed, the material shall be tested in accordance with Subsection 203-3.05, Contaminated Material Testing.  Testing will verify the contamination levels in the soils and determine if the soils can be disposed of as unclassified excavation or if it requires special handling.

2.	Contaminated Soil Removal and Segregation.  Petroleum hydrocarbon contaminated soils have been identified within or adjacent to the right-of-way in the proximity of the following locations;

Between Stations 24+60 to 27+20 LT, two soil samples were analyzed for Total Petroleum Hydrocarbons (TPH), Extractable Petroleum Hydrocarbons (EPH), Benzene-Toluene-Ethylbenzene-Xylenes (BTEX) and Halogenated Volatile Organics (HVOs).  The results indicate that soil excavated in this vicinity is anticipated to contain petroleum hydrocarbons in concentrations less than regulatory thresholds requiring action.

In the vicinity of Station 55+00 LT, TPH levels ranged from 83.3 ppm to 31,600 ppm and an EPH level of 18,600 ppm was detected.  Test results indicate contaminated soil exceeding regulatory limits is expected to be excavated in this vicinity.

In the vicinity of Station 63+00 LT, three of four samples located outside the project limits exceeded regulatory limits, the highest containing 6,600 ppm of TPH, 330 ppm of EPH, and 73 ppm total lead.  Contaminated soil is not expected to be excavated in this vicinity, however, the potential exists.

Between Stations 71+20 to 81+30 RT, four of six samples taken exceeded regulatory limits for TPH and EPH.  Petroleum contaminated soils may be encountered between these stations due to minor utility relocations.

Between Stations 124+00 to End of Project, four of nine samples taken exceeded regulatory limits.  In addition, a sample exceeding the regulatory limits for EPH was collected near Station 154+00 RT.  There is the potential to excavate contaminated soil near Station 154+00 Rt.

The firm shall screen all material excavated in these areas with a photoionization detector (PID) or other field screening devise to segregate non-contaminated soils from contaminated soils, and shall monitor and verify the contamination levels in the soils which are removed from the site for disposal.

In the event the Contractor must temporarily stockpile petroleum contaminated soil, a petroleum resistant bottom liner, water resistant top cover, and temporary fencing will be required.  The liner, cover and temporary fencing shall be provided by the Contractor.

3.	Transportation.  Petroleum contaminated soils which cannot be disposed of as unclassified excavation shall be transported to the designated temporary stockpile site or another location approved by the engineer.  Transportation of contaminated soils treated off-site must be done in such a manner to minimize the possibility of loss of materials during transport.  All soils need to be transported as a covered load.

203-4.01  METHOD OF MEASUREMENT.  Add the following:  Providing a hazardous waste professional to test for contaminated soils will not be measured for payment.  Testing soils to determine contamination will be measured for payment under Item 644(8), Contaminated Material Testing.

Item 203(20), Fuel Contaminated Soil Special Handling, will be measured for payment in accordance with Subsection 109-1.05, Compensation for Extra Work.  Backfilling within the plan excavation limits will not be measured for payment but will be subsidiary to Item 203(20), Fuel Contaminated Soil Special Handling.  Backfilling outside plan excavation limits will measured as embankment construction.

Measurement of stripping surface course will be measured for payment by the station along the center of the roadway, complete and accepted by the Engineer.  No deduction from the excavation quantities will be made for material removed under Item 203(38) Stripping Surface Course.

Standard Modifications

203-5.01  BASIS OF PAYMENT.  Change Pay Items 203(5), (6) and (7) to read:  Borrow, Type _____.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)M12

Special Provisions

203-5.01  BASIS OF PAYMENT.  Add the following:  Payment for production blasting and fluff blasting not be paid for separately, but will be subsidiary to Item 203(2) Rock Excavation.

Scaling will not be paid for separately, but will be subsidiary to Items 203(2), Rock Excavation or 203(10), Controlled Blasting.  The removal and disposal of slide and slipout material will be paid for at the contract unit price for Item 203(1) Common Excavation if determined not to be the fault of the Contractor's methods.

Payment for providing the hazardous waste professional will be made under Item 644(8), Contaminated Material Testing.

Excavating and disposing of fuel contaminated soil will be paid under Item 203(20), Fuel Contaminated Soil Special Handling.  The Contractor will be paid on a time and materials basis for authorized Work in accordance with Subsection 109-1.05, Compensation for Extra Work.  Backfilling within plan excavation limits will be paid for under the items of work involved at the prices bid for that work.  Backfilling outside plan excavation limits will be paid for as embankment construction in accordance with this Section 203.

Grading and placement of material used within 20 feet of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(6B) Borrow, Type B.

(10/1/91)R113

Payment for stripping surface course will be full compensation for furnishing all equipment, labor, tools and incidentals to provide the excavation and shaping necessary to complete the work.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

203(20)	Fuel Contaminated Soil	Contingent

Special Handling	Sum

203(38)	Stripping Surface Course	Station

(3/3/94)R149

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01 MATERIALS.  Delete this subsection in its entirety and substitute the following:  Bedding and backfill materials shall meet the requirements for Selected Material, Type B, as specified in subsection 703-2.07 Selected Material.  Pipe bedding and backfill material shall also pass the 3-inch sieve.

Selected Material, Type B pipe backfill shall extend a minimum of 12 inches above the pipe.  Excavated native material shall be utilized for the remainder of the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07 Selected Material.  Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material.  All suitable material from structure excavation shall be used for bedding and backfill prior to using material from another source.

204-3.01  CONSTRUCTION REQUIREMENTS.  Add the following to the third paragraph:  Native material may be utilized for electrical conduit bedding and backfill outside the pavement structure if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07 Selected Material.  Compaction may be as approved by the Engineer.  This material shall also meet the requirements of Section 660-2.01, Excavating and Backfilling.

(3/23/93)R25

SECTION 205

EXCAVATION, BACKFILL AND

FOUNDATION FILL FOR STRUCTURES

Special Provisions

205-2.01   MATERIALS.    Add the following:  Backfill and foundation fill for Steel Bin Walls shall meet the requirements of selected material, Type B.

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01  MATERIALS.  Delete the second sentence of the first paragraph and substitute the following:  The gradation of base course material for use under asphalt concrete pavement shall conform to the requirements for Grading D-1.  The gradation of base course material for use as a surface course for the unpaved portions of driveways and side streets shall be Grading E-1.  (10/1/91)R116

301-3.01   PLACING.   Add the following:  In areas scheduled to receive asphalt concrete pavement, the base course material shall be paved over within 30 calendar days.

Delete this Section in its entirety and substitute the following:

SECTION 401

ASPHALT CONCRETE PAVEMENT

Standard Modifications

401-1.01  DESCRIPTION.  This work consists of the furnishing and mixing of aggregate and asphalt cement at a central mixing plant and the hauling, spreading, and compaction of the asphalt concrete mixture on a previously prepared surface, all as specified in the contract and in reasonably close conformance with the lines, grades and thickness shown on the plans.

401-2.01  COMPOSITION OF MIXTURES.  Mixtures shall be composed of aggregate and asphalt cement combined as specified for the type shown in the contract.

At least 30 calendar days prior to the production of asphalt concrete pavement mix, the Contractor shall submit the following to the Engineer:

1.	Notification that aggregate proposed for the mixture is available for sampling.

2.	A letter stating the proposed gradation for the Trial Job Mix Design, gradations for individual stockpiles, and blend ratio for each aggregate stockpile.  Job Mix Design proposals by the Contractor shall be within the broad band gradations set in Table 703-3.

3.	A minimum of three 1-gallon samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a temperature viscosity curve for the asphalt cement.

4.	A 1/2 pint sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

The Contractor shall accompany the Engineer during sampling, and shall furnish all the assistance needed to assure that the Engineer obtains representative samples.

From this information, the Engineer will establish the Job Mix Design which shall become a part of the contract and shall be followed unless modified in writing.  Job Mix Design test results will be available within 7 working days after submittal.

The Job Mix Design shall be determined by and shall conform to the requirements of ATM T-17 for Class B.

Changes in the Job Mix Design warranted by changes in the aggregate or sources of aggregate shall be submitted by the Contractor in the same manner as the original submittal.

The full tolerances specified below shall be applied to the approved Job Mix Design gradations and shall not be limited to the broad bands listed in Table 703-3.  Tolerances shall not be applied to the largest specified screen.

| Sieve Size or Item | Tolerance (Percent Passing) |
| --- | --- |
| 3/4 inch | +/- 8% |
| 1/2 inch | +/- 7% |
| 3/8 inch | +/- 7% |
| No. 4 | +/- 7% |
| No. 8 | +/- 6% |
| No. 16 | +/- 6% |
| No. 30 | +/- 5% |
| No. 50 | +/- 4% |
| No. 100 | +/- 3% |
| No. 200 | +/- 3% |
| Asphalt % | +/- 0.4% |

401-2.02  AGGREGATES.  Aggregates shall conform to the requirements of Subsection 703-2.04.

401-2.03  FILLER.  Filler shall conform to the requirements of AASHTO M 17.

401-2.04  ASPHALT CEMENT.  The grade of asphalt cement will be specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702, Asphalt Materials.  Asphalt cement may be conditionally accepted at the source.  If the cement is to be conditionally accepted at the source, the Contractor shall provide a manufacturer's certificate of compliance in accordance with Subsection 106-1.05 and test results of the applicable quality requirements of Section 702 before the cement is shipped.

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at 275 degrees Fahrenheit) of the asphalt cement used on the project changes from the viscosity of the cement supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended while a new Job Mix Design proposal is submitted for approval.

401-2.05  ANTI-STRIP ADDITIVES.  Anti-strip agents used shall be an approved type in the proportions determined by ATM T-14 and included in the approved Job Mix Design.

401-2.06  PROCESS CONTROL AND ACCEPTANCE.

1.	Process Control.  Process control for production of aggregates shall be performed in accordance with Subsection 106-1.02.

A Paving and Plant Control Plan shall be submitted at a pre-paving meeting to be held a minimum of 5 working days prior to initiating paving operations.  The Paving and Plant Control Plan shall outline the steps taken to assure product consistency and to minimize segregation and premature cooling of mixtures.  This plan shall include a proposed testing frequency for gradation, asphalt content, and compaction.  It shall also include a plan for the handling of or elimination of the wings on the paver hopper to prevent dumping and placement of cooled mix onto the roadway.

2.	Acceptance Testing by Department.  The Department will perform sampling and testing for acceptance of the work in accordance with the Department's testing frequency guide and standard acceptance test methods specified below.  Such testing may be done concurrently with the Contractor's process control testing.  Acceptance test results will be available to the Contractor as soon as possible upon their completion.

Sampling for the determination of aggregate gradation will be from the aggregate cold feed, individual hot bins, or from the combined aggregate just prior to the introduction of the asphalt cement.  All aggregate        samples will be split and the second half made available to the Contractor.

Acceptance testing for asphalt cement content will be determined by ATM T-16, ATM T-23 or AASHTO T 164.  Sampling for the determination of asphalt cement content will be from the mixture at the time of placement.

Samples taken for determination of density compliance shall be taken from the finished mat after final rolling.  Acceptance testing for field density will be determined in accordance with ATM T-22 except as modified in Subsection 401-3.12, Compaction.

3.	Unacceptable Work or Material.  Any mixture which is contaminated, segregated, or which does not otherwise conform to the specifications will be rejected and replaced at no additional cost to the Department with conforming material in accordance with Subsection 105-1.11, Removal of Unacceptable and Unauthorized Work.  All costs associated with removal and replacement of unacceptable mixture shall be borne by the Contractor.  At the discretion of the Engineer, unacceptable pavement may be overlaid with acceptable pavement at no additional cost to the Department.

CONSTRUCTION REQUIREMENTS

401-3.01  WEATHER LIMITATIONS.  The mixture shall not be placed on a wet surface, or on an unstable roadbed, when the base material is frozen, or when weather conditions prevent the proper handling, compacting, or finishing of the mixture.  No mixture shall be placed when the surface upon which the pavement is to be placed is at or below 35 degrees Fahrenheit.

401-3.02  BITUMINOUS MIXING PLANTS.  Mixing plants shall conform to AASHTO M 156.

Proportioning (batch) scales shall not be used for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

401-3.03  HAULING EQUIPMENT.  Trucks used for hauling mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime solution or other manufactured asphalt release agent included in the Department's Approved Products List.  Diesel or fuel oil shall not be used.  Each truck shall have a cover of canvas or other suitable material of such size as to protect the mixture from the weather, when required, so that the mixture will be delivered on the road at the proper temperature.

401-3.04  ASPHALT PAVERS.  Asphalt pavers shall be self-propelled units, provided with a heated vibratory screed and equipped with a paver control system which shall automatically control the laying of the mixture to specified transverse slope and specified longitudinal grade.  The paver control system shall be automatically actuated by the use of a mobile string line, ski, or other approved grade follower.  The length of the ski, mobile string line or other device shall be at least 30 feet in length.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation.  The hopper shall be equipped with a distribution system to place the mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Auger extensions shall be within 1.5 feet of the gates.

Extendible wings may be permitted for tapers, guardrail widening and approaches.

The use of a pickup machine to transfer the mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collection of the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any other detrimental effects are observed.

401-3.05  ROLLERS.  Rollers shall be of the steel wheel and pneumatic tire type, self-propelled, in good condition, capable of reversing without backlash, and operated at speeds slow enough to avoid displacement of the mixture.  The number and weight of the rollers shall be sufficient to compact the mixture to the required density and surface smoothness while it is still in a workable condition, and be capable of maintaining the pace of the paving operation.  Specific roller requirements for construction of density "control strips" are further described in Subsection 401-3.12, Compaction.  The use of equipment which results in crushing of the aggregate will not be permitted.

401-3.06  PREPARATION OF EXISTING SURFACE.  When the surface of the existing pavement or old base is irregular, it shall be brought to uniform grade and cross section, as directed.

If determined necessary, the existing surface shall be cleaned of loose material by means of sweeping with a power broom, supplemented by hand sweeping as required.

Contact surfaces of curbing, gutters, manholes, and other structures shall be coated with a thin, uniform coating of prime or tack coat material prior to the asphalt concrete mixture being placed against them.

Surfaces which have received a prime or tack coat shall be allowed to cure, as directed, prior to placement of asphalt concrete mixture.  Surfaces which have received an emulsion tack coat shall be allowed to break prior to placement of asphalt concrete mixtures.

401-3.07  PREPARATION OF ASPHALT CEMENT.  A continuous supply of asphalt cement shall be supplied to the mixer at a uniform temperature, within 25 degrees Fahrenheit of the Job Mix Design mixing temperature.

401-3.08  PREPARATION OF AGGREGATES.  The aggregate for the mixture shall be heated and dried to a temperature compatible with the mix requirements herein specified.  Flames used for drying and heating shall be properly adjusted to avoid damage to the aggregate and to avoid soot or unburned fuel on the aggregate.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5 percent (by total weight of mix), as determined by ATM T-25.

401-3.09  MIXING.  The aggregate and asphalt cement shall be combined in the mixer in the amounts required to meet the Job Mix Design.  Anti-stripping additive shall be furnished as required.

The materials shall be mixed until a complete and uniform coating of the particles and a thorough distribution of the asphalt cement throughout the aggregate is obtained.  For batch plants, dry aggregate shall be in motion prior to the addition of asphalt cement.  Wet mixing time shall be determined for each plant and for each type of aggregate used.  The minimum percent of coated particles used to establish the mixing time interval shall be 98 percent using AASHTO T 195.

The temperature of the mixture at the time of mixing shall be as determined by the Job Mix Design.

401-3.10  TEMPORARY STORAGE OF ASPHALT MIXTURE.  Temporary storing or holding of hot mixture in silo type storage bins will be permitted.

All the mixture drawn from the silo type storage bins shall conform to all of the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

401-3.11  SPREADING AND FINISHING.  The mixture shall be laid only upon stable surfaces approved by the Engineer, spread and struck off and compacted to the required thickness.  Asphalt pavers shall be used to distribute the mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 401-3.13, Joints.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impractical, the mixture shall be spread, raked and luted by hand tools.  For such areas the mixture shall be placed to the required compacted thickness.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge drop-off.  When the pavement edge drop-off exceeds 2 inches, shoulder material shall be placed against the pavement edge.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that segment, as defined by the Paving Plan, have been placed and accepted.

Paving shall not begin until all adjacent concrete curb has been poured and cured for 72 hours or until satisfactory concrete strength is achieved.

Asphalt to be placed over bridge membranes shall not be placed until the membrane has cured to the proper state to prevent damage by the overlaying operation.  Vehicles, except the spreader and trucks used for hauling the asphalt overlay mix, shall not be operated on the membrane.  Paving machines used over the membrane waterproofing shall be rubber tired or rubber tracked.   The Contractor shall adhere to the manufacturer's published minimum and maximum temperature limitations for asphalt overlay material.  Steel-wheeled rollers only shall be used to compact the asphalt paving on the bridge decks.  The use of vibratory rollers, with vibrator on, will not be permitted.

401-3.12  COMPACTION.

General.  Immediately after the mixture has been spread, struck off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.  Rolling shall commence as soon as the rolling does not cause undue displacement, cracking or shoving.  Any displacement occurring as a result of the reversing of the direction of a roller, or from other causes, shall be corrected promptly by the use of rakes and addition of fresh mixture when required.  Care shall be exercised in rolling not to displace the line and grade of the mixture.  Rollers shall move at a slow but uniform speed with the drive roll or wheels nearest the paver.

Unless otherwise directed, rolling shall begin at the sides and proceed parallel with the road centerline, each overlapping one-half the roller width, gradually progressing to the crown of the road.  When paving in echelon or abutting a previously placed lane, the longitudinal joint shall be rolled first to provide pinching the material in place.  On super-elevated curves the rolling shall begin at the low side and progress to the high side by overlapping of trips parallel with the centerline.

Along forms, curbs, headers, walls, and other places not accessible to the rollers, the mixture shall be thoroughly compacted with hot hand tampers or with mechanical tampers.  On depressed areas, a trench roller may be used or cleated compression strips may be used under the roller to transmit compression to the depressed area.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

Control by Acceptance Strip.

1.	Control Strips.  A control strip shall be constructed at the start of each course after the plant and equipment are providing a consistent mix, and repeated as ordered whenever:

a.	there is a change in the mix composition,

b.	routine tests indicate changes from results found in previous qualifying control strips,

c.	there is a change in pavement thickness, or

d.	there is a change in the underlying material.

Each control strip shall be constructed with the approved Job Mix Design.  The control strip shall remain in place as a section of the completed work, provided it complies with requirements for gradations, asphalt cement content, adequacy of mixing and line and grade.  It shall be removed and replaced at the Contractor's expense or accepted to remain in place in accordance with Section 105-1.03, Conformity with Plans and Specifications, and a new control strip constructed if it does not meet specification requirements.  Paving operations may not proceed beyond the control strip until the mixture conformance to specifications has been confirmed and production paving is authorized.

Each control strip shall be one lane in width, 300 feet in length and shall be of the depth specified for the pavement course concerned.

Initial or breakdown compaction of a layer of the mixture shall be performed with a 2-axle tandem or a 3-wheel roller weighing at least 12 tons except that approved vibratory compacting equipment may be used for the initial or breakdown compaction if it is operated according to the procedures designated in the approval.

A pass shall be one movement of a roller in either direction.  A coverage shall be as many passes as are necessary to cover the entire width being paved.  Each coverage shall be completed before subsequent coverages are started.

The initial or breakdown compaction shall be followed immediately by intermediate rolling with a pneumatic-tired roller which exerts a tire pressure of at least 80 psi over the tire contact area.  Coverages with a pneumatic-tired roller shall start when the temperature of the mixture is high as practicable and shall be completed while the temperature of the mixture is at or above 160 degrees F.  Intermediate rolling shall be performed with a 2-axle tandem roller when breakdown rolling is performed with a pneumatic roller.

Each layer of mixture shall be additionally compacted, without delay, by a final rolling consisting of not less than one coverage with a steel-tired roller weighing not less than 8 tons.  Compaction of the control strip shall commence as soon as possible after placement of the mixture and be continuous and uniform over the entire control strip.

The following rolling and density testing procedures shall be used on the control strip:

a.	Breakdown rolling.  Fifteen-second minimum nuclear density counts shall be taken at three randomly selected locations after each roller coverage at each test site.  Rolling shall continue until there is less than two pound increase in average density per roller coverage.

b.	Intermediate rolling.  Rolling shall continue until at least three complete coverages have been made.

c.	Finish rolling.  Fifteen-second minimum nuclear density counts shall be taken at three randomly selected locations after each roller coverage at each test site.  The average density obtained after the first coverage shall be taken as a new beginning point.  Final rolling shall continue until all roller marks are removed and there is less than two pound increase in average density per roller coverage.

d.	Density standard.  One-minute density counts shall be taken at 10 randomly selected locations to determine the average density of the control strip.  This is the density standard for the project until a new control strip is constructed.  To confirm the adequacy of the compaction of the control strip, the Contractor shall take seven six-inch minimum diameter core samples will be taken at randomly selected locations.  The average density of these cores, as determined by ATM T-18, shall be at least 95 percent of the maximum specific gravity (as determined by AASHTO T 209) multiplied by 62.4.

2.	Acceptance Strips.  Acceptance density testing will be accomplished while the pavement is hot enough to permit further densification if such is shown to be necessary.

The pavement courses shall be divided into acceptance strips consisting of not more than 500 tons for the purpose of defining areas represented by each series of density acceptance tests.

The types of rollers used and their relative positions in acceptance strip compaction shall be the Contractor's option, provided that at least 3 coverages of a pneumatic-tired roller having an 80 psi minimum contact pressure are applied.

The density of each acceptance strip will be evaluated based on the results of three tests with a portable nuclear test device performed at randomly selected sites within the acceptance section.  Each test will consist of the average of two one-minute readings with the gauge rotated 90 degrees between readings.  The average density obtained for the three test in each acceptance strip shall be at least 98 percent of the mean density obtained in the approved control strip.  In addition, each individual test value obtained within an acceptance strip shall be at least 95 percent of the mean density of the control strip.

If either the average density of the acceptance strip or an individual test value does not meet the density requirements, the Contractor shall continue compactive effort until the required density is obtained.

After the required density has been attained in the acceptance strips, further finish rolling may be necessary to remove roller marks or other surface irregularities and to meet the required surface tolerances.

401-3.13  JOINTS.  Joints shall be made in such manner as to ensure a continuous bond between old and new sections of the course.  All joints shall present the same texture and smoothness as other sections of the course.

A thin tack coat of asphalt cement or emulsion shall be sprayed on all cold joints and allowed to break prior to placing fresh mixture against the joint.

Transverse joints shall be formed by cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.

The longitudinal joints in one layer shall offset those in the layer immediately below by approximately six inches.  However, the joints in the top layer shall be at centerline or lane lines.  Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset not more than one foot.

Pavement that are 1.5 inches or thicker shall be constructed with a modified wedge joint the entire length of the face of the exposed longitudinal joint between adjacent travel lanes.  The taper shall have a maximum horizontal to vertical slope of 3:1 at the bottom and shall be vertical at the top for a height equal to the largest aggregate size.

Improperly formed joints resulting in surface irregularities shall be removed, full depth, replaced with new material, and thoroughly compacted.  Attempting to roll out an improper joint after the material has cooled below 160 degrees Fahrenheit shall not be allowed.  All pavement removal shall be precut to a neat line using a power driven saw.

401-3.14  SURFACE TOLERANCE.  The surface will be tested after final rolling at selected locations using a 10 foot straightedge.  The variation of the surface from the testing edge of the straightedge between any two contacts with the surface shall not exceed 3/16 inch.

401-3.15  PATCHING DEFECTIVE AREAS.  Skin patching will not be permitted.  Defective materials shall be removed for the full thickness of the course.  The pavement shall be cut so that the sides are perpendicular and parallel to the direction of traffic and so that the edges are vertical.  Edges shall be tack coated with asphalt cement or emulsion.  Fresh mixture shall be placed in sufficient quantity so that the finished surface will conform to grade and smoothness requirements.  The mixture shall be compacted to the density specified herein.

401-4.01  METHOD OF MEASUREMENT.  Asphalt concrete pavement and asphalt cement will be measured by the ton or by the square yard in accordance with Section 109.  The tonnage used shall be the weight used in the accepted pavement and no deduction will be made for the weight of asphalt cement and anti-stripping additive in the mixture.

The method of measurement to be used for Asphalt Cement will be limited to one of the following procedures.  The Engineer shall approve in writing the procedure to be used.  The method used initially must be the one used for the duration of the project.

1.	Supplier's invoices minus waste, diversion and left-over.  This method may be used on projects where deliveries are made in tankers and the plant is producing material for one project only.  Tank stickings will be used to compute left-over.  Waste and diversion will be computed in a manner to be determined by the Engineer.

2.	The weight of asphalt cement shall be calculated using the percent of asphalt cement multiplied by the total tonnage represented.  Percent of asphalt cement shall be determined by ATM T-23.

The Engineer may direct at any time that tankers shall be weighed before and after unloading in the presence of the Engineer.  If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

401-5.01  BASIS OF PAYMENT.  The accepted quantity will be paid for at the contract unit price for the pay item listed below, complete in place.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $4.50 per 0.25 percent additive per ton of asphalt cement.

Special Provisions

A change order/directive is not required for anti-stripping additive.  The approved mix design will initiate Item 401(4), Anti-Stripping Additive at the prescribed rate.  (5/3/93)R169

Asphalt for tack coat will not be paid for separately, but will be subsidiary to Item 401(1), Asphalt Concrete Pavement.

Standard Modifications

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1)	Asphalt Concrete Pavement, Type __, Class __	Ton

401(2)	____ Asphalt Cement	Ton

401(4)	Anti-Stripping Additive	Contingent

Sum

(7/16/93)M61

SECTION 402

TACK COAT

Special Provisions

402-2.01  ASPHALT MATERIAL.  Delete "CSS-1" and substitute "STE-1".

402-3.04  DILUTION OF ASPHALT MATERIAL.  Delete this subsection in its entirety.

402-3.05  APPLICATION OF ASPHALT MATERIAL.  Modify the application rate given in the first paragraph from "0.05 to 0.10 gallons" to "0.02 to 0.10 gallons".

402-4.01    METHOD OF MEASUREMENT.  Replace with the following:  Asphalt for tack coat will not be measured for payment.

402-5.01  BASIS OF PAYMENT.   Delete this Subsection in its entirety and replace with the following:  Asphalt for tack coat will not be paid for separately, but will be subsidiary to work performed under Section 401.

(2/26/93)R33

SECTION 501

STRUCTURAL CONCRETE

Standard Modifications

501-3.01  PROPORTIONING.  Under Item 1., Determining the Proportions and Batch Weights, add the following to the second paragraph:  Material properties shall be determined in accordance with the following test methods:

| Property | Test Method |
| --- | --- |
| Slump | AASHTO T 119 |
| Air Content | ATM T-8 |
| Compressive Strength | AASHTO T 22 |
| Unit Weight | AASHTO T 121 |
| Cement Content | AASHTO T 121 |

(7/2/93)M51

Special Provisions

501-3.01  PROPORTIONING.  Revise this subsection as follows:  In Table 501-1 Class of Concrete, under the category Coarse Aggregate Gradation, AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S and W concrete.  (9/1/89)R37

501-3.02  BATCHING.  Add the following to item No. 5, Batching:  Furnish the mix design number and a list of all ingredients, their individual weights, moisture contents of the various aggregates and the individual truck water meter reading when batched, with each truck load or batch of concrete supplied.  (7/2/93)S54

501-3.06  PLACING CONCRETE.  Replace the last sentence of Item 2. Pumping Concrete with the following:  Concrete samples for testing shall be taken at the discharge end of the pipe.  The Contractor shall provide the necessary samples of concrete as directed.  (7/2/93)S65

SECTION 504

STEEL STRUCTURES

Special Provisions

504-1.01   DESCRIPTION.  Add the following:  This work shall include furnishing, fabricating and installing new members and connecting to existing members to form a steel pedestrian walkway and supports on existing steel girders of the South Channel Bridge, No. 1386.  This work shall also include furnishing, fabricating and installing new thrie beam transition brackets on the South Channel Bridge, No. 1386 and the Iliuliuk River Bridge, No. 1407.

Standard Modifications

504-3.01  FABRICATION.  Under item 7. Bolted Connections, High Tensile Strength Bolts,  delete paragraphs 5 through 14, and Table 504-3 and substitute the following:  All fasteners shall be tightened to give at least the required minimum tension values shown in Table 504-2 on completion of the joint.  All bolts and nuts in a connection shall be made by the same manufacturer.

In order to achieve the minimum tension values shown in Table 504-2, Required Bolt Tension, direct load indicating washers, conforming to the requirements of ASTM P959, shall be used.  The suitability of the device shall be demonstrated by testing a representative sample of not less than three devices for each diameter and grade of fastener used in the structure in a calibration device capable of indicating bolt tension.  The test assembly shall include flat, hardened washers, if required in the actual connection, arranged as those in the actual connection to be tensioned.  The calibration test shall demonstrate that the device indicates a tension not less than five percent greater than that required by Table 504-2, Required Bolt Tension.  Manufacturer's installation procedures shall be followed for installation of bolts in the calibration device and in all connections.  Special attention shall be given to proper installation of flat, hardened washers when load indicating devices are used with bolts installed in oversized or slotted holes and when the load indicating devices are used under the turned element.

Unless otherwise permitted, the load indicating device shall be placed under the bolt head, and only the nut shall be turned when tightening the bolt.  The device shall indicate full tensioning of the bolt when the opening reaches zero.

Bolts shall be installed in all holes of the connection and brought to snug tight condition.  All fasteners shall then be tightened, progressing systematically from the most rigid part (usually near the center) of the connection to the free edges, or as directed, in a manner that will minimize relaxation of previously tightened fasteners.  It may be necessary to provide multiple cycles of systematic tightening.

High-strength bolts shall not be reused.  Previously fully-tightened bolts which may have been loosened by the tightening of adjacent bolts shall be removed and replaced with new bolts, nuts, and load indicating devices.

(5/12/89)M18

Special Provisions

504-3.01   FABRICATION.  Delete item no. 8, Welding, and replace with the following:  All shop and field welding shall conform to the requirements of the AASHTO/AWS Bridge Welding Code, D1.5.

Add the following:  9. Steel Grating.  Steel grating shall be a welded rectangular design.  Main bearing bars shall be 1" x 1/8" spaced at 1-3/16" center to center.  Cross bars to be resistance welded at right angles to the bearing bars.  They shall be spaced 4" center to center.  Steel shall be ASTM A569.  No notching or cutting of bearing bars before welding is permissible.  Galvanize after fabrication.  Overall dimensions, details, direction of bearing bars, and cutouts for existing obstructions shall be as shown on the drawings.

SECTION 506

TIMBER STRUCTURES

Special Provisions

506-1.01   DESCRIPTION.  Add the following:  This work shall also consist of removing and disposing of the existing wooden bridge deck as shown on the plans.  All salvaged materials shall become the property of the Contractor.

506-2.01   MATERIALS.  Delete the 5th paragraph and replace with the following:  Pressure treatment preservatives for timber bridges shall be creosote, creosote tar, chromated copper arsenate (CCA), ammoniacal copper zinc arsenate (ACZA), or ammoniacal copper carbonate quaternary ammonium compound (ACQ).  Pentachlorophenol shall not be used.  Minimum net preservative retention shall be 12 pounds per cubic foot for creosote and 0.60 pounds per cubic foot for CCA, ACZA, or ACQ.

506-3.01  CONSTRUCTION REQUIREMENTS.  Add the following:  The removal of the existing deck and replacement with New treated timber shall not occur until the roadway asphalt paving has been completed.

506-4.01  METHOD OF MEASUREMENT.   Add the following:  Removing and disposing of the existing bridge deck will not be measured separately for payment but will be subsidiary to Item 506(1), Treated Timber.

506-5.01   BASIS OF PAYMENT.   Add the following:  Removing and disposing of the existing bridge deck will not be paid for directly but will be subsidiary to the lump sum amount paid for Item 506(1), Treated Timber.

Delete this Section in its entirety and substitute the following:

SECTION 508

MEMBRANE WATERPROOFING

Special Provisions

508-1.01  DESCRIPTION.  This work consists of furnishing and installing membrane waterproofing on the concrete deck of Bridge No. 1407.  The membrane shall cover the entire top deck surface, from beginning to end of the bridge, approximately 40 by 100 feet.

508-2.01  MEMBRANE WATERPROOFING MATERIAL.  Membranes for bridge deck waterproofing shall be a manufactured type membrane as specified herein.

Membrane shall consist of a single or multiple component elastomeric material, shall be a product listed on the Department's Approved Products List, or an approved equal.  Bituthene, Highway and Bridge Membrane, manufactured by W. R. Grace and Company, will not be allowed on this project.  If Polyguard 665 Waterproof Membrane is selected, the Contractor shall comply with the following requirements:

1.	The laydown temperature of the asphalt mix shall be a minimum of 250 degrees Fahrenheit.  Laydown temperature is defined as the temperature of the asphalt mix behind the paver screed.

2.	If a tack coat is recommended by the supplier, a STE-1 or other approved tack coat shall be used.

3.	The manufacturer shall certify that the waterproof membrane will develop a proper bond with a minimum asphalt mix laydown temperature of 250 degrees Fahrenheit.

508-2.02  OVERLAY MATERIALS.  Materials requirements for pavement overlays on waterproof membranes shall conform to those specified in Section 401.

508-3.01  APPLICATION OF MEMBRANE WATERPROOFING.

1.	General.  Membrane waterproofing shall be installed in a manner to assure the following results:

a.	A complete bond between the membrane and the concrete surface of deck and curb face.

b.	An unbroken waterproof membrane in place between the concrete deck surface and the asphalt overlay.

c.	A complete bond between the membrane and the asphalt overlay.

The membranes shall be installed under the supervision of a representative from the membrane manufacturing company and in accordance with the manufacturer's published instructions.

2.	Preparation of Concrete Deck.  All concrete surfaces to receive membranes shall have attained a compressive strength of not less than 80 percent of the ultimate strength (f'c) prior to application of the membrane.

The entire deck shall be free of all foreign materials such as dirt, dust, moisture, loose concrete, etc.  Prior to applying the tack coat, primer or emulsion, all dust and loose material shall be removed from the deck by power sweeping followed by a thorough cleaning with compressed air.  Any sharp concrete edges on the deck surface which would puncture the membrane shall be corrected in a satisfactory manner prior to application of the membrane.  Grease, oil, paint, etc., shall be removed with solvents, detergents or sand blasting on decks that are to receive manufactured membranes.

Additional power sweeping, vacuuming, compressed air cleaning, or hand brooming shall be performed immediately before applying the tack coat, primer or emulsion if deemed necessary by the Engineer.

3.	Weather and Moisture Limitations.  Membranes shall be applied in accordance with the manufacturers representative.

4.	Overlaying and Protection of Membrane.  The asphalt overlay shall be performed in accordance with the requirements of subsection 401-3.11 Spreading and Finishing.

508-4.01  METHOD OF MEASUREMENT.  Membrane waterproofing will not be measured for payment.

All materials for the asphalt overlay will be included in the measurements of quantities for the appropriate paving items.

No adjustments will be made in the quantities or prices of materials for asphalt overlay because of any variations resulting from utilizing waterproof membranes of greater or lesser thickness.

508-5.01  BASIS OF PAYMENT.  Waterproof membrane will not be paid for separately, but will be subsidiary to other bridge work.

Payment for the asphalt overlay will be made under the appropriate paving items.

Add the following Section:

SECTION 510

STEEL BIN RETAINING WALLS

Special Provisions

510-1.01  DESCRIPTION.  This item shall consist of furnishing and installing steel bin walls in reasonably close conformity with the lines, grades, and dimensions shown on the plans or as established by the Engineer.

General design criteria for the bin wall structure, such as location and elevations shall be as shown on the plans.  Design details for the wall shall conform to one of the following manufactured systems or an approved equivalent:

1.	"Steelbin Retaining Wall", as manufactured by the Syro Steel Company.  For information concerning this product, contact:

Syro Steel Company

P.O. Box 99

Centerville, Utah  84014

Phone:  (801) 292-4461

2.	"Bin-Type Retaining Wall, Type 1", as manufactured by the Contech Construction Products Company.  For information concerning this product, contact:

Contech Construction Products Inc.

1409 - 140th Place N.E., Suite 101

Bellevue, Washington  98007

Phone:  (206) 641-3328

The Contractor shall make his own arrangements to purchase or manufacture all of the necessary components.

510-1.02  SUBMITTALS.  The Contractor shall submit complete working drawings for the wall system in accordance with the provisions in Subsection 105-1.02, Plans and Working Drawings.  The working drawings shall contain all information required for the proper construction of the wall system.  The Contractor shall allow the Engineer two weeks to review the drawings after a complete set has been received.

The Contractor shall submit a Manufacturer's Certificate of Compliance in accordance with the provisions in Subsection 106-1.05, Certificate of Compliance, for all materials to be placed under Item 510(5), Steel Bin Walls.  Submittals shall also include Manufacturer's installation instructions for the application shown on the plans.

510-2.01  MATERIALS.  The steel bin walls shall consist of a series of rectangular cells composed of galvanized steel members.  They shall conform to the materials requirements of ASTM A444.  Fasteners for the bin walls shall conform to ASTM A307 and shall be galvanized in accordance with ASTM A153.

510-3.01  CONSTRUCTION REQUIREMENTS.

1.	Design Details.  The plans show type, location and details of the bin walls.

2.	Fabrication Requirements.  All bin members shall be fabricated so that members of the same nominal size shall be interchangeable.  Drilling, punching, or drifting bolt holes to correct defects in fabricating will not be permitted.  Any members twisted, bent, or with holes improperly located shall be replaced by the Contractor at his expense.

3.	Excavation and Backfill.  Excavation and backfill shall be performed in accordance with Section 205.

4.	Finishing.  The bin walls shall be galvanized.

510-4.01  METHOD OF MEASUREMENT.  Steel bin walls will be measured for payment by the square foot.  The measurement will be along the outer face for the height from the bottom of the base plate to the top of the top stringer and for a length measured from end to end of each section of wall.  Excavation and backfill, concrete and reinforcing steel, and temporary shoring will not be measured separately for payment.

510-5.01  BASIS OF PAYMENT.  The contract price paid per square foot for steel bin walls shall be full compensation for furnishing all labor, materials, tools, equipment and incidentals, and for doing all the work involved in construction of the bin walls, complete in place.

Temporary shoring will not be paid for directly, but will be subsidiary to Item 510(5), Steel Bin Walls.

Excavation and backfill will not be paid for separately but will be subsidiary to Item 510(5), Steel Bin Walls.

Concrete and associated reinforcing steel included or partially contained within the limits of the bin walls (except concrete associated with fencing) will not be paid for directly, but will be subsidiary to Item 510(5) Steel Bin Walls.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

510(5)	Steel Bin Walls	Square Foot

(9/20/93)R123

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-1.01  DESCRIPTION.  Add the following:  This work shall also consist of installing culvert marker posts.

603-2.01  MATERIALS.  Add the following to the list of materials:

Corrugated Polyethylene Pipe				706-2.07

In the second paragraph, add "Corrugated Polyethylene Pipe (24 inch maximum diameter for storm drain systems)" to the list of options allowed under Item 603(17).

Add the following to the last paragraph:  Heights of cover for corrugated polyethylene pipe shall be the same as for aluminum culvert pipe.

(5/7/91)S55

Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts.  The color shall be blue with no other markings.  The 3-¾ inch by 72 inch post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

603-3.04  JOINING PIPE.  Add the following paragraph:  Polyethylene pipe couplings shall be corrugated to match the pipe corrugations and their width shall not be less than one half the nominal pipe diameter.

603-3.06  CULVERT MARKER POSTS.  Add the following subsection:  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two inches of post shall remain above the ground after driving.

603-3.07  CONNECTIONS TO EXISTING PIPES.  Add the following subsection:  When new end sections or pipes are to be attached to existing pipes, the existing pipe ends shall be rehabilitated as necessary to obtain a good fit

between the pipe end and the end section or new pipe section.  The rehabilitation effort shall include the following:

1.	Cleaning the existing pipes (removing debris, sediment, etc.).

2.	Excavating an area adequate to install the new end section and expose the pipe end.

3.	Straighten the existing pipe ends by jacking or other means.

4.	Cutting off a segment of the existing pipes, if necessary.

603-4.01  METHOD OF MEASUREMENT.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01  BASIS OF PAYMENT.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to the pipe item.

The CMP outlet baffle will not be measured for payment, but will be subsidiary to Item 603(17-18), 18-Inch Pipe.

Connections to existing pipes will not be paid for separately, but will be subsidiary to the pipe item.

Excavation for pipe P3-3 will encounter rock.  Rock excavation at this location will not be paid for separately, but will be subsidiary to the pipe item.

Insulation board, where called for on the plans, will not be paid for separately, but will be subsidiary to pipe items.

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-1.01  DESCRIPTION.  Add the following:  This work shall include construction of cleanout structures and construction of a petroleum separator in  conformance with the plans.

Standard Modifications

604-2.01  MATERIALS.  Add the following to the list of materials:

Flexible Watertight Gaskets				705-2.05

(7/2/93)M52

Special Provisions

604-3.01  CONSTRUCTION REQUIREMENTS.  Add the following to the beginning of the second paragraph.  All access manholes, regardless of type, that fall within a concrete sidewalk or asphalt pathway shall be constructed with a frame and cover cast with a rough cobbled grit surface, or specifically designed to hold fill.  The recessed covers shall be depressed a minimum of 1-inch, and be suitable for concrete or asphalt fill, as applicable.

Add the following to the fifth paragraph referencing the reconstruction of manholes:

5.	The work necessary to rotate the cone or reducing slab to align the manhole or inlet casting as detailed on the plans.  To align the access stairs, the Contractor will have the option of rotating the barrel sections or installing new steps.

6.	The work and materials necessary to salvage the frame and grate, to remove and dispose the reducing slab and adjusting rings, and to install a new cover slab (reducing slab without an access hole).

Add the following:  Those manholes which by design must fall within the paved roadway surface shall be aligned such that the casting will not be in the wheel tracks of any driving lane, or the flow line of the gutter pan.

When new pipe is installed in an existing manhole, a hole shall be cleanly cut by approved means at the invert elevation given on the plans and 2 inches larger than the outside diameter of the new pipe.  The joint shall then be grouted with non-shrinking cement mortar.

All curb inlet structures shall have a 3-inch formed hole approximately 2 feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  The Contractor shall be responsible for keeping the openings functional, which may require temporary dikes, RMC extensions, etc., as necessary.  These holes shall be filled with grout upon final paving.

Standard drainage structure steps shall be cast during structure pour or installed before concrete hardens.

Construction of the petroleum separator shall be as shown on the plans.  All components shall meet the respective specification requirements for the portion of work involved.

Prior to backfill, manhole exteriors shall be coated with a waterproof, bitumastic coating.

604-4.01  METHOD OF MEASUREMENT.  Add the following:  Frames, grates and lids will not be measured for payment.

All materials, labor, and equipment required to construct the petroleum separator, as shown on the plans, will not be measured separately for payment but will be measured as a single storm drain manhole.

604-5.01  BASIS OF PAYMENT.  Add the following:  Frames, grates and lids are subsidiary to the drainage structure.

The completed petroleum separator will be paid for as a single storm drain manhole under Item 604(1) at the unit price bid for that item.  Payment shall be full compensation for the manhole grate, corrugated metal tee, Class I riprap, and all other components required to complete the unit accepted in place.

Delete Item 604(1) Storm Sewer Manhole and add the following new pay item:

Pay Item No.	Pay Item	Pay Unit

604(1)	Storm Drain Manhole	Each

SECTION 606

GUARDRAIL

Special Provisions

606-1.01  DESCRIPTION.  Add the following:  This work shall also consist of installing breakaway cable terminals, controlled release terminals, and guardrail/bridgerail connections at the locations shown on the plans.

606-2.01  MATERIALS.  Add the following:  Flexible markers shall have yellow reflective sheeting and be one of the following types or equivalent:

1.	"Guardrail Delineator Post" manufactured by Carsonite International, 2900 Lockheed Way, Carson City, Nevada 89701.

2.	"Guardrail Delineator" manufactured by Safe-Hit Corporation, 1930 West Winton Avenue, Building 11, Hayward, California 94545.

3.	"Flex-o-Guide", Model EY426 manufactured by Flexible Safety Zoning Company, 4152 Warren Avenue, Hillside, Illinois 60162.

606-3.01  POSTS.  Add the following:  The foundation type for the breakaway cable terminal posts shall be the steel post embedment for soil or concrete as shown on Standard Drawing G-18.S.

606-3.02  RAIL ELEMENTS.  Add the following:  Guardrail elements shall be factory bent for all radii less than 75 feet.

606-3.03  REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following:  Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.  Traffic control devices shall be placed as required by Section 643.

606-3.06  FLEXIBLE MARKERS.  Add the following subsection:  For each breakaway cable terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.  The flexible markers shall have a minimum of 21-inches of marker extending above the top of the guardrail.  The reflective tape shall face the nearest oncoming traffic.

606-3.07  EMBANKMENT WIDENING.  Add the following subsection:  Embankment widening for guardrail end treatments shall be constructed of selected material, Type B in accordance with Section 203.

606-3.08  LENGTH OF NEED VERIFICATION.  Add the following subsection:  After shaping the slopes and staking all proposed guardrail locations, the Contractor shall notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine that additional guardrail is necessary, and the Contractor shall comply without delay.

606-4.01  METHOD OF MEASUREMENT.  Delete the third paragraph and replace with the following:  Breakaway cable terminals will be measured per each installation which shall include all labor, equipment and materials.  Materials include the anchor cable assembly, terminal posts, terminal end, flexible marker, and all associated hardware.  Rail elements, standard posts, and blocking will be measured and paid under Item 606(1), W-Beam Guardrail.

Controlled Release Terminals shall be measured per each installation which consists of all materials from the terminal end to and including the breakaway cable terminal anchor cable assembly, terminal posts and associated hardware.

Guardrail/bridge rail connections shall be measured per each installation which shall include a section of nested thrie beam guardrail, thrie beam to standard W-beam transition, thrie beam transition bracket, posts and all associated hardware.

606-5.01  BASIS OF PAYMENT.  Add the following:  Selected material, Type A will be measured and paid in accordance with Section 203.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

606(8)	Breakaway Cable Terminal	Each

606(9)	Controlled Release Terminal	Each

606(12)	Guardrail/Bridgerail Connection	Each

SECTION 607

FENCES

Special Provisions

607-1.01  DESCRIPTION.    Add the following to the last paragraph:  Chain-link fence for the bridge rail section shall consist of chain-link fabric attached to metal posts and fastened to top and bottom rails as shown on the plans.

SECTION 608

SIDEWALKS

Special Provisions

608-2.01  MATERIALS.  Add the following:  PBA-2 asphalt cement shall be used in the asphalt concrete pavement mix for asphalt sidewalks, and shall conform to the requirements of subsection 702-2.01, Asphalt Cements.  Aggregate shall meet the gradation requirements of subsection 703-2.04, Aggregate for Plant Mix Asphalt Pavement, for Asphalt Concrete Type II.  In addition, the asphalt concrete shall conform to the following:

Marshall Stability, pounds, minimum	1000 lbs

Voids, Total Mix, percent	2-5 %

Compaction Blows per Side	50

608-4.01  METHOD OF MEASUREMENT.  Add the following:  Asphalt concrete for sidewalk paving will be measured by the ton in accordance with Section 109, Measurement and Payment.  Asphalt cement will not be measured for payment.

608-5.01  BASIS OF PAYMENT.  Add the following:  Asphalt cement will not be paid for separately, but will be subsidiary to Item 608(2), Asphalt Sidewalk.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

(10/22/92)R165

SECTION 609

CURBING

Standard Modifications

609-2.01  MATERIALS.  Replace paragraph 2 with the following:  Concrete shall conform to Section 501, Structural Concrete, Class A, except that the slump shall be less than 2 inches for concrete placed by the extrusion or slip-form process.  (7/2/93)M53

SECTION 611

RIPRAP

Special Provisions

611-1.01  DESCRIPTION.  Add the following:  This work shall also consist of furnishing and placing armor stone as shown on the plans.  Armor stone shall be considered a class of riprap with placement, measurement, and payment accomplished accordingly.

611-2.01  MATERIALS.  Add the following:

5.	Armor Stone.  One hundred percent by total stone count shall weigh less than 4000 pounds and  30 to 50 percent by total stone count shall weigh less than 3000 pounds.  No stones shall weigh less than 2000 pounds.

Riprap and armor stone shall have a bulk specific gravity of 2.65 minimum, as determined by AASHTO T 85.  In addition, armor stone shall meet the following requirements:

Abrasion (LA)	ASTM C535	10% Max Loss after 200 revs.

and 50% Max after 1000 revs.

Soundness (Sodium Sulfate)	AASHTO T 104	5% Max. Loss (5 cycles)

Degradation	ATM T 13	45 Min.

Absorption	AASHTO T 85	2% Max.

Solubility & Durability	COE CRD-C-148	2% Max.

(Ethylene-Glycol)

611-3.01  CONSTRUCTION REQUIREMENTS.  Add the following:  The outermost layer of armor stone shall be placed so that the long axis of stones are perpendicular to the slope.

611-5.01  BASIS OF PAYMENT.  Add the following:  Riprap geotextile will not be paid for separately, but will be subsidiary to Item 611(6), Armor Stone.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

611(6)	Armor Stone	   Ton

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01  MATERIALS.  Add the following to the end of the first sentence of the fifth paragraph:  "and the Alaska Traffic Manual."

Delete paragraphs 7 and 8 (the fourth and fifth paragraphs on page 315) and substitute the following:  Sign posts and bases shall be of the types specified.  Structural aspects of design and materials for sign supports shall comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals.

Concrete for steel-reinforced slip base and breakaway base foundations shall be Class A, conforming to the requirements of Section 501, Structural Concrete.  Concrete for other sign foundations may be Class W.

(5/7/91)S42

Add the following:  Wide flange posts shall also be hinged and equipped with the multi-directional breakaway load concentration coupler hinge plates.

615-3.01  CONSTRUCTION REQUIREMENTS.  Add the following to the sixth paragraph:  When existing signs are to be salvaged the remaining foundation shall be removed, abandoned in place, or if located within the roadway structural section shall be disposed of in a manner as approved by the Engineer.  If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than one foot below roadway subgrade or unimproved ground, whichever applies.  All signs and posts at a single installation shall be considered as one unit.

Add the following after the sixth paragraph:  Salvaged sign panels shall be delivered to the State Maintenance Yard in Unalaska.

615-3.02  SIGN PLACEMENT AND INSTALLATION.  Add the following:  Existing signs shall not be removed without authorization from the Engineer.  They shall be kept in service until either the new signs have been installed, or they are no longer needed.  As the work progresses, if their locations do not conform to Standard Drawing S-05, they shall be reinstalled at locations approved by the Engineer.

Prior to mounting the sign panel, the Contractor shall mark the date of installation on the back of the sign.  Installation dates shall be written in the format of month/day/year, using black permanent marker, with numbers a minimum of 3 inches in height, so as to be readable from the roadside after installation.

615-4.01  METHOD OF MEASUREMENT.  Add the following to the second paragraph: Concrete used for sign bases will be considered subsidiary to other work under this section and will not be measured for payment.

615-5.01   BASIS OF PAYMENT.  Add the following:   Payment for keeping existing signs in service until they are no longer needed, or temporarily relocating existing signs, will not be paid for directly, but will be subsidiary to Item 615(1), Standard Signs.

Salvaging existing signs and removal or abandonment of foundations will not be paid for directly, but will be subsidiary to Item 615(1), Standard Signs.

(2/14/92)R50

SECTION 618

SEEDING

Special Provisions

618-1.01  DESCRIPTION.  Delete this subsection and substitute the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be seeded.  This work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01  MATERIALS.  Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01  SOIL PREPARATION.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach on the wetlands.

618-3.03  APPLICATION METHOD.  In the first sentence of subparagraph b., under numbered paragraph 1. Hydraulic Method, delete the following:  "Item 619(1),".

Add the following:  Seed, mulch and fertilizer shall be applied as follows per 1,000 square feet.  If the hydraulic method for seed and mulch is used, it shall

be made in one application.  All fertilizer shall be applied by the hydraulic method.

| Item | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed Mix | Boreal Red Fescue Kentucky Bluegrass (Nugget) Bering Hairgrass (Norcoast) | 0.50 lbs. 0.30 lbs. 0.20 lbs. Total= 1.00 lbs. |
| Mulch | -- | 35.0 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

The Contractor shall not remove the required tags from the seed bags.

618-4.01  METHOD OF MEASUREMENT.  Delete the second paragraph and substitute the following:  Seeding by the pound will be the number of pounds of seed (dry measure) accepted in place.  The amount of fertilizer, mulch and water for application used in this work, including any required reseeding, will be subsidiary to this item and will not be measured separately for payment.

Delete the last paragraph.

618-5.01  BASIS OF PAYMENT.  Add the following:  Fertilizer, mulch and water for application, including any required reseeding, will not be paid for directly, but will be subsidiary to seeding.

The work described under subsection 618-3.01 Soil Preparation will not be paid for directly but will be subsidiary to seeding.

Water required for the hydraulic method of application will not be paid for separately, but will be subsidiary to seeding.

(10/1/91)R52

SECTION 627

WATER SYSTEM

Special Provisions

627-3.05.  Add the following:  It shall be the Contractor's responsibility to protect and maintain all fire valves and valves boxes in an operable condition during all phases of construction.

The Contractor shall schedule a field inspection with a representative of the City of Unalaska Public Works Department and the Engineer to witness and document the condition of the existing valve and valve box prior to beginning work on the project or adjustment.  The Contractor shall provide the City's representative 48 hours advance written notice of the scheduled field inspection and provide the Engineer with a copy.

The City's representative shall locate and inspect the existing valve and valve box to insure it is in working order.  Cleaning or repair to the valve or valve box prior to adjustment will be accomplished by the City of Unalaska at no cost to the Contractor.

Failure of the Contractor to schedule and participate in the valve and valve box inspection shall result in the Contractor forfeiting all rights to claim that the valves were damaged prior to his beginning work.

If the City's representative finds a valve or valve box damaged or otherwise rendered inoperable at any time after the inspection as described above, the Contractor shall repair the damage at his expense.

The Contractor shall schedule a final field review with the City's Representative and the Engineer upon completion of the valve box adjustment.

627-4.01  METHOD OF MEASUREMENT.  Add the following:

6.	Adjustment of Valve Box.  Measurement will be the number of valve boxes adjusted for final grade only.

(9/22/93)R181

SECTION 635

INSULATION BOARD

Special Provisions

635-1.01  DESCRIPTION.  Add the following:  Insulation will be placed between a storm drain and a sanitary sewer or waterline where designated on the plans.  This work will also consist of placing a sand blanket bedding under and over the horizontal insulation boards.

635-2.01  MATERIALS.  Add the following:  The insulation board shall be rigid, homogeneous, and essentially unicellular, and shall conform to the following:

| PROPERTY | STANDARD | VALUE |
| --- | --- | --- |
| Compression Strength, Min., @ Yield, or 5% Compression | AASHTO M230 | 35 psi |
| Water Absorption Max. % by Volume | AASHTO M230 | .25% |
| Thermal Resistance R-value @ 75F F-SF-Hr/BTU | ASTM C177 | 17 |

Sand blanket material shall contain no muck, frozen material, roots, sod, or other deleterious material.  It shall have a plastic index not greater than 6 as determined by AASHTO T-89 and T-90.  Grading, as determined by Alaska T-7 will be as follows:

| Sieve Designation | Percent Passing by Weight |
| --- | --- |
| _-inch | 100 |
| No. 4 | 95-100 |
| No. 200 | 0-6 |

635-3.01  CONSTRUCTION REQUIREMENTS.  Delete the second paragraph and substitute the following:  The horizontal insulation board shall be laid on a sand leveling course, and covered with sand blanket material, spread and compacted to a depth of 4-inches prior to the placing of subsequent lifts.  Spreading and compacting equipment shall be approved by the Engineer.

635-4.01  METHOD OF MEASUREMENT.  Add the following:  Insulation board, sand blanket, and leveling course will not be measured for payment, but will be subsidiary to other items of work.

635-5.01  BASIS OF PAYMENT. Add the following:  Insulation board, sand blanket, and leveling course will not be paid for separately, but will be subsidiary to Item 603(17-18), 18-inch Pipe.

(10/1/91)R57

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01 DESCRIPTION.  Add the following:  This work includes the construction of public approaches at locations shown on the plans.

639-1.02  CONSTRUCTION REQUIREMENTS.  Add the following subsection:  Placement of materials used in driveways and public approaches shall meet the requirements specified as follows:

Selected Material, Type B		Section 203

Crushed Aggregate Base Course	Section 301

Asphalt Concrete, Type II, Class B	Section 401

639-2.01  METHOD OF MEASUREMENT.  Add the following:  Public approaches will be measured per each constructed as shown on the plans, or as directed.

639-3.01  BASIS OF PAYMENT.  Add the following:  Payment for public approaches will be full compensation for furnishing all equipment and labor necessary to complete the work as indicated.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

639(3)	Public Approach	Each

Delete the last sentence and substitute the following:  Crushed Aggregate Base Course and Asphalt Concrete Type II required to construct driveways and public approaches will be paid for separately under the respective items listed in the bid schedule.  Material meeting the minimum requirements of Selected Material, Type B will not be paid for directly, but will be considered subsidiary to Item 639(3) Public Approach.

(10/1/91)R58

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-2.01  METHOD OF MEASUREMENT.  Delete item 3. and substitute the following:

3.	When the letter of project completion has been issued and the Contractor has made all the required submittals the remaining balance of the amount for this item will be paid.  (5/7/91)S41

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01  DESCRIPTION.  This work shall consist of planning, providing, and maintaining control of erosion, water pollution, and hazardous materials contamination.

641-1.02  SUBMITTALS.  At the preconstruction conference, the Contractor shall submit for acceptance a plan for accomplishment of temporary and permanent erosion and pollution control measures throughout the life of the contract.  This plan shall, as a minimum, include the following:

1.	Notice of Intent (NOI) to utilize the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska.

2.	Storm Water Pollution Prevention Plan (SWPPP).

3.	Hazardous Material Control Plan (HMCP).

The NOI and SWPPP shall be prepared in accordance with the requirements of the NPDES General Permit for Alaska (General Permit) and the Contractor Guidance for Preparing and Executing Storm Water Pollution Preventions Plans (Storm Water Manual).  When completing the NOI, the Contractor is the "Operator, Discharger, and Permittee" and the Department is the "Owner".

The HMCP is the Contractor's plan for the containment, cleanup, and disposal of waste material, as well as petroleum products or other hazardous substances generated by construction equipment or activities.  A list of quantities and types of equipment and materials available on site to be used for hazardous substance containment and cleanup shall be included.

The Contractor shall mail the NOI to the U.S. Environmental Protection Agency via Certified Mail, and shall send copies to the Engineer and the Alaska Department of Environmental Conservation Stormwater Coordinator.  Earth disturbing work shall not begin until 48 hours after the NOI has been postmarked.

The Contractor shall submit required amendments to the NOI or SWPPP to the Engineer at least 14 days prior to performing work affected by such amendments.

The Contractor shall submit a Notice of Termination (NOT) in accordance with the General Permit to the Engineer following completion of the final stabilization of the project.

641-2.01 CONSTRUCTION REQUIREMENTS.  The Contractor shall comply with all requirements of the NPDES General Permit for Alaska.  The Contractor shall provide the Engineer with a copy of all inspection reports required by the Permit within three days of the inspection date.  Compliance with the NPDES General Permit for Alaska does not reduce the Engineer's authority to direct additional erosion control measures deemed appropriate.

The Contractor shall be responsible for the containment, cleanup, and disposal of all construction related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water.  Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

641-3.01  METHOD OF MEASUREMENT.  Erosion and Pollution Control Administration will not be measured for payment.

Erosion and Pollution Control will be measured in the manner specified in the order authorizing the work.

641-4.01  BASIS OF PAYMENT.  Item 641(1), Erosion and Pollution Control Administration will be full compensation for administration of erosion control, including preparing and amending plans, inspecting, monitoring, reporting, and record keeping.

Item 641(2), Erosion and Pollution Control will be full compensation for providing all required labor, equipment, and materials.

Failure to comply with the requirements of the NPDES General Permit for Alaska within 24 hours notice by the Engineer will result in withholding an amount equal to five percent of the total amount earned from all subsequent progress payments.  This retainage will be released by the Engineer upon satisfactory completion of the requirements of the General Permit.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution	Lump Sum

Control Administration

641(2)	Erosion and Pollution	Contingent

Control	Sum

(2/2/93)R59

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  DESCRIPTION.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix B.

642-3.01  CONSTRUCTION REQUIREMENTS.  Add the following after item 11.:

12.	The Contractor's survey crews shall comply with approved traffic control plans.  Crews shall coordinate their activities with the project's Worksite Traffic Supervisor.

642-4.01  METHOD OF MEASUREMENT.  Add the following:  Pay Item 642(2), Three Person Survey Party, shall be used only for extra, additional, or unanticipated work made necessary by changes in the project as directed by written order of the Engineer.

642-5.01  BASIS OF PAYMENT.  Add the following:  If additional work as stated above is performed by a two person survey party, hours paid for under Item 642(2) Three Person Survey Party will be 75 percent of the hours worked.  If additional work as stated above is performed by only one person, hours paid for under Item 642(2) Three Person Survey Party will be 32 percent of the hours worked.

(10/1/91)R60

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01   DESCRIPTION.  Add the following:

DEFINITIONS

Construction Phasing Plan - A plan for each phase of the project possibly broken into segments showing how traffic will be accommodated.  It should show the sequence of work by segment or phase if required.

Phase - A construction phase consists of a single work activity or a group of work activities that are accomplished concurrently.  Each work activity should be assigned to a phase.

Segment - A portion of the roadway under construction.

Sequence - The order in which work is accomplished, either by phase or by segment, or a combination thereof.  For example, a phase, say Phase 1, might be excavation and backfill.  It must be accomplished on Segment A to provide access to a new bridge abutment site so that another phase, say Phase 2, construction of the bridge abutment, can begin.  Phase 1 may or may not occur on other segments concurrently.  Another phase which might be topsoil and seeding may occur on all segments concurrently but must occur at the end of the project.

Traffic - The movement of vehicles and pedestrians through road construction, maintenance operations, utility work, incident zones or similar operations.

Traffic Control Plan - A Traffic Control Plan (TCP) is a drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians and workers in a traffic control zone.  It depicts the traffic control devices to be used, their placement and times of use.

Traffic Control Zone - A portion of a road construction project, maintenance operation, utility work, incident zone or similar operation where traffic is affected by the operation and traffic control is needed to safely guide and protect motorists, pedestrians, or workers.

643-1.02  TRAFFIC CONTROL PLAN.  Delete the first sentence of the first paragraph.

Add the following to the third paragraph:  All TCPs submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

Add the following to the fourth paragraph:  Plan sheets developed on AutoCad can be made available, upon request, for use in preparing TCP's.

643-1.03  WORKSITE TRAFFIC SUPERVISOR.  Delete the second sentence of the first paragraph and substitute the following:  The Worksite Traffic Supervisor shall meet the following minimum requirements:

1.	Be currently certified as a Worksite Traffic Supervisor by the American Traffic Safety Services Association (ATSSA), or,

2.	Be currently certified as a Work Zone Traffic Safety Specialist or a Work Zone Safety Specialist by the International Municipal Signal Association (IMSA), or,

3.	Be currently certified as a Worksite Traffic Technician by ATSSA.

If the individual is certified under Items 2 or 3 above, the Contractor shall submit documentation prior to work requiring traffic control that the individual has also obtained:

1.	A minimum of one year of supervisory level work in worksite traffic control, or,

2.	One year of having been in responsible charge of such work.  The term "in responsible charge" shall be construed to mean having been in a position of accountability for the selection of devices and for their placement in the traffic control system, or for the continued operation of the system.  Having persons that actually perform the labor under one's control would satisfy this requirement.

643-1.04 CONSTRUCTION PHASING PLAN.  Revise the first sentence to read as follows:  A Construction Phasing Plan shall be submitted at least five working days prior to the preconstruction conference for approval by the Engineer and shall consist of the following:  (5/7/91)S57

Delete the first sentence under Item 2. and substitute the following:  A plan for each phase or segment of the project showing how traffic will be accommodated.  It should show the sequence of work by segment or phase when required.

643-2.01  MATERIALS.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8 feet.

643-3.04  TRAFFIC CONTROL DEVICES.  Add the following to the first paragraph under Item 1., Embankments:  If no distance is shown it should be assumed to be 30 feet.  The Contractor shall arrange his work to minimize the need for portable concrete barrier.

Add the following to the third paragraph under Item 1., Embankments:  If no clear zone is shown on the plans, a 30 foot clear zone should be assumed.

Add the following to Item 1., Embankments:  Barrier reflectors shall be mounted on the face of barrier adjacent to traffic on 50-foot centers and shall be a minimum height of 18 inches above the surface of the roadway.

Delete numbered Item 4., Work Zone Pavement Markings in its entirety.

Under Item 5., Flagging, add the following after the first sentence of the first paragraph:  Each flagger shall be illuminated from the front to a level of light intensity not less than one foot candle during hours of darkness.

Under Item 5., Flagging, add the following:  Flaggers shall wear reflective clothing with markings on arms, legs and head.  Flaggers directing traffic through intersections shall wear orange gloves and orange helmets as approved by the Engineer.

Under Item 7., Street Sweeping, delete the last sentence.

643-3.06  TRAFFIC PRICE ADJUSTMENT.  Add the following:  A change order is not required for traffic price adjustment, the Notice to Proceed shall constitute the notice required to initiate traffic price adjustment.

643-3.07  MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK.  Delete the first sentence and substitute the following:  The Contractor shall schedule a preliminary meeting with the Engineer and Maintenance and Operations to take place approximately one month prior to seasonal suspension of work, or no later than September 15.  This meeting shall be to outline the work the Contractor expects to complete before shutdown and the condition the roadway is to be in.  The roadway shall be paved with permanent pavement markings and signing in place.  A winter shutdown traffic control plan shall be submitted to the Engineer at this preliminary meeting.

643-3.08  CONSTRUCTION SEQUENCING.  Delete this subsection in its entirety and substitute the following:  Throughout the duration of the project, the existing roadway configuration shall be maintained (i.e., the number of lanes and their respective widths) except for restrictions to traffic allowed below and addressed through approved Traffic Control Plans.  A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes or stops traffic.  An approved Traffic Control Plan is required before any restriction to traffic is implemented.

All areas of guardrail removal where new guardrail is to be installed shall not remain without guardrail longer than 7 calendar days.  During the time no guardrail is present the areas shall be protected with traffic control devices as described below.  Standard guardrail sections shall be protected with Type II barricades spaced 25 feet on center.  Controlled release terminals, breakaway cable terminals, and stiffened guardrail at bridge approaches shall be protected with five plastic drums.  Both Type II barricades and plastic drums shall have flashing warning lights.

Slopes steeper than 2:1 and a height of 2 feet or more adjacent to the travelled way during times when no work is taking place at the area of concern, shall be protected with Type II barricades.

Allowable restrictions to traffic are as follows:

1.	Road Closures.  Two 24-hour closures of the South Channel Bridge, each separated from the other by a minimum of 7 calendar days, will be allowed for construction of the bridge abutments and glulam deck repair.

Six 12-hour closures from 7:00 pm until 7:00 am will be allowed for blasting.  The roadway shall be reopened to two lane two way traffic at the end of each closure.

No roadway closures will be allowed January 15 to March 15, and August 15 to October 15.

During road closures, the Contractor shall maintain continuous two-way radio contact with the local authorities for police, fire and emergency.  The Contractor shall be able to open one lane of the closed roadway

section within 15 minutes of being notified, for passage of emergency vehicles, if no alternate route is available.

2.	One Lane Road Operations.  One lane road operations will be allowed for installation of culvert and utility crossings, placement of fill material and base course where two 11-foot lanes cannot be provided, paving, and installation of the pedestrian walkway and glulam running planks on the South Channel Bridge.  One lane road operations are limited to 2000 feet.

643-4.01  METHOD OF MEASUREMENT.  Delete the first and second sentences under Item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the traffic control devices that are installed, accepted and maintained in place during the life of this contract.  Traffic control devices (construction signs, barricades, traffic cones, and drums) will be measured by the number of units accepted per day.

Permanent Construction Signing will not be measured for payment, but will include all permanent construction signs, as detailed on the plans, that are installed, accepted, maintained, and removed during the life of this contract.

Add the following:  Providing a "hot-line road report" telephone with pre-recorded message, attendance of open house meetings and providing weekly notices with daily updates will not be measured for payment but will be subsidiary to Item 643(1), Traffic Maintenance.

643-5.01  BASIS OF PAYMENT.  Add the following:  Barrier reflectors will not be paid for directly, but will be subsidiary to Item 643(11), Portable Concrete Barrier.

Payment for Item 643(27), Traffic Control Devices will be made for the pay unit of accepted traffic control devices (construction signs, barricades, traffic cones, drums, flagging, and temporary pavement markings) times the unit rate value contained in the following rate schedule:

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 6.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 0.80 |
| Drums | Each/Day | $ 3.00 |
| Flagging | Hour | $45.00 |

Standard Modifications

643-5.01 BASIS OF PAYMENT.  Change the pay unit for item 643(3), Permanent Construction Signing, from "Calendar Day" to "Lump Sum."  (5/7/91)M40

Special Provisions

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

643(27)	Traffic Control Devices	Contingent

Sum

(12/07/93)

SECTION 644

SERVICES TO BE PROVIDED BY THE

CONTRACTOR

Special Provisions

644-2.01  FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:  The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion.  The following office requirements shall be met:

1.	A minimum of 1,000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 150 square feet of floor area.

2.	A thermostatically controlled interior heating system capable of maintaining 70 Fahrenheit, with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power, with a minimum of two electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 8 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within one mile of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

644-2.02  FIELD LABORATORY.  Delete the sixth sentence of the first paragraph and substitute the following:  The water supply shall consist of a 500-gallon capacity tank with a pressure pump or a commercial pressurized system.

Delete the second paragraph and substitute the following:  The laboratory shall include a concrete slab, 8 feet by 10 feet by 4 inches thick, suitable for mounting a Gilson shaker and other equipment.  The slab shall be installed within an enclosed adjacent structure having a door, a window, a worktable, an exhaust fan, electrical outlets and adequate lighting and heat.

Add the following:  The Contractor shall supply 240 volt, 60 cycle power, a 100 lb. propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

644-2.05  FIELD TRANSPORTATION.   Delete the second sentence of the first paragraph and substitute the following:  The vehicles shall be available from two weeks prior to commencing work through 30 days after issuance of the notice of project completion.

Add the following:  Three pickups, 1/2 ton minimum, shall be provided for this project.  Each truck shall be a 1991 or newer model having less than 30,000 miles, and shall be equipped with flashing beacons and CB radios.

644-2.06  SCALES.  Delete the second paragraph and substitute the following:  Sanitary lavatory facilities, heating, adequate electrical lighting and 120 volt, 60 cycle power shall be furnished to the scale house.

Delete paragraph three in its entirety.

Delete the fourth paragraph and substitute the following:  Furnishing platform scales, tickets, scale house, and electronic weigh system will not be paid for separately, but will be subsidiary to work performed under Sections 203, 301 and 401.  Platform scales, scale house and the electronic weigh system shall remain the property of the Contractor upon completion of the work.

Delete the second sentence of the last paragraph and substitute the following:  Platform scales shall be equipped with a weatherproof housing constructed in a manner that protects the recording equipment and allows the scale operator convenient access to the scale computer, ticket printer, and sequential transaction printer.  All components of the scale outside at the scale, and inside the scalehouse which could be physically manipulated in a manner which could tamper with weights shall be protected by an enclosure, acceptable to the Engineer, to preclude tampering with weighing operations.

Add the following:  The Contractor shall provide an electronic equipment weighing system with the following capabilities:

1.	Self reading scale system with a load cell, scale computer, ticket printer, sequential transaction printer, and the ability to record a complete shift's transaction on a 3.5 inch double sided diskette.  All individual parts of the system shall be compatible with each other and suitable for field conditions.  All supplies (weigh tickets, paper, printer ribbons, diskettes, etc), maintenance, and repair services necessary to keep the system functional, shall also be supplied by the Contractor and will not be measured or paid for directly but will be considered a subsidiary obligation.

Sufficient spare parts, components, etc., shall be available on the Project to keep the electronic equipment weighing system operational at all times.  Unless prior written authorization is obtained from the Engineer, no payment will be allowed for any material weighed without using the electronic equipment weighing system.

2.	The scale computer shall have the ability to store multiple project numbers and multiple pay item descriptions for all projects and pay items which are weighed with the electronic equipment weighing system.

The scale computer shall store the following for each hauling vehicle utilized on the project:  vehicle identification number, license number, associated trailer license number, tare weight, and maximum allowable vehicle weight (MAVW).

Vehicles shall be tared a minimum of once daily by the scale operator. The Engineer may request additional tares to be done at any time the scale is operational.  The Engineer may also require that he be present when tares are performed.

The MAVW shall be calculated by the Engineer and a copy of the calculation sheet will be placed in the scalehouse.  The MAVW will be: the maximum allowable legal weight when overloads can not be hauled; the maximum allowable weight as determined by the Department's Chief Bridge Engineer when overloads can be hauled but are limited by bridge capacities; or an arbitrary number of 500,000 pounds (an even number in excess of what any vehicle can haul on the project) when there are no weight limitations.

The scale operator shall only utilize MAVWs which have been provided by the Engineer in writing.  No tickets shall be issued to a vehicle until the Engineer provides a MAVW.

When there are no limitations on the MAVW the last character of the vehicle identification number shall be an asterisk (*).  If no vehicles are required to haul legal loads the "asterisk" can be omitted.

3.	During weighing operations the system shall compare each vehicle's gross weight to its MAVW.  If the vehicle exceeds its MAVW the electronic equipment weighing system shall alert the scale operator that an "overload" exists and not allow a ticket to be issued.

Payment will not be made for any material (i.e., the net weight will be changed to 0) hauled in a vehicle which is not in conformance with the requirements of Subsection 105-1.12, Load Restrictions, and this Section.  Non-conforming vehicles shall dump sufficient material, prior to leaving the material loading area, so that they conform and then be reweighed.

4.	The electronic equipment weighing system shall have a battery backup as well as protection for power surges or brown outs.  The system shall be capable of retaining all stored data during a power outage and shall be operable during a power outage for at least 30 minutes.

5.	The ticket printer furnished by the Contractor shall print a one part weigh ticket on 81/2 x 41/4  inch, 80 to 90 pound white index paper with the following information on each ticket in the order listed:

Sequential ticket number (4 digits)

Project information (20 digits)

Date

Pay Item name in words

Vehicle identification number, license number, & trailer license     number

Time of Dispatch (24 hour time)

Name of scale operator

MAVW in pounds

Gross weight in pounds

Tare weight in pounds

Net weight in pounds

All of the above items are to be printed by the ticket printer and not pre-printed.  All characters shall be printed in a minimum of a 12 point font.  The ticket given to the ticket taker by the vehicle operator shall be the original.  If the Contractor wants additional copies of each ticket they shall be printed on a separate ticket printer.

The weigh ticket "number" consists of the following information:

Project Number (First 5 characters of PROJECT field)

Date

Pay Item

Pit Number (Last 3 characters of PRODUCT field)

Sequential ticket number

The sequential weigh ticket number shall be set to "1" at the beginning of each day for each unique project number, pay item, and pit number combination.  The project information, date, pay item, hauling unit identification numbers, their MAVWs, and the scale operator's name shall also be able to be set by the scale operator.  Tare weights shall only be able to be changed by a tare weighing operation.

6.	The sequential transaction printer shall print all scale transactions, including tares, voided tickets, and data that is changed by the scale operator, as soon as the transaction is concluded.  The sequential transaction printer log shall be annotated with comments, either hand written or entered from the keyboard, to clarify errors or abnormal situations,

The list of MAVWs for all vehicles, with tractor and trailer license plate numbers, shall be printed on the sequential transaction printer at the beginning and end of each shift.  The sequential transaction listing shall be given to the Engineer at the end of each shift.

7.	The double sided diskette shall record all ticket information which was produced during a shift or at selected times in the shift.  The data shall be stored in 2 files with the same information but different formats.  The first file shall be in dBASE IV format (IBM) and shall be useable by the program without any conversion or manipulation.  The naming convention for this file shall be "yymmdd.dbf".  The second file shall be a raw data file in ASCII format with fields separated by commas, character fields enclosed in double quotes, a carriage return at the end of each record, and an end of file mark following the last record.  The naming convention for this file shall be "yymmdd.csv".  If more than one scale is used on the project a scale location designation acceptable to the Engineer shall be utilized for the 7th and 8th characters of the filename.

In the event both data files on the diskette are not completely useable to obtain all truck weighing data, the Contractor shall correct, construct, or reconstruct the data file utilizing the sequential transaction log or other information, as directed by the Engineer, as a data source.  No payment will be made for any hauled material on a given date until an accurate "daily" data file has been delivered to the Engineer.  If written permission is obtained from the Engineer to weigh without the electronic system for a minor equipment failure, a data file, acceptable to the Engineer, shall be constructed as described above.

8.	The fields for each record shall be in the following format and order.  Other data fields may also be provided but shall follow the fields in the required format.

| FIELD | FIELD NAME | TYPE | WIDTH |
| --- | --- | --- | --- |
| 1 2 3 4 5 6 7 8 9 10 11 12 | TKT DATE TIME UNIT_ID MAVW GROSS TARE NET COMMENTS PRODUCT PROJECT NAME | Character Character Character Character Numeric Numeric Numeric Numeric Character Character Character Character | 4 (right justified w/ leading blanks) 8 (mm/dd/yy) 5 (hh:mm)(24hour) 10 (right justified w/ leading blanks) 6 (pounds) 6 (pounds) 6 (pounds) 6 (pounds) 20 20 20 18 |

9.	The electronic equipment weighing system shall generate a summary report, either during or at the end of the day, which summarizes the number of loads and total net weight for each Date, Project, and Product.  The original of the end of day report shall be given to the Engineer at the end of each shift.

10.	A user instructional manual shall be available for each scale which explains the complete scale operation.  A copy of this manual shall be kept in each scalehouse and be available for review by the Engineer at all times.

11.	In the event that extra construction engineering expenses are incurred due to checking non-machine data entries or other data irregularities an amount equal to the value of those expenses will be deducted from the value of the item.  A unilateral change order will be issued to make any adjustments the Engineer determines to be warranted.

644-2.08  CONTAMINATED MATERIAL TESTING.  Add the following subsection:  In accordance with subsection 203-3.05, Processing of Contaminated Material, the Contractor shall retain an independent test laboratory to conduct the following tests:

1.	Field Tests

a.  Organic Vapor Analyzer (OVA) Analysis

b.  Visual Analysis (Petroleum Odor)

2.	Laboratory Tests

a.  Volatile Aromatic Hydrocarbons

b.  Total Petroleum Hydrocarbons

644-3.01  METHOD OF MEASUREMENT.  Add the following:  Field transportation will be measured per each pickup truck provided.  If a replacement vehicle is necessary, no additional measurement for payment will be made.

Add the following: Contaminated material testing shall be reimbursed based on paid receipts for the authorized tests.

644-4.01  BASIS OF PAYMENT.  Delete the sixth paragraph and substitute the following:  Field Transportation.  The price per vehicle will be full compensation for furnishing the vehicle, fuel, and all required maintenance and insurance.

Add the following:  Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

Add the following: Payment for contaminated material testing will be made on the receipts for authorized tests plus 15 percent, and shall be considered full compensation for all labor, equipment and materials required to obtain samples and have tests performed.  A change order will not be required to initiate  contaminated material testing.

Change the pay unit for Item No. 644(6), Field Transportation, from "Lump Sum" to "Each".

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

644(8)	Contaminated Material	Contingent Sum

Testing

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01  OBJECTIVE.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.1, located in the "green pages" of this document.

645-3.01  GENERAL.  The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following:  contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02  WAGES.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03  SUBCONTRACTS.  In the event the Contractor subcontracts a portion  of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01  METHOD OF MEASUREMENT.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  BASIS OF PAYMENT.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or,

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program for	Labor Hour

___Trainees/Apprentices

Add the following Section:

SECTION 646

EQUIPMENT RENTAL

Special Provisions

646-1.01  DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of the proposed improvements at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

646-2.01  EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

646-2.02  EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL.  Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

646-3.01  CONSTRUCTION REQUIREMENTS.  The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

646-4.01  METHOD OF MEASUREMENT.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.

646-5.01  BASIS OF PAYMENT.  The pertinent contract bid price per hour for the equipment shown in the Bid Schedule shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher horsepower than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

646(1)	Wide Pad Dozer, 65-HP Min.	Hour

646(8)	Motor Grader, 125-HP Min.	Hour

(6/25/92)R15

SECTION 670

TRAFFIC MARKINGS

Standard Modifications

670-3.01  CONSTRUCTION REQUIREMENTS.  In the last paragraph under Item 2., insert "pneumatic" immediately before "roller".  (5/12/89)M22

670-3.05  PRELIMINARY SPOTTING.  Add the following:  After acceptance of the crushed aggregate base course layer, but prior to paving, the Engineer will check all horizontal and vertical curves to verify the accuracy of the initial passing/no passing zone layout in the plans.  The Engineer will adjust the no passing zones in accordance with Chapter 3 of the Alaska Traffic Manual.

In addition, a no passing zone is warranted where, when measured along the centerline, less than the following sight distance is available:

| ROADWAY SEGMENT | MINIMUM PASSING SIGHT DISTANCE |
| --- | --- |
| BOP to 50+00 50+00 to EOP | 500 ft 800 ft |

The minimum gap between no passing zones is given by the following:

| ROADWAY SEGMENT | MINIMUM GAP BETWEEN NO PASSING ZONES |
| --- | --- |
| BOP to 50+00 50+00 to EOP | 500 ft 800 ft |

SECTION 702

ASPHALT  MATERIALS

Special Provisions

702-2.01  ASPHALT CEMENTS.  Delete this subsection in its entirety and substitute the following:  PBA-2 asphalt cement shall conform to the requirements shown in the following table:

| Property | Test Method | Requirement |
| --- | --- | --- |
| Penetration (4C [39.2F], 200gr, 60s), dmm, RTFO Aged Residue (see Note 1) | AASHTO T 49 | 15 min. |
| Ductility (7.2C [45F], 1 cm/min), cm, RTFO Aged Residue (see Note 2) | AASHTO T 51 | 10 min. |
| Ductility (25C [77F], 5 cm/min), cm, RTFO Aged Residue | AASHTO T 51 | 75 min. |
| Absolute Viscosity (60C [140F]), P, Original Binder, RTFO Aged Residue | AASHTO T 202 | 1100 min. 2500-6000 |
| Kinematic Viscosity (135C [275F]), CST, RTFO Aged Residue | AASHTO T 201 | 275 min. |
| Absolute Viscosity Ratio (60C [140F]), RTFO Viscosity/Original Viscosity | - | 4.0 max. |
| Flash Point, Cleveland Open Cup, C (F), Original Binder | AASHTO T 48 | 232 min. (450 min.) |
| Solubility in Trichloroethylene, %, Original Binder | AASHTO T 44 | 99.0 min. |

Note 1:	"RTFO Aged Residue" means the asphaltic residue obtained using the Rolling Thin-Film Oven Test ("RTFO Test"), AASHTO T-240.

Note 2:	Use AASHTO T-51 as modified by Washington DOT (using a special method of applying the release agent).

702-2.03  EMULSIFIED ASPHALTS.  Delete the first and second sentences and substitute the following:  The STE-1 cationic emulsified asphalt shall comply with the requirements listed below when tested in accordance with ASTM D 244:

TESTS ON EMULSION

Viscosity, Saybolt Furol at 25o C	30 max.

Storage Stability, 1 day, %	1 max.

Demulsibility, 35 ml, 0.8% Sodium dioctyl

sulfosuccinate solution, %	25 min.

Sieve Test, % retained	0.10 max.

Particle Charge	Positive *

Distillation Oil by Volume of Emulsion, %	5 max.

Distillation Residual by Weight of Emulsion, %	45 min.

*	If particle charge test is inconclusive, materials having a maximum pH value of 6.7 will be acceptable.

TESTS ON RESIDUE

Penetration, 25o C, tenths of a mm	100 min./200 max.

Ductility, 25o C, 5 cm/min., cm	40 min.

Solubility in Trichloroethylene, %	97.5 min.

702-2.04  STORAGE AND APPLICATION TEMPERATURES.  Add the following to Table 702-1:

| Type & Grade of Material | Spray (F) | Mix (F) | Storage (F) |
| --- | --- | --- | --- |
| PBA-2 | 280+ | 250-315 | 340 max. |
| STE-1 | 70-140 | 70-150 | 50-125 |

(10/22/93)R183

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  FINE AGGREGATE FOR CONCRETE.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

703-2.02  COARSE AGGREGATE FOR CONCRETE.  In the first sentence, insert ", class B," after "AASHTO M 80".

(7/16/93)M24

703-2.03  AGGREGATE FOR BASE.  Add the following to the list under the first paragraph:

Plastic Index			AASHTO T 90			6 max

Bulk Specific Gravity	AASHTO T 85			2.65 min

Percent Sodium

Soundness Loss		AASHTO T 104	       5% max (5 cycles)

Change Percent of Wear from "50 max." to "45 max."

Change Percent Fracture from "70 min." to "80 min. single face".

(5/7/91)M45

Special Provisions

703-2.03  AGGREGATE FOR BASE.  Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading D-1 | Grading E-1 |
| --- | --- | --- |
| 1 inch | 100 | 100 |
| 3/4 inch | 70-100 | 70-95 |
| 3/8 inch | 50-79 | 60-86 |
| No. 4 | 35-58 | 40-65 |
| No. 8 | 20-47 | - |
| No. 30 | 10-26 | 15-30 |
| No. 50 | 6-19 | - |
| No. 200 | 0-6 | 8-13 |

(9/14/93)R117

Standard Modifications

703-2.04  AGGREGATE FOR PLANT MIX ASPHALT PAVEMENT.  Replace this subsection with the following:

Coarse Aggregate.  Coarse aggregate (that material retained on the No. 4 Sieve) shall be crushed stone or crushed gravel and shall consist of sound, tough, durable rock of uniform quality.  All material shall be free from clay balls, vegetative matter or other deleterious matters.  Coarse aggregate shall not be

coated with dirt or other finely divided mineral matter.  In addition, coarse aggregate shall meet the following requirements:

Bulk Specific Gravity	      AASHTO T 85			          2.65 min

Percent of Wear	AASHTO T 96	45 max.

Degradation Value	ATM T-13	45 min.

Percent Sodium Sulfate loss	AASHTO T 104	5%  max. (5 cycles)

Percent Fracture	ATM T-4	80 min. single face

Thin-Elongated Pieces	ATM T-9	8 % max.

Fine Aggregate.  Fine aggregate (passing the No. 4 sieve) shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness Test.

Blended Aggregate.  The several aggregate fractions for the mixture shall be sized, graded, and combined in such proportions that the resulting composite blend conforms to the grading requirements of Table 703-3.  The fraction actually retained between any two consecutive sieves larger than the No. 100 shall be not less than 2 percent of the total.  Aggregate gradations shall be determined by ATM T-7.  The size of extracted samples will be in corformance with AASHTO T 164; extracted gradations will be performed according to AASHTO T 30.

BROAD BAND GRADATIONS FOR ASPHALT CONCRETE PAVEMENT AGGREGATE

Percent Passing by Weight

| Sieve Designation | Gradation Designation |  |  |
| --- | --- | --- | --- |
|  | Type I | Type II | Type III |
| 1 inch | 100 | - | - |
| 3/4 inch | 75-90 | 100 | - |
| 1/2 inch | 60-86 | 75-90 | 100 |
| 3/8 inch | 50-78 | 60-88 | 75-90 |
| No. 4 | 34-62 | 44-72 | 50-78 |
| No. 8 | 24-52 | 30-58 | 32-60 |
| No. 16 | 16-42 | 20-44 | 20-45 |
| No. 30 | 10-32 | 12-34 | 12-34 |
| No. 50 | 8-24 | 8-24 | 8-24 |
| No. 100 | 5-16 | 5-16 | 4-15 |
| No. 200 | 3-8 | 3-8 | 3-8 |

(7/16/93)M62

Special Provisions

703-2.07  SELECTED MATERIAL.  Delete Item 1. and substitute the following:  Where required by the specifications or shown on the plans, Selected Material Type A shall meet the requirements of Select Material, Type B.

Add the following to Item 2., Selected Material, Type B:  It shall have 20 to 70 percent by weight of particles passing the No. 4 sieve.

SECTION 705

JOINT MATERIALS

Standard Modifications

705-2.05  FLEXIBLE WATERTIGHT GASKETS.  In the first paragraph, add: "and precast manhole sections" after "rigid pipe."  (7/2/93)M56

SECTION 706

CONCRETE, CLAY, FIBER AND PLASTIC PIPE

Special Provisions

706-2.07  CORRUGATED POLYETHYLENE PIPE.  Delete in its entirety and substitute the following:  Corrugated polyethylene pipe shall conform to the following:

Culverts and Stormdrains	AASHTO M 294

Type S (double wall)

Underdrains

diameter less than 10 inches	AASHTO M 252

diameter greater than 10 inches	AASHTO M 294

(5/7/91)S60

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.06  FRAMES, GRATES, COVERS AND LADDER RUNGS.  Add the following:  Ductile iron castings shall conform to the requirements of ASTM A536 for grade 60-4018.  (9/1/89)R78

712-2.14  PREFORMED PAVEMENT MARKINGS.  Add the following to paragraph A. under Item 1., General Requirements:  The preformed ribbon shall consist of one solid piece of required width and length.  In solid stripe areas, the tape length shall, where possible, be a minimum of 100 feet.  (2/14/92)R79

SECTION 724

SEED

Standard Modifications

724-2.02  MATERIALS.  Add the following to Table 724-1:

| Seed Type | Germination Period | Percent Purity | Percent Germination | Percent Sproutable Seed |
| --- | --- | --- | --- | --- |
| Bering Hairgrass | 14 days | 95 | 75 | 71 |

(5/12/89)M28

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04  SIGN POSTS.  Under item 1., Metal Pipe Posts, add the following to paragraph a.:  Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

(9/1/89)R81

Standard Modifications

730-2.04  SIGN POSTS.  Under Item 2., a., replace the second sentence with the following:  Sheets for post fabrication shall be zinc coated in accordance with ASTM A 525, coating designation G 90.  (7/2/93)M57

Special Provisions

730-2.04  SIGN POSTS.  Delete Item 4., "Multi-directional Breakaway Load Concentration Coupler Base Assemblies and Coupler Hinge Plate", and substitute the following:

4.	Wide Flange Posts.

a.	Steel for wide flange posts shall conform to AASHTO M 183.

b.	Post sizes shall be as designated on the plans.

c.	Posts shall be hot dip galvanized in a manner conforming to AASHTO M 111 after fabrication.  Any cutting of metal posts after hot dip galvanizing shall be accomplished with minimum damage to the zinc coating and all exposed surfaces shall be protected by treating the exposed area in the same manner as if it were abraded or damaged.

d.	Galvanized surfaces that are abraded or damaged at any time after the application of the zinc coating shall be repaired in accordance with the applicable provisions of AASHTO M 36.

(5/7/91)S43

APPENDIX A

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING

REQUIREMENTS