SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available from the Department of Transportation and Public Facilities located at 4111 Aviation Avenue in Anchorage.  Information may be obtained as follows:

1.	Copies for review and reproduction information may be obtained from the Plans Room, (907) 266-1798, for the following:

a.	Computations.

b.	Cross Sections.

c.	Geotechnical Report entitled "Geotechnical Report, Raspberry Road, Jewel Lake to Northwood".

d.	Foundation Report entitled "Raspberry Road, Jewel Lake Road to Minnesota Drive, Retaining Walls".

2.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Traffic, Safety and Utilities Engineer, (907) 266-1531.

3.	Two Environmental Impact Statements and Environmental Reevaluations addressing concerns and environmental commitments have been approved and are available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 266-1737.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS FOR HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Special Provisions

101-1.27  Holidays.  Delete Items 2  and 3 and substitute the following:

2.	Martin Luther King Jr.'s Birthday - Third Monday in January.

3.	President's Day - Third Monday in February.

(9/1/89)

Add the following Subsections

101-1.73  Non-Frost  Susceptible.  That material that contains 6 percent or less passing the No. 200 screen as determined by sieve analysis based upon minus 3-inch material.

101-1.74  Structural Section.  That section of the roadway consisting of classified Selected Material, Types A & B, upon which the pavement structure is placed.

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  Qualification of Bidders.  Delete the second paragraph in its entirety. (5/12/89)

Special Provisions

102-1.01 Qualification of Bidders.  Add the following:  The bidder, by signing the proposal and under penalty of perjury under the laws of the United States, certifies that, except as may be noted on the proposal, the bidding firm or any person associated therewith is not currently under suspension, debarment, voluntary exclusion, or determination of ineligibility by any federal agency; has not been suspended, debarred, voluntarily excluded or determined ineligible by any federal agency within the past 3 years; does not have a proposed debarment pending; and has not been indicted, convicted, or had a civil judgement rendered against (it) by a court of competent jurisdiction in any matter involving fraud or official misconduct within the past 3 years.

Exceptions to the above shall be noted by the bidder on the proposal or on an attachment thereto.

Exceptions will not necessarily result in denial of award, but will be considered in determining bidder responsibility.  For any exception noted, indicate to whom it applies, initiating agency, and dates of action.  Providing false information may result in criminal prosecution or administrative sanctions.  (3/18/88)

102-1.06   Preparation of Proposal.  Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

(2/7/89)

102-1.07  Non-Responsive Proposals.  Delete numbered subsection 3. in its entirety and substitute the following:

3.	If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a limit on the maximum gross amount of awards

acceptable to any one bidder at any one bid letting, provided that any selection of awards will be made by the Department.

(9/1/90)

Standard Modifications

102-1.07  Non-Responsive Proposals.  Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)

102-1.12  Addenda Requirements.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  Consideration of Proposals.  Add the following:  The apparent low bidder shall, within 5 working days following the bid opening, submit either a list of all firms with which the prime contractor intends to execute subcontracts for the performance of the contract or a statement that the bidder intends to perform the work without subcontractors.  The list shall include the following information for each proposed subcontractor:

1.	name,

2.	business address,

3.	Alaska business license number,

4	Contractor's registration number of each proposed subcontractor,

5.	the work to be performed, and

6.	the approximate dollar amount of the work to be performed.

If the apparent low bidder fails to submit either a list of subcontractors or a statement that the bidder intends to perform the work without subcontractors, the apparent low bidder will be found not to be a responsible bidder and may be held to forfeit to the bid security.  The Department will then consider the next lowest bidder for the award of the contract.

If the apparent low bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess of one-half of one percent of the total bid, the bidder agrees that it shall be considered to have agreed to perform that portion of work without the use of a subcontractor and to have represented that the bidder is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this section by listing as a subcontractor another contractor who, in turn, sublets the majority of the work required under the contract, violates this section.

If a contract is awarded to a bidder who violates this section, the bidder agrees that the Contracting Officer may:

1.	cancel the contract without any damages accruing to the State; or

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18;

2.	files for bankruptcy or becomes insolvent;

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith;

4.	fails to obtain bonding;

5.	fails to obtain insurance acceptable to the State;

6.	fails to perform the contract with the bidder involving work for which the subcontractor was listed;

7.	must be substituted in order for the prime contractor to satisfy required State and Federal affirmative action requirements;

8.	refuses to agree or abide with the bidder's labor agreement; or

9.	is determined by the Contracting Officer not to be  responsible.

(9/1/90)

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02 Changes.  Add the following after the third paragraph:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)

Special Provisions

104-1.02  Changes.  Delete the first three paragraphs and substitute the following:  The Engineer reserves the right to make, in writing, at any time during the work, such changes in quantities and such alterations in the work as are necessary to satisfactorily complete the project.  Such changes in quantities and alterations shall not invalidate the contract nor release the surety, and the Contractor agrees to perform the work as altered.

If the alterations or changes in quantities significantly change the character of the work under the contract, whether or not changed by any such different quantities or alterations, an adjustment, excluding loss of anticipated profits, will be made to the contract.  The basis for the adjustment shall be

agreed upon prior to the performance of the work.  If a basis cannot be agreed upon,then an adjustment will be made either for or against the Contractor in such amount as the Engineer may determine to be fair and equitable.

If the alterations or changes in quantities do not significantly change the character of the work to be performed under the contract, the altered work will be paid for as provided elsewhere in the contract.

The term "significant change" shall be construed to apply only to the following circumstances:

1.	When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction, or

2.	When a major item of work, as defined elsewhere in the contract, is increased in excess of 125 percent or decreased below 75 percent of the original contract quantity.  Any allowance for an increase in quantity shall apply only to that portion in excess of 125 percent of original contract item quantity, or in case of a decrease below 75 percent, to the actual amount of work performed.  (4/13/89)

104-1.03  Differing Site Conditions.  Delete in its entirety and substitute the following:  During the progress of the work, if subsurface or latent physical conditions are encountered at the site differing materially from those indicated in the contract or if unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the work provided for in the contract, are encountered at the site, the party discovering such conditions shall promptly notify the other party in writing of the specific differing conditions before they are disturbed and before the affected work is performed.

Upon written notification, the Engineer will investigate the conditions, and if he determines that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any work under the contract, an adjustment, excluding loss of anticipated profits, will be made and the contract modified in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment which results in a benefit to the Contractor will be allowed unless the Contractor has provided the required written notice.  (4/13/89)

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  Authority of the Engineer.  Add the following:  The Engineer may  inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract including cost or pricing data submitted under Subsection 104-1.02, Alteration of Plans or Work.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.  (5/12/89)

Special Provisions

105-1.06   Cooperation With Utilities.  Add the following:  The Contractor shall request locates from all the Utilities having facilities in the area.  Their telephone numbers are as follows:

Anchorage Telephone Utility		278-3121/564-1555

Anchorage Water and Wastewater

Utility						278-3121/564-2762

Chugach Electric Association		278-3121/562-2278

DOT/PF Maintenance & Operations	333-2411

ENSTAR Natural Gas Company		278-3121/264-3740

Prime Cable of Alaska 			278-3121/562-3133

Municipal Light and Power		278-3121/263-5441

Municipal Traffic Operations		278-3121/786-8355

All existing utilities shall remain in service until the new utilities are installed and put into service.  Temporary facilities may be installed to facilitate highway construction.  Check with each utility for status of their facilities.

Storm drains, signal interconnect conduits, and electrolier foundations with conduits along Raspberry Road shall be installed concurrently with the utility duct systems.  Retaining walls may be required to be in place prior to utility installation.  Whenever possible, laterals shall be doubled-up in the roadway crossings.  It is also anticipated that some utilities will require shoring or a digging boat for installation when adjacent to the edge of the Right-of-Way or the roadway.

A utility inspector will be on the project for all duct system installations.  His instructions will be relayed though the Engineer, and appropriate action by the Contractor will be required.

There are various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Prior to the relocation of the utility's facilities, construction stakes by the Contractor in the areas of utility conflicts may be required.  The Utility requesting the stakes, through the Engineer, shall be given two (2) weeks advance notice when the area will be staked.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the Utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

The Contractor shall coordinate his work schedule with the utilities so various utility facilities within the project limits can be adjusted or relocated.

(9/1/89)

Electrical Cable Damage

If a cable is damaged and requires splicing, the first occurrence will be repaired by the Utility with the party causing the damage paying the repair costs.

If the cable is damaged a second time, the cable will be replaced between junction points.  The party causing the damage will pay for replacing the cable.

ANCHORAGE TELEPHONE UTILITY

Upon completion of the manhole duct system installed as a part of this contract, the Anchorage Telephone Utility (ATU) will be installing telephone cables in the duct system.  The Contractor shall notify ATU, in writing, two (2) weeks prior to the availability of the manhole duct system.  It will take ATU approximately 90 days to pull in the new cables and make the cut over to the new cables.  However, this date may not be met if ATU is denied access to the duct system because of the Contractor's operation.  The existing aerial and underground cables must remain operational until the new cables are operational.

ATU will be installing a temporary aerial reroute on existing poles of the underground 100 pair cable crossing Jewel Lake Road at approximately Station "JL" 39+60.  The Contractor should check with ATU to ascertain if and when the underground cable is abandoned.

Between Blackberry Street and Cranberry Road, ATU will be installing underground cables on the south right of way.  See ATU Sheets 1, 2, 3, and 4 of 4 which are in the drawings but are not a part of the contract.

Along Arlene, ATU will be installing underground crossings at approximately "AR" 17+20 and 21+90.  The crossing at 17+20 shall be installed and operational before the aerial cables on the pole line along the centerline of Arlene is removed.  The crossing at 21+90 must be completed and operational before the aerial pole line at the same station can be removed.

CHUGACH ELECTRIC ASSOCIATION

Chugach Electric Association's (Chugach) power distribution facilities will be relocated into a Contractor installed, concrete encased duct system along the north side of Raspberry Road.  The concrete pads for the switching cabinets and transformers shall also be placed by the Contractor.  After the new underground system is operational, Chugach's Contractor will remove the electrical pole line and appurtenances.

Upon completion and acceptance of the duct system, the Contractor shall in writing, notify Chugach 30 days in advance that the Utility can commence with the underground cable installation.  Chugach anticipates completing the relocation within 60 days after the commencement of work by their Contractor.  However, this date may not be met if Chugach is denied access to the duct system because of the Contractor's operation.

Chugach will upon receipt of written notification from the Contractor, deenergize two phases of the three phase line on the west side of Jewel Lake Road south of Raspberry (between "JL" stations 30+00 and 39+00) temporarily while the sheet piling for Wall XII is being installed.  The conductors will remain in place but the street side conductor will be deenergized.  The Contractor will have to schedule this sheet pile installation for Wall XII at the convenience of Chugach.  If an emergency arises, the Contractor may have to suspend this sheet pile installation to allow Chugach to reenergize these phases.

The transmission circuits will remain in operation during the project and will be relocated or adjusted as required by Chugach during the project.

Chugach will remove their aerial facility after the underground system is operational and the telephone and cable TV aerial facilities are removed from the poles.

All buried electrical facilities contacted or exposed by the Contractor shall be handled by Chugach.  See Section 681, Private Electrical Power Relocation for more information.

ENSTAR NATURAL GAS COMPANY

Gas flow through the Jewel Lake/Raspberry intersection could be temporarily suspended from May 16 through September 30.  During colder weather, from October 1 through May 15, gas lines through the intersection must be fully operational.  Prior to stopping the flow of gas through the Jewel Lake/Raspberry intersection, the new 6 inch plastic gas line crossing at station 31+85 must be connected to the existing 6 inch steel line at station "JLR" 148+85 and operational.  This requires that the new 6 inch plastic line East to Minnesota and the new 6 inch plastic line South along Service Road which connects to the existing 6 inch steel line at 74th Court (station "JL" 28+70) must be operational.

Enstar proposes to abandon the 6-inch steel line along Jewel Lake Road between W. 74th Court and Thurman Drive.  Customers south of Raspberry would be served from a new 6-inch plastic line along Service Road.  North of Raspberry, 67th Avenue would be temporarily supplied by a service line tie from Bridget Drive.  The gas lines along Raspberry may be abandoned in place between Station 26+00 and Station 34+00 after a new crossing is installed at Station 19+40.  Using this plan, Enstar's facilities would not be in conflict with the large grade reduction at the intersection.  As each side of the intersection is lowered to subgrade, Enstar crews will install portions of the new crossings.

In conjunction with this project, Enstar proposes to install a continuous 6-inch steel and plastic gas line along Raspberry Road from Lawlor to Arlene Street with a regulator station at Sta 80+00.  The line West of the regulator station will operate at distribution pressure, the line East will be transmission pressure.  Also included in the project is a length of 2-inch plastic on Arlene Street, steel interties for cathodic protection, and various road crossings.

Enstar crews require the Contractor(s) to allow an uninterrupted work schedule for each of the following segments of new gasline being installed.

1.	Lawlor Circle to Fountain Drive along Raspberry Road, 5 feet inside the south Right of Way.

2.	Blackberry Street to Cranberry Street along Raspberry Road, between 5 feet and 8 feet inside the south Right of Way.

3.	Cranberry Street to Arlene Street along Berryman Lane, 5 feet inside the south Right of Way.

4.	Raspberry Road to 67th Ave. along Arlene Street, 5 feet inside the east Right of Way.

A cathodic protection area sweep is required after all underground work has been completed and before paving begins.  The sweep will take two (2) days to perform and will require three (3) working days notice to Enstar prior to performing the work.  If any underground contacts are detected, additional time will be required to perform repairs.

SONIC CABLE TELEVISION

All references to Sonic throughout the contract applies to their new owner Prime Cable of Alaska.

Sonic Cable Telephone (Sonics) will provide rigid metal conduit to the Contractor to place during backfill operations along the ATU duct bank on the eastside of Jewel Lake Road.  Above ground caps for future cabinets will be provided and protected at the indicated locations.  See Section 684, Cable Televisions Systems, for details.

ANCHORAGE WATER AND WASTEWATER UTILITY

A new waterline will be installed from McGill to Weimer and from Chevigny Street to Arlene Street.  This line will replace existing lines that are in conflict or that are AC pipe.  Water crossings or laterals will be placed at the following locations (See AWWU plans):

1.	Cutty Sark Circle

2.	Fountain Drive

3.	Town and Country Place

4.	Raspberry Station 32+16

5.	Linden Drive

6.	Holly Way

7.	Chevigny Street

8.	Blackberry

Sewer reconstruction will take place between Jewel Lake Road and Weimer Drive along Raspberry Road.

All AWWU construction is a part of the construction contract except that AWWU crews will make the following live taps:

1.	Fire Hydrant "SV" 18+00 LT

2.	Fire Hydrant "DK" 14+43 RT

3.	Lateral "RASP" 20+27 LT (Cutty Sark Circle)

4.	Lateral "RASP" 25+65 LT (Fountain Drive)

5.	Fire Hydrant "RASP" 25+93 LT (McGill Street)

6.	Fire Hydrant "CL" 18+83 (Carline Place)

GENERAL OVERVIEW

The following is a general overview of the anticipated utility phasing prior to the construction phase II - lowering the grade at Jewel Lake and Raspberry.

AWWU FACILITIES

1. 	Install water conduit at "RASP" stations 31+25 to 35+12 (Prior to phone duct).

2.	Extend waterline from Fountain to Jewel Lake Road (30+00).  This allows CEA and ATU ducts to be installed above waterline.

ATU  FACILITIES

1.	Grade northeast, northwest and southeast quadrants of Raspberry and Jewel Lake Intersection to near finish grade to minimize trenching.

2.	Install Jewel Lake manhole duct system from MH W7 ("JL" 28+90) to MH W3 ("JL" 256+20) this includes the boring of Raspberry Road.

3.	Install duct system from "RASP" station 25+25 to station 43+50.

CEA FACILITIES

1.	Install duct system along Raspberry from Jewel Lake to Arlene.  Include Raspberry crossings at:

a.  	"RASP" 33+50

b.  	"RASP" 36+85

c.  	"RASP" 41+00

d.	"WP"   19+00

e.	"RASP" 45+60

f.	"RASP" 46+50

g.	"RASP" 64+65

h.	"RASP" 69+60

2.	Install duct system along Raspberry from Jewel Lake to McGill.

SONIC FACILITIES

Sonic ducts are to be placed in CEA and ATU trenches.

ENSTAR FACILITIES  (To be installed by ENSTAR Forces)

Install 6-inch plastic line from Jewel Lake (74th Street) along service road to Raspberry Road and from Raspberry Road to Thurman except crossing of Raspberry Road.

When the Jewel Lake Intersection is lowered, the following utility work must be accomplished prior to removing the existing facilities:

AWWU FACILITIES

Install Raspberry crossing and connect new facilities so that they are operational.  This will allow the existing waterlines scheduled for abandonment to be abandoned.

ATU FACILITIES

Install duct crossing at Town and Country.  This will allow ATU to install cables in the ducts installed under this contract.

CEA FACILITIES

Install the duct crossing of Jewel Lake north of the intersection and the Raspberry crossing at Town and Country.  This will allow CEA to install conductors in the ducts installed under this contract.

SONIC FACILITIES

Install duct crossing at Town and Country and those associated with the CEA crossing of Jewel Lake.

ENSTAR FACILITIES

Install six inch plastic pipe across Jewel Lake Road.  This crossing must be accomplished before September 30, 1991.

105-1.12  Load Restrictions.  Delete  the first   paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25 of the Alaska Administrative Code for vehicles travelling with the general public, unless allowed for use by an approved Traffic Control Plan.  (2/7/89)

105-1.13  Maintenance During Construction.  Add the following:  During the construction season and prior to winter shutdowns, the Contractor shall monitor and clean all storm drain sumps and petroleum separator manholes.  This monitoring and maintenance of the systems effectiveness will not be paid for directly but will be considered a required responsibility of the Contractor under Sections 603, Culverts and Storm Drains, and 604, Manholes, Inlets and Catch Basins.

105-1.15  Project Completion.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work scheduled under subsection 618-3.04, Maintenance of Seeded Areas and subsection 621-3.04, Period of Establishment, a letter of project completion will be issued by the Engineer.  (7/1/90)

105-1.17  Claims for Adjustments and Disputes.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (1/1/91)

Add the following:  Legal actions will be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/29/87)

105-1.18  Cooperation Between Contractor and Property Owners:  Add the following subsection:

1.	Lakewood Terrace Townhouse Association, Parcels No. P-2A and P-2B.  The Contractor shall notify the Lakewood Terrace Association 15 days prior to beginning work on Lakeway Drive.  A written notice shall be sent to Mr. Norm Rokeberg, Association President, at 6534 Lakeway Drive, Anchorage, AK  99502, with a copy given to the Engineer.  The Contractor shall comply with the following stipulations for these parcels:

a.	Access to Lakeway Drive and homes shall be maintained at all times.

b.	Work on these parcels shall be complete by August 15, 1991 so adequate time for landscaping improvements is provided to the Association.

2.	NCB Properties, Inc., Parcel No. P-1.  There are currently two driveways accessing Raspberry Mall.  There shall be one driveway open to traffic at all times.  For the reconstruction of the Jewel Lake Road driveway, the Contractor shall grade and complete the roadbed construction as shown on the plans.  NCB Properties will complete the reconstruction of the driveway.  NCB Properties will require 21 days to complete the work, and during the time the existing driveway from Jewel Lake Road is under reconstruction, the driveway from Raspberry Road shall remain open.

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  Source of Supply and Quality Requirements.  Add the following:  All steel products which are to be incorporated into the work shall be produced in the United States except that minor amounts of steel products of foreign manufacture may be used provided the aggregate cost of such materials used does not exceed one tenth of one percent (0.1 percent) of the total contract cost, or $2500, whichever is greater.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel products into the project.  (11/9/84)

106-1.02  Local Material Sources.  Add the following to Item 1., General:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made. (2/7/89)

Add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement will be given to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (2/10/88)

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01  Laws to be Observed.  Add the following:  Specific Equal Employment Opportunity Responsibilities of Federal-Aid Construction Contractors.

1.	General

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form 25D-55) and these Special Provisions which are imposed pursuant to Section 140 of Title 23, U.S.C., as established by Section 22 of the Federal-Aid Highway Act of 1968.  The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the equal employment opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State highway agencies and the Federal Government in carrying out equal employment opportunity obligations and in their review of his/her activities under the contract.

c.	The Contractor and all his/her subcontractors holding subcontracts not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of equal employment opportunity: (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as contractors and subcontractors.)  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.

2.	Equal Employment Opportunity Policy.

The contractor will accept as his operating policy the following statement which is designed to further the provision of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include:  employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprentice-ship and/or on-the-job training.

3.	Equal Employment Opportunity Officer

The contractor will designate and make known to the State highway agency contracting officers and equal employment opportunity officer (hereinafter referred to as the EEO Officer) who will have the responsibility for and must be capable of effectively administering and promoting an active contractor program of equal employment opportunity and who must be assigned adequate authority and responsibility to do so.

4.	Dissemination of Policy

a.	All members of the contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the contractor's equal employment opportunity policy and contractual responsibilities to provide equal employment opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

(1)	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the contractor's equal employment opportunity policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the contractor's equal employment opportunity obligations within thirty days following their reporting for duty with the contractor.

(3)	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the contractor's procedures for locating and hiring minority group employees.

b.	In order to make the contractor's equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the contractor will take the following actions:

(1)	Notices and posters setting forth the contractor's equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The contractor's equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

5.	Recruitment

a.	When advertising for employees, the contractor will include in all advertisements for employees the notation:  "An Equal Opportunity Employer."  All such advertisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority group applicants, including, but not limited to, State employment agencies, schools, colleges and minority group organizations.  To meet this requirement, the contractor will, through his EEO Officer, identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority group applicants may be referred to the contractor for employment consideration.

In the event the contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the contractor's compliance with equal employment opportunity contract provisions.  (The U.S. Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or women, or obligates the contractor to do the same, such implementation violates Executive Order 11246, as amended.)

c.	The contractor will encourage his present employees to refer minority group applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures with regard to referring minority group applicants will be discussed with employees.

6.	Personnel Actions

Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The contractor will promptly investigate all complaints of alleged discrimination made to the contractor in connection with his obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the contractor will inform every complainant of all of his avenues of appeal.

7.	Training and Promotion

a.	The contractor will assist in locating, qualifying, and increasing the skills of minority group and women employees, and applicants for employment.

b.	Consistent with the contractor's work force requirements and as permissible under Federal and State regulations, the contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.  In the event the Training Special Provision is provided under this contract, this subparagraph will be superseded as indicated.

c.	The contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.	The contractor will periodically review the training and promotion potential of minority group and women employees and will encourage eligible employees to apply for such training and promotion.

8.	Unions

If the contractor relies in whole or in part upon unions as a source of employees, the contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and female employees.  Actions by the contractor either directly or through a contractor's association acting as agent will include the procedures set forth below:

a.	The contractor will use best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

b.	The contractor will use best efforts to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The contractor is to obtain information as to the referral practices and policies of the labor union except that the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the contractor, the contractor shall so certify to the State highway department and shall set forth what efforts have been made to obtain such information.

d.	In the event the union is unable to provide the contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minority group persons and women.  (The U.S. Department of Labor has held that it shall be no excuse that the union with which the contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees.)  In the event the union referral practice prevents the contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such contractor shall immediately notify the State highway agency.

9.	Subcontracting

a.	The contractor will use his best efforts to solicit bids from and to utilize minority group subcontractors or subcontractors with meaningful minority group and female representation among their employees.  Contractors shall obtain lists of minority-owned construction firms from State highway agency personnel.

b.	The contractor will use his best efforts to ensure subcontractor compliance with their equal employment opportunity obligations.

10.	Records and Reports

a.	The contractor will keep such records as are necessary to determine compliance with the

contractor's equal employment opportunity obligations.  The records kept by the contractor will be designed to indicate:

(1)	the number of minority and nonminority group members and women employed in each work classification on the project,

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to contractors who rely in whole or in part on unions as a source of their work force),

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority group subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such records must be retained for a period of three years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the State highway agency and the Federal Highway Administration.

c.	The contractors will submit an annual report to the State highway agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form PR 1391.  If on-the-job training is being required by "Training Special Provision", the contractor will be required to furnish State of Alaska Form 25A-312.

(4/8/83)

107-1.11  Protection and Restoration of Property and Landscape.  Add the following to the third paragraph:  When working near wetlands the Contractor shall place no fill, nor operate equipment, outside of the slope limits.

The Contractor shall not excavate, nor use for fill, any material containing hazardous substances or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected of containing hazardous substances or petroleum fuels.  Hazardous substances are any element compound, mixture, solution or substances designated pursuant to the Comprehensive Environmental Response, Compensation, and Liability Act of 1980 (CERCLA).  Hazardous substances include any hazardous wastes having the characteristics of ignitability, corrosivity, reactivity, or extraction procedure toxicity.

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2253.

Add the following:  The Contractor shall do no work, trespass, stockpiling, staging, or parking in or around any streams, located inside or outside of the project limits.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any significant historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.

Raspberry Road parallels Linden Park between Sta 43+58 and Sta 48+00 Rt., the Connors Bog Recreation Area and associated wetlands from Sta 76 to 92 Lt.  The Contractor is instructed that no work, trespass, stockpiling, staging or parking will be allowed in this area except as expressly detailed below.

While working adjacent to the Park, Bog, and on the Caravelle storm drain outfall the Contractor shall take ameliorative measures, and adhere to the following requirements:

1.	Before commencing any work in the Bog, the Contractor shall submit a detailed Work and Erosion Control Plan describing all anticipated steps to complete that phase of the work.  Each plan shall be submitted at least fourteen days prior to the start of each phase.

2.	Applicable State water quality standards as specified in the regulations of the Department of Environmental Conservation (18 AAC 70.010-110) shall be maintained at all times.

Standard Modifications

107-1.13  Responsibility for Damage Claims.  In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries".  (5/12/89)

107-1.16  Contractor's Responsibility for Utility Property and Service.  In the last sentence of the third paragraph delete  "...by the local fire authority."

(5/12/89)

Special Provisions

107-1.16  Contractor's Responsibility for Utility Property and Service.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mislocates the facility in the field by more than 2.5-feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.

(9/1/89)

107-1.21  Permits.  Add the following Subsection:  The following permits have been received on the Contractors behalf by the Department:

1.	Department of U.S. Army Corps. of Engineers Permit No. N-790304, Campbell Creek 1, dated June 26, 1989.

2.	Department of Environmental Conservation Water Quality Certification dated March 13, 1989.

3.	Federal Aviation Administration Highway/Airport Clearance dated July 28, 1987.

The Contractor shall be responsible for conducting all operations in compliance with Anchorage Municipal Code 15.70 (Noise).  If the Contractor can not conform with the restrictions of this Code, it is his responsibility to obtain a Noise Permit authorizing the nonconformance.  Application for  this Permit can be made through the  Municipality of Anchorage, Health and Human Services Division, 825 "L" Street, Anchorage, Alaska, (907)343-4200.

The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor's responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer.  The Engineer will then decide if a permit modification is necessary.  Copies of the permits are attached to these specifications in Appendix A.  The Engineer will have copies of the permits posted in the project office.

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  Subletting of Contract.  Add the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Driver's License.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	the owner-operator's right to control the manner in which the work is to be performed

2.	the owner-operator's opportunity for profit or loss depending upon their managerial skill

3.	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers

4.	whether the service rendered requires a special skill

5.	the degree of permanence of the working relationship, or,

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each truck driver that identifies the truck driver as either an employee or owner-operator.  The placard for owner-operators shall identify both the truck driver and the vehicle.  The placard shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.

(9/1/89)

Standard Modifications

108-1.03 Prosecution and Progress.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words " a progress schedule".  (5/12/89)

Special Provisions

108-1.03  Prosecution and Progress.  Add the following:  The construction of this project will be planned and recorded with a conventional Critical Path Method (CPM) schedule.  The schedule shall be used for coordination, monitoring, and payment of all work under the contract including all activity of subcontractors, utility companies, manufacturers, and suppliers.

1.	Preparation of Initial Schedule.	At the preconstruction conference, the Contractor shall submit for the Engineer's approval a detailed initial Progress Work Schedule in the activity-on-arrow format.  The schedule shall meet the requirements set forth below.

The construction time, for the entire project or any milestone shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed schedule are required, the Contractor shall do so promptly.  The schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements.

All activity-on-arrow diagrams shall include:

a.	Activity nodes

b.	Activity Description

c.	Activity Duration

d.	Resources Required for each of the Project Activities, including:

(1)	labor showing:

-work days per week

-holidays

-number of shifts per day

-number of hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-arrow diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and approvals and fabrication and delivery activities.  All network "dummies" are to be shown on the diagram.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60 - Day Preliminary Schedule.  Before proceeding with any work on site, the Contractor shall prepare, submit, and receive the Engineer's approval of a 60-day preliminary schedule.  This schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include:

a.	mobilization,

b.	submittals,

c.	procurement, and

d.	construction.

No contract work may be pursued at the site without an approved 60-day Preliminary Schedule or an approved CPM schedule.

4.	Schedule Updates And Progress Payments.  Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the Progress Work Schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions.

The Contractor will revise activity on arrow diagrams for the following:

a.	resource availability,

b.	delay in completion of any critical activity;

c.	actual prosecution of the work which is, as determined by the Engineer, significantly different than that represented on the schedule; or

d.	the addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

The principals involved and terms used in this section are as set forth in the Associated General Contractors of America publication, "The Use of CPM in Construction, A Manual for General Contractors and the Construction Industry", Copyright 1976.

In addition to the CPM Progress Work Schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail work activities, manpower involved by trade, work hours, equipment involved and the location of the work to be performed.

After approval of the Progress Schedule, and during the life of this project, the Contractor shall make available a spokesperson knowledgeable in the proposed construction operation.  State representatives may be attending meetings, community council meetings, throughout the Region, and it is expected that the spokesperson will accompany them to assist by briefly describing, and answering questions about the Contractor's work and time schedules.  The spokesperson will also be required to accompany the Engineer to residences and businesses abutting Raspberry Road, Jewel Lake Road, Caravelle Drive and associated side streets, when disputes or problems arise that require mediation between the public and the project.  The spokesperson must be able to speak for the Contractor and commit the Contractor to courses of action when needed to resolve problems.

Preparation of the CPM work schedule, two week work plans and providing a spokesperson will not be paid for directly, but will be subsidiary to Item 640(1), Mobilization and Demobilization.

108-1.04  Limitation of Operations.  Add the following:  The reconstruction of Cranberry Street shall be completed prior to September 1st.

The Contractor shall provide and maintain a walkway, separated from the roadway, during the school year, approximately September 1st to June 10th, along the west side of Jewel Lake Road from Sta. B.O.P. "JL" 23+00 to the intersection with Raspberry Road.

The Contractor will not have access to the properties commonly known as the Chevron Station and the Texaco station, located on the northwest corner and the southeast corner of the Raspberry Road-Jewel Lake Road intersection, until August 5, 1991.

108-1.05  Character of Workmen, Methods and Equipment.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer. (5/2/88)

108-1.06  Determination and Extension of Contract Time.  Add the following:

4.	Suspensions of Work Ordered by the Engineer.  If the performance of all or any portion of the work is suspended or delayed by the Engineer in writing for an unreasonable period of time (not originally anticipated, customary, or inherent to the construction industry) and the Contractor believes that additional compensation and/or contract time is due as a result of such suspension or delay, the Contractor shall submit to the Engineer in writing, a request for adjustment within 7 calendar days of receipt of the notice to resume work.  The request shall set forth the reasons and support for such adjustment.

Upon receipt, the Engineer will evaluate the Contractor's request.  If the Engineer agrees that the cost and/or time required for the performance of the contract has increased as a result of such suspension and the suspension was caused by conditions beyond the control of and not the fault of the Contractor, its suppliers, or subcontractors at any approved tier, and not caused by weather, the Engineer will make an adjustment (excluding profit) and modify the contract in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment will be allowed unless the Contractor has submitted the request for adjustment within the time prescribed.

No contract adjustment will be allowed under this clause to the extent that performance would have been suspended or delayed by any other cause, or for which an adjustment is provided for or excluded under any other term or condition of this contract.

(4/13/89)

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  General.  Add the following:  When more than one variety of material or work item is specified for a single pay item number, letter or numeric suffixes will be included within the parenthesis to differentiate the types.  (9/1/89)

109-1.04  Compensation for Altered Quantities.  In the third indented subparagraph, delete the following:  "..., except that the total payment for the item shall not exceed 75 percent of the total amount bid for the item.".  (4/13/89)

109-1.05  Compensation for Extra Work.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)

109-1.07  Payment For Materials on Hand.  Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Anchorage, Alaska only.

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provision

120-1.01  Description.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, CFR (Code of Federal Regulations), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  Interpretation.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  Essential Contract Provision.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  Definitions and Terms.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03.3 for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  Utilization Goal.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Utilization Goal in order to be eligible for award of this contract.

120-3.01  Determination of Compliance.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  Good Faith Effort.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE Credit.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that ALL of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least one of which must be working on this project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  Default of DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, ALL of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02, Good Faith Effort.

120-4.01  Method of Measurement.  The Contractor shall be entitled to count toward the DBE Goal those monies allowed by the Engineer in Subsection 120-3.03. paragraph No. 4, as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under Subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100 percent.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60 percent of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  Basis of Payment.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01 until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per Subsection 120-3.03, Paragraph No. 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

Payment or Deduction will be made under:

Pay Item No.        Pay Item         Pay Unit

120(1)        DBE Adjustment   Contingent Sum

(5/5/89)

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-2.01  General.  Add the following:  No burning or burying of cleared materials will be allowed on the project.

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 Description.  Add the following:  This work shall also include the removal of fences, the removal of gas pipe, removal of storage tanks (either fuel or septic) and the abandonment of ground water wells.  The foundations and any remaining building structures shall also be removed by the Contractor.

202-2.01  General.  Add the following:  All fences designated by the Engineer shall be carefully removed to the Right-of-Way limit, or to the end of the span beyond the Right-of-Way limit. These materials belong to the property owners, and shall be salvaged and stacked neatly in their yards.  After construction of any noise barrier or fence, the fencing gaps behind the property line shall be filled using portions of the salvaged fencing in accordance with Section 607, Fences for reconstructed fences.

The removal and obliteration of the foundations and structures shall be completed, including but not limited to, the removal of buildings as designated, the removal of any utility lines, the removal of sidewalks and other attached appurtenances, the filling in of the remaining depressions and the final grading to natural and pleasing contours.

Buildings being removed may contain asbestos and the Contractor shall take special handling measures when removing this material.

The removal of septic or fuel tanks, and removal or abandonment of wells shall be accomplished in a manner consistent with Alaska Department of Environmental Conservation regulations.

The ends of retaining walls to remain after partial removal shall be cut neat and true with no shatter outside the removal

area.  This work will be subsidiary to Item 202(1), Removal of Structures and Obstructions.

The building located on parcel No. 3, commonly known as the Tastee Freeze, is to be removed by others.  Should the Contractor require advance removal of the building in order to install the duct system through this parcel, he shall remove and dispose of the building, foundation, utility lines and any other attached appurtenances.  This work will be paid on a time and materials basis in accordance with Subsection 109-1.05, Compensation for Extra Work.

202-2.02  Removal of Bridges, Culverts and Other Drainage Structures.  Add the following after the second paragraph:  Sanitary sewer manholes designated to be removed on the plans or as directed by the Engineer, shall be removed and disposed of or salvaged.

Materials that are to be salvaged shall be carefully removed and delivered to a site as directed by the Engineer.  A disposal site for non-salvageable materials shall be provided by the Contractor.

Where existing sanitary manholes are designated to be removed, by the Plans or by the Engineer, the Contractor shall remove the manhole frame and cover, adjusting rings and cone section or reducing slab.  The Contractor shall plug all conduits intersecting the manhole and shall fill the remaining barrel sections of the abandoned manholes with material meeting the requirements of Selected Material, Type C and compact it to the satisfaction of the Engineer.

All existing manhole frames, covers, dustpans, adjusting rings, cone sections and reducing slabs removed but not reinstalled under these Special Provisions shall become the property of the Contractor.

Add the following to the third paragraph:  The Contractor shall plug the ends of remaining culverts.

202-2.03  Removal of Pipe.  Add the following: During project construction, ENSTAR Natural Gas Company  will abandon existing gas pipelines.  Contractor shall  follow the procedures given in Subsection 105-1.06, Cooperation  With  Utilities,  when  working around gas

pipelines until they have been abandoned.  Once the pipelines are abandoned, Contractor shall remove all those abandoned within the Right-of-Way that are in conflict with the work and dispose of all pipes off the project limits.

202-2.04  Removal of Pavement, Sidewalks, Curbs, Etc.  Add the following:  This work shall also include asphalt curbs designated for removal.

Pavement removed may be used in the construction of the embankment.  It shall be placed away from wetlands, and no closer than 300 feet to a stream.  The broken asphalt pieces shall be six inches or less in maximum dimension.

For disposal of removed asphalt, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529.

202-3.01  Method of Measurement.  Add the following:  The eradication of the foundations and structures will not be measured, but the Engineers approval of the completed work will be accepted for Lump Sum Payment under Item 202(1), Removal of Structures and Obstructions.

Removal of fence will be measured by the linear foot for the actual amount of fence taken down, disposed or delivered to the owner, regardless of the type or height.

Removal of gas pipe will be measured by the linear foot of pipe, regardless of size, that is  removed and shall include all labor, materials and equipment required to remove and dispose of the pipes.

The removal of storage tanks (either septic or fuel) will be measured for payment by each tank removed and disposed of in a manner consistent with DEC regulations and will include excavation, purging if required, backfill of the resultant hole, and any processing or removal, if necessary of fuel contaminated soils around the tanks.

Ground water well abandonment will be measured for payment for each well capped in a manner consistent with DEC regulations.

202-4.01  Basis of Payment.  Delete Item 202(6), Removal of Manholes and add the following pay items:

Pay Item No.       Pay Item             Pay Unit

202(6A)    Removal of Storm Drain        Each

Manholes

202(6B)   Removal of Sanitary Sewer      Each

Manholes

202(12)      Removal of Fence        Linear Foot         202(16)     Removal of Gas Pipe      Linear Foot

202(18)   Removal of Storage Tanks       Each

202(23) Ground Water Well Abandonment    Each

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01  Description.  Add the following:   Linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

Pathway linear grading shall include all the preparation and excavation necessary to construct a pathway or sidewalk when it is outside of the roadway slope limits, as shown on the plans, or as field located by the Engineer.

Pole shoring will include all work required to maintain utility poles in a safe and serviceable condition during excavation and backfill operations, the subsequent removal of any shoring required, and then the backfill and compaction of the void after extraction.

Standard Modifications

203-2.05  Borrow.  Add the following:  Borrow, Type A, B or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B or C, respectively.  (5/12/89)

Special Provisions

203-3.02  Embankment Construction.  Delete the first sentence of the tenth paragraph, and substitute the following:  Roadway embankments shall be placed in horizontal layers not exceeding eight inches in thickness measured before compaction.  Each layer of classified material shall have its joint offset from the joint below, longitudinally by one foot and transversely by 20-feet.

Add the following:  Where the plans call for placement of selected material and excavation is required, the existing material may be left in place if tests determine that it will meet the appropriate selected material requirements.  Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104, Scope of Work.  (9/1/89)

203-3.03  Construction of Embankment with Moisture and Density Control.  Add the following:  Compactors with vibrators engaged will not be allowed on the project.

203-3.05  Pole Shoring.  Add the following subsection:  Pole shoring will be required of the Contractor prior to any excavation within 10 feet of a utility pole.  This shoring may be provided by a line truck, or require one, two  or three steel H piles to be driven along the side of each pole to a  minimum depth of 20 feet below the deepest excavation or to refusal.

The shoring pile shall be HP 10 x 42 steel piles of the required length.  The minimum friction bearing capacity for each member shall be 10 tons.  The Contractor shall maintain a record of equipment and field measurements to insure the required bearing strength.  Attachment of the pole to the shoring pile shall be with

4 x 3/16-inch galvanized steel bands at two locations above grade.  Wood wedge spacers shall be installed between the pole and the H-pile.

As soon as the Contractor has determined the method, extent and scheduling of excavation around all poles within the project, but no later than 30 days after receipt of Notice-to-Proceed, he shall schedule a field meeting with the Engineer and owning Utility.  The Utility will determine the number of poles to be shored with a line truck, one pile, two piles,  or with three equally space piles based upon the Contractors intended operation.  These poles will then be marked, and the Contractor shall provide the appropriate shoring after 24 hour written notification to the Utility.  If for any reason the Contractor changes his operations to further jeopardize the pole, he will be required to immediately provide a three pile shoring configuration, at no additional payment.

After backfilling around the poles and the aerial system is retired, the Contractor shall remove the support piling and the utility pole.  He may either remove the steel shoring in total, or he may cut it at the bottom of Selected Material, Type A.  All wooden materials within and below the structural section shall be removed.  The resultant void shall be excavated to 4 feet below subgrade and backfilled in accordance with subsection 203-3.03, Construction of Embankment with Moisture and Density Control.  Wooden materials outside the structural section may be cut off 12-inches below final grade.  Backfill and compaction shall be in accordance with this Section.  The shoring will become the property of the Contractor.

203-4.01  Method of Measurement.  Delete the sixth paragraph in its entirety and substitute the following:  Obliteration of roadway will be measured by the square yard of obliteration in accordance with the requirements of Section 109, Measurement and Payment.

Add the following:  No deduction from the excavation quantities will be made for pavement removed under Item 202(2), Removal of Pavement.

Measurement of linear grading, whether flat bottom or "V" ditch, will be measured for payment by the station along the center of the ditch for each ditch so designated, constructed and accepted by the Engineer.

Measurement for the pathway/sidewalk linear grading will be along the center of the facility when constructed as stated above.

The pole shoring will be measured once per each such pole designated and actually protected in the field as described above.

Standard Modifications

203-5.01  Basis of Payment.  Change Pay items 203(5), (6) and (7) to read:  Borrow, Type _____.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)

Special Provisions

203-5.01  Basis of Payment.  Add the following:  Linear grading for ditches, pathways and sidewalks will be paid by the station; and payment so made will be full compensation for furnishing all equipment, labor, tools and incidentals to provide the preparation, excavating and shaping necessary to complete the work.  The materials used for the construction of the pathway or sidewalk will be paid under their respective pay items.

Payment for pole shoring will be full compensation for all labor, equipment, and materials required to protect the utility pole during construction.  Removal of pole shoring will include removing the pile(s) and backfilling and compacting the shoring hole after removal.  Poles not requiring special protection will not be included for payment under these items.  Payment for removal of the utility pole will be made under Section 681, Electrical Power Relocation.

Add the following pay items:

Pay Item No.          Pay Item              Pay Unit

203(17)        Ditch Linear Grading        Station

203(18)       Pathway Linear Grading       Station

203(20)         Pole Shoring with            Each

Line Truck

203(21)         Pole Shoring with            Each

Single Pile

203(22)    Pole Shoring With Two Piles       Each

203(23)         Pole Shoring with            Each

Three Piles

203(24)      Removal of Pole Shoring         Each

203(25)      Obliteration of Roadway      Square Yard

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01 Materials.  Add the following: Bedding and backfill materials within the structural section shall meet the requirements for the applicable lift of material.  Native material shall be utilized for pipe bedding and backfill outside the structural section if the material meets the minimum requirements of Selected Material, Type C.  Pipe bedding shall also pass a 3-inch sieve.

204-3.01  Construction Requirements.  Add the following to the third paragraph:  Native material utilized for pipe bedding and backfill outside the structural section shall be placed in layers and compacted as approved by the Engineer.

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01  Materials.  Delete the second sentence of the first paragraph.

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-2.01  Composition of Mixtures.  Add the following to the first paragraph after the first sentence:  The Contractor shall submit, in writing, the proposed ratios at which he plans to blend the various aggregate stockpiles in order to achieve the target gradation submitted.

Add the following to the tolerance table of the fourth paragraph:

Sieve Size          Tolerance

1/2 inch               + 7

No. 80                 + 4

Add the following after the tolerance table of the fourth paragraph:  The asphalt cement and aggregate submitted by the Contractor for Asphalt Concrete, Type IIA Job Mix Design approval as tested according to Alaska T-17 shall conform to the following.  The asphalt content of the mix will be expressed as a percentage of the total mix.

Marshall Stability, pounds, minimum    1500

Voids, Total Mix %                      3-5

Flow Value                              8-16

Compaction Blows per Side                75

Voids in Mineral Aggregate, %, min.     15.0

The Voids in mineral aggregate is calculated by the following formula:

GmbPs

Voids in mineral aggregate = 100 - (____)

Gsb

Where:

Gsb = bulk specific gravity of aggregate

Gmb = bulk specific gravity of compacted

mixture (ATM T-18), and

Ps = aggregate, percent by total weight of

mixture

The Contractor should be cautioned that addition of crushed fines may be required to meet the Voids in the Mineral Aggregate requirement.

The Alaska Test Method T-17 section E.4.a shall be deleted and the following should be substituted:

a.	From the data curves, asphalt contents are determined which yield the following:

1.	Maximum Unit Weight

2.	Maximum Stability

3.	Voids Total Mix at 4 percent

Add the following:  Temporary pavement may, at the Contractor's option, be Asphalt Concrete, Type III, as detailed on Table 703-3 in Subsection 703-2.04, Aggregate for Plant Mix Asphalt Pavement.

401-2.04  Asphalt Materials.  Add the following:  AC-5 asphalt cement will be used for the new asphalt concrete pavement mix.

401-3.11  Spreading and Finishing.  Add the following to the third paragraph:  Temporary pavement shall be placed in one lift.  Asphalt Concrete Type IIA shall be spread and compacted in two layers of approximately equal thickness.  The final lift shall not be placed until the initial lift throughout contiguous segments has been placed and accepted, and all adjacent curb has been poured and cured for 7 days.  Final lift paving shall be continuous, where possible, to keep the number of transverse joints to a minimum.  No temporary pavement markings will be allowed on the final lift pavement.

Add the following:  When pavement marking tape for striping is required, the longitudinal joints on the final lift shall be offset 12-inches from the plan lane lines.  The Contractor shall submit a Paving Plan for the Engineer's approval before starting this work.  The Paving Plan shall be submitted to the Engineer one week prior to initiating the paving operation.  The plan shall consist of, but not be limited to the following:

1.	Manuals for the paving machine and the rollers.

2.	Traffic Control Plan for the paving operations.

3.	Pavement widths to be placed.

4.	Traffic marking installation plan.

401-3.12  Compaction.  In the second paragraph, delete from the first sentence:  "...(94% at joints)...".

401-3.14  Pavement Samples.  Delete the third sentence of paragraph one and substitute the following:  Each sample shall be one core having a minimum diameter of six inches.

401-4.02  Contract Price Adjustments.  Add the following to the first paragraph:  Asphalt Concrete used for temporary pavement will not be subject to price adjustments.

Add the following to the sixth paragraph:  Sampling will be done in front of the screed just prior to final placement or from the mat prior to breakdown rolling.

Delete the seventh paragraph and substitute the following:  Sampling for determination of oil content will be from in front of the screed just prior to final placement or from the mat prior to breakdown rolling.

In the eighth paragraph, add the following:  On projects consisting of more than 5000 tons, density evaluation shall be as follows:

For the purpose of evaluating the density of the material, a lot will be represented by fifteen tests, three for each sublot.  Each sublot sample will consist of three cores randomly sampled throughout the sublot.  A representative single density value for each sublot will be obtained by averaging the three sublot density test valves.  This representative density shall become the density value reported for the sublot and the value used to evaluate individual lots for acceptance and price adjustment.

In the ninth paragraph, delete the second sentence and substitute the following:  Prior to computing a reduction in price, the validity of the failing test results for asphalt content and gradation tests shall be ascertained in accordance with ATM T-19.  Tests for density compliance will not be subject to ATM T-19 and no retests will be allowed.

401-5.01  Basis of Payment.  Add the following:  Anti-stripping additives will be paid on a contingent sum basis at a rate of $3.75 per 0.25 percent additive per ton of asphalt cement.

Temporary pavement will be paid by the ton when placed as approved by the Engineer.  No payment will be made for the asphalt cement, anti-stripping additive, or maintenance, nor will price adjustments apply to this item.  Removal of temporary pavement will be paid under pay item 202(2), Removal of Pavement.

Add the following pay item:

Pay Item No.              Pay Item             Pay Unit

401(6)            Temporary Pavement           Ton

SECTION 402

TACK COAT

Special Provisions

402-3.04  Dilution of Asphalt Material.  Add the following:  CSS-1 Emulsified Asphalt used for tack coat may be diluted not more than 50 percent water by weight or volume at the Engineer's direction.  The determination of this ratio shall be accomplished by weighing the distributor prior to adding water, by sticking the tank, or other means suitable to the Engineer.  Emulsified asphalt as manufactured is approximately 60 percent oil and 40 percent water.  Any required dilution is additional water.

402-3.05  Application of Asphalt Material.  Modify the application rate given in the first paragraph from "0.05 to 0.10 gallons" to "0.05 to 0.15 gallons".

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-1.01   Description.  Add the following:  This work shall also consist of construction of cast-in-place reinforced concrete retaining walls and precast concrete wall panels as shown on the plans.  All required excavation and backfill for the retaining walls shall be in accordance with Section 205, Excavation, Backfill, and Foundation Fill for Structures.

501-2.01  Materials.  Add the following:  Reinforcing steel shall conform to the requirements of Section 503, Reinforcing Steel.

Insulation Board shall conform to the requirements of Section 635, Insulation Board.

Materials for dampproofing shall be the type as shown on the plans, and material for geotextile wall drains shall conform to Section 729, Geotextiles.

Concrete Surface Treatments shall conform to Section 510.

501-3.01  Proportioning.  Revise this subsection as follows:  In Table 501-1, Class A Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S and W concrete.  (9/1/89)

501-3.02  Batching.  Add the following to item No. 5, Batching:  The Contractor shall furnish the Engineer with a list of all ingredients, their individual weights and the moisture content of the various aggregates, and the individual truck water meter reading when batched, for each truck load or batch of concrete supplied.

501-3.03  Backfill.  Add the following:  Where weepholes are shown on the plans for cast-in-place concrete walls, not less than one cubic foot of coarse concrete aggregate as approved by the Engineer, securely tied in a burlap bag, or an acceptable substitute, shall be placed in the backfill at each hole.  The bag of filter material shall extend at least 0.5 feet above the hole.

Add the following:  After stripping the forms, the back of the concrete retaining walls shall be mopped with hot liquid asphalt, and after drying, geotextile drain shall be placed against the wall.

501-3.06  Placing Concrete.  Delete the last sentence under Item 2., Pumping Concrete, and substitute the following:  Concrete samples for testing will be taken at the discharge end of the pipe.  The Contractor shall provide the necessary sample of concrete at the direction of the Engineer.

501-3.11  Precast Concrete Wall Panels.  Add the following subsection:  Precast concrete wall panels shall be handled, stored, and installed in such a manner that there is no damage to any portion of the panel, including the facia.

501-4.01  Method of Measurement.  Delete the fourth paragraph.

Add the following:  The quantity of panels to be paid will be the actual face area of all precast concrete wall panels accepted in place.  Cast-In-Place concrete walls will be measured by the cubic yard of concrete placed.

501-5.01  Basis of Payment.  Add the following:  The facia and anti-graffiti protection for the cast-in-place concrete walls and precast concrete wall panels will be paid under Items 510(1), Aesthetic Facia, and 510(2), Graffiti Protection, respectively.

Precast concrete wall panels will be paid for at the contract price per square foot and will be full compensation for all labor, materials and equipment to cast and erect the panels.

Payment for Cast-in-Place Concrete Walls will be full compensation for all labor, equipment and materials, including excavation, reinforcing steel, hot liquid asphalt, geotextile  wall drain and porous backfill required to complete the walls in accordance with the plans.

Add the following Pay Items:

Pay Item No.             Pay Item            Pay Unit

501(8)     Cast-in-Place Concrete Walls   Cubic Yard

501(9)     Precast Concrete Wall Panels   Square Foot

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01  Description.  Add the following:  This work will include the epoxy-coating of appropriate reinforcing steel bars.  All reinforcing in the exposed vertical face of a retaining wall facing the roadway, and as noted on the plans shall be epoxy-coated.

Standard Modifications

503-3.05  Splicing.  Delete the first and second paragraphs and substitute the following:  Lap splices for reinforcing bars shall be as shown on the plans or as directed.  (5/12/89)

Special Provisions

503-5.01  Basis of Payment.  Add the following:  If epoxy coating the reinforcing steel is required, it will be a subsidiary obligation and no separate payment will be made.

SECTION 505

PILING

Special Provisions

505-2.01  Materials.  Add the following:

Walls IV and V stay-in-place     SPZ17, A572 GR50

Sheet Pile

Wall XII Sheet Pile              SPZ17, A328

The steel sheet piling for Wall IV, V, and XII shall be of the continuous interlock type and shall be furnished with suitable connecting and corner pieces if applicable.  The steel sheet piling for Walls IV and V may be either new or used in good condition.

505-3.09  Driving Piles.  Add the following:  The steel sheet piling for Walls IV, V, and XII shall be driven, braced as shown on the plans, and cut off as specified under Section 505-3.11, Cutting Off Piles.  The steel sheet piling shall be driven with a vibratory pile driver that has a driving force of not less than 10 tons.

The steel sheet piling for Walls IV, V, and XII shall be driven with equipment and by methods designed to minimize noise and disruption to any surrounding inhabitants, and to not cause damage or distress to nearby existing structures.  All sheet pile installation shall be conducted between 9:00 a.m. and 6:00 p.m.  No sheet pile installation shall be performed on Sundays or holidays.

The Contractor shall protect the Nob Hill Condominiums from pile driver spray or splatter.

505-3.15  Sheet Pile Stay-in-Place Forms.  Add the following subsection:  Walls IV and V have stay-in-place sheet pile at the back of the concrete retaining wall to act as a form wall because of the existing structures near the retaining walls.  The Contractor shall use extreme caution when installing the sheet pile  for retaining Walls IV and V.  After installing the stay-in-place sheet piling, the Contractor shall excavate to the plan bottom of wall footing and promptly construct the temporary bracing strut system.  The time from start of excavation in front of the wall until the construction of any one brace (struts) location shall not exceed 12 hours, and the bracing system shall not be removed until the wall has been cured as specified under Section 501, Structural Concrete.  The design and construction details for the bracing system for Walls IV and V shall be submitted to the Engineer for approval at least 21 days prior to the start of any work on Walls IV and V.

505-4.01  Method of Measurement.  Delete the last paragraph and substitute the following:  In determining the area of sheet piling, the horizontal measurement will be made along the alignment of the sheet piling without any allowance for the structural shapes of the separate sections of the sheet piling.

SECTION 507

BRIDGE RAILING

Special Provisions

507-1.01  Description.  Add the following:  For balustrade handrailing for pedestrians and bicyclists, specifications for bridge railing shall apply.

507-4.01  Method of Measurement.  Delete in its entirety and substitute the following:  The pay quantity for balustrade handrailing paid will be that length actually installed and approved by the Engineer from out to out of the end posts.  It will include all rail

elements, rail posts, brackets, handicapped handrail as required, and all fastenings and anchors necessary to support the handrailing.

507-5.01  Basis of Payment.  Add the following Pay Item:

Pay Item No.        Pay Item         Pay Unit

507(5-__)     __-Inch Balustrade    Linear Foot

Handrailing

Add the following Section:

SECTION 510

CONCRETE SURFACE TREATMENTS

Special Provisions

510-1.01 Description.  This work consists of providing an aesthetic facia on all precast and cast-in-place concrete walls.  All concrete retaining walls shall use form liners.  In addition, all walls and surfaces designated on the plans shall be protected with a sealer to prevent unwanted graffiti.

510-2.01  Materials.  Reinforcing steel shall meet the requirements of Subsection 709-2.01, Reinforcing Steel.

Contractor shall provide standard reusable, non-porous form liners conforming to the pattern for Burke Form Liner No. BG 312, Waterfall.

Anti-graffiti protection shall be a two step system designed specifically for this use consisting of a single component clear acrylic base coat over which a clear urethane finish coat are applied.  This material is not a sealer or vapor barrier.  No appreciable discoloration will be allowed.  The Contractor should be aware that these materials require special precautions, and shall be applied by trained personnel.

510-3.01  Aesthetic Facia.  Form liners shall be used in all retaining wall forms which have exposed surfaces.  The wall dimensions and concrete quantities provided on the plans are minimum and do not include allowances for the thickness of the form liners which must be accounted for by the Contractor.   The liners will cover the majority of the form with a minimum of 2-inches and a maximum of 12-inches between the edge of liner and the finished top of the wall, pathway or original ground grade at the bottom, and edge or expansion joints of the wall on the sides.  The Engineer shall approve the liner placement on the form prior to the concrete pour.

510-3.02  Graffiti Protection.  All concrete surfaces shall have set at least 28 days before any coatings are used.  The base coat shall be applied with a roller or sprayer in accordance with the manufacturers recommendations.  After 72 hours, two coats of the finish coat shall be applied according to the manufacturer's instructions.  Appropriate masking may be required.

The work shall be scheduled so that graffiti protection is in place prior to seasonal suspension of work.

510-4.01 Method of Measurement.  Aesthetic facia will be measured by the square foot.

Anti-graffiti protection shall be measured by the square foot of surface area.

510-5.01 Basis of Payment. Add the following pay items:

Pay Item No.      Pay Item          Pay Unit

510(1)       Aesthetic Facia    Square Foot

510(2)     Graffiti Protection  Square Foot

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-1.01  Description.  Add the following:  This work shall also consist of the construction of slotted drain pipe as shown on the plans.

603-2.01  Materials.  Add the following:  Bituminous Coated Corrugated Steel Pipe shall be AASHTO M190, Type D, fully paved. Steel or aluminum pipe having a manning's n valve of 0.012 or less may be substituted, for all locations except Caravelle Street storm drain line which shall remain Bituminous Coated Corrugated Steel Pipe, Type D.

Culvert marker posts shall be a nonflammable rigid fiberglass reinforced polymer composite with the dynamic flexibility to self-erect after repeated vehicular impacts.  The color shall be blue with no other markings.  The nominal 2-1/2 by 72-inch post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9-inches.  It shall remain resilient in temperature extremes of -140 to +140 degrees F, and be unaffected by ultra violet exposure.

603-3.02  Bedding.  Add the following:  Bedding for slotted drain pipe shall be in accordance with Standard Drawing D-01.

603-3.06  Culvert Marker Posts.  Add the following subsection:  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30-inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or at the locations as directed by the Engineer.  42-inches of post shall remain above the ground after driving.

603-4.01  Method of Measurement.  Add the following:  Excavation for pipe items will not be measured for payment but will be subsidiary to the pipe item.  Bedding and backfill for pipe will be measured and paid for under the respective items listed in the bid schedule.

Culvert marker posts will not be measured for payment.

603-5.01  Basis of Payment.  Delete the last paragraph.

Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to the pipe item.

Add the following pay item:

Pay Item No.         Pay Item           Pay Unit

603(23-__)    __-inch Slotted Drain Pipe  Linear Foot

SECTION 604

MANHOLES, INLETS, AND

CATCH BASINS

Special Provisions

604-3.01  Construction Requirements.  Add the following to the beginning of the second paragraph.  All access manholes, regardless of type, that fall within a concrete sidewalk or asphalt pathway shall be constructed with a frame and cover cast with a rough cobbled grit surface, or specifically designed to hold fill.  The recessed covers shall be depressed a minimum of 1-inch, and be suitable for concrete or asphalt fill, as applicable.

Delete the first sentence in the third paragraph and substitute the following:  Invert channels shall be constructed in all manholes utilized for sanitary sewers to provide a smooth and continuous channel directing the effluent into and with the flow of the receiving sewer.

An invert channel shall be provided when the difference in elevations of the inlet and outlet pipes is between 0.6 and 6-inches.

Add the following to the fifth paragraph referencing the reconstruction of manholes:

5.	The work necessary to rotate the cone or reducing slab to align the manhole as detailed on the plans.  To align the access stairs, the Contractor will have the option of rotating the barrel sections or installing new steps.

6.	The work and materials necessary to salvage the frame and grate, to remove and dispose the reducing slab and adjusting rings, and to install a new cover slab.

Add the following:  Those manholes which by design must fall within the paved roadway surface shall be aligned such that the casting will not be in the wheel tracks of any driving lane, or the flow line of the gutter pan.

Standard drainage structure steps shall be cast during structure pour or installed before concrete hardens.

Where the plans indicate the top of manhole elevations, the Contractor shall field verify the exact elevations.  Rotating and adjusting manholes to the required location and grade shall be incidental to the cost of installing manholes.

When new pipe is installed in an existing manhole, a hole shall be cleanly cut at the invert elevation given on the plans and 2-inches larger than the outside diameter of the new pipe.  The joint shall then be grouted with non-shrinking cement mortar.  The downstream pipe in manholes shall be screened to prevent mortar or other debris from entering the system.

All curb inlet structures shall have a 3-inch formed hole approximately 2-feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  The Contractor shall be responsible for keeping the openings functional, which may require temporary dikes, RMC extensions, etc, as necessary.  These holes shall be filled with grout upon final paving.

Each precast concrete barrel section, precast concrete eccentric cone section, concrete adjusting ring, and manhole frame set, installed, reconstructed or relocated shall be sealed by use of a premolded plastic gasket pipe joint sealer manufactured in accordance with Federal Specifications SS-S-210A or AASHTO M-198.  Use and installation of premolded plastic gaskets for manhole construction shall be strictly in accordance with the manufacturer's printed instructions.  Gaskets shall be trimmed flush with the inside of the manhole.

Connections to existing sanitary sewer manholes will be allowed only after all portions of the Contractors work tributary to the connection point have been cleaned, flushed, tested and inspected.  Under certain conditions, connection prior to the completion of the system may be permitted subject to the Engineers written approval and the provision of suitable and adequate debris and sand traps and sumps upstream from the connection.

604-4.01   Method of Measurement.  Add the following:  Invert channels shall be considered an incidental part of a sanitary sewer manhole, and not be measured for payment.

Frames, grates and lids will not be measured for payment.

604-5.01  Basis of Payment.  Add the following: Frames, grates and lids are subsidiary to the drainage structure.

Delete pay item 604(1), Storm Sewer Manhole and add the following pay item:

Pay Item No.         Pay Item		     Pay Unit

604(1)      Storm Drain Manhole,        Each

Type ________

SECTION 606

GUARDRAIL

Special Provisions

606-3.04   Removal and Disposal of Existing Guardrail.  Delete in its entirety and substitute the following:  All posts, rail and hardware from the existing guardrail designated for removal shall be salvaged and delivered to the State Maintenance Yard at 5700 Tudor Road, Anchorage.

SECTION 607

FENCES

Special Provisions

607-1.01  Description.  Add the following:  Work under this Section shall also include construction of noise barrier, fences, temporary fences, picket fences and bollards.  These fences shall be built at the locations and to the dimensions indicated on the plans or as directed by the Engineer.

607-2.01  Materials.  Add the following:  Timber used in the wood noise barrier, fence and bollards shall be as follows:

Posts           Douglas Fir-Larch         Dense No. 1

Stringers       Douglas Fir-Larch               No. 2

Cedar Boards    Western Red Cedar        1-inch nominal

(rough sawn both sides)     thickness

Bollards        Douglas Fir-Larch         Dense No. 1

The noise barrier and fence posts and stringers and bollards shall be treated in accordance with Section 714, Preservatives and Preservative Treatment Processes for Wood Materials.  Any field cutting of post ends shall require an application of pentachlorophenol.

All cedar boards for noise barriers and fences shall be coated with a creosote based stain or 20 percent polyurethane base semi-transparent stain to be applied at a rate of one (1) gallon per 100 square feet.  The stain shall be Red Cedar in color, except for fences V-2 and V-3 which shall be a gray color matching the Nob Hill Condos, as approved by the Engineer.  The stain shall be furnished by a manufacturer and a manufacturers certificate attesting to the quality of the stain shall accompany the shipment.

Picket fence shall use materials as designated on the plans and shall be painted white, using a flat, oil based exterior stain.  The paint shall be applied in two coats, the first coat at a rate of 250 sq. ft. per gallon and the top coat at a rate of 350 sq. ft. per gallon.

Temporary fence shall be orange, 4-feet high, with posts as recommended by the manufacturer and shall be one of the following, or equivalent:

1.	"Safety Fence" as manufactured by Service and Materials Company, Inc., 2200 South J. Street, Elwood, Indiana 46036, (317)552-3352.

2.	"Flexible Safety Fencing" as manufactured by Carsonite, 1301 Hot Springs Road, Carson City, Nevada 89706, (702) 883-5104.

3. 	"Safety Fence" as manufactured by The Plastic Net Corporation, 1048 Niagara Street, Buffalo, New York 14213, (716)883-4400.

607-3.01  Construction Requirements.  Add the following:  The faces of the wood noise barriers shall be constructed of tongue and groove or shiplap boards, or over-lapped plywood sheets.  Boards shall be fastened to each stringer with one 10d galvanized nail per each 2-1/2 inches of board width, with two nails minimum per board.  The vertical portion of the plywood shall be a single continuous sheet without horizontal joints, and the vertical joints shall be made over a secured nailer.

Posts for the picket fence shall be placed in excavated holes.  Depth of embedment shall be as shown on the plans unless otherwise directed.  The space around the posts shall be backfilled to finish ground with selected earth or sand, free of rocks or deleterious material, placed in layers approximately 6 to 12 inches thick, and thoroughly compacted.  Surplus excavated material shall be disposed off the project.

Add the following to the fourteenth paragraph:  Reconstructed fences shall have new posts and foundations installed.

607-4.01  Method of Measurement.  Add the following:  The noise barrier and fence pay items will be measured by the square foot, with measurement being made of the height shown on the plans and the length from end post to end post.  Picket fence will be measured by the linear foot.  Temporary fence will be measured by the linear foot.

Application of wood preservatives, stains and paints will not be measured for payment.

Bollards will not be measured for payment.

607-5.01  Basis of Payment.  Add the following:  Payment for Noise Barrier will include either the concrete encased posts or the wall mounting brackets as shown on the plans.

Posts required for the noise barrier or any of the fence items will not be measured for payment but will be subsidiary to the particular pay item.

All work necessary to provide materials, equipment and labor to apply wood preservatives, stains and paints will not be paid for directly, but will be subsidiary to the appropriate fencing item.

The bollards to be installed at the end of Town and Country Drive will not be paid for directly, but will be subsidiary to the Town and Country noise barrier.

Add the following Pay Items:

Pay Item No.            Pay Item            Pay Unit

607(7)           Noise Barrier           Square Foot

607(8)               Fence               Square Foot

607(9)           Picket Fence            Linear Foot

607(10)         Temporary Fence          Linear Foot

SECTION 608

SIDEWALKS

Special Provisions

608-1.01  Description.  Add the following:  This work also consists of construction of asphalt pathways, median and driveways paving in reasonably close conformity with the plans.

Bus stop shelter pads shall be placed at those bus stops indicated on the plans or as directed by the Engineer.

Concrete sidewalk or asphalt sidewalk shall include the paved apron around pedestrian push-buttons and fire hydrants, and the approach to the bus stop shelter pads.

608-3.01  Concrete Sidewalks.  Delete the sixth paragraph, and substitute the following:

Joints.  Transverse expansion joints shall be filled with 1/4-inch thick premolded expansion joint filler and shall be placed at intervals not to exceed 30-feet.  The sidewalk shall be divided into sections by contraction joints formed by a jointing tool or other acceptable method.  These contraction joints shall be placed every 10-feet and shall extend into the concrete at least one third of the depth and shall be approximately 1/8-inch wide.

608-4.01  Method of Measurement. Add the following:  Asphalt concrete utilized in asphalt pathways, medians and driveways paving will be measured by the ton in accordance with Section 109, Measurement and Payment.  Asphalt cement will not be measured for payment.

Additional asphalt pavement used for matching existing surfaces such as paved parking lots behind a new sidewalk/pathway will be measured and paid under this Section.

Bus stop shelter pads will be measured by each unit installed and approved by the Engineer.

608-5.01  Basis of Payment.  Add the following:   Asphalt cement will not be paid for directly but will be subsidiary to Item 608(8) Asphalt Pathways, Medians and Driveways.  Asphalt concrete used for Asphalt Pathways, Medians and Driveways will not be subject to price adjustments.

Bed Course materials, as detailed on the plans, will be furnished, placed and paid under their respective bid items.

Add the following Pay Items:

Pay Item No.           Pay Item              Pay Unit

608(8)      Asphalt Pathways, Medians       Ton

and Driveways

608(10)      Bus Stop Shelter Pads          Each

SECTION 609

CURBING

Special Provisions

609-4.01  Method of Measurement.  Add the following:  Bumper curbs will be measured per each 7-foot section.

609-5.01  Basis of Payment.  Add the following pay item:

Pay Item No.            Pay Item             Pay Unit

609(7)              Bumper Curb              Each

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01  Materials.  Add the following to the end of the first sentence of the fifth paragraph, "and the Alaska Traffic Manual."

Delete the seventh paragraph and substitute the following:  All metal sign posts other than perforated steel tubes and wide flange posts shall be equipped with slip bases, unless multi-directional breakaway load concentration couplings are called for on the plans.  Wide flange posts shall always be equipped with multi-directional breakaway load concentration couplings.

615-3.01  Construction Requirements.  Add the following:  All existing sign panels, posts and hardware not required for the new roadway, as determined by the Engineer, shall be removed and delivered to the DOT-PF Maintenance Station at 5700 E. Tudor Road, Anchorage.

615-3.02  Sign Placement and Installation.  Add the following:  Existing signs shall not be removed until new signs providing the same information to motorists have been installed.  If necessary, they may be temporarily relocated to a location approved by the Engineer.  They shall be maintained until they are no longer needed.

615-5.01  Basis of Payment.  Add the following:  Maintaining existing signs until they are no longer needed and temporary relocation of existing signs will not be paid directly, but shall be subsidiary to Item 615(1), Standard Signs.

SECTION 616

CULVERT THAW PIPE

AND THAW WIRES

Special Provisions

616-2.02  Thaw Wire.  Delete this subsection and substitute the following:  All materials shall conform to the applicable sections contained in Appendix B, Thaw Wire Specifications.

616-3.02  Thaw Wire Construction Requirements.  Delete this subsection and substitute the following:  Thaw wire shall be constructed in accordance with the applicable sections contained in Appendix B, Thaw Wire Specifications.

616-4.01  Method of Measurement.  Delete the last two paragraphs, and add the following:  Furnishing thaw wire will be measured by the linear foot, for hot and cold leads from the load center to the end of the run, and shall include conduit and hangers, termination posts, junction boxes and miscellaneous hardware and accessories as required.  Load centers, to include pole, meter base, breaker box, storage cabinet (when required), junction box, risers, main and branch breakers, power connects (if applicable), and any other accessories, will be measured and paid under Section 661, Electrical Load Centers.

616-5.01  Basis of Payment.  Add the following:  Load centers for thaw wire will be paid under Section 661, Electrical Load Centers.

SECTION 618

SEEDING

Special Provisions

618-1.01   Description.  Delete this subsection and add the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded.  This work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01  Materials.  Add the following:  Mulch shall conform to the requirements of subsection 727-2.01.

618-3.01  Soil Preparation.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be covered with topsoil in accordance with Section 620 and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as topsoil is placed on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach on the wetlands.  The performance of this work is incidental to seeding and will not be paid for directly.

618-3.03  Application Method.  Add the following:  Seed, mulch and fertilizer shall be applied as shown in the following table per 1,000 square feet.  If the hydraulic method for seed and mulch is used, it shall be made in one application.  All fertilizer shall be applied by the hydraulic method.

SEED MIX, TYPE A                                                                                     Application

Item                Ingredients             Rate Lbs/MSF

Seed for		Bering Hairgrass (Norcoast)	0.40 lbs.

urban		Red Fescue (Arctared)		0.20 lbs.

erodible		Kentucky Bluegrass (Nugget)	0.30 lbs.

soils		Annual Ryegrass (Lolium)		0.10 lbs.

Mulch								35.0 lbs.

Fertilizer     20-20-10					12.0 lbs.

SEED MIX, TYPE B

Application

Item               Ingredients            Rate Lbs/MSF

Seed for      Bering Hairgrass (Norcoast)	0.40 lbs.

Wetlands      American Sloughgrass (Egan)	0.60 lbs.

Mulch                                  		35.0 lbs.

Fertilizer     20-20-10					12.0 lbs.

The Contractor shall not remove the required tags from the seed bags.

618-3.04  Maintenance of Seeded Areas.  Add the following:  A reapplication of fertilizer shall be applied with water between May 1 and September 15 of the year following seeding at a rate of one-half the initial application.

618-4.01  Method of Measurement.  Delete the second and third sentences of the second paragraph and substitute the following:  Seeding by the pound will be the number of pounds of seed (Dry Measure) accepted in place.  The amount of mulch and fertilizer used in this work, including any required reseeding will be subsidiary to this item and will not be measured separately for payment.

Delete the last paragraph.

618-5.01  Basis of Payment.  Add the following:  Fertilizer and mulch as described above, shall be included in the unit price paid for the item of Seeding.  Topsoil shall be paid under Item 620(1), Topsoil.

SECTION 620

TOPSOIL

Special Provisions

620-2.01  Materials.  Add the following:   Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

620-4.01  Method of Measurement.  Add the following:  Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1), Topsoil.

SECTION 621

PLANTING TREES AND SHRUBS

Special Provisions

621-1.01  Description.  Add the following:  After staking the clearing limits, the Engineer will flag those ornamental, deciduous and evergreen trees within this area that shall be transplanted by the Contractor.  These shall be excavated outside the drip line by approved means, the roots wrapped in burlap, and the trees temporarily stored.

In the Spring or Fall when the designated transplanting area has reached an acceptable condition, the Engineer will direct the placement of trees.

621-3.06  Plant Replacements.  Add the following:  Those stored and transplanted trees that fail to survive shall be replaced.

621-5.01  Basis of Payment.  Add the following pay item:

Pay Item No.           Pay Item              Pay Unit

621(5)         Transplanting Trees          Each

SECTION 623

BLOCK SODDING

Special Provisions

623-2.01   Materials.  Delete this subsection in its entirety and add the following:  All slopes steeper than 2:1,replacement of designated lawns, and those locations designated by the Engineer shall be sodded.  The sod shall consist of Nugget Kentucky Bluegrass.  Sod rolls shall be no less than 1-foot in width and shall include an intact root system with natural soil.

Fertilizer shall be 20-20-10 applied at a rate of 12 pounds per 1,000 square feet, and meet the requirements of Section 725, Fertilizer.

623-3.01   Construction Requirements.  Add the following after the first paragraph:  Topsoil shall be placed before rolling and staking the sod.

The Contractor shall sod the designated locations within seven (7) days of completion of each cut or fill.  If the Contractor fails to comply with this limitation, he shall repair, any erosion damage or slope sloughing that occurs, at no additional cost to the Department.

623-3.02  Block Sodding Seasons.  Add the following subsection:  All sodding shall be performed between May 15 and August 15.

SECTION 626

SANITARY SEWER SYSTEMS

Special Provisions

626-1.01  Description.  Add the following:  For the purposes of these Special Provisions "AWWU" shall mean the Anchorage Water and Wastewater Utility, Engineering Construction Section at (907) 564-2785.  This work shall include the installation and testing of sanitary sewer systems for acceptance by AWWU.  The Contractor shall also provide as-built drawings in accordance with the conditions prescribed herein.

626-3.01  Construction Requirements.  Delete the words "or flexible connection" from the third paragraph.

Delete the seventh paragraph and add the following:  Where sewer conduit constructed under this contract approaches within 10 feet horizontal clearance and is above or less than 3 feet below an existing or a new watermain, the sewer conduit shall be constructed with cast iron or ductile iron pipe for a distance of 10 feet perpendicular to and on each side of the watermain.  The Contractor shall stagger the joints for the sanitary sewer conduit such that no joint shall be closer than 9 feet from the centerline crossing of the water and sewer conduits.  In addition, the vertical separation between the water and sewer conduits shall be 18 inches minimum, outside of pipe to outside of pipe.

Add the following:

Required Clearance from Water Mains.  When it is necessary to construct a water conduit crossing below a sewer conduit or within a vertical distance of 3 feet above the sewer conduit (less than 24 inches diameter), and the sewer main is not cast or ductile iron, and provided no joint is within 3 feet horizontally of the crossing or where the Engineer may direct, the sewer conduit shall be encased in a minimum thickness of 4 inches of concrete for a distance of 10 feet perpendicular to and on each side of the water conduit.

Wire fabric or other types of wire mesh, approved by the Engineer, shall be placed around the sewer prior to encasement with concrete to minimize cracking.  Construction of concrete encasement shall be in accordance with the applicable details on the plans.

Ductile iron encasement may be substituted for concrete when approved by the Engineer.

Relocate Existing Water Main.  Where an existing water main crosses the location of the proposed sanitary sewer at an elevation to interfere with the construction of the sewer, the water main shall be raised or lowered sufficiently to permit 18 inches minimum clearance from the sewer.  The Contractor may employ either of the following methods for raising or lowering a water main.  He may raise or lower lengths of the water main as necessary on either side of the proposed sewer to allow the main to pass under or over the sewer, providing the deflection at any joint does not exceed one-half of the pipe manufacturer's recommendations, or the water main may be raised or lowered using 4 pipe bends not to exceed 22 degrees.  In special cases only, and when approved by the Engineer in advance, 45 degree bends may be used.  The method of lowering and materials to be used shall be approved by the Engineer prior to commencing work.  The Contractor shall give 48 hours notice to the Engineer, prior to any planned water shut-off.

Water lines 2 inches in diameter and smaller shall not be construed as water mains.  Any necessary lowering of water lines 2 inches and smaller shall be included under the conditions set forth in the Special Provisions for the moving and relocation of utilities occupying space within the area of construction.  With the approval of the Engineer, the Contractor may lower water lines 2 inches in diameter and smaller, but separate payment shall not be made for such lowering.  The cost shall be included under pay item 204(1), Structure Excavation For Conduits and Minor Structures.

Suspension of Work.  AWWU through the Engineer reserves the right to suspend the sanitary sewer installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

For non-emergency service interruption and suspension of service, the Contractor shall notify affected customers 7 days in advance of the scheduled suspension of service.  For emergency suspension of service, the Contractor shall provide such notice as is reasonably practicable under the circumstances.  The notification provided shall be done by leaving a door hanger at each premise notifying the customer of the date and times the suspension of service will be in effect.  Emergency suspension of service requires no notification.

If construction or excavation require the removal of any existing privately owned facilities on the provided sewer easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed 2 weeks.

Sanitary Sewer Conduit.  The outside of all ductile iron and cast iron pipe, fittings and other appurtenances used in sewer conduit construction shall be encased with one (1) layer of 8-mil thick (0.2mm) polyethylene film.  The polyethylene encasement shall be installed using any the following three methods:

Method A.

1.	Cut  polyethylene  tube  to  a length approximately 2-feet longer than the length of the pipe section.  Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

2.	 Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

3.	After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube.  Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place.  Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up the slack width to make a snug, but not tight fit along the barrel of the pipe, securing the fold at quarter points.

4.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method B.

1.	Cut  polyethylene  tube  to  a  length approximately 1-ft shorter than that of the pipe section.  Slip the tube around the pipe, centering it to provide 6-inch of bare pipe at each end.  Take up the slack width at the top of the pipe to make a snug, but not tight, fit along the barrel of the pipe, securing the fold at quarter points; secure the ends as described in Method A.

2.	Before making up a joint, slip a 3-ft length of polyethylene tube over the end of the preceding pipe section, bunching it accordion-fashion lengthwise.  After completing the joint, pull the 3-ft length of polyethylene over the joint, overlapping the polyethylene previously installed on each adjacent section of pipe by at least 1-ft; make each end snug and secure as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method C.

1.	Cut polyethylene sheet to a length approximately 2-ft longer than that of the pipe section.  Center the cut length to provide a 1-ft overlap on each adjacent pipe section, bunching it until it clears the pipe ends.  Wrap the polyethylene around the pipe so that it circumferentially overlaps the top quadrant of the pipe.  Secure the cut edge of polyethylene sheet at intervals of approximately 3-ft.

2.	Lower the wrapped pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at joints to facilitate installation of the polyethylene.  After completing the joint, make the overlap and secure the ends as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Remove or Abandoned-in-Place Sanitary Sewer Conduit.  Any existing sanitary sewer conduits, or appurtenances designated on the plans or directed by the Engineer to be abandoned-in-place or removed shall be accomplished as an incidental item of construction.  Whenever or wherever an existing sanitary sewer conduit is abandoned-in-place, the Contractor shall empty the pipe of all waste, fill the pipe with sand and plug the ends.  Asbestos concrete pipe may be either crushed or removed.  In the event of cracked or crushed lines, the Contractor shall excavate to the next joint of pipe and install the plug.  Existing sanitary sewer conduit and all other contaminated material to be removed shall be disposed of at the Municipality of Anchorage Sanitary Land Fill at the Hiland Drive Interchange.  There will be no separate payment for disposal of the contaminated material at the land fill.

Disconnect Sanitary Sewer Service Connections.  In the course of construction, the Contractor will encounter sanitary sewer service connections.  The Contractor shall disconnect at the main those sanitary sewer service lines identified on the plans for removal, and remove or abandon-in-place upstream portions of the service line.  This item of work shall include all materials, excavation, disconnection, and appurtenant materials installation. All required fittings for removing or abandoning sanitary sewer service connections shall be ductile iron, "Ty-seal" cast iron  or equivalent unless otherwise noted on the plans or directed by the Engineer.

Manhole Cover Location.  All existing manhole assemblies shall be rotated to provide the location as indicated on the plans.  The Contractor shall rotate the existing cone or reducing slab, and barrel sections in the direction shown and in accordance with Subsection 604-3.01, Construction Requirements.  The manhole base section containing the pipe carrier (inverts) shall remain in place.  These manholes are being rotated away from the driving lanes and the proposed gutter flow line.

Verification of Existing Utilities.  At a sufficient distance prior to encountering a known obstacle or pipe or tying into an existing pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled.

The cost incurred for removal and realignment of backfilled pipe sections due to improper verification methods shall be borne by the Contractor.

626-3.02  Testing.  Delete in its entirety and substitute the following:  The Contractor shall clean and flush all sanitary sewer pipe installed prior to testing and final inspection.  He shall notify the Engineer 48 hours in advance (two working days) prior to any test.  The Engineer and AWWU shall be present during all tests.  Two (2) hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or cancelled.

The Contractor shall furnish all tools, equipment, and labor necessary to complete the tests and shall verify from his own observations, or preliminary tests, that each line conforms with this specification before requesting AWWU to observe and record the actual leakage.

The Engineer may require the Contractor to repair obvious leaks even though the total length of the test section falls within the maximum allowable leakage of the test used.

No test section shall exceed 1000 lineal feet, unless approved by AWWU in writing.

All sanitary sewer pipe installed shall be subject to either an infiltration test or an exfiltration test.  In those areas where, in the opinion of AWWU, the water table is high enough to subject the pipe to a satisfactory infiltration test, it is not anticipated that an exfiltration test shall be required.  In checking leakage, there will be no allowance made for external hydrostatic head.  Where in the opinion of AWWU the water table is not high enough to provide a satisfactory infiltration test, an exfiltration test shall be required.

The type of test, either infiltration or exfiltration, shall be determined by AWWU.  The Contractor shall have the option of choosing only one method (air or water) of testing for each section tested.  All testing shall be considered a subsidiary obligation under this Contract and extra payment will not be allowed for this portion of work.

All wyes, tees, or ends of side sewer stubs and service connections shall be plugged or capped, and the plug or cap shall be securely fastened to withstand the internal test pressures.  Such plugs or caps shall be readily removable and their removal shall provide a socket suitable for extending the lateral connection.

The lengths of service connections shall be included in the computations to determine allowable leakage for the test section.

Infiltration Test.  Infiltration testing may be allowed at AWWU's option when the natural ground water table is 6-feet above the crown of the higher end of the test section.  The maximum allowable limit for infiltration shall not exceed the rate of 50 gallons per inch diameter per mile per 24 hours.

Exfiltration Test (Using Water).  On completion of a section of sanitary sewer between manholes, or otherwise, the ends of all pipe shall be plugged, including service connections, and the pipe subjected to hydrostatic pressure.  Generally all testing is to be conducted after backfilling, prior to resurfacing, and after service connections are made.

A minimum head of 6-feet of water above the crown at the upper end of the test section shall be maintained for a period of 4 hours, during which time it will be presumed that full absorption of the pipe body has taken place and thereafter for a further period of 1 hour for the actual test of leakage.  During this 1 hour period the measured loss shall not exceed the rate of 50 gallons per inch diameter per mile per 24 hours.

Infiltration or exfiltration in greater amounts than the above listed leakage rates will be cause for rejection of the sanitary sewer and all repairs necessary to meet these requirements and retesting shall be at the expense of the Contractor.  If it is apparent that the leakage test results between any two manholes is not satisfactory, then AWWU may require subsequent tests to establish the more exact location of the leakage areas.  Any section of sanitary sewer that does not meet the above requirements shall be rejected and the Contractor, at his own expense, shall make the necessary repairs to assure compliance.

Exfiltration Test (Using Air).  The Contractor shall furnish all facilities and personnel for conducting the test under the observation of AWWU.  The equipment and personnel shall be subject to their approval.  The Contractor may desire to make an air test prior to backfilling for his own purpose.  However, the acceptance air test shall be made after backfilling has been completed, and compacted.

Immediately following the pipe cleaning, the pipe installation shall be tested with low pressure air.  Air shall be slowly supplied to the plugged pipe installation until the internal air pressure reaches 4.0 pounds per square inch greater than the average back pressure of any ground water that may submerge the conduit.  At least 2 minutes shall be allowed for temperature stabilization before proceeding further.

The pipeline shall be considered acceptable when tested at an average pressure of 4.0 psi greater than the average back pressure of any ground water that may submerge the pipe, if:

The total rate of air loss from any section tested in its entirety between manholes or between manhole and cleanout structures does not exceed 2.0 cubic feet per minute, or the following table may be used as a guideline for a satisfactory test by air for pipe sizes shown:

Pipe Diameter              Allowable Pressure Drop

in Ten (10) Minutes

8-inches                         2.7 psi

10-inches                         2.1 psi

12-inches                         1.8 psi

16-inches                         1.4 psi

18-inches                         1.2 psi

24-inches                         0.9 psi

48-inches                         0.5 psi

Pressure gauges shall be incremented in not more than 1/2 pound increments for accurate tests.

If the pipe installation fails to meet test requirements, the Contractor shall determine at his own expense the source of leakage, and he shall repair (if the extent and type of repairs proposed by the Contractor are acceptable to the Engineer) or replace all defective materials or workmanship. The completed pipe installation shall meet the requirements of this test or the alternative water exfiltration test before being considered acceptable.

Safety braces shall be required to hold plugs in place and to prevent the sudden release of the compressed air.  Due to the large forces exerted by an escaping plug during the testing of the pipe, workmen shall not be allowed in the manholes in which plugs have been placed, while tests are being conducted.  The Contractors testing equipment shall be arranged in such a manner that a  pressure relief device will prohibit the pressure in the pipeline from exceeding 10 psi.

Check of Line and Grade.  After backfilling and cleaning, but before final acceptance, all sanitary sewer mains, excluding service connections, may be checked for line and grade by closed circuit television.  A full circle of light must be seen and no pipe misplaced in line or grade.  Any excess deviation shall be corrected by the Contractor at his expense prior to final acceptance of the pipe line.  AWWU acknowledges a slight deviation is anticipated in the sanitary sewer "run" from Weimer Drive (Station 35+06.80, 7.29 RT) west, where

connection to an existing pipe will require minimal horizontal and vertical deflection, impairing the "full circle of light" referenced above.

The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a semi-final inspection of the project.  This inspection will be performed in the presence of the Engineer, AWWU, and the Contractor.  Copies of a list of deficiencies, if any, indicated by the inspection will be furnished to the Contractor by the Engineer for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and at that time an acceptance inspection will be performed.

The Contractor shall take precautions to allow no sewage to enter the new sewer conduit until it has been inspected, tested and accepted for operation and maintenance by AWWU.  Any deviations shall require written approval.  The new sewer line may be tested and inspected in incremental runs, manhole to manhole.

626-3.03  As-Builts of Plans and Working Drawings.  Add the following subsection:  A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as it is actually installed.  This as-built information shall be recorded on a print of the plans affected, and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed.  Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When this sanitary sewer system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance by the owning Utility.

626-4.01  Method of Measurement.  Add the following:  Sanitary sewer cleanout will be measured by the unit from the beginning of the connecting joint of the elbow to the top of the cover, completed and accepted in final position.

Sanitary sewer pipes abandoned-in-place will not be measured for payment, however, pipes that are removed shall be measured and paid under Section 202, Removal of Structures and Obstructions.

626-5.01  Basis of Payment.  Add the following:  The unit bid prices will include all necessary excavation to the plan grade, and backfill with native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 204(1A),Structure Excavation for Sanitary Sewer Conduit.  Backfill to replace unsuitable material will be paid under Item 203(6-A), Borrow, Type A.

No separate payment for providing pumping of effluent during construction will be made but will be considered incidental to the sewer improvement.

Payment for sewer manholes will be made under Item 604(2), Sanitary Sewer Manhole, Type A.

Payment for insulation board will be made under Item 635(2), Insulation Board.

Add the following pay items:

Pay Item No.          Pay Item               Pay Unit

626(4)       Disconnect Sanitary Sewer        Each

Service

626(6-__)    ___-inch Sanitary Sewer          Each

Cleanout

626(10)      Sanitary Sewer As-Builts        Lump Sum

SECTION 627

WATER SYSTEM

Special Provisions

627-1.01  Description.  Add the following:  For purposes of these Special Provisions, "AWWU" shall mean the Anchorage Water and Wastewater Utility, Engineering Construction Section, at (907) 564-2785.  This work shall include the installation, testing, flushing, and chlorination or hand cleaning of water systems for acceptance by AWWU.  The Contractor shall also provide as-builts in accordance with the conditions prescribed herein.

In conjunction with working around and/or adjusting the AWWU water valves, the Contractor shall exercise due care.  Prior to commencement of work by the contractor, AWWU shall check and correct deficiencies which may exist in any valve or valve box.  The Engineer and Contractor shall witness the condition and location of each valve or valve box.  Failure to partake in the inspection by the Contractor will result in his forfeiting all rights to deny damages at a later date during the course of the work.  Notice that the Contractor is ready for the above inspection shall be in writing to AWWU and shall be submitted giving at least  48 hours notice.  The Contractor shall furnish a copy of the notice to the Engineer.

It shall be the Contractors responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction.  If at any time after the inspection as outlined above AWWU finds a valve or valve box damaged or rendered inoperable by the Contractor, the Contractor shall repair them at his own expense.

In scheduling his work, the Contractor is advised that all planned water interties crossing Raspberry Road west of Town & Country Place (a.k.a. Chugach View Drive) will require installation and testing and the interties be determined "used and useful" by the Engineer and AWWU prior to disrupting the 12-inch distribution main in Raspberry Road crossing Jewel Lake Road.

627-3.01  General Construction Requirements.  Add the following before the first paragraph:  AWWU through the Engineer reserves the right to suspend the water system installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

The Contractor shall furnish to the Engineer complete installation drawings for the project prior to fabrication.  All restrained joint areas shall be detailed to include fittings, piping and deflection points.  The Contractor shall provide design calculations, prepared and sealed by a licensed professional engineer, registered in the State of Alaska, for all restrained joint areas to assure adequacy, ability to resist longitudinal forces and compliance with the Contract Documents.

If construction or excavation require the removal of any existing privately owned facilities on the provided water easements, the contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed 2 weeks.

Add the following to the third sentence of the third paragraph:  "or so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled."

Add the words "and incidental" between the words "subsidiary" and "item" in the fourth paragraph.

Delete the fifth, sixth and seventh paragraphs and substitute the following:  Prior to removing or disrupting service to fire hydrants, the Contractor shall provide written notice to the Anchorage Fire Department at least 48 hours in advance of the work, with a copy to the Engineer.

Additionally, the Contractor shall notify all affected property owners, the Engineer, and AWWU 48 hours prior to interruption of any water service.  The Contractor shall provide temporary service to all those property owners with disrupted water service if the interruption exceeds 12 hours.

The Contractor shall provide any necessary fittings, valves, temporary connections or appurtenances necessary in order to maintain the water distribution system.  Any costs involved in service changeovers and providing temporary water service shall be subsidiary.  The Contractor shall be responsible for all damages incidental to interruption of service that may be due to his operations.

Prior to water system installation, the Contractor shall submit to the Engineer a detailed plan for the installation of the new water systems and for removal/abandonment of existing water systems that are to be removed or abandoned for review prior to commencement of work.  The plan shall be of sufficient detail to clearly indicate the proposed work sequence, schedules, and disruption of water service.

Add the following to the eighth paragraph:  Concrete thrust blocks or tie back rods of the type shown on the plans shall be installed where the pipe line terminates or changes alignment, utilized a tee, cross, bend, reducer, or similar fitting. Either poured-in-place or precast thrust blocks are acceptable if the minimum base area is sufficient as shown on the plans.  Concrete for the thrust blocks shall be Class A.  If the Contractor elects to use poured-in-place thrust blocks, all pipe and fittings exposed to concrete shall be double wrapped with 4-mil Visqueen or equal, prior to placement of the concrete.  Poured-in-place thrust blocks shall be cured a minimum of 7 days prior to the application of any hydraulic loads.

Add the following:

Abandon Existing Pipe.  Existing pipe shown to be abandoned shall be abandoned-in-place as an incidental item of construction.   Pipe abandoned-in-place shall be filled with a sand or cement slurry and the ends plugged or shall be crushed and backfilled as directed by the Engineer.  In those areas that the presence of existing pipe causes a conflict with new or existing utilities or facilities the pipe may be removed as an incidental item of construction.  All abandoned materials removed and not reused shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.

Disconnect and Reconnect Water Service.  In the course of construction, the Contractor will encounter water service pipe requiring disconnection from mains to be abandoned or removed, and reconnection to new water conduit facilities. The Contractor shall disconnect the existing water service, replace the service from the new main to the property line and reconnect the on-property portion of the service.  This item of work shall include all materials, excavation, disconnection, installation, reconnection, bedding, backfill, and mechanical compaction for completed services in-place.  Existing 3/4-inch services shall be replaced with 1-inch services from the main to the property line and shall have a 1-inch to 3/4-inch reducer installed at the property line reconnection point.  All service lines 2-inches and smaller shall be constructed of seamless, soft-drawn, Type "K" copper.  All service lines larger than 2-inches shall be constructed of ductile iron pipe, with two 3/4-inch tie rods installed on each service line from the main to the property line.  Connection to the water conduit of service lines larger than 2-inches shall be accomplished by AWWU connection crews, for which a minimum of 48 hours notice shall be provided prior to the required time of connection.

Water Service Connection.  This item of work shall include all materials, excavation, installation, bedding, backfill, and mechanical compaction for completed services in place from the new or existing water main to the property line.  All service lines 2-inches and smaller shall be constructed of seamless, soft drawn, Type "K" copper.  All service lines larger than 2-inches shall be constructed of ductile iron pipe, with two 3/4-inch tie rods installed on each service line from the main to the property line.  Connection of service lines larger than 2-inches shall be accomplished by AWWU connection crews, a minimum of 48 hours notice shall be provided prior to the required time of connection.

Rights In and Use of Materials Found on the Work Site.  Unless specifically addressed otherwise in these special provisions, all existing water valves, tees, bends, and conduit (including ductile iron pipe) removed but not reinstalled, and declared "salvageable materials" shall become the property of the Contractor.

Final Acceptance.  The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a pre-final inspection of the project. This inspection will be performed in the presence of the Engineer, AWWU, and the Contractor. Copies of a list of deficiencies, if any, indicated by this inspection will be furnished to the Contractor for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and an acceptance inspection will be performed.

627-3.02  Installation of Conduit.  Add the following to the second paragraph:  However, at a sufficient distance prior to encountering a known obstacle or tying into an existing pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled. The costs incurred for removal  and realignment of backfilled conduit sections due to improper verification methods shall be borne by the Contractor.

Delete the eighth paragraph and substitute the following:  Deflections from a straight line or grade, as required by vertical curves, horizontal curves, or offsets shall not exceed 50 percent of the manufacturer's recommended maximum deflection.  If the alignment requires deflection in excess of the above limitations, the Contractor shall furnish special bends to provide angular delections within the limits allowable.  Wherever possible, the Contractor shall achieve the desired deflection by taking advantage of reduced deflections over multiple joints.  Short-radius curves and closures shall be formed by shorter lengths of pipe, bevels, or fabricated specials.

A maximum 0.2-foot deviation from design alignment and elevation will be allowed.  Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed.  All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the pipe and not by blocking or wedging up.

The Contractor shall have survey instruments such as transit and level for transferring alignment and grades from offset hubs.  He shall also have in his employ a person who is qualified to use such instruments and who shall have the responsibility of placing and maintaining such construction guides.  The Contractor shall furnish to the Engineer a copy of the surveyor's record notes for the newly-installed conduit and appurtenances.  The practice of placing backfill over a section of conduit to provide a platform for the instruments shall be subject to the approval of the Engineer.

Conduit that has the grade or joint disturbed after laying shall be taken up and relaid.  Water shall be kept out of the trench until the jointing is completed

Add the following:

Conduit Joints.  Conduit that has the grade or joint disturbed after laying shall be taken up and relaid.  Water shall be kept out of the trench until the jointing is completed.

The Contractor has the option of using either mechanical or push-on joints for conduit installed in trenches, except in those areas where restrained joints are required.  All joints shall conform to the requirements of AWWA C-600.

The Contractor will be required to use mechanical joints on all fire hydrant leads.  The Engineer may check any or all mechanical joints to assure proper torque as specified by the manufacturer.

Two electrical continuity straps shall be installed on each side joint for pipes less than 12-inches in diameter.  Straps are to be welded to a clean, dry surface.  All welds and uncoated surfaces shall be coated with a coal tar pitch to the satisfaction of the Engineer.

Conduit Wrap:  The outside of all ductile iron and cast iron pipe, fittings, valves and other appurtenances used in water line construction  shall be encased with one (1) layer of 8-mil thick (0.2mm) polyethylene film.

The polyethylene encasement shall be installed using any the following three methods:

Method A.

1.	Cut  polyethylene  tube  to  a  length approximately 2-feet longer than the length of the pipe section.  Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

2.	Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

3.	After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube.  Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place.  Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up the slack width to make a snug, but not fit along the barrel of the pipe, securing the field at quarter points.

4.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method B.

1.	Cut  polyethylene  tube  to  a  length approximately 1-ft shorter than that of the pipe section.  Slip the tube around the pipe, centering it to provide 6-inch of bare pipe at each end.  Take up the slack width at the top of the pipe to make a snug, but not tight, fit along the barrel of the pipe, securing the fold at quarter points; secure the ends as described in Method A.

2.	Before making up a joint, slip a 3-ft length of polyethylene tube over the end of the preceding pipe section, bunching it accordion-fashion lengthwise.  After completing the joint, pull the 3-ft length of polyethylene over the joint, overlapping the polyethylene previously installed on each adjacent section of pipe by at least 1-ft; make each end snug and secure as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Method C.

1.	Cut polyethylene sheet to a length approximately 2-ft longer than that of the pipe section.  Center the cut length to provide a 1-ft overlap on each adjacent pipe section, bunching it until it clears the pipe ends.  Wrap the polyethylene around the pipe so that it circumferentially overlaps the top quadrant of the pipe.  Secure the cut edge of polyethylene sheet at intervals of approximately 3-ft.

2.	Lower the wrapped pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at joints to facilitate installation of the polyethylene.  After completing the joint, make the overlap and secure the ends as described in Method A.

3.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Thrust Restraint.  Concrete thrust blocks, tie back rods or restrained joints of the type shown on the plans, or specified herein, shall be installed where the pipe line changes alignment utilizing a tee, cross, bend, or similar fitting.

Conduit ends left for future connections shall be plugged or capped and anchored as shown on the plans, or as directed by the Engineer.

Relocate Existing Water Main.  Where an existing water main crosses the location of the proposed sanitary sewer at an elevation to interfere with the construction of the sewer, the water main shall be raised or lowered sufficiently to permit 18 inches minimum clearance from the sewer.  The Contractor may employ either of the following methods for raising or lowering a water main.  He may raise or lower lengths of the water main as necessary on either side of the proposed sewer to allow the main to pass under or over the sewer, providing the deflection at any joint does not exceed one-half of the pipe manufacturer's recommendations, or the water main may be raised or lowered using a pipe bends not to exceed 22 degrees.  In special cases only, and when approved by the Engineer in advance, 45 degrees bends may be used.  The method of lowering and materials to be used shall be approved by the Engineer prior to commencing work.  The Contractor shall give 48 hours notice to the Engineer, prior to any planned water shut-off.

Water lines 2-inches in diameter and smaller shall not be construed as water mains.  Any necessary lowering of water lines 2-inches and smaller shall be included under the conditions set forth in these Special Provisions for the moving and relocation of utilities occupying space within the area of construction.  With the approval of the Engineer, the Contractor may lower water lines 2-inches in diameter and smaller, but separate payment shall not be made for such lowering.  The cost shall be included under Pay Item 204(1B), Structure Excavation for Water Conduit.

627-3.03  Fire Hydrants.  Delete this subsection in its entirety and substitute the following:

Hydrant Removals:  Seven existing fire hydrants, including assemblies, are designated on the plans to be removed.  The Contractor shall salvage the fire hydrants (Mueller Improved and Waterous) and deliver them, cleaned and undamaged, to the Anchorage Water & Wastewater Utility, Operations & Maintenance Yard at 325 E. 94th Court.  At least 48 hours prior to planned delivery, the Contractor shall provide notification to the AWWU Warehouse personnel (telephone number 267-4546).  The remainder of the fire hydrant assemblies, i.e. the fire hydrant leg pipe, auxiliary gate valve, valve box, steam thaw piping, tie back rods, and guard rails shall become the property of the Contractor.

New Hydrant Installations:  The Contractor shall furnish and install "L-Base" Fire Hydrant Assemblies, including the fire hydrant leg pipe, auxiliary gate valve, valve box, steam thaw piping, tie back rods, guard rails, and fire hydrant at the locations shown on the plans.  The Contractor shall install the gate valve with box and the proper length of leg section to provide the desired offset of the fire hydrant from the centerline.  The barrel installation required will be a 10-foot section associated with the new hydrant, or the existing barrel section.  The Contractor shall give 7 days notice prior to backfilling the hydrant to AWWU giving them the existing and final traffic flange elevations.  AWWU will be responsible for vertical adjustments of all fire hydrants.

Fire hydrants shall be Mueller Centurian or equal.

The Contractor shall provide all trench excavation, backfill, and compaction necessary to install the fire hydrant assemblies and the steam thaw pipes in accordance with the details shown on the plans.

All fire hydrant legs shall be installed level. The fire hydrant barrel shall be installed plumb, and the drain plug shall not be removed prior to installation.  The Contractor shall verify that all drain plugs are in place and tighten before acceptance.

The Contractor shall paint in 2-inch black lettered stencils, the direction and distances to the nearest 0.1 foot the distance to the valve box on the face of the fire hydrant directly below the bonnet flange.

627-3.04.  Add the following:  Valves shall be installed where shown on the plans.  Valves shall have the interiors cleaned of all foreign matter before installation.  If the valve is at the end of the line, it shall be plugged prior to backfilling.  The valve shall be inspected by AWWU's representative, in the open and closed positions to ascertain that all parts are in good working condition.

627-3.05.  Delete the first paragraph and substitute the following:  Valve boxes shall be installed over the valves as shown on the plans, with base section centered over the operating nut of the valve and resting on well compacted backfill.  Top section shall be so set as to allow equal movement above and below finished grade, final elevation to be 1/4-inch below finished grade of pavement unless otherwise directed.  Top of base section shall be approximately on line with nut at top of valve stem, and the entire assembly shall be plumb.

Add the following after the second paragraph:  In areas where running sand is encountered, provisions shall be made to restrict sand from entering the bottom section of the valve box.

The Contractor shall expose all valve boxes for pre-final and final inspection.  After final inspection of the valves located in unpaved areas, sawdust shall be poured directly over the valve box lid and covered with gravel to facilitate location in the future.

627-3.06  Testing Water System.  Delete in its entirety and substitute the following:  The Contractor shall notify the Engineer in writing 48 hours in advance (two working days) prior to any test.  AWWU and the Engineer shall be present during all tests.  Two (2) hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or cancelled.

1.	Flushing.  All flushing shall be coordinated with AWWU.  All newly-laid water conduit, except the 30-inch line, shall be "open-bore" flushed to remove any foreign matter to the satisfaction of AWWU.  A detailed plan for cleaning of the lines shall be submitted to the Engineer for review and approval prior to commencement of work.

"Open-bore" flushing shall be accomplished prior to hydrostatic testing and disinfection at all extremities including all stubouts and dead-ends. The Contractor shall furnish, install and remove all fittings and conduit necessary to perform the flushing.  Under no circumstances will "open-bore" flushing through hydrants or reduced outlets be permitted.

All flushing of newly-installed conduit shall be accomplished between the hours of 1:00 AM and 6:00 AM, unless otherwise authorized by AWWU.  Flushing shall be considered incidental to this work and no separate payment shall be made.

2.	Hydrostatic Testing.  A hydrostatic test shall be conducted on all newly-constructed water conduit, fire hydrant leads and stub-outs after "open-bore" flushing in the presence of the Engineer and AWWU in accordance with the requirements of AWWA C-600 unless hereinafter modified. The Contractor, at his option, may either use a pressure test or a leakage test.

The Contractor shall furnish all necessary assistance, equipment, labor, materials and supplies (except the test pressure gauge) necessary to complete the test to the satisfaction of AWWU.  The Contractor shall suitably valve off or plug the outlet to the existing or previously-tested water main at this expense, prior to making the required hydrostatic test.

Prior to testing, all air shall be expelled from the conduit. If permanent air vents are not located at all high points, the Contractor shall, at his expense, install corporation cocks at such points so the air can be expelled as the conduit is slowly filled with water.

Where any section is provided with poured-in-place concrete thrust blocks for fittings or hydrants, the hydrostatic test shall not be made until at least 7 days after installation of the thrust blocks unless otherwise approved by the Engineer.

No hydrostatic test section shall exceed 1000-feet unless approved by AWWU in writing. All main line valves, fire hydrant auxiliary valves, fire hydrant main valves and plugs shall be tested.  All intermediate valves within the section being tested will be fully closed and reopened as directed by the Engineer during the actual test. Only static pressure will be allowed on the opposite side of the end valves of the section being tested.

All hydrostatic testing will be performed through test copper. Use of fire hydrants and service connections for testing will not be allowed.

The hydrostatic pressure shall be a minimum of 150 psi, and the duration of each hydrostatic pressure test shall be 30-minutes. After the required test pressure has been reached, the pumping will be terminated. If the pressure remains constant for 30-minutes without the aid of a pump, that section of the conduit will not be subjected to any further hydrostatic tests.

If a hydrostatic pressure test fails on any section, the Contractor has the option to perform a leakage test on that section. AWWU will furnish the test gauge and measuring device, and the Contractor shall furnish all other necessary assistance, equipment, labor, material and supplies to conduct the test.

Leakage for a newly-installed conduit is determined by the following formula:

L = (ND) P0.5  where:

7400

L = Allowable leakage in

gallons per hour

N = Summation of mechanical

and push-on joints in

length of pipe tested

D = Diameter of conduit in

inches

P = Test pressure in pounds

per square inch

The duration of each leakage test shall be 2 hours and during the test, the conduit shall be subjected to the constant test pressure as defined above. The test pump shall be valved to insure that constant test pressure is maintained throughout the test and all excess water will be returned to a storage tank.  If the pressure decreases below the required test pressure during the 2-hour period, the preceding portion of that test shall be declared void.

Cracked or defective conduit, gaskets, mechanical joints, fittings, valves or hydrants discovered as a consequence of the hydrostatic tests shall be removed and replaced with sound material at the Contractor's expense. The test shall then be repeated until the results are satisfactory.

In the instance where connection is made to a presently installed water conduit a new valve shall be installed on the connection.  The Contractor shall suitably seal off the outlet leading to the presently installed conduit prior to making the field tests.

3.	Continuity Tests.  The Contractor shall perform electrical conductivity tests on all mains less than 12-inches in the presence of the Engineer and AWWU.  The Contractor shall maintain a circuit of 600 amperes DC current for a period of 15-minutes.  Input current shall not exceed 10 percent of the return circuit.  All equipment necessary to maintain the circuit shall be supplied by the Contractor.

All continuity tests will be through wires brought to the surface or through 3/4-inch, minimum, copper pipe connected to the main.  The use of fire hydrants and valves, as substitutes for wires will not be accepted.  All wires brought to the surface to complete the continuity test shall be removed to a depth of 2-feet below finished street grade upon completion of the tests.

627-3.07  Disinfection of Waterlines.  Delete paragraphs 1 thru 4 and add the following:  This subsection applies to the disinfection of all portions of the water system, including all valves and stops and any portion of the existing connection system that might have become contaminated during construction activities.  Disinfection shall be accomplished after completion of pressure and/or leakage tests in compliance with AWWA C-601, Disinfecting Water Mains.

Chlorine shall be used for disinfection, and shall be applied only by one of the following methods:  (1) liquid chlorine gas and water mixture, (2) direct chlorine gas feed, or (3) calcium hypochlorite and water mixture. Calcium hypochlorite shall be comparable to commercial products known as HTH, Perchloren or Machochlor. The chlorinating agent shall be applied at the beginning of the section adjacent to the feeder connection, insuring treatment of the entire line. Water shall be fed slowly into the new conduit with chlorine applied in amounts to produce a dosage of forty (40) ppm to fifty (50) ppm. Application of the chlorine solution shall continue until the required dosage is evident at all extremities of the newly-laid conduit.

Chlorine gas-water mixture shall be applied by means of a solution-feed chlorinating device. Chlorine gas shall be fed directly from a chlorine cylinder equipped with a suitable device for regulating the rate of flow and effective diffusion of gas within the conduit. Calcium hyprochlorite shall be injected or pumped into the water conduit. During the chlorination process, all intermediate valves and accessories shall be manipulated so that the strong chlorine solution in the conduit being treated will not flow back into the conduit supplying the water. Hydrostatic testing of water conduit containing the chlorine mixture will not be allowed.

A residual of not less than five (5) ppm chlorine shall be produced in all parts of the water conduit and retained for a minimum period of 24 hours, after which it shall be flushed from the conduit at its extremities until the replacement water tests are equal chemically and bacteriologically to those of the permanent source of supply.  In no instance will a water conduit be chlorinated before "open-bore" flushing.

CHLORINATION

Conduit Diameter      Dosage (oz. per 100 feet)

6-inch                     1.35 oz

8-inch                     2.75 oz

10-inch                     4.30 oz

12-inch                     6.19 oz

16-inch                    11.00 oz

The above table is to be used as a guide for chlorinating mains by the calcium hypochlorite and water mixture method. The given dosage per 100 feet results in a chlorine solution of forty (40) to fifty (50) ppm.  This dosage takes into account that Contractors most frequently use granular HTH, which is 65 percent pure.  If another chlorinating agent is used, the dosage must

be adjusted.  Caution should be exercised against producing too high a concentration of chlorine in the conduit.

After completion of all testing, all test and air vent copper pipe shall be removed and the corporation cock closed at the main in the presence of the Engineer and AWWU.

627-3.08  As-Builts of Plans and Working Drawings.  Add the following subsection:  A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed.  This as-built information shall be recorded on a print of the plans affected and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed.  Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When the water system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance of the system by the owning Utility.

627-4.01  Method of Measurement.  Delete Subparagraph 1 and 5 in their entirety and substitute the following:

1.	Water Conduit.  Measurement for water conduit with appurtenances shall be per linear foot of horizontal distance of the various sizes and classes furnished and installed as set forth in the Bid Schedule.  Measurement will be from station to station as staked in the field and as shown on the plans, except where the grade exceeds 25 percent, in which case measurement will be by actual conduit length.  Fittings, tees, reducers, crosses, bends, couplings, etc., for water conduit shall be included in the linear foot cost of the water main.

5.	Valves, Valve Boxes and Markers.  The quantity to be paid shall be the actual number of valves, including boxes and marker posts, of each class and size furnished, installed, and accepted.

Add the following:

6.	Disconnect and Reconnect Water Services.  The quantity to be paid shall be the actual number of services of each size disconnected  from  the  old main and reconnected to the new main.

7.	Raise or Lower Existing Water Conduit.  Measurement will be the number of units complete in place without regard to the diameter of the water conduit or length required to be lowered (or raised).

627-5.01  Basis of Payment.  Add the following:  The unit bid prices will include all necessary excavation to plan grade, and backfill of native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 204(1B), Structure Excavation for Water Conduit.  Backfill to replace unsuitable material will be paid under Item 203(6-A), Borrow, Type A.

Payment for insulation board will be made under Item 635(2), Insulation Board.

Add the following Pay Items:

Pay Item No.           Pay Item              Pay Unit

627(11)      Disconnect Water Service        Each

627(13-_)   Disconnect/Reconnect Existing    Each

_-inch Water Service

627(14-_)   _-inch Butterfly Valve, Valve    Each

Box and Marker

627(15)         Remove Water Valve           Each

627(17)        36-inch Pipe Casing       Linear Foot    627(20)        Water Line As-Builts        Lump Sum

SECTION 630

GEOTEXTILE FOR EMBANKMENT SEPARATION

AND REINFORCEMENT

Special Provisions

Delete this Section in its entirety and substitute the following:

630-1.01  Description.  This work shall consist of preparing surfaces and furnishing and placing geotextiles for embankment separation as shown on the plans or as directed by the Engineer.

630-2.01  Materials.  Geotextile material and thread used in joining geotextiles by sewing shall conform to the requirements of Subsection 729-2.01.

630-3.01  Construction.

1.	Surface Preparation.  Before placing the fabric (geotextile), the surface on which fabric is to be placed shall be prepared by removal of all stumps, boulders and other sharp objects.  All holes and large ruts shall be filled with material as shown on the plans or as approved by the Engineer.  Material used to fill ruts and holes will be paid for at the unit price for the class material used as shown on the plans or as approved by the Engineer.  Removal of stumps, boulders and sharp objects will be considered incidental to this item.

2.	Fabric Laying.  Fabric shall be unrolled directly onto the prepared surface.  The geotextile shall be stretched to remove any creases or wrinkles.  Thereafter, it shall be kept taut by pinning or random placement of cover material, and the constant attention of laborers during the cover material placement and spreading.

a.	Separation.  Fabric for embankment separation shall be laid parallel to the direction of the material spread.  When laid along horizontal curves, it shall be placed in segment lengths not exceeding those listed in Table 630-1, with butt ends cut to match and sewn or overlapped.  When laid along tangents, the fabric shall be placed in 200 ft. maximum segments, straightened, and butt ends sewn or overlapped.

b.	Joining.  Fabric shall be joined with adjacent pieces of fabric by sewing, or overlapping.  Joining by bonding or other attachment methods may be used, subject to the approval of the Engineer.  If sewn, all seams shall be sewn by butterfly or J-seams and develop a minimum of 85 percent of the specified geotextile strength.  Seams shall be sewn with a double thread chain-lock stitch.  The seam shall be 1-1/2 inches (+1/4 inch) from the outside edge of the fabric.  If seams are to be overlapped, adjacent sections of fabric shall be overlapped a minimum of three feet unless otherwise shown on the plans.

TABLE 630-1

GEOTEXTILE PLACEMENT ON CURVES

Degree of Curve       Maximum Segment Length (Ft.)

1						125

2						 90

3						 75

4						 65

5						 55

6						 50

3.	Material Placing and Spreading.  Following placement of the fabric on the prepared surface, material of the type shown on the plans shall be end dumped on the previously spread fabric or ground adjacent to the fabric and carefully pushed or spread onto the fabric by a dozer or other machinery.  A minimum depth of 1 foot or depth shown on the plans shall be maintained at all times between the fabric and the wheels or tracks of the construction equipment.  At no time shall equipment operate on the unprotected fabric.  The material shall be spread in the direction of the fabric overlap.  Special care shall be given to maintain a proper overlap and fabric continuity.  If sewn or bonded seams are used, the cover material shall be placed and spread in only one longitudinal direction for the entire length of the geotextile.  On weak subgrades the cover material shall be spread simultaneously with dumping to minimize the potential of a localized subgrade failure.  Construction equipment shall not make sudden stops, starts, or turns on the cover material.  A smooth drum roller shall be used to achieve the specified density.  Any ruts occurring during construction shall be filled with additional cover material and compacted to the specified density.

4.	Geotextile Repair.  If fabric used for separation should be torn for any reason, the cover material shall be cleaned from the torn area and it shall be overlain with fabric with a minimum three foot overlap around the edges of the torn area.  Care shall be taken that the patch remains in place when material is placed over the affected area.

5.	Shipping and Handling.  During shipment and storage, geotextiles shall be continuously protected from direct sunlight, ultraviolet rays, temperatures greater than 140 degrees F, moisture and contamination from mud, dirt, dust, and debris.  Each roll shall be labeled or tagged to provide product identification sufficient for field identification as well as inventory and quality control purposes.  Geotextiles will be rejected if at the time cover material is placed they have been removed from protective wrapping for more than five days, or if they have defects, tears, puncture, flaws, deterioration, contamination, creases or wrinkles caused by manufacturing and/or packaging which cannot be removed in the field, or if they have been damaged from any cause.

630-4.01  Method of Measurement.  Geotextile will be measured in final position by the square yard, determined by multiplying plan neat line width by the measured length parallel to installation centerline along the ground surface, for installations acceptably completed.  No allowance will be made for overlap, whether at joints or patches.  No payment will be made for geotextile placed beyond the limits shown on the plans unless placed at the prior, written direction of the Engineer.

630-5.01  Basis of Payment.  Payment will be made at the contract unit price per square yard.  This price shall be full compensation for furnishing all materials, surface preparation, delivering and laying the fabric and for all labor, equipment, tools and incidentals necessary to complete this item.

Payment will be under:

Pay Item No.             Pay Item              Pay Unit

630(1)         Geotextile, Separation    Square Yard

SECTION 635

INSULATION BOARD

Special Provisions

635-1.01  Description.  Add the following:  Insulation will be placed between a storm drain and a sanitary sewer or waterline when the separation is less than 3-feet.  Insulation board will also be placed in back of those designated retaining walls.

635-2.01  Materials.  Add the following:  The insulation board shall be rigid, homogeneous, and essentially unicellular, and shall conform to the following:

Property                  Test Method        Value

Compression Strength,

psi, minimum at yield          AASHTO M-230        35

or 5 percent compression

Water Absorption,

maximum percent                AASHTO M-230        0.25

by volume

For Retaining Walls:

Thermal Resistance, min.

R-Value at 75F                ASTM C-177 		 10

F-SF-Hr/BTU

635-4.01  Method of Measurement.  Delete and add the following: The quantity to be paid will be the number of square feet of insulation board, including transitions, regardless of thickness, complete and accepted.

635-5.01  Basis of Payment. Add the following pay item:

Pay Item No.        Pay Item          Pay Unit

635(2)       Insulation Board     Square Foot

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01  Description.  Add the following:  This item shall also consist of the work involved in the excavation, forming, shaping and construction of public approaches.

639-2.01  Method of Measurement.  Add the following:  Public approaches will be measured per each constructed as shown on the plans, or as directed.

639-3.01  Basis of Payment.  Add the following:  Payment for public approaches will be full compensation for furnishing all equipment and labor necessary to complete the work as indicated.  Materials required to construct driveways will be paid for separately under the respective items listed in the bid schedule.

Asphalt concrete used for residence driveways, service driveways and public approaches will not be subject to price adjustments.

Add the following pay item:

Pay Item No.        Pay Item          Pay Unit

639(3)        Public Approaches      Each

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-3.01  Basis of Payment.  Add the following:  Preparation of the CPM work schedule, two week work plans and providing a spokesperson in accordance with Section 108, will not be paid for directly, but will be subsidiary to Item 640(1), Mobilization an Demobilization.

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01 Description.  Add the following: Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of Subsection 107-1.11, Protection and Restoration of Property and Landscape.  Additional silt fencing may be required at any upland site as directed by the Engineer.

641-1.03 Materials.  Add the following subsection:  The silt fence filtration material shall meet the following minimum requirements:

Property                         Test Method       Value

Equivalent Opening Size (EOS)

U.S. Standard Sieve              COE CW02215      30-100

Mullen Burst Strength            ASTM D-3786     200 psi

The silt fence support framework shall be finished 4 x 4-inch wood, 3-inch diameter wood, #6 rebar with PVC sleeves, or other posts capable of supporting the installation, as approved by the Engineer.

The mesh support shall be WWF 6x6 W1xW1 or as approved by the Engineer.

641-2.01 Construction Requirements.  Add the following:  The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other hazardous substances to the land and water.  The temporary erosion and pollution control plan shall address the measures the Contractor shall implement in the containment, cleanup, and disposal of such substances as well as the methods to be utilized for disposing of waste oil or other hazardous substances generated by construction equipment or activities.  The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.  The plan shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

The silt fence shall be installed at locations and as detailed on the plans immediately prior to May 1, 1991.  Top of silt fence will be a minimum of two feet above ground surface where fence is installed in wetlands.  The silt fence shall not be removed until adequate vegetative growth insures no further erosion of the slopes.  The silt fence designated for removal on the plans shall be removed and disposed of off the project upon completion of construction at those sites.  The fabric shall be cut off at ground level and the wire and posts shall be removed.  The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands.  If a sediment height in excess of four inches above ground remains, the sediment shall be spread on the roadway side of the fence location and seeded immediately in accordance with Section 618, Seeding.

641-2.02  Best Management Practices.  Add the following subsection:  The following factors shall be utilized by the Contractor in the development of the erosion and sediment control measures which are more easily accomplished if construction operations are properly scheduled.  Operation should be planned, when possible, for that time of year when potential for erosion is low.

1.	Clearing by cutting, slashing and disposing of the trees and other debris.

2.	Installation of temporary erosion and sediment control measures on the downhill side of the construction work area before building the embankment or excavating a slope.

3.	Construction of temporary drainage ditches to convey off-site drainage through the work area and diversion of the flow before excavating for the permanent drainage structure.

4.	Installation of all erosion and sediment control measures at the toe of embankment and excavation operations.  Silt fences are a structural method for providing temporary erosion and sediment control.

5.	Construction of the embankment in horizontal lifts, providing protection from erosion by temporarily or permanently mulching and seeding the slopes in vertical increments, preferably of no more than 10-feet.  The top of the work area should be shaped and compacted so that surface water will run off without causing serious erosion should a storm occur.  At the end of each day's work or before a storm, berms and temporary downdrains must be constructed to control the release of on-site drainage.

6.	Excavation operations performed in the same manner as the embankment operation with the exception of slope drains and compaction.  This operation will release on-site drainage at a point where appropriate control measures have been installed.  The excavated slope must be finished as it is constructed and incrementally protected and seeded.

7.	Shaping and compacting of the embankment surface or cut when the area reaches subgrade elevation.  Surface runoff should be controlled by berms and ditches and release through temporary pipes or ditches.  Detain sediment-laden runoff and trap sediment before releasing runoff from the construction area.

8.	Inspection and maintenance of each erosion and sediment control measure should be performed after each significant storm.  Silt fences should be inspected periodically for damage, such as tearing by wind, animals or equipment, and for the amount of sediment which has accumulated.  Removal of the sediment is generally necessary when it reaches half the height of the silt fence.  In situations where access is available, machinery can be used; otherwise it must be removed manually.  The key elements to remember are:

a.	The sediment deposits should be removed when heavy rain or high water is anticipated.

b.	The sediment removed should be placed in an area where there is little danger of erosion.

641-3.01  Method of Measurement.  Add the following:  Silt fence will be measured by the linear foot along the top of the fence.

641-4.01  Basis of Payment.  Add the following:  Payment for item 641(2), Silt Fence, will be full compensation for all labor, equipment and materials required to furnish, install, maintain and remove the silt fence in accordance with these specifications.

Payment will be made under:

Pay Item No.           Pay Item           Pay Unit

641(2)              Silt Fence         Linear Foot

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  Description.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix C.

642-4.01  Method of Measurement.  Add the following:  Pay Item 642(2), Three Person Survey Party, shall be used only for extra, additional, or unanticipated work made necessary by changes in the project as directed by written order of the Engineer.  The quantities shown on the Bid Schedule for this item are for bidding purposes only, and the actual quantity in the field may vary as directed.  It is not intended to cover survey costs due to minor overruns (10 percent or less) in items which require staking of individual installations such as culverts, guardrail, approaches, signs and drainage structures, etc.

642-5.01  Basis of Payment.  Add the following:  If staking for extra, additional or unanticipated work as stated above is performed by a two person survey party, payment will be made at seventy-five (75) percent of the bid amount per hour for Item 642(2), Three Person Survey Party.  If a single person is required for additional office computations or there is work requiring only one person, payment will be made at thirty-two (32) percent of the bid amount per hour for item 642(2).

(9/1/89)

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  Traffic Control Plan.  Add the following to the third paragraph:  All TCP's submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Safety Supervisor.

Add the following:  The Contractor should be aware that his traffic control plan may require traffic signal timing or re-timing adjustments.  This adjustment work will be done by the Municipality of Anchorage.  Payment for this work will be a subsidiary obligation of the Contractor under Section 660, Signals and Lighting.

643-2.01  Materials.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8-feet.

Delete Item 8., Work Zone Pavement Markings, in its entirety and substitute the following:

8.	Work Zone Pavement Markings.  Work zone pavement markings shall be either paint conforming to Section 708, Paints, and Subsection 712-2.14,  Preformed Pavement Markings (removable or non-removable) or temporary raised pavement markers conforming to Section 712, Miscellaneous.  The markings shall be applied in accordance with Section 670, Traffic Markings, and the manufacturer's recommendations.

643-3.03  Public Notice.  Add the following:  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of commencing construction, resuming construction after seasonal suspension, or any scheduled delay, or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page

newspaper advertisements for the duration of that delay, or closure.  All advertisements shall be published in the following newspapers:

1.	Anchorage Daily News

2.	Anchorage Times

The Contractor shall indicate on the ad order a first preference for the local news section, and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.  Advertisements shall be promptly cancelled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

643-3.04  Traffic Control Devices.  Under Item 1., Embankments, insert the words "or earth berm end treatment" between "crash cushion" and "for" in the last sentence of the third paragraph.

Add the following to Item 1., Embankments:  Barrier reflectors shall be mounted on the face of barrier adjacent to traffic on 50-foot centers and shall be a minimum height of 18 inches above the surface of the temporary roadway.

Delete Item 4. in its entirety and substitute the following:

4.	Work Zone Pavement Markings.  Work Zone Pavement Markings shall be installed in accordance with the Alaska Traffic Manual and shall consist of either Permanent Pavement Markings or Temporary Pavement Markings.

Permanent or Temporary Pavement Markings shall be placed before opening the traveled way to public traffic on all new and overlay Hot Asphalt Concrete

Pavement projects, or whenever pavement delineation has been obliterated or worn off (centerline or lane lines).

Conflicting pavement markings shall be removed in accordance with Section 670, Traffic Markings.  Removal shall be by burning, grinding, sandblasting or other approved method.  Painting over existing striping does not meet the requirement for removal.  Construction shall be staged so that no traffic is routed over conflicting markings.

Prior to winter shutdown, all roadways whether existing, temporary, or permanent shall be marked as though a permanent condition exists.  Lines and markings on existing roadways shall be replaced at their existing locations unless shown otherwise on the plans, an approved traffic control plan or as directed by the Engineer.  Lines and markings to be replaced at their existing locations shall be referenced by the Contractor, at his expense, prior to performing any work that may disturb them.

Temporary Pavement Markings shall consist of marking the work zone in accordance with this subsection, the traffic control plans, and Parts III and VI of the Alaska Traffic Manual.

All final paving, interim paving lifts, temporary pavements, and detours that will be open to traffic for two weeks or more shall be marked as though a permanent condition exists before being opened to traffic.  No exceptions to the requirements of the Alaska Traffic Manual for Permanent Pavement Markings will be allowed.

The Contractor shall maintain all Temporary Pavement Markings for their intended life without additional compensation for any reapplication that may be required.

Temporary Pavement Markings will be required for short-term operations.  Short-term operations are those that will last longer than one continuous work shift and will continue for a time period not to exceed two weeks.  Temporary Pavement Markings for short-term operations shall conform to the requirements of the Alaska Traffic Manual for permanent markings with the following exceptions:

a.	Broken line pavement markings shall conform to the following Table 643-1A, Short-Term Markings In Safe Passing Areas.  This applies to  both white lane lines for traffic moving in the same direction, and yellow center lines for two or three lane two-way roadways when it is safe to pass.

b.	No-passing zones shall be identified with R4-1, (DO NOT PASS) and R4-2,(PASS WITH CARE) signs and temporary raised pavement markers conforming to the following Table 643-1B, Short-Term Markings in No Passing Areas, until permanent no-passing markings can be placed.  The signs shall be supplemented with two 18 inch by 18 inch, minimum size, fluorescent red-orange flags mounted above the signs.  The signs shall be mounted so that the bottom of the sign is at least 5 feet above the adjacent roadway.  This method of marking no passing areas may be used with Annual Average Daily Traffic (AADT) up to 2000 vehicles per day.

c.	It will not be necessary to install arrows, legend, stop lines, crosswalks, or right edge line markings.  Railroad crossing markings should be considered for areas that have sight restrictions or high accident experience.  Left edge lines will not be required unless they will be the only markings on the paved surface, such as ramps.  All other types of markings are required.  These include channelizing lines and gore area outlines.

Temporary Pavement Markings may not be required for construction activities that will be completed within one continuous work shift if the roadway is adequately delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.  The Engineer shall determine the need for the Temporary Pavement Markings for these conditions.

TABLE 643-1A

SHORT-TERM MARKINGS IN SAFE PASSING AREAS

______________________________________________________________

|                  |     LENGTH OF       |       SKIP          |

|    MARKING       |     MARKINGS        |      SPACING        |

|    MATERIAL      |  NORMAL  |  SEVERE* |  NORMAL  |  SEVERE* |

|                  | CURVATURE| CURVATURE| CURVATURE| CURVATURE|

|                  |          |          |          |          |

|    REMOVABLE     |          |          |          |          |

|PRESSURE SENSITIVE|  4 feet  |  2 feet  |  36 feet |  18 feet |

|  MARKING TAPE    |          |          |          |          |

|                  |          |          |          |          |

|                  |          |          |          |          |

|    TEMPORARY     | 2 units  | 2 units  |          |          |

| RAISED PAVEMENT  | 4 feet   | 2 feet   |  36 feet |  18 feet |

|     MARKERS      | on center| on center|          |          |

|                  |          |          |          |          |

*Severe Curvature:	When the degree of curvature is 5 or greater or when it is necessary for the motorist to reduce their speed 15 miles per hour below the 85th percentile speed.

TABLE 643-1B

SHORT-TERM MARKINGS IN NO PASSING AREAS

_______________________________________________________________

| MARKING MATERIAL  |  NORMAL CURVATURE  |  SEVERE* CURVATURE |

|                   |                    |                    |

|                   |                    |                    |

| TEMPORARY RAISED  |        1 UNIT      |        1 UNIT      |

| PAVEMENT MARKERS  |  40 FOOT ON CENTER |  20 FOOT ON CENTER |

|                   |                    |                    |

*Severe Curvature:	When the degree of curvature is 5 or greater or when it is necessary for the motorist to reduce their speed 15 mile per hour below the 85th percentile speed.

643-3.08  Construction Sequencing.  Delete this subsection in its entirety and substitute the following:  Throughout the duration of the project, the existing roadway configuration shall be maintained, (i.e. the number of lanes and shoulders and their respective widths) except for restrictions to traffic addressed through approved Traffic Control Plans.  Restrictions to traffic such as flagging operations, a one lane road operation, or a detour will not be allowed during the times listed below:

1.	Monday through Friday from 7:00 AM to 9:00 AM.

2.	Monday through Friday from 4:00 PM to 6:00 PM.

A portable concrete barrier will be required if an excavation or fill area, as described in Subsection 643-3.04(1), exists within 12 feet from the edge of a traveled way.

Maintaining traffic on a gravel surface will be allowed on Caravelle Drive and at Jewel Lake Road-Raspberry Road Intersection as indicated on the plans.

643-4.01  Method of Measurement.  Add the following to Item 1:  Permanent Construction Signing will be measured by the calendar day and shall consist of furnishing all labor, tools, equipment, signs, sign supports, and incidentals necessary to install and remove the Permanent Construction Signing Plan detailed on the Plans.  The quantity to be paid for shall be the number of calendar days the Construction Signing Plan is installed, accepted and maintained in place.

Delete the second sentence of the first paragraph under Item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this contract.

Delete the fourth sentence of the first paragraph under Item 2.

Delete the last sentence of the first paragraph under Item 3. and replace with the following:  The quantities to be paid for shall be the number of hours or days that the setups are installed, accepted and maintained in place during the life of this contract.

Delete Item 6 and substitute the following:

6.	Temporary Pavement Markings will be measured by the single stripe station.  A single stripe is a marking or a temporary raised pavement marker four inches in width.  Wider striping will be measured as multiples of four inches.  Centerline gaps will not be deducted from measurements.  Installation of any word and symbol markings as well as the removal of the temporary pavement markings will not be measured separately but will be subsidiary to this item.  The No-Passing Zone signing, as described in Subsection 643-3.04, 4.  Work Zone Pavement Markings, will not be measured separately but will be subsidiary to this item.

Delete Item 7. Seasonal Pavement Markings in its entirety.

643-5.01  Basis of Payment.  Delete paragraph 1. , Seasonal Pavement Markings under the second paragraph.

Delete Pay Item 643(14), Seasonal Pavement Markings.

Add the following:  Earth berm end treatments and barrier reflectors will not be paid for directly, but will be subsidiary to Pay Item 643(11), Portable Concrete Barrier.

Change the pay unit for item 643(11), Portable Concrete Barrier from "Each" to "Linear Foot".

SECTION 644

SERVICES TO BE FURNISHED

BY THE CONTRACTOR

Special Provisions

644-2.01  Field Office.  Delete this subsection in its entirety and substitute the following:  The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy within 10 days of the receipt of Notice-to-Proceed through 30 days after the Engineer issues a letter of project completion.  The following office requirements shall be met:

1.	A minimum of 2000 square feet of floor area.  The office area shall be divided so that it contains a minimum of three (3) each office rooms separated by closable doors.  Each office room shall have a minimum of 350 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power.

4.	A minimum of 250 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 30 vehicles.

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

8.	Located within one mile of the project.

644-2.02  Field Laboratory.  Delete the sixth sentence of the first paragraph and substitute the following:  The water supply shall consist of a 500-gallon capacity tank with a pressure pump or a commercial pressurized system.

Modify the second paragraph to include the following:  The lab slab shall be 8 x 10-feet, and installed within an enclosed structure with an exhaust fan.

644-2.08  Water Testing.  Add the following subsection:  Prior to initiating work around Sand Lake, Conner's Bog Lake or DeLong Lake, the Contractor will be required to retain an independent test laboratory to test water samples taken by the Engineer.  These samples shall be tested for color, turbidity and suspended solids, in accordance with the appropriate EPA test method and the results shall be transmitted directly to the Engineer.

During construction, samples shall be tested at intervals as directed by the Engineer (ie: hourly, daily or weekly) depending on the adjacent operation.  After completion of the work final samples shall be tested.

644-3.01  Method of Measurement.  Add the following:  Water testing will be reimbursed based on paid receipts for the authorized tests.

644-4.01  Basis of Payment.  Add the following:  Payment for water testing will be made on the receipts for authorized samples plus 15 percent, and shall be considered full compensation for all labor, equipment and materials required to have tests performed.

Payment will be made under:

Pay Item No.        Pay Item             Pay Unit

644(7)         Water Testing        Contingent Sum

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  Description.  This Training Special Provision is in implementation of 23 US Code 140(a).

As part of the Contractor's equal employment opportunity affirmative action program, the Contractor shall provide on-the-job training aimed at developing full journeymen in the type of trade or job classification involved.  The number of trainees to be trained under this contract is three.

645-2.01  Objective.  Training and upgrading of minorities and women toward journeyman status is a primary objective of this program.  Accordingly, the Contractor shall make every effort to enroll minority trainees and women to the extent that such persons are available within a reasonable area of recruitment and will be responsible for documenting such efforts in order to demonstrate compliance with this Training Special Provision.  This training commitment is not intended, and shall not be used, to discriminate against any applicant for training, whether a member of a minority group or not.

645-3.01  General.  The Contractor shall determine the distribution of the required number of trainees among the various work classifications based on his needs and the availability of journeymen within a reasonable area of recruitment.

It is the intention of these provisions that training is to be provided in the construction crafts rather than clerk-typists and secretarial-type positions.  Training is permissible in lower level management positions such as office engineers, estimators, timekeepers, etc., where the training is oriented toward construction applications.  Training in the laborer classification may be permitted provided that significant and meaningful training is provided and approved.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Reimbursement for offsite training indicated above may only be made to the Contractor where he does one or more of the following and the trainees are concurrently employed on a Federal-aid project; contributes to the cost of the training, provides the instruction to the trainee or pays the trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship of training.

Prior to award of the contract, the Contractor shall submit his training proposal for approval, indicating the number of trainees to be trained in each selected classification and the training program to be used.  Furthermore, the Contractor shall specify the starting time for training in each of the classifications.  To this end, completed certification forms, appropriate to the classifications selected, shall be submitted for each trainee.

1.	Trainees in apprenticeship programs currently approved by the U.S. Department of Labor shall be entered on Form 25A311 "Contractor's FHWA Apprenticeship Certification."

2.	Trainees not in approved apprenticeship programs, including laborers and teamsters, shall be entered on Form 25A310 "Contractor's FHWA OJT Certification."  These trainees shall receive at least 500 hours training on the project.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor and approved by the Department.  The Department shall approve any program which will reasonably qualify the trainee for journeyman status in his classification by the end of the overall training program, and which conforms to the Contractor's equal employment opportunity obligations.  Existing approved programs shall be considered acceptable except in those cases where the Department has determined that the program is not being administered in a matter consistent with the equal employment obligations stipulated in Federal-Aid provisions.

It is normally expected that a trainee will begin his training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist in his work classification or until he has completed his training program.  It is not required that all trainees be on board for the entire length of the contract.  A Contractor will have fulfilled his responsibilities under this Training Special Provision if he has provided acceptable training to the number of trainees specified.

If, in the judgement of the Contractor, a trainee becomes proficient enough to qualify as a journeyman before the end of the prescribed training period, and the Contractor so employs such trainee, the individual training program will be considered completed.

The Contractor shall furnish each trainee a copy of the program he will follow during training on the project, and with a certification showing the type and length of training satisfactorily completed.  No employee shall be employed as a trainee in any classification in which he has successfully completed a training course leading to journeyman status, or in which he has been employed as a journeyman.

The Contractor shall advise all employees and applicants for employment of available training programs and entrance requirements for each.

The Contractor shall periodically review the training and promotion potential of minority group and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each trainee.

645-3.02  Wages.  Trainees will be paid at least 60 percent of the appropriate minimum journeyman's rate specified in the contract for the first half of the training period, 75 percent for the third quarter of the training period, and 90 percent for the last quarter of the training period, unless apprentices or trainees in an approved existing program are enrolled as trainees on this project.  In that case, the appropriate rates approved by the U.S. Departments of Labor or Transportation in connection with the existing program shall apply to all trainees being trained for the same classification who are covered by this Training Special Provision.

645-3.03  Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the trainees are to be trained by the subcontractor.  Any such subcontracts shall include the appropriate training provisions and pay item.  However, primary responsibility for meeting the training requirements imposed remains with the Contractor.

645-4.01  Method of Measurement.  The Contractor will be credited for each approved trainee employed by him on the project and reimbursed on the basis of man-hours worked, as listed in the certified payrolls.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  Basis of Payment.  Payment will be made at the contract unit price for each accepted man-hour of training performed.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment may be made for training persons in excess of the number specified herein, when approved by the Engineer.

Payment will be made following completion of each approved training program.  No payment will be made to the Contractor if he fails to provide the required training or fails to hire the trainee as a journeyman upon completion of the program, and if such actions indicate a lack of good faith in meeting these requirements.  (8/1/88)

Payment will be made under:

Pay Item No.          Pay Item           Pay Unit

645(1)         Training Program       Man-Hour

Add the following Section:

SECTION 646

EQUIPMENT RENTAL

Special Provisions

646-1.01  Description.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of the proposed improvements at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

646-2.01  Equipment Furnished.   In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

646-2.02  Equipment Operators and Supervision Personnel.  Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

646-3.01  Construction Requirements.  The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

646-4.01  Method of Measurement.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.

646-5.01  Basis of Payment.  The pertinent contract bid price per hour for the equipment shown in the Bid Schedule shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher horsepower than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.          Pay Item           Pay Unit

646(3)          Wide Pad Dozer,          Hour

65-HP Minimum

646(8)          Motor Grader,            Hour

125-HP Minimum

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.01  Description.  Add the following:  Item 660(12) Standard Electrolier Relocation, consists of removing and reinstalling standard electroliers at the locations shown on the plans.  Standard electroliers are those with mastarms and mounting heights of 25 feet or more.  New foundations shall have dimensions as shown on Standard drawing L-30.  Anchor bolts shall be as shown on the same drawing with the exception of bolt diameter which shall be the largest diameter that the relocated poles base plate will accept, and the bolt pattern, which shall match that of the relocated poles.

660-1.05  Maintaining Existing and Temporary Electrical Systems.  Delete this subsection in its entirety and add the following:  The Contractor shall provide all work required to maintain the existing and temporary:  traffic signal, highway lighting, flashing beacon, and sign illumination systems.  They shall be kept in effective operation during the progress of the work, except when shutdown is permitted to allow for alterations or final removal of the systems.  Systems shall be considered in effective operation when there are no damaged, inoperative, or malfunctioning components, and they operate as designed.  The State will pay for all electricity required for the operation of the systems, if they are in effective operation and the public benefits from their operation.  Replacement equipment shall be compatible with existing equipment used in the Region.

During the various phases of construction, the Contractor shall shift the signal heads as required so they are aligned both horizontally and vertically with the approaches in accordance with the following:

1.	For a signal mounted overhead, the height above the travelled way to the bottom of the signal shall be at least 17.5 to no more than 19.0-feet.

2.	For a side mounted signal, the height above the travelled way to the bottom of the signal shall be at least 9 to no more than 11-feet.

3.  	An overhead signal controlling a single lane shall be in line with the center of the lane.

4.	The overhead signal controlling two lanes and each of the two overhead signals controlling three lanes shall be in line with the stripe separating the lanes.

5.	If, when the travelled way is moved, the side mounted far right signal head is located such that the horizontal angle to it from the center of the farthest left through lane at the stop bar exceeds 20 degrees, then it shall be moved to an overhead location.  If there are two or three through lanes, then all overhead signal heads shall be realigned so that one is centered over each lane.  If there is one through lane, then the former side mounted signal head shall be located 8 feet to the right of the existing overhead signal.

6.	For a pedestrian signal, the height above the travelled way to the bottom of the signal shall be at least 7 to no more than 9 feet.

7.	All signal heads shall be aimed so they conform with Subsection 660-4.01, Installation Details.

Signal system shutdowns shall be limited to periods during normal working hours as specified in Section 643, Traffic Maintenance, during which flag control shall be used.  Lighting system shutdowns shall not interfere with the regular lighting schedule.  Local traffic enforcement and maintenance agencies shall be notified prior to any shutdown of a traffic signal system.

When the Contractor begins work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include repair or any damage prior to the date of the transfer of maintenance responsibility.  Therefore, before commencing work on the project, the Contractor should inventory the condition of the existing equipment and present written documentation of all damaged, inoperative, and malfunctioning electrical equipment.  This equipment shall be inspected jointly by the Engineer and the Contractor.  If the Contractor begins work before he provides the Engineer with an inventory, he waives the right to claim extra compensation when any component is later found to be damaged, inoperative, or malfunctioning.

At the Preconstruction Conference  the Contractor shall furnish the Engineer with the name and phone number of the person responsible for maintaining existing and temporary electrical facilities.  This person shall be available at all times until the date of Acceptance for Traffic and Maintenance and have access to all labor, materials, and equipment required to complete any repair.

Repair work on traffic signals shall begin within one hour of notification.  If repairs are not completed as required, then the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due the Contractor.  The Contractor shall maintain a hand printed record of all work performed on the signal system in the diary found in each controller cabinet.  Each entry shall include the following:

1.	The date(s) and time(s) the changes or maintenance operations began and were completed, and the names of the crew members completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the changes or performing maintenance.

The Contractor shall ascertain the location of existing conduit runs, buried cables, junction boxes, and all underground utilities before using equipment that may damage such facilities or interfere with any system.

Where roadways are to remain open to traffic and existing lighting systems are to be modified, the Contractor shall energize the modified circuit by sunset on the same day he retires the original circuit.

Where an existing system is being modified, work not shown on the plans or specified in the Special Provisions which the Engineer determines is necessary to keep all or any part of the existing system in effective operation will be paid for as extra work as provided in Subsection 109-1.05, Compensation for Extra Work.

When no longer required, the Contractor shall salvage all original and Department provided equipment in accordance with the plans and Subsection 660-6.07, Salvaging Electric Equipment, and remove all other materials used in the temporary systems from the project.

660-1.05(A)  Temporary Signal Systems.  Add the following subsection:  The Contractor shall provide temporary signalization at the intersection of Raspberry Road with Jewel Lake Road.  At no time shall the intersection operate in an unsignalized mode, except for shutdown due to change over from the existing system to a temporary system, and from the temporary system to a permanent system.  The Contractor shall also provide a temporary flashing beacon system at the intersection of Raspberry Road with Cranberry Street.

A plan for each temporary signal system shall be submitted to and approved by the Engineer prior to implementation.  The temporary signal plan shall equal or exceed the system being replaced or modified.  That is, the plan shall not downgrade the number of signal heads, signal phases, pedestrian push-button, etc.  The temporary signal system plan shall also include the layout of the temporary intersection.  The complete plan will include intersection geometrics, lane widths and auxiliary lane pocket lengths.  The Contractor shall ensure the availability of Municipal signal technicians prior to implementing a traffic control plan that either physically modifies, or otherwise changes the flow of traffic through a signalized intersection.  The costs of this work, including any standby charges, shall be a subsidiary obligation of the Contractor.

The Contractor shall furnish and install all materials and miscellaneous hardware required to provide a functional traffic signal system.  All materials shall conform to the requirements of the plans and specifications.  Temporary equipment shall be compatible with existing equipment used in the Central Region.  Load centers shall be provided as required in Subsection 660-1.05(B), Temporary Illumination Systems.

The temporary signal system may consist of:  the existing systems, relocations of the component parts, guyed wood poles, or any portion of the permanent signal system.  Traffic signals may be suspended from messenger cables provided they are mounted by standard span wire hangers and secured with a second cable to prevent misalignment in a wind.  All signal faces shall be equipped with backplates and visors.  The signal faces of each phase with two or more faces shall be energized using two circuits, with each circuit wired with an IMSA 20-1 signal cable; splices shall be made only at the terminal blocks in the signal faces.  Sufficient signal cable slack shall be left at each pole to provide for drip loops and to allow realignment of each signal head.  Temporary controller assemblies may be mounted on Type III junction boxes while work is completed on the permanent systems.

Whenever a pole of the permanent signal system is included in a span wire signal system, the Contractor shall guy the pole and provide protective collars to prevent chafe damage.  Poles with breakaway bases shall not be included in a span wire supported signal system.

Unless otherwise specified, no vehicle detection will be required in the temporary systems during the construction season after the existing loops are removed during normal construction.  At that time, the controller will revert to the pre-timed mode.  However, prior to the Department's acceptance of the signalized intersections for winter maintenance, vehicle detection shall be installed and working to the same extent as it was in the original and temporary signal systems prior to their removal.

660-1.05(B)  Temporary Illumination Systems.  Add the following subsection:  The Contractor shall provide illumination at all locations with preexisting lighting, at all intersections where temporary traffic signalization is specified to be provided, and at the following street intersections with Raspberry Road:  Fountain Drive, Service Road, Weimer Street, Dunkirk Court, Chevigny Street, Blackberry Street, Linden Drive, Cranberry Street, Arlene Street, Carline Street, Timothy Street and Northwood Drive.  This work shall be provided during the life of the contract on all roadways open to traffic within the project limits.  The temporary lighting systems shall be operational by sunset on the same day the replaced system is retired, or the roadway is opened to traffic.

A plan for each temporary lighting system shall be submitted to and approved by the Engineer prior to implementation.  The temporary lighting plan shall equal or exceed the system(s) being replaced or modified, and at intersections, consist of a luminaire located on the far right for each through street approach and installed adjacent to the through street radius returns.  The through street is the street with the vehicular right-of-way; both streets shall be considered through at signalized intersections and four-way stops.

The Contractor shall furnish and install all materials and miscellaneous hardware required to provide a functional lighting system, including electrical load centers.  All materials shall conform to the requirements of the plans and specifications, except that the branch conductors may be triplex aluminum with messenger cable if they are installed overhead.  Illumination conductors shall be sized so the voltage at the most remote luminaire is not less than the minimum required for the ballast, as recommended by the manufacturer.  The Contractor shall install intermediate conductor and supports to energize luminaires at locations without electrical service.  Luminaires used in the system may be the existing fixtures or new fixtures with a light distribution compatible with the proposed lighting configuration.

The temporary lighting systems may consist of any of the following lighting pole types, or combinations thereof, provided the luminaires have a minimum 30 feet mounting height.  Mounting height is the difference in elevation between the luminaire refractor and the edge of travelled way at the same station.  The existing poles may be reused if they are not utility owned.  Any pole of the permanent lighting and temporary signal systems, and any Contractor supplied poles may be used in the temporary lighting system(s).  Contractor supplied poles may be wood, and shall meet AASHTO design criteria for 80 miles per hour wind.  All poles, except traffic signal poles, installed within the clear zone shall be provided with FHWA approved: slip bases, transformer bases, or frangible couplings.

The load centers to power the temporary lighting and signal systems may be the permanent installations, the existing installations, or temporary installations.  The existing load centers may be used only if they are scheduled to remain intact until completion of the project, and reused only if they are approved.  The Contractor shall provide approved temporary load centers with photoelectrically controlled lighting circuits, whenever no load center is available for use or when an existing load center that is not approved is retired due to conflict with the work.  An approved load center is any load center UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "suitable for use as service equipment".  The Contractor shall provide all work to modify these load centers as required to provide functional temporary lighting and signal systems and to install them, completing all work in accordance with the NEC.

660-2.04  Poles, Steel Pedestals and Posts.  Add the following:  All poles shall be designed for 100 MPH wind speeds with gusts to 130 MPH.

660-2.09(A)  Wiring.  Add the following between the words "signal" and  "conductors" in the seventh paragraph:  ...and feeder...

660-2.10  Bonding and Grounding.  Add the following after the first paragraph:  All hardware, including insulated throat grounding bushings, ground rods, and ground rod clamps shall be UL listed.

660-4.01  Installation Details.  Under loops, numbered paragraphs 7 and 9, change "660-2.08" to read "660-2.09(A)".

660-5.02  Backplates.  In the last paragraph, change "660-2.16" to read "660-2.15".

660-6.01  Luminaires.  Add the following paragraph:  No paint may be applied to the reflecting surface of luminaire reflectors.

Luminaires shall provide the light levels and uniformities shown on the plans.

Conformance of the MC-3 and Area luminaires with the photometric performance specifications will be based on the manufacturing published photometrics.

660-6.07  Salvaging Electrical Equipment.   Add the following to the first paragraph:  All equipment to be salvaged shall be delivered to the State Maintenance yard at 5700 E. Tudor Road, Anchorage.

Delete the fourth paragraph and substitute the following:  The following existing items not being reused shall become the property of the Contractor and be disposed of as indicated.  Items that are to be removed shall be removed from the highway right of way.

1.	Junction boxes (not including lids), conductors, and post and controller assembly foundations shall be removed.

2.	Conduits and vehicle detectors may be abandoned in place provided any section of metallic conduit located within two radial feet of any new conduit is removed.

3.	Traffic signal pole and electroller foundations may be abandoned in place provided the tops of the foundations, reinforcing steel, anchor bolts, and conduits are removed to a depth of not less than one foot below roadway subgrade, sidewalk, or unimproved ground, whichever applies.

660-7.01  Basis of Payment.  In the first paragraph, modify line eleven to read:  "...involved in furnishing and installing, modifying, maintaining and...".

Add the following:	Payment for traffic signal timing or re-timing adjustments performed by the Municipality of Anchorage is estimated to be approximately 4 hours per week per signalized intersection at a cost of $50/hour for regular time and $100/hour for overtime.  These costs will be a subsidiary obligation to the appropriate 660 item.

All work necessary to temporarily relocate the existing flasher at Cranberry Street will not be paid for directly, but will be subsidiary to Item 660(7), Temporary Signal System complete at Jewel Lake Road.

Add the following pay item:

Pay Item No.            Pay Item            Pay Unit

660(12)        Standard Electrolier        Each

Relocation

SECTION 661

ELECTRICAL LOAD CENTERS

Special Provisions

661-1.02  Equipment List(s) and Drawings.  Add the following subsection:  The Contractor shall submit for review and approval, within 30 days following award of the contract, 8 collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s) and the following:

1.	For materials on the Approved Products List:  a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

2.	For materials not on the Approved Products List:  catalog cuts that include the manufacturer's name, type of product, size, model number, conformance specifications, and supplemented by other data as may be required, including manufacturer's maintenance and operations manuals, or sample articles.

This information may be included in the portfolio for 660 items.

The Department will not be liable for any material purchased, labor performed, equipment used, or delay to the work before all equipment and materials have been reviewed and approved.

661-2.01  Materials.  Add the following:  Type 1 load center cabinets shall be constructed similar to the section and elevations shown in the plans, and conform to the following requirements.  Slight variation in the dimensions is allowable, except in the anchor bolt template.

1.	The cabinet shall be constructed of zinc-coated A60 finish sheet steel per ASTM A525 with no external screws, bolts, or nuts.  The components shall have the following minimum thickness as measured by the United States Standard Gauge:  the exterior shell No. 12 gauge, the interior doors and panels No. 14 gauge, and the interior covers No. 16 gauge.

2.	The components shall be painted with a 2-part urethane paint undercoating inside and out.  The final finish shall be a 2-part urethane paint, standard white for removable panels and non-gloss silver-gray, closely matching Color No. 36622 of Federal Standard Specification No. 5950 for the enclosure.

3.	The service entrance section shall be isolated from the main load section and distribution load section by non-removable metal barriers, and shall be equipped with landing lugs for termination of service conductors.

4.	The cabinet shall be provided with internal mounting brackets sized for 1/2-inch anchor bolts for use with a standard mounting base assembly.

5.	All  doors   shall  be  equipped  with  continuous  stainless steel pin hinges, coin latches and hasp for padlock.  The meter section door shall have a clear polycarbonate resin window, 0.187" minimum thickness, with a minimum size of 10.0-inch x 10.0-inch, which shall be sealed with silicone.

6.	Each  completed  load  center  assembly  shall  be provided with an exterior name plate, safety labels, interior identification labels, wiring diagram, and installation instructions.

7.	When  two  type 1 load centers are to be installed adjacent to one another, furnish one cabinet with the load distribution section located on the left side.

When required, type 2 and 3 load center cabinets shall be sized and wired to serve the combination of highway lighting, traffic signal and thaw wire circuits shown in the plans.  Each cabinet shall be a single box, subdivided to form compartments as required, and constructed of formed and welded, code gauge steel, finished with gray baked enamel, electro-deposited on cleaned phosphatized steel and suitable for surface mounting.  A hinged lockable door with hasp shall be installed over each compartment.

The wiring configuration for each load center type shall be in accordance with the wiring diagram indicated on the load center detail sheet.  Circuit breaker ratings shall be as shown in the load center summary for each location.  Dead panels shall be indelibly labeled with the circuit number and the direction of the circuit run from the load center.

When the load centers are ready to be energized, the Contractor shall request and coordinate an electrical inspection of the load centers from the local authority having jurisdiction, allowing at least 5 working days before the inspection is needed.  The Contractor shall be present during the inspection to assist in accessing the cabinets and to answer questions.  The Contractor shall correct the deficiencies noted in each load center.

Payment of any fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be considered incidental to the Section 661 items.  (4/21/88)

All breakers shall have an ampere interrupting capacity (A.I.C.) of 20,000 or greater, unless the Contractor can show that a direct short across the serving transformer would result in a lower current.

661-3.01  Construction Requirements.  Delete the third paragraph in its entirety and substitute the following:  The Contractor shall install a rigid metal conduit at the location and depth as shown on the plans, threaded, capped and extended 12-inches from the face of the load center base.  The terminus shall be marked with a 2-inch by 4-inch by 4-foot stake.

Add the following Section:

SECTION 662

SIGNAL INTERCONNECT

Special Provisions

662-1.01  Description.  This item consists of all work required to furnish and install signal interconnect in conduit between the controller assemblies shown on the plans and along the route indicated, or as directed by the Engineer.

662-2.01  Materials.  These specifications and Section 660, Signals and Lighting, shall apply.  The interconnect cable shall be a 25 pair #19 AWG telephone cable conforming to REA Specification PE-39.  The interconnect cable shall be installed in a 2-inch galvanized rigid metal conduit.

Completed splices shall be encapsulated in waterproof reenterable type cases.  Acceptable splicing materials are listed in the REA Bulletin 344-2 entitled "Lists of Materials Acceptable for use on Telephone Systems of REA Borrowers".

All materials shall be submitted for review and approval per the requirements of Subsection 660-1.03, Equipment List and Drawings.

662-3.01  Construction Requirements.  The signal interconnect is comprised of cable, conduit, junction boxes, other necessary hardware required to complete the item, cable splicing, and the termination of conductors on terminal blocks.   These components shall be constructed in accordance with the appropriate subsections contained in Section 660, Signals and Lighting.

Junction boxes shall be installed at all abrupt changes in conduit alignment and on a maximum spacing of 300-feet.  An abrupt change is defined as an angle point or curve with a delta angle greater than 45 degrees.  Junction boxes shall be Type 1A except when a splice has to be made in the interconnect cable.  All signal interconnect splices shall be made in Type II or III junction boxes, and completed in accordance with REA PC-2 for splicing telephone cables.  The Contractor may determine the locations for making signal interconnect splices, except that splices shall not be made at low points in the terrain or the bottom of sag vertical curves.  Splices in the interconnect cable will be kept to an absolute minimum, and approved by the Engineer beforehand.

The new controller assemblies shall be furnished with terminal blocks for the interconnect cable.

662-4.01  Method of Measurement.  Signal interconnect will be measured by the station, on the slope, from the center of junction box to center of the next junction box.

662-5.01  Basis of Payment.  The contract unit price per station for signal interconnect will be full compensation for furnishing all materials, labor, and equipment required to complete the work as specified.  Terminal blocks for the interconnect cable shall be paid under Item 660(1), Traffic Signal System Complete.  Payment will be made under:

Pay Item No.          Pay Item            Pay Unit

662(1)        Signal Interconnect       Station

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDER STATIONS

Special Provisions

669-1.01  Description.  This work shall consist of furnishing and installing traffic count stations for the automated collection of traffic data on an intermittent basis.  The Automated Traffic Recorder (ATR) station is

a vehicle detection system.  Each intermittent volume count system specified herein shall consist of the following parts:

Inductive loop detectors for detecting the presence of vehicles, underground conduit, junction boxes, wiring, cabinet, and other items required to construct an operational system as specified.

The locations of traffic detection and cabinets shown on the plans are approximate and the exact locations shall be established in the field by the Engineer.

General descriptions of the Automated Traffic Recorders included in the Raspberry Road project are as follows:

Assembly H1--A four loop configuration, intermittent ATR without electrical or telephone service.

Assembly H2--A four loop configuration, intermittent ATR without electrical or telephone service.

Assembly H3--A two loop configuration, intermittent ATR without electrical and telephone service.

Assembly H4--A four loop configuration, intermittent ATR with electrical and telephone service.

669-1.02  Regulations and Code.  All materials and workmanship shall conform to the standards of the Underwriters Laboratories, Inc., and the National Electrical Safety Code, and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturers Association, where applicable.

669-2.01  Materials.  All materials provided for the work shall be new, unless otherwise stated, and must meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with Subsection 660-2.09(A), Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable.

2.	Conduit.  All conduit shall be in accordance with Subsection 660-2.05, Conduit.  Nylon pull cords shall be left in all two inch conduit.

3.	Junction Boxes.  All junction boxes shall be in accordance with Subsection 660-2.06, Junction Boxes.  Junction boxes used for ATR installations shall not contain any conductors carrying a voltage over 50 volts.

4.	Terminal Blocks.  All terminal blocks shall be provided with nickel, silver or cadmium plated brass binder head screw terminals.  Terminal blocks shall be a barrier type, 600vac @ 20amps, capacity for 12-18 AWG wire.  All terminal blocks shall have removable shorting bars in each position and have integral type marking strips.  All conductors shall be terminated and labeled to a terminal block.

All terminal blocks mounted in junction boxes shall be waterproofed with a re-enterable type sealant and encapsulated in a rigid, two piece, snap together plastic mold.

5.	Inductive Loops.  All inductive loops shall be in accordance with Subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be UL listed as Type RHW/USE/XLP 12AWG 600V rating.

Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, and aluminum shield and overall PVC or PE jacket conforming to IMSA specification 50-2.

6.	Cabinets.  All style 3 cabinets shall be in accordance with Subsection 660-3.05, Controller Cabinets.  All cabinets shall be aluminum and painted.  All cabinets shall have a NEMA 3R specification.  All style 1 and 2 cabinets shall be installed as indicated on the plans.

669-3.01  Construction Requirements.

1.	Wiring.  All wiring shall be installed in accordance with Subsection 660-2.09(A), Wiring.  All unused pairs shall be terminated within splices, at cabinets unused pairs shall be terminated at a terminal block and labeled "SPARE".

2.	Conduit.  All conduit shall be installed in accordance with Subsection 660-2.05, Conduit or as indicated on the plans.

3.	Junction Boxes.  All junction boxes shall be installed in accordance with Subsection 660-2.06, Junction Boxes or as indicated on the plans.

4.	Terminal Blocks.  All terminal blocks and wire pairs shall be clearly labeled on the block.  Terminal blocks within cabinets shall be permanently mounted so that all terminals are easily accessible from the front of the cabinet.  By convention, wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block.

Re-enterable splice kits containing terminal blocks in junction boxes shall be placed with the long dimension horizontal, and firmly mounted within six inches of the top of the box.  All conductors shall terminate and be soldered to "spade" type terminal lugs.

5.	Inductive Loops.  All inductive loops shall be installed and constructed in accordance with Subsection 660-4.01, Installation Details, Loops, unless otherwise specified in the plans.

All inductive loops shall be formed of four turns of wire, and shall be six feet square with plus-or-minus one inch tolerance.  All inductive loops shall be centered in the indicated traffic lane.  All inductive loops within a lane shall be located sixteen feet from leading edge to leading edge, with plus-or-minus one inch tolerance.  Inductive loops located in parallel lanes shall be within  one inch of being directly adjacent to each other.

Loops shall not be cut into final lift asphalt pavement.

All lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the center line of the road.

6.	Cabinets.  All style 3 cabinets shall be installed according to Subsection 660-4.01, Installation Details.  All style 1 and 2 cabinets shall be installed as indicated on the plans.

669-3.05  Deliverables.

1.	Equipment List(s) and Drawings.  The Contractor shall submit for review and approval, within thirty days following award of the contract, nine collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s), and a description that includes product name, manufacturer, model or part number.

2.	As-Built Plans.  The Contractor shall prepare four complete sets of as-built plans which will be kept current with the construction.  These as-built plans shall detail all construction changes made to the plans and also include the following information on the appropriate sheets the location and depth of all inductive loops and conduit runs, and the station and offset of all junction boxes.

Two sets of as-built plans shall be presented to the Project Engineer for distribution to the Highway Data Section (HDS), and one set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet door at the appropriate Automated Traffic Recorder installation.

3.	Tests Results.  Two written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Project

Engineer prior to acceptance of the Automated Traffic Recorder installation.  Distribution shall be:

1-Technical Services

2-Highway Data Section

1-Cabinet (in plastic holder with As-builts)

669-4.01  Method of Measurement.  The quantity to be paid for will be the actual number of completed and accepted Automated Traffic Recorder installations as shown on the plans or as directed by the Engineer.

As-built plans will not be measured for payment.

669-5.01  Basis of Payment.  The contract unit bid price per each Automated Traffic Recorder installation shall be full compensation for providing as-built plans and all equipment, labor and materials necessary to complete the work as specified.  This includes the cutting and patching of existing asphalt, where necessary.

Excavation and other modifications required for this installation shall be paid under their respective pay item numbers.

Payment will be made under:

Pay Item No.         Pay Item             Pay Unit

669(1-__)       Automated Traffic       Lump Sum

Recorder at Station ______

SECTION 670

TRAFFIC MARKINGS

Standard Modifications

670-3.01  Construction Requirements.  In the last paragraph under Item 2., insert "pneumatic" immediately before "roller".  (05/12/89)

Special Provisions

670-3.04  Paint Removal.  Change title of subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following:  Existing pavement markings shall be removed to the fullest extent possible by a grinding method that does not materially damage the surface or texture of the pavement or surfacing.  Any method utilizing burning with an open flame will not be used for the removal of pavement markings.

670-4.01  Method of Measurement.  Add the following:

6.	Station Basis.  Measurement of a traffic stripe will be the length of each individual stripe excluding gaps.  An individual stripe is a longitudinal marking less than six inches wide.

Delete the last paragraph and substitute the following:  Removal of traffic stripes and pavement markings as well as repair of any damaged pavement or surfacing caused by the pavement marking removal operation will be measured by the station for payment.

670-5.01  Basis of Payment.  Add the following:  Payment for removal of existing markings shall be made under the following:

Pay Item No.            Pay Item               Pay Unit

670(9)      Removal of Pavement Markings    Station

Add the following Section:

SECTION 680

TELEPHONE RELOCATION

Special Provisions

680-1.01  Description.  The Contractor will be responsible for the furnishing of all labor, equipment, and such material as necessary to place the owner-furnished telephone manholes at the locations shown on the plans.  The term "manhole" as employed herein shall apply to either a telephone manhole, vault or handhole.  This work also consists of the furnishing of all labor, equipment and necessary materials to complete the construction and installation of all telephone duct systems of multiple combinations of ducts or conduit, together with laterals.

The early transfer of completed sections between manholes will expedite the relocation of the telephone system.  When there is a minimum of 2-feet of compacted cover over the completed duct system, then the Contractor is encouraged to have an inspection and acceptance by the owning Utility so that cable pulling may commence.

The Contractor shall provide two sets of red-line  as-built drawings in accordance with the conditions prescribed herein.

This work will also be inspected by the Anchorage Telephone Utility (ATU) with their instructions relayed to the Contractor through the Engineer.

680-2.01  Materials.  The following materials shall be furnished by ATU at no cost to the Contractor:

1.	Manholes

2.	Manhole concrete lift rings, frames and covers

3.	Ground rods, #6 SDC ground wire, and clamps

4.	End bells, plastic or steel stubs,

and conduit caps and bushings

5.	Gasket sealant material

6.	All multiple ducts and fittings

7.	All PVC conduit, fittings and solvent cement

8.	All RMC conduit and fittings, except Erickson

fittings.

9.	EMS coils - electrical marker system

The telephone multiple ducts are 42-inch long modular fiberglass interlocking duct banks with molded gaskets and metal clips.

The manholes, duct banks, conduit and fittings will be available for pick up after March 1, 1990.  Some miscellaneous fittings over and above plan quantities must be ordered.  The Contractor shall allow 20 days for delivery after notifying ATU.

All materials to be furnished by ATU will be located at the Anchorage Telephone Utility Warehouse, 600 East 38th Avenue, Anchorage, except that the prefabricated manholes shall be within 10 miles of the project.

The Contractor shall be responsible for determining his material take-off requirements.  Within 30 days of receipt of Notice-to-Proceed, he shall prepare a complete itemized list of materials for the entire project for submittal to ATU.  A list of materials needed at any one time will be delivered to the ATU warehouse at least 24 hours in advance of pickup.  Materials shall be picked up in batch issue, and not as needed on a daily basis.

The Contractor shall sign for materials at the time of receipt.  The ATU warehouse foreman will be available for material issuance between the hours of 7:30 AM to 12:00 noon and 1:00 PM to 4:30 PM daily except Saturdays, Sundays and legal holidays.  Where it is necessary to open the warehouse for the Contractors convenience and to procure special issuing of material other than during these normal working periods, the Contractor shall be billed for the time involved plus 25 percent handling overhead.  The hourly wage and quantity of time incurred shall be that indicated as being required under the existing ATU/IBEW Union Contract.  Storage and safekeeping of all materials after pickup from ATU shall be the Contractors responsibility.  All unused materials shall be returned to the warehouse upon completion of the project.

The following items shall be furnished by the Contractor:

1.	All tie-down stakes

2.	All plastic straps, clips and binder tool

3.	Visqueen or other covering material for concrete curing

4.	Backfill material, including sand or concrete slurry

5.	Geotextile

6.	Fire hose and accessories for sand bedding

7.	All wood spacers

8.	All Erickson fittings

9.	Concrete grout, mortar and silicone

10.	Manhole lifting slings and lifting eyes

11.	All miscellaneous tools and hardware,and non-furnished material necessary to construct and install this system

12.	All 18-inch and 30-inch sleeve pipes for ducting

13.	Concrete and forming material

680-3.01  Construction Requirements.  The ATU Inspector through the  Engineer reserves the right to suspend the telephone duct system installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

All temporary bridging for traffic utilized by the Contractor will be inspected and approved by the Engineer prior to installation.  This does not relieve the Contractor of responsibility for providing bridging of sufficient size or strength.  Any bridging open to public traffic will provide a smooth driving joint.

The Contractor shall be responsible for the locating, shoring and protecting of all facilities and utility poles in the vicinity of the project.  The cost of shoring and otherwise securing existing poles shall be paid under Section 203, Excavation and Embankment.  While ATU has endeavored to reflect the location of all sewer, water, telephone and gas lines, key boxes, valves and poles on its drawings, it shall be the Contractor's responsibility to establish the location of each facility by calling for a field locate in accordance with Subsection 105-1.06, Cooperation with Utilities.

If construction or excavation require the removal of any existing privately owned facilities on the provided telephone easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practical after the installation, but in no case shall the period of time exceed 2 weeks.

Once work commences, the Contractor, the Engineer and ATU will meet at the end of each week to review the work to date, and plan the following weeks work.  The

Contractor must submit in writing, his anticipated hourly work schedule, on the Wednesday prior to the work week.

All telephone duct systems shall be constructed to within an allowable tolerance of 0.1-foot of the plan location in any phase of the construction.  The Contractor will backfill all manhole and trench excavations within 48 hours.

680-3.02  Surveying and Staking.  All manholes and telephone duct systems shall be located and staked by the Contractor at the elevations indicated on the plans.  It shall be the Contractors responsibility to schedule a physical check of all line and grades prior to placing of any manholes and ducts.  These elevation checks shall include bottom elevations and manhole top elevations, to assure adequate clearance for manhole frame and cover.  Grade stakes shall not exceed 25-feet separation, and all manholes shall have two corners staked.

680-3.03  Excavation.  The Contractor shall excavate for the manhole to the design depth of the bottom of the manhole.  Trench excavation shall precede the laying of duct or conduit by a minimum of 100-feet.

The Contractor shall excavate all frost susceptible soil in the trench to a depth of 2-feet below the designed grade of all manhole and telephone duct system installations.  If saturated material is encountered, the Contractor shall also excavate 2-feet those materials with a moisture content 2.0 percent over the optimum moisture when tested in accordance with AASHTO T-180.

680-3.04  Backfill and Compaction.  Backfill shall be in accordance Section 203, Excavation and Embankment.  All backfill for the manholes and telephone duct systems shall be compacted in 8-inch lifts to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankment with Moisture and Density Control.

Backfill up to the bottom of trench grade, if necessary, shall be in compacted 8-inch lifts of material meeting the requirements of Selected Material, Type A.  If large quantities of water are evident, the Contractor may elect to backfill with 2 to 6-inch coarse oversized rock overlaid with geotextile.  Compaction shall be by a minimum of 6  full width coverages with a mechanical

compactor.  The ducts or conduit shall then be placed on a 4-inch sand bedding on the trench bottom, with the sand being water-compacted to 4-inches above the system.  The Contractor may then use such native materials as have been excavated from the trench that meet the requirements of Selected Material, Type C, above the duct or conduit sand bedment, up to the bottom of the roadway or pathway structural section.

The soil compaction of the trenches and manhole foundations shall be randomly tested at various depths by the Engineer.

680-3.05  Manhole Concrete Lift Rings, Frames and Covers.  The manhole frame and cover shall be set to the designed finished grade of the proposed paving or existing ground level as designated by the Engineer, and shall be brought to grade by installing courses of concrete lift rings.  There will be a minimum of one (1) 6-inch lift ring for each manhole, except as directed by the Engineer.  Those manhole covers located within the sidewalk or pathway shall meet the requirements of Subsection 604-3.01, Construction Requirements.

While the plans indicate the ultimate elevation for the placement of manhole frames and covers, the Contractor shall field verify the exact elevations with the Engineer.

680-3.06  Prefabricated Manholes.  The Contractor shall be responsible for picking up the owner-furnished prefabricated manholes at the fabrication site. Unless specified otherwise, the manholes shall be loaded on the Contractors vehicle by others at no cost to the Contractor.  Manhole W-27 requires a special roof section with three conduit end bells through the roof in one corner.  Care should be taken not to use this roof at some other manhole location.

In setting a manhole, the Contractor assumes all responsibility for the cost of installation, repair and maintenance of the subject manhole until accepted by the owning Utility.  During the placement of a manhole, if the gravel foundation proves to be inadequate to support the manhole to designed line or elevation, the Contractor shall remove the manhole and recompact in accordance with Subsection 680-3.04, Backfill and Compaction, above.

The manhole sections and the frame and covers will be primed and sealed with the owner-furnished gasket sealant.  The ground wire shall be installed through the provided knockouts on both ends of manhole as directed by the Engineer.  The Contractor will place two 8-foot ground rods on each end of each manhole excavation, driven from the manhole bottom slab elevation down and will connect them to the manhole ground wire leaving a 6-foot loop of that same wire inside the manhole.

680-3.07  6-Way Ducts and 4-inch Conduit Installation.  All ducts and conduit shall be installed to conform to the line and grade shown on the plans or as directed by the Engineer.

The multiple ducts shall be installed according to the manufacturers recommended installation practices.  The ducts shall be built from each manhole towards the center, and joined using duct fittings without cutting or splicing.  The manhole terminating sections will be caulked with silicone at the manhole entry.

PVC conduits may be equipped with factory installed couplings.  It shall be the Contractors responsibility to test these couplings to assure that they will provide a waterproof connection.  If connections are not waterproof, the Contractor shall waterproof them prior to installation.  The inside of all PVC conduit fittings and the ends of all ducting shall be painted with PVC solvent cement as prescribed by the manufacturer to make a waterproof connection.

Throughout the project there are several curves where the PVC conduit will have to be formed in a smooth symmetrical curve.  Approximately 5 degrees of deflection can be obtained per 10-foot length of PVC conduit.  If additional deflection is needed, the Contractor may use either 5 degree couplings, or heat and bend the conduit in accordance with the manufacturers specifications.  Some PVC conduit runs may require the installation of owner-furnished expansion couplings as directed by the Engineer.

The Contractor may be required to field bend the RMC conduit for roadway crossings as set forth on the plans, however, ATU will make available standard 45 and 90 degree RMC conduit elbows.  All RMC conduit that is formed and bent by the Contractor will be inspected by the Engineer prior to installation.  Any bent conduit that is deformed will not be acceptable, and will be removed and replaced at the Contractors expense.

The Contractor shall design and provide all tie-down stakes.  He will be responsible for their effectiveness and shall bear all costs incurred if "flotation" or misalignment occurs.

Each night, or immediately upon completion of any phase of the telephone duct system installation, the Contractor will cap or plug the ducts to prevent any gravel or debris from entering.  All dirt, gravel and other debris shall be cleaned from the manholes and ducts prior to acceptance.  All duct ends not terminating in a manhole shall be capped or plugged.  If the end of the ducts are on the low end of the run, a 1/4-inch hole shall be drilled in the lowest point of the cap or plug, unless the run is below the water table.

All 4-inch conduit stacked two or more high shall be bound with a plastic strap fastened with a stainless steel clip, one strap at each 4-foot interval and one strap 18-inches from the end of each conduit section.  The strap shall be 5/8-inch plastic, and shall be a type that will work with a binder machine.  1 x 2-inch wood spacers will be required between the ducts, vertically on 4-foot centers.  When the conduits are stacked two or more high, the Contractor shall stagger all couplings 5-feet.

The Contractor is responsible for installing all items indicated on the plans in the trench.  The approval to backfill by the inspector does not limit the Contractors responsibility of physically checking to assure that all items have been installed prior to backfilling.  Items omitted from the trench shall be added at the Contractors own expense.

All ducts and conduit encasement shall be with water-compacted sand or concrete slurry, at the Contractors option.  The sand shall be 1/4-inch minus material with a maximum 6 percent passing the No. 200 sieve.  The concrete slurry shall be not less than two (2) standard 94-lb sacks per cubic yard of concrete.  The bottom of the trench will be free of any large stones or rock.  Sand will be water flushed around the ducts to

fill the voids created by the spacers.  All sand placed for encasement shall be water-tamped and floated to assure good compaction.

After completion of the installation, the telephone duct system shall be mandrilled and brushed by ATU, prior to acceptance.

680-3.08  Cable Pulling.  The Utility shall install and splice the telephone cable.

680-3.09  As-built Drawings.  The final red-lined as-built drawings shall be delivered to the Engineer prior to final acceptance of the system by the owning Utility.  The Contractor shall maintain an accurate record of the underground location of all the telephone manholes, ducts and conduit installed on the two sets of prints provided by ATU.  These shall include all line, grade and elevation changes.

680-4.01  Method of Measurement.  Measurement for payment of ducts and conduit will be that horizontal distance from the outside of the manhole, or change in configuration to the outside of the next manhole or change in configuration.  The 4-inch PVC drain, to the west out of manhole W3 will be measured the same as telephone ducting.

680-5.01  Basis of Payment.  Payment will be full compensation for all labor, equipment, tools and incidental materials necessary to install materials approved by the Engineer.

Payment for duct will be the length of 6-way duct units installed times the unit bid price.  Payment for conduit will be the number of conduits times the length of conduit installed times the unit bid price.

The unit bid prices will include all necessary excavation to plan grade, and backfill of native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 203(1), Common Excavation. If Borrow, Type A or oversized rock, is required for backfill to replace suitable material will be paid under Item 203(6-A), Borrow, Type A.

Payment will be made under:

Pay Item No.           Pay Item              Pay Unit

680(2)         6-Way Telephone Duct      Linear Foot

680(4-__)     _ -inch Telephone Duct     Linear Foot

680(5)      Install Telephone Manholes      Each

680(7-_)      _ -inch Steel Sleeve       Linear Foot

680(9)         Telephone As-Builts        Lump Sum

Add the following Section:

SECTION 681

ELECTRICAL POWER RELOCATION

Special Provisions

681-1.01  Description.  The Contractor shall be responsible for furnishing all labor, equipment and materials necessary to install electrical duct banks, both concrete encased and sand bedded, together with junction and pull boxes, switching cabinet pads with manhole extensions (vaults), and transformer pads for Chugach Electric Association (Chugach).  The electrical duct banks will consist of multiple conduits of the number shown on the plans.  The Utility will supply electrical vaults, and power cable and will pull the electrical power cable.  Upon completion of the utility splicing, and cut over the utility will remove the existing aerial facilities including the existing utility poles.

The Contractor shall also provide as-built drawings in accordance with the conditions prescribed herein.

The Contractor doing this work shall be a licensed electrical contractor licensed by the State of Alaska.  His work will be closely inspected by Chugach with their instructions relayed to the Contractor through the Engineer.  The Chugach representative will be assigned for the entire underground installation, and no work shall proceed without him on site.  The Contractor shall

advise Chugach in writing at least 24 hours in advance of his actual duct system work indicating both location and time.

681-2.01  Materials.  The concrete encased duct banks will consist of rigid steel conduit (RSC), or Type EB or Schedule 40 rigid polyvinyl chloride (PVC) conduit.  RSC or Schedule 40 PVC conduit shall be used for all sand bedded duct banks.  RSC conduit shall be manufactured of mild steel with a galvanized coating.  Conduit locator plates shall be supplied by the Contractor and be standard materials for locating the ends of buried conduits.

The cement shall be a recognized standard brand Portland Cement contained in 94-lb sacks or 376-lb barrels bearing the manufacturers name.  The cement shall conform to the AASHTO M-85.

681-2.02  Applicable Standards and Codes.  In order to resolve any questions on safety regulations, installation practices, and testing procedures, the Contractor shall consult and make himself familiar with the applicable parts of the current editions of the following standards and codes:

1.	Alaska State Safety Code

2.	Arctic and Subarctic Construction - Utilities,           US Army Corps of Engineers

3.	Chugach Electric Association Safety Code

4.	National Electrical Code

5.	National Electrical Safety Code

6.	National Electrical Manufacturers Association

7.	Occupational Safety Health Act

8.	Underwriters Laboratories

All equipment and material furnished under this Section shall conform to the latest applicable specifications and rules of the National Electrical Manufacturers Association, American Standards Association, American Institute of Electrical Engineers and the Federal Specifications cited hereinafter.  As appropriate, all materials used shall be listed on the latest "List of Material Acceptable for Use on Systems of REA Electrification Borrowers", and approved for this electrical system by Chugach.

All materials furnished shall be standard equipment and be of the manufacturers latest design.  These materials shall be new, and not used, manufacturers second or rejects.  Where two or more units of the same class of material are required, they shall be like products of the same manufacturer.

681-2.03  Verification of Dimensions.  The exactness of dimensions given on any Chugach drawing is not guaranteed, and therefore the Contractor shall field verify the accuracy of all dimensions.  In all cases of interrelation with other work, he shall verify in the field all the dimensions relating to the contiguous work.  Any errors due to the Contractors failure to verify shall be rectified promptly at the Contractors cost.

681-3.01  General Construction Requirements.  Chugach through the Engineer reserves the right to suspend the electrical duct bank installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspension of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

The electrical duct banks shall be installed to result in the maximum degree of reliability and maintenance-free operation.  Kinked ducts, inadequately supported, protected or swabbed ducts, and ducts that are carelessly jointed are not reliable and therefore unacceptable.  Any section of this electrical duct system that is not acceptable will be removed and replaced in accordance with these Special Provisions.

All conduit shall be stored to prevent damage or contamination prior to installation.  Conduit shall not be laid directly on the ground or floor, and it is preferable to store them in a vertical position.  They shall be kept clean and dry as possible and free from damaging or deteriorating elements.  Temporary storage and installation of electrical duct banks shall be in accordance with NEMA Bulletin TCB-2 (1976), "Users Manual for the Installation of Underground Plastic Duct".

If construction or excavation require the removal of any existing privately owned facilities on the provided electrical easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed 2 weeks.

A program of cleanup operations shall be carried out on a continuous basis throughout the progress of construction, and the site shall be left neat and clean.  All equipment, devices and structures shall be inspected after installation has been completed, and any damage shall be repaired or replaced as directed.

681-3.02  Surveying and Staking.  All vaults, pads and electrical duct systems shall be located and staked by the Contractor at the elevations indicated on the plans.  It shall be his responsibility to schedule a physical inspection of all line and grade prior to placing any vaults, pads or ducts.  Once work commences, the Contractor, the Engineer and Chugach will meet at the end of each week to review the work to date, and plan the following weeks work.

All duct systems shall be constructed to within an allowable vertical tolerance of 0.1-foot, and a horizontal tolerance of 0.2-foot from the indicated plan location.

681-3.03  Trench and Pad Excavation and Backfill.  All existing underground utilities shall be identified and located, and proper care taken not to damage them.  It shall be the Contractors responsibility to establish the location of each facility by calling for a field locate in accordance with Subsection 105-1.06, Cooperation with Utilities.

The excavation shall be dug in such a manner as to provide a foundation of undisturbed non-frost susceptible material on which to install the vaults, pads or electrical duct banks.  Trench depth shall be as shown on the plans, and as staked in the field.  Trenches shall be of the necessary width that will allow compaction equipment to be utilized, and for proper laying of structures or conduit.  The banks of the excavation shall be sloped so as to conform to the prevailing safety requirements.

The trenches shall be maintained in a safe manner at all times to protect workers from cave-ins.  Appropriate shoring shall be employed to assure safety of workers while working in trenches.  Barriers and warning signs shall be employed to protect the public and employees from falling into trenches where such trenches are in areas vulnerable to these accidents.  Vehicles and excavation equipment must not cross over or run near trenches that could cause potential cave-ins.  Construction shall be arranged so the trenches will be left open for the shortest practical time to avoid creating a hazard, and to minimize the likelihood of trench collapse due to other construction activity, rain, and accumulation of water in the trench, etc.  All temporary bridging utilized by the Contractor will be inspected and approved prior to installation.  This does not relieve the Contractor of responsibility for providing bridging of sufficient size and strength.  Any bridging open to public traffic will provide a smooth driving joint.

The Contractor shall not begin excavation of the trench until all personnel, materials and equipment are present to complete the work in the most expedient manner.  Not more than 400-feet of trench shall be open in advance of the installation unless authorized in writing by the Engineer.  There shall be no more than 100-feet of open trench at the end of the work day, unless approved by the Engineer.

The routing of the duct banks shall be as shown on the plans unless the conditions encountered are such that changes are necessary to accomplish the work.  In the event that rock or other obstructions are encountered during the trenching operation so the ducts or pads cannot be installed, the Contractor shall inform the Engineer on the nature and extent of the difficulty encountered for his review and verification.  The Engineer, with the approval of Chugach, will determine whether the duct is to be rerouted, trenched in the rock or advise on another suitable change.

All excavation shall be inspected and approved by the Engineer before duct bank installation is started.  After the ducts are installed, the Engineer shall approve their line and grade prior to concrete encasement or sand backfill. Trench Acceptance, Conduit Installation and Concrete Placement forms shall be filled out by Chugach and signed by the electrical subcontractor after approval of each stage.  Failure to complete these forms will result in the rejection of the work.  The Contractor shall provide 24 hour written notification to Chugach when a section of the duct system is ready for an acceptance inspection and a time for this inspection shall be mutually agreed upon.  Failure by Chugach to attend the prearranged inspection shall not relieve the Contractor of the requirement to have the section accepted by Chugach.  However, any additional costs which are involved, such as repumping of the vaults, will be in accordance with Subsection 109-1.05, Compensation for Extra Work.

All frost susceptible material below the specified trench depth shall be removed to a depth of 2 feet, and all organic material shall be removed to non-organic material below the manhole duct system.  Backfill to the electrical duct bank grade, if necessary, will be with material meeting the requirements of Selected Material, Type A, deposited in layers not exceeding 8-inches, and each lift shall be compacted to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankment with Moisture and Density Control.

The bottom of the trench must be transversely level to provide a uniform support for ducts.  The trench excavation shall be kept free of any water while placing concrete.  Care shall be exercised to minimize the likelihood of waterflow since this may cause trench damage and reduction in trench depth.  When this occurs, the trench must be cleared to the required depth before installing the ducts.

When below the structural section of the roadway, 8-inches of Selected Material, Type A, shall be spread over the concrete encasement in the trench not sooner than 24 hours after the concrete is placed.  The balance of the trench above the electrical duct banks shall be backfilled and compacted in 8-inch lifts with material meeting the requirements of Selected Material,  Type C, to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankment with Moisture and Density Controls, up to the bottom of the roadway structural section.  The desired compaction shall be obtained with mechanical tamping machines.  Outside of the limits of the structural section, the Contractor may backfill with native material.  No construction or other activity shall be permitted across any trench until a depth of 3 feet of fill above the duct banks has been placed and compacted in accordance with these Special Provisions.

The foundation of the vaults shall be 2 feet of non-frost susceptible materials.  Backfill, if necessary, will be with material meeting the requirements of Selected Material, Type A, placed in 8-inch layers compacted to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankment with Moisture and Density Control.  Backfill 2-foot around the vaults shall be with compacted non-frost susceptible materials.

681-3.04  Conduits.  The PVC conduit shall be provided by the Contractor, and be Type EB for concrete encasement or Schedule 40 for sand bedding.  The RSC conduit shall also be supplied by the Contractor, and used for shallow depths or roadway crossings where concrete encasement is not feasible.

Fittings - Conduits and fittings shall be jointed by means of a solvent welding cement to provide a watertight and root-proof joint.  All conduits shall be cut off square with a hacksaw.  The cut end shall be face flat and properly reamed with a reamer designed for the purpose of removing the sharp edge.

3-inch plastic spacers with a maximum horizontal spacing of 8-feet are to be used for separation for concrete encased ducts.

Only tools designed for the particular operation shall be used.  Tools shall be kept in good condition, and worn or broken tools shall be removed from the job immediately.

Bending - All bending of conduit will be by means of infrared heating and bending equipment, Carlon "Hotbox Bender" or equivalent.  No cold bending of conduit will be accepted.

All conduit shall be field bent to follow the trench line and grade with a minimum radius of 25-feet.  All bends will be per the manufacturers recommendations.  The minimum allowable bending radius for equipment entrances is 48-inches.  Preformed sweeps and preformed elbows with bending radii less than 48-inches will not be allowed.  The material for all preformed elbows of 90 degrees will be RSC conduit for concrete encasement and all other installations.  All bends will be approved by the Engineer.

Duct Finishing - After completion of backfilling and compaction, the electrical duct systems will be mandrilled, brushed and swabbed.  All bell ends shall be beveled.  The steel mandrill and steel brush shall be 3-1/2 inches in diameter for the 4-inch conduit, and 5-1/2 inches in diameter for the 6-inch conduit.  If the duct will not accept the mandrill, it will be removed and replaced at no additional expense.  All mandrilling must be done in the presence of the Engineer and Chugach.  All conduit entrances and exits into the vaults shall then be sealed and plugged.

A 3/16-inch diameter polyethylene or polypropylene pull rope, with a minimum breaking strength of 700 pounds, shall be left in each conduit with a 3-foot length of rope projecting from the conduit at each substructure and securely tied.  When a conduit plug is used, the rope shall be securely tied to it in a manner approved by the Engineer.  All pull ropes shall be new and unspliced.

Each conduit run destination shall be identified by 3/4-inch letters on 3 x 5-inch metal or plastic tags secured to the wall with silicon adhesive immediately above the conduit entrance, identifying the terminus of the conduit run, for example: "To SC 000".

681-3.05  Electrical Duct Bank Installation.  All electrical duct banks on this project will be comprised of multiple PVC or RSC conduits of the configuration shown on the plans.  The conduits for the primary distribution circuit will be concrete encased, or direct bury as noted on the plans.

It shall be the Contractors responsibility, with the Engineers approval, to determine the most expedient method to complete the required electrical duct bank installation.  All work across the roadway shall be accomplished in accordance with Section 643, Traffic Maintenance.

Concrete Encased Duct Banks - Concrete forms, when required by the Contractors operation, shall be secured and braced to resist all deformation or displacement while under load, and shall be constructed to line, grade and dimensions shown on the plans.  The forms shall be installed in such a manner as to be easily removed without hammering or prying against green concrete.  Reinforcing bars shall be provided at all locations detailed on the plans.

The concrete mix shall be designed to produce a plastic and workable mixture, and a compressive strength at 28 days of at least 2500 psi.  Only pre-mix concrete will be allowed.

The Contractor shall tie down the conduit prior to placement of concrete.  The concrete shall be placed continuously, extending from cabinet pad to cabinet pad whenever possible.  Placement not terminating at a cabinet pad shall be approved by the Engineer, and shall be ended with a shear key and reinforcing steel.  All concrete shall be placed by means of a concrete vibrator, and in such a manner as to prevent damage or displacement to either the forms, ducts, spacers, steel reinforcing, or other insert accessories.

Concrete shall not be placed if there is standing water in the forms, or if the subgrade is saturated.  Placing of concrete may be initiated when the temperature is not less than 40 degrees F and rising, and the soil temperature is greater that 34 degrees F.  The concrete shall have a minimum temperature of 50 degrees F and the addition of anti-freeze salts or solutions will not be allowed.  At temperatures of 40 degrees F and below, the Contractor shall keep the concrete covered and apply heat to maintain a minimum temperature of 41 degrees F during the total curing period.

All concrete forms shall be left in place for a minimum of 24 hours until the concrete becomes firmly set.

Sand Bedded Duct Banks - When used for roadway crossings, RSC or PSC conduits shall be bedded in compacted sand to the grades detailed on the drawings.  All sand placed for embedment shall be water-tamped and floated to assure good compaction.

Conduit for Service Connections - RSC or Schedule 40 PVC conduit will be provided for all existing service connections.  The conduits of the number shown on the plans will be installed after the encased electrical duct system has been initially backfilled.  The end of the conduit run will be marked with a standard conduit locator plate.

Residential Duct Banks.  Concrete encased residential duct banks installed behind retaining walls shall contain the number and arrangement of conduit shown on the plans.  The concrete mix shall attain a 28 day compressive strength of 2500 psi, and may be placed 3-inches around the duct bank directly into the trench without forms.  The primary conductor shall be encased in 2-inch RSC conduit, or 4-inch Schedule 40 PVC conduit as indicated on the drawings.

681-3.06  Switching Cabinet Pads with Manhole Extensions, and Transformer Pads.  The cabinet pads and extensions (vaults), and transformer pads shall be built to the dimensions detailed in the plans.  The Engineer shall be notified as soon as the manufacture of one pad is complete so final inspection can be made by the Engineer and Chugach.  The Contractor will be responsible for all pads manufactured in excess of one without approval.

The concrete mix for the switching cabinet pads with extensions, electrical transformer pads, junction boxes and pull boxes shall be so designed that tests of compressive strength at 28 days shall show at least 3000 psi and shall produce a plastic and workable mixture.

Before installation the Contractor shall verify the required clearances from curbs, sidewalks, pathways and driveways, and the orientation of the vaults with the Engineer.  The vaults shall conform to the final grade after completion of the project.  All vault joints and exterior faces are to be sealed and waterproofed with an approved sealer.

681-3.07  Cable Pulling.  The Utility shall install and splice the electric power cable.

681-3.08  Cable Burial.  Not Used.

681-3.10  As-Built Drawings.  An as-built survey by a land surveyor registered in the State of Alaska will be compiled by the Contractor on the mylars provided by Chugach of all electrical duct banks and pads, including the locations, alignment and installed depth.  The information will be referenced to established survey monuments.  Delivery shall be to the Engineer prior to acceptance of the electrical duct system by the owning Utility.

681-4.01  Method of Measurement.  Concrete encased RSC and PVC conduit, sand bedded RSC and Schedule 40 PVC conduit, residential duct bank, and service connects will be measured by the linear foot along the horizontal length of the installed construction unit.

The electrical switching cabinet pads with manhole extensions shall be measured by the unit, complete and accepted in the final position.  Concrete transformer pads, junction boxes and pull boxes will also be measured per each accepted unit.  Ground rods shall not be measured for payment, but will be included in the prices for the pads.

681-5.01  Basis of Payment.  Payment will be full compensation for all labor, equipment and materials necessary to complete this work.

Payment for a concrete encased duct bank, and a sand bedded electrical conduit system will be the length of the construction unit conduits installed times the unit bid price per linear foot for each construction unit.  Residential duct banks and electrical service connections shall be paid per linear foot of the total system regardless of the number and type of conduits.  The price paid for the electrical duct system shall include all necessary fittings.

Junction and pull box installations will be paid per each, as an electrical transformer pad.

The unit bid prices will include all necessary regardless excavation to plan grade, and backfill of native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 203(1), Common Excavation.  Borrow, if required, for backfill to replace unsuitable material will be paid under Item 203(6-A), Borrow, Type A.

Payment will be made under:

Pay Item No.          Pay Item               Pay Unit

681(1)       SUR2-6, Trenching-Direct     Linear Foot

Burial Primary Conductor

681(2A)     XUR2/6ER, Concrete Encased    Linear Foot

Duct 2-6" EB PVC Reinforced

681(2B)     XUR4/6ER, Concrete Encased    Linear Foot

Duct 4-6" EB PVC Reinforced

681(2C)     XUR6/6ER, Concrete Encased    Linear Foot

Duct 6-6" EB PVC Reinforced

681(3-2)     XURC2/2S, Road Crossing      Linear Foot

2-2 Inch Steel Conduits

681(3-4)     XURC2/4S, Road Crossing      Linear Foot

2-4 inch Steel Conduits

681(4-2)    Elbow 2-90S, Conduit-Elbow       Each                    2-inch 90 Degree Steel

681(4-4)   Elbow 4-90S, Conduit-Elbow        Each

4 inch 90 Degree Steel

681(4-6)   Elbow 6-90S, Conduit-Elbow        Each

6 inch 90 Degree Steel

681(5-3)       XUM1-G3, Wall Unit            Each

3 Sections With Floor

681(5-4)       XUM1-G4, Wall Unit            Each

4 Sections With Floor

681(6-F)  XUM1-GA, 600 AMP, Switch Cabinet   Each

Base With Front Orientation

681(7)       XUM1-GM, Manhole Base           Each

681(8)    XUM1-GR, Grade Adjustment Ring     Each

681(9)       XUM1-MC, Manhole Cover          Each

681(13)   SUM1, Pad Assembly-25 KVA/250 KVA  Each

Single Phase Concrete Pad

681(14)         XUR2-7SK, Concrete           Each

Encased Duct Splice Key

681(15)        Electrical As-Builts        Lump Sum

681(16)    XUM1-SC, Switch Opening Cover     Each

Add the following Section:

SECTION 683

NATURAL GAS RELOCATION

Special Provisions

683-1.01  Description.  The Contractor shall be responsible for the removal of all natural gas pipeline that has been abandoned and is in conflict with the work.

683-3.01  General Construction Requirements.  	That pipe designated for removal shall be cut and disposed of off the project limits.  This work cannot begin until the new main is installed and pressurized.

Add the following Section:

SECTION 684

CABLE TELEVISION RELOCATION

Special Provisions

684-1.01  Description.  The Contractor will furnish all labor, equipment, and perform all operations necessary to complete the construction and installation of the owner-furnished conduits required for the completion of the project.  The cable television system will consist of multiple conduits of the size and number shown on the plans.  This work is to be performed in accordance with this contract, the National Electric Code and the National Electric Safety Code.

The Contractor shall provide as-builts in accordance with the conditions prescribed herein.

This work shall also be inspected by Sonic Cable Television, (Sonics), with their instructions relayed by the Engineer to the Contractor.

684-2.01  Materials.  The following materials will be furnished by Sonics:

1.	All rigid metal conduit, fittings and caps

2.	All pull wires.

3.	All PVC conduits, fittings and caps.

All furnished materials may be obtained at the Sonic Cable Television Warehouse, 201 East 56th Avenue, between the hours of 8:00 AM and 4:00 PM, Monday through Friday.  The Contractor shall be responsible for pickup, storage and safekeeping of all materials after receipt.  All materials will be inspected by representative from both parties and an acceptance document stating materials are free from defects will be signed.  All unused materials shall be returned to the warehouse upon completion of the project.

684-3.01  Construction Requirements.  All cable television conduit systems should be located as shown on the plans with relation to other duct installations. Alignment should be such that there are no protrusions which will harm the cable being pulled through the conduit.

The trench excavation shall not be any deeper or wider than necessary for the proper installation of the conduit, and shall not be performed until immediately before placement of the conduit.  The bottom of the trench shall be relatively smooth.

If construction or excavation require the removal of any existing privately owned facilities on the provided television easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed 2 weeks.

All backfill for the television system shall be approved native material compacted in 8-inch lifts to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankment with Moisture and Density Controls, up to the bottom of the roadway structural section.  If outside the structural section, native backfill material shall be placed in layers and compacted as approved by the Engineer.

All television conduit shall be laid to a minimum depth of 48-inches below the finished roadway grade.

The clearance between various duct or conduit systems should be as much as possible to permit maintenance of the system without damage to other parallel systems.  Separation between conductors of 300 volts or more and the television conduit shall be either:

1.	12-inches of well compacted native materials,

2.	4-inches of masonry, or

3.	3-inches of concrete

The ends of all conduits, whether shop or field cut, shall be reamed to remove burrs and rough edges.  Cuts shall be made square and true so that the ends will butt together for the full circumference.  When a standard coupling cannot be used for coupling metal type conduit, an approved threaded union coupling shall be used.  All couplings for the metal conduit shall be tightened until the ends of the conduit are brought together, providing a good electrical connection throughout the entire length of the conduit run.

All metal conduit ends shall be threaded and capped with standard plastic pipe caps or approved threaded electrical plug and coupling combinations until wiring is started.  When caps are removed, the threaded ends shall be provided with approved conduit bushings.  All conduit runs shall be capped where open to ground until wiring is started.  Conduit shall be restrained to resist movement during backfilling and cable pulling.

All dirt, gravel, ice and other debris shall be cleaned from all conduits prior to acceptance.  Pull wires shall then be placed in all conduits with ends 2-feet in length wrapped and tied around tops of conduit.

Should moisture, galvanic action, or corrosion be observed which is attributed to Contractors workmanship (i.e., waterproofing, nongalvanic and corrosion preventative methods or materials used) the Contractor shall immediately take corrective action to resolve and correct the problems at his own expense.

684-3.02  Cable Pulling.  The utility shall install and splice the television cable and install the pedestals.

684-3.03  As-Built Drawings.  The final as-built drawings shall be delivered to the Engineer prior to final acceptance of the system by the owning Utility.  The Contractor shall provide as-built location of underground construction on plat maps supplied by Sonics.  He shall maintain accurate records of underground routing of the television system.  This shall be achieved by drawing the conduit offset from the roadway centerline to where the conduit has been buried.

684-4.01  Method of Measurement.  Measurement for payment for the cable television system will be the number of linear feet of individual RMC conduit of the size indicated, installed and accepted.

684-5.01  Basis of Payment.  Payment will be full compensation for all labor and equipment necessary to install owner-furnished conduit, approved by the Engineer in conjunction with Sonics.  All PVC items which are necessary to complete the television conduit system as detailed on the plans are incidental to the RMC pay items.  The unit bid price will include all excavation to plan grade and backfill of native materials outside the normal lines of the roadway structural section.  Any excavation of unsuitable material below plan grade shall be paid under Item 203(1A), Common Excavation.  Backfill to replace unsuitable material will be paid under Item 203(6-A), Borrow, Type A.

Payment will be made under:

Pay Item No.         Pay Item           Pay Unit

684(1-_)       __-Inch RMC          Linear Foot

Television Conduit

684(2)        Cable Television       Lump Sum

As-Builts

SECTION 702

ASPHALT MATERIALS

Standard Modifications

702-2.04  Storage And Application Temperatures.  In Table 702-1, change storage temperatures for ACs from "340 Max" to "325 Max".  (05/12/89)

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  Fine Aggregate For Concrete.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.  (Revision 05/12/89)

703-2.02  Course Aggregate For Concrete.  In the first sentence, insert ", class B," after "AASHTO M 80".  (Revision 05/12/89)

Special Provisions

703-2.03  Aggregate for Base.  Add to the requirements:

Plastic Index     AASHTO T-90     6 max.

Add the following to Table 703-2:

Sieve Designation			D-1

1-1/2 inch				---

1 inch					100

3/4 inch					70-100

3/8 inch					50-79

No. 4					35-58

No. 8					20-47

No. 40					8-23

No. 200					0-6

Standard Modifications

703-2.04  Aggregate For Plant Mix Asphalt Pavement.   Add the  following to the end of the second paragraph: ", including S1.1, Sulfate Soundness Test.  (5/12/89)

Special Provisions

703-2.04  Aggregate for Plant Mix Asphalt Pavement.  In the third paragraph, after Fine Aggregate, delete the remainder of the sentence after "thereof" and add the following:

The fine aggregate will meet the following requirements:

Plastic Index     AASHTO T-90     4 max.

Sodium Sulfate    AASHTO T-104   15 percent max.

Soundness Loss

Add the following to Table 703-3, Asphalt Concrete Aggregate:

Asphalt Concrete

Sieve Designation                   Type IIA

3/4-inch                           100

1/2-inch                          82-100

3/8-inch                          68-90

No. 4                            50-79

No. 10                           36-67

No. 40                           17-44

No. 80                            9-29

No. 200                           3-10

703-2.07  Selected Material.  Add the following to Item l., Selected Material, Type A:  It shall have 30 to 55 percent by weight of particles passing the No. 4 sieve.

SECTION 707

METAL PIPE

Special Provisions

707-2.02  Bituminous Coated Corrugated Steel Pipe, Pipe Arches and Underdrains.  Add the following to the second paragraph:  The full coating of the conduits shall be in accordance with AASHTO M-190, Type D.

707-2.05  Water Conduit.  Delete in its entirety and add the following:

1.	Applicable Standards for Water Conduit.  The most recent revision for the following standards for the American Society for Testing and Materials (ASTM), the American Association for State Highway and Transportation Officials (AASHTO), the American Standards Association (ASA), and the American Water Works Association (AWWA) are hereby made a part of these specifications:

ANSI/AWWA C-104/A21.4-85		Cement Mortar Lining            for Ductile Iron Pipe and Fittings for Water.

ANSI/AWWA C-105/A21.5-88		Polyethylene Encasement Ductile Iron Piping For Water and Other Liquids.

ANSI/AWWA C-110/A21.10-87	Ductile Iron and Gray Iron Fittings, 3-Inch Through 48-Inch, For Water And Other Liquids.

ANSI/AWWA C-111/A21.11-85	Rubber Gasket Joints for Ductile Iron and Gray Iron Pressure Pipe and Fittings.

ANSI/AWWA C-115/A21.15-88	Flanged Ductile Iron Pipe with Threaded Flanges.

ANSI/AWWA C-150/A21.50-81	Thickness Design of Ductile Iron Pipe.

ANSI/AWWA C-151/A21.51-81	Ductile Iron Pipe, Centrifugally Cast in Metal Molds Or Sand Lined Molds, For Water Or Other Liquids.

2.  Ductile Iron Pipe and Fittings.

a.		Pipe.  Ductile iron pipe shall conform to AWWA C-151, with cement mortar lining meeting the requirements of AWWA C-104.  Class 52 ductile iron pipe shall be used for water conduit between 3 and 16-inches in diameter unless otherwise indicated on the plans.

b.		Fittings.  All fittings shall be a minimum 250 psi pressure rating, mechanical joint or all bell, either lined or unlined, either cast iron or ductile iron, unless otherwise indicated on the plans or in these special provisions.  All fittings shall meet the requirements of AWWA C-110.

Rubber gasket joints for ductile iron pipe and fittings shall conform to AWWA C-111.

c.		Piping Joints and Connections.

(1)	Joint Tie Rods.  Tie rods shall be all-thread black iron or mild steel and shall be located symmetrically around the perimeter of the pipe, using anchoring lugs of standard manufacture for attachment where required.  Tie rods shall be 3/4-inch diameter on pipe 16-inches and less.  There shall be 2 rods on pipes 12-inches and less and 4 each on pipes 14-inches to 16-inches in diameter.

707-2.06  Service Pipe.  Delete in its entirety and

add the following:

Pipe.  Ductile iron pipe or soft drawn seamless copper type "K" shall be used for all water service pipe.  Galvanized pipe, asbestos-cement pipe and the use of lead-tipped gaskets shall be prohibited.

Key Box, Valve Box.  The key box shall provide clear and unobstructed access to a valve or curb stop to enable the AWWU operation of the valve or curb stop.  Key boxes or valve boxes shall be furnished and installed in accordance with Subsection 627-3.05, Valve Boxes and 4

Subsection 712-2.11, Valve Service Boxes.  AWWU key boxes shall not be in contact with a natural gas main or service line.

707-2.07  Sewer Conduit.  Add the following subsection:

1.	Applicable Standards for Sewer Conduit.  The most recent revision for the following standards for the American Society for Testing and Materials (ASTM), the American Association for State Highway and Transportation Officials (AASHTO), the American Standards Association (ASA), and the American Water Works Association (AWWA) are hereby made a part of these specifications:

ANSI/AWWA C104/A21.4			Cement Mortar lining for ductile-iron pipe and fittings for water

ANSI/AWWA C105/A21.5    		Polyethylene encasement for ductile-iron piping for water and other liquids

ANSI/AWWA C110/A21.10		Ductile-iron and gray-iron fittings, 3 in. through 48 in., for water and other liquids

ANSI/AWWA C111/A21.11		Rubber-gasket joints for ductile-iron and gray-ironpressure pipe and fittings

ABSI/AWWA C150/A21.50		Thickness design of ductile-iron pipe

ANSI/AWWA C151/A21.51		Ductile-iron pipe, centrifugally cast in metal molds or sand-lined molds, for water or other liquids

2.	Ductile Iron Pipe and Fittings.

a.		Pipe.  Ductile iron pipe shall conform to  ANSI/AWWA C151/A21.51, with cement mortar lining meeting the requirements of ANSI/AWWA C104/A21.4.  Class 50 ductile iron pipe shall be used unless otherwise required.

b.		Fittings.  All fittings shall be a minimum 250 psi pressure rating, mechanical joint or all bell, either lined or unlined, either cast iron or ductile iron, unless otherwise indicated on the plans or in these Special Provisions.  All fittings shall conform to the requirements of ANSI/AWWA C110/A21.10.

Rubber gasket joints for ductile iron pipe and fittings shall conform to ANSI/AWWA C111/A21.11.

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.05  Precast Concrete Units.  Add the following after the first paragraph:  Sanitary sewer manholes shall also conform to the requirements of the details shown on the Plans.  Cones shall be Type (b), eccentric, unless otherwise approved.

Each precast concrete barrel section shall be set upon and sealed with pre-molded plastic gasket as manufactured by K.T. Snyder Co., Ram-Nek Gasket Division, 2100 Travis Street, Houston, Texas or equal.

712-2.06  Frames, Grates, Covers and Ladder Rungs.  Add the following:  Ductile iron castings shall conform to the requirements of ASTM A536 for grade 60-4018.  (9/1/89)

712-2.09  Corporation Stops and Curb Stops.  Add the following:  Use Mueller Corporation Stop No. 15000 or equal for 3/4-inch and 1-inch service pipe connections.  Use Mueller Curb Stop No. H15214 or equal for 3/4-inch and 1-inch, copper to copper connections.  Rod to be attached to curb stop with no. 6 gauge copper wire.

Use Mueller Corporation Stop No. 15025 or equal for 1-1/2-inch and 2-inch service pipe connections.  Use Mueller Curb Stop No. H15214 Ori-Seal or equal for 1-1/2 inch and 2 inch connections.  Mueller Service Clamp or equal with two straps shall be used on all pipe.  Rod to be attached to curb stop with no. 6 gauge copper wire.

712-2.10  Gate Valves.  Delete this subsection in its entirety and substitute the following:  712-2.10  Valves.

1.	Gate Valves.  Gate valves shall be iron body, fully  bronze mounted, double disc, parallel seat valves as manufactured in accordance with the requirements of AWWA C500 "Gate Valves for Ordinary Water Works Service".  All valves shall be nonrising stem type with an O-ring seal and a 2-inch square operating nut, and shall open counterclockwise.  Valves shall have mechanical joint ends.

2.	Butterfly Valves.  Butterfly valves shall be of the rubber-seated tight-closing type.  They shall meet or exceed performance requirements of AWWA C504 for operational pressures of 150 psi working pressure and 300 psi hydrostatic pressure.

Mechanical joint valve ends shall be per AWWA C110 and C111 of the latest revision, and "Short-Body" in accordance with the requirements of Table 2 of AWWA C504.  Accessories (bolts, glands and gaskets) shall be supplied by the valve manufacturer.

Valves must use full AWWA C504 Class 150 B valve shaft diameter and full Class 150 B underground service operator torque rating throughout entire travel to provide capability for operation in emergency service.

Valve body shall be high strength cast iron ASTM A-126 Class B.  For valves with the rubber seat mounted on the disc, the mating surface in the body shall be 304 or 316 steel.  For valves containing the rubber seat in the body, the method of  retention shall be in accordance with the requirements of AWWA C504, except that no retaining fasteners or other hardware shall be permitted in the flow stream.

The valve operator, unless otherwise specified in the Special Provisions, shall be of the traveling nut type, sealed, gasketed, and lubricated for underground service and capable of withstanding an overload input torque of 450 ft-lbs at full open or closed position without damage to the valve or valve operator.  The number of turns to operate the valve shall be a minimum of two turns per inch of valve diameter for 90 degrees of closure travel at a maximum pull of 80 pounds.  All valves shall open counter clockwise and be equipped with a 2-inch square AWWA operating nut.

712-2.11  Valve Service Boxes.  Delete in its entirety and substitute the following:

1.	Valve Boxes.  Valve boxes, whether installed for mainline valves or curb stops, shall be cast iron of sliding, adjustable-height type with round or oval bottom hood sections to fit over the top of the valve.  The top section shall be recessed to receive a close fitting "eared" lid with the word "WATER" or "SEWER cast into it. Internal diameter of the smallest section shall not be less than 5-inches.  The minimum thickness of the metal shall not be less than 5/16-inch.  Castings shall be smooth and the workmanship shall be acceptable to the Engineer.

Valve boxes shall be sufficient length for the pipe cover depth shown on the profile drawings and in accordance with the details shown on the plans.

2.	Markers.  Valve boxes shall be marked with a marker consisting of 2-1/2 inch O.D. galvanized steel pipe sections, 7-feet in length, with 3-feet buried in the ground.  Markers shall be shop painted "Caterpillar Yellow" and stenciled with 2-inch black numerals, showing the appropriate references.  Markers shall be located on the nearest property line, due north, south, east or west of the valve at a maximum distance of 50-feet, unless otherwise directed by the Engineer.  Markers shall carry the notation "VB (feet)(direction)".  Markers will not be required where valve boxes are located in paved areas.

712-2.12  Hydrants.  Delete in its entirety and add the following:

1.	Fire Hydrants.  Fire hydrants shall conform to the minimum standards of AWWA C-502 for Dry Barrel Fire Hydrants.  They shall be Mueller Centurian or equal.  Also,  all fire hydrants shall meet the following requirements.

a.		All hydrants shall be supplied with a 5-1/4 inch main valve opening.

b.		All single pumper hydrants shall be furnished with a 6-inch ASA Class 125 standard mechanical-joint end with two cast-on lugs for tie backs.  All double pumper hydrants shall be furnished with an 8-inch ASA Class 125 standard mechanical joint end with two cast-on lugs.

c.		All connections shall be mechanical joint unless otherwise indicated in the Special Provisions.

d.		Single pumper hydrants shall be furnished with two 2-1/2 inch hose connections and one  4-1/2 inch pumper connection.  The double pumper hydrants shall have one 2-1/2 inch hose connection and two 4-1/2 inch pumper connections.

e.		Unless otherwise specified in the plans, all hydrants shall be furnished with a barrel length that will allow a minimum of 10-foot bury.

f.		The main valves shall be of the compression type, where water pressure holds the main valve closed, permitting easy maintenance or repair of the entire barrel assembly from above the ground without the need of a water shut-off.

g.		All fire hydrants shall be furnished with break-away flange of the type which allows both barrel and stem to break clean upon impact from any angle.  Traffic flange design must be such that repair and replacement can be accomplished above ground.

h.		Painting and coating shall be in accordance with AWWA specifications.  The hydrant section from the traffic flange to the top of the operating nut shall be painted "Caterpiller Yellow".

i.		Operating and nozzle nuts shall be pentagon shaped with 1-1/2 inch point to flat measurements.

j.		All working parts shall be bronze of noncorrosive metal in accordance with the requirements of AWWA C-502.

k.		All hydrants shall be right hand opening (clockwise).

l.		Hose nozzle threading shall be in conformance with NFPA #194 for National (American) Standard Fire Hose Coupling Screw Threads.

m.		All hydrants shall have drain outlets at the base of the barrel.  Manufacturer plugs shall not be removed prior to installation.

2.	Auxiliary Gate Valves.  All gate valves shall be furnished and installed in accordance with Subsection 627-3.04 and Subsection 627-3.05.

3.	Leg Thaw Pipe.  The leg thaw pipe shall be stenciled with a 2-inch black letter "L", installed on the left hand side of the hydrant and fabricated into an "L" shape.  The vertical portion shall be 6-inches to the side and 3-inches to the rear of the traffic flange extending 15-inches above finished grade with no perforations.  The horizontal portion shall be 6-inches above and 6-inches to the side of the hydrant leg and shall be perforated with 1/8-inch diameter holes, spaced 1-foot apart facing the center of the hydrant leg.

4.	Barrel Thaw Pipe.  The barrel thaw pipe shall be stenciled with a 2-inch black letter "B" installed on the right hand side of the hydrant from 6-inches above the hydrant leg and extending 15-inches above finished grade, and installed vertically 3-inches to the rear and 6-inches to the side of the traffic flange.  The barrel thaw pipe shall be perforated with 1/8-inch diameter holes spaced 1-foot apart starting 18-inches below finished grade and facing the hydrant barrel.  A 1/4-inch machine screw shall be installed 1-inch below the cap to provide identification of the barrel thaw pipe.

5.	Tie Rods.  Tie rods must be 3/4-inch O.D. all-thread black iron or mild steel.

712-2.14  Preformed Pavement Markings.  Add the following to paragraph A. under Item 1., General Requirements:  The preformed ribbon shall consist of one solid piece of required width and length.  In solid stripe area, the tape length shall, where possible, be a minimum of 100 feet.

712-2.15  Temporary Raised Pavement Markers.  Add the following:  The temporary raised pavement markers shall be installed utilizing an approved raised pavement marker flexible bituminous adhesive.

The color of the raised pavement markers shall conform to the color of the markings for which they serve as a positioning guide, or for which they supplement, or substitute.

SECTION 714

PRESERVATIVES AND PRESERVATIVE TREATMENT

PROCESSES FOR WOOD MATERIALS

Special Provisions

714-2.01.  Add the following:  The following preservative treatments with corresponding retention values are allowed for the material being treated.

Preservative       Retention

Material             Standard       Treatment          Value

Douglas Fir-Larch

Fence posts          AWPA C5    Pentachlorophenol    0.50 pcf

and Bollards                          ACC            0.50 pcf

ACA            0.40 pcf

ACZA            0.40 pcf

CCA            0.40 pcf

SECTION 724

SEED

Special Provisions

724-2.02   Materials.  Add the following to Table 724-1:

Percent

Seed        Germination  Percent    Percent     Sproutable

Type          Period___  Purity_  Germination     Seed

Bering

Hairgrass     14 days      95         75           71

American

Sloughgrass   14 days      95         85           81

SECTION 726

TOPSOIL

Standard Modifications

726-2.01 Topsoil.  Modify the second paragraph from "not less than 1%" to "not less than 3 percent". (5/12/89)

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01  Embankment Separation and Reinforcement.  Delete this Subsection and Table 729-1 on page 575 in their entirety and substitute the following:

1.	Fibers used in the manufacture of geotextiles, and the threads used in joining geotextiles by sewing, shall consist of long chain synthetic polymers, composed of at least 85% by weight polyolefins, or polyesters.  The geotextile shall be formed into a stable network such that the filaments or yarns retain their relative position to each other.  Both the geotextile and threads shall be resistant to chemical attach, mildew, and rot.

2.	Nonwoven geotextile may be formed by the needle-punched, spun-bonded or heat-bonded process.

3.	Woven geotextile shall be woven into a uniform pattern with distinct and measurable openings.  Edges of the cloth shall be selvaged to prevent the outer yarn from pulling away from the cloth.  The fabric shall be free from defects.

4.	The geotextile supplied shall meet the requirements listed in Table 729-1 for the type specified.

5.	The Contractor shall submit certification that the geotextile supplied meets the above requirements before it is used on the project.

Table 729-1

GEOTEXTILE REQUIREMENTS FOR

EMBANKMENT SEPARATION AND REINFORCEMENT

┌─────────────────────────────┬────────────┬───────────────┐

│                      Test   │            │               │

│Geotextile            Method │            │               │

│Property              (ASTM) │ Separation │ Reinforcement │

│                             │            │               │

│Grab Elongation,      D-4632 │  <50   >50 │    30 max.    │

│% @ Breaking Load            │            │               │

│                             │            │               │

│Grab Tensile          D-4632 │  175   105 │     180       │

│Load, lbs., min.             │            │               │

│                             │            │               │

│Bursting Strength     D-3786 │  N/A   N/A │     290       │

│psi., min.                   │            │               │

│                             │            │               │

│Trapezoid Tearing     D-4533 │   50    40 │      65       │

│Strength, lbs., min.         │            │               │

│                             │            │               │

│Puncture Resistance   D-4833 │   70    40 │      75       │

│lbs., min.                   │            │               │

│                             │            │               │

│Water Permittivity,   D-4491 │ 0.04   0.3 │               │

│1/sec., min.                 │            │     0.02      │

│                             │            │               │

│Apparent Opening      D-4751 │  0.3  0.21 │     0.85      │

│Size, mm., max.              │            │               │

│                             │            │               │

│Ultraviolet           D-4355 │   70    70 │      70       │

│Degradation @ 500            │            │               │

│hour exposure, %             │            │               │

│Strength Retained            │            │               │

│                             │            │               │

│Acceptance, Pass      D-4759 │ Pass   Pass│     Pass      │

│or Fail                      │            │               │

└─────────────────────────────┴────────────┴──────────────┴┘

NOTES:

1.	Separation geotextile supplied may have either less than, or greater than 50% elongation measured at breaking load in the Grab Tensile Test (ASTM D-4632).

2.	Geotextile Property Values = Minimum average roll values at a 95% confidence level in the weaker principal direction.

3.	0.21 mm. = US Standard Sieve Size 70.

4.	0.3 mm. = US Standard Sieve Size 50.

5.	0.85 mm. = US Standard Sieve Size 20.

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04  Sign Post.  Under Item 1., Metal Pipe Posts, add the following to paragraph a:  Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

5.	Structural Tubing and W Shape Beams

a.		Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the plans with 0.1875 (3/16) inch thick walls.  7/16 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.		W shape beams shall conform to ASTM A36.

c.		Structural  tubing  and W shape beams shall be hot dip galvanized in accordance with 1.b of this subsection.  Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

APPENDIX A

PERMITS

APPENDIX  B

THAW WIRE SPECIFICATIONS

APPENDIX C

CONSTRUCTION SURVEYING REQUIREMENTS