NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	Copies for review of the following are available in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Computations

b.	Cross Sections

c.	As-built Plans and Shop Drawings of the existing bridges over the Knik and Matanuska Rivers (Bridge Nos. 1121, 1122, 1123 and 1124).  Copies of the above documents may be obtained from Ridgeway's Reprographics, 6000 Arctic Boulevard, Anchorage, Alaska  99518, telephone (907) 561-1555.

2.	The following reports are available upon request:

a.	Geotechnical Report entitled "Glenn Highway: Eklutna to Parks Highway, Phase 1A", dated August 1990.

b.	Foundation Report entitled "Glenn Highway:  Eklutna to Parks, Phases 1C and 1D", dated November 1991.

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Traffic, Safety and Utilities Engineer, (907) 266-1531.

4.	An Environmental Assessment and Reevaluation addressing concerns and environmental commitments has been approved and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 266-1737.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS FOR HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.27  Holidays.  Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's Birthday - Third Monday in January.

3.	President's Day - Third Monday in February.

(5/7/91)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  Qualification of Bidders.  Delete the second paragraph.  (5/12/89)

102-1.06  Preparation of Proposal.  Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

(5/7/91)

102-1.07  Non-Responsive Proposals.  Delete item 3. in its entirety and substitute the following:

3.	If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to any one bidder at any one bid letting, as provided in Subsection 102-1.06.  (5/7/91)

Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)

102-1.12  Addenda Requirements.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  Consideration of Proposals.  Add the following:  The apparent low bidder shall, within 5 working days following the bid opening, submit either a list of all firms with which the prime Contractor intends to execute subcontracts for the performance of the contract  or a  statement  that  the  bidder  intends to perform the work without subcontractors.   The list shall include the following information for each proposed subcontractor:

1.	name,

2.	business address,

3.	Alaska business license number,

4.	Contractor's registration number,

5.	the work to be performed, and,

6.	the approximate dollar amount of the work to be performed.

If the apparent low bidder fails to submit either a list of subcontractors or a statement that the bidder intends to perform the work without subcontractors, the apparent low bidder will be found not to be a responsible bidder and may be required to forfeit the bid security.  The Department will then consider the next lowest bidder for the award of the contract.

If a bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess  of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this Subsection.

If a contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department, or,

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the contract with the bidder involving work for which the subcontractor was  listed,

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or,

9.	is determined by the Contracting Officer not to be responsible.

(12/26/90)

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  Changes.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)

Special Provisions

104-1.02  Changes.  Delete the first three paragraphs and substitute the following:  The Engineer reserves the right to make, in writing, at any time during the work, such changes in quantities and such alterations in the work as are necessary to satisfactorily complete the project.  Such changes in quantities and alterations shall not invalidate the contract nor release the surety, and the Contractor agrees to perform the work as altered.

If the alterations or changes in quantities significantly change the character of the work under the contract, whether or not changed by any such different quantities or alterations, an adjustment, excluding loss of anticipated profits, will be made to the contract.  The basis for the adjustment shall be agreed upon prior to the performance of the work.  If a basis cannot be agreed upon, then an adjustment will be made either for or against the Contractor in such amount as the Engineer may determine to be fair and equitable.

If the alterations or changes in quantities do not significantly change the character of the work to be performed under the contract, the altered work will be paid for as provided elsewhere in the contract.

The term "significant change" shall be construed to apply only to the following circumstances:

1.	When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction, or

2.	When a major item of work, as defined elsewhere in the contract, is increased in excess of 125 percent or decreased below 75 percent of the original contract quantity.  Any allowance for an increase in quantity shall apply only to that portion in excess of 125 percent of original contract item quantity, or in case of a decrease below 75 percent, to the actual amount of work performed.

(4/13/89)

Add the following:  No value engineering proposals will be considered for this project.  (9/1/89)

104-1.03  Differing Site Conditions.  Delete in its entirety and substitute the following:  During the progress of the work, if subsurface or latent physical conditions are encountered at the site differing materially from those indicated in the contract or if unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the work provided for in the contract, are encountered at the site, the party discovering such conditions shall promptly notify the other party in writing of the specific differing conditions before they are disturbed and before the affected work is performed.

Upon written notification, the Engineer will investigate the conditions, and if he determines that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any work under the contract, an adjustment, excluding loss of anticipated profits, will be made and the contract modified in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment which results in a benefit to the Contractor will be allowed unless the Contractor has provided the required written notice.

(4/13/89)

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  Authority of the Engineer.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)

Special Provisions

105-1.06  Cooperation With Utilities.  Add the following:  The Contractor shall request locates from all the Utilities having facilities in the area.  Their telephone numbers are as follows:

DOT/PF Maintenance & Operations          266-1584

(Palmer)

Matanuska Electric Association, Inc.     745-3231

Matanuska Telephone Association, Inc.    745-3121

Enstar Natural Gas Co. (Wasilla)         376-7979

Alaska Railroad Corporation              265-2457

Rogers Cablevision                       373-2288

City of Palmer                           745-3271

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Prior to the relocation of the utility's facilities, construction stakes by the Contractor in the areas of utility conflicts may be required.  The Utility will request the stakes, through the Engineer, with two (2) weeks advance notice.

Any work within 10 feet of any MEA facility will require prior notification and coordination with the utility.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the Utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

A cathodic protection area sweep is required after all underground work has been completed and before paving begins.  The sweep will take one (1) day to perform and will require three (3) working days notice to ENSTAR prior to performing the work.  If any underground contacts are detected, additional time will be required to perform repairs.

Electrical Cable Damage.	If a cable is damaged and requires splicing, the first time will be repaired by the Utility with the party causing the damage paying the repair costs.  If the cable is damaged a second time, the cable will be replaced between junction points.  The party causing the damage shall pay for replacing the cable.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

The following specific coordination requirements are indicated for each Utility:

1.	Matanuska Electric Association.  MEA work items associated with this project are detailed in the "UE" sheets of the contract and are as follows:

a.	Relocate guy/anchor assemblies at Sta. "NB" 889+72 Lt and Sta. "NB" 948+60 Lt.  This work will be completed by August 15, 1992.

b.	Relocate 3-phase overhead distribution line between Sta. "NB" 984+96 and the Knik River.  The Contractor shall install guardrail and/or temporary barrier (as required by the Engineer) prior to routing traffic to the southbound lanes.

c.	Upgrade existing service to serve new load center "F" at Sta. "SB" 1303+60, 50-ft Lt.  The Contractor shall install 40 feet of 6-inch culvert under the Alaska Railroad at Sta. "SB" 1301+86.48, 75-ft Lt.  The culvert will accommodate MEA's upgraded service to new load center "F".  Depth of bury of the culvert shall be 5.5 feet under the railroad ties.  The Contractor shall notify MEA in writing within five days of completion of the culvert construction so that MEA can schedule crews to install their PVC conduit and connect the load center.

d.	MEA will provide temporary overhead service to the existing meter base at the Alaska Railroad crossing.  The Contractor shall notify MEA in writing at least two weeks prior to any work in this area so that the existing service pole at approximate Sta. "SB" 1300+08, 15-ft Lt can be removed and the new temporary service pole can be installed.  The Contractor shall furnish and install conductor from the meter base to the temporary railroad signal controller.  The temporary service will be effective until new load center "F" is energized and will provide continuous power for the railroad signal.  The Contractor shall remove the existing meter pole in the southwest quadrant once the temporary service is disconnected.

e.	MEA will upgrade the existing overhead service to provide power to new load center "E" at Sta. "PH" 13+60, 55-ft Rt.  The Contractor shall install conduit from the existing service pole to the meter base on the new load center.  The Contractor shall remove the existing meter pole.

f.	Line extension to provide service to load center "B" at Sta. "NB" 1004+50, 280-ft Rt.

g.	Line extension to provide service to load centers "C" and "D" at Sta. "BRFR" 53+00,   15-ft Lt and Sta. "KRR1" 100+45, 35-ft Rt, respectively.  This line extension will cross the Knik River Ramps, Glenn NB and Glenn SB.  The Contractor shall install 445 feet of 12-inch culvert at Sta. "NB" 1077+60.16, parallel to the pipe underpass, as shown on the plans.  The culvert shall be buried a minimum of 48 inches below the ditchline.  The Contractor shall install a nylon pull-rope in the culvert.  The ends of the culvert shall be capped with plywood and the pull-rope exposed through the ends.  The Contractor shall notify MEA in writing within five days of completion of the culvert construction so that MEA can schedule crews to install their PVC conduit and connect the load centers.  The balance of the line extension work at this location will consist of direct-buried cable in an easement outside the west right-of-way from the culvert crossing to new load center "C".

2.	ENSTAR Natural Gas Company.

a.	Sta. 1003+42.  ENSTAR will open-cut the Glenn Highway to install a 4-inch steel gasline across the median ditch and the northbound lanes.  The crossing will be made from an existing 4-inch stub off of the existing 20-inch transmission pipeline.  This crossing will terminate with a new operating valve at approximate Sta. 1003+72, 250-ft Rt.  ENSTAR requires approximately one (1) week to do this work.

In order to maximize coordination with the highway construction and associated traffic control, the Contractor shall provide ENSTAR with a written, 15-day notice prior to any of the following:

(1)	Slope flattening on the new southbound lanes,

(2)	Movement of traffic onto the new southbound lanes, or,

(3)	Any slope work on the existing northbound lanes.

b.	Sta. 1252+25.  Prior to May 1, 1993, ENSTAR will install nine, 4-foot-long, 3500-lb., bolted-on saddle weights to the existing 20-inch gas transmission line that crosses Rabbit Slough approximately 50 feet downstream of the Glenn Highway.  ENSTAR will dam the slough upstream of the highway then install the weights on the gasline.  The Contractor shall notify ENSTAR, in writing, three (3) weeks prior to the construction of the Rabbit Slough culvert and rock apron.  The three (3) week notification is required so that ENSTAR can perform their work as well as locate and inspect their facility during the construction of the culvert and apron.

c.	Sta. "SB" 1293+30.  ENSTAR's existing 6-inch transmission pipeline and 4-inch gasline to their regulator station in the northwest quadrant at Nelson Road is within the muck excavation limits of the southbound lanes.  The Contractor shall contact Enstar a minimum of 36 hours prior to excavation for on-site location of the gasline.  The Contractor shall support and protect the gasline during the excavation and backfill operation.  The Contractor shall notify ENSTAR at least 24 hours in advance of any excavation within ten feet of transmission pressure facilities so that they may provide for their inspection of this work.

105-1.07  Cooperation Between Contractors.  Add the following:  Additional contracts will be let by the Department within or bordering the project limits and portions of the work under these contracts will be performed concurrently with this project.  The additional contracts are as follows:

1.	Glenn Highway, Eklutna to Parks, Phase 1-B

2.	Glenn Highway, MP 35 to 56

3.	Glenn Highway, Eklutna to Parks, Phase 1-D (to be awarded Spring 1993).  Scope of work includes an interchange at the Old Glenn Highway intersection and a frontage road from Rabbit Slough to Nelson Road.

The Contractor shall coordinate his traffic control, construction, and material hauling operations with the prime contractors of the above contracts so as to minimize impact on the travelling public, and to minimize conflicts with the work being performed under the other contracts.  No removal of existing structures that would result in interference with smooth and efficient traffic flow through the existing construction zone of Phase 1-B will be allowed.

105-1.12 Load Restrictions.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless otherwise allowed by an approved Traffic Control Plan.  (5/7/91)

Overload and oversize permits are required to move the prestressed concrete girders between the Port of Anchorage or an Anchorage fabricating yard and the job site.  No overload may cross the Ship Creek Bridge, Bridge No. 417.  Unless otherwise permitted by the overload permit officer, any permit will be subject to the following limitations:

Maximum Single Axle Load          30,000 lbs.

Maximum Tandem Axle Load          60,000 lbs.

Maximum Triple Axle Load          80,000 lbs.

Maximum Four Axle Load            95,000 lbs.

Maximum Spacing of Axle Groups    20 feet c. to c. axle                                    groups

Minimum Spacing within Group      4 feet c. to c. axles

Maximum Speed on any Structure    3 mph

The maximum axle loads tabulated above are applicable to hauling equipment with fixed axles only; variable load suspension (VLS) axles shall not be considered part of an axle group for purposes of this specification.

Vehicles shall cross structures at a constant speed, centered on the roadway, and with no shifting of gears.  Whenever the load exceeds 80,000 pounds, the vehicle shall be preceded by a walking flagger when crossing structures.

This overload allowance shall not apply to the transportation of construction materials other than prestressed concrete girder sections.

All overload permits are subject to seasonal load restrictions.  Routing shall be as prescribed by the permit officer, 1-(800) 478-7636 or (907) 345-7750.

Alternate axle configurations and loadings which may reduce the overload movement restrictions and conditions are subject to individual review and analysis by the permit officer.

105-1.15  Project Completion.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work scheduled under subsection 618-3.04, Maintenance of Seeded Areas, a letter of project completion will be issued by the Engineer.  (7/1/90)

105-1.17  Claims for Adjustment and Disputes.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (2/1/91)

Add the following:  Legal actions will be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/29/87)

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  Source of Supply and Quality Requirements.  Add the following:  All steel and iron products which are incorporated into the work and the action of applying a coating to a covered product (i.e., steel and iron) shall be produced in the United States except that minor amounts of products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater.  Coating includes epoxy coating, galvanizing, painting, and any other coating that protects or enhances the value of a material subject to the requirements of this paragraph.  For the purposes of this paragraph, the cost is the value of the steel and iron products as they are delivered to the project.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel or iron products into the project.

(6/23/92)R156

106-1.02  Local Material Sources.  General.  Add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)

Add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement will be given to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01  Laws to be Observed.  Add the following:  Specific Equal Employment Opportunity Responsibilities of Federal-Aid Construction Contractors.

1.	General.

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form 25D-55) and these Special Provisions which are imposed pursuant to Section 140 of Title 23, U.S.C., as established by Section 22 of the Federal-Aid Highway Act of 1968.  The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the equal employment opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State highway agencies and the Federal Government in carrying out equal employment opportunity obligations and in their review of his/her activities under the contract.

c.	The Contractor and all his/her subcontractors holding subcontracts not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of equal employment opportunity:  (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as Contractors and subcontractors.)  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.

2.	Equal Employment Opportunity Policy.  The Contractor will accept as his operating policy the following statement which is designed to further the provision of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

"It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include:  employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprentice-ship and/or on-the-job training."

3.	Equal Employment Opportunity Officer.  The Contractor will designate and make known to the Engineer and equal employment opportunity officer (hereinafter referred to as the EEO Officer) who will have the responsibility for and must be capable of effectively administering and promoting an active Contractor program of equal employment opportunity and who must be assigned adequate authority and responsibility to do so.

4.	Dissemination of Policy.

a.	All members of the Contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the Contractor's equal employment opportunity policy and contractual responsibilities to provide equal employment opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

(1)	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the Contractor's equal employment opportunity policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor's equal employment opportunity obligations within thirty days following their reporting for duty with the Contractor.

(3)	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the Contractor's procedures for locating and hiring minority group employees.

b.	In order to make the Contractor's equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

(1)	Notices and posters setting forth the Contractor's equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The Contractor's equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

5.	Recruitment.

a.	When advertising for employees, the Contractor will include in all advertisements for employees the notation:  "An Equal Opportunity Employer."   All such advertisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority group applicants, including, but not limited to, State employment agencies, schools, colleges and minority group organizations.  To meet this requirement, the Contractor will, through his EEO Officer, identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority group applicants may be referred to the Contractor for employment consideration.

In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor's compliance with equal employment opportunity contract provisions.  (The U.S. Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or women, or obligates the Contractor to do the same, such implementation violates Executive Order 11246, as amended.)

c.	The Contractor will encourage his present employees to refer minority group applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures with regard to referring minority group applicants will be discussed with employees.

6.	Personnel Actions.  Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The Contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The Contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with his obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the Contractor will inform every complainant of all of his avenues of appeal.

7.	Training and Promotion.

a.	The Contractor will assist in locating, qualifying, and increasing the skills of minority group and women employees, and applicants for employment.

b.	Consistent with the Contractor's work force requirements and as permissible under Federal and State regulations, the Contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.  In the event the Training Special Provision is provided under this contract, this subparagraph will be superseded as indicated.

c.	The Contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.	The Contractor will periodically review the training and promotion potential of minority group and women employees and will encourage eligible employees to apply for such training and promotion.

8.	Unions.  If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and female employees.  Actions by the Contractor either directly or through a Contractor's association acting as agent will include the procedures set forth below:

a.	The Contractor will use best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

b.	The Contractor will use best efforts to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The Contractor is to obtain information as to the referral practices and policies of the labor union except that the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the Contractor, the Contractor shall so certify to the State highway department and shall set forth what efforts have been made to obtain such information.

d.	In the event the union is unable to provide the Contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the Contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minority group persons and women.  (The U.S. Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees.)  In the event the union referral practice prevents the Contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such Contractor shall immediately notify the State highway agency.

9.	Subcontracting.

a.	The Contractor will use his best efforts to solicit bids from and to utilize minority group subcontractors or subcontractors with meaningful minority group and female representation among their employees.  Contractors shall obtain lists of minority-owned construction firms from State highway agency personnel.

b.	The Contractor will use his best efforts to ensure subcontractor compliance with their equal employment opportunity obligations.

10.	Records and Reports.

a.	The Contractor will keep such records as are necessary to determine compliance with the Contractor's equal employment opportunity obligations.  The records kept by the Contractor will be designed to indicate:

(1)	the number of minority and nonminority group members and women employed in each work classification on the project,

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to Contractors who rely in whole or in part on unions as a source of their work force),

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority group subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such records must be retained for a period of three years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the State highway agency and the Federal Highway Administration.

c.	The Contractor will submit an annual report to the State highway agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form PR 1391.  If on-the-job training is being required by "Training Special Provision", the Contractor will be required to furnish State of Alaska Form 25A312.

(4/8/83)

107-1.08  Railway-Highway Provisions.  Delete the second paragraph and add the following:

1.	Definition of Terms.

a.	Railroad's Manager of Telecommunications and Signaling - the person employed by the Railroad as head of its Telecommunications Department or his authorized representative.

b.	Railroad's Chief Engineer - the person employed by the Railroad as head of its Engineering Department or his authorized representative.

c.	Railroad's Contracting Officer - the person authorized by the Railroad to execute contractual agreements on behalf of the Railroad.

d.	Facility - any improvements owned by the Department which are to be placed on Railroad Property in accordance with a written permit executed by the Railroad and the Department.

e.	Permit Area - the space on Railroad property that is or will be occupied by the Facility plus reasonable working area and reasonable ingress and egress to the Facility.

f.	Railroad - the Alaska Railroad Corporation, P.O. Box 107500, Anchorage, Alaska  99510-7500.

g.	Railroad Property - all lands owned or withdrawn for the use of the Railroad, in and including the track right-of-way and communications pole right-of-way.

h.	Trackwork - all work on the line from the top of subgrade to the top of rail, including geotextile, when required.

i.	Track Materials - all hardware, excluding signals and controllers, associated with the running of a railroad.

2.	General Requirements.

a.	All construction, reconstruction, operation and maintenance on the Railroad Property shall be performed in compliance with these specifications.

b.	Failure to comply with these specifications  shall result in the suspension of all work on Railroad Property.  The Contractor shall comply immediately upon notification from the Department, either verbal or written.

c.	All negotiations between the Railroad and the Contractor shall be handled through the Department.

d.	All work on or about the Railroad Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with the approved Railroad practices, and as specified herein.  Railroad traffic and property shall be protected at all times.

e.	The safety and continuity of the operation of the railroad traffic shall be of first importance and shall be at all times protected and safeguarded.  The Contractor and his subcontractors shall perform and arrange their work accordingly.  The Railroad's Chief Engineer shall decide all matters involving the safety of Railroad facilities and the operation of it's railroad.  The approval of the Railroad's Chief Engineer, when given, shall not be considered as a release from responsibility or liability for any damage which the Railroad may suffer or for which it may be liable, as a result of the acts of the Contractor, his subcontractor or employees.

f.	Whenever in the opinion of the Railroad's Chief Engineer, the construction may cause a hazard to the safe operation of the Railroad, the Railroad may, at its discretion, place at the site of the work the required number of qualified employees to protect its operations.  The providing of such employees and such other precautions as may be taken shall not relieve the Contractor and his subcontractors from liability for the payment of damages caused by their operations.  The Railroad shall be the sole judge of necessity, as to the number and classification of employees required.  All Railroad cost and expense for providing such employees shall be collected from the Contractor, except for flagging which shall be paid for as described in Subsection 107-1.08.5.b.

g.	The Contractor shall be responsible for maintaining sight triangles at existing railroad crossings as well as at any temporary crossings within the project limits and at any railroad crossing outside the project limits that is designated and used as an alternate route for traffic.

3.	Insurance Requirements.

a.	The Contractor shall comply with all insurance requirements and conditions specified under Subsection 103-1.05, except that the following minimum limits shall apply for Comprehensive or General Liability Insurance:

Bodily Injury - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Property Damage - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Blanket Contractual

b.	Prior to commencement of work on Railroad Property, the Contractor shall provide evidence of Railroad Protective Liability insurance (Alaska Railroad and State of Alaska as insureds) with the following limits:

Bodily Injury - $2,000,000 per occurrence

Property Damage - $2,000,000 per occurrence

4.	Notice.

a.	The Contractor shall give written notice to the Department and the Railroad not less than 10 days in advance of the commencement of any construction, reconstruction or major maintenance activity on Railroad Property, in order that the necessary arrangements may be made for the protection of the Railroad's operation.  This notice shall include the proposed schedule of work, and the names of the subcontractors who may also be working on Railroad Property.

b.	A preconstruction meeting shall be held with the Railroad's Chief Engineer and representatives of the Department and Contractor prior to the commencement of any work on Railroad Property by the Contractor or his subcontractors.

5.	Flag Protection and Protection of Railroad Traffic.

a.	Whenever Railroad flag protection is required in the specifications, this flag protection shall be provided by person(s) authorized by the Railroad.  Each person so authorized shall have met the Railroad's qualifications for flagmen.  Railroad flag protection is to insure the safe movement of trains and other rail traffic and shall be done in strict accordance with the Railroad rules on flagging.

b.	The Contractor shall, during the progress of the work, furnish as many qualified flagmen, as in the opinion of the Railroad, may be required for the adequate protection of the Railroad traffic.  If Railroad employees are used as flagmen, all Railroad expenses for providing such flagmen shall be reimbursed by the Department, except for flagging as described in Subsections 107-1.08.8.b and c., in which case the Railroad expenses shall be paid by the Contractor.  If the Contractor calls for flagmen and, through no fault of the Department or the Railroad, the flagmen are not needed, payment shall be deducted from monies due the Contractor.

c.	Vehicles and other construction equipment shall not be parked or operated closer than 20 feet from centerline of any track without Railroad flag protection provided in accordance with Subsection 107-1.08.5.a.

d.	The Contractor shall arrange with the Railroad to keep himself informed of the time of arrival of all trains and shall entirely stop any of the operations which might be or cause a hazard to the safe passage of the train past the site of the work from 10 minutes before the expected arrival of the train until the train has passed.

6.	Train Delays.

a.	All work on Railroad property shall be conducted in such a manner as to prevent delays to trains or other rail traffic operated by the Railroad.

b.	Should any of the Contractor's or subcontractor's actions or activities cause delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

| Passenger Trains | $50 per minute for each delay. $3,000 minimum charge. |
| --- | --- |
| All other trains and rail traffic | $50 per minute for each delay over five minutes. $1,500 minimum charge. |
| Rail barges, train-ships or other connecting carrier vessels | No charge for delays of an hour or less. $1,000 per hour for each hour or any part of an hour thereafter, with a minimum charge of $6,000. |

c.	Delay time will be taken from the train sheet in the Railroad Dispatcher's Office, in Anchorage, (265-2649) for all delays and such train sheet shall be the official document by which the length of time a train is delayed will be determined.  If another crew is needed to relieve the original crew, the charge shall also apply to the second crew.  If such delay causes a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by said train sheet.

7.	Protection of Railroad Communication Lines.

a.	All work on Railroad Property shall be conducted in such a manner as to protect the Railroad's communications facilities at all times from outages resulting directly or indirectly from the Contractor's or his subcontractor's operations.

b.	Should any of the Contractor's, or his subcontractor's operations cause outages to said communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

| Open wire communication circuits | $1.00 per minute per circuit |
| --- | --- |
| Communication cable | $5.00 per minute per cable |

c.	A minimum charge of $250 will be made for each outage.  The outage time shall be that as established by the Railroad's Test Board, Anchorage.

d.	There shall be no equipment worked or excavation within 15 feet of any Railroad communication pole guy, anchor, or other communications apparatus unless authorized in advance by the Railroad's Manager of Telecommunications and Signaling.

8.	Railroad Crossings.

a.	Whenever automatic railroad crossing signals are in the permit area, these signals must remain in operating condition at all times.  If, as a result of the Contractor's activities on the facility, the signals become inoperable the crossing shall be continuously protected in accordance with Subsection 107-1.08.5. until the signals are again operable.

b.	When regular railroad crossings are used as haul routes inside or outside the permit area, flagmen shall be provided by the Contractor for said crossings in all situations at the discretion of the Railroad.

c.	Temporary road crossings may be installed, provided the Contractor has acquired from the Railroad a temporary road crossing permit for said crossing.

The temporary crossing shall be constructed to the standards specified in the temporary crossing permit.  All protective signs required by the Railroad shall be provided and properly maintained by the Contractor.  When a temporary railroad crossing is in use, Railroad flag protection shall be provided at all times in accordance with Subsection 107-1.08.5.  When not in use during the winter season, the temporary crossing shall be removed unless specifically allowed in the temporary crossing permit.  Upon completion of the work or termination of the temporary crossing permit, the temporary railroad crossing shall be removed and the area restored to its original condition.

d.	The flange ways of all road crossings used by the Contractor or subcontractor as haul routes or temporary road crossings shall be kept free of gravel at all times and shall otherwise be maintained to the satisfaction of the Railroad's Chief Engineer.

e.	When a temporary or private road crossing is not in use, the Contractor shall provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

9.	Power and Communication Lines.

a.	All power and communication lines shall be designed and constructed in accordance with National Electric Safety Code (NESC).

b.	Underground power and communication lines shall be installed in accordance with Subsection 107-1.08.10.  Whenever an underground power or communication line crosses underneath a track, a casing pipe shall be installed for carrying such lines.

c.	The minimum clearance above the top of a rail of the Railroad track shall be in accordance with the NESC, plus 6 inches to allow for future grade raises.

d.	The minimum clearance above the Railroad communication lines shall be in accordance with the NESC.

e.	Additional lines may not be added, or the characteristics of the line(s) changed without written approval of the Railroad's Contracting Officer.

f.	Wires shall be strung across the Railroad tracks only when Railroad flag protection is provided in accordance with Subsection 107-1.08.5.

g.	No wires shall be strung across the Railroad's communication lines without first receiving approval from the Railroad's Manager of Telecommunications and Signaling therefor, and such work must be accomplished only at a time and in a manner prescribed by said Manager of Telecommunications and Signaling.

10.	Underground Facilities.

a.	All underground utilities, including culverts, pipelines and underground power and communication lines, on Railroad property shall conform to the current AREA Specifications.

b.	Unless another method is authorized in advance and in writing by the Railroad's Chief Engineer, all underground facilities shall be installed under tracks and roads by boring, jacking or tunneling.

c.	Boring, jacking and tunneling shall be done under Railroad tracks only when Railroad flag protection is provided in accordance with Subsection 107-1.08.5.

d.	The proposed plan for boring, jacking or tunneling shall be approved by the Railroad's Chief Engineer prior to commencing the operation.

e.	All boring, jacking or tunneling headings shall be continuously protected against any loss of ground material by shoring or cribbing as necessary.

11.	Open Trenching.

a.	Only when authorized in advance and in writing by the Railroad's Chief Engineer shall any portion of the track be removed to allow trenching for installation of the facility.

b.	If allowed to open trench, the track may be removed from service only at the time authorized by the Railroad's Chief Engineer and shall be restored to service within the time period specified by the Railroad's Chief Engineer.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in accordance with Subsection 107-1.08.6., whichever is greater and shall be collected from the Contractor.

c.	All work on track materials shall be accomplished by qualified trackmen.

d.	Only that portion of the track structure necessary to excavate, stockpile and install the facility shall be removed.  All track material removed shall be handled, stockpiled, and relaid in a manner as to avoid damage.  Any material which is damaged shall be replaced by the Contractor at his own expense.

e.	The backfill of the trench under the track and in the roadbed prism shall be of the same type of material as taken out, except the top 2 feet shall be clean pit run gravel.  Backfilling and compaction in the area affecting the roadbed prism shall be in accordance with the requirements of Section 204, Structure Excavation for Conduits and Minor Structures.

f.	The ballast used in replacing the track shall be equal in depth and quality to that which was removed.  The track shall be relaid and brought to original grade in accordance with standard Railroad practices.

12.	Excavations.

a.	Unless authorized in advance and in writing by the Railroad, the top of any excavation shall not be within 20 feet of center line of any track.

b.	No water shall be allowed to stand in open excavations in the track area.

c.	Bridging and shoring shall be adequate to safely carry Railroad traffic and the decision of the Railroad pertaining to same shall be final.

d.	All open excavations shall be continuously protected by flags, barricades or watchmen, as directed by the Railroad.

e.	No excavation shall be left open more than three days, unless authorized by the Railroad's Chief Engineer.

f.	The Railroad embankment, and cut slopes, shall not be disturbed any more than necessary to accommodate the construction and shall be left in a stabilized condition.

g.	Railroad ditches, culverts and roadways shall be kept clean and free of rock, gravel, construction debris and equipment at all times.

13.	Railroad Inspectors.

a.	The Railroad may furnish an inspector during the periods of construction on Railroad Property.  The Railroad inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary.  The Railroad inspector will work directly with the representative of the Department and the decision of the Railroad inspector in matters pertaining to Railroad operations and safety shall be final.  In the event more than one shift is worked, a Railroad inspector will be required for each shift.  Presence or absence of a Railroad inspector shall not relieve the Contractor of liability for damage done to property of the Railroad, Railroad lessees or permittees having installations on Railroad Property.

14.	Use of Explosives.

a.	The use of explosives shall be done in compliance with all applicable Federal, State and local laws and ordinances regarding the same.

b.	No blasting of any kind will be permitted unless the Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, Railroad flag protection in accordance with Subsection 107-1.08.5., shall be provided on each side of the blast area by the Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

c.	The Contractor will notify the Alaska Railroad Inspector and the Engineer of the exact time of each blast at least two hours in advance.

15.	Snow Removal.

a.	Snow removal operations shall be conducted in such a manner as to not place snow (1) upon the tracks of the Railroad, (2) where it interferes with the normal operation of the automatic crossing signals, or (3) impairs the visibility of either highway or rail traffic  at the crossing.

b.	Snow removal operations shall be conducted in accordance with Subsection 107-1.08.5.

16.	Clean-Up.

a.	At all times, all work and activities on the Facility shall be accomplished in such a manner as to keep the Railroad Property in a neat and orderly condition satisfactory to the Railroad.

b.	Upon completion of work, all equipment and unused materials shall be removed and the Railroad property shall be left in a neat and clean condition satisfactory to the Railroad.

c.	Should the Contractor or subcontractor fail to comply with Subsections 107-1.08.16.a. and 16.b., the Railroad may perform the required clean-up.  All Railroad costs and expenses for performing this work shall be collected from the Contractor.

17.	Payment Guarantee.

a.	The Department shall withhold 10 percent of the contract price or $10,000.00, whichever is smaller, from the final payment to apply against damages or other direct costs which may be assessed by the Railroad as a result of the Contractor's operations.

b.	The amount withheld above shall not be released until after the Department has received a written statement from the Railroad's Contracting Officer agreeing to release the payment.

(5/7/91)

107-1.11  Protection and Restoration of Property and Landscape.  Add the following to the third paragraph:  When working near designated wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits.

The Contractor shall not excavate, nor use for fill, any material suspected of or found to contain hazardous substances or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected of or found to contain hazardous substances or petroleum fuels.

The Contractor shall report immediately to the Engineer any hazardous material discovered, exposed, or released into the air, ground, or water during construction of the project.  Also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery.  Hazardous materials include, but are not limited to, petroleum products, oils, solvents, paints, and chemicals that are toxic, corrosive, explosive, or flammable.  (5/7/91)

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2253.

Add the following:  The Contractor shall not use land from Palmer Hay Flats State Game Refuge or any other park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.

The Contractor shall do no work, trespass, stockpiling, staging, parking nor trespassing below the ordinary highwater mark of any watercourse, except for that work permitted in the Knik River, Matanuska River, Rabbit Slough or Spring Creek that is specified by the contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

Standard Modifications

107-1.13  Responsibility for Damage Claims.  In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries".  (5/12/89)

Special Provisions

107-1.15 Contractor's Responsibility for Work.  Add the following to the end of the first paragraph:  Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense.  (5/7/91)

Standard Modifications

107-1.16  Contractor's Responsibility For Utility Property And Services.  In the last sentence of the third paragraph delete: "by the local fire authority."  (5/12/89)

Special Provisions

107-1.16  Contractor's Responsibility for Utility Property and Service.  Add the following after the first paragraph:  When working within 10 feet of an overhead electrical line or conductor, the Contractor shall comply with the requirements of Alaska Statutes AS 18.60.670 through AS 18.60.695.

Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mislocates the facility in the field by more than 2.5-feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.

107-1.21  Permits.  Add the following subsection:  The following permits have been received on the Contractors behalf by the Department:

1.	Department of the Army, Corps of Engineers, Section 404/10, permit No. 2-900105, Knik Arm 117, dated August 24, 1990 with the following modifications:

a.	No. M-900105, dated January 9, 1991

b.	No. N-900105, dated June 28, 1991

c.	No. O-900105, dated November 21, 1991

d.	No. P-900105, dated April 9, 1992

e.	No. Q-900105, dated April 15, 1992

f.	No. R-900105, dated March 25, 1992

g.	No. S-900105, dated April 15, 1992

2.	Alaska Department of Fish and Game (ADF&G), Title 16 Permit No. FG-90-II-0117, dated July 25, 1990, with Amendment I, dated March 12, 1991

3.	Alaska Department of Fish and Game (ADF&G), Special Areas Permit No. FG-90-II-0117, Amendment IV, dated April 21, 1992, with attachment A.

4.	Municipality of Anchorage Flood Hazard Permit No. 90-0046-00, dated September 28, 1990.

5.	Matanuska Susitna Borough Flood Hazard Permit No. 90-06, dated September 27, 1990.

6.	Department of Natural Resources Temporary Water Use Permit No. TWP 90-28, dated August 9, 1990, expiring September 30, 1992.

7.	Alaska Railroad Corporation Entry Permit No. 6421, Supplement 1, dated October 17, 1991, expiring October 25, 1992.

The permits obtained by the Department are attached to those specifications as Appendix A.  The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor's responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer.  The Engineer will then decide if a permit modification is necessary.  The Engineer will have copies of the permits posted in the project office.

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  Subletting of Contract.  Add the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Driver's License.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	the owner-operator's right to control the manner in which the work is to be performed,

2. 	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3. 	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4. 	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each owner-operator.  The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.  (5/7/91)

Standard Modifications

108-1.03  Prosecution and Progress.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule". (5/12/89)

Special Provisions

108-1.03  Prosecution and Progress.  Add the following:  A representative of the structural plate pipe-arch manufacturer and any involved subcontractors shall be present at the preconstruction conference in accordance with subsection 602-3.01, Installation.

The construction of this project will be planned and recorded with a Critical Path Method (CPM) schedule.  The schedule shall be used for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

1.	Preparation of Initial Schedule.  At the preconstruction conference, the Contractor shall submit for the Engineer's approval, a detailed initial CPM schedule.  The schedule shall meet the requirements set forth below.

The construction time, for the entire project shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, the Contractor shall do so promptly.  The CPM schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements.  The CPM schedule shall be set up so that the schedule may be read by Prima Vera scheduling software being run on an IBM compatible micro computer with a 1.44 mb disk drive.  All required CPM schedule submittals shall include 1 hard copy and 1 copy of the same schedule on a 3.5-inch double sided diskette.

The CPM schedule shall be presented as a Precedence Diagram Network developed in the activity-on-node format and shall include:

a.	activity description,

b.	activity duration,

c.	resources required for each of the project activities, including:

(1)	labor, showing:

-work days per week

-holidays

-numbers of shifts per day

-number of hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-node diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60 - Day Preliminary Schedule.  Before proceeding with any work on site, the Contractor shall prepare, submit, and receive the Engineer's approval of a 60-day Preliminary Schedule.  This schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include mobilization, submittals, procurement, and construction.

No contract work may be pursued at the site without an approved 60-day Preliminary Schedule or an approved CPM schedule.

4.	Schedule Updates.  Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the CPM schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions.  The Contractor shall submit a revised CPM schedule within 7 calendar days after this meeting.  The revised schedule shall show finish dates of completed activities and updated times for the remaining work, including any addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

In addition to the CPM schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail the following:

1.	work activities,

2.	manpower involved by trade,

3.	work hours,

4.	equipment involved, and,

5.	the location of the work to be performed.

After approval of the Progress Schedule, and during the life of this project, the Contractor shall make available a spokesperson knowledgeable in the proposed construction operation.  State representatives may be attending meetings, community council meetings, throughout the Region, and it is expected that the spokesperson will accompany them to assist by briefly describing, and answering questions about the Contractor's work and time schedules.  The spokesperson must be able to speak for the Contractor and commit the Contractor to courses of action when needed to resolve problems.

Preparation and updating of the CPM schedule, two week work plans and providing a spokesperson will not be paid for directly.  Failure to perform this work will result in partial withholding of progress payments in accordance with subsection 109-1.06, Progress Payments.

(1/27/92)R11

108-1.04 Limitation of Operations.  Add the following:  Due to overlapping construction limits with the Glenn Highway, Eklutna to Parks, Phase 1-B contract, access to the following areas will not be allowed prior to October 24, 1992:

1.	Sta 1028+00 to Sta 1062+00, southbound embankment (Knik River Bridge location), and,

2.	Sta 1120+00 to Sta 1143+00, southbound embankment (Matanuska River Bridge location).

The Contractor shall complete the following items of work by the time frames indicated:

1.	Within 9 weeks from receipt of the Notice to Proceed, the Contractor shall complete the following:

a.	From the B.O.P. to Sta. "NB" 1020+00, the southbound roadway shall have all items of work completed, except final lift pavement, final pavement markings, topsoil and seeding, to provide four lanes of unrestricted traffic.

If, due to Subsection 401-3.01, Weather Limitations, the Contractor is unable to complete this work in 1992, then the remainder of the prescribed 9 week time period shall be completed at the start of the 1993 season.

b.	For the lighting system at the Old Glenn Highway intersection, temporary luminaires powered from a temporary power source are allowed.

2.	By November 1, 1993, all items of work from B.O.P. to E.O.P. shall be completed, except final lift pavement and final pavement markings, to provide four lanes of unrestricted traffic on the Glenn Highway.  In addition, the project shall be acceptable for winter maintenance in accordance with subsection 643-3.07, Maintenance of Traffic During Suspension of Work.

Acceptance of these items by the Department will be in accordance with Subsection 105-1.14, Partial Acceptance and will relieve the Contractor from further maintenance responsibilities for that portion of the work.

Failure to complete these items by the times indicated will initiate a contract reduction in accordance with subsection 643-3.06, Traffic Price Adjustment, applied for each calendar day that the work remains incomplete.

108-1.05  Character of Workmen, Methods and Equipment.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer. (9/1/89)

108-1.06  Determination and Extension of Contract Time.  Add the following:

4.	Suspensions of Work Ordered by the Engineer.  If the performance of all or any portion of the work is suspended or delayed by the Engineer in writing for an unreasonable period of time (not originally anticipated, customary, or inherent to the construction industry) and the Contractor believes that additional compensation and/or contract time is due as a result of such suspension or delay, the Contractor shall submit to the Engineer in writing, a request for adjustment within 7 calendar days of receipt of the notice to resume work.  The request shall set forth the reasons and support for such adjustment.

Upon receipt, the Engineer will evaluate the Contractor's request.  If the Engineer agrees that the cost and/or time required for the performance of the contract has increased as a result of such suspension and the suspension was caused by conditions beyond the control of and not the fault of the Contractor, its suppliers, or subcontractors at any approved tier, and not caused by weather, the Engineer will make an adjustment (excluding profit) and modify the contract in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment will be allowed unless the Contractor has submitted the request for adjustment within the time prescribed.

No contract adjustment will be allowed under this clause to the extent that performance would have been suspended or delayed by any other cause, or for which an adjustment is provided for or excluded under any other term or condition of this contract.

(4/13/89)

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  General.  Add the following:  When more than one variety of material or work item is specified for a single pay item number, letter or numeric suffixes will be included within the parenthesis to differentiate the types.  (9/1/89)

109-1.02  Measurement of Quantities.  Add the following:

TABLE 109-1

| CONVERSION TO THE SI INTERNATIONAL SYSTEM OF UNITS* |  |  |
| --- | --- | --- |
| To convert from | to | Multiply by |
| mile (US Statute) | meter (m) | 1,609.347 |
| foot | meter (m) | 0.3048 |
| foot (US survey) | meter (m) | 1200/3937 |
| inch | meter (m) | 0.0254 |
| square foot | square meter (m2) | 0.09290304 |
| square yard | square meter (m2) | 0.8361274 |
| acre (US Survey) | square meter (m2) | 4,046.873 |
| cubic foot | cubic meter (m3) | 0.02831685 |
| cubic yard | cubic meter (m3) | 0.7645549 |
| gallon (US liquid) | cubic meter (m3) | 0.003785412 |
| M. Gal. | cubic meter (m3) | 3.785412 |
| pound (lb avoirdupois) | kilogram (kg) | 0.45359237 |
| ton (short,2000 lb) | kilogram (kg) | 907.1847 |
| pound-force (lbf) | newton (N) | 4.448222 |
| footcandle | lux (lx) | 10.76391 |
| degree Fahrenheit | degree Celsius (C) | tC=(tF-32)/1.8 |

* From ASTM publication E380-89a, Standard Practice for Use of the International System of Units (SI) The Modernized Metric System

(1/31/92)

Standard Modifications

109-1.03 Scope of Payment.  Delete the last sentence of the fourth paragraph.  (5/7/91)

Special Provisions

109-1.04  Compensation for Altered Quantities.  In the third indented subparagraph, delete the following:    ", except that the total payment for the item shall not exceed 75 percent of the total amount bid for the item".  (4/13/89)

109-1.05  Compensation for Extra Work.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)

109-1.06  Progress Payments.  Add the following:  Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  This retainage may be released by the Engineer upon receipt of current schedules from the Contractor.  (1/27/92)

109-1.07  Payment For Materials on Hand.  Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska only, at a location approved by the Engineer.  (9/1/89)

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  Description.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  Interpretation.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  Essential Contract Provision.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  Definitions and Terms.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular Contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03.3 for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a Contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  Utilization Goal.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Utilization Goal in order to be eligible for award of this contract.

120-3.01  Determination of Compliance.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  Good Faith Effort.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE Credit.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that ALL of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or  demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least one of which must be working on this project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  Default of DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, ALL of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02,  Good Faith Effort.

120-4.01  Method of Measurement.  The Contractor shall be entitled to count toward the DBE Utilization Goal those monies allowed by the Engineer in Subsection 120-3.03, paragraph No. 4,  as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under Subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100 percent.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60 percent of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain  needed  supplies, personnel, materials  or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  Basis of Payment.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01 until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per Subsection 120-3.03, paragraph No. 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

Payment or Deduction will be made under:

Pay Item No.        Pay Item         Pay Unit

120(1)        DBE Adjustment   Contingent Sum

(5/12/89)

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-4.01  Basis of Payment.  Add the following:  Grubbing at the locations indicated on the plans will not be paid for directly but will be subsidiary to Item 201(1A) Clearing.

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 Description.  Add the following:  This work shall also consist of the removal of silt fence.

202-2.01  General Construction Requirements.  Add the following:  Silt fence shall be removed and disposed of off the project when adequate vegetative growth insures no further erosion of the slopes. The fabric shall be cut off at ground level and the wire and posts shall be removed.  The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands.  If a sediment height in excess of four inches above ground remains, the sediment shall be spread on the roadway side of the fence location and seeded immediately in accordance with Section 618, Seeding.

202-2.02  Removal of Bridges, Culverts and Other Drainage Structures.  Add the following:  This work shall also include removing and disposing of the following elements of the existing Knik and Matanuska River Bridges Nos. 1121 and 1124:

1.	cast-in-place concrete deck,

2.	stay-in-place forms,

3.	bridge rails,

4.	top portions of the concrete abutments and wingwalls,

5.	expansion devices, and

6.	miscellaneous hardware.

The existing bridges are two-lane, 33 feet wide, continuous welded steel plate girder bridges with cast-in-place concrete decks.  Bridge No. 1121 is 1,532 feet long with eight spans, and Bridge No. 1124 is 1,127 feet long with six spans.

Deck sections shall be removed in such a manner that damage is not done to the supporting structural steel members.  The Contractor shall repair at his own expense any damage to structural steel due to his removal operations.

On structural steel which is to be re-used, concrete shall be removed to bare metal over at least 50 percent of the contact surface, and shall be removed to within one-quarter inch of the steel surface elsewhere.  Any concrete which does not adhere tightly to the steel shall be removed.  In areas where cover plates are to be welded, concrete and other deleterious matter shall be totally removed from the steel surface.

The entire concrete deck of each bridge shall be removed prior to placing concrete for the new deck.  Where new concrete is to be cast against surfaces of existing backwalls or wingwalls, the existing surfaces shall be roughened to expose coarse aggregate.

This work also includes removing and disposing of the existing Knik River Overflow Bridges No. 1122 and 1123.  These existing bridges are two-lane, 33 feet wide continuous welded steel plate girder bridges with cast-in-place concrete decks.  They have reinforced concrete piers and abutments with reinforced concrete footings supported on cast-in-place concrete piling.

Bridge No. 1122 has a length of 521 feet and has three spans.  The deck and the concrete cap at the piers shall be removed in their entirety.  The remaining pier elements and the abutments may be left in place, provided that there is a minimum cover of 4 feet to finished roadway surface.

Bridge No. 1123 has a length of 925 feet and has five spans.  The deck shall be removed in its entirety and the piers shall be removed down to the natural stream bottom.  The abutments may be left in place, provided that there is a minimum cover of 4 feet to finished roadway surface.

Girders to be removed from the existing Knik River-Middle Channel Bridge and Knik River-Northern Channel Bridge shall become the property of the Contractor.

Waste concrete may be placed in the embankment provided that there is a minimum cover of 4 feet to finished roadway surface.  The concrete fragments shall be placed in layers not exceeding three feet in thickness.  They shall be distributed by blading or dozing in a manner such that voids, pockets, and bridging will be reduced to a minimum.  The intervening spaces shall be filled with selected material to form a dense, well compacted embankment.  The location of the disposal areas shall be clearly identified on the as-built plans.

The use of explosives to remove portions of the existing bridges is not prohibited, provided that the Contractor shall be responsible for repairing any resulting damage to those portions of the structure that are to remain in place to the satisfaction of the Engineer and at no additional cost to the Department. If the Contractor elects to use any explosives for concrete removal, he shall submit in writing two (2) weeks prior to blasting, the detailed plan to the Engineer for analysis and to determine if permits are required.  If permits are required, the Department will complete the permit applications and submit them directly to the agencies on the Contractor's behalf.  It is anticipated that a minimum of 30 days will be required by the agencies to process the applications.  The receipt and analysis by the Engineer of the Contractor's plan shall not constitute approval for implementation nor the accuracy of its implementation.

202-2.04  Removal of Pavement, Sidewalks, Curbs, Etc.  Add the following:  Pavement removed may be placed:

1.	In the embankment.  It may be placed below the Selected Material, Type A layer.  It shall be located a minimum of two feet above the water table, and no closer than 300 feet to a watercourse.  The broken asphalt pieces shall be six inches or less in maximum dimension.  The location of the disposal areas shall be clearly identified on the as-built plans.

2.	Mixed with the underlying Crushed Aggregate Base Course.  This work shall consist of crushing the existing pavement using a rotomiller or planer and blending the crushed asphalt pavement into the crushed aggregate base course layer.  The mixture shall then be shaped and compacted to the grades shown on the plans or as specified in the specifications.

The existing asphalt pavement shall be crushed to conform to the following gradation:

| Sieve Size | Percent Passing by Weight |
| --- | --- |
| 2 inch | 100 |
| 1-1/2 inch | 95-100 |

The rotomiller or planer shall have the following capabilities:

a.	self propelled,

b.	able to spray water at the cutting drum to minimize dust,

c.	adjustable as to slope and depth,

d.	able to cut up to 6 inches without producing fumes or smoke.

The crushed asphalt pavement shall be mixed with approximately 2-inches of the underlying base course.  Additional crushed aggregate base course shall be added, as directed by the Engineer, to the crushed asphalt and base course mixture and it shall be bladed until a smooth, uniform surface is obtained that is true to line, grade and cross-slope.  At bridge approaches, some material may require removal to obtain smooth transitions.

The crushed asphalt pavement/base course layer shall be of uniform gradation with no segregation or pockets of unmixed materials.

After spreading and mixing, the crushed asphalt pavement/base course shall be thoroughly watered and compacted by rolling.  The rolling shall progress by lapping uniformly each preceding rearwheel track by one-half the width of such track. Rolling shall consist of at least five (5) passes with a vibratory roller having a minimum dynamic force of 50,000 pounds impact per vibration and a minimum frequency of 1,000 vibrations per minute.

After rolling the material should be thoroughly set, the interstices of the material reduced to a minimum, and creeping of the stone ahead of the roller should no longer be visible.  Blading and rolling shall be done alternately, as required or directed, to obtain a smooth, even and uniformly compacted base.  The course shall not be rolled when the underlying course is soft or yielding or when the rolling causes undulation in the base course.

When the rolling develops irregularities that exceed 3/8 inch when tested with a 10 foot straightedge, the irregular surface shall be loosened, refilled with the same kind of material as used in constructing the base course, and rolled again as required.

In areas inaccessible to rollers, the blended crushed asphalt pavement/ base course material shall be tamped thoroughly with mechanical tampers.  The Contractor may propose an alternate method of rolling and scarifying which should be submitted to the Engineer for approval at the Pre-Construction Conference.

After grading and compaction is completed, the surface shall be tested for smoothness and accuracy of grade and crown.  Any portion lacking the required smoothness or failing in accuracy of grade or crown shall be scarified, reshaped, recompacted, and otherwise manipulated as the Engineer may direct until the required smoothness and accuracy are obtained.  The finished surface shall not vary more than 3/8-inch from a 10-foot straightedge when applied to the surface parallel with, and at right angles to, the centerline.

Work on the blended crushed asphalt pavement layer shall not be accomplished during freezing temperatures or when the subgrade is wet.  If the imported crushed aggregate base course contains frozen materials or the underlying base course is frozen, the construction shall be stopped.

Following the completion of the blended crushed asphalt pavement layer, the Contractor shall perform all maintenance work necessary to keep the surface in a condition satisfactory for applying tack coat.  After application of the tack coat, the surface shall be kept clean and free from foreign material.  The surface shall be properly drained at all times.  If cleaning is necessary, or if the tack coat becomes disturbed, any remedial effort necessary shall be performed at the expense of the Contractor.

For disposal of removed asphalt concrete not placed in the embankment or mixed with the underlying crushed aggregate base course, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529, extension 246.

202-3.01  Method of Measurement.  Add the following:  Removal of silt fence will be measured by the linear foot of actual fence removed and disposed of.

202-4.01  Basis of Payment.  Add the following:  Payment for Item 202(2), Removal of Pavement, will be made at the contract unit price per square yard and will be full compensation for all work required to remove the pavement, incorporate it into the underlying crushed aggregate base course, or dispose of it either in the embankment or outside the project limits.  Crushed aggregate base course added to the crushed asphalt mixture will be paid under Item 301(1), Crushed Aggregate Base Course.  Tack coat will be paid under Item 402(1), CSS-1 Asphalt for Tack Coat.  Removal of material at bridge approaches for smooth transitions will not be paid for directly but will be subsidiary to Item 202(2), Removal of Pavement.

Removal and disposal of waste concrete will not be paid for directly, but will be subsidiary to Item 202(1), Removal of Structures and Obstructions.

Add the following pay item:

Pay Item No.             Pay Item               Pay Unit

202(29)        Removal of Silt Fence       Linear Foot

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01  Description.  Add the following:  This work shall also include realignment of Rabbit Slough at the locations shown on the plans, and placement of vegetative material along the new channel banks as detailed in subsection 203-3.06, Construction of Rabbit Slough Realignment.

203-2.04  Muck Excavation.  Add the following:  Muck excavation shall also include the removal of permafrost.

Standard Modifications

203-2.05  Borrow.  Add the following:  Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.  (5/12/89)

Special Provisions

203-3.01  General Construction Requirements.  Add the following to the fifth paragraph:  Existing pavement shall be removed and disposed of in accordance with subsection 202-2.04, Removal of Pavement, Sidewalks, Curbs, Etc., prior to obliteration of the underlying roadway.

Add the following:  After removal of surcharge material placed under a previous contract, the Contractor shall perform compaction as necessary to develop a minimum density of 95 percent for the underlying embankment.  Maximum densities will be determined by AASHTO T 180, Method D, or Alaska T-12.  In-place field densities will be determined by Alaska T-3 or T-11.  If necessary, the Contractor shall scarify the surface to a depth of 6 inches and recompact the embankment to obtain the required density.  Any compactive effort required to achieve the required density will not be paid for directly but will be subsidiary to Pay Item 203(1), Common Excavation.

Standard Modifications

203-3.02  Embankment Construction.  On page 97, delete the 5th paragraph and substitute the following:  All embankments shall be constructed with moisture and density control unless the Engineer determines that such controls are not feasible, in accordance with approved methods.  (5/7/91)

Special Provisions

203-3.02  Embankment Construction.  Delete the first sentence of the tenth paragraph, and substitute the following:  Roadway embankments shall be placed in horizontal layers not exceeding eight inches in thickness measured before compaction.  Each layer of classified material shall have its joint offset from the joint below, longitudinally by one foot and transversely by 20-feet.

Add the following:  Where the plans call for placement of selected material and excavation is required, the existing material shall be left in place if tests determine that it will meet the appropriate selected material requirements.  Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104, Scope of Work.  (9/1/89)

The method of placement for Selected Material, Type C, placed in the slope flattening areas, and for the drainage control structure and drainage control weirs shall be at the Contractor's option.  In addition, there are no compaction requirements for these areas.

203-3.03  Construction of Embankments With Moisture and Density Control.  Add the following:  All embankment within 20 feet of a bridge abutment shall be compacted full width to not less than 100 percent of the maximum density.  All material used within this zone shall be graded to pass the 3-inch sieve.

203-3.05  Embankments in Surcharge Areas.  Add the following subsection:  The surcharge layer shall be placed as indicated on the plans with no compaction required for material placed above the finish grade.  Construction of surcharge layers will be allowed during winter.  Surcharge construction using frozen material will not be permitted.

The final embankment/surcharge height shall be based on design elevation and not construction grade stakes.  The surcharge shall be profiled after completion to verify that it is at design elevation.

After removal of surcharge material, the underlying embankment shall have a compaction density of at least 95 percent.  Maximum densities will be determined by AASHTO T 180, Method D, or Alaska T-12.  In-place field densities will be determined by Alaska T-3 or T-11.  If necessary, the Contractor shall scarify the surface to a depth of 6 inches and recompact the embankment to obtain the required density.  Any compactive effort required to achieve the required density will not be paid for directly but will be subsidiary to Pay Item 203(6A), Borrow, Type A.

203-3.06  Construction of Rabbit Slough Realignment. Add the following subsection:  After construction of the new channel, the Contractor shall spread vegetation material over the banks and seed them in accordance with Section 618.  The vegetation material shall be obtained from the clearing and grubbing operation.

203-4.01  Method of Measurement.  Add the following:  No deduction from the excavation quantities will be made for pavement removed under Item 202(2), Removal of Pavement.

No deduction from the muck excavation quantities will be made for the excavation required at the Rabbit Slough Special Ditch.

For the Rabbit Slough Realignment, items of work will be measured for payment as indicated below.

203-5.01  Basis of Payment.  Add the following:  Furnishing, installing and maintaining platform scales, tickets, scale house and electronic weigh system in accordance with Section 644 will not be paid for directly, but will be subsidiary to Item 203(6A), Borrow, Type A and Item 203(6C), Borrow, Type C.

Grading and placement of material used within 20 feet of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(6A) Borrow, Type A.  (10/1/91)

The following items of work required for the Rabbit Slough Realignment will be paid as indicated:

1.	Excavation will be paid under Item 203(4), Muck Excavation.

2.	Clearing will be paid under Item 201(1A), Clearing.

3.	Seeding will be paid under Item 618(2), Seeding.

4.	Stockpiling and spreading cleared vegetation will not be paid for directly, but will be subsidiary to Item 203(4), Muck Excavation.

Standard Modifications

203-5.01  Basis of Payment.  Change Pay items 203(5), (6) and (7) to read:  Borrow, Type _____.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01  Materials.  Add the following: Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material.  Native material shall be utilized for pipe bedding and backfill below or outside the pavement structure if the material meets the minimum requirements of Selected Material, Type C as specified in subsection 703-2.07, Selected Material.  (9/1/89)

204-3.01  Construction Requirements.  Add the following to the third paragraph:  Native material utilized for pipe bedding and backfill outside the pavement structure shall be placed in layers and compacted as approved by the Engineer.

SECTION 205

EXCAVATION, BACKFILL AND

FOUNDATION FILL FOR STRUCTURES

Special Provisions

205-1.01  Description.  Add the following:  This work shall also include excavation and backfill for the structural plate pipe-arch constructed under Section 602.

205-3.03  Backfill.  Add the following:  Structural plate pipe-arch shall be backfilled with selected material, Type A to the dimensions shown on the plans and in accordance with Section 602.

All backfill material placed within 2 feet of the pipe-arch shall be graded to pass the 3-inch sieve.

205-5.01  Basis of Payment.  Add the following:  Excavation required to install the abutment footing wingwall extensions will not be paid for separately, but will be subsidiary to Item 501(1) Class A Concrete.

Excavation and bedding required to install the structural plate pipe-arch will not be paid for separately, but will be subsidiary to work performed under Section 602.

Grading backfill material to pass the 3-inch sieve will not be paid for directly, but will be subsidiary to Item 203(6A), Borrow, Type A.

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01  Materials.  Delete the second sentence of the first paragraph and substitute the following:  The gradation of base course material shall conform to the requirements for Grading D-1.

Delete this Section in its entirety and substitute the following:

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-1.01  Description.  This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the asphalt concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thicknesses shown on the plans.

401-2.01  Composition of Asphalt Concrete Mixtures - Job Mix Design.  Asphalt concrete mixtures shall be composed of aggregate, asphalt cement, and required additives combined within the limits for the type and class specified in the contract.

The Contractor shall provide an asphalt concrete mixture that meets the asphalt concrete mix design requirements of Table 401-1.  The Engineer will evaluate the Trial Job Mix Design to determine conformance with Table 401-1, when tested in accordance with ATM T-17.

At least 15 calendar days prior to the production of asphalt concrete pavement mix, the Contractor shall submit the following to the Engineer:

1.	Notification that aggregate proposed for the asphalt concrete mixture is available for sampling.

2.	A letter stating the proposed gradation for the Trial Job Mix Design, gradations for individual stockpiles, and blend ratio for each aggregate stockpile.

3.	A minimum of three 1-gallon samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in  Section 702, manufacturer's certificate of compliance with Section 702, and a temperature viscosity curve for the asphalt cement.

4.	A 1/2 pint sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

5.	The Contractor shall accompany the Engineer during sampling, and shall furnish all the assistance needed to assure that the Engineer obtains representative samples.

The Engineer will evaluate the gradation for the Trial Job Mix Design and suitability of the materials submitted.  If the asphalt concrete mixture conforms to the asphalt concrete mix design requirements specified in Table 401-1, when tested in accordance with ATM T-17, the Engineer will approve the Trial Job Mix Design and specify a target value for the asphalt cement content, mixing temperature and additives.

If the Trial Job Mix Design does not conform to the asphalt concrete mix design requirements specified in Table 401-1, when tested by the Engineer, the Contractor shall submit in writing to the Engineer another proposed gradation for a second Trial Job Mix Design.  Samples of aggregate and additional asphalt cement shall be obtained in the same manner as for the original Trial Job Mix Design.  The Engineer shall evaluate and test the second Trial Job Mix Design and either approve or disapprove the design based on the contract requirements.  The above procedure shall be repeated until the Trial Job Mix Design is approved.  Trial Job Mix Design test results will be available within 15 calendar days of each submittal.

If the Contractor proposes a change in source of aggregate material, source of asphalt cement or a change in the gradation target values after production has started, the Contractor shall submit in writing the proposed gradation target values to the Engineer and request a new Trial Job Mix Design be evaluated for approval.  The Contractor shall accompany the Engineer during sampling and shall furnish all the assistance needed to assure that the Engineer obtains representative samples.  Approval of the new Trial Job Mix Design and/or aggregate material will require testing and evaluation.  Trial Job Mix Design test results will be available within 15 calendar days of submittal.  If the asphalt concrete mixture conforms to the asphalt concrete mix design requirements specified in Table 401-1, when tested in accordance with ATM T-17, the Engineer will develop a new target value for the asphalt cement content, mixing temperature and additives.  The new target values for gradation and asphalt cement content will only be in effect on asphalt concrete mixture produced after the Contractor submittal of the new gradation target values for the Trial Job Mix Design.

The location and type of the mixing plant shall be included with the Trial Job Mix Design data.  Asphalt concrete mixtures produced from different plants shall not be mixed.

The first trial job mix design for each source of coarse aggregate type or class will be tested at no cost to the Contractor.  If the initial job mix design meets the requirements of subsection 401-2.01, additional mix designs requested by the Contractor will be assessed a fixed fee of $1,500 each.

If the first trial job mix design does not meet the requirements of subsection 401-2.01, a second mix design will be performed at no cost to the Contractor.  All subsequent job mix designs after the second mix design will be assessed a fixed fee of $1,500 each.

Table 401-1 Asphaltic Concrete Mix Design Requirements Design Parameters Type IA and IIA Type III Stability, lbs. 1,800 min. 1,200 min. Flow, 0.01 inch (0.25 mm) 8-14 8-16 Voids in total mix, percent 3-5 3-5 Compaction, number of blows each side of test specimen 75 50 Dust-asphalt ratio (1) 0.6-1.4 0.6-1.4 Voids in mineral aggregate (VMA) IA-13.0 14.0 IIA-14.0 (1) Dust-asphalt ratio is defined as the percent of material passing the U.S. No. 200 sieve divided by the percent of asphalt (calculated by weight of mix).

Temporary pavement shall meet the requirements for Asphalt Concrete, Type IIA.

401-2.02  Aggregates.  Aggregate gradation shall be of the type specified in the contract and shall conform to the requirements of Subsection 703-2.04.

401-2.03  Asphalt Materials.  The grade of asphalt cement will be specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702.  Asphalt cement will be conditionally accepted at the source.  If the material is to be conditionally accepted at the source, the Contractor shall provide a manufacture's certificate of compliance in accordance with Subsection 106-1.05 and test results of the applicable quality requirements of Section 702 before the material is shipped.

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at 275 degrees Fahrenheit) of the asphalt cement used on the project changes from the viscosity of the asphalt supplied for the Trial Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended while a new Trial Job Mix Design proposal is submitted for approval.

401-2.04  Anti-Strip Additives.  Anti-strip agents shall be used in the proportions determined by ATM T-14 and shall be included in the approved Trial Job Mix Design.  At least 70 percent of the aggregate shall remain coated when tested in accordance with ATM T-14.

401-2.05  Process Quality Control.  It is expressly understood that the Contractor is solely responsible for the sampling and testing of material for process control of the asphalt concrete mixture including screening, crushing, blending, stockpiling of the aggregate, production of the asphalt concrete mixture and monitoring compaction of the asphalt concrete mixture.

CONSTRUCTION REQUIREMENTS

401-3.01  Weather Limitations.  The asphalt concrete mixture shall not be placed on a wet surface on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture.  No asphalt concrete mixture for a leveling course shall be placed unless the surface temperature is 40 degrees F or warmer.

401-3.02  Equipment.  All equipment shall be in good working order and free of asphalt concrete mix buildup.  All equipment shall be available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

401-3.03  Bituminous Mixing Plants.  Mixing plants shall conform to AASHTO M 156.

Proportioning (batch) scales shall not be used for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

401-3.04  Hauling Equipment.  Trucks used for hauling asphalt mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department's Approved Products List.  Diesel fuel or fuel oil shall not be used as a asphalt release agent.

Each truck shall have a watertight canvas cover of such size as to extend at least one foot over the sides and end of the truck bed and be adequately secured to protect the asphalt concrete mixture.  The use of the canvas cover shall be at the Engineer's direction.

401-3.05  Asphalt Pavers.   Asphalt pavers shall be self-propelled units provided with a heated vibratory screed. Grade and cross slope shall be controlled through the use of automatic grade and slope control devices.  The paver screed control system shall be automatically actuated by the use of an erected string line or a mobile stringline (ski) at least 30 feet in length on the high side of the paver.  Grade control shall be used on either  a) both the high and low sides or b) grade control on the high side and slope control on the low side.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation.  The hopper shall be equipped with a distribution system to place the asphalt concrete mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Auger extensions shall be within 1.5 feet of the screed extension on both sides.

The use of a pickup machine to transfer the asphalt concrete mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collection of the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any detrimental effects are observed.

401-3.06  Rollers.  The Contractor shall supply a sufficient number and weight of rollers to compact the mixture to the required density while maintaining the pace of the paving operations.  Rollers shall be of the static steel wheel, vibratory steel wheel, and pneumatic tire type, self propelled and capable of reversing without backlash.  They shall be specifically designed to compact hot asphalt concrete mixtures.  The use of equipment which results in crushing of the aggregate will not be permitted.

Pneumatic tire rollers shall be fully skirted, shall be at least 6 feet wide, and shall be configured such that the rear group of tires align to cover the spaces between the front group of tires.  The roller shall have an operating weight per tire of at least 3,000 pounds.  Tires shall be of equal size, a minimum of 20 inches in diameter, shall be inflated to at least 80 psi and  maintained so that tire pressures do not vary more than 5 psi between any two tires.

401-3.07  Preparation of Existing Surface.  Existing surfaces shall be prepared in conformance with the plans and specifications.  Existing paved surfaces shall be cleaned of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

Contact surfaces of curbing, gutters, manholes, and other structures shall be coated with a thin, uniform coating of tack coat material in conformance with Section 402 prior to the asphalt concrete mixture being placed.

Surfaces which have received a prime coat shall be allowed to cure.  Surfaces which have received an emulsion tack coat shall be allowed to break prior to placement of asphalt concrete mixture.

401-3.08  Preparation of Asphalt.  A continuous supply of the asphalt cement shall be supplied to the mixer at a uniform temperature, within 25 degrees Fahrenheit of the Job Mix Design mixing temperature.

401-3.09  Preparation of Aggregates.  The aggregate for the asphalt concrete mixture shall be heated and dried to a temperature compatible with the mix requirements specified.  Flames used for drying and heating shall be properly adjusted to avoid damage to the aggregate and to avoid the presence of unburned fuel on the aggregate.  Any asphalt concrete mixture in which soot or fuel is present shall be wasted and no payment made.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the asphalt concrete mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5 percent (by total weight of mix), as determined by ATM T-25.

401-3.10  Mixing.  The aggregate, asphalt cement and additives shall be combined in the mixer in the amounts required by the Job Mix Design.

The materials shall be mixed such that a complete and uniform coating of the aggregate is obtained.  For batch plants, dry aggregate shall be placed in motion immediately prior to the addition of asphalt cement.  Wet mixing time shall be adequate to obtain 98 percent coated particles when tested in accordance with AASHTO T 195.

The temperature of the asphalt concrete mixture at the time of the mixing shall be as determined by the Job Mix Design.

401-3.11  Temporary Storage of Asphalt Concrete Mixture.  Temporary storing or holding of hot asphalt concrete mixture in silo type storage bins will be permitted.

All the asphalt concrete mixture drawn from the silo type storage bins shall conform to all of the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Unsuitable asphalt concrete mixture shall be disposed of by the Contractor at no cost to the State.

401-3.12  Spreading and Placing.  The Contractor shall submit a Paving Plan for the Engineer's review a minimum of five working days prior to initiating the paving operation.

The plan shall consist of but not be limited to the following:

1.	Paving schedule to include sequence of operations.

2.	Operational details to include:

a.	Plant operating capacity and target production rate.

b.	Number and capacity of trucks, cycle time, and delivery rate.

c.	The manufacturer and model of the paver and pickup machine, to include information on grade followers, sensors, operating speed and production rate of the pavers.

d.	Number, type, weight, and operating speed of rollers.

e.	Location of longitudinal joints and method of constructing transverse joints.

f.	Construction plan for paving intersections and driveways.

The asphalt concrete mixture shall be laid upon a surface approved by the Engineer, spread and struck off and compacted to the required compacted thickness. Asphalt concrete shall be spread and compacted in two layers.  The first lift shall consist of 1-1/2 inches of Asphalt Concrete, Type IIA, the final lift shall consist of 2-inches of Asphalt Concrete, Type IA.  Temporary pavement shall be placed in one lift.  Asphalt pavers shall be used to distribute the asphalt concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of Section 401-3.14.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable, the asphalt concrete mixture shall be spread, raked and luted by hand tools.  For such areas the asphalt concrete mixture shall be placed to the required compacted thickness.  Asphalt Concrete, Type III used for leveling course may be spread by a grader.

Any asphalt concrete mixture which is contaminated or segregated will be rejected.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge dropoff.  When the pavement edge dropoff exceeds 2 inches, shoulder material shall be placed against the pavement edge.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that segment, as defined by the Paving Plan, has been placed and accepted.  The final lift through a segment shall not be placed until all traffic control operations that conflict with the final configuration through that segment are completed.

Asphalt to be placed over bridge membranes shall not be placed until the membrane has cured to the proper state to prevent damage by the overlaying operation.  Vehicles, except the spreader and trucks used for hauling the asphalt overlay mix, shall not be operated on the membrane.  Paving machines used over the membrane waterproofing shall be rubber tired or rubber tracked.   The Contractor shall adhere to the manufacturer's published minimum and maximum temperature limitations for asphalt overlay material.  Steel-wheeled rollers only shall be used to compact the asphalt paving on the bridge decks.  The use of vibratory rollers, with vibrator on, will not be permitted.

401-3.13  Compaction.  Immediately after the asphalt concrete mixture has been spread, struck-off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.

The target value for density will be 94 percent of the maximum specific gravity (MSG) as determined in accordance with AASHTO T 209 for the first sample from each lot of asphalt concrete  mixture as defined in Section 401-4.02.  Acceptance testing for field density will be determined in accordance with ATM T-18. (Acceptance testing for field density of leveling course will not be done.)

The asphalt concrete mixture, including leveling course, shall have a minimum of 3 complete passes with a pneumatic-tired roller prior to cooling to 175 degrees Fahrenheit.  A pass is defined as once over each point on the pavement surface.

Areas not accessible to the rollers shall be graded with rakes and lutes and compacted with mechanical tampers.  For depressed areas a trench roller may be used to achieve the required compaction.

Any asphalt concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective shall be removed and replaced with fresh hot asphalt concrete mixture, which shall be compacted to conform with the surrounding area.  Any area showing an excess or deficiency of asphalt cement shall be removed and replaced.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

401-3.14  Joints.  Joints shall be constructed to ensure a continuous bond between old and new sections of the course.  All joints shall present the same texture and smoothness as other sections of the course.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Improperly formed joints resulting in surface irregularities shall be removed full depth, replaced with new material, and thoroughly compacted.  Rolling of joints after the material has cooled below 160 degrees Fahrenheit shall not be allowed.  All pavement removal shall be precut to a neat line with a power driven saw.

A thin tack coat of asphalt cement or asphalt emulsion shall be applied on all cold joints and allowed to break prior to placing any fresh asphalt concrete mixture against the joint.  This work shall be completed by the Contractor just prior to paving.

Transverse joints shall be formed by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.

The longitudinal joints in one layer shall offset those in the layer immediately below by at least six inches.  The joints shall be at centerline or lane lines. Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset not more than 6 inches from the edge of the stripe.

401-3.15  Surface Tolerance.  The surface will be tested after final rolling at selected locations using a 10 foot straightedge.  The variation of the surface from the testing edge of the straightedge between any two contacts with the surface shall not exceed 3/16 inch.  The asphalt concrete mixture in all defective areas shall be removed and replaced.  All costs associated with removal and replacement of asphalt concrete mixture in the defective areas shall be borne by the Contractor.

401-3.16  Patching Defective Areas.  Any asphalt concrete mixture that becomes contaminated with foreign material or is in any way defective as determined by the Engineer shall be removed.  Skin patching will not be permitted.  Defective materials shall be removed for the full thickness of the course.  The pavement shall be cut so that the sides are perpendicular or parallel to the direction of traffic and so that the edges are vertical.  Edges shall be coated with a thin tack coat of material in accordance with Section 402.  Fresh asphalt concrete mixture shall be placed sufficient quantity so that the finished surface will conform to grade and smoothness requirements.  The asphalt concrete mixture shall be compacted to the density specified.  No payment shall be made for material replacing defective material.  All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01  Method of Measurement.  The asphalt concrete mixture will be measured by the ton or by the square yard in accordance with Section 109.  The tonnage used shall be the weight used in the accepted pavement and no deduction will be made for the weight of asphalt cement material and anti-stripping additive in the mixture.

The weight of asphalt cement shall be calculated using the percent of asphalt cement for each sublot as determined by ATM T-23.  These tests shall be the basis for acceptance of the lot.

No payment will be made for any asphalt cement in excess of 0.4 percent above the optimum asphalt content specified in the mix design.

Any leftover, waste and diversion will be computed in a manner to be determined by the Engineer.

401-4.02  Acceptance Sampling and Testing.  The quantity of each type of asphalt concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance.  The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project.  Acceptance sampling and testing shall be performed by the Engineer.  The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 5,000 tons.  If the contract quantity is between 2,500 tons and 8,000 tons, the contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons.   Each sublot shall be randomly sampled and tested in accordance with this Subsection for asphalt cement content, density and gradation.

If ATM T-18 is used to measure density, one core with a minimum diameter of 6 inches will be taken from each sublot.  If ASTM D 2950 is used to measure density, three random tests will be taken from each sublot.  The average of these three tests will be the value representative of the sublot.

If the project has more than one lot and if less than eight sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot shall include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

Samples taken for the determination of asphalt cement content will be taken from behind the screed prior to initial compaction.  Asphalt cement content shall be determined by ATM T-23.

Samples taken for the determination of aggregate gradation will be the same as specified for the determination of asphalt cement content.

The Contractor shall cut, within 24 hours of final rolling, full depth samples from the finished mat for density acceptance testing or for establishment of the ASTM D 2950 conversion factor.  The samples shall be neatly cut by a core drill at the randomly selected location designated by the Engineer.  All voids left by sampling shall be backfilled with new asphalt concrete material and compacted within 24 hours of sampling.  If field density is determined in accordance with ASTM D 2950 a minimum of seven, 6-inch diameter cores will be used to establish the conversion factor.

To protect the underlying membrane from damage, no samples shall be taken from the asphalt mat on the bridge decks.

Additional core samples will be required whenever a new Trial Job Mix Design is approved or whenever there is a change in the typical section.  The MSG for each lot will be determined from the first randomly selected sample from the first sublot.

All tests necessary to determine conformance with the requirements specified in Section 401-2.01 will be performed by the Engineer without cost to the Contractor.

Samples will be evaluated for acceptance in accordance with Subsection 401-4.03.

401-4.03  Evaluation of Materials for Acceptance.  The following method of price adjustment will be applied to each type of Asphalt Concrete Pavement for which the contract quantity equals or exceeds 2,500 tons.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis - Standard Deviation (Specification Conformance Analysis) Method using the procedures listed to determine the total estimated percent of the lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with ATM T-19M (attached in appendix B).  Outlier test results shall not be included in the price adjustment calculations.  If any sieve size on a gradation test is an outlier, then none of the gradation test results on that sample shall be included in the price adjustment.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s).  Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0 percent and a contractor's risk of 5.0 percent unless otherwise specified.  AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100 percent pay.  The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained.  The maximum pay factor obtainable is 1.05.  The maximum pay factor for the largest sieve size specification for gradation shall be 1.00.  The price adjustment consists of two pay factors.  The first factor is a composite pay factor for asphalt concrete mixture which includes gradation and asphalt cement content.  The second factor is a separate additional pay factor for density.

A lot containing non-specification material (less than 1.00 pay factor) may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.

A lot containing non-specification material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11.  The Contractor may submit a written request for acceptance of the material at a reduced price or approved correction.  Such a request shall include an engineering analysis showing expected effects on performance.  The Engineer will determine whether or not the material may remain in place at the reduced price.

The Engineer can reject material which appears to be defective based on visual inspection.  Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis.  Procedures for computation of composite and density pay factors are as follows:

1.	Eliminate test results found to be outliers by ATM T-19M and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ 	= summation of

x=Σxn

x 	= individual test value to xn

n 	= total number of test values

x	is rounded to the nearest tenth for density and all sieve sizes except the #200 sieve.  x is rounded to the nearest hundredth for asphalt content and the #200 sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

If the computed sample standard deviation (s) is <0.001, then use s = 0.2 for density and all sieve sizes except the #200 sieve.  Use s =  0.02 for asphalt cement content and the #200 sieve.

s=nΣ(x2)−(Σx)2n(n-1)

Where:	Σx2	 = summation of the squares of individual test values.

Σ(x)2 = square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the #200 sieve.  The sample standard deviation (s) is rounded to the nearest .001 for asphalt content and the #200 sieve.

3.	Compute the upper quality index (QU):

Where:	USL (upper specification limit) = Target Value (TV) plus allowable deviation  (Table 401-2).

QU=USL-XS

Target Value= the single specification value as defined by the Job Mix Design.

QU is rounded to the nearest hundredth.

4.	Compute the lower quality index (QL):

Where:	LSL (lower specification limit) = Target Value minus allowable deviation (Table 401-2).

QL=X-LSLS

QL is rounded to the nearest hundredth.

5.	Determine PU (percent within the upper specification limit which corresponds to a given QU) from Table 401-3.

6.	Determine PL (percent within the lower specification limit which corresponds to a given QL) from Table 401-3.

7.	Determine the Quality Level (the total percent within specification limits).

QL = (PL + PU) - 100

8.	Using the Quality Level from step 7, determine the lot Density Pay Factor (DPF) and gradation and asphalt cement content pay factors (PF) from Table 401-4.

9.	Compute the asphalt concrete mixture Composite Pay Factor (CPF) for asphalt content and gradation using the following formula:

CPF=[f3/4} }  \(  { ital PF}  rSub { size 8{ ital 34
                                        )+f1/2} }  \(  { ital PF}  rSub { size 8{ ital 12
                                        )+.......fac(PFac)]Σf

Table 401-5 is used to determine the weight factor (f) for each sieve size and asphalt content.

Table 401-2

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

Measured Characteristic        LSL            USL

3/4 inch               TV-6.0%        TV+6.0%

1/2 inch               TV-6.0%        TV+6.0%

3/8 inch               TV-6.0%        TV+6.0%

No. 4                 TV-6.0%        TV+6.0%

No. 8                 TV-6.0%        TV+6.0%

No. 16                TV-5.0%        TV+5.0%

No. 30                TV-4.0%        TV+4.0%

No. 50                TV-4.0%        TV+4.0%

No. 100               TV-3.0%        TV+3.0%

No. 200               TV-2.0%        TV+2.0%

Asphalt %              TV-0.40%       TV+0.40%

Density               TV-2.0%

Table 401 - 3

Upper Quality Index (QU) or Lower Quality Index (QL)

PU       				n = 10	n = 12	n = 15

or        				 to	 to	 to

PL	n = 7	n = 8	n =9	n = 11	n = 14	n = 18

100	2.23	2.39	2.53	2.65	2.83	3.03

99	1.89	1.95	2.00	2.04	2.09	2.14

98	1.76	1.81	1.84	1.86	1.91	1.93

97	1.67	1.70	1.72	1.74	1.77	1.79

96	1.59	1.61	1.63	1.65	1.67	1.68

95	1.52	1.54	1.55	1.56	1.58	1.59

94	1.46	1.47	1.48	1.49	1.50	1.51

93	1.40	1.41	1.42	1.43	1.44	1.44

92	1.35	1.36	1.36	1.37	1.37	1.38

91	1.30	1.30	1.31	1.31	1.32	1.32

90	1.25	1.25	1.26	1.26	1.26	1.27

89	1.20	1.21	1.21	1.21	1.21	1.22

88	1.16	1.16	1.16	1.17	1.17	1.17

87	1.12	1.12	1.12	1.12	1.12	1.12

86	1.08	1.08	1.08	1.08	1.08	1.08

85	1.04	1.04	1.04	1.04	1.04	1.04

84	1.00	1.00	1.00	1.00	1.00	1.00

83	0.97	0.96	0.96	0.96	0.96	0.96

82	0.93	0.93	0.93	0.92	0.92	0.92

81	0.90	0.89	0.89	0.89	0.89	0.88

80	0.86	0.86	0.86	0.85	0.85	0.85

79	0.83	0.82	0.82	0.82	0.82	0.81

78	0.80	0.79	0.79	0.79	0.78	0.78

77	0.76	0.76	0.76	0.75	0.75	0.75

76	0.73	0.73	0.72	0.72	0.72	0.71

75	0.70	0.70	0.69	0.69	0.69	0.68

74	0.67	0.66	0.66	0.66	0.66	0.65

73	0.64	0.63	0.63	0.63	0.62	0.62

72	0.61	0.60	0.60	0.60	0.59	0.59

71	0.58	0.57	0.57	0.57	0.57	0.56

70	0.55	0.55	0.54	0.54	0.54	0.53

69	0.52	0.52	0.51	0.51	0.51	0.50

68	0.49	0.49	0.48	0.48	0.48	0.48

67	0.46	0.46	0.46	0.45	0.45	0.45

66	0.44	0.43	0.43	0.43	0.42	0.42

65	0.41	0.40	0.40	0.40	0.40	0.39

64	0.38	0.38	0.37	0.37	0.37	0.37

63	0.35	0.35	0.35	0.34	0.34	0.34

62	0.32	0.32	0.32	0.31	0.31	0.31

61	0.30	0.29	0.29	0.29	0.29	0.29

60	0.27	0.27	0.26	0.26	0.26	0.26

59	0.24	0.24	0.24	0.24	0.23	0.23

58	0.21	0.21	0.21	0.21	0.21	0.21

57	0.19	0.19	0.18	0.18	0.18	0.18

56	0.16	0.16	0.16	0.16	0.16	0.15

55	0.13	0.13	0.13	0.13	0.13	0.13

54	0.11	0.11	0.10	0.10	0.10	0.10

53	0.08	0.08	0.08	0.08	0.08	0.08

52	0.05	0.05	0.05	0.05	0.05	0.05

51	0.03	0.03	0.03	0.03	0.03	0.03

50	0.00	0.00	0.00	0.00	0.00	0.00

NOTE:	For negative values of QU or QL, PU or PL is equal to 100 minus the table value for PU or PL. If the value of QU or QL does not correspond exactly to a figure in the table, use the next higher figure.

Table 401-4 - Pay Factors

Required Quality Level (QL) for a Given Sample Size (n)

and a Given Pay Factor

n = 12	n = 15

Pay				n = 10	n = 13	  to

Factor	n = 7	n = 8	n = 9	n = 11	n = 14	n = 18

1.05	100	100	100	100	100	100

1.04	93	93	94	94	95	95

1.03	89	90	91	91	92	93

1.02	86	87	88	88	89	90

1.01	84	85	85	86	87	88

1.00	81	82	83	84	85	86

.99	79	80	81	82	83	85

.98	77	78	79	80	81	83

.97	75	77	78	78	80	81

.96	73	75	76	77	78	80

.95	72	73	74	75	77	78

.94	70	72	73	74	75	77

.93	69	70	71	72	74	75

.92	67	69	70	71	72	74

.91	66	67	68	69	71	73

.90	64	66	67	68	70	71

.89	63	64	66	67	68	70

.88	62	63	64	65	67	69

.87	60	62	63	64	66	67

.86	59	60	62	63	64	66

.85	58	59	60	61	63	65

.84	56	58	59	60	62	64

.83	55	57	58	59	61	63

.82	54	55	57	58	60	61

.81	53	54	56	57	58	60

.80	52	53	54	55	57	59

.79	50	52	53	54	56	58

.78	49	51	52	53	55	57

.77	48	50	51	52	54	56

.76	47	48	50	51	53	55

.75	46	47	49	50	51	53

Reject	45	46	48	49	50	52

NOTE:	To obtain a given factor, the computed Quality Level shall equal or exceed the value in the table.

Table 401-5

WEIGHT FACTORS

Gradation			  Factor "f"

No. 3/4 inch sieve			 3

No. 1/2 inch sieve			 3

No. 3/8 inch sieve			 3

No. 4					 6

No. 8					 9

No. 16					 4

No. 30					 4

No. 50					 4

No. 100					 4

No. 200					20

Asphalt %					40

401-5.01  Basis of Payment.  The accepted quantity will be paid for at the contract unit price for the pay item listed below, complete in place.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $3.75 per 0.25 percent additive per ton of asphalt cement.

The Asphalt Price Adjustment shall be the sum of the price adjustments for each lot and the fees accrued for subsequent Trial Job Mix Design evaluations as outlined in Subsection 401-2.01.  The price adjustment will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value.  The price adjustment for each individual lot shall be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (tons in lot) x (PAB)

PAB = Price Adjustment Base = $30/TON

* Composite Pay Factor (CPF) or Density Pay Factor (DPF) whichever is the lower value.

Payment will be made under:

Pay Item No.           Pay Item	Pay Unit

401(1)      Asphalt Concrete, Type___	Ton

401(2)         ___ Asphalt Cement	Ton

401(4)         Anti-Strip Additive	Cont. Sum

401(5)      Asphalt Price Adjustment	Cont. Sum

401(6)         Temporary Pavement	Ton

When more than one type of Asphalt Concrete or Asphalt Cement appears on the plans and bid schedule, letter suffixes will be included within the parentheses of the pay item numbers in order to differentiate between different types.

Separate payment will not be made for asphalt cement or anti-strip additives for Item 401(6), Temporary Pavement.  Price adjustments will also not apply to Item 401(6) or for Item 401(1C), Asphalt Concrete, Type III.  Removal of temporary pavement will be paid under Item 202(2), Removal of Pavement.

SECTION 402

TACK COAT

Special Provisions

402-3.04  Dilution of Asphalt Material.  Add the following to the first paragraph:  Emulsified Asphalt as manufactured is approximately 60 percent oil and 40 percent water.  This mixture shall be diluted with an equal amount of water by weight or volume.  The determination of this ratio shall be accomplished by weighing the distributor prior to adding water, by sticking the tank, or other means acceptable to the Engineer.

402-3.05  Application of Asphalt Material.  Modify the application rate given in the first paragraph from "0.05 to 0.10 gallons" to "0.05 to 0.15 gallons".

Add the following Section:

SECTION 409

RUMBLE STRIP

Special Provisions

409-3.01  Construction Requirements.  This work shall consist of forming a series of pavement indentations along the edge of both shoulders.  These rumble strips shall be made after the breakdown rolling while the surface temperature of the mixture is a minimum of 180 degrees F and shall be accomplished in one pass of the roller.  Installation of the rumble strip prior to or following intermediate rolling shall be determined in the field and approved by the Engineer.

Rumble strips shall be placed perpendicular to centerline along both shoulders.  They shall not be placed on side streets, where the shoulder stripe is stopped, when the shoulder is less than four feet, or as directed by the Engineer.

The edges of the rumble strip indentations shall be neat, smooth and free of spalling, and shall be within the following tolerances:

Offset from outside edge 	  		+ 2-inches

shoulder stripes

Width of rumble strip				+ 2-inches

Spacing of indentations				+ 1-inch

Depth of indentations				+ 1/4-inch

Surface width of indentations			+ 1/4-inch

409-4.01  Method of Measurement.  Measurement of rumble strips shall be on a lump sum basis for rumble strips completed and accepted.  For rumble strips out of tolerance, the length out of tolerance will be divided by the total plan quantity of rumble strips and that proportion will be deducted from the lump sum amount.

409-5.01  Basis of Payment.  Payment for rumble strips shall include all equipment, material and labor necessary to complete the work.

Payment will be made under:

Pay Item No.             Pay Item                Pay Unit

409(10)             Rumble Strip              Lump Sum

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-1.01  Description.  Add the following:  This work shall also include furnishing and installing elastomeric concrete at bridge expansion joints, as shown on the plans.

501-2.01  Materials.  Add the following to the list of material specifications:

Elastomeric Concrete          Section 731

Standard Modifications

501-3.01  Proportioning.  In the second paragraph under Item 3, replace "Polysar 1186" with "Styrofan 1186".  (5/12/89)

Special Provisions

501-3.01  Proportioning.  Revise this subsection as follows:  In Table 501-1, Class of Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S, W, and A-A concrete.

Add the following to subparagraph 4:  Fly ash may be used only in the abutments and piers of the Knik Overflow Bridges, Nos. 1886 and 1887.  Fly ash shall not be used in the girders, deck, pathways, or concrete railings of any bridge on this project.

501-3.02  Batching.  Add the following to item 5. Batching:  Furnish the mix design number and a list of all ingredients, their individual weights, and moisture content of the various aggregates and the individual truck water meter reading when batched, for each truck load or batch of concrete supplied.  (5/7/91)R147

501-3.05  Forms.  Add the following:  Forms for concrete bridge decks shall be adjustable so that the specified deck thickness can be maintained in spite of irregularities in beams and girders.  Plans for formwork for concrete bridge decks shall be submitted for approval.

Tolerances for the thickness of concrete bridge decks shall be +1/4 inch and -1/8 inch.

Architectural Finish.  The thickness of concrete members that receive an architectural finish shall be increased so that the specified minimum cover to reinforcing steel is maintained.

The following concrete surfaces shall receive an architectural finish:

The vertical exterior surfaces of the concrete bridge railings that are exposed to view from the roadway beyond the limits of the bridge.

The longitudinal limits for the architectural finish shall be the outside end of the bridge rail transitions.

The architectural finish may be created by the form itself or by a liner attached to the formwork surfaces, and shall preferably be a pattern of standard manufacture.  The pattern shall produce a uniform vertical rib and groove texture.  The overall depth (relief) of the pattern shall not exceed one inch, and the center-to-center rib spacing shall not exceed three inches.   The widths of the rib surface and the base of the grooves shall be approximately equal.  Samples of the pattern shall be submitted for approval.

Inserts.  Threaded inserts may be cast in the edges of concrete decks as an aid in forming sidewalks and concrete railings.  Spacing of the inserts shall be four feet and the insert size shall be appropriate for the intended loads.  After the forms are removed, the recesses remaining at the insert shall be filled and patched with grout of the same color and texture as the deck concrete.

Permanent Metal Forms.  Permanent metal forms shall not be used for any components of the Knik or Matanuska River Bridges.

501-3.06  Placing Concrete.  Delete the last sentence of Item 2., Pumping Concrete, and substitute the following:   Concrete samples for testing will be taken at the discharge end of the pipe.  The Contractor shall provide the necessary samples of concrete at the direction of the Engineer or his representative.

Under Item 8., Installation of Expansion Joints, add the following to e., Steel Joints:  Elastomeric concrete shall be installed adjacent to the expansion joints on bridges as shown on the plans.  The manufacturer's recommendations for transport, storage, mixing, placing, finishing, and curing of the elastomeric concrete shall be rigidly followed.  A manufacturer's representative shall be on site and in control of all features of the elastomeric concrete installation.

Under Item 10., Setting Shoes and Bearing Plates, add the following:  Unless otherwise shown on the plans, pier and abutment caps on bridges shall be finished parallel to the roadway grade and parallel to the roadway cross slope or crown.  Grade strips on each side of the caps shall be independently set and the grade at the centerline of the bearings shall be carefully checked prior to casting the concrete.

501-3.07  Finishing Concrete Surfaces.  Under Item 3. Concrete Decks, modify the following:

Delete the 9th paragraph (second paragraph on page 193) and substitute the following:  After the concrete has been placed and consolidated, the surface of the concrete shall be carefully struck off by a finishing machine operating on rails.  A uniform deck surface true to the required grade and cross section shall be obtained.

Delete the 10th paragraph (third paragraph on page 193).

Delete the 11th paragraph (fourth paragraph on page 193), and substitute the following:  The finishing machine shall be self-propelled and be capable of forward and reverse movement under positive control.  Provisions shall be made for the raising and lowering of all screeds under positive control.  The upper vertical limit of screed travel shall permit the screed to clear the finished concrete surface.  It shall have the necessary adjustments to produce the required cross-section, line, and grade.  The finishing machine shall be equipped with a rotating cylindrical double drum screed not exceeding 60 inches in length preceded by a vibrating pan.  The vibrating pan shall be constructed of metal and be of sufficient length and width so as to properly consolidate the mixture.  The vibrating frequency of the vibrating pan shall be variable with positive control between 3000 and 6000 rpm.  A machine with a vibrating pan as an integral part may be proposed and will be considered for approval by the Engineer.

Floating shall be performed by metal drag pans attached to the finishing machine   These pans shall provide at least six feet of unbroken or overlapping floating, and shall be heavy enough to smooth any irregularities left by the strike-off apparatus.  The Contractor shall provide at least one hand finisher with appropriate tools to correct any imperfections left on the deck.  Hand finishing shall be performed from transverse bridges.  The bridges shall be of rigid construction and shall completely span the roadway area being finished.  A sufficient number of finishing bridges shall be provided to permit operation without undue delay.

Delete the 12th paragraph (fifth paragraph on page 193).

Delete the 13th paragraph (sixth paragraph on page 193).

Delete the second sentence of the 15th paragraph, (third paragraph on page 194) and substitute the following:  The surface shall not vary more than 0.01 feet from the lower edge of the straightedge.

501-3.08  Curing Concrete.  Add the following to Item 1. Water Curing:  The tops of concrete deck shall be completely covered with wet burlap or wet cotton mats immediately after final finishing of the surface.  The burlap or cotton mats shall be covered with an impermeable plastic film (visqueen) and kept wet by continuous application of water beneath the film covering.  The water application shall be uniform so that no area of the burlap or cotton mats becomes dry at any time during the curing period.

Add the following to Item 2. Membrane Curing:  Membrane curing shall not be used for concrete decks.

501-3.09  Backfilling and Opening to Traffic.  Add the following:  Finishing machines or any other loads shall not be placed on the screed rail supports or on any feature that supports fresh concrete after the concrete has been placed and finished and achieved initial set and prior to the concrete attaining at least 80 percent of the ultimate strength (f'c) shown on the plans.

501-4.01  Method of Measurement.  Add the following:  Elastomeric concrete will not be measured for payment.

501-5.01  Basis of Payment.  Add the following:  Architectural finish will be subsidiary to Item 507(4) Concrete Bridge Rail, Type 1.

Structural steel for the tie rod assembly will not be paid for directly but will be subsidiary to and included in Item 501(1) Class A Concrete.

Expansion joint devices will be subsidiary to items paid for under Section 504 Structural Steel.

Elastomeric concrete will not be paid for directly, but will be a subsidiary obligation included with and paid for under other items of work.

SECTION 502

PRESTRESSED CONCRETE STRUCTURES

Standard Modifications

502-1.01  Description.  Add the following to the fourth paragraph:  Alternative designs shall be based on the assumed prestressing losses outlined in Subsection 502-1.02, Prestressing Methods.  (5/12/89)

502-1.02  Prestressing Methods.  Revise the assumed stress losses in the fourth paragraph to read:

Pretensioning:

Stress relieved strand            45,000 psi

Low relaxation strand             40,000 psi

Post-tensioning, excluding friction losses:

Stress relieved strand            35,000 psi

Low relaxation strand             32,000 psi

Bar                               25,000 psi

The above losses are based on a jacking stress in the strands of no more than 0.70 GUTS (guaranteed ultimate tensile strength).

(5/12/89)

502-3.01  Construction Requirements.

6.	Pretensioning.  In the last paragraph, change "0.80 GUTS" to read "0.75 GUTS".  (5/12/89)

502-4.01  Method of Measurement;

1.	Structural Members.  In the second sentence, change reinforcing and prestressing steel," to read "reinforcing steel (uncoated and/or epoxy coated), prestressing steel,".  (5/12/89)

502-5.01  Basis of Payment.  Delete the next to the last paragraph.  (5/12/89)

Special Provisions

502-5.01  Basis of Payment.  Add the following:  No adjustment in the contract price for prestressed concrete girders will be made when epoxy coated prestressing strands are fabricated integrally with the units.

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01  Description.  Add the following:  This work also includes epoxy coating reinforcing steel as indicated on the plans.

Standard Modifications

503-3.05  Splicing.  Delete the first and second paragraphs and substitute the following:  Lap splices for reinforcing bars shall be as shown on the plans or as directed.  (5/12/89)

Special Provisions

503-5.01  Basis of Payment.  Add the following:  Reinforcing steel embedded in the bridge deck and used for anchoring bridge railings, as well as all reinforcing steel contained in the railings, will not be paid for under this section, but will be subsidiary to Item 507(4) Concrete Bridge Railing.

SECTION 504

STEEL STRUCTURES

Special Provisions

504-1.01  Description.  Add the following:  This work shall include furnishing and installing new steel plates or bars on existing steel girders, and replacement of the expansion devices as shown on the plans.

This work shall also include the following for the existing Knik and Matanuska River Bridges, Nos. 1121 and 1124:

1.	Repainting the existing steel portions of the bridges that have paint failure.  Paint failure on existing steel shall include areas that are rusted, pitted, cracked, blistered, or peeled, and,

2.	Painting a finish coat on all portions of the existing structural steel exposed to the air.

Standard Modifications

504-3.01  Fabrication.  Under item 7. Bolted Connections, High Tensile Strength Bolts,  delete paragraphs 5 through 14, and Table 504-3 and substitute the following:  All fasteners shall be tightened to give at least the required minimum tension values shown in Table 504-2 on completion of the joint.  All bolts and nuts in a connection shall be made by the same manufacturer.

In order to achieve the minimum tension values shown in Table 504-2, Required Bolt Tension, direct load indicating washers, conforming to the requirements of ASTM P959, shall be used.  The suitability of the device shall be demonstrated by testing a representative sample of not less than three devices for each diameter and grade of fastener used in the structure in a calibration device capable of indicating bolt tension.  The test assembly shall include flat, hardened washers, if required in the actual connection, arranged as those in the actual connection to be tensioned.  The calibration test shall demonstrate that the device indicates a tension not less than five percent greater than that required by Table 504-2, Required Bolt Tension.  Manufacturer's installation procedures shall be followed for installation of bolts in the calibration device and in all connections.  Special attention shall be given to proper installation of flat, hardened washers when load indicating devices are used with bolts installed in oversized or slotted holes and when the load indicating devices are used under the turned element.

Unless otherwise permitted, the load indicating device shall be placed under the bolt head, and only the nut shall be turned when tightening the bolt.  The device shall indicate full tensioning of the bolt when the opening reaches zero.

Bolts shall be installed in all holes of the connection and brought to snug tight condition.  All fasteners shall then be tightened, progressing systematically from the most rigid part (usually near the center) of the connection to the free edges, or as directed, in a manner that will minimize relaxation of previously tightened fasteners.  It may be necessary to provide multiple cycles of systematic tightening.

High-strength bolts shall not be reused.  Previously fully-tightened bolts which may have been loosened by the tightening of adjacent bolts shall be removed and replaced with new bolts, nuts, and load indicating devices.

(5/12/89)

Special Provisions

504-3.01  Fabrication.  Delete Item 8. Welding, and substitute the following:

8.	Welding.  All welding, including field welding, shall conform to the requirements of the AASHTO/AWS Bridge Welding Code, D1.5.

Welding on existing girders will cause some distortion and possibly changes in camber on existing girders.  Welding procedures which minimize distortions and which may include stress relieving shall be used to make these welds.  All these procedures shall be submitted for approval.

Add the following:  For Tension Control bolts, the Contractor shall follow the manufacturer's recommended installation procedures.

504-3.02  Erection.  Add the following under Item 8., Setting Shoes, and Bearings:  Epoxy adhesive, conforming to AASHTO M-235, Type 1, Grade 2, Class B, shall be applied to the bottom surfaces of the elastomeric bearing pads prior to placement, and the pads shall be secured and restrained from movement until the epoxy has cured and full adhesion is achieved between the pads and the concrete.

504-3.03  Painting.  Delete numbered items 1. Preparing Metal Surfaces for Painting, and 2. Schedule of Paint Coats for Metals and substitute the following:

Description.  This work shall consist of furnishing all labor, materials and equipment necessary to paint the exposed structural metal portions of the Knik and Matanuska River Bridges, including containing, collecting and disposing of waste material, in conformance with the plans and specifications.  Structural metal includes girders, stringers, floor trusses, bracing, bearings, hinges and expansion joints.  Galvanized surfaces shall not be painted.

This work shall also consist of furnishing all labor, materials and equipment necessary to remove paint on the existing steel beams in order to install new cover plates, including containing, collecting and disposing of waste material, in conformance with the plans and specifications.

The existing paint system is comprised of a red lead primer and intermediate coat and an aluminum-based top coat.

Each coat of new paint shall be tinted differently than previous coats so as to be easily distinguishable.

This paint protection shall be one of the following systems:

1.	Single Component Moisture Cure Urethane zinc rich primer, intermediate coat, and topcoat as prescribed in Option 3 of Wasser's Highway Bridges application guide.  System components as manufactured by:

Wasser High Tech Coatings, Inc.

8041 S. 228, Bldg. 103

Kent, Washington  98032

2.	"TNEMEC" Series 71 ENDURA SHIELD System, manufactured by:

Tnemec Co., Inc.

640 S. Riverside Drive

Seattle Washington  98108

3.	System 8 as described in DuPont's High Performance Coatings Manual:  Epoxy primed and urethane finished coat system.  System components as manufactured by:

E.I. DuPont Co.

Wilson Bldg., Concord Plaza

Wilmington, Delaware  19898

4.	System A3 as described in Ameron's protective coating systems for offshore platform maintenance:  High build epoxy primed and urethane finish coat system.  System components as manufactured by:

Ameron

201 North Berry Street

Brea, California  92622

Materials.  Paint furnished shall be shipped in strong, substantial containers, plainly marked with the name, weight, and volume of the contents, together with the color formula, batch number, and the name and address of the manufacturer.

The materials used in this work shall conform to the requirements specified in the appropriate section below:

SYSTEM 1

1.	Prime Coat.  The prime coat shall be MC-Zinc.

2.	Intermediate Coat.  The intermediate coat shall be MC-Ferrox B.  Color in the dry state shall closely match FED-STD-595B-23578.  The color match shall be evaluated as a general match under a daylight source in accordance with ASTM D1729.

3.	Finish Coat.  The finish coat shall be MC-Shieldcoat.  Color in the dry state shall closely match FED-STD-595B-26492.  The color match shall be evaluated as a general match under a daylight source in accordance with ASTM D1729.

SYSTEM 2

1.	Prime Coat.  The prime coat shall be TNEMEZINC No. 50-330 Poly-Ura-Prime.

2.	Intermediate Coat.  The intermediate coat shall be HI-BUILD EPOXOLINE No. 66.  Color in the dry state shall closely match FED-STD-595B-23578.  The color match shall be evaluated as a general match under a daylight source in accordance with ASTM D1729.

3.	Finish Coat.  The finish coat shall be ENDURA-SHIELD Series 71 Polyurethane Enamel.  Color in the dry state shall closely match FED-STD-595B-26492.  The color match shall be evaluated as a general match under a daylight source in accordance with ASTM D1729.

SYSTEM 3

1.	Prime Coat.  The prime coat shall be DuPont 25 P LF 63225P.

2.	Finish Coat.  The finish coat shall be IMRON, DuPont 326-Y-67637 4:1 ratio base to activator (Activator, DuPont VC-Y-511).  Color in the dry state shall closely match FED-STD-595B-26492 when evaluated under a daylight source in accordance with ASTM D1729.

SYSTEM 4

1.	Prime Coat.  The prime coat shall be Amerlock 400FD Cure.

2.	Finish Coat.  The finish coat shall be Amershield FD aliphatic polyurethane.  Color in the dry state shall closely match FED-STD-595B-26492.  The color match shall be evaluated as a general match under a daylight source in accordance with ASTM D1729.

Construction Requirements.

1.	Preparing Metal Surfaces for Painting.  Brush off blast cleaning and spot blast cleaning are required for the preparation of steel surfaces.

a.	Brush Off Blast Cleaning.  Brush off blast cleaning shall be performed in accordance with SSPC-SP7 by methods which will remove the aluminum-based top coat and all dirt, loose paint, and all other deleterious materials from the entire surface of the paint but which will not significantly damage remaining sound tight paint.  Adjustment of abrasive size or type, air pressure at the blast nozzle, or similar variations may be required.  Solvent Cleaning, SSPC-SP1 and Power Tool Cleaning, SSPC-SP3 methods shall be employed as necessary to augment blast cleaning.  Any rusted or corroded areas that show up after brush off blast cleaning shall be spot blast cleaned as described below.  The surface of the finally cleaned remaining paint shall be blown down with clean air, supplemented by brushing if required, shall be free of all residue of cleaning prior to painting, and shall be approved by the Engineer prior to painting.

b.	Spot Blast Cleaning.  All rusted or corroded areas on bridges to be spot cleaned shall be spot blast cleaned in accordance with SSPC-SP6, Commercial Blast Cleaning, and the appearance of the blast cleaned area shall approximate Pictoral Standard Sa 2 of ASTM D 2200.  The edges of existing paint surrounding the spot cleaned area shall be feathered and no loose or abrupt edges of paint shall remain.

Commercial blast cleaning and spot blast cleaning shall be performed using an abrasive of a size which will produce a minimum profile of 1 mil on the surface of the finally cleaned steel.  The maximum height of the profile shall be controlled by the Contractor by his cleaning methods, so as to produce a surface profile not considered to be detrimental to the performance of the coating.

To prevent contamination of wet paint, blast cleaning shall not be performed when coatings are being applied or where drying of coated surfaces is in progress.

Abrasive used for brush off blast cleaning and spot blast cleaning shall not be reused.

2.	Containment and Disposal.  All reasonable attempts to collect the wastes generated from existing paint repair operations shall be made during brush off blast cleaning and spot blasting cleaning activities.  Tarpaulins, drapes or other appropriate methods shall be used to recover and contain abrasives, rust, old aluminum top coat, and any debris generated during preparation and painting operations of the structure.  Recovered waste material shall be collected at a minimum at the end of each day, or as directed by the Engineer.

A Containment and Disposal Plan shall be submitted at the Pre-Construction Conference for approval by the Engineer.  No brush off blast cleaning and/or spot blast cleaning shall occur prior to approval of the Plan.

Collected debris shall not be reused and shall be disposed of at a Department of Environmental Conservation approved landfill.  Transfer to the landfill shall be in vehicles, free from leakage, and covered by tarps to prevent escapement of debris into the environment.  Temporary stockpiling of the debris material shall be on reinforced viscuine and kept covered at all times.

Liners, tarps, and drapes used to contain the wastes shall be maintained in good condition.  If punctures in the tarps or liners occur, the operator shall make every effort to repair the holes and capture the wastes.  Brush off blast cleaning and spot blast cleaning shall be stopped during periods of high wind and/or precipitation when containment is impractical, or as directed by the Engineer.

3.	Schedule of Paint Coats for Metals.

SYSTEM 1

For System 1, Structural Steel shall be painted with a minimum of 3 coats:

a.	Prime coat (dry film thickness 3.0 mils min.)

b.	Intermediate coat (dry film thickness 3.0 mils min.)

c.	Finish coat (dry film thickness 2.0 mils min.)

All coats shall be applied according to the manufacturer's written instructions.

SYSTEM 2

For System 2, Structural Steel shall be painted with a minimum of 3 coats:

a.	Prime coat (dry film thickness 2.0 to 3.0 mils)

b.	Intermediate coat (dry film thickness 4.0 mils to 6.0 mils)

c.	Finish coat (dry film thickness 1.5 to 2.5 mils)

All coats shall be applied according to the manufacturer's written instructions.

SYSTEM 3

For System 3, Structural Steel shall be painted with a minimum of 2 coats:

a.	Prime coat (dry film thickness 8.0 mils min.)

b.	Finish coat (dry film thickness 2.0 mils min.)

All coats shall be applied according to the manufacturer's written instructions.

SYSTEM 4

For System 4, Structural Steel shall be painted with a minimum of 2 coats:

a.	Prime coat (dry film thickness 5.0 mils min.)

b.	Finish coat (dry film thickness 5.0 mils min.)

All coats shall be applied according to the manufacturer's written instructions.

Make the following changes under item 3. Painting Metal Surfaces:

Delete the subparagraphs under heading a. Time of Application, and substitute the following:

a.	Time of Application.  The prime coat shall be applied as soon as possible after the surface has been cleaned and before deterioration of the surface occurs.  Any oil, grease, soil, dust or foreign matter deposited on the surface after the surface preparation is completed shall be removed prior to painting.  In the event that rusting occurs after completion of the surface preparation, the surface shall be cleaned again.

Care shall be taken to prevent the contamination of cleaned surfaces with salts, acids, alkali, or other corrosive chemicals before the prime coat is applied and between applications of the remaining coats.  Such contamination shall be removed from the surface.  Under these circumstances the prime coat shall be applied immediately after the surface has been cleaned.

Delete the subparagraphs under heading b. Storage of Paint Thinner.

Delete the subparagraphs under heading c. Mixing and Thinning.

Delete the subparagraphs under heading j. Handling of Painted Steel, and substitute the following:

j.	Handling of Painted Steel.  Painted steel shall not be handled until the coating has dried except for necessary handling and turning for painting or stacking for drying.

k.	Repair of Defects.  Paint which is damaged shall be removed and touched up with the same number of coats and kinds of paint as were previously applied to the steel or in  conformance with the coating manufacturer's written recommendations and procedures.  Galvanized steel damaged by field welding or  any other reason shall be hand cleaned and  repaired in accordance with AASHTO M36-24.  Repair of galvanizing shall be made at no additional cost to the State.

l.	Component Origin.  All components of any system shall come from one manufacturer.

m.	System Durability and Certification.  The coating system manufacturer shall review the project and the coatings proposed environment and shall issue recommendations and instructions to the applicator to insure maximum durability and proper application of the coating on this project.

The applicator shall certify to the Department that the system was applied in accordance with the manufacturer's recommendation and instructions and shall enclose a copy of the recommendation and instructions with the certificate.

504-4.01  Method of Measurement.  Add the following:  Item 504(6), Bridge Painting, will not be measured for payment.

504-5.01  Basis of Payment.  Add the following: Replacement of expansion joints will not be paid for separately, but will be included in the lump sum price for structural steel, furnished, fabricated and erected.

Furnishing and installing new steel plates or bars on existing steel girders will not be paid for separately, but will be included in the lump sum price for structural steel, furnished, fabricated and erected.

Painting of new structural steel will not be paid for separately, but will be included in the lump sum price for structural steel, furnished, fabricated and erected.

Payment for Item 504(6), Bridge Painting, will be full compensation for furnishing all labor, equipment and materials required to:

1.	Clean and paint the existing steel portions of the bridge that have paint failure, and,

2.	Clean the painted surface and paint a new finish coat on all portions of structural steel exposed to the air.

Removal of existing paint, waste containment and disposal required for bridge painting will not be paid for separately, but will be subsidiary to Item 504(6).

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

504(6)	Bridge Painting	Lump Sum

SECTION 505

PILING

Special Provisions

505-2.01  Materials.  Add the following:  All welding shall be performed in accordance with Subsection 505-3.15, Welding.

505-3.03  Pile Bearing Values.  Delete this subsection in its entirety and substitute the following:  All piles shall be driven to the required bearing capacity.  The required bearing capacity is the design load shown on the general layout sheet in the plans multiplied by a factor of safety of 2.75.

505-3.09  Driving Piles.  In the first paragraph, fifth sentence, change "1/2 inch" to "1-inch".

Delete the tenth paragraph, (second paragraph on page 250), and substitute the following:  All pile driving equipment used by the Contractor shall be subject to approval by the Engineer.  A vibratory driver may be used to initially set the piles.  The pile driving system shall be equipped with a suitable thickness of hammer cushion material to prevent damage to the hammer or pile and to insure uniform driving performance.  Hammer cushions shall be made of durable, manufactured materials, provided in accordance with the hammer manufacturer's guidelines except that wood, wire rope, and asbestos hammer cushions shall not be used.  The hammer cushion shall be inspected in the presence of the Engineer when beginning pile driving at each structure or after each 100 hours of pile driving, whichever is less.  Any reduction of hammer cushion thickness exceeding 25 percent of the original thickness shall be replaced by the Contractor before driving is permitted to continue.

The compressive stresses as indicated by the wave equation during pile driving shall not exceed 90 percent of the pile yield stress.

Thirty calendar days prior to driving the first pile, the Contractor shall submit pile driving equipment information on the "Pile Driving Equipment Data Form" provided by the Engineer.  Approval of the pile driving equipment will be based on the wave equation analysis.  In addition, as part of this approval, the Contractor will be provided a "Pile Bearing Chart".  This chart will show blow counts and hammer strokes at required bearing capacity when a pile is at or near the desirable tip elevation.  A minimum of fourteen calendar days prior to driving the first service pile, the Contractor shall attend a conference with the Engineer to evaluate and discuss the pile driving for Bridges No. 1887 and 1888.

During service pile driving, the Contractor shall use the approved driving system.  No variations in the driving system will be permitted without the Engineer's written approval.  Any change in the driving system will only be considered after the Contractor has submitted a revised "Pile Driving Equipment Data Form" for a revised wave equation analysis by the Engineer, and the analysis indicates an acceptable result.  The Contractor will be notified of the acceptance or rejection of the revised driving system within seven calendar days of the Engineer's receipt of the requested change.  The time required for submission, review, and approval of a revised driving system shall not constitute the basis for a contract time extension to the Contractor.

Add the following to the eleventh paragraph (third paragraph on page 250):  There is a possibility of encountering boulders at the pier sites and riprap at the abutment sites when driving piles for the Knik Overflow bridges.

Add the following to the fourteenth paragraph (first paragraph on page 251):  Piles may be driven before placement of new embankment, when approved by the Engineer.  The Contractor shall submit a driving plan for approval that will identify a method of isolating the piling from possible embankment settlement load transfer.  The driving plan shall also include the procedure for compacting the fill around the driven piles.

Add the following:  All piling which do not reach required bearing capacity at desirable tip elevation at the time of driving will be subject to confirmation by restrike.  At least one pile at each pile bent shall be evaluated by restrike.  The piles shall set for a minimum of fourteen days after completion of driving to the specified tip elevation, prior to restrike.

The restrike procedure shall be as follows:

1.	Air or steam hammers.  The pile to be restruck shall be driven at least 6 inches at the normal operating pressure.  For a single-acting hammer, there shall be a full upward stroke of the ram.  For a double-acting hammer, the number of blows per minute during the driving shall be that for which the hammer is rated, unless otherwise directed by the Engineer.

2.	Diesel hammers.  The pile to be restruck shall be  driven at least 6 inches, unless otherwise directed by the Engineer.

505-3.14  Painting Steel Piles and Steel Pile Shells.  Add the following:  The outside surface of the piling, above ground, shall be painted in accordance with Subsection 504-3.03 Painting.

505-3.15  Welding.  Add the following subsection:

All welding and inspection shall conform to the requirements of the latest edition of the American Welding Society (AWS) Structural Welding Code, D1.1.

1.	Qualification of Process, Procedures and Joint Details.  For each joint to be used in construction, the joint details, electrode classification or grade, electrode diameter, voltage, amperage, order and relative position of passes, number and thickness of layers and other pertinent information shall be clearly presented in the welding procedure(s) submitting by the Contractor for the approval of the Engineer.

Requirement for procedures qualification is waived if the Contractor's welding procedure is in accordance with all requirements of the welding procedures specification contained within the AWS Structural Welding Code, D1.1.

2.	Welders, Certification and Testing.  All welders and welding operators shall be certified in conformance with the AWS Structural Welding Code, D1.1.  Welders or welding operators lacking current AWS Structural Welding Code, D1.1, certification will not be permitted to perform welding on this project.

3.	Inspection of Shop Work and Records.  Welds including joint preparation, fit-up and alignment will be completely (100 percent of the weld) inspected visually and radiographed in conformance with AWS Structural Welding Code, D1.1.  Ten percent of the length, as determined by the Engineer, of each weld will be radiographic tested.  If a rejectable defect is found, then 100 percent of the lengths of the butt joints in that piece will be radiographically tested.

The Engineer will examine and approve satisfactory welds, disapprove or reject unsatisfactory welds, approve satisfactory methods proposed by the Contractor for repairing disapproved welds, and inspect the preparation and rewelding of disapproved welds.  Copies of all the welding fabrication documentation, including the weld testing results, will be forwarded to the Engineer.

4.	Obligation of Contractor.  It shall be the Contractor's responsibility to comply with all requests of the Engineer to correct improper workmanship and to remove and replace, or correct as instructed, all welds found defective or deficient by visual inspection or by nondestructive testing.

5.	Visual Inspection.  All welds shall be completely visually inspected.  A weld shall be acceptable by visual inspection if it shows that:

a.	the weld has no cracks,

b.	thorough fusion exists between adjacent layers of weld metal and between weld metal and base metal,

c.	all craters are filled to the full cross section, and,

d.	the completed weld conforms to all of the provisions of the AWS Structural Welding Code, D1.1.

6.	Nondestructive Testing.  The method of nondestructive testing will be radiographic testing in conformance with AWS Structural Welding Code, D1.1.  Field welds are not subject to nondestructive testing.

7.	Destructive Testing.  The location, method and extent of mandatory destructive testing to be performed (if any) will be indicated on the contract drawings.  All other welds will normally be inspected by visual methods and nondestructive testing;  however, the Engineer may require destructive testing of any weld that in his opinion does not meet the criteria for radiographic acceptance.

The cost associated with destructive testing of questionable welds will be borne by the Department for welds meeting radiographic acceptance criteria and by the Contractor for welds not meeting radiographic acceptance criteria.  The cost of destructive testing of welds designated for destructive testing on the contract drawings will be borne by the Contractor.

The Contractor is responsible for removing any weld specimen for destructive testing and repairing the weld afterwards.

8.	Preparation of the Weld.  The edges of the parts to be joined by welding shall be prepared by accurately cutting, grinding or machining to shape as indicated on the contract drawings and will be visually inspected prior to welding by the Engineer.

9.	Backing.  Backing rings or strips shall be utilized on all field butt welded joints welded from one side unless otherwise shown on the contract drawings or approved by the Engineer.  Open root joints are permissible where the joint is inaccessible from both sides.

10.	Cleaning.  Each completed bead shall be thoroughly cleaned of all slag, or other foreign matter, before proceeding with the next bead.  Hand clipping, power driven wire brushed, needle scalers, or grinders shall be used.

Full compensation for welding, weld inspection, weld testing, including all necessary tools, equipment, scaffolding and other support facilities required to perform welding, welding inspection, including the cost of radiographic testing will be subsidiary to the price bid for the piling items of the contract and no separate payment will be made.

(2/19/92)R146

505-4.01  Method of Measurement.  Delete the following from the sixth line of the second paragraph under Item 2, Piles, Driven.:  "...reinforcing steel, concrete fill...".

Delete numbered paragraph 6. and substitute the following:

6.	Piles not achieving the specified capacity within 5 feet of the desirable tip elevation shown on the plans shall be driven to a penetration established by the Enigneer.  Requirement to drive piles deeper than the specified tip elevation shown on the plans shall be at the written direction of the Engineer.  For depths up to 20 feet beyond the desirable tip elevation, the contract bid price for piling will be applied.  For depths beyond 20 feet, the pile unit costs will be determined per Section 109.

505-5.01  Basis of Payment.  Add the following:  The reinforcing steel to be used in the piling shall be measured and paid as Item 503(1) Reinforcing Steel.  Concrete fill used in the piling shall be measured and paid as Item 501(1) Class A Concrete.

SECTION 507

BRIDGE RAILING

Special Provisions

507-2.01  Materials.  Delete in its entirety and substitute the following:

1.	Steel.  Metal pipe handrailing on the bridge rail shall conform to the requirements of Section 722, Bridge Railing.

2.	Concrete.  Concrete for cast-in-place concrete railings shall be Class A concrete and shall conform to the applicable requirements of Section 501.  The surface finish of the railings shall conform to the requirements of a rubbed finish, or an architectural finish, as shown on the plans or specified under subsection 501-3.05, Forms.

3.	Reinforcing Steel.  Reinforcing steel shall conform to the requirements of Section 503 and shall be epoxy coated.

507-3.01  Construction Requirements.  Add the following:

1.	Concrete.  Casting of the concrete rail shall conform to the requirements of Section 501, Structural Concrete.

2.	Reinforcing Steel.  Reinforcing steel shall conform to the requirements of Section 503, Reinforcing Steel.

Standard Modifications

507-4.01  Method of Measurement.  Add the following:  It shall also include concrete and associated reinforcing steel included or partially contained within the limits of the concrete rail section.  (5/12/89)

Special Provisions

507-4.01  Method of Measurement.  Delete in its entirety and substitute the following:  The number of linear feet paid for Concrete Bridge Railing will be determined from the plan dimensions.

507-5.01  Basis of Payment.  Add the following:  Payment for Concrete Bridge Railing will be full compensation for furnishing all labor, materials, and equipment required to construct the bridge rail.  This will include the bridge rail concrete, reinforcing steel, structural tubing, utility conduits, and will include reinforcing steel embedded in the slab and extending into the railings.

Payment for concrete bridge rail transitions and all types of concrete bridge railing will be made under Item 507(4), Concrete Bridge Railing.

SECTION 508

MEMBRANE WATERPROOFING

Special Provisions

Delete this Section in its entirety and substitute the following:

508-1.01  Description.  This work consists of furnishing and installing membrane waterproofing on concrete bridge decks and backwalls in conformance with the plans for Bridges No. 1887, 1888, 1121, and 1124.  It shall also include furnishing and installing membrane waterproofing for Bridges No. 1885 and 1889 constructed under the Phase 1-B contract.

For bridge decks with precast concrete components utilizing epoxy coated reinforcing steel, this work shall consist of furnishing and applying an 18 inch minimum width strip of membrane waterproofing centered over the joints between adjacent concrete members.

For cast-in-place concrete decks, this work shall consist of furnishing and applying a complete deck covering of membrane waterproofing.

508-2.01  Membrane Waterproofing Material.  Membranes for bridge deck waterproofing shall be a manufactured type membrane as specified herein.

Membrane shall consist of a single or multiple component elastomeric material and shall be a product listed on the Department's Approved Products List, or an approved equal.

508-2.02  Overlay Materials.  Materials requirements for pavement overlays on waterproof membranes shall conform to those specified in Section 401.

508-3.01  Application of Membrane Waterproofing.

1.	General.  Membrane waterproofing shall be installed in a manner to assure the following results:

a.	A complete bond between the membrane and the concrete surface of deck and curb face.

b.	An unbroken waterproof membrane in place between the concrete deck surface and the asphalt overlay.

c.	A complete bond between the membrane and the asphalt overlay.

2.	Preparation of Concrete Deck.  All concrete surfaces to receive membranes shall have cured at least 18 days prior to application of the membrane, except grout in keyways between precast members shall have cured at least 11 days prior to application of the membrane.

The entire deck shall be free of all foreign materials such as dirt, dust, moisture, loose concrete, etc.  Prior to applying the tack coat, primer or emulsion, all dust and loose material shall be removed from the deck by power sweeping followed by a thorough cleaning with compressed air.  Any sharp concrete edges on the deck surface which would puncture the membrane shall be corrected in a satisfactory manner prior to application of the membrane.  Grease, oil, paint, etc., shall be removed with solvents, detergents or sand blasting on decks that are to receive manufactured membranes.

Additional power sweeping, vacuuming, compressed air cleaning, or hand brooming shall be performed immediately before applying the tack coat, primer or emulsion if deemed necessary by the Engineer or manufacturer's representative.

3.	Weather and Moisture Limitations.  In order to minimize outgassing, liquid-type manufactured membranes shall be applied only when deck surface temperatures are falling, or likely to fall, during the curing period of the membrane.

Work shall not be done during wet weather conditions, nor when the deck and ambient air temperatures are below 40 degrees F.

4.	Overlaying and Protection of Membrane.  The asphalt overlay shall be performed in accordance with the requirements of Subsection 401-3.11, Spreading and Finishing.

508-4.01  Method of Measurement.  Membrane waterproofing will not be measured for payment, however, for bidding purposes, the estimated quantity is the following:

| Location | Type of Covering | Estimated Quantity |
| --- | --- | --- |
| Bridge No. 1887 | Strip Membrane | 205 SY |
| Bridge No. 1888 | Strip Membrane | 205 SY |
| Bridge No. 1885 | Full Deck Covering | 6426 SY |
| Bridge No. 1889 | Full Deck Covering | 4720 SY |
| Bridge No. 1121 | Full Deck Covering | 6426 SY |
| Bridge No. 1124 | Full Deck Covering | 4720 SY |
|  | TOTAL AMOUNT | 22,702 SY |

508-5.01  Basis of Payment.  Waterproof membrane will be paid at the contract lump sum price.  Payment for the asphalt overlay will be made under the appropriate paving items.

Payment will be made under:

Pay Item No.            Pay Item              Pay Unit

508(1)        Membrane Waterproofing       Lump Sum

SECTION 602

STRUCTURAL PLATE PIPE

Special Provisions

602-1.01  Description.  Add the following:  This work shall also include all labor, equipment and materials to construct concrete thrust beams or steel ribs, provide waterproofing, and prepare bedding material as shown on the plans.

602-1.02  Testing.  Add the following subsection:  The manufacturer of the structural plate pipe-arches shall provide comprehensive live-load test data for one or more of its structures of equal or greater top radius at HS 20-44 plus 20 percent loading.  If the manufacturer has no previous live-load test data under the conditions described above, the Contractor, at his expense, shall perform such live load testing and monitoring of the structures within 30 days after paving over them.  Deflection under test conditions shall not exceed 0.75 inch and no discernable change in pavement grade or condition will be allowed.

602-2.01  Materials.  Delete this subsection in its entirety and substitute the following:  Materials shall conform to the following specifications:

Structural Plate & Hardware	AASHTO M167

Waterproofing Seam Sealant	ArmCo 101, Kopper Bitumastic Super Service Black, Chevron Wet Plastic Cement, ATCO 1714 Plastic Fibre Seal or approved equal.

Structural Steel			ASTM A36

Class A Concrete			Section 501

Reinforcing Steel			ASTM A615

Bedding Material			AASHTO M43

Gradation #57 or #67

Selected Material, Type A	Subsection 703-2.07

Corrugated metal pipe and welds shall be hot-dipped galvanized in accordance with AASHTO M111.

Alternate Structures.  The Contractor may submit for approval alternate structural plate pipe-arch structures to those indicated.  Any such substitute, including modification to other portions of the structure necessary to accommodate the substituted pipe, shall be made at the expense of the Contractor and no adjustment in unit prices or pay quantities made.  All materials shall be designed in accordance with the latest version of AASHTO Standard Specification for Highway Bridges, Section 12.

602-3.01  Installation.  In the second sentence of the first paragraph, change "Section 204" to read "Section 205".

Add the following to the second paragraph:  The bottom plates shall be laid true to line and grade on an uncompacted bedding layer as shown on the plans.  Original material in the bedding area shall be sub-excavated and replaced with approximately 8 inches of uncompacted porous backfill material which shall be graded to match the shape of the bottom plates following completion of all concrete placement.

Add the following:  The Contractor shall submit a Construction Sequencing Plan and Traffic Control Plans for the installation of the structural plate pipe-arches at least 30 days prior to installation.

A qualified representative of the structural plate pipe-arch manufacturer and any involved subcontractors shall be present at the preconstruction conference to discuss methods and responsibility for shape monitoring and control, backfill material testing and placement, and compaction methods and testing.  The structural plate pipe-arch manufacturer's recommendations and instructions shall be carefully followed during assembly.  Distortions shall be minimized and bolts shall be tightened symmetrically so that sweep and camber are kept to a minimum.  Seam sealant shall be installed in the seam laps in conformance with the manufacturer's instructions in order to achieve a relatively water-tight structure.

Except as otherwise provided, concrete work shall conform to Section 501, reinforcing steel work shall conform to Section 503, structural steel work shall conform to Section 504, welding shall conform to AWS D-1.1, and excavation, bedding and backfill shall be performed in accordance with the requirements of Section 205 and as required below.

602-3.02  Backfilling.  Add the following:  Backfilling shall progress evenly on each side of the pipe-arch in 8 inch maximum lifts compacted to 95 percent in accordance with subsection 203-3.03 Construction of Embankments With Moisture and Density Control, except that no compaction equipment shall operate within 2 feet of the side plates.  The Contractor shall monitor the structures during all backfilling and compacting operations to insure that no excessive distortions are occurring.  If, in the opinion of the Engineer, excessive distortions are likely to occur, the Contractor shall make adjustments to the backfilling operations as recommended by the pipe-arch manufacturer, and approved by the Engineer, so that distortions are minimized.

When the backfill reaches the elevation of the bottom of the concrete thrust beams, backfilling shall be halted and the thrust beams formed and cast.  In order to prevent distortions from the liquid concrete, placement of concrete shall be balanced on either side of the structure and the concrete shall be cast in layers of 10 inch maximum depth.  Forms may be removed and backfilling resumed after 72 hours following concrete placement.

When backfill outside the thrust beam reaches an elevation 2 feet above the top of the thrust beam, the top of the structures shall be covered with material deposited in 8 inch maximum lifts and compacted to 95 percent density with hand equipment or very light tractor equipment.  Until the overlay reaches a depth of at least 2 feet above the crown of the structures, large equipment shall not at any time be located closer to the structures than the outside edge of the thrust beam.  Until the fill above the structures is 2 feet thick, material shall be added and spread and compaction equipment operated perpendicular to the structure centerline.

No frozen materials shall be used in the backfill.

602-5.01  Basis of Payment.  Add the following:  Headwalls, structural steel, hardware, concrete thrust beams, excavation, bedding material and services required to construct the pipe-arch will not be paid for directly, but will be subsidiary to Item 602(2), Structural Plate Pipe-Arch, Span 25'-2", Rise 26'-1", Gauge 5.

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-1.01 Description.  Add the following:  This work includes fabrication and installation of corrugated steel pipe stoplog structures as shown on the plans.

This work shall also include constructing concrete headwalls and riprap aprons for the Rabbit Slough 84-inch Corrugated Steel Pipe.

This work shall also consist of installing culvert marker posts.

This work shall also consist of constructing a special ditch for temporarily rerouting Rabbit Slough.

603-2.01  Materials.  Add the following to the list of materials specifications:

Structural Timber Stoplogs        713-2.01

Steel Plates and Shapes           716-2.02

Corrugated Polyethylene Pipe      706-2.07

Riprap, Class I                   611-2.01

Concrete, Class W                 501-2.01

Geotextile, Separation            729-2.01

In the second paragraph, add "Corrugated Polyethylene Pipe (24 inch maximum diameter)" to the list of options allowed under Item 603(17).

Add the following to the last paragraph:  Heights of cover for corrugated polyethylene pipe shall be the same as for aluminum culvert pipe.

Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05, Delineator Posts for Item 2., Flexible Posts.  The color shall be blue with no other markings.  The 3-3/4 inch by 72-inch post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9-inches.

603-3.04 Joining Pipe.  Delete the last sentence of numbered paragraph 1., and substitute the following:  Bands for pipe with diameters greater than 30 inches shall have a minimum width of 48 inches.  (10/1/91)

Add the following:  Polyethylene pipe couplings shall be corrugated to match the pipe corrugations and their width shall not be less than one half the nominal pipe diameter.

(5/7/91)

603-3.06  Culvert Marker Posts.  Add the following subsection:  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30-inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or at the locations as directed by the Engineer.  There shall be 42-inches of post remaining above ground after driving.

603-3.07  CSP Stoplog Structures.  Add the following subsection:  Corrugated steel pipe stoplog structures shall be fabricated in accordance with the details and dimensions shown on the plans.  Plates and outlet pipes shall be welded to the riser assembly to form watertight connections.

Where indicated on the plans to furnish materials only, the Contractor shall fabricate, deliver and stack those structures at the Alaska Railroad storage yard located at 1221 Whitney Road in Anchorage.

603-3.08  Special Ditch for Rabbit Slough.  Add the following subsection:  A special ditch for temporarily rerouting Rabbit Slough shall be constructed in accordance with the sequencing contained in Attachment A, located in Appendix A, Permits.

603-4.01  Method of Measurement.  Add the following:  Culvert marker posts will not be measured for payment.

Item 603(23) CSP Stoplog Structure will be measured by the number of units furnished, fabricated and installed.

Riprap, Class I and Concrete, Class W required at the Rabbit Slough 84-inch Corrugated Steel Pipe will not be measured for payment.  Separation geotextile will be measured and paid for under Item 630(1), Geotextile, Separation.

No measurement of quantities will be made for the Rabbit Slough Special Ditch.

603-5.01  Basis of Payment.  Add the following:  The contract bid unit price per each CSP stoplog structure will be full compensation for all labor, equipment and materials required to complete the work as specified and detailed on the plans.  Excavation, bedding, steel shapes, steel plates, structural timber, backfill and other items necessary for the fabrication and installation of the structure will not be paid for directly but will be subsidiary to Item 603(23) CSP Stoplog Structure.

Riprap, Class I and Concrete Class W will not be paid for directly.  They will be subsidiary to Item 603(1-84), 84-inch Corrugated Steel Pipe.

Culvert marker posts will not be paid for directly, but will be subsidiary to the pipe item.

All items of work required for the Rabbit Slough Special Ditch will not be paid for directly, but will be subsidiary to Item 603(1-84), 84-inch Corrugated Steel Pipe.  This shall include removal of a 20-foot length of the existing culvert, excavating the ditch, furnishing, placing and removing a plastic liner in the ditch, furnishing and installing a 100-foot length of 36-inch CMP and crushing the ends, and diverting the creek as needed.

Add the following pay item:

Pay Item No.             Pay Item              Pay Unit

603(23)          CSP Stoplog Structure         Each

SECTION 606

GUARDRAIL

Special Provisions

606-1.01  Description.  Add the following:  This work shall also consist of installing breakaway cable terminals, guardrail/bridgerail connections, and controlled release terminals at the locations shown on the plans.

606-2.01  Materials.  Add the following:  Flexible markers shall have yellow reflective sheeting and be one of the following types:

1.	"Guardrail Delineator Post" manufactured by Carsonite International, 2900 Lockheed Way, Carson City, Nevada 89701.

2.	"Guardrail Delineator" manufactured by Safe-Hit Corporation, 1930 West Winton Avenue, Building 11, Hayward, California 94545.

3.	"Flex-o-Guide",  Model  EY426  manufactured by Flexible Safety Zoning Company, 4152 Warren Avenue, Hillside, Illinois 60162.

606-3.01  Posts.  Add the following:  The foundation type for the Breakaway Cable Terminal Posts shall be the "steel post embedment-soil or concrete" option as shown on Standard Drawing G-18.

606-3.02  Rail Elements.  Add the following to the first paragraph:  Guardrail elements shall be factory bent for all radii less than 75-feet.

606-3.06  Flexible Markers.  Add the following subsection:  For each breakaway cable terminal, a flexible marker shall be installed at the terminal end, attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.  The flexible markers shall have a minimum of 21-inches of marker extending above the top of the guardrail.  The reflective tape shall face the nearest oncoming traffic.

606-3.08  Length of Need Verification.  Add the following subsection:  After shaping the slopes and staking all proposed guardrail locations, the Contractor shall notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine that additional guardrail is necessary, and the Contractor shall comply without delay.  (3/17/86)

606-3.09  Embankment Widening.  Add the following subsection:  Embankment widening for guardrail end treatments shall be constructed of selected material, Type A in accordance with Section 203.

606-3.12  Guardrail/Bridgerail Connection.  Add the following subsection:  Existing guardrail/bridgerail connection shall be removed and salvaged and new guardrail/bridgerail connection installed in accordance with the details on the plans and Standard Drawing G-29.

606-4.01  Method of Measurement.  Delete the third paragraph and replace with the following:  Breakaway Cable Terminals will be measured per each installation which will include anchor cable assembly, terminal posts, terminal end, flexible marker and all associated hardware.  Rail elements, standard posts, and blocking for Breakaway Cable Terminals will be measured as Beam Type Guardrail.

Add the following:  Controlled Release Terminal/Special End Anchors will be measured per each installation which consists of all materials from the terminal end to and including the breakaway cable terminal anchor cable assembly, terminal posts and associated hardware.

Guardrail/Bridgerail Connections will be measured per each installed in place.  Each guardrail/bridgerail connection will include a 12.5 foot section of thrie beam guardrail, thrie beam to standard w-beam transition, thrie beam transition bracket, posts and all associated hardware.

Standard Modifications

606-4.01  Method of Measurement.  Delete the last sentence of the first paragraph and substitute the following:  Double faced (and nested) installations will be measured by dividing the number of panels by two, before multiplying by the panel length.  Thrie beam transition pieces shall be measured by multiplying the number of panels by 6.25 feet and shall be paid for at the contract price for Thrie Beam Guardrail.  (5/12/89)

Special Provisions

606-5.01  Basis of Payment.  Selected material, Type A will be measured and paid in accordance with Section 203.

Add the following pay items:

Pay Item No.              Pay Item              Pay Unit

606(8)           Breakaway Cable Terminal       Each

606(9)         Controlled Release Terminal/	Each

Special End Anchor

606(12)            Guardrail/Bridgerail         Each

Connection

SECTION 611

RIPRAP

Special Provisions

611-2.01  Materials.  Add the following:  Geotextile to be installed under the Riprap, Class III shall meet the requirements of Section 631 for unprotected riprap liner.

611-5.01  Basis of Payment.  Add the following:  Furnishing and installing geotextile riprap liner in accordance with Section 631 will not be paid for directly, but will be subsidiary to Item 611(2) Riprap, Class III.

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01  Materials.  Add the following to the end of the first sentence of the fifth paragraph, "and the Alaska Traffic Manual."

Delete paragraphs 7 and 8 and substitute the following:  Sign posts and bases shall be of the types specified.  Structural aspects of design and materials for sign supports shall comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals.

Concrete for steel-reinforced slip base and breakaway base foundations shall be Class A, conforming to the requirements of Section 501, Structural Concrete.  Concrete for other sign foundations may be class W.

(5/7/91)

615-3.01  Construction Requirements.  Add the following to the sixth paragraph:  When existing signs are to be salvaged the remaining foundation shall be removed or obliterated to 6 inches below the level of the surrounding grade.

Add the following after the sixth paragraph:  Salvaged sign panels shall be delivered to the State Maintenance Yard at Palmer.

615-3.02  Sign Placement and Installation:  Add the following:  Existing signs shall not be removed until the new signs providing the same information to motorists have been installed.  If necessary, they may be temporarily relocated to a location approved by the Engineer.  They shall be maintained until they are no longer needed.

Prior to mounting the sign panel, the Contractor shall mark the date of installation on the back of the sign.  Installation dates shall be written in the format of month/day/year, using black grease pencil, with numbers a minimum of 3 inches in height, so as to be readable from the roadside after installation.  (2/14/92)R143

615-5.01   Basis of Payment.  Add the following: Obliteration of foundations shall be included in Item 615(7), Salvage Signs.

Maintaining existing signs until they are no longer needed and temporary relocation of existing signs will not be paid directly, but will be subsidiary to Item 615(1), Standard Signs.

SECTION 617

RAILROAD CROSSINGS

Special Provisions

617-2.01  Materials.  Delete Item 4. and substitute the following:

4.	Railroad crossing pads shall be OMNI Rubber Grade Crossings as manufactured by Riedel OMNI Rubber Products, Inc., Portland, Oregon;  COBRA-X Crossing as manufactured by Railroad Friction Products Corp., Wilmending, PA.;  or ARRC approved equal.

Add the following:

5.	Railroad Ballast Geotextile.  Railroad Ballast Geotextile shall conform to the requirements of Subsection 729-2.01, Embankment Separation and Reinforcement.

6.	Railroad Ballast.  Railroad Ballast shall conform to the requirements of Section 740, Railroad Trackwork Materials.

7.	Timber Ties.  Timber ties shall conform to the latest AREA requirements and shall be pressure treated with creosote to a net retention of 10 pcf minimum per AWPA C-2.  Dimensions, adzing, incising, and boring shall conform to ARRC standard Plan 1.12.

617-3.01 Construction Requirements.  Add the following to Item 1., General:

e.	Work on this project involving the Alaska Railroad will include the reconstruction of an existing railroad crossing on the northbound lanes and the construction of a new railroad crossing on the southbound lanes.  In conjunction with this crossing construction, the grade of the railroad between and including these crossings will be raised approximately 0.6 feet.  This grade raise must be accomplished in three (3) steps: Half of the total grade raise at the southbound crossing, then the full grade raise at the northbound crossing, then back to the southbound crossing to complete the grade raise.  Approximately 100 feet of track between the crossings will be included in this grade raise.   The Contractor will be required to install and remove temporary wood plank crossings twice during this construction.  Due to critical train scheduling, track closures are limited to six (6) hours.  Closures are at the discretion of the ARRC and all work affecting the railroad must fall within the time restraints set by the ARRC.  The railroad crossing must have an operating signal at all times.  If the Contractor chooses to establish or operate a temporary crossing for his use, he shall obtain all permits and bear all costs associated with the crossing.  All work shall be coordinated through the Resident Engineer with the ARRC Manager, Telecommunications and Signaling.  The following coordination sequence of construction is required for installation of the railroad crossings:

(1)	The Contractor shall construct the track panel for both crossings as shown on the project plans.  The centerline of the crossings will be marked on the rail panel.  The tie spacing will be in accordance with the crossing pad manufacturer's recommendations.  This work must be approved by the ARRC inspector prior to the scheduling of the crossing rebuild or new crossing construction.  The rail anchors must be compatible with the crossing pads.

(2)	The ARRC will make the necessary rail cuts in the existing track to facilitate the removal of the existing track panels through the crossing areas.

(3)	The ARRC will raise the existing track outside of the crossing prior to the rebuild.

(4)	The Contractor will supply the ballast for the grade raise within the crossing limits and stockpile it at the site.  The Contractor will furnish a front end loader and operator required for the placement of the ballast.

(5)	The ARRC will disconnect the section of track to be removed by the Contractor.

(6)	The Contractor shall remove the existing crossing materials and track materials.  All salvaged track materials will become the property of the Contractor.

(7)	The Contractor shall excavate to the dimensions shown on the project plans.

(8)	The Contractor shall install geotextile and place ballast below design bottom of tie.

(9)	The ARRC will raise the track on the southbound lanes one-half of the total track grade raise.

(10)	The Contractor shall place the prebuilt track panel in place.

(11)	The ARRC will connect the new track panel to the existing track.

(12)	The Contractor will furnish and install the first temporary wood crossing surface on the southbound lanes.  Traffic detoured to southbound lanes.

(13)	The ARRC will raise rails on northbound lanes to finished grade.

(14)	The Contract will raise approaches to the northbound crossing.

(15)	The Contractor will install modular crossing on northbound lanes.  Traffic is detoured to northbound lanes.

(16)	The Contractor will remove the first temporary wood crossing surface from the southbound lanes upon approval of the ARRC foreman.

(17)	The Contractor will reconstruct the roadway approaches to the southbound crossing.

(18)	The ARRC will complete the second and final track grade raise at the southbound crossing.

(19)	The Contractor shall install the modular crossing in conformity with the manufacturer's recommendations.

(20)	The Contractor shall complete the match of the roadway approach surfaces to top of pavement prior to opening the roadway to highway traffic.

(21)	The ARRC will construct final track raise and tamping after three (3) days of rail traffic.

Under Item 1.c. after "appurtenances...", add the following:  "outside the crossing work limits shown on the plans...".

Delete Item 4. Railroad Crossing and substitute the following:

4.	Railroad Crossing.  Construction of railroad crossings shall take place within the limits of each crossing and shall consist of the following items of work:

a.	Perform all clearing required for sight triangles.

b.	Provide all surveying within the crossing limits which includes, but is not limited to, setting top of rail elevations, layout of electrical system, staking clearing limits and setting grade for earthwork and roadway surfacing.

c.	Furnish and install all ballast, ties, rails, rail-associated hardware, and modular crossing materials (FOB jobsite) required for crossing construction, as shown on the plan and detail sheets, rebuild and track raise.  Replace rail within limits of crossing construction and furnish ballast required for raising this area.

d.	Furnish and install new geotextile as shown on the plans and in accordance with Section 630, Geotextiles for Embankment Separation and Reinforcement.

e.	Furnish and install temporary work crossing surfaces, as required.

f.	Completion of roadway approach surfacing, to include paving.

g.	Furnish a front-end loader and operator required for the crossing construction and rebuild.  Place ballast material required for railroad reconstruction as directed by the Engineer.

h.	Perform excavation required and furnish and install engineering fabric required for the crossing areas as shown on the project plans.

i.	Perform all roadwork adjacent to the crossing including protection of modular crossing surface during paving.

j.	Furnish and install power to temporary signal controller.  Coordinate through the Engineer and the ARRC for location of temporary controller.  Notify ARRC one week prior to beginning this work.  ARRC will provide temporary signals for detour traffic.

k.	Provide and install the load center and all conduit (except conduit from controller base to J-Box No. 1) and junction boxes for the railroad warning system.  All electrical work for the signal system shall be coordinated with the ARRC Manager, Telecommunications and Signaling to assure power is available for the operation of the crossing signals and gates per ARRC schedule.  After the Contractor has completed this work approximately one week per crossing will be required for the ARRC to install the signals.

l.	Install two signal and four gate bases to be furnished by the ARRC.

m.	Construct embankment widenings for signal/gate bases and construct an approach for access to the controller and the load center.

n.	Remove existing crossing surface, i.e., planks, asphalt, or modular pads and be responsible for all slope and ditch grading and shaping of old crossing and roads following construction of a new crossing.

o.	Be responsible for all traffic control and construction signing except for railroad flag protection and railroad signals which are the responsibility of the ARRC.

p.	Remove any existing foundations, conduit or designated signing remaining within ten (10) days after the ARRC has completed their work.

q.	Furnish a water level control structure, as shown on the project plans, and deliver the structure to the ARRC's Anchorage Yard.

r.	Furnish and install 6-inch culvert pipe for future power for signals and lighting.

Coordination of the crossing reconstruction shall be arranged through the Chief Engineer of the Alaska Railroad by the Engineer.

Add the following:

5.	Cantilever Signal Foundation.  Work under this item consists of furnishing and installing cast-in-place concrete cantilever signal foundations as detailed on and at the locations shown on the plans.  Work performed under this item shall be conducted in accordance with Section 204, Structure Excavation for Conduits and Minor Structures and Section 501, Structural Concrete.  Concrete used shall be Class A.

6.	Railroad Furnished Gate Base.  Work under this item consists of installing railroad furnished metal gate bases at the locations shown on the plans.

Work performed under this item shall be conducted in accordance with Section 204, Structure Excavation for Conduits and Minor Structures.

7.	Rigid Metal Conduit With Pull Wire.  Work under this item consists of furnishing and installing rigid metal conduit with pull wire of the sizes and at the locations shown on the plans.  Removal of any existing conduit necessary to make connection to new junction boxes, gates, signals or load centers will be included in this item of work.

Work performed under this item shall be in accordance with Section 204, Structural Excavation for Conduits and Minor Structures and Section 660, Signals and Lighting.

8.	Type II Junction Box.  Work under this item consists of furnishing and installing Type II junction boxes at the locations shown and in accordance with the plans and removal of existing junction boxes.Work performed under this item shall be in accordance with Sections 204, Structural Excavation for Conduits and Minor Structures and Section 660, Signals and Lighting.

9.	Railroad Signal Load Center.  Work under this item consists of furnishing and installing railroad signal load centers at the locations shown and in accordance with the plans.  Work performed under this item shall be in accordance with Section 204, Structural Excavation for Conduits and Minor Structures and Section 660, Signals and Lighting.

617-4.01  Method of Measurement.  Add the following:  No separate measurement will be made for removal of existing junction boxes or removal of and connection to existing Rigid Metal Conduit, jacking, boring, trenching, backfilling or pavement patching.

617-5.01  Basis of Payment.  Add the following:  No separate payment will be made for removal of existing junction boxes.  Payment for removal of existing junction boxes will be subsidiary to Item No. 617(7), Type II Junction Box.  No separate payment will be made for removal of and connection to existing Rigid Metal Conduit, jacking, boring, trenching, backfilling or pavement patching.  Payment for these items of work will be subsidiary to Item No. 617(5), Rigid Metal Conduit with Pull Wire.

Add the following pay item:

Pay Item No.             Pay Item              Pay Unit

617(9)      Railroad Furnished Gate Base      Each

SECTION 618

SEEDING

Special Provisions

618-1.01   Description.  Delete this subsection and add the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be seeded.  This work shall consist of tracking the soil, followed by the application of seed, mulch, and fertilizer.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01  Materials.  Add the following to the list of material specifications:

Mulch                         Subsection 727-2.01

618-3.01  Soil Preparation.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as possible on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is on wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not traverse the wetlands.  The performance of this work is incidental to seeding and will not be paid for directly.

618-3.03  Application Method. In the first sentence of subparagraph 6. under numbered 1., Hydraulic Method, delete the following:  "Item 619(1),".

Add the following:  Seed, mulch and fertilizer shall be applied as shown in the following table per 1,000 square feet.  If the hydraulic method for seed and mulch is used, it shall be made in one application.  The mulch rate shown is a minimum, and may be increased in accordance with the manufacturers recommendations.  All fertilizer shall be applied by the hydraulic method.

Application

Item              Ingredients             Rate Lbs/MSF

Seed Mix	    Bering Hairgrass (Norcoast)     0.40 lb.

Red Fescue (Arctared)           0.30 lb.

Annual Ryegrass (Lolium)        0.10 lb.

Alsike or Dutch White Clover    0.10 lb.

Meadow Foxtail                  0.10 lb.

TOTAL =  1.00 lb/MSF

Mulch                                         35.0 lbs.

Fertilizer	20-20-10                       15.0 lbs.

The Contractor shall not remove the required tags from the seed bags.

618-3.04  Maintenance of Seeded Areas.  Add the following:  For all seeded areas except the drainage control structure, a reapplication of fertilizer shall be applied with water between May 1 and September 15 of the year following seeding at a rate of one-half the initial application.

618-4.01  Method of Measurement.  Delete the second paragraph and substitute the following:  Seeding by the pound will be the number of pounds of seed (Dry Measure) accepted in place.  The amount of mulch and fertilizer used in this work, including any required reseeding, will be subsidiary to seeding and will not be measured separately for payment.

When hydraulic seeding methods are used, mixing water for the hydraulic slurry will not be measured for payment, but will be subsidiary to seeding.

Delete the last paragraph.

618-5.01  Basis of Payment.  Add the following:  Fertilizer and mulch as described above, will not be paid directly, but will be subsidiary to Item 618(2), Seeding.

SECTION 620

TOPSOIL

Special Provisions

620-2.01  Materials.  Add the following:   Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

SECTION 630

GEOTEXTILE FOR EMBANKMENT SEPARATION

AND REINFORCEMENT

Special Provisions

Delete this Section in its entirety and substitute the following:

630-1.01  Description.  Prepare surfaces and furnish and place geotextiles for embankment separation and railroad ballast as shown on the plans or as directed.

630-2.01  Materials.  Geotextile material and thread used in joining geotextiles by sewing shall conform to Subsection 729-2.01, Embankment Separation and Reinforcement.

630-3.01  Construction.

1.	Surface Preparation.  Prepare surface by hand clearing all vegetation, removing stumps, boulders and other sharp objects, and dewatering any areas as necessary.  Fill holes and large ruts with material as shown on the plans or as approved.  Material used to fill ruts and holes will be paid for at the unit price for the class of material used.  Hand clearing of all vegetation, removal of stumps, boulders, sharp objects and dewatering, if necessary, will be considered subsidiary to this item.

2.	Fabric Laying.  Unroll fabric (geotextile) directly onto the prepared surface.  Stretch fabric to remove any creases or wrinkles.  Keep fabric taut during placement and spreading of cover material.

Lay fabric parallel to the direction of the material spread.  When laid on horizontal curves, it shall be placed in segment lengths not exceeding those listed in Table 630-1, with butt ends cut to match and sewn or overlapped.  When laid on tangents, the fabric shall be straightened and butt ends sewn or overlapped.

TABLE 630-1

GEOTEXTILE PLACEMENT ON CURVES

| Degree of Curve | Maximum Segment Length (feet) |
| --- | --- |
| 1 | 125 |
| 2 | 90 |
| 2 | 75 |
| 4 | 65 |
| 5 | 55 |
| 6 | 50 |

4.	Fabric Joining.  Join fabric by sewing or overlapping.  Bonding or other attachment methods may be used, subject to the approval of the Engineer.  If sewn, all seams shall be sewn by butterfly or J-seams and develop a minimum of 85 percent of the specified geotextile strength.  Seams shall be sewn with a double-thread chain-lock stitch.  The seam shall be 1-1/2 inches (+1/4 inch) from the outside edge of the fabric.  If seams are to be overlapped, adjacent sections of fabric shall be overlapped a minimum of three feet unless otherwise shown on the plans.

5.	Material Placing and Spreading.  During placing and spreading, a minimum depth of 1 foot shall be maintained at all times between the fabric and the wheels or tracks of the construction equipment.  Spread the material in the direction of the fabric overlap.  Maintain a proper overlap and fabric continuity.  If sewn or bonded seams are used, place the cover material and spread in only one direction for the entire length of the geotextile.  On weak subgrades, spread the cover material simultaneously with dumping to minimize the potential of a localized subgrade failure.

Construction equipment shall not make sudden stops, starts, or turns on the cover material.  Use a smooth drum roller to achieve the specified density.

6.	Geotextile Repair.  If fabric should be torn for any reason, the cover material shall be cleaned from the torn area and it shall be repaired by overlaying with fabric having a minimum three foot overlap around the edges of the torn area.  The patch shall remain in place when material is placed over the affected area.

7.	Shipping and Handling.  Protect fabric from direct sunlight, ultraviolet rays, temperatures greater than 140 degrees F, moisture, and contamination from mud, dirt, dust, and debris.  Label or tag each roll to provide product identification.  Geotextiles will be rejected if at the time cover material is placed they have been removed from protective wrapping for more than five days, or if they have detrimental defects or damage which  cannot be repaired in the field.

630-4.01  Method of Measurement.  Geotextile will be measured in final position by the square yard, determined by multiplying plan neat line width by the measured length parallel to installation centerline along the ground surface, for installations acceptably completed.  No allowance will be made for overlap, whether at joints or patches.  No payment will be made for geotextile placed beyond the limits shown on the plans unless placed at the prior, written direction of the Engineer.

630-5.01  Basis of Payment.  Payment will be made at the contract unit price per square yard.  This price shall be full compensation for furnishing all materials, surface preparation, delivering and laying the fabric and for all labor, equipment, tools and incidentals necessary to complete this item.

Payment will be made under:

Pay Item No.             Pay Item              Pay Unit

630(1)         Geotextile, Separation     Square Yard

(2/27/92)

SECTION 631

GEOTEXTILE FOR

SUBSURFACE DRAINAGE AND RIPRAP LINER

Special Provisions

631-2.01  Materials.  Add the following:  Geotextile for riprap liner shall conform to the requirements for an unprotected condition.

Standard Modifications

631-3.01 Construction.  Under Item No. 2., Fabric Laying, delete the fifth sentence.

Under Item No. 3., Material Placing and Spreading, delete the third sentence.

(5/7/91)

Add the following Section:

SECTION 638

IMPERMEABLE MEMBRANE

Special Provisions

638-1.01  Description.  This work shall consist of furnishing and placing an impermeable membrane, Class I Riprap, and timber barriers as necessary in the construction of the drainage control structure and drainage control weirs as shown on the plans.

638-2.01  Materials.  Impermeable membrane shall meet the requirements of Section 729, Geotextiles.

Class I Riprap shall meet the requirements of Section 611, Riprap.

The timber barriers shall consist of treated timbers having a stress grade of 1200 psi or more in accordance with the American Institute of Timber Construction.  They shall be treated in accordance with Section 714, Preservatives and Preservative Treatment Processes for Wood Materials.

638-3.01  Construction Requirements.

1.	Storage and Handling.  All storage and handling of the impermeable membrane shall be accomplished in accordance with the manufacturer's recommendations.

2.	Surface Preparation.  Before placing the impermeable membrane, the surface on which the material is to be placed shall be smooth and free of all boulders and other sharp objects.

3.	Trenching.  The impermeable membrane shall be installed in a trench at the toe of the drainage control structure and weirs as shown on the plans.  Backfilling the trench shall be performed using excavated materials.

638-4.01  Method of Measurement.  Impermeable membrane will be measured in final position by the square yard.  No allowance will be made for additional material at joints or repair areas.

638-5.01  Basis of Payment.  Payment for impermeable membrane will be made at the contract unit price per square yard.  This price will be full compensation for furnishing all materials, surface preparation, delivery and laying the membrane and for all labor, equipment, tools and incidentals necessary to complete this item.

No separate payment will be made for excavating and backfilling the trench for the impermeable membrane, furnishing and placing Class I Riprap, or furnishing and placing the treated timbers required for construction of the drainage control weirs.  These items will be subsidiary to Item 638(2), Impermeable Membrane.

Payment will be made under:

Pay Item No.              Pay Item              Pay Unit

638(2)           Impermeable Membrane      Square Yard

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01  Description.  Add the following:  This item shall also consist of the work involved in the excavation, forming, shaping and construction of public approaches.

639-2.01  Method of Measurement.  Add the following:  Public approaches will be measured per each constructed as shown on the plans, or as directed.

639-3.01  Basis of Payment.  Add the following:  Payment for public approaches will be full compensation for furnishing all equipment and labor necessary to complete the work as indicated.  Excavation is subsidiary  to Item 639(3), Public Approaches.  Materials required to construct the public approaches will be paid for separately under the respective items listed in the bid schedule.

Add the following pay item:

Pay Item No.              Pay Item              Pay Unit

639(3)            Public Approaches            Each

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-1.01  Description.  Add the following:  This shall also consist of all work necessary to provide construction access in the Knik River.

640-1.02  Construction Access in Knik River.  Add the following subsection:  Temporary construction access involving placement of structures, placement of fill, or dredging of the north channel of the Knik River will require modifications to the existing Department of the Army Corps of Engineers Permit and the existing Alaska Department of Fish and Game Title 16 permit.

The Contractor shall submit a work plan to the Engineer a minimum of two weeks prior to permit application.  All drawings shall be completed in accordance with the Corps of Engineers application requirements.  The Department will complete the permit applications and submit them directly to the agencies on the Contractor's behalf.  It is anticipated that a minimum of 30 days will be required by the agencies to process the applications.

The work plan shall include but not be limited to the following:

1.	The Contractor's proposed method of access to the bridge site, and a time schedule for completing the work.

2.	A drawing showing the location and typical section with elevations of the temporary trestle and abutments, if used.

3.	The size and draft of the barge, if used.

4.	A drawing showing the location and typical section for any temporary fill, with the quantity of material to be placed below mean high water indicated.

5.	The Contractor's proposed method and schedule to remove the temporary fill, or temporary trestle and abutments, including erosion control methods.

640-2.01  Method of Measurement.  Delete this subsection in its entirety and substitute the following:

1.	When 5 percent of the original contract amount is earned from other bid items, 90 percent of the amount bid for mobilization and demobilization will be paid.

2.	When the letter of project completion has been issued and the Contractor has made all the required submittals the remaining balance of the amount for this item will be paid.

640-3.01  Basis of Payment.  Add the following:  Design, construction, maintenance and removal of a temporary construction access will not be paid for directly, but will be subsidiary to Item 640(1), Mobilization and Demobilization.

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01  Description.  Delete the last sentence of the first paragraph.

Add the following: This work shall include preparation of a Temporary Erosion and Pollution Control Plan.  The Contractor shall conduct construction activities in accordance with the approved Temporary Erosion and Pollution Control Plan.

This work shall also include installation of silt fence and repair of silt fence.  Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of Subsection 107-1.11, Protection and Restoration of Property and Landscape.  Additional silt fencing may be required at any site as directed by the Engineer.  Repair of silt fence will be as directed by the Engineer.

641-1.02  Preconstruction Conference.  Delete this subsection in its entirety and substitute the following:

641-1.02  Temporary Erosion and Pollution Control Plan.  At the preconstruction conference, the Contractor shall submit for acceptance a Temporary Erosion and Pollution Control Plan consisting of the following:

1.	Methods for clearing and grubbing.

2.	Plan for installation of temporary erosion and sediment control measures, in accordance with Best Management Practices included as part of this contract as Appendix C, including, but not limited to the following activities:

a.	Excavation and embankment construction.

b.	Construction of temporary and permanent drainage features.

c.	Construction in and around waterbodies and wetlands.

d.	Haul roads and material sites.

3.	Disposal of waste material.

4.	Containment, cleanup, and disposal of such substances as well as the methods to be utilized for disposing of petroleum products or other hazardous substances generated by construction equipment or activities.  The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.

641-1.03 Materials.  Add the following subsection:  The silt fence filtration material shall meet the requirements shown in Table 729-4 in Section 729, Geotextiles.

The silt fence support framework shall be finished 4 x 4-inch wood, 3-inch diameter wood, #6 rebar with PVC sleeves, iron pipe or other posts capable of supporting the installation, as approved by the Engineer.

The mesh support shall be WWF 6x6 W1xW1 or as approved by the Engineer.

641-2.01 Construction Requirements.  Add the following:  The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water.  Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of subsection 107-1.11, Protection and Restoration of Property and Landscape.  Additional silt fencing may be required at other sites as directed by the Engineer.

The silt fence shall not be removed until slopes are stabilized from further erosion as determined by the Engineer.  If silt fence is designated for removal on the plans, it shall be removed and disposed of off the project upon completion of construction at those sites.  The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands or waterbodies.

Removal of silt fence shall be accomplished in accordance with Subsection 202-2.01, General Construction Requirements.

641-3.01  Method of Measurement.  Add the following:  Silt fence and repair of silt fence will be measured by the linear foot along the top of the fence.

641-4.01  Basis of Payment.  Add the following:  Payment for Item 641(2) Silt Fence, will be full compensation for all labor, equipment and materials required to furnish, install, and maintain the silt fence in accordance with these specifications.  Payment for Item 641(3) Repair of Silt Fence, will be full compensation for all labor, equipment and materials required to repair silt fence as directed by the Engineer.  Removal of silt fence will be paid under Item 202(29) Removal of Silt Fence.

Add the following pay items:

Pay Item No.              Pay Item              Pay Unit

641(2)                 Silt Fence           Linear Foot

641(3)            Repair of Silt Fence      Linear Foot

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  Description.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Specifications in Appendix D.

Add the following:  The Contractor shall provide bridge surveys of the existing Knik River Bridge, No. 1121, and Matanuska River Bridge, No. 1124.

642-3.01  Construction Requirements.  Add the following to the third paragraph:  During backfill of the structural plate pipe-arches, the Contractor shall continuously monitor and record horizontal and vertical displacements.  These shall be measured to the nearest 1/8-inch at locations and frequencies which will adequately indicate the structure's performance.

Add the following:

12.	The Contractor's survey crews shall comply with approved traffic control plans.  Crews shall coordinate their activities with the project's Worksite Traffic Supervisor.

The Contractor shall provide right-of-way and/or controlled-access staking for Matanuska Electric Association (MEA) and ENSTAR Natural Gas Company so that they can relocate their facilities.  The Utility, through the Engineer, shall notify the Contractor three weeks in advance to perform this survey.  The Utilities will require the staking at the following locations:

1.	ENSTAR.  New Glenn Highway/Old Glenn Highway Intersection, Sta. 1001+00 to Sta. 1004+50 Rt. (to south side of the Old Glenn Highway).

2.	MEA.  From the Knik River north to Sta. 1078+00 on the west side of the highway and from Sta. 1077+00 to Sta. 1078+00 on the east side of the highway.  Also, from Sta. 1299+25 to Sta. 1304+00. Lt.

The Contractor shall perform bridge surveys of Bridge Nos. 1121 and 1124.  The surveys shall be performed by, or under the direct supervision of, a Professional Engineer registered in the field of civil engineering in the State of Alaska.  The Contractor and  the Professional Engineer shall meet with the Engineer at least one week prior to the planned beginning of the surveys.

The surveys shall catalog the existing dimensions for all bridge elements, as well as any other information which might influence the Contractor's operations.  The surveys shall also determine any modifications which have been made on the bridge which make the information shown on the as-built drawings incomplete or erroneous and shall document such modifications.

The findings of the surveys shall be submitted in report form.  The reports shall contain the results of the dimension check (red-lined on as-builts supplied by the Engineer), the modifications surveys, and any noteworthy items incidentally noticed regarding the condition of the bridges, including but not limited to:

1.	Evidence of fatigue or cracking in any members,

2.	Extensive corrosion of any members,

3.	Loose or missing fittings, splices, members, etc.

The reports shall not contain recommendations or opinions.  It shall contain factual information from field verification of as-built drawings only.

Four draft copies of the reports shall be submitted to the Engineer allowing 10 calendar days for review and approval.  All review comments and suggestions made by the Engineer shall be addressed and/or incorporated into the reports prior to the final submittal.

The Contractor shall submit four copies of the final reports to the Engineer, each report bound in a binder and carrying the seal of the engineer responsible for the survey and the preparation of the reports.

642-4.01  Method of Measurement.  Add the following:  Pay Item 642(2), Three Person Survey Party, shall be used only for extra, additional, or unanticipated work made necessary by changes in the project as directed. (5/7/91)

642-5.01  Basis of Payment.  Add the following:  If additional work as stated above is performed by a two person survey party, hours paid for under Item 642(2), Three Person Survey Party will be 75 percent of the hours worked.  If additional work as stated above is performed by only one person, hours paid for under Item 642(2), Three Person Survey Party will be 32 percent of the hours worked.  (10/1/91)

Add the following pay item:

Pay Item No.			Pay Item	Pay Unit

642(5)              Bridge Survey	Lump Sum

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  Traffic Control Plan.  Add the following to the third paragraph:  All TCP's submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

643-1.03  Worksite Traffic Supervisor.  Delete the second sentence of the first paragraph and substitute the following:  The Worksite Traffic Supervisor shall meet the following minimum requirements:

1.	Be currently certified as a Worksite Traffic Supervisor by the American Traffic Safety Services Association (ATSSA), or,

2.	Be currently certified as a Work Zone Traffic Safety Specialist or a Signs and Lines Specialist by the International Municipal Signal Association (IMSA), or,

3.	Be currently certified as a Worksite Traffic Technician by ATSSA, or,

4.	Have successfully passed the Design and Operation of Work Zone Traffic course sponsored by the Federal Highway Administration (FHWA).

If the individual is certified under Items 2, 3 or 4 above, the Contractor shall submit documentation that the individual has also obtained:

1.	A minimum of one year of supervisory level work in worksite traffic control, or,

2.	One year of having been in responsible charge of such work.  The term "in responsible charge" shall be construed to mean having been in a position of accountability for the selection of devices and for their placement in the traffic control system, or for the continued operation of the system.  Having persons that actually perform the labor under one's control would satisfy this requirement.

643-1.04 Construction Phasing Plan.  Revise the first sentence to read as follows:  A Construction Phasing Plan shall be submitted at least five working days prior to the preconstruction conference for approval by the Engineer and shall consist of the following:  (5/7/91)

643-2.01  Materials.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8-feet.

Delete numbered paragraph 8. in its entirety and substitute the following:

8.	Work Zone Pavement Markings.  Work zone pavement markings shall be either paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08, preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.  The markings shall be applied in accordance with Section 670, Traffic Markings, and the manufacturer's recommendations.

(5/7/91)

Add the following:

12.	Portable Changeable Message Boards.  Portable changeable message boards shall be truck or trailer mounted with a self-contained power supply and shall have the following features:

a.	Message sign panel size of 5'-8" by 7'-5", minimum, with a capacity for a three line message.

b.	Eight character display per message line.

c.	Message modules containing at least 36 different preprogrammed messages (three line displays) to be selected by the Engineer.

d.	The capacity to create, preview, and display new messages and message sequences.

e.	A waterproof, lockable cover for the controller keyboard.

f.	An operator's manual, a service manual, and wiring diagram.

g.	Quick release attachments on display panel cover.

h.	Variable flash and sequence rates.

i.	Manual and automatic dimming capability on lamp bulb matrix models.

j.	The ability to mount at least 7 feet above the pavement to the bottom of the message sign panel.

k.	The capacity to operate with a battery pack for 2 hours under full load.

643-3.02  Roadway Characteristics During Construction.  Add the following to the first paragraph:  The maximum spacing between channelizing devices in a taper should be approximately equal in feet to the speed limit.

643-3.03  Public Notice.  Add the following to the list which follows the first paragraph:

Anchorage Chamber of Commerce

Palmer Chamber of Commerce

Wasilla Chamber of Commerce

Seward Chamber of Commerce

Alaska Visitors Association

Add the following:

1.	Anchorage Newspaper Advertisements.  The Worksite Traffic Supervisor shall notify the Engineer a minimum of 7 days prior to any scheduled delay or closure of driving lanes within the project corridor.  The Engineer will run newspaper advertisements in the Anchorage Daily News indicating the effective dates, and will provide the Contractor's name and the Contractor's 24-hour "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.

2.	Local Newspaper Advertisements.  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of commencing construction, resuming construction after seasonal suspension, or any scheduled delay, or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure.  The advertisements shall be published in the following newspapers:

a.	Chugiak-Eagle River Star,

b.	Frontiersman, and,

c.	Valley Sun.

The Contractor shall indicate on the ad order a first preference for the local news section and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a 24-hour "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.

Advertisements shall be promptly cancelled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

A change order will not be required to initiate newspaper advertisements.

643-3.04  Traffic Control Devices.  Under Item 1., Embankments, change the reference from "Annual Average Daily Traffic (AADT)" to read "Average Daily Traffic (ADT)".

Add the following to Item 1., Embankments:  Barrier reflectors shall be mounted on the face of barrier adjacent to traffic on 50-foot centers and shall be a minimum height of 18 inches above the surface of the roadway.

Delete numbered paragraph 4., Work Zone Pavement Markings in its entirety.

Under item 5., Flagging, add the following after the first sentence of the first paragraph:  Each flagger shall be illuminated from the front to a level of light intensity not less than one foot candle during hours of darkness.

Under item 5., Flagging, add the following:  Flaggers shall wear reflective clothing with markings on arms, legs and head.

Add the following:

9.	Portable Changeable Message Boards.  These boards shall be used to notify the travelling public of the upcoming work as deemed necessary by the Engineer.  Based on the TCP contained in the plans, a maximum of two boards are required for this project.

643-3.07  Maintenance of Traffic During Suspension of Work.  Delete the first sentence and substitute the following:  The Contractor shall submit a Winter Shutdown Plan showing roadway configuration and TCP's to be in place during seasonal suspension of work.  This plan shall be submitted for review one month prior to seasonal suspension of work or no later than September 30.  In addition, the Contractor shall schedule a preliminary meeting with the Engineer and Maintenance and Operations approximately one month prior to seasonal suspension of work.  This meeting shall be to outline the work he expects to complete before shutdown, the condition the roadway is to be in, and review the Winter Shutdown Plan.

643-3.08  Construction Sequencing.  Delete this subsection in its entirety and substitute the following:  A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes or shoulders or their respective widths, stops traffic, or causes the 85th percentile speed to fall more than 10 mph below the posted speed limit.  An approved Traffic Control Plan is required before any restriction to traffic is implemented.  No restrictions to traffic will be allowed during the times listed below:

1.	Monday through Thursday from 6:00 AM to 7:30 AM and from 4:00 PM to 7:00 PM.

2.	Friday from 6:00 AM to 7:30 AM and from 4:00 PM to 10:00 PM.

3.	Saturday and Sunday from 6:00 AM to 10:00 PM.

4.	Around any holiday as described below (in addition to times listed in items 1. through 3., above):

a.	If a holiday falls on Monday, from 6:00 AM to 10:00 PM on the day of the holiday.

b.	If a holiday falls on Tuesday, from 6:00 AM to 10:00 PM on the day before the holiday and the day of the holiday.

c.	If a holiday falls on Wednesday or Friday, from 4:30 PM to 10:00 PM on the day before the holiday and from 6:00 AM to 10:00 PM on the day of the holiday.

d.	If a holiday falls on Thursday, from 4:30 PM to 10:00 PM on the day before the holiday, and from 6:00 AM to 10:00 PM on the day of the holiday and the day after the holiday.

5.	During the Alaska State Fair:

a.	Monday through Thursday from 6:00 AM to 8:00 AM and from 4:30 PM to 11:00 PM.

b.	Friday from 6:00 AM to 8:00 AM and from 4:30 PM to 12:00 midnight.

c.	Saturday and Sunday from 6:00 AM to 12:00 midnight.

No restrictions of traffic will be allowed to remain in place during seasonal suspension of work.

A portable concrete barrier will be required if an excavation or fill area, as described in Subsection 643-3.04(1), exists within 10 feet from the edge of a traveled way.

643-3.09  Temporary Pavement Markings.  Add the following subsection:  Permanent or Temporary Pavement Markings in accordance with this subsection, approved traffic control plans, and Parts III and VI of the Alaska Traffic Manual shall be in place before existing paved roadways, temporary paved roadways and detours, interim paving lifts, and roadways with seal coats and surface treatments are opened to traffic for longer than one continuous work shift.  This work may include restriping of the existing roadway prior to beginning construction of the project.

Conflicting pavement markings shall be removed in accordance with subsection 670-3.04, Paint Removal.  Construction shall be staged so that no traffic is routed over conflicting markings.

Sections of existing roadway that will be opened to traffic during the winter shall be marked at the same location as the existing lines and markings unless shown otherwise on the plans, an approved traffic control plan, or as directed by the Engineer.

The Contractor shall maintain all Temporary Pavement Markings for their intended life without additional compensation for any reapplication that may be required.  There will be no compensation to upgrade Temporary Pavement Markings for short term operations to those required for long term operations.

Only temporary raised pavement markers or removable preformed retroreflective marking tape shall be used as Temporary Pavement Markings on the final pavement surface.  They shall be completely removed and disposed of in conjunction with the placement of the final markings.  The complete removal shall include any residual adhesive that might misguide motorists.  Final pavement markings on finished pavement surfaces and long term pavement markings on other asphalt surfaces shall be in place before work is suspended for the winter.

Temporary Pavement Markings may not be required for construction activities that will be completed within one continuous work shift if the roadway is adequately delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.  The Engineer shall determine the need for the Temporary Pavement Markings for these conditions.

1.	Long Term Operations.  Temporary Pavement Markings which will be in place for more than 2 weeks shall consist of full markings as if a permanent condition exists.

2.	Short Term Operations.  Temporary Pavement Markings which will be in place for less than 2 weeks shall be in accordance with Parts III and VI of the Alaska Traffic Manual with the following exceptions:

a.  Passing Zones.  Broken line pavement markings shall conform to Tables 643-1 or 643-2.  This  applies to both white lane lines for traffic moving in the same direction and yellow center lines for two or three lane two-way roadways when it is safe to pass.

TABLE 643-1*

|  | LENGTH OF MARKINGS |  | SKIP SPACING |  |
| --- | --- | --- | --- | --- |
| Marking Material | Normal Curvature | ** Severe Curvature | Normal Curvature | ** Severe Curvature |
| Removable Preformed Marking Tape | 4 feet | 2 feet | 36 feet | 18 feet |
| Temporary Raised Pavement Markings | 3 units 3 feet on center | 2 units 2 feet on center | 34 feet | 18 feet |

TABLE 643-2*

|  | LENGTH OF MARKINGS |  | SKIP SPACING |  |
| --- | --- | --- | --- | --- |
| Marking Material | Normal Curvature | ** Severe Curvature | Normal Curvature | ** Severe Curvature |
| Removable Preformed Marking Tape | 2 feet | 1 foot | 38 feet | 19 feet |
| Temporary Raised Pavement Markings | 1 unit 40 feet on center | 1 unit 20 feet on center | ____ | ____ |

* No passing markings and signing required per 643-3.09.2.b.

** Severe Curvature:  When the degree of curvature is 5 or greater or when it is necessary for motorists to reduce their speed at least 15 miles per hour below the 85th percentile speed.

b.  No Passing Zones.  No passing zones, as detailed in Section 3B-3 to 3B-5 of the Alaska Traffic Manual, shall be identified as follows:

Sections of asphalt concrete pavement roadways with an ADT of 2000 vehicles per day or greater, shall have broken centerline markings conforming to Table 643-1, and no-passing markings consisting of a continuous 4-inch strip of removable preformed marking tape or temporary raised pavement markers placed on 5-foot centers in the no passing direction.  If a no passing condition exists for both directions of traffic, both directions shall be marked with the two 4-inch stripes of removable preformed marking tape separated by approximately 3 inches, or two temporary raised pavement markers placed approximately 3 inches apart on 5 foot centers and the broken centerline markings are not required.

Sections of asphalt concrete pavement roadways with an Average Daily Traffic (ADT) of less than 2000 vehicles per day, and seal coat and surface treatment pavements shall be marked with temporary pavement markings conforming to Table 643-2 and shall be identified with R4-1, (DO NOT PASS) and R4-2, (PASS WITH CARE) signs.  The signs shall be supplemented with two 18-inch by 18-inch, minimum size, fluorescent red-orange flags mounted above the signs.  The signs shall be mounted so that the bottom of the sign is at least 5 feet above the adjacent roadway.

c.  Other Markings.  It will not be necessary to install arrows, legend, stop lines, crosswalks, or right edge line markings.  Railroad crossing markings are required for areas that have sight restrictions or high accident experience.  Left edge lines will not be required unless they will be the only markings on the paved surface, such as ramps.  All other types of markings are required.  These include channelizing lines and gore area outlines.

d.  Short Term Markings on Seal Coats and Surface Treatments.  Only temporary raised pavement markers conforming to Subsection 712-2.16 shall be used for short-term markings on seal coat and surface treatment pavements.  The markers shall be installed prior to the application of the asphalt surface material and cover coat.

On multicourse surface treatments the temporary raised pavement markers shall be installed following the full width application of the first layer of cover coat.  The markers shall be installed on each day's completed surface before the pilot car operations are removed and unescorted traffic is allowed on the surface treatment in accordance with Table 643-2.

If the temporary raised pavement markers cannot be adequately secured to the first course of the cover coat material with the marker's flexible bituminous adhesive, the Contractor shall secure them to the surface with two nails and washers, of the appropriate length and area, so the nails do not pull through the foot of the marker.

After application of the asphalt and cover coat material, the vinyl protective cover shall be removed to expose the retroreflective surfaces of the marker.  Temporary markers shall be installed so that the foot of the marker unit is facing the direction of the approaching distributor.

Final pavement markings shall not be placed until the seal coat or surface treatment has been opened to traffic for at least 14 days.  Final pavement markings shall be applied within 10 days of the completion of the final sweeping or brooming of the mainline seal coat or surface treatment.  Seal coat and surface treatment pavements are exempt from the two week requirement stated in short-term operations.

(2/21/92)TPM

643-4.01  Method of Measurement.  Delete the second sentence of the first paragraph under Item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted, maintained and removed during the life of this contract.

Delete the last sentence of the first paragraph under Item 3. and replace with the following:  The quantities to be paid for shall be the number of hours or days that the setups are installed, accepted, maintained and removed during the life of this contract.

Delete numbered paragraph 6 in its entirety and substitute the following:

6.	Temporary Pavement Markings will be measured by the single stripe station.  A single stripe is a marking or a temporary raised pavement marker four inches in width.  Wider striping will be measured as multiples of four inches.  Centerline gaps will not be deducted from measurements.  Installation of any word and symbol markings as well as the removal of the Temporary Pavement Markings will not be measured separately but will be subsidiary to this item.  The No-Passing Zone signing, as described in Subsection 643-3.04, 4., b., will not be measured separately but will be subsidiary to this item.

Delete paragraph 7., Seasonal Pavement Markings in its entirety.  (5/7/91)

Add the following: 	Pay Item 643(25), Portable Changeable Message Board will be measured by the day for each sign used as approved by the Engineer.

Newspaper advertisements ordered by the Department will be measured for payment based on a prorated amount of the cost for the advertisement.  The prorated amount will be calculated by dividing the cost of the advertisement among all projects currently advertising.  The Engineer will notify the Contractor within 3 days of receipt of the newspaper's bill, the amount due the newspaper for this project.

Providing a "hot-line road report" telephone with pre-recorded message will not be measured for payment but will be subsidiary to Item 643(1), Traffic Maintenance.

Standard Modifications

643-5.01  Basis of Payment.  Change the pay unit for item 643(3), Permanent Construction Signing, from "Calendar Day" to "Lump Sum."  (5/7/91)

Special Provisions

643-5.01  Basis of Payment.  In the second paragraph, delete Item 1., Seasonal Pavement Markings.

In the fourth paragraph, delete Pay Item No 643(14), Seasonal Pavement Markings.

Change the pay unit for item 643(11), Portable Concrete Barrier, from "Each" to "Linear Foot".

Add the following:  All work required to furnish, install, maintain, and remove the sign supports to be located on the bridges will be included under Item 643(4), Construction Sign.

Barrier reflectors will not be paid for directly, but will be subsidiary to Pay Item 643(11), Portable Concrete Barrier.

Payment for Pay Item 643(25), Portable Changeable Message Board will be full compensation for all labor, equipment, and materials to mobilize, move, maintain, program, and operate a portable message board on the project.

Payment for Item 643(29), Newspaper Advertisements will be made at cost plus 15 percent.  Payment will be authorized upon evidence of payment to the newspaper (paid receipt).

Add the following pay items:

Pay Item No.            Pay Item               Pay Unit

643(25)      Portable Changeable Message        Day

Board

643(29)       Newspaper Advertisements    Contingent Sum

SECTION 644

SERVICES TO BE FURNISHED

BY THE CONTRACTOR

Special Provisions

644-2.01  Field Office.  Delete this subsection in its entirety and substitute the following:  The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work through 30 days after the Engineer issues a letter of project completion.  The following office requirements shall be met:

1.	A minimum of 2000 square feet of floor area.  The office area shall be divided so that it contains a minimum of three (3) each office rooms separated by closable doors.  Each office room shall have a minimum of 350 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power.

4.	A minimum of 250 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 30 vehicles.

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within five miles of the project.

644-2.02  Field Laboratory.  Delete the sixth sentence of the first paragraph and substitute the following:  The water supply shall consist of a 500-gallon capacity tank with a pressure pump or a commercial pressurized system.

Modify the second paragraph to include the following:  The lab slab shall be 8 x 10-feet, and installed within an enclosed structure with an exhaust fan.

Add the following:  The Contractor shall supply electricity with an adequate supply of 110-volt, 60-cycle current, 100-lb. propane bottle, and a 500-gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location as designated by the Engineer.

644-2.06  Scales.  Delete the second paragraph and substitute the following:  Sanitary lavatory facilities, heating, adequate electrical lighting and 120 volt, 60 cycle power shall be furnished to the scale house.

Delete paragraph three in its entirety.

Delete the fourth paragraph and substitute the following:  Furnishing platform scales, tickets, scale house, and electronic weigh system will not be paid for directly, but will be subsidiary to Item 203(6A) Borrow, Type A and Item 203(6C), Borrow, Type C.  Platform scales, scale house and the electronic weigh system shall remain the property of the Contractor upon completion of the work.

Delete the second sentence of the last paragraph and substitute the following:  Platform scales shall be equipped with weatherproof housing and shall be constructed in a manner that protects the recording equipment and allows the scale operator convenient access to the scale computer, ticket printer, and sequential transaction printer.  All components of the scale inside the scalehouse which could be physically manipulated in a manner which could tamper with weights shall be protected by an enclosure, acceptable to the Engineer, to preclude tampering with weighing operations.

Add the following:  The Contractor shall provide an electronic equipment weighing system with the following capabilities:

1.	Self reading scale system with a load cell, scale computer, ticket printer, sequential transaction printer, and the ability to record a complete shift's transaction on a 3.5 inch double sided diskette.  All individual parts of the system shall be compatible with each other and suitable for field conditions.  All supplies (weigh tickets, paper, printer ribbons, diskettes, etc), maintenance, and repair services necessary to keep the system functional, shall also be supplied by the Contractor and will not be measured or paid for directly but will be considered a subsidiary obligation.

Sufficient spare parts, components, etc., shall be available on the Project to keep the electronic equipment weighing system operational at all times.  Unless prior written authorization is obtained from the Engineer, no payment will be allowed for any material weighed without using the electronic equipment weighing system.

2.	The scale computer shall have the ability to store vehicle: identification numbers, tare weights, and maximum allowable "legal" weight (as determined by the Engineer) for all hauling vehicles utilized on the project on each day.  It shall have the ability to store multiple project numbers and multiple pay item descriptions for all projects and pay items which are weighed with the scale system.

3.	During weighing operations, the system shall compare each vehicle's gross weight to its maximum allowable legal weight.  If the vehicle is not exempted from legal weight requirements and exceeds its maximum allowable legal weight, the system shall alert the scale operator that an "overload" exists and present two alternatives;  cancel the weighing operation, or, override the indicator and issue a ticket.  A ticket shall not be issued unless the "overload indicator" is in error (i.e. the vehicle is exempted from overweight requirements).  When the override alternative is utilized the word "OVERLOAD ?" shall be inserted in the COMMENTS field.

The Contractor may haul up to 1000 pounds over the maximum allowable legal weight for a vehicle, without classifying it as an "overload", if the program inserts the maximum allowable net weight in the NET field and inserts the difference between the actual net weight and the maximum allowable net weight in the COMMENTS field (between 1 and 1000 pounds).  If the Contractor elects to exercise this option, no payment will be made for any material in excess of the maximum allowable legal weight.

No payment will be made for any material hauled in a vehicle which is not in conformance with the requirements of Subsection 105-1.12, Load Restrictions and this Subsection.  Non-conforming vehicles shall dump sufficient material so that they conform and then be reweighed.

4.	The system shall have a battery backup as well as protection for power surges or brown outs.  The system shall be capable of retaining all stored data during a power outage and shall be operable during a power outage for at least 30 minutes.

5.	The ticket printer furnished by the Contractor shall print a one part weigh ticket on continuous feed 9-1/2 inch by 4-1/4 inch 90 pound white index paper with removable 1/2 inch perforations on each side with the following information on each ticket in the order listed:

a.	Sequential ticket number (4 digits)

b.	Project information (20 digits)

c.	Date

d.	Pay Item name in words

e.	Hauling unit identification number

f.	Time of dispatch

g.	Name of scale operator

h.	Gross weight in pounds

i.	Tare weight in pounds

j.	Net weight in pounds

All of the above items are to be printed by the ticket printer and not pre-printed.  After printing, the weigh ticket shall be automatically advanced to a position where it can be torn off at a perforation.  During pay item weighing operations, the system shall function such that the scale operator shall only have to enter a one digit code for the project number, a one or two digit code for the pay item, and the hauling unit identification number.

The weigh ticket "number" consists of the following information:

a.	Project Number (1st 5 characters of PROJECT

field)

b.	Pit Number (Last 3 characters of PRODUCT field)

c.	Date

d.	Pay Item

e.	Sequential ticket number

The sequential weigh ticket number shall be set to "1" at the beginning of each day for each unique project number, pit number, and pay item combination.  The project information, date, pay item, hauling unit identification numbers and their maximum allowable legal weight, and the scale operator's name shall also be able to be set by the scale operator.  Tare weights shall only be able to be changed by a tare weighing operation.

6.	The sequential transaction printer shall print all scales transactions including tares and data that is changed by the scale operator, as soon as the transaction is concluded.  The sequential transaction printer shall allow for the paper to be manually advanced so that the scale operator can write notes on the paper when special situations occur such as voided tickets, incorrect hauling unit number used, etc.

7.	The double sided diskette shall record all ticket information which was produced during a shift or at selected times in the shift.  Transaction data for each weighing operation shall be recorded on the disk at the end of each weighing operation.  The data shall be stored in two files with the same information but different formats.  The first file shall be in dBASE IV format (IBM) and shall be useable by the program without any conversion or manipulation.  The naming convention for this file shall be "yymmdd.dbf".  The second file shall be a raw data file in ASCII format with fields separated by commas, character fields enclosed in double quotes, a carriage return at the end of each record, and an end of file mark following the last record.  The naming convention for this file shall be "yymmdd.csv".  If more than one scale is used on the project, a scale location designation acceptable to the Engineer shall be utilized for the 7th and 8th characters of the filename.

In the event both data files on the diskette are not completely useable to obtain all truck weighing data, or permission is obtained from the Engineer to weigh without the electronic system, the Contractor shall correct or reconstruct the data file utilizing the sequential transaction log or other information, as directed by the Engineer, as a data source.  No payment will be made for any hauled material on a given date until an accurate "daily" data file has been delivered to the Engineer.

8.	The fields for each record shall be in the following format and order.  Other data fields may also be provided but shall follow the fields in the required format.

| Field | Field Name | Type | Width |
| --- | --- | --- | --- |
| 1 | TKT | Character | 4 (right justified w/leading blanks) |
| 2 | DATE | Character | 8 (mm/dd/yy) |
| 3 | TIME | Character | 5 (hh:mm) (24 hour) |
| 4 | UNIT ID | Character | 10 (right justified w/leading blanks) |
| 5 | GROSS | Numeric | 6 (pounds) |
| 6 | TARE | Numeric | 6 (pounds) |
| 7 | NET | Numeric | 6 (pounds) |
| 8 | COMMENTS | Character | 20 |
| 9 | PRODUCT | Character | 20 |
| 10 | PROJECT | Character | 20 |
| 11 | NAME | Character | 18 |

9.	The system shall be able to generate a summary report, either during or at the end of the day, which summarizes the number of loads and total net weight for each Date, Project, and Product.

When checking for overloads is being utilized, the system shall be able to generate a report which lists all hauling identification numbers and their maximum allowable gross weight.

10.	A user instructional manual shall be available for each scale which explains the complete scale operation.  A copy of this manual shall be kept in each scalehouse and be available for review by the Engineer at all times.

11.	In the event that extra construction engineering expenses are incurred due to checking non-machine data entries or other data irregularities, an amount equal to the value of those expenses will be deducted from the value of the item.  A unilateral change order will be issued to make any adjustments the Engineer determines to be warranted.

(1/8/92)R145

644-2.08  Water Testing.  Add the following subsection:  Prior to initiating work around Rabbit Slough and Spring Creek, the Contractor shall retain an independent test laboratory to test water samples taken by the Engineer.  These samples shall be tested for turbidity and suspended solids, in accordance with the appropriate EPA test method, and the results shall be transmitted directly to the Engineer.

644-3.01  Method of Measurement.  Add the following:  Water testing will be reimbursed based on paid receipts for the authorized tests.

644-4.01  Basis of Payment.  Add the following:  Payment for water testing will be made on the receipts for authorized samples plus 15 percent, and shall be considered full compensation for all labor, equipment and materials required to have tests performed.  A change order will not be required to initiate water testing.

Electricity, propane and water supplied for the State provided portable asphalt lab will not be measured for payment, but will be considered subsidiary to Item 644(2), Field Laboratory.

Add the following pay item:

Pay Item No.        Pay Item             Pay Unit

644(9)         Water Testing        Contingent Sum

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  Description.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01  Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.1, located in the "green pages" of this document.

645-3.01  General.  The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following:  contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02  Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03  Subcontracts.  In the event the Contractor subcontracts a portion  of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01  Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or,

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.			Pay Item	Pay Unit

645(1)            Training Program	Labor Hour

6 Trainees/Apprentices

(10/29/91)S16

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.01  Description.  Add the following.  Item 660(3), Highway Lighting System Complete, shall also include furnishing and installing the conduits, anchor bolts, lighting standards, and mounting brackets on Bridges 1121, 1124, 1887, and 1888 as detailed on the plans.  The ends of all lighting standards shall be threaded and shall be provided with an end cap.  The conduits on Bridge 1121 shall be provided with grounding bushings, pull ropes, and push penny plugs.  The conduits on other bridges shall be capped.

This work shall also consist of testing various types of bridge delineating lighting and installing the selected bridge delineating lighting system.  This work will be completed at the direction of the Engineer and shall include the following:

1.	Phase I - Testing.  This shall consist of supplying and installing various light fixtures and materials to support the development of the most effective lighting system for delineating the edges of the Knik River bridges in heavy fog.  The test shall be performed on bridge 1885 at the locations directed by the Engineer and shall be performed during the months of November and December 1992.  The following equipment is required to complete the testing:

a.	five light fixtures of each type specified under subsection 660-6.02(A), Delineation Light Fixtures,

b.	shields of various designs that protect the light fixtures from snow plowing operations,

c.	conduits, junction boxes, conductors, power supply and all other hardware needed to provide an operational test lighting system. Circuits shall be as specified in subsection 660-2.09(A), Wiring.

2.	Phase II - Installation.  This shall consist of installing a complete lighting system on bridges 1885 and 1121, using lights and plow shields selected from the first phase judged by the Engineer to be the most effective.  The complete lighting system shall consist of the following:

a.	64 light fixtures with plow shields on the two Knik River Bridges,

b.	conduit, junction boxes, conductors, and all other hardware required to provide an operational bridge delineation lighting system.

This work shall be accomplished using the existing conduit system and lamp poles found on bridge number 1885, and the conduit system and lamp poles which will be provided under the bridge items of this contract.

660-1.05  Maintaining Existing and Temporary Electrical Systems.  Delete this subsection in its entirety and substitute the following:  The Contractor shall provide all work required to maintain, and reinstall when necessary, the following existing and temporary systems:

1.	traffic signal,

2.	highway lighting,

3.	flashing beacon, and

4.	sign illumination systems.

They shall be kept in effective operation during the progress of the work, except when shutdown is permitted to allow for alterations or final removal of the systems.  Systems shall be considered in effective operation when there are no damaged, inoperative, or malfunctioning components, and they operate as designed.  The Department will pay for all electricity required for the operation of the systems, if they are in effective operation and the public benefits from their operation.  Replacement equipment shall be compatible with existing equipment used in the Central Region.

Signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets shall be relocated or replaced whenever they are closer than 6-feet to the travelled way.

During the various phases of construction, the Contractor shall shift the signal heads as required so they are aligned both horizontally and vertically with the approaches in accordance with the following:

1.	For a signal mounted overhead, the height above the travelled way to the bottom of the signal shall be minimum 17.5 and maximum 19.0 feet.

2.	For a side mounted signal, the height above the travelled way to the bottom of the signal shall be minimum 9.0 and maximum 11.0 feet.

3.	An overhead signal controlling a single lane shall be in line with the center of the lane.

4.	The overhead signal controlling two lanes and each of the two overhead signals controlling three lanes shall be in line with the stripe separating the lanes.

5.	If, when the travelled way is moved, the side mounted far right signal head is located such that the horizontal angle to it from the center of the farthest left through lane at the stop bar exceeds 20 degrees, then it shall be moved to an overhead location.  If there are two or three through lanes, then all overhead signal heads shall be realigned so that one is centered over each lane.  If there is one through lane, then the former side mounted signal head shall be located 8 feet to the right of the existing overhead signal.

6.	For a pedestrian signal, the height above the travelled way to the bottom of the signal shall be minimum 7.0 and maximum 9.0 feet.

7.	All signal heads shall be aimed so they conform with subsection 660-4.01, Installation Details.

Signal system shutdowns shall be limited to periods during normal working hours as specified in Section 643, Traffic Maintenance, during which flag control shall be used.  Lighting system shutdowns shall not interfere with the regular lighting schedule.  Local traffic enforcement and maintenance agencies shall be notified prior to any shutdown of a traffic signal system.

When the Contractor begins work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include repair or any damage prior to the date of the transfer of maintenance responsibility.  Therefore, before commencing work on the project, the Contractor should inventory the condition of the existing equipment and present written documentation of all damaged, inoperative, and malfunctioning electrical equipment.  This equipment shall be inspected jointly by the Engineer and the Contractor.  If the Contractor begins work before he provides the Engineer with an inventory, he waives the right to claim extra compensation when any component is later found to be damaged, inoperative, or malfunctioning.

At the Preconstruction Conference the Contractor shall furnish the Engineer with the name and phone number of the person responsible for maintaining existing and temporary electrical facilities.  This person shall be available at all times until the date of Acceptance for Traffic and Maintenance and have access to all labor, materials, and equipment required to complete any repair.

Repair work on traffic signals shall begin within one hour of notification.  If repairs are not completed as required, then the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due the Contractor.  The Contractor shall maintain a hand printed record of all work performed on the signal system in the diary found in each controller cabinet.  Each entry shall include the following:

1.	The date(s) and time(s) the changes or maintenance operations began and were completed, and the names of the crew members completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the changes or performing maintenance.

The Contractor shall ascertain the location of existing conduit runs, buried cables, junction boxes, and all underground utilities before using equipment that may damage such facilities or interfere with any system.

Where roadways are to remain open to traffic and existing lighting systems are to be modified, the Contractor shall energize the modified circuit by sunset on the same day he retires the original circuit.

Where an existing system is being modified, work not shown on the plans or specified in the Special Provisions which the Engineer determines is necessary to keep all or any part of the existing system in effective operation will be paid for as extra work as provided in subsection 109-1.05, Compensation for Extra Work.

When no longer required, the Contractor shall salvage all original and Department provided equipment in accordance with the plans and subsection 660-6.07, Salvaging Electric Equipment, and remove all other materials used in the temporary systems from the project.

660-1.05(A)  Temporary Signal Systems.  Add the following subsection;  The Contractor shall provide temporary signalization at the intersection of the Parks Highway and the Glenn Highway.  At no time shall the intersection operate in an unsignalized mode, except for shutdown due to change over from the existing system to a temporary system, and from the temporary system to a permanent system.  Temporary signal system shutdowns shall be limited to periods during normal working hours as specified in Section 643, Traffic Maintenance, during which flag control shall be used.

A plan for each temporary signal system shall be submitted to and approved by the Engineer prior to implementation.  The temporary signal plan shall equal or exceed the system being replaced or modified.  That is, the plan shall not downgrade the number of signal heads, signal phases, pedestrian push-buttons, etc.  The temporary signal system plan shall also include the layout of the temporary intersection.  The complete plan shall include intersection geometrics, lane widths and auxiliary lane pocket lengths.

The Contractor shall furnish and install all materials and miscellaneous hardware required to provide a functional traffic signal system.  All materials shall conform to the requirements of the plans and specifications.  Temporary equipment shall be compatible with existing equipment used in the Central Region.  Load centers shall be provided as required in subsection 660-1.05(B), Temporary Illumination Systems.

The temporary signal system may consist of:

1.	the existing systems,

2.	relocations of the component parts,

3,	guyed wood poles, or

4.	any portion of the permanent signal system.

Traffic signals may be suspended from messenger cables provided they are mounted by standard span wire hangers and secured with a second cable to prevent misalignment in a wind.  All signal faces shall be equipped with backplates and visors.  The signal faces of each phase with two or more faces shall be energized using two circuits, with each circuit wired with an IMSA 20-1 signal cable.  Splices shall be made only at the terminal blocks in the signal faces.  Sufficient signal cable slack shall be left at each pole to provide for drip loops and to allow realignment of each signal head.  Temporary controller assemblies may be mounted on Type III junction boxes while work is completed on the permanent systems.

Whenever a pole of the permanent signal system is included in a span wire signal system, the Contractor shall guy the pole and provide protective collars to prevent chafe damage.  Poles with breakaway bases shall not be included in a span wire supported signal system.

Unless otherwise specified, no vehicle detection will be required in the temporary systems during the construction season after the existing loops are removed during normal construction.  At that time, the controller will revert to the pre-timed mode.  However, prior to the Department's acceptance of the signalized intersections for winter maintenance, vehicle detection shall be installed and working to the same extent as it was in the original and temporary signal systems prior to their removal.

660-1.05(B)  Temporary Illumination Systems.  Add the following subsection:  The Contractor shall provide illumination at all locations with preexisting lighting, at the locations specified in the Traffic Control Plans, and at all intersections where temporary traffic signalization is specified to be provided.

This work shall be provided during the life of the contract on all roadways open to traffic within the project limits.  The temporary lighting systems shall be operational by sunset on the same day the replaced system is retired, or the roadway is opened to traffic.

A plan for each temporary lighting system shall be submitted to and approved by the Engineer prior to implementation.  The temporary lighting plan shall equal or exceed the system(s) being replaced or modified, and at intersections, consist of a luminaire located on the far right for each through street approach and installed adjacent to the through street radius returns.  The through street is the street with the vehicular right-of-way; both streets shall be considered through at signalized intersections and four-way stops.

The Contractor shall furnish and install all materials and miscellaneous hardware required to provide a functional lighting system, including electrical load centers.  All materials shall conform to the requirements of the plans and specifications, except that the branch conductors may be triplex aluminum with messenger cable if they are installed overhead.  Illumination conductors shall be sized so the voltage at the most remote luminaire is not less than the minimum required for the ballast, as recommended by the manufacturer.  The Contractor shall install intermediate conductor and supports to energize luminaires at locations without electrical service.  Luminaires used in the system may be the existing fixtures or new fixtures with a light distribution compatible with the proposed lighting configuration.

The temporary lighting systems may consist of any of the following lighting pole types, or combinations thereof, provided the luminaires have a minimum 30 feet mounting height.  Mounting height is the difference in elevation between the luminaire refractor and the edge of travelled way at the same station.  The existing poles may be reused if they are not utility owned.  Any pole of the permanent lighting and temporary signal systems, and any Contractor supplied poles may be used in the temporary lighting system(s).  Contractor supplied poles may be wood, and shall meet AASHTO design criteria for 80 miles per hour wind.  All poles, except traffic signal poles, installed within the clear zone shall be provided with FHWA approved: slip bases, transformer bases, or frangible couplings.

The load centers to power the temporary lighting and signal systems may be the permanent installations, the existing installations, or temporary installations.  The existing load centers may be used only if they are scheduled to remain intact until completion of the project, and reused only if they are approved.  The Contractor shall provide approved temporary load centers with photoelectrically controlled lighting circuits, whenever no load center is available for use or when an existing load center that is not approved is retired due to conflict with the work.  An approved load center is any load center UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "suitable for use as service equipment".  The Contractor shall provide all work to modify these load centers as required to provide functional temporary lighting and signal systems and to install them, completing all work in accordance with the NEC.

660-2.03  Foundations.  Delete the last two paragraphs of this subsection.

660-2.04  Poles, Steel Pedestals and Posts.  Add the following:  All poles and mast arms shall be designed for 100 MPH wind speeds with gusts to 130 MPH.

660-2.08  Conductors.  Add the following to Table 660-1:

Conductors                     Wire    AWG.     Band

/Cable          Circuit     Color/No.  No.    Legend

3    Highway Illumination    1      6    Circuit No.

Highway Illumination    2      or   Circuit No.

Highway Illumination    3    larger

________________________________________________________

3    Service to Controller   1      6       "SIG"

Neutral                 2      or     No Band

Spare                   3    larger   No Band

________________________________________________________

Standard Modifications

660-2.09(A)  Wiring.  In the seventh paragraph,  insert "and feeder" between "signal" and "conductors".

(5/7/91)

Add the following:  Each lighting standard shall be provided with a 4-inch long pipe nipple, coupling, and Crouse Hinds model CAS 3M PRB plug and receptacle.  The luminaires shall be installed on the nipple, which shall be threaded on one end only.  The plug and receptacle shall be installed in the coupling, and be held in place with a Crouse Hinds model 40762 secondary connection retainer.  The tails of the plug and receptacle shall be #12 AWG conductors, and the line side receptacle conductors shall be 10 feet long, and the load side plug conductors shall be 3 feet long.

Special Provisions

660-2.09(A)  Wiring.  Add the following:  The bridge delineation lighting circuits shall consist of one 3 conductor #8 AWG cable.  The parallel tap splices shall be made in the lamp pole mounting bracket using fused splice connector kits.  The tap wires shall be #10 AWG conductors.

660-2.10  Bonding and Grounding.  Add the following after the first paragraph:  The Contractor shall install a bare, number 8 AWG, solid copper conductor in all conduits as the grounding conductor.  The grounding conductors shall be attached to the conduits using insulated throat grounding bushings, leaving one foot of slack between each grounding bushing.

All hardware, including insulated throat grounding bushings, ground rods, and ground rod clamps shall be UL listed.  Grounding bushings shall be the threaded type.

Delete the fifth paragraph on page 441 and substitute the following:  Where conduit is installed as a spare or for future use, the aforementioned copper grounding conductor may be omitted.

Standard Modifications

660-4.01  Installation Details.  In numbered paragraphs 7 and 9, under "Loops", change "660-2.08" to read "660-2.09(A), Wiring".  (5/7/91)

660-5.02  Backplates.  In the last paragraph, change "660-2.16" to read "660-2.15, Painting".  (5/7/91)

Special Provisions

660-6.01  Luminaires.  Add the following paragraph:  No paint may be applied to the reflecting surface of luminaire reflectors.

Luminaires to be used shall provide the specified uniformities or better in the configurations listed in the table below.  Uniformity is defined as the average maintained illumination level divided by the maintained illumination at the dimmest point.  Uniformity shall be calculated using the manufacturer's current published photometric charts.  Uncorrected illumination values shall be derived by straight line interpolation between lines of the isofootcandle curves.  Computations shall be done assuming luminaires are located on one side of the roadway only.

Lum   Road   Mtg            Lum               Initial

Type  Width  Ht  Spacing  Offset  Uniformity    Foot-

Candles

MC-3    40'  40'   220'      0'      2.7:1      1.2

Offset  36'  50'   200'    -30'      3.0:1      1.4

Luminaire Type Definitions:

MC-3:	A cobra head style luminaire with a medium  cutoff, type 3 distribution as defined by the  Illuminating Engineering Society (I.E.S.).

Offset:	A floodlight type luminaire designed to be adjusted between 30 and 50 degrees from horizontal and be mounted on the top of a pole, which is offset back from the edge of traveled way.

660-6.02(A)  Delineation Light Fixtures.  Add the following subsection:  The following light fixtures shall be tested for their effectiveness in delineating the edges of the Knik River Bridges in foggy weather conditions.  All ballasts shall be rated for 240 volt operation.

| Model | Manufacturer | Lamp Watts | Remarks |
| --- | --- | --- | --- |
| Tubaloid | Voight Lighting | 35 W, LPS | - |
| Tubaloid | Voight Lighting | 55 W, LPS | - |
| M-250R2 | General Electric | 70 W, HPS | Medium Type III distribution |
| L-861 | ADB-ALNACO | 40 W, Incan. | A taxiway edge light |
| FBP-9 | Fail Safe | 9 W, Fluor. | 120 Volt ballast OK |

Where:

LPS = Low Pressure Sodium,

HPS = High Pressure Sodium,

Incan. = Incandescent,

Fluor. = Fluorescent

Any other light fixtures specified by the Engineer after the contract is awarded shall also be tested.

660-6.07  Salvaging Electrical Equipment.  Add the following to the first paragraph:  Controller assemblies shall be salvaged and delivered to the State Maintenance Yard at 5820 East Tudor Road in Anchorage.  All other salvaged equipment, including light fixtures tested but not selected for the bridge delineation lighting system,  shall be delivered to the State Maintenance Yard at 289 Inner Springer Loop in Palmer.

Delete the fourth paragraph and substitute the following: The following existing items shall become the property of the Contractor and be disposed of as indicated.  Items that are to be removed shall be removed from the highway right of way.

1.	Junction boxes (not including lids), conductors, and foundations for signal posts and controller assemblies shall be removed.

2.	Conduits may be abandoned in place provided elbows sweeping the conduits into junction boxes are removed.  However, existing conduits encountered while trenching shall be removed to provide two radial feet of clearance between the old and new conduits.

3.	Traffic signal pole and electrolier foundations may be abandoned in place, provided the tops of the foundations, reinforcing steel, anchor bolts, and conduits are removed to a depth of not less than one foot below roadway subgrade, sidewalk, or unimproved ground, whichever applies.

4.	Existing conductor that form vehicle detectors, which are encountered while installing new detectors, shall be removed.

660-7.00  Method of Measurement.  Add the following:  The method of measurement for Item 660(25), Bridge Delineation Lighting, shall be as specified in the order authorizing the work.

660-7.01  Basis of Payment.  In the first paragraph, modify line eleven to read:  "...involved in furnishing and installing, modifying, maintaining and...".

Add the following.  Payment for Item 660(25), Bridge Delineation Lighting, will be made on a time and materials basis in accordance with subsection 109-1.05, Compensation for Extra Work.  It will be full compensation for furnishing all labor, materials, tools, equipment, and incidentals for installing, modifying, maintaining, and salvaging the components needed to complete the work as described herein and as directed by the Engineer to provide a functional bridge delineation lighting system.  It shall also be full compensation for any required excavation and backfill, restoration of any pavement and appurtenances damaged or destroyed during construction, and for making all tests required.

Add the following pay item:

Pay Item No.          Pay Item                Pay Unit

660(25)    Bridge Delineation Lighting   Contingent Sum

SECTION 661

ELECTRICAL LOAD CENTERS

Special Provisions

661-1.02  Equipment List(s) and Drawings.  Add the following subsection:  The Contractor shall submit for review and approval, within 30 days following award of the contract, 8 collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s) and the following:

1.	For materials on the Approved Products List:  a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

2.	For materials not on the Approved Products List:  catalog cuts that include the manufacturer's name, type of product, size, model number, conformance specifications, and supplemented by other data as may be required, including manufacturer's maintenance and operations manuals, or sample articles.

This information may be included in the portfolio for 660 items.

The Department will not be liable for any material purchased, labor performed, equipment used, or delay to the work before all equipment and materials have been reviewed and approved.

661-2.01  Materials.  Add the following:  Type 1 load center cabinets shall be constructed similar to the section and elevations shown in the plans, and conform to the following requirements.  Slight variation in the dimensions is allowable, except in the anchor bolt template.

1.	The cabinet shall be constructed of zinc-coated A60 finish sheet steel per ASTM A525 with no external screws, bolts, or nuts.  The components shall have the following minimum thickness as measured by the United States Standard Gauge:  the exterior shell No. 12 gauge, the interior doors and panels No. 14 gauge, and the interior covers No. 16 gauge.

2.	The components shall be painted with a 2-part urethane paint undercoating inside and out.  The final finish shall be a 2-part urethane paint, standard white for removable panels and non-gloss silver-gray, closely matching Color No. 36622 of Federal Standard Specification No. 5950 for the enclosure.

3.	The service entrance section shall be isolated from the main load section and distribution load section by non-removable metal barriers, and shall be equipped with landing lugs for termination of service conductors.

4.	The cabinet shall be provided with internal mounting brackets sized for 1/2-inch anchor bolts for use with a standard mounting base assembly.

5.	All doors shall be equipped with continuous stainless steel pin hinges, coin latches and hasp for padlock.  The meter section door shall have a clear polycarbonate resin window, 0.187" minimum thickness, with a minimum size of 10.0-inch x 10.0-inch, which shall be sealed with silicone.

6.	Each completed load center assembly shall be provided with an exterior name plate, safety labels, interior identification labels, wiring diagram, and installation instructions.

7.	When two type 1 load centers are to be installed adjacent to one another, furnish one cabinet with the load distribution section located on the left side.

The wiring configuration for each load center type shall be in accordance with the wiring diagram indicated on the load center detail sheet.  Circuit breaker ratings shall be as shown in the load center summary for each location.  Dead panels shall be indelibly labeled with the circuit number and the direction of the circuit run from the load center.

When the load centers are ready to be energized, the Contractor shall request and coordinate an electrical inspection of the load centers from the local authority having jurisdiction, allowing at least 5 working days before the inspection is needed.  The Contractor shall be present during the inspection to assist in accessing the cabinets and to answer questions.  The Contractor shall correct the deficiencies noted in each load center.

Payment of any fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be considered incidental to the Section 661 items.  (9/1/89)

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDER STATIONS

Special Provisions

669-1.01 Description.  This work shall consist of furnishing and installing traffic count stations for the automated collection of traffic data on an intermittent or permanent basis.  The Automated Traffic Recorder (ATR) station is a vehicle detection system.

The ATR station can be a combination of detection, electronics and software and is defined as a system.  Three types of systems are defined as follows:

1.	An Intermittent ATR station shall consist of the following parts:

a.	inductive loops detectors for detecting the presence of vehicles, and

b.	underground conduit, junction boxes, cabinet, and wiring as specified on the plans.

2.	A Traffic Volume Count System shall consist of the following parts:

a.	inductive loop detectors for detecting the presence of vehicles,

b.	electronic unit for collecting and storing data obtained from the sensors, Model GK 6000-TC volume counter

c.	communications capabilities (e.g. modem and cabling) for transmitting the data to IBM PC compatible computers located both in the Highway Data Office in Anchorage, Alaska, and portable laptop computers carried to the equipment site by State personnel, and

d.	underground conduit, junction boxes, equipment cabinet, electrical and telephone service as specified.

3.	An Automated Vehicle Classification (AVC) System shall consist of the following parts:

a.	piezoelectric sensors for detecting vehicle presence and counting axles and measuring axle spacing,

b.	two electronic units for collecting, analyzing and temporarily storing the data obtained from the sensors, a model GK 6000-TC volume counter and a model PAT C100s vehicle classifier,

c.	communications capabilities (e.g. modem, remotely controllable code operated switch and cabling) for transmitting the data to IBM PC compatible computers located both in the Highway Data Office in Anchorage, Alaska, and portable laptop computers carried to the equipment site by State personnel, and

d.	underground conduit, junction boxes, equipment cabinet, electrical and telephone service as specified.

The locations of traffic detection and cabinets shown on the plans are approximate and the exact locations shall be established in the field by the Engineer.

General description of the Automated Traffic Recorders are as follows:

Assembly H1 -	A twelve loop permanent ATR for automated vehicle classification system with electrical and cellular telephone service.  Installation includes piezoelectric sensors.

Assembly H2 -	A four loop ATR for intermittent vehicle counting without electrical and telephone service.

Assembly H3-	A one loop ATR for intermittent vehicle counting without electrical and telephone service.

Assembly H4- 	N.I.C.

Assembly H5-	A one loop ATR for intermittent vehicle counting without electrical and telephone service.

Assembly H6-	A three loop ATR for intermittent vehicle counting without electrical and telephone service.

669-1.02  Regulation and Code.  All materials and workmanship shall conform to the standards of the Underwriters Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturers Association, where applicable.

669-2.01 Materials.  All materials provided for the work shall be new, unless otherwise stated, and shall meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with Subsection 660-2.09(A), Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable.

2.	Conduit.  All conduit shall be in accordance with Subsection 660-2.05, Conduit.  Nylon pull cords shall be left in all two inch conduit.

3.	Junction Boxes.  All junction boxes shall be in accordance with Subsection 660-2.06, Junction Boxes.  Junction boxes used for ATR installations shall not contain any conductors carrying a voltage greater than 50 volts.

4.	Terminal Blocks.  All terminal blocks shall be provided with nickel, silver or cadmium plated brass binder head screw terminals.  All terminal block which are installed in junction boxes shall be waterproof and resistant to corrosion.  Terminal blocks shall be a barrier type, 600vac @ 20 amps, capacity for 12-18 AWG wire with removable shorting bars in each positions and with integral type marking strips.  All conductors shall be terminated and labeled to a terminal block.

5.	Inductive Loops.  All inductive loops shall be in accordance with Subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be UL listed as Type RHW/USE/XLP 12AWG 600V rating.

Loop lead-in cable home run shall consist of a twisted pair 18AWG stranded tinned copper wire with polyethylene insulation, covered with an aluminum foil shield, stranded copper drain wire, and PE outer jacket conforming to IMSA specification 50-2.

Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, and aluminum shield, and overall PVC or PE outer jacket conforming to IMSA specification 50-2.

6.	Cabinets.  All cabinets shall be unpainted, brushed aluminum and include a thermostatically controlled heater and exhaust (cooling) fan, switched light, 3 adjustable shelves, Corbin No. 2 lock, Ground Fault Interrupt (GFI) circuit breakers, dual sets of four 110 volt receptacles mounted per the plans, and terminal blocks mounted on the walls adjacent to the door.  All cabinets shall have a NEMA 3R specification with fully gasketed full width access door.  All style 1 and 2 cabinets shall be installed as indicated on the plans.

7.	Department Furnished Materials.  The following Department furnished materials are available from the State Supply Warehouse located at 5000 Aircraft Avenue in Anchorage, Alaska.

a.	1 each Telephone modem, model Microcom QX2400C

b.	1 each Remote controlled code operated switch, model Black Box GS-SW540A

c.	1 each Traffic Volume Counter, model GK-6000- TC

d.	1 each Automated Vehicle Classification Counter, model PAT C100S

e.	2 each class II piezo electric axle sensors with 2 gallons epoxy hardener

f.	1 each cellular telephone

g.	1 each cellular telephone interface

The Contractor shall sign for materials at the time of receipt.  Materials are available for pickup between the hours of 7:30 a.m. to 11:30 a.m. and 12:30 p.m. to 4:00 p.m. daily, except Saturdays, Sundays and legal holidays.  Pickup of materials should be coordinated with Mr. Douglas Terhune, Highway Data Section Supervisor at 266-1618.  Storage and safekeeping of all materials after pickup shall be the Contractor's responsibility.

669-3.01 Construction Requirements.

1.	Wiring.  All wiring shall be installed in accordance with Subsection 660-2.09(A), Wiring. All unused pairs shall be terminated within splices, at cabinets unused pairs shall be terminated to a terminal block and labeled "SPARE".

2.	Conduit.  All conduit shall be installed in accordance with Subsection 660-2.05, Conduit or as indicated on the plans.

3.	Junction Boxes.  All junction boxes shall be installed in  accordance with Subsection 660-2.06, Junction Boxes or as indicated on the plans.

4.	Terminal Blocks.  All terminal blocks and wire pairs shall be clearly labeled on the block.  Terminal blocks within cabinets shall be mounted so that all terminals are easily accessible from the front of the cabinet.  By convention, wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block. All conductors shall terminate and be soldered to "spade" type terminal lugs.

5.	Inductive Loops.  All inductive loops shall be installed and constructed in accordance with Subsection 660-4.01, Installation Details, unless otherwise specified on the plans.

All inductive loops shall be formed of four turns of wire, and shall be six feet square with plus-or-minus one inch tolerance.  All inductive loops in a lane shall be located sixteen feet from leading edge to leading edge, with plus-or-minus one inch tolerance.  All inductive loops located in adjacent lanes shall be aligned within plus-or-minus one inch tolerance.  Inductive loops for entrance or exit ramps shall be 6 feet by 12 feet wide and located as shown on the plans or at the direction of the Engineer.

All lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the center line of the road.

6.	Cabinets.  All style 1 and 2 cabinets shall be installed as indicated on the plans.

7.	Piezoelectric Sensors for AVC.  All permanent piezoelectric sensors shall be installed per AVC equipment manufacturer's recommendations.  All coaxial cables shall be run to the equipment cabinet without splices and terminated on the specified terminal block, with at least six feet of slack cable available in the equipment cabinet prior to the terminal block.

8.	General Tests.  All ATR installations shall have tests conducted in accordance with Subsection 660-4.01, Installation Details.

9.	Piezo Electric Sensors.  All piezo electric sensors shall be tested for signal at the cabinet terminal block as per the manufacturer's specifications.

669-3.05  Deliverables.  All deliverables shall be submitted to the Engineer prior to final approval of the work or as otherwise called for herein.

1.	Equipment List(s) and Drawings.  The Contractor shall submit for review and approval within thirty days following award of the contract, three collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s), and a description that includes product name, manufacturer, model or part number.

The Department will not be liable for any materials purchased, labor performed, equipment used or delay to the work before all equipment and materials have been reviewed and approved.

2.	As-Built Plans.  The Contractor shall prepare four complete sets of as-built plans which will be kept current with the construction.  These as-built plans shall detail all  construction changes made to the plans and also include the following information on the appropriate sheets:

a.	the location and depth of all inductive loops and conduit runs, and,

b.	the station and offset of all junction boxes.

Redlines of full size construction plans will be acceptable.

Three sets of as-built plans shall be presented to the Engineer, and one set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet at the appropriate ATR installation.

3.	Test Results.  Written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Engineer prior to acceptance of the Automated Traffic Recorder installation.  Tests will be conducted in accordance with Subsection 660-4.01, Installation Details.

669-4.01  Method of Measurement.  No measurement of quantities will be made for the Automated Traffic Recorders.

669-5.01  Basis of Payment.  The lump sum price for Item 669(1), Automated Traffic Recorders will be full compensation for furnishing all equipment, labor and materials necessary to complete the work as specified, with the following exceptions:

1.	Backfill materials required will be paid for under their respective pay items.

2.	Asphalt required will be paid for under the respective asphalt pay item.

Excavation, as-built plans and acceptance testing required for these installations will not be paid for separately, but will be subsidiary to the Automated Traffic Recorders.

Payment will be made under:

Pay Item No.			Pay Item	Pay Unit

669(1)       Automated Traffic Recorders    Lump Sum

SECTION 670

TRAFFIC MARKINGS

Standard Modifications

670-3.01  Construction Requirements.  In the last paragraph under Item 2., insert "pneumatic" immediately before "roller".  (5/12/89)

Special Provisions

670-3.04  Paint Removal.  Change title of subsection to: "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following:  Existing pavement markings shall be removed to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement.  Painting over existing striping does not meet the requirement for removal.  Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.05  Preliminary Spotting.  Add the following:  Lines and markings to be replaced at their existing locations shall be referenced by the Contractor at his expense, prior to performing any work that may disturb them.  The Engineer will determine the beginning and ending points for the no-passing zones.

670-4.01  Method of Measurement.  Add the following:

6.	Station Basis.  Measurement of a traffic stripe will be the length of each individual stripe excluding gaps.  An individual stripe is a longitudinal marking less than six inches wide.

Delete the last paragraph and substitute the following:  Removal of traffic stripes and pavement markings will be measured by the station for payment.  Repair of any damaged pavement or surfacing caused by the pavement marking removal operation will be subsidiary to this item.

670-5.01  Basis of Payment.  Add the following:  Payment for removal of existing markings will be made under the following:

Pay Item No.             Pay Item             Pay Unit

670(9)      Removal of Pavement Markings    Station

SECTION 702

ASPHALT MATERIALS

Standard Modifications

702-2.04  Storage And Application Temperatures.  In Table 702-1, change storage temperatures for ACs from "340 Max" to "325 Max".  (5/12/89)

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  Fine Aggregate For Concrete.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

(5/12/89)

703-2.02  Coarse Aggregate For Concrete.  In the first sentence, insert ", class B," after "AASHTO M 80".  (5/12/89)

703-2.03  Aggregate for Base.  Add the following to the list under the first paragraph:

Plastic Index      AASHTO T 90      6 max.

(5/7/91)

Special Provisions

703-2.03  Aggregate for Base.  Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

| Sieve Designation | Percent Passing by Weight Grading D-1 |
| --- | --- |
| 1-1/2 inch | - |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 50-79 |
| No. 4 | 35-58 |
| No. 8 | 20-47 |
| No. 40 | 8-23 |
| No. 200 | 0-6 |

703-2.04  Aggregate for Plant Mix Asphalt Pavement.  Delete this subsection in its entirety and substitute the following:

Coarse Aggregate.  Coarse aggregate (that material retained on the No. 4 Sieve) shall be crushed stone or crushed gravel and shall consist of sound, tough, durable rock of uniform quality.  All material shall be free from clay balls, vegetative matter or other deleterious matters.  Coarse aggregate shall not be coated with dirt or other finely divided mineral matter.  In addition, coarse aggregate shall meet the following requirements:

Percent of Wear			AASHTO T 96	45 max.

Degradation Value			ATM T-13		30 min.

Percent Sodium Sulfate loss	AASHTO T 104	9 max.

Percent Fracture			ATM T-4		            	single face						80 min.

double face						60 min.

Asphalt concrete aggregate shall not exceed 8 percent thin - elongated pieces as determined by ATM T-9.

Fine Aggregate.  Fine aggregate (passing the No. 4 sieve) shall meet the quality requirements of AASHTO M 29.

Blended Aggregate.  The several aggregate fractions for the mixture shall be sized, graded, and combined in such proportions that the resulting composite blend conforms to the grading requirements of Table 703-3.  Aggregate gradations shall be determined by ATM T-7, except when the sample is obtained by extraction, the size of the sample will be as listed in AASHTO T 164.

TABLE 703-3

ASPHALT CONCRETE AGGREGATE

Percent Passing by Weight

Sieve Designation	Type IA	Type IIA	Type III

1 inch		  100

3/4 inch		 80-90	   100

1/2 inch		 60-84	  80-90	   100

3/8 inch		 48-78	  60-87	  80-90

No. 4		 28-63	  36-72	  44-81

No. 8		 14-55	  19-62	  26-70

No. 16		  9-46	  10-52	  16-59

No. 30		  6-39	   7-45	   9-49

No. 50		  5-29	   5-34	   6-36

No. 100		  4-18	   4-21	   4-22

No. 200		3.0-7.0	 3.0-7.0	 3.0-7.0

703-2.07  Selected Material.  Add the following to Item 1., Selected Material Type A:  It shall have 30 to 55 percent maximum by weight of particles passing the No 4 sieve.

SECTION 705

JOINT MATERIALS

Standard Modifications

705-2.03  Bridge Seal.  Under Elastic Compression Seals, delete "Z1" in the line call-out specification.

(5/12/89)

SECTION 706

CONCRETE, CLAY, FIBER, AND PLASTIC PIPE

Special Provisions

706-2.07 Corrugated Polyethylene Pipe.  Delete in its entirety and substitute the following:  Corrugated polyethylene pipe shall conform to the following:

Culverts and Stormdrains       AASHTO M 294, Type S                                         (double wall)

Underdrains                    AASHTO M 252

(5/7/91)

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.14  Preformed Pavement Markings. Add the following to paragraph A. under Item 1., General Requirements:  The preformed ribbon shall consist of one solid piece of required width and length.  In solid stripe areas, the tape length shall, where possible, be a minimum of 100 feet.

712-2.15  Temporary Raised Pavement Markers.  Add the following:  The temporary raised pavement markers shall be installed utilizing an approved raised pavement marker flexible bituminous adhesive.

The color of the raised pavement markers shall conform to the color of the marking for which they supplement, substitute, or serve as a positioning guide.

(5/7/91)

712-2.16  Temporary Raised Pavement Markers for Short-Term Operations, Seal Coats, and Surface Treatments.  Add the following subsection:  The marker shall consist of an L-shaped polyurethane body with retroreflective tape on the top vertical section and with a self-adhesive base.  Both faces of the yellow marker and one face of the white marker shall be reflectorized.  The marker body shall be made from 0.060 inch minimum thick polyurethane; the vertical leg shall be approximately 2 inches high by 4 inches wide and the base approximately 1-1/8 inches wide.  The polyurethane body shall conform to Table 712-1.

The adhesive shall be factory-applied to the marker base, and made of a pressure-sensitive material, a minimum 1/8 inch thick and 3/4 inch wide, with release paper.

Where chip seals, slurry seals or tack coats are to be utilized after placement of the temporary raised pavement markers, the markers shall come with a protective cover made of clear flexible polyvinyl chloride.

The reflective tape shall be metalized polycarbonate microprism retroreflective material with acrylic backing or equal, a minimum 0.25 inch wide by 4 inches long, and provide the minimum optical performance shown in Table 712-2, for an observation angle of 0.2 degrees.

TABLE 712-1

| PROPERTY | RESULT | ASTM TEST METHOD |
| --- | --- | --- |
| Specific Gravity (minimum) | 1.19 | D 792 |
| Hardness | 80A | D 2240 |
| Tensile Strength (min, psi) | 4600 | D 412 |
| Ultimate Elongation (minimum, percent) | 330 | D 412 |
| Modulus at 300 percent (minimum, psi) | 1000 | D 412 |
| Stiffness @-20 degrees F (min, psi) @+72 degrees F (min, psi) | 1700 900 | D 1053 D 1053 |
| Compression Set 22 hrs at 70 degrees C (maximum, percent) | 65 | D 395 |
| Taber Abrasion CS17 wheel wt loss (mg/1000 cycles) | 3 | --- |

TABLE 712-2

| HORIZONTAL ENTRANCE ANGLE | SPECIFIC INTENSITY * White Yellow |  |
| --- | --- | --- |
| 0 degrees | 3.5 | 3.0 |
| 30 degrees | 2.7 | 1.7 |

* Candelas per footcandle of illumination at the reflector on a plane perpendicular to the incident light.

(5/7/91)

SECTION 714

PRESERVATIVES AND PRESERVATIVE TREATMENT

PROCESSES FOR WOOD MATERIALS

Special Provisions

714-2.01.  Add the following:  The following preservative treatments with corresponding retention values are allowed for the material being treated.

Preservative       Retention

Material             Standard       Treatment          Value

Timber Barrier       AWPA C2   Pentachlorophenol     0.50 pcf

(for use at the                       ACC            0.50 pcf

Drainage Control                      ACA            0.40 pcf

Structure)                           ACZA            0.40 pcf

CCA            0.40 pcf

SECTION 716

STRUCTURAL STEEL

Special Provisions

716-2.02  General Requirements.  Add the following:  Square and rectangular structural steel shall conform to the requirements of ASTM A-500, Grade B.

716-2.03  High Tensile Strength Bolts.  Add the following:  All high strength bolts shall be galvanized.

Galvanized tension control bolts will be considered equivalent to the bolts specified.

Standard Modifications

716-2.03  High Tensile Strength Bolts.  Add the following:  All bolts, nuts, and washers are to be marked with a symbol identifying the manufacturer as required in ASTM A325 Section 14, A490 Section 15, A563 Section 10.7 and 10.8, A194 Section 14, and F436 Section 14.  The supplier shall provide the symbol and address of each manufacturer for all the bolts, nuts, and washers supplied to the project.

The supplier's certification shall provide a corresponding lot number appearing on the shipping package and the certification.  The supplier's certification shall note when and where all testing was done, including the rotational-capacity tests indicated below, and include zinc thickness when galvanized bolts and nuts are used.

The maximum hardness for AASHTO M 164(A325) bolts shall be 33Rc.  The maximum tensile strength shall be 150ksi for bolts 1 inch or less in diameter and 120ksi for larger bolts.

Nuts shall be Grade 2H or DH for black or galvanized fasteners.  For galvanized fasteners the nuts shall be overtapped to the minimum amount required for the fastener assembly.  All nuts, bolts and washers shall have the manufacturers markings on them.

All galvanized nuts shall be lubricated with a lubricant containing a visible dye so a visual check can be made for the lubricant at the time of field installation.  Black bolts shall be "oily" to the touch when installed.  Weathered or rusted bolts shall be cleaned and re-lubricated prior to installation.

High-strength fasteners, black and galvanized, shall be subjected to a rotational-capacity test (AASHTO M 164, Section 8.5) and shall meet the following requirements:

1.	They shall go through two times the required number of turns (from snug tight conditions) indicated in the 1988 Interim AASHTO Bridge Specification, Table 10.17B, in a Skidmore-Wilhelm Calibrator, or equivalent tension measuring device, without stripping or failure.

2. 	During this test, the maximum recorded tension shall be equal to or greater than 1.15 times the Required Fastener Tension, AASHTO Table 10.17A.

3.	The measured torque to produce the Required Fastener Tension shall not exceed the value obtained by the following equation:

Torque = 0.25 PD

Where:  Torque = Measured Torque (Foot-Pounds)

P      = Measured Bolt Tension (Pounds)

D      = Nominal Diameter (Feet)

Proof load tests (ASTM F 606 Method 1) are required for the bolts.  Wedge tests of full size bolts are required in accordance with Section 8.3 of AASHTO M 164.  Galvanized bolts shall be wedge tested after galvanizing.  Proof load tests (AASHTO M 291) are required for the nuts.  The proof load tests for nuts to be used with galvanized bolts shall be performed after galvanizing, overtapping and lubricating.

All galvanized nuts shall be lubricated in accordance with ASTM A563 Section 4.8.  In addition the name, method of application, and dilution of the lubrication applied to the nuts shall be provided with the documentation.

Section 7.4 of ASTM A563 shall be deleted and Section 7.5 changed to read as shown below.  These requirements also apply to 2H nuts covered under ASTM A194.

7.5 Nuts to be used on bolts mechanically zinc coated or on bolts hot-dip zinc-coated, shall be tapped oversize by a diametral amount sufficient to permit assembly on the coated bolt thread, unless other requirements are specified in the inquiry or purchase order.

(5/12/89)

SECTION 720

ELASTOMERIC PADS

Special Provisions

720-2.01.  Delete this subsection in its entirety and substitute the following:  Elastomeric bridge bearing pad shall conform to the requirements of AASHTO M 251-90 with the following revisions:

4.	MATERIALS.

4.1  Properties of the Elastomer.  Delete the first sentence and substitute the following:  The elastomeric compound used in the construction of the bearings shall contain only virgin natural polyisoprene (natural rubber) as the raw polymer; neoprene shall not be used.  Properties and requirements elsewhere in AASHTO M251-90 pertaining solely to polychloroprene (neoprene) shall not be applicable.

Amend Table 1 as follows:  Replace the expression "-40F (-40C)" with "-67F (-55C)" in the row labelled "Brittleness" under the column heading "Test Requirements."

5.	FABRICATION.

Add the following paragraph:

5.5.  Pads over three-quarters of an inch in thickness shall be laminated and shall consist of alternate laminations of elastomer and metal reinforcements.  The outside laminations shall be metal.  Laminations of elastomer shall be 1/2 inch +1/8 inch in thickness.

8.	BEARING TESTS AND ACCEPTABLE CRITERIA

8.2.2.  Delete Note 1 in its entirety and add the following paragraph:  The elastomer shall also be tested for ozone resistance under ASTM D1149, method A at 100 degrees F, 20 percent strain, partial pressure of ozone - 50 MPa, and 100 hours.  It shall show no cracks.

8.2.4.  Delete in its entirety and substitute the following:  A minimum of one pad per lot shall be tested for bond strength as follows:

Steel Laminations - ASTM D429 Method B - 40 lb/in., minimum.

Fabric Laminations - California Test No. 663 - 40 lb/in., minimum.

8.2.5.  Delete the word "Optional."

9.	TESTING

9.1.  Delete the word "Optional."

(4/7/92)R152

Special Provisions

720-2.02  Manufacturing Requirements.  Add the following new subsection:  Laminations of elastomer shall be 1/2-inch +1/8-inch in thickness.

The elastomeric pad shall have a virgin (unfilled) polytetrafluorethylene (TFE) sheet, 1/32 inch in thickness, bonded to the top surface.

The TFE sheet shall conform to the following requirements:

| Property | Value |
| --- | --- |
| Tensile Strength | 2000 psi, min. |
| Tensile Elongation | 200 percent, min. |
| Hardness | 50-60 Shore D |
| Coefficient of Friction (TFE against stainless steel) | 0.05 (for loads greater than 500 psi and speeds less than 1 foot/minute |
| Compressive Strength (0.2% Offset) | 1800 psi, min. |
| Shear Strength between TFE and Elastomer | Greater than the shear strength of either TFE or elastomer |

SECTION 724

SEED

Standard Modifications

724-2.02  Materials.   Add the following to Table 724-1:

| Seed Type | Germination Period | Percent Purity | Percent Germination | Percent Sproutable Seed |
| --- | --- | --- | --- | --- |
| Bering Hairgrass | 14 days | 95 | 75 | 71 |

(5/12/89)

SECTION 726

TOPSOIL

Standard Modifications

726-2.01  Topsoil.  In the second paragraph, change "not less than 1%" to read "not less than 3%".  (5/12/89)

SECTION 729

GEOTEXTILES

Special Provisions

Delete this Section in its entirety and substitute the following:

729-2.01  Embankment Separation and Reinforcement.

1.	Fibers used in the manufacturer of geotextiles, and the threads used in joining geotextiles by sewing, shall consist of long chain synthetic polymers, composed of at least 85 percent by weight polyolefins, or polyesters.  The geotextile shall be formed into a stable network such that the filaments or yarns retain their relative position to each other.  Both the geotextile and threads shall be resistant to chemical attack, mildew, and rot.

2.	Nonwoven geotextile may be formed by the needle-punched, spun-bonded or heat-bonded process.

3.	Woven geotextile shall be woven into a uniform pattern with distinct and measureable openings.  Edges of the cloth shall be selvaged to prevent the outer yarn from pulling away from the cloth.  The fabric shall be free from detrimental defects.

4.	The geotextile supplied shall meet the requirements listed in Table 729-1 for the type specified.

5.	The Contractor shall submit certification that the geotextile supplied meets the above requirements before it is used on the project.

Table 729-1

GEOTEXTILE REQUIREMENTS FOR

EMBANKMENT SEPARATION AND REINFORCEMENT

| Geotextile Property | Test Method (ASTM) | Separation |  | Railroad Ballast |
| --- | --- | --- | --- | --- |
| Grab Elongation, % at breaking load | D-4632 | <50 | >50 | 20 max. |
| Grab Tensile Load, lbs., min. | D-4632 | 175 | 105 | 225 |
| Bursting Strength, psi., min. | D-3786 | N/A | N/A | 450 |
| Trapezoid Tearing Strength, lbs., min. | D-4533 | 50 | 40 | 115 |
| Puncture Resistance, lbs., min. | D-4833 | 70 | 40 | 150 |
| Water Permittivity, 1/sec., min. | D-4491 | 0.04 | 0.30 | 0.02 |
| Apparent Opening Size, mm., max. | D-4751 | 0.30 | 0.21 | 0.21 |
| Ultraviolet Degradation at 500 hour exposure, % strength retained | D-4355 | 70 | 70 | 70 |
| Geotextile Acceptance, pass or fail | D-4759 | Pass | Pass | Pass |

NOTES:                                                   1.	Separation geotextile supplied may have either less than, or greater than 50% elongation measured at breaking load in the Grab Tensile Test (ASTM D-4632).

2.	Geotextile Property Values = Minimum average roll values at a 95% confidence level in the weaker principal direction.

3.	0.21 mm. = US Standard Sieve Size 70.

4.	0.30 mm. = US Standard Sieve Size 50.

5.	0.85 mm. = US Standard Sieve Size 20.

729-2.02 Subsurface Drainage and Riprap Liner.

1.	Fibers used in the manufacture of geotextiles, and the threads used in joining geotextiles by sewing, shall consist of long chain synthetic polymers, composed of at least 85 percent by weight polyolefins, or polyesters.  The geotextile shall be formed into a stable network such that the filaments or yarns retain their relative position to each other.  Both the geotextile and threads shall be resistant to chemical attack, mildew, and rot.

2.	Nonwoven geotextile may be formed by the needle-punched, spun-bonded, or heat-bonded process.

3.	Woven geotextile shall be woven into a uniform pattern with distinct and measureable openings.  Edges of the cloth shall be selvaged to prevent the outer yarn from pulling away from the cloth.  The fabric shall be free from detrimental defects.

4.	The geotextile supplied shall meet the requirements listed in Table 729-2 for the type specified.

5.	The Contractor shall submit certification that the geotextile supplied meets the above requirements before it is used on the project.

TABLE 729-2

GEOTEXTILE REQUIREMENTS FOR

SUBSURFACE DRAINAGE AND RIPRAP LINER

| Geotextile Property | Test Method (ASTM) | Subsurface Drainage | Riprap Liner |  |
| --- | --- | --- | --- | --- |
|  |  |  | Unprotected | Protected |
| Grab Elongation, % at breaking load | D-4632 | 15-100 | 15-80 | 15-80 |
| Grab Tensile Load, lbs., min. | D-4632 | 90 | 200 | 100 |
| Bursting Strength, psi., min. | D-3786 | 125 | 350 | 200 |
| Water Permittivity, 1/sec., min. | D-4491 | 0.8 | 0.5 | 0.5 |
| Apparent Opening Size, mm., max. | D-4751 | 0.212 | 0.600 | 0.600 |
| Ultraviolet Degradation at 500 hour exposure, % strength retained, min. | D-4355 | 70 | 70 | 70 |
| Geotextile Acceptance, pass or fail | D-4759 | Pass | Pass | Pass |

NOTES:                                                   1.	Geotextile Property Values = Minimum average roll values at a 95% confidence level in the weaker principal direction.

2.	0.212 mm. = US Standard Sieve Size 70.

3.	0.600 mm. = US Standard Sieve Size 30.

729-2.04 Temporary Silt Fence.  The geotextile supplied shall meet the physical and mechanical properties listed in Table 729-4.

Table 729-4

GEOTEXTILE REQUIREMENTS FOR

TEMPORARY SILT FENCE

| Geotextile Property | Test Method (ASTM) | Fence Supported Requirements | Self-supported Requirements |
| --- | --- | --- | --- |
| Grab Tensile Strength lbs, min. | D-4632 | 90 | 90 |
| Elongation at 50% minimum tensile strength (45 lb) % max | D-4632 | N/A | 50 |
| Water Permittivity 1/sec, min. | D-4491 | 0.01 | 0.01 |
| Apparent Opening Size mm., max. | D-4751 | 0.84 | 0.84 |
| Ultraviolet Degradation at 500 hour exposure, min % strength retained | D-4355 | 70 | 70 |
| Geotextile Acceptance Pass or Fail | D-4759 | Pass | Pass |

Notes:

1.	Geotextile Property Value = Minimum average roll values 95% confidence level in the weaker principal direction.

2.	0.84 mm. = U.S. Standard Sieve Size 20

729-2.05  Impermeable Membrane.

1.	The impermeable membrane shall be composed of a calendered polyvinyl chloride (PVC) sheeting material factory-bonded into a single panel meeting the physical and mechanical properties contained in Table 729-5.

2.	PVC Sheeting shall be formulated and manufactured from 100 percent virgin polyvinyl chloride resin and be specifically compounded for use in hydraulic structures.  Reprocessed or reground materials shall not be used.  No factory set up or trim materials that are foreign to the virgin formulation shall be used.  Only first quality phthalate and/or phosphate plasticizers shall be used.  The use of water soluble formulation ingredients is prohibited.

3.	The compound must contain a biocide at a viable formulation level.  There shall not be any unmixed formulation ingredients.  The sheeting shall contain no deep gas checks, no surface divots, no windows, and shall not exhibit cold flow.  It must have good surface quality and be free of pinholes and blisters.

4.	Individual calendered widths of PVC shall be factory fabricated into large panels so as to minimize field seaming during installation.  Factory fabricated seams shall have a minimum of 1/2-inch nominal width and shall meet at a minimum, 80 percent of the unseamed strength properties.  Field seams shall have a strength of at least 80 percent of the specified sheet strength and shall be performed in accordance with the manufacturer's recommendations.

5.	Damaged impermeable membrane materials shall be mended in such a way that the strength and hydraulic properties of the repaired area meet or exceed the requirements indicated for non-damaged impermeable membrane.  All repairs shall conform to the manufacturer's recommended procedures.

6.	Certification of impermeable membrane materials shall be based on minimum average roll values at a 95 percent confidence level.  The manufacturer's certification shall be furnished to the Engineer prior to installation of the impermeable membrane.

Table 729-5

IMPERMEABLE MEMBRANE REQUIREMENTS

| Membrane Property | Test Method | Requirement |
| --- | --- | --- |
| Thickness, mils, min. (Nominal + 5 percent) | ASTM D-1593 | 30 |
| Tensile Strength lbs/in, min. | ASTM D-882 | 69 |
| Elongation at Break percent, min. | ASTM D-882 | 350 |
| Tear Resistance lbs, min. | ASTM D-1004 | 9 |
| Low Temperature Strength | ASTM D-1790 | Pass at -20oF |
| Permeability cm/sec, max. | AASHTO M-288 | 0.000001 |

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04  Sign Posts. Delete Item 4., "Multi-directional Breakaway Load Concentration Coupler Base Assemblies and Coupler Hinge Plate", and substitute the following:

4.	Wide Flange Posts.

a.	Steel for wide flange posts shall conform to AASHTO M 183.

b.	Post sizes shall be as designated on the plans.

c.	Posts shall be hot dip galvanized in a manner conforming to AASHTO M 111 after fabrication.  Any cutting of metal posts after hot dip galvanizing shall be accomplished with minimum damage to the zinc coating and all exposed surfaces shall be protected by treating the exposed area in the same manner as if it were abraded or damaged.

d.	Galvanized surfaces that are abraded or damaged at any time after the application of the zinc coating shall be repaired in accordance with the applicable provisions of AASHTO M 36.

(5/7/91)

Add the following Section:

SECTION 731

ELASTOMERIC CONCRETE

Special Provisions

731-2.01  Elastomeric Concrete.  Elastomeric concrete shall be a two-part urethane based material with suitable reinforcing agents to provide a product which mixes rapidly, flows readily, has good adherence to asphalt, concrete, and steel, requires no external heat, and cures to a finished product which can accept traffic within one hour.  It shall conform to the physical and performance properties shown in Table 731-1.  The elastomeric binder shall conform to the physical and performance properties shown in Table 731-2.

Table 731-1

PHYSICAL AND PERFORMANCE PROPERTIES OF ELASTOMERIC CONCRETE

| Property | Test Method | Requirement |
| --- | --- | --- |
| Tensile Properties - Tensile Strength, psi - Elongation, percent - Hardness, Durometer D | Note 1 Note 1 ASTM D 2240 | 500 min. 30 min. 45 min. |
| Compression Properties - Compressive stress, psi @ 5% deflection @10% deflection @20% deflection - Compression Set B, percent after 22 hrs @ 158oF - Compressive yield strength, psi (4" by 8" cylinder) - Resilience, percent @ 5% deflection @7.5% deflection | ASTM D 695 Note 2 ASTM D 395 - Note 3 | 800 min. 1200 min. 3500 min. 60 min. 10,000 min. 90 min. 90 min. |
| Impact Properties - Ball Drop, ft-lb, no cracks @ 32oF @-20oF after 14 days @158oF | Note 4 | >10 >10 >10 |
| Adhesion Properties - Dry Bond Strength to Concrete, psi - Wet Bond Strength to Concrete, psi Steel Shear, psi Steel Tension, psi Asphalt, psi | Note 5(dry) Note 5 | 450 min. 275 min. 750 min. 700 min. >internal asphalt strength |
| Fluid Immersion Properties - Percent Weight Change After: 70 hrs @158oF in ASTM #3 oil 70 hrs @158oF in H2O 70 hrs @ RT in unleaded gasoline 70 hrs @ RT in Jet Fuel | ASTM D 471 | 15 min 12 max 20 max 20 max |
| Flexure and Fatigue Test*, cycles | special | 1 million |

*	Test performed by Port Authority of New York and New Jersey.

Notes:

1.	Test specimen one inch thickness, two inch cross section, fourteen inch length, five inch benchmark.  Test performed at Toledo University (Concrete Testing Laboratory).

2.	Test specimen is a cast two inch cube.  (Machine crosshead speed is 0.05 inch per minute.)  Specimen is loaded until ultimate strength, if any, is reached.  Compressive strength is maximum load carried by the specimen divided by original cross-section area.  (A compressometer is used to make the measurement.)

3.	Test specimen is a cast two inch cube.  Specimen compressed to desired amount.  (Machine crosshead speed is 0.05 inch per minute.)  Five minutes after load is removed the specimen thickness is measured.  Percent recovery is determined as follows:

% Deflection + final thickness - initial thickness

Deflection

4.	Test specimen is a cast disk 2.50 inches in diameter and 0.375 inches thick.  Specimens are conditioned four hours at test temperatures.  A one-pound steel ball is dropped onto the center of the specimen through a plastic guiding tube from an initial height of five feet.  The drop height is increased by one-half foot intervals until specimen cracks.  (Drop is made within ten seconds after removal of specimen from the exposure condition.)  Average of four test specimens.

5.	Elastomeric concrete is cast against a mortar-briquette half (briquette conforms to ASTM C190).  Briquette is sawed in half so that cut surface area equals approximately one square inch.  Surface is sandblasted (36 mesh).  Briquette is placed in mold and elastomeric concrete is cast against it.  Specimen is submerged in water (seven days @ RT).  Using the Riehle Briquette Tester, specimen failure is considered to occur at either the bond interface or within one of the two materials.

Table 731-2

PHYSICAL AND PERFORMANCE PROPERTIES

OF ELASTOMERIC BINDER

| Property | Test Method | Requirement |
| --- | --- | --- |
| Tensile Properties, (original) - Tensile Strength, psi - Elongation, percent - Hardness, Durometer - Tear Strength, pli - Tensile Shear Strength, psi | ASTM D 638 ASTM D 638 ASTM D 2240 ASTM D 624 ASTM D 1002 (Note 1) | 2500 min. 300 min. 90A,40D 200 min. 600 min. |
| Tensile Properties, (after oven aging for 7 days @ 158oF) - Tensile Strength, psi - Elongation, percent - Hardness, Durometer | ASTM D573 D638 D638 D2230 | 2500 min. 250 min. 95A,43D |
| Compression Properties - Compression Set B, percent after 22 hrs @158oF | ASTM D 395 | 50 max. |
| Impact Properties - Ball Drop, ft-lb, no cracks @ 32oF @-20oF after 14 days @158oF - Brittle Point, oF | Note 2 ASTM D 746 | >10 >10 >10 -30 |
| Fluid Immersion Properties - Percent Weight Change After: 70 hrs @158oF in ASTM #3 oil 70 hrs @158oF in H2O 70 hrs @ RT in unleaded gasoline 70 hrs @ RT in Jet Fuel | ASTM D 471 | 10 min. 10 max. 60 max. 10 max. |

Notes:

1.	Steel specimens (1" X 8" X 0.064") are blasted (36 mesh) for one-half inch.  This overlap area is cleaned with solvent.  Binder is applied (single coat) to the lap surfaces and the two are bonded together under moderate pressure (2 psi).  The assembly is cured at the specified conditions.  The lap area is measured and the assembly is subjected to tensile loading (0.05 inch per minute crosshead speed).  The tensile shear strength (psi) is derived from the maximum tensile load and the lap area.

2.	Test specimen is a cast disk 2.50 inches in diameter and 0.375 inches thick.  Specimens are conditioned four hours at test temperatures.  A one-pound steel ball is dropped onto the center of the specimen through a plastic guiding tube from an initial height of five feet.  The drop height is increased by one-half foot intervals until specimen cracks.  (Drop is made within ten seconds after removal of specimen from the exposure condition.)  Average of four test specimens.

Add the following Section:

SECTION 740

RAILROAD TRACKWORK MATERIALS

Special Provisions

740-1.01  Description.  This work shall consist of furnishing and placing ballast in reasonable conformance with the plans.

740-2.01  Ballast.  Prepared ballast shall be crushed stone, or crushed gravel composed of hard, strong

and durable particles, free from injurious amounts of deleterious substances and conforming to Tables 740-1 and 740-2:

Table 740-1

Gradation Tests

| Description | Test Method | Requirement |
| --- | --- | --- |
| Sampling Aggregates | ASTM D75 & ASTM C702 | - |
| Sieves with Square Openings | ASTM E11 | - |
| Sieve Analysis | ASTM C136 | see below |
| Materials Passing No. 200 | ASTM C117 | see below |

Prepared ballast shall conform to the following requirements for grading:

| Sieve Designation | Percent Passing by Weight |
| --- | --- |
| 2 inch | 100 |
| 1-1/2 inch | 90-100 |
| 1 inch | 20-55 |
| 3/4 inch | 0-15 |
| 3/8 inch | 0-5 |
| No. 200 sieve | 0-1 |

Table 740-2

Material Quality Tests

| Description | Test Method | Requirement |
| --- | --- | --- |
| Bulk Specific Gravity | ASTM C127 | 2.60 min. |
| Absorption | ASTM C127 | 1.0 max. |
| Magnesium Sulfate Soundness | ASTM C88 (five cycles) | 3.0 % max. |
| Clay Lumps & Friable Particles | ASTM C142 | 0.5 % max. |
| Flat and/or Elongated Particles | USACE CRD-C119 | 5.0 % max. |
| Degradation (LA Abrasion) | ASTM C535 | 45 max. |
| Fractured Particles Test | see below | 85% min. |

The Fractured Particles Test is as follows:

A representative sample is obtained and sized using current ASTM methods of test.  From each coarse aggregate fraction representing five percent or more of the submitted sample, split a representative portion into samples, of within 10 percent of the weight specified below.

| SIEVE PASSING | SIEVE PASSING | WEIGHT IN POUNDS + 10 PERCENT |
| --- | --- | --- |
| 2 inch | 1-1/2 inch | 13.00 |
| 1-1/2 inch | 1 inch | 6.50 |
| 1 inch | 3/4 inch | 3.50 |
| 3/4 inch | 1/2 inch | 2.25 |
| 1/2 inch | 3/8 inch | 1.00 |
| 3/8 inch | No. 4 | 0.75 |

Each sample shall then be separated into fractured and non fractured particles according to the following criteria.

A fractured particle shall be particle with three or more fractured faces.  Each fractured face on the fractured particle must have a freshly exposed rock surface with a maximum dimension of at least one third the maximum particle dimension and a minimum dimension of at least one quarter of the maximum particle dimension.  The included angle formed by the intersection of the average planes of adjoining fractured faces must be less than 135 degrees for each of the faces to be considered as separate fractured faces.

Particles which do not meet the above criterion will be classified as non fractured faces.

The fractured particles for each sample will be calculated as a percentage by the following formula:

Fractured Particles = Weight of fractured particles x 100

Original Weight

740-3.01  Construction Requirements.  Ballast shall be placed at the locations shown on the plans in strict accordance with accepted railroad practice.

740-4.01  Method of Measurement.  Ballast will not be measured for payment.

740-5.01  Basis of Payment.  Payment for Ballast will not be made separately but will be subsidiary to Item 617(1), Railroad Crossing.

APPENDIX A

PERMITS

APPENDIX B

TEST PROCEDURE ATM T-19M

FOR DETERMINATION OF OUTLIER TEST RESULTS

APPENDIX C

BEST MANAGEMENT PRACTICES

APPENDIX D

CONSTRUCTION SURVEYING

REQUIREMENTS