SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available as follows:

Copies and reproduction information may be obtained from the Plans Room (907) 266-1798 for the following:

- Computations

- Cross Sections

- Geotechnical Report, Glenn Highway,

Eklutna-Parks, Phase 1-A

- Foundation Report, Knik River Bridge No.

1885 and Matanuska River Bridge No. 1889

Glenn Highway, Eklutna to Parks Highway

- Glenn Highway Eklutna to Parks Highway

Knik River Bridge No. 1885

Matanuska River Bridge No. 1889

Hydraulics Report; August, 1990

An Environmental Impact Statement addressing environmental concerns and commitments has been approved and is available for review in the office of the Regional Environmental Coordinator, 4111 Aviation Avenue, Anchorage, (907) 266-1508.

PART 4

STANDARD MODIFICATIONS and

SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS FOR HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Special Provisions

101-1.27  Holidays.  Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third Monday in January

3.	Presidents Day - Third Monday in February

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  Qualification of Bidders.  Delete the second paragraph.  (5/12/89)

Special Provisions

102-1.01  Qualification of Bidders.  Add the following:  The bidder, by signing the proposal and under penalty of perjury under the laws of the United States, certifies that, except as may be noted on the proposal, the bidding firm or any person associated therewith is not currently under suspension, debarment, voluntary exclusion, or determination of ineligibility by any federal agency; has not been suspended, debarred, voluntarily excluded or determined ineligible by any federal agency within the past 3 years; does not have a proposed debarment pending; and has not been indicted, convicted, or had a civil judgement rendered against (it) by a court of competent jurisdiction in any matter involving fraud or official misconduct within the past 3 years.

Exceptions to the above shall be noted by the bidder on the proposal or on an attachment thereto.

Exceptions will not necessarily result in denial of award, but will be considered in determining bidder responsibility.  For any exception noted, indicate to whom it applies, initiating agency, and dates of action.  Providing false information may result in criminal prosecution or administrative sanctions.

(3/18/88)

102-1.06  Preparation of Proposal.  Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

102-1.07  Non-Responsive Proposals.  Delete the second paragraph under Item 3.

(2/07/89)

Standard Modifications

102-1.07  Non-Responsive Proposals.  Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)

102-1.12  Addenda Requirements.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  Consideration of Proposals.  Add the following:  The apparent low bidder shall, within 5 working days following the bid opening, submit either a list of all firms with which the prime Contractor intends to execute subcontracts for the performance of the contract or a statement that the bidder intends to perform the work without subcontractors.  The list shall include the following information for each proposed subcontractor:

1.	name,

2.	business address,

3.	Alaska business license number,

4.	Contractor's registration number,

5.	the work to be performed, and

6.	the approximate dollar amount of the work to be performed.

If the apparent low bidder fails to submit either a list of subcontractors or a statement that the bidder intends to perform the work without subcontractors, the apparent low bidder will be found not to be a responsible bidder and may be required to forfeit the bid security.  The Department will then consider the next lowest bidder for the award of the contract.

If the apparent low bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess  of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this Subsection.

If a contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department; or

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18;

2.	files for bankruptcy or becomes insolvent;

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith;

4.	fails to obtain bonding;

5.	fails to obtain insurance acceptable to the Department;

6.	fails to perform the contract with the bidder involving work for which the subcontractor was  listed;

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements;

8.	refuses to agree or abide with the bidder's labor agreement; or

9.	is determined by the Contracting Officer not to be responsible.

(7/1/90)

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  Changes.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)

Special Provisions

104-1.02  Changes.  Delete the first three paragraphs and substitute the following:  The Engineer reserves the right to make, in writing, at any time during the work, such changes in quantities and such alterations in the work as are necessary to satisfactorily complete the project.  Such changes in quantities and alterations shall not invalidate the contract nor release the surety, and the Contractor agrees to perform the work as altered.

If the alterations or changes in quantities significantly change the character of the work under the contract, whether or not changed by any such different quantities or alterations, an adjustment, excluding loss of anticipated profits, will be made to the contract.  The basis for the adjustment shall be agreed upon prior to the performance of the work.  If a basis cannot be agreed upon, then an adjustment will be made either for or against the Contractor in such amount as the Engineer may determine to be fair and equitable.

If the alterations or changes in quantities do not significantly change the character of the work to be performed under the contract, the altered work will be paid for as provided elsewhere in the contract.

The term "significant change" shall be construed to apply only to the following circumstances:

1.	When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction, or

2.	When a major item of work, as defined elsewhere in the contract, is increased in excess of 125 percent or decreased below 75 percent of the original contract quantity.  Any allowance for an increase in quantity shall apply only to that portion in excess of 125 percent of original contract item quantity, or in case of a decrease below 75 percent, to the actual amount of work performed.

(4/13/89)

Add the following:  Due to the complexity of developing the Environmental document, commitments to resource agencies, acquisition of rights of way, and the integration of such into plans and specifications, no value engineering proposals will be considered for this project.

104-1.03  Differing Site Conditions.  Delete in its entirety and substitute the following:  During the progress of the work, if subsurface or latent physical conditions are encountered at the site differing materially from those indicated in the contract or if unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the work provided for in the contract, are encountered at the site, the party discovering such conditions shall promptly notify the other party in writing of the specific differing conditions before they are disturbed and before the affected work is performed.

Upon written notification, the Engineer will investigate the conditions, and if he determines that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any work under the contract, an adjustment, excluding loss of anticipated profits, will be made and the contract modified in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment which results in a benefit to the Contractor will be allowed unless the Contractor has provided the required written notice.

(4/13/89)

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  Authority of the Engineer.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02, Changes.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)

Special Provisions

105-1.06  Cooperation With Utilities.  Add the following:  The Contractor shall request locates from all the Utilities having facilities in the area.  Their telephone numbers are as follows:

DOT/PF Maintenance & Operations (Palmer)  266-1584

ENSTAR Natural Gas Company (Wasilla)      376-7979

Matanuska Electric Association, Inc.      745-3231

Matanuska Telephone Association, Inc.     745-3121

All existing utilities shall remain in service.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

105-1.07  Cooperation Between Contractors.  Add the following:  Additional contracts let by the Department are within the project limits and portions of the work under these contracts will be performed concurrently with this project.  The additional contracts are as follows:

1.	Glenn Highway, Eklutna to Parks, Phase 1-A

2.	Glenn Highway, Eklutna to Parks, Phase 1-C

The Contractor shall coordinate his traffic control, construction, and material hauling operations with the prime contractors of the above contracts so as to minimize impact on the travelling public, and to minimize conflicts with the work being performed under the other contracts.

105-1.12  Load Restrictions.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless allowed for use by an approved Traffic Control Plan.  (2/7/89)

Delete the second paragraph in its entirety and substitute the following:  The load restrictions set for the above apply to all bridges, base course, and surface course that are scheduled to be a part of the finished work.

The Contractor will be allowed to transport the steel girder segments assembled in pairs, if desired.  If the Contractor elects to transport the girders assembled in pairs, overload and oversize permits will be issued for such a move on the highway between the Port of Anchorage and the job site.  No overload may cross the Ship Creek Bridge, Bridge No. 417.  Any permit will be subject to the following limitations:

Maximum Single Axle Load                30,000 lbs.

Maximum Tandem Axle Load                50,000 lbs.

Maximum Triple Axle Load                70,000 lbs.

Maximum Four Axle Load                  90,000 lbs.

Minimum Spacing of Axle Groups          20 ft. c.to c.

axle groups

Minimum Spacing within Group            4 ft. c.to c.

axles

Maximum Vehicle Speed on any Structure  3 mph

The maximum axle loads tabulated above are applicable to hauling equipment with fixed axles only; variable load suspension (VLS) axles shall not be considered part of an axle group for purposes of this specification.

Vehicles shall cross structures at a constant speed with load centered on roadway and no shifting of gears.  Whenever the load exceeds 80,000 lbs., the vehicle shall be preceded by a walking flagman when crossing structures.

This overload allowance does not apply to the transportation of construction materials other than precast prestressed concrete or steel girder sections.

All overload permits are subject to seasonal load restrictions.

Routing shall be as prescribed by the permit officer, reached at (800)478-7636 or (907) 345-7750.

Alternate axle configurations and loading which may reduce the overload movement restrictions and conditions are subject to individual analysis.

105-1.15  Project Completion.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work scheduled under subsection 618-3.04, Maintenance of Seeded Areas, and subsection 504-3.03 Painting, paragraph 3.h., Field Painting, a letter of project completion will be issued by the Engineer.

105-1.17  Claims for Adjustment and Disputes.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (12/26/90)

105-1.17  Claims for Adjustments and Disputes.  Add the following:  Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/29/87)

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  Source of Supply and Quality Requirements.  Add the following:  All steel products which are to be incorporated into the work shall be produced in the United States except that minor amounts of steel products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel products into the project.

(11/9/84)

106-1.02  Local Material Sources.  Under Item 1., General, add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)

Under Item 1., General, add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement will be given to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)

All material sources on or off the project shall be operated in accordance with the applicable, enforceable provisions and standards of the Alaska Coastal Management Program and all federal and state laws pertaining thereto.

Add the following to Item 5.:  Upon completion of work at any material source, on or off the project, the Contractor shall restore the slopes to a stable and safe condition to preclude erosion, water contamination and hazard to humans.

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01  Laws to be Observed.  Add the following:  Specific Equal Employment Opportunity Responsibilities of Federal-Aid Construction Contractors.

1.	General

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required

by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form 25D-55) and these Special Provisions which are imposed pursuant to Section 140 of Title 23, U.S.C., as established by Section 22 of the Federal-Aid Highway Act of 1968.  The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the equal employment opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State highway agencies and the Federal Government in carrying out equal employment opportunity obligations and in their review of his/her activities under the contract.

c.	The Contractor and all his/her subcontractors holding subcontracts not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of equal employment opportunity:  (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as Contractors and subcontractors.)  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.

2.	Equal Employment Opportunity Policy

The Contractor will accept as his operating policy the following statement which is designed to further the provision of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include:  employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprentice-ship and/or on-the-job training.

3.	Equal Employment Opportunity Officer

The Contractor will designate and make known to the Engineer and equal employment opportunity officer (hereinafter referred to as the EEO Officer) who will have the responsibility for and must be capable of effectively administering and promoting an active Contractor program of equal employment opportunity and who must be assigned adequate authority and responsibility to do so.

4.	Dissemination of Policy

a.	All members of the Contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the Contractor's equal employment opportunity policy and contractual responsibilities to provide equal employment opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

(1)	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the Contractor's equal employment opportunity policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor's equal employment opportunity obligations within thirty days following their reporting for duty with the Contractor.

(3)	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the Contractor's procedures for locating and hiring minority group employees.

b.	In order to make the Contractor's equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

(1)	Notices and posters setting forth the Contractor's equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The Contractor's equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

5.	Recruitment

a.	When advertising for employees, the Contractor will include in all advertisements for employees the notation:  "An Equal Opportunity Employer."  All such advertisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority group applicants, including, but not limited to, State employment agencies, schools, colleges and minority group organizations.  To meet this requirement, the Contractor will, through his EEO Officer, identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority group applicants may be referred to the Contractor for employment consideration.

In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor's compliance with equal employment opportunity contract provisions.  (The U.S. Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or women, or obligates the Contractor to do the same, such implementation violates Executive Order 11246, as amended.)

c.	The Contractor will encourage his present employees to refer minority group applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures with regard to referring minority group applicants will be discussed with employees.

6.	Personnel Actions

Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The Contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The Contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with his obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the Contractor will inform every complainant of all of his avenues of appeal.

7.	Training and Promotion

a.	The Contractor will assist in locating, qualifying, and increasing the skills of minority group and women employees, and applicants for employment.

b.	Consistent with the Contractor's work force requirements and as permissible under Federal and State regulations, the Contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.  In the event the Training Special Provision is provided under this contract, this subparagraph will be superseded as indicated.

c.	The Contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.	The Contractor will periodically review the training and promotion potential of minority group and women employees and will encourage eligible employees to apply for such training and promotion.

8.	Unions

If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and female employees.  Actions by the Contractor either directly or through a Contractor's association acting as agent will include the procedures set forth below:

a.	The Contractor will use best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

b.	The Contractor will use best efforts to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The Contractor is to obtain information as to the referral practices and policies of the labor union except that the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the Contractor, the Contractor shall so certify to the State highway department and shall set forth what efforts have been made to obtain such information.

d.	In the event the union is unable to provide the Contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the Contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minority group persons and women.  (The U.S. Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees.)  In the event the union referral practice prevents the Contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such Contractor shall immediately notify the State highway agency.

9.	Subcontracting

a.	The Contractor will use his best efforts to solicit bids from and to utilize minority group subcontractors or subcontractors with meaningful minority group and female representation among their employees.  Contractors shall obtain lists of minority-owned construction firms from State highway agency personnel.

b.	The Contractor will use his best efforts to ensure subcontractor compliance with their equal employment opportunity obligations.

10.	Records and Reports

a.	The Contractor will keep such records as are necessary to determine compliance with the Contractor's equal employment opportunity obligations.  The records kept by the Contractor will be designed to indicate:

(1)	the number of minority and nonminority group members and women employed in each work classification on the project,

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to Contractors who rely in whole or in part on unions as a source of their work force),

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority group subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such records must be retained for a period of three years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the State highway agency and the Federal Highway Administration.

c.	The Contractor will submit an annual report to the State highway agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form PR 1391.  If on-the-job training is being required by "Training Special Provision", the Contractor will be required to furnish State of Alaska Form 25A312.

107-1.11  Protection and Restoration of Property and Landscape.  Add the following to the third paragraph:  When working near designated wetlands the Contractor shall place no fill nor operate equipment outside the slope limits.

The Contractor shall not excavate, nor use for fill, any material containing hazardous substances or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected of containing hazardous substances or petroleum fuels.  Hazardous substances are any element, compound, mixture, solution or substance designated pursuant to the Comprehensive Environmental Response, Compensation, and Liability Act of 1980 (CERCLA).  Hazardous substances include any hazardous wastes having the characteristics of ignitability, corrosivity, reactivity, or extraction procedure toxicity.

The Department has further environmental concerns regarding new material sources and waste disposal sites that the Contractor may develop for this project.  The Contractor is advised that new material sources and waste disposal sites on or off the project shall be developed and operated in accordance with the applicable federal laws, including but not limited to:

-Endangered Species Act,

-Fish and Wildlife Coordination Act,

-Migratory Bird Treaty Act.

Upon identification of potential material sources and waste disposal sites the Contractor shall submit a list of these sites to the Engineer.  Negative environmental impacts due to location, development and/or operation of new material sources and new waste disposal sites may constitute a basis for rejection of the site for use by the Contractor on this project.

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, other than Loberg Lake, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2253.

Add the following:  The Contractor shall not use land from any park, recreation area, significant historical site, Palmer Hay Flats State Game Refuge or any other wildlife or waterfowl refuge located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.

The Contractor shall do no work, stockpiling, staging, parking, nor trespassing in or around any watercourses except for that work permitted in the Knik and Matanuska Rivers that is specified by the contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

Standard Modifications

107-1.13  Responsibility for Damage Claims.  In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries".  (5/12/89)

107-1.16  Contractor's Responsibility For Utility Property And Services.  In the last sentence of the third paragraph delete: "by the local fire authority."  (5/12/89)

Special Provisions

107-1.16  Contractor's Responsibility for Utility Property and Service.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mislocates the facility in the field by more than 2.5-feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.  (9/1/89)

107-1.21  Permits.  Add the following Subsection:  The following permits have been received on the Contractors behalf by the Department:

1.	Department of the Army, Corps of Engineers Permit No. Knik Arm 117 071-04D-2-900105, dated August 24, 1990, to place approximately 2.475 million cubic yards of fill into wetlands and waters of the United States, and the modifications of this permit dated January 9, 1991, to provide for construction access in the Knik and Matanuska Rivers via temporary trestle or barge..

2.	Municipality of Anchorage Flood Hazard Permit.

3.	Matanuska Susitna Borough Flood Hazard - Land Use  Permit.

4.	Department of Fish and Game Title 16 Permit No. FG 90-II-0117 dated July 25, 1990.

5.	Department of Natural Resources Temporary Water Use Permit No. 90-28, dated August 9, 1990 for Loberg Lake.

The Contractor shall be responsible for conducting all operations within the Municipality of Anchorage in compliance with Anchorage Municipal Code 15.70 (Noise).  If the Contractor can not conform with the restrictions of this Code, it is his responsibility to obtain a Noise Permit authorizing the nonconformance.  Application for  this Permit can be made through the  Municipality of Anchorage, Health and Human Services Division, 825 "L" Street, Anchorage, Alaska, (907)343-4200.

The permits obtained by the Department are attached to these specifications as Appendix A. The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor's responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of the permits,  the  Contractor  shall   cease   work  and   immediately

notify the Engineer.  The Engineer will then decide if a permit modification is necessary.   The Engineer will have copies of the permits posted in the project office.  (8/1/90)

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  Subletting of Contract.  Delete the third paragraph on page 56 and substitute the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Driver's License.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	The owner-operator's right to control the manner in which the work is to be performed.

2.	The owner-operator's opportunity for profit or loss depending upon their managerial skill.

3.	The owner-operator's investment in equipment or materials required for their task, or the employment of helpers.

4.	Whether the service rendered requires a special skill.

5.	The degree of permanence of the working relationship.

6.	Whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each truck driver that identifies the truck driver as either an employee or owner-operator.  The placard for owner-operators shall identify both the truck driver and the vehicle.  The placard shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.  (9/1/89)

Standard Modifications

108-1.03  Prosecution and Progress.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule". (5/12/89)

Special Provisions

108-1.03  Prosecution and Progress.  Add the following:  The construction of this project will be planned and recorded with a conventional Critical Path Method (CPM) schedule.  The schedule shall be used for coordination, monitoring, and payment of all work under the contract including all activity of subcontractors, vendors, and suppliers.

1.	Preparation of Initial Schedule.

At the preconstruction conference, the Contractor shall submit a detailed initial Progress Work Schedule in the activity-on-arrow format.  The schedule shall meet the requirements set forth below.

The construction time, for the entire project or any milestone shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed schedule are required, the Contractor shall do so promptly.  The schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements.

All activity-on-arrow diagrams shall include:

a.	Activity Nodes

b.	Activity Description

c.	Activity Duration

d.	Resources required for each of the project activities, including:

1) labor, showing:

- work days per week

- holidays

- shifts per day

- hours per shift

2) equipment,

3) materials.

The activity-on-arrow diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and approvals and fabrication and delivery activities.  All network "dummies" are to be shown on the diagram.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60 - Day Preliminary Schedule.

Before proceeding with any work on site, the Contractor shall have an acceptable 60-day preliminary schedule.  This schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include:

a.	mobilization,

b.	submittals,

c.	procurement, and

d.	construction.

No contract work may be pursued at the site without an accepted 60-day Preliminary Schedule or an accepted CPM schedule.

4.	Schedule Updates And Progress Payments.

Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the Progress Work Schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions.

The Contractor will revise activity-on-arrow diagrams for the following:

a.	resource availability,

b.	delay in completion of any critical activity,

c.	actual prosecution of the work which is, as determined by the Engineer, significantly different than that represented on the schedule,

d.	the addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

The principles involved and terms used in this section are as set forth in the Associated General Contractors of America publication, "The Use of CPM in Construction, A Manual for General Contractors and the Construction Industry", Copyright 1976.

In addition to the CPM Progress Work Schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail work activities, manpower involved by trade, work hours, equipment involved and the location of the work to be performed.

Preparation of the CPM work schedule and two week work plans will not be paid for directly, but will be subsidiary to Item 640(1) Mobilization and Demobilization.  (6/13/90)

108-1.05  Character of Workmen, Methods and Equipment.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer. (9/1/89)

108-1.06  Determination and Extension of Contract Time.  Add the following:

4.	Suspensions of Work Ordered by the Engineer.  If the performance of all or any portion of the work is suspended or delayed by the Engineer in writing for an unreasonable period of time (not originally anticipated, customary, or inherent to the construction industry) and the Contractor believes that additional compensation and/or contract time is due as a result of such suspension or delay, the Contractor shall submit to the Engineer in writing, a request for adjustment within 7 calendar days of receipt of the notice to resume work.  The request shall set forth the reasons and support for such adjustment.

Upon receipt, the Engineer will evaluate the Contractor's request.  If the Engineer agrees that the cost and/or time required for the performance of the contract has increased as a result of such suspension and the suspension was caused by conditions beyond the control of and not the fault of the Contractor, its suppliers, or subcontractors at any approved tier, and not caused by weather, the Engineer will make an adjustment (excluding profit) and modify the contract in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment will be allowed unless the Contractor has submitted the request for adjustment within the time prescribed.

No contract adjustment will be allowed under this clause to the extent that performance would have been suspended or delayed by any other cause, or for which an adjustment is provided for or excluded under any other term or condition of this contract.

(4/13/89)

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  General.  Add the following:  When more than one variety of material or work item is specified for a single pay item number, letter or numeric suffixes will be included within the parenthesis to differentiate the types.  (9/1/89)

109-1.04  Compensation for Altered Quantities.  In the third indented subparagraph, delete the following:  ", except that the total payment for the item shall not exceed 75 percent of the total amount bid for the item".  (4/13/89)

109-1.05  Compensation for Extra Work.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)

109-1.07  Payment  For Materials on Hand.   Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project

will be in Anchorage, Alaska, except for the following items which will be eligible for partial payment when accepted by the Engineer.

1.	Item 504(1A) Structural Steel - A572 Furnished, Fabricated and Erected

2.	Item 504(1B) Structural Steel Furnished, Fabricated and Erected

The structural steel elements shall be fully fabricated, painted, ready for shipment, and stored in a secure area at the fabricator's facility.  Acceptance of the steel elements for partial payment will be made by the Department's fabrication inspectors.  The Contractor will provide Proof of Insurance in an amount equalling the replacement value the steel from the point of acceptance for partial payment until the steel arrives on the project.  Final acceptance of the steel will be made by the Engineer on the project site.

(11/1/90)

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  Description.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  Interpretation.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  Essential Contract Provision.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  Definitions and Terms.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular Contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03 Item 3. for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a Contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  Utilization Goal.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement

of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Goal in order to be eligible for award of this contract.

120-3.01  Determination of Compliance.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  Good Faith Effort.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE Credit.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the

Contractor shall ensure that ALL of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least  one  of  which must  be  working  on this

project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  Default of DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, all of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02, Good Faith Effort.

120-4.01  Method of Measurement.  The Contractor shall be entitled to count toward the DBE Goal those monies allowed by the Engineer in 120-3.03.04 as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100 percent.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60 percent of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  Basis of Payment.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01, Utilization Goal, until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per subsection 120-3.03, Item 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

Payment or Deduction will be made under:

Pay Item No.        Pay Item         Pay Unit

120(1)        DBE Adjustment   Contingent Sum

(5/5/89)

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

202-1.01  Description.  Add the following:  This work shall include removal of existing rock riprap at the Knik and Matanuska River Bridges, as shown on the plans.

202-4.01  Method of Measurement:  Add the following:  Removal of existing rock riprap will not be measured for payment.

202-5.01  Basis of Payment.  Add the following:  Removal of existing rock riprap will not be paid for directly, but will be subsidiary to item 611(2) Riprap, Class III.

SECTION 203

EXCAVATION AND EMBANKMENT

Standard Modifications

203-2.05  Borrow.  Add the following:  Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.  (5/12/89)

Special Provisions

203-3.02  Embankment Construction.  Add the following:  All fill and embankment construction shall conform to the requirements contained in Subsection 107-1.21, Permits.

The final embankment and/or surcharge height shall be based on design elevation and not construction grade

stakes.  The embankment shall be profiled after completion to verify that it is at design elevation.

Construction of embankment and surcharges from Sta. 1028+00 to Sta. 1037+50 shall be completed no later than June 30, 1991.  Construction of embankment and surcharges on the remainder of the project shall be completed no later than October 31, 1991 except for those areas within 100 feet of the ends of the bridges.  The surcharge layer will remain as part of the completed embankment template for the duration of the project.

203-3.05  Construction of Embankments in Surcharge Areas. Add the following subsection:  There are areas within the construction limits where gravel fill was placed and the existing vegetation removed prior to this contract.  The Engineer will determine which areas are defined as having been disturbed.

1.	Initial Lift.  In areas where the existing ground has been disturbed, the Contractor may place an initial lift less than 4 feet as approved by the Engineer.  For areas where the existing ground is undisturbed, an initial lift, 4 feet thick, of selected material, Type A shall be placed by dumping the material onto the advancing embankment and spreading the material over the end or side.  Half width embankment construction will be allowed on the initial lift.

Spreading equipment on the initial lift shall be limited to a maximum weight of 55,000 pounds per unit.  A minimum separation of 30 feet shall be maintained between each piece of spreading equipment.  Hauling equipment shall be limited to a maximum total loaded weight of 60,000 pounds.

There are no equipment weight limitations on the initial lift after it has been in place for 48 hours.

Where the initial lift is placed in areas of standing water, the thickness of the initial lift shall be increased, if required, so that a minimum of one foot of initial lift embankment is above the level of the standing water.  A minimum thickness of 4 feet shall be maintained for the initial lift.

2.	Embankment Construction Above Initial Lift.  The initial lift shall be in place a minimum of 48 hours prior to placement of additional embankment material.  All embankment material placed between the top of the initial lift and a total embankment height of 6 feet above original ground, or to the bottom of the surcharge layer, whichever is lower, shall be placed in 8-inch lifts with no moisture or density requirements.  Compaction in this zone shall be obtained by routing haul equipment uniformly over the entire surface of each layer before the next layer is placed.

All embankment material placed between 6 feet above original ground and the bottom of the surcharge layer, shall be placed in 8-inch lifts in accordance with Subsection 203-3.03, Construction of Embankments with Moisture and Density Control.

3.	Surcharge Layer.  The surcharge layer may be placed in one lift with no compaction requirements.

4.	Winter Contruction.  Embankment or surcharge construction using frozen material will not be permitted.

a.	Existing Ground Disturbed Areas.  For areas where the existing ground is disturbed, the Contractor may place the initial lift on frozen ground as approved by the Engineer.  Subsequent lifts shall not be placed until the existing ground and new embankment are thawed.

b.	Existing Ground Undisturbed Areas.  For areas where the existing ground is undisturbed, winter construction of the initial lift will not be allowed.  If the initial lift is placed on unfrozen ground, placement of subsequent lifts up to 6 feet above original ground, and surcharge layers not requiring moisture and density control will be allowed during winter.

Construction of all surcharge areas shall be completed no later than October 31, 1991.  The surcharge layer will remain as part of the completed embankment template for the duration of the project.

Standard Modifications

203-5.01  Basis of Payment.  Change Pay Items 203(5), (6) and (7) to read:  Borrow, Type _____.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-3.01  Proportioning.  Revise Item 2. as follows:  In Table 501-1, Class A Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S and W concrete.  (9/1/89)

Standard Modifications

501-3.01  Proportioning.  In the second paragraph under Item 3, replace "Polysar 1186" with "Styrofan 1186".  (5/12/89)

Special Provisions

501-3.01  Proportioning.  Add the following to Item 4:  Fly ash may be used only in abutments and piers of the Knik and Matanuska River Bridges.  It shall not be used in the deck or concrete railings.

501-3.02  Batching.  Add the following to Item 5:  The Contractor shall furnish the Engineer with a list of all ingredients, their individual weights and the moisture content of the various aggregates with each truck load or batch of concrete supplied.

501-3.05 Forms.  Add the following:

Architectural Finish.  The thickness of concrete members that receive an architectural finish shall be increased so that the specified minimum cover to reinforcing steel is maintained.

The following concrete surfaces shall receive an architectural finish:

The vertical exterior surfaces of the concrete bridge railings that are exposed to view from beyond the limits of the bridge.

The longitudinal limits for the architectural finish shall be the outside end of the bridge rail transitions.

The architectural finish may be created by the form itself or by a liner attached to the formwork surfaces, and shall preferably be a pattern of standard manufacture.  The pattern shall produce a uniform vertical rib and groove texture.  The overall depth (relief) of the pattern shall not exceed one-inch, and the center-to-center rib spacing shall not exceed three inches.  The widths of the rib surface and the base of the grooves shall be approximately equal.  Samples of the pattern shall be submitted for approval.

Inserts.  Threaded inserts may be cast in the edges of concrete decks as an aid in forming sidewalks and concrete railings.  Spacing of the inserts shall be four feet and the insert size shall be as required for the intended loads.  After the forms are removed the recess remaining at the insert shall be filled and patched with grout of the same color and texture as the deck concrete.

Permanent Metal Forms.  Permanent metal forms shall not be used for any components of the Knik or Matanuska River Bridges.

501-3.07  Finishing Concrete Surfaces.  Delete the second sentence of the 15th paragraph under Item 3, Concrete Decks, and substitute the following:  The surface shall not vary more than 0.01 feet from the lower edge of the straightedge.

501-5.01  Basis of Payment.  Add the following:  Architectural finish will be subsidiary to Item 507(4) Concrete Bridge Rail, Type 1.

Expansion Joint Devices will be subsidiary to items paid for under Section 504 Structural Steel.

Additional concrete required for light pole supports will be subsidiary to Item 660(5) Structure Illumination Complete.

SECTION 503

REINFORCING STEEL

Standard Modifications

503-3.05  Splicing.  Delete the first and second paragraphs and substitute the following:  Lap splices for reinforcing bars shall be as shown on the plans or as directed.  (5/12/89)

Special Provisions

503-5.01  Basis of Payment.  Add the following:  Additional reinforcing steel required for the light pole supports will be subsidiary to Item 660(5) Structure Illumination Complete.

Reinforcing steel embedded in the bridge deck and used for anchoring bridge railings, as well as all reinforcing steel contained in the railings, will be subsidiary to Item 507(4) Concrete Bridge Rail, Type 1.

SECTION 504

STEEL STRUCTURES

Special Provisions

504-2.02  Teflon Coated Bearings.  Change the coefficient of friction value in the table to the following:

Coefficient of

Friction, TFE

against stainless

steel                   0.08 max. (Load = 1000 psi

Speed = 1 inch per minute)

504-3.01  Fabrication.  Add the following to Item 2:  All structural steel for the steel bridge in this contract shall be fabricated in a shop certified by the American Institute of Steel Construction for Category III:  Major Steel Bridges.

Add the following to Item 6:  Shop assembly shall be in sections of at least 300 feet long, and for the full width of the framing plan.  Subsequent assembled sections shall overlap previously assembled sections by at least 100 feet.

Standard Modifications

504-3.01  Fabrication.

7.	Bolted Connections.  High Tensile Strength Bolts.  Delete paragraphs 5 through 14, and Table 504-3 and substitute the following:  All fasteners shall be tightened to give at least the required minimum tension values shown in Table 504-2 on completion of the joint.  All bolts and nuts in a connection shall be made by the same manufacturer.

In order to achieve the minimum tension values shown in Table 504-2, Required Bolt Tension, direct load indicating washers, conforming to the requirements of ASTM P959, shall be used.  The suitability of the device shall be demonstrated by testing a representative sample of not less than three devices for each diameter and grade of fastener used in the structure in a calibration device capable of indicating bolt tension.  The test assembly shall include flat, hardened washers, if required in the actual connection, arranged as those in the actual connection to be tensioned.  The calibration test shall demonstrate that the device indicates a tension not less than five percent greater than that required by Table 504-2, Required Bolt Tension.  Manufacturer's installation procedures shall be followed for installation of bolts in the calibration device and in all connections.  Special attention shall be given to proper installation of flat, hardened washers when load indicating devices are used with bolts installed in oversized or slotted holes and when the load indicating devices are used under the turned element.

Unless otherwise permitted, the load indicating device shall be placed under the bolt head, and only the nut shall be turned when tightening the bolt.  The device shall indicate full tensioning of the bolt when the opening reaches zero.

Bolts shall be installed in all holes of the connection and brought to snug tight condition.  All fasteners shall then be tightened, progressing systematically from the most rigid part (usually near the center) of the connection to the free edges, or as directed, in a manner that will minimize relaxation of previously tightened fasteners.  It may be necessary to provide multiple cycles of systematic tightening.

High-strength bolts shall not be reused.  Previously fully-tightened bolts which may have been loosened by the tightening of adjacent bolts shall be removed and replaced with new bolts, nuts, and load indicating devices.

(5/12/89)

Special Provisions

504-3.02  Erection.  Add the following to Item 5:  Heat straightening ASTM A514 steel shall be in accordance with the requirements of AASHTO/AWS Bridge Welding Code D1.5, paragraph 3.7.3.

Add the following to Item 8:  Epoxy adhesive, conforming to AASHTO M-200, shall be applied to the bottom surface of the elastomeric bearing pads prior to placement, and the pad shall be secured and restrained from movement until the epoxy has cured and full adhesion is achieved between the pad and the concrete.

504-3.03  Painting.  Delete numbered items 1. Preparing Metal Surfaces for Painting, and 2. Schedule of Paint Coats for Metals and substitute the following:

A. Description.  This work shall consist of furnishing all labor, materials and equipment necessary to paint steel structures and the structural metal portions of composite structures in conformance with the plans and specifications.  Galvanized surfaces shall not be painted.

Field splice areas and bolts shall be painted in the shop with a prime coat but not an intermediate nor finish coat, which shall be applied in these areas after assembly of the structural steel.

Top flange steel surfaces that are to be field welded with stud shear connectors, shall be painted in the shop with a mist coat of primer of not more than 0.75 mils dry film thickness.  No intermediate or finish coat shall be applied in these areas.  Other areas of steel surfaces to be in contact with concrete need not be painted.

The paint protection shall consist of a high ratio zinc silicate primer, epoxy intermediate coat and high build urethane top coat system.

B. Materials.  Paint furnished shall be shipped in strong, substantial containers, plainly marked with the name, weight, and volume of the contents, together with the color formula, batch number, and the name and address of the manufacturer.

The paint shall conform to the requirements outlined below:

1.	Prime Coat.  Component characteristics for high ratio inorganic zinc silicate primer meeting U.S. Patent No. 4162169:

ASTM

Property                 Requirement          Designation

Zinc Dust				Type I or II			D 520

Average			6 to 8 microns			D 1366

particle size

Liquid Vehicle

Non volatile		26.5+0.5%				D 2369

content

Density			10.0+0.1 lbs/gal		D 1475

Si02/K20			5.3:1

ratio

The following products have been evaluated and determined to provide a material meeting specification requirements for a high ratio zinc silicate primer used in undercoating properly prepared structural steel in transportation construction projects.

Inorganic Coatings, Inc.

IC 531			High-Ratio zinc silicate

(800) 345-0531

Valspar Corp.

MZ-6				Hi-Ratio Inorganic Zinc (818) 334-8251		Rich Primer

DuPont Coatings Co.

Ganicin 347WB		High-Ratio zinc silicate

(800) 346-4748

Ameron Protective Coatings

Dimetcote 21-7		High-Ratio zinc silicate

(714) 529-1951

The effective period for this list is indeterminate.  Other products will be considered for inclusion on this list subject to evaluation and approval by:

Alaska DOT & PF

Engineering & Operations Standards Division

Headquarters Materials

5700 East Tudor Road

Anchorage, Alaska  99507

2.	Intermediate Coat.  The intermediate coat shall be a 2 component high build low VOC polyamide epoxy suitable for immersion that will withstand 1000 hours of salt spray per ASTM B117 and 400 psi pulls per ASTM D4541.  Color in the dry state shall closely match FED-STD-595B-23578.  The color match shall be evaluated as a general match under a daylight source as per ASTM D1729.

3.	Finish Coat.  The finish coat shall be a high build low VOC aliphatic acrylic urethane that when applied over the intermediate coat will yield equal results per ASTM B117 and ASTM D4541.  Color in the dry state shall closely match FED-STD-595B-36492.  The color match shall be evaluated as a general match under a daylight source as per ASTM D1729.

C.	Construction Requirements.

1.	Preparing Metal Surfaces for Painting.  All surfaces to be coated shall be prepared in accordance with Steel Structures Painting Council (SSPC) SP 10 Near White Blast Specification.  Near white blast cleaning shall be required and proper type and size of abrasive shall be used to obtain an average profile depth of 1.0 mils.  However, excessive profiles above 3 mils will demand more coating material to fill the profile.  A profile comparator shall be used to assure minimum profile depth.  Sand or flint abrasives shall not be reused.

Grit or shot must be cleansed of contamination before reuse.  Dust and grit shall be blown from the surface with clean dry air.  Remove all weld spatter and round sharp edges to a smooth curve.  If contaminated, jet wash or scrub with a stiff brush and clear water or brush blast to remove contamination.  Light rust may be removed with a steel brush or mechanical tool.

2.	Schedule of Paint Coats for Metals.  The structural steel shall be painted with a minimum of three coats:

a.	Prime coat (dry film thickness 3.0 mils minimum)

b.	Intermediate coat (dry film thickness 4.0 to 6.0 mils)

c.	Finish coat (dry film thickness 3.0 to 5.0 mils)

All coats shall be shop applied according to the manufacturer's written instruction.

All blast cleaned surfaces shall receive an undercoat consisting of a high ratio 5.3:1 zinc silicate primer.

The inorganic zinc primer shall consist of two ready to mix components which are furnished in separate containers.  The zinc dust pigment component shall contain a minimum of 18 pounds of zinc dust per gallon of primer.  The liquid vehicle component of the primer shall consist primarily of a water solution of potassium silicate with a mole ratio of 5.3 parts silicon dioxide to one part potassium oxide.  The manufacturer's published mixing and application instructions shall be followed.  Thinning of the primer will not be permitted unless approved by the Engineer.  Primer shall be used within 8 hours of initial mixing.

Inorganic zinc primer shall be applied in 1 or more applications with the initial application applied within 4 hours after blast cleaning.  A minimum drying time of 30 minutes shall be allowed between primer applications.

All areas where mudcracking occurs in the inorganic zinc primer shall be blast cleaned and painted with primer to the specified thickness.

After application of the primer all exposed surfaces shall receive the following finish coats in accordance with manufacturers recommendations:

a.	The intermediate coat shall be applied in 2 applications.  The first application shall consist of a mist coat.  The second application shall be applied after the mist coat has dried to a set to touch condition.  Mixing and thinning instructions on the manufacturers data sheet shall be followed.

b.	The finish coat shall be applied in 1 application.

Make the following changes under item 3. Painting Metal Surfaces:

Delete the subparagraphs under heading a. Time of Application, and substitute the following:

a.	Time of Application.  The prime coat shall be applied as soon as possible after the surface has been cleaned and before deterioration of the surface occurs.  Any oil, grease, soil, dust or foreign matter deposited on the surface after the surface preparation is completed shall be removed prior to painting.  In the event that rusting occurs after completion of the surface preparation, the surface shall be cleaned again.

Care shall be taken to prevent the contamination of cleaned surfaces with salts, acids, alkali, or other corrosive chemicals before the prime coat is applied and between applications of the remaining coats.  Such contamination shall be removed from the surface.  Under these circumstances the prime coat shall be applied immediately after the surface has been cleaned.

Delete the subparagraphs under heading b. Storage of Paint Thinner and heading c. Mixing and Thinning.

Delete the second sentence of the second subparagraph and the first sentence of the third subparagraph under heading g. Shop Painting.

Delete the subparagraphs under heading j. Handling of Painted Steel, and substitute the following:

j.	Handling of Painted Steel.  Painted steel shall not be handled until the coating has dried except for necessary handling and turning for painting or stacking for drying.

k.	Repair of Defects.  Paint which is damaged shall be removed and touched up with the same number of coats and kinds of paint as were previously applied to the steel or in  conformance  with  the coating manufacturer's written recommendations and procedures.  Galvanized steel damaged by field welding  or  any  other  reason  shall be hand cleaned  and  repaired   in  accordance  with AASHTO

M36-24.  Repair of galvanizing shall be made at no additional cost to the State.

l.	Component Origin.  All components of any system shall come from one manufacturer.

m.	System Durability and Certification.  The coating system manufacturer shall review the project and the coatings proposed environment and shall issue to the applicator recommendations and instructions to insure maximum durability and proper application of the coating on this project.

The applicator shall certify to the Department that the system was applied in accordance with the manufacturer's recommendation and instructions and shall enclose a copy of the recommendation and instructions with the certificate.

504-4.01  Method of Measurement.  Add the following:  Painting of structural steel or structural steel portions of composite structures will not be measured for payment.

All portions of the drainage systems located under the expansion devices on the Knik and the Matanuska River Bridges will not be measured for payment.

504-5.01  Basis of Payment.  Add the following:  Painting will not be paid for directly, but will be subsidiary to steel structures.

The drainage systems for the expansion devices on the Knik and the Matanuska River Bridges will not be paid for directly, but will be subsidiary to steel structures.

Stud shear connectors will be paid for at the contract lump sum price.

Payment will be made under:

Pay Item No.           Pay Item          Pay Unit

504(3)       Stud Shear Connectors    Lump Sum

SECTION 505

PILING

Special Provisions

505-1.01 Description.  Delete the second paragraph and substitute the following:  There shall be high-strain dynamic testing performed on 6 piles for this project.  After performing the test pile program as described below, all service piles in the two bridges shall be driven according to the installation criteria and construction control recommendations from the test pile analyses and results.  Test piles shall be driven in the order set forth in Subsection 505-3.01 Test Piles.  All piles shall be driven to at least the tip elevations shown on the plans.

The publication listed below shall be part of this specification:

(ASTM) D 4945-89 High-Strain Dynamic Testing of Piles

505-3.01  Test Piles.  In the first paragraph, delete the last sentence.

Add the following:  There shall be high-strain dynamic testing performed on 6 piles for this project.  The Contractor shall drive 1 test pile at each of 6 test sites.  The test sites are identified as follows:

Knik River Bridge (No. 1885)

Test Site            				Test Pile Type

Pier 2									Plumb

Pier 5									Battered

Pier 8									Plumb

Matanuska River Bridge (No. 1889)

Test Site							Test Pile Type

Pier 2									Plumb

Pier 4									Battered

Pier 6									Plumb

The initial pile driven at either bridge shall be a test pile.  This pile may be driven at any test site.  If the immediate results from the high strain dynamic testing on the test pile are acceptable as specified herein, the Contractor may drive the remaining piles in the pile bent at the test site prior to performing further tests at other test sites.  A pile bent is defined as all of the piles in one pier or abutment.  At either bridge, all test piles shall be driven prior to driving piles at pile bents which do not contain test piles.

The Contractor shall obtain the services of a consultant specializing in dynamic pile testing and use of the wave equation for pile driving.  The Contractor's consultant shall be experienced and qualified in the use of a pile driving analyzer, the Case Method of analysis for piles, wave equation analysis of pile driving and CAPWAPC analysis.  The following list includes engineering firms qualified to perform the pile testing program for this project:

GRL and Associates, Inc.

144 Railroad Avenue, Suite 221

Edmonds, Washington 98020

Phone:  (206) 775-5785

Fax:    (206) 778-6933

GME Consultants, Inc.

14000 21st Avenue North

Minneapolis, Minnesota 55447

Phone:  (612) 559-1859

Fax:    (612) 559-0720

Goldberg-Zoino & Associates, Inc.

320 Needham Street

Newton Upper Falls, Massachusetts 02164

Phone:  (617) 969-0050

CH2M Hill Inc.

1500 114th S.E.

Bellevue, Washington 98004

Phone:  (206) 453-5000

Insitu Tech

262 Grand Avenue, Suite 200

Oakland, California 94610

Phone:  (415) 839-6567

The Engineer will use the pile dynamic test data to verify assumptions of the initial wave equation analysis,

and to confirm pile tip elevation, pile bearing capacity, hammer system efficiency, pile stresses during driving, resistance distribution on the pile, and pile integrity.

The test piles shall remain as part of the permanent structure after testing, analysis, and recommendations are completed.

The Contractor and Contractor's consultant shall perform the following tasks:

1.	Perform an initial wave equation analysis based on subsurface conditions, pile type, pile capacity, and driving system to be used.

2.	Drive the test piles at the locations specified above and to the tip elevations shown on the plans, using criteria established by the initial wave equation analysis.  Dynamic pile testing shall be performed for the total length of each test pile.  If an obstruction is encountered during driving of a test pile, that pile will not be considered a test pile and the next pile driven at the test site shall be designated as a test pile as directed by the Engineer.  This dynamic pile testing shall be performed in accordance with ASTM D 4945-89.  Immediate results shall include the hammer transferred energy, pile compressive stresses, bending stresses indicated by strain transducers attached to the piles, and calculated Case Method bearing capacity with resistance distribution along the pile.  The immediate results shall be provided to the Engineer as soon as possible after the test pile is driven.

For the test pile program, 21 calendar days prior to driving the first test pile, the Contractor shall submit to the Engineer and the Contractor's consultant, the necessary pile driving equipment information as shown on the Pile Driving Equipment Data Form.  This form will be furnished by the Engineer.  A minimum of 14 calendar days prior to driving the first test pile, the Contractor and the Contractor's consultant shall attend a conference with the Engineer to evaluate and discuss the pile test program.

3.	Evaluate each test pile at all test sites by restriking the test pile after a minimum of 8 hours has elapsed after completion of driving to the

specified tip elevation.  The restrike shall be performed with simultaneous dynamic testing using the dynamic pile driving analyzer.

The restrike testing procedure shall be as follows:

a.	Air or Steam Hammers.  The test pile shall be given 10 consecutive blows at the normal operating pressure for air hammers or steam hammers, so that for a single-acting hammer there is a full upward stroke of the ram, and for a double-acting hammer the number of blows per minute during, and at the completion of driving is approximately equal to that at which the hammer is rated, unless otherwise directed by the Engineer.

b.	Diesel Hammers.  The test pile shall be given 10 consecutive blows with the fuel setting adjusted to the maximum position, unless otherwise directed by the Engineer.

Restrike of the test pile shall confirm that the ultimate capacity of the test pile is greater than or equal to the required ultimate capacity as specified in Section 505-3.03 Pile Bearing Values, of these Special Provisions.  During restrike, additional hammer blows and/or penetration may be required as directed by the Engineer.

4.	Perform dynamic analysis of the measured data using CAPWAPC on records taken both at the end of driving and at the beginning of restrike on each test pile for an assessment of soil setup effect and for verification of field results.

5.	A final report summarizing field results, CAPWAPC results and the conclusions of the testing firm shall be issued within 14 calendar days from completion of all dynamic testing.

6.	Three complete copies of the analysis and recommendations specified above shall be submitted to the Engineer for review and final acceptance.

505-3.03 Pile Bearing Values.  Delete this subsection in its entirety and substitute the following:  The ultimate pile capacity shall be determined by the Engineer based on a wave equation analysis.  The wave equation analysis computer program to be used on this project shall be the "GRLWEAP" program developed by GRL, Inc.  The program "WEAP87" may also be used.  The wave equation will be used with a factor of safety of 2.25 for the design load, and a factor of safety of 1.0 for the seismic load with liquefaction.  Piles shall be driven with the approved driving system to the specified tip elevation and shall obtain the required ultimate bearing capacity.  It is anticipated that when the piles are driven to the specified tip elevation, the actual ultimate pile capacity will exceed the required capacity.  The actual ultimate capacity of the piles will be established after the testing, analysis, and Contractor's consultants recommendations are completed.  The Engineer will determine the ultimate capacity along with other driving criteria.  The ultimate pile capacity is anticipated to be approximately 2400 kips.  Sample wave equation work sheets using three different hammers are attached to these specifications in Appendix C.

Required ultimate pile capacities are as follows:

Knik River Bridge (No. 1885)

Required Ultimate	Required Ultimate

Foundation				Capacity Without		Capacity With 70 Feet

Structure				Liquefaction			of Liquefaction

Abutment 1        1,465 kips             680 kips

Pier 2            1,465                  680

Pier 3            1,465                  680

Pier 4            1,720                1,380

Pier 5            1,885                1,450

Pier 6            1,720                1,380

Pier 7            1,465                  680

Pier 8            1,465                  680

Abutment 9        1,465                  680

Matanuska River Bridge (No. 1889)

Required Ultimate		Required Ultimate Foundation			Capacity Without		Capacity With 70 Feet

Structure			Liquefaction			of Liquefaction

Abutment 1          1,465 kips            680 kips

Pier 2              1,465                 680

Pier 3              1,720               1,380

Pier 4              1,885               1,450

Pier 5              1,720               1,380

Pier 6              1,465                 680

Abutment 7          1,465                 680

Specified tip elevation shall be as shown on the plans.

505-3.09  Driving Piles.  Delete the fifth sentence of the first paragraph and substitute the following:  Piles for exposed pile bents shall be within 3 inches of plan position at cutoff elevation and within 6 inches of plan position at original ground line.

Delete the tenth paragraph (second paragraph on page 250), and substitute the following:  All pile driving equipment furnished by the Contractor shall be subject to approval by the Engineer.  Vibratory hammers may only be used for driving sheet piles.  All pile driving systems shall be equipped with a suitable thickness of hammer cushion material to prevent damage to the hammer or pile and to insure uniform driving performance.  Hammer cushions shall be made of durable, manufactured materials, provided in accordance with the hammer manufacturers guidelines except that wood, wire rope, and asbestos hammer cushions shall not be used.  The hammer cushion shall be inspected in the presence of the Engineer when beginning pile driving at each structure or after each 100 hours of pile driving, whichever is less.  Any reduction of hammer cushion thickness exceeding 25% of the original thickness shall be replaced by the Contractor before driving is permitted to continue.

The pile driving equipment shall be sized such that the piles can be driven to the specified tip elevation without damage.  Approval of the pile driving equipment by the Engineer will be based on the wave equation, high-strain dynamic testing, and the Engineer's recommendations.

All service piles shall be driven to the specified pile tip elevation based on the high strain dynamic test results and the Engineer's recommendation.  Adequate pile penetration will be considered to be obtained when the specified high strain dynamic testing criteria and wave equation criteria is achieved within five (5) feet of the specified pile tip elevation.  Piles not achieving the specified ultimate capacity within these limits shall be driven to a penetration established by the Engineer.

After the test piles are driven and during the service pile driving operations, the Contractor shall use the approved driving system to drive the service piles.  No variations in the driving system will be permitted without the Engineer's written approval.  Any change in the driving system will only be considered after the Contractor has submitted a revised Pile Driving Equipment Data Form for a revised wave equation analysis by the Engineer, and the analysis indicates an acceptable result.  The Contractor will be notified of the acceptance or rejection of the revised driving system within 7 calendar days of the Engineer's receipt of the requested change.  The time required for submission, review, and approval of a revised driving system shall not constitute the basis for a contract time extension to the Contractor.

For the pile driving system to be acceptable, the compressive driving stresses as measured by the pile dynamic analysis or as indicated by CAPWAPC and Wave Equation results shall not exceed 90 percent of the pile yield stress.  The dynamic testing and CAPWAPC analysis shall be performed to confirm or modify pile driving criteria developed using wave equation for the Contractor pile-hammer combination.  The State reserves the right to require dynamic monitoring in addition to those previously specified if the Contractor's pile driving equipment does not seem to be working properly or in accordance with these specifications, or if pile design modifications are ordered by the State.  All dynamic monitoring shall be performed by the Contractor in the presence of the Engineer.  Any additional dynamic monitoring ordered by the Engineer shall be paid for at the contract unit price for Item 505(10) Test Piles.

Add the following to the eleventh paragraph (third paragraph on page 250):  There is a possibility of encountering boulders at the pier sites and riprap at the abutment sites when driving piles for both bridges.

Add the following to the fourteenth paragraph (first paragraph on page 251):  Piles may be driven before placement of new embankment, when approved by the Engineer.  The Contractor shall submit a driving plan for approval that will identify a method of isolating the piling from possible embankment settlement load transfer.  The driving plan shall also include the procedure for compacting the fill around the driven piles.

505-3.14 Painting Steel Piles and Steel Pile Shells.  Add the following:  The outside surface of the piling, above ground, shall be painted in accordance with Subsection 504-3.03 Painting.

505-4.01  Method of Measurement.  Delete the following from the sixth line of the second paragraph under Item 2., Piles, Driven:  "...reinforcing steel, concrete fill...".

Delete numbered paragraph 4. and substitute the following:

4.	Test Piles will be measured for each pile accepted by the Engineer.

Delete numbered paragraph 6. and substitute the following:

6.	The number of splices to be paid for shall be the number of piles required to be driven greater than 5 feet beyond the minimum specified tip elevation.  In no case shall the number of splices to be paid for exceed one per pile.

505-5.01  Basis of Payment.  Add the following:	Payment for test piles will include all labor, equipment and materials required to instrument, monitor, and analyze the test piles.  The piling will be paid as service piles under Items 505(5), Structural Steel Piles, Furnished and 505(6), Structural Steel Piles, Driven.

The reinforcing steel to be used in the piling shall be measured and paid as Item 503(1), Reinforcing Steel.  Concrete fill used in the piling shall be measured and paid as Item 501(1), Class A Concrete.

Pay Item No.           Pay Item          Pay Unit

505(15)            Pile Splice           Each

SECTION 507

BRIDGE RAILING

Standard Modifications

507-4.01  Method of Measurement.  Add the following:  It shall also include concrete and associated reinforcing steel included or partially contained within the limits of the concrete rail section.  (5/12/89)

Special Provisions

507-5.01  Basis of Payment.  Add the following:  Item 507(4), Concrete Bridge Railing, shall include full compensation for furnishing all labor, materials, and equipment required to construct the bridge railing on the bridges.  This shall include the bridge rail concrete, reinforcing steel and architectural finish and will include reinforcing embedded in the slab and extending into the railings and all barrier reflector assemblies.

SECTION 611

RIPRAP

Special Provisions

611-5.01  Basis of Payment.  Add the following:  Removal of existing rock riprap in accordance with Section 202, Removal of Structures and Obstructions, will not be paid for directly, but will be subsidiary to Item 611(2) Riprap, Class III.

Furnishing and installing geotextile riprap liner in accordance with Section 631, Geotextile For Subsurface Drainage and Riprap Liner, will not be paid for directly, but will be subsidiary to Item 611(2) Riprap, Class III.

Existing rock riprap to be removed under Section 202, Removal of Structures and Obstructions, which meets the requirements of Item 611(2) Riprap, Class III, may be used for this item in accordance with Section 104 of the Standard Specifications.

SECTION 618

SEEDING

Special Provisions

618-1.01  Description.  Delete this subsection and substitute the following:  Slopes at locations shown on the plans and any other areas directed by the Engineer shall be overlaid with topsoil and seeded.  This work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01  Materials.  Add the following to the list of material specifications:

Mulch                    Section 727-2.01

618-3.01  Soil Preparation.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be covered with topsoil in accordance with Section 620, and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as topsoil is placed on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach on the wetlands.  The performance of this work is subsidiary to seeding and will not be paid for directly.

618-3.03  Application Method.  In the first sentence of subparagraph b., under numbered paragraph 1., Hydraulic Method, delete the following:  "...Item 619(1),".

Add the following:  Seed, mulch and fertilizer shall be applied as shown in the following table per 1,000 square feet.  If the hydraulic method for seed and mulch is used, it shall be made in one application.  The mulch rate shown is a minimum, and may be increased in accordance with the manufacturers recommendations.  All fertilizer shall be applied by the hydraulic method.

Application

Item              Ingredients           Rate Lbs/MSF

Rural Seed     Bering Hairgrass (Norcoast)    0.60 lb.

Mix            Red Fescue (Arctared)          0.30 lb.

Annual Ryegrass (Lolium)       0.10 lb.

Alsike or Dutch White Clover   0.05 lb.

Baby Blue Eyes (Nemophila

Menzeisii)                0.05 lb.

Sun Flower (Helianthus Annus)  0.05 lb.

Ox Eye Daisy (Chrysanthemum

Leucanthemum)             0.03 lb.

Iceland Poppy (Papaver

Nudicaule)                0.03 lb.

TOTAL =      1.21 lb/MSF

Mulch                                        35.0 lbs.

Fertilizer     20-20-10                      12.0 lbs.

The Contractor shall not remove the required tags from the seed bags.

618-4.01  Method of Measurement.  Delete the second and third sentences of the second paragraph and substitute the following:  The amount of water, mulch and fertilizer used in this work, including any required reseeding will be subsidiary to seeding and will not be measured separately for payment.

618-5.01  Basis of Payment.  Add the following:  Fertilizer, water and mulch as described above, will not be paid for directly, but will be subsidiary to Item 618(2) Seeding.  (6/1/90)

SECTION 620

TOPSOIL

Special Provisions

620-2.01  Materials.  Add the following:  Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

SECTION 631

GEOTEXTILE FOR SUBSURFACE DRAINAGE

AND RIPRAP LINER

Special Provisions

631-2.01  Materials.  Add the following:  Geotextile material shall conform to the requirements for unprotected riprap liner.

631-4.01  Method of Measurement.  Delete this subsection in its entirety and substitute the following:  Geotextile riprap liner will not be measured for payment.

631-5.01  Basis of Payment.  Delete this subsection in its entirety and substitute the following:  Geotextile riprap liner will not be paid for directly, but will be subsidiary to Item 611(2) Riprap, Class III.

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01  Description.  Add the following:  This work includes construction and removal of paved temporary approaches onto the Glenn Highway for the Contractor's material hauling operation.

639-1.02  Construction Requirements:  Add the following subsection:  The embankment shall be constructed of select material, Type A.  Embankment and base course material shall be constructed in accordance with Subsection 203-3.04, Compaction of Embankments Not Constructed With Moisture and Density Control.  The base course layer shall be a compacted depth of 6 inches consisting of the Contractor's choice of grading from Table 703-2.

Asphalt material shall be placed on the compacted base course in one layer so as to yield a uniformly compacted depth of one and one half inches.

Initial rolling shall be performed while the mat temperature is above 225 degrees F with a steelwheeled tandem roller and/or a suitable pneumatic tired roller.

Following the initial rolling, at least three complete coverage of the pavement shall be completed with a pneumatic tired roller while the mat temperature is above 180 degrees F.

Pavement for temporary approaches shall be removed when they are no longer required for the Contractor's hauling operations.  Pavement may be disposed of by placement in the embankment or at a site approved by DEC for disposal of asphalt concrete.  If asphalt concrete is used in the construction of the embankment, it shall be placed away from wetlands, and no closer than 300 feet from a watercourse.  The broken asphalt concrete pieces shall be 6 inches or less in maximum dimension.

When the temporary approaches are removed, the Contractor shall repair and restore the existing roadway shoulder at each location as accepted by the Engineer.

639-2.01  Method of Measurement.  Add the following:  Item 639(4) Temporary Approaches will be measured for each approach, including materials, construction, maintenance and removal.

639-3.01  Basis of Payment.  Add the following:  The contract bid unit price per each temporary approach will be full compensation for all labor, equipment and materials required to complete the work as specified.  Base course and asphalt materials will not be paid for directly but will be subsidiary to Item 639(4) Temporary Approaches.  Embankment material will be paid for under Item 203(6-A), Borrow, Type A.

Payment will be made under:

Pay Item No.           Pay Item           Pay Unit

639(4)         Temporary Approaches       Each

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-1.01  Description.  Add the following:  This shall also consist of all work necessary to provide construction access in the Knik and Matanuska Rivers.

640-1.02  Construction Access in Knik and Matanuska Rivers.  Add the following subsection:  Construction access in the Knik and Matanuska Rivers shall be constructed in accordance with Subsection 107-1.21, Permits.  No temporary fill shall encroach into the rivers beyond the permanent abutment riprap limits.  For a temporary trestle, a minimum elevation of 21.6 feet (project datum) to the bottom of the structure and a minimum of 30 feet between pier centers shall be maintained.

The Contractor shall submit a work plan for the Engineer's approval a minimum of two weeks prior to construction of the access.  The work plan shall include but not be limited to the following:

1.	The Contractor's proposed method of access to the bridge sites, and a time schedule for completing the work.

2.	a drawing showing the location and typical section with elevations of the temporary trestle, if used,

3.	the size and draft of the barge, if used,

4.	the material to be used in approach embankments and methods for protecting the embankments from erosion, if used, and,

5.	the Contractor's proposed method to remove the temporary trestle and abutments, including methods for preventing material from entering the Knik River other than that permitted by the contract.

640-2.01  Method of Measurement.  Delete this subsection in its entirety and substitute the following:

1.	When 5 percent of the original contract amount is earned from other bid items, 90 percent of the amount bid for mobilization and demobilization will be paid.

2.	Any remaining balance of the amount bid for mobilization and demobilization will be paid in the final payment for work under this contract.

640-3.01  Basis of Payment.  Add the following:  Preparation of the CPM work schedule and two week work plans in accordance with Section 108, will not be paid for directly, but will be subsidiary to Item 640(1) Mobilization and Demobilization.

Design construction, maintenance and removal of a temporary construction access will not be paid for directly, but will be subsidiary to Item 640(1), Mobilization and Demobilization.

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

Special Provisions

641-2.01 Construction Requirements.  Add the following:  The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other substances hazardous  to the land and water.  The temporary erosion and pollution control plan shall address the measures the Contractor shall implement in the containment, cleanup, and disposal of such substances as well as the methods to be utilized for disposing of waste oil or other hazardous substances generated by construction equipment or activities.  The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.  The plan shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

The Contractor shall immediately notify the Engineer of any construction related discharge of oil and/or other substances hazardous  to the land or water.  Should any suspected hazardous substance be discovered during construction, work which would disturb the substance shall stop and the Engineer immediately notified.

641-2.02  Best Management Practices.  Add the following subsection:  Erosion and sediment control measures are more easily accomplished if construction operations are properly scheduled.  Operations should be planned, when possible, for that time of year when potential for erosion is low.

There are a number of factors to consider and operations to schedule in the development of an acceptable temporary erosion and pollution control plan.  These include, but are not necessarily limited to the following:

1.	Clearing by cutting, slashing and disposing of the trees and other debris.

2.	Installation of temporary erosion and sediment control measures on the downhill side of the construction work area before building the embankment or excavating a slope.

3.	Construction of temporary drainage ditches to convey off-site drainage through the work area and diversion of the flow before excavating for the permanent drainage structure.

4.	Installation of all erosion and sediment control measures at the toe of embankment and excavation operations.  Silt fences are a structural method for providing temporary erosion and sediment control.

5.	Construction of the embankment in horizontal lifts, providing protection from erosion by temporarily or permanently mulching and seeding the slopes in vertical increments, preferably of no more than 10-feet.  Keep the top of the work area shaped and compacted so that surface water will run off without causing serious erosion should a storm occur.  At the end of each day's work or before a storm, berms and temporary downdrains must be constructed to control the release of on-site drainage.

6.	Excavation operations performed in the same manner as the embankment operation with the exception of slope drains and compaction.  This operation will release on-site drainage at a point where appropriate control measures have been installed.  The excavated slope must be finished as it is constructed and incrementally protected and seeded.

7.	Shaping and compacting of the embankment surface or cut when the area reaches subgrade elevation.  Surface runoff should be controlled by berms and ditches and released through temporary pipes or ditches.  Detain sediment-laden runoff and trap sediment before releasing runoff from the construction area.

8.	Inspection and maintenance of each erosion and sediment control measure performed after each significant storm.  Silt fences should be inspected periodically for damage, such as tearing by wind, animals or equipment, and for the amount of sediment which has accumulated.  Removal of the sediment is generally necessary when it reaches half the height of the silt fence.  In situations where access is

available, machinery can be used; otherwise it must be removed manually.  The key elements to remember are:

a.	The sediment deposits should be removed when heavy rain or high water is anticipated.

b.	The sediment removed should be placed in an area where there is little danger of erosion.

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  Description.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix B.

642-4.01  Method of Measurement.  Add the following:  Pay Item 642(2), Three Person Survey Party, shall be used only for extra, additional, or unanticipated work made necessary by changes in the project as directed by written order of the Engineer.  The quantities shown on the Bid Schedule for this item are for bidding purposes only, and the actual quantity in the field may vary as directed.  It is not intended to cover survey costs due to minor overruns (10 percent or less) in items which require staking of individual installations such as culverts, guardrail, approaches, signs and drainage structures, etc.

642-5.01  Basis of Payment.  Add the following:  If additional work as stated above is performed by a two person survey party, hours paid for under Item 642(2) Three Person Survey Party will be 75 percent of the hours worked.  If additional work as stated above is performed by only one person, hours paid for under Item 642(2) Three Person Survey Party will be 32 percent of the hours worked.

(9/1/89)

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  Traffic Control Plan.  Add the following to the third paragraph:  All TCP's submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Safety Supervisor.

643-2.01  Materials.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8-feet.

643-3.03  Public Notice.  Add the following:  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of commencing construction, resuming construction after seasonal suspension of work, or any scheduled delay, or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure.  Advertisements shall be published in the following newspapers:

1.  Anchorage Daily News,

2.  Anchorage Times,

3.  Chugiak-Eagle River Star,

4.  Frontiersman,

5.  Valley Sun.

The Contractor shall indicate on the ad order a first preference for the local news section, and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.  Advertisements shall be promptly cancelled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least

forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

643-3.04  Traffic Control Devices.  Add the following to Item 5., Flagging:  Flagger signs are to be equipped with Type A Warning Lights, and shall be used during night time flagging operations.

Add the following:

9.	Construction Equipment.  All measures necessary to safely incorporate construction equipment which does not meet the stipulations contained in Subsection 105-1.12 Load Restrictions, with the travelling public, shall be addressed by the Contractor in an approved Traffic Control Plan.

643-3.08  Construction Sequencing.  Delete this subsection in its entirety and substitute the following:  Throughout the duration of the project, the existing roadway configuration shall be maintained (i.e., the number of lanes and shoulders and their respective widths) except for restrictions to traffic addressed through approved Traffic Control Plans.  Restrictions to traffic such as flagging operations, a one lane road operation, or a detour will not be allowed during the times listed below.

1.	Monday through Thursday from 6:00 AM to 8:00 AM and from 4:30 PM to 7:00 PM.

2.	Friday from 6:00 AM to 8:00 AM and from 4:30 PM to 10:00 PM.

3.	Saturday and Sunday from 6:00 AM to 10:00 PM.

4.	Around any holiday as described below (in addition to times listed in items 1. through 3., above):

a.	If a holiday falls on Monday, from 6:00 AM to 10:00 PM on the day of the holiday.

b.	If a holiday falls on Tuesday, from 6:00 AM to 10:00 PM on the day before the holiday and the day of the holiday.

c.	If a holiday falls on Wednesday or Friday, from 4:30 PM to 10:00 PM on the day before the holiday and from 6:00 AM to 10:00 PM on the day of the holiday.

d.	If a holiday falls on Thursday, from 4:30 PM to 10:00 PM on the day before the holiday, and from 6:00 AM to 10:00 PM on the day of the holiday and the day after the holiday.

5.	During the Alaska State Fair:

a.	Monday through Thursday from 6:00 AM to 8:00 AM and from 4:30 PM to 11:00 PM.

b.	Friday from 6:00 AM to 8:00 AM and from 4:30 PM to 12:00 midnight.

c.	Saturday and Sunday from 6:00 AM to 12:00 midnight.

A portable concrete barrier will be required if an excavation or fill area, as described in Subsection 643-3.04(1), exists within eight feet from the edge of a traveled way.

643-4.01  Method of Measurement.  Add the following to Item 1:  Permanent Construction Signing will not be measured for payment.

Delete the second sentence of the first paragraph under Item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this contract.

Delete the fourth sentence of the first paragraph under Item 2.

Delete the last sentence of the first paragraph under Item 3. and replace with the following:  The quantities to be paid for shall be the number of hours or days that the setups are installed, accepted and maintained in place during the life of this contract.

Add the following:  Fixed Type III barricades will be measured by the linear foot of permanent installation.  Fixed Type III barricades will not be removed upon completion of the project.

643-5.01  Basis of Payment.  Add the following:  Payment for Permanent Construction signing will include all permanent construction signs as detailed on the plans that are installed, accepted, maintained and removed during the life of this contract.

Payment will be made under:

Pay Item No.           Pay Item            Pay Unit

643(6A)      Fixed Type III Barricade   Linear Foot

643(24)       Permanent Construction     Lump Sum

Signing

SECTION 644

SERVICES TO BE FURNISHED

BY THE CONTRACTOR

Special Provisions

644-2.01  Field Office.  Revise this subsection to read:  The project office shall have a minimum 1,000 square feet of floor area, 100 square feet of window area, a thermostatically controlled interior heating system, and attached indoor plumbing and lavatory facilities.  There shall be adequate parking for a minimum of 16 vehicles.  The office shall be located within 5 miles of the project and be made available for occupancy within 10 days of the receipt of Notice-to-Proceed through final acceptance.

644-2.02  Field Laboratory.  Delete the sixth sentence of the first paragraph and substitute the following:  The water supply shall consist of a 500-gallon capacity tank with a pressure pump or a commercial pressurized system.

Modify the second paragraph to include the following:  The lab slab shall be 8 x 10-feet, and installed within an enclosed structure with an exhaust fan.

644-2.06  Scales.  Delete the second paragraph and substitute the following:  Sanitary lavatory facilities, heating, adequate electrical lighting and 120 volt, 60 cycle power shall be furnished to the scale house.

644-2.08  Water Testing.  Add the following subsection:  Prior to initiating work around Rabbit Slough, Knik and Matanuska Rivers, the Contractor will be required to retain an independent test laboratory to test water samples taken by the Engineer.  These samples shall be tested for quality, color, turbidity and suspended solids, in accordance with EPA standards, and the results shall be transmitted directly to the Engineer.

644-3.01  Method of Measurement.  Add the following: Water testing shall be reimbursed based on paid receipts for the authorized tests.

644-4.01  Basis of Payment.  Add the following: Payment for water testing will be made on the receipts for authorized tests plus 15 percent, and shall be considered full compensation for all labor, equipment and materials required to have tests performed.  A change order will not be required to initiate water testing.

Payment will be made under:

Pay Item No.         Pay Item             Pay Unit

644(9)         Water Testing       Contingent Sum

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  Description.  This Training Special Provision is in implementation of 23 U.S. Code 140(a).

As part of the Contractor's equal employment opportunity affirmative action program, the Contractor shall provide on-the-job training aimed at developing full journeymen in the type of trade or job classification involved.  The number of trainees to be trained under this contract is 3.

645-2.01  Objective.  Training and upgrading of minorities and women toward journeyman status is a primary objective of this program.  Accordingly, the Contractor shall make every effort to enroll minority trainees and women to the extent that such persons are available within a reasonable area of recruitment and will be responsible for documenting such efforts in order to demonstrate compliance with this Training Special Provision.  This training commitment is not intended, and shall not be used, to discriminate against any applicant for training, whether a member of a minority group or not.

645-3.01  General.  The Contractor shall determine the distribution of the required number of trainees among the various work classifications based on his needs and the availability of journeymen within a reasonable area of recruitment.

It is the intention of these provisions that training is to be provided in the construction crafts rather than clerk-typists or secretarial-type positions.  Training is permissible in lower level management positions such as office engineers, estimators, timekeepers, etc., where the training is oriented toward construction applications.  Training in the laborer classification may be permitted provided that significant and meaningful training is provided and approved.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Reimbursement for offsite training indicated above may only be made to the Contractor where he does one or more of the following and the trainees are concurrently employed on a Federal-aid project; contributes to the cost of the training, provides the instruction to the trainee or pays the trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit his training proposal for approval, indicating the number of trainees to be trained in each selected classification and the training program to be used.  Furthermore, the Contractor shall specify the starting time for training in each of the classifications.  To this end, completed certification forms, appropriate to the classifications selected, shall be submitted for each trainee.

1.	Trainees in apprenticeship programs currently approved by the U.S. Department of Labor shall be entered on Form 25A311 "Contractor's FHWA Apprenticeship Certification."

2.	Trainees not in approved apprenticeship programs, including laborers and teamsters, shall be entered on Form 25A310 "Contractor's FHWA OJT Certification."  These trainees shall receive at least 500 hours training on the project.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor and approved by the Department.  The Department shall approve any program which will reasonably qualify the trainee for journeyman status in his classification by the end of the overall training program, and which conforms to the Contractor's equal employment obligations.  Existing approved programs shall be considered acceptable except in those cases where the Department has determined that the program is not being administered in a manner consistent with the equal employment obligations stipulated in Federal-Aid provisions.

It is normally expected that a trainee will begin his training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist in his work classification or until he has completed his training program.  It is not required that all trainees be on board for the entire length of the contract.  A Contractor will have fulfilled his responsibilities under this Training Special Provision if he has provided acceptable training to the number of trainees specified.

If, in the judgement of the Contractor, a trainee becomes proficient enough to qualify as a journeyman before the end of the prescribed training period, and the Contractor so employs such trainee, the individual training program will be considered completed.

The Contractor shall furnish each trainee a copy of the program he will follow during training on the project, and with a certification showing the type and length of training satisfactorily completed.  No employee shall be employed as a trainee in any classification in which he has successfully completed a training course leading to journeyman status, or in which he has been employed as a journeyman.

The Contractor shall advise all employees and applicants for employment of available training programs and entrance requirements for each.

The Contractor shall periodically review the training and promotion potential of minority group and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each trainee.

645-3.02  Wages.  Trainees will be paid at least 60 percent of the appropriate minimum journeyman's rate specified in the contract for the first half of the training period, 75 percent for the third quarter of the training period, and 90 percent for the last quarter of the training period, unless apprentices or trainees in an approved existing program are enrolled as trainees on this project.  In that case, the appropriate rates approved by the U.S. Departments of Labor or Transportation in connection with the existing program shall apply to all trainees being trained for the same classification who are covered by this Training Special Provision.

645-3.03  Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the trainees are to be trained by the subcontractor.  Any such subcontracts shall include the appropriate training provisions and pay item.  However, primary responsibility for meeting the training requirements imposed remains with the Contractor.

645-4.01  Method of Measurement.  The Contractor will be credited for each approved trainee employed by him on the project and reimbursed on the basis of man-hours worked, as listed in the certified payrolls.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  Basis of Payment.  Payment will be made at the contract unit price for each accepted man-hour of training performed.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment may be made for training persons in excess of the number specified herein, when approved by the Engineer.

Payment will be made following completion of each approved training program for the project.  No payment will be made to the Contractor if he fails to provide the required training or fails to hire the trainee as a journeyman upon completion of the program, and if such actions indicate a lack of good faith in meeting these requirements.

Payment will be made under:

Pay Item No.          Pay Item          Pay Unit

645(1)          Training Program      Man-Hour

(8/1/88)

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.01  Description.  Add the following:  Item 660(5), Structure Illumination Complete, shall consist of the following work, which when completed will be the plumbing for a future lighting system.  The Contractor shall furnish and install junction boxes, expansion fittings, conduits, anchor bolts, mounting brackets, and lighting standards on Bridge Nos. 1885 and 1889 as detailed on the plans.  In addition, the conduits shall be provided with grounding bushings and pull ropes, and shall be capped and bonded together.  The end of each lighting standard shall be threaded and provided with an end cap.

660-2.09(A)  Wiring.  Add the following between the words "signal" and "conductors" in the seventh paragraph: ......and feeder....

660-2.10  Bonding and Grounding.  Add the following after the first paragraph:  All hardware, including insulated throat grounding bushings, ground rods, and ground rod clamps shall be UL listed.

660-4.01  Installation Details.  Under loops, numbered paragraphs 7 and 9, change "660-2.08" to read "660-2.09(A)".

660-5.02  Backplates.  In the last paragraph change "660-2.16" to read "660-2.15".

660-7.01  Basis of Payment.  In the first paragraph, modify line eleven to read:  "involved in furnishing and installing, modifying, maintaining and".

(9/1/89)

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  Fine Aggregate For Concrete.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

703-2.02  Coarse Aggregate For Concrete.  In the first sentence, insert ", class B," after "AASHTO M 80".

(5/12/89)

SECTION 705

JOINT MATERIALS

705-2.03  Bridge Seal.  Revise the requirements of ASTM D 1000 Line Call Out for both Elastic Compression Seals and Extruded Strip Seals to read:

M4AA 514 A13B13C12F19

SECTION 708

PAINTS

Special Provisions

708-2.01  Paint for Steel Structures.  Delete this subsection in its entirety.

SECTION 709

REINFORCING STEEL AND WIRE ROPE

Special Provisions

709-2.01  Reinforcing Steel.  Add the following:

Epoxy-Coated Reinforcing Bars            ASTM A775

(including patching material)

SECTION 715

STEEL FOR PILES

Special Provisions

715-2.02  General Requirements.  Delete the second paragraph under Item 1. and substitute the following:  Cylindrical pipe piles shall conform to the requirements of ASTM A252 with the following additions and revisions:

1.	Minimum yield point - 50,000 psi

2.	Minimum ultimate strength - 75,000 psi

3.	Minimum elongation in 8 inches - 18 percent

4.	Minimum elongation in 2 inches - 25 percent

5.	Minimum  charpy impact - 15 ft-lbs @ 10F

6.	Minimum individual piece length - 10 feet

7.	Minimum length, finished piece - 40 feet

8.	Wall thickness - 1.0 inch + .05 inch, except that wall thickness of 0.80 inch minimum may be used on the abutment piles of both bridges and the pier piles for piers 2 and 8 of the Knik River Bridge and piers 2 and 6 of the Matanuska River Bridge.

9.	Spiral welded pipe shall not be used.

10.	Shop butt welds shall be radiographed in conformance with AASHTO/AWS D 1.5.  10 percent of the length of each weld shall be tested.  If a rejectable defect is found, then 100 percent of the lengths of butt welds in that piece shall be tested.  Field welds are not subject to tests.

Add the following to Item 3.:  Cold rolled sheet pile is acceptable for use on this project.

SECTION 716

STRUCTURAL STEEL

Special Provisions

716-2.02  General Requirements.  Add the following to Item 2.:  A36 and A572 material shall be killed steel, fine-grain practice, except this requirement may be waived for bearing plates, drains, expansion device drains, and concrete rail expansion devices.

Add the following to Item 10.:  The specified Charpy values are based on a specimen size of 10 millimeters by 10 millimeters.  When plate thicknesses do not permit the preparation of full sized specimens, 10 millimeters by 7.5 millimeters specimens shall be used, in which case 75 percent of the tabulated values shall apply.

If the steel tested fails to meet the preceding requirements, the entire plate shall be rejected and shall not be used in the structure.

Table 716-1, Charpy V-Notch Impact Requirements, denotes the minimum impact value required for the average of three specimens.  The minimum impact value permitted on one specimen only in a set of three specimens shall be not less than 70% of the tabulated values.

Charpy values shall be for Group 3.  The (P) frequency of testing shall be used.

Add the following:  A633, Grade C or D, or A537, Class I steel, may be substituted for the A36 or A572 steel wherever specified.  A36 or A572 impact requirements shall apply as appropriate.

Special Provisions

716-2.03  High Tensile Strength Bolts.  Add the following:  All high strength bolts shall be galvanized.

Galvanized "LeJeune" bolts will be considered equivalent to the bolts specified.

Standard Modifications

716-2.03  High Tensile Strength Bolts.  Add the following:  All bolts, nuts, and washers are to be marked with a symbol identifying the manufacturer as required in ASTM A325 Section 14, A490 Section 15, A563 Section

10.7 and 10.8, A194 Section 14, and F436 Section 14.  The supplier shall provide the symbol and address of each manufacturer for all the bolts, nuts, and washers supplied to the project.

The supplier's certification shall provide a corresponding lot number appearing on the shipping package and the certification.  The supplier's certification shall note when and where all testing was done, including the rotational-capacity tests indicated below, and include zinc thickness when galvanized bolts and nuts are used.

The maximum hardness for AASHTO M 164(A325) bolts shall be 33Rc.  The maximum tensile strength shall be 150ksi for bolts 1 inch or less in diameter and 120ksi for larger bolts.

Nuts shall be Grade 2H or DH for black or galvanized fasteners.  For galvanized fasteners the nuts shall be overtapped to the minimum amount required for the fastener assembly.  All nuts, bolts and washers shall have the manufacturers markings on them.

All galvanized nuts shall be lubricated with a lubricant containing a visible dye so a visual check can be made for the lubricant at the time of field installation.  Black bolts shall be "oily" to the touch when installed.  Weathered or rusted bolts shall be cleaned and re-lubricated prior to installation.

High-strength fasteners, black and galvanized, shall be subjected to a rotational-capacity test (AASHTO M 164, Section 8.5) and shall meet the following requirements:

1.	They shall go through two times the required number of turns (from snug tight conditions) indicated in the 1988 Interim AASHTO Bridge Specification, Table 10.17B, in a Skidmore-Wilhelm Calibrator, or equivalent tension measuring device, without stripping or failure.

2. 	During this test, the maximum recorded tension shall be equal to or greater than 1.15 times the Required Fastener Tension, AASHTO Table 10.17A.

3.	The measured torque to produce the Required Fastener Tension shall not exceed the value obtained by the following equation:

Torque = 0.25 PD

Where:  Torque = Measured Torque (Foot-Pounds)

P      = Measured Bolt Tension (Pounds)

D      = Nominal Diameter (Feet)

Proof load tests (ASTM F 606 Method 1) are required for the bolts.  Wedge tests of full size bolts are required in accordance with Section 8.3 of AASHTO M 164.  Galvanized bolts shall be wedge tested after galvanizing.  Proof load tests (AASHTO M 291) are required for the nuts.  The proof load tests for nuts to be used with galvanized bolts shall be performed after galvanizing, overtapping and lubricating.

All galvanized nuts shall be lubricated in accordance with ASTM A563 Section 4.8.  In addition the name, method of application, and dilution of the lubrication applied to the nuts shall be provided with the documentation.

Section 7.4 of ASTM A563 shall be deleted and Section 7.5 changed to read as shown below.  These requirements also apply to 2H nuts covered under ASTM A194.

7.5   Nuts to be used on bolts mechanically zinc coated or on bolts hot-dip zinc-coated, shall be tapped oversize by a diametral amount sufficient to permit assembly on the coated bolt thread, unless other requirements are specified in the inquiry or purchase order.

(5/12/89)

716-2.09  Stainless Steel.  Add the following subsection:  The top plate of the sliding bearings for the bridges shall conform to ASTM A36.

The top plate shall have a stainless steel facing sheet, 20 gage minimum thickness and conforming to ASTM A167, Type 304, bonded to the bottom surface.  The face of the stainless steel in contact with the polytetraflourethylene (TFE) sheet shall have a bright annealed finish.

SECTION 720

ELASTOMERIC PADS

Standard Modifications

720-2.01.  Delete in its entirety and substitute the following:  Elastomeric bridge bearing pads shall conform to the requirements of AASHTO M 251 with the following revisions:

4.2	Elastomeric Material.  Revise the first sentence to read:  The elastomeric compound used in the construction of the bearings shall contain only virgin natural polyisoprene (natural rubber) as the raw polymer; neoprene shall not be used.

4.2.1	Delete in its entirety.

4.2.2	Revise the Line Call Out to read:

M4AA 514 A13B13C12F19Z11

Revise	Z11: Adhesion value as follows:

Steel Laminations - ASTM D429, min

Method B 40 lb/in

Add the following: Z11: Adhesion,

Fabric Laminations - California Test No. 663 min

40 lb/in

4.5	Fabrication Details.  Add the following:

Pads over 3/4 inch in thickness shall be laminated and shall consist of alternate laminations of elastomer and metal or fabric reinforcements.  The outside laminations shall be metal or fabric.  Laminations of elastomer shall be 1/2 inch in thickness.

(5/29/90)

SECTION 724

SEED

Special Provisions

724-2.02  Materials.  Add the following to Table 724-1:

Percent

Seed        Germination Percent   Percent    Sproutable

Type           Period   Purity  Germination     Seed

Bering           14       95        75           71

Hairgrass

(Norcoast)

Baby Blue Eyes   14       99        79           78

(Nemophila

Menzeisii)

Sun Flower       21       99        80           79

(Helianthus

Annus)

Ox Eye Daisy     14       96        88           84

(Chrysanthemum

Leucanthemum)

SECTION 726

TOPSOIL

Standard Modifications

726-2.01  Topsoil.  In the second paragraph, change "not less than 1%" to read "not less than 3%".  (5/12/89)

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01  Embankment Separation and Reinforcement.  Add the following to Item 4:  Water permeability requirement for the separation geotextile shall be a minimum of 0.02 cm/sec.

729-2.02  Subsurface Drainage and Riprap Liner.  Delete Item 1. in its entirety and substitute the following:

1.	Fibers used in the manufacture of geotextiles, and the threads used in joining geotextiles by sewing, shall consist of long chain synthetic polymers, composed of at least 85 percent by weight polyolefins, or polyesters.  The geotextile shall be formed into a stable network such that the filaments or yarns retain their relative position to each other.  Both the geotextile and threads shall be resistant to chemical attack, mildew, and rot.

Delete Item 3. in its entirety and substitute the following:

3.	Woven geotextile shall be woven into a uniform pattern with distinct and measurable openings.  Edges of the cloth shall be selvaged to prevent the outer yarn from pulling away from the cloth.  The fabric shall be free from defects.

Delete Table 729-2 on page 576 in its entirety and substitute the following:

Table 729-2

GEOTEXTILE REQUIREMENTS FOR

SUBSURFACE DRAINAGE AND RIPRAP LINE

_____________________________________________________________

|    Geotextile    |  Test  |Subsurface|     Riprap Liner     |

|     Property     | Method | Drainage |           |          |

|                  | (ASTM) |          |Unprotected| Protected|

|Elongation, % @   | D-4632 |  15-100  |   10-80   |  15-80   |

|Grab Tensile      |        |          |           |          |

|Breaking Load     |        |          |           |          |

|                  |        |          |           |          |

|Grab Tensile      | D-4632 |    90    |    200    |   100    |

|Load, lbs., min.  |        |          |           |          |

|                  |        |          |           |          |

|Burst Strength    | D-3786 |   125    |    350    |   200    |

|psi., min.        |        |          |           |          |

|                  |        |          |           |          |

|Water             | D-4491 |   0.8    |    0.5    |   0.5    |

|Permittivity,     |        |          |           |          |

|1/sec., min.      |        |          |           |          |

|                  |        |          |           |          |

|Apparent Opening  | D-4751 | 0.212    |    0.6    |   0.6    |

|Size, mm., max.   |        |          |           |          |

|                  |        |          |           |          |

|Ultraviolet       | D-4355 |    70    |     70    |    70    |

|Degradation @ 500 |        |          |           |          |

|hour exposure, %  |        |          |           |          |

|Strength Retained,|        |          |           |          |

|min.              |        |          |           |          |

|                  |        |          |           |          |

|Geotextile        | D-4759 |  Pass    |   Pass    |  Pass    |

|Acceptance, Pass  |        |          |           |          |

|or Fail           |        |          |           |          |

|                  |        |          |           |          |

NOTES:

1.	Geotextile Property Values = Minimum average roll values @ 95% confidence level in the weaker principal direction

2.	0.212 mm. = US Standard Sieve Size #70.

3.	0.600 mm. = US Standard Sieve Size #30.

APPENDIX A

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

Sample Wave Equation

Work Sheets