SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available from the Department of Transportation and Public Facilities, located at 4111 Aviation Avenue in Anchorage.  Information may be obtained as follows:

Copies for review and reproduction information for the computations and are available in the Plans Room, (907) 266-1674.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA 1988 STANDARD SPECIFICATIONS

FOR HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.27  Holidays.  Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third Monday in January.

3.	President's Day - Third Monday in February.

(5/7/91)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  Qualification of Bidders.  Delete the second paragraph.  (5/12/89)

Special Provisions

102-1.01  Qualification of Bidders.  Add the following:  The bidder, by signing the proposal and under penalty of perjury under the laws of the United States, certifies that, except as may be noted on the proposal, the bidding firm or any person associated therewith is not currently under suspension, debarment, voluntary exclusion, or determination of ineligibility by any federal agency; has not been suspended, debarred, voluntarily excluded or determined ineligible by any federal agency within the past 3 years; does not have a proposed debarment pending; and has not been indicted, convicted, or had a civil judgement rendered against (it) by a court of competent jurisdiction in any matter involving fraud or official misconduct within the past 3 years.

Exceptions to the above shall be noted by the bidder on the proposal or on an attachment thereto.

Exceptions will not necessarily result in denial of award, but will be considered in determining bidder responsibility.  For any exception noted, indicate to whom it applies, initiating agency, and dates of action.  Providing false information may result in criminal prosecution or administrative sanctions.

(3/18/88)

Standard Modifications

102-1.06 Preparation of Proposal.  Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

(5/7/91)

102-1.07  Non-Responsive Proposals.  Delete item 3. in its entirety and substitute the following:

3.	If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to the bidder at any one bid letting, as provided in Subsection 102-1.06, Preparation of Proposal.  (5/7/91)

102-1.07  Non-Responsive Proposals.  Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)

102-1.12  Addenda Requirements.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  Consideration of Proposals.  Add the following:  The apparent low bidder shall, within 5 working days following the bid opening, submit either a list of all firms with which the prime Contractor intends to execute subcontracts for the performance of the contract or a statement that the bidder intends to perform the work without subcontractors.  The list shall include the following information for each proposed subcontractor:

1.	name,

2.	business address,

3.	Alaska business license number,

4.	Contractor's registration number

5.	work to be performed, and

6.	approximate dollar amount of work to be performed.

If the apparent low bidder fails to submit either a list of subcontractors or a statement that the bidder intends to perform the work without subcontractors, the apparent low bidder will be found not to be a responsible bidder and may be required to forfeit the bid security.  The Department will then consider the next lowest bidder for the award of the contract.

If a bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess  of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this Subsection.

If a contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department, or,

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the contract with the bidder involving work for which the subcontractor was  listed,

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or,

9.	is determined by the Contracting Officer not to be responsible.

(9/1/90)

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  Changes.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)

Special Provisions

104-1.02  Changes.  Delete the first three paragraphs and substitute the following:  The Engineer reserves the right to make, in writing, at any time during the work, such changes in quantities and such alterations in the work as are necessary to satisfactorily complete the project.  Such changes in quantities and alterations shall not invalidate the contract nor release the surety, and the Contractor agrees to perform the work as altered.

If the alterations or changes in quantities significantly change the character of the work under the contract, whether or not changed by any such different quantities or alterations, an adjustment, excluding loss of anticipated profits, will be made to the contract.  The basis for the adjustment shall be agreed upon prior to the performance of the work.  If a basis cannot be agreed upon, then an adjustment will be made either for or against the Contractor in such amount as the Engineer may determine to be fair and equitable.

If the alterations or changes in quantities do not significantly change the character of the work to be performed under the contract, the altered work will be paid for as provided elsewhere in the contract.

The term "significant change" shall be construed to apply only to the following circumstances:

1.	When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction, or

2.	When a major item of work, as defined elsewhere in the contract, is increased in excess of 125 percent or decreased below 75 percent of the original contract quantity.  Any allowance for an increase in quantity shall apply only to that portion in excess of 125 percent of original contract item quantity, or in case of a decrease below 75 percent, to the actual amount of work performed.

(4/13/89)

104-1.03  Differing Site Conditions.  Delete in its entirety and substitute the following:  During the progress of the work, if subsurface or latent physical conditions are encountered at the site differing materially from those indicated in the contract or if unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the work provided for in the contract, are encountered at the site, the party discovering such conditions shall promptly notify the other party in writing of the specific differing conditions before they are disturbed and before the affected work is performed.

Upon written notification, the Engineer will investigate the conditions, and if he determines that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any work under the contract, an adjustment, excluding loss of anticipated profits, will be made and the contract modified in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment which results in a benefit to the Contractor will be allowed unless the Contractor has provided the required written notice.

(4/13/89)

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  Authority of the Engineer.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02, Changes.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)

Special Provisions

105-1.06  Cooperation With Utilities.  Add the following:  The Contractor shall request locates from all the Utilities having facilities in the area.  Their telephone numbers are as follows:

Matanuska Electric Association			745-3231

Matanuska Telephone Association			745-3121

DOT/PF Maintenance & Operations (Palmer)	745-2159

ENSTAR Natural Gas Company (Engineering)	264-3740

City of Wasilla Public Works Department		373-9075

Rogers Cablevision						373-2288

Standard Modifications

105-1.12  Load Restrictions.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless otherwise allowed by an approved Traffic Control Plan.  (5/7/91)

Special Provisions

105-1.17  Claims for Adjustment and Disputes.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (1/1/91)

Add the following:	Legal actions will be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/29/87)

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  Source of Supply and Quality Requirements.  Add the following:  All steel products which are to be incorporated into the work shall be produced in the United States except that minor amounts of steel products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract cost, or $2500, whichever is greater.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel products into the project.

(11/9/84)

106-1.02  Local Material Sources.  Under Item 1. General, add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)

Add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement will be given to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01  Laws to be Observed.  Add the following:  Specific Equal Employment Opportunity Responsibilities of Federal-Aid Construction Contractors.

1.	General

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form 25D-55) and these Special Provisions which are imposed pursuant to Section 140 of Title 23, U.S.C., as established by Section 22 of the Federal-Aid Highway Act of 1968.  The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the equal employment opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State highway agencies and the Federal Government in carrying out equal employment opportunity obligations and in their review of his/her activities under the contract.

c.	The Contractor and all his/her subcontractors holding subcontracts not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of equal employment opportunity:  (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as Contractors and subcontractors.)  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.

2.	Equal Employment Opportunity Policy

The Contractor will accept as his operating policy the following statement which is designed to further the provision of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include:  employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprentice-ship and/or on-the-job training.

3.	Equal Employment Opportunity Officer

The Contractor will designate and make known to the Engineer and equal employment opportunity officer (hereinafter referred to as the EEO Officer) who will have the responsibility for and must be capable of effectively administering and promoting an active Contractor program of equal employment opportunity and who must be assigned adequate authority and responsibility to do so.

4.	Dissemination of Policy

a.	All members of the Contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the Contractor's equal employment opportunity policy and contractual responsibilities to provide equal employment opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

(1)	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the Contractor's equal employment opportunity policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor's equal employment opportunity obligations within thirty days following their reporting for duty with the Contractor.

(3)	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the Contractor's procedures for locating and hiring minority group employees.

b.	In order to make the Contractor's equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

(1)	Notices and posters setting forth the Contractor's equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The Contractor's equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

5.	Recruitment

a.	When advertising for employees, the Contractor will include in all advertisements for employees the notation:  "An Equal Opportunity Employer."  All such advertisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority group applicants, including, but not limited to, State employment agencies, schools, colleges and minority group organizations.  To meet this requirement, the Contractor will, through his EEO Officer, identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority group applicants may be referred to the Contractor for employment consideration.

In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor's compliance with equal employment opportunity contract provisions.  (The U.S. Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or women, or obligates the Contractor to do the same, such implementation violates Executive Order 11246, as amended.)

c.	The Contractor will encourage his present employees to refer minority group applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures with regard to referring minority group applicants will be discussed with employees.

6.	Personnel Actions

Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The Contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The Contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with his obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the Contractor will inform every complainant of all of his avenues of appeal.

7.	Training and Promotion

a.	The Contractor will assist in locating, qualifying, and increasing the skills of minority group and women employees, and applicants for employment.

b.	Consistent with the Contractor's work force requirements and as permissible under Federal and State regulations, the Contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.  In the event the Training Special Provision is provided under this contract, this subparagraph will be superseded as indicated.

c.	The Contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.	The Contractor will periodically review the training and promotion potential of minority group and women employees and will encourage eligible employees to apply for such training and promotion.

8.	Unions

If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and female employees.  Actions by the Contractor either directly or through a Contractor's association acting as agent will include the procedures set forth below:

a.	The Contractor will use best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

b.	The Contractor will use best efforts to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The Contractor is to obtain information as to the referral practices and policies of the labor union except that the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the Contractor, the Contractor shall so certify to the State highway department and shall set forth what efforts have been made to obtain such information.

d.	In the event the union is unable to provide the Contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the Contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minority group persons and women.  (The U.S. Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees.)  In the event the union referral practice prevents the Contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such Contractor shall immediately notify the State highway agency.

9.	Subcontracting

a.	The Contractor will use his best efforts to solicit bids from and to utilize minority group subcontractors or subcontractors with meaningful minority group and female representation among their employees.  Contractors shall obtain lists of minority-owned construction firms from State highway agency personnel.

b.	The Contractor will use his best efforts to ensure subcontractor compliance with their equal employment opportunity obligations.

10.	Records and Reports

a.	The Contractor will keep such records as are necessary to determine compliance with the Contractor's equal employment opportunity obligations.  The records kept by the Contractor will be designed to indicate:

(1)	the number of minority and nonminority group members and women employed in each work classification on the project,

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to Contractors who rely in whole or in part on unions as a source of their work force),

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority group subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such records must be retained for a period of three years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the State highway agency and the Federal Highway Administration.

c.	The Contractor will submit an annual report to the State highway agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form PR 1391.  If on-the-job training is being required by "Training Special Provision", the Contractor will be required to furnish State of Alaska Form 25A312.

(4/8/83)

107-1.11  Protection and Restoration of Property and Landscape.  Add the following to the third paragraph:  The Contractor shall not stockpile material nor dispose of excess fill at any site suspected of containing contaminated material.  Contaminated material may include but not be limited to, substances hazardous to humans, wildlife or wetlands habitat.

Add the following:  The Contractor shall report immediately to the Engineer any hazardous material discovered, exposed, or released into the air, ground, or water during construction of the project.  Also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery.  Hazardous materials include, but are not limited to, petroleum products, oils, solvents, paints, and chemicals that are toxic, corrosive, explosive, or flammable.  (5/7/91)

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.

The Contractor shall do no work, trespass, stockpiling, staging, or parking in or around any watercourse.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

Standard Modifications

107-1.13  Responsibility for Damage Claims.  In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries".  (5/12/89)

Special Provisions

107-1.15 Contractor's Responsibility for Work.  Add the following to the end of the first paragraph:  Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense.  (5/7/91)

Standard Modifications

107-1.16  Contractor's Responsibility For Utility Property And Services.  In the last sentence of the third paragraph delete: "by the local fire authority."  (5/12/89)

Special Provisions

107-1.16  Contractor's  Responsibility for Utility Property and Service.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mislocates the facility in the field by more than 2.5-feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.

(9/1/89)

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  Subletting of Contract.  Delete the third paragraph on page 56 and substitute the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Driver's License.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	the owner-operator's right to control the manner in which the work is to be performed,

2.	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3.	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4.	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each owner-operator.  The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.

(5/7/91)

Standard Modifications

108-1.03  Prosecution and Progress.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule". (5/12/89)

Special Provisions

108-1.03  Prosecution and Progress.  In the first paragraph, delete the words "At this time" and substitute:  "Five working days before the preconstruction conference".  (5/7/91)

Add the following:  The Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail work activities, manpower involved by trade, work hours, equipment involved and the location of the work to be performed.

Preparation of the two week work plans will not be paid for directly, but will be subsidiary to Item 640(1), Mobilization and Demobilization.

108-1.05  Character of Workmen, Methods and Equipment.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer. (2/1/90)

108-1.06  Determination and Extension of Contract Time.  Add the following:

4.	Suspensions of Work Ordered by the Engineer.  If the performance of all or any portion of the work is suspended or delayed by the Engineer in writing for an unreasonable period of time (not originally anticipated, customary, or inherent to the construction industry) and the Contractor believes that additional compensation and/or contract time is due as a result of such suspension or delay, the Contractor shall submit to the Engineer in writing,

a request for adjustment within 7 calendar days of receipt of the notice to resume work.  The request shall set forth the reasons and support for such adjustment.

Upon receipt, the Engineer will evaluate the Contractor's request.  If the Engineer agrees that the cost and/or time required for the performance of the contract has increased as a result of such suspension and the suspension was caused by conditions beyond the control of and not the fault of the Contractor, its suppliers, or subcontractors at any approved tier, and not caused by weather, the Engineer will make an adjustment (excluding profit) and modify the contract in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment will be allowed unless the Contractor has submitted the request for adjustment within the time prescribed.

No contract adjustment will be allowed under this clause to the extent that performance would have been suspended or delayed by any other cause, or for which an adjustment is provided for or excluded under any other term or condition of this contract.

(4/13/89)

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  General.  Add the following:  When more than one variety of material or work item is specified for a single pay item number, letter or numeric suffixes will be included within the parenthesis to differentiate the types.   (9/1/89)

Standard Modifications

109-1.03 Scope of Payment.  Delete the last sentence of the fourth paragraph.  (5/7/91)

Special Provisions

109-1.04  Compensation for Altered Quantities.  In the third indented subparagraph, delete the following: ", except that the total payment for the item shall not exceed 75 percent of the total amount bid for the item".  (4/13/89)

109-1.05  Compensation for Extra Work.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)

109-1.07  Payment For Materials on Hand.  Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project will be at a location acceptable to the Engineer. (9/1/89)

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  Description.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  Interpretation.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  Essential Contract Provision.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  Definitions and Terms.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular Contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03 Item 3. for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a Contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  Utilization Goal.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Goal in order to be eligible for award of this contract.

120-3.01  Determination of Compliance.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  Good Faith Effort.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE Credit.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that ALL of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least one of which must be working on this project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  Default of DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, ALL of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02, Good Faith Effort.

120-4.01  Method of Measurement.  The Contractor shall be entitled to count toward the DBE Goal those monies allowed by the Engineer in 120-3.03.04 as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be

responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100 percent.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60 percent of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  Basis of Payment.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01, Utilization Goal, until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per subsection 120-3.03, Item 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

Payment or Deduction will be made under:

Pay Item No.        Pay Item         Pay Unit

120(1)        DBE Adjustment   Contingent Sum

(5/5/89)

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01  Materials.  Add the following: Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material.  Native material shall be utilized for pipe bedding and backfill below or outside the pavement structure if the material meets the minimum requirements of Selected Material, Type C as specified in Subsection 703-2.07, Selected Material.  Pipe bedding shall also pass a 3-inch sieve.  (9/1/89)

204-3.01  Construction Requirements.  Add the following to the third paragraph:  Native material utilized for pipe bedding and backfill outside the pavement structure shall be placed in layers and compacted as approved by the Engineer.

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-3.01  Proportioning.  Revise this subsection as follows:  In Table 501-1, Class of Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S and W concrete.  (9/1/89)

501-3.02  Batching.  Add the following to item No. 5, Batching:  Furnish the mix design number and a list of all ingredients, their individual weights, and moisture content of the various aggregates wuth each truck load or batch of concrete supplied.  (5/7/91)

SECTION 606

GUARDRAIL

Special Provisions

606-4.01  Method of Measurement.  Add the following:  Removal and reconstruction of guardrail for the installation of conduit and electroliers P18-P20 will not be measured for payment.

606-5.01  Basis of Payment.  Add the following:  Removal and reconstruction of guardrail for the installation of conduit and electroliers P18-P20 will not be paid for directly, but will be subsidiary to Pay Item 660(3A), Highway Lighting System Complete, Parks Highway-Alpine Avenue to Crusey Street.

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01  Materials.  Add the following to the end of the first sentence of the fifth paragraph, "and the Alaska Traffic Manual."

Delete paragraphs 7 and 8 and substitute the following:  Sign posts and bases shall be of the types specified.  Structural aspects of design and materials for sign supports shall comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals.

Concrete for steel-reinforced slip base and breakaway base foundations shall be Class A, conforming to the requirements of Section 501, Structural Concrete.  Concrete for other sign foundations may be class W.

(5/7/91)

615-3.01  Construction Requirements.  Add the following to the sixth paragraph:  When existing signs are to be salvaged the remaining foundation shall be removed or obliterated to six inches below the level of the surrounding grade.

Add the following after the sixth paragraph:  Salvaged sign panels shall be delivered to the State Maintenance Yard at Palmer.

615-3.02  Sign Placement and Installation.  Add the following:  Existing signs shall not be removed until new signs providing the same information to motorists have been installed.  If necessary, they may be temporarily relocated to a location approved by the Engineer.

615-5.01  Basis of Payment.  Add the following: Salvaging signs, maintaining existing signs until they are no longer needed and temporary relocation of existing signs will not be paid directly, but will be subsidiary to Item 615(1), Standard Signs.  (9/1/89)

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-2.01  Method of Measurement.  Delete item 3. and substitute the following:

3.	When the letter of project completion has been issued and the Contractor has made all the required submittals the remaining balance of the amount for this item will be paid.  (5/7/91)

640-3.01 Basis of Payment.  Add the following:  Preparation of the two week work plans in accordance with Section 108, will not be paid for directly, but will be subsidiary to Item 640(1), Mobilization and Demobilization.

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01  Description.  Add the following: Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of Subsection 107-1.11, Protection and Restoration of Property and Landscape.  Additional silt fencing may be required at other sites as directed by the Engineer.

641-1.03  Materials.  Add the following subsection:  The silt fence filtration material shall meet the requirements shown in Table 729-4 in Section 729, Geotextiles.

The silt fence support framework shall be finished 4 x 4-inch wood, 3-inch diameter wood, #6 rebar with PVC sleeves, iron pipe or other posts capable of supporting the installation, as approved by the Engineer.

641-2.01 Construction Requirements.  Add the following:  The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other hazardous substances to the land and water.  The temporary erosion and pollution control plan shall address the measures the Contractor shall implement in the containment, cleanup, and disposal of such substances as well as the methods to be utilized for disposing of waste oil or other hazardous substances generated by construction equipment or activities.  The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.  The plan shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

The silt fence shall be installed as detailed on the plans.  The base of the silt fence will be installed on the existing slope embankment and not in wetlands.  The silt fence shall not be removed until adequate vegetative growth insures no further erosion of the slopes.  The silt fence shall be removed and disposed of off the project upon completion of construction at those sites.  The fabric shall be cut off at ground level and the wire and posts shall be removed.  The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands.

641-3.01  Method of Measurement.  Add the following:  Silt fence will be measured by the linear foot along the top of the fence.

641-4.01  Basis of Payment.  Add the following:  Payment for item 641(2), Silt Fence, will be full compensation for all labor, equipment and materials required to furnish, install, maintain and remove the silt fence in accordance with these specifications.

Payment will be made under:

Pay Item No.           Pay Item          Pay Unit

641(2)              Silt Fence        Linear Foot

(6/1/90)

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  Description.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirement", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix A.

642-3.01  Construction Requirements.  Add the following:

12.	The Contractor's survey crews shall comply with approved traffic control plans.  Crews shall coordinate their activities with the project's Worksite Traffic Supervisor.

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  Traffic Control Plan.  Add the following to the third paragraph:  All TCPs submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

643-1.04 Construction Phasing Plan.  Revise the first sentence to read as follows:  A Construction Phasing Plan shall be submitted at least five working days prior to the preconstruction conference for approval by the Engineer and shall consist of the following:  (5/7/91)

643-2.01  Materials.  Add the following under Item 3., Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8-feet.

643-3.03  Public Notice.  Add the following:  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of commencing construction, resuming construction after seasonal suspension, or any scheduled delay, or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure.  All advertisements shall be published in the following newspapers:

1.	Anchorage Daily News,

2.	Anchorage Times,

3.	Frontiersman, and,

4.	Valley Sun.

The Contractor shall indicate on the Advertising order a first preference for the local news section and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and telephone number.  Advertisements shall be promptly canceled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

643-3.04  Traffic Control Devices.   Delete Item 1., Embankments and substitute the following:

1.	Excavation Areas.  Barricades, drums or cones shall be placed to delineate open trenches, jacking or drilling pits and other excavations and hazardous areas when they exist within thirty (30) feet of the edge of travelled way.  Spacing of devices along these areas shall be as directed by the Engineer but in no case greater than a distance equal in feet to twice the posted speed limit in miles per hour.

Pits for electrolier foundations shall be covered with a steel plat capable of supporting a 4000 pound vehicle if left unfilled overnight.

643-3.08  Construction Sequencing.  Delete this subsection in its entirety and substitute the following:  Throughout the duration of the project, the existing roadway configuration shall be maintained, i.e., the number of lanes and shoulders and their respective widths.  A restriction to traffic shall be considered any work operation or traffic control setup that reduces the number of lanes or lane widths, stops traffic, or causes the 85th percentile speed to fall more than 10 mph below the posted speed limit.  Restrictions to traffic will not be allowed unless described below.  An approved Traffic Control Plan is required before any restriction to traffic is implemented.

1.	Parks Highway.

Shoulder widths on the Parks Highway may be reduced to two feet.

One lane road operations will be allowed but will be restricted to between the hours of 8:00 PM and 6:00 AM, Monday through Thursday.

2.	Knik/Goose Bay Road and South Big Lake Road.

One lane road operations will be allowed except between the hours of 6:00 AM and 8:00 AM and 4:00 PM and 6:00 PM, Monday through Friday.

Existing guardrail may have to be removed to install conduit and electroliers P18-P20.  A maximum of two 12.5 foot sections may be removed at one time.  A minimum of four Type II Barricades with type 'A' flashing warning lights shall be placed to delineate the opening during periods of inactivity, and to delineate the work are when equipment and workers are present.  All guardrail shall be restored at the end of each work shift.

643-4.01  Method of Measurement.  	Delete the second sentence of the first paragraph under Item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this contract.

Add the following:  Advance Construction Signs will be measured and paid for as Item 643(4), Construction Signs.

SECTION 644

SERVICES TO BE FURNISHED

BY THE CONTRACTOR

Special Provisions

644-2.01  Field Office.  Delete this subsection in its entirety and substitute the following:  The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work through 30 days after the Engineer issues a letter of project completion.  The following office requirements shall be met:

1.	A minimum of 500 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 350 square feet of floor space.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power.

4.	A minimum of 60 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 6 vehicles.

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within five miles of the project.

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.01  Description.  Add the following:  Item 660(2), Flashing Beacon System Complete shall consist of the following work along South Big Lake Road and Aero Lane at Big Lake Elementary School.  The Contractor shall install three school flashers in accordance with the school flasher detail shown on the plans, furnishing:  conductors, conduits, junction boxes, flashing beacon control unit and all other required hardware to provide a functional beacon system.  The work to furnish and install the three S5-1 type signs shall be included in Item 615(1), Standard Signs.

660-2.02  Removing and Replacing Improvements.  Add the following:  The existing asphalt pavement to be removed for the construction of the conduit runs shall be replaced with new asphalt pavement meeting the requirements of subsection 702-2.01, Asphalt Cements for type AC-5, and subsection 703-2.04, Aggregate for Plant Mix Asphalt Pavement, for Asphalt Concrete, Type II.

For disposal of removed asphalt, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529, ext. 246.

660-2.04  Poles, Steel Pedestals and Posts.  Add the following:  All poles shall be designed for 100 MPH wind speeds with gusts to 130 MPH.

660-2.05  Conduit.  Add the following:  Where called for on the plans, rigid metal conduit shall be placed in a metal casing under existing pavement.  The metal casing shall be galvanized, schedule 40 black iron pipe meeting the requirements of ASTM A-53 and ASTM A-120.  The casing shall be placed by boring or drilling only.  When obstructions are encountered during boring or drilling operations, upon approval, test holes with a maximum diameter of 8 inches may be cut in the pavement to clear the obstruction.  Boring or drilling pits shall be kept a minimum of 10-foot clear of the edge of any pavement.  These pits shall be delineated in accordance with Section 643-3.04 of the Special Provisions.

Where polyethylene conduit is called for, high density polyethylene duct meeting the requirements of NEMA Specification TC-7 shall be installed.  Ninety degree PVC elbows shall be attached to the polyethylene conduit with screw-type compression connectors at all J-Boxes.  A bare No. 8 grounding conductor shall be installed in all runs of polyethylene conduit.

660-2.08  Conductors.  Add the following to Table 660-1:

Conductors                             Wire    AWG      Band

/Cable        Circuit             Color/No.  No.     Legend

3	Highway Illumination				1       6   	 Circuit No.

Highway Illumination				2			or		 Circuit No.

Highway Illumination				3	    Larger

_________________________________________________________________

3	Service to Controller				1			6					"SIG"

Neutral							2			or			No Band

Spare							3	    Larger		No Band

_________________________________________________________________

Standard Modifications

660-2.09(A)  Wiring.  In the seventh paragraph, insert "and feeder" between "signal" and "conductors".

(5/7/91)

Special Provisions

660-2.10  Bonding and Grounding.  Add the following after the first paragraph:  All hardware, including insulated throat grounding bushings, ground rods, and ground rod clamps shall be UL listed.

660-3.05  Controller Cabinet.  Add the following after the second sentence of numbered paragraph (6) on page 463:  The thermostat shall be set at thirty-five (35) degrees F.

Standard Modifications

660-4.01  Installation Details.  In numbered paragraphs 7 and 9, under "Loops", change "660-2.08" to read "660-2.09(A), Wiring".  (5/7/91)

660-5.02  Backplates.  In the last paragraph, change "660-2.16" to read "660-2.15, Painting".

Special Provisions

660-6.01  Luminaires.  Add the following paragraph:  No paint may be applied to the reflecting surface of luminaire reflectors.

660-6.07  Salvaging Electrical Equipment.  Add the following to the  first paragraph:  All equipment to be salvaged shall be delivered to the State Maintenance yard in Palmer.

Delete the first sentence of the fourth paragraph and substitute the following:  Unless otherwise specified, junction boxes (not including lids), underground conduit, conductors, foundations and detectors shall become the property of the Contractor and shall be removed from the highway right-of-way.  Junction box lids shall be salvaged to the State Maintenance Yard in Palmer.

660-7.01  Basis of Payment.  In the first paragraph, modify line eleven to read:  "involved in furnishing and installing, modifying, maintaining and".

(9/1/89)

Add the following:  Bored Casings, 4" minimum diameter, will be paid by the linear foot and payment so made shall be full compensation for furnishing all materials, equipment, labor, tools and incidentals to provide the casings for roadway conduit crossings shown on the plans.

SECTION 661

ELECTRICAL LOAD CENTERS

Special Provisions

661-1.02  Equipment List(s) and Drawings.  Add the following subsection:  The Contractor shall submit for review and approval, within 30 days following award of the contract, 8 collated copies of a portfolio of

equipment and materials which he proposes to install.

The portfolio(s) shall consist of a table of contents which includes each item's intended use(s) and the following:

1.	For materials on the Approved Products List:  a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

2.	For materials not on the Approved Products List:  catalog cuts that include the manufacturer's name, type of product, size, model number, conformance specifications, and supplemented by other data as may be required, including manufacturer's maintenance and operations manuals, or sample articles.

This information may be included in the portfolio

for 660 items.

The Department will not be liable for any material purchased, labor performed, equipment used, or delay to the work before all equipment and materials have been reviewed and approved.

661-2.01  Materials.  Add the following:   The wiring configuration for each load center type shall be in accordance with the wiring diagram indicated on the load center detail sheet.  Circuit breaker ratings shall be as shown in the load center summary for each location.  Dead panels shall be indelibly labeled with the circuit number and the direction of the circuit run from the load center.

When the load centers are ready to be energized, the Contractor shall request and coordinate an electrical inspection of the load centers from the local authority having jurisdiction, allowing at least 5 working days before the inspection is needed.  The Contractor shall be present during the inspection to assist in accessing the cabinets and to answer questions.  The Contractor shall correct the deficiencies noted in each load center.

Payment of any fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be considered incidental to the Section 661 items.  (9/1/89)

661-4.01  Method of Measurement.  Add the following:  Modification of existing load centers including wiring and breakers will not be measured for payment.

661-5.01  Basis of Payment. Add the following:  Modification of existing load centers including wiring and breakers will not be paid for directly, but will be subsidiary to Pay Item 660 (3A), Highway Lighting System Complete, Parks Highway-Alpine Avenue to Crusey Street; and Pay Item 660 (3D), Highway Lighting System Complete, Knik/Goose Bay Road at Edlund Road.

SECTION 670

TRAFFIC MARKINGS

Standard Modifications

670-3.01  Construction Requirements.  In the last paragraph under Item 2., insert "pneumatic" immediately before "roller".  (5/12/89)

SECTION 702

ASPHALT MATERIALS

Standard Modifications

702-2.04  Storage And Application Temperatures.  In Table 702-1, change storage temperatures for ACs from "340 Max" to "325 Max".  (5/12/89)

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  Fine Aggregate For Concrete.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

703-2.02  Coarse Aggregate For Concrete.  In the first sentence, insert ", class B," after "AASHTO M 80".

703-2.03 Aggregate for Base.  Add the following to the list under the first paragraph:

Plastic Index      AASHTO T-90        6 max

Special Provisions

703-2.04  Aggregate for Plant Mix Asphalt Pavement.  In the second paragraph, after Fine Aggregate, delete the remainder of the sentence after "thereof" and add the following:

The fine aggregate will meet the following requirements:

Plastic Index     AASHTO T-90     4 max.

Sodium Sulfate    AASHTO T-104   15 percent max.

Soundness Loss

SECTION 729

GEOTEXTILES

Special Provisions

729-2.04 Temporary Silt Fence.  Add the following subsection:  The geotextile supplied shall meet the physical and mechanical properties listed in Table 729-4.

Table 729-4

GEOTEXTILE REQUIREMENTS

FOR TEMPORARY SILT FENCE

┌─────────────────┬────────────┬───────────────┬──────────────┐

│	Geotextile     │    Test    │     Fence     │     Self-    │

│  Property       │   Method   │   Supported   │   supported  │

│                 │   (ASTM)   │  Requirements │  Requirements│

├─────────────────┼────────────┼───────────────┼──────────────┤

│                 │            │               │              │

│  Grab Tensile   │   D-4632   │       90      │      90      │

│  Strength,      │            │               │              │

│  lb., min.      │            │               │              │

│                 │            │               │              │

│  Elongation     │            │               │              │

│  at 50%         │            │               │              │

│  minimum        │   D-4632   │      N/A      │      50      │

│  Tensile        │            │               │              │

│  Strength,      │            │               │              │

│  (45 lb.),      │            │               │              │

│  % max.         │            │               │              │

│                 │            │               │              │

│  Water          │            │               │              │

│  Permittivity   │   D-4491   │      0.01     │     0.01     │

│  1/sec., min.   │            │               │              │

│                 │            │               │              │

│  Apparent       │            │               │              │

│  Opening Size,  │   D-4751   │      0.84     │     0.84     │

│  mm., max.      │            │               │              │

│                 │            │               │              │

│  Ultraviolet    │            │               │              │

│  Degradation @  │            │               │              │

│  500 hour       │   D-4355   │        70     │       70     │

│  exposure, %    │            │               │              │

│  Strength       │            │               │              │

│  Retained, min. │            │               │              │

│                 │            │               │              │

│  Geotextile     │            │               │              │

│  Acceptance,    │   D-4759   │       Pass    │      Pass    │

│  Pass or Fail   │            │               │              │

└─────────────────┴────────────┴───────────────┴──────────────┘

Notes:

1.	Geotextile Property Value = Minimum average roll values 95% confidence level in the weaker principal direction.

2.	0.85 mm. = U.S. Standard Sieve Size 20

APPENDIX A

CONSTRUCTION SURVEYING REQUIREMENTS