PART 4

STANDARD MODIFICATIONS
AND SPECIAL PROVISIONS

to the

STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION


2004 EDITION

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

- Publications.  The following are available from the Plans Room:

a.	Standard Specifications for Highway Construction, 2004 Edition.  ($25.00)

b.	Alaska Test Methods Manual (Lab & Field), 2007 Edition.  ($25.00)

c.	Alaska Storm Water Pollution Prevention Plan Guide, January 19, 2005.

d.	Quantity Computations

e.	Cross Sections

f.	Subsurface Exploration and Foundation Recommendations, Tudor Road/Lake Otis Parkway Intersection Improvements, 58890, May 2007

g.	Corrective Action Plan, Tudor Road/Lake Otis Parkway Intersection Improvements, 58890, April 2008

h.	Hydrological and Hydraulic Report, Tudor Road/Lake Otis Parkway Intersection Improvements, 58890, March 2007

- Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix D.

- Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

- Laborers Mechanics Minimum Rate of Pay.  The current Laborers Mechanics Minimum Rate of Pay contains information on remote sites and per diem.  The Department of Labor has issued WHPL #197, which further clarifies this requirement.

- Hiring Apprentices.  Administrative Order 226, issued July 24, 2005 establishes a 15% goal for hiring apprentices in certain job categories; on highway, airport, harbor, dam, tunnel, utility, or dredging projects awarded by the Alaska Department of Transportation and Public Facilities.  This Administrative Order will apply to projects advertised after September 1, 2005, where the project construction cost exceeds 2.5 million dollars.

For additional details, visit http://labor.state.ak.us//lss/forms/ApprenHireReq.pdf

- Disadvantaged Business Enterprise (DBE) Program.  Based on guidance from the US Department of Transportation’s General Counsel, effective January 10, 2006 the Alaska Department of Transportation and Public Facilities implemented a Race Neutral Disadvantaged Business Enterprise (DBE) program by setting 0% project goals on all highway, mass transit and airport projects.  All forms and reports required under the existing DBE program will continue to be required under these 0% goal contracts.

Specifically Contractors must continue to report creditable DBE participation/payments on the Monthly Summary of Disadvantaged Business Enterprise Participation Form 25A336.  This will allow the Department to continue to accurately report DBE participation to the Federal Highway Administration, Federal Transit Administration and Federal Aviation Administration.

Contractors must also continue to provide opportunities for DBE firms to participate on highway, mass transit and airport projects as appropriate.  A 0% DBE participation goal does not relieve the Contractor of the Requirement to provide equal opportunity in subcontracting, supplies or other services offered by DBE firms.

Any questions about this notice may be directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, jon.dunham@alaska.gov

- Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0650.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Subsection 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

- Asphalt Laydown Temperatures.  The Department may monitor laydown temperatures using a thermal imaging camera.  Unsatisfactory areas will be subject to additional testing and/or replacement at the Contractor’s expense as specified in Division 400.

- High Visibility Clothing.  The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retroreflectivity.  See Subsection 643-3.11.

- Signals, Lighting Poles, Load Centers, Controller Assemblies:  The Plans and Specifications are revised for these items including, anchors to the foundations, foundations and conduit installation.

- Section 670 Traffic Markings:  This section is recently revised including but not limited to submittal requirements and method of measurement.

- Subsection 107-1.05 of the Standard Specifications for Highway Construction 2004 has been modified to include the Monthly Employment Reporting requirements for construction projects with American Recovery and Reinvestment Act of 2009 (ARRA) funding.  Note the requirement for a Contractor DUNS number.  See www.dnb.com for information about obtaining a DUNS number.

- Subsections 105-1.18 and 108-1.07.  This project includes two interim completion dates which are specified in Subsections 105-1.18 and 108-1.07.

- Curb and Gutter.  All curb and gutter must be installed prior to the installation of the final lift of Hot Mix Asphalt.

- Subsections 401-3.14 and 408-3.14.  New longitudinal joint elevation differential repair requirements are included in this Contract.  See Subsections 401-3.14 Joints and 408-3.14 Joints.

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS.  Replace the definition of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.  (1/1/06)E22

101-1.03 DEFINITIONS, PLANS.  Delete text of PLANS and replace with:  The Department’s Contract drawings, profiles, typical cross-sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.  (01/27/07)E32

101-1.03 DEFINITIONS.  Add the following definition:  QUALIFIED PRODUCTS LIST.  A list of companies and products that the Department has found conforms to the SSHC.  (01/27/07)E36

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.  Replace the second paragraph with the following:  The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in Subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine Subsection 106-1.02 Material Sources for further information about material source development.  (1/1/06)E23

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after “If a bidder is a corporation, the bid must be signed by a corporate officer,” add or agent.  (6/30/04)E18

SECTION 103

PERFORMANCE AND PAYMENT BONDS

Standard Modifications

Delete Subsection 103-1.05 and replace with the following:

103-1.05 PERFORMANCE AND PAYMENT BONDS.  The successful bidder shall furnish all required Performance and Payment Bonds on forms provided by the Department for the sums specified in the Contract.  If no sum is specified, the successful bidder shall comply with AS 36.25.010.  The Surety on each bond may be any corporation or partnership authorized to do business in the state as an insurer under AS 21.09 or two individual sureties approved by the Contracting Officer.

If individual sureties are used, two individual sureties must each provide the Department with security assets located in Alaska equal to the penal amount of each bond.  Any costs incurred by the Contractor and the individual Surety are subsidiary and shall be borne by the Contractor or the individual Surety.  In no event will the Department be liable for these Costs.

Individual sureties shall provide security by one, or a combination, of the following methods:

1.	Escrow Account, with a federally insured financial institution, in the name of the Department.  Acceptable securities include, but are not limited to, cash, treasury notes, bearer instruments having a specific value, or money market certificates.

2.	Irrevocable letters of credit, with a financial institution approved by the Contracting Officer.

3.	Cashier’s or certified check, made payable to the State of Alaska issued by financial institutions approved by the Contracting Officer.

These bonds and security assets, as applicable, shall remain in effect for 12 months after the date of final payment or, if longer, until all obligations and liens under this Contract are satisfied, including, but not limited to, obligations under Subsection 107-1.19.

The Department may, in its discretion, notify the bonding company or Surety of any potential default or liability.

The Contractor shall substitute, within five working days, another bond or surety acceptable to the Department if an individual Surety or the Surety on any bond furnished in connection with the Contract:

1.	Becomes insolvent or is declared bankrupt;

2.	Loses its right to do business in any state affecting the work;

3.	Ceases to meet Contract requirements;

4.	Fails to furnish reports of financial condition upon request; or

5.	Otherwise becomes unacceptable to the Department.

When approved by the Contracting Officer, the Contractor may replace:

1.	An individual surety with a corporate surety; or

2.	Posted collateral with substitute collateral.

Failure to maintain the specified bonds or to provide substitute bonds when required under this section may be grounds for withholding contract payments until substitute bonding is obtained, and may, in the Department’s discretion, be grounds for declaring the Contractor in default.

E65 (01/12/09)

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.01 INTENT OF CONTRACT.  Add to the end of this subsection:

The Contractor is responsible for the means, methods, techniques, sequence or procedures of construction, safety, quality control, and to perform or furnish the work in accordance with the Contract documents.

E58 (07/28/08)

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  In the third paragraph, delete (24"x36") and replace with (22"x34")

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS.  In the first sentence of the first paragraph after “Work performed and materials furnished shall conform to the Plans and Specifications,” add and approved Working Drawings.

In the first sentence of the second paragraph after “Work or material not conforming to the Plans and Specifications,” add and approved Working Drawings.  E33(1/27/07)

Special Provisions

105-1.06 COOPERATION WITH UTILITIES.  Add the following:  Request locates from the utilities having facilities in the area.  Use the Alaska Digline, Inc., Locate Call Center for the following utilities:

ALASKA DIGLINE, INC.

Locate Call Center Anchorage:  811

who will notify the following:

ACS

Anchorage Water and Wastewater Utilities

Chugach Electric Association

DOT&PF Street Lights, State of Alaska

ENSTAR Natural Gas

GCI Communications

MOA Street Maintenance Department

Municipality of Anchorage

Municipal Light and Power

Call the following utilities and agencies directly:

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent’s phone number for this project.

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.

Right-of-way and/or Construction surveying is required before utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1) Construction Surveying, if the Contractor is  required to provide the surveying as part of the contract and/or

- Under Item 642(3) Three-Person Survey Party, if the construction or right-of-way staking required by the utility is either in advance of the 2-week work plan or not required by the contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking

Coordinate tie-ins between new load centers and transformers.  Contact Joe Miller with CEA (762-4634).

All utility relocation work occurring concurrent with construction work will be covered by the Contractors SWPPP, traffic control and replacement of asphalt, curb and gutter and concrete sidewalk.

Specific Utility Coordination

ENSTAR Natural Gas Company.  ENSTAR Natural Gas Company (ENSTAR) operates natural gas facilities throughout the project limits.  Some of the facilities will be relocated in conjunction with the project.

ENSTAR will perform a Cathodic Protection Sweep of the project once all underground excavation has been completed on the project and prior to any improvements such as asphalt are placed over their facilities. Notify ENSTAR at 334-7740, four (4) calendar days prior to when the sweep is to be performed, ENSTAR must be provided free access to the project and one (1) calendar day to complete the sweep.

The following locations will require coordination with the contractor’s schedule and activities to allow ENSTAR to relocate their following facilities:

Lake Otis Parkway Station 217+00 to 226+00 RT. and Tudor Road Station 127+00 to 133+00 RT.  ENSTAR’s existing steel gas line from station Lake Otis Parkway station 217+00 Rt. north to Tudor Road and then east to station 132+75 Rt. is in conflict with the proposed improvements and will be relocated. ENSTAR will place a new plastic gas line at approximately five feet inside the right of way line on the Rt. side through the area in conflict.  The contractor will allow ENSTAR fifteen (15) calendar days to complete this work.  Following installation and cutover of the new line, and re-establishment of the services to the adjacent properties, ENSTAR will abandon the existing steel gas line in place.

ENSTAR will place a plastic gas line crossing of Lake Otis Parkway and tie it to the existing steel gas line along the west side of the right of way, and place a ground wire connection to the existing above ground pipe test station.  The east end of the crossing will be connected to the new plastic gas line as described above.  The contractor will allow ENSTAR two (2) calendar days to complete the crossing and connection.  Following installation and cutover of the crossing, ENSTAR will abandon the existing steel crossing at Station 221+05.

Lake Otis Parkway Station 228+00 to 232+70 RT.  ENSTAR’s existing steel gas line which parallels the east side of Lake Otis Parkway from station 228+00 Rt. to 232+70 Rt. is in conflict with proposed improvements and will be relocated. ENSTAR will place a new plastic gas line inside the east right of way line through this area in conflict.  The contractor will allow ENSTAR six (6) calendar days to place the line and re-establish the services on the east side.  ENSTAR will be installing the new facilities on the road side of the new retaining wall between stations 230+51 Rt. and 230+84 Rt. and behind the wall from stations 231+32 Rt. to 232+39 Rt., this will require that prior to wall construction that the new facilities be installed and that the wall limits be staked.

ENSTAR will also place a plastic gas line crossing Lake Otis at 229+05 tying to the existing plastic gas line feeding the mall on the west side.  The contractor will allow ENSTAR a day to complete the crossing in coordination with a road closure, or 2-days if coordinated with lane closures.  The existing steel gas line that runs along the west side of the right of way is proposed to be abandoned by ENSTAR.  In order to accomplish the abandonment, ENSTAR will need to tie the steel gas line that extends west from the intersection of Lake Otis with 42nd, into the feed from north on Lake Otis.  ENSTAR will require a day to provide a crossing of Lake Otis at Station 232+55 if coordinated with a total closure of Lake Otis Parkway, or two days if accomplished with partial lane closures.  Following installation and cutover of the crossings and the new north-south line, ENSTAR will abandon the steel gas line on the west and the steel gas line on the east side of Lake Otis Parkway.

ALASKA COMMUNICATIONS SYSTEMS (ACS) Alaska Communication Systems (ACS) operates communication facilities within the project corridor. Some of the facilities will be relocated or adjusted in conjunction with the project.  The following locations will require coordination with the contractor’s schedule and activities to allow ACS to relocate/adjust their following facilities:

Lake Otis Parkway  Near station 223+00 an existing PVC crossing of Lake Otis Parkway will be extended beyond the new west sidewalk limit.  On the west side of the crossing an existing handhole will have existing top door section removed and replaced with a  ring and cover which will be adjusted to meet the final grade.  ACS will remove the bollards around the handhole. Allow ACS three (3) calendar days to extend the crossing and replace the top section of the handhole. Provide ACS final grade staking at the handhole prior to the work.

At station 223+70 the existing manhole will have the ring and cover adjusted to meet final grade. Allow ACS one (1) calendar day to adjust the manhole. Provide ACS final grade staking at the manhole prior to the work.

Near station 228+00 Rt. the existing pedestal will be retired.  A new pedestal will be installed behind the new sidewalk limit.  The existing conduit will be extended beyond the new sidewalk limits to the new pedestal.  New cable will be placed in the duct between MH C992 and the new pedestal. Allow ACS five (5) calendar days to extend the crossing, place the new pedestal and cable, complete the splicing and abandon the old pedestal.

At station 229+52 the existing manhole will have the ring and cover adjusted to meet the final grade. Allow ACS one (1) calendar day to adjust the manhole. Provide ACS final grade staking at the manhole prior to the work.

GENERAL COMMUNICATION INC. (GCI)  GCI Cable, Inc. (GCI) operates cable TV facilities on the east side of Lake Otis Parkway south and north of Tudor Road.  The cable is within the project limits and the proposed project improvements will conflict with the existing cables.  Relocation or adjustment is required. The following locations will require coordination with the contractor’s schedule and activities to allow GCI to relocate/adjust their following facilities:

Lake Otis Parkway  From station 216+60 Rt. to 223+12 Rt., the existing GCI cables will be relocated to the outer edge of the ROW along the east side. At station 223+12 Rt., the new facilities will extend east to an existing riser pole to connect to the existing lines. Allow GCI seven (7) calendar days to install the new facilities and abandon the existing in conflict.

From station 228+05 Rt. to 239+92 Rt., the existing GCI cable will be relocated to the outer edge of the ROW along the east side. At station 239+92 Rt., the new facilities will extend east to an existing riser pole to connect to the existing lines. Allow GCI seven (7) calendar days to install the new facilities and abandon the existing in conflict. GCI will be installing the new facilities on the road side of the new retaining wall between stations 230+51 Rt. and 230+84 Rt. and behind the wall from stations 231+32 Rt. to 232+39 Rt., this will require that prior to wall construction that the new facilities be installed and that the wall limits be staked.

CHUGACH ELECTRIC ASSOCIATION (CEA)  Chugach Electric Association, Inc (CEA) operates overhead and underground electrical facilities along the south side of Tudor Road  and on Lake Otis Parkway south of Tudor Road. The underground circuits and cabinets are within the project limits and the proposed project improvements will conflict with a portion of the existing circuits.  Relocation or adjustment is required.

The following locations will require coordination with the contractor’s schedule and activities to allow CEA to relocate/adjust their following facilities:

CEA’s existing UG primary circuit along the east side of Lake Otis Parkway falls within the proposed improvements starting at approximately station 219+85 Rt.. At this location new conduits will tie into the existing conduits and will parallel the ROW line to SC 650 at station 223+10 Rt., where the conduits will connect to the SC. A New 3Ø circuit will then be installed between SC 652 located at station 217+15 Rt. and SC 650. The existing circuit will be removed and the conduit abandoned.

Existing PM 0396 located at station 225+45 Rt. falls within the roadway and will be replaced.  The existing 1Ø circuit from JB 0375 at station 219+75 Rt. to PM 0396 will be within the roadway improvements and will be abandoned in place. New PM 0593 located at station 224+70 and a new PM 0592 (120/240) located at station 224+65 will be installed to supply power to LC’s A and B.  A new 2” HDPE with conductor will be installed from JB 0375 to feed PM 0593. A new 2” HDPE with conductor will also be installed from PM 0788 at station 223+10 Rt. to feed PM 0592. Allow CEA fifteen (15) calendar days to install the new facilities and abandon or retire the existing in conflict.

Existing Vault 0387 located at station 223+10 Rt. will fall within the outside lane and will be adjusted to final grade. Allow CEA two (2) calendar days to adjust the existing manhole to finish grade. Prior to the adjustment finish grade must be established and verified while the adjustment is taking place.

MUNICIPAL LIGHT & POWER (ML&P)  Municipal Light & Power (ML&P) operates overhead and underground electrical facilities along the north side of Tudor Road  and on Lake Otis Parkway north of Tudor Road. The underground circuits and cabinets are within the project limits and the proposed project improvements will conflict with a portion of the existing circuits.  Relocation or adjustment is required.

The following locations will require coordination with the contractor’s schedule and activities to allow ML&P to relocate/adjust their following facilities:

Along the north side of Tudor Road, west of Lake Otis Parkway: ML&P’s existing underground primary circuits will be in conflict with the proposed widening from approximate station 115+30 Lt. to 119+85 Lt. and will require relocation. New vaults will installed at station 112+99, 49 ft. Lt. and at station 119+69, 110 ft. Lt., entrapping the existing circuits. Existing vault 71A will be retired, as will the existing cables between SC30 and new vault 71A.  New conduit and cable will be installed under the pathway between the two vaults. Once the new circuits have been cutover the existing cables and conduit will be abandoned in place. Allow ML&P seven-teen (17) calendar days to install the new facilities and abandon or retire the existing in conflict.

Along the east side of Lake Otis Parkway, north of Tudor Road: ML&P’s existing underground primary circuits will be in conflict with the proposed widening and retaining wall construction from approximate station 229+80 Rt. to 232+45 Rt. and will require relocation consisting of the following. There will be three (3) new vaults installed at (12J) station 229+74, 106 ft Rt., (22N) at station 229+75, 335 ft. Rt. and (13F) at station 232+87, 111 ft. Rt.

The existing circuits in conflict will be replaced by new circuits that will run from vault 22N through Vault 12J with one extending across Lake Otis to the existing switch cabinet (SC 28) at station 229+80, 64 ft. Lt., through existing duct. The two other circuits will turn north and extend to vault 13F located on 42nd Avenue, being installed in existing ducts. An additional circuit will exit the ROW to the east at station 231+29 Rt. terminating at an existing riser pole. Two additional connections are also required out of vault 22N to the south, one terminating at an existing riser pole, the second terminating in new SC 22. Allow ML&P fifty-four (54) calendar days to install the new facilities and abandon or retire the existing in conflict.

An underground circuit will be installed along Laurel Street between new poles 32H, installed in the overhead circuit which extends east from pole 22B, and pole 32G installed in the overhead circuit which extends east from pole 12E. Allow ML&P three (3) calendar days to install the new facilities.

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:  The following state and municipal owned projects may be under construction concurrently with this project:

| Project Name | DOT&PF Project Number | MOA Project Number |
| --- | --- | --- |
| 48th Avenue/Boniface Parkway Extension |  | 05-030 |
| Muldoon Road Resurfacing, 36th to Glenn Hwy. | 50810 |  |
| HSIP: 6th Avenue at Muldoon Road Safety Improvements | 57254 |  |
| Muldoon Road at Northern Lights Boulevard Intersection Improvements | 56613 |  |
| Central Region Safety Improvement Project (Debarr Road, Boniface to Beaver) | 51210 |  |

Coordinate traffic control, construction, and material hauling operations with the prime Contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other Contracts.

105-1.13 MAINTENANCE DURING CONSTRUCTION.  Add the following at the end of this subsection:  Costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various Contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer’s opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance.  The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance.  If the Contractor fails to take the corrective action within the specified time, the Engineer may:

- Suspend the work until corrective maintenance is completed;

- Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

- Employ others for corrective maintenance and deduct the cost from the Contract amount.

E33(01/27/07)

Standard Modifications

105-1.15 PROJECT COMPLETION.  In the second paragraph, second sentence, delete:  “Subsection 621-3.04” and replace with:  Subsections 618-3.06 and 621-3.04.

In the third paragraph, first sentence, delete:  “Subsection 621-3.04” and replace with:  Subsections 618-3.06 and 621-3.04.

E59 (07/28/08)

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION.  Modify the first paragraph, Item 4; after “DOLWD” add and State Department of Revenue.  (6/30/04)E19

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following:  Appeals to the superior court under AS 36.30.685 must be filed in the Third Judicial District.  (03/21/01)R93

Add the following subsection 105-1.18:

105-1.18 INTERIM COMPLETION DATES

- Complete all storm drain work, waterline, sanitary sewer, conduit crossings, detector loop installation, curb and gutter work, cub ramp installation, and final lift of hot mix asphalt paving by July 15, 2010.

- Complete pavement markings by August 1, 2010.

- The Contract Completion date for all remaining work is October 30, 2010.

SECTION 106

CONTROL OF MATERIAL

Standard Modifications

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  In fifth paragraph, in two places remove the text: “Approved Products List” and replace with:  Qualified Products List.  E36(01/27/07)

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, before award of the contract.

Steel and iron products which are incorporated into the work shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one-tenth of one percent (0.001) of the total contract amount, or $2,500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape, or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting, or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap, pig iron, and processed, palletized, and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 U.S. Code Section 1001 and 1020.  (02/07/05)R13

Standard Modifications

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a, delete text and replace with:  Utilize Useable Excavation according to Subsection 104-1.04 before using material sources listed in Subsection 106-1.02.4.  When there is insufficient useable excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources.  Replace the first paragraph with the following:  The Contractor shall utilize Useable Excavation according to Subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

d.	Available Sources.  Replace the second paragraph with the following:  When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

e.	Excluded Material Sources.  Replace the paragraph with the following:  Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material sources or any portion of a material source, at any time after Contract award that is determined by material testing to be unsuitable for use on the project.  (1/1/06)E24

- Standard Modifications

Add new subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE.  The Contractor shall complete a Submittal Register, and shall submit it to the Engineer on forms provided by the Department.  The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified project documents.  The Contractor shall fill it out sequentially by bid item and allow at least three spaces between bid items.  The Submittal Register shall list working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to:  Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Traffic Control Plan, Storm Water Pollution Prevention Plan, Quality Control Program, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, Disadvantaged Business Enterprise (DBE) payment documentation and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items.  If the number of copies of a submittal is not otherwise specified, three copies shall be required.  On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet.  The Contractor may use forms provided by the Department or a similar form of the Contractor’s choice as approved by the Department.  The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received.  The Department will return submittals to the Contractor as either:  approved, conditionally approved with the conditions listed, or rejected with the reasons listed.  The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections.  The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department.  The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract item.

When material invoices, freight bills and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); project name and number where material will be incorporated; manufacturer, product number, quantity and cost.

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.  Add the following:  No vegetation removal shall occur during the bird-nesting period from May 15 through July 15.

Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor’s operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

The Department has received the following permits on the Contractor’s behalf:

| Permit | Issuing Agency | Permit Number | Date of Issue | Date of Expiration |
| --- | --- | --- | --- | --- |
| Flood Hazard Permit | MOA | 08-0011-00 | 6/6/2008 | N/A |
| Noise Permit | MOA-DHHS | FA0006120-2008 | 9/15/2008 | 9/14/2009 |

Provide information to comply with the U.S. Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from the Contractor.

The MOA will renew the noise permit.

Standard Modifications

107-1.05 FEDERAL AID PROVISIONS.  Add the following after paragraph two:

Monthly Employment Reports.  Submit Monthly Employment Reports on Form 25D-1589.  The Contractor shall submit both a hard copy with signed certification statement, and an electronic file copy in excel spreadsheet format, to the Engineer.

Each Monthly Employment Report is due at 5:00 pm five calendar days after the last Friday of the reporting month.

For each occurrence where a Monthly Employment Report is not submitted on or before the due date, the Department will deduct liquidated damages from the monies owed the Contractor in the amount of twenty-five hundred dollars ($2,500).  In addition to any damages for failure to report on-time, the Department will withhold one hundred percent (100%) of payment for all progress payments due the Contractor, until all Monthly Employment Reports which are due but have not been submitted are complete and delivered to the Project Engineer.  No interest will be paid on amounts withheld due to Contractor’s failure to submit Monthly Employment Reports on time and as required in this subsection.

Submit Monthly Employment Reports that include:

	Contractor’s name and address.

	Reported Month:  mm/yyyy.

	Certification Statement:

“Any intentional misrepresentation or omission made in connection with the attached Monthly Employment Report may be cause for suspension, a determination of non-responsibility on future bids, and may be cause for revocation of award, default, or debarment.  The person or entity making the false statement or omission is subject to any and all civil and criminal penalties available pursuant to applicable state and federal law.

I certify the information contained in the attached Monthly Employment Report is true, correct, and complete.  (Signature and printed name of the person preparing the Monthly Employment Report, and Date)”

Each month the Contractor shall provide all information required by the Form 25D-1589.  Each form   25D-1589 Monthly Employment Report shall include:

	Report Month:  The month and year covered by the report, as mm/yyyy.  The reporting month includes the Saturday following the last Friday of the preceding month to and including the last Friday of the reporting month.

	Contracting Agency:  “State”

	Federal-Aid Project Number:  The federal-aid project number included on the title sheet of the plans.

	State Project Number:  The AKSAS project number included on the title sheet of the plans.

	Project Location:  “Alaska”

	Contractor Name and Address:  The name and address of the Contractor, including street address, city, state, and zip code.

	Contractor DUNS Number:  The Contractor’s unique nine-digit number issued by Dun & Bradstreet.  Followed by the optional 4 digit DUNS Plus number.

	Employment Data:  The Contractor shall report the direct, on-the-project jobs for their workforce and the workforce of all subcontractors, lower tier subcontractors, and owner-operators active during the reporting month.  These jobs include all workers actively engaged in work on the jobsite or actively engaged in work directly related to the project occurring in the project office, in the home office or telework from a home or other alternative office location.  This also includes any engineering personnel, inspectors, sampling and testing technicians, and lab technicians performing work directly in support of the project.  This does not include material fabricator’s material suppliers such as steel culverts, guardrail and does not include engineering personnel, inspectors, sampling and testing technicians, and lab technicians employed by the Department or the Department’s consultant.  The form requests specifically:

○	Subcontractor Name:  The name of each subcontractor, lower tier subcontractor, and owner-operator that was active on the project for the reporting month.

○	Employees:  The number of project employees on the Contractor’s workforce each month, and the number of project employees for each of the active subcontractors, lower tier subcontractors, and owner-operators for the reporting month.  Do not include material suppliers.

○	Hours:  The total hours on the specified project for all employees reported on the Contractor’s project workforce that month, and the total hours for all project employees reported for each of the active subcontractors, lower tier subcontractors, and owner-operators that month.

○	Payroll:  The total dollar amount of wages paid by the Contractor that month for employees on the project, and the total dollar amount of wages paid by each of the active subcontractors, lower tier subcontractors, and owner-operators that month.  Payroll includes wages only, and does not include overhead or indirect costs.

	Prepared by:

○	Name:  The person responsible for preparation of the form and their job title.

○	Date:  The date that the Contractor completed the employment form.  Reported as mm/dd/yyy.

ES17-042709

Form 25D-55 H Required Contract Provisions for Federal-Aid (FHWA) Construction Contracts.  The FHWA no longer requires the contractor to fill out FHWA Form 47, Statement of Materials and Labor Used By Contractors on Highway Construction Involving Federal Funds. Section VI Records of Materials, Supplies and Labor of Form 25D-55H is no longer applicable to highway construction contracts.

Title VI Requirements. During the performance of this contract, the contractor, for itself, its assignees and successors in interest (hereinafter referred to as the "contractor") agrees as follows:

(1)	Compliance with Regulations: The contractor shall comply with the Regulation relative to nondiscrimination in Federally-assisted programs of the Department of Transportation (hereinafter, "DOT") Title 49, Code of Federal Regulations, Part 21, and the Federal Highway Administration (hereinafter "FHWA") Title 23, Code of Federal Regulations, Part 200 as they may be amended from time to time, (hereinafter referred to as the Regulations), which are herein incorporated by reference and made a part of this contract.

(2)	Nondiscrimination: The Contractor, with regard to the work performed by it during the contract, shall not discriminate on the grounds of race, color, or national origin, sex, age, and disability/handicap in the selection and retention of subcontractors, including procurements of materials and leases of equipment.  The contractor shall not participate either directly or indirectly in the discrimination prohibited by 49 CFR, section 21.5 of the Regulations, including employment practices when the contract covers a program set forth in Appendix B of the Regulations.

(3)	Solicitations for Subcontractors, Including Procurements of Materials and Equipment: In all solicitations either by competitive bidding or negotiation made by the contractor for work to be performed under a subcontract, including procurements of materials or leases of equipment, each potential subcontractor or supplier shall be notified by the contractor of the contractor's obligations under this contract and the Regulations relative to nondiscrimination on the grounds of race, color, or national origin, sex, age, and disability/handicap.

(4)	Information and Reports: The contractor shall provide all information and reports required by the Regulations or directives issued pursuant thereto, and shall permit access to its books, records, accounts, other sources of information, and its facilities as may be determined by the DOT&PF or the FHWA to be pertinent to ascertain compliance with such Regulations, orders and instructions. Where any information required of a contractor is in the exclusive possession of another who fails or refuses to furnish this information the contractor shall so certify to the DOT&PF, or the FHWA as appropriate, and shall set forth what efforts it has made to obtain the information.

(5)	Sanctions for Noncompliance: In the event of the contractor's noncompliance with the nondiscrimination provisions of this contract, the DOT&PF shall impose such contract sanctions as it or the FHWA may determine to be appropriate, including, but not limited to:

(a.)	withholding of payments to the contractor under the contract until the contractor complies, and/or

(b.)	cancellation, termination or suspension of the contract, in whole or in part.

(6)	Incorporation of Provisions: The contractor shall include the provisions of paragraphs (1) through (6) in every subcontract, including procurements of materials and leases of equipment, unless exempt by the Regulations, or directives issued pursuant thereto.

The contractor shall take such action with respect to any subcontract or procurement as the DOT&PF or the FHWA may direct as a means of enforcing such provisions including sanctions for non-compliance: Provided; however, that, in the event a contractor becomes involved in, or is threatened with, litigation with a subcontractor or supplier as a result of such direction, the contractor may request the DOT&PF to enter into such litigation to protect the interests of the DOT&PF, and, in addition, the contractor may request the United States to enter into such litigation to protect the interests of the United States.

E66(10/13/09)

ARRA Required Contract Provisions.  Section 902 of the American Recovery and Reinvestment Act (ARRA) of 2009 requires that each contract awarded using ARRA funds must include a provision that provides the U.S. Comptroller General and his representatives with the authority to:

(1)	examine any records of the contractor or any of its subcontractors, or any State or local agency administering such contract, that directly pertain to, and involve transactions relating to, the contract or subcontract; and

(2)	interview any officer or employee of the contractor or any of its subcontractors, or of any State or local government agency administering the contract, regarding such transactions.

Accordingly, the Comptroller General and his representatives shall have the authority and rights as provided under Section 902 of the ARRA with respect to this contract, which is funded with funds made available under the ARRA.  Section 902 further states that nothing in this section shall be interpreted to limit or restrict in any way any existing authority of the Comptroller General.

Section 1515(a) of the ARRA provides authority for any representatives of the Inspector General to examine any records or interview any employee or officers working on this contract.  The contractor is advised that representatives of the inspector general have the authority to examine any record and interview any employee or officer of the contractor, its subcontractors, or other firms working on this contract.  Section 1515(b) further provides that nothing in this section shall be interpreted to limit or restrict in any way any existing authority of the Comptroller General.

The Contractor shall insert, in each subcontract, all of the stipulations contained in these ARRA Required Contract Provisions, and further require their inclusion in any lower tier subcontract or purchase order that may in turn be made.  The ARRA Required Contract Provisions shall not be incorporated by reference in any case.  The prime contractor shall be responsible for compliance by any subcontractor, lower tier subcontractor, and owner-operator, with these ARRA Required Contract Provisions

ES17-042709

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Change the first sentence to the following:  When operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.  R7(05/29/02)

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following:  If required water for construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.  (05/29/02)R7

Standard Modifications

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following paragraphs:

  - Restoring Areas.  Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed.  The original condition of an area shall be determined as follows:  Before beginning operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition.  After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs.  Before demobilization the Contractor shall repair damages attributed to its operations.  The Contractor agrees that costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

  - Material Disposal Sites.  Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result there from, together with permits required by law for such dumping.  A copy of such permission, waiver of claims, and permits shall be filed with the Engineer before beginning work on private property.  The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.

E35(01/27/07)

Special Provisions

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise (DBE), and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

DBE Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

DOT&PF Training Program Request	Form 25A-310

Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.  (01/22/02)S80

SECTION 108

PROSECUTION AND PROGRESS

### Special Provisions

108-1.01 SUBLETTING OF CONTRACT.  Delete paragraph four and replace with the following:

Submit the Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or a subcontractor sublets any portion of the Contract.  The certification will be accepted by the Department in lieu of written approval of subcontracts.  The Department maintains the authority to review subcontracts, require prior written approval of subcontracts, and to deny permission to sublet work.  The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

1.	The Contractor shall ensure the following for each subcontract (agreement):

  - The Department is furnished with one completed Contractor Self certification, Form 25D-042, and two copies of the subcontract signed by both parties and including item descriptions and prices of subcontracted work before the subcontracted work begins;

  - The subcontractors have submitted a Bidder Registration, Form 25D-6;

  - The required prompt payment provisions of AS 36.90.210, as well as other items listed in Form 25D-042, are included in the subcontracts;

  - The subcontractors pay current prevailing rate of wages according to subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for work performed on the project; and

  - Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.  R57(01/02/08)

Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete the last sentence of the first paragraph in Item 1, A progress schedule, and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.  (12/13/02)R261M98

108-1.07 FAILURE TO COMPLETE ON TIME.  Delete the first sentence of the first paragraph and substitute with the following:

For each calendar day that the work remains incomplete after the expiration of the contract time or the interim completion dates as set forth in Subsection 105-1.18 Interim Completion Dates, the liquidated damages per day given in the table below shall be deducted from any monies due the Contractor:

Delete Table 108-1 and replace with the following:

TABLE 108-1
DAILY CHARGE FOR LIQUIDATED DAMAGES
FOR EACH CALENDAR DAY OF DELAY

| Completion Date | Daily Charge |
| --- | --- |
| July 15, 2010 | $2,400 |
| August 1, 2010 | $1,500 |
| October 30, 2010 | $3,000 |

SECTION 109

FINAL PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Under subtitle Electronic Computerized Weighing System Item (1), add the following to the end of the first sentence:  “, CD, or a USB device.”

109-1.05 COMPENSATION FOR EXTRA WORK.  Under Item 3, Equipment, Item a, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.  (4/31/05)R14

Standard Modifications

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:  The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of Subsection 105-1.16.  (6/30/04)E11

Special Provisions

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract.  Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department’s federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as the Department deems appropriate.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.  The following definitions will apply.

- Broker.  A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF).  The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment.  The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself.  To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work.  Other relevant factors will be considered.  The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

- DBE.  An enterprise which is a for-profit small business concern.

- that is at least 51% owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51% of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee.  Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts.  Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer.  A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification.  For purposes of soliciting DBE participation on a project and to count toward a Contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report.  Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer.  A DBE certified by the Department in a supply category that:

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount.  A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE.

- Phase I - Bid.  Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award.  The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment.  Written commitments from DBEs to be used on the project.  The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report.  Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation.  Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal.  If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal.  If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and cannot document the minimum required Good Faith Efforts (as outlined in Subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer.  At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work.  The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement.  If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  In the event the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal.  The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE’s work that cannot be replaced.

120-3.02 GOOD FAITH EFFORT.

- Good Faith Effort Criteria.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening.  It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder cannot achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department’s most current DBE Directory at least 7 calendar days prior to bid opening.  The bidder must give the DBEs no less than 5 days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs will be consistently applied.  DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor.  Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder.  Allegations of non-competitive DBE quotes must be documented and verifiable.  A DBE quote that is more than 10% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service.  Bidders must have a non-DBE subcontractor quote for comparison purposes.  Such evidence shall be provided in support of the bidder’s allegation.  Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE’s accepted quote.  This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding.  Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor’s subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration.  Under the provisions of 49 CFR Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration.  The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection.  As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so.  If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder.  The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appeal able to USDOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work.  Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.  CUF is limited to that of a:

- regular dealer,

- manufacturer,

- broker,

- subcontractor,

- joint-venture, or

- prime contractor.

- Determination of Commercially Useful Function.  In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking.  The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm.  A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker.  (This does not affect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of:

- the Engineer’s approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE’s work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE’s certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work will be performed with the DBE’s own equipment.  Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department.  The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor’s operations such as fuel, maintenance, office facilities, portable bathrooms, etc., are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- Subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions.  The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE.  Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer’s subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal.  The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, Items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of No CUF.  Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE.  Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination.  The Engineer’s decisions on CUF matters are not administratively appeal able to USDOT.

120-3.04 DEFAULT OF DBE.  In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with Items c through h of subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE’s work that cannot be replaced.

120-4.01 METHOD OF MEASUREMENT.  The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.  This shall include DBE trucking firms certified as a subcontractor and not a broker.  Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value.  The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE’s participation in the joint venture agreement, as certified for this project by the Department.  The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for subsection 120-3.04 Item 3), the Department will also consider this unsatisfactory work.  Unsatisfactory work may result in disqualification of the Contractor from future bidding under subsection 102-1.13 and withholding of progress payments consistent with subsection 109-1.06.  (11/17/00)S33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION.  Add the following:  This work shall also include the removal of fences, posts, retaining walls, manholes, and concrete barriers.

202-3.01 GENERAL.  Add the following after the first paragraph:  After fences and retaining walls have been removed it is the Contractor’s responsibility to dispose of the remains properly.  Disposal shall be incidental to the bid Item 202(1) Removal of Structures and Obstructions.

Add the following:

Dewatering for removal of water service shall be subsidiary to pay item 202(1).  Contractor shall not dispose of water from dewatering in storm drain system or wetland area without written approval from the Engineer.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following after the first sentence:  Pavement not suitable for use as recycled asphalt material (RAM) shall be disposed of at an approved DEC disposal site or at the Hiland Solid Waste Facility.

Add the following:

202-3.06  REMOVAL OF CONCRETE BARRIER.  Contractor shall remove concrete barriers from BLM Section Lot 32 W180’ and BLM Section Lot 32 E 150’; project parcels 3 and 4 respectively.  Concrete barriers shall then be delivered to the MOA storage yard at 3rd Avenue and Orca Street in Anchorage, Alaska.  Coordinate drop off time at the MOA storage yard with Shawn Dooley (343-8195).

202-4.01  METHOD OF MEASUREMENT.

Add the following to the end of the list:

For Remove and Deliver Concrete Barrier, Each refers to a complete unit removed and delivered to the MOA storage yard.

202-5.01  BASIS OF PAYMENT.

Add the following pay item:

| Pay Item | Pay Unit |
| --- | --- |
| 202(13) Remove and Deliver Concrete Barrier | Each |

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01 DESCRIPTION.  Add the following:

Work shall include special handling of contaminated soils.

Add the following subsection:

203-3.06 HANDLING OF CONTAMINATED SOIL.  The contractor shall understand and follow the criteria found in the Corrective Action Plan, prepared by DOWL HKM in 2008, when excavating and moving soil within the project area.

203-4.01 METHOD OF MEASUREMENT.  Add the following:

9.	Item 203(6A).  By weighing.

10.	Item 203(28).  On a time and materials basis.

203-5.01 BASIS OF PAYMENT.  Add the following:

Payment for Item 203(6A) will be full compensation for all material, labor, equipment, tools, and incidentals necessary to complete the work.  This includes any clearing and grubbing not already paid for under 201(3B).

Disposal of excavated material will be paid for under Item 203(3) Unclassified Excavation.

Payment for Item 203(28) includes compensation for work associated with handling of contaminated soils and compliance to the Corrective Action Plan prepared for this project.  Contractor will be paid on a time and materials basis for authorized work according to subsection 109-1.05.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 203(6A) Borrow, Type A | Ton |
| 203(28) Contaminated Soil Special Handling | Contingent Sum |

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS
AND MINOR STRUCTURES

Standard Modifications

204-3.01 CONSTRUCTION REQUIREMENTS.  In the first sentence of paragraph 4, delete “bedding and”

(01/27/07)E37

Special Provisions

204-3.01 CONSTRUCTION REQUIREMENTS.  Add the following after the third paragraph:  Excavation, bedding, backfill, and compaction for culverts outside the roadbed may be visually inspected and approved by the Engineer.  R204(2/6/08)

204-5.01 BASIS OF PAYMENT.  Add the following:

Work required to dewater storm drain, water, and sanitary sewer excavations including but not limited to dewatering design, plan preparation and submittal, installation, operation, and removal of the dewatering systems, temporary power, preparing and submitting dewatering and discharge prints, and disposal of water will not be paid for separately.  It is subsidiary to the pipe items.

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

Special Provisions

301-2.01 MATERIALS.  Add the following after the first sentence:  Recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100% by weight passing the 1.5-inch sieve and 95 to 100% by weight passing the 1-inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 to 5.0% by weight of the RAM.

(01/24/07)R176

301-3.01 PLACING.  Add the following:  Base course material used for the sidewalk and pathway foundation shall be placed with a “Layton box” or similar equipment capable of providing a specified depth with a uniform surface.  (09/01/89)R26

301-3.03 SHAPING AND COMPACTION.  Add the following:  If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Compact with a vibratory compactor having a minimum dynamic force of 40,000 pounds.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.  Add the following:  If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1) Aggregate Base Course at the unit price shown on the bid schedule for that item.  (01/24/07)R176

Special Provisions

Replace Section 401 with the following:

SECTION 401

HOT MIX ASPHALT AND SURFACE TREATMENTS

401-1.01 DESCRIPTION. Construct one or more layers of plant-mixed Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown in the Plans.

1.	In this Section, HMA refers to Type I, II, III and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV.

MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD). Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 401-1.

TABLE 401-1

hMA Design Requirements

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (Including Asphalt Cement) |  |  |
| Stability, Pounds | 1800 Min. | 1200 min. |
| Flow, 0.01 Inch | 8 – 14 | 8 - 16 |
| Voids in Total Mix, % | 3 - 5 | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 75 | 50 |
| Asphalt Cement |  |  |
| Percent Voids Filled with Asphalt Cement (VFA) | 65 - 75 | 65 - 78 |
| Asphalt Cement Content, Min. % @ 4% VTM | 5.0 | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective HMA (calculated by weight of mix).

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3, for the Type of HMA specified.  For acceptance testing, HMA mixture will have the full tolerances in Table 401-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix HMA produced from different plants for testing or production paving.  HMA from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each Type of HMA specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of HMA specified.  The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

The Engineer has the option to require further verification of the JMD.  Evaluation of the JMD may be included in the Process Quality Controls, Supplemental Process Quality Controls, Subsection 401-2.05, Test Strip construction.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not to achieve the requirements specified in Table 401-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, the materials, and the JMD, Subsection 401-2.05.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.  Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will asses a fee for each mix design subsequent to the approved Job Mix Design.  The fee will be included under Item 401(6) Asphalt Price Adjustment - Quality.

401-2.02 AGGREGATES. Conform to Subsection 703-2.04.

Use a minimum of three stockpiles for crushed HMA aggregate (coarse, intermediate, and fine). Place blend material or mineral filler, if any, in a separate pile.

401-2.03 ASPHALT CEMENT. Conform to 702-2.01.  If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt cement is required.

401-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the HMA and to provide the mat and longitudinal density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 401-4.02.

Provide copies of the documented sampling and testing results no more than 24 hrs from the time taken.

SUPPLEMENTAL PROCESS QUALITY CONTROL

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineers approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train will be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 401-3.02.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Payment for Test Strips:  Subsection 401-5.01 Basis of Payment and as noted here.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices.  Price adjustments will not be included for quality, unit price, or other.

b.	Failed.  The Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS.  Do not place the HMA on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA unless the roadway surface temperature is a minimum of 40° F and warmer.

401-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production HMA, except when a test strip is required, 24 hrs before placement of the test strip HMA.

401-3.03 ASPHALT MIXING PLANT.  Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

401-3.04 HAULING EQUIPMENT.  Costs associated with Subsection 401-3.04 are subsidiary to Section 401 Pay Items.

Vehicles/Equipment.  Haul HMA in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During HMA hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer cover the HMA in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/clean and disposal shall be submitted in writing to the Engineer and approved by the Engineer 5 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/clean and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paver.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/clean and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material and the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal as specified in Subsection 401-3.16 Patching Defective Areas.

401-3.05 ASPHALT PAVERS.  Use self-propelled pavers equipped with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.  Use means and methods approved by the paver manufacturer.  Means and methods may consist of chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance that verifies the means and methods required to prevent segregation are being used.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers.  Avoid crushing or fracturing of aggregate.  Use rollers designed to compact HMA mixtures and reverse without backlash.

Use pneumatic rollers to compact the prelevel/leveling course.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

401-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to an existing paved surface, clean loose material from cracks for the depth of the cracks.  Fill the cleaned cracks, wider than 1 inch, with an approved HMA tamped in place.  Wash and or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

●	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than 1/2-inch with HMA, Type IV.  Compact the prelevel/leveling course using pneumatic-tire rollers.  The Engineer’s approval of the material and material installation is required.  The Engineer will inspect the material and material installation.  Correct material and material installations identified by the Engineer as required by the Engineer for approval.  Density testing is not required for the leveling course (prelevel) material, material installation.

●	Where the planing equipment breaks through existing pavement, remove 2 inches of existing base material depth and replace with HMA, Type II, Class B.

During the planing operation, notify the Engineer of pavement areas that may be thin or unstable.

Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of HMA on these surfaces.

401-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable (Subsection 105-1.11).

401-3.10 MIXING.  Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD. Mix to obtain 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

401-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss, and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the HMA or similar.

401-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling (preleveling) course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the HMA surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding HMA may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Place HMA over bridge deck membranes according to Section 508 and the manufacturer's specifications.

401-3.13 COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Do not leave rollers or other equipment standing on HMA that has not sufficiently cooled to prevent indentation.

A mat area with density lower than 92% MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 95% of the MSG, as determined by WAQTC FOP for AASHTO T 209.  The MSG of the JMD will be used for the first lot of each Type of HMA.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6-inch diameter core.  (Acceptance testing for density of leveling course or temporary pavement is not required).

When directed by the Engineer provide density profiles of the mat and longitudinal joints with a nuclear density gauge.  Deliver the results of density tests to the Engineer at the time of the testing, in writing in the format detailed in the Quality Control Plan Subsection 401-2.05.

401-3.14 JOINTS. Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat, straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new HMA and thoroughly compact.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

On the final lift, before paving against the longitudinal joint (completing the joint) uniformly coat the surface below the final lift with tack coat material conforming to Section 702.  Coat the vertical edge of pavement (including milled edges) with Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal.  Apply a 1/8 inch thick band of joint adhesive over the cold mat according to manufacturer’s recommendations.

The Engineer shall evaluate the difference in the elevation of the final surface of the longitudinal joint of adjacent mats with a straight edge and by requiring the Contractor to flood the joint surface with water.  All differences in joint elevation greater than 1/8 inch or that pond water shall be repaired at no cost.  An infrared heater shall be used to heat the longitudinal joint and the asphalt ridge rolled flat or repaired with additional HMA until this tolerance is achieved.  The pavement surface shall not be heated to a temperature higher than 310 degrees Fahrenheit.

For the top layer of HMA, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the HMA is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be according to the manufacturer’s recommendations and a maximum application rate of .15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150F.  These joints do not need to be tacked and will not be measured or evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03.

401-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge.  Correct variations from the testing edge, between any two contacts of more than 1/4 inch.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, within 25 feet of the existing pavement or in areas where curb and gutter is left in place.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph (Prl) results filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

Costs associated with meeting surface tolerances are subsidiary to the HMA pay item.

401-3.16 PATCHING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt after compaction is completed or is in any way determined to be defective.  Do not skin patch. Remove defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh HMA according to Subsection 401-3.13 to grade, and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the HMA Pay Item.

401-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a)	By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive or cutting back joints.

b)	By the final HMA surface.

2.	Asphalt Cement.  By the ton, as follows.

Method 1:

Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

Method 2:

Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time, that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement. The Engineer will determine the method. The weight of asphalt cement in waste HMA will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt cement content specified in the JMD.

3.	Job Mix Design. When specified, Contractor furnished JMD(s) will be measured as one according to the HMA Class and Type.

4.	Temporary Pavement.  By weighing.  No deduction will be made for the weight of asphalt cement or anti-stripping additive.

5.	Preleveling/Leveling Course.  By weight or Lane-Station (12 foot width).  No deduction will be made for the weight of asphalt cement or anti stripping additive.

6.	Asphalt Price Adjustment - Quality.  Calculated by quality level analysis under Subsection 401-4.03.  Also included in the measurement are the fees and deductions specified in Subsection 401-2.01 and Subsection 401-4.02.

Asphalt Price Adjustment - Quality, does not apply to, and measurements will not be made for: 1) Leveling Course/Prelevel (rut repair) HMA, 2) Temporary HMA, 3) Approach HMA.

7.	Longitudinal Joint and Joint Adhesive.  By the linear foot of longitudinal joint.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 401-4.03 Evaluation of Materials for Acceptance, and is included in Item 401(6) Asphalt Price Adjustment - Quality.  Penalties assessed are also included in Item 401(6).

An mat area of finished surfacing that is visibly segregated, has a lower density than specified (Subsection 401-3.13), fails to meet surface tolerance requirements, or is flushing asphalt cement is considered unacceptable according to Subsection 105-1.11.

HOT MIX ASPHALT

The quantity of each class and Type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 5,000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  HMA quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  HMA quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 401-4.03 except as noted.

For Contract quantity of less than 1,500 tons (also for approaches and temporary pavement), HMA will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the HMA to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any HMA that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

The Engineer will determine where samples are taken.

1.	Asphalt Cement Content.  Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.  HMA samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device or from the stopped conveyor belt according to WAQTC FOP for AASHTO T2 or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.  A separate set of random numbers, different from those used for mix acceptance, will be used to determine acceptance density locations.  Cut full depth core samples from the finished HMA within 24 hours after final rolling. Neatly cut one 6 inch diameter core sample with a core drill at each location marked by the Engineer.  Use a core extractor to prevent damage to the core.  The Engineer will determine the density of the core samples according to WAQTC FOP for AASHTO T 166/T 275.  Do not core HMA on bridge decks. Backfill and compact voids left by coring with new HMA within 24 hours.  Densities will not be measured at milled edge of existing pavement.

Cores for longitudinal joint density shall be centered on the longitudinal joint at each location where the panel completing the joint is cored for mat density acceptance testing.

Failure to cut and backfill core samples within the specified period will result in a penalty being assessed.

Cores for longitudinal joint density shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

4.	Retesting.  A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 200 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 401-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

Price adjustments in this subsection are addressed under Item 401(6) Asphalt Price Adjustment - Quality.

HOT MIX ASPHALT

The total Hot Mix Asphalt price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to each Type of HMA when the contract quantity equals or exceeds 1,500 tons, except as specified in Subsection 401-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for HMA that includes gradation and asphalt cement content.  The second factor is for density.

A lot containing HMA with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing HMA that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject HMA that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected HMA and tested if requested.  If test results are within specification limits, payment will be made for the HMA.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted as a price adjustment.  Costs associated with removal and disposal of the rejected HMA are subsidiary to the Hot Mix Asphalt Pay Item.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any size on the gradations test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment.  The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment.  The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier.  If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

( x )

The arithmetic mean 	 of the remaining test results is determined:

n

x =

∑x

Where:		∑	= summation of

x 	= individual test value to xn

n 	= total number of test values

(x)

(x)

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.   The sample standard deviation (s) after the outliers have been excluded, is computed:

n∑(x2) – (∑x)2

s =

n(n-1)

Where:		∑(x2)	=	sum of the squares of individual test values.

(∑x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2.  The TV is the specified value in the approved JMD. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations.  The TV for density is 95% of the MSG, the LSL is 92% of MSG, and the USL is 98%.

TABLE 401-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt % | TV -0.4 | TV + 0.4 |
| Mat Density % | 92 | 98 |

*Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

USL  -  x

QU  =

S

4.	The Upper Quality Index (QU) is computed:

Where:		USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

x -  LSL

QL  =

S

5.	The Lower Quality Index (QL) is computed:

Where:		LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined.

See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined.

See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) – 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation and asphalt cement content pay factors from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 401-3 gives the weight factor (f), for each sieve size and asphalt cement content.

TABLE 401-3

WEIGHT FACTORS

| Sieve Size | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1 inch sieve | 4 | - | - |
| 3/4 inch sieve | 4 | 4 | - |
| 1/2 inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Cement Content, % | 40 | 40 | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

*CPF or DPF, whichever is lower.

PAB = Price Adjustment Base = $148 per ton

ASPHALT CEMENT

The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

Asphalt cement will be randomly sampled and tested in accordance with Subsection 401-4.02.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.

Table 401-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | > 1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 |  | 301-338 |  |  |  | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB 		= Price Adjustment Base

Qty 		= Quantity of asphalt cement represented by asphalt cement sample

PRF 		= Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

PAVEMENT SMOOTHNESS

The top layer of HMA will be measured according to 401-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

Smoothness Price Adjustment = PAB x PQ x SF

PAB 	= Price Adjustment Base

PQ 		= Final quantity of HMA, tons

PrI		= Final measured hot mix smoothness, inches/mile

SF 		= Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

LONGITUDINAL JOINT DENSITY

Longitudinal joint density price adjustments apply when HMA quantities equal or greater than 1,500 tons.  A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted.

Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to Subsection 401-3.14.

2.	If project average joint density is greater than 92% MSG, apply the following incentive:

a.	Longitudinal joint density price adjustment equal to $1.50 per linear foot is added.

401-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

- This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 401 thru 405, 608 and 609.

- This provision shall only apply to cost changes in asphalt material that occur between the first Friday of the month of which the bid opening occurs and the date the asphalt material is incorporated into the project.

- The asphalt material price adjustment will only apply when:

  - There is more than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

  - There is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date the asphalt material is incorporated into the project.

- The AAMPI is calculated bi-monthly on the first and third Friday of each month, and is in effect from the day of calculation until the next bi-monthly calculation.  The AAMPI is posted on the Department’s Statewide Materials website and is calculated according to the formula posted there.  Posting of new AAMPI values after the first and third Friday of each month is typically delayed one to several days.  Any delay in the Department’s Posting of an updated AAMPI value shall not constitute grounds for using any value other than the value in effect as described in this specification.

- Price adjustment will be cumulative and calculated with each progress payment.

For projects where asphalt material is purchased from a commercial plant serving multiple customers, use the AAMPI in effect on the last day of the pay period, to calculate price adjustment for asphalt material incorporated into the project during that pay period.  For projects where the asphalt material is purchased in advance of incorporating it into the project, use the AAMPI in effect on the last day of the period when the asphalt material was purchased.  Submit the asphalt material purchase invoice, showing the date purchased, to the Engineer to identify the pay period when the asphalt material was purchased.  The Department will increase or decrease payment under this contact by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP–IB)–(0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB–IPP)–(0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

- Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

401-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items:

Asphalt cement, anti-stripping additives, tack coat, crack sealing, surface sealing of longitudinal joints, surface tolerance corrections, patching defective areas and the work and materials associated with Subsection 401-3.04 Hauling Equipment are subsidiary to the associated Hot Mix Asphalt Pay Items.

Item 401(1F) Hot Mix Asphalt, Preleveling/Leveling Course, Type IV: Asphalt Cement, anti-stripping additives are subsidiary.

Item 401(3) Hot Mix Asphalt, Temporary, Type II, Class B: Asphalt cement, anti-stripping additives, removal and disposal are subsidiary.

Item 401(6) Asphalt Price Adjustment - Quality:  is the sum of the price adjustments for each material lot (excluding the Preleveling/Leveling Course (rut repair) HMA, Temporary HMA and Approach HMA) and for deductions and fees assessed.

Deductions and fees assessed:

•	Each mix design subsequent to the approved Job Mix Design (Subsection 401-2.01) for each Type and Class of Hot Mix Asphalt specified will result in a fee of $2500.00 each.

•	Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day (Subsection 401-4.02).

•	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day (Subsection 401-4.02).

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 401(1A) Hot Mix Asphalt, Type II; Class A | Ton |
| 401(2) Asphalt Cement, PG 52-28 | Ton |
| 401(6) Asphalt Price Adjustment - Quality | Contingent Sum |
| 401(10) Asphalt Material Price Adjustment - Unit Price | Contingent Sum |

Special Provisions

Add the following Section:

SECTION 408

HOT MIX ASPHALT AND SURFACE TREATMENTS
TYPE V
(Superpave)

408-1.01 DESCRIPTION.  Construct one or more layers of plant-mixed Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown in the Plans.

1.	In this Section HMA refers to Type V, except where noted otherwise.

a.	Use of Reclaimed Asphalt Pavement (RAP) is not permitted in HMA, Type V.

b.	Warm Mix Asphalt (WMA) is prohibited as a substitution for HMA, Type V.

408-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.  HMA, Type I, II, III, and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV.

MATERIALS

408-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD).  Design the JMD according to AASHTO R35 using the design requirements of Table 408-1, except evaluate the moisture sensitivity using the Alaska Test Manual (ATM) 414 and not AASHTO T 283.

TABLE 408-1

HMA Design Requirements

| DESIGN PARAMETERS |  |
| --- | --- |
| Design ESALs, Millions | 0.3 to < 3 |
| Rut Index, Max., ATM 419 | 3 |
| Asphalt Cement Content, Min. % | 5.0 |

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3, for the Type of HMA specified.  For acceptance testing, HMA mixture will have the full tolerances in Table 408-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix HMA produced from different plants for testing or production paving.  HMA from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each type of HMA specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and/or mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1 gallon samples of the asphalt cement proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will evaluate the material and the proposed gradation using the requirements of Table 408-1 for Type V Hot Mix Asphalt.  The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

The Engineer has the option to require further verification of the JMD.  Evaluation of the JMD may be included in the Process Quality Controls, Supplemental Process Quality Controls, Subsection 408-2.05, Test Strip construction.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not to achieve the requirements specified in Table 408-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, the materials, and the JMD, Subsection 408-2.05.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.  Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will asses a fee for each mix design subsequent to the approved Job Mix Design.  The fee will be included under Item 408(6) Asphalt Price Adjustment - Quality.

408-2.02 AGGREGATES.  Conform to Subsection 703-2.04.

Use a minimum of 3 stockpiles for crushed HMA aggregate (coarse, intermediate, and fine).  Place blend material or mineral filler, if any, in a separate pile.

408-2.03 ASPHALT CEMENT.  Conform to 702-2.01.  If not specified, use PG 64-34.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket.  The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturers certificate of compliance (Subsection 106-1.05).

2.	Conformance test results of the batch (provide prior to delivery as noted above)

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of materials loaded.

6.	Type and percent of anti-strip added.

408-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate shall remain coated when tested according to ATM 414. A minimum of .25% by weight of asphalt cement is required.

408-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the HMA and to provide the mat and longitudinal density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 408-4.02.

Provide copies of the documented sampling and testing results no more than 24 hrs from the time taken.

SUPPLEMENTAL PROCESS QUALITY CONTROL

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer; provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineers approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train will be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 408-3.02.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Payment for Test Strips:  Subsection 408-5.01 Basis of Payment and as noted here.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices.  Price adjustments will not be included for quality, unit price, or other.

b.	Failed.  The Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

CONSTRUCTION REQUIREMENTS

408-3.01 WEATHER LIMITATIONS.  Do not place HMA on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA unless the roadway surface temperature is 40F or warmer.  Do not place mix after September 15 unless approved by the Engineer in writing.

408-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production HMA, except when a test strip is required, 24 hrs before placement of the test strip HMA.

408-3.03 ASPHALT MIXING PLANTS.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

408-3.04 HAULING EQUIPMENT.  Costs associated with Subsection 408-3.04 are subsidiary to Section 408 Pay Items.

Vehicles/Equipment.  Haul HMA in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During HMA hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer, cover the HMA in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/clean and disposal shall be submitted in writing to the Engineer and approved by the Engineer 5 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/clean and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paver.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/clean and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material and the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal as specified in Subsection 408-3.16 Patching Defective Areas.

408-3.05 ASPHALT PAVERS.  Use self propelled asphalt pavers having a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.  Use means and methods approved by the paver manufacturer.  Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance that verifies the means and methods required to prevent segregation are being used.

408-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact HMA mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

408-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to an existing paved surface, clean loose material from cracks for the depth of the cracks.  Fill the cleaned cracks, wider than 1 inch, with an approved HMA tamped in place.  Wash and or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than 1/2-inch with HMA, Type IV.  Compact the prelevel/leveling course using pneumatic-tire rollers.  The Engineer’s approval of the material and material installation is required.  The Engineer will inspect the material and material installation.  Correct material and material installations identified by the Engineer as required by the Engineer for approval.  Density testing is not required for the leveling course (prelevel) material, material installation.

	Where planing equipment breaks through existing pavement, remove 2 inches of existing base material depth and replace with HMA, Type II, Class B.

During the planing operation, notify the Engineer of pavement areas that may be thin or unstable.

Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of HMA on these surfaces.

408-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

408-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable (Subsection 105-1.11).

408-3.10 MIXING.  Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

408-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss, and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the HMA or similar.

408-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the HMA surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding HMA may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Place HMA over bridge deck membranes according to Section 508 and the manufacturer's specifications.

408-3.13 COMPACTION.  Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Do not leave rollers or other equipment standing on HMA that has not sufficiently cooled to prevent indentation.

A mat area with density lower than 93% MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 96% of the MSG, as determined by WAQTC FOP for AASHTO T 209.  The MSG of the JMD will be used for the first lot of each type of HMA.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

When directed by the Engineer provide density profiles of the mat and longitudinal joints with a nuclear density gauge.  Deliver the results of density tests to the Engineer at the time of the testing, in writing in the format detailed in the Quality Control Plan Subsection 408-2.05.

408-3.14 JOINTS.  Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat, straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new HMA and thoroughly compact.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

On the final lift, before paving against the longitudinal joint (completing the joint) uniformly coat the surface below the final lift with tack coat material conforming to Section 702.  Coat the vertical edge of pavement (including milled edges) with Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal.  Apply a 1/8 inch thick band of joint adhesive over the cold mat according to manufacturer’s recommendations.

The Engineer shall evaluate the difference in the elevation of the final surface of the longitudinal joint of adjacent mats with a straight edge and by requiring the Contractor to flood the joint surface with water.  All differences in joint elevation greater than 1/8 inch or that pond water shall be repaired at no cost.  An infrared heater shall be used to heat the longitudinal joint and the asphalt ridge rolled flat or repaired with additional HMA until this tolerance is achieved.  The pavement surface shall not be heated to a temperature higher than 310 degrees Fahrenheit.

For the top layer of HMA, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location that the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the HMA is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be according to the manufacturer’s recommendations and a maximum application rate of .15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150°F.  These joints do not need to be tacked and will not be measured or evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to Subsection 408-4.03.

408-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  Correct variations from the testing edge, between any two contacts, greater than 1/4 inch.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, within 25 feet of the existing pavement.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph (Prl) results filtered with a 0.2 inch blanking band.  Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

Costs associated with meeting surface tolerances are subsidiary to the HMA pay item.

408-3.16 PATCHING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing or bleeding asphalt after compaction is completed or is in any way determined to be defective.  Do not skin patch. Remove defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh HMA according to Subsection 408-3.13 to grade and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the HMA Pay Item.

408-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

1.	Hot Mix Asphalt.

a)	By weighing, no deduction will be made for the weight of asphalt cement, anti-stripping additive or cutting back joints.

b)	By the area of final HMA surface.

2.	Asphalt Cement. By the ton as follows:

Method 1:

Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

Method 2:

Supplier's invoices minus waste, diversion, and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time, tankers be weighed in the Engineers presence before and after unloading.  If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement.  The Engineer will determine the method.  The weight of asphalt cement in waste HMA will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than .4% above the optimum asphalt cement content specified in the JMD.

3.	Job Mix Design. When specified, Contractor furnished JMD(s) will be measured as one according to the HMA Class and Type.

4.	Temporary Pavement.  Section 401.

5.	Preleveling/Leveling Course.  Section 401.

6.	Asphalt Price Adjustment - Quality.  Calculated by quality level analysis under Subsection 408-4.03.  Also included in the measurement are the fees and deductions specified in Subsection 408-2.01 and Subsection 408-4.02.

Asphalt Price Adjustment - Quality, does not apply to, and measurements will not be made for Approach HMA.

7.	Longitudinal Joint and Joint Adhesive.  By the linear foot of longitudinal joint.

408-4.02 ACCEPTANCE SAMPLING AND TESTING.  The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 408-4.03 Evaluation of Materials for Acceptance and is included in Item 408(6) Asphalt Price Adjustment - Quality.  Penalties assessed are also included in Item 408(6).

An area of finished surfacing that is visibly segregated, has a lower density than specified (Subsection 408-3.13), fails to meet surface tolerance requirements, or is flushing asphalt cement is considered unacceptable according to Subsection 105-1.11.

HOT MIX ASPHALT

The quantity of each class and type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 408-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 5000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  HMA quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  HMA quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 408-4.03 except as noted.

For Contract quantity of less than 1,500 tons, (also for approaches) HMA will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the HMA to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any HMA that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

The Engineer will determine where samples are taken.

1.	Asphalt Cement Content.  Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403 as directed by the Engineer.  HMA samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device, or from the stopped conveyor belt according to WAQTC FOP for AASHTO T 2, or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3. 	Density.  A separate set of random numbers, different from those used for mix acceptance, will be used to determine acceptance density locations. Cut full depth core samples from the finished HMA within 24 hours after final rolling.  Neatly cut one 6 inch diameter core sample with a core drill at each location marked by the Engineer.  Use a core extractor to prevent damage to the core.  The Engineer will determine the density of the core samples according to WAQTC FOP for AASHTO T 166/T 275.  Do not core HMA on bridge decks.  Backfill and compact voids left by coring with new HMA within 24 hours.  Densities will not be measured at milled edge of existing pavement.

Cores for longitudinal joint density shall be centered on the longitudinal joint at each location where the panel completing the joint is cored for mat density acceptance testing.

Failure to cut core samples within the specified period will result in a penalty being assessed.

Cores for longitudinal joint density shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

4.	Retesting.  A retest of any sample outside the limits specified in Table 408-2 may be requested provided the quality control requirements of 408-2.05 are met.  Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT.

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the Contract quantity of asphalt cement is between 85 – 200 tons, the contact quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 408-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 408-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

408-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

Price adjustments in this subsection are addressed under Item 408(6) Asphalt Price Adjustment - Quality.

HOT MIX ASPHALT

The total Hot Mix Asphalt price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to each type of HMA when the contract quantity equals or exceeds 1,500 tons, except as defined in Subsection 408-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for HMA that includes gradation and asphalt cement content.  The second factor is for density.

A lot containing HMA with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing HMA that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject HMA that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected HMA and tested if requested.  If test results are within specification limits, payment will be made for the HMA.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted as a price adjustment.  Costs associated with removal and disposal of the rejected HMA are subsidiary to the Hot Mix Asphalt Pay Item.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results.  Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if a sieve size on the gradation test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment. The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment.  The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier.  If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

( x )

The arithmetic mean        of the remaining test results is determined:

n

x =

∑x

Where:		∑	= summation of

x 	= individual test value to xn

n 	= total number of test values

(x)

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

(x)

is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation (s) after the outliers have been excluded, is computed:

n∑(x2) – (∑x)2

s =

n(n-1)

Where:	  ∑(x2)	=	sum of the squares of individual test values.

(∑x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 408-2.  The TV is the specified value in the approved JMD.  Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations.  The TV for density is 96% of the MSG, the LSL is 93% of MSG, and the USL is 99%.

TABLE 408-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt Cement % | TV -0.4 | TV + 0.4 |
| Mat Density % | 93 | 99 |

*Tolerances for the No. 200 sieve may not exceed the broadband limits in Table 703-3.

4.	The Upper Quality Index (QU) is computed:

USL  -  x

QU  =

S

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

x -  LSL

QL  =

S

5.	The Lower Quality Index (QL) is computed:

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined.

See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined.

See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) – 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation and asphalt cement content pay factors from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 408-3 gives the weight factor (f), for each sieve size and asphalt cement content.

TABLE 408-3

WEIGHT FACTORS

| Sieve Size | Type V Factor “f” |
| --- | --- |
| 3/4 inch sieve | 4 |
| 1/2 inch sieve | 5 |
| 3/8 inch sieve | 5 |
| No. 4 sieve | 4 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No. 30 sieve | 5 |
| No. 50 sieve | 5 |
| No. 100 sieve | 4 |
| No. 200 sieve | 20 |
| Asphalt Cement Content, % | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

*CPF or DPF, whichever is lower.

PAB = Price Adjustment Base = $164 per ton

ASPHALT CEMENT

The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

Asphalt cement will be randomly sampled and tested in accordance with Subsection 408-4.02.  Asphalt cement pay reduction factors for each sample will be determined from Table 408-4.

Table 408-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | > 1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 |  | 301-338 |  |  |  | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value m-value | > 0.300 | > 0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB 		= Price Adjustment Base

Qty 		= Quantity of asphalt cement represented by asphalt cement sample

PRF	 	= Pay Reduction Factor from Table 408-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

PAVEMENT SMOOTHNESS

No penalty will be assessed, but a bonus is available.

The top layer of HMA will be measured according to 408-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

Smoothness Price Adjustment = PAB x PQ x SF

PAB 	= 	Price Adjustment Base

PQ 		= 	Final quantity of HMA, tons

PrI		= 	Final measured hot mix smoothness, inches/mile

SF 		= 	Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

LONGITUDINAL JOINT DENSITY

Longitudinal joint density price adjustments apply when HMA quantities are equal to or greater than 1,500 tons.  A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted.

Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to Subsection 408-3.14.

2.	If project average joint density is greater than 92% MSG apply the following incentive:

a.	Longitudinal joint density price adjustment equal to $1.50 per linear foot is added.

408-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402.  Also included is the asphalt material in the Approach HMA as included in 408 or 639.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

b.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	As used in this subsection, the Alaska Asphalt Material Price Index is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation.  The Alaska Asphalt Material Price Index is posted on the Department’s Statewide Materials website, and calculated according to the formula posted there.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period.  The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation 	= [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

408-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items:

Anti-stripping additives, tack coat, crack sealing, surface sealing of longitudinal joints, surface tolerance corrections, patching defective areas and the work and materials associated with Subsection 408-3.04 Hauling Equipment are subsidiary to the associated Hot Mix Asphalt Pay Items.

Item 408(6) Asphalt Price Adjustment - Quality:  is the sum of the price adjustments for each material lot (excluding Approach HMA) and for deductions and fees assessed.

Deductions and fees assessed:

•	Each mix design subsequent to the approved Job Mix Design (Subsection 408-2.01) for each Type and Class of Hot Mix Asphalt specified will result in a fee of $2500.00 each.

•	Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day (Subsection 408-4.02).

•	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day (Subsection 408-4.02).

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 408(1A) Hot Mix Asphalt, Type V | Ton |
| 408(2) Asphalt Cement, PG 64-34 | Ton |
| 408(6) Asphalt Price Adjustment - Quality | Contingent Sum |
| 408(10) Asphalt Material Price Adjustment - Unit Price | Contingent Sum |

Special Provisions

SECTION 501

STRUCTURAL CONCRETE

501-1.01 DESCRIPTION.  Add the following:  Furnish, place, finish and cure Portland cement concrete for decorative wall structures with form liner, decorative log and metal stars as shown on plans.

501-2.01 MATERIALS.  Add the following:

Cast-In-Place Concrete Retaining Walls

Epoxy-Coated Reinforcing Bars 	Subsection 709-2.01

Decorative Wall.

Provide standard, reusable, nonporous form liners conforming to the patterns and design as shown in the drawings.  The decorative concrete wall design will be an AutoCAD template provided to the Contractor by the Landscape Architect/Engineer.  A custom form liner will be manufactured by one of the following suppliers or approved equal:

Scott Systems, Inc.	Spec Formliners, Inc.
10777 East 45th Avenue	530 East Dyer Road
Denver, CO 80239	Santa Ana, CA 92707
(303) 373-2500	(888) 429-1460

Provide standard, reusable, and nonporous form liners conforming to the pattern of the chosen supplier.  The Scott Systems’ form liner shall be #175 Oregon Basalt and #160 Rocky Mountain Flagstone.  The Spec Formliners’ form liner shall be 1626 Kleen Slate (split slate texture with 3/4” max relief) and 1550 Fractured Basalt (2” maximum depth with pattern matched edges).

See Subsection 621-1.01 for half round log specifications.

The Contractor shall submit one concrete sample (2’ x 2’ in the field or shop) with a minimum thickness of 4” for approval by the Landscape Architect, showing an area that represents the patterns and design of the decorative walls, as shown on the plans.

The metal stars shall be salvaged from the existing fencing and reused on the decorative walls as shown on the plans.  A metal rod, with galvanizing for a rust inhibitor, shall be attached to the back of each metal star and then attached to the decorative walls as shown on the plans.

Raised planter bed shall consist of a Portland Cement Concrete planter bed wall as dimensioned in the plans.  Contractor shall apply a smooth finish to the concrete.  Contractor shall also provide a 1” deep x 2” wide vertical reveal on the face of the planter every 4’ on center and a 3/4” chamfer on the edge of the planter.

501-3.08 PLACING CONCRETE.

8.	Add the following:  Crack control joints for the retaining wall shall be installed with a maximum separation of 20’.

501-4.01 METHOD OF MEASUREMENT.  Add the following:  Measurement for pay item 501(4A) Class A Concrete will be per cubic yard.

Measurement for pay item 501(4B) Class A Concrete, Decorative Wall will be per cubic yard.

Measurement for pay item 501(15) Cast-In-Place Concrete Walls will be by lump sum.

Measurement for pay item 501(16) Raised Planter Bed will be per cubic yard of wall including the footing.  Reinforcement for the raised planter bed will be subsidiary to Pay Item 501(16).

501-5.01 BASIS OF PAYMENT.  Add the following:  Labor and materials for construction of pay items 501(4A) Class A Concrete, 501(4B) Class A Concrete, Decorative Wall, 501(15) Cast-In-Place Concrete Retaining Walls, and 501(16) Raised Planter Bed; including excavation, backfill, reinforcing steel, Class A concrete, tools, and equipment shall be incidental to the pay item.

Construction of the retaining wall shall be as shown on the Plans, as provided in the Standard Specifications, Standard Modifications and these Special Provisions, and as directed by the Engineer.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 501(4A) Class A Concrete | Cubic Yard |
| 501(4B) Class A Concrete, Decorative Wall | Cubic Yard |
| 501(15) Cast-In-Place Concrete Retaining Walls | Lump Sum |
| 501(16) Raised Planter Bed | Cubic Yard |

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01 DESCRIPTION.  Add the following:  This work will also include the epoxy coating of appropriate reinforcing steel bars.  The reinforcing steel in the exposed vertical face of a retaining wall facing the roadway and as noted on the Plans shall be epoxy coated.  (02/08/96)R38

503-5.01 BASIS OF PAYMENT.  Add the following:  If epoxy coating the reinforcing steel is required, it will be a subsidiary obligation and no separate payment will be made.  (02/08/96)R38

SECTION 504

STEEL STRUCTURES

Standard Modifications

504-3.01 FABRICATION. Delete subsection 8 in its entirety and replace with the following:

8.	Welding.  Perform all welding and Nondestructive Examination (NDE) as specified or shown on the Plans.  Conform to the ANSI/AASHTO/AWS Bridge Welding Code D1.5 when welding new steel bridge girders, beams, and stringers.  Conform to the Structural Welding Code AWS D1.1 when welding all other steel structures.

At least 30 days prior to welding, submit for approval a welding plan that has been signed and stamped by a Certified Welding Inspector (CWI) responsible for Quality Control (QC) and consisting of the following documents:

- Quality Control personnel qualifications listing CWI number;

- Welding Procedure Specifications (WPS) using forms in AWS D1.1, Sample Welding Forms;

- Procedure Qualification Records (PQR) when applicable, using forms in AWS D1.1, Sample Welding Forms;

- Welder Performance Qualification Records (WPQR) using forms in AWS D1.1, Sample Welding Forms with documentation of current welder certification;

- Sample daily inspection sheet; and

- Type and extent of NDE to be conducted, as required in the specifications.

Perform all Quality Control inspection necessary to ensure the materials and workmanship meet the requirements of the contract documents.  Use a CWI for welding inspection.

Correct all deficiencies in materials and workmanship revealed by Quality Control and Quality Assurance inspections without additional compensation.

Furnish all completed Quality Control inspection documents to the Engineer and to the Quality Assurance representative designed by the State (when designated).

Meet Charpy V-notch impact test requirements as shown on the Plans and according to Sections 715 and 716; except that the impact energy values for filler metals must not be less than that of the base metals to be joined, when tested at the same temperature as the base metal.

E39 (01/27/07)

SECTION 505

PILING

Special Provisions

505-3.03  Pile Bearing Values.  Delete the first paragraph of this subsection and substitute the following:  Drive piles, except piles for lighting standards, to the required ultimate bearing capacity.  For lighting standards, install piles of sufficient length to cut the pile at the required cut off elevation and to provide the minimum installed length shown on the Plans.

505-3.09 Driving Piles.  Add the following:  Sites for the lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

When the minimum pile length shown on the Plans for a lighting standard foundation can not be achieved, install the pile tip to an elevation established by the Engineer.

505-4.01 Method of Measurement.  Add the following to the second paragraph:

Do not measure piles for lighting standards for payment.

505-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:  Include costs of furnishing and installing piles for lighting standards in Item 660(3) Highway Lighting System Complete.  (04/15/05)R65USC04

SECTION 603

CULVERTS AND STORM DRAINS

Special Provisions

603-1.01 DESCRIPTION.  Add the following:  This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS.

Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5-inch by 6-foot post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

When Item 603(21-xx), Corrugated Polyethylene Pipe is listed in the bid schedule, furnish Corrugated Polyethylene Pipe (CPEP) Type S.

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-1.01 DESCRIPTION.  Add the following:  This work also consists of providing and installing Oil/Grit Separators.

604-2.01 MATERIALS.  Add the following:

Oil/Grit Separator:  Provide oil/grit separator units from one of the following manufacturers or approved equal meeting the minimum specification:

Vortechnics			Aquashield, Inc.		Stormwater Management, Inc.

200 Enterprise Drive		2733 Kanasita Drive		10891 James Way Drive SE

Scarborough, ME 04074	Hixson, TN 37343		Aumsville, OR 97325

(877) 907-8676		(423) 870-8888		(800) 548-4667

Minimum Specification:  A structure or pair of structures in parallel or series, which together as a unit treat a minimum of 0.06 cubic yards per second (cy/s).  The water flowing out of the oil/grit separator unit shall meet the water quality standards of 18 AAC 70.020(5)(A)(iii).

Submit shop drawings for proposed oil/grit separator(s) to the Engineer for approval before ordering.

Curb Inlets:  Provide R-3246-CL inlet grates manufactured by Neenah Foundry Company or approved equal.  The approved equal shall meet the following criteria:

Minimum loading capacity:	H20

Minimum captured flow capacity:	0.05 cy/s at a longitudinal grade of 5%

Grate style:	Bicycle friendly*

*Bicycle friendly is defined as:

- The style of grate employed should allow bicycle travel from accessible directions.  Grates located in open areas, or adjacent to driveways, or in other locations where they are not adjacent to barrier curbs, require special attention in this regard.

- If slotted grates or vane-type grates are considered, they should have sufficiently narrow openings, and/or should have appropriately spaced transverse (cross) bars, to ensure that any foreseeable width and diameter of bicycle tire cannot drop down into openings to an unsafe extent.

- Gutter slopes should not be substantially swaled into the curb so as to create a disturbance in the roadway that might affect the ability of bicycles or other traffic to traverse them.

Field inlets:  Use “beehive” type inlet covers for field inlets.

Provide equipment that is capable of cleaning storm drains.  The equipment shall be inspected and accepted by the Engineer before use on this project.  Provide traffic control while cleaning storm drains.

AWWU will provide new sanitary sewer lids as determined by a pre construction inspection conducted by AWWU.  Contractor shall provide traffic control for this pre construction inspection.

604-3.01 CONSTRUCTION REQUIREMENTS.  Delete the second paragraph and substitute the following:

Install DOT&PF Inlet, Type A, consisting of a precast concrete catch basin structure, grade rings, and metal frames and grate as shown on the Plans.  Grout pipes in place.

Upon removal of manhole component parts, the Contractor shall clean and prepare existing component parts before installation of replacement parts.  This will include, but not be limited to, removing existing grout and Ram-Nek-type sealant from remaining and connecting component parts.

The Contractor shall provide a disposal site for all materials (manhole covers, frames, etc.) removed or replaced.

Add the following:

Probe the manholes with a calibrated bar.  If 50% or more of the manhole sump is filled with debris, remove the debris.  Remove debris from catch basins and inlets regardless of the quantity of debris.  No more than 5% to 10% of debris should remain.  Remove debris (sticks, plastic bags) blocking culvert inlets and outlets.  Record the date of inspection, the depth of sediments, and whether the manhole was cleaned or not, in a grid map book provided by the Engineer.

The Contractor shall provide equipment that is capable of cleaning storm drains.  The equipment shall be inspected and accepted by the Engineer before use on this project.  The contractor shall provide traffic control while cleaning storm drains.

The work shall include disposal of silt, trash, debris and other material removed from the system.  This material may be disposed at the Municipality of Anchorage Hazardous Materials Waste Disposal site.

Contractor shall install the manhole and separator in accordance with this section and in accordance to manufacturer’s specifications.

Add the following after the third sentence:  A proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 1 inch concrete or asphalt, as applicable.

Under the heading “Reconstruct existing manhole by using one or more of the following methods,” add the following:

8.	Remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab (reducing slab without an access hole).  Notify the Engineer a minimum of 5 days before removing the frame and grate.  The Engineer will notify DOT&PF M&O (262-2199) and have an M&O representative physically identify frames and grates to be salvaged.  Frames and grates not designated for salvage by DOT&PF M&O shall become the Contractor’s property.

When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the plans and 2 inches larger than the outside diameter of the new pipe.  Then, grout joint with non-shrinking cement mortar.

Curb inlet structures shall have a 3 inch formed hole approximately 2 feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  Keep the openings functional.  This may require temporary dikes, RMC extensions, as necessary.  Fill these holes with grout upon final paving.

Cast standard drainage structure steps or threaded dowels to receive steps during structure pour or install them before concrete hardens.

Install Item 604(14A), 604(14B), and 604(14C) according to the manufacturer’s instructions.  Adjust the inverts of the oil/grit separator(s) as necessary to accommodate the selected model while maintaining the minimum amount of cover.

604-4.01 METHOD OF MEASUREMENT.  Add the following:

Oil/Grit Separator:  Will be measured as a complete unit in place and shall include the concrete structure, diversion apparatus, frames, and covers.

Frames, grates, and lids will not be measured for payment.  An oil/grit separator unit may consist of one or two structures, as needed, to treat the water as specified.

604-5.01 BASIS OF PAYMENT.  Add the following:

Frames, grates, and lids are subsidiary to the drainage structure.

Component parts of existing or new manholes shall be included in the unit price for the bid item being constructed, reset, or replaced, and shall be paid for by a cumulative total of each unit constructed.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 604(1A) Storm Drain Manhole, Type I | Each |
| 604(1B) Storm Drain Manhole, Type II | Each |
| 604(14A) Oil/Grit Separator, Lake Otis - North | Each |
| 604(14B) Oil/Grit Separator, Lake Otis - South | Each |
| 604(14C) Oil/Grit Separator, Tudor - West | Each |

SECTION 606

GUARDRAIL

Special Provisions

606-1.01  DESCRIPTION.  Add the following:  Contractor shall provide and install steel posts around existing fire hydrant as detailed on the plans.

606-2.01  MATERIALS.  Add the following:  Posts shall be 4” diameter steel (SCH#40) pipe filled with concrete.  They shall be painted caterpillar yellow (NO. 4C-6129, CAT DEALER) after installation with sufficient coats of paint to mask the steel.

606-4.01  METHOD OF MEASUREMENT.  Add the following:

4.    STEEL POSTS.  Per each, installed in place.

606-5.01  BASIS OF PAYMENT.  Add the following:

| Pay Item | Pay Unit |
| --- | --- |
| 606(17) Steel Posts | Each |

SECTION 607

FENCES

- Special Provisions

607-1.01 DESCRIPTION.  Add the following:  Decorative fence shall consist of steel wide flange with half round spruce insert, square steel tubing, steel pipe top rail, welded wire mesh panels, wire rope, labor, and equipment for fabrication, installation and finishing as shown on the plans.

The slatted chain link fence shall replace the existing wood fence to be demolished adjacent to Parkside Apartments.  It shall be a chain link fence with wood slats inserted vertically.

The 7’ wood fence shall replace the existing wood fence surrounding the dumpster pad on project parcel number 2 (Tract A-1-C).  Contractor shall replace existing fence with like fencing.  The 7’ wood fence shall be constructed around the new dumpster pad located on project parcel 19 (S1/2 SW1/4 SE1/4 SE1/4 SEC. 29), as shown on the plans.

607-2.01 MATERIALS.  Add the following:

Decorative Fence Panel					Subsection 710-2.12

Galvanized							Subsection 716-2.07

607-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:

### 1.	Decorative Fence Quality Assurance

#### Qualifications of Fabricators and Installers

##### Not less than five years of continuous experience in the fabrication of similar products.

##### All welding shall be performed by welders currently certified by the American Welding Society (AWS).

#### Codes and Standards

- Comply with “Code for Welding in Building Construction” of the American Welding Society, latest edition.

#### The contractor shall take care in product handling and storage as follows:

  - All steel fabrications and materials shall be placed on skids above the ground.  It shall be kept clean and properly drained.

  - Finishes:  Keep all materials dry during delivery and storage.  Protect against exposure to weather and contact with damp or wet surfaces.

### 2.	Decorative Fence Fabrication

- Submit shop drawings of fence panels and posts prior to fabrication clearly showing all materials, finishes, connections, joining methods, location of installation and field measurements for construction of decorative fence.  Approved shop drawings shall become the basis for acceptance of Work.

- Contractor shall provide a full size sample panel that will serve as the basis of quality control for metal fabrication.  This panel shall be unfinished and available for review at an Anchorage location.  All subsequent panels shall meet the fabrication standard established by the approved sample.

- Contractor shall furnish all finished fence panels, pipes and connectors for approval prior to installation.  The completed fence components shall be free of fabrication defects, scratches, chipped paint, rust or other discoloration to be installed as part of Work.

- Prior to assembly, Contractor shall field verify wall locations and top of wall slopes in order to construct panels parallel to walls.  Panels shall be assembled in shop or factory.  Welds shall be neat and clean and all flush welds shall be ground smooth.  Holes for attachment shall be predrilled prior to powder coating.  Each wide flange column shall have a steel cap that fits over the outside as shown on Drawings preventing moisture from entering the cut end of half round log.

### 3.	Decorative Fence Galvanize Finish

a.	The steel wide flange posts, square steel tube framing, steel pipe top rail, welded wire mesh panel shall be galvanized according to the standard specifications outlined in subsection 716-2.07 Galvanizing.

4.	Slatted Chain Link Fence

- Chain link fence shall be 6’ high.

- Wood slats shall be inserted vertically in the mesh openings so the slats fit snugly.  Slats shall be fastened to prevent easy removal or displacement.

5.	7’ Wood Fence

- Fence shall be 7’ high.

607-4.01 METHOD OF MEASUREMENT.  Add the following:

Decorative Fence:  Measured by linear foot at the base of the fence parallel to the wall or ground.

Slatted Chain Link Fence:  Measured by linear foot of fence installed.

7’ Wood Fence:  Measured by linear foot of fence installed.

607-5.01 BASIS OF PAYMENT.  Add the following pay item

| Pay Item | Pay Unit |
| --- | --- |
| 607(3B) Slatted Chain Link Fence | Linear Foot |
| 607(7) Decorative Fence | Linear Foot |
| 607(9) 7’ Wood Fence | Linear Foot |

SECTION 608

SIDEWALKS

Special Provisions

608-1.01 description.  Add the following:  This work also consists of constructing asphalt pathway(s) and median(s) to conform to the Plans.  (01/24/07)R47

Add the following:  This work shall also consist of providing equipment, materials, and labor necessary to install cast-in-place Patterned Concrete and exposed aggregate concrete as shown on the plans.

Installation of detectable warning tile, in addition to the tile on each curb ramp, is included in this section.

608-2.01 MATERIALS.  Delete paragraph number 2 and substitute the following:

2.	Asphalt Sidewalk and Asphalt Pathway

###### Asphalt Cement, PG 52-28	subsection 702-2.01

Aggregate, Type II or III	subsection 703-2.04

Mix Design Requirements (ATM 417)

Marshall Stability, pounds, min.	1,000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

(01/24/07)R47

Add the following:

3.	Aggregate Concrete shall conform to Section 501, Structural Concrete, Class A, except that Subsection 501-3.03 Batching is modified as follows:

For Aggregate Concrete, concrete shall be constructed as follows:

- Minimum 28 Day Compressive Strength – 4,000 psi.

- Cement Factor – 6.5 sacks per cubic yard minimum.

- Coarse Aggregate Gradation.

| Designated Sizes | 2" | 1-1/2" | 1" | 3/4" | 1/2" | 3/8" | No. 4 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3/4" to No. 4 | - | - | 100 | 90-100 | - | 20-26 | 0-10 |
| 1-1/2" to 3/4" | 100 | 90-100 | 20-55 | 0-15 | - | 0-5 | - |

*Not more than 5% shall pass the No. 8 sieve.  All coarse aggregate to have minimum of two fracture faces.

- Fine Aggregate – See Section 703-2.01, Fine Aggregates.

- Water – Cement Ratio – 0.5 maximum by weight.

- Air Entrainment – 5 to 7%.

- Slump Range – 50 to 100 mm, maximum slump as determined by AASHTO, T 119.

- Curing Agents – Use no curing agents and/or admixtures in concrete slabs, which in any way will deter or prevent final finishing of concrete.

4. 	Patterned Concrete shall conform to Section 501, Structural Concrete, Class A, except that Subsection 501-3.03 Batching is modified as follows:

For Patterned Concrete, concrete shall be Class A with the following modification:

- Air Entrainment.  5 to 7%.  Air entraining agents complying with ASTM C260 may be used.

- Color.  The Patterned Concrete shall be colored full depth with a pigment which closely matches Bomanite Integral color “Coal Gray” and use a color hardener treatment similar to the Bomanite color hardener “Coal Gray.”  Colors and hardeners shall be approved by the Engineer before use.

- Release Agent.  A liquid Bomacron Release Agent, available from Bomanite Corporation, shall be applied to all concrete surfaces to be imprinted and textured.  The color shall be “Black.”  Color shall be submitted for Engineer approval.

Standard Modifications

608-3.03 CURB RAMPS.  Delete subsection in its entirety and replace with the following:

Construct curb ramps according to the details and the locations shown on the Plans.  Follow the construction requirements of Subsection 608-3.01.  Give the exposed concrete surface a coarse broom finish.  Install detectable warnings.

Add new subsection:

608-3.04 DETECTABLE WARNINGS.  Construct detectable warnings according to the details and the locations shown on the Plans.  Install detectable warning tile by embedding tile flanges into cast in place concrete construction so there are no vertical changes in grade exceeding 0.25 inch or horizontal gaps exceeding 0.5 inch.  Align pattern on a square grid in the predominant direction of travel.  Install the same type of detectable warning tile throughout the project.

Install cast iron, yellow polymer soaked or black asphalt dip finish, with slip resistant surface with handle or flange on bottom, and with truncated dome pattern; or approved equal.

Detectable warnings shall be manufactured and installed according to the Americans with Disabilities Act Accessibility Guidelines.

E61 (07/28/08)

Special Provisions

Add the following:

608-3.05 EXPOSED AGGREGATE CONCRETE.  Prior to construction of exposed aggregate concrete, the Contractor shall submit a sample of the completed exposed aggregate finish for approval by the Engineer.  The sample size shall be 4 square feet, thickness shall be the design thickness.

The surface of the exposed aggregate concrete shall be finished with a wooden float and troweled.  The surface shall not be seeded with aggregate.  After concrete has taken its initial set, expose surface aggregate using water fog spray and brooms to remove surface matrix.  The aggregate shall be exposed very lightly, approximately 1/16" to match approved samples.  The use of surface retarders may be permitted if application methods are accepted in writing by the Engineer.  After concrete has taken its final set, a weak acid wash to clean exposed aggregate surfaces shall be applied.  The acid wash shall be thoroughly neutralized and flushed from damage due to acid wash.

608-3.06 PATTERNED CONCRETE.  The excavation and embankment, forms and fine grading, placing and finishing, curing and protection operations for patterned concrete shall conform to Section 608-3.01 Concrete Sidewalks.

Place patterned concrete in dry weather with temperatures above 40 degrees Fahrenheit.

Color Hardener shall be applied evenly to the plastic surface by the dry-shake method using a minimum of 60 pounds per 100 square feet.  It shall be applied in two or more shakes, floated after each shake, and finished with a steel float.

While concrete is still in the plastic stage of set, the “Bomanite” patterning tools shall be applied in conformance to the manufacturer’s specifications to make the desired patterned surface.  The patterns shall be “Tool A Random Slate.”  All patterning and texturing tools used in the execution of this project shall be manufactured by Bomanite Corporation or an approved equal.

Bomacrom Color Curing Compound, thinned in the proportion of one part cure to one part mineral spirits (paint thinner), shall then be applied uniformly with a roller or sprayer immediately after patterning.  The coverage shall be approximately 600 to 650 square feet per gallon of unthinned curing compound.

At times when the air temperature is at or near freezing, the slab shall instead be cured using a suitable curing blanket, and if possible, the slab shall later be sealed with Bomanite Color Curing Compound at such time as the temperature is safely above freezing.  If, at any time during the curing period, any of the forms are removed, a coat of curing compound shall be applied immediately to the exposed surface.  Additional coats shall be applied if the Engineer determines that the coverage is not adequate.

Patterned concrete shall be 4 inches thick.

Special Provisions

608-4.01 METHOD OF MEASUREMENT.  Delete fifth paragraph beginning with:  “Curb Ramp” and replace with the following:

Curb Ramp.  By each installation, complete in place, including detectable warnings, ramp runs, backing curbs, flares, and landings necessary to provide a single street-level access.

E61 (07/28/08)

Add the following:

Asphalt Pathway.  By area of finished surface, including ramps.

Detectable Warning Tile.  By each, installed in place.

Exposed Aggregate Concrete, 4 Inches Thick.  By area of finished surface.

Patterned Concrete.  By area of finished surface.

608-5.01 BASIS OF PAYMENT.

When detectable warning tiles are installed as part of a curb ramp, payment for the detectable warning tile shall be subsidiary to the Curb Ramp 608(6) pay item.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 608(7A) Asphalt Pathway | Square Yard |
| 608(10) Detectable Warning Tile | Each |
| 608(16) Exposed Aggregate Concrete, 4 inches thick | Square Yard |
| 608(17B) Patterned Concrete | Square Yard |

SECTION 609

CURBING

609-3.01 GENERAL.  Delete second paragraph and substitute the following:  Expansion joints shall be constructed every 200 feet and as shown on Plans.  There shall be at least one expansion joint when distances between side streets are less than 200 feet.  Expansion joint material shall conform to the requirements of subsection 705-2.01.

Construct curb to separate pedestrian area from the landscaped area as shown on the plans.

609-3.02 CAST-IN-PLACE CONCRETE CURBING.  Add the following:

Curb, Landscape.  Construct using a curb forming or slip-form machine.

609-4.01 METHOD OF MEASUREMENT.  Add the following:

Curb, Landscape.  Measured along the front face of curb.

609-5.01 BASIS OF PAYMENT.  Add the following pay item:

| Pay Item | Pay Unit |
| --- | --- |
| 609(2D) Curb, Landscape | Linear Foot |

SECTION 615

STANDARD SIGNS

Special Provisions

615-1.01 DESCRIPTION.  Add the following:

Salvaged signs to be delivered to the DOT&PF M&O yard in Anchorage.  Coordinate delivery time with DOT&PF M&O.

Remove Tudor Medical Plaza sign from its existing location and reinstall it as shown on the plans.

Remove Lake Otis & Tudor sign from its existing location and reinstall it as shown on the plans.

Special Provisions

615-2.01 MATERIALS.  Delete the first paragraph of Item 2, including subitems a., b., c., and replace with:

2.	Sign Fabrication.  Use Type IV reflective sheeting (for lettering symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

For temporary installations the reflective sheeting may be placed on aluminum, plastic, or plywood sheet panels.

For flexible signs (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports:  Use white Type VIII or Type IX reflective sheeting for background of sign and strips.

c.	Non-Illuminated Overhead Signs with White Legends on Green Backgrounds:  Use Type IX reflective sheeting for legends and background.  Create the legend in one of the following ways:

(1)	Cut border and legend from white Type IX reflective sheeting and adhere to a green Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

d.	Fluorescent Yellow-Green School Area Signs:  Use Type VIII or Type IX reflective sheeting for background.

Reflective Sheeting Warranty.  Supply manufacturer’s warranty for reflective sheeting including retention of fluorescent yellow-green (measured according to ASTM E 2301) for ten years according to the following criteria:

Minimum Fluorescent Luminance Factor		YF:  20%

Minimum Total Luminance Factor			YT:  35%

The warranty shall stipulate:  If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

R615 (06/17/08)

Standard Modification

615-2.01 MATERIALS.  In Item 2.a Orange Background Signs, add:  Roll Up Signs:  Use 3M series RS 24, Reflexite Marathon Orange, or approved equal (based on durability and reflectivity, as determined by the Engineer).  Use flexible signs with fluorescent reflective sheeting that is Type VI or better.  E41(01/27/07)

Add the following:

5.	Tudor Medical Plaza Sign.  Relocated sign shall be on piles similar to the original construction of the sign.

615-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:

15.	Brick base around the Tudor Medical Plaza sign shall be relocated with the sign or reconstructed in the new location.  Extension of electrical to new locations shall be subsidiary to the sign relocation work for the Tudor Medical Plaza sign and the Lake Otis & Tudor sign.

615-4.01 METHOD OF MEASUREMENT.  Add the following:

Tudor Medical Plaza Sign Removal and Relocation.  Contingent sum work will be measured according to reestablishment of existing working order of sign in new location.

Lake Otis & Tudor Sign Removal and Relocation.  Contingent sum work will be measured according to reestablishment of existing working order of sign in new location.

615-5.01 BASIS OF PAYMENT.  Add the following:

| Pay Item | Pay Unit |
| --- | --- |
| 615(7) Remove and Relocate Tudor Medical Plaza Sign | Contingent Sum |
| 615(8) Remove and Relocate Lake Otis & Tudor Sign | Contingent Sum |

# SECTION 618

SEEDING

# Special Provisions

618-1.01 DESCRIPTION.  Add the following:  Topsoil and seed new or disturbed slopes and other areas directed by the Engineer.  Track the soil and apply seed, mulch, fertilizer, and water.  Provide a living ground cover on slopes as soon as possible.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Mulch	subsection 727-2.01

(01/27/07)R52

Standard Modifications

618-3.01 SOIL PREPARATION.  Delete the fourth paragraph and replace with the following:

Roughen the surface to be seeded by grooving the soil in a uniform pattern that is perpendicular to the fall of the slope.  Use one or more of the following grooving methods before the application of seed:

- Manual raking with landscaping rakes;

- Mechanical track walking with track equipment; or

- Mechanical raking with a scarifying slope board.  Form one inch wide grooves spaced no more than six inches apart.

Rounding the top and bottom of slopes to facilitate tracking or raking and to create a pleasant appearance is acceptable, but disrupting drainage flow lines is not.

618-3.02 SEEDING SEASONS.  Add the following:  Seed disturbed areas that require seeding within 14 days of the permanent cessation of ground disturbing activities in that area.

Seed between May 15 and August 15, or obtain written approval from the Engineer to seed at a different date.

618-3.03 APPLICATION. Delete first three sentences and replace with:  Apply seed mix, fertilizer, and mulch (if required) at the rate specified in the Special Provisions.  If no seed mix, seed mix application rate, or fertilizer rate are specified in the special provisions, use the recommendations of the Alaska Department of Natural Resources (ADNR) and Revegetation Manual for Alaska.

Do not seed areas of bedrock, plant beds, and areas indicated on the plans as “no seeding”.

Water and fertilizer required for application are subsidiary to the Seeding bid item.

E42 (01/27/07)

Special Provisions

Add the following:  Apply seed, mulch, and fertilizer as follows per msf.  Apply seed and mulch in one application if using the hydraulic method.  Apply fertilizer with the hydraulic method.

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
| Soil Stabilizer Slope ≤ 3:1 Slope >3:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.  (01/27/07)R52

Standard Modifications

Delete subsection 618-3.04 in its entirety, and add the following new subsections:

618-3.04 MAINTENANCE AND WATERING.  Protect seeded areas against traffic by approved warning signs or barricades.  Repair surfaces gullied or otherwise damaged following seeding.  Maintain seeded areas in a satisfactory condition until final acceptance of work.

Water and maintain seeded areas.  Water applied by this subsection is a paid Contract item.  If, in the opinion of the Engineer, too much water is being applied, reduce amount of water as directed.

Reseed areas not showing evidence of satisfactory growth within 3 weeks of seeding.  Bare patches of soil more than 10 square feet in area must be reseeded.  Erosion gullies over 4 inches deep must be filled and reseeded.  Fill the entire erosion gully to surrounding grade, even the portions less than 4 inches deep.

Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.  The Contractor is responsible for retracking, reseeding, refertilizing and remulching areas that do not show satisfactory growth, and those actions are subsidiary.

618-3.05 ACCEPTANCE.  During final inspection the Engineer will perform a visual inspection of seeding to determine final stabilization.  During the visual inspection each station and each side of the road will be considered a separate area.  The Engineer will accept seeding that has become a vegetative matt with 70% cover density in the inspection area.

Reseed areas that are not acceptable to the Engineer.

618-3.06 PERIOD OF ESTABLISHMENT.  Establishment periods extend for one complete growing season following acceptable seeding.  Employ possible means to preserve the new vegetative matt in a healthy and vigorous condition to ensure successful establishment.  Reseed areas that do not meet the specifications.  Watering and reseeding after the final inspection are subsidiary.

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance.  After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance in accordance with subsection 105-1.16.

618-4.01 METHOD OF MEASUREMENT.

After Seeding by the Pound, delete text and replace with:  By the weight of dry seed acceptably seeded and maintained.

618-5.01 BASIS OF PAYMENT.  Delete paragraphs beginning “Seeding by the Acre” and “Seeding by the Pound” and replace with:

Seeding by the Acre.  Payment is for established vegetative matt.  Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Seeding by the Pound.  Payment is for established vegetative matt.  Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Add new pay description:

Water for Seeding.  Water applied for growth of vegetative matt.  Water for hydraulic seeding, fertilizing or mulching is subsidiary.  Water after project completion is subsidiary.  E42(01/27/07)

- Special Provisions

618-5.01 BASIS OF PAYMENT.  Add the following pay item:

| Pay Item | Pay Unit |
| --- | --- |
| 618(4) Seeding | Lump Sum |

SECTION 620

TOPSOIL

Special Provisions

620-5.01 BASIS OF PAYMENT.  Add the following pay items:

| Pay Item | Pay Unit |
| --- | --- |
| 620(5) Topsoil, (24 inch depth) | Square Yard |
| 620(6) Topsoil, (4 inch depth) | Square Yard |

SECTION 621

PLANTING TREES AND SHRUBS

Special Provisions

621-1.01 DESCRIPTION.  Delete this subsection in its entirety and substitute the following:  This work shall consist of collecting, furnishing, planting, transplanting and maintaining Trees, Shrubs, and other plants on prepared areas as shown and scheduled on the Plans.

This work shall also include preparation of planting beds including furnishing and installing shredded bark mulch, Steel Landscape Edging, and half round logs as shown on the Plans.

The half round logs attached to the decorative walls and existing retaining wall shall be custom ordered as 10” diameter half logs from one of the following suppliers or approved equal:

Superior Logs	Husky Log Work
P.O. Box 110469	P.O. Box 873148
Anchorage, AK 99511	Wasilla, AK 99687
(907) 345-3323	(907) 357-6006

Each log shall be coped 1/2” on each side by Contractor to create a 9” half round log that will be attached to the concrete walls.  Logs shall be sealed with four coats of varnish from one of the following suppliers or approved equal:

Valspar	Sutherland Welles LTD.
100 Hale Street	P.O. Box 1387
Newburyport, MA 01950	Morrisville, VT 05661
(800) 345-4530	(800) 322-1245

The Valspar varnish shall be McCloskey Man O’War Marine Spar Varnish Finish.  The Sutherland Welles’ varnish shall be Exterior Polymerized Tung Oil.  Contractor shall furnish and install half round logs.

Landscape boulders shall be selected by Landscape Architect from one of the following suppliers or approved equal:

Skookum Rock Quarry	Rock Alaska Quarry
1010 Pack Horse Circle	17415 Old Glenn Highway
Chugiak, AK 99567	Chugiak, AK 99567
(907) 668-9700	(907) 696-3511

Landscape Architect should be contacted for field adjustment and placement of boulders.

Add the following subsection:

621-1.02 QUALIFICATIONS FOR LANDSCAPE CONTRACTOR.  The Contractor shall provide documentation which verifies the experience of the Landscape Contractor performing the work described in this section and maintaining landscaping projects comparable in scope, materials and diversity in 3 construction projects and 1 maintenance project within the last 5 years before the bid date of this project.  This experience shall only include projects from cold climate states or provinces and 3 shall be from South-central Alaska.  The Contractor shall demonstrate experience in landscape installation and tree and shrub planting and transplanting.

Add the following subsection:

621-1.04 SUBMITTALS.  The Landscape Contractor performing the work shall meet the following minimum requirements and shall submit the necessary documentation to show compliance to the Engineer for review and approval:

- Project Experience:  Documentation shall be submitted with the Bid Proposal that lists 3 construction and 1 maintenance projects completed by the Landscape Contractor under the same company name that are similar in scope, landscape materials, plant materials, methods of installation and maintenance to the project in the Plans and Specifications.  The list shall include at a minimum the dates, type, description and amount of work performed and the name and telephone number of a contact person at the agency or entity for which the work was performed.

- Personnel:  A list of proposed key personnel including the name of the superintendent and their assistant(s) who will direct the actual installation shall be submitted to the Engineer 14 days after Notice to Proceed.  The list of personnel shall be accompanied with a resume from the superintendent and their assistant(s).  The superintendent shall be assigned full time to this project during installation.

The superintendent and their assistant shall have a minimum of 5 years experience in directing landscape projects before the bid date of this project 3 of which shall have been in Alaska.  The resumes shall include the following information and demonstrate compliance with any requirements requested:

a.	Number of years of continuous relevant experience in landscaping projects.  Significant projects shall be listed in the resume.

b.	Recent relevant landscaping, vegetation restoration,  including project description, date of work, individual’s role on the project, and one reference for each project.

The Engineer shall have the right to approve or reject the personnel based on the qualifications as submitted.  Upon approval, the Landscape Contractor, the superintendent and their assistant(s) shall be authorized to work on this project.  The Engineer may suspend work if the Contractor substitutes unauthorized Landscape Contractor for authorized Landscape Contractor or unauthorized personnel for authorized personnel during construction without approval.  If work is suspended due to such substitutions the Contractor shall be fully liable for additional costs resulting from the suspension of work and no adjustments in Contract time resulting from suspension of work shall be allowed.

621-2.01 PLANT STOCK.  Delete this subsection in its entirety and substitute the following:  Plants shall be true to type and name in accordance with the current edition of Standardized Plant Names, American Joint Committee on Horticultural Nomenclature, except that plant species which are scheduled, but not included in the current edition of Standardized Plant Names, shall be certified by a botanist.  Each bundle, flat, or plant if not bundled, shall be labeled with the scientific name.

Variety and species shall be as scheduled on the Plans.  Trees and shrubs shall be typical of the species or variety and shall, unless otherwise specified, conform to the American Standard for Nursery Stock (ANSI-Z60.1-2004) of the American Association of Nurserymen (AAN) for type and grade.  Plant stock having severely damaged bark or trunks, broken leaders or main branches, severed main roots, or evidence of disease or injurious insects will be rejected.  Bare root trees and shrubs will also be rejected.

1.	Nursery Stock.

a.	Trees and shrubs furnished from a nursery shall have a fibrous compact root system suitable for the various species and sizes called for on the Plans.

- Container-grown plants shall be healthy, vigorous, well rooted and established in the container in which they are furnished.  Root mass shall retain its shape and hold together when removed from the container without being root-bound.

2.	Collected Stock.  These materials shall be plants growing under natural conditions in soils and in locations, which lend themselves to proper collecting practices.  The Contractor shall obtain any permits required for collection of plant stock from natural areas.  The root system of collected stock shall be larger than those specified for nursery grown material according to ANSI-Z60.1-2004, Section 1.5.2, 2.4.8, 3.3.6 - Collected.

3.	Balled and Burlapped Plants.

a.	The diameter and depths of balls on balled and burlapped trees and shrubs shall be in accordance with ANSI-Z60.1-2004.

- Balled and burlapped trees and shrubs shall be furnished with a firm ball of earth from the original and undisturbed soil in which the plant was growing.  The ball shall be wrapped with burlap or similar approved material and tightly laced to hold the ball firm and intact.  Balled and burlapped designated plant material arriving at the planting site with broken or loose balls or of manufactured earth will be rejected.

- Plants found to be rootbound by the determination of the Engineer will be rejected.

4.	Substitutions.  No substitutions of plant stock will be permitted without written approval of the Engineer.  Request for substitutions for trees and shrubs shall be submitted in writing 6 months before installation.

5.	Storage and Packing.  Plant material shall be handled and packed according to good nursery practices as required by soil and climatic conditions.  Plants that show signs of improper storage or handling will be rejected.

6.	Inspection.

a.	Planting stock shall be available for inspection in the nursery or collection field before it is dug.  The Contractor shall furnish complete and detailed information concerning the source of supply for each item of plant materials not less than 14 working days in advance of digging operations.

b.	Final inspection and acceptance for size of rootball, color, absence of defects, and for other requirements will be made at the planting site by the Engineer before placing the plants in their permanent positions.

c.	Plant material installed before acceptance by the Engineer will be removed, inspected and reinstalled if found acceptable.

621-2.02 FERTILIZER.  Add the following:  Fertilizer shall be delivered in moisture-proof containers marked with weight and manufacturer’s guaranteed analysis showing proportions of the chemical ingredients of nitrogen, phosphoric acid, and potassium within a tolerance of +/- 2%.  A slow release fertilizer 8-32-16 (N-P-K) shall be used with trees and shrubs early in the first full growing season following installation.  Fertilizer shall be applied at a rate determined by the Engineer, as described in Section 725, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.  The fertilizer tablets shall be placed near the root zone in accordance with the fertilizer manufacturer’s instructions.  Fertilizer shall be well-watered in immediately after application.

621-2.03 LIMESTONE.  Add the following:  Limestone shall be applied at a rate determined by the Engineer, as described in Section 725, in Table 726-1, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.

621-2.06 STAKES.  Add the following:  Stakes shall be installed as shown on Plans.

621-2.07 TREE WOUND DRESSING.  Delete this subsection in its entirety.

Add the following subsection:

621-2.08 STEEL LANDSCAPE EDGING.

1.	Landscape edging shall be 1/8" thick by 4" high galvanized steel edging as manufactured by one of the following suppliers or approved equal:

Sure-Loc Edging Corporation	COL-MET
494 East 64th Street	3333 Miller Park South
Holland, MI 49423	Garland, TX 75042
(800) 787-3562	(800) 829-8225

Install per supplier’s specifications.

2.	Stakes shall be a minimum of 12" long.  All stakes shall be manufactured of steel.

621-3.02 ADVANCE PREPARATION AND CLEANUP.  Add the following:  Areas which receive group plantings shall be laid out as shown on Plans.  Contractor shall mark these areas individually with flags, or other approved methods to delineate between planting areas.  Engineer shall approve the shape, size, location and general layout of planting areas before the work may proceed.

Contractor shall stake or mark with other approved methods the location of individual trees within each planting area for approval by the Engineer.

Half round logs shall be coped 1/2" on each side by contractor to create a 9" half round log that will be attached to the concrete wall.  Seal logs with two coats of McCloskey Man O’War® Marine Spar Varnish Satin Finish by McCloskey as distributed by Valspar, 1191 Wheeling Road, Wheeling, IL 60090, Toll Free: 800-845-9061.

621-3.03 PLANTING.  Delete Items 1 and 2 and substitute the following:

1.	Plant Season.

a.	Locally grown:  Locally grown native species of trees and shrubs shall be planted between June 1 and September 15.  Trees and shrubs shall be fully leafed out before planting.

b.	Imported:  Imported nursery grown plants shall be handled according to nursery recommendations.  Plants imported from out of state shall be planted between May 15 and August 1.

2.	Excavation:

a.	Topsoil shall be kept separate from subsoil and shall be rendered loose and friable.  Any material detrimental to plant growth shall be separated and disposed of at approved locations.

b.	Planting pits for trees and shrubs shall be according to the details shown on the Plans.

Delete paragraphs (c) and (d).

- Pruning.  Delete the last two sentences of paragraph b in their entirety.

- Transplanting.  Add the following:

Transplanting of existing trees shall include healthy plant material from areas to be demolished.  The plant material shall be heeled-in at the temporary nursery and replanted at locations shown on Plans as the project progresses.

  - Transplanting shall provide for the number and type of plants shown on Plans as part of the landscape installation.  Contractor shall mark the individual trees and shrubs to be transplanted for approval by the Engineer.

  - In case the Contractor cannot provide the required number of transplanted plants in acceptable condition at the time of replanting the Engineer shall allow a substitution of maximum 15% of the total amount of each type.  The substitution shall be new plant material of the same species in the largest size specified for the project.

- Placing Plants.

Add the following to paragraph a:  Trees and shrubs shall be planted as shown on the Plans and as directed on site by the Engineer.

Delete paragraph b and substitute the following:  Balled and burlapped plants, plants in wire baskets or containers shall be handled by the earth ball, container, or basket and not by the plant itself.  Wire baskets, and burlap shall be clipped and laid flat on the bottom of the planting pit as indicated on the Plans.  Containers shall be removed from the site.  The Engineer may reject any plants whose rootballs collapse during planting

- Backfilling.  Delete in its entirety and substitute the following:

Hold plants upright during the backfilling operation.  Backfill around the roots and lightly compact the soil to eliminate air pockets.  Avoid damaging roots.  When the backfilling is 1/3 complete, wire baskets and burlap shall be clipped from around the root ball and removed.  The engineer may reject any plants where root balls collapse during planting.  Add water while placing backfill, allowing the soil to soak up the water.  When backfilling is complete, build an earth berm approximately 3 inches high around the outer edge of the planting area, at least 6" from the root crown, to facilitate watering.  Remove berm after one growing season.

7.	Wrapping.  Delete this paragraph in its entirety.

- Staking and Guying.  Delete in its entirety and replace with the following:

Do not use wire for staking or guying.  Stake trees as required by engineer and wind conditions.  Use at least two 2x2 wooden stakes driven approximately three feet into the ground outside of root ball.  Tie trees securely to stakes at one third of tree height with broad ties of soft flexible material.  Do not use wire or cable.  Cut off stakes four inches above the tie.  Remove the ties after one full growing season.

Add the following subsection:

9.	Certified Arborist.  The Contractor shall retain the services of an arborist certified by the International Society of Arboriculture or the American Association of Nurserymen whose experience and qualifications are acceptable to the Engineer.  The arborist’s resume shall be submitted at least 10 calendar days before the delivery of plant material.  The certified arborist shall inspect plants for health and vigor before installation, to assure the requirements of Section 621-2.01 for plant stock, including that the materials are disease free, free of wounds, broken branches, double leaders, co-dominant trunks, or other defects.  Plants that do not meet the standards will be rejected before installation.  The certified arborist shall also be responsible for the following:

  - Inspect the tree planting process to assure that planting techniques meet the specifications of the Contract documents and match standard industry practices.

  - Inspect the plantings after installation is complete to assure that they are ready to be accepted by the Engineer.

c.	Inspect plantings twice during the growing season during Plant Establishment Period for any needed maintenance, such as watering, pruning, or removal of dead, dying, or untreatable diseased trees.

621-3.04 PERIOD OF ESTABLISHMENT.  Delete the first sentence and substitute the following:  Period of establishment shall extend for 2 full growing seasons after acceptance of all work described in this section and under Sections 618 and 620.

One full growing season shall be defined as the period between May 1 and September 30 for the purpose of this Contract.  The work under Section 621 will only be accepted as fully complete for period of establishment requirement purposes, no partial acceptance will be given.  The 2 full growing seasons period of establishment starts on May 1 after the acceptance of the work is complete.  Partial growing seasons will not be counted against the two full growing season requirement.

Add the following second paragraph:  The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance.  After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance in accordance with Subsection 105-1.16.

E43 (01/27/07)

621-3.05 CLEANUP.  Add the following:  Planted trees, shrubs, shall be kept clean of litter and garbage.

621-3.06 PLANT REPLACEMENTS.  Delete the last sentence and substitute the following:  Plants shall be replaced following the same details and specifications as used in the original Plans.  Plants that are dead or dying shall be replaced immediately during the months of June through September.  Plants dead at the end of the growing season shall be replaced at the beginning of the following season.

621-3.07 MAINTENANCE.  Delete the paragraph and substitute with the following:  Maintenance includes the care of trees and shrubs during the period of establishment, including the non-growing season.  Specific work includes watering, pruning, weeding, pest control, and protection of planted areas.  At the beginning and end of each growing season, the Engineer and Contractor shall undertake a joint inspection to review conditions and document any changes in maintenance or acceptance of plantings.

1.	Watering.  The Contractor shall water trees and shrubs to maintain the plants in a healthy, vigorous growing condition.  The root zone of plants shall be kept moist at all times.

2.	Disease Control.  The Contractor shall apply pesticides, insecticides, or other disease-control methods as necessary to maintain plant health.  Permission of the Engineer and appropriate permits for the application of insecticides from the Alaska Department of Environmental Conservation must be obtained prior to the application of any regulated products.

3.	Pruning.  Prune plant materials with appropriate pruning techniques to remove dead or dying wood and to improve the shape and or vigor of the plants.  Cuts shall not be painted.  Pruning of flowering trees shall be scheduled to occur right after flowers drop off or decay.  Damaged trees or those that constitute health or safety hazards shall be pruned as directed by the Owner’s Representative at any time of the year.  Evergreens are not to be pruned without the approval of the Engineer.

4.	Fertilizing.  Trees and shrubs shall receive an application of fertilizer in accordance with Section 621-2.02 Fertilizer.  The application shall occur between May 15 and June 15 of each growing season following planting.  The fertilizer tablets shall be placed near the root zone in accordance with the fertilizer manufacturer’s instructions.  Fertilizer shall be well-watered in immediately after application.  The Contractor shall notify the Engineer in writing four working days prior to applying any fertilizers.  Written notice shall state the time and location of fertilizer application.

TABLE 621-1
Maintenance Fertilizer Schedule

| Plant Type | Fertilizer | Application Rate |
| --- | --- | --- |
| Coniferous Trees | 8-32-16 | 1/3 lb for each 1 inch of Caliper |
| Deciduous Trees | 8-32-16 | 1/3 lb for each 1 inch of Caliper |
| Shrubs and Ground Cover | 8-32-16 | 7 lbs per 1,000 square feet. |

Add the following subsection:

621-3.08 TEMPORARY FENCE.  The placement of temporary fence shall occur after the trees have been installed.  The temporary fence shall be routed at the outside edges of tree planting areas as shown on the Plans.  Minor modifications and adjustments to layout and post spacing shall be made to better fit the site conditions.  Protected trees shall be enclosed in such a manner that the fabric will not damage branches and will not allow branches to protrude.  Temporary fences shall be erected at the end of the growing season no later than October 5.  They shall remain in place until the next growing season and shall be removed no later than May 10.  Contractor shall be responsible for erecting and removing the temporary fence during the period of establishment as described under 621-3.04, Period of Establishment.

Contractor shall conduct periodic visual inspections and repair immediately any damage due to moose, other wildlife, or vandalism.

Contractor shall erect the temporary fence at the end of the final growing season of the period of establishment and leave it in place for Owner to assume maintenance from that point on.

621-4.01 METHOD OF MEASUREMENT.  Delete this entire subsection and substitute the following:  Measurement of new or transplanted trees and shrubs , Pay Items 621(1), 621(2) and 621(6), shall be by the actual number planted and maintained in accordance with the Plans and Specifications, and as accepted by the Engineer.

Furnishing and installing shredded bark mulch, additional topsoil backfill mix, fertilizing, temporary fencing, disposal of unsuitable and surplus material, water for maintenance used and all work required during the two full growing season period of establishment shall not be paid for separately, but shall be subsidiary to Pay Items 621(1), 621(2) and 621(6).

Pay Item 601(1) includes the White Paper Birch and Columnar Aspen trees.  Pay Item 601(2) includes the Peking Cotoneaster, Red Twig Dogwood, Ural False Spirea, Vanhoutte Spirea, and the Canadian Lilac shrubs.  Pay Item 601(6) includes Variegated Reedgrass and the Perennial Iris.

Landscape Boulders.  By each, installed in place.

Landscape Edging.  By linear foot installed.

Half Round Log.  By linear foot installed.

Transportation, excavation, equipment, and labor for placement shall not be measured separately, but shall be subsidiary to Pay Items 621.

621-5.01 BASIS OF PAYMENT.  Delete second sentence and add the following:  Partial payments of up to 80% of full amount may be authorized for Items 621(1) and 621(2) and 621(6) at the time of acceptance.  The balance shall be paid during the period of establishment with one final payment of min 10% of the full amount paid at the completion of the period of establishment.

Add the following Pay Items:

| Pay Item | Pay Unit |
| --- | --- |
| 621(6) Perennials | Lump Sum |
| 621(8) Landscape Boulders | Each |
| 621(10) Landscape Edging | Linear Foot |
| 621(16) Half Round Log | Linear Foot |

Special Provisions

Delete Section 622 in its entirety and replace with the following:

SECTION 622

REST AREA FACILITIES

622-1.01 DESCRIPTION.  The work under this section is for installation of trash receptacles, benches, and transit shelters as shown on Plans.  Contact Randy Bergt (343-8285) with People Mover two weeks prior to installation.

622-3.01 METHOD OF MEASUREMENT.  Benches, trash receptacles, and transit shelters shall be measured by each installed unit and shall include installation materials, equipment, and cleanup.

622-4.01 BASIS OF PAYMENT.  Payment will be made under:

Installing the bench inside the transit shelter is subsidiary to Pay Item 622(32).

| Pay Item | Pay Unit |
| --- | --- |
| 622(14B) Trash Receptacle | Each |
| 622(15) Bench | Each |
| 622(32) Transit Shelter | Each |

SECTION 626

SANITARY SEWER SYSTEM

Special Provisions

626-3.01  CONSTRUCTION REQUIREMENTS.  Add the following:  AWWU will replace sanitary sewer lids as determined by a pre construction inspection conducted by AWWU.  Contractor shall provide traffic control for this pre construction inspection and coordinate with Joe Sanks at AWWU (564-2717).

Contractor shall not dispose of water from dewatering in storm drain system or wetland area without written approval from the Engineer.

Sanitary sewer abandonment work on Lake Otis Parkway shall be accomplished by using the abandon in place method.  This method is to place one foot of concrete at the beginning of the pipe, calculating the total internal volume of the pipe, filling the pipe with sand slurry (sand slurry shall consist of a mixture of water and sand with an approximate ratio of seven gallons of water per cubic foot of sand) equal to the total calculated volume, and placing one foot of concrete at the end of the pipe.  The total lineal footage of the sanitary sewer main abandoned shall be shown on the record drawings.  Abandon the sanitary sewer manhole in place by removing the lid and cone.  Fill the manhole with sand slurry and provide road structural section to bring to proposed grade of road, as shown on the plans.

The disconnection of the Tudor Motel sanitary sewer service shall include the following:

1.	Cut pipe at least 10’ from the main line and plug with a watertight cap or end plug

2.	Install a sanitary sewer service connection marker

3.	Provide AWWU a record drawing of the abandoned service connection

A disconnect permit shall be acquired from AWWU prior to the disconnection.  Contractor shall schedule inspection with AWWU and furnish the following information:

1.	Date when disconnect will be made

2.	Where disconnect will be made, including lot, block, subdivision, address, swing ties, depth, type of pipe, and size

3.	Who will disconnect the service

4.	Owners name, address, and telephone number

An AWWU inspector shall observe the disconnection to ensure quality.

626-4.01  METHOD OF MEASUREMENT.  Add the following:

Disconnect Sanitary Sewer Service.  By the number of sanitary sewer services disconnected according to current AWWU standards.

626-5.01 BASIS OF PAYMENT.  Delete the second paragraph and replace with the following:

Excavation, bedding, and backfill are subsidiary to Pay Item 626(3) and Pay Item (626(5).

Dewatering for sanitary sewer pay items shall be subsidiary to Pay Items 626(3) and 626(5).

Abandonment of sanitary sewer manhole shall be subsidiary to Pay Item 626(5).

Add the following pay items:

| Pay Item | Pay Unit |
| --- | --- |
| 626(3) Disconnect Sanitary Sewer Service | Each |
| 626(5) Abandon Sanitary Sewer Main | Lump Sum |

# SECTION 627

WATER SYSTEM

Special Provisions

627-3.01 GENERAL.  Add the following:  AWWU will replace valve box lids as determined by a pre construction inspection conducted by AWWU.  Contractor shall provide traffic control for this pre construction inspection and coordinate with Joe Sanks at AWWU (564-2717).

Contractor shall not dispose of water from dewatering in storm drain system or wetland area without written approval from the Engineer.

Contractor shall do excavation work for waterline taps.  AWWU will perform all 8” taps into existing waterlines.  Contact Joe Sanks at AWWU (564-2717) one week prior to anticipated tap to coordinate this work.

Contractor shall locate existing 6” vent and extend it to the proposed location shown in the plans.  Extend the vent with like material.

Contractor shall supply new hydrants for Pay Item 627(6) Fire Hydrant Relocation.  Existing hydrants called out to be relocated become the property of the Contractor.

627-4.01  METHOD OF MEASUREMENT.  Add the following:

6.	Disconnect Water Service.  By the number of water services disconnected from the mainline and capped according to current AWWU standards.

627-5.01 BASIS OF PAYMENT.  Delete the third paragraph and replace with the following:

Excavation, bedding, and backfill are subsidiary to Pay Items 627(8) Water Service Connection, 627(6) Fire Hydrant Relocation, and 627(13B) Disconnect Water Service, and 627(14) Relocate Vent for Water Vault.

Dewatering for fire hydrant relocation and water service connection, disconnect water service, and relocate vent for water vault shall be subsidiary to pay items 627(6), 627(8), 627(13B), and 627(14) respectively.

Installation of new hydrants and disposal of existing hydrants shall be subsidiary to Pay Item 627(6) Fire Hydrant Relocation.

Adjustment of valve boxes in connection with fire hydrant relocation shall be subsidiary to Pay Item 627(6).

The removal and disposal of the water service for Lot 13A (project parcel 9) is subsidiary to Pay Item 627(8) Water Service Connection.

Add the following pay items:

| Pay Item | Pay Unit |
| --- | --- |
| 627(13B) Disconnect Water Service | Each |
| 627(14) Relocate Vent for Water Vault | Lump Sum |

SECTION 635

INSULATION BOARD

Special Provisions

635-4.01  METHOD OF MEASUREMENT.  Add the following:

Insulation Board.  By area of board installed.

635-5.01 BASIS OF PAYMENT.  Add the following:

| Pay Item | Pay Unit |
| --- | --- |
| 635(2) Insulation Board | Square Foot |

Special Provisions

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

639-1.01 DESCRIPTION.  Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS.  Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION.  Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed as shown on the Plans or as directed.  Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule.  The contract unit price for driveways and approaches shall be full compensation for furnishing equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.  (05/09/02)R58

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 639(6) Approach | Each |

Special Provisions

Delete Section 641 and replace with the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION.  Provide project administration and construction activities to control erosion, sedimentation, and pollution from the Project, according to this section and applicable local, state, and federal requirements.  When working in contaminated soils area, the Contractor is required to follow criteria found in the Corrective Action Plan prepared by DOWL HKM in 2008.

Utilities.  Utilities will be relocated by others concurrently with construction of this project.  A utility company performing ground disturbing activity on the project shall be identified in the SWPPP.  The Contractor will be responsible for controlling sediment and erosion and stabilizing areas disturbed during underground utility relocation.

641-1.02 DEFINITIONS.  These definitions apply only to Section 641.

1.	Alaska Certified Erosion and Sediment Control Lead (AK-CESCL). Certification demonstrating the person has completed training, testing, and other requirements recognized by the Department to satisfy the Environmental Protection Agency (EPA) National Pollution Discharge Elimination System (NPDES) Construction General Permit (CGP) requirement for “qualified personnel.”  AK-CESCL certificates issued in conformance with, and under the authority of the AK-CESCL Memorandum of Understanding are recognized by the Department as meeting this standard.  Certifications published on the Department’s Construction website under the title “AK-CESCL Equivalent Certifications” will also be recognized.  Other certifications may be approved by the Engineer on a case-by-case basis.

2.	Area of Land Disturbance.  The area of land (soil) that will be disturbed by a construction activity including, but not limited to, clearing, grubbing, excavating, constructing embankment, grading, stockpiling erodible material, or processing material.  Area of pavement removal is not included if the pavement removal work does not remove the aggregate underlying the pavement.

3.	Best Management Practices (BMPs).  Devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices. BMPs include temporary or permanent structural and non-structural devices. BMPs when used alone or in combination, minimize erosion or contain sediment within the Project, and reduce the discharge of pollutants.

4.	Clean Water Act (CWA).  United States Federal Water Pollution Control Act (33 U.S.C. 1251 et seq.)

5.	Construction Activity. Physical activity by the Contractor or any Subcontractor or Utility Company within the Project that may result in land disturbance. Construction Activity includes, but is not limited to, installation and maintenance of BMPs, clearing, grading and excavating.

6.	Construction General Permit (CGP). The Storm Water Construction General Permit for Discharges from Large and Small Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES).

7.	Electronic Notice of Intent (eNOI). The Electronic Notice of Intent submitted to EPA, to begin Construction Activity under the CGP.

8.	Electronic Notice of Termination (eNOT). The Electronic Notice of Termination submitted to EPA, to end coverage under the CGP.

9.	Erosion and Sediment Control Plan (ESCP). A project-specific document developed by the Department to identify general information about the Project.  The ESCP may include measures to minimize erosion and contain sediment within the Project site.  The ESCP provides general information for the Contractor’s use in development of the Project SWPPP.

10.	Final Stabilization. Final stabilization occurs when soil disturbing activities at the site have been completed and one of the following methods, as identified in the contract, has been completed: (a) establish a uniform and evenly distributed perennial vegetative cover with a density of 70 percent of the native background vegetative cover, or (b) construct non-erodible permanent stabilization measures (such as riprap, gabions, geotextiles, pavement, and crushed aggregate base course) where vegetative cover is not required.

11.	Haul Route.  Existing or newly constructed road where construction materials are transported and where disposition of sediments or erodible materials may result from the material hauling activity or from the Contractor’s activity to construct or maintain the road.

12.	Hazardous Material Control Plan (HMCP). The Contractor's project specific detailed plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material, including but not limited to, petroleum products related to construction activities and equipment.  The HMCP is integrated into the SWPPP.

13.	Joint Inspection.  SWPPP inspection performed by the SWPPP Manager or SWPPP Manager’s Representative, and the Engineer or Engineer’s representative.  Joint Inspection is performed together, as a collaborative effort of the Contractor and the Department.

14.	Operator.  The party associated with a construction project, staging area, material site, material processing site, disposal site, or haul route, with either:

	operational control of the plans and specifications, including ability to make modification to those plans and specifications.

	day-to-day operational control (e.g. authorized to direct workers or equipment operations) of activities related to the project, staging area, haul route, or material or disposal site.

15.	Pollutant. As defined in 40 CFR 122.2 (a partial listing of this definition includes solid waste, sewage, garbage, chemical wastes, dredged spoil, rock, sand).

16.	Project.  The physical limits of the construction site, project staging areas, haul routes, and material and disposal sites directly related to the Contract.  Contractor or Commercial Operator furnished material sites, material processing sites, disposal sites, haul routes, staging, and equipment storage areas are not included in the Project.

17.	Spill Prevention, Control and Countermeasure Plan (SPCC). The Contractor’s project specific detailed plan for petroleum spill prevention and control measures that meets the requirements of 40 CFR 112.

18.	Storm Water Pollution Prevention Plan (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project site, and to prevent discharge of pollutants that exceed applicable water quality standards as required by the CGP.

19.	SWPPP Amendment.  A revision or document that adds to, deletes from, or modifies the SWPPP.

20.	SWPPP Manager.  The Contractor’s qualified representative, as defined in 641-1.04, delegated responsibility for implementing the SWPPP, updating the SWPPP, performing and certifying inspections, supervising Section 641 work, monitoring construction activities, and with authority to suspend work and implement corrective actions.

21.	SWPPP Manager’s Representative.  The Contractor’s qualified representative, as defined in 641-1.04, who may be delegated certain SWPPP Manager’s tasks and authorities.

22.	SWPPP Preparer.  The Contractor’s representative who is responsible for designing the initial SWPPP.

23.	SWPPP Subcontractor Coordinator. The Subcontractor’s representative with authority to direct the Subcontractor’s work, and who is responsible for coordination with the SWPPP Manager and for the Subcontractor’s compliance with the SWPPP.

24.	SWPPP Template. EPA’s template for the Contractor’s use in preparing the SWPPP where EPA is the NPDES permitting authority (Alaska).  The template is available online at EPA’s website.  Select “SWPPP Template – Unauthorized States.

25.	Temporary Stabilization. The protection of exposed soils (disturbed land) from wind and water erosion during the construction process until final stabilization occurs.

641-1.03 SUBMITTALS.  Submission deadlines in this section supersede Subsection 108-1.03.

1.	All Projects:

A.	HMCP.  Submit three copies of the HMCP as an appendix to the SWPPP, and in accordance with the requirements for submitting the SWPPP.

B.	SPCC. Submit three signed copies of the SPCC (if required under Subsection 641-2.03) to the Engineer. Deliver these documents to the Engineer at least 21 calendar days before beginning Construction Activity.

The Department will keep the SPCC as a record document, and reserves the right to review it and require modifications.

C.	SWPPP. Submit three signed copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 calendar days before beginning Construction Activity.

The Department will review the SWPPP submittals within 14 calendar days after they are received. Submittals will be returned to the Contractor, and marked as either requiring modification or as approved by the Department.

D.	Beginning Construction Activity. On projects that disturb one acre or more of land, submit your eNOI to EPA and submit a copy of your eNOI to the Engineer at the same time. The Department will submit the Department’s eNOI to the EPA. Allow adequate time for state and federal processing of both eNOIs, and for the EPA to list both eNOIs as active status, before beginning Construction Activity.  The Contractor and the Engineer must sign and certify the approved SWPPP according to the CGP requirements, as detailed in Appendix G of the CGP, before the Contractor submits their eNOI to EPA. The certification statement cannot be amended or edited.

E.	Ending CGP Coverage.  On projects that disturb one acre or more of land, within 30 days after the Engineer has determined you may end SWPPP activities according to Subsection 641-3.01(5), submit your eNOT to EPA and send a copy of the eNOT to the Engineer. Within 30 days of the Engineer’s determination, the Department will submit the Department’s eNOT to the EPA, and will terminate the CGP coverage.

2.	Projects that disturb five acres or more of land:

Submit a copy of the Engineer-approved, signed and certified SWPPP, and copies of the Contractor’s eNOI and the Department’s eNOI, with the required permit fee to the Alaska Department of Environmental Conservation (ADEC) Storm Water Coordinator.  Transmit a copy of the ADEC SWPPP Review Letter to the Engineer.  Amend the SWPPP as needed to address ADEC review comments.

641-1.04 PERSONNEL QUALIFICATIONS.  Include qualifications of the SWPPP Preparer, SWPPP Manager, and SWPPP Manager’s Representatives in the SWPPP.

The SWPPP Preparer must meet at least one of the following qualifications:

- current certification as a Certified Professional in Erosion and Sediment Control (CPESC)

- current certification as Alaska Certified Erosion and Sediment Control Lead (AK-CESCL) and at least three years experience in erosion and sediment control (provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement)

- Professional Engineer registered in the State of Alaska

The SWPPP Manager must meet all the following qualifications:

- current certification as Alaska Certified Erosion and Sediment Control Lead (AK-CESCL)

- duly authorized representative, as defined in the CGP, Appendix G

The SWPPP Manager’s Representative must hold a current AK-CESCL certification.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.  The eNOI and eNOT must be signed and certified by a responsible corporate officer, in accordance with CGP Appendix G, Section 11.  Signature and certification authority for the eNOI and eNOT cannot be delegated.

Delegate signature and certification authority, exclusive of the eNOI and eNOT, to the SWPPP Manager, in accordance with CGP Appendix G, Section 11.B, for the SWPPP, SWPPP amendments, SWPPP inspections, and other related CGP documents.  Include the certification statement verbatim from CGP Appendix G, Section 11.D, on the written delegation.  Delegation is not required if the SWPPP Manager is a responsible corporate officer for Contractor, as defined in CGP Appendix G, Section 11.A.  Include a copy of the written delegation in the SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  Develop the SWPPP and all associated documents, in accordance with the requirements of the CGP.

The construction site including all areas of utility relocation and all Department furnished material sources, disposal sites, haul routes, staging, and equipment storage areas must be included in the Project eNOI and must be covered in the Project SWPPP.  The Department and the Contractor are both operators for these areas.

The Department is not an operator for Contractor furnished:

- material sites

- material processing sites

- disposal sites

- haul routes

- staging areas

- equipment storage areas

Compliance with NPDES and other applicable federal, state, and local requirements, and securing all necessary clearances, rights, and permits for these Contractor furnished sites and areas are the sole responsibility of the Contractor.  Document the name of each operator, and the locations of these areas in the Project SWPPP.

The Department is not an operator for commercially operated:

- material sites

- material processing sites

- disposal sites

- haul routes

- staging areas

- equipment storage areas

Compliance with NPDES and other applicable federal, state, and local requirements, and securing all necessary clearances, rights, and permits for these commercially operated sites and areas are the sole responsibility of the commercial operator.  Document the name of each operator, and the locations of these areas in the Project SWPPP.

Use the Department’s ESCP as a starting point for designing the SWPPP.  The approved SWPPP replaces the ESCP.  Develop the SWPPP in accordance with EPA’s template for Unauthorized States. Incorporate and cite applicable requirements of the project permits and environmental commitments into the SWPPP.  Use the Department’s documentation of consultation with the State Historic Preservation Officer and federal agencies for consideration of historic properties and endangered species.  Make additional consultations as necessary for Contractor specific activities, changes to the project footprint, and changes to the construction timeline.

The initial SWPPP may be designed and submitted before the SWPPP Preparer visits the Project but Construction Activity is not permitted until the SWPPP Preparer has visited the Project.  Use the results of the Project visit in the design of the initial SWPPP, or if the visit occurs after the initial SWPPP has been submitted to the Engineer, to amend the SWPPP as necessary before beginning Construction Activity.  Consider opportunities to adjust phasing to minimize potential for erosion.  Consider appropriate selection, application, and sequencing of BMPs.  Consider sequence of BMP installations in relation to progress schedule.

The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed.  Describe site specific BMPs, source controls, sediment controls, discharge points, and a plan including schedule and implementation procedures for temporary and final stabilization.  Describe all temporary and permanent stabilization measures.  Include typical installation drawings for all BMPs that will be incorporated in the Project.  Include the Contractor’s progress schedule in the SWPPP.  The plan must include both erosion control and sediment control measures.  The plan must address first preventing erosion, then minimizing erosion, and finally trapping sediment before it leaves the project site.

The SWPPP must provide erosion and sediment control, in accordance with the CGP and this specification, for all land disturbances resulting from the Contractor, all Subcontractors and utility company activities during the course of the contract.  The SWPPP must  consider the activities of utility companies performing work on the Project.  The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, and  the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity within the Project, and identify the areas over which each operator has operational control.

Specify the line of authority and designate a SWPPP Manager for implementing SWPPP compliance.  Provide 24 hour contact information for the SWPPP Manager, and for each SWPPP Manager’s Representative.  The SWPPP Manager and each SWPPP Manager’s Representative must have 24 hour contact information for all SWPPP Subcontractor Coordinators.

The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, inspection reports, records of land disturbance and stabilization, and any other documents necessary to satisfy the requirements of the CGP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Prepare a project specific HMCP for prevention of pollution from storage, use, containment, cleanup, and disposal of hazardous material, including oil products related to construction activities and equipment (See 40 CFR 117 and 302 for listing of hazardous materials).  Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

List the types and approximate quantities of response equipment and cleanup materials available on site. Include a list and location map of cleanup materials, at each different work site and readily available off site (main site, material site, batch plant, storage yard, explosives dump, equipment or fueling yard, etc). Vehicles and other mobile equipment must carry oil absorbent pads.

Specify the line of authority and designate a Contractor field representative for spill response, and one coordinator from each subcontractor. Provide 24 hour contact information for the Contractor’s field representative.  The Contractor’s field representative must have 24 hour contact information for the coordinator from each subcontractor.

List and give the location and estimated quantities of hazardous materials, including office materials, to be used or stored on site.  Store hazardous materials in covered storage areas.  Include secondary containment for all hazardous material storage areas.

Identify the locations where storage, fueling and maintenance activities will take place, describe the maintenance activities, and list controls to prevent the accidental spillage of oil, petroleum products, and other hazardous materials. Store spill response materials, appropriate to the hazards associated with that site, in sufficient quantity at each identified location.

Detail procedures for containment and cleanup of hazardous substances.  Detail a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by accidental spills.  Detail a plan for dealing with unexpected contaminated soil and water encountered during construction.

Detail methods of disposing of waste petroleum products and other hazardous materials generated by the Project.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Include the HMCP as an appendix to the SWPPP.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC) REQUIREMENTS.  Prepare and implement a project specific SPCC when required by 40 CFR 112, including when both of the following conditions are present on the Project:

- oil or petroleum products from a spill may reach navigable waters, and

- total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Develop the SPCC and all associated documents, in accordance with the requirements of the 40 CFR 112 and include the following in your SPCC:

- Operating procedures that prevent oil spills

- Control measures installed to prevent a spill from reaching navigable waters

- Countermeasures to contain, clean up, and mitigate the effects of an oil spill

You may self-certify the SPCC if the total above ground oil storage capacity is 10,000 gallons or less, and you meet all the requirements for self-certification in 40 CFR 112. Otherwise the SPCC must be certified by, stamped with the seal of, dated by, and signed by a Professional Engineer registered in the State of Alaska.

Reference the SPCC in the SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF SWPPP MANAGER AND SWPPP MANAGER’S REPRESENTATIVE.  The SWPPP Manager is responsible for work related to this section. The SWPPP Manager is responsible for the Contractor’s compliance with the CGP and CWA, and to assure the Contractor’s Construction Activity does not result in discharge of pollutants that exceed applicable water quality standards.

The SWPPP Manager shall sign and certify inspection reports, and update the SWPPP.  The SWPPP manager may not delegate these tasks.

The SWPPP Manager may assign the SWPPP Manager’s Representative responsibility to perform SWPPP inspections, direct or oversee installation, maintenance, and removal of BMPs as detailed in the SWPPP or as directed by the Engineer.  The SWPPP Manager and the SWPPP Manager’s Representative shall be knowledgeable in the requirements of this section, the SWPPP, the BMPs, the CGP, the permits, and the environmental commitments identified in the contract.  The SWPPP inspections must be performed by either the SWPPP Manager or the SWPPP Manager’s Representative.

The SWPPP Manager and the SWPPP Manager’s Representative shall have the Contractor’s complete authority to suspend construction activities that do not conform to the SWPPP or CGP.

Report CGP noncompliance which may endanger health or the environment to the EPA. Information must be provided orally within 24 hours from the time you become aware of the circumstances. Submit written notice as described in the Appendix G, Standard Permit Conditions, #12 Reporting Requirements of the CGP.

641-2.05 MATERIALS.  Comply with the material requirements described in the Specifications.

Use materials suitable to withstand hydraulic and soil forces, and to control erosion and trap sediments in accordance with the requirements of the CGP.

641-3.01 CONSTRUCTION REQUIREMENTS.  Comply with the requirements of the CGP.

1.	Starting Construction.

	Do not begin Construction Activity until authorized by the Engineer

	On projects that disturb one acre or more of land, do not begin Construction Activity until the Project eNOI for the Department and for the Contractor are both listed as Active Status on the EPA website

	Do not begin Construction Activity until the SWPPP preparer has visited the Project and the date of the visit and the persons conducting the visit have been documented in the SWPPP.

Post notices on the outside wall of the project office, and at publicly accessible locations near the beginning and end of the Project. Protect postings from the weather and locate so the public can read them without obstructing construction activities (for example, at an existing pullout).  Include the following information in each of the postings:

	Copy of all eNOIs related to this project

	Name and phone number of SWPPP Manager

	Location of the SWPPP available for public viewing.

Keep the updated SWPPP, HMCP and SPCC at the on-site project office. If there isn’t an on-site project office, keep the information at a location suitable to the Engineer.

Install an outdoor rain gauge in a readily accessible location on the Project.

Ensure all subcontractors and utility companies operating within the Project understand and comply with the SWPPP.

Install sediment controls in accordance with the SWPPP and SWPPP sequencing and phasing, and before beginning Construction Activity that may result in land disturbance.

2.	During Construction.

Comply with requirements of the HMCP and SPCC, and all state and federal regulations that pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of discharges of petroleum products and other hazardous materials.  Perform fueling operations in a safe and environmentally responsible manner.  Place absorbent pads under fill ports while fueling, and under equipment during maintenance or repairs.  Install secondary containment under all stationary equipment that contains petroleum products.

Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.  Report petroleum product spills as required by federal, state and local law, and as described in the HMCP and SPCC.

Comply with the requirements of the SWPPP.  Implement temporary and permanent erosion and sediment control measures identified in the SWPPP. Keep the SWPPP current.  If storm water discharges threaten water quality, take immediate action. Comply with the requirements of 18 AAC 70 State of Alaska Water Quality Standards, AS 41.14.870 Protection of Fish and Game, 11 AAC 112 Alaska Coastal Management Program, Section 404 of the CWA, and all other applicable federal, state, and local statutes and regulations.

Coordinate with subcontractors and utility companies doing work in the project area so BMPs, and temporary and permanent stabilization are installed, maintained, and protected from damage.

3.	Corrective Action and Maintenance of BMPs.

Maintain temporary and permanent erosion and sediment control measures in effective operating condition.  Remove sediment and debris from sediment traps, silt fences, and sediment ponds before sediment or debris accumulates to 50% of the BMP’s design capacity.

Implement corrective action:

- if an incident of non-compliance with the SWPPP, CGP, or CWA is identified

- if an inspection identifies the SWPPP or any part of the SWPPP is ineffective in preventing the discharge of pollutants that exceed applicable water quality standards

- if the Project Engineer determines the SWPPP or any part of the SWPPP is ineffective in preventing the discharge of pollutants that exceed applicable water quality standards

- if any BMP is damaged, undercut, or unable to effectively perform the intended function

- if any BMP is at or exceeding 50% of its design storage capacity

- whenever there is a change in conditions, design, construction, operation, or maintenance that could have a significant effect on the discharge of pollutants in storm water leaving the Project

Implement corrective actions as soon as possible, and before the next storm event whenever practicable.  If implementation before the next storm event is impracticable, the situation must be documented in the SWPPP and alternative BMPs must be implemented as soon as possible.

4.	Stabilization.

Stabilization may be accomplished using temporary or permanent measures.

Initiate stabilization of disturbed areas, stockpiles, and of erodible aggregate layers so that all of the following conditions are satisfied:

- as soon as practicable

- as soon as necessary to avoid discharge of pollutants that exceed applicable water quality standards

- as identified in the SWPPP schedule and/or phasing

- in accordance with stabilization schedule requirements of applicable project permits

- no later than 14 days after each cessation of land-disturbing activities.

Land may be disturbed multiple times during a project. Coordinate work to minimize area of land disturbance as much as practicable. Do not disturb more area than you can stabilize in the time limits specified, and with the resources available.

Before deactivating a stream bypass or stream diversion install stabilization up to ordinary high water:

- drainage structure – at the inlet and outlet

- bridge – at the upstream and downstream sides and between/below

- drainage structure, bridge – in the area upstream or downstream disturbed during construction

Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install stabilization up to ordinary high water:

- at the inlet and outlet of the culvert, drainage structure, or bridge

- in the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge

- under the bridge

When installing a culvert or other drainage structure where stream bypass is not used for construction, temporary or permanent stabilization may need to be installed concurrently or immediately after placing the culvert or drainage structure in order to comply with applicable project permits and to prevent discharge of pollutants that exceed applicable water quality standards.

Install temporary or permanent stabilization:

- at the culvert or drainage structure inlet and outlet

- in the area upstream and downstream of the culvert or drainage structure, that is disturbed in the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure

Prevent project contaminates from entering all bodies of water (flowing and not flowing) on and off the project site, during all phases of construction (from “the effective date of the Notice to Proceed,” Section 108-1.02 to the issue of the “Letter of Final Acceptance,” Section 105-1.16) in conformance with the project requirements.  Maintain project water quality as specified in the Plans and Specifications (including Special Provisions).  Including, but not limited to, construction/installation of drainage structures providing erosion, sediment and pollution control measures, including stabilization, at the drainage structure inlet and outlet and up/down stream from the structure.

5.	Ending SWPPP Activities and SWPPP Maintenance.

The Engineer will determine SWPPP activities have ended when all of the following requirements are met:

	Land disturbing activities have ceased

	The Project site (including material sources, disposal sites, etc.) has achieved final stabilization

	Temporary BMPs have been removed

Submit eNOT in accordance with Subsection 641-1.03(1)E.

6.	Record Retention.

Transmit one copy of the final SWPPP, including all amendments and appendixes, to the Engineer when the eNOT is filed.

Retain copies of the SWPPP, including all amendments and appendixes, and other records required by the CGP, for at least three years after the date of eNOT.  If EPA issues a Notice of Violation (NOV) or begins investigation for a potential NOV before the three year retention period expires, retain the SWPPP and all records related to the SWPPP and CGP until EPA has determined all issues related to the NOV are settled.

641-3.02 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.  Perform inspections, prepare inspection reports, and prepare SWPPP amendments in compliance with the SWPPP and the CGP. The SWPPP of record is the SWPPP maintained by the Contractor.

1.	Before Starting Construction.

Before beginning Construction Activity, conduct a Joint Inspection of the Project.  Include the SWPPP Preparer in the inspection and consider any necessary revisions to the draft SWPPP, or if the SWPPP has already been approved, any necessary amendments to the SWPPP.  Consider opportunities to adjust phasing to minimize potential for erosion.  Consider appropriate selection, application, and sequencing of BMPs.  Consider sequence of BMP installations in relation to progress schedule.  Identify sediment controls that need to be installed prior to commencing other Construction Activity.

2.	During Construction.

Conduct Joint Inspections on one of the following schedules:

- at least once every seven days during construction, or

- at least once every 14 days during construction and within 24 hours of the end of a storm event of 1/2 inch or greater rainfall in a 24 hour period (1/2 inch rainfall as recorded at the project site rain gauge)

Indicate the inspection schedule in the SWPPP and conduct Joint Inspections in accordance with the selected schedule. At least once each month include the SWPPP Preparer in the joint inspection.

3.	Before Seasonal Suspension of Work.

Conduct Joint Inspection before seasonal suspension of work to review condition and applicability of BMPs and SWPPP.  Confirm SWPPP, temporary stabilization, and BMPs are installed and functioning in accordance with the requirements of Subsection 641-3.01.

4.	During Winter Work.

Conduct Joint Inspections in accordance with the inspection schedule indicated in the approved SWPPP.

Inspection frequency during winter work may be reduced to at least one inspection every month if all of the following requirements are met:

- runoff is unlikely due to winter conditions (e.g. the site is covered with snow, ice or the ground is frozen)

- approval from the Engineer

- the revised inspection frequency is documented as an amendment to the SWPPP.

5.	During Seasonal Suspension of Work.

Conduct Joint Inspections in accordance with the inspection schedule indicated in the approved SWPPP.

Inspection frequency during seasonal suspension of work may be reduced to at least one inspection every month if approved by the Engineer and the revised inspection frequency is documented as an amendment to the SWPPP, and either of the following requirements is met:

- the entire site is temporarily stabilized

- runoff is unlikely due to winter conditions (e.g. the site is covered with snow, ice or the ground is frozen)

The Engineer may waive winter monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

- below-freezing conditions are anticipated to continue for more than one month (Include historical weather data in the SWPPP justifying assumptions)

- land disturbance activities have been suspended

- beginning and ending dates of the waiver period are documented as an amendment to the SWPPP.

6.	Project Completion.

Conduct Joint Inspection to ensure final stabilization is complete throughout the Project and all temporary BMPs are removed.

7.	Items and Areas to Inspect.

Inspect all areas covered under the Project eNOI and included in the SWPPP.

When included in the SWPPP, inspect the following:

	Disturbed areas that have not been finally stabilized

	Areas used for storage of erodible materials that are exposed to precipitation

	BMPs

	Perimeter sediment control and discharge locations

	Staging and Equipment storage areas

Petroleum storage, handling and fueling sites

	Hazardous material storage sites

	Locations where vehicles or construction equipment enter or exit Project

	Material sources and disposal sites

	Discharge locations

Areas referenced in the Project SWPPP that are Contractor furnished, or commercially furnished, and the Department is not an operator, do not require Joint Inspection in accordance with this contract.  These areas should have their own SWPPP and eNOI. The Contractor or commercial operator is solely responsible for inspecting and assuring compliance with all NPDES requirements, and any other federal, state, or local requirements and the Project SWPPP shall include a statement to that effect.

8.	Inspection Reports.

Use the Department’s SWPPP Construction Inspection Report, Form 25D-100 to record SWPPP inspections.

Record applicable data including the following:

- inspection date, general information, type of inspection

- names, titles and qualifications of personnel inspecting

- weather information for the period since the last inspection, including storm events and any discharges that occurred during this period

- current weather information and a description of any discharges currently occurring

- location of discharges of sediment or other pollutants from the site

- locations of BMPs where maintenance is necessary

- locations of BMPs that failed to operate as designed or proved inadequate for a particular location

- locations where additional BMPs are needed that did not exist at the time of inspection

- corrective action required including any changes to the SWPPP necessary and implementation dates

- overall site issues

- whether construction site is in compliance with SWPPP and the CGP

- signatures and certifications by the SWPPP Manager and Engineer

The SWPPP Manager must sign and certify the inspection report on the day of the inspection, and must provide the report to the Engineer within 24 hours.  The Engineer will sign and certify the inspection report within three working days and will return the original to the Contractor.

9.	Amending the SWPPP.

The SWPPP Manager shall amend the SWPPP:

- whenever there is a change in design, construction operation, or maintenance at the construction site that has or could have significant effect on the discharge of pollutants that has not been previously addressed in the SWPPP

- if a Joint Inspection identifies the SWPPP or any portion of the SWPPP is ineffective in preventing the discharge of pollutants from the Project, that exceed applicable water quality standards

- if the Project Engineer determines the SWPPP or any portion of the SWPPP is ineffective in preventing the discharge of pollutants from the Project, that exceed applicable water quality standards

- whenever an inspection identifies a problem that requires additional or modified BMPs

Amend the SWPPP as soon as practicable after any change or modification, but in no case, later than seven (7) calendar days following an inspection.

Include the following information when documenting modifications to the SWPPP:

- date the action was completed

- initials of person documenting the action

- description of the action

Update the SWPPP drawings including date, location, action taken, and initials of the person recording the action for:

- installation of BMP

- modification of BMP

- removal of BMP

Give draft SWPPP Amendments to the Engineer for review and approval.  Use the Department’s Form 25D-114, SWPPP Amendment Log, to track all amendments to the SWPPP.  Keep the form current and submit a copy to the Engineer, including copies of any documents amending the SWPPP, prior to performing each scheduled SWPPP inspection.  Include the current SWPPP Amendment Log as an appendix to the SWPPP.

10.	Corrective Action Log.

Use the Department’s SWPPP Corrective Action Log, Form 25D-112, to record corrective actions to the SWPPP and to BMPs.  Preventative and routine maintenance performed to preserve effective function of BMPs or the SWPPP do not require documentation.  Action required to restore effective function of  BMPs or the SWPPP is corrective action and must be documented on Form 25D-112.

After each inspection report has been signed and certified by the SWPPP Manager, update the corrective action log to include all corrective actions noted on the inspection report.  After the corrective action has been accomplished, note action taken, the date, and the initials of the person documenting the action on the log.  Keep the corrective action log current and submit a copy to the Engineer prior to performing each scheduled SWPPP inspection.  Keep the corrective action log as an appendix to the SWPPP.

11.	SWPPP Grading and Stabilization Log.

Use the Department’s SWPPP Grading and Stabilization Activities Log, Form 25D-110, to record land disturbance and stabilization activities.  Keep the grading and stabilization activities log current and submit a copy to the Engineer prior to performing each scheduled SWPPP inspection.  The Engineer may waive requirements to update and submit the log during Seasonal Suspension of the Work.  Resume recording land disturbance and stabilization activities, and submission to the Engineer when Construction Activity resumes.  Keep the grading and stabilization activities log as an appendix to the SWPPP.

12.	Daily Weather Records.

Use the Department’s SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and submit one copy to the Engineer at least once every thirty (30) calendar days.  Include the daily record of rainfall form as an appendix to the SWPPP.

641-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Items 641(2) and (5) will be measured as specified in the Contract or directive authorizing the work.

641-5.01 BASIS OF PAYMENT.  The Bid Schedule will include items 641(1), (2), (5), and (6).

Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC preparation, updating the SWPPP, inspections, monitoring, reporting and record keeping.

Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract or directive authorizing the work to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control measures required to complete the project using the approved SWPPP and HMCP.

Item 641(5) Erosion and Pollution Control Price Adjustment. The total value of this contract will be adjusted as specified below. In addition, a price adjustment equivalent to any penalties levied against the Department by the EPA or any other local, state and/or federal agencies for pollutant violations, including violations of the CWA and the CGP. An amount equal to the maximum possible penalties and fines for the violation will be withheld temporarily until the actual cost of the penalties and fines is known. The Contractor is also responsible for the payment of penalties and fines levied against the Contractor.

Item 641(6) SWPPP Manager. At the contract price for a SWPPP Manager to update the SWPPP, perform inspections, monitoring, reporting and record keeping.

Temporary erosion, sediment and pollution control measures that are required at material sources, disposal sites, haul routes, fuel and material storage areas, and at equipment or material staging areas, will not be paid for separately but are subsidiary to other items of work. Work required by the HMCP and SPCC including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary.

Work that is paid for directly or indirectly under other pay items will not be measured and paid for under this Section 641. This work includes but is not limited to dewatering, shoring, bailing, permanent seeding, installation and removal of temporary work pads, temporary accesses, temporary drainage pipes and structures, diversion channels, settling impoundment, filtration, etc.

Temporary erosion, sediment and pollution control measures that are required due to negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Permanent erosion, sediment and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

If, after the Engineer gives written notice, the Contractor fails to pursue work required by the SWPPP, respond to inspection recommendations or deficiencies in the SWPPP, or implement erosion and sedimentation controls identified by the Engineer, or fails to perform any of the contract obligations, the Contractor will be assessed a permanent price adjustment of $500 per day for each day of non-action, under Item 641(5) Erosion and Pollution Control Price Adjustment. In addition, the Engineer may employ others to correct the condition and deduct the cost from the Contract amount.

The Engineer may also suspend earthwork operations and/or withhold monies due the Contractor for failure to:

- perform SWPPP Administration

- perform timely inspections

- update the SWPPP

- transmit SWPPP, SWPPP Inspection Reports, and associated Section 641 submittals to the Engineer

- maintain effective BMPs that minimize erosion, control sediment, or prevent discharge of pollutants that exceed applicable water quality standards

- perform duties in accordance with the requirements of this Section 641

- meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control

The Contractor shall be due no additional monies or Contract time extension as result of delays resulting from suspension of earthwork for failure to perform required erosion, sedimentation, or pollution duties as outlined in this Section 641.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 641(1) Erosion and Pollution Control Administration | Lump Sum |
| 641(2) Temporary Erosion and Pollution Control | Contingent Sum |
| 641(5) Erosion and Pollution Control Price Adjustment | Contingent Sum |
| 641(6) SWPPP Manager | Lump Sum |

# SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

642-3.04 OFFICE ENGINEERING.  Delete third sentence and replace with:  Perform the work by, or under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor or a Professional Engineer.  E53(5/1/07)

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION.  Add the following as a third paragraph:

Illuminate construction activities listed in Table 643-3 during hours of night work on roads open to the public within project limits.

643-1.02 DEFINITIONS.  Add the following paragraphs after paragraph titled “Construction Phasing Plan”:

Balloon Light:  Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The top half of the balloon enclosure shall be constructed of an opaque material.

Night Work:  Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in the table below:

| Latitude (degrees) | No Lighting Required |  | Nearby Cities |
| --- | --- | --- | --- |
|  | Start | End |  |
| <61 | Lighting Required All Year |  | Everything S of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Delta Junction, Nome, Tok |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle City |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

ES14(03/15/06)

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following:  A waiver may be requested of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project in writing.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic within the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.  (05/05/08)R222

643-1.04 WORKSITE SUPERVISOR.  Add the following to Item 2, Duties:

i.	Supervise lighting of Night Work.

ES14(03/15/06)

Standard Modifications

Add Item 3. Authority:

3.	Authority.  The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-2.01 MATERIALS.  In item 10. Temporary Crash Cushions, delete the second sentence:

“Do not use permanent crash cushions as temporary crash cushions.”

E62 (07/28/08)

Special Provisions

643-2.01 MATERIALS. Replace No. 12 with the following:

12.	Portable Changeable Message Board Signs.  Use new truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following:

a.	Message sign panel large enough to display 3 lines of 18-inch high characters.

b.	Eight character display per message line.

c.	Fully programmable message module.

d.	Remote Control Cellular, Wireless RF, Landline.

e.	A waterproof, lockable cover for the controller keyboard.

f.	Capacity for electric/hydraulic sign raising or lowering.

g.	Radar over speed detection.

h.	Variable flash and sequence rates.

i.	LED display, using ITE Amber/Yellow.

j.	The capacity for a minimum of 150 pre-programmed messages.

k.	Operate with a battery pack a minimum of 55 hours under full load.

l.	Power chords shall comply with the National Electrical Code Article 600.10 Portable and Mobile Signs, paragraph 600.10(c) (2) ground fault circuit interrupter.  The chord must have an integral GFCI Protection located either in the attachment plug or within 12 inches of the plug.

Standard Modifications

Under Item 16, Flagger Paddles, delete last sentence and replace with:  Use reflective sheeting that meets AASHTO M 268 Type VIII or IX.  Use background colors of fluorescent orange on one side and red on the other side. E56 (5/01/07)

Special Provisions

Add the following:

12.	Power cords shall comply with the National Electrical Code Article 600.10 Portable and Mobile Signs, paragraph 600.10(c) (2) ground fault circuit interrupter.  The cord must have an integral GFCI Protection located either in the attachment plug or within 12 inches of the plug

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.

Standard Modifications

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:

Immediately notify the Engineer of a traffic related accident that occurs within the project limits as soon as becoming aware of the accident.  E56(5/01/07)

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Maintain business accesses during flagging operations.

Standard Modifications

643-3.04 TRAFFIC CONTROL DEVICES.

In the sixth paragraph and also in Item 4.b, delete: “ATTSA” and replace with “ATSSA.”  E56(5/01/07)

Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES.  Delete the first sentence of the eighth paragraph and substitute the following:  Items paid under this Section remain the Contractor’s property unless stated otherwise.

Add the following to Item 1, Embankments:  Close trenches and excavations at the end of each continuous work shift.

Add the following to Item 3, Fixed Objects:  Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete Item 4.b and replace with the following:  Flagger Certification by ATSSA

Delete Item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change Items 7 and 8 to 8 and 9, respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT &PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER.  Replace the first sentence with the following:  When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice.  A written notice will follow the oral notice according to subsection 105-1.01 Authority of the Engineer.

Add the following after the second sentence:  In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following:  Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100% of the applicable rate shown in Table 643-1, for the time the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1
Adjustment Rates

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-5,000 | $30 |
| 5,001+ | $40 |

(05/25/07)R222

643-3.07 MAINTENANCE OF TRAFFIC CONTROL DURING SUSPENSION OF WORK.  Add the following after the second paragraph:  Temporary vehicle detectors shall be provided during winter shutdown if existing vehicle detectors are removed and not replaced.  Temporary vehicle detection will need to be approved by the Engineer.

During winter shutdown, span wire signal maintenance will be the responsibility of the Contractor.

643-3.08 CONSTRUCTION SEQUENCING.  Delete the last sentence and substitute the following:  Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic between 0600 hours and 2000 hours daily.

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

Road Closures

The contractor will be allowed six road closures of the Tudor Road and Lake Otis Parkway intersection.  Closures shall begin at 2000 hours on Friday and end at 0530 hours on Monday.

643-3.09 INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following:  Apply final pavement markings according to subsection 670-3.01, Construction Requirements of these Special Provisions.  (05/05/08)R222

- Add the following new subsection:

643-3.10 LIGHTING OF NIGHT WORK.

Illuminate the night work areas specified in Table 643-2 to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

TABLE 643-3
Night Work Illumination Level and Area of Coverage

| Type of Work/Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least 2 machine mounted balloon lights with a cumulative wattage of at least 4,000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): 1) with roads with ADTs over 10,000 or 2) that are controlled by portable signals or flaggers. | Two balloon lights of at least 2,000 watts each, located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |

Use balloon lighting as the main light sources.  Do not use floodlights without prior approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway.  Locate, aim, louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to meet required lighting equipment or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operations that require illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they do not interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment mounted light towers are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-2.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of at least 20 emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Provide NCHRP 350-compliant breakaway bases for post mounted electroliers located within the clear zone.

ES14(03/15/06)

Standard Modifications

Add the following new subsection:

643-3.11 HIGH VISIBILITY GARMENTS.  Ensure workers within project limits wear outer garments that are highly visible and comply with the following requirements:

- Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

- Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004; except previously purchased garments labeled in conformance with ANSI/ISEA 107-1999 may be used until 1/1/08.

- Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

- Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise).  Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottom at all times.

- Outer Raingear.  Wear raingear tops and bottoms conforming to the requirements of this subsection 643-3.11.

- Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

- Condition.  Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.  Maintain retroreflective material to Level 2 standards.

E56(5/1/07)

Special Provisions

643-4.01 METHOD OF MEASUREMENT.  Replace the second sentence of Item 2 with the following:  Special Construction Signs are measured by the total area of legend bearing sign panel, as determined under subsection 615-4.01 and compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule.

Add the following:  No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Item 643(1) or 643(2) Traffic Maintenance.

643-5.01 BASIS OF PAYMENT.  Add the following:  The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

Traffic Control Rate Schedule

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $24.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $.75 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |

The Engineer will pay for Item 643(15) Flagging on a contingent sum basis at the rate of $41/hour.  The Engineer does not require a change order/directive for the flagging pay item.  Flagging associated with Change Order work will be paid at the prices according to subsection 109-1.05 Compensation for Extra Work.  (05/05/08)R222

Add the following:

- Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items.

ES14(03/15/06)

Standard Modifications

Add the following:  Payment for high visibility garments for workers is subsidiary to other items.  (5/01/07)E56

Special Provisions

Delete Item 643(15) and substitute the following:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15) Flagging | Contingent Sum |

(05/05/08)R222

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:  Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1,000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Four telephone service lines available at the office location.  One of the lines provided is to be available for a facsimile machine/dial-up Internet connection.  Provide Internet connection with send and receive data capability supporting 56 kilobytes per second or higher data transfer rate.

8.	If a part of the Contractor’s building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture from Anchorage.

644-3.01 METHOD OF MEASUREMENT.  Delete the third paragraph and replace with the following:

Vehicle.  By each provided.

644-4.01 BASIS OF PAYMENT.  Add the following items:

Lump Sum Items.  Payment for lump sum items will be made as follows:

- A percentage of the lump sum amount, to be determined by the Engineer, will be paid as full compensation for furnishing the facility at the site.

- The balance of the lump sum amount will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, providing all utilities, and for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Add the following pay item:

| Pay Item No. | Pay Unit |
| --- | --- |
| 644(8) Vehicle | Each |

Add the following Section:

SECTION 645

## TRAINING PROGRAM

### Special Provisions

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "yellow pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish before contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and one or more of the following occurs: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the Contractor’s judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  Submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts.  In the event a portion of the work is subcontracted, the Engineer shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor according to subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section before the Contractor’s submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the Contractor’s discretion, graduates early and is employed as a journey worker according to the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of other training program funds the Contractor may receive, unless such other funding sources specifically prohibits the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Noncompliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of training programs approved for the project.  No payment or partial payment will be made if the Contractor fails to do the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why the Contractor was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

(10/29/91)S16

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 645(1) Training Program, 2 Trainees/Apprentices | Hour |

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this Subsection with the following:  Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.

Delete Item 2, 60-Day Preliminary Schedule.

Delete the first sentence of Item 3, Schedule Updates, and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.  (12/13/02)R261M98

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

Special Provisions

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor’s operations shall at all times be in accordance with the Engineer’s instructions.  These instructions by the Engineer shall be to the Contractor’s supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor’s responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer’s specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL.  Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor’s representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS.  The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day’s activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor’s representative at the end of each shift, and a copy will be provided to the Contractor’s representative.

647-4.01 METHOD OF MEASUREMENT.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.  Hours paid shall be supported by Certified Payroll.

647-5.01 BASIS OF PAYMENT.  Payment for Item 647(1A1) Backhoe, 4WD, 27 ft^3 Bucket, 75-HP, 14.5 ft Depth will be paid on a contingent sum basis at the rate of $125/hour on a per hour basis at the rate shown on the bid schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 647(1A1) Backhoe, 4WD, 27 FT^3 Bucket, 75-HP, 14.5 FT Depth | Contingent Sum |

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.01 DESCRIPTION.  Add the following:

Install pedestrian scale lighting at each bus stop as shown on the plans.  Contractor to supply and install pile, conduit, and electrical equipment for pedestrian scale lighting pole. Contractor to supply and install transit shelter electrical assembly as shown on the plans.  Contact Randy Bergt (343-8285) with People Mover two weeks prior to installation of pedestrian scale lighting pole and transit shelter electrical assembly.

Standard Modifications

660-2.01 MATERIALS.  Under Item 1.a, change title by removing:  “Materials on the Approved Products List:” and replace with:  Materials on the Qualified Products List:

660-2.01 MATERIALS.  Under Item 1.b, change title by removing:  “Materials Not on the Approved Products List:” and replace with:  Materials Not on the Qualified Products List:  E36(01/27/07)

Special Provisions

660-2.01 MATERIALS.

Replace the fourth item in the list with the following:

Paint		Subsection 708-2.01 and 708-2.05

Replace numbers 1 and 2 with the following:

1.	Equipment List(s) and Drawings.  Delete Item a in its entirety and the last sentence in Item d and substitute the following:

- Materials on the Approved Products List:  The Approved Products List does not apply to the 660 items.  Provide catalog cuts of materials to the Engineer for review and approval.

- Materials Not Requiring Certification:  Only submit these materials for review and approval if they are included on the Materials Certification List (MCL).

2.	As-Built Plans.  Add the following:

The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.  In addition, the Engineer will submit two complete sets of all electrical related plan sheets; one copy each to MOA Signal Electronics and MOA Street Light Maintenance.

CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL.  Delete Items 3 through 8 in their entirety and substitute the following:

- Excavating and Backfilling.  Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors.  Provide traffic control to complete this work according to the requirements of Section 643.  Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified side by side, to provide clearances of at least 2-1/2 inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches, and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit.  Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

Dispose of, according to subsection 203-3.01, excavated materials that remains after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in subsection 703-2.07.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations.  Backfill excavations with materials that meet the following requirements

a.	Backfill foundations with material that meets the requirements of Selected Material, Type A that passes through a 3 inch sieve.

b.	Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift.

c.	In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

d.	Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material gleaned free of rocks exceeding a 1 inch maximum dimension.  Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to subsection 203-3.04.  In other locations, compaction may be as approved by the Engineer.

- Welding.  Complete welding according to subsection 504-3.01.8.  Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval.  The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes, which were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface.  For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole.  Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole.  Grind the welds smooth and flush with the adjoining pole and disk surfaces.  Repair the damaged finish according to subsection 660-3.01.8.

- Removing and Replacing Improvements.  The Contractor shall complete the following work at the Contractor’s expense.

- Remove improvements that block completion of the work detailed in the Plans as specified herein.

- Reconstruct with new materials the nonreusable improvements the Contractor removed to complete the work, unless other items in the contract cover the improvements.

- Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

- Reconstruct with new materials improvements that the Contractor damaged or removed, that do not conflict with the work and are not scheduled for removal.

Nonreusable improvements consist of cast in place items, including:  asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings.  Reusable improvements include the items that were made before installation.  Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition.  In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil.  Match the top of the topsoil with the bottom of the vegetative mat.  Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621.  Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

- Salvaging and Reusing Electrical Equipment.  When the Plans include existing electrical equipment scheduled for removal or relocation, remove and store the equipment listed in the following paragraph without damaging it.  All traffic signal system items shall be delivered to the MOA Traffic Signal Warehouse at 5923 Rowan Street.  Signal poles and mast arms shall be delivered to the MOA Traffic Signal Pole Yard at 3rd Avenue and Orca Street.  Contractor shall allow MOA maintenance personnel to select the equipment and pole items they would like to salvage.  Contractor shall dispose of all remaining equipment and pole items.  Contact Foreman at 343-8355 one week before tentative delivery date.

Salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, load centers, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for relocation.  The Contractor shall replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.

Controller assemblies and load centers include the cabinet and equipment contained in the cabinet before Contract award.

Remove from the highway right-of-way materials associated with the equipment removed or relocated and not scheduled for reuse, including conduits, junction boxes, conductors, and foundations.  Raze the tops of foundations abandoned in place according to subsection 660-3.02.  Fill the holes left by removing junction boxes and foundations with selected material type A and compact as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned in place with a credit taken by the Department.  Remove the ends of abandoned conduits from the junction boxes that will remain in service.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer.  Note the location and condition of the materials.  When material specified for reuse is found in an unserviceable condition, the Engineer will determine whether to repair it or replace it with new material, which will be paid for as extra work under subsection 109-1.05.  Retain a copy of the inventory and give the original documents to the Engineer.

When the Plans specify reinstalling existing equipment at new locations and installing State furnished equipment, complete the following work at the Contractor’s expense.

- For poles, install new foundations, furnishing the new nuts, bolts, washers, and conduits needed to complete the installations.

- For lighting poles, install new illumination tap wires and fused disconnect kits.

- For luminaires, clean the luminaires inside and out and install new lamps of the same wattage.

- For signal heads, furnish and install the mounting brackets needed to complete the relocation, and clean the signal heads inside and out.

- For poles and undisturbed poles from which the Plans specify removing equipment, repair the holes that were made to mount equipment according to subsection 660-3.01.4.  Welding and repair the finishes according to subsection 660-3.01.8.

When ordered, the Department will pay for repairing damaged finishes on existing equipment according to subsection 660-3.01.8 as extra work.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to subsection 660-2.01.1.

- Field Tests.  Electrical circuits must pass the following tests before the Engineer will accept the work for payment.  Perform these tests in the presence of the Engineer, and document the results of each test on a per circuit basis.  Retain a copy of test results and give the original documents to the Engineer.  Furnish equipment needed to perform these tests.

Replace or repair at the Contractor’s expense, and in an approved manner, faulty materials and work revealed by these tests.  After making repairs, repeat tests on the repaired circuit and continue this process until circuits have passed required tests.  The Department reserves the right to have the Contractor retest circuits, and to use the retest results to accept or reject individual circuits.

- Grounds.  Before completing the circuitry and functional tests, physically examine conduits ends, junction box lids, load centers, and the foundations for signal posts and poles, lighting poles, and controller cabinets to ensure the grounding system required by subsections 660-3.06 and 661-3.01 has been installed and splices and connections are mechanically firm.

- Continuity.  Test each loop detector circuit for continuity at the roadside junction box before splicing the loop detector to the lead-in cable.  Each loop detector must have a resistance less than 0.5 ohms.

After splicing the loop detectors to the lead-in cables, test each pair at the controller or detector cabinet.  Each pair must have a value less than 5 ohms for single pair lead-in cables and 10 ohms for multipair lead-in cables.  The continuity test ohm reading at the cabinet must be greater than the ohm reading measured for the loop detector at the junction box.

- Insulation Resistance (megohm) Test.  Complete this test to verify the integrity of each conductor’s insulation after pulling the conductors and cables into position and before terminating the conductors.  At 500 volts DC, each conductor’s insulation shall measure a minimum resistance of 100 megohms or the minimum specified by the manufacturer.  With single conductors, complete the test between each conductor and ground.  In each multiconductor cable, complete the test between conductors and between each conductor and ground.

After splicing the loops to the shielded pairs in the lead-in cables, measure each pair in the lead-in cables at the controller or detector cabinet between one conductor and the cabinet ground rod.

- Inductance Test.  Measure each detector loop and lead-in cable system at the controller or detector cabinet.  The inductance must be in the range of 50 to 500 microhenries.

- Circuit.  Energize every signal indication circuit with lamps installed before installing the load switches.

- Functional.  Perform the following tests on each signal and lighting system after the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity, and circuitry.

  - For each new traffic signal system, complete at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory operation.  The Engineer may decide to omit the flashing portion of the test for modified signal systems and for new signals that replaced existing signals that remained in operation during the construction phase.

If the Engineer omits flashing operation and the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for five days with continuous, satisfactory operation.

Begin the signal functional tests between 9 a.m. and 2 p.m. on any day, except a Friday, Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Before each system turn on, aim signal faces according to subsection 660-3.08 and ensure equipment specified in the Plans is installed and operable, including:  pedestrian signals and push buttons; signal backplates and visors; vehicle detectors; highway lighting; and regulatory, warning, and guide signs.

  - Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5 day operational test using the photocell.

  - Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

  - Perform a continuous 5 day burning test on each pedestrian lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system functions normally when power is returned.

8.	Repairing Damaged Finishes.  Examine new, reused, and State furnished equipment for damage to its finish before putting the equipment into service.  Repair the damaged finishes found according to the following:

a.	Galvanized.  Repair damaged areas more than 12 inches away from welds and slip fit areas, by applying a minimum 7.8 mils of zinc based alloy applied according to ASTM A780.

If the damaged areas are within 12 inches of welds and slip fit areas, make the repair by applying a minimum 7.8 mils of zinc rich paint applied according to ASTM A780.

b.	Painted.  Repair damage to painted finishes according to the following:

(1)	Wash the equipment with a stiff bristle brush using a solution containing two tablespoons of heavy-duty detergent powder per gallon of water.  After rinsing, wire brush surfaces to remove poorly bonded paint, rust, scale, corrosion, grease, or dirt.  Remove dust or residue remaining after wire brushing before priming.

(2)	Factory or shop cleaning methods may be used for metals if equal to the methods specified herein.

(3)	Immediately after cleaning, coat bare metal with pretreatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

(4)	Give signal equipment, excluding standards, a spot finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

(5)	Give nongalvanized standards 2 spot finish coats on newly primed areas.

Paint coats may be applied either by hand brushing or by approved spraying machines.  Perform the work in a neat and workmanlike manner.  The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint spraying machine prove unacceptable.

Add the following new Item 9:

9.	Regulations and Code.  Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the authority having jurisdiction.

660-3.02 FOUNDATIONS.  Under Item 1, Cast-in-Place Foundations, add the following to the first paragraph:  Locate the tops of traffic signal post and pole foundations flush with the adjacent finished:  walkway, shoulder, or surrounding ground.

- Cast-in-Place Foundations.  In subparagraph f, revise the second sentence to read:  Before placing the form or reinforcing steel cage, remove loose material from the bottom of the hole to ensure the foundation rests on firm, undisturbed ground.

In the second sentence of sub-Item I, delete “prior to grouting.” and substitute “before attaching the skirt.”

In the first sentence of sub-Item j, delete “concrete pile caps” and substitute “foundations.”

Delete Item k and add the following new Items k and l:

k.	Install the bottoms of the bottom leveling nuts in a level plane within 1 inch of the top of foundations.  Adjust all nuts until their tops form a level plane.  Install one washer on top of all leveling nuts and, after setting the pole on these washers, install one washer under all top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Generously lubricate the bearing surface and internal threads of top nuts with beeswax.  Tighten all top nuts to a “snug” condition.  Use a click-type torque wrench to apply 600 foot-pounds of torque to the “snug” top nuts.

After torquing the top nuts, use a hydraulic wrench to rotate all top nuts an additional one sixth (60) turn, while preventing the leveling nuts from turning.

l.	Attach a 4 AWG, bare, solid copper wire as a grounding electrode conductor to the No. 4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector or cadweld to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled 4 AWG, bare, solid copper wire as the grounding electrode.  Route the conductor to protrude near the top, center of the foundations.  Slide a minimum 6-inch long, nonmetallic, protective sleeve over the conductor.  Allow 1 inch of the sleeve and 24 inches of conductor to protrude from the foundations.

2.	Pile Foundations.  Add the following new Item g:

g.	Use no more than one splice per foundation.  Locate the splice at least 10 feet from the top of pile.

Replace subsection 660-3.03 with the following:

660-3.03 CONDUIT.  Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified.  Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits.  Install conduits of the sizes specified along the routes detailed on the Plans.  When routing is not shown, route conduits as directed by the Engineer.

- Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4-inch-thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

- Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches.  Excavate, bed conduits, and backfill trenches according to subsection 660-3.01.3, Excavating and Backfilling.

- Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods.  Jacking conduits into position is allowed.  However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

- Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs.  To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box.

- Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box.  Extend the ends a minimum of 2 inches beyond the inside wall of the box.

- Drill a ⅜-inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs.  Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors.  Cover the holes with a wrap of approved filter cloth secured with 2 self-clinching nylon cable ties.

- Keep conduits clean.  Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends.

- At the low points of conduit runs, install sumps containing a minimum 2 cubic-feet of coarse concrete aggregate material that conforms to subsection 703-2.02.  Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

- Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary.  Install additional drains and aggregate sumps at the low spots, if any.

- Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 2-1/2 inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

- Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit.  Cut the same number of threads as found on the factory threaded ends.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.  Do not use slip joints or pieces of running thread pipe.

- Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

- When standard couplings cannot be used to join conduit components, use approved threaded unions.

- Bury a continuous strip of 4 mils thick, 6-inch-wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a red background.

- If encountering obstructions during jacking or drilling operations, obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 1¼ to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

- When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between Type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

- In foundations, install 90-degree elbows and conduits of the size and quantity shown on the Plans.  Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

- Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct-sealing compound.

- Install expansion fittings in conduits that cross expansion joints.

- Install a polypropylene pull rope with a minimum 200-pound tensile strength in future use or spare conduits, and reinstall the plugs.  Double back at least two feet of pull rope into both ends of each conduit.

- The Contractor may install conduits larger than the sizes specified.  If used, it must be for the entire length of the run.  Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

- Clean existing conduits that will remain in service using a heavy-duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch.  Clean the conduits before pulling in new cables and after removing cables specified to be removed or replaced as follows:

  - When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

  - Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

- When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit.  When extending existing conduits, add no more than 90 degrees of horizontal bend to the extension.

- When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

- When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

- Remove the ends of abandoned conduits from junction boxes that will remain in service.

- When Plans call for connecting polyethylene conduit to RMC use an electrofusion coupler rated for direct bury application.  The coupler must be rated for same wall thickness as the adjoining conduits.  Thread the ends of the RMC with the same number of threads as found on the factory threaded ends of RMC.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

Replace subsection 660-3.04 with the following:

660-3.04 JUNCTION BOXES.  Install precast reinforced concrete junction boxes of the types specified.  For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them.  For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them.

Junction Box Location.  When shown, install junction boxes at the station and offset locations specified.  When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement.  If the 8 feet offset falls:

- In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility.  When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

- In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

- Outside the right of way, install the boxes just inside the right of way line.

- In a raised median, install junction boxes near the center of the median.

- In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

- Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

- On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing type 1A junction boxes in driveways and in locations subject to use by heavy trucks.  When shown near the ends of medians, install junction boxes at least 10 feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.

Limitations.  Limit the distance between adjacent junction boxes to the following dimensions:

- 400 feet for conduits that contain signal interconnect cable only.

- 300 feet for conduits that exclusively contain two loop lead-in cables.

- 300 feet for conduits that contain a single cable other than signal interconnect.

- 190 feet for conduits that contains more than one cable.

When establishing junction box spacing a bare ground conductor is not considered a cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work; otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria.  In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade.  In seeded areas, install the tops of junction boxes to 2 inches below the seeded surface.

Bond junction box lids to an equipment grounding conductor according to subsection 660-3.06.  Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box.  Drains shall consist of coarse aggregate for concrete that conforms to subsection 703-2.02.  Minimum drain dimensions include an 18-inch depth and a length and width equal to those of the junction box it drains.  Compact the aggregate material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker that consists of an antenna encapsulated in a 4-inch-diameter red polyethylene ball.  Furnish markers that conform to the American Public Works Association standards for locating power from one of the following manufacturers or approved equal:

3M						Textron, Inc.

3M Center					1390 Aspen Way

St. Paul, MN 55144				Vista, CA 92081

(888) 364-3577				(800) 642-2155

The 3M electronic marker shall be a Dynatel EMS ball marker model number 1402-xr.  The Textron electronic marker shall be an Omni Marker model number 160.  Markers shall respond to locator devices up to 5 feet away, work at all temperatures, and contain no internal power source.  Contractor shall supply two locating devices.  Deliver one to MOA Signal Electronics and the other to MOA Street Light Maintenance.

660-3.05 WIRING.  Delete the second paragraph in its entirety and substitute the following:

Conditions.  Do not pull conductors into conduits until the following conditions are met:

  - The prescribed clearances around conduit ends are provided,

  - Crushed rock sumps are installed under junction boxes,

  - Conduit ends protrude above the bottom of junction boxes within the prescribed range,

  - New conduits are free of material that became lodged in them during the completion of the work,

  - Reused conduits are cleaned according to subsection 660-3.03,

  - Junction boxes are set to grade, and

  - Grounding bushings are installed on the ends of metallic conduits.

Delete Item 3 in its entirety and substitute the following:

3.	Pull, as a unit, the conductors specified to be installed into clean conduits, leaving existing conductors that will remain in service in place.

Add the following line to Table 660-1 under subitem a of Item 9.

| Loop Detector Number | Colored Pair |
| --- | --- |
| Usually a spare pair | Orange and Black |

Delete Items 11 and 12 in their entirety and substitute the following:

11.	Encapsulate illumination cable splices in rigid 2 piece plastic molds filled with an insulating and sealing epoxy resin.  Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin.  Furnish molds rated for 600 volts AC operation and feature fill and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, 1 splice may be used in the following cases:

    - An in-line splice may be used when a planned cable run exceeds the length available from the manufacturer on a single spool of cable.

    - In a run of 1,000 liner feet or more.

When a cable is spliced it shall occur within an appropriately sized j-box or in the base of an electrolier designed for said splice.

12.	Encapsulate loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with reenterable polyurethane electrical insulating and sealing compound.  Furnish splice kits rated for 1000 volts AC operation and direct burial.

Provide reuseable four piece molds that are held together with stainless steel hose clamps.  Two pieces form a cylinder and two flexible end caps seal the ends and allow the conductor entry.  Use molds with dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Insert a loose woven polyester web that allows a full ¼ inch of insulating compound to flow between the splice and the inside of the mold.  Fill the PVC molds with reenterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is noncorrosive to copper, and does not support fungi or mold growth.

Add the following items:

18.	Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

19.	Whenever conductors cannot be terminated as specified in the Plans in circuit breakers due to size, splice a piece of No. 8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet.  Limit the length of the No. 8 AWG conductor to 5 feet.

20.	Cap spare lighting conductors in the pole bases and load centers by cutting the wire flush with the end of the insulation and bending the conductor back against itself and securing with three layers of electrical tape to prevent a possibility of making contact with ground or current carrying conductors.

Replace subsection 660-3.06 with the following:

660-3.06 BONDING AND GROUNDING.  Bond and ground branch circuits according to the NEC and the following requirements.  Make noncurrent carrying but electrically conductive components, including:  metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor.  Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install grounding bushings with insulated throats on the ends of metallic conduits.

Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size 8 AWG grounding conductors, except in those conduits that contain circuit conductors larger than 8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installation or removal of conductors from existing conduits, retrofit with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross sectional area equal to an 8 AWG conductor and eyelets spaced at 6-inch intervals.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.  Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the 4 AWG grounding electrode conductor using irreversible compression connectors at Portland cement concrete foundations.  For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 5-foot-long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the hand hole of each pole.

Bond slip base type standards and pedestals by using two conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the hand hole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a 3/4-inch by 10-foot copper-clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

When routing a new conduit into an existing junction box or replacing an existing junction box, improve groundings in new and existing conduits to current specifications.

Replace subsection 660-3.08 with the following:

660-3.08 SIGNAL AND LIGHTING INSTALLATION REQUIREMENTS.  Install signal and lighting equipment according to the details shown on the Plans and the following:

Apply antiseizing compound to the following fasteners:  frangible couplings, mechanical grounding connectors, bolts that secure hand hole covers and signal mounting hardware to poles and mast arms.  Remove the fasteners from luminaire mounting brackets, fused disconnect kits, grounding bushings, and signal faces which secure the visors, and apply antiseizing compound to these fasteners before completing the installation.

Before passing conductors through the holes made in posts, poles, and mast arms for wireways, remove the burrs and sharp edges from the inside and outside of these holes.

Until each traffic signal goes into operation, keep the vehicular and pedestrian signal faces covered with beige colored canvas shirts sized to fit the signal faces shown in the Plans.  Each signal shirt shall feature elasticized openings that fit over the visors and at least two straps to secure it to the signal.  Provide shirts with a legend that reads “out of service” and a center section that allows an operator to see the indications during system tests.

When not shown in the Plans, determine the shaft lengths of lighting and signal poles and signal mast arm connector plate locations to provide the plan mounting heights of luminaires and traffic signal heads.

Furnish work to install foundations for relocated poles, including:  conduit, excavation, reinforcing steel, Class A concrete, anchor bolts, nuts, and washers.

1.	Electrolier Installation.  Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm.  After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

- Signal Pole Installation.  Install signal poles with a slight rake by plumbing the side of the pole opposite the mast arm just above the base plate.  Tighten the nuts on the anchor bolts as described in subsection 660-3.02k.

Cover the gap between the foundation and base plate by installing a metal skirt around the base plate, secured with stainless steel sheet metal screws.

3.	Vehicular Signal Head Installation.  With two-piece mast arms, do not install signal heads within 12 inches on either side of the slip type field splice.

Attach each side-mounted terminal compartment with two 1/2- by 1- inch bolts, with washers, threaded into holes tapped into the side of the pole at the location shown on Standard Drawing T-30.  Install the vertical pipe members plumb.

When installing five-section vertically stacked signal heads on the sides of poles, secure the vertical pipe to the pole using a steel conduit hanger mounted 6 inches below the top horizontal pipe.

Aim through phase vehicular signal faces at a point located a distance from the face as shown in Table 660-2.  If two through signal faces are not visible from this point at a height of 42 inches above finished grade, consult the Engineer for corrective measures.

TABLE 660-2

| Through Phase Signal Face Aiming Points |  |
| --- | --- |
| 85th Percentile Speed (mph) | Minimum Visibility Distance (feet) |
| 20 | 175 |
| 25 | 215 |
| 30 | 270 |
| 35 | 325 |
| 40 | 390 |
| 45 | 460 |
| 50 | 540 |
| 55 | 625 |
| 60 | 715 |

4.	Pedestrian Signal and Push Button Installation.  Orient pedestrian signal faces at the center of the crosswalk on the opposite side of the street.  Attach each clamshell bracket with two 1/2- by 13-inch bolts threaded into holes tapped into the side of the pole.  Install a spacer, furnished by the bracket manufacturer, on each bolt.

Install the push button on the crosswalk side of the pole.  Install R10-3E (R or L) push button signs above each push button.  Furnish signs with the arrow pointing in the direction of the appropriate crosswalk.  When channel is used for mounting push button signs, tap the top and bottom sign bolts into the pole.

5.	Wood Pole Installation.  Place the poles in the ground to at least 6 feet deep.

After setting each pole in the ground, backfill the space around the pole with selected earth or sand, free of rocks 4 inches and larger, or deleterious material.  Place the material in layers approximately 4 inches thick and thoroughly compact them with mechanical tampers.

Furnish poles that provide a minimum vertical clearance of 21 feet between the pavement and low point of overhead conductor.

660-3.09 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS.  Delete this subsection in its entirety and substitute the following:  This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract.  The work includes:  locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals and lighting systems to keep them wholly operational and positioned according to the following specifications.

If the existing lighting systems are not kept fully operational as specified herein, the Engineer will reduce the payments under Item 660(22) Illumination Price Adjustment.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference.  Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing equipment damaged before the transfer of maintenance responsibility.  Therefore, before starting work on the project, inventory the condition of the existing equipment with the Engineer and document the damaged and defective equipment.  If beginning work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems.  The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems.  The State will pay for electricity used to operate the systems, if the public benefits from their operation.  Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer.  If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

Records.  When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times beginning and completing work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hour’s traffic restrictions allowed in subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than 6 feet.

Alignment.  During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches according to the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 17.5 feet to 21.5 feet of clearance between the traveled way and the bottom of each signal.  For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain nine feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	When the horizontal angle to the side mounted far right signal exceeds 20, relocate this signal to an overhead location.  Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

i.	With two or more through lanes, center one signal head over each lane.

ii.	With one through lane and protected permitted signal phasing, leave the five-section signal over the lane line and center the signal to be relocated over the through lane.

iii.	Otherwise, install the relocated signal 8 feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 7 to 9 feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in subsection 660-3.08, Signal and Lighting Structures.

When no longer required, salvage original and Department provided equipment according to the Plans and Item 6, Salvaging and Reusing Electrical Equipment, found in subsection 660-3.01, and remove other materials used in the temporary systems from the project.

Temporary Interconnect (I/C) System

A temporary interconnect system shall be provided and maintained during construction.  A minimum of two 25-pair No. 19 I/C cable shall be required as a temporary bypass.  Cable to tie existing I/C system coming from the east to existing I/C system going to the south and west.  Maximum time allowed to disrupt existing I/C systems to tie in temporary bypass I/C shall be 48 hours.  All work shall be coordinated with the MOA Signal Electronics Shop.  Both cables shall be routed through temporary interconnect cabinet mounted adjacent to the temporary controller cabinet.

660-4.01 METHOD OF MEASUREMENT.  Add the following:

Item 660(28A) Pedestrian Scale Lighting Pole.  By each, installed in place.

Item 660(28B) Transit Shelter Electrical Assembly.  By each, installed in place.

660-5.01 BASIS OF PAYMENT.  Add the following:

Bust stop transformer pedestals and junction boxes are subsidiary to Pay Item 660(28A) and 660(28B).

The amount bid for an item shall include full compensation for:

- Excavation, bedding, and backfill to install the components shown in the Plans.  Dewatering excavations is subsidiary to completion of the excavation work.

- Removing and repairing existing improvements to complete the work, unless other items in the contract cover the repairs.

- Work associated with installing loop detectors, including:  saw cutting, asphalt removal, aggregate base course, tack coating, and installing new asphalt concrete.

The Engineer will pay for the disposal of surplus and unusable excavation and for imported backfill and bedding material at respective contract unit prices, or as extra work if the contract does not include these items.

The cost of repairing damage to finishes on new equipment is subsidiary.

The cost of maintaining the existing and keeping the temporary electrical system fully operational is subsidiary to 660 items included in the Contract.

For each mile of roadway with existing lighting systems that is not kept fully operational, the Engineer will deduct $1275.00 per day from the payments due the Contractor.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 660(1A) Traffic Signal System Complete at Tudor and Lake Otis | Lump Sum |
| 660(3) Highway Lighting System Complete | Lump Sum |
| 660(7) Temporary Signal System Complete | Lump Sum |
| 660(8) Temporary Lighting System Complete | Lump sum |
| 660(28A) Pedestrian Scale Lighting Pole | Each |
| 660(28B) Transit Shelter Electrical Assembly | Each |

SECTION 661

ELECTRICAL LOAD CENTERS

Standard Modifications

661-2.01 MATERIALS.  Under Item 1, change title by removing:  “Materials on the Approved Products List:” and replace with:  Materials on the Qualified Products List:

661-2.01 MATERIALS.  Under Item 2, change title by removing:  “Materials Not on the Approved Products List:” and replace with:  Materials Not on the Qualified Products List:  E36(01/27/07)

- Add the following Section:

SECTION 662

SIGNAL INTERCONNECT

Special Provisions

662-1.01 DESCRIPTION.  This item consists of the work required to furnish and install signal interconnect in conduit between the controller assemblies shown on the Plans along the route indicated or on a route as directed by the Engineer.

662-1.02 REGULATIONS AND CODE.  Complete the work according to these Specifications and Section 660, Signals and Lighting.  The Department requires third party certification for high density polyethylene conduit.  Equal to or exceeding UL 651 B and NEMA TC-7.

662-2.01 MATERIALS.  Submit the materials for review and approval according to the requirements of Item 1, Equipment List and Drawings, of subsection 660-2.01, Materials.

Furnish a 25 pair No. 19 telephone cable conforming to REA Specification PE-39 for the interconnect cable.  Install the interconnect cable in a 2 inch polyethylene conduit.

Encapsulate completed splices in waterproof reenterable type splice kits of the same type used for loop lead-in cable splices.  REA Bulletin 344-2 entitled "Lists of Materials Acceptable for use on Telephone Systems of REA Borrowers" provides a list of acceptable splice materials.

662-2.02 POLYETHYLENE DUCT SYSTEM.  Install a polyethylene duct system in which to pull the interconnect cable.  The Department will not permit the installation of the polyethylene conduit in a plowed trench.

Furnish a Type III polyethylene duct made from extra high molecular weight, high density, polyethylene (PE) pipe, with a cell classification equal to or exceeding 335444C when tested according to ASTM D3350.

Furnish fittings used in the duct system such as elbows, etc., made from the same type polyethylene as the duct.  Fuse connections using the manufacturer’s recommended procedure and equipment.  Except elbows weeping into junction boxes shall be rigid metal conduit.  Join the rigid metal conduit to the HDPE with Electrofusion Type Coupler.

- Keep junction boxes and ends of conduit covered unless pulling conductors.

Mark underground conduits with a continuous strip of polyethylene marker taped.  Furnish marker tape with a black legend on a red background that is 4 mil thick and 6 inches wide.  Install the tape 6 inches below finished grade.

Use care during compaction operations to prevent damage to the junction boxes and conduits.  Remove and replace items damaged during the backfill and compaction operations at no additional cost to the Department.

After testing and installing the conductors, plug conduit openings with duct seal to prevent water from entering the duct system.

662-2.03 JUNCTION BOX.  Furnish precast, reinforced concrete junction boxes conforming to the sizes and details shown on the Plans.  Install junction box lids made of cast iron.

662-3.01 CONSTRUCTION REQUIREMENTS.  The signal interconnect consists of cable, conduit, junction boxes, other necessary hardware required to complete the item, cable splicing, and the termination of conductors on terminal blocks.

- Install the polyethylene conduits at least 30 inches below finished grade.

Install junction boxes at all abrupt changes in conduit alignment and on 300 foot maximum centers.  Angle points and curves with delta angles greater than 45 degrees constitute an abrupt change.  Install Type 1A junction boxes, except when splicing interconnect cables together.  Complete the interconnect cable splices in Type II or III junction boxes.  Complete the splices in accordance with Rural Electrification Administration (REA) Specification PC-2 for splicing telephone cables.  The Contractor shall determine the locations for making signal interconnect splices.  The Engineer, however, will not allow splices to be made at low points in the terrain or the bottom of sag vertical curves.  Keep splices in the interconnect cable to an absolute minimum and get the splice locations approved by the Engineer beforehand.

- Furnish the controller cabinets with terminal blocks for the interconnect cable.

662-3.02 EXCAVATING AND BACKFILLING.  Backfill the excavations according to Section 204.

The Engineer will not allow ripping or plowing for installation of conduit.  Backfill around the polyethylene conduit with a 6 inch lift of material free of rocks exceeding a 1 inch maximum dimension.

662-4.01 METHOD OF MEASUREMENT.  The Engineer will measure signal interconnect by the linear foot from the center of junction box to center of the next junction box, following the slopes of the existing ground.

662-5.01 BASIS OF PAYMENT.  The contract unit price paid per linear foot for signal interconnect constitutes full compensation for furnishing work required to complete the work specified.  Terminal blocks for the interconnect cable shall be paid under Item 660(1A) Traffic Signal System Complete at Tudor and Lake Otis.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 662(2) Signal Interconnect System Complete | Lump Sum |

- SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Pavement Markings as shown on the Plans and as directed.

Pavement Marking Type:  Extruded Methyl Methacrylate (MMA).

Surface apply parking lot lines on Tract A-1-C and Forest Drive Subdivision lot 4, project parcels 2 and 15 respectively, as shown on the plans.

670-2.01 MATERIALS.  Replace the material reference,

Extruded Methyl Methacrylate Pavement Markings			Subsection 712-2.17

Extruded Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads, and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.

1.	Paint.  Delete e. and replace with the following:

e.	Paint applies to parking lot lines on Tract A-1-C and Forest Drive Subdivision lot 4, project parcels 2 and 15 respectively, as shown on the plans.

Delete No. 4 and substitute the following:

4.	Extruded Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

- Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

SURFACE APPLIED

Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 60 mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of 60 mils.

INLAID

Inlaid markings apply to the road traffic markings shown on the plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

(1)	Longitudinal Markings.  Groove the pavement to a depth of 250 mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 250 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Groove the area for inlaid markings to a depth of 250 mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 250 mils.

(b)	Gore Markings:

Diagonal gore markings will not be inlaid unless shown in the Plans.

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01)

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Replace Subsection 670-3.06 with the following Subsection:

670-3.06 TOLERANCE FOR LANE STRIPING.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

Add the following Subsection:

670-3.07 CONTRACTOR’S WARRANTY.  Provide a warranty, for the Methyl Methacrylate Pavement Markings, as specified herein.

The period of warranty is 2 years.  The warranty period will start on the date the Engineer accepts the work and authorizes payment.

Pavement markings that do not satisfy the specified performance requirements will be repaired and or replaced by the Contractor.  The Department will determine if the failed markings will be repaired or replaced.  The Contractor will be notified, in writing, of the marking failure(s) and the corrective measures required including repairs and or replacement.

The Contractor will have 6 months to complete repairs.  The Contractor will coordinate the repair start and end dates with the Department.

The warranty period, for all project MMA pavement markings, will stop until corrective work is approved complete by the Department.

Performance Requirements.

1.	Retroreflectivity.  If retroreflectivity becomes a concern during the warranty period, the Engineer will measure the retroreflectivity of the area in question.  The roadway surface will not be cleaned in preparation for taking readings, but areas of obvious contamination or debris will be avoided.

a.	Longitudinal sample areas will be a minimum length of 500 feet and have at least three samples taken.

b.	Transverse, symbols and gore samples will be three per transverse line or symbol.

Table 670-1

PAVEMENT MARKING MINIMUM RETROREFLECTIVITY REQUIREMENTS

| Marking Color | Retroreflectivity, Minimum Levels |  |  |
| --- | --- | --- | --- |
|  | Initial Retroreflectivity a | 6 Months b | 2 Years b |
| Yellow, White | 200 mcd/m2-lux | 150 mcd/m2-lux | 40 mcd/m2-lux |

Footnotes:

a.	The initial retroreflectivity readings will be completed after the MMA has cured and no more than 7 days prior to the Engineer accepting the work.

b.	The 6 month and 2 year readings will be measured from the date of the initial retroreflectivity readings.

2.	Color Stability.  The pavement markings shall retain color throughout the warranty period.  Yellow striping will be compared to the PR-1 chart, and shall meet 33538 Federal Yellow.  White striping shall have a minimum daylight reflectance of 84 throughout the Warranty period.

3.	Adhesion.  For the purpose of the warranty a cumulative 5% or greater loss of longitudinal line of any 500 foot segment of marking and 5% or greater loss of each transverse line, gore stripe and symbol, due to nonadhesion, shall constitute failure of the material in that segment.

Repair.  Repair pavement markings as specified by the Department.

Replacement.  Replace pavement markings as specified in Section 670-3.01 Construction Requirements 4.f. Application and as specified by the Department.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measure from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete No. 2.

Delete No. 3 and replace with the following:

3.	Each.  Pavement markings using letters, numbers, and arrows will be measured on a unit basis with each separate word or symbol constituting a unit.

Add the following No. 4:

4.	Foot Basis.  Longitudinal pavement markings, transverse, and gore markings, surface applied or inlaid will be measured by the linear foot of line.

670-5.01 BASIS OF PAYMENT.  Add the following:

Payment for Extruded Methyl Methacrylate (MMA) Pavement Markings includes furnishing the Warranty.  Payment for the installation of the pavement markings will be limited to 80% of the amount due until the Department has received a signed Warranty.

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with pavement markings are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Temporary pavement markings and removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

The Pavement Marking Lines pay item applies to the parking lot lines.

Replace Item 670(4) and 670(10) with the following:

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 670(4) Pavement Marking Lines | Linear Foot |
| 670(10E) MMA Pavement Markings Longitudinal Inlaid | Linear Foot |
| 670(10G) MMA Pavement Markings Arrow Inlaid | Each |
| 670(10H) MMA Transverse Markings Inlaid | Linear Foot |

Delete Items 670(11) and 670(12).

Special Provisions

Add the following Section:

SECTION 690

EROSION, SEDIMENT AND POLLUTION CONTROL - MEASURES

690-1.01 DESCRIPTION.  Furnish, install and maintain measures, countermeasures and associated materials as part of BMP(s) to prevent, control and contain erosion, erosion materials, sediments and pollution contaminates, on and off project site.

Measures:

	Permanent Measures – include, the materials, hardware, equipment and labor required for installation and maintenance of erosion, sediment and pollution control material(s).

	Temporary Measures - include, in addition to the requirements of Permanent Measures, removal and disposal of the erosion, sediment and pollution control material(s).

Related Specifications:

Erosion, Sediment and Pollution Control	Section 641

Silt Fence	Section 633

Seeding	Section 618

Soil Stabilization	Section 619

690-2.01 MATERIALS.

Erosion Sediment and Pollution Control – Materials	Section 744

Others as specified in related Sections.

CONSTRUCTION REQUIREMENTS

690-3.01 GENERAL.  BMP(s) may include individual or a combination of measures and countermeasures, including but not limited to temporary seeding, mulch, matting, staples, stabilizing emulsions, blankets and mats, soil blinders, non-erodible cover, dustless sweeping, dust palliatives.  Refer to Subsection 690-1.01, Related Specifications, for measures not included here.

690-3.02 MATERIAL STORAGE AND PROTECTION.  General:  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment and as follows:

Fiber Rolls.  Additionally, protect fiber rolls from:  precipitation, extended ultraviolet radiant including sunlight, chemicals that are strong acids or other, flames including welding sparks, excess temperatures, and any other environmental conditions that may damage the physical property value of the rolls.

690-3.03 FABRICATION.

Sandbags:  Sand bags shall measure 15 inches by 30 inches.  Use prayer type seams with a minimum of two rows of stitching using a Federal Stitch Type 401 Chain Stitch.  Place approximately 1.0 cubic foot of Select Material, Type B, in each sandbag sack.  Close the open end of the sandbag, after filling, with 2 cinch ties or as recommended by the manufacturer of the sandbag material.

690-3.04 PLACEMENT AND INSTALLATION.  Place and install where shown and detailed in the Plans and Specifications including Section 641, and as recommended by the manufacturer, directed by the Engineer and as follows:

Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Confirm application of temporary seeding with the Engineer.

Prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetation cover.  Maintain seeded areas.  Refer to Section 620 for further surface/topsoil preparation requirements.

Reseed where water quality standards are being exceeded as a result of insufficient vegetative cover.  Review with Engineer prior to reseeding.

Refer to Section 618 for further information.

690-3.05 MAINTENANCE.  Maintain the integrity of the erosion, sediment and pollution control measures for the duration of the project.  Inspect as required by the NPDES CGP and SWPPP and correct any deficiencies immediately.  Remove and dispose of temporary measures including trapped sediment contaminants off project at approved locations. Materials manufactured as biodegradable may be left in place when approved by the Engineer.

690-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Fiber Rolls: By length, measured along the centerline of the fiber roll, complete in place.

Manufactured Inlet Protection Systems:  By each, complete in place.

Sandbag Inlet Sediment Trap:  By each, complete in place.

Silt Fence:  Section 633.

Seeding:  Section 618.

Stabilization:  Section 619.

690–5.01 BASIS OF PAYMENT.  Section 641.

# SECTION 701

HYDRAULIC CEMENT

701-2.03 GROUT.  Add to end of last sentence:  from specimens made according to ATM 507.  E30(3/15/06)

SECTION 702

ASPHALT CEMENTS

Special Provisions

702-2.01 ASPHALT CEMENTS.  Meet AASHTO M 320 and the following:

ADDITIONAL REQUIREMENTS FOR

PERFORMANCE GRADED ASPHALTS

Replace the column heading, PG 64-28 with PG 64-34.

CR702-040209

SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE.

Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

(Percent Passing By Weight)

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 | - | - |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

Replace Subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT PAVEMENT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Type IV, V and R mixtures.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

Meet the following requirements:

| Description | Specification | Type IIA | Type I, IIB, III | Type IV | Type V, R |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Degradation Value, Min | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium sulfate Loss % max (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP 61 | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |
| Thin-Elongated Pieces, max % | ATM 306 |  |  |  |  |
| 1:5 |  | 8 | 8 | 8 | 8 |
| 1:3 |  | 20 | - | - | 20 |
| Nordic Abrasion, max. % | ATM 312 | 12 |  | 12 | 12 |
| Absorption, max. % | AASHTO T 85 | 2.0 | 2.0 | 2.0 | 2.0 |

Fine Aggregate.  Aggregate passing the No. 4 sieve.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type IV, V, and R mixes:

	do not blend back natural sand

	shall be non-plastic as determined by WAQTC FOP for AASHTO T 90

	shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-3
BROAD BAND GRADATIONS FOR HOT MIX ASPHALT PAVEMENT AGGREGATE

(Percent Passing by Weight)

| Sieve | Gradation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V | Type R |
| 1 inch | 100 | - | - | - | - | - |
| 3/4 inch | 80-90 | 100 | - | - | 100 | 100 |
| 1/2 inch | 60-84 | 75-90 | 100 | 100 | 65-90 | 70-100 |
| 3/8 inch | 48-78 | 60-84 | 80-90 | 80-95 | 55-80 | 50-70 |
| No. 4 | 28-63 | 33-70 | 44-81 | 55-70 | 40-60 | 30-42 |
| No. 8 | 14-55 | 19-56 | 26-70 | 35-50 | ≤ 45 | 20-32 |
| No. 16 | 9-44 | 10-44 | 16-59 | 20-40 | ≤ 35 | 15-25 |
| No. 30 | 6-34 | 7-34 | 9-49 | 15-30 | ≤ 25 | 10-20 |
| No. 50 | 5-24 | 5-24 | 6-36 | 10-24 | ≤ 20 | 7-15 |
| No. 100 | 4-16 | 4-16 | 4-22 | 5-15 | ≤ 12 | 5-12 |
| No. 200 | 3-8 | 3-8 | 3-8 | 4-8 | 3-8 | 4-10 |

Note:

1.	No tolerance is allowed beyond the Broad Band Limits of the No. 200 Sieve.

2.	For Type R, the mix design gradation JMD shall provide a minimum of 8 % difference of percent passing the No. 4 and the No. 8 sieve.

CR703-040209

SECTION 707

METAL PIPE

Standard Modifications

Delete subsection 707-2.07 and replace with the following:

707-2.07 GALVANIZED STEEL WATER CONDUIT.  Meet the following:

Galvanized Pipe	ASTM A53 or ASTM A120, galvanized according to AASHTO 111

Galvanized Fittings	ASTM A234 galvanized according to AASHTO M 232.

(6/30/04)E17

SECTION 710

FENCE AND GUARDRAIL

Special Provisions

710-2.03 CHAIN LINK FABRIC.  Delete this subsection in its entirety and substitute with the following:

Furnish chain link fence and slats, as specified, meeting the following requirements:

- CHAIN LINK FENCE.  Type CL-1.8 woven from 9-gage galvanized steel wire.  Mesh openings shall be 3 and 1/4” vertically and 5 and 1/4” horizontally.

- WOOD SLATS.  Stained, clear redwood.  Wood slats shall not be less than 1/4” thick and 2 and 3/8” wide with a length sufficient to fill the vertical opening of the fabric.

710-2.05 FENCE POST.  Add the following:  Decorative fence column shall be wide flange W8x15 steel column.

Add the following subsection:

710-2.12 DECORATIVE FENCE PANEL.  Furnish fence materials as specified below:

- FENCE FRAMING.  Fence framing shall consist of 2" x 2" x 3/16" square steel tube.

- WELDED WIRE MESH.  The welded wire mesh shall be 6 gauge, 1 and 1/2" square wire mesh, welded, not woven, with a 1" flat bar welded to the outside of the wire mesh for attachment to the fence framing as shown on the plans.

- WIRE ROPE.  Wire Rope shall be from one of the following suppliers or approved equal:

Carl Stahl DecorCable, Inc.	Atlantis Rail Systems of Suncor Stainless, Inc.
660 West Randolph Street	70 Armstrong Road
Chicago, IL 60661	Plymouth, MA 02360
(800) 444-6271	(800) 541-6829

The Carl Stahl DecorCable wire rope shall be 8 mm SS rope, screwed external thread ends, screwed internal thread ends, and cylinder turnbuckles with RH/LH internal threads.  The Atlantis Rail Systems wire rope shall be rail easy cable railing with tensioner.

- FENCE HARDWARE.  All hardware shall be structural steel machine bolts.  Decorative fence flanges shall be 1/4" structural plate steel.

- DECORATIVE LOG.  Decorative logs shall be custom ordered 10” diameter half logs from one of the following suppliers or approved equal:

Superior Logs	Husky Log Work
P.O. Box 110469	P.O. Box 873148
Anchorage, AK 99511	Wasilla, AK 99687
(907) 345-3323	(907) 357-6006

Each log shall be coped 1" on each side by contractor  to create 8" decorative log that will custom fit into channel of wide flange.  Logs shall be sealed with two coats of varnish from one of the following suppliers or approved equal:

Valspar	Sutherland Welles LTD.
100 Hale Street	P.O. Box 1387
Newburyport, MA 01950	Morrisville, VT 05661
(800) 345-4530	(800) 322-1245

The Valspar varnish shall be McCloskey Man O’War Marine Spar Varnish Finish.  The Sutherland Welles’ varnish shall be Exterior Polymerized Tung Oil.  Contractor shall furnish and install half round logs.

- STEEL PIPE TOP RAIL.  The steel pipe rail shall be made of 1 and 7/8" diameter steel pipe.  Attach to the fence posts as shown on the plans.

SECTION 712

MISCELLANEOUS

Standard Modifications

712-2.06 FRAMES, GRATES, COVERS, AND LADDER RUNGS. In Gray iron castings, delete text and replace with:  AASHTO M 306 and AASHTO M 105, Class 35B.

E46 (01/27/07)

Special Provisions

712-2.17 EXTRUDED METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for the methyl methacrylate material, glass beads, and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

2.	Performance Properties:  Add the following:

I.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

712-2.18 GLASS BEADS FOR EXTRUDED METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace the bead table with the following:

Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

Lasting retroreflectivity.  For the two-year specified Warranty Period and retroreflectivity levels, Subsection 670-3.07.  The Engineer will determine the test location.

SECTION 719

STEEL, GRAY-IRON AND MALLEABLE-IRON CASTINGS

Standard Modifications

719-2.02 GENERAL REQUIREMENTS.  In Gray-Iron Castings, delete text and replace with:  AASHTO M 306 and AASHTO M 105, Class 35B.  (01/27/07)E47

SECTION 724

SEED

Special Provisions

724-2-02 MATERIALS.  Delete Table 724-1 and substitute with the following:

TABLE 724-1
Seed Requirements

| Species | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(01/27/07)R52USC

Delete this Section, except for Table 726-1, and substitute the following:

SECTION 726

TOPSOIL

Special Provisions

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area.  Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5% or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5% cannot be used as topsoil for the project.  In this case, furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse, or foreign materials having an organic content of 5% or more, as determined by ATM 203.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the location topsoil is to be furnished at least 30 calendar days before delivery of topsoil to the project from that location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.  (11/27/07)R208

SECTION 727

SOIL STABILIZATION MATERIAL

Special Provisions

727-2.01 MULCH.  Delete numbered Item 1 in its entirety and substitute the following:

- Virgin/Recycled Wood Fiber, or Blended Wood-Paper Mulch.

Mulch shall consist of specially prepared wood fiber processed to contain no growth or germination inhibiting factors.  The mulch shall be manufactured and processed in such a manner that the fibers will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry.  The mulch shall be of a texture such that it can be applied uniformly to the soil surface.  Mulch shall not create a hard crust upon drying and it shall have moisture absorption and retention properties as well as the ability to hold grass seed in contact with the soil.

The mulch shall be shipped in packages of uniform weight (plus or minus 5%) bearing the name of the manufacturer and the air-dry weight content.

The mulch shall be dyed a suitable color to facilitate inspection of the placement of the material.

A commercial adhesive shall be used on all seeded areas where mulch is applied.  The amount added will be as recommended by the manufacturer.

- Shredded Bark Mulch:  Shredded Bark Mulch shall consist of shredded bark and wood.  Maximum length of any individual components shall be 2 inches and a minimum of 75% of the mulch shall pass through a 1 inch sieve.  Mulch shall be free of growth or germination-inhibiting ingredients.  The bark mulch shall have the characteristics of retaining moisture, forming a mat not susceptible to spreading by wind or rain, and providing a good growth medium for plants.  Shredded bark may contain up to 50% shredded wood material.  Wood chips are not acceptable.  Bark mulch containing shredded wood shall be aged for one-year minimum prior to installation.  The mulch shall not contain resin, tannin, or other compounds in quantities that are detrimental to plant life.  Mulch shall be spread evenly in all planting beds as shown on Plans.

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS.  Add the following item:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2-inch-thick walls.  0.4-inch-diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized according to 1.b of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c of this subsection.  (06/22/04)R81USC04

SECTION 740

SIGNALS AND LIGHTING MATERIALS

Special Provisions

Replace subsection 740-2.02 with the following:

740-2.02 SIGNAL AND LIGHTING POLES.

1.	Design.  Design and fabricate highway lighting and traffic signal structures with pole shaft lengths to 65 feet long and breakaway signal poles with shaft lengths 10 to 15 feet long to conform to the 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions and the highway lighting and breakaway pole sheets in the Plans.  Design and fabricate traffic signal structures to conform to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions and the signal pole sheets in the Plans.

All working drawings and calculations must be stamped with the seal of, dated by, and signed by a Professional Engineer registered in the State of Alaska.  Submit the working drawings and calculations for each pole to the Engineer for approval.  Design for all stresses on the completed structure with all hardware in place.  Show the design wind loads, projected areas, wind drag coefficients, material properties, and other design information on the working drawings.  Include a summary of the loads used in each pole’s design.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

Design poles for 100 mph winds with a 1.3 gust factor.

Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 feet above the base of the pole.

2.	Fabrication.  Fabricate signal and lighting structures from tapered steel tubes with a round or 16 sided cross section.  Orient hand holes located near the base of poles to face downstream of traffic flow.

Provide traffic signal poles, lighting poles, and signal mast arms in lengths evenly divisible by 5 feet.

Furnish poles and mast arms up to 40 feet long in one piece.  Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice.  For slip type joints, provide a minimum overlap of 2.5 feet or the overlap specified in the Plans, whichever is greater.  In mast arms, locate these splices at least 1 foot away from the Plan location of signal heads and signs.  In signal poles, locate the edge of the female section at least 6 inches above the top of the signal mast arm connection.

Fabricate tubes with walls up to 1/2 inch thick from the prequalified base metals listed in AWS D1.  Fabricate elements greater than 1/2-inch-thick from steel that conforms to ASTM A709 and meets the Fracture Critical Impact Test requirements for Zone 3.  The Department will not accept structures that contain or are made with laminated steel elements.

Fabricate each tube from no more than two pieces of steel.  When using two pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from 2 inch nominal schedule 40 pipe that conforms to ASTM A53 Grade B.

Fabricate breakaway signal poles in accordance with the Pole Sheet in the Plans.  Fabricate signal poles 10 to 15 feet long from 7 U.S. Standard Gage sheet steel.  Fabricate each post with a minimum inside diameter of 8 inches at the base plate.  Use a 4-inch-long piece of 4-inch nominal schedule 40 pipe that conforms to ASTM A53 Grade B as a post-top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms.  To add lift points, weld them to the tube opposite the longitudinal seam weld on the outside of female segments and on the inside of male segments.  Before shipment, remove lift points added to the outside of the tubes, grind the area smooth with the base metal, and hot stick repair the finish according to subsection 660-3.01.8.a.  Lift points added to the inside of tubes in place may be left in place.

Hot dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications.  Completely submerge pole and mast arm segments in one dip in a kettle of concentrated zinc ammonium chloride flux solution heated to 130ºF, then completely submerge in one dip in a separate kettle of prime western grade zinc heated to approximately 825ºF.  Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove all excess zinc from all drip lines and points and the surfaces of all tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

a.	Not fabricated according to these specifications or the approved shop drawings,

b.	Bowed with sweeps exceeding 3/4 inch throughout the length of the pole, mast arm, or segment, if furnishing a two-piece pole or mast arm,

c.	Out of round.  Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2% of the dimension specified on the shop drawings.

Fabricate pile cap adapters from grade X42 steel line pipe that conforms to API 5L and from steel plate that conforms to ASTM A709 Grade 50.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Fabricate the anchor plate to match the base plate of the lighting standard.

3.	Welding.  Perform welding to conform to subsection 504-3.01 8.  Welding and the following:

a.	Make welds continuous.  Grind exposed welds flush with the base metal at slip joints, the length of the slip fit joint plus on half diameter of the female section.

b.	Use partial joint penetration (PJP) welds in longitudinal seams.  PJP welds must provide at least 60% penetration.

c.	Use CJP groove welds to connect base plates to tubes with 1/2 walls 5/16 inch thick and thicker.  When CJP groove welds are used, the designer may use additional fillet welds when deemed necessary.

d.	Use socket type joints with two fillet welds to connect base plates to tubes with walls less than 1/16 of an inch thick.

e.	On steels 5/16 of an inch thick and thicker, inspect 100% of CJP welds by either radiography (RT) or ultrasound (UT).

f.	Inspect a random 25% of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.  In steels less than 1/8 inch thick, complete the tests according to AWS D1.3.

g.	Only visually inspect welds made on luminaire mast arms.

4.	Miscellaneous.  Finish the edges of poles and mast arms to conform to the following requirements.  Before hot dip galvanizing, neatly round the following features to the radius specified

a.	On holes through which electrical conductors pass, provide a 1/16-inch radius on both the entrance and exit edges,

b.	On pole base plates, provide a 1/8-inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16-inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus 1/2 the diameter of the female section, grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces, and

d.	Furnish 2-inch-diameter (nominal) anchor rods for signal poles that meet ASTM F1554 Grade 105, are 96 inch minimum length and conform to Supplemental Requirements; S2 Permanent Manufacturer’s Identification, S3 Permanent Grade Identification, and S5 Charpy Impact Requirements.  Hot dip galvanize according to AASHTO M 232.  Use nuts that conform to AASHTO Specification M 292 of the grade, surface finish, and style for 2-inch-diameter anchor rods.  Washers shall conform to AASHTO M 293.

Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1.  The measurements shown are for illustration purposes only.  Use tags large enough to include required information using 1/4-inch-high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text.  Secure the tags with two 1/8 inch-blind rivets at the base of poles and the under side of mast arms.  If furnishing a two-piece signal mast arm with slip type joint, mark both pieces with the same message.

TABLE 740-1
Pole Markings
Note:  Italic type indicates additional Tag Markings
if poles have 2 luminaire or 2 signal mast arms.

|  | Measurements | Tag Markings |
| --- | --- | --- |
| Signal Poles |  |  |
| a) Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| b) Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| c) Pole height | 36 ft. | PH 36 |
| d) Intersection number (if more than one) - pole number |  | 1 - P 4 |
| e) Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| f) Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| a) Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| b) Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| a) Mast arm length | 40 ft. | SMA 40 |
| b) Intersection number (if more than one) - pole number |  | 1 - P 4 |
| c) Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| d) Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| a) Mast arm length | 18 ft. | LMA 18 |
| b) Pole number (if unique arm design) |  | P 4 |

740-2.05 CONDUCTORS.  Replace Table 740-2 with the following:

TABLE 740-2
Conductor Termination Table

| Conductors Per Cable | Circuit | Wire Color | Awg. No. | Band Legend |
| --- | --- | --- | --- | --- |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red Arrow | Red | 14 | Head No. |
|  | Vehicle Yellow Arrow | Orange |  |  |
|  | Vehicle Green Arrow | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Vehicle Yellow Arrow | Black |  |  |
|  | Vehicle Green Arrow | Blue |  |  |
| 5 | Pedestrian Don’t Walk | Red | 14 | Head No. |
|  | Pedestrian Walk | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | Black |  |  |
|  | Spare | Orange |  |  |
| 3 | Pedestrian Pushbutton | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 5 | Photo Electric Control | Black | 14 | PEC |
|  | Load to Contactor | Red |  |  |
|  | Neutral | White |  |  |
|  | Spare | Orange |  |  |
|  | Spare | Green |  |  |
| 3 | Flashing Beacon | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Preemption Confirmation | Black | 14 | “PRECON” |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Highway Luminaire | Black | 8 or 6 | Circuit No. |
|  | Highway Luminaire | Red |  | Circuit No. |
|  | Highway Luminaire Spare | White |  |  |
| 3 | Service to Controller | Black | 6 or 4 | “SIG” |
|  | Neutral | White |  | No Band |
|  | Spare | Red |  | No Band |
| 3 | Sign Luminaire | Black | 8 | SIGN |
|  | Sign Luminaire | Red |  | SIGN |
|  | Sign Spare | White |  |  |

Replace Item 7 with the following:

7.	Detector Loops.  Use No. 14 AWG conductors for detector inductive loops that meet IMSA Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans or specified in the Special Provisions.

Replace subsection 740-2.06 with the following:

740-2.06 ELECTRICAL CONDUIT AND FITTINGS.  Unless specified otherwise, use rigid metal conduit and fittings for raceways.  Furnish galvanized rigid type conduit and elbows that conform to UL-6 and are manufactured of mild steel according to ANSI C80.1.  Furnish third party certified fittings designed for rigid metal conduit.

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL-651.  Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL 651 B.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle.  Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline.  The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws.  For loop detectors, furnish type X bodies and, for photoelectric control installation, furnish types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it.  The movements include:  axial expansion or contraction to 3/4 inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to 3/4 inch.  The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

740-2.11 CONTROLLER CABINET.  Add the following to the first paragraph of subpart (1) of subitem c, Cabinet Wiring, of Item 1, Standard Features:  Furnish controller cabinets wired to accommodate five 4 channel inductive loop detector units and two 2-channel inductive loop detector units.

Replace bullet (e) of subpart (3), Field Terminal Blocks, of subitem c, Cabinet Wiring, of Item 1, Standard Features:  On the right side of controller cabinets, install two 16 position bus bars, for terminating the equipment grounding and neutral conductors used inside the cabinets.  On the left side of the controller cabinets, install two 32-position bus bars, for terminating the equipment grounding and neutral conductors from field wiring.

Replace the first three sentences of subpart (5), Light Fixture, of subitem D, Cabinet Accessories, of Item 1, Standard Features, with the following:  Mount a third-party certified, incandescent luminaire on the inside of each cabinet near the top edge of the door opening.  Install white porcelain, surface mounted lamp holders that fit medium base lamps and are rated for a minimum 600 watts and 250 volts AC.  Furnish each lamp holder with a 100 watt soft white incandescent lamp.

740-2.12  STANDARD AUXILIARY EQUIPMENT.  Under Item 3, Conflict Monitors, add the following:

d.	Supply conflict monitors with an RS-232 serial port that allows the monitor to download information through an external dial up modem or to a personal computer using the Microsoft Windows NT operating system.

740-2.13 SPECIAL AUXILIARY EQUIPMENT.  Add the following items:

Add the following after 740-2.13 Special Auxiliary Equipment subpart (2):

2.	Contractor shall provide five 4-channel and two 2-channel inductive loop detector amplifiers.

Add the following after 740-2.13 Special Auxiliary Equipment subpart (3):

3.	Contractor shall coordinate with the MOA Traffic Department to provide the following two modems:

Supply an internal system modem compatible with the existing computerized traffic control system.

Supply a system modem that is compatible with the existing computerized traffic control system and provides 802.1q VLAN-aware wire-speed bridging, double tagging (VLAN stacking) for end-user VLAN transparency, L2 (Ethernet priority) and L3 (ToS/DiffServ) classification with four traffic classes, RSTP/STP, bandwidth monitoring and Multicast/Broadcast limiting.

- Opticom Priority Control System.  Install the following components of the 3M Company’s Opticom Priority Control System according to 3M’s written installation instructions at the signalized intersections listed on the Plans.

Install the quantity of model 711, 721, and 722 optical detectors on the signal pole mast arms shown on the Plans.  Before installing the detectors, gain approval of their final lateral location from the Engineer.  See the Plans for installation details.

Install Model 138 Optical detector lead in cable between the end of each signal mast arm and the controller cabinet.  Furnish enough slack in these cables for them to extend 2 feet beyond the end of each signal mast arm and to leave 10 feet of slack in the controller cabinet.  Seal both ends of each lead in cable with mastic lined, heat shrink tubing end caps.

Before attaching the conductors to the optical detectors, strip the insulation for the conductors and attach four conductors to ground in the controller cabinet.  Attach the signal cable to the confirmation light.  The Municipality of Anchorage Signal Maintenance Section (MOA Signal Maintenance) will tie down the conductors in the controller cabinet.

Furnish each controller cabinet with a Model 754 phase selector, a Model 760 card rack, and an Opticom Panel Assembly, U.S. Traffic Corporation part number 103303.  The panel assembly interfaces the card rack to the controller cabinet.  Furnish new controller assemblies with these parts installed by the controller assembly manufacturer.  To retrofit existing controller assemblies, deliver the parts to MOA Signal Maintenance, who will install the parts.

7.	Traffic Logging System.  Furnish, and others will install in the controller cabinet, a stand alone unit that collects, time stamps, and stores data in an unattended manner.  The traffic logging system shall conform to the following:

a.	Operation.  The unit shall accept a new operating program, operational parameters, and the date and time stamp from a personal computer, downloaded through an RS-232 cable.  The use of replaceable proms to change the operational program is unacceptable.  Data collection shall be automatic and not require an operator to reset or start operation.

In the event of a power interruption, data collection shall automatically restart at the proper time.  Other than, the current sample being collected, the unit shall not lose stored data because of the power interruption.  At power up or at the restoration of power after an outage, the unit shall log the date and time at the start of data collection.

The unit shall maintain the operating program, data storage, and date/time for a minimum of 5 years from when power is removed from the unit.  The internal program/data size shall be a minimum of 32,000 bytes.

b.	Input Interface.  The unit shall have a minimum of 28 inputs.  Furnish new and existing controller cabinet only with a loose Detector Systems TLS-1-C1 interface cable to connect the unit to the output of the loop detector units.  The Municipality of Anchorage’s Signal Maintenance Section will install the interface cable in the controller cabinets.  Do not furnish new controller cabinets with a built in interface panel.

c.	Output Interface.  Furnish units with an RS-232 serial port that allows a user to download and upload directly between the unit and a personal computer using the Microsoft Windows NT operating system or the external dial-up multi-port modem.

Replace subsection 740-2.14 with the following:

740-2.14 VEHICULAR SIGNAL HEADS.  LED Signal Heads shall conform to the following publications:

	Circular Indications:  Vehicle Traffic Control Signal Heads:  Light Emitting Diode (LED) Circular Signal Supplement, 6/27/05 (ITE Publication ST-052).  This is hereafter referred to as “VTCSH-05.”

	Arrow Indications:  Vehicle Traffic Control Signal Heads – Light Emitting Diode (LED) Vehicle Arrow Traffic Signal Supplement 7/1/07 (ITE Publication ST-054), 4/3/06.  This is hereafter referred to as “VTCSH-Arrow-07.”

“The applicable ITE Specification,” as used in this specification, means VTCSH-05 for circular LED indications and VTSCH-Arrow-06 for arrow LED indications.

Each signal head must:  be an adjustable vertical type with the number and type of lights specified; provide a light indication in one direction only; be adjustable through 360 degrees about a vertical axis; and be mounted at the location and in the manner shown on the Plans.  Except for programmed visibility signal heads, vehicular signal heads installed at any one intersection must be of the same make and type.

1.	Signal Heads.  Use LED optical units for all indications.

Provide a removable aluminum tunnel visor with an open slot at the bottom for each optical unit.  When indicated on the Plans or in the Special Provisions, construct the visor of polycarbonate resin with the color (black) pigment completely impregnated throughout the resin material.

Factory finish signal heads, signal head mountings, brackets and fittings, and visors with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90 kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363, and ASTM D-522.  Coat all faces in a Dull Black finish meeting Federal Standard 595b-37038.  Painting is not required where the color is an integral part of the component material

a.	Optical Units.  Use LED signal modules that meet the requirements of the applicable ITE Specification.  Use one piece EPDM (ethylene propylene rubber) gaskets to seal LED modules.

b.	Lens.  Use lenses that meet the requirements of the applicable ITE Specification.

c.	Photometric Requirements.  Meet the requirements of the applicable ITE Specification.

d.	Markings.  Permanently mark the back of each LED signal module with the information listed in Section 3.6, Identification, of the applicable ITE Specification.  In addition, add a label saying “Manufactured according to the ITE LED Circular Signal Supplement.”

e.	Electrical.  Meet the requirements of the applicable ITE Specification.  LED signal modules must be operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

The catastrophic failure of an individual LED in a circular indication shall not result in the loss of other LEDs.  The catastrophic failure of an individual LED in an arrow or pedestrian signal, shall not result in the loss of more than 5% of other LEDs in that signal.

f.	Testing Requirements.  All LEDs Functional:  LED modules with any non-functioning individual LEDs at turn-on will be rejected.

Burn-in.  Require the manufacturer to energize each new LED module for a minimum of 24 hours at operating voltage and at a temperature of 140F before shipment, to ensure electronic component reliability.

Production Testing and Inspection.  Require the manufacturer to complete the tests in Section 6.3 of the applicable ITE Specification on each signal module.  Submit a manufacturer’s certification of successful completion of all tests with each signal module.

Design Qualification Testing.  An independent test lab with the requisite expertise shall certify that tests in Section 6.4 of the applicable ITE Specification have been successfully completed.  Submit one such certification for each project for each type of LED signal module to be used.  Successful completion of the tests means the LED signal module has met the requirements of Section 3, Physical and Mechanical Requirements, Section 4, Photometric Requirements, Section 5, Electrical Requirements, as well as the requirements of Section 6.4.

Exceptions:  Indications meet or exceed minimum intensities after 60 months of continuous use in a traffic signal system.

g.	Warranty.  Provide a manufacturer’s written warranty that covers defects in materials and workmanship for the LED signal modules for a period of 60 months.  The warranty period will begin on the manufacture date; however no unit will be accepted with a manufacture date one year or older at the time of installation.

Require the manufacturer to replace failed LED modules with new LED modules at no cost to the Department, including the cost of shipping failed modules.  The warranty does not include the cost of removing failed modules from or reinstalling new modules in a traffic signal system.  Require the manufacturer, upon notification a module has failed, to send the Department prepaid authorization to return the failed module.

Require the manufacturer to deliver replacement LED modules, within 5 working days of receiving failed modules, to the location designated by the Department.

Submit all warranty documents before installing the LED modules; including the manufacturer’s toll free telephone number for returning failed LED modules.

2.	Programmed Visibility Signal Heads.

a.	Indications provide a nominal 12 inch diameter circular or arrow indication.  Meet the VTCSH requirements for color and arrow configuration.

b.	Provide each section with a 1 inch cutaway visor.

c.	Provide each signal section with an adjustable connection that permits incremental tilting from 0 to 10 degrees above or below the horizontal while maintaining a common vertical axis through couplers and mounting axis in 5 degree increments.

d.	The signal must be mountable with ordinary tools and capable of being serviced without tools.  Preset the adjustment at 4 degrees below the horizontal.

e.	The visibility of each signal face must be capable of adjustment or programming within the face.  When programmed, each signal face’s indication must be visible only in those areas or lanes to be controlled.  During dusk and darkness a faint glow to each side will be permissible.

f.	Program the head as recommended by the manufacturer and as directed by the Engineer.

3.	Housing.

a.	Parts of the housing, including the doors and end plates, must be of die cast aluminum meeting ASTM B85, and parts must be clean, smooth, and free from flaws, cracks, blow holes, or other imperfections.

b.	The housing of each signal section must be one piece with integral top, bottom, and sides, with square doors.

c.	Exposed bolts, screws, hinges, pins, and door locking devices must be stainless steel.  Interior screws and fittings must be stainless steel or approved nonferrous, corrosion resistant material.

d.	The top and bottom of each housing must have an opening to accommodate standard 1-1/2 inch pipe fittings and brackets.

e.	The top and bottom opening of each housing must have an integral serrated boss that will provide positive positioning of the signal head in 5 degree increments so as to eliminate undesirable rotation or misalignment of the signal head as well as between sections.  A total of 72 teeth must be provided in the serrated boss.  The teeth must be clean and sharp to provide positive positioning with the grooves of the mating section or framework.

f.	Fasten together individual signal sections with a cadmium plated tri-stud connector, lockwashers, and nuts with access holes for the passage of electrical conductors from one section to another.

g.	Each signal housing must have 2 integral hinge lugs located on the left side for mounting the door.

h.	Provide 1 or 2 latches on the right side of each signal housing with stainless steel wing nut assemblies to engage the door latches.

i.	Each signal housing must have a door opening with a one piece EPDM gasket around the periphery to provide a weather tight seal with the mating door.

j.	Provide the door of each signal housing with a round opening designed to accommodate any standard traffic signal lens.

4.	Backplates.  Backplates shall not be louvered.  Install backplates around vehicular signal faces except post mounted flashers.  Furnish backplates constructed of 0.063 inch minimum thickness aluminum alloy sheet meeting ASTM B209, alloy 3003-H14.  For those backplates fabricated from 2 or more pieces of sheeting, furnish them fastened together with 3/16" aluminum rivets or bolts peened after assembly.

Furnish 5 inch wide backplates regardless of where the signals are installed, on mast arms, on top of posts, or on the sides of poles.

Furnish backplates with the back and front faces factory finished with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90 kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363, and ASTM D-522.  Coat the back and front faces of the backplate in a Dull Black finish meeting Federal Standard 595b-37038.

5.	Signal Mounting Hardware.  Furnish elevator plumbizers, elbow pipe fittings, and post top adapters (without a terminal compartment) with integral serrated contacts that feature 72 teeth.

Provide signal heads that will be mounted on mast arms or pipe tenons with ferrous or bronze elevator plumbizers.

For signal faces installed on the sides of poles, furnish signal frames that consist of watertight assemblies of 11/2 inch nominal diameter standard steel pipe, malleable iron or brass pipe fittings, and bronze terminal compartments.  The side of the terminal compartment opposite the door shall feature a saddle shape for wobble free mounting on round poles and include a cable guide and two holes for mounting the compartment.

Furnish vehicular signal frames with a horizontal dimension between the center of the terminal compartment and the axis of the adjacent signal face of 22 inches in side mounted frames and 11 inches in post top installations.

Post top adapters shall slip fit over 4 inch nominal standard pipe and feature two rows of three cadmium plated steel setscrews.  Furnish post top adapters with terminal compartments, except one way signal heads may be installed on adapters without a terminal compartment provided the adapters include offset openings.  Provide post top adapters without a terminal compartment made of cast iron.

Furnish terminal compartments with a terminal block containing 12 poles, each with two screw type terminals.  Each terminal must accommodate at least three 14 AWG conductors.  Provide terminal compartments with a rain tight door that provide ready access to the terminal block.

For mounting each terminal compartment, furnish two 1/2 x 13-inch hot dip galvanized bolts that conform to ASTM A325 and two 1/2" hot dip galvanized washers that conform to ASTM F436.

740-2.15 PEDESTRIAN SIGNALS.  Add the following as Item 12:  Furnish pedestrian signals side mounted on poles with a two-piece, hinge-connected, cast aluminum clamshell bracket that mounts directly between the pole and the side of the housing.  The bracket shall fit round poles with outside diameters of 4.5 inches and greater without wobbling and allow a minimum rotation of 15 degrees when mounted on a 4.5 inch O.D. pole.  The bracket shall feature a rain-tight terminal compartment and include a 3-position terminal block.  Installed, the bracket shall take less than 3 inches of space between the housing and pole.

For mounting each clamshell bracket, furnish two 1/2 x 13-inch hot dip galvanized bolts that conform to ASTM A325 and two spacers provided by the bracket manufacturer to keep the bolt head clear of the recess that holds the nut in a through bolted installation.

Pedestrian signals shall be countdown pedestrian signals.

Replace subsection 740-2.16 with the following:

740-2.16 PEDESTRIAN PUSH BUTTONS.  Tamper proof with a 2 inch minimum diameter convex 316 stainless steel actuator button.

Construct a weatherproof assembly designed to prevent an electrical shock under any weather condition and grounded per the NEC.

Push Button Switch.  Furnish Polara model RBDLM2-B-4H or approved equal with the following features.  Provide a solid state electronic piezo type, switching unit, with screw type terminals, rated 15 amperes at 125 volts, AC.  Must have the following characteristics:

1.	Switching unit that is solid state electronic piezo rated for 100 million cycles.

2.	Sealed to prevent ice from impeding function.

3.	Must hold the call for a minimum of 5 seconds.

4.	Switch operating force of 3 pounds or less with no moving plunger or moving electrical contacts.

5.	Provide an LED indication and an audible tone or beep within the button when pushed.

6.	Must have a raised rim or ridges to protect the button from side impacts.

7.	Powder coated cast switch housing of dark olive green or black.

Where a pedestrian push button is to be mounted on top of a 2-1/2 inch diameter post, provide the housing with a slip-fitter with screws for securing to the post.

Factory finish pedestrian push button housings, mountings, brackets, and fittings with 2 coats of dull black enamel or powder coat.  Painting/powder coating is not required where the color is an integral part of the component material.

Replace subsection 740-2.18 with the following:

740-2.18 ROADWAY LUMINAIRES.  Furnish luminaires that conform the following specifications and provide the light distributions specified.  When luminaire performance criteria are specified, luminaires shall also:

- Meet or exceed the minimum initial light levels indicated.

- Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified:  luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 2000.

Furnish each luminaire with a high pressure sodium lamp of the wattage specified and matching ballast with an input voltage equal to circuit voltage.  Furnish lamps that feature a rated life of 24,000 hours based on 10 hours per start and ballasts that conform to subsection 740-2.21.

Luminaries General

Install luminaires that feature:

1.	Corrosion resistant enclosures with gray paint finish and space for the ballast.

2.	Third party certification for use in wet locations.

3.	Glass lenses, unless polycarbonate resin refractors are specified.

4.	Terminal blocks for attaching the illumination tap conductors.

5.	Aluminum reflectors with an ALZAK or ALGLAS finish.

6.	Optical components free of substances that affect photometric performance (e.g., paint).

7.	Housings cast with no provision for a photoelectric control receptacle.

8.	Airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components.  Gasket material must withstand the temperatures involved and be securely held in place.

9.	Plug in starting aids in fixtures with lamps through 400 watts.

Luminaries - Cobrahead

Each cobrahead luminaire shall also include:

1.	An easily removed hinged door used exclusively for mounting the ballast.

2.	A second door that frames the lens, hinges on the house side, and fastens on the street side with an automatic type latch.

3.	A four bolt mounting brackets that fit 2 inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

Lenses

When polycarbonate resin lenses are specified, furnish lenses the fabricator certifies conforms to the following criteria:

1.	The lenses are molded in a single piece from virgin polycarbonate resin.

2.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

3.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

4.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

5.	The resins used meet the requirements for the self extinguishing classification of ASTM D635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D256, Method A, using a 1/8-inch by 1/2-inch bar molded according to ASTM recommended practice.

Special Provisions

Add the following Section:

SECTION 744

EROSION, SEDIMENT, AND POLLUTION CONTROL - MATERIAL

744-2.01 MATERIAL.

Fiber Roll:  (commonly called straw wattle).

a.	Comprised of UV-degradable plastic netting or 100 percent biodegradable material.

b.	Filled with straw, flax, rice, coconut fiber material or composted material.

c.	Staking shall be made of 100 percent biodegradable materials.

Provide the Engineer certification stating the name of the manufacturer, product name, style number, chemical composition of the fiber, netting and certification of the weed-free status from the manufacturer.  Furnish a sample to the Engineer seven days before the scheduled installation.

Manufactured Inlet Protection System:

a.	Manufacturers:

Ultra Tech International - Ultra-DrainGuard

Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

Enpac - Catch Basin Insert, Oil and Sediment or

b.	Approved equal.

Sand Bag Inlet Sediment Trap:

a.	Sandbag sack fabric shall be a nonwoven, needle punched design meeting the following requirements:

Grab Tensile Strength	ASTM D 4632	200 pounds (min.)

Grab Elongation	ASTM D 4632	15 – 70%

Mullen Burst Strength	ASTM D 3786	400 psi. (min.)

Trapezoidal Tear Strength	ASTM D 4533	95 lbs. (min.)

Apparent Opening Size	ASTM D 4751	No. 30 U.S. STD sieve (max)

Permittivity	ASTM D 4491	0.01 sec-1 (min.)

Ultraviolet Light Stability,
Retained Strength	ASTM D 4355	90%

Puncture Strength	ASTM D 4833	120 lbs. (min.)

These requirements are for Minimum Average Roll Values (MARV) verified in accordance with ASTM D 4759.

b.	Seam Thread:

Similar durability to the sandbag sack fabric.

c.	Sandbag Fill Material:

Select Material	Type B	703-2.07.

d.	Cinch Ties:  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

CR744-022309

appendix A

Erosion Sediment Control Plan

appendix b

State of Alaska Department of Environmental Conservation’s
Storm Water Non-Objection Letter

appendix c

Municipality of Anchorage Noise Permit

appendix D

Materials Certification List

appendix E

Sign Specifications

appendix F

Parcel Maps

APPENDIX G

Tudor Road Overlay Plans

APPENDIX H

Construction Surveying Requirements