SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	Copies for review of the following are available in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Design Computations

b.	Cross Sections

Copies of the above may be obtained from Ridgway's Reprographics, 6000 Arctic Boulevard, Anchorage, Alaska 99518, (907) 561-1555 at the Contractor's cost.

2.	The following are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Geotechnical Report, "____".

b.	Storm Water Manual (Price $20.00)

c.	Laboratory Manual of Alaska Test Methods and Standard Practices (Price $20.00)

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 266-1531.

4.	An environmental document addressing concerns and environmental commitments has been approved and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 266-1508.

5.	This contract contains a newly-developed asphalt concrete pavement specification (Section 401). Due to changes in materials testing procedures and requirements, the following new items are incorporated by reference in this specification:

a.	Alaska Test Method T-17, Rev. 06/93, Standard Method of Test for Determining Bituminous Mix Design by the Marshall Method.

Alaska Test Method T-17 is the mix design method and also includes criteria which must be met for the class of mix specified in the bid schedule.

b.	Alaska Standard Practice SP-9, Rev. 07/93, Standard Practice for Abbreviated Testing Procedures to Monitor Process Control of Coarse and Fine Aggregate Gradations.

Standard practice SP-9 contains test methods for contractor process control as well as a minimum testing frequency, and a list of typical field laboratory equipment to be furnished by the Contractor.

PART 4

SPECIAL PROVISIONS

to the

ALASKA DEPARTMENT OF TRANSPORTATION

and PUBLIC FACILITIES

INTERIM

STANDARD SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

94M

Add the following subsection:

SECTION 207

REMOVING, RELOCATING AND

DEMOLISHING STRUCTURES

Special Provisions

207-1.01 DESCRIPTION. Removing and relocating structures consists of the removal, preparation for moving and relocation of buildings or other structures, herein after referred to as "structure."

Demolishing structures consists of demolishing and disposing of all parts of the structure indicated on the plans, including foundations, basements, cisterns, underground tanks, walks, drives or other appurtenances.

207-2.01 GENERAL REQUIREMENTS. The Department reserves the right to eliminate the removal of any or all structures under these items. Such elimination shall not affect contract unit prices on remaining structures to be moved or unit prices on other items of the contract, and the Contractor will not be entitled to compensation due to such elimination.

The Contractor shall conduct his operations in accordance with Section 107.

207-3.01 REMOVING AND RELOCATING STRUCTURES. Structures shall be prepared for moving, removed, and placed in their new locations as shown on the plans or as designated, and left in as good condition as originally found. Structures removed and relocated shall be placed on foundations provided by others.

Steps, outside stairways, canopies, porches, block or post supports, sills, chimneys on brackets and other appurtenances forming an integral part of the structure are considered part of the structure and shall be removed and relocated accordingly. Cellars, cellar steps, concrete or masonry porches, concrete floors, solid or semi-solid concrete and masonry foundations and supports, septic tanks, wells, fireplaces and chimneys standing on the ground, and other appurtenances attached or connected to the structure shall be removed, relocated or replaced with foundations or appurtenances of the same size, type and character as existed before the structure was moved.

Sanitary sewers, water, gas, electric or telephone service lines connected to structure being removed and relocated shall be disconnected. The Contractor shall be responsible for all notices to public utility companies and for all fees charged by them.

Material in existing foundations, concrete or masonry floors, chimneys and other appurtenances, where not used in reconstruction of appurtenances, shall be removed and disposed of as directed.

New material required in performing any of the above operations shall be furnished by the Contractor at his expense.

207-4.01 METHOD OF MEASUREMENT. This work will not be measured for payment.

207-5.01 BASIS OF PAYMENT. Structures acceptably removed, moved, relocated and demolished will be paid for at the contract lump sum price.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

207(1)	Removing and Relocating Structures	Lump Sum

207(2)	Demolishing Structures	Lump Sum

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-5.01 BASIS OF PAYMENT. Add the following: The 2400 mm Structural Plate Pipe elbow will be subsidiary to Item 602(1B), Structural Plate Pipe, Diameter 2400 mm, Thickness 4.32 mm.

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Add the following: Traffic shall be maintained on an asphalt paved roadway during winter shutdown.

643-3.08 CONSTRUCTION SEQUENCING. Delete this subsection in its entirety and substitute the following: A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes or shoulders or their respective widths or stops traffic. An approved Traffic Control Plan is required before any restriction to traffic is implemented. No restrictions to traffic will be allowed during the times listed below:

1.	Around any holiday as described below:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1:30 PM on the Friday before the holiday to 10:00 PM on the day of the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1:30 PM on the Tuesday before the holiday to 10:00 PM on the day of the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1:30 PM on the day before the holiday to 10:00 PM on the Sunday after the holiday.

Complete road closures shall be limited to Monday through Friday, during the following periods:

1.	A maximum of one (1) hour anytime between 10:00 P.M. and 6:00 A.M. These closures shall be limited to halting traffic during rock blasting.

2.	One four (4) hour closure will be allowed to construct temporary drainage at Frenchy Creek.

The following limitations are also imposed on the Contractor:

1.	The Contractor shall construct the new embankment between Station 8+200 and Station 8+340 to the top of the Selected Material, Type A layer prior to winter shutdown. Following resumption of work in the spring, the Contractor shall complete this section of the roadway.

2.	Between Station 8+880 - Station 8+980 and between Station 9+380 - Station 9+580, the Contractor shall construct new embankment to just below the top of the existing roadway pavement. In addition, all ditches shall be graded to drain. Drainage shall be provided for all existing and/or proposed culverts. The top of the new embankment shall be graded a minimum of three (3) percent cross slope away from the existing roadway. Following the resumption of construction in the spring, the Contractor shall complete these sections of roadway.

It is anticipated that traffic can be kept on the existing paved roadway until the second construction season. The following construction phasing plan is a suggestion only and is not intended to prevent the Contractor from utilizing his ingenuity to arrive at alternate construction phasing.

1.	Construct new embankment between Station 8+200 and Station 8+340 to the top of the Selected Material, Type A layer prior to winter shutdown. Following resumption of construction in the spring, complete this section of roadway.

2.	Station 8+880 to Station 8+980 and Station 9+380 to Station 9+580, construct new embankment to just below the top of the existing roadway pavement. Grade all ditches to drain. Provide for drainage of all existing and/or proposed culverts. Grade the top of the new embankment to a minimum of three (3) percent away from the existing roadway. Following resumption of work in the spring, complete these sections of roadway.

Following this phasing sequence the project would be constructed as shown below:

A. During the first construction season

Perform all excavation and place all embankment material to the top of the Selected Material, Type A layer which would not interfere with the use of the existing paved roadway during winter shutdown. Construct all drainage features in these areas and provide required drainage to the new embankments.

B. Maintain traffic on the existing paved roadway surface during winter shutdown.

C. During the second construction season

Reshape the in-place material and complete the roadway to grade.