# SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October 2001.

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

d.	The Standard Specifications for Highway Construction 2001 USC units may be viewed or downloaded at no charge from the Statewide Design and Engineering Service Division’s external website.

3.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

4.	The Materials Certification List (MCL) has been included in Appendix A.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004 STANDARD SPECIFICATIONS

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

# 102-1.05 PREPARATION OF BID.   Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid shall be signed by a corporate officer,” add: or agent. E18(6/30/04)

SECTION 105

# CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES.  Add the following:  Request locates from all the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities:

ALASKA DIGLINE, INC. Locate Call Center Anchorage Area………………… 278-3121 Statewide 800-478-3121 who will notify the following:

ACS Alaska Fiberstar Alaska Railroad Corp Anchorage Water & Wastewater Alyeska Cable AT&T Alascom, Inc. Chugach Electric Assoc Enstar Natural Gas GCI Communications Homer Electric Assoc. Interior Telecom. Tesoro Alaska Pipeline Phillips Petroleum PTI Telalaska Unocal United Utilities

Call the following utilities and agencies directly:

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent’s phone number for this project.

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.

Right of Way and/or Construction surveying is required before utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is  required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

(09/01/04)R3

Standard Modification

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION.  Modify the first paragraph, Item 4., after: “DOLWD” add: and State Department of Revenue.  E19(06/30/04)

Special Provisions

105-1.17 CLAIMS.  Add the following Appeals to the superior court under AS 36.30.685 shall be filed in the third judicial district.  (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, before award of the contract.

Steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes shall be undertaken in the United States.  The definition of “manufacturing process” is smelting or subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting or other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrape,  pig iron, and processed, pelletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.  (02/07/05)S 13

106-1.02 LOCAL MATERIAL SOURCES.  Add the following under Item 2.  Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of the Contractor’s sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for the Engineer’s personnel (non-miners) before their beginning operations in the Contractor’s surface mine.  Offer the training at each surface mine that the Contractor will be using to supply processed aggregates.  A competent person shall provide the training according to the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (05/01/02)R262M98

SECTION 107

# LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

# Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.  Add the following:  Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If  cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

Add the following:  The Department has received the following permits on the Contractor’s behalf:

1.

2.

Provide information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from the Contractor.

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Change the first sentence to the following:  When operations encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following:  If required water for construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.  (05/29/02)R7M98

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.  (01/22/02)S 80

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1. A progress schedule.  and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.  (12/13/02)R261M98

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Under subtitle Electronic Computerized Weighing System item (1) add the following to the end of the first sentence:  “, CD, or a USB device.”

109-1.05 COMPENSATION FOR EXTRA WORK.

Under item 3.  Equipment, item a. add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.  (4/31/05)R14

Standard Modification

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of subsection 105-1.16. E11(06/30/04)

###### Special Provision

###### Add the following Section:	SECTION 120

# DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract.  Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy, as ADOT&PF deems appropriate.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.  The following definitions shall apply.

- Broker.  A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project.  A broker of materials certified in a supply category shall be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF).  The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment.  The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself.  To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work.  Other relevant factors will be considered.  The Engineer makes the determination of CUF after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE).  An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department according to 49 CFR, Part 26.

- DBE Key Employee.  Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts.  Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer.  A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification.  For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report.  Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer.  A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.   If the distribution equipment is rented or leased, it shall be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount.  A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document the required Good Faith Efforts under subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C shall be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid.  Each bidder shall register with the Civil Rights Office annually according to §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.   No contract may be awarded to a bidder that is not registered.

- Phase II - Award.  The apparent low bidder shall provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment.  Written commitments from DBEs to be used on the project.  The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report.  Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation.  Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal.  If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal.  If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer shall determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer.  At the preconstruction conference, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work.  The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in subcontract, purchase order or service agreement with that DBE.

- DBE Replacement.  If the Engineer approves a DBE replacement, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended according to subsection 120-3.02.

- DBE Utilization Goal.  The DBE Utilization Goal shall be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria.  The Contracting Officer shall use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document of the following actions constitutes insufficient Good Faith Effort.

- Consideration of subcontractable items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) before bid opening.  It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days before bid opening.  The bidder shall give the DBEs no less than five days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs shall be consistently applied.  DBEs certified to perform work items identified on Form 25A324 shall be contacted to solicit their interest in participating in the execution of work with the Contractor.  Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- The bidder may reject non-competitive DBE quotes.   Allegations of non-competitive DBE quotes shall be documented and verifiable.  A DBE quote that is more than 10.0% higher than the accepted non-DBE quote shall be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service.  Bidders shall have a non-DBE subcontractor quote for comparison purposes.  Such evidence shall be provided in support of the bidder’s allegation.  Where the bidder rejects a DBE quote as being non-competitive under this condition, the work shall be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote.  This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding.  Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h shall be utilized to evaluate requests from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor’s subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration.  Under the provisions of 49 CFR.  Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder shall indicate whether they would like an opportunity for administrative reconsideration.  The bidder shall exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection.   As part of this reconsideration, the bidder shall provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The DBE Liaison Officer will make the decision on reconsideration.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so.  If a meeting is desired, the bidder shall be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder.  The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work.  Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer according to this Section.  CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function.  In order for the CUF work of the DBE to be credited toward the goal, the Contractor shall ensure that the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO before submitting a bid to a contractor for DBE trucking.  The DBE trucking firm shall demonstrate that it owns trucks (proof of title and/or registration) to be credited for work and that operators are employed by the DBE trucking firm.  A DBE trucking firm that does not certify its trucks and personnel that it employs on a job shall be considered a broker of trucking services and limited to credit for a broker.  (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- The issuance of a purchase order or service agreement by the Contractor to a DBE performing as a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor shall receive credit for the CUF performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm shall meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed shall be necessary and useful work required for the execution of the Contract.

- The scope of work shall be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work shall be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work shall be performed with the DBE’s own equipment.  Either the DBE owner or DBE key employee shall be at the work site and responsible for the work.

- The manner in which the work is sublet or performed shall conform to standard, statewide industry practice within Alaska, as determined by the Department.  The work or provision of goods or services shall have a market outside of the DBE program (shall also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service shall be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services shall be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor’s operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- Subcontract work, with the exception of truck hauling, shall be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE shall control business administration, accounting, billing, and payment transactions.  The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, according to AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE.  Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal.  The Contractor shall still meet the DBE Utilization Goal by either

- Withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF.  Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE.  Under no circumstances shall the Contractor take action against the DBE firm until the Engineer has made a final determination.  The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE.  In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor is not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended according to items c through h of subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT.  The Contractor shall be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials according to 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.  This shall include DBE trucking firms certified as a subcontractor and not a broker.  Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value.  The value shall be the actual cost paid to the DBE but shall not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee shall not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee shall not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee.  The brokerage fee shall not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department.  The DBE joint venture partner shall be responsible for performing the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT.  Work under this item is subsidiary to other contract items and no payment shall be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department shall consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for subsection 120-3.04 item 3), the Department shall also consider this unsatisfactory work.

Unsatisfactory work may result in disqualification of the Contractor from future bidding under subsection 102-1.13 and withholding of progress payments consistent with subsection 109-1.06. (11/17/00)S 33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

#### Special Provisions

202-5.01 BASIS OF PAYMENT.  Add the following:  Item 202(18).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

202(18)  	Avalanche Gate and Foundation Removal	Lump Sum

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01 DESCRIPTION.  Add the following:  This work also consists of some minor clearing and grubbing to construct the embankment as shown in the Plans.

Add the following:  Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.  (02/26/03)R20USC02

203-3.03 EMBANKMENT CONSTRUCTION.  Delete the first sentence of the tenth paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 8” in thickness measured before compaction.  Each layer of classified material shall have its joint offset from the joint below, longitudinally by 1 foot and transversely by 10’.

Add the following: Where the plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements.  Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.

The surface of Selected Material, Type D, shall be compacted by coverage of the Contractor’s placement equipment to provide a smooth and firm slope.  The surface of Selected Material, Type D shall be free of surface irregularities, rutting, slope breaks or unconsolidated material. (03/14/02)R23USC

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL.  Delete this subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP FOR AASHTO T 99/T 180 or ATM T-212.  The Engineer will determine in-place field densities using WAQTC FOP  for AASHTO T 310.

Add the following: Compact embankment within 20’ of a bridge abutment full width to not less than 100 percent of the maximum density.  Material used within this zone shall be graded to pass the 3” sieve.

203-4.01 METHOD OF MEASUREMENT.

Add the following:

Item 203(27).  Measurement of ditch linear grading, whether flat bottom or "V" ditch, will be measured for payment by the station along the center of the ditch for each ditch so designated, constructed and accepted by the Engineer.

203-5.01 BASIS OF PAYMENT.  Add the following:  Grading and placement of material used within 20’ of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(5A) Borrow, Type A. (02/01/00)R113 USC

SECTION 205

EXCAVATION, BACKFILL AND FOUNDATION

FILL FOR MAJOR STRUCTURES

# Special Provisions

205-3.03 BACKFILL.  Add the following:  Backfill placed within 1 foot of a structural unit shall be graded to pass the 3-inch sieve.

205-5.01 BASIS OF PAYMENT.  Add the following:  Grading of material used within 1 foot of structural units will be subsidiary to Item 203(___), Borrow, Type __.

(07/24/95)R154USC

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

Special Provisions

301-2.01 MATERIALS.  Add the following after the first sentence:  If no gradation type is specified in the bid schedule the base course material gradation shall conform to the requirements for Grading D-1.  (11/05/02)R116USC02

Add the following after the first sentence:  At your option, recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5-inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 to 5.0 percent by weight of the RAM.

301-3.03 SHAPING AND COMPACTION.  Add the following:  If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern.  The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.  Add the following:  If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course, Type D-1 at the unit price shown on the bid schedule for that item.  (11/05/02)R176USC02

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

Replace subsection 401-2.01 with the following:

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN.  Meet the requirements of Table 401-1 for the Job Mix Design performed in accordance with ATM 417.

TABLE 401-1

Asphalt Concrete Mix Design Requirements

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |  |
| --- | --- | --- | --- |
| Stability, pounds | 1800 min. | 1200 min. |  |
| Flow, 0.01 inch | 8-14 | 8-16 |  |
| Voids in Total Mix, % | 3-5 | 3-5 |  |
| Compaction, number of blows each side of test specimen | 75 | 50 |  |
| Percent Voids Filled with Asphalt (VFA) | 65-75 | 65-78 |  |
| Asphalt Content, min. % | 5.0 | 5.0 |  |
| Voids in the Mineral Aggregate (VMA), %, min. |  |  |  |
| Type I Type II Type III, IV | 12.0 13.0 14.0 | 11.0 12.0 13.0 |  |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt (calculated by weight of mix).

The approved Job Mix Design will specify the target values for gradation, the target value for asphalt cement content, the Maximum Specific Gravity (MSG) of the mix, the additives, and the allowable mixing temperature range.

Target values for gradation in the Job Mix Design must be within the broad band limits shown in Table 703-3, for the type of asphalt concrete pavement specified but asphalt concrete mixture will have the full tolerances in Table 401-2 applied for evaluation in accordance with 401-4.03 except the tolerances for the largest sieve specified will be plus 0% and minus 1%, and the #200 sieve is limited by the broad band limits.

Do not produce asphalt concrete mixture for payment until the Engineer approves the Job Mix Design.  Do not mix asphalt concrete mixtures produced from different plants.

Use Asphalt Concrete Type II, Class B, minimum, for temporary pavement.

Submit the following to the Engineer at least 15 days before the production of asphalt concrete mixture:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3, for each type of asphalt concrete pavement specified in the Contract.

2.	Representative samples of each aggregate (coarse and/or intermediate, fine, and natural blend material) in the proportions required for the proposed mix design.  Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the mixture.  Include name of product, manufacturer, test results of the applicable quality requirements of subsection 702-2.01, manufacturer's certificate of compliance according to subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will then evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate type and class of asphalt concrete pavement specified and establish the approved Job Mix Design, which will become a part of the Contract.

No payment for asphalt concrete pavement for which a new Job Mix Design is required, will be made until the new Job Mix Design is approved.  Approved changes apply only to asphalt concrete mixture produced after the submittal of the changes.

Changes.  Failure to achieve results conforming to Table 401-1 or changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio, will require a new Job Mix Design.  Submit changes and new samples in the same manner as the original submittal.

Replace subsection 401-2.02 with the following:

401-2.02 AGGREGATES.  Conform to subsection 703-2.04.

Use a minimum of three stockpiles for crushed asphalt concrete aggregate (coarse, intermediate, and fine).  Place blend material in a separate pile.

401-2.03 ASPHALT Materials.  Delete the second paragraph and substitute the following.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before deliver to the project.  Document the storage tanks used for each batch on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket.  The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

Manufacturer’s certificate of compliance (106-1.05).

Conformance test reports for the batch (Section 702).

Batch number and storage tanks used.

Date and time of load out for delivery.

Type, grade, temperature, and quantity of asphalt cement loaded.

Type and percent of anti-strip added.

401-2.05 PROCESS QUALITY CONTROL.  Add the following to the first paragraph:  Provide copies of these test results to the Engineer within 24 hours.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS. Replace the last sentence with the following: Do not place asphalt concrete mixture unless the roadway surface temperature is 40 F or warmer.

401-3.03 ASPHALT MIXING PLANT.  Replace the second sentence in the second paragraph with the following: Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Delete the last paragraph:

401-3.05 ASPHALT PAVERS.  Replace the third sentence in the first paragraph with the following:  Use a 30 foot minimum ski, or other approved grade follower, to automatically actuate the paver screed control system.

Delete the second paragraph.

401-3.07 PREPARATION OF EXISTING SURFACE.  Replace the second sentence in the first paragraph with the following: Clean out loose material from cracks wider than 1 inch (+1 inch) in width full depth then fill using asphalt concrete tamp in place.  Clean, wash, and sweep existing paved surfaces of loose material.  The Engineer must approve existing surface before applying tack coat.

Replace subsection 401-3.08 with the following:

401-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES.  Replace the second paragraph with the following: Heat the aggregate for the asphalt concrete mixture to a temperature specified in the mix design.

401-3.12 PLACING AND SPREADING.  Add the following to the first paragraph:  The maximum compacted lift thickness allowed is 3 inches.

Replace the fifth paragraph with the following:

Do not pave against new Portland concrete curbing until it has cured for at least 72 hours.

401-3.13 COMPACTION.  Replace the first sentence in the third paragraph with the following: Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

401-3.14 Joints.  Delete the first paragraph and substitute the following: Minimize the number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.

Replace the last paragraph with the following:  Seal the vertical edge of longitudinal joints with Crafco 34524 Joint Adhesive or approved equal before paving against it.  Apply a 1/8 inch thick band of joint adhesive over the surface according to manufacturer’s recommendations.

For the top layer of asphalt concrete pavement, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

Seal the pavement surface 12 inches on each side of the longitudinal joints while the pavement is clean, free of moisture, and before traffic marking with GSB-78 (from Asphalt Systems), or approved equal.

401-3.15 SURFACE TOLERANCE.  Add the following:

The Engineer will measure the surface smoothness of the top layer of asphalt concrete pavement in the driving lanes with an inertial profiler before final acceptance of the project.  Remove and replace, or grind smooth any area of final pavement surface that has a smoothness Profile Index (PrI) greater than 15.0 inches per mile in a 0.1 mile interval.  PrI will be calculated using a 0.2 inch per mile blanking band.  Costs associated with meeting surface tolerances are subsidiary to the Asphalt Concrete pay item.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, or within 25 feet of manholes, or existing pavement.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph results (PrI) filtered with a 0.2 inch blanking band.  Report PrI as a job average for measured lanes, calculated to the nearest 0.1 inch.

401-4.01 Method Of Measurement.  Replace Asphalt Concrete with the following:

Asphalt Concrete.  By weighing, no deduction will be made for the weight of asphalt cement or anti-stripping additive, or by the area of final pavement surface.

Delete the subparagraphs titled Anti-Strip Additive and Job Mix Design.

Replace subsection 401-4.02 with the following:

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The quantity of each type of asphalt concrete mixture produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 4,999 tons, the contract quantity will be considered one lot. The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this Subsection.  Hot mix asphalt quantities of less than 300 tons remaining after dividing the lot into sublots will be included in the last sublot, hot mix asphalt quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 401-4.03 except as noted.

For contract quantity of less than 1,500 tons (and for temporary pavement), hot mix asphalt will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the hot mix asphalt to the specified depth and finished surface requirements and tolerances. Remove and replace any hot mix asphalt that does not conform to the approved Job Mix Design.

Any area of finished surface that is visibly segregated, fails to meet surface tolerance requirements is considered unacceptable according to subsection 105-1.11.

1.	Asphalt Cement.  Samples for the determination of asphalt cement content will be taken from either the windrow in front of the paver, or at the end of the auger, or behind the screed before initial compaction.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 o WAQTC FOP for AASHTO T308.

2.	Asphalt Cement Quality.  The Contractor shall sample asphalt cement form the asphalt cement supply line when requested, witnessed by the Engineer’s representative.  After purging residual asphalt cement, take 3 one-quart samples into wide mouth one quart metal containers.  Asphalt cement will be sampled for acceptance testing according to WAQTC FOP for AASHTO T 40 and tested for conformance to specifications in Section 702.  Three separate samples will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing.

3.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device, from the stopped conveyor belt or from the same location as samples for the determination of asphalt cement content.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the asphalt concrete mixture.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

4.	Density.  Cut full depth core samples from the finished asphalt concrete pavement within 24 hours after final rolling.  Neatly cut one 6 inch diameter core sample with a core drill from each sublot at the randomly selected location marked by the Engineer.  Use a core extractor to prevent damage to the core.  The Engineer will determine the density of the core samples in accordance with WAQTC FOP for AASHTO T 166/T 275.  Do not core asphalt concrete pavement on bridge decks.  Backfill and compact all voids left by coring with new asphalt concrete mixture within 24 hours.

5.	Retesting.  A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  The Engineer will mark the sample location for the density retest.  The original test results for gradation, asphalt cement content, or density will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation or asphalt cement content retesting of the sample from the first sublot of a lot will include retesting for the MSG.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  Replace the first sentence with the following: The following method of price adjustment will be applied to each type of Asphalt Concrete Pavement for which the contract quantity equals or exceeds 1,500 tons, except as specified in subsection 401-4.02.

Replace the fifth paragraph with the following: The Engineer will reject asphalt concrete mixture that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected mixture and tested if requested.  If all test results are within specification limits, payment will be made for the mixture.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted under Item 401(6), Asphalt Price Adjustment.  Costs associated with removal and disposal of the rejected asphalt concrete mixture are subsidiary to the Asphalt Concrete pay item.

###### Add the following note after Table 401-2

Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

Replace the PAB with the following:

PAB = Price Adjustment Base

PAB for Asphalt Concrete with PG 52-28 = $40.00 per ton

PAB for Asphalt Concrete with PG 58-28 = $50.00 per ton

PAB for Asphalt Concrete with PG 64-28 = $55.00 per ton

Add the following subsections:

401-4.04 EVALUATION OF ASPHALT CEMENT.

Asphalt cement will be randomly sampled and tested every 200 tons and evaluated for price adjustment.  If the last sample increment is 100 tons or less, that quantity of asphalt cement will be added to the quantity represented by the previous sample and the total quantity will be evaluated for price adjustment.  If the last sample increment is greater than 100 tons, it will be sampled, tested and evaluated separately.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.

The total asphalt cement price adjustment is the sum of the individual sample price adjustments and will be subtracted under Item 401(6) Asphalt Price Adjustment.

## Table 401-4

## ASPHALT CEMENT PAY REDUCTION FACTORS

## (Use the single, highest pay reduction factor)

|  | #### Spec | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 0 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.1 | 0.25 | Reject or Engr Eval |
| ##### Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | <3 Pa-s | <3 |  | >3 |  |  |  |  |  |  |
| Dynamic Shear | >1.00 kPa | >1.00 |  | 0.99-0.88 |  |  |  | 0.87-0.71 | 0.70-0.50 | <0.50 |
| Toughness | >110 in-lbs | >93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | <70.0 |
| Tenacity | >75 in-lbs | >63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | <48.0 |
| ##### Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | <1.00 % | <1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | >1.076 |
| Dynamic Shear | >2.20 kPa | >2.20 |  | 2.199-1.816 |  |  |  | 1.815-1.432 | 1.431-1.048 | <1.048 |
| ##### Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | <5000 kPa | <5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | >5867 |
| Creep Stiffness, S | <300 MPa | <300 |  | 301-338 |  |  |  | 339-388 | 389-450 | >450 |
| Creep Stiffness, m-value | >0.300 | >0.300 |  | 0.299-0.287 |  |  |  | 0.286-0.274 | 0.273-0.261 | <0.261 |
| Direct Tension | >1.0 % | >1.0 |  | 0.99-0.86 |  |  |  | 0.85-0.71 | 0.70-0.56 | <0.56 |

# Asphalt Cement Price Adjustment for each sample = 5 x PAB x Qty X PRF

PAB = Price Adjustment Base

Qty = Quantity of asphalt cement represented by asphalt cement sample

PRF = Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure

Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 day s to issue a written appeal.  The appeal must be accompanied by all of the Contractor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results and using ASTM D3244 determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor under Item 401(6) Asphalt Price Adjustment, shall pay the cost of testing the referee sample.

The total Asphalt Price Adjustment is the sum of all the price adjustments for each lot.

401-4.05 EVALUATION OF PAVEMENT FOR SMOOTHNESS.

The top layer of asphalt concrete pavement will be measured in accordance with 401-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

Smoothness Price Adjustment = PAB x PQ x SF

PAB = Price Adjustment Base (401-4.03)

PQ = Final quantity of Asphalt Concrete Mixture, tons

PrI = Final measured pavement smoothness, inches/mile

SF = Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1166 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0583 – (0.0083 x PrI)

The smoothness price adjustment will be applied under Item 401(6), Asphalt Price Adjustment.

401-4.06 EVALUATION OF LONGITUDINAL JOINT DENSITY.  Longitudinal joint density price adjustments apply when asphalt concrete mixture quantities are equal to or greater than 1,5000 tons.  A price adjustment will be based on the average of the joint densities on a project and determined as follow:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

Deduct = ($1.00 per lineal foot) x (lineal feet of paved joint for the entire project) x

(91 % - Project Average Joint Density %) x 100

(Note: convert density % to decimals in this equation)

2.	If project average joint density is greater than 91% MSG apply the following incentive:

Add = ($1.00 per lineal foot) x (lineal feet of paved joint for the entire project)

x (Project Average Joint Density % - 91%) x 100

(Note: convert density % to decimals in this equation)

The longitudinal joint price adjustment will be included in Item 401(6) Asphalt Price Adjustment.

401-5.01 BASIS OF PAYMENT.  Delete the second paragraph.

Replace the third and forth paragraphs with the following:

Asphalt cement, anti-stripping additives, tack coat, and crack sealing are subsidiary to the asphalt concrete pavement unless specified as pay items.

Price adjustments will not apply to:

Asphalt Concrete Mixture for leveling course

Temporary Pavement

Delete the sixth paragraph

Replace the last paragraph with the following:

The Engineer will assess a fee of $2,500.00 under Item 401(6) Asphalt Price Adjustment for each mix design subsequent to the approved Job Mix Design for each Type and Class of Asphalt Concrete Pavement specified.

Add the following:

Costs associate with patching defective areas are subsidiary to 401(1B) Asphalt Concrete, Type II; Class B.

(8/24/04)R199USC04

SECTION 606

GUARDRAIL

# Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers.  Use flexible markers with an over all length of 72 inches.  The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag which provides approximately 20 square inches of surface area.  Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacturer:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

# Special Provisions

606-3.01 GENERAL.  Replace the second sentence of the first paragraph with the following:  Conform to these Specifications and the Standard Drawings with the following exception.  Modify Standard Drawing G-20.10 to only allow an offset of 1.5 feet for the ET-2000.  (05/12/04)R266

606-3.02 POSTS.  Delete the first two numbered items in this Subsection and substitute the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL.  Add the following:  Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL.  Delete the last sentence and substitute the following:  Notify the Engineer a minimum of 5 days before removing guardrail for disposal.  The Engineer will notify ADOT&PF M&O (907-338-1466) and have an M&O representative physically identify portions of guardrail to be salvaged.  Deliver guardrail and associated hardware designated to be salvaged to the ADOT&PF M&O yard located at 5300 East Tudor Road.  Remaining items removed becomes the Contractor’s property.  (06/12/03)R259M98

Add the following subsections:

606-3.09 FLEXIBLE MARKERS.  For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine additional guardrail is necessary and you shall comply without delay.  (10/17/02)R45aUSC

606-5.01 BASIS OF PAYMENT.  Add the following:

Payment shall be made under:

Pay Item No.	Pay Item	Pay Unit

606(6B)	Remove and Salvage ET-2000	Each

606(9)	Controlled Release Terminal (CRT)	Each

606(11)	Extruder Terminal (ET-2000)	Each

606(42)	Avalanche Gate and Foundation Removal	Each

SECTION 607

# FENCES

# Special Provisions

607-2.01 MATERIALS.

607-5.01 BASIS OF PAYMENT.  Add the following:

Payment shall be made under:

Pay Item No.	Pay Item	Pay Unit

607(14A)	Avalanche Gate & Foundation	Each

(02/7/00) R46USC

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS.  Under item 1. delete the first sentence and substitute the following:  Unless Shop Drawings have been provided in the Contract, submit shop drawings for signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS.  Replace the sixth sentence in item 7 and substitute the following:

Deliver sign panels, posts and hardware to the State Maintenance Yard located in _______________.

615-3.02 SIGN PLACEMENT AND INSTALLATION.  Add the following:  Do not remove existing signs without authorization from the Engineer.

615-5.01 BASIS OF PAYMENT.  Delete the first sentence and substitute the following:  Sign posts, bases, mounting hardware, and concrete used for sign bases are subsidiary.

Add the following:  No separate payment for keeping existing signs in service until they are no longer needed or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1) Standard Sign.

No separate payment for removal of existing sign post foundations or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1) Standard Sign.

No separate payment for salvaging activities detailed in subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1) Standard Sign.  (11/06/02)R50USC02

# SECTION 618

# SEEDING

# Special Provisions

618-1.01 DESCRIPTION.  Add the following:  Topsoil and seed new or disturbed slopes and other areas directed by the Engineer.  Track the soil and apply seed, mulch, fertilizer, and water.  Provide a living ground cover on slopes as soon as possible.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following:  Apply seed as detailed in Subsection 618-3.03 immediately after the shaping of the slopes.  Cover all slopes to be seeded with topsoil according to Section 620.  Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  Seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION.  Add the following:  Apply seed, mulch, and fertilizer as follows per acre. Apply seed and mulch in one application if using the hydraulic method.  Apply fertilizer with the hydraulic method.

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
| Soil Stabilizer Slope ≤ 3:1 Slope >3:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

618-5.01 BASIS OF PAYMENT.  Add the following:  The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

The work described under Subsection 618-3.01, Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.  (11/06/02)R52USC

SECTION 620

TOPSOIL

# Special Provisions

620-2.01 MATERIALS.  Add the following:  Provide topsoil of the class specified on the Plans.

620-4.01 METHOD OF MEASUREMENT.  Add the following:  Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.  (11/06/02)R53USC02

SECTION 641

# EROSION, SEDIMENT, AND POLLUTION CONTROL

Special Provisions

641-1.02 DEFINITIONS.  Replace the last sentence of item 1 with the following: The Department describes common BMPs in its Alaska Storm Water Pollution Prevention Plan Guide, June 1, 2004.

Standard Modification

641-1.02 DEFINITIONS.  Item 6.  Delete “7” so sentence reads:  Use EPA Form 3510-13. E15(06/30/04)

Special Provisions

641-1.02 DEFINITIONS.  Replace the last sentence of item 9.  with the following: The approved SWPPP must contain a copy of the Contractor’s signed NOI.

Replace subsection 641-1.03 with the following:

641-1.03 SUBMITTALS.  For projects that disturb one acre or more of ground submit three copies each of the SWPPP and HMCP to the Engineer for approval.  Submit one copy of the SPCC Plan (if required under subsection 641-2.03) to the Engineer.  Sign submittals.  Deliver these documents to the Engineer no less than five calendar days before the preconstruction conference.

The Department will review the SWPPP and HMCP submittals within 14 calendar days.  Submittals will be returned to the Contractor as either requiring modification unless approved by the Department.  Besides a copy of the Contractor’s NOI, the approved SWPPP must contain a certification and be signed by an authorized representative according to the Standard Permit Conditions of the NPDES General Permit Part 8, Appendix G.  The Contractor must receive written notification from the Department that the SWPPP has been approved before the Contractor submits the original NOI to EPA.  NOIs can be submitted by Certified mail or through EPA’s electronic NOI system (eNOI).

For regular U.S. Mail delivery:			For Overnight/Express mail delivery:

EPA Storm Water Notice Processing Center		EPA Storm Water Notice Processing Center

Mail Code 4203M		Room 7420

U.S. EPA		U.S. EPA

1200 Pennsylvania Avenue, NW		1201 Constitutional Avenue, NW

Washington, D.C.  20460		Washington, D.C.  20004

For electronic mail, the Contractor must register online with EPA at: http://cfpub.epa.gov/npdes/stormwater/enoi.cfm.  This website has instructions and guidance on how to set up and use the eNOI system.

Whether submitting the NOI electronically or by mail, the Contractor may not begin ground disturbing activities until the Engineer has issued a written statement that the EPA has listed the Contractor’s NOI and the Department’s NOI as active.

The Department will submit the approved SWPPP to ADEC that will include both the Contractor and Department NOIs.

The active status NOIs, approved SWPPP, approved HMCP, and submitted SPCC Plan (when required) become the basis of the work required for the project’s erosion, sediment, and pollution control.

Once the Department has determined the site has achieved final stabilization, the Engineer will provide written notification to the Contractor that the Contractor’s NOT may be submitted to EPA with a copy to the Engineer.  The Department will transmit the Department’s NOT to the EPA.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

Replace the second to the last sentence in the first paragraph with the following:  Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, June 1, 2004.

Replace subsection 641-3.01 with the following:

641-3.01 CONSTRUCTION REQUIREMENTS.  Do not begin ground disturbing work until the Engineer provides written notice that both the Contractor and the Department’s NOIs have been listed as active and that ground disturbing work can begin.

Post at the construction site:

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	Name and phone number of the local contact person, and

3.	Location of a SWPPP available for viewing by the public.

Comply with requirements of the approved HMCP, the submitted SPCC Plan, and state and federal regulations that pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms.  Perform all fueling operations in a safe and environmentally responsible manner.  Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.  Report oil spills as required by federal, state and local law, and as described in the SPCC Plan.

Comply with requirements of the NPDES General Permit, implement temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.  Maintain temporary and permanent erosion and sediment control measures in effective operating condition.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections.  Before start of construction, conduct a joint on site inspection with the Engineer and the Contractor’s field representative to discuss the implementation of the SWPPP.

Conduct the following additional joint on site inspections with the Engineer:

a.	During construction, inspect the following at least once every seven days and within 24 hours of the end of a storm exceeding 1/2 inch in 24 hours (as recorded at or near the project site):

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections.  During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 1/2 inch or greater.  The Engineer may waive monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports.  Prepare and submit, within three working days of each inspection, a report on state Form 25D-100, with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) of personnel making the inspection.

c.	The date of the inspection.

d.	Observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

f.	Incidents of noncompliance.

Where a report does not identify any incidents of noncompliance, certify that the facility complies with the SWPPP and NPDES General Permit.  The Contractor and the Engineer will sign the report according to the Standard Permit Conditions of the NPDES General Permit, Part 8, Appendix G.  Include reports as an appendix to the SWPPP.

Retain copies of the SWPPP and all other records required by the NPDES General Permit, for at least three years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP to correct problems identified because of:

1.	Storm or other circumstance that threatens water quality, and

2.	Inspection that identifies existing or potential problems.

Submit SWPPP amendments to the Engineer within seven days following the storm or inspection.  Detail additional emergency measures required and taken, to include additional or modified measures.  If modifications to existing measures are necessary, complete implementation within seven days.

Stabilize areas disturbed after the seeding deadline within seven days of the temporary or permanent cessation of ground disturbing activities.

Submit a signed NOT to EPA and a copy to the Engineer:

1.	When the Engineer has acknowledged to the Contractor in written form that the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

2.	When the construction activity operator (as defined in the NPDES General Permit) has changed and the Engineer provides written notification that the Contractor’s responsibilities with respect to compliance with the NPDES GP on the project have ceased.

If the Contractor fails to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If the Contractor fails to:

1.	Pursue work required by the approved SWPPP,

2.	Respond to inspection recommendations and/or deficiencies in the SWPPP, or

3.	Implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from progress payments.

Replace subsection 641-5.01 with the following:

641-5.01 BASIS OF PAYMENT.

1.	Item 641(1) Erosion and Pollution Control Administration.  At the contract lump sum price for administration of work under this Section.  Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting, and record keeping.

2.	Item 641(3) Temporary Erosion and Pollution Control.  At the prices specified in the contract to install and maintain temporary erosion, sedimentation, and pollution control measures.

3.	Item 641(4) Temporary Erosion and Pollution Control Amendments.  At the prices specified in the directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures.  Work paid under this item will be shown as amendments to the original approved SWPPP or HMCP.

Temporary erosion and pollution control measures that are required at Contractor furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for the Contractor’s convenience, at the Contractor’s expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.  (07/08/04)R272USC04

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

641(1)  	Erosion and Pollution Control Administration 	Lump Sum

641(2)  	Temporary Erosion and Pollution Control 	Contingent Sum

R272USC04(07/08/04)

SECTION 642

# CONSTRUCTION SURVEYING AND MONUMENTS

642-2.01 MATERIALS.  Add the following:

Digital Measuring Instrument:  Nu-metrics, Nitestar DMI (www.nu-metrics.com)

642-3.01 GENERAL.

Add the following:

11.	Document the Stationing of the beginning and ending of existing passing zones before work that will remove or obliterate the existing striping.  Measure, as outlined below, sight distance for passing zones after the base course layer or pavement milling has been accepted.  Use Table 642-1 to establish Minimum Passing Sight Distance.  Move forward alongside the centerline or edge of traveled way in order to spot check and discover locations where the Minimum Passing Sight Distance drops below what is required for 10 MPH over the posted speed limit.  Record the sight distance for each station location that falls below the posted speed limit plus 10 MPH.  Continue to record the sight distance for each station location until the sight distance drops below what is required for the posted speed limit.  Stations observed to exceed the values required for posted speed limit plus 10 MPH should be marked as “Pass” or “+”.  Stations observed to fall below the values required for the posted speed limit should be marked as “Fail” or “-”.

Measure from the roadway edge of traveled way, using a 3.5 foot object height (or “instrument height”) at 100 foot station marks looking ahead to a 3.5 foot target height at the edge of traveled way for opposing traffic.  Provide a list of each station result for each direction of travel along the roadway edge of traveled way.  Certify and record the results on standard “letter” sized paper and provide 2 copies to the Engineer at least two weeks before laying out final pavement markings.

The Engineer will forward one copy of the existing and proposed sight distance measurements on the form provided herein, to the Regional Traffic Engineer.  Table 642-1 does not automatically ensure passing striping will be provided.  The Regional Traffic Engineer’s office will take up to two weeks to review and approve pass/no pass striping against operating speeds for the roadway before installation, using Table 642-1 and the Alaska Traffic Manual as a guide.  No pass striping zones shall be at least 500 feet in length.  Passing striping shall be long enough to meet the distances in Table 642-1.  Passing striping will not extend into a segment of road without minimum sight distance.  (3/22/06)R61USC04

### TABLE 642-1

# PASSING SIGHT DISTANCE

| Operating Speed (mph) | Minimum Passing Sight Distance (ft) |
| --- | --- |
| 25 | 450 |
| 30 | 500 |
| 35 | 550 |
| 40 | 600 |
| 45 | 700 |
| 50 | 800 |
| 55 | 900 |
| 60 | 1,000 |
| 65 | 1,100 |
| 70 | 1,200 |

# Passing Sight Distance Survey Table

ROAD NAME:___________________________________________________

Stationing 	FROM:______________________________	DATE:_____________

TO:	_________________________________	Surveyor:____________________

| Project Station | Posted Speed Limit | Direction of Travel | Sight Distance Ahead | Remarks |
| --- | --- | --- | --- | --- |

Other Notes:

1.

2.

3.

Accepted By: _____________________________________________Date:    ______________

DOT/PF Project Engineer

Passing Sight Distance

Review Checked By:______________________________________Date:    ______________		 DOT/PF Regional Traffic Engineer					(2/25/05)R61USC04

642-4.01 METHOD OF MEASUREMENT.  Add the following:

Item 642(16) Passing Sight Distance Measurement.  By the number of stations on the project measured separately along centerline, once for each direction, only after the certified and recorded results have been accepted by the Engineer.

642-5.01 BASIS OF PAYMENT.  Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

642(16)  	Passing Sight Distance Measurement 	Station

(3/22/06)R61USC04

SECTION 643

TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following: A waiver may be requested of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project in writing.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic within the project limits shall be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12-foot lateral separation between the non-street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.

643-2.01 MATERIALS.  Add the following:

Flexible Markers.  Refer to subsection 606-2.01 Materials.

Standard Modifications

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Immediately notify the Engineer of a traffic related accident that occurs within the project limits as soon as becoming aware of the accident.  (02/05/04)E10

Add the following:  Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following:  Traffic may be maintained on a continuous gravel surface for 1,000 feet.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place a temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.

643-3.04 TRAFFIC CONTROL DEVICES.

Standard Modifications

In the sixth paragraph, and also in Item 4.b. delete the words “ATTSA” and replace with “ATSSA” American Traffic Safety Services Association.  E16(6/30/04)

Delete the first sentence of the eighth paragraph and substitute the following: Items paid under this Section remain the Contractor’s property unless stated otherwise.

Add the following to item 1.  Embankments.:  Close trenches and excavations at the end of each continuous work shift.

Add the following to item 3.  Fixed Objects.:  Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete item 4.b. and replace with the following:  Flagger Certification by ATSSA

Delete item 6 and replace with the following:

6.	Street Sweeping.  Loose material shall be kept off of paved portions of the roadway, haul routes open to the public, and  sections of roadway off the project, where the Contractor’s operations have deposited loose material.  A street sweeper may be used that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Loose material shall be power broomed from paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material.  The power broom shall be able to eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule shall be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT &PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER.  Add the following after the second sentence:  In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following:  Traffic Price Adjustment shall also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices.  The Engineer shall make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public.  Failure to maintain an acceptable infrastructure or traffic control plan shall result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING.  Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Friday from 1200 hours to Sunday 2300 hours

2.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

3.	During the Alaska State Fair (August 26, 2004 - September 6, 2004)

Lane restrictions, if allowed shall be conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 1/4 mile (1,320 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 20 minute stopped delay, 80 vehicles, or 1/2 mile (2,640 feet) of traffic detained, shall be allowed for motorists except school buses.  If a queue of traffic develops at a stop, the entire queue shall be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Standard Modification

- Add the following new subsection:

643-3.11. HIGH VISIBILITY CLOTHING.  Ensure workers within project limits wear an outer visible surface or layer that complies with the following requirements:

1.	Tops.

Wear fluorescent vests, jackets, or coverall tops conforming to Class 2 at all times.  Class 2 requires at least 775 square inches of conforming fluorescent red-orange background material and at least 201 square inches of conforming retroreflective striping.  Retroreflective striping shall be fluorescent yellow-green combined-performance material.

The vest, jacket, or coverall top shall have two over the shoulder combined-performance retroreflective stripes, and at least one 360-degree horizontal combined-performance retroreflective stripe around the torso.  Jackets and coverall tops shall have two horizontal combined-performance retroreflective bands on each sleeve; one above and one below the elbow.

2.	Bottoms.

Wear fluorescent red-orange Class E pants or coverall bottoms during nighttime work (sunset to sunrise).  Flaggers shall wear fluorescent red-orange Class E pants or Class E coverall bottoms at all times.  Furnish each garment with two 2-inch wide combined-performance fluorescent yellow-green retroreflective horizontal stripes on each leg.

3.	Raingear.

Raingear tops and bottoms, when worn as the outer visible surface or layer, shall conform to the requirements listed above in (1) Tops and (2) Bottoms.

4.	Exceptions.

When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility clothing.

5.	Standard.

High visibility garments shall conform to the requirements of ANSI 107-1999 as well as this specification.  Class 2 and Class E garment requirements are defined in that standard.  Retroreflective material must also qualify as combined-performance fluorescent material.

6.	Labeling.

Garments shall be labeled according to Section 10.2 of ANSI-107-1999.

7.	Condition.

Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.

643-4.01 METHOD OF MEASUREMENT.  Add the following:  Payment for high visibility clothing for workers is subsidiary to other items.  (12/02/03)E07

Add the following:  No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  Work shall be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT.  Add the following:  The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $2.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Foot Foot Each Each | $0.30 $0.65 $0.75 $40.00 |

The Engineer shall pay for Item 643(15), Flagging on a contingent sum basis at the rate of $36/hour.  The Engineer does not require a change order/directive for the flagging pay item.  Flagging associated with Change Order work shall be paid at the prices agreed to in the Change Order, or on a time and materials basis according to subsection 109-1.05.  (08/02/04)R222USC04

Delete Item 643(15) and substitute the following:

Pay Item No.	Pay Item	Pay Unit

643(15) 	Flagging 	Contingent Sum

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

#### Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:  Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1,000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one disability parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).  The Engineer's office shall be accessible by the disability parking.

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water.

7.	Four telephone service lines available at the office location.

8.	If a part of the Contractor’s building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture, from Anchorage.

(11/19/02)R63USC

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

## Special Provisions

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and operations shall be according to the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor’s supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor’s responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used will be, as the Engineer considers necessary, for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first-class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which will be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  The Contractor shall furnish personnel who will be, and shall remain to be, employees solely of the Contractor during the work performed hereunder.

Furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS.  The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity shall be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor’s representative at the end of each shift, and a copy shall be provided to the Contractor’s representative.

647-4.01 METHOD OF MEASUREMENT.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas according to the instruction of the Engineer.  The pay time will not include idle periods, and no payment shall be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project shall not be authorized for payment.

647-5.01 BASIS OF PAYMENT.  Payment for Item 647(2) Wide Pad Dozer, 65 HP Minimum shall be paid by the hour at the rate shown on the Bid Schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified shall not entitle the Contractor to extra compensation. (11/12/98)R15USC

Payment shall be made under:

Pay Item No.	Pay Item	Pay Unit

647(1A) 	Wide Pad Dozer,  65-HP Min.	Hour

SECTION 724

SEED

# Special Provisions

724-2-02. MATERIALS.  Delete Table 724-1 and substitute with the following:

TABLE 724-1

Seed Requirements

| Species | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(11/06/02)R52USC

## APPENDIX A

EROSION AND SEDIMENT CONTROL DOCUMENT

## APPENDIX B

PROGRAMMATIC CATEGORICAL EXCLUSION DOCUMENT

APPENDIX C

COST EFFECTIVENESS ANALYSIS SUMMARIES