12/28/2011 4:12 PM  H:\FPark\H Drv Actv Prjcts\59296 Seward Hwy MP 43-50\Specials\Special 01 12 09\Addendums\59296 Addndm 2 021209.doc

PART 4

STANDARD MODIFICATIONS

AND

SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004

EDITION

01/20/09

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	An Alaska DOT&PF Geology Data Report for the Seward and Sterling Highway Refurbishment 04 (Seward MP 37 to 49.6), September 2005.

c.	State of Alaska Department of Transportation and Public Facilities publication, Alaska Storm Water Pollution Prevention Plan Guide, January 19, 2005.

d.	Standard Specifications for Highway Construction 2004.  ($25.00)

e.	Alaska Test Methods Manual (Lab & Field), 2007 Edition. ($25.00)

2.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

3.	The Materials Certification List (MCL) has been included in Appendix E.  This list is provided for the Contractor to determine which materials will require submittal to the project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

- The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retro reflectivity.  See subsection 643-3.11, High Visibility Clothing for requirements.

5.	Asphalt laydown temperatures may be monitored with a thermal imaging camera.  Unsatisfactory areas will be subject to additional testing and/or replacement at the Contractor’s expense under Division 400.

6.	The current Laborers Mechanics Minimum rate of Pay contains information on remote sites and per diem.  The Department of Labor has issued WHPL #197, which further clarifies this requirement.  See pay item 640(4).

7.	Administrative Order 226, issued July 24, 2005 establishes a 15% goal for hiring apprentices in certain job categories; on highway, airport, harbor, dam, tunnel, utility, or dredging projects awarded by the Alaska Department of Transportation and Public Facilities.  This Administrative Order will apply to projects advertised after September 1, 2005, where the project construction cost exceeds 2.5 million dollars.

For additional details, visit http://labor.state.ak.us//lss/forms/ApprenHireReq.pdf

8.	Based on guidance from the US Department of Transportation’s General Counsel, effective January 10, 2006 the Alaska Department of Transportation and Public Facilities implemented a Race Neutral Disadvantaged Business Enterprise (DBE) program by setting 0% project goals on all highway, mass transit, and airport projects.  All forms and reports required under the existing DBE program will continue to be required under these 0% goal contracts.

Specifically, contractors must continue to report creditable DBE participation/payments on the Monthly Summary of Disadvantaged Business Enterprise Participation Form 25A-336. This will allow the Department to continue to accurately report DBE participation to the Federal Highway Administration, Federal Transit Administration, and Federal Aviation Administration.

Contractors must also continue to provide opportunities for DBE firms to participate on highway, mass transit, and airport projects as appropriate.  A 0% DBE participation goal does not relieve the Contractor of the requirement to provide equal opportunity in subcontracting, supplies or other services offered by DBE firms.

Any questions about this notice may directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, jon_dunham@dot.state.ak.us

9.	As-built Plans, from the 1983 Seward Highway MP 36-50 Project, are available for review in the Department Central Files.  (907) 269-0571.

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS

PLANS. Delete text of PLANS and replace with:

The Department’s Contract drawings, profiles, typical cross sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.

E32 (01/27/07)

Replace the definitions of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.

E22 (01/01/06)

Add the following definition:

QUALIFIED PRODUCTS LIST. A list of companies and products that the Department has found conforms to the SSHC.

E36 (01/27/07)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.

Replace the second paragraph with the following:

The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development.

E23 (01/01/06)

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent.

E18 (06/30/04)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modifications

Delete Subsection 103-1.05 and replace with the following:

103-1.05 PERFORMANCE AND PAYMENT BONDS.  The successful bidder shall furnish all required Performance and Payment Bonds on forms provided by the Department for the sums specified in the Contract.  If no sum is specified, the successful bidder shall comply with AS 36.25.010.  The Surety on each bond may be any corporation or partnership authorized to do business in the state as an insurer under AS 21.09 or two individual sureties approved by the Contracting Officer.

If individual sureties are used, two individual sureties must each provide the Department with security assets located in Alaska equal to the penal amount of each bond.  Any costs incurred by the Contractor and the individual Surety are subsidiary and shall be borne by the Contractor or the individual Surety.  In no event will the Department be liable for these Costs.

Individual sureties shall provide security by one, or a combination, of the following methods:

1.	Escrow Account, with a federally insured financial institution, in the name of the Department.  Acceptable securities include, but are not limited to, cash, treasury notes, bearer instruments having a specific value, or money market certificates.

2.	Irrevocable letters of credit, with a financial institution approved by the Contracting Officer.

3.	Cashier’s or certified check, made payable to the State of Alaska issued by financial institutions approved by the Contracting Officer.

These bonds and security assets, as applicable, shall remain in effect for 12 months after the date of final payment or, if longer, until all obligations and liens under this Contract are satisfied, including, but not limited to, obligations under Subsection 107-1.19.

The Department may, in its discretion, notify the bonding company or Surety of any potential default or liability.

The Contractor shall substitute, within five working days, another bond or surety acceptable to the Department if an individual Surety or the Surety on any bond furnished in connection with the Contract:

1.	Becomes insolvent or is declared bankrupt;

2.	Loses its right to do business in any state affecting the work;

3.	Ceases to meet Contract requirements;

4.	Fails to furnish reports of financial condition upon request; or

5.	Otherwise becomes unacceptable to the Department.

When approved by the Contracting Officer, the Contractor may replace:

1.	An individual surety with a corporate surety; or

2.	Posted collateral with substitute collateral.

Failure to maintain the specified bonds or to provide substitute bonds when required under this section may be grounds for withholding contract payments until substitute bonding is obtained, and may, in the Department’s discretion, be grounds for declaring the Contractor in default.

E65 (01/12/09)

SECTION 105

CONTROL OF WORK

Standard Modification

105-1.02 PLANS AND WORKING DRAWINGS.  In the third paragraph delete: “(24"x36”)” and replace with: (22”x34”)

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS.  In the first sentence of the first paragraph after:  “Work performed and materials furnished shall conform to the Plans and Specifications” add: and approved Working Drawings,

In the first sentence of the second paragraph after: “Work or material not conforming to the Plans and Specifications” add: and approved Working Drawings,

E33 (01/27/07)

Special Provisions

105-1.06 COOPERATION WITH UTILITIES.  Add the following:  Request locates from the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities:

ALASKA DIGLINE, INC. Locate Call Centers Anchorage (907) 278-3121 Statewide (800) 478 3121

Call Centers will notify the following: Anchorage Communication System (ACS) Enstar Natural Gas General Communications, Inc. (GCI) Homer Electric Assoc. (HEA) Marathon Oil Tesoro Alaska Pipeline Phillips Petroleum Unocal United

Call the following utilities and agencies directly:

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent’s phone number for this project.

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:  The following state owned projects may be under construction concurrently with this project:

| Project Name: | Project No.: |
| --- | --- |
| Central Region Rumble Strips, Phase II | 51047 |

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

Standard Modification

105-1.13 MAINTENANCE DURING CONSTRUCTION.  Add the following at the end of this subsection:  Costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various Contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer’s opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance.  The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance.  If the Contractor fails to take the corrective action within the specified time, the Engineer may:

1.	Suspend the work until corrective maintenance is completed;

2.	Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

3.	Employ others for corrective maintenance and deduct the cost from the Contract amount.

E33 (01/27/07)

105-1.15 PROJECT COMPLETION.  In the second paragraph, second sentence, delete:  “Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

In the third paragraph, first sentence, delete:  “Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

E59 (07/28/08)

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION. Modify the first paragraph, Item 4. after: “DOLWD” add: and State Department of Revenue.

E19 (06/30/04)

Special Provision

105-1.17 CLAIMS.  Add the following:  Appeals to the superior court under AS 36.30.685 must be filed in the Third Judicial District.

R93 (03/21/01)

# SECTION 106

CONTROL OF MATERIAL

Standard Modification

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  In fifth paragraph, in two places remove the text: “Approved Products List” and replace with:  Qualified Products List

E36 (01/27/07)

Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, before award of the contract.

Steel and iron products which are incorporated into the work shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape, or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting, or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap, pig iron, and processed, pelletized, and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel, and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

R13 (02/07/05)

Standard Modification

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a. delete text and replace with:  Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4.  When there is insufficient useable excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

E24 (01/01/06)

Special Provision

106-1.02 MATERIAL SOURCES. Add the following to item 1.g.:  The cost to improve or develop access roads to the designated material source and subsequent cells, if developed, are subsidiary to the cost of providing the specified material.

Standard Modification

4.	Type of Sources.  Replace the first paragraph with the following:  The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

d.	Available Sources.  Replace the second paragraph with the following:  When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

E24 (01/01/06)

Special Provision

106-1.02 MATERIAL SOURCES.

Add the following to 4.d.:  If the Contractor elects to use the available material source at Mile 42, Alaska, MS # 31-1-012-1, it will be developed according to the Negotiated Material Sale Contract attached as Appendix F.  The material source is limited to designated areas as shown on the attached sale area map in Appendix F.  Clearing shall not be performed between May 1 and July 15.

The Contractor shall conform to requirements and special provision of the Negotiated Material Sale Contract.  The Contractor shall secure permits needed to conduct operations in the available source and for payment to the Department of Natural Resources for material removed for the project.

Standard Modification

4.	e.	Excluded Material Sources.  Replace the paragraph with the following:  Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material sources or any portion of a material source, at any time after Contract award, that is determined by material testing to be unsuitable for use on the project.

E24 (01/01/06)

Special Provisions

106-1.02 MATERIAL SOURCES.

Add the following to item 4.e. Excluded Materials Sources.:  The following material source is excluded:

MS #31-1-025-1 located at approximately Mile 49 Seward Highway.  This material source is located on state land.

Add new subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE.  The Contractor shall complete a Submittal Register, and shall submit it to the Engineer on forms provided by the Department.  The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified project documents.  The Contractor shall fill it out sequentially by bid item and allow at least three spaces between bid items.  The Submittal Register shall list: working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to: Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Traffic Control Plan, Storm Water Pollution Prevention Plan, Quality Control Program, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items.  If the number of copies of a submittal is not otherwise specified, three copies shall be required.  On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet.  The Contractor may use forms provided by the Department or a similar form of the Contractor’s choice as approved by the Department.  The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received.  The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed.  The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections.  The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department.  The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract item.

When material invoices, freight bills and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); project name and number where material will be incorporated; manufacturer, product number, quantity and cost.

E34 (01/27/07)

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.  Add the following:

Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling, or staging, on off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

Add the following:

The Department has received the following permit on the Contractor’s behalf:

1.	U.S. Army Corps of Engineers Nationwide 18 Permit, Minor Discharges;

Permit Reference POA-2006-301 – D.

Permit(s) are included in Appendix C.

Provide information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.

Change the first sentence to the following:

When operations encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following:

If required water for construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

R7 (05/29/02)

Standard Modification

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following paragraphs:

  - Restoring Areas.  Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed.  The original condition of an area shall be determined as follows:  Before beginning operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition.  After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs.  Before demobilization the Contractor shall repair damages attributed to its operations.  The Contractor agrees that costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

  - Material Disposal Sites.  Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result there from, together with permits required by law for such dumping.  A copy of such permission, waiver of claims, and permits shall be filed with the Engineer before beginning work on private property.  The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.

E35 (01/27/07)

Special Provisions

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following:

Maintain a Primary Zone of 300 feet as an undisturbed habitat buffer around nesting Bald Eagles.  If topography or vegetation does not provide an adequate screen or separation, extend this buffer to 0.25 miles, or a sufficient distance to screen the nest from human activities.  The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity.  Within the Secondary Zone, between 300 and 600 feet from the eagles’ nest tree no obtrusive facilities or major habitat modifications shall occur.  If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within-line-of site of the nest, this buffer shall extend up to 0.5 miles.  No blasting, logging, and other noisy, disturbing activities should occur during the nesting period (March 1 – August 31) within the primary or secondary zones.

Extremely noisy activities such as road construction or other activities that occur within the Secondary Zone shall be conducted outside the nesting period to avoid disturbance to eagles.  If activities occur in proximity to a nest site, employ an individual qualified to observe and assess the impact of such activities on nesting eagles.  For those unfamiliar with eagle behaviors, such behavior includes alarm calls, flushing birds from the nest or perch, and aggressive behavior by the birds.

If additional nest trees are discovered within the vicinity of the project site, the U.S. Fish and Wildlife Service must be notified immediately by calling (907) 260-2809 or (907) 271 2780, before starting construction activities, for further site evaluation.  This is an advisory.  Do what is required to keep from disturbing a nesting eagle.

R51 (12/09/02)

Special Provisions

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

S80 (01/22/02)

SECTION 108

PROSECUTION AND PROGRESS

Special Provision

108-1.01 SUBLETTING OF CONTRACT. Delete paragraph four and replace with the following:

Submit the Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or a subcontractor sublets any portion of the Contract.  The certification will be accepted by the Department in lieu of written approval of subcontracts.  The Department maintains the authority to review subcontracts, require prior written approval of subcontracts, and to deny permission to sublet work.  The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

1.	The Contractor shall ensure the following for each subcontract (agreement):

  - The Department is furnished with one completed Contractor Self certification, Form   25D-042, and two copies of the subcontract signed by both parties and including item descriptions and prices of subcontracted work before the subcontracted work begins;

  - The subcontractors have submitted a Bidder Registration, Form 25D-6;

  - The required prompt payment provisions of AS 36.90.210, as well as other items listed in Form 25D-042, are included in the subcontracts;

  - The subcontractors pay current prevailing rate of wages according to subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for work performed on the project; and

  - Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

R57 (01/02/08)

Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:

Submit the following at the Preconstruction Conference:

Delete the last sentence of the first paragraph in item 1. A progress schedule. and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.

R261 (12/13/02)

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Under substitute Electronic Computerized Weighing system Item (1) add the following to the end of the first sentence:

“, CD, or a USB device.”

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.  Under Item 3.  Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

R14 (04/31/05)

Standard Modification

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of subsection 105-1.16.

E11 (06/30/04)

Special Provisions

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract.  Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as the Department deems appropriate.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.  The following definitions will apply.

1.	Broker.  A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF).  The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment.  The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself.  To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered.  The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE).  An enterprise which is a for-profit small business concern

a.	that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

b.	whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

c.	has been certified by the Department in accordance with 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts.  Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer.  A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification.  For purposes of soliciting DBE participation on a project and to count toward a Contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer.  A DBE certified by the Department in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

d.	fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on Form 25A-324 (DBE Subcontractable Items) as a percentage of the total basic bid amount.  A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A-325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A-325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE.

1.	Phase I - Bid.  Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

2.	Phase II - Award.  The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

a.	Written DBE Commitment.  Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

(1)	A description of the work that each DBE will perform;

(2)	The dollar amount of participation by the DBE firm;

(3)	Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

(4)	Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

b.	DBE Utilization Report.  Form 25A-325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation.  Summary of Good Faith Effort Documentation (Form 25A-332A and attachments) and DBE Contact Reports (Form 25A-321A) if the Contractor submits less DBE utilization on Form 25A-325C than is required to meet the DBE Utilization Goal.  If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and cannot document the minimum required Good Faith Efforts (as outlined in Subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

3.	Phase III - Construction.

a.	Designation of DBE/EEO Officer.  At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

b.	DBE Creditable Work.  The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A-325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

c.	DBE Replacement.  If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  In the event the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

(1)	The Contractor has not committed any discriminatory practice in its exercise of good business judgment to replace a DBE.

(2)	If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

d.	DBE Utilization Goal.  The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that cannot be replaced.

120-3.02 GOOD FAITH EFFORT.

1.	Good Faith Effort Criteria.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document the following actions constitutes insufficient Good Faith Effort.

a.	Consideration of all subcontractable items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A-324) prior to bid opening.  It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

b.	If the bidder cannot achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

c.	Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening.  The bidder must give the DBEs no less than 5 days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs will be consistently applied.  DBEs certified to perform work items identified on Form 25A-324 must be contacted to solicit their interest in participating in the execution of work with the Contractor.  Each contact with a DBE firm will be logged on a Contact Report (Form 25A-321A).

d.	Non-competitive DBE quotes may be rejected by the bidder.  Allegations of non-competitive DBE quotes must be documented and verifiable.  A DBE quote that is more than 10 percent higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service.  Bidders must have a non-DBE subcontractor quote for comparison purposes.  Such evidence shall be provided in support of the bidder’s allegation.  Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

e.	Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

f.	Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

g.	Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

h.	Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding.  Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A-321A).

i.	Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

2.	Administrative Reconsideration.  Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration.  The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

a.	The decision on reconsideration will be made by the DBE Liaison Officer.

b.	The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so.  If a meeting is desired, the bidder must be ready, willing, and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

c.	The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder.  The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

d.	The result of the reconsideration process is not administratively appeal able to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

1.	Creditable Work.  Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.  CUF is limited to that of a:

a.	regular dealer;

b.	manufacturer;

c.	broker;

d.	subcontractor;

e.	joint-venture; or

f.	prime contractor.

2.	Determination of Commercially Useful Function.  In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure the following requirements are met:

a.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

b.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking.  The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm.  A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker.  (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

c.	The DBE is certified in the appropriate category at the time of

1)	the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

2)	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

d.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

e.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

f.	The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

(1)	The work performed will be necessary and useful work required for the execution of the Contract.

(2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

(3)	The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

(4)	The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department.  The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

(5)	The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

(6)	Subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

(7)	The DBE will control all business administration, accounting, billing, and payment transactions.  The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

g.	On a monthly basis, report on Form 25A-336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE.  Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal.  The Contractor must still meet the DBE Utilization Goal by either

a.	withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

b.	continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

(1)	increasing the participation of other DBEs on the project;

(2)	documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

(3)	by a combination of the above.

4.	DBE Rebuttal of a Finding of No CUF.  Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination.  The Engineer’s decisions on CUF matters are not administratively appeal able to US DOT.

120-3.04 DEFAULT OF DBE.  In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of subsection 120-3.02 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that cannot be replaced.

120-4.01 METHOD OF MEASUREMENT.  The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the CUF of a DBE prime contractor is 100 percent of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the CUF of a subcontractor is 100 percent of the monies actually paid to the DBE under the subcontract for creditable work and materials.  This shall include DBE trucking firms certified as a subcontractor and not a broker.  Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

3.	Credit for the CUF of a manufacturer is 100 percent of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60 percent of its value.  The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product, or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department.  The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A-325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.  Unsatisfactory work may result in disqualification of the Contractor from future bidding under subsection 102-1.13 and withholding of progress payments consistent with subsection 109-1.06.

S33 (11/17/00)

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01 DESCRIPTION.  Add the following:  Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage to a depth greater than 6 inches by grading with a small dozer, motor grader, or other suitable means as shown on the Plans, and approved by the Engineer.

203-3.01 GENERAL.  Delete the sixth paragraph and substitute the following:  Dispose of unsuitable material at locations approved by the Engineer.  Unclassified excavation from this project may be disposed in the MP 42 Material Site (M.S. 31-1-012-1).  Comply with the terms of the existing negotiated materials sale contract located in Appendix F for disposal requirements.

Add the following subsection:

203-3.06 DITCH LINEAR GRADING.  The Contractor shall grub, brush, and clean ditches where shown on the Plans and as directed by the Engineer.

203-4.01 METHOD OF MEASUREMENT.  Add the following to item 1:  No reduction in volume will be made for material removed under Section 202.

203-5.01 BASIS OF PAYMENT.  Add the following after item 9:

10.	Clearing of trees – Clearing shall not be performed between May 1 and July 15.

Add the following:  Payment for ditch linear grading will be full compensation for furnishing equipment, labor, tools, and incidentals to provide the preparation, clearing, excavation, and shaping necessary to complete the work.

Disposal of material generated from ditch linear grading is subsidiary to Item 203(27) Ditch Linear Grading and no separate payment shall be made.

Removal of fin drain from Sta. 2850+35 to Sta. 2870+65, LT. Is subsidiary to 203(3) and no separate payment shall be made.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

203(27)	Ditch Linear Grading	Station

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provision

204-3.01 CONSTRUCTION REQUIREMENTS.  Add the following after the third paragraph:

Excavation, bedding, backfill, and compaction for culverts outside the roadbed may be visually inspected and approved by the Engineer.

R204 (02/06/08)

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

Special Provisions

301-2.01 MATERIALS.  Add the following after the first sentence:  Recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

301-3.03 SHAPING AND COMPACTION.  Add the following:  If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based determined by control strip method ATM 412.  Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.  Add the following:  If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1) Aggregate Base Course at the unit price shown on the bid schedule for that item.

R176 (01/24/07)

SECTION 308

CRUSHED ASPHALT BASE COURSE

Special Provisions

308-1.01 DESCRIPTION.  Replace this subsection with the following:  The work includes; pulverizing the existing asphalt pavement and base course (to the depth shown in the Plans), processing the pulverized asphalt and base course, and placing, compacting, and shaping the processed material as shown in the Plans.

308-3.01 PULVERIZING AND MIXING.  Replace the first sentence with the following:  Process the existing asphalt pavement and base course so that 100% by weight passes the 2 inch sieve and 95 – 100% by weight passes the 1 1/2 inch sieve.

308-4.01 METHOD OF MEASUREMENT.  Replace Item No. 1 with the following:

1.	Crushed Asphalt Base Course.  By area measured from existing fog line to outside edge of existing pavement, each side of roadway.

Special Provision

Add the following Section:

SECTION 318

FOAMED ASPHALT STABILIZED BASE COURSE

318-1.01 DESCRIPTION.  The work consists of constructing a mixed in place foamed asphalt stabilized base.  Create foamed asphalt treated base course by simultaneously injecting and thoroughly mixing metered amounts of asphalt, Portland cement, and water into the pulverized asphalt and base course.  Spread, shape, and compact the mixed material according to these specifications and conforming to the dimensions shown on the Plans.

Provide an experienced foamed asphalt technician on site to supervise the foamed asphalt process and to supervise the related process control testing.

At the Preconstruction Meeting, provide information on the equipment proposed for use, the name, and resume of the foamed asphalt technician, and the location of the demonstration site.

MATERIALS

318-2.01 COMPOSITION OF MIXTURE – JOB MIX DESIGN (JMD).

1.	Sampling.  Before foamed asphalt stabilized base course production, laboratory tests of materials submitted by the Contractor shall be made to determine the quantity of asphalt cement and Portland cement required in the mix.  At least 15 days before the production of foamed asphalt stabilized base course, the Contractor shall furnish the following:

a.	500-pound representative sample of in-place aggregate

b.	200- pound representative sample of in-place asphalt concrete pavement

c.	10-gallons of asphalt cement

d.	One sack of Portland cement

2.	Job Mix Details.  The Engineer will determine the JMD using procedures contained in the Wirtgen Manual Foamed Bitumen Mix Design Procedure, using the Wirtgen WLB 10 to generate foamed asphalt.  The JMD will provide the following:

a.	The percent by weight of foamed asphalt cement to be added to the mix.

b.	The optimum percent by weight of water to be added to the asphalt cement for the foaming process.

c.	The minimum Foamed Asphalt Expansion Characteristics required.

d.	The temperature of asphalt cement at the time of injection.

e.	The percent by weight of Portland cement to be added to the mix.

f.	The gradation of the in place aggregate.

g.	The optimum compaction moisture content.

h.	Design dry indirect splitting tensile strength.

i.	The maximum dry density.

318-2.02 ASPHALT CEMENT.  Conform to subsection 702-2.01 Asphalt Cements PG 52-28.  Each batch of asphalt cement shall be tested to conform to specifications before shipping.  Storage tanks used for the batch shall be noted on the test report.

Provide the following shipping documents:

1.	Manufacturer’s certification of compliance.

2.	Conformance test results of the batch

3.	Manufacturer shall also document:

a.	date and time of loading

b.	batch number and storage tank

c.	type, grade, and quantity of materials loaded.

The vendor’s certified test report for the asphalt cement can be used for acceptance or tested independently by the Engineer.

Excess asphalt cement shall remain the property of the Contractor.  Removal of excess asphalt cement from the project area shall be incidental to the Contract and no separate payment will be made.

318-2.03 PORTLAND CEMENT.  Conform to subsection 701-2.01, Type I or II meeting low alkali requirements.

318-2.04 WATER.  Water shall be clean and free from sewage, oil, acid, strong alkalis, or vegetable matter.  Water of questionable quality shall be tested according to the requirements of AASHTO T 26.

318-2.05 CONTRACTOR’S FOAMED ASPHALT TECHNICIAN.  The Contractor shall provide an onsite technician to supervise the foamed asphalt process and the related process control of the product on the control strip and for 10 days of production.  This technician shall have a minimum of 5 years supervising successful projects using foamed asphalt cement with similar base material and equipment.  The technician must also be qualified to develop a foamed asphalt stabilized base course mix design and supervise the process control.

Provide a submittal that includes the following information:

1.	Resume of Technician

2.	A list of successful projects; provide owners contact, address, and telephone number;  location of projects.

3.	Description of foamed asphalt cement equipment used on the project.

318-2.06 CONTRACTOR PROCESS CONTROL AND ACCEPTANCE SAMPLING AND TESTING.  The quantity of foamed asphalt stabilized base produced will be divided into lots and the lots evaluated individually.

A lot will normally be 24,000 square yards.  The lot will be divided into sublots of 4,000 square yards.  The Contractor shall randomly sample and test for density and Indirect Tensile Strength for each sublot.  The Engineer will validate this test data for each lot through independent random testing before accepting it.

The Contractor shall provide the following:

1.	Daily production records for each sublot, including the quantity of asphalt cement, Portland cement, and in place compaction moisture content.

2.	Measure and report expansion ratio and half life of foamed asphalt cement for every 4 hours of production.

3.	Monitor and report in place field density of the foamed asphalt stabilized base for each sublot.

4.	Provide a laboratory, test equipment and a qualified technician for ITS and density testing on the jobsite using ATM 412.  Sample and perform Indirect Tensile Strength testing for each sublot according to Wirtgen Foamed bitumen mix design procedure manual, using calibrated equipment and a qualified technician.  Make a minimum of 3 specimens to average for each sublot Indirect Tensile Strength test.

5.	Report process control and acceptance sampling and testing data to the Engineer within 24 hours.

318-2.07 PREPROCESS MEETING.  A minimum of 5 days before initiating operations, hold a meeting on the jobsite where the Contractor’s technician outlines a processing plan.  This plan must address the sequence of operation, equipment to be used, and process control.  Outline steps to assure product consistency, conformity to strength requirements, proposed quality control testing frequency, traffic control, and public notification.

CONSTRUCTION METHODS

318-3.01 WEATHER LIMITATIONS.  Foamed asphalt stabilized base course shall not be mixed while the air or surface temperature is below 40F, or when conditions indicate that the temperature may fall below 40F within 24 hours, or when the aggregate is above the optimum compactions moisture content, or when the aggregate or subgrade is frozen.  Follow the recommendations made by the Contractor’s technical representative as approved by the Engineer regarding the acceptability of the weather conditions for foaming operation.

318-3.02 CONTROL SECTION.  Before full production, the Contractor shall use the equipment specified for the foamed asphalt stabilized base course operation and construct a control section at a location approved by the Engineer.  Process material in the control section two passes wide, 150 feet long and to the depth shown on the Plans, and develop a density standard according to ATM 412.  The Contractor’s technical representative shall supervise this process.

318-3.03 RECLAIMER (RECYCLER).  The reclaimer shall have the following features and capabilities:

1.	A minimum power capability of 600 horsepower.

2.	The capability to pulverize to the size specified, mix, and recycle material to the depth shown on the Plans.

3.	Ability to increase the effective volume of the mixing chamber in relation to depth of cut.

4.	Two microprocessor controlled systems, complete with two independent pumping systems and spray bars, to regulate the application of foamed asphalt cement, separate from water that is used to increase the moisture content of the mixed material.  Both systems shall perform in relation to the forward speed of the reclaimer and the mass of the material being processed.

5.	Two spray bars, one for foamed asphalt cement and one for compaction moisture, shall each be fitted with self cleaning nozzles at a maximum spacing of one nozzle for each 6 inch width of the mixing chamber.  Provide a way to monitor the flow rate at each nozzle to verify that all nozzles are producing foamed asphalt at the same rate.

6.	The foamed asphalt cement shall be produced at the spray bar in individual expansion chambers into which hot asphalt cement, water, and air are injected under pressure through individual and small orifices that promote atomization.  The rate of addition of water into the hot asphalt cement shall be kept at a constant percentage by mass of asphalt cement by the same microprocessor.

7.	A system within the operator cabin to verify the foamed asphalt is being evenly distributed across the full width of the spray bar at the rate specified.  The system shall be demonstrated to the Engineer to verify even spraying.

8.	An inspection or test nozzle shall be fitted at one end of the spray bar that produces a representative sample of foamed asphalt cement.

9.	An electrical heating system capable of maintaining the temperature of asphalt cement flow components above 300 degrees F.

10.	A single asphalt cement feed pipe installed between the recycler and the supply tanker.  Do not use circulating systems that incorporate a return pipe to the supply tanker.

11.	The ability to print out asphalt cement quantities used during production.

12.	The teeth on the mandrel mixing head form a Chevron pattern.

The reclaimer model proposed for use shall have successfully been used by the Contractor/subcontractor on other projects.  Provide a submittal of the reclaimer specifications at the Preconstruction conference.

318-3.04 PORTLAND CEMENT DISTRIBUTOR.    Use a cement distributor designed to spread a uniform coverage of Portland cement at a specified rate.  The spread rate shall be integrated with the speed of travel to maintain a uniform coverage.

318-3.05 ROLLERS.  Provide the following types of rollers as required:

1.	Self propelled vibratory pad foot roller having a minimum dynamic force of 60,000 lbs. for initial compaction.

2.	Pneumatic tired roller having a minimum operating weight of 50,000 lbs. for secondary compaction and finishing.

3.	Vibratory steel drum roller for secondary compaction and finishing.

318-3.06 GRADER.  Grader must have calibrated automatic cross slope blade controls.

318-3.07 PREPARATION.  The area to be stabilized with foamed asphalt cement may require pulverization, removal of material, grading, and shaping to conform to the grades and typical cross section shown on the Plans, then provide aggregate and pay for under a separate bid item.  Soft or yielding spots shall be removed and replaced with acceptable aggregate before being stabilized.

318-3.08 PULVERIZING.  Pulverize the existing asphalt pavement and base material so that at the completion of moist mixing, 100% passes a 2 inch sieve.  Multiple passes may be required to size the insitu material and to adjust moisture content before applying Portland cement and injecting foamed asphalt.

318-3.09 FOAMED ASPHALT CEMENT AND PORTLAND CEMENT APPLICATION, MIXING, AND SPREADING.  Mix insitu material with foamed asphalt cement, Portland cement, and water in place with a reclaimer.

Measure the moisture content of insitu material before processing and adjust if necessary.  The percentage of moisture in the aggregate, at the time of Portland cement application, shall not exceed the quantity that will permit a uniform mixture during mixing operations, and it shall not exceed the specified optimum moisture content for the foamed asphalt stabilized base course mixture.

Spread the required quantity of Portland cement uniformly on the surface to be stabilized.  Pulverize to the depth required while simultaneously injecting foamed asphalt cement and compaction water.  Mixing shall continue until the foamed asphalt cement, Portland cement and compaction water have been sufficiently blended with the existing material.

318-3.10 COMPACTION.  Immediately upon completion of the mixing operations, the mixture shall be thoroughly compacted with the initial compaction done with the vibratory pad foot roller.  The intermediate compaction shall be done with the pneumatic tired roller and the finish compaction shall be done with the vibratory steel drum roller.

Acceptable field dry density of the compacted mixture shall not be less than 98 percent of the standard developed on the control strip according to ATM 412.  Determine the in place field density by direct transmission according to WAQTC FOP for AASHTO 310, Method A.   The moisture content of the mixture at the start of the compaction shall not be above the optimum moisture content as determined by the foamed asphalt mix design.

318-3.11 FINISHING.  The completed foamed asphalt stabilized base course shall conform to the required lines, grades and cross section.  If necessary, the surface shall be lightly scarified to eliminate any deep imprints made by the compacting or shaping equipment.  The surface shall then be recompacted to the required density.  Seal the surface with water and a pneumatic roller.  Keep traffic off of the finished surface for a 24 hour cure period after sealing is completed.

318-3.12 CONSTRUCTION LIMITATIONS.  When the operation, after the application of cement, is interrupted for more than 30 minutes or when the uncompacted mixture is wetted by rain so that the optimum moisture content is exceeded by 2 percentage points, the decision to reconstruct the portion affected shall rest with the Engineer.  In the event the uncompacted, rain wetted mixture exceeds the specified moisture content tolerance, the Contractor shall reconstruct at the Contractor’s expense the portion affected.  Material along the longitudinal or transverse construction joints not properly compacted shall be reconstructed, at the Contractor’s expense, with properly moistened and mixed foamed asphalt stabilized base compacted to specified density.

318-3.13 SURFACE TESTS.   The finished surface shall not vary more than 3/8 inch when tested with a 10 foot straightedge applied parallel with, or at right angles to, the longitudinal axis of the pavement.  Variations in excess of this tolerance shall be corrected by the Contractor, at the Contractor’s expense, and in a manner satisfactory to the Engineer.

318-3.14 MAINTENANCE.  Maintain, at the Contractor’s expense, the entire base course within the limits of the Contract in a condition satisfactory to the Engineer from the time work starts until the work is completed.  Maintenance includes immediate repairs of defects that may occur either before or after the foamed asphalt stabilized base course has been constructed.  The work shall be done by the Contractor at the Contractor’s expense and repeated as often as necessary to keep the area intact.  Repairs shall be made in a manner that will ensure restoration of a uniform surface and the durability of the part repaired.  Faulty work must be reconstructed for the full depth of treatment.  Low areas shall be remedied by reconstructing the material for the full depth of treatment rather than by adding a thin layer of foamed asphalt stabilized base course to the completed work.

The Contractor is responsible for cost of road spray on vehicles and informing the public of potential hazards.

318-4.01 METHOD OF MEASUREMENT.    Section 109 and the following:

1.	Foamed Asphalt Stabilized Mix.  By area measured from fog line to fog line.

2.	Asphalt Cement.  By the weight recorded on delivery tickets minus waste, diversion, and remnant.

3.	Portland Cement.  By the weight recorded on delivery tickets minus waste, diversion, and remnant.

318-4.02 EVALUATION OF MATERIAL FOR ACCEPTANCE.  The Engineer must have Indirect Tensile Strength results and passing densities of the foamed asphalt stabilized base before allowing it to be covered by HMA pavement.  The Engineer will calculate the lot average of the Indirect Tensile Strength results from the acceptance testing for the project.  Payment shall be made at the Contract unit price per square foot for foamed asphalt stabilized base course when the lot average dry Indirect Tensile Strength is greater than 85% of the mix design.  This price shall be full compensation for furnishing materials, except asphalt cement or Portland cement, and for preparation, delivering, placing, and mixing of materials; and for labor, equipment, tools, and incidentals necessary to complete the item.

If the lot average dry Indirect Tensile Strength value is less than 85% of the JMD dry Indirect Tensile Strength value, the foamed asphalt stabilized base is deemed to not meet specifications.  The Contractor shall increase the thickness of the hot asphalt pavement for that lot and adjust the surface grade at the Contractor’s expense to compensate for reduced dry Indirect Tensile Strength.

T	=	(5.5-(6.25*(lot average dry ITS/JMD dry ITS)))

T	= 	increase in hot asphalt pavement thickness in inches

ITS	= 	Indirect Tensile Strength

318-5.01 BASIS OF PAYMENT

If the Contractor chooses to remove the centerline monuments to allow easier construction of the Foamed Asphalt Stabilized Base Course, the removal of the monuments will be subsidiary to Item 318(1).  The Contractor does not need to reinstall the monuments.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

318(1)	Foamed Asphalt Stabilized Base Course	Square Yard

318(2)	Asphalt Cement, Grade PG 52-28	Ton

318(3)	Portland Cement, Type I or II	Ton

Special Provisions

Replace Section 401 with the following:

SECTION 401

HOT MIX ASPHALT AND SURFACE TREATMENTS

401-1.01 DESCRIPTION. Construct one or more layers of plant-mixed Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown in the Plans.

MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD). Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 401-1.

TABLE 401-1

hOT MIX Asphalt Design Requirements

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (including asphalt cement) |  |  |
| Stability, pounds | 1800 min. | 1200 min. |
| Flow, 0.01 inch | 8.0 - 14.0 | 8.0 - 16.0 |
| Voids in Total Mix, % | 3.0 - 5.0 | 3.0 - 5.0 |
| Compaction, number of blows each side of test specimen | 75.0 | 50.0 |
| Asphalt Cement |  |  |
| Percent Voids Filled with Asphalt Cement (VFA) | 65.0 - 75.0 | 65.0 - 78.0 |
| Asphalt Cement Content, min. % | 5.0 | 5.0 |
| Dust-asphalt ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective HMA (calculated by weight of mix).

The JMD will specify the Target Values (TV) for gradation, the target value for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3, for the Type of HMA specified.  For acceptance testing, HMA mixture will have the full tolerances in Table 401-2 applied.  Except the tolerances for the No. 200 sieve, the tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3.  The tolerance limits for the No. 200 sieve will be confined by the broad band shown in Table 703-3.  Tolerance limits will not be applied to the largest sieve specified.

Do not produce HMA for payment until the Engineer approves the JMD.  Do not mix asphalt produced from different plants.

Use Hot Mix Asphalt Type II, Class B, minimum, for Temporary Hot Mix Asphalt pavement.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each Type of Hot Mix Asphalt specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will then evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of Hot Mix Asphalt specified and establish the approved JMD that will become a part of the Contract.

No payment for HMA, for which a new JMD is required, will be made until the new JMD is approved.  Approved changes apply only to HMA produced after the submittal of the changes.

Changes. Failure to achieve results conforming to Table 401-1 or changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio, will require a new JMD. Submit changes and new samples in the same manner as the original submittal.

401-2.02 AGGREGATES. Conform to Subsection 703-2.04.

Use a minimum of three stockpiles for crushed HMA aggregate (coarse, intermediate, and fine). Place blend material or mineral filler, if any, in a separate pile.

401-2.03 ASPHALT CEMENT. Provide the grade of asphalt cement specified in the Contract meeting the applicable requirements of Section 702.  If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (Section 702).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.

401-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Provide copies of these test results to the Engineer within 24 hours.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 401-4.02.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the HMA. Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS.  Do not place the HMA on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA unless the roadway surface temperature is 40° F or warmer.  Complete all final lift paving between May 15 and August 15.

401-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of HMA.

401-3.03 ASPHALT MIXING PLANT.  Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling conditions meeting OSHA safety requirements.

401-3.04 HAULING EQUIPMENT. Haul HMA in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

Cover the HMA in the hauling vehicle, when directed.

401-3.05 ASPHALT PAVERS.  Use self-propelled pavers equipped with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip the hopper with a distribution system to place the HMA uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the HMA.  Heat and vibrate screed extensions.  Place auger extensions within 20 inches of the screed extensions or according to written manufacturer’s recommendations.

Equip the paver with a means of preventing the segregation of the coarse aggregate particles from the remainder of the bituminous plant mix when that mix is carried from the paver hopper back to the paver augers.  The means and methods used shall be approved by the paver manufacturer and may consist of chain curtains, deflector plates, or other such devices and any combination of these.

The following specific requirements apply to the identified asphalt pavers:

(1)	Blaw-Knox asphalt pavers shall be equipped with the Blaw-Knox Materials Management Kit (MMK).

(2)	Cedarapids asphalt pavers must have been manufactured in 1989 or later.

(3)	Caterpillar asphalt pavers shall be equipped with deflector plates.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers.  Operate rollers according to manufacturer's instructions.  Avoid crushing or fracturing of aggregate.  Use rollers designed to compact HMA and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers with a minimum operating weight of 3000 pounds per tire.

401-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to an existing paved surface, clean loose material from cracks for the depth of the cracks.  Fill the cleaned cracks, wider than 1 inch, with HMA tamped in place.  Wash the paved surface clean.  Sweep the surface free of loose material.

Preparation of a milled surface:

●	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than 1/2-inch with Hot Mix Asphalt, Type IV.  The Engineer’s approval of the material and material installation is required.  The Engineer will inspect the material and material installation.  Correct material and material installations identified by the Engineer as required by the Engineer for approval.  Density testing is not required for the leveling course (prelevel) material, material installation.

●	Where the planing equipment breaks through existing pavement, remove 2 inches of existing base material depth and replace with Hot Mix Asphalt, Type II.

During the planing operation, notify the Engineer of pavement areas that may be thin or unstable.

Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow prime coat to cure and emulsion tack coat to break before placement of HMA on these surfaces.

401-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA concrete containing soot or fuel is unacceptable according to Subsection 105-1.11.

401-3.10 MIXING.  Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD. Mix to obtain 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

Mix the HMA within the temperature range determined by the JMD.

401-3.11 TEMPORARY STORAGE.  Silo type storage bins are acceptable, provided the characteristics of the HMA are unaltered.  Signs of visible segregation, heat loss, changes from the JMD, and change in the characteristics of asphalt cement, lumpiness, or stiffness of the HMA are causes for rejection.

401-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling (preleveling) courses.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer may evaluate the HMA immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding HMA may produce areas of low density.  Contractor, immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland Cement concrete curbing until it has cured for at least 72 hours.

Place HMA over bridge deck membranes according to Section 508 and the manufacturer's specifications.

401-3.13 COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

The target value for density is 94% of the maximum specific gravity (MSG), as determined by WAQTC FOP for AASHTO T 209.  For the first lot of each Type of HMA, the JMD will determine the MSG.  For additional lots, the MSG will be determined by the sample from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6-inch diameter core.  (Acceptance testing for density of leveling course or temporary pavement is not required.)

Do not leave rollers or other equipment standing on HMA that has not cooled sufficiently to prevent indentation.

401-3.14 JOINTS. Minimize the number of joints.  Do not place/construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Remove to full depth improperly formed joints resulting in surface irregularities, replace with new HMA, and thoroughly compact.

Precut pavement removal to a neat line with a power saw or by other method approved by the Engineer.

Form transverse joints by saw cutting back on the previous run to expose the full depth of layer with a power saw or other method approved by the Engineer or use a removable bulkhead. Skew transverse joints between 15-25 degrees.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 12 inches from the edge of the stripe.

Uniformly coat joint surfaces below the final lift with tack coat material conforming to Section 702 before placing any fresh HMA against the joint.

Before placing an adjacent panel of HMA to form a joint in the top layer, apply Crafco Pavement Joint Adhesive No. 34524 Deery Cold Joint Adhesive or approved equal, to the edge of the existing panel.  Edge surface preparation, application temperature, thickness, and method shall be according to manufacturer’s recommendations.

For the top layer of HMA, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the HMA is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be according to the manufacturer’s recommendations and an application rate of 0.15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150F.  These joints do not need to be tacked and will be measured but not evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03.

401-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge.  Correct variations from the testing edge, between any two contacts of more than 1/4 inch.

The Engineer will measure the surface smoothness of the top layer of HMA pavement in the driving lanes with an inertial profiler before final acceptance of the project.  Remove and replace, or grind smooth any area of final pavement surface that does not meet straight edge tolerances.  Costs associated with meeting surface tolerances are subsidiary to the Hot Mix Asphalt Pay Item.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, or within 25 feet of the existing pavement at the project beginning and end.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph (Prl) results filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

401-3.16 PATCHING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated, or is in any way determined to be defective.  Do not skin patch. Remove defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh HMA according to Subsection 401-3.13 to grade and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the Hot Mix Asphalt Pay Item.

401-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

Hot Mix Asphalt.

a)	By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive.

b)	By the area of final HMA surface.

Asphalt Price Adjustment.  Calculated by quality level analysis under Subsection 401-4.03.

Asphalt Cement.  By the ton, as follows.

1.	Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASTHO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

2.	Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time, that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement. The Engineer will determine the method. The weight of asphalt cement in waste HMA will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt content specified in the JMD.

Job Mix Design. When specified, Contractor furnished JMD(s) will be measured as one according to the HMA Class and Type.

Temporary Pavement.  By weighing.  No deduction will be made for the weight of asphalt cement or anti-stripping additive.

Longitudinal Joint Adhesive and Sealing.  By the linear foot of longitudinal joint.

Preleveling.  By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.

HOT MIX ASPHALT

The quantity of each Class and Type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 4,999 tons, the contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  HMA quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  HMA quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 401-4.03 except as noted.

For contract quantity of less than 1,500 tons (also for approaches and temporary pavement), HMA will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the HMA to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any HMA that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

1.	Asphalt Cement.  Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, at the end of the auger, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.  HMA samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

The Engineer will determine sample locations.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device or from the stopped conveyor belt according to WAQTC FOP for AASHTO T2 or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.  A separate set of random numbers, different from those used for mix acceptance, will be used to determine acceptance density locations.  Cut full depth core samples from the finished HMA within 24 hours after final rolling. Neatly cut one 6 inch diameter core sample with a core drill at each location marked by the Engineer.  Use a core extractor to prevent damage to the core.  The Engineer will determine the density of the core samples according to WAQTC FOP for AASHTO T 166/T 275.  Do not core HMA on bridge decks. Backfill and compact voids left by coring with new HMA within 24 hours.  Densities will not be measured at milled edge of existing pavement.

Cores for longitudinal joint density shall be centered on the longitudinal joint at each location the panel completing the joint is cored for mat density acceptance testing.

4.	Retesting.  A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 199 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 401-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

The total asphalt cement price adjustment is the sum of the individual lot price adjustments and will be subtracted under Item 401(6) Asphalt Price Adjustment – Quality.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

HOT MIX ASPHALT

The following method of price adjustment will be applied to each Type of HMA when the contract quantity equals or exceeds 1,500 tons, except as specified in Subsection 401-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for HMA that includes gradation and asphalt cement content.  The second factor is for density.

A lot containing HMA with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing HMA that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject HMA that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected HMA and tested if requested.  If test results are within specification limits, payment will be made for the HMA.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted under Item 401(6) Asphalt Price Adjustment - Quality.  Costs associated with removal and disposal of the rejected HMA are subsidiary to the Hot Mix Asphalt Pay Item.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any size on the gradations test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment.  The density test result for that sublot will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment, however, the gradation and asphalt cement content results for that sublot will be included provided neither is an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment.  The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier.  If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

( x )

The arithmetic mean 	 of the remaining test results is determined:

n

x =

∑x

Where:	∑	= summation of

x 	= individual test value to xn

n 	= total number of test values

(x)

(x)

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation (s) after the outliers have been excluded, is computed:

n∑(x2) – (∑x)2

s =

n(n-1)

Where:	∑(x2)	=	sum of the squares of individual test values.

(∑x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2.  The TV is the specification value specified in the approved JMD. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Weight Limit (PWL) calculations.  The TV for density is 94% of the Maximum Specific Gravity (MSG), the LSL is 92% of MSG and the USL is 98%.

TABLE 401-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV +6.0 |
| 1/2 inch sieve | TV -6.0 | TV +6.0 |
| 3/8 inch sieve | TV -6.0 | TV +6.0 |
| No. 4 sieve | TV -6.0 | TV +6.0 |
| No. 8 sieve | TV -6.0 | TV +6.0 |
| No. 16 sieve | TV -5.0 | TV +5.0 |
| No. 30 sieve | TV -4.0 | TV +4.0 |
| No. 50 sieve | TV -4.0 | TV +4.0 |
| No. 100 sieve | TV -3.0 | TV +3.0 |
| No. 200 sieve1 | TV -2.0 | TV +2.0 |
| Asphalt % | TV -0.4 | TV +0.4 |
| Mat Density % | 92 | 98 |

Note 1.

Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

USL  -  x

QU  =

S

4.	The Upper Quality Index (QU) is computed:

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

x -  LSL

QL  =

S

5.	The Lower Quality Index (QL) is computed:

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined.

See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined.

See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) – 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation and asphalt cement content pay factors from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 401-3 gives the weight factor (f) for each sieve size and asphalt cement content.

TABLE 401-3

WEIGHT FACTORS

| Sieve Size | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1 inch sieve | 4 | - | - |
| 3/4 inch sieve | 4 | 4 | - |
| 1/2 inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Cement Content, % | 40 | 40 | 40 |

The price adjustment will be based on either the CPF  or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

*CPF or DPF, whichever is lower.

PAB = Price Adjustment Base = $ 91.30  per ton

The total Hot Mix Asphalt Price Adjustment is the sum of all price adjustments for each lot and will be adjusted under Item 401(6) Asphalt Price Adjustment – Quality.

ASPHALT CEMENT

Asphalt cement will be randomly sampled and tested in accordance with Subsection 401-4.02.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.

The total asphalt cement price adjustment is the sum of the individual sample price adjustments and will be subtracted under Item 401(6) Asphalt Price Adjustment – Quality.

Table 401-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | > 1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 |  | 301-338 |  |  |  | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | < 0.261 |
| Direct Tension | > 1.0 % | > 1.0 |  | 0.86-0.99 |  |  |  | 0.71-0.85 | 0.56-0.70 | < 0.56 |

Asphalt Cement Price Adjustment for each sample = 5 x PAB x Qty x PRF

PAB 	= Price Adjustment Base

Qty 	= Quantity of asphalt cement represented by asphalt cement sample

PRF 	= Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results and using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor under Item 401(6) Asphalt Price Adjustment - Quality shall pay the cost of testing the referee sample.

The total Asphalt Price Adjustment is the sum of all the price adjustments for each lot and will be included in 401(6) Asphalt Price Adjustment - Quality.

PAVEMENT SMOOTHNESS.

The top layer of HMA will be measured according to 401-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

Smoothness Price Adjustment = PAB x PQ x SF

PAB 	= Price Adjustment Base

PQ 	= Final quantity of HMA, tons

PrI	= Final measured hot mix smoothness, inches/mile

SF 	= Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

The smoothness price adjustment will be applied under Item 401(6) Asphalt Price Adjustment - Quality.

LONGITUDINAL JOINT DENSITY.

Longitudinal joint density price adjustments apply when HMA quantities are equal to or greater than 1,500 tons.  A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted under Item 401(6) Asphalt Price Adjustment - Quality.

b.	Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to Subsection 401-3.14.

2.	If project average joint density is greater than 92% MSG apply the following incentive:

a.	Longitudinal joint density price adjustment equal to $1.50 per linear foot is added under Item 401(6) Asphalt Price Adjustment - Quality.

The longitudinal joint price adjustment will be included in Item 401(6) Asphalt Price Adjustment - Quality.

401-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	There is more than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

b.	There is more than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	As used in this subsection, the Alaska asphalt material price index is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation.  The Alaska asphalt material price index is posted on the Department’s Statewide Materials website, and calculated according to the formula posted there.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP–IB)–(0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB–IPP)–(0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska asphalt material price index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska asphalt material price index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

401-5.01 BASIS OF PAYMENT.

Asphalt cement and anti-strip additives for Item 401(3), Temporary Hot Mix Asphalt, and or for the leveling course/prelevel (rut repair) HMA, is subsidiary to Item 401(3).

Sealing the surface of longitudinal joints according to Subsection 401-3.14 will be subsidiary to 401 Items.

Asphalt cement, anti stripping additives, tack coat, and crack sealing (Subsection 401-3.07) are subsidiary to the associated Hot Mix Asphalt Pay Items, unless specified as individual Pay Items.

Price adjustments, except adjustments included in Subsection 401-4.04 Asphalt Material Price Adjustment – Unit Price, will not apply to:

1.	Leveling course/prelevel (rut repair) HMA

2.	Temporary Hot Mix Asphalt

3.	Approach Hot Mix Asphalt

Payment for furnishing and installing joint adhesive will be paid as 401(9) Longitudinal Joint Adhesive and Sealing.

Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6) Asphalt Price Adjustment – Quality.

The Engineer will assess a fee of $2,500.00 under Item 401(6) Asphalt Price Adjustment - Quality, for each mix design subsequent to the approved Job Mix Design for each Type and Class of Hot Mix Asphalt specified.

Asphalt cement, anti-strip additives for Item 401(8) Hot Mix Asphalt for Approaches is subsidiary to Item 401(8).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1A) 	Hot Mix Asphalt, Type II; Class A	Ton

401(1B) 	Hot Mix Asphalt, Type II; Class B	Ton

401(2) 	Asphalt Cement, Grade PG 52-28	Ton

401(3) 	Temporary Hot Mix Asphalt 	Ton

401(4) 	Hot Mix Asphalt, Type     ; Class     	Square Yard

401(6) 	Asphalt Price Adjustment - Quality	Contingent Sum

401(8)	Hot Mix Asphalt for Approaches, Type __; Class __	Ton

401(9) 	Longitudinal Joint Adhesive and Sealing	Linear Foot

401(10)	Asphalt Material Price Adjustment – Unit Price	Contingent Sum

CR199-010109

SECTION 603

CULVERTS AND STORM DRAINS

Special Provisions

603-1.01 DESCRIPTION.  Add the following:

This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS.  Delete the second paragraph and substitute the following:

When Item 603(17-xx), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP) or Reinforced Concrete Pipe.  Corrugated Polyethylene Pipe is not allowed.  End Sections for Metal Pipe must be of the same material as the pipe.

Add the following:

Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5 inch by 6 foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9 inches.

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty two inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:

Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:

Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

R42 (08/27/03)

603-5.01 BASIS OF PAYMENT.  Add the following:

	Excavation and shaping of material around culvert inlets to allow water to drain is subsidiary to 603 items.

	Pavement removed to install pipes outside of the digout areas will not be measured separately, but will be subsidiary to 603 items.

	Clearing of vegetation for culvert installation will not be measured separately, but will be subsidiary to 603 Items.

SECTION 605

UNDERDRAINS

Special Provisions

605-3.01 PIPE INSTALLATION.  In the fourth paragraph first sentence change 12 inches to 3 inches.

605-4.01 METHOD OF MEASUREMENT. Add the following:

Underdrains installed at culverts intersecting digout areas with porous backfill will not be measured for payment.

605-5.01 BASIS OF PAYMENT.  Add the following:

Underdrains will not be paid for directly, but will be subsidiary to 605(5) item.

SECTION 606

GUARDRAIL

Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers.  Use flexible markers with an overall length of 72 inches.  The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag which provides approximately 20 square inches of surface area.  Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacturer:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval before ordering the markers.

R45 (04/06/06)

606-3.01 GENERAL.  Replace the second sentence of the first paragraph with the following:

Conform to these Specifications and the Standard Drawings with the following exception.  Modify Standard Drawing G-20.10 to only allow an offset of 1.5 feet wide by 37.5 feet long for the ET-Plus.

R266 (05/12/04)

606-3.02 POSTS.  Delete the first two numbered items in this subsection and substitute the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL.  Add the following:

Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 14 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

R45 (04/06/06)

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL.  Delete the last sentence and substitute the following:

Notify the Engineer a minimum of 5 days before removing guardrail for disposal.  The Engineer will notify ADOT&PF M&O (907-338-1466) and have an M&O representative physically identify portions of guardrail to be salvaged.  Deliver guardrail and associated hardware designated for salvage to the ADOT&PF M&O yard located at 35200 Hope Highway, MP 56.7 Seward Highway (Silvertip M&O station).  Remaining items removed becomes the Contractor’s property.

R259 (06/12/03)

Add the following subsections:

606-3.09 FLEXIBLE MARKERS.  For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  The Engineer may determine additional guardrail is necessary and the Contractor shall comply without delay.

R45 (04/06/06)

Special Provisions

606-5.01 BASIS OF PAYMENT.

Item 2.b, replace (ET-2000) with (ET-PLUS)

Payment will be made under:

Pay item 606(11), replace (ET-2000) with (ET-PLUS)

SECTION 611

RIPRAP

Special Provision

611-2.01 MATERIALS.   Add the following after the first sentence:

Apparent specific gravity will be determined by WAQTC FOP for AASHTO T85.

R277 (11/07/05)

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS.  Delete the first paragraph of Item 2, including subitems a., b., c., and replace with:

2.	Sign Fabrication.  Use Type IV reflective sheeting (for lettering symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

For temporary installations the reflective sheeting may be placed on aluminum, plastic, or plywood sheet panels.

For flexible signs (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports:  Use white Type VIII or Type IX reflective sheeting for background of sign and strips.

c.	Non-Illuminated Overhead Signs with White Legends on Green Backgrounds:  Use Type IX reflective sheeting for legends and background.  Create the legend in one of the following ways:

(1)	Cut border and legend from white Type IX reflective sheeting and adhere to a green Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

d.	Fluorescent Yellow-Green School Area Signs:  Use Type VIII or Type IX reflective sheeting for background.

Reflective Sheeting Warranty.  Supply manufacturer’s warranty for reflective sheeting including retention of fluorescent yellow-green (measured according to ASTM E 2301) for ten years according to the following criteria:

Minimum Fluorescent Luminance Factor		YF:  20%

Minimum Total Luminance Factor			YT:  35%

The warranty shall stipulate:  If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

R615 (06/20/08)

Special Provision

615-3.01 CONSTRUCTION REQUIREMENTS.  Replace the sixth sentence in item 7 with the following:

Deliver sign panels, posts, and hardware to the Silvertip Maintenance Yard.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following:

Do not remove existing signs without authorization from the Engineer.  Do not remove the following sign types: Avalanche Warning, Adopt-A-Highway, Memorial and Milepost signs.

615-5.01 BASIS OF PAYMENT. Delete the first sentence and substitute the following:

Sign posts, bases, mounting hardware, and concrete used for sign bases are subsidiary.

Add the following:

No separate payment for keeping existing signs in service until no longer needed or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1) Standard Sign.

No separate payment for removal of existing sign post foundations or work required to abandon in place shall be made, but shall be subsidiary to Item 615(1) Standard Sign.

If necessary to remove signs that are to remain in place due to construction activities, remove and replace sign in same location.  This work will be subsidiary to 615(1) and no separate payment will be made.

SECTION 616

THAW PIPE AND THAW WIRES

Standard Modifications

616-2.01 THAW PIPE.  Second sentence delete:  “and Fittings”

Add the following sentence:

Fittings 	ASTM A234 galvanized according to AASHTO M 111.

E14 (06/30/04)

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION.  Add the following:

***Deleted*** Seed new or disturbed slopes and other areas directed by the Engineer.  Track the soil and apply seed, mulch, fertilizer, and water.  Provide a living ground cover on slopes as soon as possible.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Mulch			Subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following:

Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes.

Standard Modification

618-3.01 SOIL PREPARATION.  Delete the fourth paragraph and replace with the following:

Roughen the surface to be seeded by grooving the soil in a uniform pattern that is perpendicular to the fall of the slope.  Use one or more of the following grooving methods before the application of seed:

- Manual raking with landscaping rakes;

- Mechanical track walking with track equipment; or

- Mechanical raking with a scarifying slope board.  Form one inch wide grooves spaced no more than six inches apart.

Rounding the top and bottom of slopes to facilitate tracking or raking and to create a pleasant appearance is acceptable, but disrupting drainage flow lines is not.

618-3.02 SEEDING SEASONS.  Add the following:

Seed disturbed areas that require seeding within 14 days of the permanent cessation of ground disturbing activities in that area.

Seed between May 15 and August 15, or obtain written approval from the Engineer to seed at a different date.

618-3.03 APPLICATION.  Delete the first three sentences and replace with:

Apply seed mix, fertilizer, and mulch (if required) at the rate specified in the Special Provisions.  If no seed mix, seed mix application rate, or fertilizer rate are specified in the special provisions, use the recommendations of the Alaska Department of Natural Resources (ADNR) and the Revegetation Manual for Alaska.

Do not seed areas of bedrock, plant beds, and areas indicated on the plans as “no seeding.”

Water and fertilizer required for application are subsidiary to the Seeding bid item.

E42 (01/27/07)

Special Provisions

618-3.03 APPLICATION.  Add the following:

Apply seed, mulch, and fertilizer as follows.  Apply seed and mulch in one application if using the hydraulic method.  Apply fertilizer with the hydraulic method.

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
| Soil Stabilizer Slope ≤ 3:1 Slope >3:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

Standard Modification

Delete subsection 618-3.04 in its entirety, and add the following new subsections:

618-3.04 MAINTENANCE AND WATERING.  Protect seeded areas against traffic by approved warning signs or barricades. Repair surfaces gullied or otherwise damaged following seeding.  Maintain seeded areas in a satisfactory condition until final acceptance of work.

Water and maintain seeded areas.  Water applied by this subsection is a paid Contract item.  If, in the opinion of the Engineer, too much water is being applied, reduce amount of water as directed.

Reseed areas not showing evidence of satisfactory growth within 3 weeks of seeding.  Bare patches of soil more than 10 square feet in area must be reseeded.  Erosion gullies over 4 inches deep must be filled and reseeded.  Fill the entire erosion gully to surrounding grade, even the portions less than 4 inches deep.

Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.  The Contractor is responsible for retracking, reseeding, refertilizing and remulching areas that do not show satisfactory growth, and those actions are subsidiary.

618-3.05 ACCEPTANCE.  During final inspection the Engineer will perform a visual inspection of seeding to determine final stabilization.  During the visual inspection each station and each side of the road will be considered a separate area.  The Engineer will accept seeding that has become a vegetative matt with 70% cover density in the inspection area.

Reseed areas that are not acceptable to the Engineer.

618-3.06 PERIOD OF ESTABLISHMENT.  Establishment periods extend for one complete growing season following acceptable seeding.  Employ possible means to preserve the new vegetative matt in a healthy and vigorous condition to ensure successful establishment.  Reseed areas that do not meet the specifications.  Watering and reseeding after the final inspection are subsidiary.

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance.  After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance in accordance with subsection 105-1.16.

618-4.01 METHOD OF MEASUREMENT.

After Seeding by the Pound, delete text and replace with:

By the weight of dry seed acceptably seeded and maintained.

618-5.01 BASIS OF PAYMENT.  Delete paragraphs beginning: “Seeding by the Acre” and “Seeding by the Pound” and replace with:

Seeding by the Acre.  Payment is for established vegetative matt.  Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Seeding by the Pound.  Payment is for established vegetative matt.  Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Add new pay description:

Water for Seeding. Water applied for growth of vegetative matt.  Water for hydraulic seeding, fertilizing or mulching is subsidiary.  Water after project completion is subsidiary.

E42 (01/27/07)

SECTION 619

SOIL STABILIZATION

Special Provisions

619-2.01 MATERIALS.  Replace matting requirement with the following:

Matting:	Subsection 727-2.02 Item 4.

Special Provisions

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

639-1.01 DESCRIPTION.  Construct approaches at their existing locations as shown in the Plans.

639-2.01 MATERIALS.  Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION.  Construct approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT.  By the number of approaches constructed as shown on the Plans or as directed.  Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule.  The contract unit price approaches shall be full compensation for furnishing  equipment and labor necessary to complete the work as specified.

Materials required to construct approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

639(6)	Approach 	Each

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modification

640-1.01 DESCRIPTION.  Add the following:

6.	Comply with the Alaska Department of Labor and Workforce Development (DOLWD) requirements for Worker Meals and Lodging, or Per Diem; as described in their July 25, 2005 memo WHPL #197 (A2) and the State Laborer’s and Mechanic’s Minimum Rates of Pay (current issue).

Ensure subcontractors comply with the DOLWD requirements.

Ensure facilities meet the Alaska Administrative Code 8 AAC 61.1010 and 8 AAC 61.1040 Occupational Safety and Health Standards, 18 AAC 31 Alaska Food Code, and U. S. Code of Federal Regulations 29 CFR Section 1910.142 Temporary Labor Camps.

Do not consider the cost of Meals and Lodging, or Per Diem in setting wages for the worker or in meeting wage requirements under AS 23.10.065 or AS 36.05.

640-4.01 METHOD OF MEASUREMENT.  Delete the numbered paragraph 3 and substitute the following:

3.	The remaining balance of the amount bid for Mobilization and Demobilization will be paid after all submittals required under the Contract are received and approved.

Add the following:

4.	Progress payments for Worker Meals and Lodging, or Per Diem will be computed as equivalent to the percentage, rounded to the nearest whole percent, of the original contract amount earned.

640-5.01 BASIS OF PAYMENT.  Add the following pay item:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

640(4)	Worker Meals and Lodging, or Per Diem 	Lump Sum

E27 (01/01/06)

Special Provisions

Delete Section 641 and replace with the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION.

Provide project administration and construction activities to control erosion, sedimentation, and pollution from the Project, according to this section and applicable local, state, and federal requirements.

Utilities.  Utilities will be relocated by others concurrently with construction of this project.  A utility company performing ground disturbing activity on the project shall be identified in the SWPPP.  The Contractor will be responsible for controlling sediment and erosion and stabilizing areas disturbed during underground utility relocation.

641-1.02 DEFINITIONS.

These definitions apply only to Section 641.

- Alaska Certified Erosion and Sediment Control Lead (AK-CESCL). Certification demonstrating the person has completed training, testing, and other requirements recognized by the Department to satisfy the Environmental Protection Agency (EPA) National Pollution Discharge Elimination System (NPDES) Construction General Permit (CGP) requirement for “qualified personnel.”  AK-CESCL certificates issued in conformance with, and under the authority of the AK-CESCL Memorandum of Understanding are recognized by the Department as meeting this standard.  Certifications published on the Department’s Construction website under the title “AK-CESCL Equivalent Certifications” will also be recognized.  Other certifications may be approved by the Engineer on a case-by-case basis.

- Area of Land Disturbance.  The area of land (soil) that will be disturbed by a construction activity including, but not limited to, clearing, grubbing, excavating, constructing embankment, grading, stockpiling erodible material, or processing material.  Area of pavement removal is not included if the pavement removal work does not remove the aggregate underlying the pavement.

- Best Management Practices (BMPs).  Devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices. BMPs include temporary or permanent structural and non-structural devices. BMPs when used alone or in combination, minimize erosion or contain sediment within the Project, and reduce the discharge of pollutants.

- Clean Water Act (CWA).  United States Federal Water Pollution Control Act (33 U.S.C. 1251 et seq.)

- Construction Activity. Physical activity by the Contractor or any Subcontractor or Utility Company within the Project that may result in land disturbance. Construction Activity includes, but is not limited to, installation and maintenance of BMPs, clearing, grading and excavating.

- Construction General Permit (CGP). The Storm Water Construction General Permit for Discharges from Large and Small Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES).

- Electronic Notice of Intent (eNOI). The Electronic Notice of Intent submitted to EPA, to begin Construction Activity under the CGP.

- Electronic Notice of Termination (eNOT). The Electronic Notice of Termination submitted to EPA, to end coverage under the CGP.

- Erosion and Sediment Control Plan (ESCP). A project-specific document developed by the Department to identify general information about the Project.  The ESCP may include measures to minimize erosion and contain sediment within the Project site.  The ESCP provides general information for the Contractor’s use in development of the Project SWPPP.

- Final Stabilization. Final stabilization occurs when soil disturbing activities at the site have been completed and one of the following methods, as identified in the contract, has been completed: (a) establish a uniform and evenly distributed perennial vegetative cover with a density of 70 percent of the native background vegetative cover, or (b) construct non-erodible permanent stabilization measures (such as riprap, gabions, geotextiles, pavement, and crushed aggregate base course) where vegetative cover is not required.

- Haul Route.  Existing or newly constructed road where construction materials are transported and where disposition of sediments or erodible materials may result from the material hauling activity or from the Contractor’s activity to construct or maintain the road.

- Hazardous Material Control Plan (HMCP). The Contractor's project specific detailed plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material, including but not limited to, petroleum products related to construction activities and equipment.  The HMCP is integrated into the SWPPP.

- Joint Inspection.  SWPPP inspection performed by the SWPPP Manager or SWPPP Manager’s Representative, and the Engineer or Engineer’s representative.  Joint Inspection is performed together, as a collaborative effort of the Contractor and the Department.

- Operator.  The party associated with a construction project, staging area, material site, material processing site, disposal site, or haul route, with either:

- operational control of the plans and specifications, including ability to make modification to those plans and specifications

- day-to-day operational control (e.g. authorized to direct workers or equipment operations) of activities related to the project, staging area, haul route, or material or disposal site.

- Pollutant. As defined in 40 CFR 122.2 (a partial listing of this definition includes solid waste, sewage, garbage, chemical wastes, dredged spoil, rock, sand).

- Project.  The physical limits of the construction site, project staging areas, haul routes, and material and disposal sites directly related to the Contract.  Contractor or Commercial Operator furnished material sites, material processing sites, disposal sites, haul routes, staging, and equipment storage areas are not included in the Project.

- Spill Prevention, Control and Countermeasure Plan (SPCC). The Contractor’s project specific detailed plan for petroleum spill prevention and control measures that meets the requirements of 40 CFR 112.

- Storm Water Pollution Prevention Plan (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project site, and to prevent discharge of pollutants that exceed applicable water quality standards as required by the CGP.

- SWPPP Amendment.   A revision or document that adds to, deletes from, or modifies the SWPPP.

- SWPPP Manager.   The Contractor’s qualified representative, as defined in 641-1.04, delegated responsibility for implementing the SWPPP, updating the SWPPP, performing and certifying inspections, supervising Section 641 work, monitoring construction activities, and with authority to suspend work and implement corrective actions.

- SWPPP Manager’s Representative.   The Contractor’s qualified representative, as defined in 641-1.04, who may be delegated certain SWPPP Manager’s tasks and authorities.

- SWPPP Preparer.  The Contractor’s representative who is responsible for designing the initial SWPPP.

- SWPPP Subcontractor Coordinator. The Subcontractor’s representative with authority to direct the Subcontractor’s work, and who is responsible for coordination with the SWPPP Manager and for the Subcontractor’s compliance with the SWPPP.

- SWPPP Template. EPA’s template for the Contractor’s use in preparing the SWPPP where EPA is the NPDES permitting authority (Alaska).  The template is available online at EPA’s website.  Select “SWPPP Template – Unauthorized States.”

- Temporary Stabilization. The protection of exposed soils (disturbed land) from wind and water erosion during the construction process until final stabilization occurs.

641-1.03 SUBMITTALS.

Submission deadlines in this section supersede Subsection 108-1.03.

- All Projects:

- HMCP.  Submit three copies of the HMCP as an appendix to the SWPPP, and in accordance with the requirements for submitting the SWPPP.

- SPCC. Submit three signed copies of the SPCC (if required under Subsection 641-2.03) to the Engineer. Deliver these documents to the Engineer at least 21 calendar days before beginning Construction Activity.

The Department will keep the SPCC as a record document, and reserves the right to review it and require modifications.

- SWPPP. Submit three signed copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 calendar days before beginning Construction Activity.

The Department will review the SWPPP submittals within 14 calendar days after they are received. Submittals will be returned to the Contractor, and marked as either requiring modification or as approved by the Department.

- Beginning Construction Activity. On projects that disturb one acre or more of land, submit your eNOI to EPA and submit a copy of your eNOI to the Engineer at the same time. The Department will submit the Department’s eNOI to the EPA. Allow adequate time for state and federal processing of both eNOIs, and for the EPA to list both eNOIs as active status, before beginning Construction Activity.  The Contractor and the Engineer must sign and certify the approved SWPPP according to the CGP requirements, as detailed in Appendix G of the CGP, before the Contractor submits their eNOI to EPA. The certification statement cannot be amended or edited.

- Ending CGP Coverage.  On projects that disturb one acre or more of land, within 30 days after the Engineer has determined you may end SWPPP activities according to Subsection 641-3.01(5), submit your eNOT to EPA and send a copy of the eNOT to the Engineer. Within 30 days of the Engineer’s determination, the Department will submit the Department’s eNOT to the EPA, and will terminate the CGP coverage.

- Projects that disturb five acres or more of land:

Submit a copy of the Engineer-approved, signed and certified SWPPP, and copies of the Contractor’s eNOI and the Department’s eNOI, with the required permit fee to the Alaska Department of Environmental Conservation (ADEC) Storm Water Coordinator.  Transmit a copy of the ADEC SWPPP Review Letter to the Engineer.  Amend the SWPPP as needed to address ADEC review comments.

641-1.04 PERSONNEL QUALIFICATIONS.

Include qualifications of the SWPPP Preparer, SWPPP Manager, and SWPPP Manager’s Representatives in the SWPPP.

The SWPPP Preparer must meet at least one of the following qualifications:

- current certification as a Certified Professional in Erosion and Sediment Control (CPESC)

- current certification as Alaska Certified Erosion and Sediment Control Lead (AK-CESCL) and at least three years experience in erosion and sediment control (provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement)

- Professional Engineer registered in the State of Alaska

The SWPPP Manager must meet all the following qualifications:

- current certification as Alaska Certified Erosion and Sediment Control Lead (AK-CESCL)

- duly authorized representative, as defined in the CGP, Appendix G

The SWPPP Manager’s Representative must hold a current AK-CESCL certification.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

The eNOI and eNOT must be signed and certified by a responsible corporate officer, in accordance with CGP Appendix G, Section 11.  Signature and certification authority for the eNOI and eNOT cannot be delegated.

Delegate signature and certification authority, exclusive of the eNOI and eNOT, to the SWPPP Manager, in accordance with CGP Appendix G, Section 11.B, for the SWPPP, SWPPP amendments, SWPPP inspections, and other related CGP documents.  Include the certification statement verbatim from CGP Appendix G, Section 11.D, on the written delegation.  Delegation is not required if the SWPPP Manager is a responsible corporate officer for Contractor, as defined in CGP Appendix G, Section 11.A.  Include a copy of the written delegation in the SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

Develop the SWPPP and all associated documents, in accordance with the requirements of the CGP.

The construction site including all areas of utility relocation and all Department furnished material sources, disposal sites, haul routes, staging, and equipment storage areas must be included in the Project eNOI and must be covered in the Project SWPPP.  The Department and the Contractor are both operators for these areas.

The Department is not an operator for Contractor furnished:

- material sites

- material processing sites

- disposal sites

- haul routes

- staging areas

- equipment storage areas

Compliance with NPDES and other applicable federal, state, and local requirements, and securing all necessary clearances, rights, and permits for these Contractor furnished sites and areas are the sole responsibility of the Contractor.  Document the name of each operator, and the locations of these areas in the Project SWPPP.

The Department is not an operator for commercially operated:

- material sites

- material processing sites

- disposal sites

- haul routes

- staging areas

- equipment storage areas

Compliance with NPDES and other applicable federal, state, and local requirements, and securing all necessary clearances, rights, and permits for these commercially operated sites and areas are the sole responsibility of the commercial operator.  Document the name of each operator, and the locations of these areas in the Project SWPPP.

Use the Department’s ESCP as a starting point for designing the SWPPP.  The approved SWPPP replaces the ESCP.  Develop the SWPPP in accordance with EPA’s template for Unauthorized States. Incorporate and cite applicable requirements of the project permits and environmental commitments into the SWPPP.  Use the Department’s documentation of consultation with the State Historic Preservation Officer and federal agencies for consideration of historic properties and endangered species.  Make additional consultations as necessary for Contractor specific activities, changes to the project footprint, and changes to the construction timeline.

The initial SWPPP may be designed and submitted before the SWPPP Preparer visits the Project but Construction Activity is not permitted until the SWPPP Preparer has visited the Project.  Use the results of the Project visit in the design of the initial SWPPP, or if the visit occurs after the initial SWPPP has been submitted to the Engineer, to amend the SWPPP as necessary before beginning Construction Activity.   Consider opportunities to adjust phasing to minimize potential for erosion.  Consider appropriate selection, application, and sequencing of BMPs.  Consider sequence of BMP installations in relation to progress schedule.

The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed. Describe site specific BMPs, source controls, sediment controls, discharge points, and a plan including schedule and implementation procedures for temporary and final stabilization.  Describe all temporary and permanent stabilization measures.  Include typical installation drawings for all BMPs that will be incorporated in the Project.  Include the Contractor’s progress schedule in the SWPPP.  The plan must include both erosion control and sediment control measures.  The plan must address first preventing erosion, then minimizing erosion, and finally trapping sediment before it leaves the project site.

The SWPPP must provide erosion and sediment control, in accordance with the CGP and this specification, for all land disturbances resulting from the Contractor, all Subcontractors and utility company activities during the course of the contract.  The SWPPP must  consider the activities of utility companies performing work on the Project.  The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, and  the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity within the Project, and identify the areas over which each operator has operational control.

Specify the line of authority and designate a SWPPP Manager for implementing SWPPP compliance.  Provide 24 hour contact information for the SWPPP Manager, and for each SWPPP Manager’s Representative.  The SWPPP Manager and each SWPPP Manager’s Representative must have 24 hour contact information for all SWPPP Subcontractor Coordinators.

The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, inspection reports, records of land disturbance and stabilization, and any other documents necessary to satisfy the requirements of the CGP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.

Prepare a project specific HMCP for prevention of pollution from storage, use, containment, cleanup, and disposal of hazardous material, including oil products related to construction activities and equipment (See 40 CFR 117 and 302 for listing of hazardous materials).  Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

List the types and approximate quantities of response equipment and cleanup materials available on site. Include a list and location map of cleanup materials, at each different work site and readily available off site (main site, material site, batch plant, storage yard, explosives dump, equipment or fueling yard, etc). Vehicles and other mobile equipment must carry oil absorbent pads.

Specify the line of authority and designate a Contractor field representative for spill response, and one coordinator from each subcontractor. Provide 24 hour contact information for the Contractor’s field representative.  The Contractor’s field representative must have 24 hour contact information for the coordinator from each subcontractor.

List and give the location and estimated quantities of hazardous materials, including office materials, to be used or stored on site.  Store hazardous materials in covered storage areas.  Include secondary containment for all hazardous material storage areas.

Identify the locations where storage, fueling and maintenance activities will take place, describe the maintenance activities, and list controls to prevent the accidental spillage of oil, petroleum products, and other hazardous materials. Store spill response materials, appropriate to the hazards associated with that site, in sufficient quantity at each identified location.

Detail procedures for containment and cleanup of hazardous substances.  Detail a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by accidental spills.  Detail a plan for dealing with unexpected contaminated soil and water encountered during construction.

Detail methods of disposing of waste petroleum products and other hazardous materials generated by the Project.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Include the HMCP as an appendix to the SWPPP.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC) REQUIREMENTS.

Prepare and implement a project specific SPCC when required by 40 CFR 112, including when both of the following conditions are present on the Project:

- oil or petroleum products from a spill may reach navigable waters, and

- total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Develop the SPCC and all associated documents, in accordance with the requirements of the 40 CFR 112 and include the following in your SPCC:

- Operating procedures that prevent oil spills

- Control measures installed to prevent a spill from reaching navigable waters

- Countermeasures to contain, clean up, and mitigate the effects of an oil spill

You may self-certify the SPCC if the total above ground oil storage capacity is 10,000 gallons or less, and you meet all the requirements for self-certification in 40 CFR 112. Otherwise the SPCC must be certified by, stamped with the seal of, dated by, and signed by a Professional Engineer registered in the State of Alaska.

Reference the SPCC in the SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF SWPPP MANAGER AND SWPPP MANAGER’S REPRESENTATIVE.

The SWPPP Manager is responsible for work related to this section. The SWPPP Manager is responsible for the Contractor’s compliance with the CGP and CWA, and to assure the Contractor’s Construction Activity does not result in discharge of pollutants that exceed applicable water quality standards.

The SWPPP Manager shall sign and certify inspection reports, and update the SWPPP.  The SWPPP manager may not delegate these tasks.

The SWPPP Manager may assign the SWPPP Manager’s Representative responsibility to perform SWPPP inspections, direct or oversee installation, maintenance, and removal of BMPs as detailed in the SWPPP or as directed by the Engineer.  The SWPPP Manager and the SWPPP Manager’s Representative shall be knowledgeable in the requirements of this section, the SWPPP, the BMPs, the CGP, the permits, and the environmental commitments identified in the contract.  The SWPPP inspections must be performed by either the SWPPP Manager or the SWPPP Manager’s Representative.

The SWPPP Manager and the SWPPP Manager’s Representative shall have the Contractor’s complete authority to suspend construction activities that do not conform to the SWPPP or CGP.

Report CGP noncompliance which may endanger health or the environment to the EPA. Information must be provided orally within 24 hours from the time you become aware of the circumstances. Submit written notice as described in the Appendix G, Standard Permit Conditions, #12 Reporting Requirements of the CGP.

641-2.05 MATERIALS.

Comply with the material requirements described in the Specifications.

Use materials suitable to withstand hydraulic and soil forces, and to control erosion and trap sediments in accordance with the requirements of the CGP.

641-3.01 CONSTRUCTION REQUIREMENTS.

Comply with the requirements of the CGP.

1.	Starting Construction:

- Do not begin Construction Activity until authorized by the Engineer

- On projects that disturb one acre or more of land, do not begin Construction Activity until the Project eNOI for the Department and for the Contractor are both listed as Active Status on the EPA website

- Do not begin Construction Activity until the SWPPP preparer has visited the Project and the date of the visit and the persons conducting the visit have been documented in the SWPPP.

Post notices on the outside wall of the project office, and at publicly accessible locations near the beginning and end of the Project. Protect postings from the weather and locate so the public can read them without obstructing construction activities (for example, at an existing pullout).  Include the following information in each of the postings:

- Copy of all eNOIs related to this project

- Name and phone number of SWPPP Manager

- Location of the SWPPP available for public viewing.

Keep the updated SWPPP, HMCP and SPCC at the on-site project office. If there isn’t an on-site project office, keep the information at a location suitable to the Engineer.

Install an outdoor rain gauge in a readily accessible location on the Project.

Ensure all subcontractors and utility companies operating within the Project understand and comply with the SWPPP.

Install sediment controls in accordance with the SWPPP and SWPPP sequencing and phasing, and before beginning Construction Activity that may result in land disturbance.

2.	During Construction:

Comply with requirements of the HMCP and SPCC, and all state and federal regulations that pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of discharges of petroleum products and other hazardous materials.  Perform fueling operations in a safe and environmentally responsible manner.  Place absorbent pads under fill ports while fueling, and under equipment during maintenance or repairs.  Install secondary containment under all stationary equipment that contains petroleum products.

Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.  Report petroleum product spills as required by federal, state and local law, and as described in the HMCP and SPCC.

Comply with the requirements of the SWPPP.  Implement temporary and permanent erosion and sediment control measures identified in the SWPPP. Keep the SWPPP current.  If storm water discharges threaten water quality, take immediate action. Comply with the requirements of 18 AAC 70 State of Alaska Water Quality Standards, AS 41.14.870 Protection of Fish and Game, 11 AAC 112 Alaska Coastal Management Program, Section 404 of the CWA, and all other applicable federal, state, and local statutes and regulations.

Coordinate with subcontractors and utility companies doing work in the project area so BMPs, and temporary and permanent stabilization are installed, maintained, and protected from damage.

3.	Corrective Action and Maintenance of BMPs:

Maintain temporary and permanent erosion and sediment control measures in effective operating condition.   Remove sediment and debris from sediment traps, silt fences, and sediment ponds before sediment or debris accumulates to 50% of the BMP’s design capacity.

Implement corrective action:

- if an incident of non-compliance with the SWPPP, CGP, or CWA is identified

- if an inspection identifies the SWPPP or any part of the SWPPP is ineffective in preventing the discharge of pollutants that exceed applicable water quality standards

- if the Project Engineer determines the SWPPP or any part of the SWPPP is ineffective in preventing the discharge of pollutants that exceed applicable water quality standards

- if any BMP is damaged, undercut, or unable to effectively perform the intended function

- if any BMP is at or exceeding 50% of its design storage capacity

- whenever there is a change in conditions, design, construction, operation, or maintenance that could have a significant effect on the discharge of pollutants in storm water leaving the Project

Implement corrective actions as soon as possible, and before the next storm event whenever practicable.  If implementation before the next storm event is impracticable, the situation must be documented in the SWPPP and alternative BMPs must be implemented as soon as possible.

4.	Stabilization.

Stabilization may be accomplished using temporary or permanent measures.  Initiate stabilization of disturbed areas, stockpiles, and of erodible aggregate layers so that all of the following conditions are satisfied:

- as soon as practicable

- as soon as necessary to avoid discharge of pollutants that exceed applicable water quality standards

- as identified in the SWPPP schedule and/or phasing

- in accordance with stabilization schedule requirements of applicable project permits

- no later than 14 days after each cessation of land-disturbing activities.

Land may be disturbed multiple times during a project. Coordinate work to minimize area of land disturbance as much as practicable. Do not disturb more area than you can stabilize in the time limits specified, and with the resources available.

Before deactivating a stream bypass or stream diversion install stabilization up to ordinary high water:

	drainage structure – at the inlet and outlet

	bridge – at the upstream and downstream sides and between/below

	drainage structure, bridge – in the area upstream or downstream disturbed during construction

Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install stabilization up to ordinary high water:

- at the inlet and outlet of the culvert, drainage structure, or bridge

- in the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge

- under the bridge

When installing a culvert or other drainage structure where stream bypass is not used for construction, temporary or permanent stabilization may need to be installed concurrently or immediately after placing the culvert or drainage structure in order to comply with applicable project permits and to prevent discharge of pollutants that exceed applicable water quality standards.  Install temporary or permanent stabilization:

- at the culvert or drainage structure inlet and outlet

- in the area upstream and downstream of the culvert or drainage structure, that is disturbed in the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure

Prevent project contaminates from entering all bodies of water (flowing and not flowing) on and off the project site, during all phases of construction (from “the effective date of the Notice to Proceed,” Section 108-1.02 to the issue of the “Letter of Final Acceptance,” Section 105-1.16) in conformance with the project requirements.  Maintain project water quality as specified in the Plans and Specifications (including Special Provisions).  Including, but not limited to, construction/installation of drainage structures providing erosion, sediment and pollution control measures, including stabilization, at the drainage structure inlet and outlet and up/down stream from the structure.

5.	Ending SWPPP Activities and SWPPP Maintenance

The Engineer will determine SWPPP activities have ended when all of the following requirements are met:

- Land disturbing activities have ceased

- The Project site (including material sources, disposal sites, etc.) has achieved final stabilization

- Temporary BMPs have been removed

Submit eNOT in accordance with Subsection 641-1.03(1)E.

6.	Record Retention.

Transmit one copy of the final SWPPP, including all amendments and appendixes, to the Engineer when the eNOT is filed.

Retain copies of the SWPPP, including all amendments and appendixes, and other records required by the CGP, for at least three years after the date of eNOT.  If EPA issues a Notice of Violation (NOV) or begins investigation for a potential NOV before the three year retention period expires, retain the SWPPP and all records related to the SWPPP and CGP until EPA has determined all issues related to the NOV are settled.

641-3.02 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.

Perform inspections, prepare inspection reports, and prepare SWPPP amendments in compliance with the SWPPP and the CGP. The SWPPP of record is the SWPPP maintained by the Contractor.

1.	Before Starting Construction.

Before beginning Construction Activity, conduct a Joint Inspection of the Project.  Include the SWPPP Preparer in the inspection and consider any necessary revisions to the draft SWPPP, or if the SWPPP has already been approved, any necessary amendments to the SWPPP.  Consider opportunities to adjust phasing to minimize potential for erosion.  Consider appropriate selection, application, and sequencing of BMPs.  Consider sequence of BMP installations in relation to progress schedule.  Identify sediment controls that need to be installed prior to commencing other Construction Activity.

2.	During Construction.

Conduct Joint Inspections on one of the following schedules:

- at least once every seven days during construction, or

- at least once every 14 days during construction and within 24 hours of the end of a storm event of 1/2 inch or greater rainfall in a 24 hour period (1/2 inch rainfall as recorded at the project site rain gauge)

Indicate the inspection schedule in the SWPPP and conduct Joint Inspections in accordance with the selected schedule. At least once each month include the SWPPP Preparer in the joint inspection.

3.	Before Seasonal Suspension of Work.

Conduct Joint Inspection before seasonal suspension of work to review condition and applicability of BMPs and SWPPP.  Confirm SWPPP, temporary stabilization, and BMPs are installed and functioning in accordance with the requirements of Subsection 641-3.01.

4.	During Winter Work.

Conduct Joint Inspections in accordance with the inspection schedule indicated in the approved SWPPP.  Inspection frequency during winter work may be reduced to at least one inspection every month if all of the following requirements are met:

- runoff is unlikely due to winter conditions (e.g. the site is covered with snow, ice or the ground is frozen)

- approval from the Engineer

- the revised inspection frequency is documented as an amendment to the SWPPP.

5.	During Seasonal Suspension of Work.

Conduct Joint Inspections in accordance with the inspection schedule indicated in the approved SWPPP.  Inspection frequency during seasonal suspension of work may be reduced to at least one inspection every month if approved by the Engineer and the revised inspection frequency is documented as an amendment to the SWPPP, and either of the following requirements is met:

- the entire site is temporarily stabilized

- runoff is unlikely due to winter conditions (e.g. the site is covered with snow, ice or the ground is frozen)

The Engineer may waive winter monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

- below-freezing conditions are anticipated to continue for more than one month (Include historical weather data in the SWPPP justifying assumptions)

- land disturbance activities have been suspended

- beginning and ending dates of the waiver period are documented as an amendment to the SWPPP.

6.	Project Completion.

Conduct Joint Inspection to ensure final stabilization is complete throughout the Project and all temporary BMPs are removed.

7.	Items and Areas to Inspect.

Inspect all areas covered under the Project eNOI and included in the SWPPP.

When included in the SWPPP, inspect the following:

- Disturbed areas that have not been finally stabilized

- Areas used for storage of erodible materials that are exposed to precipitation

- BMPs

- Perimeter sediment control and discharge locations

- Staging and Equipment storage areas

- Petroleum storage, handling and fueling sites

- Hazardous material storage sites

- Locations where vehicles or construction equipment enter or exit Project

- Material sources and disposal sites

- Discharge locations

Areas referenced in the Project SWPPP that are Contractor furnished, or commercially furnished, and the Department is not an operator, do not require Joint Inspection in accordance with this contract.  These areas should have their own SWPPP and eNOI. The Contractor or commercial operator is solely responsible for inspecting and assuring compliance with all NPDES requirements, and any other federal, state, or local requirements and the Project SWPPP shall include a statement to that effect.

8.	Inspection Reports.

Use the Department’s SWPPP Construction Inspection Report, Form 25D-100 to record SWPPP inspections.

Record applicable data including the following:

- inspection date, general information, type of inspection

- names, titles and qualifications of personnel inspecting

- weather information for the period since the last inspection, including storm events and any discharges that occurred during this period

- current weather information and a description of any discharges currently occurring

- location of discharges of sediment or other pollutants from the site

- locations of BMPs where maintenance is necessary

- locations of BMPs that failed to operate as designed or proved inadequate for a particular location

- locations where additional BMPs are needed that did not exist at the time of inspection

- corrective action required including any changes to the SWPPP necessary and implementation dates

- overall site issues

- whether construction site is in compliance with SWPPP and the CGP

- signatures and certifications by the SWPPP Manager and Engineer

The SWPPP Manager must sign and certify the inspection report on the day of the inspection, and must provide the report to the Engineer within 24 hours.  The Engineer will sign and certify the inspection report within three working days and will return the original to the Contractor.

9.	Amending the SWPPP.

The SWPPP Manager shall amend the SWPPP:

- whenever there is a change in design, construction operation, or maintenance at the construction site that has or could have significant effect on the discharge of pollutants that has not been previously addressed in the SWPPP

- if a Joint Inspection identifies the SWPPP or any portion of the SWPPP is ineffective in preventing the discharge of pollutants from the Project, that exceed applicable water quality standards

- if the Project Engineer determines the SWPPP or any portion of the SWPPP is ineffective in preventing the discharge of pollutants from the Project, that exceed applicable water quality standards

- whenever an inspection identifies a problem that requires additional or modified BMPs

Amend the SWPPP as soon as practicable after any change or modification, but in no case, later than seven (7) calendar days following an inspection.  Include the following information when documenting modifications to the SWPPP:

- date the action was completed

- initials of person documenting the action

- description of the action

Update the SWPPP drawings including date, location, action taken, and initials of the person recording the action for:

- installation of BMP

- modification of BMP

- removal of BMP

Give draft SWPPP Amendments to the Engineer for review and approval.  Use the Department’s Form 25D-114, SWPPP Amendment Log, to track all amendments to the SWPPP.  Keep the form current and submit a copy to the Engineer, including copies of any documents amending the SWPPP, prior to performing each scheduled SWPPP inspection.  Include the current SWPPP Amendment Log as an appendix to the SWPPP.

10.	Corrective Action Log.

Use the Department’s SWPPP Corrective Action Log, Form 25D-112, to record corrective actions to the SWPPP and to BMPs.  Preventative and routine maintenance performed to preserve effective function of BMPs or the SWPPP do not require documentation.  Action required to restore effective function of  BMPs or the SWPPP is corrective action and must be documented on Form 25D-112.

After each inspection report has been signed and certified by the SWPPP Manager, update the corrective action log to include all corrective actions noted on the inspection report.  After the corrective action has been accomplished, note action taken, the date, and the initials of the person documenting the action on the log.  Keep the corrective action log current and submit a copy to the Engineer prior to performing each scheduled SWPPP inspection.  Keep the corrective action log as an appendix to the SWPPP.

11.	SWPPP Grading and Stabilization Log.

Use the Department’s SWPPP Grading and Stabilization Activities Log, Form 25D-110, to record land disturbance and stabilization activities.  Keep the grading and stabilization activities log current and submit a copy to the Engineer prior to performing each scheduled SWPPP inspection.  The Engineer may waive requirements to update and submit the log during Seasonal Suspension of the Work.  Resume recording land disturbance and stabilization activities, and submission to the Engineer when Construction Activity resumes.  Keep the grading and stabilization activities log as an appendix to the SWPPP.

12.	Daily Weather Records.

Use the Department’s SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and submit one copy to the Engineer at least once every thirty (30) calendar days.  Include the daily record of rainfall form as an appendix to the SWPPP.

641-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Items 641(2) and (4) will be measured as specified in the Contract or directive authorizing the work.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1) and (2), or items 641(1), (3), and (4). The Bid Schedule may or may not, include Items 641(5) and 641(6).

Item 641(1) Erosion, Sediment and Pollution Control Administration. At the contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC preparation, updating the SWPPP, inspections, monitoring, reporting and record keeping.

Item 641(2) Temporary Erosion, Sediment and Pollution Control. At the prices specified in the Contract or directive authorizing the work to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control measures required to complete the project using the approved SWPPP and HMCP.

Item 641(3) Temporary Erosion, Sediment and Pollution Control. At the contract lump sum price to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control measures required to complete the project using the original approved SWPPP and HMCP.

Item 641(4) Temporary Erosion Sediment and Pollution Control Additives. At the prices specified in the directive for extra, additional, or unanticipated work to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control measures. All work paid under this Item will be shown as amendments to the original approved SWPPP or HMCP.

Item 641(5) Erosion, Sediment and Pollution Control Price Adjustment. The total value of this contract will be adjusted as specified below. In addition, a price adjustment equivalent to any penalties levied against the Department by the EPA or any other local, state and/or federal agencies for pollutant violations, including violations of the CWA and the CGP. An amount equal to the maximum possible penalties and fines for the violation will be withheld temporarily until the actual cost of the penalties and fines is known. The Contractor is also responsible for the payment of penalties and fines levied against the Contractor.

Item 641(6) SWPPP Manager. At the contract price for a SWPPP Manager to update the SWPPP, perform inspections, monitoring, reporting and record keeping.

Temporary erosion, sediment and pollution control measures that are required at material sources, disposal sites, haul routes, fuel and material storage areas, and at equipment or material staging areas, will not be paid for separately but are subsidiary to other items of work. Work required by the HMCP and SPCC including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary.

Work that is paid for directly or indirectly under other pay items will not be measured and paid for under this Section 641. This work includes but is not limited to dewatering, shoring, bailing, permanent seeding, installation and removal of temporary work pads, temporary accesses, temporary drainage pipes and structures, diversion channels, settling impoundment, filtration, etc.

Temporary erosion, sediment and pollution control measures that are required due to negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Permanent erosion, sediment and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

If, after the Engineer gives written notice, the Contractor fails to pursue work required by the SWPPP, respond to inspection recommendations or deficiencies in the SWPPP, or implement erosion and sedimentation controls identified by the Engineer, or fails to perform any of the contract obligations, the Contractor will be assessed a permanent price adjustment of $500 per day for each day of non-action, under Item 641(5) Erosion and Pollution Control Price Adjustment. In addition, the Engineer may employ others to correct the condition and deduct the cost from the Contract amount.

The Engineer may also suspend earthwork operations and/or withhold monies due the Contractor for failure to:

- perform SWPPP Administration

- perform timely inspections

- update the SWPPP

- transmit SWPPP, SWPPP Inspection Reports, and associated Section 641 submittals to the Engineer

- maintain effective BMPs that minimize erosion, control sediment, or prevent discharge of pollutants that exceed applicable water quality standards

- perform duties in accordance with the requirements of this Section 641

- meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control

The Contractor shall be due no additional monies or Contract time extension as result of delays resulting from suspension of earthwork for failure to perform required erosion, sedimentation, or pollution duties as outlined in this Section 641.

Payment will be made under:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 641(1) | Erosion, Sediment and Pollution Control Administration | Lump Sum |
| 641(2) | Temporary Erosion, Sediment and Pollution Control | Contingent Sum |
| 641(3) | Temporary Erosion, Sediment and Pollution Control | Lump Sum |
| 641(4) | Temporary Erosion, Sediment and Pollution Control Additives | Contingent Sum |
| 641(5) | Erosion, Sediment and Pollution Control Price Adjustment | Contingent Sum |
| 641(6) | SWPPP Manager | Lump Sum |

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-1.01 DESCRIPTION.  Delete the sentences that begin “Furnish and install…”  and “Adjust existing monuments….”

642-2.01 MATERIALS.  Add the following:

Digital Measuring Instrument:  Nu-metrics, Nitestar DMI (www.nu-metrics.com)

R61 (03/22/06)

642-3.01 GENERAL.   Add the following to the sixth paragraph:

Before work on the project starts, stake and reference the existing centerline on the right side of the roadway alignment.  Stake the existing centerline at 100 foot on tangents, and 50 foot intervals on curves from the beginning and ending of superelevation changes when the roadway is no longer at normal crown.  Stake sign locations at proper offset.  Stakes shall be a minimum of 1 inch by 2 inch by 2 feet and be offset 4 to 8 feet from the shoulder on the right side of the roadway.  Lath stakes will be a minimum of 2 feet above ground.  Show the offset distance to centerline and the station from the beginning of the project.  Ensure stakes are visible from roadway by clearing as necessary.  Maintain staking until the final roadway striping is completed.  Clearing will not be paid for separately and is considered subsidiary to other 642 pay items.  Staking accuracy work requires an electronic distance measuring instrument (DMI) be installed in the Contractor’s vehicle.  Calibrate the DMI to roadway alignments as stationed in the Plans before beginning work.  Record calibration and staking information in the field book.

Install a reference sign every 500 feet.  These reference signs shall meet the following requirements:

1.	mounted a minimum of 5 feet above the shoulder,

2.	located a minimum of 10 feet from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 6 inch high black lettering on an orange background.

Compute design centerline profile to best fit the existing centerline profile.  Prepare existing top of pavement cross sections for horizontal curves and transitions with design super-elevated pavement plotted on each section.  The Engineer may require adjustments to the roadway grades.  This shall not be considered extra work.  Provide this profile information to the Engineer (electronically in Excel format) immediately upon its completion, along with checked computations on all level loops, but in no case later than 7 calendar days before slope staking or blue topping.

Reference the existing beginning and ending points of the no-passing zones in a separate field book.

Determine the best fit radius to each curve and provide this information to the Engineer in an Excel spreadsheet for areas to be paved.  The Engineer will determine the appropriate super-elevation for each curve.

642-3.01 GENERAL.

Add the following:

11.	Document the Stationing of the beginning and ending of existing passing zones before work that will remove or obliterate the existing striping.  Measure, as outlined below, sight distance for passing zones after the base course layer or pavement milling has been accepted.  Use Table 642-1 to establish Minimum Passing Sight Distance.  Move forward alongside the centerline or edge of traveled way in order to spot check and discover locations where the Minimum Passing Sight Distance drops below what is required for 10 MPH over the posted speed limit.  Record the sight distance for each station location that falls below the posted speed limit plus 10 MPH.  Continue to record the sight distance for each station location until the sight distance drops below what is required for the posted speed limit.  Stations observed to exceed the values required for posted speed limit plus 10 MPH should be marked as “Pass” or “+”.  Stations observed to fall below the values required for the posted speed limit should be marked as “Fail” or “-.”

Measure from the roadway edge of traveled way, using a 3.5 foot object height (or “instrument height”) at 100 foot station marks looking ahead to a 3.5 foot target height at the edge of traveled way for opposing traffic.  Provide a list of each station result for each direction of travel along the roadway edge of traveled way.  Certify and record the results on standard “letter” sized paper and provide 2 copies to the Engineer at least two weeks before laying out final pavement markings.

The Engineer will forward one copy of the existing and proposed sight distance measurements on the form provided herein, to the Regional Traffic Engineer.  Table 642-1 does not automatically ensure passing striping will be provided.  The Regional Traffic Engineer’s office will take up to two weeks to review and approve pass/no pass striping against operating speeds for the roadway before installation, using Table 642-1 and the Alaska Traffic Manual as a guide.  No pass striping zones shall be at least 500 feet in length.  Passing striping shall be long enough to meet the distances in Table 642-1.  Passing striping will not extend into a segment of road without minimum sight distance.

TABLE 642-1

PASSING SIGHT DISTANCE

| Operating Speed(mph) | Minimum Passing Sight Distance (ft) |
| --- | --- |
| 25 | 450 |
| 30 | 500 |
| 35 | 550 |
| 40 | 600 |
| 45 | 700 |
| 50 | 800 |
| 55 | 900 |
| 60 | 1,000 |
| 65 | 1,100 |
| 70 | 1,200 |

Passing Sight Distance Survey Table

ROAD NAME:

Stationing:

FROM: ______________________________ DATE:

TO:_________________________________

SURVEYOR:

| Project Station | Posted Speed Limit | Direction of Travel | Sight Distance Ahead | Remarks |
| --- | --- | --- | --- | --- |

Other Notes:

1.

2.

3.

Accepted By: _____________________________________________Date:    ______________

DOT/PF Project Engineer

Passing Sight Distance

Review Checked By:______________________________________ Date:

DOT/PF Regional Traffic Engineer

R61 (03/22/06)

Special Provision

Add the following:

12.	Document the existing striping and traffic markings prior to construction.  The Contractor shall submit the documentation to the Engineer 15 days prior to construction and shall not begin construction activities until the Engineer has reviewed and approved the documentation for use in re-striping the repaired and resurfaced project roadway.

The Engineer may modify the passing zone striping as a result of the passing sight distance measurements.

Standard Modification

642-3.04 OFFICE ENGINEERING. Delete third sentence and replace with:

Perform the work by, or under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor or a Professional Engineer.

E53 (05/01/07)

Special Provisions

642-4.01 METHOD OF MEASUREMENT.  Add the following:

Item 642(16) Passing Sight Distance Measurement.  By the number of stations on the project measured separately along centerline, once for each direction, only after the certified and recorded results have been accepted by the Engineer.

642-5.01 BASIS OF PAYMENT.  Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

642(16)  	Passing Sight Distance Measurement 	Station

R61 (03/22/06)

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION.  Add the following:

Additional work:

	Illuminate construction activities listed in Table 643-3, Night Work Illumination Level and Area of Coverage, during hours of night work on roads open to the public within project limits.

ES14 (03/15/06)

643-1.02 DEFINITIONS.  Add the following paragraphs after paragraph titled “Construction Phasing Plan”:

Balloon Light:  Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The top half of the balloon enclosure shall be constructed of an opaque material.

Night work:  Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in Table 643-2, Night Work Lighting Requirements.

TABLE 643-2

NIGHT WORK LIGHTING REQUIREMENTS

| Latitude (degrees) | No Lighting Required |  | Nearby Cities |
| --- | --- | --- | --- |
|  | Start | End |  |
| < 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Delta Junction, Nome, Tok |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

ES14 (03/15/06)

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following:

A waiver may be requested of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project in writing.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic within the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

R222 (05/27/07)

643-1.04 WORKSITE SUPERVISOR.  Add the following to Item 2. Duties:

i.  Supervise lighting of Night Work.

ES14 (03/15/06)

Standard Modifications

Add Item 3. Authority:

3.	Authority.  The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-2.01 MATERIALS.  In Item 10. Temporary Crash Cushions, delete the second sentence:

“Do not use permanent crash cushions as temporary crash cushions.”

E62 (07/28/08)

Replace No. 12 with the following:

12.	Portable Changeable Message Board Sign.  Use new truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following:

a.	Message sign panel large enough to display 3 lines of 18 inch high characters.

b.	Ten character display per message module.

c.	Fully programmable message module.

d.	Remote control cellular, wireless RF, landline.

e.	Waterproof, lockable cover for the controller keyboard.

f.	Capacity for electric/hydraulic sign raising or lowering.

g.	Radar over speed detection.

h.	Variable flash and sequence rates.

I.	LED display, using ITE amber/yellow.

j.	The capacity for a minimum of 150 pre-programmed messages.

k.	Operate with a battery pack a minimum of 55 hours under full load.

l.	Power chords shall comply with the National Electrical Code Article 600.10 Portable and Mobile Signs, paragraph 600.10(c) (2) ground fault circuit interrupter.  The chord must have an integral GFCI Protection located either in the attachment plug or within 12 inches of the plug.

R222 (05/25/07)

Standard Modifications

Under Item 16. Flagger Paddles, replace the last sentence with the following:

Use reflective sheeting that meets AASHTO M268, Type VIII or IX.  Use background colors of fluorescent orange on one side and red on the other side.

E56 (05/01/07)

Add the following:

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.

R222 (05/25/07)

Standard Modifications

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:

Immediately notify the Engineer of a traffic related accident that occurs within the project limits as soon as becoming aware of the accident.

E56 (05/01/07)

Add the following:

Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Maintain business accesses during flagging operations.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following.

Where specified in the Plans, Specifications, Special Provisions and or the TCP traffic may be maintained on a continuous gravel surface.

1.	Gravel Surface Not Specified.

a.	Through traffic shall not traverse more than two gravel sections of roadway.***Deleted***

b.	Pavement Break(s) for Culvert or Utility Work:  Patch pavement breaks(s), with 1.5 inches of HMA and 6 inches of aggregate base course, not more than 24 hours after removing the existing pavement.

c.	When approved by the Engineer.

2.	Foamed Asphalt Process.

a.	Asphalt foaming may not occur on two or more sections of roadway at the same time.  A section of roadway to be foamed may be a maximum of 10,000 feet in length by the full roadway width.

R222 (05/01/07)

Standard Modification

643-3.04 TRAFFIC CONTROL DEVICES.

In the sixth paragraph and also in Item 4.b. delete: “ATTSA” and replace with “ATSSA.”

E56 (05/01/07)

Replace the first sentence of the eighth paragraph with:

Items paid under this Section remain the Contractor’s property unless stated otherwise.

Add the following to item 1. Embankments:

Close trenches and excavations at the end of each continuous work shift.

Add the following to Item 3., Fixed Objects:

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete Item 4.b, and replace with:

Flagger Certification by ATSSA.

Delete Item 6 and replace with:

6.	Street Sweeping and Power Brooming.  Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material.  Use equipment for brooming and sweeping as recommended by the manufacturer and the following:

Dirt, dust and construction materials, mobilized as a result of power brooming and or sweeping, shall not be pushed, ejected, thrown or drift beyond the lesser of, 2 feet from the equipment perimeter or the edge of the paved surface.

All equipment shall operate to typical industry standards.  Maintain equipment to operate as designed by the manufacturer.  Equipment will employ safety equipment, warning lights and other as required by the Specifications and these Special Provisions.

Sweeper and Broom Options:  Table 643-4, Traffic Control Rate Schedule, Street Sweeping.

a.	Regenerative Sweeper:  Sweeper that blows a stream of air at the paved surface causing fine particles to rise up and be caught through a vacuum system.

b.	Vacuum Sweeper:  Sweeper that creates a vacuum at the paved surface sucking dirt dust, and debris into the collection system.

c.	Mechanical Broom Sweeper:  Sweeper designed to pick up and collect larger size road debris, stones and litter, etc.  In addition to the requirements noted in these specifications, use of a mechanical broom sweeper requires the Engineer to approve the sweeper for the intended use.

d.	Power Broom:  Power brooming that wets, pushes and or ejects loose material directly into an attached collection/pickup container may be used when approved the Engineer.  The added moisture will be contained to the paved roadway surface.

Dry Power Brooming is not permitted.  Power brooming without direct/immediate means of collection/pickup is not permitted.

Add the following:

9.	ET-PLUS.  The price listed in the Traffic Control Rate Schedule, Table 643-4, will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-PLUS unit(s).  Deliver the salvaged unit(s) to the nearest ADOT&PF Maintenance & Operations yard or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER.  Replace the first sentence with:

When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice.  A written notice will follow the oral notice according to subsection 105-1.01 Authority of the Engineer.

Add the following after the second sentence:

In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following:

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-1,000 | $30 |
| 1,001+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING.  Replace the last sentence with:

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Friday to Sunday:  Friday from 1200 hours to Sunday 2200 hours.

2.	Around any Holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

3.	No Traffic Restrictions:  No traffic restrictions between 0900 hours to 2000 hours daily, Except as required to meet Subsection 318-3.11.

Lane restrictions, if allowed shall be conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 1/4 mile (1,320 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 20 minute stopped delay, 80 vehicles, or 1/2 mile (2,640 feet) of traffic detained, will be allowed for motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words:

“or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with:

Apply final pavement markings according to subsection 670-3.01, Construction Requirements of these Special Provisions.

R222 (05/25/07)

Add the following new subsection:

643-3.10 LIGHTING OF NIGHT WORK.  Illuminate the night work areas specified in Table 643-3, Night Work Illumination Level and Area of Coverage, to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

TABLE 643-3

NIGHT WORK ILLUMINATION LEVEL AND AREA OF COVERAGE

| Type of Work/Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least two machine mounted balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, Pavement Sweeping | At least four sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): 1) Roads with ADTs over 10,000 2) That are controlled by portable signals or flaggers | Two balloon lights of at least 2000 watts each, located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |

Use balloon lighting as the main light sources.  Do not use floodlights without prior approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers and residents living along the roadway.  Locate, aim, louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to provide the lighting equipment specified in Table 643-3 or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operations that require illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they to not interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment mounted light towers are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-3.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of at least 20 emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Provide NCHRP 350-compliant breakaway bases for post mounted electroliers located within the clear zone.

ES14 (03/15/06)

Standard Modifications

Add the following new subsection:

643-3.11 HIGH VISIBILITY CLOTHING.  Ensure workers within project limits wear an outer visible surface or layer that complies with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/SEA 107-2004.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise).  Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottoms at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to requirements in this subsection,  643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility clothing.

7.	Condition.  Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.  Maintain retroreflective material to Level 2 standards.

E56 (05/07/07)

643-4.01 METHOD OF MEASUREMENT.  Replace the second sentence of Item 2. with:

Special Construction Signs are measured by the total area of legend bearing sign panel, as determined under Subsection 615-4.01 and compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-4.

Add the following:

No measurement required to provide a 24-hour toll free (1-800 ### - ####) “hotline road report” telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT.  Add the following to No. 7:

The Engineer will pay for Item 643(15) Flagging on a contingent sum basis at the rate of $44.00/hour.  The Engineer does not require a change order/directive for the flagging pay Item.  Flagging associated with Change Order work will be paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

Add the following to No. 11:

The engineer does not require a change order/directive for Item 643(25), Traffic Control.

R222 (05/27/07)

Add No. 16.:

16.	Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items.

ES14 (03/15/06)

Standard Modification

Add No. 17.:

17.	High Visibility Garments.  Payment for high visibility garments for workers is subsidiary to other items.

E56 (05/01/07)

Add No. 18.:

18.	Pavement Breaks.  Temporary HMA and aggregate base course at pavement breaks, as noted in 643-3.02, 1. Gravel Surface Not Specified, is subsidiary to 603 Items.

TABLE 643-4

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Signs | Square Foot | $24.00 |
| Type II Barricade | Each/Day | $3.00 |
| Type III Barricade | Each/Day | $10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.00 |
| Drums | Each/Day | $3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-PLUS | Each | $5000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $20.00 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical Broom Sweeper, Power Broom | Hour | $150.00 |
| Plastic Safety Fence | Foot | $.75 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |

Replace Item 643(15) with:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 643(15) | Flagging | Contingent Sum |

R222 (05/25/07)

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:  Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1,000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Four telephone service lines available at the office location.  One of the lines provided is to be available for a facsimile machine/dial-up Internet connection.  Provide Internet connection with send and receive data capability supporting 56 kilobytes per second or higher data transfer rate.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture from Anchorage.

R63 (01/11/07)

Standard Modifications

644-2.02 FIELD LABORATORY.  Add the following to the end of the second sentence of the first paragraph: through one week after Project Completion.

E44 (01/27/07)

Special Provisions

644-2.02 FIELD LABORATORY.  Delete subitem g of item 2 and substitute the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Replace item 6. a. with the following:

- Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

Add the following:

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

R63 (01/11/07)

Standard Modifications

Add the following new subsection:

644-2.06 NUCLEAR TESTING EQUIPMENT STORAGE SHED.  Design, furnish and maintain a weatherproof, heated, and ventilated nuclear densometer/testing equipment storage shed for the Engineer to use exclusively throughout the Contract.  Install the building at least 15 feet from an occupied area at a location approved by the Engineer.  Install the shed before beginning of construction activities and maintain it until one week after project completion.  Provide sufficient floor area for the nuclear testing equipment and a portable electric heater to maintain a minimum room temperature of 50 °F in freezing weather.  Design the building with enough floor area to provide sufficient clearance between the equipment, heater, and combustibles.  Provide a commercial grade metal clad exterior entrance door of 3’-0” minimum width by 6’-8” height with dead-bolt lockset.  Hang the door so that hinge pins are not accessible from the exterior.  Provide the Engineer with 2 keys to control access.  Provide a 5/16” x 10 foot long welded steel security chain securely attached inside the structure with tamperproof hardware for the Engineer to secure the testing equipment.  Provide 120 volt, 60 cycle power, an interior light, and a wall receptacle for the heater.  Secure the structure to the ground with tamperproof anchors to resist wind loads and prevent unauthorized movement of the building.  The nuclear testing equipment storage shed remains the property of the Contractor.  Remove the shed from the site following project completion.

644-4.01 METHOD OF MEASUREMENT.  Add the following items:

Nuclear Testing Equipment Storage Shed.  By the number of storage sheds specified, to including components, installed and accepted as completed units and ready for equipment storage.

644-5.01 BASIS OF PAYMENT. Add the following items:

Lump Sum Items. Payment for lump sum items will be made as follows:

1.	A percentage of the lump sum amount, to be determined by the Engineer, will be paid as full compensation for furnishing the facility at the site.

2.	The balance of the lump sum amount will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, providing all utilities, and for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Nuclear Testing Equipment Storage Shed. At the Contract unit price to include labor, materials, tools, equipment and supplies required to furnish and install the shed before beginning construction, to maintain it for the duration of the project and to remove the shed and electrical service after project completion.  Electrical service and utility costs are subsidiary to this item.

Add to Pay Items:

Pay Item No.	Pay Item	Pay Unit

644(15)	Nuclear Testing Equipment Storage Shed	Each

E44 (01/27/07)

Special Provisions

644-5.01 BASIS OF PAYMENT.  Add the following:  Long distance calls made by State personnel and the Internet service provider will be paid by the State.  Local calls and connection fees shall be paid by the Contractor.

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

R63 (01/11/07)

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A,

Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "yellow pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish before contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and one or more of the following occurs: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the Contractor’s judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  Submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts.  In the event  a portion of the work is subcontracted, the Engineer shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor according to subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section before the Contractor’s submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the Contractor’s discretion, graduates early and is employed as a journey worker according to the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of other training program funds the Contractor may receive, unless such other funding sources specifically prohibits the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Noncompliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of training programs approved for the project.  No payment or partial payment will be made if the Contractor fails to do the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why the Contractor was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1) 	Training Program, 1 Trainee/Apprentice 	Labor Hour

S16 (10/29/91)

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this Subsection with the following:  Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.

Delete item 2.  60-Day Preliminary Schedule.

Delete the first sentence of item 3. Schedule Updates. and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

R261 (12/13/02)

Special Provisions

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, except holidays.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1) Wide Pad Dozer, 65 hp Minimum will be paid on a contingent sum basis at the rate of $125/hour on a per hour basis at the rate shown on the bid schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(5)	Backhoe, 4WD, 1 CY Bucket, 75 HP, 15 Foot Depth 	Contingent Sum

R15 (08/24/05)

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Pavement Markings as shown on the Plans and as directed.

Pavement Marking Type:  Methyl Methacrylate (MMA)

670-2.01 MATERIALS.  Replace the material reference,

“Methyl Methacrylate Markings							Subsection 712-2.17”, with,

Methyl Methacrylate Pavement Markings				Subsection 712-2.17

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.  Delete No. 4 and substitute the following:

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

SURFACE APPLIED

Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 60 mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of 60 mils.

INLAID

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

(1)	Longitudinal Markings.  Groove the pavement to a depth of  --   mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of  --   mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Groove the area for inlaid markings to a depth of  --  mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of  --   mils.

(b)	Roundabouts:

As designated on the plans, groove the area for inlaid markings in roundabouts to a depth of  --  mils.  Apply markings to yield a thickness of  --  mils.

(c)	Gore Markings:

Diagonal gore markings will not be inlaid unless shown in the Plans.

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01)

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Add the following Subsection:

670-3.06 TOLERANCE FOR LANE STRIPING.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

Add the following Subsection:

670-3.07 CONTRACTOR’S WARRANTY.  Provide a warranty, for the Methyl Methacrylate Pavement Markings, as specified herein.

The period of warranty is 2 years.  The warranty period will start on the date the Engineer accepts the work and authorizes payment.

Pavement markings that do not satisfy the specified performance requirements will be repaired and or replaced by the Contractor.  The Department will determine if the failed markings will be repaired or replaced.  The Contractor will be notified, in writing, of the marking failure(s) and the corrective measures required including repairs and or replacement.

The Contractor will have 6 months to complete repairs.  The Contractor will coordinate the repair start and end dates with the Department.

The warranty period, for all project MMA pavement markings, will stop until corrective work is approved complete by the Department.

Performance Requirements.

1.	Retroreflectivity.  If retroreflectivity becomes a concern during the warranty period, the Engineer will measure the retroreflectivity of the area in question.  The roadway surface will not be cleaned in preparation for taking readings, but areas of obvious contamination or debris will be avoided.

a.	Longitudinal sample areas will be a minimum length of 500 feet and have at least three samples taken.

b.	Transverse, symbols and gore samples will be three per transverse line or symbol.

Table 670-1

PAVEMENT MARKING MINIMUM RETROREFLECTIVITY REQUIREMENTS

| Marking Color | Retroreflectivity, Minimum Levels |  |  |
| --- | --- | --- | --- |
|  | Initial Retroreflectivity a | 6 Months b | 2 Years b |
| Yellow, White | 200 mcd/m2-lux | 150 mcd/m2-lux | 40 mcd/m2-lux |

Footnotes:

a.	The initial retroreflectivity readings will be completed after the MMA has cured and no more than 7 days prior to the Engineer accepting the work.

b.	The 6 month and 2 year readings will be measured from the date of the initial retroreflectivity readings.

2.	Color Stability.  The pavement markings shall retain color throughout the warranty period.  Yellow striping will be compared to the PR-1 chart, and shall meet 33538 Federal Yellow.  White striping shall have a minimum daylight reflectance of 84 throughout the Warranty period.

3.	Adhesion.  For the purpose of the warranty a cumulative 5% or greater loss of longitudinal line of any 500 foot segment of marking and 5% or greater loss of each transverse line, gore stripe and symbol, due to nonadhesion, shall constitute failure of the material in that segment.

Repair.  Repair pavement markings as specified by the Department.

Replacement.  Replace pavement markings as specified in Section 670-3.01 Construction Requirements 4.f. Application and as specified by the Department.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measure from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete No. 2.

Delete No. 3 and replace with the following:

3.	Each.  Pavement markings using letters, numbers, and arrows will be measured on a unit basis with each separate word or symbol constituting a unit.  Railroad Markings will be measured by the complete unit shown for each lane of travel.

Add the following No. 4:

4.	Foot Basis.  Longitudinal pavement markings, transverse, and gore markings, surface applied or inlaid will be measured by the linear foot of 4 inch wide line.  Wider striping will be measured in multiples of 4 inches.

670-5.01 BASIS OF PAYMENT.  Add the following:

Payment for Methyl Methacrylate (MMA) Pavement Markings includes furnishing the Warranty.  Payment for the installation of the pavement markings will be limited to 80% of the amount due until the Department has received a signed Warranty.

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with pavement markings are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Temporary pavement markings and removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

Replace Item 670(10) with the following:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10)	MMA Pavement Markings	Lump Sum

670(10A)	MMA Pavement Markings, Longitudinal Surface Applied	Linear Foot

670(10B)	MMA Pavement Markings, Symbols and Arrow(s) Surface Applied	Each

670(10C)	MMA Pavement Markings, Transverse and Gore Surface Applied	Linear Foot

670(10D)	MMA Pavement Markings, Longitudinal Inlaid	Linear Foot

670(10E)	MMA Pavement Markings, Symbols and Arrow(s) Inlaid	Each

670(10F)	MMA Pavement Markings, Transverse and Gore Inlaid	Linear Foot

Delete Items 670(11) and 670(12).

CR246-010109

Special Provisions

Add the following Section:

SECTION 690

EROSION, SEDIMENT AND POLLUTION CONTROL - MEASURES

690-1.01 DESCRIPTION.  Furnish, install and maintain measures, countermeasures and associated materials as part of BMP(s) to prevent, control and contain erosion, erosion materials, sediments and pollution contaminates, on and off project site.

Measures:

	Permanent Measures – include, the materials, hardware, equipment and labor required for installation and maintenance of erosion, sediment and pollution control material(s).

	Temporary Measures - include, in addition to the requirements of Permanent Measures, removal and disposal of the erosion, sediment and pollution control material(s).

Related Specifications:

Erosion, Sediment and Pollution Control		Section 641

Silt Fence		Section 633

Seeding		Section 618

Soil Stabilization		Section 619

690-2.01 MATERIALS.

Erosion Sediment and Pollution Control – Materials		Section 744

Others as specified in related Sections.

CONSTRUCTION REQUIREMENTS

690-3.01 GENERAL.  BMP(s) may include individual or a combination of measures and countermeasures, including but not limited to temporary seeding, mulch, matting, staples, stabilizing emulsions, blankets and mats, soil blinders, non-erodible cover, dustless sweeping, dust palliatives.   Refer to Subsection 690-1.01, Related Specifications, for measures not included here.

690-3.02 MATERIAL STORAGE AND PROTECTION.  General:  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment and as follows:

Fiber Rolls.  Additionally, protect fiber rolls from:  precipitation, extended ultraviolet radiant including sunlight, chemicals that are strong acids or other, flames including welding sparks, excess temperatures, and any other environmental conditions that may damage the physical property value of the rolls.

690-3.02 FABRICATION.

Sandbags:  Sand bags shall measure 15 inches by 30 inches.  Use prayer type seams with a minimum of two rows of stitching using a Federal Stitch Type 401 Chain Stitch.  Place approximately 1.0 cubic foot of Select Material, Type B, in each sandbag sack.  Close the open end of the sandbag, after filling, with 2 cinch ties or as recommended by the manufacturer of the sandbag material.

690-3.04 PLACEMENT AND INSTALLATION.  Place and install where shown and detailed in the Plans and Specifications including Section 641, and as recommended by the manufacturer, directed by the Engineer and as follows:

Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Confirm application of temporary seeding with the Engineer.

Prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetation cover.  Maintain seeded areas.  Refer to Section 620 for further surface/topsoil preparation requirements.

Reseed where water quality standards are being exceeded as a result of insufficient vegetative cover.  Review with Engineer prior to reseeding.

Refer to Section 618 for further information.

690-3.05 MAINTENANCE.  Maintain the integrity of the erosion, sediment and pollution control measures for the duration of the project.  Inspect as required by the NPDES CGP and SWPPP and correct any deficiencies immediately.  Remove and dispose of temporary measures including trapped sediment contaminants off project at approved locations. Materials manufactured as biodegradable may be left in place when approved by the Engineer.

690-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Fiber Rolls: By length, measured along the centerline of the fiber roll, complete in place.

Manufactured Inlet Protection Systems:  By each, complete in place.

Sandbag Inlet Sediment Trap:  By each, complete in place.

Silt Fence:  Section 633.

Seeding:  Section 618.

Stabilization:  Section 619.

690–5.01 BASIS OF PAYMENT.  Section 641.

Except:

Item 690(1) Fiber Rolls, includes materials, hardware, equipment and labor required for installation and maintenance.

Item 202(13). Payment for the actual amount of fence taken down, disposed or delivered to the owner, regardless of the type or height.

Payment will be made under:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 690(1) | Fiber Roll | Linear Foot |

SECTION 703

AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE.

Delete Table 703-2 and substitute the following:

###### TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 1/2 inch | 100 | - | - |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

Replace subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT PAVEMENT.

Coarse Aggregate (retained on the No. 4 sieve). Crushed stone or crushed gravel consisting of sound, tough, durable rock of uniform quality.  Remove natural fines passing a #4 sieve before crushing aggregates for Type V or VH asphalt concrete mixtures.  Free from clay balls, organic matter, and other deleterious material.  Not coated with dirt or other finely divided mineral matter.  Meet the following requirements (note A or B indicate class of mix, see Table 401-1), the Engineer may modify the fracture requirements if the hard aggregate sources stated in 106-1.02 do not meet specifications:

| Description | Specification | Type IIA, IV | Type I, IIB, III | Type V | Type VH |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max | AASHTO T96 | 45 | 45 | 45 | 45 |
| Degradation Value, min | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium Sulfate Loss % max (5 cycles) | AASHTO T104 | 9 | 9 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP61 | 90, 2 face | 80, 1 face | 98, 2 face | 98, 2 face |
| Thin-Elongated Pieces, max % 1:5 1:3 | ATM 306 | 8 30 | 8 - | 3 8 | 3 8 |
| Nordic Abrasion, max. % | ATM 312 |  |  | 12 | 8 |
| Absorption, max. % | AASHTO T85 | 2.0 | 2.0 | 2.0 | 2.0 |

TABLE 703-3

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT PAVEMENT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V, VH |
| 1 inch | 100 | - | - | - | - |
| 3/4 inch | 80 - 90 | 100 | - | - | 100 |
| 1/2 inch | 60 - 84 | 75 - 90 | 100 | 100 | 65 - 80 |
| 3/8 inch | 48 - 78 | 60 - 84 | 80 - 90 | 80 - 95 | 48 - 60 |
| No. 4 | 28 - 63 | 33 - 70 | 44 - 81 | 55 - 70 | 30 - 45 |
| No. 8 | 14 - 55 | 19 - 56 | 26 - 70 | 35 - 50 | 20 - 30 |
| No. 16 | 9 - 44 | 10 - 44 | 16 - 59 | 20 - 40 | < 22 |
| No. 30 | 6 - 34 | 7 - 34 | 9 - 49 | 15 - 30 | < 17 |
| No. 50 | 5 - 24 | 5 - 24 | 6 - 36 | 10 - 24 | < 14 |
| No. 100 | 4 - 16 | 4 - 16 | 4 - 22 | 5 - 15 | < 12 |
| No. 200 | 3 - 8 | 3 - 8 | 3 - 8 | 3 - 8 | 3 - 8 |

Fine Aggregate (passing the #4 sieve). Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

For Type IV, V and VH mixes, remove natural fines passing a #4 sieve before crushing aggregates for this HMA mixture.  Consist entirely of aggregate produced from aggregate crushing process and be non-plastic as determined by WAQTC FOP for AASHTO T 90, and meets the following:

Property	Test Method	Requirement

Fine Aggregate Angularity	AASHTO T 304	45% min.

CR199-010109

SECTION 710

FENCE AND GUARDRAIL

Standard Modifications

Delete Subsection 710-2.04 and replace with the following:

710-2.04 METAL BEAM RAIL.  Meet AASHTO M 180, Class A, Type II.  Galvanize after fabrication.  Fabrication includes forming, cutting, shearing, punching, drilling, bending, welding and riveting.

710-2.11 GUARDRAIL TERMINALS.  Add the following as the first paragraph:

Meet coating requirements of AASHTO M 180, Class A, Type II.  Galvanize after fabrication.  Fabrication includes forming, cutting, shearing, punching, drilling, bending, welding and riveting.

E64 (07/28/08)

Special Provision

710-2.11 GUARDRAIL TERMINALS.  Replace No. 2 Extruder Terminal., with the following:

2.	Extruder Terminal.  ET-PLUS manufactured by Trinity Industries, Inc., 950 West 400 South, Centerville, UT 84014, Ph:  800-772-7976, Fax:  801-292-2145.  Conform to the Trinity Industries, Inc. drawings approved by the Department (Formerly Syro, Inc. drawings).  Use slotted rail for both 25-foot sections for the cable anchor assembly attachment.  See Subsection 606-3.05 for installation.  Include an object marker, Part No. 3177B, with each ET-PLUS installation.

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

2.	Performance Properties:  Add the following:

I.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace the bead table with the following:

Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads.  Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials.  Marking Material Manufacturer will certify compatibility.

(2)	Lasting retroreflectivity.  For the two year specified Warranty Period and retroreflectivity levels, Subsection 670-3.07.  The Engineer will determine the test location.

CR246-010109

SECTION 724

SEED

Special Provisions

724-2-02. MATERIALS.  Delete Table 724-1 and substitute with the following:

TABLE 724-1

Seed Requirements

| Species | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

R52 (01/27/07)

SECTION 729

GEOSYNTHETICS

Special Provisions

729-2.05 GEOGRID.  Add the following to Table 729-1:

TABLE 729-1

GEOSYNTHETICS

| PROPERTY | REQUIREMENT | TEST METHOD |
| --- | --- | --- |
| Flexural Rigidity, Min. | 0.65 in-lb | ASTM D1388 Method A or ASTM D5732, Both Tests Modified for Geogrids |

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS.  Add the following item:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

R81 (06/22/04)

Special Provisions

Add the following Section:

SECTION 744

EROSION, SEDIMENT, AND POLLUTION CONTROL - MATERIAL

744-2.01 MATERIAL.

Fiber Roll:  (commonly called straw wattle)

a.		Comprised of UV-degradable plastic netting or 100 percent biodegradable material.

b.	Filled with straw, flax, rice, coconut fiber material or composted material.

c.	Staking shall be made of 100 percent biodegradable materials.

Provide the Engineer certification stating the name of the manufacturer, product name, style number, chemical composition of the fiber, netting and certification of the weed-free status from the manufacturer.  Furnish a sample to the Engineer seven days before the scheduled installation.

Manufactured Inlet Protection System:

a.	Manufacturers:

Ultra Tech International – Ultra-DrainGuard

Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

Enpac - Catch Basin Insert, Oil and Sediment or

b.	Approved equal.

Sand Bag Inlet Sediment Trap:

a.	Sandbag sack fabric shall be a nonwoven, needle punched design meeting the following requirements:

Grab Tensile Strength	ASTM D 4632	200 pounds (min.)

Grab Elongation	ASTM D 4632	15 – 70%

Mullen Burst Strength	ASTM D 3786	400 psi. (min.)

Trapezoidal Tear Strength	ASTM D 4533	95 lbs. (min.)

Apparent Opening Size	ASTM D 4751	No. 30 U.S. STD sieve (max)

Permittivity	ASTM D 4491	0.01 sec-1 (min.)

Ultraviolet Light Stability,

Retained Strength	ASTM D 4355	90%

Puncture Strength	ASTM D 4833	120 lbs. (min.)

These requirements are for Minimum Average Roll Values (MARV) verified in accordance with ASTM D 4759.

b.	Seam Thread:

Similar durability to the sandbag sack fabric.

c.	Sandbag Fill Material:

Select Material	Type B	703-2.07.

d.	Cinch Ties:  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

INDEX

Standard Modification

INDEX Remove the text: “Approved Products List” and replace with: Qualified Products List

E36 (01/27/07)

APPENDIX A

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX B

EROSION AND SEDIMENT CONTROL PLAN

APPENDIX C

ENVIRONMENTAL PERMITS

APPENDIX D

SIGN DETAILS

APPENDIX E

MATERIALS CERTIFICATION LIST

APPENDIX F

NEGOTIATED MATERIAL SALE CONTRACT