PART 4

ALASKA

DEPARTMENT OF TRANSPORTATION

AND

PUBLIC FACILITIES

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the

STATE OF ALASKA 1988 STANDARD SPECIFICATIONS

STERLING HIGHWAY PAVEMENT REHABILITATION

Pioneer Avenue to Lands End

Project F-021-1(39)/59342

SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available from the Alaska Department of Transportation and Public Facilities located at 4111 Aviation Avenue for the following:

1.Copies for review of the following are available in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.Design Computations

b.Cross Sections

Copies of the above documents may be obtained from Ridgway's Reprographics, 6000 Arctic Boulevard, Anchorage, Alaska 99518, (907) 561-1555, at the Contractor's cost.

2.The following are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room.

a.Sterling Highway, M.P.174-179 Geotechnical Report, Project 59342, April 1993

b.Storm Water Manual (Cost = $20)

3.An environmental "Categorical Exclusion" is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 266-1508.

4.Utility agreements pertaining to the disposition of all utility facilities on the Project are available for review at the office of the Traffic, Safety and Utilities Engineer, (907) 266-1531.

5.This Contract contains a newly-developed asphalt concrete pavement specification (Section 401).  Due to changes in materials testing procedures and requirements, the following new items are incorporated by reference in this specification and are available from the Department:

a.Alaska Test Method T-17, Rev. 06/93, "Standard Method of Test for Determining Bituminous Mix Design by the Marshall Method".

Alaska Test Method T-17 is the mix design method and also includes criteria which must be met for the class of mix specified in the bid schedule.

b.Alaska Standard Practice SP-9, Rev. 07/93, "Standard Practice for Abbreviated Testing Procedures to Monitor Process Control of Coarse and Fine Aggregate Gradations".

Standard Practice SP-9 contains test methods for contractor process control as well as a minimum testing frequency, and a list of typical field laboratory equipment to be furnished by the Contractor.

SECTION 101

DEFINITIONS AND TERMS

STANDARD MODIFICATIONS

101-1.27	HOLIDAYS.

Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr.'s Birthday - Third Monday in January

3.	President's Day - Third Monday in February

(5/7/91)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

STANDARD MODIFICATIONS

102-1.01	QUALIFICATION OF BIDDERS.

Delete the second paragraph.  (5/12/89)

102-1.06  Preparation of Proposal.

Replace the second paragraph with the following:

The bidder shall specify a unit price, in figures, for each pay item for which a quantity is given and shall also show the products of the respective unit prices and quantities written in figures in the column provided for that purpose and the total amount of the proposal obtained by adding the amounts of the several items.  All the figures shall be in ink or typed.  In the event of a discrepancy between unit bid prices and extensions, the unit bid price shall govern.  Any changes shall be initialed by the person signing the proposal.  (7/2/93)M58

Add the following:

At certain bid openings a bidder may wish to submit bids on more Work than he desires to have awarded him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the statement to the Proposal Form:

“We desire to disqualify all of our bids at this letting which exceed the total of $____________ or _____________ contracts and hereby authorize the Department to determine which bids shall be disqualified.”

102-1.07	NON-RESPONSIVE PROPOSALS.

Delete numbered Subsection 3. in its entirety and substitute the following:

3.	If the Bidder adds any provisions reserving the right to accept or reject any award, or to enter into a Contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to the Bidder at any one (1) bid letting, as provided in Subsection 102-1.06, Preparation of Proposal.  (5/7/91)

Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)

102-1.12	ADDENDA   REQUIREMENTS.

Add “or telefacsimile” in the second sentence immediately following the word “telegram”.  (5/12/89)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

SPECIAL PROVISIONS

103-1.01  Consideration of Proposals.

Add the following:

The apparent low bidder shall submit a completed Subcontractor List, form 25D-5(C), within 5 working days following receipt of written notification by the Department.

If a bidder fails to list a subcontractor or lists more than one (1) subcontractor for a particular portion of Work and the value of that Work is in excess of 1/2 of 1% of the total bid, the bidder agrees to perform that portion of Work without the use of a subcontractor and to have represented that he is qualified to perform that Work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the Work required under the Contract, violates this Subsection.

If a Contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the Contract without any damages accruing to the Department, or,

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10% of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a Contract with the bidder involving performance of the Work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the Contract with the bidder involving Work for which the subcontractor was listed,

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or,

9.	is determined by the Contracting Officer not to be responsible.

(4/1/93)R82

SECTION 104

SCOPE OF WORK

STANDARD MODIFICATIONS

104-1.02	CHANGES.

Add the following after the third paragraph:

Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra Work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra Work. (5/12/89)M5

SECTION 105

CONTROL OF WORK

STANDARD MODIFICATIONS

105-1.01	AUTHORITY OF THE ENGINEER.

Add the following:

The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the Contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the Contract or subcontract, including cost or pricing data submitted under Subsection 104-1.02.  Books and records that relate to the performance of the Contract shall be maintained by the Contractor for a period of 3 years after the date of final payment under the prime Contract and by the subcontractor for a period of 3 years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)

SPECIAL PROVISIONS

105-1.02  PLANS AND WORKING DRAWINGS.

Replace the second sentence of the second paragraph with the following:

No Work shall be performed until working drawings for such Work, or changes thereto, are approved.

Replace the second sentence of the fourth paragraph with the following:

The Contractor shall indicate on the working drawings all deviations from the Plans and Specifications and shall also itemize and explain all deviations in the letter of transmittal.

(7/2/93)S62

105-1.06	COOPERATION WITH UTILITIES.

Add the following:

The Contractor shall request locates from all the Utilities having facilities in the area.  Their telephone numbers are as follows:

Homer Electric Association		(907) 235-8551

Pacific Telecom, Inc.			(907) 562-3090 or 564-3091

City of Homer Public Works		(907) 235-3170

Homer Cablevision			(907) 235-6366

There are various aerial and underground utility facilities located within the Project limits.  The Contractor's responsibility to schedule and coordinate the Utility relocations with the Project construction as set forth in Section 108-1.03, Prosecution and Progress.  Specific coordination requirements for Homer Electric Association, Pacific Telecom, Homer Cablevision and the City of Homer Public Works are included below.

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various aerial and underground utilities located within the Project limits.  The Contractor shall recognize that these utilities will fall within the zone of influence of excavation for highway construction.  The Contractor is responsible for determining the extent of the conflicts with either the existing or relocated utilities and coordinate with the affected utility company to protect the facility while Work is in the vicinity.  The Contractor is responsible for whatever means are necessary to protect the utilities in accordance with the requirements of the affected Utility and these Special Provisions.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the Project unless advised by the Utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the utilities may prohibit the Contractor, through the Engineer, from working near the Utility's facilities when the ground is frozen.

Prior to the relocation of the Utility's facilities, construction staking may be required.  The Contractor shall give the Utility 2 weeks advance notice as to when the staking will be available and maintain the stakes until the utility relocation is completed.

Payment for this staking will be as follows:

1.	If construction staking or right-of-way staking is required by the Utility in advance of the Contractor's normal schedule, the Utility will request the staking, through the Engineer, 2 weeks prior to the time the staking is required for the Utility to start their relocation.  This staking will be paid under Item 642(2), Three Person Survey Party.

2.	If, as part of the Contract, the Contractor provides the stakes in the area needed by the Utility, this Work will be subsidiary to Item 642(1), Construction Surveying.

3.	If right-of-way staking is required by the Utility, and staking the right-of-way is not a part of the Contract, the Utility will request the staking, through the Engineer, 2 weeks prior to the time the staking is required for the Utility to start their relocation.  This staking will be paid under Item 642(2), Three Person Survey Party.

Homer Cablevision (HCATV):

HCATV owns and operates an underground cablevision system within the Project limits.  The existing buried facilities do not conflict with the proposed construction of the Project. However, HCATV has elected to install a road crossing at the following locations:

1.	At Station 6211+80.12, crossing Main Street, HCATV will install a .500 inch cable in a 2 inch ABS plastic conduit, 48 inches under the roadbed.

2.	At Station 6250, crossing Sterling Highway, HCATV will install a .500 inch cable in a 2 inch ABS plastic conduit, 48 inches under the roadbed.

3.	At Station 6276, crossing Sterling Highway, HCATV will install a .500 inch cable in a 2 inch ABS plastic conduit, 48 inches under the roadbed.

4.	At Station 6305, crossing Sterling Highway, HCATV will install a .500 inch cable in a 2 inch ABS plastic conduit, 48 inches under the roadbed.

City of Homer Public Works:

The City of Homer has water and sewer facilities located throughout the Project which are not in conflict with the proposed Project.  All exiting valves, valve boxes and manhole lid covers will be adjusted as part of the road Project.

The State's contractor will install the following underground utilities, as shown on Sheet U1, at no cost to the Utility:

1.	Svendlund Street - Water Crossing

2.	Svendlund Street - Sewer Crossing

3.	Lambert Lane - Water Crossing

Homer Electric Association, Inc. (HEA):

HEA  owns and operates an aerial distribution pole line located throughout the Project.

HEA will relocate their electrical facilities where they conflict with the proposed highway construction as detailed on Sheet P3.

The Contractor shall adhere to the HEA "Excavation and Clearance Guidelines" attached as Appendix B, when working around electrical facilities throughout the Project.  Any exceptions to the HEA Guidelines will require advance approval from HEA.

Pacific Telecom, Inc. (PTI):

PTI owns and operates an underground telecommunication system throughout the Project.  The existing PTI utility facility is not in conflict with the proposed highway Project.

105-1.07  Cooperation Between Contractors.

Add the following:

The following projects may be under construction concurrently with this Project:

1.	NATIONAL WILDLIFE VISITORS CENTER

Agency: 	U.S. Fish and Wildlife Service

Contact: 	John Harris, U.S. Fish and Wildlife Services (786-3368)

Location: 	On the north and south side of the Homer By-Pass near Svedlund Street (Station 6225+00).

Description: 	A visitor’s center and refuge office will be located on the south side of the roadway. Support facilities including a warehouse, bunkhouse, workshop and vehicle storage area will be located on the north side of the roadway.

2.	HOMER SPIT REVETMENT PROJECT

Agency: 	U.S. Army Corps of Engineers and ADOT&PF

Contact: 	Jim Broils, U.S. Army Corps of Engineers (753-5782)

Roger Head, ADOT&PF (266-1680)

Location: 	On the south side of Homer Spit Road where the existing sheet pile wall is located (Station 97+00).

Description: 	Placement of large stone along approximately 1000 feet of shoreline for erosion control.

3.	HOMER FERRY TERMINAL STAGING AREA

(ADOT&PF #74601/F-013-1(3))

Agency: 	ADOT&PF

Contact: 	Vern Hirsch, ADOT&PF (465-2707)

Location:	At the south end of Homer Spit Road near Land's End (Station 226+00).

Description: 	Construction of a paved staging area for vehicles waiting to load onto the Ferry.

4.	LAKE STREET OVERHEAD UTILITY RELOCATION

Agency:	Homer Electric

Contact:	Neil Herring (235-8551)

Location:	Near the intersection of Lake Street and Homer By-Pass (Station 6250+00).

Description:	Relocation of overhead electrical facilities.

The Contractor shall coordinate his traffic control, construction, and material hauling operations with the prime Contractor so as to minimize impact on the traveling public, and to minimize conflicts with the Work being performed under the other contract.

STANDARD MODIFICATIONS

105-1.12	LOAD RESTRICTIONS.

Delete the first paragraph and substitute the following:

The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless otherwise allowed by an approved Traffic Control Plan.  (5/7/91)M32

105-1.15  PROJECT COMPLETION.

Replace the first sentence of the third paragraph with the following:

When all physical Work and cleanup provided for under the Contract is found to be complete, except for Work scheduled under Subsection 618-3.04, Maintenance of Seeded Areas, a letter of project completion will be issued by the Engineer. (7/2/93)M7

105-1.17  CLAIMS FOR ADJUSTMENT AND DISPUTES.

Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the Contract adjustment for which the Contractor believes the Department is liable.  (7/2/93)M8

SPECIAL PROVISIONS

105-1.17	CLAIMS FOR ADJUSTMENT AND DISPUTES.

Replace the first sentence of the eighth paragraph with the following:

If the claim is not resolved by agreement within 30 days of its receipt, the Engineer will issue a written decision to the Contractor.

(7/2/93)S71

Add the following:

Legal actions will be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/29/87)

SECTION 106

CONTROL OF MATERIALS

SPECIAL PROVISIONS

106-1.01	SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.

Add the following:

All steel and iron products which are incorporated into the Work and the action of applying a coating to a covered product (i.e., steel and iron) shall be manufactured in the United States except that minor amounts of products of foreign manufacture may be used provided the aggregate cost of such does not exceed 1/10 of 1% (0.1%) of the total Contract amount, or $2,500, whichever is greater.  Coating includes epoxy coating, galvanizing, painting, and any other coating that protects or enhances the value of a material subject to the requirements of this paragraph.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the Project.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel or iron products into the Project.

(7/2/93)S13

106-1.02	LOCAL MATERIAL SOURCES.

Add the following to the first paragraph of Item 1. General:

If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)

Add the following after the first paragraph:

The Contractor is responsible for the sampling and testing of materials for process quality control, including screening, crushing, blending, and stockpiling of aggregates, production and laydown of aggregate courses or aggregate mixtures, and monitoring of compaction.  Process control tests shall be documented and shall be available for review by the Engineer.

The Contractor shall provide a field laboratory for process control testing.  The Contractor-furnished laboratory shall be fully furnished with appropriate testing equipment and shall be shared with the Engineer for concurrent process control testing.  The Contractor-furnished laboratory is in addition to and separate from the field laboratory which is specified under Section 644 for acceptance testing by the Engineer.

A Crushing Control Plan shall be submitted at least 15 working days prior to the beginning of crushing operations.  The plan shall include a proposed testing frequency for aggregate gradation and a description of the process control testing location, staffing, and equipment. Abbreviated testing for process control of gradation shall be in accordance with Alaska Standard Practice SP-9.  Such sampling and testing will be coordinated with the Department and split samples are to be provided to the Department.

(2/1/94)S74A

Add the following:

Prior to placing or removing any material in/from a location that is outside the Project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement will be given to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, Work at that site shall be stopped and the Engineer notified.  (9/1/89)

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

SPECIAL PROVISIONS

107-1.11	PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following to the third paragraph:

When working near designated wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits.

The Contractor shall not excavate, nor use for fill, any material containing hazardous substances or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected of containing hazardous substances or petroleum fuels.

The Contractor shall report immediately to the Engineer any hazardous material discovered, exposed, or released into the air, ground, or water during construction of the Project, and also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery.  Hazardous materials include, but are not limited to, petroleum products, oils, solvents, paints, and chemicals that are toxic, corrosive, explosive, or flammable.

(5/7/91)

Add the following after Item 10:

11.	If water for any construction purpose is required from a non- municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2253.

Add the following:

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the Project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the Contract.

The Contractor shall do no Work, such as stockpiling, staging, fording, parking or trespassing on wetlands or below the ordinary high water of any watercourse.

All debris from the Project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

STANDARD MODIFICATIONS

107-1.13	RESPONSIBILITY FOR DAMAGE CLAIMS.

Change "claims or actions for injuries" to read "claims, actions or liabilities for injuries" in the first sentence. (5/12/89)

SPECIAL PROVISIONS

107-1.15	CONTRACTOR'S RESPONSIBILITY FOR WORK.

Add the following to the end of the first paragraph:

Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense.  (5/7/91)

STANDARD MODIFICATIONS

107-1.16	CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICES.

Delete "by the local fire authority." in the last sentence of the third paragraph (5/12/89)

SPECIAL PROVISIONS

107-1.16	CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.

Delete paragraphs four and five in their entirety, and substitute the following:

If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mis-locates the facility in the field by more than 2.5 feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.  (9/1/89)

Add the following:

Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the Work.

1.	Operations anticipated to be within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the Work to be performed.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer will not be paid for separately, but will be subsidiary to the item(s) of Work being performed requiring cable watch services.

SECTION 108

PROSECUTION AND PROGRESS

SPECIAL PROVISIONS

108-1.01	SUBLETTING OF CONTRACT.

Delete the third paragraph on Page 56 and substitute with the following:

The hauling of materials for the Project by bona fide truck owner- operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Commercial Driver's License, with appropriate endorsements for the class of vehicle to be operated.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least 3 years after final acceptance of the Project.

Additionally, to be classified as a valid owner-operator, a truck driver must also qualify as an independent Contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner- operators is subject to evaluation throughout the Project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the Contract.  These criteria are:

1.	the owner-operator's right to control the manner in which the Work is to be performed,

2. 	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3. 	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4. 	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner- operator's business.

The Contractor shall issue a placard to each owner-operator.  The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.

(5/7/91)

STANDARD MODIFICATIONS

108-1.03	PROSECUTION AND PROGRESS.

Insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule" in Item 1. (5/12/89)

SPECIAL PROVISIONS

108-1.03	PROSECUTION AND PROGRESS.

Add the following:

The construction of this Project shall be planned and recorded with a Critical Path Method (CPM) schedule.  The schedule shall be used for coordination and monitoring of all Work under the Contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

1.	Preparation of CPM Schedule.

At the preconstruction conference, the Contractor shall submit for the Engineer's approval, a detailed initial CPM schedule.  The schedule shall meet the requirements set forth below.  The construction time, for the entire Project shall not exceed the specified Contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, the Contractor shall do so promptly.  The CPM schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements.

The CPM schedule shall be set up so that the schedule may be read by Prima Vera scheduling software being run on an IBM compatible micro computer with a 1.44 mb disk drive. All required CPM schedule submittals shall include one (1) hard copy and one (1) copy of the same schedule on a 3.5 inch double sided diskette.

The CPM schedule shall be presented as a Precedence Diagram Network developed in the activity-on-node format and shall include:

a.	activity description,

b.	activity duration,

c.	resources required for each of the Project activities, including:

(1)	labor, showing:

-  work days per week

-  holidays

-  shifts per day

-  hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-node diagram shall show the sequence and interdependence of all activities required for complete performance of all items of Work under this Contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60-Day Preliminary Schedule.

Before proceeding with any Work on site, the Contractor shall prepare, submit, and receive the Engineer's approval of a 60-Day Preliminary Schedule. This schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the Project and shall include mobilization, submittals, procurement, and construction.

No Contract Work may be pursued at the site without an approved 60-Day Preliminary Schedule or an approved CPM schedule.

4.	Schedule Updates.

Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the CPM schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions.  The Contractor shall submit a revised CPM schedule within 7 calendar days after this meeting.  The revised schedule shall show finish dates of completed activities and updated times for the remaining Work, including any addition, deletion, or revision of activities required by Contract modification.

The Contract completion time will be adjusted only for causes specified in this Contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or Contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

In addition to the CPM schedule, the Contractor shall, every 2 weeks during construction, submit a work plan detailing his proposed operations for the forthcoming 2 weeks.  This plan shall detail the following:

1.	Work activities,

2.	manpower involved by trade,

3.	work hours,

4.	equipment involved, and

5.	the location of the Work to be performed.

After approval of the progress schedule, and during the life of this Project, the Contractor shall make available a spokesperson knowledgeable in the proposed construction operation.  Department representatives may be attending public meetings and community council meetings, and the spokesperson shall accompany them and provide a brief description and answer questions about the Contractor's Work and schedules for the Project.  The spokesperson will also be required to accompany the Engineer to residents and businesses affected by the Project when disputes or problems arise as a result of the Work being performed under this Contract.  The spokesperson must be able to commit the Contractor to courses of action when needed to resolve problems.  (7/24/91)

Preparation and updating of the CPM schedule, 2 week work plans and providing a spokesperson will not be paid for directly.  Failure to submit the CPM work schedule, 2 week work plans and providing a spokesperson as specified will result in partial withholding of progress payments in accordance with Subsection 109-1.06, Progress Payments.  (1/27/92)R11

108-1.05	CHARACTER OF WORKMEN, METHODS & EQUIPMENT.

Add the following:

The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the Project.  This information shall be updated weekly unless otherwise directed by the Engineer.  (9/1/89)

STANDARD MODIFICATIONS

108-1.07	FAILURE TO COMPLETE ON TIME.

Replace the third sentence of the first paragraph with the following:

The amount of these deductions is to reimburse the Department for estimated additional Contract administration expenses incurred as a result of the Contractor's failure to complete the Work within the time specified.

Replace Table 108-1 with the following:

TABLE 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

ORIGINAL CONTRACT AMOUNT

| FROM MORE THAN | TO AND INCLUDING | DAILY CHARGE |
| --- | --- | --- |
| $ 0 | $ 100,000 | $ 300 |
| 100,000 | 500,000 | 550 |
| 500,000 | 1,000,000 | 750 |
| 1,000,000 | 2,000,000 | 1,000 |
| 2,000,000 | 5,000,000 | 1,500 |
| 5,000,000 | 10,000,000 | 2,500 |
| 10,000,000 | - | 3,000 |

(7/2/93)M49

SECTION 109

MEASUREMENT AND PAYMENT

SPECIAL PROVISIONS

109-1.01	GENERAL.

Add the following:

When more than  one (1)  type of material or Work is specified for a pay item, letter or numeric suffixes, included within the parenthesis following the pay item number, will differentiate the types.  (7/2/93)S63

109-1.02 	MEASUREMENT OF QUANTITIES.

Add the following:

TABLE 109-1

CONVERSION TO THE SI INTERNATIONAL SYSTEM OF UNITS*

| CONVERT FROM | TO | MULTIPLY BY |
| --- | --- | --- |
| mile (US Statute) | meter (m) | 1609.347 |
| foot | meter (m) | 0.3048 |
| foot (US Survey) | meter (m) | 12000/3937 |
| inch | meter (m) | 0.0254 |
| square foot | square meter (m2) | 0.09290304 |
| square yard | square meter (m2) | 0.8361274 |
| acre (US Survey) | square meter (m2) | 4046.873 |
| cubic foot | cubic meter (m3) | 0.02831685 |
| cubic yard | cubic meter (m3) | 0.7645549 |
| gallon (US liquid) | cubic meter (m3) | 0.003785412 |
| M. Gal. | cubic meter (m3) | 3.785412 |
| pound (lb avoirdupois) | kilogram (kg) | 0.045359237 |
| ton (short, 2000 lb) | kilogram (kg) | 907.1847 |
| pound-force (lbf) | newton (N) | 4.448222 |
| footcandle | lux (lx) | 10.76391 |
| degree Fahrenheit | degree Celsius (C) | tC=(tF-32)/1.8 |

* From ASTM publication E380-89a, Standard Practice for Use of the International System of Units (SI) The Modernized Metric System

(1/31/92)R136

STANDARD MODIFICATIONS

109-1.03	SCOPE OF PAYMENT.

Delete the last sentence of the fourth paragraph.  (5/7/91)

SPECIAL PROVISIONS

109-1.05	COMPENSATION FOR EXTRA WORK.

Add the following to the second paragraph under Item 3., Equipment:

The rental rate area adjustment factors for this Project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)

109-1.06	PROGRESS PAYMENTS.

Add the following:

Failure to submit 2 week work plans in accordance with Subsection 108-1.03, Prosecution and Progress, will result in withholding an amount equal to 5% of the total amount earned from all subsequent progress payments.  This retainage may be released by the Engineer upon receipt of current schedules from the Contractor.

109-1.07	PAYMENT FOR MATERIALS ON HAND.

Add the following:

The location of stockpiled materials for payment in acceptable storage facilities off the Project will be in Alaska only at a location acceptable to the Engineer. (9/1/89)

Add the following:

Materials shall be physically separated from the other materials stored at the storage location.  Materials shall be clearly labeled with the Project name and number.  Materials shall be stored in accordance with the manufacturer's published recommendations.  A copy of any such recommendations shall be provided to the Engineer.

Should storage conditions become unsatisfactory, any payments made for the materials will be classified as unearned.  If the Contractor has not earned sufficient funds to cover the cost of a deduction on the next progress payment, a request for repayment will be sent to the Contractor.  The Contractor agrees to repay the Department within 30 days from the date of a request to refund payment when the storage conditions have become unsatisfactory .

Unsatisfactory storage conditions include, but are not limited to:

1.	Storage not in accordance with the manufacturer's recommendations.

2.	Commingling or storage of other materials where any element of doubt exists as to which materials belong in which lot.

3.	Unsatisfactory labeling of materials.

4.	Any liens filed on the materials for storage or transport, or by the supplier or manufacturer of the material.

5.	Change of the storage locations without obtaining approval of the Engineer prior to the relocation.

6.	Damage to all or part of the materials by fire, theft, or other peril.

Should labor, travel, or any other costs be incurred for inspection off the limits of the Project, the Contractor shall reimburse the Department for these costs.

The Contractor releases and discharges the Department from any liability arising out of, or in any way related to, the payment for materials on hand and/or to the storage or transport of these materials.  The Contractor is responsible for damages or delays which may relate to the storage or transport of the materials.

(7/2/93)S64

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

SPECIAL PROVISIONS

120-1.01 DESCRIPTION.  The Work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this Contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of Work under this Contract.

120-1.02INTERPRETATION.  It is the intent of this Section to implement the requirements of 49 CFR, Part 23.

120-1.03ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this Section shall be considered a material breach of Contract.  The Department also considers failure to comply with this Section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04	DEFINITIONS AND TERMS.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular Project or a particular Contractor.

2.	Commercially Useful Function.  The execution of a Contract or a distinct element of Work under a Contract by the firm actually performing, controlling, managing, and supervising the Work involved.  See Subsection 120-3.03.3 for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one (1) or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal. The percent of Work that is specified in the Contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a Contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific Project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one (1) or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent Work.

120-2.01	UTILIZATION GOAL.  The DBE Utilization Goal for this Contract is shown on the Bid Schedule as a percentage of the total Contract amount.  Measurement of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful Work on this Project.

A Bidder must demonstrate the ability to meet the DBE Utilization Goal in order to be eligible for award of this Contract.

120-3.01	DETERMINATION OF COMPLIANCE.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low Bidder must demonstrate DBE responsibility prior to award of this Contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the Bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The Work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02	GOOD FAITH EFFORT.  The Bidder must demonstrate that all reasonable efforts have been made to include DBEs in the Contract at a level at least equal to the goal established for the Contract.  The Contracting Officer will use the following criteria to judge if the Bidder, who has not met the Contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBEs participation in the prosecution of the Work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the Bidder.

6.	Providing prospective DBEs with adequate information about requirements of the Contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See Item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media. Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03	DBE CREDIT.  In order for the Work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the Work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one (1) from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the Work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform Work in categories for which it is not certified, but only that Work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function. The following criteria will be used by the Engineer to determine if Work will be considered Commercially Useful:

a.	The Work performed must be necessary and useful Work required for the execution of the Contract.

b.	The scope of Work must be distinct and identifiable.

c.	The Work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the Work on site or have an on-site representative, superintendent, or foreman responsible for the Work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the Work, except as noted in subparagraph e., below.

e.	The manner in which the Work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract Work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least 12 months for two (2) or more trucks, at least one (1) of which must be working on this Project.  For all trucks operated by owner- operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful Work performed by DBEs toward the DBE Utilization Goal as provided in this Section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's Work if they have any questions about the Work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of Work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04	DEFAULT OF DBE.  In the event that a DBE who has been placed under Contract or to whom a purchase order or similar agreement has been issued defaults on their Work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, all of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02,  Good Faith Effort.

120-4.01	METHOD OF MEASUREMENT.  The Contractor shall be entitled to count toward the DBE Utilization Goal those monies allowed by the Engineer in Subsection 120-3.03, paragraph No. 4,  as actually paid to certified DBE firms for Commercially Useful Work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful Work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The Work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under Subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the Work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for Work by DBE subcontractors and manufacturers is 100%.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60% of their value. The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the Work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the Work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01	BASIS OF PAYMENT.  Payment for the Work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of Work and no separate payment will be made.

Payment for the Work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non- trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or 2% of the total Contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per Subsection 120-2.01 until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50% of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per Subsection 120-3.03, paragraph No. 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the Project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the Department within 30 days of being billed for the amount due.

Payment or Deduction will be made under:

Pay Item No	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent Sum

(5/5/89)

A change order is not required for DBE adjustment, the Notice to Proceed shall constitute the notice required to initiate this item.  (12/8/92)R166

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

SPECIAL PROVISIONS

202-2.04	REMOVAL OF PAVEMENT, SIDEWALKS, CURBS, ETC.

Add the following:

This Subsection does not apply to crushed asphalt base course as described in Section 308.

For disposal of removed asphalt, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by the DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529, extension 246.

(6/1/92)R84

SECTION 203

EXCAVATION AND EMBANKMENT

SPECIAL PROVISIONS

203-1.01	DESCRIPTION.

Add the following:

Ditch linear grading shall consist of excavation and final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

Pathway linear grading shall include all the preparation, excavation, and compaction necessary to construct a pathway or sidewalk as shown on the Drawings, or as field located by the Engineer.  It shall also include shaping as necessary at driveways.

STANDARD MODIFICATIONS

203-2.05	BORROW.

Add the following:

Borrow, Type A, B or C when required, shall meet the requirements of Subsection 703-2.07 Selected Material, Type A, B or C, respectively.

203-3.02	EMBANKMENT CONSTRUCTION.

Delete the fifth paragraph on page 97 and substitute the following:

All embankments shall be constructed with moisture and density control unless the Engineer determines that such controls are not feasible.

Special Provisions

203-3.05	Excavation of Contaminated Material.

Add the following subsection:

This work shall consist of removing fuel contaminated soils encountered during the excavation.  Disposal of fuel contaminated soils shall be at a location approved by the Engineer.

1.	Determining Limits of Contaminated Soil.  The exact limits of potential contaminated soil within the excavation can not be determined until the material is exposed.  Once exposed, the soil shall be tested in accordance with Subsection 644-2.09, Contaminated Material Testing.  Testing will verify the contamination levels in the soils and determine if the soils can be disposed of as unclassified excavation or if they will require special handling.

Soils that have a response from photoionizing detector or equivalent instrument of 1 part per million or more above background are considered to be "contaminated" and will require special handling and shall be disposed of in accordance with this Subsection.

2.	Worker Health and Safety.  Prior to the excavation of any soils identified as contaminated, the Contractor shall assure that all personnel working in the area of potential contamination have received the State of Alaska, Department of Labor, Health and Safety Training. The Contractor shall provide the Engineer a list of all personnel and subcontractors that will be working within the area identified as being potentially contaminated.

The Contractor shall notify all personnel and subcontractors prior to their beginning Work at the site that they will be working in an area identified as being potentially contaminated with petroleum fuel.

3.	Contaminated Soil Removal and Segregation.  In the event the Contractor must stockpile contaminated soil, a liner, cover and temporary fencing will be required.  The size and location of the liner shall be as approved by the Engineer.  The Contractor shall cover and secure the stockpile at the end of each work day.  The Contractor shall be responsible for removal of the stockpile liner, safety fence and cover once the fuel contaminated soil is removed.

The method of disposal shall be in accordance with Department of Environmental Conservation guidelines for reducing BTEX or TPH in soils.  Any additional testing required at the disposal site shall be done in accordance with Subsection 644-2.09, Contaminated Material Testing, unless otherwise directed by the Engineer.

Prior to the Contractor backfilling the excavation, random samples from the excavation (bottom and sides) shall be taken for confirmation testing.

Backfilling within the limits of the plan excavation shall meet the requirements for the item of work involved.  Backfill outside of the plan excavation limits shall meet the requirements of Selected Material, Type C.

SPECIAL PROVISIONS

203-4.01	METHOD OF MEASUREMENT.

Add the following:

No deduction from the excavation quantities will be made for pavement removed under Item 202(2), Removal of Pavement.

Measurement of ditch linear grading, whether flat bottom of "V" ditch, will be measured for payment by the station along the center of ditch constructed, not including the width of approaches with curb returns.

Measurement of the pathway linear grading item will be along the center of the pathway or sidewalk facility when constructed as stated above, not including the width of approaches reconstructed as part of this Project.  Any Work required to match driveways shall be considered subsidiary to this Work item.

Item 203(20), Fuel Contaminated Soil Special Handling, will be measured for payment on a time and material basis in accordance with subsection 109-1.05, Compensation For Extra Work.  Backfilling within the plan excavation limits will not be measured for payment but will be subsidiary to the respective items of work.  Backfill outside of the plan limits will be measured as embankment construction.

STANDARD MODIFICATIONS

203-5.01	BASIS OF PAYMENT.

Change Pay Item 203(6) to read:

Borrow, Type       .

Add the following:

When more than one (1) type of borrow is specified, letter suffixes A, B or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.

(5/12/89)

SPECIAL PROVISIONS

203-5.01	BASIS OF PAYMENT.

Add the following:

Linear grading shall be paid for by the station.  Payment will be full compensation for furnishing all equipment, labor, tools and incidentals to provide the preparation, excavation and shaping necessary to complete the Work.  The materials used for the construction of the pathway will be paid under their respective pay items.

Testing of fuel contaminated soils will be measured for payment under Item 644(8), Contaminated Material Testing.  Backfill of the resultant holes shall be with Selected Material, Type C.

Excavating and disposing of fuel contaminated soil will be paid under Item 203(28), Fuel Contaminated Soil Special Handling.  The Contractor will be paid on a time and materials basis for authorized Work in accordance with Subsection 109-1.05, Compensation for Extra Work.  Backfilling within the limits of other items of work will not be paid for separately.  Backfilling outside plan excavation limits will be paid for as embankment construction under this Section.

Add the following pay items:

Pay Item No	Pay Item	Pay Unit

203(17)Ditch Linear GradingStation

203(18)Pathway Linear GradingStation

203(28)Fuel Contaminated SoilContingent

Special HandlingSum

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

SPECIAL PROVISIONS

204-2.01	MATERIALS.

Delete in its entirety and substitute the following:

Bedding and roadway subgrade material shall meet the requirements for selected material, Type A, as specified in Subsection 703-2.07.  Pipe bedding and roadway subgrade material shall also pass the 3 inch sieve.  The roadway subgrade backfill material shall extend from the leveling course to 40 inches below finished grade.  Backfill below the roadway subgrade material and above pipe bedding material shall meet the requirements of selected material, Type C.

Selected material, Type A pipe backfill, shall extend a minimum of 12 inches above the pipe.  All suitable material from structure excavation shall be used for bedding and backfill prior to using material from another source.

204-3.01	CONSTRUCTION REQUIREMENTS.

Add the following to the third paragraph:

Native material may be utilized for electrical conduit bedding and backfill outside the pavement structure if it meets the minimum requirements of selected material, Type C, as specified in Subsection 703-2.07; compaction may be as approved by the Engineer.  This material shall also meet the requirements of Section 660-2.01, Excavating and Backfilling.

SECTION 301

AGGREGATE BASE COURSE

SPECIAL PROVISIONS

301-2.01	MATERIALS.

Delete this subsection and replace with the following:

The gradation of base course material shall conform to the requirements of Table 703-2 for Grading D-1.

The aggregate will be accepted for gradation based on random samples taken for each lift from the roadway following mixing but prior to compaction.

Add the following after the first paragraph:

At the Contractor's option, recycled asphalt pavement (RAP) may be substituted for crushed aggregate base course, inch for inch, if the following conditions are met:

1.	RAP shall be crushed or processed to 100% by weight passing the 1 inch sieve and 95% to 100% by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

|  | % PASSING |
| --- | --- |
| SIEVE | BY WEIGHT |
| 1 | 100 |
| 3/4 | 70 - 100 |
| 3/8 | 42 - 90 |
| No. 4 | 28 - 78 |
| No. 16 | 11 - 54 |
| No. 50 | 5 - 34 |
| No. 100 | 3 - 22 |
| No. 200 | 0 - 6 |

3.	The asphalt content shall be 2.5% to 5.0% by weight of the RAP.

301-3.01	PLACING.

Add the following:

Base course material used for sidewalk or pathway foundation shall be placed with a "Layton Box" or similar equipment capable of providing a specified depth with a uniform surface. (9/1/89)R26

301-3.03  Shaping and Compaction.

Add the following:

If recycled asphalt pavement is substituted for crushed aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern.  The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of six (6) passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 90 psi (plus or minus 5 psi) and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01  Basis of Payment.

Add the following:

If recycled asphalt pavement is substituted for crushed aggregate base course, it will be paid for as Item 301(1), Crushed Aggregate Base Course at the unit price shown on the bid schedule for that item.

Add the following Section:

SECTION 308

CRUSHED ASPHALT BASE COURSE

SPECIAL PROVISIONS

308-1.01DESCRIPTION.  This item shall consist of crushing the existing asphalt pavement using a rotomiller or planer and blending the crushed pavement into the existing base course layer.  The mixture shall then be shaped and compacted as a base course to the grades shown on the Plans.

3.08-2.01MATERIALS.  The existing asphalt pavement shall be crushed or processed to 100% by weight passing the 2 inch sieve and 95% - 100% by weight passing the 1 inch sieve.

The crushed asphalt base course mixture, as described in Subsection 308-1.01, shall be uniform gradation with no segregation or pockets of unmixed materials.

CONSTRUCTION REQUIREMENTS

308-3.01GRADING AND PLACING.  The rotomiller or planer shall have the following capabilities:

1.self propelled,

2.able to spray water at the cutting drum to minimize dust, and

3.adjustable as to slope and depth.

The crushed pavement shall be mixed with approximately 2 inches of the existing base course.  Additional crushed aggregate base course material shall be added to the crushed asphalt base course mixture as directed by the Engineer.  The crushed asphalt base course shall be bladed until a smooth, uniform surface is obtained that is true to line, grade and cross-section and the mix is in condition for compacting.

In areas where the existing asphalt pavement depth varies, and the Contractor is unable to attain a smooth grade, crushed aggregate base course material shall be added to the mix as a filler to attain the proper grade.

The Work area shall be kept free of standing water at all times.

308-3.02FINISHING AND COMPACTING.  Density acceptance will be based upon a roller pattern.  The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 50,000 pounds impact per vibration and a minimum frequency of 1,000 vibrations per minute.  The maximum density will be determined by the Engineer using a nuclear density gauge to monitor the test strip.

After spreading and mixing, the crushed asphalt base course shall be thoroughly watered and compacted by rolling.  The rolling shall progress by lapping uniformly each preceding rearwheel track by 1/2 the width of such track.  Rolling with a vibratory compactor shall be as determined by the test strip for density acceptance.

After rolling, the crushed asphalt base course should be thoroughly set, the interstices of the material reduced to a minimum, and creeping of the stone ahead of the roller should no longer be visible.  Blading and rolling shall be done alternately, as required or directed, to obtain a smooth, even and uniformly compacted base.  The crushed asphalt base course shall not be rolled when the underlying base course is soft or yielding or when the rolling causes undulation in the crushed asphalt base course.

In areas inaccessible to rollers, the crushed asphalt base course shall be compacted thoroughly with mechanical tampers.  The Contractor may propose an alternate method of rolling and scarifying which should be submitted to the Engineer for approval at the Pre-Construction Conference.

308-3.03SURFACE TEST.  After rolling and compacting of the crushed asphalt base course has been completed, the surface shall be tested for smoothness and accuracy of grade and crown.  Any portion lacking the required smoothness or failing in accuracy of grade of crown shall be scarified, reshaped, recompacted, and otherwise manipulated as the Engineer may direct until the required smoothness and accuracy are obtained.  The finished surface shall not vary more than 3/8 inch from a 10 foot straightedge when applied to the surface parallel with, and at right angles to, the centerline.

308-3.04PROTECTION.  Work on the crushed asphalt base course shall not be accomplished during freezing temperatures nor when the subgrade is wet.  If the imported crushed aggregate base course contains frozen materials or the underlying base course is frozen, construction shall be stopped.

308-3.05MAINTENANCE.  Following the completion of the crushed asphalt base course, the Contractor shall perform all maintenance Work necessary to keep the surface in a condition satisfactory for tack coat.  After application of tack coat, the surface shall be properly drained at all times.  If cleaning is necessary, or if the tack coat becomes disturbed, any remedial effort necessary shall be performed at the expense of the Contractor.

308-4.01METHOD OF MEASUREMENT.  Crushed asphalt base course shall be measured for payment by the square yard of the finished surface.

Water required for compaction of the crushed asphalt base course will be considered a subsidiary obligation.

308-5.01BASIS OF PAYMENT.  The accepted quantity of crushed asphalt base course will be paid for at the Contract unit price per square yard and shall be full compensation for all preparation, crushing, compacting, and mixing complete and in place.

Additional crushed aggregate base course, if required, will be paid for under Section 301.

Payment will be made under:

Pay Item No.Pay ItemPay Unit

308(1)Crushed Asphalt Base CourseSquare Yard

Add the following Section:

SECTION 401

ASPHALT CONCRETE PAVEMENT

SPECIAL PROVISIONS

401-1.01DESCRIPTION.  This Work consists of the furnishing and mixing of aggregate and asphalt cement at a central mixing plant and the hauling, spreading, and compaction of the asphalt concrete mixture on a previously prepared surface, all as specified in the Contract and in reasonably close conformance with the lines, grades and thickness shown on the Plans.

401-2.01COMPOSITION OF MIXTURES.  Mixtures shall be composed of aggregate and asphalt cement combined as specified for the type shown in the Contract.  Asphalt Concrete Pavement, Type II, shall meet the requirements of ATM T-17 for Class A.

At least 15 calendar days prior to the production of asphalt concrete pavement mix, the Contractor shall submit the following to the Engineer:

1.Notification that aggregate proposed for the mixture is available for sampling.

2.A letter stating the proposed gradation for the Trial Job Mix Design, gradations for individual stockpiles, and blend ratio for each aggregate stockpile.  Job Mix Design proposals by the Contractor shall be within the broad band gradations set in Table 703-3.

3.A minimum of three (3) 1 gallon samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a temperature viscosity curve for the asphalt cement.

4.A 1/2 pint sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

The Contractor shall accompany the Engineer during sampling, and shall furnish all the assistance needed to assure that the Engineer obtains representative samples.

From this information, the Engineer will establish the Job Mix Design which shall become a part of the Contract and shall be followed unless modified in writing.  Job Mix Design test results will be available within 7 working days after submittal.

The Job Mix Design shall be determined by and shall conform to the requirements of ATM T-17.

Changes in the Job Mix Design warranted by changes in the aggregate or sources of aggregate shall be submitted by the Contractor in the same manner as the original submittal.

If the mixture is obtained from a commercial source, the Contractor shall submit a certified statement of its components and their proportions as outlined in these Specifications for approval as the Job Mix Design.

The full tolerances specified below shall be applied to the approved Job Mix Design gradations and shall not be limited to the broad bands listed in Table 703-3.  Tolerances shall not be applied to the largest specified screen.

| SIEVE SIZE OR ITEM | TOLERANCE (Percent Passing) |
| --- | --- |
| 3/4 inch | +/- 8% |
| 1/2 inch | +/- 7% |
| 3/8 inch | +/- 7% |
| No. 4 | +/- 7% |
| No. 8 | +/- 6% |
| No. 16 | +/- 6% |
| No. 30 | +/- 5% |
| No. 50 | +/- 4% |
| No. 100 | +/- 3% |
| No. 200 | +/- 3% |
| Asphalt % | +/- 0.4% |

401-2.02AGGREGATES.  Aggregates shall conform to the requirements of Subsection 703-2.04.

401-2.03FILLER.  Filler shall conform to the requirements of AASHTO M 17.

401-2.04ASPHALT CEMENT.  The grade of asphalt cement will be specified in the Contract.  The asphalt cement shall conform to the applicable requirements of Section 702, Asphalt Materials.  Asphalt cement may be conditionally accepted at the source.  If the cement is to be conditionally accepted at the source, the Contractor shall provide a manufacturer's certificate of compliance in accordance with Subsection 106-1.05 and test results of the applicable quality requirements of Section 702 before the cement is shipped.

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at 275 F) of the asphalt cement used on the project changes from the viscosity of the cement supplied for the Job Mix Design by a factor of  2 (doubles or halves) or more, then operations shall be suspended while a new Job Mix Design proposal is submitted for approval.

401-2.05  ANTI-STRIP ADDITIVES.  Anti-strip agents used shall be an approved type in the proportions determined by ATM T-14 and included in the approved Job Mix Design.

401-2.06  PROCESS CONTROL AND ACCEPTANCE.

1.Process Control by Contractor.  Process Control for production of aggregates shall be performed in accordance with Subsection 106-1.02, Local Material Sources.

A Paving and Plant Control Plan shall be submitted at a pre-paving meeting to be held a minimum of 5 working days prior to initiating paving operations.  The Paving and Plant Control Plan shall outline the steps taken to assure product consistency and to minimize segregation and premature cooling of mixtures.  This plan shall include a proposed testing frequency for gradation, asphalt content, and compaction.  It shall also include a plan for the handling of or elimination of the wings on the paver hopper to prevent dumping and placement of cooled mix onto the roadway.

2.Acceptance Testing by Department.  The Department will perform sampling and testing for acceptance of the Work in accordance with the Department's testing frequency guide and standard acceptance test methods specified below.  Such testing may be done concurrently with the Contractor's process control testing.  Acceptance test results will be available to the Contractor as soon as possible upon their completion.

Sampling for the determination of aggregate gradation will be from the aggregate cold feed, individual hot bins, or from the combined aggregate just prior to the introduction of the asphalt cement.  All aggregate samples will be split and the second half made available to the Contractor.

Acceptance testing for asphalt cement content will be determined by ATM T-16, ATM T-23 or AASHTO T 164.  Sampling for the determination of asphalt cement content will be from the mixture at the time of placement.

Samples taken for determination of density compliance shall be taken from the finished mat after final rolling.  Acceptance testing for field density will be determined in accordance with ATM T-22.

3.Unacceptable Work or Material.  Any mixture which is contaminated, segregated, or which does not otherwise conform to the Specifications will be rejected and replaced at no additional cost to the Department with conforming material in accordance with Subsection 105-1.11, Removal of Unacceptable and Unauthorized Work.  All costs associated with removal and replacement of unacceptable mixture shall be borne by the Contractor.  At the discretion of the Engineer, unacceptable pavement may be overlaid with acceptable pavement at no additional cost to the Department.

CONSTRUCTION REQUIREMENTS

401-3.01	WEATHER LIMITATIONS.  The mixture shall not be placed on a wet surface, or on an unstable roadbed, when the base material is frozen, or when weather conditions prevent the proper handling, compacting, or finishing of the mixture.  No mixture shall be placed when the surface upon which the pavement is to be placed is at or below 35 F.

401-3.02	BITUMINOUS MIXING PLANTS.  Mixing plants shall conform to AASHTO M 156.

Proportioning (batch) scales shall not be used for weighing material for payment. Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

401-3.03	HAULING EQUIPMENT.  Trucks used for hauling mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime solution or other manufactured asphalt release agent included in the Department's Approved Products List.  Diesel or fuel oil shall not be used.  Each truck shall have a cover of canvas or other suitable material of such size as to protect the mixture from the weather, when required, so that the mixture will be delivered on the road at the proper temperature.

401-3.04	ASPHALT PAVERS.  Asphalt pavers shall be self-propelled units, provided with a heated vibratory screed and equipped with a paver control system which shall automatically control the laying of the mixture to specified transverse slope and specified longitudinal grade.  The paver control system shall be automatically actuated by the use of a mobile string line, ski, or other approved grade follower.  The length of the ski, mobile string line or other device shall be at least 30 feet in length.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation.  The hopper shall be equipped with a distribution system to place the mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Auger extensions shall be within 1.5 feet of the gates.

Extendible wings may be permitted for tapers, guardrail widening and approaches.

The use of a pickup machine to transfer the mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collection of the windrowed material without damage to the underlying course. The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any other detrimental effects are observed.

401-3.05  ROLLERS.  Rollers shall be of the steel wheel and pneumatic tire type, self-propelled, in good condition, capable of reversing without backlash, and operated at speeds slow enough to avoid displacement of the mixture.  The number and weight of the rollers shall be sufficient to compact the mixture to the required density and surface smoothness while it is still in a workable condition, and be capable of maintaining the pace of the paving operation. Specific roller requirements for construction of density "control strips" are further described in Subsection 401-3.12, Compaction.  The use of equipment which results in crushing of the aggregate will not be permitted.

401-3.06	PREPARATION OF EXISTING SURFACE.  When the surface of the existing pavement or old base is irregular, it shall be brought to uniform grade and cross section, as directed.

If determined necessary, the existing surface shall be cleaned of loose material by means of sweeping with a power broom, supplemented by hand sweeping as required.

Contact surfaces of curbing, gutters, manholes, and other structures shall be coated with a thin, uniform coating of prime or tack coat material prior to the asphalt concrete mixture being placed against them.

Surfaces which have received a prime or tack coat shall be allowed to cure, as directed, prior to placement of asphalt concrete mixture.  Surfaces which have received an emulsion tack coat shall be allowed to break prior to placement of asphalt concrete mixtures.

401-3.07	PREPARATION OF ASPHALT CEMENT.  A continuous supply of asphalt cement shall be supplied to the mixer at a uniform temperature, within 25 F of the Job Mix Design mixing temperature.

401-3.08	PREPARATION OF AGGREGATES.  The aggregate for the mixture shall be heated and dried to a temperature compatible with the mix requirements herein specified.  Flames used for drying and heating shall be properly adjusted to avoid damage to the aggregate and to avoid soot or unburned fuel on the aggregate.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5% (by total weight of mix), as determined by ATM T-25.

401-3.09	MIXING.  The aggregate and asphalt cement shall be combined in the mixer in the amounts required to meet the Job Mix Design.  Anti-stripping additive shall be furnished as required.

The materials shall be mixed until a complete and uniform coating of the particles and a thorough distribution of the asphalt cement throughout the aggregate is obtained.  For batch plants, dry aggregate shall be in motion prior to the addition of asphalt cement.  Wet mixing time shall be determined for each plant and for each type of aggregate used.  The minimum percent of coated particles used to establish the mixing time interval shall be 98% using AASHTO T 195.

The temperature of the mixture at the time of mixing shall be as determined by the Job Mix Design.

401-3.10	TEMPORARY STORAGE OF ASPHALT MIXTURE.  Temporary storing or holding of hot mixture in silo type storage bins will be permitted.

All the mixture drawn from the silo type storage bins shall conform to all of the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

401-3.11SPREADING AND FINISHING.  The mixture shall be laid only upon stable surfaces approved by the Engineer, spread and struck off and compacted to the required thickness.  Asphalt pavers shall be used to distribute the mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of Subsection 401-3.13, Joints.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impractical, the mixture shall be spread, raked and luted by hand tools.  For such areas the mixture shall be placed to the required compacted thickness.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge drop-off.  When the pavement edge drop-off exceeds 2 inches, shoulder material shall be placed against the pavement edge.

When multiple lifts are specified in the Contract, the final lift shall not be placed until all lower lifts throughout that segment, as defined by the Paving Plan, have been placed and accepted.

Paving shall not begin until all adjacent concrete curb has been poured and cured for 72 hours or until satisfactory concrete strength is achieved.

Asphalt to be placed over bridge membranes shall not be placed until the membrane has cured to the proper state to prevent damage by the overlaying operation.  Vehicles, except the spreader and trucks used for hauling the asphalt overlay mix, shall not be operated on the membrane.  Paving machines used over the membrane waterproofing shall be rubber tired or rubber tracked.   The Contractor shall adhere to the manufacturer's published minimum and maximum temperature limitations for asphalt overlay material.  Steel-wheeled rollers only shall be used to compact the asphalt paving on the bridge decks.  The use of vibratory rollers, with vibrator on, will not be permitted.

401-3.12	COMPACTION.

General.  Immediately after the mixture has been spread, struck off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.  Rolling shall commence as soon as the rolling does not cause undue displacement, cracking or shoving.  Any displacement occurring as a result of the reversing of the direction of a roller, or from other causes, shall be corrected promptly by the use of rakes and addition of fresh mixture when required.  Care shall be exercised in rolling not to displace the line and grade of the mixture. Rollers shall move at a slow but uniform speed with the drive roll or wheels nearest the paver.

Unless otherwise directed, rolling shall begin at the sides and proceed parallel with the road centerline, each overlapping one-half the roller width, gradually progressing to the crown of the road.  When paving in echelon or abutting a previously placed lane, the longitudinal joint shall be rolled first to provide pinching the material in place.  On super-elevated curves the rolling shall begin at the low side and progress to the high side by overlapping of trips parallel with the centerline.

Along forms, curbs, headers, walls, and other places not accessible to the rollers, the mixture shall be thoroughly compacted with hot hand tampers or with mechanical tampers.  On depressed areas, a trench roller may be used or cleated compression strips may be used under the roller to transmit compression to the depressed area.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

Control by Acceptance Strip.

1.	Control Strips.  A control strip shall be constructed at the start of each course after the plant and equipment are providing a consistent mix, and repeated as ordered whenever:

a.	there is a change in the mix composition,

b.	there is a change in ambient temperature of 30 F or greater, or,

c.	routine tests indicate changes from results found in previous qualifying control strips.

Each control strip shall be constructed with the approved Job Mix Design.  The control strip shall remain in place as a section of the completed Work, provided it complies with requirements for gradations, asphalt cement content, adequacy of mixing and line and grade.  It shall be removed and replaced at the Contractor's expense or accepted to remain in place in accordance with Section 105-1.03, Conformity with Plans and Specifications, and a new control strip constructed if it does not meet specification requirements.  Paving operations may not proceed beyond the control strip until the mixture conformance to Specifications has been confirmed and production paving is authorized.

Each control strip shall be one lane in width, 300 feet in length and shall be of the depth specified for the pavement course concerned.

Initial or breakdown compaction of a layer of the mixture shall be performed with a two (2) axle tandem or a three (3) wheel roller weighing at least 12 tons except that approved vibratory compacting equipment may be used for the initial or breakdown compaction if it is operated according to the procedures designated in the approval.

A pass shall be one movement of a roller in either direction.  A coverage shall be as many passes as are necessary to cover the entire width being paved.  Each coverage shall be completed before subsequent coverages are started.

The initial or breakdown compaction shall be followed immediately by intermediate rolling with a pneumatic-tired roller which exerts a tire pressure of at least 80 psi over the tire contact area.  Coverages with a pneumatic-tired roller shall start when the temperature of the mixture is high as practicable and shall be completed while the temperature of the mixture is at or above 160 F.  Intermediate rolling shall be performed with a two (2) axle tandem roller when breakdown rolling is performed with a pneumatic roller.

Each layer of mixture shall be additionally compacted, without delay, by a final rolling consisting of not less than one (1) coverage with a steel-tired roller weighing not less than 8 tons.  Compaction of the control strip shall commence as soon as possible after placement of the mixture and be continuous and uniform over the entire control strip.

The following rolling and density testing procedures shall be used on the control strip:

a.	Breakdown rolling.  Thirty-second nuclear density counts shall be taken at three (3) randomly selected locations after each roller coverage at each test site.  Rolling shall continue until there is less than 1 pound increase in average density per roller coverage.

b.	Intermediate rolling.  Rolling shall continue until at least three (3) complete coverages have been made and there is less than 1 pound increase in average density per roller coverage.

c.	Finish rolling.  Thirty-second nuclear density counts shall be taken at five (5) randomly selected locations after each roller coverage at each test site.  The average density obtained after the first coverage shall be taken as a new beginning point.  Final rolling shall continue until all roller marks are removed and there is less than 1 pound increase in average density per roller coverage.

d.	Density standard.  One-minute density counts shall be taken at ten (10) randomly selected locations to determine the average density of the control strip.  This is the density standard for the project until a new control strip is constructed.  To confirm the adequacy of the compaction of the control strip, seven (7) 8-inch minimum diameter core samples will be taken at randomly selected locations.  The average density of these cores shall be at least 95% of the maximum specific gravity (as determined by AASHTO T 209) multiplied by 62.4.

2.	Acceptance Strips.  Acceptance density testing will be accomplished while the pavement is hot enough to permit further densification if such is shown to be necessary.

The pavement courses shall be divided into acceptance strips consisting of not more than 500 tons for the purpose of defining areas represented by each series of density acceptance tests.

The types of rollers used and their relative positions in acceptance strip compaction shall be the Contractor's option, provided that at least two (2) coverages of a pneumatic-tired roller having an 80 psi minimum contact pressure are applied.

The density of each acceptance strip will be evaluated based on the results of three (3) tests with a portable nuclear test device performed at randomly selected sites within the acceptance section.  Each test will consist of the average of two (2) 1 minute readings with the gauge rotated 90 between readings.  The average density obtained for the three (3) test in each acceptance strip shall be at least 98% of the mean density obtained in the approved control strip.  In addition, each individual test value obtained within an acceptance strip shall be at least 95% of the mean density of the strip.

If either the average density of the acceptance strip or an individual test value does not meet the density requirements, the Contractor shall continue compactive effort until the required density is obtained.

After the required density has been attained in the acceptance strips, further finish rolling may be necessary to remove roller marks or other surface irregularities and to meet the required surface tolerances.

401-3.13	JOINTS.  Joints shall be made in such manner as to ensure a continuous bond between old and new sections of the course.  All joints shall present the same texture and smoothness as other sections of the course.

A thin tack coat of asphalt cement or emulsion shall be sprayed on all cold joints and allowed to break prior to placing fresh mixture against the joint.

Transverse joints shall be formed by cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.

The longitudinal joints in one (1) layer shall offset those in the layer immediately below by approximately 6 inches.  However, the joints in the top layer shall be at centerline or lane lines.  Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset not more than 1 foot.

Pavement that is 1.5 inches or thicker shall be constructed with a modified wedge joint the entire length of the face of the exposed longitudinal joint between adjacent travel lanes.  The taper shall have a maximum horizontal to vertical slope of 3:1 at the bottom and shall be vertical at the top for a height equal to the largest aggregate size.

Improperly formed joints resulting in surface irregularities shall be removed, full depth, replaced with new material, and thoroughly compacted.  Attempting to roll out an improper joint after the material has cooled below 160 F shall not be allowed.  All pavement removal shall be precut to a neat line using a power driven saw.

401-3.14	SURFACE TOLERANCE.  The surface will be tested after final rolling at selected locations using a 10 foot straightedge.  The variation of the surface from the testing edge of the straightedge between any two (2) contacts with the surface shall not exceed 3/16 inch.

401-3.15	PATCHING DEFECTIVE AREAS.  Skin patching will not be permitted.  Defective materials shall be removed for the full thickness of the course.  The pavement shall be cut so that the sides are perpendicular and parallel to the direction of traffic and so that the edges are vertical.  Edges shall be tack coated with asphalt cement or emulsion.  Fresh mixture shall be placed in sufficient quantity so that the finished surface will conform to grade and smoothness requirements.  The mixture shall be compacted to the density specified herein.

401-4.01	METHOD OF MEASUREMENT.  Asphalt concrete pavement and asphalt cement will be measured by the ton or by the square yard in accordance with Section 109.  The tonnage used shall be the weight used in the accepted pavement and no deduction will be made for the weight of asphalt cement and anti-stripping additive in the mixture.

The method of measurement to be used for Asphalt Cement will be limited to one (1) of the following procedures.  The Engineer shall approve in writing the procedure to be used.  The method used initially must be the one used for the duration of the Project.

1.	Supplier's invoices minus waste, diversion and left-over.  This method may be used on projects where deliveries are made in tankers and the plant is producing material for one (1) project only.  Tank stickings will be used to compute left-over.  Waste and diversion will be computed in a manner to be determined by the Engineer.

2.	The weight of asphalt cement shall be calculated using the percent of asphalt cement multiplied by the total tonnage represented.  Percent of asphalt cement shall be determined by ATM T-23.

The Engineer may direct at any time that tankers shall be weighed before and after unloading in the presence of the Engineer.  If the weight determined at the Project varies more than 1% from the invoice amount, payment will be based on the weight determined at the Project.

401-5.01	BASIS OF PAYMENT.  The accepted quantity will be paid for at the Contract unit price for the pay item listed below, complete in place.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $3.75 per 0.25% additive per ton of asphalt cement.

A change order/directive is not required for anti-stripping additive.  The approved mix design will initiate Item 401(4), Anti-Stripping Additive at the prescribed rate. (5/3/93)R169

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1)	Asphalt Concrete Pavement,

Type ___	Ton

401(2)	_____ Asphalt Cement	Ton

401(4)	Anti-Stripping Additive	Contingent Sum

(2/1/94)M61

SECTION 402

TACK COAT

SPECIAL PROVISIONS

402-2.01	ASPHALT MATERIAL.

Change "CSS-1" to "STE-1" in the first paragraph.

402-3.04	DILUTION OF ASPHALT MATERIAL.

Delete this Subsection in its entirety.

402-3.05	APPLICATION OF ASPHALT MATERIAL.

Modify the application rate given in the first paragraph from "0.05 to 0.10 gallons" to "0.02 to 0.10 gallons".

402-5.01	BASIS OF PAYMENT.

Add the following pay item:

Pay Item No	Pay Item	Pay Unit

402(3)STE-1 Asphalt for Tack CoatTon

SECTION 501

STRUCTURAL CONCRETE

STANDARD MODIFICATIONS

501-3.01	PROPORTIONING.

Under Item 1., Determining the Proportions and Batch Weights, add the following to the second paragraph:

Material properties shall be determined in accordance with the following test methods:

| PROPERTY | TEST METHOD |
| --- | --- |
| Slump | AASHTO T 119 |
| Air Content | ATM T-8 |
| Compressive Strength | AASHTO T 22 |
| Unit Weight | AASHTO T 121 |
| Cement Content | AASHTO T 121 |

(7/2/93)M51

SPECIAL PROVISIONS

501-3.01	PROPORTIONING.

Revise this Section as follows:

In Table 501-1, Class of Concrete, under the category Coarse Aggregate Gradation, AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S and W concrete.  (9/1/89)R37

501-3.02	BATCHING.

Add the following to Item 5. Batching:

Furnish the mix design number and a list of all ingredients, their individual weights, and moisture content of the various aggregates and the individual truck water meter reading when batched, for each truck load or batch of concrete supplied.  (7/2/93)S54

501-3.06	PLACING CONCRETE.

Delete the last sentence of Item 2., Pumping Concrete, and substitute the following:

Concrete samples for testing shall be taken at the discharge end of the pipe.  The Contractor shall provide the necessary samples of concrete at the direction of the Engineer or his representative. (7/2/93)S65

SECTION 503

REINFORCING STEEL

Standard Modifications

503-3.05  Splicing.

Delete the first and second paragraphs and substitute the following:

Lap splices for reinforcing bars shall be as shown on the Plans or as directed.  (5/12/89)M17

SECTION 603

CULVERTS AND STORMDRAINS

SPECIAL PROVISIONS

603-1.01  DESCRIPTION.

Add the following:

This Work shall also consist of installing culvert marker posts.

603-2.01  MATERIALS.

Add the following:

Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts.  The color shall be blue with no other markings.  The 3-1/2 inch by 72 inch post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

603-3.06  CULVERT MARKER POSTS.

Add the following subsection:

Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two inches of post shall remain above the ground after driving.

603-4.01  METHOD OF MEASUREMENT.

Add the following:

Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.

Add the following:

Culvert marker posts will not be paid for directly, but will be subsidiary to the pipe item.

(10/1/91)R42

SECTION 604

MANHOLES AND INLETS

STANDARD MODIFICATIONS

604-2.01	MATERIALS.

Add the following to the list of materials:

Flexible Watertight Gaskets 705-2.05

(7/2/93)M52

SPECIAL PROVISIONS

604-3.01	CONSTRUCTION REQUIREMENTS.

Add the following:

All curb inlet structures shall have a 3 inch formed hole approximately 2 feet below the top of casting on the Project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  The Contractor shall be responsible for keeping the openings functional, which may require temporary dikes, RMC extensions, etc., as necessary. These holes shall be filled with grout upon final paving.

604-4.01  METHOD OF MEASUREMENT.

Add the following:

Frames, grates and lids will not be measured for payment.

604-5.01 BASIS OF PAYMENT.

Add the following:

Frames, grates and lids are subsidiary to the drainage structure.

SECTION 606

GUARDRAIL

SPECIAL PROVISIONS

606-1.01	DESCRIPTION.

Add the following:

This Work shall also consist of installing breakaway cable terminals at the locations shown on the Plans.

606-2.01	MATERIALS.

Add the following:

Flexible markers shall have yellow reflective sheeting and be one (1) of the following types:

1.	"Guardrail Delineator Post" manufactured by Carsonite International, 2900 Lockheed Way, Carson City, Nevada 89701.

2.	"Guardrail Delineator" manufactured by Safe-Hit Corporation, 1930 West Winton Avenue, Building 11, Hayward, California 94545.

3.	"Flex-o-Guide", Model EY426 manufactured by Flexible Safety Zoning Company, 4152 Warren Avenue, Hillside, Illinois 60162.

606-3.01	POSTS.

Add the following:

The foundation type for the breakaway cable terminal posts shall be the steel post embedment for soil or concrete as shown on Standard Drawing G-18.00S.

All other guardrail shall have a wood post foundation as shown on Standard Drawing G-04.04W and G-14.04W.

606-3.02	RAIL ELEMENTS.

Add the following:

Guardrail elements shall be factory bent for all radii less than 75 feet.

606-3.03	REMOVAL AND RECONSTRUCTION OF GUARDRAIL.

Add the following:

Guardrail removed and to be replaced shall have the entire new run installed within 7 calendar days after removal.

606-3.06	FLEXIBLE MARKERS.

Add the following Subsection:

For each breakaway cable terminal, a flexible marker shall be installed at the terminal end, attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.  The flexible markers shall have a minimum of 21 inches of marker extending above the top of the guardrail.  The reflective tape shall face the nearest oncoming traffic.

606-3.07	EMBANKMENT WIDENING.

Add the following Subsection:

Embankment widening for guardrail end treatments shall be constructed with usable excavation material meeting the requirements of select material, Type C.

606-3.08	LENGTH OF NEED VERIFICATION.

Add the following Subsection:

After shaping the slopes and staking all proposed guard rail locations, the Contractor shall notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine that additional guard rail is necessary, and the Contractor shall comply without delay.

606-4.01	METHOD OF MEASUREMENT.

Delete the third paragraph and replace with the following:

Breakaway cable terminals will be measured per each installation.

606-5.01	BASIS OF PAYMENT.

Add the following:

Payment for Item 606(8), Breakaway Cable Terminal, will be full compensation for all labor, equipment and materials required for installations, including anchor cable assembly, terminal posts, terminal end, flexible marker and all associated hardware.  Rail elements, standard posts, and blocking for breakaway cable terminals will be paid under Item 606(1), W-Beam Guardrail.

Add the following pay item:

Pay Item No	Pay Item	Pay Unit

606(8)Breakaway Cable TerminalEach

SECTION 608

SIDEWALKS

SPECIAL PROVISIONS

608-2.01	MATERIALS.

Add the following:

AC-5 asphalt cement shall be used for the asphalt concrete pavement mix for asphalt sidewalks, and shall conform to the requirements of Subsection 702-2.01, Asphalt Cements. Aggregate shall meet the gradation requirements of Subsection 703-2.04, Aggregate for Plant Mix Asphalt Pavement, for Asphalt Concrete Type II.  In addition, the asphalt concrete shall conform to the following:

Marshall Stability, pounds, minimum	1000 lbs

Voids, Total Mix, 	2-5%

Compaction Blows per Side 	50

The Contractor shall submit a job mix design in accordance with Subsection 401-2.01, Composition of Mixtures.

608-3.02	ASPHALT SIDEWALKS.

Add the following:

Asphalt concrete used for sidewalks or pathways shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface. (9/1/89)

608-4.01	METHOD OF MEASUREMENT.

Add the following:

Additional asphalt pavement used for matching existing surfaces such as paved parking lots behind a new sidewalk/pathway will be measured and paid under this Section.

608-5.01	BASIS OF PAYMENT.

Add the following:

Asphalt concrete for asphalt sidewalks will be paid by the ton of mixture placed, with no separate payment made for asphalt cement or anti-stripping additives.  Bed course materials, as detailed on the Plans, will be furnished, placed and paid under their respective bid items.

SECTION 609

CURBING

STANDARD MODIFICATIONS

609-2.01	MATERIALS.

Replace paragraphs 2, 3, and 4 with the following:

Concrete shall conform to Section 501, Structural Concrete, Class A, except that the slump shall be less than 2 inches for concrete placed by the extrusion or slip-form process.

(7/2/93)M53

SPECIAL PROVISIONS

609-3.04	CURB RAMPS.

Add the following:

Curb ramps adjacent to concrete sidewalks shall have pigment thoroughly mixed to a depth of 1/2 inch.  Color in the dry state shall closely match FED-STD-30152 (Brick Red).  Curb ramps adjacent to asphalt pathways shall have no added coloring.

(8/25/92)R162

SECTION 615

STANDARD SIGNS

SPECIAL PROVISIONS

615-2.01	MATERIALS.

Add the following to the end of the first sentence of the fifth paragraph:

"and the Alaska Traffic Manual."

Delete paragraphs 7 and 8 (the fourth and fifth paragraphs on page 315) and substitute the following:

Sign posts and bases shall be of the types specified.  Structural aspects of design and materials for sign supports shall comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaries and Traffic Signals.

Concrete for steel-reinforced slip base and breakaway base foundations shall be Class A, conforming to the requirements of Section 501, Structural Concrete. Concrete for other sign foundations may be Class W.

(5/7/91)S42

Add the following:

Wide flange posts shall also be hinged and equipped with the multi-directional breakaway load concentration coupler hinge plates.

615-3.01	CONSTRUCTION REQUIREMENTS.

Add the following to the sixth paragraph:

When existing signs are to be salvaged the remaining foundation shall be removed or obliterated to the level of the surrounding grade or if located within the roadway structural section shall be disposed of in a manner as approved by the Engineer.  All signs and posts at a single installation shall be considered as  one (1)  unit.

Add the following after the sixth paragraph:

Salvaged sign panels shall be delivered to the State Maintenance Yard in Homer.  Contact George Church at 262-2199 for coordination.

615-3.02	SIGN PLACEMENT AND INSTALLATION.

Add the following:

All existing signs shall not be removed until the new signs have been installed.  If necessary, they may be temporarily relocated to a location approved by the Engineer.  They shall be maintained until they are no longer needed.

Prior to mounting the sign panel, the Contractor shall mark the date of installation on the back of the sign.  Installation dates shall be written in the format of month/day/year, using permanent marker, with numbers a minimum of 3 inches in height, so as to be readable from the roadside after installation.

615-4.01	METHOD OF MEASUREMENT.

Add the following at the end of the second paragraph.

Concrete used for sign bases will be considered subsidiary to other Work under this Section and will not be measured for payment.

615-5.01	BASIS OF PAYMENT.

Add the following:

Obliteration of foundations shall be included in Item 615(7) Salvage Signs.

Maintaining existing signs until they are no longer needed and temporary relocation of existing signs will not be paid directly, but shall be considered subsidiary to Item 615(1) Standard Signs.

(2/14/92)R50

SECTION 618

SEEDING

SPECIAL PROVISIONS

618-1.01	DESCRIPTION.

Delete this Subsection and substitute the following:

All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded.  This Work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01	MATERIALS.

Add the following to the list of material specifications:

Mulch                      Subsection 727-1.01

618-3.01	SOIL PREPARATION.

Add the following:

Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be covered with topsoil in accordance with Section 620, Topsoil, and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as topsoil is placed on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and shall not encroach onto the wetlands.  The performance of this Work is incidental to seeding and will not be paid for directly.

618-3.03	APPLICATION METHOD.

Delete the following in the first sentence of subparagraph b. under Item 1., Hydraulic Method:

"Item 619(1),".

Add the following:

Seed, mulch and fertilizer shall be applied as shown in the following table per 1,000 square feet.  The mulch rate shown is a minimum, and may be increased in accordance with the manufacturer's recommendations.  If the hydraulic method for seed and mulch is used, it shall be made in  one (1) application. All fertilizer shall be applied by the hydraulic method.

APPLICATION

Item	Ingredients 	Rate per MSF

Seed Mix	Red Fescue (Arcta red)	0.45 lb.

Kentucky Bluegrass (Nugget)	0.45 lb.

Annual Ryegrass (Lolium)	0.10 lb.

TOTAL 	1.00 lb.

Mulch	  35.0 lbs.

Fertilizer	20-20-10 	12.0 lbs.

The Contractor shall not remove the required tags from the seed bags.

618-4.01	METHOD OF MEASUREMENT.

Delete the second paragraph and substitute the following:

Seeding by the pound will be the number of pounds of seed (Dry Measure) accepted in place.  The amount of mulch, fertilizer and water for application used in this Work, including any required reseeding, will be subsidiary to seeding and will not be measured separately for payment.

Delete the last paragraph.

618-5.01	BASIS OF PAYMENT.

Add the following:

Fertilizer, mulch and water for application, including any required reseeding, will not be paid for directly, but will be subsidiary to Item 618(2), Seeding.

The Work described under Subsection 618-3.01, Soil Preparation, will not be paid for directly but will be subsidiary to seeding.

Water required for the hydraulic method of application will not be paid for separately, but will be subsidiary to seeding.

SECTION 620

TOPSOIL

SPECIAL PROVISIONS

620-2.01	MATERIALS.

Add the following:

Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

620-5.01	BASIS OF PAYMENT.

Add the following:

Payment for the addition of limestone, if required, will be subsidiary to Item 620(1), Topsoil.

SECTION 627

WATER SYSTEM

SPECIAL PROVISIONS

627-3.05.

Add the following:

It shall be the Contractor's responsibility to protect and maintain all valves and valve boxes in the Project area in an operable condition during all phases of construction.

The Contractor shall schedule a field inspection with the City of Homer and the Engineer to witness and document the condition of the existing valves and valve boxes prior to adjustment.  The Contractor shall provide the City of Homer 48 hours advance written notice of the scheduled field inspection and provide the Engineer with a copy.

The City of Homer shall locate and inspect the existing valves and valve boxes to insure it is in working order.  Cleaning or repair to the valves or valve boxes prior to adjustment will be accomplished by the City of Homer at no cost to the Contractor.

Failure of the Contractor to schedule and participate in the valve and valve box inspections shall result in the Contractor forfeiting all rights to claim that the valves were damaged prior to his beginning Work.

Valves or valve boxes damaged during construction of the Project shall be repaired by the Contractor at no additional expense to the Owner.

The Contractor shall schedule a final field review with the City of Homer and the Engineer upon completion of the valve or valve box adjustments.

627-4.01	METHOD OF MEASUREMENT

Add the Following:

6.	Adjustment of Valve Box.  Measurement will be the number of valve boxes adjusted to final grade only.

SECTION 639

DRIVEWAYS

SPECIAL PROVISIONS

639-1.01	DESCRIPTION.

Add the following:

This item also consists of the Work involved in the excavation, forming, shaping and construction of public approaches.

639-2.01	METHOD OF MEASUREMENT.

Add the following:

Public approaches will be measured per each constructed as shown on the Plans, or as directed.

639-3.01	BASIS OF PAYMENT.

Add the following:

Payment for public approaches will be full compensation for furnishing all equipment and labor necessary to complete the Work as indicated.  Materials required to construct public approaches will be paid for separately under the respective items listed in the bid schedule.

Add the following pay item:

Pay Item No	Pay Item	Pay Unit

639(3)Public ApproachEach

SECTION 640

MOBILIZATION AND DEMOBILIZATION

SPECIAL PROVISIONS

640-2.01	METHOD OF MEASUREMENT.

Delete Item 3. and substitute the following:

3.	When the letter of Project completion has been issued and the Contractor has made all the required submittals, the remaining balance of the amount for this item will be paid.  (5/7/91)

Delete Section 641 in its entirety and substitute the following:

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

SPECIAL PROVISIONS

641-1.01	DESCRIPTION.  This Work shall consist of planning, providing, and maintaining control of erosion, water pollution, and hazardous materials contamination.

641-1.02	SUBMITTALS.  Five days prior to the Preconstruction Conference, the Contractor shall submit for acceptance a plan for accomplishment of temporary and permanent erosion and pollution control measures throughout the life of the Contract.  This plan shall, as a minimum, include the following:

1.	Notice of Intent (NOI) to utilize the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska.

2.	Stormwater Pollution Prevention Plan (SPPP).

3.	Hazardous Material Control Plan (HMCP).

The NOI and SPPP shall be prepared in accordance with the requirements of the "NPDES General Permit for Alaska" (General Permit) and the "Contractor Guidance for Preparing and Executing Storm Water Pollution Prevention Plans" (Stormwater Manual).  When completing the NOI, the Contractor is the "Operator, Discharger, and Permittee" and the Department is the "Owner".

The HMCP is the Contractor's plan for the containment, cleanup and disposal of waste material, as well as petroleum products or other hazardous substances generated by construction equipment or activities.  A list of quantities and types of equipment and materials available on site to be used for hazardous substance containment and cleanup shall be included.

The Contractor shall mail the NOI to the US Environmental Protection Agency via Certified Mail, and shall send copes to the Engineer and the Alaska Department of Environmental Conservation Stormwater Coordinator.  Earth disturbing Work shall not begin until 48 hours after the NOI has been postmarked.

The Contractor shall submit required amendments to the NOI or SPPP to the Engineer at least 14 days prior to performing Work affected by such amendments.

The Contractor shall submit a Notice of Termination (NOT) in accordance with the General Permit to the Engineering following completion of the final stabilization of the Project.

641-2.01	CONSTRUCTION REQUIREMENTS.  The Contractor shall comply with all requirements of the NPDES General Permit for Alaska.  The Contractor shall provide the Engineer with a copy of all inspection reports required by the Permit within 3 days of the inspection date.  Compliance with the NPDES General Permit for Alaska does not reduce the Engineer's authority to direct additional erosion control measures deemed appropriate.

The Contractor shall be responsible for the containment, cleanup and disposal of all construction related discharges of petroleum fuels, oil and/or other substances hazardous to the land and water.  Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

641-3.01	METHOD OF MEASUREMENT.  Erosion and Pollution Control Administration will not be measured for payment.

Erosion and Pollution Control will be measured in a manner specified in the order authorizing the Work.

641-4.01	BASIS OF PAYMENT.  Item 641(1), Erosion and Pollution Control Administration will be full compensation for administration or erosion control, including preparing and amending plans, inspecting, monitoring, reporting and record keeping.

Item 641(2), Erosion and Pollution Control will be full compensation for providing all required labor, equipment and materials.

Failure to comply with the requirements of the NPDES General Permit for Alaska within 24 hours notice by the Engineer will result in withholding an amount equal to 5% of the total amount earned from all subsequent progress payments. This retainage will be released by the Engineer upon satisfactory completion of the requirements of the General Permit.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution

Control Administration	Lump Sum

641(2)	Erosion and Pollution	Contingent

Control	Sum

SECTION 642

CONSTRUCTION SURVEYING

SPECIAL PROVISIONS

642-1.01	DESCRIPTION.

Add the following to the first paragraph:

The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix A.

642-3.01	CONSTRUCTION REQUIREMENTS.

Add the following to the third paragraph:

The Contractor shall reference the existing centerline at 100 foot intervals on tangents, 50 foot intervals on curves. The reference stakes shall be a minimum size of 1 inch by 2 inches and shall show the offset, station and a cut or fill elevation reference.  This information shall be transmitted to the Engineer a minimum of 7 days prior to disturbing the existing pavement.  The Engineer will use this information to create the roadway profile grade.

The Contractor shall provide horizontal curve reference stakes showing begin and end of superelevation transitions and full superelevation lengths.

Add the following:

12.	The Contractor's survey crews shall comply with approved traffic control plans. Crews shall coordinate their activities with the Project's Worksite Traffic Supervisor.

The Contractor shall locate and record the following objects that are within, or near the edge of, the existing right-of-way limits to determine encroachment.  The locations of the objects shall be identified with a construction centerline station and offset to as many points as necessary to determine whether the object extends into the right-of-way area.  The indicated stations are approximate.

1.	STA 6208+00 RT - Fence

2.	STA 6237+00 LT - Parking lot

3.	STA 6277+50 RT - Building

4.	STA 6287+00 LT - Building

5.	STA 6290+00 LT - Structure

6.	STA 6306+25 RT - Building

7.	STA 2+50 RT - Fence

8.	STA 187+50 LT - Building

9.	STA 220+00 LT - Building

The Contractor shall locate and record any additional objects that are identified by the Engineer.

642-4.01	METHOD OF MEASUREMENT.

Add the following:

Pay Item 642(2), Three Person Survey Party, shall be used only for location of objects  to determine right-of-way encroachment and any other extra, additional or unanticipated Work made necessary by changes in the Project as directed by written order of the Engineer.

642-5.01	BASIS OF PAYMENT.

Add the following:

If additional Work as stated above is performed by a two-person survey party, hours paid for under Item 642(2), Three Person Survey Party, will be 75% of the hours worked.  If additional Work as stated above is performed by only one (1) person, hours paid for under Item 642(2), Three-Person Survey Party, will be 32% of the hours worked.  (10/1/91)

SECTION 643

TRAFFIC MAINTENANCE

SPECIAL PROVISIONS

643-1.02	TRAFFIC CONTROL PLAN.

Add the following to the first paragraph:

A traffic control plan shall also indicate the method of safely routing pedestrian traffic through or around the construction zone.

If the Contractor elects to use the TCPs provided in the plan set, then the Contractor shall supplement those TCPs with provisions for pedestrian traffic for approval by the Engineer.

Delete the second paragraph and substitute the following:

TCPs are required for each Work site.  TCPs included in the Plans are acceptable for use with the concurrence of the Engineer.  The Contractor may elect to modify them or design alternative TCPs.  All modified and/or alternative TCPs shall be submitted for approval of the Engineer.  The Contractor shall allow 1 week for review of any submitted TCP or for each subsequent correction.  Changes in the TCP resulting from unforeseen circumstances may be allowed during construction, provided a minimum of 48 hours are allowed for review, and the changes are approved by the Engineer.  The Contractor shall respond and make field changes as the Engineer directs.

Add the following to the third paragraph:

All TCPs submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24 hour telephone number of the Worksite Traffic Supervisor.

Add the following to the fourth paragraph:

Plan sheets developed on AutoCad can be made available, upon request, for use in preparing TCPs.

643-1.03	WORKSITE TRAFFIC SUPERVISOR.

Delete the second sentence of the first paragraph and substitute the following:

The Worksite Traffic Supervisor shall meet the following minimum requirements:

1.	Be currently certified as a Worksite Traffic Supervisor by the American Traffic Safety Services Association (ATSSA), or,

2.	Be currently certified as a Work Zone Traffic Safety Specialist or a Signs and Lines Specialist by the International Municipal Signal Association (IMSA), or,

3.	Be currently certified as a Worksite Traffic Technician by ATSSA.

If the individual is certified under Items 2 or 3 above, the Contractor shall submit documentation that the individual has also obtained:

1.	A minimum of 1 year of supervisory level Work in worksite traffic control, or,

2.	One year of having been in responsible charge of such Work.  The term "in responsible charge" shall be construed to mean having been in a position of accountability for the selection of devices and for their placement in the traffic control system, or for the continued operation of the system.  Having persons that actually perform the labor under one's control would satisfy this requirement.

643-1.04	CONSTRUCTION PHASING PLAN

Delete this Subsection in its entirety and substitute the following:

A Construction Phasing Plan shall be submitted by the Contractor at least 5 working days prior to the preconstruction conference for approval by the Engineer.  The Construction Phasing Plan shall comply with the requirements of subsection 643-3.08 Construction Sequencing.

643-1.05	public relations

Add the following Subsection:

The Contractor shall provide a Contractor Spokesperson to accomplish the Work outlined in this Subsection.  The Contractor Spokesperson shall have qualifications and responsibilities as outlined in Section 108-1.03.

This Contractor Spokesperson shall be responsible for the following tasks:

1.	Public Meetings:  Prepare a project description for presentation at meetings of business owners along the Project and the general public.  One (1) meeting will be conducted for the general public.  The meeting will be held 2 weeks prior to the beginning of construction.

Two (2) meetings will be conducted for business owners.  The first will be held 1 week prior to the beginning of construction.  The remaining meeting will be held approximately one-third of the way through construction.

2.	Mailouts:  Design and distribute two (2) mailouts which shall be approved by the Engineer.  The mailouts shall contain:

a.	a map of the Project,

b.	the construction schedule,

c.	the Contractor's project office phone number,

d.	the Engineer's project office phone number,

e.	a 24-hour contact phone number for Contractor,

f.	a 24-hour contact phone number for the Engineer,

g.	a listing of locations where current Project information may be obtained,

h.	a description of impacts to abutting property accessing Sterling Highway, and

i.	an outline of the impacts to the traveling public on Sterling Highway.

The two (2) mailouts shall be sent to all addresses within zip code 99603 and shall be distributed at the following times:

a.	2 weeks before construction begins, and

b.	approximately at the one-third point.

643-2.01	MATERIALS.

Add the following under Item 3., Barricades and Vertical Panels:

Type III barricades shall have a minimum width of 8 feet.

Delete numbered paragraph 8. in its entirety and substitute the following:

8.	Temporary Pavement Markings.  Work zone pavement markings shall be either paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08, performed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.  The markings shall be applied in accordance with Section 670, Traffic Markings, and the manufacturer's recommendations.

Add the following:

12.	Portable Changeable Message Board Signs.  Portable changeable message board signs shall be truck or trailer mounted with a self-contained power supply for the sign and shall have the following features:

a.	Message sign panel size of 5 foot - 8 inch by 7 foot - 5 inch, minimum, with a capacity for a three (3) line message.

b.	Eight (8) character display per message line.

c.	Message modules containing at least 36 different preprogrammed messages (three line displays) to be selected by the Engineer.

d.	The capacity to create, preview, and display new messages and message sequences.

e.	A waterproof, lockable cover for the controller keyboard.

f.	An operator's manual, a service manual, and wiring diagram.

g.	Quick release attachments on display panel cover.

h.	Variable flash and sequence rates.

i.	Manual and automatic dimming capability on lamp bulb matrix models.

j.	The ability to mount at least 7 feet above the pavement to the bottom of the message sign panel.

k.	The capacity to operate with a battery pack for 2 hours under full load.

643-3.02	ROADWAY CHARACTERISTICS DURING CONSTRUCTION.

Add the following to the first paragraph:

The maximum spacing between channelizing devices in a taper should be approximately equal in feet to the speed limit.

Delete the second paragraph.

Add the following after the last paragraph:

While the roadway is in an unpaved condition, all no-passing zones shall be identified by Temporary R4-1 signs (DO NOT PASS).  No-passing zones shall be identified by the Contractor in accordance with the Alaska Traffic Manual (ATM).

During paving operations, intersections shall not be closed for a period longer than 30 minutes.

643-3.03	PUBLIC NOTICE.

Add the following:

Advertisements: The Contractor shall run 1/16 page newspaper advertisements for a minimum of 1 week in advance of commencing construction, resuming construction after seasonal suspension, or any scheduled delay, or closure of driving lanes within the Project corridor.  The Contractor shall then run continuous 1/16 page newspaper advertisements for the duration of that delay, or closure.  The advertisements shall be published in the Anchorage Daily News, Homer News and Peninsula Clarion.

The Contractor shall indicate on the ad order a first preference for the local news section and an exclusion for the classified section.  These advertisements shall have the Project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a 24 hour "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status. Advertisements shall be promptly canceled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least 48 hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

A change order will not be required to initiate newspaper advertisements.

Weekly Notices:  Write and submit weekly Public Information Notices that identify road closures, restriction to traffic, and detours.  These notices shall be in a format approved by the Engineer and telephone numbers for additional information.  The Notices shall be distributed to emergency service providers (police and fire), school bus operator, Homer Public Works Department, Central Charter Booking Agency, Homer Chamber of Commerce, Harbormaster, all Homer radio stations (KWVV, KPEN, KGTL and KBBI), Homer News and the Peninsula Clarion.  Notices shall be submitted at the following times:

1.	1 week prior to the beginning of construction,

2.	on Wednesday of each week during construction, and

3.	prior to any major change or disruption to traffic or local access.

Provide daily information to those media which do non-paid public service road reports.

643-3.04	TRAFFIC CONTROL DEVICES.

Delete numbered paragraph 4., Work Zone Pavement Markings, in its entirety.

Delete Item 1. Embankments, and substitute the following:

1.	Embankments.  For roadways with a current Average Daily Traffic (ADT) greater than 4000, a portable concrete barrier shall be installed when a slope steeper than 3:1 exists for more than 12 consecutive hours within the following distances from the edge of traveled way:

| POSTED SPEED LIMIT | EXCAVATION AREAS | FILL AREAS |
| --- | --- | --- |
| 55 MPH | 20 feet | 26 feet |
| 45 to 50 MPH | 18 feet | 24 feet |
| 40 MPH or less | 14 feet | 16 feet |

The portable concrete barriers shall have a minimum clearance of 2 feet from the Work area and/or hinge point to allow for deflection if struck.  Barrier reflectors shall be mounted on the face of barrier adjacent to traffic on 50-foot centers a minimum height of 18 inches above the surface of the roadway.

For roadways with side slopes of 10:1 or flatter, the ends of portable concrete barriers shall be flared away from the roadway in accordance with the following:

| ADVISORY OR POSTED SPEED | SHY LINE1 AND FLARE RATE INSIDE SHY LINE | TOTAL OFFSET2 AND FLARE RATE OUTSIDE SHY LINE | ROADWAY APPROACH LENGTH3 |
| --- | --- | --- | --- |

| 55 MPH | 8.0 ft | 26:1 | 22 ft | 17:1 | 82 ft |
| --- | --- | --- | --- | --- | --- |
| 45-50 MPH | 6.5 ft | 21:1 | 18 ft | 14:1 | 67 ft |
| 35-40 MPH | 5.0 ft | 17:1 | 14 ft | 11:1 | 52 ft |
| 30 MPH | 3.5 ft | 13:1 | 14 ft | 8:1 | 52 ft |

Notes:

1.	Shy line is measured from the edge of traveled way.

2.	Total offset values are from the edge of traveled way to the end of the portable concrete barrier.

3.	Roadway approach length is the distance required at the end of the portable concrete barrier where a roadway side slope of 10:1 or flatter shall be maintained.

If the portable concrete barrier cannot be flared as indicated above, or for roadways with side slopes steeper than 10:1, a sloping end section for posted speed limits of 35 MPH or less, or a temporary crash cushion for posted speed limits 40 MPH or greater shall be used.

Add the following after the first sentence of the first paragraph under item 5., Flagging:

Each flagger shall be illuminated from the front to a level of light intensity not less than 1 footcandle during hours of darkness.

Flaggers shall wear reflective clothing with markings on arms, legs and head.  Flaggers directing traffic shall wear orange gloves and orange helmets as approved by the Engineer.  Gloves and helmets shall not be in faded or dirty condition such that their effectiveness is impacted.

Add the following after the last paragraph of item 5., Flagging:

Changeable message boards as described in Subsection 643-2.01 shall be used to warn drivers of road closures, phase changes and changed conditions.

643-3.06  Traffic Price Adjustment.

Add the following:

A change order is not required for traffic price adjustment, the Notice to Proceed shall constitute the notice required to initiate traffic price adjustment. (12/8/92)R168

643-3.07	MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK.

Delete the first sentence and substitute the following:

The Contractor shall schedule a preliminary meeting with the Engineer and Maintenance and Operations to take place approximately 1 month prior to seasonal suspension of Work, or no later than September 1.  This meeting shall be to outline the Work the Contractor expects to complete before shutdown and the condition the roadway is to be in.  A winter shutdown traffic control plan shall be submitted to the Engineer at this preliminary meeting.

643-3.08	construction sequencing

Delete this subsection in its entirety and replace with the following:

1.	General.  Rehabilitation of Sterling Highway primarily includes four (4) types of Work:  excavation and replacement of base material including crushed aggregate and asphalt (Phases A and B), cold planning and mixing the recycled asphalt into the crushed aggregate followed by repaving (Phase C), and overlayment of new asphalt pavement onto existing pavement (Phases D and E).  Utility installation and replacement is required at various locations within the Project.  Replacement of base and regrading is required in a limited area of Phase D.

Allowable traffic restrictions for any of the above operations are as stated in Tables 643-(1-5).  Additional restrictions are stated within the Special Provisions and on the Plans.

Tables 643(1-5) have periods which allow traffic restriction (either full or one lane closures) and periods when two-way traffic must be maintained.  Allowable traffic delay during restricted periods is 15 minutes.

The Contractor may work on only one (1) of the Phases A, B or C at any time.  Contractor may concurrently Work on Phase D or E concurrently with Phase A, B or C.  Phases D and E may be constructed concurrently. Only two (2) phases may be under construction at the same time.

TCPs are required for each Work site.  All modified and/or alternative TCPs shall be submitted for approval of the Engineer.  The Contractor shall allow 3 weeks for review of any submitted TCP or 1 week for each subsequent correction.  Changes in the TCP resulting from unforeseen circumstances may be allowed during construction provided a minimum of 48 hours are allowed for review and the changes are approved by the Engineer.

2.	Hours of Work:

Night Work (Phases A and B) shall mean from 10:00 p.m. to 6:00 a.m. the following morning Monday, Wednesday, and Thursday nights and 11:00 p.m. to 6:00 a.m. the following morning on Tuesday night.

Night Work (Phases C, D and E) shall mean from 8:00 p.m. to 6:00 a.m. the next morning Monday, Wednesday and Thursday nights and 11:00 p.m. to 6:00 a.m. the following morning Tuesday night.

Weekends shall mean from 6:00 a.m. Friday to 10:00 p.m. Monday for Phase A and B and to 12:00 noon Monday for Phases C, D and E.  Memorial Day, Independence Day and Labor Day holidays, as defined in Subsection 101-1.27, Holidays, shall extend the weekend for 1 day (to Tuesday 12:00 noon for Phases A and B and 10:00 a.m. for Phases C, D and E).  No restrictions to traffic shall be allowed during weekends.

3.	Closing Section of Road:  Road closures shall be limited to Phase A and B between Sta. 6199+00 and Sta. 6249+50.  Closures shall be allowed only during the times designated in Tables 643-1 and 643-2.

Local access shall be maintained at all times except for a 30 minute period during paving operations on intersections.

4.	One Lane Flagger Control:  One lane traffic with flagger control shall be allowed in Phases C, D and E during the times listed in Tables 643-3, 643-4 and 643-5.

5.	Intersections:  Intersections may not be fully closed.  At least one (1) lane of flagger controlled traffic must be provided at all times except for a 30 minute period during paving operations on intersections.  Traffic restrictions shall be allowed only at the times specified in Tables 643-(1-5).

6.	Work Phases:  This construction Project has been divided into five (5) phases (A-E) as shown on the Plans.  The following information as well as other information on the Plans and Special Provisions describes activities and restrictions within these phases:

a.	General:

After removal of the existing pavement, a gravel surface will be allowed for a period not to exceed 11 calendar days for any phase.

b.	Phase A - B.O.P. to Sta. 6230+00:

A graphical representation of allowable restrictions is shown in Table 643-1.

Full closures are allowed as shown in Table 643-1 between Sta. 6199+00 and 6230+00.  Intersections and local traffic are exceptions.

One lane flagger controlled traffic shall be allowed from B.O.P  to Sta. 6199+00 and at intersections at times indicated by xxx in Table 643-1.

When the closed road is reopened to traffic the driving surface shall be a minimum of 4 inches of crushed aggregate base course.

All Work within the roadway in Phase A shall be completed within 11 calendar days.  Pavement removal, excavation and backfilling shall be conducted at night.

c.	Phase B - Sta. 6230+00 to Sta. 6253+00:

A graphical representation of allowable restrictions is shown in Table 643-2.

Full closures are allowed as shown in Table 643-2.  Intersections and local traffic are exceptions.

Pavement removal, excavation and backfilling shall be conducted at night.

When the closed road is reopened to traffic the driving surface shall be a minimum of 4 inches of crushed aggregate base course.

All Work within the roadway in Phase B shall be completed within 11 calendar days.

d.	Phase C - Sta. 6253+00 to Sta. 4+00:

A graphical representation of allowable restrictions is shown in Table 643-3.

One lane closures with flagger control are allowed as shown in Table 643-3.  Local access shall be maintained at all times.

All Work within the roadway in Phase C shall be completed within 11 calendar days.

e.	Phase D - Sta. 4+00 to Sta. 175+00:

A graphical representation of allowable restrictions is shown in Table 643-4.

One lane closures with flagger control are allowed as shown in Table 643-4.  Local access shall be maintained at all times.

A longitudinal wedge joint shall be utilized unless the entire width of roadway is to be overlaid within 24 hours for any section.

All Work within the roadway in Phase D shall be completed within 11 calendar days.

f.	Phase E - Sta. 175+00 to E.O.P:

A graphical representation of allowable restrictions is shown in Table 643-5.

One lane closures with flagger control are allowed as shown in Table 643-5.  Local access shall be maintained at all times.

All Work within the roadway in Phase E shall be completed within 4 calendar days.

TABLE 643-1

PHASE A ALLOWABLE RESTRICTIONS

A graphical representation of allowable restrictions on Homer By-Pass from BOP to Svendlund Street as follows:

HOMER BY-PASS

BOP to Svedlund Street - Phase A

| HOUR |  | MON | TUES | WED | THUR | FRI | SAT | SUN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 1:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 2:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 3:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 4:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 5:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 6:00 AM |  |  |  |  |  |  |  |  |
| 7:00 AM |  |  |  |  |  |  |  |  |
| 8:00 AM |  |  |  |  |  |  |  |  |
| 9:00 AM |  |  |  |  |  |  |  |  |
| 10:00 AM |  |  |  |  |  |  |  |  |
| 11:00 AM |  |  |  |  |  |  |  |  |
| 12:00 PM |  |  |  |  |  |  |  |  |
| 1:00 PM |  |  |  |  |  |  |  |  |
| 2:00 PM |  |  |  |  |  |  |  |  |
| 3:00 PM |  |  |  |  |  |  |  |  |
| 4:00 PM |  |  |  |  |  |  |  |  |
| 5:00 PM |  |  |  |  |  |  |  |  |
| 6:00 PM |  |  |  |  |  |  |  |  |
| 7:00 PM |  |  |  |  |  |  |  |  |
| 8:00 PM |  |  |  |  |  |  |  |  |
| 9:00 PM |  |  |  |  |  |  |  |  |
| 10:00 PM |  | xxx |  | xxx | xxx |  |  |  |
| 11:00 PM |  | xxx | xxx | xxx | xxx |  |  |  |

Phase A: BOP to Sta. 6230+00

(BLANK) =	Maintain two-way traffic.

xxx =	Complete road closure allowed between Sta. 6199+00 and 6230+00.  Maintain local access at all times.  Approved TCP from Contractor is required.  Full closure from BOP to Sta. 6199+00 is not allowed.  One lane traffic with flagger control allowed BOP to Sta. 6199+00.

TABLE 643-2

PHASE B ALLOWABLE RESTRICTIONS

A graphical representation of allowable restrictions on Homer By-Pass from Svendlund Street to Lake Street as follows:

HOMER BY-PASS

Svedlund Street to Lake Street - Phase B

| HOUR |  | MON | TUES | WED | THUR | FRI | SAT | SUN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 1:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 2:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 3:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 4:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 5:00 AM |  |  | xxx | xxx | xxx | xxx |  |  |
| 6:00 AM |  |  |  |  |  |  |  |  |
| 7:00 AM |  |  |  |  |  |  |  |  |
| 8:00 AM |  |  |  |  |  |  |  |  |
| 9:00 AM |  |  |  |  |  |  |  |  |
| 10:00 AM |  |  |  |  |  |  |  |  |
| 11:00 AM |  |  |  |  |  |  |  |  |
| 12:00 PM |  |  |  |  |  |  |  |  |
| 1:00 PM |  |  |  |  |  |  |  |  |
| 2:00 PM |  |  |  |  |  |  |  |  |
| 3:00 PM |  |  |  |  |  |  |  |  |
| 4:00 PM |  |  |  |  |  |  |  |  |
| 5:00 PM |  |  |  |  |  |  |  |  |
| 6:00 PM |  |  |  |  |  |  |  |  |
| 7:00 PM |  |  |  |  |  |  |  |  |
| 8:00 PM |  |  |  |  |  |  |  |  |
| 9:00 PM |  |  |  |  |  |  |  |  |
| 10:00 PM |  | xxx |  | xxx | xxx |  |  |  |
| 11:00 PM |  | xxx | xxx | xxx | xxx |  |  |  |

Phase B: Sta. 6230+00 to 6253+00

(BLANK) =	Maintain two-way traffic.

xxx =	Complete road closure allowed.  Maintain local access at all times.  Approved TCP from Contractor is required.

TABLE 643-3

PHASE C ALLOWABLE RESTRICTIONS

A graphical representation of allowable restrictions on Lake Street and Ocean Drive from Homer By-Pass to Kachemak Bay Drive as follows:

LAKE STREET and OCEAN DRIVE

Homer By-Pass to Kachemak Bay Drive - Phase C

| HOUR |  | MON | TUES | WED | THUR | FRI | SAT | SUN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12:00 AM |  |  | F | F | F | F |  |  |
| 1:00 AM |  |  | F | F | F | F |  |  |
| 2:00 AM |  |  | F | F | F | F |  |  |
| 3:00 AM |  |  | F | F | F | F |  |  |
| 4:00 AM |  |  | F | F | F | F |  |  |
| 5:00 AM |  |  | F | F | F | F |  |  |
| 6:00 AM |  |  |  |  |  |  |  |  |
| 7:00 AM |  |  |  |  |  |  |  |  |
| 8:00 AM |  |  |  |  |  |  |  |  |
| 9:00 AM |  |  |  |  |  |  |  |  |
| 10:00 AM |  |  | F | F | F |  |  |  |
| 11:00 AM |  |  | F | F | F |  |  |  |
| 12:00 PM |  | F | F | F | F |  |  |  |
| 1:00 PM |  | F | F | F | F |  |  |  |
| 2:00 PM |  | F | F | F | F |  |  |  |
| 3:00 PM |  | F | F | F | F |  |  |  |
| 4:00 PM |  | F | F | F | F |  |  |  |
| 5:00 PM |  |  |  |  |  |  |  |  |
| 6:00 PM |  |  |  |  |  |  |  |  |
| 7:00 PM |  |  |  |  |  |  |  |  |
| 8:00 PM |  | F |  | F | F |  |  |  |
| 9:00 PM |  | F |  | F | F |  |  |  |
| 10:00 PM |  | F |  | F | F |  |  |  |
| 11:00 PM |  | F | F | F | F |  |  |  |

Phase C: Sta. 6253+00 to Sta. 4+00

(BLANK) =	Maintain two-way traffic.

F =	One lane, flagger controlled traffic allowed.

TABLE 643-4

PHASE D ALLOWABLE RESTRICTIONS

A graphical representation of allowable restrictions on Homer Spit Road from Kachemak Bay Drive to Freight Dock Road as follows:

HOMER SPIT ROAD

Kachemak Bay Drive to Freight Dock Road - Phase D

| HOUR |  | MON | TUES | WED | THUR | FRI | SAT | SUN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12:00 AM |  |  | F | F | F | F |  |  |
| 1:00 AM |  |  | F | F | F | F |  |  |
| 2:00 AM |  |  | F | F | F | F |  |  |
| 3:00 AM |  |  | F | F | F | F |  |  |
| 4:00 AM |  |  | F | F | F | F |  |  |
| 5:00 AM |  |  | F | F | F | F |  |  |
| 6:00 AM |  |  |  |  |  |  |  |  |
| 7:00 AM |  |  |  |  |  |  |  |  |
| 8:00 AM |  |  |  |  |  |  |  |  |
| 9:00 AM |  |  | F | F | F |  |  |  |
| 10:00 AM |  |  | F | F | F |  |  |  |
| 11:00 AM |  |  | F | F | F |  |  |  |
| 12:00 PM |  |  | F | F | F |  |  |  |
| 1:00 PM |  |  | F | F | F |  |  |  |
| 2:00 PM |  | F | F | F | F |  |  |  |
| 3:00 PM |  | F |  | F | F |  |  |  |
| 4:00 PM |  | F |  | F | F |  |  |  |
| 5:00 PM |  |  |  |  |  |  |  |  |
| 6:00 PM |  |  |  |  |  |  |  |  |
| 7:00 PM |  |  |  |  |  |  |  |  |
| 8:00 PM |  | F |  | F | F |  |  |  |
| 9:00 PM |  | F |  | F | F |  |  |  |
| 10:00 PM |  | F |  | F | F |  |  |  |
| 11:00 PM |  | F | F | F | F |  |  |  |

Phase D: Sta. 4+00 to Sta. 175+00

(BLANK) =	Maintain two-way traffic.

F =	One lane, flagger controlled traffic allowed.

TABLE 643-5

PHASE E ALLOWABLE RESTRICTIONS

A graphical representation of allowable restrictions on Homer Spit Road from Freight Dock Road to EOP as follows:

HOMER SPIT ROAD

Freight Dock Road to EOP - Phase E

| HOUR |  | MON | TUES | WED | THUR | FRI | SAT | SUN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12:00 AM |  |  | F | F | F | F |  |  |
| 1:00 AM |  |  | F | F | F | F |  |  |
| 2:00 AM |  |  | F | F | F | F |  |  |
| 3:00 AM |  |  | F | F | F | F |  |  |
| 4:00 AM |  |  | F | F | F | F |  |  |
| 5:00 AM |  |  | F | F | F | F |  |  |
| 6:00 AM |  |  |  |  |  |  |  |  |
| 7:00 AM |  |  |  |  |  |  |  |  |
| 8:00 AM |  |  |  |  |  |  |  |  |
| 9:00 AM |  |  | F | F | F |  |  |  |
| 10:00 AM |  |  | F | F | F |  |  |  |
| 11:00 AM |  |  | F | F | F |  |  |  |
| 12:00 PM |  | F | F | F | F |  |  |  |
| 1:00 PM |  | F | F | F | F |  |  |  |
| 2:00 PM |  | F | F | F | F |  |  |  |
| 3:00 PM |  | F |  | F | F |  |  |  |
| 4:00 PM |  | F |  | F | F |  |  |  |
| 5:00 PM |  |  |  |  |  |  |  |  |
| 6:00 PM |  |  |  |  |  |  |  |  |
| 7:00 PM |  |  |  |  |  |  |  |  |
| 8:00 PM |  | F |  | F | F |  |  |  |
| 9:00 PM |  | F |  | F | F |  |  |  |
| 10:00 PM |  | F |  | F | F |  |  |  |
| 11:00 PM |  | F | F | F | F |  |  |  |

Phase E: Sta. 175+00 to EOP

(BLANK) =	Maintain two-way traffic.

F =	One lane, flagger controlled traffic allowed.

643-3.09	TEMPORARY PAVEMENT MARKINGS.  Permanent or Temporary Pavement Markings in accordance with this Subsection, approved traffic control plans, and Parts III and VI of the Alaska Traffic Manual shall be in place before existing paved roadways, temporary paved roadways and detours, interim paving lifts, and roadways with seal coats and surface treatments are opened to traffic for longer than one (1) continuous work shift.  This Work may include restriping of the existing roadway prior to beginning construction of the Project.

Conflicting pavement markings shall be removed in accordance with Subsection 670-3.04, Paint Removal. Construction shall be staged so that no traffic is routed over conflicting markings.

Sections of existing roadway that will be opened to traffic during the winter shall be marked at the same location as the existing lines and markings unless shown otherwise on the Plans, an approved traffic control plan, or as directed by the Engineer.

The Contractor shall maintain all Temporary Pavement Markings for their intended life without additional compensation for any reapplication that may be required. There will be no compensation to upgrade Temporary Pavement Markings for short term operations to those required for long term operations.

Only temporary raised pavement markers or removable performed retroreflective marking tape shall be used as Temporary Pavement Markings on the final pavement surface.  They shall be completely removed and disposed of in conjunction with the placement of the final markings.  The complete removal shall include any residual adhesive that might misguide motorists.  Final pavement markings on finished pavement surfaces and long term pavement markings on other asphalt surfaces shall be in place before Work is suspended for the winter.

Temporary Pavement Markings may not be required for construction activities that will be completed within  one (1) continuous Work shift if the roadway is adequately delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.  The Engineer shall determine the need for the Temporary Pavement Markings for these conditions.

1.	Long Term Operations.  Temporary Pavement Markings which will be in place for more than 2 weeks shall consist of full markings as if a permanent condition exists.

2.	Short Term Operations.  Temporary Pavement Markings which will be in place for less than 2 weeks shall be in accordance with Parts III and VI of the Alaska Traffic Manual with the following exceptions:

a.	Passing Zones.  Broken line pavement markings shall conform to Table 643-6.  This  applies to both white lane lines for traffic moving in the same direction and yellow center lines for two- or three-lane two-way roadways when it is safe to pass.

TABLE 643-6*

TRAFFIC MARKINGS

|  | LENGTH OF MARKINGS | SKIP SPACING |
| --- | --- | --- |

| MARKING | Normal | **Severe | Normal | **Severe |
| --- | --- | --- | --- | --- |
| MATERIAL | Curvature | Curvature | Curvature | Curvature |
| Removable Preformed Marking Tape | 4 feet | 2 feet | 36 feet | 18 feet |
| Temporary Raised Pavement Markings | 3 units 3 feet on center | 2 units 2 feet on center | 34 feet | 18 feet |

TABLE 643-7*

TRAFFIC MARKINGS

|  | LENGTH OF MARKINGS | SKIP SPACING |
| --- | --- | --- |

| MARKING | Normal | **Severe | Normal | **Severe |
| --- | --- | --- | --- | --- |
| MATERIAL | Curvature | Curvature | Curvature | Curvature |
| Removable Preformed Marking Tape | 2 feet | 1 feet | 38 feet | 18 feet |
| Temporary Raised Pavement Markings | 1 unit 40 feet on center | 1 unit 20 feet on center | - | - |

* 	No passing markings and signing required per 643-3.09.2.b.

** 	Severe Curvature:  When the degree of curvature is 5 or greater or when it is necessary for motorists to reduce their speed at least 15 miles per hour below the 85th percentile speed.

b.	No-Passing Zones.  No-passing zones, as detailed in Section 3B-3 to 3B-5 of the Alaska Traffic Manual, shall be identified as follows:

Sections of asphalt concrete pavement roadways with an ADT of 2000 vehicles per day or greater, shall have broken centerline markings conforming to Table 643-6, and no-passing markings consisting of a continuous 4 inch strip of removable performed marking tape or temporary raised pavement markers placed on 5 foot centers in the no-passing direction.  If a no-passing condition exists for both directions of traffic, both directions shall be marked with the two (2) 4 inch stripes of removable performed marking tape separated by approximately 3 inches, or  two (2)  temporary raised pavement markers placed approximately 3 inches apart on 5 foot centers and the broken centerline markings are not required.

Sections of asphalt concrete pavement roadways with an Average Daily Traffic (ADT) of less than 2000 vehicles per day, and seal coat and surface treatment pavements shall be marked with temporary pavement markings conforming to Table 643-7 and shall be identified with R4-1, (DO NOT PASS) and R4-2, (PASS WITH CARE) signs.  The signs shall be supplemented with two 18 inch x 18 inch, minimum size, fluorescent red- orange flags mounted above the signs.  The signs shall be mounted so that the bottom of the sign is at least 5 feet above the adjacent roadway.

c.	Other Markings.  It will not be necessary to install arrows, legend, stop lines, crosswalks, or right edge line markings.  Railroad crossing markings are required for areas that have sight restrictions or high accident experience.  Left edge lines will not be required unless they will be the only markings on the paved surface, such as ramps.  All other types of markings are required. These include channelizing lines and gore area outlines.

d.	Short Term Markings on Seal Coats and Surface Treatments.  Only temporary raised pavement markers conforming to Subsection 712-2.16 shall be used for short-term markings on seal coat and surface treatment pavements.  The markers shall be installed prior to the application of the asphalt surface material and cover coat.

On multicourse surface treatments the temporary raised pavement markers shall be installed following the full width application of the first layer of cover coat.  The markers shall be installed on each day's completed surface before the pilot car operations are removed and unescorted traffic is allowed on the surface treatment in accordance with Table 643-7.

If the temporary raised pavement markers cannot be adequately secured to the first course of the cover coat material with the marker's flexible bituminous adhesive, the Contractor shall secure them to the surface with  two (2) nails and washers, of the appropriate length and area, so the nails do not pull through the foot of the marker.

After application of the asphalt and cover coat material, the vinyl protective cover shall be removed to expose the retroreflective surfaces of the marker.  Temporary markers shall be installed so that the foot of the marker unit is facing the direction of the approaching distributor.

Final pavement markings shall not be placed until the seal coat or surface treatment has been opened to traffic for at least 14 days.  Final pavement markings shall be applied within 10 days of the completion of the final sweeping or brooming of the mainline seal coat or surface treatment.  Seal coat and surface treatment pavements are exempt from the 2 week requirement stated in short-term operations.

643-4.01	METHOD OF MEASUREMENT.

Add the following to Item 1.:

Newspaper advertisements will not be included in measurement for Traffic Maintenance.

Delete the second sentence of the first paragraph under Item 2. and replace with the following:

The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this Contract.  Permanent Construction Signing will not be measured for payment, but will include all permanent construction signs, as detailed on the Plans, that are installed, accepted, maintained, and removed during the lift of this Contract.

Delete numbered paragraph 6. in its entirety and substitute the following:

6.	Temporary Pavement Markings will be measured by the single stripe station.  A single stripe is a marking or a temporary raised pavement marker 4 inches in width.  Wider striping will be measured as multiples of 4 inches.  Centerline gaps will not be deducted from measurements.  Installation of any word and symbol markings as well as the removal of the Temporary Pavement Markings will not be measured separately but will be subsidiary to this item.  The No-Passing Zone signing, as described in Subsection 643-3.09, 2., b., will not be measured separately but will be subsidiary to this item.

Delete paragraph 7., Seasonal Pavement Markings, in its entirety.

Add the following:

Newspaper advertisements will not be measured for payment.

Providing a 24 hour telephone for the public to obtain current roadway status and providing weekly notices with daily updates will not be measured for payment but will be subsidiary to Item 643(1), Traffic Maintenance.

Add the following:

Item 643(25) Portable Changeable Message Board Signs will be measured by the calendar day for each sign used as approved by the Engineer.

STANDARD MODIFICATIONS

643-5.01	BASIS OF PAYMENT.

Change the pay unit for Item 643(3), Permanent Construction Signing, from "Calendar Day" to "Lump Sum."  (5/7/91)

SPECIAL PROVISIONS

643-5.01	BASIS OF PAYMENT.

Delete Item 1, Seasonal Pavement Markings in the second paragraph.

Delete Pay Item 643(14), Seasonal Pavement Markings in the fourth paragraph.

Add the following:

Payment for Item 643(25) Portable Changeable Message Board Signs will be full compensation for all labor, equipment, and materials to provide, move, maintain, program, and operate a portable message board sign on the Project.

Payment for Item 643(29), Newspaper Advertisements, will be made at cost plus 15%.  Payment will be authorized upon evidence of payment to the newspaper (paid receipt).

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

643(25)	Portable Changeable Message	Calendar

Board Sign	Day

643(29)	Newspaper Advertisements	Contingent Sum

SECTION 644

SERVICES TO BE FURNISHED

BY THE CONTRACTOR

SPECIAL PROVISIONS

644-2.01	FIELD OFFICE.

Delete this Subsection in its entirety and substitute the following:

The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks prior to commencing Work through 30 days after issuance of the notice of Project completion.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 150 square feet of floor space.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of twelve (12) vehicles, with one (1) handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 1 mile of the Project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

644-2.02	FIELD LABORATORY.

Delete the sixth sentence of the first paragraph and substitute the following:

The water supply shall consist of a 500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Delete the second paragraph and substitute the following:

The laboratory shall include a concrete slab, 8 feet x 10 feet x 4 inches thick, suitable for mounting a Gilson shaker and other equipment.  The slab shall be installed within an enclosed adjacent structure having a door, a window, a worktable, an exhaust fan, and adequate lighting and heat.

Add the following:

The Contractor shall supply electricity with an adequate supply of 230 volt, 60 cycle current, 100 lb. propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location as designated by the Engineer.

644-2.09	Contaminated Material Testing.

Add the following subsection:

In accordance with subsection 203-3.07, Excavation of Contaminated Material, the Contractor shall retain an independent test laboratory to conduct the following tests:

1.	Field Tests

a.	Organic Vapor Analyzer (OVA) Analysis

b.	Visual Analysis (Petroleum Odor)

2.	Laboratory Tests

a.	Volatile Aromatic Hydrocarbons

b.	Total Petroleum Hydrocarbons

644-3.01	Method of Measurement.

Add the following:

Contaminated material testing will be reimbursed based on paid receipts for the authorized tests.

644-4.01	BASIS OF PAYMENT.

Add the following:

Electricity, propane and water supplied for the State provided portable asphalt lab will not be measured for payment, but will be subsidiary to Item 644(2), Field Laboratory.

Payment for contaminated material testing will be made on the receipts for authorized samples plus 15%, and shall be considered full compensation for all labor, equipment and materials required to have tests performed.

Add the following pay item:

Pay Item No.	Pay Item 	Pay Unit

644(8)	Contaminated Material	Contingent Sum

Testing

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01	DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix A.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this Contract will be as shown on the bid schedule.

645-2.01	OBJECTIVE.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.1, located in the "green pages" of this document.

645-3.01	GENERAL.  The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various Work classifications based upon the type of Work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to Contract award that training in the skilled classifications is not possible on a Project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the Project and the Contractor does one (1) or more of the following:  contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25% of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the Contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/ BAT), or one developed by the Contractor and approved prior to Contract award by the Alaska Department of Transportation and Public Facilities (ADOT &PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the Project as soon as feasible after start of Work utilizing the skill involved and remain on the Project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the Contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as Work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the Project, and with a written certification showing the type and length of training completed on the Project.  Existing USDOL/BAT apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/ trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02	WAGES.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60% (but less than 100%) of the appropriate minimum journey rate specified in the Contract for the first half of the training period, at least 75% (but less than 100%) for the third quarter of the training period, and at least 90% (but less than 100%) for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program. Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the Project shall be identified on Form 25A312.

645-3.03	SUBCONTRACTS.  In the event the Contractor subcontracts a portion of the Work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with Subsection 645-5.01, Basis of Payment.

645-4.01	METHOD OF MEASUREMENT.  The Contractor will be credited for each approved apprentice/trainee employed on the Project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01	BASIS OF PAYMENT.  Payment will be made at the Contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these Specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the Project following the completion of all training programs approved for the Project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or,

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as Work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the Project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program for	Labor Hour

______ Trainee/Apprentice

(10/29/91)S16

SECTION 660

SIGNALS AND LIGHTING

SPECIAL PROVISIONS

660-2.01	EXCAVATING AND BACKFILLING.

Change "Subsection 204-3.01" to "Section 204" in the third paragraph.

Add the following after the third paragraph:

The first 6 inches of backfill shall be free of rocks exceeding 1 inch maximum dimension.

660-2.04	POLES, STEEL PEDESTALS AND POSTS.

Add the following:

All poles and mastarms shall be designed for 100 MPH wind speeds with gusts to 130 MPH.

660-2.05	CONDUIT.

Add the following:

Trenching to install conduits across roadways with an existing paved surface will be allowed prior to final lift paving.

Delete the ninth paragraph (the fourth paragraph on page 431).

660-2.08	CONDUCTORS.

Delete the second paragraph under Item 2, Power Conductors and Cables,  and add the following:

Conductor insulation in cables consisting of three #8 AWG sized conductors shall colored black, white, and red.  Conductor insulation in cables consisting of conductors larger than #8 AWG shall either be colored black, white and red, or be black with printed numbers identifying each conductor per Insulated Cable Engineers Associated (ICEA), method 4.

660-2.09	WIRING.

Delete the phrase "and lead-in cable" from the first sentence in the eleventh paragraph.

Add the following:

Encapsulate all lead-in cable splices in rigid, transparent, PVC molds that are filled with reenterable polyurethane electrical insulating and sealing compound.  The completed splice shall be rated for 1000 volt operation and direct burial.

Provide molds that are reusable and come in four (4) pieces that are held together with stainless steel hose clamps.  Two pieces form a cylinder and the other two are flexible end caps.  Use molds that have dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Use a loose woven polyester web between the splice and the inside of the mold, which allows a full 1/4 inch of insulating compound to flow around the splice.  Fill the PVC molds with reenterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is non-corrosive to copper, and does not support fungi or mold growth.

660-2.10	BONDING AND GROUNDING.

Add the following after the first paragraph:

The Contractor shall install a bare, #8 AWG, solid copper conductor in all conduits as the grounding conductor.  The grounding conductors shall be attached to the conduits using insulated throat grounding bushings, leaving 1 foot of slack between each grounding bushing.

All hardware, including insulated thread grounding bushings, ground rods, and ground rod clamps shall be UL listed.  Grounding bushings shall be the threaded type.

Delete the fifth paragraph on page 441 and substitute the following:

Where conduit is installed as a spare or for future use, the aforementioned copper grounding conductor may be omitted.

Standard Modifications

660-4.01  Installation Details.

In numbered paragraphs 7 and 9, under "Loops", change "660-2.08" to read "660-2.09(A), Wiring".  (5/7/91)M42

SPECIAL PROVISIONS

660-6.01	luminaires.

Add the following paragraph:

No paint may be applied to the reflecting surface of luminaire reflectors.

Luminaires shall provide the specified uniformities or better in the configurations listed in the table below.  Uniformity is defined as the average maintained illumination level divided by the maintained illumination at the dimmest point.  Uniformity shall be calculated using the manufacturer's current published photometric charts.  Uncorrected illumination values shall be derived by straight line interpolation between lines of the isofootcandle curves.

| LUMINAIRE ARRANGEMENT | LUM. TYPE | ROAD WIDTH (FT) | MOUNT- ING HT. (FT) | SPACING (FT) | LUM. OFFSET (FT) | UNIFOR-MITY | AVERAGE INITIAL FOOT- CANDLES |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Staggered | MC-3 | 45.5 | 40' | 210' | 35' | 3.0:1 | 1.9 |
| Same Side | MC-3 | 45.5 | 40' | 195' | 35' | 3.0:1 | 1.9 |

Luminaire Type Definitions:

MC-3:	A roadway luminaire with a medium cutoff, type 3 light distribution as defined by the Illuminating Engineering Society (IES).

660-6.07	SALVAGING ELECTRICAL EQUIPMENT.

Add the following to the first paragraph:

Controller assemblies and other equipment not being reused shall be salvaged and delivered to the State Maintenance Yard at Homer.

Delete the fourth paragraph and substitute the following:

The following existing items not being reused shall become the property of the Contractor and be disposed of as indicated.  Items that are to be removed shall be removed from the highway right of way.

1.	Junction boxes (not including lids), conductors, and foundations for signal posts and controller assemblies shall be removed.

2.	Conduits may be abandoned in place provided elbows and nipples that sweep the conduits into junction boxes are removed.  However, existing conduits encountered while trenching shall be removed to provide 2 radial feet of clearance between the old and new conduits.

3.	Electrolier foundations shall be removed or abandoned in place.  If they are abandoned, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 1 foot below roadway subgrade, sidewalk, or unimproved ground, whichever applies.

660-7.01	BASIS OF PAYMENT

In the first paragraph, modify line eleven to read "..involved in furnishing and installing, modifying, maintaining or...".

Add the following:

Salvage of electroliers will not be paid for directly but will be subsidiary to 660(3A), Highway Lighting System Complete at Homer By-Pass.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

660(3A) 	Highway Lighting System

Complete at Homer By-Pass	Lump Sum

660(3B)	Highway Lighting System

Complete at Airport Access Road	Lump Sum

660(3C) 	Highway Lighting System

Complete at Kachemak Drive	Lump Sum

SECTION 661

ELECTRICAL LOAD CENTERS

SPECIAL PROVISIONS

Add the following subsection:

661-1.02	EQUIPMENT LIST(S) AND DRAWINGS.

The Contractor shall submit for review and approval, within 30 days following award of the Contract, eight (8) collated copies of a portfolio of equipment and materials which he proposes to install. The portfolio(s) shall consist of a table of contents which includes each item's intended use(s) and the following:

1.	For materials on the Approved Products List:  a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

2.	For materials not on the Approved Products List: catalog cuts that include the manufacturer's name, type of product, size, model number, conformance specifications, and supplemented by other data as may be required, including manufacturer's maintenance and operations manuals, or sample articles.

This information may be included in the portfolio for 660 items.

The Department will not be liable for any material purchased, labor performed, equipment used, or delay to the Work before all equipment and materials have been reviewed and approved.

661-2.01	MATERIALS.

Add the following:

Type 1 load center cabinets shall be constructed similar to the section and elevations shown on the Plans, and conform to the following requirements.  Slight variation in the dimensions is allowable, except in the anchor bolt template.

1.	The cabinet shall be constructed of zinc-coated A60 finish sheet steel per ASTM A525 with no external screws, bolts, or nuts.  The components shall have the following minimum thickness as measured by the United States Standard Gauge:  the exterior shell No. 12 gauge, the interior doors and panels No. 14 gauge, and the interior covers No. 16 gauge.

2.	The components shall be painted with a two-part urethane paint undercoating inside and out.  The final finish shall be a two-part urethane paint, standard white for removable panels and non-gloss silver-gray, closely matching Color No. 36622 of Federal Standard Specification No. 5950 for the enclosure.

3.	The service entrance section shall be isolated from the main load section and distribution load section by non-removable metal barriers, and shall be equipped with landing lugs for termination of service conductors.

4.	The cabinet shall be provided with internal mounting brackets sized for 1/2 inch anchor bolts for use with a standard mounting base assembly.

5.	All doors shall be equipped with continuous stainless steel pin hinges, coin latches and hasp for padlock.  The meter section door shall have a clear polycarbonate resin window, 0.187 inch minimum thickness, with a minimum size of 10 inch x 10 inch, which shall be sealed with silicone.

6.	Each completed load center assembly shall be provided with an exterior name plate, safety labels, interior identification labels, wiring diagram, and installation instructions.

7.	When two (2) Type 1 load centers are to be installed adjacent to one another, furnish  one (1) cabinet with the load distribution section located on the left side.

661-3.01	CONSTRUCTION REQUIREMENTS.

Delete the first sentence or the ninth paragraph (the third paragraph on page 509) and substitute the following:

Load centers with lighting circuits shall be provided with a 10 ampere, three (3) pole, three (3) position selector switch in the photoelectric control circuit.

Add the following:

The wiring configuration for each load center shall be in accordance with the wiring diagram indicated on the load center detail sheet.  Circuit breaker ratings shall be as shown in the load center summary for each location.  Dead panels shall be indelibly labeled with the circuit number and the direction of the circuit run from the load center.

When the load centers are ready to be energized, the Contractor shall request and coordinate an electrical inspection of the load centers from the local authority having jurisdiction, allowing at least 5 working days before the inspection is needed.  The Contractor shall be present during the inspection to assist in accessing the cabinets and to answer questions.  The Contractor shall correct the deficiencies noted in each load center.

661-5.01	BASIS OF PAYMENT.

Add the following:

Payment of any fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be considered incidental to the Section 661 items.

(10/1/91)

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDERS

SPECIAL PROVISIONS

669-1.01 Description.  This Work shall consist of furnishing and installing three (3) traffic count stations for the automated collection of traffic data on an intermittent or permanent basis.

Automated Traffic Recorder (ATR) stations are vehicle detection systems.  The simplest form of ATR is an intermittent volume counter, which consists of single inductive loops buried beneath the asphalt in each traffic lane, with lead wires run to a cabinet at the side of the road.  Traffic volume information is collected when a portable, battery-operated traffic counter is connected to the inductive loop wires; the traffic counter detects passage of vehicles and stores the data for later retrieval.

A Permanent Traffic Recorder (PTR) is formed when a traffic volume counter is connected to electrical and telephone service. Electrical service enables the volume counter to be operated continuously, and the data is retrieved periodically over the telephone line by a computer located at the offices of the Highway Data Section (HDS).

An Automated Vehicle Classifier (AVC) station consists of two (2) inductive loops in each lane, a piezoelectric axle sensor mounted in the pavement between the loops, and connected to a set of electronics located in a cabinet at the side of the road.  The dual inductive loops detect the presence and speed of passing vehicles, and the axle sensor determines the number and center-to-center spacing of all axles on the vehicle.  The raw data is processed by the electronics to classify the number and type of vehicles, which is stored in the electronics for later retrieval.  AVC stations may be configured to collect data on an intermittent basis, or with the addition of electrical and telephone service, on a continuous basis.

A Weigh In Motion (WIM) station consists of two (2) inductive loops in each lane, two (2) very sensitive piezoelectric axle sensors mounted in the pavement between the loops, and connected to a set of electronics located in a cabinet at the side of the road.  The dual inductive loops detect the presence and speed of passing vehicles, and the axle sensors determines the number, center-to-center spacing and weight of all axles on the vehicle.  The raw data is stored in the electronics for later retrieval.  WIM stations are configured with the addition of electrical and telephone service to collect data on a continuous basis.

In some ATR stations more than one (1) type of traffic data system is installed at the same location.  In addition, some ATR stations are equipped with a temperature probe which measures the temperatures in the road prism at intervals down to 6 feet below the pavement surface.  The multiple systems are connected to a telephone line through an electronic switch, which enables the data from each unit to be retrieved by a computer located at the HDS offices.

General descriptions of the Automated Traffic Recorders are as follows:

Assembly H1 - A two-lane AVC system which includes four inductive loops, two piezoelectric sensors, and AVC electronics housed in a medium sized controller cabinet (Style CBA2) equipped with a thermostatically controlled heater and light, with electrical and telephone service.  A remote Type 1 load center installed as part of the illumination improvements of this project will supply power to a 480-120/240V step down transformer mounted on the cabinet.  All loops, sensors, cabinet, AVC electronics, transformer and telephone modem shall be supplied, installed and commissioned by the Contractor.

Assembly H2 - A two-lane intermittent traffic volume count system, including two (2) inductive loops and a small controller cabinet (Style CBA1).  No electronics, electrical or telephone service is required at this site.

Assembly H3 - A two-lane permanent traffic volume count system, permanent AVC system and permanent WIM system. Includes a ten (10) inductive loop configuration, two (2) piezoelectric cable axle sensors for vehicle classification, two (2) lanes of dual piezoelectric cable WIM sensors for a total of 4 WIM sensors, temperature probe and data logger, and traffic volume, AVC and WIM electronics housed in a large controller cabinet (Style CBA3) equipped with heater and light.  A remote Type 2 load center will supply power to a 480-120/240V step down transformer mounted on the cabinet.  All loops, sensors, cabinet, traffic volume, AVC and WIM electronics, telephone modem, remotely controllable code operated switch, transformer, temperature probe and data logger shall be supplied, installed and commissioned by the Contractor.

669-1.02  Regulation and Code.  All materials and workmanship shall conform to the standards of the Underwriter's Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturer's Association, where applicable.

669-2.01  Materials.  All materials provided for the Work shall be new, unless otherwise stated, and shall meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with Subsection 660-2.09(A), Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable.

2.	Conduit.  All conduit shall be in accordance with Subsection 660-2.05, Conduit.  Nylon pull cords shall be left in all 2 inch conduit.

3.	Junction Boxes.  All junction boxes shall be in accordance with Subsection 660-2.06, Junction Boxes.  Junction boxes used for ATR installations shall not contain any wiring or conduit with 440 voltage.

4.	Terminal Blocks.  All terminal blocks shall be provided with nickel, silver or cadmium plated brass binder head screw terminals.  Terminal blocks shall be a barrier type, 600vac, @20 amps, capacity for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips. All conductors shall be terminated to a terminal block.

5.	Inductive Loops.  All inductive loops shall be in accordance with Subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be UL listed as Type RHW/USE/XLP 12AWG 600V rating.

Loop lead-in cable home run shall consist of a twisted pair 18AWG stranded tinned copper wire with polyethylene insulation, covered with an aluminum foil shield, stranded copper drain wire, and PE outer jacket conforming to IMSA specification 50-2.

Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, an aluminum shield and overall PVC or PE jacket.

6.	Cabinets.  All cabinets shall be unpainted, brushed aluminum and shall have a NEMA 3R rating.

The style CBA1 cabinet at Assembly H2 shall be a general purpose NEMA III enclosures 24 inch height by 14 inch width by 11 inch depth and firmly mounted on a 4 inch diameter steel post.

The style CBA2 cabinet at Assembly H1 shall be a general purpose NEMA III enclosures 40 inch height by 21 inch width by 15 inch depth and firmly mounted on a 4 inch diameter steel post.

The Style CBA3 cabinet installed at Assembly H3 shall be in accordance with Subsection 660-3.05, Controller Cabinets.  The cabinet shall be 55 inch height by 44 inch width by 26 inch depth and mounted on a concrete pedestal as specified on the Plans.  The cabinet shall include a thermostatically controlled heater and exhaust (cooling) fan, switched light, four (4) shelves, Corbin lock keyed to match existing Highway Data Section cabinets with Corbin locks, Ground Fault Interrupt (GFI) circuit breakers, dual sets of four (4) 110 volt receptacles and surge protectors for all electrical and telephone equipment.  The circuit breakers, 110 volt receptacles and terminal blocks shall be mounted on the side walls adjacent to the door.

7.	Asphalt Pavement.  Materials used for asphalt pavement shall conform to Section 401, Asphalt Concrete Pavement for Asphalt Concrete Pavement, Type II.

8.	Modem.  The Contractor shall supply and install a high-speed modem at Assembly H1. The modem shall be equal or better to a MultiTech MultiModem II 9600 baud modem, Model MT932BA, available from Multi-Tech Systems Inc., 2205 Woodale Drive, Mounds View, Minnesota 55112, Phone (612) 785-3500, FAX (612) 785-9874.  The modem shall meet the following requirements:

a.	300, 1200, 2400 4800 or 9600 baud selectable

b.	Automatic Answer Mode

c.	MNP Level 5 data compression

d.	pulse or touch-tone dialing

e.	Full or Half-duplex operation

f.	Fully compatible with the "AT" command set

g.	Compatible with CCITT V.32, CCITT V.22, Bell 103, and Bell 212A modem specifications

h.	Meets FCC Part 15, FCC Part 68 regulations for direct connection to telephone lines

i.	hardware flow control

9.	Remotely Controllable Code Operated Switch.  The Contractor shall supply and install a remotely controllable code operated switch at Assembly H1. The code operated switch shall be equal or better than a Black Box Model GS-SW540A available from Black Box Corporation, P.O. Box 12800, Pittsburgh PA 15241, phone (412) 746-5530, FAX 1-800-321-0746.  The code operated switch shall meet the following requirements:

a.	Minimum four (4) addressable ports

b.	Speed: 110 to 19,200 bps, each port individually setable

c.	Flow Control: Hardware X-ON/X-OFF

d.	Data Format: 7 or 8 data bits; odd, even, or no parity

e.	Connectors: DB25s (female); DTE/DCE strap-setable

f.	Power: 115 VAC, 60 Hz, 5 watts

10.	Traffic Volume Counters.  The Contractor shall supply and install traffic volume equipment at Assembly H3 with the capability of counting traffic in both lanes.  The permanent traffic volume counter(s) shall be GK brand units available from Northwest Signal Supply, Inc., 17410 Southwest 63rd Avenue, Lake Oswego, Oregon 97035 Ph (503) 635-4351, Fax (503) 635-4341.  The permanent traffic volume counters shall include:

a.	GK model 6000 TC

b.	loop card

c.	Communications card

d.	Rechargeable battery

e.	64KB data module

f.	Battery charger

g.	Connective cable

h.	Modem cable

i.	User manual

11.	Automated Vehicle Classification (AVC) Counters and Sensors. The Contractor shall supply and install a two-lane automated vehicle classification system at Assemblies H1 and H3.  The AVC counters and piezoelectric axle sensors shall be PAT brand C100S available from PAT Equipment Corporation, Inc., 1665 Orchard Drive, Chambersburg, PA 17201, phone (717) 263-7655. AVC counters and sensors shall include:

a.	PAT model C100S

b.	Loop card(s)

c.	Communications card

d.	Loop cable(s)

e.	Power cable

f.	Axle detector cable

g.	Modem cable

h.	User manual

i.	Rechargeable battery

j.	Battery charger

k.	Piezo axle sensor (1 per lane), with coaxial leads long enough to reach the controller cabinet without splices

l.	Epoxy with hardener for each piezo axle sensor

12.	Weigh In Motion (WIM) Counters.  The Contractor shall supply and install a two-lane weigh in motion system at Assembly H3. The WIM electronics and sensors shall be International Road Dynamics (IRD) brand piezoelectric WIM equipment available from International Road Dynamics, 702 43rd Street East, Saskatoon, Saskatchewan S7K 3T9 Canada, phone (306) 934-6777. WIM electronics and sensors shall include:

a.	IRD Piezoelectric WIM basic unit, including 386 computer, 110 volt power supply, monitor, keyboard, 3.5 inch floppy drive, 40Mb hard disk drive, and DOS software

b.	Loop card

c.	Loop cables

d.	Piezoelectric Sensors Class I AS500 (two per lane), with coaxial leads long enough to reach the cabinet without splices

e.	Piezoelectric cards, four (4) channel

f.	Modem cable

g.	User Manuals

h.	IRD WIM software

13.	Temperature Probe and Data Logger. The Contractor shall provide and install a 6 foot temperature probe at Assembly H3.  The temperature probe shall be equal to or better than a MRC Model TP101 temperature probe and data logger available from Measurement Research Corporation, 4126 4th Street NW, Gig Harbor, WA 98335, Phone (206) 851-3200.  The temperature probe shall meet the following requirement:

a.	Total of sixteen (16) thermisters

b.	Degree of accuracy plus or minus 0.1 C

c.	Thermistor number 1 on 12 inch wire lead

c.	Thermisters at 3 inch spacing for first 12 inches

d.	Thermisters at 6 inch spacing from 12 to 72 inches

e.	Side mounted cable long enough to reach the cabinet without splices

The data logger shall be equal to or better than a Model CR10 Measurement and Control Module, with CR10 Wiring Panel; PS12LS Rechargeable Power Supply; SC32A Optically Isolated RS232 Interface, and; Model ENC 12/14 Enclosure. All available from Campbell Scientific, Inc., 815 W. 1800, N Logan, Utah  84321 1784, Phone (801) 753-2342, Fax (801) 752-3268.  The data logger shall meet the following requirements:

a.	Storage capability for sixteen (16) thermal readings at 1 hour intervals for a minimum of 90 days.

b.	Battery and power supply/charging unit to enable continuous operation from 110 volt service.

c.	All RS232 interfaces, cables and connectors needed to complete the system.

669-3.01  Construction Requirements.

1.	Wiring.  All wiring shall be installed in accordance with Subsection 660-2.09(A), Wiring.  All unused pairs shall be terminated within splices, at cabinets unused pairs shall be terminated to a terminal block and labeled.  All cables shall be labeled in all junction boxes.

2.	Conduit.  All conduit shall be installed in accordance with Subsection 660-2.05, Conduit or as indicated on the Plans.

3.	Junction Boxes.  All junction boxes shall be installed in accordance with Subsection 660-2.06, Junction Boxes or as indicated on the Plans.

4.	Terminal Blocks.  All terminal blocks and wire pairs shall be clearly labeled on the block.  Terminal blocks within cabinets shall be mounted so that all terminals are easily accessible from the front of the cabinet.  By convention, wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block.  All conductors shall terminate and be soldered to "spade" type terminal lugs.

5.	Inductive Loops.  All inductive loops shall be installed and constructed in accordance with Subsection 660-4.01, Installation Details, unless otherwise specified on the Plans. The Plans are not schematics; installation of the inductive loops shall closely conform to the location and layout of conduit runs shown on the Plans.

All inductive loops installed through existing asphalt paving shall be installed using full-lane-width cuts a minimum of 8 feet in length, with the inductive loops centered in the 8 foot cut with a minimum distance of 1 foot to the edge of the cut. All edges of the cuts shall be tack-coated during patching to ensure full adhesion.  All full-width patches shall be rolled sufficiently to ensure compaction equal or better than the existing asphalt, and to prevent edge ridges or settling of the patch from 'telegraphing' through the final lift asphalt.  Compaction tests shall be required at the discretion of the Project Engineer.

All loops installed in new asphalt paving shall be installed immediately prior to final paving of the particular section of road. Installation of loops after final lift paving shall not be permitted.

There shall be no transverse seams, joints or roughness within 50 feet of any inductive loops.  The finished surface of the asphalt shall be tested with a straightedge 10 feet long. The surface shall not vary more than 0.02 foot from the lower edge of the straightedge in an area within 50 feet of all sensors at the ATR installations.  At the discretion of the Project Engineer, a profilograph equipped with a chart recorder shall be run down each wheelpath of each lane for a distance of 50 feet before and after each ATR installation.  The profilograph will be supplied by the Highway Data Section and shall be operated by Contractor personnel.  The asphalt surface as recorded by the chart recorder shall not vary more than 0.02 foot in 10 feet.

All inductive loops shall be formed of four (4) turns of wire, and shall be 6 feet square with plus or minus 1 inch tolerance.  All inductive loops in a lane shall be located 16 feet from leading edge to leading edge except for the loops used in the WIM system which shall be 30 feet from leading edge to leading edge, with plus or minus 1 inch tolerance.  All inductive loops located in adjacent lanes shall be aligned within plus or minus 1 inch tolerance.

All lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the center line of the road.

6.	Cabinets.  All style 3 control cabinets shall be installed according to Subsection 660-4.01, Installation Details.  All style 1 and 2 cabinets shall be installed as indicated on the Plans.  Cabinets shall be installed with the doors on the opposite side from the roadway.

7.	Piezoelectric Sensors for AVC.  All permanent piezoelectric sensors shall be installed per AVC equipment manufacturer's recommendations.  All coaxial cables shall be run to the equipment cabinet without splices and terminated on the specified terminal block, with at least 6 feet of slack cable available in the equipment cabinet prior to the terminal block.  Acceptance testing shall be performed by the Contractor to ensure compliance with Subsection 669-3.02 Acceptance Testing.

8.	Class I Piezo WIM Sensors and Electronics for WIM.  All permanent Piezo WIM sensors shall be installed per WIM equipment manufacturer's recommendations. A manufacturer's representative shall be present to supervise installation of the piezo WIM sensors and to commission the WIM equipment as a complete and fully functioning system.  The Contractor shall provide for and make all arrangements to schedule delivery of equipment and to schedule the manufacturer's representative.

The piezoelectric WIM sensors will be installed between two (2) inductive loops.  The 6 foot square loops shall be spaced 30 feet from leading edge to leading edge, with 24 feet between the loops as specified in Subsection 669-3.01(5).  The piezoelectric sensors shall be installed using epoxy per manufacturer's specification in saw-cut slots approximately 1.5 inches wide, 1.5 inches deep and 12.5 feet long. The sensors shall be spaced 12 feet apart with plus or minus 1 inch tolerance, centered between the loops with plus or minus 1 inch tolerance, and spaced 6 feet from each sensor to the edge of the adjacent loop.

All piezoelectric coax cables shall be run to the equipment cabinet with no more than one (1) splice per cable.  All coax cables shall be terminated on the specified terminal block, with at least 2 feet of slack cable in each junction box and at least 6 feet of slack cable available in the equipment cabinet prior to the terminal block.

Acceptance testing shall be performed by the Contractor to ensure compliance with Subsection 669-3.02 Acceptance Testing.

9.	Temperature Probe.  The temperature probe shall be installed vertically in a 7 foot deep by 6 inch diameter hole augured through the asphalt shoulder.  The probe shall be located in the shoulder in front of the cabinet for Assembly H3, at approximate Station 31+55, and placed 2 feet from the edge of the lane.  The 1.5 inch diameter temperature probe shall be placed in the center of the augured hole and the hole backfilled with fine sand to the bottom of the asphalt.  The top thermistor on the 1 foot lead shall be placed 1.5 inches below the top surface of the asphalt, and the hole shall be filled with asphalt patch material and compacted. The 80 foot cable shall be brought to the edge of the road in a saw-cut channel, which is then filled with 3-M loop sealant.  The cable shall be run underground to the nearest junction box and then through conduit to the controller cabinet and connected to the data logger. The data logger shall be connected to the matrix switch to enable remote data retrieval over the telephone line.

10.	Utilities.  The Contractor shall provide and install the Load Center per the Plans, Specifications and the requirements of the appropriate Electrical Utility.  All wiring from the Load Center to the equipment in the cabinet shall be provided and installed by the Contractor.  The Contractor shall request inspection of the Load Center by the Department of Labor, Division of Mechanical Inspection (DOL/DMI).  After approval of the Load Center by the DOL/DMI the Contractor shall inform the Resident Engineer as to when electrical service is needed at the Load Center, with sufficient time to enable the Resident Engineer to schedule the installation with the Electrical Utility prior to commissioning of the equipment. The Resident Engineer will make arrangements in writing with the Electrical Utility to connect to the Load Center.  The Electrical Utility will provide service to the Load Center upon request of the Resident Engineer.

The Telephone Utility will provide and install a Network Interface Device (NID) on or near the Cabinet.  Underground wiring for telephone service will be provided and installed by the Telephone Utility, usually in association with the Electrical Utility when electrical service is installed.  The Contractor shall provide and install a RJ-11 telephone jack inside the Cabinet, and shall provide and install all wiring to connect the telephone jack with the NID.  The Contractor shall inform the Resident Engineer as to when telephone service is needed at the telephone jack, with sufficient time to enable the Resident Engineer to schedule the installation with the Telephone Utility prior to commissioning of the equipment.  The Resident Engineer will make arrangements in writing with the Telephone Utility to install and connect the NID.  The Resident Engineer will inform the Contractor of the telephone number at the NID.

669-3.02 Acceptance Testing.  The Contractor shall perform acceptance testing on all ATR installations.  The Contractor shall provide and make all arrangements for test vehicles and drivers as needed for the acceptance testing.

1.	General Tests.  All ATR installations shall have tests conducted in accordance with Subsection 660-4.01, Installation Details.

2.	AVC Acceptance Tests.  In addition to the General Tests, Acceptance Tests shall be performed by the Contractor on all automated vehicle classification installations.  Acceptance tests shall be performed to demonstrate that the AVC system performs at or above the required accuracy.  The classification standard used shall be in accordance with FHWA Schedule F.  Exact measurements for the axle spacings to be used for each vehicle classification shall be obtained from the Highway Data Section.

a.	Accuracy Requirements - The accuracy of Automated Vehicle Classifiers is such that, if good lane discipline is maintained:

(1)	not more than plus or minus 10% of the total vehicles in FHWA class one through class three (1 through 3) and,

(2)	not more than plus or minus 5% of the total vehicles in FHWA class four through class thirteen (4 through 13 are classified in the wrong bin when compared with a concurrent manual classification count.

b.	The AVC Acceptance Test shall consist of an hour-by-hour and summary comparison of a manual classification count with the output of the permanent AVC.  A manual vehicle classification count shall be performed for 16 consecutive 16 hours at the AVC site.  During that 16 hour period, a minimum of five (5) vehicles in an individual vehicle type bin is required in order to be included in the final comparison.

c.	The difference between the number of vehicles in each type bin as observed manually and as recorded by the AVC system shall be computed.  If more than the allowed percentages as listed above are classified in the wrong bin when compared with a concurrent manual classification count, the AVC equipment shall be recalibrated and the test performed again until the system meets the required accuracy.

3.	WIM Acceptance Tests.  In addition to the General Tests, Acceptance Tests shall be performed by the Contractor on all weigh in motion installations after Calibration of the WIM system has been performed.  Acceptance tests shall be performed to demonstrate that the WIM system performs at or above the required accuracy.

a.	Acceptance Tests shall consist of three vehicles which will make ten (10) passes over the WIM sensors in each lane at speeds varying from 15 to 70 miles per hour.

b.	The three (3) test vehicles shall consist of a five-axle, eighteen-wheel single trailer vehicle (FHWA Class 9), a three-axle, ten-wheel single unit vehicle (FHWA Class 6), and a two-axle, six-wheel single unit vehicle (FHWA Class 5).  All three (3) test vehicles shall be fully loaded with non-shifting material to near legal weight limits.

c.	All tires on all three (3) test vehicles shall be inflated to recommended pressures.

d.	The gross weight of the vehicles and the weight of each axle group shall be determined by weighing on a certified static scale at a scalehouse operated by the State of Alaska Department of Commerce, Division of Weights and Measures.  An axle group is defined as any two (2) axles whose midpoints are within 8 feet of each other.  For the test vehicles, the Class 9 single trailer vehicle has three-axle groups, while the Class 6 and Class 5 each have two-axle groups.

e.	The difference in value or error between the weight of each axle group or vehicle gross weight shall be computed as follows:

d = 100(W - R)

R

where:

d =	difference between WIM value and reference value

W =	WIM value, or weight as measured by the WIM system

R =	Reference value, or weight as measured by a static scale

f.	The Accuracy requirements for the WIM equipment consist of a maximum error of plus or minus 12% with a 94% confidence interval for axle group weights, and a maximum error of plus or minus 10% with a 94% confidence interval for gross vehicle weights.

For each test vehicle, no more than two (2) of the axle group weights measured by the WIM system can differ from the axle group weights as measured at the scalehouse by more than 12%.  Similarly, for each test vehicle, no more than two (2) of the gross vehicle weights measured by the WIM system can differ from the gross vehicle weights as measured at the scalehouse by more than 10%.

g.	Errors, or differences between the weights as measured by the WIM and weights as measured at the scalehouse, shall be calculated on ten (10) consecutive passes of each of the three (3) test vehicles at various speeds.  If more than the maximum number of errors is observed, the equipment shall be recalibrated and the Acceptance test performed again until the system meets the accuracy specifications.

669-3.05  Deliverables.  All deliverables shall be submitted to the Engineer prior to final approval of the Work or as otherwise called for herein.

1.	Equipment List(s) and Drawings.  The Contractor shall submit for review and approval by the Highway Data Supervisor within 30 days following award of the Contract, three (3) collated copies of a portfolio of equipment and materials which he proposes to install for the ATRs.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s), and a description that includes product name, manufacturer, model or part number.

The Department will not be liable for any materials purchased, labor performed, equipment used or delay to the Work before all equipment and materials have been reviewed and approved.

2.	As-Built Plans and Photographs.  The Contractor shall prepare four (4) complete sets of as-built plans which will be kept current with the construction.  These as-built plans shall detail all  construction changes made to the Plans and also include the following information on the appropriate sheets:

a.	the location and depth of all inductive loops and conduit runs, and,

b.	the station and offset of all junction boxes.

Redlines of full size construction plans will be acceptable.

Three (3) sets of as-built plans shall be presented to the Engineer, and one (1) set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation.

The Contractor shall present photographs and 35 mm negatives documenting the installation of all inductive loops.  The photos shall show the loops in place prior to covering with gravel and asphalt pavement.  The photographs shall include at least one (1) view of each loop showing the conduit to the nearest junction box, and at least two (2) overall views of each ATR installation showing placement of the inductive loops.  The photographs shall be 5 inch by 7 inch color prints, and shall be labeled with the identification of each loop as indicated on the Plans (for example;  H3 - W1NLA ).

3.	Test Results.  Written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Engineer prior to acceptance of the Automated Traffic Recorder Installation.  Tests will be conducted in accordance with Subsection 660-4.01, Installation Details.

Written (computer printout) results and copies of the electronic data files collected during performance of the WIM System acceptance test shall submitted to the Project Engineer prior to acceptance of completion of the WIM system.

4.	Manuals.  The Contractor shall provide to the Project Engineer for transmittal to the Highway Data Supervisor all installation, repair and operation manuals for all traffic volume, classification and weigh-in-motion units.

5.	Materials.  The Contractor shall provide to the Project Engineer for transmittal to the Highway Data Supervisor any and all epoxy grout remaining after installation, along with the electric mixing unit for the WIM epoxy.

669-4.01  Method of Measurement.  The quantity to be paid for will be the actual number of completed and accepted Automated Traffic Recorder Installations as shown on the Plans or as directed by the Engineer.

669-5.01  Basis of Payment.  The Contract unit bid price for all Automated Traffic Recorder installations shall be full compensation for furnishing all equipment, labor and materials necessary to complete the Work as specified, with the following exceptions:

1.	Excavation and backfill materials required will be paid for under their respective pay items.

2.	Asphalt required will be paid for under Item 401(1), Asphalt Concrete, Type 1I, Class A.

3.	Installation of wiring and service to the Load Center(s) will be paid for under the Utility Agreement for Electrical Service.  Installation of wiring and service to the Network Interface Device(s) (NIDs) will be paid for under the Utility Agreement for Telephone Service.

4.	Load centers shall be paid for under their respective pay item.

As-built plans, the manufacturer's representative and acceptance testing required for these installations will not be paid for separately, but will be subsidiary to the Automated Traffic Recorder Installations.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

669(1)	Automated Traffic Recorders	Lump Sum

SECTION 670

TRAFFIC MARKINGS

SPECIAL PROVISIONS

670-1.01	DESCRIPTION.

Add the following:

This Work shall also consist of removal of pavement markings at locations shown on the Plans or as directed by the Engineer.

STANDARD MODIFICATIONS

670-3.01	CONSTRUCTION REQUIREMENTS.

Insert "pneumatic" immediately before "roller" in the last sentence of Item 2.  (5/12/89)

SPECIAL PROVISIONS

670-3.04	PAINT REMOVAL

Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following:

Pavement markings shall be removed to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement.  Painting over existing striping does not meet the requirements for removal.  Any method utilized burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.05	PRELIMINARY SPOTTING.

Add the following:

Lines and markings to be replaced at their existing locations shall be referenced by the Contractor at his expense, prior to performing any Work that may disturb them.

670-4.01	METHOD OF MEASUREMENT.

Add the following after item 5:

6.	Linear Foot Basis.  Measurement of removal of pavement marking swill be the length of each individual stripe removed, excluding gaps.  An individual stripe is a longitudinal marking less than 6 inches wide.

Delete the last paragraph and substitute the following:

Removal of pavement markings will be measured by the linear foot for payment.

670-5.01	BASIS OF PAYMENT.

Add the following:

Repair of any damaged pavement or surfacing caused by the pavement marking removal operation will be subsidiary to Item 670(9), Removal of Pavement Markings.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

670(9)	Removal of Pavement Markings	Linear Foot

SECTION 702

ASPHALT MATERIALS

SPECIAL PROVISIONS

702-2.03	EMULSIFIED ASPHALTS.

Delete the first and second sentences and substitute the following:

The STE-1 cationic emulsified asphalt shall comply with the requirements listed below when tested in accordance with ASTM D 244:

TESTS ON EMULSION

Viscosity, Saybolt Furol at 25 C	30 	max.

Storage Stability, 1 day, %	1 	max.

Demulsibility, 35 ml, 0.8% Sodium dioctyl

sulfosuccinate solution, %	25 	min.

Sieve Test, % retained	0.10 	max.

Particle Change	Positive*

Distillation Oil by Volume of Emulsion, %	5 	max.

Distillation Residual by Weight of Emulsion, %	45 	min.

TESTS ON RESIDUE

Penetration, 25 C, tenths of a mm	100	min.

200	max.

Ductility, 25 C, 5 cm/min., cm	40	min.

Solubility in Trichloroethylene, %	97.5	min.

*	If particle charge test is inconclusive, materials having a maximum pH value of 6.7 will be acceptable.

STANDARD MODIFICATIONS

702-2.04	STORAGE AND APPLICATION TEMPERATURES.

Change storage temperatures for ACs from "340 Max" to "325 Max" in Table 702-1.  (5/12/89)

SPECIAL PROVISION

Add the following to Table 702-1:

| TYPE & GRADE | SPRAY | MIX | STORAGE |
| --- | --- | --- | --- |
| OF MATERIAL | (deg. F) | (deg. F) | (deg. F) |
| STE-1 | 70-140 | 70-150 | 50-125 |

SECTION 703

AGGREGATES

STANDARD MODIFICATIONS

703-2.01	FINE AGGREGATE FOR CONCRETE.

Insert ", class A, " after "AASHTO M 6" in the first sentence.

Add the following:

AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

703-2.02	COARSE AGGREGATE FOR CONCRETE.

Insert ", class B," after "AASHTO M 80" in the first sentence. (7/16/93)M24

703-2.03	AGGREGATE FOR BASE.

Add the following to the list under the first paragraph:

Plastic Index      AASHTO T 90      6 max.

(5/7/91)

SPECIAL PROVISIONS

703-2.03	AGGREGATE FOR BASE.

Delete Table 703-2, Aggregate for Untreated Base, and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing by Weight

| SIEVE DESIGNATION | GRADING D-1 |
| --- | --- |
| 1-inch | 100 |
| 3/4-inch | 70-100 |
| 3/8-inch | 50-79 |
| No. 4 | 35-58 |
| No. 8 | 20-47 |
| No. 30 | 10-26 |
| No. 50 | 6-19 |
| No. 200 | 0-6 |

STANDARD MODIFICATIONS

703-2.04	AGGREGATE FOR PLANT MIX ASPHALT PAVEMENT.

Replace this subsection with the following:

Coarse Aggregate.  Coarse aggregate (that material retained on the No. 4 Sieve) shall be crushed stone or crushed gravel and shall consist of sound, tough, durable rock of uniform quality.  All material shall be free from clay balls, vegetative matter or other deleterious matters.  Coarse aggregate shall not be coated with dirt or other finely divided mineral matter.  In addition, coarse aggregate shall meet the following requirements:

Percent of Wear	AASHTO T 96 	45 max.

Degradation Value	ATM T-13	30 min.

Percent Sodium Sulfate loss	AASHTO T 104	9 max. (5 cycles)

Percent Fracture	ATM T-4	80 min. single face

Thin-Elongated Pieces	ATM T-9	8% max.

Fine Aggregate.  Fine aggregate (passing the No. 4 sieve) shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness Test.

Blended Aggregate.  The several aggregate fractions for the mixture shall be sized, graded, and combined in such proportions that the resulting composite blend conforms to the grading requirements of Table 703-3.  The fraction actually retained between any two (2) consecutive sieves larger than the No. 100 shall be not less than 2% of the total.  Aggregate gradations shall be determined by ATM T-7.  The size of extracted samples for gradation shall be in conformance with AASHTO T 164.

TABLE 703-3

BROAD BAND GRADATIONS FOR ASPHALT

CONCRETE PAVEMENT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION DESIGNATION |  |  |
| --- | --- | --- | --- |
| DESIGNATION | TYPE I | TYPE II | TYPE III |
| 1 inch | 100 | - | - |
| 3/4 inch | 75-90 | 100 | - |
| 1/2 inch | 60-86 | 75-90 | 100 |
| 3/8 inch | 50-78 | 60-88 | 75-90 |
| No. 4 | 34-62 | 44-72 | 50-78 |
| No. 8 | 24-52 | 30-58 | 32-60 |
| No. 16 | 16-42 | 20-44 | 20-45 |
| No. 30 | 10-32 | 12-34 | 12-34 |
| No. 50 | 8-24 | 8-24 | 8-24 |
| No. 100 | 5-16 | 5-16 | 4-15 |
| No. 200 | 3-8 | 3-8 | 3-8 |

(7/16/93)M62

SPECIAL PROVISIONS

703-2.07	SELECTED MATERIAL.

Add the following to Item 1., Selected Material Type A:

It shall have 30 to 55% maximum by weight of particles passing the No. 4 sieve.

SECTION 705

JOINT MATERIALS

Standard Modifications

705-2.05	FLEXIBLE WATERTIGHT GASKETS.

In the first paragraph, add: "and precast manhole sections" after "rigid pipe." (7/2/93)M56

SECTION 712

MISCELLANEOUS

SPECIAL PROVISIONS

712-2.06	FRAMES, GRATES, COVERS AND LADDER RUNGS.

Add the following:

Ductile iron castings shall conform to the requirements of ASTM A536 for grade 60-4018. (9/1/89)

712-2.14	PREFORMED PAVEMENT MARKINGS.

Add the following to paragraph A., under Item 1., General Requirements:

The preformed ribbon shall consist of  one (1) solid piece of the required width and length.  In solid stripe areas, the tape length shall, where possible, be a minimum of 100 feet.

712-2.15	TEMPORARY RAISED PAVEMENT MARKERS.

Add the following:

The temporary raised pavement markers shall be installed utilizing an approved raised pavement marker flexible bituminous adhesive.

The color of the raised pavement markers shall conform to the color of the marking for which they supplement, substitute, or serve as a positioning guide.

(5/7/91)

Add the following Subsection:

712-2.16	TEMPORARY RAISED PAVEMENT MARKERS FOR SHORT-TERM OPERATIONS, SEAL COATS, AND SURFACE TREATMENTS.

The marker shall consist of an L-shaped polyurethane body with retroreflective tape on the top vertical section and with a self-adhesive base.  Both faces of the yellow marker and  one (1) face of the white marker shall be reflectorized. The marker body shall be made from 0.060 inch minimum thick polyurethane; the vertical leg shall be approximately 2 inches high by 4 inches wide and the base approximately 1-1/8 inches wide.  The polyurethane body shall conform to Table 712-1.

The adhesive shall be factory-applied to the marker base, and made of a pressure-sensitive material, a minimum 1/8 inch thick and 3/4 inch wide, with release paper.

Where chip seals, slurry seals or tack coats are to be utilized after placement of the temporary raised pavement markers, the markers shall come with a protective cover made of clear flexible polyvinyl chloride.

The reflective tape shall be metalized polycarbonate microprism retroreflective material with acrylic backing or equal, a minimum 0.25 inch wide x 4 inches long, and provide the minimum optical performance shown in Table 712-2, for an observation angle of 0.2.

TABLE 712-1

| PROPERTY | RESULT | ASTM TEST METHOD |
| --- | --- | --- |
| Specific Gravity (min.) | 1.19 | D792 |
| Hardness | 80A | D2240 |
| Tensile Strength (psi, min.) | 4600 | D412 |
| Ultimate Elongation (%, min.) | 330 | D412 |
| Modulus at 30% (psi, min.) | 1000 | D412 |
| Stiffness |  |  |
| @ -20F (psi, min.) | 1700 | D1053 |
| @ +72F (psi, min.) | 900 | D1053 |
| Compression Set - 22 hr @ 70C (%, max.) | 65 | D395 |
| Taber Abrasion CS17 Wheel wt. loss (mg/1000 cycles) | 3 | - |

TABLE 712-2

| HORIZONTAL |  |  |
| --- | --- | --- |
| ENTRANCE ANGLE | White | Yellow |
| 0 degrees | 3.5 | 3.0 |
| 30 degrees | 2.7 | 1.7 |

* 	Candelas per footcandle of illumination at the reflector on a plane perpendicular to the incident light.

(5/7/91)

SECTION 726

TOPSOIL

STANDARD MODIFICATIONS

726-2.01  TOPSOIL.

Replace the second paragraph with the following:

Topsoil shall contain not less than 5% and no greater than 30% organic matter by dry weight as determined by ATM T-6.

Delete the gradation table in the third paragraph and substitute the following:

| SIEVE SIZE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| No. 10 | 100 |
| No. 200 | 40-90 |

Delete the fertilizer requirements as stated in this subsection.

Add the following:

Fertilizer shall be applied as stated in Section 618.

(11/22/93)R139R

SECTION 730

SIGN MATERIALS

SPECIAL PROVISIONS

730-2.04  SIGN POSTS.

Under item 1., Metal Pipe Posts, add the following to paragraph a.:

Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 3/16-inch thick walls. 7/16-inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this Subsection.  Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this Subsection.

(9/1/89)R81

STANDARD MODIFICATIONS

730-2.04	SIGN POSTS.

Under Item 2., a., replace the second sentence with the following:

Sheets for post fabrication shall be zinc coated in accordance with ASTM A 525, coating designation G 90.

(7/2/93)M57

APPENDIX A

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX B

HOMER ELECTRIC ASSOCIATION, INC.

EXCAVATION AND CLEARANCE GUIDELINES