SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	Copies for review of the following are available in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Computations

b.	Cross Sections

Copies of the above documents may be obtained from Ridgways Reprographics, 6000 Arctic Boulevard, Anchorage, Alaska  99518, (907) 561-1555, at the Contractor's cost.

2.	The following reports are available upon request:

a.	Glenn Highway, Eklutna to Parks Highway, Phase 1D, Final  Geotechnical Recommendations, dated April 13, 1993.

b.	Foundation Report, Glenn Highway:  Eklutna to Parks, Phases 1C & 1D, dated May, 1992.

c.	Supplemental Foundation Report, Glenn Highway:  Eklutna to Parks, Phase 1D, dated May, 1993.

d.	Storm Water Manual (Cost = $20)

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Traffic, Safety and Utilities Engineer, (907) 266-1531.

4.	An environmental document addressing concerns and environmental commitments is available for review in the office of the Preliminary Design and Environmental Supervisor (907) 266-1508.

PART 4

STANDARD MODIFICATIONS

and SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS for HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.27  Holidays.  Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third Monday in January

3.	President's Day - Third Monday in February

(5/7/91)M30

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  Qualification of Bidders.  Delete the second paragraph.  (5/12/89)M1

Special Provisions

102-1.06  Preparation of Proposal.  Replace the second paragraph with the following:  The bidder shall specify a unit price, in figures, for each pay item for which a quantity is given and shall also show the products of the respective unit prices and quantities written in figures in the column provided for that purpose and the total amount of the proposal obtained by adding the amounts of the several items.  All the figures shall be in ink or typed.  In the event of a discrepancy between unit bid prices and extensions, the unit bid price shall govern.  Any changes shall be initialed by the person signing the proposal.  (1/6/93)R171

Standard Modifications

102-1.06 Preparation of Proposal.  Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

102-1.07  Non-Responsive Proposals.  Delete item 3. in its entirety and substitute the following:

3.	If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to the bidder at any one bid letting, as provided in Subsection 102-1.06, Preparation of Proposal.

(5/7/91)M31

Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)M2

102-1.12  Addenda Requirements.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)M3

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  Consideration of Proposals.  Add the following:  The apparent low bidder shall submit a completed Subcontractor List, Form 25D-5, within 5 working days following receipt of written notification by the Department.

If a bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this Subsection.

If a contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department, or

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the contract with the bidder involving work for which the subcontractor was  listed,

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or

9.	is determined by the Contracting Officer not to be responsible.

(4/1/93)R82

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  Changes.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)M5

Special Provisions

104-1.02  Changes.  Delete the first three paragraphs and substitute the following:  The Engineer reserves the right to make, in writing, at any time during the work, such changes in quantities and such alterations in the work as are necessary to satisfactorily complete the project.  Such changes in quantities and alterations shall not invalidate the contract nor release the surety, and the Contractor agrees to perform the work as altered.

If the alterations or changes in quantities significantly change the character of the work under the contract, whether or not changed by any such different quantities or alterations, an adjustment, excluding loss of anticipated profits, will be made to the contract.  The basis for the adjustment shall be agreed upon prior to the performance of the work.  If a basis cannot be agreed upon, then an adjustment will be made either for or against the Contractor in such amount as the Engineer may determine to be fair and equitable.

If the alterations or changes in quantities do not significantly change the character of the work to be performed under the contract, the altered work will be paid for as provided elsewhere in the contract.

The term "significant change" shall be construed to apply only to the following circumstances:

1.	When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction, or

2.	When a major item of work, as defined elsewhere in the contract, is increased in excess of 125 percent or decreased below 75 percent of the original contract quantity.  Any allowance for an increase in quantity shall apply only to that portion in excess of 125 percent of original contract item quantity, or in case of a decrease below 75 percent, to the actual amount of work performed.

(4/13/89)S37

Add the following:  No value engineering proposals will be considered for this project.  (9/1/89)R2

104-1.03  Differing Site Conditions.  Delete in its entirety and substitute the following:  During the progress of the work, if subsurface or latent physical conditions are encountered at the site differing materially from those indicated in the contract or if unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the work provided for in the contract, are encountered at the site, the party discovering such conditions shall promptly notify the other party in writing of the specific differing conditions before they are disturbed and before the affected work is performed.

Upon written notification, the Engineer will investigate the conditions, and if he determines that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any work under the contract, an adjustment, excluding loss of anticipated profits, will be made and the contract modified in writing accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment which results in a benefit to the Contractor will be allowed unless the Contractor has provided the required written notice.

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  Authority of the Engineer.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02, Changes.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)M6

Special Provisions

105-1.06  Cooperation With Utilities.  Add the following:  The Contractor shall request locates from all the utilities having facilities in the area.  Their telephone numbers are as follows:

Matanuska Telephone Association, Inc.	745-3121

Matanuska Electric Association, Inc.	745-3231

DOT/PF Maintenance & Operations-Palmer	266-1584

ENSTAR Natural Gas Company-Wasilla	376-7979

Rogers Cablevision	373-2288

Alaska Railroad Corporation	265-2457

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

Prior to the relocation of the utility's facilities, construction staking may be required.  The Contractor shall give the Utility 2 weeks advance notice as to when the staking will be available and maintain the stakes until the utility relocation is completed.  Payment for this staking will be as follows:

1.	If construction staking or right-of-way staking is required by the Utility in advance of the Contractor's normal schedule, the Utility will request the staking, through the Engineer, two (2) weeks prior to the time the staking is required for the Utility to start their relocation.  This staking will be paid under Item 642(2), Three Person Survey Party.

2.	If, as part of the contract, the Contractor provides the stakes in the area needed by the Utility, this work will be subsidiary to Item 642(1), Construction Surveying.

3.	If right-of-way staking is required by the Utility, and staking the right-of-way is not a part of the contract, the Utility will request the staking, through the Engineer, two (2) weeks prior to the time the staking is required for the Utility to start their relocation.  This staking will be paid under Item 642(2), Three Person Survey Party.

If an underground cable is damaged and requires splicing, the first time will be repaired by the Utility with the party causing the damage paying the repair costs.  If an electrical cable is damaged a second time, the cable will be replaced between junction points.  The party causing the damage shall pay for replacing the cable.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

105-1.07  Cooperation Between Contractors.  Add the following:  The following Department contract will be under construction concurrently with this project:

Glenn Highway, Eklutna to Parks, Phase 1-C

Contractor:  Wilder Construction, Inc.

The Contractor shall coordinate his traffic control, construction, and material hauling operations with the prime contractor of the above contract so as to minimize impact on the travelling public, and to minimize conflicts with the work being performed under the other contract.

Standard Modifications

105-1.12  Load Restrictions.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless otherwise allowed by an approved Traffic Control Plan.  (5/7/91)M32

Special Provisions

105-1.12  Load Restrictions.  Add the following to the second paragraph:  Overload and oversize permits are required to move the prestressed concrete girders to the job site.  No overload may cross the Ship Creek Bridge, Bridge No. 417.  Unless otherwise permitted by the overload permit officer, any permit will be subject to the following limitations:

Maximum Single Axle Load	30,000 lbs.

Maximum Tandem Axle Load	60,000 lbs.

Maximum  Triple Axle Load	80,000 lbs.

Maximum Four Axle Load	95,000 lbs.

Maximum Spacing of Axle Groups	20 feet center to

center axle groups

Minimum Spacing within Group	4 feet center

to center axles

Maximum Speed on any Structure	3 mph

The maximum axle loads tabulated above are applicable to hauling equipment with fixed axles only; variable load suspension (VLS) axles shall not be considered part of an axle group for purposes of this specification.

Vehicles shall cross structures at a constant speed, centered on the roadway, and with no shifting of gears.  Whenever the load exceeds 80,000 pounds, the vehicle shall be preceded by a walking flagger when crossing structures.

This overload allowance shall not apply to the transportation of construction materials other than prestressed concrete girder sections.

All overload permits are subject to seasonal load restrictions.

Routing shall be as prescribed by the permit officer, (800) 478-7636 or (907) 345-7750.

Alternate axle configurations and loadings which may reduce the overload movement restrictions and conditions are subject to individual review and analysis by the permit officer.

105-1.15  Project Completion.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work scheduled under subsection 618-3.04 Maintenance of Seeded Areas and subsection 621-3.04 Period of Establishment, a letter of project completion will be issued by the Engineer.  (7/1/90)R4A

105-1.17  Claims for Adjustment and Disputes.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.

Add the following:  Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.

(12/26/90)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  Source of Supply and Quality Requirements.  Add the following:  All steel and iron products which are incorporated into the work and the action of applying a coating to a covered product (i.e., steel and iron) shall be produced in the United States except that minor amounts of products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater.  Coating includes epoxy coating, galvanizing, painting, and any other coating that protects or enhances the value of a material subject to the requirements of this paragraph.  For the purposes of this paragraph, the cost is the value of the steel and iron products as they are delivered to the project.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel or iron products into the project.

(6/23/92)R156

106-1.02  Local Material Sources.  Under Item 1. General, add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)S32

Add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement shall be provided to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)R5

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01  Laws to be Observed.  Add the following:  Specific Equal Employment Opportunity Responsibilities of Federal-Aid Construction Contractors.

1.	General

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form 25D-55) and these Special Provisions which are imposed pursuant to Section 140 of Title 23, U.S.C., as established by Section 22 of the Federal-Aid Highway Act of 1968.  The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the equal employment opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State highway agencies and the Federal Government in carrying out equal employment opportunity obligations and in their review of his/her activities under the contract.

c.	The Contractor and all his/her subcontractors holding subcontracts not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of equal employment opportunity:  (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as Contractors and subcontractors.)  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.

2.	Equal Employment Opportunity Policy.

The Contractor will accept as his operating policy the following statement which is designed to further the provision of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include:  employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprentice-ship and/or on-the-job training.

3.	Equal Employment Opportunity Officer

The Contractor will designate and make known to the State highway agency contracting officers and equal employment opportunity officer (hereinafter referred to as the EEO Officer) who will have the responsibility for and must be capable of effectively administering and promoting an active Contractor program of equal employment opportunity and who must be assigned adequate authority and responsibility to do so.

4.	Dissemination of Policy

a.	All members of the Contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the Contractor's equal employment opportunity policy and contractual responsibilities to provide equal employment opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

(1)	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the Contractor's equal employment opportunity policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor's equal employment opportunity obligations within thirty days following their reporting for duty with the Contractor.

(3)	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the Contractor's procedures for locating and hiring minority group employees.

b.	In order to make the Contractor's equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

(1)	Notices and posters setting forth the Contractor's equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The Contractor's equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

5.	Recruitment

a.	When advertising for employees, the Contractor will include in all advertisements for employees the notation:  "An Equal Opportunity Employer."  All such advertisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority group applicants, including, but not limited to, State employment agencies, schools, colleges and minority group organizations.  To meet this requirement, the Contractor will, through his EEO Officer, identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority group applicants may be referred to the Contractor for employment consideration.

In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor's compliance with equal employment opportunity contract provisions.  (The U.S. Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or women, or obligates the Contractor to do the same, such implementation violates Executive Order 11246, as amended.)

c.	The Contractor will encourage his present employees to refer minority group applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures with regard to referring minority group applicants will be discussed with employees.

6.	Personnel Actions

Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The Contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The Contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with his obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the Contractor will inform every complainant of all of his avenues of appeal.

7.	Training and Promotion

a.	The Contractor will assist in locating, qualifying, and increasing the skills of minority group and women employees, and applicants for employment.

b.	Consistent with the Contractor's work force requirements and as permissible under Federal and State regulations, the Contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.  In the event the Training Special Provision is provided under this contract, this subparagraph will be superseded as indicated.

c.	The Contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.	The Contractor will periodically review the training and promotion potential of minority group and women employees and will encourage eligible employees to apply for such training and promotion.

8.	Unions

If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and female employees.  Actions by the Contractor either directly or through a Contractor's association acting as agent will include the procedures set forth below:

a.	The Contractor will use best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

b.	The Contractor will use best efforts to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The Contractor is to obtain information as to the referral practices and policies of the labor union except that the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the Contractor, the Contractor shall so certify to the State highway department and shall set forth what efforts have been made to obtain such information.

d.	In the event the union is unable to provide the Contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the Contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minority group persons and women.  (The U.S. Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees.)  In the event the union referral practice prevents the Contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such Contractor shall immediately notify the State highway agency.

9.	Subcontracting

a.	The Contractor will use his best efforts to solicit bids from and to utilize minority group subcontractors or subcontractors with meaningful minority group and female representation among their employees.  Contractors shall obtain lists of minority-owned construction firms from State highway agency personnel.

b.	The Contractor will use his best efforts to ensure subcontractor compliance with their equal employment opportunity obligations.

10.	Records and Reports

a.	The Contractor will keep such records as are necessary to determine compliance with the Contractor's equal employment opportunity obligations.  The records kept by the Contractor will be designed to indicate:

(1)	the number of minority and nonminority group members and women employed in each work classification on the project,

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to Contractors who rely in whole or in part on unions as a source of their work force),

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority group subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such records must be retained for a period of three years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the State highway agency and the Federal Highway Administration.

c.	The Contractors will submit an annual report to the State highway agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form PR 1391.  If on-the-job training is being required by "Training Special Provision", the Contractor will be required to furnish State of Alaska Form 25A-312.

(4/8/83)S15

107-1.08  Railway-Highway Provisions.  Delete the second paragraph and add the following:

1.	Definition of Terms.

a.	Railroad's Manager of Telecommunications and Signaling - the person employed by the Railroad as head of its Telecommunications Department or his authorized representative.

b.	Railroad's Chief Engineer - the person employed by the Railroad as head of its Engineering Department or his authorized representative.

c.	Railroad's Contracting Officer - the person authorized by the Railroad to execute contractual agreements on behalf of the Railroad.

d.	Facility - any improvements owned by the Department which are to be placed on Railroad Property in accordance with a written permit executed by the Railroad and the Department.

e.	Permit Area - the space on Railroad property that is or will be occupied by the Facility plus reasonable working area and reasonable ingress and egress to the Facility.

f.	Railroad - the Alaska Railroad Corporation, P.O. Box 107500, Anchorage, Alaska  99510-7500.

g.	Railroad Property - all lands owned or withdrawn for the use of the Railroad, in and including the track right-of-way and communications pole right-of-way.

h.	Trackwork - all work on the line from the top of subgrade to the top of rail, including geotextile, when required.

i.	Track Materials - all hardware, excluding signals and controllers, associated with the running of a railroad.

2.	General Requirements.

a.	All construction, reconstruction, operation and maintenance on the Railroad Property shall be performed in compliance with these specifications.

b.	Failure to comply with these specifications  shall result in the suspension of all work on Railroad Property.  The Contractor shall comply immediately upon notification from the Department, either verbal or written.

c.	All negotiations between the Railroad and the Contractor shall be handled through the Department.

d.	All work on or about the Railroad Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with the approved Railroad practices, and as specified herein.  Railroad traffic and property shall be protected at all times.

e.	The safety and continuity of the operation of the railroad traffic shall be of first importance and shall be at all times protected and safeguarded.  The Contractor and his subcontractors shall perform and arrange their work accordingly.  The Railroad's Chief Engineer shall decide all matters involving the safety of Railroad facilities and the operation of it's railroad.  The approval of the Railroad's Chief Engineer, when given, shall not be considered as a release from responsibility or liability for any damage which the Railroad may suffer or for which it may be liable, as a result of the acts of the Contractor, his subcontractor or employees.

f.	Whenever in the opinion of the Railroad's Chief Engineer, the construction may cause a hazard to the safe operation of the Railroad, the Railroad may, at its discretion, place at the site of the work the required number of qualified employees to protect its operations.  The providing of such employees and such other precautions as may be taken shall not relieve the Contractor and his subcontractors from liability for the payment of damages caused by their operations.  The Railroad shall be the sole judge of necessity, as to the number and classification of employees required.  All Railroad cost and expense for providing such employees shall be collected from the Contractor, except for flagging which shall be paid for as described in Subsection 107-1.08.5.b.

g.	The Contractor shall be responsible for maintaining sight triangles at existing railroad crossings as well as at any temporary crossings within the project limits and at any railroad crossing outside the project limits that is designated and used as an alternate route for traffic.

3.	Insurance Requirements.

a.	The Contractor shall comply with all insurance requirements and conditions specified under Subsection 103-1.05, except that the following minimum limits shall apply for Comprehensive or General Liability Insurance:

Bodily Injury - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Property Damage - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Blanket Contractual

b.	Prior to commencement of work on Railroad Property, the Contractor shall provide evidence of Railroad Protective Liability insurance (Alaska Railroad and State of Alaska as insureds) with the following limits:

Bodily Injury - $2,000,000 per occurrence

Property Damage - $2,000,000 per occurrence

4.	Notice.

a.	The Contractor shall give written notice to the Department and the Railroad not less than 10 days in advance of the commencement of any construction, reconstruction or major maintenance activity on Railroad Property, in order that the necessary arrangements may be made for the protection of the Railroad's operation.  This notice shall include the proposed schedule of work, and the names of the subcontractors who may also be working on Railroad Property.

b.	A preconstruction meeting shall be held with the Railroad's Chief Engineer and representatives of the Department and Contractor prior to the commencement of any work on Railroad Property by the Contractor or his subcontractors.

5.	Flag Protection and Protection of Railroad Traffic.

a.	Whenever Railroad flag protection is required in the specifications, this flag protection shall be provided by person(s) authorized by the Railroad.  Each person so authorized shall have met the Railroad's qualifications for flagmen.  Railroad flag protection is to insure the safe movement of trains and other rail traffic and shall be done in strict accordance with the Railroad rules on flagging.

b.	The Contractor shall, during the progress of the work, furnish as many qualified flagmen, as in the opinion of the Railroad, may be required for the adequate protection of the Railroad traffic.  If Railroad employees are used as flagmen, all Railroad expenses for providing such flagmen shall be reimbursed by the Department, except for flagging as described in Subsections 107-1.08.8.b and c., in which case the Railroad expenses shall be paid by the Contractor.  If the Contractor calls for flagmen and, through no fault of the Department or the Railroad, the flagmen are not needed, payment shall be deducted from monies due the Contractor.

c.	Vehicles and other construction equipment shall not be parked or operated closer than 20 feet from centerline of any track without Railroad flag protection provided in accordance with Subsection 107-1.08.5.a.

d.	The Contractor shall arrange with the Railroad to keep himself informed of the time of arrival of all trains and shall entirely stop any of the operations which might be or cause a hazard to the safe passage of the train past the site of the work from 10 minutes before the expected arrival of the train until the train has passed.

6.	Train Delays.

a.	All work on Railroad property shall be conducted in such a manner as to prevent delays to trains or other rail traffic operated by the Railroad.

b.	Should any of the Contractor's or subcontractor's actions or activities cause delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

| Passenger Trains | $50 per minute for each delay. $3,000 minimum charge. |
| --- | --- |
| All other trains and rail traffic | $50 per minute for each delay over five minutes. $1,500 minimum charge. |
| Rail barges, train-ships or other connecting carrier vessels | No charge for delays of an hour or less. $1,000 per hour for each hour or any part of an hour thereafter, with a minimum charge of $6,000. |

c.	Delay time will be taken from the train sheet in the Railroad Dispatcher's Office, in Anchorage, (265-2649) for all delays and such train sheet shall be the official document by which the length of time a train is delayed will be determined.  If another crew is needed to relieve the original crew, the charge shall also apply to the second crew.  If such delay causes a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by said train sheet.

7.	Protection of Railroad Communication Lines.

a.	All work on Railroad Property shall be conducted in such a manner as to protect the Railroad's communications facilities at all times from outages resulting directly or indirectly from the Contractor's or his subcontractor's operations.

b.	Should any of the Contractor's, or his subcontractor's operations cause outages to said communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

| Open wire communication circuits | $1.00 per minute per circuit |
| --- | --- |
| Communication cable | $5.00 per minute per cable |

c.	A minimum charge of $250 will be made for each outage.  The outage time shall be that as established by the Railroad's Test Board, Anchorage.

d.	There shall be no equipment worked or excavation within 15 feet of any Railroad communication pole guy, anchor, or other communications apparatus unless authorized in advance by the Railroad's Manager of Telecommunications and Signaling.

8.	Railroad Crossings.

a.	Whenever automatic railroad crossing signals are in the permit area, these signals must remain in operating condition at all times.  If, as a result of the Contractor's activities on the facility, the signals become inoperable the crossing shall be continuously protected in accordance with Subsection 107-1.08.5. until the signals are again operable.

b.	When regular railroad crossings are used as haul routes inside or outside the permit area, flagmen shall be provided by the Contractor for said crossings in all situations at the discretion of the Railroad.

c.	Temporary road crossings may be installed, provided the Contractor has acquired from the Railroad a temporary road crossing permit for said crossing.

The temporary crossing shall be constructed to the standards specified in the temporary crossing permit.  All protective signs required by the Railroad shall be provided and properly maintained by the Contractor.  When a temporary railroad crossing is in use, Railroad flag protection shall be provided at all times in accordance with Subsection 107-1.08.5.  When not in use during the winter season, the temporary crossing shall be removed unless specifically allowed in the temporary crossing permit.  Upon completion of the work or termination of the temporary crossing permit, the temporary railroad crossing shall be removed and the area restored to its original condition.

d.	The flange ways of all road crossings used by the Contractor or subcontractor as haul routes or temporary road crossings shall be kept free of gravel at all times and shall otherwise be maintained to the satisfaction of the Railroad's Chief Engineer.

e.	When a temporary or private road crossing is not in use, the Contractor shall provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

9.	Power and Communication Lines.

a.	All power and communication lines shall be designed and constructed in accordance with National Electric Safety Code (NESC).

b.	Underground power and communication lines shall be installed in accordance with Subsection 107-1.08.10.  Whenever an underground power or communication line crosses underneath a track, a casing pipe shall be installed for carrying such lines.

c.	The minimum clearance above the top of a rail of the Railroad track shall be in accordance with the NESC, plus 6 inches to allow for future grade raises.

d.	The minimum clearance above the Railroad communication lines shall be in accordance with the NESC.

e.	Additional lines may not be added, or the characteristics of the line(s) changed without written approval of the Railroad's Contracting Officer.

f.	Wires shall be strung across the Railroad tracks only when Railroad flag protection is provided in accordance with Subsection 107-1.08.5.

g.	No wires shall be strung across the Railroad's communication lines without first receiving approval from the Railroad's Manager of Telecommunications and Signaling therefor, and such work must be accomplished only at a time and in a manner prescribed by said Manager of Telecommunications and Signaling.

10.	Underground Facilities.

a.	All underground utilities, including culverts, pipelines and underground power and communication lines, on Railroad property shall conform to the current AREA Specifications.

b.	Unless another method is authorized in advance and in writing by the Railroad's Chief Engineer, all underground facilities shall be installed under tracks and roads by boring, jacking or tunneling.

c.	Boring, jacking and tunneling shall be done under Railroad tracks only when Railroad flag protection is provided in accordance with Subsection 107-1.08.5.

d.	The proposed plan for boring, jacking or tunneling shall be approved by the Railroad's Chief Engineer prior to commencing the operation.

e.	All boring, jacking or tunneling headings shall be continuously protected against any loss of ground material by shoring or cribbing as necessary.

11.	Open Trenching.

a.	Only when authorized in advance and in writing by the Railroad's Chief Engineer shall any portion of the track be removed to allow trenching for installation of the facility.

b.	If allowed to open trench, the track may be removed from service only at the time authorized by the Railroad's Chief Engineer and shall be restored to service within the time period specified by the Railroad's Chief Engineer.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in accordance with Subsection 107-1.08.6., whichever is greater and shall be collected from the Contractor.

c.	All work on track materials shall be accomplished by qualified trackmen.

d.	Only that portion of the track structure necessary to excavate, stockpile and install the facility shall be removed.  All track material removed shall be handled, stockpiled, and relaid in a manner as to avoid damage.  Any material which is damaged shall be replaced by the Contractor at his own expense.

e.	The backfill of the trench under the track and in the roadbed prism shall be of the same type of material as taken out, except the top 2 feet shall be clean pit run gravel.  Backfilling and compaction in the area affecting the roadbed prism shall be in accordance with the requirements of Section 204, Structure Excavation for Conduits and Minor Structures.

f.	The ballast used in replacing the track shall be equal in depth and quality to that which was removed.  The track shall be relaid and brought to original grade in accordance with standard Railroad practices.

12.	Excavations.

a.	Unless authorized in advance and in writing by the Railroad, the top of any excavation shall not be within 20 feet of center line of any track.

b.	No water shall be allowed to stand in open excavations in the track area.

c.	Bridging and shoring shall be adequate to safely carry Railroad traffic and the decision of the Railroad pertaining to same shall be final.

d.	All open excavations shall be continuously protected by flags, barricades or watchmen, as directed by the Railroad.

e.	No excavation shall be left open more than three days, unless authorized by the Railroad's Chief Engineer.

f.	The Railroad embankment, and cut slopes, shall not be disturbed any more than necessary to accommodate the construction and shall be left in a stabilized condition.

g.	Railroad ditches, culverts and roadways shall be kept clean and free of rock, gravel, construction debris and equipment at all times.

13.	Railroad Inspectors.

a.	The Railroad may furnish an inspector during the periods of construction on Railroad Property.  The Railroad inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary.  The Railroad inspector will work directly with the representative of the Department and the decision of the Railroad inspector in matters pertaining to Railroad operations and safety shall be final.  In the event more than one shift is worked, a Railroad inspector will be required for each shift.  Presence or absence of a Railroad inspector shall not relieve the Contractor of liability for damage done to property of the Railroad, Railroad lessees or permittees having installations on Railroad Property.

14.	Use of Explosives.

a.	The use of explosives shall be done in compliance with all applicable Federal, State and local laws and ordinances regarding the same.

b.	No blasting of any kind will be permitted unless the Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, Railroad flag protection in accordance with Subsection 107-1.08.5., shall be provided on each side of the blast area by the Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

c.	The Contractor will notify the Alaska Railroad Inspector and the Engineer of the exact time of each blast at least two hours in advance.

15.	Snow Removal.

a.	Snow removal operations shall be conducted in such a manner as to not place snow (1) upon the tracks of the Railroad, (2) where it interferes with the normal operation of the automatic crossing signals, or (3) impairs the visibility of either highway or rail traffic  at the crossing.

b.	Snow removal operations shall be conducted in accordance with Subsection 107-1.08.5.

16.	Clean-Up.

a.	At all times, all work and activities on the Facility shall be accomplished in such a manner as to keep the Railroad Property in a neat and orderly condition satisfactory to the Railroad.

b.	Upon completion of work, all equipment and unused materials shall be removed and the Railroad property shall be left in a neat and clean condition satisfactory to the Railroad.

c.	Should the Contractor or subcontractor fail to comply with Subsections 107-1.08.16.a. and 16.b., the Railroad may perform the required clean-up.  All Railroad costs and expenses for performing this work shall be collected from the Contractor.

17.	Payment Guarantee.

a.	The Department shall withhold 10 percent of the contract price or $10,000.00, whichever is smaller, from the final payment to apply against damages or other direct costs which may be assessed by the Railroad as a result of the Contractor's operations.

b.	The amount withheld above shall not be released until after the Department has received a written statement from the Railroad's Contracting Officer agreeing to release the payment.

(5/7/91)S2

107-1.11  Protection and Restoration of Property and Landscape.  Add the following to the third paragraph:  When working near designated wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits.  (2/9/91)R7

The Contractor shall report immediately to the Engineer any hazardous material discovered, exposed, or released into the air, ground, or water during construction of the project.  The Contractor shall also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery.  Hazardous materials include, but are not limited to, petroleum products, oils, solvents, paints, and chemicals that are toxic, corrosive, explosive, or flammable.  (5/7/91)S47

The Contractor shall not excavate, nor use for fill, any material at any site suspected or found to contain hazardous materials or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected or found to contain hazardous materials or petroleum fuels.

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2575.

Add the following:  The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.

The Contractor shall do no work, stockpiling, staging, parking nor trespassing below the ordinary high water mark of any watercourse or in any wetlands except as permitted by the contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

(2/9/91)R7

Standard Modifications

107-1.13  Responsibility for Damage Claims.  In the first sentence, change "claims or actions for injuries" to read claims, actions or liabilities for injuries".  (5/12/89)M9

Special Provisions

107-1.15 Contractor's Responsibility for Work.  Add the following to the end of the first paragraph:  Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense.  (5/7/91)S48

Standard Modifications

107-1.16  Contractor's Responsibility For Utility Property And Services.  In the last sentence of the third paragraph delete: "by the local fire authority."  (5/12/89)M10

Special Provisions

107-1.16  Contractor's Responsibility for Utility Property and Services.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning Utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the Utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The Utility mislocates the facility in the field by more than 2.5 feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the Utility.

(10/1/91)R8

Add the following:  Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work to be performed.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will not be paid for separately, but will be subsidiary to the item(s) of work being performed requiring cable watch services.

107-1.21  Permits.  Add the following subsection:  The following permits have been received on the Contractor's behalf by the Department:

1.	Department of the Army, No. 2-900105/Q-900105, dated August 24, 1990 and April 15, 1992, respectively, expiring October 31, 1994.

2.	Department of the Army, No. T-900105, dated September 11, 1992, expiring October 31, 1994.

The Contractor shall provide the information necessary to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge stormwater from the construction site.  Requirements for this permit are given under Section 641, Erosion and Pollution Control.

The permits obtained by the Department are attached to these specifications as Appendix A.  The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor's responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer.  The Engineer will then decide if a permit modification is necessary.  The Engineer will have copies of the permits posted in the project office.

(9/10/92)R9a

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  Subletting of Contract.  Delete the third paragraph on page 56 and substitute the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Driver's License,

2.	business license for trucking together with supporting documents that list the driver as the business owner or corporate officer,

3.	documents showing the driver's ownership interest in the truck including:

a.	truck registration, and

b.	lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended  payrolls  must be submitted  listing the

driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	The owner-operator's right to control the manner in which the work is to be performed,

2. 	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3. 	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4. 	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each owner-operator.  The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.

(5/7/91)S49

Standard Modifications

108-1.03  Prosecution and Progress.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule". (5/12/89)M11

Special Provisions

108-1.03  Prosecution and Progress.  In the first paragraph, delete the words "At this time" and substitute:  "Five working days before the preconstruction conference".  (5/7/91)S50

Delete Item 5., and substitute the following:

5.	A plan for erosion and pollution control, as required under  Subsection 641-1.02, Submittals.  (9/21/92)R160

Add the following:  The construction of this project shall be planned and recorded with a Critical Path Method (CPM) schedule.  The schedule shall be used for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

1.	Preparation of CPM Schedule.  At the preconstruction conference, the Contractor shall submit for the Engineer's approval, a detailed initial CPM schedule.  The schedule shall meet the requirements set forth below.

The construction time, for the entire project shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, the Contractor shall do so promptly.  The CPM schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements.  The CPM schedule shall be set up so that the schedule may be read by Prima Vera scheduling software being run on an IBM compatible micro computer with a 1.44 mb disk drive.  All required CPM schedule submittals shall include 1 hard copy and 1 copy of the same schedule on a 3.5-inch double sided diskette.

The CPM schedule shall be presented as a Precedence Diagram Network developed in the activity-on-node format and shall include:

a.	activity description,

b.	activity duration,

c.	resources required for each of the project activities, including:

(1)	labor, showing:

-work days per week

-holidays

-shifts per day

-hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-node diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60-Day Preliminary Schedule.  Before proceeding with any work on site, the Contractor shall prepare, submit, and receive the Engineer's approval of a 60-Day Preliminary Schedule.  This schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include mobilization, submittals, procurement, and construction.

No contract work may be pursued at the site without an approved 60-Day Preliminary Schedule or an approved CPM schedule.

4.	Schedule Updates.  Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the CPM schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions.  The Contractor shall submit a revised CPM schedule within 7 calendar days after this meeting.  The revised schedule shall show finish dates of completed activities and updated times for the remaining work, including any addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

In addition to the CPM schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail the following:

1.	work activities,

2.	manpower involved by trade,

3.	work hours,

4.	equipment involved, and

5.	the location of the work to be performed.

Preparation and updating of the CPM schedule and two week work plans will not be paid for directly.  Failure to submit the CPM work schedule and two week work plans as specified will result in partial withholding of progress payments in accordance with subsection 109-1.06, Progress Payments.

(1/27/92)R11

108-1.05  Character of Workmen, Methods and Equipment.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer.  (9/1/89)R13

108-1.06  Determination and Extension of Contract Time.  Add the following:

4.	Suspensions of Work Ordered by the Engineer.  If the performance of all or any portion of the work is suspended or delayed by the Engineer in writing for an unreasonable period of time (not originally anticipated, customary, or inherent to the construction industry) and the Contractor believes that additional compensation and/or contract time is due as a result of such suspension or delay, the Contractor shall submit to the Engineer in writing, a request for adjustment within 7 calendar days of receipt of the notice to resume work.  The request shall set forth the reasons and support for such adjustment.

Upon receipt, the Engineer will evaluate the Contractor's request.  If the Engineer agrees that the cost and/or time required for the performance of the contract has increased as a result of such suspension and the suspension was caused by conditions beyond the control of and not the fault of the Contractor, its suppliers, or subcontractors at any approved tier, and not caused by weather, the Engineer will make an adjustment (excluding profit) and modify the contract in writing  accordingly.  The Engineer will notify the Contractor of his determination whether or not an adjustment of the contract is warranted.

No contract adjustment will be allowed unless the Contractor has submitted the request for adjustment within the time prescribed.

No contract adjustment will be allowed under this clause to the extent that performance would have been suspended or delayed by any other cause, or for which an adjustment is provided for or excluded under any other term or condition of this contract.

(4/13/89)S36

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  General.  Add the following:  When more than one variety of material or work item is specified for a single pay item number, letter or numeric suffixes will be included within the parenthesis to differentiate the types.  (9/1/89)R14

109-1.02  Measurement of Quantities.  Add the following:

TABLE 109-1

| CONVERSION TO THE SI INTERNATIONAL SYSTEM OF UNITS* |  |  |
| --- | --- | --- |
| To convert from | to | Multiply by |
| mile (US Statute) | meter (m) | 1,609.347 |
| foot | meter (m) | 0.3048 |
| foot (US survey) | meter (m) | 1200/3937 |
| inch | meter (m) | 0.0254 |
| square foot | square meter (m2) | 0.09290304 |
| square yard | square meter (m2) | 0.8361274 |
| acre (US Survey) | square meter (m2) | 4,046.873 |
| cubic foot | cubic meter (m3) | 0.02831685 |
| cubic yard | cubic meter (m3) | 0.7645549 |
| gallon (US liquid) | cubic meter (m3) | 0.003785412 |
| M. Gal. | cubic meter (m3) | 3.785412 |
| pound (lb avoirdupois) | kilogram (kg) | 0.45359237 |
| ton (short, 2000 lb) | kilogram (kg) | 907.1847 |
| pound-force (lbf) | newton (N) | 4.448222 |
| footcandle | lux (lx) | 10.76391 |
| degree Fahrenheit | degree Celsius (C) | tC=(tF-32)/1.8 |

* From ASTM publication E380-89a, Standard Practice for Use of the International System of Units (SI) The Modernized Metric System.

Standard Modifications

109-1.03 Scope of Payment.  Delete the last sentence of the fourth paragraph.  (5/7/91)M33

Special Provisions

109-1.04  Compensation for Altered Quantities.  In the third indented subparagraph, delete the following: ", except that the total payment for the item shall not exceed 75 percent of the total amount bid for the item".  (4/13/89)S38

109-1.05  Compensation for Extra Work.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)R14a

109-1.06  Progress Payments.  Add the following:  Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  This retainage will be released by the Engineer upon receipt of current schedules from the Contractor.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  This retainage will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(9/21/92)R137a

109-1.07  Payment For Materials on Hand.  Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project shall be at a location acceptable to the Engineer.  (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  Description.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  Interpretation.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  Essential Contract Provision.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  Definitions and Terms.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular Contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03 Item 3. for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a Contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  Utilization Goal.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Utilization Goal in order to be eligible for award of this contract.

120-3.01  Determination of Compliance.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  Good Faith Effort.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE Credit.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least one of which must be working on this project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  Default of DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, all of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02, Good Faith Effort.

120-4.01  Method of Measurement.  The Contractor shall be entitled to count toward the DBE Utilization Goal those monies allowed by the Engineer in 120-3.03.04 as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100 percent.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60 percent of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  Basis of Payment.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01, Utilization Goal, until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per subsection 120-3.03, Item 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

A change order is not required for DBE adjustment, the Notice to Proceed shall constitute the notice required to initiate this item.  (12/8/92)R166

Payment or Deduction will be made under:

Pay Item No.	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent Sum

(5/5/89)S33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 Description.  Add the following:  This work shall also consist of the removal of silt fence.

202-2.01  General Construction Requirements.  Add the following:  Silt fence shall be removed and disposed of off the project when adequate vegetative growth insures no further erosion of the slopes. The fabric shall be cut off at ground level and the wire and posts shall be removed.  The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands.  If a sediment height in excess of four inches above ground remains, the sediment shall be spread on the roadway side of the fence location and seeded immediately in accordance with Section 618, Seeding.

202-2.04  Removal of Pavement, Sidewalks, Curbs, Etc.  Add the following:  Pavement removed may be used in the construction of the embankment.  It shall be placed away from wetlands, and no closer than 300 feet to a stream.  The broken asphalt pieces shall be six inches or less in maximum dimension.

For disposal of removed asphalt not used in the embankment, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site currently approved by the DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529.

A DEC approved site for disposal of removed asphalt is available at no charge to the Contractor at the Hiland Road Solid Waste Facility.  In order to use this site, the Contractor shall meet the following requirements:

1.	All dumping shall be coordinated through the Eagle River Street Maintenance office at 694-3487.

2.	Leveling course material may be included with removed asphalt if it does not exceed 30 percent of the total volume delivered.

3.	For quantities over 500 tons, the Contractor shall stockpile materials in a manner acceptable to the Municipality of Anchorage.

4.	Asphalt pieces shall be six inches or less in size.

(6/1/92)R84a

202-3.01  Method of Measurement.  Add the following:  Removal of silt fence will be measured by the linear foot of actual fence removed and disposed of.

202-4.01  Basis of Payment.  Add the following pay item:

Pay Item No.             Pay Item               Pay Unit

202(29)        Removal of Silt Fence       Linear Foot

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-2.01  Common Excavation.  Add the following:  That strata or layer of soil laying above the common excavation unfit for embankment construction and commonly referred to as "overburden" shall be paid for as Common Excavation.

203-2.04  Muck Excavation.  Add the following:  Muck excavation shall also include the removal of permafrost.

Standard Modifications

203-2.05  Borrow.  Add the following:  Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.  (5/12/89)M12

Special Provisions

203-3.01  General.  Add the following to the fifth paragraph:  Prior to obliterating the existing roadway, the existing pavement shall be removed and disposed of in accordance with Subsection 202-2.04, Removal of Pavement, Sidewalks, Curbs, Etc.

203-3.02  Embankment Construction.  On page 96, delete the first sentence of the 3rd paragraph and substitute the following:  When the excavated material consists predominantly of rock fragments or boulders too large to be placed in 8 inch layers, the Selected Material, Type B layer may be placed in thicknesses of 4 feet; however, the top layer of Selected Material, Type B shall be placed in a thickness not greater than 2 feet.  The rock fragments within each layer shall have no dimension greater than the layer thickness.

Standard Modifications

203-3.02  Embankment Construction.  On page 97, delete the 5th paragraph and substitute the following:  All embankments shall be constructed with moisture and density control unless the Engineer determines that such controls are not feasible.  (5/7/91)M35

Special Provisions

203-3.03  Construction of Embankments With Moisture and Density Control.  Add the following:  All embankment within 20 feet of a bridge abutment shall be compacted full width to not less than 100 percent of the maximum density.  All material used within this zone shall be graded to pass the 3-inch sieve.  (10/1/91)R113

203-3.05  Construction of Embankments in Surcharge Areas.  Add the following subsection:

1.	Initial Lift.  An initial lift, 4 feet thick, of selected material, Type A shall be placed by dumping the material onto the advancing embankment and spreading the material over the end or side.  Half width construction will be allowed on the initial lift.

Where the initial lift is placed in areas of standing water, the thickness of the initial lift shall be increased, if required, so that a minimum of one foot of initial lift embankment is above the level of the standing water.  A minimum thickness of 4 feet shall be maintained for the initial lift.

a.	Weight Limitations.  Spreading equipment shall be limited to a maximum weight of 60,000 pounds per unit and a minimum separation of 30 feet shall be maintained between each piece of spreading equipment.  Hauling equipment shall be limited to a maximum total loaded weight of 60,000 pounds.

There are no weight limitations on the initial lift after it has been in place for 48 hours.

2.	Embankment Construction Above Initial Lift.  The initial lift shall be in place a minimum of 48 hours prior to placement of additional embankment material.  All embankment material placed from the top of the initial lift to up to a total embankment height of 6 feet above original ground, or to the bottom of the surcharge layer, whichever is lower, may be placed with no moisture or density requirements.  Compaction in this zone shall be obtained by routing haul equipment uniformly over the entire surface of each layer before the next layer is placed.

All embankment material placed between 6 feet above original ground and the bottom of the surcharge layer, shall be placed in accordance with Subsection 203-3.03, Construction of Embankments With Moisture and Density Control.

3.	Surcharge Layer.  The surcharge layer may be placed in one lift with no compaction requirements.

Muck to surcharge transitions shall be constructed prior to placement of the initial embankment lift.

The final embankment/surcharge height shall be based on design elevation and not construction grade stakes.  The surcharge shall be profiled after completion to verify that it is at design elevation.

Winter construction of embankment in surcharge areas will be allowed if the initial lift is placed on unfrozen ground.  Placement of subsequent lifts up to 6 feet above original ground, and surcharge layers not requiring moisture and density control will also be allowed during winter.  Embankment or surcharge construction using frozen material will not be permitted.

Construction of all surcharge areas shall be completed prior to winter shutdown in the fall of 1993.

203-3.07 Blasting Requirements for Excavation in Rock:  Add the following Subsection:  Periodic geotechnical field inspections will be conducted by representatives of the Department as the backslopes of each cut are exposed; and when unfavorable geologic structure anomalies are encountered, specific recommendations on stabilization will be made.  In the event the Contractor is required by the Engineer to revise a slope which has already been drilled and blasted according to specifications, the Contractor shall perform this work in accordance with Subsection 109-1.05, Compensation for Extra Work.

Two weeks prior to any drilling or blasting in a cut, the Contractor shall submit a blast plan to the Department for review.  The blast plan shall provide the following information:

1.  Station limits of cut or lift.

2.  Drill hole diameter.

3.  Drill pattern and spacing diagram.

4.  Proposed delay sequence of the blast holes.

5.  Explosive per hole and per delay (lb.)

6.  Types of explosives being employed.

7.  Powder factor.

8.  Time of day and day of week.

Review of the drilling, blasting and excavation procedures by the Engineer shall not relieve the Contractor of his responsibility for the accuracy and adequacy of the plan for obtaining adequate breakage, using proper detonation procedures and following proper safety procedures prior to and after the blast.

The Contractor may adopt methods of control blasting and excavation which vary from those required herein, provided short demonstration sections are first used to prove the acceptability of such methods to the satisfaction of the Engineer.

If in the opinion of the Engineer, the methods of excavation required herein or adopted by the Contractor are unsatisfactory in that they result in excessive rock throw, or do not produce a uniform slope and shear face within the neatlines specified, the Contractor shall adopt revised methods, by drilling, blasting, and excavating short sections until a technique is developed that will produce the acceptable results.

Drill hole conditions may vary from wet or filled with water to a dry condition.  The Contractor will be required to use whatever type of explosive and/or accessories necessary to accomplish the specified result.

Storage and handling of explosives shall be in accordance with Subsection 107-1.10, Use of Explosives.

The Contractor shall observe the entire blast area for 15 minutes following a blast to guard against rock fall before commencing work in the cut.

All rock that is loose, hanging, or creating a dangerous situation shall be removed or stabilized during or upon completion of excavation as an integral sequence as each lift is excavated.

Material outside the planned neatline slopes which is unstable and constitutes potential slides in the opinion of the Engineer shall be excavated and removed.  Such material shall be used in the construction of the embankment or disposed of as directed by the Engineer.  The removal and disposal of slide and slipout material will be paid for at the contract unit price for rock excavation if determined not to be the fault of the Contractor's methods.

For all cuts over 10 feet in depth, the Contractor shall use pre-shearing along the lines of the cut slope face.  This depth may be varied if field experience shows such variance will yield acceptable results.

Overburden stripping as shown on the plans shall be done before the associated pre-shear holes are drilled.

Material remaining 8 inches or more inside neat line rock slopes will be removed by pre-shearing techniques or other methods approved by the Engineer unless specifically exempted for aesthetic, geological, or safety reasons by the Engineer.

Pre-Shear Blasting:

"Pre-shearing" shall consist of drilling holes on the plane of the final cut slope and loading each hole with a well distributed explosive charge and firing the holes simultaneously to create a crack along the plane of the final cut slope.  The detonation of the pre-shear line must be before the detonation of all other blasting in the cut.  Production holes will be detonated next and buffer holes will be detonated last.

Spacing of pre-shear blast holes shall be initially set at 24 inches center to center.  If experience shows that a wider spacing will give acceptable results then the Contractor, with the approval of the Engineer, will be permitted to utilize that spacing.  The maximum explosive charge shall be approximately equal to 0.1 pounds of Kleenkut E, Ira Split, Tovex T-1 or equivalent per square foot of final surface rock slope.  Ammonium nitrate fuel oil type explosives shall not be used in pre-shear holes.  These holes will be loaded and detonated 30 feet beyond the end of the worked lift or to the end of the cut, as applicable.  All pre-shear blast holes shall be stemmed full depth with sand or drill fines if initial results without stemming are considered inferior by the Engineer.  Where backbreak becomes a definite problem in the opinion of the Engineer, guide holes shall be drilled between the controlled blast drill holes.  These shall be of the same diameter and in the same plane as the pre-shear blast holes and shall not exceed 10 feet in depth.  They shall remain unloaded.

Buffer Blasting:

Buffer holes shall be drilled approximately 3 feet out from the pre-shear holes and spaced 3 to 5 feet center to center.  These holes will be drilled parallel to the final cut slope and the loads shall not exceed 50 percent of the average explosive loads in the nearest production holes.

Production Blasting:

In production blasting the amount of explosive per delay shall not exceed 500 pounds.  This limit may be reduced or increased if ordered by the Engineer when the blast is in a position to damage equipment, utilities, or if other circumstances require a change.  Production blast holes shall not be drilled closer than 6 feet to the pre-shear line.  Where more than one lift is required, production holes shall not be drilled to an elevation lower than the pre-shear holes.

203-3.08  Rock Stabilization.  Add the following subsection:  Rock bolts of the specified lengths will be installed where directed by the Engineer.  These bolts shall be installed in such a manner as to exert a permanent normal force across potential failure planes.

All rock bolts to be installed on this project including anchorages, corrosion proofing and other appurtenances shall be products of a manufacturer regularly engaged in the manufacture of rock bolts.  Bolts shall be fabricated from deformed bars not less than 1-3/8 inches in diameter.

Anchorage shall be epoxy, polyester resins or cement grout.  Tension shall be transferred to the outer rock by means of grout, bearing plate, washer and nut or by epoxy or polyester resin within the hole.

If used, bearing plates shall be in uniform contact with the rock surface.  If the rock face is not perpendicular to the axis of the bolt, or the rock under the bearing plate is not sound, a bearing pad approved by the Engineer shall be constructed so that the bolt is not bent when the tension is applied.

All sections of the bolts and accessories necessary to the function of the bolts shall be fully corrosion protected.

Grouts, epoxies or polyester resins shall be proven, non-shrink materials capable of permanently developing the bond and internal strengths necessary for the tensioning required on this project. Fondu cement shall not be used.  Epoxy or polyester resins in cartridge form shall be approved by the Engineer.

Rock bolts shall be tensioned to 25,000 pound minimum.  When external nuts are used to transfer this tension to the surface rock, the load shall be held for 10 minutes before tightening the nut.  Load/extension measurement will be made during tensioning.  When epoxy or polyester resins are used to transfer the tension to the outer rock, the load shall be held sufficiently long to allow hardening of the material.  Load/extension measurements shall be made to assure the load is transferred to the rock upon release of the tensioning device.

During tensioning the load shall be held for at least 10 minutes and the extension of the bolt shall not exceed the elastic strain of the bolt by more than 20 percent.  If a bolt fails these tests, it shall be replaced or an additional bolt shall be installed in a separate hole.

The hydraulic jack and pressure gauge used for tensioning shall be calibrated by a registered calibration agency a maximum of one month prior to the tensioning operation and a copy of the calibration certificate shall be shown to the Engineer before tensioning begins.

The installation, corrosion protection, and the tensioning shall be carried out according to the manufacturer's specifications.

203-4.01  Method of Measurement.  Add the following:  No deduction from the excavation quantities will be made for pavement removed under Item 202(2), Removal of Pavement.

Excavation for structures will be measured and paid for under Item 203(1), Common Excavation.

Rock Bolts will be measured by each unit installed.

Standard Modifications

203-5.01  Basis of Payment.  Change Pay Items 203(5), (6) and (7) to read:  Borrow, Type __.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)M12

Special Provisions

203-5.01  Basis of Payment.  Add the following:  Grading and placement of material used within 20 feet of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(6A) Borrow, Type A.(10/1/91)R113

Furnishing, installing and maintaining platform scales, tickets, scale house and electronic weigh system in accordance with Section 644 will not be paid for directly, but will be subsidiary to Item 203(6-A) Borrow, Type A.

Pre-shear blasting, buffer blasting and production blasting will not be paid for directly, but will be subsidiary to Item 203(2), Rock Excavation.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

203(15-__)	__-Foot Rock Bolts	Each

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01 Materials.  Delete this subsection in its entirety and substitute the following:  Bedding and backfill materials shall meet the requirements for Selected Material, Type A, as specified in Subsection 703-2.07, Selected Material.  Pipe bedding and backfill material shall also pass the 3-inch sieve.  Excavations below subgrade across roadway embankments shall be compacted to not less than 98 percent of maximum density.

Selected Material, Type A pipe backfill shall extend a minimum of 12 inches above the pipe.  Excavated native material shall be utilized for the remainder of the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07, Selected Material.  Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material.  All suitable material from structure excavation shall be used for bedding and backfill prior to using material from another source.

204-3.01  Construction Requirements.  Add the following to the third paragraph:  Native material may be utilized for electrical conduit bedding and backfill outside the pavement structure if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07, Selected Material.  Compaction may be as approved by the Engineer.

(3/23/93)R25

SECTION 205

EXCAVATION, BACKFILL AND

FOUNDATION FILL FOR STRUCTURES

Special Provisions

205-1.01  Description.  Add the following:  This work shall also include excavation and backfill for the structural plate arch constructed under Section 602.

205-3.03  Backfill.  Add the following:  Structural plate arch shall be backfilled with Selected Material, Type A to the dimensions shown on the plans and in accordance with Section 602.

All backfill material placed within 2 feet of the arch shall be graded to pass the 3-inch sieve.

Backfill for the Selected Material, Type A below the binwall base plates shall placed loose to a depth below the base plates of 8 inches.  This material shall not be compacted.

205-5.01  Basis of Payment.  Add the following:  	Grading backfill material to pass the 3-inch sieve will not be paid for directly, but will be subsidiary to Item 203(6A), Borrow, Type A.

There will be no excavation for structures paid for under this section.  Excavation for structures will be measured and paid for as common excavation.

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01  Materials.  Delete the last two sentences of the first paragraph and substitute the following:  The gradation of base course material for use under asphalt concrete pavement shall conform to the requirements for Grading D-1.  The gradation of base course material for use as a surface course for the unpaved portions of driveways shall be Grading E-1.

Add the following after the first paragraph:  At the Contractor's option, recycled asphalt pavement (RAP) may be substituted for crushed aggregate base course, inch for inch, if the following conditions are met:

1.	RAP shall be crushed or processed to 100 percent by weight passing the 1½-inch sieve and 95 - 100 percent by weight passing the 1-inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| SIEVE | % PASSING BY WEIGHT |
| --- | --- |
| 1 | 100 |
| ¾ | 70-100 |
| _ | 50-90 |
| No. 4 | 35-78 |
| No. 10 | 20-65 |
| No. 40 | 8-40 |
| No. 80 | 5-25 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAP.

301-3.01  Placing.  Add the following: 	Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.  (9/1/89)R26

301-3.03  Shaping and Compaction.  Add the following:  If recycled asphalt pavement is substituted for crushed aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern.  The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 90 psi (+5 psi) and the roller shall have a minimum operating weight per tire of 2,000 pounds.

301-5.01  Basis of Payment.  Add the following:  If recycled asphalt pavement is substituted for crushed aggregate base course, it will be paid for as Item 301(1), Crushed Aggregate Base Course at the unit price shown on the bid schedule for that item.

Payment for base course material will be made under Item 301(1), Crushed Aggregate Base Course, regardless of the gradation type used.

Delete this Section and substitute the following:

SECTION 401

ASPHALT CONCRETE PAVEMENT

Standard Modifications

401-1.01  Description.  This work consists of the furnishing and mixing of aggregate and asphalt cement at a central mixing plant and the hauling, spreading, and compaction of the asphalt concrete mixture on a previously prepared surface, all as specified in the contract and in reasonably close conformance with the lines, grades and thickness shown on the plans.

401-2.01  Composition of Mixtures.  Mixtures shall be composed of aggregate and asphalt cement combined as specified for the type and class shown in the bid schedule.

At least 15 calendar days prior to the production of asphalt concrete pavement mix, the Contractor shall submit the following to the Engineer:

1.	Notification that aggregate proposed for the mixture is available for sampling.

2.	A letter stating the proposed gradation for the Trial Job Mix Design, gradations for individual stockpiles, and blend ratio for each aggregate stockpile.  Job Mix Design proposals by the Contractor shall be within the gradation target value ranges set in Table 703-3.

3.	A minimum of three 1-gallon samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a temperature viscosity curve for the asphalt cement.

4.	A 1/2 pint sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

The Contractor shall accompany the Engineer during sampling, and shall furnish all the assistance needed to assure that the Engineer obtains representative samples.

From this information, the Engineer will establish the Job Mix Design which shall become a part of the contract and shall be followed unless modified in writing.  Job Mix Design test results will be available within 7 working days after submittal.

The Job Mix Design shall be determined by and shall conform to the requirements of ATM T-17.

Changes in the Job Mix Design warranted by changes in the aggregate or sources of aggregate shall be submitted by the Contractor in the same manner as the original submittal.

If the mixture is obtained from a commercial source, the Contractor shall submit a certified statement of its components and their proportions as outlined in these specifications for approval as a Job Mix Design.

The full tolerances specified below shall be applied to the approved Job Mix Design gradations and shall not be limited to the broad bands listed in Table 703-3.  Tolerances shall not be applied to the largest specified screen.

| Sieve Size or Item | Tolerance (Percent Passing) |
| --- | --- |
| 3/4 inch | +/- 8% |
| 1/2 inch | +/- 7% |
| 3/8 inch | +/- 7% |
| No. 4 | +/- 7% |
| No. 8 | +/- 6% |
| No. 16 | +/- 6% |
| No. 30 | +/- 5% |
| No. 50 | +/- 4% |
| No. 100 | +/- 3% |
| No. 200 | +/- 3% |
| Asphalt % | +/- 0.4% |

Special Provisions

Temporary pavement shall meet the requirements for Asphalt Concrete, Type II, Class B.

Standard Modifications

401-2.02  Aggregates.  Aggregates shall conform to the requirements of Subsection 703-2.04.

401-2.03  Filler. Filler shall conform to the requirements of AASHTO M 17.

401-2.04  Asphalt Cement.  The grade of asphalt cement will be specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702, Asphalt Materials.  Asphalt cement may be conditionally accepted at the source.  If the cement is to be conditionally accepted at the source, the Contractor shall provide a manufacturer's certificate of compliance in accordance with Subsection 106-1.05 and test results of the applicable quality requirements of Section 702 before the cement is shipped.

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at 275 degrees Fahrenheit) of the asphalt cement used on the project changes from the viscosity of the cement supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended while a new Job Mix Design proposal is submitted for approval.

401-2.05  Anti-Strip Additives.  Anti-strip agents used shall be an approved type in the proportions determined by ATM T-14 and included in the approved Job Mix Design.

401-2.06  Quality Control and Acceptance.

1.	Process Control by Contractor.  It is understood that the Contractor is responsible for furnishing the sampling and testing of materials for process quality control, including screening, crushing, blending, and stockpiling of the aggregate, production and laydown of the mixture, and monitoring of compaction.

At the site, the Contractor shall furnish a field laboratory for process control testing.  The contractor-furnished laboratory shall be shared with the Department for concurrent testing.

A Crushing Control Plan shall be submitted at least 15 working days prior to the preconstruction conference.  The plan shall include a proposed testing frequency for aggregate gradation.  Abbreviated testing for process control of gradation shall be in accordance with Alaska Standard Practice SP-9.  Such sampling and testing will be coordinated with the Department and split samples are to be provided to the Department.

A Paving and Plant Control Plan shall be submitted at a pre-paving meeting to be held a minimum of 5 working days prior to initiating paving operations.  The Paving and Plant Control Plan shall outline the steps taken to assure product consistency and to minimize segregation and premature cooling of mixtures.  This plan shall include a proposed testing frequency for gradation, asphalt content, and compaction.  It shall also include a plan for the handling of or elimination of the wings on the paver hopper to prevent dumping and placement of cooled mix onto the roadway.

2.	Acceptance Testing by Department.  The Department will perform sampling and testing for acceptance of the work in accordance with the Department's testing frequency guide and standard acceptance test methods specified below.  Such testing may be done concurrently with the Contractor's process control testing.  Acceptance test results will be available to the Contractor as soon as possible upon their completion.

Sampling for the determination of aggregate gradation will be from the aggregate cold feed, individual hot bins, or from the combined aggregate just prior to the introduction of the asphalt cement.  All aggregate samples will be split and the second half made available to the Contractor.

Acceptance testing for asphalt cement content will be determined by ATM T-16, ATM T-23 or AASHTO T 164.  Sampling for the determination of asphalt cement content will be from the mixture at the time of placement.

Samples taken for determination of density compliance shall be taken from the finished mat after final rolling.  Acceptance testing for field density will be determined in accordance with ATM T-22.

3.	Unacceptable Work or Material.  Any mixture which is contaminated, segregated, or which does not otherwise conform to the specifications will be rejected and replaced at no additional cost to the Department with conforming material in accordance with Subsection 105-1.11, Removal of Unacceptable and Unauthorized Work.  All costs associated with removal and replacement of unacceptable mixture shall be borne by the Contractor.  At the discretion of the Engineer, unacceptable pavement may be overlaid with acceptable pavement at no additional cost to the Department.

CONSTRUCTION REQUIREMENTS

401-3.01  Weather Limitations.  The mixture shall not be placed on a wet surface, or on an unstable roadbed, when the base material is frozen, or when weather conditions prevent proper handling, compacting, or finishing of the mixture.  No mixture shall be placed when the surface upon which the pavement is to be placed is at or below 35 degrees Fahrenheit.

401-3.02  Bituminous Mixing Plants.  Mixing plants shall conform to AASHTO M 156.

Proportioning (batch) scales shall not be used for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

401-3.03  Hauling Equipment.  Trucks used for hauling mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime solution or other manufactured asphalt release agent included on the Department's Approved Products List.  Diesel or fuel oil shall not be used.  Each truck shall have a cover of canvas or other suitable material of such size as to protect the mixture from the weather, when required, so that the mixture will be delivered on the road at the proper temperature.

401-3.04  Asphalt Pavers.  Asphalt pavers shall be self-propelled units, provided with a heated vibratory screed and equipped with a paver control system which shall automatically control the laying of the mixture to specified transverse slope and specified longitudinal grade.  The paver control system shall be automatically actuated by the use of a mobile string line, ski, or other approved grade follower.  The length of the ski, mobile string line or other device shall be at least 30 feet in length.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation.  The hopper shall be equipped with a distribution system to place the mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Auger extensions shall be within 1.5 feet of the gates.

Extendable wings may be permitted for tapers, guardrail widening and approaches.

The use of a pickup machine to transfer the mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collection of the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any other detrimental effects are observed.

401-3.05  Rollers.  Rollers shall be of the steel wheel and pneumatic tire type, self propelled, in good condition, capable of reversing without backlash, and operated at speeds slow enough to avoid displacement of the mixture.  The number and weight of the rollers shall be sufficient to compact the mixture to the required density and surface smoothness while it is still in a workable condition, and be capable of maintaining the pace of the paving operation.  Specific roller requirements for construction of density "control strips" are further described in Subsection 401-3.12, Compaction.  The use of equipment which results in crushing of the aggregate will not be permitted.

401-3.06  Preparation of Existing Surface.  When the surface of the existing pavement or old base is irregular, it shall be brought to uniform grade and cross section, as directed.

If determined necessary, the existing surface shall be cleaned of loose material by sweeping with a power broom, supplemented by hand sweeping as required.

Contact surfaces of curbing, gutters, manholes, and other structures shall be coated with a thin, uniform coating of prime or tack coat material prior to the asphalt concrete mixture being placed against them.

Surfaces which have received a prime or tack coat shall be allowed to cure, as directed, prior to placement of asphalt concrete mixture.  Surfaces which have received an emulsion tack coat shall be allowed to break prior to placement of asphalt concrete mixtures.

401-3.07  Preparation of Asphalt Cement.  A continuous supply of asphalt cement shall be supplied to the mixer at a uniform temperature, within 25 degrees Fahrenheit of the Job Mix Design mixing temperature.

401-3.08  Preparation of Aggregates.  The aggregate for the mixture shall be heated and dried to a temperature compatible with the mix requirements herein specified.  Flames used for drying and heating shall be properly adjusted to avoid damage to the aggregate and to avoid soot or unburned fuel on the aggregate.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5 percent (by total weight of mix), as determined by ATM T-25.

401-3.09  Mixing.  The aggregate and asphalt cement shall be combined in the mixer in the amounts required to meet the Job Mix Design.  Anti-stripping additive shall be furnished as required.

The materials shall be mixed until a complete and uniform coating of the aggregate and a thorough distribution of the asphalt cement throughout the aggregate is obtained.  For batch plants, dry aggregate shall be in motion prior to the addition of asphalt cement.  Wet mixing time shall be determined for each plant and for each type of aggregate used.  The minimum percent of coated particles used to establish the mixing time interval shall be 98 percent using AASHTO T 195.

The temperature of the mixture at the time of mixing shall be as determined by the Job Mix Design.

401-3.10  Temporary Storage of Asphalt Mixture.  Temporary storing or holding of hot mixture in silo type storage bins will be permitted.

All the mixture drawn from the silo type storage bins shall conform to all of the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

401-3.11  Spreading and Placing.  The mixture shall be laid only upon stable surfaces approved by the Engineer, spread and struck off and compacted to the required thickness.  Asphalt pavers shall be used to distribute the mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 401-3.13, Joints.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable, the mixture shall be spread, raked and luted by hand tools.  For such areas the mixture shall be placed to the required compacted thickness.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge dropoff.  When the pavement edge dropoff exceeds 2 inches, shoulder material shall be placed against the pavement edge.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that segment, as defined by the Paving Plan, has been placed and accepted.

Paving shall not begin until all adjacent concrete curb has been poured and cured for 72 hours or until satisfactory concrete strength is achieved.

Special Provisions

Asphalt to be placed over bridge membranes shall not be placed until the membrane has cured to the proper state to prevent damage by the overlaying operation.  Vehicles, except the spreader and trucks used for hauling the asphalt overlay mix, shall not be operated on the membrane.  Paving machines used over the membrane waterproofing shall be rubber tired or rubber tracked.   The Contractor shall adhere to the manufacturer's published minimum and maximum temperature limitations for asphalt overlay material.  Steel-wheeled rollers only shall be used to compact the asphalt paving on the bridge decks.  The use of vibratory rollers, with vibrator on, will not be permitted.

Standard Modifications

401-3.12  Compaction.

General.  Immediately after the mixture has been spread, struck off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.  Rolling shall commence as soon as the rolling does not cause undue displacement, cracking or shoving.  Any displacement occurring as a result of the reversing of the direction of a roller, or from other causes, shall be corrected promptly by the use of rakes and addition of fresh mixture when required.  Care shall be exercised in rolling not to displace the line and grade of the mixture.  Rollers shall move at a slow but uniform speed with the drive roll or wheels nearest the paver.

Unless otherwise directed, rolling shall begin at the sides and proceed parallel with the road centerline, each overlapping one-half the roller width, gradually progressing to the crown of the road.  When paving in echelon or abutting a previously placed lane, the longitudinal joint shall be rolled first to provide pinching the material in place.  On super-elevated curves the rolling shall begin at the low side and progress to the high side by overlapping of trips parallel with the centerline.

Along forms, curbs, headers, walls, and other places not accessible to the rollers, the mixture shall be thoroughly compacted with hot hand tampers or with mechanical tampers.  On depressed areas, a trench roller may be used or cleated compression strips may be used under the roller to transmit compression to the depressed area.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

Control by Acceptance Strip.

1.	Control Strips.  A control strip shall be constructed at the start of each course after the plant and equipment are providing a consistent mix, and repeated as ordered whenever:

a.	there is a change in the mix composition,

b.	there is a change in ambient temperature of 30 degrees F or greater, or,

c.	routine tests indicate changes from results found in previous qualifying control strips.

Each control strip shall be constructed with the approved Job Mix Design.  The control strip shall remain in place as a section of the completed work, provided it complies with requirements for gradations, asphalt cement content, adequacy of mixing and line and grade.  It shall be removed and replaced at the Contractor's expense or accepted to remain in place in accordance with Section 105-1.03, Conformity with Plans and Specifications, and a new control strip constructed if it does not meet specification requirements.  Paving operations may not proceed beyond the control strip until the mixture conformance to specifications has been confirmed and production paving is authorized.

Each control strip shall be one lane in width, 300 feet in length and shall be of the depth specified for the pavement course concerned.

Initial or breakdown compaction of a layer of the mixture shall be performed with a 2-axle tandem or a 3-wheel roller weighing at least 12 tons except that approved vibratory compacting equipment may be used for the initial or breakdown compaction if it is operated according to the procedures designated in the approval.

A pass shall be one movement of a roller in either direction.  A coverage shall be as many passes as are necessary to cover the entire width being paved.  Each coverage shall be completed before subsequent coverages are started.

The initial or breakdown compaction shall be followed immediately by intermediate rolling with a pneumatic-tired roller which exerts a tire pressure of at least 80 psi over the tire contact area.  Coverages with a pneumatic-tired roller shall start when the temperature of the mixture is high as practicable and shall be completed while the temperature of the mixture is at or above 160 degrees F.  Intermediate rolling shall be performed with a 2-axle tandem roller when breakdown rolling is performed with a pneumatic roller.

Each layer of mixture shall be additionally compacted, without delay, by a final rolling consisting of not less than one coverage with a steel-tired roller weighing not less than 8 tons.  Compaction of the control strip shall commence as soon as possible after placement of the mixture and be continuous and uniform over the entire control strip.

The following rolling and density testing procedures shall be used on the control strip:

a.	Breakdown rolling.  Thirty second nuclear density counts shall be taken at three randomly selected locations after each roller coverage at each test site.  Rolling shall continue until there is less than one pound increase in average density per roller coverage.

b.	Intermediate rolling.  Rolling shall continue until at least three complete coverages have been made and there is less than one pound increase in average density per roller coverage.

c.	Finish rolling.  Thirty second nuclear density counts shall be taken at five randomly selected locations after each roller coverage at each test site.  The average density obtained after the first coverage shall be taken as a new beginning point.  Final rolling shall continue until all roller marks are removed and there is less than one pound increase in average density per roller coverage.

d.	Density standard.  Ten randomly selected one-minute density counts shall be taken to determine the average density of the control strip.  This is the density standard for the project until a new control strip is constructed.  To confirm the adequacy of the compaction of the control strip, seven 6-inch minimum diameter core samples will be taken at randomly selected locations.  The average density of these cores shall be at least 95 percent of the maximum specific gravity (as determined by AASHTO T 209) multiplied by 62.4.

2.	Acceptance Strips.  Acceptance density testing will be accomplished while the pavement is hot enough to permit further densification if such is shown to be necessary.

The pavement courses shall be divided into acceptance strips consisting of not more than 500 tons for the purpose of defining areas represented by each series of density acceptance tests.

The types of rollers used and their relative positions in acceptance strip compaction shall be the Contractor's option, provided that at least 2 coverages of a pneumatic-tired roller having an 80 psi minimum contact pressure are applied.

The density of each acceptance strip will be evaluated based on the results of three tests with a portable nuclear test device performed at randomly selected sites within the acceptance section.  Each test will consist of the average of two one-minute readings with the gauge rotated 90 degrees between readings.  The average density obtained for the three test in each acceptance strip shall be at least 98 percent of the mean density obtained in the approved control strip.  In addition, each individual test value obtained within an acceptance strip shall be at least 95 percent of the mean density of the strip.

If either the average density of the acceptance strip or an individual test value does not meet the density requirements, the Contractor shall continue compactive effort until the required density is obtained.

After the required density has been attained in the acceptance strips, further finish rolling may be necessary to remove roller marks or other surface irregularities and to meet the required surface tolerances.

401-3.13  Joints.  Joints shall be made in such manner as to ensure a continuous bond between old and new sections of the course.  All joints shall present the same texture and smoothness as other sections of the course.

A thin tack coat of asphalt cement or emulsion shall be sprayed on all cold joints and allowed to break prior to placing any fresh mixture against the joint.

Transverse joints shall be formed by cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.

The longitudinal joints in one layer shall offset those in the layer immediately below by approximately six inches.  However, the joints in the top layer shall be at centerline or lane lines.  Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset not more than one foot.

Pavement that are 1.5 inches or thicker shall be constructed with a modified wedge joint the entire length of the face of the exposed longitudinal joint between adjacent travel lanes.  The taper shall have a maximum horizontal to vertical slope of 3:1 at the bottom and

shall be vertical at the top for a height equal to the largest aggregate size.

Improperly formed joints resulting in surface irregularities shall be removed, full depth, replaced with new material, and thoroughly compacted.  Attempting to roll out an improper joint after the material has cooled below 160 degrees Fahrenheit shall not be allowed.  All pavement removal shall be precut to a neat line using a power driven saw.

401-3.14  Surface Tolerance.  The surface will be tested after final rolling at selected locations using a 10 foot straightedge.  The variation of the surface from the testing edge of the straightedge between any two contacts with the surface shall not exceed 3/16 inch.

401-3.15  Patching Defective Areas.  Skin patching will not be permitted.  Defective materials shall be removed for the full thickness of the course.  The pavement shall be cut so that the sides are perpendicular and parallel to the direction of traffic and so that the edges are vertical.  Edges shall be tack coated with asphalt cement or emulsion.  Fresh mixture shall be placed in sufficient quantity so that the finished surface will conform to grade and smoothness requirements.  The mixture shall be compacted to the density specified herein.

401-4.01  Method of Measurement.  Asphalt concrete pavement and asphalt cement will be measured by the ton or by the square yard in accordance with Section 109.  The tonnage used shall be the weight used in the accepted pavement and no deduction will be made for the weight of asphalt cement and anti-stripping additive in the mixture.

The method of measurement to be used for Asphalt Cement will be limited to one of the following procedures.  The Engineer shall approve in writing the procedure to be used.  The method used initially must be the one used for the duration of the project.

1.	Supplier's invoices minus waste, diversion and left-over.  This method may be used on projects where deliveries are made in tankers and the plant is producing material for one project only.  Tank stickings will be used to compute left-over.  Waste and diversion will be computed in a manner to be determined by the Engineer.

2.	The weight of asphalt cement shall be calculated using the percent of asphalt cement multiplied by the total tonnage represented.  Percent of asphalt cement shall be determined by ATM T-23.

The Engineer may direct at any time that tankers shall be weighed before and after unloading in the presence of the Engineer.  If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

401-5.01  Basis of Payment.  The accepted quantity will be paid for at the contract unit price for the pay item listed below, complete in place.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $3.75 per 0.25 percent additive per ton of asphalt cement.

(7/16/93)M61

Special Provisions

A change order/directive is not required for anti-stripping additive or asphalt price adjustment pay items.  The approved mix design will initiate Item 401(4), Anti-Stripping Additive at the prescribed rate and the Notice to Proceed shall constitute the notice required to initiate Item 401(5), Asphalt Price Adjustment.  (5/3/93)R169

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1)	Asphalt Concrete Pavement,	Ton

Type ___, Class ___

401(2)	___ Asphalt Cement	Ton

401(4)	Anti-Stripping Additive	Contingent

Sum

401(6)	Temporary Pavement	Ton

When more than one type of Asphalt Concrete or Asphalt Cement appears on the plans and bid schedule, letter suffixes will be included within the parentheses of the pay item numbers in order to differentiate between different types.

Separate payment will not be made for asphalt cement or anti-stripping additive for Item 401(6), Temporary Pavement.

PAGES 87 THROUGH 94 HAVE BEEN DELETED FROM THIS CONTRACT.

PAGES 87 THROUGH 94 HAVE BEEN DELETED FROM THIS CONTRACT.

SECTION 501

STRUCTURAL CONCRETE

Standard Modifications

501-3.01  Proportioning.  In the second paragraph under Item 3, replace "Polysar 1186" with "Styrofan 1186".  (5/12/89)M14

Special Provisions

501-3.01  Proportioning.  Revise this subsection as follows:  In Table 501-1, Class of Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S, W and A-A concrete.

Add the following to subparagraph 4:  Fly ash may be used only in the abutments and piers of the Old Glenn Overhead Bridge, No. 1883.  Fly ash shall not be used in the girders, deck, pathways, or concrete railings of any bridge on this project.

501-3.02  Batching.  Add the following to item 5. Batching:  Furnish the mix design number and a list of all ingredients, their individual weights, and moisture content of the various aggregates and the individual truck water meter reading when batched, for each truck load or batch of concrete supplied.  (5/7/91)R147

501-3.05  Forms.  Add the following:

Architectural Finish.  The thickness of concrete members that receive an architectural finish shall be increased so that the specified minimum cover to reinforcing steel is maintained.

The following concrete surfaces shall receive an architectural finish:

1.	The vertical exterior surfaces of the concrete bridge railings that are exposed to view from the roadway beyond the limits of the bridge.  The longitudinal limits shall be the outside end of the bridge rail transitions.

2.	The sides of the pier shaft for the Old Glenn Overcrossing.  This finish shall approximate the appearance of the abutment retaining walls.  Relief shall not exceed one inch.

The architectural finish may be created by the form itself or by a liner attached to the formwork surfaces, and shall preferably be a pattern of standard manufacture.  The pattern shall produce a uniform vertical rib and groove texture.  The overall depth (relief) of the pattern shall not exceed one inch, and the center-to-center rib spacing shall not exceed three inches.  The widths of the rib surface and the base of the grooves shall be approximately equal.  Samples of the pattern shall be submitted for approval.

Inserts.  Threaded inserts may be cast in the edges of concrete decks as an aid in forming sidewalks and concrete railings.  Spacing of the inserts shall be four feet and the insert size shall be appropriate for the intended loads.  After the forms are removed, the recesses remaining at the insert shall be filled and patched with grout of the same color and texture as the deck concrete.

501-3.06  Placing Concrete.  Delete the last sentence of item 2., Pumping Concrete, and substitute the following:  Concrete samples for testing shall be taken at the discharge end of the pipe.  The Contractor shall provide the necessary samples of concrete at the direction of the Engineer or his representative.  (10/1/91)R92

Under Item 10., Setting Shoes and Bearing Plates, add the following:  Unless otherwise shown on the plans, pier and abutment caps on bridges shall be finished parallel to the roadway grade and parallel to the roadway cross slope or crown.  Grade strips on each side of the caps shall be independently set and the grade at the centerline of the bearings shall be carefully checked prior to casting the concrete.

501-3.07  Finishing Concrete Surfaces.  Under Item 3. Concrete Decks, modify the following:

Delete the second sentence of the 15th paragraph, (third paragraph on page 194) and substitute the following:  The surface shall not vary more than 0.01 feet from the lower edge of the straightedge.

501-3.08  Curing Concrete.  Add the following to Item 2. Membrane Curing:  Membrane curing shall not be used for concrete decks.

501-5.01  Basis of Payment.  Add the following:  Architectural finish for the bridge rails will be subsidiary to Item 507(4) Concrete Bridge Rail, Type 1.

Architectural finish for the piers of the Old Glenn Overcrossing will be subsidiary to Item 501(1), Class A Concrete.

SECTION 502

PRESTRESSED CONCRETE STRUCTURES

Standard Modifications

502-1.01  Description.  Add the following to the fourth paragraph:  Alternative designs shall be based on the assumed prestressing losses outlined in Subsection 502-1.02, Prestressing Methods.

Special Provisions

502-1.01  Description.  Add the following:  This work shall also include the application of silane sealer to all surfaces of all concrete girders for this project.

Standard Modifications

502-1.02  Prestressing Methods.  Revise the assumed stress losses in the fourth paragraph to read:

Pretensioning:

Stress relieved strand            45,000 psi

Low relaxation strand             40,000 psi

Post-tensioning, excluding friction losses:

Stress relieved strand            35,000 psi

Low relaxation strand             32,000 psi

Bar                               25,000 psi

The above losses are based on a jacking stress in the strands of no more than 0.70 GUTS (guaranteed ultimate tensile strength).

502-3.01  Construction Requirements.

6.	Pretensioning.  In the last paragraph, change "0.80 GUTS" to read "0.75 GUTS".

Special Provisions

502-3.04  Placing.  Add the following to the sixth paragraph:  The grout shall be packed and rodded into the joints to form a dense, impermeable filling.  The dry consistency of the grout tends to result in a porous filling, so additional compaction effort will be needed to achieve the required density.  The grout surface shall be smooth and neat in appearance.  The grout surface shall meet the girder edges throughout their lengths, and shall match the elevation of the surface of the girders with a tolerance of + 1/8 inches.  Patching and grinding may be required.

502-3.05  Application of Silane Sealer.  Add the following subsection:  All concrete surfaces shall be treated with a solution of 40 percent by weight alkyltrialkoxysilane in an anhydrous alcohol solvent (hereafter abbreviated as silane).  Prior to the sealing operation the surfaces shall be cleaned according to the manufacturer's recommendations.  The silane sealer shall be shop applied according to the manufacturer's recommendations.

Standard Modifications

502-4.01  Method of Measurement.

1.	Structural Members.  In the second sentence, change reinforcing and prestressing steel," to read "reinforcing steel (uncoated and/or epoxy coated), prestressing steel,".

Special Provisions

502-4.01  Method of Measurement.  Add the following:  All labor, materials, equipment and work necessary for sealing the concrete surfaces with silane penetrating sealer will not be measured for payment but will be incidental to and included with Prestressed Concrete Structural Members.

Standard Modifications

502-5.01  Basis of Payment.  Delete the next to the last paragraph. (5/12/89)M16

Special Provisions

502-5.01  Basis of Payment.  Add the following:  All labor, equipment and materials required for sealing the concrete surfaces designated in subsection 502-1.01 Description, with silane penetrating sealer will not be paid for separately, but will be subsidiary to the Prestressed Concrete Structural Members.  No adjustment in the contract price for prestressed concrete girders will be made when epoxy coated prestressing strands are fabricated integrally with the units.

No adjustment in the contract price for prestressed concrete girders will be made when epoxy coated prestressing strands are fabricated integrally with the units.

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01  Description.  Add the following:  This work will include the epoxy coating of appropriate reinforcing steel bars.  All reinforcing steel in the exposed vertical face of a retaining wall facing the roadway, and as noted on the plans shall be epoxy coated.

Standard Modifications

503-3.05  Splicing.  Delete the first and second paragraphs and substitute the following:  Lap splices for reinforcing bars shall be as shown on the plans or as directed.  (5/12/89)M17

Special Provisions

503-5.01  Basis of Payment.  Add the following:  Reinforcing steel embedded in the bridge deck and used for anchoring bridge railings, as well as all reinforcing steel contained in the railings, will not be paid for under this section, but will be subsidiary to Item 507(4) Concrete Bridge Railing.

If epoxy coating the reinforcing steel is required, it will be a subsidiary obligation and no separate payment will be made.

(9/1/89)R38

SECTION 504

STEEL STRUCTURES

Standard Modifications

504-3.01  Fabrication.  Under item 7. Bolted Connections, High Tensile Strength Bolts,  delete paragraphs 5 through 14, and Table 504-3 and substitute the following:  All fasteners shall be tightened to give at least the required minimum tension values shown in Table 504-2 on completion of the joint.  All bolts and nuts in a connection shall be made by the same manufacturer.

In order to achieve the minimum tension values shown in Table 504-2, Required Bolt Tension, direct load indicating washers, conforming to the requirements of ASTM P959, shall be used.  The suitability of the device shall be demonstrated by testing a representative sample of not less than three devices for each diameter and grade of fastener used in the structure in a calibration device capable of indicating bolt tension.  The test assembly shall include flat, hardened washers, if required in the actual connection, arranged as those in the actual connection to be tensioned.  The calibration test shall demonstrate that the device indicates a tension not less than five percent greater than that required by Table 504-2, Required Bolt Tension.  Manufacturer's installation procedures shall be followed for installation of bolts in the calibration device and in all connections.  Special attention shall be given to proper installation of flat, hardened washers when load indicating devices are used with bolts installed in oversized or slotted holes and when the load indicating devices are used under the turned element.

Unless otherwise permitted, the load indicating device shall be placed under the bolt head, and only the nut shall be turned when tightening the bolt.  The device shall indicate full tensioning of the bolt when the opening reaches zero.

Bolts shall be installed in all holes of the connection and brought to snug tight condition.  All fasteners shall then be tightened, progressing systematically from the most rigid part (usually near the center) of the connection to the free edges, or as directed, in a manner that will minimize relaxation of previously tightened fasteners.  It may be necessary to provide multiple cycles of systematic tightening.

High-strength bolts shall not be reused.  Previously fully-tightened bolts which may have been loosened by the tightening of adjacent bolts shall be removed and replaced with new bolts, nuts, and load indicating devices.

(5/12/89)M18

Special Provisions

504-3.01  Fabrication.	Add the following:  For Tension Control bolts, the Contractor shall follow the manufacturer's recommended installation procedures.

504-3.02  Erection.  Add the following under Item 8., Setting Shoes, and Bearings:  Epoxy adhesive, conforming to AASHTO M-235, Type 1, Grade 2, Class B, shall be applied to the bottom surfaces of the elastomeric bearing pads prior to placement, and the pads shall be secured and restrained from movement until the epoxy has cured and full adhesion is achieved between the pads and the concrete.  (9/1/89)R39

504-3.03  Painting.  Add the following:  Damaged galvanizing shall be repaired in accordance with AASHTO M-36.

SECTION 505

PILING

Special Provisions

505-2.01  Materials.  Add the following:  All welding shall be performed in accordance with Subsection 505-3.15, Welding.

505-3.03  Pile Bearing Values.  Delete this subsection in its entirety and substitute the following:  All piles shall be driven to the required bearing capacity.  The required bearing capacity is the design load shown on the general layout sheet in the plans multiplied by a factor of safety of 2.0.

505-3.07  Extensions, Splices and Buildups.  Delete the first sentence of item 1. and substitute the following:  If the length of a steel pile is not sufficient to obtain adequate penetration, an additional length shall be spliced to it.  The length of the spliced section shall be such that no splice shall be closer than 10 feet to the cutoff elevation of the pile after driving.

505-3.09  Driving Piles.  In the first paragraph, fifth sentence, change "1/2 inch" to "1-inch".

Delete the tenth paragraph, (second paragraph on page 250), and substitute the following:  All pile driving equipment used by the Contractor shall be subject to approval by the Engineer.  A vibratory driver may be used to initially set the piles.  The pile driving system shall be equipped with a suitable thickness of new hammer cushion material to prevent damage to the hammer or pile and to insure uniform driving performance.  Hammer cushions shall be made of durable, manufactured materials, provided in accordance with the hammer manufacturer's guidelines except that wood, wire rope, and asbestos hammer cushions shall not be used.  The hammer cushion shall be inspected in the presence of the Engineer when beginning pile driving or after each 100 hours of pile driving, whichever is less.  Any reduction of hammer cushion thickness exceeding 25 percent of the original thickness shall be replaced by the Contractor before driving is permitted to continue.

The compressive stresses as indicated by the wave equation during pile driving shall not exceed 90 percent of the pile yield stress.

Thirty calendar days prior to driving the first pile, the Contractor shall submit pile driving equipment information on the "Pile Driving Equipment Data Form" provided by the Engineer.  Approval of the pile driving equipment will be based on the wave equation analysis.  In addition, as part of this approval, the Contractor will be provided a "Pile Bearing Chart".  This chart will show blow counts and hammer strokes at required bearing capacity when a pile is at or near the desirable tip elevation.

During pile driving, the Contractor shall use the approved driving system.  No variations in the driving system will be permitted without the Engineer's written approval.  Any change in the driving system will only be considered after the Contractor has submitted a revised "Pile Driving Equipment Data Form" for a revised wave equation analysis by the Engineer, and the analysis indicates an acceptable result.  The Contractor will be notified of the acceptance or rejection of the revised driving system within seven calendar days of the Engineer's receipt of the requested change.  The time required for submission, review, and approval of a revised driving system shall not constitute the basis for a contract time extension to the Contractor.

All piling which do not reach required bearing capacity at desirable tip elevation at the time of driving will be subject to confirmation by restrike.  At least one pile shall be evaluated by restrike.  The piles shall set for a minimum of seven days after completion of driving to the specified tip elevation, prior to restrike.

The restrike procedure shall be as follows:

1.	Air or steam hammers.  The pile to be restruck shall be driven at least 6 inches at the normal operating pressure.  For a single-acting hammer, there shall be a full upward stroke of the ram.  For a double-acting hammer, the number of blows per minute during the driving shall be that for which the hammer is rated, unless otherwise directed by the Engineer.

2.	Diesel hammers.  The pile to be restruck shall be  driven at least 6 inches, unless otherwise directed by the Engineer.

505-3.14  Painting Steel Piles and Steel Pile Shells.  Add the following:  At least the top 40 feet of abutment piles and at least the top 20 feet of pier piles of the Old Glenn Overcrossing shall be galvanized in accordance with the requirements of AASHTO M 111.

505-3.15  Welding.  Add the following subsection:

All welding and inspection shall conform to the requirements of the latest edition of the American Welding Society (AWS) Structural Welding Code, D1.1.

1.	Qualification of Process, Procedures and Joint Details.  For each joint to be used in construction, the joint details, electrode classification or grade, electrode diameter, voltage, amperage, order and relative position of passes, number and thickness of layers and other pertinent information shall be clearly presented in the welding procedure(s) submitting by the Contractor for the approval of the Engineer.

Requirement for procedures qualification is waived if the Contractor's welding procedure is in accordance with all requirements of the welding procedures specification contained within the AWS Structural Welding Code, D1.1.

2.	Welders, Certification and Testing.  All welders and welding operators shall be certified in conformance with the AWS Structural Welding Code, D1.1.  Welders or welding operators lacking current AWS Structural Welding Code, D1.1, certification will not be permitted to perform welding on this project.

3.	Inspection of Shop Work and Records.  Welds including joint preparation, fit-up and alignment will be completely (100 percent of the weld) inspected visually and radiographed in conformance with AWS Structural Welding Code, D1.1.  Ten percent of the length, as determined by the Engineer, of each weld will be radiographic tested.  If a rejectable defect is found, then 100 percent of the length of the weld in that piece will be radiographically tested.

The Engineer will examine and approve satisfactory welds, disapprove or reject unsatisfactory welds, approve satisfactory methods proposed by the Contractor for repairing disapproved welds, and inspect the preparation and rewelding of disapproved welds.  Copies of all the welding fabrication documentation, including the weld testing results, will be forwarded to the Engineer.

4.	Obligation of Contractor.  It shall be the Contractor's responsibility to comply with all requests of the Engineer to correct improper workmanship and to remove and replace, or correct as instructed, all welds found defective or deficient by visual inspection or by nondestructive testing.

5.	Visual Inspection.  All welds shall be completely visually inspected.  A weld shall be acceptable by visual inspection if it shows that:

a.	the weld has no cracks,

b.	thorough fusion exists between adjacent layers of weld metal and between weld metal and base metal,

c.	all craters are filled to the full cross section, and,

d.	the completed weld conforms to all of the provisions of the AWS Structural Welding Code, D1.1.

6.	Nondestructive Testing.  The method of nondestructive testing will be radiographic testing in conformance with AWS Structural Welding Code, D1.1.  Field welds are not subject to nondestructive testing.

7.	Destructive Testing.  The location, method and extent of mandatory destructive testing to be performed (if any) will be indicated on the contract drawings.  All other welds will normally be inspected by visual methods and nondestructive testing;  however, the Engineer may require destructive testing of any weld that in his opinion does not meet the criteria for radiographic acceptance.

The cost associated with destructive testing of questionable welds will be borne by the Department for welds meeting radiographic acceptance criteria and by the Contractor for welds not meeting radiographic acceptance criteria.  The cost of destructive testing of welds designated for destructive testing on the contract drawings will be borne by the Contractor.

The Contractor is responsible for removing any weld specimen for destructive testing and repairing the weld afterwards.

8.	Preparation of the Weld.  The edges of the parts to be joined by welding shall be prepared by accurately cutting, grinding or machining to shape as indicated on the contract drawings and will be visually inspected prior to welding by the Engineer.

9.	Backing.  Backing rings or strips shall be utilized on all field butt welded joints welded from one side unless otherwise shown on the contract drawings or approved by the Engineer.  Open root joints are permissible where the joint is inaccessible from both sides.

10.	Cleaning.  Each completed bead shall be thoroughly cleaned of all slag, or other foreign matter, before proceeding with the next bead.  Hand clipping, power driven wire brushed, needle scalers, or grinders shall be used.

Full compensation for welding, weld inspection, weld testing, including all necessary tools, equipment, scaffolding and other support facilities required to perform welding, welding inspection, including the cost of radiographic testing will be subsidiary to the price bid for the piling items of the contract and no separate payment will be made.

(2/19/92)R146

505-4.01  Method of Measurement.  Delete numbered paragraph 6. and substitute the following:

6.	Piles not achieving the specified capacity within 5 feet of the desirable tip elevation shown on the plans shall be driven to a penetration established by the Engineer.  Requirement to drive piles deeper than the specified tip elevation shown on the plans shall be at the written direction of the Engineer.  For depths up to 20 feet beyond the desirable tip elevation, the contract bid price for piling will be applied.  For depths beyond 20 feet, the pile unit costs will be determined per Section 109.

SECTION 507

BRIDGE RAILING

Special Provisions

507-2.01  Materials.  Delete in its entirety and substitute the following:

1.	Steel.  Metal pipe handrailing on the bridge rail shall conform to the requirements of Section 722, Bridge Railing.

2.	Concrete.  Concrete for cast-in-place concrete railings shall be Class A concrete and shall conform to the applicable requirements of Section 501.  The surface finish of the railings shall conform to the requirements of a rubbed finish, or an architectural finish, as shown on the plans or specified under subsection 501-3.05, Forms.

3.	Reinforcing Steel.  Reinforcing steel shall conform to the requirements of Section 503 and shall be epoxy coated.

507-3.01  Construction Requirements.  Add the following:

1.	Concrete.  Casting of the concrete rail shall conform to the requirements of Section 501, Structural Concrete.

2.	Reinforcing Steel.  Reinforcing steel shall conform to the requirements of Section 503, Reinforcing Steel.

Standard Modifications

507-4.01  Method of Measurement.  Add the following:  It shall also include concrete and associated reinforcing steel included or partially contained within the limits of the concrete rail section.  (5/12/89)M19

Special Provisions

507-4.01  Method of Measurement.  Delete in its entirety and substitute the following:  The number of linear feet paid for Concrete Bridge Railing will be determined from the plan dimensions.

507-5.01  Basis of Payment.  Add the following:  Payment for Concrete Bridge Railing will be full compensation for furnishing all labor, materials, and equipment required to construct the bridge rail.  This will include the bridge rail concrete, reinforcing steel, structural tubing, utility conduits, and will include reinforcing steel embedded in the slab and extending into the railings.

Payment for concrete bridge rail transitions and all types of concrete bridge railing will be made under Item 507(4), Concrete Bridge Railing.

SECTION 508

MEMBRANE WATERPROOFING

Special Provisions

Delete this Section in its entirety and substitute the following:

508-1.01  Description.  This work consists of furnishing and installing membrane waterproofing on concrete bridge decks in conformance with the plans.  The membrane shall cover the entire top deck surface, from beginning to end of the bridge.

508-2.01  Membrane Waterproofing Material.  Membranes for bridge deck waterproofing shall be a manufactured type membrane as specified herein.

Membrane shall consist of a single or multiple component elastomeric material and shall be a product listed on the Department's Approved Products List, or an approved equal, and shall comply with the following requirements:

1.	The laydown temperature of the asphalt mix shall be a minimum of 250 degrees Fahrenheit.  Laydown temperature is defined as the temperature of the asphalt mix behind the paver screed.

2.	If a tack coat is recommended by the supplier, a STE-1 or other approved tack coat shall be used.

3.	The manufacturer shall certify that the waterproof membrane will develop a proper bond with a minimum asphalt mix laydown temperature of 250 degrees Fahrenheit.

508-2.02  Overlay Materials.  Materials requirements for pavement overlays on waterproof membranes shall conform to those specified in Section 401.

508-3.01  Application of Membrane Waterproofing.

1.	General.  Membrane waterproofing shall be installed in a manner to assure the following results:

a.	A complete bond between the membrane and the concrete surface of deck and curb face.

b.	An unbroken waterproof membrane in place between the concrete deck surface and the asphalt overlay.

c.	A complete bond between the membrane and the asphalt overlay.

2.	Preparation of Concrete Deck.  All concrete surfaces to receive membranes shall have cured at least 18 days prior to application of the membrane, except grout in keyways between precast members shall have cured at least 11 days prior to application of the membrane.

The entire deck shall be free of all foreign materials such as dirt, dust, moisture, loose concrete, etc.  Prior to applying the tack coat, primer or emulsion, all dust and loose material shall be removed from the deck by power sweeping followed by a thorough cleaning with compressed air.  Any sharp concrete edges on the deck surface which would puncture the membrane shall be corrected in a satisfactory manner prior to application of the membrane.  Grease, oil, paint, etc., shall be removed with solvents, detergents or sand blasting on decks that are to receive manufactured membranes.

Additional power sweeping, vacuuming, compressed air cleaning, or hand brooming shall be performed immediately before applying the tack coat, primer or emulsion if deemed necessary by the Engineer or manufacturer's representative.

3.	Weather and Moisture Limitations.  Membranes shall be applied in accordance with the manufacturers recommendations.

4.	Overlaying and Protection of Membrane.  The asphalt overlay shall be performed in accordance with the requirements of Subsection 401-3.11, Spreading and Finishing.

508-4.01  Method of Measurement.  Membrane waterproofing will not be measured for payment.

All materials for the asphalt overlay will be included in the measurements of quantities for the appropriate paving items.

No adjustments will be made in the quantities or prices of materials for asphalt overlay because of any variations resulting from utilizing waterproof membranes of greater or lesser thickness.

508-5.01  Basis of Payment.  Waterproof membrane will be paid for at the contract lump sum price.

Payment for the asphalt overlay will be made under the appropriate paving items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

508(1)	Membrane Waterproofing	Lump Sum

(5/12/93)R172

Add the following Section:

SECTION 510

STEEL BIN RETAINING WALLS

Special Provisions

510-1.01 Description.  This item shall consist of furnishing and installing steel bin walls in reasonably close conformity with the lines, grades, and dimensions shown on the plans or as established by the Engineer.

General design criteria for the bin wall structure, such as location and elevations shall be as shown on the plans.  Design details for the wall shall conform to one of the following manufactured systems or an approved equivalent:

1.	"Steelbin Retaining Wall", as manufactured by the Syro Steel Company.  For information concerning purchase and delivery of Steel Bin Wall materials, contact:

Syro Steel Company

P.O. Box 99

Centerville, Utah  84014

Phone:  (801) 292-4461

2.	"Bin-Type Retaining Wall, Type 1", as manufactured by the Contech Construction Products Company.  For information concerning purchase and delivery of Steel Bin Wall materials, contact:

Contech Construction Products Inc.

1409 - 140th Place N.E., Suite 101

Bellevue, Washington  98007

Phone:  (206) 641-3328

The Contractor shall make his own arrangements to purchase or manufacture all of the necessary components.

510-1.02 Submittals.  The Contractor shall submit complete working drawings for the wall system in accordance with the provisions in Subsection 105-1.02, Plans and Working Drawings.  The working drawings shall contain all information required for the proper construction of the wall system.  The Contractor shall allow the Engineer two weeks to review the drawings after a complete set has been received.

The Contractor shall submit a Manufacturer's Certificate of Compliance in accordance with the provisions in Subsection 106-1.05, Certificate of Compliance, for all materials to be placed under Item 510(5), Steel Bin Walls.  Submittals shall also include Manufacturer's installation instructions for the application shown on the plans.

510-2.01 Materials.  The steel bin walls shall consist of a series of rectangular cells composed of galvanized steel members.  They shall conform to the materials requirements of ASTM A444.  Fasteners for the bin walls shall conform to ASTM A307 and shall be galvanized in accordance with ASTM A153.

510-3.01 Construction Requirements.

1.	Design details.  The plans show type, location and details of the bin walls.

2.	Fabrication Requirements.  All bin members shall be fabricated so that members of the same nominal size shall be interchangeable.  Drilling, punching, or drifting bolt holes to correct defects in fabricating will not be permitted.  Any members twisted, bent, or with holes improperly located shall be replaced by the Contractor at his expense.

3.	Excavation and Backfill.  Excavation and backfill shall be performed in accordance with Section 205.

Temporary shoring will be required behind the bin walls to stabilize the backslope during erection of the bin walls.  The temporary shoring shall be installed as per the plans and in accordance with Section 505, Piling.

4.	Finishing.  The bin walls shall be treated and painted in accordance with Subsection 504-3.03, Painting.

510-4.01 Method of Measurement.  Steel bin walls will be measured for payment by the square foot.  The measurement will be along the outer face for the height from the bottom of the base plate to the top of the top stringer and for a length measured from end to end of each section of wall.

510-5.01 Basis of Payment.  The contract price paid per square foot for steel bin walls shall include full compensation for furnishing all labor, materials, tools, equipment and incidentals, and for doing all the work involved in construction of the bin walls, complete in place.

Temporary shoring and painting will not be paid for directly, but will be subsidiary to Item 510(5), Steel Bin Walls.

Excavation will be subsidiary.   Backfill will be paid under Item 203(6A), Borrow, Type A.

Add the following pay item:

Pay Item No.            Pay Item               Pay Unit

510 (5)           Steel Bin Walls           Square Foot

Add the following Section:

SECTION 511

MECHANICALLY STABILIZED

EMBANKMENT RETAINING WALLS

Special Provisions

511-1.01  Description.  This item consists of furnishing and constructing mechanically stabilized embankment retaining walls in accordance with the lines, grades, and dimensions shown on the plans or as established by the Engineer.  Design details for these mechanically stabilized embankment structures, such as specified reinforcing strip or wire mesh length, facia panel thickness, loading conditions, and details for appurtenances, shall be as recommended by the manufacturer on their approved shop drawings.  These walls shall be either "Panel Wall", "Reinforced Earth" or "Retained Earth."

1.	Panel Wall is a patented trademark of the Hilfiker Retaining Walls.  For information concerning purchase and delivery of Reinforced Soil Embankment materials, contact Mr. Harold K. Hilfiker at the following address:

Hilfiker Retaining Walls

P.O. Box 2012

Eureka, California  95502-2012

(707) 443-5093.

2.	Reinforced Earth is a patented trademark of the Reinforced Earth Company.  For information concerning purchase and delivery of Reinforced Earth materials, contact Mr. Bill Garcia, Construction Manager at the following address:

The Reinforced Earth Company

Western Region

3201 Danville Blvd., Suite 175

Alamo, CA  94507

(510) 831-8296

3.	Retained Earth is a patented trademark of the VSL Corporation.  For information concerning purchase and delivery of Retained Earth materials, contact Mr. Scott Thompson at the following address:

VSL Corporation

1077 Dell Avenue

Campbell, California  95008

(408) 866-5000, or

4208 198th Street S.W.

Lynnwood, Washington  98036

(206) 771-3088

The Contractor shall make his own arrangements to purchase or manufacture the facia panels, reinforcing strips or wire mesh, attachment devices, joint filler, and all other necessary components.

511-2.01  Materials.  Materials furnished for mechanically stabilized embankment retaining walls shall conform to these Special Provisions.  Materials not conforming to this Section or from sources not listed in these contract documents shall not be used without written consent of the Engineer.

1.	Concrete Facia Panels.  Concrete for facia panels shall meet the requirements of Class A Concrete set forth in subsection 501-1.02 Classification.  In addition, concrete shall have a minimum 28 day compressive strength of 4,000 psi.  Retarding or acceleration agents or any additive containing chloride shall not be used.  Reinforcing strips or wire mesh, connecting pins or devices, PVC pipe, and lifting devices shall be set in place to the dimensions and tolerances shown on the plans prior to casting.

a.	Testing and Inspection.  Acceptability of the precast concrete facia panels will be determined on the basis of compressive strength tests and visual inspection.  The Engineer shall perform all necessary sampling and testing.  Notice of the fabricators address shall be given to the Engineer at least 30 days prior to start of work so that inspection arrangements can be made in accordance with subsection 106-1.01 Source of Supply and Quality Requirements.  Panels shall be considered acceptable for placement in the wall when 7 day strengths exceed 85 percent of the 28 day requirement.

b.	Casting.  The concrete facia panels shall be cast on a flat area, the front face of the panel at the bottom of the form, the back face at the upper part.  Reinforcing strips or wire mesh guides shall be set on the rear face, and shall not contact or be attached to the panel reinforcement steel.  The concrete in each panel shall be placed without interruption and shall be consolidated by the use of an approved vibrator, supplemented by such hand tamping as may be necessary to force the concrete into the corners of the forms and prevent the formation of stone pockets or cleavage planes.  Clear form oil of the same manufacture shall be used throughout the casting operations.

Special care shall be given to the coil loop inserts or imbeds.  All coil loop inserts must be attached to the alignment templates using the bolts provided with the forms.  The vertical and horizontal alignment of the inserts shall be +_-inch.  The holes inside the inserts must be 2-¼ inches deep in the finished panel and must be free of all concrete and debris, loose or otherwise.  No concrete or other debris shall be on the interior surfaces of the coil loop inserts in the finished panels.  Immediately after the alignment template is removed, duct tape or equivalent, shall be placed over the insert holes in order to prevent debris from entering the holes.  This duct tape shall not be removed except by the crew that is assembling the wall.  Care shall be taken to insure that the duct tape is not removed during shipping.

c.	Marking.  The date of manufacture, the production lot number, and the piece mark shall be clearly scribed on the back of each facia panel.

d.	Curing.  The facia panels shall be cured until the concrete develops the specified compressive strength.  They shall not be stripped from their forms until the concrete reaches a minimum compressive strength of 1,000 psi, or until they can be removed without damage to the panel.  Panels exhibiting hairline cracking will be rejected for use on the project.  The panels may be shipped after reaching a minimum compressive strength of 3,400 psi.  Any panel pour which does not reach specified strength within 28 days will be rejected.

e.	Concrete Finish.  The concrete surface of the facia panels shall use form liners having a split granite pattern.  The facia aggregate shall not significantly reduce the dimension of the panel lip, but be in addition to the minimum panel thickness.  The rear face shall have a uniform surface finish.  It shall be screeded to eliminate open pockets of aggregate and surface distortions in excess of ¼-inch.

The facia panels shall receive graffiti protection.  Graffiti protection shall be a two step system designed specifically for this use consisting of a single component clear acrylic base coat over which a clear urethane finish coat is applied.  This material is not a sealer or vapor barrier.  No appreciable discoloration will be allowed.  The Contractor should be aware that these materials require special precautions, and shall be applied by trained personnel.  All concrete surfaces shall have set at least 28 days before any coatings are used.  The base coat shall be applied with a roller or sprayer in accordance with the manufacturers recommendations.  After 72 hours, two coats of the finish coat shall be applied.  Appropriate masking may be required.

f.	Handling, Storage, and Shipping.  All concrete facia panels shall be handled, stored, and shipped in such a manner as to eliminate the dangers of chipping, discoloration, cracks, fractures, and excessive bending stresses.

g.	Tolerances.  All concrete facia panels shall be manufactured within the following tolerances:

1)	Panel Dimensions.  Position of panel connection devices shall be within 1-inch.  All other dimensions shall be within 3/16-inch.

2)	Panel Squareness.  Squareness as determined by the difference between the two diagonals, shall not exceed ½-inch.

3)	Panel Surface Finish.  Surface defects on smooth formed surfaces measured on a length of 5 feet shall not exceed _-inch.  Surface defects on the textured-finished surfaces measured over a length of 5 feet shall not exceed 5/16-inch.

Installation tolerances shall be in accordance with subsection 511-3.02 Wall Erection.

h.	Facia Panel Acceptance.  Acceptance of concrete facia panels with respect to compressive strength will be determined on the basis of production lots.  A production lot is defined as a group of panels that will be represented by a single compressive strength sample and will consist of either 40 panels or a single days production, whichever is less.

During the pouring of the panels, the Engineer will randomly sample the concrete in accordance with AASHTO T-141.  A single compressive strength sample, consisting of a minimum of 4 cylinders, will be selected from every production lot.  Compression tests shall be made on a standard 6 x 12-inch test specimen prepared in accordance with AASHTO T-23.  Compressive strength testing shall be conducted in accordance with AASHTO T-22, which will provide a compressive strength test result which will determine the compressive strength of the production lot.

If the Contractor wishes to remove forms or ship the panels prior to 28 days, a minimum of 2 additional cylinders will be cured in the same manner as the panels.  The average compressive strength of these cylinders will determine whether the forms can be removed or the panels shipped.

Acceptance of a production lot will be made if the compressive strength test result is equal to or greater than 5,000 psi.  If the compressive test result is less than 5,000 psi, then the acceptance of the production lot will be based on its meeting the following acceptance criteria in its entirety:

1)	90 percent of the compressive strength test results for the production lot shall exceed 5,200 psi.

2)	The average of any 6 consecutive compressive strength test results shall exceed 5,300 psi.

3)	No individual compressive strength test result shall fall below 4,500 psi.

i.	Rejection.  All concrete facia panels of a production lot shall be subject to rejection because of failure to meet any of the requirements specified above.   In addition, any of the following defects shall be sufficient cause for individual panel rejection.

1)	Defects that indicate imperfect molding, honeycombing or open texture concrete.

2)	Dunnage marks on front facia of panel.

3)	Chipping of the edge lip during handling or placing.

4)	Cracks or chips visible by eye at a distance of 10-feet.

5)	Significant color variation on front facia of panels.

All concrete facia panels shall be cast to the shapes, with the appropriate piece mark, as shown on the plans.  Alignment changes in the wall shall be accomplished with prefabricated corner panels.  Bevel panels or field cuts that result in a single vertical line will not be allowed.  The Contractor shall also ensure against reverse casting prior to shipping.

2.	Galvanized Steel Reinforcing Strips or Wire Mesh.  The steel reinforcing strips or wire mesh shall be galvanized after fabrication with a minimum of 2-ounces per square foot of surface area in accordance with AASHTO M-111 or ASTM A-123.  Any damage done to the galvanizing prior to installation shall be repaired in an acceptable manner and provide a galvanized coating comparable to that provided by ASTM A-123.

Reinforcing strips shall be shop fabricated of hot rolled steel conforming to the required shape and dimensions, and meeting the minimum requirements of ASTM A-572, Grade 65 or equivalent.

The reinforcing wire mesh shall meet the requirements of ASTM A-82 for cold drawn wire and shall be welded into the finished mesh fabric in accordance with ASTM A-185.  Wire size and mesh configuration shall be as shown on drawings.

Reinforcing strips or wire mesh shall be cut to lengths and tolerances shown on the plans.  Holes for bolts shall be punched at the locations shown.  They shall be carefully inspected to insure they are true to size and free from defects that may impair their strength and durability.

3.	Fasteners.  Those applicable fasteners necessary for the chosen reinforcing system shall be supplied by the Contractor.

a.	Nuts and Bolts.  Bolts shall be a high strength hexagonal cap screws with matching nuts conforming to ASTM A-325 or equivalent, and galvanized in accordance with AASHTO M-164.  Nominal size shall be 1-¼ inch by ½ inch with a ¾-inch thread length.

b.	Coil Loop Inserts or Embeds.  The 4-½ inch by 1-inch coil loop insert shall be fabricated of cold drawn steel wire conforming to AISI C-1035.  It shall be galvanized in accordance with ASTM A-164, or approved equal.

c.	Coil Loop Bolt.  The 1-inch coil loop shall have 2 inches of thread.  It shall be cast of 80-55-06 ductile iron conforming to ASTM A-536.  Galvanizing shall conform to ASTM A-164, or approved equal.

d.	Grease.  The cavity of each coil loop insert shall be greased with no-oxid type grease or equal.

e.	Alignment Pins.  The pins used to align the panels during construction shall be at least _-inch diameter, round, mild steel bars galvanized per ASTM A-123.

4.	Joint Filler.  The following materials will be utilized between the panels.  No grout will be permitted at any time due to settlement requirements.

a.	Filler for vertical joints between panels shall be flexible open cell polyether foam strips, Grade UU-34, 2 by 2 inches as manufactured by North Carolina Foam Industries; Grade P-1232 as manufactured by Firestone Tire and Rubber Company, Cory Foam Division, Miland, Tennessee; or Grade 1334 as manufactured by California Corporation of America, Santa Anna, California.

b.	Filler for horizontal and diagonal joints between panels shall be resinbonded cork filler conforming to AASHTO M-153 and/or ASTM D-1752 (Type II).

5.	Concrete Leveling Footing.  Concrete shall conform to the requirements for Class A Concrete as described in subsection 501-1.02 Classification.  The cast-in-place footing may be unreinforced.

6.	Backfill.  Backfill for mechanically stabilized embankment retaining walls shall conform to requirements for selected material, Type A, as set forth in subsection 703-2.07 Selected Material.  It

shall have a minimum in-place density of 130 pcf and shall conform to the following criteria for backfill corrosion testing:

Resistivity                      > 3000 ohm-cm

PH            ASTM D-1243        5.0 to 10.0

Chlorides     ASTM D-512B        less than 200 PPM

Sulfates      ASTM D-516B        less than 1000 PPM

Sulphides     Standard Methods   less than 3000 PPM

15th Edition,

Method 427C

Samples will be prepared for backfill corrosion testing by extracting pore water using the methods described in "Methods of Soil Analysis, Part II, Chemical and Microbiological Properties," Chapters 10-2 to 10-4.  The Contractor shall submit samples for approval at least 30 days prior to construction of the wall.

7.	Wall Coping.  The cast-in-place top wall coping shall be Class A Concrete meeting the requirements of Section 501.

CONSTRUCTION REQUIREMENTS

511-3.01  Wall Excavation.  Excavation shall be in accordance with the requirements of Section 205 Excavation for Structures, and in reasonably close conformity to the lines and grades shown on the plans.

511-3.02  Foundation Preparation.  The foundation for the structure shall be graded level for a width equal to the length of reinforcing elements plus 12-inches or as shown on the plans.  Prior to wall construction, except where constructed on rock, the foundation shall be compacted to 95 percent of the maximum density in accordance with Subsection 203-3.04, Construction of Embankment with Moisture and Density Controls.  Any foundation soils found to be unsuitable shall be removed and replaced with selected material, Type A.

At each panel foundation level, a cast-in-place unreinforced concrete leveling footing shall be provided.  The footing shall be cured in accordance with the manufacturer's recommendations.

511-3.03  Wall Erection.  The concrete facia panels shall be placed vertically with the aid of a light crane.  For erection, panels shall be handled by means of a

lifting device set into the upper edge of the panels.  Panels shall be placed in successive horizontal lifts in the sequence shown on the plans as embankment placement proceeds.  As backfill material is placed behind a panel, the panels shall be maintained in vertical position by means of temporary wooden wedges placed in the joint at the junction of the two adjacent panels on the external side of the wall.  External bracing may also be required.

Initial set-up batter of all panels shall be 1/4-inch per foot into the embankment.  The maximum allowable gap in any panel joint shall be 3/4-inch.  The overall vertical tolerance of the wall (plumbness from top to bottom) shall not exceed 3/4-inch per 10-feet of wall height.  Failure to insure these tolerances after compaction of the backfill will require removal and replacement until the correct tolerance is met.

511-3.04  Reinforced Backfill Placement.  Backfill placement shall closely follow erection of each course of facia panels.  Backfill shall be placed in such a manner as to avoid any damage or disturbance of the wall materials or misalignment of the panels.  Any wall materials which become damaged during backfill placement shall be removed and replaced at the Contractors expense.  Any misalignment or distortion of the panels due to placement of backfill outside the limits of this specification shall be corrected.

At each reinforcing strip or wire mesh level, the fill should be roughly leveled before placing and bolting the strips or mesh.  As shown on the plans, the reinforcing elements shall be placed normal to the face of the wall.  No dissimilar metals shall be in contact within the reinforcing system.  Special care shall be used when utilities are placed concurrently with the strips or mesh.

Backfill shall be placed in approximately 2 equal lifts for each reinforcing element level, and closely following panel erection.  The Contractor shall decrease this lift thickness if necessary to obtain the specified density.  Compaction shall be accomplished without disturbance or distortion of reinforcing strips or wire mesh and panels.  Compaction of the 3-foot wide section adjacent to the backside of the wall shall be achieved using lightweight mechanical tampers.

The moisture content of the backfill material prior to and during compaction shall be uniform throughout each layer.  Backfill materials shall have a placement moisture content less than or equal to the optimum moisture content.  Backfill material with a placement moisture content in excess of the optimum moisture content shall be removed and reworked until the moisture content is acceptable throughout the entire lift.

At the end of each days operation, the Contractor shall slope the last lift of backfill away from the wall panels to direct away runoff.  In addition, he shall not allow surface runoff from adjacent areas to enter the wall construction site.

511-3.05  Wall Coping Construction.  At the Contractors option, the wall coping may be cast-in-place in a single or two step operation.

511-3.06  Manufacturers Representative.  The Contractor shall provide a representative of the manufacturer on site during the wall erection and embankment placement who is knowledgeable with the process and who will direct the Contractors operation to insure an acceptable product.  The representative shall be approved by the Engineer.  The representative shall submit a resume demonstrating that he has successfully directed the construction of at least 5 similar walls within the last 5 years.  The names and phone numbers of each of the owners Project Engineers shall be included in the resume.

511-4.01  Method of Measurement.  Mechanically Stabilized Embankment Retaining Walls will be measured by the square foot along the face of the wall from top of footing to top of coping, in accordance with Section 109.

511-5.01 Basis of Payment.  Payment for Item 511(1), Mechanically Stabilized Embankment Retaining Walls, at the contract price per square foot shall be full compensation for all labor, equipment and materials required to construct the walls including excavation, concrete footing, facia panels, raised panel design, graffiti protection, reinforcing strips or mesh, wall coping, and all miscellaneous hardware, complete and in place.  Payment will not be made until the wall is completed and accepted.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

511(1)	Mechanically Stabilized	Square Foot

Embankment Retaining Wall

(10/1/91)R90

SECTION 602

STRUCTURAL PLATE PIPE

Special Provisions

602-1.01  Description.  Add the following:  This work shall also include all labor, equipment and materials to construct concrete thrust beams or steel ribs, provide waterproofing, and prepare bedding material as shown on the plans.

602-1.02  Testing.  Add the following subsection:  The manufacturer of the structural plate arch shall provide comprehensive live-load test data for one or more of its structures of equal or greater top radius at HS 20-44 plus 20 percent loading.  If the manufacturer has no previous live-load test data under the conditions described above, the Contractor, at his expense, shall perform such live load testing and monitoring of the structures within 30 days after paving over them.  Deflection under test conditions shall not exceed 0.75 inch and no discernable change in pavement grade or condition will be allowed.

602-2.01  Materials.  Delete this subsection in its entirety and substitute the following:  Materials shall conform to the following specifications:

Structural Plate & Hardware	AASHTO M167

Waterproofing Seam Sealant	ArmCo 101, Kopper Bitumastic Super Service Black, Chevron Wet Plastic Cement, ATCO 1714 Plastic Fibre Seal or approved equal.

Structural Steel			ASTM A36

Class A Concrete			Section 501

Reinforcing Steel			ASTM A615

Bedding Material			AASHTO M43

Gradation #57 or #67

Selected Material, Type A	Subsection 703-2.07

Corrugated metal pipe, all steel components and welds shall be hot-dipped galvanized in accordance with AASHTO M 111.

Metal headwalls shall be constructed of steel.  The Contractor shall submit headwall shop drawings for approval 28 calendar days prior to beginning construction of the structural plate pipe.

Alternate Structures.  The Contractor may submit for approval alternate structural plate arch structures to those indicated.  Any such substitute, including modification to other portions of the structure necessary to accommodate the substituted pipe, shall be made at the expense of the Contractor and no adjustment in unit prices or pay quantities made.  All materials shall be designed in accordance with the latest version of AASHTO Standard Specification for Highway Bridges, Section 12.

602-3.01  Installation.  In the second sentence of the first paragraph, change "Section 204" to read "Section 205".

Add the following:  The Contractor shall submit a Construction Sequencing Plan and Traffic Control Plan for the installation of the structural plate arch at least 30 days prior to installation.  The Construction Sequencing Plan shall detail the method of maintaining the railroad clearance envelope during construction of the structural plate arch by bracing, guying or other means.

The Contractor shall coordinate with the Alaska Railroad Corporation (ARRC) in accordance with Section 617, Railroad Crossings, and shall install one 4-inch, schedule 40, PVC conduit on each side of the track the length of the structural plate arch.

A qualified representative of the structural plate arch manufacturer and any involved subcontractors shall be present at the preconstruction conference to discuss methods and responsibility for shape monitoring and control, backfill material testing and placement, and compaction methods and testing.  The structural plate arch manufacturer's recommendations and instructions shall be carefully followed during assembly.  Distortions shall be minimized and bolts shall be tightened symmetrically so that sweep and camber are kept to a minimum.  Seam sealant shall be installed in the seam laps in conformance with the manufacturer's instructions in order to achieve a relatively water-tight structure.

Except as otherwise provided, concrete work shall conform to Section 501, reinforcing steel work shall conform to Section 503, structural steel work shall conform to Section 504, welding shall conform to AWS D-1.1, and excavation, bedding and backfill shall be performed in accordance with the requirements of Section 205 and as required below.

602-3.02  Backfilling.  Add the following:  Backfilling shall progress evenly on each side of the arch in 8 inch maximum lifts extending 10 feet on both sides of the arch and compacted to 95 percent in accordance with Subsection 203-3.03, Construction of Embankments With Moisture and Density Control, except that no compaction equipment shall operate within 2 feet of the side plates.  The backfill in this zone shall meet the requirements of Selected Material, Type A and shall also be graded to pass the 3-inch sieve.  The Contractor shall monitor the structures during all backfilling and compacting operations to insure that no excessive distortions are occurring.  If, in the opinion of the Engineer, excessive distortions are likely to occur, the Contractor shall make adjustments to the backfilling operations as recommended by the arch manufacturer, and approved by the Engineer, so that distortions are minimized.

When the backfill reaches the elevation of the bottom of the concrete thrust beams, backfilling shall be halted and the thrust beams formed and cast.  In order to prevent distortions from the liquid concrete, placement of concrete shall be balanced on either side of the structure and the concrete shall be cast in layers of 10 inch maximum depth.  Forms may be removed and backfilling resumed after 72 hours following concrete placement.

When backfill outside the thrust beam reaches an elevation 2 feet above the top of the thrust beam, the top of the structures shall be covered with material deposited in 8 inch maximum lifts and compacted to 95 percent density with hand equipment or very light tractor equipment.  Until the overlay reaches a depth of at least 2 feet above the crown of the structures, large equipment shall not at any time be located closer to the structures than the outside edge of the thrust beam.  Until the fill above the structures is 2 feet thick, material shall be added and spread and compaction equipment operated perpendicular to the structure centerline.

No frozen materials shall be used in the backfill.

602-5.01  Basis of Payment.  Add the following:  Headwalls, structural steel, hardware, concrete thrust beams, 4-inch PVC conduit, excavation, bedding material and bracing or guying required to construct the arch will not be paid for directly, but will be subsidiary to Item 602(3), Structural Plate Arch, Span 30'-4", Rise 25'-10", Gage 1.

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-1.01  Description.  Add the following:  This work shall also consist of installing culvert marker posts.

603-2.01  Materials.  Add the following to the list of materials:

Corrugated Polyethylene Pipe            706-2.07

In the second paragraph, add "Corrugated Polyethylene Pipe (24 inch maximum diameter)" to the list of options allowed under Item 603(17).

Add the following to the last paragraph:  Heights of cover for corrugated polyethylene pipe shall be the same as for aluminum culvert pipe.  (5/7/91)S55

Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts.  The color shall be blue with no other markings.  The 3-¾ inch by 72 inch post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

603-3.04  Joining Pipe.  Add the following:  Polyethylene pipe couplings shall be corrugated to match the pipe corrugations and their width shall not be less than one half the nominal pipe diameter.  (5/7/91)S55

603-3.06  Culvert Marker Posts.  Add the following subsection:  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two inches of post shall remain above the ground after driving.

603-4.01  Method of Measurement.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01 Basis of Payment.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to the pipe item.  (10/1/91)R42

SECTION 606

GUARDRAIL

Special Provisions

606-1.01  Description.  Add the following:  This work shall also consist of installing breakaway cable terminals, guardrail/bridgerail connections, and controlled release terminals at the locations shown on the plans.

606-2.01  Materials.  Add the following:  Flexible markers shall have yellow reflective sheeting and be one of the following types or equivalent:

1.	"Guardrail Delineator Post" manufactured by Carsonite International, 2900 Lockheed Way, Carson City, Nevada 89701.

2.	"Guardrail Delineator" manufactured by Safe-Hit Corporation, 1930 West Winton Avenue, Building 11, Hayward, California 94545.

3.	"Flex-o-Guide", Model EY426 manufactured by Flexible Safety Zoning Company, 4152 Warren Avenue, Hillside, Illinois 60162.

606-3.01  Posts.  Add the following:  The foundation type for the breakaway cable terminal posts shall be the steel post embedment for soil or concrete as shown on Standard Drawing G-18.S.

606-3.02  Rail Elements.  Add the following:  Guardrail elements shall be factory bent for all radii less than 75 feet.

606-3.03  Removal and Reconstruction of Guardrail. Add the following:  Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

606-3.06  Flexible Markers.  Add the following subsection:  For each breakaway cable terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.  The flexible markers shall have a minimum of 21-inches of marker extending above the top of the guardrail.  The reflective tape shall face the nearest oncoming traffic.

606-3.08  Length of Need Verification.  Add the following subsection:  After shaping the slopes and staking all proposed guard rail locations, the Contractor shall notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine that additional guard rail is necessary, and the Contractor shall comply without delay.

606-3.12  Guardrail/Bridgerail Connection.  Add the following subsection:  Guardrail/bridgerail connection shall be installed in accordance with the details on the plans and Standard Drawing G-29.

606-4.01  Method of Measurement.  Delete the third paragraph and replace with the following:  Breakaway Cable Terminals will be measured per each installation which will include anchor cable assembly, terminal posts, terminal end, flexible marker and all associated hardware.  Rail elements, standard posts, and blocking for Breakaway Cable Terminals will be measured as Beam Type Guardrail.

Add the following:  Controlled Release Terminal/Special End Anchors will be measured per each installation which consists of all materials from the terminal end to and including the breakaway cable terminal anchor cable assembly, terminal posts and associated hardware.

Guardrail/Bridgerail Connections will be measured per each installed in place.  Each guardrail/bridgerail connection will include a 12.5 foot section of thrie beam guardrail, thrie beam to standard w-beam transition, thrie beam transition bracket, posts and all associated hardware.

Standard Modifications

606-4.01  Method of Measurement.  Delete the last sentence of the first paragraph and substitute the following:  Double faced (and nested) installations will be measured by dividing the number of panels by two, before multiplying by the panel length.  Thrie beam transition pieces shall be measured by multiplying the number of panels by 6.25 feet and shall be paid for at the contract price for Thrie Beam Guardrail.  (5/12/89)

Special Provisions

606-5.01  Basis of Payment.  	Add the following pay items:

Pay Item No.              Pay Item              Pay Unit

606(8)           Breakaway Cable Terminal       Each

606(9)         Controlled Release Terminal	Each

606(12)            Guardrail/Bridgerail         Each

Connection

(2/14/92)R45

SECTION 607

FENCES

Special Provisions

607-1.01  Description.  Add the following:  This work shall also consist of constructing snow control fencing in accordance with the details and at the locations shown on the plans.  Fence posts and soil anchors shall be located to avoid guardrail posts.

607-2.01  Materials.  Add the following:

Tension rods (high strength)	ASTM A-572

Bolts (high strength)	ASTM A-325

Fiber Reinforced Polyethylene Straps shall be constructed of fiber reinforced polyethylene or polyvinylchloride (PVC) material to the colors and dimensions shown on the plans.

Soil anchors shall be of a type adequate to develop the strengths and to sustain the forces indicated on the plans.

All exposed hardware shall be galvanized.

607-2.02  Submittals.  Add the following subsection:  The Contractor shall submit for review and approval, within 30 days following award of the contract, a portfolio of equipment and materials which he proposes to use for the snow control fence.  The portfolio shall consist of a table of contents which includes each item's intended use(s) and the following:

1.	For materials on the Approved Products List:  a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

2.	For materials not on the Approved Products List:  catalog cuts that include the manufacturer's name, type of product, size, model number, specifications, and supplemented by other data as may be required, including manufacturer's maintenance and operations manuals, or sample articles.

The Department will not be liable for any material purchased, labor performed, equipment used, or delay to the work before all equipment and materials have been reviewed and approved.

607-3.01  Construction Requirements.  Add the following:  Soil anchors shall be installed at the angles indicated on the plans and in accordance with the manufacturer's recommended installation procedures.  The allowable horizontal and vertical angular tolerance shall be within 1 degree.

High strength bolts shall be tightened to a minimum of 40 ft-lbs.

Plastic straps shall be installed in accordance with the manufacturer's recommendations.   They shall be installed on the traffic side of the fence unless otherwise noted.

607-3.02  Soil Anchor Testing.  Add the following subsection:  For screw type anchors, the installation torque shall be recorded at one foot intervals for the final 3 feet of installation.  The proper shear pin value (500 ft lbs.) shall be used, if applicable.  The installation may be terminated only when both the minimum torque and minimum depth are achieved, however, care must be taken for anchors near the top of the CMP arch.  A consistent protrusion shall be maintained by excavating if necessary, but reversing or unscrewing anchors will not be permitted.

For planing type anchors, a load test shall be performed to the minimum forces shown on the plans.

607-5.01  Basis of Payment.  Add the following:  Item 607(21), Snow Control Fence will be paid by the linear foot for the completed installation.  No separate payment will be made for soil anchors, high strength tension rods and bolts, plastic straps, and all hardware.  These items will be subsidiary to Item 607(21), Snow Control Fence.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

607(21)	Snow Control Fence	Linear Foot

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01  Materials.  Add the following to the end of the first sentence of the fifth paragraph:  "and the Alaska Traffic Manual."

615-2.01  Materials.  Delete paragraphs 7 and 8 (the fourth and fifth paragraphs on page 315) and substitute the following:  Sign posts and bases shall be of the types specified.  Structural aspects of design and materials for sign supports shall comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals.

Concrete for steel-reinforced slip base and breakaway base foundations shall be Class A, conforming to the requirements of Section 501, Structural Concrete.  Concrete for other sign foundations may be Class W.

(5/7/91)S42

615-3.01  Construction Requirements.  Add the following to the sixth paragraph:  When existing signs are to be salvaged the existing sign foundations shall either be removed in their entirety, or they may be abandoned in place.  If they are abandoned, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than one foot below roadway subgrade or unimproved ground, whichever applies.  If located within the roadway structural section they shall be disposed of in a manner as approved by the Engineer.  All signs and posts at a single installation shall be considered as one unit.

Add the following after the sixth paragraph:  Salvaged sign panels shall be delivered to the State Maintenance Yard in Palmer.

Add the following:  The Contractor may encounter bedrock when excavating for sign foundations.

615-3.02  Sign Placement and Installation:  Add the following:  Existing signs shall not be removed without authorization from the Engineer.  They shall be kept in service until either the new signs have been installed, or they are no longer needed.  As the work progresses, if their locations do not conform to Standard Drawing S-05, they shall be reinstalled at locations approved by the Engineer.

Prior to mounting the sign panel, the Contractor shall mark the date of installation on the back of the sign.  Installation dates shall be written in the format of month/day/year, using black permanent marker, with numbers a minimum of 3 inches in height, so as to be readable from the roadside after installation.

615-4.01  Method of Measurement.  Add the following to the second paragraph: Concrete used for sign bases will be considered subsidiary to other work under this section and will not be measured for payment.

615-5.01   Basis of Payment.  Add the following:  Payment for keeping existing signs in service until they are not longer needed, or temporarily relocating existing signs, will not be paid for directly, but will be subsidiary to Item 643(1), Traffic Maintenance.

No payment will be made for rock excavation, if necessary, to install sign foundations.  This work will be subsidiary to Item 615(1), Standard Signs.

Payment for removal of existing sign post foundations, or work required to abandon them in place, shall be included in Item 615(7), Salvage Signs.

(2/14/92)R50

SECTION 617

RAILROAD CROSSINGS

Special Provisions

617-3.01  Construction Requirements.  Add the following to Item 1., General:

e.	Work on this project involving the Alaska Railroad Corporation (ARRC) will include the following:

(1)	Construction of a new structural plate arch (Bridge No. 1884) under the proposed Old Glenn Highway at approximate Sta. 147+00.

(2)	Relocation of a load center to provide power for the defect detector system at the new arch pipe.

(3)	Removal of structures and obstructions (signal foundations, bases, junction boxes) associated with the existing at-grade crossing of the Old Glenn Highway.

(4)	A 3-inch track raise from north of the new railroad tunnel to south of the existing at-grade crossing.

Due to the critical train scheduling, track closures between trains will probably average about two (2) hours, with one 3 to 4 hour closure probably possible once per 24-hour day.  Closures are at the discretion of the ARRC, through the Engineer, and all work affecting the railroad must fall within the time restraints set by the ARRC.  Track closures can be scheduled with the ARRC no more than 24 hours before the closure time, however the railroad will make every effort to allow more than 24 hours notice.

If the Contractor chooses to establish or operate a temporary crossing for his use, he shall obtain all required approvals and permits and bear all costs associated with the crossing.  All work shall be coordinated through the Engineer with the ARRC Chief Engineer.  The following coordination sequence of construction is required for the work described above.

General.  The ARRC will provide all railroad flag protection for the project.  Railroad flag protection is required for any work within 25 feet of the tracks or wherever required by ARRC Chief Engineer.

The Contractor shall provide all surveying within the crossing limits which includes, but is not limited to, setting top of rail elevations, and setting grade for earthwork and roadway surfacing.

Construct New Structural Plate Arch (Bridge No. 1884).  Construction of the new structural plate arch shall not begin unless the gates installed at the existing at-grade crossing are operational.

The Contractor shall brace or guy the structural plate arch during construction so that it will not move into the clearance envelope.

The Contractor shall install one 4-inch, Schedule 40, PVC conduit on each side of the track within the arch, as shown in the plans.

The Contractor is responsible for all traffic control and construction signing except for railroad flag protection and all railroad signals which are the responsibility of the ARRC.

Removal of Existing At-Grade Crossing.  The following work will be accomplished when construction of the new roadway and structural plate arch is complete and has been opened to vehicular traffic.

The ARRC will remove all signal-related hardware and appurtenances associated with the existing crossing.

The ARRC will remove the existing rubberized modular track crossing.

The ARRC will relocate the defect detector from the south side of the existing crossing to approximately ten feet inside the south end of the new structural plate arch.  The ARRC will install a detector controller at the south end of the arch.

The Contractor shall relocate the load center from the south side of the existing crossing to approximate Station 147+58, 80'RT.  This load center will serve the defect detector system addressed above.

The ARRC will install 2-inch rigid metal conduit and cable between load center and relocated detector controller.

The Contractor shall remove structures and obstructions associated with the existing crossing, to include concrete gate/signal bases, conduits and asphalt approaches to the crossing.  All salvaged materials will become the property of the Contractor.

The Contractor shall construct drainage ditches and berms adjacent on either side of the old crossing (as shown on the plans) to block access to the tracks and maintain positive drainage along the railroad embankment.

Track Grade Raise.  After the new grade-separated railroad crossing is complete and operational, and the existing at-grade crossing has been removed, the ARRC will replace ballast, rail and ties to complete the three-inch track grade raise between track stations 15+00 and 25+00 (approximately 500 feet north of the proposed structural plate arch to 333 feet south of the existing at-grade crossing of the Old Glenn Highway).  The ARRC will raise, line and tamp the track to design elevation and transition the track raise for the length required to match existing grade, as required.

The ARRC will relocate the defect detector from it's temporary location at the existing at-grade crossing to it's permanent location approximately ten (10) feet inside the south end of the new structural plate arch.

SECTION 618

SEEDING

Special Provisions

618-1.01  Description.  Delete this subsection and substitute the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded.  This work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01  Materials.  Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01  Soil Preparation.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be covered with topsoil in accordance with Section 620 and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as topsoil is placed on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach on the wetlands.

618-3.03  Application.  In the first sentence of subparagraph b., under numbered paragraph 1. Hydraulic Method, delete the following:  "Item 619(1),".

Add the following:  Seed, mulch and fertilizer shall be applied as follows per 1,000 square feet.  The mulch rate shown is a minimum, and may be increased in accordance with the manufacturers recommendations.  If

the hydraulic method for seed and mulch is used, it shall be made in one application.  All fertilizer shall be applied by the hydraulic method.

Application

Item			Ingredients	Rate per MSF

Seed Mix		Bering Hairgrass (Norcoast)	0.40 lb.

Red Fescue (Arctared)	0.30 lb.

Creeping Foxtail (Garrison)	0.10 lb.

Hard Fescue (Durar)	0.10 lb.

Annual Rye Grass (Lolium)	0.10 lb.

TOTAL =   1.00 lb.

Mulch	35.0 lb.

Fertilizer	20-20-10	12.0 lb.

The Contractor shall not remove the required tags from the seed bags.

618-4.01  Method of Measurement.  Delete the second paragraph and substitute the following:  Seeding by the pound will be the number of pounds of seed (dry measure) accepted in place.  The amount of fertilizer, mulch and water for application used in this work, including any required reseeding, will be subsidiary to this item and will not be measured separately for payment.

Delete the last paragraph.

618-5.01  Basis of Payment.  Add the following:  Fertilizer, mulch and water for application, including any required reseeding, will not be paid for directly, but will be subsidiary to seeding.

The work described under subsection 618-3.01 Soil Preparation will not be paid for directly but will be subsidiary to seeding.

Water required for the hydraulic method of application will not be paid for separately, but will be subsidiary to seeding.

(10/1/91)R52

SECTION 620

TOPSOIL

Special Provisions

620-2.01  Materials.  Add the following:   Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

620-4.01  Method of Measurement.  Add the following:  Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(10/1/91)R53

SECTION 630

GEOTEXTILE FOR

EMBANKMENT SEPARATION AND

REINFORCEMENT

Special Provisions

Delete this Section in its entirety and substitute the following:

630-1.01  Description.  Prepare surfaces and furnish and place geotextiles for embankment separation as shown on the plans or as directed.

630-2.01  Materials.  Geotextile material and thread used in joining geotextiles by sewing shall conform to Section 729, Geotextiles.

630-3.01  Construction.

1.	Surface Preparation.  Prepare surface by removal of stumps, boulders and other sharp objects, and dewatering any areas as necessary.  Fill holes and large ruts with material as shown on the plans or as approved.  Material used to fill ruts and holes will be paid for at the unit price for the class of material used.  Removal of stumps, boulders, sharp objects and dewatering, if necessary, will be considered subsidiary to this item.

2.	Fabric Laying.  Unroll geotextile directly onto the prepared surface.  Stretch fabric to remove any creases or wrinkles.  Keep fabric taut during placement and spreading of cover material.

Lay fabric for embankment separation parallel to the direction of the material spread.  When laid on horizontal curves, it shall be placed in segment lengths not exceeding those listed in Table 630-1, with butt ends cut to match and sewn or overlapped.  When laid on tangents, the fabric shall be straightened and butt ends sewn or overlapped.

TABLE 630-1

GEOTEXTILE PLACEMENT ON CURVES

| Degree of Curve | Maximum Segment Length (feet) |
| --- | --- |
| 1 | 125 |
| 2 | 90 |
| 3 | 75 |
| 4 | 65 |
| 5 | 55 |
| 6 | 50 |

3.	Fabric Joining.

Join fabric by sewing or overlapping.  Bonding or other attachment methods may be used, subject to the approval of the Engineer.  If sewn, all seams shall be sewn by butterfly or J-seams and develop a minimum of 85 percent of the specified geotextile strength.  Seams shall be sewn with a double-thread chain-lock stitch.  The seam shall be 1-½ inches (+¼ inch) from the outside edge of the fabric.  If seams are to be overlapped, adjacent sections of fabric shall be overlapped a minimum of three feet unless otherwise shown on the plans.

4.	Material Placing and Spreading.

During placing and spreading, a minimum depth of 1-foot shall be maintained at all times between the fabric and the wheels or tracks of the construction equipment.  Spread the material in the direction of the fabric overlap.  Maintain a proper overlap and fabric continuity.  If sewn or bonded seams are used, place the cover material and spread in only one direction for the entire length of the geotextile.  On weak subgrades, spread the cover material simultaneously with dumping to minimize the potential of a localized subgrade failure.

Construction equipment shall not make sudden stops, starts, or turns on the cover material.  Use a smooth drum roller to achieve the specified density.

5.	Geosynthetic Repair.  If fabric used for separation should be torn for any reason, the cover material shall be cleaned from the torn area and it shall be repaired as follows:

Overlay with fabric with a minimum three foot overlap around the edges of the torn area.  The patch shall remain in place when material is placed over the affected area.

6.	Shipping and Handling.  Protect geotextiles from direct sunlight, ultraviolet rays, temperatures greater than 140 degrees F, moisture, and contamination from mud, dirt, dust, and debris.  Label or tag each roll to provide product identification.  Geotextiles will be rejected if at the time cover material is placed they have been removed from protective wrapping for more than five days, or if they have detrimental defects or damage which  cannot be repaired in the field.

630-4.01  Method of Measurement.  Geotextile will be measured in final position by the square yard, determined by multiplying plan neat line width by the measured length parallel to installation centerline along the ground surface, for installations acceptably completed.  No allowance will be made for overlap, whether at joints or patches.  No payment will be made for geotextile placed beyond the limits shown on the plans unless placed at the prior, written direction of the Engineer.

630-5.01  Basis of Payment.  Payment will be made at the contract unit price per square yard.  This price shall be full compensation for furnishing all materials, surface preparation, dewatering, delivering and laying the fabric and for all labor, equipment, tools and incidentals necessary to complete this item.

Payment will be made under:

Pay Item No.			Pay Item	Pay Unit

630(1)        Geotextile, Separation 	Square Yard

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01  Description.  Add the following:  This item shall also consist of the work involved in the excavation, forming, shaping and construction of public approaches.

639-2.01  Method of Measurement.  Add the following:  Public approaches will be measured per each constructed as shown on the plans, or as directed.

639-3.01  Basis of Payment.  Add the following:  Payment for public approach will be full compensation for furnishing all equipment and labor necessary to complete the work as indicated.  Materials required to construct driveways will be paid for separately under the respective items listed in the bid schedule.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

639(3)	Public Approach	Each

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-2.01  Method of Measurement.  Delete item 3. and substitute the following:

3.	When the letter of project completion has been issued and the Contractor has made all the required submittals the remaining balance of the amount for this item will be paid.  (5/7/91)S41

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01  Description.  This work shall consist of planning, providing, and maintaining control of erosion, water pollution, and hazardous materials contamination.

This work shall also include installation of silt fence and repair of silt fence as shown on the plans or as directed by the Engineer.

641-1.02  Submittals.  Five days prior to the preconstruction conference, the Contractor shall submit for acceptance a plan for accomplishment of temporary and permanent erosion and pollution control measures throughout the life of the contract.  This plan shall, as a minimum, include the following:

1.	Notice of Intent (NOI) to utilize the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska.

2.	Stormwater Pollution Prevention Plan (SPPP).

3.	Hazardous Material Control Plan (HMCP).

The NOI and SPPP shall be prepared in accordance with the requirements of the NPDES General Permit for Alaska (General Permit) and the Contractor Guidance for Preparing and Executing Storm Water Pollution Preventions Plans (Storm Water Manual).  When completing the NOI, the Contractor is the "Operator, Discharger, and Permittee" and the Department is the "Owner".

The HMCP is the Contractor's plan for the containment, cleanup, and disposal of waste material, as well as petroleum products or other hazardous substances generated by construction equipment or activities.  A list of quantities and types of equipment and materials available on site to be used for hazardous substance containment and cleanup shall be included.

The Contractor shall mail the NOI to the U.S. Environmental Protection Agency via Certified Mail, and shall send copies to the Engineer and the Alaska Department of Environmental Conservation Stormwater Coordinator.  Earth disturbing work shall not begin until 48 hours after the NOI has been postmarked.

The Contractor shall submit required amendments to the NOI or SWPPP to the Engineer at least 14 days prior to performing work affected by such amendments.

The Contractor shall submit a Notice of Termination (NOT) in accordance with the General Permit to the Engineer following completion of the final stabilization of the project.

641-1.04  Materials.  The silt fence filtration material shall meet the requirements of Subsection 729-2.04, Sediment Control.

The silt fence support framework shall be finished 4 x 4-inch wood, 3-inch diameter wood, #6 rebar with PVC sleeves, iron pipe, or other posts capable of supporting the installation, as approved by the Engineer.

The mesh support shall be WWF 6x6 W1xW1 or as approved by the Engineer.

641-2.01 Construction Requirements.  The Contractor shall comply with all requirements of the NPDES General Permit for Alaska.  The Contractor shall provide the Engineer with a copy of all inspection reports required by the Permit within three days of the inspection date.  Compliance with the NPDES General Permit for Alaska does not reduce the Engineer's authority to direct additional erosion control measures deemed appropriate.

The Contractor shall be responsible for the containment, cleanup, and disposal of all construction related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water.  Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of subsection 107-1.11, Protection and Restoration of Property and Landscape.  Additional silt fencing may be required at other sites as directed by the Engineer.

Removal of silt fence shall be accomplished in accordance with subsection 202-2.01, General Construction Requirements.

641-3.01  Method of Measurement.  Erosion and Pollution Control Administration will not be measured for payment.

Erosion and Pollution Control will be measured in the manner specified in the order authorizing the work.

Silt fence and repair of silt fence will be measured by the linear foot along the top of the fence.

641-4.01  Basis of Payment.  Item 641(1), Erosion and Pollution Control Administration will be full compensation for administration of erosion control, including preparing and amending plans, inspecting, monitoring, reporting, and record keeping.

Item 641(2), Erosion and Pollution Control will be full compensation for providing all required labor, equipment, and materials.

Failure to comply with the requirements of the NPDES General Permit for Alaska within 24 hours notice by the Engineer will result in withholding an amount equal to five percent of the total amount earned from all subsequent progress payments.  This retainage will be released by the Engineer upon satisfactory completion of the requirements of the  General Permit.

Payment for Item 641(3) Silt Fence, will be full compensation for all labor, equipment and materials required to furnish, install, and maintain the silt fence in accordance with these specifications.  Payment for Item 641(4) Repair of Silt Fence, will be full compensation for all labor, equipment and materials required to repair silt fence as directed by the Engineer.  Removal of silt fence will be paid under Item 202(29) Removal of Silt Fence.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution	Lump Sum

Control Administration

641(2)	Erosion and Pollution	Contingent Sum

Control

641(3)	Silt Fence	Linear Foot

641(4)	Repair of Silt Fence	Linear Foot

(2/2/93)R59g

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  Description.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix B.

642-3.01  Construction Requirements.  Add the following after item 11.:

12.	The Contractor's survey crews shall comply with approved traffic control plans.  Crews shall coordinate their activities with the project's Worksite Traffic Supervisor.

642-4.01  Method of Measurement.  Add the following:  Pay Item 642(2), Three Person Survey Party, shall be used only for extra, additional, or unanticipated work made necessary by changes in the project as directed by written order of the Engineer.  The quantities shown on the Bid Schedule for this item are for bidding purposes only, and the actual quantity in the field may vary as directed.  It is not intended to cover survey costs due to minor overruns (10 percent or less) in items which require staking of individual installations, including but not limited to culverts, guardrail, approaches, signs and drainage structures.

642-5.01  Basis of Payment.  Add the following:  If additional work as stated above is performed by a two person survey party, hours paid for under Item 642(2) Three Person Survey Party will be 75 percent of the hours worked.  If additional work as stated above is performed by only one person, hours paid for under Item 642(2) Three Person Survey Party will be 32 percent of the hours worked.  (10/1/91)R60

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  Traffic Control Plan.  Delete the first sentence of the first paragraph and substitute the following:  A Traffic Control Plan (TCP) is a drawing or drawings indicating the method or scheme for safely and efficiently routing of pedestrian and/or vehicular traffic during construction. (See Section 101-1.68)

Delete the second paragraph and substitute the following:  TCP's are required for each work site.  TCP's included in the plans are acceptable for use with the concurrence of the Engineer.  The Contractor may elect to modify them or design alternative TCP's.  All modified and/or alternative TCP's shall be submitted for approval of the Engineer.  The Contractor shall allow three weeks for review of any submitted TCP or one week for each subsequent correction.  Changes in the TCP resulting from unforeseen circumstances may be allowed during construction, provided a minimum of 48 hours are allowed for review, and the changes are approved by the Engineer.

Add the following to the third paragraph:  All TCPs submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

Add the following to the fourth paragraph:  Plan sheets developed on AutoCad can be made available, upon request, for use in preparing TCP's.

643-1.03  Worksite Traffic Supervisor.  Delete the second sentence of the first paragraph and substitute the following:  The Worksite Traffic Supervisor shall meet the following minimum requirements:

1.	Be currently certified as a Worksite Traffic Supervisor by the American Traffic Safety Services Association (ATSSA), or,

2.	Be currently certified as a Work Zone Traffic Safety Specialist or a Signs and Lines Specialist by the International Municipal Signal Association (IMSA), or,

3.	Be currently certified as a Worksite Traffic Technician by ATSSA, or,

4.	Have successfully passed the Design and Operation of Work Zone Traffic course sponsored by the Federal Highway Administration (FHWA).

If the individual is certified under Items 2, 3 or 4 above, the Contractor shall submit documentation that the individual has also obtained:

1.	A minimum of one year of supervisory level work in worksite traffic control, or,

2.	One year of having been in responsible charge of such work.  The term "in responsible charge" shall be construed to mean having been in a position of accountability for the selection of devices and for their placement in the traffic control system, or for the continued operation of the system.  Having persons that actually perform the labor under one's control would satisfy this requirement.

643-1.04 Construction Phasing Plan.  Revise the first sentence to read as follows:  A Construction Phasing Plan shall be submitted at least five working days prior to the preconstruction conference for approval by the Engineer and shall consist of the following:  (5/7/91)S57

643-2.01  Materials.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8 feet.

Delete numbered paragraph 8. in its entirety and substitute the following:

8.	Work Zone Pavement Markings.  Work zone pavement markings shall be either paint conforming to subsection 708-2.03 with glass beads conforming to subsection 712-2.08, preformed marking tape (removable or non-removable) conforming to subsection 712-2.14, or temporary raised pavement markers conforming to subsection 712-2.15 or 712-2.16, as appropriate.  The markings shall be applied in accordance with Section 670, Traffic Markings, and the manufacturer's recommendations.

Add the following:

12.	Portable Changeable Message Boards.  Portable changeable message boards shall be truck or trailer mounted with a self-contained power supply and shall have the following features:

a.	Message sign panel size of 5'-8" by 7'-5", minimum, with a capacity for a three line message.

b.	Eight character display per message line.

c.	Message modules containing at least 36 different preprogrammed messages (three line displays) to be selected by the Engineer.

d.	The capacity to create, preview, and display new messages and message sequences.

e.	A waterproof, lockable cover for the controller keyboard.

f.	An operator's manual, a service manual, and wiring diagram.

g.	Quick release attachments on display panel cover.

h.	Variable flash and sequence rates.

i.	Manual and automatic dimming capability on lamp bulb matrix models.

j.	The ability to mount at least 7 feet above the pavement to the bottom of the message sign panel.

k.	The capacity to operate with a battery pack for 2 hours under full load.

643-3.02  Roadway Characteristics During Construction.  Add the following to the first paragraph:  The maximum spacing between channelizing devices in a taper should be approximately equal in feet to the posted speed limit in miles per hour.

643-3.03  Public Notice.  Add the following to the first paragraph:

Anchorage Chamber of Commerce

Palmer Chamber of Commerce

Wasilla Chamber of Commerce

Alaska Visitor's Association

Add the following:  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of commencing construction, resuming construction after seasonal suspension, or any scheduled delay, or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure.  The advertisements shall be published in the following newspapers:

1.	Anchorage Daily News

2.	Chugiak-Eagle River Star

3.	Frontiersman

The Contractor shall indicate on the ad order a first preference for the local news section and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a 24-hour "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.  Advertisements shall be promptly cancelled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

A change order is not required for newspaper advertisements, the Notice to Proceed shall constitute the notice required to initiate newspaper advertisements.  (12/8/92)R167

643-3.04  Traffic Control Devices.  Change the reference from "Annual Average Daily Traffic (AADT)" to read "Average Daily Traffic (ADT)" under Item 1., Embankments.

Delete the first paragraph under Item 1. Embankments, and substitute the following:  For roadways with a current Average Daily Traffic (ADT) greater than 4000 a portable concrete barrier shall be installed when either a two foot excavation or a fill area with a slope steeper than 3:1 will exist within a specified distance from the edge of traveled way for more than 12 consecutive hours.  The specified distance shall be 16 feet for excavation areas and 28 feet for fill areas.  The portable concrete barrier shall have a minimum clearance of two feet from the work area and/or hinge point to allow for deflection if struck.

Add the following to Item 1., Embankments:  Barrier reflectors shall be mounted on the face of barrier adjacent to traffic on 50-foot centers and shall be a minimum height of 18 inches above the surface of the roadway.

Delete numbered paragraph 4., Work Zone Pavement Markings in its entirety.

Under item 5., Flagging, add the following after the first sentence of the first paragraph:  Each flagger shall be illuminated from the front to a level of light intensity not less than one foot candle during hours of darkness.

Under item 5., Flagging, add the following:  Flaggers shall wear reflective clothing with markings on arms, legs and head.  Flaggers directing traffic through intersections shall wear orange gloves and orange helmets as approved by the Engineer.  Gloves and helmets shall not be faded or dirty such that their effectiveness as traffic control devices is impacted as determined by the Engineer.

Add the following:

9.	Portable Changeable Message Boards.  These boards shall be used to notify the travelling public of the upcoming work as deemed necessary by the Engineer.  Based on the TCP contained in the plans, a maximum of three boards are required for this project.

643-3.05  Authority of the Engineer.  Add the following:  The Contractor will be assessed a charge of $50 per hour for each hour after the specified time allowed that any work remains uncompleted.  This amount of these deductions is to cover estimated expenses incurred by the Department as a result of the Contractor's failure to complete the work within the time specified.

643-3.06  Traffic Price Adjustment.  Add the following:  A change order is not required for traffic price adjustment, the Notice to Proceed shall constitute the notice required to initiate traffic price adjustment.  (12/8/92)R168

643-3.07  Maintenance of Traffic During Suspension of Work.  Delete the first sentence and substitute the following:  The Contractor shall schedule a preliminary meeting with the Engineer and Maintenance and Operations to take place approximately one month prior to seasonal suspension of work, or no later than September 15.  This meeting shall be to outline the work the Contractor expects to complete before shutdown and the condition the roadway is to be in.  There shall be no areas with concrete barriers located on both sides of the roadway. A winter shutdown traffic control plan shall be submitted to the Engineer at this preliminary meeting.

643-3.08  Construction Sequencing.  Delete this subsection in its entirety and substitute the following:  A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes or shoulders or their respective widths, stops traffic, or causes the 85th percentile speed to fall more than 10 mph below the posted speed limit.  An approved Traffic Control Plan is required before any restriction to traffic is implemented.  No restrictions to traffic will be allowed during the times listed below:

1.	Monday through Thursday from 6:00 AM to 7:30 AM and from 4:00 PM to 7:00 PM.

2.	Friday from 6:00 AM to 7:30 AM and from 4:00 PM to 10:00 PM.

3.	Saturday and Sunday from 6:00 AM to 10:00 PM.

4.	Around any holiday as described below (in addition to times listed in items 1. through 3., above):

a.	If a holiday falls on Monday, from 6:00 AM to 10:00 PM on the day of the holiday.

b.	If a holiday falls on Tuesday, from 6:00 AM to 10:00 PM on the day before the holiday and the day of the holiday.

c.	If a holiday falls on Wednesday or Friday, from 4:30 PM to 10:00 PM on the day before the holiday and from 6:00 AM to 10:00 PM on the day of the holiday.

d.	If a holiday falls on Thursday, from 4:30 PM to 10:00 PM on the day before the holiday, and from 6:00 AM to 10:00 PM on the day of the holiday and the day after the holiday.

5.	During the Alaska State Fair:

a.	Monday through Thursday from 6:00 AM to 8:00 AM and from 4:30 PM to 11:00 PM.

b.	Friday from 6:00 AM to 8:00 AM and from 4:30 PM to 12:00 midnight.

c.	Saturday and Sunday from 6:00 AM to 12:00 midnight.

6.	During seasonal suspension of work.

Construction sequencing shown on the plans is a suggestion only and is not intended to prevent the Contractor from utilizing his ingenuity to arrive at alternate construction sequencing.

643-3.09  Temporary Pavement Markings.  Add the following subsection:  Permanent or Temporary Pavement Markings in accordance with this subsection, approved traffic control plans, and Parts III and VI of the Alaska Traffic Manual shall be in place before existing paved roadways, temporary paved roadways and detours, interim paving lifts, and roadways with seal coats and surface treatments are opened to traffic for longer than one continuous work shift.  This work may include restriping of the existing roadway prior to beginning construction of the project.

Conflicting pavement markings shall be removed in accordance with subsection 670-3.04, Paint Removal.  Construction shall be staged so that no traffic is routed over conflicting markings.

Sections of existing roadway that will be opened to traffic during the winter shall be marked at the same location as the existing lines and markings unless shown otherwise on the plans, an approved traffic control plan, or as directed by the Engineer.

The Contractor shall maintain all Temporary Pavement Markings for their intended life without additional compensation for any reapplication that may be required.  There will be no compensation to upgrade Temporary Pavement Markings for short term operations to those required for long term operations.

Only temporary raised pavement markers or removable preformed retroreflective marking tape shall be used as Temporary Pavement Markings on the final pavement surface.  They shall be completely removed and disposed of in conjunction with the placement of the final markings.  The complete removal shall include any residual adhesive that might misguide motorists.  Final pavement markings on finished pavement surfaces and long term pavement markings on other asphalt surfaces shall be in place before work is suspended for the winter.

Temporary Pavement Markings may not be required for construction activities that will be completed within one continuous work shift if the roadway is adequately delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.  The Engineer will determine the need for Temporary Pavement Markings for these conditions.

1.	Long Term Operations.  Temporary Pavement Markings to be in place for more than 2 weeks shall consist of full markings as if a permanent condition.

2.	Short Term Operations.  Temporary Pavement Markings to be in place for less than 2 weeks shall be in accordance with Parts III and VI of the Alaska Traffic Manual with the following exceptions:

a.  Passing Zones.  Broken line pavement markings shall conform to Tables 643-1 or 643-2.  This  applies to both white lane lines for traffic moving in the same direction and yellow center lines for two or three lane two-way roadways when it is safe to pass.

TABLE 643-1*

|  | LENGTH OF MARKINGS |  | SKIP SPACING |  |
| --- | --- | --- | --- | --- |
| Marking Material | Normal Curvature | ** Severe Curvature | Normal Curvature | ** Severe Curvature |
| Removable Preformed Marking Tape | 4 feet | 2 feet | 36 feet | 18 feet |
| Temporary Raised Pavement Markings | 3 units 3 feet on center | 2 units 2 feet on center | 34 feet | 18 feet |

TABLE 643-2*

|  | LENGTH OF MARKINGS |  | SKIP SPACING |  |
| --- | --- | --- | --- | --- |
| Marking Material | Normal Curvature | ** Severe Curvature | Normal Curvature | ** Severe Curvature |
| Removable Preformed Marking Tape | 2 feet | 1 foot | 38 feet | 19 feet |
| Temporary Raised Pavement Markings | 1 unit 40 feet on center | 1 unit 20 feet on center | ____ | ____ |

* No passing markings and signing required per 643-3.09.2.b.

** Severe Curvature:  When the degree of curvature is 5 or greater or when it is necessary for motorists to reduce their speed at least 15 miles per hour below the 85th percentile speed.

b.  No Passing Zones.  No passing zones, as detailed in Section 3B-3 to 3B-5 of the Alaska Traffic Manual, shall be identified as follows:

Sections of asphalt concrete pavement roadways with an ADT of 2000 vehicles per day or greater, shall have broken centerline markings conforming to Table 643-1, and no-passing markings consisting of a continuous 4-inch strip of removable preformed marking tape or temporary raised pavement markers placed on 5-foot centers in the no passing direction.  If a no passing condition exists for both directions of traffic, both directions shall be marked with the two 4-inch stripes of removable preformed marking tape separated by approximately 3 inches, or two temporary raised pavement markers placed approximately 3 inches apart on 5 foot centers and the broken centerline markings are not required.

Sections of asphalt concrete pavement roadways with an Average Daily Traffic (ADT) of less than 2000 vehicles per day, and seal coat and surface treatment pavements shall be marked with temporary pavement markings conforming to Table 643-2 and shall be identified with R4-1, (DO NOT PASS) and R4-2, (PASS WITH CARE) signs.  The signs shall be supplemented with two 18-inch by 18-inch, minimum size, fluorescent red-orange flags mounted above the signs.  The signs shall be mounted so that the bottom of the sign is at least 5 feet above the adjacent roadway.

c.  Other Markings.  It will not be necessary to install arrows, legend, stop lines, crosswalks, or right edge line markings.  Railroad crossing markings are required for areas that have sight restrictions or high accident experience.  Left edge lines will not be required unless they will be the only markings on the paved surface, such as ramps.  All other types of markings are required.  These include channelizing lines and gore area outlines.

d.  Short Term Markings on Seal Coats and Surface Treatments.  Only temporary raised pavement markers conforming to Subsection 712-2.16 shall be used for short-term markings on seal coat and surface treatment pavements.  The markers shall be installed prior to the application of the asphalt surface material and cover coat.

On multicourse surface treatments the temporary raised pavement markers shall be installed following the full width application of the first layer of cover coat.  The markers shall be installed on each day's completed surface before the pilot car operations are removed and unescorted traffic is allowed on the surface treatment in accordance with Table 643-2.

If the temporary raised pavement markers cannot be adequately secured to the first course of the cover coat material with the marker's flexible bituminous adhesive, the Contractor shall secure them to the surface with two nails and washers, of the appropriate length and area, so the nails do not pull through the foot of the marker.

After application of the asphalt and cover coat material, the vinyl protective cover shall be removed to expose the retroreflective surfaces of the marker.  Temporary markers shall be installed so that the foot of the marker unit is facing the direction of the approaching distributor.

Final pavement markings shall not be placed until the seal coat or surface treatment has been opened to traffic for at least 14 days.  Final pavement markings shall be applied within 10 days of the completion of the final sweeping or brooming of the mainline seal coat or surface treatment.  Seal coat and surface treatment pavements are exempt from the two week requirement stated in short-term operations.

643-4.01  Method of Measurement.  Add the following to item 1.:  Newspaper advertisements will not be included in measurement for Traffic Maintenance.

Delete the second sentence of the first paragraph under item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this contract.  Permanent Construction Signing will not be measured for payment, but will include all permanent construction signs, as detailed on the plans, that are installed, accepted and maintained during the life of this contract.

Add the following to Item 2:  Type II Barricades will be measured and paid for under Item 643(8), Drums.

Delete numbered paragraph 6. in its entirety and substitute the following:

6.	Temporary Pavement Markings will be measured by the single stripe station.  A single stripe is a marking or a temporary raised pavement marker four inches in width.  Wider striping will be measured as multiples of four inches.  Centerline gaps will not be deducted from measurements.  Installation of any word and symbol markings as well as the removal of the Temporary Pavement Markings will not be measured separately but will be subsidiary to this item.  The No-Passing Zone signing, as described in Subsection 643-3.09, 2., b., will not be measured separately but will be subsidiary to this item.

Delete paragraph 7., Seasonal Pavement Markings in its entirety.

Add the following:  Item 643(25) Portable Changeable Message Board will be measured by the calendar day for each sign used as approved by the Engineer.

Newspaper advertisements will not be measured for payment.

Providing a "hot-line road report" telephone with pre-recorded message will not be measured for payment but will be subsidiary to Item 643(1), Traffic Maintenance.

643-5.01  Basis of Payment.  In the second paragraph, delete Item 1., Seasonal Pavement Markings.

In the fourth paragraph, delete Pay Item 643(14) Seasonal Pavement Markings.

Standard Modifications

643-5.01 Basis of Payment.  Change the pay unit for item 643(3), Permanent Construction Signing, from "Calendar Day" to "Lump Sum."  (5/7/91)M40

Special Provisions

643-5.01 Basis of Payment.  Change the pay unit for item 643(11), Portable Concrete Barrier, from "Each" to "Linear Foot".

Add the following:	Barrier reflectors will not be paid for directly, but will be subsidiary to Pay Item 643(11), Portable Concrete Barrier.

Payment for Item 643(25) Portable Changeable Message Board will be full compensation for all labor, equipment, and materials to provide, move, maintain, program, and operate a portable message board signs on the project.

Payment for Item 643(29), Newspaper Advertisements will be made at cost plus 15 percent.  Payment will be authorized upon evidence of payment to the newspaper (paid receipt).

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

643(25)	Portable Changeable Message	Calendar

Board	Day

643(29)	Newspaper Advertisements	Contingent

Sum

(2/14/92)R62 R102 R111

SECTION 644

SERVICES TO BE FURNISHED BY THE

CONTRACTOR

Special Provisions

644-2.01  Field Office.  Delete this subsection in its entirety and substitute the following:  The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work through 30 days after issuance of the notice of project completion.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 150 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power.

4.	A minimum of 250 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 15 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

10.	Located within ten miles on the Anchorage side of the project.

644-2.02  Field Laboratory.  Delete the sixth sentence of the first paragraph and substitute the following:  The water supply shall consist of a 500-gallon capacity tank with a pressure pump or a commercial pressurized system.

Delete the second paragraph and substitute the following:  The laboratory shall include a concrete slab, 8 feet by 10 feet by 4 inches thick, suitable for mounting a Gilson shaker and other equipment.  The slab shall be installed within an enclosed adjacent structure having a door, a window, a worktable, an exhaust fan, and adequate lighting and heat.

Add the following:  The Contractor shall supply 240 volt, 60 cycle power, a 100 lb. propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

644-2.06  Scales.  Delete the second paragraph and substitute the following:  Sanitary lavatory facilities, heating, adequate electrical lighting and 120 volt, 60 cycle power shall be furnished to the scale house.

Delete paragraph three in its entirety.

Delete the fourth paragraph and substitute the following:  Furnishing platform scales, tickets, scale house, and electronic weigh system will not be paid for directly, but will be subsidiary to Item 203(6A) Borrow, Type A.  Platform scales, scale house and the electronic weigh system shall remain the property of the Contractor upon completion of the work.

Delete the second sentence of the last paragraph and substitute the following:  Platform scales shall be equipped with weatherproof housing and shall be constructed in a manner that protects the recording equipment and allows the scale operator convenient access to the scale computer, ticket printer, and sequential transaction printer.  All components of the scale inside the scalehouse which could be physically manipulated in a manner which could tamper with weights shall be protected by an enclosure, acceptable to the Engineer, to preclude tampering with weighing operations.

Add the following:  The Contractor shall provide an electronic equipment weighing system with the following capabilities:

1.	Self reading scale system with a load cell, scale computer, ticket printer, sequential transaction printer, and the ability to record a complete shift's transaction on a 3.5 inch double sided diskette.  All individual parts of the system shall be compatible with each other and suitable for field conditions.  All supplies (weigh tickets, paper, printer ribbons, diskettes, etc), maintenance, and repair services necessary to keep the system functional, shall also be supplied by the Contractor and will not be measured or paid for directly but will be considered a subsidiary obligation.

Sufficient spare parts, components, etc., shall be available on the Project to keep the electronic equipment weighing system operational at all times.  Unless prior written authorization is obtained from the Engineer, no payment will be allowed for any material weighed without using the electronic equipment weighing system.

2.	The scale computer shall have the ability to store vehicle: identification numbers, tare weights, and maximum allowable "legal" weight (as determined by the Engineer) for all hauling vehicles utilized on the project on each day.  It shall have the ability to store multiple project numbers and multiple pay item descriptions for all projects and pay items which are weighed with the scale system.

3.	During weighing operations, the system shall compare each vehicle's gross weight to its maximum allowable legal weight.  If the vehicle is not exempted from legal weight requirements and exceeds its maximum allowable legal weight, the system shall alert the scale operator that an "overload" exists and present two alternatives;  cancel the weighing operation, or, override the indicator and issue a ticket.  A ticket shall not be issued unless the "overload indicator" is in error (i.e. the vehicle is exempted from overweight requirements).  When the override alternative is utilized the word "OVERLOAD ?" shall be inserted in the COMMENTS field.

The Contractor may haul up to 1000 pounds over the maximum allowable legal weight for a vehicle, without classifying it as an "overload", if the program inserts the maximum allowable net weight in the NET field and inserts the difference between the actual net weight and the maximum allowable net weight in the COMMENTS field (between 1 and 1000 pounds).  If the Contractor elects to exercise this option, no payment will be made for any material in excess of the maximum allowable legal weight.

No payment will be made for any material hauled in a vehicle which is not in conformance with the requirements of Subsection 105-1.12, Load Restrictions and this Subsection.  Non-conforming vehicles shall dump sufficient material so that they conform and then be reweighed.

4.	The system shall have a battery backup as well as protection for power surges or brown outs.  The system shall be capable of retaining all stored data during a power outage and shall be operable during a power outage for at least 30 minutes.

5.	The ticket printer furnished by the Contractor shall print a one part weigh ticket on continuous feed 9-1/2 inch by 4-1/4 inch 90 pound white index paper with removable 1/2 inch perforations on each side with the following information on each ticket in the order listed:

a.	Sequential ticket number (4 digits)

b.	Project information (20 digits)

c.	Date

d.	Pay Item name in words

e.	Hauling unit identification number

f.	Time of dispatch

g.	Name of scale operator

h.	Gross weight in pounds

i.	Tare weight in pounds

j.	Net weight in pounds

All of the above items are to be printed by the ticket printer and not pre-printed.  After printing, the weigh ticket shall be automatically advanced to a position where it can be torn off at a perforation.  During pay item weighing operations, the system shall function such that the scale operator shall only have to enter a one digit code for the project number, a one or two digit code for the pay item, and the hauling unit identification number.

The weigh ticket "number" consists of the following information:

a.	Project Number (1st 5 characters of PROJECT

field)

b.	Pit Number (Last 3 characters of PRODUCT field)

c.	Date

d.	Pay Item

e.	Sequential ticket number

The sequential weigh ticket number shall be set to "1" at the beginning of each day for each unique project number, pit number, and pay item combination.  The project information, date, pay item, hauling unit identification numbers and their maximum allowable legal weight, and the scale operator's name shall also be able to be set by the scale operator.  Tare weights shall only be able to be changed by a tare weighing operation.

6.	The sequential transaction printer shall print all scales transactions including tares and data that is changed by the scale operator, as soon as the transaction is concluded.  The sequential transaction printer shall allow for the paper to be manually advanced so that the scale operator can write notes on the paper when special situations occur such as voided tickets, incorrect hauling unit number used, etc.

7.	The double sided diskette shall record all ticket information which was produced during a shift or at selected times in the shift.  Transaction data for each weighing operation shall be recorded on the disk at the end of each weighing operation.  The data shall be stored in two files with the same information but different formats.  The first file shall be in dBASE IV format (IBM) and shall be useable by the program without any conversion or manipulation.  The naming convention for this file shall be "yymmdd.dbf".  The second file shall be a raw data file in ASCII format with fields separated by commas, character fields enclosed in double quotes, a carriage return at the end of each record, and an end of file mark following the last record.  The naming convention for this file shall be "yymmdd.csv".  If more than one scale is used on the project, a scale location designation acceptable to the Engineer shall be utilized for the 7th and 8th characters of the filename.

In the event both data files on the diskette are not completely useable to obtain all truck weighing data, or permission is obtained from the Engineer to weigh without the electronic system, the Contractor shall correct or reconstruct the data file utilizing the sequential transaction log or other information, as directed by the Engineer, as a data source.  No payment will be made for any hauled material on a given date until an accurate "daily" data file has been delivered to the Engineer.

8.	The fields for each record shall be in the following format and order.  Other data fields may also be provided but shall follow the fields in the required format.

| Field | Field Name | Type | Width |
| --- | --- | --- | --- |
| 1 | TKT | Character | 4 (right justified w/leading blanks) |
| 2 | DATE | Character | 8 (mm/dd/yy) |
| 3 | TIME | Character | 5 (hh:mm) (24 hour) |
| 4 | UNIT ID | Character | 10 (right justified w/leading blanks) |
| 5 | GROSS | Numeric | 6 (pounds) |
| 6 | TARE | Numeric | 6 (pounds) |
| 7 | NET | Numeric | 6 (pounds) |
| 8 | COMMENTS | Character | 20 |
| 9 | PRODUCT | Character | 20 |
| 10 | PROJECT | Character | 20 |
| 11 | NAME | Character | 18 |

9.	The system shall be able to generate a summary report, either during or at the end of the day, which summarizes the number of loads and total net weight for each Date, Project, and Product.

When checking for overloads is being utilized, the system shall be able to generate a report which lists all hauling identification numbers and their maximum allowable gross weight.

10.	A user instructional manual shall be available for each scale which explains the complete scale operation.  A copy of this manual shall be kept in each scalehouse and be available for review by the Engineer at all times.

11.	In the event that extra construction engineering expenses are incurred due to checking non-machine data entries or other data irregularities, an amount equal to the value of those expenses will be deducted from the value of the item.  A unilateral change order will be issued to make any adjustments the Engineer determines to be warranted.

(1/8/92)R145

644-4.01  Basis of Payment.  Add the following:  Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

(7/7/92)R63

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  Description.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01  Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.1, located in the "green pages" of this document.

645-3.01  General.  The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following:  contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02  Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03  Subcontracts.  In the event the Contractor subcontracts a portion  of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01  Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or,

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program for	Labor Hour

4 Trainees/Apprentices

(10/29/91)S16

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.01 Description.  Add the following.  Item 660(3), Highway Lighting System Complete, consists of salvaging and reinstalling existing electroliers, salvaging and delivering three existing electroliers to maintenance, making all tests, and furnishing and installing the following:  electroliers, pile foundations for all electroliers, conduit, junction boxes, conductors, and all miscellaneous materials to make the system operational.

660-1.05  Maintaining Existing and Temporary Electrical Systems.  Delete this subsection in its entirety and substitute the following:  The Contractor shall provide all work required to maintain, and reinstall when necessary, the existing lighting system.

They shall be kept in effective operation during the progress of the work, except when shutdown is permitted to allow for alterations or final removal of the systems.  Systems shall be considered in effective operation when there are no damaged, inoperative, or malfunctioning components, and they operate as designed.  The State will pay for all electricity required for the operation of the systems, if they are in effective operation and the public benefits from their operation.  Replacement equipment shall be compatible with existing equipment used in the Central Region.

Lighting standards and load centers shall be relocated or replaced whenever they are closer than 6-feet to the travelled way.

When the Contractor begins work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include repair or any damage prior to the date of the transfer of maintenance responsibility.  Therefore, before commencing work on the project, the Contractor should inventory the condition of the existing equipment and present written documentation of all damaged, inoperative, and malfunctioning electrical equipment.  This equipment shall be inspected jointly by the Engineer and the Contractor.  If the Contractor begins work before he provides the Engineer with an inventory, he waives the right to claim extra compensation when any component is later found to be damaged, inoperative, or malfunctioning.

At the Preconstruction Conference, the Contractor shall furnish the Engineer with the name and phone number of the person responsible for maintaining existing and temporary electrical facilities.  This person shall be available at all times until the date of Acceptance for Traffic and Maintenance and have access to all labor, materials, and equipment required to complete any repair.

The Contractor shall ascertain the location of existing conduit runs, buried cables, junction boxes, and all underground utilities before using equipment that may damage such facilities or interfere with any system.

Where roadways are to remain open to traffic and existing lighting systems are to be modified, the Contractor shall energize the modified circuit by sunset on the same day he retires the original circuit.

When no longer required, the Contractor shall salvage all original and Department provided equipment in accordance with the plans and subsection 660-6.07, Salvaging Electric Equipment, and remove all other materials used in the temporary systems from the project.

660-2.01  Excavating and Backfilling.  Change "Subsection 204-3.01" to "Section 204" in the third paragraph.

660-2.03  Foundations.  Delete the last two paragraphs of this subsection.

660-2.04  Poles, Steel Pedestals and Posts.  Add the following:  All poles and mastarms shall be designed for 100 MPH wind speeds with gusts to 130 MPH.

660-2.05  Conduit.  Add the following:  Trenching to install conduits across roadways with an existing paved surface will be allowed.

660-2.08  Conductors.  Delete the second paragraph under item 2., Power Conductors and Cables, and add the following:  Conductor insulation in cables consisting of three #8 AWG sized conductors shall be colored black, white, and red.  Conductor insulation in cables consisting of conductors larger than #8 AWG shall either be colored black, white, and red, or be black with printed numbers identifying each conductor per Insulated Cable Engineers Association (ICEA), method 4.

Standard Modifications

660-2.09(A)  Wiring.  In the seventh paragraph,  insert "and feeder" between "signal" and "conductors".  (5/7/91)M41

Special Provisions

660-2.10  Bonding and Grounding.  Add the following after the first paragraph:  The Contractor shall install a bare, number 8 AWG, solid copper conductor in all conduits as the grounding conductor.  The grounding conductors shall be attached to the conduits using insulated throat grounding bushings, leaving one foot of slack between each grounding bushing.

All hardware, including insulated throat grounding bushings, ground rods, and ground rod clamps shall be UL listed.  Grounding bushings shall be the threaded type.

Delete the fifth paragraph on page 441 and substitute the following:  Where conduit is installed as a spare or for future use, the aforementioned copper grounding conductor may be omitted.

Standard Modifications

660-4.01  Installation Details.  In numbered paragraphs 7 and 9, under "Loops", change "660-2.08" to read "660-2.09(A), Wiring".  (5/7/91)M42

660-5.02  Backplates.  In the last paragraph, change "660-2.16" to read "660-2.15, Painting".  (5/7/91)M43

Special Provisions

660-6.01  Luminaires.  Add the following:  No paint may be applied to the reflecting surface of luminaire reflectors.

Luminaires shall provide the specified uniformities or better in the configurations listed below.  Uniformity is defined as the average maintained illumination level divided by the maintained illumination at the dimmest point.  Uniformity shall be calculated using the manufacturers current published photometric charts.  Uncorrected illumination values shall be derived by straight line interpolation between lines of the isofootcandle curves.  Computations shall be done assuming luminaires are located on one side of the roadway only.

| Luminaire Type | MC-3 | MC-3 | Offset |
| --- | --- | --- | --- |
| Road Width | 24 ft | 34 ft | 36 ft |
| Mounting Height | 40 ft | 50 ft | 50 ft |
| Spacing | 170 ft | 220 ft | 260 ft |
| Offset | 0 ft | 0 ft | -28 ft |
| Luminaire Uniformity | 3.0 : 1 | 3.0 : 1 | 3.0 : 1 |
| Initial Footcandles | 1.2 | 1.3 | 1.2 |

Luminaire Type Definitions:

MC-3:	A cobra head style luminaire with a medium cutoff, type 3 distribution as defined by the Illuminating Engineering Society (I.E.S.).

Offset:	A floodlight type luminaire designed to be adjusted between 30 and 50 degrees from horizontal and be mounted on the top of a pole, which is offset back from the edge of travelled way.

660-6.07  Salvaging Electrical Equipment.  Add the following to the first paragraph:  All salvaged equipment shall be delivered to the State Maintenance Yard at 289 Inner Springer Loop in Palmer.

Delete the fourth paragraph and substitute the following: The following existing items not being reused shall become the property of the Contractor and be disposed of as indicated.  Items that are to be removed shall be removed from the highway right of way.

1.	Junction boxes (not including lids) and conductors  shall be removed.

2.	Conduits may be abandoned in place provided elbows and nipples that sweep the conduits into junction boxes are removed.  However, existing conduits encountered while trenching shall be removed to provide two radial feet of clearance between the old and new conduit.

3.	Electrolier foundations may be abandoned in place, provided the tops of the foundations, reinforcing steel, anchor bolts, and conduits are removed to a depth of not less than one foot below roadway subgrade, or unimproved ground, whichever applies.

660-7.01  Basis of Payment.  In the first paragraph, modify line eleven to read:  "....involved in furnishing and installing, modifying, maintaining and....".

(10/1/91)R65

In the second paragraph, delete the end of the last sentence after the word "allowed"

SECTION 661

ELECTRICAL LOAD CENTERS

Special Provisions

661-1.01  Description.  Add the following:  Item 661(6), Relocate Existing Load Center, consists of furnishing all labor, equipment and materials necessary to remove the existing load center cabinet and foundation, abandon the existing serving conductor and/or conduit in a manner satisfactory to the serving utility, reinstall the foundation and load center cabinet at the plan location, and connect it as shown on the plans.

661-3.01  Construction Requirements.  Add the following:  After the load center is relocated, the Contractor shall request and coordinate an electrical inspection of the load center from the local authority having jurisdiction, allowing at least 5 working days before the inspection is needed.  The Contractor shall be present during the inspection to assist in accessing the cabinets and to answer questions.  The Contractor shall correct the deficiencies noted in each load center.

Payment of any fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be incidental to the Section 661 items.  (9/1/89)

When the load center is ready to be energized, the Contractor shall notify Matanuska Electric Association (MEA) Palmer District Engineer, in writing, and shall allow MEA 14 calendar days to provide power to the load center.

The Contractor shall notify the serving utility before taking any existing load center out of service.

661-5.01  Basis of Payment.  Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

661(6)	Relocate Existing Load Center	Each

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDER STATIONS

Special Provisions

669-1.01 Description.  This work shall consist of furnishing and installing a three traffic count stations for the automated collection of traffic data on an intermittent or permanent basis.  Automated Traffic Recorder (ATR) stations are a vehicle detection systems.  Intermittent ATR stations consist of the following parts:

a.	inductive loops detectors for detecting the presence of vehicles, and

b.	underground conduit, junction boxes, cabinet, and wiring as specified on the plans.

The location of traffic detection and cabinets shown on the plans is approximate and the exact locations shall be established in the field by the Engineer.

General descriptions of the Automated Traffic Recorders in this project are as follows:

Assembly H4 is located on the Old Glenn Ramp 1

Assembly H7 is located on the Old Glenn Ramp 3

Assembly H8 is located on the Old Glenn Ramp 4

All three assemblies consist of a single loop intermittent ATR for automated vehicle volume counting.  The inductive loops for Assemblies H7 and H8 are terminated in the same cabinet.  No electrical or telephone service is required for these assemblies.  No traffic volume counters or other electronics for these assemblies is included in the project; in the future, Highway Data Section personnel will bring portable volume counters to the sites and connect to the loops as needed.

669-1.02  Regulation and Code.  All materials and workmanship shall conform to the standards of the Underwriters Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturers Association, where applicable.

669-2.01 Materials.  All materials provided for the work shall be new, unless otherwise stated, and shall meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with Subsection 660-2.09(A), Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable.

2.	Conduit.  All conduit shall be in accordance with Subsection 660-2.05, Conduit.  Nylon pull cords shall be left in all two inch conduit.

3.	Junction Boxes.  All junction boxes shall be in accordance with Subsection 660-2.06, Junction Boxes.  Junction boxes used for ATR installations shall not contain any conductors carrying a voltage greater than 50 volts.

4.	Terminal Blocks.  All terminal blocks shall be provided with nickel, silver or cadmium plated brass binder head screw terminals.  All terminal block which are installed in junction boxes shall be waterproof and resistant to corrosion.  Terminal blocks shall be a barrier type, 600vac @ 20 amps, capacity for 12-18 AWG wire with removable shorting bars in each positions and with integral type marking strips.  All conductors shall be terminated and labeled to a terminal block.

5.	Inductive Loops.  All inductive loops shall be in accordance with Subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be UL listed as Type RHW/USE/XLP 12AWG 600V rating.

Loop lead-in cable home run shall consist of a twisted pair 18AWG stranded tinned copper wire with polyethylene insulation, covered with an aluminum foil shield, stranded copper drain wire, and PE outer jacket conforming to IMSA specification 50-2.

Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, and aluminum shield, and overall PVC or PE outer jacket conforming to IMSA specification 50-2.

6.	Cabinets.  All style 1 cabinets shall be unpainted, brushed aluminum and have a NEMA 3R specification with fully gasketed full width access door.

669-3.01 Construction Requirements.

1.	Wiring.  All wiring shall be installed in accordance with Subsection 660-2.09(A), Wiring. All unused pairs shall be terminated within splices, at cabinets unused pairs shall be terminated to a terminal block and labeled "SPARE".

2.	Conduit.  All conduit shall be installed in accordance with Subsection 660-2.05, Conduit or as indicated on the plans.

3.	Junction Boxes.  All junction boxes shall be installed in  accordance with Subsection 660-2.06, Junction Boxes or as indicated on the plans.

4.	Terminal Blocks.  All terminal blocks and wire pairs shall be clearly labeled on the block.  Terminal blocks within cabinets shall be mounted so that all terminals are easily accessible from the front of the cabinet.  By convention, wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block. All conductors shall terminate and be soldered to "spade" type terminal lugs.

5.	Inductive Loops.  All inductive loops shall be installed and constructed in accordance with Subsection 660-4.01, Installation Details, unless otherwise specified on the plans.  All inductive loops shall be centered in the traffic lane between the striping.

Inductive loops for Assemblies H4 and H7 shall be formed of four turns of wire, and shall be six feet square with plus-or-minus one inch tolerance.  The inductive loop for Assembly H8 shall be 6 feet by 12 feet wide.

All lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the center line of the road.

6.	Cabinets.  All style 1 and 2 cabinets shall be installed as indicated on the plans.

7.	General Tests.  All ATR installations shall have tests conducted in accordance with Subsection 660-4.01, Installation Details.

669-3.05  Deliverables.  All deliverables shall be submitted to the Engineer prior to final approval of the work or as otherwise called for herein.

1.	Equipment List(s) and Drawings.  The Contractor shall submit for review and approval within thirty days following award of the contract, three collated copies of a portfolio of equipment and materials which he proposes to install.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s), and a description that includes product name, manufacturer, model or part number.

The Department will not be liable for any materials purchased, labor performed, equipment used or delay to the work before all equipment and materials have been reviewed and approved.

2.	As-Built Plans and Photographs.  The Contractor shall prepare four complete sets of as-built plans which will be kept current with the construction.  These as-built plans shall detail all  construction changes made to the plans and also include the following information on the appropriate sheets:

a.	the location and depth of all inductive loops and conduit runs, and,

b.	the station and offset of all junction boxes.

Redlines of full size construction plans will be acceptable.

Three sets of as-built plans shall be presented to the Engineer, and one set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation.

The Contractor shall present photographs and 35 mm film negatives documenting the installation of all inductive loops.  The photos shall show the loops in place prior to covering with gravel and asphalt pavement.  The photographs shall include at least one view of each loop showing the conduit to the nearest junction box, and at least two overall views of each ATR installation showing placement of the inductive loops in relationship to the cabinet.  The photographs shall be 5"x7" color prints, and shall be labeled with the identification of each loop as indicated on the plans.

3.	Test Results.  Written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Engineer prior to acceptance of the Automated Traffic Recorder installation.  Tests will be conducted in accordance with Subsection 660-4.01, Installation Details.

669-4.01  Method of Measurement.  Item 669(1), Automated Traffic Recorder will be measured by each recorder completed and accepted.

669-5.01  Basis of Payment.  Item 669(1), Automated Traffic Recorder will be full compensation for furnishing all equipment, labor and materials necessary to complete the work as specified, with the following exceptions:

1.	Backfill materials required will be paid for under their respective pay items.

2.	Asphalt required will be paid for under the respective asphalt pay item.

Excavation, as-built plans and acceptance testing required for these installations will not be paid for separately, but will be subsidiary to the Automated Traffic Recorder.

Payment will be made under:

Pay Item No.			Pay Item	Pay Unit

669(1)       Automated Traffic Recorder	Each

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01 Description.  Add the following:  This work shall also consist of removal of pavement markings at locations shown on the plans or as directed by the Engineer.

Standard Modifications

670-3.01  Construction Requirements.  In the last paragraph under Item 2., insert "pneumatic" immediately before "roller".  (5/12/89)

Special Provisions

670-3.04   Paint Removal.  Change the title of this subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following:  Pavement markings shall be removed to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement.  Painting over existing striping does not meet the requirement for removal.  Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-4.01 Method of Measurement.  Add the following after item 5:

6.	Station Basis.  Pavement markings to be paid for by the station will be measured by taking the difference in the beginning and ending stations of each marking, excluding gaps, and multiplying that by the marking's nominal width in inches divided by 4.  Measurement of transverse markings, letters, and arrows shall be made by taking the area of the marking's rectangular footprint and multiplying it by 0.03 (the number of 4 inch multiples in 1 foot divided by 100).

Delete the last paragraph and substitute the following:  Removal of pavement markings will be measured by the station for payment.

670-5.01 Basis of Payment.  Add the following:  Repair of any damaged pavement or surfacing caused by the pavement marking removal operation will be subsidiary to Item 670(9) Removal of Pavement Markings.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

670(9)	Removal of Pavement Markings	Station

(5/13/92)R142

SECTION 702

ASPHALT MATERIALS

Standard Modifications

702-2.04  Storage And Application Temperatures.  In Table 702-1, change storage temperatures for Acs from "340 Max" to "325 Max".  (5/12/89)M23

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  Fine Aggregate For Concrete.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

703-2.02  Coarse Aggregate For Concrete.  In the first sentence, insert ", class B," after "AASHTO M 80".

(5/12/89)M24

703-2.03 Aggregate for Base.  Add the following to the list under the first paragraph:

Plastic Index      AASHTO T-90        6 max

(5/7/91)M45

Special Provisions

703-2.03  Aggregate for Base.  Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading D-1 | Grading E-1 |
| --- | --- | --- |
| 1 inch | 100 | 100 |
| 3/4 inch | 70-100 | 70-95 |
| 3/8 inch | 50-79 | 60-86 |
| No. 4 | 35-58 | 40-65 |
| No. 8 | 20-47 | - |
| No. 30 | 10-26 | 15-30 |
| No. 50 | 6-19 | - |
| No. 200 | 0-6 | 8-13 |

(10/1/91)R117

Standard Modifications

703-2.04  Aggregate For Plant Mix Asphalt Pavement.  Delete this subsection in its entirety and substitute the following:

Coarse Aggregate.  Coarse aggregate (that material retained on the No. 4 Sieve) shall be crushed stone or crushed gravel and shall consist of sound, tough, durable rock of uniform quality.  All material shall be free from clay balls, vegetative matter or other deleterious matters.  Coarse aggregate shall not be coated with dirt

or other finely divided mineral matter.  In addition, coarse aggregate shall meet the following requirements:

Percent of Wear			AASHTO T 96	45 max.

Degradation Value			ATM T-13	30 min.

Percent Sodium Sulfate loss	AASHTO T 104	9 max.

(5 cycles)

Percent Fracture			ATM T-4	80 min.

single face

Thin-Elongated Pieces		ATM T-9	8 % max.

Fine Aggregate.  Fine aggregate (passing the No. 4 sieve) shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness Test.

Blended Aggregate.  The several aggregate fractions for the mixture shall be sized, graded, and combined in such proportions that the resulting composite blend conforms to the grading requirements of Table 703-3.  The fraction actually retained between any two consecutive sieves larger than the No. 100 shall be not less than 2 percent of the total.  Aggregate gradations shall be determined by ATM T-7.  The size of extracted samples for gradation shall be in corformance with AASHTO T 164.

TABLE 703-3

BROAD BAND GRADATIONS FOR ASPHALT

CONCRETE PAVEMENT AGGREGATE

Percent Passing by Weight

| Sieve Designation | Gradation Designation |  |  |
| --- | --- | --- | --- |
|  | Type I | Type II | Type III |
| 1 inch | 100 | - | - |
| 3/4 inch | 75-90 | 100 | - |
| 1/2 inch | 60-86 | 75-90 | 100 |
| 3/8 inch | 50-78 | 60-88 | 75-90 |
| No. 4 | 34-62 | 44-72 | 50-78 |
| No. 8 | 24-52 | 30-58 | 32-60 |
| No. 16 | 16-42 | 20-44 | 20-45 |
| No. 30 | 10-32 | 12-34 | 12-34 |
| No. 50 | 8-24 | 8-24 | 8-24 |
| No. 100 | 5-16 | 5-16 | 4-15 |
| No. 200 | 3-8 | 3-8 | 3-8 |

(7/16/93)M61

Special Provisions

703-2.07  Selected Material.  Add the following to Item 1., Selected Material, Type A:  It shall have 30 to 55 percent by weight of particles passing the No. 4 sieve.  (10/1/91)R89

THIS PAGE LEFT BLANK INTENTIONALLY

SECTION 705

JOINT MATERIALS

Standard Modifications

705-2.03  Bridge Seal.  Under Elastic Compression Seals, delete "Z1" in the line call-out specification.  (5/12/89)M25

SECTION 706

CONCRETE, CLAY, FIBER AND PLASTIC PIPE

Special Provisions

706-2.07  Corrugated Polyethylene Pipe.  Delete in its entirety and substitute the following:  Corrugated polyethylene pipe shall conform to the following:

Culverts and Stormdrains	AASHTO M 294

Type S (double wall)

Underdrains	AASHTO M 252

(5/7/91)S60

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.14  Preformed Pavement Markings.  Add the following to paragraph A. under Item 1., General Requirements:  The preformed ribbon shall consist of one solid piece of required width and length.  In solid stripe area, the tape length shall, where possible, be a minimum of 100 feet.

712-2.15  Temporary Raised Pavement Markers.  Add the following:  The temporary raised pavement markers shall be installed utilizing an approved raised pavement marker flexible bituminous adhesive.

The color of the raised pavement markers shall conform to the color of the marking for which they supplement, substitute, or serve as a positioning guide.

712-2.16  Temporary Raised Pavement Markers for Short-Term Operations, Seal Coats, and Surface Treatments.  Add the following subsection:  The marker shall consist of an L-shaped polyurethane body with retroreflective tape on the top vertical section and with a self-adhesive base.  Both faces of the yellow marker and one face of the white marker shall be reflectorized.  The marker body shall be made from 0.060 inch minimum thick polyurethane; the vertical leg shall be approximately 2 inches high by 4 inches wide and the base approximately 1-1/8 inches wide.  The polyurethane body shall conform to Table 712-1.

The adhesive shall be factory-applied to the marker base, and made of a pressure-sensitive material, a minimum 1/8 inch thick and 3/4 inch wide, with release paper.

Where chip seals, slurry seals or tack coats are to be utilized after placement of the temporary raised pavement markers, the markers shall come with a protective cover made of clear flexible polyvinyl chloride.

The reflective tape shall be metalized polycarbonate microprism retroreflective material with acrylic backing or equal, a minimum 0.25 inch wide by 4 inches long, and provide the minimum optical performance shown in Table 712-2, for an observation angle of 0.2 degrees.

TABLE 712-1

| PROPERTY | RESULT | ASTM TEST METHOD |
| --- | --- | --- |
| Specific Gravity (min.) | 1.19 | D 792 |
| Hardness | 80A | D 2240 |
| Tensile Strength (psi, min.) | 4600 | D 412 |
| Ultimate Elongation (percent, min.) | 330 | D 412 |
| Modulus at 300 percent (psi, min.) | 1000 | D 412 |
| Stiffness @ -20o F (psi, min.) @ +72o F (psi, min.) | 1700 900 | D 1053 D 1053 |
| Compression Set 22 hr. @ 70o C (percent, max.) | 65 | D 395 |
| Taber Abrasion CS17 wheel wt. loss (mg/1000 cycles) | 3 | --- |

TABLE 712-2

| Horizontal Entrance Angle | Specific Intensity* |  |
| --- | --- | --- |
|  | White | Yellow |
| 0 degrees | 3.5 | 3.0 |
| 30 degrees | 2.7 | 1.7 |

* Candelas per footcandle of illumination at the reflector on a plane perpendicular to the incident light.

(5/7/91)S61

SECTION 716

STRUCTURAL STEEL

Special Provisions

716-2.03  High Tensile Strength Bolts.  Add the following:  All high strength bolts, except A490 bolts, shall be galvanized.

Galvanized tension control bolts will be considered equivalent to the bolts specified.

Standard Modifications

716-2.03  High Tensile Strength Bolts.  Add the following:  All bolts, nuts, and washers are to be marked with a symbol identifying the manufacturer as required in ASTM A325 Section 14, A490 Section 15, A563 Section 10.7 and 10.8, A194 Section 14, and F436 Section 14.  The supplier shall provide the symbol and address of each manufacturer for all the bolts, nuts, and washers supplied to the project.

The supplier's certification shall provide a corresponding lot number appearing on the shipping package and the certification.  The supplier's certification shall note when and where all testing was done, including the rotational-capacity tests indicated below, and include zinc thickness when galvanized bolts and nuts are used.

The maximum hardness for AASHTO M 164(A325) bolts shall be 33Rc.  The maximum tensile strength shall be 150ksi for bolts 1 inch or less in diameter and 120ksi for larger bolts.

Nuts shall be Grade 2H or DH for black or galvanized fasteners.  For galvanized fasteners the nuts shall be overtapped to the minimum amount required for the fastener assembly.  All nuts, bolts and washers shall have the manufacturers markings on them.

All galvanized nuts shall be lubricated with a lubricant containing a visible dye so a visual check can be made for the lubricant at the time of field installation.  Black bolts shall be "oily" to the touch when installed.  Weathered or rusted bolts shall be cleaned and re-lubricated prior to installation.

High-strength fasteners, black or galvanized, shall be subjected to a rotational-capacity test (AASHTO M 164, Section 8.5) and shall meet the following requirements:

1.	They shall go through two times the required number of turns (from snug tight conditions) indicated in the 1988 Interim AASHTO Bridge Specification, Table 10.17B, in a Skidmore-Wilhelm Calibrator, or equivalent tension measuring device, without stripping or failure.

2. 	During this test, the maximum recorded tension shall be equal to or greater than 1.15 times the Required Fastener Tension, AASHTO Table 10.17A.

3.	The measured torque to produce the Required Fastener Tension shall not exceed the value obtained by the following equation:

Torque = 0.25 PD

Where:  Torque = Measured Torque (Foot-Pounds)

P      = Measured Bolt Tension (Pounds)

D      = Nominal Diameter (Feet)

Proof load tests (ASTM F 606 Method 1) are required for the bolts.  Wedge tests of full size bolts are required in accordance with Section 8.3 of AASHTO M 164.  Galvanized bolts shall be wedge tested after galvanizing.  Proof load tests (AASHTO M 291) are required for the nuts.  The proof load tests for nuts to be used with galvanized bolts shall be performed after galvanizing, overtapping and lubricating.

All galvanized nuts shall be lubricated in accordance with ASTM A563 Section 4.8.  In addition the name, method of application, and dilution of the lubrication applied to the nuts shall be provided with the documentation.

Section 7.4 of ASTM A563 shall be deleted and Section 7.5 changed to read as shown below.  These requirements also apply to 2H nuts covered under ASTM A194.

7.5  Nuts to be used on bolts mechanically zinc coated or on bolts hot-dip zinc-coated, shall be tapped oversize by a diametral amount sufficient to permit assembly on the coated bolt thread, unless other requirements are specified in the inquiry or purchase order.

(5/12/89)M26

SECTION 720

ELASTOMERIC PADS

Special Provisions

720-2.01.  Delete this subsection in its entirety and substitute the following:  Elastomeric bridge bearing pad shall conform to the requirements of AASHTO M 251-90 with the following revisions:

4.	MATERIALS

4.1  Properties of the Elastomer.  Delete the first sentence and substitute the following:  The elastomeric compound used in the construction of the bearings shall contain only virgin natural polyisoprene (natural rubber) as the raw polymer; neoprene shall not be used.  Properties and requirements elsewhere in AASHTO M251-90 pertaining solely to polychloroprene (neoprene) shall not be applicable.

Amend Table 1 as follows:  Replace the expression "-40F (-40C)" with "-67F (-55C)" in the row labelled "Brittleness" under the column heading "Test Requirements."

5.	FABRICATION

Add the following paragraph:

5.5.  Pads over three-quarters of an inch in thickness shall be laminated and shall consist of alternate laminations of elastomer and metal reinforcements.  The outside laminations shall be metal.  Laminations of elastomer shall be 1/2 inch +1/8 inch in thickness.

8.	BEARING TESTS AND ACCEPTABLE CRITERIA

8.2.2.  Delete Note 1 in its entirety and add the following paragraph:  The elastomer shall also be tested for ozone resistance under ASTM D1149, method A at 100 degrees F, 20 percent strain, partial pressure of ozone - 50 MPa, and 100 hours.  It shall show no cracks.

8.2.4.  Delete in its entirety and substitute the following:  A minimum of one pad per lot shall be tested for bond strength as follows:

Steel Laminations - ASTM D429 Method B - 40 lb/in., minimum.

Fabric Laminations - California Test No. 663 - 40 lb/in., minimum.

8.2.5.  Delete the word "Optional."

9.	TESTING

9.1.  Delete the word "Optional."

(4/7/92)R152

Special Provisions

720-2.02  Manufacturing Requirements.  Add the following subsection:  Laminations of elastomer shall be 1/2-inch +1/8-inch in thickness.

SECTION 724

SEED

Standard Modifications

724-2.02  Materials.  Add the following to Table 724-1:

| Seed Type | Germination Period | Percent Purity | Percent Germination | Percent Sproutable Seed |
| --- | --- | --- | --- | --- |
| Bering Hairgrass | 14 days | 95 | 75 | 71 |

(5/12/89)M28

SECTION 726

TOPSOIL

Standard Modifications

726-2.01  Topsoil.  In the second paragraph, change "not less than 1%" to read "not less than 3%".  (5/12/89)M29

Special Provisions

726-2.01  Topsoil.  Delete the fertilizer requirements as stated in this subsection.

Add the following:  Fertilizer shall be applied as stated in Section 618.  (5/15/92)R139

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01  Embankment Separation.  Delete this subsection in its entirety and substitute the following:  Geotextile materials for embankment separation shall meet the requirements of AASHTO M 288 for Separation (medium survivability), except that the minimum permeability of the fabric shall be 0.005 cm/sec.  (5/17/93)R97

729-2.04  Sediment Control.  Add the following subsection:  Geotextile materials for Sediment Control shall meet the requirements of AASHTO M 288 for Sediment Control, except that the minimum permeability of the fabric shall be 0.002 cm/sec.  (5/17/93)R97

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04  Sign Posts.  Under item 1., Metal Pipe Posts, add the following to paragraph a.:  Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Delete Item 4., "Multi-directional Breakaway Load Concentration Coupler Base Assemblies and Coupler Hinge Plate", and substitute the following:

4.	Wide Flange Posts.

a.	Steel for wide flange posts shall conform to AASHTO M 183.

b.	Post sizes shall be as designated on the plans.

c.	Posts shall be hot dip galvanized in a manner conforming to AASHTO M 111 after fabrication.  Any cutting of metal posts after hot dip galvanizing shall be accomplished with minimum damage to the zinc coating and all exposed surfaces shall be protected by treating the exposed area in the same manner as if it were abraded or damaged.

d.	Galvanized surfaces that are abraded or damaged at any time after the application of the zinc coating shall be repaired in accordance with the applicable provisions of AASHTO M 36.

(5/7/91)S43

APPENDIX A

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS