SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	Copies for review of the following are available in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Computations

b.	Cross Sections

c.	Partial Plans of Existing Tidewater Slough Bridge, No. 640

Copies of the above documents may be obtained from Ridgways Reprographics, 6000 Arctic Boulevard, Anchorage, Alaska  99518, (907) 561-1555, at the Contractor's cost.

2.	The following reports are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Seward Highway, MP 90.3 to 97.0, Girdwood to Bird Point Geotechnical and Tide Report, dated September 1993.

b.	Foundation Report, Tidewater Slough Bridge Replacement, dated June 1993.

c.	Storm Water Manual (Cost = $20)

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Traffic, Safety and Utilities Engineer, (907) 266-1531.

4.	An environmental document addressing concerns and environmental commitments is available for review in the office of the Preliminary Design and Environmental Supervisor (907) 266-1508.

5.	This contract contains a newly-developed asphalt concrete pavement specification (Section 401).  Due to changes in materials testing procedures and requirements, the following new items are incorporated by reference in this specification and are available from the Department:

a.	Alaska Test Method T-17, Rev. 06/93, Standard Method of Test for Determining Bituminous Mix Design by the Marshall Method.

Alaska Test Method T-17 is the mix design method and also includes criteria which must be met for the class of mix specified in the bid schedule.

b.	Alaska Standard Practice SP-9, Rev. 07/93, Standard Practice for Abbreviated Testing Procedures to Monitor Process Control of Coarse and Fine Aggregate Gradations.

Standard practice SP-9 contains test methods for contractor process control as well as a minimum testing frequency, and a list of typical field laboratory equipment to be furnished by the Contractor.

PART 4

STANDARD MODIFICATIONS

and SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS for HIGHWAY CONSTRUCTION

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.27  HOLIDAYS.  Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third Monday in January

3.	President's Day - Third Monday in February

(5/7/91)M30

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01  QUALIFICATION OF BIDDERS.  Delete the second paragraph.  (5/12/89)M1

102-1.06  PREPARATION OF PROPOSAL.  Replace the second paragraph with the following:  The bidder shall specify a unit price, in figures, for each pay item for which a quantity is given and shall also show the products of the respective unit prices and quantities written in figures in the column provided for that purpose and the total amount of the proposal obtained by adding the amounts of the several items.  All the figures shall be in ink or typed.  In the event of a discrepancy between unit bid prices and extensions, the unit bid price shall govern.  Any changes shall be initialed by the person signing the proposal.  (7/2/93)M58

Add the following:  At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him.  The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted.  This limitation will only apply to those projects on which the bidder has added the following statement to the Proposal Form:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

102-1.07  NON-RESPONSIVE PROPOSALS.  Delete item 3. in its entirety and substitute the following:

3.	If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to the bidder at any one bid letting, as provided in Subsection 102-1.06, Preparation of Proposal.

(5/7/91)M31

Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)M2

102-1.12  ADDENDA REQUIREMENTS.  In the second sentence, add "or telefacsimile" immediately following the word "telegram".  (5/12/89)M3

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01  CONSIDERATION OF PROPOSALS.  Add the following:  The apparent low bidder shall submit the following within 5 working days following receipt of written notification of apparent low bidder by the Department:

1.	A plan for dealing with the rock excavation item, showing the following for each rock cut area:

a.	method of accomplishing the rock excavation, including the number and sequence of blasts (i.e., working the face from north to south)

b.	station limits, height and expected volume for each blast

c.	cycle time for completing each blast and for hauling

d.	number of days to complete the work, broken down by month

e.	general traffic control plans for railroad and highway closures needed, including time of day and days per week

f.	method of protecting adjacent utility and railroad facilities from damage, and plan for restoring any damage that may occur

Approximately one week after submittal of this plan, the apparent low bidder shall attend a meeting with the Department, the Railroad and Utility companies to clarify the plan and address any concerns that may arise.

2.	A completed Subcontractor List, Form 25D-5(C)

If a bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this Subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this Subsection.

If a contract is awarded to a bidder who violates this Subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department, or

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the contract with the bidder involving work for which the subcontractor was  listed,

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or

9.	is determined by the Contracting Officer not to be responsible.

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.02  CHANGES.  After the third paragraph add the following:  Before a Change Order or Supplemental Agreement is approved, the Contractor shall submit cost or pricing data regarding the changed or extra work.  The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work.  (5/12/89)M5

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01  AUTHORITY OF THE ENGINEER.  Add the following:  The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02, Changes.  Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)M6

Special Provisions

105-1.06  COOPERATION WITH UTILITIES.  Add the following:  The Contractor shall request locates from all the utilities having facilities in the area.  Their telephone numbers are as follows:

Anchorage Telephone Utility	564-1555

Chugach Electric Association	562-2278

Alaska Railroad Corporation	265-2457

DOT/PF Maintenance & Operations	783-2232

Alyeska Cable 	562-3000

Military Petroleum Fuel Line	552-5419

Locate Call Center	278-3121

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

Prior to the relocation of the utility's facilities, construction staking may be required.  The Contractor shall give the Utility 2 weeks advance notice as to when the staking will be available and maintain the stakes until the utility relocation is completed.  Payment for this staking will be as follows:

1.	If construction staking or right-of-way staking is required by the Utility in advance of the Contractor's normal schedule, the Utility will request the staking, through the Engineer, two (2) weeks prior to the time the staking is required for the Utility to start their relocation.  This staking will be paid under Item 642(2), Three Person Survey Party.

2.	If, as part of the contract, the Contractor provides the stakes in the area needed by the Utility, this work will be subsidiary to Item 642(1), Construction Surveying.

3.	If right-of-way staking is required by the Utility, and staking the right-of-way is not a part of the contract, the Utility will request the staking, through the Engineer, two (2) weeks prior to the time the staking is required for the Utility to start their relocation.  This staking will be paid under Item 642(2), Three Person Survey Party.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

Chugach Electric Association, Inc.  When working near Chugach Electric Association facilities, the Contractor shall adhere to requirements set forth in "Construction or Maintenance Near Electrical Facilities" and "Electrical Facility Clearance Requirements" attached to these specifications as Appendix A.

All work near Chugach Electric Association facilities shall be conducted in such a manner as to protect the utility facilities at all times from damage and outages resulting directly or indirectly from the Contractor's or subcontractor's operations.

All blasting operations within 1000 feet of Chugach's facilities shall be coordinated with Chugach.  A visual inspection of transmission and/or distribution lines exposed to debris shall be performed by a qualified inspector approved and authorized by Chugach at the Contractor's expense after every blasting operation.  Payment for this inspection will be made directly from the Contractor to Chugach.  It is anticipated that approximately 4 hours per blast at a cost of $100/hour is needed to perform this work.

If facilities are damaged, the responsible party shall bear the costs of repair or replacement.

If an underground electrical cable is damaged and requires splicing, the first time will be repaired by the Utility with the party causing the damage paying the repair costs.  If an electrical cable is damaged a second time, the cable will be replaced between junction points.  The party causing the damage shall pay for replacing the cable.

Chugach Electric Association's 115 kV transmission line transfers energy from the Kenai Peninsula Hydro Projects to Anchorage and Fairbanks.  It will remain energized throughout the construction period.  Unscheduled outages caused by the Contractor's activities can result in costs of up to $20,000 per hour.  Chugach will assess these costs as damages in addition to any repair costs incurred due to physical damage to its facilities.

Anchorage Telephone Utility.  ATU's fiber optic cable will be relocated during this project.  The Contractor shall install an underground conduit system (innerduct with handholes) in accordance with Section 680.  After the completed conduit system is accepted by ATU, ATU will install the new fiber optic cable.  ATU requires 28 calendar days to complete the installation and retire the existing fiber optic cable.  No blasting shall occur on the project until after the existing fiber optic cable is retired.

Alaska Railroad Corporation.  The Alaska Railroad Corporation will install two temporary railroad crossings at locations near the rock excavation section.  Two weeks prior to the construction of the temporary railroad crossings, the Contractor shall submit a plan identifying the specific location and duration needed for each crossing.

The ARRC will provide all railroad flag protection for the project.  Railroad flag protection is required for any work within 20 feet of the tracks or wherever required by the Railroad's Field Representative.

Standard Modifications

105-1.12  LOAD RESTRICTIONS.  Delete the first paragraph and substitute the following:  The Contractor shall comply with all restrictions as set forth in the "Administrative Permit Manual", and Title 17, Chapter 25, of the Alaska Administrative Code for vehicles traveling with the general public, unless otherwise allowed by an approved Traffic Control Plan.  (5/7/91)M32

Special Provisions

105-1.12  LOAD RESTRICTIONS.  Add the following to the second paragraph:  Overload and oversize permits will be issued to move the prestressed concrete girders between the Port of Anchorage, an Anchorage fabricating yard, the dock of Seward or the dock at Kenai and the job site.  No overload may cross the Ship Creek Bridge, Bridge No. 417.  Unless otherwise permitted by the overload permit officer, any permit will be subject to the following limitations:

Maximum Single Axle Load	30,000 lbs.

Maximum Tandem Axle Load	60,000 lbs.

Maximum  Triple Axle Load	80,000 lbs.

Maximum Four Axle Load	95,000 lbs.

Maximum Spacing of Axle Groups	20 feet center to

center axle groups

Minimum Spacing within Group	4 feet center

to center axles

Maximum Speed on any Structure	3 mph

The maximum axle loads tabulated above are applicable to hauling equipment with fixed axles only; variable load suspension (VLS) axles shall not be considered part of an axle group for purposes of this specification.

Vehicles shall cross structures at a constant speed, centered on the roadway, and with no shifting of gears.  Whenever the load exceeds 80,000 pounds, the vehicle shall be preceded by a walking flagger when crossing structures.

This overload allowance shall not apply to the transportation of construction materials other than prestressed concrete girder sections.

All overload permits are subject to seasonal load restrictions.

Routing shall be as prescribed by the permit officer, (800) 478-7636 or (907) 345-7750.

Alternate axle configurations and loadings which may reduce the overload movement restrictions and conditions are subject to individual review and analysis by the permit officer.

105-1.13  MAINTENANCE DURING CONSTRUCTION.  Add the following:  The Department will periodically perform avalanche control work along the mountains above the project.  This work will  halt the Contractor's operations in the avalanche zone.  Any avalanches that occur on the project, whether induced by the Department or nature, shall be removed as necessary by the Contractor for his work to continue.  The Department's control work will be standard avalanche control designed to reduce avalanche hazards to the motoring public, travelling through the project at a normal rate of speed.

The Alaska Railroad will be performing snow removal operations from their tracks.  It is possible this snow will interfere with the ability to blast, load, haul, or place material.  The Contractor shall remove the snow as necessary for his work to continue.

No separate payment will be made for removal of avalanche debris or snow.  This work will be subsidiary to Item 203(1), Common Excavation.

Standard Modifications

105-1.15  PROJECT COMPLETION.  Replace the first sentence of the third paragraph with the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work scheduled under subsection 618-3.04 Maintenance of Seeded Areas and subsection 621-3.04 Period of Establishment, a letter of project completion will be issued by the Engineer.  (7/2/93)M7

105-1.17  CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable.  (7/2/93)M8

Special Provisions

105-1.17  CLAIMS FOR ADJUSTMENT AND DISPUTES.  Replace the first sentence of the eighth paragraph with the following:  If the claim is not resolved by agreement within 30 days of its receipt, the Engineer will issue a written decision to the Contractor.  (7/2/93)S71

Add the following:  Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage.  (12/26/90)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01  SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  Add the following:  All steel and iron products which are incorporated into the work and the action of applying a coating to a covered product (i.e., steel and iron) shall be manufactured in the United States except that minor amounts of products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater.  Coating includes epoxy coating, galvanizing, painting, and any other coating that protects or enhances the value of a material subject to the requirements of this paragraph.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel or iron products into the project.

(7/2/93)S13

106-1.02  LOCAL MATERIAL SOURCES.  Under Item 1. General, add the following to the first paragraph:  If blend material is required to produce the specified product, it will be considered a subsidiary obligation and no separate payment will be made.  (2/7/89)S32

Add the following:  Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources.  A copy of this statement shall be provided to the Engineer.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at 762-2622.  Should cultural resources be discovered during material testing or extraction activities, work at that site shall be stopped and the Engineer notified.  (9/1/89)R5

SECTION 107

LEGAL RELATIONS AND

RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.08  RAILWAY-HIGHWAY PROVISIONS.  Delete the second paragraph and add the following:

1.	Definition of Terms.

a.	Railroad's Chief Engineer - the person employed by the Railroad as head of its Engineering Department.

b.	Field Representative - the person authorized to act for the Chief Engineer and the Alaska Railroad Corporation.

c.	Facility - any improvements owned by the Department which are to be placed on Railroad property in accordance with a written permit executed by the Railroad and the Department.

d.	Railroad - the Alaska Railroad Corporation, P.O. Box 107500, Anchorage, Alaska  99510-7500.

e.	Railroad Property - all lands owned or withdrawn for the use of the Railroad, in and including the track right-of-way and communications pole right-of-way.

f.	Trackwork - all work on the line from the top of subgrade to the top of rail, including geotextile, when required.

g.	Track Materials - all hardware, excluding signals and controllers, associated with the running of a railroad.

2.	General Requirements.

a.	All construction, reconstruction, operation and maintenance on the Railroad Property shall be performed in compliance with these specifications.

b.	Failure to comply with these specifications  shall result in the suspension of all work on Railroad Property.

c.	All negotiations between the Railroad and the Contractor shall be handled through the Department.

d.	All work on or about the Railroad Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with the approved Railroad practices, and as specified herein.  Railroad traffic and property shall be protected at all times.

e.	The safety and continuity of the operation of the railroad traffic shall be of first importance and shall be at all times protected and safeguarded.  The Contractor and his subcontractors shall perform and arrange their work accordingly.  The Railroad's Field Representative shall decide all matters involving the safety of Railroad facilities and the operation of it's railroad.  The approval of the Railroad's Field Representative, when given, shall not be considered as a release from responsibility or liability for any damage which the Railroad may suffer or for which it may be liable, as a result of the acts of the Contractor, his subcontractor or employees.

f.	Whenever in the opinion of the Railroad's Field Representative, the construction may cause a hazard to the safe operation of the Railroad, he may place at the site of the work the required number of qualified employees to protect the Railroad's operations.  All Railroad cost and expense for providing such employees shall be collected from the Contractor, except for flagging which shall be paid for as described in Subsection 107-1.08.5,b, Flag Protection and Protection of Railroad Traffic.

g.	The Contractor shall be responsible for maintaining sight triangles at all railroad crossings within the project limits and at any railroad crossing outside the project limits that is designated and used as an alternative route for traffic.

3.	Field Representation.  The Railroad shall furnish a full-time field representative who will have the authority to act for the Chief Engineer and the Alaska Railroad Corporation during the periods of construction on Railroad Property.  The Field Representative will inspect the tracks after each blast and at all crossing, and monitor flagging, lighting, clearances, etc., when necessary.  He  will work directly with the Engineer and the decision of the Field Representative in matters pertaining to Railroad operations and safety shall be final.  In the event more than one shift is worked, the Field Representative will be on-site for each shift.

4.	Insurance Requirements.

a.	The Contractor shall comply with all insurance requirements and conditions specified under Subsection 103-1.05, Insurance Requirements, except that the following minimum limits shall apply for Comprehensive or General Liability Insurance:

Bodily Injury - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Property Damage - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Blanket Contractual

b.	Prior to commencement of work on Railroad Property, the Contractor shall provide evidence to the Field Representative of Railroad Protective Liability insurance (Alaska Railroad and State of Alaska as insureds) with the following limits:

Bodily Injury - $2,000,000 per occurrence

Property Damage - $2,000,000 per occurrence

5.	Notice.  The Contractor shall give written notice and schedule to the Department and the Field Representative not less than 10 days in advance of the commencement of any major work on Railroad Property, in order that the necessary arrangements may be made for the protection of the Railroad's operation.

6.	Flag Protection and Protection of Railroad Traffic.

a.	Whenever Railroad flag protection is required for the two temporary crossings, this flag protection shall be provided by the Railroad.  Railroad flag protection is to insure the safe movement of trains and other rail traffic and shall be done in strict accordance with the Railroad rules on flagging.  The Alaska Railroad requires 48 hours advance notice to schedule flagging.

b.	All Railroad expenses for providing flagmen for the two temporary crossings shall be reimbursed by the Department.  If the Contractor calls for flagmen and, through no fault of the Department or the Railroad, the flagmen are not needed, payment shall be deducted from monies due the Contractor.  Other flagging, required by the Contractor's operation, shall be paid for by the Contractor.

c.	Vehicles and other construction equipment shall not be operated or parked closer than 20 feet from centerline of any track without railroad flag protection provided in accordance with Item a. above.

d.	The Contractor shall coordinate with the Field Representative information on the time of arrival of all trains and shall entirely stop any of the operations which might be or cause a hazard to the safe passage of the train past the site of the work from 10 minutes before the expected arrival of the train until the train has passed.

7.	Train Delays.

a.	All work on Railroad property shall be conducted in such a manner as to prevent delays to trains or other rail traffic operated by the Railroad.

b.	Should any of the Contractor's or subcontractor's actions or activities cause delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

| Passenger Trains | $50 per minute for each delay. $3,000 minimum charge. |
| --- | --- |
| All other trains and rail traffic | $50 per minute for each delay over five minutes. $1,500 minimum charge. |
| Rail barges, train-ships or other connecting carrier vessels | No charge for delays of an hour or less. $1,000 per hour for each hour or any part of an hour thereafter, with a minimum charge of $6,000. |

c.	Delay time will be taken from the train sheet in the Railroad Dispatcher's Office, in Anchorage, (265-2649) for all delays and such train sheet shall be the official document by which the length of time a train is delayed will be determined.  If another crew is needed to relieve the original crew, the charge shall also apply to the second crew.  If such delay causes a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by said train sheet.

8.	Protection of Railroad Communication Lines.

a.	All work on Railroad Property shall be conducted in such a manner as to protect the Railroad's communications facilities at all times from outages resulting directly or indirectly from the Contractor's or his subcontractor's operations.

b.	Should any of the Contractor's, or his subcontractor's operations cause outages to said communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

| Open wire communication circuits | $1.00 per minute per circuit |
| --- | --- |
| Communication cable | $5.00 per minute per cable |

c.	A minimum charge of $250 will be made for each outage.  The outage time shall be that as established by the Railroad's Test Board, Anchorage.

d.	There shall be no equipment worked or excavation within 15 feet of any Railroad communication pole guy, anchor, or other communications apparatus unless authorized in advance by the Field Representative.

9.	Railroad Crossings and Haul Routes.

a.	Whenever automatic railroad crossing signals are in the permit area, these signals must remain in operating condition at all times.  If, as a result of the Contractor's activities on the facility, the signals become inoperable the crossing shall be continuously protected in accordance with Subsection 107-1.08.6. until the signals are again operable.

b.	Two temporary road crossing permits have been obtained by the Department for the Contractor's operation.  Their location and times of use shall be coordinated by the Contractor with the Field Representative.

The temporary crossings will be constructed by the Alaska Railroad.  The Contractor shall notify the Alaska Railroad, in writing, at least two weeks in advance of need, of the date and exact location for the two temporary crossings.  Upon completion of the work, the temporary railroad crossings will be removed by the Alaska Railroad.

c.	The flange ways of all road crossings used by the Contractor or subcontractor as haul routes or temporary road crossings shall be kept free of gravel at all times and shall otherwise be maintained to the satisfaction of the Field Representative.

d.	All haul routes and access roads within the Railroad property shall be reviewed and approved by the Field Representative.  At the beginning and end of each route or access, the Contractor shall install a gate controlled by the Field Representative during train traffic.  Operations on these routes may be suspended in accordance with Subsection 107-1.08.6,c.

10.	Underground Facilities.

a.	All underground utilities, including culverts, pipelines and underground power and communication lines, on Railroad property shall conform to the current AREA Specifications.

b.	Unless another method is authorized in advance by the Field Representative, all underground facilities shall be installed under tracks and roads by boring, jacking or tunneling.  The proposed plan for boring, jacking or tunneling shall be approved by the Field Representative prior to commencing the operation.  All boring, jacking or tunneling headings shall be continuously protected against any loss of ground material by shoring or cribbing as necessary.

c.	Boring, jacking and tunneling shall be done under Railroad tracks only when Railroad flag protection is provided in accordance with Subsection 107-1.08.6.

11.	Open Trenching.

a.	Only when authorized in advance and in writing by the Field Representative shall any portion of the track be removed to allow trenching for installation of the facility.

b.	If allowed to open trench, the track may be removed from service only at the time authorized by the Field Representative and shall be restored to service within the time period specified.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in accordance with Subsection 107-1.08.7., whichever is greater and shall be collected from the Contractor.

c.	All work on track materials shall be accomplished by the Railroad.

d.	Only that portion of the track structure necessary to excavate, stockpile and install the facility shall be removed.  All track material removed shall be handled, stockpiled, and relaid in a manner as to avoid damage.  Any material which is damaged shall be replaced by the Contractor at his own expense.

e.	The backfill of the trench under the track and in the roadbed prism shall be of the same type of material as taken out, except the top 2 feet shall be clean pit run gravel.  Backfilling and compaction in the area affecting the roadbed prism shall be in accordance with the requirements of Section 204, Structure Excavation for Conduits and Minor Structures.

f.	The ballast used in replacing the track shall be equal in depth and quality to that which was removed.  The track shall be relaid and brought to original grade in accordance with standard Railroad practices.

12.	Excavations.

a.	Unless authorized in advance by the Field Representative, the top of any excavation shall not be within 20 feet of center line of any track.

b.	No water shall be allowed to stand in open excavations in the track area.

c.	Bridging and shoring shall be adequate to safely carry Railroad traffic.

d.	All open excavations shall be continuously protected by flags, barricades, or watchmen as directed by the Field Representative.

e.	No excavation shall be left open more than three days, unless authorized by the Field Representative.

f.	The Railroad embankment, and cut slopes, shall not be disturbed any more than necessary to accommodate the construction and shall be left in a stabilized condition.

g.	Railroad ditches, culverts and roadways shall be kept clean and free of rock, gravel, construction debris and equipment at all times.

13.	Use of Explosives.

a.	The use of explosives shall be accomplished in compliance with all applicable Federal, State and local laws and ordinances regarding the same.

b.	No blasting of any kind will be permitted unless the Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, Railroad flag protection in accordance with Subsection 107-1.08.6., shall be provided on each side of the blast area by the Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

c.	The Contractor will notify the Field Representative and the Engineer of the exact time of each blast at least two hours prior to a blast.

14.	Snow Removal.

a.	Snow removal operations shall be conducted in such a manner as to not place snow (1) upon the tracks of the Railroad, (2) where it interferes with the normal operation of the automatic crossing signals, or (3) impairs the visibility of either highway or rail traffic  at the crossings.

b.	Snow removal operations shall be conducted in accordance with Subsection 107-1.08.6.

15.	Clean-Up.

a.	At all times, all work and activities on the Facility shall be accomplished in such a manner as to keep the Railroad Property in a neat and orderly condition.  Upon completion of work, all equipment and unused materials shall be removed and the Railroad property shall be left in a neat and clean condition satisfactory to the Field Representative.

b.	Should the Contractor or subcontractor fail to comply with this Subsection, the Railroad may perform the required clean-up.  All Railroad costs and expenses for performing this work shall be collected from the Contractor.

17.	Payment Guarantee.

a.	The Department shall withhold 10 percent of the contract price or $10,000, whichever is smaller, from the final payment to apply against damages or other direct costs which may be assessed by the Railroad as a result of the Contractor's operations.

b.	The amount withheld above shall not be released until after the Department has received a written statement from the Field Representative agreeing to release the payment.

(8/4/93)

107-1.11  PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following to the third paragraph:  When working near designated wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits.  (2/9/91)R7

The Contractor shall report immediately to the Engineer any hazardous material discovered, exposed, or released into the air, ground, or water during construction of the project.  The Contractor shall also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery.  Hazardous materials include, but are not limited to, petroleum products, oils, solvents, paints, and chemicals that are toxic, corrosive, explosive, or flammable.  (5/7/91)S47

The Contractor shall not excavate, nor use for fill, any material at any site suspected or found to contain hazardous materials or petroleum fuels.  The Contractor shall not stockpile, nor dispose of, any material at any site suspected or found to contain hazardous materials or petroleum fuels.  (2/9/91)R7

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2575.

Add the following:  The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.

The Contractor shall do no work, stockpiling, staging, parking nor trespassing below the ordinary high water mark of any watercourse or in any wetlands except as permitted by the contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

(2/9/91)R7

Standard Modifications

107-1.13  RESPONSIBILITY FOR DAMAGE CLAIMS.  In the first sentence, change "claims or actions for injuries" to read claims, actions or liabilities for injuries".  (5/12/89)M9

Special Provisions

107-1.15 CONTRACTOR'S RESPONSIBILITY FOR WORK.  Add the following to the end of the first paragraph:  Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense.  (5/7/91)S48

Standard Modifications

107-1.16  CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICES.  In the last sentence of the third paragraph delete: "by the local fire authority."  (5/12/89)M10

Special Provisions

107-1.16  CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICES.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The utility mislocates the facility in the field by more than 2.5 feet horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the utility.

(10/1/91)R8

Add the following:  Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work to be performed.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, will not be paid for separately, but will be subsidiary to the item(s) of work being performed requiring cable watch services.

107-1.21  PERMITS.  Add the following subsection:  The following permits have been received on the Contractor's behalf by the Department:

1.	U.S. Army Corps of Engineers 404/10 Permit, No. 2-930117, Turnagain Arm 36, dated July 1, 1993, expiring June 30, 1998.

2.	Alaska Department of Fish and Game, Title 16 Permit, No. FG 93-II-0218, dated June 10, 1993, expiring December 31, 1994.

3.	Municipality of Anchorage Flood Hazard Permit, No. FHP 93-0034-00, dated July 26, 1993.

The Contractor shall provide the information necessary to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge stormwater from the construction site.  Requirements for this permit are given under Section 641, Erosion and Pollution Control.

The permits obtained by the Department are attached to these specifications as Appendix B.  The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor's responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer.  The Engineer will then decide if a permit modification is necessary.  The Engineer will have copies of the permits posted in the project office.

(9/10/92)R9a

107-1.22  CONSTRUCTION ACCESS.  Add the following subsection:  To access the rock excavation area from the existing Seward Highway, the Contractor is permitted to cross lands owned by Chugach State Park at approximate MP 93.5.  The Contractor shall submit a plan showing route location, road width and approximate grades, and removal and restoration steps.  This plan shall be submitted to the Engineer and the Contractor shall allow a minimum of two week period for review by Chugach State Park and the Engineer.  Approval will be required prior to implementation.  Construction, maintenance, removal and restoration of this access will be subsidiary to Item 640(1), Mobilization and Demobilization.

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01  SUBLETTING OF CONTRACT.  Delete the third paragraph on page 56 and substitute the following:  The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions.  Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator.  As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Commercial Driver's License, with appropriate endorsements for the class of vehicle to be operated.

2.	Business license for trucking together with supporting documents that list the driver as the business owner or corporate officer.

3.	Documents showing the driver's ownership interest in the truck including:

a.	Truck registration, and

b.	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor.  The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended  payrolls  must be submitted  listing the

driver as an employee subject to all labor provisions of the contract.  These criteria are:

1.	The owner-operator's right to control the manner in which the work is to be performed,

2. 	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3. 	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4. 	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each owner-operator.  The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors.  The identification system must be approved by the Engineer prior to use.

(5/7/91)S49

Standard Modifications

108-1.03  PROSECUTION AND PROGRESS.  In Item 1. insert ", in a format acceptable to the Engineer," immediately after the words "a progress schedule". (5/12/89)M11

Special Provisions

108-1.03  PROSECUTION AND PROGRESS.  In the first paragraph, delete the words "At this time" and substitute:  "Five working days before the preconstruction conference".  (5/7/91)S50

Delete Item 5., and substitute the following:

5.	A plan for erosion and pollution control, as required under Subsection 641-1.02, Submittals.  (9/21/92)R160

Add the following:  The construction of this project shall be planned and recorded with a Critical Path Method (CPM) schedule.  The schedule shall be used for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

1.	Preparation of CPM Schedule.  The Contractor shall submit for the Engineer's approval, a detailed initial CPM schedule.  The schedule shall meet the requirements set forth below.

The construction time, for the entire project shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, the Contractor shall do so promptly.  The CPM schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements.  The CPM schedule shall be set up so that the schedule may be read by Prima Vera scheduling software being run on an IBM compatible micro computer with a 1.44 mb disk drive.  All required CPM schedule submittals shall include 1 hard copy and 1 copy of the same schedule on a 3.5-inch double sided diskette.

The CPM schedule shall be presented as a Precedence Diagram Network developed in the activity-on-node format and shall include:

a.	activity description,

b.	activity duration,

c.	resources required for each of the project activities, including:

(1)	labor, showing:

-work days per week

-holidays

-shifts per day

-hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-node diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60-Day Preliminary Schedule.  Before proceeding with any work on site, the Contractor shall prepare, submit, and receive the Engineer's approval of a 60-Day Preliminary Schedule.  This schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include mobilization, submittals, procurement, and construction.

No contract work may be pursued at the site without an approved 60-Day Preliminary Schedule or an approved CPM schedule.

4.	Schedule Updates.  Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the CPM schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions.  The Contractor shall submit a revised CPM schedule within 7 calendar days after this meeting.  The revised schedule shall show finish dates of completed activities and updated times for the remaining work, including any addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

In addition to the CPM schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks.  This plan shall detail the following:

1.	work activities,

2.	manpower involved by trade,

3.	work hours,

4.	equipment involved, and

5.	the location of the work to be performed.

After approval of the progress schedule, and during the life of this project, the Contractor shall make available a spokesperson knowledgeable in the proposed construction operation.  Department representatives may be attending public meetings and community council meetings, and the spokesperson shall accompany them and provide a brief description and answer questions about the Contractor's work and schedules for the project.  The spokesperson will also be required to accompany the Engineer to residents and businesses affected by the project when disputes or problems arise as a result of the work being performed under this contract.  The spokesperson must be able to commit the Contractor to courses of action when needed to resolve problems.

Preparation and updating of the CPM schedule and two week work plans and providing a spokesperson will not be paid for directly.  Failure to submit the CPM work schedule and two week work plans as specified will result in partial withholding of progress payments in accordance with subsection 109-1.06, Progress Payments.  (1/27/92)R11

108-1.05  CHARACTER OF WORKMEN, METHODS AND EQUIPMENT.  Add the following:  The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project.  This information shall be updated weekly unless otherwise directed by the Engineer.

Prior to working on the project during periods of avalanche danger, the Contractor shall perform the following:

1.	Prepare an avalanche work plan that will address methods to safely operate in the vicinity of known avalanche areas.  This plan shall be submitted to the Engineer a minimum of 14 days prior to beginning work or within 7 days of the Engineer's request for an update.

2.	Provide a training seminar for all workers on avalanche dangers and rescue methods.

3.	Have avalanche rescue equipment available at the work site.

Standard Modifications

108-1.07  FAILURE TO COMPLETE ON TIME.  Replace the third sentence of the first paragraph with the following:  The amount of these deductions is to reimburse the Department for estimated additional contract administration expenses incurred as a result of the Contractor's failure to complete the work within the time specified.

Replace Table 108-1 with the following:

TABLE 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES FOR EACH CALENDAR DAY OF DELAY

| Original Contract Amount |  | Daily Charge |
| --- | --- | --- |
| From More Than | To and Including |  |
| $ 0 | $ 100,000 | $ 300 |
| 100,000 | 500,000 | 550 |
| 500,000 | 1,000,000 | 750 |
| 1,000,000 | 2,000,000 | 1,000 |
| 2,000,000 | 5,000,000 | 1,500 |
| 5,000,000 | 10,000,000 | 2,500 |
| 10,000,000 | - | 3,000 |

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.01  GENERAL.  Add the following:  When more than one type of material or work is specified for a pay item, letter or numeric suffixes, included within the parenthesis following the pay item number, will differentiate the types.  (7/2/93)S63

109-1.02  MEASUREMENT OF QUANTITIES.  Add the following:

TABLE 109-1

| CONVERSION TO THE SI INTERNATIONAL SYSTEM OF UNITS* |  |  |
| --- | --- | --- |
| To convert from | to | Multiply by |
| mile (US Statute) | meter (m) | 1,609.347 |
| foot | meter (m) | 0.3048 |
| foot (US survey) | meter (m) | 1200/3937 |
| inch | meter (m) | 0.0254 |
| square foot | square meter (m2) | 0.09290304 |
| square yard | square meter (m2) | 0.8361274 |
| acre (US Survey) | square meter (m2) | 4,046.873 |
| cubic foot | cubic meter (m3) | 0.02831685 |
| cubic yard | cubic meter (m3) | 0.7645549 |
| gallon (US liquid) | cubic meter (m3) | 0.003785412 |
| M. Gal. | cubic meter (m3) | 3.785412 |
| pound (lb avoirdupois) | kilogram (kg) | 0.45359237 |
| ton (short, 2000 lb) | kilogram (kg) | 907.1847 |
| pound-force (lbf) | newton (N) | 4.448222 |
| footcandle | lux (lx) | 10.76391 |
| degree Fahrenheit | degree Celsius (C) | tC=(tF-32)/1.8 |

* From ASTM publication E380-89a, Standard Practice for Use of the International System of Units (SI) The Modernized Metric System.

(1/31/92)R136

Standard Modifications

109-1.03 SCOPE OF PAYMENT.  Delete the last sentence of the fourth paragraph.  (5/7/91)M33

Special Provisions

109-1.05  COMPENSATION FOR EXTRA WORK.  Under 3, Equipment, add the following to the second paragraph:  The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the "O" Zone.  (9/1/89)R14a

109-1.06  PROGRESS PAYMENTS.  Add the following:  Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  This retainage may be released by the Engineer upon receipt of current schedules from the Contractor.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments.  This retainage will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(9/21/92)R137a

109-1.07  PAYMENT FOR MATERIALS ON HAND.  Add the following:  The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska only, at a site approved by the Engineer.  (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01  DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs) as defined in title 49, Code of Federal Regulations (CFR), Part 23 with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds.  The Contractor shall not, nor shall subcontractors or others associated with this contract, discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02  INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 23.

120-1.03  ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section shall be considered a material breach of contract.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04  DEFINITIONS AND TERMS.

1.	Ad Hoc Dealer.  A firm established for the purpose of supplying materials for a particular project or a particular Contractor.

2.	Commercially Useful Function.  The execution of a contract or a distinct element of work under a contract by the firm actually performing, controlling, managing, and supervising the work involved.  See Subsection 120-3.03 Item 3. for criteria.

3.	Disadvantaged Business Enterprise.  A small business concern which is owned and controlled by one or more socially and economically disadvantaged individuals and has been certified as such by the Department of Transportation and Public Facilities in accordance with 49 CFR, Part 23.

4.	Disadvantaged Business Enterprise Utilization Goal.  The percent of work that is specified in the contract to be performed by certified DBEs.

5.	Good Faith Effort.  The affirmative action measures taken by a Contractor to meet the Disadvantaged Business Enterprise Program's objectives and goals for a specific project.

6.	Manufacturer.  An established firm that changes the shape, form or composition of original material in some way and then provides that altered material to the general public or the industry at large on a regular basis.

7.	Regular Dealer.  An established firm that supplies one or more materials to the general public or the industry at large on a regular basis.

8.	Supplier.  A 'Regular Dealer' or an 'Ad Hoc Dealer' that provides material in an unaltered state that becomes a part of the permanent work.

120-2.01  UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total contract amount.  Measurement of attainment of this goal will be used on the actual amount of money received by the DBEs for commercially useful work on this project.

A bidder must demonstrate the ability to meet the DBE Utilization Goal in order to be eligible for award of this contract.

120-3.01  DETERMINATION OF COMPLIANCE.

1.	Phase I - Bid and Award.  In addition to bid submission requirements, the apparent low bidder must demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the 25A325C contains less DBE participation than is required to meet the goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) must be submitted.  If the Good Faith Effort is deemed sufficient, an amended bid schedule showing the revised DBE Utilization Goal will be issued with the award documents.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, failure to document sufficient Good Faith Effort will result in the bid being declared nonresponsive.

2.	Phase II - Construction.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The work items and creditable dollar amounts shown for a DBE firm and the DBE Utilization Report (Form 25A325C) must be included in any subcontract with that firm, or prior written approval for replacement of the DBE must have been granted, before the subcontract can be approved by the Department.

120-3.02  GOOD FAITH EFFORT.  The bidder must demonstrate that all reasonable efforts have been made to include DBEs in the contract at a level at least equal to the goal established for the contract.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the contract goal, has demonstrated sufficient Good Faith Effort.  Criteria (1-7) will be utilized to evaluate any request from the Contractor for a reduction in the goal due to the default of a DBE and the Contractor's subsequent inability to obtain additional DBE participation despite Good Faith Effort to do so.

1.	Consideration of all subcontractable items.

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification (in writing or by personal contact) to all appropriate DBEs in a timely manner of the bidder's/Contractor's interest in securing the DBE's participation in the prosecution of the work.  Each contact with the DBE must be logged on a "Contact Report" (Form 25A321A).

4.	Meaningful communication with DBEs for specific participation.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about requirements of the contract.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether they were interested in bidding.  Documentation of follow-up contacts must be logged on the "Contact Report" (Form 25A321A).  (See item no. 3 above.)

8.	Advertise for specific DBE participation in appropriate general circulation media, trade association publications, and minority-focus media.  Publication should be for at least 5 consecutive days commencing at least 20 days before the bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

120-3.03  DBE CREDIT.  In order for the work of the DBE to be credited toward the DBE Utilization Goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE must be certified by the Department.  The DBE must be certified at the time of:

a.	Listing on the "DBE Utilization Report" (Form 25A325C) submitted prior to award, and

b.	The Engineer's approval of the subcontract.

c.	Issuance of a purchase order by the Contractor to a DBE manufacturer, regular dealer, or ad hoc dealer.

Should a DBE performing a Commercially Useful Function become decertified during the term of the subcontract or purchase order for reasons beyond the control of and without the fault or neglect of the Contractor, the work remaining under the subcontract or purchase order may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval, the Contractor shall have the option of:

a.	Withdrawing the subcontract from consideration and expending Good Faith Effort to replace the subcontract with one from a currently certified DBE, or

b.	Having the subcontract for the decertified firm approved.  In this case, the work of the decertified firm would not be credited toward the DBE Utilization Goal.  The Contractor would also be required to submit such additional DBE participation as may be necessary to meet the DBE Utilization Goal or demonstrate Good Faith Effort.

2.	The DBE may perform work in categories for which it is not certified, but only that work performed in the certified categories will be credited toward the DBE Utilization Goal.

3.	The DBE must perform a Commercially Useful Function.  The following criteria will be used by the Engineer to determine if work will be considered Commercially Useful.

a.	The work performed must be necessary and useful work required for the execution of the contract.

b.	The scope of work must be distinct and identifiable.

c.	The work must be performed, controlled, managed, and supervised by the certified DBE.  The DBE must personally supervise the work on site or have an on-site representative, superintendent, or foreman responsible for the work.

d.	The DBE must use their own staff, employees, and equipment for the execution of the work, except as noted in subparagraph e., below.

e.	The manner in which the work is sublet or performed must conform to standard industry practice.  The goods or services must have a market outside of the DBE program and shall not represent a superfluous step in the contracting or purchasing process.

f.	The cost of the goods or services must be reasonable and competitive with the cost of the goods or services outside the DBE program.

g.	All subcontract work, with the exception of truck hauling, must be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE must control all business administration, accounting, billing, and payment transactions.  The prime Contractor shall not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420 (b), inspect the offices of the DBE and to audit the records of the DBE to assure compliance.

i.	If two-party checks are issued by the Contractor to a subcontractor, regular dealer, ad hoc dealer, manufacturer, and/or the employees or suppliers to such firms; the Engineer must be notified in writing in advance.

j.	A DBE trucker must own or have a lease of at least twelve months for two or more trucks, at least one of which must be working on this project.  For all trucks operated by owner-operators, the DBE must maintain all required records.

4.	The Contractor must provide proof of the actual monies paid for the qualifying goods and services provided by DBEs.  The Contractor will receive credit for the commercially useful work performed by DBEs toward the DBE Utilization Goal as provided in this section for portion of the funds actually paid to the certified DBEs.  Contractor's are encouraged to contact the Engineer in advance of the prosecution of the DBE's work if they have any questions about the work qualifying for participation.

Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE whether or not the DBE has been paid separately for the goods or services.

If the quantity of work of a bid item which involves a DBE is reduced, the DBE Utilization Goal will be adjusted by Change Order.

120-3.04  DEFAULT OF DBE.  In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.  The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs as necessary to assure that the DBE Utilization Goal is met.  In the event that the Contractor cannot obtain additional DBE participation, the Contractor shall submit proof of their Good Faith Effort in accordance with the provisions of Subsection 120-3.02, Good Faith Effort.  The Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, all of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find additional DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with 120-3.02, Good Faith Effort.

120-4.01  METHOD OF MEASUREMENT.  The Contractor shall be entitled to count toward the DBE Utilization Goal those monies allowed by the Engineer in 120-3.03.04 as actually paid to certified DBE firms for Commercially Useful work performed in the categories for which the DBE firm is certified.  Credit will only be allowed for Commercially Useful work.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	If the prime Contractor is a certified DBE, then the Contractor may be credited for up to but not to exceed the amount of the DBE Utilization goal.  The work of a DBE prime Contractor in excess of the DBE Utilization Goal will not be credited when calculating any incentive paid under subsection 120-5.01, Basis of Payment.

2.	Credit for a DBE joint venture partner is limited to the percent of the DBE's joint venture participation.  A DBE joint venture partner must be responsible for a clearly defined portion of the work to be performed in addition to satisfying requirements for ownership and control.

3.	Credit for work by DBE subcontractors and manufacturers is 100 percent.

4.	Permanent materials furnished by a Regular DBE Dealer are credited at 60 percent of their value.  The value will be the actual cost paid but will not exceed the bid price for the item.

5.	Credit for reasonable fees paid by the Contractor to DBE Ad Hoc Dealers are limited to that portion of the value of the fees for services rendered by the DBE Ad Hoc Dealers that help the Contractor obtain needed supplies, personnel, materials or equipment to perform the work.  Such services and fees would include but are not limited to the following:

a.	The fees charged for the delivery of supplies or permanent materials necessary for the prosecution of the work but not any part of the actual value of the supplies or permanent materials themselves (e.g. drayage services, expediting/freight consolidation).

b.	Agent's fee for providing contractually required bonding or insurance but not any portion of the value of the bonds or policies.

120-5.01  BASIS OF PAYMENT.  Payment for the work necessary to meet the specified DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Payment for the work necessary to exceed the originally specified DBE Utilization Goal will be paid in the form of an incentive as follows:

1.	Ten percent of the Total Authorized DBE Participation by non-trucking subcontractors which exceeds the DBE Utilization Goal will be paid, but not to exceed $100,000 or two percent of the total contract amount, whichever is less.

2.	The utilization of DBE prime Contractors, Regular DBE Dealers, DBE Manufacturers, DBE trucking subcontractors, and DBE Ad Hoc Dealers will only count toward meeting the DBE Utilization Goal.  No credit for their participation in excess of the original DBE Utilization Goal will be considered in calculating the amount of the incentive.

3.	No incentive will be paid for exceeding a DBE Utilization Goal that has been adjusted for Good Faith Effort as a condition of award per section 120-2.01, Utilization Goal, until the originally specified DBE Utilization Goal has been exceeded.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled, or fails to submit required DBE documentation, retainage may be withheld from progress payments.  The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive.

If the Contractor fails to meet the DBE Utilization Goal (as adjusted), payments will be reduced as a disincentive.  The amount of the disincentive shall be equal to 50 percent of the difference between the DBE Utilization Goal expressed in dollars and the Total Authorized DBE Participation as determined by the Engineer per subsection 120-3.03, Item 4.

Payment of the incentive will be made on the semi-final or final estimate.  The disincentive will be withheld in the form of retainage during the course of the project.  If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the department within 30 days of being billed for the amount due.

A change order is not required for DBE adjustment, the Notice to Proceed shall constitute the notice required to initiate this item.  (12/8/92)R166

Payment or Deduction will be made under:

Pay Item No.	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent Sum

(5/5/89)S33

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-2.06  DISPOSAL.  Delete the fourth paragraph and substitute the following:  Vegetation and clearing debris may be placed in the roadway embankment slope flattening area.  Debris shall be covered with a minimum of four feet of selected material .  If placed below high tide level, it shall be covered with selected material prior to the tide rising to prevent it from floating free.

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01  DESCRIPTION.  Add the following:  This work shall also include the removal and disposal of the existing Tidewater Slough Bridge.

The existing Tidewater Slough Bridge, No. 640, is a two span composite concrete and steel structure approximately 123 feet long by 30 feet wide.  The deck is reinforced concrete with a concrete curb and two steel tube rail system, supported by five lines of steel stringers.  The abutments and pier are reinforced concrete on concrete filled pipe piles.

202-2.01  GENERAL.  Add the following:  Waste concrete from the Tidewater Slough Bridge may be placed in the embankment provided that there is a minimum cover of 4 feet to finished roadway surface.  The concrete fragments shall be placed in layers not exceeding three feet in thickness.  They shall be distributed by blading or dozing in a manner such that voids, pockets, and bridging will be reduced to a minimum.  The intervening spaces shall be filled with selected material to form a dense, well compacted embankment.  The location of the disposal areas shall be clearly identified on the as-built plans.

The use of explosives to remove portions of the existing Tidewater Slough Bridge is not prohibited .  If the Contractor elects to use any explosives for  removal, he shall submit in writing, two weeks prior to blasting, the detailed plan to the Engineer for analysis and to determine if permits are required.  If permits are required, the Department will complete the permit applications and submit them directly to the agencies on the Contractor's behalf.  It is anticipated that a minimum of 30 days will be required by the agencies to process the applications.  The receipt and analysis by the Engineer of the Contractor's plan shall not constitute approval for implementation nor the accuracy of its implementation.

202-2.04  REMOVAL OF PAVEMENT, SIDEWALKS, CURBS, ETC.  Add the following:  Pavement removed may be used in the construction of the embankment.   All reused asphalt pavement shall be buried so as not to be exposed at the completed surface of the embankment.

For disposal of removed asphalt not used in the embankment, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by the DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 563-6529.

A DEC approved site for disposal of removed asphalt is available at no charge to the Contractor at the Hiland Road Solid Waste Facility.  In order to use this site, the Contractor shall meet the following requirements:

1.	All dumping shall be coordinated through the Eagle River Street Maintenance office at 694-3487.

2.	Leveling course material may be included with removed asphalt if it does not exceed 30 percent of the total volume delivered.

3.	For quantities over 500 tons, the Contractor shall stockpile materials in a manner acceptable to the Municipality of Anchorage.

4.	Asphalt pieces shall be six inches or less in size.

(6/1/92)R84a

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-2.01  COMMON EXCAVATION.  Add the following:  That strata or layer of soil laying above the rock excavation commonly referred to as "overburden" shall be paid for as Common Excavation.  Common excavation will apply to areas where the overburden thickness is greater than 6 inches after clearing and grubbing.  For thicknesses less than 6 inches, the overburden layer will be subsidiary to the rock excavation quantity.

Standard Modifications

203-2.05  BORROW.  Add the following:  Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.  (5/12/89)M12

Special Provisions

203-3.02  EMBANKMENT CONSTRUCTION.  Add the following to the sixth paragraph:  Embankment may be placed over seasonally frozen mud flats, as long as all ice floes and chunks are removed prior to placement of embankment materials.

Standard Modifications

203-3.02  EMBANKMENT CONSTRUCTION.  On page 97, delete the 5th paragraph and substitute the following:  All embankments shall be constructed with moisture and density control unless the Engineer determines that such controls are not feasible.  (5/7/91)M35

Special Provisions

203-3.02  EMBANKMENT CONSTRUCTION.  Add the following:  Embankment materials placed in tidal zones shall be placed when the tide is at a level where none of the material being placed is submerged.

203-3.03  CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Add the following:  All embankment within 20 feet of a bridge abutment shall be compacted full width to not less than 100 percent of the maximum density.  All material used within this zone shall be graded to pass the 3-inch sieve.  (10/1/91)R113

203-3.07 BLASTING REQUIREMENTS FOR EXCAVATION IN ROCK:  Add the following subsection:  Periodic geotechnical field inspections will be conducted by representatives of the Department as the backslopes of each cut are exposed; and when unfavorable geologic structure anomalies are encountered, specific recommendations on stabilization will be made.  In the event the Contractor is required by the Engineer to revise a slope which has already been drilled and blasted according to specifications, the Contractor shall perform this work in accordance with Subsection 109-1.05, Compensation for Extra Work.

Blasting within 1000 feet of the railroad tracks will require that the tracks be closed to rail traffic.  Blasting shall be scheduled to coincide with track closures allowed by the Alaska Railroad.  Track closures are at the discretion of the Alaska Railroad Corporation, however, at a minimum the following number of closures and closure durations will be provided:

| Winter Months (Oct 1st to May 15th) | Summer Months (May 16th to Sept 30th) |
| --- | --- |
| four, 9-hour closures per week* | two, 9-hour closures per week* |

*	A minimum of 2 hours during daylight times will be included in the 9-hour closures.  The 9-hour closures shall be considered an average 9 hour period and may be shorter or longer depending on the actual train schedule.

The Contractor shall attend daily meetings with the Railroad's Field Representative and the Department to determine track closure times.

In accordance with subsection 103-1.01, Consideration of Proposals, the Contractor shall submit a rock excavation plan within 5 days following bid opening.  Two weeks prior to any drilling or blasting, the Contractor shall  submit to the Engineer a specific blasting plan and, if necessary, a revised rock excavation plan.

The blasting plan shall include the following specific information:

1.	drill hole diameter

2.	drill pattern and spacing diagram

3.	proposed delay sequence of the blast holes

4.	explosive per hole and per delay (lb.)

5.	types of explosives being employed

6.	powder factor

Review of the drilling, blasting and excavation procedures by the Engineer shall not relieve the Contractor of his responsibility for the accuracy and adequacy of the plan for obtaining adequate breakage, using proper detonation procedures and following proper safety procedures prior to and after the blast.

Due to the proximity of the Alaska Railroad embankment to the major rock cut and the need to protect the railroad from blasting damage, the Contractor shall retain the services of a Blasting Specialist who is recognized as an expert in the field of drilling and controlled blasting and who derives his primary source of income from providing specialized blasting and/or consulting services.  The Blasting Specialist shall not be an employee of the Contractor, explosives manufacturer or explosives distributor. 

Five working days prior to  the preconstruction conference, the Contractor shall submit a resume of the  credentials of the Blasting Specialist.  The resume shall include a list of at least 5 major rock excavation projects involving controlled blasting on which the Blasting Specialist has worked.  The list shall contain a description of the projects, details of the blast plans and modifications made during the project.  The list shall also contain the names and telephone numbers of project owners with sufficient knowledge of the projects to verify the submitted information.  The Blasting Specialist shall be approved by the Engineer prior to the beginning of any drilling or blasting work, and then be available on the job site prior to excavation of the major cut, and at other times as required.

The Contractor may adopt methods of control blasting and excavation which vary from those required herein, provided short demonstration sections are first used to prove the acceptability of such methods to the satisfaction of the Engineer.

If in the opinion of the Engineer, the methods of excavation required herein or adopted by the Contractor are unsatisfactory in that they result in excessive rock throw, or do not produce a uniform slope and shear face within the neatlines specified, the Contractor shall adopt revised methods, by drilling, blasting, and excavating short sections until a technique is developed that will produce the acceptable results.

The Contractor shall provide protection to railroad facilities as outlined in Subsection 107-1.08, Railway-Highway Provisions.

No blasting shall be accomplished until after the Anchorage Telephone Utility fiber optic telephone cable is operating within the new innerduct.

The Contractor shall provide protection to Chugach Electric Association facilities.  When in the opinion of the Engineer a blast could possibly damage an electrical facility, the Contractor shall notify Chugach Electric Association 24 hours in advance of the exact time the blast will occur.  Should the electrical service be disrupted, damages will be assessed the Contractor for each hour that the electrical service is interrupted.

Drill hole conditions may vary from wet or filled with water to a dry condition.  The Contractor will be required to use whatever type of explosive and/or accessories necessary to accomplish the specified result.

Storage and handling of explosives shall be in accordance with Subsection 107-1.10, Use of Explosives.  All blasting caps and all other explosives used on this project shall be one year or less in age.  To ensure the accuracy of firing times of blasting caps, each cap period shall come from one lot number.  Mixing of lot numbers for any one cap period is prohibited.  No blasting products will be allowed on the job site if the date codes are missing.

All rock that is loose, hanging, or creating a dangerous situation shall be removed during or upon completion of excavation as an integral sequence as each lift is excavated.  Drilling of the next lift will not be allowed until this work is completed.

Material outside the planned neatline slopes which is unstable and constitutes potential slides in the opinion of the Engineer shall be excavated and removed.  Such material shall be used in the construction of the embankment or disposed of as directed by the Engineer.  The removal and disposal of slide and slipout material will be paid for at the appropriate contract unit price for Rock Excavation or Common Excavation if determined not to be the fault of the Contractor's methods.

For all cuts over 10 feet in depth, the Contractor shall use pre-shearing along the lines of the cut slope face.  This depth may be varied if field experience shows such variance will yield acceptable results.

Overburden stripping as shown on the plans shall be done before the associated pre-shear holes are drilled.

Material remaining 8 inches or more inside neat line rock slopes will be removed by pre-shearing techniques or other methods approved by the Engineer unless specifically exempted for aesthetic, geological, or safety reasons by the Engineer.

Pre-Shear Blasting:

"Pre-shearing" shall consist of drilling holes on the plane of the final cut slope and loading each hole with a well distributed explosive charge and firing the holes simultaneously to create a crack along the plane of the final cut slope.  The detonation of the pre-shear line must be before the detonation of all other blasting in the cut.  Production holes will be detonated next and buffer holes will be detonated last.

Spacing of pre-shear blast holes shall be initially set at 24 inches center to center.  If experience shows that a wider spacing will give acceptable results then the Contractor, with the approval of the Engineer, will be permitted to utilize that spacing.  The pre-shear holes shall be not less than 2.5 inches and not more than 3 inches in diameter, the length for any individual lift shall not exceed 40 feet.  Only standard explosives manufactured specifically for pre-shearing shall be used in pre-shear holes, unless otherwise approved by the Engineer.  Bulk ammonium nitrate and fuel oil (ANFO) type explosives shall not be used in pre-shear holes.  All pre-shear blast holes shall be stemmed full depth with sand or other dry angular, granular material, all of which passes a 3/8 inch sieve.

If fractional portions of standard explosive cartridges are used, they shall be firmly affixed to the detonating cord in such a manner that the cartridges will not slip down the detonating cord nor bridge across the hole.  Spacing of fractional cartridges along the length of the detonating cord shall not exceed 30 inches center to center and shall be adjusted to give the desired result.

All drilling equipment used to drill the pre-shear holes shall have mechanical devices affixed to that equipment to accurately determine the angle at which the drill steel enters the rock.  Pre-shear hole drilling will not be permitted if these devices are either missing or inoperative.

When the cut height requires more than one lift, a maximum 2 foot offset between lifts shall be permitted to allow for drill equipment clearances.  The Contractor shall begin the pre-shear hole drilling at a point which will allow for necessary offsets and shall adjust, at the start of lower lifts, to compensate for any drill hole drift which may have occurred in the upper lifts.  Payment for the additional excavation volume resulting from the allowed 2 foot offsets shall be at the contract unit price for rock excavation.

Where backbreak becomes a definite problem in the opinion of the Engineer, guide holes shall be drilled between the controlled blast drill holes.  These shall be of the same diameter and in the same plane as the pre-shear blast holes and shall not exceed 10 feet in depth.  They shall remain unloaded.

Fluff Blasting:

Fluff blasting shall consist of drilling and shooting the rock area to a depth of at least 6 feet beneath profile grade and back of ditch to back of ditch, resulting in a fractured or broken rock foundation.  It is anticipated that, in comparison with production blasting, the center to center blast hole spacing will be closer and the powder load in each hole will be restricted to the bottom of the hole to minimize rifling.  This procedure will effectively provide a stable interlock between the embankment material and the foundation material.  This procedure will also facilitate drainage through the foundation material rather than drainage along the bedrock-embankment interface.  The Contractor shall have a backhoe on site and available to enable the Engineer to verify the effectiveness of the fluff blasting.

Buffer Blasting:

Buffer holes shall be drilled approximately 3 feet out from the pre-shear holes and spaced 3 to 5 feet center to center.  These holes will be drilled parallel to the final cut slope and the loads shall not exceed 50 percent of the average explosive loads in the nearest production holes.  Detonation of the buffer holes shall be on a delay sequence toward a free face and shall follow detonation of the production holes.

Production Blasting:

In production blasting the amount of explosive per delay shall not exceed 500 pounds.  This limit may be reduced or increased if ordered by the Engineer when the blast is in a position to damage equipment, utilities, or if other circumstances require a change.  Production blast holes shall not be drilled closer than 6 feet to the pre-shear line.  Where more than one lift is required, production holes shall not be drilled to an elevation lower than the pre-shear holes.  Detonation of production holes shall be on a delay sequence toward a free face.  Stemming material used in production holes shall be sand or other dry angular granular material, all of which passes a 3/8 inch sieve.

203-3.08  ROCK STABILIZATION.  Add the following subsection:  Rock bolts of the specified lengths will be installed where directed by the Engineer.  These bolts shall be installed in such a manner as to exert a permanent normal force across potential failure planes.

All rock bolts to be installed on this project including anchorages, corrosion proofing and other appurtenances shall be products of a manufacturer regularly engaged in the manufacture of rock bolts.  Bolts shall be fabricated from deformed bars not less than 1-3/8 inches in diameter.

Anchorage shall be epoxy, polyester resins or cement grout.  Tension shall be transferred to the outer rock by means of grout, bearing plate, washer and nut or by epoxy or polyester resin within the hole.

If used, bearing plates shall be in uniform contact with the rock surface.  If the rock face is not perpendicular to the axis of the bolt, or the rock under the bearing plate is not sound, a bearing pad approved by the Engineer shall be constructed so that the bolt is not bent when the tension is applied.

All sections of the bolts and accessories necessary to the function of the bolts shall be fully corrosion protected.

Grouts, epoxies or polyester resins shall be proven, non-shrink materials capable of permanently developing the bond and internal strengths necessary for the tensioning required on this project. Fondu cement shall not be used.  Epoxy or polyester resins in cartridge form shall be approved by the Engineer.

Rock bolts shall be tensioned to 25,000 pound minimum.  When external nuts are used to transfer this tension to the surface rock, the load shall be held for 10 minutes before tightening the nut.  Load/extension measurement will be made during tensioning.  When epoxy or polyester resins are used to transfer the tension to the outer rock, the load shall be held sufficiently long to allow hardening of the material.  Load/extension measurements shall be made to assure the load is transferred to the rock upon release of the tensioning device.

During tensioning the load shall be held for at least 10 minutes and the extension of the bolt shall not exceed the elastic strain of the bolt by more than 20 percent.  If a bolt fails these tests, it shall be replaced or an additional bolt shall be installed in a separate hole.

The hydraulic jack and pressure gauge used for tensioning shall be calibrated by a registered calibration agency a maximum of one month prior to the tensioning operation and a copy of the calibration certificate shall be shown to the Engineer before tensioning begins.

The installation, corrosion protection, and the tensioning shall be carried out according to the manufacturer's specifications.

203-3.09  HORIZONTAL DRAIN HOLES.  Add the following subsection:  Drain holes to relieve water conditions in rock backslopes may be required.  Minimum hole diameter shall be three inches and lengths shall not exceed 40 feet.  Location and slope of horizontal drains will depend on conditions encountered and as directed by the Engineer, but will not exceed the limits of the equipment in use on the project for pre-shear or production holes.  Holes shall be flushed with water upon completion to remove drill fines.

203-4.01  METHOD OF MEASUREMENT.  Add the following:  No deduction from the excavation quantities will be made for pavement removed under Item 202(2), Removal of Pavement.

Areas of instability or potential slides ordered removed by the Engineer will be determined by resectioning.

Horizontal Drain Holes and Rock Bolts will be measured by the linear foot.

203-5.01  BASIS OF PAYMENT.  Add the following:  Grading to pass a 3-inch sieve and compacting to 100 percent the material placed within 20 feet of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(6A), Borrow, Type A.  (10/1/91)R113

Pre-shear blasting, fluff blasting, buffer blasting and production blasting will not be paid for directly, but will be subsidiary to Item 203(2), Rock Excavation.

Standard Modifications

203-5.01  BASIS OF PAYMENT.  Change Pay Items 203(5), (6) and (7) to read:  Borrow, Type __.

Add the following:  When more than one type of borrow is specified, letter suffixes A, B, or C will be included within the parentheses of the item number in order to differentiate between the different Borrow types.  (5/12/89)M12

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

203(12)	Horizontal Drain Holes	Linear Foot

203(16)	Rock Bolt	Linear Foot

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01 MATERIALS.  Delete this subsection in its entirety and substitute the following:  Bedding and backfill materials shall meet the requirements for Selected Material, Type A, as specified in Subsection 703-2.07, Selected Material.  Pipe bedding and backfill material shall also pass the 3-inch sieve.

Selected Material, Type A pipe backfill shall extend a minimum of 12 inches above the pipe.  Excavated native material shall be utilized for the remainder of the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07, Selected Material.  Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material.  All suitable material from structure excavation shall be used for bedding and backfill prior to using material from another source.

204-3.01  CONSTRUCTION REQUIREMENTS.  Add the following to the third paragraph:  Native material may be utilized for electrical conduit bedding and backfill outside the pavement structure if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07, Selected Material.  Compaction may be as approved by the Engineer.

(3/23/93)R25

SECTION 205

EXCAVATION, BACKFILL AND

FOUNDATION FILL FOR STRUCTURES

Special Provisions

205-5.01  BASIS OF PAYMENT.  Add the following:  There will be no excavation for structures paid for under this section.  Excavation for structures will be subsidiary to Item 202(1), Removal of Structures and Obstructions.

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01  MATERIALS.  Delete the last two sentences of the first paragraph and substitute the following:  The gradation of base course material for use under asphalt concrete pavement shall conform to the requirements for Grading D-1.  The gradation of base course material for use as a surface course for the unpaved portions of driveways shall be Grading E-1.  (10/1/91)R116

Add the following after the first paragraph:  At the Contractor's option, recycled asphalt pavement (RAP) may be substituted for crushed aggregate base course, inch for inch, if the following conditions are met:

1.	RAP shall be crushed or processed to 100 percent by weight passing the 1½-inch sieve and 95 - 100 percent by weight passing the 1-inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| SIEVE | % PASSING BY WEIGHT |
| --- | --- |
| 1 | 100 |
| ¾ | 70-100 |
| _ | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 0-6 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAP.

301-3.01  PLACING.  Add the following:  Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.  (9/1/89)R26

301-3.03  SHAPING AND COMPACTION.  Add the following:  If recycled asphalt pavement is substituted for crushed aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern.  The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 90 psi (+5 psi) and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01  BASIS OF PAYMENT.  Add the following:  If recycled asphalt pavement is substituted for crushed aggregate base course, it will be paid for as Item 301(1), Crushed Aggregate Base Course at the unit price shown on the bid schedule for that item.

Payment for base course material will be made under Item 301(1), Crushed Aggregate Base Course, regardless of the gradation type used.

(6/11/93)R176

Delete Section 401 in its entirety and substitute the following:

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-1.01  DESCRIPTION.  This work consists of the furnishing and mixing of aggregate and asphalt cement at a central mixing plant and the hauling, spreading, and compaction of the asphalt concrete mixture on a previously prepared surface, all as specified in the contract and in reasonably close conformance with the lines, grades and thickness shown on the plans.

401-2.01  COMPOSITION OF MIXTURES.  Mixtures shall be composed of aggregate and asphalt cement combined as specified for the type shown in the contract.  Asphalt Concrete, Type II, shall meet the requirements of ATM T-17, for Class A.

At least 15 calendar days prior to the production of asphalt concrete pavement mix, the Contractor shall submit the following to the Engineer:

1.	Notification that aggregate proposed for the mixture is available for sampling.

2.	A letter stating the proposed gradation for the Trial Job Mix Design, gradations for individual stockpiles, and blend ratio for each aggregate stockpile.  Job Mix Design proposals by the Contractor shall be within the broad band gradations set in Table 703-3.

3.	A minimum of three 1-gallon samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a temperature viscosity curve for the asphalt cement.

4.	A 1/2 pint sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

The Contractor shall accompany the Engineer during sampling, and shall furnish all the assistance needed to assure that the Engineer obtains representative samples.

From this information, the Engineer will establish the Job Mix Design which shall become a part of the contract and shall be followed unless modified in writing.  Job Mix Design test results will be available within 7 working days after submittal.

The Job Mix Design shall be determined by and shall conform to the requirements of ATM T-17.

Changes in the Job Mix Design warranted by changes in the aggregate or sources of aggregate shall be submitted by the Contractor in the same manner as the original submittal.

If the mixture is obtained from a commercial source, the Contractor shall submit a certified statement of its components and their proportions as outlined in these specifications for approval as the Job Mix Design.

The full tolerances specified below shall be applied to the approved Job Mix Design gradations and shall not be limited to the broad bands listed in Table 703-3.  Tolerances shall not be applied to the largest specified screen.

| Sieve Size or Item | Tolerance (Percent Passing) |
| --- | --- |
| 3/4 inch | +/- 8% |
| 1/2 inch | +/- 7% |
| 3/8 inch | +/- 7% |
| No. 4 | +/- 7% |
| No. 8 | +/- 6% |
| No. 16 | +/- 6% |
| No. 30 | +/- 5% |
| No. 50 | +/- 4% |
| No. 100 | +/- 3% |
| No. 200 | +/- 3% |
| Asphalt % | +/- 0.4% |

401-2.02  AGGREGATES.  Aggregates shall conform to the requirements of Subsection 703-2.04.

401-2.03  FILLER. Filler shall conform to the requirements of AASHTO M 17.

401-2.04  ASPHALT CEMENT.  The grade of asphalt cement will be specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702, Asphalt Materials.  Asphalt cement may be conditionally accepted at the source.  If the cement is to be conditionally accepted at the source, the Contractor shall provide a manufacturer's certificate of compliance in accordance with Subsection 106-1.05 and test results of the applicable quality requirements of Section 702 before the cement is shipped.

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at 275 degrees Fahrenheit) of the asphalt cement used on the project changes from the viscosity of the cement supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended while a new Job Mix Design proposal is submitted for approval.

401-2.05  ANTI-STRIP ADDITIVES.  Anti-strip agents used shall be an approved type in the proportions determined by ATM T-14 and included in the approved Job Mix Design.

401-2.06  QUALITY CONTROL AND ACCEPTANCE.

1.	Process Control by Contractor.  It is understood that the Contractor is responsible for furnishing the sampling and testing of materials for process quality control, including screening, crushing, blending, and stockpiling of the aggregate, production and laydown of the mixture, and monitoring of compaction.

At the site, the Contractor shall furnish a field laboratory for process control testing.  The contractor-furnished laboratory shall be shared with the Department for concurrent testing.

A Crushing Control Plan shall be submitted at least 15 working days prior to the preconstruction conference.  The plan shall include a proposed testing frequency for aggregate gradation.  Abbreviated testing for process control of gradation shall be in accordance with Alaska Standard Practice SP-9.  Such sampling and testing will be coordinated with the Department and split samples are to be provided to the Department.

A Paving and Plant Control Plan shall be submitted at a pre-paving meeting to be held a minimum of 5 working days prior to initiating paving operations.  The Paving and Plant Control Plan shall outline the steps taken to assure product consistency and to minimize segregation and premature cooling of mixtures.  This plan shall include a proposed testing frequency for gradation, asphalt content, and compaction.  It shall also include a plan for the handling of or elimination of the wings on the paver hopper to prevent dumping and placement of cooled mix onto the roadway.

2.	Acceptance Testing by Department.  The Department will perform sampling and testing for acceptance of the work in accordance with the Department's testing frequency guide and standard acceptance test methods specified below.  Such testing may be done concurrently with the Contractor's process control testing.  Acceptance test results will be available to the Contractor as soon as possible upon their completion.

Sampling for the determination of aggregate gradation will be from the aggregate cold feed, individual hot bins, or from the combined aggregate just prior to the introduction of the asphalt cement.  All aggregate samples will be split and the second half made available to the Contractor.

Acceptance testing for asphalt cement content will be determined by ATM T-16, ATM T-23 or AASHTO T 164.  Sampling for the determination of asphalt cement content will be from the mixture at the time of placement.

Samples taken for determination of density compliance shall be taken from the finished mat after final rolling.  Acceptance testing for field density will be determined in accordance with ATM T-22.

3.	Unacceptable Work or Material.  Any mixture which is contaminated, segregated, or which does not otherwise conform to the specifications will be rejected and replaced at no additional cost to the Department with conforming material in accordance with Subsection 105-1.11, Removal of Unacceptable and Unauthorized Work.  All costs associated with removal and replacement of unacceptable mixture shall be borne by the Contractor.  At the discretion of the Engineer, unacceptable pavement may be overlaid with acceptable pavement at no additional cost to the Department.

CONSTRUCTION REQUIREMENTS

401-3.01  WEATHER LIMITATIONS.  The mixture shall not be placed on a wet surface, or on an unstable roadbed, when the base material is frozen, or when weather conditions prevent the proper handling, compacting, or finishing of the mixture.  No mixture shall be placed when the surface upon which the pavement is to be placed is at or below 35 degrees Fahrenheit.

401-3.02  BITUMINOUS MIXING PLANTS.  Mixing plants shall conform to AASHTO M 156.

Proportioning (batch) scales shall not be used for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

401-3.03  HAULING EQUIPMENT.  Trucks used for hauling mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime solution or other manufactured asphalt release agent included in the Department's Approved Products List.  Diesel or fuel oil shall not be used.  Each truck shall have a cover of canvas or other suitable material of such size as to protect the mixture from the weather, when required, so that the mixture will be delivered on the road at the proper temperature.

401-3.04  ASPHALT PAVERS.  Asphalt pavers shall be self-propelled units, provided with a heated vibratory screed and equipped with a paver control system which shall automatically control the laying of the mixture to specified transverse slope and specified longitudinal grade.  The paver control system shall be automatically actuated by the use of a mobile string line, ski, or other approved grade follower.  The length of the ski, mobile string line or other device shall be at least 30 feet in length.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation.  The hopper shall be equipped with a distribution system to place the mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Auger extensions shall be within 1.5 feet of the gates.

Extendible wings may be permitted for tapers, guardrail widening and approaches.

The use of a pickup machine to transfer the mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collection of the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any other detrimental effects are observed.

401-3.05  ROLLERS.  Rollers shall be of the steel wheel and pneumatic tire type, self-propelled, in good condition, capable of reversing without backlash, and operated at speeds slow enough to avoid displacement of the mixture.  The number and weight of the rollers shall be sufficient to compact the mixture to the required density and surface smoothness while it is still in a workable condition, and be capable of maintaining the pace of the paving operation.  Specific roller requirements for construction of density "control strips" are further described in Subsection 401-3.12, Compaction.  The use of equipment which results in crushing of the aggregate will not be permitted.

401-3.06  PREPARATION OF EXISTING SURFACE.  When the surface of the existing pavement or old base is irregular, it shall be brought to uniform grade and cross section, as directed.

If determined necessary, the existing surface shall be cleaned of loose material by means of sweeping with a power broom, supplemented by hand sweeping as required.

Contact surfaces of curbing, gutters, manholes, and other structures shall be coated with a thin, uniform coating of prime or tack coat material prior to the asphalt concrete mixture being placed against them.

Surfaces which have received a prime or tack coat shall be allowed to cure, as directed, prior to placement of asphalt concrete mixture.  Surfaces which have received an emulsion tack coat shall be allowed to break prior to placement of asphalt concrete mixtures.

401-3.07  PREPARATION OF ASPHALT CEMENT.  A continuous supply of asphalt cement shall be supplied to the mixer at a uniform temperature, within 25 degrees Fahrenheit of the Job Mix Design mixing temperature.

401-3.08  PREPARATION OF AGGREGATES.  The aggregate for the mixture shall be heated and dried to a temperature compatible with the mix requirements herein specified.  Flames used for drying and heating shall be properly adjusted to avoid damage to the aggregate and to avoid soot or unburned fuel on the aggregate.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5 percent (by total weight of mix), as determined by ATM T-25.

401-3.09  MIXING.  The aggregate and asphalt cement shall be combined in the mixer in the amounts required to meet the Job Mix Design.  Anti-stripping additive shall be furnished as required.

The materials shall be mixed until a complete and uniform coating of the particles and a thorough distribution of the asphalt cement throughout the aggregate is obtained.  For batch plants, dry aggregate shall be in motion prior to the addition of asphalt cement.  Wet mixing time shall be determined for each plant and for each type of aggregate used.  The minimum percent of coated particles used to establish the mixing time interval shall be 98 percent using AASHTO T 195.

The temperature of the mixture at the time of mixing shall be as determined by the Job Mix Design.

401-3.10  TEMPORARY STORAGE OF ASPHALT MIXTURE.  Temporary storing or holding of hot mixture in silo type storage bins will be permitted.

All the mixture drawn from the silo type storage bins shall conform to all of the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

401-3.11  SPREADING AND FINISHING.  The mixture shall be laid only upon stable surfaces approved by the Engineer, spread and struck off and compacted to the required thickness.  Asphalt pavers shall be used to distribute the mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 401-3.13, Joints.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impractical, the mixture shall be spread, raked and luted by hand tools.  For such areas the mixture shall be placed to the required compacted thickness.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge drop-off.  When the pavement edge drop-off exceeds 2 inches, shoulder material shall be placed against the pavement edge.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that segment, as defined by the Paving Plan, have been placed and accepted.

Paving shall not begin until all adjacent concrete curb has been poured and cured for 72 hours or until satisfactory concrete strength is achieved.

Asphalt to be placed over bridge membranes shall not be placed until the membrane has cured to the proper state to prevent damage by the overlaying operation.  Vehicles, except the spreader and trucks used for hauling the asphalt overlay mix, shall not be operated on the membrane.  Paving machines used over the membrane waterproofing shall be rubber tired or rubber tracked.   The Contractor shall adhere to the manufacturer's published minimum and maximum temperature limitations for asphalt overlay material.  Steel-wheeled rollers only shall be used to compact the asphalt paving on the bridge decks.  The use of vibratory rollers, with vibrator on, will not be permitted.

401-3.12  COMPACTION.

General.  Immediately after the mixture has been spread, struck off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.  Rolling shall commence as soon as the rolling does not cause undue displacement, cracking or shoving.  Any displacement occurring as a result of the reversing of the direction of a roller, or from other causes, shall be corrected promptly by the use of rakes and addition of fresh mixture when required.  Care shall be exercised in rolling not to displace the line and grade of the mixture.  Rollers shall move at a slow but uniform speed with the drive roll or wheels nearest the paver.

Unless otherwise directed, rolling shall begin at the sides and proceed parallel with the road centerline, each overlapping one-half the roller width, gradually progressing to the crown of the road.  When paving in echelon or abutting a previously placed lane, the longitudinal joint shall be rolled first to provide pinching the material in place.  On super-elevated curves the rolling shall begin at the low side and progress to the high side by overlapping of trips parallel with the centerline.

Along forms, curbs, headers, walls, and other places not accessible to the rollers, the mixture shall be thoroughly compacted with hot hand tampers or with mechanical tampers.  On depressed areas, a trench roller may be used or cleated compression strips may be used under the roller to transmit compression to the depressed area.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

Control by Acceptance Strip.

1.	Control Strips.  A control strip shall be constructed at the start of each course after the plant and equipment are providing a consistent mix, and repeated as ordered whenever:

a.	there is a change in the mix composition,

b.	there is a change in ambient temperature of 30 degrees F or greater, or,

c.	routine tests indicate changes from results found in previous qualifying control strips.

Each control strip shall be constructed with the approved Job Mix Design.  The control strip shall remain in place as a section of the completed work, provided it complies with requirements for gradations, asphalt cement content, adequacy of mixing and line and grade.  It shall be removed and replaced at the Contractor's expense or accepted to remain in place in accordance with Section 105-1.03, Conformity with Plans and Specifications, and a new control strip constructed if it does not meet specification requirements.  Paving operations may not proceed beyond the control strip until the mixture conformance to specifications has been confirmed and production paving is authorized.

Each control strip shall be one lane in width, 300 feet in length and shall be of the depth specified for the pavement course concerned.

Initial or breakdown compaction of a layer of the mixture shall be performed with a 2-axle tandem or a 3-wheel roller weighing at least 12 tons except that approved vibratory compacting equipment may be used for the initial or breakdown compaction if it is operated according to the procedures designated in the approval.

A pass shall be one movement of a roller in either direction.  A coverage shall be as many passes as are necessary to cover the entire width being paved.  Each coverage shall be completed before subsequent coverages are started.

The initial or breakdown compaction shall be followed immediately by intermediate rolling with a pneumatic-tired roller which exerts a tire pressure of at least 80 psi over the tire contact area.  Coverages with a pneumatic-tired roller shall start when the temperature of the mixture is high as practicable and shall be completed while the temperature of the mixture is at or above 160 degrees F.  Intermediate rolling shall be performed with a 2-axle tandem roller when breakdown rolling is performed with a pneumatic roller.

Each layer of mixture shall be additionally compacted, without delay, by a final rolling consisting of not less than one coverage with a steel-tired roller weighing not less than 8 tons.  Compaction of the control strip shall commence as soon as possible after placement of the mixture and be continuous and uniform over the entire control strip.

The following rolling and density testing procedures shall be used on the control strip:

a.	Breakdown rolling.  Thirty-second nuclear density counts shall be taken at three randomly selected locations after each roller coverage at each test site.  Rolling shall continue until there is less than one pound increase in average density per roller coverage.

b.	Intermediate rolling.  Rolling shall continue until at least three complete coverages have been made and there is less than one pound increase in average density per roller coverage.

c.	Finish rolling.  Thirty-second nuclear density counts shall be taken at five randomly selected locations after each roller coverage at each test site.  The average density obtained after the first coverage shall be taken as a new beginning point.  Final rolling shall continue until all roller marks are removed and there is less than one pound increase in average density per roller coverage.

d.	Density standard.  One-minute density counts shall be taken at 10 randomly selected locations to determine the average density of the control strip.  This is the density standard for the project until a new control strip is constructed.  To confirm the adequacy of the compaction of the control strip, seven 8-inch minimum diameter core samples will be taken at randomly selected locations.  The average density of these cores shall be at least 95 percent of the maximum specific gravity (as determined by AASHTO T 209) multiplied by 62.4.

2.	Acceptance Strips.  Acceptance density testing will be accomplished while the pavement is hot enough to permit further densification if such is shown to be necessary.

The pavement courses shall be divided into acceptance strips consisting of not more than 500 tons for the purpose of defining areas represented by each series of density acceptance tests.

The types of rollers used and their relative positions in acceptance strip compaction shall be the Contractor's option, provided that at least 2 coverages of a pneumatic-tired roller having an 80 psi minimum contact pressure are applied.

The density of each acceptance strip will be evaluated based on the results of three tests with a portable nuclear test device performed at randomly selected sites within the acceptance section.  Each test will consist of the average of two one-minute readings with the gauge rotated 90 degrees between readings.  The average density obtained for the three test in each acceptance strip shall be at least 98 percent of the mean density obtained in the approved control strip.  In addition, each individual test value obtained within an acceptance strip shall be at least 95 percent of the mean density of the strip.

If either the average density of the acceptance strip or an individual test value does not meet the density requirements, the Contractor shall continue compactive effort until the required density is obtained.

After the required density has been attained in the acceptance strips, further finish rolling may be necessary to remove roller marks or other surface irregularities and to meet the required surface tolerances.

401-3.13  JOINTS.  Joints shall be made in such manner as to ensure a continuous bond between old and new sections of the course.  All joints shall present the same texture and smoothness as other sections of the course.

A thin tack coat of asphalt cement or emulsion shall be sprayed on all cold joints and allowed to break prior to placing fresh mixture against the joint.

Transverse joints shall be formed by cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.

The longitudinal joints in one layer shall offset those in the layer immediately below by approximately six inches.  However, the joints in the top layer shall be at centerline or lane lines.  Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset not more than one foot.

Pavement that are 1.5 inches or thicker shall be constructed with a modified wedge joint the entire length of the face of the exposed longitudinal joint between adjacent travel lanes.  The taper shall have a maximum horizontal to vertical slope of 3:1 at the bottom and shall be vertical at the top for a height equal to the largest aggregate size.

Improperly formed joints resulting in surface irregularities shall be removed, full depth, replaced with new material, and thoroughly compacted.  Attempting to roll out an improper joint after the material has cooled below 160 degrees Fahrenheit shall not be allowed.  All pavement removal shall be precut to a neat line using a power driven saw.

401-3.14  SURFACE TOLERANCE.  The surface will be tested after final rolling at selected locations using a 10 foot straightedge.  The variation of the surface from the testing edge of the straightedge between any two contacts with the surface shall not exceed 3/16 inch.

401-3.15  PATCHING DEFECTIVE AREAS.  Skin patching will not be permitted.  Defective materials shall be removed for the full thickness of the course.  The pavement shall be cut so that the sides are perpendicular and parallel to the direction of traffic and so that the edges are vertical.  Edges shall be tack coated with asphalt cement or emulsion.  Fresh mixture shall be placed in sufficient quantity so that the finished surface will conform to grade and smoothness requirements.  The mixture shall be compacted to the density specified herein.

401-4.01  METHOD OF MEASUREMENT.  Asphalt concrete pavement and asphalt cement will be measured by the ton or by the square yard in accordance with Section 109.  The tonnage used shall be the weight used in the accepted pavement and no deduction will be made for the weight of asphalt cement and anti-stripping additive in the mixture.

The method of measurement to be used for Asphalt Cement will be limited to one of the following procedures.  The Engineer shall approve in writing the procedure to be used.  The method used initially must be the one used for the duration of the project.

1.	Supplier's invoices minus waste, diversion and left-over.  This method may be used on projects where deliveries are made in tankers and the plant is producing material for one project only.  Tank stickings will be used to compute left-over.  Waste and diversion will be computed in a manner to be determined by the Engineer.

2.	The weight of asphalt cement shall be calculated using the percent of asphalt cement multiplied by the total tonnage represented.  Percent of asphalt cement shall be determined by ATM T-23.

The Engineer may direct at any time that tankers shall be weighed before and after unloading in the presence of the Engineer.  If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

401-5.01  BASIS OF PAYMENT.  The accepted quantity will be paid for at the contract unit price for the pay item listed below, complete in place.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $3.75 per 0.25 percent additive per ton of asphalt cement.

A change order/directive is not required for anti-stripping additive.  The approved mix design will initiate Item 401(4), Anti-Stripping Additive at the prescribed rate.  (5/3/93)R169

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1)	Asphalt Concrete, Type __	Ton

401(2)	___ Asphalt Cement	Ton

401(4)	Anti-Stripping Additive	Contingent

Sum

(7/16/93)M61

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-2.01  MATERIALS.  Add the following:  Reinforcing steel shall conform to the requirements of Section 503.

Standard Modifications

501-3.01  PROPORTIONING.  Under Item 1., Determining the Proportions and Batch Weights, add the following to the second paragraph:  Material properties shall be determined in accordance with the following test methods:

| Property | Test Method |
| --- | --- |
| Slump | AASHTO T 119 |
| Air Content | ATM T-8 |
| Compressive Strength | AASHTO T 22 |
| Unit Weight | AASHTO T 121 |
| Cement Content | AASHTO T 121 |

(7/2/93)M51

501-3.01  PROPORTIONING.  In the second paragraph under Item 3, replace "Polysar 1186" with "Styrofan 1186".  (5/12/89)M14

Special Provisions

501-3.01  PROPORTIONING.  Revise this subsection as follows:  In Table 501-1, Class of Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S, W and A-A concrete.  (9/1/89)R37

Add the following to subparagraph 4:  Fly ash may be used only in the abutments of the Tidewater Slough Bridge.  Fly ash shall not be used in the girders on this project.

501-3.02  BATCHING.  Add the following to item No. 5, Batching:  Furnish the mix design number and a list of all ingredients, their individual weights, moisture contents of the various aggregates and the individual truck water meter reading when batched, with each truck load or batch of concrete supplied.  (7/2/93)S54

501-3.06  PLACING CONCRETE.  Replace the last sentence of Item 2. Pumping Concrete with the following:  Concrete samples for testing shall be taken at the discharge end of the pipe.  The Contractor shall provide the necessary samples of concrete as directed.  (7/2/93)S65

Under Item 10., Setting Shoes and Bearing Plates, add the following:  Unless otherwise shown on the plans, pier and abutment caps on bridges shall be finished parallel to the roadway grade and parallel to the roadway cross slope or crown.  Grade strips on each side of the caps shall be independently set and the grade at the centerline of the bearings shall be carefully checked prior to casting the concrete.

SECTION 502

PRESTRESSED CONCRETE STRUCTURES

Standard Modifications

502-1.01  DESCRIPTION.  Add the following to the fourth paragraph:  Alternative designs shall be based on the assumed prestressing losses outlined in Subsection 502-1.02, Prestressing Methods.

Special Provisions

502-1.01  DESCRIPTION.  Add the following:  This work shall also include the application of silane sealer to all surfaces of all concrete girders for this project.

Standard Modifications

502-1.02  PRESTRESSING METHODS.  Revise the assumed stress losses in the fourth paragraph to read:

Pretensioning:

Stress relieved strand            45,000 psi

Low relaxation strand             40,000 psi

Post-tensioning, excluding friction losses:

Stress relieved strand            35,000 psi

Low relaxation strand             32,000 psi

Bar                               25,000 psi

The above losses are based on a jacking stress in the strands of no more than 0.70 GUTS (guaranteed ultimate tensile strength).

502-3.01  CONSTRUCTION REQUIREMENTS.

6.	Pretensioning.  In the last paragraph, change "0.80 GUTS" to read "0.75 GUTS".

Special Provisions

502-3.04  PLACING.  Add the following to the sixth paragraph:  The grout shall be packed and rodded into the joints to form a dense, impermeable filling.  The dry consistency of the grout tends to result in a porous filling, so additional compaction effort will be needed to achieve the required density.  The grout surface shall be smooth and neat in appearance.  The grout surface shall meet the girder edges throughout their lengths, and shall match the elevation of the surface of the girders with a tolerance of + 1/8 inches.  Patching and grinding may be required.

502-3.05  APPLICATION OF SILANE SEALER.  Add the following subsection:  All concrete surfaces shall be treated with a solution of 40 percent by weight alkyltrialkoxysilane in an anhydrous alcohol solvent (hereafter abbreviated as silane).  Prior to the sealing operation the surfaces shall be cleaned according to the manufacturer's recommendations.  The silane sealer shall be shop applied according to the manufacturer's recommendations.

Standard Modifications

502-4.01  METHOD OF MEASUREMENT.

1.	Structural Members.  In the second sentence, change "reinforcing and prestressing steel," to read "reinforcing steel (uncoated and/or epoxy coated), prestressing steel,".

Special Provisions

502-4.01  METHOD OF MEASUREMENT.  Add the following:  All labor, materials, equipment and work necessary for sealing the concrete surfaces with silane penetrating sealer will not be measured for payment but will be incidental to and included with Prestressed Concrete Structural Members.

502-5.01  BASIS OF PAYMENT.  Add the following:  All labor, equipment and materials required for sealing the concrete surfaces designated in subsection 502-1.01 Description, with silane penetrating sealer will not be paid for separately, but will be subsidiary to Item 502(1) Prestressed Concrete Structural Members.  No adjustment in the contract price for prestressed concrete girders will be made when epoxy coated prestressing strands are fabricated integrally with the units.

Standard Modifications

502-5.01  BASIS OF PAYMENT.  Delete the next to the last paragraph.  (5/12/89)M16

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01  DESCRIPTION.  Add the following:  This work will include the epoxy coating of appropriate reinforcing steel bars.  All reinforcing steel in precast concrete girders and other locations as noted on the plans, shall be epoxy coated.  (8/10/92)R38

Standard Modifications

503-3.05  SPLICING.  Delete the first and second paragraphs and substitute the following:  Lap splices for reinforcing bars shall be as shown on the plans or as directed.  (5/12/89)M17

Special Provisions

503-5.01  BASIS OF PAYMENT.  Add the following:  Epoxy coated reinforcing steel will not be paid for separately, but will be subsidiary to the items of work for which it is required.  (8/10/92)R38

SECTION 504

STEEL STRUCTURES

Special Provisions

504-1.01  DESCRIPTION.  Add the following:  This work shall also consist of furnishing and installing an avalanche control gun mount at the location and in accordance with the details shown on the plans.

504-3.01  FABRICATION.  Delete Item No. 8. Welding, and substitute the following:  All welding shall be performed in accordance with Subsection 505-3.15, Welding.

504-4.01  METHOD OF MEASUREMENT.  Add the following:  No measurement will be made for Item 504(8), Gun Mount.

504-5.01  BASIS OF PAYMENT.  Add the following:  Item 504(8), Gun Mount will be paid for a complete and accepted installation, including Class W concrete and all  excavation and backfill.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

504(8)	Gun Mount	Lump Sum

SECTION 505

PILING

Special Provisions

505-2.01  MATERIALS.  Add the following:  All welding shall be performed in accordance with Subsection 505-3.15, Welding.

505-3.03  PILE BEARING VALUES.  Delete this subsection in its entirety and substitute the following:  All piles shall be driven to the required bearing capacity.  The required bearing capacity is the design load shown on the general layout sheet in the plans multiplied by a factor of safety of 2.75.

505-3.07  EXTENSIONS, SPLICES AND BUILDUPS.  Delete the first sentence of item 1. and substitute the following:  If the length of a steel pile is not sufficient to obtain adequate penetration, an additional length shall be spliced to it.  The length of the spliced section shall be such that no splice shall be closer than 10 feet to the cutoff elevation of the pile after driving.

505-3.09  DRIVING PILES.  In the first paragraph, fifth sentence, change "1/2 inch" to "1-inch".

Delete the tenth paragraph (second paragraph on page 250), and substitute the following:  The Contractor's pile driving system shall be capable of overcoming the subsurface resistance during driving and reach the specified pile tip elevations without damage to structural steel piles.  The Wave Equation (GRLWEAP) shall be used for control of driving stresses.  The pile driving stresses shall not exceed 0.9 FY.

The Contractor shall submit a pile driving plan for approval.  At least 30 calendar days prior to the pile driving equipment mobilization, the Contractor shall furnish to the Engineer information regarding the proposed pile driving system on the "Pile Driving Equipment Data Form" for approval.  This form will be furnished by the Engineer.  Approval of the pile driving equipment will be based on wave equation analysis.  The Contractor will be notified of the acceptance or rejection of the pile driving system within 14 calendar days of the Engineer's receipt of the Pile Driving Equipment Data Form.  During the production pile driving operations, the Contractor shall use the approved driving system.  The Contractor shall submit for approval, a revised "Pile Driving Equipment Data Form" if there is any change or modification to the approved pile driving system.  The Contractor will be notified of the acceptance or rejection of the revised pile driving system within 5 calendar days of the Engineer's receipt of the requested change.  The time required for submission, review, and approval of a revised or changed pile driving system shall not constitute the basis for a contract time extension to the Contractor.

505-3.14  PAINTING STEEL PILES AND STEEL PILE SHELLS.  Add the following:  The outside surface of the piling, above ground, shall be painted in accordance with Subsection 504-3.03 Painting.

505-3.15  WELDING.  Add the following subsection:

All welding and inspection shall conform to the requirements of the latest edition of the American Welding Society (AWS) Structural Welding Code, D1.1.

1.	Qualification of Process, Procedures and Joint Details.  For each joint to be used in construction, the joint details, electrode classification or grade, electrode diameter, voltage, amperage, order and relative position of passes, number and thickness of layers and other pertinent information shall be clearly presented in the welding procedure(s) submitting by the Contractor for the approval of the Engineer.

Requirement for procedures qualification is waived if the Contractor's welding procedure is in accordance with all requirements of the welding procedures specification contained within the AWS Structural Welding Code, D1.1.

2.	Welders, Certification and Testing.  All welders and welding operators shall be certified in conformance with the AWS Structural Welding Code, D1.1.  Welders or welding operators lacking current AWS Structural Welding Code, D1.1, certification will not be permitted to perform welding on this project.

3.	Inspection of Shop Work and Records.  Welds including joint preparation, fit-up and alignment will be completely (100 percent of the weld) inspected visually and radiographed in conformance with AWS Structural Welding Code, D1.1.  Ten percent of the length, as determined by the Engineer, of each weld will be radiographic tested.  If a rejectable defect is found, then 100 percent of the lengths of the welds in that piece will be radiographically tested.

The Engineer will examine and approve satisfactory welds, disapprove or reject unsatisfactory welds, approve satisfactory methods proposed by the Contractor for repairing disapproved welds, and inspect the preparation and rewelding of disapproved welds.  Copies of all the welding fabrication documentation, including the weld testing results, will be forwarded to the Engineer.

4.	Obligation of Contractor.  It shall be the Contractor's responsibility to comply with all requests of the Engineer to correct improper workmanship and to remove and replace, or correct as instructed, all welds found defective or deficient by visual inspection or by nondestructive testing.

5.	Visual Inspection.  All welds shall be completely visually inspected.  A weld shall be acceptable by visual inspection if it shows that:

a.	the weld has no cracks,

b.	thorough fusion exists between adjacent layers of weld metal and between weld metal and base metal,

c.	all craters are filled to the full cross section, and,

d.	the completed weld conforms to all of the provisions of the AWS Structural Welding Code, D1.1.

6.	Nondestructive Testing.  The method of nondestructive testing will be radiographic testing in conformance with AWS Structural Welding Code, D1.1.  Field welds are not subject to nondestructive testing.

7.	Destructive Testing.  The location, method and extent of mandatory destructive testing to be performed (if any) will be indicated on the contract drawings.  All other welds will normally be inspected by visual methods and nondestructive testing;  however, the Engineer may require destructive testing of any weld that in his opinion does not meet the criteria for radiographic acceptance.

The cost associated with destructive testing of questionable welds will be borne by the Department for welds meeting radiographic acceptance criteria and by the Contractor for welds not meeting radiographic acceptance criteria.  The cost of destructive testing of welds designated for destructive testing on the contract drawings will be borne by the Contractor.

The Contractor is responsible for removing any weld specimen for destructive testing and repairing the weld afterwards.

8.	Preparation of the Weld.  The edges of the parts to be joined by welding shall be prepared by accurately cutting, grinding or machining to shape as indicated on the contract drawings and will be visually inspected prior to welding by the Engineer.

9.	Backing.  Backing rings or strips shall be utilized on all field butt welded joints welded from one side unless otherwise shown on the contract drawings or approved by the Engineer.  Open root joints are permissible where the joint is inaccessible from both sides.

10.	Cleaning.  Each completed bead shall be thoroughly cleaned of all slag, or other foreign matter, before proceeding with the next bead.  Hand clipping, power driven wire brushed, needle scalers, or grinders shall be used.

Full compensation for welding, weld inspection, weld testing, including all necessary tools, equipment, scaffolding and other support facilities required to perform welding, welding inspection, including the cost of radiographic testing will be subsidiary to the price bid for the piling items of the contract and no separate payment will be made.

(2/19/92)R146

505-4.01  METHOD OF MEASUREMENT.  Delete the following from the sixth line of the second paragraph under Item 2, Piles, Driven.:  "...reinforcing steel, concrete fill...".

Delete numbered paragraph 6. and substitute the following:

6.	Piles not achieving the specified capacity within 5 feet of the desirable tip elevation shown on the plans shall be driven to a penetration established by the Enigneer.  Requirement to drive piles deeper than the specified tip elevation shown on the plans shall be at the written direction of the Engineer.  For depths up to 20 feet beyond the desirable tip elevation, the contract bid price for piling will be applied.  For depths beyond 20 feet, the pile unit costs will be determined per Section 109.

505-5.01  BASIS OF PAYMENT.  Add the following:  The reinforcing steel to be used in the piling shall be measured and paid as Item 503(1) Reinforcing Steel.  Concrete fill used in the piling shall be measured and paid as Item 501(1) Class A Concrete.

SECTION 508

MEMBRANE WATERPROOFING

Special Provisions

Delete this Section in its entirety and substitute the following:

508-1.01  DESCRIPTION.  This work consists of furnishing and installing membrane waterproofing on concrete bridge decks and backwalls in conformance with the plans.  The membrane shall cover the entire top deck surface, from beginning to end of the bridge.

508-2.01  MEMBRANE WATERPROOFING MATERIAL.  Membranes for bridge deck waterproofing shall be a manufactured type membrane as specified herein.

Membrane shall consist of a single or multiple component elastomeric material, shall be a product listed on the Department's Approved Products List, or an approved equal, and shall comply with the following requirements:

1.	The laydown temperature of the asphalt mix shall be a minimum of 250 degrees Fahrenheit.  Laydown temperature is defined as the temperature of the asphalt mix behind the paver screed.

2.	If a tack coat is recommended by the supplier, a STE-1 or other approved tack coat shall be used.

3.	The manufacturer shall certify that the waterproof membrane will develop a proper bond with a minimum asphalt mix laydown temperature of 250 degrees Fahrenheit.

508-2.02  OVERLAY MATERIALS.  Materials requirements for pavement overlays on waterproof membranes shall conform to those specified in Section 401.

508-3.01  APPLICATION OF MEMBRANE WATERPROOFING.

1.	General.  Membrane waterproofing shall be installed in a manner to assure the following results:

a.	A complete bond between the membrane and the concrete surface of deck and curb face.

b.	An unbroken waterproof membrane in place between the concrete deck surface and the asphalt overlay.

c.	A complete bond between the membrane and the asphalt overlay.

2.	Preparation of Concrete Deck.  All concrete surfaces to receive membranes shall have cured at least 18 days prior to application of the membrane, except grout in keyways between precast members shall have cured at least 11 days prior to application of the membrane.

The entire deck shall be free of all foreign materials such as dirt, dust, moisture, loose concrete, etc.  Prior to applying the tack coat, primer or emulsion, all dust and loose material shall be removed from the deck by power sweeping followed by a thorough cleaning with compressed air.  Any sharp concrete edges on the deck surface which would puncture the membrane shall be corrected in a satisfactory manner prior to application of the membrane.  Grease, oil, paint, etc., shall be removed with solvents, detergents or sand blasting on decks that are to receive manufactured membranes.

Additional power sweeping, vacuuming, compressed air cleaning, or hand brooming shall be performed immediately before applying the tack coat, primer or emulsion if deemed necessary by the Engineer or manufacturer's representative.

3.	Weather and Moisture Limitations.  Membranes shall be applied in accordance with the manufacturers recommendations.

4.	Overlaying and Protection of Membrane.  The asphalt overlay shall be performed in accordance with the requirements of Subsection 401-3.11, Spreading and Finishing.

508-4.01  METHOD OF MEASUREMENT.  Membrane waterproofing will not be measured for payment.

All materials for the asphalt overlay will be included in the measurements of quantities for the appropriate paving items.

No adjustments will be made in the quantities or prices of materials for asphalt overlay because of any variations resulting from utilizing waterproof membranes of greater or lesser thickness.

508-5.01  BASIS OF PAYMENT.  Waterproof membrane will be paid for at the contract lump sum price.

Payment for the asphalt overlay will be made under the appropriate paving items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

508(1)	Membrane Waterproofing	Lump Sum

(5/12/93)R172

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-1.01 DESCRIPTION.  Add the following:  This work shall also consist of installing culvert marker posts.

603-2.01  MATERIALS.  Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts.  The color shall be blue with no other markings.  The 3-¾ inch by 72 inch post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

603-3.04  JOINING PIPE.  Delete the last sentence of numbered paragraph 1., and substitute the following:  Bands for pipe with diameters greater than 30 inches shall have a minimum width of 48 inches.  (10/1/91)

603-3.06  CULVERT MARKER POSTS.  Add the following subsection:  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  42 inches of post shall remain above the ground after driving.

603-4.01  METHOD OF MEASUREMENT.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to the pipe item.  (10/1/91)R42

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-3.01  CONSTRUCTION REQUIREMENTS.  Add the following after numbered item 4. under the paragraph referencing the reconstruction of manholes:

5.	The work necessary to rotate the cone or reducing slab to align the manhole or inlet casting as detailed on the plans.  To align the access stairs, the Contractor will have the option of rotating the barrel sections or installing new steps.

6.	The work and materials necessary to salvage the frame and grate, to remove and dispose the reducing slab and adjusting rings, and to install a new cover slab (reducing slab without an access hole).

Add the following:  When new pipe is installed in an existing manhole, a hole shall be cleanly cut by approved means at the invert elevation given on the plans and 2 inches larger than the outside diameter of the new pipe.  The joint shall then be grouted with non-shrinking cement mortar.

604-5.01  BASIS OF PAYMENT.  Add the following:  Frames, grates and lids are subsidiary to the drainage structure.

Delete Item 604(1) Storm Sewer Manhole and add the following pay item:

Pay Item No.			Pay Item         			Pay Unit

604(1)	Storm Drain Manhole, Type ___	Each

SECTION 606

GUARDRAIL

Special Provisions

606-1.01  DESCRIPTION.  Add the following:  This work shall also consist of installing breakaway cable terminals,  and guardrail/bridge rail connections, at the locations shown on the plans.

606-2.01  MATERIALS.  Add the following:  Flexible markers shall have yellow reflective sheeting and be one of the following types:

1.	"Guardrail Delineator Post" manufactured by Carsonite International, 2900 Lockheed Way, Carson City, Nevada 89701.

2.	"Guardrail Delineator" manufactured by Safe-Hit Corporation, 1930 West Winton Avenue, Building 11, Hayward, California 94545.

3.	"Flex-o-Guide", Model EY426 manufactured by Flexible Safety Zoning Company, 4152 Warren Avenue, Hillside, Illinois 60162.

606-3.01  POSTS.  Add the following:  The foundation type for the breakaway cable terminal posts shall be the steel post embedment for soil or concrete as shown on Standard Drawing G-18S.

606-3.02  RAIL ELEMENTS.  Add the following:  Guardrail elements shall be factory bent for all radii less than 75 feet.

606-3.03  REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following:  Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

606-3.08  LENGTH OF NEED VERIFICATION.  Add the following subsection:  After shaping the slopes and staking all proposed guard rail locations, the Contractor shall notify the Engineer to field verify the beginning and ends.  The staked location of the guardrail will be approved by the Engineer prior to installation.  The Engineer may determine that additional guard rail is necessary, and the Contractor shall comply without delay.

606-3.09  FLEXIBLE MARKERS.  Add the following subsection:  For each breakaway cable terminal, a flexible marker shall be installed at the terminal end, attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.  The flexible markers shall have a minimum of 21-inches of marker extending above the top of the guardrail.  The reflective tape shall face the nearest oncoming traffic.

606-3.12  GUARDRAIL/BRIDGERAIL CONNECTION.  Add the following subsection:  Existing guardrail/bridgerail connection shall be removed and salvaged and new guardrail/bridgerail connection installed in accordance with the details on the plans and Standard Drawing G-29.

Standard Modifications

606-4.01  METHOD OF MEASUREMENT.  Delete the last sentence of the first paragraph and substitute the following:  Double faced (and nested) installations will be measured by dividing the number of panels by two, before multiplying by the panel length.  Thrie beam transition pieces shall be measured by multiplying the number of panels by 6.25 feet and shall be paid for at the contract price for Thrie Beam Guardrail.  (5/12/89)M21

Special Provisions

606-4.01  METHOD OF MEASUREMENT.  Delete the third paragraph and replace with the following:  Breakaway cable terminals shall be measured per each installation which shall include all labor, equipment and materials required for installation, including anchor cable assembly, terminal posts, terminal end, flexible marker and all associated hardware.  Rail elements, standard posts, and blocking for breakaway cable terminals shall be paid under Item 606(1) W-Beam Guardrail.

Add the following:  

Guardrail/bridge rail connections shall be measured per each installation which shall include a section of nested thrie beam guardrail, thrie beam to standard W-beam transition, thrie beam transition bracket, posts and all associated hardware.

606-5.01  BASIS OF PAYMENT. Add the following pay items:

Pay Item No.			Pay Item	Pay Unit

606(8)	Breakaway Cable Terminal	Each



606(12)	Guardrail/Bridgerail Connection	Each

(2/14/92)R45 R126 R128

SECTION 607

FENCES

Special Provisions

607-1.01  DESCRIPTION.  Add the following:  This work shall also consist of the removal and reconstruction of the existing avalanche gate.

607-2.01  MATERIALS.  Add the following:  The new foundation for the relocated avalanche gate shall be constructed in accordance with the details shown on Standard Drawing T-75 for railroad signal foundations.

607-3.01  CONSTRUCTION REQUIREMENTS.  Add the following:  The existing avalanche gate arm, base and hardware shall be carefully removed from the concrete foundation and stored until ready to be reinstalled at the new location.  The Contractor shall reinstall the existing base and hardware and shall provide a new 32-ft avalanche gate arm compatible with the existing base.  The existing 25-ft gate arm shall be salvaged to the Girdwood maintenance station.  The Contractor may, if determined acceptable, provide an 8-ft arm extension to the existing gate arm.  Relocation of the gate shall occur during the months of April through September.

The existing concrete foundation shall be removed in its entirety.  If determined unacceptable for reuse, it may be disposed of in the lower reaches of the embankment, as long as the concrete fragments are less than 3 feet in greatest dimension and located no closer than 4 feet to finished grade.  If determined acceptable for reuse, the existing foundation shall be relocated to the new gate location and installed in a manner acceptable by the Engineer.

The existing gate base has a base plate attachment to fit the bolt pattern on the existing concrete foundation.  If a new foundation is constructed in accordance with the standard drawing, the base plate attachment shall be removed and salvaged to the Girdwood maintenance station.

607-4.01  METHOD OF MEASUREMENT.  Add the following: Item 607(20), Removal and Reconstruction of Avalanche Gate will not be measured for payment.

607-5.01  BASIS OF PAYMENT.  Add the following:  Payment for Item 607(20), Removal and Reconstruction of Avalanche Gate will be full compensation for performing the work described above.  Any damage done by the Contractor to the existing avalanche gate materials to be reinstalled, shall be repaired or replaced with new materials, at the Contractor's expense.  No adjustment in the lump sum price will be made for reusing the existing concrete foundation.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

607(20)	Removal and Reconstruction	Lump Sum

of Avalanche Gate

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01  MATERIALS.  Add the following to the end of the first sentence of the fifth paragraph:  "and the Alaska Traffic Manual."

Delete the seventh paragraph and substitute the following:  All metal sign posts other than perforated steel tubes, shall be equipped with slip bases.  (2/14/92)R50

615-3.01  CONSTRUCTION REQUIREMENTS.  Add the following to the sixth paragraph:  When existing signs are to be salvaged the existing sign foundations shall either be removed in their entirety, or they may be abandoned in place.  If they are abandoned, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than one foot below roadway subgrade or unimproved ground, whichever applies.  If located within the roadway structural section they shall be disposed of in a manner as approved by the Engineer.  All signs and posts at a single installation shall be considered as one unit.

615-3.02  SIGN PLACEMENT AND INSTALLATION.  Add the following:  Existing signs shall not be removed without authorization from the Engineer.  They shall be kept in service until either the new signs have been installed, or they are no longer needed.  As the work progresses, if their locations do not conform to Standard Drawing S-05, they shall be reinstalled at locations approved by the Engineer.

Prior to mounting the sign panel, the Contractor shall mark the date of installation on the back of the sign.  Installation dates shall be written in the format of month/day/year, using black permanent marker, with numbers a minimum of 3 inches in height, so as to be readable from the roadside after installation.

615-4.01  METHOD OF MEASUREMENT.  Add the following to the second paragraph: Concrete used for sign bases will be considered subsidiary to other work under this section and will not be measured for payment.

615-5.01   BASIS OF PAYMENT.  Add the following:   Payment for keeping existing signs in service until they are not longer needed, or temporarily relocating existing signs, will not be paid for directly, but will be subsidiary to Item 615(1), Standard Signs.

Payment for removal of existing sign post foundations, or work required to abandon them in place, shall be included in Item 615(7), Salvage Signs.

(2/14/92)R50

SECTION 618

SEEDING

Special Provisions

618-1.01  DESCRIPTION.  Delete this subsection and substitute the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded.  This work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01  MATERIALS.  Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01  SOIL PREPARATION.  Add the following:  Seed shall be applied as detailed below immediately after the shaping of the slopes.  All slopes to be seeded shall be covered with topsoil in accordance with Section 620 and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board.  The resultant indentations shall be perpendicular to the fall of the slope.  This should be completed as soon as topsoil is placed on the slopes.  The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted.  Where the fill is adjacent to  wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach on the wetlands.

618-3.03  APPLICATION METHOD.  In the first sentence of subparagraph b., under numbered paragraph 1. Hydraulic Method, delete the following:  "Item 619(1),".

Add the following:  Seed, mulch and fertilizer shall be applied as follows per 1,000 square feet.  The mulch rate shown is a minimum, and may be increased in accordance with  the  manufacturers  recommendations.  If the hydraulic method for seed and mulch is used, it shall be made in one application.  All fertilizer shall be applied by the hydraulic method.

| Item | Ingredients | Application Rate per MSF |
| --- | --- | --- |
| Seed Mix | Bering Hairgrass (Norcoast) Red Fescue (Arctared) Clover (Alsike or Dutch White) Annual Rye Grass (Lolium) | 0.40 lbs. 0.30 lbs. 0.20 lbs. 0.10 lbs. Total = 1.00 lbs. |
| Mulch |  | 35.0 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

The Contractor shall not remove the required tags from the seed bags.

618-4.01  METHOD OF MEASUREMENT.  Delete the second paragraph and substitute the following:  Seeding by the pound will be the number of pounds of seed (dry measure) accepted in place.  The amount of fertilizer, mulch and water for application used in this work, including any required reseeding, will be subsidiary to this item and will not be measured separately for payment.

Delete the last paragraph.

618-5.01  BASIS OF PAYMENT.  Add the following:  Fertilizer, mulch and water for application, including any required reseeding, will not be paid for directly, but will be subsidiary to seeding.

The work described under subsection 618-3.01 Soil Preparation will not be paid for directly but will be subsidiary to seeding.

Water required for the hydraulic method of application will not be paid for separately, but will be subsidiary to seeding.

(10/1/91)R52

SECTION 620

TOPSOIL

Special Provisions

620-2.01  MATERIALS.  Add the following:   Prior to seeding, the topsoil shall be tested for pH.  If the pH is less than 6.0, limestone shall be added in accordance with Table 726-1, Limestone Requirements.

620-4.01  METHOD OF MEASUREMENT.  Add the following:  Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(10/1/91)R53

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01 DESCRIPTION.  Add the following:  This work includes the construction of public approaches at locations shown on the plans.

639-1.02  CONSTRUCTION REQUIREMENTS.  Add the following subsection:  Placement of materials used in driveways and public approaches shall meet the requirements specified as follows:

Selected Material	Section 203

Crushed Aggregate Base Course	Section 301

Asphalt Concrete	Section 401

639-3.01  BASIS OF PAYMENT.  Add the following pay item:

Pay Item No.			Pay Item	Pay Unit

639(3)            Public Approach	Each

Delete the last sentence and substitute the following:  Selected Material, Crushed Aggregate Base Course, and Asphalt Concrete required to construct driveways and public approaches will be paid for separately under the respective items listed in the bid schedule.  Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to Item 639(3) Public Approaches.

(10/1/91)R58

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-2.01  METHOD OF MEASUREMENT.  Delete item 3. and substitute the following:

3.	When the letter of project completion has been issued and the Contractor has made all the required submittals the remaining balance of the amount for this item will be paid.  (5/7/91)S41

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01  DESCRIPTION.  This work shall consist of planning, providing, and maintaining control of erosion, water pollution, and hazardous materials contamination.

This work shall also include installation of silt fence as shown on the plans or as directed by the Engineer.

641-1.02  SUBMITTALS.  Five days prior to the preconstruction conference, the Contractor shall submit for acceptance a plan for accomplishment of temporary and permanent erosion and pollution control measures throughout the life of the contract.  This plan shall, as a minimum, include the following:

1.	Notice of Intent (NOI) to utilize the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska.

2.	Stormwater Pollution Prevention Plan (SPPP).

3.	Hazardous Material Control Plan (HMCP).

The NOI and SPPP shall be prepared in accordance with the requirements of the NPDES General Permit for Alaska (General Permit) and the Contractor Guidance for Preparing and Executing Storm Water Pollution Preventions Plans (Storm Water Manual).  When completing the NOI, the Contractor is the "Operator, Discharger, and Permittee" and the Department is the "Owner".

The HMCP is the Contractor's plan for the containment, cleanup, and disposal of waste material, as well as petroleum products or other hazardous substances generated by construction equipment or activities.  A list of quantities and types of equipment and materials available on site to be used for hazardous substance containment and cleanup shall be included.

The Contractor shall mail the NOI to the U.S. Environmental Protection Agency via Certified Mail, and shall send copies to the Engineer and the Alaska Department of Environmental Conservation Stormwater Coordinator.  Earth disturbing work shall not begin until 48 hours after the NOI has been postmarked.

The Contractor shall submit required amendments to the NOI or SWPPP to the Engineer at least 14 days prior to performing work affected by such amendments.

The Contractor shall submit a Notice of Termination (NOT) in accordance with the General Permit to the Engineer following completion of the final stabilization of the project.

641-1.04  MATERIALS.  The silt fence filtration material shall meet the requirements of Subsection 729-2.04, Sediment Control.

The silt fence support framework shall be finished 4 x 4-inch wood, 3-inch diameter wood, #6 rebar with PVC sleeves, iron pipe, or other posts capable of supporting the installation, as approved by the Engineer.

The mesh support shall be WWF 6x6 W1xW1 or as approved by the Engineer.

641-2.01 CONSTRUCTION REQUIREMENTS.  The Contractor shall comply with all requirements of the NPDES General Permit for Alaska.  The Contractor shall provide the Engineer with a copy of all inspection reports required by the Permit within three days of the inspection date.  Compliance with the NPDES General Permit for Alaska does not reduce the Engineer's authority to direct additional erosion control measures deemed appropriate.

The Contractor shall be responsible for the containment, cleanup, and disposal of all construction related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water.  Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of subsection 107-1.11, Protection and Restoration of Property and Landscape.  Additional silt fencing may be required at other sites as directed by the Engineer.

The silt fence shall not be removed until slopes are stabilized from further erosion as determined by the Engineer.  The silt fence shall be removed and disposed of off the project upon completion of construction at those sites.  The fabric shall be cut off at ground level and the wire and posts shall be removed.  The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands or waterbodies.  If a sediment height in excess of four inches above ground remains, the sediment shall be spread on the roadway side of the fence location and seeded immediately in accordance with Section 618, Seeding.

641-3.01  METHOD OF MEASUREMENT.  Erosion and Pollution Control Administration will not be measured for payment.

Erosion and Pollution Control will be measured in the manner specified in the order authorizing the work.

Silt fence will be measured by the linear foot along the top of the fence.

641-4.01  BASIS OF PAYMENT.  Item 641(1), Erosion and Pollution Control Administration will be full compensation for administration of erosion control, including preparing and amending plans, inspecting, monitoring, reporting, and record keeping.

Item 641(2), Erosion and Pollution Control will be full compensation for providing all required labor, equipment, and materials.

Failure to comply with the requirements of the NPDES General Permit for Alaska within 24 hours notice by the Engineer will result in withholding an amount equal to five percent of the total amount earned from all subsequent progress payments.  This retainage will be released by the Engineer upon satisfactory completion of the requirements of the  General Permit.

Payment for Item 641(3), Silt Fence, will be full compensation for all labor, equipment and materials required to furnish, install, maintain and remove the silt fence in accordance with these specifications.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution	Lump Sum

Control Administration

641(2)	Erosion and Pollution	Contingent Sum

Control

641(3)	Silt Fence	Linear Foot

(2/2/93)R59g

SECTION 642

CONSTRUCTION SURVEYING

Special Provisions

642-1.01  DESCRIPTION.  Add the following to the first paragraph:  The Contractor shall perform in accordance with the Department's "Construction Surveying Requirements", dated June, 1987.  A copy of this document is attached to these Special Provisions in Appendix C.

642-3.01  CONSTRUCTION REQUIREMENTS.  Add the following after item 11.:

12.	The Contractor's survey crews shall comply with approved traffic control plans.  Crews shall coordinate their activities with the project's Worksite Traffic Supervisor.

642-4.01  METHOD OF MEASUREMENT.  Add the following:  Pay Item 642(2), Three Person Survey Party, shall be used only for extra, additional, or unanticipated work made necessary by changes in the project as directed by written order of the Engineer.

642-5.01  BASIS OF PAYMENT.  Add the following:  If additional work as stated above is performed by a two person survey party, hours paid for under Item 642(2) Three Person Survey Party will be 75 percent of the hours worked.  If additional work as stated above is performed by only one person, hours paid for under Item 642(2) Three Person Survey Party will be 32 percent of the hours worked.  (10/1/91)R60

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.02  TRAFFIC CONTROL PLAN.  Add the following to the first paragraph:  A traffic control plan shall also indicate the method of safely routing pedestrian traffic through or around the construction zone.

A traffic control plan shall also indicate the method of safely stopping and routing the travelling public through the project during periods of possible avalanche danger.

Delete the second paragraph and substitute the following:  TCP's are required for each work site.  TCP's included in the plans are acceptable for use with the concurrence of the Engineer.  The Contractor may elect to modify them or design alternative TCP's.  All modified and/or alternative TCP's shall be submitted for approval of the Engineer.  The Contractor shall allow three weeks for review of any submitted TCP or one week for each subsequent correction.  Changes in the TCP resulting from unforeseen circumstances may be allowed during construction, provided a minimum of 48 hours are allowed for review, and the changes are approved by the Engineer.

Add the following to the third paragraph:  All TCPs submitted shall indicate the dates and hours for which the TCP will be in effect.  Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

Add the following to the fourth paragraph:  Plan sheets developed on AutoCad can be made available, upon request, for use in preparing TCP's.

643-1.03  WORKSITE TRAFFIC SUPERVISOR.  Delete the second sentence of the first paragraph and substitute the following:  The Worksite Traffic Supervisor shall meet the following minimum requirements:

1.	Be currently certified as a Worksite Traffic Supervisor by the American Traffic Safety Services Association (ATSSA), or,

2.	Be currently certified as a Work Zone Traffic Safety Specialist or a Signs and Lines Specialist by the International Municipal Signal Association (IMSA), or,

3.	Be currently certified as a Worksite Traffic Technician by ATSSA, or,

If the individual is certified under Items 2 or 3 above, the Contractor shall submit documentation that the individual has also obtained:

1.	A minimum of one year of supervisory level work in worksite traffic control, or,

2.	One year of having been in responsible charge of such work.  The term "in responsible charge" shall be construed to mean having been in a position of accountability for the selection of devices and for their placement in the traffic control system, or for the continued operation of the system.  Having persons that actually perform the labor under one's control would satisfy this requirement.

643-1.04 CONSTRUCTION PHASING PLAN.  Revise the first sentence to read as follows:  A Construction Phasing Plan shall be submitted at least five working days prior to the preconstruction conference for approval by the Engineer and shall consist of the following:  (5/7/91)S57

643-2.01  MATERIALS.  Add the following under Item 3. Barricades and Vertical Panels:  Type III barricades shall have a minimum width of 8 feet.

Delete numbered paragraph 8. in its entirety and substitute the following:

8.	Work Zone Pavement Markings.  Work zone pavement markings shall be either paint conforming to subsection 708-2.03 with glass beads conforming to subsection 712-2.08, preformed marking tape (removable or non-removable) conforming to subsection 712-2.14, or temporary raised pavement markers conforming to subsection 712-2.15 or 712-2.16, as appropriate.  The markings shall be applied in accordance with Section 670, Traffic Markings, and the manufacturer's recommendations.

(5/7/91)S59

Add the following:

12.	Portable Changeable Message Boards.  Portable changeable message boards shall be truck or trailer mounted with a self-contained power supply and shall have the following features:

a.	Message sign panel size of 5'-8" by 7'-5", minimum, with a capacity for a three line message.

b.	Eight character display per message line.

c.	Message modules containing at least 36 different preprogrammed messages (three line displays) to be selected by the Engineer.

d.	The capacity to create, preview, and display new messages and message sequences.

e.	A waterproof, lockable cover for the controller keyboard.

f.	An operator's manual, a service manual, and wiring diagram.

g.	Quick release attachments on display panel cover.

h.	Variable flash and sequence rates.

i.	Manual and automatic dimming capability on lamp bulb matrix models.

j.	The ability to mount at least 7 feet above the pavement to the bottom of the message sign panel.

k.	The capacity to operate with a battery pack for 2 hours under full load.

13.	Pedestrian Fence.  Pedestrian fence shall be orange, 4-feet high, with posts as recommended by the manufacturer and shall be one of the following, or equivalent:

a.	"Safety Fence" as manufactured by Service and Materials Company, Inc., 2200 South J. Street, Elwood, Indiana 46036, (317)552-3352.

b.	"Flexible Safety Fencing" as manufactured by Carsonite, 1301 Hot Springs Road, Carson City, Nevada 89706, (702) 883-5104.

c. 	"Safety Fence" as manufactured by The Plastic Net Corporation, 1048 Niagara Street, Buffalo, New York 14213, (716)883-4400.

643-3.01  GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  The Contractor is responsible for snow removal necessary to accomplish the ATU duct work.  This may include residual snow from highway maintenance efforts, railroad maintenance efforts, as well as possible avalanche debris.

643-3.02  ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following to the first paragraph:  The maximum spacing between channelizing devices in a taper should be approximately equal in feet to the speed limit.

643-3.03  PUBLIC NOTICE.  Add the following to the first paragraph:

Anchorage Chamber of Commerce

Seward Chamber of Commerce

Homer Chamber of Commerce

Alaska Visitor's Association

Add the following:  The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of commencing construction, resuming construction after seasonal suspension, or any scheduled delay, or closure of driving lanes within the project corridor.  The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure.  The advertisements shall be published in the Anchorage Daily News.

The Contractor shall indicate on the ad order a first preference for the local news section and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a 24-hour toll free (1-800-###-####) "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.

Advertisements shall be promptly cancelled when they have served their purpose.  The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

A change order is not required for newspaper advertisements, the Notice to Proceed shall constitute the notice required to initiate newspaper advertisements.  (12/8/92)R167

643-3.04  TRAFFIC CONTROL DEVICES.  Delete Item 1. Embankments, and substitute the following:

1.	Embankments.  A portable concrete barrier shall be installed when either an excavation or a fill with a foreslope steeper than 3:1 will exist within  the clear zone for more than 12 consecutive hours.  2:1 slopes will be allowed within the clear zone provided they do not exceed 5 feet in height, and a minimum 10 foot wide recovery area, 4:1 or flatter, is provided at the toe of the 2:1 slope.

The clear zones for embankments on this project shall be as shown in Table 643-1.  The applicable clear zone depends upon the average embankment slope within the clear zone, and is measured from the edge of travelled way.

Table 643-1

Seward Highway MP 90-97 Clear Zones

| Average Embankment Slope | Clear Zone Width |
| --- | --- |
| 6:1 or flatter | 30 feet |
| 5:1 to 6:1 | 30 feet |
| 4:1 to 5:1 | 30 feet |
| 3:1 to 4:1 | * |
| 2:1 to 3:1 | ** |
| Steeper than 2:1 | Install Barrier |

*	A minimum 10 ft recovery area at toe of slope is required.

**	Maximum height of these slopes = 5 ft, otherwise install barrier.

A minimum 2 foot shoulder, 10:1 or flatter, shall be provided between the edge of travelled way and the face of portable concrete barrier or an adjacent slope.  This applies only to construction areas and not to existing undisturbed slopes.

A minimum 2 foot shoulder, 10:1 or flatter, shall be provided between the edge of travelled way and the face of portable concrete barrier or an adjacent slope.  This applies only to construction areas and not existing undisturbed slopes.

A minimum 2 foot wide clear area, 10:1 or flatter, shall be provided behind portable concrete barrier to allow for deflection if it is struck.

The ends of portable concrete barrier shall be flared away from the roadway at a rate of 15:1 on a transverse slope of 10:1 or flatter to the edge of the clear zone.  If the portable concrete barrier cannot be flared in the manner stated above, a temporary crash cushion shall be used.

Barrier reflectors shall be mounted on the face of barrier adjacent to traffic on 50-foot centers and shall be a minimum height of 18 inches above the surface of the roadway.

Delete numbered paragraph 4., Work Zone Pavement Markings in its entirety.

Under item 5., Flagging, add the following after the first sentence of the first paragraph:  Each flagger shall be illuminated from the front to a level of light intensity not less than one foot candle during hours of darkness.

Under item 5., Flagging, add the following:  Flaggers shall wear reflective clothing with markings on arms, legs and head, as approved by the Engineer.

Add the following:

9.	Portable Changeable Message Boards.  These boards shall be used to notify the travelling public of the upcoming work as deemed necessary by the Engineer.  Based on the TCP contained in the plans, a maximum of two boards are required for this project.

643-3.05  AUTHORITY OF THE ENGINEER.  Add the following:  The Contractor will be assessed a charge of $50 per hour for each hour after the specified time allowed that any work remains uncompleted.  This amount is to cover estimated expenses incurred by the Department as a result of the Contractor's failure to complete the work within the time specified.

643-3.06  TRAFFIC PRICE ADJUSTMENT.  Add the following:  A change order is not required for traffic price adjustment, the Notice to Proceed shall constitute the notice required to initiate traffic price adjustment.  (12/8/92)R168

643-3.07  MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK.  Delete the first sentence and substitute the following:  The Contractor shall schedule a preliminary meeting with the Engineer and Maintenance and Operations to take place approximately one month prior to seasonal suspension of work, or no later than September 1.  At this meeting, the Contractor shall outline the work expected to be completed before shutdown, and obtain direction from the Department regarding what will need to be accomplished for the roadway to be accepted for winter shutdown.  A winter shutdown traffic control plan shall be submitted to the Engineer at this preliminary meeting.

643-3.08  CONSTRUCTION SEQUENCING.  Delete this subsection in its entirety and substitute the following:  A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes or shoulders or their respective widths or stops traffic.  An approved Traffic Control Plan is required before any restriction to traffic is implemented.  No restrictions to traffic will be allowed during the times listed below unless modified by these specifications:

1.	May 15 to September 15, 6:00 A.M. to 10:00 P.M.

2.	Monday through Thursday from 6:00 A.M. to 8:30 A.M. and from 5:30 P.M. to 7:30 P.M.

3.	Friday from 6:00 A.M. to 8:30 A.M. and Friday from 1:00 P.M. to Sunday at 10:00 P.M.

4.	Around any holiday as described below:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above  stipulations apply from 1:00 PM on the Friday before the holiday to 10:00 PM on the day of the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply  from 1:00 PM on the Tuesday before the holiday to 10:00 PM on the  day of the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above  stipulations apply from 1:00 PM on the day before the holiday to  10:00 PM on the Sunday after the holiday.

Complete roadway closures will be allowed as follows:

1.	Two per week between May 15 and September 15 with a maximum of 1/2 hour anytime between 8:30 A.M. and 5:30 P.M. Monday through Thursday.  These closures shall be limited to halting traffic during rock blasting.

2.	Four per week between September 15 and May 15, between the hours of 8:30 A.M. and 5:30 P.M., Monday through Thursday and 10:00 A.M. to 2:00 P.M., Friday through Sunday.

643-3.09  TEMPORARY PAVEMENT MARKINGS.  Add the following subsection:  Permanent or Temporary Pavement Markings in accordance with this subsection, approved traffic control plans, and Parts III and VI of the Alaska Traffic Manual shall be in place before existing paved roadways, temporary paved roadways and detours, interim paving lifts, and roadways with seal coats and surface treatments are opened to traffic for longer than one continuous work shift.  This work may include restriping of the existing roadway prior to beginning construction of the project.

Conflicting pavement markings shall be removed in accordance with subsection 670-3.04, Paint Removal.  Construction shall be staged so that no traffic is routed over conflicting markings.

Sections of existing roadway that will be opened to traffic during the winter shall be marked at the same location as the existing lines and markings unless shown otherwise on the plans, an approved traffic control plan, or as directed by the Engineer.

The Contractor shall maintain all Temporary Pavement Markings for their intended life without additional compensation for any reapplication that may be required.  There will be no compensation to upgrade Temporary Pavement Markings for short term operations to those required for long term operations.

Only temporary raised pavement markers or removable preformed retroreflective marking tape shall be used as Temporary Pavement Markings on the final pavement surface.  They shall be completely removed and disposed of in conjunction with the placement of the final markings.  The complete removal shall include any residual adhesive that might misguide motorists.  Final pavement markings on finished pavement surfaces and long term pavement markings on other asphalt surfaces shall be in place before work is suspended for the winter.

Temporary Pavement Markings may not be required for construction activities that will be completed within one continuous work shift if the roadway is adequately delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.  The Engineer shall determine the need for the Temporary Pavement Markings for these conditions.

1.	Long Term Operations.  Temporary Pavement Markings which will be in place for more than 2 weeks shall consist of full markings as if a permanent condition exists.

2.	Short Term Operations.  Temporary Pavement Markings which will be in place for less than 2 weeks shall be in accordance with Parts III and VI of the Alaska Traffic Manual with the following exceptions:

a.  Passing Zones.  Broken line pavement markings shall conform to Tables 643-1 or 643-2.  This  applies to both white lane lines for traffic moving in the same direction and yellow center lines for two or three lane two-way roadways when it is safe to pass.

TABLE 643-1*

|  | LENGTH OF MARKINGS |  | SKIP SPACING |  |
| --- | --- | --- | --- | --- |
| Marking Material | Normal Curvature | ** Severe Curvature | Normal Curvature | ** Severe Curvature |
| Removable Preformed Marking Tape | 4 feet | 2 feet | 36 feet | 18 feet |
| Temporary Raised Pavement Markings | 3 units 3 feet on center | 2 units 2 feet on center | 34 feet | 18 feet |

TABLE 643-2*

|  | LENGTH OF MARKINGS |  | SKIP SPACING |  |
| --- | --- | --- | --- | --- |
| Marking Material | Normal Curvature | ** Severe Curvature | Normal Curvature | ** Severe Curvature |
| Removable Preformed Marking Tape | 2 feet | 1 foot | 38 feet | 19 feet |
| Temporary Raised Pavement Markings | 1 unit 40 feet on center | 1 unit 20 feet on center | ____ | ____ |

* No passing markings and signing required per 643-3.09.2.b.

** Severe Curvature:  When the degree of curvature is 5 or greater or when it is necessary for motorists to reduce their speed at least 15 miles per hour below the 85th percentile speed.

b.  No Passing Zones.  No passing zones, as detailed in Section 3B-3 to 3B-5 of the Alaska Traffic Manual, shall be identified as follows:

Sections of asphalt concrete pavement roadways with an ADT of 2000 vehicles per day or greater, shall have broken centerline markings conforming to Table 643-1, and no-passing markings consisting of a continuous 4-inch strip of removable preformed marking tape or temporary raised pavement markers placed on 5-foot centers in the no passing direction.  If a no passing condition exists for both directions of traffic, both directions shall be marked with the two 4-inch stripes of removable preformed marking tape separated by approximately 3 inches, or two temporary raised pavement markers placed approximately 3 inches apart on 5 foot centers and the broken centerline markings are not required.

Sections of asphalt concrete pavement roadways with an Average Daily Traffic (ADT) of less than 2000 vehicles per day, and seal coat and surface treatment pavements shall be marked with temporary pavement markings conforming to Table 643-2 and shall be identified with R4-1, (DO NOT PASS) and R4-2, (PASS WITH CARE) signs.  The signs shall be supplemented with two 18-inch by 18-inch, minimum size, fluorescent red-orange flags mounted above the signs.  The signs shall be mounted so that the bottom of the sign is at least 5 feet above the adjacent roadway.

c.  Other Markings.  It will not be necessary to install arrows, legend, stop lines, crosswalks, or right edge line markings.  Railroad crossing markings are required for areas that have sight restrictions or high accident experience.  Left edge lines will not be required unless they will be the only markings on the paved surface, such as ramps.  All other types of markings are required.  These include channelizing lines and gore area outlines.

d.  Short Term Markings on Seal Coats and Surface Treatments.  Only temporary raised pavement markers conforming to Subsection 712-2.16 shall be used for short-term markings on seal coat and surface treatment pavements.  The markers shall be installed prior to the application of the asphalt surface material and cover coat.

On multicourse surface treatments the temporary raised pavement markers shall be installed following the full width application of the first layer of cover coat.  The markers shall be installed on each day's completed surface before the pilot car operations are removed and unescorted traffic is allowed on the surface treatment in accordance with Table 643-2.

If the temporary raised pavement markers cannot be adequately secured to the first course of the cover coat material with the marker's flexible bituminous adhesive, the Contractor shall secure them to the surface with two nails and washers, of the appropriate length and area, so the nails do not pull through the foot of the marker.

After application of the asphalt and cover coat material, the vinyl protective cover shall be removed to expose the retroreflective surfaces of the marker.  Temporary markers shall be installed so that the foot of the marker unit is facing the direction of the approaching distributor.

Final pavement markings shall not be placed until the seal coat or surface treatment has been opened to traffic for at least 14 days.  Final pavement markings shall be applied within 10 days of the completion of the final sweeping or brooming of the mainline seal coat or surface treatment.  Seal coat and surface treatment pavements are exempt from the two week requirement stated in short-term operations.

643-4.01  METHOD OF MEASUREMENT.  Add the following to item 1.:  Newspaper advertisements will not be included in measurement for Traffic Maintenance.

Delete the second sentence of the first paragraph under item 2. and replace with the following:  The quantities to be paid for shall be the number of units of each of the bid items that are installed, accepted and maintained in place during the life of this contract.  Permanent Construction Signing will not be measured for payment, but will include all permanent construction signs, as detailed on the plans, that are installed, accepted, maintained, and removed during the life of this contract.

Add the following to Item 2:  Type II Barricades will be measured and paid for under Item 643(8), Drums.

Delete numbered paragraph 6. in its entirety and substitute the following:

6.	Temporary Pavement Markings will be measured by the single stripe station.  A single stripe is a marking or a temporary raised pavement marker four inches in width.  Wider striping will be measured as multiples of four inches.  Centerline gaps will not be deducted from measurements.  Installation of any word and symbol markings as well as the removal of the Temporary Pavement Markings will not be measured separately but will be subsidiary to this item.  The No-Passing Zone signing, as described in Subsection 643-3.09, 2., b., will not be measured separately but will be subsidiary to this item.

Delete paragraph 7., Seasonal Pavement Markings in its entirety.

Add the following:  Item 643(25) Portable Changeable Message Board will be measured by the calendar day for each sign used as approved by the Engineer.

Newspaper advertisements will not be measured for payment.

Providing a "hot-line road report" telephone with pre-recorded message will not be measured for payment but will be subsidiary to Item 643(1), Traffic Maintenance.

Pedestrian Fence - Item No. 643(32) will be measured by the linear foot.

No measurement will be made for snow removal necessary to accomplish the ATU duct work.  This work, if necessary, will be subsidiary to Item 643(1), Traffic Maintenance.

643-5.01  BASIS OF PAYMENT.  In the second paragraph, delete Item 1., Seasonal Pavement Markings.

In the fourth paragraph, delete Pay Item 643(14) Seasonal Pavement Markings.

Standard Modifications

643-5.01 BASIS OF PAYMENT.  Change the pay unit for item 643(3), Permanent Construction Signing, from "Calendar Day" to "Lump Sum."  (5/7/91)M40

Special Provisions

643-5.01 BASIS OF PAYMENT.  Change the pay unit for item 643(11), Portable Concrete Barrier, from "Each" to "Linear Foot".

Add the following:  Barrier reflectors will not be paid for directly, but will be subsidiary to Pay Item 643(11), Portable Concrete Barrier.

Payment for Item 643(25), Portable Changeable Message Board will be full compensation for all labor, equipment, and materials to provide, move, maintain, program, and operate a portable message board signs on the project.

Payment for Item 643(29), Newspaper Advertisements will be made at cost plus 15 percent.  Payment will be authorized upon evidence of payment to the newspaper (paid receipt).

Item 643(32), Pedestrian Fence will be paid by the linear foot of fencing installed, maintained and removed at locations designated by the Engineer.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

643(25)	Portable Changeable Message	Calendar

Board	Day

643(29)	Newspaper Advertisements	Contingent

Sum

643(32)	Pedestrian Fence	Linear Foot

(2/14/92)R111

SECTION 644

SERVICES TO BE FURNISHED BY THE

CONTRACTOR

Special Provisions

644-2.01  FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:  The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work through 30 days after issuance of the notice of project completion.  The following office requirements shall be met:

1.	A minimum of 1,500 square feet of floor area.  The office area shall be divided so that it contains a minimum of three office rooms separated by closable doors.  Each office room shall have a minimum of 150 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 cycle power.

4.	A minimum of 250 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 15 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within five miles of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

644-2.02  FIELD LABORATORY.  Delete the sixth sentence of the first paragraph and substitute the following:  The water supply shall consist of a 500-gallon capacity tank with a pressure pump or a commercial pressurized system.

Delete the second paragraph and substitute the following:  The laboratory shall include a concrete slab, 8 feet by 10 feet by 4 inches thick, suitable for mounting a Gilson shaker and other equipment.  The slab shall be installed within an enclosed adjacent structure having a door, a window, a worktable, an exhaust fan, and adequate lighting and heat.

(10/1/91)R63

644-4.01  BASIS OF PAYMENT.  Add the following:  Electricity, propane and water supplied for the State provided portable asphalt lab will not be measured for payment, but will be considered subsidiary to Item 644(2), Field Laboratory.

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01  OBJECTIVE.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.1, located in the "green pages" of this document.

645-3.01  GENERAL.  The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following:  contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02  WAGES.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03  SUBCONTRACTS.  In the event the Contractor subcontracts a portion  of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01  METHOD OF MEASUREMENT.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  BASIS OF PAYMENT.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or,

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program for	Labor Hour

1 Trainee/Apprentice

(10/29/91)S16

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION.  Add the following:  This work shall also consist of removal of pavement markings at locations shown on the plans or as directed by the Engineer.

670-3.04   PAINT REMOVAL.  Change the title of this subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following:  Pavement markings shall be removed to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement.  Painting over existing striping does not meet the requirement for removal.  Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-4.01 METHOD OF MEASUREMENT.  Add the following after item 5:

6.	Station Basis.  Pavement markings to be paid for by the station will be measured by taking the difference in the beginning and ending stations of each marking, excluding gaps, and multiplying that by the marking's nominal width in inches divided by 4.  Measurement of transverse markings, letters, and arrows shall be made by taking the area of the marking's rectangular footprint and multiplying it by 0.03 (the number of 4 inch multiples in 1 foot divided by 100).

Delete the last paragraph and substitute the following:  Removal of pavement markings will be measured by the station for payment.

670-5.01 BASIS OF PAYMENT.  Add the following:  Repair of any damaged pavement or surfacing caused by the pavement marking removal operation will be subsidiary to Item 670(9) Removal of Pavement Markings.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

670(9)	Removal of Pavement Markings	Station

(5/13/92)R142

Add the following Section:

SECTION 680

TELEPHONE RELOCATION

Special Provisions

680-1.01  DESCRIPTION.  This section covers the furnishing and field installation of a complete conduit system in accordance with these Specifications and the plans.

The conduit system includes innerduct installed by trenching, trenching with concrete slurry backfill, boring and plowing, prefabricated vaults (handholes), and all appurtenances, materials, and devices required to install, support, secure and provide a complete system for support and protection of fiber optic cable.

680-1.02  CODES AND STANDARDS.  Conduit system materials and devices furnished shall be in accordance with applicable standards of ANSI, ASTM, NEMA, UL, and all local codes and permits.  Conduit system components shall be installed in accordance with applicable requirements of the NEC.  In a case of conflict between the requirements of any of the above referenced codes and standards and the requirements of these Specifications, the requirements of these Specifications shall govern.  All materials, devices, and practices shall be in accordance with the applicable requirements of the Federal "Occupational Safety and Health Standards."

680-2.01  MATERIALS.  The following materials will be furnished by ATU at no cost to the Contractor:

1.	Handholes (4848)

2.	Handhole frames and covers

3.	RAMNEK and gasket sealant material for handholes.

4.	EMS (Electronic Marker System)

5.	Ground rods, #6 SDC ground wire, and clamps.

6.	Omni Glide pull line

All materials to be furnished by ATU will be located at ATU's warehouse, 600 Telephone Avenue, Anchorage, (south yard).

Within five (5) days of receipt of Notice-to-proceed, the Contractor shall determine his material take-off requirements and shall prepare a complete itemized list of materials for submittal to ATU.  A list of materials needed will be delivered to ATU, through the ATU Construction Clerk, at least 24 hours in advance of pickup time.  Material shall be picked up for the complete project and not on an as needed, on a daily basis.  If material is ordered at least 72 hours in advance, ATU will stage the material for pick up.  Handholes will be loaded on the Contractor's vehicle by others at no cost to the Contractor.

The Contractor shall sign for materials at the time of receipt.  The ATU warehouse foreman will be available for material issuance between the hours of 7:30 AM to 12:00 noon and 1:00 PM to 4:30 PM daily except Saturdays, Sundays and ATU holidays.  Where it is necessary to open the warehouse for the Contractor's convenience and to procure special issuing of material other than during these normal working periods, the Contractor will be billed for the loaded labor rate time involved plus 25 percent handling overhead.  Storage and safekeeping of all materials after pickup from ATU shall be the Contractor's responsibility.   All unused materials shall be returned to the warehouse upon completion of the project.

The following items shall be furnished by the Contractor:

1.	Visqueen or other covering material for concrete curing.

2.	Separation geotextile.

3.	Concrete grout and mortar.

5.	Handhole lifting slings and lifting eyes.

6.	Arnco #SI 611 150 Y033 solid orange Innerduct 1-1/2"

7.	Electro Fusion Systems Coupler (Central part # 2"-coup-575-0042)

8.	Fusion Splicer (Central)

9.	Tracer wire XHHW #12 Awg. CU 600V UL listed E-11486 green.

10.	Marker Tape (Terra Tape extra stretch #540)

11.	Urethane Foam expanding 2 lbs./cu.ft.  (2 part)

12.	Innerduct Plugs

13.	All miscellaneous tools and hardware, and non-furnished material necessary to construct and install this system.

680-3.01  GENERAL CONSTRUCTION REQUIREMENTS.  The ATU Inspector reserves the right to suspend the conduit system installation, through the Engineer, at any time that the Contractor fails to meet the requirements set forth herein, until such time as the Contractor makes the necessary corrections. Suspension of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

The Contractor shall be responsible for locating, shoring and protecting of all property, (real and personal) in the vicinity of the project.  While ATU has endeavored to reflect the location of all sewer, water, storm drains, electric, telephone and gas lines, key boxes, valves and poles on its drawings, it shall be the Contractor's responsibility to establish the location of each facility by calling for field locates in accordance with Subsection 105-1.06, Cooperation with Utilities.

Once work commences, the Contractor, the Engineer, and ATU's Inspector shall meet once each week to review the work to date, and review the Contractor's schedule for the following week's work.  The Contractor shall submit in writing his anticipated hourly work shift schedule by the Wednesday noon prior to the work week.

All telephone handholes shall be constructed within an allowable tolerance of 0.1-foot of the plan location and elevation in any phase of the construction.  The Contractor will backfill all handhole and trench excavations within 48 hours.

The Contractor shall maintain trench alignment as far away as practical from the edge of the existing roadway.  This shall include the use of all wide shoulders, and turnouts, to provide maximum construction clearance from the traveled way, subject to the approval of the Engineer.

With the Engineer's approval, the Contractor may remove guardrail in areas where it impedes his progress.  Any removed guardrail shall be reconstructed within 24 hours of removal.

680-3.02  GENERAL INNERDUCT INSTALLATION REQUIREMENTS.  The Contractor shall be responsible for all handhole required openings.  Required openings not provided during fabrication shall be provided by the Contractor using a hacksaw, a hole saw, or a core drill subject to acceptance by the ATU Inspector.  Openings that have been cut through walls of masonry or concrete for the passage of innerduct shall be finished by grouting around the innerduct.  Expanding urethane foam will then be placed around the innerduct as shown on the plans.

Innerduct shall be cut, fusion spliced, and placed in accordance with the manufactures requirements, and as detailed on the plans.  Installation of tracer wire and marker tape shall be in accordance with the details shown on the plans.

In cases where the innerduct passes above or below an underground utility line, a minimum clearance of 12 inches shall be maintained.

Innerduct shall be laid to exact grade in the trench and the ends shall enter handholes horizontally and as indicated on the plans.  End bells shall be used on individual innerduct pieces where entering handholes except where another type of termination is specified or detailed on the plans.

Innerduct shall be shaded from sunlight as require to prevent curvature and deterioration due to thermal expansion and ultraviolet degradation.

Defective innerduct shall not be installed and shall be removed immediately from the site of the work.  Particular care shall be taken to keep concrete or other substances from the inside of the innerduct during construction.   All reinforcing materials and other magnetic materials installed shall be parallel to the lengths of the innerduct, except for anchoring material.

Prior to ATU installing cable in the innerduct, the innerduct shall be tested and cleaned.  Innerduct which will not be immediately used shall be plugged at each end and marked with an EMS marker by the Contractor.  All foreign material, earth, sand, and gravel shall be removed from the innerduct.  As a clearance test, the Contractor shall pass through the innerduct, a rigid mandrel with a length not less than 12 inches long and a diameter 1/4 inch less than the inside diameter of the innerduct, leaving in place the Omni Glide pull line.  The above requirements shall take place prior to the installation's acceptance by ATU.  The Contractor and the ATU Inspector shall measure and record the wall-to-wall distance of the installed innerduct, and record that measurement on the drawings provided by the Engineer.

At the Contractor's option, innerduct to be located more than 1 foot outside the fog line may be installed using either plowing methods or trenching methods as specified herein.

The Contractor shall maintain a complete and accurate record of duct offsets and sequential duct distances.  The Contractor shall supply the Engineer with a complete log of sequential distances on a per reel basis within 5 days after installation of each reel of innerduct.

680-3.03  ROAD CROSSING WITH SINGLE INNERDUCT.  A road crossing at Sta. EX 134+50 shall be installed in accordance with Detail #1 shown on the ATU plans.

The innerduct shall be trenched, bored, jacked, or otherwise forced underneath the highway or the innerduct may be installed in a casing.  There shall be no space between the earth and the outside of the innerduct or casing pipe.  No wet bores will be permitted.  Only enough water to lubricate the casing during installation may be used.

Casing pipe shall be installed using jacking equipment.  Casing shall be installed such that the hole is cased as the earth is removed through the interior of the casing.  Boring without the concurrent installation of the casing pipe will not be permitted. The installation shall be performed in a manner that will not disrupt traffic nor damage the subgrade, and will provide accurate alignment and grade of the pipe.

Smooth wall casing pipe shall be new and fabricated from welded steel.  The diameter and wall thickness of the casing shall be selected by the Contractor to allow installation in the type of materials encountered.

Joints in the casings shall be welded.  Pipe ends shall be machine cut and beveled at an angle of 37-1/2 degrees.  The beveled ends shall be butted and aligned axially and welded to provide a full strength joint capable of resisting all stresses, including the jacking stresses.

Before starting work on the crossing, the Contractor shall submit complete details of his proposed methods, materials, and time schedule to the Engineer.  Work shall not begin on the crossing until written notification to proceed has been obtained from the Engineer.

Casing pipe shall be a four (4) inch diameter steel bore casing.  Alignment of the bore casing shall be within two (2) feet of the staked requirements per one (1) hundred (100) feet of casing installed.  At no time shall the depth of the bore be less than that indicated on the plans. The successful bore shall meet the above requirements and allow for 97% utilization of the ordered bore size to be considered successful.  A stake at each end of the innerduct with the station and depth of the innerduct ends and an EMS marker on each end of casing shall be installed during backfill operations as detailed on the plans.

Existing asphalt to be removed shall be replaced with Asphalt Concrete, Type II in accordance with Section 401.  Temporary asphalt may be placed if the temperature limitations in subsection 401-3.01, Weather Limitation cannot be met.  If temporary asphalt is used, it shall be removed and replaced with Asphalt Concrete, Type II as soon as possible once the weather limitations can be met.

Removed asphalt shall be disposed of in accordance with the requirements of subsection 202-2.04, Removal of Pavement, Sidewalks, Curbs, Etc.  Disposal of waste excavation shall meet the requirements of subsection 680-3.09, Disposal of Waste Excavation.

Concrete slurry backfill shall meet the requirements of subsection 680-3.10, Concrete Slurry.

Sand bedding shall meet the requirements of subsection 680-3.11, Sand Bedding.

D-1 material shall meet the requirements of Section 301, Crushed Aggregate Base Course, Type D-1.

680-3.04  QUARRY CROSSING WITH DOUBLE INNERDUCT.  A crossing at Sta. EX 348+40 shall be installed in accordance with Detail #2 shown on the ATU plans.

Disposal of waste excavation shall meet the requirements of subsection 680-3.09, Disposal of Waste Excavation.

Concrete slurry backfill shall meet the requirements of subsection 680-3.10, Concrete Slurry.

Sand bedding shall meet the requirements of subsection 680-3.11, Sand Bedding.

680-3.05  INSTALLING INNERDUCT GREATER THAN 1 FOOT OUTSIDE FOG LINE.  Innerduct shall be installed in accordance with Detail #3 shown on the ATU plans.

Innerduct shall be laid in the center of the trench.  Winding, coiling, or snaking of the innerduct in the trench will not be allowed.  All rocks or other materials which could damage the innerduct shall be removed from the trench bottom before placing the innerduct.  The trench bottom shall be smooth.  Where a minimum cover of 36 inches cannot be maintained, the Contractor shall place, at the direction of the ATU Inspector, concrete slurry backfill.

Native material may be utilized for trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07, Selected Material, and shall also pass a 3-inch sieve.  Native backfill material shall be placed in layers and compacted as directed by the Engineer.

Disposal of waste excavation shall meet the requirements of subsection 680-3.09, Disposal of Waste Excavation.

Sand bedding shall meet the requirements of subsection 680-3.11, Sand Bedding.

680-3.06  INSTALLING INNERDUCT LESS THAN 1 FOOT OUTSIDE FOG LINE.  Innerduct shall be installed in accordance with Detail #4 shown on the ATU plans.

In cases where the innerduct passes above or below an underground obstruction such as a utility line, a minimum clearance of 6 inches shall be maintained from the concrete slurry backfill to the utility.  A minimum of 12 inches of clearance shall be maintained between the concrete slurry and a paralleling utility.

Removed asphalt shall be disposed of in accordance with the requirements of subsection 202-2.04, Removal of Pavement, Sidewalks, Curbs, Etc.  Disposal of waste excavation shall meet the requirements of subsection 680-3.09, Disposal of Waste Excavation.

Concrete slurry backfill shall meet the requirements of subsection 680-3.10, Concrete Slurry.

Sand bedding shall meet the requirements of subsection 680-3.11, Sand Bedding.

680-3.07  INSTALLING INNERDUCT BY PLOWING.  Innerduct to be installed by plowing shall be in accordance with Detail #5 shown on the ATU plans.  The innerduct plow shall be specifically designed for installing the innerduct.  Trial runs, using the proposed equipment, are required to demonstrate their abilities before actual plowing is started.  The Contractor shall demonstrate to the Engineer that the tension on the innerduct at the chute does not exceed manufacturer's recommended allowable tension.

1.	Prime Mover.  The principal factors which influence the size of the prime mover needed are soil conditions and required burial depth. The prime mover shall have an excess of horsepower to provide a smooth operation and allow the operator to focus his attention on the cable reel and cable.   The minimum size of the prime mover shall be a Caterpillar D7 or equivalent.

2.	Reel Carrier.  The reel carrier shall be configured so that the cable reels can be easily installed and shall be designed to carry reels at least 33 inches wide and 78 inches in diameter.  The reel carrier shall have a minimum load capacity of 6,000 pounds.  The reel spindle shall be at least 1/16 inch smaller but no more than 1/8 inch smaller than the reel arbor hole diameter.  Locking collars shall be used to keep the reel from sliding along the spindle bar. Either front or rear mounted cable reel carrier are acceptable.

3.	Conduit Delivery System.  The routing of the innerduct from the innerduct reel to the point of entry into feed chute is important.  All rollers or guides which cause a change in the direction of the duct path should have a minimum radius of 20 conduit diameters.

If an offset plow is used, the conduit path shall be configured to avoid any unnecessary changes in direction.  The duct feed system shall deliver the duct directly into the top of the plow chute without violating the minimum bending radius recommended for the duct.  A sheave or guide tube with the appropriate radius is recommended at this point.  Quadrants with closely spaced, multiple rollers (even though the diameter of each roller is small) may also be used if the radius of the quadrant is large enough.

4.	Conduit Feed Chute.  Conduit feed chutes shall be as manufactured by American Tractor Equipment Corporation or an acceptable equal.

The conduit path inside of the feed chute shall be free of burrs, sharp edges, or surfaces roughness.  Welds shall be smooth.  Gussets or stiffeners on the divider gate in multiple chute designs shall not interfere with the smooth passage of the duct. Clearances in the multiple chute configurations shall be maintained under operating conditions.  Divider gates shall not shift or deflect under load.  The feed chute shall have a removable gate to allow the conduit to be removed from or inserted into the feed chute at any intermediate point between splice locations.

5.	Plowing Procedure.  Before a plowing operation is started, the route ahead shall be prepared.  The route shall be graded to eliminate abrupt changes in vertical alignment.  However, every effort shall be made to minimize the damage to the environment by grading only where abrupt changes in grade would cause the plow to jerk the duct or otherwise adversely affect the placement.

Where large rocks, large amounts of fill, and other debris have been placed over the cable route, the Contractor shall blade the areas to natural grade before plowing.  After the cable has been installed, the material shall be placed back to its original position.

Ripping passes shall be made in the same direction as the cable being installed.  The final ripping pass shall be at a depth which exceeds the innerduct burial depth by a minimum of 6 inches.

During the innerduct placing operation, the conduit reel shall be tended at all times.  Free spinning or excessive tail load shall be prevented.  Start and finish pits and pits at points of intersection shall be excavated in advance.

The prime mover shall always be started slowly and speed increased gradually after all conduit slack is removed from the conduit delivery system.

The plow shank shall not be raised, lowered, or have its attitude changed unless the prime mover is moving forward and any changes in attitude shall be gradual.  The plow shall not be set at extreme forward rake angles.  All changes in depth shall be gradual with the vertical curve having a 4 foot or more radius.  The prime mover shall never be backed up with the plow in the ground.  If the conduit has to be removed from the chute, the plow shank shall be exposed by careful digging and the conduit slack pulled so that the conduit will not kink over the feed chute exit.

All excavation within 18 inches of the innerduct being installed by this Contract shall be made manually with hand tools.

If for any reason the innerduct is left exposed overnight on the right-of-way, the Contractor shall be responsible for the security of the innerduct.  He shall employ whatever means necessary to protect the exposed portion of innerduct from damage.

The Contractor, prior to installing innerduct and handhole No. I, shall construct a gravel pad as shown on the ATU plans.  Separation geotextile shall meet the requirements of Section 630, Geotextile for Embankment Separation and Reinforcement.  Borrow, Type A shall meet the requirements of subsection 703-2.07, Selected Material, and shall be constructed in accordance with the requirements of subsection 203-3.03, Construction of Embankments with Moisture and Density Control.  The Contractor shall provide a temporary access to the pad site at a location approved by the Engineer.

680-3.08  PRECAST CONCRETE HANDHOLES.  Handholes shall be installed in accordance with Detail #6 on the ATU plans.  In setting a handhole, the Contractor assumes all responsibility of the cost in transportation, installation, repair, and maintenance of the subject handhole until accepted by ATU.  During the placement of a handhole, if the gravel foundation proves to be inadequate to support the handhole to designed line or elevation, the Contractor shall remove the handhole and recompact to meet the requirements shown on the plans.

The handhole sections and the frame and covers will be primed and sealed with the ATU-furnished primer and gasket sealant (RAMNEK).  The Contractor shall install two 8-foot ground rods, one on each end of each handhole excavation, driven from the base level down, or at the direction of the ATU Inspector.  The Contractor will then connect the ground rods to the handhole ground wire leaving a 6-foot loop of that same wire inside the handhole as shown in the plans.  Tracer wire will be placed over the handhole and fastened to the cover base as depicted on the plans.  Tracer wire shall be continuous, and all splices shall be crimped, encapsulated, and watertight.

The handhole frame and cover shall be set to the designed finished grade of the proposed paving or existing ground level as designated by the Engineer.  An EMS marker shall be placed on top of handhole cover.

The Contractor shall excavate all unsuitable material, when directed by the ATU inspector, to a depth of one foot below the designed grade of all handholes and replace with Selected Material, Type A or Crushed Aggregate Base Course, Type D-1 bedding as required to bring the over-excavation up to the bottom grade of the handhole and compacted to 95% percent of the maximum density.  While the plans indicate elevations for handhole frames and covers, the Contractor shall field verify the exact elevations with the Engineer.

680-3.09  DISPOSAL OF WASTE EXCAVATION.  Waste excavation may be disposed of within the project limits at locations approved by the Engineer.  Waste disposal areas shall be feathered into surrounding grounds with no noticeable break or variation readily discernible and existing drainage patterns shall be maintained.

680-3.10  CONCRETE SLURRY.  The concrete slurry mixture shall contain a minimum of two (2) standard 94-lb sacks of cement per cubic yard of concrete.  Concrete slurry shall be placed when the air temperature is 32o F and above.  If the air temperature is below 32o F, the Contractor shall propose alternate methods to ensure adequate concrete curing temperatures will be met.  These may include concrete additives, additional cement, warming blankets, etc. and are subject to the approval of the Engineer.

680-3.11  SAND BEDDING.  Where existing material is unsuitable for innerduct bedding as determined by the ATU Inspector, the Contractor shall provide bedding sand meeting the following:

Sieve Size	Percent Passing by Weight

1/4-inch	100 %

No. 200	0 - 6%

680-3.12  SURVEYING AND STAKING.  Innerduct alignment shall be as far as practical from the edge of the existing roadway, subject to the approval of the Engineer and ATU.  All handholes and telephone duct shall be located and staked at the alignment and elevations indicated on the plans.  It shall be the Contractor's responsibility to schedule a physical check of all line and grades prior to placing of any handholes and innerduct.  These elevation checks shall include bottom elevations and handhole top elevations, to assure adequate clearance for handhole frame and cover from final grade.  Handholes shall be staked at north corners.

680-3.13  AS-BUILT DRAWINGS.  Two (2) final red-lined as-built drawings shall be delivered to the ATU Inspector prior to final acceptance of the system by the owning Utility.  The Contractor shall maintain an accurate record of the underground location of all the telephone handholes and innerduct installed on the prints provided by ATU.  These shall include all references to the highway centerline, existing land marks, and exact locations of all handholes, line, grade and elevation changes.

680-3.14  ATU INSPECTION.  ATU may at any time have access to the project site for the purpose of inspection.  The Contractor agrees to notify ATU at least forty-eight hours prior to the start of this project.  The manner of undergrounding of the innerduct, materials, and equipment used therein, shall be subject to the inspection of ATU.  Prior to backfilling any trenches, the ATU Inspector will measure the innerduct conduit.  ATU will conduct a final inspection within ten (10) days of the Contractor's informing ATU's Inspector, in writing, that the project is complete.  Incomplete items (punch list) as noted in the final inspection report, shall be completed by the Contractor within ten (10) days of the final inspection.

680-4.01 METHOD OF MEASUREMENT.  Surveying and staking will be measured and paid for under Item 642(1), Construction Surveying.

Item 680(6), Install Telephone Handhole will be measured by the unit completed and accepted in final position.

Item 680(9), Telephone As-Builts will not be measured for payment.

Item 680(10), Single 1-1/2 Inch Innerduct Crossing will be measured by the linear foot with measurement made between marker stakes.

Items 680(11), 680(12), 680(13) and 680(14), will be measured by the linear foot for the type of installation performed.  Measurement will be made from the outside of the handhole to the outside of the next handhole.

680-5.01  BASIS OF PAYMENT.  Payment for Item 680(6), Install Telephone Handholes will be full compensation for installing ATU furnished precast concrete handholes.  No separate payment will be made for excavation, bedding, backfill, ground rods and ground wire, knockout openings with urethane foam, tracer wire, frame and cover, EMS marker, and other items necessary to install a completed unit.  These items will be subsidiary to the Telephone Handhole.

Payment for Item 680(9), Telephone As-Builts will be full compensation for providing 2 sets of red-lined drawings as described above.

Payment for Item 680(10), Single 1-1/2 Inch Innerduct Crossing will be full compensation for installing the innerduct by trenching or boring.  No separate payment will be made for removal of asphalt, excavation, concrete slurry backfill, sand bedding, D-1 fill, replacement of asphalt concrete, (including placing and removing temporary asphalt, if necessary), tracer wire and marker tape, and any other items necessary to complete the installation.  These items will be subsidiary to the Single 1-1/2 Inch Innerduct Crossing.  If boring is substituted for the trench crossing, payment for the boring will be made under 680(10), Single 1-1/2 Inch Innerduct Crossing and will include installing 4-inch steel casing pipe, marker stakes, EMS markers, and any other items necessary to complete the installation.

Payment for Item 680(11), Double 1-1/2 Inch Innerduct Crossing will be full compensation for installing two innerducts in the same trench.  No separate payment will be made for excavation, concrete slurry backfill, sand bedding, tracer wire and marker tape, and any other items necessary to complete the installation.  These items will be subsidiary to the Double 1-1/2 Inch Innerduct Crossing.

Payment for Item 680(12), 1-1/2 Inch Innerduct, installed by trenching will be full compensation for installing the innerduct in areas outside 1 foot from the fog line where trenching is used.  No separate payment will be made for excavation, sand bedding, backfill, shoring or otherwise protecting adjacent property, tracer wire and marker tape, and any other items necessary to complete the installation.  These items will be subsidiary to the Innerduct installation.

Payment for Item 680(13), 1-1/2 Inch Innerduct, installed by trenching with concrete slurry backfill will be full compensation for installing the innerduct in those areas within 1 foot of the fog line.  No separate payment will be made for

excavation, removal of asphalt, concrete slurry backfill, sand bedding, tracer wire and marker tape, and any other items necessary to complete the installation.  These items will be subsidiary to the Innerduct installation.

Payment for Item 680(14), 1-1/2 Inch Innerduct, installed by plowing will be full compensation for installing the innerduct in areas outside 1 foot from the for line where plowing is used.  No separate payment will be made for grading, plowing, backfill, installing a gravel pad and temporary access, removal and replacement of guardrail, and any other items necessary to complete the installation.  These items will be subsidiary to the Innerduct installation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

680 (6)	Install Telephone Handholes	 Each

680 (9)	Telephone As-Builts	Lump Sum

680(10)	Single 1-1/2 Inch Innerduct Crossing	Linear Foot

680(11)	Double 1-1/2 Inch Innerduct Crossing	Linear Foot

680(12)	1-1/2 Inch Innerduct,	Linear Foot

installed by trenching

680(13)	1-1/2 Inch Innerduct,	Linear Foot

installed by trenching with concrete slurry

680(14)	1-1/2 Inch Innerduct,	Linear Foot

installed by plowing

SECTION 702

ASPHALT MATERIALS

Standard Modifications

702-2.04  STORAGE AND APPLICATION TEMPERATURES.  In Table 702-1, change storage temperatures for Acs from "340 Max" to "325 Max".  (5/12/89)M23

SECTION 703

AGGREGATES

Standard Modifications

703-2.01  FINE AGGREGATE FOR CONCRETE.  In the first sentence, insert ", class A," after "AASHTO M 6".

Add the following:  AASHTO T 104 shall be performed using sodium sulphate solution.

The maximum mass percent of material finer than No. 200 sieve in (a), concrete subject to surface abrasion, shall be 3.0.

703-2.02  COARSE AGGREGATE FOR CONCRETE.  In the first sentence, insert ", class B," after "AASHTO M 80".

(5/12/89)M24

703-2.03 AGGREGATE FOR BASE.  Add the following to the list under the first paragraph:

Plastic Index      AASHTO T-90        6 max

(5/7/91)M45

Special Provisions

703-2.03  AGGREGATE FOR BASE.  Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading D-1 | Grading E-1 |
| --- | --- | --- |
| 1 inch | 100 | 100 |
| 3/4 inch | 70-100 | 70-95 |
| 3/8 inch | 50-79 | 60-86 |
| No. 4 | 35-58 | 40-65 |
| No. 8 | 20-47 | - |
| No. 30 | 10-26 | 15-30 |
| No. 50 | 6-19 | - |
| No. 200 | 0-6 | 8-13 |

(10/1/91)R117

Standard Modifications

703-2.04  AGGREGATE FOR PLANT MIX ASPHALT PAVEMENT.  Replace this subsection with the following:

Coarse Aggregate.  Coarse aggregate (that material retained on the No. 4 Sieve) shall be crushed stone or crushed gravel and shall consist of sound, tough, durable rock of uniform quality.  All material shall be free from clay balls, vegetative matter or other deleterious matters.  Coarse aggregate shall not be coated with dirt or other finely divided mineral matter.  In addition, coarse aggregate shall meet the following requirements:

Percent of Wear	AASHTO T 96	45 max.

Degradation Value	ATM T-13	30 min.

Percent Sodium Sulfate loss	AASHTO T 104	9 max. (5 cycles)

Percent Fracture	ATM T-4	80 min. single face

Thin-Elongated Pieces	ATM T-9	8 % max.

Fine Aggregate.  Fine aggregate (passing the No. 4 sieve) shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness Test.

Blended Aggregate.  The several aggregate fractions for the mixture shall be sized, graded, and combined in such proportions that the resulting composite blend conforms to the grading requirements of Table 703-3.  The fraction actually retained between any two consecutive sieves larger than the No. 100 shall be not less than 2 percent of the total.  Aggregate gradations shall be determined by ATM T-7.  The size of extracted samples for gradation shall be in conformance with AASHTO T 164.

TABLE 703-3

BROAD BAND GRADATIONS FOR ASPHALT

CONCRETE PAVEMENT AGGREGATE

Percent Passing by Weight

| Sieve Designation | Gradation Designation |  |  |
| --- | --- | --- | --- |
|  | Type I | Type II | Type III |
| 1 inch | 100 | - | - |
| 3/4 inch | 75-90 | 100 | - |
| 1/2 inch | 60-86 | 75-90 | 100 |
| 3/8 inch | 50-78 | 60-88 | 75-90 |
| No. 4 | 34-62 | 44-72 | 50-78 |
| No. 8 | 24-52 | 30-58 | 32-60 |
| No. 16 | 16-42 | 20-44 | 20-45 |
| No. 30 | 10-32 | 12-34 | 12-34 |
| No. 50 | 8-24 | 8-24 | 8-24 |
| No. 100 | 5-16 | 5-16 | 4-15 |
| No. 200 | 3-8 | 3-8 | 3-8 |

(7/16/93)M62

703-2.07  SELECTED MATERIAL.  Add the following to Item 1., Selected Material, Type A:  It shall have 30 to 55 percent by weight of particles passing the No. 4 sieve.  (10/1/91)R74 R89

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.15  TEMPORARY RAISED PAVEMENT MARKERS.  Add the following:  The temporary raised pavement markers shall be installed utilizing an approved raised pavement marker flexible bituminous adhesive.

The color of the raised pavement markers shall conform to the color of the marking for which they supplement, substitute, or serve as a positioning guide.

712-2.16  TEMPORARY RAISED PAVEMENT MARKERS FOR SHORT-TERM OPERATIONS, SEAL COATS, AND SURFACE TREATMENTS.  Add the following subsection:  The marker shall consist of an L-shaped polyurethane body with retroreflective tape on the top vertical section and with a self-adhesive base.  Both faces of the yellow marker and one face of the white marker shall be reflectorized.  The marker body shall be made from 0.060 inch minimum thick polyurethane; the vertical leg shall be approximately 2 inches high by 4 inches wide and the base approximately 1-1/8 inches wide.  The polyurethane body shall conform to Table 712-1.

The adhesive shall be factory-applied to the marker base, and made of a pressure-sensitive material, a minimum 1/8 inch thick and 3/4 inch wide, with release paper.

Where chip seals, slurry seals or tack coats are to be utilized after placement of the temporary raised pavement markers, the markers shall come with a protective cover made of clear flexible polyvinyl chloride.

The reflective tape shall be metalized polycarbonate microprism retroreflective material with acrylic backing or equal, a minimum 0.25 inch wide by 4 inches long, and provide the minimum optical performance shown in Table 712-2, for an observation angle of 0.2 degrees.

TABLE 712-1

| PROPERTY | RESULT | ASTM TEST METHOD |
| --- | --- | --- |
| Specific Gravity (min.) | 1.19 | D 792 |
| Hardness | 80A | D 2240 |
| Tensile Strength (psi, min.) | 4600 | D 412 |
| Ultimate Elongation (percent, min.) | 330 | D 412 |
| Modulus at 300 percent (psi, min.) | 1000 | D 412 |
| Stiffness @ -20o F (psi, min.) @ +72o F (psi, min.) | 1700 900 | D 1053 D 1053 |
| Compression Set 22 hr. @ 70o C (percent, max.) | 65 | D 395 |
| Taber Abrasion CS17 wheel wt. loss (mg/1000 cycles) | 3 | --- |

TABLE 712-2

| Horizontal Entrance Angle | Specific Intensity* |  |
| --- | --- | --- |
|  | White | Yellow |
| 0 degrees | 3.5 | 3.0 |
| 30 degrees | 2.7 | 1.7 |

* Candelas per footcandle of illumination at the reflector on a plane perpendicular to the incident light.

(5/7/91)S61

SECTION 716

STRUCTURAL STEEL

Special Provisions

716-2.03  HIGH TENSILE STRENGTH BOLTS.  Add the following:  All high strength bolts, except A490 bolts, shall be galvanized.

Galvanized tension control bolts will be considered equivalent to the bolts specified.

Standard Modifications

716-2.03  HIGH TENSILE STRENGTH BOLTS.  Add the following:  All bolts, nuts, and washers are to be marked with a symbol identifying the manufacturer as required in ASTM A325 Section 14, A490 Section 15, A563 Section 10.7 and 10.8, A194 Section 14, and F436 Section 14.  The supplier shall provide the symbol and address of each manufacturer for all the bolts, nuts, and washers supplied to the project.

The supplier's certification shall provide a corresponding lot number appearing on the shipping package and the certification.  The supplier's certification shall note when and where all testing was done, including the rotational-capacity tests indicated below, and include zinc thickness when galvanized bolts and nuts are used.

The maximum hardness for AASHTO M 164(A325) bolts shall be 33Rc.  The maximum tensile strength shall be 150ksi for bolts 1 inch or less in diameter and 120ksi for larger bolts.

Nuts shall be Grade 2H or DH for black or galvanized fasteners.  For galvanized fasteners the nuts shall be overtapped to the minimum amount required for the fastener assembly.  All nuts, bolts and washers shall have the manufacturers markings on them.

All galvanized nuts shall be lubricated with a lubricant containing a visible dye so a visual check can be made for the lubricant at the time of field installation.  Black bolts shall be "oily" to the touch when installed.  Weathered or rusted bolts shall be cleaned and re-lubricated prior to installation.

High-strength fasteners, black or galvanized, shall be subjected to a rotational-capacity test (AASHTO M 164, Section 8.5) and shall meet the following requirements:

1.	They shall go through two times the required number of turns (from snug tight conditions) indicated in the 1988 Interim AASHTO Bridge Specification, Table 10.17B, in a Skidmore-Wilhelm Calibrator, or equivalent tension measuring device, without stripping or failure.

2. 	During this test, the maximum recorded tension shall be equal to or greater than 1.15 times the Required Fastener Tension, AASHTO Table 10.17A.

3.	The measured torque to produce the Required Fastener Tension shall not exceed the value obtained by the following equation:

Torque = 0.25 PD

Where:  Torque = Measured Torque (Foot-Pounds)

P      = Measured Bolt Tension (Pounds)

D      = Nominal Diameter (Feet)

Proof load tests (ASTM F 606 Method 1) are required for the bolts.  Wedge tests of full size bolts are required in accordance with Section 8.3 of AASHTO M 164.  Galvanized bolts shall be wedge tested after galvanizing.  Proof load tests (AASHTO M 291) are required for the nuts.  The proof load tests for nuts to be used with galvanized bolts shall be performed after galvanizing, overtapping and lubricating.

All galvanized nuts shall be lubricated in accordance with ASTM A563 Section 4.8.  In addition the name, method of application, and dilution of the lubrication applied to the nuts shall be provided with the documentation.

Section 7.4 of ASTM A563 shall be deleted and Section 7.5 changed to read as shown below.  These requirements also apply to 2H nuts covered under ASTM A194.

7.5  Nuts to be used on bolts mechanically zinc coated or on bolts hot-dip zinc-coated, shall be tapped oversize by a diametral amount sufficient to permit assembly on the coated bolt thread, unless other requirements are specified in the inquiry or purchase order.

(5/12/89)M26

SECTION 720

ELASTOMERIC PADS

Special Provisions

720-2.01.  Delete this subsection in its entirety and substitute the following:  Elastomeric bridge bearing pad shall conform to the requirements of AASHTO M 251 with the latest interims and the following revisions:

4.	MATERIALS

4.1  Properties of the Elastomer.  Delete the first sentence and substitute the following:  The elastomeric compound used in the construction of the bearings shall contain only virgin natural polyisoprene (natural rubber) as the raw polymer; neoprene shall not be used.  Properties and requirements elsewhere in AASHTO M 251 pertaining solely to polychloroprene (neoprene) shall not be applicable.

5.	FABRICATION

Add the following paragraph:

5.5.  Pads over three-quarters of an inch in thickness shall be laminated and shall consist of alternate laminations of elastomer and metal reinforcements.  The outside laminations shall be metal.  Laminations of elastomer shall be 1/2 inch +1/8 inch in thickness.

8.	BEARING TESTS AND ACCEPTABLE CRITERIA

8.2.2.  Delete Note 1 in its entirety and add the following paragraph:  The elastomer shall also be tested for ozone resistance under ASTM D-1149, method A at 100 degrees F, 20 percent strain, partial pressure of ozone - 50 mpa, and 100 hours.  It shall show no cracks.

8.2.4.  Delete in its entirety and substitute the following:  A minimum of one pad per lot shall be tested for bond strength as follows:

Steel Laminations - ASTM D-429, method B - 40 lb/in., minimum.

Fabric Laminations - California Test No. 663 - 40 lb/in., minimum.

8.2.5.  Delete the word "Optional."

9.	TESTING

9.1.  Delete the word "Optional."

(6/11/93)R152

Add the following to the requirements of AASHTO M 251:  Tidewater Slough Bridge is in temperature zone D.  Elastomer compound shall be low temperature Grade 4.

SECTION 724

SEED

Special Provisions

724-2.02  MATERIALS.  Add the following to Table 724-1:

| SEED TYPE | GERMINATION PERIOD | PERCENT PURITY | PERCENT GERMINATION | PERCENT SPROUTABLE SEED |
| --- | --- | --- | --- | --- |
| Bering Hairgrass | 14 | 95 | 75 | 71 |

(5/12/89)M28

SECTION 726

TOPSOIL

Standard Modifications

726-2.01  TOPSOIL.  In the second paragraph, change "not less than 1%" to read "not less than 3%".  (5/12/89)M29

Special Provisions



726-2.01  TOPSOIL.  Delete the fertilizer requirements as stated in this subsection.

Add the following:  Fertilizer shall be applied as stated in Section 618.  (5/15/92)R139

This page left blank intentionally.

SECTION 729

GEOTEXTILES

Special Provisions

729-2.02  SUBSURFACE DRAINAGE AND EROSION CONTROL GEOTEXTILE.  Delete this subsection in its entirety and substitute the following:  Geotextile materials for riprap liner shall meet the requirements of AASHTO M 288 for Class B Erosion Control, except that the minimum permeability of the fabric shall be 0.010 cm/sec.

729-2.04  SEDIMENT CONTROL.  Add the following subsection:  Geotextile materials for Sediment Control shall meet the requirements of AASHTO M 288 for Sediment Control, except that the minimum permeability of the fabric shall be 0.002 cm/sec.

(5/17/93)R97

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04  SIGN POSTS.  Under item 1., Metal Pipe Posts, add the following to paragraph a.:  Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Standard Modifications

730-2.04  SIGN POSTS.  Under Item 2., a., replace the second sentence with the following:  Sheets for post fabrication shall be zinc coated in accordance with ASTM A 525, coating designation G 90.

(7/2/93)M57

APPENDIX A

CONSTRUCTION OR MAINTENANCE

NEAR ELECTRICAL FACILITIES

and

ELECTRICAL FACILITY CLEARANCE REQUIREMENTS

APPENDIX B

PERMITS

APPENDIX C

CONSTRUCTION SURVEYING REQUIREMENTS