SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

1.	Publications.  The following are available from the Plans Room, download online, or as noted:

a.	Standard Specifications for Highway Construction, 2020 Edition comb bound ($25.00), download at:

www.dot.state.ak.us/stwddes/dcsspecs/assets/pdf/hwyspecs/sshc2020.pdf, or order bound book from LuLu at:

https://www.lulu.com/en/us/shop/state-of-alaska-dept-of-transportation/2020-alaska-standard-specification-for-highway-construction/paperback/product-1gq9j9qk.html

b.	Alaska Test Methods Manual (Lab & Field), May 30, 2020 Edition ($25.00). Available online at:

www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/testman.shtml

c.	Alaska Storm Water Pollution Prevention Plan Guide, March 2017.

www.dot.state.ak.us/stwddes/desenviron/resources/stormwater.shtml

d.	Utility facility clearance requirements. Available online at:

	Chugach Electric Association, Inc. (CEA) Electrical Facility Clearance Requirements

Chugach Electrical Facility Clearance Requirements 2020

	ENSTAR Natural Gas Company (ENSTAR)

www.enstarnaturalgas.com/safety-education/natural-gas-safety/safety-for-excavators-contractors/

e.	Quantity Computations

f.	Cross Sections

g.	Geotechnical Reports:

- Foundation Geology Report, Embankment Seward Highway Rehabilitation MP 75-90, 58105 (CFHWY00212), October 2016, Shannon & Wilson

- Foundation Geology Report, Placer River Overflow Bridge No. 627: Seward Highway Rehabilitation MP 75-90, CFHWY00213, October 2015, Shannon & Wilson

- Foundation Geology Report, Placer River Bridge No. 629: Seward Highway Rehabilitation MP 75-90, CFHWY00213, October 2015, Shannon & Wilson

- Foundation Geology Report, Portage Creek #1 Bridge No. 630: Seward Highway Rehabilitation MP 75-90, CFHWY00213, October 2015, Shannon & Wilson

- Foundation Geology Report, Portage Creek #2 Bridge No. 631: Seward Highway Rehabilitation MP 75-90, CFHWY00213, October 2015, Shannon & Wilson

- Foundation Geology Report, Twenty Mile River Bridge No. 634: Seward Highway Rehabilitation MP 75-90, CFHWY00213, October 2015, Shannon & Wilson

- Geotechnical Data Report: MP 88 Borrow Source Explorations. Seward Highway MP 75-90, 58105 (CFHWY00212), November 2016, Shannon & Wilson

h.	Erosion, Sediment Control Plan (ESCP): Seward Highway MP 75-90, CFHWY00213, Portage Curve Multimodal Connector, CFHWY00308, March 2021, DOT&PF/HDR

i.	Traffic Control Plan (TCP): Seward Highway MP 75-90, CFHWY00213, March 2021, HDR

j.	Phase I Survey Control Sheet (SCS): Seward Highway MP 75-90 Phase I, CFWHY00212

k.	Existing Bridge As-Builts and shop drawings (bridges 627, 629, 630, 631, & 634)

l.	XML File – XML FILES. XML file type for the original ground surface is available on the Department’s advertising website. The department expressly states that these SML files are for informational purposes only. The Department makes no representation, warranty, or guarantee, expressed, implied, or statutory, as to the accuracy, reliability, suitability, functionality, or results derived from the use of the information contained therein. The Department shall not accept, review, hear or consider any bid protest or construction claims arising from use of the information.

2.	Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix C.

3.	Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

4.	Section 120, Disadvantaged Business Enterprise (DBE) Program.  The Department, in coordination with US DOT, has adopted a Race-Neutral DBE Program effective for Federal-aid projects advertised in Central Region after June 30, 2015.  In particular, all bidders shall be aware that Good Faith Effort Documentation is required from the successful bidder for all contracts, regardless of DBE goal or DBE utilization, in accordance with Section 120 Disadvantaged Business Enterprise (DBE) Program.

The overall DBE Utilization Goal is revised to 8.83 percent.

Direct questions about this notice to the Manager of the Civil Rights Office, (907) 269-0848, http://www.dot.state.ak.us/cvlrts/index.shtml.

5.	Cargo Preference Act Requirements. The provisions of the Cargo Preference Act (CPA) must be physically incorporated into all Federal-aid Projects awarded after February 15, 2016, and must be physically incorporated in all agreements with subcontractors and lower tier subcontractors.

Form 25D-55 (2/16) is revised to include the CPA provisions to the Required Contract Provisions for Federal-Aid Construction Contracts.  See the last page of Form 25D-55 for the CPA requirements.

For additional details, please visit: https://www.fhwa.dot.gov/construction/cqit/cargo.cfm

6.	Buy America Act. On December 22, 2015, U.S. District Court for the District of Columbia issued a decision vacating the Federal Highway Administration (FHWA) 90 percent threshold exemption for manufactured steel and iron products and the miscellaneous steel or iron components, subcomponents and hardware waiver.  As a result of the federal court decision, FHWA withdrew their December 21, 2012 policy memorandum clarifying provisions of the Buy America Act requirements.

7.	Prohibition on Certain Telecommunications and Video Surveillance Services or Equipment. 2 CFR 200.216, as amended effective August 13, 2020, Federal Register, Vol. 85, No. 157, 49506 – 49582, Prohibition on certain telecommunication and video surveillance services or equipment.  Refer to Subsection 106-1.01.

8.	Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0644.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

Refer to Section 651 regarding additional restrictions on notifications prior to any disturbance, relocations, and/or disconnections of Fiber Optic lines on the project.

9.	COVID-19 Management Plan. The Governor's emergency declaration and mandates relating to COVID-19 expired on February 14, 2021. However, contractors are encouraged to review COVID-19 Response and Recovery Health Advisories that can be accessed at:

https://covid19.alaska.gov/health-advisories/

Contractors will still be required to meet any applicable local ordinances or requirements currently in effect, and comply with any future federal, state or local declarations or mandates that might be adopted while work on the project is ongoing.

Consistent with Section 107-1.01 of the Standard Specifications for Highway Construction, the Contractor will be responsible for paying all costs and expenses incurred to comply with any COVID-19 Health Mandates or Health Advisories in effect during times when the Contractor is performing project-related work activities. The Contractor will additionally be responsible for preparing any general or site-specific mitigation and response plans required for its forces, along with any attendant schedule delays or impacts.

10.	Certified Payroll. Certified payroll must be submitted electronically through AASHTOWare for contracts awarded after January 1, 2021.

In order to submit certified payroll, Contractors, Subcontractors, and lower tier Subcontractors must be active in AASHTOWare, which requires they have a valid Vendor ID with a 913 commodity code.

To obtain a Vendor ID, register with the State of Alaska via the Vendor Self-Serve (VSS). Instructions for creating a new account in the VSS system can be found under the Job Aids at the following link:

https://iris-vss.alaska.gov/webapp/PRDVSS1X1/AltSelfService

For information on certified payroll, contact the Department of Labor and Workforce Development, Wage and Hour Administration:	Juneau	(907) 465-4842

Anchorage	(907) 269-4900

Fairbanks	(907) 451-2886

DOT&PF AASHTOWare Project guidance, including schedule, FAQs, training options:

http://dot.alaska.gov/aashtoware/

11.	Interim Completion Phase.  This project includes at least one interim completion phase.  Refer to Subsection 651-1.05 Interim Completion and Subsection 652-1.05 Failure to Complete on Time for further information.

12.	Asphalt Material Price Adjustment.  The unit price adjustment for asphalt material will be combined and paid under one Pay Item. Refer to Sections in Division 300 and 400 that include an "Asphalt Material Price Adjustment" Pay Item.

13.	Escrow of Bid Documentation Affidavit.  Refer to Subsection 103-1.11 Escrow of Bid Documentation. The form "Escrow of Bid Documentation Affidavit" is included at the end of Subsection 103-1.11 and is required as part of this Contract.

14.	Limitation of Operation. Limit disturbed unstabilized ground. Refer to Subsection 652-1.04 Limitation of Operation for further information.

15.	Construction Access onto National Forest System Lands:  To facilitate access onto National Forest System lands for construction of project components, the Contractor will be required to obtain a Special Use Permit from the Chugach National Forest, Glacier Ranger district.  A draft copy of this permit is located in Appendix G.

16.	Material Disposal at Freestone Pond:  The Chugach National Forest, Glacier Ranger District has identified Freestone Pond as a possible disposal site for the following materials.  The Contractor may coordinate with Glacier Ranger District staff regarding the details of this disposal site.

- 5,700 Cubic Yards of Fine Mineral Soil

- 5,700 Cubic Yards of Organic Muck

17.	Existing and Excess Pile: Refer to 106-1.07 Department Furnished Material on existing pile to be used on the project and Subsection 505-3.07 Pile Transport on excess pile upon project completion.

FED_SOA-CRSNtB-030521_SSHC2020 / CFHWY00213 / CFHWY003008

Blank Page

PART 4

STANDARD MODIFICATIONS
AND
SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2020

EDITION

Blank Page

TABLE OF CONTENTS

Section	Page

DIVISION 100 — GENERAL PROVISIONS

103	Award and Execution of Contract	3

104	Scope of Work	8

105	Control of Work	9

106	Control of Material	10

107	Legal Relations and Responsibility to Public	12

108	Prosecution and Progress	15

109	Measurement and Payment	16

DIVISION 200 — earthwork

201	Clearing and Grubbing	19

202	Removal of Structures and Obstructions	20

203	Excavation and Embankment	22

204	Structure Excavation for Conduits and Minor Structures	23

205	Excavation and Fill for Major Structures	26

602	Filter Blanket	27

DIVISION 300 — BASES

301	Aggregate Base and Surface Course	31

304	Subbase	33

306	Asphalt Treated Base Course	34

318	Foamed Asphalt Stabilized Base Course	46

DIVISION 400 — ASPHALT PAVEMENTS AND SURFACE TREATMENTS

401	Hot Mix Asphalt Pavement	57

402	Tack Coat	76

406	Rumble Strips	77

DIVISION 500 — STRUCTURES

503	Reinforcing Steel	83

505	Piling	87

507	Bridge Barriers and Railing	89

508	Waterproofing Membrane	90

510	Removal and Repair of Concrete Bridge Deck	91

550	Commercial Concrete	93

DIVISION 600 — MISCELLANEOUS CONSTRUCTION

602	Structural Plate Pipe	97

603	Culverts and Storm Drains	103

606	Guardrail	108

608	Sidewalks	117

611	Riprap	124

615	Standard Signs	125

617	Railroad Crossings	130

618	Seeding	134

619	Soil Stabilization	137

622	Rest Area Facilities	142

633	Silt Fence	144

634	Geogrid Soil Reinforcement	145

639	Driveways	147

641	Erosion, Sediment, and Pollution Control	148

642	Construction Surveying and Monuments	175

643	Traffic Maintenance	195

644	Services to be Furnished by the Contractor	218

645	Training Program	222

646	CPM Scheduling	225

647	Equipment Rental	226

651	Control of Work – Supplemental Requirements	228

652	Prosecution and Progress – Supplemental Requirements	234

654	Monitor	235

661	Electrical Load Centers	247

669	Automated Traffic Recorders	250

670	Traffic Markings	263

682	Utility Potholing	268

686	Alaska Railroad Coordination	270

DIVISION 700 — MATERIALS

702	Asphalt Materials	273

703	Aggregates	274

706	Concrete and Plastic Pipe	276

710	Fence and Guardrail	277

712	Miscellaneous	278

715	Steel for Piles	279

724	Seed	282

722	Bridge Railing	285

726	Topsoil	286

727	Soil Stabilization Material	287

730	Sign Materials	292

731	Waterproofing Membrane	294

740	Signals and Lighting Materials	295

Appendix A	Construction Survey Requirements

Appendix B	Environmental Permits

Appendix C	Material Certification List

Appendix D	Sign Shop Drawings

Appendix E	ARRC Letter of Non-Objection and TCP

Appendix F	USFS Draft Special Use Permit

Appendix G	Wildlife Observer Protocol

DIVISION 100 — GENERAL PROVISIONS

Blank Page

SECTION 103
AWARD AND EXECUTION OF CONTRACT

Special Provisions

Add the following Subsection 103-1.11 Escrow of Bid Documentation:

103-1.11 ESCROW OF BID DOCUMENTATION.  Furnish a legible copy of your Bid documentation and an affidavit, as instructed in writing by the Contracting Officer.  Bid documentation consists of written documentation of quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and other information used to prepare your Bid for this project.

Obtain and furnish the same level of bid documentation, for each subcontractor, supplier or fabricator with a subcontract or agreement exceeding $200,000, regardless of tier.  Seal each entity’s documentation in separate envelopes, labeled with the entity’s name and address, submission date, and project name and number.  Include a cover letter or quote signed by a responsible party.

Meet the following requirements:

1.	Submitting Bid Documentation.  Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number.  Deliver the sealed container to the Department-designated document Depository for safekeeping.

2.	Affidavit.  Submit directly to the Contracting Officer a signed and certified affidavit attesting that:

a.	The affiant has examined the bid documentation and that it includes all documents used to prepare the bid;

b.	The sealed container contains all bid documentation submitted;

c.	The escrow materials were relied on to prepare the bid; and

d.	Should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

3.	Access and Use of Escrow Documents. The bid documentation will remain in escrow, without access by either party, except as otherwise provided herein.  In the event the Contractor (1) provides notice of intent to claim, (2) a claim, (3) a contract change order, or (4) initiates contract related litigation, the Department may obtain copies of the bid documentation as provided herein.

Both parties will submit to the Depository and copy to each other a list of personnel that are authorized to access the escrow documents.  Use forms provided by the Depository.

Upon request, the Depository will set the time and place for access to escrow documents, will monitor the escrow documents review, and will arrange for a method of copying escrow documents.  Access to escrow documents shall require at least five days advance written notice so that the other party has the opportunity to witness the escrow review, examination and use.  There is no requirement that both parties witness the escrow document review, but if one party is absent then the review must occur in the presence of a neutral third party observer to be designated by the Depository.

Notwithstanding paragraph five below, the Department will be allowed: to make copies of any and all escrow documentation (whether hard copy, electronic, or otherwise); to use and review any copies made whether in the presence of the Contractor, or not; and to share copies with staff and consultants directly involved in the subject dispute.

Distribution is not authorized except as related to resolution of a dispute.  The Department will be allowed to incorporate pertinent copies as supporting documentation in all significant contract change orders, contractual disputes, and the settlement of disputed claims.

The Department is not liable for any Contractor costs associated with escrow review and use.

4.	Failure to Provide Bid Documentation.  Refusal or failure to provide bid documentation or affidavit renders your bid non-responsive.  Failure or refusal to provide Subcontractor bid documentation, will result in subcontract disapproval.

5.	Confidentiality of Bid Documentation.  Materials held in escrow are your property.  Except as otherwise provided herein, the escrow materials cannot be released without your approval.

6.	Cost and Escrow Instruction.  The Department pays to store escrowed materials and instructs the Depository regarding escrow.

7.	Payment.  Include within the overall Contract bid price costs to comply with this subsection.

8.	Return of Escrow Documentation.  The original escrow documents will be returned to you once litigation is concluded, outstanding claims are resolved, you have completed the Contract, and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed.

ES11-010106

Blank Page

ESCROW OF BID DOCUMENTATION AFFIDAVIT

THE UNDERSIGNED HEREBY CERTIFIES THAT THE ESCROW OF BID DOCUMENTATION CONTAINS ALL OF THE INFORMATION THAT WAS USED TO DEVELOP THE BID AND THAT I HAVE PERSONALLY EXAMINED THESE CONTENTS AND THAT THE DOCUMENTATION IS CORRECT AND COMPLETE IN ACCORDANCE WITH SUBSECTION 103-1.11. SUBMITTAL BY THE CONTRACTOR OF A CLAIM, WHICH IS NOT CONSISTENT WITH THE CONTENTS OF THESE BID PREPARATION DOCUMENTS, SHALL RESULT IN DENIAL OF THE CLAIM.

By:

Title:

Firm:

Date of Submission:

Project Number:

CREscrowBidAffidavit-050509

Blank Page

SECTION 104
SCOPE OF WORK

Special Provisions

104-1.06 VALUE ENGINEERING CHANGE PROPOSALS BY CONTRACTOR.

Replace 104-1.06.3.e with the following:

e.	The Contractor may submit VECPs for an approved subcontractor. If the Contractor elects to submit a VECP for an approved subcontractor and it is subsequently accepted by the Department, the Department will reimburse the Contractor per 104-1.06.5.

CR104.HSM20.2-113020

SECTION 105
CONTROL OF WORK

Special Provisions

Add the following Subsection 105-1.011 Related Sections:

105-1.011 RELATED SECTIONS.

Section 651, Control of Work – Supplemental Requirements

CR105.5-012816R

SECTION 106
CONTROL OF MATERIAL

Special Provision

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.

Add the following:

PROHIBITION ON CERTAIN TELECOMMUNICATION AND VIDEO SURVEILLANCE SERVICES OR EQUIPMENT. On projects using federal funds, the Contractor shall comply with the requirements of 
2 CFR 200.216, as amended effective August 13, 2020, Federal Register, Vol. 85, No. 157, 
49506 – 49582, Prohibition on certain telecommunication and video surveillance services or equipment.

Contractor shall submit documentation acceptable to the Department certifying it has not entered into a contract nor extended or renewed a contract to procure or obtain equipment, services, or systems that uses covered telecommunications equipment or services as a substantial or essential component of any system, or as critical technology as part of any system produced by:

	Huawei Technologies Company or ZTE Corporation (or any subsidiary or affiliate of such entities).

	Hytera Communications Corporation, Hangzhou Hikvision Digital Technology Company, or Dahua Technology Company (or any subsidiary or affiliate of such entities).

	Any entity that the Secretary of Defense, in consultation with the Director of the National Intelligence or the Director of the Federal Bureau of Investigation, reasonably believes to be an entity owned or controlled by, or otherwise connected to, the government of a covered foreign country.

The Contractor shall further certify that it has complied with the requirements of 2 CFR 200.216, as amended effective August 13, 2020, Federal Register, Vol. 85, No. 157, 49506 – 49582 and that it will continue to do so throughout the term of the Contract.

CR106.2-081320R

Delete 106-1.07 in its entity and replace it with the following:

106-1.07 DEPARTMENT-FURNISHED MATERIAL. The Department will furnish to the Contractor the following material located at Northland / Boyer Logistics Inc. at 7201 2nd Avenue South, Seattle, Washington 98108:

| Description | Quantity | Length |
| --- | --- | --- |
| Structural Steel Piles (4'-0" dia. x 1" Pipe), Bare Steel | 262 pieces | ~40 LF each |
| Structural Steel Piles (4'-0" dia. x 1" Pipe), Galvanized Steel | 107 pieces | ~40 LF each |

The Department will furnish to the Contractor the following material located at the intersection of the Seward Hwy and Portage Glacier Road within the project limits (note that this material may include cut off’s from previous efforts for Phase 1 and may include damage from transportation or other activities):

| Description | Quantity | Length |
| --- | --- | --- |
| Structural Steel Piles (4'-0" dia. x 1" Pipe), Bare Steel | 1 piece | ~40 LF |
| Structural Steel Piles (4'-0" dia. x 1" Pipe), Bare Steel | 1 piece | ~12 LF |
| Structural Steel Piles (2'-0" dia. x 1/2" Pipe), Bare Steel | 29 pieces | ~35 LF – 44 LF each |
| Structural Steel Piles (2'-0" dia. x 1/2" Pipe), Bare Steel | 12 pieces | ~11 LF -18 LF each |

Transport structural steel piles located in Seattle out of their current location within sixty (60) days following the issuance of the Notice to Proceed.

The structural steel piles are for use on the project and meet the requirements of Section 715.

Within thirty (30) days following issuance of the Notice to Proceed, the Contractor and Engineer shall communicate to establish a schedule and plan for inspecting this department-furnished material at its current location.  During the inspection(s), designated representatives of the Contractor and the Engineer will mutually agree in writing on the condition of this material, and document any defects.  The Contractor shall allow adequate time for inspection of each pile.  Failure by the Contractor to undertake this inspection shall constitute unreserved acceptance of this department-furnished material in its present condition.  The Contractor and the Department will each be responsible for their respective costs relating to the participation of employees or representatives in the inspection(s).

Except for damage noted during inspection, the Contractor will thereafter accept all responsibility and risk of damage or loss for this department-furnished material.  The Contractor shall include all costs associated with inspecting, loading/unloading, transporting, handling, and placing department-furnished material as part of the Contract price for the respected pay item(s) where it will be utilized.  A post transport inspection shall take place at the project site upon delivery of piles by both the Contractor and Engineer to document the post transport condition and verify pile identification.  Deductions will be made from any monies due to the Contractor for any post-inspection damage or loss, and for demurrage charges. The Department will pay storage costs for this material for up to sixty (60) days following the issuance of the Notice to Proceed. Thereafter, all storage costs shall be paid by the Contractor.  If the Contractor fails to pay these costs, the Department may do so, and the amount paid may be withheld from payments due to the Contractor until the Contractor reimburses the Department.

Thirty (30) days prior to removing department-furnished material from its present location, the Contractor must provide to the Engineer in writing the name and contact information for the Contractor representative who will verify and document the piles to be removed are the same items that were previously inspected. Inspection and removal operations may occur simultaneously if the Contractor wishes to do so.

Unused piles become the property of the Contractor, excepting that specified in 505-3.07.

CFHWY00213

SECTION 107
LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.

The Department will: Add the following paragraph after item No. 2:

3.	The Department has received the following permits on the Contractor's behalf:

- ADF&G Title 16 Fish Habitat Permit

- United States Army Corps of Engineers (USACE) Section 404

- ADEC 401 Certification

- Municipality of Anchorage Flood Hazard Permit

- United States Coast Guard Bridge Permit

CR107.4-120117R1 / CFHWY00213

The Contractor shall: Add No. 10 and No. 11:

10.	Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual, and the Regional Supplement to the Corps of Engineers Wetland Delineations Manual (Alaska Region, Version 2.0, September 2007).  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

- Obtain the following permits:

  - Alaska Railroad Corporation draft Temporary Construction Permit is included in Appendix E. The Contractor is required to obtain the final permit from the Permitting Agency.

  - USFS Draft Special Use Permit is included in Appendix F. The Contractor is required to obtain the final permit from the Permitting Agency.

CR107.5-120117R / CFHWY00213 / CFHWY003008

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.

Replace the 1st sentence including numbers 1, 2, and 3, with:

When operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following:

Non-municipal Water Source. If water is required for a construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

CR107.3-051517

Add the following:

Eagles.  Eagles are protected under 16 U.S.C. 668-668c Protection of Bald and Golden Eagles, that prohibits “takes” of eagles, their eggs, nests, or any part of the bird.  The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of minimum 330-feet as an undisturbed habitat buffer around nesting eagles.  If topography or vegetation does not provide an adequate screen or separation, extend the buffer to 1320-feet, or a sufficient distance to screen the nest from human activities.  The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity.  Within the Secondary Zone, between 330-feet and 660-feet from a nest tree, no obtrusive facilities, or major habitat modifications shall occur.  If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, extend the buffer up to 2640-feet.  No blasting, logging and other noisy, disturbing activities should occur during the nesting period (February 1 – August 31) within the primary or secondary zones.

Do not disturb a nesting eagle.  Notify the Engineer when an active eagle nest is within the primary or secondary zones.

CR107.1-100118

Add the following:

Before initiating roadwork, install plastic safety fence adjacent to environmentally sensitive site as shown on the Plans or as directed by the Engineer.  The exact location of the environmentally sensitive site shall be field verified prior to installing plastic safety fence.  Contact the ADOT&PF Environmental Analyst at (907) 269-0534 to arrange field verification prior to installing plastic safety fence.  Construction equipment shall remain outside of the boundaries of the environmentally sensitive site so delineated for the duration of the project.  Do not work within boundaries of the site.  The plastic safety fence installed adjacent to the environmentally sensitive site shall be maintained in good condition for the duration of the project.

CFHWY00213

Replace Subsection 107-1.17 with the following:

107-1.17 FURNISHING RIGHT-OF-WAY. The Department will secure all necessary right-of-way or property. The right-of-way (ROW) shown in the plans depict the ROW area that is or will be available for the project.  Acquisition of the following properties has not been completed, and no work shall commence on these properties until a separate Notice to Proceed is given by the Engineer.

- Parcel 1 and Parcel 2, Robert A. & Amy K. Hall, as shown on R-35

The Contract Time will commence to run on the day indicated on the Notice to Proceed for the overall project.  The Notices to Proceed for the above properties will be delayed until such time as the Department obtains full rights to enter upon the property.  The Contractor shall bid this Project to include all costs associated with the delayed Notices to Proceed based on the assumption that all Notices to Proceed will be given before June 1, 2021.  If the Notices to Proceed are given on or before June 1, 2021, The Contractor agrees that it will have no claim for damages or delay arising out of or connected to the delayed Notice to Proceed for these properties.

CFHWY00213

SECTION 108
 PROSECUTION AND PROGRESS

Special Provisions

Add the following Subsection 108-1.011 Related Sections:

108-1.011 RELATED SECTIONS.

Section 652, Prosecution and Progress – Supplemental Requirements

CR108.3-012816R

Standard Modification

108-1.07 FAILURE TO COMPLETE ON TIME.

Replace Table 108-1 with the following:

Table 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Original Contract Amount |  | Daily Charge |
| --- | --- | --- |
| From More Than | To and Including |  |
| $ 0 | 500,000 | $1,000 |
| 500,000 | 1,000,000 | 1,500 |
| 1,000,000 | 5,000,000 | 1,800 |
| 5,000,000 | 10,000,000 | 2,500 |
| 10,000,000 | 25,000,000 | 3,800 |
| 25,000,000 | --------- | 4,800 |

CR108.HSM20.1-041420

SECTION 109
MEASUREMENT AND PAYMENT

Special Provision

109-1.01 GENERAL.

Replace the 2nd paragraph with the following:

When more than one type of material or work is specified for a pay item, the proposal line number, and the description are used to differentiate the material or work.

CR109.4-010120

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.

Under Item 3. Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

Provide a printed copy of the current EquipmentWatch rate sheet for each piece of equipment utilized on time and materials work.

CR109.2-110118

Standard Modification

109-1.08 final payment. Add the following after the fifth paragraph:

On federally funded projects, if DOLWD Wage and Hour Administration notifies the Department of a pending prevailing wage investigation, and that the investigation is preventing the closing out of the project, the Contractor may place the notified amount in escrow under Wage and Hour for the exclusive purpose of satisfying unpaid prevailing wages. Upon receipt of notice from Wage and Hour that the Contractor has satisfactorily transferred the necessary funds into escrow, the Department will proceed to issue final payment.

CR109.HSM20.3-113020

DIVISION 200 — EARTHWORK

Blank Page

SECTION 201
CLEARING AND GRUBBING

Special Provisions

201-3.01 GENERAL.

Add the following:

Perform the work necessary to preserve and/or restore land monuments and property corners from damage.  Restore land monuments and/or property corners that are disturbed according to Section 642.  An undisturbed area five feet in diameter may be left around existing monuments and property corners.  A list of land monuments and property corners is shown on the Right of Way maps.

CR201.3-042313

Add the following:

Clearing and grubbing is not permitted within the migratory bird window of May 1 to July 15; except as permitted by Federal, State and local laws when approved by the Engineer.

CR201.1-010114

201-5.01 BASIS OF PAYMENT.

Add the following:

The work required to preserve and restore land monuments and property corners is subsidiary to 201 Pay Items.

CR201.3-042313

SECTION 202
REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION.

Add the following: Remove the existing bridges; 627 Placer River Overflow, 629 Placer River, 630 Portage Creek No. 1, 631 Portage Creek No. 2, and 634 Twenty Mile River.

CFHWY00213

Remove Subsection 202-3.03 in its entirety and replace with the following:

202-3.03 REMOVAL OF BRIDGES, CULVERTS AND OTHER DRAINAGE STRUCTURES.

Add the following to b. Demolition under 2. Bridges: Remove existing concrete piles to a depth not less than 3 feet below the finished groundline both within and outside the waterway.

CFHWY00213

Replace Subsection 3.05 with the following:

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS. In removing pavements, curbs, walks, driveways and similar structures, make all cuts clean, vertical, and true to designated lines where an abutting structure or a part of a structure is to be left in place.

Pavement materials, base course, sidewalks, curbs, gutters, etc., designated for removal may be placed in the embankment in accordance with 203-3.03 with written approval. Maximum allowed dimension of material is 6 inches.

Dispose of materials, not placed in the embankment, outside the right-of-way project limits according to Subsection 202-3.06.

CR202.2-040120

Add the following Subsection 202-3.06 Salvage and Disposal of Construction and Demolition Materials:

202-3.06 SALVAGE AND DISPOSAL OF CONSTRUCTION AND DEMOLITION MATERIALS. Unless otherwise noted, remove, handle, salvage, transport, store, and dispose waste materials according to the Occupational, Safety, and Health Administration (OSHA), Environmental Protection Agency (EPA), Alaska Department of Environmental Conservation (ADEC), and other Federal, State and local government agency's statutes, rules and regulations.

Use disposal sites outside the project right-of-way limits unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the private or public property owner for such disposal and a waiver of all claims against the State for any damage to such land which may result, together with all permits required by law for such disposal. Furnish a copy of such permission, waiver of claims, and permits to the Engineer before commencing work. Grade disposal areas to drain.

CR202.1-040120

Standard Modification

202-5.01 BASIS OF PAYMENT.

In the first paragraph, replace "and 22.0013.____." with the following: "and 202.0013.____."

In the fourth paragraph, replace "Items 020.0014.____" with the following: "Items 202.0014.____"

CR202.HSM20.4-113020

Add the following:

Acquiring waste disposal permits is subsidiary to 202 Pay Items.

CR202.1-040120

SECTION 203
EXCAVATION AND EMBANKMENT

Special Provisions

203-3.01 GENERAL.

Add No. 5 after the 11th paragraph:

5.	within 50 feet of detection loops.

CR203.4-022015

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL.

In the second paragraph delete "and ATM 214".

CR203.HSM20.5-113020

Add the following:

The embankment materials all around a bridge abutment, and less than 20 feet from each face of the abutment, shall pass the 3-inch sieve. Compact the material to 100% maximum density according to Section 205-3.04.

Use structural fill, Subsection 703-2.13, for structural backfill material, all other materials are as noted in the Plans.

CFHWY00213 AND CFHWY00308

***DELETED***

203-5.01 BASIS OF PAYMENT.

Add the following:

The material type is payed the same whether less than or greater than 20 feet from a bridge abutment regardless of a change in a sieve size or compaction percent of maximum density.

CFHWY00213 and CFHWY00308

Special Provision

Replace Section 204 with the following:

SECTION 204
STRUCTURE EXCAVATION FOR CONDUITS AND MINOR STRUCTURES

204-1.01 DESCRIPTIONS. Excavate and backfill for conduits (pipe culverts, structural plate pipe, pipe arches, storm drains, underdrains, and electrical conduits), headwalls, manholes, inlet boxes, and other minor structures.

Dewater ground water from work areas. Construct and maintain temporary water diversion when working in waterways, and for facilities or structures with active drainage.

Perform all pumping, bailing, draining, sheeting, bracing, and incidentals required for proper execution of the work.

204-2.01 MATERIALS. Use materials that conform to the following:

Selected Material	Subsection 703-2.07

Porous Backfill Material	Subsection 703-2.10

1.	Structure Backfill and Bedding Material: Selected Material Type A.

Maximum Particle Size:

a.	Corrugated Steel and Aluminum Conduit: material passing the 3-inch sieve

b.	Precast Concrete Structures

(1)	Conduit: materials passing the 1-inch sieve, except 2-inch when bedding thickness is greater than 6 inches

(2)	Minor structures: material passing the 1-inch sieve

c.	Plastic Conduit: material passing the 2-inch sieve, except 3/4-inch for conduit between 8 inches and 15 inches and for conduit less than 8 inches 10% of the conduit diameter

d.	Electrical Conduit: material passing the 1-inch sieve

e.	Underdrain Conduit: uniform porous backfill material passing the 2-inch sieve and a minimum greater than the conduit perforations

2.	Backfill Material: Selected Material Type C

In the roadbed structure use backfill material meeting the requirements of the roadbed structure, except use the structure backfill material and bedding as specified herein.

Use all suitable material from the project excavation for bedding, structure backfill, and backfill material before using material from another source.

204-3.01 CONSTRUCTION REQUIREMENTS. Clear and grub prior to starting excavation according to the requirements of Section 201.

Keep the work areas dewatered and divert water when working in a waterway or active drainage, Subsection 204-3.02.

Remove and dispose, Subsection 203-3.01, of unsuitable foundation material, including rock or other unyielding material, below the designed elevation as directed, except no less than 6 inches, and replace with approved material.

Place bedding material to a minimum thickness of 4 inches, except 6-inch minimum thickness for conduit over rock or unyielding material, and below electrical conduit, unless shown otherwise in the plans.

Place the bedding material to provide uniform support for conduit with the material in the middle one-third loosely placed and not compacted. Do not shape the bedding to the curvature of the round conduits. Shape the bedding for pipe arches, horizontal ellipse, and underpass shapes with spans exceeding 12 feet. Provide a minimum shaped width one-half the span of the pipe arch and underpass shapes and one-third the span of horizontal ellipse shape. Shape the bedding to the relatively flat bottom arc or fine-grade the foundation to a slight "V" shape.

Place minor precast concrete structures, other than conduits, on the 4-inch bedding/leveling course, of uniform stiffness and thickness with even compaction throughout.

Place the structure backfill over the bedding each side of the structure to 12 inches above the structure or the ground surface if less than 12 inches, except 6 inches above electrical conduit.

Place the structure backfill and backfill material in uniform layers not more than 6 inches deep. Do not create unbalanced loading with the placement of the structure backfill materials. When placing material against concrete, place the material according to the requirements of Section 550.

Compact the materials, each layer, without ponding or jetting to meet Subsection 203-3.04. In the haunch area, each side of the conduit, compact the material by firmly tamping into place.

Outside the roadbed structure, the Engineer may visually inspect and approve the excavation, bedding, structure backfill, backfill material, and compaction.

Support and protect existing conduits or utilities, not scheduled for removal or abandonment, when encountered in the excavation.

Remove all sheeting and bracing used in structure excavation upon completion of the work.

204-3.02 DEWATERING AND WATER DIVERSION. Submit a plan for work area dewatering and each waterway diversion, 14 days before related construction activities. Do not implement the plan without written approval. Include the permit requirements in the plan.

1.	Do not exceed State of Alaska water quality standards.

2.	Do not divert water from dewatering into a waterway.

3.	Provide an approved disposal site for work area excess water. Maintain disposal site a minimum of 100 ft from waterway.

4.	Prevent turbid water from directly entering waterways.

5.	Do not divert water onto the roadway.

6.	In addition to other equipment required to complete the temporary water diversion and dewatering work, maintain a minimum of two trash pumps with hoses at the site during diversion construction activities. Maintain the intake to prevent fish entrapment, entrainment, or injury with the use of perforated or slotted plate and woven wire with a mesh size not greater than 3/32 inch or a profile bar and wedgewire with openings not greater than 1/16 inch.  Do not exceed passive approach velocity of 0.2 fps and active approach velocity of 0.4 fps.

Rewater to minimize sediment movement downstream of the site. Prior to rewatering, slowly wet the reconstructed waterway channel; wash the fines into the bed by using pumps, or by diverting a small portion of the waterway channel flow. Capture and pump the sediment and turbid water, from the downstream end of the channel to the upstream end of the channel, until fines are washed into the streambed and water runs clear. Attain the Engineers written approval before breaching the coffer/diversion dams. Slowly breach the coffer/diversion dams and rewater the waterway channel.

204-4.01 METHOD OF MEASUREMENT. Section 109. Use neat line method as follows:

Structure Excavation:

1.	Masonry Structures (except conduit). Between vertical planes, 18 inches outside the base of the masonry sections for the depth required.

2.	Conduit. Between parallel vertical planes located 18 inches outside the horizontal projection of the outside diameter of the conduit and to the depth shown on the Plans.

CR204-061520

3.	Round Aluminum or HDPE pipe. Between parallel vertical planes located 18 inches outside the horizontal projection of the outside diameter of the Round Aluminum or HDPE pipe and to the depth shown on the Plans.

4.	Aluminum Box Culvert pipe. Between parallel vertical planes located 36 inches outside the horizontal projection of the span of the Aluminum Box Culvert pipe and to the depth shown on the Plans.

5.	Aluminum Structural Plate Pipe Arch. Between parallel vertical planes located 48 inches outside the horizontal projection of the span of the Aluminum Structural Plate Pipe Arch.

CFHWY00213 / CFHWY00308

Structure excavation only measured below the limits of other classes of excavation. Structure's in embankment section, the natural ground line as cross-sectioned is the uppermost level of computation.

204-5.01 BASIS OF PAYMENT. The Contract price includes the placing and compacting of all backfill and bedding when the materials used are obtained from excavation, any clearing and grubbing required and not paid for under some other item, formation of any embankments made with surplus material from structure excavation, and disposal of all surplus or unsuitable excavation.

Removal of pavement, culvert baffles, headwalls, temporary water diversion, dewatering and rewatering, are subsidiary to the conduit and minor structure Pay Items.

Additional excavation to provide for shoring, sheet piles, excavation shields or flattening the excavation slopes, is subsidiary.

When item 204.0001.____, 0002.____, or 0003.____ structure Excavation, does not appear in the bid schedule, structure excavation required to complete other items of work is subsidiary, except that excavation and disposal of unsuitable material required from below a plane 12 inches below the invert elevation of conduits and 12 inches below the bottom of structures is paid as extra work.

For Aluminum Structural Plate Pipe Arch, Structure Excavation does not appear in the bid schedule. Structure excavation required to complete the Aluminum Plate Pipe Arch and other items of work is subsidiary, except that excavation and disposal of unsuitable material required from below a plane of 18 inches below the invert elevation of the bottom of structure, is paid as extra work.

Any backfill or bedding material required whose source is other than project excavation is paid at the contract unit price for the materials being used, or as extra work if no unit price has been established.

Traffic control paid under Section 643 and Erosion, Sediment, and Pollution Control paid under Section 641.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 204.0001.____ | Structure Excavation | CY |
| 204.0002.____ | Structure Excavation | TON |
| 204.0003.____ | Structure Excavation | LS |

CR204-061520 / CFHWY00213 / CFHWY00308

Page is Intentionally Blank

SECTION 205
EXCAVATION AND FILL FOR MAJOR STRUCTURES

Standard Modification

205-3.05 COMPACTION.

1.	Compaction with Moisture and Density Control. 2nd paragraph delete: "and ATM 214".

CR205.HSM20.5-113020

SECTION 206
FILTER BLANKET

Special Provisions

206-2.01 MATERIALS.	Add the following:

Use crushed stones that are angular, hard, sound, and durable with at least one face resulting from fracture. Use stones with breadth and thickness at least 1/3 of its length.

CFHWY00308

Blank Page

DIVISION 300 — BASES

Blank Page

SECTION 301
AGGREGATE BASE AND SURFACE COURSE

Special Provision

301-2.01 MATERIALS.

Add the following after the first sentence:

Recycled Asphalt Material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70 – 100 |
| 3/8 inch | 42 – 90 |
| No. 4 | 28 – 78 |
| No. 16 | 11 – 54 |
| No. 50 | 5 – 34 |
| No. 100 | 3 - 22 |
| No. 200 | 2 – 12 |

3.	The asphalt content shall be 2.5 – 5.0 percent by weight of the RAM.

CR301.1-012407R

301-3.01 PLACING.

Add the following:

Place base course material, used for the sidewalk and pathway foundations, with equipment capable of providing a specified depth and uniform surface.

CR301.2-062116

Add No. 5 after the 5th paragraph:

5.	within 50 feet of detector loops.

CR301.3-022015

Standard Modification

301-3.03 SHAPING AND COMPACTION.

In the second paragraph delete "and ATM 214".

CR301.HSM20.5-113020

Add the following:

If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be determined by control strip method ATM 412.  Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi ( 5 psi) and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.

Add the following:

Recycled asphalt material substituted for aggregate base course will be paid for as Item 301.0001.____ Aggregate Base Course, at the unit price shown in the bid schedule for that Item.

CR301.1-012407R

SECTION 304
SUBBASE

Special Provision

304-3.01 CONSTRUCTION REQUIREMENTS.

Add No. 5 after the 4th paragraph:

5.	within 50 feet of detector loops.

CR304.1-022015

Special Provisions

Replace Section 306 with the following:

SECTION 306
ASPHALT TREATED BASE COURSE

306-1.01 DESCRIPTION.  Construct a plant-mixed asphalt treated base (ATB) course on an approved foundation to the lines, grades, and depths shown in the Plans.  Recycled asphalt pavement (RAP) may be used in the mix as specified herein.

CR306-040120

Repair potholes and unstable, raveling sections as directed.

CFHWY00213

306-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.

MATERIALS

306-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD).  Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 306-1 and as specified herein.  Recycled Asphalt Pavement may be used to supplement the aggregate and asphalt binder in the ATB.

TABLE 306-1

ATB Design Requirements

| DESIGN PARAMETERS | CLASS “B” |
| --- | --- |
| ATB (Including Asphalt Binder) |  |
| Stability, Pounds | 1200 min. |
| Flow, 0.01 Inch | 8 - 16 |
| Voids in Total Mix, % | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 50 |
| Asphalt Binder |  |
| Percent Voids Filled with Asphalt Binder (VFA) | 65 - 78 |
| Asphalt Binder Content, Min. % | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |
| Type II | 12.0 |
| Recycled Asphalt Pavement (RAP) |  |
| RAP, Max. %. | 25 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt binder.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the ATB, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-4.  For acceptance testing, ATB mixture will have the full tolerances in Table 306-2 applied.

Do not mix ATB produced from different plants for testing or production paving.  ATB from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of ATB:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD including gradations for individual virgin aggregate (aggregate) stockpiles and the RAP stockpile.  Provide supporting process quality control information; including the blend ratio of each aggregate stockpile, the RAP stockpile and the RAP asphalt binder content.  For mixes with RAP, provide JMD gradation with and without RAP.  Provide calibration data if ATM 406 is used for RAP process control.

2 	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) and RAP required for the proposed JMD.  Furnish 100 lbs of each intermediate and/or coarse aggregate, 200 lbs of fine aggregate, 25 lbs of blend sand, and 200 lbs of RAP.

3.	Three separate 1-gallon samples, minimum, of the asphalt binder proposed for use in the ATB.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet (MSDS).

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current MSDS.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and Table 306-1 ATB Design Requirements.

The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 306-1

	The asphalt binder source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The source of RAP is changed

Do not produce ATB for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.

Payment for ATB will not be made until the new JMD is approved.  Approved changes apply only to ATB produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix.  The fee will be included under Pay Item 306.2001.____ ATB, Price Adjustment, Type ___; Class__.

306-2.02 AGGREGATES.  Conform to Subsection 703-2.04.  Type II, Class B (IIB) total combined aggregates.

Use a minimum of three stockpiles for crushed ATB aggregate (coarse, intermediate, and fine).  Place RAP, blend material and mineral filler in separate piles.

306-2.03 ASPHALT BINDER.  Conform to 702-2.01.  If asphalt binder is not specified use PG 52-28.

The total asphalt binder content may be a combination of the asphalt binder specified and the residual asphalt binder in the RAP.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702, before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of anti-strip added.

306-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt binder is required.

306-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the ATB according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, adjust the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 7 days before initiating pre-paving operations.  Address the sequence of operations.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the ATB, and to provide the mat density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt binder content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 306-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

306-2.06 RECYCLED ASPHALT PAVEMENT (RAP).  Process existing pavement removed under Subsection 202-3.07 so material passes the 1 1/2" sieve.  Stockpile the material separately from the crushed aggregates.  Perform one gradation and one asphalt binder content test for every 1000 tons of RAP or a minimum of 10 sets of tests whichever is greater.

CONSTRUCTION REQUIREMENTS

306-3.01 WEATHER LIMITATIONS.  Do not place ATB on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place ATB unless the roadway surface temperature is 40F or warmer.

306-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of ATB buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production ATB.

306-3.03 ASPHALT MIXING PLANTS.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before ATB production.

When using recycled asphalt pavement material, mix the RAP with the aggregate before the aggregate enters the plant thereby adding the RAP combined with the aggregate to the asphalt treated base mixture at one time.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the ATB.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.

Provide aggregate and asphalt binder sampling equipment meeting OSHA safety requirements.

306-3.04 HAULING EQUIPMENT.  Costs associated with meeting the requirements of Subsection 306-3.04 are subsidiary to Section 306 Pay Items.

Vehicles/Equipment.  Haul ATB in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During ATB hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer, cover the ATB in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surface(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 7 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paving equipment.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material, the users, and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage, as specified in Subsection 306-3.16 Patching Defective Areas, to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal.  Use repair materials of similar type to the damaged material.  Attain written approval from the Engineer for the proposed material.

306-3.05 PAVING EQUIPMENT.  Use self-propelled asphalt pavers with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the screed or blade control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Use a paver screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the ATB.

Equip pavers with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the ATB uniformly in front of screed.

Prevent segregation of the coarse aggregate particles from the remainder of the ATB during paving operations.  Specifically equip pavers to prevent segregation between the hopper and augers.  Use means and methods approved by the paver manufacturer.  Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance verifying use of the means and methods required to prevent segregation.

306-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact ATB asphalt mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

306-3.07 PREPARATION OF EXISTING SURFACE.  Prepare base surface conforming to the Plans and Specifications.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of ATB on these surfaces.

306-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

306-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the ATB, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by ATM 407.

Heat the aggregate for the ATB, and the RAP when being used in the mix, to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  ATB containing soot or fuel is unacceptable (Subsection 105-1.11).

306-3.10 MIXING.  Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

306-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the ATB remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss; and the physical characteristics of the asphalt binder, lumpiness, or stiffness of the ATB or similar.

306-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute ATB.  Place the ATB upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the ATB surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding ATB may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the ATB in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

Do not cover/place over the asphalt treated base material until the ATB material throughout that section, as defined by the Paving Plan, is placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place ATB over bridge deck membranes, except as directed by the Engineer.

306-3.13 COMPACTION.  Compact the ATB by rolling thoroughly and uniformly.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Prevent indentation of ATB.  Do not leave rollers or other equipment standing on ATB that is not sufficiently cooled to prevent indentation.

A mat area with density lower than 92.0 % MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The MSG of the JMD will be used for the first lot of ATB.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to ATM 410 using a 6 inch diameter core.

306-3.14 JOINTS.  Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the ATB to provide a continuous bond, texture, and smoothness between adjacent sections of the ATB.

Coordinate the joints in the ATB pavement layer with the layer of HMA pavement above.  Offset the longitudinal joints in the HMA pavement layer above from the joint in the ATB asphalt pavement layer immediately below by at least 6 inches.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new ATB and thoroughly compact.

306-3.15 SURFACE TOLERANCE.  Costs associated with meeting surface tolerances are subsidiary to the ATB Pay Items.

The Engineer will test the finished surface after final rolling at selected locations using a 10 ft straightedge.  Correct variations from the testing edge, between any two contacts, of more than 1/4 inch.

306-3.16 PATCHING DEFECTIVE AREAS.  Costs associated with patching defective areas are subsidiary to the ATB Pay Items.

Remove defective ATB for the full thickness of the course, do not skin patch.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh ATB to grade (Subsection 306-3.13) and surface tolerance requirements (Subsection 306-3.15).

CR306-040120

306-3.17 REPAIR ROADWAY PAVEMENT.  The Engineer will evaluate the pavement condition and determine which station ranges are raveling at lane width inclusive of the shoulder and which station ranges are suitable for pothole repairs inclusive of the shoulder. Remove and dispose loose and deteriorated pavement for the full thickness of the existing HMA and 2 inches of existing base material. Sawcut the pavement so that edges are vertical and the sides are parallel to the direction of traffic. Clean the edges of the existing pavements, which are to be adjacent to new pavement, to permit the adhesion of asphalt materials. Coat edges with a tack coat according to Section 402 and allow to cure.  Place and compact fresh ATB to grade (Subsection 306-3.13) and surface tolerance requirements (Subsection 306-3.15).

CFHWY00213

306-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Asphalt Treated Base.

a)	By weighing.  No deduction will be made for the weight of asphalt binder or anti stripping additive or cutting back joints.

2.	Asphalt Binder.  By the ton, as follows.

Method 1:

Percent of asphalt binder for each sublot multiplied by the total weight represented by that sublot.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  If no acceptance testing is required, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2:

Supplier's invoices minus waste, diversion, and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing ATB for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste ATB will be calculated using the target value for asphalt binder as specified in the JMD.

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt binder more than 0.4% above the optimal asphalt binder content specified in the JMD.

3.	ATB, Price Adjustment, Type   ; Class  .  By the fees specified in Subsections 306-2.01, 4.02, and 5.01.

CR306-040120

4.	Repair Roadway Pavement – Unstable, Raveling.  The pay unit, contingent sum, is measured by the by the lane-station.

5.	Repair Roadway Pavement – Potholes.  The pay unit, contingent sum, is measured by the by the lane-station.

CFHWY00213

306-4.02 ACCEPTANCE SAMPLING AND TESTING.

1.	Asphalt Treated Base

The bid quantity of ATB produced and placed is divided into lots and the lots evaluated individually for acceptance.

A lot is normally 10,000 tons.  The lot is divided into sublots of 1000 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this subsection.  The lot is evaluated for acceptance according to Subsection 306-4.03. Seasonal startup or a new JMD requires starting a new lot.

If less than 8 sublots have been placed at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot. The acceptance computed for the prior lot will include the samples from the shortened lot. Density test results from material in the shortened lot will be based on the MSG of the first sublot of the shortened lot. If there is no prior lot, and there are at least 3 sublots, the material in the shortened lot will be considered as a lot and acceptance will be based on the actual number of test results in the shortened lot. If there are less than 3 sublots, the ATB will be accepted for payment based on the Engineer's approval of the JMD, and placement and compaction of the ATB to the specified depth, finished surface requirements, and tolerances.

If 8 or 9 sublots have been placed at the time a lot is terminated, they will be considered as a lot and the acceptance will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the bid quantity is between 3,000 to 10,000 tons, the quantity is considered one lot.  The lot is divided into sublots of 1000 tons and each randomly sampled and tested for asphalt binder content, density, and gradation according to this subsection.

ATB quantities of less than 600 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  ATB quantities of 600 tons or greater will be treated as an individual sublot.

For bid quantity less than 3,000 tons, ATB will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the ATB to the specified depth and finished surface requirements and tolerances.

The Engineer reserves the right to perform any testing required in order to determine acceptance.

a.	Asphalt Binder Content.  ATB samples shall be taken randomly by the Contractor in the presence of the Engineer from behind the paver screed before initial compaction, or will be taken randomly by the Engineer from the windrow according to ATM 402 or ATM 403 at the discretion of the Engineer. The location (behind the paver screed or windrow) will be determined at the pre-paving meeting. The Engineer will determine random sampling locations.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  At the discretion of the Engineer, asphalt binder content will be determined according to ATM 405 or ATM 406, except ATM 405 will not be used when RAP is included in the mixture.

b.	Aggregate Gradation. Aggregates tested for gradation acceptance will have the full tolerances from Table 306-2 applied. For ATB samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder.

c.	Density. The Engineer will determine and mark the location(s) where the Contractor takes each mat core sample.  The location(s) for taking core samples is determined using a set of random numbers (independent of asphalt binder and aggregate sampling set of random numbers) and the Engineer's judgment. Take no mat cores within 1-foot of a joint or edge. Core samples are not taken on bridge decks.

Take core samples according to ATM 413 in the presence of the Engineer. Cut full depth core samples centered on the marks from the finished ATB within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  The Engineer will immediately take possession of the samples. Backfill and compact voids left by coring with new ATB within 24 hours and according to ATM 413. The Engineer will determine density of samples according to ATM 410.

d.	Asphalt Binder Content, Aggregate Gradation, and Density – Retest. When test results have failed to meet specifications, retest of acceptance test results for asphalt binder content, gradation, and density may be requested provided the quality control requirements of Subsection 306-2.05 Process Quality Control are met.  Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results are discarded and the retest result is used to evaluate the material for acceptance.  Only one retest per sample is allowed.  When gradation and asphalt binder content are determined from the same sample, a request for a retest of either gradation or asphalt binder content results in a retest of both. Both gradation and asphalt binder content retest results are used in the evaluation. Except for the first lot, retesting for gradation or asphalt binder from the first sublot of a lot will include retesting for the MSG. Retesting will be performed by the Department's regional laboratory.

2.	Asphalt Binder

The bid quantity of asphalt binder produced and placed is divided into lots and the lots evaluated individually for binder grade acceptance.

Testing will be by AASHTO accredited independent laboratories. When retesting is requested, the assigned value (ATV) will be determined using ASTM D3244. Each test will be completed by a different laboratory.

a.	Acceptance Test. The lot size for asphalt binder will normally be 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it is added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it is sampled, tested and evaluated as a separate lot.

If the bid quantity of asphalt binder is between 85 to 200 tons, the bid quantity is considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Sample asphalt binder at the plant from the supply line in the presence of the Engineer according to ATM 401.  The Engineer will take immediate possession of the samples.  Take three samples from each lot, one for acceptance testing, one for Contractor requested retesting, and one held in reserve for referee testing if requested.  Meet Subsection 702-2.01 requirements for asphalt binder quality.

b.	Retest. Submit a written request, for a retest, no more than 7 days from receiving notice of the failed acceptance test. In the request, identify the retest laboratory. The Engineer will send the second sample (retest sample) to the laboratory. Provide the retest results to the Engineer.  Contractor pays for the retest costs.

If the average of the combined test results ([acceptance + retest]/2) passes the specification requirement, the average value becomes the ATV. If this ATV fails the specification requirement, the Engineer or Contractor may request the third sample (referee sample) be tested.

c.	Referee Test. The Engineer will send the third sample (referee sample) to an agreed upon laboratory. The average of the combined test results ([acceptance + retest + referee]/3) equals the ATV. If the ATV fails to meet specifications, the Contractor pays for the referee test.

306-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  A mat area of finished surfacing that is contaminated with foreign material; is segregated (determined visually or by testing), has a lower density than specified, fails to meet surface tolerance requirements, is flushing or bleeding asphalt binder after compaction is complete, or in any other way determined to be defective is unacceptable according to Subsection 105-1.11.  ATB, not meeting the specified limits noted in Table 306-2, is considered defective.  Correct unacceptable work and materials according to Subsection 306-3.16 and as directed by the Engineer.

TABLE 306-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4-inch sieve or largest sieve size | 99 | 100 |
| 1/2-inch sieve or first sieve retaining aggregate | TV -6 | TV +6 |
| 3/8-inch sieve | TV -6 | TV +6 |
| No. 4 sieve | TV -6 | TV +6 |
| No. 8 sieve | TV -6 | TV +6 |
| No. 16 sieve | TV -5 | TV +5 |
| No. 30 sieve | TV -4 | TV +4 |
| No. 50 sieve | TV -4 | TV +4 |
| No. 100 sieve | TV -3 | TV +3 |
| No. 200 sieve* | TV -2.0 | TV +2.0 |
| Asphalt Binder Content, % | TV -0.4 | TV +0.4 |
| Mat Density % | 92.0 | 100.0 |

*LSL for the No. 200 sieve is restricted by the broadband limits in Table 703-4.

Asphalt binder will be randomly sampled and tested in accordance with Subsection 306-4.02.  Provide supplier process control test results with the delivery ticket for each load of asphalt binder to the Engineer before unloading asphalt binder at the project. No payment will be made without this documentation.

306-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Subsection 702-2.01 Asphalt Binder, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

306-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items the work and materials associated with:

Asphalt binder, anti-stripping additives, surface tolerance corrections, patching defective areas; removal and disposal of rejected ATB, and the hauling equipment are subsidiary to the Asphalt Treated Base Pay Items.

Item 306.2001.____. ATB, Price Adjustment, Type ___; Class __: is the sum of the price adjustment for the fees assessed the Contractor including:

	Each mix design subsequent to the approved Job Mix Design (Subsection 306-2.01) will result in a fee of $2500.00 each.

	Failure to cut core samples within the specified period will result in a fee of $100.00 per sample per day (Subsection 306-4.02).

	Failure to backfill voids left by sampling within the specified period will result in a fee of $100 per hole per day (Subsection 306-4.02).

	Contractor retesting, referee sample testing and Contractor requested testing for visually inspected and rejected asphalt treated base failing to meet specifications will result in a fee being assessed for all costs associated with the test (Subsection 306-4.02, 4.03).

Item 306.2002.____ . Asphalt Material Price Adjustment.

For each Section as included in Subsection 306-4.04 Asphalt Material Price Adjustment, item 1, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment", is not included, for any section, no payment will be made.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 306.0001.____ | ATB | Ton |
| 306.0002.____ | Asphalt Binder, Grade PG ##-## X | Ton |
| 306.2001.____ | ATB, Price Adjustment, Type ___; Class __ | cs |
| 306.2002.____ | Asphalt Material Price Adjustment | CS |

CR306-040120

Asphalt binder, ATB, anti-stripping additives, tack coat, base course, surface tolerance corrections, patching defective areas; removal and disposal of rejected ATB, removal and disposal of pavement and base course, and equipment are subsidiary to the Repair Roadway Pavement Pay Items.

306.2003.____ Repair Roadway Pavement – Unstable, Raveling: Paid contingent sum at the rate of $5000/STA/Lane including shoulder for the work as specified in section 306-3.17. The paid rate includes the work, materials, labor, and equipment.

306.2004.____ Repair Roadway Pavement – Pothole: Paid contingent sum at the rate of $1000/STA/Lane including shoulder for the work as specified in section 306-3.17. The paid rate includes the work, materials, labor, and equipment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

306.2003.____	Repair Roadway Pavement – Unstable, Raveling	CS

306.2004.____	Repair Roadway Pavement – Pothole	CS

CFHWY00213

Special Provision

Add the following Section:

SECTION 318
FOAMED ASPHALT STABILIZED BASE COURSE

318-1.01 DESCRIPTION.  The work consists of constructing a mixed in place foamed asphalt stabilized base.  Create foamed asphalt treated base course by simultaneously injecting and thoroughly mixing metered amounts of asphalt, Portland cement, and water into the pulverized asphalt and base course.  Spread, shape, and compact the mixed material according to these specifications and conforming to the dimensions shown on the Plans.

Haul, stockpile, and place pulverized asphalt and base course as necessary to shape Selected Material and existing subbase to proposed elevations in accordance with Section 203.

Work consists of importing aggregate surface course, grading E-1, for foamed asphalt stabilized base course aggregate to supplement available quantities of insitu asphalt pavement and base material to be pulverized for aggregate.

***Deleted***

MATERIALS

318-2.01 COMPOSITION OF MIXTURE – JOB MIX DESIGN (JMD).

1.	Sampling.  Before foamed asphalt stabilized base course production, laboratory tests of materials submitted by the Contractor shall be made to determine the quantity of asphalt binder and Portland cement required in the mix.  At least 15 days before the production of foamed asphalt stabilized base course, the Contractor shall furnish the following:

  - 500-pound representative sample of in-place aggregate

  - 500-pound representative sample of imported aggregates  (E-1)

c.	200- pound representative sample of in-place asphalt concrete pavement

d.	10-gallons of asphalt binder

e.	One sack of Portland cement

2.	Job Mix Details.  The Engineer will determine the JMD using procedures contained in the Wirtgen Manual Foamed Bitumen Mix Design Procedure, using the Wirtgen WLB 10 to generate foamed asphalt.  The JMD will provide the following:

a.	The percent by weight of foamed asphalt binder to be added to the mix.

b.	The optimum percent by weight of water to be added to the asphalt binder for the foaming process.

c.	The minimum Foamed Asphalt Expansion Characteristics required.

d.	The temperature of asphalt binder at the time of injection.

e.	The percent by weight of Portland cement to be added to the mix.

f.	The gradation of the in place aggregate.

g.	The optimum compaction moisture content and dispersion of foamed asphalt binder.

h.	Design dry indirect splitting tensile strength.

i.	The unit weight of the compacted material.

318-2.02 ASPHALT BINDER.  Conform to subsection 702-2.01 Asphalt Binders PG 52-28.  Each batch of asphalt binder shall be tested to conform to specifications before shipping.  Storage tanks used for the batch shall be noted on the test report.

Provide the following shipping documents:

1.	Manufacturer’s certification of compliance.

2.	Conformance test results of the batch

3.	Manufacturer shall also document:

a.	date and time of loading

b.	batch number and storage tank

c.	type, grade, and quantity of materials loaded.

The vendor’s certified test report for the asphalt binder can be used for acceptance or tested independently by the Engineer.

Excess asphalt binder shall remain the property of the Contractor.  Removal of excess asphalt binder from the project area shall be incidental to the Contract and no separate payment will be made.

318-2.03 PORTLAND CEMENT.  Conform to subsection 701-2.01, Type I or II meeting low alkali requirements.

318-2.04 WATER.  Water shall be clean and free from sewage, oil, acid, strong alkalis, or vegetable matter.  Water of questionable quality shall be tested according to the requirements of AASHTO T 26.

318-2.05 *** Deleted*** CONTRACTOR’S FOAMED ASPHALT TECHNICIAN.  The Contractor shall provide an onsite Foamed Asphalt Technician to supervise the foamed asphalt process and the related process control of the product during the entire production.  This technician shall have a minimum of 5 years supervising successful projects using foamed asphalt binder with similar base material and equipment.  The technician must have the experience, knowledge, ability and authority to make necessary changes in the field to the mix design as existing ground conditions or gradations change.

Provide a submittals for the technician and superintendent that include the following information:

1.	Resume

2.	A list of successful projects; provide owners contact, address, and telephone number;  location of projects.

3.	Description of foamed asphalt binder equipment used on the project.

318-2.06 CONTRACTOR PROCESS CONTROL ***Deleted*** .  The quantity of foamed asphalt stabilized base produced will be divided into lots and the lots evaluated individually.

A lot will normally be 20,000 square yards.  The lot will be divided into sublots of 5,000 square yards. ***Deleted***

The Contractor shall provide the following:

1.	Daily production records for each sublot, including the quantity of asphalt binder, Portland cement, and in place compaction moisture content.

2. 	Measure and report expansion ratio and half-life of foamed asphalt binder for every 4 hours of production.

  - Monitor and report in place field density of the foamed asphalt stabilized base for each sublot.

***Deleted***

4. 	Calibrate the load cell prior to start.

5.	Report process control and acceptance sampling and testing data to the Engineer within 24 hours.

318-2.07 PREPROCESS MEETING.  A minimum of 5 days before initiating operations, hold a meeting on the jobsite where the Contractor’s foamed asphalt technician outlines a processing plan.  This plan must address the sequence of operation, list and configuration of equipment to be used, and process control.  Outline steps to assure product consistency, conformity to strength requirements, proposed quality control testing frequency, traffic control, and public notification.

The Contractor is required to furnish a project specific QC plan that includes, at a minimum, the following operations:

- Description of the Contractor’s QC Organization. The number of full-time equivalent employees, an organizational line of authority, and reporting responsibilities.

- QC Sampling, Testing, and Analysis Plan.  Methods that include a description of how random locations for testing and sampling are determined.

- Protection from Excessive Moisture. Procedures to protect stabilized material from receiving excessive moisture from weather events and corrective actions when criteria are not met.

- Contingency Plan. Including but not limited to:

- Inclement weather

- Equipment breakdowns

- Material doesn’t cure in a timely manner

- Production modifications due to changes in ambient and/or material temperature

- Material moisture changes

- In-situ material changes

- Material shortages

318-2.08 AGGREGATE.  Borrow material imported for foamed asphalt stabilized base course aggregate shall be processed and screened to meet material specification for aggregate surface course, grading E-1, prior to being placed, graded, and shaped for asphalt foaming. Refer to Subsection 703-2.03.

CONSTRUCTION METHODS

318-3.01 WEATHER LIMITATIONS.  Foamed asphalt stabilized base course shall not be mixed while the air or surface temperature is below 40F, or when conditions indicate that the temperature may fall below 40F within 24 hours, or when the aggregate is above the optimum compactions moisture content, or when the aggregate or subgrade is frozen.  Follow the recommendations made by the Contractor’s independent technical representative as approved by the Engineer regarding the acceptability of the weather conditions for foaming operation.

318-3.02 CONTROL SECTION.  Before full production, the Contractor shall use the equipment specified for the foamed asphalt stabilized base course operation and construct a control section at a location approved by the Engineer.  Process material in the control section two passes wide, 300 feet long and to the depth shown on the Plans, and develop a density standard according to ATM 412.  The Contractor’s  ***Deleted*** technical representative shall supervise this process.  A control section shall be constructed prior to full production of each new mix design.

318-3.03 RECLAIMER (RECYCLER).  The reclaimer shall have the following features and capabilities:

1.	A minimum power capability of 600 horsepower.

2.	The capability to pulverize to the size specified, mix, and recycle material to the depth shown on the Plans.

3.	Ability to increase the effective volume of the mixing chamber in relation to depth of cut.

4.	Two microprocessor controlled systems, complete with two independent pumping systems and spray bars, to regulate the application of foamed asphalt binder, separate from water that is used to increase the moisture content of the mixed material.  Both systems shall perform in relation to the forward speed of the reclaimer and the mass of the material being processed.

5.	Two spray bars, one for foamed asphalt binder and one for compaction moisture, shall each be fitted with self-cleaning nozzles at a maximum spacing of one nozzle for each 6 inch width of the mixing chamber.  Provide a way to monitor the flow rate at each nozzle to verify that all nozzles are producing foamed asphalt at the same rate.

6.	The foamed asphalt binder shall be produced at the spray bar in individual expansion chambers into which hot asphalt binder, water, and air are injected under pressure through individual and small orifices that promote atomization.  The rate of addition of water into the hot asphalt binder shall be kept at a constant percentage by mass of asphalt binder by the same microprocessor.

7.	A system within the operator cabin to verify the foamed asphalt is being evenly distributed across the full width of the spray bar at the rate specified.  The system shall be demonstrated to the Engineer to verify even spraying.

8.	An inspection or test nozzle shall be fitted at one end of the spray bar that produces a representative  sample of foamed asphalt binder.

9.	An electrical heating system capable of maintaining the temperature of asphalt binder flow components above 300 degrees F.

10.	A single asphalt binder feed pipe installed between the recycler and the supply tanker.  Do not use circulating systems that incorporate a return pipe to the supply tanker.

11.	The ability to print out asphalt binder quantities used during production.

12.The teeth on the mandrel mixing head form a Chevron pattern.

13.	Emulsion injection system spray bar equipped with individual valves that can be turned off to minimize emulsion overlap on subsequent passes.

14.	 Minimum 4 different drum speeds for control of machine.

The reclaimer model proposed for use shall have successfully been used by the Contractor/subcontractor on other projects.  Provide a submittal of the reclaimer specifications at the Preconstruction conference.

              - Recycling Mixing Plant. Use a recycling mixing plant that has the following features and capabilities:

- Plant specifically designed to produce mixes that operates independently of external power sources and can be transported to the job site.

- Minimum mixing capacity of 200 tons per hour.

- Capable of combining all stabilizing agents and aggregates up to 2-inch diameter.

- Two microprocessor controlled systems, complete with independent pumping systems and spray bars, to regulate the application of foamed asphalt binder, separate from water that is used to increase the moisture content of the mixed material. Both systems perform in relation to the mass of the material being processed.

- Two spray bars, one for foamed asphalt binder and one for compaction moisture, each fitted with self-cleaning nozzles at a maximum spacing of one nozzle for each 6-inch width of the mixing chamber. Provide a way to monitor the flow rate at each nozzle to verify that all nozzles are producing foamed asphalt binder at the same rate.

- The foamed asphalt binder is produced at the spray bar in individual expansion chambers into which both hot asphalt binder and water are injected under pressure through individual and small orifices that promote atomization. The rate of addition to water into the hot asphalt binder is kept at a constant percentage by mass of asphalt binder by the same microprocessor.

- An inspection or test nozzle fitted at one end of the spray bar produces a representative sample of foamed asphalt binder.

- An electrical heating system capable of maintaining the temperature of asphalt binder flow components above 300F.

- A single asphalt binder feed pipe installed between the recycler and the supply tanker. A circulating system that has a return pipe to the supply tank may be used.

- A system accessible by the operator to verify the foamed asphalt binder is being evenly distributed across the full width of the spray bar. Demonstrate the system to the Engineer to verify even spraying.

- The ability to display and/or transmit asphalt binder quantities used during production, at any point during the work shift and for the entire day’s production.

318-3.04 PORTLAND CEMENT DISTRIBUTOR.    Use a cement distributor designed to spread a uniform coverage of Portland cement at a specified rate.

318-3.05 ROLLERS.  Provide the following types of rollers as required:

1.	Self-propelled vibratory pad foot roller having a minimum dynamic force of 60,000 lbs. for initial compaction.

2.	Pneumatic tired roller having a minimum operating weight of 50,000 lbs. for secondary compaction and finishing.

3.	Vibratory steel drum roller for secondary compaction and finishing.

318-3.06 GRADER.  Grader must have calibrated automatic cross slope blade controls.

318-3.07 PREPARATION.  The area to be stabilized with foamed asphalt binder may require pulverization, removal of material, grading, scarifying, shaping, and compacting, as directed by the engineer, to conform to the grades and typical cross section shown on the Plans, then provide aggregate and pay for under a separate bid item.  Soft or yielding spots shall be removed and replaced with acceptable aggregate before being stabilized.

Placement of foamed asphalt stabilized base course shall occur on an unbound layer consisting of existing or proposed base course, existing subbase course. No bound asphalt pavement may be left intact underneath the foamed asphalt stabilized base course.

Where the proposed foamed asphalt stabilized base course grades are above the existing unbound base course or subbase course, place Selected Material, Type A, on top of existing base course or subbase course and aggregate surface course, grading E-1 up to proposed grade for the foamed asphalt stabilized base course.

318-3.08 PULVERIZING.  Pulverize the existing asphalt pavement and base material so that at the completion of moist mixing, 100% passes a 2 inch sieve as determined by ATM 304.  Multiple passes may be required to size the insitu material and to adjust moisture content before applying Portland cement and injecting foamed asphalt.

318-3.09 FOAMED ASPHALT BINDER AND PORTLAND CEMENT APPLICATION, MIXING, AND SPREADING.  Mix insitu material with foamed asphalt binder, Portland cement, and water in place with a reclaimer.

Measure the moisture content of insitu material before processing and adjust if necessary.  The percentage of moisture in the aggregate, at the time of Portland cement application, shall not exceed the quantity that will permit a uniform mixture during mixing operations, and it shall not exceed the specified optimum moisture content for the foamed asphalt stabilized base course mixture.

Spread the required quantity of Portland cement uniformly on the surface to be stabilized.  Pulverize to the depth required while simultaneously injecting foamed asphalt binder and compaction water.  Mixing shall continue until the foamed asphalt binder, Portland cement and compaction water have been sufficiently blended with the existing material.

318-3.10 COMPACTION.  Immediately upon completion of the mixing operations, the mixture shall be thoroughly compacted with the initial compaction done with the vibratory pad foot roller.  The intermediate compaction shall be done with the pneumatic tired roller and the finish compaction shall be done with the vibratory steel drum roller.

Field density of the compacted mixture shall be evaluated in accordance with subsection 318-4.02. Additional control strips may be required if there are changes in the material. The in-place field density will be determined by direct transmission in accordance with ATM 213, Method A. The moisture content of the mixture at the start of compaction shall not be above the optimum moisture content as determined by the foamed asphalt stabilized base course mix design.

318-3.11 FINISHING.  The completed foamed asphalt stabilized base course shall conform to the required lines, grades and cross section.  If necessary, the surface shall be lightly scarified to eliminate any deep imprints made by the compacting or shaping equipment.  The surface shall then be recompacted to the required density.  ***Deleted*** Control traffic on the finished surface for a cure period after sealing is completed, as directed by the Engineer. Apply tack within 24 hours after the cure period.

318-3.12 CONSTRUCTION LIMITATIONS.  When the operation, after the application of cement, is interrupted for more than 30 minutes or when the uncompacted mixture is wetted by rain so that the optimum moisture content is exceeded by 2 percentage points, the decision to reconstruct the portion affected shall be determined by the Engineer.  In the event the uncompacted, rain wetted mixture exceeds the specified moisture content tolerance, the Contractor shall reconstruct at the Contractor’s expense the portion affected.  Material along the longitudinal or transverse construction joints not properly compacted shall be reconstructed, at the Contractor’s expense, with properly moistened and mixed foamed asphalt stabilized base compacted to specified density.

318-3.13 SURFACE TESTS.   The finished surface shall not vary more than 3/8 inch when tested with a 10 foot straightedge applied parallel with, or at right angles to, the longitudinal axis of the pavement.  Variations in excess of this tolerance shall be corrected by the Contractor, at the Contractor’s expense, and in a manner satisfactory to the Engineer.

318-3.14 MAINTENANCE.  Maintain, at the Contractor’s expense, the entire base course within the limits of the Contract in a condition satisfactory to the Engineer from the time work starts until the work is completed.  Maintenance includes immediate repairs of defects that may occur either before or after the foamed asphalt stabilized base course has been constructed.  The work shall be done by the Contractor at the Contractor’s expense and repeated as often as necessary to keep the area intact.  Repairs shall be made in a manner that will ensure restoration of a uniform surface and the durability of the part repaired.  Faulty work must be reconstructed for the full depth of treatment.  Low areas shall be remedied by reconstructing the material for the full depth of treatment rather than by adding a thin layer of foamed asphalt stabilized base course to the completed work.

The Contractor is responsible for cost of road spray on vehicles and informing the public of potential hazards.

318-4.01 METHOD OF MEASUREMENT.    Section 109 and the following:

1.	Asphalt Binder.  By the weight recorded on delivery tickets minus waste, diversion, and remnant.

2.	Portland Cement.  By the weight recorded on delivery tickets minus waste, diversion, and remnant.

3.	Foamed Asphalt Stabilized Mix.  By area measured across top of foamed asphalt treated base course section from edge to edge as shown in the Plans.

***Deleted***

318-4.02 EVALUATION OF MATERIAL FOR ACCEPTANCE.

The quantity of foamed asphalt stabilized base course provided will be divided into lots and the lots will be evaluated individually.

A lot will be 20,000 square yards. The lot will be divided into sublots of 5,000 square yards each. The Department shall randomly sample and test for density each sublot.  Sublots shall be tested for density by taking a nuclear density readings in accordance with ATM 213, Method A from three random test sites selected by the Engineer within each sublot. Test sites shall not be located within 12 inches of any longitudinal joint.

The average of the sublot density measurements will be compared to the maximum density from the approved mix design to determine the acceptability of the lot. Once the average density of the lot has been determined, the Contractor will not be permitted to provide additional compaction to raise the average. The Department shall notify the Contractor of density results as soon as possible.  If two consecutive sublots produce density results less than 97.0% of the target density, the Contractor shall institute corrective action as described in the QC Plan or as recommended by the Foamed Asphalt Technician. Payment will be made according to Table 318-2.

TABLE 318-2: PAYMENT SCHEDULE FOR LOT DENSITIES.

| Percent of Density from Approved Mix Design | Percent of Payment |
| --- | --- |
| 97.0 or greater | 100 |
| 96.0 to less than 97.0 | 95 |
| Less than 96.0 | See below |

If the lot density falls below 96.0%, the lot will be rejected and shall be removed, replaced, or reworked as directed by Engineer at the Contractor’s expense.

When test results have failed to meet specifications, retest of acceptance tests for density may be requested provided the quality control requirements of Subsection 318-4.3 are met. Only one sublot retest per lot will be permitted.  Deliver this request in writing to the Engineer, within 48 hours of receipt of the final test of the lot.  The Engineer will mark the locations for the density retest within a 5-foot radius of the original density locations. The original average density result will be discarded and the retest result will be used in the payment schedule regardless of whether the result gives a higher or lower percent of payment.

318-4.03 ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Subsection 702-2.01 Asphalt Binder, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

318-5.01 BASIS OF PAYMENT

Item 318.2000.        Foamed Asphalt Stabilized Base Course

Payment includes pulverizing and milling existing asphalt pavement and base course to full depth shown in plans, as measured from the existing roadway surface; hauling, stockpiling, and placement of pulverized asphalt pavement and base course; mixing and foaming pulverized asphalt pavement and base course and imported aggregate surface course, grading E-1;  and spreading, shaping, and compacting the mixed material.

Removal of existing asphalt pavement to be paid for under Pay Item 202.0002 Removal of Pavement. Additional material to be removed to meet final elevation of the foamed asphalt stabilized base section per plans, to be paid for under Pay Item 203.0003 Unclassified Excavation.

Imported aggregate surface course, grading E-1, used as aggregate for foamed asphalt stabilized base course is paid for under Pay Item 301.0003 Aggregate Surface Course, Grading E-1.

***Deleted***

Item 318.2003.       Asphalt Material Price Adjustment.

For each Section as included in Subsection 318-4.03 Asphalt Material Price Adjustment, item 1, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 318.2000.____ | Foamed Asphalt Stabilized Base Course | SY |
| 318.2001.____ | Asphalt Binder, Grade PG 52-28 | Ton |
| 318.2002.____ | Portland Cement, Type I or II | Ton |
| 318.2003.____ | Asphalt Material Price Adjustment | CS |

CR318-042020 / CFHWY00213

Page is Intentionally Blank

Blank Page

DIVISION 400 — ASPHALT PAVEMENTS
AND
SURFACE TREATMENTS

Blank Page

Special Provision

Replace Section 401 with the following:

SECTION 401
HOT MIX ASPHALT PAVEMENT

401-1.01 DESCRIPTION. Construct one or more courses of plant-produced Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

1.	In this Section, HMA refers to Type I, II, III, and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course: HMA, Type IV, Class B.

MATERIALS

401-2.01 ASPHALT BINDER.  Conform to Subsection 702-2.01. If binder performance grade is not specified, use PG 52-28.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of liquid anti-strip added.

Asphalt binder may be conditionally accepted at the source if a manufacturer's certification of compliance is provided, according to Subsection 106-1.05, and the applicable requirements of Section 702 are met.

401-2.02  LIQUID ANTI-STRIP ADDITIVE.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design (JMD). At least 90% of the aggregate must remain coated when tested according to ATM 414. The following minimum dose (percent) of liquid anti-strip by weight of asphalt binder is required:

| Liquid Anti-strip Type | Minimum Dose by Weight of Asphalt Binder, % |
| --- | --- |
| Amines based | 0.30 |
| Phosphate Ester based | 0.30 |
| Organ-Silane based | 0.05 |

401-2.03  JOINT ADHESIVE.   Conform to Subsection 702-2.05.

401-2.04  JOINT SEALANT.   Conform to Subsection 702-2.06.

401-2.05  WARM MIX ASPHALT.   Conform to Subsection 702-2.07.

401-2.06  ASPHALT RELEASE AGENT.  Conform to Subsection 702-2.08.

401-2.07 AGGREGATES.  Conform to Subsection 703-2.04.  Use a minimum of three stockpiles of crushed aggregate (coarse, intermediate, and fine).  Place blend material, if any, in a fourth pile.

401-2.08  RECYCLED ASPHALT PAVEMENT.  Recycled asphalt pavement (RAP) may be used in the production of HMA.  The RAP may be from pavements removed under the Contract, or from an existing stockpile.  Conform to Subsection 703-2.16

401-2.09 JOB MIX DESIGN.  Provide target values for gradation that satisfy both the broad band gradation limits shown in Table 703-4 and the requirements of Table 401-1, for the Type and Class of HMA specified.

TABLE 401-1

HMA MARSHALL Design Requirements

| DESIGN PARAMETER | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (Including Asphalt Binder) |  |  |
| Stability, Pounds | 1800 Min. | 1200 Min. |
| Flow, 0.01 Inch | 8 – 14 | 8 - 16 |
| Voids in Total Mix (VTM), % | 3.0 – 5.0 | 3.0 – 5.0 |
| Compaction, Number of Blows Each Side of Test Specimen | 75 | 50 |
| Asphalt Binder |  |  |
| Voids Filled with Asphalt (VFA), % | 65 - 75 | 65 - 78 |
| Asphalt Content, Min. % @ 4% VTM | 5.0 | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |
| Liquid Anti-Strip Additive**,%, Min. | 0.30 | 0.30 |
| RAP, %, Max. | 15.0 | 25.0 |

*Dust-Asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt binder (calculated by weight).

** By Weight of Asphalt Binder

The approved JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the recommended mixing temperature range.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant. The letter shall state whether or not WMA and/or RAP will be used. The letter shall include the proposed gradation for the JMD, gradations for individual stockpiles, and the blend ratio of each aggregate stockpile.

2.	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) in the proposed mix design. Furnish a total of 500 pounds of material in the proportional amounts in the proposed JMD.

3.	Five separate 1-gallon samples of the asphalt binder proposed for use in the HMA. Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature- viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, minimum 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

5.	Testing results per Subsection 106-1.03.1 for each aggregate type proposed for use.

6.	If applicable, a letter stating the WMA technology (Subsection 702-2.07) to be used, location where additive will be introduced and manufacturer’s recommended usage rate for each type of HMA.  Supply a minimum of 2-pint samples for each proposed additive.

7.	If applicable, representative samples of any RAP proposed for use.  Furnish a minimum of 200-pound sample of proposed RAP. The Engineer will evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of HMA specified, and establish the approved JMD which will become a part of the Contract.

Anti-strip evaluation (ATM 414) of HMA mix designs that include RAP will be completed without the inclusion of the RAP.

Obtain an approved JMD prior to shipment of aggregates to an asphalt plant site or producing HMA for payment.

Contractor Mix Design.  If a bid item for JMD appears in the contract, or if the Engineer approves a request from the Contractor to perform the JMD at no cost to the Department, provide a JMD following the requirements specified in this section.  Submit the JMD to the Engineer at least 15 working days before HMA production.  Submit samples to the Engineer upon request for JMD verification testing.

All Contractor-furnished JMDs must be sealed by a professional Engineer registered in the State of Alaska.  The Professional Engineer shall certify that the JMD was performed according to the specified procedures, and meets all project specifications.

Changes. Submit a new JMD with changes noted and new samples in the same manner as the original JMD submittal when:

a.	The results of the JMD evaluation do not achieve the requirements specified in Table 401-1

b.	The asphalt binder source is changed

c.	The source of aggregate, aggregate quality or gradation is changed

d.	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD; the original, or a replacement JMD.

The Engineer has the option to require further verification of the JMD under 401-2.10 Process Quality Control.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, materials, and the JMD, Subsection 401-2.10.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.

Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix Design, per Subsection 401-5.01.

401-2.10 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer at the "Pre-Paving Meeting," Subsection 401-3.01, the JMD and a documentation plan that provides a complete, accurate, and clear record of the sampling and testing results.

Failure to perform quality control forfeits the Contractor's right to a retest under Subsection 401-4.02

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

Supplemental Process Quality Control:

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips”.

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineer's approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train shall be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 401-3.04.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Failed Test Strip:  the Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

Refer to Subsection 401-5.01 for payment of test strips.

CONSTRUCTION REQUIREMENTS

401-3.01 PRE-PAVING MEETING. Meet with the Engineer for a pre-paving meeting in the presence of the project superintendent and paving foreman at least (5) working days before beginning paving operations.  Submit a paving plan and pavement inspection plan at the meeting.  When directed by the Engineer, make adjustments to the plan and resubmit.

1.	Paving Plan.  Include the following:

a.	Sequence of operations

b.	List of equipment that will be used for production, transport, pick-up (if applicable), laydown, and compaction

c.	Summary of plant modifications (if applicable) for production of WMA

d.	Procedures to produce consistent HMA

e.	Procedures to minimize material and thermal segregation

f.	Procedures to minimize premature cooling

g.	Procedures to achieve HMA density

h.	Procedures for joint construction including corrective action for joints that do not meet surface tolerance requirements

i.	Quality control testing methods, frequencies and sample locations for gradation, asphalt binder content, and density, and

J.	Any other information or procedures necessary to provide completed HMA construction that meets the Contract Requirements

2.	Pavement Inspection Plan. Include the following:

a.	Process for daily inspections

b.	Means and methods to remove and dispose of project materials

401-3.02 CONTRACTOR QUALITY CONTROL. Perform quality control (QC) of HMA materials in accordance with Subsection 106-1.03.

401-3.03  WEATHER LIMITATIONS.  Place HMA on a stable/non-yielding roadbed. Do not place HMA when the base material is wet or frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA when the roadway surface temperature is colder than 40° F.

401-3.04 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make all equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of HMA and test strip HMA.

401-3.05  ASPHALT MIXING PLANT.  Meet AASHTO M 156.  Use an HMA plant capable of producing at least 150 tons of HMA per hour noted on posted DEC air quality permit, designed to dry aggregates, maintain consistent and accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the HMA plant and furnish copies of the calibration data to the Engineer at least 24 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.  Provide aggregate and asphalt binder sampling locations meeting OSHA safety requirements.

You may use belt conveyor scales to proportion plant blends and mixtures if the scales meet the general requirements for weighing equipment and are calibrated according to the manufacturer’s instructions.

If WMA is approved by the Engineer, modify the mixing plant as required by the manufacturer and WMA additive manufacturer.

401-3.06  HAULING EQUIPMENT.  Haul HMA in trucks with tight, clean, smooth metal beds. Keep beds free of petroleum oils, solvents, or other materials that would adversely affect the mixture. Apply a thin coat of approved asphalt release agent to beds as necessary to prevent mixture adherence. Provide trucks with covers attached and available for use.

When directed by the Engineer, cover the HMA in the hauling vehicle(s).

Do not haul HMA on barges.

401-3.07 ASPHALT PAVERS.  Use self-propelled asphalt pavers with heated vibratory screed assemblies to spread and finish HMA to the specified section widths and thicknesses without introducing thermal or material segregation.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.  Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA. Heat and vibrate screed extensions. Place auger extensions within 20 inches of the screed extensions or per written manufacturer’s recommendations.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.

Equip the paver with automatic screed controls capable of operating from a reference line or a ski from either or both sides of the paver.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.08  ROLLERS. Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Use rollers designed to compact HMA and capable of reversing without shoving or tearing the mixture. Select rollers that will not crush the aggregate or displace the HMA. Equip vibratory rollers with separate vibration and propulsion controls.

Equip the rollers with an infrared thermometer that measures and displays the surface temperature to the operator. Infrared thermometer may be hand-held or fixed to the roller.

Utilize a pneumatic roller in the complement of rollers to compact the leveling course.  Use fully skirted pneumatic-tire roller having a minimum operating weight of 3000 pounds per tire.

401-3.09  RESERVED.

401-3.10  PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces according to the Contract. Prior to placing HMA, clean existing surfaces of loose material and uniformly coat contact surfaces of curbing, gutters, manholes and other structures with tack coat material meeting Section 402.  Treat cold joint surfaces according to 401-3.17. Allow tack coat to break before placement of HMA on these surfaces.  Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before applying tack coat to an existing paved surface, clean and patch the surface.  Remove irregularities to provide a reasonably smooth and uniform surface.  Remove and replace unstable areas with HMA.  Clean the edges of existing pavements, which are to be adjacent to new pavement, to permit the adhesion of asphalt materials.  Clean loose material from cracks.  Fill the cleaned cracks, wider than 1 inch, with HMA tamped in place.  Wash and/or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

1.	Prelevel remaining ruts, pavement delaminations, and depressions having a depth greater than 1/2 inch with an approved HMA.

2.	Notify the Engineer of pavement areas that appear thin or unstable.  Where milling operation creates thin or unstable pavement areas, or where it breaks through existing pavement, remove thin and unstable pavement, and 2 inches of existing base material, compact and replace with an approved HMA.

401-3.11  PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the recommended mixing temperature range.

401-3.12  PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by ATM 407.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable per Subsection 105-1.11.

401-3.13  MIXING. Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD. Mix to obtain at least 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt binder.

Mix the HMA within the temperature range determined by the JMD.

Upon the Engineer’s request, provide daily burner charts showing start/stop times and temperatures.

401-3.14  TEMPORARY STORAGE OF HMA.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.

Signs of visible segregation, heat loss, changes from the JMD, change in the characteristics of asphalt binder, lumpiness, and stiffness of the mixture, are causes for rejection.

Do not store HMA on barges.

401-3.15  PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, are placed and accepted.

Do not place HMA abutting curb and gutter until curb and gutter are installed, except as approved by the Engineer.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

When practicable, adjust elevation of metal fixtures before paving the final lift, so they will be between 1/4 and 1/2 inch below the top surface of the final lift.  Metal fixtures include, but are not limited to manholes, valve boxes, monument cases, hand holes, and drains.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make mechanical spreading and finishing equipment impracticable.

Place HMA over bridge deck membranes according to Section 508 and the membrane manufacturer's recommendations.

Do not mix HMA produced from different plants for testing or paving.

401-3.16  COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

Prevent indentation in the mat, do not leave rollers or other equipment standing on HMA that has not sufficiently cooled.

The Lower Specification Limit for density is 92.0% of the Maximum Specific Gravity (MSG) as determined by ATM 409.  The MSG from the approved JMD is used for the first lot of each type of HMA.  The MSG for additional lots is determined from the first sublot of each lot.

401-3.17  JOINTS.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the pre-paving meeting.  Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

Form transverse joints by saw-cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints 15 to 25 degrees.

For all joints below the top lift, uniformly coat joint surfaces with tack coat material meeting Section 402.

Uniformly coat the joint face of all top lift joints with a joint adhesive. Follow joint adhesive manufacturer's recommendations for temperatures and application method.  Remove joint adhesive applied to the top of pavement surface.  If infrared joint heaters are used and passing joint densities are achieved in each of the first three joint densities taken, then joint adhesive is not required.

The Lower Specification Limit for top lift longitudinal joint density is 91.0% of the MSG of the panel completing the joint. MSG will be determined according to ATM 409.

For top lift panels that have a longitudinal joint density less than 91.0% of the MSG in a sublot, seal the surface of the longitudinal joints with joint sealant within that sublot, or as directed..  Apply joint sealant according to the manufacturer’s recommendations while the HMA is clean, free of moisture and prior to final traffic marking.  Place the sealant at a maximum application rate of 0.15 gallons per square yard, and at least 12 inches wide centered on the longitudinal joint.  After surface sealing, inlay by grinding pavement striping into the sealed HMA. Use grooving equipment that grinds a dry cut to groove the width, length, and thickness of the striping within the specified striping tolerances.

Correct improperly formed joints that result in surface irregularities according to a corrective action plan.

Complete all hot lapped joints while the mat temperature is over 230F as measured by the Engineer, within 3 inches of the joint. Tack coat and joint adhesive are not required for hot lapped joints. Hot lapped joints will receive the full Longitudinal Joint Density Price Adjustment incentive without testing for joint density.

Top lift longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03

401-3.18  SURFACE REQUIREMENTS AND TOLERANCE.  The finished surface of all HMA paving must match dimensions shown in the contract for horizontal alignment and width, profile grade and elevation, crown slope, and pavement thickness. Water must drain across the pavement surface without ponding. The surface must have a uniform texture, without ridges, puddles, humps, depressions, and roller marks. The surface must not exhibit raveling, cracking, tearing, asphalt bleeding, or aggregate segregation. Leave no foreign material, uncoated aggregate, or oversize aggregate on the HMA surface.

The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  The Engineer will identify pavement areas that deviate more than 3/16 inch from the straightedge, including joints, as defective work. Perform corrective work by removing and replacing, grinding, cold milling or infrared heating such areas as required. Do not surface patch. After the Contractor performs corrective work, the Engineer will retest the area.

The Engineer will use an inertial profiler to measure the top lift HMA surface in the driving lanes for surface smoothness within 21 days after paving is complete and driving lanes are delineated.

Profiler measurements will not be taken in turn lanes, ramps, lane transitions, or within 25 feet of bridge abutments and transverse joints with pre-existing pavement.

The Engineer will measure the pavement smoothness in both wheel paths of each lane.  The smoothness is measured as International Roughness Index (IRI), reported as inches/mile, at 0.1-mile increments.  Pavement smoothness is the average of all IRI measurements for the project.

The Engineer will identify areas requiring corrective action in accordance with Table 401-4.  Perform full-width corrective action in those areas.  The Engineer may waive corrective work for localized roughness for deficiencies resulting from manholes or other similar appurtenances near the wheel path.

Perform Corrective Actions according to one of the following or by a method approved by the Engineer:

1.	Diamond Grinding.  If the required pavement thickness is not decreased by more than 0.25”, grind to the required surface tolerance and cross section.  Remove and dispose of all waste materials.  Apply joint sealant and sand to exposed aggregates per the manufacturer’s recommendations.

2.	Overlaying.  Mill or sawcut the existing pavement to provide a vertical transverse joint face to match the overlay to the existing pavement.  Apply tack coat on the milled surface and joint adhesive to all vertical joints and overlay the full width of the underlying pavement surface.  Use the same approved HMA for overlays.  Place a minimum overlay thickness of 2.0 inches.

3.	Mill and Fill. Mill the existing pavement to provide a vertical transverse joint face. Apply tack coat to the milled surface and joint adhesive to all vertical joints prior to inlaying new HMA to match the existing pavement.  Use the same approved HMA.  Place a minimum thickness of 2.0 inches.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.

Price adjustments for pavement smoothness will be calculated according to Subsection 401-4.03.3.

401-3.19  REPAIRING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt. Remove and dispose defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat according to Section 402.  Place and compact fresh HMA so that compaction, grade, and smoothness requirements are met.

401-3.20  ROADWAY MAINTENANCE.  Inspect daily according to pavement inspection plan. Remove, and dispose of project materials incorrectly deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The Contractor is responsible for damage caused by not removing these materials and any damage to the roadway from the removal method(s).

Repair damage to the existing roadway that results from fugitive materials or their removal.

401-4.01  METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a.	By weight.  No deduction is made for the weight of asphalt binder or anti stripping additive or cutting back joints. If the use of WMA is approved by the Engineer, WMA additives will not be measured and are considered subsidiary to the HMA pay item.

b.	By the final HMA surface area.

2.	Asphalt Binder.  By weight, as follows:

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment is made for any asphalt binder more than 0.4% above the optimum asphalt binder content specified in the JMD.

Method 1: Percent of asphalt binder for each sublot multiplied by the total HMA weight represented by that sublot.  The Engineer will use either ATM 405 or ATM 406 to determine the percent of asphalt binder.  The same test method used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  In the absence of testing, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2: Supplier's invoices minus waste, diversion, and remnant.  This procedure is an Engineer’s option for projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time that tankers are weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment is based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste HMA is calculated using the target value for asphalt binder as specified in the JMD.

3.	Job Mix Design. When specified, a Contractor furnished JMD is measured as one according to the HMA class and type.

4.	Temporary Pavement.  By weight, without deduction for the weight of asphalt binder or anti-strip additive.

5.	Leveling Course.  By Lane-Station (12 foot width) or by weighing without deduction for the weight of asphalt binder or anti-strip additive.

6.	HMA Price Adjustment.  Calculated by quality level analysis under Subsection 401-4.03.1.

7.	Longitudinal Joint Density Price Adjustment.  By the linear foot of top lift longitudinal joint under Subsection 401-4.03.2.

8.	Joint Adhesive.  By the linear foot of longitudinal and transverse joint.

9.	Pavement Smoothness Price Adjustment.  Calculated from inertial profiler data using FHWA’s ProVAL software under Subsection 401-4.03.3.

10.	Asphalt Material Price Adjustment.  Determined under Subsection 401-4.04.

11.	Liquid Anti-Strip Additive.  Based on the number of tons of asphalt binder containing required additive.

12.	Crack Repair.  From end to end of the crack repaired according to 401-3.10, measured horizontally along the centerline of the crack.

13.	Prelevel for Ruts, Delaminations, and Depressions.  By the surface area where prelevel is placed according to 401-3.10(1), measured according to Section 109.

14.	Repair Unstable Pavement.  By the surface area of pavement repaired according to 401-3.10(2), measured according to Section 109.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.

1.	Hot Mix Asphalt

The bid quantity of each type of HMA produced and placed is divided into lots and the lots evaluated individually for acceptance.

A lot is normally 5,000 tons. The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 401-4.03.1. Seasonal startup or a new JMD requires starting a new lot.

If less than 8 sublots have been placed at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot. The price adjustment computed for the prior lot will include the samples from the shortened lot. Density test results from material in the shortened lot will be based on the MSG of the first sublot of the shortened lot. If there is no prior lot, and there are at least 3 sublots, the material in the shortened lot will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot. If there are less than 3 sublots, the HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances.

If 8 or 9 sublots have been placed at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot.

If the bid quantity is between 1,500 to 5,000 tons, the quantity is considered one lot.  The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection.

For bid quantity less than 1,500 tons, HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances.

The Engineer reserves the right to perform any testing required in order to determine acceptance.

a.	Asphalt Binder Content. HMA samples shall be taken randomly by the Contractor in the presence of the Engineer from behind the paver screed before initial compaction, or will be taken randomly by the Engineer from the windrow, according to ATM 402 or ATM 403, at the discretion of the Engineer. The location (behind the paver screed or windrow) will be determined at the pre-paving meeting.  The Engineer will determine random sampling locations.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  At the discretion of the Engineer, Asphalt binder content will be determined according to ATM 405 or ATM 406.

b.	Aggregate Gradation. Aggregates tested for gradation acceptance will have the full tolerances from Table 401-2 applied.

(1).	Drum Mix Plants. Samples will be taken from the combined aggregate cold feed conveyor via a diverter device, from the stopped conveyor belt or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for samples from the conveyer system will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.

(2)	Batch Plants. Samples will be taken from dry batched aggregates according to ATM 301 or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for dry batch samples will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder.

c.	Density. The Engineer will determine and mark the location(s) where the Contractor takes each core sample.

(1)	Mat Cores: The location(s) for taking core samples is determined using a set of random numbers (independent of asphalt binder and aggregate sampling set of random numbers) and the Engineer's judgment. Take no mat cores within 1 foot of a joint or edge. Core samples are not taken on bridge decks.

(2)	Longitudinal Joint Cores: The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.

Take core samples according to ATM 413 in the presence of the Engineer. Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one six-inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  The Engineer will immediately take possession of the samples.  Backfill and compact voids left by coring with new HMA within 24 hours, and according to ATM 413. The Engineer will determine density of samples according to ATM 410.

d.	Asphalt binder Content, Aggregate Gradation, and Density - Retest. When test results have failed to meet specifications, retest of acceptance test results for asphalt binder content, gradation, and density may be requested provided the quality control requirements of Subsection 401-3.02 Contractor Quality Control are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2-foot radius of the original core.  The original test results are discarded and the retest result is used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  When gradation and asphalt binder content are determined from the same sample, a request for a retest of either gradation or asphalt binder content results in a retest of both. Both gradation and asphalt binder content retest results are used in the price adjustment calculation. Except for the first lot, retesting for gradation or asphalt binder from the first sublot of a lot will include retesting for the MSG. Retesting will be performed by the Department's regional laboratory.

2.	Asphalt Binder

The bid quantity of asphalt binder produced and placed is divided into lots and the lots evaluated individually for binder grade acceptance.

Testing will be by AASHTO accredited independent laboratories. When retesting is requested, the assigned value (ATV) will be determined using ASTM D3244. Each test will be completed by a different laboratory.

a.	Acceptance Test. The lot size for asphalt binder is 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it is added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it is sampled, tested and evaluated as a separate lot.

If the bid quantity of asphalt binder is between 85 to 200 tons, the quantity is considered as one lot and sampled, tested, and evaluated according to this subsection. Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Sample asphalt binder at the plant from the supply line in the presence of the Engineer according to ATM 401.  The Engineer will take immediate possession of the samples. Take three samples from each lot, one for acceptance testing, one for Contractor requested retesting, and one held in reserve for referee testing if requested.  Meet Subsection 702-2.01 requirements for asphalt binder quality.

b.	Retest. Submit a written request, for a retest, no more than 7 days from receiving notice of the failed acceptance test. In the request, identify the retest laboratory. The Engineer will send the second sample (retest sample) to the laboratory.  Provide the retest results to the Engineer. Contractor pays for the retest costs.

If the average of the combined test results ([acceptance + retest]/2) passes the specification requirement, the average value becomes the ATV. If this ATV fails the specification requirement, the Engineer or Contractor may request the third sample (referee sample) be tested.

c.	Referee Test. The Engineer will send the third sample (referee sample) to an agreed upon laboratory. The average of the combined test results ([acceptance + retest + referee]/3) equals the ATV. If the ATV fails to meet specifications, the Contractor pays for the referee test.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The Engineer may reject material which appears to be defective based on visual inspection.  If a test of rejected material is requested, a minimum of two samples are collected from the rejected material and tested.  If all test results are within specification limits, payment for the material is made.

The following methods are applied to each type of HMA with Price Adjustment Pay Items in the Contract. These methods describe how price adjustments are determined based on the quality of the HMA binder longitudinal joint density and pavement smoothness.

1.	HMA Price Adjustment.  Acceptance test results for HMA asphalt binder content, gradation and mat density are used in HMA price adjustment.  These test results for a lot are analyzed collectively and statistically by the Quality Level Analysis (QLA) method as specified in Subsection 106-1.03.3 to determine the total estimated percentage of the lot that is within specification limits. The values for percent passing the #200 sieve, asphalt binder content and density test results are reported to the nearest 0.1 percent.  All other sieves used in QLA are reported to the nearest whole number.

The HMA price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor (CPF) for HMA that includes gradation and asphalt binder content.  The second is the density pay factor (DPF).

A lot containing material with less than a 1.000 pay factor is accepted at an adjusted price, provided that pay factor is at least 0.800 and there are no isolated defects identified by the Engineer. A lot containing material that fails to obtain the minimum pay factor is considered unacceptable and rejected under Subsection 105-1.11.

HMA pay factors are computed as follows:

a.	All statistical Quality Level Analysis (QLA) is computed using the Engineer’s Price Adjustment programs.

b.	The USL and LSL are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2, or as shown below.  The TV is the specification value shown in the approved Job Mix Design.

TABLE 401-2

HMA LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4-inch or largest sieve size | 99 | 100 |
| 1/2-inch sieve or first sieve retaining aggregate | TV -6 | TV +6 |
| 3/8-inch sieve | TV -6 | TV +6 |
| No. 4 sieve | TV -6 | TV +6 |
| No. 8 sieve | TV -6 | TV +6 |
| No. 16 sieve | TV -5 | TV +5 |
| No. 30 sieve | TV -4 | TV +4 |
| No. 50 sieve | TV -4 | TV +4 |
| No. 100 sieve | TV -3 | TV +3 |
| No. 200 sieve* | TV -2.0 | TV +2.0 |
| Asphalt Binder Content, % | TV -0.4 | TV +0.4 |
| Mat Density, % | 92.0 | 100.0 |

*LSL for the No. 200 sieve is restricted by the broadband limits in Table 703-4.

c.	The percent within limits (PWL), Quality Levels and characteristic pay factors (PFs) are determined by the Engineer for each Lot in accordance with Subsection 106-1.03.3.  The Composite Pay Factor (CPF) for the lot is determined from gradation and asphalt binder content (ac) acceptance test results using the following example formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

Table 401-3 gives the weight factor (f) for each test property considered.

TABLE 401-3

WEIGHT FACTORS

| Property | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1-inch sieve | 4 | - | - |
| 3/4-inch sieve | 4 | 4 | - |
| 1/2-inch sieve | 4 | 5 | 4 |
| 3/8-inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve* | 20 | 20 | 20 |
| Asphalt Content, % | 40 | 40 | 40 |

The Density Pay Factor (DPF) is computed using HMA mat core compaction acceptance test results.

The CPF and DPF are rounded to the nearest 0.001.  The price adjustment for each individual lot is calculated as follows:

HMA Price Adjustment = [(CPF or DPF)* -1.000] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower

PAB = Price Adjustment Base = $110.00 per ton.

The HMA Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 401.0008.____.

2.	Longitudinal Joint Density Price Adjustment.  Longitudinal joint density price adjustment will be based on the project average of all top lift cold joint densities and determined as follows:

a.	Disincentive. Project average top lift joint density less than 91.0% MSG:

Deduct $3.00 per lineal foot.

b.	Incentive. Project average top lift joint density greater than:

92.0% MSG.		Add $0.50 per lineal foot

93.0% MSG.		Add $1.00 per lineal foot

94.0% MSG.		Add $1.50 per lineal foot

The longitudinal Joint Density Price Adjustment is the total price adjustment paid for under Item 401.0009.____.

3.	Pavement Smoothness Price Adjustment.  Pavement smoothness will be measured by the Engineer and reported as IRI (inches/mile), according to Subsection 401-3.18.  Incentive for pavement smoothness shall apply only if both the project average CPF and DPF are greater than or equal to 1.000.  Disincentive for pavement smoothness shall apply regardless of the project average CPF or DPF.

The Engineer will calculate the pavement smoothness price adjustment according to Method 1 (pavement placed over graded subgrade), and/or Method 2 (pavement placed over existing pavement). The SF is rounded to the nearest 0.001.

Method 1: SPA = PAB x PQ x SF,

where:

SPA = Pavement Smoothness Price Adjustment

PAB = $110.00 per ton,

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor (Table 401-4)

TABLE 401-4

SMOOTHNESS FACTOR (SF)

| IRI (in./mile) | SF |
| --- | --- |
| Less than 40.0 | 0.050 |
| 40.0 to 70.0 | 0.050 – (IRI – 40.0)/600.0 |
| 70.0 to 90.0 | 0.000 |
| 90.0 to 120.0 | (90.0 – IRI)/120.0 |
| Greater than 120.0* | - |

* Corrective Work required, see Subsection 401-3.18

Method 2: SPA = PAB x PQ x SF,

Where:

SPA = Pavement Smoothness Price Adjustment

PAB = $110.00 per ton,

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor = 0.120 x RR – 0.020; SF not to exceed 0.050

RR = Roughness Reduction = (Initial IRI – Final IRI) / Initial IRI

Initial IRI = 	Pre-project average IRI as measured and reported by the Engineer.  The Initial IRI will either be included in the bid documents or the timeline for when the Initial IRI will be measured will be identified in the bid documents.

Final IRI =	Top layer HMA average IRI as measured and reported by the Engineer according to Subsection 401-3.18.

The Pavement Smoothness Price Adjustment is the total price adjustment paid for under Item 401.2010.____.

3.	Pavement Smoothness Price Adjustment. Not applicable to this project.

4.	Asphalt Binder Price Adjustment. A lot quantity of asphalt binder, with a pay factor less than 1.00, is accepted or rejected per Table 401-3.01-1 Asphalt Binder Pay Factors.

TABLE 401-4.03-1

ASPHALT BINDER PAY FACTORS

| Pay Factor |  |  | 1.01 | 1.00 | 0.95 | 0.90 | 0.75 | Reject |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RTFO (Rolling Thin Film Oven) |  |  |  |  |  |  |  |  |
| DSR(a.1) | All Grades | G*/Sinδ, kPa-1 | ≥ 2.69 | 2.68–2.20 | 2.19–1.96 | 1.95–1.43 | 1.42–1.10 | < 1.10 |
| MSCR(a.2) | PG 52-40 V | JNR 3.2 |  0.39 | 0.40–0.50 | 0.51–0.59 | 0.60–0.69 | 0.70–1.00 | > 1.00 |
|  |  | % Rec3.2 | ≥ 86.0 | 85.9–75.0 | 74.9–68.0 | 67.9–60.0 | 59.9–55.0 | < 55.0 |
|  | PG 58-34 E | JNR 3.2 |  0.19 | 0.20–0.25 | 0.26–0.29 | 0.30–0.39 | 0.40–0.50 | > 0.50 |
|  |  | % Rec3.2 | ≥ 90.0 | 89.9–85.0 | 84.9–80.0 | 79.9–75.0 | 74.9–70.0 | < 70.0 |
|  | PG 64-40 E | JNR 3.2 | < 0.05 | 0.05–0.10 | 0.11–0.15 | 0.16–0.20 | 0.21–0.25 | > 0.25 |
|  |  | % Rec3.2 | ≥ 97.0 | 96.9–95.0 | 94.9–91.0 | 90.9–85.0 | 84.9 – 80.0 | < 80.0 |
| PAV (Pressurized Aging Vessel) |  |  |  |  |  |  |  |  |
| DS(a.3) | PG 64-40 E & All Other Grades | G*Sinδ, kPa | < 4711 | 4712–5000 | 5001–5289 | 5290–5578 | 5579–5867 | > 5867 |
|  | PG 52-40 V, PG 58-34 E | G*Sinδ, kPa | < 5700 | 5701–6000 | 6001–6300 | 6301–6600 | 6601 – 7000 | > 7000 |
| CS(a.4 & 5) | All Grades(a.4) | BBR, S, MPa | < 247 | 248–300 | 301–338 | 339–388 | 389–449 | > 450 |
|  | All Grades(a.5) | BBR, m | > 0.320 | 0.319–0.300 | 0.299–0.294 | 0.293–0.278 | 0.277–0.261 | < 0.261 |

Creep Stiffness (CS)	Dynamic Shear (DS)	Multiple Stress Creep Recovery (MSCR)

a.	Asphalt Binder Pay Adjustment = (Lowest Pay Factor – 1.00) x (tons in lot) x PAB x 5

Select the lowest pay factor from:

RTFO (test the binder residue at the performance grade temperature)

(1)	DS, All Grades, G*/Sinδ, kPa-1

(2)	MSCR: PG, Select the highest pay factor corresponding to, either JNR 3.2 or % Rec3.2 values

PAV

(3)	DS, PG, G*Sinδ, kPa

(4)	CS, All Grades, BBR, S MPa

(5)	CS, All Grades, BBR, m

b.	If three consecutive acceptance samples are out of specification, stop HMA production immediately and submit a corrective action plan to the Engineer for approval.

The Asphalt Binder Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 401.2021.____.

401-4.04  ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Subsection 702-2.01 Asphalt Binder, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

401-5.01 BASIS OF PAYMENT.

The following items, unless included as individual Pay Items, are subsidiary to the Section 401 Hot Mix Asphalt Pavement related Pay Items as included in the bid schedule:

	Asphalt binder

	Liquid anti-strip additives

	Crack sealing

	Crack repair

	Joint adhesive

	Surface sealing of longitudinal joints

	Surface tolerance corrections

	Patching defective areas

	Prelevel for ruts, delaminations, and depressions

	Repair unstable pavement

	Job mix design

	Density profiles, Subsection 401-2.10 Process Quality Control

	Repair work and materials when planing equipment breaks through existing pavement – Subsection 401-3.10 Preparation of Existing Surface

	Work and materials associated with Subsection 401-3.06 Hauling Equipment

	Work and materials associated with Subsection 401-3.20 Roadway Maintenance

Test Strips:  Subsection 401-2.10 Process Quality Control.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices for HMA and asphalt binder as included in the Bid Schedule.  Price adjustments 401.0008.____, 401.009.____, 401.0010.____ and 401.2021.____ do not apply.

b.	Failed.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Item 401.0005.____ HMA, Temporary, Type     ; Class     . Removal and disposal of temporary HMA is subsidiary.

The following price adjustment Pay Items, unless included as individual Pay Items in the bid schedule, are paid under 401.2022.____ Combined Price Adjustment.

401.0008.____ HMA Price Adjustment, Type     ; Class     ,

401.0009.____ Longitudinal Joint Density Price Adjustment,

401.0010.____ Pavement Smoothness Price Adjustment, Method    .

401.2021.____ Asphalt Binder Price Adjustment

Item 401.0008.____ HMA Price Adjustment, Type    ; Class    , is the sum of the price adjustments for each material lot, and for deductions and fees assessed.  Deductions and fees assessed include:

	Each mix design subsequent to the approved JMD for each type and class of HMA specified will result in a fee of $6000.

	Failure to cut core samples within the specified period will result in a deduction of $100 per sample per day.

	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day.

	If an asphalt binder referee test is requested and the ATV confirms the asphalt binder does not meet Contract requirements, a fee of $500 will be assessed.

Items 401.0008.____ HMA Price Adjustment, Type    ; Class    , and 401.2022.____ Combined Price Adjustment do not apply to the following:

	HMA contract quantity is less than 1500 tons.

	HMA leveling course and rut repair.

	Temporary HMA.

	Driveway and approach HMA.

Item 401.0015.____ Asphalt Material Price Adjustment.

For each Section as included in Subsection 401-4.04 Asphalt Material Price Adjustment, item 1.a, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

Item 401.0016.____ Crack Repair.  Cleaning loose material from cracks, asphalt binder, and HMA to fill cracks are subsidiary.

Item 401.0017.____ Prelevel for Ruts, Delaminations, and Depressions.  Cleaning loose material, asphalt binder, and HMA are subsidiary.

Item 401.0018.____ Repair Unstable Pavement. Removal of pavement and base course, asphalt binder, and HMA are subsidiary.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 401.0001.____ | HMA, Type ; Class . | Ton |
| 401.0002.____ | HMA, Leveling Course, Type IV ; Class B | LnSt |
| 401.0003.____ | HMA, Leveling Course, Type IV ; Class B | Ton |
| 401.0004.____ | Asphalt Binder, Grade PG . | Ton |
| 401.0005.____ | HMA, Temporary, Type II, Class B | Ton |
| 401.0006.____ | HMA, Type , Class . | SY |
| 401.0007.____ | Liquid Anti-Strip Additives | CS |
| 401.0013.____ | Job Mix Design | Each |
| 401.0014.____ | Joint Adhesive | LF |
| 401.0015.____ | Asphalt Material Price Adjustment | CS |
| 401.0016.____ | Crack Repair | LF |
| 401.0017.____ | Prelevel for Ruts, Delaminations, and Depressions | SY |
| 401.0018.____ | Repair Unstable Pavements | SY |
| 401.2022.____ | Combined Price Adjustment | CS |

CR401-040120

- SECTION 402
TACK COAT

Standard Modification

Replace Subsection 402-3.02 with the following:

402-3.02 EQUIPMENT. Furnish, maintain, and operate asphalt distributor to apply asphalt material uniformly at even heat on variable widths of surface up to 15 feet at readily determined and controlled flow rates. Provide an asphalt distributor capable of application rates from 0.01 to 0.11 gallon per square yard. Equip with a heater, tachometer, flow rate gauge, operable mechanical tank gauge, thermometer for measuring temperatures of tank contents, power unit for the pump and full circulation spray bars adjustable laterally and vertically.

402-3.04 APPLICATION OF ASPHALT MATERIAL.

Add the following at the end of the first paragraph:

Control deviation from any specified application rate to within 0.02 gallon per square yard.

Add the following after the second paragraph:

After application of the tack coat, the surface shall be allowed to cure without being disturbed for the period of time necessary to permit drying and setting of the tack coat. If necessary, the Engineer will determine when the tack has cured.

CR402.HSM20.6-113020

Special Provision

Replace Section 406 with the following:

SECTION 406
RUMBLE STRIPS

406-1.01 DESCRIPTION.  Form a series of indentations (rumble strips) into the roadway pavement.  Place rumble strips in each shoulder and the roadway centerline to the width, depth, and length as indicated in the Contract documents and/or as directed by the Engineer.

406-1.02 RUMBLE STRIP.  A single uniform circular concave (cross section) indentation/depression milled into the pavement surface having a length measured perpendicular to the direction of travel, a width measured in the direction of travel and a depth measured from the surface of the pavement to the bottom of the indentation.

406-2.01 MATERIALS.  None.

406-2.02 MILLING EQUIPMENT.  Use equipment designed specifically for milling rumble strips into asphalt pavement.  Equip milling machine with a rotary type cutting head with a maximum outside diameter of 24-inches and a minimum length of 16-inches capable of producing a depression both 12-inches and 16-inches in length by 7 1/2-inches in width to a depth shown in the Plans.  Arrange the cutting tips to provide a smooth cut (approximately 1/16-inch between peaks and valleys).

Furnish the milling equipment with a guidance system, including a guide, clearly visible to the operator, to provide for consistent alignment of each rumble strip cut at the offsets from traveled way indicated on the Plans and to provide uniformity and consistency throughout the project.  The equipment shall incorporate water into the cutting head to minimize dust caused by the milling operation.

Equipment Manufacture: provide training for the operators and a representative onsite during installation of the rumble strip test section(s) (Subsection 406-3.03).  Representative: remain onsite until test specimen(s) satisfy the Plans and Specifications as determined by the Engineer.

CONSTRUCTION REQUIREMENTS

406-3.01 PAVEMENT SURFACE PREPARATION.  Inspect roadway to receive rumble strips for acceptable pavement condition and stake locations to receive rumble strips prior to installation.  Prepare the roadway for the milling operation by providing a smooth clean surface.  Sweep all loose material from the roadway surface in line with the planned rumble strips and to each side of the strips for the width of the milling machine plus an additional 12” minimum per side or edge of pavement whichever is smaller, and as directed by the Engineer.

Sweep and broom as noted and with the equipment indicated in Subsection 643-3.04, No. 6, Sweeping and Power Brooming.

406-3.02 TOLERANCES FOR RUMBLE STRIPS.

1.	Length:   1/2-inch.

2.	Width:  1/2-inch.

3.	Depth:  1/16-inch.

4.	Spacing:   1/2-inch.

5.	Alignment:  1-inch from the striping layout in the Plans; existing striping and re-established striping.

If it is determined that the rumble strips are not being placed to specification, make immediate adjustments to correct the problem.

Rumble strips are unacceptable if:

1.	The strips are not straight.

2.	The length or width does not meet tolerance.

3.	The depth of the depression does not meet tolerance.

4.	The depression/indentation concave surface is not smooth, does not meet tolerance.

5.	The edge of the indentation/depression is not straight, smooth, and free of spalling.

6.	Pavement surface is damaged as a result of improper rumble strip installation.

Unacceptable rumble strip installation, dimensional, alignment, surface irregularities, and surface damage shall be ground, resurfaced and the rumble strip reinstalled to the satisfaction of the Engineer and at the Contractor’s expense.  Perform repairs using equipment similar to the equipment initially used to mill the rumble strip.  Do not perform repairs in a “patch work” manner.  If more than one repair is required; in a group of rumble strips repair the entire group.  Where a repair is required in a continuous run, repair the unacceptable rumble strip(s) and repair or replace the rumble strip to each side of the unacceptable rumble strip as required to provide continuity between rumble strips as originally intended.  The Engineer will confirm the extent of the repair(s) required.

If during production the work becomes unacceptable the Engineer may require resumption of testing, Subsection 406-3.03.  Testing in addition to the initial test for each rumble strip type will be at the Contractor’s expense.

406-3.03 RUMBLE STRIP TEST SECTION.  Install an initial 1/4 mile test section for each of the following rumble strip type(s):

1.	Shoulder.

2.	Centerline.

Demonstrate for each type of rumble strip that the equipment and method will provide the desired milled-in rumble strip, including the surface inside each depression, without damaging the surrounding asphalt pavement.  If any of the initial test sections do not meet tolerances, provide new equipment, new method, or make necessary adjustments and retest.  These additional test sections will be required before production runs will be allowed to begin.

Testing in addition to the initial test sections, one for the shoulder type and one for the centerline type, will be at the Contractor’s expense.

Additionally, demonstrate the means and methods, including the equipment, for containing dust and waste material.

406-3.04 TRAFFIC STRIPING RE-ESTABLISHMENT.  Traffic striping is required to provide guidance for the rumble strip installation operation.  Contractor, where shoulder and/or centerline striping is missing to the extent that rumble strip location cannot be determined by the Engineer, re-establish the striping location prior to the milling operation.  Re-establish missing striping location by measuring laterally across the roadway from adjacent visible striping.  Maintain the same lane widths that exist at each end of the missing striping.  Provide sufficient location marking or “rabbit tracks” to ensure an accurate milling operation.  Shoulder re-striping is not required.  Re-establishing roadway striping location will not be measured or paid for separately but will be subsidiary to the respective rumble strip pay items.

406-3.05  RUMBLE STRIP INSTALLATION.  Install the following types of rumble strip at the locations shown in the Plans:

1.	Shoulder.  Do not disturb existing shoulder striping.

2.	Centerline.  Place along the roadway centerline according to the patterns shown in the Plans.  Replace existing centerline stripe(s) after milling the pavement.  Payment for replacement striping is paid under Section 670, Traffic Markings.

In compacted pavement with a temperature below 80˚ F, mill each type of rumble strip to the dimensions shown in the Plans.  Locate the inside edge of the rumble strip as shown in the Plans.  The Engineer will randomly check the edge alignment of the milled pattern.

406-3.06 CLEAN UP OF MILLINGS.  Handle, transport, and store, or dispose of material according to the Alaska Department of Environmental Conservation (DEC) regulations.  Remove off the project, on a daily basis, waste material (millings) resulting from the operation.

Disposal:  Dispose waste material outside the project limits, unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the property owner.  Milled material not being spread on the roadway side slopes requires a Solid Waste Disposal Permit from the DEC.  Obtain a permit for disposal of milled material or dispose the material in a site previously approved.

Remove millings immediately following rumble strip installation.  Maintain the removal operation within 50 feet of the milling machine.  Dry power brooming and power brooming without direct immediate means of collection/pickup is not permitted.

During milling operations keep the travel lanes free of milling debris.  Do not berm the millings at the shoulder edge, do not allow milling debris to impede roadway drainage or enter waterways.  Use a sweeper, sweeper/vacuum, (Subsection 643-3.04 No. 6, Street Sweeping, and Power Brooming), continuously removing waste material, including dust from the operation.  Keep millings damp to help control airborne dust.  Millings shall not enter adjacent lanes open to traffic.

Remove the waste material from the roadway surface and any adjacent pathway beyond the shoulder.  Shoulder millings may be placed off of the road or pathway beyond the shoulder on the side slopes, except in areas where guardrail is present.  Uniformly spread shoulder millings on the roadway side slopes; alternatively, it may become property of the Contractor and disposed of off the project as indicated above.

Milled roadway segments shall be returned to debris-free state prior to re-opening for traffic.

406-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Measure pay units by station, foot, or mile parallel to the centerline of the highway.

Station.  A single lineal measurement for every measured station for each shoulder rumble strip and centerline rumble strip installed.

Linear Foot.  A single lineal measurement for every measured foot of rumble strip installed.

Mile.  A single lineal measurement for every measured mile for each shoulder rumble strip and centerline rumble strip installed.

Shoulder rumble strip measurement includes gaps (provided for bicycles or other as shown in the Plans) between groups of rumble strips.

406-5.01 BASIS OF PAYMENT.  Section 109.

All work, including test strips and materials, is subsidiary to 406 Pay Items, except where specified as individual Pay Items.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 406.0001.____ | Rumble Strips | LS |
| 406.0002.____ | Rumble Strips | STA |
| 406.0003.____ | Rumble Strips | LF |
| 406.0008.____ | Rumble Strips, Shoulders | Mile |
| 406.0012.____ | Rumble Strips, Centerline | Mile |
| 406.2001.____ | Sweeping and Disposal of Millings, Shoulders | LS |
| 406.2002.____ | Sweeping and Disposal of Millings, Centerline | LS |

CR406-110812R1

DIVISION 500 — STRUCTURES

Blank Page

SECTION 503
REINFORCING STEEL

Special Provisions

503-3.02 PROTECTION OF MATERIALS. Replace the 2nd sentence of the 1st paragraph with the following: Before placing reinforcing steel in the work, ensure that the reinforcing steel is free of salt, rust, and foreign substances that may affect the performance of the reinforcing steel.

503-3.05 SPLICING. Replace “c. Testing/Inspection” under Item 2. Electric Resistance Butt Welded Joints with the following:

c. 	Testing/Inspection.

Perform job control tests using a testing laboratory with experience with ASTM A370 and California Test Method 670. A job control test consists of the fabrication, under the same conditions used to produce the splice, and the physical testing of 4 sample splices for each lot of splices. An authorized Department representative will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of shop produced resistance welded butt joints is defined as no more than 150 splices of the same type of welds used for each combination of bar size and bar deformation pattern that is used in the work.

The Engineer or the Engineer's authorized representative shall witness the job control tests performed by the testing laboratory. Give the Engineer at least 7 working days’ notice before beginning control tests.

Identify sample splices with tamper proof and weatherproof markings prior to shipment to the testing laboratory.

The sample shall consist of a resistance welded butt splice bar and a control bar that are identified and marked as a set. The same reinforcing bar (hoop) may be used to provide the test weld and control bar.

Test each sample to failure in accordance with ASTM A706, ASTM A370 and California Test Method 670. Determine the ultimate tensile strength for all control bars by testing the bars to failure.

The production lot will be rejected if:

- a sample fails within one bar diameter of the splice at less than 95 percent of the ultimate tensile strength of the associated control bar

- necking of the bar prior to rupture, as defined in California Test Method 670, is not observed

- a sample does not meet the mechanical requirements of ASTM A706 Grade 60

Replace “c. Qualifications and Submittals.” and “d. Testing/Inspection.” under Item 4. Mechanical Butt Splices with the following:

c.	Qualifications and Submittals. A splice will be considered qualified if the splice can develop a minimum tensile strength of 80000 psi, based on the nominal bar area, and the bars within the splice do not exceed a total slip shown in Table 503-3, when tested according to the relevant material ASTM, ASTM A370 and California Test Method 670.

TABLE 503-3
ALLOWABLE TOTAL SLIP LENGTH

| Reinforcing Bar No. | Total Slip (inch) |
| --- | --- |
| 4 | 0.020 |
| 5 | 0.020 |
| 6 | 0.020 |
| 7 | 0.028 |
| 8 | 0.028 |
| 9 | 0.028 |
| 10 | 0.036 |
| 11 | 0.036 |
| 14 | 0.048 |
| 18 | 0.060 |

Submit the following information:

    - the manufacturer's name;

    - the name of the product or assembly;

    - the lot, heat, or batch number that identifies the splice;

    - the bar grade and size number to be spliced by the material;

    - a complete description of the splice and installation procedure; and,

    - Tensile Test results including:

      - bar nominal area;

      - ultimate load at failure;

      - ultimate tensile strength;

      - necking results (either visually or through strain values); and,

      - failure mechanism and location.

(7)	Slip Test results including:

      - initial length measurements;

      - final length measurements; and,

      - calculated slip.

  - Testing/Inspection. Perform job control tests consisting of the fabrication, under conditions used to produce the splice. For each lot of splices perform 6 slip tests and 6 tensile tests using different sample splices for each test. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical butt joints is defined as no more than 150 splices of the same type of mechanical butt splice used for each combination of bar size and bar deformation pattern that is used in the work.

Make splice samples using the same splice materials, position, equipment, and following the same procedures as used to make splices in the work. Make splice samples at least 5 feet long with the splice at mid-length. Shorter sample splice bars may be used if approved by the Engineer.

Perform job control tests in the presence of the Engineer. Splices tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 7 working days prior to performing testing.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample according to the relevant material ASTM, ASTM A370 and California Test Method 670. Perform tensile testing until partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection.

The production lot will be rejected if:

- the minimum individual tensile strength of the sampled splices is less than 80000 psi based on the nominal bar area

- the maximum individual slip length of the sampled splices is greater than the limits in Table 503-3

Replace “b. Qualifications” and “c. Testing/Inspection.” under Item 5. Mechanical Lap Splices. with the following:

- Qualifications. A splice will be considered qualified if the splice can develop a minimum tensile strength of 75000 psi, based on the nominal bar area, when tested according to the relevant material ASTM, ASTM A370 and California Test Method 670.

Submit the following information:

    - the manufacturer's name;

    - the name of the product or assembly;

    - the lot, heat, or batch number that identifies the splice;

    - the bar grade and size number to be spliced by the material;

    - a complete description of the splice and installation procedure; and,

    - test results indicating the splice, used according to the manufacturer's procedures, complies with the minimum tensile strength requirements.

  - Testing/Inspection. Perform job control tests consisting of the fabrication, under conditions used to produce the splice, and tensile testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical butt joints is defined as no more than 150 splices of the same type of mechanical butt splice used for each combination of bar size and bar deformation pattern that is used in the work.

Make splice samples using the same splice materials, position, equipment, and following the same procedures as used to make splices in the work. Make splice samples at least 5 feet long with the splice at mid-length. Shorter sample splice bars may be used if approved by the Engineer.

Perform job control tests in the presence of the Engineer. Splices tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 7 working days prior to performing testing.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample according to the relevant material ASTM, ASTM A370 and California Test Method 670. Tensile test each sample until partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection.

All splices in the lot represented by a test will be considered to meet the tensile strength requirements when the minimum individual tensile strength of the sampled splices is not less than 75000 psi, based on the nominal bar area.

CFHWY00213

SECTION 505
PILING

Special Provisions

505-3.03 DRIVING PILES.

Replace the 1st sentence in the 1st paragraph with the following:

Drive all piles, except piles for lighting standards, to the driving resistance and minimum penetration specified in the Contract documents using the pile driving criteria provided by the Engineer.

Add No. 5:

5.	Piles for Lighting Standards. For lighting standards, install piles of sufficient length to cut the pile at the required cut-off elevation and to provide the minimum installed length shown on the Plans.

Sites for lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

When the minimum pile length, shown on the Plans, for a lighting standard foundation cannot be achieved, install the pile tip to an elevation established by the Engineer.

CR505.2-100118R

505-3.07 pILE TRANSPORT. Add the following:

Remove, handle, and transport pile in such a matter that no damage occurs.  Repair any existing damage and any new damage that occurs to the pile and the coatings during transport.  Repair or replace the damaged pile to the satisfaction of the Engineer.  The Engineer may reject damaged pile.

Prior to project completion, three (3) pieces of excess Structural Steel Piles (4'-0" dia. x 1" Pipe), Bare Steel ~40 feet in length, shall be transported to 5300 East Tudor Road. Notify the Engineer ten (10) days prior to coordinate delivery and a storage location of excess pile.

505-4.01 METHOD OF MEASUREMENT. Add the following:

Pile Restrike. Calendar Day: Every full day shown on the calendar, beginning and ending at midnight. Measurement begins at the first midnight following the 30 hour subsidiary restrike period.  Measurement will be for each full 24 hour day that pile driving operations are ceased at a substructure unit to allow a restrike as directed by the Engineer. Measurement ends at the midnight immediately prior to the pile restrike.

505-5.01 BASIS OF PAYMENT. Remove and replace Items 1 under Drive Piles with the following:

1.	All related work required to drive the piles to the Minimum Penetration and Driving Resistance, including: pile crew time (including payroll and administrative additives), equipment costs, and other fixed or variable items incurred during pile driving, the construction of temporary work platforms, fresh heading, splicing, restrike within the first 30 hours after initial drive, pile cleanout and cutting off.

Add the following:

Pile Restrike. The contract price includes all pile crew time (including payroll and administrative additives), equipment costs, and other fixed or variable items that occur during suspension of pile driving operations. Pile Restrike is not subject to the compensation for altered quantities provisions of Subsection 109-1.04.

Add the following pay item:

| Item Number | Item Description | Pay Unit |
| --- | --- | --- |
| 505.2001.____ | Pile Restrike | DAY |

CFHWY00213

SECTION 507
BRIDGE BARRIERS AND RAILING

507-2.01 Materials. Add the following:

Epoxy			Subsection 712-2.21

507-3.01 CONSTRUCTION REQUIREMENTS.

Add the following to the end of the first paragraph:

- General.  Set the grout underneath rail post base plates monolithically.

CFHWY00213

SECTION 508
WATERPROOFING MEMBRANE

Special Provisions

CONSTRUCTION REQUIREMENTS

508-3.02 FIELD QUALITY CONTROL.

Add the following to Item 2 after the second paragraph.

- If on-site representative uses magnetic test equipment, perform testing in accordance with SSPC-PA2 Measurement of Dry Coating Thickness with Magnetic Gages.

- If on-site representative uses ultrasonic test equipment, perform testing in accordance with SSPC-PA9 Measurement of Dry Coating Thickness on Cementitious Substrates Using Ultrasonic Gages.

- Calibrate spray equipment with the stroke count per gallon of material sprayed method.

- Repair destructive areas by re-spraying or filling with special 2 component gun grade material provided by the manufacturer.

- Test the thickness of the other components of system using wet film or stroke per gallon methods.

Perform testing as needed to ensure proper thickness of each application but not less than 1 test for every 100 square feet of coated area.

Perform visual inspections of all coated surfaces throughout the installation process. Identify and repair all holidays or other defects in the waterproofing membrane system.

Add the Following:

508-3.05 SUBMITTALS. Submit for approval a copy of the manufacturer’s latest data sheets, installation procedure, curb and corner details, and manufacturer’s representative name and experience. Provide one complete submittal not less than 30 days prior to installation of the waterproofing membrane system.

508-3.06 QUALITY ASSURANCE. Install waterproofing membrane system under the on-site supervision of a representative from the manufacturer. The representative must be on site for the full duration of installation and testing operations. Do not substitute manufacturer’s representative listed in the submittal without prior written approval from the Engineer.

CFHWY00213

Special Provisions

Replace Section 510 with the following:

SECTION 510
REMOVAL AND REPAIR OF CONCRETE BRIDGE DECK

510-1.01 DESCRIPTION. Remove all loose material and repair spalled and deteriorated concrete areas as directed.

510-2.01 MATERIALS.  Use materials that conform to the following:

Grout	Subsection 701-2.03

Water	Subsection 712-2.01

CONSTRUCTION REQUIREMENTS

510-3.01 GENERAL. Perform work to meet the applicable requirements of Section 202.

Prevent damage to reinforcing steel designated to remain in place. Missing reinforcing steel will not be replaced.

Following the concrete removal, the Engineer will inspect any exposed reinforcing steel. ***Deleted***

510-3.02 METHOD OF REMOVAL. ***Deleted***

Remove dust and loose particles by compressed air or other approved methods.

Capture and contain all wastewater and debris within the work area.

***Deleted***

Reinforcing Steel. Clean all reinforcing steel that is to remain in place and has been exposed by removal operations. Remove all rust and corrosive products immediately prior to grout placement. Remove oil, dirt, concrete fragments, laitance, loose scale, and other coating that would destroy or inhibit the bond with the new concrete.

510-3.03 PATCHING DECK.  At the time of installation, the ambient air temperature must be between 40°F and 80°F unless otherwise specified by the manufacturer.

Thoroughly abrasive blast clean concrete in the repair area just prior to placing the Grout. Immediately prior to material installation vacuum clean or air-blow clean with oil-free compressed air all receiving surfaces.  Leave no loose material on any receiving surface.

After cleaning and prior to placing Grout, wet the existing concrete surface to contact the patch material, or use an approved epoxy bonding agent on the existing concrete bonding surface, according to the manufacturer’s recommendations.

Apply Grout to meet the minimum and maximum lift thickness recommended by the manufacturer.  Finish the repair smooth and level with the surrounding existing concrete.  After leveling, match the surface texture of the adjacent existing concrete.  Prior to opening to traffic, cure according to manufacturer's recommendations and to a compressive strength of 4,000 psi when tested according to AASHTO T 106 or ASTM C109 or as approved by the Engineer.  After curing and before final acceptance, sound all patched areas.  Remove and replace all unsound or cracked areas.

510-3.04 CLEANUP. Following concrete removal, clean the job site and remove debris. Dispose of debris at a Department of Environmental Conservation approved landfill. Remove dust and loose particles by compressed air or other approved methods.

510-4.01 METHOD OF MEASUREMENT. See Section 109

510-5.01 BASIS OF PAYMENT. The contract price includes full compensation for containment structures, debris collection systems, wastewater filtration systems, disposal of debris, and incidentals required to complete the work.

510.2001.____ Bridge Deck Repair Maintenance. Includes maintenance repairs after Item 510.2000.____ is complete for any new existing deck repairs exclusive of Item 510.2000.____ locations. Will be at the contingent sum prices ***Deleted***. Prices for this item will be by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor.

***Deleted***

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

510.2001.____	Bridge Deck Repair Maintenance	CS

510.2000.____	Bridge Deck Repair	SF

CFHWY00213

- SECTION 550
COMMERCIAL CONCRETE

Standard Modification

550-2.02 COMPOSITION OF MIXTURE – JOB MIX DESIGN.

Replace Table 550-1 with the following:

TABLE 550-1

COMMERCIAL CONCRETE DESIGN REQUIREMENTS

| Class | B-B | B | W |
| --- | --- | --- | --- |
| Water-Cement Ratio, lbs/lbs, maximum | 0.40 | 0.45 | 0.50 |
| Total Air Content, % | 5.5 – 6.5 | 5.5 – 6.5 | 4.0 – 6.5 |
| Coarse Aggregate Gradation, AASHTO M43a. | No. 57 or 67 | No. 57 or 67 | No. 7, 8, 57, or 67 |
| Compressive Strength, psi, minimum | 5,000 | 4,000 | 3,000 |

a.	Alternative sizes of coarse aggregate, as shown in AASHTO M 43, may be used when approved in writing.

550-5.01 BASIS OF PAYMENT.

Replace the first sentence with the following:

If items 550.0001.____, 550.0002.____, 550.0003.____, 550.0004.____, 550.0005.____, or 550.0006.____ do not appear in the Bid Schedule concrete is subsidiary to other items.

Add the following pay items:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 550.0005.____ | Class B-B Concrete | LS |
| 550.0006.____ | Class B-B Concrete | CY |

CR550.HSM20.8-113020R

Blank Page

DIVISION 600 — MISCELLANEOUS
CONSTRUCTION

Blank Page

SECTION 602
STRUCTURAL PLATE PIPE

Special Provisions

602-1.01 DESCRIPTION. Add the following:

Furnish and install buried structures for pedestrian underpasses.  Provide design calculations and load ratings with an independent design check.

Add the following Subsection:

602-1.02 DEFINITIONS.

Culvert Bridge. Culverts and buried structures meeting the requirements of National Bridge Inspection Standards (NBIS) CFR §650.305 and individual culverts and buried structures greater than 20 feet in width, as measured along the centerline of roadway crossing over the structure.  When specified in the Contract or required by the DOR, this includes the headwalls, toe walls, wingwalls, and foundation.

Culvert Bridge Design Package (CBDP).  DOR design calculations, DOR load ratings, IE design check calculations, IE load ratings, working drawings, and specifications.

Designer of Record (DOR). A civil engineer registered as a Professional Engineer in the State of Alaska, and in responsible charge of the work described. The DOR must have adequate and relevant prior structural design and inspection experience. The DOR may delegate portions of design, quality acceptance, and inspection work, to qualified technicians. The DOR and qualified technicians must not be supervised by, or under the direction of the Contractor’s superintendent and work crew.

Independent Design Check (IDC). An independent design check of the design and load rating calculations including but not limited to: design, load ratings, location and dimensions of the foundation, structural members, connections, erection plan and temporary bracing (when required), safety barrier, and independent calculations of design loads, member stress, material properties, hydraulic capacity and scour protection.

Independent Engineer (IE). An engineer registered as a Professional Engineer in the State of Alaska, and in responsible charge of the independent design check. The engineer responsible for the check must have adequate and relevant prior structural design experience.

Provide contractor-designed culvert bridges to meet the Contract and provide an independent design check.  Inspect and perform quality acceptance on culvert bridges.  Provide design calculations with load ratings for the culvert bridges.

CFHWY00213 / CFHWY00308

Replace Subsection 602-2.01 with the following:

602-2.01 MATERIALS.	Use materials that conform to the following:

Bedding and Backfill	Subsection 204-2.01

Flexible Watertight Gaskets	Subsection 705-2.05

Corrugated Steel Pipe, Pipe Arches, and Underdrains	Subsection 707-2.01

Corrugated Aluminum Alloy Culvert Pipe and Underdrains	Subsection 707-2.03

Structural Plate Culverts	Subsection 707-2.04

Concrete	Section 501

Reinforcing Steel	Section 503

Structural Steel	Section 504

Riprap	Section 611

Structural Fill	Section 703

Drain Rock	Section 703

Pea Gravel	Section 703

CR602.1-061520 / CFHWY00213 / CFHWY00308

Add the following Subsection:

602-2.02 GEOTECHNICAL DATA AND HYDROLOGY INFORMATION. The Department may provide records of geotechnical investigations.  The Contractor is responsible for obtaining additional geotechnical data necessary for the design and construction of the culvert bridge.

Add the following Subsection:

602-2.03 DESIGN REQUIREMENTS. Retain the services of a DOR to design and provide a CBDP for each culvert bridge.  Retain the services of an IE to perform an IDC of each CBDP.

1.	Design culvert bridges according to the following documents:

- Alaska DOT&PF Standard Specifications for Highway Construction for recommended construction methods, material properties, and sampling and testing;

- AASHTO LRFD Bridge Design Specifications, as modified by Subsection 602-2.03;

- Alaska Highway Preconstruction Manual; and the

- Alaska Bridges and Structures Manual (BSM).

2.	Design culvert bridges that:

- support 100% of HL93 live loads or the Contractor’s maximum construction load whichever is greater, without overstress. Follow the most recent version, including interim version, of the AASHTO LRFD Bridge Design Specifications. Indicate governing live load on working drawings;

- meet the design life specified in AASHTO LRFD Bridge Design Specifications after allowing for metal section loss associated with abrasion and pH levels of the substrate and water;

- meet the seismic acceleration values recommended in the AASHTO LRFD Bridge Design Specifications;

- include the capacities and demands of load-supporting members in the design calculations;

- meet the dimensions, stations, offsets and elevations of inverts and riprap requirements shown on the Plans;

- provide the minimum hydraulic capacity shown on the Plans when openings are required to allow for the passage of water; and

- provide the minimum horizontal and vertical clearances shown on the Plans when openings are required to allow the passage of traffic.  If no vertical clearance is provided, follow the requirements in the Alaska Highway Preconstruction Manual.

3.	Provide working drawings for culvert bridges including:

- Dimensions controlling the culvert bridge design and erection, including proposed fill depth, corrugation spacing, corrugation depth, gauge thickness, concrete thicknesses, reinforcing steel size and locations, clear opening sizes, utility size and locations, and similar controlling dimensions;

- Design loads and material properties; and

- The soil bearing values.

4.	Provide load ratings for the culvert brides according to the most recent version, including interim version, of the AASHTO Manual for Bridge Evaluation (MBE) and the BSM.  Load rate metal and concrete culvert bridges using the Load Factor Rating (LFR) and Load and Resistance Factor Rating (LRFR) methods.

Provide load ratings that reflect the bridge culvert final as-constructed condition.  Include values for moment, shear and, where applicable, thrust for concrete culvert bridges.  Include values for wall area, buckling, and seam strength for metal culvert bridges.  Specify live load type, placement for maximum stress, distribution, and impact.

Include the following cases for LFR load ratings:

- Inventory with multiple lanes and impact included

- Operating with multiple lanes and impact not included

- Operating with one lane centered on the roadway and impact not included.

Include the following cases for LRFR load ratings:

- Inventory with multiple lanes and impact included

- Operating with multiple lanes and impact included

- Operating with one lane centered on the roadway and impact not included.

Add the following Subsection:

602-2.04 DESIGN SUBMITTALS AND REVIEW. Submit the following for review and approval at least 30 days prior to the beginning of fabrication or construction related to the culvert bridges:

- The CBDP.  The design drawings and load ratings in the CBDP must be stamped with the seal of, dated by, and signed by the DOR;

- An IDC letter stamped with the seal of, dated by, and signed by the IE certifying: “The Culvert Bridge Design Package meets the AASHTO LRFD Bridge Design Specifications, the AASHTO Manual for Bridge Evaluation, and the Contract requirements”.

Revise and resubmit the CBDP to incorporate any comments received during review.  Resubmit the IDC letter after comments have been incorporated.

The approval of the CBDP shall not be construed as a complete review, but will only indicate that the general method of construction and working drawings are acceptable to the Department, that the CBDP appears complete, and that an IDC letter was provided.  The Contractor shall remain responsible for all aspects of the culvert bridge.

CFHWY00213 / CFHWY00308

Replace Subsection 602-3.01 with the following:

602-3.01 CONSTRUCTION REQUIREMENTS. Lay field-assembled plate pipes in conformance to the lines and grades approved by the Engineer. Excavation, grading, shaping, and backfill must conform to Subsection 204-3.01.

Dewater ground water from work areas; construct and maintain temporary water diversion when working in waterways, and for facilities or structures with active drainage according to Section 204.

Repair damage to the zinc coating according to AASHTO M 36.

Comply with the manufacturer's recommendations and instructions. Provide the Engineer with a copy of the documentation.

When shown on the Plans, place riprap in accordance with Section 611.

Do not begin fabrication or construction of culvert bridges without the written approval of the Engineer.  Do not open culvert bridges to traffic without the approval of the Engineer.

Perform all assembly and erection procedures under the direct supervision and control of an on-site technical representative of the culvert manufacturer.

Contractor shall place pea gravel under haunches of pipe where adequate compaction cannot be obtained by standard compaction devices (e.g. rollers, skid plates, jumping jacks, etc.).  Shape pipe bedding and pea gravel prior to installation of pipe.

The Contractor shall furnish and install an aluminum structural plate box culvert, including headwalls, wingwalls, and toewall, of the dimensions shown on the Drawings.  The structural plate box culvert must be aluminum alloy meeting the requirements of Subsection 707-2.04.  Aluminum plate thickness shall be a minimum of 0.125 inches.

Headwalls, wingwalls, and toewalls shall be of the same material as the structural plate box culvert.  A toewall extending at least 24 inches below the invert shall be installed at both ends of culvert.  Dimensions of headwalls and wingwalls shown in the Plans are approximate and may vary (plus or minus 6 inches) based on manufacturer availability as approved by the Engineer.

The Contractor shall submit shop drawings for the corrugated aluminum structural plate box culvert (including headwalls, wingwalls, and toewalls) to the Engineer for approval and approval obtained from the Engineer before purchasing any structural plate pipe.  Submitted shop Drawings must be supplied by the manufacturer of the structural plate pipe.

The Contractor may request the substitution of a corrugated aluminized steel structural plate box culvert (including headwalls, wingwalls, and toewall) for the corrugated aluminum structural plate box culvert if the Contractor can obtain a culvert of equivalent dimensions, including rise and span, as that shown in the Drawings.  The aluminized structural plate box culvert must meet the requirements of Subsection 707-2.01-02.  The requested substitution structure must be shown to have equivalent structural support for the roadway cover and vehicular loading as the structure shown in the Drawings.  Shop Drawings prepared by the manufacturer and provided by the Contractor must be provided to the Engineer for approval with a request for a material substitution and approval obtained from the Engineer before purchasing the corrugated aluminized steel structural plate box culvert.

Structural Plate Box Culvert Availability.   The Contractor is recommended to contact the following manufacturers regarding culvert fabrication:

Contech Engineered Solutions LLC	James Pipe & Supply

111 E. 100th Ave.	P.O. Box 593

Anchorage, AK 99515	Ridgefield, WA 98642

907-344-1144	360-887-3900

Ferguson Heating & Cooling	Big R Ridge

1977 E. Bogard Road	P.O. Box 97

Wasilla, AK 99654	Ravensdale, WA 98051

907-376-8765	253-797-8293

Contractor shall be responsible for shipping and transporting the structural plate box culvert, headwalls, wingwalls, and toewall to the project site.  Contractor is responsible for assembling and installing the structural plate box culvert, headwalls, wingwalls, and toewall as shown in the Drawings.

CR602.1-061520 / CFHWY00213 / CFHWY00308

Add the following Subsection 602-3.02 Joining Pipe:

602-3.02 JOINING PIPE. Joints shall provide circumferential and longitudinal strength to preserve the pipe alignment, prevent separation of pipe sections, and provide a watertight joint between new sections of pipe and joints between new and existing sections of pipe of similar and dissimilar materials. Include a continuous gasket (seal) in all joints. Construct the watertight joint capable of passing a laboratory hydrostatic pressure and vacuum test of at least 4 psi for 10 minutes.

CR602.1-061520

Add the following Subsection 602-3.03:

602-3.03 TEMPORARY WATER DIVERSION AND DEWATERING. Submit a plan for work area dewatering and each waterway diversion, 14 days before related construction activities. Do not implement the plan without written approval.

Comply with permit requirements. Additionally:

1.	Do not exceed State of Alaska water quality standards.

2.	Do not divert water from dewatering into waterway, except if the required permits are attained from, but not limited to, Alaska Department of Natural Resources, Alaska Department of Environmental Conservation, Corp of Engineers, and the U.S. Environmental Protection Agency.

3.	Provide an approved disposal site for work area excess water.

4.	Prevent turbid water from directly entering the waterway.

5.	Discharge work site water a minimum of 100 ft. from waterway.

6.	Diverting water onto the roadway is not permitted.

7.	Complete diversion and dewatering activities during the fish window described in the Alaska Department of Fish and Game Title 16 Fish Habitat Permit.

8.	Relocate fish contained inside the coffer/diversion dam areas before the site is dewatered. Relocate fish to the closest pool upstream of the construction area.

9.	In addition to other equipment required to complete the temporary water diversion and dewatering work maintain, a minimum of two trash pumps with hoses, at the site during diversion construction activities. Maintain the intake to prevent fish entrapment, entrainment, or injury with the use of perforated or slotted plate and woven wire with a mesh size not greater than 3/32 inch or a profile bar and wedgewire with openings not greater than 1/16 inch.  Do not exceed passive approach velocity of 0.2 fps and active approach velocity of 0.4 fps.

CFHWY00213 / CFHWY00308

***Deleted***

602-5.01 BASIS OF PAYMENT. Add the following:

Unclassified excavation, Selected material, Type A and C, D-1 base course, and pathway asphalt are paid for under Sections 203, 301, and 608, accordingly.

The CBDP, engineering, inspection, labor, equipment, and materials necessary to design, load rate, and install culvert bridges are subsidiary.

Concrete collar, concrete cap beam, associated reinforcing steel is subsidiary to the Section 602 pay items.  Dewatering and pea gravel are subsidiary to the Section 602 pay items.

Traffic control paid under Section 643 and Erosion, sediment, and pollution control paid under Section 641.

All work associated with transporting, assembling, and installing the structural plate box culvert, headwalls, wingwalls, and toewall is subsidiary to pay item 602.2001.0000, Aluminum Box Culvert Span 10'-0", Rise 4'-10".

Add the following Pay Items:

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 602.2001.0000 | Aluminum Box Culvert, 10’ 0” Span, 4’ 10” Rise | LF |
| 602.2006.1308 | Aluminum Structural Plate Pipe-Arch 13’-8” Span x 12’ 4” Rise | LF |

CFHWY00213 / CFHWY00308

Special Provision

Replace Section 603 with the following:

SECTION 603
CULVERTS AND STORM DRAINS

603-1.01 DESCRIPTION.  Construct or reconstruct culvert and storm drain pipe. Install culvert marker posts, and strap plastic culvert ends.

Dewater work areas as necessary to install culverts and pipes.

Provide all labor, materials, equipment, and operations required to furnish and install culverts to the lines and grades shown on the Plans. This shall include locations within the Department Right-of-Way (ROW) as well as within the Alaska Railroad Corporation’s (ARRC) ROW. This work includes the removal and reinstallation of the existing railroad tracks, ballast, and embankment.

603-1.02 REFERENCES.

ASTM D3953	Standard Specification for Strapping, Flat Steel and Seals

ASTM D4675	Standard Guide for Selection and Use of Flat Strapping Materials

ARRC Standard Specifications for Work on Railroad Property Section 12, Open Trenching

ARRC Standard Specifications for Work on Railroad Property Section 12, Excavations

ARRC Technical Standards for Roadway, Trail, and Utility Facilities in the ARRC Right-of-Way, Jan 2014

AREMA Manual for Railway Engineering, latest edition

603-2.01 MATERIALS. Use materials that conform to the following:

Bedding and Backfill	Subsection 204-2.01

Joint Mortar	Subsection 705-2.04

Flexible Watertight Gaskets	Subsection 705-2.05

Non-reinforced Concrete Pipe	Subsection 706-2.01

Reinforced Concrete Pipe	Subsection 706-2.02

Corrugated High Density Polyethylene (HDPE) Pipe	Subsection 706-2.07

Corrugated Steel Pipe and Pipe Arches	Subsection 707-2.01

Corrugated Aluminum Pipe	Subsection 707-2.03

Galvanize	Subsection 716-2.07

Culvert Marker Posts (Flexible Delineator Posts)	Subsection 730-2.05

Item 603.0017.____, Pipe, listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP), Corrugated Aluminum Pipe, Reinforced Concrete Pipe, or Corrugated Dual Wall HDPE (plastic) Pipe. Select pipe for each installation that meets or exceeds the requirements shown on the Plans for height of cover.

For steel and plastic pipe, match the end section material to the pipe material.

Separate dissimilar materials with an electrical insulating material.  The insulating material must be at least 1/16 inch thick and approved by the Engineer.

Culvert marker post is 6-foot tall by 2.5 inches wide with reinforcing ribs, capable of a 9-inch minimum bending radius, and blue with no marking.

Culvert marker Strap and Seals according to ASTM D3953. .625 inch x .02 inch, dry Type 1 regular-duty (magnetic, ferritic), galvanized Finish B (hot-dipped Grade 2 moderate coating, .18 oz./ft2 surface or .0002 inch thick minimum. Push type seals, Style III (overlap), regular duty, galvanized Finish B (hot-dipped coating) by 1.75-inch minimum length and matched to strapping width.

CONSTRUCTION REQUIREMENTS

603-3.01. GENERAL. Excavate, bed, and backfill according to the requirements of Subsections 204-2.01 and 204-3.01, and the Plans.

Dewater ground water from work areas; construct and maintain temporary water diversion when working in waterways, and for facilities or structures with active drainage according to Section 204.

Work windows for installation of culverts under the railroad are determined by ARRC as noted in the Temporary Construction Permit.

603-3.02. LAYING PIPE. Begin the pipe laying at the downstream end of the pipe. Keep the lower segment of the pipe in contact with the bedding throughout its full length. Place bell or groove ends of rigid pipe and outside circumferential laps of flexible pipe facing upstream.

Lay paved or partially lined pipe so that the longitudinal centerline of the paved segment coincides with the flow line. Install elliptical conduit and circular conduit reinforced with other than a full circular cage or cages so the orientation of a vertical plane through the longitudinal axis of the conduit does not vary more than 5 degrees from the design orientation.

Repair damaged metallic coating on metal pipe according to AASHTO M36.

603-3.03 JOINING PIPE. Joints shall provide circumferential and longitudinal strength to preserve the pipe alignment, prevent separation of pipe sections, and provide a watertight joint between new sections of pipe and joints between new and existing sections of pipe of similar and dissimilar materials. Include a continuous gasket (seal) in all joints. Construct the watertight joint capable of passing a laboratory hydrostatic pressure and vacuum test of at least 4 psi for 10 minutes.

1.	Rigid Pipe. Use either bell and spigot or tongue and groove joints. Join pipe sections with the ends fully entered and the inner surfaces reasonably flush and even.

Use one or more of the following joint materials, or any other if approved:

a.	Portland cement mortar

b.	Portland cement grout

c.	Rubber gaskets

d.	Coupling bands

e.	Preformed plastic sealing compound

Make mortar joints using an excess of mortar to form a bead around the outside of the pipe.

For grouted joints, use molds or runners to retain the poured grout. Install rubber ring gaskets to form a flexible, watertight seal.

When using portland cement mixtures, protect the completed joints against rapid drying using suitable covering material.

2.	Metal Pipe. Join the metal pipe firmly using connecting bands conforming to ASTM B745 (Corrugated Aluminum Pipe) and ASTM A760 (Corrugated Steel Pipe) and as noted herein. Use bands that are no more than two nominal sheet thicknesses lighter than the pipe jointed, and in no case more than 0.052 inches lighter. Include a gasket each side of the gap.

a.	Primary Band. Furnish and install corrugated bands so that the band corrugations match and conform to the corrugations of the pipe. Conform to the following guidelines:

(1)	The gap between the pipes joined is in the center of the band and is no wider than one corrugation width.

(2)	Band for 12-inch through 30-inch diameter pipe are at least 12 inches wide.

(3)	Bands for pipe with diameters greater than 30 inches are at least 22 inches wide.

b.	Secondary Band. Use this band only where it is not physically possible to use primary bands, such as on field-cut pipe ends, joining new pipe to existing pipe, etc. Furnish and install deformed metal sheet bands (dimple bands) so that the projections match and are the same depth as the pipe corrugations. Form these projections in circumferential rows with one projection for each corrugation of the helical pipe.

Conform to the following guidelines:

(1)	The gap between the pipes joined is in the center of the band and is no wider than 2 inches.

(2)	Bands for 12-inch diameter pipe are at least 12 inches wide and have one circumferential row of projections for each pipe end joined.

(3)	Bands for pipe with diameters greater than 12 inches are at least 24 inches wide and have two circumferential rows of projections for each pipe end joined.

3.	Plastic Pipe. Use push-on or mechanical joints. Ensure that the plastic pipe couplings' corrugation matches the pipe corrugation and that their width is not less than one-half the nominal pipe diameter.

Furnish all bolted connections on coupling bands with cut washers placed between the nut and the angle bracket or use nuts with integral washers.

Take up any pipe that is out of alignment, unduly settled, or damaged and re-lay or replace it.

603-3.04 CULVERT MARKER.

a.	Marker Post. Install a culvert marker on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed. Drive to maintain forty-two inches of post above the ground after driving, and

b.	Marker Strap. In addition to marker posts, install marker strap around the plastic pipe ends.

Position the strap in the valley of the first annular ring from the top end of the culvert. From the vertical centerline of the culvert, at the top, overlap the strap and extend the ends to approximately 30 degrees each side of the centerline. Place the strap loosely without twists in the valley, without compressing the pipe, and tight enough to keep the strap from moving out of the valley without deforming the pipe or pipe corrugation. Seal the strap at three locations, one at each of the ends, and one at the top of the culvert. Extend the strap ends beyond the end seals approximately 1/2-inch. Double crimp the seal, two pairs of crimps minimum each seal.

Repair the strap galvanizing where abraded and at cut ends according to ASTM A780. Prepare the surface with power tools per SSPC-SP11, hand tools per SSPC-SP2, and as required by the paint manufacturer. Apply paint, Type – paint containing zinc dust, to the prepared surfaces and allow enough time for curing as required by the manufacturer's printed instructions.

603-3.05 RAILROAD COORDINATION. The Contractor shall field survey the existing railroad track along the top of the proposed trench prior to track removal. The Contractor shall remove and reinstall the existing track material at the direction of the Railroad. The Railroad will cut and reconnect the track material at the edge of the work limits.

603-4.01 METHOD OF MEASUREMENT. Section 109, and as follows:

1.	Culvert Pipe. The length of pipe, measured in place, along the invert.

2.	Pipes for Storm Drains. The length of pipe, measured in place, along the invert, from center to center of structures. The length through the inlets, catch basins, and manholes is included in the measured length.

603-5.01 BASIS OF PAYMENT. Branch connections and elbows are subsidiary to the pipe unless included as a separate Pay Item.

Coupling bands, seals (gaskets), and other items necessary for the proper joining of the sections are subsidiary.

Culvert markers are subsidiary to the pipe.

Surveying, removal and reinstallation of the existing track, other work and items necessary to complete the installation of pipe under railroad track, and complying with ARRC requirements and work windows are subsidiary to the pipe.

Pavement removal, temporary pavement, temporary water diversion, dewatering and rewatering, and temporary guardrail are subsidiary to the pipe.

Existing culvert removal is paid for under Section 202.

Excavation, bedding, and backfill paid under Section 204.

Railroad ballast is paid for under Section 617.

Traffic control paid under Section 643 and erosion, sediment, and pollution control paid under Section 641.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 603.0001.____ | CSP ___ Inch | LF |
| 603.0002.____ | ___ Inch CSP Arch | LF |
| 603.0003.____ | End Section for CSP ___ Inch | Each |
| 603.0004.____ | End Section for ___ Inch CSP Arch | Each |
| 603.0009.____ | Corrugated Aluminum Pipe ___ Inch | LF |
| 603.0010.____ | ___ Inch Corrugated Aluminum Pipe Arch | LF |
| 603.0011.____ | End Section for Corrugated Aluminum Pipe ___ Inch | Each |
| 603.0012.____ | End Section for ___ Inch Corrugated Aluminum Pipe Arch | Each |
| 603.0013.____ | Reinforced Concrete Pipe, ___ Inch, Class ___ | LF |
| 603.0014.____ | Reinforced Concrete End Section, ___ Inch | Each |
| 603.0015.____ | Elbow, (Type & Size) | Each |
| 603.0016.____ | Branch Connection (Type & Size) | Each |
| 603.0017.____ | Pipe ___ Inch | LF |
| 603.0019.____ | ___ Inch Pipe Arch | LF |
| 603.0020.____ | End Section for Pipe ___ Inch | Each |
| 603.2032.____ | Corrugated HDPE Pipe ___ | LF |
| 603.2033.____ | End Section for Corrugated HDPE Pipe ___ | Each |

CR603-061520 / CFHWY00213

Special Provisions

Replace Section 606 with the following:

SECTION 606
GUARDRAIL

606-1.01 DESCRIPTION. Construct new guardrail, terminal sections, transition rail, and permanent crash cushions.

The permanent crash cushion, hereafter referred to as, "crash cushion," includes the complete assembly (crash cushion, foundation, backstop or transition) represented in the FHWA eligibility letter(s).

Remove and reconstruct or remove and dispose of existing guardrail, terminal sections, transition rail, and crash cushions.

CR606-020119R

Furnish and install bollard(s) included in the Plans and Specifications.

CR606.9-020119R

Furnish and store new highway safety appurtenance essential replacement parts (replacement parts) listed in Table 606-1. Repair damage, from highway crashes, with the replacement parts.

CR606.13-072120

606-1.02 SUBMITTALS.

1.	Submit the following at the preconstruction conference and receive approval before installation.

a.	Permanent Crash Cushions.

(1)	FHWA Eligibility Letter(s).  Eligibility letters demonstrating each crash cushion assembly is MASH 2016 compliant with the AASHTO 2016 Manual for Assessing Safety Hardware (MASH-16) Test Level 3.  Demonstrate the eligibility letter shielding widths cover the hazard widths and travel directions shown in the plans.

(2)	AASHTO Listing Category. AASHTO listing or documented updates for the crash cushion classification as listed in the 2011 AASHTO Roadside Design Guide, Section 8.4.

(3)	Manufacturers' Shop Drawings, Assembly, and Installation Instructions.  Submit shop drawings and detailed assembly and installation instructions for the crash cushion as included in the FHWA Eligibility Letters.

(4)	Manufacturer Certification Letter. Certify the crash cushion(s) meet the requirements of the FHWA eligibility letter(s), are suited to the Contract requirements including the environmental conditions at the installation site.

(5)	Manufacturers' Installer Certification Letter. Certify the installation contractor is familiar with and trained to install the crash cushion.

(6)	Manufacturers' Installation Checklist. Submit a crash cushion installation checklist.

b.	Parallel Terminals.

Manufacturer Installation Checklist. Submit an Assembly Installation Checklist.

2.	Submit the following after installation.

a.	Permanent Crash Cushions.

(1)	Manufacturer Certification Letter. Certify the installed crash cushion(s) meet the requirements of the FHWA eligibility letters. Submit the certification letters(s) signed and dated no more than 14 days after installation.

(2)	Manufacturers' Installation Checklist. Submit the completed installation checklist signed by the Installer and Manufacturer no more than 14 days after installation. Complete the checklist after each assembly.

b.	Parallel Terminals.

Manufacturer Installation Checklist. Submit the completed installation checklist signed by the Installer and Manufacturer no more than 14 days after installation. Complete the checklist after each assembly.

606-2.01 MATERIALS. Use materials that conform to the following:

Concrete, Class B	Section 550

Flexible Delineator Posts	Subsection 730-2.05

Guardrail Connection Plate	Section 722

Guardrail Hardware	Subsection 710-2.07

Guardrail Posts and Blockouts	Subsection 710-2.06

High Strength Bolts	Section 722

Metal Beam Rail	Subsection 710-2.04

Terminals	Subsection 710-2.11

Terminal Markers	Subsection 730-2.05

Wire Cable	Subsection 709-2.02

Guardrail Reflector Assembly Brackets, Side-Mounted. Aluminum alloy.

Retroreflective Sheeting.

1.	Post-Mounted Flexible Delineators and Guardrail Reflectors. ASTM D4956 Type IX or XI.

2.	Terminal Markers. ASTM D4956 Type VIII, IX or XI.

Permanent Crash Cushion Assembly.

Crash cushions include the complete assembly as included in the Eligibility Letter, the crash cushion, the foundation, and rigid backup anchorage, or transition connection. Install an added Terminal Marker or other flexible delineator to the front of the crash cushions as recommended by the Manufacturer.

Design the crash cushion for the installation location environment. Snow combined with frequent freeze-thaw cycles creates significant ice buildup that may impair the performance of the crash cushion.  Design to mitigate the effects from snow and ice. Crash cushions using supports that interlock and travel within fixed tracks at or below the first six inches from ground level, and crash cushions not designed to mitigate snow and Ice buildup are not acceptable for permanent use. Crash cushion covers, when available from the manufacturer, are required as part of the crash cushion installation.

Crash Cushion Classifications. 2011 AASHTO Roadside Design Guide, 4th Edition.  The Engineer will determine the final classification of each materials submittal.  Provide redirective and non-gating crash cushions of the type specified in the plans and matching the description noted below.

1.	Sacrificial:  Demonstrated designed for a single impact.

2.	Reusable Crash Cushion.  Demonstrated to have major components survive most impacts intact and salvageable.  Some components require replacement after a crash.

3.	Low-maintenance and Self-restoring Crash Cushion. Demonstrated to suffer very little, if any damage, upon impact and easily pulled back into their full operating condition.  They may partially rebound after an impact and may only need an inspection to ensure that no parts have been damaged or misaligned.

CR606-020119R

Bollards.

Concrete; Class B	Subsection 550-2.01

Shapes, Plates and Bars	ASTM A 36

Bollard Pipe	Subsection 716-2.06

Bollard Tube	ASTM A 500, Grade B

Welding	Subsection 716-2.02

Galvanizing	Subsection 716-2.07

Galvanizing Repair	ASTM A 780

Paint (Paint for Steel Structures/Paint of Timber)	Subsection 708-2.01/2.02

Bollard Post (WCLIB; Posts and Timbers, Douglas Fir-Larch No. 1)	Subsection 713-2.01

Preservatives and Pressure Treatment Process for Timber	Subsection 714-2.01

Backfill Material (Selected Material, Type A)	Subsection 703-2.07

Retroreflective Bands (6 inch wide reflector, smooth surface bands)	ASTM D4956, Type III-A

CR606.9-020119R

CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL. Install guardrail and terminals at the locations shown on the Plans. Conform to the Alaska Standard Plans and these Specifications.

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals, that are required to completely install a segment of guardrail before beginning work on that segment.

Start guardrail installation at the "upstream" end (the end adjacent traffic encounters first) by either installing a crashworthy terminal, connecting to an existing barrier or shielding the end with a crash cushion or truck mounted attenuator (TMA) meeting NCHRP 350, Test Level 3.  Continue installation in the direction of traffic.  Exception:  if the guardrail run connects to existing barrier, buried in the backslope terminal, existing or new bridge railing, or other existing structure at the "downstream" end, guardrail installation may start at the point of connection.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail. At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test level 3 at all non-crashworthy guardrail ends within the construction clear zone. Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

When possible, proceed with construction of guardrails with the direction of traffic.

Where necessary, adjust the height of existing guardrail to provide a smooth transition to new guardrail. Use 25 linear feet of guardrail or two 12’ 6” pieces of guardrail to transition to match the existing or new guardrail elements and/or end treatments.

After shaping the slopes and staking proposed guardrail terminal section locations, request the Engineer to field verify their locations. Receive approval of the staked locations before installing terminal sections.

Treat field cuts to timber posts and blockouts according to AWPA standard M 4.

Install blockouts according to manufacturer’s recommendations and as shown on the plans.

Install side-mounted guardrail reflectors and post-mounted flexible delineators as follows:

1.	at intervals noted on the plans or Alaska Standard Plans, starting with the first guardrail post beyond terminal sections

2.	with the retroreflective sheeting facing approaching traffic

3.	with retroreflective sheeting on both sides, on two-way roadways

4.	not on the terminal sections, except as shown on the plans

5.	at or below 500 feet in elevation, except as noted otherwise in the Plans.

Attach terminal markers, in a vertical position, to the P.T. post of Short Radius Guardrail sections and to the post where the flare begins for parallel guardrail terminals.  Coordinate terminal marker locations with the Engineer.

At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

CR606-020119R

Do not remove existing highway safety appurtenances, guardrail and similar, before mobilization of the replacement parts to the project storage location.

CR606.13-072120

606-3.02 POSTS. Set posts to accommodate the line, grade, and curvature shown on the Plans.

Use either wood or steel posts when allowed by the type of guardrail specified, subject to the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

Set posts as follows:

1.	Set posts plumb, in the location and to the depth shown on the Plans or Alaska Standard Plans.

2.	Choose an installation method that does not damage the post, adjacent pavement, structures, utility conduits, and final slopes. Repair all damage to the satisfaction of the Engineer, or replace the damaged item, as per subsection 105-1.11.

3.	Set wood or steel posts in dug, drilled, or pre-punched holes. Steel posts may also be set by ramming or driving if:

a.	The underlying material is no larger than six inch; and

b.	The posts are not damaged during installation.

4.	Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically. Compact under and around posts to the Engineer’s satisfaction.

5.	For placement in solid rock or broken rock embankment greater than six inch, set wood or steel posts in pre-dug, pre-drilled, or pre-punched holes.

6.	In new roads, install posts before final shoulder or median compaction, surfacing, and paving.

606-3.03 BEAM RAIL. Fabricate metal work in the fabricator’s shop. Bend curved guardrail elements with radii less than or equal to 100 feet in the fabricator’s shop or with an approved bending apparatus.

Receive approval before field punching, cutting, or welding. Repair damaged spelter coat areas on galvanized rail elements according to AASHTO M 36 (ASTM A760).

Lap rail elements so that the exposed ends face away from approaching traffic in the adjacent lane.

Use bolts long enough to extend at least 1/4 inch beyond the nuts. Except where required for adjustments, do not extend bolts more than 1 inch beyond the nuts.

Locate bolts at expansion joints at the center of the slotted holes.

Tighten bolts at expansion joints to snug-tight. Make all other bolts fully-tight.

606-3.04 CABLE RAIL. Install cable guardrail according to the Plans and Specifications. Install at the locations shown on the Plans.

606-3.05 TERMINAL SECTIONS.

Parallel Terminals.

Install terminal sections according to the manufacturer’s recommendations for the entire length of the terminal then, if required, transition rail height over 25’ to match guardrail height and splice location.

Install ASTM D4956 Type III, IV, or V retroreflective sheeting on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal according to guidance for Object Markers for Obstructions Adjacent to the Roadway in Chapter 2C of the ATM.

Submit the manufacturers' complete Assembly Installation Checklist signed and dated after completing installation to support acceptance for each installation, see Subsection 606-1.02 for further information.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Remove and reconstruct guardrail as specified. Replace lost or damaged materials without extra compensation.

When replacing existing guardrail complete the replacement run installed within 14 calendar days after removal.

For guardrail located within 50 feet of bridge ends, remove and replace the existing guardrail in the same work shift.

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL. Remove the existing guardrail, including the rail, cable elements, terminal sections, hardware, posts, concrete bases, and steel tubes. Backfill resulting holes with material in 6-inch layers that is similar to the existing embankment and compact to the same approximate density.

Guardrail.

Notify the Engineer a minimum of 5 days before removing guardrail.  The Engineer will notify the ADOT & PF, M & O, and have an M & O representative designate portions of guardrail for salvage.  Deliver salvaged guardrail and associated hardware to the Silvertip M & O Station located at Mile 60 of the Seward Highway. Remaining items removed become the Contractor's property.

Permanent Crash Cushion.

Notify the Engineer a minimum of 5 days before removing permanent crash cushions.  The Engineer will notify the ADOT & PF, M & O, and have an M & O representative designate portions of the crash cushion for salvage.  Deliver salvaged crash cushion and associated hardware to the Silvertip M & O Station located at Mile 60 of the Seward Highway. Remaining items removed become the Contractor's property.

606-3.08 ADJUST EXISTING GUARDRAIL. When called for on the Plans, reset existing guardrail to the height shown on the applicable Alaska Standard Plan, measured from the top of the rail to the finished shoulder surface below the rail. Raise and lower the posts several times to prevent settlement and then re-drive them to the height shown on the Plans. Use other methods if approved.

606-3.09 INSTALL NEW GUARDRAIL. Install guardrail as shown on the applicable Alaska Standard Plan, measured from the top of the rail to the finished shoulder surface below the rail.

Install MASH-16 Test Level 3-compliant W31 guardrail as shown on the plans.  Install new guardrail in conformance with tolerances shown on the plans.

606-3.10 TERMINAL MARKERS. For each parallel rail terminal, attach a terminal marker to the extreme piece of rail.

Attach flexible markers, in a vertical position, to the terminal end directly to the backside of the rail face, the face away from the traveled way, or the first post of each parallel guardrail terminal.  Provide an additional marker where the flare begins for guardrail terminal widening.  Provide two markers at the end of each run of guardrail; coordinate the locations with the Engineer.

Attach the flexible markers using hardware and attachment methods recommended by the manufacturer. The connection shall not negatively influence the performance of the guardrail as noted in 606-2.01.

606-3.11 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  When the Engineer determines additional guardrail is required, complete the installation immediately.

606-3.12 PERMANENT CRASH CUSHION.  Install crash cushions according to the manufacturer's instructions.

Construct crash cushions to shield the hazard width and travel direction shown in the plans.

Manufacturer's Crash Cushion Installation Certification. Submit the Manufacturer's Crash Cushion Installation Certification letter signed and dated after completing installation, see Subsection 606-1.02 for further information.

Manufacturer Certified Installers.  Install crash cushions using installers certified by the crash cushion manufacturer.  Install Crash cushions as follows:

1.	Parallel to the approach traveled way or as shown on the plans.

2.	Follow Section 203 for the excavation and embankment requirements of the concrete base component of the crash cushion.

3.	Follow Section 501 for a concrete pad, sized according to the manufacturer's recommendations, constructed on a minimum of 12 inches of Selected Material, Type B.

4.	Cut or fill to the top of the concrete pad with Selected Material, Type B at 12:1 or shallower on installations in grass median.

5.	Install top elevation of concrete pad flush to pavement edge when adjacent to or within asphalt pavement.

6.	Bolt crash cushion to median barrier with manufacturer approved barrier to crash cushion connector when attached to median barrier.

7.	Install a terminal marker or other flexible delineator on the nose of each crash cushion as recommended by the manufacturer.  The terminal marker is in addition to, not a substitute for, the retroreflective delineation installed on the crash cushion nose.

8.	Manufacturers' Crash Cushion Installation Checklist. Submit the installation checklist signed and dated after completing installation, see Subsection 606-1.02 for further information.

The crash cushion installation is not complete until the Crash Cushion Manufacturers' Installation Checklist and Installation Certification letter are submitted and the Engineer accepts the installation.

Excess excavated material is the property of the Contractor.

CR606-020119R

606-3.13 BOLLARDS.

1.	Steel Bollards.  Galvanize all steel members and hardware.

a.	Perform all welding according to AWS D1.1.

b.	Shop galvanize steel bollards and associated hardware, after fabrication.  Repair damage to galvanizing after installation.

2.	Wood Bollards.  Preservative treat all wood material.

a.	Treat field cuts, bolt holes, and similar according to AWPA Standard M4.

Install bollards in concrete, plumb, back fill with specified material, and compact to the satisfaction of the Engineer.  Provide the Engineer with lock keys.

Shop paint steel bollards with one coat of primer and two top coats of safety yellow. At the site repair nicks, scratches, and other damage.  In the shop and field, clean, prepare the surface and apply the materials as recommended by the manufacturer.

Apply two white retroreflective bands placed 3-4 inches from the top with a maximum of 6 inches between the bands.

CR606.9-020119R

606-3.14 HIGHWAY SAFETY APPURTENANCE – ESSENTIAL REPLACEMENT PARTS. Install replacement parts as directed.

Deliver the remaining new replacement parts, at time of substantial completion, to the State Maintenance and Operations Station, located at:

Silvertip M & O Station, Mile 60 of the Seward Highway

Notify the Engineer no less than 7 days before delivery.

CR606.13-072120

606-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

1.	Guardrail. Measured along the face of the rail or cable, from the center of the end posts.

Short Radius Guardrail. Per each, installed in place.

When the guardrail is connected to a terminal section, the pay limit for the rail ends where the specified terminal section begins.

2.	Terminals. Per each, installed in place.

3.	Transition Rail (Bridge Rail Thrie Beam Transition or Bridge Rail W-Beam Transition). Per each accepted connection.

4.	Permanent Crash Cushion.  Each installed and accepted.

606-5.01 BASIS OF PAYMENT.

Payment for temporary crash cushions or TMA installed to protect motorists when guardrail installations are not completed within 10 calendar days of beginning installation is subsidiary to other items.

1.	Guardrail. Side-mounted guardrail reflectors, post-mounted flexible delineators, terminal markers, guardrail beam, posts, blockouts, and associated hardware are subsidiary.  Installation of downstream anchors, transitions for rail height and splice locations, long span guardrail sections, and guardrail stiffening sections are subsidiary to guardrail installation.

2.	Short Radius Guardrail Sections. The contract price includes all materials from the terminal anchor to and including the first wood or steel post of standard guardrail or guardrail end terminal, and including the terminal anchor assembly, in-line anchor, terminal posts, short radius guardrail posts, rail elements, terminal markers, and associated hardware required for a complete installation.

3.	Terminal Sections.

a.	Parallel Guardrail Terminal. The contract price includes rail elements, posts, blockouts, pipe sleeves, cable assemblies, guardrail extruders, terminal markers, and all associated hardware required for a complete installation.

4.	Transition Rail. The contract price includes all brackets, beam sections, transition pieces, and all posts and associated hardware required for a complete connection of the guardrail section to a bridge rail or barrier.

5.	Permanent Crash Cushion.  The contract price includes all work and materials required to install each permanent crash cushion, foundations, and connections along with the manufacturer's field support, recommendations, and shop drawings.  Removal and salvage of existing crash cushions is subsidiary to Pay Item 606.2007.____ Pay Item(s).

6.	Bollard(s).  Payment for bollard Pay Items is full compensation for furnishing all labor, equipment, and materials required for a complete installation as shown in the Plans and included in the Specifications.  Consider the following part of a complete installation when in the Plans or included in the Specifications and are subsidiary to the Pay Item:

|  |  Concrete |  Marker(s) |  Removable bollard hardware |
| --- | --- | --- | --- |
|  |  Excavation & backfill |  Padlock(s) |  Retroreflective bands |
|  |  Galvanizing & repair |  Painting & repair |  Steel reinforcing |
|  |  Grading |  Preservative treatment & repair |  |
| Other items included in the Plans or Specifications associated with the bollards(s) |  |  |  |

All material required for embankment widening for guardrail and terminal sections is paid for under the appropriate pay items shown in the bid schedule.

Guardrail salvage is subsidiary to Pay Item 606.0006.____ Removing and Disposing of Guardrail.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 606.0001.____ | W-Beam Guardrail | LF |
| 606.0002.____ | Thrie Beam Guardrail | LF |
| 606.2003.____ | Box Beam Guardrail | LF |
| 606.0004.____ | Cable Guardrail | LF |
| 606.0005.____ | Removing and Reconstructing Guardrail | LF |
| 606.0006.____ | Removing and Disposing of Guardrail | LF |
| 606.0007.____ | Double-faced, W-Beam Guardrail | LF |
| 606.0009.____ | Short Radius Guardrail | Each |
| 606.0013.____ | Parallel Guardrail Terminal | Each |
| 606.0015.____ | Adjust Existing Guardrail | LF |
| 606.0016.____ | Transition Rail | Each |
| 606.2004.____ | Wood Bollard, Removable | Each |
| 606.2007.____ | Crash Cushion, Permanent ____________ | Each |

CR606-020119R / CFHWY00308

TABLE 606-1

HIGHWAY SAFETY APPURTENANCES – ESSENTIAL REPLACEMENT PARTS

| Essential Replacement Parts | Material Specification | Unit | Quantity |
| --- | --- | --- | --- |
| W-Beam Guardrail | Subsection 710-2.04 | LF | 275 |
| Thrie Beam Guardrail | Subsection 710-2.04 | LF |  |
| Cable Guardrail | Subsection 709-2.02 | LF |  |
| Box Beam Guardrail | Subsection 710-2.04 | LF |  |
| Wood Guardrail Post and Blockout | Subsection 710-2.06 | Each |  |
| Steel Guardrail Post and Blockout | Subsection 710-2.06 | Each |  |
| Short Radius Guardrail | Alaska Standard Plan G-26.00 | Each | 1 |
| Parallel Guardrail Terminal | Subsection 710-2.11 | Each | 1 |
| Transition Rail | Subsection 710-2.04 | Each | 1 |
| Crash Cushion, Permanent | Subsection 606-2.01 | Each |  |
| Precast Concrete Barrier | Subsection 501-3.01 & 709-2.01 | LF |  |
| Rigid Delineator | Subsection 730-2.05 | Each |  |
| Flexible Delineator | Subsection 730-2.05 | Each |  |

Replace damaged replacement parts at no additional cost to the Department.

6.	606.2006.____ Essential Replacement Parts – Installation. Installation of the replacement parts according to the directive authorizing the work.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 606.2005.____ | Essential Replacement Parts | LS |
| 606.2006.____ | Essential Replacement Parts – Installation | CS |

CR606.13-072120

Replace Section 608 with the following:

SECTION 608
SIDEWALKS

Special Provisions

608-1.01 DESCRIPTION. Construct, or retrofit asphalt, or concrete sidewalks.

Sidewalk Section 608 includes "sidewalks", pathways, medians, curb ramps, miscellaneous on-grade concrete, and asphalt surfaces not addressed elsewhere in the specifications.

608-2.01 MATERIALS. Use materials that conform to the following:

1.	Concrete

Bed Course Material	Subsection 703-2.03

Joint Fillers	Subsection 705-2.01

Joint Sealers	Subsection 705-2.02

Concrete	Section 550, Class B

Acid Wash	Muriatic or Phosphoric

Admixtures	AASHTO M 194 Chemical Admixtures†

ASTM C 494 Standard Specification for Chemical Admixtures for Concrete†

Curing Agents	ASTM C 309, Liquid Membrane-Forming Compounds for Curing Concrete †

Expansion Joints	AASHTO M-33 Preformed Expansion Joint Filler for Concrete (Bituminous Type)

Integral Color Agent	ASTM C 979 Standard Specification for Pigments for Integrally Colored Concrete

Reinforcing Steel	Section 503

†	Compatible with colorant manufacturer.

Provide concrete for slabs according to Section 501, ACI 303R, 303.1, this specification and the material manufacturer's and supplier's written instructions.

Maximum slump 4-inch, except 8-inch maximum if using super plasticizers or mid-range water reducers. Mix used for sample(s) shall be the same as the production mix(s).

Concrete - Exposed Aggregate Finish. Provide aggregate from a single source.  Keep aggregate for exposed aggregate finish separate from other project aggregate.

Concrete – Colored. Color concrete using an integral color, with a surface hardener, a color cure, a release agent, and a sealer compatible with colorant(s).

Concrete - Pattern Imprinted. Use a manufactured system designed to provide the pattern specified and a release agent compatible with the colorant.

2.	Asphalt (HMA)

Bed Course Material	Subsection 703-2.03

Asphalt Binder, PG 52-28	Subsection 702-2.01

Aggregate, Type II or III	Subsection 703-2.04

Mix Design Requirements (ATM 417)

Marshall Stability, pounds, min.	1000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

Coating/Paint:

Material - Methyl Methacrylate (MMA)	Subsection 712-2.17 (MMA only)

Color	Federal Standard 595, color 30111 (Brick Red)

3.	Detectable Warnings

Cast iron detectable warning plates with truncated dome pattern, a slip resistant surface, and with handle or flange on bottom or approved equal. Detectable warning plates shall be coated with yellow polymer soaked finish. Detectable warnings shall be manufactured according to the 2006 U.S. DOT ADA Standards for Transportation Facilities.

608-2.02 REFERENCES.

1.	ACI 303		Cast-In-Place Architectural Concrete Practice

2.	PCA PA124		Finishing Concrete Slabs with Color and Texture

3.	PCA SP021		Color and Texture in Architectural Concrete

608-2.03 SUBMITTALS – EXPOSED AGGREGATE, COLORED CONCRETE, PAINTED HMA AND PATTERN IMPRINTED CONCRETE AND HMA.  Provide complete submittals (3 printed copies, except samples as specified below), to the Engineer for review and approval, at least 21 days before beginning construction of concrete and asphalt items.  Submittals will be returned to the Contractor within 14 days from the date submitted, marked as approved by the Department, or requiring revisions.  Amend and resubmit the documents for review until approved by the Engineer.  Receive approval before beginning production.

Submit shop drawings, product data, specifications, certifications; manufacturers and installer's resumes, and samples as specified in Section 401, 501, 503, 608 and herein.

1.	Shop Drawings, Product Data, Specifications, and Certifications.

a.	Exposed aggregate finish:  manufacturer's chemical surface retarder.

b.	Integral concrete colorant:  manufacturer's color chart, and chipset.  Indicate color additive numbers and required dosage rates as part of the concrete mix submittal, Subsection 501-3.01.

c.	Manufacturer's concrete pattern imprinting system.

d.	Manufacturer's fabricated HMA pattern imprinting tool - shop drawings.

e.	Methyl Methacrylate for coating HMA.

f.	Other when requested by the Engineer.

2.	Resumes.

a.	Manufacturer.

Concrete. Provide documentation for five years of successful product performance, with a minimum of five completed projects and including but not limited to:

	Manufacturer's colorant, hardener, color cure, release agent, and sealer

	Batch Plant's mixing of manufacturer's colorants and other additives, and product delivery

	Manufacturer's pattern imprinting system

HMA. Provide documentation of two years and three projects successfully fabricating pattern imprinting tools and successful product performance applying MMA in similar applications to this Project.

b.	Installer.

Concrete and HMA. Installer(s) with 2 years' experience and 3 successfully completed projects of similar configuration and method of installation.

In addition:

1)	For projects with concrete integral colorant and or pattern imprint system, provide a minimum of one project using the proposed manufacturer's colorant and pattern imprint system.

3.	Manufacturer's.

All manufacturers, listed and other, are required to submit for review and approval.

Manufacturers of concrete colorant and pattern imprinting systems:

| Bomanite Corporation P.O. Box 599 Madera, CA 93639 Ph: 303.369.1115 Fax: 303.291.0282 Email: bomanite.com | Brickform, division of Solomon Colors, Inc. 11061 Jersey Blvd. Rancho Cucamonga, CA 91730 Ph: 800.483.9628 Email: brickform.com | Davis Colors 3700 East Olympic Blvd. Los Angeles, CA 90023 Ph: 800.356.4848 Fax: 323.269.1053 Email: daviscolors.com | L.M. Scofield Company 6533 Bandini Blvd. Los Angeles, CA 90040 Ph: 323 720.3000 Fax: 323.720.3000 Email: Scofield.com |
| --- | --- | --- | --- |

4.	Pattern Imprinting, Coloring Concrete, and HMA Painting Plans.

Provide pattern imprinting, concrete coloring, and HMA painting plans to the Engineer for review and approval.  Include the following, at a minimum, to achieve a final product that accurately represents, to scale, colored concrete, painted HMA and the pattern imprinted concrete and HMA (including the joints) elements:

a.	the sequence and schedule of operations,

b.	the proposed method of pattern imprinting,

c.	the method of coloring the concrete,

d.	the method of applying the MMA coating/paint to the HMA.

5.	Exposed aggregate, Colored Concrete and Painted HMA and Pattern Imprinted Concrete and HMA Sample(s).

Provide one sample, equal to the width of the item, 6 ft x 6 ft maximum, 4 ft x 4 ft minimum, of each item for review by the Engineer.  Demonstrate exposing the aggregate, the addition of colorant to the concrete, painting the HMA and pattern imprinting the concrete and HMA on each sample provided.

Receive written approval of the sample prior to beginning production work.

Retain samples of binder(s), sand(s), aggregate(s), and color additive, used in the sample for comparison with the item production materials.  Keep sample through completion of related work for use as a quality standard for finished work.  Keep the sample through Project completion when requested by the Engineer.

CONSTRUCTION REQUIREMENTS

608-3.01 CONCRETE SIDEWALKS. Excavate to the required depth and to a width necessary to install and brace the forms. Shape and compact the foundation to a firm, even surface conforming to the section shown on the Plans. Replace soft and yielding material with approved material. Compact bed course material according to Subsection 203-3.04.

Use full depth forms made of wood or metal. Use forms that are straight, free from warp, and strong enough to resist the pressure of the concrete without springing. Coat forms with an approved form-release agent. Brace and stake the forms so that they maintain their position until their removal.

Thoroughly moisten the foundation immediately before placing the concrete.

Finish the surface according to Section 550-3.05. Do not plaster the surface. Edge all outside slab edges and all joints to a 1/4 inch radius.

Make expansion joints to the dimensions and spacing shown on the Plans and fill with the type of preformed expansion joint fill specified.

Divide the sidewalk into specified sections using dummy joints formed by a jointing tool or other acceptable means. Make dummy joints 1/3 the depth of the concrete and approximately 1/8 inch wide.

Form construction joints around all appurtenances such as manholes, utility poles, buildings, or bridges, extending into and through the sidewalk. Install preformed expansion joint filler 1/2 inch thick in construction joints. Extend the expansion joint material the full depth of the walk.

Apply joint sealer evenly to completely seal all joints.

Cure the concrete according to Section 550-3.06. During the curing period, exclude all pedestrian and vehicular traffic. Exclude vehicular traffic for additional time as directed.

The Engineer will test the finished surface with a 10-foot straightedge. Variations of more than 1/4-inch from the edge of the straightedge across or along the sidewalk surface, except at grade changes, are unacceptable. Portions of the sidewalk surface and pedestrian ramps less than 10 feet in width, or length may be tested using a shorter straightedge.

Exposed Aggregate, Colored Concrete and Painted HMA and Pattern Imprinted Concrete and HMA

Match the Project work to the approved sample.  Significant differences in appearance (texture, color, pattern, or other) between adjacent panels/sections of work, from the approved sample including adjacent panels/sections similar to the approved sample yet significantly different to each other, as judged by the Engineer, will result in removal and replacement of the deficient panel(s)/section(s) of work.

Take all precautions to avoid damaging new and existing, concrete and asphalt.

Prevent surrounding materials from being discolored by the concrete and HMA and the HMA MMA coating (curbs, gutters, and other).  When directed by the Engineer, in writing, remove stains and coatings on other concrete and or HMA, resulting from your work.

Where HMA paving is against; exposed aggregate finish, colored, pattern imprinted; colored and pattern imprinted concrete, place the concrete prior to asphalt paving.  Do not place the HMA pavement until the concrete has cured sufficiently to prevent damage from the paving operation.

Acceptance of corrective work requires the Engineer's written approval.  Repair all new and existing damaged concrete and HMA, including the removal of surface contaminants, to the satisfaction of the Engineer.  The Engineer will not provide written approval until all damaged concrete and HMA is repaired.

1.	Slab Types.

| TABLE 608-1 Slab Type Requirementsa, b |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Typec | Description | Finishd, e, f | Added Colorg | Added Patterng | th Inches | Reinforcingi (bar spacing each way) |
| a. & b. | Typical | Broom |  |  | 4, 6 |  |
| I | Broom | Broom |  |  | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
|  |  |  |  |  | 8 | #6@12" O.C. |
| II | Exposed Aggregate | Aggregate |  |  | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
| III | Colored | Broom | Color Manufacturer |  | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
| IV | Pattern Imprinted | Coordinate |  | Pattern Manufacturer | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
| V | Colored & Pattern Imprinted | Coordinate | Color & Pattern Manufacturer |  | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
| a. Sealer and Hardener: provide for all slabs. b. Transition the slab at approaches as shown in the plans. c. Type a. & b.; Pay Items 608.0001.____, are the "Typical" concrete sidewalk. d. Broom: provide a medium broom finish. e. Aggregate: provide a uniform color slightly darker than the typical uncolored slab with a uniform reveal according to ACI 303.1. f. Coordinate: coordinate and provide finish as required by pattern imprint system manufacturer. g. Color and Pattern: provide color and or pattern similar to that noted and available from the listed manufacturer(s). Provide color and pattern from the same manufacturer or provide from different manufacturers with a certification from each permitting warranted use of their product with the product of the other manufacturer. Use a release agent as approved by the manufacturer(s). h. t: provide the slab thickness, denoted as "t" i. Reinforcing: Provide welded wire fabric in sheets not rolls. Lap joints 1 1/2 mesh minimum. |  |  |  |  |  |  |

2.	Joints.

Lay out joints as shown or noted in the Plans and Specifications, if not shown or noted provide:

a.	Control Joints.  Maximum spacing equals 12 ft.  (also referred to as, "dummy joints")

(1)	the joint configuration should create a square or rectangle with the long side no more than 1.5 times the short side,

(2)	space the control joint matching the width of the slab,

(3)	at corners and intersections, align the joints parallel to the edge(s) of the intersecting slab.

(4)	locate the joints equally spaced between the:  ends/edges of slab, slab corners, slab intersections or a combination of one and another.

b.	Expansion Joints.  Maximum spacing equals 36 ft.

Touch up pattern and finish edges with hand tools immediately after placing concrete and as directed by the manufacturer(s) and Engineer.

608-3.02 ASPHALT SIDEWALKS. Place bed course material in layers. Compact it according to Subsection 203-3.04.

Place asphalt material on the compacted bed course in one or more courses as indicated on the Plans. Compact it uniformly to required depth. Use a power roller of an acceptable type and weight. In areas inaccessible to the roller, use other approved methods.

608-3.03 CURB RAMPS. Construct curb ramps according to the details and the locations shown on the Plans. Follow the construction requirements of Subsection 608-3.01. Install detectable warnings.

Measure curb ramp slopes with a 24-inch electronic level. Calibrate and operate the level according to the manufacturer's instructions.

Provide the slab Type as identified here and elsewhere, Type ___. Refer to 608-3.01.1 Slab Type, Table 608-1 Slab Type Requirements for further information.

608-3.04 DETECTABLE WARNINGS. Construct detectable warnings according to the details and the locations shown on the Plans. Install detectable warning plates by embedding plate flanges into cast-in-place concrete construction so there are no vertical changes in grade exceeding 0.25 inch or horizontal gaps exceeding 0.5 inch. Align pattern on a square grid in the predominate direction of travel. Install the same type of detectable warning plate throughout the project.

Detectable warnings shall be installed according to the 2006 U.S. DOT ADA Standards for Transportation Facilities.

608-3.05 ASPHALT – PATTERN IMPRINTED AND PAINTED.  Construct pattern imprinted and painted HMA according to Subsection 608-3.02 Asphalt Sidewalks and as noted herein.

1.	Pattern.  Fabricate the imprint tool pattern to match standard brick dimensions in a running bond configuration with a slightly wider joint/indent spaced similar to the concrete expansion Joint.

2.	Painting.  Prepare the asphalt surface and apply the coating/paint according to the MMA manufacturer's instructions. Apply coating (MMA) completely covering the asphalt surface including pattern imprint.  Do not fill the pattern indentation, with MMA, flush with the top surface.  Leave a 1/8", smooth, concave painted/coated surface between bricks (joint).

608-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Sidewalk by area of finished surface, weight of material placed, and lump sum as included in the bid schedule. Ramps are included in the measurement unless included as a separate measured and paid item.

HMA used for matching existing surfaces, such as paved parking lots behind a new sidewalk/pathway, will be included in the measurement of the related asphalt Pay Item.

608-5.01 BASIS OF PAYMENT.

Subsidiary to the Pay Items: excavation, backfill, reinforcement, expansion joint material, samples, asphalt binder, corrective work, and other related miscellaneous items.

Embankment and bed course materials will be furnished, placed, and paid under Sections 203 and 301, respectively.

Curb Ramp when included in the bid schedule includes ramp runs, backing curbs, flares, landings to provide a single street-level access and detectable warnings, except detectable warnings are payed separately when included as an item in the bid schedule.

CR608-113020

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 608.0001.___ | Concrete Sidewalk, 4 inches thick | SY |
| 608.0001.___ | Concrete Sidewalk, 6 inches thick | SY |
| 608.0002.___ | Asphalt Sidewalk | Ton |
| 608.0006.___ | Curb Ramp | Each |
| 608.0007.___ | Curb Ramp, Retrofit | Each |
| 608.2002.___ | Asphalt Pathway | Ton |
| 608.2004.___ | Asphalt Medians | Ton |
| 608.2006.___ | Asphalt Pathways and Medians | Ton |
| 608.2007.___ | Asphalt, (Sidewalk, Plaza, etc., __ Inches Thick) | SY |
| 608.2008.___ | Asphalt Pattern Imprinted and Painted, (Median, etc., __ Inches Thick) | SY |
| 608.2010.___ | Concrete Sidewalk Wall, (Type __; Slab __ in; Wall __ in; Ht __ ft) | LF |
| 608.2011.___ | Concrete Sidewalk Retaining Wall, (Type __; Slab __ in; Wall __ in; Ht __ ft) | LF |
| 608.2012.___ | Concrete Sidewalk Barrier Wall, (Type __; Slab __ in; Wall __ in; Ht __ ft) | LF |
| 608.2013.___ | Concrete, Type I, __ inches thick, Broom Finish, (median slab, etc.) | SY |
| 608.2013.___ | Concrete, Type II, __ inches thick, Exposed Aggregate Finish, (median slab, etc.) | SY |
| 608.2013.___ | Concrete, Type III, __ inches thick, Colored, (median slab, etc.) | SY |
| 608.2013.___ | Concrete, Type IV, __ inches thick, Pattern Imprinted, (median slab, etc.) | SY |
| 608.2013.___ | Concrete, Type V, __ inches thick, Colored and Pattern Imprinted, (median slab, etc.) | SY |
| 608.2014.___ | Concrete Medians | SY |
| 608.2015.___ | Concrete Stairway | LS |
| 608.2017.___ | Detectable Warning Tile | Each |

CFHWY00308

SECTION 611
RIPRAP

Special Provision

611-2.01 MATERIALS.

Replace the first paragraph with the following:

Evenly graded stones that are hard, angular, and have no more than 50 percent wear at 500 revolutions as determined by AASHTO T 96.  Apparent specific gravity will be determined by ATM 308. Use stones with breadth and thickness at least 1/3 of its length. Do not use round boulders or cobbles on slopes steeper than 3:1.

CR611.1-020119

Special Provisions

Replace Section 615 with the following:

SECTION 615
STANDARD SIGNS

615-1.01 DESCRIPTION. Furnish and install standard signs and delineators. Remove and relocate or remove and dispose of existing signs and markers, as specified.

615-2.01 MATERIALS. Use materials that conform to the following Subsections:

Sheet Aluminum 		730-2.01

High Density Overlaid Plywood		730-2.02

Retroreflective Sheeting, ASTM D4956 		730-2.03

Sign Posts		730-2.04

Delineator Posts		730-2.05

Acrylic Prismatic Reflectors		730-2.06

Sign Support Fasteners	730-2.07

1.	Shop Drawings. Submit shop drawings, for all signs that must meet the ASDS letter width and spacing charts, for approval before fabrication. Submit 4 sets of collated shop drawings prepared according to Subsection 105-1.02. Show the following on each sign drawing:

a.	Dimensions of all horizontal and vertical characters and spaces

b.	Overall dimensions

c.	Sign material and sheeting material type

d.	Panel thickness

e.	Legend and letter series

f.	Whether the sign will be framed

2.	Sign Fabrication. Use ASTM D4956 Type IV retroreflective sheeting (for lettering, symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX or XI fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

(1)	For temporary installations, the reflective sheeting place on aluminum, plastic, or plywood sheet panels.

(2)	For flexible signs, (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports: Use white ASTM D4956 Type VIII or Type IX or XI retroreflective sheeting for background of sign and all strips.

c.	Non-Illuminated Overhead Signs with White Legends on Green Backgrounds: Use ASTM D4956 Type IX or XI retroreflective sheeting for legends and background. Create the legend in one of the following ways:

(1)	Cut border and legend from white ASTM D4956 Type IX or XI retroreflective sheeting and adhere them to a green ASTM D4956 Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white ASTM D4956 Type IX or XI retroreflective background.

d.	Fluorescent Yellow-Green School Area Signs: Use ASTM D4956 Type VIII, Type IX or XI retroreflective sheeting for background.

Use a manufacturer-recommended clear coat on all screened signs.

Use sign layouts (including characters, symbols, corner radii, and borders) that conform to the ASDS.

3.	Sign Posts and Bases. Use sign posts and bases of the types specified. The structural aspects of design and materials for sign supports must comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals. Do not splice sign posts.

Use Class A concrete meeting the requirements of Section 501 for overhead Sign support foundations.

Use Class B concrete for steel-reinforced roadside sign foundations meeting the requirements of Section 550. Concrete for other sign foundations may be Class W.

4.	Delineators. Use delineator assemblies that conform to the requirements shown on the Plans. Fabricate flexible delineators using ASTM 4956 Type III, IV, V, IX or XI retroreflective sheeting.

5.	Reflective Sheeting Warranty. Supply manufacturer’s warranty for reflective sheeting, including retention of fluorescent yellow-green (measured in accordance with ASTM E2301) for ten years according to the following criteria:

a.	Minimum Fluorescent Luminance Factor	YF: 20%

b.	Minimum Total Luminance Factor	YT: 35%

The warranty shall stipulate that: If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication of the sign, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness. If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

CONSTRUCTION REQUIREMENTS.

615-3.01 GENERAL.

1.	Place posts in excavated holes to the depth shown on the Alaska Standard Plans.

2.	Backfill the space around the posts and foundations placed in holes to finish ground with selected earth or sand, free of rocks or deleterious material. Place backfill in layers approximately 6 to 12 inches thick and thoroughly compact it.

3.	Dispose of surplus excavated material neatly along the adjacent roadway as directed.4.	Install flexible delineator posts according to the manufacturer's recommendations.

5.	Attach sign panels to posts, electroliers, traffic signal standards, bridge rails, piers, and abutments using the types and sizes of fastening hardware shown on the Plans.

6.	If using existing signs and mileposts that are removed and relocated, ensure they conform to the details shown on the Plans or as directed.

7.	Sign Salvage:

Notify the Engineer 5 working days prior to beginning sign salvage activities. The Engineer will physically identify those signs to salvage.

a.	Property of the State.  When 615-3.01 7a identifies a maintenance station to receive sign salvage, the signs (sign panels, posts, and hardware) are the property of the State.

Protect all items from damage during salvaging and delivery. For each sign so designated, disconnect sign post from panel and group the panels together. Group posts together with their hardware. Deliver sign panels, posts, and hardware to the State Maintenance Station noted in these Special Provisions. Do not deliver salvaged materials until inspected and approved by the Engineer. Replace any items damaged by you at no additional cost to the Department.

Deliver salvaged sign panels, posts, and hardware to the State Maintenance and Operations Station, located at:

Silvertip M & O Station located at Mile 60 of the Seward Highway

b.	Property of the Contractor. When 615-3.01 7a does not identify a State Maintenance and Operations Station; the signs salvaged (sign panels, posts, and hardware) are the property of the Contractor.

Remove project signs and/or parts designated for salvage, off the project site.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise). If abandoned in place, remove the tops of the foundations, reinforcing steel, anchor bolts, and conduits to a depth of not less than 12 inches below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation considered as one unit.

Dispose of sign salvage not wanted by the Contractor, not used in the project, and not accepted by the Local Maintenance and Operations Station as required by Federal, State, and Municipal environmental regulations.

8.	All materials and finished signs are subject to inspection and acceptance in place.

a.	Surfaces exposed to weathering must be free of defects in the coating that impair serviceability or detract from general appearance or color match.

b.	Finished signs must be clean and have no chatter marks, burrs, sharp edges, loose rivets, delaminated reflective sheeting, or aluminum marks. Do not make repairs to the face sheet.

9.	Install the various breakaway assemblies according to the manufacturer’s written instructions. Meet MASH crashworthiness requirement for breakaway hardware, unless approved otherwise by the Engineer.

10.	Secure the anchors in templates and install them according to the manufacturer’s written instructions.

11.	Finish the foundation according to these tolerances:

a.	Do not use more than two shims per coupling.

b.	Do not use more than three shims to plumb each post.

Remove and replace all foundations requiring more than three shims to plumb a post without extra compensation.

12.	Construct the top of any foundation located on a slope so that the finished slope passes through the top center of the foundation. Grade the area 24 inches up and down slope of the foundation edge so that no portion of the foundation projects above the surrounding slope and water will drain away from the foundation.

13.	Attach a label to the back of all standard signs in the lower right corner. Make the label at least 15 square inches and show the year the sign was purchased from the manufacturer. Show the last two digits of the year in clear and bold numbers. Make the label from ASTM D4956 Type I or brighter retroreflective sheeting. Use background and legend colors meeting Table 615-1.

TABLE 615-1

DECAL COLORS

| YEAR | BACKGROUND COLOR | LEGEND COLOR |
| --- | --- | --- |
| XXX1 | Yellow | Black |
| XXX2 | Red | White |
| XXX3 | Blue | White |
| XXX4 | Green | White |
| XXX5 | Brown | White |
| XXX6 | Orange | Black |
| XXX7 | Black | White |
| XXX8 | White | Black |
| XXX9 | Purple | White |
| XXX0 | Strong Yellow-Green | Black |
| Central values and tolerance limits for each color, as referenced in the MUTCD, are available from the Federal Highway Administration, (HHS-30), 400 7th St. SW, Washington, D.C. 20590 |  |  |

615-3.02 SIGN PLACEMENT AND INSTALLATION. The location and type of installation will be as shown on the Plans. Sign locations are approximate and subject to field adjustment by the Engineer.

Do not allow the top of the embedded steel tube to extend more than 2 inches above the surrounding ground and concrete foundation.

On all signs, install 2-inch diameter wind washers, colored to match the sign face, between the fastener head and the sign. Use rust-resistant washers fabricated from a material equal in strength to the sign blank.

Mount signs on mast arms level.

Bring existing signs that are to remain, into conformance with Standard Drawing S-05. Keep existing signs in service until they are no longer needed.

615-4.01 METHOD OF MEASUREMENT.

Standard Signs and Object Markers. By the total area of legend-bearing sign panel erected in place. No deductions in quantity for corner rounding will be made. Nominal dimensions for sign sizes indicated on the Plans will be used to calculate sign pay quantities. Octagons and round signs will be measured as rectangles. Only one side of each double-faced sign will be measured for payment.

Removal and Relocation. By each, complete in place.

Delineators. By each, complete in place.  A single delineator consists of one post equipped with three reflectors.

Salvage Sign. By each complete sign delivered in acceptable condition.

615-5.01 BASIS OF PAYMENT. Sign posts, bases, and mounting hardware are subsidiary.

When Items 615.0002.____, 615.0003.____, or 615.0006.____ do not appear on the bid schedule, this work is subsidiary.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 615.0001.____ | Standard Sign | SF |
| 615.0002.____ | Remove and Relocate Sign | Each |
| 615.0003.____ | Remove and Relocate Milepost | Each |
| 615.0004.____ | Delineator, Rigid | Each |
| 615.0005.____ | Delineator, Flexible | Each |
| 615.0006.____ | Salvage Sign | Each |
| 615.0007.____ | Salvage and Dispose Sign | Each |

CR615-010120R

Special Provision

SECTION 617
RAILROAD CROSSINGS

617-1.01 DESCRIPTION. Add the following:  This work shall consist of furnishing and placing railroad ballast in conformance with the lines, grades and thickness’ shown on the Plans.

617-2.01 MATERIALS. Add the following:

Prepared ballast shall be crushed shot rock or crushed pit-run rock, size No. 4A, composed of hard strong and durable particles, free from injurious amounts of deleterious substances and conforming to the following requirements:

TEST								TEST PROCEDURE				TEST STANDARD

Gradation Tests:

Sampling Aggregates					ASTM D75

ASTM C702

Sieves with Square Openings			ASTM E11

Sieve Analysis							ASTM C136					See table below

Materials Finer Than No. 200			ASTM C117					See table below

Material Quality Tests:

Bulk Specific Gravity	ASTM C127	2.60 min.

Absorption	ASTM C127	1.0 max.

Magnesium Sulfate Soundness	ASTM C88

(Five Cycles)	1.0% max.

Clay Lumps & Friable Particles	ASTM C142	0.5% max.

Flat and/or Elongated Particles	USACE CRD-C119	5.0% max.

Degradation (LA Abrasion)	ASTM C535	30 max.

Mill Abrasion	see description below

Abrasion Number	see description below

Fractured Particles	see description below	75% min.

TYPE 4A BALLAST GRADATIONS

| Sieve Size | Percent Passing |
| --- | --- |
| 2-1/2 in. | 100 |
| 2 in. | 90-100 |
| 1-1/2 in. | 60-95 |
| 1 in. | 10-35 |
| 3/4 in. | 0-10 |
| 3/8 in. | 0-3 |
| No. 200 | 0-0.3 |

Mill Abrasion Test Description:

A representative sample is obtained and sized using the current ASTM Methods of Test. From the coarse aggregate, split a representative portion into a sample consisting of 3.3 lb. passing the 1-1/2 inch sieve and retained on the 1 inch sieve plus 3.3 lb. passing the 1 inch sieve and retained on the 3/4 inch sieve. The sample shall be washed and oven dried in accordance with the Los Angeles Abrasion procedure. The sample will then be placed in a 1.5 gallon, 9 inch external diameter porcelain or steel ball mill pot, along with 6.6 lb. of distilled water. The mill shall be rotated at 33 rpm for a total of 10,000 revolutions (five hours). The sample shall then be wash-sieved through a No. 200 sieve and oven dried before weighing. Mill abrasion shall be calculated as a percentage loss in weight by the following formula:

Mill Abrasion = (Loss in Weight / Original Weight) x 100

Abrasion Number:

The Abrasion Number is a number calculated with the results of the Los Angeles Abrasion Test and the Mill Abrasion Test given in this specification. The Abrasion Number shall be calculated by the following formula:

Abrasion Number = LA Abrasion Number + (5 x Mill Abrasion Number)

Fractured Particles Test Description:

The Fractured Particles Test is as follows:

A representative sample is obtained and sized using current ASTM Standard Methods D75 and C702, respectively. All fractured and non-fractured aggregate particles obtained by sampling shall be included for evaluation. ASTM Standard Method D5821 shall be used to determine the percentage, by mass, of coarse aggregate fractured particles.

The following fracture criteria shall apply:

A fractured particle shall be a particle with three or more fractured faces. Each of the fractured faces on the fractured particle must have a freshly exposed rock surface with a maximum dimension of at least one third the maximum particle dimension and a minimum dimension of at least one quarter of the maximum particle dimension. The included angle formed by the intersection of the average planes of adjoining fractured faces must be less than 135 degrees for each of the faces to be considered as separate fractured faces.

For example, a particle just retained on the two inch screen (i.e., particle size =2 inch) must have at a minimum:

1	A freshly exposed maximum face of between two-thirds of an inch and 2 inches, and

2.	A second freshly exposed face with a minimum dimension of one-half inch, and

3. 	A third freshly exposed face ranging in dimension between the other two.

The angle formed between any two of these faces must not exceed 135 degrees.

Particles which do not meet the above criterion will be classified as non fractured faces.

Testing and Inspection:

Supplier shall engage the service of a qualified Professional Engineer registered in the State of Alaska to oversee performance of the above referenced tests on the processed ballast. All sampling and testing shall be done either by the Professional Engineer himself or by a qualified and experienced technician working under the direction of the Professional Engineer. Samples of processed ballast shall be taken directly off belt to minimize segregation and contamination. Material quality tests shall be done by testing laboratory which is selected by the Contractor and approved by the owner and the ARRC.

The frequency of tests shall be as follows:

1.	Pre-Manufacturing Tests: Prior to production of ballast, the Contractor shall submit whole and crushed samples of the proposed source rock along with test reports that verify that they conform to the Specifications.

2.	Start-up Manufacturing Test: When ballast manufacturing begins another full battery of tests shall be run to verify that the ballast manufactured conforms to the specifications.

3.	Periodic Full Testing: Whenever the nature of the source rock changes significantly, such that conformance to specifications is in doubt, above tests shall be redone as appropriate to verify conformance and the results submitted for approval.

4.	Periodic Gradation Testing: Perform the gradation tests and visual monitoring of degree of fracture during manufacturing on every 1,000 cubic tons of ballast that is produced, but at least daily. A complete fractured particle test shall be run on every 5,000 cubic tons of ballast manufactured.

Submit all test reports to the State for approval. The Professional Engineer shall verify that all test reports are accurate and shall indicate whether or not they conform to these specifications. Any tests that fail to conform shall be brought to the immediate attention of the State’s Project Manager and immediate steps shall be taken to bring manufacturing into conformance.

The Engineer may reject any material that does not conform to these specifications. In addition, in the event of the material’s continuing failure to conform to the specifications, the Engineer may order that manufacturing cease until the product conforms and defective material is disposed of.

The State may periodically inspect the ballast at the manufacturing site and the final stockpile area(s). The State, at its own expense, reserves the option to perform additional sampling and texting for acceptance.

Manufacturing, Handling, Delivery, and Stockpiling of Material:

The ballast shall be manufactured, handled, delivered, stockpiled, and placed in such a manner that it is kept clean and free from segregation. Processed ballast shall be washed and/or rescreened as necessary to remove fine particle contamination as defined by the specification prior to stockpiling. Stockpiling of ballast will only be allowed over firm stable base areas. In order to minimize segregation ballast shall be stockpiled in more or less horizontal layers with no dumping over the sides of the stockpile allowed. Travel of construction machinery and other vehicles over the top of the stockpiles shall be kept at a minimum. Contractor will be responsible for the control of dust when hauling to and from stockpile.

CONSTRUCTION REQUIREMENTS

617-3.01 GENERAL.

Delete c, and replace with the following:

c.	The Contractor shall provide equipment and labor to assist the ARRC crews in removing and replacing rail and ties to the limits determined by ARRC as needed to accomplish the culvert removal and installation work.

Add the following:

e.	Ballast dumped on subgrade prior to track or crossing construction shall be kept free from material tracked in by construction equipment. Ballast dumped on skeleton track and turnouts shall be distributed uniformly during the dumping operation to minimize the carrying or regulating required to provide the designed ballast section.

Contractor shall submit his plan for handling and placing ballast for approval. This plan shall include material source, type of equipment to be used (e.g. HyRail dump truck), location of stockpiles, and method of distribution and compaction.

Add the following new subsection:

617-3.02 BALLAST.

- Ballast shall be placed to the lines and grades indicated. The average thickness shall be within one-quarter inch of the thickness shown on the drawings. Ballast shall not be placed on soft, muddy, or frozen areas. Where the prepared subgrade (roadbed) is soft, muddy, rutted, exhibits severe depressions, or is otherwise damaged, the ballast shall not be placed until the damaged subgrade has been repaired and the Engineer has approved the area.

- Forming of ruts that would impair proper drainage shall be prevented when distributing ballast from trucks and off track equipment. Any ruts formed greater than one (1) inch shall be leveled and graded to drain.

- Ballast shall be unloaded as close as possible to the point of use so that unnecessary handling is prevented. Excess ballast shall be picked up and redistributed at the Contractor's expense. Ballast shall be handled in such a manner as to ensure it remains clean of deleterious materials and within specifications.

- Minimum Ballast Depth: The minimum depth of ballast below the bottom of the tie shall be 12 inches.

617-4.01 METHOD OF PAYMENT. Add the following:

Ballast placed as shown on the Plans will be measured by the ton in accordance with Section 109. Ballast will be measured pursuant to the typical cross section and the limits shown on the plans. No payment will be paid for ballast that is in excess of the typical section. Any excess ballast shall be recovered by the Contractor at no additional cost.

617-5.01 BASIS OF PAYMENT. Add the following:

The accepted quantity of ballast will be paid for at the contract unit price per ton for the pay item shown in the bid schedule, complete in place.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

617.2006.004A	Railroad Ballast, Type 4A	Ton

CFHWY00213

Special Provisions

Replace Section 618 with the following:

SECTION 618
SEEDING

618-1.01 DESCRIPTION. Establish a healthy living perennial stand of grass or other vegetative living groundcover by seeding. Maintain the living cover for the term of the Contract.

618-2.01 MATERIALS. Use materials that conform to the following:

Water	Subsection 712-2.01

Seed	Section 724 (Grass Seed)

Fertilizer	Section 725

Topsoil	Section 726

Soil Stabilization	Section 619

Soil Stabilization Material	Section 727

TABLE 618-1

GRASS SEED MIX, SOIL STABILIZER, AND FERTILIZER APPLICATION RATES

| Materials | Ingredients | Application Rate (per MSFc) |
| --- | --- | --- |
| Grass Seed Mix a, b | Nortan – Tufted Hairgrass Arctred – Red Fescue Wainwright - Slender Wheatgrass Annual Ryegrass | 0.60 lbs. 0.45 lbs. 0.37 lbs. 0.08 lbs. Total = 1.50 lbs. |
| Soil Stabilizer. |  |  |
| Slope ≤ 3:1 | Mulch | 46 lbs. |
| Slope >3:1 | Mulch with tackifier | 45-58 lbs. |
| Fertilizer | 20-20-10 | 12 lbs. |

a.	Do not remove the tags from seed bags.

b.	Submit an alternate seed mix when the specified seed is not commercially available. Provide a letter confirming the specified seed is not available. Include an agronomist certified seed mix design, including application rate, suited to the project site.

c.	MSF = 1000 ft2.

CONSTRUCTION REQUIREMENTS

618-3.01 SURFACE PREPARATION. Remove ruts, holes, humps and other irregularities from the surface. Clear stones four inches in diameter and larger, weeds, plant growth, sticks, stumps, and other debris that will interfere with the application of stabilization material, topsoil, the seeding operation, growth of vegetative groundcover, and subsequent maintenance of the cover.

Smooth the slopes for a uniform appearance and round the top and bottom of the slopes to facilitate tracking or raking. Do not disrupt drainage flow lines.

Evenly place stabilization material and or topsoil when specified.

Prepare the surface material by grooving the material in a uniform pattern that is perpendicular to the fall of the slope. Use one or more of the following grooving methods with associated equipment before the application of seed:

1.	Manual raking with landscaping rake;

2.	Mechanical track walking with track equipment; or

3.	Mechanical raking with a scarifying slope board. Form one-inch wide grooves spaced no more than six inches apart.

618-3.02 SEEDING SEASON. Seed disturbed areas after permanent cessation of ground disturbing activities in that area, within the period specified in the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) Construction General Permit (CGP) for Alaska, Section 4.5 Soil Stabilization, and Section 641 Erosion, Sediment, and Pollution Control.

Do not seed during windy conditions, when climatic conditions or ground conditions would hinder placement or proper growth.

Seed between May 15 and August 15.

618-3.03 APPLICATION. Seed, seeding, reseeding includes the application of seed, fertilizer, and stabilization material.

If the seed mix, fertilizer and stabilization material are not included in the Plans or Specifications, including their application rates, use the recommendations of the ADNR and the Revegetation Manual for Alaska.

Do not seed areas of bedrock and plant beds.

Use any of the following methods:

1.	Hydraulic Method

Apply seed and stabilization material in one application when using the hydraulic method.  Apply fertilizer with the hydraulic method.  Include the fertilizer with the seed and stabilization material or apply separately.

a.	Furnish and place a slurry made of seed, fertilizer, water, and other materials.

b.	Use hydraulic seeding equipment that will maintain a continuous agitation and apply a homogeneous mixture through a spray nozzle. The pump must produce enough pressure to maintain a continuous, nonfluctuating spray that will reach the extremities of the seeding area with the pump unit located on the roadbed. Provide enough hose to reach areas not practical to seed from the nozzle unit situated on the roadbed.

c.	If mulch material is required, it may be added to the water slurry in the hydraulic seeder after adding the proportionate amounts of seed and fertilizer. Add seed to the slurry mixture no more than 30 minutes before application.

d.	Mix the slurry and apply it evenly.

2.	Dry Methods

a.	Use mechanical spreaders, seed drills, landscape seeders, aircraft, cultipacker seeders, fertilizer spreaders, or other approved mechanical spreading equipment.

b.	Spread fertilizer separately at the specified rate.

618-3.04 MAINTENANCE.  Maintenance includes but is not limited to the following:

1.	Protecting seeded areas against traffic by approved warning signs or barricades and against erosion.

2.	Repairing surfaces gullied or otherwise damaged following seeding.  Fill erosion gullies 4 inches deep and greater filling the gully to surrounding grade including the portions less than 4 inches deep.  Apply and prepare the stabilization material and or topsoil for seeding.  Seed repaired area.  Refer to Subsections 618-3.01 & 3.03.

3.	Reseeding areas not showing evidence of satisfactory growth within 3 weeks of seeding and after repairs are complete.  Reseed bare patches of soil more than 10 square feet in area.  Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.

4.	Watering seeded areas for healthy growth of vegetative cover.  Adjust the amount of water when directed.

618-3.05 ACCEPTANCE. The vegetative groundcover will be inspected considering each station and each side of the road a separate area.  Acceptance of the cover requires a minimum of 70% cover density in the inspection area, gullies repaired and reseeded, and no bare patches of soil more than 10 square feet in area.

Repair/reseed areas that are not accepted.

618-3.06 PERIOD OF ESTABLISHMENT. For each area accepted, the establishment period extends one complete growing season following the date of Project Completion, Subsection 105-1.15.  Employ all possible means to preserve/maintain the new vegetative groundcover in a healthy and vigorous condition to ensure successful establishment.  Maintain the vegetative cover, according to Subsection 618-3.04, to not less than the requirements for acceptance, Subsection 618-3.05.

618-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Seeding by the Acre. By the area of ground surface acceptably seeded and maintained.

Seeding by the Pound.  By the weight of dry seed acceptably seeded and maintained.

Water for Seeding. If weighed, a conversion factor of 8.34 pounds per gallon will be used to convert weights to gallons.

MGAL equals 1000 gallons.

618-5.01 BASIS OF PAYMENT.

1.	Pay Items 618.0001.____ and .0002.____ Seeding. Payment is for healthy established vegetative groundcover through the establishment period.

a.	The initial surface preparation, seed, fertilizer, mulch when applied hydraulically, their application, and the water for hydraulic application are subsidiary.

b.	Maintenance fill, stabilization material, topsoil, surface preparation, seed, fertilizer, mulch when applied hydraulically, and the water required for hydraulic application are subsidiary.

2.	Pay Item 618.0003.____ Water for Seeding. Payment is for water applied for growth of vegetative groundcover through the establishment period. Water for hydraulic application of materials is subsidiary to Pay Items 618.0001.____ and .0002.____.

Except for maintenance, stabilization material is paid under Section 619 and topsoil under Section 620.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 618.0001.____ | Seeding | Acre |
| 618.0002.____ | Seeding | LB |
| 618.0003.____ | Water for Seeding | MGAL |

CR618-050118R

Typically, mulch will be subsidiary as noted herein. The use of Pay Item, 619.0001 Mulch, is very rare.  If mulch is included as a Pay Item, Section 618 will require editing to remove all references for applying mulch as part of the slurry, the initial and maintenance, and as subsidiary.  The application rate of mulch is included in Section 618 and not in Section 619 - this will have to be addressed in the project specials if mulch is paid as 619.0001 Mulch.

Include: Section 619/CR619 Soil Stabilization; Section 724/CR724.1 Seed; 726/CR726.1 Topsoil and 727/CR727 Soil Stabilization Materials when including CR618.

Section 618 is not the place to specify soil stabilization material or topsoil.  Include topsoil, and soil stabilization material, general or specific, in the Estimate of Quantities, the Plans and the Bid Schedule.  Example:  "Soil Stabilization Material" in the Plans would be paid by Section 641; "Compost" or "Topsoil" in the Plans would be paid by Section 619, 620 or might be subsidiary to 618, etc.

Special Provision

Replace Section 619 with the following:

- SECTION 619
SOIL STABILIZATION

619-1.01 DESCRIPTION.  Furnish, install, and maintain materials to stabilize the soil.  Control erosion, sediment, and pollution.

619-1.02 RELATED SECTIONS, REFERENCE ORGANIZATIONS, AND STANDARD DOCUMENTS.

1.	Alaska Department of Transportation and Public Facilities (ADOT&PF):

Standard Specifications for Highway Construction

Seeding	Section 618

Topsoil	Section 620

Planting Trees and Shrubs	Section 621

Silt Fence	Section 633

Erosion, Sediment, and Pollution Control	Section 641

Soil Stabilization Material	Section 727

2.	American Association of State Highway and Transportation Officials (AASHTO)

Standard Practice for:

	Compost for Erosion/Sediment Control (Filter Berms and Filter Socks)	R 51

	Compost for Erosion/Sediment Control (Compost Blankets)	R 52

3.	United States Composting Council (USCC)

	Testing Methods for the Examination of Compost and Composting (TMECC)

	Seal of Testing Assurance Program (STA) documents

4.	Erosion Control Technology Council (ECTC)

	Hydraulic Erosion Control Products (HECPs) Specification Chart

Table 1, Performance Chart for Standard HECPs

	Rolled Erosion Control Products (RECPs) Specification Chart

Table 1, Rolled Erosion Control - Temporary

Table 2, Rolled Erosion Control - Permanent

5.	National Transportation Product Evaluation Program (NTPEP)

	Testing and Evaluation of Products Materials and/or Devices

6.	Texas DOT/Texas Transportation Institute (TTI) Hydraulics and Erosion Control Laboratory

619-1.03 SUBMITTALS.  Submit stabilization and erosion, sediment and pollution control performance testing results with certifications for each material, Section 619-2.01 Materials.  Submit a sample of each material to the Engineer 7 days before the scheduled installation.

1)	Test compost, all applications, no more than 90 days before installation.

2)	At a minimum, certificate will include the name of the manufacturer, product name, style number or similar, chemical composition of the material, the fibers, netting, yarn and similar and the weed free status of the material.

3)	Organic materials shall be accompanied with all applicable health certificates and permits.

4)	Furnish a Material Safety Data Sheet (MSDS) that demonstrates the product is not harmful to plants, animals, and aquatic life.

619-2.01 MATERIALS.  Select stabilization materials, individually or a combination of, matched to the project applications/conditions (sheet flow, concentrated flow, slope, length of slope, access, etc.) providing performance and functional longevity meeting the most restrictive requirements of the Construction General Permit (CGP), the approved Storm Water Pollution Prevention Plan (SWPPP) and Section 641 Erosion, Sediment and Pollution Control.

1)	Mulch	Subsection 727-2.01

	Dry Erosion Control, Stabilization Products

	Hydraulic Erosion Control Products (HECPs)

2)	Matting	Subsection 727-2.02

	Rolled Erosion Control Products (RECPs)

3)	Sediment Retention Fiber Rolls (SRFRs)	Subsection 727-2.03

	Filter Socks

	Compost Socks

	Coir Logs

4)	Compost	Subsection 727-2.04

5)	Tackifier	Subsection 727-2.05

6)	Soil Binders (Polyacrylamide (PAM))	Subsection 727-2.06

7)	Geotextile-Encased Check Dams and Sediment Barriers	Subsection 727-2.07

8)	Sandbag	Subsection 727-2.08

9)	Manufactured Inlet Protection System	Subsection 727-2.09

10)	Clear Plastic Covering	Subsection 727-2.10

11)	Staples	Subsection 727-2.11

12)	Other stabilization materials submitted to and approved by the Engineer.

Include on the packaging the manufacturer's name, the content, the air dry-weight and the guaranteed chemical analysis of the contents.  Ship and deliver to the site in the original, unopened containers.

CONSTRUCTION REQUIREMENTS

619-3.01 GENERAL.  Stabilization may include individual or a combination of materials, including but not limited to temporary seeding, mulch, tackifier, staples, matting, stabilizing emulsions, soil binders, dustless sweeping, dust palliatives, and others.

1.	Material Storage and Protection.  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment including but not limited to:

	Precipitation

	Extended ultraviolet radiant including sunlight

	Chemicals that are strong acids or other

	Flames and welding sparks

	Excess temperatures

	Other environmental conditions that may damage the materials

2.	Fabrication.

a.	Sandbags.  Sand bags shall measure 15 inches by 30 inches.  Place approximately 1.0 cubic foot of select Material, Type B, in each sandbag sack.  Close the open end of the sandbag as recommended by the fabric manufacturer.

619-3.02 SURFACE PREPARATION.  Clear all areas to be stabilized of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the stabilization operation, growth of cover (where vegetative cover is part of the stabilization operation) or subsequent maintenance of the vegetative-covered area(s).

Smooth the surface of the area(s) to be stabilized; make the areas reasonably free of ruts, holes, and humps; trackwalk if required by the manufacturer; apply the stabilization material to each area.

If specified, apply topsoil to the area to be stabilized before application of the stabilizing material.  Section 618 and 620.

619-3.03 APPLICATION.  Apply stabilization material, including rate of application, according to the specifications.  If not specified, apply according to the manufacturer's requirements.  Where manufacturer requirements conflict with the specification, except where the Engineer directs otherwise, apply the material according to the requirements of the manufacturer.

If seeding is specified, except where seed is included in the stabilization material, complete the application of stabilization materials within 24 hours after seed is placed.

Do not use vehicles or equipment which cause rutting or displacement of the subgrade or topsoil.

1.	Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Prepare surface and place seed as noted under Subsection 619-3.02 Surface Preparation and Section 618 Seeding.  Confirm application of temporary seeding with the Engineer.

2.	Tacking Agents - Tackifiers.  Apply tacking agents according to the manufacturer's installation instructions matched to the application providing functional longevity, erosion control effectiveness, and vegetative establishment.

3.	Soil Binders.  Apply soil binders according to the manufacturer's installation instructions.

a.	Using Polyacrylamide (PAM) and PAM with Short-Term Mulch:

Apply PAM on bare soils.

Apply PAM and PAM with short-term mulch only where sediment control is in place and complete.

Do not apply PAM and PAM with short-term mulch on saturated ground during rainfall.

b.	Using Moderate-Term Mulch:

Apply moderate-term mulch according to manufacturer's installation instructions.  If the curing period to achieve maximum performance is greater than the time period before precipitation is predicted, or the soil is saturated, do not apply the moderate-term mulch except as approved by the Engineer.

c.	Using Long-Term Mulch:

Apply long-term mulch according to the manufactures installation instructions.

4.	Erosion Control Blankets (ECBs).  Select blankets, as specified by the manufacturer, to match the slope; and installed according to the manufacturer's instructions rolled out on well prepared soils to assure intimate contact and anchored with staples, stakes and or anchor trenches.  Temporary erosion control blankets with 60 percent or greater open area may be installed prior to seeding.  Place blankets with less than 60 percent open area immediately after the seeding operation.

Staple matting/ECBs as recommended by the manufacturer for the application.

5.	Compost Blankets.  Construct compost blankets according to latest AASHTO R 52 and as specified.  Use coarse compost and place over bare soil a blanket of 2 inch minimum thickness, except as otherwise specified.  Apply material either by hand spreading and or pneumatically.  Compost will have no free water visible or produce dust when handled.  Place compost before seeding or mix seed with compost.

6.	Check Dams.  Place check dams as soon as possible and practicable or when and where if directed by the Engineer.  Place the check dams perpendicular to channels and construct of a height sufficient to maximize detention while keeping the water in the channel.  Place and install check dams according to the Plans and anchor to maintain in effective position.

a.	Sandbag.  Place the initial row in tight contact with the ditchline for the length of the dam.  Place each following row centered across the joint between the bags of the lift/row below.

7.	Stabilized Construction Entrance.

Temporary stabilized construction entrance shall be constructed according to the Plans, prior to beginning any clearing, grubbing, earthwork, or excavation.

When the stabilized entrance no longer prevents track out of sediment or debris, the Contractor shall either rehabilitate the existing entrance to original condition, or construct a new entrance.

When the Plans require a tire wash in conjunction with the stabilized entrance, the Contractor shall include details for the tire wash and the method for containing and treating the sediment-laden runoff as part of the SWPPP.  All vehicles leaving the site shall stop and wash sediment from their tires.

8.	Sediment Control Barriers.  Sediment control barriers shall be installed according to the Plans or manufacturer's recommendations in the areas of clearing, grubbing, earthwork, or drainage prior to starting those activities.

a.	Sandbag.  Place the initial row in tight contact with the surface perpendicular to the slope.  Place each following row centered across the joint between the bags of the lift/row below.

b.	Sediment Retention Fiber Rolls.

c.	Silt Fence.

d.	Compost Berm.  Construct compost berms according to latest AASHTO R 51.  Use coarse compost.

9.	Turf Reinforcement Mats.  According to manufacturer's installation instructions.

619-3.04 MAINTENANCE.  Maintain stabilized areas in a satisfactory condition for the term of the Contract.  Inspect as required by the CGP, approved SWPPP, and Section 641 Erosion, Sediment and Pollution Control and correct any deficiencies immediately.  Remove and dispose of temporary measures, including trapped sediment and contaminants, off project at approved locations.  Materials manufactured as degradable may be left in place when approved by the Engineer.

Maintenance includes but is not limited to:

a.	Protecting stabilized areas against traffic by approved warning signs or barricades.

b.	Repairing surfaces gullied or otherwise damaged following application of stabilization material(s).

Where seeding is included as a part of the soil stabilization:

c.	Reseeding, as required by Section 618 Seeding.  Reapply the stabilization materials correcting the problems of the initial application.

d.	Watering, where vegetative growth is part of the soil stabilization, according to Section 618 Seeding.

The Engineer will perform inspection of the stabilization as required in the CGP, Section 641, and the SWPPP.  Make repairs as required by same and as directed.

619-4.01 METHOD OF MEASUREMENT.  Section 109, measured on the slope of the ground surface.

619-5.01 BASIS OF PAYMENT.  Water, maintenance, repair, removal, and disposal of temporary stabilization materials are subsidiary.

Seeding is paid under Section 618 Pay Items, topsoil under Section 620 Pay Items, silt fence under Section 633 Pay Items and temporary erosion, sediment, and pollution control under 641 Pay Items.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 619.0001.____ | Mulching | SY |
| 619.0002.____ | Matting | SY |
| 619.2001.____ | Compost | SY |
| 619.2002.____ | Turf Reinforcement Mat | SY |
| 619.2003.____ | Sediment Retention Fiber Rolls | LF |
| 619.2004.____ | Check Dam and Sediment Barrier (-Geotextile) | LF |
| 619.2005.____ | Check Dam | LF |
| 619.2006.____ | Sediment Barrier | LF |
| 619.2007.____ | Compost Berm | LF |
| 619.2008.____ | Sandbags | Each |
| 619.2009.____ | Manufactured Inlet Protection System | Each |
| 619.2010.____ | Sandbag Inlet Protection System | Each |
| 619.2016.____ | Mulch | SY |

CR619-050118R

SECTION 622
REST AREA FACILITIES

Special Provisions

622-1.01 DESCRIPTION.  Add the following:

Furnish and install rock benches included in the Plans and Specifications.

Furnish all materials and labor required in the placement and erection of the Kiosks included in the Plans and Specifications.  Work to include supplying services, materials, excavation, concrete work, placing poles, and erecting structure.

Add the following subsection:

622-2.13 ROCK BENCH.  Provide bench constructed from a single boulder to the dimensions shown in plans.  Top surface of the rock bench shall have humps or depressions no greater than 2 inches over the length and width of the bench.

Add the following subsection:

622-2.14 KIOSK.  The Kiosk with display board structure consists of the following components:

Concrete	4,000 psi ready-mix concrete formed into a 30” square by 36” minimum depth at each column base, per local codes.

Reinforcing Steel		Shall meet ASTM 0615 manufacturing standards

Trusses					6x8 full sawn Alaska Yellow Cedar, #1 or better

Purlins					2x6 Alaska Yellow Cedar or equivalent

Fascia	2x6 clear Alaska Yellow Cedar, metal trim with drip edge extended to cover entire fascia.

Columns			6x10 full sawn Alaska Yellow Cedar #1 or better with column base.

Note: contractor assembled with hardware provided.

Roofing			Fabral Delta-Rib, 29-ga. Steel roofing, with 24” coverage width.

Standard color is Dark Brown, 859.

Sign	4’8”x6’ signs consisting of 2x8 Alaska Yellow Cedar boards, trim to be 1x2 Alaska Yellow Cedar.

All exposed metal shall be powder coated, black.

Add the following subsection:

`

622-3.08 ROCK BENCH INSTALLATION.  Bury approximately 1/3 of the bench.  Depth of excavation shall accommodate boulder size.   Install boulder bench such that the op surface of the bench shall not have has an average slope of no greater than 0.5 inches over 24 inches. .

609-4.01 METHOD OF MEASUREMENT.  Add the following:

Bench.  By each, complete installation.

Kiosk.   Concrete footings, timber posts, timber sign paneling and trim, roof trusses, roof framing, metal roof, steel places, and all fasteners and hardware.

Bedding materials will be paid for under Section 203.

609-5.01 BASIS OF PAYMENT.  Add the following:

Payment will be made under:

| Item Number | Item Description | Unit |
| --- | --- | --- |
| 622.2019.0000 | Bench, Rock | Each |
| 622.2036.0000 | Kiosk, USFS | Each |

CFHWY00308

SECTION 633
SILT FENCE

Standard Modification

633-2.01 MATERIALS.

Replace "Silt Fence	Subsection 729-2.04” with the following:

Silt Fence	Subsection 729-2.02

633-3.01 CONSTRUCTION REQUIREMENTS.

Replace the first sentence with the following:

Install silt fence according to the SWPPP, Appendix B.

CR633.HSM20.13-113020

Special Provisions

Replace Section 634 with the following:

SECTION 634
GEOGRID SOIL REINFORCEMENT

634-1.01 DESCRIPTION. Furnish and install geogrid material at locations shown on the Plans.

634-2.01 MATERIALS. Use materials that conform to the following:

Geogrid	Subsection 729-2.04

CONSTRUCTION REQUIREMENTS

634-3.01 WEATHER LIMITATIONS. Do not expose geogrid to sunlight for longer than 14 days after removal of protective covering.

634-3.02 SURFACE PREPARATION.

1.	Very Soft Ground (CBR < 1).  Care should be taken to avoid disturbing any surface crust overlying softer soil.  In these cases the geogrid should be placed directly on the unprepared subgrade.

If directed by the Engineer, minimize disturbance of the subgrade by leaving root mats in place, cutting stumps and other projecting vegetation as close and even to the ground surface as practical.

Swampland, peat, muskeg or marshes may be difficult to smooth grade and/or compact.  Create a surface that is as uniformly smooth as possible.  Grade or crown the surface for positive drainage away from the construction zone.

2.	Firm Ground (CBR 1 – 3). Prepare surface by removal of stumps, brush, boulders, and sharp objects.  Fill holes and large ruts, as directed by the Engineer, with material shown on the Plans or as approved by the Engineer.

3.	Firm Ground (CBR > 3). Compact and finish subgrade or subbase prior to placement of the geogrid.

634-3.03 GEOGRID PLACEMENT.  Unroll geogrid directly onto the prepared ground surface in the direction of advancing construction, parallel to the centerline of the roadway or according to the Plans.  Do not drag the geogrid across the subgrade.  Install the geogrid in the longest continuous practical length, free from folds, creases or wrinkles.  Hold the geogrid in place with pins, staples, sandbags or piles of granular material.

1.	Very Soft Ground. Overlap geogrid panels a minimum of 36-inches at all joints with the upper geogrid in the direction that fill will be placed. Tie panels together securely with cable ties or hog rings at 5-feet intervals or as recommended by the manufacturer and approved by the Engineer.

To limit lateral spreading and separation of overlaps, if approved by the Engineer, the Contractor may unroll the geogrid transversely/perpendicular to the roadway embankment alignment. Overlap the adjacent rolls and tie together with cable ties or hog rings at 5-feet intervals.

2.	Soft Ground. Overlap geogrid panels a minimum of 24-inches at all joints with the upper geogrid in the direction that fill will be placed.  Tie panels together securely with cable ties or hog rings at 20-feet intervals or as recommended by the manufacturer and approved by the Engineer.

- Firm Ground. Overlap geogrid panels a minimum of 12-inches at all joints in the direction that fill will be placed.  Tie panels together securely with cable ties or hog rings at 20-feet intervals.  Hand-tension geogrid and stake to the ground at the edges, overlaps, and in the center of each roll, at 30-feet intervals or as specified on the Plans.

634-3.04 PLACINIG AND SPREADING COVER MATERIAL. Do not operate equipment directly on the unprotected geogrid. Spread fill material in the direction of the fabric overlap.  Compact using a smooth drum roller.  Do not allow construction equipment to make sudden stops, starts, or turns on the cover material.

1.	Very Soft Ground. End-dump material onto previously placed material and spread over the geogrid with a low ground pressure (LGP equates to tire pressure of 4 psf) dozer to the depth permitted.  Maintain a minimum depth of 12-inches of cover material at all times between the geogrid and the wheels or tracks of the construction equipment, unless otherwise shown on the Plans or directed by the Engineer.  Do not dump material directly on the geogrid.  To prevent a mud wave, end-dump fill along the edges of the geogrid to form toe berms or access roads that extend one to two panel widths ahead of the remainder of the embankment fill placement.  After constructing the two berms, spread fill in the area between the toe berms by placing material parallel to the alignment and symmetrical from the toe berms inward toward the center to maintain a U-shaped leading edge (i.e., concave outward) to contain the mud wave.  Limit height of dumped piles above the geogrid to avoid local bearing failure.  Traffic on the first lift should be parallel to the embankment alignment.  Do not allow construction equipment to turn on the first lift.  Compact the first lift by tracking in place with dozers or end-loaders.  Compact with specified compaction equipment once the embankment is at least 2-feet above the geogrid.

2.	Soft Ground.  End dump material onto previously placed material and spread over the geogrid with a LGP dozer to the depth permitted. Maintain a minimum depth of 6-inches of cover material at all times between the geogrid and the wheels or tracks of the construction equipment unless otherwise shown on the Plans or directed by the Engineer.  Place the end-dumped material along the roadway centerline and spread it outward to the roadway edges to prevent the development of wrinkles or movement of the geogrid during construction.  Fill in any ruts that form during construction with material shown on the Plans.  Do not cut down the fill adjacent to the ruts.

3.	Firm Ground. Maintain a minimum depth of 6 inches of cover material at all times between the geogrid and the wheels or tracks of the construction equipment.

634-3.05 GEOGRID REPAIR. If the geogrid is torn, punctured, or the overlaps disturbed – as evidenced by visible geogrid damage – remove the backfill around the damaged area and repair or replace the damaged area.  Make repairs to the damaged area with a patch of the same class of geogrid originally placed.  Overlay torn area with geogrid with a minimum 3-feet overlap around the edges of the torn area and secure as recommended by the geogrid manufacturer, unless otherwise directed by the Engineer.

634-4.01 METHOD OF MEASUREMENT.  Measure geogrid by the square yard of ground surface covered.  No allowance will be made for overlap, whether at joints or patches.

634-5.01 BASIS OF PAYMENT.  Payment will be made at the Contract unit price. Repair and replacement costs for damaged geogrid are subsidiary to the Section 634 Pay Items.

Material used to fill ruts and holes paid at the unit price for the class of material used.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 634.0001.____ | Geogrid, Stabilization, Class ___ | SY |
| 634.0002.____ | Geogrid, Reinforcement, Class ___ | SY |

CR634-090315R

Special Provisions

Replace Section 639 with the following:

SECTION 639
DRIVEWAYS

639-1.01 DESCRIPTION. Construct driveways and approaches.

639-2.01 MATERIALS.  Reserved.

639-3.01 CONSTRUCTION.  Reserved.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed.

639-5.01 BASIS OF PAYMENT.  The Contract unit price for driveways and approaches is for furnishing equipment and labor.

Pavement removal and excavation required constructing driveways and approaches is subsidiary to the driveway and approach pay items.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 639.0001.____ | Driveway | Each |
| 639.0002.____ | Driveway, Residential | Each |
| 639.0003.____ | Driveway, Commercial | Each |
| 639.2000.____ | Approach | Each |

CR639-092016R

Special Provision

Replace Section 641 with the following:

- SECTION 641
EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this section and applicable local, state, and federal requirements, including the APDES Construction General Permit. The state APDES program is administered by DEC.  Section 301(a) of the Clean Water Act (CWA) and 18 AAC 83.015 provide that the discharge of pollutants to water of the U.S. is unlawful except as allowed by the CGP.

641-1.02 DEFINITIONS. These definitions apply only to Section 641.

ACTIVE TREATMENT SYSTEM (ATS) OPERATOR. The Contractor’s qualified representative who is responsible for maintaining and operating an active treatment system (as defined in the CGP) for storm water runoff.

ALASKA CERTIFIED EROSION AND SEDIMENT CONTROL LEAD (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years. (See Qualified Person)

ALASKA DEPARTMENT OF ENVIRONMENTAL CONSERVATION (DEC).  The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

ALASKA POLLUTANT DISCHARGE ELIMINATION SYSTEM (APDES). A system administered by DEC that issues and tracks permits for storm water discharges.

BEST MANAGEMENT PRACTICES (BMPS).  Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or minimize the discharge of pollutants to waters of the United States. BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leaks, sludge or waste disposal, or drainage from material storage.

CLEAN WATER ACT (CWA).  Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

CONSTRUCTION ACTIVITY. Physical activity by the Contractor, Subcontractor or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. Construction Activity includes soil disturbing activities (e.g. clearing, grubbing, grading, excavating); and establishment of construction materials or equipment storage or maintenance areas (e.g. material piles, borrow area, concrete truck chute wash-down, fueling); and industrial activities that may discharge storm water and are directly related to the construction process (e.g. concrete or asphalt batch plants).

CONSTRUCTION GENERAL PERMIT (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by Alaska DEC. It authorizes storm water discharges provided permit conditions and water quality standards are met.

CORPS OF ENGINEERS PERMIT (COE PERMIT). A U.S. Army Corps of Engineers Permit for construction in waters of the US. Such permit may be issued under Section 10 of the Rivers and Harbors Act of 1899, or Section 404 of the Clean Water Act.

ELECTRONIC NOTICE OF INTENT (ENOI). The electronic Notice of Intent submitted to DEC, to obtain coverage under the CGP.

ELECTRONIC NOTICE OF TERMINATION (ENOT). The electronic Notice of Termination submitted to DEC, to end coverage under the CGP.

ENVIRONMENTAL PROTECTION AGENCY (EPA). A federal agency charged to protect human health and the environment.

ERODIBLE STOCKPILE. Any material storage area or stockpile consisting of mineral aggregate, organic material, or a combination thereof, with greater than 5 percent passing the #200 sieve, and any material storage where wind or water transports sediments or other pollutants from the stockpile.  Erodible Stockpile also includes any material storage area or stockpile where the Engineer determines there is potential for wind or water transport of sediments or other pollutants away from the stockpile.

EROSION AND SEDIMENT CONTROL PLAN (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

FINAL STABILIZATION. Is defined in this section as it is defined in the CGP, Appendix C.

HAZARDOUS MATERIAL CONTROL PLAN (HMCP).  The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

INSPECTION.  An inspection required by the CGP or the SWPPP, usually performed together by the Contractor’s SWPPP Manager and Department’s Storm Water Inspector.

MUNICIPAL SEPARATE STORM SEWER SYSTEM (MS4) PERMIT.  A DEC storm water discharge permit issued to certain local governments and other public bodies, for operation of storm water conveyances and drainage systems. See CGP for further definition.

MULTI-SECTOR GENERAL PERMIT (MSGP). The Alaska Pollutant Discharge Elimination System General Permit for storm water discharges associated with industrial activity.

LOW-ERODIBLE STOCKPILE.  Any material stockpile identified in the CGP definition for Final Stabilization Section 1.b, and includes: riprap, gabion backfill, porous backfill, railroad ballast, and sub-ballast, ditch lining, or fill material with low erodibility. The stockpile shall not have a gradation of more than 5 percent passing the #200 sieve unless approved by an Engineer. There shall be no possibility of sediment transport due to water or wind erosion.

OPERATOR(S). The party or co-parties associated with a regulated activity that has responsibility to obtain permit coverage under the CGP.  ”Operator” for the purpose of the CGP and in the context of storm water associated with construction activity, means any party associated with a construction project that meets either of the following two criteria:

1.	The party has operational control over construction plans and specifications, including the ability to make modifications to those plans and specifications; or

2.	The party has day to day operational control of those activities at a project which are necessary to ensure compliance with a SWPPP for the site or other permit conditions (e.g. they are authorized to direct workers at a site to carry out activities required by the SWPPP or comply with other permit conditions).

POLLUTANT. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sediment, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

PROJECT ZONE. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Contract.

Material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

QUALIFIED PERSON. A person knowledgeable in the principles and practice of erosion and sediment controls. A qualified Person must be certified under the Alaska Certified Erosion and Sediment Control Lead (AK-CESCL) training program. One of the following training and certification programs may substitute for AK-CESCL certification: CPESC, CESSWI, CPSWQ, OR CISEC (CGP, Appendix C).

RECORDS. Any record, report, information, document, or photograph required to be created or maintained pursuant to the requirements of the CGP, the CGP storm water requirements of the Clean Water Act; and applicable local, state, and federal laws and regulations regarding document preservation.

SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC PLAN). The Contractor’s detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

SPILL RESPONSE FIELD REPRESENTATIVE. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

STORM EVENT. A rainfall event that produces more than 0.5-inch of precipitation in 24 hours and that is separated from the previous storm event by at least 3 days of less than 0.1 inch of rain per day.

STORM WATER POLLUTION PREVENTION PLAN (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project Zone, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but is not limited to, amendments, records of activities, inspection schedules, and reports, qualifications of key personnel, and all other documentation, required by the CGP and this specification, and other applicable local, state, and federal laws and regulations.

STORM WATER POLLUTION PREVENTION PLAN TWO (SWPPP2). The Contractor’s detailed project specific plan to comply with CGP or MSGP requirements, for Contractor construction-related activities outside the Project Zone.

SUBCONTRACTOR SPILL RESPONSE COORDINATOR. The subcontractor’s representative with authority and responsibility for coordinating the subcontractor’s activities in compliance with the HMCP and SPCC Plan.

SUBCONTRACTOR SWPPP COORDINATOR. The subcontractor’s representative with authority to direct the subcontractor’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the subcontractor’s compliance with the SWPPP.

SUPERINTENDENT. The Contractor’s duly authorized representative in responsible charge of the work.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

SWPPP AMENDMENT. A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP MANAGER. The Contractor’s qualified representative who conducts Inspections, updates SWPPP records, and has authority to suspend work and to implement corrective actions required for CGP compliance.

SWPPP PREPARER. The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

TEMPORARY STABILIZATION. Protecting soils from erosion and sediment loss by rainfall, snow melt, runoff, or wind with a temporary vegetative and/or non-vegetative protection cover. Temporary stabilization may include a combination of seeding, geotextiles, mulches, surface tackifiers, rolled erosion control products, low-erodible gravel or paving, or the mentioned BMP's combined together with trackwalking.

UTILITY SPILL RESPONSE COORDINATOR. The Utility’s representative with authority and responsibility for coordinating the Utility’s activities in compliance with the HMCP and SPCC Plan.

UTILITY SWPPP COORDINATOR. The Utility’s representative with authority to direct the Utility’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the Utility’s compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS. For plans listed in Subsection 108-1.03.5 (SWPPP, HMCP, and SPCC), use the Contractor submission and Department review deadlines identified in Subsection 641-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1.	Storm Water Pollution Prevention Plan. Submit an electronic copy and three hard copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize and bind the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14-day review period will restart when the contractor submits an electronic copy and three hard copies of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved by the Department, the Contractor must sign and certify the approved SWPPP using Form 25D-111. See Subsection 641-1.03.4 for further SWPPP submittal requirements.

2.	Hazardous Material Control Plan.  The HMCP Template can be found at the following webpage: http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml. Submit an electronic copy and three hard copies of the HMCP, as an appendix to the SWPPP, to the Engineer for approval. The HMCP submittal and review timeline, and signature requirements are the same as the SWPPP.

3.	Spill Prevention, Control, and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and three signed hard copies of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

4.	CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. Do not use the SWPPP for Construction Activities outside the Project Zone where the Department is not an operator.  Use a SWPPP2 for Construction Activities outside the Project Zone.

After Department approval of the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to DEC for coverage under the Construction General Permit (CGP). Submit a copy of the signed eNOI and DEC’s written acknowledgement (by letter or other document), to the Engineer as soon as practicable and no later than 3 days after filing eNOI or receiving a written response.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to DEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and DEC’s written acknowledgment (by letter or other document), for inclusion in the SWPPP.

Before Construction Activities occur, transmit to the Engineer an electronic copy of the approved and certified SWPPP, with signed Delegations of Signature Authorities on Forms 25D-107 and 25D-108, SWPPP Certifications on Forms 25D-111 and 25D-109, both permittee’s signed eNOIs and DEC’s written acknowledgement.

5.	Ending CGP Coverage. Submit an eNOT to DEC within 30 days after the Engineer has determined the conditions listed in Subsection 641-3.01.6 have been met. Submit a copy of the signed eNOT and DEC’s acknowledgement letter to the Department within 3 days of filing the eNOT or receiving a written response.

6.	DEC SWPPP Review.  When CGP Part 2.1.3, requires DEC SWPPP review:

a.	Transmit a copy of the Department-approved SWPPP to DEC using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within 7 days of receiving the confirmation; and

c.	Retain a copy of delivery receipt confirmation in the SWPPP.

7.	Local Government SWPPP Review.  When local government or the CGP Part 2.1.4, requires local government review:

a.	Transmit a copy of the Department-approved SWPPP and other information as required to local government, with the required fee.  Use delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within 7 days of receiving the confirmation;

c.	Transmit a copy of any comments by the local government to the Engineer within 7 days of receipt;

d.	Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within 7 days of receipt of the comments;

e.	Include a copy of local government SWPPP review letter in the SWPPP; and

f.	File a notification with local government that the project is ending.

8.	Modifying Contractor’s eNOI.  When required by the CGP Part 2.7, modify your eNOI to update or correct information within 30 calendar days of the change. Reasons for modification include a change in start or end dates, change in Owner/Operator address and contact information, change in site information, any changes in number of acres to be disturbed, change in decision to use or not use treatment chemicals, or change 	in location of SWPPP records.

The Contractor must submit an eNOT and then submit a new eNOI instead of an eNOI modification when: the operator has changed.

641-1.04 PERSONNEL QUALIFICATIONS. Provide documentation in the SWPPP that the individuals serving in these positions meet the personnel qualifications.

1.	The SWPPP Preparer.

a.	Total disturbed acreage, 20 acres or less, must meet at least one of the following qualifications:

(1).	Current certification as a Certified Professional in Erosion and Sediment Control (CPESC);

(2).	Current certification as AK-CESCL, and at least two years' experience in erosion and sediment control, as a SWPPP Manager or SWPPP writer, or equivalent. Provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement; or

(3).	Professional Engineer registered in the State of Alaska with current certification as AK-CESCL.

b.	Total disturbed acreage greater than 20 acres, must meet Subsection 641-1.04.1.a. above, and complete a SWPPP Preparation course.

2.	The Superintendent must meet the following qualifications:

a.	Current certification as AK-CESCL; and

b.	Duly authorized representative, as defined in the CGP, Appendix A, Part 1.12.3.

3.	The SWPPP Manager must have current certification as AK-CESCL. The SWPPP Manager must meet the experience, and authority requirements identified in the CGP for the Storm Water Lead and Storm Water Inspector positions.

4.	The Active treatment System (ATS) operator must have current certification as AK-CESCL, and be knowledgeable in the principles and practices of treatment systems in general, and the operation of the project-specific ATS.  The ATS operator must have at least three months field experience with ATS, or completion of an ATS manufacturer’s training course, or completion of system operator certification course.

5.	The Department accepts people having any of the following certificates as equivalent to AK-CESCL, if the certificates are current according to the sponsoring organization’s policies:

a.	CPESC, Certified Professional in Erosion and Sediment Control; or

b.	CISEC, Certified Inspector in Sediment and Erosion Control.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT. The eNOI and eNOT must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12. Signature and certification authority for the eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports.  Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Superintendent position is responsible for signing and certifying the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI and eNOT.

The Engineer will provide the Department’s delegation on Form 25D-107, which the Contractor must include in the SWPPP.

3.	Subcontractor Certification. Subcontractors must certify on Form 25D-105, that they have read and will abide by the CGP and the conditions of the project SWPPP.

4.	Signatures and Initials.  Handwrite signatures or initials on CGP documents and SWPPP forms, wherever a signature or initial is required.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

1.	The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

2.	The Contractor is responsible for permitting and permit compliance outside the Project Zone. The Contractor has sole responsibility for compliance with DEC, COE, and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.4) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage.

3.	Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

4.	The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas outside the Project Zone;

b.	For Construction Activity and Support Activities outside the Project Zone; and

c.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY.

Relocation Coverage. A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06.  The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work.  Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

1.	SWPPP Preparer and Pre-Construction Site Visit.

Use a SWPPP Preparer to develop the SWPPP and associated documents, according to the requirements of the CGP and COE permit. The SWPPP Preparer must put their name, qualifications (including the expiration date of any certifications), title and company name in the SWPPP.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least 7 days advance notice of the site visit, so that the Department may participate.

During the pre-construction inspection, the SWPPP Preparer must identify, or if a draft of the SWPPP has already been prepared verify that the SWPPP fully addresses and describes:

a.	Opportunities to phase construction activities;

b.	Appropriate BMPs and their sequencing; and

c.	Sediment controls that must be installed prior to beginning Construction Activities.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, including the names of attendees and the date.

2.	Developing the SWPPP.

Use the Department’s project ESCP, Environmental commitments, and other Contract documents as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.

Develop the SWPPP with sections and appendices, according to the current DOT&PF SWPPP template. Include information required by the Contract and described in the CGP Part 5.0.

a.	Obtain the following forms after they have been completed by the Department and include them in the SWPPP:

(1)	SWPPP Delegation of Signature Authority – DOT&PF (25D-107)

(2)	SWPPP Certification for DOT&PF (25D-109)

(3)	SWPPP Delayed Action Item Report (25D-113), if needed

b.	Use the following Department forms for recording information in the SWPPP:

(1)	SWPPP Amendment Log (25D-114)

(2)	SWPPP Certification for Contractor (25D-111)

(3)	SWPPP Construction Site Inspection Report (25D-100)

(4)	SWPPP Corrective Action Log (25D-112)

(5)	SWPPP Daily Record of Rainfall (25D-115)

(6)	SWPPP Delegation of Signature Authority – Contractor (25D-108)

(7)	SWPPP Grading and Stabilization Activities Log (25D-110)

(8)	SWPPP Pre-Construction Site Visit (25D-106)

(9)	SWPPP Project Staff Tracking (25D-127)

(10)	SWPPP Subcontractor Certification (25D-105)

(11)	SWPPP Training Log (25D-125)

(12)	SWPPP Noncompliance (25D-143)

SWPPP Template forms and instructions are available online at:

http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix.

3.	SWPPP Considerations and Contents.

a.	The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone. Construction activity outside the Project Zone must have permit coverage, using a separate SWPPP2, and separate Contractor Inspections.

b.	The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity, and identify the areas:

(1)	Over which each operator has operational control; and

(2)	Where the Department and Contractor are co-operators.

c.	For work outside the Project Zone the SWPPP must identify the entity that has storm water permit coverage, the operator, and the areas that are:

(1)	Dedicated to the Project and where the Department is not an operator; and

(2)	Not dedicated to the project, but used for the project.

d.	Account for the Contractor’s construction methods and phasing. Identify the amount of mean annual precipitation.

e.	Comply with the CGP Part 1.4.3 Authorized Non-Storm Water Discharges. List locations where authorized non-storm water will be used, including the types of water that will be used on-site.

f.	Include the Department’s Antidegradation Analysis in the SWPPP if storm water from the Project Zone discharges into receiving water that is considered a high quality water and that constitutes an outstanding national resource, according to CGP Part 2.1.6.

g.	Where the project intersects a Public Water System (PWS), the Engineer will notify the PWS contact for the Department and Contractor according to the CGP Part 4.10. Contractor Amend a copy of the communications in Appendix Q.

h.	There are special requirements in the CGP Part 3.2, for storm water discharges into an impaired water body, and they may include monitoring of storm water discharges. For Projects meeting the permit criteria, the Contractor shall implement a monitoring plan approved by the Department for the storm water within the Project Zone, and shall provide the required information and reports for inclusion in the SWPPP. The Contractor is responsible for monitoring and reporting outside the Project Zone.

i.	Preserve natural topsoil unless infeasible. Delineate the site according to CGP Part 4.2.1.  Use stakes, flags, or silt fence, etc. to identify areas where land disturbing activities will occur and areas that will be left undisturbed. Minimize the amount of soil exposed during Construction activity according to CGP Part 4.2.2.

j.	Comply with CGP Part 4.4, and the DEC General Permit for Excavation Dewatering (AKG002000), requirements for dewatering for trenches and excavations.

k.	The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed.

l.	Describe methods and time limits, to initiate temporary or final soil stabilization, CGP Part 4.5.1.1. Begin stabilization no later than the end of the next work day, following the day when the earth-disturbing activities have permanently ceased on any portion of the site or temporarily ceased on any portion of the site and will not resume for a period exceeding:

(1)	7 days for areas with mean annual precipitation 40 inches or greater; or

(2)	14 days for areas with mean annual precipitation less than 40 inches.

Time allotted to complete temporary and final stabilization, Subsection 641-2.01, 3.m.

m.	Within 7 days of initiating final stabilization, CGP Part 4.5.1.4, either complete final stabilization or continue maintenance of work until final stabilization is complete. Complete temporary stabilization within 14 days of initiating stabilization, CGP Part 4.5.1.2.

n.	Include in the “Stabilize Soils” section of the SWPPP, a description of how you will minimize the amount of disturbed and unstabilized ground in the fall season. Identify anticipated dates of fall freeze-up and spring thaw. Describe how you will stabilize areas when it is close to or past the seasonal time of snow cover or frozen conditions, and before the first seasonal thaw. Include a plan for final stabilization.

o.	Plans for Active Treatment Systems must be submitted to DEC for review at least 14 days prior to use of the system and the Operator of the ATS identified in the SWPPP. Any use of treatment chemicals must be identified on the NOI, documented in the SWPPP, and meet with the requirements in the CGP Part 4.6.

p.	The SWPPP must provide designated areas for equipment and wheel washing, equipment fueling and maintenance, chemical storage, staging or material storage, waste or disposal sites, concrete washouts, paint and stucco washouts, and sanitary toilets. These activities must be done in designated areas that are located, to the extent practicable, away from drain inlets, conveyance channels, and waters of the US. No discharges are allowed from concrete washout, paint and stucco washout; or from release oils, curing compounds, fuels, oils, soaps, and solvents. Equipment and wheel washing water that doesn’t contain detergent may be discharged on-site if it is treated before discharge.

q.	Design temporary BMPs for a 2 year 24 hour precipitation amount. Describe BMPs in the SWPPP and in SWPPP Amendments, including source controls, sediment controls, discharge points, and temporary and final stabilization measures. Describe the design, placement, installation, and maintenance of each BMP, using words, and drawings as appropriate. Describe the design capacity of sediment basins (including sediment ponds and traps). Provide a citation to the BMP Manual or publication used as a source for the BMP, including the manufacturer's or BMP manual specifications for installation (CGP Part 5.3.6.2). If no published source was used to select or design a BMP, then the SWPPP or SWPPP amendment must state that “No BMP manual or publication was used for this design.”

r.	Describe the sequence and timing of activities that disturb soils and of BMP implementation and removal. Phase earth-disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization quickly. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities. Include drawings showing each phase of the project with the BMPs implemented in the Phase.

s.	Provide a legible site map or set of maps in the SWPPP, showing the entire site and identifying boundaries of the property where construction and earth-disturbing activities will occur, as described in the CGP Part 5.3.5. Include all BMPs on the site map.

t.	Identify the inspection frequency in the SWPPP:

(1)	Inspect once every 7 calendar days regardless of the precipitation amount.

u.	Linear Project Inspections, described in CGP Part 6.5, are not applicable to this contract.

v.	The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, COE permit, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities that were not included in the Department’s permitting and consultation.

w.	The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the CGP and this specification. See Subsection 641-3.03 for more information.

4.	Recording Personnel and Contact Information in the SWPPP.

Identify the SWPPP Manager as the Storm Water Lead and Storm Water Inspector positions in the SWPPP. Document the SWPPP Manager’s responsibilities in Section 2.0 Storm Water Contacts, of the SWPPP template and:

a.	Identify that the SWPPP Manager does not have authority to sign inspection reports (unless the SWPPP Manager is also the designated project Superintendent).

b.	Identify that the SWPPP Manager cannot prepare the SWPPP unless the SWPPP Manager meets the Contract requirements for the SWPPP Preparer.

Include in the SWPPP, proof of AK-CESCL, or equivalent certifications for the Superintendent and SWPPP Manager, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced permanently or temporarily, by an acting Superintendent or acting SWPPP Manager, record in the SWPPP (use Form 25D-127) the names of the replacement personnel, the date of the replacement. For temporary personnel record their beginning and ending dates.

Provide 24-hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24-hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, proof of AK-CESCL, or equivalent certifications of ATS operators. Record the names of ATS operators and their beginning and ending dates, on Form 25D-127.

The Department will provide proof of AK-CESCL, or equivalent certifications for the Department's Project Engineer, Storm Water Inspectors, and Monitoring Person (if applicable), and names and dates they are acting in that position. Include the Department’s staff certifications in Appendix E.  Include the Department’s staff names, dates acting, and assignments, in Section 2.0 of the SWPPP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.

1.	Prepare the HMCP using the DOT&PF template located at the following DOT&PF link; (http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml) for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

2.	Designate a Contractor’s Spill Response Field Representative with 24 hour contact information. Designate a Subcontractor Spill Response Coordinator for each subcontractor. The Superintendent and Contractor’s Spill Response Field Representative must have 24-hour contact information for each Subcontractor Spill Response Coordinator and the Utility Spill Response Coordinator.

3.	List and give the location and estimated quantities of hazardous materials (Including materials or substances listed in 40 CFR 117 and 302, and petroleum products) to be used or stored on the Project. Hazardous materials must be stored in covered storage areas.  Include secondary containment for all hazardous material storage areas.

4.	Identify the locations where fueling and maintenance activities will take place, describe the activities, and list controls to prevent the accidental spillage of petroleum products and other hazardous materials. Controls include placing absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

5.	List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc.). Spill response materials must be stored in sufficient quantity at each work location, appropriate to the hazards associated with that site.

6.	Describe procedures for containment and cleanup of hazardous materials.  Describe a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Describe a plan for dealing with contaminated soil and water encountered during construction. Clean up spills or contaminated surfaces immediately.

7.	Describe methods of disposing of waste petroleum products and other hazardous materials generated by the Project, including routine maintenance.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

8.	Describe methods of complying with the requirements of AS 46.04.010-900, Oil and Hazardous Substances Pollution Control, and 18 AAC 75. Include contact information for reporting hazardous materials and petroleum product spills to the Project Engineer and reporting to federal, state and local agencies.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.  Prepare and implement an SPCC Plan when required by 40 CFR 112; when both of the following conditions are present on the Project:

1.	Oil or petroleum products from a spill may reach navigable waters (as defined in 40 CFR 112); and

2.	Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project. The Superintendent shall sign and certify the SWPPP, Inspection Reports, and other reports required by the CGP, except the NOI and NOT. The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP submitted under Subsection 641-1.03.1, Inspection Reports, and other reports required by the CGP.

The Superintendent may assign certain duties to the SWPPP Manager.

1.	Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

2.	Ensuring the control of erosion, sedimentation, or discharge of pollutants;

3.	Directing and overseeing installation, maintenance, and removal of BMPs;

4.	Performing Inspections; and

5.	Updating the SWPPP including adding amendments and forms.

When Bid Item 641.0007.____ is part of the Contract, the SWPPP Manager must be available at all times to administer SWPPP requirements, and be physically present within the Project Zone or the project office, for at least eight hours per day when construction activities are occurring.

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of this Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, environmental commitments, and historic preservation commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS. Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

Use the temporary seed mixture specified, and if not specified as directed.

Use soil stabilization material as specified in Section 727.

Use silt fences as specified in Section 729.

Use straw and straw products certified weed free of prohibited and restricted noxious weed seed and quarantined pests, according to Alaska Administrative Code, Title 11, Chapter 34 (11 AAC 34). When straw or straw products certified according to 11 AAC 34 are not available, use non-certified products manufactured within Alaska before certified products manufactured in another state, country, or territory. Non-certified straw or straw products manufactured in another state, country, or territory shall not be used. Grass, legumes, or any other herbaceous plants produced as hay, shall not be substituted for straw, or straw products.

Use Oregon Scientific RGR126 wireless rain gauge with temperature, or Taylor 2751 Digital Wireless Rain Gauge with Thermometer, or approved equivalent.

641-3.01 CONSTRUCTION REQUIREMENTS. Comply with the SWPPP and the requirements of the CGP Part 5.0.

1.	Before Construction.

The following actions must be completed before Construction Activity begins:

a.	The SWPPP Preparer must visit the Project, the visit must be documented in the SWPPP Form (25D-106), and the SWPPP must be developed (or amended) with findings from the visit;

b.	The SWPPP must be approved by the Engineer on Form 25D-109;

c.	The Contractor must be authorized to begin by the Engineer;

d.	The Project eNOIs for the Department and for the Contractor, as well as any other eNOIs if there are additional operators, must be listed as Active Status on the DEC website;

e.	The Department approved SWPPP must be submitted to DEC and Local Government (when required); and

f.	The Contractor has transmitted to the Engineer an electronic copy, and at least one hardcopy of the approved SWPPP.

g.	The Delegation of Authority (Forms 25D-108 and 25D-107) for both the Contractor and DOT&PF Engineer are signed.

h.	Begin winter construction activity according to CGP Part 4.12.2, provided actions a, c, and g are completed. If winter construction activities may extend beyond spring thaw, the following actions must be completed before spring thaw:

(1)	Actions a through g, listed above, and

(2)	Appropriate control measures to minimize erosion and sediment runoff during spring thaw and summer rainfall are installed.

i.	Post notices.

Include the following information:

(1)	Copy of all eNOIs related to this project;

(2)	Location of the SWPPP.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can safely read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes.

J.	Install an outdoor rain gauge per manufacturer’s guidance in a readily accessible location on the Project.  Projects may utilize the nearest National Weather Service (NWS) precipitation gauge station, if within 20 miles of the project, to determine rainfall amounts during storm events.

k.	Delineate the site for both land disturbing activities and areas that will be left undisturbed.

l.	Install sediment controls and other BMPs that must be placed prior to the initiation of Construction Activity.

2.	During Construction.

Before subcontractors or utility companies begin soil-disturbing activities, provide to them copies of applicable portions of the SWPPP, and require them to sign a SWPPP Subcontractor Certification, Form 25D-105. Include SWPPP Subcontractor Certifications as an appendix to the SWPPP. Ensure subcontractors and utility companies understand and comply with the SWPPP and the CGP. Inform subcontractors and utility companies of SWPPP amendments that affect them in a timely manner. Coordinate with subcontractors and utility companies doing work in the Project Zone so BMPs, including temporary and final stabilization are installed, maintained, and protected from damage.

Provide on-going training to employees and subcontractors, on control measures at the site and applicable storm water pollution prevention procedures. Training must be specific to the installation, maintenance, protection, and removal of control measures CGP 4.14. Training must be given at a frequency that will be adequate to ensure proper implementation and protection of control measures, and no less frequently than once a month during construction activity. Document on the SWPPP Training Log, Form 25D-125, the dates and attendees to these trainings. Include the SWPPP Training Log as an appendix to the SWPPP.

Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

Comply with Subsection 107-1.11 Protection and Restoration of Property and Landscape. Concrete washout must be fully contained.

Comply with CGP Part 4.8.2 for fueling and maintenance activities. Place absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment. Fuel shall not be stored within 100 feet from any waterbody or wetland, and secondary containment capable of retaining 110 percent of the fuel storage capacity would be used.  No vehicles or equipment shall be fueled or serviced within 100 feet of wetlands or fish-bearing streams, with the exception of “low-mobility” equipment used for pile driving, drilled shaft construction, or other bridge construction or removal. The HMCP details the process for fueling, which includes the “low-mobility” equipment located within 100 feet of wetlands or fish-bearing streams. The HMCP would include mobile fueling operations. The project would follow EPA and ADEC refueling and containment regulations. Fuel shall be stored a minimum of 100 feet from any wetland or waterbody, except for mobile re-fueling as described above.

Comply with requirements of the HMCP and SPCC Plan, and all local, state, and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

Keep the SWPPP and HMCP current (refer to Subsection 641-2.01.3, SWPPP Considerations and Contents)

3.	Pollutant and Hazardous Materials Reporting Requirements.

If an incident of non-compliance occurs that may endanger health or the environment a report must be made, CGP, Appendix A, Part 3.4:

a.	Orally report to the Engineer as soon as the permittee becomes aware of the incident,

b.	Orally report to DEC within 24 hours after the permittee becomes aware of the incident, and

c.	In writing, report to DEC within 5 days after the permittee becomes aware of the circumstances. To report in writing, complete the written noncompliance report on Form 25D-143, and file the written report with DEC. Coordinate the report with the Engineer. Include in the report:

(1)	A description of the noncompliance and its causes;

(2)	The exact dates and times of noncompliance;

(3)	If not yet corrected the anticipated time the project will be brought back into compliance; and

(4)	The corrective action taken or planned to reduce, eliminate and prevent reoccurrence.

Notify the Engineer and COE Regulatory Program as soon as the permittee becomes aware of an incident of noncompliance with COE Permits.

Report spills of petroleum products or other hazardous materials to the Engineer as soon as the permittee becomes aware of the incident, the DEC (CGP Part 9.3), and other agencies as required by law.  Use the HMCP and SPCC Plan (if available) for contact information to report spills to regulatory agencies.

4.	Corrective Action and Maintenance of BMPs.

Implement maintenance as required by the CGP, SWPPP, and manufacturer’s specifications, whichever is more restrictive.

a.	Implement corrective action:

(1)	If an incident of noncompliance with the SWPPP, or CGP is identified;

(2)	If an Inspection or the Engineer identifies the SWPPP or any part of the SWPPP is ineffective in preventing erosion, sedimentation or the discharge of pollutants;

(3)	If a required BMP was not installed according to the SWPPP schedule or phasing, or was installed incorrectly, or was not installed according to the CGP Part 4.0;

(4)	If a BMP is not operating as intended, has not been maintained in an effective operation condition, or is unable to effectively perform the intended function;

(5)	If sediment accumulates more than one-third of the distance of the above-ground height of the silt fence;

(6)	If sediment accumulates to more than one-half retention height for an inlet BMP, check dam, berm, wattle, or other control measures;

(7)	If a prohibited discharge of pollutants, as specified in CGP Part 4.7, is occurring or will occur; or

(8)	If there is accumulation of sediment or other pollutants, that is in or near any storm water conveyance channels, or that may enter a discharge point or storm sewer system. If there is accumulation of sediment or other pollutants that is being tracked outside the project zone.

b.	Implement corrective actions so that they comply with the following time requirements:

(1)	For conditions that are easily remedied (i.e. removal of tracked sediment, maintenance of control measure, or spill clean-up), initiate corrective action within 24 hours and complete as soon as possible;

(2)	If a discharge occurs during a local 2-year, 24-hour storm event, initiate a corrective action the day after the storm event ends;

(3)	If installation of a new control measure is needed or an existing control measure requires redesign and reconstruction or replacement to make it operational, the corrective action must be completed within 7 calendar days from the time discovered.

(4)	For all other conditions initiate corrective actions so both of the following requirements are met:

(a)	Corrective action is completed in time to protect water quality; and

(b)	Corrective action is completed no later than the Complete-by-Date that was entered in an Inspection Report (see Subsection 641-3.03.2 for more information).

If a corrective action is not implemented within the time requirements of this section, document the situation in the SWPPP, notify the Engineer, and implement corrective action as soon as possible.

If a corrective action could affect a subcontractor, notify the subcontractor within 3 days of taking the corrective action. Require in your written subcontract, that subcontractors must notify the Contractor within 24 hours of becoming aware of a condition that requires a corrective action.

5.	Stabilization.

a.	Stabilization may be accomplished using temporary or permanent measures.  Initiate stabilization of disturbed soils, erodible stockpiles, disposal sites, and of erodible aggregate layers so that all of the following conditions are satisfied:

(1)	Not later than the end of the next work day, following the day when the earth-disturbing activities have temporarily or permanently ceased (CGP Part 4.5.1.1, Note:).

(2)	As soon as necessary to avoid erosion, sedimentation, or the discharge of pollutants; and

(3)	As identified in the SWPPP.

b.	Land may be disturbed and stabilized multiple times during a project. Coordinate work to minimize the amount of disturbed soil at any one time. Do not disturb more soil than you can stabilize with the resources available.

c.	Temporarily stabilize from wind and water erosion portions of disturbed soils, portions of stockpiles, and portions of disposal sites, that are not in active construction. Temporary stabilization measures may require a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, low-erodible cover,  dust palliatives, or other approved methods.

d.	When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community, the hydro-seeder must be located at the project.

e.	Before applying temporary or permanent seeding, prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover. Apply seed and maintain seeded areas. Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

f.	Apply permanent seed according to Sections 618 and 724, within the time periods allowed by the CGP and the contract, at locations where seeding is indicated on the plans and after land-disturbing activity is permanently ceased.

g.	When installing a culvert or other drainage structure where stream bypass is not used, install temporary, or final stabilization concurrently or immediately after placing the culvert or drainage structure in a manner that complies with the SWPPP, applicable project permits and prevents discharge of pollutants. Install temporary or final stabilization:

(1)	At the culvert or drainage structure inlet and outlet; and

(2)	In the areas upstream and downstream that may be disturbed by the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure.

h.	Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install final or temporary stabilization when approved by the Engineer:

(1)	At the inlet and outlet of the culvert, drainage structure, or bridge;

(2)	In the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge; and

(3)	Under the bridge.

Within 7 days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete, CGP Part 4.5.1.5,

Complete temporary stabilization within 14 days of initiating stabilization, CGP Part 4.5.1.2.

6.	Ending CGP Coverage and BMP Maintenance in the Project Zone.

a.	The Engineer will determine the date that all the following conditions for ending CGP coverage have been met within the Project Zone:

(1)	Land disturbing activities have ceased;

(2)	Final Stabilization has been achieved on all portions of the Project Zone, according to the CGP PART 4.5.2 (including at Department furnished material sources, disposal sites, staging areas, equipment areas, etc.); and

(3)	Temporary BMPs have been removed.

b.	After the Engineer has determined the conditions for ending CGP coverage have been met, the Department will:

(1)	Send written notice to the Contractor with the date that the conditions were met;

(2)	Submit an eNOT to DEC; and

(3)	Provide a copy of the eNOT and DEC’s acknowledgement letter to the Contractor.

The Contractor is responsible for ending permit coverage within the Project Zone, by submitting an eNOT to DEC within 30 days of meeting the conditions for ending CGP coverage. The Contractor is responsible for BMP maintenance and SWPPP updates until permit coverage is ended.

If the Contractor’s CGP eNOI acreage includes Support Activities and any other areas where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must amend the SWPPP and separate SWPPP2(s), to indicate the Department’s CGP coverage has ended, and the Department is no longer an Operator within the Project Zone.

The Contractor must indicate in the SWPPP the areas that have reached Final Stabilization, and the dates land disturbing activities ended and Final Stabilization was achieved. The Contractor must submit an eNOT to DEC, and insert copies of the Department’s and the Contractor’s eNOTs with DEC’s acknowledgement letters in the appendix of the SWPPP.

The Contractor must submit a copy of each signed eNOT and DEC’s acknowledgement letter to the Department within 3 days of filing the eNOT or receiving a written response.

The Contractor is responsible for coordinating local government inspections of work and ending permit coverage with local government. See Subsection 641-1.03.5 for more information.

7.	Transmit final SWPPP.

Transmit one copy of the final SWPPP, including all amendments, appendices, and maps, to the Engineer; when the project eNOTs are filed, or within 30 days of the Department’s eNOT being filed, whichever is sooner. Transmittal must be by both electronic and at least one hard copy.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.

The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP, and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown.  Update on-site postings if records are relocated during winter shutdown. Provide the Department with copies of all Records.

Retain Records and a copy of the SWPPP, for at least three years after the date of eNOT. If EPA or DEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the retention period expires, retain the SWPPP and all Records related to the SWPPP and CGP until at least three years after EPA and/or DEC has determined all issues related to the investigation  are settled.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them.  See CGP Parts 5.10, 6.6 and 9.5.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS. Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP.  Update SWPPP Corrective Action Log Form 25D-112, SWPPP Amendment Log Form 25D-114, SWPPP Grading and Stabilization Activities Log Form 25D-110, SWPPP Project Staff Tracking Form 25D-127, and SWPPP Daily Record of Rainfall Form 25D-115.  For active projects update the Records daily.

1.	Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s Storm Water Inspector jointly, unless approved by the Engineer, when:

a.	One of the inspectors is not on site, access is only by air, and weather delayed or canceled flights;

b.	One of the inspectors is sick;

c.	The project is on a reduced frequency inspection schedule with no staff on site, the only access to the site is by air, and it is economical to send only one inspector; or

d.	When the Engineer determines a safety concern that makes joint inspection impracticable.

When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within 3 days of the Inspection date and document the date of the report transmittal.

2.	Inspection Reports.

Use only the DOT&PF SWPPP Construction Site Inspection Report, Form 25D-100 to record Inspections. Changes or revisions to Form 25D-100 are not permitted; except for adding or deleting data fields that list: Location of Discharge Points, and Site Specific BMPs. Complete all fields included on the Inspection Report form; do not leave any field blank.

Insert a Complete-by-Date for each corrective action listed that complies with:

a.	Section 641-3.01 (4), and

b.	The CGP.

Provide a copy of the completed, unsigned Inspection Report to the Engineer by the end of the next business day following the inspection.

The Superintendent must review, correct errors, and sign and certify the Inspection Report, within 3 days of the date of Inspection. The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. Deliver the signed and certified Inspection Report to the Engineer on the same day the Superintendent signs it.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days.

The Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

If subsequent corrections to the certified Inspection Report are needed, document the corrections in an amendment memo that addresses only the omitted or erroneous portions of the original Inspection Report. The Superintendent and the Engineer must both sign and certify the amendment memo. The issuance of an amendment memo does not relieve the Contractor of liquidated damages that may have been incurred as a result of the error on the original certified inspection report.

3.	Inspection before Seasonal Suspension of Work.

Conduct an Inspection before seasonal suspension of work to confirm BMPs are installed and functioning according to the requirements of the SWPPP and CGP.

4.	Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

If the Engineer approves and the entire site is stabilized, the frequency of inspections may be reduced to at least one inspection every 30 days.  At actively staffed sites, inspect within 2 business days of the end of a storm event that results in a discharge from the site.

When work is suspended due to fall freeze-up, the Engineer may suspend inspection requirements after fourteen days of freezing conditions if:

a.	Soil disturbing activities are suspended; and

b.	Soil stabilizing activities are suspended.

Inspections must resume according to the normal inspection schedule identified in the SWPPP, at least 21 days before anticipated spring thaw. See CGP Part 6.2.3.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall during seasonal suspension of work.  If so, resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in runoff.  Resume recording land disturbance and stabilization activities on the Grading and Stabilization Activities Log when Construction Activity resumes.

5.	Stabilization before Fall Freeze-up and Spring Thaw.

Stabilize Construction Activities within the Project Zone with appropriate BMPs prior to the anticipated date of fall freeze-up, in accordance with the CGP Part 4.12.

Exceptions to stabilization prior to anticipated date of fall freeze up include:

a.	When stabilization activities are precluded by snow cover or frozen ground conditions prior to the anticipated date of fall freeze up, or

b.	When winter construction activity is authorized by the Engineer and conducted according to the contract.

Stabilize Construction Activities within the Project Zone with appropriate BMPs prior to spring thaw, as defined in the CGP.

6.	Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion.

7.	Items and Areas to Inspect.

Conduct Inspections of the areas required by the CGP and SWPPP.

8.	SWPPP Amendments and SWPPP Amendment Log.

The Superintendent and the SWPPP Manager are the only persons authorized to amend the SWPPP and update the SWPPP Amendment Log Form 25D-114. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

a.	Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

b.	If an Inspection identifies that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

c.	Whenever an Inspection identifies a problem that requires additional or modified BMPs

d.	Whenever a BMP is modified during construction or a BMP not shown in the original SWPPP is added;

e.	If the Inspection frequency is modified (note beginning and ending dates); or

f.	When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01.4.

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than 7 days following identification of the need for an amendment.  Every SWPPP Amendment must be signed and dated. Cross-reference the amendment number with the Corrective Action Log or SWPPP page number, as applicable. When a BMP is modified or added, describe the BMP according to Subsection 641-2.01.3.

Keep the SWPPP Amendment Log current. Prior to performing each scheduled Inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log as an appendix to the SWPPP.

9.	Site Maps.

Document installation, routine maintenance, and removal of BMPs by making notes on the SWPPP Site Maps. Include the date and the recording person’s initials by these notes. Identify areas where Construction Activities begin, areas where Construction Activities temporarily or permanently cease, and areas that are temporarily or permanently stabilized.

10.	Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112. Document the need for corrective action within 24 hours of either:

a.	Identification during an inspection; or

b.	Discovery by the Department's or Contractor’s staff, a subcontractor, or a regulatory agency inspector.

Modification or replacement of a BMP, installation of a new BMP not shown in the original SWPPP,  overdue BMP maintenance, or other reasons listed as corrective actions in 641-3.01.4 must be documented on the Corrective Action Log.

Within 24 hours of discovery, update the Corrective Action Log Form 25D-112, with the date of discovery and proposed corrective action. If discovered during an inspection, update log with inspection date and proposed corrective actions noted on the Inspection Report.  If discovered outside of an inspection, update the log with the date of discovery, the proposed corrective action, and the date the corrective action was completed.

After the corrective action has been accomplished, note in the Corrective Action Log the action taken and if a SWPPP amendment was needed. Date and initial the entry.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log as an appendix to the SWPPP.

11.	Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection. Keep the Grading and Stabilization Activities Log organized and completed to demonstrate compliance with the CGP Part 4.5.

Keep the Grading and Stabilization Activities Log as an appendix to the SWPPP.

12.	Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled Inspection.  Keep the Daily Record of Rainfall as an appendix to the SWPPP.

13.	Staff Tracking Log.

Use the SWPPP Project Staff Tracking, Form 25D-127, to keep staff records current. Include Records of the AK-CESCL or equivalent qualifications for the Superintendent, SWPPP Manager, ATS operator, any acting Superintendent and acting SWPPP Managers, and beginning and end dates for temporary personnel assignments related to administration of the CGP or Section 641. Update the SWPPP Staff Tracking Log within 24 hours of any changes in personnel, qualifications, or other staffing items related to administration of the CGP or Section 641.

641-3.04 FAILURE TO PERFORM WORK. The Engineer has authority to suspend work and withhold monies, for an incident of non-compliance with the CGP, or SWPPP, that may endanger health or the environment or for failure to perform work related to Section 641.

1.	Non-compliance.

a.	Incidents of Non-compliance. Failure to:

(1)	Obtain appropriate permits before Construction Activities occur;

(2)	Perform SWPPP Administration;

(3)	Perform timely Inspections;

(4)	Update the SWPPP;

(5)	Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms to the Engineer;

(6)	Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

(7)	Perform duties according to the requirements of Section 641; or

(8)	Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control.

b.	Notice of non-compliance, either oral or written will include:

(1)	Reason/defects

(2)	Corrective actions required

(3)	Time allowed for completing the corrective action

c.	Levels of Non-compliance and Response correspond with harm to the workers, the public or the environment and whether the harm is:

(1)	Not-imminent, the Engineer will either orally or in writing, or both, provide notice to the Contractor indicating the incident of non-compliance.

Contractor's that take corrective action and complete the action to the satisfaction of the Engineer, within the time specified, may return to the status of compliance, and avoid elevating the response to imminent.

(2)	Imminent, the Engineer will orally provide notice to the Contractor of non-compliance and promptly provide written notice to suspend work until corrective action is completed.

Additional actions, taken against the Contract whether the level of non-compliance is Not-imminent or Imminent, may include:

(1)	Withholding monies until corrective action is completed

(2)	Assessing damages or equitable adjustments

(3)	Employing others to perform the corrective action and deduct the cost

No additional Contract time or additional compensation will be allowed due to delays caused by the Engineer’s suspension of work.

641-3.05 ACCESS TO WORK.

The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies. See CGP Part 6.6.

641-4.01 METHOD OF MEASUREMENT.

See Section 109 and as follows:

Item 641.0001.____, and 641.0007.____, are lump sum.

Item 641.0005.____, measured on a contingent sum basis as specified by the Directive authorizing the work.

Item 641.0006.____, measured on a contingent sum basis with withholding determined by the Department.

TABLE 641-1 BMP VALUES - RESERVED

Liquidated Damages assessed according to Table 641-2 are not an adjustment to the Contract amount. These damages charges are related to Contract performance but are billed by the Department to the Contractor, independent of the Contract amount. An amount equal to the Liquidated Damages may be withheld for unsatisfactory performance, from payment due under the Contract, until the Contractor remits payment for billed Liquidated Damages.

TABLE 641-2- VERSION C

EROSION, SEDIMENT AND POLLUTION CONTROL – LIQUIDATED DAMAGES

| Code | Specification Section Number and Description | Deductible Amount in Dollars | Cumulative Deductible Amounts in Dollars |
| --- | --- | --- | --- |
| A | 641-1.04 Failure to have a qualified (AK-CESCL or equivalent) SWPPP Manager | Calculated in Code B or F |  |
| B | Failure to meet SWPPP requirements of: (1) 641-2.01.1 Name of SWPPP Preparer (2) Not Applicable (3) 641-3.03.8 Sign and Date SWPPP amendments by qualified person. (4) 641-3.02 Records maintained at project and made available for review | $750 per omission |  |
| C | Not Applicable. |  |  |
| D | 641-3.03.5 Failure to stabilize a Project prior to fall freeze-up. | $5,000 per Project per year |  |
| E | 641-2.01.1. Failure to conduct pre-construction inspections before Construction Activities on all projects greater than 1 acre. | $2,000 per Project |  |
| F* | 641-3.03. Failure to conduct and record CGP Inspections 641-3.03.1 Personnel conducting Inspections and Frequency 641-3.03.2 Inspection Reports, use Form 25D-100, completed with all required information | $750 per Inspection | Additional $750 for every additional 7 day period without completing the required inspection. |
| G | 641-3.01.4 Corrective action, failure to timely accomplish BMP maintenance and/or repairs. In effect until BMP maintenance and/or repairs is completed. | $500 per Project per day |  |
| H | 641-3.01.3 Failure to provide to the Engineer and DEC a timely oral noncompliance report of violations or for a deficient oral noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| I | 641-3.01.3 Failure to provide to the Engineer and DEC a timely written noncompliance report, use Form 25D-143, of violations or for a deficient written noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| J | 641-3.04 Failure to comply with the requirements of the CGP, approved SWPPP, and Section 641, except as listed above | $750 per occurrence for the first day of noncompliance | Additional $750 for every day the deficiency remains uncorrected |

*CODE F.	Liquidated Damages according to Code F will not be billed for typographic errors and minor data entry errors, except the liquidated damages will be assessed for these errors when:

a.	the Contractor has previously been notified and subsequent inspection reports repeat the same or similar error,

b.	multiple inspection reports are submitted after the submission due date and the same or similar errors are repeated on multiple overdue reports,

c.	an error in recording the inspector's AK-CESCL certification date results in an inspector performing the inspection during a period when their certification was lapsed or was otherwise invalid

641-5.01 BASIS OF PAYMENT. See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

Item 641.0001.____ Erosion, Sediment and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and Record keeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Item 641.0005.____ Temporary Erosion, Sediment and Pollution Control by Directive. At the contingent sum prices specified in the Directive using time and materials to authorize the work, for all labor, supervision, materials, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. Prices for this item will be by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor. All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641.0006.____ Withholding. The Engineer may withhold an amount equal to Liquidated Damages, assessed according to Section 641, from payment due the Contractor. Liquidated Damages for violations of the Contract, CWA, and CGP are determined by the Engineer according to Table 641-2. The Engineer may withhold payment due the Contractors until the Contractor pays the Liquidated Damages to the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Item 641.0007.____ SWPPP Manager. At the Contract lump sum price for a SWPPP Manager that conforms to this specification. When Item 641.0007.____ appears in the Bid Schedule, the SWPPP Manager must be a different person than the superintendent, and must be physically present during construction activity with duties and authority as described in Subsection 641-2.04. When Item 641.0007.____ does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to Item 641.0001.____.

Subsidiary Items.  Temporary erosion, sediment, and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641.0001.____ Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641. This work includes but is not limited to:

1.	Dewatering;

2.	Shoring;

3.	Bailing;

4.	Permanent seeding;

5.	Installation and removal of temporary work pads;

6.	Temporary accesses;

7.	Temporary drainage pipes and structures;

8.	Diversion channels;

9.	Settling impoundment; and

10.	Filtration.

Permanent erosion, sediment, and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense.  Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 641.0001.____ | Erosion, Sediment and Pollution Control Administration | LS |
| 641.0005.____ | Temporary Erosion, Sediment and Pollution Control by Directive | CS |
| 641.0006.____ | Withholding | CS |
| 641.0007.____ | SWPPP Manager | LS |

CR641-113020 / CFHWY00213

SECTION 642
CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-1.01 DESCRIPTION.  Add the following:

Furnish and maintain facilities, equipment, and services specified in this section for Digital Terrain Modeling (DTM).  All furnished facilities and equipment remain your property when you complete the work.

Replace Subsection 642-1.02 with the following:

642-1.02 DEFINITIONS.

1.	Break Line: A break line defines the horizontal location where TIN lines must break, and snap to the vertical location of the break line.

2.	Catch Point: In the cross section of a road, the point at which the fill or cut slope intersects the edge of the existing ground.

3.	CAD:  Computer-Aided Design.

4.	CORS:  Continuously Operating Reference Station.

5.	DTM: Digital Terrain Model. A computer generated 3D model representing the project terrain, and based on the association of features such as alignments, profiles, sections, grading lines, points, and surfaces.

6.	GLONASS: A radio-based satellite navigation system operated by Russia. GLONASS is an alternative and is complementary to the United States Global Positioning System.

7.	GNSS:  Global Navigation Satellite System.

8.	GPS: Global Positioning System; A radio-based satellite navigation system operated by the United States.

9.	Hinge Point: In the cross section of a road, the point at which any slope intersects another slope of different angle.

10.	Monument: A fixed physical object marking a point on the surface of the earth; used to commence or control a survey; mark the boundaries of a parcel of land; or the centerline of a right-of-way corridor. Monuments will be Primary or Secondary, as shown in the Plans.

11.	Neat-line: Defines the geometric limits of a material, as indicated by the typical section, profile, and alignment.

12.	NGS: National Geodetic Survey; United States Government Agency that provides information and products related to the definition and management of the NSRS.

13.	NSRS: The National Spatial Reference System.

14.	OPUS: On-line Positioning User Service; The National Geodetic Survey operates OPUS as a means to provide GPS users easier access to the NSRS.

15.	Point: An identified spot located on the surface of the earth. For the purpose of this definition, a point can be either physical or electronic depending on the context in which it is used. Physical points include PK nails, wooden hubs, rebar, large nails, or other structures capable of being utilized as a marker. Electronic points include all points generated by computers or electronic surveying equipment.

16.	PPK: Post Processed Kinematic; PPK surveys are similar to RTK surveys, except there is no radio communication between the reference station and the rover, so the rover cannot process a position in “real time”. Survey data from both the reference station and rover is imported into GPS processing software to determine the measured position.

17.	Reference Monument: A monument placed at a known distance and direction from a property corner or other survey point, usually not on a property or survey line. A reference monument is employed to perpetuate a corner/point that cannot be monumented at its true location or where the corner monument is subject to destruction.

18.	RTK: Real Time Kinematic; RTK surveys utilize two or more receivers with at least one receiver remaining stationary over a known coordinate. The radio at the reference station broadcasts its position to the rovers and the system processes the baselines in “real time” allowing for project coordinate information to be gathered and analyzed during the actual field survey.

19.	Slope Staking: The process of using measurements and calculations to determine where to begin a cut or fill, the slope ratio, and the depth of the cut or fill.

20.	Static: Static survey methods require multiple GPS receivers to collect data over the course of a long period of time. The data collected by the receivers is downloaded into a GPS processing software program to determine the measured position.

21.	Surveyor: The Contractor’s Professional Land Surveyor placed in “responsible charge”, and currently registered in the State of Alaska as defined in AS 08.48.341.

22.	Superelevation Rate: The roadway surface cross-slope (%), measured perpendicular from the centerline, occurring at most locations with roadway curvature. Defined by “S” on the Plans.

23.	Superelevation Transition: The total distance of “runout” and “runoff” required to attain the roadway’s full superelevation rate. Superelevation Transitions occur at both ends of roadway curvature and commence/terminate at the location where the typical roadway cross-slope is exceeded/re-established.

24.	Tessellation Spacing: The distance along a line or an arc that a TIN point is created.

25.	TIN: Triangulated Irregular Network; A vector based representation of a physical land surface.

26.	Witness Corner: A point or monument placed at a known distance and direction from a property corner or other survey point. A witness corner is employed to witness the location of a corner/point that cannot be monumented at its true location.

27.	Weeding: A procedure used to limit the frequency of information displayed.

CFHWY00308

642-2.01 MATERIALS.

Add No. 4:

4.	Digital Measuring Instrument:  Nu-metrics, Nitestar DMI (www.ae-traffic.com), or approved equal.

Replace Subsection 642-3.01 with the following:

642-3.01 GENERAL.

Work classified as Land Surveying under AS 08.48, and work involving the location, control, and monumentation of construction centerline and right-of-way, shall be performed by or directly under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor.

Use competent, qualified personnel and suitable equipment for construction surveying activities. The Surveyor’s personnel shall be supervised and trained in the avoidance of systematic errors. The Surveyor’s personnel shall be familiar with geodetic concepts and least-squares adjustments. Correcting errors resulting from the operations of said personnel shall be at the Contractor expense. The Contractor is responsible for the accuracy of the work.

Schedule a mandatory Pre-Survey Conference with the Engineer, Contractor, Surveyor, and all personnel who are to be involved in the survey work, two weeks prior to beginning survey work. The purpose of this meeting will be to discuss methods and practices of accomplishing the required survey work.

Furnish computer services to accomplish the work. All data shall be signed by the Surveyor for completeness and accuracy. As soon as practical after completion of the work, and in no case later than acceptance of the project, deliver field books, computer forms and computer output data to the Engineer. Furnish all computer generated data in a file format and medium that is compatible with Department software. This data becomes the property of the State of Alaska.

Furnish field survey notes. Keep field notes in standard bound notebooks in a clear, orderly, and neat manner consistent with the State of Alaska DOT&PF Construction Surveying Requirements. Make field books available for inspection by the Engineer’s project personnel at any time. Copies of the field books shall be kept in a separate secure location.

Furnish all equipment including but not limited to vehicles, stakes, measuring tapes, levels, rods, lasers, GPS receivers, total stations, traffic control devices, safety devices and other equipment necessary for establishing, checking and maintaining the required points, lines and grades.

Furnish traffic control necessary for surveying activities in accordance with Section 643, and the latest edition of the Alaska Traffic Manual (ATM). Outfit all field employees with appropriate High Visibility Clothing as defined in Section 643, Subsection 3.11.

The Engineer may randomly spot check the Contractor's surveys, staking, and computations. The Department assumes no responsibility for the accuracy of the work.

The Engineer has the right to communicate directly with the Surveyor. Any communication regarding changes to the original scope of work shall go through the Contractor.

The Surveyor is responsible for:

1.	Maintaining registration as a Professional Land Surveyor in the State of Alaska.

2.	Maintaining familiarity with the site conditions and progress of the project.

3.	Determining the accuracy required for each survey stake.

4.	Following the State of Alaska DOT&PF Construction Surveying Requirements.

5.	Notifying the Engineer of conflicts and changes necessary due to utilities, match point variations, design revisions, or other variables.

6.	Slope Staking.

7.	Staking all clearing and/or grubbing limits. Clearly identify all trees that are specified to remain.

8.	Staking and hubbing all layers of material shown in the typical sections, including the bottom of excavation, top of borrow, top of base course, and top of surcharge.

9.	Staking all culverts, inlets, and other drainage appurtenances.

10.	Surveying additional roadway surface cross-sections, as necessary, to accurately re-establish existing superelevation ratios and superelevation transitions.

CFHWY00308

11.	Before work on the project starts, stake and reference the existing centerline on both sides of the roadway alignment.  Stake the existing centerline on tangents at 100 ft, and 50 ft intervals on curves from the beginning and ending of super-elevation changes when the roadway is no longer at normal crown.  Stake sign locations at proper offset.  Stakes shall be a minimum of 1" x 2" x 2'-0" and be offset 4 to 8 ft from the shoulder on both sides of the roadway.  Extend lath stakes a minimum of 2 ft above ground.  Show the offset distance to centerline and the station from the beginning of the project.  Maintain staking until the final roadway striping is completed.  Staking accuracy work requires an electronic distance measuring instrument (DMI) be installed in the Contractor's vehicle.  Calibrate the DMI to roadway alignments as stationed in the Plans before beginning work.  Record the calibration and staking information in the field book.

Install a reference sign every 500 ft.  These reference signs shall meet the following requirements:

a.	mounted with the base a minimum of 5 ft above the shoulder,

b.	located a minimum of 10 ft from the edge of shoulder,

c.	marked with the station from the beginning of the project, in 6 inch high permanent black lettering with a letter proportion height to width ration of 1:0.6 and a stroke width to height ratio of 1:6, on an orange background.

CR642.1-022015R/CFHWY00308

12.	Passing Sight Distance. Record the existing centerline striping and final passing sight distance. A copy of the 8 1/2" x 11" Existing Striping, Passing Sight Distance and Final Striping form is included herein. Document the existing passing and sight distance similar to the example included.

Using the "Existing Striping, Passing Sight Distance and Final Striping" form:

a.	Document the existing striping.  Do not disturb the existing striping until the striping record is accepted by the Engineer.

1)	Project Information: Road Name, Stationing, Surveyor & license, Date surveyed.

2)	Col. 1.: Project Stationing in 100-foot intervals from beginning to end of project.

3)	Col. 2.: Posted operating speed per minimum passing sight distance (Table 642-1).

4)	Col. 3a & 4a: Each direction of travel (NB; SB, EB, WB) record the existing striping: passing (dashes) and no passing zones (continuous line) similar to the example. Maintain the orientation of travel to the form, each road, from the beginning of the project to the end of the project.

5)	Col. 6.: Add comments to help clarify the documentation and significant sight obstructions, as needed. Initial your comments.

Submit the form to the Engineer and make changes when directed by the Engineer.

b.	Document the passing sight distance. Use the form approved in a. for b. Measure and record, after the base course layer is complete, passing sight distance along the roadway in both directions of traveled way at 100-foot maximum intervals and referenced to the project station. Use a 3.5-foot object height or instrument height looking ahead to a 3.5-foot target height which is at the centerline or opposing edge of traveled way.

1)	Col. 3 & 4.: Each direction of travel (NB, SB, EB, WB) record the sight distance each station. Record the measurement to the nearest 100-foot up to 1200-foot where the passing sight distance exceeds the minimum passing sight distance. Where the passing sight distance exceeds 1200-foot, record the measurement as "1200+ Feet." Record the measurement to the nearest 10-foot at all stations that fall below the minimum passing sight distance.

2)	Col. 6.: Add comments to help clarify the documentation as needed. Initial your comments.

Submit the form to the Engineer and make changes when directed by the Engineer.

c.	Final Striping. Using the information approved in a. and b., the existing striping and passing sight distance, the Engineer will evaluate the existing striping and provide the final striping plan 14 days after the Contractor's passing sight distance submittal, 12b above.

1)	Col. 3 & 4: Engineer, indicate if the existing striping passes (P) or fails (F).

2)	Col. 5a & 5b: Engineer, indicate the final striping.

3)	Col. 6.: Engineer, add comments if needed to clarify the final striping. Initial your comments.

Do not begin striping until the Engineer returns the form, signed and dated with the final striping plan.

Engineer, provide the Regional Traffic and Safety Engineer an informational copy of the final striping plan.

TABLE 642-1

PASSING SIGHT DISTANCE REQUIREMENTS a

| Posted Speed (mph) | Minimum Passing Sight Distance and Minimum Length of Passing Zone (ft) | Minimum No-Passing Zone on Stopped Approaches to Intersections (ft) |
| --- | --- | --- |
| 30 | 500 | 220 |
| 35 | 550 | 255 |
| 40 | 600 | 295 |
| 45 | 700 | 330 |
| 50 | 800 | 365 |
| 55 | 900 | 405 |
| 60 | 1000 | 440 |
| 65 | 1100 | 480 |
| 70 | 1200 | 515 |

a.	One- and two-direction no-passing zones for one direction of traffic shall be no shorter than 500 feet

CR642.2-072215R/CFHWY00308

13.	Staking all right-of-way and material source limits.

14.	Rabbit tracking for temporary and permanent pavement striping, and pavement marking devices.

15.	Development of DTM’s, and plotted cross sections.

16.	As-built and Topographic surveying.

17.	Removal and disposal of all flagging, lath, stakes and other staking material after the Project is completed. Burning of material is not allowed on the project.

18.	All other surveying and staking necessary to complete the project.

Replace Subsections 642-3.02 through 642-3.05 with the following:

642-3.02 MONUMENTS.  The Department will reference and replace all monuments identified on the plans. The Surveyor shall notify the Engineer immediately of any monuments encountered that are not identified on the plans. The Engineer will determine whether the monuments encountered are to be referenced or adjusted by the Surveyor or the Department.

If directed by the Engineer, the adjustment of monument cases or the referencing of monuments not identified on the plans will be considered additional work and paid by 642(3), Three Person Survey Party. Set existing monument cases to be adjusted to new elevations in the manner and at the elevations directed.

The Surveyor shall complete and stamp a State of Alaska Land Survey Monument Record form for each primary and secondary monument referenced. Provide the required survey information on the form in accordance with statutory requirements, including the project name/number, section, township, and range. Meet requirements for recording at the District Recorder’s Office in which the project is located for each monument record. Deliver conforming copies of the recorded forms to the Engineer before monument removal or disturbance.

642-3.03 SURVEY CONTROL. The basis of project control is identified in the Survey Control Sheet. Use the calibration parameters shown in the Survey Control Sheet to Calibrate/Localize/Convert to the local project coordinate system. Contact the DOT&PF Central Region Survey Manager through the Engineer for calibration parameters if they are not shown in the plans. Independently recover and verify all survey control points shown in the Survey Control Sheet. Establish and verify new reference points where required, to replace missing points. Notify the Engineer immediately if a reference point is discovered to be in error, or a reset point is not in harmonious relationship to the existing control points. Provide the Engineer a signed hard copy verifying vertical loop closure of project control points.

The use of RTK is not an acceptable method for establishing additional horizontal or vertical control. Horizontal control points may be established using Static GPS or conventional traversing methods. Vertical control points shall be established with differential levels.

Survey accuracy requirements shall conform to the minimums listed in the State of Alaska DOT&PF Construction Surveying Requirements.

642-3.04 GPS SURVEYS. The specifications described in this Section are not intended to discourage the use of new GPS procedures and techniques. Procedures that are not defined by this specification may be allowed if approved by the DOT&PF Central Region Survey Manager, through the Engineer.

1.	General Requirements:

a.	All surveying shall be done in the local project coordinate system.

b.	OPUS shall be used for the determination of Reference Station positions only, and shall not be used directly for producing final positions for any Static, Fast Static, RTK or PPK surveys. OPUS may be used as a tool for verification of the final positions obtained from these types of surveys.

2.	GPS Equipment: Survey Grade dual frequency GPS receivers shall be used. For static surveys these shall be set up on adjustable leg tripods at a minimum. Fast or Rapid Static GPS surveys require a bipod at a minimum. RTK or PPK surveys may use fixed or adjustable poles, or secure lashings to vehicles.

3.	GPS Reference Stations:

a.	All Reference Stations shall be approved by the DOT&PF Central Region Survey Manager through the Engineer, prior to conducting any GPS surveys.

b.	Primary Reference Stations shall meet current NGS CORS standards. Secondary Reference Stations may be used temporarily when a Primary Reference Station is not available.

c.	Primary Reference Stations shall be permanently mounted and shall not change throughout the duration of the project.

d.	Secondary Reference Stations may be tripod mounted, however, GPS receivers shall never be mounted on aluminum tripods.

e.	All Reference Stations shall be tied to an OPUS derived position, and on the NAD83 datum. Submit GPS data files for a minimum of 2 days, 12 hours per day, 5 second epoch to OPUS to determine the final position. The OPUS derived position shall be determined at the beginning of the project, and shall not change throughout the duration of the project unless approved by the Engineer. Notify all users immediately if any changes are made to the Reference Station’s position. If OPUS is unable to process a position, the Reference Station shall be tied to existing project control.

f.	Reference Stations shall be physically located in clear view of the sky. Avoid locations near cellular towers or other areas that may disrupt satellite signal reception. Avoid locations near large flat surfaces such as buildings, large signs, fences, and other objects that may cause multi-path interference.

g.	Reference Stations shall be located to provide maximum coverage of the project area.

h.	Store 5 second epoch data, and post data online for use by the Engineer.

i.	GNSS enabled Reference Stations are allowed.

4.	RTK Surveys:

a.	The Surveyor shall follow prudent practices when conducting RTK surveys. The NGS has published a manual titled National Geodetic Survey User Guidelines For Single Base Real Time GNSS Positioning, v.3.1 issued in April 2014. The Surveyor shall become familiar with this manual, in order to better understand prudent practices. Copies of the draft manual may be available upon request or may be downloaded from the following web site: https://www.ngs.noaa.gov/PUBS_LIB/UserGuidelinesForSingleBaseRealTimeGNSSPositioningv.3.1APR2014-1.pdf.

b.	RTK surveys may not be used to permanently mark or delineate Right-Of-Way.

5.	Local Coordinate Calibration:

a.	Use GPS calibration parameters if they are provided on the Survey Control Sheet. If GPS calibration parameters are not given, develop a local site calibration based on existing project control. All included control points shall have WGS84 positions that were observed by either a GPS Static or Fast Static network, as well as the final adjusted project control coordinate values that match the values listed on the Survey Control Sheet. The calibration shall consist of the following conversion parameters; Rotation, Translation, Scale, and GPS derived orthometric heights. Values listed on the Survey Control Sheet shall be held fixed in any adjustment, barring any large residuals. Notify the Engineer of any large residuals so that the problems can be identified and corrected. Submit a signed hard copy of the calibration parameters, residuals, and related control points to the Engineer for approval before staking activities begin.

b.	Perform a local calibration each time the coordinates of the reference station change.

6.	GPS Data Summary Report:

a.	Generate reports for all surveyed points, including the Point Number, Northing, Easting, Elevation, Point Code, Annotation(s), Date, Time, residuals, observation (start and stop) times, and antenna height information. Summary reports shall bear the signature and seal of the Surveyor.

b.	The Engineer may require the Contractor to re-survey specified points at no cost to the Department if the Survey doesn’t meet the minimum accuracy requirements defined in the State of Alaska DOT&PF Construction Surveying Requirements.

7.	Weather Conditions: The Surveyor shall follow prudent practices when conducting GPS surveys in inclement weather. The following is recommended as a guideline:

a.	Regularly observe surface and solar weather forecasts prior to planning survey activities.

b.	Use sound practical judgment when performing surveys during inclement weather conditions.

c.	Observations should never be conducted during an electrical storm.

d.	Note significant or unusual weather conditions in the field notes, data collector, or receiver.

642-3.05 TOPOGRAPHIC SURVEYS. Topographic surveys shall be conducted under the direct supervision of the Surveyor. The purpose of a topographic survey is to gather field data to determine the configuration (relief) of the surface of the earth (ground). Use all data collected to generate topographic DTM surfaces as defined in Section 642-3.07, Digital Terrain Models. All data becomes the property of the State of Alaska. Conduct topographic surveys as follows:

1.	General Requirements:

a.	Collect topographic data within the right-of-way limits.

b.	Keep all shots 50 ft or closer, as necessary to accurately define all surface features within the roadway corridor.

c. 	Keep a field book of notes describing changes or errors of rod heights, point descriptors, or other annotations necessary to verify all electronic data.

d. 	Identify each point with a point number. Multiple points with the same point number are not permitted.

e. 	Identify each shot with the appropriate point code. Break line points shall be separately identifiable from ground shots.

f. 	Append any additional information required to further describe a point with point annotations.

g. 	Develop a summary of standard point codes for all points used on the project.

h. 	Develop a summary of standard point descriptors to identify all point codes used on the project (i.e. Edge of Pavement is the point descriptor corresponding to the EP point code).

2.	Functional Requirements: The purpose of a topographic survey is to develop an appropriate DTM as defined in Section 642-3.07. Conduct a topographic survey to meet the appropriate functional requirements as defined below:

a.	As-built Surfaces – Conduct a survey of all finished roadway surfaces, embankments, ditches and other topographic features as required to accurately define the project topography.

b.	Excavation Surfaces – Conduct a survey of original grade (upper) surfaces, and bottom of excavation (lower) surfaces, as necessary to produce DTM volumetric quantities. Follow the requirements listed below:

(1)	Upper surface – Survey prior to excavation. Topographic data may be collected prior to grubbing and pavement removal, and adjusted by the average depth removed as measured in the field.

(2)	Lower surface – Survey after the final grade has been established by excavation.

c.	Embankment Surfaces – Conduct a survey of excavated or original grade (lower) surfaces, and top of embankment (upper) surfaces, as necessary to produce DTM volumetric quantities. Follow the requirements listed below:

(1)	Upper surface – Survey after the final grade has been established.

(2)	Lower surface – Survey prior to the placement of embankment. If only grubbing or pavement removal is required prior to placement of embankment, the topographic data may be collected prior to grubbing and pavement removal and adjusted by the average depth removed, as measured in the field. If excavation is required prior to placement of embankment, survey only after excavation activities have been completed.

3.	Accuracy Tolerance Limits: The Surveyor shall check into and collect primary control monument locations to ensure the data being collected meets the minimum Horizontal and Vertical Accuracy Tolerances. This shall serve as a basis of acceptance for the topographic data collected by the Surveyor. The Horizontal and Vertical Accuracy Tolerances will be used to check for systematic error, and will be evaluated by comparing all control check shots taken during the topographic survey to the monument’s location as defined on the Survey Control Sheet. The Volumetric Accuracy Tolerance will be used to check for random and operator error, and will be evaluated by comparing the Contractor furnished DTM with an independent DTM developed by the Department. The Volumetric Accuracy Tolerance shall be applied only to survey data that is used to calculate volumetric quantities.

a.	Horizontal Accuracy Tolerance – Check shots shall be within ± five hundredths (0.05) of a foot of the monument’s horizontal position. If any of the data doesn’t meet the minimum the horizontal tolerance, the Engineer may require the Contractor to re-survey the non-conforming points at no additional cost to the Department.

b.	Vertical Accuracy Tolerance – Check shots shall be within ± one tenth (0.10) of a foot of the monument’s vertical position. If any of the data doesn’t meet the minimum vertical tolerance, the Engineer may direct the Contractor to re-survey the non-conforming points at no additional cost to the Department.

c.	Volumetric Accuracy Tolerance – The Department will determine the volumetric error on randomly selected areas, including at least 20% of the area within the slope limits.  The Department will calculate the volumetric error as follows:

(1)	Determine the net volume by comparing the Contractor’s DTM to the Department’s DTM.

(2)	Determine the accepted volume by comparing the Department’s DTM to the appropriate neat-line surface.

(3)	Determine the volumetric error by dividing the net volume by the accepted volume.

The Engineer may require the Contractor to re-survey any areas that exceed 5% error at no additional cost to the Department.

4.	Control Check Requirements: Collect local project control data at the following minimum frequency:

a.	Every time the instrument is turned on, at the beginning of the survey session.

b.	Prior to every time the instrument is turned off, at the end of the survey session.

c.	Every time the instrument is moved (radial survey).

d.	Every time the backsight is moved (radial survey).

e.	Every time the actual or broadcasted position of the Reference Station changes (GPS survey).

5.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted and electronic as-built surfaces (developed per Section 642-3.07) showing major and minor contours. Standard contour intervals shall be 5 ft (major) and 1 ft (minor).

b.	All field books noting any errors, corrections, or changes to the data.

c.	All electronic survey data in a comma delimited ASCII file in PNEZD format (Point number, Northing, Easting, Elevation, and Description).

- Letter of conformance signed and sealed by the Surveyor, certifying that the Topographic Survey meets the minimum Horizontal and Vertical accuracy requirements. Attach all backup data and calculations.

642-3.06 AS-BUILT SURVEYS. As-built surveys shall be conducted under the supervision of the Surveyor. The as-built survey shall document the final locations of roadways, topographic surfaces, structures, and utilities within the ROW project limits. The Surveyor shall maintain communication with the Contractor, Sub-Contractor or Utility Company as necessary to coordinate surveying activities. Surveying activities shall be conducted as soon as possible as each phase of the project is completed, and to avoid scheduling conflicts. The survey will be used to verify that the contracted work items conform to the plans and specifications. All survey data becomes the property of the State of Alaska.

1.	General Requirements:

a.	Topographic Survey of all roadway and pedestrian corridors, in accordance with Section 642-3.05, Topographic Surveys.

b.	Utility Survey of all existing and re-located utilities. Record the horizontal and vertical location of all underground and overhead utilities. Take digital photos of all exposed utility crossings. Identify the location of each photo taken, including the approximate northing, easting, and bearing.

c.	Structural Survey of all existing and re-located structures, including bridges, tunnels, manholes, signs, fences, guard rails, walls, and foundations.

2.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted as-built drawings showing the final surveyed locations of all roadways, topographic surfaces, structures, and utilities. Plotted drawings shall be identified by the Project name and number, and bear the signature and seal of the Surveyor.

b.	Printed color photos, identifying the location of all underground utility crossings.

c.	All field books used to conduct the as-built survey.

d.	All DTM and point data files generated by the as-built survey.

642-3.07 DIGITAL TERRAIN MODELS. Develop all Digital Terrain Models using CAD software that is compatible with the latest release of software used by the Department. All DTM’s shall be approved by the Engineer.

1.	DTM Development Methods:  Develop all DTM’s using the appropriate method as defined below:

a.	Engineering Method - Use this method to define all neat-line surfaces. Develop the DTM by associating all appropriate engineered features such as alignments, profiles, sections, daylight surfaces, grading lines, and other features.

(1)	CAD software shall generate and automatically update surfaces based on the association of alignments, profiles, sections, grading lines, and other parameters necessary to accurately represent neat-line geometry.

(2)	Limit tessellation spacing to allow an accurate representation of a surface feature. The Engineer may require changes to the tessellation spacing, if necessary to allow an accurate representation of the feature.

(3)	If the Contractor excavates or fills beyond the neat-line limit without the direction of the Engineer, only the neat-line limit shall be used.

b.	Topographic Method - Use this method to define all topographic surfaces. Each vertex of a triangle in the TIN shall be formed by a field measured data point, and shall be located by its (XYZ) coordinate. Develop the TIN surface by connecting Topographic Survey points to their nearest neighboring points (in XY), except as outlined below:

(1)	Break Lines – Create break lines by connecting Topographic Survey points that are identified by their appropriate break line descriptors. Break lines shall snap to vertices on adjacent break lines when two break lines intersect. Break lines shall not cross. Use break lines to establish the following features:

(a) 	Centerline of roadway.

(b)	Lane separations (for multiple lane roadways).

(c)	Edge of pavement.

(d)	Shoulder hinge points.

(e)	Bottom of ditch.

(f)	Ditch back slope catch point.

(g) 	For curb and gutter sections, break lines shall be collected at the flow line and back of curb.

(h)	Ridge lines.

(i)	Rim of pits or significant depressions.

(j) 	Areas of slope change or undulations in slope.

(k) 	Bottom of valleys or draws.

(l) 	Hydraulic features.

(m)	Around buildings and structures (including top and bottom of walls).

(2)	Boundaries – Boundaries break the TIN lines and define the edge of the surface. Use boundaries to trim all non-relevant edges from the DTM. Use either non-destructive or destructive trimming as necessary to preserve the accuracy of the DTM. Use boundaries to establish the following features:

(a)	Outer boundary of the DTM.

(b)	Edge of a void inside the surface.

(c)	Edge of an island inside of a void.

(3)	Surface Editing – Surface Editing allows changes that more accurately represent the actual terrain. Use surface editing to delete or swap edges of the triangulated network as necessary to best represent the actual site condition. Mathematically computed points for the purpose of surface smoothing may be used only if approved by the Engineer. The creation of contour lines for the purpose of DTM surface extraction is not acceptable.

c.	Combination Method - Use this method when the Engineer approves a change to the neat-line limit.

(1)	In areas where the Engineer approves a change to the neat-line limit, develop new surfaces using the Topographic Method.

(2)	Replace the neat-line surface with the new topographic surfaces to create an appropriate single surface.

642-3.08 CONTRACTOR FURNISHED COMPUTATIONS. Provide computations for volumetric Pay Items using DTM’s developed per Section 642-3.07. Cross sections developed from the appropriate DTM’s will be used as a supplementary quality control check on DTM parameters and quantities, and not for pay. The Contractor may use the Average End Area Method in accordance with Section 109, only if approved in writing by the Engineer.

1.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted cross sections from the DTM surfaces. Develop separate cross sections for each volumetric Pay Item. More than one Pay Item per plotted cross section is not allowed.

(1)	Plot every 50 ft on Station, including intermediate stations as required to define angle points, curves, or other significant changes in the roadway geometry.

(2) 	Show the elevation and offset information for all vertex points. Weeding vertex point labels is not allowed. Elevation and offset information may be shown on a separate report if the amount of information exceeds what can be legibly shown on the plot.

(3)	Show the area for each cross section.

(4)	Label each plot with the project name, project number, Pay Item number, and Pay Item name.

(5)	Label each plot with the Surveyor’s Company name and address.

b.	Plotted profiles from the DTM surfaces. Develop separate plots for each volumetric Pay Item. Each plot shall only identify the profiles appropriate to the volumetric Pay Item.

(1)	Plot the profile along the alignment centerline as shown in the plans.

(2)	Label each profile as original ground, bottom of excavation, and the top or bottom of embankment, as appropriate.

(3)	Label topographic profiles with elevation and station information, using a weeding frequency of every 100 ft, or as necessary to match the frequency shown on the plans.

(4)	Label the neat-line profiles with elevation and station information every 100 ft, and for the beginning, end, and VPI of all vertical curves and grade breaks. Label the percent slope between all grade breaks, to the fourth significant decimal.

(5)	Label each plot with the project name, project number, Pay Item number, and Pay Item name.

(6)	Label each plot with the Surveyor’s Company name and address.

c.	Electronic Data

(1)	Provide copies of all Topographic, Neat-line, and Combination surfaces to the Engineer. Include all electronic features (alignments, profiles, sections, etc.) used to generate the surfaces.

(2)	All data shall be delivered on a clearly labeled CD-ROM or DVD, unless specified otherwise by the Engineer. The label shall include the project name, project number, Surveyor’s company name, and date. All data becomes the property of the State of Alaska.

(3)	DTM files shall be saved in Autodesk, TIN, XML, or other approved formats compatible with Department software.

d.	Volume Reports

(1)	Provide interim volume reports showing quantities between every 50 ft station. The volume reports shall be summarized to allow the Department to reference the quantities per individual plan sheet, or as defined in any earthwork summary shown on the plan sheets.

(2)	Provide a final volume report reflecting the final total quantity. Attach all data, calculations, and plots to the report. The report shall be signed, sealed, and dated by the Surveyor. This report shall be used as the basis for final pay.

642-3.09 CONTRACTOR FURNISHED ENGINEERING TOOLS. Furnish and maintain Engineering Tools as directed by the Engineer, for the exclusive use of the Engineer throughout the duration of the project. The Contractor shall furnish all equipment specifications to the Engineer for approval, prior to furnishing equipment. The equipment shall be in good working condition not more than 1 model year old. The Contractor shall insure and indemnify the Department against normal wear and tear, damage, theft, and all other events that may cause a loss of function of the furnished tools. The equipment shall be returned to the Contractor upon completion of the project, or when services are terminated by the Engineer. Furnish training for the Engineer’s staff, as directed by the Engineer.

1.	GPS Rover Unit – All components shall be fully compatible to provide a stand-alone GPS Rover Unit. The Rover Unit shall be an “all on the pole” system equipped with the following:

a.	Receiver

(1)	Bluetooth compatible.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Dual frequency receiver capable of tracking at least twelve (12) satellites simultaneously on parallel channels.

(5)	Capable of RTK, Static, and Fast Static occupations.

(6)	Capable of receiving L1, L2, and GNSS frequencies.

(7)	Antenna model shall have undergone antenna calibration by the NGS.

(8)	Ensure the receiver contains the manufacturer’s latest firmware upgrades.

(9)	Provide the manufacturer’s user guide.

b.	Controller

(1)	Bluetooth compatible.

(2)	Equipped with onboard software allowing for the configuration of RTK, PPK, or Static rover modes.

(3)	Meet waterproof specification IPX7.

(4)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(5)	Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

(6)	Capable of collecting data in WGS84 and displaying local project coordinates.

(7)	Equipped with onboard software that allows automatic point logging.

(8)	Capable of creating and storing line-work in DFX or DWG format.

(9)	Equipped with onboard software to allow the user to stake-out points, 3D lines, and DTM surfaces. Software shall allow the user to read cut/fill elevations relative to a DTM surface.

(10) Capable of importing, exporting, and storing point, line, and DTM data.

(11) Capable of showing satellite, radio, and battery status.

(12) Equipped with onboard software that allow the user to create and manage survey jobs, point data, coordinate systems, and alignments.

(13) Equipped with a removable memory storage device with a minimum capacity of 512MB.

(14) Capable of storing custom configuration settings for the GPS Rover Unit.

(15) Ensure the controller contains the manufacturer’s latest firmware upgrades.

(16) Provide the manufacturer’s user guide.

c.	Radio System

(1)	Meet waterproof specification IPX7.

(2)	Support a frequency compatible with the Reference Station.

(3)	Capable of storing multiple radio frequencies.

(4)	Compatible with the Reference Station’s broadcasting format and protocol.

(5)	Power and programming cables.

(6)	Provide the manufacturer’s user guide.

d.	Batteries

(1)	Provide all batteries required to fully power and operate the GPS Rover Unit.

(2)	Batteries shall be capable of powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

(3)	Each battery shall be rechargeable and commercially available.

(4)	Provide an identical replacement backup battery for each primary battery required.

(5)	Provide all power connectors necessary to connect the batteries to the equipment.

(6)	Provide battery chargers to allow all onboard batteries to be charged simultaneously, and that safeguard against overcharging.

e.	Rod

(1)	Fixed height (non-adjustable).

(2)	Mounting hardware for GPS controller and radio.

(3)	Pole grip with bubble level.

(4)	Detachable bipod.

(5)	Interchangeable flat and pointed footings.

(6)	Quick release adapter for the GPS receiver.

f.	Carrying Case

(1)	Hard Shell.

(2)	Shockproof.

(3)	Waterproof.

(4)	Capacity to hold all components of the GPS rover, minus the rod.

2.	Continually Operating Reference Station – The location of the CORS shall not change for the duration of the project. The CORS shall be permanently mounted per NGS CORS standards. All structures, mounting hardware, power supply, computers, software, networking, and personnel required to support and operate the CORS is considered subsidiary to this item. Store CORS data for the duration of the project, and post online for use by the Engineer. The CORS shall include and conform to the following requirements:

a.	GPS Receiver

(1)	Choke-ring antenna, model shall have undergone antenna calibration by the NGS.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Able to operate in temperatures between -20º F to +140º F.

(5)	Capable of logging L1/L2 data continuously for 180 days, and storing at 1 second intervals. If onboard memory storage capacity is insufficient, backup all data on an external memory storage device.

(6)	Support multiple, simultaneous data logging sessions at different collection rates.

(7)	Equipped with a dual frequency receiver capable of tracking L1, L2, and GNSS frequencies on at least 12 satellites. Receiver shall have a minimum of 24 channels.

(8)	Support CMR/CMR+ and RTCM output simultaneously via separate ports.

(9)	Use multi-path mitigation techniques.

(10)	Satellite acquisition technology shall provide improved tracking in areas of high radio interference such as under power lines, around airports, near radio-intensive construction sites.

(11)	Capable of 1PPS output with an accuracy of 1usec.

(12)	Equipped with 1 primary and 1 secondary power input port.

(13)	The system shall automatically switch between power sources.

(14)	Equipped with over-voltage protection on all power inputs.

(15)	Capable of reporting Signal-to-Noise Ratio (SNR) values for L1 and L2.

(16)	Capable of logging data at operator selected intervals of 0.5, 1, 5, and 30 seconds.

(17)	Provide the manufacturer’s user guide.

b.	Radio

(1)	Transmission power, 25 watt minimum.

(2)	Meet waterproof specification IPX7.

(3)	Ensure the radio has a current license to broadcast in accordance with FCC requirements.

(4)	Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

(5)	Provide the manufacturer’s user guide.

c.	CORS Facility – Provide a facility to mount and house CORS station equipment.

(1)	Facility shall meet NGS CORS mounting requirements, and shall be approved by the Engineer.

(2)	Shall be physically located in a clear view of the sky, away from objects that may cause multi-path interference.

(3)	Location shall provide for maximum strength of geometry relative to the primary control network and the project limits.

(4)	Shall be connected to a primary power source, and a backup power source capable of providing uninterrupted backup power for a minimum of 48 hours.

3.	GPS Base/Repeater Station – All components shall be fully compatible to provide a stand-alone GPS Base/Repeater Station setup. The setup shall include the following:

a.	Receiver

(1)	Meet waterproof specification IPX7.

(2)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(3)	Dual frequency receiver capable of tracking at least 12 satellites simultaneously on parallel channels.

(4)	Antenna model shall have undergone antenna calibration by the NGS.

(5)	Ensure the receiver contains the manufacturer’s latest firmware upgrades.

(6)	Carrying case.

(7)	Tribrach with optical plummet and height rod.

(8)	Provide the manufacturer’s user guide.

b.	Controller

(1)	Equipped with onboard software allowing for configuration as a GPS reference station in RTK, PPK, Static, and Fast Static modes.

(2) 	Capable of logging raw observations for post processing.

(3)	Capable of showing satellite, radio, and battery status.

(4)	Meet waterproof specification IPX7.

(5)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(6)	Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

(7)	Equipped with a removable memory storage device with a minimum capacity of 512MB.

(8)	Equipped with 1 primary and 1 secondary power input port.

(9)	Ensure the controller contains the manufacturer’s latest firmware upgrades.

(10) Provide the manufacturer’s user guide.

c.	Radio

(1)	Transmission power, 25 watt minimum.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Support a frequency compatible with the Reference Station.

(5)	Capable of storing multiple radio frequencies.

(6)	Compatible with the CORS broadcasting format and protocol.

(7)	Ensure the radio has a current license to broadcast in accordance with FCC requirements.

(8)	Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

(9)	Equipped with onboard software/firmware allowing for configuration as either a Reference Station or a Repeater Station.

(10) Carrying case.

(11) Antenna.

(12) Antenna/pole mounting adapter.

(13) Provide the manufacturer’s user guide.

d.	Tripods – Provide one of each:

(1) Conventional tripod with extendible range pole. Include carrying case.

(2) Conventional wood tripod.

e.	Batteries

(1)	Provide all batteries required to fully power and operate the GPS Base/Repeater Station.

(2)	Batteries shall be capable powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

(3)	Each battery shall be rechargeable and commercially available.

(4)	Provide an identical replacement backup battery for each primary battery required.

(5) 	Provide all power connectors necessary to connect the batteries to the equipment.

(6)	Provide battery chargers to allow all batteries to be properly charged, and that safeguard against overcharging.

4.	Computer Hardware – Hardware shall meet the following minimum requirements:

a.	Laptop Computer

(1)	2.8 GHz multi-core CPU.

(2)	120GB Internal Hard Drive.

(3)	4 GB System RAM.

(4)	Display 13” with 1,600 x 1,200 resolution.

(5)	512MB video memory.

(6)	DVD Burner Drive.

(7)	Internal Bluetooth and Wi-fi.

(8)	Internal Battery.

(9)	120v AC Adapter.

(10) 12v DC Adapter.

(11) Built-in CF, SD, and PCMCIA card ports.

(12) 4 USB 2.0 ports.

(13) 1394 (firewire) port.

(14) Mouse (wireless).

(15) Travel Case (hard) for laptop and accessories.

b.	Laptop Computer Mount

(1)	Permanently installed in a vehicle, as directed by the Engineer.

(2)	Fastened to the passenger side of the vehicle.

(3)	Shock and vibration resistant.

(4)	Fully adjustable positioning with mechanically locking hinge points.

c.	Desktop Computer

(1)	3 GHz multi-core CPU

(2)	120GB Internal Hard Drive

(3)	4 GB System RAM

(4)	Compatible DVI 19” monitor with 1,600 x 1,200 resolution

(5)	Internal video card/chip, 512MB, 2 DVI ports

(6)	Internal DVD Burner Drive

(7)	CF and SD media card reader

(8)	6 USB ports

(9)	1394 (firewire) port

(10) Internal wireless (IEEE 802.11 b/g) network card

(11) Internal Ethernet card (10/100 Mbps).

(12) Uninterruptible Power Source (UPS), 8 outlets, 390 Watt

(13) 250 GB Backup Hard Drive (external)

(14) Mouse and Keyboard

d.	Laser Printer

(1)	45 pages per minute print speed.

(2)	1200 x 1200 dpi print quality.

(3)	Main tray capacity shall hold no less than 500, 8.5 x 11 inch sheets.

(4)	Multipurpose tray capable of custom sizes up to 11 x 17 inch sheets.

(5)	128 MB of onboard memory, minimum.

5.	Computer Software – All software shall be licensed and fully operational. Provide software that is similar or approved equal in accordance with the following:

a.	Operating System Software – Provide an operating system that supports the drivers of all onboard and auxiliary computer hardware systems. The operating system shall be of the latest release, with the most current updates installed. The operating system shall support all of the applications listed below.

b.	CAD Software – Provide CAD software that is capable of dynamically associating and updating alignment, profile, section, grading, point, and surface data. The software shall be capable of saving all data to formats that are compatible with the latest release of CAD software currently used by the Department. Formatting shall preserve the dynamic relationship of all DTM features. Software that doesn’t dynamically associate all DTM features is not acceptable.

c.	Word Processing Software – Provide software that is compatible with the latest release of word processing software currently used by the Department.

d.	Spreadsheet Processing Software – Provide software that is compatible with the latest release of spreadsheet processing software currently used by the Department.

e.	Anti-Virus Software – Provide software to protect against viruses and other security threats. Software shall be equipped with a firewall containing industry standards of system protection. The software shall be capable of backing up all hard drive data.

f.	GPS Processing Software – Provide GPS processing software of the latest release and from the same vendor as the GPS equipment furnished. Include all necessary hardware/software keys to enable L1 & L2 Static, PPK, and RTK processing, GNSS processing, network adjustments, datum and map transformations, and RINEX data importing and exporting.

CFHWY00308

642-4.01 METHOD OF MEASUREMENT.

Add the following:

Pay item 642.2005.____ Contractor Furnished Computations.  Prior to beginning work, develop a Lump Sum Agreement that itemizes all plan sheets labeled “Plan and Profile” (or similar) by percentage. Work will be measured by the percent completion of all computations required, per plan sheet defined in the Lump Sum Agreement.

Pay item 642.2006.____ Contractor Furnished Engineering Tools. Contingent sum work will be measured in accordance with the directive authorizing the work.

CFHWY00308

Pay Item 642.2008.____ Passing Sight Distance Measurement.  By the number of stations of the project measured separately along centerline, once for each direction, only after the certified and recorded results (642-3.01 12a & 12b) have been accepted by the Engineer.

CR642.2-072215R

642-5.01 BASIS OF PAYMENT.

Add the following:

Pay item 642.2005.____ Contractor Furnished Computations. This item includes all work required to develop and furnish quantity computations in accordance with methods required by the contract. Earthwork computations, digital terrain model development, plotted cross sections, quantity reports, and associated topographic surveying are subsidiary to this item. The Engineer may withhold payment for this item if the minimum specifications are not met. 10% of the contract lump sum bid price will be withheld until final computations are accepted by the Engineer. If the Contractor excavates or fills beyond the neat-line limit without the direction of the Engineer, the calculated volume shall only extend to the neat-line limit.

Pay item 642.2006.____ Contractor Furnished Engineering Tools. The Engineer shall issue a directive defining and authorizing the work. Payment for a GPS Rover, Base/Repeater Station, CORS, or Computer System will be made on a time and materials basis in accordance with Subsection 109-1.05-3e, Leased or Rented Equipment. Payment for training will be made on a time and materials basis in accordance with Section 109-1.05. If the training is beyond the Contractor’s ability or expertise, payment will be made in accordance with Subsection 109-1.05-4, Work by a Specialty Subcontractor. The Engineer may withhold payment for this item if the minimum specifications are not met. The Engineer may issue a directive at any time to terminate or re-authorize the work, at no additional cost to the Department.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 642.2005.____ | Contractor Furnished Computations | LS |
| 642.2006.____ | Contractor Furnished Engineering Tools | CS |
| 642.2008.____ | Passing Sight Distance Measurement | STA |

CFHWY00308

Existing Striping, Passing Sight Distance and Final Striping

Project Name and Number:  Example Project Striping, X-(XX)/XXXXX

Road Name:  Traveled Way

Stationing:  From   101+00	  To   129+00

Surveyor & License Number:   Name, License #	  Date of Survey:  	mmddyy

| 1. Station (ft.) | 2. Speed/ Req'd Dist. (mph/ft) | SB Travel |  |  | NB Travel |  |  | SB Travel |  | NB Travel |  | 6. Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 3. Sight Dist. (ft) | Existing |  | Striping |  | 4. Sight Dist. (ft) | 5. Final |  | Striping |  |  |
|  |  |  | 3a. | C | L | 4a. |  | 5a. | C | L | 5b. |  |
| 101+00 | 45/700 | >500 F |  |  |  |  | >500 F |  |  |  |  |  |
| 102+00 | 45/700 | >550 F |  |  |  |  | >400 F |  |  |  |  |  |
| 103+00 | 45/700 | >600 F |  |  |  |  | >400 F |  |  |  |  |  |
| 104+00 | 45/700 | >600 F |  |  |  |  | >400 F |  |  |  |  |  |
| 105+00 |  | >600 F |  |  |  |  | >400 F |  |  |  |  |  |
| 106+00 |  | >500 F |  |  |  |  | >500 F |  |  |  |  |  |
| 107+00 |  | >400 F |  |  |  |  | >500 F |  |  |  |  |  |
| 108+00 |  | >400 F |  |  |  |  | >600 F |  |  |  |  |  |
| 109+00 |  | >400 F |  |  |  |  | >550 F |  |  |  |  |  |
| 110+00 |  | >500 F |  |  |  |  | >500 F |  |  |  |  |  |
| 111+00 | 45/ 700 | >500 F |  |  |  |  | =700 P |  |  |  |  |  |
| 112+00 |  | =700 P |  |  |  |  | =700 P |  |  |  |  |  |
| 113+00 |  | =700 P |  |  |  |  | <800 P |  |  |  |  |  |
| 114+00 |  | <800 P |  |  |  |  | <800 P |  |  |  |  |  |
| 115+00 |  | <800 P |  |  |  |  | <800 P |  |  |  |  |  |
| 116+00 |  | <800 P |  |  |  |  | <900 P |  |  |  |  |  |
| 117+00 |  | <900 P |  |  |  |  | <900 P |  |  |  |  |  |
| 118+00 |  | <1200 P |  |  |  |  | <1000 P |  |  |  |  |  |
| 119+00 |  | <1200+ P |  |  |  |  | <1000 P |  |  |  |  |  |
| 120+00 | 45/700 | " |  |  |  |  | <1000 P |  |  |  |  |  |
| 121+00 | 30/500 | " |  |  |  |  | <1000 P |  |  |  |  |  |
| 122+00 | 30/500 | " |  |  |  |  | <1200 P |  |  |  |  |  |
| 123+00 | 30/500 | " |  |  |  |  | <1200+ P |  |  |  |  |  |
| 124+00 | 30/500 | " |  |  |  |  | " |  |  |  |  |  |
| 125+00 | 30/500 | " |  |  |  |  | " |  |  |  |  |  |
| 126+00 | 30/500 | " |  |  |  |  | " |  |  |  |  |  |
| 127+00 | 30/500 | " |  |  |  |  | " |  |  |  |  |  |
| 128+00 | 60/900 | " |  |  |  |  | " |  |  |  |  |  |
| 129+00 | 60/900 | <1200+ P |  |  |  |  | <1200+ P |  |  |  |  |  |

Existing Striping, Passing Sight Distance and Final Striping

Project Name and Number:

Road Name:

Stationing:  From  	  To

Surveyor & License Number:  	  Date of Survey:

| 1. Station (ft.) | 2. Speed/ Req'd Dist. (mph/ft) | Travel |  |  | Travel |  |  | Travel |  | Travel |  | 6. Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 3. Sight Dist. | Existing |  | Striping |  | 4. Sight Dist. | 5. Final |  | Striping |  |  |
|  |  |  | 3a. | C | L | 4a. |  | 5a. | C | L | 5b. |  |

CR642.2-072215R

Existing Striping 12a. – Date Received:

Date Returned:

DOT/PF Engineer

Sight Distance 12b. – Date Received:

Date Returned:

DOT/PF Engineer

Final Striping 12c. – Date Received:

Date Returned:

DOT/PF Engineer

CR642.2-072215R

Special Provisions

Replace Section 643 with the following:

SECTION 643
TRAFFIC MAINTENANCE

43-1.01 DESCRIPTION. Protect and control traffic during the contract. Furnish, erect, maintain, replace, clean, move, and remove the traffic control devices required to ensure the traveling public’s safety. Perform all administrative responsibilities necessary to implement this work.

Maintain all roadways and pedestrian and bicycle facilities affected by the work in a smooth and traversable condition. Construct and maintain approaches, crossings, intersections, and other necessary features throughout the project for the life of the contract.

Illuminate construction activities listed in Table 643-4 during hours of night work on roads open to the public within project limits.

643-1.02 DEFINITIONS. These definitions apply only to Section 643.

ATM. When used in this Section, ATM stands for the Alaska Traffic Manual, which is comprised of the Manual on Uniform Traffic Control Devices (MUTCD), the Alaska Traffic Manual Supplement, any adopted revisions or interim addenda to either document issued subsequently, and corrections to known errors to either document.

Balloon Light.  Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.

Construction Phasing Plan. A plan for each phase of the project showing how to accommodate traffic. Show the sequence of work by segment or phase, if required.

Fixed Objects. Private vehicles, parked flagger vehicles, idle construction equipment, construction material stockpiles, culvert ends, individual trees, power poles, utility poles and appurtenances, and other items deemed by the Engineer to present a hazard to motorists, pedestrians, or bicyclists traveling through the work zone.

Night Work. Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in the Table 643-1 below:

TABLE 643-1

PROJECT LOCATIONS – NIGHT TIME ILLUMINATION EXCLUSION

| Latitude | No Lighting Required |  | Nearby |
| --- | --- | --- | --- |
| (degrees) | Start | End | Cities |
| South of 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Tok, Delta, Nome |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle City |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

Traffic. The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, or similar operations.

Traffic Control Plan (TCP). A drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. The TCP depicts the traffic control devices and their placement and times of use.

Traffic Control Zone. A portion of a road construction project, maintenance operation, utility work or similar operation that affects traffic and requires traffic control to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. Implement an approved TCP before beginning work within the project limits.

The TCP includes, but is not limited to, signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary lighting, temporary roadways and all other items required to direct traffic through or around the traffic control zone according to these Specifications and the ATM. Address in the TCPs placement of traffic control devices, including location, spacing, size, mounting height and type. Include code designation, size, and legend per the ATM and the Alaska Sign Design Specification (ASDS). Include longitudinal buffer space for the posted speed limit, according to Table 6C-2 of the ATM unless project conditions or geometric features prohibit including all or a portion of the buffer length.

When a TCP is included in the Plans, use it, modify it, or design an alternative TCP. When a TCP is omitted from the Plans, provide one according to this Section and the ATM.

Submit new or modified TCPs to the Engineer for approval. All TCPs must include the following information:

1.	Project name and number.

2.	A designated TCP number and name on each page.

3.	For TCPs more than one page, each page must be numbered.

4.	The posted speed limit for each roadway.

5.	Existing striping width, lane width, and road surfacing.

6.	Construction lane widths, striping layout, and temporary pavement marker layout.

7.	Provisions for Pedestrian, Bicycle, and ADA travel through the work zone.

8.	Dates and times the TCP will be in effect and why it is being used.

9.	The Worksite Traffic Supervisor’s signature certifying that all TCPs conform to the ATM and the Contract.

10.	The Project Superintendent’s signature confirming the TCP is compatible with the work plan.

11.	The name(s) of the Worksite Traffic Supervisor, his/her alternate and their 24-hour telephone number(s).

12.	Signs to be used and the ASDS designation number and size.

13.	Location and spacing of all devices and signs.

14.	A plan to address any possible slopes, drop offs, paving joints, or similar temporary features that may occur during use of the TCP.

15.	For TCPs proposed to be used at night, note how the requirements will be met for the required lighting and retroreflective material.

TCPs submitted for approval without all the required information will be rejected. Allow 7 days for review of each TCP submittal. All required modifications to a TCP require a new submission and an additional 7 days for review.

A minor revision to a previously approved TCP during construction requires 48 hours for review and approval by the Engineer.

The TCPs, Plans, and Alaska Standard Plans show the minimum required number of traffic control devices. If unsafe conditions occur, the Engineer may require additional traffic control devices.

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12-foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

Road Closures and Major Traffic Sequencing (events).  Submit a written request to the Engineer for review and approval of each proposed event and event date.  Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections.  The proposed event date will be no less than 14 days from the date of written approval.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. Provide a Worksite Traffic Supervisor responsible for maintaining 24-hour traffic operations.

1.	Qualifications. The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements. The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, proposed operations, and certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Temporary Traffic Control Technician, or Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor has a minimum 4000 hours of temporary traffic control work experience, is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this section.

	Temporary traffic control work experience shall demonstrate an understanding of concepts, techniques, and practices in the installation and maintenance of traffic control devices, and skill in reading, interpreting, implementing, and modifying TCPs.

	Temporary traffic control work experience includes: flagging; installing traffic control devices in accordance with TCPs; monitoring traffic control devices and TCP performance; and recognizing and reporting deficiencies in traffic control devices and TCPs for correction.

	Temporary traffic control work experience is gained while serving as a Worksite Traffic Supervisor-in-training, temporary traffic control support personnel, and Flagger.

	Four thousand hours of experience serving solely as a Flagger does not satisfy these requirements.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

2.	Duties.

a.	Prepare the TCPs and public notices and coordinate traffic control operations between the Project Superintendent and the Engineer.

b.	Physically inspect the condition and position of all traffic control devices used on the project at least twice each day and at approximately 12-hour intervals.  Ensure that traffic control devices work properly, are clean and visible, and conform to the approved TCP.  Complete and sign a detailed written report of each inspection within 24 hours.  Use Traffic Control Daily Review Form 25D-104.

c.	Supervise the repair or replacement of damaged or missing traffic control devices.

d.	Review and anticipate traffic control needs. Make available proper traffic control devices necessary for safe and efficient traffic movement.

e.	Review work areas, equipment storage, and traffic-safety material handling and storage.

f.	Hold traffic safety meetings with superintendents, foremen, subcontractors, and others as appropriate before beginning construction, prior to implementing a new TCP, and as directed. Invite the Engineer to these meetings.

g.	Supervise all traffic control workers, flaggers, and pilot car drivers.

h.	Certify that all flaggers are certified as required by Subsection 643-3.04.4.  Submit a copy of all flagger certifications to the Engineer.

i	Supervise lighting for night work.

3.	Authority. The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-1.05 CONSTRUCTION PHASING PLAN. Submit a Construction Phasing Plan for approval no less than 5 working days prior to the preconstruction conference. Include the following:

1.	Form 25D-124 designating the Worksite Traffic Supervisor, providing the 24-hour telephone number, and certifying minimum 4,000 hours of work experience as described in 643-1.04 Worksite Traffic Supervisor.

2.	A construction-phasing plan for each phase or segment of the project.

3.	TCPs for the first phase of the project. Show permanent and temporary traffic control measures, including the times each TCP will be used.

Submit any changes to the Engineer for approval 7 days before proposed implementation.

643-1.06 TRAFFIC MAINTENANCE SETUP. When shown on the bid schedule, Traffic Maintenance Setup items are site specific and are detailed as individual TCPs on the plan sheets. They depict the method or scheme required to route traffic safely and efficiently when any of the following restrictions occur:

1.	Lane Closure. The closure of one or more lanes on a roadway.

2.	Detour. The redirection of traffic through or around a traffic control zone.

3.	Road Closure. The closure of a roadway with or without a specified detour route.

4.	One Lane Road. A two-way roadway reduced to a single-lane roadway with flaggers, pilot cars, traffic signals, stop signs, or yield signs.

643-2.01 MATERIALS. Provide traffic control devices meeting the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM, and ASDS.

a.	Construction Signs: Regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Neatly mark the size of each sign on its back in 3-inch black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 48 X 48 inch traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 8 feet long. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Contract. For each direction of traffic, equip each 12.5-foot section of barrier with at least two side-mounted retroreflective tabs placed approximately 6 to 8 feet apart, or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier. Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 28 inches high. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint meeting Subsection 708-2.03 with glass beads meeting Subsection 712-2.08,

b.	Preformed Marking Tape (removable or non-removable) meeting Subsection 712-2.14, or

c.	Temporary Raised Pavement Markers meeting Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V. Application of crash cushion must be appropriate for the intended use and be installed per manufacturer’s recommendation. Temporary crash cushions used as rail or barrier end treatments must be redirective. Temporary crash cushions that are barrels or barricade filled with sand or water may only be used when the forecasted temperature during their use is above 32 degrees Fahrenheit.

11.	Sequential Arrow Panels. Use Type A (24 X 48 inch), Type B (30 X 60 inch) or Type C (48 X 96 inch) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs.  Use new truck or trailer mounted portable changeable message board signs with self-contained power supply for the sign and with:

a.	Message sign panel large enough to display 3 lines of 18-inch high characters

b.	Eight character display per message module

c.	Fully programmable message module

d.	Remote control cellular, wireless radio frequency (RF), landline

e.	Waterproof, lockable cover for the controller keyboard

f.	Capacity for electric/hydraulic sign raising or lowering

g.	Radar over speed detection

h.	Variable flash and sequence rates

i.	Light emitting diode (LED) display, using Institute of Transportation Engineers (ITE) amber/yellow

j.	The capacity for a minimum of 150 pre-programmed messages

k.	Battery-Pack Operation Duration:  minimum of 55 hours under full load

l.	Power chords shall comply with the National Electrical Code (NEC) Article 600.10 Portable or Mobile Signs, paragraphs 600.10(C)(1) Cords and 600.10(C)(2) Ground-Fault Circuit Interrupter (GFCI). The cord will have integral GFCI protection located in either the attachment plug or 12 inches or less from the plug.

13.	Plastic Safety Fence. Use 4-foot high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	"Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306.  Phone (800) 428-8185.

b.	"Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108.  Phone (800) 648-7916.

c.	"Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104.  Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 1/2-inch thick for areas continuously supported by subgrade. Use plywood at least 1 inch thick for areas that are not continuously supported.

b.	Do not use unsupported 1-inch plywood longer than 30 inches.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 1/2-inch. Bevel overlap joints so the maximum slope of the overlapping edge is 2 horizontal to 1 vertical.

d.	Fasten so wind and traffic will not displace temporary surfacing.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

16.	Flagger Paddles. Use flagger paddles with 24 inches wide by 24 inches high sign panels, 8 inch Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM.  Use retroreflective sheeting that meets ASTM D4956 Type VIII, IX or XI. Use background colors of fluorescent orange on one side and red on the other side.

17.	Truck Mounted Attenuator, TMA. The TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight per the manufacturer’s recommendations.

18.	Portable Steel Barriers. Use portable steel barriers that conform to the contract.  For each direction of traffic, equip each section of barrier with side-mounted retroreflective tabs placed approximately 6 to 8 feet apart,   or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier.    Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV, or V.

19.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

643-2.02 Crashworthiness. Temporary Work Zone devices, including portable barriers, manufactured after December 31, 2019, must have been successfully tested to the 2016 edition of Manual for Assessing Safety Hardware (MASH). Such devices manufactured on or before this date, and successfully tested to National Cooperative Highway Research Program (NCHRP) Report 350 or the 2009 edition of MASH, may continue to be used throughout their normal service lives.

Submit documentation, by the method indicated on table 643-2, that the following devices comply with Test Level 3 requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or the Manual for Assessing Safety Hardware (MASH). Submit documentation of compliance to the Engineer before installing devices on the project.

TABLE 643-2

WORK ZONE TRAFFIC CONTROL DEVICE AND

BARRIER CRASH TESTING COMPLIANCE

| Category | Devices | Devices Manufactured Before Dec. 31, 20191 | Devices Manufactured after Dec. 31, 20191 | Method of Documentation |
| --- | --- | --- | --- | --- |
| 1 | Low-mass single-piece devices w/o attachments; traffic cones, tubular markers, single piece drums, delineators | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | Manufacturer's Certification for devices exceeding height and weight limits |
| 2 | Category 1 devices with attachments, barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in Category 1 | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, if available, at Test Level 32, or DOT&PF eligibility determination |
| 3 | Fixed sign supports, truck mounted attenuators, temporary crash cushions, bridge railing, bridge and guardrail transitions, and guardrail and barrier end treatments. | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, if available, at Test Level 32, or DOT&PF eligibility determination |
|  | Portable Concrete and steel barriers | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, if available, at Test Level 3, or DOT&PF eligibility determination, unless otherwise required in the Contract |

1	The Engineer will determine whether a device is in serviceable condition. Serviceable means the device will function equivalent to a new device of the same manufacture.

2	When no test level is specified in a FHWA Eligibility letter; it is implied that the tests were run for Test Level 3.

In Table 643-2, Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3. This certification may be a one-page affidavit signed by the vendor. Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization. No certification is required for devices less than or equal to both the weight and height on the schedule below:

Device	Composition	Weight	Height

Cones	Rubber		20 lb.	36 in.

Plastic		20 lb.	48 in.

Candles	Rubber		13 lb.	36 in.

Plastic 		13 lb.	36 in.

Drums	Hi Density Plastic		77 lb.	36 in.

Low Density Plastic	77 lb.	36 in.

Delineators	Plastic or Fiberglass	N/A	48 in.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Keep the work, and portions of the project affected by the work, in good condition to accommodate traffic safely. Provide and maintain traffic control devices and services inside and outside the project limits, day and night, to guide traffic safely.

Unless otherwise provided in this Section, keep all roadways, business accesses, recreational facilities, and pedestrian facilities within the project limits open to traffic. Obtain the Engineer’s approval before temporarily closing residential, commercial, or street approaches. Provide access through the project for emergency vehicles and school and transit buses. Properly sign and/or flag all locations where the traveling public is redirected or stopped.

Organize construction operations so the total of all construction related stoppages experienced by a vehicle traveling through the project does not exceed 20 minutes except when indicated otherwise in the Contract.

Stop equipment at all points of intersection with the traveling public unless an approved TCP shows otherwise.

Continue to operate all illumination and signalization according to the requirements of Subsection 660-3.09. When moving approach lanes, realign signal heads as necessary according to the ATM. Coordinate any modifications to existing traffic signals with the agency that maintains and operates them. Operate flood lighting at night according to the ATM. Adjust flood lighting so that it does not shine into oncoming traffic.

Provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times, except when regulations prohibit pedestrians or bicyclists. Station a flagger, where construction activity encroaches onto the safe route in a traffic control zone, to assist pedestrians, and bicyclists past the construction activity.

Maintain business access(s) during flagging operations.

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as an employee or a subcontractor becomes aware of the accident.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Obtain an approved TCP before reducing existing roadway lane and shoulder widths and before starting construction. Maintain a clear area with at least 2 feet between the edge of traveled way and the work area. Use barricades, traffic cones, or drums to delineate this area. Place traffic control devices on the work side of the clear area. Space them according to the ATM.

Where specified in the Plans, Specifications, Special Provisions, and or the TCP:  traffic may be maintained on a continuous gravel surface.

1.	Specified Gravel Surface.  Traffic may be maintained on a continuous gravel surface where specified:

a.	N/A Highway:  N/A weeks.

b.	BOP to Station N/A: No time restriction.

c.	Station N/A to Station N/A (or EOP).

d.	Other project roadways:  N/A, no time restriction.

2.	Gravel Surface Not Specified.

a.	Through traffic shall not traverse more than two gravel sections of roadway in any given period.

b.	Pavement Break(s) for Culvert or Utility Work:  Patch pavement breaks(s), with hot mix asphalt, not more than 48 hours after removing the existing pavement.

c.	When approved by the Engineer.

3.	Foamed Asphalt Process.

a. 	Asphalt Foaming may not occur on two or more sections of the roadway at the same time.  A section of roadway to be foamed may be a maximum of 10,000 feet in length by the full roadway width, and left unpaved for no more than 7 days after removing the existing pavement.

If maintaining traffic on an unpaved surface, provide a smooth and even surface that public traffic can use at all times. Properly crown the roadbed surface for drainage. Before beginning other grading operations, place sufficient fill at culverts and bridges to permit traffic to cross smoothly and unimpeded. Use part-width construction techniques when routing traffic through roadway cuts or over embankments under construction. Excavate the material or place it in layers. Alternate the construction activities from one side to the other. Route the traffic over the side opposite the one under construction.

Detour traffic when the Plans or an approved TCP allows. Maintain detour routes so that traffic can proceed safely. When detours are no longer required, obliterate the detour. Topsoil and seed appropriate areas.

If two-way traffic cannot be maintained on the existing roadway or detour, use half-width construction or a road closure if it is shown on an approved TCP. Make sure the TCP indicates closure duration and conditions. Schedule the roadway closures to avoid delaying school buses, and peak-hour traffic. For road closures, post closure-start and road-reopen times at the closure site, within view of waiting traffic.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.

643-3.03 PUBLIC NOTICE. Give notice at least 14 days before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

	Alaska Trucking Association

	Alaska State Troopers

	Division of Measurement Standards

	Local Police Department

	Local Fire Department

	Local Government Traffic Engineer

	School and Transit Authorities

	Local Emergency Medical Services

	Local Media (newspapers, radio, television)

	Railroads (where applicable)

	U.S. Postal Service

	Major Tour Operators

- Whittier Tunnel

Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system. Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. These telephone numbers are used to alert construction employees when emergency vehicles must pass through the project. When notified of emergencies make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator or 511 System for selected projects. Check the special provisions for those requirements.

643-3.04 TRAFFIC CONTROL DEVICES. Before starting construction, erect permanent and temporary traffic control devices required by the approved TCPs. The Engineer will determine advisory speeds when necessary.

For lane closures on multilane roadways, use sequential arrow panels. During hours of darkness when required by the approved TCP, use flashing warning lights to mark obstructions or hazards and steady-burn lights for channelization.

Use only one type of traffic control device in a continuous line of delineating devices, unless otherwise noted on an approved TCP. Use drums or Type II barricades for lane drop tapers.

During non-working hours and after completing a particular construction operation, remove all unnecessary traffic control devices. Store all unused traffic control devices in a designated storage area which does not present a nuisance or visual distraction to traffic. If sign panels are post mounted and cannot be readily removed, cover them entirely with either metal or plywood sheeting. Completely cover signal heads with durable material that that fully blocks the view of signal head and will not be damaged or removed by weather.

Keep signs, drums, barricades, and other devices clean at all times.

Use only traffic control devices that meet the requirements of the “Acceptable” category in ATSSA (American Traffic Safety Services Association) “Quality Guidelines for Temporary Traffic Control Devices” and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project. Stock repair parts for each Temporary Crash Cushion used on the project. Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware. All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the plans, specifications, and approved TCPs until permanent roadside safety hardware is installed. All temporary roadside safety hardware shall meet crashworthiness requirements of Subsection 643-2.02.

All items paid under this Section remain the property of the Contractor, unless noted otherwise in the contract. Remove them after completing the project.

1.	Embankments.  Close trenches and excavations at the end of each continuous work shift, except as indicated by the Engineer.

Install portable concrete or steel barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as specified on the Plans or TCPs to delineate open trenches, ditches, other excavations, and hazardous areas when they exist along the roadway for more than one continuous work shift.

2.	Adjacent Travel Lane Paving. When paving lifts are 2 inches or greater and you cannot finish paving adjacent travel lanes or paved shoulders to the same elevation before the end of the paving shift, install: W8-11 (Uneven Lanes), W8-9 (Low Shoulder), W8-17 (Shoulder Drop-Off), W14-3 (No Passing Zone), R4-1 (Do Not Pass), R4-2 (Pass with Care), and W8-1 (Bump) signs as appropriate. Place additional signs every 1500 feet if the section is longer than 1/2 mile.

3.	Fixed Objects, Construction Vehicles and Equipment Working On or Next to the Traveled Way.  Do not park equipment in medians.  Locate fixed objects at least 30 feet from the edge of traveled way. Fixed objects that exist prior to construction activity are not subject to this requirement unless the proposed temporary traffic routing moves the edge of traveled way closer to the pre-existing fixed object.  Vehicles and other objects within parking lots in urban environments are considered preexisting fixed objects regardless of whether they are or are not present continuously throughout the day.

When worksite restrictions, land features, right of way limitations, environmental restrictions, construction phasing, or other construction conditions allow no practicable location meeting the preceding requirements, the Engineer may approve alternate locations for fixed objects. Alternate locations shall be as far as practicable from the edge of traveled way. When the alternate location provides 15 feet or more separation from the edge of traveled way, the Engineer may verbally approve the alternate location. When the alternate location provides less than 15 feet separation, written approval is required.

When the Engineer determines a fixed object or fixed objects present unacceptable hazard, use drums, or Type II barricades with flashing warning lights, or use portable concrete or steel barriers, or temporary crash cushion to delineate or shield the hazard, as approved by the Engineer.

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

4.	Flagging. Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone. The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

a.	Flagging Level I Certification by IMSA

b.	Flagger Certification by ATSSA

c.	Traffic Control Supervisor, ATSSA

d.	Work Zone Safety Specialist, IMSA

- ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification.  Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned flagging location at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements. Remove, fully cover, or lay down flagger signs when no flagger is present. Keep the flaggers’ area free of encumbrances.  Keep the flagger’s vehicle well off the roadway and away from the flagging location so the flagger can be easily seen.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer’s written approval before flagging signalized intersections. When flagging a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode. Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer. Get their written approval in advance. Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

5.	Pilot Cars. You may use pilot cars when part of an approved TCP, if the Engineer determines one-way traffic is necessary, or if the route through the traffic control zone is particularly hazardous, involved, or frequently altered to preclude adequate signing,  Do not use pilot cars to avoid localized traffic control at several locations.  Pilot car operators may not control Automated Flagger Assistance Devices while operating a pilot car.

Organize construction operations so the total of all stoppages experienced by a vehicle traveling through a project does not exceed 20 minutes. However, this does not imply that you may allow 20 minutes in all cases. Coordinate multiple pilot-car operations within a project or adjoining projects to minimize inconvenience to the traveling public. Two or more pilot cars may be used to provide two-way traffic through the traffic control zone to reduce the waiting period. The flagger or pilot car operator must record each pilot car’s departure time in a bound field book furnished by the Engineer. Whenever practical, the flagger should tell the motorist the reason for and approximate length of the delay. Make every reasonable effort to yield right-of-way to the public and prevent excessive delay.

Use an automobile or pickup as the pilot car, with the company logo prominently displayed. Equip the pilot car with a two-way radio for contact with flaggers and other pilot cars. Mount a G20-4 sign (Pilot Car Follow Me) on the rear at least 5 feet above the driving surface. Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on all Pilot Cars. Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.  Identify the last vehicle in the column.

When pilot car operations are approved, establish all required pilot car traffic control devices before beginning work.  Continue pilot car operations until no longer necessary and an approved TCP is in place for operations without pilot car, including all required traffic control devices.

6.	Street Sweeping and Power Brooming. Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material.  Use equipment for brooming and sweeping as recommended by the manufacturer and the following:

Dirt, dust and construction materials, mobilized as a result of power brooming and or sweeping, shall not be pushed, ejected, thrown or drift beyond the lesser of, 2 feet from the equipment perimeter or the edge of the paved surface.

All equipment shall operate to typical industry standards.  Maintain equipment to operate as designed by the manufacturer.  Equipment will employ safety equipment, warning lights, and other as required by the Specifications and these Special Provisions.

Sweeper and Broom Options:  Table 643-5, Traffic Control Rate Schedule, Street Sweeping

a.	Regenerative Sweeper:  Sweeper that blows a stream of air at the paved surface, causing fine particles to rise, and then caught through a vacuum system.

b.	Vacuum Sweeper:  Sweeper that creates a vacuum at the paved, surface sucking dirt, dust, and debris into a collection system.

c.	Mechanical Broom Sweeper:  Sweeper designed to pick up and collect larger size road debris, stones and litter, etc.  In addition to the requirements noted in these Specifications, use of a mechanical broom sweeper requires the Engineer to approve the sweeper for the intended use.

d.	Power Broom:  Power brooming that wets, pushes and or ejects loose material directly into an attached collection/pickup container may be used when approved by the Engineer.  The added moisture will be contained to the paved roadway surface.

Dry Power Brooming is not permitted.  Power brooming without direct/immediate means of collection/pickup is not permitted.

7.	Watering. Furnish, haul, and place water for dust control and pavement flushing, as directed. Use water trucks that can provide a high-pressure water stream to flush the pavement and a light-water spray to control dust. If the flushing operations contaminate or fill adjacent catch basins, clean and restore them to their original condition. This requirement includes sections of roadway off the project where flushing is required. The Engineer will control water application.

Obtain an Alaska Department of Natural Resources permit for water removal before taking water from a lake, stream, or other natural water body. Comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

8.	Portable Changeable Message Board Signs. Furnish Changeable Message Signs when approved on a TCP. Display only messages approved on the TCP. Follow application guidelines in the ATM.

9.	Truck Mounted Attenuator (TMA). TMAs are mounted on the rear of work vehicles. Impact attenuators shall meet crashworthiness requirements of 643-2.02. TMAs shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight in accordance with the manufacturer’s recommendations. TMAs shall have an adjustable height so that it can be placed at the correct elevation during usage and to a safe height for transporting. Approach ends of TMAs shall have impact attenuator markings in accordance with the ATM. Do not use a damaged attenuator in the work. Replace any damaged TMA at your expense.

10.	Traffic Control Vehicles.  Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on the Work Zone Supervisor’s vehicle and on vehicles being used to transport and set-up traffic control devices.  Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.

643-3.05 AUTHORITY OF THE ENGINEER.  When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice, and then a written notice according to Subsection 105-1.01, Authority of the Engineer. The notice will state the defect(s), the corrective action(s) required, and the time required to complete the corrective action(s). In no case shall this time exceed 24 hours.  If corrective action(s) are not completed within the specified time, the Engineer may immediately suspend work on the offending operations until the defect(s) are corrected. The Engineer may require outside forces to correct unsafe conditions. The cost of work by outside forces will be deducted from any monies due under the terms of this Contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. A Traffic Price Adjustment, under Item 643.0023.____, will be assessed for unauthorized lane closures or reductions. Unauthorized lane reductions will be assessed as one full lane closure, for each lane reduced without authorization.

Authorized lane closures and/or lane reductions are those shown in the Contract, an approved TCP, or authorized in writing.

Unauthorized lane reductions include unacceptable roadway, pedestrian walkway or route, and bicycle route or pathway surfaces, such as severe bumps, ruts, washboarding, potholes, excessive dust or mud, and non-conforming or out of place traffic control devices. Failure to install temporary crash cushions or barriers, when required according to the Contract or TCP, is also considered an unauthorized lane reduction. The Engineer will make the sole determination whether unauthorized lane reductions or closures are present.

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-3, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

The rates are liquidated damages which represent highway user costs, based on Average Daily Traffic (ADT). The Engineer will use the rate shown for the current ADT for this project, as published in the Regional Traffic Volume Report prepared by the Department's Planning Section. Adjustment rates for unauthorized reduction or closure of each lane of pedestrian walkways or route, and bicycle route or pathway, are the same as for one full roadway lane closure.

TABLE 643-3

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0 – 5,000 | $30 |
| 5,000 + | $40 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month before work is suspended for the season, schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the anticipated roadway condition and the work expected to be completed before shutdown. Schedule a field review with the Department for winter maintenance acceptance. At the field review, the Engineer will prepare a punch list for implementation before acceptance.

To be relieved of winter maintenance responsibility, leave all roads with a smooth and even surface for public use at all times. Properly crown the roadbed surface for drainage and install adequate safety facilities. Make sure all illumination and signals, including vehicle detectors, are in good working order.

After the project is accepted for winter maintenance and until ordered to resume construction operations, the Department is responsible for maintaining the facility. The Department will accept maintenance responsibility only for portions of the work that are open to the public, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. The contractor is responsible for maintaining all other portions of the work. The Engineer will issue a letter of “Acceptance for Winter Maintenance” that lists all portions of the work that the Department will maintain during a seasonal work suspension. The contractor retains all contractually required maintenance responsibilities until receipt of this letter.

If the contractor suspends work due to unfavorable weather (other than seasonal) or due to failure to correct unsafe conditions, carry out Contract provisions, or carry out the Engineer’s orders. All costs for traffic maintenance during the suspended period will be borne by the Contractor.

When work is resumed, replace or renew any work or materials lost or damaged during temporary use. If the Department caused damage during winter suspension, payment will be made for repairs by unit pay item or in accord with Subsection 109-1.05, Compensation for Extra Work. When the Engineer directs, remove any work or materials used in the temporary maintenance. Complete the project as though work has been continuous.

643-3.08 CONSTRUCTION SEQUENCING. The construction sequencing detailed in these provisions, the Special Provisions, and the Plans is suggested only. The Contractor may propose alternative construction sequencing.

Throughout the project, maintain the existing roadway, pedestrian walkway, or route, and bicycle route or pathway configuration (such as the number of lanes and their respective widths) except for restrictions to traffic allowed in the Special Provisions or on the Plans, and addressed through approved TCPs. A restriction to traffic is any roadway surface condition, work operation, or traffic control setup that reduces the number of lanes or impedes traffic. Obtain an approved TCP before restricting traffic.

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below:

1.	May 1 to September 30:

a.	Monday through Thursday:  0500 hrs to 2000 hrs.

b.	Weekends: Friday 0500 hrs to Sunday 2200 hrs.

2.	October 1 to April 30:

a.	Monday through Friday:  0500 hrs to 2000 hrs.

3.	Around any Holiday:

a.	If a holiday falls on Sunday, Monday, or Tuesday, the above stipulations apply from 1200 hrs on the Friday before the holiday to 0300 hrs on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 hrs on the Tuesday before the holiday to 0300 hrs on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 hrs on the day before the holiday to 0300 hrs on the Monday after the holiday.

4.	During the  Hooligan Fishing (May 1 to May 30):  No work to occur between MP 80.50 and MP 84 for Hooligan fishing access.

5.	During races/events:  Multiple races/events occur throughout the year within proximity to the project.  The contractor will be responsible for confirming these activity dates and coordinate work efforts and traffic restrictions appropriately.

6.	Road Closure:  A total of 20 full closures for up to 6 hours each will be allowed Monday through Thursday evenings beginning 2000 and ending 0500 for various work items.  Work items include, but are not limited to bridge girder placement, culvert placement, and utility relocation. No road closures allowed from Memorial Day thru Labor Day weekends.

7.	Pay Item 510.2000____ Bridge Deck Repair: Lane restrictions are allowed from Sunday 2000 to Friday 0500.

Lane restrictions, if allowed, conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 20 minute stopped delay, 80 vehicles, or 1/2 mile (2640 feet) of traffic detained, allowed for motorists, except school buses.  If a queue of traffic develops at a stop, empty the entire queue to include the last car that entered the queue at the time the queue was released.

Do not delay the school busses through the construction zone; obtain the local school bus schedule and coordinate work efforts.  Submit the plan, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

Obtain the local race/event schedules and coordinate work efforts to minimize impacts to the public.  Submit the plan, as a TCP, to the Engineer for approval before the implementation of the race/event coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS. Place permanent or interim pavement markings according to this Subsection, details shown on the Plans, approved TCPs, and Parts III and VI of the ATM before opening existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments for more than one continuous work shift. This work may include restriping the existing roadway before beginning construction, before seasonal suspension, and/or after seasonal suspension.

Remove conflicting pavement markings according to Subsection 670-3.04, Paint Removal.

Mark existing roadway sections that will be opened to traffic during the winter. Mark over the existing lines and markings, unless shown otherwise on the Plans or an approved TCP.

Maintain all interim pavement markings for their intended life including reapplication when necessary. There will be no compensation to upgrade interim pavement markings required for work operations lasting up to 2 weeks.

Use only temporary raised pavement markers as interim pavement markings on final pavement surfaces. Completely remove and dispose of them when placing the final markings. Completely remove any residual adhesive that might misguide motorists. Place final pavement markings on finished pavement surfaces and interim pavement surfaces before suspending work for the winter.

Stage the construction to avoid routing traffic over conflicting markings, for more than one continuous work shift. If traffic is routed over conflicting markings during a work shift, delineate the roadway with a complement of warning signs, channelizing devices, and flaggers as required by the ATM.

Use only temporary raised pavement markers meeting Subsection 712-2.16 as interim markings on seal coat and surface treatment pavements. Install the markers according to the manufacturer’s instructions before applying the asphalt surface material and cover coat. Remove the vinyl protective covers after applying the asphalt pavement.

On multicourse surface treatments, install the temporary raised pavement markers after applying the full width of the first layer of cover coat. Install the markers on each day's completed surface before removing the pilot car operations and allowing unescorted traffic on the surface treatment.

Apply final pavement markings according to Subsection 670-3.01, Construction Requirements, of these Special Provisions.

Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer.

643-3.10 LIGHTING FOR NIGHT WORK. Illuminate the night work areas according to Table 643-4.

Table 643-4 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

Use balloon lighting as the main light sources. Do not use floodlights without prior approval by the Engineer. When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway. Locate, aim, louver, and/or shield light sources to reduce glare.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences. When notified of unacceptable glare, modify the lighting system to reduce glare to an acceptable level.

TABLE 643-4

NIGHT WORK ILLUMINATION EQUIPMENT AND LOCATION REQUIREMENTS

| Type of Work or Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation. | At least one machine-mounted balloon light of at least 2000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping. | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging. | One balloon light of at least 2000 watts, located within 30 feet of the flagger location. Locate so the flagger and the flagging location are illuminated. Provide additional lights or wattage if necessary to provide complete coverage of the flagging location. |
| Truck Crossings where haul vehicles cross or enter a road with more than 10,000 ADT, or where the haul vehicle crossing or entering location is controlled by portable traffic signals or flaggers. | At least one balloon light of at least 2000 watts, located on the main road on the far right side of the intersection. Locate light within 30 feet of the edge of the side street. If there is a flagger at the crossing, locate the lights or lights so the lighting requirements for Flagging are also satisfied. |

If the Contractor fails to provide required lighting equipment or provides lighting that creates unacceptable glare, the Contractor shall cease all construction activities that require illumination, including flagging operations, until the condition or conditions are corrected.

Use lighting equipment in good operating condition and that complies with applicable state and local adopted codes and standards, and OSHA, NEC, and NEMA requirements.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment. Design mountings so lights can be aimed and positioned as necessary to reduce glare. Locate mounting brackets and fixtures so they don’t interfere with the equipment operator or overhead structures. Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment-mounted light towers or poles are sturdy and freestanding without the aid of guy wires. Towers shall be capable of being moved as necessary to keep pace with the construction operation. Position the ground and trailer-mounted towers and trailers, to minimize the risk of being impacted by traffic on the roadway, or by construction traffic, or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as overhead signals, overhead signs, trees, aerial utilities, or bridges. Aim and adjust lights to provide the required light levels. Provide uniform illumination on the hopper, auger, and screed areas of pavers. Illuminate the operator’s controls on all machines uniformly.

Furnish each side of non-street legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights may supplement but do not relieve the Contract requirement to provide lighting for night work, according to the requirements of Table 643-4.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that all required lights operate continuously during nighttime operations. Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours. In the event of any failure of the lighting system, discontinue the operation that requires illumination until the required level and quality of illumination is restored.

Maintain a supply of at least twenty emergency flares for use in the event of emergency or unanticipated situations. Comply with local noise ordinances.

Install all post-mounted electroliers located within the clear zone, on NCHRP 350 or MASH compliant breakaway bases.

643-3.11 HIGH VISIBILITY GARMENTS. Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004 or ANSI/ISEA 107-2010.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise). Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottom at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to the requirements of this Subsection 643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

7.	Condition.  Furnish and maintain all vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition. Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic contract items.

643-4.01 METHOD OF MEASUREMENT. Section 109 and as follows: Quantities will not be measured during winter suspension of work.

1.	Traffic Maintenance. Calendar Day: Every day shown on the calendar, beginning and ending at midnight. Measurement begins on the day following receipt of the Notice to Proceed or on the first day of work at the project site, whichever is later, and ends on the date of project completion.

2.	Traffic Control Device Items. By the number of units of each bid item shown on the bid schedule (or the Traffic Control Rate Schedule, if item 643.0025.____, Traffic Control, is included) that are installed, accepted, and operational. Incomplete or unsatisfactory devices will not be measured. Special Construction Signs are measured by the total area of legend-bearing sign panel, as determined under Subsection 615-4.01. Compensation for a 24-hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-5. Items measured by the day are for each item per 24-hour period.

3.	Traffic Maintenance Setup Items. By each lane closure or one-lane road in place per hour. By each detour or road closure in place per 24-hour period.

4.	Portable Concrete Barrier. By each nominal 12.5-foot section placed according to the approved TCPs, for the initial placement and for each subsequent relocation when moved more than 10 feet in any direction. Each transition piece (sloping end) will be measured as a single section.

5.	Temporary Crash Cushion. By each acceptable installation.

6.	Interim Pavement Marking. By the single-stripe station. A single stripe is a marking or a temporary raised pavement marker 4 inches wide. Wider striping is measured in multiples of 4 inches. Centerline gaps are not deducted from measurements.

7.	Flagging and Pilot Car. By the number of approved hours, supported by certified payroll.

8.	Street Sweeping. By the number of operated hours, supported by certified payroll and approved by the Engineer.

9.	Watering. By the 1,000 gallons (M-Gallon) of water applied. The Engineer may specify measurement by weight or volume. If by weight, convert to gallons at 8.34 pounds per gallon. If by volume, convert to gallons at 7.48 gallons per cubic foot.

10.	Traffic Price Adjustment. By each minute that any lane of traffic is not open to full use by the traveling public, measured to the nearest minute. The Engineer will determine whether the roadway is opened to full use.

11.	Traffic Control. By the units specified in the Special Provisions.

12.	Portable Changeable Message Board Sign. By the 24-hour period for each sign, as shown on an approved TCP and displaying an approved message.

13.	Plastic Safety Fence. By the linear foot, as placed, to protect or channelize pedestrian traffic as shown on an approved TCP. Any adjustment in configuration of the fence at the same location that does not result in an increased amount of fence is not measured. Opening and closing the fence to gain access to and from the worksite is not measured.

14.	Temporary Sidewalk Surfacing. By the square yard as shown on an approved TCP.

15.	Temporary Guardrail. By the linear foot, including end treatments, as shown on an approved TCP.

16.	Portable Steel Barrier. By the linear foot placed according to the manufacturer’s recommendation and approved TCPs, for the initial placement, and for each subsequent relocation when moved more than 10 feet in any direction.

17.	Hotline Road Report.  No measurement required to provide a 24-hour toll free (1-800 ###-####) “Hotline Road Report” telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Pay Item 643.0001.____ or 643.0002.____, Traffic Maintenance.

643-5.01 BASIS OF PAYMENT.

1.	Traffic Maintenance. The contract price includes all resources required to provide the Worksite Traffic Supervisor, all required TCPs and public notices, the Construction Phasing Plan, and the maintenance of all roadways, approaches, crossings, intersections and pedestrian and bicycle facilities, as required. This item also includes any Traffic Control Devices required but not shown on the bid schedule.

Items required by the Contract that are not listed on the bid schedule or not included in other items are subsidiary to Item 643.0001.____ or 643.0002.____ Traffic Maintenance, except the following:

Traffic Price Adjustment

Traffic Maintenance Setup

2.	Traffic Control Device Items. The contract price includes all resources required to provide, install, maintain, move, and remove the specified devices. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

3.	Traffic Maintenance Setup Items. Each setup consists of all traffic control devices, flaggers, pilot cars, and subsidiary items necessary to implement the TCP shown on the Plans. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

Construction and obliteration of temporary roadways, when required on the Plans or approved TCP under a traffic maintenance setup item, is paid for under their respective roadway pay items.

When topsoil or seeding is required for detours, payment will be made under Sections 620 and/or 618.

4.	Portable Concrete Barrier. The contract price includes all resources required to provide, install, maintain, and remove each barrier section.

5.	Temporary Crash Cushion. The contract price includes all resources required to provide, install, maintain, repair, and remove each crash cushion.

6.	Interim Pavement Marking. The contract price includes all resources required to provide, install, maintain, and remove the specified markings. Installation of word and symbol markings are subsidiary. The No-Passing Zone signing, described in Subsection 643-3.04, is subsidiary.

7.	Flagging and Pilot Car. The contract price includes all required labor, vehicles, radios, flagger paddles and pilot car signs, and transportation to and from the worksite.

The Engineer will pay for Item 643.0032.____ Flagging on a contingent sum basis at the rate of $58.00/hour.  The Engineer does not require a change order/directive for the flagging Pay Item.  Flagging associated with Change Order work paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

8.	Street Sweeping. The contract price includes all resources required to keep the roadway free of loose material.

9.	Watering. The contract price includes all resources required to provide watering, as directed.

10.	Traffic Price Adjustment. If Item 643.0023.____, Traffic Price Adjustment, is shown on the bid schedule, the total value of this contract will be adjusted, for unauthorized lane reductions or closures, at the rates listed in Table 643-3.

11.	Traffic Control. Payment for Item 643.0025.____, Traffic Control, will be made at the unit rate value contained in the Traffic Control Rate Schedule shown in the Special Provisions for the accepted units of traffic control devices. The Engineer does not require a change order/directive for Pay Item 643.0025.____, Traffic Control.

12.	Portable Changeable Message Board Sign. The contract price includes all resources required to furnish, move, and operate the sign.

Two Portable Changeable Message Board Signs used for Permanent Construction Signing paid for under Item 643.0003.____ Permanent Construction Signs.  Additional portable changeable message board signs will be paid for under 643.0025.____, Traffic Control.

13.	Plastic Safety Fence. The contract price includes all resources required to install, maintain, and remove the fence.

14.	Temporary Sidewalk Surfacing. The contract price includes all resources required to construct, maintain, and remove the surfacing.

15.	Temporary Guardrail. The contract price includes all resources required to construct, maintain, and remove the guardrail.

16.	Portable Steel Barrier. The contract price includes all resources required to provide, install, maintain, move, and remove each barrier.

17.	Lighting for Night Work.  Payment for illuminating night work areas and any required adjustments to work zone illumination is subsidiary to other items.

18.	Pavement Breaks.  Temporary hot mix asphalt at pavement breaks, as noted in Subsection 643-3.02.2. Gravel Surface Not Specified is subsidiary to Pay Item 401.0001.____.

19.	Temporary Pavement Markings.  Except where specified as an individual Pay Item (Interim Pavement Markings) temporary pavement markings are subsidiary to Section 670 Pay Items. Refer to Section 670 Traffic Markings, for further information.

20.	Temporary Crash Cushion / Redirective.  The price listed in the Traffic Control Rate Schedule, Table 643-5, will be full compensation for the purchase, installation, maintenance during construction, removal, and salvaging the Temporary Crash Cushion / Redirective unit(s).  Deliver the salvaged unit(s) to the nearest ADOT & PF Maintenance & Operations Station or as directed by the Engineer.

Traffic control devices, barriers, and crash cushions required to delineate or shield fixed objects will not be measured or paid for separately, but will be subsidiary

Traffic control devices, barriers, and crash cushions required to delineate or shield guardrail posts or non-crashworthy ends will not be measured or paid for separately, but will be subsidiary, when required for failure to meet completion timelines in subsection 606-3.01.

TABLE 643-5

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $28.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Sequential Arrow Panel | Each/Day | $36.00 |
| Portable Concrete or Steel F Shape Barrier (12.5 foot long or $8/foot for other lengths) | Each | $100.00 |
| Temporary Crash Cushion / Non-redirective Water Filled Barrier (all required per end) | Each | $2500.00 |
| Temporary Crash Cushion / Non-redirective Water Filled Barrels (all required per end) | Each | $3285.00 |
| Temporary Crash Cushion / Non-redirective Sand Filled Barrels (all required per end) | Each | $4325.00 |
| Temporary Crash Cushion / Redirective | Each | $9230.00 |
| Pilot Car (4x2, 1/2 ton truck) | Hour | $72.00 |
| Watering Truck – up to 4900 gallon capacity | M-Gallon | $28.00 |
| Watering Truck – more than 4900 gallon | M-Gallon | $21.00 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical or Power Broom with Vacuum | Hour | $214.00 |
| 40,000 GVW Truck with Crash Attenuator | Hour | $162.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Portable Changeable Message Board Sign | Calendar Day | $130.00 |
| Temporary Sidewalk Surfacing | Square Foot | $2.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |
| Temporary Guardrail | Lineal Foot | $25.00 |

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 643.0001.____ | Traffic Maintenance | CDAY |
| 643.0002.____ | Traffic Maintenance | LS |
| 643.0003.____ | Permanent Construction Signs | LS |
| 643.0004.____ | Construction Sign | Day |
| 643.0005.____ | Type II Barricade | Day |
| 643.0006.____ | Type III barricade | Day |
| 643.0007.____ | Traffic Cone/Tubular Marker | Day |
| 643.0008.____ | Plastic Safety Fence | LF |
| 643.0009.____ | Drum | Day |
| 643.0010.____ | Sequential Arrow Panel, Type C | Day |
| 643.0011.____ | Special Construction Signs | SF |
| 643.0012.____ | Portable Concrete Barrier | Each |
| 643.0013.____ | Temporary Crash Cushion | Each |
| 643.0014.____ | Interim Pavement Marking | STA |
| 643.0015.____ | Flagging | HR |
| 643.0016.____ | Pilot Car | HR |
| 643.0017.____ | Street Sweeping | HR |
| 643.0018.____ | Watering | MGAL |
| 643.0019.____ | Lane Closure | HR |
| 643.0020.____ | Detour | Day |
| 643.0021.____ | Road Closure | Day |
| 643.0022.____ | One Lane Road | HR |
| 643.0023.____ | Traffic Price Adjustment | CS |
| 643.0024.____ | Portable Changeable Message Board Sign | Day |
| 643.0025.____ | Traffic Control | CS |
| 643.0026.____ | Temporary Sidewalk Surfacing | SY |
| 643.0027.____ | Temporary Guardrail | LF |
| 643.0030.____ | Portable Steel Barrier | LF |
| 643.0031.____ | Interim Pavement Marking | LS |
| 643.0032.____ | Flagging | CS |
| 643.0033.____ | Detour | LS |

CR643-010120 / CFHWY00213

- SECTION 644
SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

Replace Subsection 644-2.01 with the following:

644-2.01 FIELD OFFICE. Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1200 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

a. Office. Provide each office with:

(1) Floor area: 160 ft2 minimum and 200 ft2 maximum

(2) Minimum wall length 9 ft.

(3) Two electrical outlets. One outlet on two different walls

(4) Entrance through a closeable door directly from the common area

(5) Window: one window operable and lockable approximately 16 ft2 providing adequate ventilation

b. Lavatory.

(1) Floor area: 60 ft2 minimum, 80 ft2 maximum

(2) Minimum wall length 5 ft

(3) Plumbed toilet and sink with potable water

(4) One electrical outlet

(5) Entrance through an inside closeable lockable door directly from the common area

c. Common Area.

(1) Floor area: overall floor area less the offices and lavatory floor areas

(2) Seven electrical outlets spaced around the outside walls

(3) Two entrance doors from the exterior on the same side as the parking, closeable and lockable

(4) Potable water: watercooler with five gallon tank and refrigerated dispenser

(5) Windows: 80 ft2, approximately four operable and lockable windows with a minimum area 16 ft2 each and spaced approximately equally along the perimeter walls to provide adequate ventilation.

2.	A thermostatically controlled interior heating and air conditioning system with necessary fuel and the ability to maintain an ambient temperature of 70 degrees Fahrenheit.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 12 electrical outlets.

4.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

5.	Provide engineering communication services to the field office, Subsection 644-2.08.

6.	Located within 3 miles of the project.

7.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

8.	Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

9.	Furnish, install, and maintain a security system for exclusive use and controlled by the Department for the office including camera coverage for the vehicle parking.

CR644.FOCOM-080120 / CFHWY00213

644-2.02 FIELD LABORATORY.

Replace 2.g. with the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Replace Subsection 2.h.(2) and (3) with the following:

(2)	Wiring system to support a 100-amp user load demand with one 50-amp and two 20-amp circuits, all GFI protected.

(3)	Outlets, ten conveniently spaced around the lab, 20-amp capacity, with no more than five outlets per circuit, and consistent with local codes.

Add 2.h.(6):

(6)	Outside outlet, 220-volt.

Replace Subsection 4.c.(3) with the following:

Wiring system with each circuit GFI protected to satisfy a 60-amp user load demand. Provide three 20-amp circuits each with a 20-amp outlet. Space the outlets around the shed for the users convenience.

Replace 6.a. with the following:

a.	Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

Add the following:

7.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

8.	Provide engineering communication services to the field laboratory, Subsection 644-2.08.

9.	Furnish, install, and maintain a security system for exclusive use and controlled by the Department for the office including camera coverage for the vehicle parking.

CR644.LAB-080120 / CFHWY00213

Add the following Subsection 644-2.08 Engineering Communication and Office Equipment:

644-2.08 ENGINEERING COMMUNICATION AND OFFICE EQUIPMENT.  Engineering Communications and Office Equipment, minimum service includes:

1.	Three phone/facsimile lines and commercial phones (different phone numbers for each line)

a.	One phone with built-in digital answering machine.

b.	Ancillary equipment for operational service and as required by the Engineer.

2.	High speed internet service with modem (DSL or Cable)

a.	Send and receive capability supporting 10.0 Mbps download and upload speed or higher at all times.

b.	Data usage, 10 GB minimum monthly.

c.	Wireless router.

d.	Battery backup.

e.	Ancillary equipment for operational service and as required by the Engineer.

3.	Equipment rental services

a.	All-in-one printer/copier/scanner

(1)	Black-white and color

(2)	Pages per minute (ppm): 50

(3)	Paper trays: 8.5" x 11" and 11" x 17"

(4)	Capacity: 1100 sheets minimum

(5)	Include all paper and Ink

CR644.FOCOM-080120 / CFHWY00213

644-5.01 BASIS OF PAYMENT.

Add the following:

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Pay Item 644.0002.____ Field Laboratory.

CR644.LAB-080120

Add the following:

Pay Item 644.2004.____ Engineering Communications:

Usage services including long distance calls made by State personnel and the Internet service provider will be reimbursed by the State.  Payment for communication usage services and equipment rental agreements shall be based on paid receipts to the service provider plus 15%.

Connection fees (initial connection) local calls, providing equipment and disconnection are subsidiary to Pay Item 644.0001.____ Field Office and as such are paid by the Contractor.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 644.2004.____ | Engineering Communications | CS |

CR644.FOCOM-080120

Special Provision

Add the following Section:

SECTION 645
TRAINING PROGRAM

645-1.01 DESCRIPTION. This Statewide Special Provision for on-the-job training (OJT) implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective. Training and upgrading of minorities and women toward journey status is the primary objective of this program. The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision. Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301.

645-3.01 General. The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive. Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Office of Apprenticeship (USDOL/OA); or one developed by the Contractor using Form 25A-310 and approved prior to contract award by the OJT Coordinator in the DOT&PF Civil Rights Office.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor. Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed. It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project. Existing USDOL/OA apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. The Contractor must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period. Trainee wages shall be identified on Form 25A-310. Apprentices in USDOL/OA training programs shall be paid in accordance with their approved program. Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts. In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor. Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate. However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls. There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section. Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment. Payment will be made at the contract unit price for each hour of training credited. Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311 may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project. No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown in the Bid Schedule and approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown in the Bid Schedule and approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry. Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program. Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits. The journey worker scale is that for the classification identified in the approved programs.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 645.0001.____ | Training Program, Trainees/Apprentices | LH |

HSP20.2-113020

SECTION 646
CPM SCHEDULING

Special Provisions

Replace Subsection 646-2.01 with the following:

646-2.01 SUBMITTAL OF SCHEDULE.

Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.

Delete No. 2.

2.	60-Day Preliminary Schedule.

Replace the first sentence of No. 3 Schedule Updates. with the following:

Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

CR646.1-070214R

Special Provisions

Add the following Section:

SECTION 647
EQUIPMENT RENTAL

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled, and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, except holidays.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. Section 109.

Hourly Rental Rate: Includes the equipment rate plus the operating costs including: furnishing, travel time, operating, maintaining/servicing and repairing the equipment along with the costs incidental to the equipment and its' operation.

647-5.01 BASIS OF PAYMENT. Payment is for the time that fully operational equipment is engaged in the performance of the work directed by the Engineer. Time not payed for includes: idle periods, maintaining/servicing and repairing the equipment, making change-overs of equipment parts, and time to travel to and from the project.  Payment will only be for time supported by certified payroll.

Furnishing and operating equipment that is heavier, has larger capacity, or greater power than specified will not entitle the Contractor to extra compensation.

Pay Item 647.2000.____ Wide Pad Dozer, 65-HP Minimum: payed at the rate of $160/hour.

Pay Item 647.2002.____ Backhoe, 4WD, 1 CY Bucket, 75-HP Minimum, 15 ft Depth: payed at the rate of $160/hour.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 647.2000.____ | Wide Pad Dozer, 65-HP Minimum | CS |
| 647.2002.____ | Backhoe, 4WD, 1 CY Bucket, 75-HP Minimum, 15 ft Depth | CS |

CR647-110316R

Special Provision

Replace Section 651 with the following:

SECTION 651
CONTROL OF WORK – SUPPLEMENTAL REQUIREMENTS

651-1.01 DESCRIPTION. Supplemental requirements for Section 105, Control of Work.

651-1.02 RELATED SECTIONS. Section 105, Control of Work

651-1.03 UTILITIES.  Request locates from the utilities having facilities in the area.

Use the Alaska Digline, Inc. "Locate Call Center" for the following utilities.

ALASKA DIGLINE, INC.

Locate Call Centers: Anchorage 278-3121 Statewide (800) 478-3121

Call Centers will notify the following: Alaska Communications Systems (ACS) Alaska Railroad Corporation (ARRC) AT & T Alascom (AT&T) Chugach Electric Association (CEA) General Communications, Inc. (GCI)

State Facility Utilities: before beginning work, contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the District Superintendent's phone number where the project is located, and request locates.

Utilities Relocated by Others.

Utilities will be relocated by others concurrently with construction of this project. The Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.

For utilities being relocated, the Contractor shall:

1.	include utility work on the Construction Phasing Plan and Progress Schedule;

2.	provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work.  Identify all utility companies performing ground disturbing activity in the Storm Water pollution Prevention Plan (SWPPP).  Refer to Section 641 for further information;

3.	clear and grub.  Payment will be made under Section 201, Clearing and Grubbing;

4.	provide traffic control and flagging.  Payment will be made under Section 643, Traffic Maintenance;

5	provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

	Control for utility relocation - either ROW or Centerline staking with Station information.

	Slope staking.

	Proposed structures, not including utilities to be relocated by others.

Payment will be made as follows:

a.	Subsidiary to Pay Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642(3) Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 7 calendar days advance written notice for required staking.

6.	remove and replace pavement.  Payment will be made under Section 202, Removal of Structures and Obstructions; Section 401, Hot Mix Asphalt and Surface Treatments; Section 408, Hot Mix Asphalt and Surface Treatments, Type V; Section 409, Hot Mix Asphalt and Surface Treatments, Type R (Crumb Rubber) and according to project typical section.

7.	remove and replace sidewalk and curb and gutter.  Payment will be made under Section 202, Removal of Structures and Obstructions, Section 608, Sidewalks, and Section 609, Curbing.

8.	provide bedding and backfill material, in accordance with Section 204, Structure Excavation for Conduits and Minor Structures, and the project typical sections.

9.	coordinate with the utility owner(s) and provide potholing services at the locations identified or as directed by the Engineer. Payment will be made under Section 682, Utility Potholing.

Work done by utility owner(s) is as follows:

The working days provided within this section for utility relocation only account for the time necessary to complete the described utility company construction and cutover work, with the assumption that the Contractor has performed, to the satisfaction of the utility, all necessary site preparations, and is ready/able to support utility construction activities when requested.  Utility company working days shall not be assumed to be consecutive and cannot overlap with the Contractor’s or other utility’s work unless expressly stated in the utility’s respective Agreement, or approved by the Engineer.

ALASKA RAILROAD CORPORATION (ARRC)

ARRC owns and operates railroad facilities and Right-of-Way within the project area.  ARRC will perform/complete the following work to accommodate the proposed project improvements.  All coordination with ARRC shall be handled in accordance with Section 686.

Project CFHWY00213:

To facilitate the proposed culvert pipe installation at “SH” station 1796+00 ARRC will:

Prior to the Track Outage:

- Participate in an onsite coordination meeting to determine the scope/sequence of the Contractor’s work and mark where the tracks need to be cut to accommodate the pipe work.

- Cut and bolt the track in advance of the scheduled track outage.

During the Track Outage:

- Unbolt the tracks and provide the required rigging to lift the track panel.

- Bolt the rail, surface the track, and then weld the rail.

The Contractor shall coordinate with the Engineer and ARRC, a minimum of three (3) weeks in advance of the proposed culvert work, to schedule and participate in an onsite coordination meeting and track outage.  The current train schedule and availability of ARRC personnel and equipment will dictate when a track outage can be scheduled.  During the track outage the Contractor shall allocate the first hour for ARRC personnel to unbolt the rail, and the final six (6) hours for ARRC personnel to bolt the rail, surface the track, and weld the rail.  ARRC will coordinate with the Contractor to place additional ballast during the surfacing process.  The Contractor may perform other activities concurrently with the ARRC work so long as those activities do not prohibit or interfere with ARRC operations.

Project CFHWY00308:

The proposed connector trail to Trail of Blue Ice crosses ARRC railroad facilities at “BI” station 110+50.  ARRC will extend the existing Portage Glacier Road crossing, installing new 10ft. ties, concrete grade crossing panels, and the associated track hardware required, to accommodate the proposed pathway.  The Contractor shall allow two (2) working days to complete this work.

ACS OF ANCHORAGE, LLC (ACS)

ACS owns and operates underground telecommunication distribution, and service facilities within the project area.  The system consists of both copper and fiber optic circuits and the associated pedestals, handholes, and poles.

Project CFHWY00213:

ACS’s existing pedestal at “SH” station 276+38 1’ RT is in conflict with the proposed Seward Highway alignment and will be relocated.  ACS will install a new copper line in 2-inch duct between “SH” stations 276+25 213’ RT and 276+16 132’ LT, exposing/capturing/redirecting the existing facilities at either end into a new handhole and pedestal respectively.  The new facility will be bored under the existing driveway on project right and the existing Seward Highway alignment.  Once cutover, the existing facilities retired as a result of this work will be removed/abandoned in-place.  The above described scope of work must be completed prior to construction of the proposed embankment for the new Seward Highway alignment.  The Contractor shall allow ACS nine (9) working days to complete the above defined scope of work.

The ACS duct and cable attached to the existing Portage Creek #2 bridge is in conflict with the proposed demolition of the structure and will be relocated.  ACS will set new pedestals over the existing ACS facilities at “SH” stations 287+00 RT and 302+00 RT, and connect them with a new copper cable in 4-inch duct.  The new facility will be installed adjacent to the Right of Way and be bored under Portage Creek #2.  The above described scope of work must be completed prior to the demolition of Portage Creek #2 bridge.  The Contractor shall allow ACS twelve (12) working days to complete the proposed relocation work.

ALASCOM, INC., AN ALASKA CORP., D.B.A. AT&T (AT&T)

AT&T owns and operates underground telecommunications facilities within the project limits.  The system consists of underground fiber optic circuits and the associated ducts/vaults.  The existing facilities are not anticipated to be in conflict with the proposed improvements.

CHUGACH ELECTRIC ASSOCIATION, INC (CEA)

CEA owns and operates electrical transmission, distribution, and service facilities within the project limits.  The system consists of both overhead and underground circuits.  CEA will complete the following work to resolve conflicts between the Department’s project and its existing facilities:

Project CFHWY00213:

The existing CEA 14.4 KV single-phase overhead distribution line crossing the proposed Seward Highway alignment at “SH” station 272+75 is in conflict with the proposed roadway alignment, and the associated grade changes and bridge construction.  CEA will relocate the existing single-phase overhead facility between Pole 1394 (“PGR” station 13+03 130’ RT) and “SH” station 276+23 120’ LT.  The new alignment will extend west from Pole 1394, crossing the proposed Seward Highway alignment at “SH” station 267+85, and then turn north and continue across Portage Creek #1 to proposed Pole 9112 (“SH” station 276+23 120’ LT).  Once the new facility has been energized, the conductor and poles retired as a result of this work will be removed from the Right-of-Way.  The Contractor shall allow CEA twelve (12) working days to complete the above defined scope of work.

The existing 14.4 KV overhead single-phase conductor between “SH” stations 286+35 238’ LT and 296+36 237’ LT, as well as the existing pole/anchor at “SH” station 300+57 52’ LT, are in conflict with the grade changes associated with the proposed Alaska Wildlife Conservation Center (AWCC) driveway, trail access parking area, and Seward Highway alignment.  CEA will:

- Replace Poles A15 (“SH” station 286+35 238’ LT), A16 (“SH” station 288+90, 237’ LT), A17 (“SH” station 288+90 237’ LT), A18 (“SH” station 293+86, 237’ LT), and A19 (“SH” station 296+36 237’ LT) with taller poles.

- Set a pole (8758) and two anchors at “SH” station 300+54 80’ LT.

- Install new overhead conductor between Pole 8758 (“SH” station 300+54 80’ LT) and Pole 8830 (“SH” station 286+35 238’ LT).

- Detach/transfer the existing overhead span extending north from Pole A20A (“SH” station 300+57 52’ LT) to Pole 8758, and energizing the new facilities.

- Dismantle and remove the existing facilities retired as a result of the proposed work.

The Contractor shall allow CEA fifteen (15) working days to complete the above defined scope of work.

Line Extension

Prior to CEA establishing service to a load center, the Contractor shall have it inspected, and green tagged for compliance.  Once tagged, the Contractor shall notify the Engineer who will contact the utility.  CEA will schedule and complete the line extension work based on its current workload.  The following work will be completed to provide electrical service to the proposed load center locations:

Project CFHWY00213:

Load Center A (“SH” station 270+25.2 135.0’ LT) will be served from proposed CEA Pole 8802 (“SH” station 270+12.6 145.0’ LT).  CEA will mount an overhead transformer and riser on Pole 8802 and install 2-inch conduit and conductor to the load center location.  The Contractor shall allow one (1) working day to complete this work.

Load Center B (“SH” station 288+85.2 230.3’ LT) will be served from proposed CEA Pole 8735 (“SH” station 288+90.0 240.5’ LT).  CEA will mount an overhead transformer and riser on new Pole 8735 and install 2-inch conduit and conductor to the load center location.  The Contractor shall allow two (2) working days to complete this work.

Load Center C (“SH” station 348+07.3 135.5’ RT) will be served from existing CEA Pole R2 (“SH” station 347+75.9 196.5’ RT).  CEA will install a new riser, secondary pedestal and extend conduit and conductor to the load center location.  The Contractor shall allow two (2) working days to complete this work.

Load Center D (“SH” station 268+30.9 286.0’ RT) will be served from existing CEA Pole 1394 (“SH” station 267+75.4 340.0’ RT).  CEA will mount an overhead transformer and riser on existing Pole 1394 and install 2-inch conduit and conductor to the load center location.  The Contractor shall allow three (3) working days to complete this work.

Load Center T (“SH” station 300+61.2 71.8’ LT) will be served from proposed CEA Pole 8758 (“SH” station 300+54.0 80.0’ LT).  CEA will mount an overhead transformer and riser on new Pole 8758 and install 2-inch conduit and conductor to the load center location.  The Contractor shall allow two (2) working days to complete this work.

Load Center P (“SH” station 270+19.7 131.0’ LT) will be served from proposed CEA Pole 8802 (“SH” station 270+12.6 145.0’ LT).  CEA will install an overhead transformer and riser on new Pole 8802 and install 2-inch conduit and conductor to the load center location.  The Contractor shall allow one (1) working day to complete this work.

Load Center R (“SH” station 348+01.5 135.5’ RT) will be served from existing CEA Pole R2 (“SH” station 347+75.9 198.5’ RT).  CEA will install a new riser, secondary pedestal and extend conduit and conductor to the load center location.  The Contractor shall allow two (2) working days to complete this work.

GCI COMMUNICATION CORP (GCI)

GCI owns and operates underground telecommunications facilities within the project limits.  The system consists of fiber optic circuits and the associated ducts, vaults, and Hut.  GCI will complete the following work to resolve conflicts between the Department’s project and its existing facilities:

Project CFHWY00213:

The Contractor shall coordinate with GCI and slope stake/pothole the following locations/facilities:

- “SH” station 348+75 67’ RT where GCI’s existing underground fiber optic facility crosses the proposed cut limits.  If the facility will have less than 4-feet of cover from final grade, GCI will expose and lower this line.  The Contractor shall allow GCI three (3) working days to complete this work.

GCI’s existing fiber vault at “SH” station 269+55 59’ LT is in conflict with the proposed slope limits and will be relocated.  Once the contractor has completed the required clearing/grubbing and slope staking work between “SH” stations 267+00 LT and 270+00 LT, GCI will expose and move the existing duct and vault system outside of the proposed slope limits.  The Contractor shall allow GCI ten (10) working days to complete the above defined scope of work.

GCI’s existing underground fiber optic facilities extend throughout the project and are attached to both the Portage Creek #2 and Twenty Mile bridge structures.  The proposed relocation work has been broken into two sections:

- Section 1 (“PGR” 16+00 LT to “SH” 348+60 LT) – GCI will set a new vault over the existing fiber optic facilities at “PGR” station 16+00 90’ LT and install a new duct and vault system to the existing fiber optic vault at “SH” station 318+00 LT.  The proposed crossings of Portage Creek #1, Portage Creek #2, and the Seward Highway will be bored.  Once the duct system is continuous, GCI will pull new fiber optic cable from “PGR” station 16+00 90’ LT to “SH” station 348+60 LT, and cutover to the new facility.  The existing fiber optic cable and vaults retired as a result of this work will be removed from the Right-of-Way.  Retired duct will be abandoned in-place.  The Contractor shall allow GCI fifty (50) working days to complete the proposed installation, cutover, and retirement work.  Fiber cutovers will be scheduled 30 calendar days in advance of the splice work, and the cutover cannot be initiated until the replacement facility is in place and ready to be spliced.  The 30 day scheduling window is included in the construction timeframe provided, GCI will provide written notice to the Engineer once the 30 day window has been initiated.  All new facilities must be installed and cutover before any portion of the existing system can be retired.	

Due to the sensitive nature of the traffic being transmitted through this facility, the line may not be out of service for any period of time.  Scheduled cutovers may be canceled at any point during the 30 day window.  If the fiber cutover date must be adjusted for any reason, the 30 calendar day scheduling window will reset.

- Section 2 (“SH” 348+60 LT to “SH” 442+30 RT) – GCI will set a new vaults over the existing fiber optic facilities at “SH” station 348+60 LT and 377+50 LT, and install a new duct and vault system along project left connecting them.  The proposed crossing of Twenty Mile River will be bored.  Once the duct system is continuous, GCI will pull new fiber optic cable from “SH” station 348+60 LT to “SH” station 442+30 RT, and cutover to the new facility.  The existing fiber optic cable and vaults retired as a result of this work will be removed from the Right-of-Way.  Retired duct will be abandoned in-place.  The Contractor shall allow GCI forty (40) working days to complete the above defined scope of work.  Fiber cutovers will be scheduled 30 calendar days in advance of the splice work, and the cutover cannot be initiated until the replacement facility is in place and ready to be spliced.  The 30 day scheduling window is included in the construction timeframe provided, GCI will provide written notice to the Engineer once the 30 day window has been initiated.  All new facilities must be installed and cutover before any portion of the existing system can be retired.	

Due to the sensitive nature of the traffic being transmitted through this facility, the line may not be out of service for any period of time.  Scheduled cutovers may be canceled at any point during the 30 day window.  If the fiber cutover date must be adjusted for any reason, the 30 calendar day scheduling window will reset.

Project CFHWY00308:

Survey of the existing fiber optic duct and vault system paralleling and crossing Portage Glacier Road is incomplete.  Conflicts between the existing facilities and proposed improvements are not anticipated.  The Contractor shall slope stake and confirm that the existing vaults and surface features are not in conflict with the proposed embankment.  The Engineer will provide direction and coordinate with GCI in the event conflicts are discovered.

651-1.04 COOPERATION BETWEEN CONTRACTORS.  The following state owned projects may be under construction concurrently with this project.

| Project Name: | Project No.: |
| --- | --- |
| Seward Hwy: MP 100-105 Improvements | CFHWY00011 |
| Seward Hwy: MP 105-107 Windy Corner | Z566310000 |
| Seward Hwy: MP 75-90 Road and Bridge Rehabilitation, Phase I | CFHWY00212 |

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

651-1.05 INTERIM COMPLETION.  This project includes one interim completion phase.

Interim Completion Phase:

Date:	30 June, 2021

Work:	Complete all initial Roadway Repair Pavement – Unstable, Raveling; Repair Roadway Pavement – Pothole; and Bridge Deck Repair locations by the interim completion date.

Final Completion Phase:

Date:	See the Invitation to Bid for the final completion date.

Work:	All remaining work in the Contract.

CR651-020118R_SSHC2017.20 / CFHWY 00213 CFHWY00308

Special Provisions

Replace Section 652 with the following:

SECTION 652
PROSECUTION AND PROGRESS – SUPPLEMENTAL REQUIREMENTS

652-1.01 DESCRIPTION.  Supplemental requirements for Section 108. Prosecution and Progress.

652-1.02 RELATED SECTIONS.  Section 108, Prosecution and Progress.

652-1.03 PROSECUTION AND PROGRESS.  In Subsection 108-1.03:

	Replace the last sentence in the 1st paragraph with: "Submit the following at the Preconstruction Conference:"

	Replace the last sentence in No. 1 with: "A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor, subcontractors and utilities will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer."

652-1.04 LIMITATION OF OPERATIONS. In Subsection 108-1.04:

	Add: "Limit ground disturbed by construction activities and not permanently stabilized between all roadways combined, at any specific time, to a maximum of 11,000 feet parallel to the roadway(s), unless additional length is approved. Stabilize disturbed ground according to Section 641 Erosion, Sediment, and Pollution Control."

652-1.05 FAILURE TO COMPLETE ON TIME. In Subsection 108-1.07:

      Add: "for each calendar day that the work remains incomplete after the expiration of the interim completion date(s) as set forth in Subsection 651-1.05 Interim Completion, the liquidated damages per day given in the table below shall be deducted from any monies due the Contractor."

TABLE 652-1

INTERIM COMPLETION

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Completion Date | Daily Charge |
| --- | --- |
| 1st Interim Completion Date | $4,800 |

CR652-071519 / CFHWY 00213

Special Provision

Add the following Section:

- SECTION 654
MONITOR

654-1.01 DESCRIPTION.  Comply with the National Marine Fisheries Service (NMFS) requirements listed in Appendix H, Letter of Concurrence (LOC), Marine Mammal Monitoring Plan and subsequent Reinitiation letter. Engage a professional services contractor to act as an observer or monitor for endangered species within the requirements shown in the appendix. At the preconstruction conference, provide the names and qualifications of the professional services contract manager and the on-site monitors or observers.

654-2.01 CONSTRUCTION REQUIREMENTS.  Meet all monitoring requirements and methods in Appendix H. Provide sufficient numbers of qualified and trained observers as required. Prepare all reports and forms, and supply all required equipment as outlined in the appendix.

654-3.01 METHOD OF MEASUREMENT.  Subsection 109-1.05 and in the manner specified in the directive authorizing the work.

The pay unit, contingent sum, is measured by the hour of work performed.

654-4.01 BASIS OF PAYMENT.  Subsection 109-1.05 and paid for as specified in the directive authorizing the work.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

654.2004.0000	Monitor, Marine Mammal	Contingent Sum

CFHWY00213

SECTION 660
SIGNALS AND LIGHTING

Special Provision

Add the following subsections:

660-1.03 REGULATIONS AND CODE. All materials and workmanship shall conform to the standards of the Underwriter's Laboratories, Inc. and the National Electrical Code and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturer's Association, where applicable.

MATERIALS

660-2.01 MATERIALS. Replace Item 1. Equipment List(s) and Drawings with the following:

1. Equipment List(s) and Drawings. Within 30 days after the Contract award, submit three (3) collated copies of a portfolio of equipment and materials proposed for installation to the Department for review and approval. Include a table of contents in the portfolios that includes each item’s intended use(s); identity of each component's proposed features; and the following:

a. 	Materials on the Qualified Products List: A description that includes product name, manufacturer, model or part number and the conditions listed for approval.

b. 	Materials Not on the Qualified Products List: Catalog cuts that include the manufacturer’s name, type of product, size, model number, conformance specifications, and other data as may be required, including manufacturer’s maintenance and operations manuals, or sample articles. Catalog cuts shall be clearly marked indicating which item on the catalog cut will be used when multiple items are shown.

c. 	Materials Requiring Certification: Submit certification from the supplier for all steel products incorporated in the RWIS installation indicating origin with the material catalog cuts or the shop drawings in accordance with Subsection 106-1.01, Source of Supply and Quality Requirements.

d. 	Materials Not Requiring Certification: Incidental materials incorporated into the work (such as nuts, ties, bolts, washers, etc.) must meet all applicable Specifications and be installed per all manufacturer’s recommendations. Certification is not needed unless required by the Special Provisions or requested by the Engineer.

CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL.  Replace 2. though 5. with the following:

- Safety Precautions. Before starting work on existing street lighting circuits, de-energize the system by opening disconnect switches, and/or opening bypass switch plugs, and tagging each opened device as detailed in Part 4, Section 44, Article 440 of NESC. Where said circuits are under the control of an electric utility, obtain written assurance daily from the utility that the circuit being worked on has been de-energized.

Prior to beginning work, perform lockout/tagout procedures and establish an electrically-safe work condition per NFPA 70E Article 120.Post suitable signs at load centers when any of the circuits from that load center are being worked on.

Existing circuits listed on the wiring diagrams and Plan sheets were obtained from as-built information and must be verified before work involving those circuits.

- Excavating and Backfilling.  Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors before final lift paving.  Provide traffic control to complete this work according to the requirements of Section 643.  Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit.  Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

When conditions allow HDPE conduit to be installed by a plowed technique, restoring the area disturbed from the process shall be accomplished according to Subsection 204-3.01. Density testing may be waived and compactive effort substituted at the discretion of the Engineer.  This work is subsidiary to conduit installation.  Use Selected Material, Type A for backfill.

Dispose of, according to Subsection 203-3.01, excavated materials that remain after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in Subsection 703-2.07. Disposal of this material is subsidiary to the 660 Pay Items.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations.  Backfill excavations with materials that meet the following requirements:

- Backfill foundations with material that meets the requirements of Selected Material, Type A that passes through a 3 inch sieve.

- Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift.

- In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

- Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material cleaned free of rocks exceeding a 1 inch maximum dimension.  Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to Subsection 203-3.04.  In other locations, compaction may be as approved by the Engineer.

4.	Welding.  Complete welding according to Subsection 504-3.01.8. Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval.  The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes that were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface.  For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole.  Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole.  Grind the welds smooth and flush with the adjoining pole and disk surfaces.  Repair the damaged finish according to Subsection 660-3.01.8.

5.	Removing and Replacing Improvements.  The Contractor shall complete the following work at the Contractor’s expense.

a.	Remove improvements that block completion of the work detailed in the Plans as specified herein.

b.	Reconstruct with new materials the non-reusable improvements the Contractor removed to complete the work.

c.	Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

d.	Reconstruct with new materials improvements damaged or removed by the Contractor not conflicting with the work and not scheduled for removal.

Nonreusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings.  Reusable improvements include the items that were made before installation.  Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition.  In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil.  Match the top of the topsoil with the bottom of the vegetative mat. Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621.  Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

Add the following:

9. 	Regulation and Code.  Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the Authority Having Jurisdiction.

10.	Failed Equipment and Workmanship.  For the term of the Contract, from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair failed workmanship.

Replace Subsection 3.03 with the following:

660-3.03 CONDUIT.  Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified.  Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits.  Install conduits of the sizes specified along the routes detailed on the Plans.  When routing is not shown, route conduits as directed by the Engineer.

- Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

- Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches.  Excavate, bed conduits, and backfill trenches according to Subsection 660-3.01.3, Excavating and Backfilling.

- Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods.  Jacking conduits into position is allowed.  However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

- If encountering obstructions during jacking or drilling operations obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 11/4 to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

- Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs.  To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box. At junction boxes where polyethylene conduits runs are to enter the junction box, install a 5 foot section of RMC on the horizontal end of the RMC sweeps.

- Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box.  Extend the ends a minimum of 2 inches beyond the inside wall of the box.

- Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs.  Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors.  Cover the holes with a wrap of approved filter cloth secured with 2 self-clinching nylon cable ties.

- Keep conduits clean.  Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends. Tapered or universal fit plugs are acceptable for temporary usage. Any permanent plug or cap shall be an approved watertight cap.

- At the low points of conduit runs, install sumps containing a minimum 2 cubic feet of coarse concrete aggregate material that conforms to Subsection 703-2.02.  Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

- Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary.  Install additional drains and aggregate sumps at the low spots, if any.

- Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 21/2 inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

- Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit.  Cut the same number of threads as found on the factory threaded ends.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.  Do not use slip joints or pieces of running thread pipe.

- Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

- When standard couplings cannot be used to join conduit components, use approved threaded unions.

- Bury a continuous strip of 4 mils thick, 6 inch wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a red background.

- When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

- In foundations, install 90 degree elbows and conduits of the size and quantity shown on the Plans.  Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

- Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct sealing compound.

- Install expansion fittings in conduits that cross expansion joints.

- Install a polypropylene pull rope with a minimum 200 pound tensile strength in future use or spare conduits, and reinstall the plugs.  Double back pull rope, at least two feet, into both ends of each conduit. Tapered or universal fit plugs are acceptable for temporary usage. Any permanent plug or cap shall be an approved watertight cap.

- The Contractor may install conduits larger than the sizes specified.  If used, it must be for the entire length of the run.  Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

- Clean existing conduits that will remain in service using a heavy duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch.  Clean the conduits before pulling in new cables and after removing cables to be removed or replaced as follows:

  - When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

  - Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

- When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit.  When extending existing conduits, add no more than a 90 degree horizontal bend to the extension.

- When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

- When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

- Remove the ends of abandoned conduits from junction boxes that will remain in service.

- When Plans call for connecting polyethylene conduit to RMC use a UL listed electrofusion coupler rated for direct bury application. The coupler must be rated for same wall thickness as the adjoining conduits. If electrofusion coupler fails to properly bond to conduits, the Engineer may give approval to use DuraLine Shur Lock type couplers or approved equivalent, but only after first attempting use of electrofusion couplers in each case. Thread the ends of the RMC with the same number of threads as found on the factory threaded ends of RMC.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

Replace Subsection 3.04 with the following:

660-3.04 JUNCTION BOXES.  Install precast reinforced concrete junction boxes of the types specified.  For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them.  For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them. Emboss the word WEATHER on the lids of all junction boxes that contain loop or sensor conductors. Emboss the word ELECTRIC on the lids of all junction boxes used to provide electrical service to RWIS installations.

Junction boxes for 120V/240V electrical service must be kept separate from junction boxes containing sensor conductors.

Junction Box Location

When shown, install junction boxes at the station and offset locations specified.  When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement.  If the 8 feet offset falls:

1.	In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility. When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

2.	In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

3.	Outside the right of way, install the boxes just inside the right of way line.

4.	In a raised median, install junction boxes near the center of the median.

5.	In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

6.	Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

7.	On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing Type 1A junction boxes in driveways and in locations subject to use by heavy trucks.  When shown near the ends of medians, install junction boxes at least 10 feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.  When installing copper signal interconnect cable use minimum size Type II junction boxes.

Four (4) Limitations

Limit the distance between adjacent junction boxes to the following dimensions:

1.	400 feet for conduits that contain signal interconnect cable only.

2.	300 feet for conduits, that exclusively contains two loop lead-in cables.

3.	300 feet for conduits that contain a single cable other than signal interconnect.

4.	190 feet for conduits, that contains more than one cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work; otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria.  In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade.  In seeded areas, install the tops of junction boxes to 2 inches below all other areas.

Bond junction box lids to an equipment grounding conductor according to Subsection 660-3.06.  Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box.  Drains shall consist of porous backfill material that conforms to Subsection 703-2.10.  Minimum drain dimensions include an 18" depth and a length and width equal to those of the junction box it drains.  Compact material under junction boxes as directed by the Engineer to prevent settlement of foundations, junction boxes and adjacent improvements.

In every new and reused junction box, install an electronic marker.  Conform markers to the American Public Works Association Standards including but not limited to:

- Color - red

- Material - high-density polyethylene

- Shape - round (ball like)

- Size - 4 to 5 inches in diameter

- Configuration - encapsulating an antenna tuned to the appropriate frequency for locating power

- Responsive range - up to 5 feet away from the locator device

- Environmental conditions - including extremes in temperature at the installation site

- Contain no internal power source

Acceptable marker manufacturers include:

- 3M, Dynatel EMS ball marker model no. 1402-XR

- Tempo (a Textron Company), Omni Marker

- Substituted, equivalent approved equal device

Replace Subsection 3.05 with the following:

660-3.05 WIRING. Install power conductors serving the cabinet sized such that their ampacity rating is greater than the cabinet total connected load after applicable diversity factors have been applied. Make wiring neat in cabinets by cabling wires together with self-clinching nylon ties. Terminate all spare conductors on terminal blocks. Attach all conductors, including spares, to terminal blocks with “spade” type terminal lugs. Furnish additional terminal blocks if enough locations are unavailable in existing terminal blocks.

- Do not pull conductors into conduits until the following conditions are met:

  - The prescribed clearances around conduit ends are provided,

  - Crushed rock sumps are installed under junction boxes,

  - Conduit ends protrude above the bottom of junction boxes within the prescribed range,

  - New conduits are free of material that became lodged in them during the completion of the work,

  - Reused conduits are cleaned according to Subsection 660-3.03,

  - Junction boxes are set to grade, and

  - Grounding bushings are installed on the ends of metallic conduits.

- Pull conductors by hand or by approved commercially built cable-pulling equipment that is specially designed for that purpose. Do not pull cable by any other means. Equip the cable pulling device with a force limiting circuit and force gauge.

- Use wire-pulling lubricant when placing the cables and conductors in conduit. Do not allow the tension of the wire or cable to exceed the manufacturer’s recommend allowable tension for the conductor or cable.

- When adding new conductors to a conduit with existing conductors, remove all conductors and clean the conduit with a mandrel or brush. Pull both old and new conductors through as a unit. In a new installation, pull all conductors through the conduit as a unit.

- Leave at least 1 foot of slack in the bottom of each signal or combination signal and lighting pole of each signal conductor or cable. Neatly leave at least 3 feet of slack illumination and signal conductor or cable curled up in the bottom of each junction box or splice location. All other cable types provide a minimum of 3-ft of slack conductor in each junction box and a minimum of 6-ft of slack conductor in the equipment cabinet prior to the terminal block.

- Separate the neutral for pedestrian push button circuits from the signal light circuit neutral.

- Run all signal and feeder conductors continuously without splices from a terminal block located in a cabinet, compartment, or signal head, to a similarly located terminal block. When modifying an existing signal system when specifically shown in plans, splice existing conductors (cables) to new conductors (cables) as required to complete the signal system. Make these splices when indicated in the plans.

- Route highway illumination cable through each lighting pole designated for connection to that cable’s circuit. Do not splice illumination cable between a load center and a pole or between poles. Join the individual conductors by using non-insulated, overlap type pressure connectors. Insulate with mastic-lined heat shrink tubing or 2 layers of one-half lapped UL listed electrical tape. Do not use wire binding screws, studs, or nuts. Stagger splices to minimize the overall diameter.

- Install all loops in 1-inch rigid schedule 80 PVC conduit in the roadway and to the nearest junction box. Run loop lead-in cable continuously without splices from the controller cabinet to the curbside detection junction box nearest the loop being spliced to the lead-in cable. Splice the loop(s) to the lead-in cable by soldering at the junction box and encapsulating in a waterproof splice kit.

Multiple loop configurations must have the individual lead-ins, multiple pair, or single pair brought to the controller cabinet for termination. Make series connection of loop lead-ins in the controller cabinet only. Wind all loops in the same direction with the starting lead marked with an “S.” Connect the black conductor of the pair shown in Table 660-1 to the “S” designated conductor of the loop. Connect multiple loop detectors in the same lane so that the adjacent loops are in alternating directions clock wise (CW), counter clock wise (CCW), etc.

- When splicing loop detectors to multi-pair loop lead-in cables, complete the work according to the following.

a.	See the Plans for the identifying number assigned to each loop detector and the loops assigned to each loop lead-in cable. Using this information, splice the loop detector tails to the paired conductors found in each lead-in cable, using the color code in Table 660-1.

b.	Remove a short section of cable jacket and only cut the shielded pairs dedicated to loop detectors being spliced. Run these pairs, without splices, to the controller cabinet.

c.	Solder the loop and lead-in conductors together using the pre-loaded low temperature solder with heat shrink tubing approved splice connector.

TABLE 660-1 
MULTIPLE PAIR LOOP LEAD-IN COLOR CONNECTION SCHEDULE

| Loop Detector Number | Colored Pair |
| --- | --- |
| The lowest numbered loop detector | Red and Black |
| The second lowest numbered loop detector | Blue and Black |
| The third lowest numbered loop detector | White and Black |
| The fourth lowest numbered loop detector | Green and Black |
| The fifth lowest numbered loop detector | Brown and Black |
| The sixth lowest number loop detector | Yellow and Black |
| Usually a spare pair | Orange and Black |

e.	Crimp spade terminals to the ends of the shielded pairs in the controller cabinet.

- Maintain the electrical isolation between shields and do not allow the drain wires to come in contact at any point other than the ground bus in the cabinet. Tie all drain wires to the ground bus at the controller cabinet.

- Encapsulate illumination/power cable splices in four piece molds that are held together with stainless steel hose clamps. Two pieces form a cylinder and two flexible end caps. Seal the ends and allow the conductor entry. Use molds with dimensions suitable for the splice made, encase the cable jackets, and fill with an insulating and sealing epoxy resin.  Furnish molds rated for 600 VAC operation, feature fill, and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, one splice may be used in the following cases:

a.	An in-line splice may be used when a planned cable run exceeds the length available from the manufacturer on a single spool of cable.

b.	In a run of 1,000 linear feet or more.

When a cable is spliced, it shall occur within an appropriately sized junction box or in the base of an electrolier designed for said splice.

Insert a loose woven polyester web that allows a full 1/4 inch of insulating compound to flow between the splice and the inside of the mold. Fill the PVC molds with epoxy resin that cures transparent, is nontoxic, is non-corrosive to copper, and does not support fungi or mold growth.

- Encapsulate all loop lead-in cable splices in rigid, transparent, PVC or PE approved tubing filled with re-enterable polyurethane electrical insulating and sealing compound. Furnish splice kits rated for 1000 volts AC operation and direct burial. When filling the mold bodies of loop lead-in cable splices, use a compound that provides re-entry capabilities.

- Permanently identify all cables and single wire conductors by labeling all pole bases and cabinets, at each detector loop tail/lead-in cable and illumination cable splices, and in junction boxes adjacent to lighting and signal poles. When modifying an existing system, label all new and existing lighting cables/conductors with circuit numbers at locations noted above. If the existing circuits are not identified, the Engineer will provide the required circuit numbers.

- Label the cables used in the signal and illumination systems with the following legends:

  - Use the legends included in Table 740-2, for the cables listed.

  - Use the loop number shown on the Plans to label each tail of all loop detectors and the paired loop lead-in conductors in the controller cabinet.

  - For interconnect cables, use the first letter of the direction the cable follows to the adjacent intersection on each cable. Add a number suffix if more than one cable is routed to the adjacent intersection.

Furnish the two types of identification tags listed below that feature hand written legends. Write the legends specified neatly and legibly, using a black marking pen recommended by the tag manufacturer. Replace at no expense to the State all identification tags the Engineer deems illegible.

- Use identification cable ties for labeling loop detector tails and the paired conductors included in each loop lead-in cable in the controller cabinet. Furnish identification cable ties made of nylon that feature a nonmagnetic stainless steel locking device embedded in the head and a tag attached "flag style" to the head. Use cable ties consisting of a single strap with a minimum size tag of 3/4 inch by 3/8 inch.

- To label all other cables, use cable tags made of nylon reinforced vinyl impervious to the elements and which will not tear. Provide tags with a 4 inch by 1-3/4 inch minimum size that attach flag style at one corner to a single strap. Furnish yellow tags for labeling all signal and interconnect cables and red tags for labeling lighting and feeder cables.

- Terminate the control and power cables as shown in Table 740-2, terminate all unused pairs with splices at junction boxes .

- Telemetry cable termination shall be coordinated with a signal technician. Provide type No. 66B3-50 terminal blocks as required.

- Wire luminaires using No. 10 AWG illumination tap conductors that run from the fused disconnect kit in the pole base.

Install a fused splice connector between the line and luminaire ballast tap conductors in the base of every pole equipped with a luminaire.

Attach the conductors to the connector halves with setscrew type pressure connectors. Provide the plug and socket assembly so that the fuse remains in the load side plug without exposing live metal parts when the connector separates and the coil springs are not included in the current carrying circuit.

Make the fused connectors readily accessible from the handhole. Install tap conductors to prevent slack when their ends touch the top of the foundation.

- Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

- Whenever conductors cannot be terminated as specified in the Plans in circuit breakers due to size, splice a piece of #8 AWG copper power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductors to 5 feet. Note: this splice is acceptable only if the overcurrent protective device protecting the #8 AWG conductors is rated 40A or less.

- Spare lighting conductors shall be capped in the pole bases and load centers by cutting the wire flush with the end of the insulation and bending the conductor back against itself and securing with three layers of electrical tape to prevent any possibility of making contact with ground or current carrying conductors.

Replace Subsection 3.06 with the following:

660-3.06 BONDING AND GROUNDING.  All installations must comply with the grounding and bonding requirements of NEC Article 250 and the following requirements:   Normally non-current-carrying conductive materials enclosing electrical conductors or equipment, or forming part of such equipment, including metallic cable sheaths, metal conduits, non-metallic conduit grounding wire, junction box lids and frames, cabinets, transformer cases, and metal posts and poles, must be electrically connected to earth ground, and must be connected together and to the electrical supply source in a manner that establishes an effective ground-fault current path. Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole. An equipment grounding conductor must be installed between the grounding lug near the base of the pole and the lighting fixture.

Install grounding bushings with insulated throats on the ends of metallic conduits.

Install an insulated or bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size #8 AWG grounding conductors, except in those conduits that contain circuit conductors larger than #8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installation or removal of conductors from existing conduits, retrofit with new equipment grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the equipment grounding conductor using copper braid with a cross sectional area equal to a #8 AWG and eyelet spaced at 6 inch intervals.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.

Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the #4 AWG grounding electrode conductor using irreversible compression type connectors at Portland cement concrete foundations.  For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 5 feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the handhole of each pole.

Bond slip base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the handhole of each pole.

Solidly ground one side of the secondary circuit of a transformer.

Install a 3/4 inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a #6 AWG bare stranded copper wire for the grounding electrode conductor. Furnish one piece bronze clamps with a hex head setscrew that are suitable for direct burial and for use with copper clad ground rods.

When routing a new conduit into an existing junction box or replacing an existing junction box, new and existing conduits shall have the grounding improved to current specifications.

Add the following subsections:

660-3.11 TERMINAL BLOCKS. Mount terminal blocks within cabinets so that all terminals are easily accessible from the front of the cabinet.

Label wire pairs clearly on both sides of the terminal block.

Terminate and solder all conductors, including unused spares, to “spade” type terminal lugs on the terminal block.

660-3.12 ACCEPTANCE TESTING & COMMISSIONING. Final sensor connections inside the RPU, repowering, testing, calibrating, and commissioning will be provided by the state’s O&M Contractors. Coordinate completion of this work to follow immediately after completion of the installation. Assist with repairs and modifications as required to ensure a fully implemented and operational station.

660-3.13 ARC FLASH HAZARD WARNING.  Label traffic controller cabinets, and other electrical equipment that is likely to require examination, adjustment, servicing, or maintenance while energized, to warn qualified persons of potential electrical arc flash hazards per NEC 110.16.  The labels must meet the requirements in NEC 110.21(B), and must contain the information required in NFPA 70E 130.5(H).

Replace Subsection 5.01 with the following:

660-5.01 BASIS OF PAYMENT.

Payment Includes labor, equipment, and materials required to provide fully functional traffic signals and lighting systems, permanent and temporary, using new equipment.  Remanufactured or rebuilt equipment will not be permitted.

Subsidiary to each Pay Item including but not limited to (Except when included as a separate Pay Item):

(1)	General construction requirements,

(2)	Bonding and grounding,

(3)	Bored Casings,

(4)	Completing tests,

(5)	Conductors,

(6)	Conduit,

(7)	Dewatering excavations,

(8)	Excavation, trenches in rock or soil, bedding, backfill for foundations, conduits, components,

(9)	Foundations including concrete to complete foundations,

(10)	J-boxes including adjustment to final grade,

(11)	Labeling conductors,

(12)	Maintaining temporary and existing electrical systems,

(13)	Minor routing changes directed by the Engineer

(14)	Preparing as-builts

(15)	Removal and disposal of existing/new unused foundations, conduit, conductors, and J-boxes,

(16)	Removing, repairing and replacing improvements

(17)	Removal of signs and reinstallations required to install foundations, conduits, and J-boxes,

(18)	Repairing damage to finishes on new equipment

(19)	Salvaging reusable equipment and materials and delivering to the local Maintenance and Operations station including but not limited to existing signal structure

(20)	Wiring

(21)	Replacing failed equipment, equipment components and repairing failed workmanship.

660 Pay Items do not include:  roadway planing, roadway paving, drainage structures, erosion, sediment and pollution control, signing, striping and pavement markings, traffic control, and components of the traffic signal communication system.

Providing new load center(s) size indicated on the plans will be subsidiary to the 661 Pay Items. The electrical utility service to the load centers that are scheduled to become a permanent part of the work shall be an incidental part of the installation of the load centers.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

660.0003.0000	Highway Lighting System Complete, Portage		Lump Sum

660.0003.0000	Highway Lighting System Complete, Railroad Entrance	Lump Sum

660.0012.0000	Underpass Lighting System Complete( Portage No. 1)	Lump Sum

660.0012.0000	Underpass Lighting System Complete( Portage No. 2)	Lump sum

660.0012.0000	Underpass Lighting System Complete( Twentymile)	Lump sum

660.2004.0000	Adjust Junction Box	Each

CFHWY00213 / CFHWY00308

SECTION 661
ELECTRICAL LOAD CENTERS

Special Provision

661-2.01 MATERIALS.  Add the following:

Anchor Bolts	Section 740-2.02

Load Center.  Replace the 1st paragraph with the following:

NEMA 3R enclosure constructed of .125” thick aluminum, with no external screws, bolts, or nuts.

CR661.1-0101201 / CFHWY00213

Equipment List(s) and Drawings.

Replace No. 1. with the following:

1.	Materials on the Qualified Products List:  The Qualified Products List does not apply to the 661 Pay Items.  Provide catalog cuts of materials to the Engineer for review and approval.

3.	Materials Not Requiring Certification:  Replace the 2nd sentence with the following:

Submit these materials for review and approval if included on the Materials Certification List (MCL) or requested by the Engineer.

Add the following materials:

Ground Rods.  Furnish one piece 3/4” diameter by 10 feet long copper clad steel rods.

Ground Rod Clamps.  Furnish one piece bronze clamps with a hex head setscrew that are suitable for direct burial and for use with copper clad ground rods.

Meters.  Furnish meter sockets and landing pads rated for 200 Ampere Service.

Photoelectric Controls.  Delete the first sentence and substitute the following:

Use three wire photoelectric controls that directly switch a circuit from one conductor to another.  Furnish two piece photoelectric controls that consist of a plug-in control unit and a locking type receptacle set in a cast aluminum adapter.

1.	Plug-in Control Unit.

Furnish photoelectric control units that consist of a light sensitive element connected directly to a normally closed, single-pole, single-throw, and control relay free of intermediate amplifications.  For highway lighting, use horizontal or zenith type sensing units that:

a.	Operate at voltages between 120 and 277 VAC, 60 Hz,

b.	Handle loads up to 1,800 volt-amperes,

c.	Operate at temperatures from -40 °F to +150 °F,

d.	Consumes less than 10 watts of power,

e.	Feature a 3-prong, EEI-NEMA standard, twist-lock plug,

f.	Turn-on between 1.0 and 5.0 foot-candles and turn-off at light levels between 1.5 and 5.0 times those at turn-on.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices used in the Control of Roadway Lighting.

Screen the photoelectric control units to prevent artificial light from interfering with normal photoelectric control operation.  Extend screens to the top of the control units.  Use 3 inch wide x 0.063 inch thick (min) aluminum meeting ASTM B209, Alloy 3003-H14.

2.	Locking Receptacles.

Furnish twist lock type, phenolic resin receptacles set in one of the following cast-aluminum adapters.

a.	For photoelectric controls installed on signal poles and load centers, furnish a mounting adapter with a threaded connection that fits conduit outlet bodies threaded for 1/2 inch rigid metal conduit, General Electric model MB-PECTL or approved equal.

b.	For photoelectric controls installed atop lighting poles (with mast arms,) furnish a pole top adapter:  equipped with a terminal block, made to slip over the ends of poles 3 1/2 to 4 1/2 inches in outside diameter, and secured by set-screws, General Electric model PTA-PECTL or approved equal.

661-3.01 CONSTRUCTION REQUIREMENTS.  Replace the 11th paragraph with the following:

Install two ground rods at least 8 feet apart at each load center.  Connect the neutral bus to the ground rods with a soft drawn bare copper grounding electrode conductor sized per the NEC, 6 AWG minimum.  Bond non-current carrying metal parts in each load center to the ground bus.  At Type 1 load centers, install one ground rod inside the base, readily accessible though the removable cover, and the second ground rod outside the base.  Route the grounding electrode conductor to the second ground rod through one of the knockouts.

Replace the 12th paragraph with the following:

Install photoelectric controls at the locations indicated. Orient photoelectric control units to face the north sky.  Install a screen to prevent artificial light from interfering with normal photoelectric control operation.

For photoelectric controls installed on load centers, install a Myers hub in a cabinet wall shielded from traffic.  To the hub, attach an assembly that consists of a Type LB conduit body, a length of conduit, and a Type C conduit body.  Fabricate the conduit at least 3 ft long and locate the photoelectric control 1 ft above the top of the load center.  Mount the photoelectric control adapter on the Type C conduit body.  Install a conduit hanger to brace the top of the conduit.

For photoelectric controls installed on signal poles, install a Myers hub in the center of the rain cap.  Attach a Type C conduit body to the hub with a close nipple.  Mount the photoelectric control adapter on the conduit body.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

For photoelectric controls installed on electroliers, install a pole top adapter.  When the photoelectric control is on a lighting standard with a slip base or frangible coupling style base, use an approved breakaway disconnect in the base of the light standard.  Restrain the cable in a similar manner as the illumination cable in the pole base.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

Add the following:

Coordinate new load centers with existing and or new service utilities.

Failed Equipment and Workmanship

For the term of the Contract from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair failed workmanship.

661-5.01 BASIS OF PAYMENT.  Add the following:

The following work is subsidiary to 661 Pay Items:

	All necessary hardware for mounting (shelf angles, rack, shelving, harness, etc.).

	Removing existing load centers being replaced with new load centers, their foundations, and ground rods.

	Payment of fees required by the local authority for electrical inspection(s) and the costs of correcting the deficiencies noted during the inspection(s).

	All work including, but not limited to, contacting and coordinating with the utilities for service; maintenance and usage payments until the Engineer provides the notice of final acceptance.

	Replaced failed equipment, equipment components and repaired failed workmanship.

CR661.1-010120

Special Provisions

Add the following Section:

- SECTION 669
AUTOMATED TRAFFIC RECORDERS

669-1.01 DESCRIPTION. This work shall consist of reconstruction, refurbishing, and installation of Automated Traffic Recorder (ATR) stations and construction of three (3) new Roadway Weather Information System (RWIS) sites. Refer to Section 660 Signals and Lighting for additional requirements.

ATR consists of inductive loops and piezoelectric sensors connected to a traffic counter. In each traffic lane, two inductive loops are separated by a specific travel distance and buried beneath the pavement. Two piezoelectric sensors are located adjacent each inductive loop, embedded in the pavement surface. Lead wires run in underground conduit from the sensors to a type CBA2 cabinet located at the side of the road. Inside the type CBA2 cabinet, the lead wires connect to the traffic counter. The traffic counter detects the presence and speed of passing vehicles from inductive loop signals. The traffic counter detects axle number and center-to-center axle spacing from the piezoelectric signals. Presence, speed and axle passage information is processed by the traffic counter to classify the number and type of vehicles, which is stored for later retrieval. ATRs are operated and maintained by personnel of the Highway Data Section (HDS); main office located at 2200 E. 42nd Ave., Anchorage, phone (907) 269-0876.

The ATR station will be equipped with a Temperature Data Probe (TDP), which consists of temperature sensors connected to a datalogger. Sampled conditions may include air temperature, pavement profile temperatures, and subgrade profile temperatures. Temperature sensors send voltage signals to the datalogger. Sensor voltage levels are processed by the datalogger to yield temperature information, which is stored for later retrieval.

The locations of traffic detection sensors and cabinets, shown on the Plans are approximate and the Engineer shall establish the exact locations in the field after consultation with the DOT/PF HDS.

The Contractor will furnish and install all components to assemble a complete and fully functional Environmental Sensor Station (ESS) as called for in the plans. These include but are not limited to:

- Hinged sensor support pole and foundation

- Data logger

- Anemometer/wind vane & anemometer interface

- Temperature/relative humidity/barometric pressure sensor

- Present weather sensor

- Non-intrusive pavement temperature sensor

- Pavement surface state sensor

- Precipitation gauge

- Vertical temperature data probe

- Cellular modem with antenna & cell extender

- Communication Utility modem

- Camera and PoE injectors

- Ethernet switch

- Photovoltaic solar panel

- Wind turbine

- Conduit, cables, conductors, grounding, support stands and poles, junction boxes, and cabinets

The work requires coordination and provision of utility services to the site as illustrated in the Plans, including power, direct connected communication and/or cellular data communications. Include connection fees with the Bid.

The Department will perform the RWIS site commissioning upon completion of the installation of the site.

669-1.02 REGULATIONS AND CODE.  Use materials and workmanship that conforms to the standards of the Underwriter's Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

Use electrical equipment that conforms to the standards of the National Electrical Manufacturer's Association, where applicable.

669-1.03 UTILITY SCHEDULE. Within 30 days after the Contract award, submit three (3) collated copies of a Utility Schedule identifying all actions required to ensure activation of electrical service and communication service prior to installation and commissioning of RWIS equipment at affected sites.

Create a separate list of chronologically and sequentially organized actions for affected RWIS station.

On the lists, include the following:

1. 	A description of the action.

2. 	When the action will occur.

3. 	The name, employer, position title and telephone number of the point of contact for initiating the action.

4. 	The name, employer, position title and telephone number of the party responsible for completing the action.

669-2.01 MATERIALS.  Unless otherwise stated, provide new materials that meet the following requirements:

1.	Wiring.  Subsection 660-3.05, Wiring.  Use single wire conductors and cables that have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, insulation type-letter designation, conductor size, voltage rating and the number of conductors if a cable.  Home run label all wires and cables in each junction box and cabinet; for example, W1SLA (for wire) and GaSLA (for cable) as shown on the Plans.

2.	Conduit.  Subsection 660-3.03, Conduit. Use galvanized rigid metal for conduits, except for PVC conduit forming the inductive loops. Provide grounding bushings with plastic-sleeves to minimize the potential for insulation damage during wire pulls. Make all conduit entries through the bottom of cabinet enclosures. No cuts through the sides or top of cabinets are permitted.

- Junction Boxes.  Subsection 660-3.04, Junction Boxes.

4.	Terminal Blocks.  Mount Terminal Blocks horizontally as shown in the plans.  Use terminal blocks with nickel, silver or cadmium plated brass binder-head screw terminals.  Use barrier type terminal blocks rated 600 VAC at 20 Amps, sized for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips.

5.	Presence Loops.  Use UL listed IMSA specification #51-5-1984 single conductor PVC nylon with tube jacket, type THHN, #14 AWG conductors for detector presence loops.

Use twisted pairs of 18 AWG stranded tinned copper wire for multiple pair loop lead-in cable.  Each twisted pair shall have its own 20AWG tinned copper drain wire.  An aluminum foil shield shall surround each individual bundle of twisted pair and drain wire. Multiple pair loop lead-in cable shall have an overall PVC or PE outer jacket.

- Electrical Load Centers. Use NEMA Type 3R Electrical Load Centers and provide a 120/240 V 100 amp single-phase, three-wired circuit electrical service.

- Style CBA2 Cabinets.  Cabinets shall meet or exceed a UL 50, NEMA Type 3R rating. Cabinets shall be third party certified as an assembly. Style CBA2 cabinets shall meet the following requirements:

- Cabinet Dimensions. Unless otherwise shown on the Plans, the cabinet shall be 48 inches high, 27 inches wide, and 16 inches deep.

- Cabinet Construction. Construct the cabinet and door from 5052-H32 or better unpainted sheet aluminum alloy with a minimum thickness of 1/8 inch and a smooth grain finish on the exterior. Ensure that welds are neatly formed and free of cracks, blowholes and other irregularities. Ensure inside and outside edges of the cabinet are free of burrs. Design the cabinet with a loped top to prevent the accumulation of water on its top surface.

- Door. Use double flanged door opening on four sides to prevent dirt and liquids from entering the enclosure when the door is opened. Provide a door restraint to prevent door movement in windy conditions. Provide a cabinet door that encompasses at least 80% of the cabinet frontal surface area and is hinged on the right side when facing the cabinet. Furnish the door with a gasket that satisfies the physical properties found in UL508 table 21.1 and forms a weather tight seal between the cabinet and the door. Use a hinge that is continuous and made of stainless steel or at least 2.2 mm thick aluminum. Securely weld the hinge along a quarter, or more, of its length or bolt the cabinet using stainless steel bolts and non-slip nuts.

- Latch/Lock. Use a 3 point draw roller type latching mechanism. Use either stainless steel or cadmium plated, Type II Class 1 or better center catch and pushrods. Use rollers with a minimum diameter of 3.4 inch made of nylon. Furnish a stainless steel operating handle with a ¾ inch shank. Use a Corbin #2 lock keyed lock that matches existing HDS cabinets. Furnish two keys with each lock.

- Ventilation. Provide ventilation using louvered vents in the front door with a removable air filter. Ensure lovers satisfy the NEMA rod entry test for 3R ventilated cabinets. Provide filters that cover the vents and are held firmly in place with bottom and top brackets and a spring-loaded top clamp. Vent exhaust air out between the top of the cabinet and the door.

- Shelves. Mount adjustable equipment shelves on “C” factory mounting channels inside of cabinet and support them on both sides. Mount 2 vertical channels on both sides of the cabinet and on the back, for a total of 6 inside each CAB2 cabinet. Construct shelves from 5052-H32 or better sheet aluminum alloy with a minimum thickness of 1/8 inch. Provide a shelf with a minimum depth of 10 inches. Ensure that shelves are adjustable to within 4 inches of the bottom and to within 8 inches of the top of the cabinet.

- Keyboard Tray. Mount a retractable tray as shown in the Plans.

- Circuit Breaker Panel. Ensure the circuit-breaker panel conforms to the UL67 and NEMA PB1 standards. Use a MLO, single-phase, 3 wire configuration circuit breaker panel rated at 70 Amp (minimum) 120/240 Volts in a NEMA Type 2 enclosure with separated neutral and ground buses. Unless shown otherwise in the Plans, or described herein, provide two 20 amp single pole type circuit breakers with a minimum short-circuit interrupting rating of 10,000 AIC. Circuit breaker #1 will serve the utility and equipment receptacles, and circuit breaker #2 will serve the thermostatically controlled outlet, cooling fan, and cabinet light.

- Transient Voltage Surge Protection. Provide transient voltage surge protection, rated at a minimum 500 Volts at 3000 Amps integral to the circuit breaker panel, or integral to each individual circuit breaker.

- Interior Light. Provide a fluorescent, 120-volt single-tube lamp interior light fixture rated at 13 watts minimum with ballast that will start the lamp at temperatures of 0° F. Provide a single pole, illuminated toggle switch, mounted inside of the cabinet door to control the light.

- Cooling Fan. Provide a thermostatically controlled fan in the top of the cabinet that operates at a settable high temperature limit and exhausts air through a filtered and hooded vent at the top front of the cabinet. Set an integral thermostat at a temperature lower than the thermostat noted in Item “M” below so that the auxiliary thermostat controls the fan, and not any integral thermostat.

- Thermostatically Controlled Outlet. Ensure that a thermostatically controlled single duplex outlet operates at a settable low temperature limit.

- Thermostats. Provide remote bulb-type thermostats with SPDT contacts, rated for 16 amps @ 120 VAC for combined motor and resistive loads, for the for the thermostatically controlled outlet and cooling fan use Tradeline T6031A1029 (equal or better), White Rogers, Johnson Controls, or Sunne brand thermostats. Ensure the thermostats for the “Thermostatically Controlled Outlet” have a contact that closes on lowering temperature and set at 50° F. Provide a thermostat for the “Cooling Fan” that has a contact that closes on rising temperature and set at 90° F. Mount sensing bulbs as shown on the Plans.

- Conduit, Raceway, and Layup. Provide EMT, liquid tight, metal flex or metal clad conduit for wiring on terminal blocks and neatly train within the cabinet using wiring duct or ties.

- Certification. The Cabinet Assembly consists of the cabinet itself and high voltage (greater than 24 volts) components that are permanently installed, including the circuit breaker panel, receptacles, light and fan as shown on the Plans or described herein. Obtain certification that the cabinet and associated permanently installed equipment, as a unit, complies with recognized applicable national standards through an authorized local or national testing agency or fabrication shop that complies with ANSI Z34,1-1987 “Third-Party Certification Programs for Products, Processes, and Services”, including but not limited to: Electrical Testing Laboratories (ETL), Underwriters Laboratories (UL), Canadian Standards Association (CSA), Electro Test Incorporated (ETI) or other certified testing agency recognized by the Labor Standards & Safety Division of the State of Alaska Department of Labor.

- Ambient Air Temperature Sensor. Provide one Campbell Scientific 107 Temperature Probe meeting the following requirements: Cable Length = 50 feet.

- Cabinet Orientation. Unless the orientation is otherwise shown or noted on the plans, install ESS cabinets and generator building with the doors facing away from the roadway.

- Measurement and Control Datalogger. Provide a Campbell Scientific (CSI), Model CR1000X-XT-SW-NC datalogger.

- Pavement Temperature Sensor. Provide a Campbell Scientific, Model 105E-L sensor.

- Solar Radiation Shield. Provide a Campbell Scientific, Model 41303-5A shield.

- Heater. Portable heater rated 1200-15000 watts @ 120 VAC, fan forced, cord connected electric heater. Broan Model 6201 or equal. Single stage thematically controlled heater connection power cord, rated 16 at 120 VAC. 30oF to 100oF range. Sure-stat Cat #T118P or equal.

- Ground Temperature Probe. Provide a Campbell Scientific, Model CS230-L92-S15-E0, Part No. 32279-69 Ground Temperature Probe meeting the following requirements

  - Cable Length. 50 m

  - Internal probes 15

| Internal Sensor | Depth (m) |
| --- | --- |
| 1 | 0.0 |
| 2 | 0.0762 |
| 3 | 0.1524 |
| 4 | 0.2286 |
| 5 | 0.3048 |
| 6 | 0.4572 |
| 7 | 0.6096 |
| 8 | 0.7620 |
| 9 | 0.9144 |
| 10 | 1.0668 |
| 11 | 1.2192 |
| 12 | 1.3716 |
| 13 | 1.5240 |
| 14 | 1.6764 |
| 15 | 1.8288 |

- Piezoelectric Sensor, Class II. Locate 10 foot long piezoelectric sensor as shown in the plans.

  - Center Core. 16 gauge, flat, braided, silver plated copper wire.

  - Piezoelectric Material. Highly compressed piezoelectric copolymer, P(VDF-TrFE).

  - Outer sheath. 0.406 mm thick brass. CDA-260, ASTM B 587-88.

  - Final Dimensions. 1.4 inch wide X 1.16 inch thick; 0.13 mm.

  - Insulation. Insulation resistance between core and shield: > 500M ohms.

  - Piezoelectric Coefficient. ≥20 pC/N- nominal.

  - Passive Signal Cable. RG 58 type with an underground/direct burial rated outer jacket. The OD of the cable is 1/5 inch. The nominal capacitance of the cable is 89 pF/m.

669-3.01 CONSTRUCTION REQUIREMENTS.

1.	Wiring.

  - Referenced Requirements. Subsection 660-3.05, Wiring.

  - Termination. Terminate unused pairs at junction boxes within splices.  Terminate unused pairs in terminal blocks at cabinets.  Terminate and solder conductors, including unused spares to “spade” type terminal lugs at terminal blocks.

  - Relief. Provide at least 2 feet of slack cable for wiring in each junction box and at least 6 feet of slack cable available in the equipment cabinet before the terminal block.

  - Labeling. Label wiring in junction boxes and at terminal blocks.

2.	Conduit.

- Referenced Requirements. Subsection 660-3.03, Conduit, or as indicated on the Plans.

- Pull Cords. Leave nylon pull cords in all conduits larger than 1 inch and in spare conduits.

- Bushings.  Ensure that plastic or plastic-sleeved bushings are in place before wire pulls are performed.

3.	Junction Boxes.

- Referenced Requirements. Subsection 660-3.04, Junction Boxes, or as indicated on the Plans.

- Voltage Limitation.  Junction boxes used for ATR installations shall not contain wiring of systems at or greater than 24 V or conduits carrying wiring of systems at or greater than 24 V.

4.	Terminal Blocks.

- Terminal Block Placement. Mount terminal blocks within cabinets so that terminals are easily accessible from the front of the cabinet.

- Labeling. Clearly label terminal blocks and wire pairs on the block.

- Termination. Terminate and solder conductors, including unused spares to "spade" type terminal lugs

5.	Presence Loops.

- Placement Design Adherence.  The Plans are not schematics; installation of the presence loops shall closely conform to the location and layout of conduit runs shown in the Plans.  The contractor shall notify the Project Engineer 14 days prior to saw cutting the pavement for approval of the site layout.

- Presence Loop Dimensions.  Unless otherwise noted on the plans, form presence loops using four turns of wire, making 6 feet square with a tolerance of ± 1 inch.

- Presence Loop Dimensions for On-Ramps and Off-Ramps. Form presence loops in On-Ramps and Off-Ramps using four turns of wire, making a rectangular 8 feet wide and 6 inch long with a tolerance of ± 1 inch.

- Lead-in Conduit. Place lead-in conduits straight and perpendicular to the centerline of the road from the edge of pavement to the presence loops.

- Presence Loop Alignment. Center presence detector loops in the traffic lane with a tolerance of ± 1 inch.

- Presence Loops in Asphalt.

- Loop Placement. Locate presence loops 16 feet from leading edge to leading edge unless otherwise noted on the Plans with a tolerance of ± 1 inch.  Align presence loops in adjacent lanes within a tolerance of ± 1 inch.

- Compaction tests.  Compaction test requirements are at the discretion of the Engineer.

- Piezoelectric Sensors.

  - Manufacturer’s Recommendations. Install piezoelectric sensors according to AVC equipment and piezoelectric sensor manufacturer’s recommendations. The piezoelectric sensor manufacturer’s representative or a piezoelectric sensor manufacturer-certified installation technician must observe and approve piezoelectric sensor installations.

  - Placement Design Adherence. The Plans are not schematics; install the piezoelectric sensors as close as possible to the locations and layouts of conduit runs shown in the Plans.

  - Saw Cut Requirement. Install piezoelectric sensors in saw cut slots in final pavement. “Block outs” are not allowed.

  - Coaxial Cable. Run coaxial cables to the equipment cabinet without splices. Terminate on the specified terminal block, with at least 6 feet of slack cable available in the equipment cabinet before the terminal block.

  - Lead-in Conduit. Install lead-in conduits from edge of pavement to the piezoelectric sensors straight and perpendicular to the centerline of the road. Install and cap lead-in conduits for piezoelectric sensors at the sensor end with tape or sealant before paving. Extend lead-in conduits beyond the edge of the pavement. Completing lead-in conduit runs to junction boxes and cabinets may be done before or after paving.

  - Piezoelectric Sensor Placement. Center each piezoelectric sensor in the travel lanes between sensors adjoining inductive loops unless otherwise noted on the Plans or directed by the Engineer. Install piezoelectric sensors with a tolerance of ± 1 inch.

  - Piezoelectric Sensors in New Asphalt. Install piezoelectric sensors in new asphalt pavement only after three days of normal traffic has passed over the final paving.

- Cabinets.

  - Cabinet Placement and Orientation.  Install cabinets out of the Clear Zone with the doors facing away from the road.  Unless the orientation is otherwise noted on the plans.

  - Conduit Entry.  Install conduit entries for above-ground enclosure through the bottom of the enclosure.  No conduit runs shall be cut through the sides or top of above-ground enclosure.

  - Style CBA2 Cabinets Mounting. Mount style CBA2 cabinets on 4 inch GRMC or DN100 galvanized pipe and support with reinforced concrete foundations shown on the Plans.

- RWIS

  - Prior to installing conduit, conductors, sensors, cameras, or cabinets, notify the Engineer in writing, a minimum of 3 working days prior to installation. The Engineer shall be present to approve the installation prior to final burial or encasement. Correct any unacceptable installations and then request reinspection by the Engineer for completeness prior to burial or encasement. Uncover, remove and replace any burial or encasement not approved by the Engineer.

  - After staking RWIS ESS components, verify that there will be no overhead or underground utility conflicts. Locate and protect all existing underground and overhead utilities. The location of cables, conduits, junction boxes, foundations, and poles that are shown on the plan sheets are approximate and it is the Contractor's responsibility to verify the actual locations when working in the area. See Subsection 105-1.06.

9 	Utilities.

  - Electrical. Provide and install the Load Center as required per the Plans, specifications and the requirements of the appropriate Electrical Utility. Provide and install wiring from the load center to the equipment in the cabinet. Request inspection of the Load Center by the Department of Labor, Division of Mechanical Inspection (DOL/DMI). After approval of the load center by the DOL/DMI, inform the Engineer as to when electrical service is needed at the load center, with sufficient time to enable the HDS to schedule the installation with the Electrical Utility before commissioning of the equipment. The HDS will make arrangements in writing with the Electrical Utility to establish billing accounts. The Electrical Utility will provide service to the Load Center upon request of the Engineer.

  - DSL. Provide and install the phone line from the NID service box to the cabinet and connect to modem to ensure DSL connection.

  - Telephone. Install conduit between equipment with new service and to within 5’ from utility service connection location.

- Asphalt Pavement Roughness. No transverse seams, joints or roughness within 50 feet of any inductive loops placed in asphalt pavement section is allowed. Test the finished surface of the asphalt with a straightedge 10 feet long. Ensure that the surface does not vary more than ¼ inch from the lower edge of the straightedge within 50 feet of sensors at the ATR installations. At the Engineer’s discretion, run an inertial profiler  or a profilograph equipped with a chart recorder down each wheelpath of each lane for a distance of 50 feet before and after the ATR installation. HDS will supply the profilograph for the Contractor’s personnel to operate. Ensure that the asphalt surface as recorded by the chart recorder does not vary more than ¼ inch in 10 feet.

- Field Inspection. Notify the Engineer in writing a minimum of 3 working days in advance (excluding Saturday, Sunday and State or Federal Holidays) before installing conduit/wiring, inductive loops, bending plate equipment, piezoelectric cable, axle sensors, and cabinets. The Engineer will be present to approve the installation before backfill placement and paving. At the Contractor’s expense, correct and allow the Engineer to re-inspect unacceptable installations for completeness prior to backfill placement and paving. The Contractor shall be required to excavate, remove, and replace all installations backfilled or paved without prior approval by the Engineer at the Contractor’s expense.

- Failed Equipment and Workmanship. For the term of the Contract, from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair workmanship.

669-3.02 ACCEPTANCE TESTING.  Perform acceptance testing on ATR installations.

- General Tests.	Perform  tests  for  the  ATR  installations  according  to  subsection  660-3.01, Installation Details.

- AVC Acceptance Tests.

  - Scope and Governance. In addition to the General Tests, perform Acceptance Tests on AVC installations. AVC acceptance tests govern acceptance or rejection of the AVC installation.

  - Manufacturer Participation. Observe acceptance tests and assist the AVC counter manufacturer’s representative, or an AVC counter manufacturer-certified installation technician.

  - Highway Data Section Participation. Before beginning AVC Acceptance Tests, notify the HDS Manager 907-269-0876 through the Engineer, a minimum of 3 working days before proposed testing (excluding Saturday, Sunday and State or Federal Holidays). Notification includes descriptions of the proposed test vehicles. A representative of the HDS approves descriptions of the proposed test vehicles in writing before testing and be on-site during final acceptance testing. Provide a tabulated listing of each vehicle’s gross weight and measured axle spacing to the HDS representative before testing. The HDS representative must approve scheduling of data sampling and testing for each lane.

  - Results Certification. The Highway Data Manager or designated representative shall certify in writing when the installation has met the accuracy requirements of the acceptance tests.

  - Acceptance Test Procedure. Perform the Acceptance Tests as follows:

Acquire a set of test data for the AVC sensor array. Obtain test data by passing test vehicles over the AVC sensors in each lane. Test data consists of 10 valid samples per lane, for each of 3 test vehicles. Test data samples will include FHWA class designation and computed axle spacing for each sensor pass.

.To be considered valid, obtain sample data under the following conditions:

The test vehicle must maintain good lane discipline while traversing the entire sensor array.

To be considered valid, obtain sample data under the following conditions:

The test vehicle must maintain good lane discipline while traversing the entire sensor array.

    - The test vehicle must maintain a constant speed, between 40 mph and the maximum speed limit, while traversing the entire sensor array.

    - Acquire data for a particular lane using the same group of 3 test vehicles.

    - Sample data from successive sensor passes of each test vehicle.  Data may not be omitted or included out of order for any 10 samples.

    - Sensor passes for the 3 classes of vehicles may be intermixed.

    - Sensor passes for multiple lanes may be acquired simultaneously.

  - Accuracy Requirements. The Automated Vehicle Classifier must meet the following requirements separately in each lane:

    - The AVC  system  correctly assigns  FHWA class  designation  for  9  out  of  10 successive sensor passes of each vehicle class.

    - The  AVC  system  computes  axle  spacing  to  within  6  inches  of  the  actual measurements, for 9 out of 10 successive sensor passes of each vehicle class.

  - Test Vehicles. Provide, and make arrangements for; test vehicles and drivers as needed for the acceptance testing.

The group of three test vehicles shall consist of one each of the following:

    - A two axle, six wheel, single unit vehicle (FHWA Class 5)

    - A three axle, ten wheel, single unit vehicle (FHWA Class 6)

    - A  five  axle,  eighteen  wheel,  single  trailer  vehicle  (FHWA Class  9),  with high-cube-rated (HCR) trailer

  - Class 5 Vehicles. Class 5 vehicles shall meet the following requirements:

    - Spacing between steering and drive axles of 13 feet to 23 feet

    - Weight on the steering axle between 2,200 lb and 12,000 lb.

    - Weight on the driving axle between 7,000 lbs and 18,000 lb.

  - Class 6 Vehicles. Class 6 vehicles shall meet the following requirements:

    - Spacing between steering axle and the drive axle group of 13 feet to 23 feet

    - Spacing between the drive axles of 4 feet to 6 feet

    - Weight on the steering axle between 6,000 lb. and 12,000 lb

    - Weight on the drive axle group between 20,000 lb. and 37,500 lb...

  - Class 9 Vehicles. Class 9 vehicles shall meet the following requirements:

    - Spacing between the steering axle and the drive axle group of 13 feet to 23 feet

    - Spacing between the drive axles of 4 feet to 6 feet

    - Spacing between the drive axle group and the trailer axle group of 25 feet to 45 feet

    - Spacing between the trailer axles of 4 feet to 6 feet

    - Weight on the steering axle between 6,000 lb. and 12,000 lb.

    - Weight on the trailer axle group between 20,000 lb. and 37,500 lb.

  - Vehicle Loading. Ensure that three-test vehicles are loaded with non-shifting material to a minimum of 50% of legal load during testing.

  - Tire Inflation. Ensure that tires on the three-test vehicles are inflated to recommended pressures during testing.

  - Weighing Method. The gross weight of each test vehicle and the weight of each test vehicle’s axle groups shall be determined by weighing on a static scale at a scale house operated by the State of Alaska Department of Commerce, Division of Weights and Measures.

An axle group is defined as any two axles whose centers are within 8 feet of each other. The Class 5 and Class 6 test vehicles each have two axle groups.  The Class 9 single trailer test vehicle has three axle groups.

669-3.05 DELIVERABLES.  Submit deliverables to the HDS before final approval of the work or as otherwise called for herein.

- Materials Submittal.

  - Format and Contents. Provide a Materials Submittal of proposed equipment and materials for the ATR installations. The Materials Submittal shall consist of three collated copies of an equipment and materials portfolio. Each identical portfolio shall contain information of sufficient detail to determine the suitability of the equipment and materials proposed.

  - Table of Contents. Each portfolio shall include a table of contents listing each item's intended uses, item description, product name, manufacturer, model or part number and reference to associated information within the portfolio.

  - Reference Drawings. The Materials Submittal shall include a detailed shop drawing of each equipment cabinet showing the location of mounted components.

  - Delivery Interval. Deliver Materials Submittal for review and approval of the Highway Data Supervisor within thirty days following award of the Contract.

  - Liability. The State of Alaska will not be liable for any materials purchased, labor performed, equipment used or delay to the work before equipment and materials have been reviewed and approved.

2.	As-Built Plans.

- Prepare four complete sets of as-built plans, which will be current with the construction. These as-built plans shall detail construction changes made to the ATR design and include the following information on the appropriate sheets:

- Location and depth of inductive loops, piezo sensors, and conduit runs and scales.

- Locations of equipment cabinets and junction boxes.

- Station and offset of junction boxes

- Present three sets of as-built plans to the Engineer, and affix one set to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation in a waterproof, clear plastic holder.

- Redlines of full size construction plans will be acceptable as-builts.

3.	Photographs.

- Provide digital photographic prints CD format CD ROMs documenting sensor installations.

- Deliver photographs and CD ROMs organized in one or more white colored, D-ring style, 3 ring binders with clear insert overlays on fronts and spines.  CD ROMs will be placed in CD storage sheets inside the binders.

- The photographs shall show the inductive loops and conduit in place before covering with gravel and pavement for asphalt pavement sites, or before covering with epoxy compound for concrete pavement sites.  The photographs shall include:

- Two or more overall views of each ATR installation showing placement of the inductive loops.

- One or more views of each loop showing the loop and the conduit to the nearest junction box.

- One or more views of each piezo sensor conduit showing the coaxial cable, saw cut, and conduit to the nearest junction box.

- One or more views of each temperature sensor showing the lead cables, saw cut, and conduit to nearest junction box.

- Two or more overall views of the installation showing placement of the sensors, ESS pole, and cabinet.

- Test Results. Written or printed copies of the final results of tests, signed by the Contractor, shall be provided to the Engineer before acceptance of the Automated Traffic Recorder Installation.

- Manuals. Provide to the Highway Data Manager installation, repair, and operation manuals for Automated Traffic Recording equipment supplied by the Contractor.

- Materials.

- Provide to the Highway Data Manager any ATR equipment, sensors, and epoxy grout remaining after installation.

- Palletize the Deliverable Materials.

- Group the contents of each pallet by like items.

- Attach to each pallet a sealed plastic pouch containing complete copies of Material Safety Data Sheets that apply to the contents of that pallet.

- Provide an itemized list of Deliverable Materials. For each item, the list shall detail:

- Item description: including nature of the item, brand name, manufacturer name, model number, type number and serial number.

- Item condition

- Item quantity

- Provide complete copies of Material Safety Data Sheets that apply to the Deliverable Materials.  Attach Material Safety Data Sheets after the last page of the Deliverable Materials list.

669-4.01 METHOD OF MEASUREMENT. See Section 109 and the following:

Automated Traffic Recorder will be measured per Lump Sum. Roadway Weather Information Systems shall be measured per Each for Type A and Type B RWIS installations. RWIS installations at Ingram Creek and Glacier Creek are Type A. RWIS Installation at Portage is Type B.

669-5.01 BASIS OF PAYMENT.

The Contract unit price for Automated Traffic Recorder installations shall be full compensation for furnishing all equipment, labor and subsidiary materials required for completion of a site for which there is no specific item in the Plans is subsidiary to the 669 item. This includes but is not limited to:

- backfill materials,

- seeding,

- topsoil,

- removal of structures and obstructions,

- structural excavation for conduits and minor structures,

- work in support of utilities as specified in Subsection 105-1.06,

- as-built plans,

- providing the manufacturer’s representative,

- acceptance testing,

- j-boxes,

- CBA cabinets,

- rigid conduit,

- loops,

- piezoelectric sensors,

- TDP's,

- surface temperature probes,

- ambient air sensors, and

- other ATR equipment or work as shown on the plans.

Wet cutting with a concrete saw for piezoelectric sensor installations are subsidiary to 669 items. Replacing failed equipment, equipment components and repairing failed workmanship is subsidiary to 669 Pay Items.

The quantity to be paid for each Roadway Weather Information System Installation shall be full compensation for furnishing all equipment, labor and subsidiary materials required for completion of a site for which there is no specific item in the Plans is subsidiary to the 669 item. This includes but is not limited to: conductors, conduit, junction boxes, sensors, cameras, support poles and foundations, excavation, backfill materials, cabinets, bollards, as-built plans, acceptance testing, and calibration required for these installations.

Installation of cellular service will be subsidiary to the 669 Pay Item.

Providing new load center(s) size indicated on the plans will be subsidiary to the 661 Pay Items. The electrical utility service to the load centers that are scheduled to become a permanent part of the work shall be an incidental part of the installation of the load centers

Withholding:  To ensure full compliance under this Section, twenty percent (20%) of the billings for each 669 item shall be withheld until deliverables have been provided to the Engineer as required and approval of the deliverables by the HDS has been received in writing.

Payment will be made under:

Pay Item No.							Pay Item									  Pay Unit

669.2000.0000 	Traffic Data - Automated Traffic Recorder	Lump Sum

669.2012.00A	RWIS ESS, Type A	Each

669.2012.00B	RWIS ESS, Type B	Each

CFHWY00213

SECTION 670
TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Pavement Markings as shown on the Plans and as directed.

Pavement Marking Type:  Methyl Methacrylate (MMA)

670-2.01 MATERIALS.  Replace the material reference,

“Methyl Methacrylate Markings							Subsection 712-2.17”, with,

Methyl Methacrylate Pavement Markings				Subsection 712-2.17

Add the following:

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.  Replace No. 4 with the following:

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

SURFACE APPLIED

Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 60 mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of 60 mils.

INLAID

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

(1)	Longitudinal Markings.  Groove the pavement to a depth of 250 mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 250 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Groove the area for inlaid markings to a depth of 250 mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 250 mils.

(b)	Roundabouts:

As designated on the plans, groove the area for inlaid markings in roundabouts to a depth of 500 mils.  Apply markings to yield a thickness of 500 mils.

(c)	Gore Markings:

Diagonal gore markings will not be inlaid unless shown in the Plans.

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01)

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Replace Subsection 670-3.06 with the following:

670-3.06 TOLERANCE FOR LANE STRIPING.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measured from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete No. 2.

Replace No. 3 with the following:

3.	Each.  Pavement markings using letters, numbers, and arrows will be measured on a unit basis with each separate word or symbol constituting a unit.  Railroad Markings will be measured by the complete unit shown for each lane of travel.

Replace No. 4 with the following:

4.	Foot Basis.  Longitudinal pavement markings, transverse, and gore markings, surface applied or inlaid will be measured by the linear foot of 4 inch wide line.  Wider striping will be measured in multiples of 4 inches.

670-5.01 BASIS OF PAYMENT.  Add the following:

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with pavement markings are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Temporary pavement markings and removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

Add the following:

Project CFHWY00213 will be paid under 670.2003.____; 670.2006.____; 670.2007.____; 670.2008.____.  Project CFHWY00308 will be paid under 670.0010____.

Add the following Pay Items:

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 670.0010.____ | Methyl Methacrylate Pavement Markings | LS |
| 670.2003.____ | MMA Pavement Markings, Longitudinal Surface Applied | LF |
| 670.2004.____ | MMA Pavement Markings, Symbols and Arrow(s) Surface Applied | Each |
| 670.2005.____ | MMA Pavement Markings, Transverse and Gore Surface Applied | LF |
| 670.2006.____ | MMA Pavement Markings, Longitudinal Inlaid | LF |
| 670.2007.____ | MMA Pavement Markings, Symbols and Arrow(s) Inlaid | Each |
| 670.2008.____ | MMA Pavement Markings, Transverse and Gore Inlaid | LF |

CR670.1-110812R / CFHWY00213 / CFHWY00308

Special Provision

Add the following Section:

SECTION 682
UTILITY POTHOLING

682-1.01 DESCRIPTION.  Expose subsurface utilities using a vacuum-extract truck.  Record the location of the utility(s). Backfill the pothole and dispose of waste materials.

682-2.01 MATERIALS.

Backfill Material:			Aggregate Base Course, Grading D-1		Section 703

Asphalt Patch Material:		Hot Mix Asphalt Type II, Class B				Section 401

682-3.01 CONSTRUCTION.  Submit the utility potholing schedule to the Engineer and utility companies not less than 7 days before starting potholing.

Deliver the vacuum-extract truck to the job-site with the debris tank empty.

Expose the subsurface utilities.  Log the as-built information, subsection 682-3.02.  Backfill the pothole immediately after the Engineer accepts the logged data.  Backfill the first 6 inch lift using the excavated material, compact the material.  Backfill the balance of the pothole using Aggregate Base Course, Grading D-1, compact the material.  In paved areas, use Hot Mix Asphalt Type II, Class B to patch over the pothole, match the thickness of the surrounding pavement.

Dispose of excavations off-site.  Before beginning potholing, provide to the Engineer a certificate, signed by the owner or owner's representative, identifying the disposal site and acceptance of the project potholing excavations.

Utilities damaged by the potholing operation require the Engineer to be immediately notified.  The Contractor is responsible for the repairs and the associated costs.  Contact and coordinate repairs with the utility owner.

682-3.02 AS-BUILTS.  Create a utility pothole log, as-built, recording for each pothole: the date of potholing operation, utility type and size, station, offset, elevation, groundwater, and other pertinent data.  Survey the utility location using the project horizontal and vertical control; comply with the requirements of Section 642.  Submit the completed log to the Engineer within two working days following the completion of the pothole excavation.

682-4.01 METHOD OF MEASUREMENT.  The pay unit, contingent sum, is measured by the hour of work performed.

682-5.01 BASIS OF PAYMENT.  Pay Item No. 682.2000.____ is paid at $450/hour for the work to pothole; expose the utility(s), backfill the hole, patch disturbed pavement and dispose of excavations.  The paid time includes the work; labor, and the fully operated vacuum truck or combination of vacuum truck and other Engineer approved equipment engaged in potholing at the area(s) identified in the Plans and/or identified by the Engineer.

Travel time to and from the project, idle time, maintenance and repairs (labor, material and time) are incidental and not included in the measured time.

As-built, utility pothole log, per subsection 682-3.02, will be paid under Section 642.

Potholes for the Contractor's information and potholes not accepted by the Engineer will not be paid for by the Department.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 682.2000.____ | Vac-Truck Pothole | CS |

CR682-010114R

Special Provision

Add the following Section:

- SECTION 686
ALASKA RAILROAD COORDINATION

686-1.01 DESCRIPTION. Obtain Alaska Railroad Corporation (ARRC) temporary construction permit(s) for any work within ARRC Right-of-Way, or for any work that may impact ARRC’s operations. Coordinate construction phasing, scheduling, and track flagging, in compliance with the ARRC temporary construction permit.

686-2.01 DEFINITIONS.

ALASKA RAILROAD CORPORATION TEMPORARY CONSTRUCTION PERMIT (ARRCTCP). ARRCTCP is a permit required by the ARRC for any work that the ARRC determines will impact its facilities, operations, and/or right-of-way.

686-3.01 CONSTRUCTION PHASING. The Contractor shall coordinate with the Engineer to phase construction to ensure continuous compliance with the conditions and requirements of the ARRCTCP, referenced in Appendix F.

686-3.02 FLAGGING REQUIREMENTS. Flagging requirements shall comply with the ARRCTCP.

686-3.03 SCHEDULING. Construction schedules shall comply with Section 643 and the ARRCTCP.

686-5.01 BASIS OF PAYMENT. Contractor coordination with the ARRC, obtaining the ARRCTCP, and compliance with the ARRCTCP will be subsidiary to pay item 643.0002.____ Traffic Maintenance.  The Department will pay ARRC directly for railroad flagging per the ARRC Utility Agreement.

CFHWY00213

DIVISION 700 — MATERIALS

Blank Page

SECTION 702
ASPHALT MATERIALS

Special Provision

702-2.01 ASPHALT BINDER. Replace the 1st. paragraph with the following:

Meet AASHTO M 320 Performance-Graded Asphalt Binder and AASHTO M332 Performance-Graded Asphalt Binder Using MSCR Test Specification; except, as included in Table 702-2.01-1 Performance-Graded Asphalt Binder – Exceptions.

TABLE 702-2.01-1

PERFORMANCE-GRADED ASPHALT BINDER - EXCEPTIONS

| Performance Grade | Viscosity AASHTO T 316 | Multiple Stress Creep Recovery MSCR, AASHTO T 350 |  |  | Dynamic Shear PAV, AASHTO T 315 | Direct Tension AASHTO T 314 | Elastic Recovery AASHTO T 301 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | JNR3.2 kPa-1 | JNR Diff | % Recovery3.2 | G*Sinδ, kPa |  |  |
| AASHTO M320 Performance-Graded Asphalt Binder |  |  |  |  |  |  |  |
| PG 52-28 | None | — | — | — | None | Delete | None |
| PG 52-40 | None | — | — | — | None | Delete | None |
| PG 52-40 ER | None | — | — | — | None | Delete | 50% min. |
| PG 58-34 ER | None | — | — | — | None | Delete | 60% min. |
| PG 64-40 ER | None | — | — | — | None | Delete | 60% min. |
| AASHTO M332 Performance-Graded Asphalt Binder Using MSCR Test Specification |  |  |  |  |  |  |  |
| PG52-40 V | None | 0.50 max. | Delete | 75 min. | None | Delete | None |
| PG58-34 E | None | 0.25 max. | Delete | 85 min. | None | Delete | None |
| PG 64-40 E | 1 Pas max. | 0.10 max. | Delete | 95 min. | 5000 max. @ 4°C | Delete | None |

CR702.3-100118R

SECTION 703
AGGREGATES

Special Provisions

Replace Subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Type IV, and V mixes.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

Meet Table 703-3 requirements:

TABLE 703-3

COARSE AGGREGATE QUALITY FOR HMA

| Description | Specification | Type II, Class A | Type I; Type II, Class B; Type III | Type IV | Type V |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max. | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Degradation Value, min. | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium Sulfate Loss, % max. (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, % min. | ATM 305 | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |
| Flat-Elongated Pieces, % max. | ATM 306 |  |  |  |  |
| 1:5 |  | 8 | 8 | 8 | 8 |
| Absorption, % max. | ATM 308 | 2.0 | 2.0 | 2.0 | 2.0 |
| Nordic Abrasion, % max. | ATM 312 | - | - | - | - |

Fine Aggregate.  Aggregate passing the No. 4 sieve.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type II, Class A mix shall not contain more than 10% natural fines (blend sand and mineral filler) added to the crushed aggregate, and shall not exhibit rut depth larger than 1/4-inch, as determined by ATM 419.

Fine aggregate for Type IV and V mixes:

	do not blend back natural sand

	shall be non-plastic as determined by ATM 205

	shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-4

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V |
| 1 inch | 100 | - | - | - | - |
| 3/4 inch | 80-90 | 100 | - | - | 100 |
| 1/2 inch | 60-84 | 77-99 | 100 | 100 | 65-90 |
| 3/8 inch | 48-78 | 68-88 | 80-90 | 80-95 | 55-80 |
| No. 4 | 28-63 | 48-68 | 44-81 | 55-70 | 40-60 |
| No. 8 | 14-55 | 33-53 | 26-70 | 35-50 | ≤ 45 |
| No. 16 | 9-44 | 20-40 | 16-59 | 20-40 | ≤ 35 |
| No. 30 | 6-34 | 14-30 | 9-49 | 15-30 | ≤ 25 |
| No. 50 | 5-24 | 9-21 | 6-36 | 10-24 | ≤ 20 |
| No. 100 | 4-16 | 6-16 | 4-22 | 5-15 | ≤ 12 |
| No. 200 | 4-7 | 3-6 | 4-7 | 4-7 | 4-7 |

703-2.07 SELECTED MATERIAL.

Replace 1. Type A with the following:

1.	Type A. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by ATM 204 and ATM 205.  Meet the following gradation as tested by ATM 304:

Sieve	Percent Passing by Weight

No. 4	20-55%

No. 200	0-6%, determined on the minus 3-inch portion of the sample

703-2.13 STRUCTURAL FILL. Replace Table 703-12 with the following:

TABLE 703-12

AGGREGATE GRADATION FOR STRUCTURAL FILL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3-inch | 100 |
| 3/4-inch | 75-100 |
| No. 4 | 20-55 |
| No. 200 | 0-6 |

Replace Subsection 703-2.16 with the following:

703-2.16 RECYCLED ASPHALT PAVEMENT (RAP). RAP shall be free of contamination and deleterious materials.  RAP maximum particle size shall not exceed 1.5-inch.

CR703.1-100117R

SECTION 706
CONCRETE AND PLASTIC PIPE

Special Provisions

Replace Subsection 706-2.07 with the following:

706-2.07 CORRUGATED HIGH DENSITY POLYETHYLENE (HDPE) PIPE FOR CULVERTS, STORM DRAINS, AND UNDERDRAINS. Meet the following:

Corrugated Pipe and Fittings (non-pressurized)

AASHTO M 294 and 252	Type S

Perforations

1.	Underdrains	Class 2

2.	Underdrains and Storm Drains	Class 1

Joints	Subsection 705-2.05.3.

Polyethylene Pipe Manufacturer

1.	Participate in the National Transportation Product Evaluation Program (NTPEP) work plan for HDPE thermoplastic pipe and listed on the NTPEP audit website displaying NTPEP compliance.

2.	Conduct and maintain a quality control program under the NTPEP.

3.	Provide a manufacturer's certificate of compliance identifying production lots for all materials.

Provide corrugated polyethylene pipe and fittings manufactured from high-density polyethylene (HDPE) virgin compounds. May use clean, reworked polyethylene materials from the manufacturer's own production.

Do not install pipe that is more than two years from the date of manufacture.

CR706.1-050119

SECTION 710
FENCE AND GUARDRAIL

Special Provisions

Replace Subsection 710-2.04 with the following:

710-2.04 METAL BEAM RAIL.

1.	W-Beam and Thrie Beam Guardrail. Meet AASHTO M 180, Class A, Type II. Galvanize after fabrication. Meet the coating requirements of AASHTO M 180 9, Type II Beams and AASHTO M 111 (ASTM A123) as referenced.

2.	Box-Beams Guardrail. Meet:

a.	ASTM A500 Grade B, or

b.	ASTM A501.

Galvanize after fabrication. Meet the coating requirements of AASHTO M 111 (ASTM A123).

CR710.3-020119

SECTION 712
MISCELLANEOUS

Special Provisions

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti-skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

4.	Performance Properties:  Add the following:

k.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

Replace Subsection 712-2.18 with the following:

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads.  Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials.  Marking Material Manufacturer will certify compatibility.

(2)	Lasting retro reflectivity.

CR712.1-010109R

Delete Section 715 Steel for Piles and replace with the following:

SECTION 715
STEEL FOR PILES

715-2.01 SCOPE. Steel used for Structural Steel Piling and Sheet Piling.

715-2.02 GENERAL REQUIREMENTS. Furnish steel piles of the dimensions, weights, cross-sections, and grades specified. Satisfy the impact test requirements of Subsection 716-2.02. Meet the following:

1.	Structural Steel HP Piling. Furnish HP shape piles meeting ASTM A709, Grade 50T3.

2.	Structural Steel Pipe Piling. Furnish pipe piles meeting one of the following:

a.	American Petroleum Institute (API) 5L X52 PSL2 with one longitudinal seam.

b.	ASTM A709, Grade 50T3 with one longitudinal seam fabricated  and monogrammed according to API 2B.

c.	ASTM A709, Grade 50T3 fabricated according to the following:

(1)	General. Fabricate single seam helical weld pipe piling from coiled skelp. Use skelp material that does not contain repair welds. Use skelp having a width not less than 0.8 times the outside diameter of the pipe and not greater than 3.0 times the outside diameter of the pipe. Form pipe when the steel temperature is below 400°F. Locate junctions of skelp end welds and the helical seam welds at distances greater than 1.0 times the outside diameter of the pipe from the pipe ends and at distances greater than 5.0 times the outside diameter of the pipe from other junctions of skelp end welds and helical seam welds.

(2)	Welding. Use complete joint penetration welds produced by the automatic submerged–arc welding process, the automatic gas metal-arc welding process, or a combination of both processes. Perform welding according to Section 504.

(3)	Welding Inspection. Perform welding inspection according to AWS D1.1. Provide 100% visual inspection of welds on the inside and outside surfaces of the pipe.

(4)	Non-Destructive Examination. Randomly examine 10% of the total length of helical seam welds and skelp end welds. Examine welds by performing one of the following tests:

(a)	Radiographic testing according to the requirements of AWS D1.1 Section 6, Part E with Subsection 6.12.3 of AWS D1.1.

(b)	Ultrasonic testing according to the requirements of AWS D1.1 Section 6, Part F with Subsection 6.13.3.1 of AWS D1.1.

If more than 10% of the weld lengths examined are defective, examine a second random sample of 25% of the total length of welds. If more than 10% of the weld length examined in the second sample are defective, examine 100% of the total length of welds.

Repair all weld defects in accordance with AWS D1.1.

(5)	Destructive Examination. Perform destructive examination on specimens from finished pipe of each specified outside diameter, wall thickness, steel type, heat, and grade. Examine specimens at a frequency of at least one set of tests for each lot representing 2000 linear feet of finished pipe or once per week during each production run, whichever occurs first. Do not use specimens containing repaired welds.

(a)	Tensile Tests. Meet the specified tensile requirements for yield strength, tensile strength, and elongation. Perform tension tests according to ASTM A370 using one base metal specimen and two weld specimens taken at 90° to the length of the weld with the weld across the center of the sample. For base metal specimen, determine and report yield point, yield strength, tensile strength, and elongation. For weld test specimens, determine and report tensile strength.

Each lot of pipe will be considered to meet the tensile requirements if the base metal test results meet the specified yield strength, tensile strength, and elongation and the weld test results meet the specified tensile strength result.

(b)	Bend Tests. Perform transverse side bend tests according to ASTM E190. Each lot of pipe will be considered to meet the bend test requirements if no cracks occur in the specimen.

(6)	Tolerances. Meet the following tolerances:

(a)	Roundness. Limit the difference between the major and minor outside diameter to 1% of the specified outside diameter of the pipe or 1/4 inch, whichever is less.

(b)	Circumference. Limit the outside circumference to 1% of the nominal outside circumference of the pipe or 1/2 inch, whichever is less.

(c)	Straightness. Do not deviate from a straight line parallel to centerline of the pile more than 1/8 inch per 10 feet of length, but not to exceed 3/8 inch in any 40-foot length.

(d)	Length. ±1-1/2 inch per 10 feet of length.

(7)	Defects. The Engineer may reject piles containing surface defects. The depth of the surface defect will be measured as the gap between the lowest point of the defect and a prolongation of the original contour of the pipe. Use of piles containing surface defects may be authorized according to the following requirements based on the depth of the surface defect:

(a)	If the surface defect is not greater than 5% of the wall thickness in depth, the defect need not be repaired.

(b)	If the surface defect is deeper than 5%, but not greater than 7%, of the specified wall thickness, grind smooth the surface defect. Remove abrupt changes in contour, but do not reduce the thickness in the ground area more than 7% of the specified wall thickness.

(c)	If the surface defect is deeper than 7%, but not greater than 20%, of the specified wall thickness, repair the defect by welding according to Section 504.

(d)	If the surface defect is deeper than 20% of the specified wall thickness, repairs will not be permitted and the pile will be rejected.

3.	Pile Tip Reinforcing. Use pile tip reinforcement conforming to the requirements of ASTM A27 Grade 65-35 or ASTM A148 Grade 90-60. Make each pile tip in one piece of cast steel. Weld tip reinforcing to the piles in conformance with the manufacturer's written directions.

4.	Structural Steel Sheet Piling. Furnish sheet piles meeting AASHTO M 202.  Provide piling and connectors of the same ASTM designation and grade shown on the Plans.  Do not mix piling of different grades.

715-2.03 CERTIFICATION. Furnish a certified test report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number;

2.	the manufacturer's name;

3.	the name of the product or assembly;

4.	a complete description of the material;

5.	country of origin;

6.	the lot, heat, or batch number that identifies the material;

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 715-2.03.6; and,

8.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

For pipe manufactured to API 5L, submit an inspection certificate with test results according to API 5L 10.1.3.

715-2.04 MARKING. Mark all pipe and sheet piling using dot peen, die stamp or other low stress engraving process that is legible after coating or galvanizing.  Mark the exterior and interior faces of one end of the piling with the lot number, heat number, batch number, or other appropriate identification that matches the accompanying certified test report.

Also mark helical welded pipe piles with the fabricator’s name, measured major diameter, measured minor diameter, and nominal wall thickness on the exterior face at both ends.

CFHWY00213

Special Provision

Replace Section 724 with the following:

SECTION 724
SEED

724-2.01 DESCRIPTION. Grass seed to provide a living vegetative cover.

724-2.02 MATERIALS. Provide seed mix as specified in the Special Provisions. Provide seed collected or harvested within 2 years of the targeted seeding date. Provide all seed in pure live seed (PLS) unless otherwise directed.

Furnish seed true of genus and species. Meet applicable requirements of the State of Alaska Seed Regulations, Alaska Administrative Code, Title 11, Chapter 34, (11 AAC 34), and the Federal Seed Act, 7 CFR Part 201.

The Engineer will review requests for genus, species, or cultivar substitutions(s). The Contractor shall submit a proposed seed mix accompanied by approval from the Alaska Plant Materials Center, and confirmation the vendor can provide the requested mix in quantities adequate for the project.

1.	Prohibited and Restricted Noxious Weeds and Quarantined Pests. Furnish seed certified to be free of prohibited noxious weeds or quarantined pests, and certified to contain no more than the maximum allowable tolerances for restricted noxious weeds, according to 11 ACC 34.

a.	Seed found to contain prohibited noxious weeds or quarantined pests will be rejected, according to 11 AAC 34.020(a) and 11 AAC 34.105 through 34.180, respectively.

b.	Seed found to contain restricted noxious weed seed in excess of the maximum allowable tolerance per pound will be rejected, according to 11 AAC 34.020(b).

Prohibited and restricted noxious weeds are listed in 11 AAC 34.020, and can be viewed at the following URL: http://plants.alaska.gov/invasives/noxious-weeds.htm.

2.	Labeling. Ensure each bag or container of individual seed species is labeled to meet requirements of 11 AAC 34.010. Do not remove labels from bags or containers.

3.	Certification. Certify seed is free of prohibited noxious weeds and restricted noxious weeds are within allowable tolerances. Furnish to the Engineer a statement signed by the vendor identifying the lot number or lot numbers, certifying each lot of seed has been tested within the preceding nine months, by a recognized seed testing laboratory, a member of the Association of Official Seed Certifying Agency (AOSCA), or the Alaska Plant Materials Center.

Seed will be rejected if:

a.	Contains prohibited noxious weeds;

b.	Contains restricted noxious weeds above maximum allowable tolerances;

c.	Not certified as tested within the preceding nine months;

d.	Wet, moldy, or otherwise damaged in transit or storage; or

e.	Containers do not have labels or the labels have been removed.

Seed may be rejected for:

a.	Discrepancies in the lot numbers listed on the statement to the lot numbers indicated on the labels of the seed containers.

The Contractor shall immediately remove rejected seed from the project premises. If seed is rejected for containing prohibited noxious weeds or for exceeding maximum allowable tolerances of restricted noxious weeds, dispose of rejected seed according to 11 AAC 34.075(g).

CR724.HSM20.17-113020

SECTION 722
BRIDGE RAILING

Special Provisions

722-2.01 BRIDGE RAILING.  Replace “Steel tube rail elements”, “Steel Thrie Beam elements”, “Posts”, “Anchor bolts”, “Shims, plates, angles and sleeves”, and “Plate Washers and Tapered Plate Washers” with the following:

Steel tube rail elements				AASHTO A500, Grade B or C

Steel thrie beam elements			AASHTO M 180, Class B, Type II

Posts								ASTM A709, Grade 50

Anchor bolts and rods   				ASTM F3125, Grade A325 or ASTM A449, Type 1

Shims, plates, plate washers,

angles, sleeves, and scuppers		ASTM A709, Grade 50

Beveled washers and tapered

plate washers						ASTM F436

CFHWY00213

SECTION 726
TOPSOIL

Special Provision

Replace Subsection 726-2.01 with the following:

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area, and free of prohibited and restricted noxious weeds (Prohibited and Restricted Noxious Weeds 11AAC 34.020 http://plants.alaska.gov/invasives/noxious-weeds.htm). Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project.  In this case furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse or foreign materials having an organic content of 5 percent or more, as determined by ATM 203.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the topsoil source location at least 30 calendar days before delivery of topsoil to the project from the identified location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

TABLE 726-1

LIMESTONE REQUIREMENTS

| Soil pH | Limestone, tons/acre |
| --- | --- |
| Above 6.0 | 0 |
| 5.0-6.0 | 1.5 |
| Below 5.0 | 3.0 |

CR726.1-010120

Special Provisions

Replace Section 727 with the following:

SECTION 727
SOIL STABILIZATION MATERIAL

727-2.00 GENERAL.  Free of restricted and prohibited noxious weeds (11 AAC 34), seeds, chemical printing ink, germination and growth inhibitors, herbicide residue, chlorine bleach, (except where specified: rock, metal, plastics) and other deleterious materials and not harmful to plants, animals and aquatic life.  Wood cellulose "paper" fiber, wood chips, sawdust, and hay are not permitted as stabilization materials.

727-2.01 MULCH.  Flexible blanket/covering, temporary degradable (bio/photo) form of erosion control.  Use one of the following:

Dry Erosion Control, Stabilization Products.  Hand applied or spread with mulch blower equipment.

1.	Straw.  Use straw, in an air-dried condition, from oats, wheat, rye, barley, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life. Straw material shall be certified weed-free straw using North American Invasive Species Management Association (NAISMA) Standards.  In-lieu of certified weed-free straw provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

2.	Shredded Bark Mulch.  Shredded bark and wood with the following characteristics:

a.	Not containing resin, tannin, or other compounds in quantities harmful to plant life.

b.	Maximum length of individual pieces is 2 inches with 75% passing through a 1 inch sieve.

c.	Will form a uniform ground cover/mat, have moisture absorption, retention, and percolation properties, not be susceptible to spreading by wind or rain providing a good growth medium.

d.	May contain up to 50% shredded wood material.

e.	Shredded wood material aged 1 year minimum prior to use.

Hydraulic Erosion Control Products (HECPs) Applied hydraulically.

A fiber mulch matrix:  biodegradable and composed of wood, straw, coconut and other fibers natural and man-made.  When applied, create a continuous, porous, absorbent high water holding, flexible blanket/mat/mulch/covering making intimate contact with, and adhering to sloped soil surface; permitting water infiltration; resists erosion and promotes rapid germination and accelerated plant growth.  The fibers may be thermally processed, and cross-linked with a hydro-colloidal or linear anionic tackifier (curing period 24-48 hours) or mechanically-bonded (no curing period).  When agitated in slurry tanks with water the fibers will become uniformly suspended, without clumping to form homogeneous slurry.

The HECPs shall be delivered premixed by the manufacturer.  The HECP will contain only the materials provided in the sealed containers from the manufacturer.  No added components are permitted after the manufacturer seals the product container, before application, during application or otherwise.  Submit documentation dated within 3 years of application, from an independent accredited laboratory as approved by the Engineer, showing that the product's testing performance meets the requirements for the slope(s) to be protected on the project, according to the National Transportation Product Evaluation Program (NTPEP), Erosion Control Technology Council (ECTC) and or the Texas DOT/Texas Transportation Institute (TTI) Laboratory.

If the HECP contains cotton or straw provide documentation that the material is certified weed free using NAISMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

The HECP shall contain a dye to facilitate placement and inspection of the material.

1.	Wood Strand, Fiber.

A blend of angular, loose, long thin wood pieces with a high length to width ratio and that are frayed.  Minimum 95% of strands between 2 inches and 10 inches, at least 50% of the length shall have a width thickness between 1/16 and 1/8 inch.  No single strand shall have a width or thickness greater than 1/2 inch.  Processed wood fiber with the following characteristics:

a.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form homogeneous slurry.

b.	Will form a blotter-like uniform ground cover on application, have moisture absorption, retention and percolation properties, the ability to cover, and hold grass seed in contact with soil, and not create a hard crust upon drying providing a good growth medium.

2.	Dried Peat Moss.  Partially decomposed fibrous or cellular stems and leaves of any of several species of Sphagnum mosses with the following characteristics:

a.	Chopped or shredded to allow distribution through normal hydraulic type seeding equipment and capable of being suspended in water to form part of a homogeneous slurry.

b.	Free from woody substances and mineral matter such as sulfur or iron and with a pH value of between 4.0 and 6.5.

c.	Furnished in an air dry condition and containing less than 35% moisture by weight.  Have a water holding capacity of not less than 800% by weight on an oven dry basis.

3.	Fiber Matrix (FM) Mulch - Types.

a.	Stabilized Mulch Matrices (SMMs)

b.	Bonded Fiber Matrices (BFMs)

c.	Mechanical Bonded Fiber Matrix (MBFM)

d.	Polymer Stabilized Fiber Matrix (PSFM)

e.	Fiber Reinforced Matrices (FRMs)

	Flexible Growth Medium (FGM)

	Extended-Term Flexible Growth Medium (ET-FGM)

727-2.02 MATTING.  Fiber mulches, mulch matrices, nets and turf reinforcement mats manufactured from wood fibers, straw, jute, coir, polyolefins, PVC, nylon and others creating dimensionally stable nets, meshes, geotextiles and blankets; creating a continuous, porous, absorbent, flexible blanket/mat/mulch/covering making intimate contact with and adhering to sloped soil surface, resisting erosion and promoting rapid germination and accelerated plant growth.

Rolled Erosion Control Products (RECPs) (Temporary Degradable and Permanent Erosion Control)

Use RECPs that bear the Quality and Date Oversight and Review (QDOR) Seal from the ECTC.  Independent test results from the NTPEP, that the mulch, when tested according to ASTM 6459 Standard Test Method for Determination of Rolled Erosion Control Products (RECP), Performance in Protecting Hillslopes from Rainfall-Induced Erosion, meets the performance requirement using the Revised Universal Soil Loss Equation (RUSL).

Functional Longevity.

1.	Temporary Degradable.

a.	Duration.

1)	Short-Term RECPs. (RECPs 3 - 12 months)

C Factor = .15 maximum

Test Soil Type = Sandy Loam

(National Resources Conservation Service (NCRS) Soil Texture Triangle)

2)	Moderate (Extended) -Term RECPs.  (RECPs 24 months)

C Factor = .05 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

3)	Long-Term RECPs.  (RECPs 36 months)

C Factor = .01 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

b.	Product types.

1)	Mulch-Control Nets (MCNs).  Planar woven natural fiber or extruded geosynthetic mesh used to anchor loose fiber matting/mulches.

2)	Erosion Control Blankets (ECBs).  Processed natural and/or polymer fibers, yarns or twines mechanically, structurally, or chemically bound together to form a continuous matrix with a minimum weight of 8 oz/yd2 and a limiting shear stress of 0.45 lb/ft2.

3)	Netless.  Fibers mechanically interlocked and/or chemically adhered together.

4)	Single-net and Double-net.  Fibers mechanically bound together by single or double netting.

5)	Open Weave Textiles (OWTs).  Fibers woven into a continuous matrix.

c.	Materials.

1)	Burlap.  Standard weave with a weight of 3.5 to 10 oz/yd2.

2)	Jute Mesh Fabric.  Cloth of a uniform, open, plain weave of undyed and unbleached single jute yarn.  Use yarn that is loosely twisted and not varying in thickness more than one-half its normal diameter.  Furnish jute mesh in rolled strips meeting the following requirements:

a)	Width:  45 to 48 inches,  1 inch

b)	78 warp-ends per width of cloth (minimum)

c)	41 weft-ends per yard (minimum)

d)	Weight:  20 ounces per linear yard,  5%

3)	Woven Paper or Sisal Mesh Netting.  Woven from twisted yarns available in rolls 45 to 48 inches wide.  Mesh may vary from closed to open weave, ranging from 1/8 to 1/4 inch openings.  Shrinkage after wetting may not exceed 20% of the surface area.

4)	Knitted Straw Mat.  Commercially manufactured ECB.  Use photodegradable netting and biodegradable thread.  Use straw, in an air-dried condition, from oats, wheat, rye, barley, or other approved grain crops that are certified weed free of prohibited and restricted noxious weed seed and quarantined pests, according to Alaska Administrative Code, Title 11, Chapter 34 (11 AAC 34), and in conjunction with North American Invasive Species Management Association (NAISMA) standards, and free of mold, or other objectionable materials detrimental to plant life.  When straw or straw products certified according to 11 AAC 34 are not available, use non-certified products manufactured within Alaska before certified products manufactured in another state, country, or territory. Non-certified products manufactured in Alaska In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw. Non-certified straw or straw products manufactured in another state, country, or territory shall not be used. ECB may contain coconut or fiber to reinforce the straw.

5)	Woven/Curled Wood blanket.  Machine produced mat of curled wood shavings with a minimum of 80% 6-inch or longer fibers, with consistent thickness and the fibers evenly distributed over the entire area of the blanket.  Smolder resistant without the use of chemical additives.  Cover the top side of the blanket with biodegradable extruded plastic mesh.

6)	Coconut (Coir Fiber).  Machine produced mat, ECB of consistent thickness and coir fiber evenly distributed over the area of the mat.  Use bio/photo degradable netting and thread.

2.	Permanent.

a.	Product Types and Materials.

1)	Turf Reinforcement Mats (TRMs).  A rolled erosion control product composed of non-degradable synthetic fibers, filaments, nets, wire mesh, and/or other elements, processed into a permanent, three-dimensional matrix of sufficient thickness with a minimum weight of 8 oz/yd2 and a minimum limiting shear stress of 1.5 lb/ft2.  TRMs (may be supplemented with degradable components) shall impart immediate erosion protection, enhance vegetation establishment during and after maturation and permanent vegetation reinforcement providing long-term functionality.

727-2.03 SEDIMENT RETENTION FIBER ROLLS (SRFRs).  Fiber rolls also referred to as wattles.  Manufacture of photodegradable or biodegradable fabric netting without preservative treatment, evenly woven, free of crusted material, cuts, and tears.  Manufacture stakes of photodegradable or biodegradable material (wood stakes, except as approved by the Engineer).

1.	Filter Sock (Wattle)

a.	Fabric netting.

b.	Filled with wood fiber, straw, flax, rice, coconut fiber material.

c.	Minimum diameter 5 inches.

2.	Compost Sock.

a.	Extra Heavy weight fabric netting with a minimum strand width of 5 mils.

b.	Filled with coarse compost.

c.	Minimum diameter 8 inches.

3.	Coir Log.

a.	Woven wrap bristle coir twine netting.

b.	Filled with 100% coconut (coir) fiber uniformly compacted.

c.	Segments maximum length 20 foot, diameter as suited to the application and a density of 7 lbs/pcf or greater.

d.	Coir twine strength equal to 80 lb minimum weaved to a 2 inch x 2 inch opening pattern.

e.	Ties made of hemp rope by 1/4 inch diameter.

727-2.04 COMPOST.  Suitable for serving as a soil amendment or an erosion control material.  Sanitized, mature compost meeting local, state, and Federal quality requirements tested and certified by the U.S. Composting Council (USCC) under the Seal of Testing Assurance (STA) Program.  Biosolids compost must meet the Standards for Class A biosolids outlined in 40 Code of Federal Regulations (CFR) Part 503.  Additionally, meet the requirements of the AASHTO specifications:

1.	Compost Blankets.  Standard Practice for Compost for Erosion/Sediment Control (Compost Blankets) R 52.

2.	Compost Filter Berms and Filter Socks.  Standard Practice for Compost for Erosion/Sediment Control (Filter Berms and Filter socks) R 51.

727-2.05 TACKIFIER.  Tackifier, viscous overspray, generally composed of dry powered vegetable gums derived from guar gum, psyllium and sodium alginase; asphaltic emulsions; petroleum distillates; co-polymer emulsions; and lignosulfonates and used to anchor soil, compost, seed, the mulch fibers to one another, and the ground.  Contain no growth or germination inhibiting materials nor significantly reduce infiltration rates.  Tackifier shall hydrate in water and readily blend with other slurry material.  Tackifier options include:

1.	Type A.  Organic tackifier with certification of plant sources; or

2.	Type B.  Synthetic tackifier with certification confirming product is not harmful to plants, animals, or aquatic life.

727-2.06 POLYACRYLAMIDE (PAM).  Use as a tie-down for soil, compost, seed and as a flocculent. Polyacrylamide (PAM) products shall meet the requirements of American National Standards Institute (ANSI)/National Sanitation Foundation International (NSF) Standard 60 for drinking water treatment, be anionic (not cationic), linear and not cross-linked with an average molecular weight greater than 5 Mg/mole, minimum 30 percent charge density; contain at least 80% active ingredients and a moisture content not exceeding 10% by weight.

Deliver PAM in a dry granular powder or liquid form.

727-2.07 GEOTEXTILE-ENCASED CHECK DAM AND SEDIMENT BARRIER.  Urethane foam core encased in geotextile material (silt fence material Section 633), minimum 8 inches height by minimum base width of 16 inches by minimum 7 foot length.  Overhang the geotextile 6 inch minimum each end with apron type ties by 24 inches each side of the foam core.

727-2.08 SANDBAG.

1.	Sandbag Sack Fabric. Fabric shall be a nonwoven, needle punched design meeting the Minimum Average Roll Values (MARV) verified in accordance with ASTM D4759.

2.	Seam Thread.  Similar durability to the sandbag sack fabric.

3.	Sandbag Fill Material.

a.	Selected Material	703-2.07	Type B

4.	Cinch Ties.  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

727-2.09 MANUFACTURED INLET PROTECTION SYSTEM.

1.	Manufacturers:

a.	Ultra Tech International – Ultra-DrainGuard

b.	Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

c.	Enpac - Catch Basin Insert, Oil and Sediment or

d.	Approved equal.

727-2.10 CLEAR PLASTIC COVERING.  A clear plastic covering meeting the requirements of the National Institute of Standards and Technology (NIST) voluntary Product Standard PS 17 - 69 for polyethylene sheeting having a minimum thickness of 6 mils.

727-2.11 STAPLES.  U-shaped staples for anchoring matting, approximately 6 inches long and 1 inch wide.  Machine-made:  No. 11 gage or heavier steel wire.  Hand-made:  12-inch lengths of No. 9 gage or heavier steel wire.

CR727-050812R1

SECTION 730
SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS.

Add No. 7:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to ASTM A500, Grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

CR730.1-062204

Replace Subsection 730-2.05 with the following:

730-2.05 FLEXIBLE DELINEATOR POSTS.  Durable fiberglass composite, polymer, or plastic material meeting the dimensions and colors shown on the Plans. Resistant to ultraviolet light, ozone and hydrocarbon damage and remain flexible at a temperature of minus 40 °F. Provide posts with reflectors that are capable of self-erecting and remaining serviceable after 5 head-on impacts at 55 mph and 10 impacts at 35 mph with an automobile at an air temperature of plus 40 °F.

Terminal Markers - Flexible (marker).  The marker includes the pole/post/rod (pole), reflective and retroreflective sheeting and mounting hardware.

Provide durable markers: resistant to impact from (snow and vehicle), vandals, ultraviolet light, moisture, ozone, and hydrocarbons.

When the pole is loaded, the marker shall bend/flex, remain flexible and oriented as installed continuing to function as designed without permanent displacement along the length of the member.  Provide the flexibility in the primary vertical element, a connecting device between the vertical element and connection to the support member (spring or other) or a combination.

Provide a connection sufficient to transfer the loads from the pole to the supporting member without reducing the strength, flexibility, or durability of either.  The connection shall not negatively influence the performance of the guardrail.  Provide approval of the connection from the marker manufacturer and support member manufacturer (if proprietary).

	Design Loads:

	Impact load from snow thrown by snowplows

Ø	Weight of snow covering the pole (snow thrown from snowplows)

Ø	Wind loads (100 mph, 3 sec gust)

·	Service Temperature Range:	-40˚ F to +140˚ F.

·	Pole:

1.	Material:

Ø	Steel, or

Ø	Stainless Steel, or

Ø	Other Poles:

(a)	Continuous glass fiber and marble reinforced thermosetting composite, or

(b)	Engineered plastic alloy, or

(c)	Fiberglass Reinforced Polyester (FRP)

(d)	High-Impact Polyolefins

2.	Dimensions

Ø	Top of Pole:  60 inches to 84 inches above top of guardrail

Ø	Width/Diameter:  minimum = 1 1/4 inches, maximum = 2 inches (steel/stainless steel not be greater than 5/8 inch diameter)

Ø	Thickness:  as required by design

3.	Visibility:

Ø	Daytime: Pole - color orange

a.	Steel and Stainless Steel Poles:  Applied permanent finish.

b.	Other Poles:  Color pigment ultraviolet stabilized and solid through the cross section from end to end.

Ø	Nighttime:  Added retroreflective sheeting - color white

a.	Approximately 12 square inches visible from the traveled way before and after the marker.  Applied to a flag attached to the pole or as banding applied directly to the pole.  (A flag is required when using steel/stainless steel poles.)

b.	Place top edge of flag/banding 1 inch from top of pole.

(1)	Flag:  Single retroreflective sheet each face

(2)	Banding:  Two bands completely around marker, 4 inches between bands

·	Hardware and Fasteners:

Ø	Steel, and/or

Ø	Stainless Steel, or

Ø	Aluminum alloy (hardware only)

Manufacturers of flexible markers (snowpoles):

| Manufacturer | Model | Type | Contact |
| --- | --- | --- | --- |
| Nordic Fiberglass, Inc. | FF2 | Steel Pole w/ Flag | Ph: (218) 745-5095 |
| PEXCO | Model 3639 | High-Impact Polyolefins | Ph: (404) 564-8560 |
| New Century Northwest, LLC | NCN2549 | Engineered Plastic Alloy | Ph: (541) 485-5566 |
| Carsonite Composites, LLC | SNFB | Continuous glass fiber and marble reinforced thermosetting composite | Ph: (800) 648-7916 |

Submit manufacturer's specifications to the Engineer for review and approval before ordering terminal markers.

CR730.2-122217

Special Provisions

SECTION 731
WATERPROOFING MEMBRANE

TABLE 731-1 SPRAY-APPLIED WATERPROOFING MEMBRANE

Replace the value under “Requirements” for “Interlayer Shear Strength” with the following: 30 psi min.

CFHWY00213

SECTION 740
SIGNALS AND LIGHTING MATERIALS

Special Provisions

Replace Subsection 740-2.06 with the following:

740-2.06 ELECTRICAL CONDUIT AND FITTINGS.  Unless specified otherwise, use rigid metal conduit and fittings for raceways.  Furnish galvanized rigid type conduit and elbows conforming to UL Standard 6 and are manufactured of mild steel according to ANSI C80.1.  Furnish third party certified fittings designed for rigid metal conduit.

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL Standard 651.  Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL Standard 651 B and NEMA TC-7-2000.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle.  Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline.  The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws.  For loop detectors, furnish Type X bodies and, for photoelectric control installation, furnish Types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it.  The movements include:  axial expansion or contraction to 3/4 inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to 3/4 inch.  The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

Replace Subsection 740-2.18 with the following:

740-2.18 LUMINAIRES.  Furnish luminaires that conform to the following specifications and provide the light distributions specified.  When luminaire performance criteria are specified, luminaires shall also:

- Meet or exceed the minimum initial light levels indicated.

- Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified:  luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses (when used) and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8, dated 2014.

Furnish each luminaire with a high pressure sodium lamp or LED of the wattage specified and matching ballast with an input voltage equal to circuit voltage.

Luminaries General

Install luminaires that feature:

- Corrosion resistant enclosures with gray painted finish, cooling elements not required to be painted, and space for the ballast.

    - Painted or finished luminaire surfaces exposed to the environment shall exceed a rating of six (6), after 1,000 hours or four (4) of 5,000 hours salt spray test according to ASTM D1654 and ASTM B117 testing. The coating shall exhibit no greater than 30% reduction of gloss, according to ASTM D523, after 500 hours of ASTM G154 Cycle 6 QUV® accelerated weathering testing.

- All luminaires shall have ANSI C136.15 external labels and ANSI C136.22 internal labels. The luminaire shall be listed for wet locations by a nationally recognized testing laboratory (NRTL) as defined by OSHA and shall be in compliance with UL 8750 and UL 1598. It shall be identified as such by a tag/sticker on the inside of the luminaire.

- All hardware shall be stainless steel or suitably corrosion resistant to match the 20-year expected life of the fixture. Captive screws are required on any component that requires maintenance after installation.

- Glass lenses, unless polycarbonate resin refractors are specified.

- Terminal blocks for attaching the illumination tap conductors.

- Aluminum reflectors with an ALZAK or ALGLAS finish when using HPS fixtures.

- Optical components free of substances that affect photometric performance, paint.

- Housings cast with no provision for a photoelectric control receptacle. Unless specified otherwise in the plans.

- For HPS fixtures; airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components, gasket material must withstand the temperatures involved and be securely held in place.

- For HPS fixtures include plug in starting aids with lamps through 400 watts.

- Luminaries – High Pressure Sodium; Cobrahead and Offset/Turnpike

Furnish HPS fixtures that feature a rated life of 40,000 hours based on 10 hours per start and ballasts that conform to Subsection 740-2.21. Each cobrahead or offset luminaire shall also include:

  - An easily removed hinged door used exclusively for mounting the ballast.

  - A second door that frames the lens (for HPS), hinges on the house side, and fastens on the street side with an automatic type latch.

  - A two (2) or four (4) bolt mounting brackets that is designed to fit a 2-inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

- Luminaires - LED

  - General. The luminaire shall be assembled in the United States and shall be assembled by and manufactured by the same Manufacturer. For easy removal, quick-connect/disconnect plugs shall be supplied between the discrete electrical components within the luminaire such as the driver, surge protection device, and optical assembly. The quick-connect/disconnect plugs shall be operable without the use of tools and while insulated gloves are worn. The luminaire shall be in compliance with ANSI C136.37 LED light source(s), and driver(s) shall be compliant with the Restriction of Hazardous Substances (RoHS) Directive 2011/65/EU.

    - Manufacturer Experience. The luminaire shall be designed to be incorporated into a lighting system with an expected 20-year lifetime. The luminaire Manufacturer shall have a minimum of 20 years’ experience manufacturing high-intensity discharge (HID) roadway luminaires and shall have a minimum of 5 years’ experience manufacturing LED roadway luminaires. The Manufacturer shall have a minimum of 5,000 total LED roadway luminaires installed on a minimum of 30 separate installations, all within the United States.

  - Housing. The housing shall be designed to ensure maximum heat dissipation and to prevent the accumulation of water, ice, dirt, and debris. A passive cooling method with no moving or rotating parts shall be employed for heat management. The effective projected area of the luminaire shall not exceed 1.2 sq. ft and the total weight of the luminaire(s) and accessories shall not exceed 55 lb for standard roadway pole mounted fixtures. Other fixture types shall have weight and dimensions as specified in the plans.

  - Optical Assembly. The LED optical assembly, consisting of LED packages, shall have a minimum ingress protection rating of 66 (IP66) as defined in ANSI/IEC 60529. Circuiting shall be designed to minimize the impact of individual LED failures on the operation of the other LEDs.

The optical assembly shall utilize high-brightness, long-life LEDs with a minimum color rendering index (CRI) of 70, 4000 K (+/- 300 K) color temperature, and binned according to ANSI C78.377. Lenses shall be UV-stabilized acrylic or glass. For roadway fixtures provisions for house-side shielding shall be specified along with means of attachment.

Lumen depreciation at 50,000 hours of operation shall not exceed 15% of initial lumen output at the specified LED drive current and an ambient temperature of 77°F (25°C).

The assembly shall have individual serial numbers or other means for Manufacturer tracking.

    - Photometric Performance Testing.  Roadway luminaires shall be tested according to IES LM-79. The laboratory performing this test shall hold accreditation from the National Voluntary Laboratory Accreditation Program (NVLAP) under NIST. Submitted reports shall have a backlight, uplight, and glare (BUG) rating according to IESNA TM-15, including a luminaire classification system graph with both the recorded lumen value and percent lumens by zone. Non-roadway fixtures do not need to meet this requirement.

Lumen maintenance shall be measured for the LEDs according to LM-80, or when available for the luminaires according to LM-84. The LM-80 report shall be based on a minimum of 6000 hours; however, 10,000-hour reports shall be provided for luminaires in cases in which tests have been completed.

Thermal testing shall be provided according to UL 1598. The luminaire shall start and operate in the ambient temperature range specified. The maximum rated case temperature of the driver, LEDs, and other internal components shall not be exceeded when the luminaire is operated in the ambient temperature range specified.

Mechanical design of protruding external surfaces such as heat sink fins shall facilitate hose-down cleaning and discourage debris accumulation. Testing shall be submitted when available to show that the maximum rated case temperature of the driver, LEDs, and other internal components are not exceeded when the luminaire is operated with the heat sink filled with debris.

    - Calculations.  Complete point-by-point luminance and veiling luminance calculations as well as listings of all indicated averages and ratios as applicable shall be provided according to IES RP-8 recommendations. Lighting calculations shall be performed using AGi32 software with calculations performed to two decimal places (i.e., x.xx cd/m2). Calculation results shall demonstrate that the submitted luminaire meets the lighting metrics specified in the plans. Scotopic or mesopic factors will not be allowed.

    - Lumen Maintenance Projection.  The LEDs shall have long-term lumen maintenance documented according to IESNA TM-21, or when available for the luminaires according to IESNA TM-28. The submitted calculations shall incorporate an in situ temperature measurement test (ISTMT) and LM-80 data with TM-21 inputs and reports according to the TM-21 calculator, or when available an ISTMT and LM-84 data with TM-28 inputs and reports according to the TM-28 calculator. Ambient temperature shall be 77°F (25°C).

  - Driver.  The driver for the luminaire shall be integral to the unit. It shall be mounted in the rear of the luminaire on the inside of a removable door or on a removable mounting pad for standard pole mounted roadway fixtures. The removable door or pad shall be secure when fastened in place, and all individual components shall be secured upon the removable element. Each component shall be readily removable from the removable door or pad for replacement.

The driver shall be installed in a manner to keep it mechanically separated from the LED array heat sink.

    - Circuit Protection. The driver shall tolerate indefinitely open and short-circuit output conditions without damage.

    - Ingress Protection. The driver itself shall have an IP65 or IP66 rating, not the driver door. Do not gasket the driver door or seal in order to prevent condensation and allow for draining.

    - Input Voltage. The driver shall be suitable for operation over a range of 120 to 277 V or 347 to 480 V as required by the system operating voltage.

    - Operating Temperature. The driver shall have an operating ambient temperature range of      -40°F to 131°F (-40°C to 55°C).

    - Driver Life. The driver shall provide a lifetime of 100,000 hours at an ambient temperature of 77°F (25°C).

    - Safety/UL.  The driver shall be listed under UL 1012 or UL 1310.

    - Power Factor.  The driver shall maintain a power factor of 0.9 or higher and total harmonic distortion of less than 20%.

    - Driver Efficiency.  The driver shall have a minimum efficiency of 90% at maximum load and a minimum efficiency of 85% for the driver operating at 50% power, with driver efficiency defined as output power divided by input power.

    - Electrical Interference.  The driver shall meet the electromagnetic compatibility (EMC) requirements for Class A digital devices included in the FCC Rules and Regulations, Title 47, Part 15.

    - Thermal Fold Back.  The driver shall reduce the current to the LED module if the driver is overheating as a result of abnormal conditions.

    - Dimming.  The driver shall have 0 to 10 V dimming capability.

    - Leakage Current.  The driver shall comply with safety standards according to IEC 61347-1.

  - Surge Protection Device (SPD).  SPD shall be labeled as Type 4 in accordance with UL 1449 and be an integral part of the luminaire. It shall provide a minimum system protection level of 10 kV, 10 kA. To protect for a 10 kV, 10 kA surge the required clamping voltage of the external metal oxide varistor (MOV) or other SPD shall be lower than 1 kV at 8 kA {(10 kV – 2 kV)/1 ohm = 8 kA}.

The SPD shall comply with the following standards:

    - IEEE C62.41.1, IEEE Guide on the Surge Environment in Low-Voltage (1000 V and Less) AC Power Circuits,

    - IEEE C62.41.2, IEEE Recommended Practice on Characterization of Surges in Low-Voltage (1000 V and Less) AC Power Circuits,

    - IEEE C62.45, IEEE Recommended Practice on Surge Testing for Equipment Connected to Low-Voltage (1000 V and Less) AC Power Circuits, and

    - ANSI C136.2, American National Standard for Roadway and Area Lighting Equipment — Luminaire Voltage Classification.

The SPD and performance parameters shall be posted at www.UL.com under category code VZCA2.

  - Photoelectric Control.  For Roadway fixtures, furnish fixtures with a built in ANSI C136.41 7-pin twist type photo cell receptacle. Receptacles shall be provided with shorting caps. Other fixture types see plans for requirements.

  - Failed Equipment and Workmanship. The luminaire and all of its components, for the term of the Contract, from initial installation through final acceptance 105-1.16, when directed, promptly replace failed equipment and repair failed workmanship.

(1)	Negligible light output from more than 10% of the LED packages,

(2)	Moisture inside the optical assembly,

(3)	Driver that continues to operate at a reduced output, and/or

(4)	Other failed conditions that do not meet specifications.

  - Submittal Requirements.  The Contractor shall submit, for approval, an electronic version of all associated luminaire IES files, AGi32 files, and the TM-21 or TM-28 calculator spreadsheet with inputs and reports associated with the project luminaires. The Contractor shall also provide an electronic version of each of the following Manufacturers’ product data sheets for each type of luminaire.

    - Descriptive literature and catalog cuts for luminaire, LED package, driver, and surge protection device;

    - LED drive current, total luminaire input wattage, and total luminaire current at the system operating voltage or voltage range and ambient temperature of 77°F (25°C);

    - Luminaire efficacy expressed in lumens per watt (lpw) per luminaire;

    - Initial delivered lumens at the specified color temperature, drive current, and ambient temperature;

    - Computer photometric calculation reports;

    - TM-15 BUG rating report (Roadway Fixtures);

    - Certification of Manufacturers’ experience and certification that luminaires were assembled in the United States;

    - Supporting documentation of compliance with ANSI standards, as well as listing requirements;

    - Supporting documentation of laboratory accreditations and certifications for specified testing;

    - Thermal testing documents;

    - IES LM-79, LM-80 (or LM-84), and TM-21 (or TM-28) reports;

    - Salt spray (fog) test reports and certification;

    - Vibration characteristics test reports and certification;

    - IP test reports;

    - Manufacturer written warranty; and

    - Luminaire installation, maintenance, and washing instructions.

- Lenses

When polycarbonate resin lenses are specified, the fabricator shall furnish certified lenses conforming to the following criteria:

a.	The lenses are molded in a single piece from virgin polycarbonate resin.

b.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

c.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

d.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

e.	The resins used meet the requirements for the self-extinguishing classification of ASTM D 635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D 256, Method A, using a 1/8 inch by 1/2 inch bar molded according to ASTM recommended practice.

Replace Subsection 740-2.21 with the following:

740-2.21 Reserved

Replace Subsection 740-2.23 with the following:

740-2.23 Reserved

CFHWY00213 / CFHWY00308

APPENDIX A

CONSTRUCTION SURVEY REQUIREMENTS

Blank Page

APPENDIX B

ENVIRONMENTAL PERMITS

Blank Page

APPENDIX C

MATERIAL CERTIFICATION LIST

Blank Page

APPENDIX D

SIGN SHOP DRAWINGS

Blank Page

APPENDIX E

ARRC Letter of non-objection & tcp

Blank Page

APPENDIX F

USFS DRAFT SPECIAL USE PERMIT

Blank Page

APPENDIX G

WILDLIFE OBSERVER PROTOCOL