SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

1.	Publications.  The following are available from the Plans Room or for download online:

a.	Standard Specifications for Highway Construction, 2017 Edition ($25.00).  Available online at:

www.dot.state.ak.us/stwddes/dcsspecs/assets/pdf/hwyspecs/sshc2017.pdf

b.	Alaska Test Methods Manual (Lab & Field), May 1, 2016 Edition ($25.00). Available online at:

www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/pop_testman.shtml

c.	Alaska Storm Water Pollution Prevention Plan Guide, March 2017.

www.dot.state.ak.us/stwddes/desenviron/resources/stormwater.shtml

d.	Utility facility clearance requirements. Available online at:

	ENSTAR Natural Gas Company (ENSTAR)

www.enstarnaturalgas.com/safety-education/natural-gas-safety/safety-for-excavators-contractors/

e.	Quantity Computations

f.	Cross Sections

g.	Geotechnical Report, Glenn Highway Reconstruction, MP 34-42, Project No. 0A1-5(24)/Z581040000, February 2017

h.	Limited Phase II Environmental Site Assessment Report, March 2013

i.	Hazardous Building Materials Surveys.

- Parcel 92: 1150 S. Town and Country Ln, Palmer, AK

- Parcel 93 and 94: 1130 and 1110 S. Town and Country Ln, Palmer, AK

- Parcel 95, 96 and 100: 1020 S. Blunk St, Palmer, AK

- Parcel 101: 945 S. Blunk St, Palmer, AK

- Parcel 103: 2108 S. Glenn Hwy, Palmer, AK

- Parcel 112: 405 S. Rose Dr, Palmer, AK

- Parcel 129: 1600 S. Glenn Hwy, Palmer, AK

- Parcel 147 and 148: 245 and 265 W. Bogard Rd, Palmer, AK

j.	Erosion, Sediment Control Plan (ESCP). Glenn Highway: S. Inner Springer Lp to W Arctic Ave, Project No. 0A15036/CFHWY00317, October 2017.

k.	XML Files. XML file type for the original ground surface is available on the Department’s website. The Department expressly states that these XML files are for informational purposes only. The Department makes no representation, warranty, or guarantee, expressed, implied, or statutory, as to the accuracy, reliability, suitability, functionality, or results derived from the use of the information contained therein. The Department shall not accept, review, hear or consider any bid protest or construction claims arising from use of the information.

2.	Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix 	C	.

3.	Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

4.	Section 120, Disadvantaged Business Enterprise (DBE) Program.  The Department, in coordination with US DOT, has adopted a Race-Neutral DBE Program effective for Federal-aid projects advertised in Central Region after June 30, 2015.  In particular, all bidders shall be aware that Good Faith Effort Documentation is required from the successful bidder for all contracts, regardless of DBE goal or DBE utilization, in accordance with Section 120 Disadvantaged Business Enterprise (DBE) Program.

The overall DBE Utilization Goal is revised to 8.83 percent.

Any questions about this notice may be directed to Dennis Good, Manager of the Civil Rights Office, (907) 269-0848, or email dennis.good@alaska.gov.

5.	Cargo Preference Act Requirements. The provisions of the Cargo Preference Act (CPA) must be physically incorporated into all Federal-aid Projects awarded after February 15, 2016, and must be physically incorporated in all agreements with subcontractors and lower tier subcontractors.

Form 25D-55 (2/16) is revised to include the CPA provisions to the Required Contract Provisions for Federal-Aid Construction Contracts.  See the last page of Form 25D-55 for the CPA requirements.

For additional details, please visit: www.marad.dot.gov/ships-and-shipping/cargo-preference/laws-and-regulations/

6.	Buy America Act. On December 22, 2015, U.S. District Court for the District of Columbia issued a decision vacating the Federal Highway Administration (FHWA) 90 percent threshold exemption for manufactured steel and iron products and the miscellaneous steel or iron components, subcomponents and hardware waiver.  As a result of the federal court decision, FHWA withdrew their December 21, 2012 policy memorandum clarifying provisions of the Buy America Act requirements.

7.	Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0644.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

8.	Section 401 and 703 Hard Aggregate.  HMA, Type II, Class AH requires hard aggregate.  Refer to the table in 703-2.04 Coarse Aggregate for the specified Nordic Abrasion value.  Material suppliers are also included in 703-2.04.

9.	Asphalt Material Price Adjustment.  The unit price adjustment for asphalt material will be combined and paid under one Pay Item. Refer to Sections in Division 300 and 400 that include an "Asphalt Material Price Adjustment" Pay Item.

10.	Administrative Order (AO) 278. On November 10, 2015, Governor Walker issued Administrative Order (AO) 278. The order establishes a 15% goal for utilizing registered apprentices in certain job categories on construction projects awarded by the Alaska Department of Transportation and Public Facilities. AO 278 applies to all projects with a contract award amount that equals or exceeds 2.5 million dollars.

11.	Properties Not Acquired. Acquisition of four properties have not been completed, and no work shall commence on these properties until a separate Notice to Proceed is given by the Engineer, see Section 1.07-1.17.

12,	Pavement Removal. Pavement removal for this project is required to be by cold planing method.  Pavement material planed from the project is the property of the State, and will be delivered and stockpiled at the Palmer Maintenance yard, as described in Section 202-3.05.

FED_SOA-CRSNtB/CFHWY00317

PART 4

STANDARD MODIFICATIONS
AND
SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2017

EDITION

Blank Page

TABLE OF CONTENTS

Section	Page

DIVISION 100 — GENERAL PROVISIONS

105	Control of Work	3

107	Legal Relations and Responsibility to Public	4

108	Prosecution and Progress	7

109	Measurement and Payment	8

120	Disadvantaged Business Enterprise (DBE) Program	9

DIVISION 200 — earthwork

201	Clearing and Grubbing	13

202	Removal of Structures and Obstructions	14

203	Excavation and Embankment	22

204	Structure Excavation for Conduits and Minor Structures	25

DIVISION 300 — BASES

301	Aggregate Base and Surface Course	29

306	Asphalt Treated Base Course	31

DIVISION 400 — ASPHALT PAVEMENTS AND SURFACE TREATMENTS

401	Hot Mix Asphalt Pavement	45

406	Rumble Strips	65

DIVISION 500 — STRUCTURES

505	Piling	71

514	Concrete Surface Finish and Treatment	72

DIVISION 600 — MISCELLANEOUS CONSTRUCTION

601	Metal Flume Inlet	77

603	Culverts and Storm Drains	78

604	Manholes and Inlets	82

606	Guardrail	83

607	Fences	90

608	Sidewalks	91

610	Ditch Lining	98

611	Riprap	99

615	Standard Signs	100

618	Seeding	105

619	Soil Stabilization	109

620	Topsoil	114

621	Planting Trees and Shrubs	115

622	Rest Area Facilities	120

626	Sanitary Sewer System	121

627	Water System	135

631	Geotextile for Subsurface Drainage and Erosion Control	154

633	Silt Fence	157

635	Insulation Board	158

636	Gabions	159

639	Driveways	160

641	Erosion, Sediment, and Pollution Control	161

642	Construction Surveying and Monuments	187

643	Traffic Maintenance	203

644	Services to be Furnished by the Contractor	225

645	Training Program	228

646	CPM Scheduling	231

647	Equipment Rental	232

649	Governor's Workforce Development	234

651	Control of Work – Supplemental Requirements	236

652	Prosecution and Progress – Supplemental Requirements	243

660	Signals and Lighting	244

661	Electrical Load Centers	270

662	Fiber Optic Signal Interconnect System	280

667	Traffic Signal Communication System	297

669	Automated Traffic Recorders	299

670	Traffic Markings	305

682	Utility Potholing	310

DIVISION 700 — MATERIALS

702	Asphalt Materials	314

703	Aggregates	315

710	Fence and Guardrail	318

712	Miscellaneous	320

724	Seeding	321

725	Fertilizer	322

726	Topsoil	323

727	Soil Stabilization Material	324

729	Geosynthetics	329

730	Sign Materials	331

740	Signals and Lighting Materials	333

Appendix A	Construction Survey Requirements

Appendix B	Environmental Permits

Appendix C	Material Certification List

Appendix D	Sign Shop Drawings

Appendix E	Temporary Construction Easements Temporary Construction Permits

Appendix F	ARRC Draft Temporary Construction Permit and Letter of No Objection

DIVISION 100 — GENERAL PROVISIONS

Blank Page

SECTION 105
CONTROL OF WORK

Special Provisions

Add the following Subsection 105-1.011 Related Sections:

105-1.011 RELATED SECTIONS.

Section 651, Control of Work – Supplemental Requirements

CR105.5-012816

105-1.15 PROJECT COMPLETION.

3rd paragraph 1st sentence, replace: "621-3.04" with "618-3.06 and 621-3.04"

CR105.7-042015

SECTION 107
LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

Replace Subsection 107-1.02 Permits, Licenses, and Taxes with the following:

107-1.02 PERMITS, LICENSES, AND TAXES. The terms, conditions, and stipulations in permits obtained either by the Department or by the Contractor are made a part of this Contract. Permits obtained by the Department for this project are attached to these Specifications as appendices. Contact names and phone numbers for permits obtained by the Department are shown on the individual permits.

The Department will:

1.	Secure permits and licenses that the Department determines are required for the construction of the proposed project, and the use of mandatory sources, designated sources and designated material disposal areas for the proposed project; and

2.	Modify Department-acquired permits during the performance of the contract, if deemed necessary by the Engineer.

3.	The Department has received the following permits on the Contractor's behalf:

- Storm Water Letter of No Objection Permit No. 18-WW-320-004

- Public Water System No. 226020 Conditional Approval to Construct Project Reference No. 14579

- Public Water System No. 226020 Conditional Approval of Separation Distance Waiver Request Project Reference No. 14579

The Contractor shall:

1.	Acquire any permits and licenses required to complete the project that are not acquired by the Department;

2.	Provide qualified professionals to collect data or perform studies necessary to acquire permits for the use of sites not previously permitted;

3.	Give all notices required for the prosecution of the work;

4.	Abide by all permits and licenses whether acquired by the Department or by the Contractor;

5.	Notify the Engineer promptly if any activity cannot be performed as specified in the permits, and cease conducting the activity until permit modifications or any required additional permits are obtained;

6.	Obtain modifications to permits acquired by the Contractor;

7.	Pay all charges, fees and taxes;

8.	Provide proof of payment of all taxes before the Department makes final payment; and

9.	Provide the information necessary to comply with the Alaska Department of Environmental Conservation (DEC), Alaska Pollutant Discharge Elimination System (APDES) to discharge storm water from the construction site.  Requirements for this permit are given under Section 641, Erosion, Sediment, and Pollution Control.

10.	Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual, and the Regional Supplement to the Corps of Engineers Wetland Delineations Manual (Alaska Region, Version 2.0, September 2007).  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

The provisions of permits acquired by the Contractor, and of notices and information under this section does not shift or create responsibility for compliance with Federal or State law to the Department, or otherwise impose a duty for oversight or review.

In addition, before using an area on or off project site not previously permitted for use by the Contract, the Contractor shall:

1.	Contact all government agencies having possible or apparent permit authority over that area;

2.	Obtain all required permits, clearances, and licenses from those agencies;

3.	Obtain permission from any property owners or lessees with an interest in the property; and

4.	Provide all of the following to the Engineer:

a.	All permits or clearances necessary to use the site for its intended purpose(s);

b.	A written statement that all permits or clearances necessary have been obtained;

c.	Written evidence that the Contractor has contacted all of the relevant agencies and that no additional permits are required on the part of the Contractor, including at a minimum the name of the agency and staff person contacted, the date contacted, and result of coordination; and

d.	A plan that identifies how the site will be finally stabilized and protected.

The Engineer may reject a proposed site if the Contractor fails to provide any of the above information or to demonstrate that a proposed site can be finally stabilized to eliminate future adverse impacts on natural resources and the environment.

CR107.2-120117.SSHC2017

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Replace the 1st sentence including numbers 1, 2, and 3, with:

When operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following:

Non-municipal Water Source. If water is required for a construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

CR107.3-051517

Add the following:

Bald Eagles.  Bald Eagles are protected under the Bald Eagle Protection Act (16 U.S.C. 668-668c) which prohibits “takes” of bald eagles, their eggs, nests, or any part of the bird.  The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of minimum 330-feet as an undisturbed habitat buffer around nesting bald eagles.  If topography or vegetation does not provide an adequate screen or separation, extend the buffer to 1320-feet, or a sufficient distance to screen the nest from human activities.  The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity.  Within the Secondary Zone, between 330-feet and 660-feet from a nest tree, no obtrusive facilities, or major habitat modifications shall occur.  If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, extend the buffer up to 2640-feet.  No blasting, logging and other noisy, disturbing activities should occur during the nesting period (February 1 – August 31) within the primary or secondary zones.

Do not disturb a nesting eagle.  Notify the Engineer if an active eagle nest is observed within the primary or secondary zones.

CR107.1-081216

Replace Subsection 107-1.17 with the following:

107-1.17 FURNISHING RIGHT-OF-WAY. The Department will secure all necessary right-of-way or property. The right-of-way (ROW) shown in the plans depict the ROW area that is or will be available for the project.  Acquisition of the following properties has not been completed, and no work including utility relocations shall commence on these properties until a separate Notice to Proceed is given by the Engineer.

- Parcel 105, Church of God, as shown on R-35; TCP 105, Church of God as shown on F-6 and F-19;

- Parcels 120 and E-120, Kerttula, as shown on R-38, R-39, R-41, and R-42; TCE-120 Kerttula as shown on F-10 and F-24; TCP-120 Kerttula as shown on F-23;

- Parcel E-143C, Safeway, Inc., as shown on R-48; TCE-143C Safeway, Inc. as shown on F-33 and F-34; TCE-143D Safeway, Inc. as shown on F-33, TCP-143C Safeway, Inc. as shown on F-33; TCP 143D Safeway, Inc.  as shown on F-33,

- Parcel E-145, US Postal Service, as shown on R-49; TCE-145 US Postal Service as shown on  F-14, F-37, and F-43.

The Contract Time will commence to run on the day indicated on the Notice to Proceed for the overall project.  The Notices to Proceed for the above properties will be delayed until such time as the Department obtains full rights to enter upon the property.  The Contractor shall bid this Project to include all costs associated with the delayed Notices to Proceed based on the assumption that all Notices to Proceed will be given before May 1, 2019.   If the Notices to Proceed are given on or before May 1, 2019, The Contractor agrees that it will have no claim for damages or delay arising out of or connected to the delayed Notice to Proceed for these properties.

CFHWY00317

SECTION 108
 PROSECUTION AND PROGRESS

Special Provisions

Add the following Subsection 108-1.011 Related Sections:

108-1.011 RELATED SECTIONS.

Section 652, Prosecution and Progress – Supplemental Requirements

CR108.3-012816

SECTION 109
MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Replace item, "14. Weighing Procedures" with "Weighing Procedures".  "Weighing Procedures" is a subtopic under item "13. Ton (2,000 pounds)."

CR109.3-042015

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.  Under Item 3. Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

CR109.2-042015

SECTION 120
DISADVANTAGED BUSINESS eNTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01 DESCRIPTION.

Delete the second paragraph of Subsection 120-1.01 and replace with the following:

The Department, in coordination with the Federal Highway Administration (FHWA), adopted a Race-Neutral DBE Program with an overall DBE Utilization Goal of 8.83 percent for Alaska’s FHWA Federal-Aid program.  Although the Race-Neutral program does not establish or require individual project DBE Utilization Goals, 49 CFR establishes the Bidder is responsible to make a portion of the work available to DBEs and to select those portions of the work or material needs consistent with the available DBEs to facilitate DBE participation.

SM3-122217.SSHC2017

Blank Page

DIVISION 200 — EARTHWORK

Blank Page

SECTION 201
CLEARING AND GRUBBING

Special Provisions

201-3.01 GENERAL.  Add the following:

Timber for Public Removal.  Cut timber, with a 5 inch diameter or larger at breast height, into 8 foot lengths, de-limbed, and stacked to a height no greater than 6 feet.  Place the stacks at locations shown in the Plans, included in Specifications or at other locations approved by the Engineer.  Make locations adjacent to the nearest turnout, side street, or other approved site that does not create a traffic hazard due to lack of adequate parking for the public.  Access to the site(s) shall be maintained and controlled by flaggers, in accordance with Subsection 643-3.04.  The Contractor shall provide and maintain a separate firewood telephone hotline that details when and where the wood is available to the public.  Special Construction signs, in accordance with Subsection 643-2.01, shall be used to advertise the firewood telephone hotline.  Provide two weeks for the public to access each area of the project where timber is made available. Dispose of the timber left by the public after the two week time period.

Mechanical loading by the public is not permitted.

CR201.2-010114

Add the following:

Perform the work necessary to preserve and/or restore land monuments and property corners from damage.  Restore land monuments and/or property corners that are disturbed according to Section 642.  An undisturbed area five feet in diameter may be left around existing monuments and property corners.  A list of land monuments and property corners is shown on the Right of Way maps.

CR201.3-042313

Add the following:

Clearing and grubbing is not permitted within the migratory bird window of May 1 to July 15; except as permitted by Federal, State and local laws when approved by the Engineer.

CR201.1-010114

201-5.01 BASIS OF PAYMENT.  Add the following:

The work required to cut, de-limb, and stack timber for public removal is subsidiary to 201 Pay Items.

CR201.2-010114

Add the following:

The work required to preserve and restore land monuments and property corners is subsidiary to 201 Pay Items.

CR201.3-042313

SECTION 202
REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION.  Add the following:

Remove gas pipe, remove storage tanks (either fuel or septic) and decommission ground water wells.

CR202.5R-010610/CFHWY00317

Replace the last sentence with: Install, remove and reset mailboxes and newspaper delivery tubes and preserve from injury and defacement all vegetation and objects not scheduled to be removed.

CFHWY00317

202-2.01 MATERIALS. Add the following:

Class A Concrete	Section 501.

CFHWY00317

202-3.01 GENERAL. Add the following:

Demolish and remove all improvements located within the right-of-way and temporary construction easements at:

Parcel 92: 1150 S. Town and Country Ln, Palmer, AK

Parcel 93 and 94: 1130 and 1110 S. Town and Country Ln, Palmer, AK

Parcel 95, 96 and 100: 1020 S. Blunk St, Palmer, AK

Parcel 101: 945 S. Blunk St, Palmer, AK

Parcel 103: 2108 S. Glenn Hwy, Palmer, AK

Parcel 112: 405 S. Rose Dr, Palmer, AK

Parcel 129: 1600 S. Glenn Hwy, Palmer, AK

Parcel 147 and 148: 245 and 265 W. Bogard Rd, Palmer, AK

- Raze, remove, and dispose of, or salvage all buildings and foundations, structures, fences, sidewalks, concrete and asphalt pavement, debris and other obstructions, any portions of which are within the limits of the ROW and TCE, except utilities and those for which other provisions have been made for removal.

- Fill basements, or cavities left by structure removal, to the level of the surrounding ground and, if within the prism of construction, compact backfill as specified under Section 203.

- Provide the Engineer with copies of all permits, agreements with utility companies and written consent to access private and or government property before starting work.

- Where traffic maintenance is required for activities on the local, state and federal roads as defined in the Standard Specifications for Highway Construction, Section 643 and Special Provisions submit a Traffic Control Plan to the Engineer for review and receive approval before beginning related construction activity, coordinate with the Engineer. Activities including moving whole or partial structures will require a Traffic Control Plan.

- All hazardous material found on site must be removed and disposed of in accordance with the Alaska DEC Regulations. Hazardous building materials surveys have been completed for this project. Buildings being demolished may contain asbestos. Take special handling measures when removing this material.

- Verify actual limits of demolition with the Engineer prior to start of work.

- Provide temporary security fencing around the worksite before beginning demolition.

- Demolish and remove the complete structures, the roof, floors, walls; including chimneys, foundations; including foundation walls, footings, posts, piers, and pilings. Remove basement walls, footings, and the basement floor (slab on grade below the finish grade). Remove asphalt paving and concrete slabs, including floor slabs at finish grade (with surrounding foundation walls and footings).

- Demolish and remove existing fencing. Remove posts, braces, anchors, and all other items associated with the fencing and retaining walls.

- All demolished materials are the property of the Contractor unless noted otherwise. Handle and transport materials according to DEC regulations. Store materials at a Contractor DEC approved site. No portion of the demolition debris will be used as backfill or left on site for any other purpose. Areas of demolition will be cleaned of visible debris and inspected by the Engineer prior to conducting any excavation at that location.

- Demolition materials not being used in the project, stored at a Contractor DEC approved site, or disposed of at a previously approved DEC disposal site require a DEC Solid Waste Disposal Permit.

- Disposal sites shall be outside the project limits unless directed otherwise, in writing, by the Engineer. Obtain written consent from the property owner. Dispose of solid waste materials (including handling, transporting, storing and disposing) according to DEC Regulations. A DEC Permitting Officer in Anchorage may be contacted at (907) 269-7590.

- The Contractor shall disconnect/terminate all site utilities in accordance with each governing utility owner and governing codes. Coordinate all utility disconnects with the utility companies and the Engineer. Disconnects for this project shall be of permanent type, including shut-off valves, caps, plugs and other as required to stop the flow of materials, (water, sewer, gas, power, telephone, cable TV, etc.). All permits required for this work will be paid for by the Contractor.

- On-site wastewater disposal systems shall be decommissioned in accordance with applicable DEC requirements.   These include, but are not limited to, pumping the holding tank, removing the piping from the structure to the tank and removing the tank.  All cleanouts and monitoring points shall be removed to at least five feet below final grade.  Contractor is responsible for verifying size, location, and number of holding tanks.

- Backfill all trenches, holes and pits flush to the surrounding finish grade with Selected Material, Type C. Grade fills and disturbed areas to drain. Seed, mulch, and fertilize all disturbed ground, in accordance with Section 618.

- Burning and use of explosives will not be permitted on the project.

The structures and improvements located on the following parcels are to be removed by others:

Parcel 91: 11861 E. Cienna Ave, Palmer, AK

Parcel 108: 2040 S. Glenn Hwy, Palmer, AK

Parcel 110: 460 S. Rose Dr, Palmer, AK

Parcel 111: 435 S. Rose Dr, Palmer AK

Parcel 115: 12460 E. Drift Ln, Palmer, AK

Parcel 117: 1930 S. Glenn Hwy, Palmer, AK

Parcel 119: 1910 S. Glenn Hwy, Palmer, AK

The contractor shall coordinate and cooperate with other contractors working to remove these structures.

CR202.5R/CFHWY00317

Add the following:

Carefully remove fences designated by the Engineer to the right-of-way limit, or to the end of the span beyond the right-of-way limit.  These materials belong to the property owners, and shall be salvaged and stacked neatly in their yards.  After the construction of noise barrier or fence is complete, use salvaged fencing to fill possible fencing gaps behind the property line.  Use salvaged fencing according to Section 607, for reconstructed fences.

CR202.6R-102402

202-3.02 MAIL BOXES  Add the following:

Contractor shall coordinate with personnel from US Postal Service or the USPS Palmer Carrier Annex at least 72 hours prior to placing concrete for cluster mailbox foundations to schedule a pre-pour inspection by USPS personnel.  Anchor bolt pattern and foundation forms will be approved by the Engineer prior to placing concrete.

Contractor shall not relocate cluster mailbox or obliterate and destroy existing foundations prior to inspection of the new foundations by USPS personnel.

CFHWY00317

202-3.04 REMOVAL OF PIPE.  Add the following:

During project construction, ENSTAR Natural Gas Company will abandon existing gas pipelines.  Follow the procedures given in Subsection 105-1.06 Cooperation With Utilities, when working around gas pipelines until they have been abandoned.  Once the pipelines are abandoned, remove abandoned natural gas pipe within the right-of-way that are in conflict with the work and dispose of pipes off the project limits.

CR202.5R-010610/CFHWY00317

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following:

Remove existing asphalt pavement by cold planing.  Planed material shall have 100% passing the 1 ½” sieve, and 95-100% by weight pass the 1” sieve, or as directed by the Engineer.

Pavement material planed from the project roadway is the property of the State. Remove planed material from the project immediately after planing.  Stockpile planed material at the Palmer maintenance station located at Inner Springer Loop.  Coordinate with Kyler Hylton, Maintenance Foreman for acceptance of material and desired location of stockpile.  Dispose of planed material not accepted by the Maintenance Foreman in an acceptable manner, or incorporate into the road structure prism as directed by the Engineer.  Handle, transport, store, or dispose material according to Subsection 3.05, Removal of Pavement, Sidewalks, and Curbs.

Dispose of planed material not accepted by the maintenance station, not used in the project, and not wanted by the Contractor according to Subsection 3.09.

Do not damage or disturb the existing curb, gutter, and edge of existing Portland cement pavement not designated for removal.  Remove and replace damage caused by the Contractor's planing operation at the Contractor’s expense.

Provide a capable planing machine:

1.	Self-propelled and capable of milling at speeds from 0 ft to 40+ ft per minute.

2.	Able to spray water inside the milling chamber to reduce dust.

3.	Able to mill adjacent to a gutter without damaging gutter.

CFHWY00317

Removed sidewalks and curbs is the property of the Contractor.  Handle and transport materials according to DEC regulations.  Store materials at a Contractor DEC approved site.

The use of sidewalk and curb in the embankment requires written approval and direction for use from the Engineer. Maximum allowed dimension of broken material is 6 inches.  Bury the material below the finished surface.

Dispose of removed sidewalks and curbs not wanted by the Contractor and not used in the project, according to Subsection 3.09.

CR202.2R/CFHWY00317

Add the following Subsection 3.07:

202-3.07 GROUND WATER WELL DECOMMISSIONING.  Decommission the water wells according to DEC requirements conforming to 18AAC 80.015 Well Protection Source Water Protection, and Well Decommissioning, or a DEC approved alternate method.  Develop and submit a detailed Ground Water Well Decommissioning Plan to the Engineer.  Contact the 	Wasilla	  DEC office at (907) 376-1851, for plan review requirements of alternate methods.

CR202.5R-010610/CFHWY00317

Add the following Subsection 3.09:

202-3.09 DISPOSAL OF PAVEMENT, SIDEWALKS, AND CURBS.

Pavement, sidewalk, and curb materials not used in the project, stored at a Contractor DEC approved site, provided to the local DOT Maintenance and Operations Station, or disposed of at a previously approved DEC disposal site require a DEC Solid Waste Disposal Permit.

Use disposal sites outside the project limits unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the property owner.  Dispose of solid waste materials, pavement, sidewalk, and curb (including handling, transporting, storing and disposing) according to the DEC Regulations.

A DEC Permitting Officer in Anchorage, contact at (907) 269-7590.

CR202.1R-010114

Add the following Subsection 3.10:

202-3.10 HAZARDOUS MATERIALS REQUIREMENTS. Remove hazardous materials from the building and site in accordance with the following.

- Hazardous Materials Assessments (Assessment) have been performed at the buildings affected by this project, including estimated quantities of hazardous materials as shown in the Assessment.  The hazards abatement portion of this project includes the removal and disposal of asbestos-containing materials, mercury-containing materials, lead-containing materials and/or other hazardous materials in the buildings.  The Contractor shall remove or disturb hazardous materials as coordinated with other trades, as specified and/or indicated in the Assessments and as required to complete the work.  It is the Contractors responsibility to take the Assessments baseline data and coordinate and fully develop a hazardous materials removal plan that will identify the locations of asbestos and/or other hazardous materials that will be affected by this project.  That responsibility includes sampling of suspect bulk materials (if necessary) and review of previous sampling data.

The asbestos-containing materials (ACM) known or assumed to be present are identified in the Assessment.  If any bulk sampling is conducted to disprove any assumed ACM, that sampling shall be conducted by EPA certified Building Inspectors in full compliance with 40 CFR 763, and the results submitted to the Engineer.

- The lead-containing materials known or assumed to be present are identified in the Assessment.  The Contractor may conduct testing of painted or other materials to determine the lead content.

- The chemicals known or assumed to be present are identified in the Assessment.

- Submit the following as components of the Hazardous Material Control Plan (HMCP) submittal to the Engineer for review, approval or rejection per Section 641.  Work shall not begin until submittals are approved.  The work plan shall be signed by an EPA certified Project Designer.

- Shop drawings.

- Work area set-up and protection.

- Work plan with procedures for all materials affected by the work.

- Worker protection and decontamination procedures.

- Alaska Department of Labor & Workforce Development Notification.

- EPA NESHAP notification, if required.

- EPA Lead Training certifications and notification plan, if required.

- Schedule.

- Copy of current Project Designer certification.

- Independent testing laboratory and laboratory personnel

- Sampling plan, including number and locations of samples, tests, etc.

- Waste transporter and disposal site designations.

- Submit the following components of a Close-Out Submittal to the Engineer for review, approval or rejection:

  - EPA and DOL notifications and revisions.

  - Copies of worker and IH technician certifications.

  - Copies of worker refresher course certifications.

  - Waste manifests and disposal receipts.

  - Final, signed copies of air monitoring results.

  - Copies of any bulk sampling or lead testing results.

  - Signed copies of all field data sheets.

  - Signed copies of all visual inspection forms.

  - Sketches of all sample locations.

  - Daily logs with worker sign-in sheets.

- Contractor shall provide standard commercial quality materials and equipment as required to prepare and complete the work, and as required by regulation.

- Notification to the EPA is required, unless the contractor certifies in writing that no mechanical means will be used during removal, and that the materials will not become friable during the course of the work.

- All environmental monitoring shall be performed by fully trained industrial hygiene technicians, who may be employees of the abatement firm.  Asbestos air samples shall be analyzed by a laboratory currently rated as proficient in the National Institute of Occupational Safety and Health (NIOSH) Proficiency in Analytical Testing (PAT) program or by microscopists listed in the American Industrial Hygiene Association (AIHA) Asbestos Analyst Registry (AAR).  Lead air and dust wipe samples shall be analyzed by a laboratory currently rated as proficient as determined by ELPAT or ELLAP performance for NIOSH Method 7082 and/or NIOSH Method 7105 analytical method for the determination of lead in air and lead in paint chip, soil, and dust wipe samples.  For renovation work that is regulated by 40 CFR 745, comply with any additional cleaning, inspection and testing standards of that regulation.

- The Contractor shall conduct asbestos worker exposure monitoring in accordance with 29 CFR 1926.1101.  Personal samples for an employee shall include a minimum of three samples per 8 hour shift.  Employees shall be monitored at the rate of at least one employee for every eight people performing each task in each work area.  Persons performing separate tasks or in separate work areas shall be sampled separately.  The Contractor shall take a minimum of 3 air samples per day inside the work area, and 3 air samples in adjacent areas.  The Contractor shall take one air sample at the exhaust of the HEPA Filtration Unit(s) (if utilized), rotating between units so that each unit is monitored every 3 days.

- The Contractor shall conduct lead personnel air samples in accordance with 29 CFR 1926.62.  Personal samples for an employee shall include a minimum of two samples per 8 hour shift.  Employees shall be monitored at the rate of at least one employee for every eight people performing each task in each work area.  Persons performing separate tasks or in separate lead work areas shall be sampled separately.  The Contractor shall take a minimum of 2 lead in air samples per day inside the work area, and 2 lead in air samples in adjacent areas.

- A minimum of 5 PCM clearance samples and a visual inspection is required if the building will be entered by non-abatement personnel prior to demolition.  If the final clearance air monitoring results show that the work area has failed to be less than 0.1 f/cc, the Contractor shall re-clean the work area and request a follow-up inspection to be followed by another set of clearance air monitoring samples.  All work beyond the initial set of clearance samples for each work area shall be done at no additional expense.

- Lead work area clearance testing by the Contractor is required for each lead control area where the lead action level has been exceeded.  Clearance testing shall be performed only after a visual inspection report by the IH Technician has documented that the work area is clean and that all lead disturbance required by the contract has been completed.  Clearance testing shall include the following:

- A visual inspection report by the Contractor’s IH Technician verifying that all lead removal required by the contract has been completed and that all visible dust and debris has been removed and the area HEPA vacuumed, wet mopped or wet wiped.

- Three (3) lead wipe and/or lead soil sample results from within the lead control area per the Contractor’s approved work plan and in accordance with NIOSH method 9100.  Clearance levels shall be 200 µg/ft2 for wipes or 800 ppm in soil.

- The Contractor shall determine current waste handling, storage, transportation, and disposal requirements for the chosen waste disposal facilities.  Contractor must comply fully with these requirements and all U. S. Department of Transportation and EPA regulations.

- Asbestos wastes shall be disposed of in an EPA and DEC permitted asbestos landfill.

- Lead-containing wastes shall be TCLP tested by the Contractor to determine if they are classified as hazardous waste.  TCLP’s shall be analyzed by a lab with demonstrated proficiency in performing analyses according to Method 1311 TCLP, corresponding to the current version of Test Methods for Evaluating Solid Wastes (Chemical Physical Methods), SW-846.  Evidence may include successful participation in a recognized inter-laboratory quality control program such as a laboratory certified by the California Health and Welfare Agency, Department of Health Services, or a more informal inter-laboratory quality control program.

- PCB and other chemical hazard wastes shall be disposed of in an EPA permitted hazardous waste disposal site as required by 40 CFR 260, 40 CFR 761 and 40 CFR 763, the Contractor's approved plan, and the disposal site operator.  Comply with current waste disposal, handling, labeling, storage, and transportation requirements of the waste disposal facility, U.S. Department of Transportation, and EPA regulations.  Fluorescent, mercury vapor, metal halide and high pressure sodium lamps are classified by the EPA as hazardous mercury waste under the Universal Waste Rule under 40 CFR 273.  Mercury and mercury-containing products are considered hazardous waste unless TCLP testing of the waste for mercury confirms the mercury content to be less than the EPA criteria of 0.2 mg/l..

- Dispose of radioactive materials and equipment in accordance with the manufacturer's recommendations, the disposal site's requirements and 10 CFR 20, Subpart K.  Provide list of manufacturer name and serial numbers for all removed radioactive exit signs to the Engineer.

- Refrigerants in refrigeration and cooling systems in the building may contain ozone depleting substances (ODS) components that must be recovered and recycled or disposed of in accordance with 40 CFR 82.  Personnel decommissioning or removing ODS refrigerants shall hold appropriate EPA training and certificate for handling and recovering these materials.

- Heating systems containing glycol shall be drained and all glycol collected in appropriate waste containers for recycling or disposal.  Glycol shall be tested for heavy metals using the Toxicity Characteristics Leaching Procedure (TCLP).  Glycol that failed the TCLP shall be packaged for disposal as hazardous waste.

CFHWY00317

202-5.01 BASIS OF PAYMENT.  Add the following:

Acquiring a solid waste disposal permit from DEC is subsidiary to 202 Pay Items.

CR202.1R-010114

Add the following:

Items 202(11A).  Payment is full compensation for installation of new concrete cluster mailbox foundation, relocating existing cluster mailboxes, removing and disposing of existing concrete foundations, and coordination with the USPS. Excavation, backfill, and aggregate base course for foundation is subsidiary.

Payment will be made under.

Pay Item No.	Pay Item	Pay Unit

202(11A)	Relocate Cluster Mailbox	Each

CFHWY00317

Add the following:

Item 202(13).  At the Contract Unit price for the actual length of fence taken down, disposed, or delivered to the owner, regardless of the type or height.  Payment includes full compensation required to perform this work.

Pay Item No.	Pay Item	Pay Unit

202(13)	Removal of Fence	Linear Foot

CR202.6R-102402

Add the following:

Item 202(16).  At the Contract Unit price for the length of pipe removed, regardless of size.  Payment includes full compensation to remove and dispose of the pipes as shown in the Plans.

Item 202(18).  At the Contract Lump Sum price for each tank removed and disposed of according to DEC regulations.  Payment includes full compensation for necessary excavation, purging, processing, or removing fuel-contaminated soils around the tanks, and backfilling the resultant hole.

Item 202(23A).  At the Contract Unit price for each well decommissioned according to DEC regulations.

Pay Item No.	Pay Item	Pay Unit

202(16)	Removal of Gas Pipe	Linear Foot

202(18)	Removal of Storage Tanks	Each

202(23A)	Ground Water Well Decommissioning	Each

CR202.5R-010610/CFHWY00317

SECTION 203
EXCAVATION AND EMBANKMENT

Special Provisions

203-3.01 GENERAL.  Add No. 5 after the 11th paragraph:

5.	within 50 feet of detection loops.

CR203.4-022015

Add the following subsections 3.08 and 3.09:

203-3.08 CONTAMINATED MATERIAL TESTING. This work consists of testing soils for contaminants. Each truckload of soil exported from a suspected site or other location at the direction of the Engineer shall be examined for contamination.

According to Subsection 203-3.09, Excavation of Contaminated Material, retain an independent test laboratory to conduct the following tests:

1.	Field Tests

a. Organic Vapor Analyzer (OVA) Analysis

b. Visual Analysis (Petroleum Odor)

2.	Laboratory Tests

a. Volatile Aromatic Hydrocarbons

b. Total Petroleum Hydrocarbons

Obtain the services of a qualified hazardous waste professional per DEC 18 AAC 75 regulations to conduct field testing using an organic vapor analyzer (OVA) or equivalent equipped with a photoionizing detector (PID), or other instrument approved by DEC.  Submit the name of the hazardous waste professional to the Engineer at the preconstruction conference. The hazardous waste professional shall be available to conduct the required field tests at all times hauling from the identified sites is in progress.

The hazardous waste professional shall sample and test according to standard DEC approved testing procedures described in 18 AAC 75 and 18 AAC 78 and its referenced Procedures Manual. If an OVA response indicates the presence of contamination, the soils will have failed the test and will be designated as contaminated. If no response is observed, the soil will be examined for odor. If a petroleum odor is detected, the soils will fail the test and will be designated as contaminated. If no petroleum odor is detected, the soil will be considered to have passed field criteria.

The hazardous waste professional shall be responsible for ensuring soils exhibiting an OVA response that indicate the presence of contamination, or soils exhibiting characteristics of fuel contamination (i.e. odor, sheen, or stain), are identified to the Engineer.  Contaminated material shall be immediately removed from the site.

Calibrate the OVA at the beginning and end of each day, and after every four (4) hours of use.

203-3.09 EXCAVATION AND HANDLING OF CONTAMINATED MATERIAL. This work consists of handling, removing, and disposing of contaminated soils encountered during the excavation. Comply with State and Federal regulations pertaining to the handling, storage, cleanup, and disposal of contaminated materials.  Disposal of contaminated soils shall be at a location approved by the Engineer.

- Worker Health and Safety. Ensure that personnel working in the area of potential contamination have received the State of Alaska, Department of Labor, Health and Safety Training before excavation at sites identified as potentially contaminated.  Provide the Engineer a list of the personnel and subcontractors working within the area identified as being potentially contaminated.  Notify personnel and subcontractors before beginning work at the site that they will be working in an area identified as being potentially contaminated

- Determining Limits of Contaminated Soil. Sites identified as potentially containing contaminated soil and/or water in the March 2013 Limited Phase II Environmental Site Assessment Report, or in Hazardous Building Materials Surveys, include:

- Parcel 91: 11861 E. Cienna Ave, Palmer, AK

- Parcel 108: 2040 S. Glenn Hwy, Palmer, AK

- Parcel 119: 1910 S. Glenn Hwy, Palmer, AK

- Parcel 120: 1452 S. Glenn Hwy, Palmer, AK

- Parcel 129: 1600 S. Glenn Hwy, Palmer, AK

- Parcel 143A: 439 West Evergreen Ave, Palmer, AK

- Parcel E-146: 175 West Arctic Ave, Palmer, AK

The exact limits of potential contaminated soil within the excavation cannot be determined until the material is exposed. Once exposed, test soils according to Subsection 203- 3.08, Contaminated Material Testing.  Testing will verify the contamination levels in the soils and determine if the soils can be disposed of as unclassified excavation or if it will require special handling. Soils that have a response from photoionizing detector or equivalent instrument of 1 part per million (1 ppm) or more above background are “contaminated” and will require special handling.  Dispose of this material according to this Subsection.

- Contaminated Soil Removal and Segregation. If necessary to stockpile the contaminated soil, a liner, cover and temporary fencing shall be required. The Engineer shall approve of the size and location of stockpile, liner, cover and fencing.  Cover and secure the stockpile at the end of each work day. Remove the stockpile liner, safety fence, and cover when the contaminated soil is disposed of.

- Contaminated Soil Disposal.  Dispose of contaminated soil according to DEC 18 AAC 75 approved procedures.  The Engineer may allow contaminated soil to be taken directly to a facility that handles contaminated material and is approved to operate by the DEC.  Additional testing required at the disposal site shall be done according to Subsection 203-3.08, Contaminated Material Testing, unless otherwise directed by the Engineer.

- Responsibility. With respect to preexisting hazardous substances or contaminated materials in the project area, nothing in this contract is intended to impose the Contractor, or to require the Contractor to assume the status under state or federal environmental law of a facility owner or operator, or an owner or generator of those preexisting hazardous substances or contaminated materials. However, the Contractor is advised, that they assumes the responsibility to obtain administrative approvals and to coordinate the activities with the DEC and/or any federal agency having jurisdiction, to carefully abide by the applicable laws, regulations, and the terms of any administrative approvals, and to use environmentally sound management practices such that the Contractor does not, as a result of its own actions, become a facility owner or operator, or an owner or generator of hazardous substances by reason of an unpermitted release of hazardous substances. The Contractor will assume the responsibility of the proper management and disposal of any drum of hazardous waste generated at the site, including disposal at a facility that can legally store, treat, and/or dispose of the hazardous waste.  The qualified hazardous waste professional shall perform a weekly inspection of the drums until they are transferred to the facility where they will be treated and/or disposed.

203-4.01 METHOD OF MEASUREMENT. Replace No. 1 with::

1.	Items 203(1) through 203(5) and 203(8). The volume measured in original position according to Subsection 642.308, Contractor Furnished Computations.

Add the following:

No deduction from the excavation quantities will be made for grubbing removed under 201(2B), Grubbing, and pavement removed under Item 202(2), Removal of Pavement.

Item 203(31), Contaminated Material Testing and Special Handling, will be measured for payment on a time and materials basis according to Subsection 109-1.05, Compensation for Extra Work on Time and Materials Basis. Backfilling will be measured for payment as embankment construction under their respective material pay items.

203-5.01 BASIS OF PAYMENT. Add the following:

Progress payments will be made using interim volume reports per Subsection 642-3.08.1.d(1). Progress payments require the submittal of neat-line and topographic surfaces with each request for payment. 10% of the Contract excavation quantity will be withheld until the final computations are accepted by the Engineer. Final payment will be made per Subsection 642-3.08.1.d(2).

Payment for testing, handling, removing, and disposing of contaminated material and providing a hazardous waste professional will be paid on a time and materials basis for authorized work according to Subsection 109.105.  A change order will not be required to initiate water sampling or contaminated material testing.

Add the following pay item:

Pay Item No.	Pay Item 	Pay Unit

203(31)	Contaminated Material Testing and Special Handling	Contingent Sum

CFHWY00317

SECTION 204
STRUCTURE EXCAVATION FOR CONDUITS AND MINOR STRUCTURES

Special Provision

204-2.01 MATERIALS.  In paragraph three replace: "pavement" with "roadbed."

204-3.01 CONSTRUCTION REQUIREMENTS.  Replace paragraph four with:

Native material may be utilized for conduit, pipe culvert, storm drain, manhole, inlet and other minor structure backfill outside the roadbed structure if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07.  Excavation, bedding, backfill, and compaction may be visually inspected and approved by the Engineer.

CR204.1-121212

Blank Page

DIVISION 300 — BASES

Blank Page

SECTION 301
AGGREGATE BASE AND SURFACE COURSE

Special Provision

301-2.01 MATERIALS.  Add the following after the first sentence:

Recycled Asphalt Material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70 – 100 |
| 3/8 inch | 42 – 90 |
| No. 4 | 28 – 78 |
| No. 16 | 11 – 54 |
| No. 50 | 5 – 34 |
| No. 100 | 3 - 22 |
| No. 200 | 2 – 12 |

3.	The asphalt content shall be 2.5 – 5.0 percent by weight of the RAM.

CR301.1-012407

301-3.01 PLACING.  Add the following:

Place base course material, used for the sidewalk and pathway foundations, with equipment capable of providing a specified depth and uniform surface.

CR301.2-062116

Add No. 5 after the 5th paragraph:

5.	within 50 feet of detector loops.

CR301.3-022015

301-3.03 SHAPING AND COMPACTION. Add the following:

If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be determined by control strip method ATM 412.  Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi ( 5 psi) and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.  Add the following:

Recycled asphalt material substituted for aggregate base course will be paid for as Item 301(1) Aggregate Base Course, at the unit price shown in the bid schedule for that Item.

CR301.1-012407

Special Provisions

Replace Section 306 with the following:

SECTION 306
ASPHALT TREATED BASE COURSE

306-1.01 DESCRIPTION.  Construct a plant-mixed asphalt treated base (ATB) course on an approved foundation to the lines, grades, and depths shown in the Plans.  Recycled asphalt pavement (RAP) may be used in the mix as specified herein.

306-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.

MATERIALS

306-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD).  Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 306-1 and as specified herein.  Recycled Asphalt Pavement may be used to supplement the aggregate and asphalt binder in the ATB.

TABLE 306-1

ATB Design Requirements

| DESIGN PARAMETERS | CLASS “B” |
| --- | --- |
| ATB (Including Asphalt Binder) |  |
| Stability, Pounds | 1200 min. |
| Flow, 0.01 Inch | 8 - 16 |
| Voids in Total Mix, % | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 50 |
| Asphalt Binder |  |
| Percent Voids Filled with Asphalt Binder (VFA) | 65 - 78 |
| Asphalt Binder Content, Min. % | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |
| Type II | 12.0 |
| Recycled Asphalt Pavement (RAP) |  |
| RAP, Max. %. | 25 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt binder.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the ATB, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3.  For acceptance testing, ATB mixture will have the full tolerances in Table 306-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix ATB produced from different plants for testing or production paving.  ATB from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of ATB:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD including gradations for individual virgin aggregate (aggregate) stockpiles and the RAP stockpile.  Provide supporting process quality control information; including the blend ratio of each aggregate stockpile, the RAP stockpile and the RAP asphalt binder content.  For mixes with RAP, provide JMD gradation with and without RAP.  Provide calibration data if WAQTC FOP for AASHTO T308 is used for RAP process control.

2 	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) and RAP required for the proposed JMD.  Furnish 100 lbs of each intermediate and/or coarse aggregate, 200 lbs of fine aggregate, 25 lbs of blend sand, and 200 lbs of RAP.

3.	Three separate 1-gallon samples, minimum, of the asphalt binder proposed for use in the ATB.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet (MSDS).

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current MSDS.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and Table 306-1 ATB Design Requirements.

The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 306-1

	The asphalt binder source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The source of RAP is changed

Do not produce ATB for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.

Payment for ATB will not be made until the new JMD is approved.  Approved changes apply only to ATB produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix.  The fee will be included under Pay Item 306(8_) ATB, Asphalt Price Adjustment, Type ___; Class__.

306-2.02 AGGREGATES.  Conform to Subsection 703-2.04.  Type II, Class B (IIB) total combined aggregates.

Use a minimum of three stockpiles for crushed ATB aggregate (coarse, intermediate, and fine).  Place RAP, blend material and mineral filler in separate piles.

306-2.03 ASPHALT BINDER.  Conform to 702-2.01.  If asphalt binder is not specified use PG 52-28.

The total asphalt binder content may be a combination of the asphalt binder specified and the residual asphalt binder in the RAP.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702, before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of anti-strip added.

306-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt binder is required.

306-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the ATB according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 7 days before initiating pre-paving operations.  Address the sequence of operations.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the ATB, and to provide the mat density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt binder content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 306-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

306-2.06 RECYCLED ASPHALT PAVEMENT (RAP).  Process existing pavement removed under Subsection 202-3.05 and 3.06 so material passes the 1 1/2" sieve.  Stockpile the material separately from the crushed aggregates.  Perform one gradation and one asphalt binder content test for every 1000 tons of RAP or a minimum of 10 sets of tests whichever is greater.

CONSTRUCTION REQUIREMENTS

306-3.01 WEATHER LIMITATIONS.  Do not place ATB on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place ATB unless the roadway surface temperature is 40F or warmer.

306-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of ATB buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production ATB.

306-3.03 ASPHALT MIXING PLANTS.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before ATB production.

When using recycled asphalt pavement material, mix the RAP with the aggregate before the aggregate enters the plant thereby adding the RAP combined with the aggregate to the asphalt treated base mixture at one time.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the ATB.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.

Provide aggregate and asphalt binder sampling equipment meeting OSHA safety requirements.

306-3.04 HAULING EQUIPMENT.  Costs associated with meeting the requirements of Subsection 306-3.04 are subsidiary to Section 306 Pay Items.

Vehicles/Equipment.  Haul ATB in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During ATB hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer, cover the ATB in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surface(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 7 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paving equipment.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material, the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage, as specified in Subsection 306-3.16 Patching Defective Areas, to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal.  Use repair materials of similar type to the damaged material.  Attain written approval from the Engineer for the proposed material.

306-3.05 PAVING EQUIPMENT.  Use self-propelled asphalt pavers with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the screed or blade control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Use a paver screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the ATB.

Equip pavers with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the ATB uniformly in front of screed.

Prevent segregation of the coarse aggregate particles from the remainder of the ATB during paving operations.  Specifically equip pavers to prevent segregation between the hopper and augers.  Use means and methods approved by the paver manufacturer.  Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance verifying use of the means and methods required to prevent segregation.

306-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact ATB asphalt mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

306-3.07 PREPARATION OF EXISTING SURFACE.  Prepare base surface conforming to the Plans and Specifications.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of ATB on these surfaces.

306-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

306-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the ATB, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the ATB, and the RAP when being used in the mix, to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  ATB containing soot or fuel is unacceptable (Subsection 105-1.11).

306-3.10 MIXING.  Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

306-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the ATB remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss; and the physical characteristics of the asphalt binder, lumpiness, or stiffness of the ATB or similar.

306-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute ATB.  Place the ATB upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the ATB surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding ATB may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the ATB in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

Do not cover/place over the asphalt treated base material until the ATB material throughout that section, as defined by the Paving Plan, is placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place ATB over bridge deck membranes, except as directed by the Engineer.

306-3.13 COMPACTION.  Compact the ATB by rolling thoroughly and uniformly.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Prevent indentation of ATB.  Do not leave rollers or other equipment standing on ATB that is not sufficiently cooled to prevent indentation.

A mat area with density lower than 92.0 % MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The MSG of the JMD will be used for the first lot of ATB.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

306-3.14 JOINTS.  Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the ATB to provide a continuous bond, texture, and smoothness between adjacent sections of the ATB.

Coordinate the joints in the ATB pavement layer with the layer of HMA pavement above.  Offset the longitudinal joints in the HMA pavement layer above from the joint in the ATB asphalt pavement layer immediately below by at least 6 inches.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new ATB and thoroughly compact.

306-3.15 SURFACE TOLERANCE.  Costs associated with meeting surface tolerances are subsidiary to the ATB Pay Items.

The Engineer will test the finished surface after final rolling at selected locations using a 10 ft straightedge.  Correct variations from the testing edge, between any two contacts, of more than 1/4 inch.

306-3.16 PATCHING DEFECTIVE AREAS.  Costs associated with patching defective areas are subsidiary to the ATB Pay Items.

Remove defective ATB for the full thickness of the course, do not skin patch.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh ATB to grade (Subsection 306-3.13) and surface tolerance requirements (Subsection 306-3.15).

306-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Asphalt Treated Base.

a)	By weighing.  No deduction will be made for the weight of asphalt binder or anti stripping additive or cutting back joints.

2.	Asphalt Binder.  By the ton, as follows.

Method 1:

Percent of asphalt binder for each sublot multiplied by the total weight represented by that sublot.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  If no acceptance testing is required, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2:

Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing ATB for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste ATB will be calculated using the target value for asphalt binder as specified in the JMD.

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt binder more than 0.4% above the optimal asphalt binder content specified in the JMD.

3.	ATB, Price Adjustment, Type   ; Class  .  Determined under Subsection 306-4.03 Evaluation of Materials for Acceptance.  Also included in the measurement are the fees specified in Subsections 306-2.01, 4.02, 4.03 and 5.01.

306-4.02 ACCEPTANCE SAMPLING AND TESTING.  The Engineer will evaluate ATB for conformance to specifications according to Subsection 306-4.03 Evaluation of Materials for Acceptance.

ASPHALT TREATED BASE

The quantity of ATB produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 10,000 tons.  The lot will be divided into sublots of 1000 tons; each randomly sampled and tested for asphalt binder content, density, and gradation according to this subsection.

If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and evaluation will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 3,000 tons and 10,000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 1000 tons and randomly sampled for asphalt binder content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  ATB quantities of less than 600 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  ATB quantities of 600 tons or greater will be treated as an individual sublot.  The lot will be evaluated according to Subsection 306-4.03 except as noted.

For Contract quantity of less than 3,000 tons, ATB will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the ATB to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any ATB that does not conform to the approved JMD.

The Engineer will determine where samples are taken.

1.	Asphalt Binder Content.  Asphalt treated base mix samples taken for the determination of asphalt binder content will be taken randomly from behind the paver screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt binder content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308, except ATM 405 will not be used when RAP is included in the mixture.

2.	Aggregate Gradation. The gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt binder.

3.	Density.

The Engineer will determine and mark the location(s) where the Contractor will take each mat core sample.  The location(s) for taking mat core samples will be determined using a set of random numbers and the Engineer's judgment.

Cut full depth core samples centered on the marks from the finished ATB within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  Backfill and compact voids left by coring with new ATB within 24 hours.

The Engineer will immediately take possession of the samples.  Density of the samples will be determined, by the Engineer, according to WAQTC FOP for AASHTO T 166/T 275.

A fee will be assessed for each failure to take core samples, backfill core sample voids, backfill core samples within the specified period, or take core samples at the location marked by the Engineer.

4.	Retesting.

A retest of any sample outside the limits specified in Table 306-2 may be requested provided the quality control requirements of 306-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used to evaluate the material regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, when gradation and asphalt binder content are determined from the same sample, retesting for gradation or asphalt binder from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt binder content will include retesting for MSG.

ASPHALT BINDER

The lot size for asphalt binder will normally be 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt binder is between 85 – 200 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt binder will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated in accordance with 306-4.03.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

306-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  A mat area of finished surfacing that is contaminated with foreign material; is segregated (determined visually or by testing), has a lower density than specified, fails to meet surface tolerance requirements, is flushing or bleeding asphalt binder after compaction is complete, or in any other way determined to be defective is unacceptable according to Subsection 105-1.11.  ATB, not meeting the specified limits noted in Table 306-2, is considered defective.  Correct unacceptable work and materials according to Subsection 306-3.16 and as directed by the Engineer.

TABLE 306-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt % | TV -0.4 | TV + 0.4 |
| Mat Density % | 92.0 | 100 |

*Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

ASPHALT BINDER

Asphalt binder will be randomly sampled and tested in accordance with Subsection 306-4.02.  Provide supplier process control test results with the delivery ticket for each load of asphalt binder to the Engineer before unloading asphalt binder at the project. No payment will be made without this documentation.

306-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402.  Also included is the asphalt material in the Prelevel/Leveling Course (rut repair) HMA and Temporary HMA as part of 401, Approach HMA as included in 401 or 639 and Pathway HMA as part of 608.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	The Alaska Asphalt Material Price Index (AAMPI) is posted on the Department’s Materials website along with the formula used to calculate the Index.  The AAMPI as used in the determination of the “Asphalt Material Price Adjustment” is calculated for the first and third Friday of each month.  The index applies from the beginning of the period start day 00:00 hrs, and ends 00:00 hrs the start of the next period.  Other calculation and or period start/end days, including the post day (except as fall on the 1st and 3rd Friday) are not permitted.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP–IB)–(0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB–IPP)–(0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

306-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items the work and materials associated with:

Asphalt binder, anti-stripping additives, surface tolerance corrections, patching defective areas; removal and disposal of rejected ATB, and the hauling equipment are subsidiary to the Asphalt Treated Base Pay Items.

Item 306(8_) ATB, Price Adjustment, Type ___ ; Class __ : is the sum of the price adjustments for each material lot and for fees assessed the Contractor including:

	Each mix design subsequent to the approved Job Mix Design (Subsection 306-2.01) will result in a fee of $2500.00 each.

	Failure to cut core samples within the specified period will result in a fee of $100.00 per sample per day (Subsection 306-4.02).

	Failure to backfill voids left by sampling within the specified period will result in a fee of $100 per hole per day (Subsection 306-4.02).

	Contractor retesting, referee sample testing and Contractor requested testing for visually inspected and rejected asphalt treated base failing to meet specifications will result in a fee being assessed for all costs associated with the test (Subsection 306-4.02, 4.03).

Item 306(15). Asphalt Material Price Adjustment.

For each Section as included in Subsection 306-4.04 Asphalt Material Price Adjustment, item 1, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

306(1)	ATB	Ton

306(2)	Asphalt Binder, Grade PG 64E-40	Ton

306(8_)	ATB, Price Adjustment, Type ___; Class __	Contingent Sum

306(15)	Asphalt Material Price Adjustment	Contingent Sum

CR306-112116

DIVISION 400 — ASPHALT PAVEMENTS
AND
SURFACE TREATMENTS

Blank Page

Special Provision

Replace Section 401 with the following:

SECTION 401
HOT MIX ASPHALT PAVEMENT

401-1.01 DESCRIPTION. Construct one or more courses of plant-produced Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

1.	In this Section, HMA refers to Type I, II, III, and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course: HMA, Type IV, Class B.

MATERIALS

401-2.01 ASPHALT BINDER.  Conform to Subsection 702-2.01. If binder performance grade is not specified, use PG 52-28.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of liquid anti-strip added.

Asphalt binder may be conditionally accepted at the source if a manufacturer's certification of compliance is provided, according to Subsection 106-1.05, and the applicable requirements of Section 702 are met.

401-2.02  LIQUID ANTI-STRIP ADDITIVE.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design (JMD). At least 70% of the aggregate must remain coated when tested according to ATM 414. A minimum of 0.30% by weight of asphalt binder is required.

401-2.03  JOINT ADHESIVE.   Conform to Subsection 702-2.05.

401-2.04  JOINT SEALANT.   Conform to Subsection 702-2.06.

401-2.05  WARM MIX ASPHALT.   Conform to Subsection 702-2.07.

401-2.06  ASPHALT RELEASE AGENT.  Conform to Subsection 702-2.08.

401-2.07 AGGREGATES.  Conform to Subsection 703-2.04.  Use a minimum of three stockpiles of crushed aggregate (coarse, intermediate, and fine).  Place blend material, if any, in a fourth pile.

401-2.08  RECYCLED ASPHALT PAVEMENT.  Recycled asphalt pavement (RAP) may be used in the production of HMA.  The RAP may be from pavements removed under the Contract, or from an existing stockpile.  Conform to Subsection 703-2.16

401-2.09 JOB MIX DESIGN.  Provide target values for gradation that satisfy both the broad band gradation limits shown in Table 703-4 and the requirements of Table 401-1, for the Type and Class of HMA specified.

TABLE 401-1

HMA MARSHALL Design Requirements

| DESIGN PARAMETER | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (Including Asphalt Binder) |  |  |
| Stability, Pounds | 1800 Min. | 1200 Min. |
| Flow, 0.01 Inch | 8 – 14 | 8 - 16 |
| Voids in Total Mix (VTM), % | 3.0 – 5.0 | 3.0 – 5.0 |
| Compaction, Number of Blows Each Side of Test Specimen | 75 | 50 |
| Asphalt Binder |  |  |
| Voids Filled with Asphalt (VFA), % | 65 - 75 | 65 - 78 |
| Asphalt Content, Min. % @ 4% VTM | 5.0 | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |
| Liquid Anti-Strip Additive**,%, Min. | 0.30 | 0.30 |
| RAP, %, Max. | 15.0 | 25.0 |

*Dust-Asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt binder (calculated by weight).

** By Weight of Asphalt Binder

The approved JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the recommended mixing temperature range.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant. The letter shall state whether or not WMA and/or RAP will be used. The letter shall include the proposed gradation for the JMD, gradations for individual stockpiles, and the blend ratio of each aggregate stockpile.

2.	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) in the proposed mix design. Furnish a total of 500 pounds of material in the proportional amounts in the proposed JMD.

3.	Five separate 1-gallon samples of the asphalt binder proposed for use in the HMA. Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature- viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, minimum 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

5.	Testing results per Subsection 106-1.03.1 for each aggregate type proposed for use.

6.	If applicable, a letter stating the WMA technology (Subsection 702-2.07) to be used, location where additive will be introduced and manufacturer’s recommended usage rate for each type of HMA.  Supply a minimum of 2-pint samples for each proposed additive.

7.	If applicable, representative samples of any RAP proposed for use.  Furnish a minimum of 200-pound sample of proposed RAP.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of HMA specified, and establish the approved JMD which will become a part of the Contract.

Anti-strip evaluation (ATM 414) of HMA mix designs that include RAP will be completed without the inclusion of the RAP.

Obtain an approved JMD prior to shipment of aggregates to an asphalt plant site or producing HMA for payment.

Contractor Mix Design.  If a bid item for JMD appears in the contract, or if the Engineer approves a request from the Contractor to perform the JMD at no cost to the Department, provide a JMD following the requirements specified in this section.  Submit the JMD to the Engineer at least 15 working days before HMA production.  Submit samples to the Engineer upon request for JMD verification testing.

All Contractor-furnished JMDs must be sealed by a professional Engineer registered in the State of Alaska.  The Professional Engineer shall certify that the JMD was performed according to the specified procedures, and meets all project specifications.

Changes. Submit a new JMD with changes noted and new samples in the same manner as the original JMD submittal when:

a.	The results of the JMD evaluation do not achieve the requirements specified in Table 401-1

b.	The asphalt binder source is changed

c.	The source of aggregate, aggregate quality or gradation is changed

d.	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD; the original, or a replacement JMD.

The Engineer has the option to require further verification of the JMD under 401-2.10 Process Quality Control.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, materials, and the JMD, Subsection 401-2.10.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.

Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix Design, per Subsection 401-5.01.

401-2.10 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer at the "Pre-Paving Meeting," Subsection 401-3.01, the JMD and a documentation plan that provides a complete, accurate, and clear record of the sampling and testing results.

Failure to perform quality control forfeits the Contractor's right to a retest under Subsection 401-4.02

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

Supplemental Process Quality Control:

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineer's approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train shall be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 401-3.04.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Failed Test Strip:  the Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

Refer to Subsection 401-5.01 for payment of test strips.

CONSTRUCTION REQUIREMENTS

401-3.01 PRE-PAVING MEETING. Meet with the Engineer for a pre-paving meeting in the presence of the project superintendent and paving foreman at least (5) working days before beginning paving operations.  Submit a paving plan and pavement inspection plan at the meeting.  When directed by the Engineer, make adjustments to the plan and resubmit.

1.	Paving Plan.  Include the following:

a.	Sequence of operations

b.	List of equipment that will be used for production, transport, pick-up (if applicable), laydown, and compaction

c.	Summary of plant modifications (if applicable) for production of WMA

d.	Procedures to produce consistent HMA

e.	Procedures to minimize material and thermal segregation

f.	Procedures to minimize premature cooling

g.	Procedures to achieve HMA density

h.	Procedures for joint construction including corrective action for joints that do not meet surface tolerance requirements

i.	Quality control testing methods, frequencies and sample locations for gradation, asphalt binder content, and density, and

J.	Any other information or procedures necessary to provide completed HMA construction that meets the Contract Requirements

2.	Pavement Inspection Plan. Include the following:

a.	Process for daily inspections

b.	Means and methods to remove and dispose of project materials

401-3.02 CONTRACTOR QUALITY CONTROL. Perform quality control (QC) of HMA materials in accordance with Subsection 106-1.03.

401-3.03  WEATHER LIMITATIONS.  Place HMA on a stable/non-yielding roadbed. Do not place HMA when the base material is wet or frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA when the roadway surface temperature is colder than 40° F.

401-3.04 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make all equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of HMA and test strip HMA.

401-3.05  ASPHALT MIXING PLANT.  Meet AASHTO M 156.  Use an HMA plant capable of producing at least 150 tons of HMA per hour noted on posted DEC air quality permit, designed to dry aggregates, maintain consistent and accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the HMA plant and furnish copies of the calibration data to the Engineer at least 24 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.  Provide aggregate and asphalt binder sampling locations meeting OSHA safety requirements.

You may use belt conveyor scales to proportion plant blends and mixtures if the scales meet the general requirements for weighing equipment and are calibrated according to the manufacturer’s instructions.

If WMA is approved by the Engineer, modify the mixing plant as required by the manufacturer and WMA additive manufacturer.

401-3.06  HAULING EQUIPMENT.  Haul HMA in trucks with tight, clean, smooth metal beds. Keep beds free of petroleum oils, solvents, or other materials that would adversely affect the mixture. Apply a thin coat of approved asphalt release agent to beds as necessary to prevent mixture adherence. Provide trucks with covers attached and available for use.

When directed by the Engineer, cover the HMA in the hauling vehicle(s).

Do not haul HMA on barges.

401-3.07 ASPHALT PAVERS.  Use self-propelled asphalt pavers with heated vibratory screed assemblies to spread and finish HMA to the specified section widths and thicknesses without introducing thermal or material segregation.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.  Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA. Heat and vibrate screed extensions. Place auger extensions within 20 inches of the screed extensions or per written manufacturer’s recommendations.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.

Equip the paver with automatic screed controls capable of operating from a reference line or a ski from either or both sides of the paver.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.08  ROLLERS. Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Use rollers designed to compact HMA and capable of reversing without shoving or tearing the mixture. Select rollers that will not crush the aggregate or displace the HMA. Equip vibratory rollers with separate vibration and propulsion controls.

Equip the rollers with an infrared thermometer that measures and displays the surface temperature to the operator. Infrared thermometer may be hand-held or fixed to the roller.

Utilize a pneumatic roller in the complement of rollers to compact the leveling course.  Use fully skirted pneumatic-tire roller having a minimum operating weight of 3000 pounds per tire.

401-3.09  RESERVED.

401-3.10  PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces according to the Contract. Prior to placing HMA, clean existing surfaces of loose material and uniformly coat contact surfaces of curbing, gutters, manholes and other structures with tack coat material meeting Section 402.  Treat cold joint surfaces according to 401-3.17. Allow tack coat to break before placement of HMA on these surfaces.  Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before applying tack coat to an existing paved surface, clean and patch the surface.  Remove irregularities to provide a reasonably smooth and uniform surface.  Remove and replace unstable areas with HMA.  Clean the edges of existing pavements, which are to be adjacent to new pavement, to permit the adhesion of asphalt materials.  Clean loose material from cracks.  Fill the cleaned cracks, wider than 1 inch, with HMA tamped in place.  Wash and/or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

1.	Prelevel remaining ruts, pavement delaminations, and depressions having a depth greater than 1/2 inch with an approved HMA.

2.	Notify the Engineer of pavement areas that appear thin or unstable.  Where milling operation creates thin or unstable pavement areas, or where it breaks through existing pavement, remove thin and unstable pavement, and 2 inches of existing base material, compact and replace with an approved HMA.

401-3.11  PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the recommended mixing temperature range.

401-3.12  PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by ATM 407.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable per Subsection 105-1.11.

401-3.13  MIXING. Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD. Mix to obtain at least 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt binder.

Mix the HMA within the temperature range determined by the JMD.

Upon the Engineer’s request, provide daily burner charts showing start/stop times and temperatures.

401-3.14  TEMPORARY STORAGE OF HMA.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.

Signs of visible segregation, heat loss, changes from the JMD, change in the characteristics of asphalt binder, lumpiness, and stiffness of the mixture, are causes for rejection.

Do not store HMA on barges.

401-3.15  PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, are placed and accepted.

Do not place HMA abutting curb and gutter until curb and gutter are installed, except as approved by the Engineer.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

When practicable, adjust elevation of metal fixtures before paving the final lift, so they will be between 1/4 and 1/2 inch below the top surface of the final lift.  Metal fixtures include, but are not limited to manholes, valve boxes, monument cases, hand holes, and drains.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make mechanical spreading and finishing equipment impracticable.

Place HMA over bridge deck membranes according to Section 508 and the membrane manufacturer's recommendations.

Do not mix HMA produced from different plants for testing or paving.

401-3.16  COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

Prevent indentation in the mat, do not leave rollers or other equipment standing on HMA that has not sufficiently cooled.

The Lower Specification Limit for density is 92.0% of the Maximum Specific Gravity (MSG) as determined by ATM 409.  The MSG from the approved JMD is used for the first lot of each type of HMA.  The MSG for additional lots is determined from the first sublot of each lot.

401-3.17  JOINTS.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the pre-paving meeting.  Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

Form transverse joints by saw-cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints 15 to 25 degrees.

For all joints below the top lift, uniformly coat joint surfaces with tack coat material meeting Section 402.

Uniformly coat the joint face of all top lift joints with a joint adhesive. Follow joint adhesive manufacturer's recommendations for temperatures and application method.  Remove joint adhesive applied to the top of pavement surface.  If infrared joint heaters are used and passing joint densities are achieved in each of the first three joint densities taken, then joint adhesive is not required.

The Lower Specification Limit for top lift longitudinal joint density is 91.0% of the MSG of the panel completing the joint. MSG will be determined according to ATM 409.  Top lift longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03.

For top lift panels that have a longitudinal joint density less than 91.0% of the MSG, seal the surface of the longitudinal joints with joint sealant.  Apply joint sealant according to the manufacturer’s recommendations while the HMA is clean, free of moisture and prior to final traffic marking.  Place the sealant at a maximum application rate of 0.15 gallons per square yard, and at least 12 inches wide centered on the longitudinal joint.  After surface sealing, inlay by grinding pavement striping into the sealed HMA. Use grooving equipment that grinds a dry cut to groove the width, length, and thickness of the striping within the specified striping tolerances.

Correct improperly formed joints that result in surface irregularities according to a corrective action plan.

Complete all hot lapped joints while the mat temperature is over 230F as measured by the Engineer, within 3 inches of the joint. Tack coat and joint adhesive are not required for hot lapped joints. Hot lapped joints will receive the full Longitudinal Joint Density Price Adjustment incentive without testing for joint density.

401-3.18  SURFACE REQUIREMENTS AND TOLERANCE.  The finished surface of all HMA paving must match dimensions shown in the contract for horizontal alignment and width, profile grade and elevation, crown slope, and pavement thickness. Water must drain across the pavement surface without ponding. The surface must have a uniform texture, without ridges, puddles, humps, depressions, and roller marks. The surface must not exhibit raveling, cracking, tearing, asphalt bleeding, or aggregate segregation. Leave no foreign material, uncoated aggregate, or oversize aggregate on the HMA surface.

The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  The Engineer will identify pavement areas that deviate more than 3/16 inch from the straightedge, including joints, as defective work. Perform corrective work by removing and replacing, grinding, cold milling or infrared heating such areas as required. Do not surface patch. After the Contractor performs corrective work, the Engineer will retest the area.

The Engineer will use an inertial profiler to measure the top lift HMA surface in the driving lanes for surface smoothness within 21 days after paving is complete and driving lanes are delineated.

Profiler measurements will not be taken in turn lanes, ramps, lane transitions, or within 25 feet of bridge abutments and transverse joints with pre-existing pavement.

The Engineer will measure the pavement smoothness in both wheel paths of each lane.  The smoothness is measured as International Roughness Index (IRI), reported as inches/mile, at 0.1-mile increments.  Pavement smoothness is the average of all IRI measurements for the project.

The Engineer will identify areas requiring corrective action in accordance with Table 401-4.  Perform full-width corrective action in those areas.  The Engineer may waive corrective work for localized roughness for deficiencies resulting from manholes or other similar appurtenances near the wheel path.

Perform Corrective Actions according to one of the following or by a method approved by the Engineer:

1.	Diamond Grinding.  If the required pavement thickness is not decreased by more than 0.25”, grind to the required surface tolerance and cross section.  Remove and dispose of all waste materials.  Apply joint sealant and sand to exposed aggregates per the manufacturer’s recommendations.

2.	Overlaying.  Mill or sawcut the existing pavement to provide a vertical transverse joint face to match the overlay to the existing pavement.  Apply tack coat on the milled surface and joint adhesive to all vertical joints and overlay the full width of the underlying pavement surface.  Use the same approved HMA for overlays.  Place a minimum overlay thickness of 2.0 inches.

3.	Mill and Fill. Mill the existing pavement to provide a vertical transverse joint face. Apply tack coat to the milled surface and joint adhesive to all vertical joints prior to inlay new HMA to match the existing pavement.  Use the same approved HMA.  Place a minimum thickness of 2.0 inches.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.

Price adjustments for pavement smoothness will be calculated according to Subsection 401-4.03.3.

401-3.19  REPAIRING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt. Remove and dispose defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat according to Section 402.  Place and compact fresh HMA so that compaction, grade, and smoothness requirements are met.

401-3.20  ROADWAY MAINTENANCE.  Inspect daily according to pavement inspection plan. Remove, and dispose of project materials incorrectly deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The Contractor is responsible for damage caused by not removing these materials and any damage to the roadway from the removal method(s).

Repair damage to the existing roadway that results from fugitive materials or their removal.

401-4.01  METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a.	By weight.  No deduction is made for the weight of asphalt binder or anti stripping additive or cutting back joints. If the use of WMA is approved by the Engineer, WMA additives will not be measured and are considered subsidiary to the HMA pay item.

b.	By the final HMA surface area.

2.	Asphalt Binder.  By weight, as follows:

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment is made for any asphalt binder more than 0.4% above the optimum asphalt binder content specified in the JMD.

Method 1: Percent of asphalt binder for each sublot multiplied by the total HMA weight represented by that sublot.  The Engineer will use either ATM 405 or ATM 406 to determine the percent of asphalt binder.  The same test method used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  In the absence of testing, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2: Supplier's invoices minus waste, diversion, and remnant.  This procedure is an Engineer’s option for projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time that tankers are weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment is based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste HMA is calculated using the target value for asphalt binder as specified in the JMD.

3.	Job Mix Design. When specified, a Contractor furnished JMD is measured as one according to the HMA class and type.

4.	Temporary Pavement.  By weight, without deduction for the weight of asphalt binder or anti-strip additive.

5.	Leveling Course.  By Lane-Station (12 foot width) or by weighing without deduction for the weight of asphalt binder or anti-strip additive.

6.	HMA Price Adjustment.  Calculated by quality level analysis under Subsection 401-4.03.1.

7.	Longitudinal Joint Density Price Adjustment.  By the linear foot of top lift longitudinal joint under Subsection 401-4.03.2.

8.	Joint Adhesive.  By the linear foot of longitudinal and transverse joint.

9.	Pavement Smoothness Price Adjustment.  Calculated from inertial profiler data using FHWA’s ProVAL software under Subsection 401-4.03.3.

10.	Asphalt Material Price Adjustment.  Determined under Subsection 401-4.04.

11.	Liquid Anti-Strip Additive.  Based on the number of tons of asphalt binder containing required additive.

12.	Crack Repair.  From end to end of the crack repaired according to 401-3.10, measured horizontally along the centerline of the crack.

13.	Prelevel for Ruts, Delaminations, and Depressions.  By the surface area where prelevel is placed according to 401-3.10(1), measured according to Section 109.

14.	Repair Unstable Pavement.  By the surface area of pavement repaired according to 401-3.10(2), measured according to Section 109.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The bid quantity of each type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot is normally 5,000 tons. The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 401-4.03.1. Seasonal startup or a new JMD requires starting a new lot.

If less than 8 sublots have been placed at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot. The price adjustment computed for the prior lot will include the samples from the shortened lot. If there is no prior lot, and there are at least 3 sublots, the material in the shortened lot will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot. If there are less than 3 sublots, the HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance.

If 8 or 9 sublots have been placed at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot

If the bid quantity is between 1,500 to 4,999 tons, the quantity is considered one lot.  The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 401-4.03.1.

For bid quantity less than 1,500 tons, HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance.

Sampling and testing include the following:

1.	Asphalt Binder Content.  HMA samples shall be taken randomly by the Contractor in the presence of the Engineer from behind the paver screed before initial compaction, or will be taken randomly by the Engineer from the windrow, according to ATM 402 or ATM 403, at the discretion of the Engineer. The location (behind the paver screed or windrow) will be determined at the pre-paving meeting. Random sampling locations will be determined by the Engineer.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  Asphalt binder content will be determined according to ATM 405 or ATM 406, at the discretion of the Engineer.

2.	Aggregate Gradation. Aggregates tested for gradation acceptance will have the full tolerances from Table 401-2 applied.

a.	Drum Mix Plants.  Samples will be taken from the combined aggregate cold feed conveyor via a diverter device, from the stopped conveyor belt or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for samples from the conveyer system will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.

b.	Batch Plants.  Samples will be taken from dry batched aggregates according to ATM 301 or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for dry batch samples will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder.

3.	Density.  The Engineer will determine and mark the location(s) where the Contractor takes each core sample.

a.	Mat Cores:  The location(s) for taking core samples is determined using a set of random numbers (independent of asphalt binder and aggregate sampling set of random numbers) and the Engineer's judgment.  Take no mat cores within 1 foot of a joint or edge. Core samples are not taken on bridge decks.

Longitudinal Joint Cores:  The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.

b.	Take core samples according to ATM 413 in the presence of the Engineer. Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one six-inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  The Engineer will immediately take possession of the samples.  Backfill and compact voids left by coring with new HMA within 24 hours. The Engineer will determine density of samples according to ATM 410.

4.	Retest.  When test results have failed to meet specifications, retest of acceptance test results for asphalt binder content, gradation, and density may be requested provided the quality control requirements of Subsection 401-3.02 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2-foot radius of the original core.  The original test results are discarded and the retest result is used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  When gradation and asphalt binder content are determined from the same sample, a request for a retest of either gradation or asphalt binder content results in a retest of both. Both gradation and asphalt binder content retest results are used in the price adjustment calculation. Retesting will be performed by the Department's regional laboratory.

5.	Asphalt Binder Grade.  The lot size for asphalt binder is 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it is added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it is sampled, tested and evaluated as a separate lot.

If the bid quantity of asphalt binder is between 85 – 200 tons, the bid quantity is considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Sample asphalt binder at the plant from the supply line in the presence of the Engineer according to ATM 401.  The Engineer will take immediate possession of the samples.  Take three samples from each lot, one for acceptance testing, one for Contractor requested retesting, and one held in reserve for referee testing if requested.  Meet Subsection 702 requirements for asphalt binder quality.

6.	Asphalt Binder Grade Retest. Replace with the following:

Asphalt Binder Grade Retest. The assigned test value (ATV) will be determined using ASTM D3244. Testing will be by AASHTO accredited independent laboratories.  Each test will be completed by a different laboratory.

Retest.  Submit a written request, for a retest, no more than 7 days from receiving notice of the failed acceptance test. In the request, identify the retest laboratory. The Engineer will send the second sample (retest sample) to the laboratory.  Provide the retest results to the Engineer. Contractor pays for the retest costs.

If the average of the combined test results ([acceptance + retest]/2) passes the specification requirement, the average value becomes the ATV. If this ATV fails the specification requirement, the Engineer or Contractor may request the third sample (referee sample) be tested.

Referee Test. The Engineer will send the third sample (referee sample) to an agreed upon laboratory. The average of the combined test results ([acceptance + retest + referee]/3) equals the ATV. If the ATV fails to meet specifications, the Contractor pays for the referee test.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The following methods are applied to each type of HMA with Price Adjustment Pay Items in the Contract.  These methods describe how price adjustments are determined based on the quality of the HMA binder longitudinal joint density and pavement smoothness.

The Engineer may reject material which appears to be defective based on visual inspection.  If a test of rejected material is requested, a minimum of two samples are collected from the rejected material and tested.  If all test results are within specification limits, payment for the material is made.

1.	HMA Price Adjustment.  Acceptance test results for HMA asphalt binder content, gradation and mat density are used in HMA price adjustment.  These test results for a lot are analyzed collectively and statistically by the Quality Level Analysis (QLA) method as specified in Subsection 106-1.03.3 to determine the total estimated percentage of the lot that is within specification limits. The values for percent passing the #200 sieve, asphalt binder content and density test results are reported to the nearest 0.1 percent.  All other sieves used in QLA are reported to the nearest whole number.

The HMA price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor (CPF) for HMA that includes gradation and asphalt binder content.  The second is the density pay factor (DPF).

A lot containing material with less than a 1.00 pay factor is accepted at an adjusted price, provided that pay factor is at least 0.80 and there are no isolated defects identified by the Engineer. A lot containing material that fails to obtain the minimum pay factor is considered unacceptable and rejected under Subsection 105-1.11.

HMA pay factors are computed as follows:

a.	All statistical Quality Level Analysis (QLA) is computed using the Engineer’s Price Adjustment programs.

b.	The USL and LSL are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2, or as shown below.  The TV is the specification value shown in the approved Job Mix Design.

TABLE 401-2

HMA LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| ¾” or largest sieve size | 99 | 100 |
| ½ inch sieve or first sieve retaining aggregate | TV-6 | TV+6 |
| 3/8 inch sieve | TV-6 | TV+6 |
| No. 4 sieve | TV-6 | TV+6 |
| No. 8 sieve | TV-6 | TV+6 |
| No. 16 sieve | TV-5 | TV+5 |
| No. 30 sieve | TV-4 | TV+4 |
| No. 50 sieve | TV-4 | TV+4 |
| No. 100 sieve | TV-3 | TV+3 |
| No. 200 sieve | TV-2.0 | TV+2.0 |
| Asphalt Binder Content, % | TV-0.4 | TV+0.4 |
| Mat Density, % | 92.0 | 100.0 |

c.	The percent within limits (PWL), Quality Levels and characteristic pay factors (PFs) are determined by the Engineer for each Lot in accordance with Subsection 106-1.03.3.  The Composite Pay Factor (CPF) for the lot is determined from gradation and asphalt binder content (ac) acceptance test results using the following example formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

Table 401-3 gives the weight factor (f) for each test property considered.

TABLE 401-3

WEIGHT FACTORS

| Property | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1 inch sieve | 4 | - | - |
| ¾ inch sieve | 4 | 4 | - |
| ½ inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Content, % | 40 | 40 | 40 |

The Density Pay Factor (DPF) is computed using HMA mat core compaction acceptance test results.

The CPF and DPF are rounded to the nearest 0.001.  The price adjustment for each individual lot is calculated as follows:

HMA Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower

PAB = Price Adjustment Base = $110.00 per ton.

The HMA Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 401(8A) and Item 401(8AH).

2.	Longitudinal Joint Density Price Adjustment.  Longitudinal joint density price adjustment will be based on the project average of all top lift cold joint densities and determined as follows:

a.	Disincentive. Project average top lift joint density less than 91.0% MSG:

Deduct $3.00 per lineal foot.

b.	Incentive. Project average top lift joint density greater than:

92.0% MSG.		Add $0.50 per lineal foot

93.0% MSG.		Add $1.00 per lineal foot

94.0% MSG.		Add $1.50 per lineal foot

The longitudinal Joint Density Price Adjustment is the total price adjustment paid for under Item 401(9).

3.	Pavement Smoothness Price Adjustment.  Pavement smoothness will be measured by the Engineer and reported as IRI (inches/mile), according to Subsection 401-3.18.  Incentive for pavement smoothness shall apply only if both the project average CPF and DPF are greater than or equal to 1.000.  Disincentive for pavement smoothness shall apply regardless of the project average CPF or DPF.

The Engineer will calculate the pavement smoothness price adjustment according to Method 1 (pavement placed over graded subgrade), or Method 2 (pavement placed over existing pavement).

Method 1: SPA = PAB x PQ x SF,

where:

SPA = Pavement Smoothness Price Adjustment

PAB = $110.00 per ton,

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor (Table 401-4)

TABLE 401-4

SMOOTHNESS FACTOR (SF)

| IRI (in./mile) | SF |
| --- | --- |
| Less than 40 | 0.05 |
| 40 to 70 | 0.05 – (IRI - 40)/600 |
| 70 to 90 | 0.00 |
| 90 to 120 | (90 – IRI)/120 |
| Greater than 120* | - |

* Corrective Work required, see Subsection 401-3.18

Method 2: SPA = PAB x PQ x SF,

Where:

SPA = Pavement Smoothness Price Adjustment

PAB = $110.00 per ton,

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor = 0.12 x RR – 0.02; SF not to exceed 0.05

RR = Roughness Reduction = (Initial IRI – Final IRI) / Initial IRI

Initial IRI = 	Pre-project average IRI as measured and reported by the Engineer.  The Initial IRI will either be included in the bid documents or the timeline for when the Initial IRI will be measured will be identified in the bid documents.

Final IRI =	Top layer HMA average IRI as measured and reported by the Engineer according to Subsection 401-3.18.

The Pavement Smoothness Price Adjustment is the total price adjustment paid for under Item 401(10).

4.	Asphalt Binder Price Adjustment. A lot quantity of asphalt binder, with a pay factor less than 1.0, is accepted or rejected per Table 401-3.01-1 Asphalt Binder Pay Factors.

TABLE 401-4.03-1

ASPHALT BINDER PAY FACTORS

| Pay Factor |  |  | 1.01 | 1.00 | 0.95 | 0.90 | 0.75 | Reject |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RTFO (Rolling Thin Film Oven) |  |  |  |  |  |  |  |  |
| DSR(a.1) | All Grades | G*/Sinδ, kPa-1 | ≥ 2.69 | 2.68–2.20 | 2.19–1.96 | 1.95–1.43 | 1.42–1.10 | < 1.10 |
| MSCR(a.2) | PG 52V-40 | JNR 3.2 |  0.39 | 0.40–0.50 | 0.51–0.59 | 0.60–0.69 | 0.70–1.00 | > 1.00 |
|  |  | % Rec3.2 | ≥ 86 | 85–75 | 74–68 | 67–60 | 59–55 | < 55 |
|  | PG 58E-34 | JNR 3.2 |  0.19 | 0.20–0.25 | 0.26–0.29 | 0.30–0.39 | 0.40–0.50 | > 0.50 |
|  |  | % Rec3.2 | ≥ 90 | 89–85 | 84–80 | 79–75 | 74–70 | < 70 |
|  | PG 64E-40 | JNR 3.2 | < 0.05 | 0.05–0.10 | 0.11–0.15 | 0.16–0.20 | 0.21–0.25 | > 0.25 |
|  |  | % Rec3.2 | ≥ 97 | 96–95 | 94–91 | 90–85 | 84 – 80 | < 80 |
| PAV (Pressurized Aging Vessel) |  |  |  |  |  |  |  |  |
| DS(a.3) | PG 64E-40 & All Other Grades | G*Sinδ, kPa | < 4711 | 4712–5000 | 5001–5289 | 5290–5578 | 5579–5867 | > 5867 |
|  | PG 52V-40, PG 58E-34 | G*Sinδ, kPa | < 5700 | 5701–6000 | 6001–6300 | 6301–6600 | 6601 – 7000 | > 7000 |
| CS(a.4 & 5) | All Grades(a.4) | BBR, S, MPa | < 247 | 248–300 | 301–338 | 339–388 | 389–449 | > 450 |
|  | All Grades(a.5) | BBR, m | > 0.320 | 0.319–0.300 | 0.299–0.294 | 0.293–0.278 | 0.277–0.261 | < 0.261 |

Creep Stiffness (CS)	Dynamic Shear (DS)	Multiple Stress Creep Recovery (MSCR)

a.	Asphalt Binder Pay Adjustment = (Lowest Pay Factor – 1) x (tons in lot) x PAB x 5

Select the lowest pay factor from:

RTFO (test the binder residue at the performance grade temperature)

(1)	DS, All Grades, G*/Sinδ, kPa-1

(2)	MSCR: PG, Select the highest pay factor corresponding to, either JNR 3.2 or % Rec3.2 values

PAV

(3)	DS, PG, G*Sinδ, kPa

(4)	CS, All Grades, BBR, S MPa

(5)	CS, All Grades, BBR, m

b.	If three consecutive acceptance samples are out of specification, stop HMA production immediately and submit a corrective action plan to the Engineer for approval.

The Asphalt Binder Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 401(21).

401-4.04  ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 401 thru 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project during the pay period, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

401-5.01 BASIS OF PAYMENT.

The following items, unless included as individual Pay Items, are subsidiary to the Section 401 Hot Mix Asphalt Pavement related Pay Items as included in the bid schedule:

	Asphalt binder

	Liquid anti-strip additives

	Tack coat

	Crack sealing

	Crack repair

	Joint adhesive

	Surface sealing of longitudinal joints

	Surface tolerance corrections

	Patching defective areas

	Prelevel for ruts, delaminations, and depressions

	Repair unstable pavement

	Job mix design

	Density profiles, Subsection 401-2.10 Process Quality Control

	Repair work and materials when planing equipment breaks through existing pavement – Subsection 401-3.10 Preparation of Existing Surface

	Work and materials associated with Subsection 401-3.06 Hauling Equipment

	Work and materials associated with Subsection 401-3.20 Roadway Maintenance

Test Strips:  Subsection 401-2.10 Process Quality Control.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices for HMA and asphalt binder as included in the Bid Schedule.  Price adjustments 401(8_), 401(9), 401(10) and 401(15) do not apply.

b.	Failed.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

CR401R-120117_SSHC2017/CFHWY00317

Item 401(5) HMA, Temporary, Type II ; Class B . Asphalt binder, liquid anti-strip additives, and removal and disposal of temporary HMA is subsidiary.

CR401R-SSHC2017/CFHWY00317

The following price adjustment Pay Items, unless included as individual Pay Items in the bid schedule, are payed under 401(8A) HMA Price Adjustment, Type II; Class A:and 401(8AH) HMA Price Adjustment, Type II; Class AH.

401(8_) HMA Price Adjustment, Type     ; Class     ,

401(9) Longitudinal Joint Density Price Adjustment,

401(10) Pavement Smoothness Price Adjustment, Method    .

401(21) Asphalt Binder Price Adjustment

Items 401(8A) HMA Price Adjustment, Type II; Class A and 401(8AH) HMA Price Adjustment, Type II; Class AH are the sum of the price adjustments for each material lot, and for deductions and fees assessed.  Deductions and fees assessed include:

	Each mix design subsequent to the approved JMD for each type and class of HMA specified will result in a fee of $6000.

	Failure to cut core samples within the specified period will result in a deduction of $100 per sample per day.

	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day.

	If an asphalt binder referee test is requested and the ATV confirms the asphalt binder does not meet Contract requirements, a fee of $500 will be assessed.

Items 401(8A) HMA Price Adjustment, Type II; Class A and 401(8AH) HMA Price Adjustment, Type II; Class AH do not apply to the following:

	HMA contract quantity is less than 1500 tons.

	HMA leveling course and rut repair.

	Temporary HMA.

	Driveway and approach HMA.

Item 401(15) Asphalt Material Price Adjustment.

For each Section as included in Subsection 401-4.04 Asphalt Material Price Adjustment, item 1.a, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

Item 401(16) Crack Repair.  Cleaning loose material from cracks, asphalt binder, and HMA to fill cracks are subsidiary.

Item 401(17) Prelevel for Ruts, Delaminations, and Depressions.  Cleaning loose material, asphalt binder, and HMA are subsidiary.

Item 401(18) Repair Unstable Pavement. Removal of pavement and base course, asphalt binder, and HMA are subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1A)	HMA, Type II; Class A 	Ton

401(1AH)	HMA, Type II; Class AH 	Ton

401(2)	HMA, Leveling Course, Type  IV ; Class  B 	Lane-Station

401(3)	HMA, Leveling Course, Type  IV ; Class  B 	Ton

401(4)	Asphalt Binder, Grade PG 64E-40 	Ton

401(5)	HMA, Temporary, Type  II ; Class  B 	Ton

401(6)	HMA, Type     , Class     	Square Yard

401(7)	Liquid Anti-Strip Additives	Contingent Sum

401(8A)	HMA Price Adjustment, Type II ; Class A 	Contingent Sum

401(8AH)	HMA Price Adjustment, Type II ; Class AH 	Contingent Sum

401(9)	Longitudinal Joint Density Price Adjustment	Contingent Sum

401(10)	Pavement Smoothness Price Adjustment, Method     	Contingent Sum

401(13)	Job Mix Design	Each

401(14)	Joint Adhesive	Linear Foot

401(15)	Asphalt Material Price Adjustment	Contingent Sum

401(16)	Crack Repair	Linear Foot

401(17)	Prelevel for Ruts, Delaminations, and Depressions	Square Yard

401(18)	Repair Unstable Pavements	Square Yard

401(21)	Asphalt Binder Price Adjustment	Contingent Sum

CR401R-120117_SSHC2017/CFHWY00317

Special Provision

Replace Section 406 with the following:

SECTION 406
RUMBLE STRIPS

406-1.01 DESCRIPTION.  Form a series of indentations (rumble strips) into the roadway pavement.  Place rumble strips in each shoulder to the width, depth and length as indicated in the Contract documents and/or as directed by the Engineer.

406-1.02 RUMBLE STRIP.  A single uniform circular concave (cross section) indentation/depression milled into the pavement surface having a length measured perpendicular to the direction of travel, a width measured in the direction of travel and a depth measured from the surface of the pavement to the bottom of the indentation.

406-2.01 MATERIALS.  None.

406-2.02 MILLING EQUIPMENT.  Use equipment designed specifically for milling rumble strips into asphalt pavement.  Equip milling machine with a rotary type cutting head with a maximum outside diameter of 24-inches and a minimum length of 16-inches capable of producing a depression both 12-inches and 16-inches in length by 7 1/2-inches in width to a depth shown in the Plans.  Arrange the cutting tips to provide a smooth cut (approximately 1/16-inch between peaks and valleys).

Furnish the milling equipment with a guidance system, including a guide, clearly visible to the operator, to provide for consistent alignment of each rumble strip cut at the offsets from traveled way indicated on the Plans and to provide uniformity and consistency throughout the project.  The equipment shall incorporate water into the cutting head to minimize dust caused by the milling operation.

Equipment Manufacture: provide training for the operators and a representative onsite during installation of the rumble strip test section(s) (Subsection 406-3.03).  Representative: remain onsite until test specimen(s) satisfy the Plans and Specifications as determined by the Engineer.

CONSTRUCTION REQUIREMENTS

406-3.01 PAVEMENT SURFACE PREPARATION.  Inspect roadway to receive rumble strips for acceptable pavement condition and stake locations to receive rumble strips prior to installation.  Prepare the roadway for the milling operation by providing a smooth clean surface.  Sweep all loose material from the roadway surface in line with the planned rumble strips and to each side of the strips for the width of the milling machine plus an additional 12” minimum per side or edge of pavement whichever is smaller, and as directed by the Engineer.

Sweep and broom as noted and with the equipment indicated in Subsection 643-3.04, No. 6, Sweeping and Power Brooming.

406-3.02 TOLERANCES FOR RUMBLE STRIPS.

1.	Length:   1/2-inch.

2.	Width:  1/2-inch.

3.	Depth:  1/16-inch.

4.	Spacing:   1/2-inch.

5.	Alignment:  1-inch from the striping layout in the Plans; existing striping and re-established striping.

If it is determined that the rumble strips are not being placed to specification, make immediate adjustments to correct the problem.

Rumble strips are unacceptable if:

1.	The strips are not straight.

2.	The length or width does not meet tolerance.

3.	The depth of the depression does not meet tolerance.

4.	The depression/indentation concave surface is not smooth, does not meet tolerance.

5.	The edge of the indentation/depression is not straight, smooth, and free of spalling.

6.	Pavement surface is damaged as a result of improper rumble strip installation.

Unacceptable rumble strip installation, dimensional, alignment, surface irregularities, and surface damage shall be ground, resurfaced and the rumble strip reinstalled to the satisfaction of the Engineer and at the Contractor’s expense.  Perform repairs using equipment similar to the equipment initially used to mill the rumble strip.  Do not perform repairs in a “patch work” manner.  If more than one repair is required; in a group of rumble strips repair the entire group.  Where a repair is required in a continuous run, repair the unacceptable rumble strip(s) and repair or replace the rumble strip to each side of the unacceptable rumble strip as required to provide continuity between rumble strips as originally intended.  The Engineer will confirm the extent of the repair(s) required.

If during production the work becomes unacceptable the Engineer may require resumption of testing, Subsection 406-3.03.  Testing in addition to the initial test for each rumble strip type will be at the Contractor’s expense.

406-3.03 RUMBLE STRIP TEST SECTION.  Install an initial 1/4 mile test section for each of the following rumble strip type(s):

1.	Shoulder.

Demonstrate for each type of rumble strip that the equipment and method will provide the desired milled-in rumble strip, including the surface inside each depression, without damaging the surrounding asphalt pavement.  If any of the initial test sections do not meet tolerances, provide new equipment, new method, or make necessary adjustments and retest.  These additional test sections will be required before production runs will be allowed to begin.

Testing in addition to the initial test sections, one for the shoulder type and one for the centerline type, will be at the Contractor’s expense.

Additionally, demonstrate the means and methods, including the equipment, for containing dust and waste material.

406-3.04 TRAFFIC STRIPING RE-ESTABLISHMENT.  Traffic striping is required to provide guidance for the rumble strip installation operation.  Contractor, where shoulder and/or centerline striping is missing to the extent that rumble strip location cannot be determined by the Engineer, re-establish the striping location prior to the milling operation.  Re-establish missing striping location by measuring laterally across the roadway from adjacent visible striping.  Maintain the same lane widths that exist at each end of the missing striping.  Provide sufficient location marking or “rabbit tracks” to ensure an accurate milling operation.  Shoulder re-striping is not required.  Re-establishing roadway striping location will not be measured or paid for separately but will be subsidiary to the respective rumble strip pay items.

406-3.05  RUMBLE STRIP INSTALLATION.  Install the following types of rumble strip at the locations shown in the Plans:

1.	Shoulder.  Do not disturb existing shoulder striping.

In compacted pavement with a temperature below 80˚ F, mill each type of rumble strip to the dimensions shown in the Plans.  Locate the inside edge of the rumble strip as shown in the Plans.  The Engineer will randomly check the edge alignment of the milled pattern.

406-3.06 CLEAN UP OF MILLINGS.  Handle, transport, and store, or dispose of material according to DEC regulations.  Remove off the project, on a daily basis, waste material (millings) resulting from the operation.

Disposal:  Dispose waste material outside the project limits, unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the property owner.  Milled material not being spread on the roadway side slopes requires a Solid Waste Disposal Permit from the DEC.  Obtain a permit for disposal of milled material or dispose the material in a site previously approved.

Remove millings immediately following rumble strip installation.  Maintain the removal operation within 50 feet of the milling machine.  Dry power brooming and power brooming without direct immediate means of collection/pickup is not permitted.

During milling operations keep the travel lanes free of milling debris.  Do not berm the millings at the shoulder edge, do not allow milling debris to impede roadway drainage or enter waterways.  Use a sweeper, sweeper/vacuum, (Subsection 643-3.04 No. 6, Street Sweeping, and Power Brooming), continuously removing waste material, including dust from the operation.  Keep millings damp to help control airborne dust.  Millings shall not enter adjacent lanes open to traffic.

Remove the waste material from the roadway surface and any adjacent pathway beyond the shoulder.  Shoulder millings may be placed off of the road or pathway beyond the shoulder on the side slopes, except in areas where guardrail is present.  Uniformly spread shoulder millings on the roadway side slopes; alternatively, it may become property of the Contractor and disposed of off the project as indicated above.

Milled roadway segments shall be returned to debris-free state prior to re-opening for traffic.

406-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Measure pay units by station, foot, or mile parallel to the centerline of the highway.

Station.  A single lineal measurement for every measured station for each shoulder rumble strip and centerline rumble strip installed.

Linear Foot.  A single lineal measurement for every measured foot of rumble strip installed.

Mile.  A single lineal measurement for every measured mile for each shoulder rumble strip and centerline rumble strip installed.

Shoulder rumble strip measurement includes gaps (provided for bicycles or other as shown in the Plans) between groups of rumble strips.

406-5.01 BASIS OF PAYMENT.  Section 109.

Except where specified as individual Pay Items:

All work, including test strips and materials is subsidiary to 406 Pay Items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

406(1)	Rumble Strips	Lump Sum

406(2)	Rumble Strips	Station

406(3)	Rumble Strips	Linear Foot

406(4)	Rumble Strips – Shoulders	Mile

406(5)	Rumble Strips – Centerline	Mile

406(6)	Sweeping and Disposal of Millings – Shoulders	Lump Sum

406(7)	Sweeping and Disposal of Millings – Centerline	Lump Sum

CR406-110812

DIVISION 500 — STRUCTURES

Blank Page

SECTION 505
PILING

Special Provisions

505-3.03 PILE BEARING VALUES.  Delete the first paragraph of this subsection and substitute the following:

Drive piles, except piles for lighting standards and traffic signals, to the required ultimate bearing capacity.  For lighting standards and traffic signals, install piles of sufficient length to cut the pile at the required cut off elevation and to provide the minimum installed length shown on the Plans.

CR505.2/CFHWY00317

CR505.1/CFHWY00317

505-3.09 DRIVING PILES.  Add the following:

Sites for the lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

CR505.2-012317/CFHWY00317

When the minimum pile length shown on the Plans for a lighting standard or traffic signal foundation cannot be achieved, install the pile tip to an elevation established by the Engineer.

CR505.2/CFHWY00317

505-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

Include costs of furnishing and installing piles for lighting standards for Pay Item 660(3) Highway Lighting System Complete.

CR505.2-012317

Add the following to the second paragraph:

Include costs of furnishing and installing piles for traffic signal standards for Pay Item 660(1) Traffic Signal System Complete.

CR505.1/CFHWY00317

Special Provision

Add the following Section:

SECTION 514
CONCRETE SURFACE FINISH AND TREATMENT

514-1.01 DESCRIPTION. Construct surface finish and apply surface treatment on concrete walls.

514-1.02 SUBMITTAL. All manufacturers are required to submit documentation for the Engineers review and approval. Allow 21 days for review. Refer to 105-1.02 Plans and Working Drawings. Submit:

1.	Shop drawings including form liner layout and termination details. Indicate backup, rustication, reveal, and chamfer strip locations. Show jointing, form tie location and pattern of placement.

2.	Product data verifying compliance with specification.

3.	Installation instructions.

4.	Samples 24-inch x 24-inch of each pattern required.

514-2.01 MATERIALS.

Rubbed Finish	Section 501, ACI 301.

Aesthetic Fascia	Cultured stone product made of limestone and 50% recycled material.

Pattern	Similar to Boral Limestone Veneer as supplied by Anchorage Sand and Gravel.

Anti-graffiti Protection	Permanent, no discoloration, and not a sealer or vapor barrier.

Two step system:

1.	Single component clear acrylic base coat

2.	Single component clear urethane finish

CR514/CFHWY00317

514-3.01 CONSTRUCTION REQUIREMENTS. Construct surface finish, and surface treatment with trained personnel according to these specifications, ACI 301 and the manufacturer.

514-3.02 SURFACE FINISH. Apply a rubbed finish, Section 501-3.09, to all exposed concrete surface, except where an aesthetic fascia is noted in the Plans.

CR514-092016/CFHWY00317

Aesthetic Fascia. Apply an aesthetic fascia, using cultured stone, to exposed vertical concrete surface where noted in the Plans. Account for the concrete quantity and dimensions associated with the cultured stone veneer. Wall dimensions and concrete quantities provided on the plans are minimums and do not include allowances for the thickness of the cultured stone veneer.

Place the cultured stone veneer as required by the manufacturer. The Engineer will inspect the veneer placement and installation and provide directions for required changes, corrections, or adjustment.

CR514/CFHWY00317

514-3.03 SURFACE TREATMENT.

Anti-graffiti Protection.  Allow 28 days after the forms are removed and the concrete finish is completed before applying anti-graffiti protection treatment.  Apply base coat and two top coats. Follow the manufacturer's instructions for application and curing of the treatment materials.  Protect surfaces from the treatment materials that are not specified for coating.

CR514-092016/CFHWY00317

514-4.01 METHOD OF MEASUREMENT.  Section 109.

514-5.01 BASIS OF PAYMENT.

Payment for aesthetic fascia is subsidiary to the Gateway Sign.

Work and materials required to construct the supporting element will be paid separately under the respective items listed in the bid schedule.

Rubbed finish is subsidiary to the item being finished.

CR514/CFHWY00317

Blank Page

DIVISION 600 — MISCELLANEOUS
CONSTRUCTION

Blank Page

Special Provisions

Replace Section 601 with the following:

SECTION 601

METAL FLUME INLET

601-1.01 DESCRIPTION.  Furnish and install metal flume inlet as shown on the Plans or as directed by the Engineer.

601-2.01 MATERIALS.  Use materials that conform to the following:

Class A Concrete	Section 501

Metal Flume Inlet.  Use any one of the base metals listed in AASHTO M 36 or AASHTO M 196, minimum sheet thickness of 0.125 inches.  Galvanize Metal flume inlet according to AASHTO M 111 and steel nuts and bolts according to ASHTO M 232.

601-3.01 CONSTRUCTION REQUIREMENTS.  Use metal flume inlet conforming to the details and dimensions shown on the Plans.  Submit manufacturer’s specifications and installation guide to the Engineer for review and approval before ordering metal flume inlet.

Restore the ground adjacent to the completed metal flume inlet to the surrounding ground contours as directed by the Engineer.

601-4.01 METHOD OF MEASUREMENT.  Section 109, by each, complete in place.

601-5.01 BASIS OF PAYMENT. The contract price includes furnishing and installing new metal flume inlet, concrete and associated hardware.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

601(2)	Metal Flume Inlet	Each

CFHWY00317

SECTION 603
CULVERTS AND STORM DRAINS

Special Provisions

603-1.01 DESCRIPTION.  Add the following:

This work shall consist of installing culvert marker posts.  This work shall also consist of installing pipe sleeves on storm drain pipes at all locations where storm drain pipes cross water lines.

CR603.2/CFHWY00317

603-2.01 MATERIALS.  Delete the second paragraph and substitute the following:

When Item 603(17-XX), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP) or Reinforced Concrete Pipe.  Corrugated Polyethylene Pipe is not allowed.  End Sections for Metal Pipe must be of the same material as the pipe.

Add the following:

Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5-inch by 6-foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9-inches.

CR603.2-110316/CFHWY00317

Add the following:

When Item 603(22-XX) XX-Inch CSP, Smooth Wall is listed in the bid schedule, furnish Corrugated Steel Pipe (CSP) with a smooth interior surface, exterior ribs, and a maximum Manning’s value of n=0.012.

CFHWY00317

603-3.02 LAYING PIPE

Add the following:

Lay storm drain pipe so that there are no joints within 9 feet of waterline crossings.

CFHWY00317

603-3.03 JOINING PIPE.

2.	Metal Pipe.  Add the following after the 2nd sentence:

Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe of similar or dissimilar materials, regardless of the type of coupling band.  Except, the end section joint does not require a gasket.  Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

CR603.1-102016/CFHWY00317

Add the following:

- Watertight Band. Furnish and install bands with gasket that resist 10 PSI. Use at locations shown in the Plans or as directed by the Engineer.

After installation, perform a pressure test to verify resistance to exfiltration and leakage. Testing, retesting, and any required repairs to pass testing of the installed pipe is an obligation of the Contractor to perform and is incidental to the bid item.  Acceptance testing is to be performed in the presence of the Engineer.

Pressure testing shall conform to one of the following methods:

(1)	Hydrostatic Exfiltration Test

Upon completion of a section of pipe between manholes the Contractor is to plug all ends of the pipe prior to commencing testing.

A minimum head of 6 feet of water above the crown at the upper end of the test section is to be maintained for a period of four hours during which time it will be presumed that full absorption of the pipe body has taken place and thereafter for a further period of one hour for the actual test of leakage.  During this one-hour period, the measured loss must not exceed the rate of 50 gallons per inch diameter per mile per twenty-four hours.  Exfiltration in greater amounts will be cause for rejection of the pipe.

The maximum length of pipe for the above allowable leakage test is 1,000 feet.  If it is not apparent that leakage test results between any two manholes is satisfactory, then the Engineer may require subsequent tests to establish the more exact location of the leakage areas.  Any section of pipe between any two manholes that does not meet the above requirements will be rejected.

(2)	Low Pressure Pneumatic Exfiltration Test

Safety braces are required to hold plugs in place and to prevent a sudden release of compressed air.  Due to the large forces that could be exerted by an escaping plug during the testing of the pipe, workmen must not be allowed in the manholes in which plugs have been placed while internal pipe pressure is above atmospheric pressure such as while testing is in progress.  The Contractor’s testing equipment is to be arranged in such a manner that a pressure relief device will prohibit the pressure in the pipeline from exceeding ten pounds per square inch (10 PSI).

All air used to pressure up the line being tested is to pass through a single above ground control panel.  The above ground air control equipment is to include a shut-off valve, pressure relief valve, input pressure gauge, and a continuous monitoring pressure gauge having a pressure range from 0 to at least 10 PSI.  The continuous monitory gauge is to be no less than 3 inches in diameter with a minimum division of 0.10 PSI and an accuracy of plus or minus 3%.  Two separate hoses connected to their own dedicated plug connection are to be used to:

- Connect the control panel to the sealed line for introducing low-pressure air, and

- A separate hose connection for constant monitoring of air pressure build-up in the line.

Air is to be slowly supplied to the test section until the internal air pressure reaches 4.0 PSI.  At least two minutes will be allowed for temperature stabilization before proceeding further.

When temperatures have been equalized and the pressure stabilized at 4.0 PSI, the air hose from the control panel to the air supply is to be disconnected.  The pressure is to be decreased through bleeding to the test pressure which is to be 3.5 PSI.  Upon reaching the test pressure, begin timing with a stopwatch.

If the pressure drops 1.0 PSI before time expires as found in the table below then the section undergoing testing has failed and must be repaired and/or retested.

| Nominal Pipe Diameter (Inches) | Minimum Test Time by Length (Minutes : Seconds) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 100 ft | 150 ft | 200 ft | 250 ft | 300 ft | 350 ft | 400 ft | 450 ft |
| 12 | 11:20 | 11:20 | 11:24 | 14:15 | 17:05 | 19:56 | 22:47 | 25:38 |
| 18 | 17:00 | 19:13 | 25:38 | 32:03 | 38:27 | 44:52 | 51:16 | 57:41 |
| 24 | 22:47 | 34:11 | 45:34 | 56:58 | 68:22 | 79:46 | 91:10 | 102:33 |

CFHWY00317

3.	Polyethylene Pipe.  Add the following after the 1st sentence:

Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe.  Except, the end section joint, and where the pipe is manufactured with a locking joint such that the joint seals watertight, a gasket is not required.  Use flexible watertight gaskets meeting ASTM F 477 or ASTM F 913.

CR603.1-102016/CFHWY00317

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two inches of post shall remain above the ground after driving.

CR603.2-110316/CFHWY00317

Add the following subsection:

603-3.07 PIPE SLEEVE.  Pipe sleeve shall be corrugated polyethylene pipe, Type S.  Pipe sleeve diameter shall be the next larger diameter that fits over the storm drain pipe being sleeved.

Pipe sleeves shall be continuous (no joints) for the required length or the joint shall be wrapped with a water tight heat shrink covering.  Sleeves shall extend a minimum of 10 feet horizontally from any water pipe joint.  Seal open ends of pipe sleeves with stainless steel banded, synthetic rubber end seal to mitigate against soil intrusion.

CFHWY00317

603-5.01 BASIS OF PAYMENT.  Replace the first sentence with:

Coupling bands, gaskets and other items necessary for the proper joining of the sections are subsidiary.

CR603.1-102016/CFHWY00317

Add the following:

Culvert marker post(s) are subsidiary to pipe Pay Items.

CR603.2-110316/CFHWY00317

Add the following:

Pipe sleeves are subsidiary to pipe Pay Items.

CFHWY00317

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

603(22-_)	_ Inch CSP, Smooth Wall	Linear Foot

CFHWY00317

SECTION 604
MANHOLES AND INLETS

Special Provisions

Add the following:

604-3.02 MANHOLE EXFILTRATION TEST.  Where noted on the plans, or as directed by the Engineer, perform exfiltration test to check for leaks and ensure water tightness.  Labor, equipment, supplies and water required for the test shall be furnished by the Contractor.  The Engineer shall witness and approve all manhole exfiltration tests.

Exfiltration Test Procedure:

- Manholes shall be tested after installation and backfill with all connections in place.

- The inlet and outlet of the manhole being tested shall be sealed with watertight plugs or bulkheads, and the manhole shall be filled with water until the elevation of the water is within 4 inches from the base of the cone.  Prior to test allow manhole to soak for a minimum of 4 hours to maximum of 72 hours.  After soak period, adjust water level inside manhole to within 4 inches from the base of the cone.

- Prior to starting test, measure and record water level from the top of the manhole frame; at the end of 4 hour test period, measure and record water level from the top of the manhole frame; compute the drop in water level during the test period.

- The maximum allowable drop in vertical water height in the manhole shall be ¼ inch for all diameter sizes of manholes.

- If the water level in the manhole drops below the allowable drop amount, Contractor shall repair leak and retest until results meet criteria; repair visible leaks regardless of quantity of leakage.

604-5.01 BASIS OF PAYMENT.  Delete Pay Item 604(2) Sanitary Sewer Manhole.  Refer to Special Provision Section 626 for Sanitary Sewer Manhole materials, construction and payment.

Add the following:

The contract price for Storm Sewer Manhole, Type II includes furnishing and installing of end cap orifice assembly as shown on the plans.

Manhole Exfiltration Testing is subsidiary.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

604(1A)	Storm Sewer Manhole, Type I	Each

604(1B)	Storm Sewer Manhole, Type II	Each

604(5A)	Inlet, Type A	Each

604(5C)	Inlet, Type C	Each

604(5D)	Inlet, Type D	Each

CFHWY00317

Special Provisions

Replace Section 606 with the following:

SECTION 606
GUARDRAIL

606-1.01 DESCRIPTION. Construct new guardrail, terminal sections, and transition rail of the kind and type specified.

Remove and reconstruct or remove and dispose of existing guardrail, terminal sections, and transition rail.

CR606-020118_SSHC2015.17/CFHWY00317

Install batter board when constructing new guardrail at locations specified in the plans.

CFHWY00317

Construct all new permanent crash cushions to shield the hazard width and travel direction shown in the plans.

606-1.02 SUBMITTALS.  Submit the following for permanent crash cushions:

1.	A letter from the Manufacturer or their approved representative with the name of their representative, certification of their installation contractor, and their recommendations for the crash cushions shown on the plans, including product information, foundations, and rigid backup or transition connection type.

2.	A copy of the manufacturer's installation requirements and recommendations. Provide detailed assembly instructions and shop drawings for the crash cushion, foundation, and rigid backup anchorage, or transition connection before beginning installation.

3.	FHWA Acceptance Letters(s) for the crash cushion submitted to support either AASHTO Manual for Assessing Safety Hardware (MASH) Test Level 3 or NCHRP 350 Test Level 3. Acceptance must include the shielding typical hazard widths and travel directions shown in the plans.

4.	AASHTO listing or written updates for the crash cushion classification as listed in the 2011 AASHTO Roadside Design Guide, Section 8.4.

5.	Manufacturer Certified Installers:  Submit the installer certification to the Engineer at the Preconstruction Conference.

CR606.10-122217_SSHC2015.17/CFHWY00317

606-2.01 MATERIALS. Use materials that conform to the following:

Concrete	Section 501, Class A

Flexible Delineator Posts	Subsection 730-2.05

Guardrail Connection Plate	Section 722

Guardrail Hardware	Subsection 710-2.07

Guardrail Posts and Blockouts	Subsection 710-2.06

High Strength Bolts	Section 722

Metal Beam Rail	Subsection 710-2.04

Terminals	Subsection 710-2.11

Terminal Markers	Subsection 730-2.05

Wire Cable	Subsection 709-2.02

Batter Board	Subsection 710-2.12

Preservatives for Timber	Subsection 714-2.01

Fabricate side-mounted guardrail reflector assembly brackets from aluminum alloy.

Use retroreflective sheeting for terminal markers, post-mounted flexible delineators, and side-mounted guardrail reflectors meeting ASTM D4956 requirements for Type VIII, IX or XI.

CR606_SSHC2015.17/CFHWY00317

Crash Cushion.

Generally accepted crash cushion classifications are in the 2011 AASHTO Roadside Design Guide, 4th Edition.  The Engineer will determine the final classification of each materials submittal.  Each crash cushion in the plans specified as one of the following:

1.	Sacrificial:  Demonstrated designed for a single impact.  They may be "narrow" crash cushions or "median barrier" crash cushions as defined by the FHWA Office of Safety.

2.	Reusable Crash Cushion.  Demonstrated to have major components survive most impacts intact and salvageable.  Some components require replacement after a crash.

3.	Low-maintenance and Self-restoring Crash Cushion. Demonstrated to suffer very little, if any damage, upon impact and easily pulled back into their full operating condition.  They may partially rebound after an impact and may only need an inspection to ensure that no parts have been damaged or misaligned.  Supply crash cushions that are redirective and non-gating.

Crash Cushion – Install an added Terminal Marker or other flexible delineator to the front of the crash cushions as recommended by the Manufacturer.

CR606.10-122217_SSHC2015.17/CFHWY00317

CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL. Install guardrail and terminals at the locations shown on the Plans. Conform with the Standard Drawings and these Specifications.

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals, that are required to completely install a segment of guardrail before beginning work on that segment.

Start guardrail installation at the "upstream" end (the end adjacent traffic encounters first) by either installing a crashworthy terminal, connecting to an existing barrier or shielding the end with a truck mounted attenuator (TMA) meeting NCHRP 350, Test Level 3.  Continue installation in the direction of traffic.  Exception:  if the guardrail run connects to existing barrier, buried in the backslope, or guardrail, existing or new bridge railing, or other existing structure at the "downstream" end, guardrail installation may start at the point of connection.  The exception allows for starting at the downstream end. A temporary crash cushion or TMA is required at all incomplete upstream guardrail ends within the construction clear zone before leaving them unattended for more than 10 days.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail. At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test level 3 at all non-crashworthy guardrail ends within the construction clear zone. Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

When possible, proceed with construction of guardrails with the direction of traffic.

Where necessary, adjust the height of existing guardrail to provide a smooth transition to new guardrail. Use 25 linear feet of guardrail or two 12’ 6” pieces of guardrail to transition to match the existing or new guardrail elements and/or end treatments.

After shaping the slopes and staking proposed guardrail terminal section locations, request the Engineer to field verify their locations. Receive approval of the staked locations before installing terminal sections.

Treat field cuts to timber posts and blockouts according to AWPA standard M 4.

Install blockouts according to manufacturer’s recommendations and as shown on the plans.

Install side-mounted guardrail reflectors and post-mounted flexible delineators as follows:

1.	At intervals noted on the plans or Standard Drawings, starting with the first guardrail post beyond terminal sections

2.	With the retroreflective sheeting facing approaching traffic

3.	With retroreflective sheeting on both sides, on two-way roadways

4.	Not on the terminal sections, except as shown on the plans

5.	At or below 500 feet in elevation, except as noted otherwise in the Plans.

Attach terminal markers, in a vertical position, to the P.T. post of Short Radius Guardrail sections and to the post where the flare begins for parallel guardrail terminals.  Coordinate terminal marker locations with the Engineer.

At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

CR606-020118_SSHC2015.17/CFHWY00317

606-3.02 POSTS. Set posts to accommodate the line, grade, and curvature shown on the Plans.

Use either wood or steel posts when allowed by the type of guardrail specified, subject to the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

Set posts as follows:

1.	Set posts plumb, in the location and to the depth shown on the Plans or Standard Drawings.

2.	Choose an installation method that does not damage the post, adjacent pavement, structures, utility conduits, and final slopes. Repair all damage to the satisfaction of the Engineer, or replace the damaged item, as per subsection 105-1.11.

3.	Set wood or steel posts in dug, drilled, or pre-punched holes. Steel posts may also be set by ramming or driving if:

a.	The underlying material is no larger than six inch; and

b.	The posts are not damaged during installation.

4.	Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically. Compact under and around posts to the Engineer’s satisfaction.

5.	For placement in solid rock or broken rock embankment greater than six inch, set wood or steel posts in pre-dug, pre-drilled, or pre-punched holes.

6.	In new roads, install posts before final shoulder or median compaction, surfacing, and paving.

606-3.03 BEAM RAIL. Fabricate metal work in the fabricator’s shop. Bend curved guardrail elements with radii less than or equal to 100 feet in the fabricator’s shop or with an approved bending apparatus.

Receive approval before field punching, cutting, or welding. Repair damaged spelter coat areas on galvanized rail elements according to AASHTO M 36.

Lap rail elements so that the exposed ends face away from approaching traffic in the adjacent lane.

Use bolts long enough to extend at least 1/4 inch beyond the nuts. Except where required for adjustments, do not extend bolts more than 1 inch beyond the nuts.

Locate bolts at expansion joints at the center of the slotted holes.

Tighten bolts at expansion joints to snug-tight. Make all other bolts fully-tight.

606-3.04 CABLE RAIL. Install cable guardrail according to the Plans and Specifications. Install at the locations shown on the Plans.

606-3.05 TERMINAL SECTIONS. Install terminal sections according to the manufacturer’s recommendations. Install where shown on the Plans.

1.	Parallel Terminals. Install terminal sections according to the manufacturer’s recommendations for the entire length of the terminal then, if required, transition rail height over 25’ to match guardrail height and splice location. Install where shown on the Plans.

Install ASTM D4956 Type III, IV, or V retroreflective sheeting on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal according to guidance for Object Markers for Obstructions Adjacent to the Roadway in Chapter 2C of the ATM.

2.	Buried-in-Backslope Terminals. Install buried-in-backslope terminals where shown on the plans.  If required, transition rail height over 25’ to match guardrail height and splice location.

Attach flexible markers, in a vertical position, to the terminal end directly to the backside of the rail face, the face away from the traveled way, or the first post of each parallel guardrail terminal.  Attach flexible markers to the "P.T." post of the buried-in-backslope Terminals.  Provide an additional marker where the flare begins for guardrail terminal widening.  Provide two markers at the end of each run of guardrail; coordinate the locations with the Engineer.

The connection shall not negatively influence the performance of the guardrail as noted in 606-2.01.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Remove and reconstruct guardrail as specified. Replace lost or damaged materials without extra compensation.

When replacing existing guardrail complete the replacement run installed within 14 calendar days after removal.

For guardrail located within 50 feet of bridge ends, remove and replace the existing guardrail in the same work shift.

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL. Remove the existing guardrail shown on the Plans, including the rail, cable elements, terminal sections, hardware, posts, concrete bases, and steel tubes. Backfill resulting holes with material in 6-inch layers that is similar to the existing embankment and compact to the same approximate density.

Guardrail.

Notify the Engineer a minimum of 5 days before removing guardrail.  The Engineer will notify the ADOT & PF, M & O, and have an M & O representative designate portions of guardrail for salvage.  Deliver salvaged guardrail and associated hardware to the M & O station located at E. Inner Springer Loop, Palmer.  Remaining items removed become the Contractor's property.

CR606-020118_SSHC2015.17/CFHWY00317

CR606.10_SSHC2015.17/CFHWY00317

606-3.08 ADJUST EXISTING GUARDRAIL. When called for on the Plans, reset existing guardrail to the height shown on the applicable Standard Drawing, measured from the top of the rail to the finished shoulder surface below the rail. Raise and lower the posts several times to prevent settlement and then re-drive them to the height shown on the Plans. Use other methods if approved.

606-3.09 INSTALL NEW GUARDRAIL. Install guardrail as shown on the applicable Standard Drawings, measured from the top of the rail to the finished shoulder surface below the rail.

Install MASH Test Level 3-compliant W31 guardrail as shown on the plans.  Install new guardrail in conformance with tolerances shown on the plans.

606-3.10 TERMINAL MARKERS. For each parallel rail terminal, attach a terminal marker to the extreme piece of rail.  Attach the flexible markers using hardware and attachment methods recommended by the manufacturer.

606-3.11 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  When the Engineer determines additional guardrail is required, complete the installation immediately.

CR606-020118_SSHC2015.17/CFHWY00317

606-3.12 BATTER BOARDS.  Install batter board flush with bottom of asphalt pavement, at the base of the guardrail posts, and fastened to the posts as shown on the Plans.  Prior to constructing asphalt pavement, coat the roadside face of the batter boards with STE-1 asphalt cement.

CFHWY00317

606-3.13 CRASH CUSHION.  Install crash cushions according to the manufacturer's recommendations.

Manufacturer's Representative.  Provide the services of a manufacturer's representative to review both the initial planned installation and the final installation onsite.  Pre-installation inspection and observation of the installation onsite by the manufacturer's representative is required.  Cooperate with the Manufacturer's Representative and the Engineer and place the materials according to these specifications and the manufacturer's recommended procedures.

Manufacturer Certified Installers.  Install crash cushions using installers certified by the materials manufacturer.  Install Crash cushions as follows:

1.	Parallel to the approach traveled way or as shown on the plans.

2.	Follow Section 203 for the excavation and embankment requirements of the concrete base component of the crash cushion.

3.	Follow Section 501 for a concrete pad, sized according to the manufacturer's recommendations, constructed on a minimum of 12 inches of Selected Material, Type B.

4.	Cut or fill to the top of the concrete pad with Selected Material, Type B at 12:1 or shallower on installations in grass median.

5.	Install top elevation of concrete pad flush to pavement edge when adjacent to or within asphalt pavement.

6.	Bolt crash cushion to median barrier with manufacturer approved barrier to crash cushion connector when attached to median barrier.

7.	Install a terminal marker or other flexible delineator on the nose of each crash cushion as recommended by the manufacturer.  The terminal marker is in addition to, not a substitute for, the retroreflective delineation installed on the crash cushion nose.

Excess excavated material is the property of the Contractor.

Provide permanent crash cushions with performance features designed to minimize the impacts of snow and ice buildup due to frequent freeze and thaw cycles.  Crash cushions using supports that interlock and travel within fixed tracks at or below the first six inches from ground level, are not acceptable for permanent winter use.  Provide crash cushion covers, when available from the manufacturer.

CR606.10-122217_SSHC2015.17/CFHWY00317

606-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

1.	Guardrail. Measured along the face of the rail or cable, from the center of the end posts.

Short Radius Guardrail. Per each, installed in place.

When the guardrail is connected to a terminal section, the pay limit for the rail ends where the specified terminal section begins.

2.	Terminals. (Bridge Rail Thrie Beam Transition or Bridge Rail W-Beam Transition). Per each, installed in place.

3.	Transition Rail. Per each accepted connection.

CR606-020118_SSHC2015.17/CFHWY00317

4.	Permanent Crash Cushion.  Each installed and accepted.

CR606.10-122217_SSHC2015.17/CFHWY00317

606-5.01 BASIS OF PAYMENT.

Payment for temporary crash cushions or TMA installed to protect motorists from guardrail installations not been completed within 10 calendar days of beginning installation, is subsidiary to other items.

CR606-020118_SSHC2015.17/CFHWY00317

1.	Guardrail. Side-mounted guardrail reflectors, post-mounted flexible delineators, terminal markers, batter board, guardrail beam, posts, blockouts, and associated hardware are subsidiary.  Installation of downstream anchors, transitions for rail height and splice locations, long span guardrail sections, and guardrail stiffening sections are subsidiary to guardrail installation.

CR606_SSHC2015.17/CFHWY00317

2.	Short radius guardrail sections. The contract price includes all materials from the terminal anchor to and including the first wood or steel post of standard guardrail or guardrail end terminal, and including the terminal anchor assembly, in-line anchor, terminal posts, short radius guardrail posts, rail elements, terminal markers, and associated hardware required for a complete installation.

3.	Terminal Sections.

a.	Parallel Guardrail Terminal. The contract price includes rail elements, posts, blockouts, pipe sleeves, cable assemblies, guardrail extruders, terminal markers, and all associated hardware required for a complete installation.

b.	Buried in Backslope Guardrail Terminal. The contract price includes rail elements, posts, blockouts, concrete, rebar, anchors, and all associated hardware required for a complete installation.

4.	Transition Rail. The contract price includes all brackets, beam sections, transition pieces, and all posts and associated hardware required for a complete connection of the guardrail section to a bridge rail or barrier.

All material required for embankment widening for guardrail and terminal sections is paid for under the appropriate pay items shown in the bid schedule.

Guardrail salvage is subsidiary to Pay Item 606(6) Removing and Disposing of Guardrail.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

606(1)	W-Beam Guardrail	Linear Foot

606(2)	Thrie Beam Guardrail	Linear Foot

606(3)	Box Beam Guardrail	Linear Foot

606(4)	Cable Guardrail	Linear Foot

606(5)	Removing and Reconstructing Guardrail	Linear Foot

606(6)	Removing and Disposing of Guardrail	Linear Foot

606(7)	Raising Existing Guardrail (retired)	Linear Foot

606(8)	Double-faced, W-Beam Guardrail	Linear Foot

606(9)	Short Radius Guardrail	Each

606(10)	Slotted Rail Terminal (SRT-350) (Retired) 	Each

606(11)	Extruder Terminal (ET-2000) (Retired)	Each

606(12)	Guardrail/Bridge Rail Connection (Retired)	Each

606(13)	Parallel Guardrail Terminal	Each

606(14)	Buried in Backslope Guardrail Terminal	Each

606(15)	Adjust Existing Guardrail	Linear Foot

606(16)	Transition Rail	Each

CR606-020118_SSHC2015.17/CFHWY00317

5.	Permanent Crash Cushion.  The contract price includes all work and materials required to install each permanent crash cushion, foundations, and connections along with the manufacturer's field support, recommendations, and shop drawings.  Removal and salvage of existing crash cushions is subsidiary to Pay Item 606(18) Pay Item(s).

Pay Item No.	Pay Item	Pay Unit

606(18)	Low Maintenance and Self-Restoring Permanent Crash Cushion	Each

CR606.10-122217_SSHC2015.17/CFHWY00317

SECTION 607
FENCES

Special Provisions

607-1.01 DESCRIPTION. Add the following: Split rail fence consists of wood rails, posts, Selected Material Type A, and all fittings and hardware.

Concrete pilaster consists of concrete formwork, Selected Material Type A, concrete, and aesthetic fascia.

607-2.01 MATERIALS. Add the following:

Pilaster Concrete 	Section 550, Class B

Wood				Subsection 710-2.13

607-4.01 METHOD OF MEASUREMENT. Add the following:

Split Rail Fence. Measured at the height of the lowest rail parallel to the ground. Selected Material Type A is subsidiary and will not be measured separately.

Pilaster. Each complete unit installed in place. Selected Material Type A is subsidiary and will not be measured separately.

607-5.01 BASIS OF PAYMENT.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

607(7)	Split Rail Fence	Linear Foot

607(8)	Pilaster	Each

CFHWY00317

SECTION 608

SIDEWALKS

Special Provisions

608-1.01 DESCRIPTION.  Add the following:

Construct asphalt (HMA) pathways and medians.

CR608.1-022015

608-2.01 MATERIALS.

1.	Concrete Sidewalk

CR608.2-102015/CFHWY00317

Add the following before:  "Concrete		 Section 550, Class B"

Concrete	Section 501, Class P

CR608.2/CFHWY00317

Add the following after:  "Concrete, Class B"

Acid Wash	Muriatic or Phosphoric

Admixtures	AASHTO M 194 Chemical Admixtures†

ASTM C 494 Standard Specification for Chemical Admixtures for Concrete†

Curing Agents	ASTM C 309, Liquid Membrane-Forming Compounds for Curing Concrete †

Expansion Joints	AASHTO M-33 Preformed Expansion Joint Filler for Concrete (Bituminous Type)

Integral Color Agent	ASTM C 979 Standard Specification for Pigments for Integrally Colored Concrete

Reinforcing Steel	Section 503

†	Compatible with colorant manufacturer.

Provide concrete for slabs according to Section 550, ACI 303R, 303.1, this specification and the material manufacturer's and supplier's written instructions.

Maximum slump 4," except "8 maximum if using super plasticizers or mid-range water reducers. Mix used for sample(s) shall be the same as the production mix(s).

Concrete - Exposed Aggregate Finish:  provide aggregate from a single source.  Keep aggregate for exposed aggregate finish separate from other project aggregate.

Concrete - Colored:  color concrete using an integral color, with a surface hardener, a color cure, a release agent, and a sealer compatible with colorant(s).

Concrete - Pattern Imprinted:  Use a manufactured system that is designed to provide the pattern specified and a release agent compatible with the colorant.

CR608.2-102015/CFHWY00317

Delete paragraph number 2 and substitute the following:

2.	Asphalt (HMA)

Asphalt Binder, PG 52-28	Subsection 702-2.01

Aggregate, Type II or III	Subsection 703-2.04

Mix Design Requirements (ATM 417)

Marshall Stability, pounds, min.	1000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

CR608.1-022015

Add the following to paragraph number 2:

Coating/Paint:

Material - Methyl Methacrylate (MMA)	Subsection 712-2.17 (MMA only)

Color	Federal Standard 595, color 30111 (Brick Red)

Add the following Subsections 2.02 and 2.03:

608-2.02 REFERENCES.

1.	ACI 303		Cast-In-Place Architectural Concrete Practice.

2.	PCA PA124		Finishing Concrete Slabs with Color and Texture.

3.	PCA SP021		Color and Texture in Architectural Concrete.

CR608.2-102015/CFHWY00317

608-2.03 SUBMITTALS – HIGH STRENGTH, EXPOSED AGGREGATE, COLORED CONCRETE, PAINTED HMA AND PATTERN IMPRINTED CONCRETE AND HMA.  Provide complete submittals (3 printed copies, except samples as specified below), to the Engineer for review and approval, at least 21 days before beginning construction of concrete and asphalt items.  Submittals will be returned to the Contractor within 14 days from the date submitted, marked as approved by the Department, or requiring revisions.  Amend and resubmit the documents for review until approved by the Engineer.  Receive approval before beginning production.

CR608.2/CFHWY00317

Submit shop drawings, product data, specifications, certifications; manufacturers and installer's resumes, and samples as specified in Section 401, 501, 503, 608 and herein.

1.	Shop Drawings, Product Data, Specifications, and Certifications.

a.	Exposed aggregate finish:  manufacturer's chemical surface retarder.

b.	Integral concrete colorant:  manufacturer's color chart, and chipset.  Indicate color additive numbers and required dosage rates as part of the concrete mix submittal, Subsection 501-3.01.

c.	Manufacturer's concrete pattern imprinting system.

d.	Manufacturer's fabricated HMA pattern imprinting tool - shop drawings.

e.	Methyl Methacrylate for coating HMA.

f.	Other when requested by the Engineer.

2.	Resumes.

a.	Manufacturer.

Concrete.  Provide documentation for five years of successful product performance, with a minimum of five completed projects and including but not limited to:

	Manufacturer's colorant, hardener, color cure, release agent, and sealer

	Batch Plant's mixing of manufacturer's colorants and other additives, and product delivery

	Manufacturer's pattern imprinting system

HMA.  Provide documentation of two years and three projects successfully fabricating pattern imprinting tools and successful product performance applying MMA in similar applications to this Project.

b.	Installer.

Concrete and HMA.  Installer(s) with 2 years experience and 3 successfully completed projects of similar configuration and method of installation.

In addition:

1)	for projects with concrete integral colorant and or pattern imprint system, provide a minimum of one project using the proposed manufacturer's colorant and pattern imprint system.

3.	Manufacturer's.

All manufacturers, listed and other, are required to submit for review and approval.

Manufacturers of concrete colorant and pattern imprinting systems:

| Bomanite Corporation P.O. Box 599 Madera, CA 93639 Ph: 303.369.1115 Fax: 303.291.0282 Email: bomanite.com | Brickform, division of Solomon Colors, Inc. 11061 Jersey Blvd. Rancho Cucamonga, CA 91730 Ph: 800.483.9628 Email: brickform.com | Davis Colors 3700 East Olympic Blvd. Los Angeles, CA 90023 Ph: 800.356.4848 Fax: 323.269.1053 Email: daviscolors.com | L.M. Scofield Company 6533 Bandini Blvd. Los Angeles, CA 90040 Ph: 323 720.3000 Fax: 323.720.3000 Email: Scofield.com |
| --- | --- | --- | --- |

4.	Pattern Imprinting, Coloring Concrete and HMA Painting Plans.

Provide pattern imprinting, concrete coloring and HMA painting plans to the Engineer for review and approval.  Include the following, at a minimum, to achieve a final product that accurately represents, to scale, colored concrete, painted HMA and the pattern imprinted concrete and HMA (including the joints) elements:

a.	the sequence and schedule of operations,

b.	the proposed method of pattern imprinting,

c.	the method of coloring the concrete,

d.	the method of applying the MMA coating/paint to the HMA.

CR608.2-102015/CFHWY00317

5.	High Strength, Exposed aggregate, Colored Concrete and Painted HMA and Pattern Imprinted Concrete and HMA Sample(s).

CR608.2/CFHWY00317

Provide one sample, equal to the width of the item, 6 ft x 6 ft maximum, 4 ft x 4 ft minimum, of each item for review by the Engineer.  Demonstrate exposing the aggregate, the addition of colorant to the concrete, painting the HMA and pattern imprinting the concrete and HMA on each sample provided.

Receive written approval of the sample prior to beginning production work.

Retain samples of binder(s), sand(s), aggregate(s), and color additive, used in the sample for comparison with the item production materials.  Keep sample through completion of related work for use as a quality standard for finished work.  Keep the sample through Project completion when requested by the Engineer.

608-3.01 CONSTRUCTION.  Add the following:

CR608.2-102015/CFHWY00317

High Strength, Exposed Aggregate, Colored Concrete and Painted HMA and Pattern Imprinted Concrete and HMA.

CR608.2/CFHWY00317

Match the Project work to the approved sample.  Significant differences in appearance (texture, color, pattern, or other) between adjacent panels/sections of work, from the approved sample including adjacent panels/sections similar to the approved sample yet significantly different to each other, as judged by the Engineer, will result in removal and replacement of the deficient panel(s)/section(s) of work.

Take all precautions to avoid damaging new and existing, concrete and asphalt.

Prevent surrounding materials from being discolored by the concrete and HMA and the HMA MMA coating (curbs, gutters, and other).  When directed by the Engineer, in writing, remove stains and coatings on other concrete and or HMA, resulting from your work.

Where HMA paving is against; exposed aggregate finish, colored, pattern imprinted; colored and pattern imprinted concrete, place the concrete prior to asphalt paving.  Do not place the HMA pavement until the concrete has cured sufficiently to prevent damage from the paving operation.

Acceptance of corrective work requires the Engineer's written approval.  Repair all new and existing damaged concrete and HMA, including the removal of surface contaminants, to the satisfaction of the Engineer.  The Engineer will not provide written approval until all damaged concrete and HMA is repaired.

CR608.2-102015/CFHWY00317

- Slab Types.

| Slab Type Requirementsa, b. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Typec. | Description | Finishd, e, f. j | Added Colorg. | Added Patterng. | th. Inches | Reinforcingi. (bar spacing each way) | Concrete Class |
| a. & b. | Typical | Broom |  |  | 4, 6 |  | B |
| I | Broom | Broom |  |  | 4 | 4x4  W2.9xW2.9 | B |
|  |  |  |  |  | 6 | #5@12" O.C. |  |
|  |  |  |  |  | 8 | #6@12" O.C. |  |
| II | Exposed Aggregate | Aggregate |  |  | 4 | 4x4  W2.9xW2.9 | B |
|  |  |  |  |  | 6 | #5@12" O.C. |  |
| III | Colored | Broom |  |  | 4 | 4x4  W2.9xW2.9 | B |
|  |  |  |  |  | 6 | #5@12" O.C. |  |
| IV | Pattern Imprinted | Coordinate |  |  | 4 | 4x4  W2.9xW2.9 | B |
|  |  |  |  |  | 6 | #5@12" O.C. |  |
| V | Colored & Pattern Imprinted | Coordinate | 5092, Sage Solomon Colors | 6” X 6” Granite Setts Single Bomanite | 4 | 4x4  W2.9xW2.9 | B |
|  |  |  |  |  | 6 | #5@12" O.C. |  |
| VI | High Strength | Float |  |  | 4 | #5@12" O.C | P |
|  |  | Broom |  |  | 8 | #5@12" O.C |  |
| a. Sealer and Hardener: provide for all slabs. b. Transition the slab at approaches as shown in the plans. c. Type a. & b.; Pay Items 608(1a) and 608(1b), are the "Typical" concrete sidewalk. d. Broom: provide a medium broom finish. e. Aggregate: provide a uniform color slightly darker than the typical uncolored slab with a uniform reveal according to ACI 303.1. f. Coordinate: coordinate and provide finish as required by pattern imprint system manufacturer. g. Color and Pattern: provide color and or pattern similar to that noted and available from the listed manufacturer(s). Provide color and pattern from the same manufacturer or provide from different manufacturers with a certification from each permitting warranted use of their product with the product of the other manufacturer. Use a release agent as approved by the manufacturer(s). h. t: provide the slab thickness, denoted as "t." i. Reinforcing: Provide welded wire fabric in sheets not rolls. Lap joints 1 1/2 mesh minimum. j. Float. provide a uniform surface as shown in the plans |  |  |  |  |  |  |  |

CFHWY00317

2.	Joints.

Lay out joints as shown or noted in the Plans and Specifications, if not shown or noted provide:

a.	Control Joints.  Maximum spacing equals 12 ft.  (also referred to as, "dummy joints")

(1)	the joint configuration should create a square or rectangle with the long side no more than 1.5 times the short side,

(2)	space the control joint matching the width of the slab,

(3)	at corners and intersections, align the joints parallel to the edge(s) of the intersecting slab.

(4)	locate the joints equally spaced between the:  ends/edges of slab, slab corners, slab intersections or a combination of one and another.

b.	Expansion Joints.  Maximum spacing equals 36 ft.

Touch up pattern and finish edges with hand tools immediately after placing concrete and as directed by the manufacturer(s) and Engineer.

Add the following Subsection 608-3.05:

608-3.05 ASPHALT PATHWAYS AND MEDIANS.  Construct pathways and medians according to Subsection 608-3.02, Asphalt Sidewalks.

CR608.1-022015

Add the following Subsections 608-3.06 and 608-3.07:

608-3.06 RESERVED.

608-3.07 ASPHALT – PATTERN IMPRINTED AND PAINTED.  Construct pattern imprinted and painted HMA according to Subsection 608-3.02 Asphalt Sidewalks and as noted herein.

1.	Pattern.  Fabricate the imprint tool pattern to match standard brick dimensions in a running bond configuration with a slightly wider joint/indent spaced similar to the concrete expansion Joint.

2.	Painting.  Prepare the asphalt surface and apply the coating/paint according to the MMA manufacturer's instructions. Apply coating (MMA) completely covering the asphalt surface including pattern imprint.  Do not fill the pattern indentation, with MMA, flush with the top surface.  Leave a 1/8", smooth, concave painted/coated surface between bricks (joint).

CR608.2-102015/ CFHWY00317

608-4.01 METHOD OF MEASUREMENT.  Add the following:

Asphalt Pathways, and Medians are measured by the ton of HMA.

Additional HMA used for matching existing surfaces, such as paved parking lots behind a new sidewalk/pathway, will be included in the measurement of the related asphalt Pay Item.

CR608.1-022015

Add the following:

Concrete Slabs: By area of finished surface, including detectable warning tiles.

CR608.2/CFHWY00317

608-5.01 BASIS OF PAYMENT.  Add the following:

Asphalt binder is subsidiary to related HMA Pay Items.

Embankment and bed course materials will be furnished, placed, and paid under Sections 203 and 301, respectively.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

608(7)	Asphalt Pathway	Ton

608(8)	Asphalt Medians	Ton

CR608.1-022015

Add the following:

Reinforcing, samples, and corrective work are subsidiary to related Pay Items.

Pay Item No.	Pay Item	Pay Unit

608(13A4)	Concrete (Slabs), Type I, 4 inches thick, Broom Finish	Square Yard

608(13A6)	Concrete (Slabs), Type I, 6 inches thick, Broom Finish	Square Yard

608(13E)	Concrete (Slabs), Type V, 6 inches thick, Colored and Pattern Imprinted	Square Yard

608(13F4)	Concrete (Slabs), Type VI, 4 inches thick, Float Finish	Square Yard

608(13F8)	Concrete (Slabs), Type VI, 8 inches thick, Broom Finish	Square Yard

CR608.2/CFHWY00317

Special Provisions

Replace Section 610 with the following:

SECTION 610
DITCH LINING

610-1.01 DESCRIPTION. Construct ditch lining at the locations on the Plans or as staked.

610-2.01. MATERIALS. Use crushed stones that are angular, hard, sound, and durable with at least one face resulting from fracture.

1.	Angular—stones, the particles of which possess well-defined edges formed at the intersection of roughly planar faces.

2.	Hardness—resistance of a material to indentation or scratching. AASHTO T96, not more than 50% wear at 500 revolutions.

3.	Soundness—measure of aggregates durability when exposed to the elements, AASHTO T104.

4.	Gradation—ATM 304:

a.	maximum of 6 inches in greatest dimension

b.	not more than 50% by weight passing a 3-inch sieve,

c.	not more than 5% passing a 1-inch sieve

5.	Breadth and Width—at least 1/3 of the length

610-3.01 CONSTRUCTION REQUIREMENTS. Place and spread ditch lining materials so that the finished face is uniform. 	Place stones on slopes 1.5:1 and flatter.

610-4.01 METHOD OF MEASUREMENT. Section 109.

610-5.01 BASIS OF PAYMENT. Excavation required below normal ditch grade is subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

610(1)	Ditch Lining	Cubic Yard

610(2)	Ditch Lining	Ton

610(3)	Ditch Lining	Station

CR610-060117

SECTION 611
RIPRAP

Special Provision

611-2.01 MATERIALS.  In the 1st paragraph add the following after the first sentence:

Apparent specific gravity will be determined by ATM 308.

In the 1st paragraph replace "2:1." with "3:1."

CR611.1-102015

Special Provisions

Replace section 615 with the following:

SECTION 615
STANDARD SIGNS

615-1.01 DESCRIPTION. Furnish and install standard signs and delineators. Remove and relocate or remove and dispose of existing signs and markers, as specified.

615-2.01 MATERIALS. Use materials that conform to the following Subsections:

Sheet Aluminum 		730-2.01

High Density Overlaid Plywood		730-2.02

Retroreflective Sheeting, ASTM D4956 		730-2.03

Sign Posts		730-2.04

Delineator Posts		730-2.05

Acrylic Prismatic Reflectors		730-2.06

1.	Shop Drawings. Submit shop drawings, for all signs that must meet the ASDS letter width and spacing charts, for approval before fabrication. Submit 4 sets of collated shop drawings prepared according to Subsection 105-1.02. Show the following on each sign drawing:

a.	Dimensions of all horizontal and vertical characters and spaces

b.	Overall dimensions

c.	Sign material and sheeting material type

d.	Panel thickness

e.	Legend and letter series

f.	Whether the sign will be framed

2.	Sign Fabrication. Use ASTM D4956 Type IV retroreflective sheeting (for lettering, symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

(1)	For temporary installations, the reflective sheeting place on aluminum, plastic, or plywood sheet panels.

(2)	For flexible signs, (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports: Use white ASTM D4956 Type VIII or Type IX retroreflective sheeting for background of sign and all strips.

c.	Non-Illuminated Overhead Signs with White Legends on Green Backgrounds: Use ASTM D4956 Type IX retroreflective sheeting for legends and background. Create the legend in one of the following ways:

(1)	Cut border and legend from white ASTM D4956 Type IX retroreflective sheeting and adhere them to a green ASTM D4956 Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white ASTM D4956 Type IX retroreflective background.

d.	Fluorescent Yellow-Green School Area Signs: Use ASTM D4956 Type VIII or Type IX retroreflective sheeting for background.

Use a manufacturer-recommended clear coat on all screened signs.

Use sign layouts (including characters, symbols, corner radii, and borders) that conform to the ASDS.

3.	Sign Posts and Bases. Use sign posts and bases of the types specified. The structural aspects of design and materials for sign supports must comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals. Do not splice sign posts.

Use Class A concrete for steel-reinforced slip base and breakaway base foundations meeting the requirements of Section 501. Concrete for other sign foundations may be Class W.

4.	Delineators. Use delineator assemblies that conform to the requirements shown on the Plans. Fabricate flexible delineators using ASTM 4956 Type III, IV, or V Retroreflective Sheeting.

5.	Reflective Sheeting Warranty. Supply manufacturer’s warranty for reflective sheeting, including retention of fluorescent yellow-green (measured in accordance with ASTM E2301) for ten years according to the following criteria:

a.	Minimum Fluorescent Luminance Factor	YF: 20%

b.	Minimum Total Luminance Factor	YT: 35%

The warranty shall stipulate that: If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness. If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

615-3.01 CONSTRUCTION REQUIREMENTS.

1.	Place wooden posts in excavated holes to the depth shown on the Standard Drawings.

2.	Backfill the space around the posts in the holes to finish ground with selected earth or sand, free of rocks or deleterious material. Place backfill in layers approximately 6 to 12 inches thick and thoroughly compact it.

3.	Dispose of surplus excavated material neatly along the adjacent roadway as directed.

4.	Install flexible delineator posts according to the manufacturer's recommendations.

5.	Attach sign panels to posts, electroliers, traffic signal standards, bridge rails, piers, and abutments using the types and sizes of fastening hardware shown on the Plans.

6.	If using existing signs and mileposts that are removed and relocated, ensure they conform to the details shown on the Plans or as directed.

7.	Sign Salvage:

Notify the Engineer 5 working days prior to beginning sign salvage activities. The Engineer will physically identify those signs to salvage.

a.	Property of the State.  When 615-3.01 7a identifies a maintenance station to receive sign salvage, the signs (sign panels, posts, and hardware) are the property of the State.

Protect all items from damage during salvaging and delivery. For each sign so designated, disconnect sign post from panel and group the panels together. Group posts together with their hardware. Deliver sign panels, posts, and hardware to the State Maintenance Station noted in these Special Provisions. Do not deliver salvaged materials until inspected and approved by the Engineer. Replace any items damaged by you at no additional cost to the Department.

Deliver salvaged sign panels, posts, and hardware to the State Maintenance and Operations Station, located at:

E. Inner Springer Loop, Palmer.

b.	Property of the Contractor. When 615-3.01 7a does not identify a State Maintenance and Operations Station; the signs salvaged (sign panels, posts, and hardware) are the property of the Contractor.

Remove project signs and/or parts designated for salvage, off the project site.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise). If abandoned in place, remove the tops of the foundations, reinforcing steel, anchor bolts, and conduits to a depth of not less than 12 inches below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation considered as one unit.

Dispose of sign salvage not wanted by the Contractor, not used in the project, and not accepted by the Local Maintenance and Operations Station as required by Federal, State, and Municipal environmental regulations.

8.	All materials and finished signs are subject to inspection and acceptance in place.

a.	Surfaces exposed to weathering must be free of defects in the coating that impair serviceability or detract from general appearance or color match.

b.	Finished signs must be clean and have no chatter marks, burrs, sharp edges, loose rivets, delaminated reflective sheeting, or aluminum marks. Do not make repairs to the face sheet.

9.	Install the various breakaway assemblies according to the manufacturer’s written instructions.

10.	Secure the anchors in templates and install them according to the manufacturer’s written instructions.

11.	Finish the foundation according to these tolerances:

a.	Do not use more than two shims per coupling.

b.	Do not use more than three shims to plumb each post.

12.	Remove and replace all foundations requiring more than three shims to plumb a post without extra compensation.

13.	Construct the top of any foundation located on a slope so that the finished slope passes through the top center of the foundation. Grade the area 24 inches up and down slope of the foundation edge so that no portion of the foundation projects above the surrounding slope and water will drain away from the foundation.

14.	Attach a label to the back of all standard signs in the lower right corner. Make the label at least 15 square inches and show the year the sign was purchased from the manufacturer. Show the last two digits of the year in clear and bold numbers. Make the label from ASTM D4956 Type I or brighter retroreflective sheeting. Use background and legend colors meeting Table 615-1.

TABLE 615-1

DECAL COLORS

| YEAR | BACKGROUND COLOR | LEGEND COLOR |
| --- | --- | --- |
| XXX1 | Yellow | Black |
| XXX2 | Red | White |
| XXX3 | Blue | White |
| XXX4 | Green | White |
| XXX5 | Brown | White |
| XXX6 | Orange | Black |
| XXX7 | Black | White |
| XXX8 | White | Black |
| XXX9 | Purple | White |
| XXX0 | Strong Yellow-Green | Black |
| Central values and tolerance limits for each color, as referenced in the MUTCD, are available from the Federal Highway Administration, (HHS-30), 400 7th St. SW, Washington, D.C. 20590 |  |  |

615-3.02 SIGN PLACEMENT AND INSTALLATION. The location and type of installation will be as shown on the Plans. Sign locations are approximate and subject to field adjustment by the Engineer.

Do not allow the top of the embedded steel tube to extend more than 2 inches above the surrounding ground and concrete foundation.

On all signs, install 2-inch diameter wind washers, colored to match the sign face, between the fastener head and the sign. Use rust-resistant washers fabricated from a material equal in strength to the sign blank.

Mount signs on mast arms level.

Bring existing signs that are to remain, into conformance with Standard Drawing S-05. Keep existing signs in service until they are no longer needed.

615-4.01 METHOD OF MEASUREMENT.

Standard Signs and Object Markers. By the total area of legend-bearing sign panel erected in place. No deductions in quantity for corner rounding will be made. Nominal dimensions for sign sizes indicated on the Plans will be used to calculate sign pay quantities. Octagons and round signs will be measured as rectangles. Only one side of each double-faced sign will be measured for payment.

Removal and Relocation. By each, complete in place.

Delineators. By each, complete in place.  A single delineator consists of one post equipped with three reflectors.

Salvage Sign. By each complete sign delivered in acceptable condition.

615-5.01 BASIS OF PAYMENT. Sign posts, bases, and mounting hardware are subsidiary.

When Items 615(2), 615(3), or 615(6) do not appear on the bid schedule, this work is subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

615(1)	Standard Sign	Square Foot

615(2)	Remove and Relocate Existing Sign	Each

615(3)	Remove and Relocate Milepost	Each

615(4)	Delineator, Rigid	Each

615(5)	Delineator, Flexible	Each

615(6)	Salvage Sign	Each

CR615-070117

SECTION 618
SEEDING

Special Provisions

618-1.01 DESCRIPTION.  Replace the 1st sentence with:  Establish a perennial stand of grass or other specified living vegetative cover, by clearing, applying soil stabilization material(s) and seeding the area(s) shown in the Plans, including new and disturbed area(s), and area(s) identified by the Engineer.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Soil Stabilization Material	Section 727 (Stabilization Material)

Topsoil	Section 726

(In this specification, topsoil is included when referencing Stabilization Material)

CR618.1-112116/CFHWY00317

618-3.01 SURFACE PREPARATION.  Replace the 1st, 2nd, 3rd and 4th paragraphs with the following:

Clear the area(s) to be seeded; make the area(s) reasonably free of ruts, holes, and humps. Clear area(s) of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the application of stabilization material, the seeding operation, growth of cover, or subsequent maintenance of the vegetative-covered areas.

Apply stabilization material after clearing is complete, refer to 618-3.02.

Mix the seed with the stabilization material before applying the material (not including topsoil), or seed the stabilization material immediately after the material is applied for the best results as recommended by the supplier/manufacturer.

Prepare the stabilization material by grooving the material in a uniform pattern that is perpendicular to the fall of the slope.  Use one or more of the following grooving methods with associated equipment before the application of seed:

CR618.2-022015

618-3.02 SEEDING SEASONS.  Replace the 1st and 3rd paragraph with the following:  Seed disturbed areas after permanent cessation of ground disturbing activities in that area, within the time period specified in the DEC Alaska Pollutant Discharge Elimination System (APDES) Construction General Permit (CGP) for Alaska, Section 4.5 Soil Stabilization, and Section 641 Erosion, Sediment, and Pollution Control.

CR618.3-092616

618-3.03 APPLICATION.  Replace the 1st and 3rd paragraphs with the following:  Seed, seeding, reseeding includes the application of seed, fertilizer and stabilization material.

Apply seed mix, fertilizer, and stabilization material at the rate specified.  If the seed mix, fertilizer and stabilization material are not included in the Plans or Specifications, including their application rates, use the recommendations of the ADNR and the Revegetation Manual for Alaska.

Add the following:

Apply seed and stabilization material in one application when using the hydraulic method.  Apply fertilizer with the hydraulic method.  Include the fertilizer with the seed and stabilization material or apply separately.

TABLE 618-1

APPLICATION RATES

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed Mix A Seed Mix B Seed Mix C | Native Fireweed White Yarrow Western Yarrow Perennial Lupine ‘Nortran’ tufted hairgrass Glaucous bluegrass Native Iris Norcoast Bering hairgrass Sourdough bluejoint wheatgrass Annual ryegrass Kenai Kentucky bluegrass Baron Kentucky bluegrass Boreal fescue | 0.50 lbs. 0.25 lbs. 0.25 lbs. 0.25 lbs. 0.50 lbs. 0.25 lbs. Total = 2.00 lbs. 0.25 lbs. 1.00 lbs. 1.25 lbs. Total = 2.50 lbs 0.25 lbs. 1.25 lbs. 1.25 lbs. 1.00 lbs. Total = 3.75 lbs |
| Slope ≤ 3:1 | Mulch | 46 lbs. |
| Slope >3:1 | Mulch with tackifier | 45-58 lbs. |
| Fertilizer | 5-5-5 | 12 lbs. |

a.	Soil Stabilizer/Stabilization Material.  Refer to Section 619 and 727 for additional soil stabilization and soil stabilization materials.

Do not remove required tags from seed bags.

CR618.1-112116/CFHWY00317

The Engineer may approve substitutions that meet design intent as stated on drawings

CR618.1/CFHWY00317

Replace Subsection 3.04 with the following:

618-3.04 MAINTENANCE.  Maintain seeded areas in a satisfactory condition for the term of the Contract, including warranty obligations.

Maintenance includes but is not limited to:

1.	Protecting seeded areas against traffic by approved warning signs or barricades and against erosion.

2.	Repairing surfaces gullied or otherwise damaged following seeding.  Fill erosion gullies 4 inches deep and greater filling the gully to surrounding grade including the portions less than 4 inches deep.  Apply and prepare the stabilization material for seeding.  Seed repaired area(s).  Refer to Subsections 618-3.01 & 3.03.

3.	Reseeding areas not showing evidence of satisfactory growth within 3 weeks of seeding and after repairs are complete.  Reseed bare patches of soil more than 10 square feet in area.  Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.

4.	Watering seeded areas for growth of vegetative cover.  If in the opinion of the Engineer, too little or too much water is being applied, adjust the amount of water as directed.

Replace Subsections 618-3.05 with the following:

618-3.05 ACCEPTANCE.  The Engineer will perform a visual inspection of the vegetative mat considering each station and each side of the road a separate area.  Acceptance of the vegetative mat requires a minimum of 70% cover density in the inspection area, gullies repaired and reseeded, and no bare patches of soil more than 10 square feet in area.

Repair/reseed areas that are not accepted.

Replace Subsection 618-3.06 with the following:

618-3.06 PERIOD OF ESTABLISHMENT.  For each area accepted, the establishment period extends one complete growing season following the date of acceptance.  Employ all possible means to preserve/maintain the new vegetative mat in a healthy and vigorous condition to ensure successful establishment.  Maintain the vegetative mat, according to Subsection 618-3.04, to not less than the requirements for acceptance, Subsection 618-3.05.

618-4.01 METHOD OF MEASUREMENT.  Add the following:

M Gal is equal to 1000 gallons.

618-5.01 BASIS OF PAYMENT.  Delete the 1st sentence:  "Mulching will be paid for under Section 619".

Delete paragraphs beginning: “Seeding by the Acre”, “Seeding by the Pound” and "Water for Seeding" and replace with:

Seeding by the Acre.  Pay Item 618(1), Seeding:  Payment is for established vegetative mat.  Stabilization material preparation (seed, fertilizer, stabilization material, and the water required for all hydraulic applications) are subsidiary.  Maintenance including:  1. Protection, 2. Repairs, 3. Reseeding, is also subsidiary.  Repairs and reseeding include, but are not limited to:  fill, stabilization material and preparation for seeding, seed, fertilizer, and the water required for hydraulic application.

Seeding by the Pound.  Pay Item 618(2), Seeding:  Payment is for established vegetative mat.  Stabilization material preparation (seed, fertilizer, stabilization material and the water required for all hydraulic applications) are subsidiary.  Maintenance including:  1. Protection, 2. Repairs, 3. Reseeding, is also subsidiary.  Repairs and reseeding include, but are not limited to:  fill, stabilization material and preparation for seeding, seed, fertilizer, and the water required for hydraulic application.

Water for Seeding.

	Water for hydraulic application is subsidiary to Pay Items 618(1) and 618(2), and includes, but is not limited to:  the initial application of seed, fertilizer, and stabilization material and the reapplication for repairs and reseeding.

	Water applied for growth of vegetative mat (Subsection 618-3.04.4 Watering), for the term of the Contract, including warranty obligations, is paid under Pay Item 618(3).

Add the following:

Stabilization materials are paid under Section 619 and 620 Pay Items, except as noted for "Seeding by the Acre", "Seeding by the Pound" and warranty obligations, Subsection 105-1.16.

CR618.2-022015/CFHWY00317

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

618(2A)	Seeding, Type A	Pound

618(2B)	Seeding, Type B	Pound

618(2C)	Seeding, Type C	Pound

CFHWY00317

Special Provision

Replace Section 619 with the following:

SECTION 619
SOIL STABILIZATION

619-1.01 DESCRIPTION.  Furnish, install, and maintain materials to stabilize the soil.  Control erosion, sediment, and pollution.

619-1.02 RELATED SECTIONS, REFERENCE ORGANIZATIONS, AND STANDARD DOCUMENTS.

1.	Alaska Department of Transportation and Public Facilities (ADOT&PF):

Standard Specifications for Highway Construction, 2017 Edition.

Seeding	Section 618

Topsoil	Section 620

Planting Trees and Shrubs	Section 621

Silt Fence	Section 633

Erosion, Sediment, and Pollution Control	Section 641

Soil Stabilization Material	Section 727

2.	American Association of State Highway and Transportation Officials (AASHTO):

Standard Practice for:

	Compost for Erosion/Sediment Control (Filter Berms and Filter Socks)	R 51

	Compost for Erosion/Sediment Control (Compost Blankets)	R 52

3.	United States Composting Council (USCC):

	Testing Methods for the Examination of Compost and Composting (TMECC)

	Seal of Testing Assurance Program (STA) documents

4.	Erosion Control Technology Council (ECTC)

	Hydraulic Erosion Control Products (HECPs) Specification Chart

Table 1, Performance Chart for Standard HECPs

	Rolled Erosion Control Products (RECPs) Specification Chart

Table 1, Rolled Erosion Control - Temporary

Table 2, Rolled Erosion Control - Permanent

5.	National Transportation Product Evaluation Program (NTPEP)

	Testing and Evaluation of Products Materials and/or Devices

6.	Texas DOT/Texas Transportation Institute (TTI) Hydraulics and Erosion Control Laboratory

619-1.03 SUBMITTALS.  Submit stabilization and erosion, sediment and pollution control performance testing results with certifications for each material, Section 619-2.01 Materials.  Submit a sample of each material to the Engineer 7 days before the scheduled installation.

1)	Test compost, all applications, no more than 90 days before installation.

2)	At a minimum, certificate will include the name of the manufacturer, product name, style number or similar, chemical composition of the material, the fibers, netting, yarn and similar and the weed free status of the material.

3)	Organic materials shall be accompanied with all applicable health certificates and permits.

4)	Furnish a Material Safety Data Sheet (MSDS) that demonstrates the product is not harmful to plants, animals, and aquatic life.

619-2.01 MATERIALS.  Select stabilization materials, individually or a combination of, matched to the project applications/conditions (sheet flow, concentrated flow, slope, length of slope, access, etc.) providing performance and functional longevity meeting the most restrictive requirements of the Construction General Permit (CGP), the approved Stormwater Pollution Prevention Plan (SWPPP) and Section 641 Erosion, Sediment and Pollution Control.

1)	Mulch	Subsection 727-2.01

	Dry Erosion Control, Stabilization Products

	Hydraulic Erosion Control Products (HECPs)

2)	Matting	Subsection 727-2.02

	Rolled Erosion Control Products (RECPs)

3)	Sediment Retention Fiber Rolls (SRFRs)	Subsection 727-2.03

	Filter Socks

	Compost Socks

	Coir Logs

4)	Compost	Subsection 727-2.04

5)	Tackifier	Subsection 727-2.05

6)	Soil Binders (Polyacrylamide (PAM))	Subsection 727-2.06

7)	Geotextile-Encased Check Dams and Sediment Barriers	Subsection 727-2.07

8)	Sandbag	Subsection 727-2.08

9)	Manufactured Inlet Protection System	Subsection 727-2.09

10)	Clear Plastic Covering	Subsection 727-2.10

11)	Staples	Subsection 727-2.11

12)	Other stabilization materials submitted to and approved by the Engineer.

Include on the packaging the manufacturer's name, the content, the air dry-weight and the guaranteed chemical analysis of the contents.  Ship and deliver to the site in the original, unopened containers.

CONSTRUCTION REQUIREMENTS

619-3.01 GENERAL.  Stabilization may include individual or a combination of materials, including but not limited to temporary seeding, mulch, tackifier, staples, matting, stabilizing emulsions, soil binders, dustless sweeping, dust palliatives, and others.

1.	Material Storage and Protection.  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment including but not limited to:

	Precipitation

	Extended ultraviolet radiant including sunlight

	Chemicals that are strong acids or other

	Flames and welding sparks

	Excess temperatures

	Other environmental conditions that may damage the materials

2.	Fabrication.

a.	Sandbags.  Sand bags shall measure 15 inches by 30 inches.  Place approximately 1.0 cubic foot of select Material, Type B, in each sandbag sack.  Close the open end of the sandbag as recommended by the fabric manufacturer.

619-3.02 SURFACE PREPARATION.  Clear all areas to be stabilized of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the stabilization operation, growth of cover (where vegetative cover is part of the stabilization operation) or subsequent maintenance of the vegetative-covered area(s).

Smooth the surface of the area(s) to be stabilized; make the areas reasonably free of ruts, holes, and humps; trackwalk if required by the manufacturer; apply the stabilization material to each area.

If specified, apply topsoil to the area to be stabilized before application of the stabilizing material.  Section 618 and 620.

619-3.03 APPLICATION.  Apply stabilization material, including rate of application, according to the specifications.  If not specified, apply according to the manufacturer's requirements.  Where manufacturer requirements conflict with the specification, except where the Engineer directs otherwise, apply the material according to the requirements of the manufacturer.

If seeding is specified, except where seed is included in the stabilization material, complete the application of stabilization materials within 24 hours after seed is placed.

Do not use vehicles or equipment which cause rutting or displacement of the subgrade or topsoil.

1.	Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Prepare surface and place seed as noted under Subsection 619-3.02 Surface Preparation and Section 618 Seeding.  Confirm application of temporary seeding with the Engineer.

2.	Tacking Agents - Tackifiers.  Apply tacking agents according to the manufacturer's installation instructions matched to the application providing functional longevity, erosion control effectiveness, and vegetative establishment.

3.	Soil Binders.  Apply soil binders according to the manufacturer's installation instructions.

a.	Using Polyacrylamide (PAM) and PAM with Short-Term Mulch:

Apply PAM on bare soils.

Apply PAM and PAM with short-term mulch only where sediment control is in place and complete.

Do not apply PAM and PAM with short-term mulch on saturated ground during rainfall.

b.	Using Moderate-Term Mulch:

Apply moderate-term mulch according to manufacturer's installation instructions.  If the curing period to achieve maximum performance is greater than the time period before precipitation is predicted, or the soil is saturated, do not apply the moderate-term mulch except as approved by the Engineer.

c.	Using Long-Term Mulch:

Apply long-term mulch according to the manufactures installation instructions.

4.	Erosion Control Blankets (ECBs).  Select blankets, as specified by the manufacturer, to match the slope; and installed according to the manufacturer's instructions rolled out on well prepared soils to assure intimate contact and anchored with staples, stakes and or anchor trenches.  Temporary erosion control blankets with 60 percent or greater open area may be installed prior to seeding.  Place blankets with less than 60 percent open area immediately after the seeding operation.

Staple matting/ECBs as recommended by the manufacturer for the application.

5.	Compost Blankets.  Construct compost blankets according to latest AASHTO R 52 and as specified.  Use coarse compost and place over bare soil a blanket of 2 inch minimum thickness, except as otherwise specified.  Apply material either by hand spreading and or pneumatically.  Compost will have no free water visible or produce dust when handled.  Place compost before seeding or mix seed with compost.

6.	Check Dams.  Place check dams as soon as possible and practicable or when and where if directed by the Engineer.  Place the check dams perpendicular to channels and construct of a height sufficient to maximize detention while keeping the water in the channel.  Place and install check dams according to the Plans and anchor to maintain in effective position.

a.	Sandbag.  Place the initial row in tight contact with the ditchline for the length of the dam.  Place each following row centered across the joint between the bags of the lift/row below.

7.	Stabilized Construction Entrance.

Temporary stabilized construction entrance shall be constructed according to the Plans, prior to beginning any clearing, grubbing, earthwork, or excavation.

When the stabilized entrance no longer prevents track out of sediment or debris, the Contractor shall either rehabilitate the existing entrance to original condition, or construct a new entrance.

When the Plans require a tire wash in conjunction with the stabilized entrance, the Contractor shall include details for the tire wash and the method for containing and treating the sediment-laden runoff as part of the SWPPP.  All vehicles leaving the site shall stop and wash sediment from their tires.

8.	Sediment Control Barriers.  Sediment control barriers shall be installed according to the Plans or manufacturer's recommendations in the areas of clearing, grubbing, earthwork, or drainage prior to starting those activities.

a.	Sandbag.  Place the initial row in tight contact with the surface perpendicular to the slope.  Place each following row centered across the joint between the bags of the lift/row below.

b.	Sediment Retention Fiber Rolls.

c.	Silt Fence.

d.	Compost Berm.  Construct compost berms according to latest AASHTO R 51.  Use coarse compost.

CR619-070115.SSHC2017/CFHWY00317

9.	Turf Reinforcement Mats.  According to manufacturers installation instructions for the corresponding slope (?H:1V) identified in the plans.

CR619.SSHC2017/CFHWY00317

619-3.04 MAINTENANCE.  Maintain stabilized areas in a satisfactory condition for the term of the Contract, including warranty obligations.  Inspect as required by the CGP, approved SWPPP, and Section 641 Erosion, Sediment and Pollution Control and correct any deficiencies immediately.  Remove and dispose of temporary measures, including trapped sediment and contaminants, off project at approved locations.  Materials manufactured as degradable may be left in place when approved by the Engineer.

Maintenance includes but is not limited to:

a.	Protecting stabilized areas against traffic by approved warning signs or barricades.

b.	Repairing surfaces gullied or otherwise damaged following application of stabilization material(s).

Where seeding is included as a part of the soil stabilization:

c.	Reseeding, as required by Section 618 Seeding.  Reapply the stabilization materials correcting the problems of the initial application.

d.	Watering, where vegetative growth is part of the soil stabilization, according to Section 618 Seeding.

The Engineer will perform inspection of the stabilization as required in the CGP, Section 641, and the SWPPP.  Make repairs as required by same and as directed.

619-4.01 METHOD OF MEASUREMENT.  Section 109, measured on the slope of the ground surface.

619-5.01 BASIS OF PAYMENT.  Water, maintenance, repair, removal, and disposal of temporary stabilization materials are subsidiary.

Seeding is paid under Section 618 Pay Items, topsoil under Section 620 Pay Items, silt fence under Section 633 Pay Items and temporary erosion, sediment, and pollution control under 641 Pay Items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

619(1)	Mulching	Square Yard

619(2)	Matting	Square Yard

619(3)	Compost	Square Yard

619(4)	Turf Reinforcement Mat	Square Yard

619(5)	Sediment Retention Fiber Rolls (SRFRs)	Linear Foot

619(6)	Check Dam and Sediment Barrier - Geotextile	Linear Foot

619(8)	Compost Berm	Linear Foot

619(9)	Sandbags	Each

619(10)	Manufactured Inlet Protection System	Each

619(11)	Sandbag Inlet Protection System	Each

CR619-070115.SSHC2017

SECTION 620
TOPSOIL

620-1.01 DESCRIPTION.  Add the following:

Community garden beds include topsoil at depth as shown or specified on plans.

Rain gardens include a rain garden topsoil mix.

620-2.01 MATERIALS. Add the following:

Sand		Subsection 703-2.14

620-4.01 METHOD OF MEASUREMENT.  Replace with the following:

Topsoil for planting beds (backfill mix) and Community Gard Beds will not be measured.

Topsoil for rain gardens is measured by area on the slope of the ground surface.

620-5.01 BASIS OF PAYMENT.  Add the following:

Topsoil for planting beds and Community Garden Beds is subsidiary to Section 621 Pay Items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

620(2)	Rain Garden Soil	Square Yard

CFHWY00317

SECTION 621
PLANTING TREES AND SHRUBS

Special Provisions

Add the following subsection:

621-1.02 SUBMITTALS.

Submit plant availability list within 60 days of award of contract. The quantities, sizes, and species of plants may require 12-18 months of lead time. On the availability list include the species by common and botanical name, size, available quantity, and source for material.  For the material source, provide name, address and phone number for nursery and/or grower. For plants located outside Southcentral Alaska provide photographs typical to each species.  Include tape measure or other graphic means to allow verification of size. Provide evidence that the plants have been secured for use including receipt for partial payment or vendor certification that material is available in sizes and quantities.

621-2.01 PLANT STOCK.  Add the following:

Variety and species are listed in the Schedule on the plans. Bare root trees and shrubs are not permitted.

1.	Nursery Stock.

b.	Delete paragraph in its entirety and substitute the following: Use container-grown plants that are healthy, vigorous, well rooted and established in the container in which they are furnished.  Assure the root mass retains its shape within the soil volume and hold together when removed from the container without being root-bound. Remove weeds, grasses and foreign materials including foreign roots.  Provide plants with healthy full leaf growth.  Dormant plants are not permitted.

2.	Collected Stock. Add the following: Only use collected stock when the source is no greater than 250 miles from the project site.  Dig and store collected stock in a nursery for no less than one year prior to installation.

6.	Inspection.

a.	Delete Paragraph (a) and substitute the following: Make all planting stock available for inspection in the nursery at least 10 working days before digging operations.

621-2.02 FERTILIZER. Delete this subsection and substitute the following:

Do not use chemical fertilizer for trees, shrubs and perennials.  Use organic fertilizer or compost tea. Supplement with mycorrhizae soluble powder.

621-2.04 MULCH. Delete this subsection and substitute the following:

Use shredded bark mulch consisting of shredded wood fibers with the characteristics of retaining moisture and forming a mat so as not to be disturbed by wind or rain. Ensure individual components are not greater than 3 inches in length with a minimum of 75 percent of the total mulch component passing through a 1 inch screen.  Remove growth or germinating inhibiting ingredients.  Age locally harvested shredded wood fibers for one-year minimum prior to installation.  Commercially available shredded wood fiber landscape mulch may be used, provided no chemical color has been added.  Wood chips are not acceptable.  Resin, tannin, or other compounds in quantities that are detrimental to plant life are not allowed. Provide dried mulch sample in 1 quart container at least thirty days prior to installation.

Add the following subsection:

621-2.09 ANTI-DESICCANT. Use commercial anti-desiccant product that eliminates or reduces windburn on evergreen plants.

CONSTRUCTION REQUIREMENTS

621-3.02 ADVANCE PREPARATION AND CLEANUP. Delete the second paragraph.

621-3.03 PLANTING. Delete Item 1. Plant Season, and substitute the following:

- Plant Season.

a.	Locally Grown:  When locally grown plants are furnished for the project, plant them between May 15 and September 15. Do not plant when snow is on the ground or when the ground is frozen.

b.	Imported:  Handle plants shipped in from out-of-state according to the nursery recommendations.  Install plants imported from out-of-state between May 15 and August 15.

Delete Item 2. Excavation, and substitute the following:

2.	Prepare Planting Beds

  - Planting bed preparation includes excavation to depth as shown on plans, loosening of sub-grade soils and placement of topsoil. Do not prepare planting beds more than two (2) days prior to planting.

  - Prior to excavation of planting areas, ascertain the location of all utilities so that proper precautions may be taken not to disturb or damage any subsurface improvements.  Should obstructions or conflicts be found, promptly notify the Engineer.  Prepare a revised plan that avoids conflicts with the Utility and meets the intent of the original plan to the extent possible.  Submit the revised plan for the Engineer’s approval prior to construction of the planting bed.

  - Excavate planting beds for trees and shrubs to the depth as shown on plans.

  - Planting beds with only perennials may be excavated to a depth of 12 inches, shrub beds to a depth of 18” as shown on plans.

  - Once excavated, sub-grade do not compact planting bed.  Do not use heavy equipment within planting beds.

  - Soak planting beds with water.  Allow to drain completely. Notify Engineer if planting beds are not draining properly. The engineer may determine that gravel is required at the bottom of planting pits to allow drainage.  Following approval of planting pits, place topsoil in eight inch lifts.  Water planting beds to moisten topsoil. Allow water to absorb in throughout planting bed.  Moisten topsoil backfill during planting if topsoil is dry.  Do not plant if topsoil has excess water including pools, puddles, inability to compact or muddiness.

  - After approval of topsoil filled planting beds by Engineer, dig planting holes within the planting bed.  Firmly tamp the base of the planting hole to assure plants will not settle to lower than their proper planting depth.  Water planting holes prior to planting if soil appears dry or if planting bed has not been planted within 24 hours of initial watering.

- Pruning.  Delete the last two sentences of paragraph (b.) in their entirety.  Add the following:

c.	Clear Vision/Sight Triangle. Pruning may be required to assure plants do not constitute a hazard within or adjacent to areas noted on plans as sight triangles.  Prune only under the direction of the Engineer. Pruning only after all landscaping has been completely installed.

- Placing Plants.  Delete paragraph a. in its entirety and replace with the following : Set plants plumb on lightly tamped backfill mix and at a level so that the root collar or root flare is at or just above the finished grade as.  Do not bury plant root flares, where nursery grown stock includes plants with buried root flares, excavate as required to expose root flare.

Delete Paragraph (b) and substitute the following:

b.	Handle balled and burlapped plants, plants in wire baskets or containers by the earth ball, container, or basket and not by the plant itself.  Remove wire baskets and burlap completely and dispose of properly.  The Engineer may reject any plants whose rootballs collapse during planting.

- Wrapping. Delete in its entirety and replace with the following :

7. Fertilizer application. Apply organic fertilizer or compost tea to plant materials in the fall after initial planting. Notify Engineer 3 work days prior to application to coordinate inspection of fertilizer application.  Apply Vitamin A mix to topsoil during planting operations for all trees following manufacturer’s recommended rates. Apply mycorrhizae soluble powder to plants during planting operations following manufacturer’s recommended rates.  Apply to each individual tree and shrub as it is installed and to perennial planting areas to allow even distribution throughout the planting area.

Add the following:

9. Mulch. Place approved mulch throughout planting beds at a depth of 3-inches.  Do not bury bases of tree, shrubs or perennials. Leave the area around the base of the plant free of mulch keeping 3-6” clear.  Place mulch within 24 hours of planting.

621-3.05 CLEANUP.  Add the following:  Keep planted and seeded areas clean of litter and garbage during the growing season.

621-3.06 PLANT REPLACEMENTS. Delete in its entirety and add the following:  Replace plants following details and specifications in the original Contract Documents. Within 48 hours of notification, replace plants that are dead, dying or no longer meet specifications. A plant is considered dead or unacceptable when the main leader is dead or gone in the case of a tree, or when twenty-five percent (25%) of the crown, twigs, or leafing area is dead. The Engineer makes the determination as to whether a plant is dead or dying.

If damaged plants are not replaced as required, the Engineer may replace or have replaced the damaged items and deduct the cost of said repair or replacement work from remaining payments.

621-3.07 MAINTENANCE.  Add the following:

Maintenance Schedule

Submit a project-specific maintenance schedule based on the anticipated Engineer approval of plant installation.

In addition to describing the weekly maintenance routine, identify specific dates for less-frequent activities such as pruning, and applying anti-desiccants, fertilizer, and pesticides.

Scope

Maintenance begins as soon as each plant is installed and continues in accordance with these specifications for a full growing season following acceptance of plantings.  Maintenance includes:

- The care of all trees, shrubs, perennials, and seeded areas with activities including watering, disease control, pruning, fertilizing, and weeding;

- Resetting edging that has lifted or been displaced;

- Replacement of plants as required; and

- Repair or replacement of related elements such as stakes and mulch.

Perform the following maintenance activities:

a.	Mowing.

Mow seeded areas using seed mix A and B once at the end of the first complete growing season or as directed by the Engineer. Mow seed Mix C at least three times per month for a three month period once it has been established and accepted.  Where establishment occurs after September 15 mow the following growing season. Continue mowing for a three month period but not after first heavy frost as determined by the Engineer.

b.	Watering.

Deep water the root balls of all trees and shrubs on a bi-weekly basis.  Deep watering means water penetration through the root zone to a depth of the planting pits. Minimize runoff.  Rain will not be considered as a substitute for deep watering unless permitted by the Engineer.  Deep water all evergreen plants just prior to freeze-up in order to minimize over-wintering desiccation.  Apply anti-desiccants to conifers while the Engineer is present.  Notify the Engineer in writing 4 working days prior to applying anti-desiccants.

Equip watering equipment with, or followed by a vehicle equipped with a Type B advance warning arrow panel using caution mode according to Part VI of the Alaska Traffic Manual.

c.	Disease Control.

Apply pesticides, insecticides, or other disease-control methods as necessary to maintain plant health.  Permission of the Engineer and appropriate permits for the application of insecticides from the DEC must be obtained prior to the application of any regulated products.

d.	Pruning.

Prune all plant materials, with appropriate pruning techniques, only to remove dead or dying twigs and branches on the plants.  Do not treat or paint cuts. Prune flowering trees no more than two weeks after flowers drop off or decay.  Prune damaged trees or those that constitute health or safety hazards as directed by the Engineer at any time of the year.  Prune trees under the direction of the Engineer.  Provide 48 hours-notice to the Engineer prior to pruning.

e.	Fertilizer.

Fertilize all trees, shrubs, and perennials in the prior to June 15 at the rates shown in Table 621-1.  Apply per manufacturer’s recommendations and thoroughly water into the ground.   Notify the Engineer in writing 4 working days prior to applying any fertilizers, stating the time and location of fertilizer application if they differ from the maintenance schedule.

TABLE 621-1

MAINTENANCE FERTILIZER SCHEDULE

Plant Type							Fertilizer			Application Rate

Deciduous Trees					5-5-5				1 lb. for each 1-inch caliper

Shrubs and Perennials				5-5-5 				15 lbs. per 1000 square feet

f.	Weeding.

Keep all planting beds and seeded areas in a weed-free condition during planting and throughout the growing season.  Remove weeds on a weekly basis and as requested by the Engineer.  Weeds include grasses and other undesirable plants within planting beds.

Schedule a joint inspection with the Engineer at the complete growing season.  Correct all deficiencies noted during the inspection to the satisfaction of the Engineer.

Add the following:

621-3.08 COMMUNITY GARDEN BED INSTALLATION.

The work in this section includes the preparation of community planting beds at the gateway sign planter and at community garden areas and installation of aluminum edging at community gardens.  At the gateway sign and community garden areas, backfill planter with approved topsoil mix as required compacting topsoil in six inch lifts.  Provide three (3) inches of shredded bark mulch cover over topsoil with maximum 6-inch wide transition to meet adjacent flush surfaces.

621-4.01 METHOD OF MEASUREMENT.  Delete this subsection in its entirety and substitute the following:

Section 109, by the number of plants alive and healthy at the time of final inspection.

621-5.01 BASIS OF PAYMENT.  Add the following:

The quantity of all plant materials accepted in place will be paid for at 70% of the Contract price, per unit of measurement for each pay item.  Payment of the remaining 30% will be made after all deficiencies noted during the inspection at the end of one complete growing season following acceptance by the Engineer.

Water for maintenance of trees, shrubs, and perennials is subsidiary to 621(1_), 621(2_), and 621(3_) Pay Items.

Edging and shredded bark mulch at Community Garden Beds are subsidiary to 621(4) Community Garden Bed.

Topsoil for planting beds, shredded bark mulch, excavation of planting beds, disposal of unsuitable and surplus material, stakes and staking,  preparing the maintenance schedule, the maintenance required following planting, and the correction of deficiencies at the end of the complete growing season are subsidiary to 621(1_), 621(2_), and 621(3_) Pay Items.

Pay Item No.	Pay Item	Pay Unit

621(1A)	Tree, Amur Chokecherry (Prunus maackii), 2-Inch Caliper	Each

621(1B)	Tree, Aspen Columnar (Populus tremula ‘Erecta’), 3-Inch Caliper	Each

621(1C)	Tree, Birch (Betula papyifera), 3-Inch Caliper	Each

621(1D)	Tree, Birch, Clump (Betula papyifera), 2-4 Inch Caliper, 3 trunks	Each

621(1E)	Tree, Larch (Larix siberica), 6’ Tall	Each

621(1F)	Tree, Maple (Acer platanoides ‘Deborah’), 3-Inch Caliper	Each

621(1G)	Tree, Spruce (Picea glauca), 5’ Tall	Each

621(1H)	Tree, Spruce (Picea glauca), 7’ Tall	Each

621(2A)	Shrub, Lilac Mix A (Syringa vulgaris sp.), #5 Cont.	Each

621(2B)	Shrub, Lilac Mix B (Syringa vulgaris sp.), #5 Cont.	Each

621(2C)	Shrub, Lilac Mix C (Syringa vulgaris sp.), #5 Cont.	Each

621(2D)	Shrub, Cotoneaster (Cotoneaster lucidus) #5 Cont.	Each

621(2E)	Shrub, Dwarf Korean Lilac (Syringa meyeri), #5 Cont.	Each

621(2F)	Shrub, Highbush Cranberry (Viburnum trilobum), #5 Cont.	Each

621(2G)	Shrub, Miss Kim Lilac (Syringa patula ‘Miss Kim’), #5 Cont.	Each

621(2H)	Shrub, Rose, Native (Rosa rugosa) , #5 Cont.	Each

621(2I)	Shrub, Spirea (Spirea japonica ‘Goldflame’), #5 Cont.	Each

621(3A)	Perennial, Iris (Iris setosa),  1 Gallon	Each

621(3B)	Perennial, Meadow Rue (Thalitcrum rochebruneanum),  1 Gallon	Each

621(4)	Community Garden Bed	Each

CFHWY00317

SECTION 622
REST AREA FACILITIES

Special Provisions

622-1.01 DESCRIPTION.  Add the following:

9. Edging

622-2.12 REST AREA SIGN. Add the following:

Meet the requirements in Section 730.

Remount existing Gateway Sign panel as shown on drawings.

Add the following Subsection:

622-2.13 EDGING.  Use commercially manufactured aluminum edging. Install per manufacturer's specifications, straight, level and secure, using stakes at distances recommend by manufacturer.  Use full length pieces to extent possible, do not use pieces shorter than 6-feet long.  Bend edging at corners to clean 90-degree angles, keep seams at least 4-feet away from corners, replace buckled or warped edging.

Wood edging made of 12-foot lengths of 1x6 cedar.

622-4.01 METHOD OF MEASUREMENT. Add the following:

622(6A) Gateway Sign. The contract price includes concrete, footings, excavation, backfill, porous backfill, geotextile fabric, aesthetic fascia, anti-graffiti protection, remounting of existing sign panel, mounting hardware, artwork and related components.

622(6B) Interpretive Sign, Type C. By each, complete in place.

622-5.01 BASIS OF PAYMENT. Add the following:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

622(6A)	Gateway Sign	Lump Sum

622(6B)	Interpretive Sign, Type C	Each

622(17)	Edging, Aluminum	Linear Foot

622(18)	Edging, Wood	Linear Foot

CFHWY00317

Special Provisions

Delete Section 626 in its entirety and replace with the following:

SECTION 626
SANITARY SEWER SYSTEM

626-1.01 DESCRIPTION. For the purposes of these specifications, Sewer Utility shall mean the sewer system operated by the City of Palmer.  Construct or reconstruct sanitary sewers and appurtenances to conform to the plans.  This section refers to conduit used for sanitary sewers as “sewer conduit.”

626-2.01 MATERIALS. Provide product data submittals for each material to be incorporated into the work.  Include sufficient data to document the material provided meets or exceeds these specifications, as well as any additional data requested below.  Provide a Wastewater Bypass Pumping Plan that clearly illustrates how service will be maintained during construction of required utility sections.

- Class “C” Bedding:  Materials used as Class “C” bedding and initial backfill shall be graded within the limitations delineated below:

| Sieve Size | Cumulative percent Passing by Weight |
| --- | --- |
| 2-inch | 100 |
| 1-inch | 40-100 |
| No. 4 | 20-75 |
| No. 10 | 12-60 |
| No. 40 | 2-30 |
| No. 200 | 0-6 |

In addition to the bedding limits listed above, the fraction of material passing the No. 200 sieve shall not be greater than 20% of that fraction passing the No. 4 sieve.

Onsite material meeting these requirements may be used or material may be furnished by the Contractor.

2.	Class “E” Pipe Bedding Material.  Service connections shall be bedded with Class “E” bedding material conforming to the following:

| Sieve Size | Cumulative Percent Passing by Weight |
| --- | --- |
| ½-inch | 100 |
| 3/8” | 80-100 |
| #4 | 20-75 |
| #8 | 12-60 |
| #30 | 2-30 |
| #200 | 0-6 |

3.	Sand Slurry.  Sand slurry consists of a mixture of water and sand with an approximate ratio of seven (7) gallons of water per cubic foot of sand.  Sand may consist of native material with a particle size distribution such that one hundred percent (100%) of the material passes the No. 4 U.S. Standard Sieve and contains no lumps, frozen material, organic matter, or other deleterious material.

4.	High Density Polyethylene (HDPE) Pipe and Fittings:  Materials used for the manufacture of HDPE and fittings shall be categorized as extra high molecular weight and meet all requirements of ASTM D3350 and the Plastic Pipe Institute’s (PPI) PE4710.  The high-density polyethylene material shall be a cell class of 445474C per ASTM D3350 and shall be assigned a PPI designation of PE4710.  Pipe manufacturer shall be a member in good standing of the Plastic Pipe Institute.

In addition, materials used for the manufacture of the HDPE pipe and fittings shall meet the following physical property requirements:

| PROPERTY | UNIT | Test Method(1) | Nominal Value |
| --- | --- | --- | --- |
| Material designation | — | PPI/ASTM | PE4710 |
| Cell classification |  | D3350 | 445474C |
| Further, the material must have a |  |  |  |
| Density | gm/cc | D1505 | 0.947-.955 |
| Melt index | gm/10min. | D1238 | <0.15 |
| Flexural modulus | psi | D790 | >110,000-160,000 |
| Tensile strength @ yield | psi | D638 | >3,600 |
| Slow Crack Growth |  |  |  |
| ESCR | Hrs. in 100% igepal | D1693 | >5,000 |
| PENT | hours | F1473 | >500 |
| HDB @ 73.4°F | psi | D2837 | 1600 |
| @ 140° F | psi | D2837 | 1000 |
| UV Stabilizer | %C | D1603 | 2 to 2.5% |

(1) Test procedures are ASTM unless otherwise specified. (PPI = Plastics Pipe Institute, and GPC = Gel Permeation Chromatography)

Pipe and fittings shall be manufactured from material meeting the requirements of the above table.  The manufacturer shall certify that samples of the manufacturer's production product have been tested in-house in accordance with ASTM D2837, and validated in accordance with the latest revision of PPI TR-4.

a.	Manufacturer shall comply with AWWA Standard C901 (1/2" through 3") and C906 (4" through 63").  The material shall be listed by PPI a division of The Society of the Plastics Industry in PPI TR-4.  The pipe material shall have a Hydrostatic Design Basis of 1600 psi at 73.4° F and 800 psi at 140°F.  The PPI listing shall be in the name of the pipe manufacturer and testing and validation of samples of the pipe manufacturer’s product shall be based upon ASTM D2837 and PPI TR-3.

b.	Reference Standards: AWWA, C-901, AWWA C-906, ASTM D2683, ASTM D3261, ASTM D3350, PPI TR-3, PPI TR-4.

Both pipe and fittings shall carry the same pressure rating.  All fittings shall be pressure rated to match the system piping to which they are joined.  At the point of fusion, the outside diameter and minimum wall thickness of the fitting shall meet the outside diameter and minimum wall thickness specifications of ASTM F714 for the same size of pipe.  All fittings shall be properly rated according to manufacturer's written recommendations, and clearly labeled on the fitting as such.  Manufacturer shall have a written specification for all standard fittings which establishes Quality Control criteria and tolerances.  The manufacturer of the pipe shall be the same manufacturer of the fabricated fittings and other fabrications.  The manufacturer shall certify that the materials used to manufacture pipe and fittings meet the requirements of this specification.

Pipe supplied shall have a nominal IPS (Iron Pipe Size) outside diameter.  The Standard Dimension Ratio (SDR) and pressure rating of the pipe in accordance with ASTM 2837 at 73 degrees F and a service rating of 0.5 shall be 160 psi for SDR 11 and 100 psi for SDR 17.

The pipe shall have product traceability.  This shall be accomplished by the inclusion of a product code into the printline of all products.  This shall notate the manufacturer, the date of manufacture, the lot and supplier of raw material, the location of manufacture, and the production shift on which the product was produced.  The printline shall also include other markings as required by AWWA C901 or C906 and shall be made permanent by heat indentation.  The printline shall be easily readable against the black pipe.

Pipe and fittings shall be butt fusible according to the manufacturer recommended procedures.  The socket or sidewall fittings shall also be to manufacturer's recommended procedures.

Internal bead resulting from fusion welding shall be removed from all fabricated bends.

Provide a copy of the manufacturer’s PPI certification, a statement that the raw materials used to manufacture the pipe meet the cell classification requirements.

5.	HDPE Pipe Jointing.  Pipe joints shall be in accordance with PPI TR-33 Generic Butt Fusion Procedures.  Electrofusion couplings may be used only where the use of butt fusion in not practicable or where indicated.  Electrofusion couplings shall be in accordance with AWWA C906 and shall be the same pressure rating as pipe.  Where necessary, pipe and fittings may be joined with flanged adapters and hot-dip galvanized back-up rings.

6.	Ductile Iron Pipe (DIP) and Fittings.  DIP shall conform to ASTM A 746/AWWA C151 thickness class 50, with a working pressure not less than 250 psi, unless otherwise shown or specified.  Pipe shall be cement-mortar lined in accordance with AWWA C104.  Linings shall be standard.

Fittings and specials shall be suitable for 250 psi pressure rating, unless otherwise specified.  Fittings and specials for mechanical joint pipe shall conform to AWWA C110.  Fittings and specials for use with push-on joint pipe shall conform to AWWA C110 and AWWA C111.  Fittings and specials shall be cement-mortar lined (standard thickness) in accordance with AWWA C104.  Ductile iron compact fittings shall conform to AWWA C153.

7.	DIP Pipe Jointing.  DIP Pipe joints shall be push-on joints conforming to AWWA C111.  Rubber gaskets and lubricants for all joints shall conform to applicable requirements of AWWA C111.

8.	Service Saddle.  Connection to the sanitary sewer main shall be made with a Romac Style CB epoxy coated sewer saddle or approved equal.

- Repair Clamp.  Decommissioned service connection hole in main shall be repaired with Romac Style CL3 Cast Lug Repair Clamp or approved equal of sufficient length to extend at least 4” on each side of the repaired hole.

10.	DIP Pipe Coupler.  Joining of new DIP to existing DIP shall be made with Romac Macro HP Coupling or Equal.

11.	Insulation Board.  Where insulation is required, conform to Section 635.

12.	Polyethylene Encasement.  Where required material shall conform to Subsection 707-2.05

13.	Warning Tape.  Metallic core or metallic-faced, acid- and alkali-resistant, polyethylene plastic warning tape manufactured specifically for warning and identification of buried utility lines.  Minimum thickness of tape shall be 0.003 inch.  Tape shall have a minimum strength of 1500 psi lengthwise, and 1250 psi crosswise, with a maximum 350 percent elongation.  Provide tape on rolls, 3-inch minimum width, color coded green for the sewer utility with warning and identification imprinted in bold black letters continuously over the entire tape length.  Warning and identification to read: "CAUTION, BURIED SEWER LINE BELOW" or similar wording.  Color and printing shall be permanent, unaffected by moisture or soil.

14.	Detection Wire.  Detection wire shall be insulated single strand, solid copper with a minimum of 10 AWG.  Labels shall be cable tags made of nylon reinforced vinyl that is impervious to the elements and will not tear, 4 inches by 1-¾ inches minimum size, attached flag style at one corner to a single strap, and red in color.

15.	Casing.  Casing shall be size, type, and thickness as shown on the plans and specified herein.  Corrugated Polyethylene Pipe (CPEP) used for casings shall meet the requirements of Subsection 706-2.07.  HDPE pipe casings shall meet the requirements of this section.  Steel pipe casings shall be smooth walled with minimum yield strength of 35,000 psi without protective coating with a minimum wall thickness per the plans.  End seals shall be watertight, segmented elastomeric end seals or, for an empty casing for future use, a suitable, slip-over pipe cap may be used.  Casing spacers shall be as specified on the Plans.

Casing Marker posts shall meet the requirements of Subsection 730-2.05, Flexible Delineator Posts.  The color shall be yellow with no other markings.  The 2.5-inch by 6-foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9-inches.

16.	Precast Concrete Manholes.  Precast concrete manhole risers, base sections, and tops shall conform to ASTM C 478; base and first riser shall be monolithic, except for horseshoe manholes.

Concrete is to be of a suitable mixture of aggregates, cement, and water to achieve a 28-day break strength of 4,000 psi per ASTM C39.  Maximum aggregate size is to be no greater than one and one-half inch (1-1/2”), one fifth (1/5) the wall thickness and half (1/2) of the minimum space between reinforcement to other reinforcement or forms.

Reinforcement steel must conform to the requirements of ASTM A-1064, ASTM A-615, Grade 40 or 60 steel, or ASTM A706, Grade 60 steel, and the plans.  Reinforcement steel is to be installed through the transition from the base to the vertical walls of the manhole.

Cones shall be eccentric, unless otherwise noted.  Grade rings shall be a minimum of three inches (3”) thick and provide a clear opening that is at least as large as what the casting provides.

17.	Gaskets and Connectors:  Gaskets for joints between manhole sections shall conform to ASTM C 443, RAM-NEK or approved equal.  Resilient connectors for making joints between manhole and pipes entering manhole (boots) shall conform to ASTM C 923 or ASTM C 990.  Z Lok Connector by A-Lok Products, Inc., or equal shall be cast integral with the concrete structure.  G3 Boot by A-Lok Products, Inc., Kor-N-Seal 1 and, Wedge Style Pipe to Manhole Connector, or equal shall be used for core drilled penetrations.

18.	Cement Mortar.  Cement mortar shall conform to ASTM C 150, Type II.  Sand shall conform with AASHTO Specification M-45.  The mortar shall be composed on one (1) part cement and three (3) parts sand.  The joints shall be constructed to produce a smooth regular watertight surface.  Only enough water shall be added to provide plasticity in placing the mortar.

19.	Portland Cement.  Refer to Section 501 for specification pertaining to Class A Concrete as required for forming manhole inverts and capping decommissioned services.  The use of Transite or Asbestos Cement (AC) pipe to form manhole inverts is prohibited.

20.	Frames, Covers, and Gratings for Manholes.  Frames and covers shall be cast iron and shall be as indicated on the drawings.  The word “Sewer” shall be stamped or cast into covers so that it is plainly visible.  The tensile strength shall be 30,000 psi minimum, conforming with the requirements of ASTM A-48.  The requirement for transverse breaking load shall be 2,000 pounds, conforming with the requirements of ASTM A-438.  Manhole covers shall be fitted with a pre-approved locking device when indicated on the plans.

21.	Manhole Steps.  Manhole steps shall meet the requirements of ASTM C-478 and AASHTO M-199 constructed with Grade 60 rebar with copolymer polypropylene molded cover with footing grip pegs, contoured back side for fingers and reflective surface on each side of the rung visible from above, such as, but not limited to the polypropylene steps manufactured by Lane International Corporation.

CONSTRUCTION REQUIREMENTS.

626-3.01 GENERAL

Contractor shall furnish and install all incidental parts not shown on the Plans or specified in this section that are necessary to complete sanitary sewer system.

- Delivery, Storage and Handling

Inspect materials delivered to site for damage; store with minimum of handling.  Store materials on-site in enclosures or under protective coverings.  Store plastic piping, jointing materials and rubber gaskets under cover and out of direct sunlight.  Do not store materials directly on the ground.  Keep inside of pipes and fittings free of dirt and debris; temporary end seals on HDPE pipe are to remain in place until it is necessary to remove them for welding or other final connection.  Immediately remove any dirt or debris introduced into the pipe or fittings.

Handle HDPE pipe, fittings and other accessories in accordance with AWWA C906 and the manufacturer’s written instructions.  Handle pipe, fittings, and other accessories in such manner as to ensure delivery to the trench in sound, undamaged condition with a clean interior.  Take special care not to damage exterior of HDPE pipe and fittings; pipe with gouges or scratches that exceed 10% of the wall thickness must be removed and not used.  Carry, do not drag HDPE pipe to trench.

Take special care not to damage linings of pipe and fittings; if lining is damaged, make satisfactory repairs.

- Trench Excavation and Backfill

Excavation and backfill shall be to the width and depth as shown on the Plans.  Trench width at or below the top of the pipe shall be of a width that will allow compaction equipment to be utilized at the sides of the pipe.

Contractor shall erect and maintain barricades to prevent access around all excavations left open at the end of the workday.  Contractor shall provide and maintain adequate barricades to ensure public safety at all times during the prosecution of the Work.

Contractor shall perform all excavation of every material encountered.  Excavated material shall be placed in an orderly manner and at a distance from the trench conforming to all State and/or Federal safety codes.  Excavated material meeting the requirements of Select Material shall be stockpiled separately and reused in the Work.

Not more than 200 feet of trench shall be open in advance of the pipe installation unless authorization, in writing, is obtained from the Engineer.  Trench shall not be left open at the end of the workday, unless otherwise approved by the Engineer.

All bedding and initial backfill material shall be placed in uniform layers of not more than 6 inches in depth and compacted to not less than 90% of maximum density for HDPE pipe and not less than 95% for DIP pipe. In no case shall bedding material be placed above the springline of the pipe in a single lift.  Care shall be taken to ensure there is no settlement, no deformation, and no displacement of the pipe.  Final backfill material shall be placed in uniform layers of not more than 12 inches in depth and compacted to not less than 95% of maximum density in accordance with Subsection 203-3.04.  Ponding or jetting of backfill will not be permitted.

When existing conduits or utilities, which are not scheduled for removal or abandonment, are encountered in the excavation, they shall be adequately supported and protected from damage.  All shoring and support for the existing power, communications and natural gas facilities shall be approved by the respective utility.

All sheeting and bracing used in excavation shall be removed by the Contractor following the completion of the work.

- HDPE Pipe Installer’s Qualification

The Contractor shall supply a written certificate of qualification from the pipe manufacturer identifying the individuals employed by the Contractor qualified to supervise the proper installation and testing of the pipe in accordance with the manufacturer’s prescribed procedures.  Alternatively, the Contractor shall have a manufacturer's field representative present at the jobsite during the initial installation and testing of HDPE pipe to provide technical assistance and to verify that the materials are being installed in accordance with the manufacturer's prescribed procedures.  When the representative feels that the Contractor is installing and testing the pipe in a satisfactory manner, certification shall be written to note which individuals employed by the Contractor are capable of properly installing the pipe.  The field representative shall advise the Contractor of unsatisfactory conditions immediately when they occur.  Such conditions include improper diameter of pipe ends, poorly prepared joints, improper curing of joints, moving pipe before joints are cured, bending pipe to follow abrupt changes in trench contours, leaving pipe ends open in trench overnight, not properly drying joints after rain storms, exceeding effective adhesive life, sharp objects in trench bed, backfill that could damage pipe, improper procedure for concrete encasement of pipe, omission of thrust blocks at changes in direction or any other condition which could have an adverse effect on the satisfactory completion and operation of the piping system.

- HDPE Pipe Fusion-welder Qualifications

Jointing of HDPE pipe shall be performed by qualified workers, possessing current certificates of qualifications issued by the fusion-equipment manufacturer.  Provide copies of current certificates for each welder.

- Bypass Pumping

The Contractor shall provide bypass pumping of sanitary sewer as required to maintain service during construction.  The Contractor shall provide any necessary piping, pumps, valves, temporary connections or appurtenances to maintain sewer service.  Any costs involved in service changeovers and with providing bypass pumping shall be subsidiary.  The Contractor shall be responsible for all damages incidental to interruption of service that may be due to his operations.  Bypass pumping systems shall be in accordance with DEC regulations, and shall be approved by the Engineer and the Sewer Utility prior to implementation.

- Final Acceptance

The Contractor shall, upon completion of all work involved for the Sanitary Sewer System, notify the Engineer in writing of completion and request a pre-final inspection of the water system construction. This inspection will be performed in the presence of the Engineer, the Water/Sewer Utility, and the Contractor.  Copies of a list of deficiencies indicated by this inspection, if any, will be furnished to the Contractor for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and an acceptance inspection will be performed.

626-3.02 SANITARY SEWER CONDUIT.

- General.  In all cases pipe installation is to proceed from lower to higher elevations with the spigot ends of the pipe at the lower end of each pipe segment.  Lay conduit to the grades and lines shown on the Plans.  However, at a sufficient distance prior to encountering a known obstacle or tying into an existing conduit, the Contractor shall expose and verify the exact location of the obstacle or conduit so proper alignment and/or grade may be determined before the conduit sections are laid in the trench and backfilled. The costs incurred for removal and realignment of backfilled conduit sections due to improper verification methods shall be borne by the Contractor.

Inspect each pipe and fitting before and after installation; replace those found defective and remove from site.  Pipe and accessories shall be carefully lowered into the trench by means of derrick, ropes, belt slings, or other authorized equipment.  Pipeline materials shall not be dropped or dumped into the trench.  The full length of each section of pipe shall rest solidly upon the pipe bed.  Pipe that has the grade or joint disturbed after laying shall be taken up and re-laid.  Pipe shall not be laid in water or when trench conditions are unsuitable for the work.  Water shall be kept out of the trench until joints are complete.  When work is not in progress, open ends of pipe, fittings, and valves shall be securely closed so that no trench water, earth, or other substance will enter the pipes or fittings.  Pipe ends left for future connections shall be valved, plugged, or capped, and anchored, as shown.  Provide batter boards not more than 25 feet apart in trenches for checking and ensuring that pipe invert elevations are as indicated for gravity systems.  Laser beam method may be used in lieu of batter boards for the same purpose.

Place bedding to conform to plan details and to give conduit a uniform bearing for its full length.  Do not permit bell ends to rest on original trench bottoms.

Cutting of pipe shall be done in a neat and workmanlike manner without damage to the pipe.  Unless otherwise recommended by the manufacturer and authorized by the Engineer, cutting shall be done with an approved-type mechanical cutter.

The Contractor shall have survey instruments such as transit and level for transferring alignment and grades from offset hubs.  He shall also have in his employ a person who is qualified to use such instruments and who shall have the responsibility of placing and maintaining such construction guides.  The Contractor shall furnish to the Engineer a copy of the surveyor’s record notes for the newly installed conduit and appurtenances.  The practice of placing backfill over a section of conduit to provide a platform for the instruments shall be subject to the approval of the Engineer.

A minimum of 10-foot horizontal separation shall be maintained between water and sanitary sewer mains, or water and storm drains.  Locations having less than 10-foot minimum separation require an ADEC waiver.

A minimum vertical separation of 18 inches shall be maintained at water and sewer or water and storm drain crossings.  Where a storm drain and water main cross, insulate the water main with 4-inch thick rigid insulation board (R min=4.5 per inch).

- HDPE Pipe.  Installation shall be in accordance with these specifications, AWWA C900, and ASTM D 2774.

Jointing shall comply with ASTM D 2657, Technique II-Butt Fusion.

- Butt-Fusion technician shall be properly trained and certified by the fusion machine manufacturer for the pipe sizes in the project, current within the past 12 months.

- Fusion machine shall be hydraulically operated and provide automated hydraulic pressure application at the proper temperature during the fusion process.

- Fusion machine shall be approved by pipe manufacturer and shall include an integral data logger, recording at a minimum the temperature, fusion pressure, time, and technician name.

- Data log sheets shall be provided to Engineer prior to installation of pipe in the trench and summary sheets provided daily.  Any data outside of specifications will be cause to reject the joint at any time.

- Each joint shall be visually inspected by the Engineer prior to installation in the trench.

- Each joint shall be indexed and identified by station and offset and correlated to data logger.

- All branch connections shall be made using factory-fabricated fittings.

- Joining different SDRs:  Fusing of unlike SDRs to one another will not be permitted.  Transition from unlike SDRs by means of mechanical joining systems or machined HDPE nipples where a thicker wall HDPE has been matched to the companion pipe wall.

The minimum allowable bending radius for HDPE pipe shall be in accordance with the pipe manufacturer’s recommendations.  If the alignment requires a shorter radius than allowable, a fitting shall be utilized to make the bend.

- DIP Pipe.  Installation shall be in accordance with these specifications and AWWA C600.  The conduit shall be kept clean during laying operations by plugging.  Except where necessary in making connections with other lines or as authorized by the Engineer, pipe shall be laid with the bells facing in the direction of laying.  The full length of each section of pipe shall rest solidly upon the pipe bed, with recesses excavated to accommodate bells, couplings, and joints.

Make push-on joints with the gaskets and lubricant specified for this type joint and assemble in accordance with the applicable requirements of AWWA C600 for joint assembly.  Make mechanical-joints with the gaskets, glands, bolts, and nuts specified for this type joint and assemble in accordance with the applicable requirements of AWWA C600 for joint assembly and the recommendations of Appendix A to AWWA C111. The Contractor has the option of using either mechanical or push-on joints for conduit.

Abrasion of the pipe lining shall be avoided.  Where any part of the lining is damaged, the repair shall be made by and at the Contractor’s expense in a satisfactory manner.

Deflections from a straight line or grade on force main piping, as required by vertical curves, horizontal curves, or offsets shall not exceed 80 percent of the manufacturer’s recommended maximum deflection.  If the alignment requires deflection in excess of the above limitations, the Contractor shall furnish special bends to provide angular deflections within the limits allowable.  Wherever possible, the Contractor shall achieve the desired deflection by taking advantage of reduced deflections over multiple joints. Short-radius curves and closures shall be formed by shorter lengths of conduit, bevels, or fabricated specials.

Conduit shall be so laid in the trench that after the line is completed the bottom of the conduit conforms accurately to the grades and alignment shown on the Plans.  A maximum 0.2-foot deviation from design alignment and elevation will be allowed.  Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed.  All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the conduit and not by blocking or wedging up.

Conduit that has the grade or joint disturbed after laying shall be taken up and re-laid. No conduit length less than 8 feet shall be incorporated into the system.

- Polyethylene Encasement.  The outside of all ductile iron conduit and fittings shall be encased with one layer of 8 mil thick polyethylene film conforming to AWWA C105/ANSI A21.5.  The polyethylene encasement shall be installed in strict conformance to the methods described in AWWA C105/ANSI A21.5 and the Ductile Iron Pipe Research Association’s “A Guide for the Installation of Ductile Iron Pipe.”

- Casing.  Install CPEP pipe casings in accordance with the requirements of Section 603 and the Plans.  Steel and HDPE pipe casings shall be installed in a similar manner as those specified in this section and in accordance with the Plans.  Boring or jacking of casings will not be allowed.  Seal ends of casings watertight.  Install casing spacers as shown on the Plans where sewer conduit is shown to be installed through casing.

- Detection Wire.  Install detection wire as shown on the Plans.  Install a cable tag on each wire end and mark tag with size of pipe and direction of the wire (i.e. “north 18”” to indicate the wire continues north from the wire end marking an 18” pipe).

- Sanitary Sewer Service Decommissioning.  Locate the service connection at the main, remove service pipe within 20 feet of any existing or proposed roadway edge and install a repair clamp on the main at the point of connection.

Service pipes beyond 20-feet of existing or proposed roadway may be removed completely or abandoned in place.  Abandonment in-place consists of emptying the line, placing a one foot (1’) thick concrete plug with vent tube at the higher end of the line, filling the pipe with a quantity of sand slurry equal to the total calculated volume from the newly installed plug to the point of injection, and placing a one foot concrete plug at the injection end of the pipe.  Work is typically started on the downhill end of the pipe.

In the event the pipeline to be abandoned is cracked or crushed, the Contractor shall excavate to the next joint of pipe and install the plug.  Crushed pipe sections or portions thereof are to be removed and disposed of by the contractor

Service decommissioning includes all associated trench excavation and backfill.

626-3.03 SANITARY SEWER MANHOLES.

- Manhole Construction.  Construct base using precast concrete base sections.  Cast inverts on precast concrete bases with a smooth-surfaced semi-circular bottom conforming to the inside contour of the adjacent sewer sections.  For changes in direction of the sewer and entering branches into the manhole, make a circular curve in the manhole invert of as large a radius as manhole size will permit.  For precast concrete construction, make joints between manhole sections with the gaskets specified for this purpose; install in accordance with the manufacturer’s instructions.  Trim gaskets on the inside of manhole to prevent gasket material from entering sewer lines.  Make joints between concrete manholes and HDPE pipes entering manholes with the resilient connectors specified for this purpose; install in accordance with the recommendations of the connector manufacturer.  Fill space between concrete manholes and ductile iron pipes entering manholes with cement mortar.  Pipes shall be centered on manhole and centered in hole.  Hole shall be no more than 8 inches larger diameter than the diameter of the pipe.  Where a new manhole is constructed on an existing line, remove existing pipe as necessary to construct the manhole and provide new pipe connected to the new manhole.  New pipe required for this purpose will not be measured or paid for separately, but shall be incidental to the manhole.  Cut pipe so that pipe ends are approximately flush with the interior face of manhole wall, but not protruding into the manhole.

- Connecting to Existing Manholes.  Pipe connections to existing manholes shall be made so that finish work will conform as nearly as practicable to the applicable requirements specified for new manholes, including all necessary concrete work, cutting, and shaping.  The connection shall be centered on the manhole.  Holes for the new pipe shall be of sufficient diameter to allow packing cement mortar around the entire periphery of the pipe but no more than 8 inches larger than the diameter of the pipe.  Cutting the manhole shall be done in a manner that will cause the least damage to the walls.

- Removal of Existing Manholes.  Contractor shall completely remove manhole and salvage manhole components that can be reused (manhole covers, frames, etc.) for delivery to sanitary sewer utility.  Prior to delivery, salvaged components shall be cleaned and prepared by removing grout and Ram Nek sealant.  Manhole excavation shall be backfilled with suitable, compacted, clean fill material that matches adjacent soils to the greatest extent possible.

Where applicable, the removal of existing manholes shall include work associated with pipe repair to connect to the existing system.  Repair pipe using materials specified under this section and as shown on the plans.

- Adjustment of Existing Manholes.  Adjust existing manholes by raising or lowering the frame or ring casting 12 inches or less, without reconstructing the cone section.  Set the manhole frame and cover approximately 3/8 inch below the finished pavement surface.  In walkways and bike paths, set the manhole frame flush with the surface.

- Reconstruction of Existing Manholes.  Reconstruct existing manholes by using one or more of the following methods:

- Bring the manhole frame and cover to grade if you remove the cone for lowering.

- Raise the manhole frame and cover more than 12 inches.

- Reconstruct a portion of the manhole with no change in line or grade.

- Tap one or more additional pipes into an existing manhole.

- Rotate the manhole cone to align the lid to the shoulder, lane line, or middle of driving lane.

- Rotate the manhole cone to align the inlet casting to the curb line.

- Align the access stairs by rotating the barrel sections or install new steps.

Reconstruct the manhole to the required elevation so that it conforms to plan details.  Complete this work according to the requirements for new construction.  Reuse material only if the Engineer approves.

626-3.04 FIELD QUALITY CONTROL.

- General.  The Engineer and Sewer Utility or its representative will jointly conduct field inspections and witness field tests specified in this section.  The Contractor shall perform field tests and provide labor, equipment, and incidentals required for testing.  Be able to produce evidence, when required, that each item of work has been constructed in accordance with the plans and specifications.

Perform a closed-circuit television (CCTV) inspection of the entire length of pipe installed.  Flush section to be tested with potable water and immediately pull camera through pipe.  Flushing shall be accomplished with a vactor truck with a water jetting tool or by adding clean water to the upslope end of the section being flushed.  The Contractor may use City water for this purpose.  Flow shall continue for approximately 5 minutes and until all objects have been flushed from the pipe.  Prior to cleaning, a temporary 1-inch mesh screen strainer shall be installed in the first downstream manhole beyond the section being tested.  The strainer shall be constructed and installed so that all of the flow will pass through the screen.  The screen shall be frequently cleaned by the Contractor so that no stones, debris, etc. collect on the strainer.

If puddles in excess of ¼ inch deep are identified, replace the section that is not true to line and grade and retest.  The height of the fusion-joint bead on HDPE pipe will be subtracted from the puddle depth, where the bead influences the puddles.  Record all camera inspections and provide Engineer and Sewer Utility with copies on DVD or USB flash drive with stationing indicated continuously.  If CCTV inspection indicates the need for additional cleaning of the pipe, the Contractor shall conduct additional flushing until the Engineer is assured of adequate pipe cleaning.

The Contractor shall notify the Engineer and Sewer Utility 48 hours (2 working days) prior to cleaning and testing and shall notify the Engineer 2 hours in advance of the scheduled time if the test is to be canceled.  In the event the Engineer has not been notified of cancellation and the Contractor is not prepared for the test as scheduled, the Contractor shall reimburse the Engineer for all expenses incurred.  These will include, but not be limited to, salaries, transportation, and administrative costs.

- Tests for HDPE Gravity Lines

Test lines for leakage by Monitored Make-up Water Test.  Prior to testing for leakage, backfill trench up to at least 3 feet above pipe.  Joints may be left uncovered to permit inspection.  When leakage exceeds the allowable amount specified, make satisfactory correction and retest pipeline section in the same manner.  Correct visible leaks regardless of leakage test results.

Monitored Make-up Water Test Procedure:  The test procedure consists of initial expansion and test phases.  During the initial expansion phase, the test section is pressurized to 6 feet of head at the upstream end of the test section and sufficient make-up water is added each hour for 3 additional hours to return to test pressure.  After the initial expansion and absorption is complete, the test phase begins.  The test phase is for 2 hours, during which make-up water is added and measured to maintain to test pressure.  During this period, the measured loss shall not exceed 3.3 gallons per 100 feet of pipe for 16” diameter pipe and 8.9 gallons per 100 feet of pipe for 24” diameter pipe.  Maximum test length is 1000 feet.

Deflection Testing:  Perform a deflection test on entire length of installed HDPE pipeline on completion of work adjacent to and over the pipeline, including leakage tests, backfilling, placement of fill, grading, paving, concreting, and any other superimposed loads determined in accordance with ASTM D 2412.  Deflection of pipe in the installed pipeline under external loads shall not exceed 7.0 percent of the average inside diameter of pipe.  Determine whether the allowable deflection has been exceeded by use of a pull-through device or a deflection measuring device.

Pull-through device shall be a spherical, spheroidal, or elliptical ball, a cylinder, or circular sections fused to a common shaft.  Circular sections shall be so spaced on the shaft that distance from external faces of front and back sections will equal or exceed diameter of the circular section.  Pull-through device may also be of a design promulgated by the Uni-Bell Plastic Pipe Association, provided the device meets the applicable requirements specified in this paragraph, including those for diameter of the device, and that the mandrel has a minimum of 9 arms.  Ball, cylinder, or circular sections shall conform to the following:

- A diameter, or minor diameter as applicable, of 92.5 percent of the average inside diameter of the pipe; tolerance of plus 0.5 percent will be permitted.

- Homogeneous material throughout, shall have a density greater than 1.0 as related to water at 39.2 degrees F, and shall have a surface Brinell hardness of not less than 150.

- Center bored and through-bolted with a ¼ inch minimum diameter steel shaft having a yield strength of not less than 70,000 psi, with eyes or loops at each end for attaching pulling cables.

- Each eye or loop shall be suitably backed with a flange or heavy washer such that a pull exerted on opposite end of shaft will produce compression throughout remote end.

Pull-through device procedure:  Pass the pull-through device through each run of pipe, either by pulling it through or flushing it through with water.  If the device fails to pass freely through a pipe run, replace pipe which has the excessive deflection and completely retest in same manner and under same conditions.

Deflection measuring device shall be sensitive to 1.0 percent of the diameter of the pipe being tested and shall be accurate to 1.0 percent of the indicated dimension.  Deflection measuring device shall be approved prior to use.

Deflection measuring device procedure:  Measure deflections through each run of installed pipe.  If deflection readings in excess of 7.0 percent of average inside diameter of pipe are obtained, retest pipe by a run from the opposite direction.  If retest continues to show a deflection in excess of 7.0 percent of average inside diameter of pipe, replace pipe which has excessive deflection and completely retest in same manner and under same conditions.  Beads resulting from butt-fusion procedure shall not be included in computation of average diameter.

HDPE Destructive Testing:  Contractor shall provide 2 fusion-joint samples per day for destructive testing; the first joint of the day and one joint randomly selected by the Engineer.  Contractor shall provide all labor and equipment to remove the joints.  Joints will be tested by the “bend-back” method.  Any cracks or evidence of separation will be cause for rejection of all joints completed since the last successful test.  Rejected joints shall be cut out and replaced.

- Tests for Ductile Iron Gravity Lines

Visual Inspection:  Check each straight run of ductile iron pipeline for gross deficiencies by holding a light in a manhole; it shall show a practically full circle of light through the pipeline when viewed from the adjoining end of line.  Replace pipe that is not true to line and grade and retest.

Leakage Tests:  Test lines for leakage by Monitored Make-up Water Test.  Prior to testing for leakage, backfill trench up to at least 3 feet above pipe.  Joints may be left uncovered to permit inspection.  When leakage exceeds the allowable amount specified, make satisfactory correction and retest pipeline section in the same manner.  Correct visible leaks regardless of leakage test results.

Monitored Make-up Water Test:  The test procedure consists of initial absorption and test phases.  During the initial absorption phase, the test section is pressurized to a minimum 6 feet of head at the upstream end of the test section and maintained for a period of 4 hours, at which time it is assumed that all absorption is complete.  After the absorption is complete, the test phase begins.  The test phase is for one hour, during which make-up water is added and measured to maintain to test pressure.  During this period, the measured loss shall not exceed 3.4 gallons per 100 feet of pipe for 36” diameter pipe.  Maximum test length is 1000 feet.

626-3.05 AS-BUILT PLANS AND WORKING DRAWINGS.

A complete and accurately dimensioned record of all deviations, deletions, additional and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as accurately installed.  This as-built information shall be recorded on a print of the plans affected and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor and shall be made available to the Engineer and Sewer Utility upon request.  Conduit and appurtenances shall be referenced by stationing showing design line and grade, and as-built line and grade.

When the sewer system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer within 14 days following completion of testing.

626-3.06 CONTRACTOR’S WARRANTY

The Contractor shall warranty all materials and workmanship for one (1) year from the Final Acceptance Date unless otherwise specified.  This warranty shall require the Contractor to remedy promptly, without cost to the Department, any and all defects in material and workmanship including any consequential damages resulting from defective materials or workmanship.

All Warranty Work shall be subject to the same Contract provisions, including materials, quality of work, authority of the Engineer and inspection, as provided for in the original Work. All warranty Work shall be at the sole expense of the Contractor.  All materials and workmanship directly or indirectly involved in repairs or replacements under this subsection shall carry an extended warranty of not less than one (1) year from the date of the Engineer’s written acceptance of the repair or replacement Work, or through the warranty period for the original project Work, whichever is longer.

If the defect, in the opinion of the Engineer, is of such nature as to demand immediate repair, the Department shall have the right to take corrective action and the cost thereof shall be borne by the Contractor.

At the completion of the Warranty, the Contractor and the Department shall conduct a pre-Warranty Inspection.  All deficiencies indicated by the pre-Warranty Inspection shall be listed and promptly furnished to the Contractor for action. When all listed deficiencies have been corrected, the Contractor shall notify the Engineer and a final Warranty Inspection will be performed.  When the Warranty Inspection verifies correction of any listed deficiencies, the Engineer shall issue a Certificate of Completion.

626-4.01 METHOD OF MEASUREMENT.

Measurement for Sewer Conduit will be made from center of manhole to center of manhole.  No deduction will be made for the space occupied by manholes.

Manholes will be measured per each, complete in place.

Removal of Manholes shall be measured per each manhole removed, including reconnection of sewer line, if applicable.

Sanitary Sewer Pipe Casings shall be measured by the linear foot installed.

626-5.01 BASIS OF PAYMENT.

Branch connections and service fittings are subsidiary

Price for Sewer Conduit shall include trench excavation, bedding, and backfill, compaction, disposal of surplus excavated material, fittings, polyethylene encasement, detection wire, marking tape, testing, connections to new manholes, and abandonment or removal of existing conduit.

Price for Manholes shall include excavation, bedding, backfill, compaction, disposal of surplus excavated materials, castings, grouting, testing, and connection of pipe to manholes.

Price for Sanitary Sewer Pipe Casings shall include trench excavation, bedding, backfill, compaction, disposal of surplus excavated materials, fittings, testing, connections to existing, and staking/locating of casings ends of future use.

Price for Removal of Existing Manhole shall include all excavation, bedding, backfill, compaction, disposal of materials, and disposal of surplus excavated materials.  Conduit and fittings required to reconnect existing sanitary sewer system are subsidiary.

Price for Decommission Sewer Service shall include all excavation, fittings, bedding, backfill, compaction, and material disposal required to fully decommission the sewer service.

Preparation and submittal of as-build plans is subsidiary.

Repair of existing improvements on private property and repair of existing utilities damaged by the Contractor will not be paid for directly but will be considered subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

626(1)	Sanitary Sewer Conduit, ___-Inch, Type	Linear Foot

626(2)	Sewer Service Connection, ___-Inch	Each

626(2A)	Decommission Sewer Service	Each

626(3)	Sanitary Sewer Manhole, Type A Horseshoe Manhole	Each

626(4-24)	Sanitary Sewer Pipe Casing, 24-inch, Type S CPEP	Linear Foot

626(4-30)	Sanitary Sewer Pipe Casing, 30-inch, Type S CPEP	Linear Foot

626(4-36)	Sanitary Sewer Pipe Casing, 36-inch, Type S CPEP	Linear Foot

626(5)	Remove Sanitary Sewer Manhole	Each

626(6)	Adjust Existing Sanitary Sewer Manhole	Each

626(7)	Decommission Sewer Service	Each

CFHWY00317

Special Provisions

Delete Section 627 and replace with the following:

SECTION 627
WATER SYSTEM

627-1.01 DESCRIPTION.  For purposes of these specifications, Water Utility shall mean the water system operated by the City of Palmer.  Furnish and place water main improvements and replacements including all appurtenances, as shown on the Plans or as specified in this Section.  Remove salvage and reinstall or abandon existing fire hydrants, valve boxes, and water meters, as specified.

The term “water conduit” refers to all conduits used for water mains.  The term “service pipe refers to service lines.

    - MATERIALS.

All pipe and appurtenances in contact with potable water shall comply with ANSI/NSF Standard 61, latest edition, as approved by National Sanitation Foundation (NSF) Underwriter Laboratories or an equivalent organization that evaluates products using ANSI/NSF Standard 61.

Per 18 AAC 80.500, except for leaded joints necessary to repair cast iron pipes, lead free pipe, solder or flux is required in the installation or repair of (1) a public water system or (2) plumbing in a residential or nonresidential facility that provides water for human consumption and is connected to a public water system.

- Class "C" Pipe Bedding Material.  Water main shall be bedded in Class “C” bedding material conforming to the following:

| Sieve Size | Cumulative percent Passing by Weight |
| --- | --- |
| 2-inch | 100 |
| 1-inch | 40-100 |
| No. 4 | 20-75 |
| No. 10 | 12-60 |
| No. 40 | 2-30 |
| No. 200 | 0-6 |

In addition to the bedding limits listed above, the fraction of material passing the No. 200 sieve shall not be greater than 20% of that fraction passing the No. 4 sieve.

- Sand Slurry.  Sand slurry consists of a mixture of water and sand with an approximate ration of seven (7) gallons of water per cubic foot of sand.  Sand may consist of native material with a particle size distribution such that one hundred percent (100%) of the material passes the No. 4 U.S. Standard Sieve and contains no lumps, frozen material, organic matter, or other deleterious material.

- High Density Polyethylene (HDPE) Pipe.  HDPE pipe and fittings shall be manufactured in accordance with AWWA C906.  HDPE shall be manufactured from PE 4710 polyethylene compounds that meet or exceed ASTM D3350 Cell Classification 445474 HDPE pipe and fitting material compound shall contain color and ultraviolet (UV) stabilizer meeting or exceeding the requirements of Code C per ASTM D3350.  Electrofusion fittings will not be allowed except where shown on the plans.

In addition, materials used for the manufacture of the HDPE pipe and fittings shall meet the following physical property requirements:

| PROPERTY | UNIT | Test Method(1) | Nominal Value |
| --- | --- | --- | --- |
| Material designation | — | PPI/ASTM | PE4710 |
| Cell classification |  | D3350 | 445474C |
| Further, the material must have a |  |  |  |
| Density | gm/cc | D1505 | 0.947-.955 |
| Melt index | gm/10min. | D1238 | <0.15 |
| Flexural modulus | psi | D790 | >110,000-160,000 |
| Tensile strength @ yield | psi | D638 | >3,600 |
| Slow Crack Growth |  |  |  |
| ESCR | Hrs. in 100% igepal | D1693 | >5,000 |
| PENT | hours | F1473 | >500 |
| HDB @ 73.4°F | psi | D2837 | 1600 |
| @ 140° F | psi | D2837 | 1000 |
| UV Stabilizer | %C | D1603 | 2 to 2.5% |

(1) Test procedures are ASTM unless otherwise specified. (PPI = Plastics Pipe Institute, and GPC = Gel Permeation Chromatography)

Pipe and fittings shall be manufactured from material meeting the requirements of the above table.  The manufacturer shall certify that samples of the manufacturer's production product have been tested in-house in accordance with ASTM D2837, and validated in accordance with the latest revision of PPI TR-4.

- Manufacturer shall comply with AWWA Standard C901 (1/2" through 3") and C906 (4" through 63").  The material shall be listed by the Plastics Pipe Institute (PPI) a division of The Society of the Plastics Industry in PPI TR-4.  The pipe material shall have a Hydrostatic Design Basis of 1600 psi at 73.4° F and 800 psi at 140°F.  The PPI listing shall be in the name of the pipe manufacturer and testing and validation of samples of the pipe manufacturer’s product shall be based upon ASTM D2837 and PPI TR-3.

- .	Reference Standards: AWWA, C-901, AWWA C-906, ASTM D2683, ASTM D3261, ASTM D3350, PPI TR-3, PPI TR-4.

Both pipe and fittings shall carry the same pressure rating.  All fittings shall be pressure rated to match the system piping to which they are joined.  At the point of fusion, the outside diameter and minimum wall thickness of the fitting shall meet the outside diameter and minimum wall thickness specifications of ASTM F714 for the same size of pipe.  All fittings shall be properly rated according to manufacturer's written recommendations, and clearly labeled on the fitting as such.  Manufacturer shall have a written specification for all standard fittings which establishes Quality Control criteria and tolerances.  The manufacturer of the pipe shall be the same manufacturer of the fabricated fittings and other fabrications.  The manufacturer shall certify that the materials used to manufacture pipe and fittings meet the requirements of this specification.

Pipe supplied shall have a nominal IPS (Iron Pipe Size) outside diameter.  The Standard Dimension Ration (SDR) and pressure rating of the pipe in accordance with ASTM 2837 at 73 degrees F and a service rating of 0.5 shall be 160 psi for SDR 11 and 100 psi for SDR 17.

The pipe shall have product traceability.  This shall be accomplished by the inclusion of a product code into the printline of all products.  This shall notate the manufacturer, the date of manufacture, the lot and supplier of raw material, the location of manufacture, and the production shift on which the product was produced.  The printline shall also include other markings as required by AWWA C901 or C906 and shall be made permanent by heat indentation.  The printline shall be easily readable against the black pipe.

Pipe and fittings shall be butt fusible according to the manufacturer recommended procedures.  The socket or sidewall fittings shall also be to manufacturer's recommended procedures.

Internal bead resulting from fusion welding shall be removed from all fabricated bends.

Provide a copy of the manufacturer’s PPI certification, a statement that the raw materials used to manufacture the pipe meet the cell classification requirements, and a copy of the manufacturer’s NSF 61 certification.

- HDPE Pipe Jointing.  Pipe joints shall be in accordance with PPI TR-33 Generic Butt Fusion Procedures.  Electrofusion couplings may be used only where the use of butt fusion in not practicable or where indicated.  Electrofusion fittings shall comply with ASTM F1055.  All fittings shall have pressure class ratings not less than the pressure class rating of the pipe to which they are joined.

- Ductile Iron Pipe (DIP)  Ductile Iron pipe must conform to the requirements of AWWA C151, with cement mortar lining conforming to the requirements of AWWA C104ANSI A24.1.  Class 52 pipe shall be used for all water pipe unless otherwise specified.  All ductile iron pipe and fittings are to be encased in one layer of 8 mil polyethylene encasement.

- Fittings and Gaskets.  Fittings, including pipe caps, are to have exterior and interior surfaces coated with fusion bonded epoxy in accordance with AWWA C116/A21.13-09.

Rubber gaskets for ductile iron pipe joints shall conform to AWWA C111.  Fittings shall be a minimum of 250 pounds pressure rating, mechanical joint or bell, lined or unlined, either cast iron or ductile iron, unless otherwise required by the contract documents.  All fittings must conform to the requirements of AWWA C110 ANSI A21.10 or C153 A21.53-06.

Fittings shall utilize carbon steel or stainless steel nuts and bolts, fittings with carbon steel bolts and nuts must conform to the dimensional and material standards as outlined in AWWA C111 and C115 and be factory-coated with a blue fluoropolymer coating system.  Fittings with stainless steel bolts and nuts must conform to the dimensional standards as outlined in AWWA C111 and C115 and the material standards in ASTM F593 and F594 with a minimum tensile strength of 75,000 psi.  Bolts and nuts must have imprinted markings indicating the material and grade of the metal used in fabrication.  Where bolts and nuts for fittings cannot be covered by the above references then the contractor must submit to the engineer for approval corrosion resistant bolts and nuts and supported reasons for the request of an alternate to this standard.

Per 18 AAC 80.500, except for leaded joints necessary to repair cast iron pipes, lead-free pipe, solder or flux is required in the installation or repair of (1) a public water system or (2) plumbing in a residential or nonresidential facility that provides water for human consumption and is connected to a public water system.

- End of Pipe Carsonite Marker.  End of pipe marker posts shall meet the requirements of Subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5-inch by 6-foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9-inches.

- Polyethylene Encasement.  Where required material shall conform to Subsection 707-2.05

- Copper Service Pipe.  Copper Service Pipe must be soft-drawn Type K, one inch (1”) minimum inner diameter, seamless, annealed, copper pipe, suitable for use as underground service water connections for general plumbing purposes and ASTM B88 compliant.

- Continuity Straps.  Continuity straps shall be stranded No.2 AWG copper wire with High Molecular Weight Polyethylene (HMWPE) insulation suitable for direct burial.

- Restrained Joints.  Where specified on the Drawings and/or required in these Specifications, water distribution piping must be installed with thrust restraint systems.  Allowed ductile iron thrust restraint systems are EBBA Iron MEGALUG, Romac, RomaGrip, Romac GripRing, Romac RFCA, Foster Adaptor, U.S. Pipe Field LOK 350 Gasket, Ford Uni-Flange Series 1400, or approved equal thrust restraint system.  Tie back rods and/or tie back rod and shackle assemblies will not be acceptable as restrained joints or restraining system for fittings, piping, deflection points, or inside casings.

Contractor shall provide manufacturer submittals for each type of thrust restraint to be used.  Such submittals shall include thrust restraint calculations and other appropriate data.

- Thrust Blocks.  Concrete for thrust blocks shall be cast-in-place or pre-cast concrete with the minimum base area as shown in the plans shall be installed where pipeline terminates, branches or changes alignment utilizing a fitting except 11-1/4° bends, including tees for hydrant lines.  Thrust blocks shall be placed against undisturbed soil or Select Material, Type A, that has previously been compacted to 95% maximum density.  Concrete for thrust blocks shall be meet Class A Requirements described in Section 501-2.02.  All pipe and fittings exposed to concrete shall be double wrapped with 8 mil polyethylene film prior to placement of the concrete.

- Gate Valves.  Gate valves shall be iron body, fully bronze mounted, double disc, parallel or resilient seat valves manufactured in accordance with AWWA C509 “Resilient-Sealed Gate Valves for Water Supply Service” or AWWA C515 “Reduced-Wall, Resilient-Seated Gate Valves for Water Supply Service.”

Gate valve bonnet bolts shall be Type 316 stainless steel with a minimum tensile strength of 75,000 psi and shall conform to ASTM F593 and F594.  All bolts shall be stamped with the grade marking on the head of the bolt, and shall be “T-316”, “316” or “F593”.

All valves shall be non-rising stem type with an O-ring seal and a two-inch square operating nut.  Valves shall open counter-clockwise and have mechanical joint ends.

- Valve Boxes.  Valve boxes shall be cast iron sliding, adjustable height type with round or oval bottom hood sections to fit over the top of the valve. The top section shall be recessed to receive a close fitting "eared" lid with the word "water" cast into it. Internal diameter of the smallest section shall not be less than five (5) inches.  Minimum thickness of the metal shall not be less than five-sixteenth (5/16) inch.  Castings shall be smooth and the workmanship shall be acceptable to the Engineer.

Valve boxes shall be of sufficient length for the pipe cover depth on the profile drawings and in accordance with the details.

- Rubber Centering Ring.  A rubber compound sleeve placed on a valve to align the valve box bottom section with the valve top, such as Valve Box Adaptor II or equal.  The centering ring must confirm to the shape of the valve and valve box to seal out soil.

- Fire Hydrants.  Fire hydrants shall conform to the requirements of ANSI/AWWA C502 for Dry Barrel Fire Hydrants.  Fire hydrants shall be Mueller Centurian or equal.

a.	All fire hydrants shall be supplied with 5-1/4-inch main valve opening.

b.	All single pumper hydrants shall be furnished with a 6-inch ANSI Class 125 standard mechanical joint end with restrained joint.

c.	All connections, including hydrant leg pipe joints, shall be restrained mechanical joints unless otherwise indicated in the Contract Documents.

d.	Fire hydrants shall be single-pumper furnished with two (2) 1-1/2-inch hose connections and one (1) 5-inch STORZ pumper connection.

e.	Unless otherwise required by the Contract Documents, all hydrants shall be furnished with a barrel length that will allow a minimum of 10 feet of bury.

f.	The main valves shall be of the compression type, where water pressure holds the main valve closed permitting easy maintenance or repair of the entire barrel assembly from above the ground without the need of a water shut-off.

g.	All fire hydrants shall be furnished with a breakaway flange which allows both barrel and stem to break clean upon impact from any angle.  Traffic flange design must be such that repair and replacement can be accomplished above ground.

h.	Painting and coating shall be in accordance with cited AWWA specifications. The hydrant section from the traffic flange to the top of the operating nut shall be painted "Caterpillar Yellow".

i.	Operating and nozzle nuts shall be pentagon shaped with 1-1/2-inch point to flat measurements.

j.	Hose nozzle threading shall be in conformance with NFPA #194 for National (America) Standard Fire Hose Coupling Screw Threads.

k.	All working parts shall be bronze or noncorrosive metal in accordance with the requirements of ANSI/AWWA C502.

l.	All hydrants shall be left-hand opening (counter-clockwise).

m.	All hydrants shall be free draining (drain plugs removed and delivered to the Engineer), unless hydrant is installed within two feet of groundwater or directed otherwise by Engineer.

n.	The operating nut of the hydrant is to be a minimum of twenty-eight inches (28”) above the traffic breakaway flange.  The traffic breakaway flange is to be between three inches (3”) to nine inches (9”) above adjacent grades.

- Water Service Key Box, Valve and Valve Box.  Key boxes are to be telescoping, furnished with a lid, have an arch pattern base and is to be constructed of cast or ductile iron.  The operating rod and connection pin are to be constructed of black iron or stainless steel alloy type 304 or 316.  The connection pin is to be a minimum of 3/16” by two inches (2”) long.  Mueller 10306 or 10310 or equal.

The curb stop shall be brass, line size, quarter turn, closed bottom, flare connections, with drain.  Mueller Mark II Oriseal H-15214 or approved equal.

The corporation stop shall be line size, quarter turn, IPT by copper flare.  Mueller H 15025 or approved equal.

Water service marker posts shall meet the requirements of Subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5-inch by 6-foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9-inches

- Live Tap Tapping Saddle.  Where plans show a live tap connection to the existing main, provide Romac STS, Stainless Steel Tapping Sleeve, or approved equal.

- Solid Copper Retainer Disc.  Muller Co. Catalog No H-15535 or Equal.

- Casing.  Casing shall be size, type, and thickness as shown on the plans and specified herein.  Corrugated Polyethylene Pipe (CPEP) used for casings shall meet the requirements of Subsection 706-2.07.  HDPE pipe casings shall meet the requirements of this section.  Steel pipe casings shall be smooth walled with minimum yield strength of 35,000 psi without protective coating with a minimum wall thickness per the plans.  End seals shall be watertight, segmented elastomeric end seals or, for an empty casing for future use, a suitable, slip-over pipe cap may be used.  Casing spacers shall be as specified on the Plans.

- Insulated Pipe:  Insulated Pipe shall consist of a three component assembly as follows:

- Inner core (fluid pipe) of DIP as specified in this subsection

- Insulation of Urethane foam

- Outer jacket of minimum 175 mil thickness HDPE pipe except 80 mil polyuria jacket for fitting and joint half shell kits.

Insulation shall be low-density, rigid, closed cell urethane foam with a nominal thickness as shown on the Drawings.  Urethane foam shall exhibit the following properties and characteristics meeting ASTM D2341 cell classification 550674970034 or shall comply with a new ASTM cell classification that exceeds these properties:

| Maximum K-factor (ASTM C177) | 0.155 btu-in/hr-ft2-°F |
| --- | --- |
| Core Density Range (ASTM D1622) | 4.0 lbs/ft3 minimum |
| Minimum Compressive Strength (ASTM D1621) (Foam sample to be tested parallel and perpendicular to the axis to the pipe) | 35 psi |
| Minimum Closed Cell Content (ASTM D2856) | 90% (porosity) |
| Maximum Water Absorption (ASTM D2842) | 0.05 psf (22.7 g/ft2) |
| Maximum Water Vapor Permeability (ASTM C355) | 5.0 psf (2,267.96 g/ft2) |
| Dimensional Stability (ASTM D2126, Maximum Linear Change) | 1% (at -20 °F) and 3% (at +100 °F) |

Exposed urethane foam faces at pipe and fitting ends shall be coated to protect against physical abuse, UV attach during shipping and storage, and against water intrusion in service.  The coating shall be suitable for direct application over urethane foam with no deleterious effects to the foam or coating.  The coating shall be formulated for long-term service and retained flexibility over extended periods of exposure to sunlight, harsh weather, and saltwater spray.  The strength of the adhesive bond of the coating of the foam shall be greater than the tensile strength of the coating.  In the event the coating is nicked or an edge is rolled up in handling, the coating that has been dislodged shall tear free from the coating still adhering to the foam rather than pull the balance of the coating off as a sheet.  The exposed ends of the pipe shall have the wax removed in order to allow the coating to adhere to the pipe.  The coating shall be applied and cured in accordance with the manufacturer's recommendations and good practice.  The coating material shall be NoKorode "Lion Seal" or approved equal and exhibit the following properties:

| Minimum Service Temperature Range | -50 to +150 °F |
| --- | --- |
| Maximum Water Vapor Permeance (ASTM E398 or E96) | 1.0 perm |
| Dry Film Thickness Range (actual dry film thickness) | 15 to 63 mils |

After coating, the plane of the exposed foam face shall be perpendicular to the centerline axis of the outer jacket.

Inner pipe shall extend beyond the outer pipe sufficient to allow fusion welding to the adjacent pipe.

Insulated pipe shall be fabricated such that the offset of the centerline of the outer jacket and inner core pipe is not more than ¼-inch at the pipe ends and 3/8-inch along the remainder of the pipe.

The foaming operation shall be designed and operated in a manner to result in void-free insulation.  Foam shall be placed into the pipe by a single injection application.

The inner core pipe shall be bonded to the urethane foam insulation in such a manner as to produce foam-to-foam separation when a sample is tested in shear.

CONSTRUCTION REQUIREMENTS

627-3.01 GENERAL.

- Pre-Construction Inspection.  The Contractor shall coordinate, and participate in, a pre and post construction inspection with the Engineer and Water Utility, of all water facilities located within the project limits. The pre-construction inspection shall be conducted before construction work begins and the post-construction inspection after construction has been completed. During these inspections document the location, condition, and operation of each facility, making specific note of any deficiencies. Copies of the inspection reports shall be provided to both the Engineer and Water Utility.

The Contractor forfeits all right to assert pre-existing damage if the Contractor fails to participate in the inspections.

Any deficiencies in the water system found during the pre-construction inspection will be the Water Utility’s responsibility to correct. Replace additional facility items as directed by the Engineer.

The Contractor shall coordinate with the Water Utility to complete the following work:

- Perform a test shutdown of each water main prior to beginning waterline/hydrant work.  Allow three (3) working days to complete the test.

- Perform shutdown, and after waterline/hydrant work is complete, re-pressurize the necessary water mains to facilitate the Contractor’s work.  Allow one (1) working day to shutdown each main, and one (1) working day to re-pressurize the system.

- Permanent Water System.  Prior to commencement of work to install the water system, the Contractor shall submit to the Engineer for review, a detailed plan for the installation of the new water systems and for removal/abandonment of existing water systems that are to be removed or abandoned.  The plan shall be of sufficient detail to clearly indicate the proposed work sequence and schedules, as well as identify existing valves to be used to isolate the system during construction.  Valve and hydrant maps for the entire City of Palmer water system are available at the Public Works Office.

The Water Utility, through the Engineer, reserves the right to suspend the permanent water system installation at any time if the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

If construction or excavation require the removal of any existing privately owned facilities or improvements within the provided temporary construction easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at the Contractor’s cost.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed two weeks.  The contractor shall restore property disturbed by contract activity to the preconstruction condition.

Consult the Plans for estimated locations of existing sewers, water mains, and other utilities near the construction.  Use this data for information only.  The Department and Water Utility do not guarantee their accuracy.  Confirm and mark the exact locations of all existing utilities before starting work or so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled.

Excavate, bore, or probe by hand ahead of your work where necessary to determine the exact location of underground conduit or other features that might interfere with construction.  Support and protect conduits or other services that cross the trench.  Immediately repair or replace any existing utilities that you break or damage.  Immediately replace any existing valves, valve boxes, or water lines that you break or damage.

At least 48 hours prior to removing or disrupting service to fire hydrants, the Contractor shall contact Palmer Fire & Rescue, Chief McNutt at 745-3854 and the Water Utility.  Any hydrant taken out of service shall be immediately and securely wrapped in Water Utility-supplied plastic to indicate its status.

The Contractor shall notify the Water Utility, Greg Wickham at 863-0742, 72 hours prior to an interruption of their water service. Additionally, the Contractor shall notify all affected property owners and the Engineer, 48 hours prior to interruption of the Water Utility's water service.  It shall be the Contractor’s responsibility to coordinate “turn-off” and “turn on” with the Engineer and Water Utility and additionally, provide temporary service to all property owners with disrupted water service if the interruption exceeds four (4) hours in duration.  The Contractor shall draft a temporary service plan and have it reviewed and approved by ADEC prior to shutdown.  The temporary service plan shall address the following criteria:

- 25 psi minimum, 60 psi maximum (or existing system pressure, whichever is greater) delivery pressure measured at the connection to the residence.

- 5 gallons per minute flow rate at the above delivery pressure measured at the connection to the structure.

- Potable water system and water quality shall conform to 18 AAC 80 Alaska Drinking Water Standards.

- All services to structures shall be valved to allow individual control of service.

- Materials shall conform to requirements of this section, ANSI/NSF 61 (latest addition).  All equipment used must be specifically designed and properly disinfected for the storage, handling, and delivery of potable water.

The Contractor shall provide any necessary fittings, valves, or appurtenances necessary in order to maintain the water distribution system.  Any costs involved in service changeovers shall be subsidiary.  The Contractor shall be responsible for all damages incidental to interruption of service that may be due to his operations.

In addition to restrained joints, pre-cast concrete thrust blocks with the minimum base area as shown in the details shall be installed where pipeline terminates, branches or changes alignment utilizing a fitting except 11-1/4° bends, including hydrant lines.

Connect to existing water lines and structures, avoiding contamination of water in lines that are in use.

Water mains shall be constructed to meet all separation requirements of 18 AAC 80.020.  Where new water mains cross existing sanitary sewer or storm drain pipes, new water main shall be installed a minimum of 18 inches vertically from the sanitary sewer or storm drain pipe, water pipe joints shall be a minimum of 9 feet horizontally from sanitary sewer or storm drain pipes, and water pipe shall be insulated pipe.

- Trench Excavation and Backfill.  Excavation and backfill shall be to the width and depth as shown on the drawings.  Trench width at or below the top of the pipe shall be of a width that will allow compaction equipment to be utilized at the sides of the pipe.

Contractor shall erect and maintain barricades to prevent access around all excavations left open at the end of the workday.  Contractor shall provide and maintain adequate barricades to ensure public safety at all times during the prosecution of the Work.

Contractor shall perform all excavation of every material encountered.  Excavated material shall be placed in an orderly manner and at a distance from the trench conforming to all State and/or Federal safety codes.  Excavated material meeting the requirements of Select Material shall be stockpiled separately and reused in the Work.

Not more than 200 feet of trench shall be open in advance of the pipe installation unless authorization, in writing, is obtained from the Engineer.  The trench shall not be left open at the end of the workday, unless otherwise approved by the Engineer.

All bedding material and backfill material shall be placed in uniform layers of not more than 12 inches in depth and compacted in accordance with Subsection 203-3.04.  In no case shall bedding material be placed above the springline of the pipe in a single lift.  Compaction by hydraulic jetting or flooding will not be permitted unless approved in writing.

When existing conduits or utilities, which are not scheduled for removal or abandonment, are encountered in the excavation, they shall be adequately supported and protected from damage.

All sheeting and bracing used in excavation shall be removed by the Contractor following the completion of the work.

- Abandon Existing Pipe.  Existing pipe shown to be abandoned shall be abandoned-in-place as an incidental item of construction.  Pipe abandoned-in-place shall be slurried and have the ends capped.  In those areas that the presence of existing pipe causes a conflict with new or existing utilities or facilities, the pipe may be removed as an incidental item of construction.  All abandoned materials removed and not reused shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.

- Remove Existing Pipe.  Pipe and appurtenances called out on the plans to be removed shall be an incidental item of construction.  All removed materials shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.

- Rights In and Use of Materials Found on the Work Site.  Unless specifically addressed otherwise in these special provisions, all existing water valves, tees, bends, and conduit (including ductile iron pipe) removed but not reinstalled, and declared "salvageable materials" shall become the property of the Contractor.

- Final Acceptance.  The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a pre-final inspection of the project. This inspection will be performed in the presence of the Engineer, the Water Utility, and the Contractor.  Copies of a list of deficiencies, if any, indicated by this inspection will be furnished to the Contractor for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and an acceptance inspection will be performed.

627-3.02 WATER CONDUIT.

- General.  Installation shall be in accordance with these specifications and AWWA C600.  The interior of the conduit and accessories shall be thoroughly cleaned of foreign matter before being lowered into the trench.  The conduit shall be kept clean during laying operations by plugging.  Lay conduit to the grades and lines shown on the Plans.  However, at a sufficient distance prior to encountering a known obstacle or tying into an existing conduit, the Contractor shall expose and verify the exact location of the obstacle or conduit so proper alignment and/or grade may be determined before the conduit sections are laid in the trench and backfilled. The costs incurred for removal and realignment of backfilled conduit sections due to improper verification methods shall be borne by the Contractor.

Keep trenches dry to avoid laying conduit in water.  Do not lay conduit when weather or trench conditions are unsuitable.  Keep water away from new joints, until the joint materials have hardened.

Use methods to cut conduit that will produce tight joints and will not damage the conduit.

Inspect conduit before lowering it into the trench.  Replace defective, damaged or unsound conduit.

Place conduit bedding to conform to plan details.  Place bedding, if required, to give conduit a uniform bearing for its full length.  Do not permit couplings to rest on solid or original trench bottoms.

Conduit shall be laid in the trench so that after the line is completed, the bottom of the conduit conforms accurately to the grades and alignment shown on the Plans.  A maximum 0.2-foot deviation from design alignment and elevation will be allowed.  Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed.  All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the conduit and not by blocking or wedging up.

The Contractor shall have survey instruments, such as transit and level, for transferring alignment and grades from offset hubs.  The Contractor shall provide a qualified person to use such instruments and who shall have the responsibility of placing and maintaining such construction guides. The Contractor shall provide to the Engineer a copy of the surveyor's record notes for the newly installed conduit and appurtenances. The practice of placing backfill over a section of conduit to provide a platform for the instruments shall be subject to the approval of the Engineer.

A minimum of 10-foot horizontal separation shall be maintained between water and sanitary sewer mains and services.  Locations having less than 10-foot minimum separation require an ADEC waiver.

A minimum vertical separation of 18 inches shall be maintained at water and sewer crossings.

Conduit that has the grade or joint disturbed after laying shall be taken up and re-laid. Water shall be kept out of the trench until the jointing is completed.  No conduit length less than 8 feet shall be incorporated into the system except those necessary for fire hydrants or valve locations.

All pipe openings left on abandoned water lines shall be plugged or capped.

The Contractor will be required to use restrained joints on all fire hydrant leads. The Engineer may check any or all restrained joints to assure proper torque as specified by the manufacturer.

Two electrical continuity straps shall be installed on each side of ductile iron pipe joints for pipes less than 12 inches in diameter.  Straps are to be welded to a clean, dry surface.  All welds and uncoated surfaces shall be coated with a coal tar pitch to the satisfaction of the Engineer.  Continuity straps shall be extended to the surface in at least one valve box per intersection.  Wire shall come up on the outside of the extension piece and inside the top section.

Make service and other connections to conform to the Plans.  Valve, plug or cap conduit ends for future connections as shown on the Plans and provide thrust blocks.

- Install HDPE Pipe.  Installation shall be in accordance with these specifications, AWWA C900, and ASTM D 2774.

Jointing shall comply with ASTM D 2657, Technique II-Butt Fusion.

- Butt-Fusion technician shall be properly trained and certified by the fusion machine manufacturer for the pipe sizes in the project, current within the past 12 months.

- Fusion machine shall be hydraulically operated and provide automated hydraulic pressure application at the proper temperature during the fusion process.

- Fusion machine shall be approved by pipe manufacturer and shall include an integral data logger, recording at a minimum the temperature, fusion pressure, time, and technician name.

- Data log sheets shall be provided to Engineer prior to installation of pipe in the trench and summary sheets provided daily.  Any data outside of specifications will be cause to reject the joint at any time.

- Each joint shall be visually inspected by the Engineer prior to installation in the trench.

- Each joint shall be indexed and identified by station and offset and correlated to data logger.

- All branch or hydrant connections shall be made using factory-fabricated fittings.

- Joining different SDRs:  Fusing of unlike SDRs to one another will not be permitted.  Transition from unlike SDRs by means of mechanical joining systems or machined HDPE nipples where a thicker wall HDPE has been matched to the companion pipe wall.

The minimum allowable bending radius for HDPE pipe shall be in accordance with the pipe manufacturer’s recommendations.  If the alignment requires a shorter radius than allowable, a fitting shall be utilized to make the bend.

- Install Ductile Iron Pipe.  Installation shall be in accordance with these specifications and AWWA C600.  The conduit shall be kept clean during laying operations by plugging.  Except where necessary in making connections with other lines or as authorized by the Engineer, pipe shall be laid with the bells facing in the direction of laying.  The full length of each section of pipe shall rest solidly upon the pipe bed, with recesses excavated to accommodate bells, couplings, and joints.

Make push-on joints with the gaskets and lubricant specified for this type joint and assemble in accordance with the applicable requirements of AWWA C600 for joint assembly.  Make mechanical-joints with the gaskets, glands, bolts, and nuts specified for this type joint and assemble in accordance with the applicable requirements of AWWA C600 for joint assembly and the recommendations of Appendix A to AWWA C111. The Contractor has the option of using either mechanical or push-on joints for conduit.

Abrasion of the pipe lining shall be avoided.  Where any part of the lining is damaged, the repair shall be made by and at the Contractor’s expense in a satisfactory manner.

Deflections from a straight line or grade, as required by vertical curves, horizontal curves, or offsets shall not exceed 80 percent of the manufacturer’s recommended maximum deflection.  If the alignment requires deflection in excess of the above limitations, the Contractor shall furnish special bends to provide angular deflections within the limits allowable.  Wherever possible, the Contractor shall achieve the desired deflection by taking advantage of reduced deflections over multiple joints. Short-radius curves and closures shall be formed by shorter lengths of conduit, bevels, or fabricated specials.

Conduit shall be so laid in the trench that after the line is completed the bottom of the conduit conforms accurately to the grades and alignment shown on the Plans.  A maximum 0.2-foot deviation from design alignment and elevation will be allowed.  Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed.  All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the conduit and not by blocking or wedging up.

Conduit that has the grade or joint disturbed after laying shall be taken up and re-laid. No conduit length less than 8 feet shall be incorporated into the system except those necessary for fire hydrants or valve locations.

Install two electrical continuity straps on each joint for all DIP pipes.  Straps are to be welded to a clean, dry surface.  All welds and uncoated surfaces shall be protected from corrosion.

- Polyethylene Encasement.  The outside of all ductile iron conduit and fittings shall be encased with one layer of 8 mil thick polyethylene film.  The polyethylene encasement shall be installed in strict conformance to the methods described in AWWA C105/ANSI A21.5 and the Ductile Iron Pipe Research Association’s “A Guide for the Installation of Ductile Iron Pipe.”

- Casing.  Install CPEP pipe casings in accordance with the requirements of Section 603 and the Plans.  Steel and HDPE pipe casings shall be installed in a similar manner as those specified in this section and in accordance with the Plans.  Boring or jacking of casings will not be allowed.  Seal ends of casings watertight.  Install casing spacers as shown on the Plans where water conduit is shown to be installed through casing.

Casing Marker posts shall meet the requirements of Subsection 730-2.05, Flexible Delineator Posts.  The color shall be yellow with no other markings.  The 2.5-inch by 6-foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9-inches

- Detection Wire.  Install detection wire as shown on the Plans.  Install a cable tag on each wire end and mark tag with size of pipe and direction of the wire (i.e. “north 18”” to indicate the wire continues north from the wire end marking an 18” pipe).

- Thrust Restraint.  Restrained joints, of the type specified herein, and thrust blocks shall be installed where identified on the plans and where the conduit line changes alignment utilizing a tee, cross, bend greater than 11.25°, or similar fitting and at conduit ends.  Cast-in-Place thrust blocks will not be allowed.

Conduit ends left for future connections and all pipe openings left on abandoned water lines, shall be plugged or capped in accordance with the plans, or as approved by the Engineer.  Abandoned copper service lines may be capped with a sweat fitting or folded and crimped tight two times.

- Live-tap Connections.  Contractor shall provide all trench excavation, backfill, and compaction necessary for the live tap connections.  Excavation for live tap connections shall be subsidiary and Contractor shall excavate substances encountered to the depth required for the live tap connections.  Variations from the depth indicated in the plans will not be grounds for additional compensation.  It shall be Contractor's responsibility to familiarize himself with the depth of water mains for the project.  Contractor shall excavate for live tap connections in such a manner that the excavation is 90 degrees to the main water line, whenever possible.  The trench shall be long enough and of sufficient width at the bottom to allow installation of the valve for the live tap connection and provide for safety.

Contractor shall be responsible for, and shall bear the expenses incurred, if a water main should be damaged during excavation or backfilling.

Contractor shall provide equipment, labor, materials, and supplies necessary to complete the live tap connection.  Contractor shall notify the Engineer and Water Utility 48 hours (two working days) prior to installation of the live tap connection.

Tie back rods and/or tie back rod and shackle assemblies will not be acceptable as restrained joints or restraining system for valves and valve/pipe joint interface.

- Water Service Extensions.  Where shown on the plans remove existing key box and copper service up to existing corporation stop.  Connect new service line at the existing corporation stop and install new water service key box as shown on the plans.

- Water Service Decommissioning.  Locate the service connection at the main, remove service pipe within 20-feet of any existing or proposed roadway edge, turn off corporation stop at the main, disconnect copper at the corporation stop, place a solid copper retainer disc in the corporation stop, and remove key box with operating rod.  Provide a record of the service connection location via swing ties to permanent structures.

Water service lines beyond 20-feet from existing or proposed roadway edge may be removed completely or abandoned in place.  Water service lines abandoned in-place shall be capped or have ends folded over and crimped three times to ensure water tightness.

Water service decommissioning also includes all associated trench excavation and backfill in accordance with these specifications.

- Abandon in Place.  Abandon in place method of water mains requires emptying the line, placing a one foot (1’) thick concrete plug with vent tube at the higher end of the line, filling the pipe with a quantity of sand slurry equal to the total calculated volume from the newly installed plug to the point of injection then finally placing a one foot concrete plug at the injection end of the pipe.  The concert plugs the pipe and the slurry fills the pipe.  Work is typically started on the downhill end of the pipe.

In the event the pipeline to be abandoned is cracked or crushed, the Contractor shall excavate to the next joint of pipe and install the plug.  Crushed pipe sections or portions thereof are to be removed and disposed of by the contractor.

627-3.03 FIRE HYDRANTS.

The work under this section consists of the performance of all work required for the Fire Hydrant Installation, Fire Hydrant Relocations, and Fire Hydrant Removals as shown on the Plans.  Where required, furnish and install a single pumper fire hydrant, conduit between the hydrant and the main, auxiliary gate valve, valve box, thrust restraint, guard posts, and polyethylene wrap.  When removing a hydrant from an existing main, plug the tee in the main and test for leakage in accordance with Subsection 627-3.06.

- General.  Contractor shall make final adjustments to the traffic flange.

Hydrants installed but not available for use shall be covered with Water Utility-supplied cover and securely tied.

Hydrant legs shall be installed level and barrels installed plumb.

Hydrant leg and barrel section shall be wrapped with 8-mil polyethylene wrap.

Contractor shall paint or use permanent-ink marker to stencil 2-inch black letters on the hydrant bonnet indicating the direction and distance to the auxiliary valve box, to the nearest 0.1-foot.

- Auxiliary Gate Valve and Valve Box.  Auxiliary gate valves and valve boxes shall be furnished and installed in accordance with 627-2.01, 627-3.04 and 627-3.07.

- Joint Restraint.  All joints shall be restrained in accordance with 627-2.01 and 627-3.02.

- Guard Posts.  Install guard posts at each hydrant installation as shown on the plans.

- Hydrant Removal.  Where hydrants are removed, the entire hydrant assembly between the hydrant auxiliary gate valve and existing hydrant shall be removed and a plug shall be installed on the hydrant side of the auxiliary valve, unless shown otherwise.  Fire hydrant materials shall be salvaged and delivered to the Water Utility.  If the water main is to remain in active service, the plug shall be tested for leakage by visual inspection.  After leakage testing, auxiliary valve shall be shut.

627-3.04 VALVES.  Valves shall be installed where shown on the plans. Valves shall be installed plumb.  Valves shall have the interiors cleaned of all foreign matter before installation.  If the valve is at the end of the line, it shall be plugged prior to backfilling.  The valve shall be inspected by the Water Utility's representative, in the open and closed positions to ascertain that all parts are in good working condition.

627-3.05 VALVE BOXES.  Valve boxes shall be installed over the valves as shown on the plans, with base section centered over the operating nut of the valve and resting on well compacted backfill.  Top section shall be so set as to allow equal movement above and below finished grade.  Final elevation shall be as shown on the Plans.

Top of base section shall be approximately on line with nut at top of valve stem, and the entire assembly shall be plumb.  Provisions shall be made to restrict the soils from entering the bottom section of the valve box.  Place rubber centering ring to align valve box bottom section with the valve top.  Wrap 3 layers of non-woven geotextile fabric around the outside of the valve and base section of the valve box and secure the fabric at the top and bottom with wire or tape.

The Contractor shall expose all valve boxes for pre-final and final inspection. After final inspection of the valves located in unpaved areas, sawdust shall be poured directly over the valve box lid and covered with gravel to facilitate location in the future.

627-3.06 TESTING WATER SYSTEM.

- General  The Contractor shall notify the Engineer in writing 48 hours in advance (two working days) prior to any test.  The Water Utility and the Engineer shall be present during all tests.  Two hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or canceled.

Contractor shall submit a request to supply water for flushing, testing and disinfecting in writing to the Engineer at least 24 hours prior to obtaining Water Utility supplied water.  The request for water will be subject to water availability and meeting the Contractor’s schedule may not be possible.

The Water Utility reserves the right to provide a test gauge or to check and test the Contractor’s test gauge at any time.

- Flushing.  All flushing shall be coordinated with the Water Utility.  All newly laid water conduit shall be "open-bore" flushed to remove any foreign matter to the satisfaction of the Water Utility. A detailed plan for cleaning of the lines shall be submitted to the Engineer for review and approval prior to commencement of work.

"Open-bore" flushing shall be accomplished prior to hydrostatic testing and disinfection at all extremities including all stub-outs and dead-ends.  The Contractor shall furnish, install and remove all fittings and conduit necessary to perform the flushing.  Under no circumstances will "open-bore" flushing through hydrants or reduced outlets be permitted.

Flushing of newly installed conduit may be required to occur between the hours of 1:00 AM and 6:00 AM, depending on availability of water, as authorized by the Water Utility.  Flushing shall be considered incidental to this work and no separate payment will be made.

- Hydrostatic Testing.  A hydrostatic test shall be conducted on all newly constructed water conduit, fire lines, fire hydrant leads and stub-outs after "open-bore" flushing in the presence of the Engineer and the Water Utility in accordance with the requirements of AWWA C600 unless hereinafter modified.  The Contractor, at his option, may either use a pressure test or a leakage test.

The Contractor shall furnish all necessary assistance, equipment, labor, materials and supplies (including the test pressure gauge) necessary to complete the test to the satisfaction of the Water Utility.  The Contractor shall suitably valve off or plug the outlet to the existing or previously-tested water main at his expense, prior to making the required hydrostatic test.

Prior to testing, all air shall be expelled from the conduit. If permanent air vents are not located at all high points, the Contractor shall, at his expense, install corporation cocks at such points so the air can be expelled as the conduit is slowly filled with water.

No hydrostatic test section shall exceed 1,000 feet unless approved by the Water Utility in writing.  All main line valves, fire hydrant auxiliary valves, fire hydrant main valves and plugs shall be tested.  All intermediate valves within the section being tested will be fully closed and reopened as directed by the Engineer during the actual test.  Only static pressure will be allowed on the opposite side of the end valves of the section being tested.

All hydrostatic testing will be performed through test copper.  Use of fire hydrants and service connections for testing will not be allowed.

- For HDPE Pipe:  The test pressure shall be 150 psi.  The testing medium shall be clean water.  The test method shall be Monitored Make-up Water or Non-monitored Make-up Water, at the Contractor’s option.  Prior to testing for leakage, backfill trench up to at least 3 feet above pipe.  Joints may be left uncovered to permit inspection.  When leakage exceeds the allowable amount specified, make satisfactory correction and retest pipeline section in the same manner.  Correct visible leaks regardless of leakage test results.

  - Monitored Make-up Water.  The test procedure consists of initial expansion and test phases.  During the initial expansion phase, the test section is pressurized to the test pressure and sufficient water is added each hour for three hours to return to test pressure.  After the initial expansion phase, about 4 hours after pressurization, the test phase begins.  The test phase shall be 2 hours, after which a measured amount of make-up water is added to return to test pressure.  If the amount of make-up water does not exceed 4.3 gallons per 100 feet of pipe for 18-inch diameter pipe size, leakage is not indicated.

  - Non-monitored Make-up Water.  The test procedure consists of initial expansion and test phases.  For the initial expansion phase, make-up water is added as required to maintain the test pressure for 4 hours.  For the test phase, the test pressure is reduced by 10 psi.  If the pressure remains steady (within 5% of the target value) for 1 hour, no leakage is indicated.

  - Test methods described above are from the Plastic Pipe Institute Engineering Handbook; Inspections, Tests, and Safety Concerns.

  - The total test time including initial pressurization, initial expansion, and time at test pressure shall not exceed 8 hours.  If the test is not completed, the test section should be de-pressurized and allowed to relax for at least 8 hours before bringing the test section up to test pressure again.

- For Ductile Iron Pipe:  The hydrostatic pressure shall be 150 psi and the duration of each hydrostatic pressure test shall be 30 minutes. After the required test pressure has been reached, the pumping will be terminated. If the pressure remains constant for 30 minutes without the aid of a pump, that section of the conduit will not be subjected to any further hydrostatic tests.

Cracked or defective conduit, gaskets, mechanical joints, fittings, valves or hydrants discovered as a consequence of the hydrostatic tests shall be removed and replaced with sound material at the Contractor's expense. The test shall then be repeated until the results are satisfactory.

In the instance where connection is made to an existing water conduit, a new valve shall be installed on the connection.  The Contractor shall suitably seal off the outlet leading to the existing conduit prior to making the field tests.

- Continuity Tests.  The Contractor shall perform electrical conductivity tests on all ductile iron pipe mains less than 12 inches in diameter in the presence of the Engineer and the Water Utility.  The Contractor shall maintain a circuit of 600 amperes DC current for a period of 15 minutes.  Return current shall be at least 90 percent of the input current.  All equipment necessary to maintain the circuit shall be supplied by the Contractor.

All continuity tests will be through wires brought to the surface or through ¾-inch minimum copper pipe connected to the main.  The use of fire hydrants and valves, as substitutes for wires will not be accepted.  All wires brought to the surface to complete the continuity test shall be removed to a depth of 2 feet below finished street grade upon completion of the tests.

- Removal of Test and Air Vent Copper Pipe.  After completion of testing, all test and air vent copper pipe shall be removed and the stop closed at the main, in the presence of the Engineer and Water Utility.

627-3.07 DISINFECTION OF WATER LINES. All portions of the water system shall be disinfected, including all valves and stops and any portion of the existing connection system that might have become contaminated during construction activities.  Disinfection shall be accomplished after completion of pressure and/or leakage tests in compliance with AWWA C651, Disinfecting Water Mains.  Disinfectant chemicals shall be NSF 60 certified.

Chlorine shall be used for disinfection, and shall be applied only by one of the following methods:

- liquid chlorine gas and water mixture

- direct chlorine gas feed

- calcium hypochlorite and water mixture

Calcium hypochlorite shall be comparable to commercial products known as HTH, Perchloren or Machochlor.  The chlorinating agent shall be applied at the beginning of the section adjacent to the feeder connection, insuring treatment of the entire line.  Water shall be fed slowly into the new conduit with chlorine applied in amounts to produce a dosage of 40 to 50 ppm.  Application of the chlorine solution shall continue until the required dosage is evident at all extremities of the newly-laid conduit.

Chlorine gas-water mixture shall be applied by means of a solution-feed chlorinating device.  Chlorine gas shall be fed directly from a chlorine cylinder equipped with a suitable device for regulating the rate of flow and effective diffusion of gas within the conduit.  Calcium hypochlorite shall be injected or pumped into the water conduit.  During the chlorination process, all intermediate valves and accessories shall be manipulated so that the strong chlorine solution in the conduit being treated will not flow back into the conduit supplying the water.  Hydrostatic testing of water conduit containing the chlorine mixture will not be allowed.

A residual of not less than 5 ppm chlorine shall be produced in all parts of the water conduit and retained for a minimum period of 24 hours, after which it shall be flushed from the conduit at its extremities until the replacement water tests are equal chemically and bacteriologically to those of the permanent source of supply.  In no instance will a water conduit be chlorinated before "open-bore" flushing.

CHLORINATION

| Conduit Diameter | Dosage (oz. per 100 feet) |
| --- | --- |
| 6 in | 1.35 oz. |
| 8 in | 2.75 oz. |
| 10 in | 4.30 oz. |
| 12 in | 6.19 oz. |
| 16 in | 11.00 oz. |

The above table is to be used as a guide for chlorinating mains by the calcium hypochlorite and water mixture method.  The given dosage per 100 feet results in a chlorine solution of 40 to 50 ppm.  This dosage takes into account that Contractors most frequently use granular HTH, which is 65 percent pure.  If another chlorinating agent is used, the dosage must be adjusted.  Caution should be exercised against producing too high a concentration of chlorine in the conduit.

All water with a chlorine concentration of greater than 1 ppm shall be captured and de-chlorinated prior to disposal using an approved de-chlorination agent.  Do not dose neutralizing chemical beyond the minimum required to neutralize the chlorine actually present in discharge.  Submit Water System De-chlorination Plan to ADEC and Engineer for approval.  Plan shall address de-chlorination method and disposal of water.

Upon completion of disinfection, perform bacteriological sample testing using a Contractor-supplied testing laboratory certified by the State of Alaska.  Provide test results from two consecutive days or a minimum of 15 minutes apart while the test location is left running indicating an absence of fecal coliform.  Test locations shall be at the end of all dead-ends and no more than 1,200 feet apart.  Sampling and testing shall comply with ADEC requirements.

After completion of all testing, all test and air vent copper pipe shall be removed and the corporation cock closed at the main in the presence of the Engineer and the Water Utility.

627-3.08 AS-BUILT PLANS AND WORKING DRAWINGS.  A complete and accurately dimensioned record of all deviations, deletions, additions, and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed.

This as-built information shall be recorded on a print of the plans affected and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor.  Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When the water system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance of the system by the Water Utility.

627-3.09 CONTRACTOR’S WARRANTY

The Contractor shall warranty all materials and workmanship for one (1) year from the Final Acceptance Date unless otherwise specified.  This warranty shall require the Contractor to remedy promptly, without cost to the Department, any and all defects in material and workmanship including any consequential damages resulting from defective materials or workmanship.

All Warranty Work shall be subject to the same Contract provisions, including materials, quality of work, authority of the Engineer and inspection, as provided for in the original Work. All warranty Work shall be at the sole expense of the Contractor.  All materials and workmanship directly or indirectly involved in repairs or replacements under this subsection shall carry an extended warranty of not less than one (1) year from the date of the Engineer’s written acceptance of the repair or replacement Work, or through the warranty period for the original project Work, whichever is longer.

If the defect, in the opinion of the Engineer, is of such nature as to demand immediate repair, the Department shall have the right to take corrective action and the cost thereof shall be borne by the Contractor.

At the completion of the Warranty, the Contractor and the Department shall conduct a pre-Warranty Inspection.  All deficiencies indicated by the pre-Warranty Inspection shall be listed and promptly furnished to the Contractor for action. When all listed deficiencies have been corrected, the Contractor shall notify the Engineer and a final Warranty Inspection will be performed.  When the Warranty Inspection verifies correction of any listed deficiencies, the Engineer shall issue a Certificate of Completion.

627-4.01 METHOD OF MEASUREMENT.

  - Water Conduit.  Measurement for water conduit with appurtenances will be per linear foot of horizontal distance of the various sizes and classes furnished and installed.  Measurement will be from station to station as staked in the field and as shown on the plans.  No deduction in length will be made for valves and fittings.

  - Fire Hydrant Adjustment.  By the number of fire hydrants adjusted only for grade.

  - Fire Hydrant Installation or Fire Hydrant Removal.  Measurement will be the number of fire hydrant assemblies installed or removed, including excavation, backfill, Select Material, Type A, and Class "C" bedding.

  - Water Service Connection or Extension.  By the number of water services installed or extended.

  - Gate Valves and Valve Boxes. The quantity to be paid will be the actual number of valves, including valve boxes and marker posts, of each class and size that is furnished and installed.

  - Removal and Adjustment of Valves and Valve Boxes.  By the number of valves and valve boxes adjusted or removed.

  - Live Tap Connection.  By the number of live tap connections performed.  Connections to existing mains made by cutting in fittings or valves will not be considered under this pay item.

  - Water Pipe Casings.  By the linear foot of horizontal distance of the various sizes and types furnished and installed.  Measurement will be from station to station as staked in the field and as shown on the plans.

627-5.01 BASIS OF PAYMENT.

All labor, tools, equipment, fittings, pipe, and demolition necessary to connect new water main to the existing water mains, as shown on the drawings, will be considered subsidiary.

The contract price for Water Conduit includes trench excavation, bedding, backfill, disposal of surplus excavated material, pipe, fittings, tees, reducers, crosses, bends, thrust restraints, polyethylene encasement continuity straps, detection wire, marking tape, couplings, thrust blocks, testing, disinfection, and abandonment or removal of existing conduit.

The contract price for Fire Hydrant Installation includes trench excavation, bedding, backfill, disposal of surplus excavated material, fire hydrant, tee in main, auxiliary gate valve with valve box, conduit between the main and the hydrant, all fittings and materials required, testing, disinfection, and painting.

The contract price for Fire Hydrant Removal includes trench excavation, bedding, backfill, disposal of surplus excavated material, removal of existing hydrant, associated piping, and guard posts, valves and appurtenances, and installation of cap and thrust block.

The contract price for Live Tap Connection includes excavation, bedding, backfill, disposal of surplus excavated material, tapping saddle and gate valve, thrust block, testing, and disinfection.

Repair of existing improvements on private property and repair of existing utilities damaged by the Contractor will not be paid for directly but will be considered subsidiary.

Any costs involved in service changeovers and providing temporary water service are subsidiary.

Removing or abandoning existing water lines or appurtenances designated on the Plans is subsidiary.

Preparation and submittal of as-built plans is subsidiary.

Pay Item No.	Pay Item	Pay Unit

627(1-6)	6-Inch Ductile Iron Water Conduit, Class 52	Linear Foot

627(1-8)	8-Inch Ductile Iron Water Conduit, Class 52	Linear Foot

627(1-16)	16-Inch Ductile Iron Water Conduit, Class 52	Linear Foot

627(2)	__Inch Steel Water Conduit	Linear Foot

627(3)	Install Valve Box	Each

627(4)	Fire Hydrant Adjustment	Each

627(5)	Fire Hydrant Installation	Each

627(6)	Fire Hydrant Relocation	Each

627(7)	Fire Hydrant Removal	Each

627(8)	Water Service Connection	Each

627(8A)	Decommission Water Service	Each

627(8B-1)	Water Service Extension, 1-Inch	Each

627(8B-2)	Water Service Extension, 2-Inch	Each

627(9-6)	Install 6-Inch Gate Valve	Each

627(9-8)	Install 8-Inch Gate Valve	Each

627(9A)	Install Air Relief Valve	Each

627(9-16)	Install 16-Inch Gate Valve	Each

627(9-18)	Install 18-Inch Gate Valve	Each

627(10)	Adjustment of Valve Box	Each

627(10A)	Remove Valve and Valve Box	Each

627(13A)	Live Tap Connection, 8” x 6”	Each

627(13B)	Live Tap Connection, 16” x 6”	Each

627(13C)	Live Tap Connection, 16” x 16”	Each

627(14-18)	18-Inch HDPE Water Conduit, SDR 11	Linear Foot

627(15-18)	18-Inch CPEP Water Pipe Casing, Type S	Linear Foot

627(15-24)	24-Inch CPEP Water Pipe Casing, Type S	Linear Foot

627(15-24A)	24-Inch Steel Water Pipe Casing 	Linear Foot

CFHWY00317

Special Provisions

Replace Section 631 with the following:

SECTION 631
GEOTEXTILE FOR SUBSURFACE DRAINAGE AND EROSION CONTROL

631-1.01 DESCRIPTION. Prepare ground surface, and furnish and place geotextiles for subsurface drainage and erosion control, as shown on the Plans.

631-2.01 MATERIALS. Use materials that conform to the following, for the class specified in the bid schedule:

Geotextiles and Sewn Seam Strength	Subsection 729-2.01

Sewing Thread. Use high strength polypropylene, or polyester. Do not use nylon thread.  Use thread of contrasting color to that of the geotextile itself.

631-3.01 CONSTRUCTION.

1.	Surface Preparation. Prepare ground surface by removing stumps, brush, boulders, and sharp objects.  Fill holes and large ruts, as directed by the Engineer, with material shown on the Plans or as approved by the Engineer.  Construct smooth and stable trench walls.

2.	Geotextile Placement. Unroll geotextile directly onto the prepared surface.  Stretch geotextile to remove any creases, folds or wrinkles.  Place geotextile in a manner which ensures intimate contact between the trench wall and the geotextile (i.e., no voids, folds, or wrinkles).  The geotextile may be held in place with securing pins at 3-feet spacing along all edges (but not closer than 2-inches from the edge) to prevent movement during construction.  Do not expose geotextiles to sunlight for longer than 14 days after removal of protective covering.  Do not allow geotextile rolls to get wet prior to installation.

a.	Subsurface Drainage.  In trenches, after placing the geotextile and material shown on the Plans, fold the geotextile over the top of the material shown on the Plans to produce a minimum overlap of 12-inches, for trenches greater than 12-inches wide.  In trenches less than 12-inches wide, make the overlap equal to the width of the trench.  Then cover the geotextile with the subsequent course of material.

b.	Erosion Control.  Place and anchor the geotextile on the approved surface so not to tear or excessively stretch the geotextile by placement of the overlying materials.  Secure the geotextile to the slope but secure it loosely enough so that the geotextile will not tear when riprap or other cover material is placed on the geotextile.  The geotextile shall not be keyed at the top of the slope until the riprap or other cover material is in place at the top of the slope.  Anchor the terminal ends of the geotextile using key trenches or aprons with a minimum of 24-inch depth into the soil substrate at the crest and toe of slope, or as shown on the Plans.  Other temporary or permanent anchoring method may be used, as approved by the Engineer.  Place geotextile with the machine direction parallel to the direction of water flow (normally parallel to the slope for erosion control runoff and wave action, and parallel to the stream or channel).

3.	Joining. Join geotextile by sewing or overlapping. Joining by bonding or other attachment methods may be used, subject to approval by the Engineer.

a.	Sew seams with a Butterfly or J-Seam. Use a double thread chain stitch (lock stitch). Bring adjacent sections of geotextile together and fold so that the stitching penetrates four layers of geotextile for the full seam length.  Make the stitching line 1 1/4-inches (± 1/4-inch) from the seams so that they can be easily inspected by the Engineer or representative.  Illustrations showing correct stitch formation and seam configurations are provided in Figure 1-2 (page 1-28) of the FHWA publication, Geosynthetic Design & Construction Guidelines, FHWA-NHI-07-092, August 2008. Conform both factory and field sewn seams to the strength requirements of Table 1 as outlined in the AASHTO M 288 for subsurface drainage and erosion control applications.

b.	Overlap geotextile sections by a minimum of 3-feet at all longitudinal and transverse joints.  Overlap successive geotextile sheets in the direction of flow so that the upstream sheet is placed over the downstream sheet and/or upslope over downslope.  In trenches, where overlapped seams are constructed in the longitudinal trench direction, make the overlap equal to the width of the trench.

4.	Placement of Cover Material. Following placement of the geotextile on the prepared surface, place cover material of the type shown on the Plans. Place the cover material and armor from the bottom to the top of the slope using methods which minimize tearing and/or excessive stretching of geotextile.  In underwater applications, place the geotextile and the required thickness of cover material in the same day.  Maintain proper overlap and geotextile continuity.  Do not exceed the allowable drop heights for cover material shown in Table 631-1.  Do not allow stones with a weight of more than 100-pounds to roll down the slope on the geotextile.  Do not grade the slope in a way that will disturb the cover material or armor stone once it has been placed.  Backfill all voids in the riprap or other cover material that exposes the geotextile, with material approved by the Engineer, so that the geotextile is completely covered.

TABLE 631-1

ALLOWABLE DROP HEIGHT FOR GEOTEXTILE

| INDIVIDUAL STONE Max. Weight (lbs.) | ALLOWABLE DROP HEIGHT (ft.) |  |
| --- | --- | --- |
|  | UNPROTECTED GEOTEXTILE | PROTECTED GEOTEXTILE * |
| < 5 | 3 | 3 |
| 5 – 250 | 0 | 3 |
| > 250 | 0 | 0 ** |

* Protected geotextile is defined as having a gravelly covering (cushion layer) at least 6-inches thick.

** If stones greater than 250-pounds must be dropped or if a height of drop greater than 3-feet is required, then perform field trials to determine the minimum cushion thickness and/or maximum height of safe drop without damaging the geotextile.

Maintain a minimum depth of 12 inches of cover material between the geotextile and the wheels or tracks of the construction equipment.

5.	Geotextile Repair. Should the geotextile be torn, punctured, or the overlaps or sewn joints disturbed – as evidenced by visible geotextile damage – remove the backfill around the damaged area and repair or replace the damaged area at no additional expense to the State.  Make repairs to the damaged area with a patch of the same type and class of geotextile originally placed.  Overlay torn area with geotextile with a minimum 3-feet overlap around the edges of the torn area.  Ensure that the patch remains in place when material is placed over the affected area.

631-4.01 METHOD OF MEASUREMENT.  By the area covered, measured along the ground surface.  No allowance will be made for geotextile in key trenches or for overlap, whether at joints or patches.

631-5.01 BASIS OF PAYMENT.  Payment will be at the Contract unit price.  Repair and replacement costs for damaged geotextile are subsidiary to the Section 631 Pay Items.

Material used to fill ruts and holes will be paid for at the unit price for the type of material used.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

631(1)	Geotextile, Drainage, Class 2	Square Yard

631(2)	Geotextile, Erosion Control, Class 1	Square Yard

CR631-070115

Special Provisions

Replace Section 633 with the following:

SECTION 633
SILT FENCE

633-1.01 DESCRIPTION. Furnish, install, maintain, and remove temporary silt fence as shown on the Plans or as directed by the Engineer.

633-2.01 MATERIALS. Use materials that conform to the following:

Geotextile	Subsection 729-2.01

Silt Fence	Subsection 729-2.04

Posts	Wood 1.5-inch x 1.5-inch x 36-inch min., steel, or approved synthetic material.

Prefabricated Silt Fence	Meet the Plans and Section 633 requirements.

Attachment Devices	Staples; wire; self-locking nylon, plastic or wire ties; or other approved means to attach fabric to posts.

Support Mesh between Posts	14-guage welded wire fencing, metal chain-link fabric, or geosynthetic mesh with equivalent strength. Use maximum mesh spacing of 6 inches. Height shown on the Plans, or specified in the Bid Schedule.

633-3.01 CONSTRUCTION.  Install silt fence according to Plans.  Use Trenchless Detail when installing silt fence over permanently frozen ground. Holes may need to be predrilled for support posts. When joining to another roll, place both end posts together and wrap them with silt fence by turning them one full rotation.  Drive the wrapped posts.

633-3.02 MAINTENANCE. Maintain the integrity of the fence to contain sediment in runoff until final stabilization.

633-3.04 REMOVAL. After disturbed area has been accepted as permanently stabilized or when sediment protection is no longer needed, remove silt fence according to the Plans.

633-4.01 METHOD OF MEASUREMENT. Section 109. Measure silt fence by the length of fence installed.  No allowance will be made for overlap, whether at joints or patches.

633-5.01 BASIS OF PAYMENT.  The contract price includes installation, maintenance, removal and disposal of the fence.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

633(1)	Silt Fence	Linear Foot

633(2)	Support Mesh Reinforced Silt Fence	Linear Foot

CR633-070115

SECTION 635
INSULATION BOARD

Special Provision

635-5.01 BASIS OF PAYMENT.

Add the following pay item:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

635(2)	Insulation Board, 4-Inch Thick	SF

CFHWY00317

SECTION 636
GABIONS

Special Provision

636-5.01 BASIS OF PAYMENT.

Replace the first sentence with the following: Excavation, aggregate base course, and geotextile fabric are subsidiary.

CFHWY00317

Special Provisions

Replace Section 639 with the following:

SECTION 639
DRIVEWAYS

639-1.01 DESCRIPTION. Construct driveways and approaches.

639-2.01 MATERIALS.  Reserved.

639-3.01 CONSTRUCTION.  Reserved.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed.

639-5.01 BASIS OF PAYMENT.  The Contract unit price for driveways and approaches is for furnishing equipment and labor.

Pavement removal and excavation required constructing driveways and approaches is subsidiary to the driveway and approach pay items.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

639(1)	Residence Driveway	Each

639(2)	Commercial Driveway	Each

639(3)	Public Approach	Each

639(4)	Driveway	Each

639(6)	Approach	Each

CR639-092016

Special Provision

Replace Section 641 with the following:

SECTION 641
EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this section and applicable local, state, and federal requirements, including the APDES Construction General Permit. The state APDES program is administered by DEC.  Section 301(a) of the Clean Water Act (CWA) and 18 AAC 83.015 provide that the discharge of pollutants to water of the U.S. is unlawful except as allowed by the CGP.

641-1.02 DEFINITIONS. These definitions apply only to Section 641.

ACTIVE TREATMENT SYSTEM (ATS) OPERATOR. The Contractor’s qualified representative who is responsible for maintaining and operating an active treatment system (as defined in the CGP) for storm water runoff.

ALASKA CERTIFIED EROSION AND SEDIMENT CONTROL LEAD (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years.

ALASKA DEPARTMENT OF ENVIRONMENTAL CONSERVATION (DEC).  The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

ALASKA POLLUTANT DISCHARGE ELIMINATION SYSTEM (APDES). A system administered by DEC that issues and tracks permits for storm water discharges.

BEST MANAGEMENT PRACTICES (BMPS).  Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or minimize the discharge of pollutants to waters of the United States. BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leaks, sludge or waste disposal, or drainage from material storage.

CLEAN WATER ACT (CWA).  Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

CONSTRUCTION ACTIVITY. Physical activity by the Contractor, Subcontractor or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. Construction Activity includes soil disturbing activities (e.g. clearing, grubbing, grading, excavating); and establishment of construction materials or equipment storage or maintenance areas (e.g. material piles, borrow area, concrete truck chute washdown, fueling); and industrial activities that may discharge storm water and are directly related to the construction process (e.g. concrete or asphalt batch plants).

CONSTRUCTION GENERAL PERMIT (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by DEC. It authorizes stormwater discharges provided permit conditions and water quality standards are met.

CORPS OF ENGINEERS PERMIT (COE PERMIT). A U.S. Army Corps of Engineers Permit for construction in waters of the US. Such permit may be issued under Section 10 of the Rivers and Harbors Act of 1899, or Section 404 of the Clean Water Act.

ELECTRONIC NOTICE OF INTENT (ENOI). The electronic Notice of Intent submitted to DEC, to obtain coverage under the CGP.

ELECTRONIC NOTICE OF TERMINATION (ENOT). The electronic Notice of Termination submitted to DEC, to end coverage under the CGP.

ENVIRONMENTAL PROTECTION AGENCY (EPA). A federal agency charged to protect human health and the environment.

ERODIBLE STOCKPILE. Any material storage area or stockpile consisting of mineral aggregate, organic material, or a combination thereof, with greater than 5% passing the #200 sieve, and any material storage where wind or water transports sediments or other pollutants from the stockpile.  Erodible stockpile also includes any material storage area or stockpile where the Engineer determines there is potential for wind or water transport of sediments or other pollutants away from the stockpile.

EROSION AND SEDIMENT CONTROL PLAN (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

FINAL STABILIZATION. Is defined in this section as it is defined in the CGP.

HAZARDOUS MATERIAL CONTROL PLAN (HMCP).  The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

INSPECTION.  An inspection required by the CGP or the SWPPP, usually performed together by the Contractor’s SWPPP Manager and Department’s Stormwater Inspector.

MUNICIPAL SEPARATE STORM SEWER SYSTEM (MS4) PERMIT.  A DEC storm water discharge permit issued to certain local governments and other public bodies, for operation of storm water conveyances and drainage systems. See CGP for further definition.

MULTI-SECTOR GENERAL PERMIT (MSGP). The Alaska Pollutant Discharge Elimination System General Permit for storm water discharges associated with industrial activity.

LOW-ERODIBLE STOCKPILE.  Any material stockpile identified in the CGP definition for Final Stabilization Section 1.b, and includes: riprap, gabion backfill, porous backfill, railroad ballast, and sub-ballast, ditch lining, or fill material with low erodibility. The stockpile shall not have a gradation of more than 5% passing the #200 sieve unless approved by an Engineer. There shall be no possibility of sediment transport due to water or wind erosion.

OPERATOR(S). The party or co-parties associated with a regulated activity that has responsibility to obtain permit coverage under the CGP.  ”Operator” for the purpose of the CGP and in the context of storm water associated with construction activity, means any party associated with a construction project that meets either of the following two criteria:

1.	The party has operational control over construction plans and specifications, including the ability to make modifications to those plans and specifications; or

2.	The party has day to day operational control of those activities at a project which are necessary to ensure compliance with a SWPPP for the site or other permit conditions (e.g. they are authorized to direct workers at a site to carry out activities required by the SWPPP or comply with other permit conditions).

POLLUTANT. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sediment, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

PROJECT ZONE. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Contract.

Material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

RECORDS. Any record, report, information, document, or photograph required to be created or maintained pursuant to the requirements of the CGP, the CGP storm water requirements of the Clean Water Act; and applicable local, state, and federal laws and regulations regarding document preservation.

SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC PLAN). The Contractor’s detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

SPILL RESPONSE FIELD REPRESENTATIVE. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

STORM EVENT. A rainfall event that produces 0.5 inch or more of precipitation in 24 hours and that is separated from the previous storm event by at least 3 days of less than 0.1 inch of rain per day.

STORM WATER POLLUTION PREVENTION PLAN (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project Zone, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but is not limited to, amendments, records of activities, inspection schedules, and reports, qualifications of key personnel, and all other documentation, required by the CGP and this specification, and other applicable local, state, and federal laws and regulations.

STORM WATER POLLUTION PREVENTION PLAN TWO (SWPPP2). The Contractor’s detailed project specific plan to comply with CGP or MSGP requirements, for Contractor construction-related activities outside the Project Zone.

SUBCONTRACTOR SPILL RESPONSE COORDINATOR. The subcontractor’s representative with authority and responsibility for coordinating the subcontractor’s activities in compliance with the HMCP and SPCC Plan.

SUBCONTRACTOR SWPPP COORDINATOR. The subcontractor’s representative with authority to direct the subcontractor’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the subcontractor’s compliance with the SWPPP.

SUPERINTENDENT. The Contractor’s duly authorized representative in responsible charge of the work.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

SWPPP AMENDMENT. A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP MANAGER. The Contractor’s qualified representative who conducts Inspections, updates SWPPP records, and has authority to suspend work and to implement corrective actions required for CGP compliance.

SWPPP PREPARER. The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

TEMPORARY STABILIZATION. Protecting soils from erosion and sediment loss by rainfall, snow melt, runoff, or wind with a temporary vegetative and/or non-vegetative protection cover. Temporary stabilization may include a combination of seeding, geotextiles, mulches, surface tackifiers, rolled erosion control products, low-erodible gravel or paving, or the mentioned BMPs combined together with trackwalking.

UTILITY SPILL RESPONSE COORDINATOR. The Utility’s representative with authority and responsibility for coordinating the Utility’s activities in compliance with the HMCP and SPCC Plan.

UTILITY SWPPP COORDINATOR. The Utility’s representative with authority to direct the Utility’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the Utility’s compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS. For plans listed in Subsection 108-1.03.5 (SWPPP and HMCP), use the Contractor submission and Department review deadlines identified in Subsection 641-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1.	Storm Water Pollution Prevention Plan. Submit an electronic copy and three hard copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize and bind the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14-day review period will restart when the contractor submits an electronic copy and three hard copies of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved by the Department, the Contractor must sign and certify the approved SWPPP using Form 25D-111. See Item 4 for further SWPPP submittal requirements.

2.	Hazardous Material Control Plan.  The HMCP template can be found at the following webpage: http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml. Submit an electronic copy and three hard copies of the HMCP, as an appendix to the SWPPP, to the Engineer for approval. The HMCP submittal and review timeline, and signature requirements are the same as the SWPPP.

3.	Spill Prevention, Control, and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and three signed hard copies of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

4.	CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. Do not use the SWPPP for Construction Activities outside the Project Zone where the Department is not an operator.  Use a SWPPP2 for Construction Activities outside the Project Zone.

After Department approval of the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to DEC for coverage under the Construction General Permit (CGP). Submit a copy of the signed eNOI and DEC’s written acknowledgement (by letter or other document), to the Engineer as soon as practicable and no later than three days after filing eNOI or receiving a written response.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to DEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and DEC’s written acknowledgment (by letter or other document), for inclusion in the SWPPP.

Before Construction Activities occur, transmit to the Engineer an electronic copy of the approved and certified SWPPP, with signed Delegations of Signature Authorities on forms 25D-107 and 25D-108, SWPPP Certifications on forms 25D-111 and 25D-109, both permittee’s signed eNOIs and DEC’s written acknowledgement.

5.	Ending CGP Coverage. Submit an eNOT to DEC within 30 days after the Engineer has determined the conditions listed in Subsection 641-3.01.6 have been met. Submit a copy of the signed eNOT and DEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response.

6.	DEC SWPPP Review.  When CGP Part 2.1.3, requires DEC SWPPP review:

a.	Transmit a copy of the Department-approved SWPPP to DEC using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven (7) days of receiving the confirmation; and

c.	Retain a copy of delivery receipt confirmation in the SWPPP.

7.	Local Government SWPPP Review.  When local government or the CGP Part 2.1.4, requires local government review:

a.	Transmit a copy of the Department-approved SWPPP and other information as required to local government, with the required fee.  Use delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation;

c.	Transmit a copy of any comments by the local government to the Engineer within seven days of receipt;

d.	Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven days of receipt of the comments;

e.	Include a copy of local government SWPPP review letter in the SWPPP; and

f.	File a notification with local government that the project is ending.

8.	Modifying Contractor’s eNOI.  When required by the CGP Part 2.7, modify your eNOI to update or correct information within 30 calendar days of the change. Reasons for modification include a change in start or end dates, change in Owner/Operator address and contact information, change in site information, any changes in number of acres to be disturbed, change in decision to use or not use treatment chemicals, or change 	in location of SWPPP records.

The Contractor must submit an eNOT and then submit a new eNOI instead of an eNOI modification when: the operator has changed.

641-1.04 PERSONNEL QUALIFICATIONS. Provide documentation in the SWPPP that the individuals serving in these positions meet the personnel qualifications.

1.	The SWPPP Preparer.

a.	Total disturbed acreage, 20 acres or less, meet at least one of the following qualifications:

(1).	Current certification as a Certified Professional in Erosion and Sediment Control (CPESC);

(2).	Current certification as AK-CESCL, and at least two years' experience in erosion and sediment control, as a SWPPP Manager or SWPPP writer, or equivalent. Provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement; or

(3).	Professional Engineer registered in the State of Alaska with current certification as AK-CESCL.

b.	Total disturbed acreage greater than 20 acres, meet a. above, and complete a SWPPP Preparation course.

2.	The Superintendent must meet the following qualifications:

a.	Current certification as AK-CESCL; and

b.	Duly authorized representative, as defined in the CGP, Appendix A, Part 1.12.3.

3.	The SWPPP Manager must have current certification as AK-CESCL and must meet the CGP experience, training, and authority requirements identified for the Storm Water Lead and Storm Water Inspector positions.

4.	ATS operator must have current certification as AK-CESCL, and be knowledgeable in the principles and practices of treatment systems in general, and the operation of the project-specific ATS.  The ATS operator must have at least three months field experience with ATS, or completion of an ATS manufacturer’s training course, or completion of system operator certification course.

5.	The Department accepts people having any of the following certificates as equivalent to AK-CESCL, if the certificates are current according to the sponsoring organization’s policies:

a.	CPESC, Certified Professional in Erosion and Sediment Control; or

b.	CISEC, Certified Inspector in Sediment and Erosion Control.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT. The eNOI and eNOT must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12. Signature and certification authority for the eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports.  Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Superintendent position is responsible for signing and certifying the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI and eNOT.

The Engineer will provide the Department’s delegation on Form 25D-107, which the Contractor must include in the SWPPP.

3.	Subcontractor Certification. Subcontractors must certify on Form 25D-105, that they have read and will abide by the CGP and the conditions of the project SWPPP.

4.	Signatures and Initials.  Handwrite signatures or initials on CGP documents and SWPPP forms, wherever a signature or initial is required.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

1.	The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

2.	The Contractor is responsible for permitting and permit compliance outside the Project Zone. The Contractor has sole responsibility for compliance with DEC, COE, and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

3.	An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.3) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage.

Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

4.	The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas outside the Project Zone;

b.	For Construction Activity and Support Activities outside the Project Zone; and

c.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY.

Relocation Coverage. A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 651.  The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work.  Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

1.	SWPPP Preparer and Pre-Construction Site Visit.

Use a SWPPP Preparer to develop the SWPPP and associated documents, according to the requirements of the CGP and COE permit. The SWPPP Preparer must put their name, qualifications (including the expiration date of any certifications), title and company name in the SWPPP.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least seven days advance notice of the site visit, so that the Department may participate.

During the pre-construction inspection, the SWPPP Preparer must identify, or if a draft of the SWPPP has already been prepared verify that the SWPPP fully addresses and describes:

a.	Opportunities to phase construction activities;

b.	Appropriate BMPs and their sequencing; and

c.	Sediment controls that must be installed prior to beginning Construction Activities.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, including the names of attendees and the date.

2.	Developing the SWPPP.

Use the Department’s project ESCP, Environmental commitments, and other Contract documents as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.

Develop the SWPPP with sections and appendices, according to the current DOT&PF SWPPP template. Include information required by the Contract and described in the CGP Part 5.0.

a.	Obtain the following forms after they have been completed by the Department and include them in the SWPPP:

(1)	SWPPP Delegation of Signature Authority – DOT&PF (25D-107)

(2)	SWPPP Certification for DOT&PF (25D-109)

(3)	SWPPP Delayed Action Item Report (25D-113), if needed

b.	Use the following Department forms for recording information in the SWPPP:

(1)	SWPPP Amendment Log (25D-114)

(2)	SWPPP Certification for Contractor (25D-111)

(3)	SWPPP Construction Site Inspection Report (25D-100)

(4)	SWPPP Corrective Action Log (25D-112)

(5)	SWPPP Daily Record of Rainfall (25D-115)

(6)	SWPPP Delegation of Signature Authority – Contractor (25D-108)

(7)	SWPPP Grading and Stabilization Activities Log (25D-110)

(8)	SWPPP Pre-Construction Site Visit (25D-106)

(9)	SWPPP Project Staff Tracking (25D-127)

(10)	SWPPP Subcontractor Certification (25D-105)

(11)	SWPPP Training Log (25D-125)

(12)	SWPPP Noncompliance (25D-143)

SWPPP Template forms and instructions are available online at:

http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix.

3.	SWPPP Considerations and Contents.

a.	The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone. Construction activity outside the Project Zone must have permit coverage, using a separate SWPPP2, and separate Contractor Inspections.

b.	The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity, and identify the areas:

(1)	Over which each operator has operational control; and

(2)	Where the Department and Contractor are co-operators.

c.	For work outside the Project Zone the SWPPP must identify the entity that has stormwater permit coverage, the operator, and the areas that are:

(1)	Dedicated to the Project and where the Department is not an operator; and

(2)	Not dedicated to the project, but used for the project.

d.	Account for the Contractor’s construction methods and phasing. Identify the amount of mean annual precipitation.

e.	Comply with the CGP Part 1.4.3 Authorized Non-Storm Water Discharges. List locations where authorized non-storm water will be used, including the types of water that will be used on-site.

f.	Include the Department’s Antidegradation Analysis in the SWPPP if storm water from the Project Zone discharges into receiving water that is considered a high quality water and that constitutes an outstanding national resource, according to CGP Part 2.1.6.

g.	There are special requirements in the CGP Part 3.2, for storm water discharges into an impaired water body, and they may include monitoring of storm water discharges. For Projects meeting the permit criteria, the Contractor shall implement a monitoring plan approved by the Department for the storm water within the Project Zone, and shall provide the required information and reports for inclusion in the SWPPP. The Contractor is responsible for monitoring and reporting outside the Project Zone.

h.	Preserve natural topsoil unless infeasible. Delineate the site according to CGP Part 4.2.1.  Use stakes, flags, or silt fence, etc. to identifying areas where land disturbing activities will occur and areas that will be left undisturbed. Minimize the amount of soil exposed during Construction activity according to CGP Part 4.2.2.

i.	Comply with CGP Part 4.4, and the DEC General Permit for Excavation Dewatering (AKG002000), requirements for dewatering for trenches and excavations.

j.	The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed.

k.	Describe methods and time limits, to initiate temporary or final soil stabilization, CGP 4.5.1.1.. Begin stabilization no later than the end of the next work day, following the day when the earth-disturbing activities have permanently ceased on any portion of the site or temporarily ceased on any portion of the site and will not resume for a period exceeding:

(1)	Seven days for areas with mean annual precipitation 40 inches or greater; or

(2)	Fourteen days for areas with mean annual precipitation less than 40 inches.

Time allotted to complete temporary and final stabilization, 641-2.01, 3l.

l.	Within seven days of initiating final stabilization, CGP 4.5.1.4, either complete final stabilization or continue maintenance of work until final stabilization is complete. Complete temporary stabilization within 14 days of initiating stabilization, CGP 4.5.1.2.

m.	Include in the “Stabilize Soils” section of the SWPPP, a description of how you will minimize the amount of disturbed and unstabilized ground in the fall season. Identify anticipated dates of fall freeze-up and spring thaw. Describe how you will stabilize areas when it is close to or past the seasonal time of snow cover or frozen conditions, and before the first seasonal thaw. Include a plan for final stabilization.

n.	Plans for Active Treatment Systems must be submitted to DEC for review at least 14 days prior to their use and the Operator of the ATS identified in the SWPPP. Any use of treatment chemicals must be identified on the NOI, documented in the SWPPP, and meet with the requirements in the CGP Part 4.6.

o.	The SWPPP must provide designated areas for equipment and wheel washing, equipment fueling and maintenance, chemical storage, staging or material storage, waste or disposal sites, concrete washouts, paint and stucco washouts, and sanitary toilets. These activities must be done in designated areas that are located, to the extent practicable, away from drain inlets, conveyance channels, and waters of the US. No discharges are allowed from concrete washout, paint and stucco washout; or from release oils, curing compounds, fuels, oils, soaps, and solvents. Equipment and wheel washing water that doesn’t contain detergent may be discharged on-site if it is treated before discharge.

p.	Design temporary BMPs for a 2 year 24 hour precipitation amount. Describe BMPs in the SWPPP and in SWPPP Amendments, including source controls, sediment controls, discharge points, and temporary and final stabilization measures. Describe the design, placement, installation, and maintenance of each BMP, using words, and drawings as appropriate. Describe the design capacity of sediment basins (including sediment ponds and traps). Provide a citation to the BMP Manual or publication used as a source for the BMP, including the manufacturer's or BMP manual specifications for installation CGP Part 5.3.6.2. If no published source was used to select or design a BMP, then the SWPPP or SWPPP amendment must state that “No BMP manual or publication was used for this design.”

q.	Describe the sequence and timing of activities that disturb soils and of BMP implementation and removal. Phase earth-disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization quickly. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities.

r.	Provide a legible site map or set of maps in the SWPPP, showing the entire site and identifying boundaries of the property where construction and earth-disturbing activities will occur, as described in the CGP Part 5.3.5.

s.	Identify the inspection frequency in the SWPPP:

(1)	Inspect once every seven (7) days regardless of the precipitation amount.

t.	Linear Project Inspections, described in CGP Part 6.5, are not applicable to this contract.

u.	The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, COE permit, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities which were not included in the Department’s permitting and consultation.

v.	The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the CGP and this specification. See Subsection 641-3.03 for more information.

4.	Recording Personnel and Contact Information in the SWPPP.

Identify the SWPPP Manager as the Storm Water Lead and Storm Water Inspector positions in the SWPPP. Document the SWPPP Manager’s responsibilities in Section 2.0 Storm Water Contacts, of the SWPPP template and:

a.	Identify that the SWPPP Manager does not have authority to sign inspection reports (unless the SWPPP Manager is also the designated project Superintendent).

b.	Identify that the SWPPP Manager cannot prepare the SWPPP unless the SWPPP Manager meets the Contract requirements for the SWPPP Preparer.

Include in the SWPPP, proof of AK-CESCL or equivalent certifications for the Superintendent and SWPPP Manager, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced permanently or temporarily, by an acting Superintendent or acting SWPPP Manager, record in the SWPPP (use form 25D-127) the names of the replacement personnel, the date of the replacement. For temporary personnel record their beginning and ending dates.

Provide 24-hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24-hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, proof of AK-CESCL, or equivalent certifications of ATS operators. Record the names of ATS operators and their beginning and ending dates, on Form 25D-127.

The Department will provide proof of AK-CESCL, or equivalent certifications for the Project Engineer, Storm Water Inspectors, and Monitoring Person (if applicable), and names and dates they are acting in that position. Include the Department’s staff certifications in the Appendix E.  Include the Department’s staff names, dates acting, and assignments, in Section 2.0 of the SWPPP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Prepare the HMCP using the DOT&PF template located at the following DOT&PF link; (http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml) for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

Designate a Contractor’s Spill Response Field Representative with 24 hour contact information. Designate a Subcontractor Spill Response Coordinator for each subcontractor. The Superintendent and Contractor’s Spill Response Field Representative must have 24-hour contact information for each Subcontractor Spill Response Coordinator and the Utility Spill Response Coordinator.

List and give the location and estimated quantities of hazardous materials (Including materials or substances listed in 40 CFR 117 and 302, and petroleum products) to be used or stored on the Project. Hazardous materials must be stored in covered storage areas.  Include secondary containment for all hazardous material storage areas.

Identify the locations where fueling and maintenance activities will take place, describe the activities, and list controls to prevent the accidental spillage of petroleum products and other hazardous materials. Controls include placing absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc). Spill response materials must be stored in sufficient quantity at each work location, appropriate to the hazards associated with that site.

Describe procedures for containment and cleanup of hazardous materials.  Describe a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Describe a plan for dealing with contaminated soil and water encountered during construction. Clean up spills or contaminated surfaces immediately.

Describe methods of disposing of waste petroleum products and other hazardous materials generated by the Project, including routine maintenance.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Describe methods of complying with the requirements of AS 46.04.010-900, Oil and Hazardous Substances Pollution Control, and 18 AAC 75. Include contact information for reporting hazardous materials and petroleum product spills to the Project Engineer and reporting to federal, state and local agencies.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.  Prepare and implement an SPCC Plan when required by 40 CFR 112; when both of the following conditions are present on the Project:

1.	Oil or petroleum products from a spill may reach navigable waters (as defined in 40 CFR 112); and

2.	Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project. The Superintendent shall sign and certify the SWPPP, Inspection Reports, and other reports required by the CGP, except the NOI and NOT. The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP submitted under Subsection 641-1.03.1, Inspection Reports, and other reports required by the CGP.

The Superintendent may assign certain duties to the SWPPP Manager, those duties may include:

1.	Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

2.	Ensuring the control of erosion, sedimentation, or discharge of pollutants;

3.	Directing and overseeing installation, maintenance, and removal of BMPs;

4.	Performing Inspections; and

5.	Updating the SWPPP including adding amendments and forms.

When Bid Item 641(7) is part of the Contract, the SWPPP Manager must be available at all times to administer SWPPP requirements, and be physically present within the Project Zone or the project office, for at least eight hours per day when construction activities are occurring.

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of this Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, environmental commitments, and historic preservation commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS. Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

Use the temporary seed mixture specified by special provision, or use annual rye grass if no temporary seed mix is specified.

Use soil stabilization material as specified in Section 727.

Use silt fences as specified in Section 729.

Use straw that is certified as free of noxious weed by the United States Department of Agriculture, Natural Resources Conservation Service, Local Soil, and Water Conservative District. Alaska Weed Free Forage Certification Program must be used when available. Hay may not be substituted for straw.

Use Oregon Scientific RGR126 wireless rain gauge with temperature, or Taylor 2751 Digital Wireless Rain Gauge with Thermometer, or approved equivalent.

641-2.06 CONTRACTOR REQUIREMENTS. Contractor, be familiar with the requirements of the CGP.

641-3.01 CONSTRUCTION REQUIREMENTS. Comply with the SWPPP and the requirements of the CGP Part 5.0.

1.	Before Construction Activity may Begin.

The following actions must be completed before Construction Activity begins:

a.	The SWPPP Preparer must visit the Project, the visit must be documented in the SWPPP Form (25D-106), and the SWPPP must be developed (or amended) with findings from the visit;

b.	The SWPPP must be approved by the Engineer on Form 25D-109;

c.	The Contractor must be authorized to begin by the Engineer;

d.	The Project eNOIs for the Department and for the Contractor, as well as any other eNOIs if there are additional operators, must be listed as Active Status on the DEC website;

e.	The Department approved SWPPP must be submitted to DEC and Local Government (when required); and

f.	The Contractor has transmitted to the Engineer an electronic copy of the approved SWPPP.

g.	The Delegation of Authority (Forms 25D-108 and 25D-107) for both the Contractor and DOT&PF Engineer are signed.

h.	Begin winter construction activity according to CGP Part 4.12.2, provided actions a, c, and g are completed. If winter construction activities may extend beyond spring thaw, the following actions must be completed before spring thaw:

(1)	Actions a through g, listed above, and

(2)	Appropriate control measures to minimize erosion and sediment runoff during spring thaw and summer rainfall are installed.

j.	Post notices.

Include the following information:

(1)	Copy of all eNOIs related to this project;

(2)	Location of the SWPPP.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can safely read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes.

k.	Install an outdoor rain gauge, per manufacturer’s guidance, in a readily accessible location on the Project.  Projects may utilize the nearest National Weather Service (NWS) precipitation gauge station, if within 20 miles of the project, to determine rainfall amounts during storm events.

l.	Delineate the site for both land disturbing activities and areas that will be left undisturbed.

m.	Install sediment controls and other BMPs that must be placed prior to the initiation of Construction Activity.

2.	During Construction.

Before subcontractors or utility companies begin soil-disturbing activities, provide to them copies of applicable portions of the SWPPP, and require them to sign a SWPPP Subcontractor Certification, Form 25D-105. Include SWPPP Subcontractor Certifications as an appendix to the SWPPP. Ensure subcontractors and utility companies understand and comply with the SWPPP and the CGP. Inform subcontractors and utility companies of SWPPP amendments that affect them in a timely manner. Coordinate with subcontractors and utility companies doing work in the Project Zone so BMPs, including temporary and final stabilization are installed, maintained, and protected from damage.

Provide on-going training to employees and subcontractors, on control measures at the site and applicable storm water pollution prevention procedures. Training must be specific to the installation, maintenance, protection, and removal of control measures CGP 4.14. Training must be given at a frequency that will be adequate to ensure proper implementation and protection of control measures, and no less frequently than once a month during construction activity. Document on the SWPPP Training Log. Form 25D-125, the dates, and attendees to these trainings. Include the SWPPP Training Log as an appendix to the SWPPP.

Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

Comply with Subsection 107-1.11 Protection and Restoration of Property and Landscape. Concrete washout must be fully contained.

Comply with CGP Part 4.8.2 for fueling and maintenance activities. Place absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

Comply with requirements of the HMCP and SPCC Plan, and all local, state, and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

Keep the SWPPP and HMCP current (refer to Subsection 641-2.01.3, SWPPP Considerations and Contents)

3.	Pollutant and Hazardous Materials Reporting Requirements.

If an incident of non-compliance occurs that may endanger health or the environment a report must be made, CGP, Appendix A, Part 3.4:

a.	Orally immediately report the incident to the Engineer,

b.	Orally within 24 hours after the permittee becomes aware of the incident, report to DEC, and

c.	In writing within five days after the permittee becomes aware of the circumstances complete the written noncompliance report on Form 25D-143, and file the written report with the DEC. Coordinate the report with the Engineer. Include in the report:

(1)	A description of the noncompliance and its causes;

(2)	The exact dates and times of noncompliance;

(3)	If not yet corrected the anticipated time the project will be brought back into compliance; and

(4)	The corrective action taken or planned to reduce, eliminate and prevent reoccurrence.

Notify the Engineer and COE regulatory Program immediately if there is incident of noncompliance with COE Permits.

Report spills of petroleum products or other hazardous materials to the Engineer and other agencies as required by law.  Use the HMCP and SPCC Plan (if available) for contact information to report spills to regulatory agencies.

4.	Corrective Action and Maintenance of BMPs.

Implement maintenance as required by the CGP, SWPPP, and manufacturer’s specifications, whichever is more restrictive.

a.	Implement corrective action:

(1)	If an incident of noncompliance with the SWPPP, or CGP is identified;

(2)	If an Inspection or the Engineer identifies the SWPPP or any part of the SWPPP is ineffective in preventing erosion, sedimentation or the discharge of pollutants;

(3)	If a required BMP was not installed according to the SWPPP schedule or phasing, or was installed incorrectly, or was not installed according to the CGP Part 4.0;

(4)	If a BMP is not operating as intended, has not been maintained in an effective operation condition, or is unable to effectively perform the intended function;

(5)	If sediment accumulates more than one-third of the distance of the above-ground height of the silt fence;

(6)	If sediment accumulates to more than one-half retention height for an inlet, check dam, berm, wattle, or other control measures;

(7)	If a prohibited discharge of pollutants, as specified in CGP Part 4.7, is occurring or will occur; or

(8)	If there is accumulation of sediment or other pollutants, that is in or near any storm water conveyance channels, or that may enter a discharge point or storm sewer system. If there is accumulation of sediment or other pollutants that is being tracked outside the project zone.

b.	Implement corrective actions so that they comply with the following time requirements:

(1)	For conditions that are easily remedied (i.e. removal of tracked sediment, maintenance of control measure, or spill clean-up), initiate corrective action within 24 hours and complete as soon as possible;

(2)	If a discharge occurs during a local 2-year, 24-hour storm event, initiate a corrective action a day after the storm event ends;

(3)	If installation of a new control measure is needed or an existing control measure requires redesign and reconstruction or replacement to make it operational, the corrective action must be completed within seven calendar days from the time discovered.

(4)	For all other conditions initiate corrective actions so both of the following requirements are met:

(a)	Corrective action is completed in time to protect water quality; and

(b)	Corrective action is completed no later than the Complete-by-Date that was entered in an Inspection Report (see Subsection 641-3.03.2 for more information).

If a corrective action is not implemented within the time requirements of this section, document the situation in the SWPPP, notify the Engineer, and implement corrective action as soon as possible.

If a corrective action could affect a subcontractor, notify the subcontractor within three days of taking the corrective action. Require in your written subcontract, that subcontractors must notify the Contractor within 24 hours of becoming aware of a condition that requires a corrective action.

5.	Stabilization.

a.	Stabilization may be accomplished using temporary or permanent measures.  Initiate stabilization of disturbed soils, erodible stockpiles, disposal sites, and of erodible aggregate layers so that all of the following conditions are satisfied:

(1)	Not later than the end of the next work day, following the day when the earth-disturbing activities have temporarily or permanently ceased (CGP 4.5.1.1 Note:).

(2)	As soon as necessary to avoid erosion, sedimentation, or the discharge of pollutants; and

(3)	As identified in the SWPPP.

b.	Land may be disturbed and stabilized multiple times during a project. Coordinate work to minimize the amount of disturbed soil at any one time. Do not disturb more soil than you can stabilize with the resources available.

c.	Temporarily stabilize from wind and water erosion portions of disturbed soils, portions of stockpiles, and portions of disposal sites, that are not in active construction. Temporary stabilization measures may require a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, non-erodible cover,  dust palliatives, or other approved methods.

d.	When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community, the hydro-seeder must be located at the project.

e.	Before applying temporary or permanent seeding, prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover. Apply seed and maintain seeded areas. Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

f.	Apply permanent seed according to Sections 618 and 724, within the time periods allowed by the CGP and the contract, at locations where seeding is indicated on the plans and after land-disturbing activity is permanently ceased.

g.	When installing a culvert or other drainage structure where stream bypass is not used, install temporary, or final stabilization concurrently or immediately after placing the culvert or drainage structure in a manner that complies with the SWPPP, applicable project permits and prevents discharge of pollutants. Install temporary and final stabilization:

(1)	At the culvert or drainage structure inlet and outlet; and

(2)	In the areas upstream and downstream that may be disturbed by the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure.

h.	Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install final or temporary stabilization when approved by the Engineer:

(1)	At the inlet and outlet of the culvert, drainage structure, or bridge;

(2)	In the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge; and

(3)	Under the bridge.

Within seven days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete, CGP 4.5.1.4,

Complete temporary stabilization within 14 days of initiating stabilization, CGP 4.5.1.2

6.	Ending CGP Coverage and BMP Maintenance in the Project Zone.

a.	The Engineer will determine the date that all the following conditions for ending CGP coverage have been met within the Project Zone:

(1)	Land disturbing activities have ceased;

(2)	Final Stabilization has been achieved on all portions of the Project Zone, according to the CGP PART 4.5.2 (including at Department furnished material sources, disposal sites, staging areas, equipment areas, etc.); and

(3)	Temporary BMPs have been removed.

b.	After the Engineer has determined the conditions for ending CGP coverage have been met, the Department will:

(1)	Send written notice to the Contractor with the date that the conditions were met;

(2)	Submit an eNOT to DEC; and

(3)	Provide a copy of the eNOT and DEC’s acknowledgement letter to the Contractor.

The Contractor is responsible for ending permit coverage within the Project Zone, by submitting an eNOT to DEC within 30 days of meeting the conditions for ending CGP coverage. The Contractor is responsible for BMP maintenance and SWPPP updates until permit coverage is ended.

If the Contractor’s CGP eNOI acreage includes Support Activities and any other areas where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must amend the SWPPP and separate SWPPP2(s), to indicate the Department’s CGP coverage has ended, and the Department is no longer an Operator within the Project Zone.

The Contractor must indicate in the SWPPP the areas that have reached Final Stabilization, and the dates land disturbing activities ended and Final Stabilization was achieved. The Contractor must submit an eNOT to DEC, and insert copies of the Department’s and the Contractor’s eNOTs with DEC’s acknowledgement letters in the appendix of the SWPPP.

The Contractor must submit a copy of each signed eNOT and DEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response.

The Contractor is responsible for coordinating local government inspections of work and ending permit coverage with local government. See Subsection 641-1.03.5 for more information.

7.	Transmit final SWPPP.

Transmit one copy of the final SWPPP, including all amendments, appendices, and maps, to the Engineer; when the project eNOTs are filed, or within 30 days of the Department’s eNOT being filed, whichever is sooner. Transmittal must be by both electronic and hard copy.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.

The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP, and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown.  Update on-site postings if records are relocated during winter shutdown. Provide the Department with copies of all Records.

Retain Records and a copy of the SWPPP, for at least three years after the date of eNOT. If EPA or DEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the retention period expires, retain the SWPPP and all Records related to the SWPPP and CGP until at least three years after EPA and/or DEC has determined all issues related to the investigation  are settled.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them.  See CGP Parts 5.10, 6.6 and 9.5.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS. Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP.  Update SWPPP Corrective Action Log Form 25D-112, SWPPP Amendment Log Form 25D-114, SWPPP Grading and Stabilization Activities Log Form 25D-110, SWPPP Project Staff Tracking Form 25D-127, and SWPPP Daily Record of Rainfall Form 25D-115.  For active projects, update the Records daily.

1.	Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s Storm Water Inspector jointly, unless approved by the Engineer, when:

a.	One of the inspectors is not on site, access is only by air, and weather delayed or canceled flights;

b.	One of the inspectors is sick;

c.	The project is on a reduced frequency inspection schedule with no staff on site, the only access to the site is by air, and it is economical to send only one inspector; or

d.	When the Engineer determines a safety concern which makes joint inspection impracticable.

When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within three days of the Inspection date and document the date of the report transmittal.

2.	Inspection Reports.

Use only the DOT&PF SWPPP Construction Site Inspection Report, Form 25D-100 to record Inspections. Changes or revisions to Form 25D-100 are not permitted; except for adding or deleting data fields that list: Location of Discharge Points, and Site Specific BMPs. Complete all fields included on the Inspection Report form; do not leave any field blank.

Insert a Complete-by-Date for each corrective action listed that complies with:

a.	Section 641-3.01 (4), and

b.	The CGP.

Provide a copy of the completed, unsigned Inspection Report to the Engineer by the end of the next business day following the inspection.

The Superintendent must review, correct errors, and sign and certify the Inspection Report, within three days of the date of Inspection. The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. Deliver the signed and certified Inspection Report to the Engineer on the same day the Superintendent signs it.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days.

The Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

If subsequent corrections to the certified Inspection Report are needed, document the corrections in an amendment memo that addresses only the omitted or erroneous portions of the original Inspection Report. The Superintendent and the Engineer must both sign and certify the amendment memo. The issuance of a amendment memo does not relieve the Contractor of liquidated damages that may have been incurred as a result of the error on the original certified inspection report.

3.	Inspection before Seasonal Suspension of Work.

Conduct an Inspection before seasonal suspension of work to confirm BMPs are installed and functioning according to the requirements of the SWPPP and CGP.

4.	Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

If the Engineer approves and the entire site is stabilized, the frequency of inspections may be reduced to at least one inspection every 30 days.  At actively staffed sites, inspect within two business days of the end of a storm event that, results in a discharge from the site.

When work is suspended due to fall freeze-up, the Engineer may suspend inspection requirements after fourteen days of freezing conditions if:

a.	Soil disturbing activities are suspended; and

b.	Soil stabilizing activities are suspended.

Inspections must resume according to the normal inspection schedule identified in the SWPPP, at least 21 days before anticipated spring thaw. See CGP Part 6.2.3.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall during seasonal suspension of work.  If so, resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in runoff.  Resume recording land disturbance and stabilization activities on the Grading and Stabilization Activities Log when Construction Activity resumes.

5.	Stabilization before Fall Freeze-up and Spring Thaw.

Construction Activities within the Project Zone must be stabilized with appropriate BMPs prior to the anticipated date of fall freeze-up, in accordance with the CGP, Section 4.12.

Exceptions to stabilization prior to anticipated date of fall freeze up include:

a.	When stabilization activities are precluded by snow cover or frozen ground conditions prior to the anticipated date of fall freeze up, or

b.	When winter construction activity is authorized by the Engineer and conducted according to the contract.

Construction Activities within the Project Zone must be stabilized with appropriate BMPs prior to spring thaw, as defined in the CGP.

6.	Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion.

7.	Items and Areas to Inspect.

Conduct Inspections of the areas required by the CGP and SWPPP.

8.	SWPPP Amendments and SWPPP Amendment Log.

The Superintendent and the SWPPP Manager are the only persons authorized to amend the SWPPP and update the SWPPP Amendment Log Form 25D-114. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

a.	Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

b.	If an Inspection identifies, that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

c.	Whenever an Inspection identifies a problem that requires additional or modified BMPs

d.	Whenever a BMP is modified during construction or a BMP not shown in the original SWPPP is added;

e.	If the Inspection frequency is modified (note beginning and ending dates); or

f.	When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01.4.

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than seven days following identification of the need for an amendment.  Every SWPPP Amendment must be signed and dated. Cross-reference the amendment number with the Corrective Action Log or SWPPP page number, as applicable. When a BMP is modified or added, describe the BMP according to Subsection 641-2.01.3.

Keep the SWPPP Amendment Log current. Prior to performing each scheduled Inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log as an appendix to the SWPPP.

9.	Site Maps.

Document installation, routine maintenance, and removal of BMPs by making notes on the SWPPP Site Maps. Include the date and the recording person’s initials by these notes. Identify areas where Construction Activities begin, areas where Construction Activities temporarily or permanently cease, and areas that are temporarily or permanently stabilized.

10.	Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112. Document the need for corrective action within 24 hours of either:

a.	Identification during an inspection; or

b.	Discovery by the Department or Contractor’s staff, a subcontractor, or a regulatory agency inspector.

Modification or replacement of a BMP, installation of a new BMP not shown in the original SWPPP,  overdue BMP maintenance, or other reasons listed as corrective actions in 641-3.01.4 must be documented on the Corrective Action Log.

Within 24 hours of discovery, update the Corrective Action Log Form 25D-112, with the date of discovery and proposed corrective action. If discovered during an inspection, update log with inspection date and proposed corrective actions noted on the Inspection Report.  If discovered outside of an inspection, update the log with the date of discovery, the proposed corrective action, and the date the corrective action was completed.

After the corrective action has been accomplished, note in the Corrective Action Log the action taken and if a SWPPP amendment was needed. Date and initial the entry.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log as an appendix to the SWPPP.

11.	Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection. Keep the Grading and Stabilization Activities Log organized and completed to demonstrate compliance with the CGP Part 4.5.

Keep the Grading and Stabilization Activities Log as an appendix to the SWPPP.

12.	Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled Inspection.  Keep the Daily Record of Rainfall as an appendix to the SWPPP.

13.	Staff Tracking Log.

Use the SWPPP Project Staff Tracking, Form 25D-127, to keep staff records current. Include Records of the AK-CESCL or equivalent qualifications for the Superintendent, SWPPP Manager, ATS operator, any acting Superintendent and acting SWPPP Managers, and beginning and end dates for temporary personnel assignments related to administration of the CGP or Section 641. Update the SWPPP Staff Tracking Log within 24 hours of any changes in personnel, qualifications, or other staffing items related to administration of the CGP or Section 641.

641-3.04 FAILURE TO PERFORM WORK. The Engineer has authority to suspend work and withhold monies, for an incident of non-compliance with the CGP, or SWPPP, that may endanger health or the environment or for failure to perform work related to Section 641.

1.	Non-compliance.

a.	Incidents of Non-compliance. Failure to:

(1)	Obtain appropriate permits before Construction Activities occur;

(2)	Perform SWPPP Administration;

(3)	Perform timely Inspections;

(4)	Update the SWPPP;

(5)	Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms to the Engineer;

(6)	Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

(7)	Perform duties according to the requirements of Section 641; or

(8)	Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control.

b.	Notice of non-compliance, either oral or written will include:

(1)	Reason/defects

(2)	Corrective actions required

(3)	Time allowed for completing the corrective action

c.	Levels of Non-compliance and Response correspond with harm to the workers, the public or the environment and whether the harm is:

(1)	Not-imminent, the Engineer will either orally or in writing, or both, provide notice to the Contractor indicating the incident of non-compliance.

Contractor's that take corrective action and complete the action to the satisfaction of the Engineer, within the time specified, may return to the status of compliance, and avoid elevating the response to imminent.

.

(2)	Imminent, the Engineer will orally provide notice to the Contractor of non-compliance and promptly provide written notice to suspend work until corrective action is completed.

Additional actions, taken against the Contract whether the level of non-compliance is Not-imminent or Imminent, may include:

(a)	Withholding monies until corrective action is completed

(b)	Assessing damages or equitable adjustments

(c)	Employing others to perform the corrective action and deduct the cost

No additional Contract time or additional compensation will be allowed due to delays caused by the Engineer’s suspension of work.

641-3.05 ACCESS TO WORK.

The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies. See CGP Part 6.6.

641-4.01 METHOD OF MEASUREMENT.

Section 109 and as follows:

Item 641(1), and 641(7), are lump sum.

Item 641(2), measured on a contingent sum basis as specified by the Directive authorizing the work.

Item 641(6), measured on a contingent sum basis with withholding determined by the Department.

TABLE 641-1 BMP VALUES - RESERVED

Liquidated Damages assessed according to Table 641-2 are not an adjustment to the Contract amount. These damages charges are related to Contract performance but are billed by the Department to the Contractor, independent of the Contract amount. An amount equal to the Liquidated Damages may be withheld for unsatisfactory performance, from payment due under the Contract, until the Contractor remits payment for billed Liquidated Damages.

TABLE 641-2- VERSION C

EROSION, SEDIMENT AND POLLUTION CONTROL – LIQUIDATED DAMAGES

| Code | Specification Section Number and Description | Deductible Amount in Dollars | Cumulative Deductible Amounts in Dollars |
| --- | --- | --- | --- |
| A | 641-1.04 Failure to have a qualified (AK-CESCL or equivalent) SWPPP Manager | Calculated in Code B or F |  |
| B | Failure to meet SWPPP requirements of: (1) 641-2.01.1 Name of SWPPP Preparer (2) Not Applicable (3) 641-3.03.8 Sign and Date SWPPP amendments with qualified person 641-2.01.4 SWPPP Include approving person’s name and AK-CESCL expiration date (4) 641-3.02 Records maintained at project and made available for review | $750 per omission |  |
| C | Not applicable. |  |  |
| D | 641-3.03.5 Failure to stabilize a Project prior to Fall Freeze-up | $5,000 per Project per year |  |
| E | 641-2.01.1. Failure to conduct pre-construction inspections before Construction Activities on all projects greater than 1 acre. | $2,000 per Project |  |
| F* | 641-3.03. Failure to conduct and record CGP Inspections 641-3.03.1 Personnel conducting Inspections and Frequency 641-3.03.2 Inspection Reports, use Form 25D-100, completed with all required information | $750 per Inspection | Additional $750 for every additional 7 day period without completing the required inspection. |
| G | 641-3.01.4 Corrective action, failure to timely accomplish BMP maintenance and/or repairs. In effect until BMP maintenance and/or repairs is completed. | $500 per Project per day |  |
| H | 641-3.01.3 Failure to provide to the Engineer and DEC a timely oral noncompliance report of violations or for a deficient oral noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| I | 641-3.01.3 Failure to provide to the Engineer and DEC a timely written noncompliance report, use Form 25D-143, of violations or for a deficient written noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| J | 641-3.04 Failure to comply with the requirements of the CGP, approved SWPPP, and Section 641, except as listed above | $750 per occurrence for the first day of noncompliance | Additional $750 for every day the deficiency remains uncorrected |

*CODE F.	Liquidated Damages according to Code F will not be billed for typographic errors and minor data entry errors, except the liquidated damages will be billed for these errors when:

	the Contractor has previously been notified and subsequent inspection reports repeat the same or similar error,

	multiple inspection reports are submitted after the submission due date and the same or similar errors are repeated on multiple overdue reports,

	an error in recording the inspector's AK-CESCL certification date results in an inspector performing the inspection during a period when their certification was lapse or was otherwise invalid

641-5.01 BASIS OF PAYMENT. See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

Item 641(1) Erosion, Sediment and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and Record keeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Item 641(2) Temporary Erosion, Sediment and Pollution Control. At the contingent sum prices specified for all labor, supervision, material, equipment, and incidentals to install, maintain, remove, and dispose of approved temporary erosion, sedimentation, and pollution control BMPs required to implement the SWPPP and SPCC Plan.

Item 641(6) Withholding. The Engineer may withhold an amount equal to Liquidated Damages, assessed according to Section 641, from payment due the Contractor. Liquidated Damages for violations of the Contract, CWA, and CGP are determined by the Engineer according to Table 641-2. The Engineer may withhold payment due the Contractors until the Contractor pays the Liquidated Damages to the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Item 641(7) SWPPP Manager. At the Contract lump sum price for a SWPPP Manager that conforms to this specification. When Item 641(7) appears in the Bid Schedule, the SWPPP Manager must be a different person than the superintendent, and must be physically present during construction activity with duties and authority as described in Subsection 641-2.04. When Item 641(7) does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to Item 641(1).

Subsidiary Items.  Temporary erosion, sediment, and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641(1) Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641. This work includes but is not limited to:

1.	Dewatering;

2.	Shoring;

3.	Bailing;

4.	Permanent seeding;

5.	Installation and removal of temporary work pads;

6.	Temporary accesses;

7.	Temporary drainage pipes and structures;

8.	Diversion channels;

9.	Settling impoundment; and

10.	Filtration.

Permanent erosion, sediment, and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense.  Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion, Sediment and pollution Control Administration	Lump Sum

641(2)	Temporary Erosion, Sediment and Pollution Control	Contingent Sum

641(6)	Withholding	Contingent Sum

641(7)	SWPPP Manager	Lump Sum

CR641-043017R

Special Provisions

Delete Section 642 and replace with the following:

SECTION 642
CONSTRUCTION SURVEYING AND MONUMENTS

642-1.01 DESCRIPTION. Perform surveying and staking essential for the completion of the project and perform the necessary calculations required to accomplish the work in conformance with the Plans and Specifications and industry standard engineering and survey practice.

Furnish and maintain facilities, equipment, and services specified in this section for Digital Terrain Modeling (DTM).  All furnished facilities and equipment remain your property when you complete the work.

642-1.02 DEFINITIONS.

1.	Break Line: A break line defines the horizontal location where TIN lines must break, and snap to the vertical location of the break line.

2.	Catch Point: In the cross section of a road, the point at which the fill or cut slope intersects the edge of the existing ground.

3.	CAD:  Computer-Aided Design.

4.	CORS:  Continuously Operating Reference Station.

5.	DTM: Digital Terrain Model. A computer generated 3D model representing the project terrain, and based on the association of features such as alignments, profiles, sections, grading lines, points, and surfaces.

6.	GLONASS: A radio-based satellite navigation system operated by Russia. GLONASS is an alternative and is complementary to the United States Global Positioning System.

7.	GNSS:  Global Navigation Satellite System.

8.	GPS: Global Positioning System; A radio-based satellite navigation system operated by the United States.

9.	Hinge Point: In the cross section of a road, the point at which any slope intersects another slope of different angle.

10.	Monument: A fixed physical object marking a point on the surface of the earth; used to commence or control a survey; mark the boundaries of a parcel of land; or the centerline of a right-of-way corridor. Monuments will be Primary or Secondary, as shown in the Plans.

11.	Neat-line: Defines the geometric limits of a material, as indicated by the typical section, profile, and alignment.

12.	NGS: National Geodetic Survey; United States Government Agency that provides information and products related to the definition and management of the NSRS.

13.	NSRS: The National Spatial Reference System.

14.	OPUS: On-line Positioning User Service; The National Geodetic Survey operates OPUS as a means to provide GPS users easier access to the NSRS.

15.	Point: An identified spot located on the surface of the earth. For the purpose of this definition, a point can be either physical or electronic depending on the context in which it is used. Physical points include PK nails, wooden hubs, rebar, large nails, or other structures capable of being utilized as a marker. Electronic points include all points generated by computers or electronic surveying equipment.

16.	PPK: Post Processed Kinematic; PPK surveys are similar to RTK surveys, except there is no radio communication between the reference station and the rover, so the rover cannot process a position in “real time”. Survey data from both the reference station and rover is imported into GPS processing software to determine the measured position.

17.	Reference Monument: A monument placed at a known distance and direction from a property corner or other survey point, usually not on a property or survey line. A reference monument is employed to perpetuate a corner/point that cannot be monumented at its true location or where the corner monument is subject to destruction.

18.	RTK: Real Time Kinematic; RTK surveys utilize two or more receivers with at least one receiver remaining stationary over a known coordinate. The radio at the reference station broadcasts its position to the rovers and the system processes the baselines in “real time” allowing for project coordinate information to be gathered and analyzed during the actual field survey.

19.	Slope Staking: The process of using measurements and calculations to determine where to begin a cut or fill, the slope ratio, and the depth of the cut or fill.

20.	Static: Static survey methods require multiple GPS receivers to collect data over the course of a long period of time. The data collected by the receivers is downloaded into a GPS processing software program to determine the measured position.

21.	Surveyor: The Contractor’s Professional Land Surveyor placed in “responsible charge”, and currently registered in the State of Alaska as defined in AS 08.48.341.

22.	Tessellation Spacing: The distance along a line or an arc that a TIN point is created.

23.	TIN: Triangulated Irregular Network; A vector based representation of a physical land surface.

24.	Witness Corner: A point or monument placed at a known distance and direction from a property corner or other survey point. A witness corner is employed to witness the location of a corner/point that cannot be monumented at its true location.

25.	Weeding: A procedure used to limit the frequency of information displayed.

642-2.01 MATERIALS.

1.	Monument Cases: Use castings meeting AASHTO M 105, Class No. 30A. Coat castings with a bituminous damp-proof coating. Bolting tops shall be used.

2.	Primary Monument: A minimum 2 3/8” diameter nonferrous pipe at least 30 inches long, with a minimum 4-inch flange at the bottom and having magnets attached at the top and bottom. A minimum 3 1/4” diameter nonferrous metal cap shall be permanently attached to the top. Mark the cap around the outside edge with the words “STATE OF ALASKA DOT&PF". Permanently stamp every monument with the Surveyor’s registration number, the year set, and the point/corner identification. Orient cap so that the data may be read when the reader is facing north, except for centerline monuments that will be oriented to be read facing up-station.

3.	Secondary Monument: A minimum 5/8 inch x 30 inch rebar with a 2-inch aluminum cap attached to the top. Permanently stamp every secondary monument with the Surveyor’s registration number, the point/corner identification, and the year set.

CONSTRUCTION REQUIREMENTS

642-3.01 GENERAL REQUIREMENTS. Work classified as Land Surveying under AS 08.48, and work involving the location, control, and monumentation of construction centerline and right-of-way, shall be performed by or directly under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor.

Use competent, qualified personnel and suitable equipment for construction surveying activities. The Surveyor’s personnel shall be supervised and trained in the avoidance of systematic errors. The Surveyor’s personnel shall be familiar with geodetic concepts and least-squares adjustments. Correcting errors resulting from the operations of said personnel shall be at the Contractor expense. The Contractor is responsible for the accuracy of the work.

Schedule a mandatory Pre-Survey Conference with the Engineer, Contractor, Surveyor, and all personnel who are to be involved in the survey work, two weeks prior to beginning survey work. The purpose of this meeting will be to discuss methods and practices of accomplishing the required survey work.

Furnish computer services to accomplish the work. All data shall be signed by the Surveyor for completeness and accuracy. As soon as practical after completion of the work, and in no case later than acceptance of the project, deliver field books, computer forms and computer output data to the Engineer. Furnish all computer generated data in a file format and medium that is compatible with Department software. This data becomes the property of the State of Alaska.

Furnish field survey notes. Keep field notes in standard bound notebooks in a clear, orderly, and neat manner consistent with the State of Alaska DOT&PF Construction Surveying Requirements. Make field books available for inspection by the Engineer’s project personnel at any time. Copies of the field books shall be kept in a separate secure location.

Furnish all equipment including but not limited to vehicles, stakes, measuring tapes, levels, rods, lasers, GPS receivers, total stations, traffic control devices, safety devices and other equipment necessary for establishing, checking and maintaining the required points, lines and grades.

Furnish traffic control necessary for surveying activities in accordance with Section 643, and the latest edition of the Alaska Traffic Manual (ATM). Outfit all field employees with appropriate High Visibility Clothing as defined in Section 643, Subsection 3.11.

The Engineer may randomly spot check the Contractor's surveys, staking, and computations. The Department assumes no responsibility for the accuracy of the work.

The Engineer has the right to communicate directly with the Surveyor. Any communication regarding changes to the original scope of work shall go through the Contractor.

The Surveyor is responsible for:

1.	Maintaining registration as a Professional Land Surveyor in the State of Alaska.

2.	Maintaining familiarity with the site conditions and progress of the project.

3.	Determining the accuracy required for each survey stake.

4.	Following the State of Alaska DOT&PF Construction Surveying Requirements.

5.	Notifying the Engineer of conflicts and changes necessary due to utilities, match point variations, design revisions, or other variables.

6.	Slope Staking.

7.	Staking all clearing and/or grubbing limits. Clearly identify all trees that are specified to remain.

8.	Staking and hubbing all layers of material shown in the typical sections, including the bottom of excavation, top of borrow, top of base course, and top of surcharge.

9.	Staking all culverts, curbs, inlets, and other drainage appurtenances.

10.	Staking all bridge and pedestrian over/under-crossings.

11.	Staking all right-of-way and material source limits.

12.	Rabbit tracking for temporary and permanent pavement striping, and pavement marking devices.

13.	Weekly settlement platform elevation monitoring.

14.	Development of DTM’s, and plotted cross sections.

15.	As-built and Topographic surveying.

16. Performing elevation readings on settlement platforms.

17.	Removal and disposal of all flagging, lath, stakes and other staking material after the Project is completed. Burning of material is not allowed on the project.

18.	All other surveying and staking necessary to complete the project.

642-3.02 MONUMENTS.  The Department will reference and replace all monuments identified on the plans. The Surveyor shall notify the Engineer immediately of any monuments encountered that are not identified on the plans. The Engineer will determine whether the monuments encountered are to be referenced or adjusted by the Surveyor or the Department.

If directed by the Engineer, the adjustment of monument cases or the referencing of monuments not identified on the plans will be considered additional work and paid by 642(3), Three Person Survey Party. Set existing monument cases to be adjusted to new elevations in the manner and at the elevations directed.

The Surveyor shall complete and stamp a State of Alaska Land Survey Monument Record form for each primary and secondary monument referenced. Provide the required survey information on the form in accordance with statutory requirements, including the project name/number, section, township, and range. Meet requirements for recording at the District Recorder’s Office in which the project is located for each monument record. Deliver conforming copies of the recorded forms to the Engineer before monument removal or disturbance.

642-3.03 SURVEY CONTROL. The basis of project control is identified in the Survey Control Sheet. Use the calibration parameters shown in the Survey Control Sheet to Calibrate/Localize/Convert to the local project coordinate system. Contact the AK DOT&PF Central Region Survey Manager through the Engineer for calibration parameters if they are not shown in the plans. Independently recover and verify all survey control points shown in the Survey Control Sheet. Establish and verify new reference points where required, to replace missing points. Notify the Engineer immediately if a reference point is discovered to be in error, or a reset point is not in harmonious relationship to the existing control points. Provide the Engineer a signed hard copy verifying vertical loop closure of project control points.

The use of RTK is not an acceptable method for establishing additional horizontal or vertical control. Horizontal control points may be established using Static GPS or conventional traversing methods. Vertical control points shall be established with differential levels.

Survey accuracy requirements shall conform to the minimums listed in the State of Alaska DOT&PF Construction Surveying Requirements.

642-3.04 GPS SURVEYS. The specifications described in this Section are not intended to discourage the use of new GPS procedures and techniques. Procedures that are not defined by this specification may be allowed if approved by the AK DOT&PF Central Region Survey Manager, through the Engineer.

1.	General Requirements:

a.	All surveying shall be done in the local project coordinate system.

b.	OPUS shall be used for the determination of Reference Station positions only, and shall not be used directly for producing final positions for any Static, Fast Static, RTK or PPK surveys. OPUS may be used as a tool for verification of the final positions obtained from these types of surveys.

2.	GPS Equipment: Survey Grade dual frequency GPS receivers shall be used. For static surveys these shall be set up on adjustable leg tripods at a minimum. Fast or Rapid Static GPS surveys require a bipod at a minimum. RTK or PPK surveys may use fixed or adjustable poles, or secure lashings to vehicles.

3.	GPS Reference Stations:

a.	All Reference Stations shall be approved by the AK DOT&PF Central Region Survey Manager through the Engineer, prior to conducting any GPS surveys.

b.	Primary Reference Stations shall meet current NGS CORS standards. Secondary Reference Stations may be used temporarily when a Primary Reference Station is not available.

c.	Primary Reference Stations shall be permanently mounted and shall not change throughout the duration of the project.

d.	Secondary Reference Stations may be tripod mounted, however, GPS receivers shall never be mounted on aluminum tripods.

e.	All Reference Stations shall be tied to an OPUS derived position, and on the NAD83 datum. Submit GPS data files for a minimum of 2 days, 12 hours per day, 5 second epoch to OPUS to determine the final position. The OPUS derived position shall be determined at the beginning of the project, and shall not change throughout the duration of the project unless approved by the Engineer. Notify all users immediately if any changes are made to the Reference Station’s position. If OPUS is unable to process a position, the Reference Station shall be tied to existing project control.

f.	Reference Stations shall be physically located in clear view of the sky. Avoid locations near cellular towers or other areas that may disrupt satellite signal reception. Avoid locations near large flat surfaces such as buildings, large signs, fences, and other objects that may cause multi-path interference.

g.	Reference Stations shall be located to provide maximum coverage of the project area.

h.	Store 5 second epoch data, and post data online for use by the Engineer.

i.	GNSS enabled Reference Stations are allowed.

4.	RTK Surveys:

a.	The Surveyor shall follow prudent practices when conducting RTK surveys. The NGS has published a draft manual titled National Geodetic Survey User Guidelines For Classical Real Time GNSS Positioning, v.2.0.3 issued in September, 2008. The Surveyor shall become familiar with this manual, in order to better understand prudent practices. Copies of the draft manual may be available upon request or may be downloaded from the following web site: http://www.ngs.noaa.gov/PUBS_LIB/NGSRealTimeUserGuidelines.v2.0.4.pdf.

b.	RTK surveys may not be used to permanently mark or delineate Right-Of-Way.

5.	Local Coordinate Calibration:

a.	Use GPS calibration parameters if they are provided on the Survey Control Sheet. If GPS calibration parameters are not given, develop a local site calibration based on existing project control. All included control points shall have WGS84 positions that were observed by either a GPS Static or Fast Static network, as well as the final adjusted project control coordinate values that match the values listed on the Survey Control Sheet. The calibration shall consist of the following conversion parameters; Rotation, Translation, Scale, and GPS derived orthometric heights. Values listed on the Survey Control Sheet shall be held fixed in any adjustment, barring any large residuals. Notify the Engineer of any large residuals so that the problems can be identified and corrected. Submit a signed hard copy of the calibration parameters, residuals, and related control points to the Engineer for approval before staking activities begin.

b.	Perform a local calibration each time the coordinates of the reference station change.

6.	GPS Data Summary Report:

a.	Generate reports for all surveyed points, including the Point Number, Northing, Easting, Elevation, Point Code, Annotation(s), Date, Time, residuals, observation (start and stop) times, and antenna height information. Summary reports shall bear the signature and seal of the Surveyor.

b.	The Engineer may require the Contractor to re-survey specified points at no cost to the Department if the Survey doesn’t meet the minimum accuracy requirements defined in the State of Alaska DOT&PF Construction Surveying Requirements.

7.	Weather Conditions: The Surveyor shall follow prudent practices when conducting GPS surveys in inclement weather. The following is recommended as a guideline:

a.	Regularly observe surface and solar weather forecasts prior to planning survey activities.

b.	Use sound practical judgment when performing surveys during inclement weather conditions.

c.	Observations should never be conducted during an electrical storm.

d.	Note significant or unusual weather conditions in the field notes, data collector, or receiver.

642-3.05 TOPOGRAPHIC SURVEYS. Topographic surveys shall be conducted under the direct supervision of the Surveyor. The purpose of a topographic survey is to gather field data to determine the configuration (relief) of the surface of the earth (ground). Use all data collected to generate topographic DTM surfaces as defined in Section 642-3.07, Digital Terrain Models. All data becomes the property of the State of Alaska. Conduct topographic surveys as follows:

1.	General Requirements:

a.	Collect topographic data within the right-of-way limits.

b.	Keep all shots 50 ft or closer, as necessary to accurately define all surface features within the roadway corridor.

c. 	Keep a field book of notes describing changes or errors of rod heights, point descriptors, or other annotations necessary to verify all electronic data.

d. 	Identify each point with a point number. Multiple points with the same point number are not permitted.

e. 	Identify each shot with the appropriate point code. Break line points shall be separately identifiable from ground shots.

f. 	Append any additional information required to further describe a point with point annotations.

g. 	Develop a summary of standard point codes for all points used on the project.

h. 	Develop a summary of standard point descriptors to identify all point codes used on the project (i.e. Edge of Pavement is the point descriptor corresponding to the EP point code).

2.	Functional Requirements: The purpose of a topographic survey is to develop an appropriate DTM as defined in Section 642-3.07. Conduct a topographic survey to meet the appropriate functional requirements as defined below:

a.	As-built Surfaces – Conduct a survey of all finished roadway surfaces, embankments, ditches and other topographic features as required to accurately define the project topography.

b.	Excavation Surfaces – Conduct a survey of original grade (upper) surfaces, and bottom of excavation (lower) surfaces, as necessary to produce DTM volumetric quantities. Follow the requirements listed below:

(1)	Upper surface – Survey prior to excavation. Topographic data may be collected prior to grubbing and pavement removal, and adjusted by the average depth removed as measured in the field.

(2)	Lower surface – Survey after the final grade has been established by excavation.

c.	Embankment Surfaces – Conduct a survey of excavated or original grade (lower) surfaces, and top of embankment (upper) surfaces, as necessary to produce DTM volumetric quantities. Follow the requirements listed below:

(1)	Upper surface – Survey after the final grade has been established.

(2)	Lower surface – Survey prior to the placement of embankment. If only grubbing or pavement removal is required prior to placement of embankment, the topographic data may be collected prior to grubbing and pavement removal and adjusted by the average depth removed, as measured in the field. If excavation is required prior to placement of embankment, survey only after excavation activities have been completed.

3.	Accuracy Tolerance Limits: The Surveyor shall check into and collect primary control monument locations to ensure the data being collected meets the minimum Horizontal and Vertical Accuracy Tolerances. This shall serve as a basis of acceptance for the topographic data collected by the Surveyor. The Horizontal and Vertical Accuracy Tolerances will be used to check for systematic error, and will be evaluated by comparing all control check shots taken during the topographic survey to the monument’s location as defined on the Survey Control Sheet. The Volumetric Accuracy Tolerance will be used to check for random and operator error, and will be evaluated by comparing the Contractor furnished DTM with an independent DTM developed by the Department. The Volumetric Accuracy Tolerance shall be applied only to survey data that is used to calculate volumetric quantities.

a.	Horizontal Accuracy Tolerance – Check shots shall be within ± five hundredths (0.05) of a foot of the monument’s horizontal position. If any of the data doesn’t meet the minimum the horizontal tolerance, the Engineer may require the Contractor to re-survey the non-conforming points at no additional cost to the Department.

b.	Vertical Accuracy Tolerance – Check shots shall be within ± one tenth (0.10) of a foot of the monument’s vertical position. If any of the data doesn’t meet the minimum vertical tolerance, the Engineer may direct the Contractor to re-survey the non-conforming points at no additional cost to the Department.

c.	Volumetric Accuracy Tolerance – The Department will determine the volumetric error on randomly selected areas, including at least 20% of the area within the slope limits.  The Department will calculate the volumetric error as follows:

(1)	Determine the net volume by comparing the Contractor’s DTM to the Department’s DTM.

(2)	Determine the accepted volume by comparing the Department’s DTM to the appropriate neat-line surface.

(3)	Determine the volumetric error by dividing the net volume by the accepted volume.

The Engineer may require the Contractor to re-survey any areas that exceed 5% error at no additional cost to the Department.

4.	Control Check Requirements: Collect local project control data at the following minimum frequency:

a.	Every time the instrument is turned on, at the beginning of the survey session.

b.	Prior to every time the instrument is turned off, at the end of the survey session.

c.	Every time the instrument is moved (radial survey).

d.	Every time the backsight is moved (radial survey).

e.	Every time the actual or broadcasted position of the Reference Station changes (GPS survey).

5.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted and electronic as-built surfaces (developed per Section 642-3.07) showing major and minor contours. Standard contour intervals shall be 5 ft (major) and 1 ft (minor).

b.	All field books noting any errors, corrections, or changes to the data.

c.	All electronic survey data in a comma delimited ASCII file in PNEZD format (Point number, Northing, Easting, Elevation, and Description).

- Letter of conformance signed and sealed by the Surveyor, certifying that the Topographic Survey meets the minimum Horizontal and Vertical accuracy requirements. Attach all backup data and calculations.

642-3.06 AS-BUILT SURVEYS. As-built surveys shall be conducted under the supervision of the Surveyor. The as-built survey shall document the final locations of roadways, topographic surfaces, structures, and utilities within the ROW project limits. The Surveyor shall maintain communication with the Contractor, Sub-Contractor or Utility Company as necessary to coordinate surveying activities. Surveying activities shall be conducted as soon as possible as each phase of the project is completed, and to avoid scheduling conflicts. The survey will be used to verify that the contracted work items conform to the plans and specifications. All survey data becomes the property of the State of Alaska.

1.	General Requirements:

a.	Topographic Survey of all roadway and pedestrian corridors, in accordance with Section 642-3.05, Topographic Surveys.

b.	Utility Survey of all existing and re-located utilities. Record the horizontal and vertical location of all underground and overhead utilities. Take digital photos of all exposed utility crossings. Identify the location of each photo taken, including the approximate northing, easting, and bearing.

c.	Structural Survey of all existing and re-located structures, including bridges, tunnels, manholes, signs, fences, guard rails, walls, and foundations.

2.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted as-built drawings showing the final surveyed locations of all roadways, topographic surfaces, structures, and utilities. Plotted drawings shall be identified by the Project name and number, and bear the signature and seal of the Surveyor.

b.	Printed color photos, identifying the location of all underground utility crossings.

c.	All field books used to conduct the as-built survey.

d.	All DTM and point data files generated by the as-built survey.

642-3.07 DIGITAL TERRAIN MODELS. Develop all Digital Terrain Models using CAD software that is compatible with the latest release of software used by the Department. All DTM’s shall be approved by the Engineer.

1.	DTM Development Methods:  Develop all DTM’s using the appropriate method as defined below:

a.	Engineering Method - Use this method to define all neat-line surfaces. Develop the DTM by associating all appropriate engineered features such as alignments, profiles, sections, daylight surfaces, grading lines, and other features.

(1)	CAD software shall generate and automatically update surfaces based on the association of alignments, profiles, sections, grading lines, and other parameters necessary to accurately represent neat-line geometry.

(2)	Limit tessellation spacing to allow an accurate representation of a surface feature. The Engineer may require changes to the tessellation spacing, if necessary to allow an accurate representation of the feature.

(3)	If the Contractor excavates or fills beyond the neat-line limit without the direction of the Engineer, only the neat-line limit shall be used.

b.	Topographic Method - Use this method to define all topographic surfaces. Each vertex of a triangle in the TIN shall be formed by a field measured data point, and shall be located by its (XYZ) coordinate. Develop the TIN surface by connecting Topographic Survey points to their nearest neighboring points (in XY), except as outlined below:

(1)	Break Lines – Create break lines by connecting Topographic Survey points that are identified by their appropriate break line descriptors. Break lines shall snap to vertices on adjacent break lines when two break lines intersect. Break lines shall not cross. Use break lines to establish the following features:

(a) 	Centerline of roadway.

(b)	Lane separations (for multiple lane roadways).

(c)	Edge of pavement.

(d)	Shoulder hinge points.

(e)	Bottom of ditch.

(f)	Ditch back slope catch point.

(g) 	For curb and gutter sections, break lines shall be collected at the flow line and back of curb.

(h)	Ridge lines.

(i)	Rim of pits or significant depressions.

(j) 	Areas of slope change or undulations in slope.

(k) 	Bottom of valleys or draws.

(l) 	Hydraulic features.

(m)	Around buildings and structures (including top and bottom of walls).

(2)	Boundaries – Boundaries break the TIN lines and define the edge of the surface. Use boundaries to trim all non-relevant edges from the DTM. Use either non-destructive or destructive trimming as necessary to preserve the accuracy of the DTM. Use boundaries to establish the following features:

(a)	Outer boundary of the DTM.

(b)	Edge of a void inside the surface.

(c)	Edge of an island inside of a void.

(3)	Surface Editing – Surface Editing allows changes that more accurately represent the actual terrain. Use surface editing to delete or swap edges of the triangulated network as necessary to best represent the actual site condition. Mathematically computed points for the purpose of surface smoothing may be used only if approved by the Engineer. The creation of contour lines for the purpose of DTM surface extraction is not acceptable.

c.	Combination Method - Use this method when the Engineer approves a change to the neat-line limit.

(1)	In areas where the Engineer approves a change to the neat-line limit, develop new surfaces using the Topographic Method.

(2)	Replace the neat-line surface with the new topographic surfaces to create an appropriate single surface.

642-3.08 CONTRACTOR FURNISHED COMPUTATIONS. Provide computations for volumetric pay items using DTM’s developed per Section 642-3.07. Cross sections developed from the appropriate DTM’s will be used as a supplementary quality control check on DTM parameters and quantities, and not for pay. The Contractor may use the Average End Area Method in accordance with Section 109, only if approved in writing by the Engineer.

1.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted cross sections from the DTM surfaces. Develop separate cross sections for each volumetric pay item. More than one pay item per plotted cross section is not allowed.

(1)	Plot every 50 ft on Station, including intermediate stations as required to define angle points, curves, or other significant changes in the roadway geometry.

(2) 	Show the elevation and offset information for all vertex points. Weeding vertex point labels is not allowed. Elevation and offset information may be shown on a separate report if the amount of information exceeds what can be legibly shown on the plot.

(3)	Show the area for each cross section.

(4)	Label each plot with the project name, project number, pay item number, and pay item name.

(5)	Label each plot with the Surveyor’s Company name and address.

b.	Plotted profiles from the DTM surfaces. Develop separate plots for each volumetric pay item. Each plot shall only identify the profiles appropriate to the volumetric pay item.

(1)	Plot the profile along the alignment centerline as shown in the plans.

(2)	Label each profile as original ground, bottom of excavation, and the top or bottom of embankment, as appropriate.

(3)	Label topographic profiles with elevation and station information, using a weeding frequency of every 100 ft, or as necessary to match the frequency shown on the plans.

(4)	Label the neat-line profiles with elevation and station information every 100 ft, and for the beginning, end, and VPI of all vertical curves and grade breaks. Label the percent slope between all grade breaks, to the fourth significant decimal.

(5)	Label each plot with the project name, project number, pay item number, and pay item name.

(6)	Label each plot with the Surveyor’s Company name and address.

c.	Electronic Data

(1)	Provide copies of all Topographic, Neat-line, and Combination surfaces to the Engineer. Include all electronic features (alignments, profiles, sections, etc.) used to generate the surfaces.

(2)	All data shall be delivered on a clearly labeled CD-ROM or DVD, unless specified otherwise by the Engineer. The label shall include the project name, project number, Surveyor’s company name, and date. All data becomes the property of the State of Alaska.

(3)	DTM files shall be saved in Autodesk, TIN, XML, or other approved formats compatible with Department software.

d.	Volume Reports

(1)	Provide interim volume reports showing quantities between every 50 ft station. The volume reports shall be summarized to allow the Department to reference the quantities per individual plan sheet, or as defined in any earthwork summary shown on the plan sheets.

(2)	Provide a final volume report reflecting the final total quantity. Attach all data, calculations, and plots to the report. The report shall be signed, sealed, and dated by the Surveyor. This report shall be used as the basis for final pay.

642-3.09 CONTRACTOR FURNISHED ENGINEERING TOOLS. Furnish and maintain Engineering Tools as directed by the Engineer, for the exclusive use of the Engineer throughout the duration of the project. The Contractor shall furnish all equipment specifications to the Engineer for approval, prior to furnishing equipment. The equipment shall be in good working condition not more than 1 model year old. The Contractor shall insure and indemnify the Department against normal wear and tear, damage, theft, and all other events that may cause a loss of function of the furnished tools. The equipment shall be returned to the Contractor upon completion of the project, or when services are terminated by the Engineer. Furnish training for the Engineer’s staff, as directed by the Engineer.

1.	GPS Rover Unit – All components shall be fully compatible to provide a stand-alone GPS Rover Unit. The Rover Unit shall be an “all on the pole” system equipped with the following:

a.	Receiver

(1)	Bluetooth compatible.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Dual frequency receiver capable of tracking at least twelve (12) satellites simultaneously on parallel channels.

(5)	Capable of RTK, Static, and Fast Static occupations.

(6)	Capable of receiving L1, L2, and GNSS frequencies.

(7)	Antenna model shall have undergone antenna calibration by the NGS.

(8)	Ensure the receiver contains the manufacturer’s latest firmware upgrades.

(9)	Provide the manufacturer’s user guide.

b.	Controller

(1)	Bluetooth compatible.

(2)	Equipped with onboard software allowing for the configuration of RTK, PPK, or Static rover modes.

(3)	Meet waterproof specification IPX7.

(4)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(5)	Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

(6)	Capable of collecting data in WGS84 and displaying local project coordinates.

(7)	Equipped with onboard software that allows automatic point logging.

(8)	Capable of creating and storing line-work in DFX or DWG format.

(9)	Equipped with onboard software to allow the user to stake-out points, 3D lines, and DTM surfaces. Software shall allow the user to read cut/fill elevations relative to a DTM surface.

(10) Capable of importing, exporting, and storing point, line, and DTM data.

(11) Capable of showing satellite, radio, and battery status.

(12) Equipped with onboard software that allow the user to create and manage survey jobs, point data, coordinate systems, and alignments.

(13) Equipped with a removable memory storage device with a minimum capacity of 512MB.

(14) Capable of storing custom configuration settings for the GPS Rover Unit.

(15) Ensure the controller contains the manufacturer’s latest firmware upgrades.

(16) Provide the manufacturer’s user guide.

c.	Radio System

(1)	Meet waterproof specification IPX7.

(2)	Support a frequency compatible with the Reference Station.

(3)	Capable of storing multiple radio frequencies.

(4)	Compatible with the Reference Station’s broadcasting format and protocol.

(5)	Power and programming cables.

(6)	Provide the manufacturer’s user guide.

d.	Batteries

(1)	Provide all batteries required to fully power and operate the GPS Rover Unit.

(2)	Batteries shall be capable of powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

(3)	Each battery shall be rechargeable and commercially available.

(4)	Provide an identical replacement backup battery for each primary battery required.

(5)	Provide all power connectors necessary to connect the batteries to the equipment.

(6)	Provide battery chargers to allow all onboard batteries to be charged simultaneously, and that safeguard against overcharging.

e.	Rod

(1)	Fixed height (non-adjustable).

(2)	Mounting hardware for GPS controller and radio.

(3)	Pole grip with bubble level.

(4)	Detachable bipod.

(5)	Interchangeable flat and pointed footings.

(6)	Quick release adapter for the GPS receiver.

f.	Carrying Case

(1)	Hard Shell.

(2)	Shockproof.

(3)	Waterproof.

(4)	Capacity to hold all components of the GPS rover, minus the rod.

2.	Continually Operating Reference Station – The location of the CORS shall not change for the duration of the project. The CORS shall be permanently mounted per NGS CORS standards. All structures, mounting hardware, power supply, computers, software, networking, and personnel required to support and operate the CORS is considered subsidiary to this item. Store CORS data for the duration of the project, and post online for use by the Engineer. The CORS shall include and conform to the following requirements:

a.	GPS Receiver

(1)	Choke-ring antenna, model shall have undergone antenna calibration by the NGS.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Able to operate in temperatures between -20º F to +140º F.

(5)	Capable of logging L1/L2 data continuously for 180 days, and storing at 1 second intervals. If onboard memory storage capacity is insufficient, backup all data on an external memory storage device.

(6)	Support multiple, simultaneous data logging sessions at different collection rates.

(7)	Equipped with a dual frequency receiver capable of tracking L1, L2, and GNSS frequencies on at least 12 satellites. Receiver shall have a minimum of 24 channels.

(8)	Support CMR/CMR+ and RTCM output simultaneously via separate ports.

(9)	Use multi-path mitigation techniques.

(10)	Satellite acquisition technology shall provide improved tracking in areas of high radio interference such as under power lines, around airports, near radio-intensive construction sites.

(11)	Capable of 1PPS output with an accuracy of 1usec.

(12)	Equipped with 1 primary and 1 secondary power input port.

(13)	The system shall automatically switch between power sources.

(14)	Equipped with over-voltage protection on all power inputs.

(15)	Capable of reporting Signal-to-Noise Ratio (SNR) values for L1 and L2.

(16)	Capable of logging data at operator selected intervals of 0.5, 1, 5, and 30 seconds.

(17)	Provide the manufacturer’s user guide.

b.	Radio

(1)	Transmission power, 25 watt minimum.

(2)	Meet waterproof specification IPX7.

(3)	Ensure the radio has a current license to broadcast in accordance with FCC requirements.

(4)	Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

(5)	Provide the manufacturer’s user guide.

c.	CORS Facility – Provide a facility to mount and house CORS station equipment.

(1)	Facility shall meet NGS CORS mounting requirements, and shall be approved by the Engineer.

(2)	Shall be physically located in a clear view of the sky, away from objects that may cause multi-path interference.

(3)	Location shall provide for maximum strength of geometry relative to the primary control network and the project limits.

(4)	Shall be connected to a primary power source, and a backup power source capable of providing uninterrupted backup power for a minimum of 48 hours.

3.	GPS Base/Repeater Station – All components shall be fully compatible to provide a stand-alone GPS Base/Repeater Station setup. The setup shall include the following:

a.	Receiver

(1)	Meet waterproof specification IPX7.

(2)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(3)	Dual frequency receiver capable of tracking at least 12 satellites simultaneously on parallel channels.

(4)	Antenna model shall have undergone antenna calibration by the NGS.

(5)	Ensure the receiver contains the manufacturer’s latest firmware upgrades.

(6)	Carrying case.

(7)	Tribrach with optical plummet and height rod.

(8)	Provide the manufacturer’s user guide.

b.	Controller

(1)	Equipped with onboard software allowing for configuration as a GPS reference station in RTK, PPK, Static, and Fast Static modes.

(2) 	Capable of logging raw observations for post processing.

(3)	Capable of showing satellite, radio, and battery status.

(4)	Meet waterproof specification IPX7.

(5)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(6)	Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

(7)	Equipped with a removable memory storage device with a minimum capacity of 512MB.

(8)	Equipped with 1 primary and 1 secondary power input port.

(9)	Ensure the controller contains the manufacturer’s latest firmware upgrades.

(10) Provide the manufacturer’s user guide.

c.	Radio

(1)	Transmission power, 25 watt minimum.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Support a frequency compatible with the Reference Station.

(5)	Capable of storing multiple radio frequencies.

(6)	Compatible with the CORS broadcasting format and protocol.

(7)	Ensure the radio has a current license to broadcast in accordance with FCC requirements.

(8)	Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

(9)	Equipped with onboard software/firmware allowing for configuration as either a Reference Station or a Repeater Station.

(10) Carrying case.

(11) Antenna.

(12) Antenna/pole mounting adapter.

(13) Provide the manufacturer’s user guide.

d.	Tripods – Provide one of each:

(1) Conventional tripod with extendible range pole. Include carrying case.

(2) Conventional wood tripod.

e.	Batteries

(1)	Provide all batteries required to fully power and operate the GPS Base/Repeater Station.

(2)	Batteries shall be capable powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

(3)	Each battery shall be rechargeable and commercially available.

(4)	Provide an identical replacement backup battery for each primary battery required.

(5) 	Provide all power connectors necessary to connect the batteries to the equipment.

(6)	Provide battery chargers to allow all batteries to be properly charged, and that safeguard against overcharging.

4.	Computer Hardware – Hardware shall meet the following minimum requirements:

a.	Laptop Computer

(1)	2.8 GHz multi-core CPU.

(2)	120GB Internal Hard Drive.

(3)	4 GB System RAM.

(4)	Display 13” with 1,600 x 1,200 resolution.

(5)	512MB video memory.

(6)	DVD Burner Drive.

(7)	Internal Bluetooth and Wi-fi.

(8)	Internal Battery.

(9)	120v AC Adapter.

(10) 12v DC Adapter.

(11) Built-in CF, SD, and PCMCIA card ports.

(12) 4 USB 2.0 ports.

(13) 1394 (firewire) port.

(14) Mouse (wireless).

(15) Travel Case (hard) for laptop and accessories.

b.	Laptop Computer Mount

(1)	Permanently installed in a vehicle, as directed by the Engineer.

(2)	Fastened to the passenger side of the vehicle.

(3)	Shock and vibration resistant.

(4)	Fully adjustable positioning with mechanically locking hinge points.

c.	Desktop Computer

(1)	3 GHz multi-core CPU

(2)	120GB Internal Hard Drive

(3)	4 GB System RAM

(4)	Compatible DVI 19” monitor with 1,600 x 1,200 resolution

(5)	Internal video card/chip, 512MB, 2 DVI ports

(6)	Internal DVD Burner Drive

(7)	CF and SD media card reader

(8)	6 USB ports

(9)	1394 (firewire) port

(10) Internal wireless (IEEE 802.11 b/g) network card

(11) Internal Ethernet card (10/100 Mbps).

(12) Uninterruptible Power Source (UPS), 8 outlets, 390 Watt

(13) 250 GB Backup Hard Drive (external)

(14) Mouse and Keyboard

d.	Laser Printer

(1)	45 pages per minute print speed.

(2)	1200 x 1200 dpi print quality.

(3)	Main tray capacity shall hold no less than 500, 8.5 x 11 inch sheets.

(4)	Multipurpose tray capable of custom sizes up to 11 x 17 inch sheets.

(5)	128 MB of onboard memory, minimum.

5.	Computer Software – All software shall be licensed and fully operational. Provide software that is similar or approved equal in accordance with the following:

a.	Operating System Software – Provide an operating system that supports the drivers of all onboard and auxiliary computer hardware systems. The operating system shall be of the latest release, with the most current updates installed. The operating system shall support all of the applications listed below.

b.	CAD Software – Provide CAD software that is capable of dynamically associating and updating alignment, profile, section, grading, point, and surface data. The software shall be capable of saving all data to formats that are compatible with the latest release of CAD software currently used by the Department. Formatting shall preserve the dynamic relationship of all DTM features. Software that doesn’t dynamically associate all DTM features is not acceptable.

c.	Word Processing Software – Provide software that is compatible with the latest release of word processing software currently used by the Department.

d.	Spreadsheet Processing Software – Provide software that is compatible with the latest release of spreadsheet processing software currently used by the Department.

e.	Anti-Virus Software – Provide software to protect against viruses and other security threats. Software shall be equipped with a firewall containing industry standards of system protection. The software shall be capable of backing up all hard drive data.

f.	GPS Processing Software – Provide GPS processing software of the latest release and from the same vendor as the GPS equipment furnished. Include all necessary hardware/software keys to enable L1 & L2 Static, PPK, and RTK processing, GNSS processing, network adjustments, datum and map transformations, and RINEX data importing and exporting.

642-4.01 METHOD OF MEASUREMENT. The work will be measured according to Section 109, and as follows:

Item 642(1) Construction Surveying.  Prior to beginning work, develop a Lump Sum Agreement that itemizes major contract work requirements by percentage. Work will be measured by the percent completion of all major contract work requirements defined in the Lump Sum Agreement.

Item 642(3) Three Person Survey Party.  By the hour for extra, additional, or unanticipated work made necessary by changes in the project, as directed, and as supported by certified payrolls. Work accomplished by a three person survey party will be paid at 100% of the contract unit price. Work accomplished by a two person survey party will be paid at 75% of the contract unit price. Work accomplished by a one person survey party will be paid at 32% of the contract unit price.

Item 642(13) Contractor Furnished Computations.  Prior to beginning work, develop a Lump Sum Agreement that itemizes all plan sheets labeled “Plan and Profile” (or similar) by percentage. Work will be measured by the percent completion of all computations required, per plan sheet defined in the Lump Sum Agreement.

Item 642(14) Contractor Furnished Engineering Tools.  Contingent sum work will be measured in accordance with the directive authorizing the work.

642-5.01 BASIS OF PAYMENT. Pay Items include all necessary personnel, equipment, transportation, traffic control, and supplies to accomplish the work described in the Contract, or directed by the Engineer.

Pay Item 642(1) Construction Surveying.  This item includes all surveying work described in the Contract except for work paid for under 642(3), 642(13), and 642(14). 5% of the contract lump sum bid price will be withheld until the final As-Built Survey is completed and accepted by the Engineer.  Surveying required for determining volumetric quantities is considered subsidiary to Item 642(13).

Pay Item 642(3) Three Person Survey Party.  Adjustment according to 109-1.04 is not allowed for this pay item. When directed by the Engineer to reference an existing monument not shown in the plans, payment will be made after the Monument Record Forms are prepared and recorded in the local Recorder’s Office and accepted by the Engineer.

Pay Item 642(13) Contractor Furnished Computations.  This item includes all work required to develop and furnish quantity computations in accordance with methods required by the contract. Earthwork computations, digital terrain model development, plotted cross sections, quantity reports, and associated topographic surveying are subsidiary to this item. The Engineer may withhold payment for this item if the minimum specifications are not met.  10% of the contract lump sum bid price will be withheld until final computations are accepted by the Engineer. If the Contractor excavates or fills beyond the neat-line limit without the direction of the Engineer, the calculated volume shall only extend to the neat-line limit.

Pay Item 642(14) Contractor Furnished Engineering Tools.  The Engineer shall issue a directive defining and authorizing the work. Payment for a GPS Rover, Base/Repeater Station, CORS, or Computer System will be made on a time and materials basis in accordance with Subsection 109-1.05-3e, Leased or Rented Equipment. Payment for training will be made on a time and materials basis in accordance with Section 109-1.05. If the training is beyond the Contractor’s ability or expertise, payment will be made in accordance with Subsection 109-1.05-4, Work by a Specialty Subcontractor. The Engineer may withhold payment for this item if the minimum specifications are not met. The Engineer may issue a directive at any time to terminate or re-authorize the work, at no additional cost to the Department.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

642(1)	Construction Surveying	Lump Sum

642(3)	Three Person Survey Party	Hour

642(13)	Contractor Furnished Computations	Lump Sum

642(14)	Contractor Furnished Engineering Tools	Contingent Sum

CFHWY00317

Special Provisions

Replace Section 643 with the following:

SECTION 643
TRAFFIC MAINTENANCE

643-1.01 DESCRIPTION. Protect and control traffic during the contract. Furnish, erect, maintain, replace, clean, move, and remove the traffic control devices required to ensure the traveling public’s safety. Perform all administrative responsibilities necessary to implement this work.

Maintain all roadways and pedestrian and bicycle facilities affected by the work in a smooth and traversable condition. Construct and maintain approaches, crossings, intersections, and other necessary features throughout the project for the life of the contract.

Illuminate construction activities listed in Table 643-4 during hours of night work on roads open to the public within project limits.

643-1.02 DEFINITIONS.

ATM. When used in this Section, ATM stands for the Alaska Traffic Manual, which is the MUTCD with Alaska Supplement.

Balloon Light.  Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.

Construction Phasing Plan. A plan for each phase of the project showing how to accommodate traffic. Show the sequence of work by segment or phase, if required.

Fixed Objects. Private vehicles, parked flagger vehicles, idle construction equipment, construction material stockpiles, culvert ends, individual trees, power poles, utility poles and appurtenances, and other items deemed by the Engineer to present a hazard to motorists, pedestrians, or bicyclists traveling through the work zone.

Night Work. Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in the Table 643-1 below:

TABLE 643-1

PROJECT LOCATIONS – NIGHT TIME ILLUMINATION EXCLUSION

| Latitude | No Lighting Required |  | Nearby |
| --- | --- | --- | --- |
| (degrees) | Start | End | Cities |
| South of 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Tok, Delta, Nome |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle City |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

Traffic. The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, or similar operations.

Traffic Control Plan (TCP). A drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. The TCP depicts the traffic control devices and their placement and times of use.

Traffic Control Zone. A portion of a road construction project, maintenance operation, utility work or similar operation that affects traffic and requires traffic control to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. Implement an approved TCP before beginning work within the project limits.

The TCP includes, but is not limited to, signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary lighting, temporary roadways and all other items required to direct traffic through or around the traffic control zone according to these Specifications and the ATM. Address in the TCPs placement of traffic control devices, including location, spacing, size, mounting height and type. Include code designation, size, and legend per the ATM and the Alaska Sign Design Specification (ASDS). Include longitudinal buffer space for the posted speed limit, according to Table 6C-2 of the ATM unless project conditions or geometric features prohibit including all or a portion of the buffer length.

When a TCP is included in the Plans, use it, modify it, or design an alternative TCP. When a TCP is omitted from the Plans, provide one according to this Section and the ATM.

Submit new or modified TCPs to the Engineer for approval. All TCPs must include the following information:

1.	Project name and number.

2.	A designated TCP number and name on each page.

3.	For TCPs more than one page, each page must be numbered.

4.	The posted speed limit for each roadway.

5.	Existing striping width, lane width, and road surfacing.

6.	Construction lane widths, striping layout, and temporary pavement marker layout.

7.	Provisions for Pedestrian, Bicycle, and ADA travel through the work zone.

8.	Dates and times the TCP will be in effect and why it is being used.

9.	The Worksite Traffic Supervisor’s signature certifying that all TCPs conform to the ATM and the Contract.

10.	The Project Superintendent’s signature confirming the TCP is compatible with the work plan.

11.	The name(s) of the Worksite Traffic Supervisor, his/her alternate and their 24-hour telephone number(s).

12.	Signs to be used and the ASDS designation number and size.

13.	Location and spacing of all devices and signs.

14.	A plan to address any possible slopes, drop offs, paving joints, or similar temporary features that may occur during use of the TCP.

15.	For TCPs proposed to be used at night, note how the requirements will be met for the required lighting and retroreflective material.

TCPs submitted for approval without all the required information will be rejected. Allow 7 days for review of each TCP submittal. All required modifications to a TCP require a new submission and an additional 7 days for review.

A minor revision to a previously approved TCP during construction requires 48 hours for review and approval by the Engineer.

The TCPs, Plans, and Standard Drawings show the minimum required number of traffic control devices. If unsafe conditions occur, the Engineer may require additional traffic control devices.

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12-foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

Road Closures and Major Traffic Sequencing (events).  Submit a written request to the Engineer for review and approval of each proposed event and event date.  Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections.  The proposed event date will be no less than 14 days from the date of written approval.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. Provide a Worksite Traffic Supervisor responsible for maintaining 24-hour traffic operations.

1.	Qualifications. The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements. The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, proposed operations, and certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Temporary Traffic Control Technician, or Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor has a minimum 4000 hours of temporary traffic control work experience, is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this section.

	Temporary traffic control work experience shall demonstrate an understanding of concepts, techniques, and practices in the installation and maintenance of traffic control devices, and skill in reading, interpreting, implementing, and modifying TCPs.

	Temporary traffic control work experience includes: flagging; installing traffic control devices in accordance with TCPs; monitoring traffic control devices and TCP performance; and recognizing and reporting deficiencies in traffic control devices and TCPs for correction.

	Temporary traffic control work experience is gained while serving as a Worksite Traffic Supervisor-in-training, temporary traffic control support personnel, and Flagger.

	Four thousand hours of experience serving solely as a Flagger does not satisfy these requirements.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

2.	Duties.

a.	Prepare the TCPs and public notices and coordinate traffic control operations between the Project Superintendent and the Engineer.

b.	Physically inspect the condition and position of all traffic control devices used on the project at least twice each day and at approximately 12-hour intervals.  Ensure that traffic control devices work properly, are clean and visible, and conform to the approved TCP.  Complete and sign a detailed written report of each inspection within 24 hours.  Use Traffic Control Daily Review Form 25D-104.

c.	Supervise the repair or replacement of damaged or missing traffic control devices.

d.	Review and anticipate traffic control needs. Make available proper traffic control devices necessary for safe and efficient traffic movement.

e.	Review work areas, equipment storage, and traffic-safety material handling and storage.

f.	Hold traffic safety meetings with superintendents, foremen, subcontractors, and others as appropriate before beginning construction, prior to implementing a new TCP, and as directed. Invite the Engineer to these meetings.

g.	Supervise all traffic control workers, flaggers, and pilot car drivers.

h.	Certify that all flaggers are certified as required by Subsection 643-3.04.4.  Submit a copy of all flagger certifications to the Engineer.

i	Supervise lighting for night work.

3.	Authority. The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-1.05 CONSTRUCTION PHASING PLAN. Submit a Construction Phasing Plan for approval no less than 5 working days prior to the preconstruction conference. Include the following:

1.	Form 25D-124 designating the Worksite Traffic Supervisor, providing the 24-hour telephone number, and certifying minimum 4,000 hours of work experience as described in 643-1.04 Worksite Traffic Supervisor.

2.	A construction-phasing plan for each phase or segment of the project.

3.	TCPs for the first phase of the project. Show permanent and temporary traffic control measures, including the times each TCP will be used.

Submit any changes to the Engineer for approval 7 days before proposed implementation.

643-1.06 TRAFFIC MAINTENANCE SETUP. When shown on the bid schedule, Traffic Maintenance Setup items are site specific and are detailed as individual TCPs on the plan sheets. They depict the method or scheme required to route traffic safely and efficiently when any of the following restrictions occur:

1.	Lane Closure. The closure of one or more lanes on a roadway.

2.	Detour. The redirection of traffic through or around a traffic control zone.

3.	Road Closure. The closure of a roadway with or without a specified detour route.

4.	One Lane Road. A two-way roadway reduced to a single-lane roadway with flaggers, pilot cars, traffic signals, stop signs, or yield signs.

643-2.01 MATERIALS. Provide traffic control devices meeting the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM, and ASDS.

a.	Construction Signs: Regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Neatly mark the size of each sign on its back in 3-inch black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 48 X 48 inch traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 8 feet long. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Contract. For each direction of traffic, equip each 12.5-foot section of barrier with at least two side-mounted retroreflective tabs placed approximately 6 to 8 feet apart, or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier. Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 28 inches high. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint meeting Subsection 708-2.03 with glass beads meeting Subsection 712-2.08,

b.	Preformed Marking Tape (removable or non-removable) meeting Subsection 712-2.14, or

c.	Temporary Raised Pavement Markers meeting Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V. Application of crash cushion must be appropriate for the intended use and be installed per manufacturer’s recommendation. Temporary crash cushions used as rail or barrier end treatments must be redirective. Temporary crash cushions that are barrels or barricade filled with sand or water may only be used when the forecasted temperature during their use is above 32 degrees Fahrenheit.

11.	Sequential Arrow Panels. Use Type A (24 X 48 inch), Type B (30 X 60 inch) or Type C (48 X 96 inch) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs.  Use new truck or trailer mounted portable changeable message board signs with self-contained power supply for the sign and with:

a.	Message sign panel large enough to display 3 lines of 18-inch high characters

b.	Eight character display per message module

c.	Fully programmable message module

d.	Remote control cellular, wireless radio frequency (RF), landline

e.	Waterproof, lockable cover for the controller keyboard

f.	Capacity for electric/hydraulic sign raising or lowering

g.	Radar over speed detection

h.	Variable flash and sequence rates

i.	Light emitting diode (LED) display, using Institute of Transportation Engineers (ITE) amber/yellow

j.	The capacity for a minimum of 150 pre-programmed messages

k.	Battery-Pack Operation Duration:  minimum of 55 hours under full load

l.	Power chords shall comply with the National Electrical Code (NEC) Article 600.10 Portable and Mobile Signs, paragraph 600.10(c) (2) ground fault circuit interrupter (GFCI).  The chord will have integral GFCI protection located in either the attachment plug or 12 inches or less from the plug.

13.	Plastic Safety Fence. Use 4-foot high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	"Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306.  Phone (800) 428-8185.

b.	"Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108.  Phone (800) 648-7916.

c.	"Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104.  Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 1/2-inch thick for areas continuously supported by subgrade. Use plywood at least 1 inch thick for areas that are not continuously supported.

b.	Do not use unsupported 1-inch plywood longer than 30 inches.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 1/2-inch. Bevel overlap joints so the maximum slope of the overlapping edge is 2 horizontal to 1 vertical.

d.	Fasten so wind and traffic will not displace temporary surfacing.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

16.	Flagger Paddles. Use flagger paddles with 24 inches wide by 24 inches high sign panels, 8 inch Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM.  Use retroreflective sheeting that meets ASTM D4956 Type VIII or IX. Use background colors of fluorescent orange on one side and red on the other side.

17.	Truck Mounted Attenuator, TMA. The TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight per the manufacturer’s recommendations.

18.	Portable Steel Barriers. Use portable steel barriers that conform to the contract.  For each direction of traffic, equip each section of barrier with side-mounted retroreflective tabs placed approximately 6 to 8 feet apart,   or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier.    Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV, or V.

19.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

643-2.02 Crashworthiness. Submit documentation, by the method indicated on table 643-2, that the following devices comply with Test Level 3 requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or the Manual for Assessing Safety Hardware (MASH). Submit documentation of compliance to the Engineer before installing devices on the project.

TABLE 643-2

WORK ZONE TRAFFIC CONTROL DEVICE AND

BARRIER CRASH TESTING COMPLIANCE

| Category | Devices |  | Method of Documentation |
| --- | --- | --- | --- |
| 1 | Cones, candles, drums w/o attachments, delineators | Manufacturer's Certification for devices exceeding height and weight limits |  |
| 2 | Barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in category 1 | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |  |
| 3 | Truck mounted attenuators, redirective and nondirective temporary crash cushions, bridge railing, bridge and guardrail transitions, and guardrail and barrier end treatments. | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |  |
|  | Portable steel barriers | FHWA acceptance letter indicating acceptance at Test Level 3 unless otherwise required in the contract. |  |

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3. This certification may be a one-page affidavit signed by the vendor. Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization. No certification is required for devices less than or equal to both the weight and height on the schedule below:

Device	Composition	Weight	Height

Cones	Rubber		20 lb.	36 in.

Plastic		20 lb.	48 in.

Candles	Rubber		13 lb.	36 in.

Plastic 		13 lb.	36 in.

Drums	Hi Density Plastic		77 lb.	36 in.

Low Density Plastic	77 lb.	36 in.

Delineators	Plastic or Fiberglass	N/A	48 in.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Keep the work, and portions of the project affected by the work, in good condition to accommodate traffic safely. Provide and maintain traffic control devices and services inside and outside the project limits, day and night, to guide traffic safely.

Unless otherwise provided in this Section, keep all roadways, business accesses, and pedestrian facilities within the project limits open to traffic. Obtain the Engineer’s approval before temporarily closing residential, commercial, or street approaches. Provide access through the project for emergency vehicles and school and transit buses. Properly sign and/or flag all locations where the traveling public is redirected or stopped. Organize construction operations so the total of all construction related stoppages experienced by a vehicle traveling through the project does not exceed 20 minutes except when indicated otherwise in the Contract.

Stop equipment at all points of intersection with the traveling public unless an approved TCP shows otherwise.

Continue to operate all illumination and signalization according to the requirements of Subsection 660-3.09. When moving approach lanes, realign signal heads as necessary according to the ATM. Coordinate any modifications to existing traffic signals with the agency that maintains and operates them. Operate flood lighting at night according to the ATM. Adjust flood lighting so that it does not shine into oncoming traffic.

Provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times, except when regulations prohibit pedestrians or bicyclists. Station a flagger, where construction activity encroaches onto the safe route in a traffic control zone, to assist pedestrians, and bicyclists past the construction activity.

Maintain business access(s) during flagging operations.

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as an employee or a subcontractor becomes aware of the accident.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Obtain an approved TCP before reducing existing roadway lane and shoulder widths and before starting construction. Maintain a clear area with at least 2 feet between the edge of traveled way and the work area. Use barricades, traffic cones, or drums to delineate this area. Place traffic control devices on the work side of the clear area. Space them according to the ATM.

Where specified in the Plans, Specifications, Special Provisions, and or the TCP:  traffic may be maintained on a continuous gravel surface.

1.	Specified Gravel Surface.  Traffic may be maintained on a continuous gravel surface where specified:

a.		N/A		 Highway:  		N/A		 weeks.

b.	BOP to Station 		N/A		 : No time restriction.

c.	Station 		N/A		 to Station 		N/A		 (or EOP).

d.	Other project roadways:  1000 ft/5000 ft/10000 ft, no time restriction.

2.	Gravel Surface Not Specified.

a.	Through traffic shall not traverse more than two gravel sections of roadway in any given period.

b.	Pavement Break(s) for Culvert or Utility Work:  Patch pavement breaks(s), with hot mix asphalt, not more than 48 hours after removing the existing pavement.

c.	When approved by the Engineer.

If maintaining traffic on an unpaved surface, provide a smooth and even surface that public traffic can use at all times. Properly crown the roadbed surface for drainage. Before beginning other grading operations, place sufficient fill at culverts and bridges to permit traffic to cross smoothly and unimpeded. Use part-width construction techniques when routing traffic through roadway cuts or over embankments under construction. Excavate the material or place it in layers. Alternate the construction activities from one side to the other. Route the traffic over the side opposite the one under construction.

Detour traffic when the Plans or an approved TCP allows. Maintain detour routes so that traffic can proceed safely. When detours are no longer required, obliterate the detour. Topsoil and seed appropriate areas.

If two-way traffic cannot be maintained on the existing roadway or detour, use half-width construction or a road closure if it is shown on an approved TCP. Make sure the TCP indicates closure duration and conditions. Schedule the roadway closures to avoid delaying school buses, and peak-hour traffic. For road closures, post closure-start and road-reopen times at the closure site, within view of waiting traffic.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.

643-3.03 PUBLIC NOTICE. Give notice at least 3 days before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

	Alaska Trucking Association

	Alaska State Troopers

	Division of Measurement Standards

	Local Police Department

	Local Fire Department

	Local Government Traffic Engineer

	School and Transit Authorities

	Local Emergency Medical Services

	Local Media (newspapers, radio, television)

	Railroads (where applicable)

	U.S. Postal Service

	Major Tour Operators

Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system. Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. These telephone numbers are used to alert construction employees when emergency vehicles must pass through the project. When notified of emergencies make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator or 511 System for selected projects. Check the special provisions for those requirements.

643-3.04 TRAFFIC CONTROL DEVICES. Before starting construction, erect permanent and temporary traffic control devices required by the approved TCPs. The Engineer will determine advisory speeds when necessary.

For lane closures on multilane roadways, use sequential arrow panels. During hours of darkness when required by the approved TCP, use flashing warning lights to mark obstructions or hazards and steady-burn lights for channelization.

Use only one type of traffic control device in a continuous line of delineating devices, unless otherwise noted on an approved TCP. Use drums or Type II barricades for lane drop tapers.

During non-working hours and after completing a particular construction operation, remove all unnecessary traffic control devices. Store all unused traffic control devices in a designated storage area which does not present a nuisance or visual distraction to traffic. If sign panels are post mounted and cannot be readily removed, cover them entirely with either metal or plywood sheeting. Completely cover signal heads with durable material that that fully blocks the view of signal head and will not be damaged or removed by weather.

Keep signs, drums, barricades, and other devices clean at all times.

Use only traffic control devices that meet the requirements of the “Acceptable” category in ATSSA (American Traffic Safety Services Association) “Quality Guidelines for Temporary Traffic Control Devices” and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project. Stock repair parts for each Temporary Crash Cushion used on the project. Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware. All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the plans, specifications, and approved TCPs until permanent roadside safety hardware is installed. All temporary roadside safety hardware shall meet NCHRP 350 or MASH Test Level 3 unless otherwise noted.

All items paid under this Section remain the property of the Contractor, unless noted otherwise in the contract. Remove them after completing the project.

1.	Embankments.  Close trenches and excavations at the end of each continuous work shift, except as indicated by the Engineer.

Install portable concrete or steel barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as specified on the Plans or TCPs to delineate open trenches, ditches, other excavations, and hazardous areas when they exist along the roadway for more than one continuous work shift.

2.	Adjacent Travel Lane Paving. When paving lifts are 2 inches or greater and you cannot finish paving adjacent travel lanes or paved shoulders to the same elevation before the end of the paving shift, install: W8-11 (Uneven Lanes), W8-9 (Low Shoulder), W8-17 (Shoulder Drop-Off), W14-3 (No Passing Zone), R4-1 (Do Not Pass), R4-2 (Pass with Care), and W8-1 (Bump) signs as appropriate. Place additional signs every 1500 feet if the section is longer than 1/2 mile.

3.	Fixed Objects And Construction Vehicles And Equipment Working On Or Next To The Traveled Way.  Do not park equipment in medians.  Locate fixed objects at least 30 feet from the edge of traveled way. Fixed objects that exist prior to construction activity are not subject to this requirement unless the proposed temporary traffic routing moves the edge of traveled way closer to the pre-existing fixed object.  Vehicles and other objects within parking lots in urban environments are considered preexisting fixed objects regardless of whether they are or are not present continuously throughout the day.

When worksite restrictions, land features, right of way limitations, environmental restrictions, construction phasing, or other construction conditions allow no practicable location meeting the preceding requirements, the Engineer may approve alternate locations for fixed objects. Alternate locations shall be as far as practicable from the edge of traveled way. When the alternate location provides 15 feet or more separation from the edge of traveled way, the Engineer may verbally approve the alternate location. When the alternate location provides less than 15 feet separation, written approval is required.

When the Engineer determines a fixed object or fixed objects present unacceptable hazard, use drums, or Type II barricades with flashing warning lights, or use portable concrete or steel barriers, or temporary crash cushion to delineate or shield the hazard, as approved by the Engineer.

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

4.	Flagging. Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone. The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

a.	Flagging Level I Certification by IMSA

b.	Flagger Certification by ATSSA

c.	Traffic Control Supervisor, ATSSA

d.	Work Zone Safety Specialist, IMSA

e.	ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification.  Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned flagging location at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements. Remove, fully cover, or lay down flagger signs when no flagger is present. Keep the flaggers’ area free of encumbrances.  Keep the flagger’s vehicle well off the roadway and away from the flagging location so the flagger can be easily seen.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer’s written approval before flagging signalized intersections. When flagging a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode. Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer. Get their written approval in advance. Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

5.	Pilot Cars. You may use pilot cars when part of an approved TCP, if the Engineer determines one-way traffic is necessary, or if the route through the traffic control zone is particularly hazardous, involved, or frequently altered to preclude adequate signing,  Do not use pilot cars to avoid localized traffic control at several locations.  Pilot car operators may not control Automated Flagger Assistance Devices while operating a pilot car.

Organize construction operations so the total of all stoppages experienced by a vehicle traveling through a project does not exceed 20 minutes. However, this does not imply that you may allow 20 minutes in all cases. Coordinate multiple pilot-car operations within a project or adjoining projects to minimize inconvenience to the traveling public. Two or more pilot cars may be used to provide two-way traffic through the traffic control zone to reduce the waiting period. The flagger or pilot car operator must record each pilot car’s departure time in a bound field book furnished by the Engineer. Whenever practical, the flagger should tell the motorist the reason for and approximate length of the delay. Make every reasonable effort to yield right-of-way to the public and prevent excessive delay.

Use an automobile or pickup as the pilot car, with the company logo prominently displayed. Equip the pilot car with a two-way radio for contact with flaggers and other pilot cars. Mount a G20-4 sign (Pilot Car Follow Me) on the rear at least 5 feet above the driving surface. Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on all Pilot Cars. Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.  Identify the last vehicle in the column.

When pilot car operations are approved, establish all required pilot car traffic control devices before beginning work.  Continue pilot car operations until no longer necessary and an approved TCP is in place for operations without pilot car, including all required traffic control devices.

6.	Street Sweeping and Power Brooming. Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material.  Use equipment for brooming and sweeping as recommended by the manufacturer and the following:

Dirt, dust and construction materials, mobilized as a result of power brooming and or sweeping, shall not be pushed, ejected, thrown or drift beyond the lesser of, 2 feet from the equipment perimeter or the edge of the paved surface.

All equipment shall operate to typical industry standards.  Maintain equipment to operate as designed by the manufacturer.  Equipment will employ safety equipment, warning lights, and other as required by the Specifications and these Special Provisions.

Sweeper and Broom Options:  Table 643-5, Traffic Control Rate Schedule, Street Sweeping

a.	Regenerative Sweeper:  Sweeper that blows a stream of air at the paved surface, causing fine particles to rise, and then caught through a vacuum system.

b.	Vacuum Sweeper:  Sweeper that creates a vacuum at the paved, surface sucking dirt, dust, and debris into a collection system.

c.	Mechanical Broom Sweeper:  Sweeper designed to pick up and collect larger size road debris, stones and litter, etc.  In addition to the requirements noted in these Specifications, use of a mechanical broom sweeper requires the Engineer to approve the sweeper for the intended use.

d.	Power Broom:  Power brooming that wets, pushes and or ejects loose material directly into an attached collection/pickup container may be used when approved by the Engineer.  The added moisture will be contained to the paved roadway surface.

Dry Power Brooming is not permitted.  Power brooming without direct/immediate means of collection/pickup is not permitted.

7.	Watering. Furnish, haul, and place water for dust control and pavement flushing, as directed. Use water trucks that can provide a high-pressure water stream to flush the pavement and a light-water spray to control dust. If the flushing operations contaminate or fill adjacent catch basins, clean and restore them to their original condition. This requirement includes sections of roadway off the project where flushing is required. The Engineer will control water application.

Obtain an Alaska Department of Natural Resources permit for water removal before taking water from a lake, stream, or other natural water body. Comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

8.	Portable Changeable Message Board Signs. Furnish Changeable Message Signs when approved on a TCP. Display only messages approved on the TCP. Follow application guidelines in the ATM.

9.	Truck Mounted Attenuator (TMA.) TMAs are mounted on the rear of work vehicles. Impact attenuators are defined by NCHRP 350 or MASH as a category 3 device. TMAs shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight in accordance with the manufacturer’s recommendations. TMAs shall have an adjustable height so that it can be placed at the correct elevation during usage and to a safe height for transporting. Approach ends of TMAs shall have impact attenuator markings in accordance with the ATM. Do not use a damaged attenuator in the work. Replace any damaged TMA at your expense.

10.	Traffic Control Vehicles.  Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on the Work Zone Supervisor’s vehicle and on vehicles being used to transport and set-up traffic control devices.  Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.

643-3.05 AUTHORITY OF THE ENGINEER.  When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice, and then a written notice according to Subsection 105-1.01, Authority of the Engineer. The notice will state the defect(s), the corrective action(s) required, and the time required to complete the corrective action(s). In no case shall this time exceed 24 hours.  If corrective action(s) are not completed within the specified time, the Engineer may immediately suspend work on the offending operations until the defect(s) are corrected. The Engineer may require outside forces to correct unsafe conditions. The cost of work by outside forces will be deducted from any monies due under the terms of this Contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. A Traffic Price Adjustment, under Item 643(23), will be assessed for unauthorized lane closures or reductions. Unauthorized lane reductions will be assessed as one full lane closure, for each lane reduced without authorization.

Authorized lane closures and/or lane reductions are those shown in the Contract, an approved TCP, or authorized in writing.

Unauthorized lane reductions include unacceptable roadway, pedestrian walkway or route, and bicycle route or pathway surfaces, such as severe bumps, ruts, washboarding, potholes, excessive dust or mud, and non-conforming or out of place traffic control devices. Failure to install temporary crash cushions or barriers, when required according to the Contract or TCP, is also considered an unauthorized lane reduction. The Engineer will make the sole determination whether unauthorized lane reductions or closures are present.

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-3, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

The rates are liquidated damages which represent highway user costs, based on Average Daily Traffic (ADT). The Engineer will use the rate shown for the current ADT for this project, as published in the Regional Traffic Volume Report prepared by the Department's Planning Section. Adjustment rates for unauthorized reduction or closure of each lane of pedestrian walkways or route, and bicycle route or pathway, are the same as for one full roadway lane closure.

TABLE 643-3

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0 – 5,000 | $30 |
| 5,000 + | $40 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month before work is suspended for the season, schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the anticipated roadway condition and the work expected to be completed before shutdown. Schedule a field review with the Department for winter maintenance acceptance. At the field review, the Engineer will prepare a punch list for implementation before acceptance.

To be relieved of winter maintenance responsibility, leave all roads with a smooth and even surface for public use at all times. Properly crown the roadbed surface for drainage and install adequate safety facilities. Make sure all illumination and signals, including vehicle detectors, are in good working order.

After the project is accepted for winter maintenance and until ordered to resume construction operations, the Department is responsible for maintaining the facility. The Department will accept maintenance responsibility only for portions of the work that are open to the public, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. The contractor is responsible for maintaining all other portions of the work. The Engineer will issue a letter of “Acceptance for Winter Maintenance” that lists all portions of the work that the Department will maintain during a seasonal work suspension. The contractor retains all contractually required maintenance responsibilities until receipt of this letter.

If the contractor suspends work due to unfavorable weather (other than seasonal) or due to failure to correct unsafe conditions, carry out Contract provisions, or carry out the Engineer’s orders. All costs for traffic maintenance during the suspended period will be borne by the Contractor.

When work is resumed, replace or renew any work or materials lost or damaged during temporary use. If the Department caused damage during winter suspension, payment will be made for repairs by unit pay item or in accord with Subsection 109-1.05, Compensation for Extra Work. When the Engineer directs, remove any work or materials used in the temporary maintenance. Complete the project as though work has been continuous.

643-3.08 CONSTRUCTION SEQUENCING. The construction sequencing detailed in these provisions, the Special Provisions, and the Plans is suggested only. The Contractor may propose alternative construction sequencing.

Throughout the project, maintain the existing roadway, pedestrian walkway, or route, and bicycle route or pathway configuration (such as the number of lanes and their respective widths) except for restrictions to traffic allowed in the Special Provisions or on the Plans, and addressed through approved TCPs. A restriction to traffic is any roadway surface condition, work operation, or traffic control setup that reduces the number of lanes or impedes traffic. Obtain an approved TCP before restricting traffic.

CR643-100117.SSHC2017/CFHWY00317

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below:

1.	Monday through Sunday:  0600 hrs to 2000 hrs.

2.	Around any Holiday and Other Major Events:

a.	If a holiday falls on Sunday, Monday, or Tuesday, the above stipulations apply from 1200 hrs on the Friday before the holiday to 0300 hrs. on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 hrs on the Tuesday before the holiday to 0300 hrs. on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 hrs on the day before the holiday to 0300 hrs. on the Monday after the holiday.

3.	During the Alaska State Fair:  No construction activities are allowed within project limits between the first and last day of the Alaska State Fair

CR643.SSHC2017/CFHWY00317

Road Closures:

| Event | Maximum Duration | Remarks |
| --- | --- | --- |
| Intersection Work on Palmer-Wasilla Hwy/Evergreen Ave at Glenn Hwy | Two weeks (14 consecutive days) | Glenn Hwy to remain open. |
| Intersection Work on Bogard Rd/Arctic Ave at Glenn Hwy | Two weeks (14 consecutive days) | Glenn Hwy to remain open. |
| Intersection Work at Evergreen Ave and Cobb St | 10 consecutive days |  |
| Utility and Water Service Work on Evergreen Ave at Sta. “E” 52+75 | One night closure (2100 hrs to 0500 hrs) |  |

Provide three weeks’ notice to local businesses and property owners along affected street and adjacent streets as determined by the Engineer with an approved TCP. Each full closure shall not be concurrent with other roadway closures. All local access shall be maintained.

CFHWY00317

Lane restrictions, if allowed shall be conducted so that no more than a 5 minute accumulated stopped delay, 20 vehicles, or 1/8 mile (660 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 10 minute stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic detained, allowed for motorists, except school buses.  If a queue of traffic develops at a stop, empty the entire queue to include the last car that entered the queue at the time the queue was released.

Do not delay the school busses through the construction zone; obtain the local school bus schedule and coordinate work efforts.  Submit the plan, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS. Place permanent or interim pavement markings according to this Subsection, details shown on the Plans, approved TCPs, and Parts III and VI of the ATM before opening existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments for more than one continuous work shift. This work may include restriping the existing roadway before beginning construction, before seasonal suspension, and/or after seasonal suspension.

Remove conflicting pavement markings according to Subsection 670-3.04, Paint Removal.

Mark existing roadway sections that will be opened to traffic during the winter. Mark over the existing lines and markings, unless shown otherwise on the Plans or an approved TCP.

Maintain all interim pavement markings for their intended life including reapplication when necessary. There will be no compensation to upgrade interim pavement markings required for work operations lasting up to 2 weeks.

Use only temporary raised pavement markers as interim pavement markings on final pavement surfaces. Completely remove and dispose of them when placing the final markings. Completely remove any residual adhesive that might misguide motorists. Place final pavement markings on finished pavement surfaces and interim pavement surfaces before suspending work for the winter.

Stage the construction to avoid routing traffic over conflicting markings, for more than one continuous work shift. If traffic is routed over conflicting markings during a work shift, delineate the roadway with a complement of warning signs, channelizing devices, and flaggers as required by the ATM.

Use only temporary raised pavement markers meeting Subsection 712-2.16 as interim markings on seal coat and surface treatment pavements. Install the markers according to the manufacturer’s instructions before applying the asphalt surface material and cover coat. Remove the vinyl protective covers after applying the asphalt pavement.

On multicourse surface treatments, install the temporary raised pavement markers after applying the full width of the first layer of cover coat. Install the markers on each day's completed surface before removing the pilot car operations and allowing unescorted traffic on the surface treatment.

Apply final pavement markings according to Subsection 670-3.01, Construction Requirements, of these Special Provisions.

Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer.

643-3.10 LIGHTING FOR NIGHT WORK. Illuminate the night work areas according to Table 643-4.

Table 643-4 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

Use balloon lighting as the main light sources. Do not use floodlights without prior approval by the Engineer. When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway. Locate, aim, louver, and/or shield light sources to minimize glare.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences. When notified of unacceptable glare, modify the lighting system to eliminate it.

TABLE 643-4

NIGHT WORK ILLUMINATION EQUIPMENT AND LOCATION REQUIREMENTS

| Type of Work or Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least one machine-mounted balloon light of at least 2000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | One balloon light of at least 2000 watts, located within 30 feet of the flagger location. Locate so the flagger and the flagging location are illuminated. Provide additional lights or wattage if necessary to provide complete coverage of the flagging location. |
| Truck Crossings where haul vehicles cross or enter a road with more than 10,000 ADT, or where the haul vehicle crossing or entering location is controlled by portable traffic signals or flaggers | At least one balloon light of at least 2000 watts, located on the main road on the far right side of the intersection. Locate light within 30 feet of the edge of the side street. If there is a flagger at the crossing, locate the lights or lights so the lighting requirements for Flagging are also satisfied. |

If the Contractor fails to provide required lighting equipment or provides lighting that creates unacceptable glare, the Contractor shall cease all construction activities that require illumination, including flagging operations, until the condition or conditions are corrected.

Use lighting equipment in good operating condition and that complies with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment. Design mountings so lights can be aimed and positioned as necessary to reduce glare. Locate mounting brackets and fixtures so they don’t interfere with the equipment operator or overhead structures. Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment-mounted light towers or poles are sturdy and freestanding without the aid of guy wires. Towers shall be capable of being moved as necessary to keep pace with the construction operation. Position the ground and trailer-mounted towers and trailers, to minimize the risk of being impacted by traffic on the roadway, or by construction traffic, or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as overhead signals, overhead signs, trees, aerial utilities, or bridges. Aim and adjust lights to provide the required light levels. Provide uniform illumination on the hopper, auger, and screed areas of pavers. Illuminate the operator’s controls on all machines uniformly.

Furnish each side of non-street legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights may supplement but do not relieve the Contract requirement to provide lighting for night work, according to the requirements of Table 643-4.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that all required lights operate continuously during nighttime operations. Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours. In the event of any failure of the lighting system, discontinue the operation that requires illumination until the required level and quality of illumination is restored.

Maintain a supply of at least twenty emergency flares for use in the event of emergency or unanticipated situations. Comply with local noise ordinances.

Install all post-mounted electroliers located within the clear zone, on NCHRP 350 or MASH compliant breakaway bases.

643-3.11 HIGH VISIBILITY GARMENTS. Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004 or ANSI/ISEA 107-2010.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise). Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottom at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to the requirements of this Subsection 643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

7.	Condition.  Furnish and maintain all vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition. Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic contract items.

643-4.01 METHOD OF MEASUREMENT. Section 109 and as follows: Quantities will not be measured during winter suspension of work.

1.	Traffic Maintenance. Calendar Day: Every day shown on the calendar, beginning and ending at midnight. Measurement begins on the day following receipt of the Notice to Proceed or on the first day of work at the project site, whichever is later, and ends on the date of project completion.

2.	Traffic Control Device Items. By the number of units of each bid item shown on the bid schedule (or the Traffic Control Rate Schedule, if item 643(25), Traffic Control, is included) that are installed, accepted, and operational. Incomplete or unsatisfactory devices will not be measured. Special Construction Signs are measured by the total area of legend-bearing sign panel, as determined under Subsection 615-4.01. Compensation for a 24-hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-5. Items measured by the day are for each item per 24-hour period.

3.	Traffic Maintenance Setup Items. By each lane closure or one-lane road in place per hour. By each detour or road closure in place per 24-hour period.

4.	Portable Concrete Barrier. By each nominal 12.5-foot section placed according to the approved TCPs, for the initial placement and for each subsequent relocation when moved more than 10 feet in any direction. Each transition piece (sloping end) will be measured as a single section.

5.	Temporary Crash Cushion. By each acceptable installation.

6.	Interim Pavement Marking. By the single-stripe station. A single stripe is a marking or a temporary raised pavement marker 4 inches wide. Wider striping is measured in multiples of 4 inches. Centerline gaps are not deducted from measurements.

7.	Flagging and Pilot Car. By the number of approved hours, supported by certified payroll.

8.	Street Sweeping. By the number of operated hours, supported by certified payroll and approved by the Engineer.

9.	Watering. By the 1,000 gallons (M-Gallon) of water applied. The Engineer may specify measurement by weight or volume. If by weight, convert to gallons at 8.34 pounds per gallon. If by volume, convert to gallons at 7.48 gallons per cubic foot.

10.	Traffic Price Adjustment. By each minute that any lane of traffic is not open to full use by the traveling public, measured to the nearest minute. The Engineer will determine whether the roadway is opened to full use.

11.	Traffic Control. By the units specified in the Special Provisions.

12.	Portable Changeable Message Board Sign. By the 24-hour period for each sign, as shown on an approved TCP and displaying an approved message.

13.	Plastic Safety Fence. By the linear foot, as placed, to protect or channelize pedestrian traffic as shown on an approved TCP. Any adjustment in configuration of the fence at the same location that does not result in an increased amount of fence is not measured. Opening and closing the fence to gain access to and from the worksite is not measured.

14.	Temporary Sidewalk Surfacing. By the square yard as shown on an approved TCP.

15.	Temporary Guardrail. By the linear foot, including end treatments, as shown on an approved TCP.

16.	Portable Steel Barrier. By the linear foot placed according to the manufacturer’s recommendation and approved TCPs, for the initial placement, and for each subsequent relocation when moved more than 10 feet in any direction.

17.	Hotline Road Report.  No measurement required to provide a 24-hour toll free (1-800 ###-####) “Hotline Road Report” telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Pay Item 643(1) or 643(2), Traffic Maintenance.

CR643-100117.SSHC2017/CFHWY00317

18.	Palmer-Wasilla Hwy Detour.  By lump sum, for the materials, equipment and labor required to construct, maintain, and remove the detour shown on the plans.

19.	Bogard Rd Detour.  By lump sum, for the materials, equipment and labor required to construct, maintain, and remove the detour shown on the plans.

20.	Pedestrian Detour.  By lump sum, for the materials, equipment and labor required to construct, maintain, and remove the detour shown on the plans.

CFHWY00317

643-5.01 BASIS OF PAYMENT.

1.	Traffic Maintenance. The contract price includes all resources required to provide the Worksite Traffic Supervisor, all required TCPs and public notices, the Construction Phasing Plan, and the maintenance of all roadways, approaches, crossings, intersections and pedestrian and bicycle facilities, as required. This item also includes any Traffic Control Devices required but not shown on the bid schedule.

Items required by the Contract that are not listed on the bid schedule or not included in other items are subsidiary to Item 643(1) or 643(2) Traffic Maintenance, except the following:

Traffic Price Adjustment

Traffic Maintenance Setup

2.	Traffic Control Device Items. The contract price includes all resources required to provide, install, maintain, move, and remove the specified devices. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

3.	Traffic Maintenance Setup Items. Each setup consists of all traffic control devices, flaggers, pilot cars, and subsidiary items necessary to implement the TCP shown on the Plans. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

Construction and obliteration of temporary roadways, when required on the Plans or approved TCP under a traffic maintenance setup item, is paid for under their respective roadway pay items.

When topsoil or seeding is required for detours, payment will be made under Sections 620 and/or 618.

4.	Portable Concrete Barrier. The contract price includes all resources required to provide, install, maintain, and remove each barrier section.

5.	Temporary Crash Cushion. The contract price includes all resources required to provide, install, maintain, repair, and remove each crash cushion.

6.	Interim Pavement Marking. The contract price includes all resources required to provide, install, maintain, and remove the specified markings. Installation of word and symbol markings are subsidiary. The No-Passing Zone signing, described in Subsection 643-3.04, is subsidiary.

7.	Flagging and Pilot Car. The contract price includes all required labor, vehicles, radios, flagger paddles and pilot car signs, and transportation to and from the worksite.

The Engineer will pay for Item 643(15A) Flagging on a contingent sum basis at the rate of $58.00/hour.  The Engineer does not require a change order/directive for the flagging Pay Item.  Flagging associated with Change Order work paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

8.	Street Sweeping. The contract price includes all resources required to keep the roadway free of loose material.

9.	Watering. The contract price includes all resources required to provide watering, as directed.

10.	Traffic Price Adjustment. If Item 643(23), Traffic Price Adjustment, is shown on the bid schedule, the total value of this contract will be adjusted, for unauthorized lane reductions or closures, at the rates listed in Table 643-3.

11.	Traffic Control. Payment for Item 643(25), Traffic Control, will be made at the unit rate value contained in the Traffic Control Rate Schedule shown in the Special Provisions for the accepted units of traffic control devices. The Engineer does not require a change order/directive for Pay Item 643(25), Traffic Control.

12.	Portable Changeable Message Board Sign. The contract price includes all resources required to furnish, move, and operate the sign.

Two Portable Changeable Message Board Signs used for Permanent Construction Signing paid for under Item 643(3) Permanent Construction Signs.  Additional portable changeable message board signs will be paid for under 643(25), Traffic Control.

13.	Plastic Safety Fence. The contract price includes all resources required to install, maintain, and remove the fence.

14.	Temporary Sidewalk Surfacing. The contract price includes all resources required to construct, maintain, and remove the surfacing.

15.	Temporary Guardrail. The contract price includes all resources required to construct, maintain, and remove the guardrail.

16.	Portable Steel Barrier. The contract price includes all resources required to provide, install, maintain, move, and remove each barrier.

17.	Lighting for Night Work.  Payment for illuminating night work areas and any required adjustments to work zone illumination is subsidiary to other items.

18.	Pavement Breaks.  Temporary hot mix asphalt at pavement breaks, as noted in Subsection 643-3.02.2. Gravel Surface Not Specified is subsidiary to Pay Item 401(5).

19.	Temporary Pavement Markings.  Except where specified as an individual Pay Item (Interim Pavement Markings) temporary pavement markings are subsidiary to Section 670 Pay Items. Refer to Section 670 Traffic Markings, for further information.

20.	Temporary Crash Cushion / Redirective.  The price listed in the Traffic Control Rate Schedule, Table 643-5, will be full compensation for the purchase, installation, maintenance during construction, removal, and salvaging the Temporary Crash Cushion / Redirective unit(s).  Deliver the salvaged unit(s) to the nearest ADOT & PF Maintenance & Operations Station or as directed by the Engineer.

CR643-100117.SSHC2017/CFHWY00317

21.	Palmer-Wasilla Hwy Detour.  Payment for item 643(20A) Palmer-Wasilla Hwy Detour, shall be full compensation for constructing, maintaining, and removing the detour shown on the plans.

22.	Bogard Rd Detour.  Payment for item 643(20B) Bogard Rd Detour, shall be full compensation for constructing, maintaining, and removing the detour shown on the plans.

23.	Pedestrian Detour.  Payment for item 643(20C) Pedestrian Detour, shall be full compensation for constructing, maintaining, and removing the detour shown on the plans.

CFHWY00317

Traffic control devices, barriers, and crash cushions required to delineate or shield fixed objects will not be measured or paid for separately, but will be subsidiary

Traffic control devices, barriers, and crash cushions required to delineate or shield guardrail posts or non-crashworthy ends will not be measured or paid for separately, but will be subsidiary, when required for failure to meet completion timelines in subsection 606-3.01.

TABLE 643-5

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $28.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Sequential Arrow Panel | Each/Day | $36.00 |
| Portable Concrete or Steel F Shape Barrier (12.5 foot long or $8/foot for other lengths) | Each | $100.00 |
| Temporary Crash Cushion / Sand or Water Filled Barrels or Barrier (all required per end) | Each | $4325.00 |
| Temporary Crash Cushion / Redirective | Each | $9230.00 |
| Pilot Car | Hour | $71.00 |
| Watering | M-Gallon | $28.50 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical or Power Broom with Vacuum | Hour | $214.00 |
| 40,000 GVW Truck with Crash Attenuator | Hour | $162.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Portable Changeable Message Board Sign | Calendar Day | $130.00 |
| Temporary Sidewalk Surfacing | Square Foot | $2.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |
| Temporary Guardrail | Lineal Foot | $25.00 |

CR643-100117.SSHC2017/CFHWY00317

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(1)	Traffic Maintenance	Calendar Day

643(2)	Traffic Maintenance	Lump Sum

643(3)	Permanent Construction Signs	Lump Sum

643(4)	Construction Sign	Day

643(5)	Type II Barricade	Day

643(6)	Type III Barricade	Day

643(7)	Traffic Cone/Tubular Marker	Day

643(8)	Plastic Safety Fence	Linear Foot

643(9)	Drum	Day

643(10)	Sequential Arrow Panel, Type C	Day

643(11)	Special Construction Signs	Square Foot

643(12)	Portable Concrete Barrier	Each

643(13)	Temporary Crash Cushion	Each

643(14)	Interim Pavement Marking	Station

643(15)	Flagging	Hour

643(15A)	Flagging	Contingent Sum

643(16)	Pilot Car	Hour

643(17)	Street Sweeping	Hour

643(18)	Watering	M-Gallon

643(19)	Lane Closure	Hour

643(20)	Detour	Day

643(20A)	Palmer-Wasilla Hwy Detour	Lump Sum

643(20B)	Bogard Rd Detour	Lump Sum

643(20C)	Pedestrian Detour	Lump Sum

643(21)	Road Closure	Day

643(22)	One Lane Road	Hour

643(23)	Traffic Price Adjustment	Contingent Sum

643(24)	Portable Changeable Message Board Sign	Day

643(25)	Traffic Control	Contingent Sum

643(26)	Temporary Sidewalk Surfacing	Square Yard

643(27)	Temporary Guardrail	Linear Foot

643(28)	Power Brooming (Retired)	Hour

643(29)	Steel F Shaped Barrier (Retired)	Linear Foot

643(30)	Portable Steel Barrier	Linear Foot

CR643-SSHC2017/CFHWY00317

SECTION 644
SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:

Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Provide engineering communication services to the field office, Subsection 644-2.08.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

CR644.FOCOM-022015_SSHC2015.17

644-2.02 FIELD LABORATORY.  Replace 2.g. with the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Replace 6.a. with the following:

a.	Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

Add the following:

7.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

CR644.LAB-022015_SSHC2015.17

644-2.05 VEHICLES.  Delete the second and third paragraphs and substitute the following:

Pickup(LT)/Sport Utility Vehicle (SUV):  Furnish full-size, four-wheel drive vehicles, either pickup/light truck(s) with crew cabs or sport utility vehicle(s).  Provide vehicles less than three model years old, in good condition, and with less than 36,000 miles on the odometer.  Furnish all fuels, maintenance and parts, and insurance during the Department’s operation and use.

Equip each vehicle with lightbars wired into the vehicle’s electrical system with a dash mounted switch easily accessible to the vehicle operator.  Provide Code 3; Model 6005H (formerly PE 6200 LE) lightbars, or approved equal.  Approved equal equipment shall have the following characteristics:

	(4) 55 watt rotators with amber filters

	1200 flashes per minute

	(2) diamond mirrors

	55 inches in length

If you are working after October 1, provide four studded snow tires mounted on each vehicle.

You are responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use.  The Department is responsible for damage to any vehicle caused by its own negligent operation.

CR644.LTSUV-022015_SSHC2015.17/CFHWY00317

The Department will provide non-owned auto liability insurance providing third party liability coverage for any accident during the Department’s operation and use.

CR644.LTSUV_SSHC2015.17/CFHWY00317

Add the following subsection:

644-2.08 ENGINEERING COMMUNICATION.  Engineering Communications, minimum service includes:

a.	Three phone/facsimile lines (different phone numbers for each line)

b.	High speed internet service with modem (DSL or Cable)

CR644.FOCOM-022015_SSHC2015.17

644-4.01 METHOD OF MEASUREMENT. Delete the third paragraph and substitute the following:

Vehicle (LT/SUV). For each vehicle provided. If a replacement vehicle is necessary, no additional measurement will be made.

CR644.LTSUV-022015_SSHC2015.17/CFHWY00317

644-5.01 BASIS OF PAYMENT.  Add the following:

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Pay Item 644(2) Field Laboratory.

CR644.LAB-022015_SSHC2015.17

Add the following:

Pay Item 644(8) Vehicle (LT/SUV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(8)	Vehicle (LT/SUV)	Each

CR644.LTSUV-022015_SSHC2015.17/CFHWY00317

Add the following:

Pay Item 644(10) Engineering Communications.  Usage services including long distance calls made by State personnel and the Internet service provider will be reimbursed by the State.  Payment for communication usage services shall be based on paid receipts to the service provider plus 15%.

Connection fees (initial connection) local calls, providing equipment and disconnection are subsidiary to Pay Item 644(1) Field Office and as such are paid by the Contractor.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(10)	Engineering Communications	Contingent Sum

CR644.FOCOM-022015_SSHC2015.17

Special Provision

Add the following Section:

SECTION 645
TRAINING PROGRAM

645-1.01 DESCRIPTION. This Statewide Special Provision for on-the-job training (OJT) implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective. Training and upgrading of minorities and women toward journey status is the primary objective of this program. The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision. Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301.

645-3.01 General. The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive. Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Office of Apprenticeship (USDOL/OA); or one developed by the Contractor using Form 25A-310 and approved prior to contract award by the OJT Coordinator in the DOT&PF Civil Rights Office.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor. Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed. It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project. Existing USDOL/OA apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. The Contractor must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period. Trainee wages shall be identified on Form 25A-310. Apprentices in USDOL/OA training programs shall be paid in accordance with their approved program. Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts. In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor. Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate. However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls. There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section. Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment. Payment will be made at the contract unit price for each hour of training credited. Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311 may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project. No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown in the Bid Schedule and approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown in the Bid Schedule and approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry. Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program. Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits. The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program,  6  Trainees/Apprentices	Labor Hour

SSP-39-010116

SECTION 646
CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this Subsection with the following:

Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete No. 2.

2.	60-Day Preliminary Schedule.

Delete the first sentence of No. 3. Schedule Updates.  and substitute the following:

Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

CR646.1-070214

646-5.01 METHOD OF MEASUREMENT.  Add the following:

Schedule Price Adjustment.  By each calendar day that the required schedule, preliminary schedule or schedule update has not been submitted measured to the nearest day.

646-5.01 BASIS OF PAYMENT.  Add the following:

Schedule Price Adjustment.  If Item 646(2), Traffic Price Adjustment, is shown on the bid schedule, the total value of this contract will be adjusted by $1000 per calendar day for failure to provide the initial CPM Schedule, 60 day Preliminary Schedule or CPM Schedule updates as required.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

646(2)	Schedule Price Adjustment	Contingent Sum

CFHWY00317

Special Provisions

Add the following Section:

SECTION 647
EQUIPMENT RENTAL

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled, and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, except holidays.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. Section 109.

Hourly Rental Rate: Includes the equipment rate plus the operating costs including: furnishing, travel time, operating, maintaining/servicing and repairing the equipment along with the costs incidental to the equipment and its' operation.

647-5.01 BASIS OF PAYMENT. Payment is for the time that fully operational equipment is engaged in the performance of the work directed by the Engineer. Time not payed for includes: idle periods, maintaining/servicing and repairing the equipment, making change-overs of equipment parts, and time to travel to and from the project.  Payment will only be for time supported by certified payroll.

Furnishing and operating equipment that is heavier, has larger capacity, or greater power than specified will not entitle the Contractor to extra compensation.

Pay Item 647(1) Wide Pad Dozer, 65 hp min: payed at the rate of $160/hour.

Pay Item 647(5) Backhoe, 4WD, 1 cy Bucket, 75 hp min, 15 ft Depth: payed at the rate of $160/hour.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)	Wide Pad Dozer, 65 hp Min	Contingent Sum

647(5)	Backhoe, 4WD, 1 cy Bucket, 75 hp Min, 15 ft Depth	Contingent Sum

CR647-110316

Special Provisions

Add the following Section 649:

SECTION 649
GOVERNOR'S WORKFORCE DEVELOPMENT

649-1.01 DESCRIPTION. Provide workforce training and employment for workers according to Governor Walker’s Administrative Order No. 278 (AO 278), for projects with contract award amounts equal to or greater than $2,500,000.

649-2.01 OBJECTIVE. The primary objective of AO 278 is development and maintenance of a well-trained Alaska construction workforce for the efficient and economical completion of construction projects.

As part of AO 278, the Contractor shall strive to attain not less than 15 percent (15%) of labor hours performed by apprentices.  15% apprenticeship utilization is a goal for this Project but is not a requirement of the Contract.  Maintenance of records and reporting under subsection 649-3.01 are requirements of the Contract.

TABLE 649-1

JOB TITLES ELIGIBLE FOR APPRENTICESHIP CREDIT:

| Boilermakers | Bricklayers |
| --- | --- |
| Carpenters | Cement Masons |
| Culinary Workers | Electricians |
| Equipment Operators | Elevator Constructors & Mechanics |
| Insulation Workers | Ironworkers |
| Laborers | Mechanics |
| Millwrights | Painters |
| Pile Driving Occupations | Plumbers and Pipefitters |
| Roofers | Sheet Metal Workers |
| Surveyors | Sprinkler Fitters |
| Truck Drivers | Tug Boat Workers |
| Welders |  |

Apprentice hours applicable toward the Section 649 apprentice utilization goal are those performed by employees in United States Department of Labor Standard Occupational System eligible job titles listed in Table 649-1 above, who are enrolled in a federally registered apprenticeship training program under 29 USC 50 and 29 CFR 29.1 – 29.3.

649-3.01 GENERAL. The Contractor shall determine the distribution and number of apprentices and the number of hours of training among the various work classifications based on the Section 649 apprentice utilization goal, the type of work to be performed, the size of the workforce in each trade or job classification, and the availability of apprentice and journey level workers within a reasonable area of recruitment.

The Contractor shall provide for the maintenance of records and shall submit an OJT Monthly Summary of Journey and Apprenticeship Hours, Form 25A-314, to the Engineer and the Alaska Department of Labor and Workforce Development (DOLWD) by the 15th of each following month. The monthly reporting shall include all journeyman and apprentice hours for the Contractor and all subcontractors.  Monthly reporting on Form 25A-314 is not required if the Contractor’s and all subcontractors’ certified payrolls (required according to subsection 107-1.04) are submitted electronically using the DOWLD Online Payroll Filing System (manual entry or Excel Spreadsheet upload through MyAlaska portal).

649-3.02 WAGES. Apprentices shall be paid in accordance with their registered apprenticeship program.

649-4.01 METHOD OF MEASUREMENT. Section 649 will not be measured for payment.

649-5.01 BASIS OF PAYMENT. Payment will not be made separately but will be subsidiary to other items of work. Non-compliance with records maintenance and reporting required in Section 649 is considered unsatisfactory performance and may result in withholding progress payments according to subsection 109-1.06.

SM-1-043017

Special Provisions

Replace Section 651 with the following:

SECTION 651
CONTROL OF WORK – SUPPLEMENTAL REQUIREMENTS

651-1.01 DESCRIPTION. Supplemental requirements for Section 105, Control of Work.

651-1.02 RELATED SECTIONS. Section 105, Control of Work

651-1.03 UTILITIES.  Request locates from the utilities having facilities in the area.

Use the Alaska Digline, Inc. "Locate Call Center" for the following utilities.

ALASKA DIGLINE, INC.

Locate Call Centers: Anchorage 278-3121 Statewide (800) 478-3121

Call Centers will notify the following: Alaska Communications Systems (ACS) Alaska Fiber Star (WCI) Alaska Railroad Corporation (ARRC) AT & T Alascom (AT&T) ENSTAR Natural Gas (ENS) General Communications, Inc. (GCI) Matanuska Electric Association (MEA) Matanuska Telephone Association (MTA)

State Facility Utilities: before beginning work, contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the District Superintendent's phone number where the project is located, and request locates.

Call the following utilities and agencies directly:

City of Palmer (COP)		(907) 745-3400

DOT&PF M&O Palmer		(907) 745-2159

Utilities Relocated by Others.

Utilities will be relocated by others concurrently with construction of this project. The Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.

For utilities being relocated, the Contractor will:

1.	include utility work on the Construction Phasing Plan and Progress Schedule;

2.	provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work.  Identify all utility companies performing ground disturbing activity in the Storm Water pollution Prevention Plan (SWPPP).  Refer to Section 641 for further information;

3.	clear and grub.  Payment will be made under Section 201, Clearing and Grubbing;

4.	provide traffic control and flagging.  Payment will be made under Section 643, Traffic Maintenance;

5	provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

	Control for utility relocation - either ROW or Centerline staking with Station information.

	Slope staking.

	Proposed structures, not including utilities to be relocated by others.

Payment will be made as follows:

a.	Subsidiary to Pay Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642(3) Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

6.	remove and replace pavement.  Payment will be made under Section 202, Removal of Structures and Obstructions; Section 401, Hot Mix Asphalt and Surface Treatments; Section 408, Hot Mix Asphalt and Surface Treatments, Type V; Section 409, Hot Mix Asphalt and Surface Treatments, Type R (Crumb Rubber) and according to project typical section.

7.	remove and replace sidewalk and curb and gutter.  Payment will be made under Section 202, Removal of Structures and Obstructions, Section 608, Sidewalks, and Section 609, Curbing.

8.	provide bedding and backfill material, in accordance with Section 204, Structure Excavation for Conduits and Minor Structures, and the project typical sections.

9.	coordinate with the utility owner(s) and provide potholing services at the locations identified or as directed by the Engineer. Payment will be made under Section 682, Utility Potholing.

Work done by utility owner(s) is as follows:

The utility relocation for the project has been broken into two segments following the proposed construction sequencing plans provided within the contract plans. The break point between Segment One and Segment Two will be different for each utility and will be described below in detail.

| COMPANY | Segment 1 |  | Segment 2 |  |
| --- | --- | --- | --- | --- |
|  | Begin | End | Begin | End |
| ENSTAR Natural Gas Company | “G” 1606+50 | EOP | BOP | “G” 1606+50 |
| GCI Communication Corp | “G” 1602+00 | EOP | BOP | “G” 1606+00 |
| Matanuska Electric Association, Inc | “G” 1616+00 | EOP | BOP | “G” 1616+00 |
| Matanuska Telephone Association | “G” 1582+00 | EOP | BOP | “G” 1582+00 |

Reference section 107-1.17 for specific Right-of-way restrictions that will affect the calendar days listed below.

MATANUSKA ELECTRIC ASSOCIATION, INC (MEA) owns and operates overhead and underground electrical facilities throughout the project.

Segment One

The existing transmission and distribution pole lines crossing the Glenn Highway right of way at the Lucas Substation (“G” Sta. 1617+50 RT) are in conflict with the proposed frontage road and associated grade changes, and will be relocated. MEA will set new poles between Glenn Highway and Margaret Drive, and just beyond the right of way on project left.  Once installed MEA will transfer the overhead lines and retire the old poles.

The existing underground electrical distribution circuit feeding from the Lucas Substation (“G” Sta. 1617+50 RT), across and then along the Glenn Highway between “G” Sta. 1616+50 LT and 1649+80 LT, is in conflict with the proposed cut limits between “G” Sta. 1617+60 RT and 1626+75 LT and the proposed improvements between “G” Sta. 1640+00 LT and 1649+80 LT, and will be relocated.  MEA will install a temporary overhead line from “G” Sta. 1617+50 LT to 1626+00 LT to energize the new infrastructure to the north until the contractor has cut the area surrounding the Glenn Highway / W. Harold Street / S. Colony Way intersection to final grade.  Once final grade has been established MEA will install the new underground facility between stations 1617+50 LT and 1626+50 LT adjacent to the right of way via trench and horizontal directional drill and retire/remove the temporary overhead circuit.  From “G” Sta. 1649+80 to 1670+00 LT, MEA will replace the existing underground circuit; this line is not in conflict with the project.

MEA’s existing underground facilities along W. Dogwood Avenue are within the footprint of the widened roadway and will be relocated.  MEA will install a new underground distribution circuit via trench and horizontal directional drill from “G” Sta. 16749+80 LT along Dogwood to the existing electrical distribution pole line paralleling the west side of Cobb Street.  As part of this work MEA will rerun the existing service drop to the Post Office.

MEA’s existing overhead distribution facilities surrounding the Glenn Highway / E. Bogard Road / W. Arctic Avenue intersection are in conflict with the proposed signalization work and will be relocated.  MEA will reconfigure and relocate its overhead infrastructure to resolve conflicts with the proposed signal work.  Once the new system is in place and energized, the existing facilities will be retired/removed.

MEA’s existing overhead electrical distribution circuit which parallels the south side of Evergreen Avenue between “E” Sta. 52+40 RT and 55+70 RT will be impacted by the widening of the roadway and will be relocated underground. MEA will install a new underground circuit extending from the Glenn Highway at “E” Sta. 51+00 RT to 54+55 RT where the new underground will connect back into the existing overhead circuit.  The Contractor shall remove the existing sidewalk and curb & gutter along the south side of W. Evergreen Avenue to facilitate this work.

The existing MEA poles on the west side of the W. Evergreen Avenue and Cobb Street intersection will be relocated/replaced to accommodate the new signals.

MEA’s angle pole, at the intersection of Glacier View Avenue and S. Colony Way, is within the radius of the modified approach and will be relocated. MEA will set new poles and reconfigure the alignment of the overhead circuit.  Once complete the existing pole and associated guy pole will be retired/removed.

Work will commence after clearing and all required surveying are completed. MEA will require 90 working days to complete the relocation listed above under Segment One.

Segment Two

MEA’s existing overhead distribution pole line from “G” Sta. 1512+00 to 1616+20 LT conflicts with the proposed widening of the highway and will be relocated. MEA will install a new pole line fifteen (15) feet inside the right of way, except at the following locations:

- “G” Sta. 1530+00 LT - 1534+40 LT, where Margaret Drive (frontage road) ties into the mainline at Clair Street / S. Inner Springer Loop;

- “G” Sta. 1580+25 LT – 1601+90 LT, where Margaret Drive ties into the mainline at E. Jay Street  / E. Inner Springer Loop;

- “G” Sta. 1607+30 LT – 1616+20 LT, where Margaret drives ties into the mainline at W. Harold Street / S. Colony Way.

At “G” Sta. 1616+20 the existing overhead electrical distribution circuit that feeds out of the Lucas Substation across the Glenn Highway and continue south along the left side of the Glenn Highway. The crossing will be relocated north twenty (20) feet, turn south between the mainline and Margaret drive, and extend back to 1607+30 LT.

With the realignment of S. Inner Springer Loop and its’ connection to the Glenn Highway, MEA’s existing overhead distribution pole line is in conflict requiring relocation of 5 spans of the pole line. The new poles will be placed at the edge of the ROW starting at “SIS Sta. 12+75 LT and connecting back into the existing line approximately 300 feet past the project limits.  The existing crossing at “SIS Sta. 12+75 will be extended south to the new poles. MEA will install an overhead guy wire crossing at “SIS” Sta.17+45 with a new pole on project LT. Guy wires will be installed at the connection point with the existing line.

Work will commence after clearing and required surveying are completed. MEA will require 82 working days to complete the relocation listed above under Segment Two.

Electrical Service Connects:

Prior to MEA establishing service to a load center, the Contractor shall have it inspected, and green tagged for compliance. Once tagged, the Contractor shall notify the Project Engineer who will contact the utility.  The Utility will schedule the service connection and complete the line extension work based on their current work load.

ENSTAR NATURAL GAS COOMPANY (ENSTAR) owns and operates a 4” plastic distribution and a 6”steel transmission natural gas lines through the project.

Segment One

ENSTAR’s existing plastic line conflicts with the improvements from the crossing at “G” Sta. 1606+20 LT to 1624+50 LT. ENSTAR will connect to the existing crossing at “G” Sta. 1606+20 LT extending the main out to the west edge of the ROW. A new plastic line will be installed along the west edge of the ROW to “G” Sta. 1626+50 where it will tie into the existing main. ENSTAR will require ten (10) working days to complete the above relocation.

ENSTAR’s existing plastic line cuts on each side. ENSTAR will bore a new 4-inch main across the Glenn Highway at approximately the same location. ENSTAR will require four (4) working days to complete the above relocation.

ENSTAR’s existing plastic line which crosses the Glenn Highway at Sta. 1644+45 conflicts with the proposed storm drain facilities. ENSTAR will bore a new plastic line across at “G” Sta. 1646+40. ENSTAR will require four (4) working days to complete the above relocation.

ENSTAR’s plastic line crossing and along the Glenn Highway from “G” Sta. 1672+20 to 1675+75 is in conflict with the proposed cut. ENSTAR will install a new plastic line from “B” Sta. 7+50 LT behind the cut slope and connect to the existing line at “G” Sta. 1677+50 LT. A new plastic line will be bored under Glenn Highway at “G” Sta. 1678+75 and continue south to “G” Sta. 1675+20 reconnecting to the existing line. ENSTAR will require ten (10) working days to complete the above relocation.

Segment Two

ENSTAR’s existing steel line and plastic line from “G” Sta. 1521+00 LT to 1606+00 LT is located in the shoulder of the proposed roadway and will be impacted by the excavation for the structural section and drainage.

ENSTAR will the tie into the existing plastic and steel lines at “G” Sta. 1512+00 LT.  The new mains will extend along the edge of the ROW crossing the proposed E. Clair Road.  At “G” Sta. 1530+50 LT the plastic and steel lines will transition to the edge of the ROW behind the proposed S. Margaret Drive frontage road. The existing plastic lines along Cienna Drive, “G” Sta. 1524+00 LT, and Blunck Street, “BS” Sta. 1532+35 LT, will be rerouted and tied into the new plastic line.

The new plastic and steel lines continue along the edge of the ROW from “MA” Sta. 29+25 LT north to “MA” Sta. 85+75 LT. From here the plastic and steel lines will cross Margaret Drive and follow along the edge of ROW on the RT side to “MA” Sta. 97+50. At 97+50 RT the plastic and steel lines will cross Margaret Drive back to the left edge of the ROW and continue to “MA” Sta. 104+80 LT.

At “MA” Sta. 104+35 LT a 4” and 6” plastic line will connect to the existing lines crossing the Glenn Highway at “G” Sta. 1606+20. The contractor shall pothole the lines on each side of the highway to verify depth under the ditch sections.  The Project Engineer will determine if the lines need to be lowered.  If the Project Engineer determines the existing elevation is acceptable, the contractor shall locate, shore, and protect.

The steel transmission main will extend ahead to “MA” Sta. 104+80 LT where it will turn west utilizing a notch in the ROW to install a pig launching station.

Work will commence after clearing and required surveying are completed. ENSTAR will require 98 working days to complete the relocation work described in Segment Two.

Along S. Inner Springer Loop ENSTAR’s plastic line is in conflict with the road widening.  A new line will be installed from “SIS” Sta. 15+35 LT to 16+60 LT. ENSTAR will require three (3) working days to complete the above relocation.

Along E. Inner Springer Loop ENSTAR’s plastic line will conflict with the widening and realignment of the road. ENSTAR will install new line along the LT side of the ROW from “EIS” Sta. 24+50 to 29+50. The crossing at 24+50 will be abandoned and a new crossing will be installed at 25+50 to reconnect to the line serving the fairgrounds. ENSTAR will require four (4) working days to complete the above relocation.

MATANUSKA TELEPHONE ASSOCIATION (MTA) owns and operates overhead and underground telecommunications facilities throughout the project.

Segment One

MTA’s existing underground telecommunications facilities that extend from Glenn Highway “G” Sta. 1592+50 to 1643+00 LT, extending east along Palmer Wasilla Highway to “PW Sta. 530+00 RT and west along Evergreen Avenue “E” Sta. 57+20 RT conflict with the proposed widening and will require relocation.

MTA will install new underground facilities from an existing vault at Evergreen Avenue “E” Sta. 57+20 RT to “E” Sta. 51+10 RT where the facilities will turn south. At “G” Sta. 1640+75 the new facilities will cross the Glenn Highway with a new vault at the edge of the ROW on the LT side. From the new vault MTA will install new underground facilities west along the alley to Daron Drive where they will continue north to Palmer Wasilla Highway extending to an existing vault at “PW” Sta. 530+00 RT where the new facilities will connect to the existing facilities. The Contractor shall remove the existing sidewalk and curb & gutter along the south side of W. Evergreen Avenue to facilitate this work.

MTA will install new facilities south along the edge of the Glenn Highway ROW from the vault at “G” Sta. 1640+75 LT to “MA” Sta. 124+00, cross Margaret Drive, then continue along the edge of the ROW to “MA” Sta. 85+80 LT. A new vault will be installed at this location with new facilities extending east across Margaret Drive continuing the Glenn Highway “G” Sta. 1592+50 LT where it will tie into the existing facilities.

MTA has an existing crossing at “G” Sta. 1604+35 which is in conflict and will be replaced with a new crossing at “G” Sta. 1604+05. MTA has an existing pedestal at “G” Sta. 1607+00 RT and underground cable that extends back to “G” 1588+65 RT that is in the shoulder and conflicts with the improvements at E. Inner Springer Loop. MTA will replace the cable along E. Inner Springer Loop by installing new facilities along Commercial Drive and south through a utility easement to E. Inner Springer Loop where it will turn west to “SIS” Sta. 19+35 LT. The facilities along E. Inner Springer Loop west of 19+35 LT and along the Glenn Highway Sta. “G” 1588+65 RT to 1604+05 RT will then be abandoned in place.

Work will commence after clearing, grubbing, and required surveying are completed.  MTA will require 110 working days to complete the construction and cutover required for Segment One. No portion of the existing system can be retired until the new system is in place and has been cutover.

Segment Two

MTA’s existing underground telecommunications facilities that parallel the Glenn Highway from “G” Sta. 1518+00 LT to 1592+50 LT conflicts with the proposed widening and will require relocation. MTA will connect to existing facilities at “G” Sta. 1504+00 LT and install new underground facilities along the outer edge of the ROW to Margaret Drive “MA” Sta. 85+80 LT where it will connect to the new facilities installed under Segment One.

MTA will bore a new crossing under the Glenn Highway “G” Sta. 1524+95 connecting to an existing MTA hut on the RT side of the railroad tracks. MTA will install new facilities from the hut across S. Inner Springer Loop “SIS” Sta. 12+50 LT connecting to existing cables extending north along the ARRC ROW. New facilities will continue east along S. Inner Springer Loop and connect to the existing facilities at “SIS” 20+00 LT.

Work will commence after clearing, grubbing, and required surveying are completed. MTA will require 60 working days to complete the construction and cutover required for Segment Two. No portion of the existing system can be retired until the new system is in place and has been cutover.

GENERAL COMMUNICATIONS INC. (GCI) owns and operates overhead and underground telecommunications facilities throughout the project.

Segment One

GCI’s existing underground telecommunications facilities that extend from Glenn Highway “G” Sta. 1604+50 RT to 1618+00 RT, extending east along Palmer Wasilla Highway to approximately “PW Sta. 525+00 RT and west along Evergreen Avenue “E” Sta. 61+00 RT conflict with the proposed widening and will require relocation.

GCI will install new facilities from Glenn Highway “G” Sta. 1604+50 LT along the outer edge of the ROW utilizing a joint trench with MTA to “G” Sta. 1640+75 LT. Between “G” Sta. 1640+75 LT and 1649+50 LT GCI will utilize a joint trench with MEA.

The existing crossing at “G” Sta. 1618+00 will be replaced by a new bore crossing at “G” Sta. 1640+75, GCI will place new facilities joint trench with MTA and/or MEA on Project RT from the crossing at 1640+75 to Evergreen Avenue “E” Sta. 55+75 RT where they will riser up MEA’s pole and continue overhead to “E” Sta. 61+50 RT. New facilities will extend west from “G” Sta. 1640+75 LT joint trench with MTA to Palmer Wasilla Highway “PW” Sta. 530+00 RT, GCI will then extend underground back to an existing vault at approximately “PW” Sta. 525+00 RT. The Contractor shall remove the existing sidewalk and curb & gutter along the south side of W. Evergreen Avenue to facilitate this work.

From “G” Sta. 1649+50 LT to 1660+75 LT GCI will place new cable through existing ducts. GCI’s existing underground crossing at Glenn Highway “G” Sta. 1670+50 is in conflict. GCI will relocate the crossing to overhead once MEA has installed their new poles.  GCI will attach new cable to MEA’s new poles from “G” Sta. 1660+75 RT across the Glenn Highway and continue up the south side of E. Bogard Road beyond the project limits to Montgomery Way. This extension will eliminate the existing underground crossing at “G” Sta. 1670+50.

GCI will need to install temporary overhead facilities on MEA poles between “G” Sta. 1602+00 LT to 1660+50 RT to complete the cutover of Segment One.

At E. Glacier View Avenue and S. Colony Way GCI will install new overhead cable on new MEA poles.

Work will commence after clearing, grubbing, and required surveying are completed.  GCI will require 110 working days to complete the construction cutover required for Segment One. No portion of the existing system can be retired until the new system is in place and has been cutover.

Segment Two

GCI’s existing underground telecommunications facilities that parallel the Glenn Highway from “G” Sta. 1518+00 LT to 1604+50 LT conflicts with the proposed widening and will require relocation. GCI will place new underground facilities starting at “G” Sta. 1505+50 LT, where connection to the existing facilities will take place, continuing ahead near the outer edge of the ROW to Margaret Drive “MA” Sta. 104+35 LT where it will connect to the new facilities installed under Segment One.

Work will commence after clearing, grubbing, and required surveying are completed.  GCI will require 60 working days to complete the construction and cutover required for Segment One. No portion of the existing system can be retired until the new system is in place and has been cutover.

CR651-020118_SSHC2015.17

Special Provisions

Replace Section 652 with the following:

SECTION 652
PROSECUTION AND PROGRESS – SUPPLEMENTAL REQUIREMENTS

652-1.01 DESCRIPTION.  Supplemental requirements for Section 108. Prosecution and Progress.

652-1.02 RELATED SECTIONS.  Section 108, Prosecution and Progress.

652-1.03 PROSECUTION AND PROGRESS.  In Subsection 108-1.03:

	Replace the last sentence in the 1st paragraph with: "Submit the following at the Preconstruction Conference:"

	Replace the last sentence in No. 1 with: "A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor, subcontractors and utilities will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer."

CR652/CFHWY00317

Special Provision

Replace Section 660 with:

SECTION 660
SIGNALS AND LIGHTING

660-1.01 DESCRIPTION.  Furnish and install, modify, remove, or salvage one or more traffic signal systems, flashing beacon systems, highway lighting systems, sign illumination systems, traffic count systems, electrical equipment on structures, falsework lighting, partial installations for future systems, or combinations thereof, as specified.

Where an existing system is to be modified, reuse the existing material in the revised system as shown on the Plans or specified in the Special Provisions, and salvage or dispose of all other materials.

When required by the Special Provisions, provide an on-site manufacturer’s representative to:

- Turn on and adjust the electrical system.

- Provide acceptable instruction for the operation and maintenance of the electrical system.

660-1.02 DEFINITIONS.

Use the definitions in NEMA TS 2-2003 V02.06, Traffic Controller Assemblies With NTCIP Requirements, Section 1, Definitions, along with the following:

- Electrolier. The complete assembly of pole, mast arm, luminaire, ballast, and lamp.

- Luminaire.  The assembly which houses the light source and controls the light emitted from the light source. Luminaires consist of hood (including socket, lamp, and ballast), reflector, and glass globe or refractor.

- Lighting Standard.  The pole and mast arm which supports the luminaire.

- Vehicle.  Any motor vehicle licensed for highway use by the State of Alaska.

660-2.01 MATERIALS.  Use materials that conform to Section 740, the Materials Certification List, the Plans, specifications, and the following:

Concrete	Section 501 (Class A)

Grout	Subsection 701-2.03

Reinforcing Steel	Section 503

Paint	Subsection 708-2.01

Steel Pipe Pile	Section 715

Anchor Plate	ASTM A709

Galvanizing				Subsection 716-2.07

Anchor Bolts			Section 740-2.02

- Equipment List(s) and Drawings.  Within 30 days after the Contract award, submit 8 collated copies of a portfolio of equipment and materials proposed for installation to the Department for review and approval. Include a table of contents in the portfolio(s) that includes each item’s intended use(s) and the following:

  - Materials on the Qualified Products List: The Qualified Products List does not apply to the 660 items.  Provide catalog cuts of materials to the Engineer for review and approval.

  - Materials Not on the Qualified Products List: Catalog cuts that include the manufacturer’s name, type of product, size, model number, conformance specifications, and other data as may be required, including manufacturer’s maintenance and operations manuals, or sample articles.

  - Pole Package.  A complete set of design, fabrication, and installation proposals for each signal and lighting pole. Include stamped engineering calculations, mill certifications, shop drawings, welding plans, equipment lists, and pole installation plans.

  - Materials Not Requiring Certification: Only submit those materials for review and approval if they are included on the Materials Certification List (MCL).

- As-Built Plans.  Prepare 3 complete sets of red lined as-built plans and keep them current with the construction. Detail in the as-built plans all construction changes made to the Plans. Include the following information on the appropriate sheets:

  - Location and depth of conduit runs

  - Station and offset of all junction boxes

  - Heights of signal faces and overhead signs

  - A list of equipment, including manufacturer, brand, and model number installed in each controller cabinet

Furnish copies of the as-built plans at least twice a month during construction so that they may be reviewed for accuracy and completeness. Furnish any additional information required to clarify the as-built plans and correct all discrepancies. The Department will not make progress payments for the signal and illumination work completed until reviewing accurate as-built plans reflecting the construction progress. Correct any deficiencies before payment.

Before final inspection of the work, submit 3 complete sets of as-built plans to the Engineer. You may substitute 2 colored copies of the as-built plans in lieu of keeping the 3 separate original copies. If you elect to do this, a sample of the method of copying must be approved before starting any work on the signal and lighting items.

Place 1 copy of the controller cabinet diagram, detector assignment sheet and the intersection and phase diagram as reviewed by the Engineer in clear plastic envelopes and attach to the inside of each controller cabinet.

- Warranties, Guarantees, and Instruction Sheets.  Deliver to the Engineer all manufacturers’ warranties, guaranties, instruction sheets, and parts furnished with materials used in the work before the Department assumes maintenance responsibilities.

CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL.

- Scheduling of Work.  Complete each new traffic signal system, highway lighting system, and sign illumination system and ensure it is ready for operation before opening to traffic the corresponding section of new alignment. Contact the regional DOT&PF Traffic Signal Technician 24 hours in advance of work on a signal or lighting system. Contact shall be made through the Engineer.

After staking pole foundations, verify there will be no overhead or underground utility conflicts with foundations, poles, mast arms, or conduits.  Locate and protect existing underground and overhead utilities.  The location of cables, conduits, J-boxes, foundations and poles that are shown on the Plan sheets are approximate and it is the Contractor’s responsibility to verify the actual location when working in the area.  See Subsection 105-1.06.

Existing signing and traffic markings shall not be allowed to conflict with new signal modifications.  New signing and traffic marking modifications shall not conflict with existing signals and shall be kept current with signal modifications.

Conduct work with the existing traffic signal systems remaining in operation unless authorized otherwise by the Engineer.

Incidental materials and other items that are not shown on the Plans, assembly drawings, or specified herein, that are necessary to complete the system, must be furnished and installed as though such materials and other items were shown on the Plans, assembly drawings, or specified herein.

Protect metallic materials against corrosion.  Hot-dip galvanize ferrous metals such as bolts, braces, bodies, clamps, fittings, guards, nuts, pins, rods, shims, thimbles, washers, and miscellaneous parts not of corrosion resistant steel, according to ASTM A 123 or A 153, except where other equivalent protection treatment is specifically approved in writing by the Engineer.

Asphalt Patches placed in existing asphalt for loops and conduit crossings must be placed prior to the end of shift in which the loops and crossings are placed. Asphalt patches will match the thickness of the existing asphalt to a maximum of 3 inches thick. Where the existing asphalt is thicker than 3 inches, use compacted crushed aggregate base course to make up the difference.

Do not place traffic signal systems in operation until the street lighting is energized at controlled intersections.

Install detector loops and underground conduit before applying new pavement.

Do not pull conductors into conduit until the junction boxes are set to grade, crushed rock sumps are installed, grout is placed around the conduit, and metallic conduit is bonded.

In vehicular undercrossings, place soffit lights in operation as soon as practicable after removing falsework from the structure. Place lighting for pedestrian structures in operation before opening the structure to pedestrian traffic.

- Safety Precautions. Before starting work on existing street lighting circuits, de-energize the system by opening disconnect switches, and/or opening bypass switch plugs, and tagging each opened device as detailed in Part 4, Section 44, Article 440 of NESC. Where said circuits are under the control of an electric utility, obtain written assurance daily from the utility that the circuit being worked on has been de-energized.

Post suitable signs at load centers when any of the circuits from that load center are being worked on.

Existing circuits listed on the wiring diagrams and Plan sheets were obtained from as-built information and must be verified before work involving those circuits.

- Excavating and Backfilling.  Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors before final lift paving.  Provide traffic control to complete this work according to the requirements of Section 643.  Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit.  Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

When conditions allow HDPE conduit to be installed by a plowed technique, restoring the area disturbed from the process, shall be accomplished according to Subsection 204-3.01. Density testing may be waived and compactive effort substituted at the discretion of the Engineer.  This work is subsidiary to conduit installation.  Use Selected Material, Type A for backfill.

Dispose of, according to Subsection 203-3.01, excavated materials that remain after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in Subsection 703-2.07. Disposal of this material is subsidiary to the 660 Pay Items.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations.  Backfill excavations with materials that meet the following requirements:

- Backfill foundations with material that meets the requirements of Selected Material, Type A that passes through a 3 inch sieve.

- Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift.

- In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

- Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material cleaned free of rocks exceeding a 1 inch maximum dimension.  Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to Subsection 203-3.04.  In other locations, compaction may be as approved by the Engineer.

4.	Welding.  Complete welding according to Subsection 504-3.01.8. Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval.  The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes that were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface.  For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole.  Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole.  Grind the welds smooth and flush with the adjoining pole and disk surfaces.  Repair the damaged finish according to Subsection 660-3.01.8.

5.	Removing and Replacing Improvements.  The Contractor shall complete the following work at the Contractor’s expense.

a.	Remove improvements that block completion of the work detailed in the Plans as specified herein.

b.	Reconstruct with new materials the non-reusable improvements the Contractor removed to complete the work.

c.	Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

d.	Reconstruct with new materials improvements damaged or removed by the Contractor not conflicting with the work and not scheduled for removal.

Nonreusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings.  Reusable improvements include the items that were made before installation.  Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition.  In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil.  Match the top of the topsoil with the bottom of the vegetative mat. Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621.  Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

6.	Salvaging and Reusing Electrical Equipment.  When the Plans include existing electrical equipment scheduled for removal or relocation, remove, and store the equipment listed in the following paragraph without damaging it.  Deliver removed equipment not scheduled for reuse to the local District Maintenance Station or place specified in the Plans or Special Provisions.  Notify the district superintendent or person specified by telephone one week before planned delivery date.

Salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, load centers, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for relocation.  The Contractor shall replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.

Controller assemblies and load centers include the cabinet and equipment contained in the cabinet before Contract award.

Remove from the highway right-of-way materials associated with the equipment removed or relocated and not scheduled for reuse, including conduits, junction boxes, conductors, and foundations.  Raze the tops of foundations abandoned in place according to Subsection 660-3.02.  Fill the holes left by removing junction boxes and foundations with Selected Material, Type A and compact as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned in place.  The Department may require a credit for this waiver.  Remove the ends of abandoned conduits from the junction boxes that will remain in service.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer.  Note the location and condition of the materials.  When material specified for reuse is found in an unserviceable condition, the Engineer will determine whether to repair it or replace it with new material that will be paid for as extra work under Subsection 109-1.05.  Retain a copy of the inventory and give the original documents to the Engineer.

When the Plans specify reinstalling existing equipment at new locations and installing State furnished equipment, complete the following work at the Contractor’s expense.

a.	For poles, install new foundations, furnishing the new nuts, bolts, washers, and conduits needed to complete the installations.

b.	For lighting poles, install new illumination tap wires and fused disconnect kits.

c.	For luminaires, clean the luminaires inside and out and install new lamps of the same wattage.

d.	For signal heads, furnish and install the mounting brackets needed to complete the relocation, and clean the signal heads inside and out.

e.	For poles and undisturbed poles from which the Plans specify removing equipment, repair the holes that were made to mount equipment according to Subsection 660-3.01.4 Welding and repair the finishes according to Subsection 660-3.01.8 Repairing Damaged Finishes.

Repair holes left in the shafts of exiting metal poles, due to removal of equipment or mast arms, by welding in a suitable disk, grinding smooth, and painting as provided for repair of damaged coatings in AASHTO M 36.

When ordered, the Engineer will pay for repairing existing damaged finishes on existing equipment according to Subsection 660-3.01.8 as extra work.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to Subsection 660-2.01.1.

Deliver the salvaged materials undamaged to the local DOT & PF Maintenance and Operations Yard.

Contact the local state Electrician one week before planned delivery.

7.	Field Tests.  Electrical circuits must pass the following tests before the Engineer will accept the work for payment.  Perform these tests in the presence of the Engineer, and document the results of each test on a per circuit basis.  Retain a copy of test results and give the original documents to the Engineer.  Furnish equipment needed to perform these tests.

Replace or repair at the Contractor’s expense, and in an approved manner, faulty materials and work revealed by these tests.  After making repairs, repeat tests on the repaired circuit and continue this process until circuits have passed required tests.  The Department reserves the right to have the Contractor retest circuits, and to use the retest results to accept or reject individual circuits.

a.	Grounds. Before completing the circuitry and functional tests, physically examine conduits ends, junction box lids, load centers, and the foundations for signal posts and poles, lighting poles, and controller cabinets to ensure the grounding system required by Subsections 660-3.06 and 661-3.01 has been installed and splices and connections are mechanically firm.

b.	Continuity.  Test each loop detector circuit for continuity at the roadside junction box before splicing the loop detector to the lead-in cable.  Each loop detector must have a resistance less than 0.5 ohms.

After splicing the loop detectors to the lead-in cables, test each pair at the controller or detector cabinet.  Each pair must have a value less than 5 ohms for single pair lead-in cables and 10 ohms for multipair lead-in cables.  The continuity test ohm reading at the cabinet must be greater than the ohm reading measured for the loop detector at the junction box.

c.	Insulation Resistance (megohm) Test.  Complete this test to verify the integrity of each conductor’s insulation after pulling the conductors and cables into position and before terminating the conductors.  At 500 VDC, each conductor’s insulation shall measure a minimum resistance of 100 megohms or the minimum specified by the manufacturer.  With single conductors, complete the test between each conductor and ground.  In each multiconductor cable, complete the test between conductors and between each conductor and ground.

After splicing the loops to the shielded pairs in the lead-in cables, measure each pair in the lead-in cables at the controller or detector cabinet between one conductor and the cabinet ground rod.

d.	Inductance Test.  Measure each detector loop and lead-in cable system at the controller or detector cabinet.  The inductance must be in the range of 50 to 500 microhenries.

e.	Circuit.  Energize every signal indication circuit with lamps installed before installing the load switches.

f.	Functional.  Perform the following tests on each signal and lighting system after the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity, and circuitry.

(1)	For each new traffic signal system, complete at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory operation.  The Engineer may decide to omit the flashing portion of the test for modified signal systems and for new signals that replaced existing signals that remained in operation during the construction phase.

If the Engineer omits flashing operation and the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for five days with continuous, satisfactory operation.

Begin the signal functional tests between 9:00 a.m. and 2:00 p.m. on any day, except a Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Before each system turn on, aim signal faces according to Subsection 660-3.08 and ensure equipment specified in the Plans is installed and operable, including: pedestrian signals and push buttons; signal backplates and visors; vehicle detectors; highway lighting; and regulatory, warning, and guide signs.

(2)	Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5 day operational test using the photocell.

(3)	Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

(4)	Perform a continuous 5 day burning test on each pedestrian overpass and underpass lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system functions normally when power is returned.

8.	Repairing Damaged Finishes.  Examine new, reused, and State furnished equipment for damage to its finish before putting the equipment into service.  Repair the damaged finishes found according to the following:

a.	Galvanized.  Repair damaged areas more than 12 inches away from welds and slip fit areas, by applying minimum 7.8 mils of zinc based alloy applied according to ASTM A780.

If the damaged areas are within 12 inches of welds and slip fit areas, make the repair by applying a minimum 7.8 mils of zinc rich paint applied according to ASTM A780.

b.	Painted.  Repair damage to painted finishes according to the following

(1)	Wash the equipment with a stiff bristle brush using a solution containing two tablespoons of heavy duty detergent powder per gallon of water.  After rinsing, wire brush surfaces to remove poorly bonded paint, rust, scale, corrosion, grease, or dirt.  Remove dust or residue remaining after wire brushing before priming.

(2)	Factory or shop cleaning methods may be used for metals if equal to the methods specified herein.

(3)	Immediately after cleaning, coat bare metal with pretreatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

(4)	Give signal equipment, excluding standards, a spot finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

(5)	Give nongalvanized standards 2 spot finish coats on newly primed areas.

Paint coats may be applied either by hand brushing or by approved spraying machines.  Perform the work in a neat and workmanlike manner.  The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint spraying machine prove unacceptable.

9.	Regulation and Code.  Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the Authority Having Jurisdiction.

660-3.02 FOUNDATIONS.

- Cast-in-Place Foundations.  Cast-in-place foundations for posts and poles in drilled holes. Use either precast or cast-in-place foundations for cabinets. Locate the tops of traffic signal post and pole foundations flush with the adjacent finished walkway, shoulder, or surrounding ground.

- Form the entire controller foundation and the top 12 inches of pole or post foundations and give the top a smooth steel trowel finish.

- Place conduits in the center of the pole-post foundations with clearance allowed for bushings. If subsurface conditions prevent completing a drilled hole, and when approved, use a corrugated metal pipe (CMP) form as a substitute for the drilled hole. Consider the savings in concrete to offset the cost of supplying and installing the CMP form. No additional payment will be made for the CMP formed foundation.

- When a CMP is used, over-excavate the area around the form enough to allow for proper compaction around the form. Perform backfill operations according to Section 204. Do not use water for drilling operations or for any other purpose where it may enter the hole.

- Use controller cabinet anchor bolts as recommended by cabinet manufacturer and set with a template.

- Place Class A concrete meeting Section 501. Place reinforcing steel meeting Section 503. If required, use corrugated steel pipe that is at least 14 gage, meeting Subsection 707-2.01.

- Drill holes or use forms that are vertical and true to the locations shown in the Plans. Before placing the form or reinforcing steel cage, remove loose material to ensure the foundation rests on firm, undisturbed ground.

- If a reinforcing steel cage is required, place and secure it symmetrically about the vertical axis and securely block it to clear the sides of the foundation. Use a template to securely support all anchor bolt assemblies and conduit ends so they do not move during concrete placement.

- Do not permit surface water to enter the hole. Before placing concrete, remove all water that may have infiltrated in the hole. Thoroughly moisten both the forms and the ground before placing concrete. Pour each foundation in one continuous pour.

- Do not erect or place posts, poles, and pedestals on the foundation until 7 days after placing the concrete. Plumb the assembly by adjusting the nuts on the anchor bolts before attaching the skirt.

- Replace, with no additional compensation, all finished foundations with anchor bolts that do not match the base plate of the pole or are out of plumb. Do not modify the anchor bolts or base plate to get the base plate set on the leveling nuts. Protect foundation anchor rods from damage before installing controller cabinets.  The Engineer must approve the method used for protection.  This work does not relieve the Contractor of responsibility specified under Subsection 107-1.15.

- Furnish anchor rods that conform to ASTM F1554, the grade and supplementary Charpy V-Notch requirements listed in the Plans. Furnish each anchor bolt with three nuts and two washers.

Install the bottoms of the bottom leveling nuts in a level plane within 1 inch of the top of foundations.  Adjust nuts until their tops form a level plane.  Install one washer on top of leveling nuts and, after setting the pole on these washers, install one washer under top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Generously lubricate the bearing surface and internal threads of top nuts with beeswax.  Tighten top nuts to a "snug" condition.  Use a click type torque wrench to apply 600 foot-pounds of torque to the "snug" top nuts.

After the top nuts are tightened to the correct torque, use a hydraulic wrench to rotate top nuts an additional one sixth (60) turn, while preventing the leveling nuts from turning.

- Attach a bare, copper wire as a grounding electrode conductor to the spiral bar in the reinforcing steel cage.  Use an irreversible compression connector to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled #4 AWG, bare, copper wire as the grounding electrode. Route the conductor to protrude near the top, center of the foundations.  Slide a minimum 6 inch long, PVC or HDPE, protective sleeve over the conductor.  Allow 1 inch of the sleeve and 24 inches of conductor to protrude from the foundations.

- Pile Foundations.

  - Install pipe piles according to Section 505.

  - Install pipe piles open-ended and to a minimum depth of 15 feet (less top projection).

  - Use CJP groove welds for all circumferential welds.

  - Inspect 100% of CJP welds using UT or RT.

  - Backfill and compact the work hole around upper portion of each pile in 8-inch lifts with a soil-cement mixture.

  - Certify steel pipe piles by matching the stencils on the pipe piles (by 300 foot lots) to the physical and chemical tests for the applicable lot.

  - Use no more than one splice per foundation. Locate the splice at least 10 feet from the top of the pile.

    - All Foundations.

- Install frangible couplings according to the manufacturers written installation instructions. Use shims furnished by the coupling manufacturer.

- Provide new foundations and anchor bolts of the proper type and size for standards that are to be relocated. Install the anchor bolts on a bolt circle that matches the base plate.

- Install a raised Type III junction box on the door side of the controller cabinet, and butt it against the cabinet’s foundation unless installing a one-piece cabinet/junction box foundation. Extend the top of the controller cabinet foundation 18 inches above the junction box and provide it with a 1-inch diameter drain. The drain connected to the cabinet interior must empty to the rear and above the ground. Place all conduits in the door side half of the foundation to provide adequate terminal block clearance.

- Existing foundations may be abandoned-in-place. However, remove the tops of the foundations, reinforcing steel, anchor bolts, and conduits to at least 12 inches below the roadway subgrade, sidewalk, or unimproved ground. Backfill the resulting hole with Selected Material, Type A and compact material as directed by the Engineer.

660-3.03 CONDUIT.  Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified.  Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits.  Install conduits of the sizes specified along the routes detailed on the Plans.  When routing is not shown, route conduits as directed by the Engineer.

- Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

- Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches.  Excavate, bed conduits, and backfill trenches according to Subsection 660-3.01.3, Excavating and Backfilling.

- Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods.  Jacking conduits into position is allowed.  However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

- If encountering obstructions during jacking or drilling operations obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 11/4 to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

- Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs.  To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box. At junction boxes where polyethylene conduits runs are to enter the junction box, install a 5 foot section of RMC on the horizontal end of the RMC sweeps.

- Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box.  Extend the ends a minimum of 2 inches beyond the inside wall of the box.

- Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs.  Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors.  Cover the holes with a wrap of approved filter cloth secured with 2 self clinching nylon cable ties.

- Keep conduits clean.  Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends.

- At the low points of conduit runs, install sumps containing a minimum 2 cubic feet of coarse concrete aggregate material that conforms to Subsection 703-2.02.  Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

- Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary.  Install additional drains and aggregate sumps at the low spots, if any.

- Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 21/2 inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

- Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit.  Cut the same number of threads as found on the factory threaded ends.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.  Do not use slip joints or pieces of running thread pipe.

- Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

- When standard couplings cannot be used to join conduit components, use approved threaded unions.

- Bury a continuous strip of 4 mils thick, 6 inch wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a red background.

- When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

- In foundations, install 90 degree elbows and conduits of the size and quantity shown on the Plans.  Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

- Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct sealing compound.

- Install expansion fittings in conduits that cross expansion joints.

- Install a polypropylene pull rope with a minimum 200 pound tensile strength in future use or spare conduits, and reinstall the plugs.  Double back pull rope, at least two feet, into both ends of each conduit.

- The Contractor may install conduits larger than the sizes specified.  If used, it must be for the entire length of the run.  Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

- Clean existing conduits that will remain in service using a heavy duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch.  Clean the conduits before pulling in new cables and after removing cables to be removed or replaced as follows:

  - When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

  - Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

- When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit.  When extending existing conduits, add no more than a 90 degree horizontal bend to the extension.

- When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

- When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

- Remove the ends of abandoned conduits from junction boxes that will remain in service.

CR660.1-110316/CFHWY00317

- When Plans call for connecting polyethylene conduit to RMC use a Shur-lock type couplers or approved equivalent. Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

CFHWY00317

660-3.04 JUNCTION BOXES.  Install precast reinforced concrete junction boxes of the types specified.  For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them.  For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them.

Junction Box Location

When shown, install junction boxes at the station and offset locations specified.  When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement.  If the 8 feet offset falls:

1.	In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility. When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

2.	In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

3.	Outside the right of way, install the boxes just inside the right of way line.

4.	In a raised median, install junction boxes near the center of the median.

5.	In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

6.	Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

7.	On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing Type 1A junction boxes in driveways and in locations subject to use by heavy trucks.  When shown near the ends of medians, install junction boxes at least 10 feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.  When installing copper signal interconnect cable use minimum size Type II junction boxes.

Four (4) Limitations

Limit the distance between adjacent junction boxes to the following dimensions:

1.	400 feet for conduits that contain signal interconnect cable only.

2.	300 feet for conduits, that exclusively contains two loop lead-in cables.

3.	300 feet for conduits that contain a single cable other than signal interconnect.

4.	190 feet for conduits, that contains more than one cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work; otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria.  In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade.  In seeded areas, install the tops of junction boxes to 2 inches below all other areas.

Bond junction box lids to an equipment grounding conductor according to Subsection 660-3.06.  Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box.  Drains shall consist of porous backfill material that conforms to Subsection 703-2.10.  Minimum drain dimensions include an 18" depth and a length and width equal to those of the junction box it drains.  Compact the porous backfill material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker.  Conform markers to the American Public Works Association Standards including but not limited to:

- Color - red

- Material - high-density polyethylene

- Shape - round (ball like)

- Size - 4 to 5 inches in diameter

- Configuration - encapsulating an antenna tuned to the appropriate frequency for locating power

- Responsive range - up to 5 feet away from the locator device

- Environmental conditions - including extremes in temperature at the installation site

- Contain no internal power source

Acceptable marker manufacturers include:

- 3M, Dynatel EMS ball marker model no. 1402-XR

- Tempo (a Textron Company), Omni Marker

- Substituted, equivalent approved equal device

660-3.05 WIRING.  Wire all cabinets with conductors sized to handle the amperage drawn under full cabinet use. Make wiring neat in cabinets by cabling wires together with self-clinching nylon ties. Terminate all spare conductors on terminal blocks. Attach all conductors, including spares, to terminal blocks with “spade” type terminal lugs. Furnish additional terminal blocks if enough locations are unavailable in existing terminal blocks. Run signal cabling continuously without splices from the controller cabinet to the termination lugs in the signal housing.

- Do not pull conductors into conduits until the following conditions are met:

  - The prescribed clearances around conduit ends are provided,

  - Crushed rock sumps are installed under junction boxes,

  - Conduit ends protrude above the bottom of junction boxes within the prescribed range,

  - New conduits are free of material that became lodged in them during the completion of the work,

  - Reused conduits are cleaned according to Subsection 660-3.03,

  - Junction boxes are set to grade, and

  - Grounding bushings are installed on the ends of metallic conduits.

- Pull conductors by hand or by approved commercially built cable-pulling equipment that is specially designed for that purpose. Do not pull cable by any other means. Equip the cable pulling device with a force limiting circuit and force gauge.

- Use wire-pulling lubricant when placing the cables and conductors in conduit. Do not allow the tension of the wire or cable to exceed the manufacturer’s recommend allowable tension for the conductor or cable.

- When adding new conductors to a conduit with existing conductors, remove all conductors and clean the conduit with a mandrel or brush. Pull both old and new conductors through as a unit. In a new installation, pull all conductors through the conduit as a unit.

- Leave at least 1 foot of slack in the bottom of each signal or combination signal and lighting pole of each signal conductor or cable. Neatly leave at least 3 feet of slack illumination and signal conductor or cable curled up in the bottom of each junction box or splice location.

- Separate the neutral for pedestrian push button circuits from the signal light circuit neutral.

- Run all signal and feeder conductors continuously without splices from a terminal block located in a cabinet, compartment, or signal head, to a similarly located terminal block. When modifying an existing signal system when specifically shown in plans, splice existing conductors (cables) to new conductors (cables) as required to complete the signalsystem. Make these splices when indicated in the plans.

- Route highway illumination cable through each lighting pole designated for connection to that cable’s circuit. Do not splice illumination cable between a load center and a pole or between poles. Join the individual conductors by using non-insulated, overlap type pressure connectors. Insulate with mastic-lined heat shrink tubing or 2 layers of one-half lapped UL listed electrical tape. Do not use wire binding screws, studs, or nuts. Stagger splices to minimize the overall diameter.

- Install all loops in 1-inch rigid schedule 80 PVC conduit in the roadway and to the nearest junction box. Run loop lead-in cable continuously without splices from the controller cabinet to the curbside detection junction box nearest the loop being spliced to the lead-in cable. Splice the loop(s) to the lead-in cable by soldering at the junction box and encapsulating in a waterproof splice kit.

Multiple loop configurations must have the individual lead-ins, multiple pair, or single pair brought to the controller cabinet for termination. Make series connection of loop lead-ins in the controller cabinet only. Wind all loops in the same direction with the starting lead marked with an “S.” Connect the black conductor of the pair shown in Table 660-1 to the “S” designated conductor of the loop. Connect multiple loop detectors in the same lane so that the adjacent loops are in alternating directions clock wise (CW), counter clock wise (CCW), etc.

- When splicing loop detectors to multi-pair loop lead-in cables, complete the work according to the following.

a.	See the Plans for the identifying number assigned to each loop detector and the loops assigned to each loop lead-in cable. Using this information, splice the loop detector tails to the paired conductors found in each lead-in cable, using the color code in Table 660-1.

b.	Remove a short section of cable jacket and only cut the shielded pairs dedicated to loop detectors being spliced. Run these pairs, without splices, to the controller cabinet.

c.	Strip the insulation from the ends of the conductors. With the loop and lead-in conductors parallel to one another, solder them together using approved splice connectors.

d.	Insulate and seal each soldered connection with a mastic lined heat shrink tubing; crimp the ends of the heat shrink tubing with a pair of needle nose pliers.

TABLE 660-1 
MULTIPLE PAIR LOOP LEAD-IN COLOR CONNECTION SCHEDULE

| Loop Detector Number | Colored Pair |
| --- | --- |
| The lowest numbered loop detector | Red and Black |
| The second lowest numbered loop detector | Blue and Black |
| The third lowest numbered loop detector | White and Black |
| The fourth lowest numbered loop detector | Green and Black |
| The fifth lowest numbered loop detector | Brown and Black |
| The sixth lowest number loop detector | Yellow and Black |
| Usually a spare pair | Orange and Black |

e.	Crimp spade terminals to the ends of the shielded pairs in the controller cabinet.

- Maintain the electrical isolation between shields and do not allow the drain wires to come in contact at any point other than the ground bus in the cabinet. Tie all drain wires to the ground bus at the controller cabinet.

- Encapsulate illumination/power cable splices in four piece molds that are held together with stainless steel hose clamps. Two pieces form a cylinder and two flexible end caps. Seal the ends and allow the conductor entry. Use molds with dimensions suitable for the splice made, encase the cable jackets, and fill  with an insulating and sealing epoxy resin.  .  Furnish molds rated for 600 VAC operation, feature fill, and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, one splice may be used in the following cases:

a.	An in-line splice may be used when a planned cable run exceeds the length available from the manufacturer on a single spool of cable.

b.	In a run of 1,000 linear feet or more.

When a cable is spliced, it shall occur within an appropriately sized junction box or in the base of an electrolier designed for said splice.

Insert a loose woven polyester web that allows a full 1/4 inch of insulating compound to flow between the splice and the inside of the mold. Fill the PVC molds with re-enterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is non-corrosive to copper, and does not support fungi or mold growth.

- Encapsulate all loop lead-in cable splices in rigid, transparent, PVC or PE approved tubing filled with re-enterable polyurethane electrical insulating and sealing compound. Furnish splice kits rated for 1000 volts AC operation and direct burial. When filling the mold bodies of loop lead-in cable splices, use a compound that provides re-entry capabilities.

- Permanently identify all cables and single wire conductors by labeling all pole bases and cabinets, at each detector loop tail/lead-in cable and illumination cable splices, and in junction boxes adjacent to lighting and signal poles. When modifying an existing system, label all new and existing lighting cables/conductors with circuit numbers at locations noted above. If the existing circuits are not identified, the Engineer will provide the required circuit numbers.

- Label the cables used in the signal and illumination systems with the following legends:

  - Use the legends included in Table 740-2, for the cables listed.

  - Use the loop number shown on the Plans to label each tail of all loop detectors and the paired loop lead-in conductors in the controller cabinet.

  - For interconnect cables, use the first letter of the direction the cable follows to the adjacent intersection on each cable. Add a number suffix if more than one cable is routed to the adjacent intersection.

Furnish the two types of identification tags listed below that feature hand written legends. Write the legends specified neatly and legibly, using a black marking pen recommended by the tag manufacturer. Replace at no expense to the State all identification tags the Engineer deems illegible.

- Use identification cable ties for labeling loop detector tails and the paired conductors included in each loop lead-in cable in the controller cabinet. Furnish identification cable ties made of nylon that feature a nonmagnetic stainless steel locking device embedded in the head and a tag attached "flag style" to the head. Use cable ties consisting of a single strap with a minimum size tag of 3/4 inch by 3/8 inch.

- To label all other cables, use cable tags made of nylon reinforced vinyl impervious to the elements and which will not tear. Provide tags with a 4 inch by 1-3/4 inch minimum size that attach flag style at one corner to a single strap. Furnish yellow tags for labeling all signal and interconnect cables and red tags for labeling lighting and feeder cables.

- Terminate the control and power cables as shown in Table 740-2.

- Telementry cable termination shall be coordinated with a signal technician. Provide type No. 66B3-50 terminal blocks as required.

- Wire luminaires using No. 10 AWG illumination tap conductors that run from the fused disconnect kit in the pole base.

Install a fused splice connector between the line and luminaire ballast tap conductors in the base of every pole equipped with a luminaire.

Attach the conductors to the connector halves with setscrew type pressure connectors. Provide the plug and socket assembly so that the fuse remains in the load side plug without exposing live metal parts when the connector separates and the coil springs are not included in the current carrying circuit.

Make the fused connectors readily accessible from the handhole. Install tap conductors to prevent slack when their ends touch the top of the foundation.

- Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

- Whenever conductors cannot be terminated as specified in the Plans in circuit breakers due to size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductors to 5 feet.

- Spare lighting conductors shall be capped in the pole bases and load centers by cutting the wire flush with the end of the insulation and bending the conductor back against itself and securing with three layers of electrical tape to prevent any possibility of making contact with ground or current carrying conductors.

660-3.06 BONDING AND GROUNDING.  Bond and ground branch circuits according to the NEC and the following requirements:  Make noncurrent carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor.  Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install grounding bushings with insulated throats on the ends of metallic conduits.

Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size #8 AWG grounding conductors, except in those conduits that contain circuit conductors larger than #8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installation or removal of conductors from existing conduits, retrofit with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross sectional area equal to a #8 AWG and eyelet spaced at 6 inch intervals.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.

Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the #4 AWG grounding electrode conductor using irreversible compression connectors at Portland cement concrete foundations.  For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 5 feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the handhole of each pole.

Bond slip base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the handhole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a 3/4 inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

When routing a new conduit into an existing junction box or replacing an existing junction box, new and existing conduits shall have the grounding improved to current specifications.

660-3.07 TRAFFIC CONTROLLER ASSEMBLIES.  Prepare each solid-state, traffic controller assembly to operate various traffic signal devices as shown on the Plans. The controller must provide right-of-way, clearance, and other indications using duration and sequence as determined by preset programming.

Details of operation for the complete controller assembly must be according to the traffic phases; preferential phase sequence and concurrence; signal indications; signal indication sequence; detection requirements; and other details shown on the Plans or as specified herein.

- Shop Tests.  The Controller Assembly manufacturer shall conduct a pretest of the cabinet and controller assembly. The pretest includes but is not limited to:

  - Ensure the cabinet is free of paint scratches, dents, sharp edges, and other physical defect.

  - Ensure cabinet hinges, heater, ventilation system, lighting, and door locking mechanism function properly.

  - Ensure that there are no shorts between AC+, AC-, and GND anywhere in the cabinet.

  - Check that there is no continuity between AC+ and DC+.

  - Check for continuity between any green wire connection point and GND.

  - Ensure devices within the cabinet are labeled properly.

The Controller Assembly manufacturer shall conduct a final test of the cabinet and controller assembly.  Qualified Cabinet Test Technicians shall conduct the final test.  The final test includes but is not limited to ensuring proper operation of; flash colors & combination, standard controller phasing, pedestrian pushbutton isolation, MMU, circuit breaker/fuse operation, telemetry operation, loop panel/detector rack operation, EVP operation and, proper police & auxiliary panel operation.

Upon completing the final test the cabinet shall be run, "burned in," under full loads for a period of not less than 48 hours with a test timing plan in effect which utilizes full cabinet phases and functionality.

In the course of testing, a component found to function incorrectly or exhibit physical damage must be replaced with an equivalent new component before delivery.  Should the cabinet fail during burn in, the cause of the failure must be remedied and the test restarted with another 48 hours of burn in. The intent of this specification is to meet or exceed the requirements of Econolite test procedure MWI-10-28 Rev. C. With prior approval of the Engineer, other equivalent test procedures may be substituted.

Upon completion of the pretest, final test, and burn in, the Controller Assembly manufacturer shall issue a letter of certification stating that the required tests have been completed, note defects found and the remedial action taken.  Further, the certification shall state the assembly conforms to the NEMA TS 2-2003 v02.06, Traffic Controller Assemblies with NTCIP Requirements, Section 2 Environmental Requirements.  Submit the certification letter and copies of the test results to the Engineer.

The work required in this subsection is subsidiary to the associated traffic signal system under Pay Item 660(1X) Traffic Signal System Complete.

- Controller Cabinet Installation.

  - Where the cabinet is mounted on a concrete pedestal foundation, place a 1-inch drain hole or pipe with screen in the foundation, connecting to the cabinet and emptying above the ground line.

  - Place a 3/8-inch fillet of silicone caulking between each controller cabinet and the concrete slab foundation to prevent dust and dirt from entering the cabinet.

  - When called for in the Plans or Special Provisions, add 2 inches of approved foam insulation within the bottom of the cabinet between the control equipment and the concrete base. Design all wiring, terminals, and other items to allow sufficient room for the insulation.

  - On Precast Controller Foundations. When called for in the Plans or Special Provisions, place a 3/8-inch thick, 2-piece exterior grade plywood board on the bottom of the cabinet and under the foam insulation. Place the plywood within the controller cabinet, and do not extend under it. Make holes to allow for the conduits entering the cabinet. Place a pliable sealant composed of a silicon caulking compound between the plywood board and the cabinet and between the plywood board and all the conduits.

  - Place a ground rod in the Type III junction box next to the cabinet or in the foundation of the cabinet if it is precast foundation.

  - See Subsection 660-3.05 and Section 740 for wiring requirements.

- Controller Operation.  Provide the following operations.

  - Wire the controller cabinet to flash the yellow signals on the main street or highway, and the red signals on the cross streets and left turn lanes.

  - Make the flashing circuit independent of the controller unit. They must remain in operation upon shutdown of the controller or removal of the controller from the cabinet.

  - Wire the controller cabinet so that removal of the conflict monitor causes the intersection to go into flashing operation.

  - Accomplish transfer to flashing operation by relays between the normal load switching device and the field terminals.

  - Do not operate pedestrian pushbuttons at more than 24 volts.

  - Controller Priorities.  Prioritize the drives, controls and equipment so that each device, control, or item of equipment overrides the operation of those items listed below it:

    - Power failure

    - Power restart

    - Flashing

    - Railroad preemptor

    - Emergency vehicle preemptor

    - Phase selector

    - Interconnect

    - Time switch

    - Normal controller unit operation

Provide the following preemption operations when called for on the Plans or as specified in the Special Provisions.

  - General.  Preemption units must use the controller unit functional inputs and timings to the largest extent possible. Signal load switching control must remain with the controller unit.

  - Railroad Preemption.  The Railroad Preemption Routine must consist of 4 functional intervals in the order listed below:

    - Enter Preemption Interval.

        - Energize a 120 VAC alarm circuit which may be used for a sign, bell, or beacon.

        - Immediately advance to the pedestrian clearance interval of any walk that is being displayed. On any phase other than the track clearance phase(s), abbreviate the pedestrian clearance interval by a timer with a minimum range of 0-30 seconds.

        - Following the pedestrian clearance period, the controller must advance into and time normally the vehicle clearance intervals.

        - If the preemption is received while in the track clearance phase(s), skip step (b) and (c) above.

    - Track Clearance Interval.

        - Provide a timing period to allow sufficient green clearance time for any vehicles that may be stopped on or immediately behind the railroad tracks. The timing must be adjustable over a range of 0 to 30 seconds.

        - Following the track clearance period, the controller must advance into and time normally the vehicle clearance interval(s).

    - During Preemption Interval.  Allow the controller to operate normally with the exception of not serving those phases that conflict with the railroad crossing. Keep this interval in effect until the preemption call is removed.

    - Leaving Preemption Interval.

        - De-energize alarm circuit.

        - Immediately advance to the active phase normal pedestrian and/or vehicle clearance interval(s).

        - The controller must advance to those phases that were omitted under preemption control when complete control is returned to the controller unit.

  - Emergency Equipment Preemption.  The Emergency Equipment Preemption Routine must consist of 3 functional intervals in the order listed below:

    - Enter Preemption Interval.

        - Energize a 120 VAC alarm circuit which may be used for a sign, bell, or beacon.

        - Immediately advance to the pedestrian clearance interval of any walk that is being displayed. On any phase other than the track clearance phase(s), abbreviate the pedestrian clearance interval by a timer with a minimum range of 0-30 seconds.

        - Following the pedestrian clearance period, the controller must advance into and time normally the vehicle clearance intervals.

        - If the preemption call is received while in the preempt phase(s), skip step (b) and (c) above.

    - Preempt Phase Interval.  Hold the controller in the preempt phase(s) until the call is removed.

    - Leaving Preemption Interval.  When the preemption call is removed, the controller unit must immediately revert to normal operation.

660-3.08 SIGNAL AND LIGHTING INSTALLATION REQUIREMENTS. Install signal and lighting equipment according to the details shown on the Plans and the following:

Apply antiseizing compound to the following fasteners:  frangible couplings, mechanical grounding connectors, bolts that secure handhole covers and signal mounting hardware to poles and mast arms.  Remove the fasteners from luminaire mounting brackets, fused disconnect kits, grounding bushings, and signal faces that secure the visors, and apply antiseizing compound to these fasteners before completing the installation.

Before passing conductors through the holes made in posts, poles, and mast arms for wireways, remove the burrs and sharp edges from the inside and outside of these holes.

Until each traffic signal and/or flashing beacon goes into operation, keep the vehicular and pedestrian signal faces covered with beige colored canvas shirts sized to fit the signal faces shown in the Plans.  Each signal shirt shall feature elasticized openings that fit over the visors and at least two straps to secure it to the signal.  Provide shirts with a legend that reads "out of service" and a center section that allows an operator to see the indications during system tests.

When not shown in the Plans, determine the shaft lengths of lighting and signal poles and signal mast arm connector plate locations to provide the plan mounting heights of luminaires and traffic signal heads.

Furnish work to install foundations for relocated poles, including: conduit, excavation, reinforcing steel, class A concrete, anchor bolts, nuts, and washers.

- Electrolier Installation.  Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm.  After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

- Signal Pole Installation.  Install signal poles with a slight rake by plumbing the side of the pole opposite the mast arm just above the base plate.  Tighten the nuts on the anchor bolts/rods as described in Subsection 660-3.02..

Cover the gap between the foundation and base plate by installing a metal skirt around the base plate, secured with stainless steel sheet metal screws.

- Vehicular Signal Head Installation.  With two piece mast arms, do not install signal heads within 12 inches on either side of the overlapped splice section.

Attach each side mounted terminal compartment with two 1/2" x 13 bolts, with washers, threaded into holes tapped into the side of the pole at the location shown on the Traffic Signal Hardware Detail Sheet in the Plans.  Install the vertical pipe members plumb.

When installing 4 or 5 sections vertically stacked signal heads on the sides of poles, secure the vertical pipe to the pole using a steel conduit hanger mounted 6 inches below the top horizontal pipe.

Aim through phase vehicular signal faces at a point located a distance from the face as shown in Table 660-2.  If two through signal faces are not visible from this point at a height of 42 inches above finished grade, consult the Engineer for corrective measures.

| TABLE 660-2 |  |
| --- | --- |
| THROUGH PHASE SIGNAL FACE AIMING POINTS |  |
| 85th Percentile Speed (mph) | Minimum Visibility Distance (feet) |
| 20 | 175 |
| 25 | 215 |
| 30 | 270 |
| 35 | 325 |
| 40 | 390 |
| 45 | 460 |
| 50 | 540 |
| 55 | 625 |
| 60 | 715 |

- Pedestrian Signal and Push Button Installation.  Orient pedestrian signal faces at the center of the crosswalk on the opposite side of the street.  Attach each clamshell bracket with two 1/2" x 13 bolts threaded into holes tapped into the side of the pole.  Install a spacer, furnished by the bracket manufacturer, on each bolt.

Install the push button on the crosswalk side of the pole.  Install push button signs above each push button.  Furnish signs with the arrow pointing in the direction of the appropriate crosswalk.  When channel is used for mounting push button signs, tap the top and bottom sign bolts into the pole.

- Underpass Lighting System Installation.  Mount the luminaires as detailed on the drawings to orient the axis of the lamp perpendicular to the axis of the underpass.

- Flashing Beacon Installation.  When the Plans specify using the flasher in a signal controller cabinet to energize beacons, furnish a two pole, fused block with built in fuse pullers and two fuses to protect the flasher.  Furnish and leave 5 feet of cable in the cabinet.  Others will install the fused block and terminate the beacon cables.

- Wood Pole Installation.  Place the poles in the ground to at least 6 feet deep.

After setting each pole in the ground, backfill the space around the pole with selected earth or sand, free of rocks 4 inches and larger, or deleterious material.  Place the material in layers approximately 4 inches thick and thoroughly compact them with mechanical tampers.

Furnish poles that provide a minimum vertical clearance of 21 feet between the pavement and low point of overhead conductor.

660-3.09 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS.  This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the Contract.  The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, interconnect, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference.  Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing equipment damaged before the transfer of maintenance responsibility.  Therefore, before starting work on the project, inventory the condition of the existing equipment with the Engineer and document the damaged and defective equipment.  If beginning work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems.  The State will pay for electricity used to operate the systems, if the public benefits from their operation.  Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer.  If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

Records.  When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times beginning and completing work, and the names of the Crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than 15.0 feet.

Alignment.  During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches according to the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 18.0 feet to 20 feet of clearance between the traveled way and the bottom of each signal.  For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain 9 feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two lanes with the lane lines separating the lanes.

5.	When the horizontal angle to the side mounted far right signal exceeds 20 degrees, relocate this signal to an overhead location.  Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

a.	With two or more through lanes, center one signal head over each lane.

b.	With one through lane and protected permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

c.	Otherwise, install the relocated signal 8 feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 7 to 9 feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in Subsection 660-3.08 Signal and Lighting Structures.

When no longer required, salvage original and Department provided equipment according to the Plans and No. 6.  Salvaging or Reusing Electrical Equipment, found in Subsection 660-3.01.  Remove other materials used in the temporary systems from the project.

660-3.10 FALSEWORK LIGHTING.  When required by the Special Provisions, install falsework lighting where vehicular traffic with or without pedestrian traffic crosses through or under structure falsework.

Provide illumination of the portal faces of falsework during the hours from dusk to dawn. Provide illumination of the pavement and pedestrian openings through or under falsework 24 hours a day.

Submit a plan for the proposed lighting installations and do not commence falsework construction until the Engineer has reviewed such plans. The Engineer will make a subsequent review after you place falsework lights in operation.

Falsework lighting equipment remains your property and must be removed from the site of the work upon completion of the project or when directed.

660-3.11 TRAFFIC SIGNAL MODIFICATIONS.  Required work is detailed in the Plan sheets and notes and the following.  Work related to the Traffic Signal Communications System will be paid for separately.

The Contractor will have 10 hours to "changeover" the new controller assembly. Changeover includes but is not limited to: removing the existing controller assembly, replacing with new controller assembly, landing new and existing wires, programming the new controller unit, and bringing the signal back to full functionality.  The 10 hour window will only occur on the days assigned under an approved traffic control plan.The Contractor will be assessed a Traffic Price Adjustment for an unauthorized lane closure according to Subsection 643-3.06. Refer to section 643 for further restrictions.

Traffic control during the changeover will be paid for under section 643 Pay Items.  At a minimum, traffic control will include the following:

- A portable changeable message board in advance of each approach with the message "Traffic Signal Work, New Traffic Pattern Ahead, from 00:00 AM/PM mm/dd/yy to 00:00 AM/PM mm/dd/yy

- A flagger for each approach

Traffic signal modifications are subject to the full Standard Specification for Highway Construction, the Special Provisions and the following:

- Traffic Controller Cabinet:  When a new traffic controller cabinet is called for, ensure legible labeling of all cabinet cables including but not limited to; control, loop, EVP, UPS, interconnect, and telephone. Label loops and signal heads individually.

- Traffic Signal Heads:  When new traffic signal heads are required, provide with new LED units and new mounting hardware. If new heads are not called for, replace any missing visors or backplates subsidiary to the Traffic Signal Modification Pay Item.

When replacing traffic signal or pedestrian indications conform to Subsections 740-2.14 and 2.15 and maintain brand consistency throughout intersection. When new heads are provided aim heads according to Table 660-2.

- Loops:  When shown in the plans, replace inductive loops including homerun cable and required splice. Loop tests are required per Section 660-3.01.7.

- Conduits:  Unless new conduits are called for reuse existing conduits.  When new conductors are being added to existing conduits, conform to sections 660-3.03, 3.05, and 3.06.

- EVP Components:  When called for in the plans provide EVP components including all cables and mounting hardware. Ensure proper operation of EVP system.

- UPS:  When called for in the plans provide fully function UPS system. If no separate UPS item exist, the UPS will be paid for subsidiary to the Traffic Signal Modifications Pay Item.

- Load Center:  When called for in the plans provide fully functioning Load Center. If no separate load center item exists, the load center will be paid for subsidiary to the Traffic Signal Modifications Pay Item.

- Conductors:  Reuse existing conductors except where the plans call for new conductors.

Salvage decommissioned reusable traffic signal equipment, components/materials and deliver to the local Maintenance & Operations station within 72 hours of removal. Refer to section 660-3.01 for delivery locations. Decommissioned components damaged as part of the salvage effort must be replaced with new components at no additional cost.

660-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

CR660.1-110316/CFHWY00317

Pay Item 660(1_) Traffic Signal System Complete.  By each fully functional signal system furnished and installed.

Pay Item 660(3) Highway Lighting System Complete.  By each fully functional highway lighting system furnished and installed.

Pay Item 660(5) Structure Illumination System Complete (Pedestrian Undercrossing).  By each fully functional pedestrian undercrossing furnished and installed.

Pay Item 660(7_) Temporary Traffic Signal System Complete.  By each temporary signal system furnished, installed, and maintained as directed by the Engineer.

CFHWY00317

Item 660(9), Bored Casing.  By the linear foot along the slope of the bored or jacked casing for the actual length bored or jacked, in place.

Item 660(11), Traffic Loop.  By each loop unit, complete and in place, including all conduit, conductors, and other equipment to the nearest junction box.

Item 660(13), Relocate Electrolier.  By each complete unit, removed, relocated, reinstalled, and functional.

Item 660(14) Temporary Electrolier.  By each electrolier and foundation furnished, installed, and maintained as directed by the Engineer.

CR660.1-110316/CFHWY00317

Pay Item 660(99) will be measured in accordance with the directive authorizing the work

CFHWY00317

660-5.01 BASIS OF PAYMENT.

Payment Includes labor, equipment, and materials required to provide fully functional traffic signals and lighting systems, permanent and temporary, using new equipment.  Remanufactured or rebuilt equipment will not be permitted.

Subsidiary to each Pay Item including but not limited to (Except when included as a separate Pay Item):

- General construction requirements,

- Bonding and grounding,

- Bored Casings,

- Completing tests,

- Conductors,

- Conduit,

- Dewatering excavations,

- Excavation, trenches in rock or soil, bedding, backfill for foundations, conduits, components,

- Foundations including concrete to complete foundations,

- J-boxes including adjustment to final grade,

- Labeling conductors,

- Maintaining temporary and existing electrical systems,

- Minor routing changes directed by the Engineer

- Preparing as-builts

- Removal and disposal of existing/new unused foundations, conduit, conductors, and J-boxes,

- Removing, repairing and replacing improvements

- Removal of signs and reinstallations required to install foundations, conduits, and J-boxes,

- Repairing damage to finishes on new equipment

- Salvaging reusable equipment and materials and delivering to the local Maintenance and Operations station including but not limited to existing signal structure. Refer to section 660-3.01 for delivery locations.

- Wiring

660 Pay Items do not include:  roadway planing, roadway paving, drainage structures, erosion, sediment and pollution control, signing, striping and pavement markings, traffic control, and components of the traffic signal communication system when included as separate pay items.

CR660.1-110316/CFHWY00317

Pay Item 660(1	) Traffic Signal System Complete (			).

1.	Signal structures

2.	Traffic controller assemblies including assembly testing and preparation, vehicle and pedestrian indications, video detection systems, radar detection, inductive loop detection, emergency vehicle preemption systems, PTZ cameras, auxiliary and test equipment, on-site manufacturer assisted start up, minimum 2 year equipment warranty, and training when called for in the Plans.

3.	Work associated with installing loop detectors and conduit crossings, and any other items except when included in a separate Pay Items such as  saw cutting, asphalt removal, aggregate base course, tack coating, and installing new hot mix asphalt.

4.	Includes salvage of existing signal system components not specified in plans to be reused, when not included as a separate item.

5.	Work associated with relocating active advance warning beacons as shown on the plans.

Pay Item 660(3	) Highway Lighting System Complete (			).

1.	Lighting structures.

2.	Includes salvage of existing lighting components not specified in plans to be reused, when not included as a separate item.

3.	Includes relocation of existing lighting components as specified in plans for reuse, when not included as a separate item.

4.	All necessary conduits, conductors, and all other necessary components required for a fully functional highway lighting system.

Pay Item 660(5) Structure Illumination System Complete (Pedestrian Undercrossing)

1.	Lighting structures for the pedestrian undercrossing.

2.	All necessary conduits, conductors, and all other necessary components required for a fully functional pedestrian undercrossing system.

Pay Item 660(7_) Temporary Traffic Signal System Complete.

1.	Work to have plans and materials approved.

2.	All necessary conduits, conductors, and all other necessary components required for a fully functional temporary traffic system.

3. All demolition and salvage work required for the removal of the existing signal system in accordance with the Plans.

CFHWY00317

Pay Item 660(11A) Data Sensor Replacement. Replace the loop detectors, piezoelectric sensors, RWIS or other data sensors inside the specified planing depth that are damaged during the planing operation (Section 202) at a rate of $	 each.

Pay Item 660(14	) Temporary Electrolier.

1.	Work to have plans and materials approved.

2.	Temporary electrolier including the structures, foundations, and load centers (as needed) and their removal.  Moving the electroliers, assembly and operational installation, removing and replacing, and installing conductors (in conduit or direct bury only).  Furnishing and installing temporary electrical load centers when existing load centers are not available for use.

3.	Temporary electrolier will be paid on a contingent sum basis at the unit price of $2400/each.  The Engineer does not require a change order/directive for this Pay Item.

CR660.1-110316/CFHWY00317

Item 660(99) will be full payment for labor, materials, and equipment to complete additional work required to provide acceptable electrical installations as listed in the plans.

CFHWY00317

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

660(1A)		Traffic Signal System Complete (S Inner Springer)		Lump Sum

660(1B)		Traffic Signal System Complete (E Inner Springer)		Lump Sum

660(1C)		Traffic Signal System Complete (Colony)		Lump Sum

660(1D)		Traffic Signal System Complete (Palmer-Wasilla Hwy/Evergreen)	Lump Sum

660(1E)		Traffic Signal System Complete (Dogwood)		Lump Sum

660(1F)		Traffic Signal System Complete (Bogard/Arctic)		Lump Sum

660(1G)		Traffic Signal System Complete (Evergreen/Cobb)		Lump Sum

660(2)	Flashing Beacon System Complete	Lump Sum

660(3)	Highway Lighting System Complete 		Lump Sum

660(4)	Sign Illumination System Complete	Lump Sum

660(5_)	Structure Illumination System Complete (Pedestrian Undercrossing)	Lump Sum

660(7A)		Temporary Signal System Complete (Palmer-Wasilla Hwy/Evergreen)	Lump Sum

660(7B)		Temporary Signal System Complete (Dogwood)		Lump Sum

660(7C)		Temporary Signal System Complete (Bogard/Arctic)		Lump Sum

660(7_)	Temporary Signal System Complete 		Lump Sum

660(8)	Underpass Lighting System Complete	Lump sum

660(9)	Bored Casing 	Inch Minimum Diameter	Linear Foot

660(11)	Traffic Loop	Each

660(12_)	Underpass Lighting System Complete (Pedestrian Undercrossing)	Lump Sum

660(13)	Relocate Electrolier	Each

660(14_)	Temporary Electrolier 		Contingent Sum

660(15_)	Signal and Lighting Salvage 		Lump Sum

660(16_)	Pedestrian Lighting 		Lump Sum

660(17_)	Traffic Signal System Modifications 		Lump Sum

660(18)	Adjust Junction Box	Each

660(19_)	Junction Box, Type 		Each

660(20_)	Signal System Timing and Adjustments 		Contingent Sum

CR660.1/CFHWY00317, EDC-110217

660(99)	Miscellaneous Electrical Work		Contingent Sum

CFHWY00317

SECTION 661
ELECTRICAL LOAD CENTERS

Special Provisions

661-1.01 DESCRIPTION.  Add the following:  Furnish and install load center assembly Type 1A with an integral uninterruptible power supply (secondary power source) to power intersection traffic and pedestrian signals (no lighting) and control equipment during interruptions to the utility power (primary power source).

Add the following load center type:

Type 1A with UPS:	Pad mounted with underground service (large)

Add the following Subsections 661-1.02 Acronyms, 661-1.03 Definitions:

661-1.02 ACRONYMS.

BBS	Battery Backup System

LC	Load Center

LCD	Liquid Crystal Display

LED	Light Emitting Diode

LC/UPS	Load Center with Integral Uninterruptible Power Supply

MBPS	Power Transfer Switch

MMU	Malfunction Management Unit

PLC	Powerline Communications

PTS	Power Transfer Switch

THD	Total Harmonic Distortion

UPS	Uninterruptible Power Supply

661-1.03 DEFINITIONS.

BUCK-BOOST.  Switch-mode voltage regulator in which voltage can be above or below the input voltage.

CR661.2-041413

661-2.01 MATERIALS.  Add the following:

Anchor Bolts	Section 740-2.02

Load Center.  Replace the 1st paragraph with the following:

NEMA 3R enclosure constructed of .125” thick aluminum, with no external screws, bolts, or nuts.

CR661.1-022015/CFHWY000317

Add the following:

1.	Load Center with Integral Uninterruptible Power Supply (LC/UPS).

Design, fabricate, deliver, and install as specified in the Specifications and Plans.

a.	Design of LC/UPS

Design and manufacture for outdoor applications and the environment specific to the project location.

The UPS shall be designed to provide for efficient fabrication and assembly using standard, readily available industry components facilitating the current project requirements.  The design shall provide for future quick replacement of the complete system or the individual components.  The design shall allow the maintenance department to quickly acquire a replacement UPS or replacement parts and personnel to easily remove the existing UPS and install the new UPS or UPS parts as may be needed (complete turnkey system with all necessary hardware).  Special tools shall not be required to install the UPS.

The design shall specifically include a shelf-mount, rack-mount, swing-tray mount, or combination thereof.  The UPS and PTS units individually shall not exceed 5.25” in height.  If swing-trays are used, a minimum of 6 bolts/fasteners shall be used to secure the tray to the cabinet rack.

b.	Submit.

Submit shop drawings, equipment technical specifications, and certifications for review and approval.  Do not begin manufacture of the LC/UPS prior to submitting and receiving approval of shop drawings and required certifications for the system assembly, the individual equipment pieces, components, and hardware.  Provide documentation confirming delivery dates of the individual pieces of equipment and overall system in-place completion date satisfying the project construction schedule.

c.	Manufacturers.

(1)	Meyers Power Products, Inc.

LC/UPS:  Power Model MEUG35-PB Metered/Unmetered with MP2000 UPS

Address:

725 E. Harrison Street

Corona, CA 92879

Ph:  (951) 520 - 1900

(2)	Or equal:

Manufacturers satisfying the requirements of the Plans, Specifications and Contractual requirements for the assembled system, including delivery, quality and timeliness of installation and responsive remote and onsite service, shall submit, as a substitution, for review and approval.

d.	UPS Run Time Capacity.

Power intersection LED traffic, pedestrian signals, and control equipment for the consecutive time periods noted below: (lighting and traffic controller auxiliary circuits are not included)

| RUN TIME CAPACITY |  |
| --- | --- |
| Operation Mode | Continuous Uninterruptible Operation Time* |
| Normal | 2 Hours |
| Flash | 2 Hours |
| Total (Normal + Flash) | 4 hours |

*Continuous uninterruptible operation time at 77 °F (25 °C) at load 875 W.

e.	Operation.

The transfer from utility power to the UPS shall not interfere with the normal operation of the traffic controller, MMU and other peripheral devices within the traffic controller assembly.

The MBPS shall be rated at 240 VAC, 40 Amps minimum.  The MBPS shall allow replacement of the UPS without interrupting power to the intersection. The MBPS and PTS shall be separate units.  Without interrupting power to the intersection, the MBPS shall permit the replacement of the PTS, and the MBPS and PTS shall each permit replacement of the UPS.

The UPS shall use a temperature compensated battery charging system. The charging system shall compensate over a range of 2.5 to 4 mV / °C / Cell and be rated 10 Amps at 48 VDC. Batteries shall not be charged when battery temperature exceeds 122 °F ± 5.4 °F (50 °C ± 3 °C). The temperature sensor shall be external to the UPS unit and supplied with 9' - 10" of wire.

The UPS shall automatically and continually monitor and display the current percent of battery power available for use.  A "Battery Not Connected" alarm shall be issued if battery power is not present. When utilizing battery power, the UPS output voltage shall be between 110 VAC and 125 VAC, pure sine wave output with THD < 3% at 60 Hz +/- 3 Hz.

The UPS shall provide the power beyond the temperature that would be field programmable for an external fan located in the same or in a separate battery cabinet. The temperature setting shall be adjustable locally and remotely.  The temperature range shall be from +68 °F to +131 °F (+20 °C to +55 °C) in 1 degree F increment.

In the event of UPS failure, battery failure, or complete battery discharge, the PTS shall revert to the utility or line mode (in a de-energized state) where utility power is supplying the cabinet.

f.	Components:

The LC/UPS shall include all equipment, hardware, foundation and foundation materials, interconnecting wiring and other materials for a complete operable LC/UPS inclusive of materials and performance requirements specified herein, but not limited to:

(1)	UPS

(2)	UPS Controller Unit

(a)	Re-settable Inverter Event Counter

(b)	Cumulative Inverter Timer

(c)	Event log, Time and Dated (stores the last 100 events, minimum)

(d)	Self-Test (programmable in 1-minute increments from 1 min. to 255 min.)

(e)	Low Battery Alarm (programmable, adjustable in increments of .25 VDC)

(f)	Buck-Boost Mode (UPS shall be capable of Buck-Boost 10% ±)

(3)	PTS (activated during Buck-Boost operations; transfer times 10 milliseconds)

(4)	MBPS (non-electrical)

(5)	Batteries and Battery Enclosure

(6)	Battery Heater Mats

(7)	Cabinets and Enclosures

(8)	External Fan

g.	UPS Access and Password Protection.

	Provide local and remote access.

	Provide the UPS with a default password.

Access:

(1)	Local – provide an LCD display screen and touch pad as part of the UPS

(2)	Remote

(a)	RS232 interface

(b)	USB interface

Local and remote access shall provide same access use.

User:

(1)	The “User” includes the Department Traffic Engineers and Maintenance Personnel.

(2)	The User shall be able to monitor the following at the LC/UPS cabinet (locally) and remotely.

Use:

(1)	Provide the Department with the default password and administrative authority to add/change password protection.  Make the procedure intuitive and direct.

(2)	Control, programming, maintenance, and inquiry (view and adjust) including but not limited to:

Monitor:

(a)	Time,

(b)	Date,

(c)	Current battery charge status,

(d)	Input/output voltages,

(e)	Power output,

(f)	Battery temperature,

(g)	Field programmable relay settings

Current status shall be indicated by LED lights:

(a)	Green – Flashing for battery back-up mode

(b)	Green – Steady ON for normal line mode operation

(c)	Red – Flashing for ALARM conditions

(d)	Red – Steady ON for FAULT conditions

Maintenance Controls - password protect:

(a)	UPS Inverter ON/OF,

(b)	Battery Test,

(c)	Event Log (Retrieving, viewing and printing in plain English),

(d)	Changing Default Settings

Other Settings:

(a)	Temperature Settings,

(b)	Re-Settable Inverter Event Counter,

(c)	Cumulative Inverter Timer,

(d)	Self-Test,

(e)	Low Battery Alarm

(3)	Upload firmware software updates of the non-volatile, read-only memory type.

h.	Specifications.

(1)	Environmental:

The operating temperature for the (UPS), (PTS) and (MBPS) shall be -34.6 °F to 165.2 °F

(-37 °C to +74 °C).

(2)	UPS Input/Output:

| UPS SPECIFICATIONS |  |
| --- | --- |
| Input Specifications |  |
| Nominal Input Voltage | 120 VAC, Single Phase |
| Input Voltage Range | 120 VAC ± 25% |
| Input Frequency | 60 Hz ± 5% |
| Output Specifications |  |
| Nominal Output Voltage | 120 VAC, Single Phase |
| Power Rating* | 2000 VA (1500 Watts) |
| Output Frequency | 60 Hz ± 5% |
| Voltage Wave Form | Sine Wave, THD < 3% |
| Efficiency (nominal) | 95 – 97% |

*The UPS power rating of 2000 VA / 1500 Watts shall be with a minimum inverter efficiency of 80%.

(3)	Loss/Restoration of Utility Power:

When the utility line voltage is outside the High and Low Limits (100 & 130 VAC respectively set as defaults), the UPS shall transfer the load to battery power. The UPS shall return to line mode when the utility power has been restored to above 105 VAC or below 125 VAC; or the UPS shall return to line mode when the utility power is back to nominal for more than 30 seconds (the line qualification time).  The line qualification time shall be adjustable to 3, 10 or 30 seconds.

The maximum transfer time allowed, from disruption of normal utility line voltage to stabilized UPS line voltage from batteries, shall be 65 milliseconds. The same maximum allowable transfer time shall also apply when switching from UPS line voltage to utility line voltage.

(4)	Battery(s):

(a)	Batteries as part of the UPS provide the power.

Individual batteries shall be rated at 105 Amp-Hour minimum. Batteries shall be 12 VDC type and shall be easily replaced and commercially available off the shelf. The battery system used in the UPS shall consist of 4 batteries and shall be of a voltage not to exceed 60 VDC. Batteries shall be provided with quick disconnect terminals and a polarized - keyed battery cable for easy field installation.

Batteries shall be deep cycle, sealed prismatic lead-calcium based AGMNRLA (Absorbed Glass Mat/Valve Regulated Lead Acid) batteries - able to withstand extreme temperature. Batteries shall be certified to operate over a temperature range -4 °F to 165.2 °F (-20 °C to +74 °C).  The batteries shall be provided with appropriate interconnect wiring and a corrosion-resistant stationary or swing-out mounting tray and/or brackets appropriate for the cabinet into which they will be installed as specified in “Design of LC/UPS”.

Batteries shall indicate maximum recharge data and recharging cycles. Recharge time for the battery from protective low cutoff to 80% or more of full battery charge capacity, shall not exceed twenty (20) hours.

(b)	Battery Compartment:

The battery cabinet shall be vented through the use of louvered vents, filter, and one thermostatically controlled fan operated from the UPS. The fan will automatically turn ON at the temperature programmed into the UPS.

External battery compartments may be used to satisfy environmental and physical requirements.  When submitting shop drawings, material and equipment submittals, request in writing and demonstrate graphically the need for an external compartment(s).

(c)	Back-Feed and Other Protections:

The UPS shall be equipped to prevent a malfunction feedback to the cabinet or from feeding back to the utility service per UL 1778, Section 48 "Back-Feed Protection Test". The upstream back-feed voltage from the UPS shall be less than 1 VAC for the protection of persons accessing the equipment.

The UPS shall have lightning surge protection compliant with IEEE/ANSI C.62.41 for 2000 VAC.

(5)	Relay Contacts:

The UPS shall provide the user with 6 sets of fully programmable, relay contacts of type NO/NC, panel-mounted, potential free and rated 1 Amp, 120 VAC and labeled C1 through C6. Each relay's setting shall be programmable to activate under conditions through local access or remote access.  The minimum number of relay settings is outlined below.

Independently configure relay contacts C1 through C6 to activate under the following conditions:

(a)	ON BATTERY - relay activates when BBS switches to battery power.

(b)	LOW BATTERY - relay activates when batteries have reached a specified level of remaining useful capacity while on battery power. The specified level shall be adjustable from 0 to 100%.

(c)	TIMER- relay activates after being on battery power for a specified amount of time. The specified time shall be adjustable from 0 to 8 hours.

(d)	ALARM - relay activates after a specific or general alarm is detected. These alarm conditions include:

	Line frequency

	Low output voltage

	No temperature probe

	Overload

	Batteries not connected

	High temperature

	Low temperature

The relay shall be programmed to activate when any of these alarm conditions occur, or when a specified condition occurs.

(e)	FAULT- relay activates after a specific or general fault is detected. These fault conditions include:

	Short circuit

	Low battery voltage

	High battery voltage

	High internal temperature

	Overload

The relay shall be programmed to activate when any of these fault conditions occur, or when a specific condition occurs.

(f)	OFF- relay is disabled and shall not activate under any condition.

(6)	Default Relay Settings:

(a)	Relay C1 and C2 shall be set to activate whenever the UPS transfers to battery power and shall be labeled "ON BATT."

(b).	Relays C3 and C4 shall be set to activate whenever the batteries reach 40% of remaining useful capacity and shall be labeled "LOW BATT."

(c)	Relays C5 and C6 shall be set to activate whenever the UPS has been on battery power for 2 hours and shall be labeled "TIMER."

Terminal block position 19 & 20 shall be set to activate a self-test. This test confirms that a unit can transfer into and out of battery mode while supporting the output load.

(7)	Load Center for Temporary Power:

Use the following load centers for distribution of power for temporary lighting and signals including the control systems.  Provide work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

(a)	Permanent load centers installed in their plan location.

(b)	Existing load centers scheduled to remain intact until completion of the project.  Relocate and reuse existing load centers only if approved.

(c)	Approved temporary load centers with photoelectrical controlled lighting circuits.  Provide a temporary load center when retiring an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked “Suitable for use as service equipment.”

CR661.2-041413

Equipment List(s) and Drawings.

Delete No. 1. and replace with the following:

1.	Materials on the Qualified Products List:  The Qualified Products List does not apply to the 661 Pay Items.  Provide catalog cuts of materials to the Engineer for review and approval.

3.	Materials Not Requiring Certification:  Replace the 2nd sentence with the following:

Submit these materials for review and approval if included on the Materials Certification List (MCL) or requested by the Engineer.

Add the following materials:

Ground Rods.  Furnish one piece 3/4” diameter by 10 feet long copper clad steel rods.

Ground Rod Clamps.  Furnish one piece bronze clamps with a hex head setscrew that are suitable for direct burial and for use with copper clad ground rods.

Meters.  Furnish meter sockets and landing pads rated for 200 Ampere Service.

Photoelectric Controls.  Delete the first sentence and substitute the following:

Use three wire photoelectric controls that directly switch a circuit from one conductor to another.  Furnish two piece photoelectric controls that consist of a plug-in control unit and a locking type receptacle set in a cast aluminum adapter.

1.	Plug-in Control Unit.

Furnish photoelectric control units that consist of a light sensitive element connected directly to a normally closed, single-pole, single-throw, and control relay free of intermediate amplifications.  For highway lighting, use horizontal or zenith type sensing units that:

a.	Operate at voltages between 120 and 277 VAC, 60 Hz,

b.	Handle loads up to 1,800 volt-amperes,

c.	Operate at temperatures from -40 °F to +150 °F,

d.	Consumes less than 10 watts of power,

e.	Feature a 3-prong, EEI-NEMA standard, twist-lock plug,

f.	Turn-on between 1.0 and 5.0 foot-candles and turn-off at light levels between 1.5 and 5.0 times those at turn-on.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices used in the Control of Roadway Lighting.

Screen the photoelectric control units to prevent artificial light from interfering with normal photoelectric control operation.  Extend screens to the top of the control units.  Use 3 inch wide x 0.063 inch thick (min) aluminum meeting ASTM B209, Alloy 3003-H14.

2.	Locking Receptacles.

Furnish twist lock type, phenolic resin receptacles set in one of the following cast-aluminum adapters.

a.	For photoelectric controls installed on signal poles and load centers, furnish a mounting adapter with a threaded connection that fits conduit outlet bodies threaded for 1/2 inch rigid metal conduit, General Electric model MB-PECTL or approved equal.

b.	For photoelectric controls installed atop lighting poles (with mast arms,) furnish a pole top adapter:  equipped with a terminal block, made to slip over the ends of poles 3 1/2 to 4 1/2 inches in outside diameter, and secured by set-screws, General Electric model PTA-PECTL or approved equal.

661-3.01 CONSTRUCTION REQUIREMENTS.  Replace the 11th paragraph with the following:

Install two ground rods at least 6 feet apart at each load center.  Connect the neutral bus to the ground rods with a soft drawn bare copper conductor sized per the NEC, 6 AWG minimum.  Bond non-current carrying metal parts in each load center to the ground bus.  At Type 1 load centers, install one ground rod inside the base, readily accessible though the removable cover, and the second ground rod outside the base.  Route the grounding electrode conductor to the second ground rod through one of the knockouts.

Replace the 12th paragraph with the following:

Install photoelectric controls at the locations indicated. Orient photoelectric control units to face the north sky.  Install a screen to prevent artificial light from interfering with normal photoelectric control operation.

For photoelectric controls installed on load centers, install a Myers hub in a cabinet wall shielded from traffic.  To the hub, attach an assembly that consists of a Type LB conduit body, a length of conduit, and a Type C conduit body.  Fabricate the conduit at least 3 ft long and locate the photoelectric control 1 ft above the top of the load center.  Mount the photoelectric control adapter on the Type C conduit body.  Install a conduit hanger to brace the top of the conduit.

For photoelectric controls installed on signal poles, install a Myers hub in the center of the rain cap.  Attach a Type C conduit body to the hub with a close nipple.  Mount the photoelectric control adapter on the conduit body.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

For photoelectric controls installed on electroliers, install a pole top adapter.  When the photoelectric control is on a lighting standard with a slip base or frangible coupling style base, use an approved breakaway disconnect in the base of the light standard.  Restrain the cable in a similar manner as the illumination cable in the pole base.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

CR661.1-022015/CFHWY00317

Add the following:

The Engineer shall coordinate new load centers with existing and or new service utilities.

CR661.1/CFHWY00317

661-3.02 CONTRACTOR’S WARRANTY.

Load Center Type 1A with UPS (LC/UPS)

The period of performance for this warranty shall be two (2) years from the time the Department assumes maintenance responsibilities.  The price for this warranty will be included in the bid price for the LC/UPS assembly.

The LC/UPS system, all equipment, components, hardware, accessories, factory and field workmanship shall be warranted against failure from normal usage during the first two years of service from the time the Department assumes maintenance responsibilities.  Manufacturer warranties, guarantees, and instruction sheets and all parts used in the work shall be delivered to the Engineer before the Department assumes maintenance responsibilities.  Where repairs cannot be made via telephone support or modem the Contractor shall respond at the site to service or repair the malfunctioning equipment within two (2) weeks of the initial notification of the malfunction.  All materials and equipment shall be repaired or replaced at the Manufacturer’s expense including labor to complete the repair and an onsite representative to inspect and certify the repaired LC/UPS meets the requirements of the original specifications using original equipment manufacturer (OEM) parts, and equipment.  All expenses associated with the repair shall be included in the Manufacturer’s Warranty.

The warranty period will stop at the time of the failure.  The Manufacturer shall warrant the repairs as part of the original warranty.  At the completion of the repairs, the Manufacturer shall supply the Department Traffic Engineer with additional equipment and part warranties, guarantees, and instruction sheets as applicable to the repairs as required for the original equipment and work.  The Manufacturer will supply a letter certifying the repairs satisfy the specifications for the original work.  The remaining time of the warranty, the original warranty period less the time passed from the date established as the warranty start date, will begin after the repair is complete and the Department Traffic Engineer receives the repair certification letter.

CR661.2-041413

661-5.01 BASIS OF PAYMENT.  Add the following:

The following work is subsidiary to 661 Pay Items:

	All necessary hardware for mounting (shelf angles, rack, shelving, harness, etc.).

	Removing existing load centers being replaced with new load centers, their foundations, and ground rods.

	Payment of fees required by the local authority for electrical inspection(s) and the costs of correcting the deficiencies noted during the inspection(s).

CR661.1-022015/CFHWY00317

	All work including, but not limited to, contacting and coordinating with the Engineer for service with utilities and maintenance until the Engineer provides the notice of final acceptance.

CR661.1/CFHWY000317

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

661(2A)	Load Center, Type 1A with UPS (LC/UPS)	Each

CR661.2-041413

Special Provisions

Add the following Section:

SECTION 662
FIBER OPTIC SIGNAL INTERCONNECT SYSTEM

662-1.01 DESCRIPTION.  Furnish and install fiber-optic signal interconnect system as shown on the Plans along the route indicated or on a route as directed by the Engineer.

662-1.02 INSTRUCTIONS AND GUARANTEES.  One set of maintenance and repair manuals shall be included with each project installation and submitted to the Engineer.

No changes or substitutions in these requirements will be acceptable unless authorized in writing.

The supplied conduit shall carry a two-year warranty from the date of project acceptance to be free of defects. The installer shall be fully responsible for the installation of defect free conduit and for the replacement of any conduit found to be defective.

662-2.01 MATERIALS.  Submit materials for review and approval per the requirements of subsection 106-1.05, Certificates of Compliance and subsection 660-2.01, Materials.

662-2.02 POLYETHYLENE DUCT SYSTEM.  Install a high density polyethylene (HDPE) duct system in which to pull the interconnect cable. Unless noted on the plans install conduit per the requirements of 660-3.03, Conduit.

Unless specified on the plans, furnish 1-1/4-inch HDPE conforming to the requirements of subsection 740-2.06 Electrical Conduit and Fittings.

Furnish fittings used in the duct system such as elbows, etc., made from the same type polyethylene as the duct.  Fuse connections using the manufacturer’s recommended procedure and equipment.

Mark underground conduits with a continuous strip of polyethylene marker tape. Marking tape shall feature the words “Buried Fiber-optic Cable” (or similar). Two strips shall be laid horizontally side by side above the conduit(s) 12 inches below final grade.  The marking tape shall be at least 6 inches wide, at least 4 mils thick and orange in color.

Keep junction boxes and ends of the conduit covered unless pulling conductors.

Use care during compaction operations to prevent damage to the junction boxes and conduits.  Remove and replace items damaged as per subsection 105-1.11.

After testing and installing the conductors, plug conduit openings with duct seal to prevent water from entering the duct system.

662-2.03 FIBER-OPTIC CABLE.  Cable shall be suitable for placement in an underground duct and shall conform to:

	United States Department of Agriculture Rural Utilities Service (RUS) standard 7 CFR 1755.900.

	Department of Agriculture Rural Electrification Administration (REA) Bulletin 1753f-601 (PE-90) dated August 4, 1994, and these specifications.

	National Electrical Code (NEC) Article 770; NFPA-National Fire Protection Agency.

	Telecommunications Industry Association/Electronic Industries Association (TIA/EIA) FOTP-Fiber-optic Test Procedures.

1.	Fibers.

a.	Fiber-optic cables shall be loose tube, all-dielectric, non-metallic slotted core with an integral dry water blocking tape and sheath designed for indoor/outdoor installation. Each cable shall be equipped with 6 kink resistant buffer tubes containing 12 optical fibers each.

b.	Each buffer tube shall have an inside diameter much larger than total diameter of the fiber it supports.

c.	Fillers are allowed in the cable to achieve cable cross-section symmetry.

d.	All cable fibers shall be usable and shall be sufficiently free of surface imperfections and inclusions to meet or exceed the optical, mechanical, and environmental requirements contained in this specification.

e.	Each optical fiber shall consist of a doped silica core surrounded by a concentric silica cladding.

f.	Fibers shall contain no factory splices.

- Fiber coating shall be a dual-layered, UV cured acrylate applied by the fiber manufacturer.  The coating shall be mechanically or chemically strippable without damaging the fiber.

- Repairs to the fiber coatings are not allowed except as determined by the State Traffic Signal personnel at designated splice locations.

- Two (polyester or aramid) yarn binders shall be applied contra-helically with sufficient tension to secure each buffer tube layer to the central strength member without crushing the buffer tubes.  The binders shall be non-hygroscopic, non-wicking, and dielectric with low shrinkage.

- Tensile strength shall be provided in the cable by a combination of high tensile strength yarns helically stranded around the cable core.  High tensile strength yarns shall be wrapped helically around the buffer tubes before the application of the outer jacket (sheath).

- Individual buffer tubes and optical fibers shall be distinguishable by means of distinct and recognizable color-coding in accordance with TIA/EIA-598-B, “Optical Fiber Cable Color Coding.”  The colors shall be stable during temperature cycling and not subject to fading or smearing onto each other or into the gel filling material.  Ensure colors do not cause fibers to stick together.

l.	Distinguish each fiber and buffer from others by means of color-coding according to the following:

| 1. Blue | 5. Slate | 9. Yellow |
| --- | --- | --- |
| 2. Orange | 6. White | 10. Violet |
| 3. Green | 7. Red | 11. Rose |
| 4. Brown | 8. Black | 12. Aqua |

- For cables containing more than 12 buffer tubes, use the color code shown above for tubes 1 through 12, and use stripes or tracers in conjunction with the standard color code for tubes 13 through 24.

2.	Jacket.

a.	The outer jacketing (sheath) material shall be applied directly over the high tensile strength yarns.  The minimum nominal jacket thickness shall be 55 mils.

- The outer jacket material shall be a medium density polyethylene (MDPE) conforming to ASTM D1248, Type II, Class C, Category 4 or 5, Grade J4.  The light absorption coefficient, when measured in accordance with ASTM D3349, shall be a minimum of 400 at a wavelength of 375 nanometers.

- The polyethylene jacket (sheath) shall contain carbon black to provide ultra-violet light protection.  The jacket material shall be fungus inert as described in ASTM G21.

- The jacket shall be free of any holes, splits, or blisters.

3.	Cable Features.

a.	The cable shall contain at least one ripcord under the sheath for easy sheath removal.

- The shipping, storage and operating temperature range of the cable shall be –400 F to +1600 F.

- The fiber-optic cable shall be capable of withstanding a maximum pulling tension of 600 lbs during installation (short-term loading) and 200 lbs (long term loading) with no damage. Tensions on the cables shall not be exceeded under any circumstances.

4.	Manufacturer.

- All Fiber-optic Cable shall be supplied by an ISO9001 certified manufacturer who is regularly engaged in the production of these specifications for fiber-optic cable.

- Fiber-optic cables shall be manufactured, tested, and prepared for shipping by one manufacturer. That manufacturer shall provide all fiber-optic cables and connectors called for on the project.

5.	Cable Markings.

- Markings shall be approximately 1/8-inch (3 mm) nominal height.

- Be clearly legible and distinguishable.

- Made at 2-foot intervals to be used as length markers.

- If initial markings fail to meet marking criteria (i.e., non-legible, incorrect spacing, spelling error, etc.), cables may be remarked to meet criteria.  Cable markings shall include:

- Cable ID

- Sequential numbers in whole foot or meter intervals to determine the length of the cable and amount remaining on the reel.

- Number of fibers

- “SM” (for Single Mode Fiber)

- “ADOT Fiber”

662-2.04 FIBER-OPTIC DROP CABLE.  Drop Cable is defined as the assembly or pigtail consisting of fiber-optic cable, connectors, protective tubing, fan-outs (if required) and all incidental materials. This is used for connectivity between a fiber trunk cable and field devices (i.e., signal controller, modems etc.).  Drop cables shall be factory assembled.  Drop cables shall be packaged individually within a plastic bag marked clearly with the manufacturer’s part number.

Cable design and installation shall meet requirements for outdoor use as described in subsection 662-2.03, Fiber-optic Cable.  Optical jackets (3mm), where used, shall be yellow for single mode fibers.  No splices are allowed within the cable length.  Non-connectorized ends shall be suitable for heat fusion splicing as described in subsection 662-3.09, Splices.

Factory testing information of each Fiber-optic Drop cable (fully assembled) shall be provided for each connector/fiber. The information shall be provided in test tags attached to individual or paired connector/fiber.

Field testing information of each Fiber-optic Drop cable (fully assembled) shall in accordance with subsection 662-3.04, Field Testing and Performance of Fibers.  Documentation of testing shall be in accordance with subsection 662-3.05, Documentation of Testing.

Fiber-optic drop cables shall be equipped with:

1.	Twelve (12) optical fibers or as specified on the plans.

2.	Fiber-optic connectors shall be:

a.	Compatible with the equipment being used for fiber strands with preset usage.

b.	In accordance with subsection 662-3.07, Connectorization.

c.	Factory installed unless otherwise allowed by Engineer.

3.	Drop Cable Fan-out Kits:

a.	heavy-duty Spider design.

b.	Install fan-out kits for all connectorized ends to build up to a 3 mm jacket.

4.	Tubing that is 900 µm or 3 mm fan-out as required by the application.

5.	Buffer tubes shall protected by the cable sheath or fan out kit.  Exposed buffer tubes are not acceptable.

6.	Individual fiber strands shall be protected by aramid fiber tubes.

662-2.05 SINGLE-MODE OPTICAL FIBERS.  Single mode (SM) fibers utilized in the cable shall be fabricated from 100 kpsi proof stress glass and primarily composed of silica which shall provide a matched clad index of refraction (n) profile and the following physical and performance characteristics:

1.	Core Diameter: 8.3µm

2.	Maximum Attenuation: 0.4/0.25 dB/Km at 1310/1550 nm, respectively

3.	Maximum Dispersion:  < 3.2 ps/nm-km from 1285 nm to 1330 nm; < 17 ps/nm-km at 1550 nm

4.	Dispersion Wavelength (ZWD): 1301.5 to 1321.5 nm

5.	Zero Dispersion Slope:  0.092 ps/nm2-km

6.	Cladding Diameter: 125 +/- 1.0 µm

7.	Core-to-Cladding Offset (concentricity): < 0.8 µm

8.	Cladding Non-Circularity:  < 1.0 percent

9.	Fiber Coating Diameter:  245 +/- 10  µm

10.	Secondary Coating:  900 µm (as specified for breakout cable/kits, distribution cable, pigtails and patch chords only)

11.	Fiber Colored Diameter:  250 +/- 10 µm nominal

12.	Mode-Field Diameter:  9.3 +/- 0.5 µm at 1310 nm; 10.5 +/- 1 µm at 1550 nm

13.	Attenuation Uniformity:  No point discontinuity greater than 0.10 dB at either 1310nm or 1550nm

14.	Cutoff Wavelength:  <1260 nm

15.	Maximum End-to-End Attenuation per cable length 15 db.

16.	Maximum cable outside diameter: 0.5-inch

17.	Fiber Polarization Mode Dispersion (PMD): 0.5 ps/km1/2

18.	Proof Test:  All Optical fibers shall be proof tested by fiber manufacturer

19.	Attenuation at Water Peak:  The attenuation at 1383 ± 3 nm shall not exceed 2.1 dB/km.

20.	Numerical Aperture:  0.13

662-2.06 FIBER-OPTIC MANHOLES AND VAULTS.

1.	General.

- Shall be spaced at intervals no greater than 2,640 feet (1,320 feet typical).  In extreme cases where conduit has no bend as permitted by the Engineer, 5,280 feet is allowable (conduit shall be lubricated with no bends).

- Shall be installed at locations where the cumulative, conduit bends, measured from the last manhole/vault, exceed 360 degrees.

- Are not required for change in conduit installation method.

- Shall not be greater than 5 feet in depth as measured from the lid to the base.

- Covers shall meet the Heavy Duty requirements of AASHTO M306, Drainage, Sewer, Utility, and Related Castings.

- Finished grade shall be in accordance with pertinent sections of section 660-3.04, Junction Boxes. Manholes and vaults shall be located in the field to avoid drainage swales.

- When communication conduit is located in the same trench as conduit intended for other purposes (i.e., electrical circuits), manholes shall be offset a minimum of 2 feet from the conduit trench.

- A fiber-optic cable support assembly shall consist of multiple brackets, racks, and/or rails required to suspend the required surplus cabling and any splice enclosures for a single vault.  The support assemblies shall be recommended and approved by the manufacturer of the fiber-optic cable and splice enclosure. The support assembly shall be made from or coated weather resistant material such that there is no corrosion of the supports. The support assemblies shall be anchored to the existing wall using stainless steel hardware.  The fiber-optic cable support assemblies shall be incidental to the manholes/vaults.

- Void areas between openings and conduit shall be filled with a self-curing caulk that will provide a permanent, flexible rubber seal. The caulk shall be unaffected by sunlight, water, oils, mild acids, alkali, mildew and is non-flammable. The material shall provide a permanent bond between the conduit entering the manhole/vault and the polymer concrete. The caulking shall be gray in color.

- All openings in manhole/vaults shall be machined at the time of fabrication, as shown on the plans, or punch-driven at the time of placement. Openings shall be sized to facilitate conduit called for in the plan.

- Manhole/vault walls that receive only one or no conduits shall be provided with at least one 5-3/4 inch diameter knockouts for future multi-duct installation. The knockouts shall be aligned across from each other.

2.	Manholes.

- All openings in Type 1 manholes shall be cored or blocked out at the time of fabrication, or cored at the time of placement.  Where conduit is terminated in a manhole, the coring shall be no larger than 1/2 inch from each side of conduit.

- Shall be constructed on top of 12 inches of porous backfill material (subsection 703-2.10).

- Shall have a 1-inch-diameter drain hole in the base.

- Proposed manholes shall be fabricated with fiber-optic cable support assemblies, as specified herein, and as shown on the plans.  The cost to provide the fiber-optic support assemblies shall be incidental to manholes.

- Type M covers are required for manholes when installed within terrace, median or off-roadway areas.  Type K covers are required for manholes when installed in the roadway.

3.	Vaults.

- Shall be 30 x 48 inches and shall have an effective height of 57 inches (one 24-inch tall stackable vault and one 36-inch stackable vault with a 3-inch overlap).

- Shall be constructed on top of 12 inches of porous backfill material (subsection 703-2.10).

- The vault lid shall have a minimum design load of 15,000 pounds and shall have a permanently recessed logo that reads "TRAFFIC.” The vault lid shall have two (2) 1/2-inch x 4-inch pull slots. The lid surface shall have a coefficient of friction of 0.50 in accordance with ASTM C1028.

- The vault and vault lid shall be constructed of the polymer concrete material, "cosmopolite" and be gray in color. The vault lid shall have steel rebar or mesh added to it so the vault can be easily found with a metal detector under heavy snow. The steel rebar and mesh shall be completely enclosed within the lid such that grounding is not required. The added steel shall have 1 in of cover and not add excess weight to the lid.

- Manufacturer approved gasketing to resist water from entering the vault shall be installed between the lid and the top 24-inch-deep stackable vault.

- The vault lid shall be secured to the vault with two 3/8-inch 16 UNC stainless steel pentahead bolts in which to lock the lid and shall include the appropriate stainless steel washers.

662-3.01 CONSTRUCTION REQUIREMENTS.

1.	Fiber-optic Cable.  All splicing, testing and terminating of optical fibers shall be performed by a technician in accordance with subsection 662-3.02, Certified Fiber-optic Technician.

Physical condition of the cable upon receipt shall be recorded as outlined in subsection 662-3.05, Documentation of Testing.  Cable reel shall be inspected for nails, staples and other materials that might otherwise kink or damage the cable when unreeling.  All fibers should be tested upon receiving cable. The Contractor shall assume full responsibility of cable that is damaged if testing is not performed after receiving cable.

A detailed construction plan and installation procedure shall be submitted and approved by the Engineer before cable installation.  Cable shall only be spliced at designated splice points as specified on the plan.

Before installation, all cables shall be inspected to be free of damage (nail or staple holes, jacket tears, kinks, etc.), material defects, manufacturing defects, and dimensional non-uniformity that would:

- Interfere with the cable installation using accepted cable installation practices.

- Degrade the transmission performance and environmental resistance after installation.

- Inhibit proper connection to interfacing elements.

- Otherwise yield an inferior product.

Take all necessary precautions to protect reeled cable from possible damage while unattended. Exposed cable shall be protected at all times from vehicular and public traffic.  If cable ends are exposed and unattended, cable caps shall be taped onto cable ends to prevent ingress of moisture into the cable.

When cable is installed by pulling, a swivel and woven cable grip designed for fiber-optic cable shall be used.  Materials for lubricating shall be utilized when pulling. Cable shall be pulled in one continuous run.  Splicing is not allowed until the entire length of cable is installed.  Cable shall be pulled in multiple runs when 2 or more 90o bends occur in the run. One continuous cable pull shall not contain more than one 90o bend.

Cable installation in conduit (duct) systems shall conform to Corning Cable Systems procedure SRP-005-011, “Fiber-optic Cable Placing-Duct,” or manufacturer approved methods of jetting or pulling. Cable shall not be kinked or forced abruptly against conduit edge when pulling cable from conduit ends. Cable feed systems (reels, rollers, guide, tubes etc.) shall be used to install or retrieve cable from conduit ends in vaults, manholes, or junction boxes.

Equipment shall be provided to monitor tensile forces on long cable runs. Monitoring equipment shall measure pulling tension as it occurs and record the maximum tension incurred during the pull.

Unless cable is assisted by jetting or winching, lengthy cables requiring multiple pulls shall be coiled in a “figure-eight” pattern. Coiled cable will be staged at intermediated access points to avoid twisting of cable. The figure-eight patterns shall be approximately 15 feet in length. Cardboard shims shall be installed between cable layers at the crossover of the “figure eight” to relieve pressure on the cable.  Fiber-optic cable lengths greater than 100 ft shall not be coiled in one continuous direction.

Minimum bend radii (20 x diameter of the cable with loading, 10 x cable diameters without loading) on the cable shall not be exceeding at any time.

Temporary aerial installation methods shall be consistent with Corning Cable Systems SRP-005-010, “Fiber-optic Cable Placing-Lashed Aerial” or manufacturers approved method.

Excess fiber cable slack shall be stored in vaults and manholes on hooks in accordance with the plans.  Cable slack shall be neatly coiled around the inside perimeter of manholes and vaults and shall be supported by cable brackets.  Cable slack shall be supported as to not interfere with access into manholes and vaults.  Excess fiber cable slack shall be provided as follows:

- Approximately 100 feet per manhole and vaults containing splices.

- 65 feet per splice vault.

- 20 feet per junction box or vault not containing splices.

- 6 feet per controller cabinet.

All fiber-optic cable shall be installed with marking tape, copper wire tracer and above ground markers.

2.	Vaults.  Vaults shall not be placed near drainage collection areas or where vehicle traffic is anticipated.  To the extent possible, vaults shall be placed so that they are accessible by service vehicles driving close to them.

Brackets for splice enclosures shall be mounted as per vault manufacturer recommendations.  Mounting equipment for cable or splice closures shall not fully penetrate the vaults in order to prevent water intrusion.

Where applicable, conduits shall be terminated in vaults to allow for proper grounding and bonding of metallic conduit. Multi-duct conduit termination kits shall terminate at vaults inside wall (or slightly into the vaults interior) to the extent possible.

Conduit, conduit terminations, and caulking shall be allowed to fully cure as per the manufacture’s specification before backfilling vault.  Openings required to install special or directional conduit shall be sealed with manufacturer approved termination kit.

662-3.02 CERTIFIED FIBER-OPTIC TECHNICIAN.  The Fiber-Optic Technician shall have attended and successfully completed at least one four-day "Installation of Fiber-optic Products School." This school shall be conducted by a major manufacturer of fiber-optic products and encompasses all aspects of fiber-optic technician certification.

Employ only technicians demonstrating a minimum of two years work experience with the splicing, termination, and testing of fiber-optic cable.

The approved technician shall provide evidence of completed courses within one week before the beginning of construction. The Engineer reserves the right to revoke the approval of any technician not demonstrating the skill and knowledge to perform at accepted industry standards or to the quality required in these specifications.

662-3.03 TESTING AND PERFORMANCE BY MANUFACTURER.  All outdoor cable installations shall meet or exceed requirements of the Fiber-optic Test Procedure (FOTP) criteria referenced in RUS 7 CFR 1755.9 and Bulletin 1753f-601 (PE-90) and these specifications.

Following specifications shall apply to the appropriate Fiber-optic Test Procedures (FOTP):

1.	TIA-455-3-A, FOTP-3 “Procedure to Measure Temperature Cycling Effects on Optical Fibers, Optical Cable, and Other Passive Fiber Optic Components”:  The average change in attenuation at extreme operational temperatures (-400 F to +1600 F) shall not exceed 0.05 dB/km at 1,550 nm for single-mode fiber.  The magnitude of the maximum attenuation change of each individual fiber shall not be greater than 0.15 dB/km at 1,550 nm.

2.	TIA-45-82-B, FOTP-82, “Fluid Penetration Test for Fluid-Blocked Fiber-optic Cable.”  When a one-meter static head or equivalent continuous pressure is applied at one end of one-meter length of un-aged cable for 24 hours, no water shall leak through the open cable end.  When a one-meter static head or equivalent continuous pressure is applied at one end of one-meter length of aged cable of one hour, no water shall leak through the open cable end.  The aging cycle is defined as exposing the cable to 850C for 168 hours and two cycles of –400C to +700C with cable held at these temperatures for 24 hours.  At the end of this cycle, the cable will be decreased to +230C and held for 24 hours. The water penetration test is completed at the end of the 24 hours hold period.

3.	TIA/EIA-455-81-B, FOTP-81, “Compound Flow (Drip) Test for Filled Fiber-optic Cable”:  The cable shall exhibit no flow (drip or leak) of filling and/or flooding material at +650C.

4.	TIA/EIA-455-41-A, FOTP-41, “Compressive Loading Resistance of Fiber-optic Cables”:  Ten percent of the fibers shall not experience a magnitude of attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The magnitude of the attenuation change shall be within the repeatability of the measurement system for the remaining 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  No fibers shall exhibit a measurable change in attenuation after test load is removed.

5.	TIA/EIA-455-104-A, FOTP-104, “Fiber-optic Cable Cyclic Flexing Test.”  Change in attenuation shall not exceed 0.1 dB at 1550 nm for single mode fiber.  The magnitude of the attenuation change shall be within the repeatability of the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable jacket shall not exhibit evidence of cracking or splitting at the completion of the test.

6.	TIA/EIA-455-25-C FOTP-25, “Repeated Impact Testing of Fiber-optic Cables and Cable Assemblies.”  The magnitude of the attenuation change shall be within the repeatability of the measurement of 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable jacket shall not exhibit evidence of cracking or splitting at the completion of the test.

7.	TIA-455-33-A FOTP-33, “Fiber-optic Cable Tensile Loading and Bending Test.”  While subjected to a minimum load of 600 lbf, the cable sample shall be able to withstand a twist of 360 degrees in less than 3 meters of length.  The magnitude of the attenuation change shall be within the repeatability for the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable shall not experience a measurable increase in attenuation when subjected to the rated residual tensile load, 200 lbf.

8.	TIA/EIA-455-85-A FOTP-85, “Fiber-optic Cable Twist Test”:  The magnitude of the attenuation change shall be within the repeatability for the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The average increase in attenuation for the fibers shall be <0.40 dB at 1300 nm.  The cable jacket will exhibit no cracking or splitting under a 5x magnification after completion of test.

9.	TIA/EIA-455-181 FOTP-181, “Lightning Damage Susceptibility Test for Optic Cables with Metallic Components.”

10.	TIA/EIA-455-37-A FOTP-37, “Low or High Temperature Bend Test for Fiber-optic Cable”.

11.	TIA/EIA-455-98, FOTP-98-A, “Fiber-optic Cable External Freezing Test”.

662-3.04 FIELD TESTING AND PERFORMANCE OF FIBERS.  All testing of optical fibers shall be performed by a Certified Technician as described in subsection 662-3.02, Certified Fiber-Optic Technician.

The Contractor shall schedule the date, time, and location of any tests required by this specification with the Engineer at least 72 hours before performing the tests.  The Engineer or designee shall be present when the tests are conducted.  The Certified Technician shall demonstrate clearly how the tests are being performed and shall be made available to discuss testing strategies with the Engineer.

Tests shall be conducted using standard operating procedures as defined by the manufacturer of the test equipment.

The following tests shall be conducted after the cable has been installed, spliced, and connectorized.  Test results shall be submitted in accordance with subsection 662-3.05, Documentation of Testing.  Tests shall be performed before any permanent equipment connections.  All fibers shall be tests for continuity, events above 0.05 dB and total attenuation of the cable.  If the fiber-optic cable installed is connected to an existing fiber-optic cable, perform installation tests the installed cable and all existing fibers to which it is spliced or connected:

1.	End-to-end OTDR (Optical Time Domain Reflectometer) Testing. This test shall be conducted to identify attenuation associated with each fiber. Traces shall be provided for each operational wavelength for the type of fiber in the system to indicate attenuations and their locations.

A Certified Technician utilizing an OTDR and Optical Source/Power Meter shall conduct the tests after installation. The Technician shall conduct the test according to the standard operating procedure as defined by the manufacturer of the test equipment.

To eliminate or shift the “dead zone,” either a factory patch chord or “fiber launch box” of length greater than the dead zone shall be used.

Measurement shall be conducted for 1310 nm and 1550 nm for single mode fiber.

2.	Attenuation Test.  All fiber links shall be tested with a standard power-meter test and all attenuation shall be documented. For every fiber installed or connected to under this Contract, perform end to-end attenuation test.

For the test, use a calibrated optical source and power meter using the standard three-stage procedure.  Determine acceptable link attenuation by the cumulative value of standard losses based on length, number, and type of splices and connectors.

Provide test results of the fiber-optic cable that demonstrate the dB/km loss does not exceed +3 percent of the factory test or 1 percent of the cables published production loss.  The Engineer may elect to allow bi-directional averaging of OTDR testing due to splice loss core alignments.  Fiber-optic cable loss limits shall be in accordance with the following:

a.	No event shall exceed 0.10 dB.  If any event is above 0.10 dB, repair or replace that event location.

b.	Total dB loss of a cable fiber less events shall not exceed +3 percent of the factory test or 1 percent of the manufacturer’s published production loss at 1310 and 1550 nm.  Cable fiber loss shall not exceed Maximum Attenuation Limits as defined in subsection, “Single Mode Fiber-optic Cable.”

Cable Fiber Loss (dB)  =   Total Loss (dB)  - ∑ events (dB)

Cable Fiber Loss (dB/km) =  Cable Fiber Loss (dB)

Cable Fiber Length (km)

c.	Where total or event losses exceed these specifications, replace or repair that cable run and assume all expenses, both labor and materials. Elevated attenuation due to exceeding pulling tension during installation will require replacement of cable at the Contractor’s expense.

d.	Fusion splice losses shall not exceed 0.10 dB per fiber.  Mechanical splices, where allowed, shall not exceed 0.30 dB.

e.	Each connector, after factory assembled, shall not exceed the maximum loss of 0.50 dB (typical loss is 0.25dB) and optical return reflective loss of <-0.45dB.

f.	If event losses exceed these specifications, event locations shall be replaced or repaired without additional cost reimbursement for expenses.

g.	If total loss exceeds these specifications, Fiber-optic cable shall be replaced or repaired without reimbursement for expenses.

h.	All fibers within the cable shall be tested and proven usable in accordance with these specifications.

662-3.05 DOCUMENTATION OF TESTING.  Upon completion of the field test, the Contractor shall provide three copies of all documentation to the Engineer.  Except for standard bound materials, documentation shall be neatly bound in 8.5” x 11” (size A4) documentation in logical groupings.  Bindings shall be of either the 3-ring or plastic slide-ring type.  Permanently and appropriately label each such bound grouping of documentation.

Documentation from manufacturer shall include manufacturer data of cable and fiber including:

- Optical performance (OTDR) including dB/km loss measured at 1310 and 1550 nm for single mode.

- Manufacturer’s name

- Date of manufacture

- Index of Refraction

- Cable ID

- Connector losses and bandwidth/dispersion data

Documentation of field testing shall include a map. This map shall show:

- Cable part numbers

- Manufacturer

- Cable length markings

- As-built cable routing

- Location of splice points and hardware at each splice point location (see below under testing also).

Documentation shall include the information below for end-to-end testing, splice loss measurements, OTDR traces.

The documentation shall be neatly tabulated for each field test and shall include the following:

- Cable and Fiber Identification.

- Manufacturer

- Cable ID

- Fiber ID (include tube and fiber color)

- Cable Location – begin and end point

- Operator Name

- Date and Time

- Date of installation

- Fiber Count

2.	Setup Parameters.

- Wavelength

- Pulse Width (OTDR)

- Refractory index (OTDR)

- Jumper and/or Launch Box Length

- Range (OTDR)

- Scale (OTDR)

3.	Test Results.

a.	OTDR Test:

- Total Fiber Trace (mile)

- Splice Loss/Gain

- Measured Length (Cable Marking)

- Provide traces on Diskette to Engineer

- Total Length (OTDR) (mile)

- Events > 0.05 dB

- Backscatter

- End-to-End Attenuation Test:

- Length

- Number and type of splices and connectors

- Link Attenuation

Fiber-optic cable test results shall demonstrate that dB/km losses do not exceed limits in accordance with subsection, 662-3.04 Field Testing and Performance of Fibers.

662-3.06 PACKAGING.  Fiber-optic cables shall be shipped on wooden reels.  The diameter of the drum shall be a least 20 times the diameter of the cable.  The following information shall be either stenciled on the reel or on a weatherproof tag firmly attached to the reel or a combination of both in order to trace the manufacturing history of the cable:

- Optical Cable

- Number of Fibers

- Date cable was tested

- Non-armored

- Year of cable manufacture

- Name of cable manufacturer

- Gross weight

- Part Number

- Handling Instructions

- Arrow indicating cable wind direction

Cable data sheets shall be supplied to Engineer containing the following:

- Manufacturer Name

- Cable ID Number and fiber type

- Factory Order Number

- Cable Length

- Factory measured attenuation (each fiber)

- Index of Refraction

- Bandwidth Specification (where applicable

Sufficient cable length, in addition to the quantities shown on the plan, shall be provided for testing.  Both ends of the cable shall be available for testing.  Pack one continuous length of fiber-optic cable per reel; maximum overage shall not exceed 10 percent unless approved by The Engineer.  Compensation will not be granted for overage or excess cable needed for testing and installation methods.

Package the cable for shipping to prevent the cable from coming loose in transit.  Secure the outer and inner end of the cable.  Cover the reel with thermal wrap to protect the cable.  Apply end seals to each end of the cable to prevent moisture and from entering the cable.

Include the manufacturers test documentation with each reel. This documentation indicates the attenuation of each cable fiber in dB/km (dB/ft), measured at 1310 and 1550 nm for single mode fiber.

662-3.07 CONNECTORIZATION.

1.	Connectors.  This subsection shall consist of furnishing and installing connectors (in-line or terminated ends), attenuators as required in the plans, or as required for working fiber-optic system. All connectors shall be installed by a Certified Technician as described in this specification.

Hybrid adaptors shall not be used to connect two different connectors.  Hybrid jumpers with different connectors at each end of cable shall interface with equipment or cables with different connectors where needed.

Connectors shall be SC connectors for single mode fibers.  FC and ST connectors are allowed only where compatibility with equipment is required for fibers with a preset usage. These must be approved by the Engineer.

Connectors shall be installed with ceramic ferrules.  The fibers shall be secured within ferrule with epoxy, heat set or air dried, as specified by the manufacturer.  Machine polished mating faces shall be provided.  Install connectors per manufacturer application and recommendations, including proper termination to the outer tubing (900 micron, 3 mm fan-out) as required by the application.  Connectors shall be rated for operating temperatures of -400 F to 1600 F.  Connectors shall be factory-installed for all applications except where approved by the Engineer.

If connections are made, connectors shall be cleaned once before the first connection and once every time thereafter before reconnection. Connectors shall be cleaned according to manufacturers recommended practice.

Connector losses shall not exceed limits as described in subsection 662-3.04, Field Testing and Performance of Fibers.  Repeatability of keyed connectors shall not exceed 0.2 dB.

Boots shall be provided for durable cable strain relief.

Dust caps shall be provided and installed at all times when connector is not in use.

2.	Patch Panels.  Terminate and secure 4 fiber pairs from one buffer tube in the cable to a Gator Patch TM type drop cable located in the traffic signal controller cabinet that the fiber is shown to enter in the plans.

Ensure the fibers used throughout the system are matched correctly to allow for communications from one cabinet to the next in the system.

Ensure that the patch is compatible with the fiber optic cable/cables being terminated and color-coded to match the optical fiber color scheme.

All patch connectors shall be clearly labeled. The panel shall have a minimum of 8 SC type connectors, and shall be din rail mountable.

All installed patch panels shall include documentation regarding the identification, route, and function of each patch panel connector at that location.

Place at least one copy of this information alongside the installed equipment or in the controller cabinet door pouch.

662-3.08 ATTENUATORS.  Attenuators shall be provided at no extra payment to the Contractor to achieve the desirable signal loss. Attenuators shall only be installed on the receiving end closest to the originating transmission (typically closest to the Traffic Signal Management Center).

Connecting ends shall be compatible to connectors described in subsection 662-3.07, Connectorization.

662-3.09 SPLICES.  Two weeks before the start of the fiber-optic cabling installation, the Contractor shall submit the following:

- Proposed locations of the mainline spliced points for review by the Engineer.

- Proposed process to be used for splicing including procedure.

- Cleave tool and specific fusion splicer to be used.

1.	All Splices.

a.	Splicing and termination of optical fibers shall be performed by a Certified Technician as described in 662-3.02 Certified Fiber-Optic Technician.

b.	Splicing shall only be allowed in areas as designated on the plans or as approved by the Engineer.

c.	Splices and stripped cable shall be housed by a fiber splice closure (FCS) in designated locations shown on the plans.

d.	Cable ends involved in splicing shall match colors of the fibers and buffer tubes to the extent possible.

e.	No stresses shall be placed on the fibers before or after the splice is completed.

f.	Splice loss shall not exceed limits as described in subsection 662-3.04, Field Testing and Performance of Fibers

g.	Fan-out kits are required for splices to multiple fibers in the buffer tubes for single mode fiber.

h.	Splices shall be located in the center of the slack cable in manholes or vaults.

2. 	End-To-End Splices.

a.	End-to-end splicing shall be performed as per manufacturer instructions for the supplied splice closure units.

b.	End-to-end fusion splicing shall be conducted for any disturbed fibers within the disturbed buffer tube(s).  Remaining buffer tube(s) that are not required for splicing shall be undisturbed and protected in the Splice Closure.

c.	End-to-end fusion splices shall be used on mainline splices for all fibers (72 fibers typical) within the fiber-optic cable where designated in the plans.

3.	Fusion Splices.

a.	Fusion splices shall be made with a portable fusion splicer, capable of AC or internal battery-powered operation.  The unit shall be able to splice fibers specified herein with 250  micrometercoating and 900 micrometer coating with little or no modification in the field.  The fusion splicer shall be capable of full battery recharge in an eight-hour charging period.

4.	Drop Fiber Splices.

a.	Drop fiber splices (6 fiber typical) and drop cables (6-fibers typical) shall be used for connectivity between a primary mainline fiber-optic cable (72-count typical) and field devices (i.e., traffic signal controller cabinet) as identified in the plans.

b.	Drop fiber splices shall consist of breaking out the required buffer tube(s) from the fiber-optic trunk cable (72-count typical) and fusion splicing the appropriate number of fibers to the fiber-optic drop cable (6 fibers typical). Remaining undisturbed fibers, if any, shall be protected in the splice tray.

- Drop fiber splice shall be performed for each device location at locations shown on the plans.  Splicing shall be performed as per Corning Cabling Systems Recommended Procedure SRP-004-013, Mid-Span Access of Fiber-optic Cable (Cable Slack Present), or an equivalent manufacturer’s 	recommended procedure approved by the Engineer.

662-3.10 SPLICE CLOSURES.  Fiber-optic splice closures (FSC) shall be installed in the locations on the plans at designated splice locations. Closures shall contain splice trays or organizers that contain the splices.

Before installation, the Contractor shall provide certification from the manufacturer that the splice closures conform to the specifications and test procedures.

1.	Closures.

a.	Splice closures shall be designed for use under the most severe conditions such as moisture, vibration, impact, cable stress, and flex temperature extremes. This will be demonstrated by successfully passing factory test procedures and these specifications.  The closure shall prevent the intrusion of water without the use of encapsulates.

b.	Closure re-entry and subsequent reassemble shall not require specialized tools or equipment; these operations shall not require the use of additional parts.

c.	Splice closures shall provide housing and storage for all splices, stripped cable, and undisturbed buffer tubes.  All splices enclosures shall provide protection and strain relief to optical fibers. Splice closures shall be suitable to handle straight, butt or branch splices.

d.	Splice closures requiring greater than 48 splices shall provide for the following requirements:

1)	6-inch diameter by 22-inch length.

2)	One, six-cable entry end plate.

3)	One blank end plate.

4)	All endplates shall be 3-section, pre-molded, and suitable for use with Coyote closures.

5)	Required accessories to complete splice.

6)	One future cable entry kit for each splice closure.

e.	Closures shall be provided with external valve pressurization ports.  Closure shells shall be glass-filled high-density thermoplastic that effectively withstands corrosion; high impact and freeze thaw stresses.

f.	Closure endplates shall be interchangeable with each size of closure available from the closure supplier.

g.	Where additional access is required into an existing splice closure, replace the existing endplate with an endplate suitable for the task.

h.	Splice closures shall accept up to six cables in a butt configuration, and 12 for in-line configuration without special adaptors.

i.	Closure shall contain a permanent neoprene gasket seal.

j.	All closures, including closing hardware, shall be from the same supplier.

k.	External Shrader valve pressurization port shall be supplied.

l.	The splice closure shall be designed and equipped with the necessary mounting hardware to be attached to the side of the manhole or vault, and to be suspended with sufficient clearance at each end for acceptable cable bends.

m.	All cables shall be properly dressed and affixed to rails or racks within the manhole or vault.  No cables or enclosures will be permitted to lie on the floor.

n.	Fiber-optic cables shall be restrained within the splice enclosure such that there is no discernible tensile force on the optical fiber.

o.	The splice closure shall have provisions for storing fiber splices in an orderly manner, mountings for splice organizer assemblies and space for excess or unspliced fiber.  Splice organizers shall be re-enterable and re-sealable.

p.	The closure shall be capable of accommodating a minimum of 2 splice organizer trays, which shall accept mechanical, fusion, or multi-fiber array splices.

q.	Splice closures shall contain a basket allowing fiber buffer tube storage of exposed buffer tubes. The splice case shall be UL rated.

r.	The closure shall be installed according to the manufacturer’s recommended guidelines.

2.	Splice Tray.

a.	One splice tray shall be designed to hold a minimum of 12 mechanical splices.  A second splice tray (for Fiber-optic Drop Cable splicing) shall be designed to hold a minimum of 12 fusion splices.  All other splice trays provided in the closure shall be designed to hold fusion splices of 12 (typical) up to 36 splices. Total number of splices supported shall be 96 splices.

b.	Splice trays shall allow for optical fiber storage as recommended by the manufacturer.  The splice closure shall have provisions for controlling the fiber bend radius (1.5 inches typical) to a minimum as required by the manufacturer.

662-3.11 SPLICE CLOSURES -FACTORY TESTING REQUIREMENTS.  The construction and testing of the fiber-optic splices and splice enclosures shall comply with all applicable industry standards including Electronic Industry Standards (EIA/TIA), ANSI and ASTM standards.

Splice closures shall meet the following test requirements:

1.	Compression Test.  The closure shall not deform more than 10 percent in its largest cross-sectional dimension. When 	subjected to a uniformly distributed load of 300 lbf (1335 N) at temperatures between 00F and 1000F 	(–180C 	and +380C).  The test shall be performed after stabilizing at the required temperature for a minimum of 2 hours.  It shall consist of placing an assembled closure between two flat paralleled surfaces, with the 	longest 	closure dimension parallel to the surfaces.  The weight shall be placed on the upper surface 	for a minimum of 15 minutes. The measurement shall then be taken with weight in place.

2.	Impact Test.  The assembled closure shall be capable of withstanding an impact of 21 ft-lbf (28 N-m) at 	temperatures of 100F and 1000F (-120C and 380C).  The test shall be performed after stabilizing the 	closure at the required temperature for a minimum of 2 hours.  The test fixture shall consist of a 20 lb (9 kg) cylindrical steel impacting head with a 2-inch (5 cm) 	spherical radius at the point where it contacts the closure.  It shall be dropped from a height of 12 inches (30 cm).  The closure shall not exhibit any cracks or fractures to the housing that would preclude it from passing the water immersion test.  There shall be no permanent deformation to the original diameter or characteristic vertical dimension by more than 5 percent.

3.	Cable Gripping and Sealing Testing.  The cable gripping and sealing hardware shall not cause an increase in fiber attenuation in excess of 0.05 dB/fiber @ 1550 nm when attached to the cables and the closure assembly. The test shall consist of measurements from six fibers, from each buffer tube or channel, or randomly 	selected in the case of a single fiber bundle.  The measurements shall be taken from the test fibers, before and after assembly. This will determine the effects of the cable gripping and sealing hardware on the optical transmission of the fibers.

4.	Vibrations Test. The fiber splice organizers and splice retaining hardware shall be tested per EIA standard FOTP-11, 	Test condition I. The individual fibers shall not show an increase in attenuation in excess of 0.1 dB/fiber.

5.	Water Immersion Test.  The closure shall be capable of preventing a 10-ft (3-meter) waterhead from intruding into the splice 	compartment for a period of 7 days.  Testing of splice closure is to be accomplished by the placing the closure into a pressure vessel and filling the vessel with tap water to cover the closure.  Apply continuous pressure to the vessel and maintain a hydrostatic head equivalent to 10 ft (3 m) on the closure and cable.  This process shall be continued for 7 days.  Remove the closure and open to check for the presence of water.  Any intrusion of water into the compartment containing the splices constitutes a failure.

6.	Certification.  It is the responsibility of the Contractor to insure that all of the above tests have been performed by either the manufacturer, or an independent testing laboratory, and the appropriate documentation has 	been submitted to the Engineer.  Manufacturer certification is necessary for the model of closure supplied. It is not necessary to subject each supplied closure to the actual tests described herein.

662-3.12 WARRANTY AND MAINTENANCE.  Manufacturer’s support (customary warranties) period shall be provided for all equipment and materials furnished and installed as part of the fiber-optic system. This includes end equipment such as modems, panels, switches and etc. Manufacturer’s and Contractor’s warranties or guarantees shall be continuous throughout their intended duration and be stated that they are subject to transfer.

662-4.01 METHOD OF MEASUREMENT.  Section 109.

662-5.01 BASIS OF PAYMENT.  The contract lump sum price for 662(3) pay item is full compensation for a complete working signal interconnects system.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

662(3)	Signal Interconnect System Complete - Fiber	Lump Sum

CFHWY00317

Special Provisions

Add the following Section:

SECTION 667
TRAFFIC SIGNAL COMMUNICATION SYSTEM

667-1.01 DESCRIPTION. Provide all labor, equipment and materials, mounting hardware and ancillary items to provide a fully functional traffic signal communication system. Requirements include all items detailed in this Section and the Plans including but not limited to:

1.	Installation and setup of radio interconnect system between traffic signal controllers shown in Plans

2.	Providing other equipment and deliverables as specified

3.	Manufacturer assisted startup of the system

667-2.01 MATERIALS.

Approved Products List. The Approved Products List does not apply to the 667 Pay Items. Provide catalog cuts of materials to the Engineer for review and approval.

Materials Not Requiring Certification. Only submit these materials for review and approval if they are included in the Materials Certification List (MCL).

Provide new materials that meet the requirements set forth in Section 740 of the Special Provisions, the Material Certification List (MCL) and the latest version of the Standard Specifications for Highway Construction. The following equipment is required as part of the Traffic Signal Communication System:

1.	Radio Interconnect System. Provide the following materials in the number and locations detailed in the Plans. All connecting cables, mounting hardware, conduit, and appurtenances are to be included.

a.	Antenna

b.	Antenna Cable

c.	AC Adaptor

d.	Lightning Protector

e.	Antenna Cable Connectors

667-3.01 CONSTRUCTION REQUIREMENTS. The Manufacturer’s Representative shall be available over the phone during installation and startup of the system. The contractor must meet the requirements of Subsection 660-3.01, Construction Requirements of the Standard Specifications for Highway Construction, Special Provisions and the following:

1.	Radio Interconnect System.

(1)	Installation:

(a)	Installation is to be neat and attractive.

(b)	Install shelf mounted radio(s) in each traffic signal controller cabinet shown in the Plans. Mount radios to the top of the controller shelves. Where room is not available to mount the radios to the shelf top, provide under shelf mounts.

(c)	Provide additional AC outlets on wall of traffic signal controller cabinet as required. Power strips are not permitted.

(d)	Install antenna wire between traffic controller and antenna according to manufacturer’s recommendations, the Plans, and Specifications.

(e)	Mount antenna on traffic signal pole nearest traffic controller, except where the radio site survey dictates placing the antenna at another location or otherwise directed.

(f)	Antennas are to be mounted at least 10 feet above the mastarm on the vertical member of the signal pole or as shown in the Plans. Only one 3/4" or smaller hole may be drilled in the pole. Deburr the hole and protect from corrosion with an approved zinc based finish.

(g)	Run antenna wire inside pole.

(h)	Install antenna wire in conduit as shown in the Plans.

(i)	Provide lightening suppression designed to protect radios and other signal controller assembly components.

(j)	Establish communication with traffic signal controller.

(k)	Enable radio diagnostics.

- Hardened Router:

      - Install Hardened Router in the Traffic Signal Controller in the location specified in the plans.

      - Program Hardened Router as specified by manufacture.

      - Establish communications with Ethernet Switches, and Centracs traffic signal monitoring software.

- Ethernet Switch

- Establish communications with, but not limited to: antenna, GPS, Radio, Controller, MMU, Opticom, PTZ, Fiber interconnect, Copper interconnect, other Ethernet Switches, and router.

Submit shop drawings, catalog cuts, product specifications, and industry standard certifications for the required materials, equipment and services specified in the plans to the Engineer for review and receive approval prior to fabrication, or delivery if prefabricated, to the project site or ADOT & PF Maintenance and Operations Yard.

667-3.05 DELIVERABLES. The Contractor shall provide the Engineer with each of the following prior to final acceptance of the item:

1.	Operations Manuals. Provide 2 complete sets of operations manuals for all equipment associated with the Traffic Signal Communication System components. This should include but not be limited to; radios, switches, and cables.

667-4.01 METHOD OF MEASUREMENT. Per Section 109.

667-5.01 BASIS OF PAYMENT.

Payment will be made under:

All traffic signal communications items will be paid under 660(1E).

CFHWY00317

Special Provisions

Add the following Section:

SECTION 669
AUTOMATED TRAFFIC RECORDERS

Special Provisions

669-1.01 DESCRIPTION. Furnish and install Automated Traffic Recorder (ATR) stations at locations shown on the Plans.

ATR stations consist of inductive loops that detect the presence and speed of passing vehicles.  Inductive loops are connected to an Automatic Vehicle Classifier (AVC) traffic counter.  In each traffic lane, two inductive loops are separated by a specific travel distance and buried beneath the pavement.  Lead wires run in underground conduit from the sensors to a type CBA1 cabinet located at the side of the road.  Inside the type CBA1 cabinet, the lead wires mount to a terminal block which facilitates the connection to the AVC traffic counter.

ATR stations are operated and maintained by personnel of the Highway Data Section (HDS); main office located at 2200 E. 42nd Ave., Anchorage, phone (907) 269-0876.

The locations of junction boxes, inductive loops, and cabinets, shown on the Plans are approximate and the Engineer will establish the exact locations in the field after consultation with the DOT/PF HDS.

669-1.02 REGULATIONS AND CODE.  Use materials and workmanship that conforms to the standards of the Underwriter's Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

Use electrical equipment that conforms to the standards of the National Electrical Manufacturer's Association, where applicable.

669-2.01 MATERIALS.  Provide all new materials that meet the following requirements:

1.	Wiring.  Subsection 660-3.05, Wiring.  Use single wire conductors and cables that have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, insulation type-letter designation, conductor size, voltage rating and the number of conductors if a cable.  Home run label all wires and cables in each junction box and cabinet; for example, W1SLA (for wire) and GaSLA (for cable) as shown on the Plans.

2.	Conduit.  Subsection 660-3.03, Conduit. Use galvanized rigid metal for conduits, except for PVC conduit forming the inductive loops. Provide grounding bushings with plastic-sleeves to minimize the potential for insulation damage during wire pulls.

3.	Junction Boxes.  Subsection 660-3.04, Junction Boxes.  Label the covers of all junction boxes used for loops or sensor wires 'TRAFFIC'.  Label the covers of all junction boxes used to provide electrical service to ATR installations 'ELECTRIC’.  Keep junction boxes for 120V/240V electrical service completely separate from junction boxes containing loop or sensor wiring

4.	Terminal Blocks.  Mount Terminal Blocks horizontally as shown in the plans.  Use terminal blocks with nickel, silver or cadmium plated brass binder-head screw terminals.  Use barrier type terminal blocks rated 600 VAC at 20 Amps, sized for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips.

5.	Presence Loops.  Use UL listed IMSA specification #51-5-1984 single conductor PVC nylon with tube jacket, type THHN, #14 AWG conductors for detector presence loops.  Use twisted pairs of 18 AWG stranded tinned copper wire for multiple pair loop lead-in cable.  Each twisted pair shall have its own 20AWG tinned copper drain wire.  An aluminum foil shield shall surround each individual bundle of twisted pair and drain wire. Multiple pair loop lead-in cable shall have an overall PVC or PE outer jacket.

- Style CBA1 Cabinets.  Cabinets shall meet or exceed a UL 50, NEMA Type 3R rating.  CBA1 cabinet shall be a Hoffman #131JF, 20X17X15 or equal.  Construct the cabinet and hinged door from 5052-H32 or better unpainted sheet aluminum alloy with a minimum thickness of 1/8 inch and a smooth grain finish on the exterior.  Corbin #2 Key Lock.  One (1) adjustable shelf.  Drip Shield.  Interior has four (4) instruct channels for installing adjustable shelves.  Grounding points included on body and door.  Door latching mechanism is a single point PowerGlide padlocking handly system which secures the door in the middle. A door stay is included at the bottom of the door with three positions:  90, 120, and 180 degrees.  Ensure that welds are neatly formed and free of cracks, blowholes and other irregularities.  Ensure inside and outside edges of the cabinet are free of burrs.  Design the cabinet with a sloped top to prevent the accumulation of water on its top surface.

669-3.01 CONSTRUCTION REQUIREMENTS.

1.	Wiring.

  - Referenced Requirements. Subsection 660-3.05, Wiring.

  - Termination. Terminate unused pairs at junction boxes within splices.  Terminate unused pairs in terminal blocks at cabinets.  Terminate and solder conductors, including unused spares to “spade” type terminal lugs at terminal blocks.

  - Relief. Provide at least 2 feet of slack cable for wiring in each junction box and at least 6 feet of slack cable available in the equipment cabinet before the terminal block.

  - Labeling. Label wiring in junction boxes and at terminal blocks.

2.	Conduit.

- Referenced Requirements. Subsection 660-3.03, Conduit, or as indicated on the Plans.

- Pull Cords. Leave nylon pull cords in all conduits larger than 1 inch and in spare conduits.

- Bushings.  Ensure that plastic or plastic-sleeved bushings are in place before wire pulls are performed.

3.	Junction Boxes.

- Referenced Requirements. Subsection 660-3.04, Junction Boxes, or as indicated on the Plans.

- Voltage Limitation.  Junction boxes used for ATR installations shall not contain wiring of 24 V.

4.	Terminal Blocks.

- Terminal Block Placement. Mount terminal blocks within cabinets so that terminals are easily accessible from the front of the cabinet.

- Labeling. Clearly label terminal blocks and wire pairs on the block.

- Termination. Terminate and solder conductors, including unused spares to "spade" type terminal lugs

5.	Presence Loops.

- Placement Design Adherence.  The Plans are not schematics; installation of the presence loops shall closely conform to the location and layout of conduit runs shown in the Plans.  The contractor shall notify the Project Engineer 14 days prior to saw cutting the pavement for approval of the site layout.

- Presence Loop Dimensions.  Unless otherwise noted on the plans, form presence loops using four turns of wire, making 6 feet square with a tolerance of ± 1 inch.

- Presence Loop Dimensions for On-Ramps and Off-Ramps. Form presence loops in On-Ramps and Off-Ramps using four turns of wire, making a rectangular 8 feet wide and 6 inch long with a tolerance of ± 1 inch.

- Lead-in Conduit. Place lead-in conduits straight and perpendicular to the centerline of the road from the edge of pavement to the presence loops.

- Presence Loop Alignment. Center presence detector loops in the traffic lane with a tolerance of ± 1 inch.

- Presence Loops in Asphalt.

- Loop Placement. Locate presence loops 16 feet from leading edge to leading edge unless otherwise noted on the Plans with a tolerance of ± 1 inch.  Align  presence loops in adjacent lanes within a tolerance of ± 1 inch.

- Compaction tests.  Compaction test requirements are at the discretion of the Engineer.

  - Cabinets.

  - Cabinet Placement and Orientation.  Install cabinets out of the Clear Zone with the doors facing away from the road.  Unless the orientation is otherwise noted on the plans.

  - Conduit Entry.  Install conduit entries for above-ground enclosure through the bottom of the enclosure.  No conduit runs shall be cut through the sides or top of above-ground enclosure.

8.		Utilities.

- Asphalt Pavement Roughness. No transverse seams, joints or roughness within 50 feet of any inductive loops placed in asphalt pavement section is allowed.  Test the finished surface of the asphalt with a straightedge 10 feet long.  Ensure that the surface does not vary more than ¼ inch from the lower edge of the straightedge within 50 feet of sensors at the ATR installations.  At the Engineer’s discretion, run an inertial profiler or a profilograph equipped with a chart recorder down each wheelpath of each lane for a distance of 50 feet before and after each ATR installation.  HDS will supply the profilograph for the Contractor’s personnel to operate.  Ensure that the asphalt surface as recorded by the chart recorder does not vary more than ¼ inch in 10 feet.

- Field Inspection.  Notify the Engineer in writing a minimum of 3 working days in advance (excluding Saturday, Sunday and State or Federal Holidays) before installing conduit/wiring, inductive loops, bending plate equipment, piezoelectric cable, axle sensors, and cabinets.  The Engineer will be present to approve the installation before backfill placement and paving.  At the Contractor's expense, correct and allow the Engineer to re-inspect unacceptable installations for completeness prior to backfill placement and paving.  The Contractor shall be required to excavate, remove, and replace all installations backfilled or paved without prior approval by the Engineer at the Contractor’s expense.

669-3.02 ACCEPTANCE TESTING.  Perform acceptance testing on ATR installations.

      - General Tests.  Perform tests for the ATR installations according to subsection 660-3.01, Installation Details.

669-3.03 WARRANTY. For the period of 1 year after final acceptance of the ATR, the Contractor shall promptly replace any failed ATR components upon notification by Highway Data Section. This includes: the cabinet, foundation, loops, piezoelectric sensors, associated conduit and wiring, and other devices listed in the 669 specifications.

669-3.04 DELIVERABLES.  Submit deliverables to the HDS before final approval of the work or as otherwise called for herein.

1.	Materials Submittal.

    - Format and Contents.  Provide a Materials Submittal of proposed equipment and materials for the ATR installations.  The Materials Submittal shall consist of three collated copies of an equipment and materials portfolio.  Each identical portfolio shall contain information of sufficient detail to determine the suitability of the equipment and materials proposed.

    - Table of Contents.  Each portfolio shall include a table of contents listing each item's intended uses, item description, product name, manufacturer, model or part number and reference to associated information within the portfolio.

    - Reference Drawings. The Materials Submittal shall include a detailed shop drawing of each equipment cabinet showing the location of mounted components.

    - Delivery Interval. Deliver Materials Submittal through the Engineer for review and approval of the Highway Data Supervisor within thirty days following award of the Contract.

    - Liability. The State of Alaska will not be liable for any materials purchased, labor performed, equipment used or delay to the work before equipment and materials have been reviewed and approved.

2.	As-Built Plans.

- Prepare four complete sets of as-built plans, which will be current with the construction. These as-built plans shall detail construction changes made to the ATR design and include the following information on the appropriate sheets:

- Location and depth of inductive loops, piezo sensors, conduit runs and scales.

- Locations of equipment cabinets and junction boxes.

- Station and offset of junction boxes

- Present three sets of as-built plans to the Engineer, and affix one set to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation in a waterproof, clear plastic holder.

- Redlines of full size construction plans will be acceptable as-builts.

3.	Photographs.

- Provide digital photographic prints CD format CD ROMs documenting sensor installations.

- Deliver photographs and CD ROMs organized in one or more white colored, D-ring style, 3 ring binders with clear insert overlays on fronts and spines.  CD ROMs will be placed in CD storage sheets inside the binders.

- The photographs shall show the inductive loops and conduit in place before covering with gravel and pavement for asphalt pavement sites, or before covering with epoxy compound for concrete pavement sites.  The photographs shall include:

- Two or more overall views of each ATR installation showing placement of the inductive loops.

- One or more views of each loop showing the loop and the conduit to the nearest junction box.

- One or more views of each piezo sensor conduit showing the coaxial cable, saw cut, and conduit to the nearest junction box

- One or more views of each temperature sensor showing the lead cables, saw cut, and conduit to the nearest junction box

4.	Test Results. Written or printed copies of the final results of tests, signed by the Contractor, shall 	be provided to the Engineer before acceptance of the Automated Traffic Recorder Installation.

5.	Manuals. Provide through the Engineer to the Highway Data Manager installation, repair, and operation manuals for 	Automated Traffic Recording equipment supplied by the Contractor.

6.	Materials.

- Provide to the Highway Data Manager any ATR equipment, sensors, and epoxy grout remaining after installation.

- Palletize the Deliverable Materials.

- Group the contents of each pallet by like items.

- Attach to each pallet a sealed plastic pouch containing complete copies of Material Safety Data Sheets that apply to the contents of that pallet.

- Provide an itemized list of Deliverable Materials for each item, the list shall detail:

- Item description: including nature of the item, brand name, manufacturer name, model number, type number and serial number.

- Item condition

- Item quantity

- Provide complete copies of Material Safety Data Sheets that apply to the Deliverable Materials.  Attach Material Safety Data Sheets after the last page of the Deliverable Materials list.

669-4.01 METHOD OF MEASUREMENT. Section 109.

Automated Traffic Recorder sites will be measured Lump Sum.

669-5.01 BASIS OF PAYMENT.

The Contract unit price for Automated Traffic Recorder installations shall be full compensation for furnishing all equipment, labor and subsidiary materials required for completion of a site for which there is no specific item in the Plans is subsidiary to the 669 item.  This includes but is not limited to:

- backfill materials,

- clearing and grubbing for utilities,

- seeding,

- topsoil,

- removal of structures and obstructions,

- structural excavation for conduits and minor structures,

- work in support of utilities as specified in Subsection 105-1.06,

- as-built plans,

- providing the manufacturer’s representative,

- acceptance testing,

- j-boxes,

- CBA cabinets,

- portable heater and cooling fan,

- tilt poles,

- rigid conduit,

- load centers,

- demolition of CBA cabinet foundations and associated utility lines/conduits/appurtenances,

- loops,

- piezoelectric sensors,

- radar sensors,

- TDP's,

- surface temperature probes,

- ambient air sensors,

- AVCs

- ATR equipment or work as shown on the plans or specifications.

WITHHOLDING.  To ensure full compliance under this Section, twenty percent (20%) of the billings for each 669 item shall be withheld until written acceptance of the site has been received from the Engineer.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

669 (K1)	Automated Traffic Recorder - Site 1	Lump Sum

669 (K2)	Automated Traffic Recorder  - Site 2	Lump Sum

CFHWY00317

SECTION 670
TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Pavement Markings as shown on the Plans and as directed.

Pavement Marking Type:  Methyl Methacrylate (MMA)

670-2.01 MATERIALS.  Replace the material reference,

“Methyl Methacrylate Markings							Subsection 712-2.17”, with,

Methyl Methacrylate Pavement Markings				Subsection 712-2.17

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.  Delete No. 4 and substitute the following:

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

SURFACE APPLIED

Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 60 mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of 60 mils.

INLAID

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

(1)	Longitudinal Markings.  Groove the pavement to a depth of  250  mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of  250  mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Groove the area for inlaid markings to a depth of  250  mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of  250  mils.

(b)	Roundabouts:

As designated on the plans, groove the area for inlaid markings in roundabouts to a depth of 500 mils.  Apply markings to yield a thickness of 500 mils.

(c)	Gore Markings:

Diagonal gore markings will not be inlaid unless shown in the Plans.

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01)

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Replace Subsection 3.06 with the following:

670-3.06 TOLERANCE FOR LANE STRIPING.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measured from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete No. 2.

Delete No. 3 and replace with the following:

3.	Each.  Pavement markings using letters, numbers, and arrows will be measured on a unit basis with each separate word or symbol constituting a unit.  Railroad Markings will be measured by the complete unit shown for each lane of travel.

Add the following No. 4:

4.	Foot Basis.  Longitudinal pavement markings, transverse, and gore markings, surface applied or inlaid will be measured by the linear foot of 4 inch wide line.  Wider striping will be measured in multiples of 4 inches.

670-5.01 BASIS OF PAYMENT.  Add the following:

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with pavement markings are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Temporary pavement markings and removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

Replace Item 670(10) with the following:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10)	MMA Pavement Markings	Lump Sum

670(10A)	MMA Pavement Markings, Longitudinal Surface Applied	Linear Foot

670(10B)	MMA Pavement Markings, Symbols and Arrow(s) Surface Applied	Each

670(10C)	MMA Pavement Markings, Transverse and Gore Surface Applied	Linear Foot

670(10D)	MMA Pavement Markings, Longitudinal Inlaid	Linear Foot

670(10E)	MMA Pavement Markings, Symbols and Arrow(s) Inlaid	Each

670(10F)	MMA Pavement Markings, Transverse and Gore Inlaid	Linear Foot

Delete Items 670(11) and 670(12).

CR670.1-110812

Special Provision

Add the following Section:

SECTION 682
UTILITY POTHOLING

682-1.01 DESCRIPTION.  Expose subsurface utilities using a vacuum-extract truck.  Record the location of the utility(s). Backfill the pothole and dispose of waste materials.

682-2.01 MATERIALS.

Backfill Material:			Aggregate Base Course, Grading D-1		Section 703

Asphalt Patch Material:		Hot Mix Asphalt Type II, Class B				Section 401

682-3.01 CONSTRUCTION.  Submit the utility potholing schedule to the Engineer and utility companies not less than 7 days before starting potholing.

Deliver the vacuum-extract truck to the job-site with the debris tank empty.

Expose the subsurface utilities.  Log the as-built information, subsection 682-3.02.  Backfill the pothole immediately after the Engineer accepts the logged data.  Backfill the first 6 inch lift using the excavated material, compact the material.  Backfill the balance of the pothole using Aggregate Base Course, Grading D-1, compact the material.  In paved areas, use Hot Mix Asphalt Type II, Class B to patch over the pothole, match the thickness of the surrounding pavement.

Dispose of excavations off-site.  Before beginning potholing, provide to the Engineer a certificate, signed by the owner or owner's representative, identifying the disposal site and acceptance of the project potholing excavations.

Utilities damaged by the potholing operation require the Engineer to be immediately notified.  The Contractor is responsible for the repairs and the associated costs.  Contact and coordinate repairs with the utility owner.

682-3.02 AS-BUILTS.  Create a utility pothole log, as-built, recording for each pothole: the date of potholing operation, utility type and size, station, offset, elevation, groundwater, and other pertinent data.  Survey the utility location using the project horizontal and vertical control; comply with the requirements of Section 642.  Submit the completed log to the Engineer within two working days following the completion of the pothole excavation.

682-4.01 METHOD OF MEASUREMENT.  The pay unit, contingent sum, is measured by the hour of work performed.

682-5.01 BASIS OF PAYMENT.  Pay Item No. 682(1) is paid at $450/hour for the work to pothole; expose the utility(s), backfill the hole, patch disturbed pavement and dispose of excavations.  The paid time includes the work; labor, and the fully operated vacuum truck or combination of vacuum truck and other Engineer approved equipment engaged in potholing at the area(s) identified in the Plans and/or identified by the Engineer.  The paid time includes the time to empty the vacuum truck of excavation material, including the travel time, from this project only, to a certified disposal site.

Travel time to and from the project, idle time, maintenance and repairs (labor, material and time) are incidental and not included in the measured time.

As-built, utility pothole log, per subsection 682-3.02, will be paid under Section 642.

Potholes for the Contractor's information and potholes not accepted by the Engineer will not be paid for by the Department.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

682(1)	Vac-Truck Pothole	Contingent Sum

CR682-010114

DIVISION 700 — MATERIALS

Blank Page

SECTION 702
ASPHALT MATERIALS

Special Provision

702-2.01 ASPHALT BINDER. Add the following:

Meet AASHTO M 320 Performance-Graded Asphalt Binder and AASHTO M332 Performance-Graded Asphalt Binder Using MSCR Test Specification; except, as included in Table 702-2.01-1 Performance-Graded Asphalt Binder – Exceptions.

TABLE 702-2.01-1

PERFORMANCE-GRADED ASPHALT BINDER - EXCEPTIONS

| Performance Grade | Viscosity AASHTO T 316 | Multiple Stress Creep Recovery MSCR, AASHTO T 350 |  |  | Dynamic Shear PAV, AASHTO T 315 | Direct Tension AASHTO T 314 | Elastic Recovery AASHTO T 301 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | JNR3.2 kPa-1 | JNR Diff | % Recovery3.2 | G*Sinδ, kPa |  |  |
| AASHTO M320 Performance-Graded Asphalt Binder |  |  |  |  |  |  |  |
| PG 52-28 | None | — | — | — | None | Delete | None |
| PG 52-40 | None | — | — | — | None | Delete | None |
| PG 52-40ER | None | — | — | — | None | Delete | 50% min. |
| PG 58-34ER | None | — | — | — | None | Delete | 60% min. |
| PG 64-40ER | None | — | — | — | None | Delete | 60% min. |
| AASHTO M332 Performance-Graded Asphalt Binder Using MSCR Test Specification |  |  |  |  |  |  |  |
| PG52V-40 | None | 0.50 max. | Delete | 75 min. | None | Delete | None |
| PG58E-34 | None | 0.25 max. | Delete | 85 min. | None | Delete | None |
| PG 64E-40 | 1 Pas max. | 0.10 max. | Delete | 95 min. | 5000 max. @ 4°C | Delete | None |

CR702.3R-100117

702-2.03 EMULSIFIED ASPHALT.

2.	Special Tack Emulsion, STE-1.

TESTS ON RESIDUE

Replace the first line: 	Penetration @ 77 °F	100-200,

with:	Penetration @ 77 °F	100-250

CR702.2R1-060115

SECTION 703
AGGREGATES

Special Provisions

Replace Subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Type IV, and VH mixes.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

CR703.1-100117/CFHWY00317

Meet Table 703-3 requirements:

TABLE 703-3

COARSE AGGREGATE QUALITY FOR HMA

| Description | Specification | Type II, Class A | Type II, Class AH | Type I; Type II, Class B; Type III | Type IV | Type VH |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| LA Wear, % max. | AASHTO T 96 | 45 | 45 | 45 | 45 | 45 |  |
| Degradation Value, min. | ATM 313 | 30 | 30 | 30 | 30 | 30 |  |
| Sodium Sulfate Loss, % max. (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 | 9 |  |
| Fracture, % min. | ATM 305 | 90, 2 face | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |  |
| Flat-Elongated Pieces, % max. | ATM 306 |  |  |  |  |  |  |
| 1:5 |  | 8 | 8 | 8 | 8 | 8 |  |
| Absorption, % max. | ATM 308 | 2.0 | 2.0 | 2.0 | 2.0 | 2.0 |  |
| Nordic Abrasion, % max. | ATM 312 | - | 8 a | - | - | 8 a |  |

a.	Hard Aggregate that meets the Nordic Abrasion values specified may be obtained from, but not limited to, the following sources:

	MS 52-068-2, located at MP 217 on the Parks Highway near Cantwell

	Alaska Lime Co, Jim Caswell, located at MP 216.5 on the Parks Highway near Cantwell

	CalPortland plants located in Dupont Washington

	Jack Cewe Ltd located in Coquitlam British Columbia, Canada

CR703.1/CFHWY00317

Fine Aggregate.  Aggregate passing the No. 4 sieve.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type II, Class A mix shall not contain more than 10% natural fines (blend sand and mineral filler) added to the crushed aggregate, and shall not exhibit rut depth larger than 1/4-inch, as determined by ATM 419.

Fine aggregate for Type IV and VH mixes:

	do not blend back natural sand

	shall be non-plastic as determined by ATM 205

	shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-4

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type VH |
| 1 inch | 100 | - | - | - | - |
| 3/4 inch | 80-90 | 100 | - | - | 100 |
| 1/2 inch | 60-84 | 77-99 | 100 | 100 | 65-90 |
| 3/8 inch | 48-78 | 68-88 | 80-90 | 80-95 | 55-80 |
| No. 4 | 28-63 | 48-68 | 44-81 | 55-70 | 40-60 |
| No. 8 | 14-55 | 33-53 | 26-70 | 35-50 | ≤ 45 |
| No. 16 | 9-44 | 20-40 | 16-59 | 20-40 | ≤ 35 |
| No. 30 | 6-34 | 14-30 | 9-49 | 15-30 | ≤ 25 |
| No. 50 | 5-24 | 9-21 | 6-36 | 10-24 | ≤ 20 |
| No. 100 | 4-16 | 6-16 | 4-22 | 5-15 | ≤ 12 |
| No. 200 | 4-7 | 3-6 | 4-7 | 4-7 | 4-7 |

703-2.07 SELECTED MATERIAL.

Replace 1. with the following:

1.	Type A. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by ATM 204 and ATM 205.  Meet the following gradation as tested by ATM 304:

Sieve	Percent Passing by Weight

No. 4	20-55%

No. 200	0-6%, determined on the minus 3-inch portion of the sample

703-2.13 STRUCTURAL FILL. Replace Table 703-12 with the following:

TABLE 703-12

AGGREGATE GRADATION FOR STRUCTURAL FILL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3-inch | 100 |
| 3/4-inch | 75-100 |
| No. 4 | 20-55 |
| No. 200 | 0-6 |

Replace Subsection 703-2.16 with the following:

703-2.16 RECYCLED ASPHALT PAVEMENT (RAP). RAP shall be free of contamination and deleterious materials.  RAP maximum particle size shall not exceed 1.5-inch.

CR703.1-100117/CFHWY00317

SECTION 710
FENCE AND GUARDRAIL

Special Provisions

Replace Subsection 710-2.04 with the following:

710-2.04 METAL BEAM RAIL.

1.	W-Beam and Thrie Beam Guardrail.  Meet AASHTO M 180, Class A, Type II.

2.	Box-Beam Guardrail.  Meet:

a.	ASTM A500 Grade B, or

b.	ASTM A501.

Galvanize the rail per AASHTO M 111 after fabrication.

CR710.3-122217

Replace Subsection 710-2.11 with the following:

710-2.11 GUARDRAIL TERMINALS. Meet coating requirements of AASHTO M 180, Class A, Type II. Galvanize after fabrication. Provide one of the following:

1.	Parallel Terminal.

a.	Crashworthiness: NCHRP 350, or MASH Test Level 3

b.	Length: 50 feet

c.	End Offset: 0 to 2 feet (25:1 or flatter straight taper)

e.	Posts: (numbered on Manufacturer's drawing)

(1)	No. 1: Steel post in steel tube, or hinged steel post

(2)	No. 2 through 8: Steel post in steel tube

f.	Guardrail terminal widening: Standard Drawing G-20.11. End offset, X = 2 Feet.

g.	Manufacturers:

(1)	Road Systems, Inc.	Model: Sequential Kinking Terminal (SKT)

3616 Old Howard County Airport	Drawing No.: SKT-S-8US

Big Spring, Texas 79720

Ph: (432) 263-2435.

(2)	Trinity Highway Products, L.L.C.	Model: Extruder Terminal (ET-Plus)

950 West 400 South	Drawing No.: SS357

Centerville, Utah 84014

Ph: (801) 292-4461

(3)	Approved Equivalent

h.	Retroreflective Sheeting:

(1)	ASTM D4956 Type III, IV, or V (2.0 square feet, minimum)

(2)	Yellow and black bars sloping 45 degrees downward toward the traffic side

(3)	Place on the end section

3.	Buried in Backslope Terminal:	Standard Drawing G-15.

CR710.2R-012317

Add the following subsections:

710-2.12 BATTER BOARD. Furnish timber meeting the following requirements

      - Wood Batter Board. Use timber to the nominal dimensions shown in the plans.

      - Hardware. Use galvanized bolts, washers and accessories meeting AASHTO M 111 or AASHTO M 232 whichever applies.

      - Treat all timber to meet section 714.

710-2.13 SPLIT RAIL POSTS AND RAILS.  Furnish posts and rails as specified, meeting the following requirements:

- Rails. Standard rails in lengths as shown, western red cedar, 12-13” girth.

- Posts. 2-Rail post for line end and corner, western red cedar, 18” – 20” girth.

CFHWY00317

SECTION 712
MISCELLANEOUS

Special Provisions

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti-skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

2.	Performance Properties:  Add the following:

I.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace the bead table with the following:

Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads.  Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials.  Marking Material Manufacturer will certify compatibility.

(2)	Lasting retro reflectivity.

CR712.1-010109

SECTION 724
SEEDING

Special Provision

724-2.02 MATERIALS.

Add the following:

See Table 618-1 for seed species and rates of application.

CFHWY00317

SECTION 725
FERTILIZER

Special Provision

725-2.01 DESCRIPTION.

Add the following:

Use organic fertilizer amended to include commercially produced mycorrhizal fungi as supplement to fertilizer applications for planting beds and seeded areas.

725-2.01 MATERIALS.

Delete section in its entirety and replace with the following:

Furnish a mixture of organic components including naturally occurring elements such as fish meal or bat guano, that meet National Organic program (NOP) standards for organically produced agricultural products.

Use commercially available mycorrhizal fungi known to activate soils to improve plant growth.

CFHWY00317

SECTION 726
TOPSOIL

Special Provision

Delete Subsection 726-2.01, except for Table 726-1 and replace with the following:

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area.  Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project.  In this case furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse or foreign materials having an organic content of 5 percent or more, as determined by ATM 203.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the topsoil source location at least 30 calendar days before delivery of topsoil to the project from the identified location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

CR726.1-112707

Add the following Subsection:

726-2.02 BACKFILL MIX/TOPSOIL FOR PLANTING BEDS.  Furnish topsoil meeting Subsection 726-2.01 with a minimum of 15 percent and no greater than 25 percent organic matter by dry weight as determined by ATM T-6 and the following:

Grading Requirements:

Sieve Designation	Percent Passing (by Weight)

10	100

20	90

100	50

Submit to the Engineer, 10 working days prior to final placement, a soil analysis for particle size, nutrient content and organic content.  The Engineer may test the topsoil at any time to verify compliance with the topsoil analysis.  If the supplied topsoil does not meet limestone and fertilizer requirements, locate a new topsoil source of a quality required to meet the section standards.

Fertilizer Requirements:

Nitrogen	21 – 35 PPM

Phosphoric Acid	11 - 20 PPM

Potassium				76 - 150 PPM

Add the following Subsection:

726-2.03 RAIN GARDEN TOPSOIL.  For raingardens, use topsoil backfill mix amended to include 50% mason sand.

CFHWY00317

Special Provisions

Replace Section 727 with the following:

SECTION 727
SOIL STABILIZATION MATERIAL

727-2.00 GENERAL.  Free of noxious weeds, seeds, chemical printing ink, germination and growth inhibitors, herbicide residue, chlorine bleach, (except where specified: rock, metal, plastics) and other deleterious materials and not harmful to plants, animals and aquatic life.  Wood cellulose "paper" fiber, wood chips, sawdust, and hay are not permitted as stabilization materials.

727-2.01 MULCH.  Flexible blanket/covering, temporary degradable (bio/photo) form of erosion control.  Use one of the following:

Dry Erosion Control, Stabilization Products.  Hand applied or spread with mulch blower equipment.

1.	Straw.  Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life. Straw material shall be certified weed-free straw using North American Weed Management Association (NAWMA) Standards.  In-lieu of certified weed-free straw provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

2.	Shredded Bark Mulch.  Shredded bark and wood with the following characteristics:

a.	Not containing resin, tannin, or other compounds in quantities harmful to plant life.

b.	Maximum length of individual pieces is 2 inches with 75% passing through a 1 inch sieve.

c.	Will form a uniform ground cover/mat, have moisture absorption, retention, and percolation properties, not be susceptible to spreading by wind or rain providing a good growth medium.

d.	May contain up to 50% shredded wood material.

e.	Shredded wood material aged 1 year minimum prior to use.

Hydraulic Erosion Control Products (HECPs) Applied hydraulically.

A fiber mulch matrix:  biodegradable and composed of wood, straw, coconut and other fibers natural and man-made.  When applied, create a continuous, porous, absorbent high water holding, flexible blanket/mat/mulch/covering making intimate contact with, and adhering to sloped soil surface; permitting water infiltration; resists erosion and promotes rapid germination and accelerated plant growth.  The fibers may be thermally processed, and cross-linked with a hydro-colloidal or linear anionic tackifier (curing period 24-48 hours) or mechanically-bonded (no curing period).  When agitated in slurry tanks with water the fibers will become uniformly suspended, without clumping to form homogeneous slurry.

The HECPs shall be delivered premixed by the manufacturer.  The HECP will contain only the materials provided in the sealed containers from the manufacturer.  No added components are permitted after the manufacturer seals the product container, before application, during application or otherwise.  Submit documentation dated within 3 years of application, from an independent accredited laboratory as approved by the Engineer, showing that the product's testing performance meets the requirements for the slope(s) to be protected on the project, according to the National Transportation Product Evaluation Program (NTPEP), Erosion Control Technology Council (ECTC) and or the Texas DOT/Texas Transportation Institute (TTI) Laboratory.

If the HECP contains cotton or straw provide documentation that the material is certified weed free using NAWMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

The HECP shall contain a dye to facilitate placement and inspection of the material.

1.	Wood Strand, Fiber.

A blend of angular, loose, long thin wood pieces with a high length to width ratio and that are frayed.  Minimum 95% of strands between 2 inches and 10 inches, at least 50% of the length shall have a width thickness between 1/16 and 1/8 inch.  No single strand shall have a width or thickness greater than 1/2 inch.  Processed wood fiber with the following characteristics:

a.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form homogeneous slurry.

b.	Will form a blotter-like uniform ground cover on application, have moisture absorption, retention and percolation properties, the ability to cover, and hold grass seed in contact with soil, and not create a hard crust upon drying providing a good growth medium.

2.	Dried Peat Moss.  Partially decomposed fibrous or cellular stems and leaves of any of several species of Sphagnum mosses with the following characteristics:

a.	Chopped or shredded to allow distribution through normal hydraulic type seeding equipment and capable of being suspended in water to form part of a homogeneous slurry.

b.	Free from woody substances and mineral matter such as sulfur or iron and with a pH value of between 4.0 and 6.5.

c.	Furnished in an air dry condition and containing less than 35% moisture by weight.  Have a water holding capacity of not less than 800% by weight on an oven dry basis.

3.	Fiber Matrix (FM) Mulch - Types.

a.	Stabilized Mulch Matrices (SMMs)

b.	Bonded Fiber Matrices (BFMs)

c.	Mechanical Bonded Fiber Matrix (MBFM)

d.	Polymer Stabilized Fiber Matrix (PSFM)

e.	Fiber Reinforced Matrices (FRMs)

	Flexible Growth Medium (FGM)

	Extended-Term Flexible Growth Medium (ET-FGM)

727-2.02 MATTING.  Fiber mulches, mulch matrices, nets and turf reinforcement mats manufactured from wood fibers, straw, jute, coir, polyolefins, PVC, nylon and others creating dimensionally stable nets, meshes, geotextiles and blankets; creating a continuous, porous, absorbent, flexible blanket/mat/mulch/covering making intimate contact with and adhering to sloped soil surface, resisting erosion and promoting rapid germination and accelerated plant growth.

Rolled Erosion Control Products (RECPs) (Temporary Degradable and Permanent Erosion Control)

Use RECPs that bear the Quality and Date Oversight and Review (QDOR) Seal from the ECTC.  Independent test results from the NTPEP, that the mulch, when tested according to ASTM 6459 Standard Test Method for Determination of Rolled Erosion Control Products (RECP), Performance in Protecting Hillslopes from Rainfall-Induced Erosion, meets the performance requirement using the Revised Universal Soil Loss Equation (RUSL).

Functional Longevity.

1.	Temporary Degradable.

a.	Duration.

1)	Short-Term RECPs. (RECPs 3 - 12 months)

C Factor = .15 maximum

Test Soil Type = Sandy Loam

(National Resources Conservation Service (NCRS) Soil Texture Triangle)

2)	Moderate (Extended) -Term RECPs.  (RECPs 24 months)

C Factor = .05 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

3)	Long-Term RECPs.  (RECPs 36 months)

C Factor = .01 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

b.	Product types.

1)	Mulch-Control Nets (MCNs).  Planar woven natural fiber or extruded geosynthetic mesh used to anchor loose fiber matting/mulches.

2)	Erosion Control Blankets (ECBs).  Processed natural and/or polymer fibers, yarns or twines mechanically, structurally, or chemically bound together to form a continuous matrix with a minimum weight of 8 oz/yd2 and a limiting shear stress of 0.45 lb/ft2.

3)	Netless.  Fibers mechanically interlocked and/or chemically adhered together.

4)	Single-net and Double-net.  Fibers mechanically bound together by single or double netting.

5)	Open Weave Textiles (OWTs).  Fibers woven into a continuous matrix.

c.	Materials.

1)	Burlap.  Standard weave with a weight of 3.5 to 10 oz/yd2.

2)	Jute Mesh Fabric.  Cloth of a uniform, open, plain weave of undyed and unbleached single jute yarn.  Use yarn that is loosely twisted and not varying in thickness more than one-half its normal diameter.  Furnish jute mesh in rolled strips meeting the following requirements:

a)	Width:  45 to 48 inches,  1 inch

b)	78 warp-ends per width of cloth (minimum)

c)	41 weft-ends per yard (minimum)

d)	Weight:  20 ounces per linear yard,  5%

3)	Woven Paper or Sisal Mesh Netting.  Woven from twisted yarns available in rolls 45 to 48 inches wide.  Mesh may vary from closed to open weave, ranging from 1/8 to 1/4 inch openings.  Shrinkage after wetting may not exceed 20% of the surface area.

4)	Knitted Straw Mat.  Commercially manufactured ECB.  Use photodegradable netting and biodegradable thread.  Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life.  ECB may contain coconut or fiber to reinforce the straw.  Straw material shall be certified weed-free straw using NAWMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

5)	Woven/Curled Wood blanket.  Machine produced mat of curled wood shavings with a minimum of 80% 6-inch or longer fibers, with consistent thickness and the fibers evenly distributed over the entire area of the blanket.  Smolder resistant without the use of chemical additives.  Cover the top side of the blanket with biodegradable extruded plastic mesh.

6)	Coconut (Coir Fiber).  Machine produced mat, ECB of consistent thickness and coir fiber evenly distributed over the area of the mat.  Use bio/photo degradable netting and thread.

CR727-050812/CFHWY00317

2.	Permanent.

a.	Product Types and Materials.

1)	Turf Reinforcement Mats (TRMs).  A rolled erosion control product composed of non-degradable synthetic fibers, filaments, nets, wire mesh, and/or other elements, processed into a permanent, three-dimensional matrix of sufficient thickness with a minimum weight of 8 oz/yd2 and a minimum limiting shear stress of 1.5 lb/ft2.  TRMs (may be supplemented with degradable components) shall impart immediate erosion protection, enhance vegetation establishment during and after maturation and permanent vegetation reinforcement providing long-term functionality.  TRMs should be rated for slope gradients up to 1 horizontal / 1 vertical (1H:1V).

CR727/CFHWY00317

727-2.03 SEDIMENT RETENTION FIBER ROLLS (SRFRs).  Fiber rolls also referred to as wattles.  Manufacture of photodegradable or biodegradable fabric netting without preservative treatment, evenly woven, free of crusted material, cuts, and tears.  Manufacture stakes of photodegradable or biodegradable material (wood stakes, except as approved by the Engineer).

1.	Filter Sock (Wattle)

a.	Fabric netting.

b.	Filled with wood fiber, straw, flax, rice, coconut fiber material.

c.	Minimum diameter 5 inches.

2.	Compost Sock.

a.	Extra Heavy weight fabric netting with a minimum strand width of 5 mils.

b.	Filled with coarse compost.

c.	Minimum diameter 8 inches.

3.	Coir Log.

a.	Woven wrap bristle coir twine netting.

b.	Filled with 100% coconut (coir) fiber uniformly compacted.

c.	Segments maximum length 20 foot, diameter as suited to the application and a density of 7 lbs/pcf or greater.

d.	Coir twine strength equal to 80 lb minimum weaved to a 2 inch x 2 inch opening pattern.

e.	Ties made of hemp rope by 1/4 inch diameter.

727-2.04 COMPOST.  Suitable for serving as a soil amendment or an erosion control material.  Sanitized, mature compost meeting local, state, and Federal quality requirements tested and certified by the U.S. Composting Council (USCC) under the Seal of Testing Assurance (STA) Program.  Biosolids compost must meet the Standards for Class A biosolids outlined in 40 Code of Federal Regulations (CFR) Part 503.  Additionally, meet the requirements of the AASHTO specifications:

1.	Compost Blankets.  Standard Practice for Compost for Erosion/Sediment Control (Compost Blankets) R 52.

2.	Compost Filter Berms and Filter Socks.  Standard Practice for Compost for Erosion/Sediment Control (Filter Berms and Filter socks) R 51.

727-2.05 TACKIFIER.  Tackifier, viscous overspray, generally composed of dry powered vegetable gums derived from guar gum, psyllium and sodium alginase; asphaltic emulsions; petroleum distillates; co-polymer emulsions; and lignosulfonates and used to anchor soil, compost, seed, the mulch fibers to one another, and the ground.  Contain no growth or germination inhibiting materials nor significantly reduce infiltration rates.  Tackifier shall hydrate in water and readily blend with other slurry material.  Tackifier options include:

1.	Type A.  Organic tackifier with certification of plant sources; or

2.	Type B.  Synthetic tackifier with certification confirming product is not harmful to plants, animals, or aquatic life.

727-2.06 POLYACRYLAMIDE (PAM).  Use as a tie-down for soil, compost, seed and as a flocculent. Polyacrylamide (PAM) products shall meet the requirements of American National Standards Institute (ANSI)/National Sanitation Foundation International (NSF) Standard 60 for drinking water treatment, be anionic (not cationic), linear and not cross-linked with an average molecular weight greater than 5 Mg/mole, minimum 30 percent charge density; contain at least 80% active ingredients and a moisture content not exceeding 10% by weight.

Deliver PAM in a dry granular powder or liquid form.

727-2.07 GEOTEXTILE-ENCASED CHECK DAM AND SEDIMENT BARRIER.  Urethane foam core encased in geotextile material (silt fence material Section 633), minimum 8 inches height by minimum base width of 16 inches by minimum 7 foot length.  Overhang the geotextile 6 inch minimum each end with apron type ties by 24 inches each side of the foam core.

727-2.08 SANDBAG.

1.	Sandbag Sack Fabric. Fabric shall be a nonwoven, needle punched design meeting the Minimum Average Roll Values (MARV) verified in accordance with ASTM D4759.

2.	Seam Thread.  Similar durability to the sandbag sack fabric.

3.	Sandbag Fill Material.

a.	Selected Material	703-2.07	Type B

4.	Cinch Ties.  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

727-2.09 MANUFACTURED INLET PROTECTION SYSTEM.

1.	Manufacturers:

a.	Ultra Tech International – Ultra-DrainGuard

b.	Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

c.	Enpac - Catch Basin Insert, Oil and Sediment or

d.	Approved equal.

727-2.10 CLEAR PLASTIC COVERING.  A clear plastic covering meeting the requirements of the National Institute of Standards and Technology (NIST) voluntary Product Standard PS 17 - 69 for polyethylene sheeting having a minimum thickness of 6 mils.

727-2.11 STAPLES.  U-shaped staples for anchoring matting, approximately 6 inches long and 1 inch wide.  Machine-made:  No. 11 gage or heavier steel wire.  Hand-made:  12-inch lengths of No. 9 gage or heavier steel wire.

CR727-050812/CFHWY00317

Special Provision

Replace Section 729 with the following:

SECTION 729
GEOSYNTHETICS

729-2.01 GEOTEXTILE FOR SUBSURFACE DRAINAGE, SEPARATION, STABILIZATION, EROSION CONTROL AND EMBANKMENT REINFORCEMENT.

1.	Subsurface Drainage. Meet AASHTO M 288 for Subsurface Drainage, except provide a minimum permittivity of 0.5 sec-1, and meet Class 2 Strength Property Requirements.

2.	Separation. Meet AASHTO M 288 for Separation, except provide a minimum permittivity of 0.50 sec-1, and meet Class 3 Strength Property Requirements.

3.	Stabilization. Meet AASHTO M 288 for Stabilization, except provide a minimum permittivity of 0.50 sec-1, and meet Class 1 Strength Property Requirements.

4.	Erosion Control. Meets AASHTO M 288 for Permanent Erosion Control and meet Class 1 Strength Property Requirements.

5.	Reinforcement. Meet the requirements in Table 729-1 for Type 1 or Type 2.

Package, label, handle and store geotextile materials according to ASTM D 4873.

TABLE 729-1

GEOTEXTILE REINFORCEMENT PROPERTIES

| Property | Test Method | Units | Requirement a |  |
| --- | --- | --- | --- | --- |
|  |  |  | Type 1 | Type 2 |
| Grab Tensile | ASTM D 4632 | lb. | 200/200 | 400/400 |
| Grab Elongation | ASTM D 4632 | % (MD) | 10 | 10 |
| Wide Width Tensile | ASTM D 4595 | lb./in. (ultimate) | 200/200 | 400/400 |
| Wide Width Tensile | ASTM D 4595 | lb./in. (@ 5% strain) | 100/100 | 200/200 |
| Seam Breaking Strength | ASTM D 4632 | lb./in. | 180 | 360 |
| Puncture | ASTM D 6241 | lb. | 500 | 1500 |
| Trapezoidal Tear | ASTM D 4533 | lb. | 100 | 150 |
| AOS | ASTM D 4751 | U.S. sieve size | #30 b | #30 b |
| Permittivity | ASTM D 4491 | sec-1 | 0.20 | 0.20 |
| Flow Rate | ASTM D 4491 | gal./min./ft2 | 10 | 10 |

a.	Minimum Average Roll Values (MARV) in machine-direction (MD) and cross-machine direction (XD) unless otherwise specified.

b.	Maximum average roll value

729-2.02 RESERVED.

729-2.03 PAVING FABRIC. Meet AASHTO M 288 for Paving Fabric.

729-2.04 SILT FENCE. Meet AASHTO M 288 for Temporary Silt Fence.

729-2.05 GEOGRID FOR EMBANKMENT AND ROADWAY STABILIZATION AND REINFORCEMENT. Provide geogrid consisting of a regular network of connected polymer tensile elements with aperture geometry sufficient to provide significant mechanical interlock with the surrounding material.  Provide dimensionally stable geogrid that is able to retain its geometry during construction.  Provide geogrid structure that resists ultraviolet degradation and all forms of chemical and biological degradation encountered in the material in which it is buried.

Package, label, handle, and store geogrid material according to ASTM D 4873.

1.	Stabilization. Provide geogrid that meets the survivability requirements in Table 729-2 and meets the physical requirements in Table 729-3.

2.	Reinforcement. Provide geogrid that meets the survivability requirements in Table 729-2.

TABLE 729-2

GEOGRID SURVIVABILITY REQUIREMENTS

| Property | Test Method | Units | Requirement |  |
| --- | --- | --- | --- | --- |
|  |  |  | Class 1 | Class 2 |
| Ultimate Multi –Rib Tensile Strength a | ASTM D 6637 | lb./ft. | 1230 | 820 |
| Junction Strength a | ASTM D 7737 | lb. | 25 | 25 |
| Ultraviolet Stability (Retained Strength) | ASTM D 4355 | % | 50% after 500 hours of exposure |  |

a.	Minimum Average Roll Values (MARV) in any rib direction.

TABLE 729-3

Geogrid Physical Requirements

| Property | Test Method | Units | Requirement |
| --- | --- | --- | --- |
| 2% Tensile Strength a | ASTM D 6637 | lb./ft. |  400 |
| 5% Tensile Strength a | ASTM D 6637 | lb./ft. |  800 |
| Percent Open Area | COE, CW-02215 | % | 50 – 80 |
| Aperture Size b | Direct measure | in. | 0.5 – 3.0 |

a.	Minimum Average Roll Values (MARV) in machine-direction (MD) and cross-machine direction (XD).

b.	Measured as the spacing between parallel ribs.

CR729-050117

SECTION 730
SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS.

Add No. 7:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to ASTM A500, Grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

CR730.1-062204

Replace Subsection 730-2.05 with the following:

730-2.05 FLEXIBLE DELINEATOR POSTS.  Durable fiberglass composite, polymer, or plastic material meeting the dimensions and colors shown on the Plans. Resistant to ultraviolet light, ozone and hydrocarbon damage and remain flexible at a temperature of minus 40 °F. Provide posts with reflectors that are capable of self-erecting and remaining serviceable after 5 head-on impacts at 55 mph and 10 impacts at 35 mph with an automobile at an air temperature of plus 40 °F.

Terminal Markers - Flexible (marker).  The marker includes the pole/post/rod (pole), reflective and retroreflective sheeting and mounting hardware.

Provide durable markers: resistant to impact from (snow and vehicle), vandals, ultraviolet light, moisture, ozone, and hydrocarbons.

When the pole is loaded, the marker shall bend/flex, remain flexible and oriented as installed continuing to function as designed without permanent displacement along the length of the member.  Provide the flexibility in the primary vertical element, a connecting device between the vertical element and connection to the support member (spring or other) or a combination.

Provide a connection sufficient to transfer the loads from the pole to the supporting member without reducing the strength, flexibility, or durability of either.  The connection shall not negatively influence the performance of the guardrail.  Provide approval of the connection from the marker manufacturer and support member manufacturer (if proprietary).

	Design Loads:

	Impact load from snow thrown by snowplows

Ø	Weight of snow covering the pole (snow thrown from snowplows)

Ø	Wind loads (100 mph, 3 sec gust)

·	Service Temperature Range:	-40˚ F to +140˚ F.

·	Pole:

1.	Material:

Ø	Steel, or

Ø	Stainless Steel, or

Ø	Other Poles:

(a)	Continuous glass fiber and marble reinforced thermosetting composite, or

(b)	Engineered plastic alloy, or

(c)	Fiberglass Reinforced Polyester (FRP)

(d)	High-Impact Polyolefins

2.	Dimensions

Ø	Top of Pole:  60 inches to 84 inches above top of guardrail

Ø	Width/Diameter:  minimum = 1 1/4 inches, maximum = 2 inches (steel/stainless steel not be greater than 5/8 inch diameter)

Ø	Thickness:  as required by design

3.	Visibility:

Ø	Daytime: Pole - color orange

a.	Steel and Stainless Steel Poles:  Applied permanent finish.

b.	Other Poles:  Color pigment ultraviolet stabilized and solid through the cross section from end to end.

Ø	Nighttime:  Added retroreflective sheeting - color white

a.	Approximately 12 square inches visible from the traveled way before and after the marker.  Applied to a flag attached to the pole or as banding applied directly to the pole.  (A flag is required when using steel/stainless steel poles.)

b.	Place top edge of flag/banding 1 inch from top of pole.

(1)	Flag:  Single retroreflective sheet each face

(2)	Banding:  Two bands completely around marker, 4 inches between bands

·	Hardware and Fasteners:

Ø	Steel, and/or

Ø	Stainless Steel, or

Ø	Aluminum alloy (hardware only)

Manufacturers of flexible markers (snowpoles):

| Manufacturer | Model | Type | Contact |
| --- | --- | --- | --- |
| Nordic Fiberglass, Inc. | FF2 | Steel Pole w/ Flag | Ph: (218) 745-5095 |
| PEXCO | Model 3639 | High-Impact Polyolefins | Ph: (404) 564-8560 |
| New Century Northwest, LLC | NCN2549 | Engineered Plastic Alloy | Ph: (541) 485-5566 |
| Carsonite Composites, LLC | SNFB | Continuous glass fiber and marble reinforced thermosetting composite | Ph: (800) 648-7916 |

Submit manufacturer's specifications to the Engineer for review and approval before ordering terminal markers.

CR730.2-122217

Special Provision

Replace Section 740 with:

SECTION 740
SIGNALS AND LIGHTING MATERIALS

740-2.01 GENERAL.  Use electrical materials, devices, fittings, and hardware that conform to applicable NEMA and ANSI standards.

Use electrical products that are Third Party Labeled or Listed (by an approved independent electrical testing laboratory such as UL, ETL, CSA, etc.), unless otherwise indicated on the Materials Certification List (MCL).

Ensure that all material and workmanship, as determined by the Department, conform to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the authority having jurisdiction.

740-2.02 SIGNAL AND LIGHTING POLES.

1.	Design.  Design and fabricate highway lighting structures to conform to the 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions and the highway lighting sheets in the Plans.  Use a wind speed of 100 mph with a gust factor of 1.3.  Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 ft above the pole base.

Design and fabricate traffic signal structures to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions and Central Region Traffic Signal Details.  Design must meet Fatigue Category III, with galloping using a basic wind speed of 100 mph and Central Region standard loads.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations.  Submit the stamped drawings and calculations for each pole to the Engineer for approval.  Design for the complete-in-place structure including the supported hardware.

a.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole and mast arm, including:  design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide design wind speed and the details for building the poles and mast arms, including:  materials specifications, slip fit joint dimensions, pole component dimensions, welds that will be made, and the welding inspection that will be done.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

2.	Fabrication.  Fabricate signal and lighting structures from tapered steel tubes with a round or 16 sided cross section.  Orient handholes located near the base of poles to face downstream of traffic flow.

Provide traffic signal poles, lighting poles, and signal mast arms in lengths evenly divisible by 5 feet.

Furnish poles and mast arms up to 40 feet long in one piece.  Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice.  For slip type joints, provide the minimum overlap specified in the Plans.  In mast arms, locate these splices at least one foot away from the Plan location of signal heads and signs.  In signal poles, locate the edge of the female section at least 6 inches above the top of the signal mast arm connection.

Fabricate tubes with walls up to 1/2 inch thick from the prequalified base metals listed in AWS D1.1.  Fabricate elements greater than 1/2 inch thick from steel that conforms to AASHTO M270 and meets the Fracture Critical Impact Test requirements for Zone 3.  The Department will not accept structures that use laminated steel elements.

Fabricate the cross section of each tube from no more than 2 pieces of steel.  When using 2 pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from two inch nominal schedule 40 pipe that conform to ASTM A 53 Grade B.

Fabricate breakaway signal poles in accordance with the Pole Sheet in the Plans. Fabricate signal poles 10 to 16 feet long from 7 gage (US Standard) sheet steel.  Fabricate each post with a minimum inside diameter at the base plate as shown in the Plans.  Use 4 inch diameter by 4 inch Schedule 40, ASTM A53, Grade B pipe as a post-top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms.  To add lift points, weld them to the tube opposite the longitudinal seam weld on the outside of female segments and on the inside of male segments. Before shipment, remove lift points added to the outside of the tubes, grind the area smooth with the base metal, and hot stick repair the finish according to Subsection 660-3.01.8.a.  Lift points added to the inside of tubes in place may be left in place.

Hot-dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications. Galvanizing kettles will be large enough to completely submerge each element, the mast arm, and the pole.  Submerge the complete/whole element in the galvanizing process.  An element galvanized in sections will not be accepted.  Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove all excess zinc from all drip lines and points and the surfaces of all tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

a.	Not fabricated according to these specifications or the approved shop drawings,

b.	Bowed with sweeps exceeding 1 inch throughout the length of the pole, mast arm, or segment, if furnishing a 2 piece pole or mast arm,

c.	Out of round.  Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

Fabricate pile cap adapters from Grade X42 steel line pipe that conforms to API 5L and from steel plate that conforms to ASTM A 709 Grade 50.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Fabricate the anchor plate to match the base plate of the lighting standard.

3.	Welding.  Perform welding to conform to Subsection 504-3.01.8. Welding and the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions, the Central Region Traffic Signal Details, and the following:

a.	Make welds continuous.  Grind exposed welds flush with the base metal at slip fit joints for the length of the slip fit joint plus one half the diameter of the female section.

b.	On steels 5/16 of an inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

c.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.  In steels less than 1/8 inch thick, complete the tests according to AWS D1.1.

d.	Only visually inspect welds made on luminaire mast arms.

4.	Anchor Rods & Bolts.  Furnish 2 inch diameter (nominal) anchor rods for signal poles that meet ASTM F1554 Grade 105, are 96 inch minimum length and conform to Supplemental Requirements; S2, Permanent Manufacturer’s Identification, S3, Permanent Grade Identification and S-5 Charpy Impact Requirements.  Hot dip galvanize according to AASHTO M232.  Use nuts that conform to AASHTO Specification M292 of the grade, surface finish, and style for 2 inch diameter anchor rods.  Washers shall conform to AASHTO M293.

5.	Miscellaneous.  Finish the edges of poles and mast arms to conform to the following requirements.  Before hot dip galvanizing, neatly round the following features to the radius specified.

a.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both the entrance and exit edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus one half the diameter of the female section grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces.

Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1.  The measurements shown are for illustration purposes only.  Use tags large enough to include required information using 1/4 inch high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text.  Secure the tags with two 1/8 inch blind rivets at the base of poles and the underside of mast arms.  If furnishing a two piece signal mast arm with slip type joint, mark both pieces with the same message.  Provide the holes for the blind rivets before galvanizing.

TABLE 740-1

POLE MARKINGS

Note: Italic type indicates additional Tag Markings if poles have 2 luminaire or 2 signal mast arms.

| POLES (Including Mast Arms ) | MEASUREMENTS | TAG MARKINGS |
| --- | --- | --- |
| Signal Poles |  |  |
| Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| Pole height | 36 ft. | PH 36 |
| Intersection number (if more than one) -pole number |  | 1 - P 4 |
| Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| Mast arm length | 40 ft. | SMA 40 |
| Intersection number (if more than one) -pole number |  | 1 - P 4 |
| Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| Mast arm length | 18 ft. | LMA 18 |
| Pole number (if unique arm design) |  | P 4 |

740-2.03 WOOD POLES.  Use wood poles for service or temporary installations of the class shown on the Plans or as specified in the Special Provisions.

Use 45-foot poles, except for service poles use 25-foot poles.

Use mastarms and tie rods for wood pole installations that conform to Subsection 740-2.02, and to the details shown on the Plans. Provide each mastarm with an insulated wire inlet and wood pole-mounting bracket for mastarm and tie rod crossarm.

Use structural timber meeting Section 713. Do not use poles that have more than 180 degrees twist in grain over the full length. Ensure that the sweep is no more than 4 inches. Pressure-treat wood poles, that are not to be painted, after fabrication. Meet Section 714.

740-2.04 reserved.

740-2.05 CONDUCTORS.  Use conductor sizes based on the American Wire Gage (AWG). Use sizes that conform to the Plans or, when not shown, to this subsection.

Use insulated conductors made of uncoated, stranded copper that conforms to the specifications of ASTM B8. Use grounding conductors that are bare copper of the gage required by the NEC. They may be stranded, solid, or braided.

Provide the following markings on the outer coverings of conductors and cables on intervals of 2 feet or less: manufacturer, the number of conductors or pairs in cables, conductor size, 600V, the conductor or cable type and environmental conditions for which the conductor or cables are listed, and the symbol of an approved independent testing laboratory.

Use conductors meeting the referenced specifications for the following purposes:

- Power Conductors. For individual conductors, install general-purpose building wire manufactured according to UL Standard 44, and NEMA No. WC7. Furnish conductors insulated with cross-linked polyethylene listed as type XHHW-2 and rated for 600 volts AC operation.

TABLE 740-2

CONDUCTOR TERMINATION TABLE

| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG. NO. | BAND LEGEND |
| --- | --- | --- | --- | --- |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red Arrow | Red | 14 | Head No. |
|  | Vehicle Yellow Arrow | Orange |  |  |
|  | Vehicle Green Arrow | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Vehicle Yellow Arrow | Black |  |  |
|  | Vehicle Green Arrow | Blue |  |  |

TABLE 740-2

CONDUCTOR TERMINATION TABLE

(Continued)

| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG NO. | BAND LEGEND |
| --- | --- | --- | --- | --- |
| 3 | Flashing Beacon | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Per Manufacturer Installation Instructions | Orange | 20 | "PRE" |
|  |  | Blue |  |  |
|  |  | Yellow |  |  |
| 3 | Preemption Confirmation | Black | 14 | "PRECON" |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Highway Luminaire | Black | 8 or 6 | Circuit No. |
|  | Highway Luminaire | Red |  | Circuit No. |
|  | Highway Luminaire Spare | White |  |  |
| 5 | Photo Electric Control | Black | 14 | PEC |
|  | Load to Contactor | Red |  |  |
|  | Neutral | White |  |  |
|  | Spare | Orange |  |  |
|  | Spare | Green |  |  |
| 3 | Service to Controller | Black | 6 or 4 | "SIG" |
|  | Neutral | White |  | No Band |
|  | Spare | Red |  | No Band |
| 3 | Sign Luminaire | Black | 8 | SIGN |
|  | Sign Luminaire | Red |  | SIGN |
|  | Sign Spare | White |  |  |
| 6 | DC Power | Red | 20 | +DC |
|  | DC Ground | Black |  | -DC |
|  | 485 data bus | Orange/Wh |  | +485 |
|  | 485 data bus | Orange |  | -485 |
|  | 485 control bridge | Blue/Wh |  | +485 |
|  | 485 control bridge | Blue |  | -485 |

Use size 10 AWG wire for illumination tap conductors. In an electrolier, the illumination tap conductors run from the fused disconnect kit to the ballast in the luminaire. Furnish conductors with black, red, or white colored insulation as required to identify the two phase and neutral conductors, respectively.

If conductors in controller cabinets carry the full signal load circuit, use size 10 AWG or larger conductors. Use orange colored conductors from the flash transfer relay to program emergency flashing operation.

- Illumination Cables.  For cables that consist of three size 6 or 8 AWG conductors, furnish power cables that feature three conductors, each insulated with cross-linked polyethylene, and a black, low density, high molecular weight polyethylene jacket. Use insulated conductors listed as type XHHW-2. Furnish these cables with one black, one white, and one red colored conductor and no grounding conductor. Use cables rated for 600 volts AC operation.

Use insulated conductors meeting UL Standard 44. The jacket must also meet NEMA No. WC70.

- Power Cables.  For cables that consist of three size 4 AWG and larger conductors, furnish tray cables that feature three conductors, each insulated with cross-linked polyethylene that meets the requirements of XHHW-2, and a PVC jacket. Furnish these cables without an integral grounding conductor. Use cables manufactured according to UL Standard 1277, ICEA S-95-658, and NEMA No. WC70. Provide cables listed for direct burial and resistance to sunlight and rated for 600 volts AC operation.

Furnish these cables with black conductor insulation with one printed number (1, 2, or 3) identifying each conductor.

- Control Cables.  Wire with signal cable meeting IMSA 20-1 all vehicular signal heads, pedestrian signal heads, pedestrian push button detectors, flashing beacons, hardwired local coordination and preemption devices, and photoelectric controls.

- Detector Loops.  Use No. 14 AWG conductors for detector inductive loops that meet IMSA Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans or specified in the Special Provisions.

- Loop Lead-In Cables.  Unless otherwise specified, use a tray cable that conforms to the following specifications to connect the loop detectors to the terminal blocks in the controller cabinet. Furnish this cable, also known as Snyder Cable; manufactured according to UL Standard 1277. Supply these cables third party certified as Type TC and certified for use in underground conduit or as an aerial cable supported by a messenger, and rated for 600 volts AC operation.

Use size 18 AWG, 16 strand, tinned copper conductors per ASTM B33 insulated with wet-rated, cross-linked polyethylene similar to XHHW. Furnish conductors with insulation colors that match Table 660-1 twisted into pairs.

Provide each twisted pair with an overall aluminum foil coated mylar shield that provides 100% coverage and a 20 AWG tinned copper drain wire that is in constant contact with the foil side of the shield. Apply a tight fitting polyvinyl chloride jacket over the conductor assembly.

Only use the following loop lead-in cable, also known as shielded data cable, to rewire existing traffic signals when specified. Use cables that consist of 7 twisted pairs that consist of stranded, size 18 AWG tinned copper wire and polyethylene or polypropylene insulation. Furnish each pair covered with an aluminum foil shield, stranded copper drain wire, and an overall PVC or PE jacket. Use cable rated for 300 volts and whose colored pairs match those specified in Table 660-1.

- Telemetry Cable.  Use interconnect cable that consists of solid copper conductors of the number of pairs called for in the Plans meeting the requirements of Rural Utilities Service (formerly the Rural Electrification Administration (REA) specification PE-39 for filled telephone cables. The shield may be either copper or aluminum.

TABLE 740-3

INTERCONNECT TERMINATION TABLE

| TELEMETRY CABLE: Type PE-39, No. 19 AWG, Solid Copper, as noted on the Plans or in the Special Provisions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Pair No. | Tip | Ring | Pair No. | Tip | Ring |
| 1 | White | Blue | 14 | Black | Brown |
| 2 | White | Orange | 15 | Black | Slate |
| 3 | White | Green | 16 | Yellow | Blue |
| 4 | White | Brown | 17 | Yellow | Orange |
| 5 | White | Slate | 18 | Yellow | Green |
| 6 | Red | Blue | 19 | Yellow | Brown |
| 7 | Red | Orange | 20 | Yellow | Slate |
| 8 | Red | Green | 21 | Violet | Blue |
| 9 | Red | Brown | 22 | Violet | Orange |
| 10 | Red | Slate | 23 | Violet | Green |
| 11 | Black | Blue | 24 | Violet | Brown |
| 12 | Black | Orange | 25 | Violet | Slate |
| 13 | Black | Green |  |  |  |

| Hardwire CableS: IMSA Type 20-1, (2) 7 conductor No. 14 AWG |  |  |  |
| --- | --- | --- | --- |
| Cable No. 1 |  | Cable No. 2 |  |
| Circuit | Color | Circuit | Color |
| Cycle 2 | Green | Offset 1 | Green |
| Cycle 3 | Orange | Offset 2 | Orange |
| Cycle 4 | Red | Offset 3 | Red |
| Free | Blue | Split 2 | Blue |
| Common | White | Common | White |
| Spare | Black | Spare | Black |
| Spare | White/Black | Spare | White/Black |

740-2.06 ELECTRICAL CONDUIT AND FITTINGS.  Unless specified otherwise, use rigid metal conduit and fittings for raceways.  Furnish galvanized rigid type conduit and elbows conforming to UL Standard 6 and are manufactured of mild steel according to ANSI C80.1.  Furnish third party certified fittings designed for rigid metal conduit.

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL Standard 651.  Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL Standard 651 B and NEMA TC-7-2000.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle.  Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline.  The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws.  For loop detectors, furnish Type X bodies and, for photoelectric control installation, furnish Types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it.  The movements include:  axial expansion or contraction to 3/4 inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to 3/4 inch.  The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

740-2.07 FUSED SPLICE CONNECTORS.  Use fused, quick disconnect, splice connector that is weather tight and has two halves: a single-unit line side socket and a load-side plug. Use fuses that are 10 ampere, midget (13/32” x 1-1/2“) ferrule type with a fast acting current limiting (KTK type) design.

740-2.08 SIGN SWITCHES.  Provide a NEMA 3R non-fused disconnect switch as shown on the Plans for each sign illumination installation.

740-2.09 CONTROLLER ASSEMBLIES.  Provide solid state, traffic controller assemblies having level 2 conformance to NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements as defined in NTCIP1202.  Traffic Controller Assemblies must meet or exceed the Environmental Requirements of Section 2 of the NEMA TS2-2003 V02.06 document. The Original Equipment Manufacturer (OEM) and its manufacturing and testing facilities shall be ISO 9001:2000 certified for processes involving the Traffic Controller Assemblies.

Use traffic control equipment that is compatible with the existing traffic signal monitoring system.  Compatibility must be 100% at the cabinet level to include inputs, outputs, telemetry protocol, and block upload and download of RAM data.

In addition, features of the existing local controllers and controller modules must be functionally duplicated to meet or exceed the performance of the existing equipment.

The existing local controller cabinets at other intersections include the following equipment:

- Econolite ASC/3-2100

- Econolite Cobalt ATC Touch 2100

Use LED indicators for all electronic devices covered under Subsections 740-2.09 through 740-2.13.

740-2.10 CONTROLLER UNIT.

Actuated Controller Unit (CU).

Provide solid state, Type A2N Actuated Controller Units (CU) meeting the requirements of Section 3 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements.

- The CU must meet the referenced National Transportation Communications for ITS Protocol (NTCIP) and comply with publication TS 3.2 the Simple Transportation Management Framework, and shall meet the requirements for Conformance Level 2

- The software shall comply with NEMA TS 3.3, the Class B Profile, and shall include both an EIA/TIA 232-E and an FSK modem interface for NTCIP based communications.

- The CU shall implement conformance groups and optional object groups as defined in NEMA TS 3.4 and TS 3.5 for A2N level 2.

- Provide controllers with display heaters or enhancements to improve viewing in temperatures below 0 F.

- Provide controllers having an interface compatible with SYNCRO-7 traffic modeling software.

Furnish Econolite Cobalt ATC Touch 2100 controller unit with the following optional features:

- User interface Advanced Display with graphics and touch-screen

- TS2 Type I connector

- Data Key 3.3V, 32MB

740-2.11 CONTROLLER CABINET.  Provide a controller cabinet that meets the requirements of NEMA Standard TS 2-2003 V02.06 Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2), Section 5 Terminals and Facilities and Section 7 Cabinets.

- Standard Features. Supply the following standard features:

  - Materials

Unless otherwise designated in the Plans, provide cabinets constructed of sheet Aluminum.

  - Cabinet Dimensions

Unless otherwise designated in the Plans, provide a size 7 cabinet as defined in NEMA TS-2 Table 7-1.

  - Doors

    - Provide doors meeting the requirements of NEMA TS-2 Section 7.5.  The lock must accept a Best CX series core that will be installed by the Department after the Contract is complete.

    - Provide a Police Compartment meeting the requirements of NEMA TS-2 Section 7.5.7.  The Police Compartment shall house the following switches:

      - "flash/automatic" switches that when placed in the "flash" position causes the intersection displays to go into the flashing mode.  When placed in the "automatic" position, the signal system must resume normal operation.

      - "signals on/off" switch that when placed in the "off" position removes power from the signal bus.  Do not allow power on the bus when either "automatic" or "flash" operation is selected by any means.

    - Permanently label switches in the Police Compartment.

  - Shelves

Provide shelves meeting the requirements of NEMA TS-2 Section 7.6. Provide additional laptop computer shelf mounted approximately 30” above cabinet floor.  The laptop shelf must accommodate a standard 17" computer and be retractable below one of the cabinets’ shelves.

  - Finish and Preparation

Unless otherwise designated in the Plans, provide unpainted Aluminum Cabinets with a "natural" brushed appearance.

  - Cabinet Mounting

    - Provide cabinet mounting features as defined NEMA TS-2 Section 7.8.

    - The cabinet manufacturer is responsible for providing a cabinet that will mount without modification on the foundation detailed in Alaska Department of Transportation Central Region, Regional Detail, Controller Cabinet Foundation.

  - Cabinet Ventilation

Furnish a cabinet that fully meets the requirements of NEMA TS-2 Section 7.9 and the following:

    - Furnish the fan and cabinet vent with internally mounted metal covers that are fabricated to close off the flow of air during winter operation.

    - Equip the cabinet with a selectable, 750/1500 watt cabinet heating device.  The heating device must have a remote air sensing thermostat. The contacts must be rated 20 amps, 120 volts, 60 hertz.

      - Construct the thermostat so that contacts close on descending temperature and are adjustable between 0 and 30 °F ±5 °F. The contacts must open on rising temperatures of 15 °F above the closing temperature.  The adjustment must have an indicating pointer.

      - Connect the thermostat in series with an electrical resistance heater and blower fan.  The blower fan must be rated for continuous duty.  The heater and fan must be connected in parallel and rated 120 volts, 60 Hertz.  Mount the unit in the vertical position on the cabinet door beneath the auxiliary "goose neck" cabinet light.  The thermostat shall be mounted immediately to the left of the heating device on the cabinet door.

      - Do not block the air intake or outlet.  Provide the unit with a SPST manual override switch that bypasses the thermostat to enable the fan and heater to operate at warmer temperatures.

  - Auxiliary Cabinet Equipment

    - Mount a hooded incandescent light fixture with a Type A base on a 15 inch flexible "goose neck" from the cabinet door.  Use a fixture UL rated to accommodate a 2700 k LED lamp, 450 Lumen output with an integral "ON-OFF" rotary switch mounted on the lamp hood.  Mount a LED strip lighting fixture on the inside of the cabinet near the top front edge and under the controller shelf.  Use a fixture rated to accommodate 4000K LED operated from a high power factor UL or ETL listed ballast.  The lamp must be included.  The lighting fixture "ON-Off" switch must be a toggle switch mounted on an inside control panel.  Include in the circuit a door actuated switch that turns the light ON when the door is open and OFF when the door is closed.

    - Provide three (3) paper sets of complete and accurate cabinet drawings with delivery of each cabinet.  Make cabinet drawings available electronically in AK DOT’s current version of AutoCAD and deliver with paper set, along with a “.pdf” copy.

    - Provide two (2) paper set of manuals for the controller, Malfunction Management Unit and vehicle detector amplifiers with each cabinet. Make said manuals available in electronic Adobe ".pdf" format and deliver with paper set.

  - Cabinet Wiring

Neatly arrange the wiring within controller cabinets to conform to the requirements of Subsections 660-3.05 and 740-2.05.  Furnish controller cabinets wired to accommodate

    - Configuration #4 in Table 5-2 of the NEMA Standards Publications No. TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP requirements with two each Type 2 detector racks.

      - Equip the cabinet with required control and auxiliary equipment connecting cables to operate the phases and detection indicated on the Plans, including future use.

      - Size wiring, switches, surge protectors, flash relays, and flashers to handle the necessary amperage required under full cabinet use.  Use orange colored wires to run from the flash transfer relay used for emergency flash programming.

      - Wire the cabinet to accommodate 6 unique preempt sequences as defined by NEMA TS-2 Section 3.7 and 2 auxiliary preempt sequences.  Configure each detector rack to accommodate 4 unique sequences.

  - Field Terminal Blocks

Provide Terminals and Facilities meeting the requirements of NEMA TS-2 Section 5, Configuration #4 (Table 5-2) and the following:

    - Provide 2 or more insulated terminal blocks to terminate field conductors.  Provide each block with 12 poles with 10-32 screw type terminals.  Use a terminal block that is a barrier type with removable shorting bars in each of the 12 positions and with integral type marking strips.  Terminate conductors to a terminal block.

    - Terminate conductors from the controller unit in ring type terminal lugs or solder them to a through panel solder lug on the rear side of the terminal.  Terminate other conductors in spade type terminal lugs.

    - Do not bring more than 3 conductors to any one terminal.  Two flat metal jumpers, straight or U shaped, may also be placed under a terminal screw.  Fully engage at least 2 full threads of terminal screws when the screw is tightened.  Do not extend live parts beyond the barrier.

    - Terminals must be provided to terminate a future 25 pair interconnect cable with each conductor terminated on individual terminals.  Terminate interconnect cable conductors on individual terminals.

    - On the right side of controller cabinets, install two 16 position bus bars, for terminating the equipment grounding and neutral conductors used inside the cabinets.  On the left side of the controller cabinets, install two 32 position bus bars, for terminating the equipment grounding and neutral conductors from field wiring.

  - Cabinet Accessories

See NEMA Standard TS 2-2003 V02.06, Section 5 Terminals and Facilities, Figure 5-4 Cabinet Power Distribution Schematic for Items (1) through (6).

    - Disconnecting Means

      - Main circuit breaker must be a single pole, 20 ampere, 10,000 amperes interrupting capacity for each cabinet.

      - Auxiliary circuit breaker(s) must be single pole, 20 ampere, 10,000 amperes interrupting capacity to protect fan, heater, light, and convenience outlet(s).

The rating of the main disconnect means with overcurrent protection must be not less than 125% of the maximum anticipated continuous load.  When using disconnecting circuit breakers, use "trip indicating trip free," Type.

    - Signal Bus.  Connect the signal bus to the incoming AC line through a signal bus mercury contactor and an overcurrent protection device.  Energize the signal bus mercury contactor to provide power to the signal bus.  The current rating of the signal bus mercury contactor must be at least the current rating of the main overcurrent protection device.

    - AC Service Transient Suppression.  Connect the transient suppression device for the primary feed of the cabinet on the load side of the cabinet overcurrent protection device.  The transient voltage suppression device connected to the controller power circuit must provide protection against voltage abnormalities of 1 cycle or less duration.

      - The suppressor must be solid state high energy circuit containing no spark gap, gas tube, or crow bar component.  The current rating of the device must be 15 amps minimum.  The device must provide transient protection between neutral and ground, line and ground, as well as line and neutral.  If the protection circuits fail, they must fail to an open circuit condition.  The device must meet requirements of UL Standard 1449.

      - The suppressed voltage rating must be 600 volts or less when subject to an impulse of 6,000 volt, 3,000 amp source impedance, 8.0/20 microsecond waveform as described in UL Standard 1449.  In addition, the device must withstand, without failure or permanent damage, one full cycle at 264 volts RMS.

      - The device must contain circuitry to prevent self induced regenerative ringing.  There must be a failure warning indicator light that must illuminate when the device has failed and is no longer operable.  The transient suppression device must withstand a 20,000 ampere surge current with an 8x20 microsecond (time to crest x time to second halfcrest) waveform 20 times at 3 minute intervals between surges without damage or degradation to the suppressor.  Output voltage must not exceed 500 volts at any time during the test.  Use a device that is a solid state, high energy circuit with no spark gap, gas tube, or bar component.

    - Radio Interference Suppression.  Equip each traffic cabinet, flasher, and other current interrupting device with a suitable radio interference suppressor installed at the input power point.  Install the radio interference suppressor after the AC service transient suppression unit described in Subsection 740-2.11.1.k (3).  It must provide a minimum attenuation of 50 decibels over a frequency range from 200 kilohertz to 75 megahertz, when used with normal installations.

      - The interference suppressor must be hermetically sealed in a substantial metal case filled with suitable insulating compound. Terminals must be nickel plated, 10-24 brass studs of sufficient external length to provide space for connecting two No. 8 conductors and must be so mounted that the terminals cannot be turned in the case.  Ungrounded terminals must be properly insulated from each other and must maintain a surface leakage distance of not less than 1/4 inch between any exposed current conductor and any other metallic part, with an insulation factor of 100 to 200 megohms dependent on external circuit conditions.

      - The radio interference suppressor must have a minimum current rating equal to the rating of the main disconnect means as specified in Subsection 740-2.11.1.k (1) (a).  It must be designed for operation on 120 volts, 60 hertz, single phase circuits and be UL and EIA compliant.

      - Connect the ground connection of the radio interference suppressor only to AC neutral.  Do not connect to Earth Ground directly.

    - Communications Transient Suppression.  Provide a transient suppressor for the system interface communications lines when used.  This suppressor must withstand a 100 ampere 10 x 700 microsecond waveform 20 times at 30 second intervals between surges without damage or degradation to the suppressor.  Apply the transient surge both line to line and line to ground. Output voltage must not exceed 8 volts line to line and line to ground.  Output voltage must not exceed 8 volts line to line or 250 volts line to ground at any time during the test.

    - Control Panel.  Provide and label a control panel assembly that is readily accessible from the front of the cabinet. The control panel assembly must consist of:

      - "controller power" switch to energize the controller while the signal lights are off or are being operated by the flasher.  Label and rate the switch for load current.

      - An electrical outlet.  It must be a duplex, 3 prong, NEMA Type 5-20R grounding type outlet with independent ground fault circuit protection.

      - "auto/flash" switch that when placed in the "flash" position provides flashing operation without interrupting the controller unit power. When the switch is placed in the "auto" position the controller unit must provide normal operation.

      - "stop time/off/on" switch that when placed in the "stop time" position causes the controller unit to stop time.  In the "off" position, the controller unit must be active regardless of external commands.  In the "on" position, the timing must be normal but subject to external command interruptions.

      - "heater by-pass" switch to bypass the remote heater thermostat.

      - momentary contact test switches to place calls on each vehicle and pedestrian phase.  Switches must provide tactile feedback and be rated at 1 ampere, minimum, for a resistive load at 120 VAC and at 28 VDC.  Contacts must be coin silver or gold plated and be enclosed and labeled as to their function.

- Special Features.  Provide special features if called for in the Plans or as specified in the Special Provisions.

Coordination "Remote/Time of Day/Free" Switch.  When the switch is in the "Remote" position, supervisory functions performed on the controller unit from a master coordinator or central computer must operate normally.

When the switch is in the "Time of Day" position, the local controller must use the local coordinators time of day plan.  When the switch is in the "Free" position, it must be possible to remove any or all coordination devices and maintain normal, non-coordinated controller operation without wire jumpers, jumper plugs or other special devices.  Provide this switch if a local coordination or system modem/interface unit is shown on the Plans.

740-2.12 STANDARD AUXILIARY EQUIPMENT.

Provide equipment meeting the requirements of Section 6 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

- Three Circuit Solid State Load Switches.  Use load switches conforming to NEMA TS-2, Section 6.2 Three Circuit Solid State Load Switches and as a minimum include Light Emitting Diode indicators on the DC input circuitry.  The load switch must have three independent switching circuits, each being an individually replaceable solid state module.

- Solid State Flasher.  Use a NEMA Type III flasher unit that conforms to NEMA TS-2, Section 6.3 Solid State Flashers.

- Malfunction Management Unit (MMU2).  Provide Type 16 MMU2 to be fully compliant with the requirements of NEMA TS-2, Section 4.  In addition, the MMU2 shall have a full intersection LCD back lighted signal on the front panel and shall be downward compatible with TS-1 CMUs.

- Flash Transfer Relay.  Use flash transfer relays that meet the requirements of NEMA TS-2, Section 6.4 Flash Transfer Relays.

740-2.13 SPECIAL AUXILIARY EQUIPMENT. Use the following special auxiliary equipment when called for on the Plans and/or Special Provisions:

Provide equipment meeting the requirements of the cited Sections of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

- Inductive Loop Detector Units.  Provide inductive loop detectors that conform to the requirements of NEMA TS-2, Section 6.5 Inductive Loop Detector Units.  Unless otherwise called for in the Plans provide 2 Channel Inductive Loop Detectors with audible feedback of detection events.  The audible feature must be manually switchable between audible "on" and silent "off."

- Local Coordination Units.  Provide actuated coordination that conforms to the requirements of NEMA TS-2, Section 3.6 Actuated Coordination.

- System Modem/Interface Unit.  Supply a system modem/interface unit assembly that is compatible with the existing computerized traffic control system.

- Preemption Units.  Provide preemption that conforms to the requirements of NEMA TS-2, Section 3.7 Preemption and the following:

  - EVP Infrared Opticom

Install the following components of the GTT Company’s Opticom Priority Control System according to GTT’s written installation instructions at the signalized intersections listed on the Plans.

    - The system must be capable of sending a signal to the controller when an Opticom signal from a vehicle-mounted "GTT OPTICOM Emitter" has been received and maintained for a period of 1.7 seconds.

    - Unless otherwise shown on the Plan use Opticom Traffic Control Systems Opticom Detector Model 721 preemption detectors.

    - Furnish the appropriate number of Opticom Traffic Control Systems 764 Phase Selectors to meet the number of channels of detection for each intersection. Use rack mounted phase selectors.

    - The controller cabinet shall be wired with a Model 768 Auxiliary Interface Panel for the full utilization of all auxiliary detector and green sensing operations of the 764 Phase Selectors. Wire the cabinet with a Model 757 Auxiliary harness for interface between cabinet terminal blocks and Model 768 Auxiliary Interface panel.

    - Install Model 138 detector lead in cable between the end of each signal mast arm and the controller cabinet.  Furnish enough slack in these cables for them to extend 2 feet beyond the end of each signal mast arm and to leave 10 feet of slack in the controller cabinet.  Seal both ends of each lead in cable with mastic lined, heat shrink tubing end caps.

    - The controller, rather than the phase selector or auxiliary logic, must perform interval timing, signal sequences, and phase skips.

    - Mount detectors according to manufacturer recommendations or as approved by the Engineer.  Mount and aim detectors to provide maximum emergency vehicle recognition.  Detector locations shown on the Plans are approximate and subject to change as directed by the Engineer.

    - When emitters are required, provide GTT Opticom Priority Control System, Model 794H Emitter with 793 in vehicle switch.  The Emitter shall be factory programmed to the class and vehicle identification numbers assigned by jurisdiction as shown in the Plans and the following:

      - Class 0 and Vehicle ID. Number 0 (Zero) shall be disabled for Emitters.

      - Vehicle Id. Numbers shall be sequential, beginning with the lowest number in the EVP Emitter table for the appropriate class.

      - Provide one copy of 790IS Emitter Software Kit including "Y" cable.

      - One GTT Opticom Portable Emitter Kit with 792R emitter on a magnetic base, 793R switch and cigarette lighter adapter power cord in a "Camera Bag" case.

  - GPS Opticom Unit

Install the following components of the GTT Company’s Opticom Priority Control System according to GTT’s written installation instructions at the signalized intersections listed on the Plans.

- The system must be capable of sending a signal to the controller when an Opticom signal from a vehicle-mounted "GTT OPTICOM Emitter" has been received and maintained for a period of 1.7 seconds.

- Unless otherwise shown on the Plan use Opticom Model 3100 GPS/Radio Unit containing a GPS receiver with Antenna and a 2.4 GHz spread transceiver with antenna.

- Furnish a 11 conductor radio/GPS cable to connect the Traffic Control Systems 764 Phase Selectors to the Model 3100 GPS Radio Unit.

- Install Model 1070 GPS Installation cable when GPS units are specified.  Furnish enough slack in these cables for them to extend 2 feet beyond the end of each signal mast arm and to leave 10 feet of slack in the controller cabinet.  Seal both ends of each lead in cable with mastic lined, heat shrink tubing end caps.

- Mount GPS Unit according to manufacturer recommendations or as approved by the Engineer.  Mount and aim detectors to provide maximum emergency vehicle recognition.  Detector locations shown on the Plans are approximate and subject to change as directed by the Engineer.

- When GPS emitters are included in the project, provide GTT Opticom Priority Control System, Model 792H Emitter with 793 in vehicle switch.  The Emitter shall be factory programmed to the class and vehicle identification numbers assigned by jurisdiction as shown in the Plans and the following:

      - Class 0 and Vehicle ID. Number 0 (Zero) shall be disabled for Emitters.

      - Vehicle Id. Numbers shall be sequential, beginning with the lowest number in the EVP Emitter table for the appropriate class.

      - Provide one copy of the Emitter Software Kit including required connection cables.

      - One GTT Opticom Portable Emitter Kit with 794R emitter on a magnetic base, 2100 Control Unit and cigarette lighter adapter power cord in a "Camera Bag" case.

- Manufacturer Assisted Start up.  The Contractor shall retain the services of a representative from the GTT Opticom GPS equipment manufacturer and the controller equipment manufacturer Econolite (collectively Manufacturer’s Representative), subject to the approval of the Engineer.  The Manufacturer’s Representative shall have previous experience with either the Central Region DOT&PF or Northern Region DOT&PF in assisting with traffic signal controller testing, field testing and turn on.  Submit name(s) and professional credentials at least 30 days before beginning this work.  When required, work on, and connections to, the Opticom GPS preemption system, vehicle equipment, and related equipment shall be performed by or directly supervised by a qualified person serving as the Manufacturer’s Representative.

On-Site manufacturer assisted startup will be required for all intersections scheduled for GPS Opticom installations shown in the Plans. Red-lined cabinet prints shall be altered electronically and provided in hard copy, “.pdf”, and AutoCAD format for each cabinet receiving GPS Opticom installation.

Telephonic manufacturer assisted start-up required for all intersections that do not require on-site manufacturer assisted start up as indicated above.

- Required Credentials of Manufacturer’s Representative

  - 10 years experience working in the traffic controller industry, 5 years of that must have been as a signal technician.

  - Must have IMSA Traffic Signal Technician, Level II certification

  - Experience assisting with the Northern Region ADOT, or the Central Region ADOT

  - Familiarity with both the NEMA TS1 and TS2 specifications

  - Competent to read cabinet wiring diagrams and troubleshoot cabinet components

  - Competent to troubleshoot Preemption issues

- Competent to test and Install GPS Preemption components

- Competent to conduct training on installed components

- Training Except as otherwise noted, immediately preceding or following the Manufacturers Startup of the GPS Opticom System, the vendor shall provide training. All training is to be provided by a representative of the original equipment manufacturer. Training may be attended by any number of ADOT personnel from any of its three regions. Required training includes:

  - Provide 7.5 hours of instruction on the proper setup of the Radio/GPS Opticom Emergency Vehicle Preemption system. Training is to include all information necessary to properly set up and operate the Radio/GPS Opticom system as well as instruction on integration or use of the Opticom equipment/software with the Traffic Management system software, Centracs. The training audience is ADOT & MOA traffic Engineers. Deliver training time, day and location mutually agreeable to the contractor and the Traffic Design or Operations Engineer.

  - When emitters are included in the project provide two (2) 4.0 hour sessions of instruction on the proper use of the Radio/GPS based Opticom emitter. Training must be provided by a representative authorized by the original equipment manufacturer. Training is to include all information necessary to properly operate the Radio/GPS Opticom emitter. Deliver training at a time, day and location mutually agreeable to the contractor and the Traffic Design or Operations Engineer. One of the two training sessions will be delivered in the evening between 6:00pm and 12:00 am. Note; training will not be accepted until contract required equipment is delivered

  - Upon completion of training the manufacturer representative shall provide two (2) copies on thumb drives and two (2) copies on CD of any software required for setup, operation of, or maintenance of the GPS Opticom system components. This includes but is not limited to On-Site Interface Software and Central Managements Software.

- Bus Interface Unit (BIU).  Provide BIU’s that fully meet the requirements of NEMA TS-2 Section 8.  Unless otherwise called for in the Plans provide BIU’s that meet the NEMA designation BIU2.

- Traffic Logging System.  If called for in the Plans, furnish, and install in the controller cabinet, a stand-alone unit that collects, time stamps, and stores data in an unattended manner.

7.	Radar Detection System.

a.	General.

(1)	System Hardware. Use digital wave radar vision system hardware consisting of the following components:

(a)	Provide an above-ground stop bar detector (SBD) equivalent to the Wavetronix SmartSensor Matrix® that will detect all vehicles, including bicycles for reliable and accurate presence detection where shown on the Plans

(b)	Provide an above-ground continuous tracking advance extended range detector (CTAD) equivalent to the Wavetronix SmartSensor Advance Extended Range® for enhanced dilemma zone detection where shown on the Plans

(c)	A Click 650 cabinet interface device (CIB)

(d)	Contact closure input file detector rack cards with patch cables

(e)	SmartSensor Manager Matrix (SSMM) software

(f)	SmartSensor Manager Advance software for automatic and manual sensor configurations

Stop Bar Detector (SBD)

a. 	General. Provide an above-ground digital wave radar stop bar detector (SBD) equivalent to the Wavetronix SmartSensor Matrix® that will detect all stopped vehicles, including bicycles for reliable and accurate presence detection where shown on the Plans.

b. 	Product Description. The SBD units shall:

(1) 	Be able to simultaneously detect and track vehicles through a 90 degree field of view in two dimensions.

(2) 	Reports real-time presence of both moving and stopped vehicles for up to 10 lanes.

(3) 	Maximum number of zones: 16.

(4) 	Maximum number of channels: 16.

(5) 	User-selectable zone to channel mapping.

(6) 	AND logic triggers the channel when all the selected zones are active.

(7) 	OR logic used to combine multiple zones to a channel output.

(8) 	Channel output extend and delay functionality.

(9) 	Algorithms mitigate detections from wrong way or cross traffic.

(10)	Fail-safe mode for contact closure outputs if communication is lost.

c. 	Detectable Area.

(1)	Mounting Location.

(a)	The SBD shall be able to detect and report vehicle information when mounted between 15-35 ft. (4.6-10.7 m) above the road surface.

(2)	Detection Range.

(a) 	The SBD shall have a 90 degree field of view, and be able to detect and report information on the roadway located with the near boundary at 6 ft. (1.8 m) and a far boundary of 140 ft. (42.7 m) from the base of the pole on which the SBD is mounted.

(3) 	Lane Configuration.

(a)	Be capable of providing flexible lane configuration support including:

- Up to 10 lanes

- Curved lanes

- Islands and medians

d.	Performance.

(1) 	Stop Bar – Approach Only Counting Accuracy. For a four-lane, 35 mph approach, the SBD shall detect at least 80 percent of vehicles.

e. 	Performance Maintenance.

(1) 	The SBD shall not require cleaning or adjustment to maintain performance.

(2) 	The SBD shall not rely on battery backup to store configuration information.

(3) 	Once the SBD is calibrated, it shall not require recalibration to maintain performance unless the roadway configuration changes.

f. 	Physical Properties. The SBD shall not exceed 5 lbs. (2.3 kg) in weight. The SBD shall not exceed 14 in. by 12 in. by 4 in. (35.5 cm x 30.5 cm x 10 cm) in its physical dimensions. All external parts of the SBD shall be ultraviolet-resistant, corrosion resistant, and protected from fungus growth and moisture deterioration.

(1) 	Enclosure. The SBD shall be enclosed in a Lexan EXL polycarbonate.

(a) 	The enclosure shall be classified "f1" outdoor weather ability in accordance with UL 746C.

(b) 	The SBD shall be classified as watertight according to the NEMA 250 Standard.

(c) 	The SBD enclosure shall conform to test criteria set forth in the NEMA 250 standard for type 4X enclosures. Test results shall be provided for each of the following type 4X criteria:

- External Icing (NEMA 250 clause 5.6)

- Hose-down (NEMA 250 clause 5.7)

- 4X Corrosion Protection (NEMA 250 clause 5.10)

- Gasket (NEMA 250 clause 5.14)

(d) 	The SBD shall be able to withstand a drop of up to 5 ft. (1.5 m) without compromising its functional and structural integrity.

(e) 	The SBD enclosure shall include a connector that meets the MIL-C-26482 specification. The MIL-C-26482 connector shall provide contacts for all data and power connections.

g. 	Power.

(1) 	The SBD shall consume less than 10 W.

(2) 	The SBD shall operate with a DC input between 9 VDC and 28 VDC.

(3)	The SBD shall have an onboard surge protection.

h. 	Communication.

(1) 	The SBD shall have two half-duplex RS-485 com ports support:

(a)	Dedicated detection comms

(b)	Configuration, verification or traffic display without disrupting detection comms

(2) 	The SBD shall support the upload of new firmware into the SBD's non-volatile memory over Ethernet communication port.

(3) 	The SBD shall support the user configuration of the following:

(a) 	Baud rate

(b) 	Communication port response delay

(c) 	Contact closure output frequency

(4) 	Both communication ports shall support all of the following baud rates: 9600, 19200, 38400, 57600 and 115200 bps.

i.	Radar Design.

(1) 	Frequency Stability. The circuitry shall be void of any manual tuning elements that could lead to human error and degraded performance over time. All transmit modulated signals shall be generated by means of digital circuitry, such as a direct digital synthesizer, that is referenced to a frequency source that is at least 50 parts per million (ppm) stable over the specified temperature range, and ages less than 6 ppm per year. Any upconversion of a digitally generated modulated signal shall preserve the phase stability and frequency stability inherent in the digitally generated signal.

(a) 	The SBD shall not rely on temperature compensation circuitry to maintain transmit frequency stability.

(b) 	The bandwidth of the transmit signal of the SBD shall not vary by more than 1% under all specified operating conditions and over the expected life of the SBD.

(c)	Matrix of 16 radars.

(2)	Antenna Design. The SBD antennae shall be designed on printed circuit boards.

(a) 	The vertical beam width of the SBD at the 6dB points of the two-way pattern shall be 65 degrees or greater.

(b) 	The horizontal field of view: 90 degrees.

(c) 	The sidelobes in the SBD two-way antenna pattern shall be -40dB or less.

(d)	Transmit bandwidth:	245 MHz

(e)	Un-windowed resolution:	2 ft. (0.6 m)

(3) 	RF Channels. The SBD shall provide at least eight RF channels so that multiple units can be mounted in the same vicinity without causing interference between them.

j. 	Configuration.

(1) 	Automatic and manual configuration of lanes, stop bars and zones.

(2) 	Lane positioning increment: 1 ft. (0.3 m)

(3)	Four-sided zones of any shape and size

(4)	Overlapping zones supported

(5)	Sensor reconfiguration without detection disruption supported

(6)	Graphical user interface with traffic pattern display

(7)	Counting and Pulsed channels supported

(8) 	Windows Mobile®-based Software. The SBD shall include graphical user interface software that displays the current traffic pattern using a graphical traffic representation.

(a) 	The graphical user interface shall also display all configured alerts and provide visual representation of their actuation.

(b) 	The graphical user interface shall provide a means of logging the vehicular track files with an update rate of greater than five times per second.

(c) 	The graphical interface shall operate on Windows Mobile v5.0 or greater, Windows XP, Windows Vista, and Windows 7 in the .NET framework.

(d) 	The software shall support the following functionality:

- Automatically find the correct baud rate

- Automatically find the correct serial communication port

- Operate over a TCP/IP connection

- Provide a virtual sensor connection for software usabilty without a sensor

- Give the operator the ability to save/back up the SBD configuration to a file or load/restore the SBD configuration from a file

- Real-time traffic visualization for performance verification

- Zone and channel actuation display

- Local or remote sensor firmware upgradability

k. 	Operating Conditions. The SBD shall maintain accurate performance in all weather conditions, including

(1) 	Rain, freezing rain, snow, wind, dust, fog and changes in temperature and light, including direct light on sensor at dawn and dusk.

(2) 	SBD operation shall continue in rain up to 1 in. (2.5 cm) per hour.

(3) 	The SBD shall be capable of continuous operation over an ambient temperature range of -40°F to 165°F (-40°C to 74°C).

(4) 	The SBD shall be capable of continuous operation over a relative humidity range of 5% to 95% (non-condensing).

I. 	Testing.

(1) 	FCC. Each SBD shall be Federal Communications Commission (FCC) certified under CFR 47, Part 15, section 15.249 as an intentional radiator.

(a) 	The FCC certification shall be displayed on an external label on each SBD according to the rules set forth by the FCC.

(b) 	The SBD shall comply with FCC regulations under all specified operating conditions and over the expected life of the SBD.

(2) 	Tested under IEC 61000-4-5 class 4

(3) 	NEMA TS2-2003 Testing. The SBD shall comply with the applicable standards stated in the NEMA TS2-2003 Standard. Third party test results shall be made available for each of the following tests:

(a) 	Shock pulses of 10g, 11 ms half sine wave

(b) 	Vibration of 0.5 g up to 30 Hz

(c) 	300 V positive/negative pulses applied at one pulse per second at minimum and maximum DC supply voltage

(d) 	Cold temperature storage at -49°F (-45°C) for 24 hours

(e) 	High temperature storage at 185°F (85°C) for 24 hours

(f) 	Low temp, low DC supply voltage at -29.2°F (-34°C) and 10.8 VDC

(g) 	Low temp, high DC supply voltage at -29.2°F (-34°C) and 26.5 VDC

(h) 	High temp, high DC supply voltage at 165.2°F (74°C) and 26.5 VDC

(i) 	High temp, low DC supply voltage at 165.2°F (74°C) and 10.8 VDC

m. 	Manufacturing. The SBD shall be manufactured and assembled in the U.S.A.

(1) 	The internal electronics of the SBD shall utilize automation for surface mount and wave solder assembly, and shall comply with the requirements set forth in IPC-A-610C Class 2, Acceptability of Electronic Assemblies.

(2) 	The SBD shall undergo a rigorous sequence of operational testing to ensure product functionality and reliability. Testing shall include the following:

(a) 	Functionality testing of all internal sub-assemblies

(b) 	Unit level burn-in testing of duration 48 hours or greater

(c) 	Final unit functionality testing prior to shipment

(d) 	Test results and all associated data for the above testing shall be provided for each purchased SBD by serial number.

n. 	Support. The SBD manufacturer shall provide both training and technical support services.

(1) 	Training. The manufacturer-provided training shall be sufficient to fully train installers and operators in the installation, auto-configuration, and use of the SBD to ensure accurate SBD performance.

(a) 	The manufacturer-provided training shall consist of comprehensive classroom labs and hands-on, in-the-field, installation and configuration training.

(b) 	Classroom lab training shall involve presentations outlining and defining the SBD, its functions, and the procedures for proper operation. These presentations shall be followed by hands-on labs in which trainees shall practice using the equipment to calibrate and configure a virtual SBD. To facilitate the classroom presentation and hands-on labs, the manufacturer-provided training shall include the following items:

- Knowledgeable trainer or trainers thoroughly familiar with the SBD and its processes.

- Presentation materials, including visual aids, printed manuals and other handout materials for each student.

- Computer files, including video and raw data, to facilitate the virtual configuration of the SBD.

- Laptop computers or Windows CE hand-held devices with the necessary software, and all necessary cables, connectors, etc.

- All other equipment necessary to facilitate the virtual configuration of the SBD.

(c) 	Field training shall provide each trainee with the hands-on opportunity to install and configure the SBD at road-side. Training shall be such that each trainee will mount and align the SBD correctly.

(2) 	Technical Assistance. A manufacturer-provided technical representative shall be available to assist with the physical installation, alignment, and configuration of each supplied SBD. Technical support shall be provided thereafter to assist with troubleshooting, maintenance, or replacement of SBDs should such services be required.

o. 	Documentation. SBD documentation shall include an instructional training guide, a comprehensive user guide, as well as an installer quick-reference guide and a user quick-reference guide.

(1) 	The SBD manufacturer shall supply the following documentation and specification test results at the time of the bid submittal:

(a) 	FCC CFR 47 certification

(b) 	IEC 61000-4-5 class 4 test report

p. 	Warranty. The SBD shall be warranted free from material and workmanship defects for a period of two years from date of shipment.

Extended Range Detector (CTAD)

The CTAD shall:

(1) 	Be able to simultaneously detect and report information from up to 25 vehicles on the roadway when they are serially sequenced between the near and far boundaries.

(2) 	Turn on a zone output when the range, speed, ETA, and qualified count or instantaneous roadway efficiency requirements for that zone are satisfied.

(3) 	Turn on an alert output on when the user-defined zone output combinational logical is satisfied.

(4) 	Turn on a normal channel output when any of the channel's alerts is on and the channel’s delay and extend time constraints are satisfied.

(5) 	Turn on a latched channel output when the on alert is turned on and the delay time is satisfied. The CTAD shall turn off a latched channel output when the off alert is turned on or the max timer expires and the extension time is satisfied.

(6) 	Provide vehicle call and extend data on up to eight channels that can be connected to contact closure modules compliant with NEMA TS1, NEMA TS2, 170, and 2070 controller cabinets.

(7) 	Be capable of providing data for each tracked detection over the serial ports.

a. 	Detectable Area.

(1) 	Mounting Location.

(a) 	The CTAD shall be able to detect and report vehicle information when mounted within 50 ft. (15.2 m) of the center of the lanes of interest.

(b) 	The CTAD shall be able to detect and report vehicle information when mounted at heights up to 40 ft. (12.2 m) above the road surface.

(2) 	Detection Range.

(a) 	The CTAD shall be able to detect and report information on the roadway located with the near boundary at 50 ft. (15.2 m) and a far boundary of 500 ft. (152.4 m) from the base of the pole on which the CTAD is mounted.

(b) 	For incoming traffic, 95 percent of large vehicles within the line-of-site of the CTAD shall be detected and reported before they arrive 400 ft. (121.9 m) from the sensor. For incoming traffic, 90 percent of all motor vehicles within the line-of-site of the CTAD shall be detected and reported before they arrive 400 ft. (121.9 m) from the sensor.

b.	Performance.

(1) 	Detection Accuracy. The CTAD shall detect at least 98 percent of large vehicles like truck-trailer combinations and at least 95 percent of all motor vehicles within the line-of-sight of the CTAD sensor where multiple detections of multi-unit vehicles are not considered false detections and merged detections of adjacent lane vehicles are not considered missed detections.

(2) 	Range Accuracy. The CTAD shall provide range measurements in which 90% of the measurements are accurate within 10 ft. (3 m) when the vehicle is tracked independently.

(3) 	Speed Accuracy. The CTAD shall provide per vehicle speed measurements in which 90% of the measurements are accurate within 5 mph when tracked independently.

(4) 	ETA Accuracy. The CTAD shall provide estimated time-of-arrival (ETA) measurements in which 85% of the measurements are accurate within one second, when the detected vehicles are tracked independently at a constant speed above 40 mph (64 kph} and are within 2.5 and 5.5 seconds of the stop bar.

c. 	Performance Maintenance.

(1) 	The CTAD shall not require cleaning or adjustment to maintain performance.

(2) 	The CTAD shall not rely on battery backup to store configuration information.

(3) 	Once the CTAD is calibrated, it shall not require recalibration to maintain performance unless the roadway configuration changes.

d. 	Physical Properties. The CTAD shall not exceed 5 lbs. (2.3 kg) in weight. The CTAD shall not exceed 14 in. by 12 in. by 4 in. (35.5 cm x 30.5 cm x 10 cm) in its physical dimensions. All external parts of the CTAD shall be ultraviolet-resistant, corrosion resistant, and protected from fungus growth and moisture deterioration.

(1) 	Enclosure. The CTAD shall be enclosed in a Lexan EXL polycarbonate.

(a) 	The enclosure shall be classified "f1" outdoor weather ability in accordance with UL 746C.

(b) 	The CTAD shall be classified as watertight according to the NEMA 250 Standard.

(c) 	The CTAD enclosure shall conform to test criteria set forth in the NEMA 250 standard for type 4X enclosures. Test results shall be provided for each of the following type 4X criteria:

- External Icing (NEMA 250 clause 5.6)

- Hose-down (NEMA 250 clause 5.7)

- 4X Corrosion Protection (NEMA 250 clause 5.10)

- Gasket (NEMA 250 clause 5.14)

(d) 	The CTAD shall be able to withstand a drop of up to 5 ft. (1.5 m) without compromising its functional and structural integrity.

(e) 	The CTAD enclosure shall include a connector that meets the MIL-C-26482 specification. The MIL-C-26482 connector shall provide contacts for all data and power connections.

e. 	Power.

(1) 	The CTAD shall consume less than 8 W.

(2) 	The CTAD shall operate with a DC input between 12 VDC and 28 VDC.

f. 	Communication.

(1) 	The CTAD shall have two serial communication ports, and both ports shall communicate independently and simultaneously.

(2) 	The CTAD shall support the upload of new firmware into the CTAD's non-volatile memory over Ethernet communication port.

(3) 	The CTAD shall support the user configuration of the following:

(a) 	Baud rate

(b) 	Communication port response delay

(c) 	Contact closure output frequency

(4) 	Both communication ports shall support all of the following baud rates: 9600, 19200, 38400, 57600 and 115200 bps.

(5) 	The contact closure output frequency shall be user configurable as short as 10 ms, with a default near 130 ms for compatibility.

(6) 	Contact closure data shall be reliably communicated over homerun cable connections as long as 600 ft. (182.9 m) with latency from the time of channel requirement satisfaction to the eventual reporting of on the back edge of the contact closure card in 15 ms or less.

g. 	Radar Design.

(1) 	Frequency Stability. The circuitry shall be void of any manual tuning elements that could lead to human error and degraded performance over time. All transmit modulated signals shall be generated by means of digital circuitry, such as a direct digital synthesizer, that is referenced to a frequency source that is at least 50 parts per million (ppm) stable over the specified temperature range, and ages less than 6 ppm per year. Any upconversion of a digitally generated modulated signal shall preserve the phase stability and frequency stability inherent in the digitally generated signal.

(a) 	The CTAD shall not rely on temperature compensation circuitry to maintain transmit frequency stability.

(b) 	The bandwidth of the transmit signal of the CTAD shall not vary by more than 1% under all specified operating conditions and over the expected life of the CTAD.

(2)	Antenna Design. The CTAD antennae shall be designed on printed circuit boards.

(a) 	The vertical beam width of the CTAD at the 6dB points of the two-way pattern shall be 65 degrees or greater.

(b) 	The horizontal beam width of the CTAD at the 6dB points of the two-way pattern shall be 11 degrees or less.

(c) 	The sidelobes in the CTAD two-way antenna pattern shall be -40dB or less.

(3) 	RF Channels. The CTAD shall provide at least four RF channels so that multiple units can be mounted in the same vicinity without causing interference between them.

h. 	Configuration.

(1) 	Auto-configuration. The CTAD shall have a method for automatically configuring the sensitivity of detection in at least 5-ft. (1.5-m) increments.

(a) 	The auto-configuration method shall not prohibit the ability of the user to manually adjust the CTAD configuration.

(b) 	The CTAD shall support the configuration of up to eight channel outputs with up to four alerts per channel and up to four zones per alert, resulting in 32 configurable alerts and 128 configurable zones.

(2) 	Zone Configuration.

(a) 	The CTAD shall support the configuring of zones in 5-ft. (1.5 m) increments.

(b) 	The CTAD shall support detection zones as long as 450 ft. (137.2 m).

(c) 	The CTAD shall support user configurable high-speed and low-speed detection filters for each zone.

(d) 	The CTAD shall support the configuring of speed filters in 1-mph (1.6-kph) increments.

(e) 	The CTAD shall support user configurable upper and lower estimated time-of-arrival (ETA) filters for each zone.

(f) 	The CTAD shall support the configuring of ETA filters in increments of 0.1 seconds.

(g) 	The CTAD shall provide configurable upper and lower count filters that help determine if a required number of qualified detections are present.

(h) 	The CTAD shall support the configuring of qualified count filters in increments of one.

(3) 	Windows Mobile®-based Software. The CTAD shall include graphical user interface software that displays the current traffic pattern using a graphical traffic representation.

(a) 	The graphical user interface shall also display all configured alerts and provide visual representation of their actuation.

(b) 	The graphical user interface shall provide a means of logging the vehicular track files with an update rate of greater than five times per second.

(c) 	The graphical interface shall operate on Windows Mobile, Windows 2000, Windows XP and Windows Vista in the .NET framework.

(d) 	The software shall support the following functionality:

- Automatically find the correct baud rate

- Automatically find the correct serial communication port

- Operate over a TCP/IP connection

- Provide a virtual sensor connection for software usabilty without a sensor

- Give the operator the ability to save/back up the CTAD configuration to a file or load/restore the CTAD configuration from a file

i. 	Operating Conditions. The CTAD shall maintain accurate performance in all weather conditions, including

(1) 	Rain, freezing rain, snow, wind, dust, fog and changes in temperature and light, including direct light on sensor at dawn and dusk.

(2) 	CTAD operation shall continue in snow or rain up to 4 in. (10 cm) per hour.

(3) 	The CTAD shall be capable of continuous operation over an ambient temperature range of -40°F to 165°F (-40°C to 74°C).

(4) 	The CTAD shall be capable of continuous operation over a relative humidity range of 5% to 95% (non-condensing).

j. 	Testing.

(1) 	FCC. Each CTAD shall be Federal Communications Commission (FCC) certified under CFR 47, Part 15, section 15.245or15.249 as an intentional radiator.

(a) 	The FCC certification shall be displayed on an external label on each CTAD according to the rules set forth by the FCC.

(b) 	The CTAD shall comply with FCC regulations under all specified operating conditions and over the expected life of the CTAD.

(2) 	NEMA TS2-1998 Testing. The CTAD shall comply with the applicable standards stated in the NEMA TS2-1998 Standard. Third party test results shall be made available for each of the following tests:

(a) 	Shock pulses of 10g, 11 ms half sine wave

(b) 	Vibration of 0.5 g up to 30 Hz

(c) 	300 V positive/negative pulses applied at one pulse per second at minimum and maximum DC supply voltage

(d) 	Cold temperature storage at -49°F (-45°C) for 24 hours

(e) 	High temperature storage at 185°F (85°C) for 24 hours

(f) 	Low temp, low DC supply voltage at -29.2°F (-34°C) and 10.8 VDC

(g) 	Low temp, high DC supply voltage at -29.2°F (-34°C) and 26.5 VDC

(h) 	High temp, high DC supply voltage at 165.2°F (74°C) and 26.5 VDC

(i) 	High temp, low DC supply voltage at 165.2°F (74°C) and 10.8 VDC

k. 	Manufacturing. The CTAD shall be manufactured and assembled in the U.S.A.

(1) 	The internal electronics of the CTAD shall utilize automation for surface mount and wave solder assembly, and shall comply with the requirements set forth in IPC-A-61 OC Class 3, Acceptability of Electronic Assemblies.

(2) 	The CTAD shall undergo a rigorous sequence of operational testing to ensure product functionality and reliability. Testing shall include the following:

(a) 	Functionality testing of all internal sub-assemblies

(b) 	Unit level burn-in testing of duration 48 hours or greater

(c) 	Final unit functionality testing prior to shipment

(d) 	Test results and all associated data for the above testing shall be provided for each purchased CTAD by serial number.

l. 	Support. The CTAD manufacturer shall provide both training and technical support services.

(1) 	Training. The manufacturer-provided training shall be sufficient to fully train installers and operators in the installation, auto-configuration, and use of the CTAD to ensure accurate CTAD performance.

(a) 	The manufacturer-provided training shall consist of comprehensive classroom labs and hands-on, in-the-field, installation and configuration training.

(b) 	Classroom lab training shall involve presentations outlining and defining the CTAD, its functions, and the procedures for proper operation. These presentations shall be followed by hands-on labs in which trainees shall practice using the equipment to calibrate and configure a virtual CTAD. To facilitate the classroom presentation and hands-on labs, the manufacturer-provided training shall include the following items:

- Knowledgeable trainer or trainers thoroughly familiar with the CTAD and its processes.

- Presentation materials, including visual aids, printed manuals and other handout materials for each student.

- Computer files, including video and raw data, to facilitate the virtual configuration of the CTAD.

- Laptop computers or Windows CE hand-held devices with the necessary software, and all necessary cables, connectors, etc.

- All other equipment necessary to facilitate the virtual configuration of the CTAD.

(c) 	Field training shall provide each trainee with the hands-on opportunity to install and configure the CTAD at road-side. Training shall be such that each trainee will mount and align the CTAD correctly.

(2) 	Technical Assistance. A manufacturer-provided technical representative shall be available to assist with the physical installation, alignment, and configuration of each supplied CTAD. Technical support shall be provided thereafter to assist with troubleshooting, maintenance, or replacement of CTADs should such services be required.

m. 	Documentation. CTAD documentation shall include a comprehensive user guide as well as an installer quick-reference guide and a user quick-reference guide.

(1) 	The CTAD manufacturer shall supply the following documentation and specification test results at the time of the bid submittal:

(a) 	Detection accuracy

(b) 	Range accuracy Earliest range of detection

(c) 	Speed accuracy

(d) 	ETA accuracy

(e) 	FCC CFR 47 certification

(f) 	NEMA 250 Standard for Type 4X Enclosure third-party test data

(g) 	NEMA TS2-1998 Standard third-party test data

n. 	Warranty. The CTAD shall be warranted free from material and workmanship defects for a period of two years from date of shipment.

Click! 200

a. 	General. Provide and install a surge suppression module (SSM) equivalent to the Wavetronix Click! 200™. Test results and other documentation demonstrating performance and capabilities shall be provided.

b. 	Product Description. The SSM shall suppress electrical surges up to 4 kV on DC power lines, RS-485 and RS-232 with CTS/RTS communication lines to any device connected to the SSM. The SSM shall be designed to protect a radar vehicle sensing device (RSVD) equivalent to the Wavetronix SmartSensor™ from surges coming from a traffic cabinet, or protect a cabinet from surges coming from the RVSD.

c. 	Physical. The SSM shall not exceed 0.3 lbs. (0.14 kg) in weight.

(1) 	The SSM shall not exceed 4.5 in. x 4 in. x 0.9 in. (11.4 cm x 10.2 cm x 2.3 cm) in its physical dimensions.

(2) 	The SSM shall operate in the temperature range of -29°F to 165°F (-34°C to 74°C).

(3) 	The SSM shall operate in humidity up to 95% RH.

d. 	Mounting. The SSM shall mount to a DIN rail with hot swappable surge protected power and communication buses for quick installation and replacement.

e. 	Connections. The SSM shall have pluggable screw terminals allowing the user to wire a contact closure data collector to the SSM before installation to make installation easy and to minimize incorrect wiring.

(1) 	The SSM shall also have a protected DB-9 connector tor the RS-232DTE with CTS/RTS communication bus.

(2) 	The SSM shall also have a protected RJ-11 connector tor the RS-485 communication bus.

(3) 	The SSM shall also have a 5-position connector tor connecting power and RS-485 communications to and from the T-bus.

f. 	Three-stage Protection. The SSM shall have a three-stage surge suppression design. The first stage shall be gas tubes followed by a second stage using inductors on the DC power lines and TVS diodes on the communication buses. The third stage shall have a resettable fuse (PTC) on the DC power line and varistors on all communication buses.

g. 	DC Power Protection. The SSM shall comply with the applicable standards stated in the IEC 61000-4-5 Standard for DC power lines. Test results shall be made available tor the following test conditions:

(1) 	Surge voltages + 0.5kVA, 1 kVA, 2kVA and 4kVA

(2) 	Common mode (input to ground)

(3) 	Differential mode (input to input)

(4) 	8x20μs waveform

(5) 	ohm generator impedance

(6) 	Minute-long pause between surges

h. 	RS-485 Protection. The SSM shall comply with the applicable standards stated in the IEC 61000-4-5 Standard for communication lines. The RS-485 communication bus shall have a clamping voltage of 8 VDC and a 12 VDC differential clamping voltage. Test results shall be made available for the following test conditions:

(1) 	Surge voltages ±0.5kVA, 1 kVA, 2kVA and 4kVA

(2) 	Common mode (input to ground)

(3) 	Differential mode (input to input)

(4) 	8x20μs waveform

(5) 	12 ohm generator impedance

(6) 	Minute-long pause between surges

i. 	RS-232 with CTS/RTS Protection. The SSM shall comply with the applicable standards stated in the IEC 61000-4-5 Standard tor communication lines. The RS-232 communication bus shall have a clamping voltage of 11 VDC. Test results shall be made available for the following test conditions:

(1) 	Surge voltages ±0.5kVA, 1 kVA, 2kVA and 4kVA

(2) 	Common mode (input to ground)

(3) 	Differential mode (input to input)

(4) 	8x20μs waveform

(5) 	12 ohm generator impedance

(6) 	Minute-long pause between surges

j. 	NEMA TS2-1998 Testing. The SSM shall comply with the applicable standards stated in the NEMA TS2-1998 Standard. Test results shall be made available for each of the following tests:

(1) 	Shock pulses of 10g, 11 ms half sine wave

(2) 	Vibration of 0.5 Grms up to 30 Hz

(3) 	300 V positive/negative pulses applied at one pulse per second at minimum and maximum DC supply voltage

(4) 	Cold temperature storage at -49°F (-45°C) tor 24 hours

(5) 	High temperature storage at 185°F (85°C} for 24 hours

(6) 	Low temp, low DC supply voltage at -29.2°F (-34°C} and 10.8 VDC

(7) 	Low temp, high DC supply voltage at -29.2°F (-34°C) and 26.5 VDC

(8) 	High temp, high DC supply voltage at 165.2°F (74°C) and 26.5 voe

(9) 	High temp, low DC supply voltage at 165.2°F (74°C) and 10.8 VDC

k. 	Testing. Each SSM shall be tested by the manufacturer before shipment.

I. 	Support. A manufacturer-provided technical representative shall be available to assist with the physical installation, setup, and configuration of each Click! 200 provided. Technical support shall be provided thereafter to assist with troubleshooting, maintenance, or replacement of Click! 200 should such services be required.

m. 	Warranty. The SSM shall be warranted to be free from material and workmanship defects for a period of one year from date of shipment.

Click! 650

a. 	General. When called for on the plans, provide and install the number of cabinet interface devices(s) (CID) equivalent to the Wavetronix Click! 650. The CID shall be used to provide power to the SBD and CTAD sensors, protects the controller cabinet from surges, and communicates with the IFCC contact closure devices.

b. 	Product Description. The CID can be used in place of Intersection Preassembled Backplates (IPB) or the Click 600. It shall convert real-time serial data from the RVSD to contact closure data in a form factor compatible with 170, 2070, NEMA TS2 and NEMA TS1 input file racks, or SDLC communication to the Controller BIU, allowing the RVSD to emulate loop-based traffic detection systems without replacing existing contact closure data collection infrastructure.

c. 	Physical. The CID shall not exceed 5 lbs. (2.25 kg) in weight.

(1) 	The CID shall not exceed 7.8 in. x 10.3 in. x 3.9 in. (19.8 cm x 26.2 cm x 9.9 cm) in its physical dimensions.

(2) 	The CID shall operate in the temperature range of -29°F to 165°F (-34°C to 74°C).

(3) 	The CID shall operate in up to 95% relative humidity.

d. 	Mounting. The CID shall be a shelf mounted unit capable of being mounted to the side of the controller cabinet using u-channel mounting brackets.

e. 	Power. The CID shall be capable of providing:

(1) 	Power supply voltage: 90 to 260 VAC

(2)	AC frequency: 50-60 Hz

(3) 	Maximum Power: 75 W at 80°C

(4)	24 VDC on sensor connectors

f. 	Connections and Communication.

(1) 	Power.

(a)	AC input: IEC AC input.

(2) 	Four RJ-11 jacks on faceplate of device for connecting to contact closure devices.

(a)	Communicate via RS-485

(b)	Jacks make up physical interface of data bus on device and are for sending detection data from CTAD and SBD sensors on to contact closure devices such as rack cards.

(c)	Communicate with rack cards via jumper cables

(3)	Terminal Block Connectors. Four terminal block connectors on back of device for connecting to SBD and CTAD sensors.

(a)	Cable terminal points for sensor power and RS-485 communications

(b)	Matching terminal blocks are included with the CID

(c)	Matches terminal blocks used for cable termination with Wavetronix intersection preassembled backplates

(4)	Four communication ports on faceplate make up physical interface of control bus and are for connecting to the sensors to configure them.

(a)	DB-9 port for communicating via RS-232

(b)	Two RJ-11 jacks for communicating via RS-485

(c)	USB mini-B connector

(d)	T-bus port for connecting to a T-bus; allows the CID to send DC power and RS-485 communications to other devices connected to a T-bus

(5)	SDLC

(a)	One SDLC port on the front of the Device

(6) 	Ethernet

(a)	One RJ-45 10/100 Ethernet jack on the front of the device

g. 	Other Features. The CID shall have the following features:

(1) 	LEDs. The CID shall have four multicolored LEDs with activity indicating functions.

(a)	Red LED (PW) illuminates when device has power

(b)	Blue LED (OK) extinguishes if device has been disabled by surges

(c)	Green LED (TD) illuminates when data is transmitted on the control bus

(d)	Yellow LED (RD) illuminates when data is received on the control bus

(2) 	Data Bus RJ-11 Jack. Each data bus RJ-11 jack on the faceplate corresponds to one sensor and has the following features:

(a)	Switch for turning the power to each SBD and CTAD sensor on and off

(b)	LED for indicating when that sensor has power

(3) 	Power Switch. Switch for turning power on and off to entire CID

- OLED Panel with Keypad.  Panel and keypad for CID device configuration.

- Web Interface.  Web interface for CID device configuration, accessible through a web browser from a network-connected device.

- Configuration.  CID configuration shall support up to 64 detector channels.

h. 	NEMA Testing. The CID shall comply with the applicable standards stated in NEMA TS2-2003. Test results shall be made available for each of the following tests:

(1) 	Shock pulses of 10 g, 11 ms half sine wave

(2) 	Vibration of 0.5 Grms up to 30 Hz

(3) 	300 V positive/negative pulses applied at one pulse per second at minimum and maximum DC supply voltage

(4) 	Cold temperature storage at -49°F (-45°C) for 24 hours

(5) 	High temperature storage at 185°F (85°C) for 24 hours

(6) 	Low temp, low DC supply voltage at -29.2°F (-34°C) and 10.8 VDC

(7) 	Low temp, high DC supply voltage at -29.2°F (-34°C) and 26.5 VDC

(8) 	High temp, high DC supply voltage at 165.2°F (7 4 °C) and 26.5 VDC

(9) 	High temp, low DC supply voltage at 165.2°F (7 4 °C) and 10.8 VDC

i. 	Testing. Before shipping, each CID shall have passed a manufacturer's test and be FCC compliant.

j. 	Support. A manufacturer-provided technical representative shall be available to assist with the physical installation, setup, and configuration of each Click! 650 provided. Technical support shall be provided thereafter to assist with troubleshooting, maintenance, or replacement of Click! 650 should such services be required.

k. 	Warranty. The CID shall be warranted to be free from material and workmanship defects for a period of one year from date of shipment.

Cabling and Connectors

Supply cable and connectors of the appropriate length for the application stated.

a. 	General. Provide a traffic sensor-to-pole mounted cabinet cable equivalent to the Wavetronix SmartSensor cable.

(1) 	Cable. The cable shall be the Orion Wire Combo-2207-2002-PVCGY or an equivalent cable that conforms to the following specifications:

(a) 	The RS-485 conductors shall be a twisted pair.

(b) 	The RS-232 and RS-485 conductors shall have nominal capacitance conductor to conductor of less than 71 pF/Ft at 1 Khz.

(c) 	The RS-232 and RS-485 conductors shall have nominal conductor DC resistance of less than 16.5 ohms/1000 ft. at 20°C.

(d) 	The power conductors shall be a twisted pair with nominal conductor DC resistance of less than 11.5 ohms/1000 ft. at 20°C.

(e) 	Each wire bundle shall be shielded with an aluminum/mylar shield with a drain wire or the entire cable shall be shielded with an aluminum/mylar shield with a drain wire.

(2) 	Connector. The cable end connector shall meet the MIL-C-26482 specification and shall be designed to interface with the appropriate MIL-C-26482 connector. The connector backshell shall be an environmentally sealed shell that offers excellent immersion capability. All conductors that interface with the connector shall be encased in a single jacket, and the outer diameter of this jacket shall be within the backshell's cable O.D. range to ensure proper sealing. The backshell shall have a strain relief with enough strength to support the cable slack under extreme weather conditions. Recommended connectors are Cannon's KPT series, and recommended backshells are Glenair Series 37 cable sealing backshells.

b. 	General. Provide a pole mounted cabinet-to-traffic cabinet home-run cable.

(1) 	Cable. The home-run cable shall be the Alphawire 6023C or an equivalent cable that conforms to the following specifications:

(a) 	Operate between -20°C to 60°C

(b) 	Rated to 300 volts

(c) 	Conductor: Stranded Tinned Copper

(d) 	Insulation: Color-Coded Polypropylene

(e) 	Shield: Individually Foil Shielded Pairs

(f) 	Drain Wire: Stranded Tinned Copper

(g) 	UL Type CM, AWM 2493

(h) 	CSA CMG FT

SmartSensor Mount

a. 	General. Provide traffic sensor mounting assembly equivalent to the Wavetronix SmartSensor mount.

b. 	Mounting. The mounting assembly shall provide at least two axes of rotation to ensure proper installation.

(1) 	The mounting assembly shall be able to support at least a 15-lb. (6.8-kg) load.

(2)	The mounting assembly shall feature a symmetric hole pattern that mates with fixed and rotational SmartSensor back plates.

(3) 	The mounting assembly shall have two contact points with the pole.

(4) 	The mounting assembly shall be slotted for 3/4" banding.

c. 	Construction. The mounting assembly shall be constructed of 0.1875" thick or thicker aluminum with 316 stainless steel hardware.

(1) 	The mounting assembly shall be powder coated for oxidation resistance.

Installation Kit

a. 	General. Provide an installation kit equivalent to the Wavetronix Install Kit, for use while installing and configuring radar vehicle sensing devices (RVSDs) or continuous tracking advance detectors (CTADs), equivalent to the Wavetronix SmartSensor products, or in-cabinet contact closure and communication connectivity devices (ICD) equivalent to the Wavetronix Click! products.

b. 	Product Description. The RVSD, CTAD or ICD shall be installed and configured using a manufacturer supplied installation kit that includes the following elements: a handheld computer equivalent to the Socket Mobile SoMo 650, a serial to USB adapter equivalent to the Socket Serial USB to serial adapter, a Bluetooth to serial converter equivalent to the Click! 421, and pertinent documentation.

Smartsensor Cable Junction Box

For each radar sensor, provide a 6-conductor Type 4X cable junction box enclosure (WX-SS-710) to connect the Wavetronix 6-conductor pigtail cable (WX-SS-704) to the APT Matrix 2 homerun cable. Place this cable junction box in the upper portion of the nearest Type II traffic junction box; or controller cabinet foundation (for signal poles with traffic conduits running directly to the controller).

- Pan Tilt Zoom Video Camera System

- General.

  - System Hardware. Furnish only fully functional new equipment of the name and type as stated on the Plans or approved equal. To be considered an approved equal, equipment must meet or exceed the listed specifications.

    - Pan-Tilt-Zoom (PTZ) Camera. Furnish a Camera meeting the following specifications.

PAN-TILT ZOOM CAMERA SPECIFICATIONS

| Camera | Detail |
| --- | --- |
| Effective Pixels | Approx. 0.38 Megapixel |
| Minimum Illumination | Color: 1.4lx (F1.6, shutter 1/60sec, AGC ON, 50IRE[IP]) 0.9lx (F1.6, shutter 1/60sec, AGC ON, 30IRE[IP]), |
|  | B/W: 0.15lx (F1.6, shutter 1/60sec, AGC ON, Night Mode, 50IRE[IP]) 0.10lx (F1.6, shutter 1/60sec, AGC ON, Night Mode, 30IRE[IP]) |
| Signal System | NTSC standard |
| Electronic Shutter Speed | 1/1 to 1/10,000 s |
| Gain Control | Auto/Manual (-3 to 28 dB) |
| Exposure Control | Full auto, Shutter priority, Iris Priority, Manual |
| White Balance Mode | Auto, ATW, Indoor, Outdoor, One-push, Manual, Sodium vapour lamp |
| Lens Type | Auto-focus Zoom Lens |
| Zoom Ratio | Optical zoom 36x, Digital zoom 12x |
| Horizontal Viewing Angle | 57.8 to 1.7 degrees |
| Minimum Object Distance | 10 mm (wide) to 1500 mm (tele) |
| Pan Angle | 340 degrees |
| Pan Speed | 300 degrees/s (max) |
| Tilt Angle | 105 degrees |
| Tilt Speed | 300 degrees/s (max) |
| Tour Day/Night | 5 Yes |
| Wide-D | Yes (92 dB) |
| Noise Reduction | Yes |
| Image | Detail |
| Codec Image Size (H x V) | 704 x 576, 720 x 480, 640 x 480, 384 x 288, 320 x 240 |
| Video Compression Format | H.264, MPEG-4, JPEG |
| Codec Streaming Capability | Dual streaming |
| Maximum Frame Rate | 30 fps (H.264/MPEG-4/JPEG) |
| Scene Analytics | Detail |
| Intelligent Motion Detection | Yes |
| Network | Detail |
| Protocols | IPv4, IPv6, TCP, UDP, ARP, ICMP, IGMP, HTTP, HTTPS, FTP (client/server), SMTP, DHCP, DNS, NTP, RTP/RTCP, RTSP, SNMP (MIB-2) |
| ONVIF Software | Yes (Ver. 1.02) |
| Number of Clients | 5 |
| Authentication | IEEE802.1X |

PAN-TILT ZOOM CAMERA SPECIFICATIONS

SPECIFICATIONS Cont.

| Interface | Detail |  |
| --- | --- | --- |
| Ethernet | 10BASE-T / 100BASE-TX (RJ-45) |  |
| Card Slots | SD memory card x 1 (Compatible with the SD/SDHC standards) |  |
| Sensor Input | x2 |  |
| Alarm Output | x1 |  |
| General | Detail |  |
| Power Requirements | HPoE (IEEE802.3at compliant), AC24V |  |
| Power Consumption | Approx. 25W |  |
| Operating Temperature | 23 to 122° F (-5 to +50° C) |  |
| System Requirements | Detail |  |
| Operating System | Microsoft Windows 7 (32/64bit) – compatible |  |
| Web Browser | Microsoft Internet Explorer Ver. 6.0, Ver. 7.0, Ver. 8.0 Firefox Ver.3.5 (Plug-in free viewer only) Safari Ver.4.0 (Plug-in free viewer only) Google Chrome Ver.4.0 (Plug-in free viewer only) |  |
| Additional Equipment | Detail |  |
| Enclosure | Outdoor vandal resistant housing with heater and blower |  |
| SD Card Installed | Provide one (1) 120GB Class 10 SD card installed in each camera |  |
| Warranty | 3 years |  |

740-2.14 VEHICULAR SIGNAL HEADS.  Provide Light Emitting Diode, (LED) Signal Heads that conform to the following publications:

- Circular Indications: Vehicle Traffic Control Signal Heads:  Light Emitting Diode (LED) Circular Signal Supplement, 6/27/05 (ITE Publication ST-052). This is hereafter referred to as “VTCSH-Circular-05”.

- Arrow Indications: Vehicle Traffic Control Signal Heads – Light Emitting Diode (LED) Vehicle Arrow Traffic Signal Supplement, 7/1/07 (ITE Publication ST-054). This is hereafter referred to as “VTCSH-Arrow-07”.

“The applicable ITE Specification”, as used in this specification, means VTCSH-Circular-05 for circular LED indications and VTCSH-Arrow-07 for arrow LED indications.

- Signal Heads.

Use signal heads that: are the adjustable, vertical type with the number and type of lights specified; provide a light indication in one direction only; are adjustable through 360 degrees about a vertical axis; and are mounted at the location and in the manner shown on the Plans. Ensure that all vehicular signal heads at any one intersection, except for programmed visibility signal heads, are of the same make and type.

Programmed Visibility Signal Heads.

  - Indications provide a nominal 12 inch diameter circular or arrow indication.  Meet the VTCSH requirements for color and arrow configuration.

  - Provide each section with a 1 inch cutaway visor.

  - Provide each signal section with an adjustable connection that permits incremental tilting from 0 to 10 degrees above or below the horizontal while maintaining a common vertical axis through couplers and mounting axis in 5 degree increments.

  - The signal must be mountable with ordinary tools and capable of being serviced without tools.  Preset the adjustment at 4 degrees below the horizontal.

  - The visibility of each signal face must be capable of adjustment or programming within the face.  When programmed, each signal face's indication must be visible only in those areas or lanes to be controlled.  During dusk and darkness, a faint glow to each side will be permissible.

  - Program the head as recommended by the manufacturer and as directed by the Engineer.

Provide a removable aluminum tunnel visor with an open slot at the bottom for each optical unit.

Furnish housing, backplates and visors factory finished with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D3359, ASTM D3363 and ASTM D522. Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

  - LED Optical Units.  Use LED optical units and lenses meeting the requirement of the applicable ITE specification for all indications.  Also meet the following requirements:

    - Gaskets. Use one-piece EPDM (ethylene propylene rubber) gaskets to seal LED modules.

    - Markings. Provide LED Signal module with manufacturer applied markings listed in Section 3.6, Module Identification, of the applicable ITE Specification.  For circular indications marking shall include: “Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads: LED Vehicle Circular Traffic Signal Supplement (June 27, 2005).”  For arrow indication markings shall include: “Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads: LED Vehicle Arrow Traffic Signal Supplement (July 1, 2007).”

    - Compatibility. Use LED signal modules that are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

    - Testing Requirements.

        - All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

        - Burn-in. Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

        - Production Testing and Inspection.  Submit manufacturer’s certification that all tests in Section 6.3 of the applicable ITE Specification have been successfully completed on each LED module to be used on the project.

Show results of each individual test on the certification.

        - Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA “Nationally Recognized Testing Laboratory” do the following:

              - Perform an initial assessment of the manufacturer’s factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

              - Perform initial Design Qualification Testing as specified in Section 6.4 of the applicable ITE specification.

              - Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following sections of the applicable ITE specification:

6.4.2 Conditioning 
6.4.4.1 - 6.4.4.4 Luminous Intensity 
6.4.4.6 Chromaticity 
6.4.6.1 Current Consumption 
6.4.6.6 Power Factor 
6.4.6.7 Total Harmonic Distortion

              - Provide a certification label on each certified LED traffic signal module verifying the manufacturer’s factory and modules passed the tests listed in a. through c. above.

    - Warranty. Provide written warranty by the signal module manufacturer that covers defects in materials, workmanship, and compliance with the applicable ITE specification for a period of 60 months after the manufacture date.  No new LED module will be accepted if its manufacture date is more than 12 months before the date of installation.  Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules. The warranty does not include the cost of removing failed modules or reinstalling new modules. Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

  - Lens.  Use only clear lenses for all green signal modules.  Use lenses that meet the requirements of the applicable ITE Specification.

  - Housing.

  - Use polycarbonate housing material, meeting latest version of ITE equipment standards, for all parts of the housing, including the doors and end plates. Ensure all parts are clean, smooth, and free from flaws, cracks, blow holes, or other imperfections.

  - Use a one-piece housing with integral top, bottom, sides, and with square doors, for each signal section.

  - Use stainless steel for all exposed bolts, screws, hinges, pins, and door-locking devices.  Use stainless steel or approved non-ferrous, corrosion-resistant material for all interior screws and fittings.

  - Provide an opening in the top and bottom of each housing to accommodate standard 1-1/2 inch pipe fittings and brackets.

  - Provide the top and bottom openings of each housing with integral serrated bosses that will provide positive positioning of the signal head in 5-degree increments to eliminate undesirable rotation or misalignment of the signal head as well as between sections.  Provide a total of 72 teeth in the serrated boss.  Ensure teeth are clean and sharp to provide positive position with the grooves of the mating section or framework.

  - Fasten individual signal sections together with a cadmium-plated tri-stud connector, lock washers, and nuts with access holes for the passage of electrical conductors form one section to another.

  - Provide 2 integral hinge lugs on the left side of each signal housing for mounting the door.

  - Provide 2 latches with stainless steel wing nut assemblies on the right side of each signal housing to engage the door latches.

  - Provide each signal housing door opening with a one-piece EPDM gasket around the periphery to provide a weather tight seal in a NEMA Type 3R enclosure.

  - Provide a round opening designed to accommodate any standard traffic signal lens in each signal housing door.

  - Backplates.  Backplates shall not be louvered.  Install backplates around vehicular signal faces except post mounted flashers.  Furnish backplates constructed of 0.100 inch minimum thickness aluminum alloy sheet meeting ASTM B209, alloy 3003-H14.  For those backplates fabricated from 2 or more pieces of sheeting, furnish them fastened together with 3/16" aluminum rivets or bolts peened after assembly.

Furnish 3 inch wide backplates regardless of where the signals are installed, on mast arms, on top of posts, or on the sides of poles.

  - Signal Mounting Hardware: Furnish elevator plumbizers, elbow pipe fittings, and post top adapters (without a terminal compartment) with integral serrated contacts that feature 72 teeth.

Provide signal heads that will be mounted on mast arms or pipe tenons with ferrous or bronze elevator plumbizers.

For signal faces installed on the sides of poles, furnish signal frames that consist of watertight assemblies of 1 1/2 inch nominal diameter standard steel pipe, malleable iron or brass pipe fittings, and bronze terminal compartments.  The side of the terminal compartment opposite the door shall feature a saddle shape for wobble free mounting on round poles and include a cable guide and two holes for mounting the compartment.

Furnish vehicular signal frames with a horizontal dimension between the center of the terminal compartment and the axis of the adjacent signal face of 22 inches in side mounted frames and 11 inches on double headed post top installations.

Post top adapters shall slip fit over 4 inch nominal standard pipe and feature two rows of three cadmium plated steel setscrews.  Furnish post top adapters with terminal compartments, except one way signal heads may be installed on adapters without a terminal compartment provided the adapters include offset openings.  Post top adapters without a terminal compartment or compartments - provide manufactured of bronze metal.

Furnish terminal compartments with a terminal block containing 12 poles, each with two screw type terminals.  Each terminal must accommodate at least three 14 AWG conductors.  Provide terminal compartments with a rain tight door that provide ready access to the terminal block.

For mounting each terminal compartment, furnish (2) 1/2" x 13 hot dip galvanized bolts that conform to ASTM A325 and (2) 1/2" hot dip galvanized washers that conform to ASTM F 436.

When replacing signal heads include all mounting hardware, backplates and visors.

  - Finish. Factory finish housing, brackets, fittings, backplates, and visors, each face, with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363, and ASTM D-522.  Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

740-2.15 PEDESTRIAN SIGNALS. Use LED Pedestrian Countdown modules that use the international "HAND/WALKING PERSON" symbols.  Except for the countdown indication and as otherwise noted in this specification, use modules that conform to “Pedestrian Traffic Control Signal Indications - Part 2: Light Emitting Diode (LED) Pedestrian Traffic Signal Modules” Institute of Transportation Engineers, 3/19/2004, (hereafter referred to in this document as “PTCSI-04”) and to the applicable Sections of the current Alaska Traffic Manual.

Provide pedestrian signal heads according to the following:

  - Pedestrian Signal Modules: Provide Portland Orange “HAND” and “COUNTDOWN DIGITS” and lunar white “WALKING PERSON.”   Locate COUNTDOWN DIGITS adjacent to the associated UPRAISED HAND.    Make “HAND” and “WALKING PERSON” symbols a minimum of 11 inches high and 7 inches wide and COUNTDOWN DIGITS a minimum of 9 inches high and 7 inches wide.  Provide incandescent looking WALKING PERSON, HAND and COUNTDOWN DIGITS.  Ensure the WALKING PERSON, UPRAISED HAND and COUNTDOWN DIGITS are not readily visible when not illuminated.  Provide “AlInGaP” Portland Orange LEDs or equivalent, rated for 100,000 hours or more at 77ºF and 20 mA. Provide “InGaN” White LEDs.

Make all exposed components of modules suitable for prolonged exposure to the environment, without appreciable degradation that would interfere with function or appearance.

Provide modules with an installed gasket to seal the junction with the signal housing.

  - Lens.  Use modules with internal masks to prevent the icons and digits from being visible when not in operation. No external silk-screen is permitted. Provide a smooth or textured lens of transparent polycarbonate material, frosted to prevent sun phantom. Use lenses that will not crack, craze or yellow due to solar UV exposure typical for a south-facing Arizona desert installation, after a minimum of 60 months in service.

  - Retrofit.  When a module will replace an existing module in an existing signal housing, furnish signal modules designed as retrofit replacements for existing neon type pedestrian signals (ICC 4090 and/or 4094).  Provide modules that do not require special tools for installation. Provide modules that fit securely into existing pedestrian signal housings without any modification to the housing, connect directly to existing electrical wiring, and form a weather-tight seal. Provide modules and components constructed so each retrofit of existing pedestrian signals only requires the removal of the existing neon message module, gasket, and power supply and installation of the new LED pedestrian countdown module. Provide all necessary components to complete conversion including a one piece gasket.

  - Photometric Requirements.  Meet the following requirements:

    - Minimum Luminance.  Maintain the following minimum luminance values for at least 60 months, under the operating conditions defined in Sections 3.3.1 and 5.2.1 of PTCSI-04 (when measured normal to the plane of the icon surface):

        - WALKING PERSON 2,200 cd/m2,

        - UPRAISED HAND 1,400 cd/m2,

        - DIGITS 1,400 cd/m2 (when “88” is displayed).

    - Maximum Luminance.  Provide modules for which the actual luminance of a module does not exceed three times the minimum maintained luminance, as defined in Section 4.1.1 of PTCSI-04,  when operated within the temperature range -40°F to +165°F

    - Uniformity:  Provide modules for which the uniformity of the signal output across the emitting section of the module lens (i.e. icons or digits) does not exceed a ratio of 5 to 1 between the maximum and minimum luminance values as measured in 0.5 in. diameter spots.

    - Markings. Permanently mark the back of each LED signal module with:

        - Manufacturer’s name, trademark, and other necessary identification

        - Warranty information

        - Rated voltage and power consumption in volt-amperes

        - An up arrow or the word “UP” or “TOP” for orientation within a signal housing.

  - Electrical. Provide LED pedestrian countdown signal modules that:

    - are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

    - have a maximum of 4 each secured, color coded, 36 inches long, 600V, 18 AWG minimum, jacketed wires, conforming to the National Electrical Code, rated for service at +221ºF for electrical connection.

    - operate from a 60 ±3 Hz AC line over a voltage range of 80 VAC to 135 VAC. Test voltage for all photometric performance measurements shall be 120 ±3 volts rms.

    - use LED circuitry that prevents perceptible flicker over the voltage range specified above.

    - include voltage surge protection against high-repetition noise transients and low-repetition noise transients as stated in Section 2.1.8, NEMA Standard TS-2, 2003.  Module must meet the following test requirements:  Section 8.2 IEC 1000-4-5 & Section 6.1.2 ANSI/IEEE C62.41.2, 3kV, 2 ohm and Section 8.0 IEC 1000-4-12 & Section 6.1.1 ANSI/IEEE C62.41.2, 6kV, 30 ohm.

    - have a current draw sufficient to ensure compatibility and proper triggering and operation of load current switches and conflict monitors in signal controller units. When the module is switched from the On state to the Off state the terminal voltage shall decay to a value less than 10VAC RMS in less than 100 milliseconds when driven by a maximum allowed load switch leakage current of 10 milliamps peak (7.1 milliamps AC).

    - have a maximum power consumption at 77°F of:  Hand 11.0 watts, Walking Person 8.0 watts, Digits 10.0 watts (when display shows “88”)

    - have waterproof strain relief and anti-capillary wires, or have electrical wires that do not penetrate the LED module housing.  This is intended to prevent water seepage between the back cover and the electrical wires, or between the copper and insulation of the wires (Connection may be made by use of an over molded connector).

    - will default to the hand symbol for abnormal conditions when nominal voltage is applied to the unit across the two phase wires (rather than being applied to the phase wire and the neutral wire).

    - have three separate power supplies: one each for the Walking Person, the Upraised Hand and the countdown digits.  Use separate circuitry to power the LED Walking Person icon and the LED Upraised Hand icon, in order to virtually eliminate the risk of displaying the wrong icon.

  - Testing Requirements.

    - All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

    - Burn-in.  Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

    - Production Testing and Inspection by Manufacturer    Submit manufacturer’s certification that all tests in Section 6.3 of PTCSI-04 have been successfully completed on each LED module to be used on the project.  Show result of each individual test on the certification.

    - Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA “Nationally Recognized Testing Laboratory” do the following:

        - Perform an initial assessment of the manufacturer’s factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

        - Perform initial Design Qualification Testing as specified in Section 6.4 of the PTCSI-04.

        - Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following sections of PTCSI-04:

6.4.2 Conditioning 
6.4.4.1 - 6.4.4.4 Luminous Intensity 
6.4.4.6 Chromaticity 
6.4.6.1 Current Consumption 
6.4.6.6 Power Factor 
6.4.6.7 Total Harmonic Distortion

        - Provide a certification label on each certified LED traffic signal module verifying the manufacturer’s factory and modules passed the tests listed in a. through c. above.

  - Warranty. Provide a manufacturer’s written warranty that covers defects in materials, workmanship, and compliance with PTCSI-04 for a period of 60 months after the manufacture date.  No new LED module will be accepted on a project if its manufacture date is more than 12 months before the date of installation. Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules. The warranty does not include the cost of removing failed modules or reinstalling new modules. Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

  - Countdown Module Functions.

    - General.  Begin the countdown at the beginning of the FLASHING HAND indication.  End the countdown at “0” at the end of the FLASHING HAND indication.  Make the countdown display dark from the end of one FLASHING HAND indication until the beginning of the next. Display steady, not flashing, countdown digits.  Do not provide user accessible switches, controls, or options that would allow modification of cycle time, icons, digits or that would allow the countdown to operate while the WALKING PERSON or STEADY HAND is displayed.

    - Learning Cycle.  At power on, make the countdown display dark for one learning cycle in which it will determine the duration of the FLASHING HAND indication.

    - Normal Operation.  Display the countdown/FLASHING HAND for the duration measured in the learning cycle for every cycle until the module measures a different FLASHING HAND duration.

    - Countdown Duration Modification.  When a different duration is measured, make the countdown dark for the next cycle, and enter a Learning Cycle as previously described. Resume Normal Operation with the new FLASHING HAND duration if the measured FLASHING HAND duration for the next cycle is the same as for the first cycle when a change was detected. Continue Learning Cycles, if the duration is different, until the measured FLASHING HAND duration is the same for two cycles. Resume Normal Operation with the new duration when that happens.

    - Countdown Truncation.  Make the digits dark if the controller output displays a STEADY HAND or if both the HAND and WALKING PERSON go dark, regardless of whether the countdown to zero has been completed.

    - Preemption.  Handle preemption events as described under Countdown Duration Modification and, if necessary, Countdown Truncation.

    - Recycling.  Allow for consecutive cycles without display of the STEADY HAND .

    - Power Outage.  Maintain an uninterrupted countdown during short power failures (<1.5 seconds).  Make the digits dark after a loss of power of more than 1.5 seconds and enter a Learning Cycle when the power is restored.

- Housing

  - Provide signal housings that have a maximum overall dimensions of 18-1/2 inches wide, 18-3/4 inches high, and 9 inches deep.

  - Provide a dustproof and weatherproof housing that allows easy access to and replacement of all components.

  - Provide a one-piece, corrosion-resistant, aluminum-alloy die-cast case complete with integrally cast top, bottom, sides and back. Provide 4 integrally cast hinge lug pairs, 2 at the top and 2 at the bottom of each case, for operation of a swing-down door.

  - Provide 1 of the following 3 versions of the case, according to project specifications:

    - Clamshell mount, with hardware, for “pole left of message” installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight. No other openings are allowed.

    - Clamshell mount, with hardware, for “pole right of message” installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight. No other openings are allowed.

    - Make suitable for either post top or bracket mounting with upper and lower openings to accommodate standard 1-1/2 inch pipe brackets.  Plug unused openings to be weathertight. This case is only allowed when called for in the plans.  Integrally cast a shurlock boss into the bottom opening of the signal case. Make the dimensions of the shurlock boss as follows: outside diameter, 2-5/8 inch; inside diameter, 1-31/32 inch; number of radial teeth, 72; and depth of teeth, 5/64 inch. Use clean and sharp teeth that provide full engagement to eliminate rotation or misalignment of the signal.

  - Make the door frame a one-piece, corrosion-resistant, aluminum-alloy die-casting, complete with 2 hinge lugs cast at the bottom and 2 latch slots cast at the top of each door. Attach the door to the case by means of two Type 304 stainless steel spring pins. Attach 2 stainless steel hinged bolts with captive stainless steel wing nuts and washers to the case with the use of stainless steel spring pins. Provide a door that will latch and unlatch without the use of tools.

- Conductors:  Meet IMSA specifications 20-1 with No. 14 AWG or larger.

- Load Switches: Place all load switches for operation of pedestrian signals in the controller cabinet.

- Fasteners.  Use machine screws, studs, and washers that are stainless steel.

- Gaskets:  Use gaskets that conform to ASTM D1056, Grade 2C2.

- Terminal Blocks:  Provide a rain tight terminal compartment with a 12 position terminal block.

- Finish.  Factory finish the outside of pedestrian signal head housings and visors and signal visor interiors with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D3359, ASTM D3363 and ASTM D522. Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

740-2.16 PEDESTRIAN PUSH BUTTONS.  Push buttons shall be Tamper proof with a 2 inch minimum diameter convex 316 stainless steel actuator button.

Construct a weatherproof assembly designed to prevent an electrical shock under any weather condition and grounded per the NEC.

Push Button Switch.  Furnish Polara model RBDLM2-B-4H or approved equal with the following features.  Provide a solid state electronic piezo type, switching unit, with screw type terminals, rated 15 amperes at 125 VAC.  Must have the following characteristics:

            - Switching unit that is solid state electronic piezo rated for 100 million cycles.

            - Sealed to prevent ice from impeding function.

            - Must hold the call for a minimum of 5 seconds.

            - Switch operating force of 3 pounds or less with no moving plunger or moving electrical contacts.

            - Provide an LED indication and an audible tone or beep within the button when pushed.

            - Must have a raised rim or ridges to protect the button from side impacts.

            - Powder coated cast switch housing.

Where a pedestrian push button is to be mounted on top of a 2-1/2 inch diameter post, provide the housing with a slip-fitter with screws for securing to the post.

Factory finish pedestrian push button housings, mountings, brackets, and fittings with 2 coats of dull black enamel or powder coat.  Painting/powder coating is not required where the color is an integral part of the component material.

740-2.17 FLASHING BEACONS.  Furnish beacons that consist of one or more traffic signal sections meeting the requirements of Subsection 740-2.14 Vehicular Signal Heads. See the Plans for the number, size and color of the signal sections required for each beacon.

            - Use the flasher in signal controller cabinets to energize beacons that flash continuously and are installed near traffic signals.

When a signal controller cabinet flasher is used to energize a beacon, furnish a two pole, fused block with built in fuse pullers to protect the flasher.  Furnish third party certified blocks that hold 13/32" x 1-1/2" midget ferrule fuses, are rated for 30 amperes, and feature tubular screw terminals that accommodate conductors to 8 AWG.  Furnish blocks with two fast acting, 3 ampere (BAF-3) fuses, and flat bases that can be directly mounted on a dead panel.

740-2.18 ROADWAY LUMINAIRES.  Furnish luminaires that conform to the following specifications and provide the light distributions specified.  When luminaire performance criteria are specified, luminaires shall also:

- Meet or exceed the minimum initial light levels indicated.

- Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified:  luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses (when used) and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8, dated 2000.

Furnish each luminaire with a high pressure sodium lamp or LED of the wattage specified and matching ballast with an input voltage equal to circuit voltage.

Luminaries General

Install luminaires that feature:

- Corrosion resistant enclosures with gray painted finish, cooling elements not required to be painted, and space for the ballast.

    - Painted or finished luminaire surfaces exposed to the environment shall exceed a rating of six (6), after 1,000 hours or four (4) of 5,000 hours salt spray test according to ASTM D1654 and ASTM B117 testing. The coating shall exhibit no greater than 30% reduction of gloss, according to ASTM D523, after 500 hours of ASTM G154 Cycle 6 QUV® accelerated weathering testing.

- All luminaires shall have ANSI C136.15 external labels and ANSI C136.22 internal labels. The luminaire shall be listed for wet locations by a nationally recognized testing laboratory (NRTL) as defined by OSHA and shall be in compliance with UL 8750 and UL 1598. It shall be identified as such by a tag/sticker on the inside of the luminaire.

- All hardware shall be stainless steel or suitably corrosion resistant to match the 20-year expected life of the fixture. Captive screws are required on any component that requires maintenance after installation.

- Glass lenses, unless polycarbonate resin refractors are specified.

- Terminal blocks for attaching the illumination tap conductors.

- Aluminum reflectors with an ALZAK or ALGLAS finish when using HPS fixtures.

- Optical components free of substances that affect photometric performance, paint.

- Housings cast with no provision for a photoelectric control receptacle.

- For HPS fixtures; airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components, gasket material must withstand the temperatures involved and be securely held in place.

- For HPS fixtures include plug in starting aids with lamps through 400 watts.

- Luminaries – High Pressure Sodium; Cobrahead and Offset/Turnpike

Furnish HPS fixtures that feature a rated life of 40,000 hours based on 10 hours per start and ballasts that conform to Subsection 740-2.21. Each cobrahead or offset luminaire shall also include:

  - An easily removed hinged door used exclusively for mounting the ballast.

  - A second door that frames the lens (for HPS), hinges on the house side, and fastens on the street side with an automatic type latch.

  - A two (2) or four (4) bolt mounting brackets that is designed to fit a 2-inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

- Luminaires - LED

  - General. The luminaire shall be assembled in the United States and shall be assembled by and manufactured by the same Manufacturer. For easy removal, quick-connect/disconnect plugs shall be supplied between the discrete electrical components within the luminaire such as the driver, surge protection device, and optical assembly. The quick-connect/disconnect plugs shall be operable without the use of tools and while insulated gloves are worn. The luminaire shall be in compliance with ANSI C136.37 LED light source(s), and driver(s) shall be compliant with the Restriction of Hazardous Substances (RoHS) Directive 2011/65/EU.

    - Manufacturer Experience. The luminaire shall be designed to be incorporated into a lighting system with an expected 20-year lifetime. The luminaire Manufacturer shall have a minimum of 20 years’ experience manufacturing high-intensity discharge (HID) roadway luminaires and shall have a minimum of 5 years’ experience manufacturing LED roadway luminaires. The Manufacturer shall have a minimum of 5,000 total LED roadway luminaires installed on a minimum of 30 separate installations, all within the United States.

  - Housing. The housing shall be designed to ensure maximum heat dissipation and to prevent the accumulation of water, ice, dirt, and debris. A passive cooling method with no moving or rotating parts shall be employed for heat management. The effective projected area of the luminaire shall not exceed 1.2 sq. ft. The total weight of the luminaire(s) and accessories shall not exceed 55 lb.

  - Optical Assembly. The LED optical assembly, consisting of LED packages, shall have a minimum ingress protection rating of 66 (IP66) as defined in ANSI/IEC 60529. Circuiting shall be designed to minimize the impact of individual LED failures on the operation of the other LEDs.

The optical assembly shall utilize high-brightness, long-life LEDs with a minimum color rendering index (CRI) of 70, 3000 K (+/- 300 K) color temperature, and binned according to ANSI C78.377. Lenses shall be UV-stabilized acrylic or glass. Provisions for house-side shielding shall be specified along with means of attachment.

Lumen depreciation at 50,000 hours of operation shall not exceed 15% of initial lumen output at the specified LED drive current and an ambient temperature of 77°F (25°C).

The assembly shall have individual serial numbers or other means for Manufacturer tracking.

    - Photometric Performance Testing.  Luminaires shall be tested according to IES LM-79. The laboratory performing this test shall hold accreditation from the National Voluntary Laboratory Accreditation Program (NVLAP) under NIST. Submitted reports shall have a backlight, uplight, and glare (BUG) rating according to IESNA TM-15, including a luminaire classification system graph with both the recorded lumen value and percent lumens by zone.

Lumen maintenance shall be measured for the LEDs according to LM-80, or when available for the luminaires according to LM-84. The LM-80 report shall be based on a minimum of 6000 hours; however, 10,000-hour reports shall be provided for luminaires in cases in which tests have been completed.

Thermal testing shall be provided according to UL 1598. The luminaire shall start and operate in the ambient temperature range specified. The maximum rated case temperature of the driver, LEDs, and other internal components shall not be exceeded when the luminaire is operated in the ambient temperature range specified.

Mechanical design of protruding external surfaces such as heat sink fins shall facilitate hose-down cleaning and discourage debris accumulation. Testing shall be submitted when available to show that the maximum rated case temperature of the driver, LEDs, and other internal components are not exceeded when the luminaire is operated with the heat sink filled with debris.

    - Calculations.  Complete point-by-point luminance and veiling luminance calculations as well as listings of all indicated averages and ratios as applicable shall be provided according to IES RP-8 recommendations. Lighting calculations shall be performed using AGi32 software with calculations performed to two decimal places (i.e., x.xx cd/m2). Calculation results shall demonstrate that the submitted luminaire meets the lighting metrics specified in the plans. Scotopic or mesopic factors will not be allowed.

    - Lumen Maintenance Projection.  The LEDs shall have long-term lumen maintenance documented according to IESNA TM-21, or when available for the luminaires according to IESNA TM-28. The submitted calculations shall incorporate an in situ temperature measurement test (ISTMT) and LM-80 data with TM-21 inputs and reports according to the TM-21 calculator, or when available an ISTMT and LM-84 data with TM-28 inputs and reports according to the TM-28 calculator. Ambient temperature shall be 77°F (25°C).

  - Driver.  The driver for the luminaire shall be integral to the unit. It shall be mounted in the rear of the luminaire on the inside of a removable door or on a removable mounting pad. The removable door or pad shall be secure when fastened in place, and all individual components shall be secured upon the removable element. Each component shall be readily removable from the removable door or pad for replacement.

The driver shall be installed in a manner to keep it mechanically separated from the LED array heat sink.

    - Circuit Protection. The driver shall tolerate indefinitely open and short-circuit output conditions without damage.

    - Ingress Protection. The driver shall have an IP65 or IP66 rating.

    - Input Voltage. The driver shall be suitable for operation over a range of 120 to 277 V or 347 to 480 V as required by the system operating voltage.

    - Operating Temperature. The driver shall have an operating ambient temperature range of      -40°F to 131°F (-40°C to 55°C).

    - Driver Life. The driver shall provide a lifetime of 100,000 hours at an ambient temperature of 77°F (25°C).

    - Safety/UL.  The driver shall be listed under UL 1012 or UL 1310.

    - Power Factor.  The driver shall maintain a power factor of 0.9 or higher and total harmonic distortion of less than 20%.

    - Driver Efficiency.  The driver shall have a minimum efficiency of 90% at maximum load and a minimum efficiency of 85% for the driver operating at 50% power, with driver efficiency defined as output power divided by input power.

    - Electrical Interference.  The driver shall meet the electromagnetic compatibility (EMC) requirements for Class A digital devices included in the FCC Rules and Regulations, Title 47, Part 15.

    - Thermal Fold Back.  The driver shall reduce the current to the LED module if the driver is overheating as a result of abnormal conditions.

    - Dimming.  The driver shall have 0 to 10 V dimming capability.

    - Leakage Current.  The driver shall comply with safety standards according to IEC 61347-1.

  - Surge Protection Device (SPD).  SPD shall be labeled as Type 4 in accordance with UL 1449 and be an integral part of the luminaire. It shall provide a minimum system protection level of 10 kV, 10 kA. To protect for a 10 kV, 10 kA surge the required clamping voltage of the external metal oxide varistor (MOV) or other SPD shall be lower than 1 kV at 8 kA {(10 kV – 2 kV)/1 ohm = 8 kA}.

The SPD shall comply with the following standards:

    - IEEE C62.41.1, IEEE Guide on the Surge Environment in Low-Voltage (1000 V and Less) AC Power Circuits,

    - IEEE C62.41.2, IEEE Recommended Practice on Characterization of Surges in Low-Voltage (1000 V and Less) AC Power Circuits,

    - IEEE C62.45, IEEE Recommended Practice on Surge Testing for Equipment Connected to Low-Voltage (1000 V and Less) AC Power Circuits, and

    - ANSI C136.2, American National Standard for Roadway and Area Lighting Equipment — Luminaire Voltage Classification.

The SPD and performance parameters shall be posted at www.UL.com under category code VZCA2.

  - Photoelectric Control.  Furnish fixtures with a built in ANSI C136.41 7-pin twist type photo cell receptacle. Receptacles shall be provided with shorting caps.

  - Warranty.  The entire luminaire and all of its component parts shall be covered by a 10-year warranty. Failure is defined as when one or more of the following occur:

    - Negligible light output from more than 10% of the LED packages,

    - Moisture inside the optical assembly,

    - Driver that continues to operate at a reduced output, and/or

    - Other failed conditions that do not meet specifications.

The warranty period shall begin on the date of final acceptance of the lighting work as documented in the Resident Engineer’s project notes.

  - Submittal Requirements.  The Contractor shall submit, for approval, an electronic version of all associated luminaire IES files, AGi32 files, and the TM-21 or TM-28 calculator spreadsheet with inputs and reports associated with the project luminaires. The Contractor shall also provide an electronic version of each of the following Manufacturers’ product data sheets for each type of luminaire.

    - Descriptive literature and catalog cuts for luminaire, LED package, driver, and surge protection device;

    - LED drive current, total luminaire input wattage, and total luminaire current at the system operating voltage or voltage range and ambient temperature of 77°F (25°C);

    - Luminaire efficacy expressed in lumens per watt (lpw) per luminaire;

    - Initial delivered lumens at the specified color temperature, drive current, and ambient temperature;

    - Computer photometric calculation reports;

    - TM-15 BUG rating report;

    - Certification of Manufacturers’ experience and certification that luminaires were assembled in the United States;

    - Supporting documentation of compliance with ANSI standards, as well as listing requirements;

    - Supporting documentation of laboratory accreditations and certifications for specified testing;

    - Thermal testing documents;

    - IES LM-79, LM-80 (or LM-84), and TM-21 (or TM-28) reports;

    - Salt spray (fog) test reports and certification;

    - Vibration characteristics test reports and certification;

    - IP test reports;

    - Manufacturer written warranty; and

    - Luminaire installation, maintenance, and washing instructions.

- Lenses

When polycarbonate resin lenses are specified, the fabricator shall furnish certified lenses conforming to the following criteria:

a.	The lenses are molded in a single piece from virgin polycarbonate resin.

b.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

c.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

d.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

e.	The resins used meet the requirements for the self-extinguishing classification of ASTM D 635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D 256, Method A, using a 1/8 inch by 1/2 inch bar molded according to ASTM recommended practice.

740-2.20 ILLUMINATION CONTROL.  Use photoelectric controls capable of directly switching multiple lighting systems. Furnish photoelectric units designed for pole top mounting which include a slip-fitter, terminal block, and cable supports or clamps to support pole wires.

- Photoelectric Unit.  A light sensitive element connected directly to a normally closed, single-pole throw control relay without intermediate amplifications. Plug the unit into a phenolic resin twist lock receptacle set in a cast aluminum mounting bracket with a threaded base. Screen photoelectric units to prevent artificial light from causing cycling.

Use either horizontal sensing or zenith sensing type units meeting the following:

  - A supply voltage rating of 60 Hz, 105-277 volts

  - A maximum rated load at a minimum of 1,800 volt-amperes

  - An operating temperature range from -40 °F to +150 °F

  - A power consumption of less than 10 watts

  - A unit base with a 3-prong, EEI-NEMA standard, twist-lock plug mounting

Furnish units for highway lighting that have a “turn-on” between 10.8 and 54 lux and a “turn-off” at between 1.5 and 5 times “turn-on.”

Furnish units for illuminated signs that have a “turn-on” level of between 215 and 270 lux. (“Turn-on” level specified above corresponds to a switching level of approximately 430 to 540 lux measured in the horizontal plane.) "Turn-off" level must not exceed 3 times “turn-on” level.

- Temperature Switch.  When mercury vapor sign lighting fixtures are used, provide a temperature switch in each photoelectric control circuit for lighting systems which will:

  - bypass the photoelectric unit when the ambient temperature drops to -13 °F, and energize the mercury vapor light circuits;

  - return switching functions to the photoelectric unit upon a temperature rise of 5 to 10 °F above the turn-on temperature; and

  - have a minimum range of (-40 F to +40 F), and be setable in increments no greater than 5 F.

740-2.21 BALLASTS.  Include ballasts for high intensity discharge lamps as an integral part of each luminaire and design for the voltages and lamp types specified in the Plans or Special Provisions. Ensure that the current needed to start the lamps is less than the operating current.

Furnish regulator-type ballasts with copper windings electrically isolated from each other, which will start and operate the lamps in temperatures down to -40 °F. The allowable line voltage variation is plus and minus 10%.

Equip high-pressure sodium luminaires, except those with 1000 watt lamps, with magnetic regulator ballasts with the following additional operating characteristics:

- The lamp wattage regulation spread at any time over the life of the lamp must not exceed 18% of nominal lamp watts at plus and minus 10% line voltage variations.

- With nominal line and lamp voltages, the ballast must regulate the lamp output to within 5% of the ballast design center, and sustain lamp operation with a minimum 60% voltage drop lasting 4 seconds or less.

Equip luminaires with 1000 watt high pressure sodium lamps with auto-regulator ballasts that provide a maximum 30% lamp regulation spread, a minimum 35% voltage dip tolerance, and with nominal line and lamp voltages regulate lamp output to within 5% of the ballast design center.

Furnish ballasts, for soffit luminaires, with mounting brackets attached and equip with terminal blocks for primary connections and lamp socket preconnected to the secondary for flush mounted luminaires and with terminal blocks for both primary and secondary connections for use with suspended luminaires.

Submit the ballast manufacturer’s specification sheets for review and approval.

740-2.23 TRAFFIC SIGNAL COMMUNICATIONS SYSTEM.  Furnish only fully functioning new equipment of the brand and type listed or approved equal. To be considered an approved equal equipment must meet or exceed the listed specifications. The products listed in this subsection are subject to review and approval if they are included on the Materials Certification List (MCL).

            - Broadband Ethernet Radio Interconnect System.

The contractor shall provide a 5GHz Broadband Wireless Ethernet Radio Interconnect System. The system shall be the Intuicom Nitro58™ Wireless Solutions or an approved equal meeting the following minimum specifications:

- Comply with FCC part 15 and IC RSS-210 rules/regulations.

- Support and provide the following wireless protocols:

    - IEEE 802.11a (OFDM)

    - IEEE 802.11n (MIMO 2x2:2, OFDM)

    - Proprietary Wireless Protocol

- Shall be available in the following wireless hardware configurations:

    - 108Mbps – Integrated Panel Antenna or Stand Alone Radio

    - 216Mbps – Stand Alone (Dual) Radio

    - 432Mbps - Access Point Cluster (Quad) Radio

    - 300Mbps – 802.11n Integrated Panel Antenna

- All Radios shall contain embedded GPS for automatic Geo-location of fixed or mobile wireless locations.

- Integrated Panel Antennas must contain an external status panel which combines Received Signal Strength Indicators (RSSI), Power Indicator, and a Reset Button.

- Radios include Adaptive Modulation, Dynamic Frequency Selection, Automatic Transmit Power Control – RF link is monitored to automatically adjust the data rate to optimize the maximum link performance.

- Any Radio shall be configurable as an Access Point, Remote, Repeater and Mesh Node.

- The manufacturer and/or supplier of the Radio will be located in the North America with performance testing over the Radio’s operating temperatures of -40° to +85 C. Shall be IP67 and NEMA exceeding environmental specifications.

- Detailed Requirements:

    - Operating Frequency: 5.150 – 5.825 GHz

    - Ethernet: Auto-sensing 10/100/1000BASE-T Ethernet

    - Electrical: Gigabit PoE Compliant (IEEE 802.3af/at)

    - Receiver Sensitivity: -74 to -94dBm

    - Peek Transmit Power: 802.11a (Up to 28dBm), 802.11n (Up to 27dBm, +/- 2dBm)

    - Channel Width: 5, 10, 20, 40 MHz

    - Range: 20+ miles-LOS

    - Supported Network Topologies: Point to Point, Point to Multipoint, Mesh

    - Wireless Security Options:

- 802.11i WPA/WPA2 (PSK, EAP), AES-CCM, TKIP, 802. 1X, RSN.

- Radius Authentication

- MAC Access Control List

- User Login Controls

    - Support the minimum IEEE Networking Features:

- 802.11e (WMM & QoS)

- 802.11h (DFS & TPC)

- 802.1d (Ethernet Bridging)

- 802.1p (Traffic Prioritization)

- 802.1q (VLAN)

- 802.1w (Rapid Spanning Tree)

- 802.3ac (802.1q & 802p support)

- 802.3ad (Link Aggregation)

- 802.3x (Full Duplex and Flow Control)

    - Minimum Wireless Software Features:

- Automatic Geolocation of embedded GPS radios

- Icon roll over feature displays latitude and longitude coordinates of radios

- Customizable Menu Interface

- Automatically discover, organize, configure radios in network tree

- Provide a “Drag and Drop” radio configuration tool

- A color coded display of network-wide wireless diagnostics illustrated on map

- Data Rate, RSSI, Client Connection Quality

- Provide Wireless Alert Reporting

- A unique slider control allowing users to adjust upper and lower alert limits

- Network Management Capabilities

    - Firewall, ARP/Bridge Tables, Spanning Tree, Data Throughput

    - IP Discovery, IP/Subnet Configuration, IP Conflict Tool

    - Ping Watchdog

- Real-time wireless diagnostic tools

- Bandwidth Test Tool, RSSI and CCQ

- Spectrum Analysis with AP Scan Tool

- Audio Antenna Aiming Tool

- Advanced User Control

    - Terminal Window, Telnet, SSH2

    - Dynamic Routing (BGP+, OSPFv3 and RIP protocols)

    - Sniffer and Fetch tools

    - IPV6 support

    - DNS

CFHWY00317

Blank Page

APPENDIX A

CONSTRUCTION SURVEY REQUIREMENTS

Blank Page

APPENDIX B

ENVIRONMENTAL PERMITS

Blank Page

APPENDIX C

MATERIAL CERTIFICATION LIST

Blank Page

APPENDIX D

SIGN SHOP DRAWINGS

Blank Page

APPENDIX E

TEMPORARY CONSTRUCTION EASEMENTS

TEMPORARY CONSTRUCTION PERMITS

Blank Page

APPENDIX F

ARRC DRAFT TEMPORARY CONSTRUCTION pERMIT AND

LETTER OF NO OBJECTION

Blank Page