SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

1.	Publications.  The following are available from the Plans Room, download online, or as noted:

a.	Standard Specifications for Highway Construction, 2020 Edition comb bound ($25.00), download at:

www.dot.state.ak.us/stwddes/dcsspecs/assets/pdf/hwyspecs/sshc2020.pdf, or order bound book from LuLu at:

https://www.lulu.com/en/us/shop/state-of-alaska-dept-of-transportation/2020-alaska-standard-specification-for-highway-construction/paperback/product-1gq9j9qk.html

b.	Alaska Test Methods Manual (Lab & Field), April, 2021 Edition ($25.00). Available online at:

www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/testman.shtml

c.	Alaska Storm Water Pollution Prevention Plan Guide, March 2017.

www.dot.state.ak.us/stwddes/desenviron/resources/stormwater.shtml

d.	Utility facility clearance requirements. Available online at:

	Matanuska Electric Association, Inc. (MEA) Electrical Facility Clearance Requirements

https://www.mea.coop/power-safety/electrical-safety

	ENSTAR Natural Gas Company (ENSTAR)

www.enstarnaturalgas.com/safety-education/natural-gas-safety/safety-for-excavators-contractors/

e.	Quantity Computations

f.	Cross Sections

g.	Geotechnical Report, Knik-Goose Bay Road Reconstruction, CFHWY00599, January 2021 By Alaska Department of Transportation & Public Facilities Central Region Materials

h.	Erosion, Sediment Control Plan (ESCP). Knik-Goose Bay Road Reconstruction – Phase I: Fairview Loop to Centaur Avenue, CFHWY00599, February 2022.

i.	Traffic Control Plan (TCP). Knik-Goose Bay Road Reconstruction – Phase I: Fairview Loop to Centaur Avenue, CFHWY00599, March, 2022.

j.	XML Files. XML file type for the original ground surface is available on the Department’s advertising website. The department expressly states that these XML files are for informational purposes only. The Department makes no representation, warranty, or guarantee, expressed, implied, or statutory, as to the accuracy, reliability, suitability, functionality, or results derived from the use of the information contained therein. The Department shall not accept, review, hear or consider any bid protest or construction claims arising from use of the information.

2.	Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix C.

3.	Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

4.	Section 120, Disadvantaged Business Enterprise (DBE) Program.  The Department, in coordination with US DOT, has adopted a Race-Neutral DBE Program effective for Federal-aid projects advertised in Central Region after June 30, 2015.  In particular, all bidders shall be aware that Good Faith Effort Documentation is required from the successful bidder for all contracts, regardless of DBE goal or DBE utilization, in accordance with Section 120 Disadvantaged Business Enterprise (DBE) Program.

The overall DBE Utilization Goal is revised to 8.83 percent.

Direct questions about this notice to the Manager of the Civil Rights Office, (907) 269-0848, http://www.dot.state.ak.us/cvlrts/index.shtml.

5.	Cargo Preference Act Requirements. The provisions of the Cargo Preference Act (CPA) must be physically incorporated into all Federal-aid Projects awarded after February 15, 2016, and must be physically incorporated in all agreements with subcontractors and lower tier subcontractors.

Form 25D-55 (2/16) is revised to include the CPA provisions to the Required Contract Provisions for Federal-Aid Construction Contracts.  See the last page of Form 25D-55 for the CPA requirements.

For additional details, please visit: https://www.fhwa.dot.gov/construction/cqit/cargo.cfm

6.	Buy America Act. On December 22, 2015, U.S. District Court for the District of Columbia issued a decision vacating the Federal Highway Administration (FHWA) 90 percent threshold exemption for manufactured steel and iron products and the miscellaneous steel or iron components, subcomponents and hardware waiver.  As a result of the federal court decision, FHWA withdrew their December 21, 2012 policy memorandum clarifying provisions of the Buy America Act requirements.

7.	Prohibition on Certain Telecommunications and Video Surveillance Services or Equipment. 2 CFR 200.216, as amended effective August 13, 2020, Federal Register, Vol. 85, No. 157, 49506 – 49582, Prohibition on certain telecommunication and video surveillance services or equipment.  Refer to Subsection 106-1.01.

8.	Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0644.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

9.	COVID-19 Management Plan. The Governor's emergency declaration and mandates relating to COVID-19 expired on February 14, 2021. However, contractors are encouraged to review COVID-19 Response and Recovery Health Advisories that can be accessed at:

https://covid19.alaska.gov/health-advisories/

Contractors will still be required to meet any applicable local ordinances or requirements currently in effect, and comply with any future federal, state or local declarations or mandates that might be adopted while work on the project is ongoing.

Consistent with Section 107-1.01 of the Standard Specifications for Highway Construction, the Contractor will be responsible for paying all costs and expenses incurred to comply with any COVID-19 Health Mandates or Health Advisories in effect during times when the Contractor is performing project-related work activities. The Contractor will additionally be responsible for preparing any general or site-specific mitigation and response plans required for its forces, along with any attendant schedule delays or impacts.

10.	Certified Payroll. Certified payroll must be submitted electronically through AASHTOWare for contracts awarded after January 1, 2021.

In order to submit certified payroll, Contractors, Subcontractors, and lower tier Subcontractors must be active in AASHTOWare, which requires they have a valid Vendor ID with a 913 commodity code.

To obtain a Vendor ID, register with the State of Alaska via the Vendor Self-Serve (VSS). Instructions for creating a new account in the VSS system can be found under the Job Aids at the following link:

https://iris-vss.alaska.gov/webapp/PRDVSS1X1/AltSelfService

For information on certified payroll, contact the Department of Labor and Workforce Development, Wage and Hour Administration:	Juneau	(907) 465-4842

Anchorage	(907) 269-4900

Fairbanks	(907) 451-2886

DOT&PF AASHTOWare Project guidance, including schedule, FAQs, training options:

http://dot.alaska.gov/aashtoware/

11. Section 408 and 703 Hard Aggregate.  Hot Mix Asphalt, Type VH requires hard aggregate.  Refer to the table in 703-2.04 Coarse Aggregate for the specified Nordic Abrasion value.  Material suppliers are also included in 703-2.04.

12.	Asphalt Material Price Adjustment.  The unit price adjustment for asphalt material will be combined and paid under one Pay Item. Refer to Sections in Division 300 and 400 that include an "Asphalt Material Price Adjustment" Pay Item.

13.	Escrow of Bid Documentation Affidavit.  Refer to Subsection 103-1.11 Escrow of Bid Documentation. The form "Escrow of Bid Documentation Affidavit" is included at the end of Subsection 103-1.11 and is required as part of this Contract.

14.	Limitation of Operation. Limit disturbed unstabilized ground. Refer to Subsection 652-1.04 Limitation of Operation for further information.

15. Contract Price Adjustment(s). The Department will not provide cost escalation or de-escalation price adjustments for this contract, except for specific items described in the bid package at the time of bid opening.

FED_SOA-CRSNtB-081320R_SSHC2020

PART 4

STANDARD MODIFICATIONS
AND
SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2020

EDITION

Blank Page

TABLE OF CONTENTS

Section	Page

DIVISION 100 — GENERAL PROVISIONS

103	Award and Execution of Contract	3

104	Scope of Work	7

105	Control of Work	8

106	Control of Material	9

107	Legal Relations and Responsibility to Public	10

108	Prosecution and Progress	12

109	Measurement and Payment	13

120	Disadvantaged Business Enterprise (DBE) Program	14

DIVISION 200 — earthwork

201	Clearing and Grubbing	17

202	Removal of Structures and Obstructions	18

203	Excavation and Embankment	23

205	Excavation and Fill for Major Structures	28

DIVISION 300 — BASES

301	Aggregate Base and Surface Course	31

304	Subbase	33

306	Asphalt Treated Base Course	34

DIVISION 400 — ASPHALT PAVEMENTS AND SURFACE TREATMENTS

401	Hot Mix Asphalt Pavement	49

402	Tack Coat	69

406	Rumble Strips	70

408	Hot Mix Asphalt Pavement – Type V	74

DIVISION 500 — STRUCTURES

501	Concrete for Structures	95

503	Reinforcing Steel	96

504	Steel Structures	100

505	Piling	101

DIVISION 600 — MISCELLANEOUS CONSTRUCTION

603	Culverts and Storm Drains	109

605	Underdrains	116

606	Guardrail	118

607	Fences	126

611	Riprap	136

615	Standard Signs	137

618	Seeding	142

619	Soil Stabilization	146

626	Sanitary Sewer System	151

627	Water System	163

633	Silt Fence	181

639	Driveways	182

642	Construction Surveying and Monuments	205

643	Traffic Maintenance	221

644	Services to be Furnished by the Contractor	244

645	Training Program	249

646	CPM Scheduling	252

647	Equipment Rental	253

651	Control of Work – Supplemental Requirements	255

652	Prosecution and Progress – Supplemental Requirements	280

654	Monitor	281

660	Signals and lighting	283

661	Electrical Load Centers	309

670	Traffic Markings	344

682	Utility Potholing	349

688	Utility Support	351

DIVISION 700 — MATERIALS

702	Asphalt Materials	357

703	Aggregates	358

706	Concrete and Plastic Pipe	361

708	Paints	362

710	Fence and Guardrail	363

712	Miscellaneous	365

722	Bridge Railing	366

724	Seed	367

725	Fertilizer	369

726	Topsoil	370

727	Soil Stabilization Material	371

730	Sign Materials	376

740	Signals and Lighting Materials	379

Appendix A	Construction Survey Requirements

Appendix B	Environmental Permits

Appendix C	Material Certification List

Appendix D	Sign Shop Drawings

Appendix E	Temporary Construction Easements

DIVISION 100 — GENERAL PROVISIONS

Blank Page

SECTION 103
AWARD AND EXECUTION OF CONTRACT

Special Provisions

Add the following Subsection 103-1.11 Escrow of Bid Documentation:

103-1.11 ESCROW OF BID DOCUMENTATION.  Furnish a legible copy of your Bid documentation and an affidavit, as instructed in writing by the Contracting Officer.  Bid documentation consists of written documentation of quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and other information used to prepare your Bid for this project.

Obtain and furnish the same level of bid documentation, for each subcontractor, supplier or fabricator with a subcontract or agreement exceeding $200,000, regardless of tier.  Seal each entity’s documentation in separate envelopes, labeled with the entity’s name and address, submission date, and project name and number.  Include a cover letter or quote signed by a responsible party.

Meet the following requirements:

1.	Submitting Bid Documentation.  Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number.  Deliver the sealed container to the Department-designated document Depository for safekeeping.

2.	Affidavit.  Submit directly to the Contracting Officer a signed and certified affidavit attesting that:

a.	The affiant has examined the bid documentation and that it includes all documents used to prepare the bid;

b.	The sealed container contains all bid documentation submitted;

c.	The escrow materials were relied on to prepare the bid; and

d.	Should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

3.	Access and Use of Escrow Documents. The bid documentation will remain in escrow, without access by either party, except as otherwise provided herein.  In the event the Contractor (1) provides notice of intent to claim, (2) a claim, (3) a contract change order, or (4) initiates contract related litigation, the Department may obtain copies of the bid documentation as provided herein.

Both parties will submit to the Depository and copy to each other a list of personnel that are authorized to access the escrow documents.  Use forms provided by the Depository.

Upon request, the Depository will set the time and place for access to escrow documents, will monitor the escrow documents review, and will arrange for a method of copying escrow documents.  Access to escrow documents shall require at least five days advance written notice so that the other party has the opportunity to witness the escrow review, examination and use.  There is no requirement that both parties witness the escrow document review, but if one party is absent then the review must occur in the presence of a neutral third party observer to be designated by the Depository.

Notwithstanding paragraph five below, the Department will be allowed: to make copies of any and all escrow documentation (whether hard copy, electronic, or otherwise); to use and review any copies made whether in the presence of the Contractor, or not; and to share copies with staff and consultants directly involved in the subject dispute.

Distribution is not authorized except as related to resolution of a dispute.  The Department will be allowed to incorporate pertinent copies as supporting documentation in all significant contract change orders, contractual disputes, and the settlement of disputed claims.

The Department is not liable for any Contractor costs associated with escrow review and use.

4.	Failure to Provide Bid Documentation.  Refusal or failure to provide bid documentation or affidavit renders your bid non-responsive.  Failure or refusal to provide Subcontractor bid documentation, will result in subcontract disapproval.

5.	Confidentiality of Bid Documentation.  Materials held in escrow are your property.  Except as otherwise provided herein, the escrow materials cannot be released without your approval.

6.	Cost and Escrow Instruction.  The Department pays to store escrowed materials and instructs the Depository regarding escrow.

7.	Payment.  Include within the overall Contract bid price costs to comply with this subsection.

8.	Return of Escrow Documentation.  The original escrow documents will be returned to you once litigation is concluded, outstanding claims are resolved, you have completed the Contract, and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed.

ES11-010106

ESCROW OF BID DOCUMENTATION AFFIDAVIT

THE UNDERSIGNED HEREBY CERTIFIES THAT THE ESCROW OF BID DOCUMENTATION CONTAINS ALL OF THE INFORMATION THAT WAS USED TO DEVELOP THE BID AND THAT I HAVE PERSONALLY EXAMINED THESE CONTENTS AND THAT THE DOCUMENTATION IS CORRECT AND COMPLETE IN ACCORDANCE WITH SUBSECTION 103-1.11. SUBMITTAL BY THE CONTRACTOR OF A CLAIM, WHICH IS NOT CONSISTENT WITH THE CONTENTS OF THESE BID PREPARATION DOCUMENTS, SHALL RESULT IN DENIAL OF THE CLAIM.

By:

Title:

Firm:

Date of Submission:

Project Number:

CREscrowBidAffidavit-050509

Blank Page

SECTION 104
SCOPE OF WORK

Special Provisions

104-1.06 VALUE ENGINEERING CHANGE PROPOSALS BY CONTRACTOR.

Replace 104-1.06.3.e with the following:

e.	The Contractor may submit VECPs for an approved subcontractor. If the Contractor elects to submit a VECP for an approved subcontractor and it is subsequently accepted by the Department, the Department will reimburse the Contractor per 104-1.06.5.

CR104.HSM20.2-113020

SECTION 105
CONTROL OF WORK

Special Provisions

Add the following Subsection 105-1.011 Related Sections:

105-1.011 RELATED SECTIONS.

Section 651, Control of Work – Supplemental Requirements

CR105.5-012816R

SECTION 106
CONTROL OF MATERIAL

Standard Modification

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.

Add the following:

PROHIBITION ON CERTAIN TELECOMMUNICATION AND VIDEO SURVEILLANCE SERVICES OR EQUIPMENT. On projects using federal funds, the Contractor shall comply with the requirements of 2 CFR 200.216, Prohibition on certain telecommunication and video surveillance services or equipment, including any future amends thereto that are applicable to the project.

By submitting a bid or by execution of the contract, the Contractor certifies that it has not entered into a contract nor extended or renewed a contract to procure or obtain equipment, services, or systems that uses covered telecommunications equipment or services as a substantial or essential component of any system, or as critical technology as part of any system produced by:

- Huawei Technologies Company or ZTE Corporation (or any subsidiary or affiliate of such entities).

- Hytera Communications Corporation, Hangzhou Hikvision Digital Technology Company, or Dahua Technology Company (or any subsidiary or affiliate of such entities).

- Any entity that the Secretary of Defense, in consultation with the Director of the National Intelligence or the Director of the Federal Bureau of Investigation, reasonably believes to be an entity owned or controlled by, or otherwise connected to, the government of a covered foreign country.

The Contractor further certifies that it has complied with the requirements of 2 CFR 200.216 and that it will continue to do so throughout the term of the Contract.

HSM20-20-123121

SECTION 107
LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.

The Department will: Add No. 3:

3.	The Department has received the following permits on the Contractor's behalf:

a.	Alaska Department of Fish & Game, Fish Habitat Permit FH22-IV-0073, dated April 4, 2022

b. 	U.S. Army Corps. of Engineers, Nationwide Permit POA-2022-00051, dated April 7, 2022

c.	Matanuska-Susitna Borough, Flood Hazard Development Permit F10229, dated March 21, 2022.

CR107.4-120117R1

The Contractor shall:

Add No. 10:

10.	Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual, and the Regional Supplement to the Corps of Engineers Wetland Delineations Manual (Alaska Region, Version 2.0, September 2007).  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

CR107.5-120117R

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.

Replace the 1st sentence including numbers 1, 2, and 3, with:

When operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following:

Non-municipal Water Source. If water is required for a construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

CR107.3-051517

Add the following:

Eagles.  Eagles are protected under 16 U.S.C. 668-668c Protection of Bald and Golden Eagles, that prohibits “takes” of eagles, their eggs, nests, or any part of the bird.  The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of minimum 330-feet as an undisturbed habitat buffer around nesting eagles.  If topography or vegetation does not provide an adequate screen or separation, extend the buffer to 1320-feet, or a sufficient distance to screen the nest from human activities.  The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity.  Within the Secondary Zone, between 330-feet and 660-feet from a nest tree, no obtrusive facilities, or major habitat modifications shall occur.  If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, extend the buffer up to 2640-feet.  No blasting, logging and other noisy, disturbing activities should occur during the nesting period (February 1 – August 31) within the primary or secondary zones.

Do not disturb a nesting eagle.  Notify the Engineer when an active eagle nest is within the primary or secondary zones.

CR107.1-100118

Replace Subsection 107-1.17 with the following:

107-1.11 FURNISHING RIGHT-OF-WAY. The Department will secure all necessary right-of-way (ROW) or property. The ROW shown in the plans depicts the ROW area that is or will be available for the project. Acquisition of the following properties has not been completed, and no work (including utility relocations) shall commence on these properties until a separate Notice to Proceed is given by the Engineer.

- Parcel 69, Ward, as shown on sheets R07 and F01;

- Parcel 72 and E-72, McNally, as shown on sheets R07 and F01;

- Parcel 74, McNally, as shown on sheets R07 and F02;

- Parcel 78, Lowe, as shown on sheets R08 and F22;

- Parcel 93, Little Ruda Enterprises, as shown on sheets R10, F04, and F28;

- Parcel 94, Ungaro, as shown on sheets R10, F04, F27, and F28;

- Parcel 96, Wendland, as shown on sheets R11, F05, F27, and F28;

- Parcel 102, Thompson, as shown on sheets R12 and F30;

- TCP-128, Kretschek, as shown on R17, F12, and F40;

- Parcel E-131A, Wasilla Christian Church, as shown on sheets R18, F42, and F43;

- Parcel 158, E-158, and E158A, Wasilla Area Seniors Inc., as shown on sheets R24, F18, and F55;

- Parcel 160 and E-160, Wasilla Area Seniors Inc., TCE-160 and TCE-160A, as shown on sheets R25, F18, F19, and F55;

- Parcel 161 and E-161, Wasilla Area Seniors Inc., TCE-161, as shown on sheets R25, F19, and F56;

- Parcel 163, E-163, and E-163A, Wasilla Area Seniors Inc., TCE-163, as shown on sheets R25, F19, and F56.

The Contract Time will commence to run on the day indicated on the Notice to Proceed for the overall project. The Notices to Proceed for the above properties will be delayed until such time as the Department obtains full rights to enter upon the property. The Contractor shall bid this Project to include all costs associated with the delayed Notices to Proceed based on the assumption that all Notices to Proceed will be given before May 1, 2023. If the Notices to Proceed are given on or before May 1, 2023, the Contractor will have no claim for damages or delay arising out of or connected to the delayed Notice to Proceed for these properties.

CFHWY00599

SECTION 108
 PROSECUTION AND PROGRESS

Standard Modification

108-1.01 SUBCONTRACTING OF CONTRACT.

In item 1g. replace AS 45.45.101(a) with AS 45.45.010(a).

In item 2f. replace AS 45.45.101(a) with AS 45.45.010(a).

HSM20.41-010122

Special Provision

Replace Subsection 108-1.01 1h. with the following:

1h.  Other required items listed in Form 25D-042 are included in the subcontracts;

Replace Subsection 108-1.01 2g. with the following:

2g.  Other required items listed in Form 25D-042, are included in the lower tier subcontracts;

CR108.4-010120

Add the following Subsection 108-1.011 Related Sections:

108-1.011 RELATED SECTIONS.

Section 652, Prosecution and Progress – Supplemental Requirements

CR108.3-012816R

108-1.07 FAILURE TO COMPLETE ON TIME.

Replace Table 108-1 with the following:

Table 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Original Contract Amount |  | Daily Charge |
| --- | --- | --- |
| From More Than | To and Including |  |
| $ 0 | 500,000 | $1,000 |
| 500,000 | 1,000,000 | 1,500 |
| 1,000,000 | 5,000,000 | 1,800 |
| 5,000,000 | 10,000,000 | 2,500 |
| 10,000,000 | 25,000,000 | 3,800 |
| 25,000,000 | --------- | 4,800 |

HSM20.1-063020

SECTION 109
MEASUREMENT AND PAYMENT

Special Provision

109-1.01 GENERAL.

Replace the 2nd paragraph with the following:

When more than one type of material or work is specified for a pay item, the proposal line number, and the description are used to differentiate the material or work.

CR109.4-010120

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.

Under Item 3. Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

Provide a printed copy of the current EquipmentWatch rate sheet for each piece of equipment utilized on time and materials work.

CR109.2-110118

Standard Modification

109-1.08 final payment. Add the following after the fifth paragraph:

On federally funded projects, if DOLWD Wage and Hour Administration notifies the Department of a pending prevailing wage investigation, and that the investigation is preventing the closing out of the project, the Contractor may place the notified amount in escrow under Wage and Hour for the exclusive purpose of satisfying unpaid prevailing wages. Upon receipt of notice from Wage and Hour that the Contractor has satisfactorily transferred the necessary funds into escrow, the Department will proceed to issue final payment.

CR109.HSM20.3-113020

SECTION 120
DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Standard Modification

120-1.01 DESCRIPTION.

In the first sentence of the second paragraph, replace “8.83 percent" with “8.28 percent”.

120-3.01 DETERMINATION OF COMPLIANCE.  Replace 2a. with the following:

2a.	Written DBE Commitment. Complete Form 25A-326 for each DBE to be used on the project.

HSM20.21-123121

DIVISION 200 — EARTHWORK

Blank Page

SECTION 201
CLEARING AND GRUBBING

Special Provisions

201-3.01 GENERAL.

Add the following:

Perform the work necessary to preserve and/or restore land monuments and property corners from damage.  Restore land monuments and/or property corners that are disturbed according to Section 642.  An undisturbed area five feet in diameter may be left around existing monuments and property corners.  A list of land monuments and property corners is shown on the Right of Way maps.

CR201.3-042313

Add the following:

Clearing and grubbing is not permitted within the migratory bird window of May 1 to July 15; except as permitted by Federal, State and local laws when approved by the Engineer.

CR201.1-010114

201-4.01 METHOD OF MEASUREMENT.  Replace No. 1 with the following:

1. Acre. The area acceptably cleared and/or grubbed, measured horizontally. Only areas shown on the Plans or staked for clearing and/or grubbing will be measured.

Existing roadways, pathways, shoulders, lakes, ponds, stream beds, and other areas not covered by trees or brush will not be included for measurement.

CFHWY00599

Add the following:

The work required to preserve and restore land monuments and property corners is subsidiary to 201 Pay Items.

CR201.3-042313

SECTION 202
REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION.

Add the following:

This work shall also include all work and materials necessary to install and/or relocate cluster mail boxes and mail box foundations at all locations shown on the Plans.

This work shall also include all work and materials necessary to abandon water and sanitary sewer pipelines at all locations shown on the Plans.

This work shall also include all work and materials necessary to remove natural gas pipelines at all locations shown on the Plans.

CFHWY00599

Add the following:

Gas Pipe: remove and dispose.

CR202.5-040120

Add the following:

Ground Water Wells: decommission.

CR202.8-040120/CFHWY00599

202-2.01 MATERIALS.

Add the following:

Use Materials that conform to the following:

Cluster Mail Box Unit	Pedestal-mounted United States Postal Service (USPS)-approved cluster mail box unit.

Class B Concrete	Section 550

202-3.01 GENERAL.

Add the following:

Provide foundation, 8 inches thick, minimum of 4’ x 4’, per plans or as recommended by the manufacturer for the Cluster Mail Box Unit.

CFHWY00599

Add the following:

Property Owner Fence: carefully remove fences, designated by the Engineer, to the right-of-way limit, or to the end of the span beyond the right-of-way limit. Fence materials belong to the property owners. Salvage and stack fence materials neatly in the property owner's yard. If a noise barrier or separation fence is constructed, with the owner's permission, use salvaged fencing to fill fencing gaps behind the property line.  Use salvaged fencing according to Section 607, for reconstructed fences.

CR202.6-040120

202-3.02 MAIL BOXES.

Add the following:

Contractor shall contact the USPS Growth Coordinator, Jordan Matthews, at 907-273-5859 at least 72 hours before relocating the existing cluster mail boxes. After new cluster mail box units have been installed, Contractor shall contact the USPS Growth Coordinator, Jordan Matthews, at 907-273-5859 at least 72 hours before removing the existing mail boxes.

Provide keys to the USPS Station once installation of the cluster mail boxes has been completed. Do not remove the existing mail boxes until the USPS office has approved the mail box installations.

CFHWY00599

202-3.04 REMOVAL OF PIPE.

Add the following:

ENSTAR Natural Gas Company (ENSTAR) will abandon sections of its existing pipe network as part of its proposed relocation work for the project.  These sections are comprised of both HDPE and steel pipelines.  The Contractor shall coordinate with ENSTAR to confirm the abandonment of these facilities, and then remove the portions of the abandoned natural gas pipes that intersect/conflict with the Contractor’s work.  The pipes shall be disposed of off the project limits.  Coordinate with ENSTAR in accordance with the procedures given in Subsection 105-1.06 Cooperation With Utilities, when working around gas pipelines until they have been abandoned.

CR202.5R-010610/CFHWY00599

Replace Subsection 3.05 with the following:

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS. In removing pavements, curbs, walks, driveways and similar structures, make all cuts clean, vertical, and true to designated lines where an abutting structure or a part of a structure is to be left in place.

Pavement materials, base course, sidewalks, curbs, gutters, etc., designated for removal may be placed in the embankment in accordance with 203-3.03 with written approval. Maximum allowed dimension of material is 6 inches.

Dispose of materials, not placed in the embankment, outside the right-of-way project limits according to Subsection 202-3.06.

CR202.2-040120

Add the following Subsection 202-3.06 Salvage and Disposal of Construction and Demolition Materials:

202-3.06 SALVAGE AND DISPOSAL OF CONSTRUCTION AND DEMOLITION MATERIALS. Unless otherwise noted, remove, handle, salvage, transport, store, and dispose waste materials according to the Occupational, Safety, and Health Administration (OSHA), Environmental Protection Agency (EPA), Alaska Department of Environmental Conservation (ADEC), and other Federal, State and local government agency's statutes, rules and regulations.

Use disposal sites outside the project right-of-way limits unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the private or public property owner for such disposal and a waiver of all claims against the State for any damage to such land which may result, together with all permits required by law for such disposal. Furnish a copy of such permission, waiver of claims, and permits to the Engineer before commencing work. Grade disposal areas to drain.

CR202.1-040120

Add the following Subsection 202-3.08 Ground Water Decommissioning:

202-3.08 GROUND WATER WELL DECOMMISSIONING.  Decommission the water wells according to ADEC requirements conforming to 18AAC 80.015(e) Well Protection Source Water Protection, and Well Decommissioning, or a ADEC approved alternate method.  Develop and submit a detailed Ground Water Well Decommissioning Plan to the Engineer.  Contact the Wasilla ADEC office at (907) 376-1850, for plan review requirements of alternate methods.

CR202.8-040120

Add the following Subsection 202-3.09 Abandon Pipeline in Place:

202-3.09 ABANDON PIPELINE IN PLACE.  Wherever existing pipe is to be abandoned in place, the Contractor shall empty and dispose of all contents in the pipe in accordance with DEC regulations, fill the pipe with sand slurry, and plug the ends.  Placement of the sand slurry shall be by means of another pipe being abandoned.  The Contractor shall demonstrate the entire pipe to be abandoned has been filled prior to the installation of end caps.  Validation shall include placement of a predetermined volume of sand slurry into the pipe to be abandoned.

In the event the pipeline to be abandoned is cracked of crushed, the Contractor shall excavate to the next joint of pipe and install the plug.  Crushed pipe sections or portions thereof shall be removed and disposed of by the Contractor.

The Contractor shall remove all valve boxes connected to the section of pipe to be abandoned.  This work shall be an incidental item of abandonment.  All removed materials shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.

All excavation, shoring, dewatering, disposal of unsuitable material, backfilling, and compactive effort required for completion of this Work shall conform to the requirements of Section 203 Excavation and Embankment.

During the execution of this effort, the Contractor shall maintain vehicular traffic and pedestrian access as required in Section 643 Traffic Maintenance.

The Contractor shall restore the Work area to preconstruction conditions.

The Contractor shall notify the Engineer twenty-four (24) hours in advance of abandoning each water and sewer main and shall provide safe access for the inspection of the process.

CFHWY00599

202-4.01 METHOD OF MEASUREMENT.

Delete number 3. And replace with the following:

3.	Each.  Each complete unit relocated or installed, including concrete foundation and coordination with the USPS.

Add the following:

Abandon Pipeline In Place.  Measurement of quantities of pipeline to be abandoned in place shall be per lineal foot of pipeline to be abandoned for each nominal pipeline size.  Length shall include pipeline that is removed due to damaged ends.  Removal and disposal of pipeline sections that have damaged ends and cannot be plugged in place shall be considered incidental to the Abandon Pipeline in Place scope of Work identified in this Section.

CFHWY00599

202-5.01 BASIS OF PAYMENT.

In the first paragraph, replace "and 22.0013.____." with the following: "and 202.0013.____."

In the fourth paragraph, replace "Items 020.0014.____" with the following: "Items 202.0014.____"

CR202.HSM20.4-113020

Add the following after the last sentence of the third paragraph:

Removal and temporary relocation of existing mailboxes and newspaper tubes is subsidiary.

CFHWY00599

Add the following:

Acquiring waste disposal permits is subsidiary to 202 Pay Items.

CR202.1-040120

Add the following:

Item 202.2008.____.  At the Contract Unit Price per lineal foot of pipe, regardless of material type or pipe diameter, removed and disposed.  Payment includes full compensation to remove and dispose of the pipes as shown in the Plans.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 202.2008.____ | Removal of Pipe, Gas | LF |

CFHWY00599

Add the following:

Item 202.2012.____.  At the Contract Unit price for each well decommissioned according to DEC regulations.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 202.2012.____ | Ground Water Well Decommissioning | Each |

CR202.8-040120

Add the following:

Item 202.2016.____.  At the Contract Unit Price per lineal foot of pipe, regardless of diameter, abandoned in accordance with these specifications and the Plans.  Payment includes full compensation for necessary excavation, purging, removal and processing of pipeline contents and any soils contaminated by abandonment activities, and backfilling/compacting excavations associated with the work.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 202.2016.____ | Abandon Pipe in Place, ________ | LF |

CFHWY00599

Add the following:

Item 202.2022.____.  At the Contract Unit price for the actual length of fence taken down, disposed, or delivered to the owner, regardless of the type or height.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 202.2022.____ | Removal of Fence | LF |

CR202.6-040120

Add the following:

Item 202.0027.____.  Payment is full compensation for coordination with the USPS and the installation of new cluster mail box units, relocation of existing cluster mail box units, reinforcing steel and Class B concrete foundation for mail boxes, removing and disposing of existing mail boxes and reinstallation of mail box tubes.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 202.2027.____ | Cluster Mail Box Unit | EACH |

CFHWY00599

SECTION 203
EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01 DESCRIPTION.

Add the following:

Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

CR203.2-010114R/CFHWY00599

Add the following:

This work shall also include the mixing and placing of Engineered Soil as shown in the Plans.

Construct and shape special ditches at the locations and elevations shown in the Plans.

Engineered Soil shall be a homogenous 50/50 by volume composition mix of topsoil and sand mixture.

CFHWY00599

203-2.01 MATERIALS

Add the following:

7. Topsoil: Meet 726-2.01 requirements.

8. Sand: Meet 703-2.12 requirements.

CFHWY00599

203-3.01 GENERAL.

Add the following:

Prior to ditch linear grading work, conduct utility potholing as defined in Section 682. Pothole existing utilities intersecting with the proposed ditch linear grading work area every 50 feet or as directed by the Engineer. Coordinate with the Engineer and adjust the proposed scope/extents of the ditch linear grading work to maintain the existing amount of cover or 4 feet, whichever is less.

CFHWY00599

Standard Modification

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL.

In the second paragraph delete "and ATM 214".

203.HSM20.5-113020

203-4.01 METHOD OF MEASUREMENT.

Add the following:

9.	Item 203.2038.____.  Measurement of ditch linear grading, whether flat bottom or “V” ditch, will be measured for payment by the station along the center of the ditch for each ditch so designated, constructed, and accepted by the Engineer.

CR203.2-010114R/CFHWY00599

Add the following:

10. Item 203.2056.____. Measurement of Engineered Soil will be measured for payment once the material is placed and spread evenly on the designated areas to the depth shown in the plans.

CFHWY00599

203-5.01 BASIS OF PAYMENT.

Add the following:

203.2038.____ Payment for ditch linear grading will be full compensation for furnishing equipment, labor, tools, and incidentals to provide the preparation, excavation and shaping necessary to complete the work.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 203.2038.____ | Ditch Linear Grading | Sta |

CR203.2-010114R

Add the following:

203.2056._____ Handling, labor, and mixing of Engineered Soil shall be subsidiary to the Engineered Soil Pay Item.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 203.2056.____ | Engineered Soil | SY |

CFHWY00599

Special Provision

Replace Section 204 with the following:

SECTION 204
STRUCTURE EXCAVATION FOR CONDUITS AND MINOR STRUCTURES

204-1.01 DESCRIPTIONS. Excavate and backfill for conduits (pipe culverts, structural plate pipe, pipe arches, storm drains, underdrains, and electrical conduits), headwalls, manholes, inlet boxes, and other minor structures.

Dewater ground water from work areas. Construct and maintain temporary water diversion when working in waterways, and for facilities or structures with active drainage.

Perform all pumping, bailing, draining, sheeting, bracing, and incidentals required for proper execution of the work.

204-2.01 MATERIALS. Use materials that conform to the following:

Selected Material	Subsection 703-2.07

Porous Backfill Material	Subsection 703-2.10

1. Structure Backfill and Bedding Material: Selected Material Type A.

Maximum Particle Size:

a.	Corrugated Steel and Aluminum Conduit: material passing the 3-inch sieve

b.	Precast Concrete Structures

(1)	Conduit: materials passing the 1-inch sieve, except 2-inch when bedding thickness is greater than 6 inches

(2)	Minor structures: material passing the 1-inch sieve , except 2-inch when bedding thickness is greater than 6 inches

c.	Plastic Conduit: material passing the 2-inch sieve, except 3/4-inch for conduit between 8 inches and 15 inches and for conduit less than 8 inches 10% of the conduit diameter

d.	Electrical Conduit: material passing the 1-inch sieve

e.	Underdrain Conduit: uniform porous backfill material passing the 2-inch sieve and a minimum greater than the conduit perforations

2. Backfill Material: Selected Material Type C

In the roadbed structure use backfill material meeting the requirements of the roadbed structure, except use the structure backfill material and bedding as specified herein.

Use all suitable material from the project excavation for bedding, structure backfill, and backfill material before using material from another source.

204-3.01 CONSTRUCTION REQUIREMENTS. Clear and grub prior to starting excavation according to the requirements of Section 201.

Keep the work areas dewatered and divert water when working in a waterway or active drainage, Subsection 204-3.02.

Remove and dispose, Subsection 203-3.01, of unsuitable foundation material, including rock or other unyielding material, below the designed elevation as directed, except no less than 6 inches, and replace with approved material.

Place bedding material to a minimum thickness of 4 inches, except 6-inch minimum thickness for conduit over rock or unyielding material, and below electrical conduit, unless shown otherwise in the plans.

Place the bedding material to provide uniform support for conduit with the material in the middle one-third loosely placed and not compacted. Do not shape the bedding to the curvature of the round conduits. Shape the bedding for pipe arches, horizontal ellipse, and underpass shapes with spans exceeding 12 feet. Provide a minimum shaped width one-half the span of the pipe arch and underpass shapes and one-third the span of horizontal ellipse shape. Shape the bedding to the relatively flat bottom arc or fine-grade the foundation to a slight "V" shape.

Place minor precast concrete structures, other than conduits, on the 4-inch bedding/leveling course, of uniform stiffness and thickness with even compaction throughout.

Place the structure backfill over the bedding each side of the structure to 12 inches above the structure or the ground surface if less than 12 inches, except 6 inches above electrical conduit.

Place the structure backfill and backfill material in uniform layers not more than 6 inches deep. Do not create unbalanced loading with the placement of the structure backfill materials. When placing material against concrete, place the material according to the requirements of Section 550.

Compact the materials, each layer, without ponding or jetting to meet Subsection 203-3.04. In the haunch area, each side of the conduit, compact the material by firmly tamping into place.

Outside the roadbed structure, the Engineer may visually inspect and approve the excavation, bedding, structure backfill, backfill material, and compaction.

Support and protect existing conduits or utilities, not scheduled for removal or abandonment, when encountered in the excavation.

Remove all sheeting and bracing used in structure excavation upon completion of the work.

204-3.02 DEWATERING AND WATER DIVERSION. Submit a plan for work area dewatering and each waterway diversion, 14 days before related construction activities. Do not implement the plan without written approval. Include the permit requirements in the plan.

1. 	Do not exceed State of Alaska water quality standards.

2.	Do not divert water from dewatering into a waterway.

3.	Provide an approved disposal site for work area excess water. Maintain disposal site a minimum of 100 ft from waterway.

4.	Prevent turbid water from directly entering waterways.

5.	Do not divert water onto the roadway.

6.	In addition to other equipment required to complete the temporary water diversion and dewatering work, maintain a minimum of two trash pumps with hoses at the site during diversion construction activities. Maintain the intake to prevent fish entrapment, entrainment, or injury with the use of perforated or slotted plate and woven wire with a mesh size not greater than 3/32 inch or a profile bar and wedgewire with openings not greater than 1/16 inch.  Do not exceed passive approach velocity of 0.2 fps and active approach velocity of 0.4 fps.

Rewater to minimize sediment movement downstream of the site. Prior to rewatering, slowly wet the reconstructed waterway channel; wash the fines into the bed by using pumps, or by diverting a small portion of the waterway channel flow. Capture and pump the sediment and turbid water, from the downstream end of the channel to the upstream end of the channel, until fines are washed into the streambed and water runs clear. Attain the Engineers written approval before breaching the coffer/diversion dams. Slowly breach the coffer/diversion dams and rewater the waterway channel.

204-4.01 METHOD OF MEASUREMENT. Section 109. Use neat line method as follows:

Structure Excavation:

1.	Masonry Structures (except conduit). Between vertical planes, 18 inches outside the base of the masonry sections for the depth required.

2.	Conduit. Between parallel vertical planes located 18 inches outside the horizontal projection of the outside diameter of the conduit and to the depth shown on the Plans.

Structure excavation only measured below the limits of other classes of excavation. Structure's in embankment section, the natural ground line as cross-sectioned is the uppermost level of computation.

204-5.01 BASIS OF PAYMENT. The Contract price includes the placing and compacting of all backfill and bedding when the materials used are obtained from excavation, any clearing and grubbing required and not paid for under some other item, formation of any embankments made with surplus material from structure excavation, and disposal of all surplus or unsuitable excavation.

Culvert baffles, headwalls, temporary water diversion, dewatering and rewatering, and the removal of pavement are subsidiary to the conduit and minor structure Pay Items.

Additional excavation to provide for shoring, sheet piles, excavation shields or flattening the excavation slopes, is subsidiary.

When item 204.0001.____, 0002.____, or 0003.____ Structure Excavation, does not appear in the bid schedule, structure excavation required to complete other items of work is subsidiary, except that excavation and disposal of unsuitable material required from below a plane 12 inches below the invert elevation of conduits and 12 inches below the bottom of structures is paid as extra work.

Any backfill or bedding material required whose source is other than project excavation is paid at the contract unit price for the materials being used, or as extra work if no unit price has been established.

Traffic control paid under Section 643 and Erosion, Sediment, and Pollution Control paid under Section 641.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 204.0001.____ | Structure Excavation | CY |
| 204.0002.____ | Structure Excavation | Ton |
| 204.0003.____ | Structure Excavation | LS |

CR204-070121

SECTION 205
EXCAVATION AND FILL FOR MAJOR STRUCTURES

Standard Modification

205-3.05 COMPACTION.

1.	Compaction with Moisture and Density Control. 2nd paragraph delete: "and ATM 214".

CR205.HSM20.5-113020

DIVISION 300 — BASES

Blank Page

SECTION 301
AGGREGATE BASE AND SURFACE COURSE

Special Provision

301-2.01 MATERIALS.

Add the following after the first sentence:

Recycled Asphalt Material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70 – 100 |
| 3/8 inch | 42 – 90 |
| No. 4 | 28 – 78 |
| No. 16 | 11 – 54 |
| No. 50 | 5 – 34 |
| No. 100 | 3 - 22 |
| No. 200 | 2 – 12 |

3.	The asphalt content shall be 2.5 – 5.0 percent by weight of the RAM.

CR301.1-012407R

301-3.01 PLACING.

Add the following:

Place base course material, used for the sidewalk and pathway foundations, with equipment capable of providing a specified depth and uniform surface.

CR301.2-062116

Add No. 5 after the 5th paragraph:

5.	within 50 feet of detector loops.

CR301.3-022015

Standard Modification

301-3.03 SHAPING AND COMPACTION.

In the second paragraph delete "and ATM 214".

CR301.HSM20.5-113020

Add the following:

If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be determined by control strip method ATM 412.  Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi ( 5 psi) and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.

Add the following:

Recycled asphalt material substituted for aggregate base course will be paid for as Item 301.0001.____ Aggregate Base Course, at the unit price shown in the bid schedule for that Item.

CR301.1-012407R

SECTION 304
SUBBASE

Special Provision

304-3.01 CONSTRUCTION REQUIREMENTS.

Add No. 5 after the 4th paragraph:

5.	within 50 feet of detector loops.

CR304.1-022015

Special Provisions

Replace Section 306 with the following:

SECTION 306
ASPHALT TREATED BASE COURSE

306-1.01 DESCRIPTION.  Construct a plant-mixed asphalt treated base (ATB) course on an approved foundation to the lines, grades, and depths shown in the Plans.  Recycled asphalt pavement (RAP) may be used in the mix as specified herein.

306-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.

MATERIALS

306-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD).  Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 306-1 and as specified herein.  Recycled Asphalt Pavement may be used to supplement the aggregate and asphalt binder in the ATB.

TABLE 306-1

ATB Design Requirements

| DESIGN PARAMETERS | CLASS “B” |
| --- | --- |
| ATB (Including Asphalt Binder) |  |
| Stability, Pounds | 1200 min. |
| Flow, 0.01 Inch | 8 - 16 |
| Voids in Total Mix, % | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 50 |
| Asphalt Binder |  |
| Percent Voids Filled with Asphalt Binder (VFA) | 65 - 78 |
| Asphalt Binder Content, Min. % | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |
| Type II | 12.0 |
| Recycled Asphalt Pavement (RAP) |  |
| RAP, Max. %. | 25 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt binder.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the ATB, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-4.  For acceptance testing, ATB mixture will have the full tolerances in Table 306-2 applied.

Do not mix ATB produced from different plants for testing or production paving.  ATB from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of ATB:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD including gradations for individual virgin aggregate (aggregate) stockpiles and the RAP stockpile.  Provide supporting process quality control information; including the blend ratio of each aggregate stockpile, the RAP stockpile and the RAP asphalt binder content.  For mixes with RAP, provide JMD gradation with and without RAP.  Provide calibration data if ATM 406 is used for RAP process control.

2 	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) and RAP required for the proposed JMD.  Furnish 100 lbs of each intermediate and/or coarse aggregate, 200 lbs of fine aggregate, 25 lbs of blend sand, and 200 lbs of RAP.

3.	Three separate 1-gallon samples, minimum, of the asphalt binder proposed for use in the ATB.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet (MSDS).

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current MSDS.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and Table 306-1 ATB Design Requirements.

The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 306-1

	The asphalt binder source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The source of RAP is changed

Do not produce ATB for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.

Payment for ATB will not be made until the new JMD is approved.  Approved changes apply only to ATB produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix.  The fee will be included under Pay Item 306.2001.____ ATB, Price Adjustment, Type ___; Class__.

306-2.02 AGGREGATES.  Conform to Subsection 703-2.04. Type II, Class B (IIB) total combined aggregates.

Use a minimum of three stockpiles for crushed ATB aggregate (coarse, intermediate, and fine).  Place RAP, blend material and mineral filler in separate piles.

306-2.03 ASPHALT BINDER.  Conform to 702-2.01.  If asphalt binder is not specified use PG 52-28.

The total asphalt binder content may be a combination of the asphalt binder specified and the residual asphalt binder in the RAP.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702, before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of anti-strip added.

306-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt binder is required.

306-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the ATB according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, adjust the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 7 days before initiating pre-paving operations.  Address the sequence of operations.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the ATB, and to provide the mat density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt binder content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 306-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

306-2.06 RECYCLED ASPHALT PAVEMENT (RAP).  Process existing pavement removed under Subsection 202-3.07 so material passes the 1 1/2" sieve.  Stockpile the material separately from the crushed aggregates.  Perform one gradation and one asphalt binder content test for every 1000 tons of RAP or a minimum of 10 sets of tests whichever is greater.

CONSTRUCTION REQUIREMENTS

306-3.01 WEATHER LIMITATIONS.  Do not place ATB on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place ATB unless the roadway surface temperature is 40F or warmer.

306-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of ATB buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production ATB.

306-3.03 ASPHALT MIXING PLANTS.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before ATB production.

When using recycled asphalt pavement material, mix the RAP with the aggregate before the aggregate enters the plant thereby adding the RAP combined with the aggregate to the asphalt treated base mixture at one time.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the ATB.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.

Provide aggregate and asphalt binder sampling equipment meeting OSHA safety requirements.

306-3.04 HAULING EQUIPMENT.  Costs associated with meeting the requirements of Subsection 306-3.04 are subsidiary to Section 306 Pay Items.

Vehicles/Equipment.  Haul ATB in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During ATB hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer, cover the ATB in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surface(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 7 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paving equipment.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material, the users, and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage, as specified in Subsection 306-3.16 Patching Defective Areas, to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal.  Use repair materials of similar type to the damaged material.  Attain written approval from the Engineer for the proposed material.

306-3.05 PAVING EQUIPMENT.  Use self-propelled asphalt pavers with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the screed or blade control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Use a paver screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the ATB.

Equip pavers with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the ATB uniformly in front of screed.

Prevent segregation of the coarse aggregate particles from the remainder of the ATB during paving operations.  Specifically equip pavers to prevent segregation between the hopper and augers.  Use means and methods approved by the paver manufacturer.  Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance verifying use of the means and methods required to prevent segregation.

306-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact ATB asphalt mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

306-3.07 PREPARATION OF EXISTING SURFACE.  Prepare base surface conforming to the Plans and Specifications.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of ATB on these surfaces.

306-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

306-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the ATB, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by ATM 407.

Heat the aggregate for the ATB, and the RAP when being used in the mix, to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  ATB containing soot or fuel is unacceptable (Subsection 105-1.11).

306-3.10 MIXING.  Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

306-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the ATB remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss; and the physical characteristics of the asphalt binder, lumpiness, or stiffness of the ATB or similar.

306-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute ATB.  Place the ATB upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the ATB surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding ATB may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the ATB in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

Do not cover/place over the asphalt treated base material until the ATB material throughout that section, as defined by the Paving Plan, is placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place ATB over bridge deck membranes, except as directed by the Engineer.

306-3.13 COMPACTION.  Compact the ATB by rolling thoroughly and uniformly.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Prevent indentation of ATB.  Do not leave rollers or other equipment standing on ATB that is not sufficiently cooled to prevent indentation.

A mat area with density lower than 92.0 % MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The MSG of the JMD will be used for the first lot of ATB.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to ATM 410 using a 6 inch diameter core.

306-3.14 JOINTS.  Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the ATB to provide a continuous bond, texture, and smoothness between adjacent sections of the ATB.

Coordinate the joints in the ATB pavement layer with the layer of HMA pavement above.  Offset the longitudinal joints in the HMA pavement layer above from the joint in the ATB asphalt pavement layer immediately below by at least 6 inches.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new ATB and thoroughly compact.

306-3.15 SURFACE TOLERANCE.  Costs associated with meeting surface tolerances are subsidiary to the ATB Pay Items.

The Engineer will test the finished surface after final rolling at selected locations using a 10 ft straightedge.  Correct variations from the testing edge, between any two contacts, of more than 1/4 inch.

306-3.16 PATCHING DEFECTIVE AREAS.  Costs associated with patching defective areas are subsidiary to the ATB Pay Items.

Remove defective ATB for the full thickness of the course, do not skin patch.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh ATB to grade (Subsection 306-3.13) and surface tolerance requirements (Subsection 306-3.15).

306-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Asphalt Treated Base.

a) By weighing.  No deduction will be made for the weight of asphalt binder or anti stripping additive or cutting back joints.

2.	Asphalt Binder.  By the ton, as follows.

Method 1:

Percent of asphalt binder for each sublot multiplied by the total weight represented by that sublot.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  If no acceptance testing is required, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2:

Supplier's invoices minus waste, diversion, and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing ATB for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste ATB will be calculated using the target value for asphalt binder as specified in the JMD.

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt binder more than 0.4% above the optimal asphalt binder content specified in the JMD.

3.	ATB, Price Adjustment, Type   ; Class  .  By the fees specified in Subsections 306-2.01, 4.02, and 5.01.

306-4.02 ACCEPTANCE SAMPLING AND TESTING.

1.	Asphalt Treated Base

The bid quantity of ATB produced and placed is divided into lots and the lots evaluated individually for acceptance.

A lot is normally 10,000 tons.  The lot is divided into sublots of 1000 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this subsection.  The lot is evaluated for acceptance according to Subsection 306-4.03. Seasonal startup or a new JMD requires starting a new lot.

If less than 8 sublots have been placed at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot. The acceptance computed for the prior lot will include the samples from the shortened lot. Density test results from material in the shortened lot will be based on the MSG of the first sublot of the shortened lot. If there is no prior lot, and there are at least 3 sublots, the material in the shortened lot will be considered as a lot and acceptance will be based on the actual number of test results in the shortened lot. If there are less than 3 sublots, the ATB will be accepted for payment based on the Engineer's approval of the JMD, and placement and compaction of the ATB to the specified depth, finished surface requirements, and tolerances.

If 8 or 9 sublots have been placed at the time a lot is terminated, they will be considered as a lot and the acceptance will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the bid quantity is between 3,000 to 10,000 tons, the quantity is considered one lot.  The lot is divided into sublots of 1000 tons, and each randomly sampled and tested for asphalt binder content, density, and gradation according to this subsection.

ATB quantities of less than 600 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  ATB quantities of 600 tons or greater will be treated as an individual sublot.

For bid quantity less than 3,000 tons, ATB will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the ATB to the specified depth and finished surface requirements and tolerances.

The Engineer reserves the right to perform any testing required in order to determine acceptance.

a.	Asphalt Binder Content.  ATB samples shall be taken randomly by the Contractor in the presence of the Engineer from behind the paver screed before initial compaction, or will be taken randomly by the Engineer from the windrow according to ATM 402 or ATM 403 at the discretion of the Engineer. The location (behind the paver screed or windrow) will be determined at the pre-paving meeting. The Engineer will determine random sampling locations.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  At the discretion of the Engineer, asphalt binder content will be determined according to ATM 405 or ATM 406, except ATM 405 will not be used when RAP is included in the mixture.

b.	Aggregate Gradation. Aggregates tested for gradation acceptance will have the full tolerances from Table 306-2 applied. For ATB samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder.

c.	Density. The Engineer will determine and mark the location(s) where the Contractor takes each mat core sample.  The location(s) for taking core samples is determined using a set of random numbers (independent of asphalt binder and aggregate sampling set of random numbers) and the Engineer's judgment. Take no mat cores within 1-foot of a joint or edge. Core samples are not taken on bridge decks.

Take core samples according to ATM 413 in the presence of the Engineer. Cut full depth core samples centered on the marks from the finished ATB within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  The Engineer will immediately take possession of the samples. Backfill and compact voids left by coring with new ATB within 24 hours and according to ATM 413. The Engineer will determine density of samples according to ATM 410.

d.	Asphalt Binder Content, Aggregate Gradation, and Density – Retest. When test results have failed to meet specifications, retest of acceptance test results for asphalt binder content, gradation, and density may be requested provided the quality control requirements of Subsection 306-2.05 Process Quality Control are met.  Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results are discarded and the retest result is used to evaluate the material for acceptance.  Only one retest per sample is allowed.  When gradation and asphalt binder content are determined from the same sample, a request for a retest of either gradation or asphalt binder content results in a retest of both. Both gradation and asphalt binder content retest results are used in the evaluation. Except for the first lot, retesting for gradation or asphalt binder from the first sublot of a lot will include retesting for the MSG. Retesting will be performed by a Department laboratory.

2.	Asphalt Binder

The bid quantity of asphalt binder produced and placed is divided into lots and the lots evaluated individually for binder grade acceptance.

Testing will be by AASHTO accredited independent laboratories. When retesting is requested, the assigned value (ATV) will be determined using ASTM D3244. Each test will be completed by a different laboratory.

a.	Acceptance Test. The lot size for asphalt binder will normally be 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it is added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it is sampled, tested and evaluated as a separate lot.

If the bid quantity of asphalt binder is between 85 to 200 tons, the bid quantity is considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Sample asphalt binder at the plant from the supply line in the presence of the Engineer according to ATM 401.  The Engineer will take immediate possession of the samples.  Take three samples from each lot, one for acceptance testing, one for Contractor requested retesting, and one held in reserve for referee testing if requested.  Meet Subsection 702-2.01 requirements for asphalt binder quality.

b.	Retest. Submit a written request, for a retest, no more than 7 days from receiving notice of the failed acceptance test. In the request, identify the retest laboratory. The Engineer will send the second sample (retest sample) to the laboratory. Provide the retest results to the Engineer.  Contractor pays for the retest costs.

If the average of the combined test results ([acceptance + retest]/2) passes the specification requirement, the average value becomes the ATV. If this ATV fails the specification requirement, the Engineer or Contractor may request the third sample (referee sample) be tested.

c.	Referee Test. The Engineer will send the third sample (referee sample) to an agreed upon laboratory. The average of the combined test results ([acceptance + retest + referee]/3) equals the ATV. If the ATV fails to meet specifications, the Contractor pays for the referee test.

306-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  A mat area of finished surfacing that is contaminated with foreign material; is segregated (determined visually or by testing), has a lower density than specified, fails to meet surface tolerance requirements, is flushing or bleeding asphalt binder after compaction is complete, or in any other way determined to be defective is unacceptable according to Subsection 105-1.11.  ATB, not meeting the specified limits noted in Table 306-2, is considered defective.  Correct unacceptable work and materials according to Subsection 306-3.16 and as directed by the Engineer.

TABLE 306-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4-inch sieve or largest sieve size | 99 | 100 |
| 1/2-inch sieve or first sieve retaining aggregate | TV -6 | TV +6 |
| 3/8-inch sieve | TV -6 | TV +6 |
| No. 4 sieve | TV -6 | TV +6 |
| No. 8 sieve | TV -6 | TV +6 |
| No. 16 sieve | TV -5 | TV +5 |
| No. 30 sieve | TV -4 | TV +4 |
| No. 50 sieve | TV -4 | TV +4 |
| No. 100 sieve | TV -3 | TV +3 |
| No. 200 sieve* | TV -2.0 | TV +2.0 |
| Asphalt Binder Content, % | TV -0.4 | TV +0.4 |
| Mat Density % | 92.0 | 100.0 |

*LSL for the No. 200 sieve is restricted by the broadband limits in Table 703-4.

Asphalt binder will be randomly sampled and tested in accordance with Subsection 306-4.02.  Provide supplier process control test results with the delivery ticket for each load of asphalt binder to the Engineer before unloading asphalt binder at the project. No payment will be made without this documentation.

306-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Subsection 702-2.01 Asphalt Binder, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

306-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items the work and materials associated with:

Asphalt binder, anti-stripping additives, surface tolerance corrections, patching defective areas; removal and disposal of rejected ATB, and the hauling equipment are subsidiary to the Asphalt Treated Base Pay Items.

Item 306.2001.____. ATB, Price Adjustment, Type ___; Class __: is the sum of the price adjustment for the fees assessed the Contractor including:

	Each mix design subsequent to the approved Job Mix Design (Subsection 306-2.01) will result in a fee of $2500.00 each.

	Failure to cut core samples within the specified period will result in a fee of $100.00 per sample per day (Subsection 306-4.02).

	Failure to backfill voids left by sampling within the specified period will result in a fee of $100 per hole per day (Subsection 306-4.02).

	Contractor retesting, referee sample testing and Contractor requested testing for visually inspected and rejected asphalt treated base failing to meet specifications will result in a fee being assessed for all costs associated with the test (Subsection 306-4.02, 4.03).

Item 306.2002.____ . Asphalt Material Price Adjustment.

For each Section as included in Subsection 306-4.04 Asphalt Material Price Adjustment, item 1, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment", is not included, for any section, no payment will be made.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 306.0001.____ | ATB | Ton |
| 306.0002.____ | Asphalt Binder, Grade PG ## - ## X | Ton |
| 306.2001.____ | ATB, Price Adjustment, Type ___; Class __ | cs |
| 306.2002.____ | Asphalt Material Price Adjustment | CS |

CR306-010122

Blank Page

DIVISION 400 — ASPHALT PAVEMENTS
AND
SURFACE TREATMENTS

Blank Page

Special Provision

Replace Section 401 with the following:

SECTION 401
HOT MIX ASPHALT PAVEMENT

401-1.01 DESCRIPTION. Construct one or more courses of plant-produced Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

1.	In this Section, HMA refers to Type I, II, III, and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course: HMA, Type IV, Class B.

MATERIALS

401-2.01 ASPHALT BINDER.  Conform to Subsection 702-2.01. If binder performance grade is not specified, use PG 52-28.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of liquid anti-strip added.

Asphalt binder may be conditionally accepted at the source if a manufacturer's certification of compliance is provided, according to Subsection 106-1.05, and the applicable requirements of Section 702 are met.

401-2.02  LIQUID ANTI-STRIP ADDITIVE.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design (JMD). At least 90% of the aggregate must remain coated when tested according to ATM 414. The following minimum dose (percent) of liquid anti-strip by weight of asphalt binder is required:

| Liquid Anti-strip Type | Minimum Dose by Weight of Asphalt Binder, % |
| --- | --- |
| Amines based | 0.30 |
| Phosphate Ester based | 0.30 |
| Organ-Silane based | 0.05 |

401-2.03  JOINT ADHESIVE.   Conform to Subsection 702-2.05.

401-2.04  JOINT SEALANT.   Conform to Subsection 702-2.06.

401-2.05  WARM MIX ASPHALT.   Conform to Subsection 702-2.07.

401-2.06  ASPHALT RELEASE AGENT.  Conform to Subsection 702-2.08.

401-2.07 AGGREGATES.  Conform to Subsection 703-2.04.  Use a minimum of three stockpiles of crushed aggregate (coarse, intermediate, and fine).  Place blend material, if any, in a fourth pile.

401-2.08  RECYCLED ASPHALT PAVEMENT.  Recycled asphalt pavement (RAP) may be used in the production of HMA.  The RAP may be from pavements removed under the Contract, or from an existing stockpile.  Conform to Subsection 703-2.16

401-2.09 JOB MIX DESIGN.  Provide target values for gradation that satisfy both the broad band gradation limits shown in Table 703-4 and the requirements of Table 401-1, for the Type and Class of HMA specified.

TABLE 401-1

HMA MARSHALL Design Requirements

| DESIGN PARAMETER | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (Including Asphalt Binder) |  |  |
| Stability, Pounds | 1800 Min. | 1200 Min. |
| Flow, 0.01 Inch | 8 – 14 | 8 - 16 |
| Voids in Total Mix (VTM), % | 3.0 – 5.0 | 3.0 – 5.0 |
| Compaction, Number of Blows Each Side of Test Specimen | 75 | 50 |
| Asphalt Binder |  |  |
| Voids Filled with Asphalt (VFA), % | 65 - 75 | 65 - 78 |
| Asphalt Content, Min. % @ 4% VTM | 5.0 | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |
| Liquid Anti-Strip Additive**,%, Min. | 0.30 | 0.30 |
| RAP, %, Max. | 15.0 | 25.0 |

*Dust-Asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt binder (calculated by weight).

** By Weight of Asphalt Binder

The approved JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the recommended mixing temperature range.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant. The letter shall state whether or not WMA and/or RAP will be used. The letter shall include the proposed gradation for the JMD, gradations for individual stockpiles, and the blend ratio of each aggregate stockpile.

2.	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) in the proposed mix design. Furnish a total of 500 pounds of material in the proportional amounts in the proposed JMD.

3.	Five separate 1-gallon samples of the asphalt binder proposed for use in the HMA. Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature- viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, minimum 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

5.	Testing results per Subsection 106-1.03.1 for each aggregate type proposed for use.

6.	If applicable, a letter stating the WMA technology (Subsection 702-2.07) to be used, location where additive will be introduced and manufacturer’s recommended usage rate for each type of HMA.  Supply a minimum of 2-pint samples for each proposed additive.

7.	If applicable, representative samples of any RAP proposed for use.  Furnish a minimum of 200-pound sample of proposed RAP.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of HMA specified, and establish the approved JMD which will become a part of the Contract.

Anti-strip evaluation (ATM 414) of HMA mix designs that include RAP will be completed without the inclusion of the RAP.

Obtain an approved JMD prior to shipment of aggregates to an asphalt plant site or producing HMA for payment.

Contractor Mix Design.  If a bid item for JMD appears in the contract, or if the Engineer approves a request from the Contractor to perform the JMD at no cost to the Department, provide a JMD following the requirements specified in this section.  Submit the JMD to the Engineer at least 15 working days before HMA production.  Submit samples to the Engineer upon request for JMD verification testing.

All Contractor-furnished JMDs must be sealed by a professional Engineer registered in the State of Alaska.  The Professional Engineer shall certify that the JMD was performed according to the specified procedures, and meets all project specifications.

Changes. Submit a new JMD with changes noted and new samples in the same manner as the original JMD submittal when:

a.	The results of the JMD evaluation do not achieve the requirements specified in Table 401-1

b.	The asphalt binder source is changed

c.	The source of aggregate, aggregate quality or gradation is changed

d.	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD; the original, or a replacement JMD.

The Engineer has the option to require further verification of the JMD under 401-2.10 Process Quality Control.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, materials, and the JMD, Subsection 401-2.10.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.

Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix Design, per Subsection 401-5.01.

401-2.10 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer at the "Pre-Paving Meeting," Subsection 401-3.01, the JMD and a documentation plan that provides a complete, accurate, and clear record of the sampling and testing results.

Failure to perform quality control forfeits the Contractor's right to a retest under Subsection 401-4.02

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

Supplemental Process Quality Control:

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips”.

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineer's approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train shall be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 401-3.04.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Failed Test Strip:  the Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

Refer to Subsection 401-5.01 for payment of test strips.

CONSTRUCTION REQUIREMENTS

401-3.01 PRE-PAVING MEETING. Meet with the Engineer for a pre-paving meeting in the presence of the project superintendent and paving foreman at least (5) working days before beginning paving operations.  Submit a paving plan and pavement inspection plan at the meeting.  When directed by the Engineer, make adjustments to the plan and resubmit.

1.	Paving Plan.  Include the following:

a.	Sequence of operations

b.	List of equipment that will be used for production, transport, pick-up (if applicable), laydown, and compaction

c.	Summary of plant modifications (if applicable) for production of WMA

d.	Procedures to produce consistent HMA

e.	Procedures to minimize material and thermal segregation

f.	Procedures to minimize premature cooling

g.	Procedures to achieve HMA density

h.	Procedures for joint construction including corrective action for joints that do not meet surface tolerance requirements

i.	Quality control testing methods, frequencies and sample locations for gradation, asphalt binder content, and density, and

J.	Any other information or procedures necessary to provide completed HMA construction that meets the Contract Requirements

2.	Pavement Inspection Plan. Include the following:

a.	Process for daily inspections

b.	Means and methods to remove and dispose of project materials

401-3.02 CONTRACTOR QUALITY CONTROL. Perform quality control (QC) of HMA materials in accordance with Subsection 106-1.03.

401-3.03  WEATHER LIMITATIONS.  Place HMA on a stable/non-yielding roadbed. Do not place HMA when the base material is wet or frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA when the roadway surface temperature is colder than 40° F.

401-3.04 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make all equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of HMA and test strip HMA.

401-3.05  ASPHALT MIXING PLANT.  Meet AASHTO M 156.  Use an HMA plant capable of producing at least 150 tons of HMA per hour noted on posted DEC air quality permit, designed to dry aggregates, maintain consistent and accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the HMA plant and furnish copies of the calibration data to the Engineer at least 24 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.  Provide aggregate and asphalt binder sampling locations meeting OSHA safety requirements.

You may use belt conveyor scales to proportion plant blends and mixtures if the scales meet the general requirements for weighing equipment and are calibrated according to the manufacturer’s instructions.

If WMA is approved by the Engineer, modify the mixing plant as required by the manufacturer and WMA additive manufacturer.

401-3.06  HAULING EQUIPMENT.  Haul HMA in trucks with tight, clean, smooth metal beds. Keep beds free of petroleum oils, solvents, or other materials that would adversely affect the mixture. Apply a thin coat of approved asphalt release agent to beds as necessary to prevent mixture adherence. Provide trucks with covers attached and available for use.

When directed by the Engineer, cover the HMA in the hauling vehicle(s).

Do not haul HMA on barges.

401-3.07 ASPHALT PAVERS.  Use self-propelled asphalt pavers with heated vibratory screed assemblies to spread and finish HMA to the specified section widths and thicknesses without introducing thermal or material segregation.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.  Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA. Heat and vibrate screed extensions. Place auger extensions within 20 inches of the screed extensions or per written manufacturer’s recommendations.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.

Equip the paver with automatic screed controls capable of operating from a reference line or a ski from either or both sides of the paver.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.08  ROLLERS. Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Use rollers designed to compact HMA and capable of reversing without shoving or tearing the mixture. Select rollers that will not crush the aggregate or displace the HMA. Equip vibratory rollers with separate vibration and propulsion controls.

Equip the rollers with an infrared thermometer that measures and displays the surface temperature to the operator. Infrared thermometer may be hand-held or fixed to the roller.

Utilize a pneumatic roller in the complement of rollers to compact the leveling course.  Use fully skirted pneumatic-tire roller having a minimum operating weight of 3000 pounds per tire.

401-3.09  RESERVED.

401-3.10  PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces according to the Contract. Prior to placing HMA, clean existing surfaces of loose material and uniformly coat contact surfaces of curbing, gutters, manholes and other structures with tack coat material meeting Section 402.  Treat cold joint surfaces according to 401-3.17. Allow tack coat to break before placement of HMA on these surfaces.  Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before applying tack coat to an existing paved surface, clean and patch the surface.  Remove irregularities to provide a reasonably smooth and uniform surface.  Remove and replace unstable areas with HMA.  Clean the edges of existing pavements, which are to be adjacent to new pavement, to permit the adhesion of asphalt materials.  Clean loose material from cracks.  Fill the cleaned cracks, wider than 1 inch, with HMA tamped in place.  Wash and/or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

1.	Prelevel remaining ruts, pavement delaminations, and depressions having a depth greater than 1/2 inch with an approved HMA.

2.	Notify the Engineer of pavement areas that appear thin or unstable.  Where milling operation creates thin or unstable pavement areas, or where it breaks through existing pavement, remove thin and unstable pavement, and 2 inches of existing base material, compact and replace with an approved HMA.

401-3.11  PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the recommended mixing temperature range.

401-3.12  PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by ATM 407.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable per Subsection 105-1.11.

401-3.13  MIXING. Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD. Mix to obtain at least 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt binder.

Mix the HMA within the temperature range determined by the JMD.

Upon the Engineer’s request, provide daily burner charts showing start/stop times and temperatures.

401-3.14  TEMPORARY STORAGE OF HMA.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.

Signs of visible segregation, heat loss, changes from the JMD, change in the characteristics of asphalt binder, lumpiness, and stiffness of the mixture, are causes for rejection.

Do not store HMA on barges.

401-3.15  PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, are placed and accepted.

Do not place HMA abutting curb and gutter until curb and gutter are installed, except as approved by the Engineer.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

When practicable, adjust elevation of metal fixtures before paving the final lift, so they will be between 1/4 and 1/2 inch below the top surface of the final lift.  Metal fixtures include, but are not limited to manholes, valve boxes, monument cases, hand holes, and drains.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make mechanical spreading and finishing equipment impracticable.

Place HMA over bridge deck membranes according to Section 508 and the membrane manufacturer's recommendations.

Do not mix HMA produced from different plants for testing or paving.

401-3.16  COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

Prevent indentation in the mat, do not leave rollers or other equipment standing on HMA that has not sufficiently cooled.

The Lower Specification Limit for density is 92.0% of the Maximum Specific Gravity (MSG) as determined by ATM 409.  The MSG from the approved JMD is used for the first lot of each type of HMA.  The MSG for additional lots is determined from the first sublot of each lot.

401-3.17  JOINTS.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the pre-paving meeting.  Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

Form transverse joints by saw-cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints 15 to 25 degrees.

For all joints below the top lift, uniformly coat joint surfaces with tack coat material meeting Section 402.

Uniformly coat the joint face of all top lift joints with a joint adhesive. Follow joint adhesive manufacturer's recommendations for temperatures and application method.  Remove joint adhesive applied to the top of pavement surface.  If infrared joint heaters are used and passing joint densities are achieved in each of the first three joint densities taken, then joint adhesive is not required.

The Lower Specification Limit for top lift longitudinal joint density is 91.0% of the MSG of the panel completing the joint. MSG will be determined according to ATM 409.

For top lift panels that have a longitudinal joint density less than 91.0% of the MSG in a sublot, seal the surface of the longitudinal joints with joint sealant within that sublot, or as directed..  Apply joint sealant according to the manufacturer’s recommendations while the HMA is clean, free of moisture and prior to final traffic marking.  Place the sealant at a maximum application rate of 0.15 gallons per square yard, and at least 12 inches wide centered on the longitudinal joint.  After surface sealing, inlay by grinding pavement striping into the sealed HMA. Use grooving equipment that grinds a dry cut to groove the width, length, and thickness of the striping within the specified striping tolerances.

Correct improperly formed joints that result in surface irregularities according to a corrective action plan.

Complete all hot lapped joints while the mat temperature is over 230F as measured by the Engineer, within 3 inches of the joint. Tack coat and joint adhesive are not required for hot lapped joints. Hot lapped joints will receive the full Longitudinal Joint Density Price Adjustment incentive without testing for joint density.

Top lift longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03

401-3.18  SURFACE REQUIREMENTS AND TOLERANCE.  The finished surface of all HMA paving must match dimensions shown in the contract for horizontal alignment and width, profile grade and elevation, crown slope, and pavement thickness. Water must drain across the pavement surface without ponding. The surface must have a uniform texture, without ridges, puddles, humps, depressions, and roller marks. The surface must not exhibit raveling, cracking, tearing, asphalt bleeding, or aggregate segregation. Leave no foreign material, uncoated aggregate, or oversize aggregate on the HMA surface.

The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  The Engineer will identify pavement areas that deviate more than 3/16 inch from the straightedge, including joints, as defective work. Perform corrective work by removing and replacing, grinding, cold milling or infrared heating such areas as required. Do not surface patch. After the Contractor performs corrective work, the Engineer will retest the area.

The Engineer will use an inertial profiler to measure the top lift HMA surface in the driving lanes for surface smoothness within 21 days after paving is complete and driving lanes are delineated.

Profiler measurements will not be taken in turn lanes, ramps, lane transitions, or within 25 feet of bridge abutments and transverse joints with pre-existing pavement.

The Engineer will measure the pavement smoothness in both wheel paths of each lane.  The smoothness is measured as International Roughness Index (IRI), reported as inches/mile, at 0.1-mile increments.  Pavement smoothness is the average of all IRI measurements for the project.

The Engineer will identify areas requiring corrective action in accordance with Table 401-4.  Perform full-width corrective action in those areas.  The Engineer may waive corrective work for localized roughness for deficiencies resulting from manholes or other similar appurtenances near the wheel path.

Perform Corrective Actions according to one of the following or by a method approved by the Engineer:

1.	Diamond Grinding.  If the required pavement thickness is not decreased by more than 0.25”, grind to the required surface tolerance and cross section.  Remove and dispose of all waste materials.  Apply joint sealant and sand to exposed aggregates per the manufacturer’s recommendations.

2.	Overlaying.  Mill or sawcut the existing pavement to provide a vertical transverse joint face to match the overlay to the existing pavement.  Apply tack coat on the milled surface and joint adhesive to all vertical joints and overlay the full width of the underlying pavement surface.  Use the same approved HMA for overlays.  Place a minimum overlay thickness of 2.0 inches.

3.	Mill and Fill. Mill the existing pavement to provide a vertical transverse joint face. Apply tack coat to the milled surface and joint adhesive to all vertical joints prior to inlaying new HMA to match the existing pavement.  Use the same approved HMA.  Place a minimum thickness of 2.0 inches.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.

Price adjustments for pavement smoothness will be calculated according to Subsection 401-4.03.3.

401-3.19  REPAIRING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt. Remove and dispose defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat according to Section 402.  Place and compact fresh HMA so that compaction, grade, and smoothness requirements are met.

401-3.20  ROADWAY MAINTENANCE.  Inspect daily according to pavement inspection plan. Remove, and dispose of project materials incorrectly deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The Contractor is responsible for damage caused by not removing these materials and any damage to the roadway from the removal method(s).

Repair damage to the existing roadway that results from fugitive materials or their removal.

401-4.01  METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a.	By weight.  No deduction is made for the weight of asphalt binder or anti stripping additive or cutting back joints. If the use of WMA is approved by the Engineer, WMA additives will not be measured and are considered subsidiary to the HMA pay item.

b.	By the final HMA surface area.

2.	Asphalt Binder.  By weight, as follows:

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment is made for any asphalt binder more than 0.4% above the optimum asphalt binder content specified in the JMD.

Method 1: Percent of asphalt binder for each sublot multiplied by the total HMA weight represented by that sublot.  The Engineer will use either ATM 405 or ATM 406 to determine the percent of asphalt binder.  The same test method used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  In the absence of testing, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2: Supplier's invoices minus waste, diversion, and remnant.  This procedure is an Engineer’s option for projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time that tankers are weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment is based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste HMA is calculated using the target value for asphalt binder as specified in the JMD.

3.	Job Mix Design. When specified, a Contractor furnished JMD is measured as one according to the HMA class and type.

4.	Temporary Pavement.  By weight, without deduction for the weight of asphalt binder or anti-strip additive.

5.	Leveling Course.  By Lane-Station (12 foot width) or by weighing without deduction for the weight of asphalt binder or anti-strip additive.

6.	HMA Price Adjustment.  Calculated by quality level analysis under Subsection 401-4.03.1.

7.	Longitudinal Joint Density Price Adjustment.  By the linear foot of top lift longitudinal joint under Subsection 401-4.03.2.

8.	Joint Adhesive.  By the linear foot of longitudinal and transverse joint.

9.	Pavement Smoothness Price Adjustment.  Calculated from inertial profiler data using FHWA’s ProVAL software under Subsection 401-4.03.3.

10.	Asphalt Material Price Adjustment.  Determined under Subsection 401-4.04.

11.	Liquid Anti-Strip Additive.  Based on the number of tons of asphalt binder containing required additive.

12.	Crack Repair.  From end to end of the crack repaired according to 401-3.10, measured horizontally along the centerline of the crack.

13.	Prelevel for Ruts, Delaminations, and Depressions.  By the surface area where prelevel is placed according to 401-3.10(1), measured according to Section 109.

14.	Repair Unstable Pavement.  By the surface area of pavement repaired according to 401-3.10(2), measured according to Section 109.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.

1.	Hot Mix Asphalt

The bid quantity of each type of HMA produced and placed is divided into lots and the lots evaluated individually for acceptance.

A lot is normally 5,000 tons. The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 401-4.03.1. Seasonal startup or a new JMD requires starting a new lot.

If less than 8 sublots have been placed at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot. The price adjustment computed for the prior lot will include the samples from the shortened lot. Density test results from material in the shortened lot will be based on the MSG of the first sublot of the shortened lot. If there is no prior lot, and there are at least 3 sublots, the material in the shortened lot will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot. If there are less than 3 sublots, the HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances.

If 8 or 9 sublots have been placed at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot.

If the bid quantity is between 1,500 to 5,000 tons, the quantity is considered one lot.  The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection.

For bid quantity less than 1,500 tons, HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances.

The Engineer reserves the right to perform any testing required in order to determine acceptance.

a.	Asphalt Binder Content. HMA samples shall be taken randomly by the Contractor in the presence of the Engineer from behind the paver screed before initial compaction, or will be taken randomly by the Engineer from the windrow, according to ATM 402 or ATM 403, at the discretion of the Engineer. The location (behind the paver screed or windrow) will be determined at the pre-paving meeting.  The Engineer will determine random sampling locations.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  At the discretion of the Engineer, Asphalt binder content will be determined according to ATM 405 or ATM 406.

b.	Aggregate Gradation. Aggregates tested for gradation acceptance will have the full tolerances from Table 401-2 applied.

(1).	Drum Mix Plants. Samples will be taken from the combined aggregate cold feed conveyor via a diverter device, from the stopped conveyor belt or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for samples from the conveyer system will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.

(2)	Batch Plants. Samples will be taken from dry batched aggregates according to ATM 301 or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for dry batch samples will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder.

c.	Density. The Engineer will determine and mark the location(s) where the Contractor takes each core sample.

(1)	Mat Cores: The location(s) for taking core samples is determined using a set of random numbers (independent of asphalt binder and aggregate sampling set of random numbers) and the Engineer's judgment. Take no mat cores within 1 foot of a joint or edge. Core samples are not taken on bridge decks.

(2)	Longitudinal Joint Cores: The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.

Take core samples according to ATM 413 in the presence of the Engineer. Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one six-inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  The Engineer will immediately take possession of the samples.  Backfill and compact voids left by coring with new HMA within 24 hours, and according to ATM 413. The Engineer will determine density of samples according to ATM 410.

d.	Asphalt Binder Content, Aggregate Gradation, and Density - Retest. When test results have failed to meet specifications, retest of acceptance test results for asphalt binder content, gradation, and density may be requested provided the quality control requirements of Subsection 401-3.02 Contractor Quality Control are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2-foot radius of the original core.  The original test results are discarded and the retest result is used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  When gradation and asphalt binder content are determined from the same sample, a request for a retest of either gradation or asphalt binder content results in a retest of both. Both gradation and asphalt binder content retest results are used in the price adjustment calculation. Except for the first lot, retesting for gradation or asphalt binder from the first sublot of a lot will include retesting for the MSG. Retesting will be performed by a Department laboratory.

2.	Asphalt Binder

The bid quantity of asphalt binder produced and placed is divided into lots and the lots evaluated individually for binder grade acceptance.

Testing will be by AASHTO accredited independent laboratories. When retesting is requested, the assigned value (ATV) will be determined using ASTM D3244. Each test will be completed by a different laboratory.

a.	Acceptance Test. The lot size for asphalt binder is 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it is added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it is sampled, tested and evaluated as a separate lot.

If the bid quantity of asphalt binder is between 85 to 200 tons, the quantity is considered as one lot and sampled, tested, and evaluated according to this subsection. Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Sample asphalt binder at the plant from the supply line in the presence of the Engineer according to ATM 401.  The Engineer will take immediate possession of the samples. Take three samples from each lot, one for acceptance testing, one for Contractor requested retesting, and one held in reserve for referee testing if requested.  Meet Subsection 702-2.01 requirements for asphalt binder quality.

b.	Retest. Submit a written request, for a retest, no more than 7 days from receiving notice of the failed acceptance test. In the request, identify the retest laboratory. The Engineer will send the second sample (retest sample) to the laboratory.  Provide the retest results to the Engineer. Contractor pays for the retest costs.

If the average of the combined test results ([acceptance + retest]/2) passes the specification requirement, the average value becomes the ATV. If this ATV fails the specification requirement, the Engineer or Contractor may request the third sample (referee sample) be tested.

c.	Referee Test. The Engineer will send the third sample (referee sample) to an agreed upon laboratory. The average of the combined test results ([acceptance + retest + referee]/3) equals the ATV. If the ATV fails to meet specifications, the Contractor pays for the referee test.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The Engineer may reject material which appears to be defective based on visual inspection.  If a test of rejected material is requested, a minimum of two samples are collected from the rejected material and tested.  If all test results are within specification limits, payment for the material is made.

The following methods are applied to each type of HMA with Price Adjustment Pay Items in the Contract. These methods describe how price adjustments are determined based on the quality of the HMA binder longitudinal joint density and pavement smoothness.

1.	HMA Price Adjustment.  Acceptance test results for HMA asphalt binder content, gradation and mat density are used in HMA price adjustment.  These test results for a lot are analyzed collectively and statistically by the Quality Level Analysis (QLA) method as specified in Subsection 106-1.03.3 to determine the total estimated percentage of the lot that is within specification limits. The values for percent passing the #200 sieve, asphalt binder content and density test results are reported to the nearest 0.1 percent.  All other sieves used in QLA are reported to the nearest whole number.

The HMA price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor (CPF) for HMA that includes gradation and asphalt binder content.  The second is the density pay factor (DPF).

A lot containing material with less than a 1.000 pay factor is accepted at an adjusted price, provided that pay factor is at least 0.800 and there are no isolated defects identified by the Engineer. A lot containing material that fails to obtain the minimum pay factor is considered unacceptable and rejected under Subsection 105-1.11.

HMA pay factors are computed as follows:

a.	All statistical Quality Level Analysis (QLA) is computed using the Engineer’s Price Adjustment programs.

b.	The USL and LSL are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2, or as shown below.  The TV is the specification value shown in the approved Job Mix Design.

TABLE 401-2

HMA LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4-inch or largest sieve size | 99 | 100 |
| 1/2-inch sieve or first sieve retaining aggregate | TV -6 | TV +6 |
| 3/8-inch sieve | TV -6 | TV +6 |
| No. 4 sieve | TV -6 | TV +6 |
| No. 8 sieve | TV -6 | TV +6 |
| No. 16 sieve | TV -5 | TV +5 |
| No. 30 sieve | TV -4 | TV +4 |
| No. 50 sieve | TV -4 | TV +4 |
| No. 100 sieve | TV -3 | TV +3 |
| No. 200 sieve* | TV -2.0 | TV +2.0 |
| Asphalt Binder Content, % | TV -0.4 | TV +0.4 |
| Mat Density, % | 92.0 | 100.0 |

*LSL for the No. 200 sieve is restricted by the broadband limits in Table 703-4.

c.	The percent within limits (PWL), Quality Levels and characteristic pay factors (PFs) are determined by the Engineer for each Lot in accordance with Subsection 106-1.03.3.  The Composite Pay Factor (CPF) for the lot is determined from gradation and asphalt binder content (ac) acceptance test results using the following example formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

Table 401-3 gives the weight factor (f) for each test property considered.

TABLE 401-3

WEIGHT FACTORS

| Property | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1-inch sieve | 4 | - | - |
| 3/4-inch sieve | 4 | 4 | - |
| 1/2-inch sieve | 4 | 5 | 4 |
| 3/8-inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve* | 20 | 20 | 20 |
| Asphalt Content, % | 40 | 40 | 40 |

The Density Pay Factor (DPF) is computed using HMA mat core compaction acceptance test results.

The CPF and DPF are rounded to the nearest 0.001.  The price adjustment for each individual lot is calculated as follows:

HMA Price Adjustment = [(CPF or DPF)* -1.000] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower

PAB = Price Adjustment Base = $110.00 per ton.

The HMA Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 401.0008.____.

2.	Longitudinal Joint Density Price Adjustment.  Longitudinal joint density price adjustment will be based on the project average of all top lift cold joint densities and determined as follows:

a.	Disincentive. Project average top lift joint density less than 91.0% MSG:

Deduct $3.00 per lineal foot.

b.	Incentive. Project average top lift joint density greater than:

92.0% MSG.		Add $0.50 per lineal foot

93.0% MSG.		Add $1.00 per lineal foot

94.0% MSG.		Add $1.50 per lineal foot

The longitudinal Joint Density Price Adjustment is the total price adjustment paid for under Item 401.0009.____.

3.	Pavement Smoothness Price Adjustment.  Pavement smoothness will be measured by the Engineer and reported as IRI (inches/mile), according to Subsection 401-3.18.  Incentive for pavement smoothness shall apply only if both the project average CPF and DPF are greater than or equal to 1.000.  Disincentive for pavement smoothness shall apply regardless of the project average CPF or DPF.

The Engineer will calculate the pavement smoothness price adjustment according to Method 1 (pavement placed over graded subgrade), and/or Method 2 (pavement placed over existing pavement). The SF is rounded to the nearest 0.001.

Method 1: SPA = PAB x PQ x SF,

where:

SPA = Pavement Smoothness Price Adjustment

PAB = $110.00 per ton,

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor (Table 401-4)

TABLE 401-4

SMOOTHNESS FACTOR (SF)

| IRI (in./mile) | SF |
| --- | --- |
| Less than 40.0 | 0.050 |
| 40.0 to 70.0 | 0.050 – (IRI – 40.0)/600.0 |
| 70.0 to 90.0 | 0.000 |
| 90.0 to 120.0 | (90.0 – IRI)/120.0 |
| Greater than 120.0* | - |

* Corrective Work required, see Subsection 401-3.18

Method 2: SPA = PAB x PQ x SF,

Where:

SPA = Pavement Smoothness Price Adjustment

PAB = $110.00 per ton,

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor = 0.120 x RR – 0.020; SF not to exceed 0.050

RR = Roughness Reduction = (Initial IRI – Final IRI) / Initial IRI

Initial IRI = 	Pre-project average IRI as measured and reported by the Engineer.  The Initial IRI will either be included in the bid documents or the timeline for when the Initial IRI will be measured will be identified in the bid documents.

Final IRI =	Top layer HMA average IRI as measured and reported by the Engineer according to Subsection 401-3.18.

The Pavement Smoothness Price Adjustment is the total price adjustment paid for under Item 401.2010.____.

4.	Asphalt Binder Price Adjustment. A lot quantity of asphalt binder, with a pay factor less than 1.00, is accepted or rejected per Table 401-3.01-1 Asphalt Binder Pay Factors.

TABLE 401-4.03-1

ASPHALT BINDER PAY FACTORS

| Pay Factor |  |  | 1.01 | 1.00 | 0.95 | 0.90 | 0.75 | Reject |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RTFO (Rolling Thin Film Oven) |  |  |  |  |  |  |  |  |
| DSR(a.1) | All Grades | G*/Sinδ, kPa-1 | ≥ 2.69 | 2.68–2.20 | 2.19–1.96 | 1.95–1.43 | 1.42–1.10 | < 1.10 |
| MSCR(a.2) | PG 52-40 E | JNR 3.2 |  0.39 | 0.40–0.50 | 0.51–0.59 | 0.60–0.69 | 0.70–1.00 | > 1.00 |
|  |  | % Rec3.2 | ≥ 86.0 | 85.9–75.0 | 74.9–68.0 | 67.9–60.0 | 59.9–55.0 | < 55.0 |
|  | PG 58-34 E | JNR 3.2 |  0.19 | 0.20–0.25 | 0.26–0.29 | 0.30–0.39 | 0.40–0.50 | > 0.50 |
|  |  | % Rec3.2 | ≥ 90.0 | 89.9–85.0 | 84.9–80.0 | 79.9–75.0 | 74.9–70.0 | < 70.0 |
|  | PG 64-40 E | JNR 3.2 | < 0.05 | 0.05–0.10 | 0.11–0.15 | 0.16–0.20 | 0.21–0.25 | > 0.25 |
|  |  | % Rec3.2 | ≥ 97.0 | 96.9–95.0 | 94.9–91.0 | 90.9–85.0 | 84.9 – 80.0 | < 80.0 |
| PAV (Pressurized Aging Vessel) |  |  |  |  |  |  |  |  |
| DS(a.3) | PG 64-40 E & All Other Grades | G*Sinδ, kPa | < 4711 | 4712–5000 | 5001–5289 | 5290–5578 | 5579–5867 | > 5867 |
|  | PG 52-40 E, PG 58-34 E | G*Sinδ, kPa | < 5700 | 5701–6000 | 6001–6300 | 6301–6600 | 6601 – 7000 | > 7000 |
| CS(a.4 & 5) | All Grades(a.4) | BBR, S, MPa | < 247 | 248–300 | 301–338 | 339–388 | 389–449 | > 450 |
|  | All Grades(a.5) | BBR, m | > 0.320 | 0.319–0.300 | 0.299–0.294 | 0.293–0.278 | 0.277–0.261 | < 0.261 |

Creep Stiffness (CS)	Dynamic Shear (DS)	Multiple Stress Creep Recovery (MSCR)

a.	Asphalt Binder Pay Adjustment = (Lowest Pay Factor – 1.00) x (tons in lot) x PAB x 5

Select the lowest pay factor from:

RTFO (test the binder residue at the performance grade temperature)

(1)	DS, All Grades, G*/Sinδ, kPa-1

(2)	MSCR: PG, Select the highest pay factor corresponding to, either JNR 3.2 or % Rec3.2 values

PAV

(3)	DS, PG, G*Sinδ, kPa

(4)	CS, All Grades, BBR, S MPa

(5)	CS, All Grades, BBR, m

b.	If three consecutive acceptance samples are out of specification, stop HMA production immediately and submit a corrective action plan to the Engineer for approval.

The Asphalt Binder Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 401.2021.____.

401-4.04  ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Subsection 702-2.01 Asphalt Binder, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

401-5.01 BASIS OF PAYMENT.

The following items, unless included as individual Pay Items, are subsidiary to the Section 401 Hot Mix Asphalt Pavement related Pay Items as included in the bid schedule:

	Asphalt binder

	Liquid anti-strip additives

	Tack coat

	Crack sealing

	Crack repair

	Joint adhesive

	Surface sealing of longitudinal joints

	Surface tolerance corrections

	Patching defective areas

	Prelevel for ruts, delaminations, and depressions

	Repair unstable pavement

	Job mix design

	Density profiles, Subsection 401-2.10 Process Quality Control

	Repair work and materials when planing equipment breaks through existing pavement – Subsection 401-3.10 Preparation of Existing Surface

	Work and materials associated with Subsection 401-3.06 Hauling Equipment

	Work and materials associated with Subsection 401-3.20 Roadway Maintenance

Test Strips:  Subsection 401-2.10 Process Quality Control.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices for HMA and asphalt binder as included in the Bid Schedule.  Price adjustments 401.0008.____, 401.009.____, 401.0010.____ and 401.2021.____ do not apply.

b.	Failed.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Item 401.0005.____ HMA, Temporary, Type     ; Class     . Removal and disposal of temporary HMA is subsidiary.

The following price adjustment Pay Items, unless included as individual Pay Items in the bid schedule, are paid under 401.2022.____ Combined Price Adjustment.

401.0008.____ HMA Price Adjustment, Type     ; Class     ,

401.0009.____ Longitudinal Joint Density Price Adjustment,

401.0010.____ Pavement Smoothness Price Adjustment, Method    .

401.2021.____ Asphalt Binder Price Adjustment

Item 401.0008.____ HMA Price Adjustment, Type    ; Class    , is the sum of the price adjustments for each material lot, and for deductions and fees assessed.  Deductions and fees assessed include:

	Each mix design subsequent to the approved JMD for each type and class of HMA specified will result in a fee of $6000.

	Failure to cut core samples within the specified period will result in a deduction of $100 per sample per day.

	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day.

	If an asphalt binder referee test is requested and the ATV confirms the asphalt binder does not meet Contract requirements, a fee of $500 will be assessed.

Items 401.0008.____ HMA Price Adjustment, Type    ; Class    , and 401.2022.____ Combined Price Adjustment do not apply to the following:

	HMA contract quantity is less than 1500 tons.

	HMA leveling course and rut repair.

	Temporary HMA.

	Driveway and approach HMA.

Item 401.0015.____ Asphalt Material Price Adjustment.

For each Section as included in Subsection 401-4.04 Asphalt Material Price Adjustment, item 1.a, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

Item 401.0016.____ Crack Repair.  Cleaning loose material from cracks, asphalt binder, and HMA to fill cracks are subsidiary.

Item 401.0017.____ Prelevel for Ruts, Delaminations, and Depressions.  Cleaning loose material, asphalt binder, and HMA are subsidiary.

Item 401.0018.____ Repair Unstable Pavement. Removal of pavement and base course, asphalt binder, and HMA are subsidiary.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 401.0001.____ | HMA, Type ; Class . | Ton |
| 401.0002.____ | HMA, Leveling Course, Type IV ; Class B | LnSt |
| 401.0003.____ | HMA, Leveling Course, Type IV ; Class B | Ton |
| 401.0004.____ | Asphalt Binder, Grade PG ##-## X | Ton |
| 401.0005.____ | HMA, Temporary, Type II, Class B | Ton |
| 401.0006.____ | HMA, Type , Class . | SY |
| 401.0007.____ | Liquid Anti-Strip Additives | CS |
| 401.0013.____ | Job Mix Design | Each |
| 401.0014.____ | Joint Adhesive | LF |
| 401.0015.____ | Asphalt Material Price Adjustment | CS |
| 401.0016.____ | Crack Repair | LF |
| 401.0017.____ | Prelevel for Ruts, Delaminations, and Depressions | SY |
| 401.0018.____ | Repair Unstable Pavements | SY |
| 401.2022.____ | Combined Price Adjustment | CS |

CR401-010122

- SECTION 402
TACK COAT

Standard Modification

Replace Subsection 402-3.02 with the following:

402-3.02 EQUIPMENT. Furnish, maintain, and operate asphalt distributor to apply asphalt material uniformly at even heat on variable widths of surface up to 15 feet at readily determined and controlled flow rates. Provide an asphalt distributor capable of application rates from 0.01 to 0.11 gallon per square yard. Equip with a heater, tachometer, flow rate gauge, operable mechanical tank gauge, thermometer for measuring temperatures of tank contents, power unit for the pump and full circulation spray bars adjustable laterally and vertically.

402-3.04 APPLICATION OF ASPHALT MATERIAL.

Add the following at the end of the first paragraph:

Control deviation from any specified application rate to within 0.02 gallon per square yard.

Add the following after the second paragraph:

After application of the tack coat, the surface shall be allowed to cure without being disturbed for the period of time necessary to permit drying and setting of the tack coat. If necessary, the Engineer will determine when the tack has cured.

CR402.HSM20.6-113020

Special Provision

Replace Section 406 with the following:

SECTION 406
RUMBLE STRIPS

406-1.01 DESCRIPTION.  Form a series of indentations (rumble strips) into the roadway pavement.  Place rumble strips in each shoulder to the width, depth, and length as indicated in the Contract documents and/or as directed by the Engineer.

406-1.02 RUMBLE STRIP.  A single uniform circular concave (cross section) indentation/depression milled into the pavement surface having a length measured perpendicular to the direction of travel, a width measured in the direction of travel and a depth measured from the surface of the pavement to the bottom of the indentation.

406-2.01 MATERIALS.  None.

406-2.02 MILLING EQUIPMENT.  Use equipment designed specifically for milling rumble strips into asphalt pavement.  Equip milling machine with a rotary type cutting head with a maximum outside diameter of 24-inches and a minimum length of 16-inches capable of producing a depression both 12-inches and 16-inches in length by 7 1/2-inches in width to a depth shown in the Plans.  Arrange the cutting tips to provide a smooth cut (approximately 1/16-inch between peaks and valleys).

Furnish the milling equipment with a guidance system, including a guide, clearly visible to the operator, to provide for consistent alignment of each rumble strip cut at the offsets from traveled way indicated on the Plans and to provide uniformity and consistency throughout the project.  The equipment shall incorporate water into the cutting head to minimize dust caused by the milling operation.

Equipment Manufacture: provide training for the operators and a representative onsite during installation of the rumble strip test section(s) (Subsection 406-3.03).  Representative: remain onsite until test specimen(s) satisfy the Plans and Specifications as determined by the Engineer.

CONSTRUCTION REQUIREMENTS

406-3.01 PAVEMENT SURFACE PREPARATION.  Inspect roadway to receive rumble strips for acceptable pavement condition and stake locations to receive rumble strips prior to installation.  Prepare the roadway for the milling operation by providing a smooth clean surface.  Sweep all loose material from the roadway surface in line with the planned rumble strips and to each side of the strips for the width of the milling machine plus an additional 12” minimum per side or edge of pavement whichever is smaller, and as directed by the Engineer.

Sweep and broom as noted and with the equipment indicated in Subsection 643-3.04, No. 6, Sweeping and Power Brooming.

406-3.02 TOLERANCES FOR RUMBLE STRIPS.

1. Length:   1/2-inch.

2. Width:  1/2-inch.

3. Depth:  1/16-inch.

4. Spacing:   1/2-inch.

5. Alignment:  1-inch from the striping layout in the Plans; existing striping and re-established striping.

If it is determined that the rumble strips are not being placed to specification, make immediate adjustments to correct the problem.

Rumble strips are unacceptable if:

1. The strips are not straight.

2. The length or width does not meet tolerance.

3. The depth of the depression does not meet tolerance.

4. The depression/indentation concave surface is not smooth, does not meet tolerance.

5. The edge of the indentation/depression is not straight, smooth, and free of spalling.

6. Pavement surface is damaged as a result of improper rumble strip installation.

Unacceptable rumble strip installation, dimensional, alignment, surface irregularities, and surface damage shall be ground, resurfaced and the rumble strip reinstalled to the satisfaction of the Engineer and at the Contractor’s expense.  Perform repairs using equipment similar to the equipment initially used to mill the rumble strip.  Do not perform repairs in a “patch work” manner.  If more than one repair is required; in a group of rumble strips repair the entire group.  Where a repair is required in a continuous run, repair the unacceptable rumble strip(s) and repair or replace the rumble strip to each side of the unacceptable rumble strip as required to provide continuity between rumble strips as originally intended.  The Engineer will confirm the extent of the repair(s) required.

If during production the work becomes unacceptable the Engineer may require resumption of testing, Subsection 406-3.03.  Testing in addition to the initial test for each rumble strip type will be at the Contractor’s expense.

406-3.03 RUMBLE STRIP TEST SECTION.  Install an initial 1/4 mile test section for each of the following rumble strip type(s):

1.	Shoulder.

Demonstrate for each type of rumble strip that the equipment and method will provide the desired milled-in rumble strip, including the surface inside each depression, without damaging the surrounding asphalt pavement.  If any of the initial test sections do not meet tolerances, provide new equipment, new method, or make necessary adjustments and retest.  These additional test sections will be required before production runs will be allowed to begin.

Testing in addition to the initial test sections, one for the shoulder type and one for the centerline type, will be at the Contractor’s expense.

Additionally, demonstrate the means and methods, including the equipment, for containing dust and waste material.

406-3.04 TRAFFIC STRIPING RE-ESTABLISHMENT.  Traffic striping is required to provide guidance for the rumble strip installation operation.  Contractor, where shoulder and/or centerline striping is missing to the extent that rumble strip location cannot be determined by the Engineer, re-establish the striping location prior to the milling operation.  Re-establish missing striping location by measuring laterally across the roadway from adjacent visible striping.  Maintain the same lane widths that exist at each end of the missing striping.  Provide sufficient location marking or “rabbit tracks” to ensure an accurate milling operation.  Shoulder re-striping is not required.  Re-establishing roadway striping location will not be measured or paid for separately but will be subsidiary to the respective rumble strip pay items.

406-3.05  RUMBLE STRIP INSTALLATION.  Install the following types of rumble strip at the locations shown in the Plans:

1.	Shoulder.  Do not disturb existing shoulder striping.

In compacted pavement with a temperature below 80˚ F, mill each type of rumble strip to the dimensions shown in the Plans.  Locate the inside edge of the rumble strip as shown in the Plans.  The Engineer will randomly check the edge alignment of the milled pattern.

406-3.06 CLEAN UP OF MILLINGS.  Handle, transport, and store, or dispose of material according to the Alaska Department of Environmental Conservation (ADEC) regulations.  Remove off the project, on a daily basis, waste material (millings) resulting from the operation.

Disposal:  Dispose waste material outside the project limits, unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the property owner.  Milled material not being spread on the roadway side slopes requires a Solid Waste Disposal Permit from the DEC.  Obtain a permit for disposal of milled material or dispose the material in a site previously approved.

Remove millings immediately following rumble strip installation.  Maintain the removal operation within 50 feet of the milling machine.  Dry power brooming and power brooming without direct immediate means of collection/pickup is not permitted.

During milling operations keep the travel lanes free of milling debris.  Do not berm the millings at the shoulder edge, do not allow milling debris to impede roadway drainage or enter waterways.  Use a sweeper, sweeper/vacuum, (Subsection 643-3.04 No. 6, Street Sweeping, and Power Brooming), continuously removing waste material, including dust from the operation.  Keep millings damp to help control airborne dust.  Millings shall not enter adjacent lanes open to traffic.

Remove the waste material from the roadway surface and any adjacent pathway beyond the shoulder.  Shoulder millings may be placed off of the road or pathway beyond the shoulder on the side slopes, except in areas where guardrail is present.  Uniformly spread shoulder millings on the roadway side slopes; alternatively, it may become property of the Contractor and disposed of off the project as indicated above.

Milled roadway segments shall be returned to debris-free state prior to re-opening for traffic.

406-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Measure pay units by station, foot, or mile parallel to the centerline of the highway.

Station.  A single lineal measurement for every measured station for each shoulder rumble strip and centerline rumble strip installed.

Linear Foot.  A single lineal measurement for every measured foot of rumble strip installed.

Mile.  A single lineal measurement for every measured mile for each shoulder rumble strip and centerline rumble strip installed.

CR406-110812R1/CFHWY00599

Shoulder rumble strip measurement includes gaps (provided for bicycles, intersections, or other as shown in the Plans) between groups of rumble strips.

CFHWY00599

406-5.01 BASIS OF PAYMENT.  Section 109.

All work, including test strips and materials, is subsidiary to 406 Pay Items, except where specified as individual Pay Items.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 406.0001.____ | Rumble Strips | LS |
| 406.0002.____ | Rumble Strips | STA |
| 406.0003.____ | Rumble Strips | LF |
| 406.0008.____ | Rumble Strips, Shoulders | Mile |
| 406.0012.____ | Rumble Strips, Centerline | Mile |
| 406.2001.____ | Sweeping and Disposal of Millings, Shoulders | LS |
| 406.2002.____ | Sweeping and Disposal of Millings, Centerline | LS |

CR406-110812R1

Special Provision

Add the following Section:

SECTION 408
HOT MIX ASPHALT PAVEMENT - TYPE Vh

(Superpave)

408-1.01  DESCRIPTION.  Construct one or more courses of plant-produced Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

1.	In this Section HMA refers to Type VH, except where noted otherwise.

408-1.02  REFERENCES.

1.	Section 401 Hot Mix Asphalt Pavement. (HMA Type I, II, III, and IV)

a.	Temporary Asphalt Pavement: HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV, Class B.

MATERIALS

408-2.01  ASPHALT BINDER.  Conform to Subsection 702-2.01. If binder performance grade is not specified, use PG 64-40E.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of liquid anti-strip added.

Asphalt binder may be conditionally accepted at the source if a manufacturer's certification of compliance is provided, according to Subsection 106-1.05, and the applicable requirements of Section 702 are met.

408-2.02  LIQUID ANTI-STRIP ADDITIVE. Use anti-strip agents in proportions determined by ATM 414 and included in the approved Job Mix Design (JMD). At least 90% of the aggregate must remain coated when tested according to ATM 414. The following minimum dose (percent) of liquid anti-strip by weight of asphalt binder is required:

| Liquid Anti-strip Type | Minimum Dose by Weight of Asphalt Binder, % |
| --- | --- |
| Amines based | 0.30 |
| Phosphate Ester based | 0.30 |
| Organ-Silane based | 0.05 |

408-2.03 JOINT ADHESIVE. Conform to Subsection 702-2.05.

408-2.04  JOINT SEALANT. Conform to Subsection 702-2.06.

408-2.05  WARM MIX ASPHALT. Conform to Subsection 702-2.07.

408-2.06  ASPHALT RELEASE AGENT.  Conform to Subsection 702-2.08.

408-2.07  AGGREGATES. Conform to Subsection 703.2.04. Use a minimum of three stockpiles of crushed aggregate (coarse, intermediate, and fine).  Place blend material, if any, in a fourth pile.

408-2.08  RECYCLED ASPHALT PAVEMENT. Not allowed in connection with HMA Type VH.

408-2.09  JOB MIX DESIGN.  Provide target values for gradation that satisfy both the broad band gradation limits shown in Table 703-4 and the requirements for Table 408-1 for Type VH HMA.

TABLE 408-1

HMA Design Requirements

| DESIGN PARAMETERS |  |
| --- | --- |
| Design ESALs, Millions | 0.3 to < 3 |
| Rut Index, Max., ATM 419. mm | 3 |
| Asphalt Binder Content, Min. % | 5.0 |
| Liquid Anti-Strip Additive*, % Min. | 0.3 |

* By weight of asphalt binder.

The approved JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the HMA, the Additives, and the recommended mixing temperature range.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant.  The letter shall include the proposed gradation for the JMD, gradation for individual stockpiles, and the blend ratio of each aggregate stockpile.

2.	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) in the proposed mix design. Furnish a total of 500 pounds of material in the proportional amounts in the proposed JMD.

3.	Five separate 1-gallon samples of the asphalt binder proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

5.	Testing results per Subsection 106-1.03.1 for each aggregate type proposed for use.

The Engineer will evaluate the material and the proposed gradation using ATM 417 or AASHTO R35 and the requirements of Table 408-1 for Type VH HMA, and establish the approved JMD which will become a part of the Contract.

Obtain an approved JMD prior to shipment of aggregates to an asphalt plant site or producing HMA for payment.

Contractor Mix Design.  If a bid item for JMD appears in the contract, or if the Engineer approves a request from the Contractor to perform the JMD at no cost to the Department, provide a JMD following the requirements specified in this section.  Submit the JMD to the Engineer at least 15 working days before HMA production.  Submit samples to the Engineer upon request for JMD verification testing.

All Contractor-furnished JMDs must be sealed by a professional Engineer registered in the State of Alaska.  The Professional Engineer shall certify that the JMD was performed according to the specified procedures, and meets all project specifications.

Changes. Submit a new JMD with changes noted and new samples in the same manner as the original JMD submittal when:

a.	The results of the JMD evaluation do not achieve the requirements specified in Table 408-1

b.	The asphalt binder source is changed

c.	The source of aggregate, aggregate quality or gradation is changed

d.	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD; the original, or a replacement JMD.

The Engineer has the option to require further verification of the JMD under 408-2.10 Process Quality Control.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, materials, and the JMD, Subsection 408-2.10.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.

Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix Design, per Subsection 408-5.01.

408-2.10 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer at the "Pre-Paving Meeting", Subsection 408-3.01, the JMD, and a documentation plan that provides a complete, accurate, and clear record of the sampling and testing results.

Failure to perform quality control forfeits the Contractor's right to a retest under Subsection 408-4.02

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

Supplemental Process Quality Control.

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips”.

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineer's approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train shall be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 408-3.04.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Failed Test Strip:  the Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

Refer to Subsection 408-5.01 for payment of test strips.

CONSTRUCTION REQUIREMENTS

408-3.01  PRE-PAVING MEETING. Meet with the Engineer for a pre-paving meeting in the presence of the project superintendent and paving foreman at least (5) working days before beginning paving operations.  Submit a paving plan and pavement inspection plan at the meeting.  When directed by the Engineer, adjust the plan and resubmit.

1.	Paving Plan.  Include the following:

a.	Sequence of operations

b.	List of equipment that will be used for production, transport, pick-up (if applicable), laydown, and compaction

c.	Reserved

d.	Procedures to produce consistent HMA

e.	Procedures to minimize material and thermal segregation

f.	Procedures to minimize premature cooling

g.	Procedures to achieve HMA density

h.	Procedures for joint construction including corrective action for joints that do not meet surface tolerance requirements

i.	Quality control testing methods, frequencies and sample locations for gradation, asphalt binder content, and density, and

J.	Any other information or procedures necessary to provide completed HMA construction that meets the Contract Requirements

2.	Pavement Inspection Plan. Include the following:

a.	Process for daily inspections

b.	Means and methods to remove and dispose of project materials

408-3.02 CONTRACTOR QUALITY CONTROL. Perform quality control (QC) of HMA materials in accordance with Subsection 106-1.03.

408-3.03  WEATHER LIMITATIONS.  Place HMA on a stable/non-yielding roadbed. Do not place HMA when the base material is wet or frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA when the roadway surface temperature is colder than 40° F, or after September 15th without the Engineer's approval in writing.

408-3.04  EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production and test strip HMA.

408-3.05  ASPHALT MIXING PLANT.  Meet AASHTO M 156.  Use an HMA plant capable of producing at least 150 tons of HMA per hour noted on posted DEC air quality permit, designed to dry aggregates, maintain consistent and accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the HMA plant and furnish copies of the calibration data to the Engineer at least 24 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.  Provide aggregate and asphalt binder-sampling locations meeting OSHA safety requirements.

You may use belt conveyor scales to proportion plant blends and mixtures if the scales meet the general requirements for weighing equipment and are calibrated according to the manufacturer’s instructions.

408-3.06  HAULING EQUIPMENT.  Haul HMA in trucks with tight, clean, smooth metal beds. Keep beds free of petroleum oils, solvents, or other materials that would adversely affect the mixture. Apply a thin coat of approved asphalt release agent to beds as necessary to prevent mixture adherence. Provide trucks with covers attached and available for use.

Do not haul HMA on barges.

When directed by the Engineer cover the HMA in the hauling vehicle(s).

408-3.07  ASPHALT PAVERS. Use self-propelled asphalt pavers with heated vibratory screed assemblies to spread and finish HMA to the specified section widths and thicknesses without introducing thermal or material segregation.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.  Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA. Heat and vibrate screed extensions. Place auger extensions within 20 inches of the screed extensions or per written manufacturer’s recommendations.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.

Equip the paver with automatic screed controls capable of operating from a reference line or a ski from either or both sides of the paver.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

408-3.08  ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Use rollers designed to compact HMA and capable of reversing without shoving or tearing the mixture. Select rollers that will not crush the aggregate or displace the HMA. Equip vibratory rollers with separate vibration and propulsion controls.

Equip the rollers with an infrared thermometer that measures and displays the surface temperature to the operator. Infrared thermometer may be hand-held or fixed to the roller.

Utilize a pneumatic roller in the complement of rollers to compact the leveling course.  Use fully skirted pneumatic-tire roller having a minimum operating weight of 3000 pounds per tire.

408-3.09  RESERVED.

408-3.10  PREPARATION OF EXISTING SURFACE. Prepare existing surfaces according to the Contract. Prior to placing HMA, clean existing surfaces of loose material and uniformly coat contact surfaces of curbing, gutters, manholes and other structures with tack coat material meeting Section 402.  Treat cold joint surfaces according to 408-3.17.  Allow tack coat to break before placement of HMA on these surfaces.  Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before applying tack coat to an existing paved surface, clean and patch the surface.  Remove irregularities to provide a reasonably smooth and uniform surface.  Remove and replace unstable areas with HMA.  Clean the edges of existing pavements, which are to be adjacent to new pavement, to permit the adhesion of asphalt materials.  Clean loose material from cracks.  Fill the cleaned cracks, wider than 1 inch, with HMA tamped in place.  Wash and/or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

1.	Prelevel remaining ruts, pavement delaminations, and depressions having a depth greater than 1/2 inch with an approved HMA.

2.	Notify the Engineer of pavement areas that appear thin or unstable.  Where milling operation creates thin or unstable pavement areas, or where it breaks through existing pavement, remove thin and unstable pavement, and 2 inches of existing base material, compact and replace with an approved HMA.

408-3.11  PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the recommended mixing temperature range.

408-3.12  PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by ATM 407.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable per Subsection 105-1.11.

408-3.13  MIXING. Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD. Mix to obtain at least 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt binder.

Mix the HMA within the temperature range determined by the JMD.

Upon the Engineer’s request, provide daily burner charts showing start/stop times and temperatures.

408-3.14  TEMPORARY STORAGE OF HMA.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.

Signs of visible segregation, heat loss, changes from the JMD, change in the characteristics of asphalt binder, lumpiness, and stiffness of the mixture, are causes for rejection.

Do not store HMA on barges.

408-3.15  PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, are placed and accepted.

Do not place HMA abutting curb and gutter until curb and gutter are installed, except as approved by the Engineer. Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

When practicable, adjust elevation of metal fixtures before paving the final lift, so they will be between 1/4 and 1/2 inch below the top surface of the final lift.  Metal fixtures include, but are not limited to manholes, valve boxes, monument cases, hand holes, and drains.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

Place HMA over bridge deck membranes according to Section 508 and the membrane manufacturer's recommendations.

Do not mix HMA produced from different plants for testing or paving.

408-3.16  COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers. Prevent indentation in the mat; do not leave rollers or other equipment standing on HMA that has not sufficiently cooled.

The Lower Specification Limit for density is 93.0% of the Maximum Specific Gravity (MSG) as determined by ATM 409.  The MSG from the approved JMD is used for the first lot of each type of HMA.  The MSG for additional lots is determined from the first sublot of each lot.

408-3.17  JOINTS.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the pre-paving meeting.  Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

Form transverse joints by saw-cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints 15 to 25 degrees.

For all joints below the top lift, uniformly coat joint surfaces with tack coat material meeting Section 402.

Uniformly coat the joint face of all top lift joints with a joint adhesive. Follow joint adhesive manufacturer's recommendations for temperatures and application method.  Remove joint adhesive applied to the top of pavement surface.  If infrared joint heaters are used and passing joint densities are achieved in each of the first three joint densities taken, then joint adhesive is not required.

The Lower Specification Limit for top lift longitudinal joint density is 91.0% of the MSG of the panel completing the joint. MSG will be determined according to ATM 409.

For top lift panels that have a longitudinal joint density less than 91.0% of the MSG in a sublot, seal the surface of the longitudinal joints with joint sealant within that sublot or as directed.  Apply joint sealant according to the manufacturer’s recommendations while the HMA is clean, free of moisture and prior to final traffic marking.  Place the sealant at a maximum application rate of 0.15 gallons per square yard, and at least 12 inches wide centered on the longitudinal joint.  After surface sealing, inlay by grinding pavement striping into the sealed HMA. Use grooving equipment that grinds a dry cut to groove the width, length, and thickness of the striping within the specified striping tolerances.

Correct improperly formed joints that result in surface irregularities according to a corrective action plan.

Complete all hot lapped joints while the mat temperature is over 230F as measured by the Engineer, within 3 inches of the joint. Tack coat and joint adhesive are not required for hot lapped joints. Hot lapped joints will receive the full Longitudinal Joint Density Price Adjustment incentive without testing for joint density.

Top lift longitudinal joints will be evaluated for acceptance according to Subsection 408-4.03.

408-3.18  SURFACE REQUIREMENTS AND TOLERANCE.  The finished surface of all HMA paving must match dimensions shown in the contract for horizontal alignment and width, profile grade and elevation, crown slope, and pavement thickness. Water must drain across the pavement surface without ponding. The surface must have a uniform texture, without ridges, puddles, humps, depressions, and roller marks. The surface must not exhibit raveling, cracking, tearing, asphalt bleeding, or aggregate segregation. Leave no foreign material, uncoated aggregate, or oversize aggregate on the HMA surface.

The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  The Engineer will identify pavement areas that deviate more than 3/16 inch from the straightedge, including joints, as defective work. Perform corrective work by removing and replacing, grinding, cold milling or infrared heating such areas as required. Do not surface patch. After the Contractor performs corrective work, the Engineer will retest the area.

The Engineer will use an inertial profiler to measure the top lift HMA surface in the driving lanes for surface smoothness within 21 days after paving is complete and driving lanes are delineated.

Profiler measurements will not be taken in turn lanes, ramps, lane transitions, or within 25 feet of bridge abutments and transverse joints with pre-existing pavement.

The Engineer will measure the pavement smoothness in both wheel paths of each lane.  The smoothness is measured as International Roughness Index (IRI), reported as inches/mile, at 0.1-mile increments.  Pavement smoothness is the average of all IRI measurements for the project.

The Engineer will identify areas requiring corrective action in accordance with Table 408-4.  Perform full-width corrective action in those areas.  The Engineer may waive corrective work for localized roughness for deficiencies resulting from manholes or other similar appurtenances near the wheel path.

Perform Corrective Actions according to one of the following or by a method approved by the Engineer:

1.	Diamond Grinding.  If the required pavement thickness is not decreased by more than 1/4-inch, grind to the required surface tolerance and cross section.  Remove and dispose of all waste materials.  Apply joint sealant and sand to exposed aggregates per the manufacturer’s recommendations.

2.	Overlaying.  Mill or sawcut the existing pavement to provide a vertical transverse joint face to match the overlay to the existing pavement.  Apply tack coat on the milled surface and joint adhesive to all vertical joints and overlay the full width of the underlying pavement surface.  Use the same approved HMA for overlays.  Place a minimum overlay thickness of 2.0 inches.

3.	Mill and Fill. Mill the existing pavement to provide a vertical transverse joint face. Apply tack coat to the milled surface and joint adhesive to all vertical joints prior to inlay new HMA to match the existing pavement.  Use the same approved HMA.  Place a minimum thickness of 2.0 inches.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.

Price adjustments for pavement smoothness will be calculated according to Subsection 408-4.03.3.

408-3.19  REPAIRING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt. Remove and dispose defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat according to Section 402.  Place and compact fresh HMA so that compaction, grade, and smoothness requirements are met.

408-3.20  ROADWAY MAINTENANCE.  Inspect daily according to pavement inspection plan. Remove, and dispose of project materials incorrectly deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The Contractor is responsible for damage caused by not removing these materials and any damage to the roadway from the removal method(s).

Repair damage to the existing roadway that results from fugitive materials or their removal.

408-4.01  METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a.	By weight.  No deduction is made for the weight of asphalt binder or anti stripping additive or cutting back joints.

b.	By the final HMA surface area.

2.	Asphalt Binder.  By weight, as follows:

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment is made for any asphalt binder more than 0.4% above the optimum asphalt binder content specified in the JMD.

Method 1: Percent of asphalt binder for each sublot multiplied by the total HMA weight represented by that sublot.  The Engineer will use either ATM 405 or ATM 406 to determine the percent of asphalt binder.  The same test method used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  In the absence of testing, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2: Supplier's invoices minus waste, diversion, and remnant.  This procedure is an Engineer’s option for projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time that tankers are weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment is based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste HMA is calculated using the target value for asphalt binder as specified in the JMD.

3.	Job Mix Design. When specified, a Contractor furnished JMD is measured as one according to the HMA type.

4.	Temporary Pavement.  Per Section 401.

5.	Leveling Course.  Per Section 401.

6.	HMA Price Adjustment.  Calculated by quality level analysis under Subsection 408-4.03.1.

7.	Longitudinal Joint Density Price Adjustment.  By the linear foot of top lift longitudinal joint under Subsection 408-4.03.2.

8.	Joint Adhesive.  By the linear foot of longitudinal and transverse joint.

9.	Pavement Smoothness Price Adjustment.  Calculated from inertial profiler data using FHWA’s ProVAL software under Subsection 408-4.03.3.

10.	Asphalt Material Price Adjustment.  Determined under Subsection 408-4.04.

11.	Liquid Anti-Strip Additive.  Based on the number of tons of asphalt binder containing required additive.

12.	Crack Repair.  From end to end of the crack repaired according to 408-3.10, measured horizontally along the centerline of the crack.

13.	Prelevel for Ruts, Delaminations, and Depressions.  By the surface area where prelevel is placed according to 408-3.10(1), measured according to Section 109.

14.	Repair Unstable Pavement.  By the surface area of pavement repaired according to 408-3.10(2), measured according to Section 109.

408-4.02 ACCEPTANCE SAMPLING AND TESTING.

1.	Hot Mix Asphalt

The bid quantity of each type of HMA produced and placed is divided into lots and the lots evaluated individually for acceptance.

A lot is normally 5,000 tons. The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 408-4.03.1. Seasonal startup or a new JMD requires starting a new lot.

If less than 8 sublots have been placed at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot. The price adjustment computed for the prior lot will include the samples from the shortened lot. Density test results from material in the shortened lot will be based on the MSG of the first sublot of the shortened lot. If there is no prior lot, and there are at least 3 sublots, the material in the shortened lot will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot. If there are less than 3 sublots, the HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances.

If 8 or 9 sublots have been placed at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot.

If the bid quantity is between 1,500 to 5,000 tons, the quantity is considered one lot.  The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection.

For bid quantity less than 1,500 tons, HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances.

The Engineer reserves the right to perform any testing required in order to determine acceptance.

a.	Asphalt Binder Content. HMA samples shall be taken randomly by the Contractor in the presence of the Engineer from behind the paver screed before initial compaction, or will be taken randomly by the Engineer from the windrow, according to ATM 402 or ATM 403, at the discretion of the Engineer. The location (behind the paver screed or windrow) will be determined at the pre-paving meeting.  The Engineer will determine random sampling locations.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  At the discretion of the Engineer, Asphalt binder content will be determined according to ATM 405 or ATM 406.

b.	Aggregate Gradation. Aggregates tested for gradation acceptance will have the full tolerances from Table 408-2 applied.

(1).	Drum Mix Plants. Samples will be taken from the combined aggregate cold feed conveyor via a diverter device, from the stopped conveyor belt or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for samples from the conveyer system will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.

(2)	Batch Plants. Samples will be taken from dry batched aggregates according to ATM 301 or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested. The aggregate gradation for dry batch samples will be determined according to ATM 304. For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder.

c.	Density. The Engineer will determine and mark the location(s) where the Contractor takes each core sample.

(1)	Mat Cores: The location(s) for taking core samples is determined using a set of random numbers (independent of asphalt binder and aggregate sampling set of random numbers) and the Engineer's judgment. Take no mat cores within 1 foot of a joint or edge. Core samples are not taken on bridge decks.

(2)	Longitudinal Joint Cores: The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.

Take core samples according to ATM 413 in the presence of the Engineer. Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one six-inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  The Engineer will immediately take possession of the samples. Backfill and compact voids left by coring with new HMA within 24 hours, and according to ATM 413. The Engineer will determine density of samples according to ATM 410.

d.	Asphalt binder Content, Aggregate Gradation, and Density - Retest. When test results have failed to meet specifications, retest of acceptance test results for asphalt binder content, gradation, and density may be requested provided the quality control requirements of Subsection 408-3.02 Contractor Quality Control are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2-foot radius of the original core.  The original test results are discarded and the retest result is used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  When gradation and asphalt binder content are determined from the same sample, a request for a retest of either gradation or asphalt binder content results in a retest of both. Both gradation and asphalt binder content retest results are used in the price adjustment calculation. Except for the first lot, retesting for gradation or asphalt binder from the first sublot of a lot will include retesting for the MSG. Retesting will be performed by a Department laboratory.

2.	Asphalt Binder

The bid quantity of asphalt binder produced and placed is divided into lots and the lots evaluated individually for binder grade acceptance.

Testing will be by AASHTO accredited independent laboratories. When retesting is requested, the assigned value (ATV) will be determined using ASTM D3244. Each test will be completed by a different laboratory.

a.	Acceptance Test. The lot size for asphalt binder is 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it is added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it is sampled, tested and evaluated as a separate lot.

If the bid quantity of asphalt binder is between 85 to 200 tons, the quantity is considered as one lot and sampled, tested, and evaluated according to this subsection. Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Sample asphalt binder at the plant from the supply line in the presence of the Engineer according to ATM 401.  The Engineer will take immediate possession of the samples. Take three samples from each lot, one for acceptance testing, one for Contractor requested retesting, and one held in reserve for referee testing if requested.  Meet Subsection 702-2.01 requirements for asphalt binder quality.

b.	Retest. Submit a written request, for a retest, no more than 7 days from receiving notice of the failed acceptance test. In the request, identify the retest laboratory. The Engineer will send the second sample (retest sample) to the laboratory.  Provide the retest results to the Engineer. Contractor pays for the retest costs.

If the average of the combined test results ([acceptance + retest]/2) passes the specification requirement, the average value becomes the ATV. If this ATV fails the specification requirement, the Engineer or Contractor may request the third sample (referee sample) be tested.

c.	Referee Test. The Engineer will send the third sample (referee sample) to an agreed upon laboratory. The average of the combined test results ([acceptance + retest + referee]/3) equals the ATV. If the ATV fails to meet specifications, the Contractor pays for the referee test.

408-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The Engineer may reject material which appears to be defective based on visual inspection.  If a test of rejected material is requested, a minimum of two samples are collected from the rejected material and tested.  If all test results are within specification limits, payment for the material is made.

The following methods are applied to each type of HMA with Price Adjustment Pay Items in the Contract. These methods describe how price adjustments are determined based on the quality of the HMA, binder, longitudinal joint density, and pavement smoothness

1.	HMA Price Adjustment.  Acceptance test results for HMA asphalt binder content, gradation and mat density are used in HMA price adjustment.  These test results for a lot are analyzed collectively and statistically by the Quality Level Analysis (QLA) method as specified in Subsection 106-1.03.3 to determine the total estimated percentage of the lot that is within specification limits. The values for percent passing the #200 sieve, asphalt binder content and density test results are reported to the nearest 0.1 percent.  All other sieves used in QLA are reported to the nearest whole number.

The HMA price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor (CPF) for HMA that includes gradation and asphalt binder content.  The second is the density pay factor (DPF).

A lot containing material with less than a 1.000 pay factor is accepted at an adjusted price, provided that pay factor is at least 0.800 and there are no isolated defects identified by the Engineer. A lot containing material that fails to obtain the minimum pay factor is considered unacceptable and rejected under Subsection 105-1.11.

HMA pay factors are computed as follows:

a.	All statistical Quality Level Analysis (QLA) is computed using the Engineer’s Price Adjustment programs.

b.	The USL and LSL are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 408-2, or as shown below.  The TV is the specification value shown in the approved Job Mix Design.

TABLE 408-2

HMA LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICAITON LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4-inch or largest sieve size | 99 | 100 |
| 1/2-inch sieve or first sieve retaining aggregate | TV-6 | TV+6 |
| 3/8-inch sieve | TV-6 | TV+6 |
| No. 4 sieve | TV-6 | TV+6 |
| No. 8 sieve | TV-6 | TV+6 |
| No. 16 sieve | TV-5 | TV+5 |
| No. 30 sieve | TV-4 | TV+4 |
| No. 50 sieve | TV-4 | TV+4 |
| No. 100 sieve | TV-3 | TV+3 |
| No. 200 sieve* | TV-2.0 | TV+2.0 |
| Asphalt Binder Content, % | TV-0.4 | TV+0.4 |
| Mat Density, % | 93.0 | 100.0 |

*LSL for the No. 200 Sieve is restricted by the broad band limits in Table 703-4.

c.	The percent within limits (PWL), Quality Levels and characteristic pay factors (PFs) are determined by the Engineer for each Lot in accordance with Subsection 106-1.03.3.  The Composite Pay Factor (CPF) for the lot is determined from gradation and asphalt binder content (ac) acceptance test results using the following example formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

Table 408-3 gives the weight factor (f) for each test property considered.

TABLE 408-3

WEIGHT FACTORS

| Property | Type VH Factor “f” |
| --- | --- |
| 3/4-inch sieve | 4 |
| 1/2-inch sieve | 5 |
| 3/8-inch sieve | 5 |
| No. 4 sieve | 4 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No. 30 sieve | 5 |
| No. 50 sieve | 5 |
| No. 100 sieve | 4 |
| No. 200 sieve | 20 |
| Asphalt Content, % | 40 |

The Density Pay Factor (DPF) is computed using HMA mat core compaction acceptance test results.

The CPF and DPF are rounded to the nearest 0.001.  The price adjustment for each individual lot is calculated as follows:

HMA Price Adjustment = [(CPF or DPF)* -1.000] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower

PAB = Price Adjustment Base = $140.00 per ton.

The HMA Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 408.2008.____.

2.	Longitudinal Joint Density Price Adjustment. Longitudinal joint density price adjustment will be based on the project average of all top lift cold joint densities and determined as follows:

a.	Disincentive. Project average top lift joint density less than 91.0% MSG:

Deduct $3.00 per lineal foot.

b.	Incentive. Project average top lift joint density greater than:

92.0% MSG.		Add $0.50 per lineal foot

93.0% MSG.		Add $1.00 per lineal foot

94.0% MSG.		Add $1.50 per lineal foot

The longitudinal Joint Density Price Adjustment is the total price adjustment paid for under Item 408.2009.____.

3.	Pavement Smoothness Price Adjustment.  Pavement smoothness will be measured by the Engineer and reported as IRI (inches/mile), according to Subsection 408-3.18.  Incentive for pavement smoothness shall apply only if both the project average CPF and DPF are greater than or equal to 1.000.  Disincentive for pavement smoothness shall apply regardless of the project average CPF or DPF.

The Engineer will calculate the pavement smoothness price adjustment according to Method 1 (pavement placed over graded subgrade) and/or Method 2 (pavement placed over existing pavement). The SF is rounded to the nearest 0.001.

Method 1: SPA = PAB x PQ x SF,

Where:

SPA = Pavement Smoothness Price Adjustment

PAB = Price Adjustment Base = $140.00 per ton

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor (Table 408-4)

TABLE 408-4

SMOOTHNESS FACTOR (SF)

| IRI (in./mile) | SF |
| --- | --- |
| Less than 40.0 | 0.050 |
| 40.0 to 70.0 | 0.050 – (IRI – 40.0)/600.0 |
| 70.0 to 90.0 | 0.000 |
| 90.0 to 120.0 | (90.0 – IRI)/120.0 |
| Greater than 120.0* | - |

* Corrective Work required, see Subsection 408-3.18

Method 2: SPA = PAB x PQ x SF,

Where:

SPA = Pavement Smoothness Price Adjustment

PAB = Price Adjustment Base = $140.00 per ton

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor = 0.120 x RR – 0.020; SF not to exceed 0.050

RR = Roughness Reduction = (Initial IRI – Final IRI) / Initial IRI

Initial IRI = 	Pre-project average IRI as measured and reported by the Engineer.  The Initial IRI will either be included in the bid documents or the timeline for when the Initial IRI will be measured will be identified in the bid documents.

Final IRI =	Top layer HMA average IRI as measured and reported by the Engineer according to Subsection 408-3.18.

The Pavement Smoothness Price Adjustment is the total price adjustment paid for under Item 408.2010.____.

4.	Asphalt Binder Price Adjustment. A lot quantity of asphalt binder, with a pay factor less than 1.00, is accepted or rejected per Table 408-3.01-1 Asphalt Binder Pay Factors.

TABLE 408-4.03-1

ASPHALT BINDER PAY FACTORS

| Pay Factor |  |  | 1.01 | 1.00 | 0.95 | 0.90 | 0.75 | Reject |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RTFO (Rolling Thin Film Oven) |  |  |  |  |  |  |  |  |
| DSR(a.1) | All Grades | G*/Sinδ, kPa-1 | ≥ 2.69 | 2.68–2.20 | 2.19–1.96 | 1.95–1.43 | 1.42–1.10 | < 1.10 |
| MSCR(a.2) | PG 52-40 E | JNR 3.2 |  0.39 | 0.40–0.50 | 0.51–0.59 | 0.60–0.69 | 0.70–1.00 | > 1.00 |
|  |  | % Rec3.2 | ≥ 86.0 | 85.9–75.0 | 74.9–68.0 | 67.9–60.0 | 59.9–55.0 | < 55.0 |
|  | PG 58-34 E | JNR 3.2 |  0.19 | 0.20–0.25 | 0.26–0.29 | 0.30–0.39 | 0.40–0.50 | > 0.50 |
|  |  | % Rec3.2 | ≥ 90.0 | 89.9–85.0 | 84.9–80.0 | 79.9–75.0 | 74.9–70.0 | < 70.0 |
|  | PG 64-40 E | JNR 3.2 | < 0.05 | 0.05–0.10 | 0.11–0.15 | 0.16–0.20 | 0.21–0.25 | > 0.25 |
|  |  | % Rec3.2 | ≥ 97.0 | 96.9–95.0 | 94.9–91.0 | 90.9–85.0 | 84.9 – 80.0 | < 80.0 |
| PAV (Pressurized Aging Vessel) |  |  |  |  |  |  |  |  |
| DS(a.3) | PG 64-40 E & All Other Grades | G*Sinδ, kPa | < 4711 | 4712–5000 | 5001–5289 | 5290–5578 | 5579–5867 | > 5867 |
|  | PG 52-40 E, PG 58-34 E | G*Sinδ, kPa | < 5700 | 5701–6000 | 6001–6300 | 6301–6600 | 6601 – 7000 | > 7000 |
| CS(a.4 & 5) | All Grades(a.4) | BBR, S, MPa | < 247 | 248–300 | 301–338 | 339–388 | 389–449 | > 450 |
|  | All Grades(a.5) | BBR, m | > 0.320 | 0.319–0.300 | 0.299–0.294 | 0.293–0.278 | 0.277–0.261 | < 0.261 |

Creep Stiffness (CS)	Dynamic Shear (DS)	Multiple Stress Creep Recovery (MSCR

a.	Asphalt Binder Pay Adjustment = (Lowest Pay Factor – 1.00) x (tons in lot) x PAB x 5

Select the lowest pay factor from:

RTFO (test the binder residue at the performance grade temperature)

(1)	DS, All Grades, G*/Sinδ, kPa-1

(2)	MSCR: PG, Select the highest pay factor corresponding to, either JNR 3.2 or % Rec3.2 values

PAV

(3)	DS, PG, G*Sinδ, kPa

(4)	CS, All Grades, BBR, S MPa

(5)	CS, All Grades, BBR, m

b.	If three consecutive acceptance samples are out of specification, stop HMA production immediately and submit a corrective action plan to the Engineer for approval.

The Asphalt Binder Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 408.2021.____.

408-4.04  ASPHALT MATERIAL PRICE ADJUSTMENT.

Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Subsection 702-2.01 Asphalt Binder, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP =	Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

408-5.01  BASIS OF PAYMENT.

The following items, unless included as individual Pay Items, are subsidiary to the Section 408 Hot Mix Asphalt Pavement related Pay Items as included in the bid schedule:

	Asphalt binder

	Liquid anti-strip additives

	Tack coat

	Crack sealing

	Crack repair

	Joint adhesive

	Surface sealing of longitudinal joints

	Surface tolerance corrections

	Patching defective areas

	Prelevel for ruts, delaminations, and depressions

	Repair unstable pavement

	Job mix design

	Density profiles, Subsection 408-2.10 Process Quality Control

	Repair work and materials when planing equipment breaks through existing pavement – Subsection 408-3.10 Preparation of Existing Surface

	Work and materials associated with Subsection 408-3.06 Hauling Equipment

	Work and materials associated with Subsection 408-3.20 Roadway Maintenance

Test Strips:  Subsection 408-2.10 Process Quality Control.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices for HMA and asphalt binder as included in the Bid Schedule.  Price adjustments 408.2008.____, 408.2009.____, 408.2010.____ and 408.2021.____ do not apply.

b.	Failed.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

The following price adjustment Pay Items, unless included as individual Pay Items in the bid schedule, are paid under 408.2022.____ Combined Price Adjustment.

408.2008.____ HMA Price Adjustment, Type     ,

408.2009.____ Longitudinal Joint Density Price Adjustment,

408.2010.____ Pavement Smoothness Price Adjustment, Method    .

408.2021.____ Asphalt Binder Price Adjustment

Item 408.2008.____ HMA Price Adjustment, Type    , is the sum of the price adjustments for each material lot, and for deductions and fees assessed.  Deductions and fees assessed include:

	Each mix design subsequent to the approved JMD for each type and class of HMA specified will result in a fee of $6000.

	Failure to cut core samples within the specified period will result in a deduction of $100 per sample per day.

	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day.

	If an asphalt binder referee test is requested and the ATV confirms the asphalt binder does not meet Contract requirements, a fee of $500 will be assessed.

Item 408.2008.____ HMA Price Adjustment, Type    , and 408.2022.____ Combined Price Adjustment do not apply to the following:

	Driveway and approach HMA.

	HMA contract quantity is less than 1500 tons.

Item 408.2015.____ Asphalt Material Price Adjustment.

For each Section as included in Subsection 408-4.04 Asphalt Material Price Adjustment, item 1.a, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment", is not included, for any section, no payment will be made.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 408.2001.____ | HMA, Type . | Ton |
| 408.2004.____ | Asphalt Binder, Grade PG ##-## X | Ton |
| 408.2007.____ | Liquid Anti-Strip Additives | CS |
| 408.2014.____ | Joint Adhesive | LF |
| 408.2015.____ | Asphalt Material Price Adjustment | CS |
| 408.2020.____ | HMA, Fiber Reinforced, Type VF | Ton |
| 408.2022.____ | Combined Price Adjustment | CS |

CR408-010122

DIVISION 500 — STRUCTURES

Blank Page

SECTION 501
CONCRETE FOR STRUCTURES

Standard Modification

501-2.02 COMPOSITION OF MIXTURE – JOB MIX DESIGN.

Replace Table 501-4 with the following:

TABLE 501-4

AIR CONTENT REQUIREMENTS

| Class of Concrete | Air Content |
| --- | --- |
| A | 6.0% 0.5% |
| A-A | 6.0% 0.5% |
| P | 3.50% minimum1 and Super Air Meter (SAM) number 0.201 |
| DS | Not required |

1Not required for web and bottom flange of precast, prestressed decked bulb-tee girders.

HSM20.23-123121

Special Provisions

501-3.13 PRECAST CONCRETE MEMBERS.

Add the following to Paragraph 4. Erection:

After all slabs have been placed, and after receiving approval from the Engineer, saw cut lifting devices and grind flush and smooth to the top of slab.

501-5.01 BASIS OF PAYMENT.

Add the following after Paragraph 2:

Payment for rebar in the coping and cast in place wall panels is subsidiary.

CFHWY00599

SECTION 503
REINFORCING STEEL

Special Provisions

503-3.02 PROTECTION OF MATERIALS.

Replace the 2nd sentence of the 1st paragraph with the following:

Before placing reinforcing steel in the work, ensure that the reinforcing steel is free of salt, rust, and foreign substances that may affect the performance of the reinforcing steel.

503-3.05 SPLICING.

Replace “c. Testing/Inspection” under Item 2. Electric Resistance Butt Welded Joints with the following:

c. 	Testing/Inspection.

Perform job control tests using a testing laboratory with experience with ASTM A370 and California Test Method 670. A job control test consists of the fabrication, under the same conditions used to produce the splice, and the physical testing of 4 sample splices for each lot of splices. An authorized Department representative will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of shop produced resistance welded butt joints is defined as no more than 150 splices of the same type of welds used for each combination of bar size and bar deformation pattern that is used in the work.

The Engineer or the Engineer's authorized representative shall witness the job control tests performed by the testing laboratory. Give the Engineer at least 7 working days’ notice before beginning control tests.

Identify sample splices with tamper proof and weatherproof markings prior to shipment to the testing laboratory.

The sample shall consist of a resistance welded butt splice bar and a control bar that are identified and marked as a set. The same reinforcing bar (hoop) may be used to provide the test weld and control bar.

Test each sample to failure in accordance with ASTM A706, ASTM A370 and California Test Method 670. Determine the ultimate tensile strength for all control bars by testing the bars to failure.

The production lot will be rejected if:

- a sample fails within one bar diameter of the splice at less than 95 percent of the ultimate tensile strength of the associated control bar

- necking of the bar prior to rupture, as defined in California Test Method 670, is not observed

- a sample does not meet the mechanical requirements of ASTM A706 Grade 60

Replace “c. Qualifications and Submittals.” and “d. Testing/Inspection.” under Item 4. Mechanical Butt Splices with the following:

c.	Qualifications and Submittals. A splice will be considered qualified if the splice can develop a minimum tensile strength of 80000 psi, based on the nominal bar area, and the bars within the splice do not exceed a total slip shown in Table 503-3, when tested according to the relevant material ASTM, ASTM A370 and California Test Method 670.

TABLE 503-3
ALLOWABLE TOTAL SLIP LENGTH

| Reinforcing Bar No. | Total Slip (inch) |
| --- | --- |
| 4 | 0.020 |
| 5 | 0.020 |
| 6 | 0.020 |
| 7 | 0.028 |
| 8 | 0.028 |
| 9 | 0.028 |
| 10 | 0.036 |
| 11 | 0.036 |
| 14 | 0.048 |
| 18 | 0.060 |

Submit the following information:

    - the manufacturer's name;

    - the name of the product or assembly;

    - the lot, heat, or batch number that identifies the splice;

    - the bar grade and size number to be spliced by the material;

    - a complete description of the splice and installation procedure; and,

    - Tensile Test results including:

      - bar nominal area;

      - ultimate load at failure;

      - ultimate tensile strength;

      - necking results (either visually or through strain values); and,

      - failure mechanism and location.

(7)	Slip Test results including:

      - initial length measurements;

      - final length measurements; and,

      - calculated slip.

  - Testing/Inspection. Perform job control tests consisting of the fabrication, under conditions used to produce the splice. For each lot of splices perform 6 slip tests and 6 tensile tests using different sample splices for each test. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical butt joints is defined as no more than 150 splices of the same type of mechanical butt splice used for each combination of bar size and bar deformation pattern that is used in the work.

Make splice samples using the same splice materials, position, equipment, and following the same procedures as used to make splices in the work. Make splice samples at least 5 feet long with the splice at mid-length. Shorter sample splice bars may be used if approved by the Engineer.

Perform job control tests in the presence of the Engineer. Splices tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 7 working days prior to performing testing.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample according to the relevant material ASTM, ASTM A370 and California Test Method 670. Perform tensile testing until partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection.

The production lot will be rejected if:

- the minimum individual tensile strength of the sampled splices is less than 80000 psi based on the nominal bar area

- the maximum individual slip length of the sampled splices is greater than the limits in Table 503-3

Replace “b. Qualifications” and “c. Testing/Inspection.” under Item 5. Mechanical Lap Splices. with the following:

- Qualifications. A splice will be considered qualified if the splice can develop a minimum tensile strength of 75000 psi, based on the nominal bar area, when tested according to the relevant material ASTM, ASTM A370 and California Test Method 670.

Submit the following information:

    - the manufacturer's name;

    - the name of the product or assembly;

    - the lot, heat, or batch number that identifies the splice;

    - the bar grade and size number to be spliced by the material;

    - a complete description of the splice and installation procedure; and,

    - test results indicating the splice, used according to the manufacturer's procedures, complies with the minimum tensile strength requirements.

  - Testing/Inspection. Perform job control tests consisting of the fabrication, under conditions used to produce the splice, and tensile testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical butt joints is defined as no more than 150 splices of the same type of mechanical butt splice used for each combination of bar size and bar deformation pattern that is used in the work.

Make splice samples using the same splice materials, position, equipment, and following the same procedures as used to make splices in the work. Make splice samples at least 5 feet long with the splice at mid-length. Shorter sample splice bars may be used if approved by the Engineer.

Perform job control tests in the presence of the Engineer. Splices tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 7 working days prior to performing testing.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample according to the relevant material ASTM, ASTM A370 and California Test Method 670. Tensile test each sample until partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection.

All splices in the lot represented by a test will be considered to meet the tensile strength requirements when the minimum individual tensile strength of the sampled splices is not less than 75000 psi, based on the nominal bar area.

503-5.01 BASIS OF PAYMENT.

Add the following before Paragraph 1:

Payment for rebar in the coping and cast in place wall panels is subsidiary.

CFHWY00599

SECTION 504
STEEL STRUCTURES

Special Provision

504-3.01 FABRICATION.

2. General

Replace the 10th paragraph and subparagraphs after “Cold bend load-carrying rolled-steel plates as follows” with the following:

Cold bend at room temperature cross-frame or diaphragm connection plates up to 0.75 inches thick with minimum bending radii of 1.5 times the plate thickness in inches. Cold bend all other steel plates and bars with minimum bend radii of 5 times the plate thickness in inches measured to the concave face of the plate.

Before bending, round the edges of the plate to a radius of 1/16 inch throughout the portion of the plate to be bent.

Orient bend lines perpendicular to the direction of final rolling of the plate.  Obtain approval from the Engineer before orienting bend lines parallel to the direction of final rolling and increase the minimum bend radii to 7.5 times the plate thickness in inches.

CFHWY00599

SECTION 505
PILING

Special Provisions

505-1.01 DESCRIPTION. Remove and replace with the following:

Furnish piles, steel plates, and appurtenances, drive piles, and assist in high strain dynamic pile testing.

505-1.02 DEFINITIONS. Add the following:

PILE PILOT BORE. A vertical boring drilled along the pile alignment to a prescribed depth and size, prior to driving the pile, intended to loosen or weaken hard soil conditions, and reduce risk of pile damage during driving. A pile pilot bore hole does not necessarily have to be void of the cuttings.

505-2.01 MATERIALS. Add the following:

Structural Steel			Section 716

505-3.01 PILE DRIVING EQUIPMENT. Add the following:

- Pile Pilot Bore Equipment. Pile pilot bore holes may be drilled using auger, rotary-wash with casing, downhole hammers, cable-tools, and/or other appropriate equipment. Use only equipment included in the approved pile driving plan. The Engineer will inspect the pile pilot bore equipment for conformance with the approved pile driving plan after it has been mobilized to the site and prior to beginning pile operations. Remove and replace pile pilot bore equipment found out of conformance with the approved pile driving plan at no extra cost to the Department and with no adjustment to contract time.

505-3.03 DRIVING PILES.

Add the following:

5.	Pile Pilot Bore. Drill a pile pilot bore hole, prior to driving, at each pile location to one foot above the Minimum Penetration shown on the Plans. The diameter of the pile pilot bore hole will be sufficient diameter to install piles to minimum penetration, but no larger than 21 inches.

6.	Piles for Lighting Standards. For lighting standards, install piles of sufficient length to cut the pile at the required cut-off elevation and to provide the minimum installed length shown on the Plans.

For installations of highway lighting piles, the Wave Equation Analysis is not required.

Sites for lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

When the minimum pile length, shown on the Plans, for a lighting standard foundation cannot be achieved, install the pile tip to an elevation established by the Engineer.

505-5.01 BASIS OF PAYMENT.

Replace the 1st paragraph with the following:

Furnish Piles.  The contract price includes pile materials delivered to the site, pile shoes, reinforced tips, casing, steel plates welded to the piles, and appurtenances. Unused pile lengths removed by cut-offs and fresh heading are subsidiary. The payment amount will be calculated using the quantity of pile indicated on the bid schedule, or the measured quantity of installed piles, whichever is greater.

Add the following numbered item to Drive Piles:

- All equipment, material, labor and work required for pilot bore holes for the piles.

CFHWY00599

SECTION 508
WATERPROOFING MEMBRANE

Special Provisions

508-1.01 DESCRIPTION.

Add the following:

The spray-applied waterproofing membrane system consists of: a primer, a membrane and a tack coat.

508-3.01 CONSTRUCTION.

1. General.

Replace the first paragraph with the following:

Install the waterproofing membrane system in accordance with the manufacturer’s installation procedure and the approved submittal. Use the primer and tack coat listed in the approved submittal. Do not apply primers or membranes until the end of the curing period and until concrete and grout has reached at least 80 percent of the specified 28-day compressive strength (f’c). Apply the membrane system vertically at curb faces up to the pavement thickness shown on the Plans. Protect adjacent surfaces not to be covered with the membrane from splatter or coating. Use pavement overlay material within the membrane manufacturer’s temperature limitations.

2. Deck Preparation.

Replace the first paragraph with the following:

Remove existing pavement and membrane systems by methods that do not damage the concrete deck. Do not use a mechanical milling machine such as a reclaimer or planer. Meet the requirements of Subsection 105-1.12. Prepare the concrete surfaces that are to receive the waterproofing membrane system as required by the manufacturer.

508-3.02 QUALITY CONTROL.

2. Spray-Applied Waterproofing Membrane.

Replace the first paragraph with the following:

Perform tensile adhesion bond testing of the waterproofing membrane system, at locations determined by the engineer, in accordance with ASTM D7234 at least once every 2000 square feet of coated area.

508-3.03 ACCEPTANCE TESTING.

1. Flood Testing.

Replace the first paragraph with the following:

Perform flood testing of spray-applied waterproofing membrane prior to placement of tack coat or asphalt. With the written approval of the manufacturer’s on-site representative, perform flood testing of sheet waterproofing membrane prior to asphalt overlay, otherwise perform flood testing after asphalt overlay.

508-3.04 MEMBRANE REPAIRS.

3. Sheet Waterproofing Membrane.

Replace the first paragraph with the following:

If flood test acceptance testing is used after placement of asphalt and breaches in the membrane system are found, repairs may be attempted with the written approval of the manufacturer’s on-site representative. Patch areas where asphalt overlay is removed to the satisfaction of the Engineer.

CFHWY00599

Special Provision

SECTION 550
COMMERCIAL CONCRETE

Replace Subsection 550-1.01 with the following:

550-1.01 description. Furnish, place, finish, and cure Portland cement concrete for minor structures and incidental construction.

CR550.1-060121

550-2.02 COMPOSITION OF MIXTURE – JOB MIX DESIGN.

1.   Submittals:

Add the following to the first paragraph:

Submit the JMD on Form 25D-203.

CR550.1-123121

Add the following Subsection 550-2.03 Precast Concrete Products:

550-2.03 PRECAST CONCRETE PRODUCTS. Provide precast concrete products from an ATM 520 certified plant. Submit certification for each product.

Minor and Incidental Structure Products

1.	Curb and gutter

2.	Manhole sections

3.	Headwall

4.	Modular retaining wall units

5.	Noise wall panels and posts

6.	Portable barriers

7.	Utility structures

a.	Cabinet base

(1)	Load center base/foundation

(2)	Controller base/foundation

b.	Junction box

c.	Similar structures

8.	Water and waste water structures

a.	Catch basin

b.	Inlet box

c.	Outlet box

d.	Similar structures

Major Structure Products	Section 501 Concrete for Structures

Major structure products include box culvert, mechanically stabilized earth, retaining walls, three-sided flat-topped culvert, three-sided arch culvert, and similar structures.

CR550.1-060121

Blank Page

DIVISION 600 — MISCELLANEOUS
CONSTRUCTION

Blank Page

Special Provision

Replace Section 603 with the following:

SECTION 603
CULVERTS AND STORM DRAINS

603-1.01 DESCRIPTION.  Construct or reconstruct culvert and storm drain pipe. Install culvert marker posts, and strap plastic culvert ends.

603-1.02 REFERENCES.

ASTM D3953	Standard Specification for Strapping, Flat Steel and Seals

ASTM D4675	Standard Guide for Selection and Use of Flat Strapping Materials

603-2.01 MATERIALS. Use materials that conform to the following:

Bedding and Backfill	Subsection 204-2.01

Joint Mortar	Subsection 705-2.04

Flexible Watertight Gaskets	Subsection 705-2.05

Non-reinforced Concrete Pipe	Subsection 706-2.01

Reinforced Concrete Pipe	Subsection 706-2.02

Corrugated High Density Polyethylene (HDPE) Pipe	Subsection 706-2.07

Corrugated Steel Pipe and Pipe Arches	Subsection 707-2.01

Corrugated Aluminum Pipe	Subsection 707-2.03

Galvanize	Subsection 716-2.07

Culvert Marker Posts (Flexible Delineator Posts)	Subsection 730-2.05

Item 603.0017.____, Pipe, listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP), Corrugated Aluminum Pipe, Reinforced Concrete Pipe, or Corrugated Dual Wall HDPE (plastic) Pipe. Select pipe for each installation that meets or exceeds the requirements shown on the Plans for height of cover.

For steel and plastic pipe, match the end section material to the pipe material.

Separate dissimilar materials with an electrical insulating material.  The insulating material must be at least 1/16 inch thick and approved by the Engineer.

Culvert marker post is 6-foot tall by 2.5 inches wide with reinforcing ribs, capable of a 9-inch minimum bending radius, and blue with no marking.

Culvert marker Strap and Seals according to ASTM D3953. .625 inch x .02 inch, dry Type 1 regular-duty (magnetic, ferritic), galvanized Finish B (hot-dipped Grade 2 moderate coating, .18 oz./ft2 surface or .0002 inch thick minimum. Push type seals, Style III (overlap), regular duty, galvanized Finish B (hot-dipped coating) by 1.75-inch minimum length and matched to strapping width.

CONSTRUCTION REQUIREMENTS

603-3.01. GENERAL. Excavate, bed, and backfill according to the requirements of Subsections 204-2.01 and 204-3.01, and the Plans.

Dewater ground water from work areas; construct and maintain temporary water diversion when working in waterways, and for facilities or structures with active drainage according to Section 204.

603-3.02. LAYING PIPE. Begin the pipe laying at the downstream end of the pipe. Keep the lower segment of the pipe in contact with the bedding throughout its full length. Place bell or groove ends of rigid pipe and outside circumferential laps of flexible pipe facing upstream.

Lay paved or partially lined pipe so that the longitudinal centerline of the paved segment coincides with the flow line. Install elliptical conduit and circular conduit reinforced with other than a full circular cage or cages so the orientation of a vertical plane through the longitudinal axis of the conduit does not vary more than 5 degrees from the design orientation.

Repair damaged metallic coating on metal pipe according to AASHTO M36.

603-3.03 JOINING PIPE. Joints shall provide circumferential and longitudinal strength to preserve the pipe alignment, prevent separation of pipe sections, and provide a watertight joint between new sections of pipe and joints between new and existing sections of pipe of similar and dissimilar materials. Include a continuous gasket (seal) in all joints. Construct the watertight joint capable of passing a laboratory hydrostatic pressure and vacuum test of at least 4 psi for 10 minutes.

1.	Rigid Pipe. Use either bell and spigot or tongue and groove joints. Join pipe sections with the ends fully entered and the inner surfaces reasonably flush and even.

Use one or more of the following joint materials, or any other if approved:

a.	Portland cement mortar

b.	Portland cement grout

c.	Rubber gaskets

d.	Coupling bands

e.	Preformed plastic sealing compound

Make mortar joints using an excess of mortar to form a bead around the outside of the pipe.

For grouted joints, use molds or runners to retain the poured grout. Install rubber ring gaskets to form a flexible, watertight seal.

When using portland cement mixtures, protect the completed joints against rapid drying using suitable covering material.

2.	Metal Pipe. Join the metal pipe firmly using connecting bands conforming to ASTM B745 (Corrugated Aluminum Pipe) and ASTM A760 (Corrugated Steel Pipe) and as noted herein. Use bands that are no more than two nominal sheet thicknesses lighter than the pipe jointed, and in no case more than 0.052 inches lighter. Include a gasket each side of the gap.

a.	Primary Band. Furnish and install corrugated bands so that the band corrugations match and conform to the corrugations of the pipe. Conform to the following guidelines:

(1)	The gap between the pipes joined is in the center of the band and is no wider than one corrugation width.

(2)	Band for 12-inch through 30-inch diameter pipe are at least 12 inches wide.

(3)	Bands for pipe with diameters greater than 30 inches are at least 22 inches wide.

b.	Secondary Band. Use this band only where it is not physically possible to use primary bands, such as on field-cut pipe ends, joining new pipe to existing pipe, etc. Furnish and install deformed metal sheet bands (dimple bands) so that the projections match and are the same depth as the pipe corrugations. Form these projections in circumferential rows with one projection for each corrugation of the helical pipe.

Conform to the following guidelines:

(1)	The gap between the pipes joined is in the center of the band and is no wider than 2 inches.

(2)	Bands for 12-inch diameter pipe are at least 12 inches wide and have one circumferential row of projections for each pipe end joined.

(3)	Bands for pipe with diameters greater than 12 inches are at least 24 inches wide and have two circumferential rows of projections for each pipe end joined.

3.	Plastic Pipe. Use push-on or mechanical joints. Ensure that the plastic pipe couplings' corrugation matches the pipe corrugation and that their width is not less than one-half the nominal pipe diameter.

Furnish all bolted connections on coupling bands with cut washers placed between the nut and the angle bracket or use nuts with integral washers.

Take up any pipe that is out of alignment, unduly settled, or damaged and re-lay or replace it.

603-3.04 CULVERT MARKER.

a.	Marker Post. Install a culvert marker on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed. Drive to maintain forty-two inches of post above the ground after driving, and

b.	Marker Strap. In addition to marker posts, install marker strap around the plastic pipe ends.

Position the strap in the valley of the first annular ring from the top end of the culvert. From the vertical centerline of the culvert, at the top, overlap the strap and extend the ends to approximately 30 degrees each side of the centerline. Place the strap loosely without twists in the valley, without compressing the pipe, and tight enough to keep the strap from moving out of the valley without deforming the pipe or pipe corrugation. Seal the strap at three locations, one at each of the ends, and one at the top of the culvert. Extend the strap ends beyond the end seals approximately 1/2-inch. Double crimp the seal, two pairs of crimps minimum each seal.

Repair the strap galvanizing where abraded and at cut ends according to ASTM A780. Prepare the surface with power tools per SSPC-SP11, hand tools per SSPC-SP2, and as required by the paint manufacturer. Apply paint, Type – paint containing zinc dust, to the prepared surfaces and allow enough time for curing as required by the manufacturer's printed instructions.

603-4.01 METHOD OF MEASUREMENT. Section 109, and as follows:

1.	Culvert Pipe. The length of pipe, measured in place, along the invert.

2.	Pipes for Storm Drains. The length of pipe, measured in place, along the invert, from center to center of structures. The length through the inlets, catch basins, and manholes is included in the measured length.

603-5.01 BASIS OF PAYMENT. Branch connections and elbows are subsidiary to the pipe unless included as a separate Pay Item.

Coupling bands, seals (gaskets), and other items necessary for the proper joining of the sections are subsidiary.

Culvert markers are subsidiary to the pipe.

Excavation, bedding, and backfill paid under Section 204.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 603.0001.____ | CSP ___ Inch | LF |
| 603.0002.____ | ___ Inch CSP Arch | LF |
| 603.0003.____ | End Section for CSP ___ Inch | Each |
| 603.0004.____ | End Section for ___ Inch CSP Arch | Each |
| 603.0009.____ | Corrugated Aluminum Pipe ___ Inch | LF |
| 603.0010.____ | ___ Inch Corrugated Aluminum Pipe Arch | LF |
| 603.0011.____ | End Section for Corrugated Aluminum Pipe ___ Inch | Each |
| 603.0012.____ | End Section for ___ Inch Corrugated Aluminum Pipe Arch | Each |
| 603.0013.____ | Reinforced Concrete Pipe, ___ Inch, Class ___ | LF |
| 603.0014.____ | Reinforced Concrete End Section, ___ Inch | Each |
| 603.0015.____ | Elbow, (Type & Size) | Each |
| 603.0016.____ | Branch Connection (Type & Size) | Each |
| 603.0017.____ | Pipe ___ Inch | LF |
| 603.0019.____ | ___ Inch Pipe Arch | LF |
| 603.0020.____ | End Section for Pipe ___ Inch | Each |
| 603.2032.____ | Corrugated HDPE Pipe ___ | LF |
| 603.2033.____ | End Section for Corrugated HDPE Pipe ___ | Each |

CR603-061520

SECTION 604
MANHOLES AND INLETS

Special Provisions

604-1.01 DESCRIPTION.

Add the following:

For the purpose of this Section, "Utility" is the City of Wasilla, Department of Public Works.

Sanitary Sewer and Storm Drain Facilities – Condition Inspections and Item Replacement

Sanitary Sewer Facilities:

Coordinate with the Engineer and Utility; and participate in a pre-construction condition inspection, and a post-construction condition inspection of the sanitary sewer facilities.

Storm Drain Facilities:

Coordinate with the Engineer and participate in a pre-construction condition inspection of the storm drain facilities.

The pre-construction inspections may identify additional items, manhole metal frames, covers, lids, catch basin inlets and grates, to be repaired and or replaced.  Make repairs and or replace additional facility items as directed by the Engineer.

CR604.1-061520R

604-2.01 MATERIALS.

Replace "Precast Concrete Manhole Sections           Subsection 712-2.05" with the following:

Precast Concrete Products	Subsection 550-2.03, 712-2.05

CR604.2-060121

604-3.01 CONSTRUCTION REQUIREMENTS.

Add the following:

Dewater ground water from work areas; construct and maintain temporary water diversion when working in waterways, and for facilities or structures with active drainage according to Section 204.

Sanitary Sewer and Storm Drain Facilities – Condition Inspections and Item Replacement

Contractor furnishes the required traffic control, including personnel to assist, while performing inspections.

The Contractor forfeits all right to assert pre-existing damage if the Contractor fails to participate in the inspections.

Make repairs and install the replacement facility items as shown in the Plans.

CR604.1-061520R/CFHWY00599

Add the following:

Sanitary Sewer Facilities:

Contact the Utility to determine where to send the written notice, (907) 373-9010.

Provide the Engineer a copy of all written notices sent to the Utility.

During inspections the Utility, the Engineer and the Contractor will observe and document each facility's location and condition.  The Engineer will indicate the additional facility items to be replaced.

Provide three (3) days advance written notice to the Utility and Engineer scheduling a pre-construction condition inspection of the sanitary sewer facilities.  This inspection shall be scheduled and completed prior to commencement of any ground-disturbing construction activities for the project.

Contractor shall furnish all sanitary sewer manhole grade rings, frames, and covers required for the Work.

Salvage the replaced manhole frames and covers.  Coordinate with, and deliver to the Utility the salvaged materials.

Provide three (3) days advance written notice to the Utility and Engineer scheduling a post-construction condition inspection of the facilities, after paving operations are complete.

CFHWY00599

Add the following:

Storm Drain Facilities:

Contact the Engineer, a minimum of 15 days in advance, to schedule a pre-construction inspection of the storm drain facilities.  Conduct this inspection before pavement removal begins.

During inspections, the Engineer and Contractor will observe and document each facility's location and condition.  The Engineer will indicate the additional facility items to be replaced.

Contractor furnishes the storm drain manhole frames and lids; and catch basin inlets and grates.

Storm drain materials and sanitary sewer materials not wanted by the Utility are the property of the Contractor.  Dispose of construction and demolition materials according to Subsection 202-3.06.

CR604.1-061520R

604-5.01 BASIS OF PAYMENT.

Add the following:

Pay Items 604.0012.____, Item 604.0014.____, and Item 604.0015.____ include full compensation for labor, equipment, and incidental materials for installation, complete-in-place after final paving as accepted by the Engineer, including but not limited to:

	inspections

	removal and disposal of existing manhole metal frame and cover/lid; and catch basin inlets and grates

	repairs and installing the replacement materials

	adjusting the facility item down prior to the planing operations

	adjusting the facility item up prior to the paving operations

CR604.1-061520R

Repairs to facilities damaged or rendered inoperable, after the pre-construction condition inspection and before the post-construction condition inspection, are the responsibility of the Contractor and no additional payment will be made.

All traffic control required for the inspections will be paid under the 643 Pay Items.

Except as being paid under Pay Item 604.0012.____, 604.0014.____, and 604.0015.____, existing manholes being adjusted by raising or lowering the frame or ring casting 12" or less – comply with Subsection 604-3.01, paragraph beginning, "adjust existing manhole …" The corresponding Pay Item for this adjustment is 604.0004.____ Adjust Existing Manhole.

CFHWY00599

SECTION 605
UNDERDRAINS

Special Provisions

Replace Subsection 605-2.01 with the following:

605-2.01 MATERIALS. Use materials that conform to the following:

Porous Backfill Material	Subsection 703-2.10

Flexible Watertight Gaskets	Subsection 705-2.05

Perforated Concrete Pipe	Subsection 706-2.03

Corrugated High Density Polyethylene (HDPE) Pipe	Subsection 706-2.07

Corrugated Steel Pipe	Subsection 707-2.01

Corrugated Aluminum Pipe	Subsection 707-2.03

Gray Iron Casting	Subsection 719-2.02

Marker Post	Subsection 730-2.05

Replace Subsection 605-3.01 with the following:

605-3.01 PIPE INSTALLATION. Excavate, bed, and backfill according to the requirements of Subsection 204-2.01 and 204-3.01.

Dewater ground water from work areas; construct and maintain temporary water diversion when working in waterways, and for facilities or structures with active drainage according to Section 204.

Provide pipe with Class 2 perforations where designated in the plans or as directed by the Engineer.

Joints shall provide circumferential and longitudinal strength to preserve the pipe alignment, prevent separation of pipe sections, and provide a watertight joint between new sections of pipe and joints between new and existing sections of pipe of similar and dissimilar materials. Include a continuous gasket (seal) in all joints. Construct the watertight joint capable of passing a laboratory hydrostatic pressure and vacuum test of at least 4 psi for 10 minutes.

Use corrugated tees and elbows as specified in the plans. Use push-on, screw-on, or corrugated couplings matching the pipe corrugation of bell and spigot or split collar type engaging at least two full corrugations on each pipe section. Use fittings supplied or recommended by the pipe manufacturer.

Join pipe end sections and plug or cap up-grade ends of subdrain pipe.

Wrap pipe with Geotextile, Drainage, Class II as shown in plans.

After the pipe installation inspection and approval, place and compact the porous backfill material to the height specified in the plans above the top of pipe. Fill trench above the porous backfill with specified material.

CR605.1-061520/CFHWY00599

605-5.01 BASIS OF PAYMENT.

Add the following:

Pipe cleanouts, including the cast iron cover and marker post are subsidiary.

CFHWY00599

Delete pay item 605.0006.____ and .0007.____.

Add the following:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 605.2008.____ | Perforated Corrugated HDPE Pipe ___ | LF |

CR605.1-061520

Special Provisions

Replace Section 606 with the following:

SECTION 606
GUARDRAIL

606-1.01 DESCRIPTION. Construct new guardrail, terminal sections, transition rail, and permanent crash cushions.

The permanent crash cushion, hereafter referred to as, "crash cushion," includes the complete assembly (crash cushion, foundation, backstop or transition) represented in the FHWA eligibility letter(s).

Remove and reconstruct or remove and dispose of existing guardrail, terminal sections, transition rail, and crash cushions.

606-1.02 SUBMITTALS.

1.	Submit the following at the preconstruction conference and receive approval before installation.

a.	Permanent Crash Cushions.

(1)	FHWA Eligibility Letter(s).  Eligibility letters demonstrating each crash cushion assembly is MASH 2016 compliant with the AASHTO 2016 Manual for Assessing Safety Hardware (MASH-16) Test Level 3.  Demonstrate the eligibility letter shielding widths cover the hazard widths and travel directions shown in the plans.

(2)	AASHTO Listing Category. AASHTO listing or documented updates for the crash cushion classification as listed in the 2011 AASHTO Roadside Design Guide, Section 8.4.

(3)	Manufacturers' Shop Drawings, Assembly, and Installation Instructions.  Submit shop drawings and detailed assembly and installation instructions for the crash cushion as included in the FHWA Eligibility Letters.

(4)	Manufacturer Certification Letter. Certify the crash cushion(s) meet the requirements of the FHWA eligibility letter(s), are suited to the Contract requirements including the environmental conditions at the installation site.

(5)	Manufacturers' Installer Certification Letter. Certify the installation contractor is familiar with and trained to install the crash cushion.

(6)	Manufacturers' Installation Checklist. Submit a crash cushion installation checklist.

b.	Parallel Terminals.

Manufacturer Installation Checklist. Submit an Assembly Installation Checklist.

2.	Submit the following after installation.

a.	Permanent Crash Cushions.

(1)	Manufacturer Certification Letter. Certify the installed crash cushion(s) meet the requirements of the FHWA eligibility letters. Submit the certification letters(s) signed and dated no more than 14 days after installation.

(2)	Manufacturers' Installation Checklist. Submit the completed installation checklist signed by the Installer and Manufacturer no more than 14 days after installation. Complete the checklist after each assembly.

b.	Parallel Terminals.

Manufacturer Installation Checklist. Submit the completed installation checklist signed by the Installer and Manufacturer no more than 14 days after installation. Complete the checklist after each assembly.

606-2.01 MATERIALS. Use materials that conform to the following:

Concrete, Class B	Section 550

Flexible Delineator Posts	Subsection 730-2.05

Guardrail Connection Plate	Section 722

Guardrail Hardware	Subsection 710-2.07

Guardrail Posts and Blockouts	Subsection 710-2.06

High Strength Bolts	Section 722

Metal Beam Rail	Subsection 710-2.04

Terminals	Subsection 710-2.11

Terminal Markers	Subsection 730-2.05

Wire Cable	Subsection 709-2.02

Guardrail Reflector Assembly Brackets, Side-Mounted. Aluminum alloy.

Retroreflective Sheeting.

1.	Post-Mounted Flexible Delineators and Guardrail Reflectors. ASTM D4956 Type IX or XI.

2.	Terminal Markers. ASTM D4956 Type VIII, IX or XI.

Permanent Crash Cushion Assembly.

Crash cushions include the complete assembly as included in the Eligibility Letter, the crash cushion, the foundation, and rigid backup anchorage, or transition connection. Install an added Terminal Marker or other flexible delineator to the front of the crash cushions as recommended by the Manufacturer.

Design the crash cushion for the installation location environment. Snow combined with frequent freeze-thaw cycles creates significant ice buildup that may impair the performance of the crash cushion.  Design to mitigate the effects from snow and ice. Crash cushions using supports that interlock and travel within fixed tracks at or below the first six inches from ground level, and crash cushions not designed to mitigate snow and Ice buildup are not acceptable for permanent use. Crash cushion covers, when available from the manufacturer, are required as part of the crash cushion installation.

Crash Cushion Classifications. 2011 AASHTO Roadside Design Guide, 4th Edition.  The Engineer will determine the final classification of each materials submittal.  Provide redirective and non-gating crash cushions of the type specified in the plans and matching the description noted below.

1.	Sacrificial:  Demonstrated designed for a single impact.

2.	Reusable Crash Cushion.  Demonstrated to have major components survive most impacts intact and salvageable.  Some components require replacement after a crash.

3.	Low-maintenance and Self-restoring Crash Cushion. Demonstrated to suffer very little, if any damage, upon impact and easily pulled back into their full operating condition.  They may partially rebound after an impact and may only need an inspection to ensure that no parts have been damaged or misaligned.

CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL. Install guardrail and terminals at the locations shown on the Plans. Conform to the Alaska Standard Plans and these Specifications.

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals, that are required to completely install a segment of guardrail before beginning work on that segment.

Start guardrail installation at the "upstream" end (the end adjacent traffic encounters first) by either installing a crashworthy terminal, connecting to an existing barrier or shielding the end with a crash cushion or truck mounted attenuator (TMA) meeting NCHRP 350, Test Level 3.  Continue installation in the direction of traffic.  Exception:  if the guardrail run connects to existing barrier, buried in the backslope terminal, existing or new bridge railing, or other existing structure at the "downstream" end, guardrail installation may start at the point of connection.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail. At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test level 3 at all non-crashworthy guardrail ends within the construction clear zone. Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

When possible, proceed with construction of guardrails with the direction of traffic.

Where necessary, adjust the height of existing guardrail to provide a smooth transition to new guardrail. Use 25 linear feet of guardrail or two 12’ 6” pieces of guardrail to transition to match the existing or new guardrail elements and/or end treatments.

After shaping the slopes and staking proposed guardrail terminal section locations, request the Engineer to field verify their locations. Receive approval of the staked locations before installing terminal sections.

Treat field cuts to timber posts and blockouts according to AWPA standard M 4.

Install blockouts according to manufacturer’s recommendations and as shown on the plans.

Install side-mounted guardrail reflectors and post-mounted flexible delineators as follows:

1.	at intervals noted on the plans or Alaska Standard Plans, starting with the first guardrail post beyond terminal sections

2.	with the retroreflective sheeting facing approaching traffic

3. 	with retroreflective sheeting on both sides, on two-way roadways

4.	not on the terminal sections, except as shown on the plans

5.	at or below 500 feet in elevation, except as noted otherwise in the Plans.

Attach terminal markers, in a vertical position, to the P.T. post of Short Radius Guardrail sections and to the post where the flare begins for parallel guardrail terminals.  Coordinate terminal marker locations with the Engineer.

At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

606-3.02 POSTS. Set posts to accommodate the line, grade, and curvature shown on the Plans.

Use either wood or steel posts when allowed by the type of guardrail specified, subject to the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

Set posts as follows:

1.	Set posts plumb, in the location and to the depth shown on the Plans or Alaska Standard Plans.

2.	Choose an installation method that does not damage the post, adjacent pavement, structures, utility conduits, and final slopes. Repair all damage to the satisfaction of the Engineer, or replace the damaged item, as per subsection 105-1.11.

3.	Set wood or steel posts in dug, drilled, or pre-punched holes. Steel posts may also be set by ramming or driving if:

a.	The underlying material is no larger than six inch; and

b.	The posts are not damaged during installation.

4.	Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically. Compact under and around posts to the Engineer’s satisfaction.

5.	For placement in solid rock or broken rock embankment greater than six inch, set wood or steel posts in pre-dug, pre-drilled, or pre-punched holes.

6.	In new roads, install posts before final shoulder or median compaction, surfacing, and paving.

606-3.03 BEAM RAIL. Fabricate metal work in the fabricator’s shop. Bend curved guardrail elements with radii less than or equal to 100 feet in the fabricator’s shop or with an approved bending apparatus.

Receive approval before field punching, cutting, or welding. Repair damaged spelter coat areas on galvanized rail elements according to AASHTO M 36 (ASTM A760).

Lap rail elements so that the exposed ends face away from approaching traffic in the adjacent lane.

Use bolts long enough to extend at least 1/4 inch beyond the nuts. Except where required for adjustments, do not extend bolts more than 1 inch beyond the nuts.

Locate bolts at expansion joints at the center of the slotted holes.

Tighten bolts at expansion joints to snug-tight. Make all other bolts fully-tight.

606-3.04 CABLE RAIL. Install cable guardrail according to the Plans and Specifications. Install at the locations shown on the Plans.

606-3.05 TERMINAL SECTIONS.

Parallel Terminals.

Install terminal sections according to the manufacturer’s recommendations for the entire length of the terminal then, if required, transition rail height over 25’ to match guardrail height and splice location.

Install ASTM D4956 Type III, IV, or V retroreflective sheeting on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal according to guidance for Object Markers for Obstructions Adjacent to the Roadway in Chapter 2C of the ATM.

Submit the manufacturers' complete Assembly Installation Checklist signed and dated after completing installation to support acceptance for each installation, see Subsection 606-1.02 for further information.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Remove and reconstruct guardrail as specified. Replace lost or damaged materials without extra compensation.

When replacing existing guardrail complete the replacement run installed within 14 calendar days after removal.

For guardrail located within 50 feet of bridge ends, remove and replace the existing guardrail in the same work shift.

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL. Remove the existing guardrail, including the rail, cable elements, terminal sections, hardware, posts, concrete bases, and steel tubes. Backfill resulting holes with material in 6-inch layers that is similar to the existing embankment and compact to the same approximate density.

Guardrail.

Notify the Engineer a minimum of 5 days before removing guardrail.  The Engineer will notify the ADOT & PF, M & O, and have an M & O representative designate portions of guardrail for salvage.  Deliver salvaged guardrail and associated hardware to the M & O station located at 289 Inner Springer Loop, Palmer, AK 99645.  Remaining items removed become the Contractor's property.

Permanent Crash Cushion.

Notify the Engineer a minimum of 5 days before removing permanent crash cushions.  The Engineer will notify the ADOT & PF, M & O, and have an M & O representative designate portions of the crash cushion for salvage.  Deliver salvaged crash cushion and associated hardware to the M & O station located at 289 Inner Springer Loop, Palmer, AK 99645. Remaining items removed become the Contractor's property.

606-3.08 ADJUST EXISTING GUARDRAIL. When called for on the Plans, reset existing guardrail to the height shown on the applicable Alaska Standard Plan, measured from the top of the rail to the finished shoulder surface below the rail. Raise and lower the posts several times to prevent settlement and then re-drive them to the height shown on the Plans. Use other methods if approved.

606-3.09 INSTALL NEW GUARDRAIL. Install guardrail as shown on the applicable Alaska Standard Plan, measured from the top of the rail to the finished shoulder surface below the rail.

Install MASH-16 Test Level 3-compliant W31 guardrail as shown on the plans.  Install new guardrail in conformance with tolerances shown on the plans.

606-3.10 TERMINAL MARKERS. For each parallel rail terminal, attach a terminal marker to the extreme piece of rail.

Attach flexible markers, in a vertical position, to the terminal end directly to the backside of the rail face, the face away from the traveled way, or the first post of each parallel guardrail terminal.  Provide an additional marker where the flare begins for guardrail terminal widening.  Provide two markers at the end of each run of guardrail; coordinate the locations with the Engineer.

Attach the flexible markers using hardware and attachment methods recommended by the manufacturer. The connection shall not negatively influence the performance of the guardrail as noted in 606-2.01.

606-3.11 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  When the Engineer determines additional guardrail is required, complete the installation immediately.

606-3.12 PERMANENT CRASH CUSHION.  Install crash cushions according to the manufacturer's instructions.

Construct crash cushions to shield the hazard width and travel direction shown in the plans.

Manufacturer's Crash Cushion Installation Certification. Submit the Manufacturer's Crash Cushion Installation Certification letter signed and dated after completing installation, see Subsection 606-1.02 for further information.

Manufacturer Certified Installers.  Install crash cushions using installers certified by the crash cushion manufacturer.  Install Crash cushions as follows:

1.	Parallel to the approach traveled way or as shown on the plans.

2.	Follow Section 203 for the excavation and embankment requirements of the concrete base component of the crash cushion.

3.	Follow Section 501 for a concrete pad, sized according to the manufacturer's recommendations, constructed on a minimum of 12 inches of Selected Material, Type B.

4.	Cut or fill to the top of the concrete pad with Selected Material, Type B at 12:1 or shallower on installations in grass median.

5.	Install top elevation of concrete pad flush to pavement edge when adjacent to or within asphalt pavement.

6.	Bolt crash cushion to median barrier with manufacturer approved barrier to crash cushion connector when attached to median barrier.

7.	Install a terminal marker or other flexible delineator on the nose of each crash cushion as recommended by the manufacturer.  The terminal marker is in addition to, not a substitute for, the retroreflective delineation installed on the crash cushion nose.

8.	Manufacturers' Crash Cushion Installation Checklist. Submit the installation checklist signed and dated after completing installation, see Subsection 606-1.02 for further information.

The crash cushion installation is not complete until the Crash Cushion Manufacturers' Installation Checklist and Installation Certification letter are submitted and the Engineer accepts the installation.

Excess excavated material is the property of the Contractor.

606-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

- Guardrail. Measured along the face of the rail or cable, from the center of the end posts.

Short Radius Guardrail. Per each, installed in place.

When the guardrail is connected to a terminal section, the pay limit for the rail ends where the specified terminal section begins.

2.	Terminals. Per each, installed in place.

3.	Transition Rail (Bridge Rail Thrie Beam Transition or Bridge Rail W-Beam Transition). Per each accepted connection.

4.	Permanent Crash Cushion.  Each installed and accepted.

606-5.01 BASIS OF PAYMENT.

Payment for temporary crash cushions or TMA installed to protect motorists when guardrail installations are not completed within 10 calendar days of beginning installation is subsidiary to other items.

1.	Guardrail. Side-mounted guardrail reflectors, post-mounted flexible delineators, terminal markers, guardrail beam, posts, blockouts, and associated hardware are subsidiary.  Installation of downstream anchors, transitions for rail height and splice locations, long span guardrail sections, and guardrail stiffening sections are subsidiary to guardrail installation.

2.	Short Radius Guardrail Sections. The contract price includes all materials from the terminal anchor to and including the first wood or steel post of standard guardrail or guardrail end terminal, and including the terminal anchor assembly, in-line anchor, terminal posts, short radius guardrail posts, rail elements, terminal markers, and associated hardware required for a complete installation.

3. 	Terminal Sections.

a.	Parallel Guardrail Terminal. The contract price includes rail elements, posts, blockouts, pipe sleeves, cable assemblies, guardrail extruders, terminal markers, and all associated hardware required for a complete installation.

4.	Transition Rail. The contract price includes all brackets, beam sections, transition pieces, and all posts and associated hardware required for a complete connection of the guardrail section to a bridge rail or barrier.

5.	Permanent Crash Cushion.  The contract price includes all work and materials required to install each permanent crash cushion, foundations, and connections along with the manufacturer's field support, recommendations, and shop drawings.  Removal and salvage of existing crash cushions is subsidiary to Pay Item 606.2007.____ Pay Item(s).

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 606.0001.____ | W-Beam Guardrail | LF |
| 606.0002.____ | Thrie Beam Guardrail | LF |
| 606.2003.____ | Box Beam Guardrail | LF |
| 606.0004.____ | Cable Guardrail | LF |
| 606.0005.____ | Removing and Reconstructing Guardrail | LF |
| 606.0006.____ | Removing and Disposing of Guardrail | LF |
| 606.0007.____ | Double-faced, W-Beam Guardrail | LF |
| 606.0009.____ | Short Radius Guardrail | Each |
| 606.0013.____ | Parallel Guardrail Terminal | Each |
| 606.0015.____ | Adjust Existing Guardrail | LF |
| 606.0016.____ | Transition Rail | Each |
| 606.2007.____ | Crash Cushion, Permanent ____________ | Each |

CR606-123121

SECTION 607
FENCES

Special Provisions

607-1.01 DESCRIPTION.

Add the following:  Construct a noise barrier.

607-2.01 MATERIALS.

Replace	 "Concrete           		Section 550, Class W" with the following:

Concrete	Section 550, Class B

Add the following:

Timber used in the wood noise barrier, shall be as follows:

Posts		Douglas Fir-Larch		Dense No. 1

Stringers	 	Douglas Fir			No. 2

Cedar Boards	Western Red Cedar	1-inch nominal thickness (rough sawn both sides use tight knot cedar)

The noise barrier posts and stringers shall be treated in accordance with Section 714, Preservatives and Preservative Treatment Processes for Wood Materials, unless otherwise directed by the Engineer.  Any field cutting of post ends shall require an application of minimum 10 percent copper naphthenate preservative. Color to match preservative pressure treatment color.

All cedar boards for noise barriers shall be coated with a creosote based stain or 20 percent polyurethane base semi-transparent stain to be applied at a rate of one (1) gallon per 100 square feet. The stain shall be Red Cedar in color.

607-3.01 CONSTRUCTION REQUIREMENTS.

Add the following:

The faces of the wood noise barriers shall be constructed of shiplap boards.  Construct the vertical portion of the shiplap boards on the face of the noise barrier using individual boards continuous between top and bottom of noise barrier.  No horizontal joints are permitted in the fascia boards on the face of the noise barrier.  Horizontal joints for the fascia opposite the face of the noise barrier are acceptable.  Make all vertical joints and horizontal joints (where acceptable) over a secured nailer.

Install reflective sheeting facing outward on chain link fence posts centered 4 feet from ground. Sheeting shall be 2 inches wide and 2 feet long, alternating red and white stripes, and weather, impact, and abrasion resistant.

607-4.01 METHOD OF MEASUREMENT.

Add the following:

The noise barrier will be measured by the square foot from the bottom of the barrier to top of barrier.

607-5.01 BASIS OF PAYMENT.

Add the following:

Payment for Noise Barrier will be full compensation for all labor, materials, and equipment required to construct the Barrier.

Installation of reflective sheeting shall be subsidiary to installation of chain link fence.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 607.2003.____ | Noise Barrier | SF |

CFHWY00599

Special Provision

Replace Section 608 with the following:

SECTION 608
SIDEWALKS

608-1.01 DESCRIPTION. Construct, or retrofit asphalt, or concrete sidewalks.

Sidewalk Section 608 includes "sidewalks", pathways, medians, curb ramps, miscellaneous on-grade concrete, and asphalt surfaces not addressed elsewhere in the specifications.

608-2.01 MATERIALS. Use materials that conform to the following:

1.	Concrete

Bed Course Material	Subsection 703-2.03

Joint Fillers	Subsection 705-2.01

Joint Sealers	Subsection 705-2.02

Concrete	Section 550, Class B

Acid Wash	Muriatic or Phosphoric

Admixtures	AASHTO M 194 Chemical Admixtures†

ASTM C 494 Standard Specification for Chemical Admixtures for Concrete†

Curing Agents	ASTM C 309, Liquid Membrane-Forming Compounds for Curing Concrete †

Expansion Joints	AASHTO M-33 Preformed Expansion Joint Filler for Concrete (Bituminous Type)

Integral Color Agent	ASTM C 979 Standard Specification for Pigments for Integrally Colored Concrete

Reinforcing Steel	Section 503

†	Compatible with colorant manufacturer.

Provide concrete for slabs according to Section 501, ACI 303R, 303.1, this specification and the material manufacturer's and supplier's written instructions.

Maximum slump 4-inch, except 8-inch maximum if using super plasticizers or mid-range water reducers. Mix used for sample(s) shall be the same as the production mix(s).

Concrete - Exposed Aggregate Finish. Provide aggregate from a single source.  Keep aggregate for exposed aggregate finish separate from other project aggregate.

Concrete – Colored. Color concrete using an integral color, with a surface hardener, a color cure, a release agent, and a sealer compatible with colorant(s).

Concrete - Pattern Imprinted. Use a manufactured system designed to provide the pattern specified and a release agent compatible with the colorant.

2.	Asphalt (HMA)

Bed Course Material	Subsection 703-2.03

Asphalt Binder, PG 52-28	Subsection 702-2.01

Aggregate, Type II or III	Subsection 703-2.04

Mix Design Requirements (ATM 417)

Marshall Stability, pounds, min.	1000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

Coating/Paint:

Material - Methyl Methacrylate (MMA)	Subsection 712-2.17 (MMA only)

Color	Federal Standard 595, color 30111 (Brick Red)

3.	Detectable Warnings

Cast iron detectable warning plates with truncated dome pattern, a slip resistant surface, and with handle or flange on bottom or approved equal. Detectable warning plates shall be coated with yellow polymer soaked finish. Detectable warnings shall be manufactured according to the 2006 U.S. DOT ADA Standards for Transportation Facilities.

608-2.02 REFERENCES.

1.	ACI 303		Cast-In-Place Architectural Concrete Practice

2.	PCA PA124		Finishing Concrete Slabs with Color and Texture

3.	PCA SP021		Color and Texture in Architectural Concrete

608-2.03 SUBMITTALS – EXPOSED AGGREGATE, COLORED CONCRETE, PAINTED HMA AND PATTERN IMPRINTED CONCRETE AND HMA.  Provide complete submittals (3 printed copies, except samples as specified below), to the Engineer for review and approval, at least 21 days before beginning construction of concrete and asphalt items.  Submittals will be returned to the Contractor within 14 days from the date submitted, marked as approved by the Department, or requiring revisions.  Amend and resubmit the documents for review until approved by the Engineer.  Receive approval before beginning production.

Submit shop drawings, product data, specifications, certifications; manufacturers and installer's resumes, and samples as specified in Section 401, 501, 503, 608 and herein.

1.	Shop Drawings, Product Data, Specifications, and Certifications.

a.	Exposed aggregate finish:  manufacturer's chemical surface retarder.

b.	Integral concrete colorant:  manufacturer's color chart, and chipset.  Indicate color additive numbers and required dosage rates as part of the concrete mix submittal, Subsection 501-3.01.

c.	Manufacturer's concrete pattern imprinting system.

d.	Manufacturer's fabricated HMA pattern imprinting tool - shop drawings.

e.	Methyl Methacrylate for coating HMA.

f.	Other when requested by the Engineer.

2.	Resumes.

a.	Manufacturer.

Concrete. Provide documentation for five years of successful product performance, with a minimum of five completed projects and including but not limited to:

	Manufacturer's colorant, hardener, color cure, release agent, and sealer

	Batch Plant's mixing of manufacturer's colorants and other additives, and product delivery

	Manufacturer's pattern imprinting system

HMA. Provide documentation of two years and three projects successfully fabricating pattern imprinting tools and successful product performance applying MMA in similar applications to this Project.

b.	Installer.

Concrete and HMA. Installer(s) with 2 years' experience and 3 successfully completed projects of similar configuration and method of installation.

In addition:

1)	For projects with concrete integral colorant and or pattern imprint system, provide a minimum of one project using the proposed manufacturer's colorant and pattern imprint system.

3.	Manufacturer's.

All manufacturers, listed and other, are required to submit for review and approval.

Manufacturers of concrete colorant and pattern imprinting systems:

| Bomanite Corporation P.O. Box 599 Madera, CA 93639 Ph: 303.369.1115 Fax: 303.291.0282 Email: bomanite.com | Brickform, division of Solomon Colors, Inc. 11061 Jersey Blvd. Rancho Cucamonga, CA 91730 Ph: 800.483.9628 Email: brickform.com | Davis Colors 3700 East Olympic Blvd. Los Angeles, CA 90023 Ph: 800.356.4848 Fax: 323.269.1053 Email: daviscolors.com | L.M. Scofield Company 6533 Bandini Blvd. Los Angeles, CA 90040 Ph: 323 720.3000 Fax: 323.720.3000 Email: Scofield.com |
| --- | --- | --- | --- |

4.	Pattern Imprinting, Coloring Concrete, and HMA Painting Plans.

Provide pattern imprinting, concrete coloring, and HMA painting plans to the Engineer for review and approval.  Include the following, at a minimum, to achieve a final product that accurately represents, to scale, colored concrete, painted HMA and the pattern imprinted concrete and HMA (including the joints) elements:

a.	the sequence and schedule of operations,

b.	the proposed method of pattern imprinting,

c.	the method of coloring the concrete,

d.	the method of applying the MMA coating/paint to the HMA.

5.	Exposed aggregate, Colored Concrete and Painted HMA and Pattern Imprinted Concrete and HMA Sample(s).

Provide one sample, equal to the width of the item, 6 ft x 6 ft maximum, 4 ft x 4 ft minimum, of each item for review by the Engineer.  Demonstrate exposing the aggregate, the addition of colorant to the concrete, painting the HMA and pattern imprinting the concrete and HMA on each sample provided.

Receive written approval of the sample prior to beginning production work.

Retain samples of binder(s), sand(s), aggregate(s), and color additive, used in the sample for comparison with the item production materials.  Keep sample through completion of related work for use as a quality standard for finished work.  Keep the sample through Project completion when requested by the Engineer.

CONSTRUCTION REQUIREMENTS

608-3.01 CONCRETE SIDEWALKS. Excavate to the required depth and to a width necessary to install and brace the forms. Shape and compact the foundation to a firm, even surface conforming to the section shown on the Plans. Replace soft and yielding material with approved material. Compact bed course material according to Subsection 203-3.04.

Use full depth forms made of wood or metal. Use forms that are straight, free from warp, and strong enough to resist the pressure of the concrete without springing. Coat forms with an approved form-release agent. Brace and stake the forms so that they maintain their position until their removal.

Thoroughly moisten the foundation immediately before placing the concrete.

Finish the surface according to Section 550-3.05. Do not plaster the surface. Edge all outside slab edges and all joints to a 1/4 inch radius.

Make expansion joints to the dimensions and spacing shown on the Plans and fill with the type of preformed expansion joint fill specified.

Divide the sidewalk into specified sections using dummy joints formed by a jointing tool or other acceptable means. Make dummy joints 1/3 the depth of the concrete and approximately 1/8 inch wide.

Form construction joints around all appurtenances such as manholes, utility poles, buildings, or bridges, extending into and through the sidewalk. Install preformed expansion joint filler 1/2 inch thick in construction joints. Extend the expansion joint material the full depth of the walk.

Apply joint sealer evenly to completely seal all joints.

Cure the concrete according to Section 550-3.06. During the curing period, exclude all pedestrian and vehicular traffic. Exclude vehicular traffic for additional time as directed.

The Engineer will test the finished surface with a 10-foot straightedge. Variations of more than 1/4-inch from the edge of the straightedge across or along the sidewalk surface, except at grade changes, are unacceptable. Portions of the sidewalk surface and pedestrian ramps less than 10 feet in width, or length may be tested using a shorter straightedge.

Exposed Aggregate, Colored Concrete and Painted HMA and Pattern Imprinted Concrete and HMA

Match the Project work to the approved sample.  Significant differences in appearance (texture, color, pattern, or other) between adjacent panels/sections of work, from the approved sample including adjacent panels/sections similar to the approved sample yet significantly different to each other, as judged by the Engineer, will result in removal and replacement of the deficient panel(s)/section(s) of work.

Take all precautions to avoid damaging new and existing, concrete and asphalt.

Prevent surrounding materials from being discolored by the concrete and HMA and the HMA MMA coating (curbs, gutters, and other).  When directed by the Engineer, in writing, remove stains and coatings on other concrete and or HMA, resulting from your work.

Where HMA paving is against; exposed aggregate finish, colored, pattern imprinted; colored and pattern imprinted concrete, place the concrete prior to asphalt paving.  Do not place the HMA pavement until the concrete has cured sufficiently to prevent damage from the paving operation.

Acceptance of corrective work requires the Engineer's written approval.  Repair all new and existing damaged concrete and HMA, including the removal of surface contaminants, to the satisfaction of the Engineer.  The Engineer will not provide written approval until all damaged concrete and HMA is repaired.

1.	Slab Types.

| TABLE 608-1 Slab Type Requirementsa, b |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Typec | Description | Finishd, e, f | Added Colorg | Added Patterng | th Inches | Reinforcingi (bar spacing each way) |
| a. & b. | Typical | Broom |  |  | 4, 6 |  |
| I | Broom | Broom |  |  | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
|  |  |  |  |  | 8 | #6@12" O.C. |
| II | Exposed Aggregate | Aggregate |  |  | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
| III | Colored | Broom | Color Manufacturer |  | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
| IV | Pattern Imprinted | Coordinate |  | Pattern Manufacturer | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
| V | Colored & Pattern Imprinted | Coordinate | Brick Red & Herringbone Manufacturer |  | 4 | 4x4  W2.9xW2.9 |
|  |  |  |  |  | 6 | #5@12" O.C. |
| a. Sealer and Hardener: provide for all slabs. b. Transition the slab at approaches as shown in the plans. c. Type a. & b.; Pay Items 608.0001.____, are the "Typical" concrete sidewalk. d. Broom: provide a medium broom finish. e. Aggregate: provide a uniform color slightly darker than the typical uncolored slab with a uniform reveal according to ACI 303.1. f. Coordinate: coordinate and provide finish as required by pattern imprint system manufacturer. g. Color and Pattern: provide color and or pattern similar to that noted and available from the listed manufacturer(s). Provide color and pattern from the same manufacturer or provide from different manufacturers with a certification from each permitting warranted use of their product with the product of the other manufacturer. Use a release agent as approved by the manufacturer(s). h. t: provide the slab thickness, denoted as "t" i. Reinforcing: Provide welded wire fabric in sheets not rolls. Lap joints 1 1/2 mesh minimum. |  |  |  |  |  |  |

2.	Joints.

Lay out joints as shown or noted in the Plans and Specifications, if not shown or noted provide:

a.	Control Joints.  Maximum spacing equals 12 ft.  (also referred to as, "dummy joints")

(1)	the joint configuration should create a square or rectangle with the long side no more than 1.5 times the short side,

(2)	space the control joint matching the width of the slab,

(3)	at corners and intersections, align the joints parallel to the edge(s) of the intersecting slab.

(4)	locate the joints equally spaced between the:  ends/edges of slab, slab corners, slab intersections or a combination of one and another.

b.	Expansion Joints.  Maximum spacing equals 36 ft.

Touch up pattern and finish edges with hand tools immediately after placing concrete and as directed by the manufacturer(s) and Engineer.

608-3.02 ASPHALT SIDEWALKS. Place bed course material in layers. Compact it according to Subsection 203-3.04.

Place asphalt material on the compacted bed course in one or more courses as indicated on the Plans. Compact it uniformly to required depth. Use a power roller of an acceptable type and weight. In areas inaccessible to the roller, use other approved methods.

608-3.03 CURB RAMPS.

Measure curb ramp slopes with a 24-inch electronic level. Calibrate and operate the level according to the manufacturer's instructions.

608-3.04 DETECTABLE WARNINGS. Construct detectable warnings according to the details and the locations shown on the Plans. Install detectable warning plates by embedding plate flanges into cast-in-place concrete construction so there are no vertical changes in grade exceeding 0.25 inch or horizontal gaps exceeding 0.5 inch. Align pattern on a square grid in the predominate direction of travel. Install the same type of detectable warning plate throughout the project.

Detectable warnings shall be installed according to the 2006 U.S. DOT ADA Standards for Transportation Facilities.

608-3.05 ASPHALT – PATTERN IMPRINTED AND PAINTED.  Construct pattern imprinted and painted HMA according to Subsection 608-3.02 Asphalt Sidewalks and as noted herein.

1.	Pattern.  Fabricate the imprint tool pattern to match standard brick dimensions in a running bond configuration with a slightly wider joint/indent spaced similar to the concrete expansion Joint.

2.	Painting.  Prepare the asphalt surface and apply the coating/paint according to the MMA manufacturer's instructions. Apply coating (MMA) completely covering the asphalt surface including pattern imprint.  Do not fill the pattern indentation, with MMA, flush with the top surface.  Leave a 1/8", smooth, concave painted/coated surface between bricks (joint).

608-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Sidewalk. By area of finished surface, weight of material placed, and lump sum as included in the bid schedule. Ramps are included in the measurement unless included as a separate measured and paid item.

HMA. HMA used for matching existing surfaces, such as paved parking lots behind a new sidewalk/pathway, will be included in the measurement of the related asphalt Pay Item.

CR608-113020R/CFHWY00599

Detectable Warning Tile. Per each unit installed that are not included in the curb ramp quantity.

CFHWY00599

608-5.01 BASIS OF PAYMENT.

Subsidiary to the Pay Items: excavation, backfill, reinforcement, expansion joint material, samples, asphalt binder, corrective work, and other related miscellaneous items.

Embankment and bed course materials will be furnished, placed, and paid under Sections 203 and 301, respectively.

Curb Ramp when included in the bid schedule, includes ramp runs, backing curbs, flares, landings to provide a single street-level access and detectable warnings, except detectable warnings are paid separately when included as an item in the bid schedule.

CR608-113020R/CFHWY00599

Detectable Warning Tile. Includes detectable warning tiles, concrete foundation material, and work associated with installation per Plan.

CFHWY00599

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 608.0001.___ | Concrete Sidewalk, 4 inches thick | SY |
| 608.0001.___ | Concrete Sidewalk, 6 inches thick | SY |
| 608.0002.___ | Asphalt Sidewalk | Ton |
| 608.0006.___ | Curb Ramp | Each |
| 608.0007.___ | Curb Ramp, Retrofit | Each |
| 608.2002.___ | Asphalt Pathway | Ton |
| 608.2004.___ | Asphalt Medians | Ton |
| 608.2006.___ | Asphalt Pathways and Medians | Ton |
| 608.2007.___ | Asphalt, (Sidewalk, Plaza, etc., __ Inches Thick) | SY |
| 608.2008.___ | Asphalt Pattern Imprinted and Painted, (Median, etc., __ Inches Thick) | SY |
| 608.2010.___ | Concrete Sidewalk Wall, (Type __; Slab __ in; Wall __ in; Ht __ ft) | LF |
| 608.2011.___ | Concrete Sidewalk Retaining Wall, (Type __; Slab __ in; Wall __ in; Ht __ ft) | LF |
| 608.2012.___ | Concrete Sidewalk Barrier Wall, (Type __; Slab __ in; Wall __ in; Ht __ ft) | LF |
| 608.2013.___ | Concrete, Type I, __ inches thick, Broom Finish, (median slab, etc.) | SY |
| 608.2013.___ | Concrete, Type II, __ inches thick, Exposed Aggregate Finish, (median slab, etc.) | SY |
| 608.2013.___ | Concrete, Type III, __ inches thick, Colored, (median slab, etc.) | SY |
| 608.2013.___ | Concrete, Type IV, __ inches thick, Pattern Imprinted, (median slab, etc.) | SY |
| 608.2013.___ | Concrete, Type V, __ inches thick, Colored and Pattern Imprinted, (median slab, etc.) | SY |
| 608.2014.___ | Concrete Medians | SY |
| 608.2015.___ | Concrete Stairway | LS |
| 608.2032.___ | Detectable Warning Tile | SY |

CR608-113020R

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 608.2017.___ | Detectable Warning Tile | ea |

CFHWY00599

Special Provisions

Replace Section 610 with the following:

SECTION 610
DITCH LINING

610-1.01 DESCRIPTION. Construct ditch lining at the locations on the Plans or as staked.

610-2.01. MATERIALS. Use crushed stones that are angular, hard, sound, and durable with at least one face resulting from fracture.

1.	Angular—stones, the particles of which possess well-defined edges formed at the intersection of roughly planar faces.

2.	Hardness—resistance of a material to indentation or scratching. AASHTO T96, not more than 50% wear at 500 revolutions.

3.	Soundness—measure of aggregates durability when exposed to the elements, AASHTO T104.

4.	Gradation—ATM 304:

a.	Maximum of 6 inches in greatest dimension

b.	Not more than 50% by weight passing a 3-inch sieve

c.	Not more than 5% passing a 1-inch sieve

5.	Breadth and Width—at least 1/3 of the length

610-3.01 CONSTRUCTION REQUIREMENTS. Place and spread ditch lining materials so that the finished face is uniform. 	Place stones on slopes 1.5:1 and flatter.

610-4.01 METHOD OF MEASUREMENT. Section 109.

610-5.01 BASIS OF PAYMENT. Excavation required below normal ditch grade is subsidiary.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 610.0001.____ | Ditch Lining | CY |
| 610.0002.____ | Ditch Lining | Ton |
| 610.0003.____ | Ditch Lining | STA |

CR610-060117R

SECTION 611
RIPRAP

Special Provision

611-2.01 MATERIALS.

Replace the first paragraph with the following:

Evenly graded stones that are hard, angular, and have no more than 50 percent wear at 500 revolutions as determined by AASHTO T 96.  Apparent specific gravity will be determined by ATM 308. Use stones with breadth and thickness at least 1/3 of its length. Do not use round boulders or cobbles on slopes steeper than 3:1.

CR611.1-020119

Special Provisions

Replace Section 615 with the following:

SECTION 615
STANDARD SIGNS

615-1.01 DESCRIPTION. Furnish and install standard signs and delineators. Remove and relocate or remove and dispose of existing signs and markers, as specified.

615-2.01 MATERIALS. Use materials that conform to the following Subsections:

Sheet Aluminum 		730-2.01

High Density Overlaid Plywood		730-2.02

Retroreflective Sheeting, ASTM D4956 		730-2.03

Sign Posts		730-2.04

Delineator Posts		730-2.05

Acrylic Prismatic Reflectors		730-2.06

Sign Support Fasteners		730-2.07

1.	Shop Drawings. Submit shop drawings, for all signs that must meet the ASDS letter width and spacing charts for variable width legends (such as D-series and I-3 signs), and which require custom shop drawings specific to the project. Submit 4 sets of collated shop drawings prepared according to Subsection 105-1.02. Show the following on each sign drawing:

a.	Dimensions of all horizontal and vertical characters and spaces

b.	Overall dimensions

c.	Sign material and sheeting material type

d.	Panel thickness

e.	Legend and letter series

f.	Whether the sign will be framed

2.	Sign Fabrication. Use ASTM D4956 Type IV retroreflective sheeting (for lettering, symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX or XI fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

(1)	For temporary installations, the reflective sheeting place on aluminum, plastic, or plywood sheet panels.

(2)	For flexible signs, (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports: Use white ASTM D4956 Type VIII or Type IX or XI retroreflective sheeting for background of sign and all strips.

c.	Non-Illuminated Overhead Signs with White Legends on Green Backgrounds: Use ASTM D4956 Type IX or XI retroreflective sheeting for legends and background. Create the legend in one of the following ways:

(1)	Cut border and legend from white ASTM D4956 Type IX or XI retroreflective sheeting and adhere them to a green ASTM D4956 Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white ASTM D4956 Type IX or XI retroreflective background.

d.	Fluorescent Yellow-Green School Area Signs: Use ASTM D4956 Type VIII, Type IX or XI retroreflective sheeting for background.

Use a manufacturer-recommended clear coat on all screened signs.

Use sign layouts (including characters, symbols, corner radii, and borders) that conform to the ASDS.

3.	Sign Posts and Bases. Use sign posts and bases of the types specified. The structural aspects of design and materials for sign supports must comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals. Do not splice sign posts.

Use Class A concrete meeting the requirements of Section 501 for overhead Sign support foundations.

Use Class B concrete for steel-reinforced roadside sign foundations meeting the requirements of Section 550. Concrete for other sign foundations may be Class W.

4.	Delineators. Use delineator assemblies that conform to the requirements shown on the Plans. Fabricate flexible delineators using ASTM 4956 Type III, IV, V, IX or XI retroreflective sheeting.

5.	Reflective Sheeting Warranty. Supply manufacturer’s warranty for reflective sheeting, including retention of fluorescent yellow-green (measured in accordance with ASTM E2301) for ten years according to the following criteria:

a.	Minimum Fluorescent Luminance Factor	YF: 20%

b.	Minimum Total Luminance Factor	YT: 35%

The warranty shall stipulate that: If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication of the sign, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness. If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

CONSTRUCTION REQUIREMENTS.

615-3.01 GENERAL.

1.	Place posts in excavated holes to the depth shown on the Alaska Standard Plans.

2.	Backfill the space around the posts and foundations placed in holes to finish ground with selected earth or sand, free of rocks or deleterious material. Place backfill in layers approximately 6 to 12 inches thick and thoroughly compact it.

3.	Dispose of surplus excavated material neatly along the adjacent roadway as directed.4.	Install flexible delineator posts according to the manufacturer's recommendations.

5.	Attach sign panels to posts, electroliers, traffic signal standards, bridge rails, piers, and abutments using the types and sizes of fastening hardware shown on the Plans.

6.	If using existing signs and mileposts that are removed and relocated, ensure they conform to the details shown on the Plans or as directed.

CR615-123121/CFHWY00599

7.	Sign Salvage:

Notify the Engineer 5 working days prior to beginning sign salvage activities. The Engineer will physically identify those signs to salvage.

- Property of the State.  When 615-3.01 7a identifies a maintenance station to receive sign salvage, the signs (sign panels, posts, and hardware) are the property of the State.

Protect all items from damage during salvaging and delivery. For each sign so designated, disconnect sign post from panel and group the panels together. Group posts together with their hardware. Deliver posts, and hardware to the State Maintenance Station noted in these Special Provisions. Do not deliver salvaged materials until inspected and approved by the Engineer. Replace any items damaged by you at no additional cost to the Department.

Deliver select salvaged sign panels identified in the Plans and all salvaged posts, and hardware to the State Maintenance and Operations Station, located at:

289 Inner Springer Loop Road, Palmer, AK.

b.	Property of the Contractor. Salvaged sign panels not identified in the Plans for delivery to the State Maintenance and Operations Station are the property of the Contractor.

Remove project signs and/or parts designated for salvage, off the project site.

CR615/CFHWY00599

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise). If abandoned in place, remove the tops of the foundations, reinforcing steel, anchor bolts, and conduits to a depth of not less than 12 inches below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation considered as one unit.

Dispose of sign salvage not wanted by the Contractor, not used in the project, and not accepted by the Local Maintenance and Operations Station as required by Federal, State, and Municipal environmental regulations.

8.	All materials and finished signs are subject to inspection and acceptance in place.

a.	Surfaces exposed to weathering must be free of defects in the coating that impair serviceability or detract from general appearance or color match.

b.	Finished signs must be clean and have no chatter marks, burrs, sharp edges, loose rivets, delaminated reflective sheeting, or aluminum marks. Do not make repairs to the face sheet.

9.	Install the various breakaway assemblies according to the manufacturer’s written instructions. Meet MASH crashworthiness requirement for breakaway hardware, unless approved otherwise by the Engineer.

10.	Secure the anchors in templates and install them according to the manufacturer’s written instructions.

11.	Finish the foundation according to these tolerances:

a.	Do not use more than two shims per coupling.

b.	Do not use more than three shims to plumb each post.

Remove and replace all foundations requiring more than three shims to plumb a post without extra compensation.

12.	Construct the top of any foundation located on a slope so that the finished slope passes through the top center of the foundation. Grade the area 24 inches up and down slope of the foundation edge so that no portion of the foundation projects above the surrounding slope and water will drain away from the foundation.

13.	Attach a label to the back of all standard signs in the lower right corner. Make the label at least 15 square inches and show the year the sign was purchased from the manufacturer. Show the last two digits of the year in clear and bold numbers. Make the label from ASTM D4956 Type I or brighter retroreflective sheeting. Use background and legend colors meeting Table 615-1.

TABLE 615-1

DECAL COLORS

| YEAR | BACKGROUND COLOR | LEGEND COLOR |
| --- | --- | --- |
| XXX1 | Yellow | Black |
| XXX2 | Red | White |
| XXX3 | Blue | White |
| XXX4 | Green | White |
| XXX5 | Brown | White |
| XXX6 | Orange | Black |
| XXX7 | Black | White |
| XXX8 | White | Black |
| XXX9 | Purple | White |
| XXX0 | Strong Yellow-Green | Black |
| Central values and tolerance limits for each color, as referenced in the MUTCD, are available from the Federal Highway Administration, (HHS-30), 400 7th St. SW, Washington, D.C. 20590 |  |  |

615-3.02 SIGN PLACEMENT AND INSTALLATION. The location and type of installation will be as shown on the Plans. Sign locations are approximate and subject to field adjustment by the Engineer.

Do not allow the top of the embedded steel tube to extend more than 2 inches above the surrounding ground and concrete foundation.

On all signs, install 2-inch diameter wind washers, colored to match the sign face, between the fastener head and the sign. Use rust-resistant washers fabricated from a material equal in strength to the sign blank.

Mount signs on mast arms level.

Bring existing signs that are to remain, into conformance with Standard Drawing S-05. Keep existing signs in service until they are no longer needed.

615-4.01 METHOD OF MEASUREMENT.

Standard Signs and Object Markers. By the total area of legend-bearing sign panel erected in place. No deductions in quantity for corner rounding will be made. Nominal dimensions for sign sizes indicated on the Plans will be used to calculate sign pay quantities. Octagons and round signs will be measured as rectangles. Only one side of each double-faced sign will be measured for payment.

Removal and Relocation. By each, complete in place.

Delineators. By each, complete in place.  A single delineator consists of one post equipped with three reflectors.

Salvage Sign. By each complete sign delivered in acceptable condition.

615-5.01 BASIS OF PAYMENT. Sign posts, bases, and mounting hardware are subsidiary.

When Items 615.0002.____, 615.0003.____, or 615.0006.____ do not appear on the bid schedule, this work is subsidiary.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 615.0001.____ | Standard Sign | SF |
| 615.0002.____ | Remove and Relocate Sign | Each |
| 615.0003.____ | Remove and Relocate Milepost | Each |
| 615.0004.____ | Delineator, Rigid | Each |
| 615.0005.____ | Delineator, Flexible | Each |
| 615.0006.____ | Salvage Sign | Each |
| 615.0007.____ | Salvage and Dispose Sign | Each |

CR615-123121

Special Provisions

Replace Section 618 with the following:

SECTION 618
SEEDING

618-1.01 DESCRIPTION. Establish a healthy living perennial stand of grass or other vegetative living groundcover by seeding. Maintain the living cover for the term of the Contract.

CR618-050118R/CFHWY00599

618-2.01 MATERIALS. Use materials that conform to the following:

Water	Subsection 712-2.01

Seed	Section 724 (Grass Seed)

Fertilizer	Section 725

Topsoil	Section 726

Soil Stabilization	Section 619

Soil Stabilization Material	Section 727

TABLE 618-1

GRASS SEED MIX (A), SOIL STABILIZER, AND FERTILIZER APPLICATION RATES

| Materials | Ingredients | Application Rate (per MSFc) |
| --- | --- | --- |
| Grass Seed Mix a, b | Nortan – Tufted Hairgrass Arctred – Red Fescue Wainwright - Slender Wheatgrass Annual Ryegrass | 0.60 lbs. 0.45 lbs. 0.37 lbs. 0.08 lbs. Total = 1.50 lbs. |
| Soil Stabilizer. |  |  |
| Slope ≤ 3:1 | Mulch | 46 lbs. |
| Slope >3:1 | Mulch with tackifier | 45-58 lbs. |
| Fertilizer | 20-20-10 | 12 lbs. |

TABLE 618-2

GRASS SEED MIX (B), SOIL STABILIZER, AND FERTILIZER APPLICATION RATES

| Materials | Ingredients | Application Rate (per MSFc) |
| --- | --- | --- |
| Grass Seed Mix a, b | Nortan – Tufted Hairgrass Boreal – Red Fescue Sourdough - Bluejoint Reedgrass Beckmannia - American Sloughgrass Annual Ryegrass | 0.60 lbs. 0.30 lbs 0.23 lbs. 0.30 lbs. 0.07 lbs. Total = 1.50 lbs. |
| Soil Stabilizer. |  |  |
| Slope ≤ 3:1 | Mulch | 46 lbs. |
| Slope >3:1 | Mulch with tackifier | 45-58 lbs. |
| Fertilizer | 10-10-10-8 | 7 lbs. |

Table 618-1 and 618-2 Notes:

a. 	Do not remove the tags from seed bags.

b.	Submit an alternate seed mix when the specified seed is not commercially available. Provide a letter confirming the specified seed is not available. Include an agronomist certified seed mix design, including application rate, suited to the project site.

c.	MSF = 1000 ft2.

CFHWY00599

CONSTRUCTION REQUIREMENTS

618-3.01 SURFACE PREPARATION. Remove ruts, holes, humps and other irregularities from the surface. Clear stones four inches in diameter and larger, weeds, plant growth, sticks, stumps, and other debris that will interfere with the application of stabilization material, topsoil, the seeding operation, growth of vegetative groundcover, and subsequent maintenance of the cover.

Smooth the slopes for a uniform appearance and round the top and bottom of the slopes to facilitate tracking or raking. Do not disrupt drainage flow lines.

Evenly place stabilization material and or topsoil when specified.

Prepare the surface material by grooving the material in a uniform pattern that is perpendicular to the fall of the slope. Use one or more of the following grooving methods with associated equipment before the application of seed:

1.	Manual raking with landscaping rake;

2.	Mechanical track walking with track equipment; or

3.	Mechanical raking with a scarifying slope board. Form one-inch wide grooves spaced no more than six inches apart.

618-3.02 SEEDING SEASON. Seed disturbed areas after permanent cessation of ground disturbing activities in that area, within the period specified in the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) Construction General Permit (CGP) for Alaska, Section 4.5 Soil Stabilization, and Section 641 Erosion, Sediment, and Pollution Control.

Do not seed during windy conditions, when climatic conditions or ground conditions would hinder placement or proper growth.

Seed between May 15 and August 15.

618-3.03 APPLICATION. Seed, seeding, reseeding includes the application of seed, fertilizer, and stabilization material.

CR618-050118R/CFHWY00599

Apply Seed Mix (B) at the basin locations within the limits shown in the plans. Apply Seed Mix (A) on all other areas requiring seeding.

CFHWY00599

If the seed mix, fertilizer and stabilization material are not included in the Plans or Specifications, including their application rates, use the recommendations of the ADNR and the Revegetation Manual for Alaska.

Do not seed areas of bedrock and plant beds.

Use any of the following methods:

1.	Hydraulic Method

Apply seed and stabilization material in one application when using the hydraulic method.  Apply fertilizer with the hydraulic method.  Include the fertilizer with the seed and stabilization material or apply separately.

a.	Furnish and place a slurry made of seed, fertilizer, water, and other materials.

b.	Use hydraulic seeding equipment that will maintain a continuous agitation and apply a homogeneous mixture through a spray nozzle. The pump must produce enough pressure to maintain a continuous, nonfluctuating spray that will reach the extremities of the seeding area with the pump unit located on the roadbed. Provide enough hose to reach areas not practical to seed from the nozzle unit situated on the roadbed.

c.	If mulch material is required, it may be added to the water slurry in the hydraulic seeder after adding the proportionate amounts of seed and fertilizer. Add seed to the slurry mixture no more than 30 minutes before application.

d.	Mix the slurry and apply it evenly.

2.	Dry Methods

a.	Use mechanical spreaders, seed drills, landscape seeders, aircraft, cultipacker seeders, fertilizer spreaders, or other approved mechanical spreading equipment.

b.	Spread fertilizer separately at the specified rate.

618-3.04 MAINTENANCE.  Maintenance includes but is not limited to the following:

1.	Protecting seeded areas against traffic by approved warning signs or barricades and against erosion.

2.	Repairing surfaces gullied or otherwise damaged following seeding.  Fill erosion gullies 4 inches deep and greater filling the gully to surrounding grade including the portions less than 4 inches deep.  Apply and prepare the stabilization material and or topsoil for seeding.  Seed repaired area.  Refer to Subsections 618-3.01 & 3.03.

3.	Reseeding areas not showing evidence of satisfactory growth within 3 weeks of seeding and after repairs are complete.  Reseed bare patches of soil more than 10 square feet in area.  Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.

4.	Watering seeded areas for healthy growth of vegetative cover.  Adjust the amount of water when directed.

618-3.05 ACCEPTANCE. The vegetative groundcover will be inspected considering each station and each side of the road a separate area.  Acceptance of the cover requires a minimum of 70% cover density in the inspection area, gullies repaired and reseeded, and no bare patches of soil more than 10 square feet in area.

Repair/reseed areas that are not accepted.

618-3.06 PERIOD OF ESTABLISHMENT. For each area accepted, the establishment period extends one complete growing season following the date of Project Completion, Subsection 105-1.15.  Employ all possible means to preserve/maintain the new vegetative groundcover in a healthy and vigorous condition to ensure successful establishment.  Maintain the vegetative cover, according to Subsection 618-3.04, to not less than the requirements for acceptance, Subsection 618-3.05.

618-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Seeding by the Acre. By the area of ground surface acceptably seeded and maintained.

Seeding by the Pound.  By the weight of dry seed acceptably seeded and maintained.

Water for Seeding. If weighed, a conversion factor of 8.34 pounds per gallon will be used to convert weights to gallons.

MGAL equals 1000 gallons.

618-5.01 BASIS OF PAYMENT.

1.	Pay Items 618.0001.____ and .0002.____ Seeding. Payment is for healthy established vegetative groundcover through the establishment period.

a.	The initial surface preparation, seed, fertilizer, mulch when applied hydraulically, their application, and the water for hydraulic application are subsidiary.

b.	Maintenance fill, stabilization material, topsoil, surface preparation, seed, fertilizer, mulch when applied hydraulically, and the water required for hydraulic application are subsidiary.

2.	Pay Item 618.0003.____ Water for Seeding. Payment is for water applied for growth of vegetative groundcover through the establishment period. Water for hydraulic application of materials is subsidiary to Pay Items 618.0001.____ and .0002.____.

Except for maintenance, stabilization material is paid under Section 619 and topsoil under Section 620.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 618.0001.____ | Seeding | Acre |
| 618.0002.____ | Seeding | LB |
| 618.0003.____ | Water for Seeding | MGAL |

CR618-050118R

Include: Section 619/CR619 Soil Stabilization; Section 724/CR724.1 Seed; 726/CR726.1 Topsoil and 727/CR727 Soil Stabilization Materials when including CR618.

Section 618 is not the place to specify soil stabilization material or topsoil.  Include topsoil, and soil stabilization material, general or specific, in the Estimate of Quantities, the Plans and the Bid Schedule.  Example:  "Soil Stabilization Material" in the Plans would be paid by Section 641; "Compost" or "Topsoil" in the Plans would be paid by Section 619, 620 or might be subsidiary to 618, etc.

Special Provision

Replace Section 619 with the following:

- SECTION 619
SOIL STABILIZATION

619-1.01 DESCRIPTION.  Furnish, install, and maintain materials to stabilize the soil.  Control erosion, sediment, and pollution.

619-1.02 RELATED SECTIONS, REFERENCE ORGANIZATIONS, AND STANDARD DOCUMENTS.

1.	Alaska Department of Transportation and Public Facilities (ADOT&PF):

Standard Specifications for Highway Construction

Seeding	Section 618

Topsoil	Section 620

Planting Trees and Shrubs	Section 621

Silt Fence	Section 633

Erosion, Sediment, and Pollution Control	Section 641

Soil Stabilization Material	Section 727

2.	American Association of State Highway and Transportation Officials (AASHTO)

Standard Practice for:

	Compost for Erosion/Sediment Control (Filter Berms and Filter Socks)	R 51

	Compost for Erosion/Sediment Control (Compost Blankets)	R 52

3.	United States Composting Council (USCC)

	Testing Methods for the Examination of Compost and Composting (TMECC)

	Seal of Testing Assurance Program (STA) documents

4.	Erosion Control Technology Council (ECTC)

	Hydraulic Erosion Control Products (HECPs) Specification Chart

Table 1, Performance Chart for Standard HECPs

	Rolled Erosion Control Products (RECPs) Specification Chart

Table 1, Rolled Erosion Control - Temporary

Table 2, Rolled Erosion Control - Permanent

5.	National Transportation Product Evaluation Program (NTPEP)

	Testing and Evaluation of Products Materials and/or Devices

6.	Texas DOT/Texas Transportation Institute (TTI) Hydraulics and Erosion Control Laboratory

619-1.03 SUBMITTALS.  Submit stabilization and erosion, sediment and pollution control performance testing results with certifications for each material, Section 619-2.01 Materials.  Submit a sample of each material to the Engineer 7 days before the scheduled installation.

1)	Test compost, all applications, no more than 90 days before installation.

2)	At a minimum, certificate will include the name of the manufacturer, product name, style number or similar, chemical composition of the material, the fibers, netting, yarn and similar and the weed free status of the material.

3)	Organic materials shall be accompanied with all applicable health certificates and permits.

4)	Furnish a Material Safety Data Sheet (MSDS) that demonstrates the product is not harmful to plants, animals, and aquatic life.

619-2.01 MATERIALS.  Select stabilization materials, individually or a combination of, matched to the project applications/conditions (sheet flow, concentrated flow, slope, length of slope, access, etc.) providing performance and functional longevity meeting the most restrictive requirements of the Construction General Permit (CGP), the approved Storm Water Pollution Prevention Plan (SWPPP) and Section 641 Erosion, Sediment and Pollution Control.

1)	Mulch	Subsection 727-2.01

	Dry Erosion Control, Stabilization Products

	Hydraulic Erosion Control Products (HECPs)

2)	Matting	Subsection 727-2.02

	Rolled Erosion Control Products (RECPs)

3)	Sediment Retention Fiber Rolls (SRFRs)	Subsection 727-2.03

	Filter Socks

	Compost Socks

	Coir Logs

4)	Compost	Subsection 727-2.04

5)	Tackifier	Subsection 727-2.05

6)	Soil Binders (Polyacrylamide (PAM))	Subsection 727-2.06

7)	Geotextile-Encased Check Dams and Sediment Barriers	Subsection 727-2.07

8)	Sandbag	Subsection 727-2.08

9)	Manufactured Inlet Protection System	Subsection 727-2.09

10)	Clear Plastic Covering	Subsection 727-2.10

11)	Staples	Subsection 727-2.11

12)	Other stabilization materials submitted to and approved by the Engineer.

Include on the packaging the manufacturer's name, the content, the air dry-weight and the guaranteed chemical analysis of the contents.  Ship and deliver to the site in the original, unopened containers.

CONSTRUCTION REQUIREMENTS

619-3.01 GENERAL.  Stabilization may include individual or a combination of materials, including but not limited to temporary seeding, mulch, tackifier, staples, matting, stabilizing emulsions, soil binders, dustless sweeping, dust palliatives, and others.

1.	Material Storage and Protection.  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment including but not limited to:

	Precipitation

	Extended ultraviolet radiant including sunlight

	Chemicals that are strong acids or other

	Flames and welding sparks

	Excess temperatures

	Other environmental conditions that may damage the materials

2.	Fabrication.

a.	Sandbags.  Sand bags shall measure 15 inches by 30 inches.  Place approximately 1.0 cubic foot of select Material, Type B, in each sandbag sack.  Close the open end of the sandbag as recommended by the fabric manufacturer.

619-3.02 SURFACE PREPARATION.  Clear all areas to be stabilized of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the stabilization operation, growth of cover (where vegetative cover is part of the stabilization operation) or subsequent maintenance of the vegetative-covered area(s).

Smooth the surface of the area(s) to be stabilized; make the areas reasonably free of ruts, holes, and humps; trackwalk if required by the manufacturer; apply the stabilization material to each area.

If specified, apply topsoil to the area to be stabilized before application of the stabilizing material. Section 618 and 620.

619-3.03 APPLICATION.  Apply stabilization material, including rate of application, according to the specifications.  If not specified, apply according to the manufacturer's requirements.  Where manufacturer requirements conflict with the specification, except where the Engineer directs otherwise, apply the material according to the requirements of the manufacturer.

If seeding is specified, except where seed is included in the stabilization material, complete the application of stabilization materials within 24 hours after seed is placed.

Do not use vehicles or equipment which cause rutting or displacement of the subgrade or topsoil.

1.	Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Prepare surface and place seed as noted under Subsection 619-3.02 Surface Preparation and Section 618 Seeding.  Confirm application of temporary seeding with the Engineer.

2.	Tacking Agents - Tackifiers. Apply tacking agents according to the manufacturer's installation instructions matched to the application providing functional longevity, erosion control effectiveness, and vegetative establishment.

3.	Soil Binders.  Apply soil binders according to the manufacturer's installation instructions.

a.	Using Polyacrylamide (PAM) and PAM with Short-Term Mulch:

Apply PAM on bare soils.

Apply PAM and PAM with short-term mulch only where sediment control is in place and complete.

Do not apply PAM and PAM with short-term mulch on saturated ground during rainfall.

b.	Using Moderate-Term Mulch:

Apply moderate-term mulch according to manufacturer's installation instructions.  If the curing period to achieve maximum performance is greater than the time period before precipitation is predicted, or the soil is saturated, do not apply the moderate-term mulch except as approved by the Engineer.

c.	Using Long-Term Mulch:

Apply long-term mulch according to the manufactures installation instructions.

4.	Erosion Control Blankets (ECBs).  Select blankets, as specified by the manufacturer, to match the slope; and installed according to the manufacturer's instructions rolled out on well prepared soils to assure intimate contact and anchored with staples, stakes and or anchor trenches.  Temporary erosion control blankets with 60 percent or greater open area may be installed prior to seeding.  Place blankets with less than 60 percent open area immediately after the seeding operation.

Staple matting/ECBs as recommended by the manufacturer for the application.

5.	Compost Blankets.  Construct compost blankets according to latest AASHTO R 52 and as specified.  Use coarse compost and place over bare soil a blanket of 2 inch minimum thickness, except as otherwise specified.  Apply material either by hand spreading and or pneumatically.  Compost will have no free water visible or produce dust when handled.  Place compost before seeding or mix seed with compost.

6.	Check Dams.  Place check dams as soon as possible and practicable or when and where if directed by the Engineer.  Place the check dams perpendicular to channels and construct of a height sufficient to maximize detention while keeping the water in the channel.  Place and install check dams according to the Plans and anchor to maintain in effective position.

a.	Sandbag.  Place the initial row in tight contact with the ditchline for the length of the dam.  Place each following row centered across the joint between the bags of the lift/row below.

7.	Stabilized Construction Entrance.

Temporary stabilized construction entrance shall be constructed according to the Plans, prior to beginning any clearing, grubbing, earthwork, or excavation.

When the stabilized entrance no longer prevents track out of sediment or debris, the Contractor shall either rehabilitate the existing entrance to original condition, or construct a new entrance.

When the Plans require a tire wash in conjunction with the stabilized entrance, the Contractor shall include details for the tire wash and the method for containing and treating the sediment-laden runoff as part of the SWPPP.  All vehicles leaving the site shall stop and wash sediment from their tires.

8.	Sediment Control Barriers.  Sediment control barriers shall be installed according to the Plans or manufacturer's recommendations in the areas of clearing, grubbing, earthwork, or drainage prior to starting those activities.

a.	Sandbag.  Place the initial row in tight contact with the surface perpendicular to the slope.  Place each following row centered across the joint between the bags of the lift/row below.

b.	Sediment Retention Fiber Rolls.

c.	Silt Fence.

d.	Compost Berm.  Construct compost berms according to latest AASHTO R 51.  Use coarse compost.

9.	Turf Reinforcement Mats.  According to manufacturer's installation instructions.

619-3.04 MAINTENANCE.  Maintain stabilized areas in a satisfactory condition for the term of the Contract.  Inspect as required by the CGP, approved SWPPP, and Section 641 Erosion, Sediment and Pollution Control and correct any deficiencies immediately.  Remove and dispose of temporary measures, including trapped sediment and contaminants, off project at approved locations.  Materials manufactured as degradable may be left in place when approved by the Engineer.

Maintenance includes but is not limited to:

a.	Protecting stabilized areas against traffic by approved warning signs or barricades.

b.	Repairing surfaces gullied or otherwise damaged following application of stabilization material(s).

Where seeding is included as a part of the soil stabilization:

c.	Reseeding, as required by Section 618 Seeding.  Reapply the stabilization materials correcting the problems of the initial application.

d.	Watering, where vegetative growth is part of the soil stabilization, according to Section 618 Seeding.

The Engineer will perform inspection of the stabilization as required in the CGP, Section 641, and the SWPPP.  Make repairs as required by same and as directed.

619-4.01 METHOD OF MEASUREMENT.  Section 109, measured on the slope of the ground surface.

619-5.01 BASIS OF PAYMENT.  Water, maintenance, repair, removal, and disposal of temporary stabilization materials are subsidiary.

Seeding is paid under Section 618 Pay Items, topsoil under Section 620 Pay Items, silt fence under Section 633 Pay Items and temporary erosion, sediment, and pollution control under 641 Pay Items.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 619.0001.____ | Mulching | SY |
| 619.0002.____ | Matting | SY |
| 619.2001.____ | Compost | SY |
| 619.2002.____ | Turf Reinforcement Mat | SY |
| 619.2003.____ | Sediment Retention Fiber Rolls | LF |
| 619.2004.____ | Check Dam and Sediment Barrier (-Geotextile) | LF |
| 619.2005.____ | Check Dam | LF |
| 619.2006.____ | Sediment Barrier | LF |
| 619.2007.____ | Compost Berm | LF |
| 619.2008.____ | Sandbags | Each |
| 619.2009.____ | Manufactured Inlet Protection System | Each |
| 619.2010.____ | Sandbag Inlet Protection System | Each |
| 619.2016.____ | Mulch | SY |

CR619-050118R

Special Provision

Replace Section 626 with:

SECTION 626
SANITARY SEWER SYSTEM

626-1.01 DESCRIPTION.  Construct or reconstruct sanitary sewers and appurtenances to conform to the Plans. This Section refers to conduit used for sanitary sewers as “sewer conduit.”  The Work covered by these Specifications consists of providing all plant, labor, equipment, supplies, material, transportation, handling and storage, and performing all operations necessary to complete the construction for pipe laying, jointing, and testing of sanitary sewers.  Construction is to be completed according to the included details and these special provisions.

This section covers the work necessary for furnishing and installing the insulated and un-insulated polyethylene sewer service piping, heat trace channel, fittings, and heat tracing, complete, as shown on the Plans.  The pipe system furnished shall be complete with all adapters, fittings, pipe plugs, jointing materials, accessories, and all other necessary appurtenances needed for a complete installation.

The Contractor, by providing a Bid Proposal and entering a Contract with DOT&PF has found that the access, easements, rights-of-way, and other work areas designated in the Plans are adequate to perform the work and/or the Contractor has secured additional work areas at their own expense that is included in the Bid Proposal to complete the work.

Additional areas secured by the Contractor from parties not associated with the Contract are to be memorialized in the form of a right of entry agreement between the Contractor and party having authority to enter an agreement for the work area.  A copy of the right of entry agreement is to be provided to the DOT&PF.  The right of entry agreement is to extend the indemnification requirements found in the Contract to Contractor obtained work areas.

The Contractor is to restore the area of Work to preconstruction conditions or better except where shown different on the Plans or required by the Contract Documents.  Where preconstruction conditions cannot be obtained such as items that require growth to obtain height, thickness, and other prized attributes then they are to be replaced with standard nursery stock plant material of the same species and type that will grow back to preconstruction conditions and maintained in accordance with the Contract.  The Contractor is to secure written approval by the Engineer for replacement material that does not match preconstruction conditions.

626-2.01 MATERIALS.  Use materials that conform to the following, and/or as modified by additional stated requirements in this sub section:

Bedding and Backfill 		Subsection 204-2.01

PVC Pipe 			Subsection 706-2.05

Polypropylene Pipe 		Subsection 706-2.09

HDPE Pipe 			Subsection 706-2.08

Ductile Iron Pipe 		Subsection 707-2.05

- Pipe Bedding.  All sewer conduit bedding shall be Class “E” as defined by the following:

TABLE 627-1

Class “E” Pipe Bedding

| Sieve Size | Cumulative Percent Passing by Weight |
| --- | --- |
| ½-inch | 100 |
| 3/8” | 80-100 |
| #4 | 20-75 |
| #8 | 12-60 |
| #30 | 2-30 |
| #200 | 0-6 |

- Ductile Iron Pipe (DIP).  All DIP sewer conduit is to conform to ASTM A 746 (AWWA C 151) with a cement mortar lining conforming to AWWA C-104.  Cast and ductile iron fittings and pipe bells are to conform to AWWA C110 or AWWA C-153.  Rubber gasket joints for ductile iron pipe fittings are to conform to AWWA C-111.  Polyethylene encasement material for pipe is to be eight (8) mils thick and conform to AWWA C105.  Polyethylene encasement is to include a VBio film system incorporating corrosion control additives and MIC control additives as provided by US Pipe or approved equal.

- HDPE Pipe.  High Density Polyethylene Pipe (HDPE) and fittings are to be manufactured in accordance with AWWA C906. In addition to the requirements of AWWA C906, HDPE is to be manufactured from PE4710 polyethylene compounds that meet or exceed ASTM D3350 Cell Classification 445574.  All HDPE pipe and fittings must be certified by the NSF for potable water service.  HDPE pipe and fitting material compound are to contain color and ultraviolet (UV) stabilizer meeting or exceeding the requirements of Code C per ASTM D3350.  All fittings will have pressure class ratings not less than the pressure class rating of the pipe to which they are joined.  The pipe is to be homogeneous throughout and free of visible cracks, holes, foreign inclusions or other injurious defects.  It is to be uniform in color, opacity, density and other physical properties.  Butt fusion of the pipe and fittings is to be performed in accordance with the pipe manufacturer's recommendations as to equipment and technique.  The fusion operation is to be performed by an individual who has demonstrated the ability to fuse polyethylene pipe in the manner recommended by the pipe supplier.

The Contractor shall inspect HDPE piping for damage immediately prior to joining.  Damage is defined as cuts or gouges exceeding 10% of the pipe wall thickness, kinked pipe sections, pipe sections flattened to more than 5% of the original diameter, or any abrasion or cutting of the inside surface of the piping. Damage portions of piping shall be cut out and discarded.

The Contractor shall ensure that each joint is fused at the temperature and pressure recommended by the pipe manufacturer in order to achieve the maximum pressure rating for that joint.  All butt-fused joints and fabricated fittings shall be documented by a computer data logger that records pressure and temperature applied at each at each fused joint, along with the date and time the joint was fused.  Computer printouts and electronic data for each fitting shall be submitted to the Engineer prior to installation of the fitting.  All fittings shall be labeled with a unique identifier that corresponds with the fusion computer printouts for each fitting.

The use of electro-fusion couplings to join HDPE piping may be allowed upon written approval by the Engineer.  Electro-fusion couplings shall comply with ASTM F-1055.  The Contractor shall as-built the exact location of any installed electrofusion couplings.

The handling of joined pipe shall be in such a manner that the pipe is not damaged.  Ropes, fabric, or rubber protected slings, or straps shall be used when handling pipe.  Chains, cables, or hooks, inserted into the pipe ends shall not be allowed.  Two slings spread apart shall be used for lifting each length of pipe. Slings for handling the pipe shall not be positioned at butt-fused joints.

A tracer wire shall be installed above all HDPE sewer mains in accordance with the manufacturer’s recommendations.  Tracer wire shall be suitable for direct bury applications and shall be 10 AWG with 30-mil HDPE jacket (jacket color blue), capable of a 575-pound average tensile break load.  Tracer wire shall be Copperhead Industries reinforced tracer wire or approved equal.  Trace wire shall be installed in continuous lengths with no splices.  Terminate each end of the tracer wire at ground surface next to a manhole.

- Service Pipe.  For the purpose of designating the type and grade of polyethylene pipe, heat tracing and insulation desired, a manufacturer’s name and list or figure number may be given in the following specifications.  Polyethylene pipe, heat tracing and insulation of equal quality by other manufacturers which conform to these specifications may be offered for approval by the Engineer.  Compression fittings may be used to adapt the plastic pipe to threaded valves or pipe fittings in all lines less than 3 inches in diameter.  Threading of the polyethylene pipe directly will not be allowed.

Compression fittings shall incorporate stainless steel stiffeners in all applications.  Fittings shall be Mueller 110 Compression Fittings for Plastic Pipe, Ford Meter Box Company, Pack Joint Coupling or Insert Fitting for Polyethylene Pipe with stainless steel clamps (2 per insert), Emco Successor Compression Fitting or equal.

The Contractor shall provide and install the pipe insulation and heat tracing system complete and operable.  Submittals and shop drawings shall include design details for installation of test and junction boxes in reaches where valve vault spacing exceeds the manufacturer’s recommended distance between heat tracing terminals.  Before installation, the Contractor shall provide a system plan showing locations of required additional terminal points with details of heat trace mounting, termination, and terminal box mounting for review and approval by the Engineer.

Inner Core Pipe

The pipe shall conform to the same specification as the uninsulated pipe.

Insulation

The insulation installed between the inner core and outer jacket shall be a low density rigid closed-cell polyurethane foam with a minimum thickness of 1.90 inches.  For 2-inch diameter inner core, 1.75 inches for 3-inch diameter inner core, and 2.0 inches for all other insulated pipe. It shall be applied and cured in strict accordance with the manufacturer’s recommendations and good commercial practices such that the resulting cellular insulation completely fills the annular space between inner pipe and outer jacket.  The insulation shall be free of defects affecting its intended use.  The contractor shall provide manufacturer’s certified test results for voids.  The exterior of the inner core pipe shall be prepared by shot blasting, or other approved method, to a maximum depth of 0.002 inches, to ensure adhesion of the foam insulation to the pipe.  The polyurethane foam shall be in accordance with the requirements of ASTM D 2341 for insulation sample conditioning, test temperature, and relative humidity conditions.  Other requirements shall be as follows:

| Core Density Range | 2.5 to 3.5 lbs/ft3 | ASTM D 1622 |
| --- | --- | --- |
| Minimum Compressive Strength | 35 psi | ASTM D 1621 |
| Minimum Closed Cell | 90% Content (Porosity) | ASTM D 2856 |
| Maximum Water Absorption | 0.05 lbs/ft2 | ASTM D 2842 |
| Maximum Water Vapor | 5.0 lbs/ft2 Permeability | ASTM C 355 |
| Dimensional Stability (Maximum Linear Change) | 1% at – 20°F | ASTM D 2126 |
| Dimensional Stability (Maximum Linear Change) | 3% at +100°F | ASTM D 2126 |
| Maximum K-Factor as Produced | 0.13 btu-inch hr ft2 °F | ASTM C 518 or C 177 |
| Maximum K-Factor as Received by Owner | 0.15 btu-inch hr ft2 °F | ASTM C 518 or C 177 |

Exposed faces of polyurethane foam at pipe ends shall be coated to protect against physical abuse and ultra-violet attack during shipping and storage and against water intrusion in service.  The coating shall be an asphaltic based sealant, specifically formulated by the manufacturer for direct application over urethane foam insulation and for long-term service and retained flexibility over extended periods of exposure to sunlight, harsh weather, and salt water spray.  It shall be applied and cured in strict accordance with the manufacturer’s recommendations and good commercial practice such that the finished product is free of defects affecting its intended purpose.  The coating shall be capable of field application with a brush for touch-up shipping damage and recoating field cut piping.  A minimum of 5 gallons shall be provided with each 5,000 linear feet of pipe supplied.

Heat Trace Channel

A heat trace channel shall be provided on insulated pipe. The channel shall be applied longitudinally on the exterior of the core pipe.  It shall be taped with 1-inch (minimum) wide adhesive tape longitudinally along both seams where the channel meets the pipe and circumferentially to hold the channel in place as required.  The maximum lateral displacement of the channel along the length of the pipe shall be ¼ of the nominal pipe diameter, but in no case greater than 1-inch.  It is essential that the entire length of the channel be free from kinked, squashed, or any other kind of deformity and that there be no obstruction or ridges anywhere along the length.  The channel shall extend 1-inch (minimum) beyond the insulation cutback point.  A method shall be provided for easy removal and replacement of heat tracing for service connections from the pumping vault end only.

Outer Jacket Material

The pipe shall be factory jacketed with a continuous, seamless, single layer, extruded high-density polyethylene jacket of minimum thickness of 0.060-inches.  The jacket shall be bonded to the foam insulation by using a layer of elastomeric sealant a minimum of 0.010 inches thick.

The outer jacket shall exhibit the following properties and characteristics:

| Color | Black |  |
| --- | --- | --- |
| Carbon Black Content | 2.0% | ASTM D 1603 |
| Minimum Base Density | 0.952 gm/cm3 (compounded) | ASTM D 792 |
| Minimum Tensile Yield | 3,200 psi | ASTM D 638 |
| Minimum Elongation | 400% | ASTM D 638 |
| Minimum Hardness, Shored | 45 | ASTM 1706 |
| Minimum Izod Impact | 1.5 ft-lbs/inch | ASTM D 256 |
| Minimum Brittleness | -94°F | ASTM D 746 |
| Vicat Softening Point | 248°F | ASTM D 1525 |

The outer jacket shall be marked at minimum 6 feet intervals in a permanent manner to indicate manufacturer, pipe size, pressure rating, nominal insulation thickness, and the words “CAUTION: ELECTRICALLY HEAT TRACED”.  Each end of each joint of insulated pipe shall be covered with an end cap.  The end cap shall prevent water, dirt, or foreign objects from entering the heat tracing channel or the core pipe.

Joints

Finished ends of pre-insulated pipe shall have the insulation and outer jacket cutback for each length of pipe to leave approximately 8-inches of bare polyethylene pipe.  The ends of the cutback portion shall be coated as specified in Paragraph INSULATION.  The insulation material for each pipe joint shall consist of two split insulation halves (half shells) with outer jacket, precut to a minimum length of 16 inches and shall be provided for each length of pipe.  The insulation shall contain an appropriate groove for the heat trace channel.  The Contractor shall supply cross linked polyolefin heat shrink sleeves and tape with heat sensitive color indicator, sized to overlap the preformed insulation ends a minimum of 3 inches and to form a seal when shrunk with heat application; Raychem Dual-Seal, or approved equal.  Heat shrink tape shall be of the same material as the sleeves, and in widths recommended by the manufacturer not to be less than two inches wide.  An extra joint assembly (shrink sleeve tape and half shells) shall be provided for each 20 joints of insulated pipe furnished.

Fittings and Special Assemblies

Polyethylene fittings shall be manufactured by molding or fabrication from polyethylene using thermal butt-fusion.  The fittings shall be at least the same grade as the polyethylene inner core pipe.  Fabricated pipe fittings shall be joined to the polyethylene pipe by using flanges, butt-fused to the pipe unless otherwise specified.  The Contractor shall provide the proper bolts, back-up rings, and gaskets for the fittings.  Bolts shall be provided for the intended use.  Gaskets shall be reinforced black rubber, asbestos-rubber compound, Buna N, or red rubber.  All fabricated fittings shall be reinforced with a suitable fiberglass-reinforced- polyester (FRP) material or be of sufficient allowable working pressure design to be equal to or better than the pipe to which they are attached.  This material shall meet all applicable governing standards for reinforced polyester materials.  The thickness of the FRP material shall be based on the pipe pressure rating.  All fittings will be factory pre-insulated to a nominal thickness of 2 inches.  The exposed foam ends will be sealed as previously specified under INSULATION.  Compression fittings incorporating stainless steel stiffeners may be used to adapt the polyethylene pipe to threaded valves or pipe fittings in all lines less than 3 inches in diameter.  Threading of the polyethylene pipe directly will not be allowed. Fittings shall be Mueller 110 Compression Fittings for Plastic Pipe, Ford Meter Box Company, Pack Joint Coupling or Insert Fitting for Polyethylene Pipe with stainless steel clamps (2 per insert), Emco Successor Compression Fitting, or equal.  Polyethylene pipe and molded or fabricated fittings shall be as provided by Phillips Driscopipe, or equal.

Insulation Kits for Special Couplings

Insulation kits shall be provided for all flange assemblies, valves, and for special couplings.  Valve insulation kits shall be provided for valves as indicated on the Drawings and shall be custom tailored to the valves provided.  The Contractor shall be responsible for this coordination.

Each kit shall contain the following components.  Two form-fitting polyurethane foam halves with integral FRP jacket or approved other material for watertight seal.  Halves shall extend to cover flange connections on fittings, or other intended purpose as described in this Specification.

Appropriate stainless steel strapping and seals. Caulking / adhesive compound.

Installation instructions.

Components of the insulation kits

  - Insulation
Same as specified for pipe with 2 inches minimum over flanges.

  - Jacket
Pigmented black polyvinyl resin for fiberglass reinforced plastic of commercial grade suitable for continuous exposure to solar radiation and water.  Minimum thickness shall be 0.10-inch.  The exterior shall be coated with a gel coat suitable for sealing.

  - Caulking
The material shall be suitable for low temperature use and application.  PRC 6000, Childers CP-76 or equal.

Stainless Steel Straps and Seals – Strapping shall be ACME Steel Type 300 or equal. It shall be ½-inch wide and 0.015-inch thick. Seals shall be double notch stainless steel closed seals, ACME Type 42 or equal.

The manufacturer of the insulated and un-insulated piping system shall demonstrate a minimum of 5 years of satisfactory operating experience in cold region conditions.  The Contractor shall guarantee the piping system for a period of 2 years and will be responsible for the full cost of repairs or replacement of any supplied materials that fail during the period.

Heat Tracing

Heat tracing shall be a self-limiting 240-volt electrical heating strip of parallel circuit construction consisting of a continuous inner core of variable resistance conductive heating material between two parallel copper bus wires.  The heat tracing shall be capable of producing 5 watts per foot at a pipe temperature of 50°F.  Heat tracing shall be equal to Chemelex Auto-Trace, 5 BTV2-CR, with metallic braid and protective outer jacket or equal.  Heat tracing cable shall have a minimum rating, according to Table 500-2(6) of the National Electric Code of T6.  Under no circumstance shall the heating cable produce sheath temperatures in excess of the temperature limitations of the polyethylene pipe or heat-tracing channel, or damage the empty pipe by excessive heating.  The Contractor shall provide certification of compatibility of the heat tracing and pipe from the manufacturers.  Heat tracing cable shall have an extruded outer jacket capable of passing the Canadian Standards Association Standard 22.2, No. 130-1974 TEST FOR CUT- THROUGH AND INSULATION RESISTANCE.  Heat tracing shall be furnished with all the necessary components to ensure a complete installation.  These components shall include connectors, end caps, splice kits, aluminum fastening tape, labels, pull boxes, wiring, and junction boxes as required and in accordance with Section ELECTRICAL.  Components shall be provided by the heat-tracing supplier.  Continuity and Megger tests shall be performed on heat tracing cable before and after installation (including insulation) has been completed.  Megger test shall be at 2,500 V dc from each bus wire to the sheath.  Resistance value shall be a minimum of 5-megohms per 100 ft.  The manufacturer of heat tracing cable shall demonstrate a minimum of 2 years of satisfactory operating experience in cold region conditions with self-regulating heaters.  The Contractor shall guarantee the heat tracing for a period of two years and will be responsible for the full cost of repairs or replacement of any supplied materials that fail during the period.

Detection Tape

Detection tape shall be 3 inches wide with a metallic backing.  The tape shall be imprinted with the words, CAUTION PRESSURE SEWER LINE BELOW.  Tape shall be Safety Green, “Terra Tape/D” as manufactured by Griffolyn Company, Inc., Houston, Texas; “Detectatape” by Calpico, South San Francisco, California; or equal.

- Sewer structures, manhole cones, risers, bases and grade rings.  Materials used in the construction of manholes is to conform to the requirements of ASTM C-478 (AASHTO-199), these specifications and the included details.  Concrete is to be of a suitable mixture of aggregates, cement, and water to achieve a 28-day break strength of 4,000 psi per ASTM C39. Maximum aggregate size is to be no greater than one and one-half inch (1-1/2”), one fifth (1/5) the wall thickness and 1/2 of the minimum space between reinforcement to other reinforcement or forms.  Mortar is to be composed of one (1) part cement and three (3) parts sand. Sand must conform to AASHTO Specification M-45.  Only enough water is to be added to provide plasticity in placing the mortar Cement is to conform to ASTM C150 Type II or Type III.  The water to cement ratio is not to exceed 0.53 by weight.

Grade rings are to be a minimum of three inches (3”) thick and provide a clear opening that is at least as large as what the casting provides.  Castings Frames and covers are to conform to the details, meet the requirements of ASTM A-48, and be rated Heavy Duty (H-20 loading minimum).  Gray cast iron is to have a minimum tensile strength of 30,000 pounds per square inch (PSI). Castings placed within airport properties and other heavy load areas are to be specified in the special provisions to resist loading forces associated with those areas.  Gray iron castings are to have appropriate certifications and be individually marked in accordance with the requirements of AASHTO M-306. Castings which do not possess appropriate AASHTO M-306 certifications and markings must be replaced by the Contractor at no expense to the Owner.

Coatings and Waterproofing.  External cold joint sealant is to be WrapidSeal (18” wide), manufactured by CCI Pipeline Systems, Viscotaq ViscoWrap (12” wide) or approved equal for external joint sealing.  GMX Ultra-Shield WB, or approved equal for exterior buried concrete structure coatings.  Clear or opaque 8-mil polyethylene tube or sheeting for encasement.  Cold joint gaskets are to be Ram-Nek preformed concrete joint sealant by Henry Company, Inc., Viscotaq ViscoPaste (1/2”x1” profile) or equal.  Internal coatings are to be resistant to low PH (1.5), bond well to concrete, and withstand submersion in industrial sewerage, such as but not limited to a 150 mil thick Carboline “Semstone 140” 100% solids, high performance epoxy liner system with primer.

Pipe Connections to new manholes (boots).  Material and manufacture of waterstops is to conform to applicable provision of the ASTM Standard Specifications for Resilient Connectors between Reinforced Concrete Manhole Structure and Pipes, ASTM C923. Pipe connectors’ metallic components are to be stainless steel.  Z Lok Connector by A•Lok® Products Inc. or equal is to be cast integral with the concrete structure. G3 Boot by A•Lok® Products Inc., Kor-N-Seal I and II, Wedge Style Pipe to Manhole connector or equal are to be used for core drilled penetrations.

- Insulation Board.  The insulation boards shall be extruded polystyrene insulation board, have a minimum full board size of 2' x 8' and meet the thickness specified on the Plans.  The insulation board shall be rigid, homogeneous, and essentially unicellular, and shall conform to the requirements of Subsection 635-2.01.

- Concrete.  Concrete used in the construction of sanitary sewer systems with the exception of precast manholes, manhole risers, cones, and reinforced concrete pipe is to be Class A.  Cement for mortar used in the construction of sanitary sewer systems is to conform with the requirements of ASTM C-150, Type II.  Sand is to conform with the requirements of AASHTO M-45.  The mortar is to be composed of one (1) part cement and three (3) parts sand.  The addition of lime is not permitted.  The use of five (5) minute or fast-cure mortar requires prior approval of the Engineer prior to use.

- Connections.  Connections of four and six inch (4” & 6”) sewer pipe to non-concrete collectors, trunks and interceptors are to be accomplished with an epoxy coated ROMAC CB saddle or equal.  Connection to concrete pipe is to be accomplished with an Inserta Tee™, Romac SST, modified Romac SST or equal.  To modify a Romac SST is to remove bolts and receiver lugs so that the tee, half clamshell and partial gasket remain.  The clamshell gasket and tee are to be connected to the concrete sewer pipe with stainless steel concrete wedge anchors at each corner and fastened tightly to the concrete sewer pipe.  A connection of eight inch (8”) and larger sewer pipe to larger pipe is to be accomplished with a manhole, Inserta Tee™, Romac SST, modified Romac SST or equal.  A Romac SST or equal is to be used for deep service riser connects. When connecting a sanitary sewer connection to a sanitary sewer extension a ROMAC 501, Romac Macro HP or their equal is required when a satisfactory pipe bell is not present.  When making a repair to Sanitary Sewer Extensions the Romac SC or equal may be used but the ROMAC 501, Romac Macro HP or their equal is strongly recommended and is required for repairs replacing pipe longer than eight feet (8’) in length.  Pressure sewer pipe connections are to utilize ROMAC 305, 306 stainless steel service saddles or equal.

CONSTRUCTION REQUIREMENTS

626-3.01  GENERAL.  Complete the sanitary sewer system and make sure it operates properly at the time of acceptance of the work.  Furnish and install all incidental parts not shown on the Plans or specified in this Section that are necessary to complete the sanitary sewer system.

Meet the applicable provisions of Sections 201, 204, and 603 for all clearing and grubbing, excavation, bedding, backfill, conduit, and appurtenances.

If sewer conduit is directly connected to or supported by rigid structures such as manholes, it must have a joint or flexible connection located 5 feet or less from the point of connection or support.

Lay sewer conduit accurately to the staked line and grade.  Install all service connections as indicated on the Plans.  Provide suitable fittings and adapters when connecting existing service sewers.

Clean all foreign matter from sewer conduit.  Keep water out of trenches until joints are completed.  Plug or cover open ends of conduit and fittings when work is not in progress to keep out foreign matter and rodents.

Join pipe according to manufacturer’s recommendations, or as detailed on the Plans.

When sewer conduit is laid within a 10-foot horizontal radius of an existing or a new water main and is above or 3 feet below the water main, use cast-iron pipe.

Remove trench sheeting and bracing above the elevation of the conduit.  Do not pull, remove, or disturb sheeting below the conduit.

Minimum slopes for gravity sewers are as follow:

| Pipe Diameter | Slope (%) | Slope (FT/FT) |
| --- | --- | --- |
| 4" | 2.08% | .0208 feet per foot |
| 6" | 1.00% | .0100 feet per foot |
| 8" | 0.40% | .0040 feet per foot |
| 10" | 0.28% | .0028 feet per foot |

The minimum standard depth of bury for gravity sewer is eight feet (8’).  Where this cannot be achieved, the sewer pipe is to be laid at the minimum slope to achieve the greatest depth of bury possible.  Where the depth of bury is reduced to five and one-half feet (5 ½’), but greater than four and one-half feet (4 ½’) the sewer pipe is to be fully encapsulated with a minimum of three inches of rigid foam.  Pressure sewer is to have a minimum cover of ten feet (10’) with no reduction allowance for insulation.  Pipe installation with less than minimum separation, slope or bury will be cause for rejection.

During the progress of the Work, the Contractor shall provide instruments such as transits, levels, laser devices, and other facilities for transferring grades from offset hubs or for setting of batter boards or other construction guides from the control points and bench marks provided by the Contractor.  The Contractor is to provide qualified personnel to use such instruments and who have the duty and responsibility for placing and maintaining such construction guides.

In all cases pipe installation is to proceed from lower to higher elevations with the spigot ends of the pipe at the lower end of each pipe segment. Each pipe is to be laid true to line and grade.  Joints may not deflect or be offset.  The alignment of the installed pipe is to appear visually straight so that a full circle of light can be seen between manholes.  Each section of pipe is to be handled carefully, placed accurately; and joined in accordance with the pipe manufacturer’s recommended standards.  Each section of pipe is to be properly supported to ensure true alignment and an invert which is smooth and free from roughness or irregularity.

The Contractor is to stagger the joints for sanitary sewer pipe such that no sewer pipeline joint is closer than nine feet (9’) measured horizontally (outside of pipe to outside of pipe) from its intersection with water mains encountered in the Work.

The Contractor shall take every precaution to preclude foreign debris from entering the sanitary sewer system.  Temporary screening techniques of the downstream manholes proposed for use by the Contractor must first be reviewed and approved by the Engineer prior to their use in the Work.  Contractor is responsible for removing and cleaning any foreign debris that enters the sanitary sewer system.  All costs associated with the removal of foreign debris from the sanitary sewer system resulting from the Contractor’s activities is considered subsidiary to the Contract.

At all times, when Work is not in progress, open ends of pipe and fittings are to be securely and satisfactorily closed so that no undesirable substance will enter the pipe or fittings.

The pipe is to be laid in trenches when the trench bottom and sides to one foot (1’) above the pipe are in a thawed state.  The trench is to be immediate backfilled with completely thawed material.  The trench is to be backfilled at the end of the work shift during freezing and near freezing temperatures to prevent the pipe zone from freezing.

Tracer wire must be installed on all non-metallic pressure sewer pipes.  Tracer wire must be brought to the surface near sewer structures.

The warning tape must be continuously laid with the pipe and be at least twenty-four inches (24”) and no more than thirty-six inches (36”) above the pipe.

Preformed gasket joint sealer is to be applied per the manufacturer’s recommendation between each cold joint except for grade ring joints.  Gaskets are to be trimmed on the inside of the manhole to prevent the excess gasket material from entering the sanitary sewer lines.  Grade rings are to be bed in mortar. Smearing of mortar to cover the joint on the inside of the grade ring will be cause for rejection.  Heat shrink external joint sealer is to be applied per the manufacturer’s recommendation over the casting, grade rings and over the eccentric cone joint.  Manholes and other unheated underground structures are to have a minimum of three (3) layers of 8-mil polyethylene encasement on the outside.  The polyethylene encasement may be applied one layer at a time with three individual tubes, continuously wrapping, or three separate tape secured layers of polyethylene.

Polyethylene joints are to overlap a minimum of twelve inches and be secured with tape.  The boot pipe connector is to be installed so that leakage between the pipe and structure is eliminated.  Pipe-to-structure boot connections are to fit snugly over a pipe and be cast integrally with the structure.  The boot is to be held firmly against the pipe surface by means of a stainless steel mechanical take-up device which, when tightened, will compress the boot to provide a water tight fit.  The mechanical take-up device is to remain accessible from the interior of the manhole.  Pipes are to be stabbed into the structure through the boots such that at least two inches (2”) but no more than three (3”) of pipe extend past the inside face of the manhole.  When directed by the Engineer, the Contractor may core in new penetration(s) when in the opinion of the Engineer a pre-cast pipe penetration is not feasible.  Boots for cored in pipe connectors are to be secured in place with stainless steel mechanical devices that will seal the rubber boot against the concrete structure.  Mortar is not to be placed on the boot inside the structure.  Class ‘E’ Bedding material is to be placed a minimum of three feet (3’) outside the manhole and compacted to a minimum of 95% of the modified proctor.  In the case of poured-in-place manhole construction, if the Contractor elects to accomplish the manhole construction utilizing more than one continuous concrete pour, a keyed construction joint must be used.  Pre-cast bases may not be used in conjunction with poured-in-place manhole sections.

The heat trace cable shall be installed in the appropriate channel on the pipe before pipe joints, fittings and connections are insulated.  This cable should be pulled into position using manufacturer’s recommendations.  Care shall be taken to ensure that the cable is not excessively stretched, is not cut, gouged, or twisted during insertion.  Every precaution should be taken to ensure that the cable channel remains dry after the pipe is installed.  This will include caulking at pipe ends as necessary.  The heat tracing shall be accessible from the heat trace pull points and be able to be replaced easily.

626-3.02 TESTING.  With the Engineer present, test the sewer for grade, alignment, and leakage. Grade and alignment must conform to staking with no deviation allowed that would inhibit flow.

Test for infiltration if the normal groundwater table lies above the invert of the sewer conduit.  Infiltration must not exceed 4 gallons per inch of conduit diameter per 1000 feet of pipe per day.

Test for exfiltration when no groundwater exists above the conduit invert.  Leakage must not exceed 5 gallons per inch of conduit diameter per 1000 feet of pipe per day.  Use minimum test pressure of 4 feet of water column above the crown at the upper end of the conduit.

Correct all leakage before backfilling.

After backfilling, test each run of conduit for obstructions and alignment by placing a light at one end. The light must be visible through the sewer conduit at the next manhole.

Testing (PE Service Pipe in Collection System)

All sewer service pipe shall be inspected at the point of manufacture in accordance with the appropriate ASTM specification.  Provide a certificate of test results to the Engineer.  After all piping, including individual property services, has been installed and backfilled, and pipe-laying has proceeded beyond the nearest isolation valve, the Contractor shall pressurize the reach of line between the adjacent isolation valves.  After the line has been filled and the test pressure allowed to stabilize (usually after 2-3 hours), the test section shall be pressurized to the allowable operating pressure or 110 psig maximum for a minimum of 2 hours.  Allowable amounts of make up water for expansion during the pressure test are shown in the table below.  If there are no visible leaks or significant pressure drops during the final test period, the pipe reach will be accepted.

ALLOWANCE FOR EXPANSION AT PRESSURE

| Diameter | U.S. Gallons/100-ft. |
| --- | --- |
| 1-1/2” | 0.05 |
| 2” | 0.09 |
| 3” | 0.15 |
| 4” | 0.25 |
| 6” | 0.60 |
| 8” | 1.00 |
| 10” | 1.30 |
| 12” | 2.30 |
| 14” | 2.80 |
| 16” | 3.30 |

Under no circumstances shall the total time under test exceed 8 hours at 1-1/2 times the pressure rating.  If the test is not completed due to leakage, equipment failure, etc., the test section shall be permitted to “relax” for 8 hours prior to the next testing sequence.

Heat tracing Cable testing

The Contractor will be required to ensure a working heat trace system by testing the resistance of the cable in accordance with the manufacturer’s recommendations.  The Contractor shall log the length of cable at each point where a test was made and submit the log to the Engineer and City of Wasilla.  The Contractor shall also ensure that the cable moves freely at the pull points by pulling the cable each direction to see that it does not bind or hang up in any way.

626-4.01 METHOD OF MEASUREMENT.

Slopes of 10 percent or less.  By the length of the horizontal projection of the conduit from center to center of manholes or cleanouts.

Slopes of more than 10 percent.  By the length along the centerline of the conduit from center to center of manholes or cleanouts.

626-5.01 BASIS OF PAYMENT.  All labor, tools, equipment, fittings, service fittings, pipe, and demolition necessary to connect new sewer mains to the existing sewer mains as shown on the drawings, as well as branch connections, is subsidiary.

The contract price for Sewer Service Connection includes trench excavation, shoring as required, dewatering as required, bedding, backfill with native soils, compaction, pipe, fittings, bends, repair of or provision of polyethylene encasement on ductile iron pipe, couplings, testing, etc., unless covered under a specific pay item.  Any excavation below plan grade approved by the Engineer shall be paid under Item 203.0003.___ Unclassified Excavation.  Backfill and bedding to replace unsuitable material shall be paid in accordance with Section 203.

The contract price for Sewer Service Connection includes installation of service pipe, insulation, heat trace, and connection to existing sewer service with necessary coupling, and connection to a new or existing sewer main with a service saddle, tapped, or coupling as shown on the Plans and/or described in this section.

Unless specific pay item is listed below, pipe, and appurtenances called out on the Plans to be removed shall be an incidental item of construction.  All removed materials shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.  Backfill for removed sewer manholes shall be paid in accordance with Section 203.

Any costs involved in sewer service changeovers and providing temporary sewer service bypass (flow control) are subsidiary.

Protection of landscaping, testing, coupling to existing pipe, repair and/or restoration of existing improvements on private property, such as fences, and repair of existing utilities damaged by the Contractor will not be paid for directly but will be considered subsidiary to Section 626 pay items.

All Work required to coordinate with facility owners and to shore (includes engineering, developing, implementing, and removal of shoring setups), adjust, remove and replace, and/or relocate existing facilities within the working area/excavation limits associated with the pay items in Section 626 is subsidiary to those items.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 626.0002.____ | Sanitary Sewer Service Connection | Each |

CFHWY00599

Special Provision

Replace Section 627 with:

SECTION 627
WATER SYSTEM

627-1.01 DESCRIPTION.  Furnish and place water main and service improvements and replacements, including all appurtenances, as shown on the Plans or specified in this Section.  Remove, salvage and reinstall fire hydrants, valve boxes, and water meters, as specified.  Submit product data to the Engineer for approval before installation.

The term “water conduit” refers to all conduits used for water mains.  The term “service pipe” refers to service lines.

For purposes of these specifications, “COW” shall mean the City of Wasilla.  This work shall include the installation and testing of the water system for acceptance by the Engineer.  The Contractor shall provide record drawings in accordance with the conditions prescribed herein.

Coordinate with the Engineer and COW; and schedule/participate in a pre-construction condition inspection, and a post-construction condition inspection of the water system facilities.  The pre-construction inspection shall be completed before the Contractor begins work on the project, and the post-construction inspection shall be completed after paving operations are complete.

The inspections may identify main valve boxes, the top section, the lid and additional items, to be replaced.  Replace additional facility items as directed by the Engineer.

Any deficiencies in the water system facilities discovered during the pre-construction condition inspection are COW’s responsibility to correct.

The locations of the existing water utilities shown on the Plans are not exact.  The Contractor shall confirm the location and elevation of the existing water mains at the proposed connection points shown in the Plans.

Install, test, flush, and disinfect water system for acceptance by the Engineer.

Provide three (3) days advance written notice to COW, through the Engineer, and schedule/perform valve operations and mainline live taps.

COW reserves the right to postpone or reschedule Contractor operations directly impacting active water mains and services for any reason.

627-2.01 MATERIALS.  Use materials that conform to the following, and/or as modified by additional stated requirements in this sub section:

Backfill	Subsection 204-2.01

Pipe Bedding	This Subsection

Concrete for Thrust Blocks	Subsection 550, Class W

HDPE Pipe	Subsection 706-2.08

Ductile Iron Pipe	Subsection 707-2.05

Service Pipe	Subsection 707-2.06

Corporation Stops	Subsection 712-2.09

Gate Valves	Subsection 712-2.10

Valve Boxes	Subsection 712-2.11

Hydrants	Subsection 712-2.12

Insulation Board	Subsection 635-2.01

- Pipe Bedding.  All water conduit bedding shall be Class “E” as defined by the following:

TABLE 627-1

Class “E” Pipe Bedding

| Sieve Size | Cumulative Percent Passing by Weight |
| --- | --- |
| ½-inch | 100 |
| 3/8” | 80-100 |
| #4 | 20-75 |
| #8 | 12-60 |
| #30 | 2-30 |
| #200 | 0-6 |

- Ductile Iron Pipe (DIP).  All DIP water conduit shall be Zinc Coated Ductile Iron Pipe (qualifies as tightly bonded).  Zinc Coated Ductile Iron Pipe is to be ductile iron pipe meeting these requirements: Ductile iron pipe is to be cement mortar lined, conform to the requirements of AWWA C151, and have a minimum pipe wall thickness meeting Class 52 requirements. The cement mortar lining is to conform to the requirements of AWWA C104/ANSI A24.1.  At least 10% of the pipe delivered is to be gauged full length of the pipe and marked as such.  All water conduit shall have a metallic zinc coat and a bituminous finish layer in accordance with ISO 8179-1, with the minimum mass of zinc being 150 grams per square meter and a mean mass of 200 grams per square meter of 99.99% pure metallic zinc.

- HDPE Pipe.  All water mains, hydrant lines and service lines 3 inches and larger shall be SDR-11 High Density Polyethylene Pipe (HDPE).  The material shall be listed by the N.S.F. for potable water service and shall be pre compounded.  In plant blending shall not be allowed.  HDPE pipe, tubing, and fittings shall conform to all applicable provisions and requirements of the latest revision of AWWA C901 and AWWA C906 and by inclusion, all appropriate standards referenced therein.

The pipe shall be homogenous throughout and free of visible cracks, holes, foreign inclusions or other injurious defects.  It shall be uniform in color, opacity, density, and other physical properties.

All HDPE water main piping and fittings shall be butt fused in accordance with ASTM D-2657.  Butt fusion of the pipe and fittings shall be performed in accordance with the pipe manufacturer’s recommendations as to the equipment and technique.  The fusion operation shall be performed by an individual who has demonstrated the ability to fuse polyethylene pipe in the manner recommended by the pipe supplier and has provided written certification from an HDPE pipe manufacturer stating he/she has successfully completed an 8-hour (minimum) certification class on butt fusion techniques and procedures.  In addition, this individual shall have fused a combined total of more than 5,000 feet of HDPE piping in diameters of 4-inches and larger.

The Contractor shall inspect HDPE piping for damage immediately prior to joining.  Damage is defined as cuts or gouges exceeding 10% of the pipe wall thickness, kinked pipe sections, pipe sections flattened to more than 5% of the original diameter, or any abrasion or cutting of the inside surface of the piping.  Damage portions of piping shall be cut out and discarded.

The Contractor shall ensure that each joint is fused at the temperature and pressure recommended by the pipe manufacturer in order to achieve the maximum pressure rating for that joint.  All butt-fused joints and fabricated fittings shall be documented by a computer data logger that records pressure and temperature applied at each at each fused joint, along with the date and time the joint was fused.  Computer printouts and electronic data for each fitting shall be submitted to the Engineer and approved by the Engineer prior to installation of the fitting.  All fittings shall be labeled with a unique identifier that corresponds with the fusion computer printouts for each fitting.

The use of electro-fusion couplings to join HDPE piping may be allowed upon written approval by the Engineer.  Electro-fusion couplings shall comply with ASTM F-1055.  The Contractor shall as-built the exact location of any installed electro-fusion couplings.

The handling of joined pipe shall be in such a manner that the pipe is not damaged.  Ropes, fabric, or rubber protected slings, or straps shall be used when handling pipe.  Chains, cables, or hooks, inserted into the pipe ends shall not be allowed.  Two slings spread apart shall be used for lifting each length of pipe. Slings for handling the pipe shall not be positioned at butt-fused joints.

A tracer wire shall be installed above all HDPE water mains in accordance with the manufacturer’s recommendations.  Tracer wire shall be suitable for direct bury applications and shall be 10 AWG with 30-mil HDPE jacket (jacket color blue), capable of a 575-pound average tensile break load.  Tracer wire shall be Copperhead Industries reinforced tracer wire or approved equal.  Trace wire shall be installed in continuous lengths with no splices.  Terminate each end of the tracer wire at ground surface in a valve box top section with cap.  Provide a minimum 5 feet of additional wire neatly coiled within valve box at each end.

- Service Pipe.  Water service connection lines smaller than 3 inches shall be coated copper pipe and must be soft-drawn Type K, seamless, annealed copper pipe suitable for use as underground service water connections for general plumbing purposes and ASTM B88 compliant with an approved coating system.  Approved coatings include factory applied minimum twenty six (26) mil thick polyethylene or a field applied coating.  Where a coating is required, field applied coatings may be used for repair of, in conjunction with or substitution for other coatings.  Field applied coatings are to be denso wrap system, trenton wax tape system or viscotaq viscowrap system, or approved equal.  The term “system” requires the use of more than one product from the specified manufacturer to be used in concert to seal the pipe from corrosive and/or potentially contaminated environments and water.  At a minimum, the system shall fully encapsulate the piping and fittings, fill voids/gaps and adhere to the pipe.  The coating system must not interfere with the operation of moving parts.

- Restrained Joints.  Where specified on the Drawings and/or required in these specifications, ductile iron pipe shall be installed with restrained joint thrust restraint systems.  Ductile iron thrust restraint systems shall be EBAA Iron MEGALUG®, Romac Industries GripRing®, or U.S. Pipe Field LOK Gasket System or approved equal.  If the ductile iron pipe restrained joint system proposed for use in the Work is not one of these systems, the Contractor must field demonstrate to the Engineer the installation and/or construction of each new restrained joint or restraining system.  Coordinate with COW through the Engineer, provide COW with a minimum of forty-eight (48) hours notice, excluding non-working days, to coordinate the review of the field demonstration.  The Engineer will ask for verification that the restrained joint system is installed in accordance with the jointing system manufacturer’s written instructions.  If in the opinion of the Engineer the Contractor fails to install the restrained joint system in accordance with the jointing system manufacturer’s recommendations, the Contractor shall remove the disapproved system and replace with a new restrained joint system.  The Contractor shall provide access to the field demonstration location and all trench excavation, dewatering and backfill operations prior to, during, and after the restrained joint system is reviewed by the Engineer.  The cost for coordinating and providing access for review of the Contractor’s installation and/or construction of the restrained joint system shall be incidental to the bid item under construction.

Restrained joint installation areas shall include all valves, fittings, and piping deflection points.  The Contractor shall provide pipe manufacturer submittals, which must include thrust restraint calculations prior to construction.  Tie back rods and/or tie back rod and shackle assemblies will not be acceptable as restrained joints or restraining system for fittings, piping, deflection points, or inside casings.

- Gate Valves.  Gate valve bonnet bolts shall be Type 316 stainless steel with a minimum tensile strength of 75,000 PSI and shall conform to ASTM F593 and F594.  All bolts shall be stamped with the grade marking on the head of the bolt, and shall be “T-316”, “316”, or “F593”.  Valve nuts, bolts, and washers shall be stainless steel, Type 316.  Carbon steel galvanized or zinc plated nuts, bolts, and washers shall not be allowed.

Gate valves shall be ductile iron body resilient wedge type rated for 250 psi cold water working pressure, and in full compliance with AWWA C515 and NSF Standard 61.  The wedge shall be ductile iron encapsulated in nitrile rubber and shall seat equally well against flow in either direction.  The stem and wedge nut shall be manganese bronze.  All exposed interior and exterior surfaces of the valve body, bonnet, and stuffing box shall have a fusion bonded epoxy coating, complying with AWWA C550, applied electrostatically prior to valve assembly.  Gate valves shall be non-rising stem type, with a triple O-ring seal.  Gate valves shall have a 2-inch square operating nut and shall open counter-clockwise.  Gate valves shall have mechanical joint ends.

- Valve Boxes.  Valve boxes shall be cast iron of sliding, adjustable height type with round or oval bottom hood sections to fit over the top of the valve.  The top section shall be recessed to receive a close fitting "eared" lid with the word "water" cast into it.  Internal diameter of the smallest section shall not be less than five (5) inches.  Minimum thickness of the metal shall not be less than five-sixteenth (5/16) inch.  Castings shall be smooth and the workmanship shall be acceptable to the Engineer.

Valve boxes shall be of sufficient length for the pipe cover depth on the profile drawings and in accordance with the Plans.

Valve box and valve box base sections shall be tape coated as shown in the Plans.  Tape coat and primer shall be products of the same manufacturer.  Prepare surfaces by hand-removing all loose dirt, dust, or other foreign matter that may interfere with the tape adhesion.  Power tool cleaning of the surfaces is not required.  Ensure valve box and base section surfaces are clean and dry prior to beginning coating application.  Apply a thin coat of primer to the surfaces and spiral wrap the tape with a 50% overlap.  Continuously wrap the tape coat between valve box and base section.  While wrapping, press air pockets out and smooth all lap seams.  Denso wrap, trenton wax tape, or viscotaq viscowrap systems are acceptable, or approved equal.

- Fire Hydrants.  Fire hydrants shall conform to the requirements of ANSI/AWWA C502 for Dry Barrel Fire Hydrants.  Fire hydrants shall be Mueller Super Centurion, American Darling 5-1/4 B62B with 20” nozzle section or approved equal.

  - All fire hydrants shall be supplied with 5-1/4-inch main valve opening.

  - All single pumper hydrants shall be furnished with a 6-inch ANSI Class 125 standard mechanical joint end with restrained joint.

  - All connections shall be restrained mechanical joints unless otherwise indicated in the Contract Documents.

  - Fire hydrants shall be single pumper, furnished with two (2) 2-1/2-inch hose connections and one (1) 4-1/2-inch pumper connection.

  - Unless otherwise required by the Contract Documents, all hydrants shall be furnished with a barrel length that will allow a minimum of 10 feet of bury.  Hydrants barrels, in areas requiring a depth of bury greater than ten feet, shall be adjusted to grade to the satisfaction of the Engineer.

  - The main valves shall be of the compression type, where water pressure holds the main valve closed permitting easy maintenance or repair of the entire barrel assembly from above the ground without the need of a water shut-off.

  - All fire hydrants shall be furnished with a breakaway flange which allows both barrel and stem to break clean upon impact from any angle.  Traffic flange design must be such that repair and replacement can be accomplished above ground.

  - Painting and coating shall be in accordance with cited AWWA specifications.  After installation, the hydrant section from the traffic flange to the top of the operating nut shall be painted Fire Red.

  - The hydrant barrel section shall be wrapped with three layers of 8-mil thick polyethylene encasement up to the finish ground surface.

  - Operating and nozzle nuts shall be pentagon shaped with 1-1/2 inch point to flat measurements.

  - Hose nozzle threading shall be in conformance with NFPA #194 for National (America) Standard Fire Hose Coupling Screw Threads.

  - All working parts shall be bronze or noncorrosive metal in accordance with the requirements of ANSI/AWWA C502.

  - All hydrants shall be left-hand opening (counterclockwise).

  - All hydrants shall be non-draining

  - Hydrant lower barrel, shoe and DIP MJ adapter shall be tape coated in a manner similar to copper services and valve boxes as shown in the Plans.

  - Hydrant barrel extensions shall be by the same manufacturer as the hydrants, and shall include new barrel extensions, extension rods, gaskets, bolting materials, and all required incidentals.  For extensions up to 4-feet, the extension sections shall be furnished and installed in the precise length needed, one extension section per hydrant.  For extensions greater than 4-feet, two extension sections shall be stacked, provided that the extension rod in the lower extension section is fitted with a centering mechanism acceptable to the Engineer, to limit operating rod deflection.

- Galvanic Bag Anode.  Anodes shall be High Potential Cast Magnesium Anodes.  Anodes utilized for the galvanic anode system installation shall be prepackaged magnesium style anodes weighing twenty pounds bare and seventy pounds packaged.

Anodes shall be packaged in a low resistive backfill consisting of 75% gypsum, 20% bentonite, and 5% sodium sulfate.  Anodes shall be provided with No. 10 AWG stranded copper, single conductor cable with HMWPE insulation.  Lead wire cable shall be rated for 600 volts and designed for direct burial applications.  Equipment and materials used to bond the No. 10 AWG HMWPE to the pipeline shall be “CADWELD” type as manufactured by ERICO Products, Inc. of Cleveland, Ohio, or approved equal.  Exothermic weld areas shall be repaired with Royston “Handy Caps”, Tapecoat TC Mastic or approved equal.

Anodes shall be provided for all water main gate valves, water service gate valves, water service curb stops, and fire hydrants.  Jumper wires shall be installed between valves and hydrants as shown in the Plans.  If more than one gate valve and/or hydrant is within a 20-foot radius, use two AWG 10 HMWPE lead wires to bond the hydrant and valves. Use only one anode for the cluster.

- Insulation Board.  The insulation boards shall be extruded polystyrene insulation board, have a minimum full board size of 2' x 8' and meet the thickness specified on the Plans.  The insulation board shall be rigid, homogeneous, and essentially unicellular, and shall conform to the requirements of Subsection 635-2.01.

CONSTRUCTION REQUIREMENTS

627-3.01 GENERAL.  Complete the water system and make sure it operates properly at the time of acceptance of the work.  Furnish and install all incidental parts not shown on the Plans or specified in this Section that are necessary to complete the water system.

Meet the applicable provisions of Sections 201, 204, and 603 for all clearing and grubbing, excavation, backfill, conduit, and appurtenances.

Consult the Plans for estimated locations of existing sewers, water mains, and other utilities near the construction.  Use this data for information only.  The Department does not guarantee their accuracy.  Confirm and mark the exact locations of all existing utilities before starting work so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled.

Excavate, bore, or probe by hand ahead of your work where necessary to determine the exact location of underground facilities or other features that might interfere with construction.  Coordinate with facility owners and develop shoring plans to support and protect existing infrastructure.  Shoring plans shall be reviewed and approved by facility owners prior to being implemented.  Facilities owners shall be notified immediately if Contractor operations damage an existing facility.  The Contractor is not permitted to make any repair to a facility without approval from the facility owner.

Contractor shall take every effort to protect existing services, both located and unlocated, from damage and shall anticipate one service to each developed lot adjacent to the sewer main.  Repairs to any damaged sewer services shall be made using HDPE and Romac (or approved equal) repair couplings with stainless steel bands.  Pipe inside diameter shall match the existing pipe or, if the exact match is not available, the new pipe may be slightly larger.  The inverts of the new pipe shall match the inverts of the existing pipe, regardless of pipe diameter.  Pipe shall be bedded and backfilled in accordance with the trench detail.  Contractor shall notify the sewer service user immediately if a service is damaged and advise the user to not introduce any flow into the service until it is repaired.  Contractor shall perform the repair immediately to restore service and shall advise the user when the service is usable.  Contractor shall contain any flow that spills from the damaged service and shall dispose of waste and contaminated soil in accordance with DEC regulations.  Repair to any sewer services is incidental to the water pipe construction and no separate payment will be made.

At least 72 hours prior to removing or disrupting service to fire hydrants, the Contractor, through the Engineer, shall contact the COW.  Any hydrant taken out of service shall be immediately and securely wrapped in burlap to indicate its status.

Contractor shall provide seventy-two (72) hours written notice to the Engineer, COW, and affected property owners/businesses prior to anticipated mainline flow interruptions.  It shall be the Contractor’s responsibility to coordinate “turn-off” and “turn-on” with the Engineer.  Additionally, the Contractor shall notify all affected property owners and the Engineer, 72 hours prior to interruption of COW's water service.  The Contractor shall provide temporary service to all those property owners with disrupted water service if the interruption exceeds 6 hours in duration.  Water interruptions should only occur during periods of low water demands, as determined by the COW.  The Contractor shall minimize the number and duration of water service interruptions throughout the project.  When authorized by the Engineer and COW, water services may be shut-off between the hours of 8:00 a.m. and 5:00 p.m.

If Contractor operations cause service interruptions, the Contractor is responsible for all damages.

Furnish and install concrete thrust blocks as shown on the Plans or specified in this Section.  Place blocks against firm natural ground at the trench site.  When the trench is in soft, unstable soil, remove the soft soil and replace it with a ballast backing large and heavy enough to resist the thrust.

Connect to existing water lines and structures.  The Contractor shall perform this Work in a manner not to contaminate water in active waterlines.

Where new water mains cross existing sanitary sewer or storm sewer pipes, the new water main shall be installed a minimum of 18 inches vertically from the sanitary sewer or storm sewer pipe.  Water pipe joints shall be a minimum of 9 feet horizontally from sanitary sewer pipes, storm sewer pipes, or manholes.

Where the required clearance cannot be obtained, the existing pipe may be replaced with HDPE with joints spaced at least 9 feet from the crossing and a heat shrink wrap on joints within 10 feet of the pipe intersection.

Contractor shall furnish the required traffic control, including personnel to assist, while performing all water system inspections.  The Contractor forfeits all right to assert pre-existing damage if the Contractor fails to participate in the inspections.  During inspections the COW representative, the Engineer and the Contractor will observe each facility's location and condition.  The Engineer will indicate the additional facility items to be replaced.

Provide three (3) days advance written notice to COW, through the Engineer, scheduling a pre-construction inspection of the facilities.  Conduct this inspection before pavement removal begins.  Contact the COW Project Manager, through the Engineer, to determine where to send the written notice.  Provide the Engineer a copy of the written notice.

The Contractor shall furnish the valve box top sections and lids for the Work.

If service connection locates are required, contact COW, through the Engineer.  Allow three (3) working days from the time of the request for COW to complete the locate request.

Salvage the valve box top sections and lids scheduled for replacement.  Coordinate with COW, through the Engineer, and deliver the salvaged materials to COW.  Dispose of water system facility materials not wanted by COW, according to DOT&PF rules and regulations.

Provide a written notice to COW, through the Engineer, scheduling a post-construction inspection of the facilities, after the paving operations are complete and three (3) days in advance of the inspection.

It is the Contractor’s responsibility to protect and maintain valves and valve boxes in an operable condition during all phases of construction.  The Contractor shall coordinate with the COW and the Engineer, to review and concur with any construction plan that will render COW’s facilities inaccessible prior to beginning the proposed work.

Prior to commencement of work to install the water system, the Contractor shall submit to the Engineer for review, a detailed plan for the installation of the new water systems.  The plan shall be of sufficient detail to clearly indicate the proposed work sequence, schedules, disruption of water service, and temporary water services, if needed.

The Engineer reserves the right to suspend the water system installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project and will not entitle the Contractor to extra payment for costs incurred.

If construction or excavation require the removal of any existing privately-owned facilities or improvements installed within and outside of the provided temporary construction easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at the Contractor’s cost.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed two weeks.  The Contractor shall restore property disturbed by contract activity to the preconstruction condition.

Trench Shoring.  The Contractor shall obtain approval from the Engineer for all sheeting, bracing, and shoring materials and/or equipment to be used on the project.  Materials used shall be in accordance with Section 1926.651, Subparagraph 1 of the Federal Register, Volume 37, No. 243, page 27553, OSHA Regs., December 1972.

All construction requirements for design, installation, and use of sheeting, shoring, bracing, and shielding shall be in accordance with current safety regulations.  All sheeting, shoring, bracing, and shielding shall be designed by a Professional Engineer registered in the State of Alaska, hired by the Contractor.  All working drawings and design data shall be submitted to the Engineer for approval.

No bracing requiring driven or vibratory installation methods shall be used on this Project.  Any Contractor provided portable trench shielding shall comply with relevant OSHA regulations.  The Contractor shall provide the Engineer certification of such compliance from the portable shield manufacturer or supplier.

The Contractor shall coordinate with COW, through the Engineer, to complete the following work:

- Perform a test shutdown of the main prior to beginning waterline/hydrant work.  Allow three (3) working days to complete the test.

- Perform final vertical adjustment of hydrants.  Allow one (1) working day per hydrant.

Water System Trench Excavation and Backfill.  Excavation and backfill shall be to the width and depth as shown on the drawings.  Trench width at or below the top of the pipe shall be of a width that will allow compaction equipment to be used at the sides of the pipe.

Contractor shall erect and maintain barricades to prevent access around all excavations left open at the end of the workday.  Contractor shall provide and maintain adequate barricades to ensure public safety at all times during the prosecution of the Work.

Contractor shall perform all excavation of every material encountered.  Excavated material shall be placed in an orderly manner and at a distance from the trench conforming to all State and/or Federal safety codes.  Excavated material meeting the requirements of Select Material shall be stockpiled separately and reused in the Work.

Not more than 200 feet of trench shall be open in advance of the pipe installation unless written authorization is obtained from the Engineer.  Not more than 100 feet of trench shall be left open at the end of the workday, unless otherwise approved by the Engineer.

All bedding material and backfill material shall be placed in uniform layers of not more than 12 inches in depth and compacted in accordance with Subsection 203-3.04.  In no case shall bedding material be placed above the spring line of the pipe in a single lift.  Ponding or jetting of backfill will not be permitted.

When existing conduits or utilities are encountered in the excavation, they shall be adequately supported and protected from damage.  The contractor shall develop and submit shoring designs, through the Engineer, to each Utility impacted by the proposed excavation work for review and concurrence.

All sheeting and bracing used in excavation shall be removed by the Contractor following the completion of the work.

Remove Existing Pipe.  Pipe, hydrants, and appurtenances called out on the plans to be removed shall be an incidental item of construction.  All removed materials shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.

Depth of Bury.  All water mains and services shall have a minimum of 10 feet of bury at all points except where otherwise indicated.

Temporary Water Systems.  If utilized, the Contractor shall submit the name and phone number of a contact person and at least one alternative who shall be available on a 24-hour basis for repair and/or maintenance of any temporary water system associated with this project.  In the event that the Contractor fails to repair and/or maintain the temporary system and DOT&PF is required to perform the repairs and/or maintenance, all costs associated with said repairs and/or maintenance shall be deducted from the Contract amount.

Prior to the construction of a temporary water system the Contractor shall obtain a written “Permission to Enter” from the property owner.  Such permission shall hold the Department, the COW, and its agent(s) harmless for any claims resulting from damage or harm sustained due to the Contractor’s operation.  The Contractor shall provide a copy of each “Permission to Enter” to both the Engineer and COW.

The Contractor shall provide all necessary fittings, valves, temporary connections or appurtenances in order to maintain the water distribution system.  Any costs involved in service changeovers and providing temporary water service shall be subsidiary.

All temporary water service equipment shall be disinfected per ANSI/AWWA C652, Disinfection of Water Storage Facilities and ANSI/AWWA C651, Disinfection of Water Mains.  All bacteriological samples required under these Specifications shall be done by a testing laboratory certified by the State of Alaska.  Two bacteriological samples shall be taken 24 hours apart to confirm the system is free of coliform bacteria before commissioning a temporary water system.

Following the successful installation of the temporary water system, the existing water service shall be appropriately disconnected at a main shutoff valve inside the structure.  Qualified personnel who are familiar with building plumbing systems shall accomplish the disconnection of the existing water service.  The work shall be done to prevent back feeding water through the service connection.

Fire hydrants may be used as a water source for a temporary water system.  The Contractor shall be required to obtain a hydrant permit from COW and will be required to meet all permit conditions (winter use of a hydrant shall require special permission from the Engineer).  In addition, the Contractor shall provide a backflow preventer and gate valve assembly at the fire hydrant as a shutoff valve for the temporary water system.  The Contractor shall be responsible for any damage to the hydrant and temporary piping and shall repair such damage at no cost to the Department.

The Contractor shall be responsible for all damages incidental to interruption of service that are due to the Contractor’s operations.

Final Acceptance.  The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a pre-final inspection of the project.  This inspection will be performed in the presence of the Engineer, COW, and the Contractor.  A list of the deficiencies indicated by this inspection will be furnished to the Contractor for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and a final inspection will be performed.

627-3.02 INSTALLATION OF CONDUIT.  Installation shall be in accordance with these specifications, AWWA C600.  The interior of the conduit and accessories shall be thoroughly cleaned of foreign matter before being lowered into the trench.  The conduit shall be kept clean during laying operations by plugging.  Lay conduit to the grades and lines shown on the Plans.  However, at a sufficient distance prior to encountering a known obstacle or tying into an existing conduit, the Contractor shall expose and verify the exact location of the obstacle or conduit so proper alignment and/or grade may be determined before the conduit sections are laid in the trench and backfilled.  The costs incurred for removal and realignment of backfilled conduit sections due to improper verification methods shall be borne by the Contractor.

Keep trenches dry to avoid laying conduit in water.  Do not lay conduit when weather or trench conditions are unsuitable.  Keep water away from new joints, until the joint materials have hardened.

Use methods to cut conduit that will produce tight joints and will not damage the conduit.  Inspect conduit before lowering it into the trench.  Replace defective, damaged, or unsound conduit.

Place conduit bedding to conform to plan and specification details.  Place bedding, if required, to give conduit a uniform bearing for its full length.  Do not permit couplings to rest on solid or original trench bottoms.

Deflections from a straight line or grade, as required by vertical curves, horizontal curves, or offsets shall not exceed 80% of the manufacturer's recommended maximum deflection.  If the alignment requires deflection in excess of the above limitations, the Contractor shall furnish special bends to provide angular deflections within the limits allowable.  Wherever possible, the Contractor shall achieve the desired deflection by taking advantage of reduced deflections over multiple joints.  Short-radius curves and closures shall be formed by shorter lengths of conduit, bevels, or fabricated specials.  No pipe lengths less than 8’ are allowed.

Make service and other connections to conform to the Plans.  Valve, plug or cap conduit ends for future connections as shown on the Plans and provide mechanical end restraint or thrust blocks.

Conduit shall be so laid in the trench that after the line is completed the bottom of the conduit conforms accurately to the grades and alignment shown on the Plans.  A maximum 0.2-foot deviation from design alignment and elevation will be allowed.  Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed.  All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the conduit and not by blocking or wedging up.

The Contractor shall have survey instruments such as transit and level for transferring alignment and grades from offset hubs.  The Contractor shall also employ a person who is qualified to use such instruments and who shall have the responsibility of placing and maintaining such construction guides.  The Contractor shall furnish to the Engineer a copy of the surveyor's record notes for the newly installed conduit and appurtenances.  The practice of placing back fill over a section of conduit to provide a platform for the instruments shall be subject to the approval of the Engineer.

A minimum vertical separation of 18 inches shall be maintained at water and sewer or water and storm sewer crossings.  Where a storm sewer and water main cross with less than 3-feet vertical separation (outside of conduit to outside of conduit), insulate the water main with 4-inch thick extruded rigid insulation board (R min=4.5 per inch).

Conduit that has the grade or joint disturbed after laying shall be taken up and re-laid.  Water shall be kept out of the trench until the jointing is completed.  No conduit length less than 8 feet shall be incorporated into the system except those necessary for fire hydrants or valve locations unless restrained by use of field-lok gaskets, meg-a-lug fittings, or approved equal for ductile iron pipe sections.

Polyethylene Encasement.  The outside of all ductile iron conduit and fittings used in water system construction shall be encased with one layer of 8 mil thick polyethylene film, which shall include a V-bio film system.  Valves and other appurtenances used in water system construction shall be encased with one layer of 8-mil thick polyethylene film, which shall include a V-bio film system.  The polyethylene encasement material for conduit shall conform to AWWA C105/ANSI A21.5.  The polyethylene encasement shall be installed using the following method:

- Cut polyethylene tube to a length approximately 2-feet longer than the length of the pipe section.  Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

- Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

- After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube. Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place.  Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up the slack width to make a snug, but not tight fit along the barrel of the pipe, securing the fold at quarter points.

- Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place. Proceed with installation of the next section of pipe in the same manner.

Mainline Taps.  All mainline taps are to be done by the Contractor, by an individual qualified and experienced in this procedure.  The mainline tap must be accomplished with a drilling machine approved for use on the pipe material being tapped, capable of drilling through the tapping saddle and corporation stop and pipe wall.

Tapping saddles are to be used for all taps with the exception that one inch (1”) taps into eight inch (8”) and larger ductile iron pipe can be directly tapped into the pipe.

Taps are to be made at sufficient distances from each other, tees, bells, joints and other critical areas to prevent compromising the structural integrity of the pipe being tapped.  Taps are not to be made any closer than three feet (3’) to each other or to a bell.  Live taps proposed on mains larger than twelve inches (12”) or constructed of HDPE may require additional time for ordering and receiving of parts.

The Contractor shall perform all proposed live taps required by the Work and provide all trench excavation, shoring, bracing, backfill and compaction necessary to complete a successful live tap connection.  The trench shall be long enough and of sufficient width at the bottom to allow installation of the valve for the live tap connection.  The Contractor shall provide the valve, tapping machine, tapping saddle, as well as all necessary equipment and manpower to perform the Work and move piping, valves, tapping machines, and miscellaneous items into and out of the trench.

Contractor shall excavate for live tap connections in such a manner that the excavation is ninety degrees (90°) to the main water line, whenever possible.

627-3.03 FIRE HYDRANTS.  The Work under this section consists of the performance of all Work required for furnishing all necessary hydrants, pipe, auxiliary valve, and associated appurtenances required to install new or relocate a hydrant to a location indicated on the plans.

Auxiliary Gate Valve and Valve Box.  Auxiliary gate valves and valve boxes shall be furnished and installed in accordance with 627-2.01 and 627-3.04 and 627-3.05.

Joint Restraint.  The Contractor will be required to use restrained joints on all fire hydrant leads.  The Engineer may check any or all restrained joints to assure proper torque as specified by the manufacturer.  All joints shall be restrained in accordance with 627-2.01.

Guard Posts.  Contractor shall install guard posts at each hydrant installation in accordance with the Plans.  If, in the opinion of the Engineer, the guard posts are not to be installed, they will not be required.

The Contractor is responsible for final fire hydrant adjustment.  The Contractor shall be responsible for access to the hydrant location and all trench excavation, dewatering, and backfill operations prior to, during, and after the fire hydrants are adjusted.

Hydrants installed but not available for use shall be covered with burlap and securely tied.

Hydrant legs shall be installed level and barrels installed plumb.

Contractor shall stencil 2-inch black letters, using paint, on the hydrant bonnet indicating the direction and distance to the auxiliary valve box, to the nearest 0.1 foot.

627-3.04 VALVES.  Valves shall be installed where shown on the plans with valve operator placed on the side of the water line away from the centerline of the street or easement.  Valves shall be installed plumb.  Valves shall have the interiors cleaned of all foreign matter before installation.  If the valve is at the end of the line, it shall be plugged prior to backfilling.  The valve shall be inspected by the Engineer, in the open and closed positions to ascertain that all parts are in good working condition.

627-3.05 VALVE BOXES.  Valve boxes shall be installed over the valves as shown on the plans.  The rubber centering ring shall be inserted into the base of the top section and then placed over the operating nut of the valve.  The top section shall be so set as to allow equal movement above and below finished grade.  Final elevation shall be as shown on the Plans.  The Contractor shall wrap the valve and bottom section of the valve box in three (3) layers of woven geotextile fabric secured in place to the bottom section and pipes using PVC pipe tape.  The valve box assembly shall then be wrapped with three layers of eight-mil (8 mil) polyethylene and secured in place using wire or tape.

The Contractor shall expose all valve boxes for pre-final and final inspection.  After final inspection of the valves located in unpaved areas, sawdust shall be poured directly over the valve box lid and covered with gravel to facilitate location in the future.

627-3.06 TESTING WATER SYSTEM.  The Contractor shall notify the Engineer in writing seventy-two (72) hours in advance prior to any test.  COW and the Engineer shall be present during all tests.  Two hours’ notice in advance of the scheduled time shall be given to COW and the Engineer if the test is to be postponed or canceled.

Contractor shall submit a request to obtain and supply water for flushing, testing and disinfecting in writing to the Engineer and COW at least forty-eight (48) hours prior to obtaining COW fire hydrant supplied water.

COW reserves the right to provide a test gauge or to check and test the Contractor’s test gauge at any time.

Flushing.  All flushing shall be coordinated with COW, through the Engineer.  All newly laid water conduit shall be flushed to remove any foreign matter to the satisfaction of the Engineer.  A detailed plan for cleaning of the lines shall be submitted to the Engineer for review and approval prior to commencement of work.

The Contractor may elect to utilize hydraulically propelled bullet shaped foam pigs in accordance with AWWA C651 and this special provision in lieu of full velocity flushing or utilize clean, well maintained, and functioning hydraulic jetting equipment dedicated to water line cleaning.  Where hydraulic jetting equipment is utilized, the pipeline is to be visually verified to be clean of deleterious material by the use of dedicated water CCTV equipment.  If the Contractor elects to utilize hydraulic jetting equipment, the Contractor shall provide all the equipment and manpower required to complete the jetting and video verification work.

When the Contractor elects to utilize foam pigs, the pig is to be constructed of open cell polyurethane medium density foam having a density between five to eight pounds per cubic foot and contain a steel rod that runs through the center of the pig that ends with an eye bolt in order for easy retrieval once the pipe segment has been pigged.  The pig must be coated with polyurethane elastomer coating such that the ends are coated in their entirety and have a crisscross pattern on the sides.  The flat end is to be concave.  The pig is to be sized such that it will make firm contact with the entire interior of the surface of the pipe with such force that it will push deleterious material to the pig retrieval location.  All material gathered at the retrieval location is to be removed from the pipe by the Contractor.  Upon pigging all of the water main, the Contractor is to connect one end of the main to the COW infrastructure and flush the pig push water out of the pigged main.  This flush is to exchange an approximate volume of one and one half the volume of water that could be within the main.  The Contractor is to submit and receive approval of a pig launch and retrieval plan prior to the start of any pigging operation.  The plan must contain information such as water source to push the pig, the pig launching and receiving apparatuses, flush water handling and discharge and how the main is to be finally connected to the COW system for the remainder of the testing.  The Contractor is responsible for all costs and effort to extricate a trapped pig.

Flushing shall be accomplished prior to hydrostatic testing and disinfection at all extremities including all stubouts and dead-ends.  The Contractor shall furnish, install and remove all fittings and conduit necessary to perform the flushing.

Flushing of newly installed conduit may be required to occur between the hours of 1:00 AM and 6:00 AM, depending on availability of water, as authorized by the Engineer.  Flushing shall be considered incidental to this work and no separate payment will be made.

When in the opinion of COW or the Engineer, the Contractor’s proposed testing and flushing plan is deficient, inadequate, improper, or conditions are such that the impact to existing water service area are adversely affected by service interruptions, the Contractor will be notified in writing by the Engineer.  Such notification shall be accompanied by a statement of the corrective action(s) to be taken.  Contractor shall adhere to the testing and flushing schedule and comply with instruction as directed by the Engineer.

Hydrostatic Testing.  Prior to chlorination and after completion of “open-bore” flushing, hydrostatic testing shall be conducted on all newly constructed water conduit, service lines, fire hydrant leads and stub-outs.  The Contractor shall furnish all necessary assistance, equipment, labor, materials and supplies (including the test pressure gauge) necessary to complete the test to the satisfaction of the Engineer.

The Contractor shall notify the Engineer and COW forty-eight (48) hours (two working days), prior to any test and shall notify the Engineer and COW two (2) hours in advance of the scheduled time if the test is to be canceled.

No hydrostatic test section shall exceed 1,000 feet unless approved by the Engineer in writing.  All main line valves, fire hydrant auxiliary valves, fire hydrant main valves and plugs shall be tested.  All intermediate valves within the section being tested will be fully closed and reopened as directed by the Engineer during the actual test.  Only static pressure will be allowed on the opposite side of the end valves of the section being tested.

All hydrostatic testing will be performed through a test copper.  The test station is to be placed at the highest end of the pipe being tested when there is an elevation change in the pipe greater than ten feet (10’).  The test pressure is not to exceed the maximum allowable operating pressure of the pipe, fittings, valves, thrust restraints, or other appurtenances of the test section.  Use of fire hydrants for testing will not be allowed.  The specified test pressure shall be applied by means of an approved pumping assembly connected to the pipe in a manner satisfactory to the Engineer.

Prior to hydrostatic testing, all air shall be expelled from the conduit.  If permanent air vents are not located at all high points, the Contractor shall, at the Contractor expense, install corporation cocks at such points so the air can be expelled as the conduit is slowly filled with water.

The Contractor shall incorporate a COW provided test pressure gauge to confirm the hydrostatic test results.  The gauge shall be returned to the COW at the completion of the hydrostatic testing.

In the instance where connection is made to an existing water conduit, a new valve shall be installed on the connection.  The Contractor shall suitably seal off the outlet leading to the existing conduit prior to making the field tests.

Hydrostatic testing of water lines containing a chlorine mixture above 2 ppm will not be allowed.

The minimum hydrostatic test pressure is to be one hundred fifty pounds per square inch (150 psi) for a minimum duration of thirty (30) minutes for non-fire lines.  Fire lines are to be tested at two hundred pounds per square inch (200 psi) for a minimum duration of two hours.

Pumping will be terminated and disconnected upon starting the test.  The test pressure at the start of the test is to be maintained for the duration of the test period.  Any loss of pressure will be considered a failed pressure test. Cracked or defective conduit, gaskets, mechanical joints, fittings, valves or hydrants discovered as a consequence of the hydrostatic tests shall be removed and replaced with sound material at the Contractor's expense.  The test shall then be repeated until the results are satisfactory.

Continuity Tests.  The Contractor shall perform electrical conductivity tests on all DIP water mains in the presence of the Engineer and COW.  Continuity testing shall also be performed on all DIP water service connections and extensions greater than two inches in diameter.  The Contractor shall maintain a circuit of 600 amperes DC current for a period of 15 minutes.  Return current shall be at least 90 percent of the input current.  All equipment necessary to maintain the circuit shall be supplied by the Contractor.

All continuity tests will be through wires brought to the surface or through ¾-inch minimum copper pipe connected to the main.  The use of water service thaw wires, fire hydrants and valves, as substitutes for wires will not be accepted.  All wires brought to the surface to complete the continuity test are to be placed in a valve box adjustment sleeve.

Removal of Test and Air Vent Copper Pipe.  After completion of testing, all test and air vent copper pipe shall be removed, and the corporation stop closed at the main, in the presence of the Engineer and COW.  In addition, a visual inspection for leaks will be performed in the presence of the Engineer and COW.

627-3.07 DISINFECTION.  All portions of the water system shall be disinfected, including small sections of pipe, all valves and stops and any portion of the existing connection system that might have become contaminated during construction activities.  Disinfection shall be accomplished after completion of pressure and/or leakage tests in compliance with AWWA C651, Disinfecting Water Mains.

Disinfection.  Chlorine shall be used for disinfection.  Chlorine shall be applied by using a calcium hypochlorite and water mixture.  Calcium hypochlorite shall be comparable to commercial products known as HTH, Perchloren, or Machochlor.  The chlorinating agent shall be applied at the beginning of the section adjacent to the feeder connection, insuring treatment of the entire line.  Water shall be fed slowly into the new line with chlorine applied in amounts to produce a dosage of 25 ppm.  Application of the chlorine solution shall continue until the required dosage is evident at extremities of the newly laid line.  Under no circumstances shall the chlorinating agent be introduced through a fire hydrant.

Calcium hypochloride shall be injected or pumped into the water main.  During the chlorination process, intermediate valves and accessories shall be operated.  Valves shall be manipulated so that the strong chlorine solution in the line being treated will not flow back into the line supplying the water.  Hydrostatic testing of a water line containing the chlorine mixture will not be allowed.  A residual of not less than 10 ppm chlorine shall be produced in the water main and retained for a minimum period of 24 hours, after which this residual shall be flushed from the line at its extremities until the replacement water tests are equal chemically and bacteriologically to those of the permanent source of supply.  In no instance shall a water main be chlorinated before flushing.  The Contractor shall provide a plan for approval by the Engineer for disposal of chlorinated waters from the disinfection of the system.  The governing authority shall approve the discharge location.

Table 627-2 is to be used as a guide for chlorinating mains by the calcium hypochlorite and water mixture method.  The given dosage per 100 feet results in a chlorine solution of 25 ppm.  Depending on the chlorinating agent used, the dosage must be adjusted based on the associated purity.  Caution should be exercised against producing too high a concentration of chlorine in the line.

Table 627-2

| Pipe Diameter (inches) | Dosage (oz.) per 100 feet |
| --- | --- |
| 6 | 0.76 |
| 8 | 1.34 |
| 10 | 2.10 |
| 12 | 3.02 |
| 16 | 5.37 |

After completion of all testing, including bacteriological tests, all test and air vent copper pipe shall be removed, and the corporation cock closed at the main in the presence of the Engineer and COW.

Contractor shall prepare and submit a written plan to ADEC for disposal of chlorine solution used for disinfection of water lines.  Upon ADEC approval, Contractor shall dispose of chlorine solution in accordance with the plan.

627-3.08 GALVANIC ANODES.  Galvanic anode installation shall be accomplished as specified and shown on the Drawings and as specified herein.  The following is a list of general procedures utilized for typical installation of galvanic anodes.

- Anode Installation

Anodes shall be installed 18” to 36” from the sidewall of the pipe, to a centerline depth in-line with the approximate horizontal plane of the pipe’s BDC.  One anode may not protect more than twenty-seven feet (27’) of pipe segments.  One anode on all fittings within a twenty-foot (20’) radius as long as all fittings are electrically connected to the anode.  Exact anode location shall be shown on the Record Drawings.

- Lead Wire Connection to Pipe

The No. 10 AWG HMWPE lead wires shall be attached to the top of the pipe.  Lead wire connection to the pipe shall utilize exothermic weld connection methodology as outlined above and on the drawings.  Contractor shall follow exothermic manufacturer’s recommendations and instructions for use.

- Backfilling

Anodes or lead wires damaged during backfill procedures shall be repaired at no additional cost to the Department.

627-3.10 AS-BUILT DRAWINGS AND RECORD DOCUMENTS.  A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed for both sewer and water work.  This as-built information shall be recorded on a print of plans affected and on the applicable pages of the specifications with supplementary notes.  This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed.  The Contractor shall maintain record documents on the job site consisting of a complete set of plans, survey line and grade books, and other contract documents, and keep them current on a daily basis. Record documents shall be available to the Engineer at all times.  The Engineer may periodically review the status of the record documents during the course of the work.  Failure to keep the record documents current and in the required condition will be considered cause for withholding progress payments.

Conduit and appurtenances shall be referenced by stationing, showing design line and grade and as-built line and grade.

The Contractor shall prepare as-built drawings as the work progresses and final record drawings as described below.  Acceptable record drawings will be prepared on copies of the project construction drawings to depict all lines, grades, locations, materials, and other elements of the work as actually constructed with clearly marked final elevations and locations with actual dimensions.  Noted stations, elevations, slopes and other design dimensions shall be shown on the construction drawings with “ASB” if no change occurs in the field.

The Contractor shall survey the work and all utilities and obstructions encountered during construction in a manner producing an accuracy of 0.03 feet vertically and 0.5 feet horizontally, and reference that as-built information to both project survey control and to pipe stationing.

The Contractor shall submit as-built drawings to the Engineer for review each month, providing five (5) working days to review and approve the information, or to return the drawings for additional information.  The Engineer will review all Record Documents for completeness and conformance to standards.  The Contractor shall make all corrections, changes, additions, and deletions required by the Engineer.

The Contractor shall prepare final record drawings on a clean set of full-sized construction plans at the completion of water & sewer construction as follows:

- Note the name of the person who prepared the record drawings, the Contractor, and the date of preparation in the appropriate title block on each record drawing sheet.

- Make all additions and collections neat, clean, and legible in red ink or red pencil to clearly describe the work as actually constructed.  Identify any and all changes to the original design.  If additional plan sheets are required, prepare them on reproducible mylar-type material and sized as the original plans.

- Complete the revisions in conformance with the scale of the drawings.

- Show each change, deletion, or omission with the appropriate entries and symbols.  Draw one straight line through stationing, elevations, and/or notes.  Crossed out information must remain legible.  For every entry on the construction drawings that was not changed in the field, mark “ASB” next to that entry.

- Cross-hatch any deleted or relocated water or sanitary sewer.

- Note reference information used to prepare record drawings, such as change orders and field books.

- Make profile changes with new elevations or stationing entries only, unless the change is significant.  If the change exceeds 1.5 feet, cross-hatch the original pipe and redraw the profile line.

- Provide complete information for all water and sanitary sewer services that were reconnected or constructed.  If the service was reconnected, record the size and material of the service and the centerline station at the main.  If the service was constructed, also provide horizontal and vertical locations at the property or lease lot line through a GPS enabled survey, and note on the final record drawings.

- Provide complete tables for each water and sanitary sewer service showing the material and size of the service pipe, stationing of the service at the main and the location and elevation of each service at the property line.

The Contractor shall clearly stamp the as-built drawings “Record Drawings” and submit them to both the Engineer and COW for approval.  Approved final Record Documents, bearing certification by the Contractor that the Record Documents are a complete and accurate representation of the project as constructed must be delivered to the Engineer within thirty (30) days of Substantial Completion of water and sewer construction.

When the water system additions are complete, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specification by written signature endorsement and deliver them to both the Engineer and COW prior to final acceptance of the system.  The Contractor will be required to provide signed Record Drawings prior to final payment.

627-4.01 METHOD OF MEASUREMENT.

- Water Conduit.  Measurement for water conduit with appurtenances will be per linear foot of horizontal distance of the various sizes and classes furnished and installed as set forth in the Bid Schedule.  Measurement will be from station to station as staked in the field and as shown on the plans.  No deduction in length will be made for valves and fittings.

- Fire Hydrant Installation.  Measurement for fire hydrant installation shall be per each new hydrant assembly.

- Fire Hydrant Removal.  Measurement for fire hydrant removal shall be per each removed hydrant.

- Water Service Connection.  The quantity will be paid by the number of services installed.

- Gate Valves and Valve Boxes.  The quantity to be paid by the number of valves installed. Valve boxes shall be incidental to valves.

- Adjustment of Valve Box.  Measurement shall be per unit, complete in place.  One adjustment includes the adjustment of the valve box one time down and up.

- Remove and Replace Water Valve Box and Lid.  Measurement shall be per unit, complete in place.

- Galvanic Bag Anode.  The quantity to be paid will be the actual number furnished, installed, and accepted.

- Water System As-Built Drawings.  Record drawings will be measured by acceptance of completed As-Built drawings for section 626 and 627 work items.

627-5.01 BASIS OF PAYMENT.  All labor, tools, equipment, fittings, pipe, and demolition necessary to connect new water mains to the existing water mains as shown on the drawings, is subsidiary.

The contract price for Water Conduit includes trench excavation, shoring as required, dewatering as required, bedding, backfill, with native soils, compaction, pipe, fittings, tees, reducers, crosses, bends, repair of or provision of polyethylene encasement on ductile iron pipe, couplings, testing, disinfection, etc., unless covered under a specific pay item.  Any excavation below plan grade approved by the Engineer shall be paid under Item 203.0003.___ Unclassified Excavation.  Backfill and bedding to replace unsuitable material shall be paid in accordance with Section 203.

The cost for coordinating and providing trenching operations, as well as all parts of the fire hydrant assembly between the water main and the hydrant, for hydrant installation is incidental to the fire hydrant installation.  Measurement and payment for the guard posts shall be incidental to Pay Item 627.0005.____ Fire Hydrant Installation.  No deduction will be made for guard posts not installed at the direction of the Engineer.

The contract price for Water Service Connection includes installation of curb stop, valve box, service pipe and connection to a new or existing water main with a service saddle, tapped, coupling or corporation stop, anode, and tape coating, as shown on the Plans.

Unless specific pay item is listed below, pipe, hydrants, valves, and appurtenances called out on the Plans to be removed shall be an incidental item of construction.  All removed materials shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.

Landscaping, disinfection, testing, couplings and/or thrust blocks, and encasement or replacement of existing sewer lines is subsidiary.

Any costs involved in service changeovers and providing temporary water service are subsidiary.

Full payment for items in Section 627 may be held until such time that record drawings are approved by the Engineer and Contractor signs final record drawings.

Protection of valve boxes and lids, repair and/or restoration of existing improvements on private property, such as fences, and repair of existing utilities damaged by the Contractor will not be paid for directly but will be considered subsidiary to Section 627 pay items.

All Work required to coordinate with facility owners and to shore (includes engineering, developing, implementing, and removal of shoring setups), adjust, remove and replace, and/or relocate existing facilities within the working area/excavation limits associated with the pay items in Section 627 is subsidiary to those items.

Repairs to facilities damaged or rendered inoperable, after the pre-construction inspection and before the final inspection, are the responsibility of the Contractor and no additional payment will be made.

The same valve box shall not be paid for under a separate pay item if it is paid for under Item 627.0009.____ Gate Valve, __ Inch.  In particular, related work includes, but is not limited to, removal of debris from inside the valve box standpipe, trench excavation and backfill, disposal of unsuitable or surplus material, mechanical compaction, adjust mainline valve box to finish grade, replace broken valve box components, and classified material.

The pre-inspections and post inspections are subsidiary to other pay items.  Contractor is responsible for protecting valve boxes and lids prior to and after installation.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 627.0005.____ | Fire Hydrant Installation | Each |
| 627.0007.____ | Fire Hydrant Removal | Each |
| 627.0008.____ | Water Service Connection | Each |
| 627.0009.____ | Gate Valve, ____ Inch | Each |
| 627.2012.____ | HDPE Water Conduit, ____ Inch, SDR __ | LF |
| 627.2015.____ | Galvanic, ____ | Each |
| 627.2017.____ | Water System As-Built Drawings | LS |

CFHWY00599

SECTION 633
SILT FENCE

Standard Modification

633-2.01 MATERIALS.

Replace "Silt Fence	Subsection 729-2.04” with the following:

Silt Fence	Subsection 729-2.02

633-3.01 CONSTRUCTION REQUIREMENTS.

Replace the first sentence with the following:

Install silt fence according to the SWPPP, Appendix B.

CR633.HSM20.13-113020

Special Provisions

Replace Section 639 with the following:

SECTION 639
DRIVEWAYS

639-1.01 DESCRIPTION. Construct driveways and approaches.

639-2.01 MATERIALS.  Reserved.

639-3.01 CONSTRUCTION.  Reserved.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed.

639-5.01 BASIS OF PAYMENT.  The Contract unit price for driveways and approaches is for furnishing equipment and labor.

Pavement removal and excavation required constructing driveways and approaches is subsidiary to the driveway and approach pay items.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 639.0001.____ | Driveway | Each |
| 639.0002.____ | Driveway, Residential | Each |
| 639.0003.____ | Driveway, Commercial | Each |
| 639.2000.____ | Approach | Each |

CR639-092016R

Special Provision

Replace Section 641 with the following:

- SECTION 641
EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION.

Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this Section and applicable local, state, and federal requirements, including the Alaska Pollution Discharge Elimination System (APDES) Construction General Permit (CGP). The state APDES program is administered by the Department of Environmental Conservation (DEC). Section 301(a) of the Clean Water Act (CWA) and 18 AAC 83.015 provide that the discharge of pollutants to water of the U.S. is unlawful except as allowed by the CGP.

641-1.02 DEFINITIONS.

These definitions apply only to Section 641.

ACTIVE TREATMENT SYSTEM (ATS) OPERATOR. CGP Appendix C.

ALASKA CERTIFIED EROSION AND SEDIMENT CONTROL LEAD (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years. (See Qualified Person)

ALASKA DEPARTMENT OF ENVIRONMENTAL CONSERVATION (DEC).  The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

ALASKA GENERAL PERMIT FOR EXCAVATION, DEWATERING (Excavation Dewatering Permit).

Permit authorizing excavation dewatering discharges from Construction Activities.

ALASKA MULTI-SECTOR GENERAL PERMIT (MSGP). Permit authorizing storm water discharges associated with Industrial Activity.

ALASKA POLLUTANT DISCHARGE ELIMINATION SYSTEM (APDES). A system administered by DEC that issues and tracks permits for storm water discharges.

BEST MANAGEMENT PRACTICES (BMPS). CGP Appendix C.

CLEAN WATER ACT (CWA).  Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

CONSTRUCTION ACTIVITY. Ground disturbing activity by the Contractor, Subcontractor or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. CGP Appendix C.

CONSTRUCTION GENERAL PERMIT (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by Alaska DEC. It authorizes storm water discharges providing permit conditions and water quality standards are met.

U.S. ARMY CORPS OF ENGINEERS PERMIT (COE Permit). U.S. Army Corps of Engineers Permit for construction in waters of the U.S. may be issued under Section 10 of the Rivers and Harbors Act of 1899, or Section 404 of the Clean Water Act.

ELECTRONIC NOTICE OF INTENT (ENOI). CGP Appendix C.

ELECTRONIC NOTICE OF TERMINATION (ENOT). CGP Appendix C.

ENVIRONMENTAL PROTECTION AGENCY (EPA). The federal agency charged to protect human health and the environment.

ERODIBLE STOCKPILE. Any material storage area or stockpile consisting of mineral aggregate, organic material, or a combination thereof, with greater than 5 percent passing the #200 sieve, and any material storage where wind or water transports sediments or other pollutants from the stockpile.  Erodible Stockpile also includes any material storage area or stockpile where the Engineer determines there is potential for wind or water transport of sediments or other pollutants away from the stockpile.

EROSION AND SEDIMENT CONTROL PLAN (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

FINAL STABILIZATION. CGP Appendix C, "Stabilization".

HAZARDOUS MATERIAL CONTROL PLAN (HMCP).  The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

MUNICIPAL SEPARATE STORM SEWER SYSTEM (MS4) PERMIT.  A DEC storm water discharge permit issued to certain local governments and other public bodies, for operation of storm water conveyances and drainage systems. CGP Appendix C.

OPERATOR(S). The party(s) responsible to obtain CGP permit coverage. CGP Appendix C.

1.	Contractor – the Contractor is an Operator inside and outside the Project Zone.

2.	Department – the Department is an Operator inside the Project Zone.

POLLUTANT. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sediment, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

PROJECT ZONE. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Contract.

Material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

QUALIFIED PERSON. CGP Appendix C and Section 641-1.04.

SPILL PREVENTION, CONTROL, AND COUNTERMEASURE PLAN (SPCC PLAN). The Contractor’s detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

SPILL RESPONSE FIELD REPRESENTATIVE. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

STORM EVENT. CGP Appendix C.

STORM WATER POLLUTION PREVENTION PLAN (SWPPP). The Contractor's plan for compliance with the CGP for construction activities inside the Project zone, CGP Appendix C and Section 641.

STORM WATER POLLUTION PREVENTION PLAN TWO (SWPPP2). The Contractor's plan for compliance with the CGP and MSGP for construction activities outside the Project Zone.

SUPERINTENDENT. The Contractor's duly authorized representative with authority and responsibility for the overall operation of the Project and Contractor furnished sites and facilities.

SWPPP AMENDMENT. A modification to the SWPPP. CGP Part 5.0.

SWPPP MANAGER. The Contractor's Qualified Person with authority and responsibility. CGP Appendix C.

SWPPP PREPARER. The Contractor’s Qualified Person with authority and responsibility. CGP Appendix C.

TEMPORARY STABILIZATION. CGP Appendix C, "Stabilization".

641-1.02.01 REFERENCE.

A list of websites and documents referenced herein, including SWPPP preparation documents and construction forms, are available at the DOT&PF Statewide Design and Engineering Services Storm Water web page and Construction Forms webpage.

DEC Permit information is available at the DEC Division of Water webpage.

641-1.03 PLAN AND PERMIT SUBMITTALS.

For plans listed in Subsection 108-1.03.5 (SWPPP, HMCP, and SPCC), use the Contractor submission and Department review deadlines identified in this subsection.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1.	Storm Water Pollution Prevention Plan. Submit one electronic copy (single PDF file) and one hard copy of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14-day review period will restart when the contractor submits an electronic copy and one hard copy of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved and certified by the Department using Form 25D-109, the Contractor must certify the approved SWPPP using Form 25D-111. See Subsection 641-1.03.4 for further SWPPP submittal requirements.

Submit the final SWPPP. Transmit an electronic copy (single pdf file) of the final SWPPP to the Engineer when the Contractor's eNOT is filed, or within 30 days of the Department's eNOT being filed, whichever is sooner. Include all SWPPP documents.

2.	Hazardous Material Control Plan. The HMCP Template is available at the DOT&PF Construction Forms webpage. The HMCP submittal, review timeline, and signature requirements are the same as the SWPPP.

3.	Spill Prevention, Control, and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and one hard copy of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

4.	CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. Do not use the SWPPP for Construction Activities outside the Project Zone where the Department is not an operator. For Construction Activities outside the Project Zone, the Contractor must use a SWPPP2. Department approval is not required for a SWPPP2.

After the Department certifies the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to DEC for coverage under the CGP. Submit a copy of the signed eNOI and DEC’s written acknowledgement (by letter or other document), to the Engineer as soon as practicable and no later than three days after filing eNOI or receiving a written response.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to DEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and DEC’s written acknowledgment (by letter or other document), for inclusion in the SWPPP.

Before Construction Activities occur, transmit to the Engineer an electronic copy and one hard copy of the approved and certified SWPPP, with signed Delegations of Signature Authorities on Forms 25D-107 and 25D-108, SWPPP Certifications on Forms 25D-111 and 25D-109, both permittee’s signed eNOIs and DEC’s written acknowledgement.

5.	DEC SWPPP Review.  When CGP Part 2.1.3, or 2.1.4 requires DEC SWPPP review:

a.	Transmit a copy of the Department-approved SWPPP to DEC using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation; and

c.	Retain a copy of delivery receipt confirmation in the SWPPP.

6.	Local Government SWPPP Review.  When local government or the CGP Part 2.1.4, requires local government review:

a.	Transmit a copy of the Department-approved SWPPP and other information as required to local government, with the required fee.  Use delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation;

c.	Transmit a copy of any comments by the local government to the Engineer within seven days of receipt;

d.	Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven days of receipt of the comments;

e.	Include a copy of local government SWPPP review letter in the SWPPP; and

f.	File a notification with local government that the project is ending.

7.	Modifying Contractor’s eNOI.  When required by the CGP Part 2.7, modify your eNOI to update or correct information within 30 calendar days of the change. Reasons for modification are in the CGP Part 2.7.1. The Contractor must submit an eNOT instead of an eNOI modification when the operator has changed. The new operator must file an eNOI to obtain permit coverage.

641-1.04 PERSONNEL QUALIFICATIONS.

Provide documentation in the SWPPP that the individuals serving in these positions meet the personnel qualifications. The Department accepts the following certificates as equivalent to AK-CESCL: Certified Professional in Erosion and Sediment Control (CPESC), or Certified Inspector in Sediment, and Erosion Control Certified (CISEC). These equivalent certificates are included in the CGP Appendix C and repeated below.

TABLE 641-1.04 PERSONNEL QUALIFICATIONS

| Personnel Title | Required Qualifications |
| --- | --- |
| SWPPP Preparer | 1. Current certification as a Certified Professional in Erosion and Sediment Control (CPESC); or 2. Current certification as AK-CESCL, and at least two years' experience in erosion and sediment control as a SWPPP Manager or SWPPP writer, or equivalent; or 3. Professional Engineer registered in the State of Alaska with current certification as AK-CESCL. |
| Superintendent | Current AK-CESCL, or substitute training from CGP Appendix C, Qualified Person Table 4 |
| SWPPP Manager | Current AK-CESCL or substitute training from CGP Appendix C, Qualified Person Table 4. |
| Active Treatment System Operator | Current AK-CESCL or substitute training from CGP Appendix C, Qualified Person Table 4. ATS operator should possess a recognized certification, or professional standing, or who by extensive knowledge, training, and experience has successfully demonstrated the ability to meet the ATS requirement. |

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT. The eNOI, eNOT, and eNOI Modifications must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12. Signature and certification authority for the eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports.  Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Superintendent position is responsible for signing and certifying the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI, eNOI Modifications, and eNOT.

The Engineer will provide the Department’s delegation on Form 25D-107, which the Contractor must include in the SWPPP.

3.	Subcontractor Certification. Subcontractors must certify on Form 25D-105, that they have read and will abide by the CGP and the conditions of the project SWPPP.

4.	Signatures and Initials.  Certify or initial the CGP documents and SWPPP forms, wherever a signature or initial is required.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

107-1.02 includes the requirements to obtain permits, and to provide permit documents to the Engineer.

1.	The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

2.	The Contractor is responsible for permitting and permit compliance for all construction support activity in the Project Zone and outside the Project Zone. The Contractor has sole responsibility for compliance with DEC, COE, and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. The Contractor is responsible for protection, care, and upkeep of all work, and all associated off-site zones.

3.	The Contractor is responsible for obtaining an Excavation Dewatering Permit (AKG002000) if construction activities are within 1,500 feet of a DEC-identified contaminated site or groundwater plume.

4.	An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.4) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage.

5.	The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas outside the Project Zone;

b.	For Construction Activity and Support Activities outside the Project Zone; and

c.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY.

Relocation Coverage. A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06.  The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work.  Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

1.	SWPPP Preparer and Pre-Construction Site Visit.

Use a SWPPP Preparer to develop the SWPPP according to the CGP, DEC and Department SWPPP Template. Subsection 641-1.02.01 provides directions to templates.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least seven days advance notice of the site visit, so that the Department may participate.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, include the names of attendees and the date.

2. 	Developing the SWPPP.

a.	Meet all CGP requirements.

b.	Use the Department’s ESCP, Environmental commitments, and other Contract documents as a starting point for developing the SWPPP.

c.	Develop the SWPPP with sections and appendices according to the DEC CGP SWPPP Template and DOT&PF SWPPP Template. Include the information required by the Contract and described in the CGP Part 5.0. Use the forms available at the DOT&PF Construction Forms website.

d.	Compile the SWPPP in three ring binders with tabbed and labeled dividers for each appendix. Submit the SWPPP according to Subsection 641-1.03.

3.	SWPPP Considerations and Contents.

a.	The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone.

Construction activity outside the Project Zone must have permit coverage. Document permit compliance according to SWPPP2 requirements.

b.	The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. Describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP. Include the utility companies and other operators performing Construction Activity.

Identify areas:

(1)	Over which each operator has operational control; and

(2)	Where the Department and Contractor are co-operators.

c.	For work outside the Project Zone the SWPPP must identify the entity that has storm water permit coverage, the operator, and areas that are:

(1)	Dedicated to the Project and where the Department is not an operator; and

(2)	Not dedicated to the project, but used for the project.

d.	If the project discharges to a Tier III, Outstanding Natural Resource Water, comply with the CGP Part 2.1.6. Submittal deadlines apply prior to filing an eNOI and beginning construction activities. As of the issuance of the CGP 2021, no Tier III, Outstanding Natural Resource Water is designated in the State of Alaska.

e.	There are special requirements in the CGP Part 3.2, for storm water discharges into an impaired water body. Monitoring of storm water discharges may be required. The Contractor is responsible for monitoring and reporting inside and outside the project zone.

f.	Describe the sequence and timing of activities that disturb soils and BMP implementation and removal. Phase earth-disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities. Include drawings showing each phase of the project with the BMPs implemented in the Phase.

g.	Delineate the site according to the CGP Part 4.2.1.

h.	Minimize the amount of soil exposed and preserve natural topsoil on site, unless infeasible according to the CGP Part 4.2.2.

i.	Describe methods and time limits, to initiate temporary or final soil stabilization. Comply with stabilization requirements in the CGP Part 4.5.

j.	If construction will cease during winter months, describe all requirements for winter shutdown according to the CGP Part 4.12.

k.	Plans for ATS must meet with the requirements in the CGP Part 2.1.5 and 4.6.

l.	Design all temporary BMPs to accommodate a two year 24-hour storm event. Describe and document all installed control measures in the SWPPP according to the CGP Part 5.3.6. Include a citation from a published BMP Manual, publication, or manufacturers specification used as a source, or include a statement "No BMP Manual was used for this design". If using out of state BMPs, follow the instructions in the DOT&PF SWPPP Guide.

m.	Provide a legible site map or set of maps in the SWPPP, showing the entire site and identifying boundaries of the property where construction and earth-disturbing activities will occur. Include all elements described in the CGP Part 5.3.5 and the DEC CGP SWPPP Template Section 5.0.

n.	Identify the inspection frequency in the SWPPP according to the CGP Part 6.1; except, inspect once every seven calendar days regardless of the precipitation amount.

o.	Linear Project Inspections, described in CGP Part 6.5, are not applicable to this Contract.

p.	The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, COE permit, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities that were not included in the Department’s permitting and consultation.

q.	The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the CGP and this specification. See Subsection 641-3.03 for more information.

4.	Recording Personnel and Contact Information in the SWPPP.

Identify the SWPPP Manager as the Storm Water Lead and Storm Water Inspector positions in the SWPPP. Document the SWPPP Manager’s responsibilities in Section 2.0 Storm Water Contacts, of the SWPPP Template and:

a.	Identify that the SWPPP Manager does not have authority to sign inspection reports (unless the SWPPP Manager is also the designated project Superintendent).

b.	Identify that the SWPPP Manager cannot prepare the SWPPP unless the SWPPP Manager meets the Contract requirements for the SWPPP Preparer.

Include in the SWPPP proof of AK-CESCL, or equivalent certifications for the Superintendent and SWPPP Manager, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced, permanently or temporarily, by an acting Superintendent or acting SWPPP Manager; record in the SWPPP, on Form 25D-127, the names of the replacement personnel, and date of replacement. For temporary personnel, record their beginning and ending dates.

Provide 24-hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24-hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, proof of AK-CESCL or equivalent certifications of ATS operators. Record names of ATS operators and their beginning and ending dates, on Form 25D-127.

The Department will provide proof of AK-CESCL, or equivalent certifications for the Department's Project Engineer, Storm Water Inspectors, and Monitoring Person, and names and dates they are acting in that position. Include Department’s staff certifications in SWPPP Appendix E.  Include the Department’s staff names, dates acting, and assignments in Section 2.0 of the SWPPP and on Form 25D-127.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.

Prepare the HMCP using the Department template for the prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

641-2.03 SPILL PREVENTION, CONTROL, AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.

Prepare and implement an SPCC Plan, required by 40 CFR 112; when both of the following conditions are present on the project:

1.	Oil or petroleum products from a spill may reach navigable waters (defined in 40 CFR 112), and

2.	Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons).

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent shall certify the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI and eNOT. The Superintendent may not delegate the task or responsibility of certifying these documents.

The Superintendent may assign certain duties to the SWPPP Manager.

1.	Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

2.	Ensuring the control of erosion, sedimentation, or discharge of pollutants;

3.	Directing and overseeing installation, maintenance, and removal of BMPs;

4.	Performing Inspections; and

5.	Updating the SWPPP including adding amendments and forms.

When Bid Item 641.0007.____ is part of the Contract, the SWPPP Manager must be a different person than the Superintendent, be available at all times to administer SWPPP requirements, and be physically present within the Project Zone or the project office, when construction activities are occurring.

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, and environmental commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS.

Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

Use the seed mixture specified in the Contract or as directed by the Engineer.

Use soil stabilization material as specified in Section 727.

Use silt fences as specified in Section 729.

Use straw and straw products certified weed free of prohibited and restricted noxious weed seed and quarantined pests, according to Alaska Administrative Code, Title 11, Chapter 34 (11 AAC 34). When straw or straw products certified according to 11 AAC 34 are not available, use non-certified products manufactured within Alaska before certified products manufactured in another state, country, or territory. Non-certified straw or straw products manufactured in another state, country, or territory shall not be used. Grass, legumes, or any other herbaceous plants produced as hay, shall not be substituted for straw, or straw products.

641-3.01 CONSTRUCTION REQUIREMENTS.

Comply with the SWPPP and the requirements of the CGP Part 5.0.

1.	Before Construction.

The following actions must be completed before Construction Activity begins:

a.	The SWPPP Preparer must visit the Project. Document the visit on SWPPP Form 25D-106. The SWPPP must be developed, or amended with the findings from the visit.

b.	The SWPPP must be approved by the Engineer on Form 25D-109.

c.	The Contractor must be authorized to begin work by the Engineer.

d.	The Project must have an eNOI for the Department and for the Contractor.

e.	The Department approved SWPPP must be submitted to DEC and Local Governments per CGP Part 2.1.2, Part 2.1.4, and Part 2.4.1.

f.	The Contractor has transmitted to the Engineer an electronic copy, and at least one hardcopy of the approved SWPPP.

g.	The Delegation of Authority, Forms 25D-108 and 25D-107, for both the Contractor and Engineer are signed.

h.	Main entrance signage must meet the requirements of CGP Part 5.10.2.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can safely read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes.

i.	Track precipitation according to CGP Part 7.3.9. Submit the method to track precipitation to the Engineer for approval.

2.	During Construction.

a.	Delineate The Site. Comply with the CGP Part 4.2.1.

b.	BMPs. Install BMPs according to the SWPPP prior to the initiation of ground disturbance.

c.	Document subcontractors. Provide a copy of the SWPPP and the CGP to all subcontractors and utility companies before they begin soil-disturbing activities. Verify they understand and comply with the SWPPP and CGP.

(1)	Document all subcontractors and utility companies that may work on the site, according to the CGP Part 5.3.1, and SWPPP Section 1.2.

(2)	Require subcontractors and utility companies to sign the SWPPP Subcontractor Certification, Form 25D-105. Include Form 25D-105 in the SWPPP Appendix E.

(3)	Inform subcontractors and utility companies, in a timely manner, of SWPPP amendments that affect them. Coordinate with subcontractors and utility companies to protect BMPs, including temporary and final stabilization from damage.

(4)	Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

d.	Provide Training. Provide ongoing training to all employees, subcontractors, and utility companies according to the CGP Part 4.14.

(1)	Provide training no less than once a month during construction activity;

(2)	Document training in the SWPPP Training Log on Form 25D-125. Include the training record in the SWPPP Appendix l.

e.	Protection and Restoration. Comply with Subsection 107-1.11.

f.	Good Housekeeping Measures.  Comply with the SWPPP and CGP Part 4.8.

g.	Control Measures. Comply with the SWPPP and CGP Part 5.3.6.

(1)	 Maintain BMPs.

(2)	Comply with requirements of the HMCP and SPCC Plan, and all local, state, and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

(3)	Keep the SWPPP and HMCP current, Subsection 641-2.01.3, SWPPP Considerations and Contents.

3.	Winter Construction.

If winter construction activity occurs, the project must have BMPs in place, Part 4.12.2. Inspections can be reduced to once per month if the project meets the CGP Part 6.2.4.

4.	Storm Water Discharge Pollutant Reporting Requirements.

If an incident of non-compliance occurs, that may endanger health or the environment, a report must be made, CGP Appendix A, Part 3.4.

A permit non-compliance is any type of pollutant, such as turbidity or petroleum that enters storm water runoff and flows into a receiving water body, MS4, or wetland that is connected to waters of the U.S.

a.	Report the incident to the Engineer immediately;

b.	Report to DEC orally within 24 hours after the permittee becomes aware of the incident; and

c.	Report to DEC in writing within five days after the permittee becomes aware of the circumstances. To report in writing, complete the written noncompliance report on Form 25D-143, and file the written report with DEC. Coordinate the report with the Engineer. Include in the report:

(1)	A description of the noncompliance and its causes;

(2)	The exact dates and times of noncompliance;

(3)	If not yet corrected the anticipated time the project will be brought back into compliance; and

(4)	The corrective action taken or planned to reduce, eliminate and prevent reoccurrence.

d.	Report an incident of noncompliance with COE Permits to the Engineer immediately. The Engineer will notify the COE.

5.	Hazardous Materials Reporting Requirements.

Report any release of a hazardous substance immediately to the Engineer, as soon as the person has knowledge of the discharge.

Report spills of petroleum products or other hazardous materials to the Engineer and other agencies as required by law, and according to the CGP Part 9.3.

a.	To water.

Any amount of hazardous material released must be reported immediately to the Engineer, DEC, and the Coast Guard.

b.	To land.

Any release of a petroleum product, must be reported as soon as the person has knowledge of the discharge, CGP Part 9.3.2.

(1)	Release in excess of 55 gallons,

(2)	Release in excess of 10 gallons but less than 55 gallons, must be reported to the DEC within 48 hours after the person has knowledge of the discharge, and

(3)	Release in excess of 1 gallon to 10 gallons, must be recorded, logged, and provided to the DEC on a monthly basis.

c.	Use the HMCP and SPCC Plan for contact information to report spills to regulatory agencies.

d.	Implement measures to prevent the reoccurrence of and to respond to the release of hazardous materials.

e.	Prior to disposal of contaminated material, submit a Contaminated Media Transport and Treatment Disposal Approval Form to the DEC Division of Spill Prevention and Response. Dispose as approved by the DEC.

6.	Maintenance of BMPs and Corrective Action.

Implement maintenance and corrective action as required by the CGP Part 4.13 and Part 8.0, SWPPP, and manufacturer’s specifications, whichever is more restrictive.

a.	Implement corrective actions. Comply with the CGP Part 8.0 and the SWPPP.

b.	Corrective Action deadlines and documentation.

(1)	Complete Corrective actions according to the CGP Part 8.2.

(2)	Document corrective actions in the Corrective Action Log, Form 25D-112, according to the SWPPP, CGP Part 5.9.2, and Part 8.3.

If a different BMP is installed to correct the condition leading to the corrective action, a SWPPP Amendment must be completed.

(3)	Document the conditions, in the Corrective Action Log, for corrective actions not completed according to the CGP 8.2. Notify the Engineer, and implement the corrective action as soon as possible.

The Engineer may assign a new complete-by date using a Delayed Action Item Report, Form 25D-113 (DAIR Form), if the Contractor is unable to complete the corrective action within the required timeframe. The DAIR Form can only be authorized and completed by the Engineer.

7.	Stabilization.

a.	All Soil stabilization requirements must be met in accordance with CGP Part 4.5 and the SWPPP.

b.	When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community, the hydro-seeder must be located at the project.

c.	Apply temporary seed and stabilization measures after preparing the surface to reduce erosion potential and to facilitate germination and growth of vegetative cover according to Section 618 and 619.

d.	Apply permanent seed and other stabilization measures after land-disturbing activity has permanently ceased. Comply with the CGP, SWPPP, and the Contract Sections 618, 619, 724, and 727.

e.	Incorporate final or temporary stabilization immediately after installing culverts or other drainage structures to satisfy the CGP Part 4.5, SWPPP and Engineer. Stabilize under any bridge and in areas upstream and downstream of culverts, drainages and areas disturbed by related construction activities after installation, or before deactivating stream bypass or diversion.

f.	Stabilization before Fall Freeze-up, and Spring Thaw.

Stabilize Construction Activities within the Project Zone with BMPs prior to the anticipated date of fall freeze-up, according to the SWPPP and CGP Part 4.12.

Exceptions to stabilization prior to anticipated date of fall freeze-up include:

(1)	Where temporary stabilization activities are precluded by snow cover or frozen ground conditions prior to the anticipated date of fall freeze-up, stabilization measures must be initiated as soon as practicable following the actual spring thaw.

(2)	When winter construction activity is authorized by the Engineer and conducted according to the Contract.

8.	Ending CGP Coverage.

a.	The Engineer will determine the date that the following conditions for ending CGP coverage have been met within the Project Zone:

(1)	Land disturbing activities have ceased;

(2)	Final Stabilization has been achieved on all portions of the Project Zone, including Department furnished material sources, disposal sites, staging areas, equipment areas, etc., according to the CGP Part 4.5.2; and

(3)	Temporary BMPs have been removed.

b.	After the Engineer has determined the conditions for submitting an eNOT have been met according to the CGP Part 10.2, the Department will:

(1)	Send written notice to the Contractor with the date that the conditions were met;

(2)	Submit an eNOT to DEC within 30 days, and

(3)	Provide a copy of the eNOT and DEC’s acknowledgement letter to the Contractor.

c.	If the Contractor’s CGP eNOI acreage includes Support Activities and any other areas where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.

d.	The Contractor must submit a copy of each signed eNOT and DEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response. Insert the eNOT and DEC acknowledgement letter in the SWPPP Appendix Q.

e.	The Contractor is responsible for coordinating local government inspections of work and ending permit coverage with local governments. See Subsection 641-1.03.6 for more information.

9.	Ending Inspections, BMP maintenance, and SWPPP Updates in the Project Zone.

The Contractor is responsible for continuing inspections, BMP maintenance, and SWPPP updates until permit coverage is ended.

10.	Transmit final SWPPP.

Transmit one electronic copy of the final SWPPP to the Engineer according to Subsection 641-1.03.1.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.

The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP, and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown.  Update on-site postings if records are relocated during winter shutdown. Provide the Department with copies of all Records.

Retain Records including a copy of the SWPPP, for at least three years after the date of eNOT according to the CGP Part 9.4.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them.  See CGP Parts 5.10, 6.6 and 9.5.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.

Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP using Department forms from the DOT&PF Construction Forms website.

1.	Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP Part 6.0, except inspect once every seven calendar days regardless of the precipitation amount, Subsection 641-2.01.3.n.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s Storm Water Inspector jointly, unless approved by the Engineer, when:

a.	One of the inspectors is not on site, access is only by air, and weather delayed or canceled flights;

b.	One of the inspectors is sick;

c.	The project is on a reduced frequency inspection schedule with no staff on site, the only access to the site is by air, and it is economical to send only one inspector; or

d.	When the Engineer determines a safety concern that makes joint inspection impracticable.

When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within three days of the Inspection date and document the date of the report transmittal in Appendix K.

2.	Inspection Reports.

Use only the Department SWPPP Construction Site Inspection Report, Form 25D-100, to record Inspections. Changes or revisions to Form 25D-100 are not permitted, except for adding or deleting data fields that list: Location of Discharge Points and Site Specific BMPs. Complete all fields in the Inspection Report; do not leave any field blank.

The Superintendent or SWPPP Manager must review and correct all errors within three days of the date of inspection.

Inspection Reports must be signed by the person described in the CGP Appendix A, Part 1.12 or by a duly authorized representative of that person. Only the Superintendent can certify the Inspection Form.

Insert a Complete-by-Date for each corrective action listed that complies with the CGP Part 8.2.

Provide a copy of the completed, unsigned Inspection Report to the Engineer by the end of the next business day following the inspection.

The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. The signed and certified Inspection Report must be provided to the Engineer on the same day the Superintendent signed the form.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days if compliant with the CGP and SWPPP.

If the Inspection Report is not compliant with the CGP or SWPPP, the Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

When an Inspection Report, certified by both the Superintendent and Engineer, requires corrections:

a.	Document the corrections in an addendum memo addressing only the omitted or erroneous portions.

b.	 Superintendent and Engineer sign and certify the updated Inspection Report and the addendum memo.

c.	File the corrected Inspection Report and addendum memo in Appendix K and update the amendment log.

The issuance of an addendum memo does not relieve the Contractor of liquidated damages that may have been incurred as a result of the error on the original certified inspection report.

3.	Items and Areas to Inspect.

Conduct inspections of all areas required by the CGP Part 6.4 and SWPPP.

4.	Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

The frequency of inspections may be reduced according to the CGP Part 6.2.1 if the site is stabilized and the reduced frequency is approved by the Engineer. At actively staffed sites, inspect within two business days of the end of a storm event that results in a discharge from the site.

5.	Winter Shutdown Inspections.

Conduct winter shutdown inspection 14 calendar days after the anticipated fall freeze-up date and conditions under the CGP Parts 4.12.and 6.2.3, and the SWPPP are met. The Engineer may approve suspension of inspections and waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall, Form 25D-115, during winter shutdown.

Inspections must resume on a regular frequency or reduced inspection frequency identified in the SWPPP, at least 21 days before anticipated spring thaw, CGP Part 6.2.3. Resume updating the Daily Record of Rainfall Form at the start of the 21-day spring thaw inspection.

6.	Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion if approved by the Engineer.

7.	SWPPP Amendments and SWPPP Amendment Log.

The SWPPP Amendment Log, Form 25D-114, must be filled out by an individual who holds a current AK-CESCL, or equivalent certification. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

a.	Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

b.	If an Inspection identifies that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

c.	Whenever an Inspection identifies a problem that requires additional or modified BMPs or a BMP not shown in the original SWPPP is added;

d.	If the Inspection frequency is modified (note beginning and ending dates);

e.	When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01;

f.	When an inspection is not conducted jointly;

g.	When an eNOI modification is filed;

h.	When a Noncompliance Report is filed with the DEC.

Place all correspondence with the DEC, EPA or MS4s in Appendix Q.

Amend the SWPPP as soon as practicable after any change or modification, but in no case, later than seven days following identification of the need for an amendment. All SWPPP Amendments must have an amendment number, be dated, and signed.

Keep the SWPPP Amendment Log current. Prior to a scheduled Inspection or submittal of an inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log in appendix M.

8.	Site Maps.

Maintain site maps in accordance with CGP Part 5.3.5 and the SWPPP Template 5.0. It is acceptable to have separate site maps for BMPs, grading and stabilization activities.

9.	Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112.

The Corrective Action Log must document corrective actions required by the conditions listed in the CGP Part 8.0. Document the need for corrective action within 24 hours of either:

a.	Identification during an inspection, or

b.	Discovery by the Department's or Contractor’s staff, a subcontractor, or a regulatory agency inspector.

c.	If a corrective action is discovered outside of an inspection, update the log with the date of discovery, the proposed corrective action, and the date the corrective action was completed.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log in Appendix J.

10.	Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection. Keep the Grading and Stabilization Activities Log organized and completed to demonstrate compliance with the CGP Part 4.5.

Keep the Grading and Stabilization Activities Log in Appendix G.

11.	Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to comply with CGP Part 7.3.9. Submit a copy to the Engineer with each completed Inspection Report. Keep the Daily Record of Rainfall current in Appendix N.

12.	Staff Tracking Log.

Use the SWPPP Project Staff Tracking, Form 25D-127, to identify project staff that are required to be AK-CESCL certified or an equivalent qualification, CGP Appendix C. Complete this form to document the positions of Superintendent, SWPPP Manager, Engineer, DOT&PF Storm Water Inspector, and when these positions have changed personnel, either permanently or temporarily. Update the SWPPP Project Staff Tracking Form within 24 hours of any changes in personnel, qualifications, or other staffing items related to administration of the CGP or Section 641.

641-3.04 FAILURE TO PERFORM WORK.

The Engineer has authority to suspend work and withhold monies for an incident of non-compliance with the CGP, or the SWPPP, that may endanger health or the environment or for failure to perform work related to Section 641.

Non-compliance.

1.	Incidents of Non-compliance. Failure to:

a.	Obtain appropriate permits before Construction Activities occur;

b.	Perform SWPPP Administration;

c.	Perform timely Inspections;

d.	Update the SWPPP;

e.	Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms to the Engineer;

f.	Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

g.	Perform duties according to the requirements of Section 641;

h.	Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control; or

i.	Any other requirements established or included in the Contract.

2.	Notice of non-compliance, either oral or written will include:

a.	Reason/defects

b.	Corrective actions required

c.	Time allowed for completing the corrective action

3.	Levels of Non-compliance and Response correspond with harm to the workers, the public or the environment and whether the harm is:

a.	Not-imminent, the Engineer will either orally or in writing, or both, provide notice to the Contractor indicating the incident of non-compliance.

Contractor's that take corrective action and complete the action to the satisfaction of the Engineer, within the time specified, may return to the status of compliance, and avoid elevating the response to imminent.

b.	Imminent, the Engineer will orally provide notice to the Contractor of non-compliance and promptly provide written notice to suspend work until corrective action is completed.

Additional actions, taken against the Contract whether the level of non-compliance is Not-imminent or Imminent, may include:

a.	Withholding monies until corrective action is completed

b.	Assessing damages or equitable adjustments

c.	Employing others to perform the corrective action and deduct the cost

No additional Contract time or additional compensation is allowed due to delays caused by the Engineer’s suspension of work.

641-3.05 ACCESS TO WORK.

The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies. CGP Part 6.6.

641-4.01 METHOD OF MEASUREMENT.

See Section 109 and as follows:

Item 641.0005.____, measured as specified in the Directive authorizing the work.

Item 641.0006.____, measured as specified in Table 641-2 Version C.

641-5.01 BASIS OF PAYMENT.

1.	BMP Values. Table 641-1 BMP Values – Reserved.

2.	Erosion, Sediment, and Pollution Control - Liquidated Damages. Liquidated Damages assessed according to Table 641-2 are not an adjustment to the Contract amount. These damages charges are related to Contract performance but are billed by the Department to the Contractor, independent of the Contract amount. An amount equal to the Liquidated Damages may be withheld, for unsatisfactory performance, from payment due under the Contract until the Contractor remits payment for billed Liquidated Damages.

TABLE 641-2- VERSION C

EROSION, SEDIMENT AND POLLUTION CONTROL – LIQUIDATED DAMAGES

| Code | Specification Section Number and Description | Deductible Amount in Dollars | Cumulative Deductible Amounts in Dollars |
| --- | --- | --- | --- |
| A | 641-1.05 Failure to have a qualified (AK-CESCL or equivalent) SWPPP Manager | Calculated in Code B or F |  |
| B | Failure to meet SWPPP requirements of: (1) 641-2.01.1 Name of SWPPP Preparer (2) Not Applicable (3) 641-3.03.8 Sign and Date SWPPP amendments by qualified person. (4) 641-3.02 Records maintained at project and made available for review | $750 per omission |  |
| C | Not Applicable. |  |  |
| D | 641-3.03.5 Failure to stabilize a Project prior to fall freeze-up. | $5,000 per Project per year |  |
| E | 641-2.01.1. Failure to conduct pre-construction inspections before Construction Activities on all projects greater than 1 acre. | $2,000 per Project |  |
| F* | 641-3.03. Failure to conduct and record CGP Inspections 641-3.03.1 Personnel conducting Inspections and Frequency 641-3.03.2 Inspection Reports, use Form 25D-100, completed with all required information | $750 per Inspection | Additional $750 for every additional 7 day period without completing the required inspection. |
| G | 641-3.01.4 Corrective action, failure to timely accomplish BMP maintenance and/or repairs. In effect until BMP maintenance and/or repairs is completed. | $500 per Project per day |  |
| H | 641-3.01.3 Failure to provide to the Engineer and DEC a timely oral noncompliance report of violations or for a deficient oral noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| I | 641-3.01.3 Failure to provide to the Engineer and DEC a timely written noncompliance report, use Form 25D-143, of violations or for a deficient written noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| J | 641-3.04 Failure to comply with the requirements of the CGP, approved SWPPP, and Section 641, except as listed above | $750 per occurrence for the first day of noncompliance | Additional $750 for every day the deficiency remains uncorrected |

*CODE F. Liquidated Damages according to Code F will not be billed for typographic errors and minor data entry errors, except the liquidated damages will be assessed for these errors when:

a.	the Contractor has previously been notified and subsequent inspection reports repeat the same or similar error,

b.	multiple inspection reports are submitted after the submission due date and the same or similar errors are repeated on multiple overdue reports,

c.	an error in recording the inspector's AK-CESCL certification date results in an inspector performing the inspection during a period when their certification was lapsed or was otherwise invalid

See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

Item 641.0001.____ Erosion, Sediment, and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and recordkeeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Item 641.0005.____ Temporary Erosion, Sediment and Pollution Control by Directive. At the contingent sum prices specified in the Directive using time and materials to authorize the work, for all labor, supervision, materials, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. Prices for this item will be by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor. All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641.0006.____ Withholding. The Engineer may withhold an amount equal to Liquidated Damages, assessed according to Section 641, from payment due the Contractor. Liquidated Damages for violations of the Contract, CWA, and CGP are determined by the Engineer according to Table 641-2. The Engineer may withhold payment due the Contractors until the Contractor pays the Liquidated Damages to the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Item 641.0007.____ SWPPP Manager. At the Contract lump sum price for a SWPPP Manager that conforms to this specification. When Item 641.0007.____ appears in the Bid Schedule, the SWPPP Manager must be a different person than the superintendent, and must be physically present during construction activity with duties and authority as described in Subsection 641-2.04. When Item 641.0007.____ does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to Item 641.0001.____.

Subsidiary Items.  Temporary erosion, sediment, and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641.0001.____ Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641. This work includes but is not limited to:

1.	Dewatering;

2.	Shoring;

3.	Bailing;

4.	Permanent seeding;

5.	Installation and removal of temporary work pads;

6.	Temporary accesses;

7.	Temporary drainage pipes and structures;

8.	Diversion channels;

9.	Settling impoundment; and

10.	Filtration.

Permanent erosion, sediment, and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense.  Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 641.0001.____ | Erosion, Sediment and Pollution Control Administration | LS |
| 641.0005.____ | Temporary Erosion, Sediment and Pollution Control by Directive | CS |
| 641.0006.____ | Withholding | CS |
| 641.0007.____ | SWPPP Manager | LS |

CR641-123121

Special Provision

Replace Section 642 with the following:

SECTION 642
CONSTRUCTION SURVEYING AND MONUMENTS

642-1.01 DESCRIPTION. Perform surveying and staking essential for the completion of the project and perform the necessary calculations required to accomplish the work in conformance with the Plans and Specifications and industry standard engineering and survey practice.

Furnish and maintain facilities, equipment, and services specified in this section for Digital Terrain Modeling (DTM).  All furnished facilities and equipment remain your property when you complete the work.

642-1.02 DEFINITIONS.

1.	Break Line: A break line defines the horizontal location where TIN lines must break, and snap to the vertical location of the break line.

2.	Catch Point: In the cross section of a road, the point at which the fill or cut slope intersects the edge of the existing ground.

3.	CAD:  Computer-Aided Design.

4.	CORS:  Continuously Operating Reference Station.

5.	DTM: Digital Terrain Model. A computer generated 3D model representing the project terrain, and based on the association of features such as alignments, profiles, sections, grading lines, points, and surfaces.

6.	GLONASS: A radio-based satellite navigation system operated by Russia. GLONASS is an alternative and is complementary to the United States Global Positioning System.

7.	GNSS:  Global Navigation Satellite System.

8.	GPS: Global Positioning System; A radio-based satellite navigation system operated by the United States.

9.	Hinge Point: In the cross section of a road, the point at which any slope intersects another slope of different angle.

10.	Monument: A fixed physical object marking a point on the surface of the earth; used to commence or control a survey; mark the boundaries of a parcel of land; or the centerline of a right-of-way corridor. Monuments will be Primary or Secondary, as shown in the Plans.

11.	Neat-line: Defines the geometric limits of a material, as indicated by the typical section, profile, and alignment.

12.	NGS: National Geodetic Survey; United States Government Agency that provides information and products related to the definition and management of the NSRS.

13.	NSRS: The National Spatial Reference System.

14.	OPUS: On-line Positioning User Service; The National Geodetic Survey operates OPUS as a means to provide GPS users easier access to the NSRS.

15.	Point: An identified spot located on the surface of the earth. For the purpose of this definition, a point can be either physical or electronic depending on the context in which it is used. Physical points include PK nails, wooden hubs, rebar, large nails, or other structures capable of being utilized as a marker. Electronic points include all points generated by computers or electronic surveying equipment.

16.	PPK: Post Processed Kinematic; PPK surveys are similar to RTK surveys, except there is no radio communication between the reference station and the rover, so the rover cannot process a position in “real time”. Survey data from both the reference station and rover is imported into GPS processing software to determine the measured position.

17.	Reference Monument: A monument placed at a known distance and direction from a property corner or other survey point, usually not on a property or survey line. A reference monument is employed to perpetuate a corner/point that cannot be monumented at its true location or where the corner monument is subject to destruction.

18.	RTK: Real Time Kinematic; RTK surveys utilize two or more receivers with at least one receiver remaining stationary over a known coordinate. The radio at the reference station broadcasts its position to the rovers and the system processes the baselines in “real time” allowing for project coordinate information to be gathered and analyzed during the actual field survey.

19.	Slope Staking: The process of using measurements and calculations to determine where to begin a cut or fill, the slope ratio, and the depth of the cut or fill.

20.	Static: Static survey methods require multiple GPS receivers to collect data over the course of a long period of time. The data collected by the receivers is downloaded into a GPS processing software program to determine the measured position.

21.	Surveyor: The Contractor’s Professional Land Surveyor placed in “responsible charge”, and currently registered in the State of Alaska as defined in AS 08.48.341.

22.	Tessellation Spacing: The distance along a line or an arc that a TIN point is created.

23.	TIN: Triangulated Irregular Network; A vector based representation of a physical land surface.

24.	Witness Corner: A point or monument placed at a known distance and direction from a property corner or other survey point. A witness corner is employed to witness the location of a corner/point that cannot be monumented at its true location.

25.	Weeding: A procedure used to limit the frequency of information displayed.

642-2.01 MATERIALS.

1.	Monument Cases: Use castings meeting AASHTO M 105, Class No. 30A. Coat castings with a bituminous damp-proof coating. Bolting tops shall be used.

2.	Primary Monument: A minimum 2 3/8” diameter nonferrous pipe at least 30 inches long, with a minimum 4-inch flange at the bottom and having magnets attached at the top and bottom. A minimum 3 1/4” diameter nonferrous metal cap shall be permanently attached to the top. Mark the cap around the outside edge with the words “STATE OF ALASKA DOT&PF". Permanently stamp every monument with the Surveyor’s registration number, the year set, and the point/corner identification. Orient cap so that the data may be read when the reader is facing north, except for centerline monuments that will be oriented to be read facing up-station.

3.	Secondary Monument: A minimum 5/8 inch x 30 inch rebar with a 2-inch aluminum cap attached to the top. Permanently stamp every secondary monument with the Surveyor’s registration number, the point/corner identification, and the year set.

CONSTRUCTION REQUIREMENTS

642-3.01 GENERAL REQUIREMENTS. Work classified as Land Surveying under AS 08.48, and work involving the location, control, and monumentation of construction centerline and right-of-way, shall be performed by or directly under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor.

Use competent, qualified personnel and suitable equipment for construction surveying activities. The Surveyor’s personnel shall be supervised and trained in the avoidance of systematic errors. The Surveyor’s personnel shall be familiar with geodetic concepts and least-squares adjustments. Correcting errors resulting from the operations of said personnel shall be at the Contractor expense. The Contractor is responsible for the accuracy of the work.

Schedule a mandatory Pre-Survey Conference with the Engineer, Contractor, Surveyor, and all personnel who are to be involved in the survey work, two weeks prior to beginning survey work. The purpose of this meeting will be to discuss methods and practices of accomplishing the required survey work.

Furnish computer services to accomplish the work. All data shall be signed by the Surveyor for completeness and accuracy. As soon as practical after completion of the work, and in no case later than acceptance of the project, deliver field books, computer forms and computer output data to the Engineer. Furnish all computer generated data in a file format and medium that is compatible with Department software. This data becomes the property of the State of Alaska.

Furnish field survey notes. Keep field notes in standard bound notebooks in a clear, orderly, and neat manner consistent with the State of Alaska DOT&PF Construction Surveying Requirements. Make field books available for inspection by the Engineer’s project personnel at any time. Copies of the field books shall be kept in a separate secure location.

Furnish all equipment including but not limited to vehicles, stakes, measuring tapes, levels, rods, lasers, GPS receivers, total stations, traffic control devices, safety devices and other equipment necessary for establishing, checking and maintaining the required points, lines and grades.

Furnish traffic control necessary for surveying activities in accordance with Section 643, and the latest edition of the Alaska Traffic Manual (ATM). Outfit all field employees with appropriate High Visibility Clothing as defined in Section 643, Subsection 3.11.

The Engineer may randomly spot check the Contractor's surveys, staking, and computations. The Department assumes no responsibility for the accuracy of the work.

The Engineer has the right to communicate directly with the Surveyor. Any communication regarding changes to the original scope of work shall go through the Contractor.

The Surveyor is responsible for:

1.	Maintaining registration as a Professional Land Surveyor in the State of Alaska.

2.	Maintaining familiarity with the site conditions and progress of the project.

3.	Determining the accuracy required for each survey stake.

4.	Following the State of Alaska DOT&PF Construction Surveying Requirements.

5.	Notifying the Engineer of conflicts and changes necessary due to utilities, match point variations, design revisions, or other variables.

6.	Slope Staking.

7.	Staking all clearing and/or grubbing limits. Clearly identify all trees that are specified to remain.

8.	Staking and hubbing all layers of material shown in the typical sections, including the bottom of excavation, top of borrow, top of base course, and top of surcharge.

9.	Staking all culverts, curbs, inlets, and other drainage appurtenances.

10. Staking all bridge and pedestrian over/under-crossings.

11.	Staking all right-of-way and material source limits.

12.	Rabbit tracking for temporary and permanent pavement striping, and pavement marking devices.

13.	Weekly settlement platform elevation monitoring.

14.	Development of DTM’s, and plotted cross sections.

15.	As-built and Topographic surveying.

16. Performing elevation readings on settlement platforms.

17.	Removal and disposal of all flagging, lath, stakes and other staking material after the Project is completed. Burning of material is not allowed on the project.

18.	All other surveying and staking necessary to complete the project.

642-3.02 MONUMENTS.  The Department will reference and replace all monuments identified on the plans. The Surveyor shall notify the Engineer immediately of any monuments encountered that are not identified on the plans. The Engineer will determine whether the monuments encountered are to be referenced or adjusted by the Surveyor or the Department.

If directed by the Engineer, the adjustment of monument cases or the referencing of monuments not identified on the plans will be considered additional work and paid by 642(3), Three Person Survey Party. Set existing monument cases to be adjusted to new elevations in the manner and at the elevations directed.

The Surveyor shall complete and stamp a State of Alaska Land Survey Monument Record form for each primary and secondary monument referenced. Provide the required survey information on the form in accordance with statutory requirements, including the project name/number, section, township, and range. Meet requirements for recording at the District Recorder’s Office in which the project is located for each monument record. Deliver conforming copies of the recorded forms to the Engineer before monument removal or disturbance.

642-3.03 SURVEY CONTROL. The basis of project control is identified in the Survey Control Sheet. Use the calibration parameters shown in the Survey Control Sheet to Calibrate/Localize/Convert to the local project coordinate system. Contact the AK DOT&PF Central Region Survey Manager through the Engineer for calibration parameters if they are not shown in the plans. Independently recover and verify all survey control points shown in the Survey Control Sheet. Establish and verify new reference points where required, to replace missing points. Notify the Engineer immediately if a reference point is discovered to be in error, or a reset point is not in harmonious relationship to the existing control points. Provide the Engineer a signed hard copy verifying vertical loop closure of project control points.

The use of RTK is not an acceptable method for establishing additional horizontal or vertical control. Horizontal control points may be established using Static GPS or conventional traversing methods. Vertical control points shall be established with differential levels.

Survey accuracy requirements shall conform to the minimums listed in the State of Alaska DOT&PF Construction Surveying Requirements.

642-3.04 GPS SURVEYS. The specifications described in this Section are not intended to discourage the use of new GPS procedures and techniques. Procedures that are not defined by this specification may be allowed if approved by the AK DOT&PF Central Region Survey Manager, through the Engineer.

1.	General Requirements:

a.	All surveying shall be done in the local project coordinate system.

b.	OPUS shall be used for the determination of Reference Station positions only, and shall not be used directly for producing final positions for any Static, Fast Static, RTK or PPK surveys. OPUS may be used as a tool for verification of the final positions obtained from these types of surveys.

2.	GPS Equipment: Survey Grade dual frequency GPS receivers shall be used. For static surveys these shall be set up on adjustable leg tripods at a minimum. Fast or Rapid Static GPS surveys require a bipod at a minimum. RTK or PPK surveys may use fixed or adjustable poles, or secure lashings to vehicles.

3.	GPS Reference Stations:

a.	All Reference Stations shall be approved by the AK DOT&PF Central Region Survey Manager through the Engineer, prior to conducting any GPS surveys.

b.	Primary Reference Stations shall meet current NGS CORS standards. Secondary Reference Stations may be used temporarily when a Primary Reference Station is not available.

c.	Primary Reference Stations shall be permanently mounted and shall not change throughout the duration of the project.

d.	Secondary Reference Stations may be tripod mounted, however, GPS receivers shall never be mounted on aluminum tripods.

e.	All Reference Stations shall be tied to an OPUS derived position, and on the NAD83 datum. Submit GPS data files for a minimum of 2 days, 12 hours per day, 5 second epoch to OPUS to determine the final position. The OPUS derived position shall be determined at the beginning of the project, and shall not change throughout the duration of the project unless approved by the Engineer. Notify all users immediately if any changes are made to the Reference Station’s position. If OPUS is unable to process a position, the Reference Station shall be tied to existing project control.

f.	Reference Stations shall be physically located in clear view of the sky. Avoid locations near cellular towers or other areas that may disrupt satellite signal reception. Avoid locations near large flat surfaces such as buildings, large signs, fences, and other objects that may cause multi-path interference.

g.	Reference Stations shall be located to provide maximum coverage of the project area.

h.	Store 5 second epoch data, and post data online for use by the Engineer.

i.	GNSS enabled Reference Stations are allowed.

4.	RTK Surveys:

a.	The Surveyor shall follow prudent practices when conducting RTK surveys. The NGS has published a draft manual titled National Geodetic Survey User Guidelines For Classical Real Time GNSS Positioning, v.2.0.3 issued in September, 2008. The Surveyor shall become familiar with this manual, in order to better understand prudent practices. Copies of the draft manual may be available upon request or may be downloaded from the following web site: http://www.ngs.noaa.gov/PUBS_LIB/NGSRealTimeUserGuidelines.v2.0.4.pdf.

b.	RTK surveys may not be used to permanently mark or delineate Right-Of-Way.

5.	Local Coordinate Calibration:

a.	Use GPS calibration parameters if they are provided on the Survey Control Sheet. If GPS calibration parameters are not given, develop a local site calibration based on existing project control. All included control points shall have WGS84 positions that were observed by either a GPS Static or Fast Static network, as well as the final adjusted project control coordinate values that match the values listed on the Survey Control Sheet. The calibration shall consist of the following conversion parameters; Rotation, Translation, Scale, and GPS derived orthometric heights. Values listed on the Survey Control Sheet shall be held fixed in any adjustment, barring any large residuals. Notify the Engineer of any large residuals so that the problems can be identified and corrected. Submit a signed hard copy of the calibration parameters, residuals, and related control points to the Engineer for approval before staking activities begin.

b.	Perform a local calibration each time the coordinates of the reference station change.

6.	GPS Data Summary Report:

a.	Generate reports for all surveyed points, including the Point Number, Northing, Easting, Elevation, Point Code, Annotation(s), Date, Time, residuals, observation (start and stop) times, and antenna height information. Summary reports shall bear the signature and seal of the Surveyor.

b.	The Engineer may require the Contractor to re-survey specified points at no cost to the Department if the Survey doesn’t meet the minimum accuracy requirements defined in the State of Alaska DOT&PF Construction Surveying Requirements.

7.	Weather Conditions: The Surveyor shall follow prudent practices when conducting GPS surveys in inclement weather. The following is recommended as a guideline:

a.	Regularly observe surface and solar weather forecasts prior to planning survey activities.

b.	Use sound practical judgment when performing surveys during inclement weather conditions.

c.	Observations should never be conducted during an electrical storm.

d.	Note significant or unusual weather conditions in the field notes, data collector, or receiver.

642-3.05 TOPOGRAPHIC SURVEYS. Topographic surveys shall be conducted under the direct supervision of the Surveyor. The purpose of a topographic survey is to gather field data to determine the configuration (relief) of the surface of the earth (ground). Use all data collected to generate topographic DTM surfaces as defined in Section 642-3.07, Digital Terrain Models. All data becomes the property of the State of Alaska. Conduct topographic surveys as follows:

1.	General Requirements:

a.	Collect topographic data within the right-of-way limits.

b.	Keep all shots 50 ft or closer, as necessary to accurately define all surface features within the roadway corridor.

c. 	Keep a field book of notes describing changes or errors of rod heights, point descriptors, or other annotations necessary to verify all electronic data.

d. 	Identify each point with a point number. Multiple points with the same point number are not permitted.

e. 	Identify each shot with the appropriate point code. Break line points shall be separately identifiable from ground shots.

f. 	Append any additional information required to further describe a point with point annotations.

g. 	Develop a summary of standard point codes for all points used on the project.

h. 	Develop a summary of standard point descriptors to identify all point codes used on the project (i.e. Edge of Pavement is the point descriptor corresponding to the EP point code).

2.	Functional Requirements: The purpose of a topographic survey is to develop an appropriate DTM as defined in Section 642-3.07. Conduct a topographic survey to meet the appropriate functional requirements as defined below:

a.	As-built Surfaces – Conduct a survey of all finished roadway surfaces, embankments, ditches and other topographic features as required to accurately define the project topography.

b.	Excavation Surfaces – Conduct a survey of original grade (upper) surfaces, and bottom of excavation (lower) surfaces, as necessary to produce DTM volumetric quantities. Follow the requirements listed below:

(1)	Upper surface – Survey prior to excavation. Topographic data may be collected prior to grubbing and pavement removal, and adjusted by the average depth removed as measured in the field.

(2)	Lower surface – Survey after the final grade has been established by excavation.

c.	Embankment Surfaces – Conduct a survey of excavated or original grade (lower) surfaces, and top of embankment (upper) surfaces, as necessary to produce DTM volumetric quantities. Follow the requirements listed below:

(1)	Upper surface – Survey after the final grade has been established.

(2)	Lower surface – Survey prior to the placement of embankment. If only grubbing or pavement removal is required prior to placement of embankment, the topographic data may be collected prior to grubbing and pavement removal and adjusted by the average depth removed, as measured in the field. If excavation is required prior to placement of embankment, survey only after excavation activities have been completed.

3.	Accuracy Tolerance Limits: The Surveyor shall check into and collect primary control monument locations to ensure the data being collected meets the minimum Horizontal and Vertical Accuracy Tolerances. This shall serve as a basis of acceptance for the topographic data collected by the Surveyor. The Horizontal and Vertical Accuracy Tolerances will be used to check for systematic error, and will be evaluated by comparing all control check shots taken during the topographic survey to the monument’s location as defined on the Survey Control Sheet. The Volumetric Accuracy Tolerance will be used to check for random and operator error, and will be evaluated by comparing the Contractor furnished DTM with an independent DTM developed by the Department. The Volumetric Accuracy Tolerance shall be applied only to survey data that is used to calculate volumetric quantities.

a.	Horizontal Accuracy Tolerance – Check shots shall be within ± five hundredths (0.05) of a foot of the monument’s horizontal position. If any of the data doesn’t meet the minimum the horizontal tolerance, the Engineer may require the Contractor to re-survey the non-conforming points at no additional cost to the Department.

b.	Vertical Accuracy Tolerance – Check shots shall be within ± one tenth (0.10) of a foot of the monument’s vertical position. If any of the data doesn’t meet the minimum vertical tolerance, the Engineer may direct the Contractor to re-survey the non-conforming points at no additional cost to the Department.

c.	Volumetric Accuracy Tolerance – The Department will determine the volumetric error on randomly selected areas, including at least 20% of the area within the slope limits.  The Department will calculate the volumetric error as follows:

(1)	Determine the net volume by comparing the Contractor’s DTM to the Department’s DTM.

(2)	Determine the accepted volume by comparing the Department’s DTM to the appropriate neat-line surface.

(3)	Determine the volumetric error by dividing the net volume by the accepted volume.

The Engineer may require the Contractor to re-survey any areas that exceed 5% error at no additional cost to the Department.

4.	Control Check Requirements: Collect local project control data at the following minimum frequency:

a.	Every time the instrument is turned on, at the beginning of the survey session.

b.	Prior to every time the instrument is turned off, at the end of the survey session.

c.	Every time the instrument is moved (radial survey).

d.	Every time the backsight is moved (radial survey).

e.	Every time the actual or broadcasted position of the Reference Station changes (GPS survey).

5.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted and electronic as-built surfaces (developed per Section 642-3.07) showing major and minor contours. Standard contour intervals shall be 5 ft (major) and 1 ft (minor).

b.	All field books noting any errors, corrections, or changes to the data.

c.	All electronic survey data in a comma delimited ASCII file in PNEZD format (Point number, Northing, Easting, Elevation, and Description).

- Letter of conformance signed and sealed by the Surveyor, certifying that the Topographic Survey meets the minimum Horizontal and Vertical accuracy requirements. Attach all backup data and calculations.

642-3.06 AS-BUILT SURVEYS. As-built surveys shall be conducted under the supervision of the Surveyor. The as-built survey shall document the final locations of roadways, topographic surfaces, structures, and utilities within the ROW project limits. The Surveyor shall maintain communication with the Contractor, Sub-Contractor or Utility Company as necessary to coordinate surveying activities. Surveying activities shall be conducted as soon as possible as each phase of the project is completed, and to avoid scheduling conflicts. The survey will be used to verify that the contracted work items conform to the plans and specifications. All survey data becomes the property of the State of Alaska.

1.	General Requirements:

a.	Topographic Survey of all roadway and pedestrian corridors, in accordance with Section 642-3.05, Topographic Surveys.

b.	Utility Survey of all existing and re-located utilities. Record the horizontal and vertical location of all underground and overhead utilities. Take digital photos of all exposed utility crossings. Identify the location of each photo taken, including the approximate northing, easting, and bearing.

c.	Structural Survey of all existing and re-located structures, including bridges, tunnels, manholes, signs, fences, guard rails, walls, and foundations.

2.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted as-built drawings showing the final surveyed locations of all roadways, topographic surfaces, structures, and utilities. Plotted drawings shall be identified by the Project name and number, and bear the signature and seal of the Surveyor.

b.	Printed color photos, identifying the location of all underground utility crossings.

c.	All field books used to conduct the as-built survey.

d.	All DTM and point data files generated by the as-built survey.

642-3.07 DIGITAL TERRAIN MODELS. Develop all Digital Terrain Models using CAD software that is compatible with the latest release of software used by the Department. All DTM’s shall be approved by the Engineer.

1.	DTM Development Methods:  Develop all DTM’s using the appropriate method as defined below:

a.	Engineering Method - Use this method to define all neat-line surfaces. Develop the DTM by associating all appropriate engineered features such as alignments, profiles, sections, daylight surfaces, grading lines, and other features.

(1)	CAD software shall generate and automatically update surfaces based on the association of alignments, profiles, sections, grading lines, and other parameters necessary to accurately represent neat-line geometry.

(2)	Limit tessellation spacing to allow an accurate representation of a surface feature. The Engineer may require changes to the tessellation spacing, if necessary to allow an accurate representation of the feature.

(3)	If the Contractor excavates or fills beyond the neat-line limit without the direction of the Engineer, only the neat-line limit shall be used.

b.	Topographic Method - Use this method to define all topographic surfaces. Each vertex of a triangle in the TIN shall be formed by a field measured data point, and shall be located by its (XYZ) coordinate. Develop the TIN surface by connecting Topographic Survey points to their nearest neighboring points (in XY), except as outlined below:

(1)	Break Lines – Create break lines by connecting Topographic Survey points that are identified by their appropriate break line descriptors. Break lines shall snap to vertices on adjacent break lines when two break lines intersect. Break lines shall not cross. Use break lines to establish the following features:

(a) 	Centerline of roadway.

(b)	Lane separations (for multiple lane roadways).

(c)	Edge of pavement.

(d)	Shoulder hinge points.

(e)	Bottom of ditch.

(f)	Ditch back slope catch point.

(g) 	For curb and gutter sections, break lines shall be collected at the flow line and back of curb.

(h)	Ridge lines.

(i)	Rim of pits or significant depressions.

(j) 	Areas of slope change or undulations in slope.

(k) 	Bottom of valleys or draws.

(l) 	Hydraulic features.

(m)	Around buildings and structures (including top and bottom of walls).

(2)	Boundaries – Boundaries break the TIN lines and define the edge of the surface. Use boundaries to trim all non-relevant edges from the DTM. Use either non-destructive or destructive trimming as necessary to preserve the accuracy of the DTM. Use boundaries to establish the following features:

(a)	Outer boundary of the DTM.

(b)	Edge of a void inside the surface.

(c)	Edge of an island inside of a void.

(3)	Surface Editing – Surface Editing allows changes that more accurately represent the actual terrain. Use surface editing to delete or swap edges of the triangulated network as necessary to best represent the actual site condition. Mathematically computed points for the purpose of surface smoothing may be used only if approved by the Engineer. The creation of contour lines for the purpose of DTM surface extraction is not acceptable.

c.	Combination Method - Use this method when the Engineer approves a change to the neat-line limit.

(1)	In areas where the Engineer approves a change to the neat-line limit, develop new surfaces using the Topographic Method.

(2)	Replace the neat-line surface with the new topographic surfaces to create an appropriate single surface.

642-3.08 CONTRACTOR FURNISHED COMPUTATIONS. Provide computations for volumetric pay items using DTM’s developed per Section 642-3.07. Cross sections developed from the appropriate DTM’s will be used as a supplementary quality control check on DTM parameters and quantities, and not for pay. The Contractor may use the Average End Area Method in accordance with Section 109, only if approved in writing by the Engineer.

1.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted cross sections from the DTM surfaces. Develop separate cross sections for each volumetric pay item. More than one pay item per plotted cross section is not allowed.

(1)	Plot every 50 ft on Station, including intermediate stations as required to define angle points, curves, or other significant changes in the roadway geometry.

(2) 	Show the elevation and offset information for all vertex points. Weeding vertex point labels is not allowed. Elevation and offset information may be shown on a separate report if the amount of information exceeds what can be legibly shown on the plot.

(3)	Show the area for each cross section.

(4)	Label each plot with the project name, project number, pay item number, and pay item name.

(5)	Label each plot with the Surveyor’s Company name and address.

b.	Plotted profiles from the DTM surfaces. Develop separate plots for each volumetric pay item. Each plot shall only identify the profiles appropriate to the volumetric pay item.

(1)	Plot the profile along the alignment centerline as shown in the plans.

(2)	Label each profile as original ground, bottom of excavation, and the top or bottom of embankment, as appropriate.

(3)	Label topographic profiles with elevation and station information, using a weeding frequency of every 100 ft, or as necessary to match the frequency shown on the plans.

(4)	Label the neat-line profiles with elevation and station information every 100 ft, and for the beginning, end, and VPI of all vertical curves and grade breaks. Label the percent slope between all grade breaks, to the fourth significant decimal.

(5)	Label each plot with the project name, project number, pay item number, and pay item name.

(6)	Label each plot with the Surveyor’s Company name and address.

c.	Electronic Data

(1)	Provide copies of all Topographic, Neat-line, and Combination surfaces to the Engineer. Include all electronic features (alignments, profiles, sections, etc.) used to generate the surfaces.

(2)	All data shall be delivered on a clearly labeled CD-ROM or DVD, unless specified otherwise by the Engineer. The label shall include the project name, project number, Surveyor’s company name, and date. All data becomes the property of the State of Alaska.

(3)	DTM files shall be saved in Autodesk, TIN, XML, or other approved formats compatible with Department software.

d.	Volume Reports

(1)	Provide interim volume reports showing quantities between every 50 ft station. The volume reports shall be summarized to allow the Department to reference the quantities per individual plan sheet, or as defined in any earthwork summary shown on the plan sheets.

(2)	Provide a final volume report reflecting the final total quantity. Attach all data, calculations, and plots to the report. The report shall be signed, sealed, and dated by the Surveyor. This report shall be used as the basis for final pay.

642-3.09 CONTRACTOR FURNISHED ENGINEERING TOOLS. Furnish and maintain Engineering Tools as directed by the Engineer, for the exclusive use of the Engineer throughout the duration of the project. The Contractor shall furnish all equipment specifications to the Engineer for approval, prior to furnishing equipment. The equipment shall be in good working condition not more than 1 model year old. The Contractor shall insure and indemnify the Department against normal wear and tear, damage, theft, and all other events that may cause a loss of function of the furnished tools. The equipment shall be returned to the Contractor upon completion of the project, or when services are terminated by the Engineer. Furnish training for the Engineer’s staff, as directed by the Engineer.

1.	GPS Rover Unit – All components shall be fully compatible to provide a stand-alone GPS Rover Unit. The Rover Unit shall be an “all on the pole” system equipped with the following:

a.	Receiver

(1)	Bluetooth compatible.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Dual frequency receiver capable of tracking at least twelve (12) satellites simultaneously on parallel channels.

(5)	Capable of RTK, Static, and Fast Static occupations.

(6)	Capable of receiving L1, L2, and GNSS frequencies.

(7)	Antenna model shall have undergone antenna calibration by the NGS.

(8)	Ensure the receiver contains the manufacturer’s latest firmware upgrades.

(9)	Provide the manufacturer’s user guide.

b.	Controller

(1)	Bluetooth compatible.

(2)	Equipped with onboard software allowing for the configuration of RTK, PPK, or Static rover modes.

(3)	Meet waterproof specification IPX7.

(4)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(5)	Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

(6)	Capable of collecting data in WGS84 and displaying local project coordinates.

(7)	Equipped with onboard software that allows automatic point logging.

(8)	Capable of creating and storing line-work in DFX or DWG format.

(9)	Equipped with onboard software to allow the user to stake-out points, 3D lines, and DTM surfaces. Software shall allow the user to read cut/fill elevations relative to a DTM surface.

(10) Capable of importing, exporting, and storing point, line, and DTM data.

(11) Capable of showing satellite, radio, and battery status.

(12) Equipped with onboard software that allow the user to create and manage survey jobs, point data, coordinate systems, and alignments.

(13) Equipped with a removable memory storage device with a minimum capacity of 512MB.

(14) Capable of storing custom configuration settings for the GPS Rover Unit.

(15) Ensure the controller contains the manufacturer’s latest firmware upgrades.

(16) Provide the manufacturer’s user guide.

c.	Radio System

(1)	Meet waterproof specification IPX7.

(2)	Support a frequency compatible with the Reference Station.

(3)	Capable of storing multiple radio frequencies.

(4)	Compatible with the Reference Station’s broadcasting format and protocol.

(5)	Power and programming cables.

(6)	Provide the manufacturer’s user guide.

d.	Batteries

(1)	Provide all batteries required to fully power and operate the GPS Rover Unit.

(2)	Batteries shall be capable of powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

(3)	Each battery shall be rechargeable and commercially available.

(4)	Provide an identical replacement backup battery for each primary battery required.

(5)	Provide all power connectors necessary to connect the batteries to the equipment.

(6)	Provide battery chargers to allow all onboard batteries to be charged simultaneously, and that safeguard against overcharging.

e.	Rod

(1)	Fixed height (non-adjustable).

(2)	Mounting hardware for GPS controller and radio.

(3)	Pole grip with bubble level.

(4)	Detachable bipod.

(5)	Interchangeable flat and pointed footings.

(6)	Quick release adapter for the GPS receiver.

f.	Carrying Case

(1)	Hard Shell.

(2)	Shockproof.

(3)	Waterproof.

(4)	Capacity to hold all components of the GPS rover, minus the rod.

2.	Continually Operating Reference Station – The location of the CORS shall not change for the duration of the project. The CORS shall be permanently mounted per NGS CORS standards. All structures, mounting hardware, power supply, computers, software, networking, and personnel required to support and operate the CORS is considered subsidiary to this item. Store CORS data for the duration of the project, and post online for use by the Engineer. The CORS shall include and conform to the following requirements:

a.	GPS Receiver

(1)	Choke-ring antenna, model shall have undergone antenna calibration by the NGS.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Able to operate in temperatures between -20º F to +140º F.

(5)	Capable of logging L1/L2 data continuously for 180 days, and storing at 1 second intervals. If onboard memory storage capacity is insufficient, backup all data on an external memory storage device.

(6)	Support multiple, simultaneous data logging sessions at different collection rates.

(7)	Equipped with a dual frequency receiver capable of tracking L1, L2, and GNSS frequencies on at least 12 satellites. Receiver shall have a minimum of 24 channels.

(8)	Support CMR/CMR+ and RTCM output simultaneously via separate ports.

(9)	Use multi-path mitigation techniques.

(10)	Satellite acquisition technology shall provide improved tracking in areas of high radio interference such as under power lines, around airports, near radio-intensive construction sites.

(11)	Capable of 1PPS output with an accuracy of 1usec.

(12)	Equipped with 1 primary and 1 secondary power input port.

(13)	The system shall automatically switch between power sources.

(14)	Equipped with over-voltage protection on all power inputs.

(15)	Capable of reporting Signal-to-Noise Ratio (SNR) values for L1 and L2.

(16)	Capable of logging data at operator selected intervals of 0.5, 1, 5, and 30 seconds.

(17)	Provide the manufacturer’s user guide.

b.	Radio

(1)	Transmission power, 25 watt minimum.

(2)	Meet waterproof specification IPX7.

(3)	Ensure the radio has a current license to broadcast in accordance with FCC requirements.

(4)	Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

(5)	Provide the manufacturer’s user guide.

c.	CORS Facility – Provide a facility to mount and house CORS station equipment.

(1)	Facility shall meet NGS CORS mounting requirements, and shall be approved by the Engineer.

(2)	Shall be physically located in a clear view of the sky, away from objects that may cause multi-path interference.

(3)	Location shall provide for maximum strength of geometry relative to the primary control network and the project limits.

(4)	Shall be connected to a primary power source, and a backup power source capable of providing uninterrupted backup power for a minimum of 48 hours.

3.	GPS Base/Repeater Station – All components shall be fully compatible to provide a stand-alone GPS Base/Repeater Station setup. The setup shall include the following:

a.	Receiver

(1)	Meet waterproof specification IPX7.

(2)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(3)	Dual frequency receiver capable of tracking at least 12 satellites simultaneously on parallel channels.

(4)	Antenna model shall have undergone antenna calibration by the NGS.

(5)	Ensure the receiver contains the manufacturer’s latest firmware upgrades.

(6)	Carrying case.

(7)	Tribrach with optical plummet and height rod.

(8)	Provide the manufacturer’s user guide.

b.	Controller

(1)	Equipped with onboard software allowing for configuration as a GPS reference station in RTK, PPK, Static, and Fast Static modes.

(2) 	Capable of logging raw observations for post processing.

(3)	Capable of showing satellite, radio, and battery status.

(4)	Meet waterproof specification IPX7.

(5)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(6)	Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

(7)	Equipped with a removable memory storage device with a minimum capacity of 512MB.

(8)	Equipped with 1 primary and 1 secondary power input port.

(9)	Ensure the controller contains the manufacturer’s latest firmware upgrades.

(10) Provide the manufacturer’s user guide.

c.	Radio

(1)	Transmission power, 25 watt minimum.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Support a frequency compatible with the Reference Station.

(5)	Capable of storing multiple radio frequencies.

(6)	Compatible with the CORS broadcasting format and protocol.

(7)	Ensure the radio has a current license to broadcast in accordance with FCC requirements.

(8)	Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

(9)	Equipped with onboard software/firmware allowing for configuration as either a Reference Station or a Repeater Station.

(10) Carrying case.

(11) Antenna.

(12) Antenna/pole mounting adapter.

(13) Provide the manufacturer’s user guide.

d.	Tripods – Provide one of each:

(1) Conventional tripod with extendible range pole. Include carrying case.

(2) Conventional wood tripod.

e.	Batteries

(1)	Provide all batteries required to fully power and operate the GPS Base/Repeater Station.

(2)	Batteries shall be capable powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

(3)	Each battery shall be rechargeable and commercially available.

(4)	Provide an identical replacement backup battery for each primary battery required.

(5) 	Provide all power connectors necessary to connect the batteries to the equipment.

(6)	Provide battery chargers to allow all batteries to be properly charged, and that safeguard against overcharging.

4.	Computer Hardware – Hardware shall meet the following minimum requirements:

a.	Laptop Computer

(1)	2.8 GHz multi-core CPU.

(2)	120GB Internal Hard Drive.

(3)	4 GB System RAM.

(4)	Display 13” with 1,600 x 1,200 resolution.

(5)	512MB video memory.

(6)	DVD Burner Drive.

(7)	Internal Bluetooth and Wi-fi.

(8)	Internal Battery.

(9)	120v AC Adapter.

(10) 12v DC Adapter.

(11) Built-in CF, SD, and PCMCIA card ports.

(12) 4 USB 2.0 ports.

(13) 1394 (firewire) port.

(14) Mouse (wireless).

(15) Travel Case (hard) for laptop and accessories.

b.	Laptop Computer Mount

(1)	Permanently installed in a vehicle, as directed by the Engineer.

(2)	Fastened to the passenger side of the vehicle.

(3)	Shock and vibration resistant.

(4)	Fully adjustable positioning with mechanically locking hinge points.

c.	Desktop Computer

(1)	3 GHz multi-core CPU

(2)	120GB Internal Hard Drive

(3)	4 GB System RAM

(4)	Compatible DVI 19” monitor with 1,600 x 1,200 resolution

(5)	Internal video card/chip, 512MB, 2 DVI ports

(6)	Internal DVD Burner Drive

(7)	CF and SD media card reader

(8)	6 USB ports

(9)	1394 (firewire) port

(10) Internal wireless (IEEE 802.11 b/g) network card

(11) Internal Ethernet card (10/100 Mbps).

(12) Uninterruptible Power Source (UPS), 8 outlets, 390 Watt

(13) 250 GB Backup Hard Drive (external)

(14) Mouse and Keyboard

d.	Laser Printer

(1)	45 pages per minute print speed.

(2)	1200 x 1200 dpi print quality.

(3)	Main tray capacity shall hold no less than 500, 8.5 x 11 inch sheets.

(4)	Multipurpose tray capable of custom sizes up to 11 x 17 inch sheets.

(5)	128 MB of onboard memory, minimum.

5.	Computer Software – All software shall be licensed and fully operational. Provide software that is similar or approved equal in accordance with the following:

a.	Operating System Software – Provide an operating system that supports the drivers of all onboard and auxiliary computer hardware systems. The operating system shall be of the latest release, with the most current updates installed. The operating system shall support all of the applications listed below.

b.	CAD Software – Provide CAD software that is capable of dynamically associating and updating alignment, profile, section, grading, point, and surface data. The software shall be capable of saving all data to formats that are compatible with the latest release of CAD software currently used by the Department. Formatting shall preserve the dynamic relationship of all DTM features. Software that doesn’t dynamically associate all DTM features is not acceptable.

c.	Word Processing Software – Provide software that is compatible with the latest release of word processing software currently used by the Department.

d.	Spreadsheet Processing Software – Provide software that is compatible with the latest release of spreadsheet processing software currently used by the Department.

e.	Anti-Virus Software – Provide software to protect against viruses and other security threats. Software shall be equipped with a firewall containing industry standards of system protection. The software shall be capable of backing up all hard drive data.

f.	GPS Processing Software – Provide GPS processing software of the latest release and from the same vendor as the GPS equipment furnished. Include all necessary hardware/software keys to enable L1 & L2 Static, PPK, and RTK processing, GNSS processing, network adjustments, datum and map transformations, and RINEX data importing and exporting.

642-4.01 METHOD OF MEASUREMENT. The work will be measured according to Section 109, and as follows:

1.  Item 642.0001.____ Construction Surveying.  Prior to beginning work, develop a Lump Sum Agreement that itemizes major contract work requirements by percentage. Work will be measured by the percent completion of all major contract work requirements defined in the Lump Sum Agreement.

2.  Item 642.0003.____ Three Person Survey Party.  By the hour for extra, additional, or unanticipated work made necessary by changes in the project, as directed, and as supported by certified payrolls. Work accomplished by a three person survey party will be paid at 100% of the contract unit price. Work accomplished by a two person survey party will be paid at 75% of the contract unit price. Work accomplished by a one person survey party will be paid at 32% of the contract unit price.

3.  Item 642.2005.____ Contractor Furnished Computations.  Prior to beginning work, develop a Lump Sum Agreement that itemizes all plan sheets labeled “Plan and Profile” (or similar) by percentage. Work will be measured by the percent completion of all computations required, per plan sheet defined in the Lump Sum Agreement.

4.  Item 6432.2006.____ Contractor Furnished Engineering Tools.  Contingent sum work will be measured in accordance with the directive authorizing the work.

642-5.01 BASIS OF PAYMENT. Pay Items include all necessary personnel, equipment, transportation, traffic control, and supplies to accomplish the work described in the Contract, or directed by the Engineer.

1.  Item 642.0001.____ Construction Surveying. This item includes all surveying work described in the Contract except for work paid for under 642.0003.____, 642.2005.____, and 642.2006.____. 5% of the contract lump sum bid price will be withheld until the final As-Built Survey is completed and accepted by the Engineer.  Surveying required for determining volumetric quantities is considered subsidiary to Item 642.2005.____.

2.  Item 642.0003.____ Three Person Survey Party.  Adjustment according to 109-1.04 is not allowed for this pay item. When directed by the Engineer to reference an existing monument not shown in the plans, payment will be made after the Monument Record Forms are prepared and recorded in the local Recorder’s Office and accepted by the Engineer.

3.  Item 642.2005.____ Contractor Furnished Computations.  This item includes all work required to develop and furnish quantity computations in accordance with methods required by the contract. Earthwork computations, digital terrain model development, plotted cross sections, quantity reports, and associated topographic surveying are subsidiary to this item. The Engineer may withhold payment for this item if the minimum specifications are not met. 10% of the contract lump sum bid price will be withheld until final computations are accepted by the Engineer. If the Contractor excavates or fills beyond the neat-line limit without the direction of the Engineer, the calculated volume shall only extend to the neat-line limit.

4.  Item 6432.2006.____ Contractor Furnished Engineering Tools. The Engineer shall issue a directive defining and authorizing the work. Payment for a GPS Rover, Base/Repeater Station, CORS, or Computer System will be made on a time and materials basis in accordance with Subsection 109-1.05-3e, Leased or Rented Equipment. Payment for training will be made on a time and materials basis in accordance with Section 109-1.05. If the training is beyond the Contractor’s ability or expertise, payment will be made in accordance with Subsection 109-1.05-4, Work by a Specialty Subcontractor. The Engineer may withhold payment for this item if the minimum specifications are not met. The Engineer may issue a directive at any time to terminate or re-authorize the work, at no additional cost to the Department.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 642.0001.____ | Construction Surveying | LS |
| 642.0003.____ | Three Person Survey Party | Hour |
| 642.2005.____ | Contractor-Furnished Computations | LS |
| 642.2006.____ | Contractor-Furnished Engineering Tools | CS |

CFHWY00599

Special Provisions

Replace Section 643 with the following:

SECTION 643
TRAFFIC MAINTENANCE

643-1.01 DESCRIPTION. Protect and control traffic during the contract. Furnish, erect, maintain, replace, clean, move, and remove the traffic control devices required to ensure the traveling public’s safety. Perform all administrative responsibilities necessary to implement this work.

Maintain all roadways and pedestrian and bicycle facilities affected by the work in a smooth and traversable condition. Construct and maintain approaches, crossings, intersections, and other necessary features throughout the project for the life of the contract.

Illuminate construction activities listed in Table 643-4 during hours of night work on roads open to the public within project limits.

CR643-010122/CFHWY00599

Furnish and install interim lane configuration traffic control devices at the Knik-Goose Bar Rd and Palmer-Wasilla Hwy intersection as shown on the Plans.

CFHWY00599

643-1.02 DEFINITIONS. These definitions apply only to Section 643.

ATM. When used in this Section, ATM stands for the Alaska Traffic Manual, which is comprised of the Manual on Uniform Traffic Control Devices (MUTCD), the Alaska Traffic Manual Supplement, any adopted revisions or interim addenda to either document issued subsequently, and corrections to known errors to either document.

Balloon Light.  Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.

Construction Phasing Plan. A plan for each phase of the project showing how to accommodate traffic. Show the sequence of work by segment or phase, if required.

Fixed Objects. Private vehicles, parked flagger vehicles, idle construction equipment, construction material stockpiles, culvert ends, individual trees, power poles, utility poles and appurtenances, and other items deemed by the Engineer to present a hazard to motorists, pedestrians, or bicyclists traveling through the work zone.

Night Work. Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in the Table 643-1 below:

TABLE 643-1

PROJECT LOCATIONS – NIGHT TIME ILLUMINATION EXCLUSION

| Latitude | No Lighting Required |  | Nearby |
| --- | --- | --- | --- |
| (degrees) | Start | End | Cities |
| South of 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Tok, Delta, Nome |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle City |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

Traffic. The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, or similar operations.

Traffic Control Plan (TCP). A drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. The TCP depicts the traffic control devices and their placement and times of use.

Traffic Control Zone. A portion of a road construction project, maintenance operation, utility work or similar operation that affects traffic and requires traffic control to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. Implement an approved TCP before beginning work within the project limits.

The TCP includes, but is not limited to, signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary lighting, temporary roadways and all other items required to direct traffic through or around the traffic control zone according to these Specifications and the ATM. Address in the TCPs placement of traffic control devices, including location, spacing, size, mounting height and type. Include code designation, size, and legend per the ATM and the Alaska Sign Design Specification (ASDS). Include longitudinal buffer space for the posted speed limit, according to Table 6C-2 of the ATM unless project conditions or geometric features prohibit including all or a portion of the buffer length.

When a TCP is included in the Plans, use it, modify it, or design an alternative TCP. When a TCP is omitted from the Plans, provide one according to this Section and the ATM.

Submit new or modified TCPs to the Engineer for approval. All TCPs must include the following information:

1.	Project name and number.

2.	A designated TCP number and name on each page.

3.	For TCPs more than one page, each page must be numbered.

4.	The posted speed limit for each roadway.

5.	Existing striping width, lane width, and road surfacing.

6.	Construction lane widths, striping layout, and temporary pavement marker layout.

7.	Provisions for Pedestrian, Bicycle, and ADA travel through the work zone.

8.	Dates and times the TCP will be in effect and why it is being used.

9.	The Worksite Traffic Supervisor’s signature certifying that all TCPs conform to the ATM and the Contract.

10.	The Project Superintendent’s signature confirming the TCP is compatible with the work plan.

11.	The name(s) of the Worksite Traffic Supervisor, his/her alternate and their 24-hour telephone number(s).

12.	Signs to be used and the ASDS designation number and size.

13.	Location and spacing of all devices and signs.

14.	A plan to address any possible slopes, drop offs, paving joints, or similar temporary features that may occur during use of the TCP.

15.	For TCPs proposed to be used at night, note how the requirements will be met for the required lighting and retroreflective material.

TCPs submitted for approval without all the required information will be rejected. Allow 7 days for review of each TCP submittal. All required modifications to a TCP require a new submission and an additional 7 days for review.

A minor revision to a previously approved TCP during construction requires 48 hours for review and approval by the Engineer.

The TCPs, Plans, and Alaska Standard Plans show the minimum required number of traffic control devices. If unsafe conditions occur, the Engineer may require additional traffic control devices.

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12-foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

Road Closures and Major Traffic Sequencing (events).  Submit a written request to the Engineer for review and approval of each proposed event and event date.  Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections.  The proposed event date will be no less than 14 days from the date of written approval.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. Provide a Worksite Traffic Supervisor responsible for maintaining 24-hour traffic operations.

1.	Qualifications. The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements. The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, proposed operations, and certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Temporary Traffic Control Technician, or Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor has a minimum 4000 hours of temporary traffic control work experience, is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this section.

a.	Temporary traffic control work experience shall demonstrate an understanding of concepts, techniques, and practices in the installation and maintenance of traffic control devices, and skill in reading, interpreting, implementing, and modifying TCPs.

b.	Temporary traffic control work experience includes: flagging; installing traffic control devices in accordance with TCPs; monitoring traffic control devices and TCP performance; and recognizing and reporting deficiencies in traffic control devices and TCPs for correction.

c.	Temporary traffic control work experience is gained while serving as a Worksite Traffic Supervisor-in-training, temporary traffic control support personnel, and Flagger.

d.	Four thousand hours of experience serving solely as a Flagger does not satisfy these requirements.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

2.	Duties.

a.	Prepare the TCPs and public notices and coordinate traffic control operations between the Project Superintendent and the Engineer.

b.	Physically inspect the condition and position of all traffic control devices used on the project at least twice each day and at approximately 12-hour intervals.  Ensure that traffic control devices work properly, are clean and visible, and conform to the approved TCP.  Complete and sign a detailed written report of each inspection within 24 hours.  Use Traffic Control Daily Review Form 25D-104.

c.	Supervise the repair or replacement of damaged or missing traffic control devices.

d.	Review and anticipate traffic control needs. Make available proper traffic control devices necessary for safe and efficient traffic movement.

e.	Review work areas, equipment storage, and traffic-safety material handling and storage.

f.	Hold traffic safety meetings with superintendents, foremen, subcontractors, and others as appropriate before beginning construction, prior to implementing a new TCP, and as directed. Invite the Engineer to these meetings.

g.	Supervise all traffic control workers, flaggers, and pilot car drivers.

h.	Certify that all flaggers are certified as required by Subsection 643-3.04.4.  Submit a copy of all flagger certifications to the Engineer.

i	Supervise lighting for night work.

3.	Authority. The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-1.05 CONSTRUCTION PHASING PLAN. Submit a Construction Phasing Plan for approval no less than 5 working days prior to the preconstruction conference. Include the following:

1.	Form 25D-124 designating the Worksite Traffic Supervisor, providing the 24-hour telephone number, and certifying minimum 4,000 hours of work experience as described in 643-1.04 Worksite Traffic Supervisor.

2.	A construction-phasing plan for each phase or segment of the project.

3.	TCPs for the first phase of the project. Show permanent and temporary traffic control measures, including the times each TCP will be used.

Submit any changes to the Engineer for approval 7 days before proposed implementation.

643-1.06 TRAFFIC MAINTENANCE SETUP. When shown on the bid schedule, Traffic Maintenance Setup items are site specific and are detailed as individual TCPs on the plan sheets. They depict the method or scheme required to route traffic safely and efficiently when any of the following restrictions occur:

1.	Lane Closure. The closure of one or more lanes on a roadway.

2.	Detour. The redirection of traffic through or around a traffic control zone.

3.	Road Closure. The closure of a roadway with or without a specified detour route.

4.	One Lane Road. A two-way roadway reduced to a single-lane roadway with flaggers, pilot cars, traffic signals, stop signs, or yield signs.

643-2.01 MATERIALS. Provide traffic control devices meeting the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM, and ASDS.

a.	Construction Signs: Regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Neatly mark the size of each sign on its back in 3-inch black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 48 X 48 inch traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 8 feet long. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Contract. For each direction of traffic, equip each 12.5-foot section of barrier with at least two side-mounted retroreflective tabs placed approximately 6 to 8 feet apart, or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier. Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 28 inches high. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint meeting Subsection 708-2.03 with glass beads meeting Subsection 712-2.08,

b.	Preformed Marking Tape (removable or non-removable) meeting Subsection 712-2.14, or

c.	Temporary Raised Pavement Markers meeting Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V. Application of crash cushion must be appropriate for the intended use and be installed per manufacturer’s recommendation. Temporary crash cushions used as rail or barrier end treatments must be redirective. Temporary crash cushions that are barrels or barricade filled with sand or water may only be used when the forecasted temperature during their use is above 32 degrees Fahrenheit.

11.	Sequential Arrow Panels. Use Type A (24 X 48 inch), Type B (30 X 60 inch) or Type C (48 X 96 inch) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs.  Use new truck or trailer mounted portable changeable message board signs with self-contained power supply for the sign and with:

a.	Message sign panel large enough to display 3 lines of 18-inch high characters

b.	Eight character display per message module

c.	Fully programmable message module

d.	Remote control cellular, wireless radio frequency (RF), landline

e.	Waterproof, lockable cover for the controller keyboard

f.	Capacity for electric/hydraulic sign raising or lowering

g.	Radar over speed detection

h.	Variable flash and sequence rates

i.	Light emitting diode (LED) display, using Institute of Transportation Engineers (ITE) amber/yellow

j.	The capacity for a minimum of 150 pre-programmed messages

k.	Battery-Pack Operation Duration:  minimum of 55 hours under full load

l.	Power chords shall comply with the National Electrical Code (NEC) Article 600.10 Portable or Mobile Signs, paragraphs 600.10(C)(1) Cords and 600.10(C)(2) Ground-Fault Circuit Interrupter (GFCI). The cord will have integral GFCI protection located in either the attachment plug or 12 inches or less from the plug.

13.	Plastic Safety Fence. Use 4-foot high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	"Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306.  Phone (800) 428-8185.

b.	"Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108.  Phone (800) 648-7916.

c.	"Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104.  Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 1/2-inch thick for areas continuously supported by subgrade. Use plywood at least 1 inch thick for areas that are not continuously supported.

b.	Do not use unsupported 1-inch plywood longer than 30 inches.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 1/2-inch. Bevel overlap joints so the maximum slope of the overlapping edge is 2 horizontal to 1 vertical.

d.	Fasten so wind and traffic will not displace temporary surfacing.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

16.	Flagger Paddles. Use flagger paddles with 24 inches wide by 24 inches high sign panels, 8 inch Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM.  Use retroreflective sheeting that meets ASTM D4956 Type VIII, IX or XI. Use background colors of fluorescent orange on one side and red on the other side.

17.	Truck Mounted Attenuator, TMA. The TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight per the manufacturer’s recommendations.

18.	Portable Steel Barriers. Use portable steel barriers that conform to the contract. For each direction of traffic, equip each section of barrier with side-mounted retroreflective tabs placed approximately 6 to 8 feet apart, or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier. Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV, or V.

19.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

CR643-010122/CFHWY00599

20. Pedestrian Barricades. Barricades shall be Americans with Disabilities Act (ADA) compliant with no trip hazards for pedestrians and meet MUTCD standards and ADA guidelines. Barricades must have FHWA Acceptance letter for National Cooperative Highway Research Program (NCHRP) 350 or Manual of Assessing Safety Hardware (MASH), Test Level 3. Barricade must be highly visible (color: white, orange or combination) that will allow them to be seen by the motorist and provide a stable support not easily blown over by the wind or traffic. Barricades can be a single unit or manufactured with a top wall and bottom base that connect together. Individual barricades shall be interlocked together to delineate for channelized flow with no gaps that allow pedestrians to stray from the channelizing path. Reflective sheeting must meet AASHTO M 268 Type III, IV, or V. Pedestrian barriers must be installed per manufacturer’s recommendations

CFHWY00599

643-2.02 Crashworthiness. Temporary Work Zone devices, including portable barriers, manufactured after December 31, 2019, must have been successfully tested to the 2016 edition of Manual for Assessing Safety Hardware (MASH). Such devices manufactured on or before this date, and successfully tested to National Cooperative Highway Research Program (NCHRP) Report 350 or the 2009 edition of MASH, may continue to be used throughout their normal service lives.

Submit documentation, by the method indicated on table 643-2, that the following devices comply with Test Level 3 requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or the Manual for Assessing Safety Hardware (MASH). Submit documentation of compliance to the Engineer before installing devices on the project.

TABLE 643-2

WORK ZONE TRAFFIC CONTROL DEVICE AND

BARRIER CRASH TESTING COMPLIANCE

| Category | Devices | Devices Manufactured Before Dec. 31, 20191 | Devices Manufactured after Dec. 31, 20191 | Method of Documentation |
| --- | --- | --- | --- | --- |
| 1 | Low-mass single-piece devices w/o attachments; traffic cones, tubular markers, single piece drums, delineators | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | Manufacturer's Certification for devices exceeding height and weight limits |
| 2 | Category 1 devices with attachments, barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in Category 1 | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, at Test Level 32. |
| 3 | Fixed sign supports, truck mounted attenuators, temporary crash cushions, bridge railing, bridge and guardrail transitions, and guardrail and barrier end treatments. | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, at Test Level 32. |
|  | Portable Concrete and steel barriers | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, if available, at Test Level 3, or DOT&PF eligibility determination, unless otherwise required in the Contract |

1The Engineer will determine whether a device is in serviceable condition. Serviceable means the device will function equivalent to a new device of the same manufacture.

2When no test level is specified in a FHWA Eligibility letter; it is implied that the tests were run for Test Level 3.

In Table 643-2, Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3. This certification may be a one-page affidavit signed by the vendor. Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization. No certification is required for devices less than or equal to both the weight and height on the schedule below:

Device	Composition	Weight	Height

Cones	Rubber	20 lb.	36 in.

Plastic	20 lb.	48 in.

Candles	Rubber	13 lb.	36 in.

Plastic 	13 lb.	36 in.

Drums	Hi Density Plastic	77 lb.	36 in.

Low Density Plastic	77 lb.	36 in.

Delineators	Plastic or Fiberglass	N/A	48 in.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Keep the work, and portions of the project affected by the work, in good condition to accommodate traffic safely. Provide and maintain traffic control devices and services inside and outside the project limits, day and night, to guide traffic safely.

Unless otherwise provided in this Section, keep all roadways, business accesses, and pedestrian facilities within the project limits open to traffic. Obtain the Engineer’s approval before temporarily closing residential, commercial, or street approaches. Provide access through the project for emergency vehicles and school and transit buses. Properly sign and/or flag all locations where the traveling public is redirected or stopped. Organize construction operations so the total of all construction related stoppages experienced by a vehicle traveling through the project does not exceed 20 minutes except when indicated otherwise in the Contract.

Stop equipment at all points of intersection with the traveling public unless an approved TCP shows otherwise.

Continue to operate all illumination and signalization according to the requirements of Subsection 660-3.09. When moving approach lanes, realign signal heads as necessary according to the ATM. Coordinate any modifications to existing traffic signals with the agency that maintains and operates them. Operate flood lighting at night according to the ATM. Adjust flood lighting so that it does not shine into oncoming traffic.

Provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times, except when regulations prohibit pedestrians or bicyclists. Station a flagger, where construction activity encroaches onto the safe route in a traffic control zone, to assist pedestrians, and bicyclists past the construction activity.

Maintain business access(s) during flagging operations.

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as an employee or a subcontractor becomes aware of the accident.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Obtain an approved TCP before reducing existing roadway lane and shoulder widths and before starting construction. Maintain a clear area with at least 2 feet between the edge of traveled way and the work area. Use barricades, traffic cones, or drums to delineate this area. Place traffic control devices on the work side of the clear area. Space them according to the ATM.

Where specified in the Plans, Specifications, Special Provisions, and or the TCP:  traffic may be maintained on a continuous gravel surface.

1.	Specified Gravel Surface.  Traffic may be maintained on a continuous gravel surface where specified:

a.			N/A		 Roadway 		N/A			 weeks.

b.	BOP to Station 			N/A		 : No time restriction.

c.	Station 		N/A			 to Station 		N/A		 (or EOP).

d.	Other project roadways:  1000 ft/5000 … ft, no time restriction.

2.	Gravel Surface Not Specified.

a.	Through traffic shall not traverse more than two gravel sections of roadway in any given period.

b.	Pavement Break(s) for Culvert or Utility Work:  Patch pavement breaks(s), with hot mix asphalt, not more than 48 hours after removing the existing pavement.

c.	When approved by the Engineer.

If maintaining traffic on an unpaved surface, provide a smooth and even surface that public traffic can use at all times. Properly crown the roadbed surface for drainage. Before beginning other grading operations, place sufficient fill at culverts and bridges to permit traffic to cross smoothly and unimpeded. Use part-width construction techniques when routing traffic through roadway cuts or over embankments under construction. Excavate the material or place it in layers. Alternate the construction activities from one side to the other. Route the traffic over the side opposite the one under construction.

Detour traffic when the Plans or an approved TCP allows. Maintain detour routes so that traffic can proceed safely. When detours are no longer required, obliterate the detour. Topsoil and seed appropriate areas.

If two-way traffic cannot be maintained on the existing roadway or detour, use half-width construction or a road closure if it is shown on an approved TCP. Make sure the TCP indicates closure duration and conditions. Schedule the roadway closures to avoid delaying school buses, and peak-hour traffic. For road closures, post closure-start and road-reopen times at the closure site, within view of waiting traffic.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.

643-3.03 PUBLIC NOTICE. Give notice at least 3 days before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

	Alaska Trucking Association

	Alaska State Troopers

	Division of Measurement Standards

	Local Police Department

	Local Fire Department

	Local Government Traffic Engineer

	School and Transit Authorities

	Local Emergency Medical Services

	Local Media (newspapers, radio, television)

	Railroads (where applicable)

	U.S. Postal Service

	Major Tour Operators

Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system. Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. These telephone numbers are used to alert construction employees when emergency vehicles must pass through the project. When notified of emergencies make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator or 511 System for selected projects. Check the special provisions for those requirements.

643-3.04 TRAFFIC CONTROL DEVICES. Before starting construction, erect permanent and temporary traffic control devices required by the approved TCPs. The Engineer will determine advisory speeds when necessary.

For lane closures on multilane roadways, use sequential arrow panels. During hours of darkness when required by the approved TCP, use flashing warning lights to mark obstructions or hazards and steady-burn lights for channelization.

Use only one type of traffic control device in a continuous line of delineating devices, unless otherwise noted on an approved TCP. Use drums or Type II barricades for lane drop tapers.

During non-working hours and after completing a particular construction operation, remove all unnecessary traffic control devices. Store all unused traffic control devices in a designated storage area which does not present a nuisance or visual distraction to traffic. If sign panels are post mounted and cannot be readily removed, cover them entirely with either metal or plywood sheeting. Completely cover signal heads with durable material that that fully blocks the view of signal head and will not be damaged or removed by weather.

Keep signs, drums, barricades, and other devices clean at all times.

Use only traffic control devices that meet the requirements of the “Acceptable” category in ATSSA (American Traffic Safety Services Association) “Quality Guidelines for Temporary Traffic Control Devices” and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project. Stock repair parts for each Temporary Crash Cushion used on the project. Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware. All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the plans, specifications, and approved TCPs until permanent roadside safety hardware is installed. All temporary roadside safety hardware shall meet crashworthiness requirements of Subsection 643-2.02.

All items paid under this Section remain the property of the Contractor, unless noted otherwise in the contract. Remove them after completing the project.

1.	Embankments.  Close trenches and excavations at the end of each continuous work shift, except as indicated by the Engineer.

Install portable concrete or steel barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as specified on the Plans or TCPs to delineate open trenches, ditches, other excavations, and hazardous areas when they exist along the roadway for more than one continuous work shift.

2.	Adjacent Travel Lane Paving. When paving lifts are 2 inches or greater and you cannot finish paving adjacent travel lanes or paved shoulders to the same elevation before the end of the paving shift, install: W8-11 (Uneven Lanes), W8-9 (Low Shoulder), W8-17 (Shoulder Drop-Off), W14-3 (No Passing Zone), R4-1 (Do Not Pass), R4-2 (Pass with Care), and W8-1 (Bump) signs as appropriate. Place additional signs every 1500 feet if the section is longer than 1/2 mile.

3.	Fixed Objects, Construction Vehicles and Equipment Working On or Next to the Traveled Way.  Do not park equipment in medians.  Locate fixed objects at least 30 feet from the edge of traveled way. Fixed objects that exist prior to construction activity are not subject to this requirement unless the proposed temporary traffic routing moves the edge of traveled way closer to the pre-existing fixed object.  Vehicles and other objects within parking lots in urban environments are considered preexisting fixed objects regardless of whether they are or are not present continuously throughout the day.

When worksite restrictions, land features, right of way limitations, environmental restrictions, construction phasing, or other construction conditions allow no practicable location meeting the preceding requirements, the Engineer may approve alternate locations for fixed objects. Alternate locations shall be as far as practicable from the edge of traveled way. When the alternate location provides 15 feet or more separation from the edge of traveled way, the Engineer may verbally approve the alternate location. When the alternate location provides less than 15 feet separation, written approval is required.

When the Engineer determines a fixed object or fixed objects present unacceptable hazard, use drums, or Type II barricades with flashing warning lights, or use portable concrete or steel barriers, or temporary crash cushion to delineate or shield the hazard, as approved by the Engineer.

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

4.	Flagging. Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone. The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

a.	Flagging Level I Certification by IMSA

b.	Flagger Certification by ATSSA

c.	Traffic Control Supervisor, ATSSA

d.	Work Zone Safety Specialist, IMSA

e.	ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification.  Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned flagging location at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements. Remove, fully cover, or lay down flagger signs when no flagger is present. Keep the flaggers’ area free of encumbrances.  Keep the flagger’s vehicle well off the roadway and away from the flagging location so the flagger can be easily seen.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer’s written approval before flagging signalized intersections. When flagging a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode. Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer. Get their written approval in advance. Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

5.	Pilot Cars. You may use pilot cars when part of an approved TCP, if the Engineer determines one-way traffic is necessary, or if the route through the traffic control zone is particularly hazardous, involved, or frequently altered to preclude adequate signing,  Do not use pilot cars to avoid localized traffic control at several locations.  Pilot car operators may not control Automated Flagger Assistance Devices while operating a pilot car.

Organize construction operations so the total of all stoppages experienced by a vehicle traveling through a project does not exceed 20 minutes. However, this does not imply that you may allow 20 minutes in all cases. Coordinate multiple pilot-car operations within a project or adjoining projects to minimize inconvenience to the traveling public. Two or more pilot cars may be used to provide two-way traffic through the traffic control zone to reduce the waiting period. The flagger or pilot car operator must record each pilot car’s departure time in a bound field book furnished by the Engineer. Whenever practical, the flagger should tell the motorist the reason for and approximate length of the delay. Make every reasonable effort to yield right-of-way to the public and prevent excessive delay.

Use an automobile or pickup as the pilot car, with the company logo prominently displayed. Equip the pilot car with a two-way radio for contact with flaggers and other pilot cars. Mount a G20-4 sign (Pilot Car Follow Me) on the rear at least 5 feet above the driving surface. Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on all Pilot Cars. Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.  Identify the last vehicle in the column.

When pilot car operations are approved, establish all required pilot car traffic control devices before beginning work.  Continue pilot car operations until no longer necessary and an approved TCP is in place for operations without pilot car, including all required traffic control devices.

6.	Street Sweeping and Power Brooming. Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material.  Use equipment for brooming and sweeping as recommended by the manufacturer and the following:

Dirt, dust and construction materials, mobilized as a result of power brooming and or sweeping, shall not be pushed, ejected, thrown or drift beyond the lesser of, 2 feet from the equipment perimeter or the edge of the paved surface.

All equipment shall operate to typical industry standards.  Maintain equipment to operate as designed by the manufacturer.  Equipment will employ safety equipment, warning lights, and other as required by the Specifications and these Special Provisions.

Sweeper and Broom Options:  Table 643-5, Traffic Control Rate Schedule, Street Sweeping

a.	Regenerative Sweeper:  Sweeper that blows a stream of air at the paved surface, causing fine particles to rise, and then caught through a vacuum system.

b.	Vacuum Sweeper:  Sweeper that creates a vacuum at the paved, surface sucking dirt, dust, and debris into a collection system.

c.	Mechanical Broom Sweeper:  Sweeper designed to pick up and collect larger size road debris, stones and litter, etc.  In addition to the requirements noted in these Specifications, use of a mechanical broom sweeper requires the Engineer to approve the sweeper for the intended use.

d.	Power Broom:  Power brooming that wets, pushes and or ejects loose material directly into an attached collection/pickup container may be used when approved by the Engineer.  The added moisture will be contained to the paved roadway surface.

Dry Power Brooming is not permitted.  Power brooming without direct/immediate means of collection/pickup is not permitted.

7.	Watering. Furnish, haul, and place water for dust control and pavement flushing, as directed. Use water trucks that can provide a high-pressure water stream to flush the pavement and a light-water spray to control dust. If the flushing operations contaminate or fill adjacent catch basins, clean and restore them to their original condition. This requirement includes sections of roadway off the project where flushing is required. The Engineer will control water application.

Obtain an Alaska Department of Natural Resources permit for water removal before taking water from a lake, stream, or other natural water body. Comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

8.	Portable Changeable Message Board Signs. Furnish Changeable Message Signs when approved on a TCP. Display only messages approved on the TCP. Follow application guidelines in the ATM.

9.	Truck Mounted Attenuator (TMA). TMAs are mounted on the rear of work vehicles. Impact attenuators shall meet crashworthiness requirements of 643-2.02. TMAs shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight in accordance with the manufacturer’s recommendations. TMAs shall have an adjustable height so that it can be placed at the correct elevation during usage and to a safe height for transporting. Approach ends of TMAs shall have impact attenuator markings in accordance with the ATM. Do not use a damaged attenuator in the work. Replace any damaged TMA at your expense.

10.	Traffic Control Vehicles.  Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on the Work Zone Supervisor’s vehicle and on vehicles being used to transport and set-up traffic control devices.  Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.

643-3.05 AUTHORITY OF THE ENGINEER.  When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice, and then a written notice according to Subsection 105-1.01, Authority of the Engineer. The notice will state the defect(s), the corrective action(s) required, and the time required to complete the corrective action(s). In no case shall this time exceed 24 hours.  If corrective action(s) are not completed within the specified time, the Engineer may immediately suspend work on the offending operations until the defect(s) are corrected. The Engineer may require outside forces to correct unsafe conditions. The cost of work by outside forces will be deducted from any monies due under the terms of this Contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. A Traffic Price Adjustment, under Item 643.0023.____, will be assessed for unauthorized lane closures or reductions. Unauthorized lane reductions will be assessed as one full lane closure, for each lane reduced without authorization.

Authorized lane closures and/or lane reductions are those shown in the Contract, an approved TCP, or authorized in writing.

Unauthorized lane reductions include unacceptable roadway, pedestrian walkway or route, and bicycle route or pathway surfaces, such as severe bumps, ruts, washboarding, potholes, excessive dust or mud, and non-conforming or out of place traffic control devices. Failure to install temporary crash cushions or barriers, when required according to the Contract or TCP, is also considered an unauthorized lane reduction. The Engineer will make the sole determination whether unauthorized lane reductions or closures are present.

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-3, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

The rates are liquidated damages which represent highway user costs, based on Average Daily Traffic (ADT). The Engineer will use the rate shown for the current ADT for this project, as published in the Regional Traffic Volume Report prepared by the Department's Planning Section. Adjustment rates for unauthorized reduction or closure of each lane of pedestrian walkways or route, and bicycle route or pathway, are the same as for one full roadway lane closure.

TABLE 643-3

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Unauthorized Lane Reduction or Closure |
| --- | --- |
| Less than 1,000 | $6 |
| 1,000-4,999 | $25 |
| 5,000-9,999 | $75 |
| 10,000-29,999 | $105 |
| 30,000+ | $150 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month before work is suspended for the season, schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the anticipated roadway condition and the work expected to be completed before shutdown. Schedule a field review with the Department for winter maintenance acceptance. At the field review, the Engineer will prepare a punch list for implementation before acceptance.

To be relieved of winter maintenance responsibility, leave all roads with a smooth and even surface for public use at all times. Properly crown the roadbed surface for drainage and install adequate safety facilities. Make sure all illumination and signals, including vehicle detectors, are in good working order.

After the project is accepted for winter maintenance and until ordered to resume construction operations, the Department is responsible for maintaining the facility. The Department will accept maintenance responsibility only for portions of the work that are open to the public, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. The contractor is responsible for maintaining all other portions of the work. The Engineer will issue a letter of “Acceptance for Winter Maintenance” that lists all portions of the work that the Department will maintain during a seasonal work suspension. The contractor retains all contractually required maintenance responsibilities until receipt of this letter.

If the contractor suspends work due to unfavorable weather (other than seasonal) or due to failure to correct unsafe conditions, carry out Contract provisions, or carry out the Engineer’s orders. All costs for traffic maintenance during the suspended period will be borne by the Contractor.

When work is resumed, replace or renew any work or materials lost or damaged during temporary use. If the Department caused damage during winter suspension, payment will be made for repairs by unit pay item or in accord with Subsection 109-1.05, Compensation for Extra Work. When the Engineer directs, remove any work or materials used in the temporary maintenance. Complete the project as though work has been continuous.

643-3.08 CONSTRUCTION SEQUENCING. The construction sequencing detailed in these provisions, the Special Provisions, and the Plans is suggested only. The Contractor may propose alternative construction sequencing.

Throughout the project, maintain the existing roadway, pedestrian walkway, or route, and bicycle route or pathway configuration (such as the number of lanes and their respective widths) except for restrictions to traffic allowed in the Special Provisions or on the Plans, and addressed through approved TCPs. A restriction to traffic is any roadway surface condition, work operation, or traffic control setup that reduces the number of lanes or impedes traffic. Obtain an approved TCP before restricting traffic.

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below:

1.	Monday through Sunday:  0530 hrs to 2100 hrs.

2.	Around any Holiday:

a.	If a holiday falls on Sunday, Monday, or Tuesday, the above stipulations apply from 1200 hrs on the Friday before the holiday to 0300 hrs. on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 hrs on the Tuesday before the holiday to 0300 hrs. on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 hrs on the day before the holiday to 0300 hrs. on the Monday after the holiday.

3.	During the Alaska State Fair:  Friday from 1600 hrs. to Sunday 2300 hrs on all streets except Palmer-Wasilla Highway.  Weekend traffic restrictions not allowed on Palmer-Wasilla Highway.

4.	Road Closures:

| Event | Maximum Duration | Minimum Notice | Remarks |
| --- | --- | --- | --- |
| Riley Avenue – Utility Work | 2 Calendar Days | Three weeks’ notice to local businesses and property owners along S. Knik Goose Bay Road and adjacent side streets as determined by the Engineer with an approved TCP. | - Each full closure shall not be concurrent with other roadway closures. - All local accesses shall be maintained. |
| S. Endeavor Street – Utility Work | 2 Calendar Days |  |  |
| S. Weeping Birch Street – Utility Work | 2 Calendar Days |  |  |
| Volt Road – Utility Work | 2 Calendar Days |  |  |
| S. Heritage Farm Road & W. Stonebluff Drive Intersection – Utility Work | 4 Calendar Days |  |  |
| W. Pipestone Drive – Utility Work | 1 Calendar Day |  |  |
| W. Kanabec Drive – Utility Work | 1 Calendar Day |  |  |

Lane restrictions, if allowed shall be conducted so that no more than a 5 minute accumulated stopped delay, 20 vehicles, or 1/8 mile (660 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 10 minute stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic detained, allowed for motorists, except school buses.  If a queue of traffic develops at a stop, empty the entire queue to include the last car that entered the queue at the time the queue was released.

Do not delay the school busses through the construction zone; obtain the local school bus schedule and coordinate work efforts.  Submit the plan, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS. Place permanent or interim pavement markings according to this Subsection, details shown on the Plans, approved TCPs, and Parts III and VI of the ATM before opening existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments for more than one continuous work shift. This work may include restriping the existing roadway before beginning construction, before seasonal suspension, and/or after seasonal suspension.

Remove conflicting pavement markings according to Subsection 670-3.04, Paint Removal.

Mark existing roadway sections that will be opened to traffic during the winter. Mark over the existing lines and markings, unless shown otherwise on the Plans or an approved TCP.

Maintain all interim pavement markings for their intended life including reapplication when necessary. There will be no compensation to upgrade interim pavement markings required for work operations lasting up to 2 weeks.

Use only temporary raised pavement markers as interim pavement markings on final pavement surfaces. Completely remove and dispose of them when placing the final markings. Completely remove any residual adhesive that might misguide motorists. Place final pavement markings on finished pavement surfaces and interim pavement surfaces before suspending work for the winter.

Stage the construction to avoid routing traffic over conflicting markings, for more than one continuous work shift. If traffic is routed over conflicting markings during a work shift, delineate the roadway with a complement of warning signs, channelizing devices, and flaggers as required by the ATM.

Use only temporary raised pavement markers meeting Subsection 712-2.16 as interim markings on seal coat and surface treatment pavements. Install the markers according to the manufacturer’s instructions before applying the asphalt surface material and cover coat. Remove the vinyl protective covers after applying the asphalt pavement.

On multicourse surface treatments, install the temporary raised pavement markers after applying the full width of the first layer of cover coat. Install the markers on each day's completed surface before removing the pilot car operations and allowing unescorted traffic on the surface treatment.

Apply final pavement markings according to Subsection 670-3.01, Construction Requirements, of these Special Provisions.

Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer.

643-3.10 LIGHTING FOR NIGHT WORK. Illuminate the night work areas according to Table 643-4.

Table 643-4 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

Use balloon lighting as the main light sources. Do not use floodlights without prior approval by the Engineer. When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway. Locate, aim, louver, and/or shield light sources to reduce glare.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences. When notified of unacceptable glare, modify the lighting system to reduce glare to an acceptable level.

TABLE 643-4

NIGHT WORK ILLUMINATION EQUIPMENT AND LOCATION REQUIREMENTS

| Type of Work or Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation. | At least one machine-mounted balloon light of at least 2000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping. | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging. | One balloon light of at least 2000 watts, located within 30 feet of the flagger location. Locate so the flagger and the flagging location are illuminated. Provide additional lights or wattage if necessary to provide complete coverage of the flagging location. |
| Truck Crossings where haul vehicles cross or enter a road with more than 10,000 ADT, or where the haul vehicle crossing or entering location is controlled by portable traffic signals or flaggers. | At least one balloon light of at least 2000 watts, located on the main road on the far right side of the intersection. Locate light within 30 feet of the edge of the side street. If there is a flagger at the crossing, locate the lights or lights so the lighting requirements for Flagging are also satisfied. |

If the Contractor fails to provide required lighting equipment or provides lighting that creates unacceptable glare, the Contractor shall cease all construction activities that require illumination, including flagging operations, until the condition or conditions are corrected.

Use lighting equipment in good operating condition and that complies with applicable state and local adopted codes and standards, and OSHA, NEC, and NEMA requirements.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment. Design mountings so lights can be aimed and positioned as necessary to reduce glare. Locate mounting brackets and fixtures so they don’t interfere with the equipment operator or overhead structures. Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment-mounted light towers or poles are sturdy and freestanding without the aid of guy wires. Towers shall be capable of being moved as necessary to keep pace with the construction operation. Position the ground and trailer-mounted towers and trailers, to minimize the risk of being impacted by traffic on the roadway, or by construction traffic, or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as overhead signals, overhead signs, trees, aerial utilities, or bridges. Aim and adjust lights to provide the required light levels. Provide uniform illumination on the hopper, auger, and screed areas of pavers. Illuminate the operator’s controls on all machines uniformly.

Furnish each side of non-street legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights may supplement but do not relieve the Contract requirement to provide lighting for night work, according to the requirements of Table 643-4.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that all required lights operate continuously during nighttime operations. Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours. In the event of any failure of the lighting system, discontinue the operation that requires illumination until the required level and quality of illumination is restored.

Maintain a supply of at least twenty emergency flares for use in the event of emergency or unanticipated situations. Comply with local noise ordinances.

Install all post-mounted electroliers located within the clear zone, on NCHRP 350 or MASH compliant breakaway bases.

643-3.11 HIGH VISIBILITY GARMENTS. Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004 or ANSI/ISEA 107-2010.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise). Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottom at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to the requirements of this Subsection 643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

7.	Condition.  Furnish and maintain all vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition. Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic contract items.

643-4.01 METHOD OF MEASUREMENT. Section 109 and as follows: Quantities will not be measured during winter suspension of work.

1.	Traffic Maintenance. Calendar Day: Every day shown on the calendar, beginning and ending at midnight. Measurement begins on the day following receipt of the Notice to Proceed or on the first day of work at the project site, whichever is later, and ends on the date of project completion.

2.	Traffic Control Device Items. By the number of units of each bid item shown on the bid schedule (or the Traffic Control Rate Schedule, if item 643.0025.____, Traffic Control, is included) that are installed, accepted, and operational. Incomplete or unsatisfactory devices will not be measured. Special Construction Signs are measured by the total area of legend-bearing sign panel, as determined under Subsection 615-4.01. Compensation for a 24-hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-5. Items measured by the day are for each item per 24-hour period.

3.	Traffic Maintenance Setup Items. By each lane closure or one-lane road in place per hour. By each detour or road closure in place per 24-hour period.

4.	Portable Concrete Barrier. By each nominal 12.5-foot section placed according to the approved TCPs, for the initial placement and for each subsequent relocation when moved more than 10 feet in any direction. Each transition piece (sloping end) will be measured as a single section.

5.	Temporary Crash Cushion. By each acceptable installation.

6.	Interim Pavement Marking. By the single-stripe station. A single stripe is a marking or a temporary raised pavement marker 4 inches wide. Wider striping is measured in multiples of 4 inches. Centerline gaps are not deducted from measurements.

7.	Flagging and Pilot Car. By the number of approved hours, supported by certified payroll.

8.	Street Sweeping. By the number of operated hours, supported by certified payroll and approved by the Engineer.

9.	Watering. By the 1,000 gallons (M-Gallon) of water applied. The Engineer may specify measurement by weight or volume. If by weight, convert to gallons at 8.34 pounds per gallon. If by volume, convert to gallons at 7.48 gallons per cubic foot.

10.	Traffic Price Adjustment. By each minute that any lane of traffic is not open to full use by the traveling public, measured to the nearest minute. The Engineer will determine whether the roadway is opened to full use.

11.	Traffic Control. By the units specified in the Special Provisions.

12.	Portable Changeable Message Board Sign. By the 24-hour period for each sign, as shown on an approved TCP and displaying an approved message.

13.	Plastic Safety Fence. By the linear foot, as placed, to protect or channelize pedestrian traffic as shown on an approved TCP. Any adjustment in configuration of the fence at the same location that does not result in an increased amount of fence is not measured. Opening and closing the fence to gain access to and from the worksite is not measured.

14.	Temporary Sidewalk Surfacing. By the square yard as shown on an approved TCP.

15.	Temporary Guardrail. By the linear foot, including end treatments, as shown on an approved TCP.

16.	Portable Steel Barrier. By the linear foot placed according to the manufacturer’s recommendation and approved TCPs, for the initial placement, and for each subsequent relocation when moved more than 10 feet in any direction.

17.	Hotline Road Report.  No measurement required to provide a 24-hour toll free (1-800 ###-####) “Hotline Road Report” telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Pay Item 643.0001.____ or 643.0002.____, Traffic Maintenance.

CR643-010122/CFHWY00599

18. Pedestrian Barrier. By each nominal 4 foot section placed according to the approved TCPs, for the initial placement and for each subsequent relocation when moved more than 10 feet in any direction.

CFHWY00599

643-5.01 BASIS OF PAYMENT.

1.	Traffic Maintenance. The contract price includes all resources required to provide the Worksite Traffic Supervisor, all required TCPs and public notices, the Construction Phasing Plan, and the maintenance of all roadways, approaches, crossings, intersections and pedestrian and bicycle facilities, as required. This item also includes any Traffic Control Devices required but not shown on the bid schedule.

Items required by the Contract that are not listed on the bid schedule or not included in other items are subsidiary to Item 643.0001.____ or 643.0002.____ Traffic Maintenance, except the following:

a.	Traffic Price Adjustment

b.	Traffic Maintenance Setup

2.	Traffic Control Device Items. The contract price includes all resources required to provide, install, maintain, move, and remove the specified devices. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

3.	Traffic Maintenance Setup Items. Each setup consists of all traffic control devices, flaggers, pilot cars, and subsidiary items necessary to implement the TCP shown on the Plans. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

Construction and obliteration of temporary roadways, when required on the Plans or approved TCP under a traffic maintenance setup item, is paid for under their respective roadway pay items.

When topsoil or seeding is required for detours, payment will be made under Sections 620 and/or 618.

4.	Portable Concrete Barrier. The contract price includes all resources required to provide, install, maintain, and remove each barrier section.

5.	Temporary Crash Cushion. The contract price includes all resources required to provide, install, maintain, repair, and remove each crash cushion.

6.	Interim Pavement Marking. The contract price includes all resources required to provide, install, maintain, and remove the specified markings. Installation of word and symbol markings are subsidiary. The No-Passing Zone signing, described in Subsection 643-3.04, is subsidiary.

7.	Flagging and Pilot Car. The contract price includes all required labor, vehicles, radios, flagger paddles and pilot car signs, and transportation to and from the worksite.

The Engineer will pay for Item 643.0032.____ Flagging on a contingent sum basis at the rate of $65.00/hour.  The Engineer does not require a change order/directive for the flagging Pay Item.  Flagging associated with Change Order work paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

8.	Street Sweeping. The contract price includes all resources required to keep the roadway free of loose material.

9.	Watering. The contract price includes all resources required to provide watering, as directed.

10.	Traffic Price Adjustment. If Item 643.0023.____, Traffic Price Adjustment, is shown on the bid schedule, the total value of this contract will be adjusted, for unauthorized lane reductions or closures, at the rates listed in Table 643-3.

11.	Traffic Control. Payment for Item 643.0025.____, Traffic Control, will be made at the unit rate value contained in the Traffic Control Rate Schedule shown in the Special Provisions for the accepted units of traffic control devices. The Engineer does not require a change order/directive for Pay Item 643.0025.____, Traffic Control.

12.	Portable Changeable Message Board Sign.  The contract price includes all resources required to furnish, move, and operate the sign.

Four Portable Changeable Message Board Signs used for Permanent Construction Signing paid for under Item 643.0003.____ Permanent Construction Signs.  Additional portable changeable message board signs will be paid for under 643.0025.____, Traffic Control.

13.	Plastic Safety Fence.  The contract price includes all resources required to install, maintain, and remove the fence.

14.	Temporary Sidewalk Surfacing.  The contract price includes all resources required to construct, maintain, and remove the surfacing.

15.	Temporary Guardrail.  The contract price includes all resources required to construct, maintain, and remove the guardrail.

16.	Portable Steel Barrier.  The contract price includes all resources required to provide, install, maintain, move, and remove each barrier.

17.	Lighting for Night Work.  Payment for illuminating night work areas and any required adjustments to work zone illumination is subsidiary to other items.

18.	Pavement Breaks.  Temporary hot mix asphalt at pavement breaks, as noted in Subsection 643-3.02.2. Gravel Surface Not Specified is subsidiary to Pay Item 401.0001.____.

19.	Temporary Pavement Markings.  Except where specified as an individual Pay Item (Interim Pavement Markings) temporary pavement markings are subsidiary to Section 670 Pay Items. Refer to Section 670 Traffic Markings, for further information.

20.	Temporary Crash Cushion / Redirective.  The price listed in the Traffic Control Rate Schedule, Table 643-5, will be full compensation for the purchase, installation, maintenance during construction, removal, and salvaging the Temporary Crash Cushion / Redirective unit(s).  Deliver the salvaged unit(s) to the nearest ADOT & PF Maintenance & Operations Station or as directed by the Engineer.

CR643-010122/CFHWY00599

21.	Pedestrian Barrier.  The contract price includes all resources required to provide, install, maintain, and remove each barrier section.

22. Interim Lane Configuration Traffic Control Devices. The contract price includes furnishing and installing permanent Type III barricades and flexible delineators at the Knik-Goose Bay Rd and Palmer-Wasilla Hwy intersection as shown on the Plans.

MMA pavement markings for the interim configuration will be paid under 670.2000.____.

CFHWY00599

Traffic control devices, barriers, and crash cushions required to delineate or shield fixed objects will not be measured or paid for separately, but will be subsidiary

Traffic control devices, barriers, and crash cushions required to delineate or shield guardrail posts or non-crashworthy ends will not be measured or paid for separately, but will be subsidiary, when required for failure to meet completion timelines in subsection 606-3.01.

TABLE 643-5

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $31.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Sequential Arrow Panel | Each/Day | $40.00 |
| Portable Concrete or Steel F Shape Barrier (12.5 foot long or $8/foot for other lengths) | Each | $100.00 |
| Temporary Crash Cushion / Non-redirective Water Filled Barrier (all required per end) | Each | $2500.00 |
| Temporary Crash Cushion / Non-redirective Water Filled Barrels (all required per end) | Each | $3285.00 |
| Temporary Crash Cushion / Non-redirective Sand Filled Barrels (all required per end) | Each | $4325.00 |
| Temporary Crash Cushion / Redirective | Each | $9230.00 |
| Pilot Car (4x2, 1/2 ton truck) | Hour | $77.00 |
| Watering Truck – up to 4900 gallon capacity | M-Gallon | $28.00 |
| Watering Truck – more than 4900 gallon | M-Gallon | $21.00 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical or Power Broom with Vacuum | Hour | $214.00 |
| 40,000 GVW Truck with Crash Attenuator | Hour | $162.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Portable Changeable Message Board Sign | Calendar Day | $130.00 |
| Temporary Sidewalk Surfacing | Square Foot | $2.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |
| Temporary Guardrail | Lineal Foot | $25.00 |
| Interim Pavement Markings |  |  |
| Painted Markings | Lineal Foot | $0.30 |
| Temporary Raised Pavement Markers | Lineal Foot | $1.00 |
| Word or Symbol Markings | Each | $55.00 |
| Temporary Cover markings | Lineal Foot | $4.00 |
| Removal of Pavement Markings | Lineal Foot | $1.25 |

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 643.0001.____ | Traffic Maintenance | CDAY |
| 643.0002.____ | Traffic Maintenance | LS |
| 643.0003.____ | Permanent Construction Signs | LS |
| 643.0004.____ | Construction Sign | Day |
| 643.0005.____ | Type II Barricade | Day |
| 643.0006.____ | Type III barricade | Day |
| 643.0007.____ | Traffic Cone/Tubular Marker | Day |
| 643.0008.____ | Plastic Safety Fence | LF |
| 643.0009.____ | Drum | Day |
| 643.0010.____ | Sequential Arrow Panel, Type C | Day |
| 643.0011.____ | Special Construction Signs | SF |
| 643.0012.____ | Portable Concrete Barrier | Each |
| 643.0013.____ | Temporary Crash Cushion | Each |
| 643.0014.____ | Interim Pavement Marking | STA |
| 643.0015.____ | Flagging | HR |
| 643.0016.____ | Pilot Car | HR |
| 643.0017.____ | Street Sweeping | HR |
| 643.0018.____ | Watering | MGAL |
| 643.0019.____ | Lane Closure | HR |
| 643.0020.____ | Detour | Day |
| 643.0021.____ | Road Closure | Day |
| 643.0022.____ | One Lane Road | HR |
| 643.0023.____ | Traffic Price Adjustment | CS |
| 643.0024.____ | Portable Changeable Message Board Sign | Day |
| 643.0025.____ | Traffic Control | CS |
| 643.0026.____ | Temporary Sidewalk Surfacing | SY |
| 643.0027.____ | Temporary Guardrail | LF |
| 643.0030.____ | Portable Steel Barrier | LF |
| 643.0031.____ | Interim Pavement Marking | LS |
| 643.0032.____ | Flagging | CS |
| 643.0033.____ | Detour | LS |

CR643-010122

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 643.2022.____ | Pedestrian Barrier | Each |
| 643.2036.____ | Interim Lane Configuration Traffic Control Devices | LS |

CFHWY00599

- SECTION 644
SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

Replace Subsection 644-2.01 with the following:

644-2.01 FIELD OFFICE. Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Provide engineering communication services to the field office, Subsection 644-2.08.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

12.	Provide a security system controlled by the Department for the office including camera coverage for the vehicle parking.

CR644.FOCOM-080120

644-2.02 FIELD LABORATORY.

Replace 2.g. with the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Replace Subsection 2.h.(2) and (3) with the following:

(2)	Wiring system to support a 100-amp user load demand with one 50-amp and two 20-amp circuits, all GFI protected.

(3)	Outlets, ten conveniently spaced around the lab, 20-amp capacity, with no more than five outlets per circuit, and consistent with local codes.

Add 2.h.(6):

(6)	Outside outlet, 220-volt.

Replace Subsection 4.c.(3) with the following:

Wiring system with each circuit GFI protected to satisfy a 60-amp user load demand. Provide three 20-amp circuits each with a 20-amp outlet. Space the outlets around the shed for the users convenience.

Replace 6.a. with the following:

a.	Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

Add the following:

7.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

8.	Provide engineering communication services to the field laboratory, Subsection 644-2.08.

9.	Provide a security system controlled by the Department for the lab including camera coverage for the vehicle parking.

CR644.LAB-080120

644-2.05 VEHICLES.

Replace the second and third paragraphs with the following:

Pickup(LT)/Sport Utility Vehicle (SUV):  Furnish full-size, four-wheel drive vehicles, either pickup/light truck(s) with crew cabs or sport utility vehicle(s).  Provide vehicles less than three model years old, in good condition, and with less than 36,000 miles on the odometer.  Furnish all fuels, maintenance and parts, and insurance during the Department’s operation and use.

Equip each vehicle with lightbars wired into the vehicle’s electrical system with a dash mounted switch easily accessible to the vehicle operator.  Provide Code 3; Reflex C5590AA 15.3-inch mini lightbar, or approved equal.  Approved equal equipment shall have the following characteristics:

	(4) 55 watt rotators with amber filters

	1200 flashes per minute

	(2) diamond mirrors

	55 inches in length

Equip each vehicle with hands-free communication connectivity.

If you are working after October 1, provide four studded snow tires mounted on each vehicle.

You are responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use.  The State of Alaska is responsible for damage to any vehicle caused by its own negligent operation.

CR644.LTSUV-113020

Add the following:

All-Terrain Vehicle (ATV):  Provide a 4x4 all-terrain vehicle (ATV), 300 cc minimum, with a 500 lb capacity trailer.  The ATV must be less than three model years old and in good condition.  Equip, with a set of portable two-way radios with a secure transport anchor/holder and a vertically extended rotating beacon or strobe light.  All vehicle requirements for fuel, oil, maintenance, and insurance apply to the ATV.  Submit the ATV and accessory specifications including photos of the exterior to the Engineer and receive approval prior to providing the vehicle for use.  Coordinate the schedule for submittal and delivery (for use) with the Engineer.

CR644.ATV-022015R

Add the following:

Utility Vehicle (UTV).

Model Year	Three or less model years old

Good Condition

Body:	All original parts, straight, no rust, broken plastic or fiberglass, minor dings, chips, working head and tail lights

Frame:	Original factory condition, (Includes roll cage and bumpers)

Mechanical & Elec	Condition would not preclude manufacture warranty coverage

(actual warranty coverage is not required)

Tires/Rims	All purpose tires, less than 1/3 tread wear, straight rims

Seating	Side-by-side, buckets or bench, 2 person seating

Engine & Electrical

Type		4-cycle gas, liquid cooled, electronic fuel injection

Displacement	450 cc minimum, 20 hp minimum

Fuel Capacity	6 gallons, minimum

Ignition Type	Solid state 12V – electronic, keyed

Drive System

4WD	On-demand true four-wheel drive system

Front/Rear Differential	Auto-locking, 4 wheel shaft drive

Transmission	Automatic, dual range forward/reverse

Transaxle	Two speed

Brakes	Front/rear hydraulic disk

Park Brake	Mechanical, hand operated

Suspension

Front	Independent with Struts

Rear	Independent with coil over shock

Occupant Protective Sys (OPS)	Tubular overhead structure, passenger grab handles

Seat Belts	3-point seat belts

Certification	ROPS standards (Rollover Protective Structure)

All Weather Cab	Enclosed with hard top, storage glove box

Sound Rating@ Op Ear	87-90 dB

Tires	Dia. 25x, 14 psi max (fully loaded), all purpose

Wheelbase/Tread Centers	1.75 maximum, 12 inch min ground clearance

Towing Capacity	1300 lb, include hitch, ball mount and ball

Payload Capacity	1400 lbs

Cargo Box	Steel, 43L x 46W x 9D, 10 cu ft, 400 lb min, hinged tailgate,

cargo restraint system

Safety Lights	Safety Lights	Vertically extended operable rotating amber beacon or

strobe light.  SAE Spec. Class 1 or 2, J845 – 360 Rotating Lights or J1318 Flashing Strobe Lights.  Mount beacon to be visible at eye level at all times inside a 60 ft radius about the equipment, day or night.

Manufacturers:	Whelen Engineering Company,	Public Safety Equipment (PSE),

Federal Signal,	Or Approved Equal

UTV(s) meeting these specifications include, but are not limited to:

Polaris	Ranger 4x4	Kawasaki	Mule 4010 4x4

Honda	Big Red	John Deere	Gator HPX 4x4, or

Yamaha	Rhino 700	Approved Equal

Typical vehicle requirements including but not limited to: fuel, preventative maintenance, maintenance, and insurance apply to the UTV.

Submittal:  Submit the UTV vehicle and accessory specifications including photos of the UTV to the Engineer and receive approval prior to providing the vehicle for use.

CR644.UTV-022015R

Add the following Subsection 644-2.08 Engineering Communication and Office Equipment:

644-2.08 ENGINEERING COMMUNICATION AND OFFICE EQUIPMENT.  Engineering Communications and Office Equipment, minimum service includes:

1.	Three phone/facsimile lines and commercial phones (different phone numbers for each line)

a.	One phone with built-in digital answering machine.

b.	Ancillary equipment for operational service and as required by the Engineer.

2.	High speed internet service with modem (DSL or Cable)

a.	Send and receive capability supporting 10.0 Mbps download and upload speed or higher at all times.

b.	Data usage, 10 GB minimum monthly.

c.	Wireless router.

d.	Battery backup.

e.	Ancillary equipment for operational service and as required by the Engineer.

3.	Equipment rental services

a.	All-in-one printer/copier/scanner

(1)	Black-white and color

(2)	Pages per minute (ppm): 50

(3)	Paper trays: 8.5" x 11" and 11" x 17"

(4)	Capacity: 1100 sheets minimum

CR644.FOCOM-080120

644-4.01 METHOD OF MEASUREMENT.

Replace the third paragraph with following:

Vehicle (LT/SUV). For each vehicle provided. If a replacement vehicle is necessary, no additional measurement will be made.

CR644.LTSUV-113020

Replace the third paragraph with the following:

Vehicle (ATV).  For each vehicle provided.  If a replacement vehicle is necessary, no additional measurement will be made.

CR644.ATV-022015R

644-5.01 BASIS OF PAYMENT.

Add the following:

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Pay Item 644.0002.____ Field Laboratory.

CR644.LAB-080120

Add the following:

Pay Item 644.2004.____ Engineering Communications:

Usage services including long distance calls made by State personnel and the Internet service provider will be reimbursed by the State.  Payment for communication usage services and equipment rental agreements shall be based on paid receipts to the service provider plus 15%.

Connection fees (initial connection) local calls, providing equipment and disconnection are subsidiary to Pay Item 644.0001.____ Field Office and as such are paid by the Contractor.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 644.2004.____ | Engineering Communications | CS |

CR644.FOCOM-080120

Add the following:

Pay Item 644.2007.____ Vehicle (LT/SUV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 644.2007.____ | Vehicle (LT/SUV) | Each |

CR644.LTSUV-113020

Special Provision

Add the following Section:

SECTION 645
TRAINING PROGRAM

645-1.01 DESCRIPTION. This Statewide Special Provision for on-the-job training (OJT) implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective. Training and upgrading of minorities and women toward journey status is the primary objective of this program. The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision. Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301.

645-3.01 General. The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive. Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Office of Apprenticeship (USDOL/OA); or one developed by the Contractor using Form 25A-310 and approved prior to contract award by the OJT Coordinator in the DOT&PF Civil Rights Office.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor. Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed. It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project. Existing USDOL/OA apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. The Contractor must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period. Trainee wages shall be identified on Form 25A-310. Apprentices in USDOL/OA training programs shall be paid in accordance with their approved program. Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts. In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor. Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate. However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls. There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section. Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment. Payment will be made at the contract unit price for each hour of training credited. Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311 may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project. No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown in the Bid Schedule and approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown in the Bid Schedule and approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry. Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program. Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits. The journey worker scale is that for the classification identified in the approved programs.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 645.0001.____ | Training Program, Trainees/Apprentices | LH |

HSP20.2-113020

SECTION 646
CPM SCHEDULING

Special Provisions

Replace Subsection 646-2.01 with the following:

646-2.01 SUBMITTAL OF SCHEDULE.

Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.

Delete No. 2.

2.	60-Day Preliminary Schedule.

Replace the first sentence of No. 3 Schedule Updates. with the following:

Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

CR646.1-070214R

Special Provisions

Add the following Section:

SECTION 647
EQUIPMENT RENTAL

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled, and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, except holidays.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. Section 109.

Hourly Rental Rate: Includes the equipment rate plus the operating costs including: furnishing, travel time, operating, maintaining/servicing and repairing the equipment along with the costs incidental to the equipment and its' operation.

647-5.01 BASIS OF PAYMENT. Payment is for the time that fully operational equipment is engaged in the performance of the work directed by the Engineer. Time not paid for includes: idle periods, maintaining/servicing and repairing the equipment, making change-overs of equipment parts, and time to travel to and from the project.  Payment will only be for time supported by certified payroll.

Furnishing and operating equipment that is heavier, has larger capacity, or greater power than specified will not entitle the Contractor to extra compensation.

Pay Item 647.2002.____ Backhoe, 4WD, 1 CY Bucket, 75-HP Minimum, 15 ft Depth: paid at the rate of $180/hour.

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 647.2002.____ | Backhoe, 4WD, 1 CY Bucket, 75-HP Minimum, 15 ft Depth | CS |

CR647-110316R

Special Provision

Replace Section 651 with the following:

SECTION 651
CONTROL OF WORK – SUPPLEMENTAL REQUIREMENTS

651-1.01 DESCRIPTION.  Supplemental requirements for Section 105, Control of Work.

651-1.02 RELATED SECTIONS.  Section 105, Control of Work

651-1.03 UTILITIES.  Request locates from the utilities having facilities in the area.

Use the Alaska Digline, Inc. "Locate Call Center" for the following utilities.

ALASKA DIGLINE, INC.

Locate Call Centers: Anchorage 278-3121 Statewide (800) 478-3121

Call Centers will notify the following: City of Wasilla – Public Works (CWPW) ENSTAR Natural Gas Company (ENS) GCI Communication Corp. (GCI) Matanuska Electric Association, Inc (MEA) Matanuska Telephone Association (MTA)

State Facility Utilities: before beginning work, contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the District Superintendent's phone number where the project is located, and request locates.

Utilities Relocated by Others.

Utilities will be relocated by others concurrently with construction of this project.  The Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.

For utilities being relocated, the Contractor shall:

1.	include utility work on the Construction Phasing Plan and Progress Schedule;

2.	provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work.  Identify all utility companies performing ground disturbing activity in the Storm Water Pollution Prevention Plan (SWPPP).  Refer to Section 641 for further information;

3.	clear and grub.  Payment will be made under Section 201, Clearing and Grubbing;

4.	provide traffic control and flagging.  Payment will be made under Section 643, Traffic Maintenance;

CR651-020118R2_SSHC2020/CFHWY00599

5.	provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

	Control for utility relocation - either ROW or Centerline staking with Station information.

	Slope staking.

	Proposed structures, not including utilities to be relocated by others.

Payment will be made as follows:

a.	Subsidiary to Pay Item 642.0001.___ Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642.0003.___ Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 7 calendar days advance written notice for required staking.

CFHWY00599

6.	remove and replace pavement.  Payment will be made under Section 202, Removal of Structures and Obstructions; Section 401, Hot Mix Asphalt and Surface Treatments; Section 408, Hot Mix Asphalt and Surface Treatments, Type V; Section 409, Hot Mix Asphalt and Surface Treatments, Type R (Crumb Rubber) and according to project typical section.

7.	remove and replace sidewalk and curb and gutter.  Payment will be made under Section 202, Removal of Structures and Obstructions, Section 608, Sidewalks, and Section 609, Curbing.

8.	provide bedding and backfill material, in accordance with Section 204, Structure Excavation for Conduits and Minor Structures, and the project typical sections.

9.	coordinate with the utility owner(s) and provide potholing services at the locations identified or as directed by the Engineer.  Payment will be made under Section 682, Utility Potholing.

CR651-020118R2_SSHC2020/CFHWY00599

Work done by utility owner(s) is as follows:

The utility relocation work has been broken into two segments to maximize the overall efficiency of the project and minimize overlaps between the Utility’s and Contractor’s construction operations.  This setup allows both the utilities and the Contractor to work less encumbered, work larger areas, and be less affected by minor fluctuations in schedule and productivity.  The start and end points for each Segment vary by utility company (see Table below).  The working days provided within this section for utility relocation only account for the time necessary to complete the described utility construction and cutover work, with the assumption that the Contractor has performed, to the satisfaction of the Utility, all necessary site preparations, and is ready/able to support utility construction activities when requested.  Utility company working days shall not be assumed to be consecutive and cannot overlap with the Contractor’s or other utility’s work unless expressly stated in the utility’s respective Agreement or approved by the Engineer.  The Contractor will have the option to determine the order in which the segments are completed.

| COMPANY | Segment 1 |  | Segment 2 |  |
| --- | --- | --- | --- | --- |
|  | Start | End | Start | End |
| GCI | “KGB” Sta. 1124+42 | “KGB” Sta. 1253+98 | “KGB” Sta. 1251+83 | “KGB” Sta. 1353+95 |
| MTA | “KGB” Sta. 1124+33 | “KGB” Sta. 1238+26 | “KGB” Sta. 1225+57 | “KGB” Sta. 1351+03 |

CITY OF WASILLA (COW)

COW owns and operates water distribution and service facilities, and gravity/pressure services and conveyance lines within the project area.  The Contractor is tasked with the adjustment, relocation, and abandonment work required for the project.  COW will coordinate with the Engineer and Contractor as required by Sections 202, 604, 626, and 627.

ENSTAR NATURAL GAS COMPANY (ENSTAR)

ENSTAR owns and operates natural gas transmission, distribution, and service facilities within the project area.  ENSTAR will complete the following work to resolve conflicts between the Department’s project and its existing facilities:

The Contractor shall coordinate with ENSTAR and slopestake/pothole the following locations/facilities:

- “CARY” Sta. 1521+58.0 18.0’ LT, where the existing 2-inch HDPE distribution main paralleling the left side of S. Caryshea Street intersects with the proposed ditch cut.

- “CARY” Sta. 1500+73.0 17.1’ LT, where the existing 2-inch HDPE distribution main paralleling the left side of S. Caryshea Street intersects with the proposed approach culvert P3-1.

- “CARY” Sta. 1500+00.0 18.0’ LT, where the existing 2-inch HDPE distribution main paralleling the left side of S. Caryshea Street intersects with the proposed ditch bottom.

- “OLDK” Sta. 2101+81.4 21.0’ RT, where the existing 4-inch HDPE distribution main paralleling the right side of S. Old Knik Road intersects with the proposed ditch bottom.

- “KGB” Sta. 1173+86.5 62.5’ RT, where the existing 4-inch HDPE distribution main paralleling the right side of S. Old Knik Road intersects with the proposed ditch bottom.

- “MACK” Sta. 3084+95 28.2’ RT, where the existing 2-inch HDPE distribution main paralleling the right side of S. Mack Drive crosses into the proposed cut limits.

- “HERI” Sta. 3123+80.0 21.8’ LT, where the existing 2-inch HDPE distribution main paralleling the left side of S. Heritage Farm Road crosses into the proposed cut limits.

The existing HDPE service line feeding into Parcel 70 is in conflict with the ditch cuts associated with the Caryshea Connector between stations “CARY” Sta. 1520+33.8 25.6’ RT and 1520+67.7 26.2’ RT and will be abandoned.  ENSTAR will remove the existing meter located near the structure foundation on Parcel 70 and cut/cap the existing service line where it connects with the 1-inch HDPE distribution main crossing S. Caryshea Street at “CARY” Sta. 1522+61.6.
The Contractor shall allow ENSTAR one (1) working day to complete the required abandonment work.

The 2-inch HDPE distribution main paralleling the left side of S. Caryshea Street between “CARY” Sta. 1511+22.8 16.0’ LT and 1512+20.2 18.3’ LT, and the associated service line crossing the road at “CARY” Sta. 1511+72.5, are in conflict with the proposed ditch cuts on either side of the roadway and will be relocated/adjusted.  ENSTAR will install a new distribution main out to/along the edge of the Right of Way from “CARY” Sta. 1511+22.8 16.0’ LT to 1520+05.8 93.2’ LT, connecting/looping the distribution system along S. Caryshea Street.  The impacted service line will be vertically adjusted under the roadway and associated ditches to maintain four (4) feet of cover from finish grade and extended out to feed from the new distribution main.
The Contractor shall allow ENSTAR four (4) working days to complete the required relocation and adjustment work.

The existing locate box/test station at “KGB” Sta. 1177+31.0 100.4’ LT is in conflict with the proposed pathway fill limits and will be removed.  ENSTAR will remove all surface mounted components of its system at this location.  The existing transmission line valve at this same location is not currently operated or maintained, and will be left in place.
The Contractor shall allow ENSTAR one (1) working day to complete the required relocation and adjustment work.

The existing 4-inch HDPE and 2-inch HDPE mains installed across and around the S. Knik-Goose Bay Road/S. Heritage Farm Road and S. Heritage Farm Road/W. Stonebluff Drive intersections are in conflict with the proposed ditch cuts, guardrail installation, and culvert pipes P15-5 and P15-6 and require relocation.  ENSTAR will install a new 4-inch HDPE distribution main from “KGB” Sta. 1186+16.4 50.8’ RT to “STBL” Sta. 3140+67.1 22.0’ RT, across W. Stonebluff Drive, and a new 2-inch HDPE distribution main from “KGB” Sta. 1185+84.4 124.1’ RT to “KGB” Sta. 1184+29.3 82.1’ RT, across S. Heritage Farm Road.  This work includes adjustment of the existing 4-inch distribution main under the proposed ditch along the right side of W. Stonebluff Drive between “STBL” Sta. 3140+42.0 48.5’ RT and 3140+65.6 22.2’ RT.  The proposed crossings of W. Stonebluff Drive and S. Heritage Farm Road are proposed to be open cut (see Section 643-3.08).
The Contractor shall allow ENSTAR four (4) working days to complete the required relocation and adjustment work.

The existing 4-inch HDPE main crossing S. Knik-Goose Bay Road at “KGB” Sta. 1208+45.0 is in conflict with the proposed ditch cuts and installation of culvert P8-1 and requires relocation.  ENSTAR will replace the existing 2-inch HDPE main between “KGB” 1207+48.6 104.5’ LT and 1208+60.0 99.7’ LT with 4-inch HDPE, and install a new 4-inch HDPE line from “KGB” Sta. 1207+61.5 104.3’ LT to 1208+15.7 118.1’ RT.  This work includes a new bore across S. Knik-Goose Bay Road and an open cut crossing of S. Donna’s Way.
The Contractor shall allow ENSTAR six (6) working days to complete the required relocation and adjustment work.

The existing 2-inch HDPE main paralleling W. Stonebluff Drive between “STBL” Sta. 3280+15.2 19.5’ RT and 3281+20.8 21.8’ RT, and the associated HDPE service line to Parcel 114, are in conflict with the proposed ditch cuts and require adjustment.  ENSTAR will expose and vertically adjust these facilities to maintain a minimum of 4-feet of cover from finish grade.  This work includes an open cut of the existing driveway at “STBL” Sta. 3280+74.0 RT.
The Contractor shall allow ENSTAR one (1) working day to complete the required relocation and adjustment work.

The existing 1-inch HDPE service line crossing S. Knik-Goose Bay Road at “KGB” Sta. 1216+71.3 is in conflict with the proposed sub-excavation work and requires relocation.  ENSTAR will install a new 1-inch HDPE line from “KGB” Sta. 1216+79.1 107.1’ LT to 1216+79.1 83.0’ RT.  The proposed crossing of S. Knik-Goose Bay Road will be bored.
The Contractor shall allow ENSTAR four (4) working days to complete the required relocation and adjustment work.

The existing 4-inch HDPE, and subsequent 2-inch HDPE, mains installed across and along S. Lakewood Drive between “LAKE” Sta. 3310+48.4 23.4’ LT and 3311+85.5 32.5’ RT are in conflict with the proposed ditch cuts/special ditches and mailbox cluster installation and will be relocated and adjusted.  ENSTAR will expose and vertically adjust the existing 4-inch HDPE distribution main crossing S. Lakewood Drive to maintain a minimum of four (4) feet of cover under the proposed special ditches and install a new main using a combination of 4-inch and 2-inch HDPE pipe, out to/along the back of the existing utility easement on the left side of S. Lakewood Drive.  The existing service facilities within the relocation area shall be captured and transferred to feed from the new main.
The Contractor shall allow ENSTAR four (4) working days to complete the required relocation and adjustment work.

The existing natural gas valvebox at “KGB” Sta. 1252+74.8 85.8’ LT is in conflict with the proposed final grade of the pathway and requires adjustment.  ENSTAR will extend the valvebox up to match the proposed finish grade.
The Contractor shall allow ENSTAR one (1) working day to complete the required relocation and adjustment work.

The existing 4-inch HDPE distribution main installed across S. Knik-Goose Bay Road (“KGB” Sta. 1253+66.1) and along the left side of W. Edlund Road, as well as the 2-inch main installed along the right side of S. Knik-Goose Bay Road between “KGB” Sta. 1252+31.0 80.0’ RT and 1262+26.6 83.7’ RT, are in conflict with the proposed ditch cuts, grade modifications, and the construction of Basin-3, and will be relocated.  ENSTAR will install a new 4-inch HDPE main between “KGB” Sta. 1255+71.7 108.5’ LT and 1253+23.0 195.5’ RT, and install a new 2-inch HDPE main between “KGB” Sta. 1255+68.7 186.2’ RT and 1262+26.6 83.7’ RT.  The existing 5/8-inch HDPE service line feeding into Parcel 120 will be refed from the new 4-inch main on the left side of W. Edlund Road.  The proposed crossings of S. Knik-Goose Bay Road and W. Edlund Road will be bored.  Existing services within the relocation area will be captured and transferred to feed from the new main.
The Contractor shall set the portion of Parcel 128 not encumbered by existing utilities to rough finished grade as soon as practicable.  The Contractor agrees that it will have no claim for damages or delay arising out of or connected to a failure to complete the required excavation work ahead of the utility’s relocation work.  The Contractor shall allow ENSTAR twelve (12) working days to complete the required relocation and adjustment work.

The existing 2-inch main crossing S. Knik-Goose Bay Road at “KGB” Sta. 1258+14.3 is redundant and no longer required.  ENSTAR will retire and abandoned this facility.
The Contractor shall allow ENSTAR two (2) working days to complete the abandonment of this facility.

The existing 2-inch HDPE distribution main installed along the left side of W. Minnetonka Drive, and its connection to the 4-inch HDPE distribution main installed within the S. Knik-Goose Bay Road right of way, are located within/under the structural section of W. Minnetonka Drive and require relocation.  ENSTAR will install a new 2-inch HDPE main between “KGB” 1258+34.4 174.4’ LT and 1258+34.2 108.9’ RT, maximizing the facility’s separation from W. Minnetonka Drive.
The Contractor shall allow ENSTAR two (2) working days to complete the required relocation and adjustment work.

The existing 2-inch HDPE distribution main installed along the right side of S. Knik-Goose Bay Road between “KGB” Sta. 1269+15.8 86.3’ RT and 1269+22.8 86.0’ RT is in conflict with the proposed cuts associated with Basin-4 and will be removed.  ENSTAR will cut and cap the existing main +5-feet outside of the proposed cut limits and remove the retired section of pipe.
The Contractor shall allow ENSTAR two (2) working days to complete the required relocation and adjustment work.

The existing 4-inch HDPE distribution and 4-inch Steel transmission mains paralleling the left side of S. Knik-Goose Bay Road between “KGB” Sta. 1270+18.9 LT and 1271+93.4 LT are in conflict with the proposed grade changes and ditch cuts associated with the realignment of S. Endeavor Street and require adjustment.  ENSTAR will depressurize the existing steel transmission line, and then trench along/expose both the distribution and transmission facilities.  The existing distribution line will be vertically adjusted within the trench; the existing transmission line will be removed and a new transmission line, accommodating the proposed project improvements, constructed in the same alignment.  Each line will maintain a minimum of 4-feet of cover from finish grade.
The Contractor shall allow ENSTAR five (5) working days to complete the required relocation and adjustment work.

The existing 4-inch HDPE distribution and 4-inch Steel transmission mains paralleling the left side of S. Knik-Goose Bay Road between “KGB” Sta. 1275+87.5 LT and 1282+92.3 LT are in conflict with the proposed grade changes and cut limits associated with the pathway and require adjustment.  ENSTAR will depressurize the existing steel transmission line, and then trench along/expose both the distribution and transmission facilities.  The existing distribution line will be vertically adjusted within the trench; the existing transmission line will be removed and a new transmission line, accommodating the proposed project improvements, constructed in the same alignment.  Each line will maintain a minimum of 4-feet of cover from finish grade.
The Contractor shall allow ENSTAR eight (8) working days to complete the required relocation and adjustment work.

The existing 1-inch HDPE distribution main crossing S. Knik-Goose Bay Road at “KGB” Sta. 1298+71.6 and the subsequent 5/8-inch service line are in conflict with the proposed ditch cut along the right side of road and will be abandoned.  ENSTAR will cut, cap, and abandon the existing crossing at the main on project left.
The Contractor shall allow ENSTAR two (2) working days to complete the required relocation and adjustment work.

The existing 2-inch HDPE distribution main paralleling the right side of S. Knik-Goose Bay Road and S. Eagle Eye Circle between “KGB” Sta. 1301+17.6 138.5’ RT and 1310+80.8 85.6’ RT is in conflict with the proposed grade changes and ditch cuts and requires relocation.  ENSTAR will install a new 2-inch HDPE main along the edge of the new right of way, and through an existing utility easement.  The proposed crossing of S. Eagle Eye Circle will be open cut.  Existing services within the relocation area will be captured and transferred to feed from the new main.
The Contractor shall allow ENSTAR ten (10) working days to complete the required relocation and adjustment work.

The existing 4-inch HDPE distribution and 4-inch Steel transmission mains paralleling the left side of S. Knik-Goose Bay Road between “KGB” Sta. 1307+95.2 LT and 1310+80.3 LT are in conflict with the proposed ditch cuts and require relocation.  ENSTAR will install a new 4-inch HDPE distribution and a new 4-inch steel transmission line out to/along the right of way.  Once cutover, the existing facilities will be retired and abandoned in place.
The Contractor shall allow ENSTAR eight (8) working days to complete the required relocation and adjustment work.

The existing HDPE service lines entering into Parcel 145A are in conflict with the proposed demolition of the existing structures on the parcel and will be abandoned.  Once the structures have been vacated ENSTAR will cut and cap the existing services at the main.
The Contractor shall coordinate with ENSTAR through the Engineer to schedule abandonment of the service facilities, and allow ENSTAR three (3) working days to complete required work.

The existing 4-inch HDPE distribution and 4-inch Steel transmission mains paralleling the left side of S. Knik-Goose Bay Road between “KGB” Sta. 1316+01.4 LT and 1326+28.8 LT are in conflict with the proposed ditch cuts and require relocation.  ENSTAR will install a new 4-inch HDPE distribution and a new 4-inch Steel transmission line out to/along the new right of way between “KGB” Sta. 1315+27.9 LT to 1326+37.7 LT.  This work includes an open cut crossing of E. Harmonious Drive.  Once cutover, the existing facilities will be retired and abandoned in place.
The Contractor shall allow ENSTAR fourteen (14) working days to complete the required relocation and adjustment work.

The existing 2-inch HDPE distribution main installed across S. Knik-Goose Bay Road (“KGB” Sta. 1326+23.4) and down the left side of S. Fern Street is in conflict with proposed signals at the S. Knik-Goose Bay Road/S. Fern Street intersection, pipe P66-1, and is within/under the structural section of S. Fern Street and requires relocation.  ENSTAR will install a new 2-inch HDPE distribution main through a combination of new/existing right of way and utility easements from “FERN” Sta. 3690+94.5 62.0’ RT to 3692+69.7 46’ LT, and from “FERN” 3692+23.0 46.0’ LT to 3694+99.6 16.8’ LT.  This work includes a new 2-inch HDPE crossing of S. Knik-Goose Bay Road at “KGB” Sta. 1311+50 and relocation of ~84-feet of the existing 2-inch HDPE main installed along E. Hard Rock Circle out to the edge of the road/right of way easement.  The proposed crossings of S. Knik-Goose Bay Road and S. Fern Street will be bored, the crossing of E. Hard Rock Circle will be open cut.
The Contractor shall allow ENSTAR twelve (12) working days to complete the required relocation and adjustment work.

The existing 4-inch HDPE distribution and 4-inch Steel transmission mains paralleling the left side of S. Knik-Goose Bay Road between “KGB” Sta. 1326+41.1 LT and 1329+83.5 LT are in conflict with the cut limits associated with the proposed pathway and require adjustment.  ENSTAR will depressurize the existing steel transmission line, and then trench along/expose both the distribution and transmission facilities.  The existing distribution line will be vertically adjusted within the trench; the existing transmission line will be removed and a new transmission line, accommodating the proposed project improvements, constructed in the same alignment.  Each line will maintain a minimum of 4-feet of cover from finish grade.
The Contractor shall allow ENSTAR five (5) working days to complete the required relocation and adjustment work.

The existing 4-inch HDPE distribution main paralleling the left side of S. Knik-Goose Bay Road between “KGB” Sta. 1332+29.7 97.6’ LT and 1350+16.3 172.3’ LT, and the associated branch mains and services, are in conflict with the proposed grade changes, ditch cuts, and proposed sound barrier installation and require a combination of relocation and adjustment.  ENSTAR will:

- Install a new 4-inch HDPE main between “KGB” Sta. 1350+16.3 172.3’ LT and 1333+03.1 96.0’ LT.  The existing services within the relocation area which feed the properties on the left side of S. Knik-Goose Bay Road will be captured and transferred to feed from the new main.  This work includes open cut crossings of E. Riley Avenue and Frank Smith Way.

- Install a new 2-inch HDPE main across S. Knik-Goose Bay Road (“KGB” Sta. 1345+07.8) and a new 1-inch HDPE service to the structure on Parcel 162.  This work includes a new bore across S. Knik-Goose Bay Road.

- Install a new 1-inch HDPE main across S. Knik-Goose Bay Road (“KGB” Sta. 1338+39.5) and a new 7/8-inch HDPE service to the structure on Parcel 159.  This work includes a new bore across S. Knik-Goose Bay Road.

- Intercept and transfer the existing 2-inch HDPE main paralleling the left side of E. Frank Smith Way to feed from the new main, and vertically adjust the segment located within the proposed ditch cut along the right side E. Frank Smith Way to maintain a minimum of 4-feet of cover from finish grade.

- Expose and vertically adjust the existing 4-inch HDPE main paralleling S. Knik-Goose Bay Road between “KGB” Sta. 1332+29.7 97.6’ LT and 1333+03.1 96.0’ LT to maintain a minimum of 4-feet of cover from finish grade between.

The Contractor shall allow ENSTAR eighteen (18) working days to complete the required relocation and adjustment work.

The existing 8-inch HDPE distribution main located in the northwest quadrant of the S. Knik-Goose Bay Road/E. Palmer-Wasilla Highway intersection is in conflict with the proposed ditch cuts and requires adjustment.  ENSTAR will expose and vertically adjust the facility to maintain a minimum of 4-feet of cover from finish grade.
The Contractor shall allow ENSTAR two (2) working days to complete the required relocation and adjustment work.

The existing 6-inch HDPE distribution main crossing S. Knik-Goose Bay Road at “KGB” Sta. 1351+80.8 is in conflict with the proposed ditch cut on project right and requires adjustment.  ENSTAR will expose and vertically adjust the facility to maintain a minimum of 4-feet of cover from finish grade.
The Contractor shall allow ENSTAR one (1) working day to complete the required relocation and adjustment work.

The existing 2-inch HDPE distribution main paralleling the right side of S. Clapp Street between “PIPE” Sta. 2062+24.5 37.8’ RT and 2062+89.5 36.2’ RT is in conflict with the proposed cut limits and requires adjustment.  ENSTAR will expose and vertically this facilities to maintain a minimum of 4-feet of cover from finish grade.
The Contractor shall allow ENSTAR two (2) working days to complete the required adjustment work.

The existing 2-inch HDPE distribution main paralleling the left side of S. Weeping Birch Street between “WEEP” Sta. 3560+48.3 46.1’ RT and 3563+49.0 46.4’ RT, and the associated 7/8-inch HDPE service line crossing the roadway at approximately “WEEP” Sta. 3561+57, are in conflict with the proposed ditch cuts and require relocation.  ENSTAR will install a new 2-inch HDPE main across W. Moose Park Drive and along the back of the existing utility easement to W. Edlund Road.  A new 7/8-inch HDPE service line will be bored across the roadway at “WEEP” Sta. 3561+41.4.  The proposed crossing of W. Moose Park Drive will be open cut.
The Contractor shall allow ENSTAR five (5) working days to complete the required relocation and adjustment work.

The existing 2-inch HDPE distribution main paralleling the right side of W. Pipestone Drive between “PIPE” Sta. 3350+48.0 24.2’ RT and 3358+32.5 20.3’ RT is in conflict with the proposed ditch cuts and requires relocation.  ENSTAR will install a new 2-inch HDPE main along the edge of the right of way between “PIPE” Sta. 3350+09.9 RT and 3358+31.1 RT, except between “PIPE” Sta. 3350+56.9 RT and 3351+79.5 RT where the alignment will transition into the proposed ditch line due to the steep slopes extending from the ditch bottom out to/beyond the acquired right of way.  Existing services within the relocation area shall be captured and transferred, or extended out to, the new main.  This work includes open cut crossings of the existing driveways at “PIPE” Sta. 3350+42.5 RT and 3353+11.4 RT, and a bore across the new driveway to Parcel 121C.
The Contractor shall allow ENSTAR five (5) working days to complete the required relocation and adjustment work.

The existing 2-inch HDPE distribution line crossing W. Pipestone Drive at “PIPE” Sta. 3358+34.1, and the associated 5/8-inch service crossing W. Harvest Loop, are in conflict with the proposed final grade and ditch cuts associated with W. Pipestone Drive and require adjustment.  ENSTAR will expose and vertically adjust these facilities to maintain a minimum of 4-feet of cover from finish grade.
The Contractor shall allow ENSTAR two (2) working days to complete the required relocation and adjustment work.

GCI COMMUNICATION CORP (GCI)

GCI owns and operates overhead and underground telecommunications facilities within the project limits.  The system consists of both coax and fiber optic cables and the associated pedestals, vaults, and poles.  GCI will complete the following work to resolve conflicts between the Department’s project and its existing facilities:

Segment One

The existing overhead/underground coax and fiber optic facilities installed along and across S. Knik-Goose Bay Road are in conflict with the final roadway grades and the associated ditch cuts/fill limits and require relocation.  GCI will coordinate with the Contractor, through the Engineer, to have the Contractor construct the proposed “Utility Trail” and provide a schedule for when utility relocation work through the area can begin.  GCI will complete the following relocation work to resolve the conflicts between the proposed improvements and the COMPANY’s existing facilities.

- GCI will install duct adjacent to the right of way between “KGB” Sta. 1126+10.0 116.4’ LT and “KGB” Sta. 1140+81.4 125.0’ LT.  This work includes installation of a new pedestals at “KGB” Sta. 1126+10.0 116.4’ LT and “KGB” Sta. 1126+10.0 116.4’ LT, and a new pedestal/fiber vault near 1140+77.4 125.0’ LT.  The cable and conduits extending up-station from the existing pedestal/fiber vault near “KGB” Sta. 1140+00.1 114.5’ LT will be exposed, captured, and rerouted to the new pedestal/fiber vault location.

The Contractor shall allow GCI five (5) working days to complete the required relocation and adjustment work.

- GCI will install a new fiber optic cable between the existing fiber optic vault at “KGB” Sta. 1124+42.1 77.6’ RT and the existing aerial splice case located on the span between Poles K39 and K40 (approx. “KGB” Sta. 1251+89.6 103.9’ RT).  The new facility will use a combination of new and existing infrastructure and vary between overhead and underground.  The duct and vault system constructed through the underground sections will be completed via joint trench/bore with other utilities performing work for the project.  The work in this segment also includes:

  - Construction of a new duct and vault system along and across S. Knik-Goose Bay Road between GCI’s proposed fiber optic vault at “KGB” Sta. 1171+98.3 106.4’ RT and the existing cell tower at “KGB” Sta. 1169+23.8 341.0’ LT.  The proposed crossings of S. Old Knik Road and S. Knik-Goose Bay Road will be bored.  Once complete, GCI will pull in and terminate a new fiber optic cable;

The Contractor shall allow GCI ten (10) working days to complete the above described scope of work.  The proposed fiber work will be cutover concurrently with the primary fiber optic facility being relocated along S. Knik-Goose Bay Road.

  - Installation of a new fiber optic cable in duct between the proposed fiber vault at “KGB” Sta. 1171+98.3 106.4’ RT and the new node at “KGB” Sta. 1172+04.5 106.4’ RT.  Additional duct will be installed between the same fiber vault and the proposed utility pole at “KGB” Sta. 1172+17.6 127.3’ LT;

The Contractor shall allow GCI five (5) working days to complete the above described scope of work.  The proposed fiber work will be cutover concurrently with the primary fiber optic facility being relocated along S. Knik-Goose Bay Road.

  - Construction of a new duct and vault system along the left side of S. Volt Road.  The existing facilities will be exposed/captured, and new vaults set, where the new and existing facilities intersect.  Once complete, GCI will pull in new fiber optic cable from the proposed vault at “KGB” Sta. 1212+80.8 104.7’ RT to the existing cell tower (“KGB” Sta. 1213+80.2 347.0’ RT ) and fiber vault (“KGB” Sta. 1211+11.1 750.7’ RT).

The Contractor shall allow GCI six (6) working days to complete the above described scope of work.  The proposed fiber work will be cutover concurrently with the primary fiber optic facility being relocated along S. Knik-Goose Bay Road.

  - Installation of a new fiber optic cable from the proposed aerial splice at “KGB” Sta. 1251+89.6 103.9’ RT to the new node at “KGB” Sta. 1251+83.6 103.8’ RT.  The new facility will riser down the proposed pole at 1251+39.5 84.1’ RT and continue underground in conduit to the node through the adjacent fiber optic vault; and

The Contractor shall allow GCI three (3) working days to complete the above described scope of work.  The proposed fiber work will be cutover concurrently with the primary fiber optic facility being relocated along S. Knik-Goose Bay Road.

  - Transfer of the existing overhead fiber optic facility installed across and along W. Edlund Road onto the new MEA poles.

The Contractor shall allow GCI two (2) working days to complete the above described scope of work.

Once all the new underground duct has been installed/proofed, and MEA has completed its proposed relocation work between “KGB” Sta. 1128+33.6 RT and 1153+05.1 RT, and “KGB” Sta. 1222+54.8 RT and 1251+41.5 RT, GCI will install and cutover the proposed fiber optic cables.  Fiber cutovers will be scheduled 30 calendar days in advance of the splice work, and cannot be initiated until the replacement facility is in place and ready to be spliced.  If the fiber cutover date must be adjusted for any reason, the 30 calendar day scheduling window will reset.  Once the new facility is operational the existing overhead and non-direct buried facilities retried as a result of this work will be removed from the right of way, direct buried cable and conduits retired will be cutoff below grade and abandoned in place.

The Contractor shall allow GCI eighty-eight (88) working days to complete the required relocation work.

- GCI will relocate portions of its existing coax network to resolve conflicts between the GCI’s facilities and the proposed roadway improvements.  The following describes the required work based on the source node.

Node (“KGB” Sta. 1172+04.5 106.4’ RT)

GCI will install a new remote meter panel, power supply, and node near “KGB” Sta. 1172+04.5 106.4’ RT.  The following work is associated with this node location.

  - Once MEA has completed its relocation work associated with the pole at “KGB” Sta. 1172+38.0 108.1’ RT and installed service to GCI’s new remote meter panel, GCI will activate the new power supply/node and install a temporary coax distribution line in conduit between the new power supply and the existing node.  Once cutover the existing remote meter panel and power supply will be retired and removed.

The Contractor shall allow GCI four (4) working days to complete the above described scope.

  - GCI will transfer/attach the existing overhead coax distribution cables paralleling the left side of S. Old Knik Road to the new pole at “KGB” Sta. 1172+38.0 108.1’ RT and install a conduit and new coax distribution cables between the pole and the node.

The Contractor shall allow GCI four (4) working days to complete the above described scope.

  - GCI will install conduit and a new coax distribution cable from the node to “KGB” Sta. 1154+69.3 94.5’ RT.  From there the facility will split with one leg continuing down-station to “CARY” Sta. 1502+18.6 35.7’ LT, and the other continuing down-station through the S. Knik-Goose Bay right of way, terminating in the existing pedestal at “KGB” Sta. 1142+51.0 186.5’ RT.  The proposed road crossings of W. Fairview Loop and S. Caryshea Street will be bored.  All taps and services located within the relocation area will be captured and transferred to the new system.

The Contractor shall allow GCI sixteen (16) working days to complete the above described scope.

  - GCI will install conduit and a new coax distribution cable from the node to a new pedestal at “KGB” Sta. 1174+82.8 127.6’ RT, and then turn and continue across S. Knik-Goose Bay Road to a new pedestal at “KGB” Sta. 1174+59.0 133.1’ LT.  From there the facility will split in two.  One leg will proceed down-station to “KGB” Sta. 1172+42.1 176.5’ LT; the other leg will proceed up-station to “KGB” Sta. 1185+08.5 111.3’ LT.  At the termination of each leg the existing cables will be exposed/redirected into a new pedestal where they will be spliced with the new facilities.  The proposed crossings of S. Old Knik Road and S. Knik-Goose Bay Road shall be bored.

The Contractor shall allow GCI twenty (20) working days to complete the above described scope.

  - GCI will install duct from the proposed pedestal at “KGB” Sta. 1174+82.8 127.6’ RT to the pedestal being relocated in the southeast quadrant of the S. Knik-Goose Bay Road/S. Avalon Circle intersection (“KGB” Sta. 1181+12.9 108.8’ RT).  The proposed crossing of Basin-1 will be bored.

The Contractor shall allow GCI eight (8) working days to complete the above described scope.

The new coax facilities will be fed by the fiber optic facilities being relocated throughout Segment 1 and therefore must be cutover concurrently.  Once the cutover is complete, the overhead and non-direct buried facilities retried as a result of this work will be removed from the right of way, direct buried cable and conduits retired shall be cutoff below grade and abandoned in place.

The Contractor shall allow GCI thirty-five (35) working days to complete the required relocation work.

Node (“KGB” Sta. 1251+83.6 103.8’ RT)

GCI will install a new remote meter panel, power supply, and node near “KGB” Sta. 1251+83.6 103.8’ RT.  The following work is associated with this node location.

- GCI will install conduit and a new distribution coax cable along project right from the node location down-station to the existing pedestal at “KGB” Sta. 1208+92.9 90.0’ RT.  The proposed crossings of Basin-2 and S. Volt Place shall be completed via bore and open cut respectively.  This work also includes:

  - Transferring/securing the existing overhead distribution coax cable feeding into Parcel 118 to the proposed power pole at “KGB Sta. 1245+82.3 104.1’ RT and refeeding the line from the relocated facilities within the S. Knik-Goose Bay Road right of way; and

  - Installing conduit and a new distribution coax cable from the proposed pedestal at “KGB” Sta. 1232+14.7 118.4’ RT to a new pedestal at “LAKE” Sta. 3310+55.2 47.0’ LT.  The new facility will be bored across S. Knik-Goose Bay Road and then proceed through the existing easement located within the fenced yard.  The existing underground coax facility paralleling Lakewood Drive will be exposed, captured, and swept into the new pedestal location.

- GCI will install conduit and a new distribution coax cable from the existing pedestal at “KGB” Sta. 1203+97.4 98.2’ RT to 1206+66.9 119.0’ LT.  The proposed crossings of S. Knik-Goose Bay Road and driveway A-KGB-120616-LT will be completed via bore and open cut respectively.

- GCI will install conduit and a new underground distribution coax cable from the proposed “KGB” Sta. 1188+19.7 108.8’ RT, to the existing pedestal located in the southeast quadrant of the S. Heritage Farm Road/W. Stonebluff Drive intersection, and then continue to “KGB” Sta. 1181+12.9 108.8’ RT.  The existing facilities will be exposed, captured, and terminated in new pedestals at each end of the proposed relocation, and the pedestal enclosure and internal equipment installed in the southeast quadrant of the S. Heritage Farm Road/W. Stonebluff Drive intersection will be replaced.  The proposed crossings of S. Heritage Farm Road and W. Stonebluff Drive will be open cut.

The new coax facilities will be fed by the fiber optic facilities being relocated throughout Segment 1 and therefore must be cutover concurrently.  Once the cutover is complete, the overhead and non-direct buried facilities retried as a result of this work will be removed from the right of way, direct buried cable and conduits retired shall be cutoff below grade and abandoned in place.

The Contractor shall allow GCI forty-five (45) working days to complete the required relocation work.

The Contractor shall construct the proposed “Utility Trail” as soon as practicable to facilitate the utility relocations for the project.  The Contractor agrees that it will have no claim for damages or delay arising out of or connected to a failure to complete construction of the “Utility Trail” ahead of the utility’s relocation work.  The Contractor shall allow GCI one hundred and thirty-five (135) working days to complete the proposed relocation work for Segment 1.

Segment Two

The existing underground coax facilities and overhead/underground fiber optic facility installed along and across S. Knik-Goose Bay Road are in conflict with the final roadway grades and the associated ditch cuts/fill limits and require relocation.  GCI will coordinate with the Department’s Contractor, through the Engineer, to perform the proposed grade modifications on Parcel 126 in advance of the proposed work and complete the following relocation work to resolve the conflicts between the proposed improvements and GCI’s existing facilities.

- GCI will install a new fiber optic cable between the aerial splice cases at “KGB” Sta. 1251+89.6 103.9’ RT and “KGB” Sta. 1345+62.2 904.7’ LT.  The new facility will use a combination of new and existing infrastructure and vary between an overhead and underground configuration.  The duct and vault system constructed through the underground sections will be completed via joint trench/bore with other utilities performing work for the project.  The work in this segment includes exposing, capturing, and redirecting the existing fiber optic cable installed along the right side of S. Fern Street to feed from the new system.  Once all the underground duct has been installed/proofed, and MEA has completed its proposed relocation work between “KGB” Sta. 1253+97.4 RT and 1327+01.9 RT GCI will install and cutover the new fiber optic cables.  Fiber cutovers will be scheduled 30 calendar days in advance of the splice work, and cannot be initiated until the replacement facility is in place and ready to be spliced.  If the fiber cutover date must be adjusted for any reason, the 30 calendar day scheduling window will reset.  Once the new facility is operational the existing overhead and non-direct buried facilities retried as a result of this work shall be removed from the right of way, direct buried cable and conduits retired shall be cutoff below grade and abandoned in place.

The Contractor shall allow GCI fifty-two (52) working days to complete the required relocation work.  All new facilities must be installed and cutover before any portion of the existing system can be retired.

- GCI will install duct and a new fiber optic cable from the existing fiber vault at “KGB” Sta. 1353+94.2 94.0’ RT to the proposed node at “PWHY” Sta. 3761+68.7 107.1’ RT.  The proposed crossing of the existing detention basin and E. Palmer-Wasilla Highway shall be bored.

The Contractor shall allow GCI eight (8) working days to complete the required relocation work.  All new facilities must be installed and cutover before any portion of the existing system can be retired.

- GCI will install duct from the existing fiber vault at “PWHY” Sta. 3761+74.6 106.2’ RT, up-station along the right side of E. Palmer-Wasilla Highway, to “PWHY” Sta. 3768+38.3 RT.  The proposed crossings of the driveway at “PWHY” Sta. 3763+23.6 RT and S. Rogers Way will be open cut.

The Contractor shall allow GCI four (4) working days to complete the required relocation work.  All new facilities must be installed and cutover before any portion of the existing system can be retired.

- GCI is required to relocate portions of its existing coax network to resolve conflicts between the GCI’s facilities and the proposed roadway improvements.  As part of that relocation work, the GCI will replace the existing node at “KGB” Sta. 1326+62.4 92.0’ RT with two new nodes located at “PWHY” Sta. 3761+68.7 107.1’ RT and on the existing overhead span north of the S. Fern Street/E. Leota Street intersection.  The following narrative describes the work based on the source node.

Node (“KGB” Sta. 1251+83.6 103.8’ RT)

GCI will install a new remote meter panel, power supply, and node near “KGB” Sta. 1251+83.6 103.8’ RT.  The following work is associated with this node location.

- GCI will install conduit and a new distribution coax cables from the new node, across W. Edlund Road, to “KGB” Sta. 1255+80.2 182.3’ RT where the facility will split.  One leg will extend across and along S. Knik-Goose Bay Road to an existing pedestal at “KGB” Sta. 1257+23.6 118.0’ LT, the other will continue along the right side of S. Knik-Goose Bay Road to “KGB” Sta. 1300+13.0 86.3’ RT.  The facility will riser up onto the MEA pole line and continue overhead across S. Knik-Goose Bay Road and along the right side of the road to “KGB” Sta. 1311+78.5 RT.  This work also includes installation of a new coax service cable from the proposed pedestal at “KGB” 1258+20.1’ RT to new a new pedestal located on Parcel 128, transfer of the existing overhead coax distribution line crossing over S. Knik-Goose Bay Road at “KGB” Sta. 1276+49.2 to new MEA poles, and the installation of various pedestals/access points.  Most of the proposed installations will be completed joint with other utilities performing relocation work for the project.  The proposed crossings of W. Edlund Road, S. Knik-Goose Bay Road, S. Weeping Birch Street/Basin-4, and Basin-5 will be bored.

The new coax facilities will be fed by the fiber optic facilities being relocated throughout Segment 2 and therefore must be cutover concurrently.  Once the cutover is complete, the overhead and non-direct buried facilities retried as a result of this work will be removed from the right of way, direct buried cable and conduits retired will be cutoff below grade and abandoned in place.  MEA will remove any/all utility poles retired by this work.

The Contractor shall allow GCI fifty-five (55) working days to complete the required relocation work.

Node (“PWHY” Sta. 3761+68.7 107.1’ RT)

GCI will install a new remote meter panel, two power supplies, and node near “PWHY” Sta. 3761+68.7 107.1’ RT.  The following work is associated with this node location.

- GCI will install conduit and two new coax distribution cables from the new node location, up-station along the right side of E. Palmer-Wasilla Highway, to the existing pedestal at “PWHY” Sta. 3768+38.3 RT.  The proposed crossings of the driveway at “PWHY” Sta. 3763+23.6 RT and S. Rogers Way shall be open cut.  The Contractor shall allow GCI four (4) working days to complete the required relocation work.

- GCI will install conduit and a new coax distribution cable from the new node location, along the edge of the right of way and through the easement E-162, to a new pedestal at “KGB” Sta. 1343+59.7 RT.  The proposed crossing of driveway A-KGB-134443-RT will be open cut.

The Contractor shall allow GCI four (4) working days to complete the required relocation work.

- GCI will install conduit and new coax distribution cables across and along S. Knik-Goose Bay Road between the new node and “KGB” Sta. 1334+87.1 119.4’ LT.  This work will be completed joint with multiple other utilities performing relocation work for the project and includes the installation of four new pedestals, a new coax service to the structure on Parcel 64, and a new bore across S. Knik-Goose Bay Road.

The Contractor shall allow GCI eighteen (18) working days to complete the required relocation work.

The new coax facilities will be fed by the fiber optic facilities being relocated throughout Segment 2 and therefore must be cutover concurrently.  Once the cutover is complete, the overhead and non-direct buried facilities retried as a result of this work will be removed from the right of way, direct buried cable and conduits retired will be cutoff below grade and abandoned in place.

The Contractor shall allow GCI thirty (30) working days to complete the required relocation work.

Node (S. Fern Street and E. Leota Street)

GCI will hang a new node on the existing overhead span north of the S. Fern Street/E. Leota Street intersection and install a fiber optic cable to the existing fiber vault on the south side of E. Leota Street 130-feet east of the intersection.  The new fiber optic cable will be looped on the overhead span and then routed through an existing duct and vault system.  Once the new facilities have been cutover, and the existing overhead amplifier across from E. Snowbird Lane has been reversed, the new node will feed all the surrounding coax facilities, which includes the existing coax distribution cable installed along the right side of S. Fern Street and S. Knik-Goose Bay Road to S. Minnicks Way.  The existing pedestals at “KGB” Sta. 1317+30.2 119.9’ RT, 1319+00.3 119.4’ RT, 1321+61.4 124.9’ RT, and 1321+48.5 125.0’ RT will be replaced with new ones accommodate the proposed change to the system configuration.

The Contractor shall allow GCI six (6) working days to complete the required relocation work.

The Contractor shall set the portion of Parcel 126 not encumbered by existing utilities to rough finished grade as soon as practicable.  The Contractor agrees that it will have no claim for damages or delay arising out of or connected to a failure to complete the required excavation work ahead of the utility’s relocation work.  The Contractor shall allow GCI one hundred and ten (110) working days to complete the proposed relocation work for Segment 2.

Other

GCI will install a new coax distribution cable in duct from the existing pedestal at “PIPE” Sta. 3350+09.8 56.0’ RT to “PIPE” Sta. 3353+72.9 44.0’ RT.  This work includes the installation of two new pedestals and will be performed joint with ENSTAR and MTA.

The Contractor shall allow GCI five (5) working days to complete the required relocation work.

The existing pedestal at “PIPE” Sta. 3358+30.2 26.0’ LT and the associated underground distribution coax cables are in conflict with the proposed ditch cuts on either side of W. Pipestone Drive and require relocation.  GCI will install duct and a new coax distribution cable from the existing pedestal at “PIPE” Sta. 3358+32.7 173.5’ RT to a new pedestal “PIPE” Sta. 3358+18.6 106.0’ LT.  The new facility will be installed through the utility easements running adjacent to the right of way and bored across W. Pipestone Drive.  GCI will expose, capture, and feed its existing underground distribution cable into the new pedestal location.

The Contractor shall allow GCI seven (7) working days to complete the required relocation work.

The existing underground coax distribution cable crossing S. Weeping Birch Street at “WEEP” Sta. 3560+38.5 is in conflict with the proposed ditch cuts on either side of the roadway and requires adjustment.  GCI will vertically adjust this facility to maintain a minimum of 4-feet of cover.  The excavation work will be performed by MEA.

The Contractor shall allow GCI three (3) working days to complete the required adjustment work.

The existing underground coax distribution cable paralleling the right side of S. Weeping Birch Street between “PIPE” Sta. 3561+71.3 34.8’ LT and Sta. 3563+36.3 35.2’ LT is in conflict with the proposed ditch cuts and requires adjustment.  GCI will expose and vertically adjust the facility to maintain a minimum of 4-feet of cover.

The Contractor shall allow GCI three (3) working days to complete the required adjustment work.

MATANUSKA ELECTRIC ASSOCIATION, INC (MEA)

MEA owns and operates electrical transmission, distribution, and service facilities within the project limits.  The system consists of both overhead and underground circuits.  MEA will complete the following work to resolve conflicts between the Department’s project and its existing facilities:

The Contractor shall coordinate with MEA and slopestake/pothole the following locations/facilities:

- “HERI” Sta. 3121+82.8 26.1’ LT, where the existing underground electrical distribution line in 2-inch HDPE conduit intersects the proposed ditch bottom on the left side of S. Heritage Farm Road.  If the facility will have less than 4-feet of cover from final grade, MEA will expose and adjust this facility to meet the Department’s minimum depth requirements.  The Contractor shall allow MEA three (3) working days to complete the adjustment work if required.

The pole at “PWHY” Sta. 3761+10.6 55.2’ RT and the associated guying/electrical service drops are in conflict with the proposed ditch cuts/clear zone and require relocation.  MEA will install a new overhead distribution line between the existing poles at “PWHY” Sta. 3764+65.8 56.1’ RT and 3761+44.1 107.8’ RT, which includes a new span guy crossing the E. Palmer-Wasilla Highway at “PWHY” Sta. 3764+61.7.  The line will then riser down the pole (“PWHY” Sta. 3764+65.8 56.1’ RT) and proceed underground to a new pad mount transformer at “PWHY” Sta. 3761+44.1.  The existing services extending from the pole at “PWHY” Sta. 3761+10.6 55.2’ RT will be reestablished from the new transformer location.  The existing underground distribution line feeding into Parcel 162 will be intercepted and transferred to the new transformer.  Once the new facilities have been terminated/energized the existing facilities retired as a result of this work will be abandoned/removed.

The Contractor shall allow MEA four (4) working days to complete the proposed relocation work.  The Contractor shall coordinate with MEA, through the Engineer, to schedule the retirement/reinstallation of electrical service to the Load Center G.  The Contractor shall allow MEA three (3) working days to retire the existing service, and once Load Center G has been relocated and “Green Tagged”, another three (3) working days for MEA to install the new electrical service.

The existing overhead electrical distribution line paralleling the right side of E. Palmer-Wasilla Highway is in conflict with electrolier G36 (proposed) and will be modified.  MEA will install a new pole at “PWHY” Sta. 3767+23.0 57.2’ RT, replace the pole at “PWHY” Sta. 3768+38.4 57.6’ RT with a taller pole, and transfer/secure the existing overhead conductor.  The existing primary riser attached to the pole at “PWHY” Sta. 3768+38.4 57.6’ RT will be transferred to the new pole, and the associated underground distribution line replaced.
The Contractor shall allow MEA three (3) working days to complete the proposed relocation work.

The transformers at “KGB” Sta. 1337+88.9 96.1’ LT and “KGB” Sta. 1342+76.0 100.1’ LT, and the underground distribution line crossing E. Riley Avenue at “PWHY” Sta. 3758+73.2, are in conflict with the proposed cut/fill limits and sound barrier installation and will be relocated.  MEA will install duct and a new underground distribution line from “PWHY” Sta. 3758+95.4 56.0’ LT to the existing transmission pole at “KGB” Sta. 1335+01.0 100.9’ LT.  This work includes the installation of three new junction boxes (“PWHY” Sta. 3758+95.4 56.0’ LT, “PWHY” Sta. 3758+52.7 47.7’ RT, and “KGB” Sta. 1346+57.7 112.6’ LT) and two new transformers (“KGB” Sta. 1343+72.1 115.9’ LT and 1338+04.8 110.3’ LT).  Due to the location of the existing utility facilities within the right of way and inability to reroute power to maintain the existing electrical services, the new installation will be completed multiple segments.  Each segment will need to be installed and energized prior to moving into the next section.  The proposed crossing of E. Riley Avenue will be trenched and require a road closure (See Section 643-3.08).
The Contractor shall allow MEA twenty (20) working days to complete the proposed relocation work.

The distribution pole line and associated guying/services between “KGB” Sta. 1325+46.4 RT and 1329+72.2 101.5’ LT are in conflict with the proposed improvements (signal installation, roadway grade, clear zone, slope limits, etc.) to the S. Knik-Goose Bay Road/S. Fern Street intersection and require relocation.  MEA will:

- Construct a temporary pole line, using service conductor, from the pole at “KGB” Sta. 1321+32.0 128.8’ RT to “KGB” Sta. 1323+34.7 85.6’ RT.  Temporary services will be ground laid in corrugated conduit from the last pole to the existing Department load center (“KGB” Sta. 1325+11.2 55.9’ RT) and the remote meter panel on Parcel 152 (“KGB” Sta. 1324+09.4 139.7’ RT).  Once the temporary facilities have been terminated and energized the existing pole line between “KGB” Sta. 1321+32.0 128.8’ RT and 1329+72.2 101.5’ LT, and running down S. Fern Street to “FERN” Sta. 3694+46.1 61.6’ RT, will be retired and removed.

- Construct a new distribution pole line between “KGB” Sta. 1321+32.0 128.8’ RT and 1329+72.2 101.5’ LT, and down S. Fern Street to “FERN” Sta. 3694+46.1 61.6’ RT.  This work includes re-establishing the temporary service drop to the Load Center F (existing location) from the new pole line and installing the permanent underground electrical service to the remote meter panel on Parcel 152.

- Schedule and complete the disconnect/removal of the temporary service, and installation of the permanent underground service drop to Load Center F, in coordination with the Contractor’s work to relocate the load center.

- Schedule and complete the retirement of the existing underground electrical service feeding the Department’s load center at “KGB” Sta. 1332+82.9 78.7’ LT in coordination with the Contractor’s retirement of the existing highway lighting.

The Contractor shall allow MEA ten (10) working days to complete the proposed relocation work.  The Contractor shall coordinate with MEA, through the Engineer, to schedule the retirement/reinstallation of electrical service to the Load Center F.  The Contractor shall allow MEA three (3) working days to retire the existing service, and once Load Center F has been relocated and “Green Tagged”, another three (3) working days to install the new electrical service.  The Contractor shall coordinate with MEA to schedule the retirement of the existing underground electrical service to the highway lighting load center at “KGB” Sta. 1332+82.9 78.7’ LT in conjunction with the Contractor’s retirement/removal of the existing highway lighting powered from this location.  The Contractor shall allow MEA three (3) working days to retire/abandon the service facility.

The down guy/anchor attached to the pole at KGB” Sta. 1316+03.3 100.2’ RT are in conflict with the proposed fill limits and will be relocated.  MEA will remove and reinstall the down guy/anchor outside the proposed improvements.
The Contractor shall allow MEA three (3) working days to complete the proposed relocation work.

The poles at “KGB” Sta. 1314+18.7 90.0’ RT, “KGB” Sta. 1317+22.3 108.3’ RT, and “KGB” Sta. 1319+46.8 108.2’ LT do not have sufficient height to accommodate GCI’s proposed overhead relocation work for the project.  MEA will replace these poles with taller ones to ensure all attached facilities comply with the Department’s minimum vertical clearance requirements.  Once installed, the existing overhead lines paralleling the right side the road will be transferred/secured to the new poles.
The Contractor shall allow MEA five (5) working days to complete the proposed relocation work.

The pole at “KGB” Sta. 1308+61.3 89.6’ RT is in conflict with the proposed cut limits and will be relocated.  MEA will set a new pole at “KGB” Sta. 1309+64.4 89.7’ RT, in line with the existing overhead facility and outside the proposed improvements, and install a new overhead electric service to the structure located on Parcels 145 & 146.  A lift pole will be installed outside the right of way (“KGB” Sta. 1309+06.9 135.5’ RT) to ensure the new overhead service meets the Department’s minimum vertical clearance requirement.  Once the new facilities have been terminated and energized the facilities retired by this work, which includes the existing distribution line crossing over S. Knik-Goose Bay Road and the subsequent service facilities, will be retired and removed.
The proposed relocation work cannot be completed until the structures on Parcel 145A no longer require utility service.  The Contractor shall allow MEA four (4) working days to complete the proposed relocation work.

The poles at “KGB” Sta. 1288+79.4 89.2’ RT, “KGB” Sta. 1291+79.8 84.6’ RT, “KGB” Sta. 1294+07.0 87.2’ RT, “KGB” Sta. 1297+06.7 88.5’ LT, “KGB” Sta. 1300+07.8 86.2’ RT, “KGB” Sta. 1299+86.4 112.3’ LT, “KGB” Sta. 1300+56.8 87.3’ RT, “KGB” Sta. 1302+03.2 90.5’ RT, and “KGB” Sta. 1306+31.0 89.7’ RT do not have sufficient height to accommodate GCI’s proposed overhead relocation work for the project.  MEA will replace these poles with taller ones to ensure all attached facilities comply with the Department’s minimum vertical clearance requirements.  The existing overhead distribution line crossing S. Knik-Goose Bay Road at “KGB” Sta. 1299+98.5 will be replaced, and the overhead lines paralleling the right side the road will be transferred/secured to the new poles.
The Contractor shall allow MEA five (5) working days to complete the proposed relocation work.

The poles and associated guying at “KGB” Sta. 1281+99.8 79.0’ LT, “KGB” Sta. 1282+37.1 96.8’ LT, and “KGB” Sta. 1285+66.7 96.9’ LT are in conflict with the proposed cut limits and pathway alignment and will be relocated.  MEA will reconstruct/realign the existing overhead road crossing to be perpendicular to the road alignment, setting new/taller poles near the edge of the right of way on either side of the road, and pulling in/terminating new conductor.  MEA will also set a new self-supporting pole at “KGB” Sta. 1285+66.7 96.9’ LT and then transfer/secure the existing overhead conductors paralleling the right side of the S. Knik-Goose Bay Road to the new pole. 
The Contractor shall allow MEA five (5) working days to complete the required relocation work.

The poles at “KGB” Sta. 1273+46.2 96.7’ RT, “KGB” Sta. 1276+41.3 94.9’ RT, “KGB” Sta. 1276+53.3 107.4’ LT, and “KGB” Sta. 1279+43.2 98.4’ RT do not have sufficient height to accommodate GCI’s proposed overhead relocation work for the project.  MEA will replace these poles with taller ones to ensure all attached facilities comply with the Department’s minimum vertical clearance requirements.  Once the new poles are in place, the existing overhead facilities will be transferred, and the existing poles retired and removed.
The Contractor shall allow MEA three (3) working days to complete the proposed relocation work.

The utility owned electrolier at “KGB” Sta. 1274+80.7’ LT, illuminating the approach to Iditarod Trail Headquarters, is in conflict with the proposed widening of S. Knik-Goose Bay Road and shall be removed.  MEA will retire and remove the electrolier and associated overhead service drop.
The Contractor shall allow MEA two (2) working days to complete the retirement/removal work.

The distribution pole line installed between “KGB” Sta. 1270+39.4 109.8’ RT and “ENDV” Sta. 3510+12.5 67.0’ RT, the utility owned electrolier at “KGB” Sta. 1269+60.4 56.2’ RT, and the underground distribution line paralleling the left side of the existing S. Endeavor Street alignment between “ENDV”  Sta. 3507+23.9 29.0’ RT and “ENDV” Sta. 3511+33.2 36.8’ LT are in conflict with the proposed ditch cuts and final grades associated with the realignment of S. Endeavor Street, expansion of S. Knik-Goose Bay Road, and construction of Basin-4 and will be relocated.  MEA will:

- Set two poles in line with the existing distribution overhead facilities paralleling the right side of S. Knik-Goose Bay Road at “KGB” Sta. 1270+39.4 109.8’ RT and 1271+76.8 95.1’ RT.

- Construct a new distribution pole line between the new inset pole at “KGB” Sta. 1270+39.4 109.8’ RT and the existing pole at “ENDV” Sta. 3510+12.5 67.0’ RT.

- Install a new underground distribution line in 2-inch HDPE duct from the junction box at “ENDV” Sta. 3510+03.7 68.5’ RT, along and across S. Endeavor Street, to “ENDV” Sta. 3507+23.9 29.0’ LT; where a new junction box will be installed.  The existing underground distribution line will be exposed, captured, and swept into the new junction box.

- Install a temporary overhead jumper between the new pole line and the current source pole providing power to the lights illuminating the S. Knik-Goose Bay Road/S. Endeavor Street intersection.  MEA will schedule and complete the retirement/removal of the temporary facilities in coordination with the Contractor’s removal of the highway lighting.

- Remove all non-direct buried conductor/conduit, and any overhead/surface mounted facilities, retired as result of the proposed relocation work.  Direct buried conductor/conduit shall be cutoff below grade and abandoned in place.

The Contractor shall allow MEA eight (8) working days to complete the required relocation work.  The Contractor shall coordinate with MEA through the Engineer to schedule the retirement/removal of the temporary facilities serving the existing highway lighting at the S. Knik-Goose Bay Road/S. Endeavor Street intersection, and allow MEA three (3) working days to retire/remove the temporary infrastructure.

The existing underground distribution line paralleling the left side of S. Endeavor Street between “ENDV” Sta. 3502+22.0 27.8’ LT and “ENDV” Sta. 3502+36.1 28.4’ LT is in conflict with the proposed ditch cuts associated with the new Smith Ball Field access and will be adjusted.  MEA will expose and adjust this facility to maintain 4-feet of cover from finish grade.
The Contractor shall allow MEA three (3) working days to complete the proposed adjustment work.

The poles at “KGB” Sta. 1261+21.4 90.8’ RT, “KGB” Sta. 1264+41.5 90.3’ RT, and “KGB” Sta. 1267+39.3 91.4’ RT do not have sufficient height to accommodate GCI’s proposed overhead relocation work for the project.  MEA will replace these poles with taller ones to ensure all attached facilities comply with the Department’s minimum vertical clearance requirements.  This work includes the removal and reinstallation of the existing underground electrical services to Parcel 131 (Wasilla Christian Church).  Once the new poles are in place, the existing overhead facilities will be transferred, and the existing poles retired and removed.
The Contractor shall allow MEA three (3) working days to complete the proposed relocation work.

The existing underground distribution line crossing S. Knik-Goose Bay Road at “KGB” Sta. 1257+03.4, and the overhead distribution facilities installed across Parcel 126 & 128 are in conflict with the proposed grade changes and drainage improvements and will be relocated.  MEA will install taller poles adjacent to existing structures, and then transfer/secure the existing overhead conductor to the new facilities.  The pole line installed along the left side of W. Edlund Road will be extended across S. Knik-Goose Bay Road, and then transition and proceed up underground to “KGB” Sta. 1257+45.1 119.7’ LT, where it will be connected back into the existing system via a new junction box.
The Contractor shall allow MEA seven (7) working days to complete the proposed relocation work.

The distribution pole line between “KGB” Sta. 1225+57.0 90.2’ RT and 1248+50.7 77.1’ RT, as well as the associated taps, services, and guying, are in conflict with the proposed final grade and clear zone for S. Knik-Goose Bay Road and will be relocated.  Once the Contractor has completed construction of the proposed “Utility Trail” MEA will install a new distribution pole line between “KGB” Sta. 1222+54.8 83.9’ RT and 1251+41.5 84.1’ RT.  This work will also include modification/adjustment of the existing overhead distribution line crossing S. Knik-Goose Bay Road at “KGB” Sta. 1225+56.7, and installation of a temporary overhead jumper between the new pole line and the current source pole providing power to the lights at the S. Knik-Goose Bay Road/S. Lakewood Drive intersection.  Once the new facilities have been energized, the existing pole line will be retired/removed.  The facilities providing power to the intersection lighting will be maintained in place until the Contractor is ready to remove the lights.
The Contractor shall construct the proposed “Utility Trail” as soon as practicable to facilitate the utility relocations for the project.  The Contractor agrees that it will have no claim for damages or delay arising out of or connected to a failure to complete construction of the “Utility Trail” ahead of the utility’s relocation work.  The Contractor shall allow MEA thirteen (13) working days to complete the proposed relocation work.  The Contractor shall coordinate with MEA, through the Engineer, to schedule the retirement/removal of the temporary facilities serving the lighting at the S. Knik-Goose Bay Road/S. Lakewood Drive intersection, and allow MEA three (3) working days to retire/remove the temporary infrastructure.

The down guys/anchors attached to the poles at “KGB” Sta. 1216+50.5 92.8’ RT, “KGB” Sta. 1219+48.2 82.2’ RT, and “KGB” Sta. 1222+54.8 83.9’ RT are in conflict with the proposed roadway widening and the associated clear zone/ditching and will be relocated.  MEA will install new span guys across S. Knik-Goose Bay Road at each location and then retire and remove the existing guying.
The Contractor shall allow MEA four (4) working days to complete this work.

The grounded anti-slip grating near the base of the pole at “KGB” Sta. 1212+43.6 97.3’ RT, which is required to safely operate the Ground Operated Air Break installed on the pole, is in conflict with the proposed grade modifications and will be removed and later reinstalled.
The Contractor shall coordinate with MEA through the Engineer a minimum of seven (7) working days in advance of any grading work occurring in the vicinity of the pole to schedule removal of the grate and grounding elements.  Once grading operations near the base of the pole are complete, the Contractor shall coordinate with MEA through the Engineer to schedule the reinstallation of these facilities.  The Contractor shall perform the grading work in a manner to minimize the duration between removal and replacement of the grate.  The Contractor shall allow MEA three (3) working days for removal, and three (3) working days for reinstallation of the grate.

The pole at “KGB” Sta. 1211+76.6 94.0’ RT and associated underground distribution line installed across and along Volt Road are in conflict with the proposed ditch cuts and final grade of Volt Road and will be relocated.  MEA will set a new pole at “KGB” Sta. 1211+38.0 95.6’ RT and expose/capture the existing underground distribution circuits coming from the COTTLE sub-station down Volt Road in new vaults at “VOLT” Sta. 3271+20.3 LT and 3271+37.9 LT.  Conductor in conduit will be installed from the vaults to the new pole location, and to the existing pole at (“KGB” Sta. 1212+81.2 99.8’ RT).  The proposed crossing of Volt Road will be trenched (see Section 643-3.08).
The Contractor shall allow MEA seven (7) working days to complete the described relocation work.

The pole and the associated down guy/anchor at “KGB” Sta. 1203+67.8 63.6’ RT are within the proposed ditch cut and clear zone of S. Knik-Goose Bay Road and will be relocated.  MEA will:

- Set a new pole at “KGB” Sta. 1205+33.2 96.3’ RT, in line with the existing overhead distribution facility, and construct a new distribution pole line along and across S. Knik-Goose Bay Road to the existing pole at “KGB” Sta. 1199+30.3 235.3’ LT.

- Set a new pole at “KGB” Sta. 1205+33.2 108.7’ LT and install new overhead distribution line back to the proposed pole at “KGB” Sta. 1205+33.2 96.3’ RT.  This work includes the installation of new down guys/anchors at both ends of the proposed road crossing.

- Set a new pad mount transformer at “KGB” Sta. 1205+45.3 117.7’ LT and expose, capture, and sweep the existing underground distribution and service lines running through the existing utility easement into the new cabinet.  A new service line, in conduit, will be installed from the new transformer to the pole at “KGB” Sta. 1205+33.2 108.7’ LT to maintain the existing overhead service facilities.

- Remove all non-direct buried conductor/conduit, and any overhead/surface mounted facilities, retired as result of the proposed relocation work.  Direct buried conductor/conduit shall be cutoff below grade and abandoned in place.

The Contractor shall allow MEA seven (7) working days to complete the described relocation work.

The pad mounted junction box (“HERI” Sta. 3121+80.8 14.9’ RT) and transformer (“HERI” Sta. 3121+85.9 15.0’ RT) on the right side of S. Heritage Farm Road are in conflict with the proposed fill slopes and clear zone of the realigned roadway and will be relocated.  MEA will disconnect and remove the existing junction box, transformer, and associated underground distribution/service conductors, and then set a new transformer over/capture the existing underground distribution line at “HERI” Sta. 3121+26.6 41.4’ RT.  New conduit will be plumbed from the transformer, along the edge of the right of way, to existing road crossing at “HERI” Sta. 3121+80.8, and to where the existing underground service line to MTA”s Hut exits the right of way (“HERI” Sta. 3122+42.5 31.7’ RT).  Once complete, new conductor will be pulled and terminated.  An outage impacting MTA’s MACK hut and the homes on S. Avalon Circle will be required.
The Contractor shall allow MEA four (4) working days to complete the described removal work.

The existing utility owned electrolier at “KGB” Sta. 1185+35.6 49.3’ LT is in conflict with the proposed widening of S. Knik-Goose Bay Road and shall be temporarily relocated before ultimately being removed from the project.
The Contractor shall coordinate with MEA through the Engineer to schedule relocation of the existing MEA electrolier outside the proposed improvements.  Once the permanent lighting at the intersection has been installed and activated the Contractor shall coordinate with MEA through the Engineer to schedule removal of the MEA electrolier and the associated overhead service line.  The Contractor shall allow MEA three (3) working days to relocate the electrolier, and three (3) working days to remove the electrolier and overhead service.

The pole (“KGB” Sta. 1172+38.0 108.1’ RT), pedestal (“KGB” Sta. 1172+23.3 106.9’ RT), privately owned remote meter panel (“KGB” Sta. 1171+82.2 114.6’ RT), and associated underground electrical services are in conflict with the proposed telecommunication relocation work being performed for the project and will be relocated.  MEA will install a new pole (“KGB” Sta. 1172+17.6 127.3’ RT) and pedestal (“KGB” Sta. 1172+14.6 135.7’ RT) in the existing utility easement on Parcel 94, relocate the privately owned remote meter panel back out of the right of way, and re-feed the existing load centers from the new pedestal location.  Once cutover, MEA will remove all non-direct bury conductor/conduit and any overhead/surface mounted facilities retired as result of this work.  Direct buried conductor/conduit shall be cutoff below grade and abandoned in place.
The Contractor shall allow MEA six (6) working days to complete the described relocation work.  The Contractor shall coordinate with MEA through the Engineer to schedule the retirement/removal of the service to the Department’s load center.

The underground electrical service installed between the pole at “FAIR” Sta. 2082+60.6 110.6’ LT and Load Center A (“FAIR” Sta. 2081+03.4 76.8’ LT) is in conflict with the proposed cut limits and will be relocated.  MEA will install new service drop, outside the proposed improvements and parallel to the W. Fairview Loop alignment, between the pole and load center and then retire/abandon the existing service.
The Contractor shall allow MEA three (3) working days to complete the required relocation work.

The existing electrical service drop installed between the pole at “KGB” Sta. 1154+72.3 87.0’ RT and the ATR load center (“KGB” Sta. 1154+72.1 54.7’ RT) is in conflict with the proposed ditch cuts associated with S. Knik-Goose Bay Road and will be relocated in coordination with the Contractor’s relocation of the ATR site.
The Contractor shall coordinate with MEA through the Engineer to schedule/retire the existing electrical service.  The Contractor shall allow MEA three (3) working days to complete the required retirement work.  Once Load Center H1 has been reinstalled and “Green Tagged”, the Contractor shall coordinate with MEA to schedule the installation of the new underground electrical service.  The Contractor shall allow MEA three (3) working days to install and energize the new underground electrical service.

The existing down guys/anchors attached to the pole at “KGB” Sta. 1154+72.3 87.0’ RT are in conflict with the proposed cut limits.  MEA will reset these facilities to finish grade.
The Contractor shall allow MEA three (3) working days to complete the required relocation work.

The existing distribution pole line between “KGB” Sta. 1136+05.9 84.4’ RT and 1151+36.2 83.5’ RT is in conflict with the proposed cut/fill slopes associated with the expansion of S. Knik-Goose Bay Road and will be relocated.  MEA will:

- Install temporary facilities to reroute/maintain electrical service to its customers while performing the required relocation work.  This work includes the installation of a new overhead distribution line, and guying, along the left side of S. Caryshea Street between “CARY” Sta. 1500+83.5 LT and 1504+97.9 LT, and two ground laid sections of service conductor in corrugated conduit (“KGB” Sta. 1142+52.2 200.3’ RT – 1144+31.8 221.8’ RT and “KGB” Sta. 1146+62.7 201.2’ RT – 1148+82.6 124.3’ RT).

- Construct a new pole line approximately 15-feet inside the right of way between “KGB” Sta. 1133+86.9 86.6’ RT and 1154+72.3 87.0’ RT.  This work includes the installation of four new span guys across S. Knik-Goose Bay Road, and two small sections of underground electrical work; one to reconfigure/refeed the existing underground distribution lines feeding into Parcels 79 & 81, and one to capture/transfer the existing underground electrical service feeding into Parcel 84 to the new pole.

- Terminate/energize the new system and then retire/remove the existing and temporary facilities.

The Contractor shall allow MEA fifteen (15) working days to complete the required relocation work.

The poles at “KGB” Sta. 1133+86.9 86.6’ RT, “KGB” Sta. 1130+92.7 89.5’ RT, and “KGB” Sta. 1128+33.6 120.8’ RT do not have sufficient height to accommodate GCI’s proposed overhead relocation work for the project.  MEA will replace these poles with taller ones to ensure all the attached facilities comply with the Department’s minimum vertical clearance requirement.  Once the new poles are in place, the existing overhead facilities will be transferred and the existing poles retired and removed from the right of way.

The Contractor shall allow MEA four (4) working days to complete the proposed relocation work.

The underground distribution line paralleling the left side of W. Pipestone Drive and associated riser pole at “PIPE” Sta. 3358+30.6 41.0’ LT, as well as the underground distribution line crossing W. Pipestone Drive at “PIPE” Sta. 3352+88.1, are in conflict with the proposed roadway finish grade and cut limits and will be relocated.  MEA will:

- Install a new underground distribution line in duct from the existing junction box located in the northeast quadrant of the W. Kanabec Drive/W. Pipestone Drive intersection, along the right of way on the left side of the road, to “PIPE” Sta. 3358+30.6 41.0’ LT where a new riser pole will be set.  This work includes the installation of a new junction box at “PIPE” Sta. 3352+776 41.0’ LT.  The proposed crossing of W. Kanabec Drive will be open cut.

- Install a temporary service to the structure on Parcel 121C to retire the existing distribution line crossing and facilitate the proposed grade work required along W. Pipestone Drive.  Two new poles will be set, outside the right of way, on either side of the roadway near “PIPE” Sta. 3353+00, and a new pad mount transformer set next to the proposed junction box at “PIPE” Sta. 3352+776 41.0’ LT.  A new distribution line will be installed between the junction box and transformer, and a new service line installed overhead across the road, and then across the ground outside the right of way on the right side of the road to “PIPE” Sta. 3353+78.5 58.9’ RT.  The permanent service to Parcel 121C will be installed along and across the proposed driveway alignment to the existing meter panel attached to the structure.  The temporary and permanent service lines will be spliced together and encased in a new pad mount transformer to be set at “PIPE” Sta. 3353+78.5 58.9’ RT.

- Schedule/complete installation of the permanent distribution line between the new junction box (“PIPE” Sta. 3352+776 41.0’ LT) and pad mount transformer (“PIPE” Sta. 3353+78.5 58.9’ RT) once the Contractor has established rough finish grade for W. Pipestone Drive and the associated ditches.  Once terminated and energized the non-direct buried conductor/conduit and overhead/surface mounted facilities associated with the temporary service will be retired and removed.  Direct buried conductor/conduit will be cutoff below grade and abandoned in place.  The proposed crossing of W. Pipestone Drive will be open cut.

- Shift Pole K47-14N (existing) to maintain tangency of the overhead pole line.

The Contractor shall allow MEA twelve (12) working days to relocate the existing distribution facilities within the W. Pipestone Drive corridor and install the temporary service to Parcel 121C.  The Contractor shall establish rough finish grade for W. Pipestone Drive and the associated ditches and then coordinate through the Engineer to schedule MEA to return and install the permanent electrical service to Parcel 121C.  The Contractor shall allow MEA four (4) working days to install/energize the new underground electrical service and retire and remove the temporary service.

The underground distribution line in 2-inch conduit crossing S. Weeping Birch Street at “WEEP” Sta. 3355+47.7 is in conflict with the proposed ditch cut on the left side of the road and will be adjusted.  MEA will expose and vertically adjust the facility to maintain 4-feet of cover from finished grade.

The Contractor shall allow MEA three (3) working days to complete the required adjustment work.

The underground distribution line in 2-inch conduit crossing S. Weeping Birch Street at “WEEP” Sta. 3560+41.3 is in conflict with the proposed ditch cuts on either side of the road and will be adjusted.  MEA will expose and vertically adjust this facility to maintain 4-feet of cover from finished grade.  This work will require a full open cut of the existing roadway and be performed joint with GCI and MTA (see Section 643-3.08).
The Contractor shall allow MEA three (3) working days to complete the required adjustment work.

Line Extensions

Prior to MEA establishing service to a load center, the Contractor shall have it inspected, and green tagged for compliance.  Once tagged, the Contractor shall notify the Engineer who will contact the utility.  MEA will schedule and complete the line extension work based on its current workload.  The following facilities will be installed to provide electrical service to the proposed load center locations:

Load Center B (“KGB” Sta. 1184+90.7 92.8’ RT)

MEA will provide a meter and install a new underground electrical service drop in 2-inch conduit from the pad mounted transformer (proposed) at “KGB” Sta. 1184+81.4 116.6’ RT to Load Center B.

Note:  The pad mount transformer that will provide electrical service to Load Center B is scheduled to be installed as part of MEA’s proposed relocation work for the project.  The new transformer must be installed and energized prior to the line extension work.

The Contractor shall allow one (1) working day to complete this work.

Load Center C (“KGB” Sta. 1212+81.6 84.2’ RT)

MEA will provide a meter and install a new underground electrical service drop in 2-inch conduit between the existing pole/overhead transformer at “KGB” Sta. 1214+59.3 93.3’ RT and Load Center C.  The Contractor shall allow one (1) working day to complete this work.

Load Center D (“KGB” Sta. 1271+59.5 89.8’ RT)

MEA will provide a meter and install a new overhead transformer and underground electrical service drop in 2-inch conduit between the utility pole (proposed) at “KGB” Sta. 1271+76.8 95.1’ RT and Load Center D.

Note:  The utility pole that will be used to establish the new electrical service to Load Center D is scheduled to be installed as part of MEA’s proposed relocation work for the project.  The new utility pole must be installed prior to the line extension work.

The Contractor shall allow one (1) working day to complete this work.

Load Center E (“KGB” Sta. 1297+73.2 85.0’ RT)

MEA will provide a meter and install a new overhead transformer and underground electrical service drop in 2-inch conduit between the utility pole (proposed) at “KGB” Sta. 1297+11.7 88.5’ RT and Load Center E.

Note:  The utility pole that will be used to establish the new electrical service to Load Center E is scheduled to be installed as part of MEA’s proposed relocation work for the project.  The new utility pole must be installed prior to the line extension work.

The Contractor shall allow one (1) working day to complete this work.

Load Center H3 (“KGB” Sta. 1290+93.8 79.0’ RT)

MEA will provide a meter and install a new overhead transformer and underground electrical service drop in 2-inch conduit between the utility pole at “KGB” Sta. 1291+79.8 84.6’ RT and Load Center H3.  The Contractor shall allow one (1) working day to complete this work.

MATANUSKA TELECOM ASSOCIATION, INC (MTA)

MTA owns and operates overhead/underground telecommunication distribution, and service facilities throughout the project area.  The system consists of both copper and fiber optic cables and the associated huts, pedestals, handholes, and poles.  MTA will complete the following work to resolve conflicts between the Department’s project and its existing facilities.

Segment One

The existing underground copper and fiber optic facilities installed along and across S. Knik-Goose Bay Road are in conflict with the final roadway grades and the associated ditch cuts/fill limits and require relocation.  MTA will complete the following relocation work to resolve the conflicts between the proposed improvements and the MTA’s existing facilities.

MTA will construct a new fiber optic duct and vault system and place copper cables in a common alignment along the right side of S. Knik-Goose Bay Road from the existing pedestal and fiber optic vault located on the south side of S. Donovan Drive to the proposed fiber optic vault at “KGB” Sta. 1238+26.1 RT.  The new facilities will be installed through the existing telecommunications hut (MACK Hut) located on S. Heritage Farm Road, and will extend out along S. Caryshea Street, the section line easement paralleling the eastern boundary of S24, T17N, R2W (the old S. Clapp Street alignment), and S. Mack Drive to tie back into MTA’s existing system.  The existing service drops impacted by the proposed relocation work will be rerun or captured/transferred to the new facilities.  The proposed crossings of S. Avalon Circle, S. Heritage Farm Road, W. Stonebluff Drive, S. Donna’s Way, and the existing residential/commercial driveways will be open cut; all other basin and roadway crossings will be bored.

Once the new facilities have been installed, MTA will proof duct and pull in the various fiber optic cables proposed between S. Donovan and the new vault at “KGB” Sta. 1238+26.1 151.7’ RT and complete the necessary cutovers.  Fiber cutovers will be scheduled 30 calendar days in advance of the splice work and cannot be initiated until the replacement facility is in place and ready to be spliced.  If the fiber cutover date must be adjusted for any reason, the 30 calendar day scheduling window will reset.  Existing overhead and non-direct buried facilities retried as a result of this work will be removed from the right of way, direct buried cable and conduits retired will be cutoff below grade and abandoned in place.  MTA will coordinate with MEA as required to remove any/all utility poles retired by this work.

The Contractor shall construct the proposed “Utility Trail” (A-KGB-122736-UTILITY), remove the earthen mounds on Parcel 70, and provide a schedule for when utility relocation work through those areas can begin.  Once complete, allow MTA one hundred and ten (110) working days to complete the required relocation work.

The existing pedestal at “KGB” Sta. 1174+32.9 99.8’ LT, and the associated underground copper distribution cable, are in conflict with the proposed fill limits and will be adjusted.  MTA will expose and shift the pedestal back out of the proposed improvements.

The Contractor shall allow MTA three (3) working days to complete the proposed scope of work.

The existing underground copper service cable extending from the pedestal at “VOLT” Sta. 3280+48.6 33.8’ RT, across S. Volt Place, to MEA’s COTTLE substation is in conflict with the proposed ditch cuts/drainage improvements associated with S. Volt Place and requires relocation.  MTA will install a new underground service cable accommodating the proposed improvements.

The Contractor shall allow MTA three (3) working days to complete the proposed scope of work.

Segment Two

The existing underground/overhead copper and fiber optic facilities installed along and across S. Knik-Goose Bay Road are in conflict with the final roadway grades and the associated ditch cuts/fill limits and require relocation.  MTA will complete the following relocation work to resolve the conflicts between the proposed improvements and MTA’s existing facilities.

MTA will continue construction of the fiber optic duct and vault system and installation of direct bury copper cables along the right side of S. Knik-Goose Bay Road from the proposed fiber optic vault at “KGB” Sta. 1238+26.1 RT to the south side of S. Minnicks Way (“KGB” Sta. 1314+28.4), and from the existing fiber vault at “KGB” Sta. 1325+52.0 RT to the existing pedestal and fiber vault near “KGB” Sta. 1336+40.0.  MTA will use the existing duct installed between the two previously described sections of work to facilitate the proposed fiber optic cable installation for this segment.  MTA will continue installing copper facilities and spare duct from the existing pedestal at “KGB” 1336+32.0 110.4’ RT across and along S. Knik-Goose Bay Road to the north side of E. Riley Avenue (“KGB” Sta. 1351+02.4).  This work includes the installation of new facilities along S. Lakewood Drive, S. Endeavor Street, and E. Riley Avenue, and across S. Knik-Goose Bay Road at “KGB” Sta. 1276+49.2, 1282+91.4, 1300+02.3, and 1349+37.5 to tie back into the MTA’s existing system and reestablish service from the new facilities.  The proposed crossings of S. Avalon Circle, S. Heritage Farm Road, W. Stonebluff Drive, S. Donna’s Way, and the existing residential/commercial driveways will be open cut; crossings of all other basins and roadways will be bored.

Once the new facilities are in place, MTA will proof duct and pull in the proposed fiber optic cables between the proposed fiber vault at “KGB” Sta. 1238+26.1 151.7’ RT and the existing fiber vault at “KGB” Sta. 1336+48.0 123.9’ RT, and from the new DLC cabinet located on the south side of E. Riley Avenue 210-feet west of Century Circle, to the existing fiber vault located within the section line easement paralleling the western boundary of S10, T17N, R1W (“KGB” Sta. 1357+77.4 1,357.0’ LT).  Fiber cutovers will be scheduled 30 calendar days in advance of the splice work and cannot be initiated until the replacement facility is in place and ready to be spliced.  If the fiber cutover date must be adjusted for any reason, the 30 calendar day scheduling window will reset.  Existing overhead and non-direct buried facilities retried as a result of this work will be removed from the right of way, direct buried cable and conduits retired will be cutoff below grade and abandoned in place.  MTA will coordinate with MEA as required to remove any/all utility poles retired by this work.

The Contractor shall construct driveway A-EDLN-341461-RT, complete the grade modifications on Parcel 126, and provide a schedule for when utility relocation work through those areas can begin.  The Contractor shall allow MTA one hundred and forty (140) working days to complete the required relocation work.

Other

The existing underground copper service line installed between the pedestal at “PIPE” Sta. 3350+65.4 40.0’ RT and the structure located on Parcel 121C is in conflict with the proposed ditch cuts associated with the new W. Pipestone Drive profile and requires relocation.  MTA will install a new copper distribution line and duct from the existing source pedestal to a new pedestal at “PIPE” Sta. 3352+86.2 44.0’ RT.  A new copper service line will be installed between the new pedestal and where the existing service enters into Parcel 121C.

The Contractor shall allow MTA four (4) working days to complete the above-described scope of work.

The existing underground copper distribution cable paralleling the north side of W. Harvest Loop is in conflict with the proposed ditch cuts associated W. Pipestone Drive and requires relocation.  MTA will install a new underground copper distribution line and spare duct from the existing pedestal at “PIPE” Sta. 3358+32.3 175.4’ RT to a new pedestal at “PIPE” Sta. 3358+20.1 100.0’ LT.  This work includes a new bore across W. Pipestone Drive to a new pedestal at “PIPE” Sta. 3352+86.2 44.0’ RT.

The Contractor shall allow MTA seven (7) working days to complete the above-described scope of work.

The existing underground copper distribution cable and spare duct crossing S. Weeping Birch Street at “WEEP” Sta. 3560+38.5 are in conflict with the proposed ditch cuts on either side of the roadway and require adjustment.  MTA will vertically adjust this facility to maintain a minimum of 4-feet of cover.  The excavation work will be performed by MEA.

The Contractor shall allow MTA three (3) working days to complete the above-described scope of work.

CFHWY00599

651-1.04 COOPERATION BETWEEN CONTRACTORS.  The following state owned projects may be under construction concurrently with this project.

| Project Name: | Project No.: |
| --- | --- |
| Wasilla Main Street Rehabilitation | Z600770000 |

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

CR651-020118R2_SSHC2020

Special Provisions

Replace Section 652 with the following:

SECTION 652
PROSECUTION AND PROGRESS – SUPPLEMENTAL REQUIREMENTS

652-1.01 DESCRIPTION.  Supplemental requirements for Section 108. Prosecution and Progress.

652-1.02 RELATED SECTIONS.  Section 108, Prosecution and Progress.

652-1.03 PROSECUTION AND PROGRESS.  In Subsection 108-1.03:

	Replace the last sentence in the 1st paragraph with: "Submit the following at the Preconstruction Conference:"

	Replace the last sentence in No. 1 with: "A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor, subcontractors and utilities will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer."

652-1.04 LIMITATION OF OPERATIONS. In Subsection 108-1.04:

	Add: "Limit ground disturbed by construction activities and not permanently stabilized between all roadways combined, at any specific time, to a maximum of 11,000 feet parallel to the roadway(s), unless additional length is approved. Stabilize disturbed ground according to Section 641 Erosion, Sediment, and Pollution Control."

CR652-071519

Special Provision

Add the following Section:

- SECTION 654
MONITOR

654-1.01 DESCRIPTION. When authorized by directive, engage a Professional Service Contractor to monitor eagle(s) at their nests.

654-1.02 SUBMITTAL.

1.	Eagle Monitoring Plan and documentation as required by the monitoring plan.

2.	Professional Service Contractor resume(s).

654-1.03 QUALIFICATIONS. Each position is required to be an employee of the Professional Service Contractor.

Professional Service Contract Manager.

1.	Bachelor of Science degree in biology, environmental science, or ecology and working in the field of the degree, or

2.	Two years of experience monitoring or studying the habitat of birds of prey.

Monitor.

1.	Professional Service Contract Manager or a person trained and supervised by the Professional Service Contract Manager or other similarly qualified representative.

654-2.01 MATERIALS.

Video Camera	Optical zoom lens, minimum 10 power

654-3.01 CONSTRUCTION REQUIREMENTS.

Before beginning construction activity in the restricted area(s) specified in the directive, submit and receive approval for the following:

1.	The qualifications of the Professional Service Contract Manager and Monitor.

2.	An Eagle Monitoring Plan prepared by the Professional Service Contract Manager coordinated with the Contractors' Work Plan for work in the restricted area or any timing restricted period.

During Construction, submit and receive approval for the following:

1.	Eagle monitoring documentation, reports, forms, video as required by the approved Eagle Monitoring Plan and included in the authorizing directive.

Refer to Section 107-1.11 Eagles for further information.

654-4.01 METHOD OF MEASUREMENT. Eagle monitoring measured as specified in the authorizing directive.

654-5.01 BASIS OF PAYMENT. Eagle monitoring work specified in the authorizing directive.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 654.2002.____ | Eagle Monitoring | CS |

CR654-100117R

Special Provision

Replace Section 660 with the following:

- SECTION 660
SIGNALS AND LIGHTING

660-1.01 DESCRIPTION.  Furnish and install, modify, remove, or salvage one or more traffic signal systems, flashing beacon systems, highway lighting systems, sign illumination systems, traffic count systems, electrical equipment on structures, falsework lighting, partial installations for future systems, or combinations thereof, as specified.

Where an existing system is to be modified, reuse the existing material in the revised system as shown on the Plans or specified in the Special Provisions, and salvage or dispose of all other materials.

When required by the Special Provisions, provide an on-site manufacturer’s representative to:

- Energize and adjust the electrical system.

- Provide acceptable instruction for the operation and maintenance of the electrical system.

660-1.02 DEFINITIONS.

Use the definitions in NEMA TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements, Section 1, Definitions, along with the following:

- Electrolier. The complete assembly of pole, mast arm, luminaire, ballast or driver, and light source.

- Luminaire.  The assembly which houses the light source and controls the light emitted from the light source. Luminaires consist of hood (including socket, lamp, and ballast or driver), reflector, and glass globe or refractor.

- Lighting Standard.  The pole and mast arm which supports the luminaire.

- Vehicle.  Any motor vehicle licensed for highway use by the State of Alaska.

660-2.01 MATERIALS.  Use materials that conform to Section 740, the Materials Certification List, the Plans, specifications, and the following:

Concrete			Section 501 (Class A)

Grout			Subsection 701-2.03

Reinforcing Steel			Section 503

Paint			Subsection 708-2.01

Steel Pipe Pile			Section 715

Anchor Plate			ASTM A709

Galvanizing				Subsection 716-2.07

Anchor Bolts				Section 740-2.02

Precast Concrete Products		Subsection 550-2.03

- Equipment List(s) and Drawings.  Within 30 days after the Contract award, submit 8 collated copies of a portfolio of equipment and materials proposed for installation to the Department for review and approval. Include a table of contents in the portfolio(s) that includes each item’s intended use(s) and the following:

  - Materials on the Qualified Products List: The Qualified Products List does not apply to the 660 items.  Provide catalog cuts of materials to the Engineer for review and approval.

  - Materials Not on the Qualified Products List: Catalog cuts that include the manufacturer’s name, type of product, size, model number, conformance specifications, and other data as may be required, including manufacturer’s maintenance and operations manuals, or sample articles.

  - Pole Package.  A complete set of design, fabrication, and installation proposals for each signal and lighting pole. Include stamped engineering calculations, mill certifications, shop drawings, welding plans, equipment lists, and pole installation plans.

  - Materials Not Requiring Certification: Only submit those materials for review and approval if they are included on the Materials Certification List (MCL).

- As-Built Plans.  Prepare 3 complete sets of red lined as-built plans and keep them current with the construction. Detail in the as-built plans all construction changes made to the Plans. Include the following information on the appropriate sheets:

  - Location and depth of conduit runs

  - Station and offset of all junction boxes

  - Heights of signal faces and overhead signs

  - A list of equipment, including manufacturer, brand, and model number installed in each controller cabinet

Furnish copies of the as-built plans at least twice a month during construction so that they may be reviewed for accuracy and completeness. Furnish any additional information required to clarify the as-built plans and correct all discrepancies. The Department will not make progress payments for the signal and illumination work completed until reviewing accurate as-built plans reflecting the construction progress. Correct any deficiencies before payment.

Before final inspection of the work, submit 3 complete sets of as-built plans to the Engineer. You may substitute 2 colored copies of the as-built plans in lieu of keeping the 3 separate original copies. If you elect to do this, a sample of the method of copying must be approved before starting any work on the signal and lighting items.

Place 1 copy of the controller cabinet diagram, detector assignment sheet and the intersection and phase diagram as reviewed by the Engineer inside of each controller cabinet.

3. 	Warranties, Guarantees, and Instruction Sheets.  Deliver to the Engineer all manufacturers’ warranties, guaranties, instruction sheets, and parts furnished with materials used in the work before the Department assumes maintenance responsibilities.

CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL.

- Scheduling of Work.  Complete each new traffic signal system, highway lighting system, and sign illumination system and ensure it is ready for operation before opening to traffic the corresponding section of new alignment. Contact the regional DOT&PF Traffic Signal Technician 24 hours in advance of work on a signal or lighting system. Contact shall be made through the Engineer.

After staking pole foundations, verify there will be no overhead or underground utility conflicts with foundations, poles, mast arms, or conduits.  Locate and protect existing underground and overhead utilities.  The location of cables, conduits, junction boxes, foundations and poles that are shown on the Plan sheets are approximate and it is the Contractor’s responsibility to verify the actual location when working in the area.  See Subsection 105-1.06.

Existing signing and traffic markings shall not be allowed to conflict with new signal modifications.  New signing and traffic marking modifications shall not conflict with existing signals and shall be kept current with signal modifications. Conduct work with the existing traffic signal systems remaining in operation unless authorized otherwise by the Engineer.

Incidental materials and other items that are not shown on the Plans, assembly drawings, or specified herein, that are necessary to complete the system, must be furnished and installed as though such materials and other items were shown on the Plans, assembly drawings, or specified herein.

Protect metallic materials against corrosion.  Hot-dip galvanize ferrous metals such as bolts, braces, bodies, clamps, fittings, guards, nuts, pins, rods, shims, thimbles, washers, and miscellaneous parts not of corrosion resistant steel, according to ASTM A 123 or A 153, except where other equivalent protection treatment is specifically approved in writing by the Engineer.

Asphalt patches placed in existing asphalt for loops and conduit crossings must be placed prior to the end of shift in which the loops and crossings are placed. Asphalt patches will match the thickness of the existing asphalt to a maximum of 3 inches thick. Where the existing asphalt is thicker than 3 inches, use compacted crushed aggregate base course to make up the difference.

Do not place traffic signal systems in operation until the street lighting is energized at controlled intersections.

Install detector loops and underground conduit before applying new pavement. 

Do not pull conductors or cables into conduit until the junction boxes are set to grade, crushed rock sumps are installed, grout is placed around the conduit, and metallic conduit is bonded.

In vehicular undercrossings, place soffit lights in operation as soon as practicable after removing falsework from the structure. Place lighting for pedestrian structures in operation before opening the structure to pedestrian traffic.

- Safety Precautions.	Before starting work on existing street lighting circuits, de-energize the system by opening disconnect switches, and/or opening bypass switch plugs, and tagging each opened device as detailed in Part 4, Section 44, Article 440 of NESC. Where said circuits are under the control of an electric utility, obtain written assurance daily from the utility that the circuit being worked on has been de-energized. 

Prior to beginning work, perform lockout/tagout procedures and establish an electrically-safe work condition per NFPA 70E Article 120.Post suitable signs at load centers when any of the circuits from that load center are being worked on. 

Existing circuits listed on the wiring diagrams and Plan sheets were obtained from as-built information and must be verified before work involving those circuits.

- Excavating and Backfilling.  Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors before final lift paving.  Provide traffic control to complete this work according to the requirements of Section 643.  Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit.  Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

When conditions allow HDPE conduit to be installed by a plowed technique, restoring the area disturbed from the process shall be accomplished according to Subsection 204-3.01. Density testing may be waived and compactive effort substituted at the discretion of the Engineer.  This work is subsidiary to conduit installation.  Use Selected Material, Type A for backfill.

Dispose of, according to Subsection 203-3.01, excavated materials that remain after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in Subsection 703-2.07. Disposal of this material is subsidiary to the 660 Pay Items.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations.  Backfill excavations with materials that meet the following requirements:

- Backfill foundations with material that meets the requirements of Selected Material, Type A that passes through a 3 inch sieve.

- Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift.

- In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

- Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material cleaned free of rocks exceeding a 1 inch maximum dimension.  Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to Subsection 203-3.04.  In other locations, compaction may be as approved by the Engineer.

4.	Welding.  Complete welding according to Subsection 504-3.01.7. Welding and approved shop drawings.  

Submit shop drawings of the proposed work with the welding plans for approval.  The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes that were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface.  For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole.  Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole.  Grind the welds smooth and flush with the adjoining pole and disk surfaces.  Repair the damaged finish according to Subsection 660-3.01.8.

5.	Removing and Replacing Improvements.  The Contractor shall complete the following work at the Contractor’s expense.

a.	Remove improvements that block completion of the work detailed in the Plans as specified herein.

b.	Reconstruct with new materials the non-reusable improvements the Contractor removed to complete the work.

c.	Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

d.	Reconstruct with new materials improvements damaged or removed by the Contractor not conflicting with the work and not scheduled for removal.

Nonreusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings.  Reusable improvements include the items that were made before installation.  Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition.  In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil.  Match the top of the topsoil with the bottom of the vegetative mat. Apply seed and keep the seeded areas watered according to Section 618. 

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621.  Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

6.	Salvaging and Reusing Electrical Equipment.  When the Plans include existing electrical equipment scheduled for removal or relocation, remove, and store the equipment listed in the following paragraph without damaging it.  Deliver removed equipment not scheduled for reuse to the local District Maintenance Station or place specified in the Plans or Special Provisions.  Notify the district superintendent or person specified by telephone one week before planned delivery date.

Salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, load centers, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for relocation.  The Contractor shall replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.

Controller assemblies and load centers include the cabinet and equipment contained in the cabinet before Contract award.

Remove from the highway right-of-way materials associated with the equipment removed or relocated and not scheduled for reuse, including conduits, junction boxes, conductors, and foundations.  Raze the tops of foundations abandoned in place according to Subsection 660-3.02.  Fill the holes left by removing junction boxes and foundations with Selected Material, Type A and compact as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned in place.  The Department may require a credit for this waiver.  Remove the ends of abandoned conduits from the junction boxes that will remain in service.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer.  Note the location and condition of the materials.  When material specified for reuse is found in an unserviceable condition, the Engineer will determine whether to repair it or replace it with new material that will be paid for as extra work under Subsection 109-1.05.  Retain a copy of the inventory and give the original documents to the Engineer.

When the Plans specify reinstalling existing equipment at new locations and installing State furnished equipment, complete the following work at the Contractor’s expense.

a.	For poles, install new foundations, furnishing the new nuts, bolts, washers, and conduits needed to complete the installations.

b.	For lighting poles, install new illumination tap wires and fused disconnect kits.

c.	For luminaires, clean the luminaires inside and out and install new lamps of the same wattage.

d.	For signal heads, furnish and install the mounting brackets needed to complete the relocation, and clean the signal heads inside and out.

e.	For poles and undisturbed poles from which the Plans specify removing equipment, repair the holes that were made to mount equipment according to Subsection 660-3.01.4 Welding and repair the finishes according to Subsection 660-3.01.8 Repairing Damaged Finishes.

Repair holes left in the shafts of exiting metal poles, due to removal of equipment or mast arms, by welding in a suitable disk, grinding smooth, and painting as provided for repair of damaged coatings in AASHTO M 36 or using a knockout seal.

When ordered, the Engineer will pay for repairing existing damaged finishes on existing equipment according to Subsection 660-3.01.8 as extra work.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to Subsection 660-2.01.1.

Deliver the salvaged materials undamaged to the local DOT & PF Maintenance and Operations Yard.

Contact the local state Electrician one week before planned delivery.

7.	Field Tests.  Electrical circuits must pass the following tests before the Engineer will accept the work for payment.  Perform these tests in the presence of the Engineer, and document the results of each test on a per circuit basis.  Retain a copy of test results and give the original documents to the Engineer.  Furnish equipment needed to perform these tests.

Replace or repair at the Contractor’s expense, and in an approved manner, faulty materials and work revealed by these tests.  After making repairs, repeat tests on the repaired circuit and continue this process until circuits have passed required tests.  The Department reserves the right to have the Contractor retest circuits, and to use the retest results to accept or reject individual circuits.

a.	Grounds.  Before completing the circuitry and functional tests, physically examine conduits ends, junction box lids, load centers, and the foundations for signal posts and poles, lighting poles, and controller cabinets to ensure the grounding system required by Subsections 660-3.06 and 661-3.01 has been installed and splices and connections are mechanically firm.

b.	Continuity.  When loop detector work is included, test each loop detector circuit for continuity at the roadside junction box before splicing the loop detector to the lead-in cable.  Each loop detector must have a resistance less than 0.5 ohms.

After splicing the loop detectors to the lead-in cables, test each pair at the controller or detector cabinet.  Each pair must have a value less than 5 ohms for single pair lead-in cables and 10 ohms for multipair lead-in cables.  The continuity test ohm reading at the cabinet must be greater than the ohm reading measured for the loop detector at the junction box.

c.	Insulation Resistance (megohm) Test.  Complete this test to verify the integrity of each conductor’s insulation after pulling the conductors and cables into position and before terminating the conductors.  At 500 VDC, each conductor’s insulation shall measure a minimum resistance of 100 megohms or the minimum specified by the manufacturer.  With single conductors, complete the test between each conductor and ground.  In each multiconductor cable, complete the test between conductors and between each conductor and ground.

When loop detector work is included, after splicing the loops to the shielded pairs in the lead-in cables, measure each pair in the lead-in cables at the controller or detector cabinet between one conductor and the cabinet ground rod.

d.	Inductance Test.  When loop detector work is included, measure each detector loop and lead-in cable system at the controller or detector cabinet.  The inductance must be in the range of 50 to 500 microhenries.

e.	Circuit.  Energize every signal indication circuit with lamps installed before installing the load switches.

f.	Functional.  Perform the following tests on each signal and lighting system after the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity, and circuitry.

(1)	For each new traffic signal system, complete at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory operation.  The Engineer may decide to omit the flashing portion of the test for modified signal systems and for new signals that replaced existing signals that remained in operation during the construction phase.

If the Engineer omits flashing operation and the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for five days with continuous, satisfactory operation.

Begin the signal functional tests between 9:00 a.m. and 2:00 p.m. on any day, except a Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Before each system activation, aim signal faces according to Subsection 660-3.08 and ensure equipment specified in the Plans is installed and operable, including: pedestrian signals and push buttons; signal backplates and visors; vehicle detectors; highway lighting; and regulatory, warning, and guide signs.

(2)	Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5 day operational test using the photocell.

(3)	Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

(4)	Perform a continuous 5 day burning test on each pedestrian overpass and underpass lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system functions normally when power is returned.

8.	Repairing Damaged Finishes.  Examine new, reused, and State furnished equipment for damage to its finish before putting the equipment into service.  Repair the damaged finishes found according to the following:

a.	Galvanized.  Repair damaged areas more than 12 inches away from welds and slip fit areas, by applying minimum 7.8 mils of zinc based alloy applied according to ASTM A780.

If the damaged areas are within 12 inches of welds and slip fit areas, make the repair by applying a minimum 7.8 mils of zinc rich paint applied according to ASTM A780.

b.	Painted.  Repair damage to painted finishes according to the following

(1)	Wash the equipment with a stiff bristle brush using a solution containing two tablespoons of heavy duty detergent powder per gallon of water.  After rinsing, wire brush surfaces to remove poorly bonded paint, rust, scale, corrosion, grease, or dirt.  Remove dust or residue remaining after wire brushing before priming.

(2)	Factory or shop cleaning methods may be used for metals if equal to the methods specified herein.

(3)	Immediately after cleaning, coat bare metal with pretreatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

(4)	Give signal equipment, excluding standards, a spot finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

(5)	Give nongalvanized standards 2 spot finish coats on newly primed areas.

Paint coats may be applied either by hand brushing or by approved spraying machines.  Perform the work in a neat and workmanlike manner.  The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint spraying machine prove unacceptable.

9.	Regulation and Code.  Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the Authority Having Jurisdiction.

10.	Failed Equipment and Workmanship.  For the term of the Contract, from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair failed workmanship.

660-3.02 FOUNDATIONS.

- Cast-in-Place Foundations.  Cast-in-place foundations for posts and poles in drilled holes. Use either precast or cast-in-place foundations for cabinets. Locate the tops of traffic signal post and pole foundations flush with the adjacent finished walkway, shoulder, or surrounding ground.

- Form the entire controller foundation and the top 12 inches of pole or post foundations and give the top a smooth steel trowel finish.

- Place conduits in the center of the pole-post foundations with clearance allowed for bushings. If subsurface conditions prevent completing a drilled hole, and when approved, use a corrugated metal pipe (CMP) form as a substitute for the drilled hole. Consider the savings in concrete to offset the cost of supplying and installing the CMP form. No additional payment will be made for the CMP formed foundation.

- When a CMP is used, over-excavate the area around the form enough to allow for proper compaction around the form. Perform backfill operations according to Section 204. Do not use water for drilling operations or for any other purpose where it may enter the hole.

- Use controller cabinet anchor bolts as recommended by cabinet manufacturer and set with a template.

- Place Class A concrete meeting Section 501. Place reinforcing steel meeting Section 503. If required, use corrugated steel pipe that is at least 14 gage, meeting Subsection 707-2.01.

- Drill holes or use forms that are vertical and true to the locations shown in the Plans. Before placing the form or reinforcing steel cage, remove loose material to ensure the foundation rests on firm, undisturbed ground.

- If a reinforcing steel cage is required, place and secure it symmetrically about the vertical axis and securely block it to clear the sides of the foundation. Use a template to securely support all anchor bolt assemblies and conduit ends so they do not move during concrete placement.

- Do not permit surface water to enter the hole. Before placing concrete, remove all water that may have infiltrated in the hole. Thoroughly moisten both the forms and the ground before placing concrete. Pour each foundation in one continuous pour.

- Do not erect or place posts, poles, and pedestals on the foundation until 7 days after placing the concrete. Plumb the assembly by adjusting the nuts on the anchor bolts before attaching the skirt.

- Replace, with no additional compensation, all finished foundations with anchor bolts that do not match the base plate of the pole or are out of plumb. Do not modify the anchor bolts or base plate to get the base plate set on the leveling nuts. Protect foundation anchor rods from damage before installing controller cabinets.  The Engineer must approve the method used for protection.  This work does not relieve the Contractor of responsibility specified under Subsection 107-1.15.

- Furnish anchor rods that conform to ASTM F1554, the grade and supplementary Charpy V-Notch requirements listed in the Plans. Furnish each anchor bolt with three nuts and two washers.

Install the bottoms of the bottom leveling nuts in a level plane within 1 inch of the top of foundations.  Adjust nuts until their tops form a level plane.  Install one washer on top of leveling nuts and, after setting the pole on these washers, install one washer under top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Generously lubricate the bearing surface and internal threads of top nuts with beeswax.  Tighten top nuts to a "snug" condition.  Use a click type torque wrench to apply 600 foot-pounds of torque to the "snug" top nuts.

- Attach a bare, copper wire as a grounding electrode conductor to the spiral bar in the reinforcing steel cage.  Use an irreversible compression type connector to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled #4 AWG, bare, copper wire as the grounding electrode. Route the conductor to protrude near the top, center of the foundations.  Slide a minimum 6 inch long, Schedule 80 polyvinyl chloride (PVC) or high density polyethylene (HDPE), protective sleeve over the conductor.  Allow 1 inch of the sleeve and 24 inches of conductor to protrude from the foundations.

- Pile Foundations.

  - Install pipe piles according to Section 505.

  - Install pipe piles open-ended and to a minimum depth of 15 feet (less top projection).

  - Use CJP groove welds for all circumferential welds.

  - Inspect 100% of CJP welds using UT or RT.

  - Backfill and compact the work hole around upper portion of each pile in 8-inch lifts with a soil-cement mixture.

  - Certify steel pipe piles by matching the stencils on the pipe piles (by 300 foot lots) to the physical and chemical tests for the applicable lot.

  - Use no more than one splice per foundation. Locate the splice at least 10 feet from the top of the pile.

    - All Foundations.

- Install frangible couplings according to the manufacturers written installation instructions. Use shims furnished by the coupling manufacturer.

- Provide new foundations and anchor bolts of the proper type and size for standards that are to be relocated. Install the anchor bolts on a bolt circle that matches the base plate.

- Install a raised Type III junction box on the door side of the controller cabinet, and butt it against the cabinet’s foundation unless installing a one-piece cabinet/junction box foundation. Extend the top of the controller cabinet foundation 18 inches above the junction box and provide it with a 1-inch diameter drain. The drain connected to the cabinet interior must empty to the rear and above the ground. Place all conduits in the door side half of the foundation to provide adequate terminal block clearance.

- Existing foundations may be abandoned-in-place. However, remove the tops of the foundations, reinforcing steel, anchor bolts, and conduits to at least 12 inches below the roadway subgrade, sidewalk, or unimproved ground. Backfill the resulting hole with Selected Material, Type A and compact material as directed by the Engineer.

660-3.03 CONDUIT.  Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified.  Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits.  Install conduits of the sizes specified along the routes detailed on the Plans.  When routing is not shown, route conduits as directed by the Engineer.

- Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

- Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches.  Excavate, bed conduits, and backfill trenches according to Subsection 660-3.01.3, Excavating and Backfilling.

- Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods.  Jacking conduits into position is allowed.  However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

- If encountering obstructions during jacking or drilling operations obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 11/4 to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

- Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs.  To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box. At junction boxes where polyethylene conduits runs are to enter the junction box, install a 5 foot section of RMC on the horizontal end of the RMC sweeps.

- When installing loop detectors, install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box.  Extend the ends a minimum of 2 inches beyond the inside wall of the box.

- Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs.  Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors.  Cover the holes with a wrap of approved filter cloth secured with 2 self-clinching nylon cable ties.

- Keep conduits clean.  Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends. Tapered or universal fit plugs are acceptable for temporary usage. Any permanent plug or cap shall be an approved watertight cap.

- At the low points of conduit runs, install sumps containing a minimum 2 cubic feet of coarse concrete aggregate material that conforms to Subsection 703-2.02.  Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

- Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary.  Install additional drains and aggregate sumps at the low spots, if any.

- Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 21/2 inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

- Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit.  Cut the same number of threads as found on the factory threaded ends.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.  Do not use slip joints or pieces of running thread pipe.

- Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

- When standard couplings cannot be used to join conduit components, use approved threaded unions.

- Bury a continuous strip of 4 mils thick, 6 inch wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a red background.

- When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

- In foundations, install 90 degree elbows and conduits of the size and quantity shown on the Plans.  Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

- Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct sealing compound.

- Install expansion fittings in conduits that cross expansion joints.

- Install a polypropylene pull rope with a minimum 200 pound tensile strength in future use or spare conduits, and reinstall the plugs.  Double back pull rope, at least two feet, into both ends of each conduit. Tapered or universal fit plugs are acceptable for temporary usage. Any permanent plug or cap shall be an approved watertight cap.

- Install a pull tape with a minimum 200 pound tensile strength in all traffic signal conduits entering signal poles, signal junction boxes, signal controller cabinet foundations. Double back pull tape, at least two feet, into both ends of each conduit.

- The Contractor may install conduits larger than the sizes specified.  If used, it must be for the entire length of the run.  Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

- Clean existing conduits that will remain in service using a heavy duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch.  Clean the conduits before pulling in new cables and after removing cables planned to be removed or replaced as follows:

  - When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

  - Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

- When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit.  When extending existing conduits, add no more than a 90 degree horizontal bend to the extension.

- When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

- When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

- Remove the ends of abandoned conduits from junction boxes that will remain in service.

- When Plans call for connecting polyethylene conduit to RMC use a UL listed electrofusion coupler rated for direct bury application. The coupler must be rated for same wall thickness as the adjoining conduits. If electrofusion coupler fails to properly bond to conduits, the Engineer may give approval to use DuraLine Shur Lock type couplers or approved equivalent, but only after first attempting use of electrofusion couplers in each case. Thread the ends of the RMC with the same number of threads as found on the factory threaded ends of RMC.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

660-3.04 JUNCTION BOXES.  Install precast reinforced concrete junction boxes of the types specified.  For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them.  For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them.

Junction Box Location

When shown, install junction boxes at the station and offset locations specified.  When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement.  If the 8 feet offset falls:

1.	In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility. When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

2.	In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

3.	Outside the right of way, install the boxes just inside the right of way line.

4.	In a raised median, install junction boxes near the center of the median.

5.	In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

6.	Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

7.	On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing Type 1A junction boxes in driveways and in locations subject to use by heavy trucks.  When shown near the ends of medians, install junction boxes at least 10 feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes behind electroliers and posts.  When installing copper signal interconnect cable use minimum size Type II junction boxes.

Four (4) Limitations

Limit the distance between adjacent junction boxes to the following dimensions:

1.	400 feet for conduits that contain signal interconnect cable only.

2.	300 feet for conduits, that exclusively contains two loop lead-in cables.

3.	300 feet for conduits that contain a single cable other than signal interconnect.

4.	190 feet for conduits, that contains more than one cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work; otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria.  In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade.  In seeded areas, install the tops of junction boxes to 2 inches below all other areas.

Bond junction box lids to an equipment grounding conductor according to Subsection 660-3.06.  Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box.  Drains shall consist of porous backfill material that conforms to Subsection 703-2.10.  Minimum drain dimensions include an 18" depth and a length and width equal to those of the junction box it drains.  Compact the porous backfill material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker.  Conform markers to the American Public Works Association Standards including but not limited to:

- Color - red

- Material - high-density polyethylene

- Shape - round (ball like)

- Size - 4 to 5 inches in diameter

- Configuration - encapsulating an antenna tuned to the appropriate frequency for locating power

- Responsive range - up to 5 feet away from the locator device

- Environmental conditions - including extremes in temperature at the installation site

8. 	Contain no internal power source

Acceptable marker manufacturers include:

- 3M, Dynatel EMS ball marker model no. 1402-XR

- Tempo (a Textron Company), Omni Marker

- Substituted, equivalent approved equal device

660-3.05 WIRING. Install power conductors serving the cabinet sized such that their ampacity rating is greater than the cabinet total connected load after applicable diversity factors have been applied. Make wiring neat in cabinets by cabling wires together with self-clinching nylon ties. Terminate all spare conductors on terminal blocks. Attach all conductors, including spares, to terminal blocks with “spade” type terminal lugs. Furnish additional terminal blocks if enough locations are unavailable in existing terminal blocks. Install signal cabling continuously without splices from the controller cabinet to the termination lugs in the signal housing.

- Do not pull conductors into conduits until the following conditions are met:

  - The prescribed clearances around conduit ends are provided,

  - Crushed rock sumps are installed under junction boxes,

  - Conduit ends protrude above the bottom of junction boxes within the prescribed range,

  - New conduits are free of material that became lodged in them during the completion of the work,

  - Reused conduits are cleaned according to Subsection 660-3.03,

  - Junction boxes are set to grade, and

  - Grounding bushings are installed on the ends of metallic conduits.

- Pull conductors by hand or by approved commercially built cable-pulling equipment that is specially designed for that purpose. Do not pull cable by any other means. Equip the cable pulling device with a force limiting circuit and force gauge.

- Use wire-pulling lubricant when placing the cables and conductors in conduit. Do not allow the tension of the wire or cable to exceed the manufacturer’s recommend allowable tension for the conductor or cable.

- When adding new conductors to a conduit with existing conductors, remove all conductors and clean the conduit with a mandrel or brush. Pull both old and new conductors through as a unit. In a new installation, pull all conductors through the conduit as a unit.

- Leave at least 1 foot of slack in the bottom of each signal or combination signal and lighting pole of each signal conductor or cable. Neatly leave at least 3 feet of slack illumination and signal conductor or cable curled up in the bottom of each junction box or splice location.

- Separate the neutral for pedestrian push button circuits from the signal light circuit neutral.

- Run all signal and feeder conductors continuously without splices from a terminal block located in a cabinet, compartment, or signal head, to a similarly located terminal block. When modifying an existing signal system when specifically shown in plans, splice existing conductors (cables) to new conductors (cables) as required to complete the signal system. Make these splices when indicated in the plans.

- Route highway illumination cable through each lighting pole designated for connection to that cable’s circuit. Do not splice illumination cable between a load center and a pole or between poles. Join the individual conductors by using non-insulated, overlap type pressure connectors. Insulate with mastic-lined heat shrink tubing or 2 layers of one-half lapped UL listed electrical tape. Do not use wire binding screws, studs, or nuts. Stagger splices to minimize the overall diameter.

- Install all loops in 1-inch rigid schedule 80 PVC conduit in the roadway and to the nearest junction box. Run loop lead-in cable continuously without splices from the controller cabinet to the curbside detection junction box nearest the loop being spliced to the lead-in cable. Splice the loop(s) to the lead-in cable by soldering at the junction box and encapsulating in a waterproof splice kit.

Multiple loop configurations must have the individual lead-ins, multiple pair, or single pair brought to the controller cabinet for termination. Make series connection of loop lead-ins in the controller cabinet only. Wind all loops in the same direction with the starting lead marked with an “S.” Connect the black conductor of the pair shown in Table 660-1 to the “S” designated conductor of the loop. Connect multiple loop detectors in the same lane so that the adjacent loops are in alternating directions clock wise (CW), counter clock wise (CCW), etc.

- When splicing loop detectors to multi-pair loop lead-in cables, complete the work according to the following.

a.	See the Plans for the identifying number assigned to each loop detector and the loops assigned to each loop lead-in cable. Using this information, splice the loop detector tails to the paired conductors found in each lead-in cable, using the color code in Table 660-1.

b.	Remove a short section of cable jacket and only cut the shielded pairs dedicated to loop detectors being spliced. Run these pairs, without splices, to the controller cabinet.

c.	Solder the loop and lead-in conductors together using the pre-loaded low temperature solder with heat shrink tubing approved splice connector.

TABLE 660-1 
MULTIPLE PAIR LOOP LEAD-IN COLOR CONNECTION SCHEDULE

| Loop Detector Number | Colored Pair |
| --- | --- |
| The lowest numbered loop detector | Red and Black |
| The second lowest numbered loop detector | Blue and Black |
| The third lowest numbered loop detector | White and Black |
| The fourth lowest numbered loop detector | Green and Black |
| The fifth lowest numbered loop detector | Brown and Black |
| The sixth lowest number loop detector | Yellow and Black |
| Usually a spare pair | Orange and Black |

d.	Crimp spade terminals to the ends of the shielded pairs in the controller cabinet.

- Maintain the electrical isolation between shields and do not allow the drain wires to come in contact at any point other than the ground bus in the cabinet. Tie all drain wires to the ground bus at the controller cabinet.

- Encapsulate illumination/power cable splices in four piece molds that are held together with stainless steel hose clamps. Two pieces form a cylinder and two flexible end caps. Seal the ends and allow the conductor entry. Use molds with dimensions suitable for the splice made, encase the cable jackets, and fill with an insulating and sealing epoxy resin.  Furnish molds rated for 600 VAC operation, feature fill, and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, one splice may be used in the following cases:

a.	An in-line splice may be used when a planned cable run exceeds the length available from the manufacturer on a single spool of cable.

b.	In a run of 1,000 linear feet or more.

When a cable is spliced, it shall occur within an appropriately sized junction box or in the base of an electrolier designed for said splice.

Insert a loose woven polyester web that allows a full 1/4 inch of insulating compound to flow between the splice and the inside of the mold. Fill the PVC molds with epoxy resin that cures transparent, is nontoxic, is non-corrosive to copper, and does not support fungi or mold growth.

- Encapsulate all loop lead-in cable splices in rigid, transparent, PVC or PE approved tubing filled with re-enterable polyurethane electrical insulating and sealing compound. Furnish splice kits rated for 1000 volts AC operation and direct burial. When filling the mold bodies of loop lead-in cable splices, use a compound that provides re-entry capabilities.

- Permanently identify all cables and single wire conductors by labeling all pole bases and cabinets, at each detector loop tail/lead-in cable and illumination cable splices, and in junction boxes adjacent to lighting and signal poles. When modifying an existing system, label all new and existing lighting cables/conductors with circuit numbers at locations noted above. If the existing circuits are not identified, the Engineer will provide the required circuit numbers.

- Label the cables used in the signal and illumination systems with the following legends:

  - Use the legends included in Table 740-2, for the cables listed.

  - Use the loop number shown on the Plans to label each tail of all loop detectors and the paired loop lead-in conductors in the controller cabinet.

  - For interconnect cables, use the first letter of the direction the cable follows to the adjacent intersection on each cable. Add a number suffix if more than one cable is routed to the adjacent intersection.

Furnish the two types of identification tags listed below that feature hand written legends. Write the legends specified neatly and legibly, using a black marking pen recommended by the tag manufacturer. Replace at no expense to the State all identification tags the Engineer deems illegible.

- Use identification cable ties for labeling loop detector tails and the paired conductors included in each loop lead-in cable in the controller cabinet. Furnish identification cable ties made of nylon that feature a nonmagnetic stainless steel locking device embedded in the head and a tag attached "flag style" to the head. Use cable ties consisting of a single strap with a minimum size tag of 3/4 inch by 3/8 inch.

- To label all other cables, use cable tags made of nylon reinforced vinyl impervious to the elements and which will not tear. Provide tags with a 4 inch by 1-3/4 inch minimum size that attach flag style at one corner to a single strap. Furnish yellow tags for labeling all signal and interconnect cables and red tags for labeling lighting and feeder cables.

- Terminate the control and power cables as shown in Table 740-2.

- Telemetry cable termination shall be coordinated with a signal technician. Provide type No. 66B3-50 terminal blocks as required.

- Wire luminaires using No. 10 AWG illumination tap conductors that run from the fused disconnect kit in the pole base.

Install a fused splice connector between the line and luminaire ballast tap conductors in the base of every pole equipped with a luminaire.

Attach the conductors to the connector halves with setscrew type pressure connectors. Provide the plug and socket assembly so that the fuse remains in the load side plug without exposing live metal parts when the connector separates and the coil springs are not included in the current carrying circuit.

Make the fused connectors readily accessible from the handhole. Install tap conductors to prevent slack when their ends touch the top of the foundation.

- Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

- Whenever conductors cannot be terminated as specified in the Plans in circuit breakers due to size, splice a piece of #8 AWG copper power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductors to 5 feet. Note: this splice is acceptable only if the overcurrent protective device protecting the #8 AWG conductors is rated 40A or less.

- Spare lighting conductors shall be capped in the pole bases and load centers by cutting the wire flush with the end of the insulation and bending the conductor back against itself and securing with three layers of electrical tape to prevent any possibility of making contact with ground or current carrying conductors.

660-3.06 BONDING AND GROUNDING.  All installations must comply with the grounding and bonding requirements of NEC Article 250 and the following requirements:   Normally non-current-carrying conductive materials enclosing electrical conductors or equipment, or forming part of such equipment, including metallic cable sheaths, metal conduits, non-metallic conduit grounding wire, junction box lids and frames, cabinets, transformer cases, and metal posts and poles, must be electrically connected to earth ground, and must be connected together and to the electrical supply source in a manner that establishes an effective ground-fault current path. Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole. An equipment grounding conductor must be installed between the grounding lug near the base of the pole and the lighting fixture.

Install grounding bushings with insulated throats on the ends of metallic conduits. 

Install an insulated or bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size #8 AWG grounding conductors, except in those conduits that contain circuit conductors larger than #8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installation or removal of conductors from existing conduits, retrofit with new equipment grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the equipment grounding conductor using copper braid with a cross sectional area equal to a #8 AWG and eyelet spaced at 6 inch intervals.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors. 

Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the #4 AWG grounding electrode conductor using irreversible compression type connectors at Portland cement concrete foundations.  For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 5 feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the handhole of each pole.

Bond slip base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the handhole of each pole.

Solidly ground one side of the secondary circuit of a transformer.

Install a 3/4 inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a #6 AWG bare stranded copper wire for the grounding electrode conductor. Furnish one piece bronze clamps with a hex head setscrew that are suitable for direct burial and for use with copper clad ground rods.

When routing a new conduit into an existing junction box or replacing an existing junction box, new and existing conduits shall have the grounding improved to current specifications.

660-3.07 TRAFFIC CONTROLLER ASSEMBLIES.  Prepare each solid-state, traffic controller assembly to operate various traffic signal devices as shown on the Plans. The controller must provide right-of-way, clearance, and other indications using duration and sequence as determined by preset programming.

Details of operation for the complete controller assembly must be according to the traffic phases; preferential phase sequence and concurrence; signal indications; signal indication sequence; detection requirements; and other details shown on the Plans or as specified herein.

- Shop Tests.  The Controller Assembly manufacturer shall conduct a pretest of the cabinet and controller assembly. The pretest includes but is not limited to:

  - Ensure the cabinet is free of paint scratches, dents, sharp edges, and other physical defect.

  - Ensure cabinet hinges, heater, ventilation system, lighting, and door locking mechanism function properly.

  - Ensure that there are no short circuits between AC+, AC-, and GND anywhere in the cabinet.

  - Check that there is no continuity between AC+ and DC+.

  - Check for continuity between any green wire connection point and GND.

  - Ensure devices within the cabinet are labeled properly.

The Controller Assembly manufacturer shall conduct a final test of the cabinet and controller assembly.  Qualified Cabinet Test Technicians shall conduct the final test.  The final test includes but is not limited to ensuring proper operation of flash colors & combination, standard controller phasing, pedestrian pushbutton isolation, MMU, circuit breaker/fuse operation, telemetry operation, loop panel/detector rack operation, EVP operation, and proper police & auxiliary panel operation.

Upon completing the final test the cabinet shall be run, "burned in," under full loads for a period of not less than 48 hours with a test timing plan in effect which utilizes full cabinet phases and functionality.

In the course of testing, a component found to function incorrectly or exhibit physical damage must be replaced with an equivalent new component before delivery.  Should the cabinet fail during burn in, the cause of the failure must be remedied and the test restarted with another 48 hours of burn in. The intent of this specification is to meet or exceed the requirements of Econolite test procedure MWI-10-28 Rev. C. With prior approval of the Engineer, other equivalent test procedures may be substituted.

Upon completion of the pretest, final test, and burn in, the Controller Assembly manufacturer shall issue a letter of certification stating that the required tests have been completed, note defects found and the remedial action taken.  Further, the certification shall state the assembly conforms to the NEMA TS 2-2003 v02.06, Traffic Controller Assemblies with NTCIP Requirements, Section 2 Environmental Requirements.  Submit the certification letter and copies of the test results to the Engineer.

The work required in this subsection is subsidiary to the associated traffic signal system under Pay Item 660.0001.____Traffic Signal System Complete.

- Controller Cabinet Installation.

  - Where the cabinet is mounted on a concrete pedestal foundation, place a 1-inch drain hole or pipe with screen in the foundation, connecting to the cabinet and emptying above the ground line.

  - Place a 3/8-inch fillet of silicone caulking between each controller cabinet and the concrete slab foundation to prevent dust and dirt from entering the cabinet.

  - When called for in the Plans or Special Provisions, add 2 inches of approved foam insulation within the bottom of the cabinet between the control equipment and the concrete base. Design all wiring, terminals, and other items to allow sufficient room for the insulation.

  - On Precast Controller Foundations. When called for in the Plans or Special Provisions, place a 3/8-inch thick, 2-piece exterior grade plywood board on the bottom of the cabinet and under the foam insulation. Place the plywood within the controller cabinet, and do not extend under it. Make holes to allow for the conduits entering the cabinet. Place a pliable sealant composed of a silicon caulking compound between the plywood board and the cabinet and between the plywood board and all the conduits.

  - Place a ground rod in the Type III junction box next to the cabinet or in the foundation of the cabinet if it is precast foundation.

  - See Subsection 660-3.05 and Section 740 for wiring requirements.

- Controller Operation.  Provide the following operations.

  - Wire the controller cabinet to flash the yellow signals on the main street or highway, and the red signals on the cross streets and left turn lanes.

  - Make the flashing circuit independent of the controller unit. They must remain in operation upon shutdown of the controller or removal of the controller from the cabinet.

  - Wire the controller cabinet so that removal of the conflict monitor causes the intersection to go into flashing operation.

  - Accomplish transfer to flashing operation by relays between the normal load switching device and the field terminals.

  - Do not operate pedestrian pushbuttons at more than 24 volts.

  - Controller Priorities.  Prioritize the drives, controls and equipment so that each device, control, or item of equipment overrides the operation of those items listed below it:

    - Power failure

    - Power restart

    - Flashing

    - Railroad preemptor

    - Emergency vehicle preemptor

    - Phase selector

    - Interconnect

    - Time switch

    - Normal controller unit operation

Provide the following preemption operations when called for on the Plans or as specified in the Special Provisions.

  - General.  Preemption units must use the controller unit functional inputs and timings to the largest extent possible. Signal load switching control must remain with the controller unit.

  - Railroad Preemption.  The Railroad Preemption Routine must consist of 4 functional intervals in the order listed below:

    - Enter Preemption Interval.

        - Energize a 120 VAC alarm circuit which may be used for a sign, bell, or beacon.

        - Immediately advance to the pedestrian clearance interval of any walk that is being displayed. On any phase other than the track clearance phase(s), abbreviate the pedestrian clearance interval by a timer with a minimum range of 0-30 seconds.

        - Following the pedestrian clearance period, the controller must advance into and time normally the vehicle clearance intervals.

        - If the preemption is received while in the track clearance phase(s), skip step (b) and (c) above.

    - Track Clearance Interval.

        - Provide a timing period to allow sufficient green clearance time for any vehicles that may be stopped on or immediately behind the railroad tracks. The timing must be adjustable over a range of 0 to 30 seconds.

        - Following the track clearance period, the controller must advance into and time normally the vehicle clearance interval(s).

    - During Preemption Interval.  Allow the controller to operate normally with the exception of not serving those phases that conflict with the railroad crossing. Keep this interval in effect until the preemption call is removed.

    - Leaving Preemption Interval.

        - De-energize alarm circuit.

        - Immediately advance to the active phase normal pedestrian and/or vehicle clearance interval(s).

        - The controller must advance to those phases that were omitted under preemption control when complete control is returned to the controller unit.

  - Emergency Equipment Preemption.  The Emergency Equipment Preemption Routine must consist of 3 functional intervals in the order listed below:

    - Enter Preemption Interval.

        - Energize a 120 VAC alarm circuit which may be used for a sign, bell, or beacon.

        - Immediately advance to the pedestrian clearance interval of any walk that is being displayed. On any phase other than the track clearance phase(s), abbreviate the pedestrian clearance interval by a timer with a minimum range of 0-30 seconds.

        - Following the pedestrian clearance period, the controller must advance into and time normally the vehicle clearance intervals.

        - If the preemption call is received while in the preempt phase(s), skip step (b) and (c) above.

    - Preempt Phase Interval.  Hold the controller in the preempt phase(s) until the call is removed.

    - Leaving Preemption Interval.  When the preemption call is removed, the controller unit must immediately revert to normal operation.

660-3.08 SIGNAL AND LIGHTING INSTALLATION REQUIREMENTS.  Install signal and lighting equipment according to the details shown on the Plans and the following:

Apply antiseizing compound to the following fasteners:  frangible couplings, mechanical grounding connectors, bolts that secure handhole covers and signal mounting hardware to poles and mast arms.  Remove the fasteners from luminaire mounting brackets, fused disconnect kits, grounding bushings, and signal faces that secure the visors, and apply antiseizing compound to these fasteners before completing the installation.

Before passing conductors through the holes made in posts, poles, and mast arms for wireways, remove the burrs and sharp edges from the inside and outside of these holes.

Until each traffic signal and/or flashing beacon goes into operation, keep the vehicular and pedestrian signal faces covered with beige colored canvas shirts sized to fit the signal faces shown in the Plans.  Each signal shirt shall feature elasticized openings that fit over the visors and at least two straps to secure it to the signal.  Provide shirts with a legend that reads "out of service" and a center section that allows an operator to see the indications during system tests.

When not shown in the Plans, determine the shaft lengths of lighting and signal poles and signal mast arm connector plate locations to provide the plan mounting heights of luminaires and traffic signal heads.

Furnish work to install foundations for relocated poles, including: conduit, excavation, reinforcing steel, class A concrete, anchor bolts, nuts, and washers.

- Electrolier Installation.  Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm.  After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

- Signal Pole Installation.  Install signal poles with a slight rake by plumbing the side of the pole opposite the mast arm just above the base plate.  Tighten the nuts on the anchor bolts/rods as described in Subsection 660-3.02.

Cover the gap between the foundation and base plate by installing a metal skirt around the base plate, secured with stainless steel sheet metal screws.

- Vehicular Signal Head Installation.  With two piece mast arms, do not install signal heads within 12 inches on either side of the overlapped splice section.

Attach each side mounted terminal compartment with two 1/2" x 13 bolts, with washers, threaded into holes tapped into the side of the pole at the location shown on Alaska Standard Plan T-30.  Install the vertical pipe members plumb.

When installing 4 or 5 sections vertically stacked signal heads on the sides of poles, secure the vertical pipe to the pole using a steel conduit hanger mounted 6 inches below the top horizontal pipe.

Aim through phase vehicular signal faces at a point located a distance from the face as shown in Table 660-2.  If two through signal faces are not visible from this point at a height of 42 inches above finished grade, consult the Engineer for corrective measures.

| TABLE 660-2 |  |
| --- | --- |
| THROUGH PHASE SIGNAL FACE AIMING POINTS |  |
| 85th Percentile Speed (mph) | Minimum Visibility Distance (feet) |
| 20 | 175 |
| 25 | 215 |
| 30 | 270 |
| 35 | 325 |
| 40 | 390 |
| 45 | 460 |
| 50 | 540 |
| 55 | 625 |
| 60 | 715 |

- Pedestrian Signal and Push Button Installation.  Orient pedestrian signal faces at the center of the crosswalk on the opposite side of the street.  Attach each clamshell bracket with two 1/2" x 13 bolts threaded into holes tapped into the side of the pole.  Install a spacer, furnished by the bracket manufacturer, on each bolt.

Install the push button on the crosswalk side of the pole.  Install push button signs above each push button.  Furnish signs with the arrow pointing in the direction of the appropriate crosswalk.  When channel is used for mounting push button signs, tap the top and bottom sign bolts into the pole.

- Underpass Lighting System Installation.  Mount the luminaires as detailed on the drawings to orient the axis of the lamp perpendicular to the axis of the underpass.

- Flashing Beacon Installation.  When the Plans specify using the flasher in a signal controller cabinet to energize beacons, furnish a two pole, fused block with built in fuse pullers and two fuses to protect the flasher.  Furnish and leave 5 feet of cable in the cabinet.  Others will install the fused block and terminate the beacon cables.

- Wood Pole Installation.  Place the poles in the ground to at least 6 feet deep.

After setting each pole in the ground, backfill the space around the pole with selected earth or sand, free of rocks 4 inches and larger, or deleterious material.  Place the material in layers approximately 4 inches thick and thoroughly compact them with mechanical tampers.

Furnish poles that provide a minimum vertical clearance of 21 feet between the pavement and low point of overhead conductor.

660-3.09 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS.  This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the Contract.  The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, interconnect, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference.  Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing equipment damaged before the transfer of maintenance responsibility.  Therefore, before starting work on the project, inventory the condition of the existing equipment with the Engineer and document the damaged and defective equipment.  If beginning work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems.  The State will pay for electricity used to operate the systems, if the public benefits from their operation.  Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer.  If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

Records.  When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times beginning and completing work, and the names of the Crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than 15 feet.

Alignment.  During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches according to the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 18 feet to 20 feet of clearance between the traveled way and the bottom of each signal.  For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain 9 feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two lanes with the lane lines separating the lanes.

5.	When the horizontal angle to the side mounted far right signal exceeds 20 degrees, relocate this signal to an overhead location.  Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

a.	With two or more through lanes, center one signal head over each lane.

b.	With one through lane and protected permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

c.	Otherwise, install the relocated signal 8 feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 7 to 9 feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in Subsection 660-3.08 Signal and Lighting Installation Requirements.

When no longer required, salvage original and Department provided equipment according to the Plans and No. 6.  Salvaging or Reusing Electrical Equipment, found in Subsection 660-3.01.  Remove other materials used in the temporary systems from the project.

660-3.10 FALSEWORK LIGHTING.  When required by the Special Provisions, install falsework lighting where vehicular traffic with or without pedestrian traffic crosses through or under structure falsework.

Provide illumination of the portal faces of falsework during the hours from dusk to dawn. Provide illumination of the pavement and pedestrian openings through or under falsework 24 hours a day.

Submit a plan for the proposed lighting installations and do not commence falsework construction until the Engineer has reviewed such plans. The Engineer will make a subsequent review after you place falsework lights in operation.

Falsework lighting equipment remains your property and must be removed from the site of the work upon completion of the project or when directed.

660-3.11 TRAFFIC SIGNAL MODIFICATIONS.  Required work is detailed in the Plan sheets and notes and the following.  Work related to the Traffic Signal Communications System will be paid for separately.

The Contractor will have 10 hours to "changeover" the new controller assembly. Changeover includes but is not limited to: removing the existing controller assembly, replacing with new controller assembly, landing new and existing wires, programming the new controller unit, and bringing the signal back to full functionality.  The 10 hour window will only occur on the days assigned under an approved traffic control plan. The Contractor will be assessed a Traffic Price Adjustment for an unauthorized lane closure according to Subsection 643-3.06. Refer to section 643 for further restrictions.

Traffic control during the changeover will be paid for under section 643 Pay Items.  At a minimum, traffic control will include the following:

- A portable changeable message board in advance of each approach with the message "Traffic Signal Work, New Traffic Pattern Ahead, from 00:00 AM/PM mm/dd/yy to 00:00 AM/PM mm/dd/yy

- A flagger for each approach

Traffic signal modifications are subject to the full Standard Specification for Highway Construction, the Special Provisions and the following:

- Traffic Controller Cabinet:  When a new traffic controller cabinet is called for, ensure legible labeling of all cabinet cables including but not limited to; control, detector, EVP, UPS, interconnect, and telephone. Label detectors and signal heads individually.

- Traffic Signal Heads:  When new traffic signal heads are required, provide with new LED units and new mounting hardware. If new heads are not called for, replace any missing visors or backplates subsidiary to the Traffic Signal Modification Pay Item.

When replacing traffic signal or pedestrian indications conform to Subsections 740-2.14 and 2.15 and maintain brand consistency throughout intersection. When new heads are provided aim heads according to Table 660-2.

- Loops:  When shown in the plans, replace inductive loops including homerun cable and required splice. Loop tests are required per Section 660-3.01.7.

- Conduits:  Unless new conduits are called for reuse existing conduits.  When new conductors are being added to existing conduits, conform to sections 660-3.03, 3.05, and 3.06.

- EVP Components:  When called for in the plans provide EVP components including all cables and mounting hardware. Ensure proper operation of EVP system.

- UPS:  When called for in the plans provide fully functioning UPS system. If no separate UPS item exist, the UPS will be paid for subsidiary to the Traffic Signal Modifications Pay Item.

- Load Center:  When called for in the plans provide fully functioning Load Center. If no separate load center item exists, the load center will be paid for subsidiary to the Traffic Signal Modifications Pay Item.

- Conductors: Reuse existing conductors except where the plans call for new conductors.

Conductors:  Reuse existing conductors except where the plans call for new conductors.

Salvage decommissioned reusable traffic signal equipment, components/materials and deliver to the local Maintenance & Operations station within 72 hours of removal. Refer to section 660-3.01 for delivery locations. Decommissioned components damaged as part of the salvage effort must be replaced with new components at no additional cost.

660-3.12 ARC FLASH HAZARD WARNING.  Label traffic controller cabinets, and other electrical equipment that is likely to require examination, adjustment, servicing, or maintenance while energized, to warn qualified persons of potential electrical arc flash hazards per NEC 110.16.  The labels must meet the requirements in NEC 110.21(B), and must contain the information required in NFPA 70E 130.5(H).

660-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Bored Casing.  By the linear foot along the slope of the bored or jacked casing for the actual length bored or jacked, in place.

Traffic Loop.  By each loop unit, complete and in place, including all conduit, conductors, and other equipment to the nearest junction box.

Traffic Loop Replacement.  By each loop unit damaged during the milling operation, complete and in place, including all conduit, conductors, and other items necessary per this section to replace fully functioning loops.  Work to include splicing of loops to existing lead-in cable.

Relocate Electrolier.  By each complete unit, removed, relocated, reinstalled, and functional.

Temporary Electrolier.  By each electrolier and foundation furnished, installed, and maintained as directed by the Engineer.

Signals and Lighting (Miscellaneous).  Measured in accordance with the directive authorizing the work.

660-5.01 BASIS OF PAYMENT.

Payment Includes labor, equipment, and materials required to provide fully functional traffic signals and lighting systems, permanent and temporary, using new equipment.  Remanufactured or rebuilt equipment will not be permitted.

Subsidiary to each Pay Item including but not limited to (Except when included as a separate Pay Item):

- General construction requirements,

- Bonding and grounding,

- Bored Casings,

- Completing tests,

- Conductors,

- Conduit,

- Dewatering excavations,

- Excavation, trenches in rock or soil, bedding, backfill for foundations, conduits, components,

- Foundations including concrete to complete foundations,

- Junction boxes including adjustment to final grade,

- Labeling conductors,

- Maintaining temporary and existing electrical systems,

- Minor routing changes directed by the Engineer

- Preparing as-builts

- Removal and disposal of existing/new unused foundations, conduit, conductors, and junction boxes,

- Removing, repairing and replacing improvements

- Removal of signs and reinstallations required to install foundations, conduits, and junction boxes,

- Repairing damage to finishes on new equipment

- Salvaging reusable equipment and materials and delivering to the local Maintenance and Operations station including but not limited to existing signal structure. Refer to section 660-3.01 for delivery locations.

- Wiring

21.  Replacing failed equipment, equipment components and repairing failed workmanship.

660 Pay Items do not include:  roadway planing, roadway paving, drainage structures, erosion, sediment and pollution control, signing, striping and pavement markings, traffic control, and components of the traffic signal communication system when included as separate pay items.

Pay Item 660.0001.____Traffic Signal System Complete, (Location).

1.	Signal structures

2.	Traffic controller assemblies including assembly testing and preparation, vehicle and pedestrian indications, detection systems, emergency vehicle preemption systems, PTZ cameras, auxiliary and test equipment, on-site manufacturer assisted start up, and training when called for in the Plans.

3.	Work associated with installing loop detectors and conduit crossings, and any other items except when included in a separate Pay Items such as  saw cutting, asphalt removal, aggregate base course, tack coating, and installing new hot mix asphalt.

4.	Includes salvage of existing signal system components not specified in plans to be reused, when not included as a separate item.

Pay Item 660.0003.____Highway Lighting System Complete, (Location).

- Lighting structures.

- Includes salvage of existing lighting components not specified in plans to be reused, when not included as a separate item

Pay Item 660.2000.____ Temporary Electrolier.

- Work to have plans and materials approved.

- Temporary electrolier including the structures, foundations, and load centers (as needed) and their removal.  Moving the electroliers, assembly and operational installation, removing and replacing, and installing conductors (in conduit or direct bury only).  Furnishing and installing temporary electrical load centers when existing load centers are not available for use.

- Temporary electrolier will be paid on a contingent sum basis at the unit price of $2400/each.  The Engineer does not require a change order/directive for this Pay Item.

Pay Item 660.2008.____ Traffic Loop Replacement.

- Replace loops within the specified depth of planning that are damaged during the planning operation at a rate of $1250 each.  Loops outside the specified depth of planning that are damaged during the planning operation are replaced at no expense to the Department per 202-5.01.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 660.0001.____ | Traffic Signal System Complete, ______ | LS |
| 660.0002.____ | Flashing Beacon System Complete, ______ | LS |
| 660.0003.____ | Highway Lighting System Complete, ______ | LS |
| 660.0004.____ | Sign Illumination System Complete, ______ | LS |
| 660.0005.____ | Structure Illumination System Complete, ______ | LS |
| 660.0007.____ | Temporary Signal System Complete, ______ | LS |
| 660.0008.____ | Temporary Illumination System Complete | LS |
| 660.0009.____ | Bored Casing, ___-Inch Minimum Diameter | LF |
| 660.0011.____ | Traffic Loop | Each |
| 660.0012.____ | Underpass Lighting System Complete | LS |
| 660.0013.____ | Relocate Electrolier | Each |
| 660.2000.____ | Temporary Electrolier, ______ | CS |
| 660.2001.____ | Signal and Lighting Salvage, ______ | LS |
| 660.2002.____ | Pedestrian Lighting, ______ | LS |
| 660.2003.____ | Traffic Signal System Modifications ______ | LS |
| 660.2004.____ | Adjust Junction Box | Each |
| 660.2005.____ | Junction Box, Type __ | Each |
| 660.2008.____ | Traffic Loop Replacement | CS |
| 660.2013.____ | VMS – Radar Speed Sign Relocate | Each |

CFHWY00599

SECTION 661
ELECTRICAL LOAD CENTERS

Special Provisions

661-2.01 MATERIALS.

Add the following:

Precast Concrete Products	Subsection 550-2.03

CR661.3-060121

Add the following:

Anchor Bolts		Section 740-2.02

Load Center.

Replace the 1st and 2nd paragraphs with the following two paragraphs:

NEMA 3R enclosure constructed of .125” thick aluminum, with no external screws, bolts, or nuts.

Shop coat cabinet components with a 2-part urethane paint undercoat and 2-part urethane finish coat. Finish coats must be standard white for removable panels and non-gloss silver-gray, closely matching FSS No. 595 Color No. 36622, for the enclosure.

Equipment List(s) and Drawings.

Replace No. 1. with the following:

1.	Materials on the Qualified Products List:  The Qualified Products List does not apply to the 661 Pay Items.  Provide catalog cuts of materials to the Engineer for review and approval.

3.	Materials Not Requiring Certification:  Replace the 2nd sentence with the following:

Submit these materials for review and approval if included on the Materials Certification List (MCL) or requested by the Engineer.

Add the following materials:

Ground Rods.  Furnish one piece 3/4” diameter by 10 feet long copper clad steel rods.

Ground Rod Clamps.  Furnish one piece bronze clamps with a hex head setscrew that are suitable for direct burial and for use with copper clad ground rods.

CR661.1-123121/CFHWY00599

Grounding Electrode Conductor. Furnish #4 AWG bare copper wire, or size per NEC table 250.66, whichever is larger

CFHWY00599

Meters.  Furnish meter sockets and landing pads rated for 200 Ampere Service.

Photoelectric Controls.

Delete the first sentence and substitute the following:

Use three wire photoelectric controls that directly switch a circuit from one conductor to another.  Furnish two piece photoelectric controls that consist of a plug-in control unit and a locking type receptacle set in a cast aluminum adapter.

1.	Plug-in Control Unit.

Furnish photoelectric control units that consist of a light sensitive element connected directly to a normally closed, single-pole, single-throw, and control relay free of intermediate amplifications.  For highway lighting, use horizontal or zenith type sensing units that:

a.	Operate at voltages between 120 and 277 VAC, 60 Hz,

b.	Handle loads up to 1,800 volt-amperes,

c.	Operate at temperatures from -40 °F to +150 °F,

d.	Consumes less than 10 watts of power,

e.	Feature a 3-prong, EEI-NEMA standard, twist-lock plug,

f.	Turn-on between 1.0 and 5.0 foot-candles and turn-off at light levels between 1.5 and 5.0 times those at turn-on.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices used in the Control of Roadway Lighting.

Screen the photoelectric control units to prevent artificial light from interfering with normal photoelectric control operation.  Extend screens to the top of the control units.  Use 3 inch wide x 0.063 inch thick (min) aluminum meeting ASTM B209, Alloy 3003-H14.

2.	Locking Receptacles.

Furnish twist lock type, phenolic resin receptacles set in one of the following cast-aluminum adapters.

a.	For photoelectric controls installed on signal poles and load centers, furnish a mounting adapter with a threaded connection that fits conduit outlet bodies threaded for 1/2 inch rigid metal conduit, General Electric model MB-PECTL or approved equal.

b.	For photoelectric controls installed atop lighting poles (with mast arms,) furnish a pole top adapter:  equipped with a terminal block, made to slip over the ends of poles 3 1/2 to 4 1/2 inches in outside diameter, and secured by set-screws, General Electric model PTA-PECTL or approved equal.

661-3.01 CONSTRUCTION REQUIREMENTS.

Replace the 11th paragraph with the following:

Install two ground rods at least 8 feet apart at each load center.  Connect the neutral bus to the ground rods with a soft drawn bare copper grounding electrode conductor sized per the NEC, 6 AWG minimum.  Bond non-current carrying metal parts in each load center to the ground bus.  At Type 1 load centers, install one ground rod inside the base, readily accessible though the removable cover, and the second ground rod outside the base.  Route the grounding electrode conductor to the second ground rod through one of the knockouts.

Replace the 12th paragraph with the following:

Install photoelectric controls at the locations indicated. Orient photoelectric control units to face the north sky.  Install a screen to prevent artificial light from interfering with normal photoelectric control operation.

For photoelectric controls installed on load centers, install a Myers hub in a cabinet wall shielded from traffic.  To the hub, attach an assembly that consists of a Type LB conduit body, a length of conduit, and a Type C conduit body.  Fabricate the conduit at least 3 ft long and locate the photoelectric control 1 ft above the top of the load center.  Mount the photoelectric control adapter on the Type C conduit body.  Install a conduit hanger to brace the top of the conduit.

For photoelectric controls installed on signal poles, install a Myers hub in the center of the rain cap.  Attach a Type C conduit body to the hub with a close nipple.  Mount the photoelectric control adapter on the conduit body.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

For photoelectric controls installed on electroliers, install a pole top adapter.  When the photoelectric control is on a lighting standard with a slip base or frangible coupling style base, use an approved breakaway disconnect in the base of the light standard.  Restrain the cable in a similar manner as the illumination cable in the pole base.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

Add the following:

Coordinate new load centers with existing and or new service utilities.

Failed Equipment and Workmanship

For the term of the Contract from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair failed workmanship.

661-5.01 BASIS OF PAYMENT.

Add the following:

The following work is subsidiary to 661 Pay Items:

	All necessary hardware for mounting (shelf angles, rack, shelving, harness, etc.).

	Removing existing load centers being replaced with new load centers, their foundations, and ground rods.

	Payment of fees required by the local authority for electrical inspection(s) and the costs of correcting the deficiencies noted during the inspection(s).

	All work including, but not limited to, contacting and coordinating with the utilities for service; maintenance and usage payments until the Engineer provides the notice of final acceptance.

	Replaced failed equipment, equipment components and repaired failed workmanship.

CR661.1-123121

Special Provisions

Add the following Section:

SECTION 662
FIBER OPTIC SIGNAL INTERCONNECT SYSTEM

662-1.01 DESCRIPTION.  Furnish and install fiber optic signal interconnect system as shown on the Plans along the route indicated or on a route as directed by the Engineer.

662-1.02 INSTRUCTIONS AND GUARANTEES.  One set of maintenance and repair manuals shall be included with each project installation and submitted to the designated traffic signal technician through the Engineer.

No changes or substitutions in these requirements will be acceptable unless authorized in writing.

The supplied conduit shall carry a two-year warranty from the date of project acceptance to be free of defects. The installer shall be fully responsible for the installation of defect free conduit and for the replacement of any conduit found to be defective.

662-2.01 MATERIALS.  Submit materials for review and approval per the requirements of subsection 106-1.05, Certificates of Compliance and subsection 660-2.01, Materials.

662-2.02 POLYETHYLENE DUCT SYSTEM.  Install a high density polyethylene (HDPE) duct system in which to pull the interconnect cable. Unless otherwise noted in the plans install conduit per the requirements of 660-3.03, Conduit.

Unless otherwise specified in the plans, furnish 2-inch HDPE conforming to the requirements of subsection 740-2.06 Electrical Conduit and Fittings.

Furnish fittings used in the duct system such as elbows, etc., made from the same type polyethylene as the duct.  Fuse connections using the manufacturer’s recommended procedure and equipment.

662-2.03 FIBER OPTIC CABLE.  Cable shall be suitable for placement in an underground duct and shall conform to:

	United States Department of Agriculture Rural Utilities Service (RUS) standard 7 CFR 1755.900.

	Department of Agriculture Rural Electrification Administration (REA) Bulletin 1753f-601 (PE-90) dated August 4, 1994, and these specifications.

	National Electrical Code (NEC) Article 770; NFPA 70-National Fire Protection Agency.

- National Electrical Contractors Association (NECA) / Fiber Optic Association (FOA) 301

	Telecommunications Industry Association/Electronic Industries Association (TIA/EIA) FOTP-Fiber-optic Test Procedures.

1. Fibers.

a.	Fiber optic cables shall be loose tube, all-dielectric, non-metallic slotted core with an integral dry water blocking tape and sheath designed for indoor/outdoor installation. Each cable shall be equipped with 6 kink resistant buffer tubes containing 12 optical fibers each. Buffer tubes shall be stranded around a dielectrical anti-buckling central strength member using a reverse oscillation or “SZ” stranding process.

b.	Each buffer tube shall have an inside diameter much larger than total diameter of the fiber it supports.

c.	Fillers are allowed in the cable to achieve cable cross-section symmetry.

d.	All cable fibers shall be usable and shall be sufficiently free of surface imperfections and inclusions to meet or exceed the optical, mechanical, and environmental requirements contained in this specification.

e.	Each optical fiber shall consist of a doped silica core surrounded by a concentric silica cladding.

f.	Fibers shall contain no factory splices.

- Fiber coating shall be a dual-layered, UV cured acrylate applied by the fiber manufacturer.  The coating shall be mechanically or chemically strippable without damaging the fiber.

- Repairs to the fiber coatings are not allowed except as determined by the designated traffic signal technician at designated splice locations.

- Two (polyester or aramid) yarn binders shall be applied contra-helically with sufficient tension to secure each buffer tube layer to the central strength member without crushing the buffer tubes.  The binders shall be non-hygroscopic, non-wicking, and dielectric with low shrinkage.

- Tensile strength shall be provided in the cable by a combination of high tensile strength yarns helically stranded around the cable core.  High tensile strength yarns shall be wrapped helically around the buffer tubes before the application of the outer jacket (sheath).

- Individual buffer tubes and optical fibers shall be distinguishable by means of distinct and recognizable color-coding in accordance with TIA/EIA-598-B, “Optical Fiber Cable Color Coding.”  The colors shall be stable during temperature cycling and not subject to fading or smearing onto each other or into the gel filling material.  Ensure colors do not cause fibers to stick together.

l.	Distinguish each fiber and buffer from others by means of color-coding according to the following:

| 1. Blue | 5. Slate | 9. Yellow |
| --- | --- | --- |
| 2. Orange | 6. White | 10. Violet |
| 3. Green | 7. Red | 11. Rose |
| 4. Brown | 8. Black | 12. Aqua |

- For cables containing more than 12 buffer tubes, use the color code shown above for tubes 1 through 12, and use stripes or tracers in conjunction with the standard color code for tubes 13 through 24.

2.	Jacket.

a.	The outer jacketing (sheath) material shall be applied directly over the high tensile strength yarns.  The minimum nominal jacket thickness shall be 55 mils.

- The outer jacket material shall be a medium density polyethylene (MDPE) conforming to ASTM D1248, Type II, Class C, Category 4 or 5, Grade J4.  The light absorption coefficient, when measured in accordance with ASTM D3349, shall be a minimum of 400 at a wavelength of 375 nanometers.

- The polyethylene jacket (sheath) shall contain carbon black to provide ultra-violet light protection.  The jacket material shall be fungus inert as described in ASTM G21.

- The jacket shall be free of any holes, splits, or blisters.

3.	Cable Features.

a.	The cable shall contain at least one ripcord under the sheath for easy sheath removal.

- The shipping, storage and operating temperature range of the cable shall be –400 F to +1600 F.

- The fiber optic cable shall be capable of withstanding a maximum pulling tension of 600 lbs during installation (short-term loading) and 200 lbs (long term loading) with no damage. Tensions on the cables shall not be exceeded under any circumstances.

4.	Manufacturer.

- All Fiber optic Cable shall be supplied by an ISO9001 certified manufacturer who is regularly engaged in the production of these specifications for fiber optic cable.

- Fiber optic cables shall be manufactured, tested, and prepared for shipping by one manufacturer. That manufacturer shall provide all fiber optic cables and connectors called for on the project.

5.	Cable Markings.

- Markings shall be approximately 1/8-inch (3 mm) nominal height.

- Be clearly legible and distinguishable.

- Made at 2-foot intervals to be used as length markers.

- If initial markings fail to meet marking criteria (i.e., non-legible, incorrect spacing, spelling error, etc.), cables may be remarked to meet criteria.  Cable markings shall include:

- Cable ID

- Sequential numbers in whole foot or meter intervals to determine the length of the cable and amount remaining on the reel.

- Number of fibers

- “SM” (for Single Mode Fiber)

- “ADOT Fiber”

662-2.04 FIBER OPTIC DROP CABLE (PATCH PANEL).  Drop Cable is defined as the assembly or pigtail consisting of fiber optic cable, connectors, protective tubing, fan-outs (if required) and all incidental materials. This is used for connectivity between a fiber trunk cable and field devices (i.e., signal controller, modems etc.).  Drop cables shall be factory assembled.  Drop cables shall be packaged individually within a plastic bag marked clearly with the manufacturer’s part number. Fiber optic drop cables shall be a SM fiber Gator patch Drop cable with LC or SC type as shown on plans Duplex connections manufactured by Fiber Connections Inc. or an approved equal. Pigtail shall be approximately 100 feet in length (30 meters).

Cable design and installation shall meet requirements for outdoor use as described in subsection 662-2.03, Fiber optic Cable.  Optical jackets (3mm), where used, shall be yellow for single mode fibers.  No splices are allowed within the cable length.  Non-connectorized ends shall be suitable for heat fusion splicing as described in subsection 662-3.09, Splices.

Factory testing information of each Fiber optic Drop cable (fully assembled) shall be provided for each connector/fiber. The information shall be provided in test tags attached to individual or paired connector/fiber.

Field testing information of each Fiber optic Drop cable (fully assembled) shall in accordance with subsection 662-3.04, Field Testing and Performance of Fibers.  Documentation of testing shall be in accordance with subsection 662-3.05, Documentation of Testing.

Fiber optic drop cables shall be equipped with:

- At least, twelve (12) optical fibers or as shown on the plans.

- Fiber optic connectors shall be:

a.	Compatible with the equipment being used for fiber strands with preset usage.

b.	In accordance with subsection 662-3.07, Connectorization.

c.	Factory installed unless otherwise allowed by Engineer.

- Drop Cable Fan-out Kits:

a.	heavy-duty Spider design.

b.	Install fan-out kits for all connectorized ends to build up to a 3 mm jacket.

4.	Tubing that is 900 µm or 3 mm fan-out as required by the application.

5.	Buffer tubes shall protected by the cable sheath or fan out kit.  Exposed buffer tubes are not acceptable.

6.	Individual fiber strands shall be protected by aramid fiber tubes.

662-2.05 SINGLE-MODE OPTICAL FIBERS.  Single mode (SM) fibers utilized in the cable shall be fabricated from 100 kpsi proof stress glass and primarily composed of silica which shall provide a matched clad index of refraction (n) profile and the following physical and performance characteristics:

1.	Core Diameter: 8.3µm

2.	Maximum Attenuation: 0.4/0.25 dB/km at 1310/1550 nm, respectively

3.		Maximum Dispersion:  < 3.2 ps/nm-km from 1285 nm to 1330 nm; < 17 ps/nm-km at 1550 nm

4.	Dispersion Wavelength (ZWD): 1301.5 to 1321.5 nm

5.	Zero Dispersion Slope:  0.092 ps/nm2-km

6.	Cladding Diameter: 125 +/- 1.0 µm

7.	Core-to-Cladding Offset (concentricity): < 0.8 µm

8.	Cladding Non-Circularity:  < 1.0 percent

9.	Fiber Coating Diameter:  245 +/- 10  µm

10.	Secondary Coating:  900 µm (as specified for breakout cable/kits, distribution cable, pigtails and patch chords only)

11.	Fiber Colored Diameter:  250 +/- 10 µm nominal

12.	Mode-Field Diameter:  9.3 +/- 0.5 µm at 1310 nm; 10.5 +/- 1 µm at 1550 nm

13.	Attenuation Uniformity:  No point discontinuity greater than 0.10 dB at either 1310nm or 1550nm

14.	Cutoff Wavelength:  <1260 nm

15.	Maximum End-to-End Attenuation per cable length 15 dB.

16.	Maximum cable outside diameter: 0.5-inch

17.	Fiber Polarization Mode Dispersion (PMD): 0.5 ps/km1/2

18.	Proof Test:  All Optical fibers shall be proof tested by fiber manufacturer

19.	Attenuation at Water Peak:  The attenuation at 1383 ± 3 nm shall not exceed 2.1 dB/km.

20.	Numerical Aperture:  0.13

662-2.06 FIBER OPTIC MANHOLES AND VAULTS.

1.	General.

- Shall be spaced at intervals no greater than 2,500 feet (800-1000 feet typical).  In extreme cases where conduit has no bend as permitted by the Engineer, 5,280 feet is allowable (conduit shall be lubricated with no bends).

- Shall be installed at locations where the cumulative, conduit bends, measured from the last manhole/vault, exceed 360 degrees.

- Are not required for change in conduit installation method.

- Shall not be greater than 5 feet in depth as measured from the lid to the base.

- Covers shall meet the Heavy Duty requirements of AASHTO M306, Drainage, Sewer, Utility, and Related Castings.

- Finished grade shall be in accordance with pertinent sections of section 660-3.04, Junction Boxes. Manholes and vaults shall be located in the field to avoid drainage swales. Do not install manholes or vaults within the traveled way or shoulders.

- When communication conduit is located in the same trench as conduit intended for other purposes (i.e., electrical circuits), manholes shall be offset a minimum of 2 feet from the conduit trench.

- A fiber optic cable support assembly shall consist of multiple brackets, racks, and/or rails required to suspend the required surplus cabling and any splice closures for a single vault.  The support assemblies shall be recommended and approved by the manufacturer of the fiber optic cable and splice closure. The support assembly shall be made from or coated weather resistant material such that there is no corrosion of the supports. The support assemblies shall be anchored to the existing wall using stainless steel hardware.  The fiber optic cable support assemblies shall be incidental to the manholes/vaults.

- Void areas between openings and conduit shall be filled with a self-curing caulk that will provide a permanent, flexible rubber seal. The caulk shall be unaffected by sunlight, water, oils, mild acids, alkali, mildew and is non-flammable. The material shall provide a permanent bond between the conduit entering the manhole/vault and the polymer concrete. The caulking shall be gray in color.

- All openings in manhole/vaults shall be machined at the time of fabrication, as shown on the plans, or punch-driven at the time of placement. Openings shall be sized to facilitate conduit called for in the plan. Make core drilled holes in vaults shall not be more than ¼ inch larger than the conduit diameter. Do not “knock out” thin wall sections.

- Manhole/vault walls that receive only one or no conduits shall be provided with at least one 5-3/4 inch diameter knockouts for future multi-duct installation. The knockouts shall be aligned across from each other.

- Provide one electronic ball marker in each vault and manhole in accordance with Section 660-3.04, Junction Boxes.

2.	Manholes.

- All openings in Type 1 manholes shall be cored or blocked out at the time of fabrication, or cored at the time of placement.  Where conduit is terminated in a manhole, the coring shall be no larger than 1/2 inch from each side of conduit.

- Shall be constructed on top of 12 inches of porous backfill material (subsection 703-2.10).

- Shall have a 1-inch-diameter drain hole in the base.

- Proposed manholes shall be fabricated with fiber optic cable support assemblies, as specified herein, and as shown on the plans.  The cost to provide the fiber optic support assemblies shall be incidental to manholes.

- Type M covers are required for manholes when installed within terrace, median or off-roadway areas.  Type K covers are required for manholes when installed in the roadway.

3.	Vaults.

- Shall be 30 x 48 inches and shall have an effective height of 56 inches (one 11-inch tall stackable vault and one 48-inch stackable vault with a 3-inch overlap). The vault shall have a minimum design load of 22,500 pounds and minimum test load of 33,750 pounds.

- Shall be constructed on top of 12 inches of porous backfill material (subsection 703-2.10).

- The vault lid shall have a minimum design load of 22,500 pounds and minimum test load of 33,750 pounds. The vault lid shall have a permanently recessed logo that reads "TRAFFIC.” The vault lid shall have two (2) 1/2-inch x 4-inch pull slots. The lid surface shall have a coefficient of friction of 0.50 in accordance with ASTM C1028.

- The vault and vault lid shall be constructed of the polymer concrete material, "cosmopolite" and be gray in color. The vault lid shall have steel rebar or mesh added to it so the vault can be easily found with a metal detector under heavy snow. The steel rebar and mesh shall be completely enclosed within the lid such that grounding is not required. The added steel shall have 1 in of cover and not add excess weight to the lid.

- Manufacturer approved gasketing to resist water from entering the vault shall be installed between the lid and the top 24-inch-deep stackable vault.

- The vault lid shall be secured to the vault with two 3/8-inch 16 UNC stainless steel pentahead bolts in which to lock the lid and shall include the appropriate stainless steel washers.

662-3.01 CONSTRUCTION REQUIREMENTS.

1.	Fiber optic Cable.  All splicing, testing and terminating of optical fibers shall be performed by a technician in accordance with subsection 662-3.02, Certified Fiber optic Technician.

Physical condition of the cable upon receipt shall be recorded as outlined in subsection 662-3.05, Documentation of Testing.  Cable reel shall be inspected for nails, staples and other materials that might otherwise kink or damage the cable when unreeling.  All fibers should be tested upon receiving cable. The Contractor shall assume full responsibility of cable that is damaged if testing is not performed after receiving cable.

A detailed construction plan and installation procedure shall be submitted and approved by the Engineer before cable installation.  Cable shall only be spliced at designated splice points as specified in the plans.

Before installation, all cables shall be inspected to be free of damage (nail or staple holes, jacket tears, kinks, etc.), material defects, manufacturing defects, and dimensional non-uniformity that would:

- Interfere with the cable installation using accepted cable installation practices.

- Degrade the transmission performance and environmental resistance after installation.

- Inhibit proper connection to interfacing elements.

- Otherwise yield an inferior product.

Take all necessary precautions to protect reeled cable from possible damage while unattended. Exposed cable shall be protected at all times from vehicular and public traffic.  If cable ends are exposed and unattended, cable caps shall be taped onto cable ends to prevent ingress of moisture into the cable.

When cable is installed by pulling, a swivel and woven cable grip designed for fiber optic cable shall be used.  Materials for lubricating shall be utilized when pulling. Cable shall be pulled in one continuous run.  Splicing is not allowed until the entire length of cable is installed.  Cable shall be pulled in multiple runs when 2 or more 90o bends occur in the run. One continuous cable pull shall not contain more than one 90o bend.

Cable installation in conduit (duct) systems shall conform to manufacturer approved methods of jetting or pulling. Cable shall not be kinked or forced abruptly against conduit edge when pulling cable from conduit ends. Cable feed systems (reels, rollers, guide, tubes etc.) shall be used to install or retrieve cable from conduit ends in vaults, manholes, or junction boxes.

Equipment shall be provided to monitor tensile forces on long cable runs. Monitoring equipment shall measure pulling tension as it occurs and record the maximum tension incurred during the pull. Prior to starting the cable installation, provide manufacturer’s documentation to the Engineer indicating the maximum tension (short term loading and long term loading) when pulling the cable during the installation. Maximum limits shall not be exceeded under any circumstances.

Unless cable is assisted by jetting or winching, lengthy cables requiring multiple pulls shall be coiled in a “figure-eight” pattern. Coiled cable will be staged at intermediated access points to avoid twisting of cable. The figure-eight patterns shall be approximately 15 feet in length. Cardboard shims shall be installed between cable layers at the crossover of the “figure eight” to relieve pressure on the cable.  Fiber optic cable lengths greater than 100 ft. shall not be coiled in one continuous direction.

Minimum bend radii (20 x diameter of the cable with loading, 10 x cable diameters without loading) on the cable shall not be exceeding at any time.

Temporary aerial installation methods shall be consistent with manufacturers approved method.

Install tracer wire in all conduits containing fiber optic cable. Pull the tracer wire simultaneously with the fiber optic cable. Where multiple fiber optic cables are required and are pulled in separate conduits placed in the same trench, only one tracer wire is required. Tracer wire splicing is only allowed in vaults or junction boxes. Provide waterproof mechanical splices where a tracer wire splice is required. Pull tracer wire into each controller cabinet foundation with six feet of slack.

Excess fiber cable slack shall be stored in vaults and manholes on hooks in accordance with the plans.  Cable slack shall be neatly coiled around the inside perimeter of manholes and vaults on the fiber optic cable support assembly.  Cable slack shall be supported as to not interfere with access into manholes and vaults.  Excess fiber cable slack shall be provided as follows:

- Approximately 100 feet per manhole and vaults.

- 50 feet per junction box.

- 6 feet per controller cabinet.

2.	Vaults.  Vaults shall not be placed near drainage collection areas or where vehicle traffic is anticipated.  To the extent possible, vaults shall be placed so that they are accessible by service vehicles driving close to them.

Fiber optic cable support assembly shall be mounted as per vault manufacturer recommendations.  Mounting equipment for support assembly shall not fully penetrate the vaults in order to prevent water intrusion.

Where applicable, conduits shall be terminated in vaults to allow for proper grounding and bonding of metallic conduit. Multi-duct conduit termination kits shall terminate at vaults inside wall (or slightly into the vaults interior) to the extent possible.

Conduit, conduit terminations, and caulking shall be allowed to fully cure as per the manufacture’s specification before backfilling vault.  Openings required to install special or directional conduit shall be sealed with manufacturer approved termination kit.

Keep vault covered unless pulling conductors.

3.	Polyethylene Conduit.  Install polyethylene conduits at 36 inches below finished grade in trenches separate from those used to install traffic signal and highway lighting systems.

Keep ends of conduit covered unless pulling conductors.

Conduit shall be installed in one continuous run between access points.

Conduit shall be installed as linear as possible so as to maximize pulling distances dictated by fiber optic tension requirements. Bends in conduits shall be minimized to the extent possible.

Directional changes in continuous conduit runs shall not exceed 90°. Manholes, junction boxes, or vaults shall be provided where 90°directional changes are exceeded.

Required bends, sweeps, fittings, and parts necessary to connect the conduit to vaults, manholes, and junction boxes shall be subsidiary and will not be paid for separately.

Flexible bend sections are not allowed.

Conduit bending radii shall not exceed the minimum-bending radius as dictated by fiber optic cable requirements.

Where lubrication has not been provided in existing conduit, conduits shall be lubricated according to cable manufacturer recommended procedures.  Lubrication, when required shall be suitable to avoid long-term cable jacket damage.

Conduit ends shall be protected at all times from migration of foreign materials and rodents during and after shipment and during installation.  Pre-lubricated conduit with exposed ends will be rejected. Where provided, non-lubricated conduits left unprotected shall be cleaned before cable installation.

Where pull tape has not been pre-installed in conduit by manufacturer, install a pre-lubricated flat pull tape rated for 1,000 lbs. or greater. Where conduit is supplied with pre-installed pull tape do not remove pull tape for any purposes other than fiber optic pulls.

Special termination kits shall be provided by the conduit manufacturer for terminating the conduit in manholes and vaults. The kits shall seal ducts from contamination, rodents, and flooding. Kits shall be designed to fit the number and size of cable(s) within the conduit and shall allow cable entry and exit within vaults or manholes without inducing stress on the fiber optic cable or damaging cable jacket.

Terminate all conduit entering vaults or manholes 3 inches past the inside walls of vaults or manholes.

Backfill requirements shall be in accordance with Section 204.

Bury a continuous strip of 4 mils thick, 6 inch wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a orange background. Legend shall read “Buried Fiber optic Cable” or similar.

All sharp objects (rocks, debris, etc.) shall be removed from the conduit trench before backfilling. The first 6 inches of backfill shall be free of rocks exceeding 1 inch maximum dimension.

Use care during compaction operations to prevent damage to junction boxes and conduits.  Remove and replace items damaged during the backfill and compaction operations per section 105-1.11.

Install above ground markers at 400-foot intervals and at each vault.  Markers shall be orange flexible delineators reading “Fiber optic Interconnect System” (or similar).

662-3.02 CERTIFIED FIBER OPTIC TECHNICIAN.  The Fiber optic Technician shall have attended and successfully completed at least one four-day "Installation of Fiber optic Products School." This school shall be conducted by a major manufacturer of fiber optic products and encompasses all aspects of fiber optic technician certification.

Employ only technicians demonstrating a minimum of two years work experience with the splicing, termination, and testing of fiber optic cable.

The approved technician shall provide evidence of completed courses within one week before the beginning of construction.  The Engineer reserves the right to revoke the approval of any technician not demonstrating the skill and knowledge to perform at accepted industry standards or to the quality required in these specifications.

662-3.03 TESTING AND PERFORMANCE BY MANUFACTURER.  All outdoor cable installations shall meet or exceed requirements of the Fiber optic Test Procedure (FOTP) criteria referenced in RUS 7 CFR 1755.9 and Bulletin 1753f-601 (PE-90) and these specifications.

Following specifications shall apply to the appropriate Fiber optic Test Procedures (FOTP):

1.	TIA-455-3-A, FOTP-3 “Procedure to Measure Temperature Cycling Effects on Optical Fibers, Optical Cable, and Other Passive Fiber Optic Components”:  The average change in attenuation at extreme operational temperatures (-400 F to +1600 F) shall not exceed 0.05 dB/km at 1,550 nm for single-mode fiber.  The magnitude of the maximum attenuation change of each individual fiber shall not be greater than 0.15 dB/km at 1,550 nm.

2.	TIA-45-82-B, FOTP-82, “Fluid Penetration Test for Fluid-Blocked Fiber-optic Cable.”  When a one-meter static head or equivalent continuous pressure is applied at one end of one-meter length of un-aged cable for 24 hours, no water shall leak through the open cable end.  When a one-meter static head or equivalent continuous pressure is applied at one end of one-meter length of aged cable of one hour, no water shall leak through the open cable end.  The aging cycle is defined as exposing the cable to 850C for 168 hours and two cycles of –400C to +700C with cable held at these temperatures for 24 hours.  At the end of this cycle, the cable will be decreased to +230C and held for 24 hours. The water penetration test is completed at the end of the 24 hours hold period.

3.	TIA/EIA-455-81-B, FOTP-81, “Compound Flow (Drip) Test for Filled Fiber-optic Cable”:  The cable shall exhibit no flow (drip or leak) of filling and/or flooding material at +650C.

4.	TIA/EIA-455-41-A, FOTP-41, “Compressive Loading Resistance of Fiber-optic Cables”:  Ten percent of the fibers shall not experience a magnitude of attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The magnitude of the attenuation change shall be within the repeatability of the measurement system for the remaining 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  No fibers shall exhibit a measurable change in attenuation after test load is removed.

5.	TIA/EIA-455-104-A, FOTP-104, “Fiber-optic Cable Cyclic Flexing Test.”  Change in attenuation shall not exceed 0.1 dB at 1550 nm for single mode fiber.  The magnitude of the attenuation change shall be within the repeatability of the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable jacket shall not exhibit evidence of cracking or splitting at the completion of the test.

6.	TIA/EIA-455-25-C FOTP-25, “Repeated Impact Testing of Fiber-optic Cables and Cable Assemblies.”  The magnitude of the attenuation change shall be within the repeatability of the measurement of 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable jacket shall not exhibit evidence of cracking or splitting at the completion of the test.

7.  TIA-455-33-A FOTP-33, “Fiber-optic Cable Tensile Loading and Bending Test.”  While subjected to a minimum load of 600 lbf, the cable sample shall be able to withstand a twist of 360 degrees in less than 3 meters of length.  The magnitude of the attenuation change shall be within the repeatability for the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable shall not experience a measurable increase in attenuation when subjected to the rated residual tensile load, 200 lbf.

8.	TIA/EIA-455-85-A FOTP-85, “Fiber-optic Cable Twist Test”:  The magnitude of the attenuation change shall be within the repeatability for the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The average increase in attenuation for the fibers shall be <0.40 dB at 1300 nm.  The cable jacket will exhibit no cracking or splitting under a 5x magnification after completion of test.

9.	TIA/EIA-455-181 FOTP-181, “Lightning Damage Susceptibility Test for Optic Cables with Metallic Components.”

10.	TIA/EIA-455-37-A FOTP-37, “Low or High Temperature Bend Test for Fiber-optic Cable”.

11.	TIA/EIA-455-98, FOTP-98-A, “Fiber-optic Cable External Freezing Test”.

662-3.04 FIELD TESTING AND PERFORMANCE OF FIBERS.  All testing of optical fibers shall be performed by a Certified Technician as described in subsection 662-3.02, Certified Fiber optic Technician.

The Contractor shall schedule the date, time, and location of any tests required by this specification with the Engineer and designated traffic signal technician at least 72 hours before performing the tests.  The designated traffic signal technician and the Engineer, or designee, shall be present when the tests are conducted.  The Certified Technician shall demonstrate clearly how the tests are being performed and shall be made available to discuss testing strategies with designated traffic signal technician and the Engineer.

Tests shall be conducted using standard operating procedures as defined by the manufacturer of the test equipment.

The following tests shall be conducted before the cable is deactivated by designated traffic signal technician and after the cable has been installed, spliced and connectorized. Test results shall be submitted in accordance with subsection 662-3.05, Documentation of Testing.  Tests shall be performed before any permanent equipment connections.  All fibers shall be tests for continuity, events above 0.05 dB and total attenuation of the cable.  If the fiber optic cable installed is connected to an existing fiber optic cable, perform installation tests the installed cable and all existing fibers to which it is spliced or connected:

1.	End-to-end OTDR (Optical Time Domain Reflectometer) Testing. This test shall be conducted to identify attenuation associated with each fiber. Traces shall be provided for each operational wavelength for the type of fiber in the system to indicate attenuations and their locations.

A Certified Technician utilizing an OTDR and Optical Source/Power Meter shall conduct the tests after installation. The Technician shall conduct the test according to the standard operating procedure as defined by the manufacturer of the test equipment.

To eliminate or shift the “dead zone,” either a factory patch chord or “fiber launch box” of length greater than the dead zone shall be used.

Measurement shall be conducted for 1310 nm and 1550 nm for single mode fiber.

2.	Attenuation Test.  All fiber links shall be tested with a standard power-meter test and all attenuation shall be documented. For every fiber installed or connected to under this Contract, perform end to-end attenuation test.

For the test, use a calibrated optical source and power meter using the standard three-stage procedure.  Determine acceptable link attenuation by the cumulative value of standard losses based on length, number, and type of splices and connectors.

Provide test results of the fiber optic cable that demonstrate the dB/km loss does not exceed +3 percent of the factory test or 1 percent of the cables published production loss.  The Engineer may elect to allow bi-directional averaging of OTDR testing due to splice loss core alignments.  Fiber optic cable loss limits shall be in accordance with the following:

a.	No event shall exceed 0.10 dB.  If any event is above 0.10 dB, repair or replace that event location.

b.	Total dB loss of a cable fiber less events shall not exceed +3 percent of the factory test or 1 percent of the manufacturer’s published production loss at 1310 and 1550 nm.  Cable fiber loss shall not exceed Maximum Attenuation Limits as defined in subsection, “Single Mode Fiber optic Cable.”

Cable Fiber Loss (dB)  =   Total Loss (dB)  - ∑ events (dB)

Cable Fiber Loss (dB/km) =  Cable Fiber Loss (dB)

Cable Fiber Length (km)

c.	Where total or event losses exceed these specifications, replace or repair that cable run and assume all expenses, both labor and materials. Elevated attenuation due to exceeding pulling tension during installation will require replacement of cable at the Contractor’s expense.

d.	Fusion splice losses shall not exceed 0.10 dB per fiber.  Mechanical splices, where allowed, shall not exceed 0.30 dB.

e.	Each connection, after factory assembled, shall not exceed the maximum loss of 0.50 dB (typical loss is 0.25dB) and optical return reflective loss of <-0.45dB. A connection consists of two mated connectors.

f.	If event losses exceed these specifications, event locations shall be replaced or repaired without additional cost reimbursement for expenses.

g.	If total loss exceeds these specifications, Fiber optic cable shall be replaced or repaired without reimbursement for expenses.

h.	All fibers within the cable shall be tested and proven usable in accordance with these specifications.

662-3.05 DOCUMENTATION OF TESTING.  Upon completion of the field test, the Contractor shall provide three copies of all documentation to the Engineer.  Except for standard bound materials, documentation shall be neatly bound in 8.5” x 11” (size A4) documentation in logical groupings.  Bindings shall be of either the 3-ring or plastic slide-ring type.  Permanently and appropriately label each such bound grouping of documentation. The Engineer shall be provided with two paper copies of all documentation and a copy of the test result in .pdf to designated traffic personnel. Use labeling scheme established in 662-3.07.2.

Documentation from manufacturer shall include manufacturer data of cable and fiber including:

- Optical performance (OTDR) including dB/km loss measured at 1310 and 1550 nm for single mode.

- Manufacturer’s name

- Date of manufacture

- Index of Refraction

- Cable ID

- Connector losses and bandwidth/dispersion data

Documentation of field testing shall include a map. This map shall show:

- Cable part numbers

- Manufacturer

- Cable length markings, including slack length markings at all vaults and junction boxes.

- As-built cable routing

- Location of splice points and hardware at each splice point location (see below under testing also).

Documentation shall include the information below for end-to-end testing, splice loss measurements, OTDR traces.

The documentation shall be neatly tabulated for each field test and shall include the following:

- Cable and Fiber Identification.

- Manufacturer

- Cable ID

- Cable Type

- Fiber ID (include tube and fiber color)

- Cable Location – begin and end point

- Operator Name

- Date and Time

- Date of installation

- Fiber Count

2.	Setup Parameters.

- Wavelength

- Pulse Width (OTDR)

- Refractory index (OTDR)

- Jumper and/or Launch Box Length

- Range (OTDR)

- Scale (OTDR)

3.	Test Results.

a.	OTDR Test:

- Total Fiber Trace (mile)

- Splice Loss/Gain

- Measured Length (Cable Marking)

- Provide traces on a CD to Engineer

- Total Length (OTDR) (mile)

- Events ≥ 0.05 dB. Trace vertical scale shall allow easy identification of 0.05dB loss.

- Backscatter

- End-to-End Attenuation Test:

- Length

- Number and type of splices and connectors

- Link Attenuation

Fiber optic cable test results shall demonstrate that dB/km losses do not exceed limits in accordance with subsection, 662-3.04 Field Testing and Performance of Fibers.

662-3.06 PACKAGING.  Fiber optic cables shall be shipped on wooden reels.  The diameter of the drum shall be a least 20 times the diameter of the cable.  The following information shall be either stenciled on the reel or on a weatherproof tag firmly attached to the reel or a combination of both in order to trace the manufacturing history of the cable:

- Optical Cable

- Number of Fibers

- Date cable was tested

- Non-armored

- Year of cable manufacture

- Name of cable manufacturer

- Gross weight

- Part Number

- Handling Instructions

- Arrow indicating cable wind direction

Cable data sheets shall be supplied to Engineer containing the following:

- Manufacturer Name

- Cable ID Number and fiber type

- Factory Order Number

- Cable Length

- Factory measured attenuation (each fiber)

- Index of Refraction

- Bandwidth Specification (where applicable

Sufficient cable length, in addition to the quantities shown on the plan, shall be provided for testing.  Both ends of the cable shall be available for testing.  Pack one continuous length of fiber optic cable per reel; maximum overage shall not exceed 10 percent unless approved by The Engineer.  Compensation will not be granted for overage or excess cable needed for testing and installation methods.

Package the cable for shipping to prevent the cable from coming loose in transit.  Secure the outer and inner end of the cable.  Cover the reel with thermal wrap to protect the cable.  Apply end seals to each end of the cable to prevent moisture and from entering the cable.

Include the manufacturers test documentation with each reel. This documentation indicates the attenuation of each cable fiber in dB/km (dB/ft), measured at 1310 and 1550 nm for single mode fiber.

662-3.07 CONNECTORIZATION.

1.	Connectors.  This subsection shall consist of furnishing and installing connectors (in-line or terminated ends), attenuators as required in the plans, or as required for working fiber optic system. All connectors shall be installed by a Certified Technician as described in this specification.

Hybrid adaptors shall not be used to connect two different connectors.  Hybrid jumpers with different connectors at each end of cable shall interface with equipment or cables with different connectors where needed.

Connectors shall be LC or SC connectors for single mode fibers.  FC and ST connectors are allowed only where compatibility with equipment is required for fibers with a preset usage. These must be approved by the Engineer.

Connectors shall be installed with ceramic ferrules.  The fibers shall be secured within ferrule with epoxy, heat set or air dried, as specified by the manufacturer.  Machine polished mating faces shall be provided.  Install connectors per manufacturer application and recommendations, including proper termination to the outer tubing (900 micron, 3 mm fan-out) as required by the application.  Connectors shall be rated for operating temperatures of -400 F to 1600 F.  Connectors shall be factory-installed for all applications except where approved by the Engineer.

If connections are made, connectors shall be cleaned once before the first connection and once every time thereafter before reconnection. Connectors shall be cleaned according to manufacturers recommended practice.

Connector losses shall not exceed limits as described in subsection 662-3.04, Field Testing and Performance of Fibers.  Repeatability of keyed connectors shall not exceed 0.2 dB.

Boots shall be provided for durable cable strain relief.

Dust caps shall be provided and installed at all times when connector is not in use.

2.	Patch Panels.  Terminate and secure the number of fibers splices specified by the engineer from one buffer tube in the cable to a fiber optic drop cable located in the traffic signal controller cabinet that the fiber is shown to enter in the plans. Each patch panel will connect to only one fiber cable.

Ensure the fibers used throughout the system are matched correctly to allow for communications from one cabinet to the next in the system.

Ensure that the patch is compatible with the fiber optic cable/cables being terminated and color-coded to match the optical fiber color scheme.

All patch connectors shall be clearly labeled including the cable route, buffer and color. The panel shall have the number of LC type or SC type connectors as indicated in the plans or as directed by the Engineer.

All installed patch panels shall include documentation regarding the identification, route, buffer and color of each patch panel connector at that location.

Place at least one copy of this information alongside the installed equipment or in the controller cabinet door pouch.

662-3.08 ATTENUATORS.  Attenuators shall be provided at no extra payment to the Contractor to achieve the desirable signal loss. Attenuators shall only be installed on the receiving end closest to the originating transmission (typically closest to the Traffic Signal Management Center).

Connecting ends shall be compatible to connectors described in subsection 662-3.07, Connectorization.

662-3.09 SPLICES.  Two weeks before the start of the fiber optic cabling installation, the Contractor shall submit the following:

- Proposed locations of the mainline spliced points for review by the Engineer designated traffic Traffic personnel.

- Proposed process to be used for splicing including procedure.

- Cleave tool and specific fusion splicer to be used.

1.	All Splices.

a.	Splicing and termination of optical fibers shall be performed by a Certified Technician as described in 662-3.02 Certified Fiber optic Technician.

b.	Splicing shall only be allowed in areas as designated on the plans or as approved by the Engineer.

c.	Splices and stripped cable shall be housed by a fiber splice closure (FCS) in designated locations shown on the plans.

d.	Cable ends involved in splicing shall match colors of the fibers and buffer tubes to the extent possible.

e.	No stresses shall be placed on the fibers before or after the splice is completed.

f.	Splice loss shall not exceed limits as described in subsection 662-3.04, Field Testing and Performance of Fibers

g.	Fan-out kits are required for splices to multiple fibers in the buffer tubes for single mode fiber.

- Splices shall be located in the center of the slack cable in manholes or vaults.

i. 	All splices shall be fusion splices protected with heat shrink sealant (RTV fusion splices). 60 mm heat shrink protectors shall be used. Mechanical splices are not allowed.

- End-To-End Splices.

a.	End-to-end splicing shall be performed as per manufacturer instructions for the supplied splice closure units.

b.	End-to-end fusion splicing shall be conducted for any disturbed fibers within the disturbed buffer tube(s).  Remaining buffer tube(s) that are not required for splicing shall be undisturbed and protected in the Splice Closure.

c.	End-to-end fusion splices shall be used on mainline splices for all fibers (72 fibers typical) within the fiber optic cable where designated in the plans.

3.	Fusion Splices.

a.	All splices to be fusion splices unless otherwise indicated on plans.

- Fusion splices shall be made with a portable fusion splicer, capable of AC or internal battery-powered operation.  The unit shall be able to splice fibers specified herein with 250 micrometer coating and 900 micrometer coating with little or no modification in the field.  The fusion splicer shall be capable of full battery recharge in an eight-hour charging period.

4. 	Drop Fiber Splices.

a.	Drop fiber splices (12 fiber typical) and drop cables (12-fibers typical) shall be used for connectivity between a primary mainline fiber optic cable (72-count typical) and field devices (i.e., traffic signal controller cabinet) as identified in the plans.

b.	Drop fiber splices shall consist of breaking out the required buffer tube(s) from the fiber optic trunk cable (12-count typical) and fusion splicing the appropriate number of fibers to the fiber optic drop cable (12 fibers typical). Remaining undisturbed fibers, if any, shall be protected in the splice tray.

- Drop fiber splice shall be performed for each device location at locations shown on the plans.  Splicing shall be performed as per manufacturer’s recommended procedure approved by the Engineer.

662-3.10 SPLICE CLOSURES.  Fiber optic splice closures (FSC) shall be installed in the locations on the plans at designated splice locations. Closures shall contain splice trays or organizers that contain the splices.

Before installation, the Contractor shall provide certification from the manufacturer that the splice closures conform to the specifications and test procedures.

1.	Closures.

a.	Splice closures shall be designed for use under the most severe conditions such as moisture, vibration, impact, cable stress, and flex temperature extremes. This will be demonstrated by successfully passing factory test procedures and these specifications.  The closure shall prevent the intrusion of water without the use of encapsulates.

b.	Closure re-entry and subsequent reassemble shall not require specialized tools or equipment; these operations shall not require the use of additional parts.

c.	Splice closures shall provide housing and storage for all splices, stripped cable, and undisturbed buffer tubes.  All splice closures shall provide protection and strain relief to optical fibers. Splice closures shall be suitable to handle straight, butt or branch splices.

d.	Splice closures requiring greater than 48 splices shall provide for the following requirements:

1)	6-inch diameter by 22-inch length.

2)	One, six-cable entry end plate.

3)	One blank end plate.

4)	All endplates shall be 3-section, pre-molded, and suitable for use with Coyote closures.

5)	Required accessories to complete splice.

6)	One future cable entry kit for each splice closure.

e.	Closures shall be provided with external valve pressurization ports.  Closure shells shall be glass-filled high-density thermoplastic that effectively withstands corrosion; high impact and freeze thaw stresses.

f.	Closure endplates shall be interchangeable with each size of closure available from the closure supplier.

g.	Where additional access is required into an existing splice closure, replace the existing endplate with an endplate suitable for the task.

h.	Splice closures shall accept up to six cables in a butt configuration, and 12 for in-line configuration without special adaptors.

i.	Closure shall contain a permanent neoprene gasket seal.

j.	All closures, including closing hardware, shall be from the same supplier.

k.	External Shrader valve pressurization port shall be supplied.

l.	The splice closure shall be designed and equipped with the necessary mounting hardware to be attached to the side of the manhole or vault, and to be suspended with sufficient clearance at each end for acceptable cable bends.

m.	All cables shall be properly dressed and affixed to rails or racks within the manhole or vault.  No cables or closures will be permitted to lie on the floor.

n.	Fiber optic cables shall be restrained within the splice enclosure such that there is no discernible tensile force on the optical fiber.

o.	The splice closure shall have provisions for storing fiber splices in an orderly manner, mountings for splice organizer assemblies and space for excess or unspliced fiber.  Splice organizers shall be re-enterable and re-sealable.

p.	The closure shall be capable of accommodating a minimum of 2 splice organizer trays, which shall accept mechanical, fusion, or multi-fiber array splices.

q.	Splice closures shall contain a basket allowing fiber buffer tube storage of exposed buffer tubes. The splice case shall be UL rated.

r.	The closure shall be installed according to the manufacturer’s recommended guidelines.

2.	Splice Tray.

a.	One splice tray shall be designed to hold a minimum of 12 mechanical splices.  A second splice tray (for Fiber optic Drop Cable splicing) shall be designed to hold a minimum of 12 fusion splices.  All other splice trays provided in the closure shall be designed to hold fusion splices of 12 (typical) up to 36 splices. Total number of splices supported shall be 96 splices.

b.	Splice trays shall allow for optical fiber storage as recommended by the manufacturer.  The splice closure shall have provisions for controlling the fiber bend radius (1.5 inches typical) to a minimum as required by the manufacturer.

662-3.11 SPLICE CLOSURES -FACTORY TESTING REQUIREMENTS.  The construction and testing of the fiber optic splices and splice closures shall comply with all applicable industry standards including Electronic Industry Standards (EIA/TIA), ANSI and ASTM standards.

Splice closures shall meet the following test requirements:

1.	Compression Test.  The closure shall not deform more than 10 percent in its largest cross-sectional dimension. When 	subjected to a uniformly distributed load of 300 lbf (1335 N) at temperatures between 00F and 1000F (–180C and +380C). The test shall be performed after stabilizing at the required temperature for a minimum of 2 hours. It shall consist of placing an assembled closure between two flat paralleled surfaces, with the longest closure dimension parallel to the surfaces.  The weight shall be placed on the upper surface 	for a minimum of 15 minutes. The measurement shall then be taken with weight in place.

2.   Impact Test.  The assembled closure shall be capable of withstanding an impact of 21 ft-lbf (28 N-m) at 	temperatures of 100F and 1000F (-120C and 380C).  The test shall be performed after stabilizing the closure at the required temperature for a minimum of 2 hours.  The test fixture shall consist of a 20 lb (9 kg) cylindrical steel impacting head with a 2-inch (5 cm) spherical radius at the point where it contacts the closure.  It shall be dropped from a height of 12 inches (30 cm). The closure shall not exhibit any cracks or fractures to the housing that would preclude it from passing the water immersion test. There shall be no permanent deformation to the original diameter or characteristic vertical dimension by more than 5 percent.

3.	Cable Gripping and Sealing Testing. The cable gripping and sealing hardware shall not cause an increase in fiber attenuation in excess of 0.05 dB/fiber @ 1550 nm when attached to the cables and the closure assembly. The test shall consist of measurements from six fibers, from each buffer tube or channel, or randomly selected in the case of a single fiber bundle. The measurements shall be taken from the test fibers, before and after assembly. This will determine the effects of the cable gripping and sealing hardware on the optical transmission of the fibers.

4.	Vibrations Test. The fiber splice organizers and splice retaining hardware shall be tested per EIA standard FOTP-11, 	Test condition I. The individual fibers shall not show an increase in attenuation in excess of 0.1 dB/fiber.

5.	Water Immersion Test.  The closure shall be capable of preventing a 10-ft (3-meter) waterhead from intruding into the splice compartment for a period of 7 days. Testing of splice closure is to be accomplished by the placing the closure into a pressure vessel and filling the vessel with tap water to cover the closure.  Apply continuous pressure to the vessel and maintain a hydrostatic head equivalent to 10 ft (3 m) on the closure and cable.  This process shall be continued for 7 days.  Remove the closure and open to check for the presence of water.  Any intrusion of water into the compartment containing the splices constitutes a failure.

6.	Certification.  It is the responsibility of the Contractor to insure that all of the above tests have been performed by either the manufacturer, or an independent testing laboratory, and the appropriate documentation has 	been submitted to the Engineer.  Manufacturer certification is necessary for the model of closure supplied. It is not necessary to subject each supplied closure to the actual tests described herein.

662-3.12 WARRANTY AND MAINTENANCE.  Manufacturer’s support (customary warranties) period shall be provided for all equipment and materials furnished and installed as part of the fiber optic system. This includes end equipment such as modems, panels, switches and etc. Manufacturer’s and Contractor’s warranties or guarantees shall be continuous throughout their intended duration and be stated that they are subject to transfer.

662-4.01 METHOD OF MEASUREMENT.  The Engineer will measure all work required to install a complete signal interconnect system as lump sum.

662-5.01 BASIS OF PAYMENT.  The contract lump sum price for 662.2001.0000 pay item(s) shall be full compensation for furnishing all work and materials required to complete the work specified.  Terminal blocks for the interconnect cable shall be paid under item 660.0001.0000, Traffic Signal System Complete.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 662.2000.____ | Signal Interconnect | LF |
| 662.2001.____ | Signal Interconnect, Fiber | LS |
| 662.2002.____ | Fiber Optic Interconnect | LF |
| 662.2005.____ | Fiber Optic Interconnect | LS |

CFHWY00599

Special Provisions

Add the following Section:

SECTION 669
AUTOMATED TRAFFIC RECORDERS

669-1.01   DESCRIPTION. This work shall consist of reconstruction, refurbishing, and installation of Automated Traffic Recorder (ATR) stations.

ATR consists of inductive loop and piezoelectric sensors connected to a traffic counter.  In each traffic lane, two inductive loops are separated by a specific travel distance and buried beneath the pavement. Two piezoelectric sensors are located adjacent each inductive loop, embedded in the pavement surface. Lead wires run in underground conduit from the sensors to a type CBA2 cabinet located at the side of the road. Inside the type CBA2 cabinet, the lead wires connect to the traffic counter. The traffic counter detects the presence and speed of passing vehicles from inductive loop signals. The traffic counter detects axle number and center-to-center axle spacing from piezoelectric signals. Presence, speed and axle passage information is processed by the traffic counter to classify the number and type of vehicles, which is stored for later retrieval. ATRs are operated and maintained by personnel of the Highway Data Section (HDS); main office located at 2200 E. 42nd Ave., Anchorage, phone (907) 269-0876.

ATR stations may be equipped with a Temperature Data Probe (TDP), which consists of temperature sensors connected to a datalogger. Sampled conditions may include air temperature, pavement profile temperatures and subgrade profile temperatures. Temperature sensors send voltage signals to the datalogger. Sensor voltage levels are processed by the datalogger to yield temperature information, which is stored for later retrieval.

The locations of traffic detection sensors and cabinets, shown on the Plans are approximate and the Engineer shall establish the exact locations in the field after consultation with the DOT/PF HDS.

669-1.02 REGULATIONS AND CODE.  Use materials and workmanship that conforms to the standards of the Underwriter's Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

Use electrical equipment that conforms to the standards of the National Electrical Manufacturer's Association, where applicable.

669-2.01 MATERIALS. Unless otherwise stated, provide new materials that meet the following requirements:

1.	Wiring.  Subsection 660-3.05, Wiring.  Use single wire conductors and cables that have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, insulation type-letter designation, conductor size, voltage rating and the number of conductors if a cable.   Home run label all wires and cables in each junction box and cabinet; for example, W1SLA (for wire) and GaSLA (for cable) as shown on the Plans.

2.	Conduit.  Subsection 660-3.03, Conduit. Use galvanized rigid metal for conduits, except for PVC conduit forming the inductive loops. Provide grounding bushings with plastic-sleeves to minimize the potential for insulation damage during wire pulls.

3.	Junction Boxes.  Subsection 660-3.04, Junction Boxes.  Label the covers of all junction boxes used for loops or sensor wires 'TRAFFIC'.  Label the covers of all junction boxes used to provide electrical service to ATR installations 'ELECTRIC’.  Keep junction boxes for 120V/240V electrical service completely separate from junction boxes containing loop or sensor wiring

4.	Terminal Blocks.  Mount Terminal Blocks to match orientation of the roadway.  Use terminal blocks with nickel, silver or  cadmium plated brass binder-head screw terminals.   Use barrier type terminal blocks rated 600 VAC at 20 Amps, sized for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips.

5.	Presence Loops.  Use UL listed IMSA specification #51-5-1984 single conductor PVC nylon with tube jacket, type THHN, #14 AWG conductors for detector presence loops.

Use twisted pairs of 18 AWG stranded tinned copper wire for multiple pair loop lead-in cable. Each twisted pair shall have its own 20AWG tinned copper drain wire.  An aluminum foil shield shall surround each individual bundle of twisted pair and drain wire. Multiple pair loop lead-in cable shall have an overall PVC or PE outer jacket.

6.	Electrical Load Centers. Use NEMA Type 3R Electrical Load Centers and provide a 120/240V

100 amp single-phase, three-wire-circuit electrical service.

7.	Style CBA1 Cabinets.  Cabinets shall meet or exceed a UL 50, NEMA Type 3R rating.  CBA1 cabinet shall be a Hoffman #131JF, 20X17X15 or equal.  Construct the cabinet and hinged door from 5052-H32 or better unpainted sheet aluminum alloy with a minimum thickness of 1/8 inch and a smooth grain finish on the exterior.  Corbin #2 Key Lock.  One (1) adjustable shelf.  Drip Shield.  Interior has four (4) instruct channels for installing adjustable shelves.  Grounding points included on body and door.  Door latching mechanism is a single point PowerGlide padlocking handly system which secures the door in the middle. A door stay is included at the botton of the door with three positions:  90, 120, and 180 degrees.  Ensure that welds are neatly formed and free of cracks, blowholes and other irregularities. Ensure inside and outside edges of the cabinet are free of burrs. Design the cabinet with a sloped top to prevent the accumulation of water on its top surface.

8.	Style CBA2 Cabinets. Cabinets shall meet or exceed a NEMA Type 3R rating.  Cabinets shall be third party certified as an assembly. Style CBA2 cabinets shall meet the following requirements:

a.	Cabinet Dimensions.   Unless otherwise shown on the Plans, the cabinet shall be 48 inches high, 27 inches wide, and 16 inches deep.

b.	Cabinet Construction. Construct the cabinet and door from 5052-H32 or better unpainted sheet aluminum alloy with a minimum thickness of 1/8 inch and a smooth grain finish on the exterior. Ensure that welds are neatly formed and free of cracks, blowholes and other irregularities.  Ensure inside and outside edges of the cabinet are free of burrs.  Design the cabinet with a sloped top to prevent the accumulation of water on its top surface.

c.	Door.  Use double flanged door opening on four sides to prevent dirt and liquids from entering the enclosure when the door is opened.  Provide a door restraint to prevent door movement in windy conditions. Provide a cabinet door that encompasses at least 80% of the cabinet frontal surface area and is hinged on the right side when facing the cabinet. Furnish the door with a gasket that satisfies the physical properties found in UL508 table

21.1 and forms a weather tight seal between the cabinet and the door.  Use a hinge that is continuous and made of stainless steel or at least 2.2 mm thick aluminum.  Securely weld the hinge along a quarter, or more, of its length or bolt the cabinet using stainless steel bolts and non-slip nuts.

d.	Latch/Lock.  Use a 3 point draw roller type latching mechanism.  Use either stainless steel or cadmium plated, Type II Class 1 or better center catch and pushrods. Use rollers with a minimum diameter of ¾ inch and made of nylon.   Furnish a stainless steel operating handle with a ¾ inch shank.  Use a Corbin #2 lock keyed lock that matches existing HDS cabinets. Furnish two keys with each lock.

e.	Ventilation.  Provide ventilation using louvered vents in the front door with a removable air filter.  Ensure louvers satisfy the NEMA rod entry test for 3R ventilated cabinets. Provide filters that cover the vents and are held firmly in place with bottom and top brackets and a spring-loaded top clamp.  Vent exhaust air out between the top of the cabinet and the door.

f.	Shelves.  Mount adjustable equipment shelves on "C" factory mounting channels inside

of cabinet and support them on both sides.  Mount 2 vertical channels on both sides of the cabinet and on the back, for a total of 6 inside each CBA2 cabinet. Construct shelves from 5052-H32 or better sheet aluminum alloy with a minimum thickness of 1/8 inch. Provide a shelf with a minimum depth of 10 inches. Ensure that shelves are adjustable to within 4 inches of the bottom and to within 8 inches of the top of the cabinet.

g.	Keyboard Tray. Mount a retractable tray as shown in the Plans.

h.	Circuit Breaker Panel.  Ensure the circuit breaker panel conforms to the UL67 and NEMA PB1 standards.   Use a MLO, single-phase, 3 wire configuration circuit breaker panel rated at 70 Amp (minimum) 120/240 Volts, in a NEMA Type 2 enclosure with separate neutral and ground buses.  Unless shown otherwise in the Plans, or described herein, provide two 20 amp single pole type circuit breakers with a minimum short-circuit interrupting rating of 10,000 AIC.  Circuit breaker #1 will serve the utility and equipment receptacles,  and  circuit  breaker  #2  will  serve  the  thermostatically controlled  outlet, cooling fan, and cabinet light.

i.	Transient Voltage Surge Protection. Provide transient voltage surge protection, rated at a minimum 500 Volts at 3000 Amps integral to the circuit breaker panel, or integral to each individual circuit breaker.

j.	Interior Light. Provide a fluorescent, 120-volt single-tube lamp interior light fixture rated at

13 watts minimum with ballast that will start the lamp at temperatures of 0°F.  Provide a single pole, illuminated toggle switch, mounted inside of the cabinet door to control the light.

k.	Cooling Fan.   Provide a thermostatically controlled fan in the top of the cabinet that operates at a settable high temperature limit and exhausts air through a filtered and hooded vent at the top front of the cabinet.  Set an integral thermostat at a temperature lower than the thermostat noted in Item  “m” below so that the  auxiliary thermostat controls the fan, and not any integral thermostat.

l.	Thermostatically Controlled  Outlet.    Ensure  that  a  thermostatically controlled  single duplex outlet operates at a settable low temperature limit.

m.	Thermostats.  Provide remote bulb-type thermostats with SPDT contacts, rated for 16 amps @ 120 VAC for combined motor and resistive loads, for the thermostatically controlled outlet and cooling fan.  Use Tradeline T6031A1029 (equal or better), White- Rogers, Johnson Controls, or Sunne brand thermostats.  Ensure the thermostats for the “Thermostatically Controlled Outlet” have a contact that closes on lowering temperature and set at 50°F. Provide a thermostat for the “Cooling Fan” that has a contact that closes on rising temperature and set at 90°F. Mount sensing bulbs as shown on the Plans.

n.	Conduit, Raceway and Layup.  Provide EMT, liquid tight metal flex or metal clad conduit for wiring in 120V equipment including circuit breaker panel boards, lights, vent fans, and power receptacles.   Terminate other low voltage wiring on terminal blocks and neatly train within the cabinet using wiring duct or ties.

o.	Certification. The  Cabinet  Assembly consists  of  the  cabinet  itself  and  high  voltage (greater than 24 volts) components that are permanently installed, including the circuit breaker panel, receptacles, light and fan as shown on the Plans or described herein. Obtain certification that the cabinet and associated permanently installed equipment, as a unit, complies with recognized applicable national standards through an authorized local or national testing agency or fabrication shop that complies with ANSI Z34.1-1987 “Third- Party Certification Programs for Products, Processes, and Services”, including but not limited to; Electrical Testing Laboratories (ETL), Underwriters Laboratories (UL), Canadian Standards Association (CSA), Electro Test Incorporated (ETI), or other certified testing agency recognized by the Labor Standards & Safety Division of the State of Alaska Department of Labor.

- Temperature Data Probe

  - Ground Temperature Probe. Provide the following:  Campbell Scientific temperature probe model 105E-L with 150 feet of cable length

  - Ambient Air Temperature Sensor. Provide the following:  Campbell Scientific temperature probe 107-L with 50 feet of cable length

  - Temperature Data Probe.  Provide the following:  Campbell Scientific model CS230-L50meters-S15-E0.  
Cable length=50meters
# of External Probes=0
# of Internal Probes=15
Measurement Depth Starting Point=0

  - Datalogger.  Provide the following:  Campbell Scientific CR1000-XT-SW-NC Part 16130-24.  XT -55C to +85C, SW Standard 3yr Warranty, NC No Calibration Cert.

  - Solar Radiation Shield. Provide the following:  Campbell Scientific Model 41303-5A 6 Plate Radiation Shield UV-Stabilized white thermoplastic plates, aluminum mounting bracket, white powder coated stainless-steel U-bolt clamp.

  - Heater. Portable heater rated 1200-1500 watts @ 120 VAC, fan forced, cord connected electric heater. Broan Model 6201 or equal.  Single stage thematically controlled heater connection power cord, rated 16 at 120 VAC. 30oF to 100oF range. Sure-stat Cat

#T118P or equal.

10.	Automated Volume and Classification Count Equipment.

- Housing: Weather resistant cast aluminum (powder coat) with carrying handle.

- Weight:  Less than 15lbs.

- Size:  7inx13.5inx6in

- Display:  20-Character by 4-Line

- Inputs:  16 Piezo/8 Loop inputs

- Data Storage: 2GB-16 GB; User-set memory rollover

- Study Periods: 1-60 minute intervals

- Classifciation: FHWA 15-category classification or a user set classification table

- Communications:  RS232 serial comms from 300 to 115K baud with 9 Pin female port, USB capable

- Power:  Up to 31 days per charge; On/Off switch

11.	Piezoelectric Sensor, Class II. Locate 10 foot long piezoelectric sensor as shown in the plans.

- Center Core. 16 gauge, flat, braided, silver plated copper wire.

- Piezoelectric Material. Highly compressed piezoelectric copolymer, P(VDF-TrFE).

- Outer Sheath. 0.406 mm thick brass, CDA-260, ASTM B 587-88.

- Final Dimensions. ¼ inch wide x 1/16 inch thick; ±0.13 mm.

- Insulation. Insulation resistance between core and shield: > 500M ohms.

- Piezoelectric Coefficient: ≥ 20 pC/N – nominal.

- Passive Signal Cable. RG 58 type with an underground/direct burial rated outer jacket.

The OD of the cable is 1/5 inch. The nominal capacitance of the cable is 89 pF/m.

CFHWY00599

12.	Precast Concrete Products	Subsection 550-2.03

CR669-070121

669-3.01 CONSTRUCTION REQUIREMENTS.

1.   Wiring.

  - Referenced Requirements. Subsection 660-3.05, Wiring.

  - Termination. Terminate unused pairs at junction boxes within splices.   Terminate unused pairs in terminal blocks at cabinets.  Terminate and solder conductors, including unused spares to “spade” type terminal lugs at terminal blocks.

  - Relief. Provide at least 2 feet of slack cable for wiring in each junction box and at least 6 feet of slack cable available in the equipment cabinet before the terminal block.

  - Labeling. Label wiring in junction boxes and at terminal blocks.

2.   Conduit.

  - Referenced Requirements. Subsection 660-3.03, Conduit, or as indicated on the Plans.

b. 	Pull Cords. Leave nylon pull cords in all conduits larger than 1 inch and in spare conduits.

c.	Bushings.  Ensure that plastic or plastic-sleeved bushings are in place before wire pulls are performed.

3.   Junction Boxes.

              - Referenced Requirements. Subsection 660-3.04, Junction Boxes, or as indicated on the Plans.

              - Voltage Limitation.   Junction boxes used for ATR installations shall not contain wiring of systems at or greater than 24 V or conduits carrying wiring of systems at or greater than 24 V.

4.   Terminal Blocks.

a.  	Terminal Block Placement. Mount terminal blocks within cabinets so that terminals are easily accessible from the front of the cabinet.

b.   	Labeling. Clearly label terminal blocks and wire pairs on the block.

c.		Termination. Terminate and solder conductors, including unused spares to "spade" type terminal lugs

5.   Presence Loops.

a.  	Placement Design Adherence.  The Plans are not schematics; installation of the presence loops shall closely conform to the location and layout of conduit runs shown in the Plans. The contractor shall notify the Project Engineer 14 days prior to saw cutting the pavement for approval of the site layout.

b.   	Presence Loop Dimensions.   Unless otherwise noted on the plans, form presence loops using four turns of wire, making 6 feet square with a tolerance of ± 1 inch.

c.		Presence  Loop  Dimensions  for  On-Ramps  and  Off-Ramps.  Form  presence  loops  in On-Ramps and Off-Ramps using four turns of wire, making a rectangular 8 feet wide and 6 inch long with a tolerance of ± 1 inch.

d.   	Lead-in Conduit. Place lead-in conduits straight and perpendicular to the centerline of the road from the edge of pavement to the presence loops.

e.   	Presence Loop Alignment. Center presence detector loops in the traffic lane with a tolerance of ± 1 inch.

f.	Presence Loops in Asphalt.

I.	Loop Placement. Locate presence loops 16 feet from leading edge to leading edge unless otherwise noted on the Plans with a tolerance of ± 1 inch.   Align presence loops in adjacent lanes within a tolerance of ± 1 inch.

II.	Compaction tests.   Compaction test requirements are at the discretion of the

Engineer.

6.   Piezoelectric Sensors.

a.	Manufacturer's  Recommendations:  Install  piezoelectric  sensors  according  to  AVC equipment and piezoelectric sensor manufacturer's recommendations.  The piezoelectric sensor manufacturer’s representative or a piezoelectric sensor manufacturer-certified installation technician must observe and approve piezoelectric sensor installations.

b.	Placement Design Adherence. The Plans are not schematics; install the piezoelectric sensors as close as possible to the locations and layouts of conduit runs shown in the Plans.

c.	Saw cut Requirement. Install piezoelectric sensors in saw cut slots in final pavement. "Block outs" are not allowed.

  - Coaxial Cable. Run coaxial cables to the equipment cabinet without splices.  Terminate on the specified terminal block, with at least 6 feet of slack cable available in the equipment cabinet before the terminal block.

  - Lead-in Conduit. Install lead-in conduits from edge of pavement to the piezoelectric sensors straight and perpendicular to the centerline of the road.  Install and cap lead-in conduits for piezoelectric sensors at the sensor end with tape or sealant before paving. Extend lead-in conduits beyond the edge of the pavement.  Completing lead-in conduit runs to junction boxes and cabinets may be done before or after paving.

  - Piezoelectric Sensor Placement. Center each piezoelectric sensor in the travel lanes between sensors adjoining inductive loops unless otherwise noted on the Plans or directed by the Engineer. Install piezoelectric sensors with a tolerance of ± 1 inch.

  - Piezoelectric Sensors in  New Asphalt.	Install piezoelectric sensors in  new  asphalt pavement only after three days of normal traffic has passed over the final paving.

- Cabinets

  - Cabinet Placement and Orientation.  Install cabinets out of the Clear Zone with the doors facing away from the road. Unless the orientation is otherwise noted on the plans.

  - Conduit Entry.  Install conduit entries for above-ground enclosure through the bottom of the enclosure.  No conduit runs shall be cut through the sides or top of above-ground enclosure.

  - Style CBA2 Cabinets Mounting. Mount style CBA2 cabinets on 4 inch GRMC or DN100 galvanized pipe and support with reinforced concrete foundations as shown on the Plans.

- Utilities

  - Electrical. Provide and install the Load Center as required per the Plans, specifications and the requirements of the appropriate Electrical Utility.  Provide and install wiring from the load center to the equipment in the cabinet.  Request inspection of the Load Center by the Department of Labor, Division of Mechanical Inspection (DOL/DMI). After approval of the load center by the DOL/DMI, inform the Engineer as to when electrical service is needed at the load center, with sufficient time to enable the HDS to schedule the installation with the Electrical Utility before commissioning of the equipment.  The HDS will make arrangements in writing with the Electrical Utility to establish billing accounts. The Electrical Utility will provide service to the Load Center upon request of the Engineer.

  - Asphalt Pavement Roughness. No transverse seams, joints or roughness within 50 feet of any inductive loops placed in asphalt pavement section is allowed. Test the finished surface of the asphalt with a straightedge 10 feet long.  Ensure that the surface does not vary more than ¼ inch from the lower edge of the straightedge within 50 feet of sensors at the ATR installations.  At the Engineer’s discretion, run an inertial profiler or a profilograph equipped with a chart recorder down each wheelpath of each lane for a distance of 50 feet before and after each ATR installation.  HDS will supply the profilograph for the Contractor’s personnel to operate. Ensure that the asphalt surface as recorded by the chart recorder does not vary more than ¼ inch in 10 feet.

  - Field Inspection.  Notify the Engineer in writing a minimum of 3 working days in advance (excluding Saturday, Sunday and State or Federal Holidays) before installing conduit/wiring, inductive loops, bending plate equipment, piezoelectric cable, axle sensors, and cabinets. The Engineer shall be present to approve the installation before backfill placement and paving.   At the Contractor's expense, correct and allow the Engineer to re-inspect unacceptable installations for completeness prior to backfill placement and paving.   The Contractor shall be required to excavate, remove, and replace all installations backfilled or paved without prior approval by the Engineer at the Contractor’s expense.

  - Communications. Provide and install the phone line from the NID service box to the cabinet and connect to modem to ensure DSL connection.  At ATR locations to be provisioned with cellular modems, provide Sierra Wireless RV50 configured for AT&T as the service provider.

CFHWY00599

9.   Failed Equipment and Workmanship.  For the term of the Contract, from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair workmanship.

CR669-070121/CFHWY00599

669-3.02 ACCEPTANCE TESTING. Perform acceptance testing on ATR installations.

1.	General  Tests.	Perform  tests  for  the  ATR  installations  according  to  subsection  660-3.01, Installation Details.

2.	AVC Acceptance Tests.

a.	Scope and Governance.  In addition to the General Tests, perform Acceptance Tests on AVC installations.   AVC acceptance tests govern acceptance or rejection of the AVC installation.

b.	Manufacturer Participation.    Observe acceptance tests  and  assist  the  AVC  counter manufacturer’s representative, or an AVC counter manufacturer-certified installation technician.

c.	Highway Data Section Participation. Before beginning AVC Acceptance Tests, notify the HDS.  Notify in writing, through the Engineer, a minimum of 3 working days before proposed  testing  (excluding  Saturday,  Sunday  and  State  or   Federal  Holidays). Notification includes descriptions of the proposed test vehicles.  A representative of the HDS approves descriptions of the proposed test vehicles in writing before testing and be on-site during final acceptance testing. Provide a tabulated listing of each vehicle’s gross weight and measured axle spacing to the HDS representative before testing.  The HDS representative must approve scheduling of data sampling and testing for each lane.

d.	Results Certification.   The Highway Data Manager or designated representative shall certify in writing when the installation has met the accuracy requirements of the acceptance tests.

e.	Acceptance Test Procedure. Perform the Acceptance Tests as follows:

Acquire a set of test data for the AVC sensor array.   Obtain test data by passing test vehicles over the AVC sensors in each lane.  Test data consists of 10 valid samples per lane, for each of 3 test vehicles.  Test data samples will include FHWA class designation and computed axle spacing for each sensor pass.

To be considered valid, obtain sample data under the following conditions:

The test vehicle must maintain good lane discipline while traversing the entire sensor array.

I.	The test vehicle must maintain a constant speed, between 40 mph and the maximum speed limit, while traversing the entire sensor array.

II.	Acquire data for a particular lane using the same group of 3 test vehicles.

III.	Sample data from successive sensor passes of each test vehicle.  Data may not be omitted or included out of order for any 10 samples.

IV.	Sensor passes for the 3 classes of vehicles may be intermixed.

V.	Sensor passes for multiple lanes may be acquired simultaneously.

f.	Accuracy Requirements.	The Automated Vehicle Classifier must meet the following requirements separately in each lane:

I.	The  AVC  system  correctly assigns  FHWA class  designation for  9  out  of  10 successive sensor passes of each vehicle class.

II.  	The  AVC  system  computes  axle  spacing  to  within  6  inches  of  the  actual measurements, for 9 out of 10 successive sensor passes of each vehicle class.

g.	Test Vehicles. Provide, and make arrangements for; test vehicles and drivers as needed for the acceptance testing.

The group of three test vehicles shall consist of one each of the following:

I. 	A two axle, six wheel, single unit vehicle (FHWA Class 5)

II.	A three axle, ten wheel, single unit vehicle (FHWA Class 6)

III.	A  five  axle,  eighteen  wheel,  single  trailer  vehicle  (FHWA Class  9),  with high-cube-rated (HCR) trailer

h.	Class 5 Vehicles. Class 5 vehicles shall meet the following requirements: I.	Spacing between steering and drive axles of 14 feet to 23 feet

II.	Weight on the steering axle between 2,200 lb and 12,000 lb.

III.	Weight on the driving axle between 7,000 lbs and 18,000 lb.

i.	Class 6 Vehicles. Class 6 vehicles shall meet the following requirements:

I.	Spacing between steering axle and the drive axle group of 13 feet to 23 feet

II.	Spacing between the drive axles of 4 feet to 6 feet

III.	Weight on the steering axle between 6,000 lb. and 12,000 lb

IV.	Weight on the drive axle group between 20,000 lb. and 37,500 lb... j.	Class 9 Vehicles. Class 9 vehicles shall meet the following requirements:

I.	Spacing between the steering axle and the drive axle group of 13 feet to 23 feet

II.	Spacing between the drive axles of 4 feet to 6 feet

III.	Spacing between the drive axle group and the trailer axle group of 25 feet to 45 feet

IV.	Spacing between the trailer axles of 4 feet to 6 feet

V.	Weight on the steering axle between 6,000 lb. and 12,000 lb.

VI.	Weight on the trailer axle group between.20,000 lb. and.37,500 lb

k.	Vehicle Loading. Ensure that three-test vehicles are loaded with non-shifting material to a minimum of 50% of legal load during testing.

l.	Tire Inflation. Ensure that tires on the three-test vehicles are inflated to recommended pressures during testing.

m.	Weighing Method.  The gross weight of each test vehicle and the weight of each test vehicle’s axle groups shall be determined by weighing on a static scale at a scale house operated by the State of Alaska Department of Commerce, Division of Weights and Measures.

An axle group is defined as any two axles whose centers are within 8 feet of each other
The Class 5 and Class 6 test vehicles each have two axle groups.  The Class 9 single trailer test vehicle has three axle groups.

669-3.05 DELIVERABLES.   Submit deliverables to the HDS before final approval of the work or as otherwise called for herein.

1.	Materials Submittal.

a.	Format  and  Contents.    Provide  a  Materials  Submittal  of  proposed  equipment  and materials for the ATR installations. The Materials Submittal shall consist of three collated copies of an equipment and materials portfolio.  Each identical portfolio shall contain information of sufficient detail to determine the suitability of the equipment and materials proposed.

b.	Table of Contents.   Each portfolio shall include a table of contents listing each item's intended uses, item description, product name, manufacturer, model or part number and reference to associated information within the portfolio.

c.	Reference Drawings. The Materials Submittal shall include a detailed shop drawing of each equipment cabinet showing the location of mounted components.

d.	Delivery Interval. Deliver Materials Submittal for review and approval of the Highway Data

Supervisor within thirty days following award of the Contract.

e.	Liability.  The  State  of  Alaska  will  not  be  liable  for  any  materials  purchased, labor performed, equipment used or delay to the work before equipment and materials have been reviewed and approved.

2.	As-Built Plans.

a.	Prepare four complete sets of as-built plans, which will be current with the construction.

These as-built plans shall detail construction changes made to the ATR design and include the following information on the appropriate sheets:

- Location and depth of inductive loops, piezo sensors, conduit runs and scales.

- Locations of equipment cabinets and junction boxes.

III.	Station and offset of junction boxes

b.	Present three sets of as-built plans to the Engineer, and affix one set to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation in a waterproof, clear plastic holder.

c.	Redlines of full size construction plans will be acceptable as-builts.

3.   Photographs.

a.	Provide   digital   photographic   prints   CD   format   CD   ROMs   documenting   sensor installations.

b.	Deliver photographs and CD ROMs organized in one or more white colored, D-ring style,

3 ring binders with clear insert overlays on fronts and spines.  CD ROMs will be placed in

CD storage sheets inside the binders.

c.	The photographs shall show the inductive loops and conduit in place before covering with gravel  and  pavement  for  asphalt  pavement  sites,  or  before  covering  with  epoxy compound for concrete pavement sites. The photographs shall include:

I.	Two or more overall views of each ATR installation showing placement of the inductive loops.

II.	One or more views of each loop showing the loop and the conduit to the nearest junction box.

III.	One or more views of each piezo sensor conduit showing the coaxial cable, saw cut, and conduit to the nearest junction box

IV.	One or more views of each temperature sensor showing the lead cables, saw cut, and conduit to the nearest junction box

4.	Test Results. Written or printed copies of the final results of tests, signed by the Contractor, shall be provided to the Engineer before acceptance of the Automated Traffic Recorder Installation.

5.	Manuals.  Provide to the Highway Data Manager installation, repair, and operation manuals for

Automated Traffic Recording equipment supplied by the Contractor.

6.	Materials.

a.	Provide to the Highway Data Manager any ATR equipment, sensors, and epoxy grout remaining after installation.

b.	Palletize the Deliverable Materials.

c.	Group the contents of each pallet by like items.

d.	Attach to each pallet a sealed plastic pouch containing complete copies of Material

Safety Data Sheets that apply to the contents of that pallet.

e.	Provide an itemized list of Deliverable Materials. For each item, the list shall detail:

I.	Item description: including nature of the item, brand name, manufacturer name, model number, type number and serial number.

II.	Item condition

III.	Item quantity

f.	Provide complete copies of Material Safety Data Sheets that apply to the Deliverable Materials.  Attach Material Safety Data Sheets after the last page of the Deliverable Materials list.

669-4.01 METHOD OF MEASUREMENT. Section 109. Automated Traffic Recorder sites will be measured Lump Sum.

669-5.01 BASIS OF PAYMENT.

The Contract unit price for Automated Traffic Recorder installations shall be full compensation for furnishing all equipment, labor and subsidiary materials required for completion of a site for which there is no specific item in the Plans is subsidiary to the 669 item. This includes but is not limited to:

•	backfill materials,

•	seeding,

•	topsoil,

•	removal of structures and obstructions,

•	structural excavation for conduits and minor structures,

•	work in support of utilities as specified in Subsection 105-1.06,

•	as-built plans,

•	providing the manufacturer’s representative,

•	acceptance testing,

•	j-boxes,

•	CBA cabinets,

•	portable heater and cooling fan,

•	tilt poles,

•	rigid conduit,

•	load centers,

•	demolition of CBA cabinet foundations and associated utility lines/conduits/appurtenances,

•	loops,

•	piezoelectric sensors,

•	radar sensors,

•	TDP's,

•	surface temperature probes,

•	ambient air sensors, and

•	other ATR equipment or work as shown on the plans.

Wet cutting with a concrete saw for piezoelectric sensor installations are subsidiary to 669 items.

CFHWY00599

	Replacing failed equipment, equipment components and repairing failed workmanship is subsidiary to 669 Pay Items.

CR669-070121

WITHHOLDING.  To ensure full compliance under this Section, twenty percent (20%) of the billings for each 669 item shall be withheld until written acceptance of the site has been received from the Highway Data Manager.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 669.2003.____ | Automated Traffic Recorder | LS |

CFHWY00599

SECTION 670
TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Pavement Markings as shown on the Plans and as directed.

Pavement Marking Type:  Methyl Methacrylate (MMA)

670-2.01 MATERIALS.  Replace the material reference,

“Methyl Methacrylate Markings 					Subsection 712-2.17”, with,

Methyl Methacrylate Pavement Markings				Subsection 712-2.17

Add the following:

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.  Replace No. 4 with the following:

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

SURFACE APPLIED

Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 60 mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of 60 mils.

INLAID

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

- Longitudinal Markings.

- Knik-Goose Bay Road and Palmer-Wasilla Hwy:

Groove the pavement to a depth of 250 mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 250 mils.

- All other roads:

Groove the pavement to a depth of 125 mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 125 mils.

- Transverse and Symbol Markings:

(a)	Knik-Goose Bay Road and Palmer-Wasilla Hwy:

Groove the area for inlaid markings to a depth of 250 mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 250 mils.

- All other roads:

Groove the area for inlaid markings to a depth of 125 mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 125 mils.

- Gore Markings:

Knik-Goose Bay Road and Palmer-Wasilla Hwy:

Groove the area for inlaid markings to a depth of 250 mils. Apply markings for diagonal and chevron-shaped gore to yield a thickness of 250 mils

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01)

670-3.04 PAVEMENT MARKING REMOVAL.

Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Replace Subsection 670-3.06 with the following:

670-3.06 TOLERANCE FOR LANE STRIPING.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measured from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete No. 2.

Replace No. 3 with the following:

3.	Each.  Pavement markings using letters, numbers, and arrows will be measured on a unit basis with each separate word or symbol constituting a unit.  Railroad Markings will be measured by the complete unit shown for each lane of travel.

Replace No. 4 with the following:

4.	Foot Basis.  Longitudinal pavement markings, transverse, and gore markings, surface applied or inlaid will be measured by the linear foot of 4 inch wide line.  Wider striping will be measured in multiples of 4 inches.

670-5.01 BASIS OF PAYMENT.  Add the following:

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with pavement markings are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Temporary pavement markings and removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

Add the following Pay Items:

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 670.2000____ | MMA Pavement Markings | LS |
| 670.2003.____ | MMA Pavement Markings, Longitudinal Surface Applied | LF |
| 670.2004.____ | MMA Pavement Markings, Symbols and Arrow(s) Surface Applied | Each |
| 670.2005.____ | MMA Pavement Markings, Transverse and Gore Surface Applied | LF |
| 670.2006.____ | MMA Pavement Markings, Longitudinal Inlaid | LF |
| 670.2007.____ | MMA Pavement Markings, Symbols and Arrow(s) Inlaid | Each |
| 670.2008.____ | MMA Pavement Markings, Transverse and Gore Inlaid | LF |

CR670.1-110812R/CFHWY00599

Special Provision

Add the following Section:

SECTION 682
UTILITY POTHOLING

682-1.01 DESCRIPTION.  Expose subsurface utilities using a vacuum-extract truck.  Record the location of the utility(s). Backfill the pothole and dispose of waste materials.

682-2.01 MATERIALS.

Backfill Material:	Aggregate Base Course, Grading D-1	Section 703

Asphalt Patch Material:	Hot Mix Asphalt Type II, Class B	Section 401

682-3.01 CONSTRUCTION.  Submit the utility potholing schedule to the Engineer and utility companies not less than 7 days before starting potholing.

Deliver the vacuum-extract truck to the job-site with the debris tank empty.

Expose the subsurface utilities.  Log the as-built information, subsection 682-3.02.  Backfill the pothole immediately after the Engineer accepts the logged data.  Backfill the first 6 inch lift using the excavated material, compact the material.  Backfill the balance of the pothole using Aggregate Base Course, Grading D-1, compact the material.  In paved areas, use Hot Mix Asphalt Type II, Class B to patch over the pothole, match the thickness of the surrounding pavement.

Dispose of excavations off-site.  Before beginning potholing, provide to the Engineer a certificate, signed by the owner or owner's representative, identifying the disposal site and acceptance of the project potholing excavations.

Utilities damaged by the potholing operation require the Engineer to be immediately notified.  The Contractor is responsible for the repairs and the associated costs.  Contact and coordinate repairs with the utility owner.

682-3.02 AS-BUILTS.  Create a utility pothole log, as-built, recording for each pothole: the date of potholing operation, utility type and size, station, offset, elevation, groundwater, and other pertinent data.  Survey the utility location using the project horizontal and vertical control; comply with the requirements of Section 642.  Submit the completed log to the Engineer within two working days following the completion of the pothole excavation.

682-4.01 METHOD OF MEASUREMENT.  The pay unit, contingent sum, is measured by the hour of work performed.

682-5.01 BASIS OF PAYMENT.  Pay Item No. 682.2000.____ is paid at $450/hour for the work to pothole; expose the utility(s), backfill the hole, patch disturbed pavement and dispose of excavations.  The paid time includes the work; labor, and the fully operated vacuum truck or combination of vacuum truck and other Engineer approved equipment engaged in potholing at the area(s) identified in the Plans and/or identified by the Engineer.  The paid time includes the time to empty the vacuum truck of excavation material, including the travel time, from this project only, to a certified disposal site.

Travel time to and from the project, idle time, maintenance and repairs (labor, material and time) are incidental and not included in the measured time.

As-built, utility pothole log, per subsection 682-3.02, will be paid under Section 642.

Potholes for the Contractor's information and potholes not accepted by the Engineer will not be paid for by the Department.

Payment will be made under:

| pay item |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 682.2000.____ | Vac-Truck Pothole | CS |

CR682-010114R

Special Provisions

Add the following Section:

SECTION 688
UTILITY SUPPORT

688-1.01 DESCRIPTION.  Coordinate the project work with all utility work by others in accordance with subsection 105-1.06 and these Specifications.  Utility work by others includes all installation, service connections and disconnections.  The Contractor shall perform utility support work including scheduling work by others; erosion, sediment, and pollution control; excavation, backfill, surveying, and traffic maintenance.

688-1.02 UTILITY NOTIFICATION AND CONTACT INFORMATION.  Make initial contact with each Utility Company through the Engineer.  Contact information for the Utilities:

City of Wasilla

| Name of Contact: | Danielle Bischoff |
| --- | --- |
| Address: | 290 E. Herning Avenue Wasilla, Alaska 99654 |
| Phone: | (907) 373-9018 |
| Email: | dbischoff@ci.wasilla.ak.us |

ENSTAR Natural Gas Company

| Name of Contact: | Jake Stephl |
| --- | --- |
| Address: | 401 E. International Airport Road Anchorage, AK 99518-1219 |
| Phone: | (907) 334-7915 (907) 831-0267 |
| Email: | jake.stephl@enstarnaturalgas.com |
| Name of Contact: | Lucas Portera |
| Address: | 401 E. International Airport Road Anchorage, AK 99518-1219 |
| Phone: | (907) 334-7794 (423) 298-5701 |
| Email: | lucas.portera@enstarnaturalgas.com |

GCI Communication Corp

| Name of Contact: | Mitch Stivers |
| --- | --- |
| Address: | 5151 Fairbanks Street Anchorage, AK 99503 |
| Phone: | (907) 868-6215 (907) 727-9945 |
| Email: | mstivers@gci.com |
| Name of Contact: | Brian Parker |
| Address: | 5151 Fairbanks Street Anchorage, AK 99503 |
| Phone: | (907) 868-1059 (907) 232-4354 |
| Email: | bparker@gci.com |

Matanuska Electric Association, Inc

| Name of Contact: | Taylor Roth |
| --- | --- |
| Address: | 163 E. Industrial Way Palmer, Alaska 99645-2929 |
| Phone: | (907) 761-9571 (907) 707-4285 |
| Email: | taylor.roth@mea.coop |

Matanuska Telecom Association, Inc

| Name of Contact: | Robbie Nash |
| --- | --- |
| Address: | 1740 South Chugach Street Palmer, Alaska 99645 |
| Phone: | (907) 761-2704 (907) 355-1034 |
| Email: | rnash@mtasolutions.com |

688-1.03 SCHEDULING AND COORDINATING THE UTILITY WORK BY OTHERS.  Prior to commencing utility related groundbreaking activities, develop a detailed schedule for the complete installation of all utility work.  Develop and maintain the schedule based on information provided by the utility.  Develop and furnish a project schedule identifying utility support work in accordance with subsections 105-1.06 and 108-1.03.  Incorporate the schedule into the CPM schedule and update as required.

Work with the Engineer and utilities to develop two-week look ahead schedules.  The Contractor’s Superintendent, or Engineer approved designee, is the singular point of contact for coordinating scheduling with the Engineer.  Submit the two-week look ahead schedules to the Engineer on a weekly basis and in sufficient detail to plan supplemental needs for traffic maintenance, stormwater management, surveying support, and/or other activities authorized by the Engineer though directive.

Provide the support work and coordination with the utilities in a manner that limits utility outages and outage durations.  Schedule longer utility outages during non-peak hours and anticipate performing support activities during these times which may include night and weekend work.

Each utility has determined the timeframes that their utility relocation work is anticipated to take, see section 651 Control of Work – Supplemental Requirements for these timeframes.  These general work timeframes are subject to change.

688-1.04 RESERVED

688-2.01 RESERVED.

CONSTRUCTION REQUIREMENTS

653-3.01 WORK BY UTILITIES.  The utilities will perform installation of permanent utilities and removal or abandonment of utilities that are decommissioned in accordance with the Utility Agreements and dispositions completed between the Department and each utility.

653-3.02 WORK BY CONTRACTOR SUPPORTING THE UTILITIES.  Provide support to facilitate work by the utility company, including an approved representative, on site during utility work by others.

688-4.01 METHOD OF MEASUREMENT.  Utility support is measured in accordance with the directive authorizing the work.

688-5.01 BASIS OF PAYMENT.  Payment is for work, authorized by directive, for time and materials to support utility work by others, 109-1.05.

Erosion, Sediment, and Pollution Control work in support of utilities is paid for under Section 641.

Surveying in support of utilities will be paid as follows:

a.	Subsidiary to Pay Item 642.0001.___ Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642.0003.___ Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2-week work plan, or not required by the Contract.

Traffic Maintenance in support of utilities is paid for under Section 643.

Utility Support Price Adjustment. The total value of this contract will be adjusted by $1,500 per calendar day for failure to provide the utility support or scheduling of utility work.

Payment made under:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 688.2001.____ | Utility Support | CS |
| 688.2002.____ | Utility Support Price Adjustment | CS |

CFHWY00599

Blank Page

DIVISION 700 — MATERIALS

Blank Page

SECTION 702
ASPHALT MATERIALS

Special Provision

702-2.01 ASPHALT BINDER. Replace the 1st. paragraph with the following:

Meet AASHTO M 320 Performance-Graded Asphalt Binder and AASHTO M332 Performance-Graded Asphalt Binder Using MSCR Test Specification; except, as included in Table 702-2.01-1 Performance-Graded Asphalt Binder – Exceptions.

TABLE 702-2.01-1

PERFORMANCE-GRADED ASPHALT BINDER - EXCEPTIONS

| Performance Grade | Viscosity AASHTO T 316 | Multiple Stress Creep Recovery MSCR, AASHTO T 350 |  |  | Dynamic Shear PAV, AASHTO T 315 | Direct Tension AASHTO T 314 | Elastic Recovery AASHTO T 301 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | JNR3.2 kPa-1 | JNR Diff | % Recovery3.2 | G*Sinδ, kPa |  |  |
| AASHTO M320 Performance-Graded Asphalt Binder |  |  |  |  |  |  |  |
| PG 52-28 | None | — | — | — | None | Delete | None |
| PG 52-40 | None | — | — | — | None | Delete | None |
| PG 52-40 ER | None | — | — | — | None | Delete | 50% min. |
| PG 58-34 ER | None | — | — | — | None | Delete | 60% min. |
| PG 64-40 ER | None | — | — | — | None | Delete | 60% min. |
| AASHTO M332 Performance-Graded Asphalt Binder Using MSCR Test Specification |  |  |  |  |  |  |  |
| PG52-40 E | None | 0.50 max. | Delete | 75 min. | None | Delete | None |
| PG58-34 E | None | 0.25 max. | Delete | 85 min. | None | Delete | None |
| PG 64-40 E | 1 Pas max. | 0.10 max. | Delete | 95 min. | 5000 max. @ 4°C | Delete | None |

CR702.3-010122

Standard Modification

702-2.03 EMULSIFIED ASPHALT.

Replace item 1. with the following:

1.	Cationic Emulsified Asphalt. Meet AASHTO M 208, except CRS-2P meet AASHTO M316.

HSM20.32-123121

SECTION 703
AGGREGATES

Standard Modification

703-2.03 AGGREGATE FOR BASE AND SURFACE COURSE. In Table 703-1 replace the line for Degradation Value with the following:

TABLE 703-1

AGGREGATE QUALITY PROPERTIES FOR BASE AND SURFACE COURSE

| PROPERTY | base COURSE | SURFACE COURSE | TEST METHOD |
| --- | --- | --- | --- |
| Micro-Deval | 15%, max. | 15%, max. | AASHTO T 327 |

HSM20.40-050122

Special Provisions

Replace Subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Type IV, and VH mixes.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

Meet Table 703-3 requirements:

TABLE 703-3

COARSE AGGREGATE QUALITY FOR HMA

| Description | Specification | Type II, Class A | Type I; Type II, Class B; Type III | Type IV | Type VH |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max. | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Micro-Deval, max. | AASHTO T 327 | 18% | 18% | 18% | 18% |
| Sodium Sulfate Loss, % max. (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, % min. | ATM 305 | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |
| Flat-Elongated Pieces, % max. | ATM 306 |  |  |  |  |
| 1:5 |  | 8 | 8 | 8 | 8 |
| Absorption, % max. | ATM 308 | 2.0 | 2.0 | 2.0 | 2.0 |
| Nordic Abrasion, % max. | ATM 312 | - | - | - | 8 a |

a.	Hard Aggregate that meets the Nordic Abrasion values specified may be obtained from, but not limited to, the following sources:

	MS 52-068-2, located at MP 217 on the Parks Highway near Cantwell

	Alaska Lime Co, Jim Caswell, located at MP 216.5 on the Parks Highway near Cantwell

	CalPortland plants located in Dupont Washington

	Jack Cewe Ltd located in Coquitlam British Columbia, Canada

Fine Aggregate.  Aggregate passing the No. 4 sieve.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type II, Class A mix shall not contain more than 10% natural fines (blend sand and mineral filler) added to the crushed aggregate, and shall not exhibit rut depth larger than 1/4-inch, as determined by ATM 419.

Fine aggregate for Type IV and VH mixes:

- do not blend back natural sand

- shall be non-plastic as determined by ATM 205

- shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-4

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type VH |
| 1 inch | 100 | - | - | - | - |
| 3/4 inch | 80-90 | 100 | - | - | 100 |
| 1/2 inch | 60-84 | 77-99 | 100 | 100 | 65-90 |
| 3/8 inch | 48-78 | 68-88 | 80-90 | 80-95 | 55-80 |
| No. 4 | 28-63 | 48-68 | 44-81 | 55-70 | 40-60 |
| No. 8 | 14-55 | 33-53 | 26-70 | 35-50 | ≤ 45 |
| No. 16 | 9-44 | 20-40 | 16-59 | 20-40 | ≤ 35 |
| No. 30 | 6-34 | 14-30 | 9-49 | 15-30 | ≤ 25 |
| No. 50 | 5-24 | 9-21 | 6-36 | 10-24 | ≤ 20 |
| No. 100 | 4-16 | 6-16 | 4-22 | 5-15 | ≤ 12 |
| No. 200 | 4-7 | 3-6 | 4-7 | 4-7 | 4-7 |

703-2.05 AGGREGATE FOR COVER COAT AND SURFACE TREATMENT. In Table 703-5 replace the line for Degradation Value with the following:

TABLE 703-5
QUALITY PROPERTIES FOR COVER COAT AND SURFACE TREATMENT

| Micro-Deval | AASHTO T 327 | 15%, max. |
| --- | --- | --- |

703-2.07 SELECTED MATERIAL.

Replace 1. Type A with the following:

1.	Type A. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by ATM 204 and ATM 205.  Meet the following gradation as tested by ATM 304:

Sieve	Percent Passing by Weight

No. 4	20-55%

No. 200	0-6%, determined on the minus 3-inch portion of the sample

703-2.09 SUBBASE. In Table 703-8 replace the line for Degradation Value with the following:

TABLE 703-8
QUALITY PROPERTIES FOR SUBBASE

| Micro-Deval | AASHTO T 327 | 25%, max. |
| --- | --- | --- |

CR703.1-100117R/HSM20.40-050122

703-2.10 POROUS BACKFILL MATERIAL.

Add the following to the end of the paragraph:

Use Gradation A unless otherwise specified.

HSM20.33-123121

703-2.13 STRUCTURAL FILL. Replace Table 703-12 with the following:

TABLE 703-12

AGGREGATE GRADATION FOR STRUCTURAL FILL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3-inch | 100 |
| 3/4-inch | 75-100 |
| No. 4 | 20-55 |
| No. 200 | 0-6 |

Replace Subsection 703-2.16 with the following:

703-2.16 RECYCLED ASPHALT PAVEMENT (RAP). RAP shall be free of contamination and deleterious materials.  RAP maximum particle size shall not exceed 1.5-inch.

CR703.1-100117R

SECTION 706
CONCRETE AND PLASTIC PIPE

Special Provisions

Replace Subsection 706-2.07 with the following:

706-2.07 CORRUGATED HIGH DENSITY POLYETHYLENE (HDPE) PIPE FOR CULVERTS, STORM DRAINS, AND UNDERDRAINS. Meet the following:

Corrugated Pipe and Fittings (non-pressurized)

AASHTO M 294 and 252	Type S

Perforations

1.	Underdrains	Class 2

2.	Underdrains and Storm Drains	Class 1

Joints	Subsection 705-2.05.3.

Polyethylene Pipe Manufacturer

1.	Participate in the National Transportation Product Evaluation Program (NTPEP) work plan for HDPE thermoplastic pipe and listed on the NTPEP audit website displaying NTPEP compliance.

2.	Conduct and maintain a quality control program under the NTPEP.

3.	Provide a manufacturer's certificate of compliance identifying production lots for all materials.

Provide corrugated polyethylene pipe and fittings manufactured from high-density polyethylene (HDPE) virgin compounds. May use clean, reworked polyethylene materials from the manufacturer's own production.

Do not install pipe that is more than two years from the date of manufacture.

CR706.1-050119

SECTION 708
PAINTS

Standard Modification

708-2.01 PAINT FOR STEEL STRUCTURES.

3.	Top Coat. In the 2nd sentence of the 1st paragraph, replace Federal paint specification "FSS No. 595B" with "AMS-STD-595".

HSM20.31-123121

SECTION 710
FENCE AND GUARDRAIL

Special Provisions

Replace Subsection 710-2.04 with the following:

710-2.04 METAL BEAM RAIL.

1.	W-Beam and Thrie Beam Guardrail. Meet AASHTO M 180, Class A, Type II.

2.	Box-Beam Guardrail. Meet ASTM A500 Grade B, or ASTM A501.

3.	Symmetric and Asymmetric W-Thrie Beam Transition Section. Meet AASHTO M 180, Class B, Type II.

Galvanize the rail per AASHTO M 111 after fabrication.

710-2.06 GUARDRAIL POSTS AND BLOCKOUTS.

Add the following:

4.	Transition Posts. Meet the section and length specified on the Plans. Meet ASTM A992 or ASTM A709, Grade 50.

5.	Transition Blockouts. Meet the shape and dimensions shown on the Plans. Meet ASTM A500. Grade B or Grade C.

Replace Subsection 710-2.11 with the following:

710-2.11 GUARDRAIL TERMINALS.

W-beam shall meet requirements of AASHTO M 180, Class A, Type II. Box beam shall meet requirements of ASTM A500 Grade B, or ASTM A501. Galvanize after fabrication.

Components made from rolled pressed and forged shapes, castings, plates, bars, and strips shall meet the coating requirements of AASHTO M 111. Galvanize after fabrication.

All hardware or fasteners supplied shall meet the coating requirements of AASHTO M 232.

Guardrail Terminals shall be AASHTO MASH Test Level 3.

1.	W-Beam. Provide one of the following terminal types, as shown on the plans, for single-rail W-beam guardrail. Design requirements: 31-inch top of rail height, 8-inch blockouts, W6x8.5 steel posts, 12 ft x 6-inch w-beam panels, and mid-span splice connection to run of rail.

a.	Parallel Terminals. Provide terminals meeting the following:

(1)	Length: 50 ft nominal effective length.

(2)	End Offset: 0 ft to 2 ft (25:1 or flatter straight taper). Offset end as shown on the plans.

b.	Buried in Backslope Terminal. Provide terminals as shown on the Plans.

2.	Box Beam. Provide terminals, as shown on the plans for box beam guardrail. Design requirements: 28-inch top of rail height, designed for use with 6-inch by 6-inch by 3/16-inch box beam.

a.	Parallel Terminals. Provide terminals meeting the following:

(1)	Length: 33 ft nominal effective length, or a minimum 18 ft of box beam rail and standard 3-inch weak posts beyond the 1/8-inch tube rail, or as recommended by the manufacturer's installation manual.

(2)	End Offset: 25:1 or flatter straight taper. Offset end as shown on the plans.

Add the following Subsection 710-2.12 Transition Connection:

710-2.12 TRANSITION CONNECTION.

1.	Thrie Beam Terminal Connector. Meet AASHTO M 180, Class B, Type II.

2.	Guardrail Connection Plate. Meet ASTM A709, Grade 50.

HSM20.34-123121

SECTION 712
MISCELLANEOUS

Standard Modification

712-2.08 GLASS BEADS.

Replace the 2nd sentence with the following:

Glass Beads shall contain no more than 200 ppm of lead or 200 ppm of arsenic when tested in accordance with EPA testing methods 3052, 6020B, or 6020C.

HSM20.35-123121

Special Provision

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti-skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

4.	Performance Properties:  Add the following:

k.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

Replace Subsection 712-2.18 with the following:

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads.  Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials.  Marking Material Manufacturer will certify compatibility.

(2)	Lasting retro reflectivity.

CR712.1-010109R

SECTION 722
BRIDGE RAILING

Special Provisions

Replaces Subsection 722-2.01 Bridge Railing with the following:

722-2.01 BRIDGE RAILING.

| Steel Tube Bridge Rail Elements | ASTM A500, Grade B or Grade C |
| --- | --- |
| Thrie-Beam Bridge Rail Elements | AASHTO M 180, Class B, Type II |
| Posts | ASTM A709, Grade 50 |
| Machine Bolts, Cap Screws, Nuts and Washers | ASTM A307 |
| High Strength Bolts | Subsection 716-2.03 |
| Anchor Bolts and Rods | ASTM F3125, Grade A325 or ASTM A449, Type 1 |
| Welded Studs | AASHTO M 169, Grade 1015 or 1020 |
| Bent Anchor Rods | ASTM A709, Grade 36 or Grade 50 |
| Shims, Plates, Plate Washers, Angles, Sleeves, and Scuppers | ASTM A709, Grade 50 |
| Guardrail Connection Plate | ASTM A709, Grade 50 |
| Beveled Washers and Tapered Plate Washers | ASTM F436 |
| Galvanize steel portions of railing after fabrication. | AASHTO M 111 or M 232 and Subsection 716-2.07 |

CFHWY00599

Special Provision

Replace Section 724 with the following:

SECTION 724
SEED

724-2.01 DESCRIPTION. Grass seed to provide a living vegetative cover.

724-2.02 MATERIALS. Provide seed mix as specified in the Special Provisions. Provide seed collected or harvested within 2 years of the targeted seeding date. Provide all seed in pure live seed (PLS) unless otherwise directed.

Furnish seed true of genus and species. Meet applicable requirements of the State of Alaska Seed Regulations, Alaska Administrative Code, Title 11, Chapter 34, (11 AAC 34), and the Federal Seed Act, 7 CFR Part 201.

The Engineer will review requests for genus, species, or cultivar substitutions(s). The Contractor shall submit a proposed seed mix accompanied by approval from the Alaska Plant Materials Center, and confirmation the vendor can provide the requested mix in quantities adequate for the project.

1.	Prohibited and Restricted Noxious Weeds and Quarantined Pests. Furnish seed certified to be free of prohibited noxious weeds or quarantined pests, and certified to contain no more than the maximum allowable tolerances for restricted noxious weeds, according to 11 ACC 34.

a.	Seed found to contain prohibited noxious weeds or quarantined pests will be rejected, according to 11 AAC 34.020(a) and 11 AAC 34.105 through 34.180, respectively.

b.	Seed found to contain restricted noxious weed seed in excess of the maximum allowable tolerance per pound will be rejected, according to 11 AAC 34.020(b).

Prohibited and restricted noxious weeds are listed in 11 AAC 34.020, and can be viewed at the following URL: http://plants.alaska.gov/invasives/noxious-weeds.htm.

2.	Labeling. Ensure each bag or container of individual seed species is labeled to meet requirements of 11 AAC 34.010. Do not remove labels from bags or containers.

3.	Certification. Certify seed is free of prohibited noxious weeds and restricted noxious weeds are within allowable tolerances. Furnish to the Engineer a statement signed by the vendor identifying the lot number or lot numbers, certifying each lot of seed has been tested within the preceding nine months, by a recognized seed testing laboratory, a member of the Association of Official Seed Certifying Agency (AOSCA), or the Alaska Plant Materials Center.

Seed will be rejected if:

a.	Contains prohibited noxious weeds;

b.	Contains restricted noxious weeds above maximum allowable tolerances;

c.	Not certified as tested within the preceding nine months;

d.	Wet, moldy, or otherwise damaged in transit or storage; or

e.	Containers do not have labels or the labels have been removed.

Seed may be rejected for:

a.	Discrepancies in the lot numbers listed on the statement to the lot numbers indicated on the labels of the seed containers.

The Contractor shall immediately remove rejected seed from the project premises. If seed is rejected

for containing prohibited noxious weeds or for exceeding maximum allowable tolerances of restricted noxious weeds, dispose of rejected seed according to 11 AAC 34.075(g).

CR724.HSM20.17-113020

SECTION 725
FERTILIZER

Special Provisions

725-2.01 MATERIALS.

Add the following after the first sentence:

For Seed Mix (B), furnish a mixture of chemical ingredients providing the total available nitrogen, phosphorus, potassium, and sulfur required in Table 618-2. Mixture shall be slow release.

CFHWY00599

SECTION 726
TOPSOIL

Special Provision

Replace Subsection 726-2.01 with the following:

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area, and free of prohibited and restricted noxious weeds (Prohibited and Restricted Noxious Weeds 11AAC 34.020 http://plants.alaska.gov/invasives/noxious-weeds.htm). Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project.  In this case furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse or foreign materials having an organic content of 5 percent or more, as determined by ATM 203.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the topsoil source location at least 30 calendar days before delivery of topsoil to the project from the identified location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

TABLE 726-1

LIMESTONE REQUIREMENTS

| Soil pH | Limestone, tons/acre |
| --- | --- |
| Above 6.0 | 0 |
| 5.0-6.0 | 1.5 |
| Below 5.0 | 3.0 |

CR726.1-010120

Special Provisions

Replace Section 727 with the following:

SECTION 727
SOIL STABILIZATION MATERIAL

727-2.00 GENERAL.  Free of restricted and prohibited noxious weeds (11 AAC 34), seeds, chemical printing ink, germination and growth inhibitors, herbicide residue, chlorine bleach, (except where specified: rock, metal, plastics) and other deleterious materials and not harmful to plants, animals and aquatic life.  Wood cellulose "paper" fiber, wood chips, sawdust, and hay are not permitted as stabilization materials.

727-2.01 MULCH.  Flexible blanket/covering, temporary degradable (bio/photo) form of erosion control.  Use one of the following:

Dry Erosion Control, Stabilization Products.  Hand applied or spread with mulch blower equipment.

1.	Straw.  Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life. Straw material shall be certified weed-free straw using North American Weed Management Association (NAWMA) Standards.  In-lieu of certified weed-free straw provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

2.	Shredded Bark Mulch.  Shredded bark and wood with the following characteristics:

a.	Not containing resin, tannin, or other compounds in quantities harmful to plant life.

b.	Maximum length of individual pieces is 2 inches with 75% passing through a 1 inch sieve.

c.	Will form a uniform ground cover/mat, have moisture absorption, retention, and percolation properties, not be susceptible to spreading by wind or rain providing a good growth medium.

d.	May contain up to 50% shredded wood material.

e.	Shredded wood material aged 1 year minimum prior to use.

Hydraulic Erosion Control Products (HECPs) Applied hydraulically.

A fiber mulch matrix:  biodegradable and composed of wood, straw, coconut and other fibers natural and man-made.  When applied, create a continuous, porous, absorbent high water holding, flexible blanket/mat/mulch/covering making intimate contact with, and adhering to sloped soil surface; permitting water infiltration; resists erosion and promotes rapid germination and accelerated plant growth.  The fibers may be thermally processed, and cross-linked with a hydro-colloidal or linear anionic tackifier (curing period 24-48 hours) or mechanically-bonded (no curing period).  When agitated in slurry tanks with water the fibers will become uniformly suspended, without clumping to form homogeneous slurry.

The HECPs shall be delivered premixed by the manufacturer.  The HECP will contain only the materials provided in the sealed containers from the manufacturer.  No added components are permitted after the manufacturer seals the product container, before application, during application or otherwise.  Submit documentation dated within 3 years of application, from an independent accredited laboratory as approved by the Engineer, showing that the product's testing performance meets the requirements for the slope(s) to be protected on the project, according to the National Transportation Product Evaluation Program (NTPEP), Erosion Control Technology Council (ECTC) and or the Texas DOT/Texas Transportation Institute (TTI) Laboratory.

If the HECP contains cotton or straw provide documentation that the material is certified weed free using NAWMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

The HECP shall contain a dye to facilitate placement and inspection of the material.

1.	Wood Strand, Fiber.

A blend of angular, loose, long thin wood pieces with a high length to width ratio and that are frayed.  Minimum 95% of strands between 2 inches and 10 inches, at least 50% of the length shall have a width thickness between 1/16 and 1/8 inch.  No single strand shall have a width or thickness greater than 1/2 inch.  Processed wood fiber with the following characteristics:

a.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form homogeneous slurry.

b.	Will form a blotter-like uniform ground cover on application, have moisture absorption, retention and percolation properties, the ability to cover, and hold grass seed in contact with soil, and not create a hard crust upon drying providing a good growth medium.

2.	Dried Peat Moss.  Partially decomposed fibrous or cellular stems and leaves of any of several species of Sphagnum mosses with the following characteristics:

a.	Chopped or shredded to allow distribution through normal hydraulic type seeding equipment and capable of being suspended in water to form part of a homogeneous slurry.

b.	Free from woody substances and mineral matter such as sulfur or iron and with a pH value of between 4.0 and 6.5.

c.	Furnished in an air dry condition and containing less than 35% moisture by weight.  Have a water holding capacity of not less than 800% by weight on an oven dry basis.

3.	Fiber Matrix (FM) Mulch - Types.

a.	Stabilized Mulch Matrices (SMMs)

b.	Bonded Fiber Matrices (BFMs)

c.	Mechanical Bonded Fiber Matrix (MBFM)

d.	Polymer Stabilized Fiber Matrix (PSFM)

e.	Fiber Reinforced Matrices (FRMs)

	Flexible Growth Medium (FGM)

	Extended-Term Flexible Growth Medium (ET-FGM)

727-2.02 MATTING.  Fiber mulches, mulch matrices, nets and turf reinforcement mats manufactured from wood fibers, straw, jute, coir, polyolefins, PVC, nylon and others creating dimensionally stable nets, meshes, geotextiles and blankets; creating a continuous, porous, absorbent, flexible blanket/mat/mulch/covering making intimate contact with and adhering to sloped soil surface, resisting erosion and promoting rapid germination and accelerated plant growth.

Rolled Erosion Control Products (RECPs) (Temporary Degradable and Permanent Erosion Control)

Use RECPs that bear the Quality and Date Oversight and Review (QDOR) Seal from the ECTC.  Independent test results from the NTPEP, that the mulch, when tested according to ASTM 6459 Standard Test Method for Determination of Rolled Erosion Control Products (RECP), Performance in Protecting Hillslopes from Rainfall-Induced Erosion, meets the performance requirement using the Revised Universal Soil Loss Equation (RUSL).

Functional Longevity.

1.	Temporary Degradable.

a.	Duration.

1)	Short-Term RECPs. (RECPs 3 - 12 months)

C Factor = .15 maximum

Test Soil Type = Sandy Loam

(National Resources Conservation Service (NCRS) Soil Texture Triangle)

2)	Moderate (Extended) -Term RECPs.  (RECPs 24 months)

C Factor = .05 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

3)	Long-Term RECPs.  (RECPs 36 months)

C Factor = .01 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

b.	Product types.

1)	Mulch-Control Nets (MCNs).  Planar woven natural fiber or extruded geosynthetic mesh used to anchor loose fiber matting/mulches.

2)	Erosion Control Blankets (ECBs).  Processed natural and/or polymer fibers, yarns or twines mechanically, structurally, or chemically bound together to form a continuous matrix with a minimum weight of 8 oz/yd2 and a limiting shear stress of 0.45 lb/ft2.

3)	Netless.  Fibers mechanically interlocked and/or chemically adhered together.

4)	Single-net and Double-net.  Fibers mechanically bound together by single or double netting.

5)	Open Weave Textiles (OWTs).  Fibers woven into a continuous matrix.

c.	Materials.

1)	Burlap.  Standard weave with a weight of 3.5 to 10 oz/yd2.

2)	Jute Mesh Fabric.  Cloth of a uniform, open, plain weave of undyed and unbleached single jute yarn.  Use yarn that is loosely twisted and not varying in thickness more than one-half its normal diameter.  Furnish jute mesh in rolled strips meeting the following requirements:

a)	Width:  45 to 48 inches,  1 inch

b)	78 warp-ends per width of cloth (minimum)

c)	41 weft-ends per yard (minimum)

d)	Weight:  20 ounces per linear yard,  5%

3)	Woven Paper or Sisal Mesh Netting.  Woven from twisted yarns available in rolls 45 to 48 inches wide.  Mesh may vary from closed to open weave, ranging from 1/8 to 1/4 inch openings.  Shrinkage after wetting may not exceed 20% of the surface area.

4)	Knitted Straw Mat.  Commercially manufactured ECB.  Use photodegradable netting and biodegradable thread.  Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life.  ECB may contain coconut or fiber to reinforce the straw.  Straw material shall be certified weed-free straw using NAWMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

5)	Woven/Curled Wood blanket.  Machine produced mat of curled wood shavings with a minimum of 80% 6-inch or longer fibers, with consistent thickness and the fibers evenly distributed over the entire area of the blanket.  Smolder resistant without the use of chemical additives.  Cover the top side of the blanket with biodegradable extruded plastic mesh.

6)	Coconut (Coir Fiber).  Machine produced mat, ECB of consistent thickness and coir fiber evenly distributed over the area of the mat.  Use bio/photo degradable netting and thread.

2.	Permanent.

a.	Product Types and Materials.

1)	Turf Reinforcement Mats (TRMs).  A rolled erosion control product composed of non-degradable synthetic fibers, filaments, nets, wire mesh, and/or other elements, processed into a permanent, three-dimensional matrix of sufficient thickness with a minimum weight of 8 oz/yd2 and a minimum limiting shear stress of 1.5 lb/ft2.  TRMs (may be supplemented with degradable components) shall impart immediate erosion protection, enhance vegetation establishment during and after maturation and permanent vegetation reinforcement providing long-term functionality.

727-2.03 SEDIMENT RETENTION FIBER ROLLS (SRFRs).  Fiber rolls also referred to as wattles.  Manufacture of photodegradable or biodegradable fabric netting without preservative treatment, evenly woven, free of crusted material, cuts, and tears.  Manufacture stakes of photodegradable or biodegradable material (wood stakes, except as approved by the Engineer).

1.	Filter Sock (Wattle)

a.	Fabric netting.

b.	Filled with wood fiber, straw, flax, rice, coconut fiber material.

c.	Minimum diameter 5 inches.

2.	Compost Sock.

a.	Extra Heavy weight fabric netting with a minimum strand width of 5 mils.

b.	Filled with coarse compost.

c.	Minimum diameter 8 inches.

3.	Coir Log.

a.	Woven wrap bristle coir twine netting.

b.	Filled with 100% coconut (coir) fiber uniformly compacted.

c.	Segments maximum length 20 foot, diameter as suited to the application and a density of 7 lbs/pcf or greater.

d.	Coir twine strength equal to 80 lb minimum weaved to a 2 inch x 2 inch opening pattern.

e.	Ties made of hemp rope by 1/4 inch diameter.

727-2.04 COMPOST.  Suitable for serving as a soil amendment or an erosion control material.  Sanitized, mature compost meeting local, state, and Federal quality requirements tested and certified by the U.S. Composting Council (USCC) under the Seal of Testing Assurance (STA) Program.  Biosolids compost must meet the Standards for Class A biosolids outlined in 40 Code of Federal Regulations (CFR) Part 503.  Additionally, meet the requirements of the AASHTO specifications:

1.	Compost Blankets.  Standard Practice for Compost for Erosion/Sediment Control (Compost Blankets) R 52.

2.	Compost Filter Berms and Filter Socks.  Standard Practice for Compost for Erosion/Sediment Control (Filter Berms and Filter socks) R 51.

727-2.05 TACKIFIER.  Tackifier, viscous overspray, generally composed of dry powered vegetable gums derived from guar gum, psyllium and sodium alginase; asphaltic emulsions; petroleum distillates; co-polymer emulsions; and lignosulfonates and used to anchor soil, compost, seed, the mulch fibers to one another, and the ground.  Contain no growth or germination inhibiting materials nor significantly reduce infiltration rates.  Tackifier shall hydrate in water and readily blend with other slurry material.  Tackifier options include:

1.	Type A.  Organic tackifier with certification of plant sources; or

2.	Type B.  Synthetic tackifier with certification confirming product is not harmful to plants, animals, or aquatic life.

727-2.06 POLYACRYLAMIDE (PAM).  Use as a tie-down for soil, compost, seed and as a flocculent. Polyacrylamide (PAM) products shall meet the requirements of American National Standards Institute (ANSI)/National Sanitation Foundation International (NSF) Standard 60 for drinking water treatment, be anionic (not cationic), linear and not cross-linked with an average molecular weight greater than 5 Mg/mole, minimum 30 percent charge density; contain at least 80% active ingredients and a moisture content not exceeding 10% by weight.

Deliver PAM in a dry granular powder or liquid form.

727-2.07 GEOTEXTILE-ENCASED CHECK DAM AND SEDIMENT BARRIER.  Urethane foam core encased in geotextile material (silt fence material Section 633), minimum 8 inches height by minimum base width of 16 inches by minimum 7 foot length.  Overhang the geotextile 6 inch minimum each end with apron type ties by 24 inches each side of the foam core.

727-2.08 SANDBAG.

1.	Sandbag Sack Fabric. Fabric shall be a nonwoven, needle punched design meeting the Minimum Average Roll Values (MARV) verified in accordance with ASTM D4759.

2.	Seam Thread.  Similar durability to the sandbag sack fabric.

3.	Sandbag Fill Material.

a.	Selected Material	703-2.07	Type B

4.	Cinch Ties.  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

727-2.09 MANUFACTURED INLET PROTECTION SYSTEM.

1.	Manufacturers:

a.	Ultra Tech International – Ultra-DrainGuard

b.	Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

c.	Enpac - Catch Basin Insert, Oil and Sediment or

d.	Approved equal.

727-2.10 CLEAR PLASTIC COVERING.  A clear plastic covering meeting the requirements of the National Institute of Standards and Technology (NIST) voluntary Product Standard PS 17 - 69 for polyethylene sheeting having a minimum thickness of 6 mils.

727-2.11 STAPLES.  U-shaped staples for anchoring matting, approximately 6 inches long and 1 inch wide.  Machine-made:  No. 11 gage or heavier steel wire.  Hand-made:  12-inch lengths of No. 9 gage or heavier steel wire.

CR727-050812R

SECTION 730
SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS.

Add No. 7:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to ASTM A500, Grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

CR730.1-062204

Replace Subsection 730-2.05 with the following:

730-2.05 FLEXIBLE DELINEATOR POSTS.  Durable fiberglass composite, polymer, or plastic material meeting the dimensions and colors shown on the Plans. Resistant to ultraviolet light, ozone and hydrocarbon damage and remain flexible at a temperature of minus 40 °F. Provide posts with reflectors that are capable of self-erecting and remaining serviceable after 5 head-on impacts at 55 mph and 10 impacts at 35 mph with an automobile at an air temperature of plus 40 °F.

Terminal Markers - Flexible (marker).  The marker includes the pole/post/rod (pole), reflective and retroreflective sheeting and mounting hardware.

Provide durable markers: resistant to impact from (snow and vehicle), vandals, ultraviolet light, moisture, ozone, and hydrocarbons.

When the pole is loaded, the marker shall bend/flex, remain flexible and oriented as installed continuing to function as designed without permanent displacement along the length of the member.  Provide the flexibility in the primary vertical element, a connecting device between the vertical element and connection to the support member (spring or other) or a combination.

Provide a connection sufficient to transfer the loads from the pole to the supporting member without reducing the strength, flexibility, or durability of either.  The connection shall not negatively influence the performance of the guardrail.  Provide approval of the connection from the marker manufacturer and support member manufacturer (if proprietary).

	Design Loads:

	Impact load from snow thrown by snowplows

Ø	Weight of snow covering the pole (snow thrown from snowplows)

Ø	Wind loads (100 mph, 3 sec gust)

·	Service Temperature Range:	-40˚ F to +140˚ F.

·	Pole:

1.	Material:

Ø	Steel, or

Ø	Stainless Steel, or

Ø	Other Poles:

(a)	Continuous glass fiber and marble reinforced thermosetting composite, or

(b)	Engineered plastic alloy, or

(c)	Fiberglass Reinforced Polyester (FRP)

(d)	High-Impact Polyolefins

2.	Dimensions

Ø	Top of Pole:  60 inches to 84 inches above top of guardrail

Ø	Width/Diameter:  minimum = 1 1/4 inches, maximum = 2 inches (steel/stainless steel not be greater than 5/8 inch diameter)

Ø	Thickness:  as required by design

3.	Visibility:

Ø	Daytime: Pole - color orange

a.	Steel and Stainless Steel Poles:  Applied permanent finish.

b.	Other Poles:  Color pigment ultraviolet stabilized and solid through the cross section from end to end.

Ø	Nighttime:  Added retroreflective sheeting - color white

a.	Approximately 12 square inches visible from the traveled way before and after the marker.  Applied to a flag attached to the pole or as banding applied directly to the pole.  (A flag is required when using steel/stainless steel poles.)

b.	Place top edge of flag/banding 1 inch from top of pole.

(1)	Flag:  Single retroreflective sheet each face

(2)	Banding:  Two bands completely around marker, 4 inches between bands

·	Hardware and Fasteners:

Ø	Steel, and/or

Ø	Stainless Steel, or

Ø	Aluminum alloy (hardware only)

Manufacturers of flexible markers (snowpoles):

| Manufacturer | Model | Type | Contact |
| --- | --- | --- | --- |
| Nordic Fiberglass, Inc. | FF2 | Steel Pole w/ Flag | Ph: (218) 745-5095 |
| PEXCO | Model 3639 | High-Impact Polyolefins | Ph: (404) 564-8560 |
| New Century Northwest, LLC | NCN2549 | Engineered Plastic Alloy | Ph: (541) 485-5566 |
| Carsonite Composites, LLC | SNFB | Continuous glass fiber and marble reinforced thermosetting composite | Ph: (800) 648-7916 |

Submit manufacturer's specifications to the Engineer for review and approval before ordering terminal markers.

CR730.2-122217

SECTION 731

WATERPROOFING MEMBRANE

731.2.01 SPRAY-APPLED WATERPROOFING MEMBRANE.

Replace Table 731-1 SPRAY APPLIED WATERPROOFING MEMBRANE with the following:

| Table 731-1 SPRAY-APPLIED WATERPROOFING MEMBRANE |  |  |
| --- | --- | --- |
| Test | Requirements | Test Method |
| Adhesion to Concrete | 100 psi min., with failure in concrete | ASTM D7234 |
| Tensile Strength at Break | 1500 psi min. | ASTM D638 |
| Elongation at Break | 130% min. | ASTM D638 |
| Crack Bridging | Pass at 10 cycles of 1/8 inch when tested at -15°F | ASTM C1305 |
| Interlayer Shear Strength | 30 psi min. | AASHTO TP-114 |

CFHWY00599

Special Provision

Replace Section 740 with:

SECTION 740
SIGNALS AND LIGHTING MATERIALS

740-2.01 GENERAL.  Use electrical materials, devices, fittings, and hardware that conform to applicable NEMA and ANSI standards.

Use electrical products that are Third Party Labeled or Listed (by an approved independent electrical testing laboratory such as UL, ETL, CSA, etc.), unless otherwise indicated on the Materials Certification List (MCL).

Ensure that all material and workmanship, as determined by the Department, conform to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the authority having jurisdiction.

740-2.02 SIGNAL AND LIGHTING POLES.

- Design.  Design and fabricate structures to conform to:

  - Highway Lighting Structures: 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions and the highway lighting sheets in the Plans.  Use a wind speed of 100 mph with a gust factor of 1.3.  Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 ft. above the pole base.

  - Breakaway Traffic Signal Structures: 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions and Central Region Traffic Signal Details.  Design must meet Fatigue Category II, a vibration mitigating device may be used in lieu of providing galloping computations, using a basic wind speed of 100 mph and Central Region standard loads.

  - Mastarm Traffic Signal Structures: 2013 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with 2013 Errata and 2015 Interim Revision, and Central Region Traffic Signal Details.  Design must meet Fatigue Category I, a vibration mitigating device may be used in lieu of providing galloping computations, using a basic wind speed of 100 mph and Central Region standard loads.

A vibration mitigation device is a non-aerodynamic damper system that is purpose-built to mitigate vertical movement of signal mast arms. Effectiveness shall be proven through analytical methods approved by the Engineer. The system shall be self-adapting and must not require structure specific tuning. The device must provide an 85 percent or greater vibration reduction.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations.  Submit the stamped drawings and calculations for each pole to the Engineer for approval.  Design for the complete-in-place structure including the supported hardware.

a.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole and mast arm, including:  design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide design wind speed and the details for building the poles and mast arms, including:  materials specifications, slip fit joint dimensions, pole component dimensions, welds that will be made, and the welding inspection that will be done.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

2.	Fabrication.  Fabricate signal and lighting structures from tapered steel tubes with a round or 16 sided cross section.  Orient handholes located near the base of poles to face downstream of traffic flow.

Furnish poles and mast arms up to 40 feet long in one piece.  Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice.  For slip type joints, provide the minimum overlap specified in the Plans.  In mast arms, locate these splices at least one foot away from the Plan location of signal heads and signs.  In signal poles, locate the edge of the female section at least 6 inches above the top of the signal mast arm connection.

Fabricate tubes with walls up to 1/2 inch thick from the prequalified base metals listed in AWS D1.1.  Fabricate elements greater than 1/2 inch thick from steel that conforms to AASHTO M270 and meets the Fracture Critical Impact Test requirements for Zone 3.  The Department will not accept structures that use laminated steel elements.

Fabricate the cross section of each tube from no more than 2 pieces of steel.  When using 2 pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from two inch nominal schedule 40 pipe that conform to ASTM A 53 Grade B.

Fabricate breakaway signal poles in accordance with the Pole Sheet in the Plans. Fabricate signal poles 10 to 16 feet long from 7 gage (US Standard) sheet steel.  Fabricate each post with a minimum inside diameter at the base plate as shown in the Plans.  Use 4 inch diameter by 4 inch Schedule 40, ASTM A53, Grade B pipe as a post-top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms.  To add lift points, weld them to the tube opposite the longitudinal seam weld on the outside of female segments and on the inside of male segments. Before shipment, remove lift points added to the outside of the tubes, grind the area smooth with the base metal, and hot stick repair the finish according to Subsection 660-3.01.8.a.  Lift points added to the inside of tubes in place may be left in place.

Hot-dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications. Galvanizing kettles will be large enough to completely submerge each element, the mast arm, and the pole.  Submerge the complete/whole element in the galvanizing process.  An element galvanized in sections will not be accepted.  Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove all excess zinc from all drip lines and points and the surfaces of all tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

a.	Not fabricated according to these specifications or the approved shop drawings,

b.	Bowed with sweeps exceeding 1 inch throughout the length of the pole, mast arm, or segment, if furnishing a 2 piece pole or mast arm,

c.	Out of round.  Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

Fabricate pile cap adapters from Grade X42 steel line pipe that conforms to API 5L and from steel plate that conforms to ASTM A 709 Grade 50.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Fabricate the anchor plate to match the base plate of the lighting standard.

3.	Welding.  Perform welding to conform to Subsection 504-3.01.7 and the 2013 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals, the Central Region Traffic Signal Details, and the following:

a.	Make welds continuous.  Grind exposed welds flush with the base metal at slip fit joints for the length of the slip fit joint plus one half the diameter of the female section.

b.	On steels 5/16 of an inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

c.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.  In steels less than 1/8 inch thick, complete the tests according to AWS D1.1.

d.	Only visually inspect welds made on luminaire mast arms.

4.	Anchor Rods & Bolts.  Furnish 2 inch diameter (nominal) anchor rods for signal poles that meet ASTM F1554 Grade 105, are 96 inch minimum length and conform to Supplemental Requirements; S2, Permanent Manufacturer’s Identification, S3, Permanent Grade Identification and S-5 Charpy Impact Requirements.  Hot dip galvanize according to AASHTO M232.  Use nuts that conform to AASHTO Specification M292 of the grade, surface finish, and style for 2 inch diameter anchor rods.  Washers shall conform to AASHTO M293.

5.	Miscellaneous.  Finish the edges of poles and mast arms to conform to the following requirements.  Before hot dip galvanizing, neatly round the following features to the radius specified.

a.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both the entrance and exit edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus one half the diameter of the female section grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces.

Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1.  The measurements shown are for illustration purposes only.  Use tags large enough to include required information using 1/4 inch high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text.  Secure the tags with two 1/8 inch blind rivets at the base of poles and the underside of mast arms.  If furnishing a two piece signal mast arm with slip type joint, mark both pieces with the same message.  Provide the holes for the blind rivets before galvanizing.

TABLE 740-1

POLE MARKINGS

Note: Italic type indicates additional Tag Markings if poles have 2 luminaire or 2 signal mast arms.

| POLES (Including Mast Arms ) | MEASUREMENTS | TAG MARKINGS |
| --- | --- | --- |
| Signal Poles |  |  |
| Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| Pole height | 36 ft. | PH 36 |
| Intersection number (if more than one) -pole number |  | 1 - P 4 |
| Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| Mast arm length | 40 ft. | SMA 40 |
| Intersection number (if more than one) -pole number |  | 1 - P 4 |
| Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| Mast arm length | 18 ft. | LMA 18 |
| Pole number (if unique arm design) |  | P 4 |

740-2.03 WOOD POLES.  Use wood poles for service or temporary installations of the class shown on the Plans or as specified in the Special Provisions.

Use 45-foot poles, except for service poles use 25-foot poles.

Use mastarms and tie rods for wood pole installations that conform to Subsection 740-2.02, and to the details shown on the Plans. Provide each mastarm with an insulated wire inlet and wood pole-mounting bracket for mastarm and tie rod crossarm.

Use structural timber meeting Section 713. Do not use poles that have more than 180 degrees twist in grain over the full length. Ensure that the sweep is no more than 4 inches. Pressure-treat wood poles, that are not to be painted, after fabrication. Meet Section 714.

740-2.04 reserved.

740-2.05 CONDUCTORS.  Use conductor sizes based on the American Wire Gage (AWG). Use sizes that conform to the Plans or, when not shown, to this subsection.

Use insulated conductors made of uncoated, stranded copper that conforms to the specifications of ASTM B8. Use grounding conductors that are bare copper of the gage required by the NEC. They may be stranded, solid, or braided.

Provide the following markings on the outer coverings of conductors and cables on intervals of 2 feet or less: manufacturer, the number of conductors or pairs in cables, conductor size, 600V, the conductor or cable type and environmental conditions for which the conductor or cables are listed, and the symbol of an approved independent testing laboratory.

Use conductors meeting the referenced specifications for the following purposes:

- Power Conductors. For individual conductors, install general-purpose building wire manufactured according to UL Standard 44, and NEMA No. WC7. Furnish conductors insulated with cross-linked polyethylene listed as type XHHW-2 and rated for 600 volts AC operation.

| TABLE 740-2 CONDUCTOR TERMINATION TABLE |  |  |  |  |
| --- | --- | --- | --- | --- |
| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG. NO. | BAND LEGEND |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red Arrow | Red | 14 | Head No. |
|  | Vehicle Yellow Arrow | Orange |  |  |
|  | Vehicle Green Arrow | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Vehicle Yellow Arrow | Black |  |  |
|  | Vehicle Green Arrow | Blue |  |  |
| 5 MOA Ped Signals | Pedestrian Don’t Walk | Red | 14 | Head No. |
|  | Pedestrian Walk | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | Orange |  |  |
|  | Spare | Black |  |  |
| 4 SOA Ped Signals | Pedestrian Don’t Walk | Red | 14 | Head No. |
|  | Pedestrian Walk | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | Black |  |  |
| 4 SOA Ped Buttons | Pedestrian Pushbutton | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
|  | Spare | Green |  |  |
| 3 MOA Ped Buttons | Pedestrian Pushbutton | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |

TABLE 740-2

CONDUCTOR TERMINATION TABLE

(Continued)

| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG NO. | BAND LEGEND |
| --- | --- | --- | --- | --- |
| 3 | Flashing Beacon | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Per Manufacturer Installation Instructions | Orange | 20 | "PRE" |
|  |  | Blue |  |  |
|  |  | Yellow |  |  |
| 3 | Preemption Confirmation | Black | 14 | "PRECON" |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Highway Luminaire | Black | 8 or 6 | Circuit No. |
|  | Highway Luminaire | Red |  | Circuit No. |
|  | Highway Luminaire Spare | White |  |  |
| 5 | Photo Electric Control | Black | 14 | PEC |
|  | Load to Contactor | Red |  |  |
|  | Neutral | White |  |  |
|  | Spare | Orange |  |  |
|  | Spare | Green |  |  |
| 3 | Service to Controller | Black | 6 or 4 | "SIG" |
|  | Neutral | White |  | No Band |
|  | Spare | Red |  | No Band |
| 3 | Sign Luminaire | Black | 8 | SIGN |
|  | Sign Luminaire | Red |  | SIGN |
|  | Sign Spare | White |  |  |

Use size 10 AWG wire for illumination tap conductors. In an electrolier, the illumination tap conductors run from the fused disconnect kit to the ballast in the luminaire. Furnish conductors with black, red, or white colored insulation as required to identify the two phase and neutral conductors, respectively.

If conductors in controller cabinets carry the full signal load circuit, use size 10 AWG or larger conductors. Use orange colored conductors from the flash transfer relay to program emergency flashing operation.

- Illumination Cables.  For cables that consist of three size 6 or 8 AWG conductors, furnish power cables that feature three conductors, each insulated with cross-linked polyethylene, and a black, low density, high molecular weight polyethylene jacket. Use insulated conductors listed as type XHHW-2. Furnish these cables with one black, one white, and one red colored conductor and no grounding conductor. Use cables rated for 600 volts AC operation.

Use insulated conductors meeting UL Standard 44. The jacket must also meet NEMA No. WC70.

- Power Cables.  For cables that consist of three size 4 AWG and larger conductors, furnish tray cables that feature three conductors, each insulated with cross-linked polyethylene that meets the requirements of XHHW-2, and a PVC jacket. Furnish these cables without an integral grounding conductor. Use cables manufactured according to UL Standard 1277, ICEA S-95-658, and NEMA No. WC70. Provide cables listed for direct burial and resistance to sunlight and rated for 600 volts AC operation.

Furnish these cables with black conductor insulation with one printed number (1, 2, or 3) identifying each conductor.

- Control Cables.  Wire with signal cable meeting IMSA 20-1 all vehicular signal heads, pedestrian signal heads, pedestrian push button detectors, flashing beacons, hardwired local coordination and preemption devices, and photoelectric controls.

- Detector Loops.  Use No. 14 AWG conductors for detector inductive loops that meet IMSA Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans or specified in the Special Provisions.

- Loop Lead-In Cables.  Unless otherwise specified, use a tray cable that conforms to the following specifications to connect the loop detectors to the terminal blocks in the controller cabinet. Furnish this cable, also known as Snyder Cable; manufactured according to UL Standard 1277. Supply these cables third party certified as Type TC and certified for use in underground conduit or as an aerial cable supported by a messenger, and rated for 600 volts AC operation.

Use size 18 AWG, 16 strand, tinned copper conductors per ASTM B33 insulated with wet-rated, cross-linked polyethylene similar to XHHW. Furnish conductors with insulation colors that match Table 660-1 twisted into pairs.

Provide each twisted pair with an overall aluminum foil coated mylar shield that provides 100% coverage and a 20 AWG tinned copper drain wire that is in constant contact with the foil side of the shield. Apply a tight fitting polyvinyl chloride jacket over the conductor assembly.

Only use the following loop lead-in cable, also known as shielded data cable, to rewire existing traffic signals when specified. Use cables that consist of 7 twisted pairs that consist of stranded, size 18 AWG tinned copper wire and polyethylene or polypropylene insulation. Furnish each pair covered with an aluminum foil shield, stranded copper drain wire, and an overall PVC or PE jacket. Use cable rated for 300 volts and whose colored pairs match those specified in Table 660-1.

- Telemetry Cable.  Use interconnect cable that consists of solid copper conductors of the number of pairs called for in the Plans meeting the requirements of Rural Utilities Service (formerly the Rural Electrification Administration (REA) specification PE-39 for filled telephone cables. The shield may be either copper or aluminum.

TABLE 740-3

INTERCONNECT TERMINATION TABLE

| TELEMETRY CABLE: Type PE-39, No. 19 AWG, Solid Copper, as noted on the Plans or in the Special Provisions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Pair No. | Tip | Ring | Pair No. | Tip | Ring |
| 1 | White | Blue | 14 | Black | Brown |
| 2 | White | Orange | 15 | Black | Slate |
| 3 | White | Green | 16 | Yellow | Blue |
| 4 | White | Brown | 17 | Yellow | Orange |
| 5 | White | Slate | 18 | Yellow | Green |
| 6 | Red | Blue | 19 | Yellow | Brown |
| 7 | Red | Orange | 20 | Yellow | Slate |
| 8 | Red | Green | 21 | Violet | Blue |
| 9 | Red | Brown | 22 | Violet | Orange |
| 10 | Red | Slate | 23 | Violet | Green |
| 11 | Black | Blue | 24 | Violet | Brown |
| 12 | Black | Orange | 25 | Violet | Slate |
| 13 | Black | Green |  |  |  |

| Hardwire CableS: IMSA Type 20-1, (2) 7 conductor No. 14 AWG |  |  |  |
| --- | --- | --- | --- |
| Cable No. 1 |  | Cable No. 2 |  |
| Circuit | Color | Circuit | Color |
| Cycle 2 | Green | Offset 1 | Green |
| Cycle 3 | Orange | Offset 2 | Orange |
| Cycle 4 | Red | Offset 3 | Red |
| Free | Blue | Split 2 | Blue |
| Common | White | Common | White |
| Spare | Black | Spare | Black |
| Spare | White/Black | Spare | White/Black |

740-2.06 ELECTRICAL CONDUIT AND FITTINGS.  Unless specified otherwise, use rigid metal conduit and fittings for raceways.  Furnish galvanized rigid type conduit and elbows conforming to UL Standard 6 and are manufactured of mild steel according to ANSI C80.1.  Furnish third party certified fittings designed for rigid metal conduit.

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL Standard 651.  Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL Standard 651 B and NEMA TC-7-2000.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle.  Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline.  The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws.  For loop detectors, furnish Type X bodies and, for photoelectric control installation, furnish Types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it.  The movements include:  axial expansion or contraction to 3/4 inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to 3/4 inch.  The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

740-2.07 FUSED SPLICE CONNECTORS.  Use fused, quick disconnect, splice connector that is weather tight and has two halves: a single-unit line side socket and a load-side plug. For LED fixtures, use fuses that are 5 ampere, midget (13/32” x 1-1/2“) ferrule type with a time delay (slow blow) type design. For all other fixtures use 10 ampere midget (13/32” x 1-1/2”) ferrule type with a fast acting current limiting design.

740-2.08 SIGN SWITCHES.  Provide a NEMA 3R non-fused disconnect switch as shown on the Plans for each sign illumination installation.

740-2.09 CONTROLLER ASSEMBLIES.  Provide solid state, traffic controller assemblies having level 2 conformance to NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements as defined in NTCIP1202.  Traffic Controller Assemblies must meet or exceed the Environmental Requirements of Section 2 of the NEMA TS2-2003 V02.06 document. The Original Equipment Manufacturer (OEM) and its manufacturing and testing facilities shall be ISO 9001:2000 certified for processes involving the Traffic Controller Assemblies.

Use traffic control equipment that is compatible with the existing traffic signal monitoring system.  Compatibility must be 100% at the cabinet level to include inputs, outputs, telemetry protocol, and block upload and download of RAM data.

In addition, features of the existing local controllers and controller modules must be functionally duplicated to meet or exceed the performance of the existing equipment.

The existing local controller cabinets at other intersections include the following equipment:

- Econolite Cobalt ATC Touch 2100

Use LED indicators for all electronic devices covered under Subsections 740-2.09 through 740-2.13.

740-2.10 CONTROLLER UNIT.

Actuated Controller Unit (CU).

Provide solid state, Type A2N Actuated Controller Units (CU) meeting the requirements of Section 3 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements.

- The CU must meet the referenced National Transportation Communications for ITS Protocol (NTCIP) and comply with publication TS 3.2 the Simple Transportation Management Framework, and shall meet the requirements for Conformance Level 2

- The software shall comply with NEMA TS 3.3, the Class B Profile, and shall include both an EIA/TIA 232-E and an FSK modem interface for NTCIP based communications.

- The CU shall implement conformance groups and optional object groups as defined in NEMA TS 3.4 and TS 3.5 for A2N level 2.

- Provide controllers with display heaters or enhancements to improve viewing in temperatures below 0 F.

- Provide controllers having an interface compatible with SYNCRO-7 traffic modeling software.

Furnish Econolite Cobalt ATC Touch 2100 controller unit with the following optional features:

- User interface Advanced Display with graphics and touch-screen

- TS2 Type I connector

- Data Key 3.3V, 32MB

740-2.11 CONTROLLER CABINET.  Provide a controller cabinet that meets the requirements of NEMA Standard TS 2-2003 V02.06 Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2), Section 5 Terminals and Facilities and Section 7 Cabinets.

- Standard Features. Supply the following standard features:

  - Materials

Unless otherwise designated in the Plans, provide cabinets constructed of sheet Aluminum.

  - Cabinet Dimensions and Bracing

Unless otherwise designated in the Plans, provide a size 7 cabinet as defined in NEMA TS-2 Table 7-1.

The cabinet shall include 1.0” x 0.25” diagonal aluminum cross bracing welded to the back door frame of the cabinet.

  - Doors

Provide a cabinet with lockable front and rear doors meeting the requirements of NEMA TS-2 Section 7.5.  The locks must accept a Best CX series core that will be installed by the Department after the Contract is complete.

The front and rear doors shall be provided with top and bottom catches to hold the door open at both 90 and 180 ± 10 degrees. The catches shall be capable of holding the doors open at 90 degrees in a 60-mph wind acting at an angle perpendicular to the plane of the door.

  - Shelves

Provide shelves meeting the requirements of NEMA TS-2 Section 7.6.

Shelves shall have a 3/8” lip on the front and back while not limiting access to equipment. Top shelf shall be braced to support additional weight of uninterruptable power supply (UPS) battery up to 150 lbs. Provide a restraint at the front and back.

Provide additional laptop computer shelf mounted approximately 30” above cabinet floor.  The laptop shelf must accommodate a standard 17" computer and be retractable below one of the cabinets’ shelves.

  - Finish and Preparation

Unless otherwise designated in the Plans, provide unpainted Aluminum Cabinets with a "natural" brushed appearance.

  - Cabinet Mounting

    - Provide cabinet mounting features as defined NEMA TS-2 Section 7.8.

    - The cabinet manufacturer is responsible for providing a cabinet that will mount without modification on the foundation detailed in Alaska Department of Transportation Central Region, Regional Detail, Controller Cabinet Foundation.

  - Cabinet Ventilation

Furnish a cabinet that fully meets the requirements of NEMA TS-2 Section 7.9 and the following:

    - Furnish the fan and cabinet vent with internally mounted metal covers that are fabricated to close off the flow of air during winter operation.

    - Equip the cabinet with a selectable, 750/1500 watt cabinet heating device.  The heating device must have a remote air sensing thermostat. The contacts must be rated 20 amps, 120 volts, 60 hertz.

      - Construct the thermostat so that contacts close on descending temperature and are adjustable between 0 and 30 °F ±5 °F. The contacts must open on rising temperatures of 15 °F above the closing temperature.  The adjustment must have an indicating pointer.

      - Connect the thermostat in series with an electrical resistance heater and blower fan.  The blower fan must be rated for continuous duty.  The heater and fan must be connected in parallel and rated 120 volts, 60 Hertz.  Mount the unit in the vertical position on the cabinet door.  The thermostat shall be mounted immediately to the left of the heating device on the cabinet door.

      - Do not block the air intake or outlet.  Provide the unit with a SPST manual override switch that bypasses the thermostat to enable the fan and heater to operate at warmer temperatures.

  - Auxiliary Cabinet Equipment

    - Mount a 4000K LED strip lighting fixture on the inside of the cabinet near the top front edge and under the controller shelf.  The lighting fixture "ON-Off" switch must be a toggle switch mounted on an inside control panel.  Include in the circuit a door actuated switch that turns the light ON when the door is open and OFF when the door is closed.

    - Provide three (3) paper sets of complete and accurate cabinet drawings with delivery of each cabinet.  Make cabinet drawings available electronically in AK DOT’s current version of AutoCAD and deliver with paper set, along with a “.pdf” copy.

    - Provide one (1) paper set of manuals for the controller and Malfunction Management Unit with each cabinet. Make said manual available in electronic Adobe ".pdf" format and deliver with paper set.

  - Cabinet Wiring

Neatly arrange the wiring within controller cabinets to conform to the requirements of Subsections 660-3.05 and 740-2.05.  Furnish controller cabinets wired to accommodate

    - Configuration #4 in Table 5-2 of the NEMA Standards Publications No. TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP requirements with two each Type 2 detector racks.

      - Equip the cabinet with required control and auxiliary equipment connecting cables to operate the phases and detection indicated on the Plans, including future use.

      - Size wiring, switches, surge protectors, flash relays, and flashers to handle the necessary amperage required under full cabinet use.  Use orange colored wires to run from the flash transfer relay used for emergency flash programming.

      - Wire the cabinet to accommodate 6 unique preempt sequences as defined by NEMA TS-2 Section 3.7 and 2 auxiliary preempt sequences.  Configure each detector rack to accommodate 4 unique sequences.

  - Field Terminal Blocks

Provide Terminals and Facilities meeting the requirements of NEMA TS-2 Section 5, Configuration #4 (Table 5-2) and the following:

    - Provide 2 or more insulated terminal blocks to terminate field conductors.  Provide each block with 12 poles with 10-32 screw type terminals.  Use a terminal block that is a barrier type with removable shorting bars in each of the 12 positions and with integral type marking strips.  Terminate conductors to a terminal block.

    - Terminate conductors from the controller unit in ring type terminal lugs or solder them to a through panel solder lug on the rear side of the terminal.  Terminate other conductors in spade type terminal lugs.

    - Do not bring more than 3 conductors to any one terminal.  Two flat metal jumpers, straight or U shaped, may also be placed under a terminal screw.  Fully engage at least 2 full threads of terminal screws when the screw is tightened.  Do not extend live parts beyond the barrier.

    - Terminals must be provided to terminate a future 25 pair interconnect cable with each conductor terminated on individual terminals.  Terminate interconnect cable conductors on individual terminals.

    - On the right side of controller cabinets, install three (3) 16 position bus bars, for terminating the equipment grounding and neutral conductors used inside the cabinets.  On the left side of the controller cabinets, install one (1) 32 position bus bar and one (1) 16 position bus bar, for terminating the equipment grounding and neutral conductors from field wiring.

  - Cabinet Accessories

See NEMA Standard TS 2-2003 V02.06, Section 5 Terminals and Facilities, Figure 5-4 Cabinet Power Distribution Schematic for Items (1) through (6).

    - Disconnecting Means

      - Main circuit breaker must be a single pole, 20 ampere, 10,000 amperes interrupting capacity for each cabinet.

      - Auxiliary circuit breaker(s) must be single pole, 20 ampere, 10,000 amperes interrupting capacity to protect fan, heater, light, and convenience outlet(s).

The rating of the main disconnect means with overcurrent protection must be not less than 125% of the maximum anticipated continuous load.  When using disconnecting circuit breakers, use "trip indicating trip free," Type.

    - Signal Bus.  Connect the signal bus to the incoming AC line through a signal bus mercury contactor and an overcurrent protection device.  Energize the signal bus mercury contactor to provide power to the signal bus.  The current rating of the signal bus mercury contactor must be at least the current rating of the main overcurrent protection device.

    - AC Service Transient Suppression.  Connect the transient suppression device for the primary feed of the cabinet on the load side of the cabinet overcurrent protection device.  The transient voltage suppression device connected to the controller power circuit must provide protection against voltage abnormalities of 1 cycle or less duration.

      - The suppressor must be solid state high energy circuit containing no spark gap, gas tube, or crow bar component.  The current rating of the device must be 15 amps minimum.  The device must provide transient protection between neutral and ground, line and ground, as well as line and neutral.  If the protection circuits fail, they must fail to an open circuit condition.  The device must meet requirements of UL Standard 1449.

      - The suppressed voltage rating must be 600 volts or less when subject to an impulse of 6,000 volt, 3,000 amp source impedance, 8.0/20 microsecond waveform as described in UL Standard 1449.  In addition, the device must withstand, without failure or permanent damage, one full cycle at 264 volts RMS.

      - The device must contain circuitry to prevent self induced regenerative ringing.  There must be a failure warning indicator light that must illuminate when the device has failed and is no longer operable.  The transient suppression device must withstand a 20,000 ampere surge current with an 8x20 microsecond (time to crest x time to second halfcrest) waveform 20 times at 3 minute intervals between surges without damage or degradation to the suppressor.  Output voltage must not exceed 500 volts at any time during the test.  Use a device that is a solid state, high energy circuit with no spark gap, gas tube, or bar component.

    - Radio Interference Suppression.  Equip each traffic cabinet, flasher, and other current interrupting device with a suitable radio interference suppressor installed at the input power point.  Install the radio interference suppressor after the AC service transient suppression unit described in Subsection 740-2.11.1.k (3).  It must provide a minimum attenuation of 50 decibels over a frequency range from 200 kilohertz to 75 megahertz, when used with normal installations.

      - The interference suppressor must be hermetically sealed in a substantial metal case filled with suitable insulating compound. Terminals must be nickel plated, 10-24 brass studs of sufficient external length to provide space for connecting two No. 8 conductors and must be so mounted that the terminals cannot be turned in the case.  Ungrounded terminals must be properly insulated from each other and must maintain a surface leakage distance of not less than 1/4 inch between any exposed current conductor and any other metallic part, with an insulation factor of 100 to 200 megohms dependent on external circuit conditions.

      - The radio interference suppressor must have a minimum current rating equal to the rating of the main disconnect means as specified in Subsection 740-2.11.1.k (1) (a).  It must be designed for operation on 120 volts, 60 hertz, single phase circuits and be UL and EIA compliant.

      - Connect the ground connection of the radio interference suppressor only to AC neutral.  Do not connect to Earth Ground directly.

    - Communications Transient Suppression.  Provide a transient suppressor for the system interface communications lines when used.  This suppressor must withstand a 100 ampere 10 x 700 microsecond waveform 20 times at 30 second intervals between surges without damage or degradation to the suppressor.  Apply the transient surge both line to line and line to ground. Output voltage must not exceed 8 volts line to line and line to ground.  Output voltage must not exceed 8 volts line to line or 250 volts line to ground at any time during the test.

    - Control Panel.  Provide and label a control panel assembly that is readily accessible from the front of the cabinet. The control panel assembly must consist of:

      - "controller power" switch to energize the controller while the signal lights are off or are being operated by the flasher.  Label and rate the switch for load current.

      - An electrical outlet.  It must be a duplex, 3 prong, NEMA Type 5-20R grounding type outlet with independent ground fault circuit protection.

      - "auto/flash" switch that when placed in the "flash" position provides flashing operation without interrupting the controller unit power. When the switch is placed in the "auto" position the controller unit must provide normal operation.

      - "stop time/off/on" switch that when placed in the "stop time" position causes the controller unit to stop time.  In the "off" position, the controller unit must be active regardless of external commands.  In the "on" position, the timing must be normal but subject to external command interruptions.

      - momentary contact test switches to place calls on each vehicle and pedestrian phase.  Switches must provide tactile feedback and be rated at 1 ampere, minimum, for a resistive load at 120 VAC and at 28 VDC.  Contacts must be coin silver or gold plated and be enclosed and labeled as to their function.

      - Tamper-proof toggle covers on door control switches.

    - Police Panel Assembly. Provide a Police Compartment meeting the requirements of NEMA TS-2 Section 7.5.7.  The Police Compartment shall include a Universal Serial Bus (USB) port allowing connectivity with the controller when the door is closed and house the following switches with permanent labels:

      - "flash/automatic" switches that when placed in the "flash" position causes the intersection displays to go into the flashing mode.  When placed in the "automatic" position, the signal system must resume normal operation.

      - "signals on/off" switch that when placed in the "off" position removes power from the signal bus.  Do not allow power on the bus when either "automatic" or "flash" operation is selected by any means.

    - Power panel cover.  Provide a clear plastic cover over the power panel and Utility power terminal block.  Cover shall be a minimum thickness of 0.1” and firmly attach at four points. Holes shall be slotted for easy removal and replacement.

    - Power Input Module. Provide an Econolite Zinc Blue Power Input Module (PIM).

      - Separate the power circuit for auxiliary equipment not intended to be powered by UPS or generator per plans and specifications.

      - Wire signal equipment to be powered by UPS or generator through existing individual breaker, filters, sine wave trackers, surge protector, and PIM or size new breaker, if required.

    - Power outlet strips. Provide filtered aluminum power strip(s) as listed in the Plans. Power strips shall have 125 volt receptacles and 15 amp thermal-type circuit breakers with resets.

- Special Features.  Provide special features if called for in the Plans or as specified in the Special Provisions.

Coordination "Remote/Time of Day/Free" Switch.  When the switch is in the "Remote" position, supervisory functions performed on the controller unit from a master coordinator or central computer must operate normally.

When the switch is in the "Time of Day" position, the local controller must use the local coordinators time of day plan.  When the switch is in the "Free" position, it must be possible to remove any or all coordination devices and maintain normal, non-coordinated controller operation without wire jumpers, jumper plugs or other special devices.  Provide this switch if a local coordination or system modem/interface unit is shown on the Plans.

740-2.12 STANDARD AUXILIARY EQUIPMENT.

Provide equipment meeting the requirements of Section 6 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

- Three Circuit Solid State Load Switches.  Use load switches conforming to NEMA TS-2, Section 6.2 Three Circuit Solid State Load Switches and as a minimum include Light Emitting Diode indicators on the DC input circuitry.  The load switch must have three independent switching circuits, each being an individually replaceable solid state module.

- Solid State Flasher.  Use a NEMA Type III flasher unit that conforms to NEMA TS-2, Section 6.3 Solid State Flashers.

- Malfunction Management Unit (MMU2).  Provide Type 16 MMU2 to be fully compliant with the requirements of NEMA TS-2, Section 4.  In addition, the MMU2 shall have a full intersection LCD back lighted signal on the front panel and shall be downward compatible with TS-1 CMUs.

- Flash Transfer Relay.  Use flash transfer relays that meet the requirements of NEMA TS-2, Section 6.4 Flash Transfer Relays.

- Load Switch Test Socket. Provide a 120V AC receptacle to allow for bump testing of indications.

740-2.13 SPECIAL AUXILIARY EQUIPMENT. Use the following special auxiliary equipment when called for on the Plans and/or Special Provisions:

Provide equipment meeting the requirements of the cited Sections of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

- Local Coordination Units.  Provide actuated coordination that conforms to the requirements of NEMA TS-2, Section 3.6 Actuated Coordination.

- System Modem/Interface Unit.  Supply a system modem/interface unit assembly that is compatible with the existing computerized traffic control system.

- Preemption Units.  Provide preemption that conforms to the requirements of NEMA TS-2, Section 3.7 Preemption and the following:

Install the following components of the GTT Company’s Opticom Priority Control System according to GTT’s written installation instructions at the signalized intersections listed on the Plans.

  - The system must be capable of sending a signal to the controller when an Opticom signal from a vehicle-mounted "GTT OPTICOM Emitter" has been received and maintained for a period of 1.7 seconds.

  - Unless otherwise shown on the Plan use Opticom Traffic Control Systems Opticom Detector Model 721 preemption detectors for infrared detector units and Opticom Model 3100 GPS/Radio Unit containing a GPS receiver with Antenna and a 2.4 GHz spread transceiver with antenna for GPS detector units.

  - Furnish the appropriate number of Opticom Traffic Control Systems 764 Phase Selectors to meet the number of channels of detection for each intersection. Use rack mounted phase selectors.

  - The controller cabinet shall be wired with a Model 768 Auxiliary Interface Panel for the full utilization of all auxiliary detector and green sensing operations of the 764 Phase Selectors. Wire the cabinet with a Model 757 Auxiliary harness for interface between cabinet terminal blocks and Model 768 Auxiliary Interface panel.

  - Install Model 138 detector lead in cable between the end of each signal mast arm and the controller cabinet for infrared detector units. Install Model 1070 GPS Installation cable when GPS units are specified.  Furnish enough slack in these cables for them to extend 2 feet beyond the end of each signal mast arm and to leave 10 feet of slack in the controller cabinet.  Seal both ends of each lead in cable with mastic lined, heat shrink tubing end caps.

  - The controller, rather than the phase selector or auxiliary logic, must perform interval timing, signal sequences, and phase skips.

  - Mount detectors according to manufacturer recommendations or as approved by the Engineer.  Mount and aim detectors to provide maximum emergency vehicle recognition.  Detector locations shown on the Plans are approximate and subject to change as directed by the Engineer.

  - When emitters are required, provide GTT Opticom Priority Control System, Model 794HM Emitter with Model 2100 High Priority Radio/GPS Vehicle Control Unit and 210 Vehicle Interface Cable. The Emitter shall be factory programmed to the class and vehicle identification numbers assigned by jurisdiction as shown in the Plans and the following:

    - Class 0 and Vehicle ID. Number 0 (Zero) shall be disabled for Emitters.

    - Vehicle Id. Numbers shall be sequential, beginning with the lowest number in the EVP Emitter table for the appropriate class.

    - Provide one copy of 790IS Emitter Software Kit including "Y" cable.

    - One GTT Opticom Portable Emitter Kit with 794R emitter on a magnetic base, 793R switch and cigarette lighter adapter power cord in a "Camera Bag" case.

  - Manufacturer Assisted Start up.  The Contractor shall retain the services of a representative from the GTT Opticom GPS equipment manufacturer and the controller equipment manufacturer Econolite (collectively Manufacturer’s Representative), subject to the approval of the Engineer.  The Manufacturer’s Representative shall have previous experience with either the Central Region DOT&PF or Northern Region DOT&PF in assisting with traffic signal controller testing, field testing and turn on.  Submit name(s) and professional credentials at least 30 days before beginning this work.  When required, work on, and connections to, the Opticom GPS preemption system, vehicle equipment, and related equipment shall be performed by or directly supervised by a qualified person serving as the Manufacturer’s Representative.

On-Site manufacturer assisted startup will be required for all intersections scheduled for GPS Opticom installations shown in the Plans. Red-lined cabinet prints shall be altered electronically and provided in hard copy, “.pdf”, and AutoCAD format for each cabinet receiving GPS Opticom installation.

Telephonic manufacturer assisted start-up required for all intersections that do not require on-site manufacturer assisted start up as indicated above.

- Required Credentials of Manufacturer’s Representative

  - 10 years experience working in the traffic controller industry, 5 years of that must have been as a signal technician.

  - Must have IMSA Traffic Signal Technician, Level II certification

  - Experience assisting with the Northern Region ADOT, or the Central Region ADOT

  - Familiarity with both the NEMA TS1 and TS2 specifications

  - Competent to read cabinet wiring diagrams and troubleshoot cabinet components

  - Competent to troubleshoot Preemption issues

  - Competent to test and Install GPS Preemption components

  - Competent to conduct training on installed components

- Training Except as otherwise noted, immediately preceding or following the Manufacturers Startup of the GPS Opticom System, the vendor shall provide training. All training is to be provided by a representative of the original equipment manufacturer. Training may be attended by any number of ADOT personnel from any of its three regions. Required training includes:

  - Provide 7.5 hours of instruction on the proper setup of the Radio/GPS Opticom Emergency Vehicle Preemption system. Training is to include all information necessary to properly set up and operate the Radio/GPS Opticom system as well as instruction on integration or use of the Opticom equipment/software with the Traffic Management system software, Centracs. The training audience is ADOT & MOA traffic Engineers. Deliver training time, day and location mutually agreeable to the contractor and the Traffic Design or Operations Engineer.

  - When emitters are included in the project provide two (2) 4.0 hour sessions of instruction on the proper use of the Radio/GPS based Opticom emitter. Training must be provided by a representative authorized by the original equipment manufacturer. Training is to include all information necessary to properly operate the Radio/GPS Opticom emitter. Deliver training at a time, day and location mutually agreeable to the contractor and the Traffic Design or Operations Engineer. One of the two training sessions will be delivered in the evening between 6:00pm and 12:00 am. Note; training will not be accepted until contract required equipment is delivered

  - Upon completion of training the manufacturer representative shall provide two (2) copies on thumb drives and two (2) copies on CD of any software required for setup, operation of, or maintenance of the GPS Opticom system components. This includes but is not limited to On-Site Interface Software and Central Managements Software.

- Bus Interface Unit (BIU).  Provide BIU’s that fully meet the requirements of NEMA TS-2 Section 8.  Unless otherwise called for in the Plans provide BIU’s that meet the NEMA designation BIU2.

- Traffic Logging System.  If called for in the Plans, furnish, and install in the controller cabinet, a stand-alone unit that collects, time stamps, and stores data in an unattended manner.

- Radar Detection System.

a.	System Hardware. For vehicle detection, provide a complete and functional Wavetronix digital wave radar vision system, Econolite AcccuScan or Smartmicro Type 42 forward-fire radar system, or approved alternative including the following:

(1)	Stop bar detector (SBD). For all approaches indicated in the plans, provide an above-ground stop bar detector (SBD). If utilizing a Wavetronix digital wave radar vision system, provide a Wavetronix SmartSensor Matrix®. Otherwise provide an AccuScan 600C, Smartmicro Type 42, or approved alternative.

(a) 	Testing. Each sensor shall be Federal Communications Commission (FCC) certified under CFR 47, Part 15, section 15.249 as an intentional radiator and a FCC certification shall be displayed on an external label on each SBD according to the rules set forth by the FCC. The SBD shall also be tested under IEC 61000-4-5 class 4 and NEMA TS2-2003 Testing. The SBD shall comply with the applicable standards stated in the NEMA TS2-2003 Standard. Third party test results shall be made available when requested.

(b)	Support. The SBD manufacturer shall provide both training and technical support services.

Training. The manufacturer-provided training shall be sufficient to fully train installers and operators in the installation, configuration, and use of the SBD to ensure accurate SBD performance.

Technical Assistance. A manufacturer-provided technical representative shall be available to assist with the physical installation, alignment, and configuration of each supplied SBD. Technical support shall be provided thereafter to assist with troubleshooting, maintenance, or replacement of SBDs should such services be required.

(c)	Documentation. SBD documentation shall include an instructional training guide, a comprehensive user guide, as well as an installer quick-reference guide and a user quick-reference guide. The SBD manufacturer shall supply the following documentation and specification test results at the time of the bid submittal:

        - FCC CFR 47 certification

        - IEC 61000-4-5 class 4 test report

    - Continuous tracking advance extended range detector (CTAD). For all intersection approaches indicated in the plans defined with high AADT, provide a CTAD. If Wavetronix digital wave radar vision system is used, provide a Wavetronix SmartSensor Advance Extended Range®. Otherwise provide an approved alternative. If utilizing an Econolite AcccuScan or Smartmicro Type 42 forward-fire radar for stop bar and advanced detection, no CTAD is needed.

      - Testing. Each CTAD shall be Federal Communications Commission (FCC) certified under CFR 47, Part 15, section 15.249 as an intentional radiator and a FCC certification shall be displayed on an external label on each SBD according to the rules set forth by the FCC. The SBD shall also be tested under IEC 61000-4-5 class 4 and NEMA TS2-2003 Testing. The SBD shall comply with the applicable standards stated in the NEMA TS2-2003 Standard. Third party test results shall be made available when requested.

      - Support. The CTAD manufacturer shall provide both training and technical support services.

Training. The manufacturer-provided training shall be sufficient to fully train installers and operators in the installation, configuration, and use of the detector unit to ensure accurate CTAD performance.

Technical Assistance. A manufacturer-provided technical representative shall be available to assist with the physical installation, alignment, and configuration of each supplied detector unit. Technical support shall be provided thereafter to assist with troubleshooting, maintenance, or replacement of the detector unit should such services be required.

      - Documentation. Documentation shall include an instructional training guide, a comprehensive user guide, as well as an installer quick-reference guide and a user quick-reference guide. The manufacturer shall supply the following documentation and specification test results at the time of the bid submittal:

        - FCC CFR 47 certification

        - IEC 61000-4-5 class 4 test report

    - Cabinet interface system. As shown in plans for permanent signals and for each temporary signal cabinet, provide the devices required by the radar system manufacturer to provide streamlined communication from radar sensors to traffic controllers. This system shall communicate directly to the controller through SDLC, and support contact closure devices as well. It shall also provide power, surge protection, and Ethernet connectivity for all sensors.

      - Mounting.

        - Shelf-mount or DIN rail mount

      - Connections and Communications.

        - One RJ-45 10/100 Ethernet jack

        - One SDLC port

        - Four or six ports for connecting to sensors via RS-485

        - USB connector

      - Testing.

        - Complies with the applicable standards stated in the NEMA TS2-2003 Standard

        - FCC-compliant

        - Passes manufacturers test before shipping

  - Configuration software. Provide software from the radar system manufacturer to configure and monitor the radar sensors.

  - Detector mount. Provide a mounting assembly from the radar sensor manufacturer for each sensor.

  - Installation Kit. Provide an installation kit from the radar system manufacturer, for use while installing and configuring radar vehicle sensing devices or continuous tracking advance detectors and in-cabinet contact closure and communication connectivity devices.

  - Econolite AccuScan 600C or Smartmicro Type 42 forward-fire radar: For each sensor, provide a manufacturer recommended 4-pair communication cable of length to run without splicing from the radar sensor to the cabinet interface system inside the controller cabinet. Provide 15 feet of neatly coiled slack cable in the base of the controller foundation. Provide 5 feet of slack at the mast arm simplex.

  - Wavetronix APT Matrix Type 2 Home Run cable. For each detector provide a cable of length to run from the in-line terminal enclosure at the pole base handhole to the cabinet interface system inside the controller cabinet. Provide 15 feet of neatly coiled slack cable in the base of the controller foundation. Provide sufficient slack at pole, so the in-line terminal enclosure can be pulled out of the handhole for maintenance work.

    - Smartsensor Cable Junction Box. For each Wavetronix digital wave radar vision system radar sensor, provide a Type 4X cable junction box enclosure to connect the Wavetronix 6-conductor cable to the APT Matrix 2 HomeRun cable.

    - SmartSensor 6-conductor cable. For each Wavetronix digital wave radar vision system detector provide a cable of length indicated in the plans.

- Pan-Tilt-Zoom (PTZ) Camera.

  - Furnish an Axis Q6010-E 60 Hz Camera with the following specifications:

- Micro SDXC card with a capacity of 256GB and speed class U3 or V30

  - Furnish an Axis Q6075-E PTZ Dome network camera 60Hz camera with the following specifications:

- Power with Axis High PoE midspan 1-port 100-240 V AC, max 60 W.

- Micro SDXC card with a capacity of 256GB and speed class U3 or V30.

  - Include T91 mounting accessories.

740-2.14 VEHICULAR SIGNAL HEADS.  Provide Light Emitting Diode, (LED) Signal Heads that conform to the following publications:

- Circular Indications: Vehicle Traffic Control Signal Heads:  Light Emitting Diode (LED) Circular Signal Supplement, 6/27/05 (ITE Publication ST-052). This is hereafter referred to as “VTCSH-Circular-05”.

- Arrow Indications: Vehicle Traffic Control Signal Heads – Light Emitting Diode (LED) Vehicle Arrow Traffic Signal Supplement, 7/1/07 (ITE Publication ST-054). This is hereafter referred to as “VTCSH-Arrow-07”.

“The applicable ITE Specification”, as used in this specification, means VTCSH-Circular-05 for circular LED indications and VTCSH-Arrow-07 for arrow LED indications.

- Signal Heads.

Use signal heads that: are the adjustable, vertical type with the number and type of lights specified; provide a light indication in one direction only; are adjustable through 360 degrees about a vertical axis; and are mounted at the location and in the manner shown on the Plans. Ensure that all vehicular signal heads at any one intersection, except for programmed visibility signal heads, are of the same make and type.

Programmed Visibility Signal Heads.

  - Indications provide a nominal 12 inch diameter circular or arrow indication.  Meet the VTCSH requirements for color and arrow configuration.

  - Provide each section with a 1 inch cutaway visor.

  - Provide each signal section with an adjustable connection that permits incremental tilting from 0 to 10 degrees above or below the horizontal while maintaining a common vertical axis through couplers and mounting axis in 5 degree increments.

  - The signal must be mountable with ordinary tools and capable of being serviced without tools.  Preset the adjustment at 4 degrees below the horizontal.

  - The visibility of each signal face must be capable of adjustment or programming within the face.  When programmed, each signal face's indication must be visible only in those areas or lanes to be controlled.  During dusk and darkness, a faint glow to each side will be permissible.

  - Program the head as recommended by the manufacturer and as directed by the Engineer.

Provide a removable aluminum tunnel visor with an open slot at the bottom for each optical unit.

Furnish housing, backplates and visors factory finished with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D3359, ASTM D3363 and ASTM D522. Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

  - LED Optical Units.  Use LED optical units and lenses meeting the requirement of the applicable ITE specification for all indications.  Also meet the following requirements:

    - Gaskets. Use one-piece EPDM (ethylene propylene rubber) gaskets to seal LED modules.

    - Markings. Provide LED Signal module with manufacturer applied markings listed in Section 3.6, Module Identification, of the applicable ITE Specification.  For circular indications marking shall include: “Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads: LED Vehicle Circular Traffic Signal Supplement (June 27, 2005).”  For arrow indication markings shall include: “Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads: LED Vehicle Arrow Traffic Signal Supplement (July 1, 2007).”

    - Compatibility. Use LED signal modules that are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

    - Testing Requirements.

        - All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

        - Burn-in. Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

        - Production Testing and Inspection.  Submit manufacturer’s certification that all tests in Section 6.3 of the applicable ITE Specification have been successfully completed on each LED module to be used on the project.

Show results of each individual test on the certification.

        - Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA “Nationally Recognized Testing Laboratory” do the following:

              - Perform an initial assessment of the manufacturer’s factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

              - Perform initial Design Qualification Testing as specified in Section 6.4 of the applicable ITE specification.

              - Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following sections of the applicable ITE specification:

6.4.2 Conditioning 
6.4.4.1 - 6.4.4.4 Luminous Intensity 
6.4.4.6 Chromaticity 
6.4.6.1 Current Consumption 
6.4.6.6 Power Factor 
6.4.6.7 Total Harmonic Distortion

              - Provide a certification label on each certified LED traffic signal module verifying the manufacturer’s factory and modules passed the tests listed in a. through c. above.

    - Warranty. Provide written warranty by the signal module manufacturer that covers defects in materials, workmanship, and compliance with the applicable ITE specification for a period of 60 months after the manufacture date.  No new LED module will be accepted if its manufacture date is more than 12 months before the date of installation.  Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules. The warranty does not include the cost of removing failed modules or reinstalling new modules. Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

  - Lens.  Use only clear lenses for all green signal modules.  Use lenses that meet the requirements of the applicable ITE Specification.

  - Housing.

  - Use die cast aluminum, meeting ASTM B85, for all parts of the housing, including the doors and end plates. Ensure all parts are clean, smooth, and free from flaws, cracks, blow holes, or other imperfections.

  - Use a one-piece housing with integral top, bottom, sides, and with square doors, for each signal section.

  - Use stainless steel for all exposed bolts, screws, hinges, pins, and door-locking devices.  Use stainless steel or approved non-ferrous, corrosion-resistant material for all interior screws and fittings.

  - Provide an opening in the top and bottom of each housing to accommodate standard 1-1/2 inch pipe fittings and brackets.

  - Provide the top and bottom openings of each housing with integral serrated bosses that will provide positive positioning of the signal head in 5-degree increments to eliminate undesirable rotation or misalignment of the signal head as well as between sections.  Provide a total of 72 teeth in the serrated boss.  Ensure teeth are clean and sharp to provide positive position with the grooves of the mating section or framework.

  - Fasten individual signal sections together with a cadmium-plated tri-stud connector, lock washers, and nuts with access holes for the passage of electrical conductors form one section to another.

  - Provide 2 integral hinge lugs on the left side of each signal housing for mounting the door.

  - Provide 2 latches with stainless steel wing nut assemblies on the right side of each signal housing to engage the door latches.

  - Provide each signal housing door opening with a one-piece EPDM gasket around the periphery to provide a weather tight seal in a NEMA Type 3R enclosure.

  - Provide a round opening designed to accommodate any standard traffic signal lens in each signal housing door.

  - Backplates.  Backplates shall not be louvered.  Install backplates around vehicular signal faces except post mounted flashers.  Furnish backplates constructed of 0.100 inch minimum thickness aluminum alloy sheet meeting ASTM B209, alloy 3003-H14.  For those backplates fabricated from 2 or more pieces of sheeting, furnish them fastened together with 3/16" aluminum rivets or bolts peened after assembly.

Furnish 3 inch wide backplates regardless of where the signals are installed, on mast arms, on top of posts, or on the sides of poles.

  - Signal Mounting Hardware: Furnish elevator plumbizers, elbow pipe fittings, and post top adapters (without a terminal compartment) with integral serrated contacts that feature 72 teeth.

Provide signal heads that will be mounted on mast arms or pipe tenons with ferrous or bronze elevator plumbizers.

For signal faces installed on the sides of poles, furnish signal frames that consist of watertight assemblies of 1 1/2 inch nominal diameter standard steel pipe, malleable iron or brass pipe fittings, and bronze terminal compartments.  The side of the terminal compartment opposite the door shall feature a saddle shape for wobble free mounting on round poles and include a cable guide and two holes for mounting the compartment.

Furnish vehicular signal frames with a horizontal dimension between the center of the terminal compartment and the axis of the adjacent signal face of 22 inches in side mounted frames and 11 inches on double headed post top installations.

Post top adapters shall slip fit over 4 inch nominal standard pipe and feature two rows of three cadmium plated steel setscrews.  Furnish post top adapters with terminal compartments, except one way signal heads may be installed on adapters without a terminal compartment provided the adapters include offset openings.  Post top adapters without a terminal compartment or compartments - provide manufactured of bronze metal.

Furnish terminal compartments with a terminal block containing 12 poles, each with two screw type terminals.  Each terminal must accommodate at least three 14 AWG conductors.  Provide terminal compartments with a rain tight door that provide ready access to the terminal block.

For mounting each terminal compartment, furnish (2) 1/2" x 13 hot dip galvanized bolts that conform to ASTM A325 and (2) 1/2" hot dip galvanized washers that conform to ASTM F 436.

When replacing signal heads include all mounting hardware, backplates and visors.

  - Finish. Factory finish housing, brackets, fittings, backplates, and visors, each face, with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363, and ASTM D-522.  Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

740-2.15 PEDESTRIAN SIGNALS. Use LED Pedestrian Countdown modules that use the international "HAND/WALKING PERSON" symbols.  Except for the countdown indication and as otherwise noted in this specification, use modules that conform to “Pedestrian Traffic Control Signal Indications - Part 2: Light Emitting Diode (LED) Pedestrian Traffic Signal Modules” Institute of Transportation Engineers, 3/19/2004, (hereafter referred to in this document as “PTCSI-04”) and to the applicable Sections of the current Alaska Traffic Manual.

Provide pedestrian signal heads according to the following:

  - Pedestrian Signal Modules: Provide Portland Orange “HAND” and “COUNTDOWN DIGITS” and lunar white “WALKING PERSON.”   Locate COUNTDOWN DIGITS adjacent to the associated UPRAISED HAND.    Make “HAND” and “WALKING PERSON” symbols a minimum of 11 inches high and 7 inches wide and COUNTDOWN DIGITS a minimum of 9 inches high and 7 inches wide.  Provide incandescent looking WALKING PERSON, HAND and COUNTDOWN DIGITS.  Ensure the WALKING PERSON, UPRAISED HAND and COUNTDOWN DIGITS are not readily visible when not illuminated.  Provide “AlInGaP” Portland Orange LEDs or equivalent, rated for 100,000 hours or more at 77ºF and 20 mA. Provide “InGaN” White LEDs.

Make all exposed components of modules suitable for prolonged exposure to the environment, without appreciable degradation that would interfere with function or appearance.

Provide modules with an installed gasket to seal the junction with the signal housing.

  - Lens.  Use modules with internal masks to prevent the icons and digits from being visible when not in operation. No external silk-screen is permitted. Provide a smooth or textured lens of transparent polycarbonate material, frosted to prevent sun phantom. Use lenses that will not crack, craze or yellow due to solar UV exposure typical for a south-facing Arizona desert installation, after a minimum of 60 months in service.

  - Retrofit.  When a module will replace an existing module in an existing signal housing, furnish signal modules designed as retrofit replacements for existing neon type pedestrian signals (ICC 4090 and/or 4094).  Provide modules that do not require special tools for installation. Provide modules that fit securely into existing pedestrian signal housings without any modification to the housing, connect directly to existing electrical wiring, and form a weather-tight seal. Provide modules and components constructed so each retrofit of existing pedestrian signals only requires the removal of the existing neon message module, gasket, and power supply and installation of the new LED pedestrian countdown module. Provide all necessary components to complete conversion including a one piece gasket.

  - Photometric Requirements.  Meet the following requirements:

    - Minimum Luminance.  Maintain the following minimum luminance values for at least 60 months, under the operating conditions defined in Sections 3.3.1 and 5.2.1 of PTCSI-04 (when measured normal to the plane of the icon surface):

        - WALKING PERSON 2,200 cd/m2,

        - UPRAISED HAND 1,400 cd/m2,

        - DIGITS 1,400 cd/m2 (when “88” is displayed).

    - Maximum Luminance.  Provide modules for which the actual luminance of a module does not exceed three times the minimum maintained luminance, as defined in Section 4.1.1 of PTCSI-04,  when operated within the temperature range -40°F to +165°F

    - Uniformity:  Provide modules for which the uniformity of the signal output across the emitting section of the module lens (i.e. icons or digits) does not exceed a ratio of 5 to 1 between the maximum and minimum luminance values as measured in 0.5 in. diameter spots.

    - Markings. Permanently mark the back of each LED signal module with:

        - Manufacturer’s name, trademark, and other necessary identification

        - Warranty information

        - Rated voltage and power consumption in volt-amperes

        - An up arrow or the word “UP” or “TOP” for orientation within a signal housing.

  - Electrical. Provide LED pedestrian countdown signal modules that:

    - Are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

    - Have a maximum of 4 each secured, color coded, 36 inches long, 600V, 18 AWG minimum, jacketed wires, conforming to the National Electrical Code, rated for service at +221ºF for electrical connection.

    - Operate from a 60 ±3 Hz AC line over a voltage range of 80 VAC to 135 VAC. Test voltage for all photometric performance measurements shall be 120 ±3 volts rms.

    - Use LED circuitry that prevents perceptible flicker over the voltage range specified above.

    - Include voltage surge protection against high-repetition noise transients and low-repetition noise transients as stated in Section 2.1.8, NEMA Standard TS-2, 2003.  Module must meet the following test requirements:  Section 8.2 IEC 1000-4-5 & Section 6.1.2 ANSI/IEEE C62.41.2, 3kV, 2 ohm and Section 8.0 IEC 1000-4-12 & Section 6.1.1 ANSI/IEEE C62.41.2, 6kV, 30 ohm.

    - Have a current draw sufficient to ensure compatibility and proper triggering and operation of load current switches and conflict monitors in signal controller units. When the module is switched from the On state to the Off state the terminal voltage shall decay to a value less than 10VAC RMS in less than 100 milliseconds when driven by a maximum allowed load switch leakage current of 10 milliamps peak (7.1 milliamps AC).

    - Have a maximum power consumption at 77°F of:  Hand 11.0 watts, Walking Person 8.0 watts, Digits 10.0 watts (when display shows “88”)

    - Have waterproof strain relief and anti-capillary wires, or have electrical wires that do not penetrate the LED module housing.  This is intended to prevent water seepage between the back cover and the electrical wires, or between the copper and insulation of the wires (Connection may be made by use of an over molded connector).

    - Will default to the hand symbol for abnormal conditions when nominal voltage is applied to the unit across the two phase wires (rather than being applied to the phase wire and the neutral wire).

    - Have three separate power supplies: one each for the Walking Person, the Upraised Hand and the countdown digits.  Use separate circuitry to power the LED Walking Person icon and the LED Upraised Hand icon, in order to virtually eliminate the risk of displaying the wrong icon.

  - Testing Requirements.

    - All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

    - Burn-in.  Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

    - Production Testing and Inspection by Manufacturer    Submit manufacturer’s certification that all tests in Section 6.3 of PTCSI-04 have been successfully completed on each LED module to be used on the project.  Show result of each individual test on the certification.

    - Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA “Nationally Recognized Testing Laboratory” do the following:

        - Perform an initial assessment of the manufacturer’s factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

        - Perform initial Design Qualification Testing as specified in Section 6.4 of the PTCSI-04.

        - Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following sections of PTCSI-04:

6.4.2 Conditioning 
6.4.4.1 - 6.4.4.4 Luminous Intensity 
6.4.4.6 Chromaticity 
6.4.6.1 Current Consumption 
6.4.6.6 Power Factor 
6.4.6.7 Total Harmonic Distortion

        - Provide a certification label on each certified LED traffic signal module verifying the manufacturer’s factory and modules passed the tests listed in a. through c. above.

  - Warranty. Provide a manufacturer’s written warranty that covers defects in materials, workmanship, and compliance with PTCSI-04 for a period of 60 months after the manufacture date.  No new LED module will be accepted on a project if its manufacture date is more than 12 months before the date of installation. Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules. The warranty does not include the cost of removing failed modules or reinstalling new modules. Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

  - Countdown Module Functions.

    - General.  Begin the countdown at the beginning of the FLASHING HAND indication.  End the countdown at “0” at the end of the FLASHING HAND indication.  Make the countdown display dark from the end of one FLASHING HAND indication until the beginning of the next. Display steady, not flashing, countdown digits.  Do not provide user accessible switches, controls, or options that would allow modification of cycle time, icons, digits or that would allow the countdown to operate while the WALKING PERSON or STEADY HAND is displayed.

    - Learning Cycle.  At power on, make the countdown display dark for one learning cycle in which it will determine the duration of the FLASHING HAND indication.

    - Normal Operation.  Display the countdown/FLASHING HAND for the duration measured in the learning cycle for every cycle until the module measures a different FLASHING HAND duration.

    - Countdown Duration Modification.  When a different duration is measured, make the countdown dark for the next cycle, and enter a Learning Cycle as previously described. Resume Normal Operation with the new FLASHING HAND duration if the measured FLASHING HAND duration for the next cycle is the same as for the first cycle when a change was detected. Continue Learning Cycles, if the duration is different, until the measured FLASHING HAND duration is the same for two cycles. Resume Normal Operation with the new duration when that happens.

    - Countdown Truncation.  Make the digits dark if the controller output displays a STEADY HAND or if both the HAND and WALKING PERSON go dark, regardless of whether the countdown to zero has been completed.

    - Preemption.  Handle preemption events as described under Countdown Duration Modification and, if necessary, Countdown Truncation.

    - Recycling.  Allow for consecutive cycles without display of the STEADY HAND.

    - Power Outage.  Maintain an uninterrupted countdown during short power failures (<1.5 seconds).  Make the digits dark after a loss of power of more than 1.5 seconds and enter a Learning Cycle when the power is restored.

- Housing

  - Provide signal housings that have a maximum overall dimensions of 18-1/2 inches wide, 18-3/4 inches high, and 9 inches deep.

  - Provide a dustproof and weatherproof housing that allows easy access to and replacement of all components.

  - Provide a one-piece, corrosion-resistant, aluminum-alloy die-cast case complete with integrally cast top, bottom, sides and back. Provide 4 integrally cast hinge lug pairs, 2 at the top and 2 at the bottom of each case, for operation of a swing-down door.

  - Provide 1 of the following 3 versions of the case, according to project specifications:

    - Clamshell mount, with hardware, for “pole left of message” installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight. No other openings are allowed.

    - Clamshell mount, with hardware, for “pole right of message” installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight. No other openings are allowed.

    - Make suitable for either post top or bracket mounting with upper and lower openings to accommodate standard 1-1/2 inch pipe brackets.  Plug unused openings to be weathertight. This case is only allowed when called for in the plans.  Integrally cast a shurlock boss into the bottom opening of the signal case. Make the dimensions of the shurlock boss as follows: outside diameter, 2-5/8 inch; inside diameter, 1-31/32 inch; number of radial teeth, 72; and depth of teeth, 5/64 inch. Use clean and sharp teeth that provide full engagement to eliminate rotation or misalignment of the signal.

  - Make the door frame a one-piece, corrosion-resistant, aluminum-alloy die-casting, complete with 2 hinge lugs cast at the bottom and 2 latch slots cast at the top of each door. Attach the door to the case by means of two Type 304 stainless steel spring pins. Attach 2 stainless steel hinged bolts with captive stainless steel wing nuts and washers to the case with the use of stainless steel spring pins. Provide a door that will latch and unlatch without the use of tools.

- Conductors:  Meet IMSA specifications 20-1 with No. 14 AWG or larger.

- Load Switches: Place all load switches for operation of pedestrian signals in the controller cabinet.

- Fasteners.  Use machine screws, studs, and washers that are stainless steel.

- Gaskets:  Use gaskets that conform to ASTM D1056, Grade 2C2.

- Terminal Blocks:  Provide a rain tight terminal compartment with a 12 position terminal block.

- Finish.  Factory finish the outside of pedestrian signal head housings and visors and signal visor interiors with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D3359, ASTM D3363 and ASTM D522. Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

740-2.16 PEDESTRIAN PUSH BUTTONS.  Push buttons shall be Tamper proof with a 2 inch minimum diameter convex 316 stainless steel actuator button.

Construct a weatherproof assembly designed to prevent an electrical shock under any weather condition and grounded per the NEC.

Push Button Switch.  Furnish Polara model RBDLM2-B-4H or approved equal with the following features.  Provide a solid state electronic piezo type, switching unit, with screw type terminals, rated 15 amperes at 125 VAC.  Must have the following characteristics:

            - Switching unit that is solid state electronic piezo rated for 100 million cycles.

            - Sealed to prevent ice from impeding function.

            - Must hold the call for a minimum of 5 seconds.

            - Switch operating force of 3 pounds or less with no moving plunger or moving electrical contacts.

            - Provide an LED indication and an audible tone or beep within the button when pushed, at a minimum 68 db. at 1 meter.

            - Must have a raised rim or ridges to protect the button from side impacts.

            - Powder coated cast switch housing.

Where a pedestrian push button is to be mounted on top of a 2-1/2 inch diameter post, provide the housing with a slip-fitter with screws for securing to the post.

Factory finish pedestrian push button housings, mountings, brackets, and fittings with 2 coats of dull black enamel or powder coat.  Painting/powder coating is not required where the color is an integral part of the component material.

740-2.17 FLASHING BEACONS.  Furnish beacons that consist of one or more traffic signal sections meeting the requirements of Subsection 740-2.14 Vehicular Signal Heads. See the Plans for the number, size and color of the signal sections required for each beacon.

Use the flasher in signal controller cabinets to energize beacons that flash continuously and are installed near traffic signals.  Otherwise, each flashing beacon controller assembly consists of the following 120 VAC equipment housed in a NEMA 3R enclosure: a circuit breaker, a radio interference suppressor, a transient voltage suppressor, a NEMA Type 3 flasher, neutral and ground busses, and terminal blocks. The cabinet assembly shall contain a thermostatically controlled incandescent cabinet light with a door activated bypass switch. The cabinet light fixture shall be an incandescent type porcelain lamp holder rated for 660W-250V AC/CA. the lamp shall be 75W.

Controller assemblies for school zone speed limit sign beacons shall also include a time switch.

The NEMA 3R enclosure shall feature a hinged door. Hinge shall run the full length of the enclosure and shall be attached to the left side of cabinet. The door locking mechanism shall contain a Best CX series lock with a Best blue construction core lock. Provide two keys for lock.

The AC transient voltage and radio interference suppressors shall meet the requirements of Subsections 740-2.11.1.k. (3) and (4), respectively.

Use a solid state NEMA Type 3 flasher meeting the requirements of NEMA Standard TS 1-1989, Traffic Control Systems.

Use 20 ampere, 600 volt barrier type phenolic terminal blocks with plated brass screw type terminals. Field wiring termination blocks shall be sized to accept No. 8 AWG conductors. Power feed termination block shall be a single three (3) position box lug type terminal block capable of accepting up to No. 6 AWG conductors for terminating power feed cable.

Furnish an RTC Manufacturing model AP22 time switch complete with wiring harness, or an approved, calendar programmable, solid state time switch with liquid crystal display, keyboard, input/output port, and wiring harness.  The approved time switch shall:

            - Operate on line voltages from 95 to 135 VAC, operate in temperatures from -22 F to 165 F, and include a capacitor that provides 48 hours of backup power to retain programming and time when the unit is disconnected from AC voltage.

            - Include a backlit display and provide 2 lines of alphanumeric legend with 16 characters per line.  The display shall automatically prompt the operator while programming the device through the keyboard for ease of use.

            - Include an input/output port and keyboard activated special functions that transfer the program to other units and download the program to a printer for a hard copy record of the program.

            - Automatically compensate for changes in Daylight Savings Time and leap years and include a keyboard activated special function to quickly change the dates for the begin and end of Daylight Savings Time.

            - Provide at least 10 basic plans for daily and/or weekly use and at least 200 program steps that are equally divided amongst the actual number of basic plans.  Each program step shall be assignable to a single day, weekend, weekday, or every day.  The time switch shall also include 20 plans that activate the basic plans to provide one year of time based control.

            - Include 2 single pole double throw, relay controlled outputs rated for 15 amperes of resistive load at 115 VAC.  Each pole shall be independently activated for steady on or momentary on and be manually switched on through the keyboard.

            - Provide a 9 pin RS232 serial I/O port connector on the unit for programming via laptop, Ethernet, or cellular.

When a signal controller cabinet flasher is used to energize a beacon, furnish a two pole, fused block with built in fuse pullers to protect the flasher.  Furnish third party certified blocks that hold 13/32" x 1-1/2" midget ferrule fuses, are rated for 30 amperes, and feature tubular screw terminals that accommodate conductors to 8 AWG.  Furnish blocks with two fast acting, 3 ampere (BAF-3) fuses, and flat bases that can be directly mounted on a dead panel.

740-2.18 ROADWAY LUMINAIRES.  Furnish luminaires that conform to the following specifications and provide the light distributions specified.  When luminaire performance criteria are specified, luminaires shall also:

- Meet or exceed the minimum initial light levels indicated.

- Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified:  luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses (when used) and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8, dated 2014.

Furnish each luminaire with a high pressure sodium lamp or LED of the wattage specified and matching ballast with an input voltage equal to circuit voltage.

The following luminaires are proven to meet A.N.S.I/I.E.S. RP-8-14 light levels, uniformities, and veiling luminance ratios as specified in the plans, but are still subject to verification:

            - Roadway luminaire

              - GE Current: ERL2-__-25-C3-30…

              - Cooper Streetworks: VERD-M-A0485-__-__-T3…

              - Leotek: Green Cobra GC2-96G-__-WW-3R-GY-700…

            - Intersection luminaire

              - GE Current: ERL2-__-25-D3-30…

              - Cooper Streetworks: VERD-M-A0485-__-__-T4…

              - Leotek: Green Cobra GC2-96G-__-WW-4-GY-700…

Luminaires General

Install luminaires that feature:

- Corrosion resistant enclosures with gray painted finish, cooling elements not required to be painted, and space for the ballast.

    - Painted or finished luminaire surfaces exposed to the environment shall exceed a rating of six (6), after 1,000 hours or four (4) of 5,000 hours salt spray test according to ASTM D1654 and ASTM B117 testing. The coating shall exhibit no greater than 30% reduction of gloss, according to ASTM D523, after 500 hours of ASTM G154 Cycle 6 QUV® accelerated weathering testing.

- All luminaires shall have ANSI C136.15 external labels and ANSI C136.22 internal labels. The luminaire shall be listed for wet locations by a nationally recognized testing laboratory (NRTL) as defined by OSHA and shall be in compliance with UL 8750 and UL 1598. It shall be identified as such by a tag/sticker on the inside of the luminaire.

- All hardware shall be stainless steel or suitably corrosion resistant to match the 20-year expected life of the fixture. Captive screws are required on any component that requires maintenance after installation.

- Glass lenses, unless polycarbonate resin refractors are specified.

- Terminal blocks for attaching the illumination tap conductors.

- Aluminum reflectors with an ALZAK or ALGLAS finish when using HPS fixtures.

- Optical components free of substances that affect photometric performance, paint.

- Housings cast with no provision for a photoelectric control receptacle.

- For HPS fixtures; airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components, gasket material must withstand the temperatures involved and be securely held in place.

- For HPS fixtures include plug in starting aids with lamps through 400 watts.

- Luminaries – High Pressure Sodium; Cobrahead and Offset/Turnpike

Furnish HPS fixtures that feature a rated life of 40,000 hours based on 10 hours per start and ballasts that conform to Subsection 740-2.21. Each cobrahead or offset luminaire shall also include:

  - An easily removed hinged door used exclusively for mounting the ballast.

  - A second door that frames the lens (for HPS), hinges on the house side, and fastens on the street side with an automatic type latch.

  - A two (2) or four (4) bolt mounting brackets that is designed to fit a 2-inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

- Luminaires - LED

  - General. The luminaire shall be assembled in the United States and shall be assembled by and manufactured by the same Manufacturer. For easy removal, quick-connect/disconnect plugs shall be supplied between the discrete electrical components within the luminaire such as the driver, surge protection device, and optical assembly. The quick-connect/disconnect plugs shall be operable without the use of tools and while insulated gloves are worn. The luminaire shall be in compliance with ANSI C136.37 LED light source(s), and driver(s) shall be compliant with the Restriction of Hazardous Substances (RoHS) Directive 2011/65/EU.

    - Manufacturer Experience. The luminaire shall be designed to be incorporated into a lighting system with an expected 20-year lifetime. The luminaire Manufacturer shall have a minimum of 20 years’ experience manufacturing high-intensity discharge (HID) roadway luminaires and shall have a minimum of 5 years’ experience manufacturing LED roadway luminaires. The Manufacturer shall have a minimum of 5,000 total LED roadway luminaires installed on a minimum of 30 separate installations, all within the United States.

  - Housing. The housing shall be designed to ensure maximum heat dissipation and to prevent the accumulation of water, ice, dirt, and debris. A passive cooling method with no moving or rotating parts shall be employed for heat management. The effective projected area of the luminaire shall not exceed 1.2 sq. ft. The total weight of the luminaire(s) and accessories shall not exceed 55 lb.

  - Optical Assembly. The LED optical assembly, consisting of LED packages, shall have a minimum ingress protection rating of 66 (IP66) as defined in ANSI/IEC 60529. Circuiting shall be designed to minimize the impact of individual LED failures on the operation of the other LEDs.

The optical assembly shall utilize high-brightness, long-life LEDs with a minimum color rendering index (CRI) of 70, 4000 K (+/- 300 K) color temperature, and binned according to ANSI C78.377. Lenses shall be UV-stabilized acrylic or glass. Provisions for house-side shielding shall be specified along with means of attachment.

Lumen depreciation at 50,000 hours of operation shall not exceed 15% of initial lumen output at the specified LED drive current and an ambient temperature of 77°F (25°C).

The assembly shall have individual serial numbers or other means for Manufacturer tracking.

    - Photometric Performance Testing.  Luminaires shall be tested according to IES LM-79. The laboratory performing this test shall hold accreditation from the National Voluntary Laboratory Accreditation Program (NVLAP) under NIST. Submitted reports shall have a backlight, uplight, and glare (BUG) rating according to IESNA TM-15, including a luminaire classification system graph with both the recorded lumen value and percent lumens by zone.

Lumen maintenance shall be measured for the LEDs according to LM-80, or when available for the luminaires according to LM-84. The LM-80 report shall be based on a minimum of 6000 hours; however, 10,000-hour reports shall be provided for luminaires in cases in which tests have been completed.

Thermal testing shall be provided according to UL 1598. The luminaire shall start and operate in the ambient temperature range specified. The maximum rated case temperature of the driver, LEDs, and other internal components shall not be exceeded when the luminaire is operated in the ambient temperature range specified.

Mechanical design of protruding external surfaces such as heat sink fins shall facilitate hose-down cleaning and discourage debris accumulation. Testing shall be submitted when available to show that the maximum rated case temperature of the driver, LEDs, and other internal components are not exceeded when the luminaire is operated with the heat sink filled with debris.

    - Calculations.  Complete point-by-point luminance and veiling luminance calculations as well as listings of all indicated averages and ratios as applicable shall be provided according to IES RP-8 recommendations. Lighting calculations shall be performed using AGi32 software with calculations performed to two decimal places (i.e., x.xx cd/m2). Calculation results shall demonstrate that the submitted luminaire meets the lighting metrics specified in the plans. Scotopic or mesopic factors will not be allowed.

    - Lumen Maintenance Projection.  The LEDs shall have long-term lumen maintenance documented according to IESNA TM-21, or when available for the luminaires according to IESNA TM-28. The submitted calculations shall incorporate an in situ temperature measurement test (ISTMT) and LM-80 data with TM-21 inputs and reports according to the TM-21 calculator, or when available an ISTMT and LM-84 data with TM-28 inputs and reports according to the TM-28 calculator. Ambient temperature shall be 77°F (25°C).

  - Driver.  The driver for the luminaire shall be integral to the unit. It shall be mounted in the rear of the luminaire on the inside of a removable door or on a removable mounting pad. The removable door or pad shall be secure when fastened in place, and all individual components shall be secured upon the removable element. Each component shall be readily removable from the removable door or pad for replacement.

The driver shall be installed in a manner to keep it mechanically separated from the LED array heat sink.

    - Circuit Protection. The driver shall tolerate indefinitely open and short-circuit output conditions without damage.

    - Ingress Protection. The driver itself shall have an IP65 or IP66 rating, not the driver door. Do not gasket the driver door or seal in order to prevent condensation and allow for draining.

    - Input Voltage. The driver shall be suitable for operation over a range of 120 to 277 V or 347 to 480 V as required by the system operating voltage.

    - Operating Temperature. The driver shall have an operating ambient temperature range of      -40°F to 131°F (-40°C to 55°C).

    - Driver Life. The driver shall provide a lifetime of 100,000 hours at an ambient temperature of 77°F (25°C).

    - Safety/UL.  The driver shall be listed under UL 1012 or UL 1310.

    - Power Factor.  The driver shall maintain a power factor of 0.9 or higher and total harmonic distortion of less than 20%.

    - Driver Efficiency.  The driver shall have a minimum efficiency of 90% at maximum load and a minimum efficiency of 85% for the driver operating at 50% power, with driver efficiency defined as output power divided by input power.

    - Electrical Interference.  The driver shall meet the electromagnetic compatibility (EMC) requirements for Class A digital devices included in the FCC Rules and Regulations, Title 47, Part 15.

    - Thermal Fold Back.  The driver shall reduce the current to the LED module if the driver is overheating as a result of abnormal conditions.

    - Dimming.  The driver shall have 0 to 10 V dimming capability.

    - Leakage Current.  The driver shall comply with safety standards according to IEC 61347-1.

  - Surge Protection Device (SPD).  SPD shall be labeled as Type 4 in accordance with UL 1449 and be an integral part of the luminaire. It shall provide a minimum system protection level of 10 kV, 10 kA. To protect for a 10 kV, 10 kA surge the required clamping voltage of the external metal oxide varistor (MOV) or other SPD shall be lower than 1 kV at 8 kA {(10 kV – 2 kV)/1 ohm = 8 kA}.

The SPD shall comply with the following standards:

    - IEEE C62.41.1, IEEE Guide on the Surge Environment in Low-Voltage (1000 V and Less) AC Power Circuits,

    - IEEE C62.41.2, IEEE Recommended Practice on Characterization of Surges in Low-Voltage (1000 V and Less) AC Power Circuits,

    - IEEE C62.45, IEEE Recommended Practice on Surge Testing for Equipment Connected to Low-Voltage (1000 V and Less) AC Power Circuits, and

    - ANSI C136.2, American National Standard for Roadway and Area Lighting Equipment — Luminaire Voltage Classification.

The SPD and performance parameters shall be posted at www.UL.com under category code VZCA2.

  - Photoelectric Control.  Furnish fixtures with a built in ANSI C136.41 7-pin twist type photo cell receptacle. Receptacles shall be provided with shorting caps.

  - Failed Equipment and Workmanship. The luminaire and all of its components, for the term of the Contract, from initial installation through final acceptance 105-1.16, when directed, promptly replace failed equipment and repair failed workmanship.

(1)	Negligible light output from more than 10% of the LED packages,

(2)	Moisture inside the optical assembly,

(3)	Driver that continues to operate at a reduced output, and/or

(4)	Other failed conditions that do not meet specifications.

  - Submittal Requirements.  The Contractor shall submit, for approval, an electronic version of all associated luminaire IES files, AGi32 files, and the TM-21 or TM-28 calculator spreadsheet with inputs and reports associated with the project luminaires. The Contractor shall also provide an electronic version of each of the following Manufacturers’ product data sheets for each type of luminaire.

    - Descriptive literature and catalog cuts for luminaire, LED package, driver, and surge protection device;

    - LED drive current, total luminaire input wattage, and total luminaire current at the system operating voltage or voltage range and ambient temperature of 77°F (25°C);

    - Luminaire efficacy expressed in lumens per watt (lpw) per luminaire;

    - Initial delivered lumens at the specified color temperature, drive current, and ambient temperature;

    - Computer photometric calculation reports;

    - TM-15 BUG rating report;

    - Certification of Manufacturers’ experience and certification that luminaires were assembled in the United States;

    - Supporting documentation of compliance with ANSI standards, as well as listing requirements;

    - Supporting documentation of laboratory accreditations and certifications for specified testing;

    - Thermal testing documents;

    - IES LM-79, LM-80 (or LM-84), and TM-21 (or TM-28) reports;

    - Salt spray (fog) test reports and certification;

    - Vibration characteristics test reports and certification;

    - IP test reports;

    - Manufacturer written warranty; and

    - Luminaire installation, maintenance, and washing instructions.

- Lenses

When polycarbonate resin lenses are specified, the fabricator shall furnish certified lenses conforming to the following criteria:

a.	The lenses are molded in a single piece from virgin polycarbonate resin.

b.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

c.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

d.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

e.	The resins used meet the requirements for the self-extinguishing classification of ASTM D 635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D 256, Method A, using a 1/8 inch by 1/2 inch bar molded according to ASTM recommended practice.

740-2.19 SIGN LIGHTING FIXTURES.

- Incandescent Down Light.  Provide the type of sign lighting fixture, with incandescent lamp, shown on the Plans or as specified in the Special Provisions.

  - Hood. Cadmium plated, finished with aluminum paint, and side outlet tapped for conduit.

  - Reflector. Symmetrical 8-inch steel. Porcelain enameled green finish on the outside and white on the inside.

  - Lamp. Provide 2,900 lumen.

- Mercury Vapor.  Fully enclosed, rain-tight, dust-tight, and corrosion-resistant. Design each fixture for mounting at the bottom of the sign on an overhead sign structure as shown on the Plans. Painting of fixture is not required.

  - Housing.  Cast aluminum alloy or other non-corrosive material conforming to the Plans. Finish all housings in a workmanlike manner with no exposed burrs or sharp edges.

  - Refractor.  Glass having inner prisms with a smooth exposed face. Mount the refractor in a door frame assembly which is hinged to the body of the fixture and fastened with an automatic type latch.

  - Gaskets.  Made of a material capable of withstanding the temperatures involved, and securely held in place.

  - Light Distribution.  Light distribution over the sign face must conform to the isolux distribution patterns shown in the Plans. Accomplish light distribution entirely by refraction through the lens with no additional refractors or reflectors.

  - Miscellaneous.  All ballasts, lampholders, lamps, terminal blocks, and necessary fuses must conform to applicable requirements of Subsection 740-2.21 or to the Plans.

  - Lamps.  Color-improved to provide good color rendition of signs.

740-2.20 ILLUMINATION CONTROL.  Use photoelectric controls capable of directly switching multiple lighting systems. Furnish photoelectric units designed for pole top mounting which include a slip-fitter, terminal block, and cable supports or clamps to support pole wires.

- Photoelectric Unit.  A light sensitive element connected directly to a normally closed, single-pole throw control relay without intermediate amplifications. Plug the unit into a phenolic resin twist lock receptacle set in a cast aluminum mounting bracket with a threaded base. Screen photoelectric units to prevent artificial light from causing cycling.

Use either horizontal sensing or zenith sensing type units meeting the following:

  - A supply voltage rating of 60 Hz, 105-277 volts

  - A maximum rated load at a minimum of 1,800 volt-amperes

  - An operating temperature range from -40 °F to +150 °F

  - A power consumption of less than 10 watts

  - A unit base with a 3-prong, EEI-NEMA standard, twist-lock plug mounting

Furnish units for highway lighting that have a “turn-on” between 10.8 and 54 lux and a “turn-off” at between 1.5 and 5 times “turn-on.”

Furnish units for illuminated signs that have a “turn-on” level of between 215 and 270 lux. (“Turn-on” level specified above corresponds to a switching level of approximately 430 to 540 lux measured in the horizontal plane.) "Turn-off" level must not exceed 3 times “turn-on” level.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices Used in the Control of Roadway Lighting.

- Temperature Switch.  When mercury vapor sign lighting fixtures are used, provide a temperature switch in each photoelectric control circuit for lighting systems which will:

  - bypass the photoelectric unit when the ambient temperature drops to -13 °F, and energize the mercury vapor light circuits;

  - return switching functions to the photoelectric unit upon a temperature rise of 5 to 10 °F above the turn-on temperature; and

  - have a minimum range of (-40 F to +40 F), and be setable in increments no greater than 5 F.

740-2.21 BALLASTS.  Include ballasts for high intensity discharge lamps as an integral part of each luminaire and design for the voltages and lamp types specified in the Plans or Special Provisions. Ensure that the current needed to start the lamps is less than the operating current.

Furnish regulator-type ballasts with copper windings electrically isolated from each other, which will start and operate the lamps in temperatures down to -40 °F. The allowable line voltage variation is plus and minus 10%.

Equip high-pressure sodium luminaires, except those with 1000 watt lamps, with magnetic regulator ballasts with the following additional operating characteristics:

- The lamp wattage regulation spread at any time over the life of the lamp must not exceed 18% of nominal lamp watts at plus and minus 10% line voltage variations.

- With nominal line and lamp voltages, the ballast must regulate the lamp output to within 5% of the ballast design center, and sustain lamp operation with a minimum 60% voltage drop lasting 4 seconds or less.

Equip luminaires with 1000 watt high pressure sodium lamps with auto-regulator ballasts that provide a maximum 30% lamp regulation spread, a minimum 35% voltage dip tolerance, and with nominal line and lamp voltages regulate lamp output to within 5% of the ballast design center.

Furnish ballasts, for soffit luminaires, with mounting brackets attached and equip with terminal blocks for primary connections and lamp socket preconnected to the secondary for flush mounted luminaires and with terminal blocks for both primary and secondary connections for use with suspended luminaires.

Submit the ballast manufacturer’s specification sheets for review and approval.

740-2.22 UNDERPASS LIGHTING SYSTEM.  Use underpass luminaires that have vandal-resistant surface-mounted fixtures installed in a galvanized welded steel enclosure as detailed on the Plans. The lamp must be a mogul based 150-watt, clear, ANSI/NEMA C78.42, horizontal mount, high pressure sodium type. The lamp must provide a minimum of 15,000 initial lumens with a rated life of 24,000+ hours based on a minimum burn period of 3 hours.

Mount the ballast within the body of the fixture with a constant wattage autoregulator CWA type meeting ANSI/NEMA C78.1355 operating characteristics. See Plans for input voltage.

Provide a square lens that is semi-recessed, extra thick, injection molded polycarbonate prismatic type, with internal specular aluminum reflector. The lens must provide the uniformity specified in the Plans or Specifications with a minimum spacing to mounting height ratio (S/MH) of 3.5:1, in the plane defined by the axis of the lamp, and a minimum S/MH ratio of 1:1 in the plane passing vertically through the length of the lamp axis.

Provide a lens frame and side housing made of ASTM B209, alloy 6061-T6 tempered aluminum a minimum of 0.177 inch thick, or equivalent stainless steel, secured with tamper proof screws requiring a special manufacturer’s tool to remove.

Provide fixtures that are Third Party listed for wet, damp, and dry locations. Fasten the fixture into the mounting enclosure with stainless steel screws accessible only from within the fixture housing.

Fabricate the mounting enclosure from 0.138 inch thick mild steel with continuous welded seams and hot-dipped galvanized, as detailed on the Plans. Use wiring within the enclosure that might come in contact with the ballast rated at 390 F [type SR-2]. Provide a grounding screw or lug within the enclosure for a maximum No. 8 AWG ground conductor.

Submit the manufacture’s fixture specifications, photometric data, and a computer-generated lighting layout for approval prior to ordering. Calculate, by the point-to-point method, the light level on the walkway surface through the underpass with no wall, ceiling, or walkway reflectances. The calculated light level on the walking surface and the calculated average-to-minimum uniformity ratio may not be worse than the light level and uniformity ratio noted on the drawings. Center the calculation area on the light fixtures and base it on the width of the walkway less 12 inches, and the length of the walkway equal to the distance between the first and last fixtures plus a distance equal to 50% of the spacing between the fixtures added to each end of the walkway. You may substitute fixtures having similar construction, electrical, and light distribution characteristics, if approved. In the case of a substitution, construct the enclosure shown on the drawing to match the mounting requirements of the submitted fixture. Submit shop drawings for the enclosure for approval along with the fixture shop drawings.

740-2.23 TRAFFIC SIGNAL COMMUNICATIONS SYSTEM.  Furnish only fully functioning new equipment of the brand and type listed or approved equal. To be considered an approved equal equipment must meet or exceed the listed specifications. The products listed in this subsection are subject to review and approval if they are included on the Materials Certification List (MCL).

            - Broadband Ethernet Radio Interconnect System.

The contractor shall provide a 5GHz Broadband Wireless Ethernet Radio Interconnect System. The system shall be the Intuicom Nitro58™ Wireless Solutions or an approved equal meeting the following minimum specifications:

- Comply with FCC part 15 and IC RSS-210 rules/regulations.

- Support and provide the following wireless protocols:

    - IEEE 802.11a (OFDM)

    - IEEE 802.11n (MIMO 2x2:2, OFDM)

    - Proprietary Wireless Protocol

- Shall be available in the following wireless hardware configurations:

    - 108Mbps – Integrated Panel Antenna or Stand Alone Radio

    - 216Mbps – Stand Alone (Dual) Radio

    - 432Mbps - Access Point Cluster (Quad) Radio

    - 300Mbps – 802.11n Integrated Panel Antenna

- All Radios shall contain embedded GPS for automatic Geo-location of fixed or mobile wireless locations.

- Integrated Panel Antennas must contain an external status panel which combines Received Signal Strength Indicators (RSSI), Power Indicator, and a Reset Button.

- Radios include Adaptive Modulation, Dynamic Frequency Selection, Automatic Transmit Power Control – RF link is monitored to automatically adjust the data rate to optimize the maximum link performance.

- Any Radio shall be configurable as an Access Point, Remote, Repeater and Mesh Node.

- The manufacturer and/or supplier of the Radio will be located in the North America with performance testing over the Radio’s operating temperatures of -40° to +85 C. Shall be IP67 and NEMA exceeding environmental specifications.

- Detailed Requirements:

    - Operating Frequency: 5.150 – 5.825 GHz

    - Ethernet: Auto-sensing 10/100/1000BASE-T Ethernet

    - Electrical: Gigabit PoE Compliant (IEEE 802.3af/at)

    - Receiver Sensitivity: -74 to -94dBm

    - Peek Transmit Power: 802.11a (Up to 28dBm), 802.11n (Up to 27dBm, +/- 2dBm)

    - Channel Width: 5, 10, 20, 40 MHz

    - Range: 20+ miles-LOS

    - Supported Network Topologies: Point to Point, Point to Multipoint, Mesh

    - Wireless Security Options:

- 802.11i WPA/WPA2 (PSK, EAP), AES-CCM, TKIP, 802. 1X, RSN.

- Radius Authentication

- MAC Access Control List

- User Login Controls

    - Support the minimum IEEE Networking Features:

- 802.11e (WMM & QoS)

- 802.11h (DFS & TPC)

- 802.1d (Ethernet Bridging)

- 802.1p (Traffic Prioritization)

- 802.1q (VLAN)

- 802.1w (Rapid Spanning Tree)

- 802.3ac (802.1q & 802p support)

- 802.3ad (Link Aggregation)

- 802.3x (Full Duplex and Flow Control)

    - Minimum Wireless Software Features:

- Automatic Geolocation of embedded GPS radios

- Icon roll over feature displays latitude and longitude coordinates of radios

- Customizable Menu Interface

- Automatically discover, organize, configure radios in network tree

- Provide a “Drag and Drop” radio configuration tool

- A color coded display of network-wide wireless diagnostics illustrated on map

- Data Rate, RSSI, Client Connection Quality

- Provide Wireless Alert Reporting

- A unique slider control allowing users to adjust upper and lower alert limits

- Network Management Capabilities

    - Firewall, ARP/Bridge Tables, Spanning Tree, Data Throughput

    - IP Discovery, IP/Subnet Configuration, IP Conflict Tool

    - Ping Watchdog

- Real-time wireless diagnostic tools

- Bandwidth Test Tool, RSSI and CCQ

- Spectrum Analysis with AP Scan Tool

- Audio Antenna Aiming Tool

- Advanced User Control

    - Terminal Window, Telnet, SSH2

    - Dynamic Routing (BGP+, OSPFv3 and RIP protocols)

    - Sniffer and Fetch tools

    - IPV6 support

    - DNS

            - Copper and Fiber Ethernet Switch Furnish the number and type Siemens RuggedCom Ethernet Switch  or approved equal meeting or exceeding the following specifications.  Provision switch with ROS 5.4.2 or higher.   Populate all SFPs with 1000LX (Gb) 1310nm single mode 10km  LC connector or Gb RJ45 copper connector modules as specified per table.  All SFP modules must be industrially rated to operate between -40C and 85C.

            - a.	Requirements:

| Model | RS900G (32MB) | RSL910 | RSG920P |
| --- | --- | --- | --- |
| (1) Power Supply |  |  |  |
| Power Consumption (Max) | 10W | 13W | 27W |
| HI Supply Voltage AC/DC | 85-264VAC | 85-264VAC | 85-264VAC |
| (2) Physical & Environmental |  |  |  |
| Height mm | 188 | 188 | 177 |
| Width mm | 66 | 66 | 152 |
| Depth mm | 127 | 125 | 166 |
| Weight kg | 1.2 | 1.1 | 4.7 |
| Oper Temp Range -40C to 85C | fanless | fanless | fanless |
| Ingress Protection | IP40 | IP30 | IP40 |
| Enclosure | 20 AWG galvanized | 20 AWG galvanized | Cast Aluminum |
| Mounting | DIN rail mounted | DIN rail mounted | DIN rail mounted |
| (3) Switch Properties |  |  |  |
| Switching method: Store & Forward | Req | Req | Req |
| Switching latency us | 7 (100Mbps) | 8 (100Mbps) | 4 us |
| Switching bandwidth, Gbps | 5.6 | 2.8 | 108 |
| Priority Queues | 4 | 4 |  |
| Frame buffer memory |  | 1 Mbit |  |
| 255 Simultaneous VLANs | Req | Req | Req |
| VLAN ID Range 1-4096 | Req | Req | Req |
| IGMP and static multicast groups |  | 256 |  |
| Port rate limiting: 128kbps, 256, 512, 4, 8Mbps | Req | Req | Req |
| No head of line blocking | Req | Req | Req |
| Non Blocking Ethernet Ports RJ-45 (speed) | 8 (10/100) | 6 (10/100) | 12 (Gb) |
| Non Blocking Gb SFP Ports | 0 | 2 | 4 |
| Non Blocking Gb POE ports | 0 | 0 | 4 |
| VDSL2 Ports | 0 | 2 | 0 |
| Non Blocking Gb SC Transceiver | 2 (1310nm, 10km) | 0 | 0 |
| (4) Approvals |  |  |  |
| CE Marking | Req | Req | Req |
| Emissions: FCC Part 15 (Class A), EN55022 (CISPR22 Class A) | Req | Req | Req |
| Safety: cCSAus (Compliant with CSA C22.2 No. 60950, UL 60950, EN60950) | Req | Req | Req |
| Laser Eye Safety (FDA/CDRH): Complies with 21 CFR, Chapter1, Subchapter J. | Req | Req | Req |
| (5) EMI Immunity and Environmental Compliance |  |  |  |
| IEEE 1613 Electric Utility Substations | Req | Req | Req |
| NEMA TS 2 Traffic Control Equipment | Req | Req | Req |
| (6) Network Management |  |  |  |
| HTTP graphical web-based, SSL (128-bit encryption) | Req | Req | Req |
| SNMP v1, v2c, v3 (56-bit encryption) | Req | Req | Req |
| Telnet, SSH | Req | Req | Req |
| Command Line Interface (CLI) | Req | Req | Req |
| RSA Key Management (1024 bit key) | Req | Req | Req |
| Authentication and Accounting - TACACS+ (encrypted), | Req | Req | Req |
| (7) Warranty |  |  |  |
| 5 Years-Applicable to design or manufacturing related product defects. | Req | Req | Req |
| (8) IEEE Compliance |  |  |  |
| 802.3-10BaseT | Req | Req | Req |
| 802.3u-100BaseTX, 100BaseFX | Req | Req | Req |
| 802.3x-Flow Control | Req | Req | Req |
| 802.3z-1000BaseLX | Req | Req | Req |
| 802.3ab-1000BaseT | Req | Req | Req |
| 802.3ad-Link Aggregation | Req | Req | Req |
| 802.1D-MAC Bridges | Req | Req | Req |
| 802.1D-Spanning Tree Protocol | Req | Req | Req |
| 802.1p-Class of Service | Req | Req | Req |
| 802.1Q-VLAN Tagging | Req | Req | Req |
| 802.1D-2004 -Rapid Spanning Tree Protocol | Req | Req | Req |
| 802.1x-Port Based Network Access Control | Req | Req | Req |
| 802.1Q-2005 (formerly 802.1s) MSTP | Req | Req | Req |
| (9) IETF RFC Compliance |  |  |  |
| RFC768-UDP | Req | Req | Req |
| RFC783-TFTP | Req | Req | Req |
| RFC791-IP | Req | Req | Req |
| RFC792-ICMP | Req | Req | Req |
| RFC793-TCP | Req | Req | Req |
| RFC826-ARP | Req | Req | Req |
| RFC854-Telnet | Req | Req | Req |
| RFC894-IP over Ethernet | Req | Req | Req |
| RFC1112-IGMP v1 | Req | Req | Req |
| RFC1519-CIDR | Req | Req | Req |
| RFC1541-DHCP (client) | Req | Req | Req |
| RFC2030-SNTP | Req | Req | Req |
| RFC2068-HTTP | Req | Req | Req |
| RFC2236-IGMP v2 | Req | Req | Req |
| RFC2284-EAP | Req | Req | Req |
| RFC2475-Differentiated Services | Req | Req | Req |
| RFC2865-RADIUS | Req | Req | Req |
| RFC3414-SNMPv3-USM | Req | Req | Req |
| RFC3415-SNMPv3-VACM | Req | Req | Req |
| (10) IETF SNMP MIBS |  |  |  |
| RFC1659-RS-232-MIB | Req | Req | Req |
| RFC1907-SNMPv2-MIB | Req | Req | Req |
| RFC2011-IP-MIB | Req | Req | Req |
| RFC2012-TCP-MIB | Req | Req | Req |
| RFC2013-UDP-MIB | Req | Req | Req |
| RFC2578-SNMPv2-SMI | Req | Req | Req |
| RFC2579-SNMPv2-TC | Req | Req | Req |
| RFC2580-SNPv2-CONF | Req | Req | Req |
| RFC2580-IANAifType | Req | Req | Req |
| RFC2819-RMON-MIB | Req | Req | Req |
| RFC2863-IF-MIB | Req | Req | Req |
| RFC3411-SNMP-FRAMEWORK-MIB | Req | Req | Req |
| RFC3414-SNMP-USER-BASED-SM-MIB | Req | Req | Req |
| RFC3415-SNMP-VIEW-BASED-ACM-MIB | Req | Req | Req |
| RFC4188-BRIDGE-MIB | Req | Req | Req |
| RFC4318-RSTP-MIB | Req | Req | Req |
| RFC4363-Q-BRIDGE-MIB | Req | Req | Req |
| IEEE8023-LAG-MIB | Req | Req | Req |
| IEEE8021-LLDP-MIB | Req | Req | Req |

CFHWY00599

Blank Page

APPENDIX A

CONSTRUCTION SURVEY REQUIREMENTS

Blank Page

APPENDIX B

ENVIRONMENTAL PERMITS

Blank Page

APPENDIX C

MATERIAL CERTIFICATION LIST

Blank Page

APPENDIX D

SIGN SHOP DRAWINGS

Blank Page

APPENDIX E

TEMPORARY CONSTRUCTION EASEMENTS

Blank Page