### SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

- Publications. The following are available from the Plans Room, download online, or as noted:

  - Standard Specifications for Highway Construction, 2020 Edition comb bound ($25.00), download at: www.dot.state.ak.us/stwddes/dcsspecs/assets/pdf/hwyspecs/sshc2020.pdf, or order bound book from LuLu at: https://www.lulu.com/en/us/shop/state-of-alaska-dept-of-transportation/2020-alaska-standard-specification-for-highway- construction/paperback/product-1gq9j9qk.html

  - Alaska Test Methods Manual (Lab & Field), May 15, 23 Edition ($25.00). Available online at:

www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/testman.shtml

  - Alaska Storm Water Pollution Prevention Plan Guide, March 2021.

www.dot.state.ak.us/stwddes/desenviron/resources/stormwater.shtml

  - Quantity Computations

  - Final Structural Foundation Engineering Report, Juneau Creek Bridge, Project no. 0A33034/CFHWY01060, June 2023, Jacobs

- Materials Certification List (MCL). The MCL provides the Engineer with the appropriate approving authority. Contractor, submit certification for each material to the Engineer. The MCL is included in Appendix C.

- Environmental Documents. The Department has approved an environmental document addressing concerns and environmental commitments. This document is available for review in the Department Section of Preliminary Design and Environmental. (907) 269-0542.

- Section 120, Disadvantaged Business Enterprise (DBE) Program. The Department, in coordination with US DOT, has adopted a Race-Neutral DBE Program effective for Federal-aid projects advertised in Central Region after June 30, 2015. In particular, all bidders shall be aware that Good Faith Effort Documentation is required from the successful bidder for all contracts, regardless of DBE goal or DBE utilization, in accordance with Section 120 Disadvantaged Business Enterprise (DBE) Program.

The overall DBE Utilization Goal is revised to 8.28 percent.

Direct questions about this notice to the Manager of the Civil Rights Office, (907) 269-0848, http://www.dot.state.ak.us/cvlrts/index.shtml.

- Cargo Preference Act Requirements. The provisions of the Cargo Preference Act (CPA) must be physically incorporated into all Federal-aid Projects awarded after February 15, 2016, and must be physically incorporated in all agreements with subcontractors and lower tier subcontractors.

Form 25D-55 (2/16) is revised to include the CPA provisions to the Required Contract Provisions for Federal- Aid Construction Contracts. See the last page of Form 25D-55 for the CPA requirements.

For additional details, please visit: https://www.fhwa.dot.gov/construction/cqit/cargo.cfm

- Buy America Act. On December 22, 2015, U.S. District Court for the District of Columbia issued a decision vacating the Federal Highway Administration (FHWA) 90 percent threshold exemption for manufactured steel and iron products and the miscellaneous steel or iron components, subcomponents and hardware waiver. As a result of the federal court decision, FHWA withdrew their December 21, 2012 policy memorandum clarifying provisions of the Buy America Act requirements.

- Prohibition on Certain Telecommunications and Video Surveillance Services or Equipment. 2 CFR 200.216, as amended effective August 13, 2020, Federal Register, Vol. 85, No. 157, 49506 – 49582, Prohibition on certain telecommunication and video surveillance services or equipment. Refer to Subsection 106- 1.01.

- COVID-19 Management Plan. The Governor's emergency declaration and mandates relating to COVID-19 expired on February 14, 2021. However, contractors are encouraged to review COVID-19 Response and Recovery Health Advisories that can be accessed at:

https://covid19.alaska.gov/health-advisories/

Contractors will still be required to meet any applicable local ordinances or requirements currently in effect, and comply with any future federal, state or local declarations or mandates that might be adopted while work on the project is ongoing.

Consistent with Section 107-1.01 of the Standard Specifications for Highway Construction, the Contractor will be responsible for paying all costs and expenses incurred to comply with any COVID-19 Health Mandates or Health Advisories in effect during times when the Contractor is performing project-related work activities. The Contractor will additionally be responsible for preparing any general or site-specific mitigation and response plans required for its forces, along with any attendant schedule delays or impacts.

- Certified Payroll. Certified payroll must be submitted electronically through AASHTOWare for contracts awarded after January 1, 2021.

In order to submit certified payroll, Contractors, Subcontractors, and lower tier Subcontractors must be active in AASHTOWare, which requires they have a valid Vendor ID with a 913 commodity code.

To obtain a Vendor ID, register with the State of Alaska via the Vendor Self-Serve (VSS). Instructions for creating a new account in the VSS system can be found under the Job Aids at the following link:

https://iris-vss.alaska.gov/webapp/PRDVSS1X1/AltSelfService

For information on certified payroll, contact the Department of Labor and Workforce Development, Wage and Hour Administration:	Juneau	(907) 465-4842

Anchorage	(907) 269-4900

Fairbanks	(907) 451-2886

DOT&PF AASHTOWare Project guidance, including schedule, FAQs, training options: http://dot.alaska.gov/aashtoware/

- Laborers Mechanics Minimum Rate of Pay. The current Laborers Mechanics Minimum Rate of Pay contains information on remote sites and per diem. The Department of Labor has issued WHPL #197, which further

clarifies this requirement. See pay item 640.0004.	.

- Limitation of Operation. Limit disturbed unstabilized ground. Refer to Subsection 652-1.04 Limitation of Operation for further information.

- Contract Price Adjustment(s). The Department will not provide cost escalation or de-escalation price adjustment for this contract, except for specific items described in the bid package at the time of bid opening.

- The Alaska Department of Transportation & Public Facilities and QAP/Traylor Joint Venture have agreed to a 14.9% Fee for all work performed by the Joint Venture or subcontractor partnership on packages associated with the Sterling Highway MP 45-60 Sunrise to Skilak Lake Rd Phases 2-5 CM/GC Project. QAP/Traylor Joint Venture will only be permitted a 5% fee for subcontractor work or subcontractor-supplied materials. This agreed-upon Fee represents the total amount of general management, overhead and profit the Contractor is entitled to for this scope of work. The 14.9% Fee has been incorporated into the bid schedule and is reflected in the Final Negotiated Price.

- USDOL Davis-Bacon and Related Acts Final Rule. On September 29, 2023 FHWA updated form FHWA-1273 to incorporate the new Davis-Bacon and Related Acts final rule. Form FHWA-1273 is required to be physically incorporated into construction contracts, subcontracts, and lower-tier subcontracts for awards made after October 23, 2023. DOT&PF satisfies this requirement by incorporating Form 25D-55H into contracts.

A section-by-section change of form FHWA-1273 is available at https://www.fhwa.dot.gov/construction/cqit/form1273.cfm

The USDOL has a website containing the final rule, frequently asked questions, and a comparison chart of changes at https://www.dol.gov/agencies/whd/government-contracts/construction/rulemaking-davis-bacon

FED_SOA-CRSNtB-23.1015_SSHC2020

### PART 4

STANDARD MODIFICATIONS AND

SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD SPECIFICATIONS FOR

HIGHWAY CONSTRUCTION

2020

EDITION

## Blank Page

### DIVISION 100 — GENERAL PROVISIONS

- Bidding Requirements and Conditions	3

- Award and Execution of Contract	4

- Scope of Work	5

- Control of Work	6

- Control of Material	7

- Legal Relations and Responsibility to Public	10

- Prosecution and Progress	12

- Measurement and Payment	13

120	Disadvantaged Business Enterprise (DBE) Program	14

### DIVISION 200 — EARTHWORK

203	Excavation and Embankment	17

205	Excavation and Fill for Major Structures	29

### DIVISION 500 — STRUCTURES

501	Concrete for Structures	33

503	Reinforcing Steel	35

504	Steel Structures	38

506	Timber Structures	41

507	Bridge Barrier and Railing	42

515	Drilled Shafts	43

516	Expansion Joints and Bearings and Waterstops	44

### DIVISION 600 — MISCELLANEOUS CONSTRUCTION

606	Guardrail	49

619	Soil Stabilization	55

- Erosion, Sediment, and Pollution Control	60

- Construction Surveying and Monuments	82

- Traffic Maintenance	89

- Services to be Furnished by the Contractor	112

- Training Program	116

- CPM Scheduling	119

- Equipment Rental	120

654	Monitor	122

### DIVISION 700 — MATERIALS

703	Aggregates	129

709	Reinforcing Steel and Wire Rope	130

716	Structural Steel	131

720	Bearings	132

Appendix A	Construction Survey Requirements Appendix B	Environmental Permits

Appendix C	Material Certification List Appendix D	Human Remains Protocol Appendix E	Inadvertent Discovery Procedure Appendix F	Vegetation Management Plan

Blank Page

# DIVISION 100 — GENERAL PROVISIONS

Division 100

## Blank Page

### SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

### 102-1.05 PREPARATION OF BID.

In the third paragraph, replace the fourth sentence with the following:

If the bidder is a joint venture, the bid must be signed by an officer or agent with authority to bind the joint venture.

HSM20.42-043022

### SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modification

103-1.01 CONSIDERATION OF BIDS. Delete the subsection in its entirety and replace with the following:

The Proposer shall, within 5 working days following successful negotiation of the final Contract price, submit a completed Subcontractor list, Form 250-5, listing all firms with which the prime Contractor intends to execute subcontracts for the performance of the Contract. The list shall include the name, business address, Alaska business license number and contractor's registration number of each proposed Subcontractor.

If a subcontractor on the list did not have a valid Alaska business license and a valid certificate of registration under AS 08.18 at the time the proposal was opened, the Proposer may not use the subcontractor in the performance of the contract, and shall replace the subcontractor with a subcontractor who had a valid Alaska business license and a valid certificate of registration under AS 08.18 at the time the proposal was opened.

Attempts to circumvent the requirements of this section by listing as a Subcontractor another contractor who, in turn, sublets the majority of the Work required under the Contract, violates this section.

If a Contract is awarded and the Proposer violates this section, the Proposer agrees that the Contracting Officer may:

- cancel the Contract without any damages accruing to the State; or

- after notice and a hearing, assess a penalty on the Proposer in an amount that does not exceed 10 percent of the value of the Subcontract at issue.

A Proposer may replace a listed Subcontractor who:

- fails to comply with AS 08.18;

- files for bankruptcy or becomes insolvent;

- fails to execute a contract with the Proposer involving performance of the Work for which Subcontractor was listed and the Proposer acted in good faith;

- fails to obtain bonding;

- fails to obtain insurance acceptable to the State;

- fails to perform the contract with the Proposer involving Work for which the Subcontractor was listed;

- must be substituted in order for the prime Contractor to satisfy required State and Federal affirmative action requirements;

- refuses to agree or abide with the Proposer's labor agreement; or

- is determined by the Contracting Officer not to be a responsible subcontractor.

In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State.

#### HSM18-1.103/CFHWY01060

Standard Modification

### 104-1.06 VALUE ENGINEERING CHANGE PROPOSALS BY CONTRACTOR.

Replace 104-1.06.3.e with the following:

e. The Contractor may submit VECPs for an approved subcontractor. If the Contractor elects to submit a VECP for an approved subcontractor and it is subsequently accepted by the Department, the Department will reimburse the Contractor per 104-1.06.5.

#### HSM20.2-113020R

Special Provisions

Add the following Subsection 105-1.011 Related Sections:

### 105-1.011 RELATED SECTIONS.

Section 651, Control of Work – Supplemental Requirements CR105.5-012816R

Standard Modification

### 106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.

Add the following:

### PROHIBITION ON CERTAIN TELECOMMUNICATION AND VIDEO SURVEILLANCE SERVICES OR

EQUIPMENT. On projects using federal funds, the Contractor shall comply with the requirements of 2 CFR 200.216, Prohibition on certain telecommunication and video surveillance services or equipment, including any future amends thereto that are applicable to the project.

By submitting a bid or by execution of the contract, the Contractor certifies that it has not entered into a contract nor extended or renewed a contract to procure or obtain equipment, services, or systems that uses covered telecommunications equipment or services as a substantial or essential component of any system, or as critical technology as part of any system produced by:

- Huawei Technologies Company or ZTE Corporation (or any subsidiary or affiliate of such entities).

- Hytera Communications Corporation, Hangzhou Hikvision Digital Technology Company, or Dahua Technology Company (or any subsidiary or affiliate of such entities).

- Any entity that the Secretary of Defense, in consultation with the Director of the National Intelligence or the Director of the Federal Bureau of Investigation, reasonably believes to be an entity owned or controlled by, or otherwise connected to, the government of a covered foreign country.

The Contractor further certifies that it has complied with the requirements of 2 CFR 200.216 and that it will continue to do so throughout the term of the Contract.

#### HSM20-20-123121

Special Provisions

Replace the BUY AMERICA PROVISION with the following:

BUY AMERICA PROVISION. On projects using federal funds, the Contractor shall comply with the requirements of Public Law No. 117-58, Sections 70901-52 and 23 CFR 635.410, Buy America requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract. When the Contractor becomes aware of a change from or error in a previously submitted Material Origin Certificate (Form 25D-60), the Contractor shall submit an updated Material Origin Certificate (Form 25D-60). All construction materials, steel products and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of construction materials, steel products and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2,500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

The Contractor shall ensure that all manufacturing processes for each covered product comply with this Buy America Provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and debarment.

Provide a Certificate of Buy America Act Compliance Form 25D-62 from the supplier for each construction material, steel product, or iron product and each component that is manufactured predominantly of steel or iron, prior to incorporating any construction material, steel products, iron products or any components manufactured predominantly of steel or iron into the project. The supplier certifying Form 25D-62 may be the original manufacturer, fabricator, vendor, contractor, or subcontractor; provided the supplier has sufficient control and knowledge of the manufacturing process to accept responsibility and certify full and

complete conformance with the certification statement on the form. Provide mill certificates when required by the Engineer. False statements may result in criminal penalties prescribed under AS 36.30.687 and Title 18 US Code Section 1001 and 1020.

Buy America does not apply to construction materials, steel products, and iron products brought to the construction site and removed at or before the completion of the project. Further, it does not apply to construction materials, steel products, and iron products which remain in place at the Contractor’s convenience.

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

Construction Materials

A construction material includes an article, material, or supply other than

- an item of primarily iron or steel;

- a manufactured product;

- cement and cementitious materials;

- aggregates such as stone, sand, or gravel; or

- aggregate binding agents or additives – that is or consists primarily of

- Non-ferrous metals;

- Plastic and polymer-based products (including polyvinylchloride, composite building materials, and polymers used in fiber optic cables);

- Glass (including optic glass);

- Lumber; or

- Drywall.

For construction materials, manufactured in the United States means the final manufacturing process and the immediately preceding manufacturing stage were undertaken in the United States.

An item that consists of two or more construction materials combined together through a manufacturing process, and items that include at least one construction material combined with another material through a manufacturing process, will be treated as a manufactured product instead of a construction material. Manufactured products that are not predominantly steel or iron are not subject to Buy America requirements.

Steel and Iron Products

“Manufactured in the United States” means all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the requirements of Section 106-1.01, Buy America Provision and of the Buy America Act.

Buy America does not apply to iron ore, pig iron, and processed, pelletized and reduced iron ore.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

HSP20.7-110822

### SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

### 107-1.02 PERMITS, LICENSES, AND TAXES.

The Department will: Add No. 3:

- The Department has received the following permits on the Contractor's behalf:

  - USACE Section 404 Permit No. POA-1991-00836-M1

  - ADEC 401 Certificate of Reasonable Assurance No. POA-1991-00836

  - USFWS Eagle Permit No. MB70047D-0 CR107.4-120117R2

The Contractor shall:

Replace No. 1. with the following:

1. Acquire all permits and licenses required to complete the project that are not acquired by the Department.

#### CR107.2-070121

Add No. 10:

10. Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual, and the Regional Supplement to the Corps of Engineers Wetland Delineations Manual (Alaska Region, Version 2.0, September 2007). The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

CR107.5-120117R

### 107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.

Replace the 1st sentence including numbers 1, 2, and 3, with:

When operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

Section 107

### 107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following:

Non-municipal Water Source. If water is required for a construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

#### CR107.3-051517

Add the following:

Eagles. Eagles are protected under 16 U.S.C. 668-668c Protection of Bald and Golden Eagles, that prohibits “takes” of eagles, their eggs, nests, or any part of the bird. The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of minimum 330-feet as an undisturbed habitat buffer around nesting eagles. If topography or vegetation does not provide an adequate screen or separation, extend the buffer to 1320- feet, or a sufficient distance to screen the nest from human activities. The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity. Within the Secondary Zone, between 330-feet and 660-feet from a nest tree, no obtrusive facilities, or major habitat modifications shall occur. If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, extend the buffer up to 2640-feet. No blasting, logging and other noisy, disturbing activities should occur during the nesting period (February 1 – August 31) within the primary or secondary zones. Unless otherwise allowable by USFWS Eagle Nest Disturbance Permit.

Do not disturb a nesting eagle. Notify the Engineer when an active eagle nest is within the primary or secondary zones.

#### CR107.1/CFHWY01060

Standard Modification

### 108-1.01 SUBCONTRACTING OF CONTRACT.

In item 1g. replace AS 45.45.101(a) with AS 45.45.010(a).

In item 2f. replace AS 45.45.101(a) with AS 45.45.010(a).

#### HSM20.41-010122

Add the following Subsection 108-1.011 Related Sections:

### 108-1.011 RELATED SECTIONS.

Section 652, Prosecution and Progress – Supplemental Requirements CR108.3-012816R

### 108-1.07 FAILURE TO COMPLETE ON TIME.

Replace Table 108-1 with the following:

### Table 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES FOR EACH CALENDAR DAY OF DELAY

| Original Contract Amount |  | Daily Charge |
| --- | --- | --- |
| From More Than | To and Including |  |
| $ 0 | 500,000 | $1,400 |
| 500,000 | 1,000,000 | 1,700 |
| 1,000,000 | 5,000,000 | 2,600 |
| 5,000,000 | 10,000,000 | 3,800 |
| 10,000,000 | 25,000,000 | 4,500 |
| 25,000,000 | --------- | 6,600 |

#### HSM20.43-070122

Special Provision

### 109-1.01 GENERAL.

Replace the 2nd paragraph with the following:

When more than one type of material or work is specified for a pay item, the proposal line number, and the description are used to differentiate the material or work.

CR109.4-010120

### 109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.

Under Item 3. Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

Provide a printed copy of the current EquipmentWatch rate sheet for each piece of equipment utilized on time and materials work.

#### CR109.2-110118

Standard Modification

109-1.08 FINAL PAYMENT. Add the following after the fifth paragraph:

On federally funded projects, if DOLWD Wage and Hour Administration notifies the Department of a pending prevailing wage investigation, and that the investigation is preventing the closing out of the project, the Contractor may place the notified amount in escrow under Wage and Hour for the exclusive purpose of satisfying unpaid prevailing wages. Upon receipt of notice from Wage and Hour that the Contractor has satisfactorily transferred the necessary funds into escrow, the Department will proceed to issue final payment.

HSM20.3-113020R

### SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Standard Modification

### 120-1.01 DESCRIPTION.

In the first sentence of the second paragraph, replace “8.83 percent" with “8.28 percent”.

120-3.01 DETERMINATION OF COMPLIANCE. Replace 2a. with the following:

2a. Written DBE Commitment. Complete Form 25A-326 for each DBE to be used on the project.

HSM20.21-123121

# DIVISION 200 — EARTHWORK

Division 200

## Blank Page

Special Provisions

Replace Section 203 with the following:

### SECTION 203

EXCAVATION AND EMBANKMENT

203-1.01 DESCRIPTION. Excavate, haul, place, and compact or dispose of specified materials necessary to construct the project. Conform to the lines, grades, depths and typical cross sections shown on the Plans or as established. The Contract will designate material to be removed within the excavation limits as classified or unclassified excavation.

Install Rock Bolts or Dowels and associated Hardware, Cement Grout, and Associated Hardware as necessary to stabilize rock slopes at locations directed by the Engineer. The Engineer will determine the lengths and orientations of the rock bolts or dowels.

Special ditching shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

### 203-2.01 MATERIALS.

- Unclassified Excavation. All materials of whatever character encountered in the work. May include rock, common, or muck.

- Classified Excavation.

  - Common Excavation. Clay, silt, sand, gravel, cobbles, boulders and granular material other than rock or muck.

  - Rock Excavation. Rock that cannot be excavated without blasting or ripping with a 300 HP D8 bulldozer.

  - Muck Excavation. Soils, organic matter, and other material not suitable for foundation material regardless of moisture content.

- Borrow. Approved material required for embankments or for other portions of the work, and obtained from sources outside the right-of-way limits for the project. Use fill material from weed-free material sites. Fill material from off project alignment shall be certified through the Kenai Soil & Water Conservation District weed-free program. All stockpiled materials shall be reviewed and certified quarterly by a weed-free specialist.

- Turf Reinforcement Mats (TRM). The TRM shall meet the requirements indicated in Sections 619 and 727-2.02.

- Crushed Glass: May be combined with soil-aggregate material to be used in embankment construction. Meet 703-2.15 requirements.

### CONSTRUCTION REQUIREMENTS

203-3.01 GENERAL. Perform all necessary clearing and grubbing prior to beginning excavation, grading, and embankment operations in any area.

Keep excavation and embankment areas free draining at all times as the work progresses. Finish the excavation and embankments to reasonably smooth and uniform surfaces.

Excavate and embank material only within the limits on the Plans or as directed. Prevent disturbing material and vegetation outside of the slope limits.

The Engineer may designate excavated soils that cannot be properly compacted in embankments, as unsuitable.

When unsuitable material is encountered at the required minimum depth of excavation, remove the unsuitable material to the depth directed. Allow for measurements to be taken before backfill is placed.

Dispose of unsuitable material or excess usable material at approved locations. Protect and preserve geotechnical instrumentation as shown on the plans.

Obtain the property owner’s written permission to dispose of unsuitable material or excess usable material at locations outside the right-of-way limits and a waiver of all claims against the State for any damage to such land which may result. Obtain all permits required by law for such disposal. Furnish a copy of such permission, waiver of claims, and permits to the Engineer before commencing work.

Ensure that all disposal areas are properly graded and drained. Blend the outer limits of unsuitable material into surrounding grounds with no noticeable break or variation readily discernible. When existing roadway embankment slopes are used as disposal sites for unsuitable or excess useable material, finish the slopes with a motor grader or other approved method.

When the volume of suitable excavation is not sufficient for constructing the fill to the grades indicated, furnish the necessary borrow from approved sources. Borrow may be necessary even though not shown on the Plans. The source and acceptability of the borrow is subject to approval.

Do not place borrow material until after the usable roadway excavation has been placed in the fill. If more borrow than is required in placed, resulting in or as a result of the unnecessary disposal of usable excavation, the amount of such disposed material will be deducted from the borrow quantity.

Obliteration of Roadways includes all grading operations necessary to incorporate the existing roadway into the new roadway and surroundings in order to provide a pleasing appearance from the new roadway. Fill ditches not required for drainage and grade to the approximate original ground contour.

Do not place soil-aggregate containing glass cullet:

- Within four feet from the face of any embankment slope,

- Within 150 feet from any surface water body,

- In embankment areas where culvert placement is required,

- In contact with any geosynthetic material.

Submit site plans for the planned use/development of Staging and Disposal Sites for the engineer’s approval. Site plans must be consistent with the applicable permit found in Appendix E. Site plan should ensure that all areas are graded to drain.

  - Provide a site development plan to the Project Engineer for approval.

  - The Department will provide engineered slopes based on material properties encountered in the field.

203-3.02 ROCK EXCAVATION AND SLOPE STABILIZATION. Excavate rock by blasting, ripping, or both.

- Overburden Exploration. Conduct overburden exploration to determine the depth of soil overlying proposed rock cuts. Use this information to adjust the planned slope limits, and the excavation quantities. Provide the Engineer a daily report of the depths encountered during exploration. Report depths at 25-foot intervals along the cut. Include station, offset and depth at each location.

Conduct exploration by drilling, probing, excavating test pits or any other method approved by the Engineer.

Submit an exploration plan for the Engineer’s approval prior to conducting any work. Include the station limits of the proposed exploration, the spacing between holes or pits, and the method of exploration.

- Blasting. This work includes drilling, loading, and blasting rock, using controlled blasting, production blasting and trim blasting techniques as shown in the Plans and specifications or as directed by the Engineer.

  - General Blasting Program and Plan. Not later than two (2) weeks prior to the commencement of any drilling and blasting operations, submit to the Engineer for his approval, a General Blasting Program Plan for the entire project. Do not commence any drilling or blasting operations until the General Blasting Program Plan is accepted by the Engineer. Include the following in the General Blast Program Plan:

    - Description of the overall blasting program, including general sequence of the work and a generalized schedule showing where and when blasting and excavation is expected to be conducted.

    - Traffic routes and scheduled closures.

    - Tentative blast design details for each major rock cut or sequence of cuts, rock type and tested blast parameters, including hole diameters, production and line hole spacing and depths, type of explosives and initiators, powder factors, and delay and firing sequences to be used in the test sections described below. Provide a results report within three (3) days of test blast, including a proposed Production Blasting Plan for the applicable rock cut(s). Allow one (1) day for Engineer review. Revise proposed Production Blasting Plan as required by the Engineer. Incorporate results into Production Blasting Plans following Engineer approval.

    - Provide a Production Blast Plan Prior to each production blast as set forth in Subsection g, below.

    - Location of explosive storage facilities.

    - Description of warning signals and signs and safety procedures.

    - Proposed measures for protection of structures, facilities, adjoining work, and sensitive fish and wildlife habitat.

    - Number and type of seismographs (if required) proposed for monitoring the blasts.

    - Techniques for drilling and loading explosives in wet or water filled blast holes. (10)Proposed Rock Bolt, Rock Dowel, and Drain Hole work, where needed. (11)Proposed measures to identify and protect existing utilities during blasting operations.

For convenience, the General Blasting Program may group together similar cuts with similar rock types, geometry and other characteristics. Conduct test blasting to establish that the General Blasting Program results in acceptable final rock slope conditions. Submit results of the test blasting for evaluation and approval by the Engineer. The General Blasting Program shall be tentative, pending the approval by the Engineer or test blasting conducted as set forth in Subsection g. below.

  - Blaster in Charge. Not later than two (2) weeks prior to the commencement of any drilling and blasting operations, employ and designate the Blaster in Charge (“Blaster”) for the project to the Engineer. Provide documentation showing that the Blaster is licensed and authorized under all applicable federal, state, and local laws or regulations to possess, transport, store and use explosives of the type to be used on the project. Document the Blaster has at least 8 years of

blasting experience utilizing controlled blasting techniques including pre-splitting. Require the Blaster to be on the site during all loading and blasting operations. Assign the Blaster the responsibility for ensuring that the safety procedures set forth below are followed and the record keeping requirements are met.

  - Pre-blast Meeting. Hold a pre-blasting meeting at the jobsite, prior to commencement of any drilling and blasting operations, with a minimum of the Contractor, Blaster and representatives of the Engineer. Discuss the General Blasting Program and Blasting Plans and visit enough specific sites as are necessary to familiarize the participants with the details of the blasting operations.

  - Safety. Submit a safety plan for approval by the Engineer that includes plans for closure of roads, warning signals, notification of affected local, state and federal agencies. Include in the plan methods used to protect life and health, public and private property, new work or existing work on the project, nearby structures, wetlands, waters and wildlife. Hold a safety meeting prior to the commencement of drilling and blasting work to address safety issues with respect to drilling and blasting.

    - Warning Signals. Establish a method of warning all personnel on the job site near the blast area of an impending blast. The warning signals shall consist of an audible horn or siren signal five (5) minutes prior to the blast and a second signal one (1) minute before the blast, at a minimum.

    - Inspection and All Clear Signal. After the blast, the Blaster shall observe the area of the blast for five (5) minutes to guard against injury or damage due to rockfall. The Blaster shall then inspect the blast area to determine that all explosive charges were detonated. After these inspections, the Blaster shall sound an audible horn or siren as an all-clear signal to alert all personnel that the area is safe for entry.

    - Misfires. If a misfire occurs, the Blaster shall follow appropriate procedures to handle the misfire, including, but not limited to: determining why the misfire occurred; excluding all but essential personnel from the blast area; closing nearby roads or facilities; repairing the initiation system; and correcting the misfire in a safe manner. If unable to solve the problem call consultants skilled in correcting misfires.

  - Use of Explosives.

    - Conduct all blasting operations, including storage, transportation and handling of explosives and blasting agents in accordance with all local, State, and Federal laws and regulations, including the applicable provisions of the Standard Specifications. Submit storage plans to the Engineer for approval and confirm the Engineer’s approval prior to ordering and shipping any explosive materials to the jobsite.

    - Use caps for a specific period from a single lot number, to help ensure the accuracy of firing times.

    - Blast hole conditions may range from dry to wet and filled with water. Describe in the General Blasting Program Plan appropriate techniques for any moisture conditions that are encountered. Use whatever type of explosives and accessories are necessary to achieve the desired result.

  - Test Blasts. Drill, blast, excavate and scale to a final finish surface short cut sections of each rock type on the project as necessary to determine appropriate methodology to achieve the desired result prior to commencement of full-scale blasting operations. The General Blasting Program Plan sets the initial methodology for the Test Blast(s). The Blaster shall prepare the Blasting Plans for each full-scale blast after results of the Test Blast(s) are analyzed.

Record each Test Blast using a digital video camera. Provide the video records to the Engineer for approval of the method prior to completion of the Test Blasting.

Set the controlled blast hole spacing initially to a maximum of 2.5 feet between 3 inch holes. After analysis of the initial Test Blast results, the Blaster or the Engineer may adjust the controlled blast hole spacing and/or diameter in additional test sections.

Do not commence work on any Test Blast until the Engineer analyzes the previous Test Blast results and approves the next test. The Engineer will complete the analysis of each Test Blast within 48 hours of the shot.

The Engineer will analyze the characteristics of the blasts and the final surfaces of the Test Blast cut slopes with respect to criteria the Engineer deems necessary. The Blaster shall adjust the blasting methods with respect to hole spacing, hole diameter, hole loading, sequencing and other factors that may require adjustment until methods and the final product are acceptable and approved by the Engineer.

Following completion of Test Blasting, revise the General Blast Program Plan and submit to the Engineer for approval. If at any time during the progress of the work, the approved methods of blasting and drilling fail to produce the desired results (a smooth, stable backslope), the Blaster shall revise the blasting methodology and submit an updated General Blast Program. Conduct additional Test Blasts as is necessary to evaluate if the revised methods are achieving the desired results.

  - Production Blasting Plan. Submit a Production Blasting Plan to the Engineer for approval at least 24 hours prior to each blast. Include in the Production Blasting Plan details of the drilling and blasting pattern including, at a minimum, the following information:

    - Station limits, number of blasts, and time of blast.

    - Plan and section view drawings of each blast indicating sizes, depths, angles, patterns and spacing of the holes, burden thickness and expected rock types.

    - Drill hole diameters and depths including subdrilling depths.

    - Drill steel diameter and bit types.

    - Stemming length and type of materials used for stemming.

    - Loading details including trade names, types, sizes of explosives.

    - Sizes, trade names of primers, initiators and other accessories.

    - Proposed initiation and delay sequences of the blast holes.

    - Weight of explosives per hole and per delay and powder factors, including weight of explosives per square yard of finished backslope.

    - Anticipated peak particle velocities at locations specified and as requested by the Engineer.

    - Show recreational access points and/or trail locations.

If a change in drilling or blasting methods is necessary, submit a revised Production Blasting Plan for the affected work at least one (1) week prior to commencing the change of work.

  - Blasting Records. Maintain a blasting record for each day of blasting work. Submit the record to the Engineer prior to the next workday. At a minimum, the record shall include the following:

    - The date of blasting.

    - The number of blasts.

    - The time of blasts.

    - The station limits of the blasts.

    - Plan view and section view of each blast with notes indicating free face, burden, spacing, height of lift, hole diameter, stemming depth, hole angles, hole depths, including subdrill depth.

    - Notes regarding conditions encountered in the drill holes, including soft or fractured zones, water table, alignment problems.

    - Loading diagram indicating types and amounts of explosive, primers, initiators, stemming depth, powder factors, trade names and sizes of explosives, primers and initiators.

    - Sequence of the shot, including surface delay times, and initiator delay times.

    - Remarks regarding results of the shot including damage, misfires, fly rock and other unusual results or effects.

    - Digital videos or high-speed photographs of each blast, using a method approved by the Engineer in the test blasting program. The photographs, film, videotape or electronic files recoding each blast will become part of the project records.

    - Signature of Blaster.

  - Controlled Blasting. Use controlled blasting techniques to prevent back break and produce a stable cut face sheared along the designated neat excavation line.

    - Excavate all rock cuts over 10 feet in height using controlled blasting methods to protect the backslope. Controlled blasting holes are closely spaced holes drilled along the plane of the final design slope. Controlled blasting is either preshear blasting or cushion (trim) blasting. Where the total burden is greater than 10 feet, use preshear blasting. Where the total burden is less than 10 feet, use cushion blasting. Detonate explosives in the preshear holes before the production hole charges are detonated. Detonate explosives in cushion blasting holes after the production hole charges are detonated.

    - Drill controlled blasting holes between 2.5 inch and 3 inch in diameter and spaced 2 feet to

2.5 feet apart as approved by the Engineer following Test Blasts. Do not drill controlled blasting holes deeper than 30 feet, unless the Contractor demonstrates that deeper holes can be drilled while maintaining specified tolerances and achieving the desired result. Determine the optimum spacing for controlled blast holes for each rock type and condition during the test blasting.

    - Do not construct benches in finished rock back slopes unless approved by the Engineer or shown in the plans. Where more than one lift is required in a cut, the Engineer allows an offset for drilling equipment clearances as shown in the plans.

    - Lightly load controlled blasting holes with explosives designed for the purpose and no larger than one half the diameter of the hole. Evenly distribute the explosives throughout the plane of the final slope. Load all controlled blasting holes. Do not use Ammonium Nitrate Fuel Oil (ANFO) in controlled blasting holes. Stem controlled blast holes from the top charge to the collar of the drill hole with dry sand or angular granular material passing the 3/8 inch sieve.

    - Drill controlled blasting holes to tolerances of plus or minus 3 inch at the collar and plus or minus 9 inch along the length of the hole.

  - Production Blasting. Use methods and materials necessary to fragment and loosen the rock inside the design excavation limits, while leaving a smooth, stable back slope using the controlled blasting methods discussed above. Use appropriately designed delay sequences and allowable

charge weights per delay to minimize ground vibrations and prevent damage to buildings, structures, utilities, sensitive fish or wildlife habitat and other facilities.

    - Remove all loose rock, overhanging trees and other loose objects or dangerous conditions in or in close proximity to the cut slope area or render the condition safe prior to blasting. Remove all material loosened or render safe all conditions aggravated by blasting operations as an integral part of the excavation and scaling operations. Cease further drilling or blasting work until the Engineer approves the resolution of such conditions.

    - Strip overburden before drilling blast holes.

    - Drill production holes no closer than 6 feet of the controlled blasting line. Drill the last line of production holes (or buffer holes) closest to the controlled blasting line parallel to the controlled blasting line.

    - Drill production holes shall not be greater than 6 inch in diameter, unless approved by the Engineer.

    - Detonate production hole charges in a delay sequence toward the free face, with no more than 500 lb of explosive detonated per delay.

    - Drill buffer holes, if used, from 2.5 inch to 3 inch in diameter in one line parallel to, and not closer than 3 feet from the controlled blasting line. Load buffer holes to no more than 50% of the charge that would be used in adjoining production blasting holes. Detonate the buffer hole charges toward the free face on a delay sequence, after the production hole charges are detonated. Determine the need for buffer holes in the test blasting section.

    - Remove material remaining more than 8 inches inside neat line rock slopes by scaling, controlled blasting techniques or other methods approved by the Engineer unless specifically exempted by the Engineer for aesthetic, geological or safety reasons.

    - Remove loose material from rock slope failures or slides and dispose of the material at the contract price for unclassified excavation if the Engineer determines the failure did not occur as a result of the Contractor’s methods.

  - Access for Inspections. Unless dangerous conditions prevent access, provide continuous access to the excavated rock surfaces for inspections by the Engineer or designated representatives. Provide all labor and equipment required by the Engineer to access the rock surfaces. Inspections shall be conducted within forty eight (48) hours following each blast.

  - Scaling. Stabilize new rock slopes following completion of each shot and throughout the Contract period to ensure that rock slopes are stable by removing all loose, hanging, or potentially dangerous rock from the new face and from surrounding existing slopes, as required by the Engineer.

    - Conduct scaling work in accordance with Section 210 of these special provisions or as approved by the Engineer.

    - Scale following each shot as an integral part of the excavation of each lift. Do not commence drilling for the next lift until scaling is completed, inspected and approved.

    - The Engineer may require additional scaling in accordance with Section 210 following completion of excavation, due to rebound effects, loosening caused by weather or other reasons.

  - Ditchline/Subgrade Blasting. Where rock is encountered in ditches and below the subgrade, rip or drill and blast to the depth shown on the plans or as directed by the Engineer to fracture the rock foundation. Use either procedure to provide a stable draining interlock between selected material and the rock surface. If blasting is used, space holes closer than production holes and load the

holes lighter. Stem appropriately to minimize rifling. Provide an excavator / backhoe or other equipment to enable the Engineer to verify the effectiveness of ripping/blasting. Provide additional ripping or adjust the hole pattern and loading if the procedure fails to fracture the underlying rock to the depth shown on the plans. Prior to placement of selected material, compact the ripped/fluff blasted area to the satisfaction of the Engineer.

  - Drain Holes. Drill drain holes in rock slopes to relieve excess water pressure as specified or as directed by the Engineer. The Engineer will determine the location and construction details of the drain holes depending on the conditions encountered in each slope to target seepage location. Drain holes will be 2- to 4-inch diameter, unlined, inclined upward 2 to 10 percent from horizontal, and extended 30 feet into the rock slope.

  - Access Road Stabilization. Remnant access roads/trails remaining after excavation work shall be stabilized in a manner consistent with other project work (TRM for slopes between 2H:1V and 1.5H:1V or anchored wire mesh or rock buttresses for slopes steeper than 1.5H:1V). Permanent over-steepened slopes will not be permitted.

- Stabilization. Stabilize new and existing rock as directed by the Engineer. Rock stabilization shall be by rock bolts or rock dowels. Install rock bolts and rock dowels in accordance with Section 211 of these special provisions.

203-3.03 EMBANKMENT CONSTRUCTION. Prepare the areas upon which embankments are to be placed, construct dikes within or outside the right-of-way when required, place and compact approved material within the roadway areas where unsuitable material has been removed, and place and compact embankment material in holes, pits, and other depressions within the roadway area. Use only approved materials in the construction of embankments and backfills. Embankment material will be approved for gradation following placement but prior to compaction.

Construct the embankment with selected material meeting the requirements of Subsection 703-2.07. Embankment and selected material may be obtained from excavation, rock excavation, common excavation or borrow.

Where the plans call for placement of selected material and excavation is required, the existing material may be left in place if tests determine that it will meet the appropriate selected material requirements and as approved by the Engineer. Any reduction in excavation quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.

Do not place rocks, broken concrete or other solid materials in embankment areas where piling is to be placed or driven, or where culvert placement is required.

Bench slopes when embankment is to be placed and compacted on hillsides, or when new embankment is to be compacted against existing embankments, or when embankment is built half-width at a time. Continuously bench over those areas as the work is brought up in layers. Make benches wide enough to permit placing and compacting operations. Begin each horizontal cut at the intersection of the original ground and the vertical side of the previous bench. Incorporate material cut out, and deemed suitable, into the new embankment and recompact along with the new material.

Scarify existing roadways, lying within 3 feet of subgrade, to a depth of 6 inches and recompact to meet Subsection 203-3.04 or 203-3.05.

When permanently frozen soils are encountered, place backfill or embankment materials in a timely manner, as directed, to minimize degradation of the foundation material. Do not place embankment over seasonally frozen ground unless authorized in writing.

Thaw and drain frozen material deemed acceptable for fill before placing in the embankment. Frozen cuts may require stage excavation: remove thawed material and allow the cut to thaw while work continues on some other portions of the project. After the material in the cut has thawed to a sufficient depth, remove

the thawed material. Repeat this operation until all frozen material is removed or the cut is excavated to grade.

When excavation is performed when freezing weather is imminent, place the specified backfill promptly, following the excavation work, at least up to a level which will allow the surface to adequately drain. Make arrangements for the timely availability of such embankment or backfill materials prior to commencement of the stripping or excavation operations, when required.

If embankment can be deposited on one side only of abutments, wing walls, piers or culvert headwalls, prevent the overturning of or excessive pressure against the structure. Do not place the fill adjacent to the abutment of a bridge higher than the bottom of the back-wall of the abutment until the superstructure is in place. When embankment is to be placed on both sides of a concrete wall or box type structure, keep the embankment at approximately the same elevation on both sides of the structure.

Place roadway embankment of earth materials in horizontal layers not to exceed 8 inches (uncompacted) for the full width of the embankment, except as required for traffic, and compact as specified before the next layer is placed. Use spreading equipment on each lift to obtain uniform thickness prior to compacting. Maintain uniform density, during compaction. Add or remove water, as necessary, to obtain the required density. Route compaction equipment uniformly over the entire surface of each layer.

Place rock embankment in lifts not thinner than the thickness of the largest rocks. Restrict maximum rock dimension to 3 feet. Distribute spalls and finer rock fragments to level and smooth each lift. Place succeeding lifts without damaging previously completed lifts. Dump rock on the lift being constructed and distribute by blading or dozing to fill voids and to form a dense, well-compacted embankment. Do not place rocks over 8 inches within 2 feet of finished subgrade.

Rock is considered usable material, regardless of size. Rocks too large to be embanked, as specified above, may either be reduced to a suitable size for incorporation into the embankment or disposed of in approved areas, at your option. Replace all wasted rock from excavation with borrow at no additional cost to the Department, unless such rock is excess to project embankment requirements.

Finish the subgrade surface so it will not vary more than 0.10 foot when tested using a 10-foot straightedge nor vary more than 0.10 ft from the established grade.

When embankment is to be placed over swampy or saturated ground, end dump an initial lift of material of sufficient depth to support hauling equipment, as directed.

Repair damage to embankment caused by hauling equipment.

Construct all embankments with moisture and density control unless the Engineer determines that such controls are not feasible.

Temporary surcharging consists of two methods:

- Static Surcharge. Leave surcharge in place until the foundation material has reached stability or the required settlement has taken place.

- Rolling Surcharge. Construct a surcharge on top of the embankment to the specified elevation and continually advance the surcharge as the embankment is constructed ahead.

Use material removed from the temporary surcharge in areas indicated on the Plans. Do not dispose of temporary surcharge material without written approval. Compaction is not required for material placed in a temporary surcharge.

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL. The maximum density and

optimum moisture will be determined by ATM 207 or ATM 212.

Adjust the moisture content of the embankment material to within 2 percent of the optimum moisture content and compact each layer to not less than 95 percent of the maximum density. Acceptance densities will be determined by ATM 213.

Moisture content adjustment can be achieved through air drying or mixing soils to reduce average moisture content. Use of a Portland Cement admixture may be used at the contractor’s option or through Change Order by direction of the Engineer.

Use Portland Cement, Type I or Type I/II meeting Section 701-2.01 to amend soils that are within 6 percent of optimum moisture content when using a Portland Cement admixture. Prepare test strips for each soil type to receive a Portland Cement admixture with 40:1, 20:1 and 13.3:1 soil to Portland Cement ratios (by weight). Additional ratios can be requested by the Engineer. Submit test strip moisture density testing results to the Engineer for Approval. Embank Portland Cement treated soils at the ratio approved by the Engineer.

Apply cement at uniform rate using equipment and methods that will ensure uniformity of distribution. Allow only equipment that is used for applying and mixing the cement to pass over the treated area until after it is mixed into the soil.

Use of Portland Cement requires submission of a narrative prior to test strip construction or use with fill materials. The narrative describes proposed equipment and methods for producing and placing cement- treated fill soil. Include description and specifications of proposed equipment. Include equipment for excavating, handling, hauling, placing, mixing, and compacting cement-treated fill soil. Specifically address techniques proposed for controlling cement percentage and mixing soil and cement to form a uniform mix. Include procedures for handling soft ground conditions, wet soil conditions, and wet weather during soil treatment and placement. Describe methods for monitoring and controlling cement content during placement. Adhere to the methods described after the narrative is approved by the Engineer.

Do not use this method when wet original ground is encountered. Place three lifts using the method specified in 203-3.05 or as approved by the Engineer until attempting 203-3.04 again. Continue using 203-3.05 until embankment materials are compatible with the native or placed foundation materials as approved by the Engineer.

Compact the embankment within 20 feet of a bridge abutment full width to not less than 100 percent of the maximum density. Material used within this zone shall be graded to pass the 3 inch sieve.

203-3.05 COMPACTION WITHOUT MOISTURE AND DENSITY CONTROL. Except for rock fills and the first layer of fills over swampy ground, deposit embankment materials in layers not exceeding 8 inches in thickness before compaction.

Compact by routing construction equipment and/or rollers uniformly over the entire surface of each layer before the next layer is placed. Compact until embankment does not rut under the loaded hauling equipment with a minimum axle weight of 50,000 pounds. Drive the vehicle at a speed of 2-4 miles/hour over the entire compacted layer. If the layer being tested exhibits excessive yielding, deflection, reaction or pumping, rework the area to provide acceptable tests results prior to placement of any additional material. The following criteria apply:

- Embankment fill layers deeper than 20 feet below finished subgrade – maximum allowable deflection of 2-inches.

- Embankment fill layers within 5 to 20 feet of finished subgrade – maximum allowable deflection of 1/2-inch.

- Embankment fill layers within 5 feet of finished subgrade – if the layer being tested exhibits any yielding, deflection, reaction or pumping, rework the area to provide acceptable test results prior to placement of any additional material.

Keep dumping and rolling areas separate. Do not cover any lift by another until the required compaction has been completed.

203-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

- Items 203.0001.   through 203.0004.   and 203.0008.  . The volume measured in original position.

- Item 203.0010.	. By adding the sum of the depths of line holes drilled and loaded.

- Item 203.0016.	. By the length measured along the base of the fence.

- Items 203.0015.	and 203.0018.	. By the area covered, measured along the slope.

- Item 203.0017.  . By the square yard, in final position, measured on the slope of the ground surface. The upper and lower boundary ropes will be the measurement limits, unrestrained mesh will not be measured. No allowance will be made for overlap, whether at joints or patches. Excavation of the slope and haul will be measured under Item 203 Unclassified Excavation.

203-5.01 BASIS OF PAYMENT. When no pay item is shown in the bid schedule for “Stripping Material Sources”, removal of overburden and other unsuitable material from such Material Sources is subsidiary.

The following work is subsidiary:

- Scarifying material in place.

- Hauling of material.

- Excavating overbreak material.

- Slope rounding excavation and benching of slopes.

- Water for compaction.

- Placing and removing of temporary surcharge material.

- Work required to continually advance the heading on a rolling surcharge.

- Test pits, explorations, and testing required to evaluate the acceptability of borrow.

- Stage construction of cuts and stage excavation of material sources.

- Overburden investigation and reporting.

- Stabilization of remnant access road/trails.

- Portland Cement amendment test strip preparation.

- Portland Cement is incidental to fill placement.

Removal of slides and associated work will be paid for at the contract unit price for excavation at the location of the slide or as extra work under Subsection 109-1.05.

Grading and placement of material used within 20 feet of bridge abutments will not be paid for directly but will be subsidiary to Pay Item 203.2005.   Borrow.

Developing Staging and Disposal sites will not be measured for payment. Staging and Disposal sites are subsidiary to this section. No payment shall be made for grubbing, developing access, maintenance, operation, or final stabilization of staging and disposal areas.

All temporary drainage work shall be subsidiary to the excavation pay item.

All temporary embankment is subsidiary to the Mobilization and Demobilization pay item. Any restoration associated with temporary access or staging is subsidiary to the excavation pay item. Restoration shall be as close as practicable to original ground as determined by the project engineer.

Grading and placement of material used outside or near the bridge abutments will not be paid for directly but will be subsidiary to Pay Item 205.0006.0000 Structural Fill.

Payment will be made under:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 203.0001. | Common Excavation | CY |
| 203.0002. | Rock Excavation | CY |
| 203.0003. | Unclassified Excavation | CY |
| 203.0004. | Muck Excavation | CY |
| 203.0005. | Borrow | CY |
| 203.0006. | Borrow | TON |
| 203.0010. | Controlled Blasting | LF |
| 203.0011. | Ditchline/Subgrade Blasting | SY |
| 203.0012. | Drain Holes | LF |
| 203.0013. | Stabilization – Rock Bolt | EACH |
| 203.0014. | Stabilization – Rock Dowel | EACH |
| 203.0019. | Unclassified Excavation | LS |

CFHWY01060

### SECTION 205

EXCAVATION AND FILL FOR MAJOR STRUCTURES

Standard Modification

### 205-3.05 COMPACTION.

- Compaction with Moisture and Density Control. 2nd paragraph delete: "and ATM 214".

#### HSM20.5-113020R

Section 205

Blank Page

# DIVISION 500 — STRUCTURES

Division 500

## Blank Page

### SECTION 501 CONCRETE FOR STRUCTURES

Standard Modification

### 501-2.02 COMPOSITION OF MIXTURE – JOB MIX DESIGN.

Replace Table 501-4 with the following:

### TABLE 501-4

AIR CONTENT REQUIREMENTS

| Class of Concrete | Air Content |
| --- | --- |
| A | 6.0% 0.5% |
| A-A | 6.0% 0.5% |
| P | 3.50% minimum1 and Super Air Meter (SAM) number 0.201 |
| DS | Not required |

1Not required for web and bottom flange of precast, prestressed decked bulb-tee girders.

HSM20.23-123121

### 501-3.09 PROTECTION OF CONCRETE.

Add the following:

- Mass Concrete. Provide mass concrete plan for all cast in place concrete elements with the least dimension greater than nine feet.

Remove mass concrete elements that do not comply with the temperature acceptance criteria. The temperature acceptance criteria for mass concrete elements are:

  - Maximum allowable temperature must not exceed 160 degrees Fahrenheit.

  - Maximum temperature differential must not exceed that listed in the thermal control plan.

- Submittals. Submit a thermal control plan with design calculations for each mass concrete element. The thermal control plan and calculations must be sealed and signed by a Registered Professional Engineer in the State or Alaska. Include the following:

  - Mix design

  - Duration and method of curing

  - Maximum allowable temperature differentials between the hottest point of the concrete and the exterior concrete faces.

  - Procedures to control concrete temperature differentials at time of placement

  - Methods for controlling temperature differential

  - Temperature differential monitoring and recording system details and sample reports

  - Temperature sensor types and locations

  - Measures to ensure compliance with maximum temperature and temperature differential requirements

Determine the maximum allowable temperature differential assuming cracking due to heat of hydration does not occur.

Submit daily temperature data and progress reports to the Engineer.

Section 501

- Monitoring. Provide a temperature monitoring and recording system for mass concrete elements. The system must consist of temperature sensors connected to a data acquisition system. The system must be capable of recording, printing, and downloading temperature data to a computer.

Locate temperature sensors within mass concrete elements such that the maximum temperature difference within the element is monitored. At a minimum, monitor temperatures at the following locations:

  - Calculated hottest location

  - Two outer faces

  - Two corners except for drilled shaft elements

  - Top surfaces

Record temperature readings automatically at least every hour. Install a redundant set of sensors near the primary set with recording capability. Make records using the redundant set if the primary set fails.

Discontinue hourly temperature recording when all the following conditions are met:

    - Maximum internal temperature is falling for the previous 8 hourly measurements

    - Difference between the interior concrete temperature and the average daily air temperature is less than the allowable temperature differential for 3 consecutive days

    - There are no mass concrete elements to be placed adjacent

Protect the temperature sensor wiring to prevent movement during concrete placement. Keep wire runs as short as possible. Do not let the ends of temperature sensors come into contact with concrete supports, forms, or reinforcement.

Do not damage the monitoring and recording system.

Correct equipment failures in temperature control and monitoring and recording systems immediately.

CFHWY01060

### SECTION 503 REINFORCING STEEL

Special Provisions

### 503-2.01 MATERIALS.

Add the following:

Corrosion-Resistant Reinforcing Steel (Low-Carbon Chromium)	Subsection 709-2.01

### 503-3.02 PROTECTION OF MATERIALS.

Replace the 2nd sentence of the 1st paragraph with the following:

Before placing reinforcing steel in the work, ensure that the reinforcing steel is free of salt, rust, and foreign substances that may affect the performance of the reinforcing steel.

503-3.05 SPLICING. Replace “c. Testing/Inspection” under Item 2. Electric Resistance Butt Welded Joints with the following:

- Testing/Inspection.

Perform job control tests using a testing laboratory with experience with ASTM A370 and California Test Method 670. A job control test consists of the fabrication, under the same conditions used to produce the splice, and the physical testing of 4 sample splices for each lot of splices. An authorized Department representative will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of shop produced resistance welded butt joints is defined as no more than 150 splices of the same type of welds used for each combination of bar size and bar deformation pattern that is used in the work.

The Engineer or the Engineer's authorized representative shall witness the job control tests performed by the testing laboratory. Give the Engineer at least 7 working days’ notice before beginning control tests.

Identify sample splices with tamper proof and weatherproof markings prior to shipment to the testing laboratory.

The sample shall consist of a resistance welded butt splice bar and a control bar that are identified and marked as a set. The same reinforcing bar (hoop) may be used to provide the test weld and control bar.

Test each sample to failure in accordance with ASTM A706, ASTM A370 and California Test Method 670. Determine the ultimate tensile strength for all control bars by testing the bars to failure.

The production lot will be rejected if:

  - a sample fails within one bar diameter of the splice at less than 95 percent of the ultimate tensile strength of the associated control bar

  - necking of the bar prior to rupture, as defined in California Test Method 670, is not observed

  - a sample does not meet the mechanical requirements of ASTM A706 Grade 60

Replace “c. Qualifications and Submittals.” and “d. Testing/Inspection.” under Item 4. Mechanical Butt Splices with the following:

- Qualifications and Submittals. A splice will be considered qualified if the splice can develop a minimum tensile strength of 80000 psi, based on the nominal bar area, and the bars within the splice do not exceed a total slip shown in Table 503-3, when tested according to the relevant material ASTM, ASTM A370 and California Test Method 670.

### TABLE 503-3 ALLOWABLE TOTAL SLIP LENGTH

| Reinforcing Bar No. | Total Slip (inch) |
| --- | --- |
| 4 | 0.020 |
| 5 | 0.020 |
| 6 | 0.020 |
| 7 | 0.028 |
| 8 | 0.028 |
| 9 | 0.028 |
| 10 | 0.036 |
| 11 | 0.036 |
| 14 | 0.048 |
| 18 | 0.060 |

Submit the following information:

  - the manufacturer's name;

  - the name of the product or assembly;

  - the lot, heat, or batch number that identifies the splice;

  - the bar grade and size number to be spliced by the material;

  - a complete description of the splice and installation procedure; and,

  - Tensile Test results including:

    - bar nominal area;

    - ultimate load at failure;

    - ultimate tensile strength;

    - necking results (either visually or through strain values); and,

    - failure mechanism and location.

  - Slip Test results including:

- initial length measurements;

- final length measurements; and,

- calculated slip.

- Testing/Inspection. Perform job control tests consisting of the fabrication, under conditions used to produce the splice. For each lot of splices perform 6 slip tests and 6 tensile tests using different sample splices for each test. The Engineer will determine the limits of the lot represented by each job control test.

A lot of mechanical butt joints is defined as no more than 150 splices of the same type of mechanical butt splice used for each combination of bar size and bar deformation pattern that is used in the work.

Make splice samples using the same splice materials, position, equipment, and following the same procedures as used to make splices in the work. Make splice samples at least 5 feet long with the splice at mid-length. Shorter sample splice bars may be used if approved by the Engineer. Splice samples may be produced at the time of bar manufacture.

Perform job control tests in the presence of the Engineer. Splices tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 7 working days prior to performing testing.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample according to the relevant material ASTM, ASTM A370 and California Test Method 670. Perform tensile testing until partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection.

The production lot will be rejected if:

  - the minimum individual tensile strength of the sampled splices is less than 80000 psi based on the nominal bar area

  - the maximum individual slip length of the sampled splices is greater than the limits in Table 503-3

Delete numbered paragraph 5. Mechanical Lap Splices and substitute the following:

- Mechanical lap Splices. Do not use mechanical lap splices.

503-5.01 BASIS OF PAYMENT. Add the following

Payment will be made under:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 503.2000. | Corrosion-Resistant Reinforcing Steel, Low Carbon Chromium | LS |

CFHWY01060

### SECTION 504 STEEL STRUCTURES

Special Provisions

504-2.01 MATERIALS. Add the following:

High Performance Steel	ASTM A709 Grade 70T3

### 504-3.01 FABRICATION.

Under Item 2 replace the 10th paragraph and subparagraphs after “Cold bend load-carrying rolled-steel plates as follows” with the following:

Cold bend at room temperature cross-frame or diaphragm connection plates up to 0.75 inches thick with minimum bending radii of 2.25 times the plate thickness in inches. Cold bend all other steel plates and bars with minimum bend radii of 5 times the plate thickness in inches measured to the concave face of the plate.

Before bending, round the edges of the plate to a radius of 1/16 inch throughout the portion of the plate to be bent.

Under Item 3 replace the 3rd paragraph with the following:

Use tension flange splices only as shown on the Plans or as approved.

Replace Item 4 Bolt Holes with the following:

- Bolt Holes. Drill bolt holes. Make finished bolt holes 1/16 inch larger than the nominal diameter of the bolt. Ensure holes are clean cut without burrs or ragged edges. Material with poorly matched holes will be rejected.

When material forming parts of a member is composed of not more than 5 thicknesses of metal, and whenever the thickness of the metal is not greater than 3/4 inch for structural carbon steel or 5/8 inch for alloy steel drill the holes to full size.

With approval from the Engineer, holes for field connections and field splices may be drilled full size when there are more than 5 thicknesses or when any of the main material is thicker than 3/4 inch in carbon steel, or 5/8 inch in alloy steel. If not allowed or when required under paragraph 7 below, subpunch or subdrill the holes 3/16 inch smaller. After assembling, ream them to size or drill them from the solid to full size.

Ream holes cylindrical and perpendicular to the member. Direct reamers mechanically, where practicable.

Ream and drill using twist drills. Assemble connecting parts requiring reamed or drilled holes and securely hold them while reaming or drilling them. Match mark them before disassembling.

Subpunch (or subdrill if required) holes for field connections and field splices of continuous beams while assembled in the shop. Obtain approval of the assembly, including camber, alignment, and accuracy of holes and milled joints before beginning reaming.

When partial assembly is permitted ream holes for web member connections with steel templates.

Ream or drill the full size of the field connection through templates after carefully locating the templates as to position and angle and firmly bolting them. Use exact duplicate templates used to ream matching members or the opposite faces of one member. Accurately locate templates for connections that duplicate so that like members are duplicates and require no match-marking.

Accurately subpunch or subdrill holes so that after assembling (before reaming), a cylindrical pin 1/8 inch smaller in diameter than the nominal size of the punched hole may be entered perpendicular to the face of the member, without drifting, in at least 75 percent of the contiguous holes in the same plane. If the requirement is not fulfilled, the badly punched pieces will be rejected. If any hole will not pass a pin 3/16 inch smaller in diameter than the nominal size of the punched hole, the material will be rejected.

Ream or drill holes so that 85 percent of the holes in any contiguous group after being reamed or drilled show no offset greater than 1/32 inch between adjacent thicknesses of metal.

Provide in steel templates hardened steel bushings in holes accurately dimensioned from the center lines of the connection as inscribed on the template. Use the center lines to locate accurately the template from the milled or scribed ends of the members.

Delete the first paragraph of Item 7. Welding and replace with the following:

- Welding. Perform all welding, including welding of shear connectors, and Nondestructive Examination (NDE) as specified or shown on the Plans. Conform to ANSI/AASHTO/AWS Bridge Welding Code D1.5 when welding new steel bridge girders, beams, stringers and shear connectors. Conform to the Structural Welding Code AWS D1.1 when welding all other carbon steel structures and to the Structural Welding Code – Stainless Steel AWS D1.6 when welding stainless steel.

Test all steels for acoustically anisotropic properties and modify testing procedures when high levels of anisotropy are observed. Coordinate testing procedures with the Department’s QA inspector prior to starting fabrication.

### 504-3.02 ERECTION.

Replace the second sentence of the first paragraph of Item 4. Erection Plan with the following:

Submit the erection plan not less than 60 days prior to erecting the structural steel.

### 504-3.03 PAINTING.

Remove this section and replace with the following:

### 504-3.03 COATING.

Apply a thermal spray coating on all girders and splice plates in accordance with SSPC-CS 23.00 to provide a Class B surface condition on all faying surfaces at slip-critical connections. Lateral bracing, cross frames and other associated members may be hot-dip galvanized in accordance with Subsection 716-2.07.

The top surface of girder top flanges outside of splice locations may be coated with a single component, moisture cure, polyurethane meeting the prime coat requirements of Subsection 708-2.01

### 504-5.01 BASIS OF PAYMENT

Add the following:

Item 504.XXXX.XXXX Structural Steel Freight. At the contingent sum prices specified in the Directive to authorize the work, for all labor, supervision, materials, equipment, and incidentals to store, handle, & transport the Structural Steel from Port of Long Beach, California to the Project site located in Cooper Landing, Alaska.

Payment will be made under:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 504.xxxx. | Structural Steel Freight | CS |

#### CFHWY01060

506-2.01 MATERIALS. Add the following:

Ekki Wood Railing. Use Lophira Procera meeting the following requirements:

  - Pieces free of sapwood and wane

  - Width tolerances within +/- 1/8 inch

  - Depth tolerance within +/- 1/8 inch

  - Hole position within +/- 1/8 inch

  - Length of surface checks and splits less than 10 inches

  - Crook 1 inch maximum over full length Submit certification from one of the following agencies:

    - Messrs. Supervise Marine & Engineering Co., Wallenhaven NE-71, Rotterdam

    - Lloyds of London, London

    - Other approved internationally recognized grading bureau

506-3.01 GENERAL. Add the following:

Have Ekki supplier chamfer edges as shown on the plans prior to shipping. Treat cut ends, drilled holes and surface abrasions with wax to prevent drying. Plug unfilled holes in accordance with suppliers written instructions.

Do not drag, drop, or otherwise damage Ekki members. Use belt type slings and chokers when handling Ekki members to prevent damage. Use protective angles and blocking at pick up points to prevent damage of Ekki members.

506-5.01 BASIS OF PAYMENT. Add the following:

Payment for the Ekki Wood Railing and it’s attachment to the pedestrian railing is subsidiary to the 507.0002.0000 Pedestrian Railing item.

#### CFHWY01060

507-1.01 DESCRIPTION. Add the following:

Bridge barriers and railing are not included in this contract but are shown for completeness. Provide and install reinforcing steel in the deck and wingwalls needed for future bridge barriers and railing as part of this contract.

507-5.01 BASIS OF PAYMENT. Replace the subsection with the following:

Reinforcing steel partially contained within bridge barriers or railing will be paid for under Section 503.

### 515-3.11 INSTRUMENTATION AND DATA COLLECTION.

Delete Item 1. Shaft Inspection Device.

Replace the first paragraph of Item 2. Crosshole Sonic Logging with the following:

Provide CSL inspection of all drilled shaft foundations across their entire lengths with the following exception:

a) CSL inspection may be omitted in drilled shafts four feet or less in diameter where concrete in placed in the Dry-Shaft Process according to the requirements of Subsection 501-3.05.

Provide an independent CSL inspector with at least 3 years’ experience in CSL testing to inspect the drilled shaft and prepare the CSL report.

515-5.01 BASIS OF PAYMENT. Replace with the last paragraph with the following:

Payment will be made under:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 515.0001. | Drilled Shaft | LS |
| 515.0002. | Unclassified Shaft Excavation, (Shaft Size) | LF |
| 515.0003. | Special Shaft Excavation, (Shaft Size) | LF |
| 515.0004. | Shaft Casing, (Shaft Size) | LF |
| 515.0005. | Shaft Instrumentation and Data Collection | CS |

#### CFHWY01060

516-2.01 MATERIALS. Add the following:

Modular Bridge Joint System,	Subsection 732 Add the following Subsection:

516-3.04 MODULAR BRIDGE JOINT SYSTEM. Design, fabricate, form, and install expansion joints as shown on the Plans. For portions of expansion joints embedded in bridge barriers or bridge railing, design, fabricate, deliver and store for future installation.

- Modular Bridge Joint Systems (MBJS).

  - General. Provide MBJS that satisfy the testing requirements of the AASHTO LRFD Bridge Construction Specifications, Second Edition, Appendix A19.

Provide and install MBJS in one piece for the length of the joint.

Install the expansion joints according to the manufacturer's recommendations.

  - Design. Design MBJS in accordance with the current edition of the AASHTO LRFD Bridge Design Specifications (LRFD), as modified by the interim revisions in effect at receipt of the Notice to Proceed.

Design MBJS to accommodate the required minimum design movement range specified in the LRFD using the estimated movement range shown on the Plans.

  - Working Drawings. Submit for approval working drawings for Modular Bridge Joint Systems. Include in the drawings details not provided in the Plans for the fabrication and installation of the MBJS including, but not limited to:

    - Plan and section views of the MBJS showing dimensions and tolerances.

    - Details showing all welded and bolted centerbeam/support bar joints and all shop splices.

    - Complete details of all components and sections showing all material incorporated into the MBJS.

    - All ASTM, AASHTO, or other material designations.

    - Details of the corrosion protection system

    - Details showing all lifting locations and lifting mechanisms

    - Details showing temperature adjustment devices and opening dimensions relative to temperature

    - Calculations, stamped by a registered Professional Engineer documenting the design of the MBJS.

    - Manufacturer’s certificate of compliance with the AISC Quality Certification Program, Simple Steel Bridges.

    - Welding plan as specified in Subsection 504-3.01.7.

    - Certification that the MBJS has passed the Prequalification Test required in Subsection 516-3.04.1.a.

    - Certification that the bearings, springs, and equidistant devices are the same formulation, manufacturer, and configuration as were used in the Prequalification Test. In each certification, provide the name and address of the manufacturer of the springs, bearings and equidistant devices.

    - Manufacturer’s certificate of compliance for the PTFE sheeting and fabric.

    - A written maintenance and part replacement plan prepared by the joint manufacturer, including a list of parts and instruction for maintenance inspection, acceptable wear tolerances, methods for determining wear, and procedures for replacing worn parts.

    - Method of installation, including, but not limited to: sequence, installation gap setting for various temperatures, and support during concrete placement.

    - Requirements for proper MBJS storage and details of temporary support of the MBJS for shipping and handling.

    - Details of blockout reinforcement required to satisfy AASHTO LRFD requirements and accommodate the MBJS.

    - Temporary bridging plan to accommodate construction traffic following installation.

  - Fabrication. Fabricate MBJS in accordance with the Contract documents and the approved working drawings.

  - Installation. Install MBJS in accordance with the Contract documents, the approved working drawings and all MBJS manufacturer’s recommendations.

Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

    - Preinstallation Inspection. Immediately prior to installation, allow the Engineer to inspect the MBJS for:

      - Damage due to shipping and handling

      - Alignment of MBJS in accordance with approved working drawings

      - Complete bond between the seal and the steel locking edge

      - Correct placement and full connection of concrete anchors or studs

      - Correct placement of elastomeric springs and bearings

      - Correct and successful placement of waterproofing membranes, if utilized

      - Other items at the discretion of the Engineer

Correct all deficiencies noted in the Engineer’s inspection to the satisfaction of the Engineer prior to commencing installation of the MBJS.

    - Installation. Protect the blockout and supporting system from damage and construction traffic prior to installation of the MBJS.

Install the MBJS at the proper gap opening corresponding to the ambient air temperature at the time of installation as shown on the approved working drawings.

Remove temporary connections and attachments prior to concrete placement. Grind smooth surfaces where temporary attachments were made with welds and repair all damage to the corrosion protection system to the satisfaction of the Engineer using a method approved by the Engineer.

Construct formwork that excludes concrete entry into MBJS support boxes and that does not impede the free movement of the MBJS.

    - Concrete Placement. After MBJS installation, completely backfill the blockout with Class A concrete conforming to the requirements of Section 501.

Fully support the MBJS during concrete placement. Thoroughly vibrate concrete so as to adequately consolidate concrete underneath the support boxes and edgebeams.

    - Tolerances. Fabricate and install MBJS conforming to the following tolerances.

      - Grade and Cross slope. Top of MBJS recessed from the finished roadway surface +0 inch to -1/4 inch.

      - Vertical Position of Edgebeams and Centerbeams. No more than ±1/8 inch difference, as measured vertically from a straight line connecting the top of deck profile in each side of the MBJS, among the tops of all edgebeams and centerbeams.

      - Gap Width. Do not vary the distance measured at each end of an MBJS between adjacent edgebeams and centerbeams or adjacent centerbeams more than 1/2 inch.

    - Protection of MBJS Installation. Do not allow construction traffic on the MBJS for at least 72 hours after concrete placement. With the approval of the Engineer, bridge over the MBJS in accordance with the approved working drawings.

At no extra cost to the Department, completely replace all joint seals that are broken or cut during installation operations and due to post-installation construction activities.

    - Watertightness Test. No more than seven days prior to opening the bridge to traffic, conduct a watertightness test on completed MBJS installations. Flood the MBJS to a minimum depth of three inches for a minimum of one hour. At no extra cost to the Department, repair all observed leaks in accordance with the manufacturer’s recommendations and the requirements of item (5). Perform a retest on the repaired joint.

- Curb and Barrier Sliding Plates. Fabricate curb and barrier sliding plate assemblies in accordance with the requirements of Section 504. Deliver and store curb and barrier sliding plate assemblies at a location designated by the Engineer.

CFHWY01060

# DIVISION 600 — MISCELLANEOUS CONSTRUCTION

## Blank Page

Special Provisions

Replace Section 606 with the following:

### SECTION 606 GUARDRAIL

606-1.01 DESCRIPTION. Construct new guardrail, terminal sections, transition rail, and permanent crash cushions.

The permanent crash cushion, hereafter referred to as, "crash cushion," includes the complete assembly (crash cushion, foundation, backstop or transition) represented in the FHWA eligibility letter(s).

Remove and reconstruct or remove and dispose of existing guardrail, terminal sections, transition rail, and crash cushions.

#### CR606-123121R

Furnish and store new highway safety appurtenance essential replacement parts (replacement parts) listed in Table 606-1. Repair damage, from highway crashes, with the replacement parts.

CR606.13-072120R

### 606-1.02 SUBMITTALS.

- Submit the following at the preconstruction conference and receive approval before installation.

  - Permanent Crash Cushions.

    - FHWA Eligibility Letter(s). Eligibility letters demonstrating each crash cushion assembly is MASH 2016 compliant with the AASHTO 2016 Manual for Assessing Safety Hardware (MASH-16) Test Level 3. Demonstrate the eligibility letter shielding widths cover the hazard widths and travel directions shown in the plans.

    - AASHTO Listing Category. AASHTO listing or documented updates for the crash cushion classification as listed in the 2011 AASHTO Roadside Design Guide, Section 8.4.

    - Manufacturers' Shop Drawings, Assembly, and Installation Instructions. Submit shop drawings and detailed assembly and installation instructions for the crash cushion as included in the FHWA Eligibility Letters.

    - Manufacturer Certification Letter. Certify the crash cushion(s) meet the requirements of the FHWA eligibility letter(s), are suited to the Contract requirements including the environmental conditions at the installation site.

    - Manufacturers' Installer Certification Letter. Certify the installation contractor is familiar with and trained to install the crash cushion.

    - Manufacturers' Installation Checklist. Submit a crash cushion installation checklist.

  - Parallel Terminals.

Manufacturer Installation Checklist. Submit an Assembly Installation Checklist.

- Submit the following after installation.

  - Permanent Crash Cushions.

    - Manufacturer Certification Letter. Certify the installed crash cushion(s) meet the requirements of the FHWA eligibility letters. Submit the certification letters(s) signed and dated no more than 14 days after installation.

    - Manufacturers' Installation Checklist. Submit the completed installation checklist signed by the Installer and Manufacturer no more than 14 days after installation. Complete the checklist after each assembly.

  - Parallel Terminals.

Manufacturer Installation Checklist. Submit the completed installation checklist signed by the Installer and Manufacturer no more than 14 days after installation. Complete the checklist after each assembly.

606-2.01 MATERIALS. Use materials that conform to the following: Concrete, Class B	Section 550

Flexible Delineator Posts	Subsection 730-2.05

Guardrail Connection Plate	Subsection 710-2.12

Thrie-Beam Terminal Connector	Subsection 710-2.12

Guardrail Hardware	Subsection 710-2.07

Guardrail Posts and Blockouts	Subsection 710-2.06

High Strength Bolts	Subsection 716-2.03

Metal Beam Rail	Subsection 710-2.04

Terminals	Subsection 710-2.11

Terminal Markers	Subsection 730-2.05

Wire Cable	Subsection 709-2.02

Guardrail Reflector Assembly Brackets, Side-Mounted. Aluminum alloy. Retroreflective Sheeting.

- Post-Mounted Flexible Delineators and Guardrail Reflectors. ASTM D4956 Type IX or XI.

- Terminal Markers. ASTM D4956 Type VIII, IX or XI. Permanent Crash Cushion Assembly.

Crash cushions include the complete assembly as included in the Eligibility Letter, the crash cushion, the foundation, and rigid backup anchorage, or transition connection. Install an added Terminal Marker or other flexible delineator to the front of the crash cushions as recommended by the Manufacturer.

Design the crash cushion for the installation location environment. Snow combined with frequent freeze- thaw cycles creates significant ice buildup that may impair the performance of the crash cushion. Design to mitigate the effects from snow and ice. Crash cushions using supports that interlock and travel within fixed tracks at or below the first six inches from ground level, and crash cushions not designed to mitigate snow and Ice buildup are not acceptable for permanent use. Crash cushion covers, when available from the manufacturer, are required as part of the crash cushion installation.

Crash Cushion Classifications. 2011 AASHTO Roadside Design Guide, 4th Edition. The Engineer will determine the final classification of each materials submittal. Provide redirective and non-gating crash cushions of the type specified in the plans and matching the description noted below.

- Sacrificial: Demonstrated designed for a single impact.

- Reusable Crash Cushion. Demonstrated to have major components survive most impacts intact and salvageable. Some components require replacement after a crash.

- Low-maintenance and Self-restoring Crash Cushion. Demonstrated to suffer very little, if any damage, upon impact and easily pulled back into their full operating condition. They may partially rebound after an impact and may only need an inspection to ensure that no parts have been damaged or misaligned.

CR606-123121R

### CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL. Install guardrail and terminals at the locations shown on the Plans. Conform to the Alaska Standard Plans and these Specifications.

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals, that are required to completely install a segment of guardrail before beginning work on that segment.

Start guardrail installation at the "upstream" end (the end adjacent traffic encounters first) by either installing a crashworthy terminal, connecting to an existing barrier or shielding the end with a crash cushion or truck mounted attenuator (TMA) meeting NCHRP 350, Test Level 3. Continue installation in the direction of traffic. Exception: if the guardrail run connects to existing barrier, buried in the backslope terminal, existing or new bridge railing, or other existing structure at the "downstream" end, guardrail installation may start at the point of connection.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail. At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test level 3 at all non-crashworthy guardrail ends within the construction clear zone. Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

When possible, proceed with construction of guardrails with the direction of traffic.

Where necessary, adjust the height of existing guardrail to provide a smooth transition to new guardrail. Use 25 linear feet of guardrail or two 12’ 6” pieces of guardrail to transition to match the existing or new guardrail elements and/or end treatments.

After shaping the slopes and staking proposed guardrail terminal section locations, request the Engineer to field verify their locations. Receive approval of the staked locations before installing terminal sections.

Treat field cuts to timber posts and blockouts according to AWPA standard M 4.

Install blockouts according to manufacturer’s recommendations and as shown on the plans. Install side-mounted guardrail reflectors and post-mounted flexible delineators as follows:

- at intervals noted on the plans or Alaska Standard Plans, starting with the first guardrail post beyond terminal sections

- with the retroreflective sheeting facing approaching traffic

- with retroreflective sheeting on both sides, on two-way roadways

- not on the terminal sections, except as shown on the plans

- at or below 500 feet in elevation, except as noted otherwise in the Plans.

Attach terminal markers, in a vertical position, to the P.T. post of Short Radius Guardrail sections and to the post where the flare begins for parallel guardrail terminals. Coordinate terminal marker locations with the Engineer.

At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

#### CR606-123121R

606-3.02 POSTS. Set posts to accommodate the line, grade, and curvature shown on the Plans.

Use either wood or steel posts when allowed by the type of guardrail specified, subject to the following:

- Exclusive of end treatments, use one type of post in each run of guardrail.

Set posts as follows:

- Set posts plumb, in the location and to the depth shown on the Plans or Alaska Standard Plans.

- Choose an installation method that does not damage the post, adjacent pavement, structures, utility conduits, and final slopes. Repair all damage to the satisfaction of the Engineer, or replace the damaged item, as per subsection 105-1.11.

- Set wood or steel posts in dug, drilled, or pre-punched holes. Steel posts may also be set by ramming or driving if:

  - The underlying material is no larger than six inch; and

  - The posts are not damaged during installation.

- Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically. Compact under and around posts to the Engineer’s satisfaction.

- For placement in solid rock or broken rock embankment greater than six inch, set wood or steel posts in pre-dug, pre-drilled, or pre-punched holes.

- In new roads, install posts before final shoulder or median compaction, surfacing, and paving.

606-3.03 BEAM RAIL. Fabricate metal work in the fabricator’s shop. Bend curved guardrail elements with radii less than or equal to 100 feet in the fabricator’s shop or with an approved bending apparatus.

Receive approval before field punching, cutting, or welding. Repair damaged spelter coat areas on galvanized rail elements according to AASHTO M 36 (ASTM A760).

Lap rail elements so that the exposed ends face away from approaching traffic in the adjacent lane.

Use bolts long enough to extend at least 1/4 inch beyond the nuts. Except where required for adjustments, do not extend bolts more than 1 inch beyond the nuts.

Locate bolts at expansion joints at the center of the slotted holes.

Tighten bolts at expansion joints to snug-tight. Make all other bolts fully-tight.

### 606-3.05 TERMINAL SECTIONS.

Parallel Terminals.

Install terminal sections according to the manufacturer’s recommendations for the entire length of the terminal then, if required, transition rail height over 25’ to match guardrail height and splice location.

Install ASTM D4956 Type III, IV, or V retroreflective sheeting on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal according to guidance for Object Markers for Obstructions Adjacent to the Roadway in Chapter 2C of the ATM.

Submit the manufacturers' complete Assembly Installation Checklist signed and dated after completing installation to support acceptance for each installation, see Subsection 606-1.02 for further information.

606-3.09 INSTALL NEW GUARDRAIL. Install guardrail as shown on the Plans.

606-3.10 TERMINAL MARKERS. For each parallel rail terminal, attach a terminal marker to the extreme piece of rail.

Attach flexible markers, in a vertical position, to the terminal end directly to the backside of the rail face, the face away from the traveled way, or the first post of each parallel guardrail terminal. Provide an additional marker where the flare begins for guardrail terminal widening. Provide two markers at the end of each run of guardrail; coordinate the locations with the Engineer.

Attach the flexible markers using hardware and attachment methods recommended by the manufacturer. The connection shall not negatively influence the performance of the guardrail as noted in 606-2.01.

606-3.11 LENGTH OF NEED VERIFICATION. After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends. The Engineer will approve the staked location of the guardrail before installation. When the Engineer determines additional guardrail is required, complete the installation immediately.

#### CR606-123121R

606-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

- Guardrail. Measured along the face of the rail or cable, from the center of the end posts.

Short Radius Guardrail. Per each, installed in place.

When the guardrail is connected to a terminal section, the pay limit for the rail ends where the specified terminal section begins.

- Terminals. Per each, installed in place.

- Transition Rail. Per each accepted connection.

- Permanent Crash Cushion. Each installed and accepted.

### 606-5.01 BASIS OF PAYMENT.

Payment for temporary crash cushions or TMA installed to protect motorists when guardrail installations are not completed within 10 calendar days of beginning installation is subsidiary to other items.

- Guardrail. Side-mounted guardrail reflectors, post-mounted flexible delineators, terminal markers, guardrail beam, posts, blockouts, and associated hardware are subsidiary. Installation of downstream anchors, transitions for rail height and splice locations, long span guardrail sections, and guardrail stiffening sections are subsidiary to guardrail installation.

- Short Radius Guardrail Sections. The contract price includes all materials from the terminal anchor to and including the first wood or steel post of standard guardrail or guardrail end terminal, and including

the terminal anchor assembly, in-line anchor, terminal posts, short radius guardrail posts, rail elements, terminal markers, and associated hardware required for a complete installation.

- Terminal Sections.

  - Parallel Guardrail Terminal. The contract price includes rail elements, posts, blockouts, pipe sleeves, cable assemblies, guardrail extruders, terminal markers, and all associated hardware required for a complete installation.

- Transition Rail. The contract price includes all brackets, beam sections, transition pieces, and all posts and associated hardware required for a complete connection of the guardrail section to a bridge rail or barrier.

- Permanent Crash Cushion. The contract price includes all work and materials required to install each permanent crash cushion, foundations, and connections along with the manufacturer's field support, recommendations, and shop drawings. Removal and salvage of existing crash cushions is subsidiary to Pay Item 606.2007.   Pay Item(s).

All material required for embankment widening for guardrail and terminal sections is paid for under the appropriate pay items shown in the bid schedule.

Guardrail salvage is subsidiary to Pay Item 606.0006.	Removing and Disposing of Guardrail.

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 606.0001. | W-Beam Guardrail | LF |
| 606.0002. | Thrie Beam Guardrail | LF |
| 606.2003. | Box Beam Guardrail | LF |
| 606.0004. | Cable Guardrail | LF |
| 606.0005. | Removing and Reconstructing Guardrail | LF |
| 606.0006. | Removing and Disposing of Guardrail | LF |
| 606.0007. | Double-faced, W-Beam Guardrail | LF |
| 606.0009. | Short Radius Guardrail | Each |
| 606.0013. | Parallel Guardrail Terminal | Each |
| 606.0015. | Adjust Existing Guardrail | LF |
| 606.0016. | Transition Rail | Each |
| 606.2007. | Crash Cushion, Permanent | Each |

#### CR606-123121R

Special Provision

Replace Section 619 with the following:

### SECTION 619 SOIL STABILIZATION

619-1.01 DESCRIPTION. Furnish, install, and maintain materials to stabilize the soil. Control erosion, sediment, and pollution.

### 619-1.02 RELATED SECTIONS, REFERENCE ORGANIZATIONS, AND STANDARD DOCUMENTS.

- Alaska Department of Transportation and Public Facilities (ADOT&PF): Standard Specifications for Highway Construction

Seeding	Section 618

Topsoil	Section 620

Planting Trees and Shrubs	Section 621

Silt Fence	Section 633

Erosion, Sediment, and Pollution Control	Section 641

Soil Stabilization Material	Section 727

- American Association of State Highway and Transportation Officials (AASHTO) Standard Practice for:

  - Compost for Erosion/Sediment Control (Filter Berms and Filter Socks)	R 51

  - Compost for Erosion/Sediment Control (Compost Blankets)	R 52

- United States Composting Council (USCC)

  - Testing Methods for the Examination of Compost and Composting (TMECC)

  - Seal of Testing Assurance Program (STA) documents

- Erosion Control Technology Council (ECTC)

  - Hydraulic Erosion Control Products (HECPs) Specification Chart Table 1, Performance Chart for Standard HECPs

  - Rolled Erosion Control Products (RECPs) Specification Chart Table 1, Rolled Erosion Control - Temporary

Table 2, Rolled Erosion Control - Permanent

- National Transportation Product Evaluation Program (NTPEP)

  - Testing and Evaluation of Products Materials and/or Devices

- Texas DOT/Texas Transportation Institute (TTI) Hydraulics and Erosion Control Laboratory

619-1.03 SUBMITTALS. Submit stabilization and erosion, sediment and pollution control performance testing results with certifications for each material, Section 619-2.01 Materials. Submit a sample of each material to the Engineer 7 days before the scheduled installation.

- Test compost, all applications, no more than 90 days before installation.

- At a minimum, certificate will include the name of the manufacturer, product name, style number or similar, chemical composition of the material, the fibers, netting, yarn and similar and the weed free status of the material.

- Organic materials shall be accompanied with all applicable health certificates and permits.

- Furnish a Material Safety Data Sheet (MSDS) that demonstrates the product is not harmful to plants, animals, and aquatic life.

619-2.01 MATERIALS. Select stabilization materials, individually or a combination of, matched to the project applications/conditions (sheet flow, concentrated flow, slope, length of slope, access, etc.) providing performance and functional longevity meeting the most restrictive requirements of the Construction General Permit (CGP), the approved Storm Water Pollution Prevention Plan (SWPPP) and Section 641 Erosion, Sediment and Pollution Control.

- Mulch	Subsection 727-2.01

  - Dry Erosion Control, Stabilization Products

  - Hydraulic Erosion Control Products (HECPs)

- Matting	Subsection 727-2.02

  - Rolled Erosion Control Products (RECPs)

- Sediment Retention Fiber Rolls (SRFRs)	Subsection 727-2.03

  - Filter Socks

  - Compost Socks

  - Coir Logs

- Compost	Subsection 727-2.04

- Tackifier	Subsection 727-2.05

- Soil Binders (Polyacrylamide (PAM))	Subsection 727-2.06

- Geotextile-Encased Check Dams and Sediment Barriers	Subsection 727-2.07

- Sandbag	Subsection 727-2.08

- Manufactured Inlet Protection System	Subsection 727-2.09

- Clear Plastic Covering	Subsection 727-2.10

- Staples	Subsection 727-2.11

- Other stabilization materials submitted to and approved by the Engineer.

Include on the packaging the manufacturer's name, the content, the air dry-weight and the guaranteed chemical analysis of the contents. Ship and deliver to the site in the original, unopened containers.

### CONSTRUCTION REQUIREMENTS

619-3.01 GENERAL. Stabilization may include individual or a combination of materials, including but not limited to temporary seeding, mulch, tackifier, staples, matting, stabilizing emulsions, soil binders, dustless sweeping, dust palliatives, and others.

- Material Storage and Protection. Store materials elevated off the ground and covered protecting them from construction and or damage from the environment including but not limited to:

  - Precipitation

  - Extended ultraviolet radiant including sunlight

  - Chemicals that are strong acids or other

  - Flames and welding sparks

  - Excess temperatures

  - Other environmental conditions that may damage the materials

- Fabrication.

a. Sandbags. Sand bags shall measure 15 inches by 30 inches. Place approximately 1.0 cubic foot of select Material, Type B, in each sandbag sack. Close the open end of the sandbag as recommended by the fabric manufacturer.

619-3.02 SURFACE PREPARATION. Clear all areas to be stabilized of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the stabilization operation, growth of cover (where vegetative cover is part of the stabilization operation) or subsequent maintenance of the vegetative-covered area(s).

Smooth the surface of the area(s) to be stabilized; make the areas reasonably free of ruts, holes, and humps; trackwalk if required by the manufacturer; apply the stabilization material to each area.

If specified, apply topsoil to the area to be stabilized before application of the stabilizing material. Section 618 and 620.

619-3.03 APPLICATION. Apply stabilization material, including rate of application, according to the specifications. If not specified, apply according to the manufacturer's requirements. Where manufacturer requirements conflict with the specification, except where the Engineer directs otherwise, apply the material according to the requirements of the manufacturer.

If seeding is specified, except where seed is included in the stabilization material, complete the application of stabilization materials within 24 hours after seed is placed.

Do not use vehicles or equipment which cause rutting or displacement of the subgrade or topsoil.

- Temporary Seeding. Annual Ryegrass per Subsection 724-2.02, Table 724-1. Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils. Prepare surface and place seed as noted under Subsection 619-

3.02 Surface Preparation and Section 618 Seeding. Confirm application of temporary seeding with the Engineer.

- Tacking Agents - Tackifiers. Apply tacking agents according to the manufacturer's installation instructions matched to the application providing functional longevity, erosion control effectiveness, and vegetative establishment.

- Soil Binders. Apply soil binders according to the manufacturer's installation instructions.

  - Using Polyacrylamide (PAM) and PAM with Short-Term Mulch: Apply PAM on bare soils.

Apply PAM and PAM with short-term mulch only where sediment control is in place and complete. Do not apply PAM and PAM with short-term mulch on saturated ground during rainfall.

  - Using Moderate-Term Mulch:

Apply moderate-term mulch according to manufacturer's installation instructions. If the curing period to achieve maximum performance is greater than the time period before precipitation is predicted, or the soil is saturated, do not apply the moderate-term mulch except as approved by the Engineer.

  - Using Long-Term Mulch:

Apply long-term mulch according to the manufactures installation instructions.

- Erosion Control Blankets (ECBs). Select blankets, as specified by the manufacturer, to match the slope; and installed according to the manufacturer's instructions rolled out on well prepared soils to assure intimate contact and anchored with staples, stakes and or anchor trenches. Temporary erosion control blankets with 60 percent or greater open area may be installed prior to seeding. Place blankets with less than 60 percent open area immediately after the seeding operation.

Staple matting/ECBs as recommended by the manufacturer for the application.

- Compost Blankets. Construct compost blankets according to latest AASHTO R 52 and as specified. Use coarse compost and place over bare soil a blanket of 2 inch minimum thickness, except as otherwise specified. Apply material either by hand spreading and or pneumatically. Compost will have no free water visible or produce dust when handled. Place compost before seeding or mix seed with compost.

- Check Dams. Place check dams as soon as possible and practicable or when and where if directed by the Engineer. Place the check dams perpendicular to channels and construct of a height sufficient to maximize detention while keeping the water in the channel. Place and install check dams according to the Plans and anchor to maintain in effective position.

  - Sandbag. Place the initial row in tight contact with the ditchline for the length of the dam. Place each following row centered across the joint between the bags of the lift/row below.

- Stabilized Construction Entrance.

Temporary stabilized construction entrance shall be constructed according to the Plans, prior to beginning any clearing, grubbing, earthwork, or excavation.

When the stabilized entrance no longer prevents track out of sediment or debris, the Contractor shall either rehabilitate the existing entrance to original condition, or construct a new entrance.

When the Plans require a tire wash in conjunction with the stabilized entrance, the Contractor shall include details for the tire wash and the method for containing and treating the sediment-laden runoff as part of the SWPPP. All vehicles leaving the site shall stop and wash sediment from their tires.

- Sediment Control Barriers. Sediment control barriers shall be installed according to the Plans or manufacturer's recommendations in the areas of clearing, grubbing, earthwork, or drainage prior to starting those activities.

  - Sandbag. Place the initial row in tight contact with the surface perpendicular to the slope. Place each following row centered across the joint between the bags of the lift/row below.

  - Sediment Retention Fiber Rolls.

  - Silt Fence.

  - Compost Berm.	Construct compost berms according to latest AASHTO R 51.	Use coarse compost.

- Turf Reinforcement Mats. According to manufacturer's installation instructions.

619-3.04 MAINTENANCE. Maintain stabilized areas in a satisfactory condition for the term of the Contract. Inspect as required by the CGP, approved SWPPP, and Section 641 Erosion, Sediment and Pollution Control and correct any deficiencies immediately. Remove and dispose of temporary measures, including trapped sediment and contaminants, off project at approved locations. Materials manufactured as degradable may be left in place when approved by the Engineer.

Maintenance includes but is not limited to:

- Protecting stabilized areas against traffic by approved warning signs or barricades.

- Repairing surfaces gullied or otherwise damaged following application of stabilization material(s).

Where seeding is included as a part of the soil stabilization:

- Reseeding, as required by Section 618 Seeding. Reapply the stabilization materials correcting the problems of the initial application.

- Watering, where vegetative growth is part of the soil stabilization, according to Section 618 Seeding.

The Engineer will perform inspection of the stabilization as required in the CGP, Section 641, and the SWPPP. Make repairs as required by same and as directed.

619-4.01 METHOD OF MEASUREMENT. Section 109, measured on the slope of the ground surface.

619-5.01 BASIS OF PAYMENT.	Water, maintenance, repair, removal, and disposal of temporary stabilization materials are subsidiary.

Seeding is paid under Section 618 Pay Items, topsoil under Section 620 Pay Items, silt fence under Section 633 Pay Items and temporary erosion, sediment, and pollution control under 641 Pay Items.

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 619.0001. | Mulching | SY |
| 619.0002. | Matting | SY |
| 619.2001. | Compost | SY |
| 619.2002. | Turf Reinforcement Mat | SY |
| 619.2003. | Sediment Retention Fiber Rolls | LF |
| 619.2004. | Check Dam and Sediment Barrier (-Geotextile) | LF |
| 619.2005. | Check Dam | LF |
| 619.2006. | Sediment Barrier | LF |
| 619.2007. | Compost Berm | LF |
| 619.2008. | Sandbags | Each |
| 619.2009. | Manufactured Inlet Protection System | Each |
| 619.2010. | Sandbag Inlet Protection System | Each |
| 619.2016. | Mulch | SY |

#### CR619-18.0501R1

Replace Section 641 with the following:

### SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL 641-1.01 DESCRIPTION.

Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this Section and applicable local, state, and federal requirements, including the Alaska Pollution Discharge Elimination System (APDES) Construction General Permit (CGP). The state APDES program is administered by the Department of Environmental Conservation (DEC). Section 301(a) of the Clean Water Act (CWA) and 18 AAC 83.015 provide that the discharge of pollutants to water of the U.S. is unlawful except as allowed by the CGP.

### 641-1.02 DEFINITIONS.

These definitions apply only to Section 641.

ACTIVE TREATMENT SYSTEM (ATS) OPERATOR. CGP Appendix C.

ALASKA CERTIFIED EROSION AND SEDIMENT CONTROL LEAD (AK-CESCL). A person who has

completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years. (See Qualified Person)

ALASKA DEPARTMENT OF ENVIRONMENTAL CONSERVATION (DEC).	The state agency

authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System. ALASKA GENERAL PERMIT FOR EXCAVATION, DEWATERING (Excavation Dewatering Permit). Permit authorizing excavation dewatering discharges from Construction Activities.

ALASKA MULTI-SECTOR GENERAL PERMIT (MSGP). Permit authorizing storm water discharges associated with Industrial Activity.

ALASKA POLLUTANT DISCHARGE ELIMINATION SYSTEM (APDES). A system administered by DEC

that issues and tracks permits for storm water discharges.

BEST MANAGEMENT PRACTICES (BMPS). CGP Appendix C.

CLEAN WATER ACT (CWA). Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

CONSTRUCTION ACTIVITY. Ground disturbing activity by the Contractor, Subcontractor or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. CGP Appendix C.

CONSTRUCTION GENERAL PERMIT (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by Alaska DEC. It authorizes storm water discharges providing permit conditions and water quality standards are met.

U.S. ARMY CORPS OF ENGINEERS PERMIT (COE Permit). U.S. Army Corps of Engineers Permit for construction in waters of the U.S. may be issued under Section 10 of the Rivers and Harbors Act of 1899, or Section 404 of the Clean Water Act.

ELECTRONIC NOTICE OF INTENT (ENOI). CGP Appendix C.

ELECTRONIC NOTICE OF TERMINATION (ENOT). CGP Appendix C.

ENVIRONMENTAL PROTECTION AGENCY (EPA). The federal agency charged to protect human health and the environment.

ERODIBLE STOCKPILE. Any material storage area or stockpile consisting of mineral aggregate, organic material, or a combination thereof, with greater than 5 percent passing the #200 sieve, and any material storage where wind or water transports sediments or other pollutants from the stockpile. Erodible Stockpile also includes any material storage area or stockpile where the Engineer determines there is potential for wind or water transport of sediments or other pollutants away from the stockpile.

EROSION AND SEDIMENT CONTROL PLAN (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

FINAL STABILIZATION. CGP Appendix C, "Stabilization".

HAZARDOUS MATERIAL CONTROL PLAN (HMCP). The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment). The HMCP is included as an appendix to the SWPPP.

MUNICIPAL SEPARATE STORM SEWER SYSTEM (MS4) PERMIT.  A DEC storm water discharge

permit issued to certain local governments and other public bodies, for operation of storm water conveyances and drainage systems. CGP Appendix C.

OPERATOR(S). The party(s) responsible to obtain CGP permit coverage. CGP Appendix C.

- Contractor – the Contractor is an Operator inside and outside the Project Zone.

- Department – the Department is an Operator inside the Project Zone.

POLLUTANT. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sediment, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

PROJECT ZONE. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Contract.

Material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

QUALIFIED PERSON. CGP Appendix C and Section 641-1.04.

### SPILL PREVENTION, CONTROL, AND COUNTERMEASURE PLAN (SPCC PLAN). The Contractor’s

detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

SPILL RESPONSE FIELD REPRESENTATIVE. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

STORM EVENT. CGP Appendix C.

STORM WATER POLLUTION PREVENTION PLAN (SWPPP). The Contractor's plan for compliance with the CGP for construction activities inside the Project zone, CGP Appendix C and Section 641.

STORM WATER POLLUTION PREVENTION PLAN TWO (SWPPP2). The Contractor's plan for

compliance with the CGP and MSGP for construction activities outside the Project Zone.

SUPERINTENDENT. The Contractor's duly authorized representative with authority and responsibility for the overall operation of the Project and Contractor furnished sites and facilities.

SWPPP AMENDMENT. A modification to the SWPPP. CGP Part 5.0.

SWPPP MANAGER. The Contractor's Qualified Person with authority and responsibility. CGP Appendix C. SWPPP PREPARER. The Contractor’s Qualified Person with authority and responsibility. CGP Appendix C. TEMPORARY STABILIZATION. CGP Appendix C, "Stabilization".

### 641-1.02.01 REFERENCE.

A list of websites and documents referenced herein, including SWPPP preparation documents and construction forms, are available at the DOT&PF Statewide Design and Engineering Services Storm Water web page and Construction Forms webpage.

DEC Permit information is available at the DEC Division of Water webpage.

### 641-1.03 PLAN AND PERMIT SUBMITTALS.

For plans listed in Subsection 108-1.03.5 (SWPPP, HMCP, and SPCC), use the Contractor submission and Department review deadlines identified in this subsection.

Partial and incomplete submittals will not be accepted for review. Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1. Storm Water Pollution Prevention Plan. Submit one electronic copy (single PDF file) and one hard copy of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14-day review period will restart when the contractor submits an electronic copy and one hard copy of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved and certified by the Department using Form 25D-109, the Contractor must certify the approved SWPPP using Form 25D-111. See Subsection 641-1.03.4 for further SWPPP submittal requirements.

Submit the final SWPPP. Transmit an electronic copy (single pdf file) of the final SWPPP to the Engineer when the Contractor's eNOT is filed, or within 30 days of the Department's eNOT being filed, whichever is sooner. Include all SWPPP documents.

Hazardous Material Control Plan. The HMCP Template is available at the DOT&PF Construction Forms webpage. The HMCP submittal, review timeline, and signature requirements are the same as the SWPPP.

- Spill Prevention, Control, and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and one hard copy of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

- CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. Do not use the SWPPP for Construction Activities outside the Project Zone where the Department is not an operator. For Construction Activities outside the Project Zone, the Contractor must use a SWPPP2. Department approval is not required for a SWPPP2.

After the Department certifies the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to DEC for coverage under the CGP. Submit a copy of the signed eNOI and DEC’s written acknowledgement (by letter or other document), to the Engineer as soon as practicable and no later than three days after filing eNOI or receiving a written response.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to DEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and DEC’s written acknowledgment (by letter or other document), for inclusion in the SWPPP.

Before Construction Activities occur, transmit to the Engineer an electronic copy and one hard copy of the approved and certified SWPPP, with signed Delegations of Signature Authorities on Forms 25D- 107 and 25D-108, SWPPP Certifications on Forms 25D-111 and 25D-109, both permittee’s signed eNOIs and DEC’s written acknowledgement.

- DEC SWPPP Review. When CGP Part 2.1.3, or 2.1.4 requires DEC SWPPP review:

  - Transmit a copy of the Department-approved SWPPP to DEC using delivery receipt confirmation;

  - Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation; and

  - Retain a copy of delivery receipt confirmation in the SWPPP.

- Local Government SWPPP Review. When local government or the CGP Part 2.1.4, requires local government review:

  - Transmit a copy of the Department-approved SWPPP and other information as required to local government, with the required fee. Use delivery receipt confirmation;

  - Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation;

  - Transmit a copy of any comments by the local government to the Engineer within seven days of receipt;

  - Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven days of receipt of the comments;

  - Include a copy of local government SWPPP review letter in the SWPPP; and

  - File a notification with local government that the project is ending.

- Modifying Contractor’s eNOI. When required by the CGP Part 2.7, modify your eNOI to update or correct information within 30 calendar days of the change. Reasons for modification are in the CGP Part 2.7.1. The Contractor must submit an eNOT instead of an eNOI modification when the operator has changed. The new operator must file an eNOI to obtain permit coverage.

### 641-1.04 PERSONNEL QUALIFICATIONS.

Provide documentation in the SWPPP that the individuals serving in these positions meet the personnel qualifications. The Department accepts the following certificates as equivalent to AK-CESCL: Certified Professional in Erosion and Sediment Control (CPESC), or Certified Inspector in Sediment, and Erosion Control Certified (CISEC). These equivalent certificates are included in the CGP Appendix C and repeated below.

### TABLE 641-1.04 PERSONNEL QUALIFICATIONS

| Personnel Title | Required Qualifications |
| --- | --- |
| SWPPP Preparer | - Current certification as a Certified Professional in Erosion and Sediment Control (CPESC); or - Current certification as AK-CESCL, and at least two years' experience in erosion and sediment control as a SWPPP Manager or SWPPP writer, or equivalent; or - Professional Engineer registered in the State of Alaska with current certification as AK-CESCL. |
| Superintendent | Current AK-CESCL, or substitute training from CGP Appendix C, Qualified Person Table 4 |
| SWPPP Manager | Current AK-CESCL or substitute training from CGP Appendix C, Qualified Person Table 4. |
| Active Treatment System Operator | Current AK-CESCL or substitute training from CGP Appendix C, Qualified Person Table 4. ATS operator should possess a recognized certification, or professional standing, or who by extensive knowledge, training, and experience has successfully demonstrated the ability to meet the ATS requirement. |

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

- eNOI and eNOT. The eNOI, eNOT, and eNOI Modifications must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12. Signature and certification authority for the eNOI and eNOT cannot be delegated.

- Delegation of Signature Authority for Other SWPPP Documents and Reports. Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Superintendent position is responsible for signing and certifying the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI, eNOI Modifications, and eNOT.

The Engineer will provide the Department’s delegation on Form 25D-107, which the Contractor must include in the SWPPP.

- Subcontractor Certification. Subcontractors must certify on Form 25D-105, that they have read and will abide by the CGP and the conditions of the project SWPPP.

- Signatures and Initials. Certify or initial the CGP documents and SWPPP forms, wherever a signature or initial is required.

### 641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

107-1.02 includes the requirements to obtain permits, and to provide permit documents to the Engineer.

- The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

- The Contractor is responsible for permitting and permit compliance for all construction support activity in the Project Zone and outside the Project Zone. The Contractor has sole responsibility for compliance with DEC, COE, and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. The Contractor is responsible for protection, care, and upkeep of all work, and all associated off-site zones.

- The Contractor is responsible for obtaining an Excavation Dewatering Permit (AKG002000) if construction activities are within 1,500 feet of a DEC-identified contaminated site or groundwater plume.

- An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.4) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage.

- The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

  - For areas outside the Project Zone;

  - For Construction Activity and Support Activities outside the Project Zone; and

  - For commercial plants, commercial material sources, and commercial disposal sites.

### 641-1.07 UTILITY.

Relocation Coverage. A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06. The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project. A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work. Remaining utility relocation work is included in and performed under the Project SWPPP.

### 641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

- SWPPP Preparer and Pre-Construction Site Visit.

Use a SWPPP Preparer to develop the SWPPP according to the CGP, DEC and Department SWPPP Template. Subsection 641-1.02.01 provides directions to templates.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least seven days advance notice of the site visit, so that the Department may participate.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, include the names of attendees and the date.

- Developing the SWPPP.

  - Meet all CGP requirements.

  - Use the Department’s ESCP, Environmental commitments, and other Contract documents as a starting point for developing the SWPPP.

  - Develop the SWPPP with sections and appendices according to the DEC CGP SWPPP Template and DOT&PF SWPPP Template. Include the information required by the Contract and described in the CGP Part 5.0. Use the forms available at the DOT&PF Construction Forms website.

  - Compile the SWPPP in three ring binders with tabbed and labeled dividers for each appendix. Submit the SWPPP according to Subsection 641-1.03.

- SWPPP Considerations and Contents.

  - The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone.

Construction activity outside the Project Zone must have permit coverage. Document permit compliance according to SWPPP2 requirements.

  - The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. Describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP. Include the utility companies and other operators performing Construction Activity.

Identify areas:

    - Over which each operator has operational control; and

    - Where the Department and Contractor are co-operators.

  - For work outside the Project Zone the SWPPP must identify the entity that has storm water permit coverage, the operator, and areas that are:

    - Dedicated to the Project and where the Department is not an operator; and

    - Not dedicated to the project, but used for the project.

  - If the project discharges to a Tier III, Outstanding Natural Resource Water, comply with the CGP Part 2.1.6. Submittal deadlines apply prior to filing an eNOI and beginning construction activities. As of the issuance of the CGP 2021, no Tier III, Outstanding Natural Resource Water is designated in the State of Alaska.

  - There are special requirements in the CGP Part 3.2, for storm water discharges into an impaired water body. Monitoring of storm water discharges may be required. The Contractor is responsible for monitoring and reporting inside and outside the project zone.

  - Describe the sequence and timing of activities that disturb soils and BMP implementation and removal. Phase earth-disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities. Include drawings showing each phase of the project with the BMPs implemented in the Phase.

  - Delineate the site according to the CGP Part 4.2.1.

  - Minimize the amount of soil exposed and preserve natural topsoil on site, unless infeasible according to the CGP Part 4.2.2.

  - Describe methods and time limits, to initiate temporary or final soil stabilization. Comply with stabilization requirements in the CGP Part 4.5.

  - If construction will cease during winter months, describe all requirements for winter shutdown according to the CGP Part 4.12.

  - Plans for ATS must meet with the requirements in the CGP Part 2.1.5 and 4.6.

  - Design all temporary BMPs to accommodate a two year 24-hour storm event. Describe and document all installed control measures in the SWPPP according to the CGP Part 5.3.6. Include a citation from a published BMP Manual, publication, or manufacturers specification used as a source, or include a statement "No BMP Manual was used for this design". If using out of state BMPs, follow the instructions in the DOT&PF SWPPP Guide.

  - Provide a legible site map or set of maps in the SWPPP, showing the entire site and identifying boundaries of the property where construction and earth-disturbing activities will occur. Include all elements described in the CGP Part 5.3.5 and the DEC CGP SWPPP Template Section 5.0.

  - Identify the inspection frequency in the SWPPP according to the CGP Part 6.1; except, inspect once every seven calendar days regardless of the precipitation amount.

  - Linear Project Inspections, described in CGP Part 6.5, are not applicable to this Contract.

  - The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, COE permit, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities that were not included in the Department’s permitting and consultation.

  - The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the CGP and this specification. See Subsection 641-3.03 for more information.

- Recording Personnel and Contact Information in the SWPPP.

Identify the SWPPP Manager as the Storm Water Lead and Storm Water Inspector positions in the SWPPP. Document the SWPPP Manager’s responsibilities in Section 2.0 Storm Water Contacts, of the SWPPP Template and:

  - Identify that the SWPPP Manager does not have authority to sign inspection reports (unless the SWPPP Manager is also the designated project Superintendent).

  - Identify that the SWPPP Manager cannot prepare the SWPPP unless the SWPPP Manager meets the Contract requirements for the SWPPP Preparer.

Include in the SWPPP proof of AK-CESCL, or equivalent certifications for the Superintendent and SWPPP Manager, and for any acting Superintendent and acting SWPPP Managers. If the Superintendent or SWPPP Manager is replaced, permanently or temporarily, by an acting Superintendent or acting SWPPP Manager; record in the SWPPP, on Form 25D-127, the names of the replacement personnel, and date of replacement. For temporary personnel, record their beginning and ending dates.

Provide 24-hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24-hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, proof of AK-CESCL or equivalent certifications of ATS operators. Record names of ATS operators and their beginning and ending dates, on Form 25D-127.

The Department will provide proof of AK-CESCL, or equivalent certifications for the Department's Project Engineer, Storm Water Inspectors, and Monitoring Person, and names and dates they are acting in that position. Include Department’s staff certifications in SWPPP Appendix E. Include the Department’s staff names, dates acting, and assignments in Section 2.0 of the SWPPP and on Form 25D-127.

### 641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.

Prepare the HMCP using the Department template for the prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

### 641-2.03 SPILL PREVENTION, CONTROL, AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.

Prepare and implement an SPCC Plan, required by 40 CFR 112; when both of the following conditions are present on the project:

- Oil or petroleum products from a spill may reach navigable waters (defined in 40 CFR 112), and

- Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons).

Reference the SPCC Plan in the HMCP and SWPPP.

### 641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent shall certify the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI and eNOT. The Superintendent may not delegate the task or responsibility of certifying these documents.

The Superintendent may assign certain duties to the SWPPP Manager.

- Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

- Ensuring the control of erosion, sedimentation, or discharge of pollutants;

- Directing and overseeing installation, maintenance, and removal of BMPs;

- Performing Inspections; and

- Updating the SWPPP including adding amendments and forms.

When Bid Item 641.0007.    is part of the Contract, the SWPPP Manager must be a different person than the Superintendent, be available at all times to administer SWPPP requirements, and be physically present within the Project Zone or the project office, when construction activities are occurring.

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, and environmental commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

### 641-2.05 MATERIALS.

Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

Use the seed mixture specified in the Contract or as directed by the Engineer. Use soil stabilization material as specified in Section 727.

Use silt fences as specified in Section 729.

Use straw and straw products certified weed free of prohibited and restricted noxious weed seed and quarantined pests, according to Alaska Administrative Code, Title 11, Chapter 34 (11 AAC 34). When straw or straw products certified according to 11 AAC 34 are not available, use non-certified products manufactured within Alaska before certified products manufactured in another state, country, or territory. Non-certified straw or straw products manufactured in another state, country, or territory shall not be used. Grass, legumes, or any other herbaceous plants produced as hay, shall not be substituted for straw, or straw products.

### 641-3.01 CONSTRUCTION REQUIREMENTS.

Comply with the SWPPP and the requirements of the CGP Part 5.0.

- Before Construction.

The following actions must be completed before Construction Activity begins:

  - The SWPPP Preparer must visit the Project. Document the visit on SWPPP Form 25D-106. The SWPPP must be developed, or amended with the findings from the visit.

  - The SWPPP must be approved by the Engineer on Form 25D-109.

  - The Contractor must be authorized to begin work by the Engineer.

  - The Project must have an eNOI for the Department and for the Contractor.

  - The Department approved SWPPP must be submitted to DEC and Local Governments per CGP Part 2.1.2, Part 2.1.4, and Part 2.4.1.

  - The Contractor has transmitted to the Engineer an electronic copy, and at least one hardcopy of the approved SWPPP.

  - The Delegation of Authority, Forms 25D-108 and 25D-107, for both the Contractor and Engineer are signed.

  - Main entrance signage must meet the requirements of CGP Part 5.10.2.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can safely read them without obstructing construction activities or the traveling public (for example, at an existing pullout). Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes.

  - Track precipitation according to CGP Part 7.3.9. Submit the method to track precipitation to the Engineer for approval.

- During Construction.

  - Delineate The Site. Comply with the CGP Part 4.2.1.

  - BMPs. Install BMPs according to the SWPPP prior to the initiation of ground disturbance.

  - Document subcontractors. Provide a copy of the SWPPP and the CGP to all subcontractors and utility companies before they begin soil-disturbing activities. Verify they understand and comply with the SWPPP and CGP.

    - Document all subcontractors and utility companies that may work on the site, according to the CGP Part 5.3.1, and SWPPP Section 1.2.

    - Require subcontractors and utility companies to sign the SWPPP Subcontractor Certification, Form 25D-105. Include Form 25D-105 in the SWPPP Appendix E.

    - Inform subcontractors and utility companies, in a timely manner, of SWPPP amendments that affect them. Coordinate with subcontractors and utility companies to protect BMPs, including temporary and final stabilization from damage.

    - Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

  - Provide Training. Provide ongoing training to all employees, subcontractors, and utility companies according to the CGP Part 4.14.

    - Provide training no less than once a month during construction activity;

    - Document training in the SWPPP Training Log on Form 25D-125. Include the training record in the SWPPP Appendix l.

  - Protection and Restoration. Comply with Subsection 107-1.11.

  - Good Housekeeping Measures. Comply with the SWPPP and CGP Part 4.8.

  - Control Measures. Comply with the SWPPP and CGP Part 5.3.6.

    - Maintain BMPs.

    - Comply with requirements of the HMCP and SPCC Plan, and all local, state, and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

    - Keep the SWPPP and HMCP current, Subsection 641-2.01.3, SWPPP Considerations and Contents.

- Winter Construction.

If winter construction activity occurs, the project must have BMPs in place, Part 4.12.2. Inspections can be reduced to once per month if the project meets the CGP Part 6.2.4.

- Storm Water Discharge Pollutant Reporting Requirements.

If an incident of non-compliance occurs, that may endanger health or the environment, a report must be made, CGP Appendix A, Part 3.4.

A permit non-compliance is any type of pollutant, such as turbidity or petroleum that enters storm water runoff and flows into a receiving water body, MS4, or wetland that is connected to waters of the U.S.

  - Report the incident to the Engineer immediately;

  - Report to DEC orally within 24 hours after the permittee becomes aware of the incident; and

  - Report to DEC in writing within five days after the permittee becomes aware of the circumstances. To report in writing, complete the written noncompliance report on Form 25D-143, and file the written report with DEC. Coordinate the report with the Engineer. Include in the report:

    - A description of the noncompliance and its causes;

    - The exact dates and times of noncompliance;

    - If not yet corrected the anticipated time the project will be brought back into compliance; and

    - The corrective action taken or planned to reduce, eliminate and prevent reoccurrence.

  - Report an incident of noncompliance with COE Permits to the Engineer immediately. The Engineer will notify the COE.

- Hazardous Materials Reporting Requirements.

Report any release of a hazardous substance immediately to the Engineer, as soon as the person has knowledge of the discharge.

Report spills of petroleum products or other hazardous materials to the Engineer and other agencies as required by law, and according to the CGP Part 9.3.

  - To water.

Any amount of hazardous material released must be reported immediately to the Engineer, DEC, and the Coast Guard.

  - To land.

Any release of a petroleum product, must be reported as soon as the person has knowledge of the discharge, CGP Part 9.3.2.

    - Release in excess of 55 gallons,

    - Release in excess of 10 gallons but less than 55 gallons, must be reported to the DEC within 48 hours after the person has knowledge of the discharge, and

    - Release in excess of 1 gallon to 10 gallons, must be recorded, logged, and provided to the DEC on a monthly basis.

  - Use the HMCP and SPCC Plan for contact information to report spills to regulatory agencies.

  - Implement measures to prevent the reoccurrence of and to respond to the release of hazardous materials.

  - Prior to disposal of contaminated material, submit a Contaminated Media Transport and Treatment Disposal Approval Form to the DEC Division of Spill Prevention and Response. Dispose as approved by the DEC.

- Maintenance of BMPs and Corrective Action.

Implement maintenance and corrective action as required by the CGP Part 4.13 and Part 8.0, SWPPP, and manufacturer’s specifications, whichever is more restrictive.

  - Implement corrective actions. Comply with the CGP Part 8.0 and the SWPPP.

  - Corrective Action deadlines and documentation.

    - Complete Corrective actions according to the CGP Part 8.2.

    - Document corrective actions in the Corrective Action Log, Form 25D-112, according to the SWPPP, CGP Part 5.9.2, and Part 8.3.

If a different BMP is installed to correct the condition leading to the corrective action, a SWPPP Amendment must be completed.

    - Document the conditions, in the Corrective Action Log, for corrective actions not completed according to the CGP 8.2. Notify the Engineer, and implement the corrective action as soon as possible.

The Engineer may assign a new complete-by date using a Delayed Action Item Report, Form 25D-113 (DAIR Form), if the Contractor is unable to complete the corrective action within the required timeframe. The DAIR Form can only be authorized and completed by the Engineer.

- Stabilization.

  - All Soil stabilization requirements must be met in accordance with CGP Part 4.5 and the SWPPP.

  - When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community, the hydro-seeder must be located at the project.

  - Apply temporary seed and stabilization measures after preparing the surface to reduce erosion potential and to facilitate germination and growth of vegetative cover according to Section 618 and 619.

  - Apply permanent seed and other stabilization measures after land-disturbing activity has permanently ceased. Comply with the CGP, SWPPP, and the Contract Sections 618, 619, 724, and 727.

  - Incorporate final or temporary stabilization immediately after installing culverts or other drainage structures to satisfy the CGP Part 4.5, SWPPP and Engineer. Stabilize under any bridge and in areas upstream and downstream of culverts, drainages and areas disturbed by related construction activities after installation, or before deactivating stream bypass or diversion.

  - Stabilization before Fall Freeze-up, and Spring Thaw.

Stabilize Construction Activities within the Project Zone with BMPs prior to the anticipated date of fall freeze-up, according to the SWPPP and CGP Part 4.12.

Exceptions to stabilization prior to anticipated date of fall freeze-up include:

    - Where temporary stabilization activities are precluded by snow cover or frozen ground conditions prior to the anticipated date of fall freeze-up, stabilization measures must be initiated as soon as practicable following the actual spring thaw.

    - When winter construction activity is authorized by the Engineer and conducted according to the Contract.

- Ending CGP Coverage.

  - The Engineer will determine the date that the following conditions for ending CGP coverage have been met within the Project Zone:

    - Land disturbing activities have ceased;

    - Final Stabilization has been achieved on all portions of the Project Zone, including Department furnished material sources, disposal sites, staging areas, equipment areas, etc., according to the CGP Part 4.5.2; and

    - Temporary BMPs have been removed.

  - After the Engineer has determined the conditions for submitting an eNOT have been met according to the CGP Part 10.2, the Department will:

    - Send written notice to the Contractor with the date that the conditions were met;

    - Submit an eNOT to DEC within 30 days, and

    - Provide a copy of the eNOT and DEC’s acknowledgement letter to the Contractor.

  - If the Contractor’s CGP eNOI acreage includes Support Activities and any other areas where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.

  - The Contractor must submit a copy of each signed eNOT and DEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response. Insert the eNOT and DEC acknowledgement letter in the SWPPP Appendix Q.

  - The Contractor is responsible for coordinating local government inspections of work and ending permit coverage with local governments. See Subsection 641-1.03.6 for more information.

- Ending Inspections, BMP maintenance, and SWPPP Updates in the Project Zone.

The Contractor is responsible for continuing inspections, BMP maintenance, and SWPPP updates until permit coverage is ended.

- Transmit final SWPPP.

Transmit one electronic copy of the final SWPPP to the Engineer according to Subsection 641-1.03.1.

### 641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.

The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP, and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown. Update on-site postings if records are relocated during winter shutdown. Provide the Department with copies of all Records.

Retain Records including a copy of the SWPPP, for at least three years after the date of eNOT according to the CGP Part 9.4.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them. See CGP Parts 5.10, 6.6 and 9.5.

### 641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.

Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP using Department forms from the DOT&PF Construction Forms website.

- Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP Part 6.0, except inspect once every seven calendar days regardless of the precipitation amount, Subsection 641-2.01.3.n.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s Storm Water Inspector jointly, unless approved by the Engineer, when:

  - One of the inspectors is not on site, access is only by air, and weather delayed or canceled flights;

  - One of the inspectors is sick;

  - The project is on a reduced frequency inspection schedule with no staff on site, the only access to the site is by air, and it is economical to send only one inspector; or

  - When the Engineer determines a safety concern that makes joint inspection impracticable.

When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within three days of the Inspection date and document the date of the report transmittal in Appendix K.

- Inspection Reports.

Use only the Department SWPPP Construction Site Inspection Report, Form 25D-100, to record Inspections. Changes or revisions to Form 25D-100 are not permitted, except for adding or deleting data fields that list: Location of Discharge Points and Site Specific BMPs. Complete all fields in the Inspection Report; do not leave any field blank.

The Superintendent or SWPPP Manager must review and correct all errors within three days of the date of inspection.

Inspection Reports must be signed by the person described in the CGP Appendix A, Part 1.12 or by a duly authorized representative of that person. Only the Superintendent can certify the Inspection Form.

Insert a Complete-by-Date for each corrective action listed that complies with the CGP Part 8.2.

Provide a copy of the completed, unsigned Inspection Report to the Engineer by the end of the next business day following the inspection.

The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. The signed and certified Inspection Report must be provided to the Engineer on the same day the Superintendent signed the form.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days if compliant with the CGP and SWPPP.

If the Inspection Report is not compliant with the CGP or SWPPP, the Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

When an Inspection Report, certified by both the Superintendent and Engineer, requires corrections:

  - Document the corrections in an addendum memo addressing only the omitted or erroneous portions.

  - Superintendent and Engineer sign and certify the updated Inspection Report and the addendum memo.

  - File the corrected Inspection Report and addendum memo in Appendix K and update the amendment log.

The issuance of an addendum memo does not relieve the Contractor of liquidated damages that may have been incurred as a result of the error on the original certified inspection report.

- Items and Areas to Inspect.

Conduct inspections of all areas required by the CGP Part 6.4 and SWPPP.

- Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP. Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

The frequency of inspections may be reduced according to the CGP Part 6.2.1 if the site is stabilized and the reduced frequency is approved by the Engineer. At actively staffed sites, inspect within two business days of the end of a storm event that results in a discharge from the site.

- Winter Shutdown Inspections.

Conduct winter shutdown inspection 14 calendar days after the anticipated fall freeze-up date and conditions under the CGP Parts 4.12.and 6.2.3, and the SWPPP are met. The Engineer may approve suspension of inspections and waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall, Form 25D-115, during winter shutdown.

Inspections must resume on a regular frequency or reduced inspection frequency identified in the SWPPP, at least 21 days before anticipated spring thaw, CGP Part 6.2.3. Resume updating the Daily Record of Rainfall Form at the start of the 21-day spring thaw inspection.

- Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion if approved by the Engineer.

- SWPPP Amendments and SWPPP Amendment Log.

The SWPPP Amendment Log, Form 25D-114, must be filled out by an individual who holds a current AK-CESCL, or equivalent certification. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer. Amendments must occur:

  - Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

  - If an Inspection identifies that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

  - Whenever an Inspection identifies a problem that requires additional or modified BMPs or a BMP not shown in the original SWPPP is added;

  - If the Inspection frequency is modified (note beginning and ending dates);

  - When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01;

  - When an inspection is not conducted jointly;

  - When an eNOI modification is filed;

  - When a Noncompliance Report is filed with the DEC.

Place all correspondence with the DEC, EPA or MS4s in Appendix Q.

Amend the SWPPP as soon as practicable after any change or modification, but in no case, later than seven days following identification of the need for an amendment. All SWPPP Amendments must have an amendment number, be dated, and signed.

Keep the SWPPP Amendment Log current. Prior to a scheduled Inspection or submittal of an inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log in appendix M.

- Site Maps.

Maintain site maps in accordance with CGP Part 5.3.5 and the SWPPP Template 5.0. It is acceptable to have separate site maps for BMPs, grading and stabilization activities.

- Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112.

The Corrective Action Log must document corrective actions required by the conditions listed in the CGP Part 8.0. Document the need for corrective action within 24 hours of either:

  - Identification during an inspection, or

  - Discovery by the Department's or Contractor’s staff, a subcontractor, or a regulatory agency inspector.

  - If a corrective action is discovered outside of an inspection, update the log with the date of discovery, the proposed corrective action, and the date the corrective action was completed.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log in Appendix J.

- Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection. Keep the Grading and Stabilization Activities Log organized and completed to demonstrate compliance with the CGP Part 4.5.

Keep the Grading and Stabilization Activities Log in Appendix G.

- Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to comply with CGP Part 7.3.9. Submit a copy to the Engineer with each completed Inspection Report. Keep the Daily Record of Rainfall current in Appendix N.

- Staff Tracking Log.

Use the SWPPP Project Staff Tracking, Form 25D-127, to identify project staff that are required to be AK-CESCL certified or an equivalent qualification, CGP Appendix C. Complete this form to document the positions of Superintendent, SWPPP Manager, Engineer, DOT&PF Storm Water Inspector, and when these positions have changed personnel, either permanently or temporarily. Update the SWPPP Project Staff Tracking Form within 24 hours of any changes in personnel, qualifications, or other staffing items related to administration of the CGP or Section 641.

### 641-3.04 FAILURE TO PERFORM WORK.

The Engineer has authority to suspend work and withhold monies for an incident of non-compliance with the CGP, or the SWPPP, that may endanger health or the environment or for failure to perform work related to Section 641.

### Non-compliance.

- Incidents of Non-compliance. Failure to:

  - Obtain appropriate permits before Construction Activities occur;

  - Perform SWPPP Administration;

  - Perform timely Inspections;

  - Update the SWPPP;

  - Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms to the Engineer;

  - Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

  - Perform duties according to the requirements of Section 641;

  - Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control; or

  - Any other requirements established or included in the Contract.

- Notice of non-compliance, either oral or written will include:

  - Reason/defects

  - Corrective actions required

  - Time allowed for completing the corrective action

- Levels of Non-compliance and Response correspond with harm to the workers, the public or the environment and whether the harm is:

  - Not-imminent, the Engineer will either orally or in writing, or both, provide notice to the Contractor indicating the incident of non-compliance.

Contractor's that take corrective action and complete the action to the satisfaction of the Engineer, within the time specified, may return to the status of compliance, and avoid elevating the response to imminent.

  - Imminent, the Engineer will orally provide notice to the Contractor of non-compliance and promptly provide written notice to suspend work until corrective action is completed.

Additional actions, taken against the Contract whether the level of non-compliance is Not-imminent or Imminent, may include:

- Withholding monies until corrective action is completed

- Assessing damages or equitable adjustments

- Employing others to perform the corrective action and deduct the cost

No additional Contract time or additional compensation is allowed due to delays caused by the Engineer’s suspension of work.

### 641-3.05 ACCESS TO WORK.

The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies. CGP Part 6.6.

### 641-4.01 METHOD OF MEASUREMENT.

See Section 109 and as follows:

Item 641.0005.	 , measured as specified in the Directive authorizing the work. Item 641.0006.	, measured as specified in Table 641-2 Version C.

### 641-5.01 BASIS OF PAYMENT.

- BMP Values. Table 641-1 BMP Values – Reserved.

- Erosion, Sediment, and Pollution Control - Liquidated Damages. Liquidated Damages assessed according to Table 641-2 are not an adjustment to the Contract amount. These damages charges are related to Contract performance but are billed by the Department to the Contractor, independent of the Contract amount. An amount equal to the Liquidated Damages may be withheld, for unsatisfactory performance, from payment due under the Contract until the Contractor remits payment for billed Liquidated Damages.

### TABLE 641-2- VERSION C

EROSION, SEDIMENT AND POLLUTION CONTROL – LIQUIDATED DAMAGES

| Code | Specification Section Number and Description | Deductible Amount in Dollars | Cumulative Deductible Amounts in Dollars |
| --- | --- | --- | --- |
| A | 641-1.05 Failure to have a qualified (AK-CESCL or equivalent) SWPPP Manager | Calculated in Code B or F |  |
| B | Failure to meet SWPPP requirements of: - 641-2.01.1 Name of SWPPP Preparer - Not Applicable - 641-3.03.8 Sign and Date SWPPP amendments by qualified person. - 641-3.02 Records maintained at project and made available for review | $750 per omission |  |
| C | Not Applicable. |  |  |
| D | 641-3.03.5 Failure to stabilize a Project prior to fall freeze-up. | $5,000 per Project per year |  |
| E | 641-2.01.1. Failure to conduct pre-construction inspections before Construction Activities on all projects greater than 1 acre. | $2,000 per Project |  |
| F* | 641-3.03. Failure to conduct and record CGP Inspections 641-3.03.1 Personnel conducting Inspections and Frequency 641-3.03.2 Inspection Reports, use Form 25D-100, completed with all required information | $750 per Inspection | Additional $750 for every additional 7 day period without completing the required inspection. |
| G | 641-3.01.4 Corrective action, failure to timely accomplish BMP maintenance and/or repairs. In effect until BMP maintenance and/or repairs is completed. | $500 per Project per day |  |
| H | 641-3.01.3 Failure to provide to the Engineer and DEC a timely oral noncompliance report of violations or for a deficient oral noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| I | 641-3.01.3 Failure to provide to the Engineer and DEC a timely written noncompliance report, use Form 25D-143, of violations or for a deficient written noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| J | 641-3.04 Failure to comply with the requirements of the CGP, approved SWPPP, and Section 641, except as listed above | $750 per occurrence for the first day of noncompliance | Additional $750 for every day the deficiency remains uncorrected |

*CODE F.	Liquidated Damages according to Code F will not be billed for typographic errors and minor data entry errors, except the liquidated damages will be assessed for these errors when:

  - the Contractor has previously been notified and subsequent inspection reports repeat the same or similar error,

  - multiple inspection reports are submitted after the submission due date and the same or similar errors are repeated on multiple overdue reports,

  - an error in recording the inspector's AK-CESCL certification date results in an inspector performing the inspection during a period when their certification was lapsed or was otherwise invalid.

See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

Item 641.0001.   Erosion, Sediment, and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and recordkeeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Item 641.0005.   Temporary Erosion, Sediment and Pollution Control by Directive. At the contingent sum prices specified in the Directive using time and materials to authorize the work, for all labor, supervision, materials, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. Prices for this item will be by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor. All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641.0006.   Withholding. The Engineer may withhold an amount equal to Liquidated Damages, assessed according to Section 641, from payment due the Contractor. Liquidated Damages for violations of the Contract, CWA, and CGP are determined by the Engineer according to Table 641-2. The Engineer may withhold payment due the Contractors until the Contractor pays the Liquidated Damages to the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Item 641.0007.  SWPPP Manager. At the contingent sum price for a SWPPP Manager that conforms to this specification. When Item 641.0007.  appears in the Bid Schedule, the SWPPP Manager must be a different person than the superintendent, and must be physically present during construction activity with duties and authority as described in Subsection 641-2.04. When Item 641.0007.  does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to Item 641.0001.   .

Subsidiary Items. Temporary erosion, sediment, and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641.0001.   Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641. This work includes but is not limited to:

- Dewatering;

- Shoring;

- Bailing;

- Permanent seeding;

- Installation and removal of temporary work pads;

- Temporary accesses;

- Temporary drainage pipes and structures;

- Diversion channels;

- Settling impoundment; and

- Filtration.

Permanent erosion, sediment, and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense. Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Payment will be made under:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 641.0001. | Erosion, Sediment and Pollution Control Administration | LS |
| 641.0005. | Temporary Erosion, Sediment and Pollution Control by Directive | CS |
| 641.0006. | Withholding | CS |
| 641.0007. | SWPPP Manager | CS |

CR641-123121R/CFHWY01060

### SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-3.08 CONTRACTOR FURNISHED COMPUTATIONS. Provide computations for volumetric Pay Items using DTM's developed per Section 642-3.07. Cross sections developed from the appropriate DTM's will be used as a supplementary quality control check on DTM parameters and quantities, and not for pay. The Contractor may use the Average End Area Method in accordance with Section 109, only if approved in writing by the Engineer.

- Deliverables: Provide copies of the following to the Engineer:

  - Plotted cross sections from the DTM surfaces. Develop separate cross sections for each volumetric Pay Item. More than one Pay Item per plotted cross section is not allowed.

    - Plot every 50 ft on Station, including intermediate stations as required to define angle points, curves, or other significant changes in the roadway geometry.

    - Show the elevation and offset information for all vertex points. Weeding vertex point labels is not allowed. Elevation and offset information may be shown on a separate report if the amount of information exceeds what can be legibly shown on the plot.

    - Show the area for each cross section.

    - Label each plot with the project name, project number, Pay Item number, and Pay Item name.

    - Label each plot with the Surveyor's Company name and address.

  - Plotted profiles from the DTM surfaces. Develop separate plots for each volumetric Pay Item. Each plot shall only identify the profiles appropriate to the volumetric Pay Item.

    - Plot the profile along the alignment centerline as shown in the plans.

    - Label each profile as original ground, bottom of excavation, and the top or bottom of embankment, as appropriate.

    - Label topographic profiles with elevation and station information, using a weeding frequency of every 100 ft, or as necessary to match the frequency shown on the plans.

    - Label the neat-line profiles with elevation and station information every 100 ft, and for the beginning, end, and VPI of all vertical curves and grade breaks. Label the percent slope between all grade breaks, to the fourth significant decimal.

    - Label each plot with the project name, project number, Pay Item number, and Pay Item name.

    - Label each plot with the Surveyor's Company name and address.

  - Electronic Data

    - Provide copies of all Topographic, Neat-line, and Combination surfaces to the Engineer. Include all electronic features (alignments, profiles, sections, etc.) used to generate the surfaces.

    - All data shall be delivered on a clearly labeled CD-ROM or DVD, unless specified otherwise by the Engineer. The label shall include the project name, project number, Surveyor's company name, and date. All data becomes the property of the State of Alaska.

    - DTM files shall be saved in Autodesk, TIN, XML, or other approved formats compatible with Department software.

  - Volume Reports

    - Provide interim volume reports showing quantities between every 50 ft station. The volume reports shall be summarized to allow the Department to reference the quantities per individual plan sheet, or as defined in any earthwork summary shown on the plan sheets.

    - Provide a final volume report reflecting the final total quantity. Attach all data, calculations and plots to the report. The report shall be signed, sealed, and dated by the Surveyor. This report shall be used as the basis for final pay.

642-3.09 CONTRACTOR FURNISHED ENGINEERING TOOLS. Furnish and maintain Engineering Tools as directed by the Engineer, for the exclusive use of the Engineer throughout the duration of the project. The Contractor shall furnish all equipment specifications to the Engineer for approval, prior to furnishing equipment. The equipment shall be in good working condition not more than 1 model year old. The Contractor shall insure and indemnify the Department against normal wear and tear, damage, theft, and all other events that may cause a loss of function of the furnished tools. The equipment shall be returned to the Contractor upon completion of the project, or when services are terminated by the Engineer. Furnish training for the Engineer’s staff, as directed by the Engineer.

- GPS Rover Unit – All components shall be fully compatible to provide a stand-alone GPS Rover Unit and be the same or compatible to the contractor’s unit. The Rover Unit shall be an “all on the pole” system equipped with the following:

  - Receiver

    - Bluetooth compatible.

    - Meet waterproof specification IPX7.

    - Shockproof for a drop onto a hard surface from a height of 4 feet.

    - Dual frequency receiver capable of tracking at least twelve (12) satellites simultaneously on parallel channels.

    - Capable of RTK, Static, and Fast Static occupations.

    - Capable of receiving L1, L2, and GNSS frequencies.

    - Antenna model shall have undergone antenna calibration by the NGS.

    - Ensure the receiver contains the manufacturer’s latest firmware upgrades.

    - Provide the manufacturer’s user guide.

  - Controller

    - Bluetooth compatible.

    - Equipped with onboard software allowing for the configuration of RTK, PPK, or Static rover modes.

    - Meet waterproof specification IPX7.

    - Shockproof for a drop onto a hard surface from a height of 4 feet.

    - Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

    - Capable of collecting data in WGS84 and displaying local project coordinates.

    - Equipped with onboard software that allows automatic point logging.

    - Capable of creating and storing line-work in DFX or DWG format.

    - Equipped with onboard software to allow the user to stake-out points, 3D lines, and DTM surfaces. Software shall allow the user to read cut/fill elevations relative to a DTM surface.

    - Capable of importing, exporting, and storing point, line, and DTM data. (11)Capable of showing satellite, radio, and battery status.

(12)Equipped with onboard software that allow the user to create and manage survey jobs, point data, coordinate systems, and alignments.

(13)Equipped with a removable memory storage device with a minimum capacity of 512MB. (14)Capable of storing custom configuration settings for the GPS Rover Unit.

(15)Ensure the controller contains the manufacturer’s latest firmware upgrades. (16)Provide the manufacturer’s user guide.

  - Radio System

    - Meet waterproof specification IPX7.

    - Support a frequency compatible with the Reference Station.

    - Capable of storing multiple radio frequencies.

    - Compatible with the Reference Station’s broadcasting format and protocol.

    - Power and programming cables.

    - Provide the manufacturer’s user guide.

  - Batteries

    - Provide all batteries required to fully power and operate the GPS Rover Unit.

    - Batteries shall be capable of powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

    - Each battery shall be rechargeable and commercially available.

    - Provide an identical replacement backup battery for each primary battery required.

    - Provide all power connectors necessary to connect the batteries to the equipment.

    - Provide battery chargers to allow all onboard batteries to be charged simultaneously, and that safeguard against overcharging.

  - Rod

    - Fixed height (non-adjustable).

    - Mounting hardware for GPS controller and radio.

    - Pole grip with bubble level.

    - Detachable bipod.

    - Interchangeable flat and pointed footings.

    - Quick release adapter for the GPS receiver.

  - Carrying Case

    - Hard Shell.

    - Shockproof.

    - Waterproof.

    - Capacity to hold all components of the GPS rover, minus the rod.

- Continually Operating Reference Station – The location of the CORS shall not change for the duration of the project. The CORS shall be permanently mounted per NGS CORS standards. All structures, mounting hardware, power supply, computers, software, networking, and personnel required to support and operate the CORS is considered subsidiary to this item. Store CORS data for the duration of the project, and post online for use by the Engineer. The CORS shall include and conform to the following requirements:

  - GPS Receiver

    - Choke-ring antenna, model shall have undergone antenna calibration by the NGS.

    - Meet waterproof specification IPX7.

    - Shockproof for a drop onto a hard surface from a height of 4 feet.

    - Able to operate in temperatures between -20º F to +140º F.

    - Capable of logging L1/L2 data continuously for 180 days, and storing at 1 second intervals. If onboard memory storage capacity is insufficient, backup all data on an external memory storage device.

    - Support multiple, simultaneous data logging sessions at different collection rates.

    - Equipped with a dual frequency receiver capable of tracking L1, L2, and GNSS frequencies on at least 12 satellites. Receiver shall have a minimum of 24 channels.

    - Support CMR/CMR+ and RTCM output simultaneously via separate ports.

    - Use multi-path mitigation techniques.

    - Satellite acquisition technology shall provide improved tracking in areas of high radio interference such as under power lines, around airports, near radio-intensive construction sites.

    - Capable of 1PPS output with an accuracy of 1usec. (12)Equipped with 1 primary and 1 secondary power input port.

(13)The system shall automatically switch between power sources. (14)Equipped with over-voltage protection on all power inputs.

(15)Capable of reporting Signal-to-Noise Ratio (SNR) values for L1 and L2. (16)Capable of logging data at operator selected intervals of 0.5, 1, 5, and 30 seconds. (17)Provide the manufacturer’s user guide.

  - Radio

    - Transmission power, 25 watt minimum.

    - Meet waterproof specification IPX7.

    - Ensure the radio has a current license to broadcast in accordance with FCC requirements.

    - Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

    - Provide the manufacturer’s user guide.

  - CORS Facility – Provide a facility to mount and house CORS station equipment.

    - Facility shall meet NGS CORS mounting requirements, and shall be approved by the Engineer.

    - Shall be physically located in a clear view of the sky, away from objects that may cause multi- path interference.

    - Location shall provide for maximum strength of geometry relative to the primary control network and the project limits.

    - Shall be connected to a primary power source, and a backup power source capable of providing uninterrupted backup power for a minimum of 48 hours.

- GPS Base/Repeater Station – All components shall be fully compatible to provide a stand-alone GPS Base/Repeater Station setup. The setup shall include the following:

  - Receiver

    - Meet waterproof specification IPX7.

    - Shockproof for a drop onto a hard surface from a height of 4 feet.

    - Dual frequency receiver capable of tracking at least 12 satellites simultaneously on parallel channels.

    - Antenna model shall have undergone antenna calibration by the NGS.

    - Ensure the receiver contains the manufacturer’s latest firmware upgrades.

    - Carrying case.

    - Tribrach with optical plummet and height rod.

    - Provide the manufacturer’s user guide.

  - Controller

    - Equipped with onboard software allowing for configuration as a GPS reference station in RTK, PPK, Static, and Fast Static modes.

    - Capable of logging raw observations for post processing.

    - Capable of showing satellite, radio, and battery status.

    - Meet waterproof specification IPX7.

    - Shockproof for a drop onto a hard surface from a height of 4 feet.

    - Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

    - Equipped with a removable memory storage device with a minimum capacity of 512MB.

    - Equipped with 1 primary and 1 secondary power input port.

    - Ensure the controller contains the manufacturer’s latest firmware upgrades. (10)Provide the manufacturer’s user guide.

  - Radio

    - Transmission power, 1 watt minimum.

    - Meet waterproof specification IPX7.

    - Shockproof for a drop onto a hard surface from a height of 4 feet.

    - Support a frequency compatible with the Reference Station.

    - Capable of storing multiple radio frequencies.

    - Compatible with the CORS broadcasting format and protocol.

    - Ensure the radio has a current license to broadcast in accordance with FCC requirements.

    - Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

    - Equipped with onboard software/firmware allowing for configuration as either a Reference Station or a Repeater Station.

    - Carrying case. (11)Antenna.

- Antenna/pole mounting adapter. (13)Provide the manufacturer’s user guide.

  - Tripods – Provide one of each:

    - Conventional tripod with extendible range pole. Include carrying case.

    - Conventional wood tripod.

  - Batteries

    - Provide all batteries required to fully power and operate the GPS Base/Repeater Station.

    - Batteries shall be capable powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

    - Each battery shall be rechargeable and commercially available.

    - Provide an identical replacement backup battery for each primary battery required.

    - Provide all power connectors necessary to connect the batteries to the equipment.

    - Provide battery chargers to allow all batteries to be properly charged, and that safeguard against overcharging.

- Computer Hardware – Hardware shall meet the following minimum requirements:

  - Laptop Computer

    - 2.8 GHz multi-core CPU.

    - 120GB Internal Hard Drive.

    - 4 GB System RAM.

    - Display 13” with 1,600 x 1,200 resolution.

    - 512MB video memory.

    - DVD Burner Drive.

    - Internal Bluetooth and Wi-fi.

    - Internal Battery.

    - 120v AC Adapter.

    - 12v DC Adapter.

    - Built-in CF, SD, and PCMCIA card ports.

    - 4 USB 2.0 ports.

    - 1394 (firewire) port.

    - Mouse (wireless).

    - Travel Case (hard) for laptop and accessories.

  - Laptop Computer Mount

    - Permanently installed in a vehicle, as directed by the Engineer.

    - Fastened to the passenger side of the vehicle.

    - Shock and vibration resistant.

    - Fully adjustable positioning with mechanically locking hinge points.

  - Desktop Computer

    - 3 GHz multi-core CPU

    - 120GB Internal Hard Drive

    - 4 GB System RAM

    - Compatible DVI 19” monitor with 1,600 x 1,200 resolution

    - Internal video card/chip, 512MB, 2 DVI ports

    - Internal DVD Burner Drive

    - CF and SD media card reader

    - 6 USB ports

    - 1394 (firewire) port

    - Internal wireless (IEEE 802.11 b/g) network card (11)Internal Ethernet card (10/100 Mbps). (12)Uninterruptible Power Source (UPS), 8 outlets, 390 Watt

- 250 GB Backup Hard Drive (external)

- Mouse and Keyboard

  - Laser Printer

    - 45 pages per minute print speed.

    - 1200 x 1200 dpi print quality.

    - Main tray capacity shall hold no less than 500, 8.5 x 11 inch sheets.

    - Multipurpose tray capable of custom sizes up to 11 x 17 inch sheets.

    - 128 MB of onboard memory, minimum.

- Computer Software – All software shall be licensed and fully operational. Provide software that is similar or approved equal in accordance with the following:

  - Operating System Software – Provide an operating system that supports the drivers of all onboard and auxiliary computer hardware systems. The operating system shall be of the latest release, with the most current updates installed. The operating system shall support all of the applications listed below.

  - CAD Software – Provide CAD software that is capable of dynamically associating and updating alignment, profile, section, grading, point, and surface data. The software shall be capable of saving all data to formats that are compatible with the latest release of CAD software currently used by the Department. Formatting shall preserve the dynamic relationship of all DTM features. Software that doesn’t dynamically associate all DTM features is not acceptable.

  - Word Processing Software – Provide software that is compatible with the latest release of word processing software currently used by the Department.

  - Spreadsheet Processing Software – Provide software that is compatible with the latest release of spreadsheet processing software currently used by the Department.

  - Anti-Virus Software – Provide software to protect against viruses and other security threats. Software shall be equipped with a firewall containing industry standards of system protection. The software shall be capable of backing up all hard drive data.

  - GPS Processing Software – Provide GPS processing software of the latest release and from the same vendor as the GPS equipment furnished. Include all necessary hardware/software keys to enable L1 & L2 Static, PPK, and RTK processing, GNSS processing, network adjustments, datum and map transformations, and RINEX data importing and exporting.

642-4.01 METHOD OF MEASUREMENT. The work will be measured according to Section 109, and as follows:

Contractor Furnished Computations. Contingent sum work will be measured in accordance with the directive authorizing the work.

Contractor Furnished Engineering Tools. Contingent sum work will be measured in accordance with the directive authorizing the work.

### 642-5.01 BASIS OF PAYMENT.

Add the following Pay Item:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 642.2005.0000 | Contractor Furnished Computations | LS |
| 642.2006.0000 | Contractor Furnished Engineering Tools | CS |

#### CFHWY01060

Special Provisions

Replace Section 643 with the following:

### SECTION 643 TRAFFIC MAINTENANCE

Protect and control traffic during the contract. Furnish, erect, maintain, replace, clean, move, and remove the traffic control devices required to ensure the traveling public’s safety. Perform all administrative responsibilities necessary to implement this work.

Maintain all roadways and pedestrian and bicycle facilities affected by the work in a smooth and traversable condition. Construct and maintain approaches, crossings, intersections, and other necessary features throughout the project for the life of the contract.

Illuminate construction activities listed in Table 643-4 during hours of night work on roads open to the public within project limits.

643-1.02 DEFINITIONS. These definitions apply only to Section 643.

ATM. When used in this Section, ATM stands for the Alaska Traffic Manual, which is comprised of the Manual on Uniform Traffic Control Devices (MUTCD), the Alaska Traffic Manual Supplement, any adopted revisions or interim addenda to either document issued subsequently, and corrections to known errors to either document.

BALLOON LIGHT. Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.

CONSTRUCTION PHASING PLAN. A plan for each phase of the project showing how to accommodate traffic. Show the sequence of work by segment or phase, if required.

FIXED OBJECTS. Private vehicles, parked flagger vehicles, idle construction equipment, construction material stockpiles, culvert ends, individual trees, power poles, utility poles and appurtenances, and other items deemed by the Engineer to present a hazard to motorists, pedestrians, or bicyclists traveling through the work zone.

NIGHT WORK. Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in the Table 643-1 below:

### TABLE 643-1

PROJECT LOCATIONS – NIGHT TIME ILLUMINATION EXCLUSION

| Latitude | No Lighting Required |  | Nearby |
| --- | --- | --- | --- |
| (degrees) | Start | End | Cities |
| South of 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Tok, Delta, Nome |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle City |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

TRAFFIC. The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, or similar operations.

TRAFFIC CONTROL PLAN (TCP). A drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. The TCP depicts the traffic control devices and their placement and times of use.

TRAFFIC CONTROL ZONE. A portion of a road construction project, maintenance operation, utility work or similar operation that affects traffic and requires traffic control to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. Implement an approved TCP before beginning work within the project limits.

The TCP includes, but is not limited to, signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary lighting, temporary roadways and all other items required to direct traffic through or around the traffic control zone according to these Specifications and the ATM. Address in the TCPs placement of traffic control devices, including location, spacing, size, mounting height and type. Include code designation, size, and legend per the ATM and the Alaska Sign Design Specification (ASDS). Include longitudinal buffer space for the posted speed limit, according to Table 6C-2 of the ATM unless project conditions or geometric features prohibit including all or a portion of the buffer length.

When a TCP is included in the Plans, use it, modify it, or design an alternative TCP. When a TCP is omitted from the Plans, provide one according to this Section and the ATM.

Submit new or modified TCPs to the Engineer for approval. All TCPs must include the following information:

- Project name and number.

- A designated TCP number and name on each page.

- For TCPs more than one page, each page must be numbered.

- The posted speed limit for each roadway.

- Existing striping width, lane width, and road surfacing.

- Construction lane widths, striping layout, and temporary pavement marker layout.

- Provisions for Pedestrian, Bicycle, and ADA travel through the work zone.

- Dates and times the TCP will be in effect and why it is being used.

- The Worksite Traffic Supervisor’s signature certifying that all TCPs conform to the ATM and the Contract.

- The Project Superintendent’s signature confirming the TCP is compatible with the work plan.

- The name(s) of the Worksite Traffic Supervisor, his/her alternate and their 24-hour telephone number(s).

- Signs to be used and the ASDS designation number and size.

- Location and spacing of all devices and signs.

- A plan to address any possible slopes, drop offs, paving joints, or similar temporary features that may occur during use of the TCP.

- For TCPs proposed to be used at night, note how the requirements will be met for the required lighting and retroreflective material.

TCPs submitted for approval without all the required information will be rejected. Allow 7 days for review of each TCP submittal. All required modifications to a TCP require a new submission and an additional 7 days for review.

A minor revision to a previously approved TCP during construction requires 48 hours for review and approval by the Engineer.

The TCPs, Plans, and Alaska Standard Plans show the minimum required number of traffic control devices. If unsafe conditions occur, the Engineer may require additional traffic control devices.

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits. If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan. Maintain a minimum 12-foot lateral separation between the nonstreet legal vehicles and the motoring public. The Traffic Control Plan shall specify the traffic control devices required for these operations.

Road Closures and Major Traffic Sequencing (events). Submit a written request to the Engineer for review and approval of each proposed event and event date. Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections. The proposed event date will be no less than 14 days from the date of written approval.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. Provide a Worksite Traffic Supervisor responsible for maintaining 24-hour traffic operations.

- Qualifications. The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements. The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, proposed operations, and certified as one of the following:

  - Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

  - Work Zone Temporary Traffic Control Technician, or Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor has a minimum 4000 hours of temporary traffic control work experience, is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this section.

- Temporary traffic control work experience shall demonstrate an understanding of concepts, techniques, and practices in the installation and maintenance of traffic control devices, and skill in reading, interpreting, implementing, and modifying TCPs.

- Temporary traffic control work experience includes: flagging; installing traffic control devices in accordance with TCPs; monitoring traffic control devices and TCP performance; and recognizing and reporting deficiencies in traffic control devices and TCPs for correction.

- Temporary traffic control work experience is gained while serving as a Worksite Traffic Supervisor-in-training, temporary traffic control support personnel, and Flagger.

- Four thousand hours of experience serving solely as a Flagger does not satisfy these requirements.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

### Duties.

  - Prepare the TCPs and public notices and coordinate traffic control operations between the Project Superintendent and the Engineer.

  - Physically inspect the condition and position of all traffic control devices used on the project at least twice each day and at approximately 12-hour intervals. Ensure that traffic control devices work properly, are clean and visible, and conform to the approved TCP. Complete and sign a detailed written report of each inspection within 24 hours. Use Traffic Control Daily Review Form 25D-104.

  - Supervise the repair or replacement of damaged or missing traffic control devices.

  - Review and anticipate traffic control needs. Make available proper traffic control devices necessary for safe and efficient traffic movement.

  - Review work areas, equipment storage, and traffic-safety material handling and storage.

  - Hold traffic safety meetings with superintendents, foremen, subcontractors, and others as appropriate before beginning construction, prior to implementing a new TCP, and as directed. Invite the Engineer to these meetings.

  - Supervise all traffic control workers, flaggers, and pilot car drivers.

  - Certify that all flaggers are certified as required by Subsection 643-3.04.4. Submit a copy of all flagger certifications to the Engineer.

i	Supervise lighting for night work.

- Authority. The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-1.05 CONSTRUCTION PHASING PLAN. Submit a Construction Phasing Plan for approval no less than 5 working days prior to the preconstruction conference. Include the following:

- Form 25D-124 designating the Worksite Traffic Supervisor, providing the 24-hour telephone number, and certifying minimum 4,000 hours of work experience as described in 643-1.04 Worksite Traffic Supervisor.

- A construction-phasing plan for each phase or segment of the project.

- TCPs for the first phase of the project. Show permanent and temporary traffic control measures, including the times each TCP will be used.

Submit any changes to the Engineer for approval 7 days before proposed implementation.

643-1.06 TRAFFIC MAINTENANCE SETUP. When shown on the bid schedule, Traffic Maintenance Setup items are site specific and are detailed as individual TCPs on the plan sheets. They depict the method or scheme required to route traffic safely and efficiently when any of the following restrictions occur:

- Lane Closure. The closure of one or more lanes on a roadway.

- Detour. The redirection of traffic through or around a traffic control zone.

- Road Closure. The closure of a roadway with or without a specified detour route.

- One Lane Road. A two-way roadway reduced to a single-lane roadway with flaggers, pilot cars, traffic signals, stop signs, or yield signs.

643-2.01 MATERIALS. Provide traffic control devices meeting the following requirements:

- Signs. Use signs, including sign supports, that conform to Section 615, the ATM, and ASDS.

  - Construction Signs: Regulatory, guide, or construction warning signs designated in the ASDS.

  - Permanent Construction Signs: As designated on the Plans or an approved TCP.

  - Special Construction Signs: All other signs are Special Construction Signs. Neatly mark the size of each sign on its back in 3-inch black numerals.

- Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 48 X 48 inch traffic control sign at the height above the adjacent roadway surface required by the ATM.

- Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 8 feet long. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

- Portable Concrete Barriers. Use portable concrete barriers that conform to the Contract. For each direction of traffic, equip each 12.5-foot section of barrier with at least two side-mounted retroreflective tabs placed approximately 6 to 8 feet apart, or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier. Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V.

- Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

- Drums. Use plastic drums that conform to the requirements of the ATM. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

- Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 28 inches high. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

- Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

  - Paint meeting Subsection 708-2.03 with glass beads meeting Subsection 712-2.08,

  - Preformed Marking Tape (removable or non-removable) meeting Subsection 712-2.14, or

  - Temporary Raised Pavement Markers meeting Subsection 712-2.15 or 712-2.16, as appropriate.

- High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

- Temporary Crash Cushions. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V. Application of crash cushion must be appropriate for the intended use and be installed per manufacturer’s recommendation. Temporary crash cushions used as rail or barrier end treatments must be redirective. Temporary crash cushions that are barrels or barricade filled with sand or water may only be used when the forecasted temperature during their use is above 32 degrees Fahrenheit.

- Sequential Arrow Panels. Use Type A (24 X 48 inch), Type B (30 X 60 inch) or Type C (48 X 96 inch) panels that conform to the ATM.

- Portable Changeable Message Board Signs. Use new truck or trailer mounted portable changeable message board signs with self-contained power supply for the sign and with:

  - Message sign panel large enough to display 3 lines of 18-inch high characters

  - Eight character display per message module

  - Fully programmable message module

  - Remote control cellular, wireless radio frequency (RF), landline

  - Waterproof, lockable cover for the controller keyboard

  - Capacity for electric/hydraulic sign raising or lowering

  - Radar over speed detection

  - Variable flash and sequence rates

  - Light emitting diode (LED) display, using Institute of Transportation Engineers (ITE) amber/yellow

  - The capacity for a minimum of 150 pre-programmed messages

  - Battery-Pack Operation Duration: minimum of 55 hours under full load

  - Power chords shall comply with the National Electrical Code (NEC) Article 600.10 Portable or Mobile Signs, paragraphs 600.10(C)(1) Cords and 600.10(C)(2) Ground-Fault Circuit Interrupter (GFCI). The cord will have integral GFCI protection located in either the attachment plug or 12 inches or less from the plug.

- Plastic Safety Fence. Use 4-foot high construction orange fence manufactured by one of the following companies, or an approved equal:

  - "Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306. Phone (800) 428-8185.

  - "Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108. Phone (800) 648-7916.

  - "Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104. Phone (800) 662-6338.

- Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

  - Use plywood at least 1/2-inch thick for areas continuously supported by subgrade. Use plywood at least 1 inch thick for areas that are not continuously supported.

  - Do not use unsupported 1-inch plywood longer than 30 inches.

  - Use plywood with regular surfaces. Do not overlap plywood joints higher than 1/2-inch. Bevel overlap joints so the maximum slope of the overlapping edge is 2 horizontal to 1 vertical.

  - Fasten so wind and traffic will not displace temporary surfacing.

- Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

- Flagger Paddles. Use flagger paddles with 24 inches wide by 24 inches high sign panels, 8 inch Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use retroreflective sheeting that meets ASTM D4956 Type VIII, IX or XI. Use background colors of fluorescent orange on one side and red on the other side.

- Truck Mounted Attenuator, TMA. The TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight per the manufacturer’s recommendations.

- Portable Steel Barriers. Use portable steel barriers that conform to the contract. For each direction of traffic, equip each section of barrier with side-mounted retroreflective tabs placed approximately 6 to 8 feet apart, or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier.  Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV, or V.

- Flexible Markers. Refer to Subsection 606-2.01 Materials.

643-2.02 CRASHWORTHINESS. Temporary Work Zone devices, including portable barriers, manufactured after December 31, 2019, must have been successfully tested to the 2016 edition of Manual for Assessing Safety Hardware (MASH). Such devices manufactured on or before this date, and successfully tested to National Cooperative Highway Research Program (NCHRP) Report 350 or the 2009 edition of MASH, may continue to be used throughout their normal service lives.

Submit documentation, by the method indicated on table 643-2, that the following devices comply with Test Level 3 requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or the Manual for Assessing Safety Hardware (MASH). Submit documentation of compliance to the Engineer before installing devices on the project.

### TABLE 643-2

WORK ZONE TRAFFIC CONTROL DEVICE AND BARRIER CRASH TESTING COMPLIANCE

| Category | Devices | Devices Manufactured Before Dec. 31, 20191 | Devices Manufactured after Dec. 31, 20191 | Method of Documentation |
| --- | --- | --- | --- | --- |
| 1 | Low-mass single-piece devices w/o attachments; traffic cones, tubular markers, single piece drums, delineators | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | Manufacturer's Certification for devices exceeding height and weight limits |
| 2 | Category 1 devices with attachments, barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in Category 1 | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, at Test Level 32. |
| 3 | Fixed sign supports, truck mounted attenuators, temporary crash cushions, bridge railing, bridge and guardrail transitions, and guardrail and barrier end treatments. | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, at Test Level 32. |
|  | Portable Concrete and steel barriers | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, if available, at Test Level 3, or DOT&PF eligibility determination, unless otherwise required in the Contract |

- The Engineer will determine whether a device is in serviceable condition. Serviceable means the device will function equivalent to a new device of the same manufacture.

- When no test level is specified in a FHWA Eligibility letter; it is implied that the tests were run for Test Level 3.

In Table 643-2, Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3. This certification may be a one-page affidavit signed by the vendor. Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization. No certification is required for devices less than or equal to both the weight and height on the schedule below:

| Device | Composition | Weight | Height |
| --- | --- | --- | --- |
| Cones | Rubber | 20 lb | 36 in. |
|  | Plastic | 20 lb | 48 in. |
| Candles | Rubber | 13 lb | 36 in. |
|  | Plastic | 13 lb | 36 in. |
| Drums | Hi Density Plastic | 77 lb | 36 in. |
|  | Low Density Plastic | 77 lb | 36 in. |
| Delineators | Plastic or fiberglass | N/A | 48 in. |

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Keep the work, and portions of the project affected by the work, in good condition to accommodate traffic safely. Provide and maintain traffic control devices and services inside and outside the project limits, day and night, to guide traffic safely.

Unless otherwise provided in this Section, keep all roadways, business accesses, and pedestrian facilities within the project limits open to traffic. Obtain the Engineer’s approval before temporarily closing residential, commercial, or street approaches. Provide access through the project for emergency vehicles and school and transit buses. Properly sign and/or flag all locations where the traveling public is redirected or stopped. Organize construction operations so the total of all construction related stoppages experienced by a vehicle traveling through the project does not exceed 20 minutes except when indicated otherwise in the Contract.

Stop equipment at all points of intersection with the traveling public unless an approved TCP shows otherwise.

Continue to operate all illumination and signalization according to the requirements of Subsection 660-

3.09. When moving approach lanes, realign signal heads as necessary according to the ATM. Coordinate any modifications to existing traffic signals with the agency that maintains and operates them. Operate flood lighting at night according to the ATM. Adjust flood lighting so that it does not shine into oncoming traffic.

Provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times, except when regulations prohibit pedestrians or bicyclists. Station a flagger, where construction activity encroaches onto the safe route in a traffic control zone, to assist pedestrians, and bicyclists past the construction activity.

Maintain business access(s) during flagging operations.

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as an employee or a subcontractor becomes aware of the accident.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Obtain an approved TCP before

reducing existing roadway lane and shoulder widths and before starting construction. Maintain a clear area with at least 2 feet between the edge of traveled way and the work area. Use barricades, traffic cones, or drums to delineate this area. Place traffic control devices on the work side of the clear area. Space them according to the ATM.

### Traffic Traversing Unpaved Surface(s).

The total length of unpaved surfaces(s), measured parallel to the roadway, may not exceed the disturbed ground limit in Subsection 652-1.04 and as noted in 643-3.02.

Limit the concurrent unpaved surfaces to [NA], and the immediate area of work. Patch with hot mix asphalt less than 48 hours after removing the existing pavement.

If maintaining traffic on an unpaved surface, provide a smooth and even surface that public traffic can use at all times. Properly crown the roadbed surface for drainage. Before beginning other grading operations, place sufficient fill at culverts and bridges to permit traffic to cross smoothly and unimpeded. Use part- width construction techniques when routing traffic through roadway cuts or over embankments under construction. Excavate the material or place it in layers. Alternate the construction activities from one side to the other. Route the traffic over the side opposite the one under construction.

Detour traffic when the Plans or an approved TCP allows. Maintain detour routes so that traffic can proceed safely. When detours are no longer required, obliterate the detour. Topsoil and seed appropriate areas.

If two-way traffic cannot be maintained on the existing roadway or detour, use half-width construction or a road closure if it is shown on an approved TCP. Make sure the TCP indicates closure duration and conditions. Schedule the roadway closures to avoid delaying school buses, and peak-hour traffic. For road closures, post closure-start and road-reopen times at the closure site, within view of waiting traffic.

Pave lanes next to the median first. Pave lanes next to exit and entrance ramps last. Place temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps. Do not open the roadway to traffic until slope wedges are in place.

643-3.03 PUBLIC NOTICE. Give notice at least 3 days before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

- Alaska Trucking Association

- Alaska State Troopers

- Division of Measurement Standards

- Local Police Department

- Local Fire Department

- Local Government Traffic Engineer

- School and Transit Authorities

- Local Emergency Medical Services

- Local Media (newspapers, radio, television)

- Railroads (where applicable)

- U.S. Postal Service

- Major Tour Operators

Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system. Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. These telephone numbers are used to alert construction employees when emergency vehicles must pass through the project. When notified of emergencies make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator or 511 System for selected projects. Check the special provisions for those requirements.

#### CR643-010122/CFHWY01060

Notice of the reroute and construction zone crossings shall be provided to land managers and trail users and posted well in advance at trailheads for the Resurrection Pass Trail (both ends), Bean Creek Trail, Slaughter Gulch Trail, Birch Hill Trail, Summit Creek Trail, Devils Pass Trail, and area campgrounds and public buildings. Notices also shall be published in Anchorage and Kenai Peninsula newspapers.

#### CFHWY01060

643-3.04 TRAFFIC CONTROL DEVICES. Before starting construction, erect permanent and temporary traffic control devices required by the approved TCPs. The Engineer will determine advisory speeds when necessary.

For lane closures on multilane roadways, use sequential arrow panels. During hours of darkness when required by the approved TCP, use flashing warning lights to mark obstructions or hazards and steady- burn lights for channelization.

Use only one type of traffic control device in a continuous line of delineating devices, unless otherwise noted on an approved TCP. Use drums or Type II barricades for lane drop tapers.

During non-working hours and after completing a particular construction operation, remove all unnecessary traffic control devices. Store all unused traffic control devices in a designated storage area which does not present a nuisance or visual distraction to traffic. If sign panels are post mounted and cannot be readily removed, cover them entirely with either metal or plywood sheeting. Completely cover signal heads with durable material that that fully blocks the view of signal head and will not be damaged or removed by weather.

Keep signs, drums, barricades, and other devices clean at all times.

Use only traffic control devices that meet the requirements of the “Acceptable” category in ATSSA (American Traffic Safety Services Association) “Quality Guidelines for Temporary Traffic Control Devices” and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project. Stock repair parts for each Temporary Crash Cushion used on the project. Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware. All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the plans, specifications, and approved TCPs until permanent roadside safety hardware is installed. All temporary roadside safety hardware shall meet crashworthiness requirements of Subsection 643-2.02.

All items paid under this Section remain the property of the Contractor, unless noted otherwise in the contract. Remove them after completing the project.

- Embankments. Close trenches and excavations at the end of each continuous work shift, except as indicated by the Engineer.

Install portable concrete or steel barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as specified on the Plans or TCPs to delineate open trenches, ditches, other excavations, and hazardous areas when they exist along the roadway for more than one continuous work shift.

- Adjacent Travel Lane Paving. When paving lifts are 2 inches or greater and you cannot finish paving adjacent travel lanes or paved shoulders to the same elevation before the end of the paving shift, install: W8-11 (Uneven Lanes), W8-9 (Low Shoulder), W8-17 (Shoulder Drop-Off), W14-3 (No Passing Zone), R4-1 (Do Not Pass), R4-2 (Pass with Care), and W8-1 (Bump) signs as appropriate. Place additional signs every 1500 feet if the section is longer than 1/2 mile.

- Fixed Objects, Construction Vehicles and Equipment Working On or Next to the Traveled Way. Do not park equipment in medians. Locate fixed objects at least 30 feet from the edge of traveled way. Fixed objects that exist prior to construction activity are not subject to this requirement unless the proposed temporary traffic routing moves the edge of traveled way closer to the pre-existing fixed object. Vehicles and other objects within parking lots in urban environments are considered preexisting fixed objects regardless of whether they are or are not present continuously throughout the day.

When worksite restrictions, land features, right of way limitations, environmental restrictions, construction phasing, or other construction conditions allow no practicable location meeting the preceding requirements, the Engineer may approve alternate locations for fixed objects. Alternate locations shall be as far as practicable from the edge of traveled way. When the alternate location provides 15 feet or more separation from the edge of traveled way, the Engineer may verbally approve the alternate location. When the alternate location provides less than 15 feet separation, written approval is required.

When the Engineer determines a fixed object or fixed objects present unacceptable hazard, use drums, or Type II barricades with flashing warning lights, or use portable concrete or steel barriers, or temporary crash cushion to delineate or shield the hazard, as approved by the Engineer.

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

- Flagging. Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone. The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

  - Flagging Level I Certification by IMSA

  - Flagger Certification by ATSSA

  - Traffic Control Supervisor, ATSSA

  - Work Zone Safety Specialist, IMSA

  - ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification. Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned flagging location at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements. Remove, fully cover, or lay down flagger signs when no flagger is present. Keep the flaggers’ area free of encumbrances. Keep the flagger’s vehicle well off the roadway and away from the flagging location so the flagger can be easily seen.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer’s written approval before flagging signalized intersections. When flagging a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode. Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer. Get their written approval in advance. Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

- Pilot Cars. You may use pilot cars when part of an approved TCP, if the Engineer determines one- way traffic is necessary, or if the route through the traffic control zone is particularly hazardous, involved, or frequently altered to preclude adequate signing, Do not use pilot cars to avoid localized traffic control at several locations. Pilot car operators may not control Automated Flagger Assistance Devices while operating a pilot car.

Organize construction operations so the total of all stoppages experienced by a vehicle traveling through a project does not exceed 20 minutes. However, this does not imply that you may allow 20 minutes in all cases. Coordinate multiple pilot-car operations within a project or adjoining projects to minimize inconvenience to the traveling public. Two or more pilot cars may be used to provide two- way traffic through the traffic control zone to reduce the waiting period. The flagger or pilot car operator must record each pilot car’s departure time in a bound field book furnished by the Engineer. Whenever practical, the flagger should tell the motorist the reason for and approximate length of the delay. Make every reasonable effort to yield right-of-way to the public and prevent excessive delay.

Use an automobile or pickup as the pilot car, with the company logo prominently displayed. Equip the pilot car with a two-way radio for contact with flaggers and other pilot cars. Mount a G20-4 sign (Pilot Car Follow Me) on the rear at least 5 feet above the driving surface. Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on all Pilot Cars. Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons. Identify the last vehicle in the column.

When pilot car operations are approved, establish all required pilot car traffic control devices before beginning work. Continue pilot car operations until no longer necessary and an approved TCP is in place for operations without pilot car, including all required traffic control devices.

- Street Sweeping and Power Brooming. Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material. Use equipment for brooming and sweeping as recommended by the manufacturer and the following:

Dirt, dust and construction materials, mobilized as a result of power brooming and or sweeping, shall not be pushed, ejected, thrown or drift beyond the lesser of, 2 feet from the equipment perimeter or the edge of the paved surface.

All equipment shall operate to typical industry standards. Maintain equipment to operate as designed by the manufacturer. Equipment will employ safety equipment, warning lights, and other as required by the Specifications and these Special Provisions.

Sweeper and Broom Options: Table 643-5, Traffic Control Rate Schedule, Street Sweeping

  - Regenerative Sweeper: Sweeper that blows a stream of air at the paved surface, causing fine particles to rise, and then caught through a vacuum system.

  - Vacuum Sweeper: Sweeper that creates a vacuum at the paved, surface sucking dirt, dust, and debris into a collection system.

  - Mechanical Broom Sweeper: Sweeper designed to pick up and collect larger size road debris, stones and litter, etc. In addition to the requirements noted in these Specifications, use of a mechanical broom sweeper requires the Engineer to approve the sweeper for the intended use.

  - Power Broom: Power brooming that wets, pushes and or ejects loose material directly into an attached collection/pickup container may be used when approved by the Engineer. The added moisture will be contained to the paved roadway surface.

Dry Power Brooming is not permitted.	Power brooming without direct/immediate means of collection/pickup is not permitted.

- Watering. Furnish, haul, and place water for dust control and pavement flushing, as directed. Use water trucks that can provide a high-pressure water stream to flush the pavement and a light-water spray to control dust. If the flushing operations contaminate or fill adjacent catch basins, clean and restore them to their original condition. This requirement includes sections of roadway off the project where flushing is required. The Engineer will control water application.

Obtain an Alaska Department of Natural Resources permit for water removal before taking water from a lake, stream, or other natural water body. Comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

- Portable Changeable Message Board Signs. Furnish Changeable Message Signs when approved on a TCP. Display only messages approved on the TCP. Follow application guidelines in the ATM.

- Truck Mounted Attenuator (TMA). TMAs are mounted on the rear of work vehicles. Impact attenuators shall meet crashworthiness requirements of 643-2.02. TMAs shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight in accordance with the manufacturer’s recommendations. TMAs shall have an adjustable height so that it can be placed at the correct elevation during usage and to a safe height for transporting. Approach ends of TMAs shall have impact attenuator markings in accordance with the ATM. Do not use a damaged attenuator in the work. Replace any damaged TMA at your expense.

- Traffic Control Vehicles. Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on the Work Zone Supervisor’s vehicle and on vehicles being used to transport and set-up traffic control devices. Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.

643-3.05 AUTHORITY OF THE ENGINEER. When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice, and then a written notice according to Subsection 105-1.01, Authority of the Engineer. The notice will state the defect(s), the corrective action(s) required, and the time required to complete the corrective action(s). In no case shall this time exceed 24 hours. If corrective action(s) are not completed within the specified time, the Engineer may immediately suspend work on the offending operations until the defect(s) are corrected. The Engineer may require outside forces to correct unsafe conditions. The cost of work by outside forces will be deducted from any monies due under the terms of this Contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. A Traffic Price Adjustment, under Item 643.0023.  , will be assessed for unauthorized lane closures or reductions. Unauthorized lane reductions will be assessed as one full lane closure, for each lane reduced without authorization.

Authorized lane closures and/or lane reductions are those shown in the Contract, an approved TCP, or authorized in writing.

Unauthorized lane reductions include unacceptable roadway, pedestrian walkway or route, and bicycle route or pathway surfaces, such as severe bumps, ruts, washboarding, potholes, excessive dust or mud, and non-conforming or out of place traffic control devices. Failure to install temporary crash cushions or barriers, when required according to the Contract or TCP, is also considered an unauthorized lane reduction. The Engineer will make the sole determination whether unauthorized lane reductions or closures are present.

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-3, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

The rates are liquidated damages which represent highway user costs, based on Average Daily Traffic (ADT). The Engineer will use the rate shown for the current ADT for this project, as published in the Regional Traffic Volume Report prepared by the Department's Planning Section. Adjustment rates for unauthorized reduction or closure of each lane of pedestrian walkways or route, and bicycle route or pathway, are the same as for one full roadway lane closure.

### TABLE 643-3 ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Unauthorized Lane Reduction or Closure |
| --- | --- |
| Less than 1,000 | $6 |
| 1,000-4,999 | $25 |
| 5,000-9,999 | $75 |
| 10,000-29,999 | $105 |
| 30,000+ | $150 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month

before work is suspended for the season, schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the anticipated roadway condition and the work expected to be completed before shutdown. Schedule a field review with the Department for winter maintenance acceptance. At the field review, the Engineer will prepare a punch list for implementation before acceptance.

To be relieved of winter maintenance responsibility, leave all roads with a smooth and even surface for public use at all times. Properly crown the roadbed surface for drainage and install adequate safety facilities. Make sure all illumination and signals, including vehicle detectors, are in good working order.

After the project is accepted for winter maintenance and until ordered to resume construction operations, the Department is responsible for maintaining the facility. The Department will accept maintenance responsibility only for portions of the work that are open to the public, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. The contractor is responsible for maintaining all other portions of the work. The Engineer will issue a letter of “Acceptance for Winter Maintenance” that lists all portions of the work that the Department will maintain during a seasonal work suspension. The contractor retains all contractually required maintenance responsibilities until receipt of this letter.

If the contractor suspends work due to unfavorable weather (other than seasonal) or due to failure to correct unsafe conditions, carry out Contract provisions, or carry out the Engineer’s orders. All costs for traffic maintenance during the suspended period will be borne by the Contractor.

When work is resumed, replace or renew any work or materials lost or damaged during temporary use. If the Department caused damage during winter suspension, payment will be made for repairs by unit pay item or in accord with Subsection 109-1.05, Compensation for Extra Work. When the Engineer directs, remove any work or materials used in the temporary maintenance. Complete the project as though work has been continuous.

643-3.08 CONSTRUCTION SEQUENCING. The construction sequencing detailed in these provisions, the Special Provisions, and the Plans is suggested only. The Contractor may propose alternative construction sequencing.

Throughout the project, maintain the existing roadway, pedestrian walkway, or route, and bicycle route or pathway configuration (such as the number of lanes and their respective widths) except for restrictions to traffic allowed in the Special Provisions or on the Plans, and addressed through approved TCPs. A restriction to traffic is any roadway surface condition, work operation, or traffic control setup that reduces the number of lanes or impedes traffic. Obtain an approved TCP before restricting traffic.

#### CR643-010122/CFHWY01060

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below:

- May 1 to September 30:

  - Monday through Thursday: 0600 hrs to 2100 hrs.

  - Weekends: Friday 0600 hrs to Sunday 2200 hrs.

- October 1 to April 30:

  - Monday through Thursday: 0600 hrs to 0800 hrs.

- Around any Holiday:

  - If a holiday falls on Monday, or Tuesday, the above stipulations apply from 1200 hrs on the Friday before the holiday to 0300 hrs. on the day after the holiday.

  - If a holiday falls on Wednesday, the above stipulations apply from 1200 hrs on the Tuesday before the holiday to 0300 hrs. on the Thursday after the holiday.

  - If a holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 hrs on the day before the holiday to 0300 hrs. on the Monday after the holiday.

- July 10 through July 31: No travel restrictions

Lane restrictions, if allowed, conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic detained, whichever occurs first, before releasing the detained motorists. During paving operations, a 20 minute stopped delay, 80 vehicles, or 1/2 mile (2640 feet) of traffic detained, allowed for motorists, except school buses. If a queue of traffic develops at a stop, empty the entire queue to include the last car that entered the queue at the time the queue was released.

Do not delay the school busses through the construction zone; obtain the local school bus schedule and coordinate work efforts. Submit the plan, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

#### CR643/CFHWY01060

Vehicle and pedestrian access to all trails, Kenai Peninsula Borough roadways, and other recreational resources shall be maintained at all times for the duration of the project, unless approved by the Engineer.

Coordinate temporary detours of the Resurrection Pass and Bean Creek Trails with the United States Forest Service (USFS) at least two weeks before detour shall begin.

Coordinate closures of United States Forest Service (USFS) access roads with the USFS. Provide the USFS with dates and durations of closures at least two weeks before closures shall begin.

Notices of trail impacts shall be published in the Anchorage and Kenai Peninsula newspapers.

Special Construction signs, in accordance with Subsection 643-2.01, shall be used to advise the public of work in the vicinity of trails and planned closures of trails. Special Construction signs shall be placed at trailheads at least two weeks before construction begins and be maintained in serviceable condition for the duration of the project. Signs shall state dates and duration of work and dates and duration of trail closures.

Use Plastic Safety Fence, in accordance with Subsection 643-2.01, or other means approved by the Engineer to delineate trails through the work site and close the trails as necessitated. No equipment shall be staged in locations that will impede trail access.

#### CFHWY01060

643-3.09 INTERIM PAVEMENT MARKINGS. Place permanent or interim pavement markings according to this Subsection, details shown on the Plans, approved TCPs, and Parts III and VI of the ATM before opening existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments for more than one continuous work shift. This work may include restriping the existing roadway before beginning construction, before seasonal suspension, and/or after seasonal suspension.

Remove conflicting pavement markings according to Subsection 670-3.04, Paint Removal.

Mark existing roadway sections that will be opened to traffic during the winter. Mark over the existing lines and markings, unless shown otherwise on the Plans or an approved TCP.

Maintain all interim pavement markings for their intended life including reapplication when necessary. There will be no compensation to upgrade interim pavement markings required for work operations lasting up to 2 weeks.

Use only temporary raised pavement markers as interim pavement markings on final pavement surfaces. Completely remove and dispose of them when placing the final markings. Completely remove any residual adhesive that might misguide motorists. Place final pavement markings on finished pavement surfaces and interim pavement surfaces before suspending work for the winter.

Stage the construction to avoid routing traffic over conflicting markings, for more than one continuous work shift. If traffic is routed over conflicting markings during a work shift, delineate the roadway with a complement of warning signs, channelizing devices, and flaggers as required by the ATM.

Use only temporary raised pavement markers meeting Subsection 712-2.16 as interim markings on seal coat and surface treatment pavements. Install the markers according to the manufacturer’s instructions before applying the asphalt surface material and cover coat. Remove the vinyl protective covers after applying the asphalt pavement.

On multicourse surface treatments, install the temporary raised pavement markers after applying the full width of the first layer of cover coat. Install the markers on each day's completed surface before removing the pilot car operations and allowing unescorted traffic on the surface treatment.

Apply final pavement markings according to Subsection 670-3.01, Construction Requirements, of these Special Provisions.

Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer.

643-3.10 LIGHTING FOR NIGHT WORK. Illuminate the night work areas according to Table 643-4.

Table 643-4 does not provide a comprehensive list of operations that require lighting. Provide lighting for other operations when necessary.

Use balloon lighting as the main light sources. Do not use floodlights without prior approval by the Engineer. When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway. Locate, aim, louver, and/or shield light sources to reduce glare.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences. When notified of unacceptable glare, modify the lighting system to reduce glare to an acceptable level.

### TABLE 643-4

NIGHT WORK ILLUMINATION EQUIPMENT AND LOCATION REQUIREMENTS

| Type of Work or Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation. | At least one machine-mounted balloon light of at least 2000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping. | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging. | One balloon light of at least 2000 watts, located within 30 feet of the flagger location. Locate so the flagger and the flagging location are illuminated. Provide additional lights or wattage if necessary to provide complete coverage of the flagging location. |
| Truck Crossings where haul vehicles cross or enter a road with more than 10,000 ADT, or where the haul vehicle crossing or entering location is controlled by portable traffic signals or flaggers. | At least one balloon light of at least 2000 watts, located on the main road on the far right side of the intersection. Locate light within 30 feet of the edge of the side street. If there is a flagger at the crossing, locate the lights or lights so the lighting requirements for Flagging are also satisfied. |

If the Contractor fails to provide required lighting equipment or provides lighting that creates unacceptable glare, the Contractor shall cease all construction activities that require illumination, including flagging operations, until the condition or conditions are corrected.

Use lighting equipment in good operating condition and that complies with applicable state and local adopted codes and standards, and OSHA, NEC, and NEMA requirements.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment. Design mountings so lights can be aimed and positioned as necessary to reduce glare. Locate mounting brackets and fixtures so they don’t interfere with the equipment operator or overhead structures. Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment-mounted light towers or poles are sturdy and freestanding without the aid of guy wires. Towers shall be capable of being moved as necessary to keep pace with the construction operation. Position the ground and trailer-mounted towers and trailers, to minimize the risk of being impacted by traffic on the roadway, or by construction traffic, or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as overhead signals, overhead signs, trees, aerial utilities, or bridges. Aim and adjust lights to provide the required light levels. Provide uniform illumination on the hopper, auger, and screed areas of pavers. Illuminate the operator’s controls on all machines uniformly.

Furnish each side of non-street legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction. Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights may supplement but do not relieve the Contract requirement to provide lighting for night work, according to the requirements of Table 643-4.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that all required lights operate continuously during nighttime operations. Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours. In the event of any failure of the lighting system, discontinue the operation that requires illumination until the required level and quality of illumination is restored.

Maintain a supply of at least twenty emergency flares for use in the event of emergency or unanticipated situations. Comply with local noise ordinances.

Install all post-mounted electroliers located within the clear zone, on NCHRP 350 or MASH compliant breakaway bases.

643-3.11 HIGH VISIBILITY GARMENTS. Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

- Standards. Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

- Labeling. Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004 or ANSI/ISEA 107-2010.

- Tops. Wear high visibility vests, jackets, or coverall tops at all times.

- Bottoms. Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise). Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottom at all times.

- Outer Raingear. Wear raingear tops and bottoms conforming to the requirements of this Subsection 643-3.11.

- Exceptions. When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

- Condition. Furnish and maintain all vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition. Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic contract items.

643-4.01 METHOD OF MEASUREMENT. Section 109 and as follows: Quantities will not be measured during winter suspension of work.

- Traffic Maintenance. Calendar Day: Every day shown on the calendar, beginning and ending at midnight. Measurement begins on the day following receipt of the Notice to Proceed or on the first day of work at the project site, whichever is later, and ends on the date of project completion.

- Traffic Control Device Items. By the number of units of each bid item shown on the bid schedule (or the Traffic Control Rate Schedule, if item 643.0025.  , Traffic Control, is included) that are installed, accepted, and operational. Incomplete or unsatisfactory devices will not be measured. Special Construction Signs are measured by the total area of legend-bearing sign panel, as determined under Subsection 615-4.01. Compensation for a 24-hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-5. Items measured by the day are for each item per 24-hour period.

- Traffic Maintenance Setup Items. By each lane closure or one-lane road in place per hour. By each detour or road closure in place per 24-hour period.

- Portable Concrete Barrier. By each nominal 12.5-foot section placed according to the approved TCPs, for the initial placement and for each subsequent relocation when moved more than 10 feet in any direction. Each transition piece (sloping end) will be measured as a single section.

- Temporary Crash Cushion. By each acceptable installation.

- Interim Pavement Marking. By the single-stripe station. A single stripe is a marking or a temporary raised pavement marker 4 inches wide. Wider striping is measured in multiples of 4 inches. Centerline gaps are not deducted from measurements.

- Flagging and Pilot Car. By the number of approved hours, supported by certified payroll.

- Street Sweeping. By the number of operated hours, supported by certified payroll and approved by the Engineer.

- Watering. By the 1,000 gallons (M-Gallon) of water applied. The Engineer may specify measurement by weight or volume. If by weight, convert to gallons at 8.34 pounds per gallon. If by volume, convert to gallons at 7.48 gallons per cubic foot.

- Traffic Price Adjustment. By each minute that any lane of traffic is not open to full use by the traveling public, measured to the nearest minute. The Engineer will determine whether the roadway is opened to full use.

- Traffic Control. By the units specified in the Special Provisions.

- Portable Changeable Message Board Sign. By the 24-hour period for each sign, as shown on an approved TCP and displaying an approved message.

- Plastic Safety Fence. By the linear foot, as placed, to protect or channelize pedestrian traffic as shown on an approved TCP. Any adjustment in configuration of the fence at the same location that does not result in an increased amount of fence is not measured. Opening and closing the fence to gain access to and from the worksite is not measured.

- Temporary Sidewalk Surfacing. By the square yard as shown on an approved TCP.

- Temporary Guardrail. By the linear foot, including end treatments, as shown on an approved TCP.

- Portable Steel Barrier. By the linear foot placed according to the manufacturer’s recommendation and approved TCPs, for the initial placement, and for each subsequent relocation when moved more than 10 feet in any direction.

- Hotline Road Report. No measurement required to provide a 24-hour toll free (1-800 ###-####) “Hotline Road Report” telephone with a prerecorded message, and weekly notices with daily updates. Work will be subsidiary to Pay Item 643.0001.   or 643.0002.   , Traffic Maintenance.

### 643-5.01 BASIS OF PAYMENT.

- Traffic Maintenance. The contract price includes all resources required to provide the Worksite Traffic Supervisor, all required TCPs and public notices, the Construction Phasing Plan, and the maintenance of all roadways, approaches, crossings, intersections and pedestrian and bicycle facilities, as required. This item also includes any Traffic Control Devices required but not shown on the bid schedule.

Items required by the Contract that are not listed on the bid schedule or not included in other items are subsidiary to Item 643.0001.	or 643.0002.	Traffic Maintenance, except the following:

  - Traffic Price Adjustment

  - Traffic Maintenance Setup

- Traffic Control Device Items. The contract price includes all resources required to provide, install, maintain, move, and remove the specified devices. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

- Traffic Maintenance Setup Items. Each setup consists of all traffic control devices, flaggers, pilot cars, and subsidiary items necessary to implement the TCP shown on the Plans. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

Construction and obliteration of temporary roadways, when required on the Plans or approved TCP under a traffic maintenance setup item, is paid for under their respective roadway pay items.

When topsoil or seeding is required for detours, payment will be made under Sections 620 and/or 618.

- Portable Concrete Barrier. The contract price includes all resources required to provide, install, maintain, and remove each barrier section.

- Temporary Crash Cushion. The contract price includes all resources required to provide, install, maintain, repair, and remove each crash cushion.

- Interim Pavement Marking. The contract price includes all resources required to provide, install, maintain, and remove the specified markings. Installation of word and symbol markings are subsidiary. The No-Passing Zone signing, described in Subsection 643-3.04, is subsidiary.

- Flagging and Pilot Car. The contract price includes all required labor, vehicles, radios, flagger paddles and pilot car signs, and transportation to and from the worksite.

The Engineer will pay for Item 643.0032.    Flagging on a contingent sum basis at the rate of

$69.00/hour. The Engineer does not require a change order/directive for the flagging Pay Item. Flagging associated with Change Order work paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

- Street Sweeping. The contract price includes all resources required to keep the roadway free of loose material.

- Watering. The contract price includes all resources required to provide watering, as directed.

- Traffic Price Adjustment. If Item 643.0023.  , Traffic Price Adjustment, is shown on the bid schedule, the total value of this contract will be adjusted, for unauthorized lane reductions or closures, at the rates listed in Table 643-3.

- Traffic Control. Payment for Item 643.0025.  , Traffic Control, will be made at the unit rate value contained in the Traffic Control Rate Schedule shown in the Special Provisions for the accepted units of traffic control devices. The Engineer does not require a change order/directive for Pay Item 643.0025.  , Traffic Control.

- Portable Changeable Message Board Sign. The contract price includes all resources required to furnish, move, and operate the sign.

Two Portable Changeable Message Board Signs used for Permanent Construction Signing paid for under Item 643.0003.   Permanent Construction Signs. Additional portable changeable message board signs will be paid for under 643.0025.   , Traffic Control.

- Plastic Safety Fence. The contract price includes all resources required to install, maintain, and remove the fence.

- Temporary Sidewalk Surfacing. The contract price includes all resources required to construct, maintain, and remove the surfacing.

- Temporary Guardrail. The contract price includes all resources required to construct, maintain, and remove the guardrail.

- Portable Steel Barrier. The contract price includes all resources required to provide, install, maintain, move, and remove each barrier.

- Lighting for Night Work. Payment for illuminating night work areas and any required adjustments to work zone illumination is subsidiary to other items.

- Pavement Breaks. Temporary hot mix asphalt at pavement breaks, as noted in Subsection 643-

3.02.2. Gravel Surface Not Specified is subsidiary to Pay Item 401.0001.	.

- Temporary Pavement Markings. Except where specified as an individual Pay Item (Interim Pavement Markings) temporary pavement markings are subsidiary to Section 670 Pay Items. Refer to Section 670 Traffic Markings, for further information.

- Temporary Crash Cushion / Redirective. The price listed in the Traffic Control Rate Schedule, Table 643-5, will be full compensation for the purchase, installation, maintenance during construction, removal, and salvaging the Temporary Crash Cushion / Redirective unit(s). Deliver the salvaged unit(s) to the nearest ADOT & PF Maintenance & Operations Station or as directed by the Engineer.

Traffic control devices, barriers, and crash cushions required to delineate or shield fixed objects will not be measured or paid for separately, but will be subsidiary

Traffic control devices, barriers, and crash cushions required to delineate or shield guardrail posts or non-crashworthy ends will not be measured or paid for separately, but will be subsidiary, when required for failure to meet completion timelines in subsection 606-3.01.

### TABLE 643-5

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $31.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Sequential Arrow Panel | Each/Day | $40.00 |
| Portable Concrete or Steel F Shape Barrier (12.5 foot long or $8/foot for other lengths) | Each | $100.00 |
| Temporary Crash Cushion / Non-redirective Water Filled Barrier (all required per end) | Each | $2500.00 |
| Temporary Crash Cushion / Non-redirective Water Filled Barrels (all required per end) | Each | $3285.00 |
| Temporary Crash Cushion / Non-redirective Sand Filled Barrels (all required per end) | Each | $4325.00 |
| Temporary Crash Cushion / Redirective | Each | $9230.00 |
| Pilot Car (4x2, 1/2 ton truck) | Hour | $83.00 |
| Watering Truck – up to 4900 gallon capacity | M-Gallon | $28.00 |
| Watering Truck – more than 4900 gallon | M-Gallon | $21.00 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical or Power Broom with Vacuum | Hour | $214.00 |
| 40,000 GVW Truck with Crash Attenuator | Hour | $162.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Portable Changeable Message Board Sign | Calendar Day | $130.00 |
| Temporary Sidewalk Surfacing | Square Foot | $2.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |
| Temporary Guardrail | Lineal Foot | $25.00 |

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 643.0001. | Traffic Maintenance | CDAY |
| 643.0002. | Traffic Maintenance | LS |
| 643.0003. | Permanent Construction Signs | LS |
| 643.0004. | Construction Sign | Day |
| 643.0005. | Type II Barricade | Day |
| 643.0006. | Type III barricade | Day |
| 643.0007. | Traffic Cone/Tubular Marker | Day |
| 643.0008. | Plastic Safety Fence | LF |
| 643.0009. | Drum | Day |
| 643.0010. | Sequential Arrow Panel, Type C | Day |
| 643.0011. | Special Construction Signs | SF |
| 643.0012. | Portable Concrete Barrier | Each |
| 643.0013. | Temporary Crash Cushion | Each |
| 643.0014. | Interim Pavement Marking | STA |
| 643.0015. | Flagging | HR |
| 643.0016. | Pilot Car | HR |
| 643.0017. | Street Sweeping | HR |
| 643.0018. | Watering | MGAL |
| 643.0019. | Lane Closure | HR |
| 643.0020. | Detour | Day |
| 643.0021. | Road Closure | Day |
| 643.0022. | One Lane Road | HR |
| 643.0023. | Traffic Price Adjustment | CS |
| 643.0024. | Portable Changeable Message Board Sign | Day |
| 643.0025. | Traffic Control | CS |
| 643.0026. | Temporary Sidewalk Surfacing | SY |
| 643.0027. | Temporary Guardrail | LF |
| 643.0030. | Portable Steel Barrier | LF |
| 643.0031. | Interim Pavement Marking | LS |
| 643.0032. | Flagging | CS |
| 643.0033. | Detour | LS |

CR643-010122/CFHWY01060

### SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

Replace Subsection 644-2.01 with the following:

644-2.01 FIELD OFFICE. Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15. The following office requirements shall be met:

- A minimum of 1000 square feet of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 160 square feet of floor area.

- A thermostatically controlled interior heating system with necessary fuel.

- Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

- A minimum of 100 square feet of window area and adequate ventilation.

- Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

- Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

- Provide engineering communication services to the field office, Subsection 644-2.08.

- If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

- Located within 3 miles of the project.

- Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

- Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

- Provide a security system controlled by the Department for the office including camera coverage for the vehicle parking.

#### CR644.FOCOM-080120

Replace Subsection 644-2.02 with the following:

644-2.02 FIELD LABORATORY. Maintain the existing field laboratory, engineering communications, and security system located on “Tract C” for the Engineer to use exclusively throughout the contract.

CFHWY01060

### 644-2.05 VEHICLES.

Replace the second and third paragraphs with the following:

Pickup(LT)/Sport Utility Vehicle (SUV): Furnish full-size, four-wheel drive vehicles, either pickup/light truck(s) with crew cabs or sport utility vehicle(s). Provide vehicles less than three model years old, in good condition, and with less than 36,000 miles on the odometer. Furnish all fuels, maintenance and parts, and insurance during the Department’s operation and use.

Equip each vehicle with lightbars wired into the vehicle’s electrical system with a dash mounted switch easily accessible to the vehicle operator. Provide Code 3; Reflex C5590AA 15.3-inch mini lightbar, or approved equal. Approved equal equipment shall have the following characteristics:

- (4) 55 watt rotators with amber filters

- 1200 flashes per minute

- (2) diamond mirrors

- 55 inches in length

Equip each vehicle with hands-free communication connectivity.

If you are working after October 1, provide four studded snow tires mounted on each vehicle.

You are responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use. The State of Alaska is responsible for damage to any vehicle caused by its own negligent operation.

#### CR644.LTSUV-113020

Replace Subsections 644-2.02 and 2.03 with the following:

644-2.06 NUCLEAR TESTING EQUIPMENT STORAGE SHED. Maintain the existing nuclear densometer/testing equipment storage shed located on “Tract C” for the Engineer to use exclusively throughout the contract.

644-2.07 STORAGE CONTAINER. Maintain the existing storage container located on “Tract C” for the Engineer to use exclusively throughout the contract.

#### CFHWY01060

Add the following Subsection 644-2.08 Engineering Communication and Office Equipment:

644-2.08 ENGINEERING COMMUNICATION AND OFFICE EQUIPMENT. Engineering Communications and Office Equipment, minimum service includes:

- Three phone/facsimile lines and commercial phones (different phone numbers for each line)

  - One phone with built-in digital answering machine.

  - Ancillary equipment for operational service and as required by the Engineer.

- High speed internet service with modem (DSL, Cable or Starlink)

  - Send and receive capability supporting 10.0 Mbps download and upload speed or higher at all times.

  - Data usage, 10 GB minimum monthly.

  - Wireless router.

  - Battery backup.

  - Ancillary equipment for operational service and as required by the Engineer.

- Equipment rental services

  - All-in-one printer/copier/scanner

    - Black-white and color

    - Pages per minute (ppm): 50

    - Paper trays: 8.5" x 11" and 11" x 17"

    - Capacity: 1100 sheets minimum CR644.FOCOM-080120/CFHWY01060

### 644-4.01 METHOD OF MEASUREMENT.

Replace the third paragraph with following:

Vehicle (LT/SUV). For each vehicle provided. If a replacement vehicle is necessary, no additional measurement will be made.

Replace the fourth paragraph with following:

Nuclear Testing Equipment Storage Shed. By the number of storage sheds specified to be maintained for the duration of the contract.

Replace the fifth paragraph with following:

Storage Container. By the number of storage containers specified to be maintained for the duration of the contract.

CR644.LTSUV-113020/CFHWY01060

### 644-5.01 BASIS OF PAYMENT.

Add the following:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 644.0002. | Field Laboratory | Contingent Sum |
| 644.0003. | Curing Shed | Contingent Sum |

Replace the seventh paragraph with following:

Nuclear Testing Equipment Storage Shed. Includes all labor, materials, tools, equipment and supplies required to maintain it for the duration of the Contract. Electrical service and utility costs are subsidiary to this item.

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 644.2010. | Nuclear Testing Equipment Storage Shed | Contingent Sum |

Replace the eighth paragraph with following:

Storage Container. At the contingent sum price to include all labor, materials, tools, equipment and supplies required to maintain it for the duration of the Contract. Electrical service and utility costs are subsidiary to this item.

#### CFHWY01060

Add the following:

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Pay Item 644.0002.	Field Laboratory.

#### CR644.LAB-080120/CFHWY01060

Add the following:

Pay Item 644.2007.	Vehicle (LT/SUV):

- A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

- The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site. If anticipated construction period changes, the final increment will be held until final payment.

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 644.2007. | Vehicle (LT/SUV) | Each |

#### CR644.LTSUV-113020/CFHWY01060

Add the following:

Pay Item 644.2004.	Engineering Communications:

Usage services including long distance calls made by State personnel and the Internet service provider will be reimbursed by the State. Payment for communication usage services and equipment rental agreements shall be based on paid receipts to the service provider plus 15%.

Connection fees (initial connection) local calls, providing equipment and disconnection are subsidiary to Pay Item 644.0001.   Field Office and as such are paid by the Contractor.

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 644.2004. | Engineering Communications | CS |

#### CR644.FOCOM-080120/CFHWY01060

Pay Item 644.2011.0000 Field Office. Measured on a contingent sum basis to cover all field office activities on Tract C and as approved and determined by the Department. Prices for this item will be by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor.

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 644.2011.0000 | Field Office | CS |

#### CFHWY01060

Special Provision

Add the following Section:

### SECTION 645 TRAINING PROGRAM

645-1.01 DESCRIPTION. This Statewide Special Provision for on-the-job training (OJT) implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 OBJECTIVE. Training and upgrading of minorities and women toward journey status is the primary objective of this program. The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision. Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301.

645-3.01 GENERAL. The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive. Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Office of Apprenticeship (USDOL/OA); or one developed by the Contractor using Form 25A-310 and approved prior to contract award by the OJT Coordinator in the DOT&PF Civil Rights Office.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor. Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed. It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project. Existing USDOL/OA apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. The Contractor must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 WAGES. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period. Trainee wages shall be identified on Form 25A-310. Apprentices in USDOL/OA training programs shall be paid in accordance with their approved program. Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 SUBCONTRACTS. In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor. Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate. However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non- compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 METHOD OF MEASUREMENT. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls. There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section. Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 BASIS OF PAYMENT. Payment will be made at the contract unit price for each hour of training credited. Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311 may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project. No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

- provide the required hours of training (as shown in the Bid Schedule and approved Form 25A-311),

- train the required number of trainees/apprentices in each training program (as shown in the Bid Schedule and approved Form 25A-311), or

- hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry. Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program. Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits. The journey worker scale is that for the classification identified in the approved programs.

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 645.0001. | Training Program, Trainees/Apprentices | LH |

HSP20.2-113020

### SECTION 646 CPM SCHEDULING

Special Provisions

Replace Subsection 646-2.01 with the following:

### 646-2.01 SUBMITTAL OF SCHEDULE.

Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time. Allow the Engineer 14 days to review the initial CPM Schedule. Revise promptly. The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

### 646-3.01 REQUIREMENTS AND USE OF SCHEDULE.

Replace the first sentence of No. 2 Schedule Updates. with the following:

Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule. Meet with the Engineer monthly or as deemed necessary by the Engineer.

#### CR646.1-23.0501

Special Provisions

Add the following Section:

### SECTION 647 EQUIPMENT RENTAL

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled, and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, except holidays.

Section 647

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer. Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. Section 109.

Hourly Rental Rate: Includes the equipment rate plus the operating costs including: furnishing, travel time, operating, maintaining/servicing and repairing the equipment along with the costs incidental to the equipment and its' operation.

647-5.01 BASIS OF PAYMENT. Payment is for the time that fully operational equipment is engaged in the performance of the work directed by the Engineer. Time not payed for includes: idle periods, maintaining/servicing and repairing the equipment, making change-overs of equipment parts, and time to travel to and from the project. Payment will only be for time supported by certified payroll.

Furnishing and operating equipment that is heavier, has larger capacity, or greater power than specified will not entitle the Contractor to extra compensation.

Pay Item 647.2000.   Wide Pad Dozer, 65-HP Minimum: paid at the rate of $200/hour.

Pay Item 647.2002.	 Backhoe, 4WD, 1 CY Bucket, 75-HP Minimum, 15 ft Depth: paid at the rate of

$170/hour.

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 647.2000. | Wide Pad Dozer, 65-HP Minimum | CS |
| 647.2002. | Backhoe, 4WD, 1 CY Bucket, 75-HP Minimum, 15 ft Depth | CS |

#### CR647-110316R

Special Provision

Add the following Section:

### SECTION 654 MONITOR

654-1.01 DESCRIPTION. Provide qualified personnel to monitor archeological findings and document construction activities in the specified locations.

When authorized by directive, engage a Professional Service Contractor to monitor eagle(s) at their nests and any additional bird monitoring required to comply with Section 107.

### 654-1.02 SUBMITTAL.

- Eagle Monitoring Plan and documentation as required by the monitoring plan.

- Professional Service Contractor resume(s).

654-1.03 QUALIFICATIONS. Each position is required to be an employee of the Professional Service Contractor.

Professional Service Contract Manager.

- Bachelor of Science degree in biology, environmental science, or ecology and working in the field of the degree, or

- Two years of experience monitoring or studying the habitat of birds of prey.

Monitor.

- Professional Service Contract Manager or a person trained and supervised by the Professional Service Contract Manager or other similarly qualified representative.

### 654-2.01 MATERIALS.

Video Camera	Optical zoom lens, minimum 10 power

### 654-3.01 GENERAL REQUIREMENTS.

Bird Monitor. Before beginning construction activity in the restricted area(s) specified in the directive, submit and receive approval for the following:

- The qualifications of the Professional Service Contract Manager and Monitor.

- An Eagle Monitoring Plan prepared by the Professional Service Contract Manager coordinated with the Contractors' Work Plan for work in the restricted area or any timing restricted period.

During Construction, submit and receive approval for the following:

- Eagle monitoring documentation, reports, forms, video as required by the approved Eagle Monitoring Plan and included in the authorizing directive.

Refer to Section 107-1.11 Eagles for further information

Archeological Monitor. The Contractor shall provide a Secretary of the Interior (SOI) qualified Professional Archaeological Monitor (36 CFR 61, Appendix A) who will be on site to observe clearing, grubbing, and all other earth disturbing activities. The Department will coordinate Tribal Monitors from Kenaitze Indian Tribe (KIT) and Cook Inlet Region, Inc (CIRI) or their designated representative who are authorized to participate in the archaeological construction monitoring. The Contractor will provide the Department two weeks’ written notice before monitoring activities are scheduled to begin.

Archaeological construction monitoring will involve the close inspection of excavations and other ground- disturbing activities within the Project construction footprint. Monitoring will follow excavations and construction as closely as conditions require, making all reasonable efforts for safety and noninterference with construction. The DOT&PF Professionally Qualified Individual (PQI / Central Region Cultural Resources Specialist) shall coordinate with the Project Engineer to ensure that an appropriate Supervisory Archaeological Monitor is provided and/or contracted prior to the beginning of construction. More than one (1) Archaeological Monitor may be required, depending on how much activity occurs simultaneously. The Supervisory Archaeological Monitor will determine the number and placement of Archaeological Monitors after consultation with the PQI and Project Engineer. Monitoring will continue until the Supervisory Archaeological Monitor has determined that excavation of the identified sensitive areas has reached the maximum depth at which cultural deposits can be expected.

Prior to Construction:

- Development of Cultural Resources Sensitivity Area Maps

  - DOT&PF shall develop and distribute maps exhibiting areas that may contain or have high sensitivity for cultural resources in Project ground-disturbance locations.

  - Signatories and Monitors will have sixty (60) days to provide comments on the archaeological sensitivity area maps

  - DOT&PF will provide Archaeological and Tribal Monitors with final cultural resources sensitivity area data prior to monitoring activities

- Acquire Permits for Archaeological Monitoring

- Pre-construction Meeting and Cultural Resources Awareness Training

  - DOT&PF will conduct a preconstruction meeting that includes the DOT&PF project engineer, Contractor, any on-site construction supervisory staff, resident engineer, and Supervisory Archaeological Monitor to discuss the requirements of the Programmatic Agreement with the Signatories.

  - DOT&PF will provide electronic and written notice of the meeting to the Signatories at least fifteen (15) working days prior to the meeting.

  - DOT&PF shall provide advance written and electronic notice of the construction schedule. The first notice shall occur when the construction phase is approved in the Statewide Transportation Improvement Plan (STIP). The second notice shall occur within a minimum of ninety (90) days before construction begins.

  - The Archaeological Monitor will conduct on-site cultural resource awareness training with construction personnel.

    - The training will provide guidance regarding the recognition of archaeological material and identify procedures for notifying supervisory personnel in the event suspicious or sensitive materials are encountered.

    - Construction personnel will be shown examples of the types of sites, artifacts, and features that might be encountered in the Project area

    - training will also include a discussion of pertinent federal, State, and local laws.

- Historic Property Protection Measures

  - Avoid historic properties when possible during Project activities.

  - Prior to construction, the Archaeological Monitors will flag or guide the placement of construction fencing around historic properties as “avoidance areas” for construction personnel. No construction activities may occur in these areas. No one shall remove the flagging material and/or construction fencing from the “avoidance areas” until construction activities at the location are complete.

  - Flagging material and/or construction fencing will be removed only by or under the guidance of the Supervisory Archaeological Monitor.

  - The Supervisory Archaeological Monitor or PQI may employ other means at his or her discretion to avoid and minimize adverse effects to historic properties.

Archaeological Construction Monitoring Responsibilities:

- The Contractor will notify DOT&PF 14 days ahead of working in a culturally sensitive area.

- During construction, at least one (1) SOI-qualified Archaeological Monitor and Tribal Monitors shall be on the Project site while all ground-disturbing activities are occurring. Following completion of the ground-disturbing activities, the Archaeological Monitor and Tribal Monitor

shall conduct a final site check for any inadvertently discovered or affected historic properties and human remains.

- Archaeological Monitors and Tribal Monitors have “stop-work” authority in accordance with the PA.

- The Supervisory Archaeological Monitor shall take appropriate action to protect archaeological deposits and potentially eligible historic properties.

- The Archaeological Monitor(s) shall remain on-site in the delineated areas unless the Supervising Archaeological Monitor determines that monitoring is not necessary in a particular location.

- The Archaeological and Tribal Monitor(s) shall maintain daily logs documenting construction and ground-disturbing activities; communications with construction personnel, descriptions and provenience of any inadvertent discoveries or artifacts collected; historic properties inadvertently affected; and other pertinent information. If the Supervisory Archaeological Monitor and Tribal Monitor(s) disagree regarding the potential for inadvertent adverse effects to historic properties and human remains, construction activities shall stop, and consultation with the Signatories shall occur immediately.

- If a previously unidentified cultural resource is encountered during construction activities, or a historic property is affected in an unanticipated manner, the Archaeological Monitor(s), Tribal Monitors, and construction personnel shall follow the procedures and protocols outlined in PA Stipulation VII, Inadvertent Discoveries and Unanticipated Effects, and Appendix G, Cultural Resources Discovery Plan.

- If human remains/cremains are inadvertently discovered or affected during monitoring or any construction activities, the Archaeological Monitor(s), Tribal Monitors, and construction personnel shall follow the procedures and protocols outlined in PA Stipulation VI, Treatment of Human Remains, and Appendix F, Human Remains Protocol.

- In the event that a previously unidentified cultural resource is inadvertently discovered during Project activities, archaeological construction monitoring will occur within a two-hundred (200)-foot buffer of the discovery boundary once the resource has been fully documented.

- Construction activities may continue elsewhere in the Project area. Construction personnel and subcontractors may conduct no further work at the discovery site until the DOT&PF Project Engineer, in consultation with the Supervising Archaeological Monitor, Tribal Monitors and Signatories, provides authorization to resume Project construction activities. Vehicles, equipment, and unauthorized personnel shall not to traverse the discovery site.

### 654-3.02 REPORTING.

- Weekly Monitoring Memos. The Supervising Archaeological Monitor and Tribal Monitors shall provide a summary construction monitoring memorandum on a weekly basis to the DOT&PF Project Engineer and the PQI. The PQI shall submit an electronic copy of the memo to the PA Signatories within two (2) days of its receipt for their ongoing information.

- Summary Monitoring Report. When the construction monitoring is complete, the Supervisory Archaeological Monitor, with input from the Tribal Monitors, shall provide to the Project Engineer and PQI a draft monitoring report summarizing the construction monitoring activities within ninety

(90) days.

- The report is to meet contemporary professional standards and the SOI Standards and Guidelines for Archaeological Documentation (48 FR 44734–44737).

- The PQI shall provide the draft monitoring report to the PA Signatories for review and comment.

- Signatories shall have ninety (90) days to review and provide comments on the draft monitoring report to DOT&PF.

- DOT&PF shall address comments received during the review period, and will submit a final report to the Signatories within one (1) year after completion of all archaeological construction monitoring and prior to the conclusion of this PA.

- If construction monitoring occurs over several years, the Supervisory Archaeological Monitor shall provide to the Project Engineer and PQI annual monitoring reports and one

(1) final report summarizing the annual reports following the timeframes provided in this section.

654-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Monitor, Bird. Contingent sum work will be measured in accordance with the directive authorizing the work required for monitoring and reporting.

Monitor, Archaeological.	Contingent sum work will be measured in accordance with the directive authorizing the work required for monitoring and reporting.

654-5.01 BASIS OF PAYMENT. Monitoring will be paid according to Subsection 109-1.05. Payment will be made under:

| PAY ITEM |  |  |
| --- | --- | --- |
| Item Number | Item Description | Unit |
| 654.2004. | Monitor, Archaeological | CS |
| 654.2004. | Monitor, Bird | CS |

CFHWY01060

# DIVISION 700 — MATERIALS

Division 700

## Blank Page

Replace 1. Type A with the following:

1. Type A. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by ATM 204 and ATM 205. Meet the following gradation as tested by ATM 304:

Sieve	Percent Passing by Weight

No. 4	20-55%

No. 200	0-6%, determined on the minus 3-inch portion of the sample

703-2.13 STRUCTURAL FILL. Replace Table 703-12 with the following:

### TABLE 703-12

AGGREGATE GRADATION FOR STRUCTURAL FILL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3-inch | 100 |
| 3/4-inch | 75-100 |
| No. 4 | 20-55 |
| No. 200 | 0-6 |

#### CR703.1-050122/CFHWY01060

Add the following:

9. Corrosion-Resistant Reinforcing Steel (Low Carbon Chromium). Furnish deformed reinforcing bars of the type, grade and size as specified. For steel reinforcing bars used in bridge structures, use bars meeting ASTM A1035 CM Grade 100.

#### CFHWY01060

716-2.02 GENERAL REQUIREMENTS. Add the following:

7.	Permanent Metal Deck Forms.	ASTM A653 and ASTM A924

716-2.03 FASTENERS. Replace item 1 with the following:

1.	High Strength Bolts	ASTM F3125, Grade A325 or F1852, or Grade A490 or F2280 as shown on the plans

Replace item 4 with the following:

- Zinc Coated Load Indicating Washers	ASTM F959, Type 490

716-2.07 GALVANIZING. Add the following to the first paragraph:

For hot dip galvanized steel, the silicon content shall be in the range of 0.00 percent to 0.06 percent or in the range of 0.13 percent to 0.25 percent. Submit mill test certificates verifying silicon content to the Engineer and the galvanizer before galvanizing steel.

Replace the 5th and 6th paragraphs with the following:

In lieu of hot-dip galvanizing, steel bridge members may be spray-metalized. Apply between 10 mils and

15 mils of zinc galvanizing by the spray-metalizing process according to Steel Structures Painting Council’s coating system guide SSPC-CS 23.00. Prepare surfaces before galvanizing according to Steel Structures Painting Council's surface preparation guide SSPC-SP 5/NACE No. 1, White Metal Blast Cleaning. Provide Class B surface conditions on all elements per the AASHTO LRFD Bridge Design Specifications at bolted splice locations and at pier and abutment cross frame locations.

Repair damaged coatings according to ASTM A780 Annex A1 or Annex A3, except as modified herein. Clean the damaged area according to SSPC-SP 3, Power Tool Cleaning for repairs meeting Annex A1 and SSPC-SP 5/NACE No. 1, White Metal Blast Cleaning for repairs meeting Annex A3. Extend the cleaned area 1/2 inch to 3/4 inch into the undamaged section of the coating. Keep the cleaned area dry and free of rust and soiling. Within 24 hours of cleaning, coat the cleaned section with zinc to a thickness of not less than 10 mils when using the method in Annex A3 and not less than 3 mils when using the method in Annex A1. Taper the thickness of the repair coating to match the original coating thickness at the edges of the cleaned section. Apply two coats of zinc rich paint containing a minimum of 65% zinc dust following repairs made in accordance with Annex A1. Where repairs are made in accordance with Annex A3, use zinc wire containing not less than 99.98 percent zinc.

#### CFHWY01060

720-2.01 ELASTOMERIC BEARING PADS. Remove Item 1 and replace with the following:

Elastomeric bearing pads include plain pads, consisting of elastomer only, and laminated pads with steel laminates.

1. General. Meet AASHTO M 251, with the following revisions:

### Properties of the Elastomer

Delete the first sentence and replace with the following: Use elastomeric compound in the construction of the bearings containing only virgin natural polyisoprene (natural rubber) as the raw polymer. Do not use neoprene. Properties and requirements elsewhere in AASHTO M 251 pertaining solely to polychloroprene (neoprene) do not apply.

Add the following:

Use elastomer compound classified as low temperature Grade 5 and meeting the requirements of paragraph 8.9.1.

### FABRICATION

Add the following paragraph:

5.5. Fabricate pads over 3/4 inch thick with alternating laminations of elastomer and metal or fabric reinforcements. The outside laminations must be metal or fabric with a minimum elastomer cover as shown on the Plans.

### Table 2 – Tolerances.

Delete Item 6 and replace with the following:

- Top, bottom, and edge cover of embedded laminates or connection members -1/32 inch, +1/8 inch.

720-2.03 POLYTETRAFLUOROETHYLENE (PTFE) BEARINGS. Replace item 1 with the following:

- Materials.

Elastomeric Bearing Pads	Subsection 720-2.01

Stainless Steel Plates	ASTM A240, Type 304 or Type 316 Steel Plates	ASTM A709, Grade 50

Use PTFE from virgin material (not reprocessed) meeting the requirements of ASTM D4894 or D4895, and Table 720-1.

#### CFHWY01060

Special Provision

Replace Section 727 with the following:

### SECTION 727

SOIL STABILIZATION MATERIAL

727-2.00 GENERAL. Free of restricted and prohibited noxious weeds (11 AAC 34), seeds, chemical printing ink, germination and growth inhibitors, herbicide residue, chlorine bleach, (except where specified: rock, metal, plastics) and other deleterious materials and not harmful to plants, animals and aquatic life. Wood cellulose "paper" fiber, wood chips, sawdust, and hay are not permitted as stand-alone stabilization materials.

727-2.01 MULCH. Flexible blanket/covering, temporary degradable (bio/photo) form of erosion control. Use one of the following:

Dry Erosion Control, Stabilization Products. Hand applied or spread with mulch blower equipment.

- Straw. Use straw, in an air-dried condition, from oats, wheat, rye, barley, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life. Straw material shall be certified weed-free straw using North American Invasive Species Management Association (NAISMA) Standards. In-lieu of certified weed-free straw provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

- Shredded Bark Mulch. Shredded bark and wood with the following characteristics:

  - Not containing resin, tannin, or other compounds in quantities harmful to plant life.

  - Maximum length of individual pieces is 2 inches with 75% passing through a 1 inch sieve.

  - Will form a uniform ground cover/mat, have moisture absorption, retention, and percolation properties, not be susceptible to spreading by wind or rain providing a good growth medium.

  - May contain up to 50% shredded wood material.

  - Shredded wood material aged 1 year minimum prior to use.

Hydraulic Erosion Control Products (HECPs) Applied hydraulically.

A fiber mulch matrix: biodegradable and composed of wood, straw, coconut and other fibers natural and man-made. When applied, create a continuous, porous, absorbent high water holding, flexible blanket/mat/mulch/covering making intimate contact with, and adhering to sloped soil surface; permitting water infiltration; resists erosion and promotes rapid germination and accelerated plant growth. The fibers may be thermally processed, and cross-linked with a hydro-colloidal or linear anionic tackifier (curing period 24-48 hours) or mechanically-bonded (no curing period). When agitated in slurry tanks with water the fibers will become uniformly suspended, without clumping to form homogeneous slurry.

The HECPs shall be delivered premixed by the manufacturer. The HECP will contain only the materials provided in the sealed containers from the manufacturer. No added components are permitted after the manufacturer seals the product container, before application, during application or otherwise. Submit documentation dated within 3 years of application, from an independent accredited laboratory as approved by the Engineer, showing that the product's testing performance meets the requirements for the slope(s) to be protected on the project, according to the National Transportation Product Evaluation Program (NTPEP), Erosion Control Technology Council (ECTC) and or the Texas DOT/Texas Transportation Institute (TTI) Laboratory.

If the HECP contains cotton or straw provide documentation that the material is certified weed free using NAISMA Standards. In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

The HECP shall contain a dye to facilitate placement and inspection of the material.

- Wood Strand, Fiber.

A blend of angular, loose, long thin wood pieces with a high length to width ratio and that are frayed. Minimum 95% of strands between 2 inches and 10 inches, at least 50% of the length shall have a width thickness between 1/16 and 1/8 inch. No single strand shall have a width or thickness greater than 1/2 inch. Processed wood fiber with the following characteristics:

  - Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form homogeneous slurry.

  - Will form a blotter-like uniform ground cover on application, have moisture absorption, retention and percolation properties, the ability to cover, and hold grass seed in contact with soil, and not create a hard crust upon drying providing a good growth medium.

- Dried Peat Moss.	Partially decomposed fibrous or cellular stems and leaves of any of several species of Sphagnum mosses with the following characteristics:

  - Chopped or shredded to allow distribution through normal hydraulic type seeding equipment and capable of being suspended in water to form part of a homogeneous slurry.

  - Free from woody substances and mineral matter such as sulfur or iron and with a pH value of between 4.0 and 6.5.

  - Furnished in an air dry condition and containing less than 35% moisture by weight. Have a water holding capacity of not less than 800% by weight on an oven dry basis.

- Fiber Matrix (FM) Mulch - Types.

  - Stabilized Mulch Matrices (SMMs)

  - Bonded Fiber Matrices (BFMs)

  - Mechanical Bonded Fiber Matrix (MBFM)

  - Polymer Stabilized Fiber Matrix (PSFM)

  - Fiber Reinforced Matrices (FRMs)

    - Flexible Growth Medium (FGM)

    - Extended-Term Flexible Growth Medium (ET-FGM)

727-2.02 MATTING. Fiber mulches, mulch matrices, nets and turf reinforcement mats manufactured from wood fibers, straw, jute, coir, polyolefins, PVC, nylon and others creating dimensionally stable nets, meshes, geotextiles and blankets; creating a continuous, porous, absorbent, flexible blanket/mat/mulch/covering making intimate contact with and adhering to sloped soil surface, resisting erosion and promoting rapid germination and accelerated plant growth.

Rolled Erosion Control Products (RECPs) (Temporary Degradable and Permanent Erosion Control) Use RECPs that bear the Quality and Date Oversight and Review (QDOR) Seal from the ECTC. Independent test results from the NTPEP, that the mulch, when tested according to ASTM 6459 Standard Test Method for Determination of Rolled Erosion Control Products (RECP), Performance in Protecting Hillslopes from Rainfall-Induced Erosion, meets the performance requirement using the Revised Universal Soil Loss Equation (RUSL).

Functional Longevity.

- Temporary Degradable.

  - Duration.

    - Short-Term RECPs. (RECPs 3 - 12 months) C Factor = .15 maximum

Test Soil Type = Sandy Loam

(National Resources Conservation Service (NCRS) Soil Texture Triangle)

    - Moderate (Extended) -Term RECPs. (RECPs 24 months) C Factor = .05 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

    - Long-Term RECPs. (RECPs 36 months) C Factor = .01 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

  - Product types.

    - Mulch-Control Nets (MCNs). Planar woven natural fiber or extruded geosynthetic mesh used to anchor loose fiber matting/mulches.

    - Erosion Control Blankets (ECBs). Processed natural and/or polymer fibers, yarns or twines mechanically, structurally, or chemically bound together to form a continuous matrix with a minimum weight of 8 oz/yd2 and a limiting shear stress of 0.45 lb/ft2.

    - Netless. Fibers mechanically interlocked and/or chemically adhered together.

    - Single-net and Double-net. Fibers mechanically bound together by single or double netting.

    - Open Weave Textiles (OWTs). Fibers woven into a continuous matrix.

  - Materials.

    - Burlap. Standard weave with a weight of 3.5 to 10 oz/yd2.

    - Jute Mesh Fabric. Cloth of a uniform, open, plain weave of undyed and unbleached single jute yarn. Use yarn that is loosely twisted and not varying in thickness more than one-half its normal diameter. Furnish jute mesh in rolled strips meeting the following requirements:

      - Width: 45 to 48 inches,  1 inch

      - 78 warp-ends per width of cloth (minimum)

      - 41 weft-ends per yard (minimum)

      - Weight: 20 ounces per linear yard,  5%

    - Woven Paper or Sisal Mesh Netting. Woven from twisted yarns available in rolls 45 to 48 inches wide. Mesh may vary from closed to open weave, ranging from 1/8 to 1/4 inch openings. Shrinkage after wetting may not exceed 20% of the surface area.

    - Knitted Straw Mat. Commercially manufactured ECB. Use photodegradable netting and biodegradable thread. Use straw, in an air-dried condition, from oats, wheat, rye, barley, or other approved grain crops that are certified weed free of prohibited and restricted noxious weed seed and quarantined pests, according to Alaska Administrative Code, Title 11, Chapter 34 (11 AAC 34), and in conjunction with North American Invasive Species Management Association (NAISMA) standards, and free of mold, or other objectionable materials detrimental to plant life. When straw or straw products certified according to 11 AAC 34 are not available, use non-certified products manufactured within Alaska before certified products manufactured in another state, country, or territory. Non-certified products manufactured in Alaska In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw. Non-certified straw or straw products manufactured in another state, country, or territory shall not be used. ECB may contain coconut or fiber to reinforce the straw.

    - Woven/Curled Wood blanket. Machine produced mat of curled wood shavings with a minimum of 80% 6-inch or longer fibers, with consistent thickness and the fibers evenly distributed over the entire area of the blanket. Smolder resistant without the use of chemical additives. Cover the top side of the blanket with biodegradable extruded plastic mesh.

    - Coconut (Coir Fiber). Machine produced mat, ECB of consistent thickness and coir fiber evenly distributed over the area of the mat. Use bio/photo degradable netting and thread.

- Permanent.

  - Product Types and Materials.

    - Turf Reinforcement Mats (TRMs). A rolled erosion control product composed of non- degradable synthetic fibers, filaments, nets, wire mesh, and/or other elements, processed into a permanent, three-dimensional matrix of sufficient thickness with a minimum weight of 8 oz/yd2 and a minimum limiting shear stress of 1.5 lb/ft2. TRMs (may be supplemented with degradable components) shall impart immediate erosion protection, enhance vegetation establishment during and after maturation and permanent vegetation reinforcement providing long-term functionality.

727-2.03 SEDIMENT RETENTION FIBER ROLLS (SRFRs). Fiber rolls also referred to as wattles. Manufacture of photodegradable or biodegradable fabric netting without preservative treatment, evenly woven, free of crusted material, cuts, and tears. Manufacture stakes of photodegradable or biodegradable material (wood stakes, except as approved by the Engineer).

- Filter Sock (Wattle)

  - Fabric netting.

  - Filled with wood fiber, straw, flax, rice, coconut fiber material.

  - Minimum diameter 5 inches.

- Compost Sock.

  - Extra Heavy weight fabric netting with a minimum strand width of 5 mils.

  - Filled with coarse compost.

  - Minimum diameter 8 inches.

- Coir Log.

  - Woven wrap bristle coir twine netting.

  - Filled with 100% coconut (coir) fiber uniformly compacted.

  - Segments maximum length 20 foot, diameter as suited to the application and a density of 7 lbs/pcf or greater.

  - Coir twine strength equal to 80 lb minimum weaved to a 2 inch x 2 inch opening pattern.

  - Ties made of hemp rope by 1/4 inch diameter.

727-2.04 COMPOST. Suitable for serving as a soil amendment or an erosion control material. Sanitized, mature compost meeting local, state, and Federal quality requirements tested and certified by the U.S. Composting Council (USCC) under the Seal of Testing Assurance (STA) Program. Biosolids compost must meet the Standards for Class A biosolids outlined in 40 Code of Federal Regulations (CFR) Part

503. Additionally, meet the requirements of the AASHTO specifications:

- Compost Blankets. Standard Practice for Compost for Erosion/Sediment Control (Compost Blankets) R 52.

- Compost Filter Berms and Filter Socks. Standard Practice for Compost for Erosion/Sediment Control (Filter Berms and Filter socks) R 51.

727-2.05 TACKIFIER. Tackifier, viscous overspray, generally composed of dry powered vegetable gums derived from guar gum, psyllium and sodium alginase; asphaltic emulsions; petroleum distillates; co- polymer emulsions; and lignosulfonates and used to anchor soil, compost, seed, the mulch fibers to one another, and the ground. Contain no growth or germination inhibiting materials nor significantly reduce infiltration rates. Tackifier shall hydrate in water and readily blend with other slurry material. Tackifier options include:

- Type A. Organic tackifier with certification of plant sources; or

- Type B. Synthetic tackifier with certification confirming product is not harmful to plants, animals, or aquatic life.

727-2.06 POLYACRYLAMIDE (PAM). Use as a tie-down for soil, compost, seed and as a flocculent. Polyacrylamide (PAM) products shall meet the requirements of American National Standards Institute (ANSI)/National Sanitation Foundation International (NSF) Standard 60 for drinking water treatment, be anionic (not cationic), linear and not cross-linked with an average molecular weight greater than 5 Mg/mole, minimum 30 percent charge density; contain at least 80% active ingredients and a moisture content not exceeding 10% by weight.

Deliver PAM in a dry granular powder or liquid form.

727-2.07 GEOTEXTILE-ENCASED CHECK DAM AND SEDIMENT BARRIER.  Urethane foam core

encased in geotextile material (silt fence material Section 633), minimum 8 inches height by minimum base width of 16 inches by minimum 7 foot length. Overhang the geotextile 6 inch minimum each end with apron type ties by 24 inches each side of the foam core.

### 727-2.08 SANDBAG.

- Sandbag Sack Fabric. Fabric shall be a nonwoven, needle punched design meeting the Minimum Average Roll Values (MARV) verified in accordance with ASTM D4759.

- Seam Thread. Similar durability to the sandbag sack fabric.

- Sandbag Fill Material.

  - Selected Material	703-2.07	Type B

- Cinch Ties. Plastic ties or equivalent tie recommended by the sandbag manufacturer.

### 727-2.09 MANUFACTURED INLET PROTECTION SYSTEM.

- Manufacturers:

  - Ultra Tech International – Ultra-DrainGuard

  - Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

  - Enpac - Catch Basin Insert, Oil and Sediment or

  - Approved equal.

727-2.10 CLEAR PLASTIC COVERING. A clear plastic covering meeting the requirements of the National Institute of Standards and Technology (NIST) voluntary Product Standard PS 17 - 69 for polyethylene sheeting having a minimum thickness of 6 mils.

727-2.11 STAPLES. U-shaped staples for anchoring matting, approximately 6 inches long and 1 inch wide. Machine-made: No. 11 gage or heavier steel wire. Hand-made: 12-inch lengths of No. 9 gage or heavier steel wire.

#### CR727-12.0508R2

Add the following section:

### SECTION 732

MODULAR BRIDGE JOINT SYSTEMS

732-2.01 SCOPE. Modular Bridge Joint Systems (MBJS) for use on bridges.

732-2.02 ELASTOMERIC JOINT SEALS. Use continuous preformed strip-type seals conforming to ASTM D 5973 constructed with only virgin natural polyisoprene (natural rubber) as the raw polymer in the elastomeric compound. Do not use neoprene. Use preformed material meeting the following requirements of ASTM D2000:

M4AA 514 A13B13C12F17

732-2.03 LUBRICANT-ADHESIVE FOR ELASTOMERIC JOINT SEALS. Use lubricant-adhesive

conforming to ASTM D4070.

732-2.04 STEEL EXTRUSIONS. Use steel extrusions meeting ASTM D5973, fabricated from steel conforming to ASTM A 709 Grade 36. Galvanize steel extrusions in accordance with Subsection 716- 2.07.

732-2.05 POLYTETRAFLUORETHYLENE (PTFE). Use 100 percent virgin woven PTFE fabric or dimpled PTFE conforming to ASTM D4894 and Table 720-1. Provide PTFE on every sliding surface in the MBJS.

732-2.06 STAINLESS STEEL. Use stainless steel plates and sheets conforming to ASTM A240, Type 304 of Type 316 on every sliding surface opposite PTFE.

CFHWY01060

APPENDIX A CONSTRUCTION SURVEY REQUIREMENTS

## Blank Page

APPENDIX B ENVIRONMENTAL PERMITS

## Blank Page

APPENDIX C MATERIAL CERTIFICATION LIST

## Blank Page

APPENDIX D

HUMAN REMAINS PROTOCOL

## Blank Page

APPENDIX E INADVERTENT DISCOVERY PROCEDURE

## Blank Page

APPENDIX F VEGETATION MANAGEMENT PLAN

Blank Page