SECTION 623

- BLOCK SODDING

Special Provisions

623-1.01 DESCRIPTION. Delete this Subsection in its entirety and substitute the following:  This wetland restoration work consists of two separate items: 1) retrieving, transporting and  installing  living Vegetated Mats which will be produced by the Alaska Department of Natural Resources Plant Materials Center in Palmer, and 2) extract, move, and install Wetland Sod Blocks in the areas designated on the Plans or as directed by the Engineer.  The purpose of this work is to expedite the revegetation of restored wetland areas as required under Special Condition # 8 of the Corps of Engineers Permit 2-980650.

623-1.01 MATERIALS. Delete this Subsection in its entirety and substitute the following:

1. Vegetated Mats.  	Vegetated Mats will be provided by the Plant Materials Center (PMC) in Palmer for installation in Wetland Restoration Area A.

- a.   	Transportation and Storage: Coordinate the pick up the Vegetated Mats with Nancy Moore, PMC, at (907) 746-7241.  The Vegetated Mats shall be transported from the PMC, in a truck large enough to accommodate the entire 0.9 m x 3 m Mats whole. Insure that the Mats are protected during transport and that they do not dry out.  If the material must be stored on site prior to installation, the storage area shall be shaded and Mats kept moist throughout the root zone.  Installation shall occur within 48 hours of transport from PMC.

2. Wetland Sod Blocks. 	Wetland Sod Blocks shall be harvested from Wetland Restoration Area B, as specified on the Plans. Sod Blocks shall be cut to measure approximately 1.5 m by 1.5 m. Sod Blocks shall be 0.4 meter thick. Sod Blocks shall be removed only from areas approved by the Engineer in and adjacent to Wetland Restoration Area B. Use approved mechanized methods to obtain and place Wetland Sod Blocks.

623-3.01 CONSTRUCTION REQUIREMENTS. Delete this Subsection in its entirety and substitute the following:

Plant Season:  Both the Vegetated Mats and Wetland Sod Blocks shall be planted between May 15 and August 1.

1.  	Vegetated Mats.

- a.	Layout. 	Stake all areas to be planted with Vegetated Mats as shown on the Plans prior to installation.  Notify the Engineer of the delineated areas 3 working days prior to installation, and installation shall commence only after approval by the Engineer.

- b.	Installation.

- i.	Commencement of work assumes that you accept the conditions of the cut and fill grades, of areas in question.  Any discrepancies in work shall be brought to the attention of the Engineer, in written format, immediately.

ii.	Before installing the Vegetated Mats, you must insure that the embankment is moist. Vegetated Mats shall be placed in position insuring complete contact of root mass to the soil surface. Tamp into place. Staple or stake mats into place as shown on the Plans.

iii.	Water Vegetated Mats  within one hour of placing. Continue to                                                   keep Mats moist until final acceptance of the project.

2.	Wetland Sod Blocks.

- a.	Removal of Wetland Sod Blocks.

- The sod blocks shall be harvested from the existing vegetation in and adjacent to Restoration Area B.  Sod Block removal sites shall be approved by the Engineer prior to harvest.  Blocks shall be cut prior to removal from growing site.  The sod blocks shall be stockpiled in a single layer and in the upright position.  Remove and transport sod blocks in a manner that allows continued access to the remaining sod blocks and maintains the areas to remain undisturbed without damage.

- b.	Placement of Wetland Sod Blocks.

- Final grading of the receiving site shall be completed and approved by the Engineer.   No removal and transport of sod blocks is permitted prior to preparation of the receiving site.  The Wetland Sod Blocks shall be placed within 24 hours of their removal.

- The Wetland Sod Blocks shall be placed in the upright position in the locations shown on the Plans.

3.	Fertilization.

Apply a slow-release granular fertilizer, 8-32-16, at an application rate of                                           20 grams per square meter between May 1 and June 1 of the growing season following installation.

Add the following Subsection:

623-3.02 MAINTENANCE.  The maintenance period extends from the time of planting to August 1 of the next growing season.  Water, repair damaged areas, and replace dead vegetation in the Wetland Sod Blocks as necessary and directed by the Engineer during the maintenance period.

623-4.01 METHOD OF MEASUREMENT. Delete this Subsection in its entirety and substitute the following:

Measurement of Pay Items 623(5) and 623(6) shall be by the square meter installed, per Subsection 109-1.02.  Watering shall be subsidiary to these pay items.

623-5.01 BASIS OF PAYMENT.  Add the following:  All equipment and materials, watering, stapling, fertilizing and labor associated with the work described in this section shall be subsidiary to Pay Items 623(5) and 623(6).

Partial payments of up to 80% of full amount may be authorized for installation of Vegetated Mats, Pay Item 623(5) at the time of acceptance.  The balance will be paid with one final payment at the completion of the maintenance period, if at that time 70% of plant materials, by area, are living.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 623(5) Vegetated Mats, Installed | Square Meter |
| 623(6) Wetland Sod Block, Installed | Square Meter |