Special Provisions

Replace Section 505 with the following:

SECTION 505

PILING

505-1.01 DESCRIPTION. Furnish and drive piles, and assist in pile testing.

The Engineer will perform high-strain dynamic pile testing on at least five piles, one pile at each abutment for the Ptarmigan Creek Bridge, one pile at each abutment for the Falls Creek Bridge and one pile at abutment one for the Trail River Bridge.  After the test pile program is completed, the installation and construction control criteria for the remaining bridge foundation piles will be established. The Engineer may select additional piles for high strain dynamic testing at their discretion.

505-1.02 DEFINITIONS.

CUT-OFF. The cut off end of a pile, or cutting a pile end at the finish elevation.

DRIVECAP. A pile driver component that is used to transmit impact forces from the hammer ram to the pile top. The drivecap includes the anvil or striker plate, hammer cushion (capblock), helmet, and pile cushion, if used. (Also termed the driving head).

DRIVING RESISTANCE. The required axial resistance, in units of force, to be achieved during pile driving.

ESTIMATED PILE TIP ELEVATION. The elevation at which the Department expects the driving resistance to be achieved.

FRESH HEADING. Cutting the end of a pile perpendicular to the long axis to remove damage, and to obtain a proper driving or splicing surface.

FOLLOWER. A pile driving aid placed between the helmet and the pile top when the pile head is below the reach of the hammer.

HAMMER CUSHION. A disk of material placed on top of the helmet but below the anvil or striker plate to relieve impact shock and provide protection for the hammer and pile.

HAMMER ENERGY:

MAXIMUM RATED HAMMER ENERGY. The theoretical maximum amount of gross energy that a pile driving hammer can generate.

TRANSFERRED HAMMER ENERGY. The amount of energy transferred to the pile for a given blow accounting for friction energy during the ram down stroke, energy retained in the ram and drivecap during rebound, and other impact losses.

HELMET. A pile driver component that fits closely on top of the pile to ensure the impact force is transmitted uniformly across the top of the pile and concentric with the axis of the pile.

LEADS. Pile driver components used to maintain pile and hammer alignment during driving, and on which the pile hammer may travel. Types of leads include :

FIXED LEADS. Pile driving leads that are attached at the top of the boom by a pivot and to the crane at the bottom with a brace. The pile is held at the top by the helmet and is guided at the bottom by the pile gate.

SEMI-FIXED LEADS. Pile driving leads that are attached at the top of the boom by a pivot and supported by the lead line. The lead can slide axially along the pivoted boom point and may be fitted with an extendable brace at the bottom of the leads.

SWINGING LEADS. Pile driving leads that are suspended from the boom by the cable and are not attached to the crane at the bottom with a brace. (Also known as offshore leads)

MINIMUM PENETRATION. The minimum length of pile below the footing or finished ground elevation to which the pile must be driven.

OBSTRUCTION. An unanticipated object projecting within the path of the pile that causes pile refusal or impedes the pile's advance within required tolerances.

PILE GATE. A device at the base of the leads that is closed around the pile to maintain alignment.

REFUSAL. Refusal occurs when the hammer requires 15 or more blows to move the pile one inch, and the hammer is operating near the maximum allowable compressive driving stress (within 80-90% of the specified pile yield stress).

SUBSTRUCTURE UNIT. A unit of the substructure such as an abutment or pier that transmits loads directly from the superstructure to the ground.

TEST PILE. A pile that has a high-strain dynamic test performed on it.

TEMPLATE. A structure affixed to the ground used to maintain proper pile alignment during driving.

WAVE EQUATION ANALYSIS. A numerical method of analysis for the behavior of driven piles that predicts the pile capacity versus blow count relationship (bearing graph) and pile driving stress. Wave equation analysis is performed using the wave equation analysis program (WEAP) with a version dated 1987 or later.

505-2.01 MATERIALS. Use materials that conform to the following:

Structural Steel Piles	Section 715

Sand	Subsection 703-2.12

505-2.02 PILES. Furnish piles sufficient in length to obtain the driving resistance and to extend to the estimated pile tip elevation specified in the Contract documents. Furnish full-length piles where practical. Where splices are required, follow the provisions of Subsection 505-3.04. Furnish additional pile length to provide for fresh heading and to suit the method of installation. Use metal shoes or reinforced tips as required. Store and handle piles in a manner that protects them from damage.

1.	Steel Piles. Furnish Pipe piles, sheet piles or other structural steel sections described in the Contract.

Spirally welded pipe piles may be furnished for pipe pile diameters of 2’-0” and smaller.

The Engineer will reject steel piles that exceed the camber and sweep permitted by allowable mill tolerance.

CONSTRUCTION REQUIREMENTS

505-3.01 PILE DRIVING EQUIPMENT.

1.	Pile Driving System. Use impact hammers to drive piles and to determine resistance during pile driving. If a vibratory hammer is used, use an impact hammer to determine pile resistance by driving the pile an additional penetration of at least 5 feet. Use pile driver leads that allow the hammer to move freely. Do not use followers to drive piles.

Fit the pile driving hammer with a cast-steel driving head (or similar device) that is recommended in the hammer manufacturer’s guidelines, is compatible with the pile, and aligns concentrically and fits closely with the top of the pile.

If the pile driving hammer is fitted with a hammer cushion, use a cushion that satisfies the recommendation in the hammer manufacturer’s guidelines, is appropriate to prevent damage to the hammer or pile, and ensures uniform driving performance. If not new, ensure the hammer cushion is at least 75 percent of the manufactured thickness. Replace driving hammer cushions with a reduction in cushion thickness exceeding 25 percent of the manufactured thickness. Do not use wood, wire rope, or asbestos hammer cushions.

For piles that will not be exposed in the completed work, use fixed leads, a ground template, or other means to ensure proper placement and alignment of piles.

For piles that will be exposed in the completed work, use fixed leads, a two-tiered template that laterally supports the pile within 5 feet of the finished ground or water elevation and within 5 feet of the cut-off elevation, or other means to ensure proper placement and alignment of piles.

To ensure rigid lateral support to the pile during driving when using fixed leads, hold the leads in position at the top and bottom by using guys, steel braces, or other means of restraint that provide sufficient lateral support to prevent movement of the pile. Do not use semi-fixed leads or swinging leads without other means of providing sufficient lateral support to prevent movement of the pile. Wooden templates are not permitted.

Use only equipment included in the approved pile driving plan. The Engineer will inspect the pile driving equipment for conformance with the approved pile driving plan after it has been mobilized to the site and prior to beginning pile driving operations. Remove and replace pile driving equipment found out of conformance with the approved pile driving plan at no extra cost to the Department and with no adjustment to contract time.

2.	Wave Equation Analysis. Perform a wave equation analysis for all pile driving systems used to drive piling according to the requirements of this subsection and the user’s manual for the program. Verify that the pile driving system proposed does not produce stresses greater than 90-percent of the yield stress.  Also verify that the rate of pile penetration is 100-blows per foot or less at the Driving Resistance specified in the Contract.

TABLE 505-1

HAMMER EFFICIENCIES USED IN HAMMER APPROVAL

| Hammer Type | For Analysis of Driving Resistance | For Analysis of Driving Stresses |
| --- | --- | --- |
| Single acting diesel hammers | 0.72 | 0.84 |
| Closed-ended diesel hammers | 0.72 | 0.84 |
| Single acting air/steam hammers | 0.60 | 0.70 |
| Double acting air/steam hammers | 0.45 | 0.53 |
| Hydraulic hammers or other external combustion hammers having ram velocity monitors that may be used to assign an equivalent stroke. | 0.85 | 1.00 |

Unless otherwise specified in the Contract, or directed by the Engineer, use the following default values and the applicable values from Table 1 as input to the wave equation analysis program:

Output option (IOUT)	0

Factor of safety applied to (Rult)	1.0

Type of damping	Smith

Residual stress option	No

3.	Pile Driving Plan. No less than 30 days prior to the anticipated start of pile driving, submit for approval the details of each proposed pile driving system. Include in the pile driving plan:

a.	A completed Pile Driving Equipment Data form (Form 25D-098).

b.	Manufacturer’s catalog cuts, specifications, manuals, guidelines, and technical bulletins for all pile driving equipment to be used.

c.	A description of the techniques to be used for ensuring proper placement and alignment of the piles, obtaining the driving resistance, and advancing the piles to the estimated pile tip elevation.

d.	Alternate methods of pile installation in the event obstructions are encountered.

e.	A wave equation analysis for each pile driving system.

The Engineer will base approval of the pile driving plan on the wave equation analysis submitted by the Contractor, and the requirements in this Subsection. The Department will verify the wave equation analysis using the computer program “GRLWEAP” and GRLWEAP industry standard hammer input data.

Approval by the Engineer of the pile driving plan will not relieve the Contractor of responsibility for piles damaged during pile driving operations. Do not mobilize pile driving equipment to the site without an approved pile driving plan.

Submit all revisions to the approved pile driving plan to the Engineer for approval. For all pile driving equipment not previously identified in the pile driving plan, include in the submittal all of the information required above for the pile driving plan. Explain to the Engineer, in writing, which portions of the approved pile driving plan will be superseded by the revision and which portions remain unchanged. Allow at least 5 days for the Engineer’s approval of pile driving plan revisions.

505-3.02 PILE TESTING AND PILE DRIVING CRITERIA. The Engineer will use one or more of the following to set criteria to monitor pile driving performance and the resistance of the pile during driving. The Engineer may also perform pile testing to confirm hammer-system efficiency, pile driving stresses and pile integrity. Attend a meeting with the Engineer at least 14 days prior to the beginning of pile driving operations to evaluate and discuss the test pile program. Give the Engineer 7 days advance notice before driving each test pile.

1.	Wave Equation Analysis. The Engineer will provide pile driving criteria based on the wave equation analysis that was performed by the Department. The wave equation analysis computer program to be used will be the "GRLWEAP" program using the GRLWEAP industry standard hammer input data.

2.	High-Strain Dynamic Testing. The Engineer will perform high-strain dynamic testing at the first pile driven at each substructure unit designated for pile testing or as determined by the Engineer. The Engineer will perform the high-strain dynamic testing in accordance with ASTM D 4945. Piles tested using high-strain dynamic testing may be incorporated into the work.

Do not drive any production piles, at the substructure unit until the test pile has been driven to the driving resistance and minimum penetration specified in the Contract documents. The Engineer will require 4 hours at each test pile to set up and install the test equipment. The Engineer will attach testing instruments near the top of the test pile through drilled and threaded holes. The Department will furnish the testing equipment and labor necessary to mount the testing instruments to the pile. Provide a reasonable and safe means of access to the top of the test pile after the pile is placed in the leads. Furnish electrical power (a 115 volt, 55-60 cycle AC outlet, 10 amp minimum) for the Engineer’s use during the installation and operation of the testing instruments.

Drive each test pile to the driving resistance and minimum penetration specified in the Contract documents as indicated by the wave equation analysis. The Engineer will record driving data for the test pile. If an obstruction is encountered during driving of the test pile, testing will stop on that pile and the next pile driven at the substructure unit will be designated as a test pile.

If the test results do not conclude the driving resistance has been obtained, the Engineer may direct suspension of pile driving operations for up to 72 hours and then require restriking the pile with the Engineer present to record driving data. Perform the restrike with a warmed-up hammer with the energy or fuel setting adjusted to the position indicated in the approved pile driving plan. Strike the test pile with 60 consecutive blows or until the pile penetrates an additional 3 inches, whichever comes first. The Engineer may terminate the re-strike after 25 blows if pile penetration is less than 1 inch.

If the results from the high-strain dynamic testing are acceptable to the Engineer, drive the remaining piles at the substructure unit using the criteria set by the Engineer and based on the results of the high-strain dynamic testing. The Engineer will provide new driving criteria within 1 day of the completion of high-strain dynamic testing that confirms the driving resistance of a test pile.

Account for the entire allotted equipment installation time and restrike suspension time required by the Engineer in the progress schedule submitted under Subsection 108-1.03 or Section 646, as applicable. Suspension of pile driving operations at a testing location to allow for testing instrument installation or a re-strike of a test pile is not a suspension of work per Subsection 108-1.06 and additional contract time will not be allowed.

505-3.03 DRIVING PILES. Drive all piles to the driving resistance and minimum penetration specified in the Contract documents using the pile driving criteria provided by the Engineer. Use the same pile driving system used to set pile driving criteria to drive all piles. Install piles in groups starting from the center of the group and proceed outward in either direction.

If the pile is driven to the estimated pile tip elevation and does not achieve the driving resistance, continue driving the pile to a penetration established by the written direction of the Engineer.

1.	Driving Through New Embankment. When driving piles through new embankment and the depth of the embankment at the pile location is in excess of 5 feet, drive the pile in a hole made through the embankment. Make the hole diameter 6 inches greater than the pile. After driving the pile, fill the annular space around the pile with sand.

2.	Placement and Alignment. Ensure proper placement and alignment of the piles. The Engineer will reject piles that are bent or otherwise damaged by forcing the pile into the leads or template.

Drive piles within an allowed variation as to direction of pile of not more than 1/4 inch per foot. Limit the rotation of steel piles about their longitudinal axis to 15 degrees from the plan position. In addition, position piles to the following tolerances:

a.	Abutments. Position the piles at the bottom of an abutment within 3 inches of the position specified in the Contract documents. Do not vary the distance between any two piles more than 3 inches from that specified in the Contract documents, and keep the clear distance from the edge of pile to the edge of footing to at least 9 inches.

3.	Protection of New Concrete. When driving a pile near concrete placed within 28 days, ensure the distance between the pile being driven and the nearest edge of concrete is not less than the distance determined by the following formula:

Where:	D = Distance in feet

E = Maximum rated hammer energy in foot-pounds

C = Vibration coefficient shown in Table 505-2 based on the number of calendar days after concrete placement

4.	Obstructions. Use alternate methods to drive through or remove obstructions. Obtain written approval from the Engineer before employing any alternative methods of pile advancement.

After exhausting all practicable means to obtain the minimum penetration, but without success, the Engineer will evaluate the structural adequacy of the bridge at a lesser penetration. This review will be based on the resistance of the pile during driving. If the Engineer finds the structure to be adequate, the pile will be accepted at the lesser pile penetration.

5.	Concrete Filled Pipe Piles. After driving pile, clean out the pile to the bottom of concrete elevation specified in the Contract documents. If there is a delay between cleanout and placing concrete, verify that the soil level in the pile has not rebounded before placing concrete.

TABLE 505-2

VIBRATION COEFFICIENT

| Concrete Age (days) | Coefficient |
| --- | --- |
| 1 | 0.34 |
| 2 | 0.23 |
| 3 | 0.18 |
| 4 | 0.15 |
| 5 | 0.13 |
| 6 | 0.12 |
| 7-9 | 0.11 |
| 10-13 | 0.10 |
| 14-20 | 0.09 |
| 21-28 | 0.08 |

505-3.04 SPLICES, EXTENSIONS AND BUILD-UPS. If the length of a steel pile is not sufficient to obtain the estimated pile tip elevation and driving resistance specified in the Contract documents, the pile may be spliced in order to obtain the length required to reach the minimum penetration and driving resistance. Use additions with cross sections identical to the pile cross sections.

Make splices with complete joint penetration welds over the entire cross section. If approved, piles may be spliced using pile cut-offs and short pieces if no piece used is less than 10 feet long.

Meet the welding requirements of Section 504. Align the piles at a splice to meet the dimensional tolerances for the allowable variation in straightness of welded columns in AWS D1.1.

505-3.05 DEFECTIVE PILES. Use a pile driving method which does not damage the pile. Do not manipulate the piles to force them into proper position. Correct damaged or improperly driven piles using a method approved by the Engineer. Drive down all piles pushed up by driving adjacent piles or by any other cause. Approved methods may include one of the following:

1.	Withdraw and replace the pile with a new and, when necessary, longer pile.

2.	Drive a second pile adjacent to the defective pile.

3.	Splice or build up the pile.

4.	Extend a sufficient portion of the footing to properly imbed the pile.

505-3.06 CUTTING OFF PILES. Cut off the piles at the elevations indicated on the Plans. Ensure that all injured material is removed.

When steel piles are shown embedded in concrete footings or pile caps, cut off piles within -1/2 inch to +3 inches of the plan embedment, but do not interfere with reinforcing steel or other items embedded in concrete. When steel pipe piles are shown cutoff below concrete footings or pile caps, cut off piles within -1/2 inch to +1/2 inch of the plan elevation. In pile bents with steel cap beams, make accurate cut-offs to ensure full bearing between the caps and piles.

505-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Furnish Piles. The sum of the lengths of the piles in place in the completed structure, measured along the centerline of piles from the tip of pile to the cut-off elevation.

Drive Piles. The number of piles driven in place in the completed structure conforming to the contract.

Sheet Piles. The projected area of furnished and driven sheet piles remaining in place in the permanent structure as called for on the Plans, measured in final position.

505-5.01 BASIS OF PAYMENT.

Furnish Piles. The contract price includes pile materials delivered to the site, pile shoes, reinforced tips and casing. Unused pile lengths removed by cut-offs and fresh heading are subsidiary. The payment amount will be calculated using the quantity of pile indicated on the bid schedule, or the quantity of installed piles, whichever is greater.

Drive Piles. The contract price includes:

1.	All related work required to drive the piles including: pile crew time (including payroll and administrative additives), equipment costs, and other fixed or variable items incurred during pile driving, fresh heading, splicing, restrike, pile cleanout and cutting off.

2.	All related work required to assist the Engineer in performing High Strain Dynamic Testing is subsidiary.

Sheet Piles. Sheet piles used as temporary shoring for excavation, whether removed or left in place at your option with permission of the Engineer, are subsidiary.

Obstruction Removal. Alternate methods of pile advancement through obstructions performed at the direction of the Engineer will be paid as 505(14) Special Pile Excavation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

505(5)	Furnish Structural Steel Piles (2’-0” x 0.5” Pipe Piles)	Linear Foot

505(6)	Drive Structural Steel Piles (2’-0” x 0.5” Pipe Piles)	Each

505(9)	Structural Steel Sheet Piles	Square Foot

505(14)	Special Pile Excavation	Contingent Sum

52035-022511