MULLIKIN SURVEYS

P.O. Box 790, Homer, AK  99603-0790

Ph. & Fax: (907) 235-8975

January 30, 2009

TECHNICAL PROPOSAL & SCHEDULE

RFP 2006-22, PSA 62118, Alaska Tideland Survey No. 1672

After receiving Notice to Proceed, preliminary research and computations will proceed in the Homer office of Mullikin Surveys. A Professional Land Surveyor (PLS) will compute or check the data generated. About 15 plats with multiple sheets will be reviewed to confirm original meanders, existing monuments, and potential fill areas. We will review the DNR preliminary and final decisions. We would complete basic research to determine upland ownership and obtain permission to set monuments.

We have discussed the project with the Port Lions City Clerk and the Kodiak Island Borough Land Management Development Department Director. We have also briefly discussed the project with Patrick Green, PLS, DNR scrivener of Special Instructions.

We will meet with the Port Lion’s mayor to apprise him of our survey efforts. The Kodiak Island Borough will not require a review of the plat.

We asked Patrick Green about the level of detail of as-builts of improvements within the Tideland Survey boundaries and his emphasis was to determine that improvements are within or outside of the survey limits, with some detail necessary only along boundary lines, e.g., we do not need to measure every finger of the mooring slips.

We will use a tide bench mark as available; if not, then several days of tides will be measured to determine mean high water (MHW). This elevation will be extended to determine the meander lines via RTK GPS. Appropriate quality control via redundant measurements and total station will verify integrity of datum and measurements. Static GPS/GLONASS measurements will verify recovered and set monuments and control. We shall endeavor to set or recover suitable points for future GPS surveys.

We will obtain RTK “shots” near the MHW points and will also obtain a “shot” higher and lower in elevation. This will ensure we can depict the MHW lines, via an elevation line in a TIN, should further modification of elevations occur in the office.

A Professional Land Surveyor will be in Port Lions to guide the survey and ensure that quality control measures are implemented. This will probably be Don Mullikin, PLS, or Murray Nash, PLS.

Primary office work/review will be accomplished by Tom Latimer, PLS, or Mike Frame, PLS, with a final review by the Project Manager, Don Mullikin, PLS.

TENTATIVE SCHEDULE

January 30		Submit proposal

March 1		Notice to Proceed

March 5		Complete preliminary research and computations

March 18		Mobilize equipment and mail supplies, as possible

March 30		Travel to site via commercial airline; consider charter air craft or use

Alaska ferry, as possible

April 22		Submit preliminary plat to DNR & DOT

May 22		Make any revisions required on the plat

June 22		Final plat recorded