## Task1
COST ESTIMATE PER TASK
FIRM: | MULLIKIN SURVEYS |  |  |  | PROJECT TITLE: |  | Alaska Tideland Survey 1672, Port Lions
TASK NO: | PSA 62118 | TASK DESCRIPTION: |  | Alaska Tideland Survey | [7 empty] | DATE: | 2009-02-22
GROUP: |  | METHOD OF PAYMENT: |  | FP | FPPE | T&E | CPFF |  |  | PREPARED BY: | DEM/JM
SUB- | [5 empty] | LABOR HOURS PER JOB CLASSIFICATION
TASK NO. | SUB-TASK DESCRIPTION |  |  | Project Manager | P.L.S. S.T. | P.L.S. O.T. | P.L.S. S.T. | P.L.S. O.T. | AutoCAD Tech | AutoCAD Tech - O.T. | GPS Tech S.T. | GPS Tech O.T. | Secretary
Office | 1. Project Management & Coordination |  |  | 12
Office | 2. Project Document Research |  |  |  | 10 |  |  |  | 4
Office | 3. Plat & Notes Download, & Comps |  |  |  | 28 |  |  |  | 14
Office | 4. Mobilize, Pack & Ship Equipment | [7 empty] | 12
Travel | 5. Travel to Port Lion |  |  |  | 7 |  |  |  | 7
Travel | 6. Return Travel |  |  |  | 7 |  |  |  | 7
Survey | 7. Recover Mons., Set Mons., Meanders, As-builts |  |  |  | 62 | 26 |  |  |  |  | 62 | 26
Office | 8. Draft Preliminary Plat, Computations |  |  |  | 52 | [5 empty] | 30
Office | 9. Complete Final Plat |  |  |  | 12 | [5 empty] | 4
Office
TOTAL LABOR HOURS |  |  |  | 12 | 178 | 26 | 0 | 0 | 44 | 0 | 96 | 26 | 0
* LABOR RATES ($/HR) |  |  |  | 38 | 38 | 57 | 35 | 52.5 | 30 | 45 | 26 | 39 | 25
LABOR COSTS ($) |  |  |  | 456 | 6764 | 1482 | 0 | 0 | 1320 | 0 | 2496 | 1014 | 0
EXPENSES
SUB-TASK NO. | ITEM(S) |  |  |  | QUANTITY | UNIT PRICE | TOTAL PRICE
Travel | RT Air Homer to Port Lions |  |  |  | 2 | 897 | 1794
Freight | Excess Baggage Homer to Anchorage |  |  |  | 300 | 0.45 | 135
Freight | Excess Baggage Anchorage to Kodiak |  |  |  | 300 | 0.69 | 207
Freight | Excess Baggage Kodiak to Port Lions |  |  |  | 300 | 0.4 | 120
Rental | 4-wheeler rent, 10 days |  |  |  | 10 | 100 | 1000
Rental | Skiff, 5 days |  |  |  | 5 | 300 | 1500 | FIRM'S TOTAL COST OF LABOR (or Fixed Price): |  |  |  |  | 13532
R&B | $145/day x 2 people, 10 days |  |  |  | 20 | 145 | 2900 | IF CPFF, TOTAL INDIRECT COST @ |  |  |  | 130.5% | 17659.26
Materials | Monuments & fiberglass posts | [5 empty] | 440 | FIRM'S TOTAL COST (no Subcontracts or Fee) |  |  |  |  | 31191.26
Freight | Fly or mail equipment |  |  |  | 1 | 400 | 400
Fee | DNR plat review fee | [5 empty] | 400 | Firms Proposed Fee |  |  |  |  | 3383
[6 empty] | TOTAL EXPENSES: | 8896 | FIRM'S TOTAL EXPENSES |  |  |  |  | 8896
SUB-CONTRACTORS: Firm Initials and Price Per Task | [7 empty] | Firms Total Cost + Proposed Fee + Expenses |  |  |  |  | 43470.26
FIRM: | [7 empty] | TOTAL SUBCONTRACTOR PRICES: |  |  |  |  | 0
AMOUNT: | [7 empty] | Total Contract Price |  |  |  |  | 43470.26
COMMENTS: