## In-House Estimate
COST ESTIMATE PER TASK
FIRM: | ADOT&PF Estimate |  |  |  | PROJECT TITLE: |  | Port Lions Airport
TASK NO: |  | TASK DESCRIPTION: |  | Design and ROW Surveying | [7 empty] | DATE: | 2014-07-04 | RED Cells are Auto Computed
GROUP: |  | METHOD OF PAYMENT: |  | FP | FPPE | T&E | CPFF |  |  | PREPARED BY: | Travis Test
SUB- | [5 empty] | LABOR HOURS PER JOB CLASSIFICATION
TASK NO. | SUB-TASK DESCRIPTION |  | Survey Manager | Project Surveyor | Survey Tech | Survey Tech OT |  |  | 3 Person Crew | 3 Person Crew OT | Party Chief | Party Chief OT | Admin |  |  | Days | Regular Time | OT
| Management | [14 empty] | 1 | 7.5 | 2.5
| Research |  |  | 4 | [11 empty] | 2 | 15 | 5
| DOT Meeting | [14 empty] | 3 | 22.5 | 7.5
[16 empty] | 4 | 30 | 10
| Field | [12 empty] | 3Man Days | Notes | 5 | 37.5 | 12.5
| Mobe/Demobe | [7 empty] | 8 |  |  |  |  | 1.0667 |  | 6 | 45 | 15
| Control |  |  | 2 |  |  |  |  | 8 | 2 |  |  |  | 1.0667 |  | 7 | 52.5 | 17.5
| Airport Boundary |  |  | 2 |  |  |  |  | 16 | 4 |  |  |  | 2.1333 |  | 8 | 60 | 20
| Boundary Stake | [7 empty] | 8 | 2 |  |  |  | 1.0667 |  | 9 | 67.5 | 22.5
| 20:1 Obs |  |  | 1 |  |  |  |  | 4 |  |  |  |  | 0.53333 |  | 10 | 75 | 25
| ALP Requests |  |  | 4 |  |  |  |  | 12 | 4 |  |  |  | 1.6 |  | 11 | 82.5 | 27.5
[14 empty] | 0 |  | 12 | 90 | 30
| Office | [12 empty] | 7.4667 | Total Crew Days | 13 | 97.5 | 32.5
| SCD (ROS) |  |  | 40 | [11 empty] | 14 | 105 | 35
| Deliverables |  |  | 8 | [11 empty] | 15 | 112.5 | 37.5
| QA/QC |  |  | 4 | [11 empty] | Computed | Regular Time | OT
[16 empty] | 70 | 525 | 175
Revisions
Total Hours
TOTAL LABOR HOURS |  |  | 0 | 65 | 0 | 0 | 0 | 0 | 56 | 12 | 0 | 0 | 0 | 133
* LABOR RATES ($/HR) |  |  | 75.57 | 64.33 | 56.37 | 64.12 |  |  | 139.18 | 158.29 | 50.21 | 57.11 | 57.11
LABOR COSTS ($) |  |  | 0 | 4181.45 | 0 | 0 | 0 | 0 | 7794.08 | 1899.48 | 0 | 0 | 0
EXPENSES
SUB-TASK NO. | ITEM(S) |  |  |  | QUANTITY | UNIT PRICE | TOTAL PRICE
| Travel |  |  |  | 3 | 350 | 1050
| Per Diem |  |  |  | 18 | 60 | 1080
| Local Transportation |  |  |  | 6 | 150 | 900
| Freight |  |  |  | 1 | 1250 | 1250
| Lodging |  |  |  | 18 | 200 | 3600
| Charter from ADQ to ORI |  |  |  | 2 | 750 | 1500 | FIRM'S TOTAL COST OF LABOR (or Fixed Price): |  |  |  |  | 13875.01
[8 empty] | IF CPFF, TOTAL INDIRECT COST @ |  |  |  | 0% | 0
[6 empty] | TOTAL EXPENSES: | 9380 | FIRM'S TOTAL EXPENSES |  |  |  |  | 9380
SUB-CONTRACTORS: Firm Initials and Price Per Task | [7 empty] | FIRM'S TOTAL COST (no Subcontracts or Fee) |  |  |  |  | 23255.01
FIRM: | [7 empty] | FEE\FUDGE | 15% |  |  |  | 3488.2515
AMOUNT: | [7 empty] | TOTAL |  |  |  |  | 26743.2615
* Labor Rates shall be direct labor (base pay) only if Method of Payment is CPFF; otherwise, Labor Rates shall be total rates (i.e. base pay + benefits + overhead + profit.)
COMMENTS:

## Consultant Estimate
COST ESTIMATE PER TASK
FIRM: |  |  |  |  | PROJECT TITLE:
TASK NO: |  | TASK DESCRIPTION: |  | Design and ROW Surveying | [7 empty] | DATE: |  |  | ORANGE Cells are Auto Computed
GROUP: |  | METHOD OF PAYMENT: |  | FP | FPPE | T&E | CPFF |  |  | PREPARED BY: | Bob Keiner
SUB- | [5 empty] | LABOR HOURS PER JOB CLASSIFICATION
TASK NO. | SUB-TASK DESCRIPTION |  | Survey Manager | Project Surveyor | Survey Tech | Survey Tech OT | 2 Man Crew | 2 Man Crew OT | 3 Man Crew | 3 Man Crew OT | Proj Surveyor | Project Surv OT | Admin |  |  |  | Days | Regular Time | OT
| Management | [15 empty] | 1 | 8 | 2
| Research | [15 empty] | 2 | 16 | 4
| DOT Meeting | [15 empty] | 3 | 24 | 6
[17 empty] | 4 | 32 | 8
| Field | [12 empty] | 2Man Days | 3Man Days | Notes | 5 | 40 | 10
| Mobe/Demobe | [12 empty] | 0 | 0 |  | 6 | 48 | 12
| Control | [12 empty] | 0 | 0 |  | 7 | 56 | 14
| ROW | [12 empty] | 0 | 0 |  | 8 | 64 | 16
| Topo | [12 empty] | 0 | 0 |  | 9 | 72 | 18
[14 empty] | 0 | 0 |  | 10 | 80 | 20
[14 empty] | 0 | 0 |  | 11 | 88 | 22
[14 empty] | 0 | 0 |  | 12 | 96 | 24
| Office | [12 empty] | 0 | 0 | Total Crew Days ea. | 13 | 104 | 26
| SCD (ROS) | [12 empty] | 0 |  | Total Crew Days | 14 | 112 | 28
| Deliverables | [15 empty] | 15 | 120 | 30
| QA/QC | [15 empty] | Computed | Regular Time | OT
[17 empty] | 70 | 560 | 140
Revisions
Total Hours
TOTAL LABOR HOURS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
* LABOR RATES ($/HR) |  |  | 65 | 45 | 30 | 45 | 60 | 90 | 100 | 150 | 45 | 67.5 | 25
LABOR COSTS ($) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EXPENSES
SUB-TASK NO. | ITEM(S) |  |  |  | QUANTITY | UNIT PRICE | TOTAL PRICE
| Travel | [5 empty] | 0
| Per Diem | [5 empty] | 0
| Local Transportation | [5 empty] | 0
| Survey Supplies (Monuments) | [5 empty] | 0
| Survey Equipment | [5 empty] | 0
| Vehicles | [5 empty] | 0 | FIRM'S TOTAL COST OF LABOR (or Fixed Price): |  |  |  |  | 0
[8 empty] | IF CPFF, TOTAL INDIRECT COST @ |  |  |  | 125% | 0
[6 empty] | TOTAL EXPENSES: | 0 | FIRM'S TOTAL EXPENSES |  |  |  |  | 0
SUB-CONTRACTORS: Firm Initials and Price Per Task | [7 empty] | FIRM'S TOTAL COST (no Subcontracts or Fee) |  |  |  |  | 0
FIRM: | [7 empty] | FEE | 10% | Direct | 15% | Indirect | 0
AMOUNT: | [7 empty] | TOTAL |  |  |  |  | 0
* Labor Rates shall be direct labor (base pay) only if Method of Payment is CPFF; otherwise, Labor Rates shall be total rates (i.e. base pay + benefits + overhead + profit.)
COMMENTS: