ALASKA DEPARTMENT OF TRANSPORTATION AND PUBLIC FACILITIES

# Systems Engineering Review and Analysis Checklist for Intelligent Transportation Systems Projects

Project screening scaled documentation and lifecycle readiness

Use this checklist to identify ITS early, determine the appropriate level of systems engineering, document the seven elements required by 23 CFR 940.11, and confirm that the resulting system can be accepted, operated, maintained, secured, and supported throughout its useful life.

| Project title |  |
| --- | --- |
| Project identifiers | IRIS: ____________________ Need ID: ____________________ |
| Project manager |  |
| Region or sponsoring office |  |
| Checklist version | Proposed update September 2026 |
| Initial completion date |  |
| Most recent update |  |

This checklist is intended to replace the Alaska Iways Architecture Systems Engineering Checklist published in 2019 after departmental and FHWA review. Until formally adopted, project teams must continue to follow current Alaska Highway Preconstruction Manual requirements and project-specific federal oversight direction.

# Purpose and use

Complete Part A for every DOT&PF project that may contain electronics, communications, software, sensing, information processing, traffic control, traveler information, connected infrastructure, or another technology-enabled operational function. If Part A identifies ITS, complete the remaining parts at the level selected in Part B.

For an ITS project funded in whole or in part with Highway Trust Fund dollars, 23 CFR 940.11 requires a systems engineering analysis scaled to the project scope. This checklist records the analysis and points to supporting documents. It does not replace a Concept of Operations, requirements specification, architecture mapping, test plan, operations plan, or other project artifact when the selected documentation level calls for one.

## How to complete the checklist

Begin during scoping or project initiation and update the form as decisions mature.

Use concise responses for simple, repeatable deployments. Reference existing standards, plans, specifications, or approved system documents instead of restating them.

For complex systems, summarize the decision in this checklist and cite the controlling document, version, date, and section.

Coordinate early with the statewide TSMO or ITS program, affected system owners, Maintenance and Operations, information technology and cybersecurity staff, regional Traffic and Safety staff, communications owners, procurement staff, and FHWA when applicable.

Do not mark an item complete solely because a document exists. Confirm that the document applies to this project and that the responsible owner has reviewed it.

Attach the completed checklist and referenced systems-engineering documentation to the Design Study Report or project file as required by current department procedures.

## Checklist structure

| Part | Purpose | When completed |
| --- | --- | --- |
| A | Project identification and ITS screening | Scoping or project initiation |
| B | Complexity assessment and documentation level | Before scope and budget are fixed |
| C | Seven required systems engineering analysis elements | Concept development through design |
| D | Lifecycle engineering and operational readiness | Design through acceptance |
| E | Deliverables and stage reviews | Throughout project development |
| F | Determination review and signatures | At major updates and before authorization |

## Key determination

A project is not exempt from consideration simply because it uses familiar equipment, installs only communications infrastructure, or initially operates as a stand-alone device. Complete the screening and document why a streamlined analysis is appropriate. Consider future integration, shared communications, central software, data exchange, cybersecurity, ownership, and maintenance before selecting the documentation level.

# Part A Project identification and ITS screening

## A1 Project information

| Project title |  |
| --- | --- |
| IRIS number |  |
| STIP or TIP Need ID |  |
| Federal aid project number |  |
| Route and location |  |
| Region or office |  |
| Project manager | Name: ____________________ Email: ____________________ |
| Design lead | Name or organization: ______________________________________ |
| Primary system owner |  |
| Operations owner |  |
| Maintenance owner |  |
| Current project phase | ☐ Planning ☐ Scoping ☐ Environmental ☐ Design ☐ Procurement ☐ Construction ☐ Operations |
| Estimated ITS amount | $____________________ Total project amount: $____________________ |
| Funding | ☐ Highway Trust Fund ☐ Other federal ☐ State ☐ Local ☐ Other: ____________________ |

## A2 Project description

Purpose need and operational outcome

Describe the transportation need, the outcome expected from the project, the users or operators who benefit, and how success will be recognized.

ITS scope and major elements

Describe all field devices, communications, software, data services, central systems, cloud services, vehicles, mobile applications, interfaces, and operational changes included in or affected by the project.

Relationship to other projects and systems

Identify related project phases, existing systems, planned expansions, shared communications, enterprise platforms, partner systems, or dependencies.

## A3 ITS screening

Answer each question for the entire project, including technology embedded in an otherwise conventional roadway, bridge, transit, ferry, maintenance, safety, or construction project.

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| Does the project acquire, develop, replace, configure, or materially upgrade electronics, communications, software, sensing, control, or information-processing technology used to improve surface transportation safety or efficiency? | ☐ | ☐ |  |
| Does the project provide or significantly contribute to an ITS service represented in ARC IT or an applicable statewide or regional ITS architecture? | ☐ | ☐ |  |
| Will any element exchange data with another device, vehicle, center, agency, vendor platform, public service, or future system? | ☐ | ☐ |  |
| Does the project create, consume, store, transform, display, publish, or archive operational transportation data? | ☐ | ☐ |  |
| Does the project affect traffic signals, dynamic message signs, cameras, detection, road weather, traveler information, work zones, incident management, transit, commercial vehicles, maintenance fleets, connected vehicles, or a transportation operations center? | ☐ | ☐ |  |
| Does the project install fiber, conduit, radio, cellular, satellite, network equipment, edge computing, or another communications capability intended for current or future operational technology? | ☐ | ☐ |  |
| Does the project introduce centrally managed software, software as a service, cloud hosting, mobile applications, APIs, artificial intelligence, analytics, or automated decision support? | ☐ | ☐ |  |
| Could failure, erroneous data, loss of communications, or unauthorized access affect safety, mobility, emergency response, public information, or continuity of operations? | ☐ | ☐ |  |
| Will an outside agency, municipality, contractor, service provider, carrier, fleet, or public user participate in implementation or operation? | ☐ | ☐ |  |
| Is any part of the project funded with Highway Trust Fund dollars? | ☐ | ☐ |  |

## A4 Screening determination

| Determination | ☐ Not an ITS project or element ☐ ITS element within a broader project ☐ Stand-alone ITS project ☐ ITS system expansion or modernization ☐ Determination requires program review |
| --- | --- |
| Basis | Cite the answers above, applicable definition, architecture service package, or consultation supporting this determination. |
| Federal requirement | ☐ 23 CFR 940.11 applies ☐ Does not apply ☐ To be confirmed with FHWA |
| Program coordination | Reviewer: ____________________ Date: __________ Comments: ______________________________ |

# Part B Complexity assessment and documentation level

The federal analysis must be commensurate with project scope. Use this assessment to select a practical documentation level. The level controls the depth of the work, not whether the seven required elements are considered.

## B1 Complexity and risk factors

| Factor | Low | Moderate | High | Reason or reference |
| --- | --- | --- | --- | --- |
| Technology maturity | ☐ Proven repeat deployment | ☐ New model or configuration | ☐ First of kind or rapidly evolving |  |
| System interfaces | ☐ None or one known interface | ☐ Several known interfaces | ☐ Many new or external interfaces |  |
| Software and configuration | ☐ Fixed standard configuration | ☐ Material configuration or integration | ☐ Custom software algorithm or platform |  |
| Stakeholders | ☐ One owner and operator | ☐ Several internal groups | ☐ Multiple agencies vendors or agreements |  |
| Geographic scope | ☐ Single site | ☐ Corridor or regional | ☐ Statewide multi region or enterprise |  |
| Operational criticality | ☐ Limited service effect | ☐ Material mobility or information effect | ☐ Safety emergency or continuity critical |  |
| Communications | ☐ Existing proven connection | ☐ New carrier network or bandwidth | ☐ Multiple paths spectrum or high availability |  |
| Cybersecurity and privacy | ☐ Known controls no sensitive data | ☐ New accounts remote access or data sharing | ☐ High consequence access PII PKI or external exposure |  |
| Data complexity | ☐ Simple local data | ☐ Shared feeds APIs or archives | ☐ High volume multi source analytics or automated decisions |  |
| Procurement | ☐ Standard item and specification | ☐ Systems integrator or service contract | ☐ Multi contract custom IP or performance procurement |  |
| Operations and maintenance | ☐ Existing owner budget and skills | ☐ New training licenses or procedures | ☐ New organization staffing or sustained service |  |
| Testing | ☐ Standard inspection | ☐ Interface and operational testing | ☐ Formal verification validation pilots or safety testing |  |

## B2 Recommended documentation levels

| Level | Typical characteristics | Expected approach | Select |
| --- | --- | --- | --- |
| Level 1 Streamlined | Repeatable low complexity deployment using approved standards and an established owner | Complete this checklist with concise references to standard requirements testing and O&M documents | ☐ |
| Level 2 Tailored | Moderate integration configuration stakeholder or lifecycle risk | Complete the checklist and produce selected stand-alone artifacts for needs requirements interfaces testing and operations | ☐ |
| Level 3 Full | New complex multiagency enterprise connected software-heavy or safety-critical system | Use a documented systems-engineering management approach with a Concept of Operations traceable requirements architecture interfaces staged verification validation and transition planning | ☐ |

| Selected level | ☐ Level 1 ☐ Level 2 ☐ Level 3 |
| --- | --- |
| Rationale | Identify the factors that control the level and any requirements imposed by DOT&PF or FHWA. |
| Required artifacts | List the stand-alone documents selected in Part E. |
| Approved by | TSMO or ITS reviewer: ____________________ FHWA concurrence if required: ____________________ |

# Part C Systems engineering analysis

Part C documents the seven minimum elements in 23 CFR 940.11. Complete every section for an ITS project subject to the rule. Scale the response to the documentation level selected in Part B.

## C1 Applicable ITS architecture

Identify the portions of the applicable statewide, regional, or project ITS architecture implemented by the project. Final design should accommodate the applicable interface requirements and information exchanges. If the project differs from the architecture, document the difference and the architecture update needed.

| Applicable architecture | ☐ Alaska statewide ITS architecture ☐ Anchorage regional ITS architecture ☐ Project architecture ☐ ARC IT ☐ Other: ____________________ |
| --- | --- |
| Architecture version and date |  |
| Service packages |  |
| Elements and functional objects |  |
| Information flows and interfaces |  |
| Applicable standards from architecture |  |
| Architecture consistency | ☐ Consistent ☐ Update needed ☐ Project architecture needed ☐ Not yet determined |
| Architecture update owner and timing |  |

Architecture mapping summary

Summarize the operational services implemented, affected systems and stakeholders, important interfaces and information exchanges, and any gap or update. Attach architecture diagrams or reports when appropriate.

## C2 Participating organizations roles and responsibilities

Identify responsibility across the full lifecycle. Include organizations that authorize, fund, design, procure, host, integrate, secure, own data, operate, maintain, communicate with the public, respond to incidents, and accept the system.

| Organization or role | Design and delivery | Operations | Maintenance and support | Agreement or commitment |
| --- | --- | --- | --- | --- |

Responsibility summary

Describe decision authority, escalation paths, 24 hour or after-hours responsibilities, data ownership, security responsibilities, acceptance authority, and unresolved commitments.

| Agreements in place | List MOAs MOUs service-level agreements permits carrier agreements data-sharing agreements or maintenance agreements. |
| --- | --- |
| Agreements still needed | Identify owner target date and effect if not completed. |

## C3 Needs and system requirements

Requirements state what the system must do and the conditions and performance it must satisfy. Each requirement should be necessary, clear, feasible, verifiable, uniquely identified, and traceable to an approved need. Avoid embedding a preferred product or design unless the constraint is justified.

| Concept of Operations | Document title version date and section: _______________________________________________ |
| --- | --- |
| Requirements source | ☐ Project specification ☐ System requirements specification ☐ Standard requirements ☐ Other: ____________________ |
| Requirements owner |  |
| Requirements baseline date |  |
| Traceability method | ☐ Requirements traceability matrix ☐ Requirements tool ☐ Specification crosswalk ☐ Other: ____________________ |

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| Stakeholder and user needs are documented and approved. | ☐ | ☐ |  |
| Functional requirements define required system behavior without prescribing unnecessary design details. | ☐ | ☐ |  |
| Performance requirements define measurable capacity accuracy availability latency reliability or response targets. | ☐ | ☐ |  |
| Interface requirements define data content protocols timing ownership and error handling. | ☐ | ☐ |  |
| Environmental and physical requirements address Alaska climate location enclosure power grounding and access conditions. | ☐ | ☐ |  |
| Cybersecurity privacy and access-control requirements are included. | ☐ | ☐ |  |
| Data quality metadata retention sharing public-record and archival requirements are included. | ☐ | ☐ |  |
| Operations maintenance training support warranty licensing and replacement requirements are included. | ☐ | ☐ |  |
| Safety human-factors accessibility and fail-safe behavior are addressed where applicable. | ☐ | ☐ |  |
| Every requirement has an identified verification method and acceptance authority. | ☐ | ☐ |  |

Requirements gaps decisions and references

Identify missing baselines, unresolved needs, assumptions, waivers, constraints, or requirements that must be completed before procurement or final design.

## C4 Alternatives and technology options

Analyze alternatives against approved needs and requirements before locking the project into a product, vendor, communications path, hosting model, or system configuration. Include the no-build or maintain-existing condition when it is a meaningful comparison.

| Alternative | Meets needs | Integration | Lifecycle cost | Risk and resilience | Disposition |
| --- | --- | --- | --- | --- | --- |

Preferred alternative and basis

Explain why the selected configuration provides the best overall value. Address technical feasibility, interoperability, institutional fit, cybersecurity, communications, maintainability, vendor support, implementation risk, expansion, obsolescence, and lifecycle cost.

| Analysis reference | Document version date and section: _______________________________________________________ |
| --- | --- |
| Assumptions requiring validation |  |

## C5 Procurement and contracting

Select a procurement approach that fits the maturity of the requirements, allocation of risk, need for integration, available staff capability, desired competition, and long-term support model. Preserve the department's ability to verify requirements and control its operational baseline.

| Procurement approach | ☐ Design bid build ☐ Design build ☐ Systems integrator ☐ Product purchase ☐ Service or subscription ☐ Interagency ☐ Other: ____________________ |
| --- | --- |
| Selected contract type |  |
| Procurement decision reference |  |
| Owner furnished components |  |
| Separate contracts or dependencies |  |

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| Requirements and acceptance criteria are included in the solicitation and contract. | ☐ | ☐ |  |
| Systems-engineering deliverables reviews and approval points are included in the scope and schedule. | ☐ | ☐ |  |
| Interface responsibilities are allocated across contractors agencies and vendors. | ☐ | ☐ |  |
| Software licensing source code configuration data ownership API access and intellectual-property rights are defined. | ☐ | ☐ |  |
| Cybersecurity supply-chain vulnerability disclosure patching remote-access and incident-notification obligations are defined. | ☐ | ☐ |  |
| Testing environments equipment data personnel travel and retesting responsibilities are defined. | ☐ | ☐ |  |
| Payment milestones are tied to verified deliverables and acceptance rather than shipment or installation alone. | ☐ | ☐ |  |
| Warranty support service-level performance spare parts and end-of-life notification are defined. | ☐ | ☐ |  |
| Transition training documentation as-built configuration and knowledge-transfer requirements are defined. | ☐ | ☐ |  |
| Competition and future replacement are protected through standards data portability and avoidance of unnecessary lock-in. | ☐ | ☐ |  |

Procurement risks and controls

Identify requirements maturity, schedule dependencies, market limitations, sole-source considerations, owner staffing, contract interfaces, and controls needed before advertisement or award.

## C6 Standards verification and validation

Identify applicable standards and define how the project will demonstrate that requirements are satisfied and that the completed system supports the intended operational use. Inspection of installed equipment alone is not sufficient for integrated or software-based systems.

| Standard or specification | Applies to | Required optional | Conformance method | Owner |
| --- | --- | --- | --- | --- |

### Verification and validation plan

| Stage | Scope | Responsible party | Evidence and acceptance | Status |
| --- | --- | --- | --- | --- |
| Requirements review |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Design review |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Factory or bench test |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Installation inspection |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Interface and integration test |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Cybersecurity test |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Site acceptance test |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Operational validation |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Burn in or reliability period |  |  |  | ☐ Planned ☐ Complete ☐ N/A |
| Final acceptance |  |  |  | ☐ Planned ☐ Complete ☐ N/A |

| Test plan reference | Document version date and section: _______________________________________________________ |
| --- | --- |
| Requirements traceability | Explain how every requirement is linked to a verification method result and disposition. |
| Defect and retest process | Identify severity levels responsible party waiver authority retest and closure records. |

## C7 Operations management and maintenance

Identify the procedures, people, funding, tools, agreements, and technical resources needed to operate and manage the system after acceptance. Include all recurring costs and the transition from project delivery to sustained service.

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| An accountable operational owner has accepted the intended service and operating concept. | ☐ | ☐ |  |
| An accountable maintenance owner has reviewed maintainability access safety and staffing needs. | ☐ | ☐ |  |
| Standard operating procedures cover normal degraded emergency and recovery conditions. | ☐ | ☐ |  |
| Monitoring alarms help-desk escalation and after-hours responsibilities are defined. | ☐ | ☐ |  |
| Preventive corrective and emergency maintenance procedures and response targets are defined. | ☐ | ☐ |  |
| Staffing qualifications training and refresher training are funded and scheduled. | ☐ | ☐ |  |
| Software licenses hosting carrier charges certificates subscriptions and vendor support are budgeted. | ☐ | ☐ |  |
| Spare parts test equipment tools vehicles access and inventory responsibilities are defined. | ☐ | ☐ |  |
| Configuration backups restoration patching and release-management procedures are defined. | ☐ | ☐ |  |
| Performance measures data collection reporting and periodic service review are defined. | ☐ | ☐ |  |
| Warranty transition end-of-support replacement and decommissioning are planned. | ☐ | ☐ |  |
| As-built drawings asset records manuals credentials configurations and source files will be transferred and controlled. | ☐ | ☐ |  |

| Operations plan | Document version date owner and approval: __________________________________________________ |
| --- | --- |
| Maintenance plan | Document version date owner and approval: __________________________________________________ |
| Annual recurring cost | $____________________ Funding source: ____________________ First funded fiscal year: ______ |
| Lifecycle period | Planned service life: ______ years Replacement year or trigger: ____________________ |

Operational readiness gaps

Identify unfilled positions unfunded costs missing agreements tools training procedures documentation support contracts or acceptance conditions.

# Part D Lifecycle engineering and operational readiness

Part D extends the minimum federal analysis into the controls needed for a durable operational system. Complete each topic at the depth appropriate to the selected documentation level.

## D1 Cybersecurity resilience and continuity

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| System assets software accounts connections trust relationships and data flows are inventoried. | ☐ | ☐ |  |
| A cybersecurity risk assessment identifies credible threats vulnerabilities consequences and mitigations. | ☐ | ☐ |  |
| The design applies network segmentation least privilege strong authentication secure remote access and protected management interfaces. | ☐ | ☐ |  |
| Encryption certificate or key management and trusted communications are defined where applicable. | ☐ | ☐ |  |
| Default credentials unnecessary services and unsupported software are prohibited or controlled. | ☐ | ☐ |  |
| Logging monitoring time synchronization alerting and audit responsibilities are defined. | ☐ | ☐ |  |
| Vulnerability notification patch testing deployment exceptions and compensating controls are defined. | ☐ | ☐ |  |
| Backups restoration configuration recovery communications failover and continuity procedures are tested. | ☐ | ☐ |  |
| Vendor integrator and service-provider cybersecurity obligations continue through the support period. | ☐ | ☐ |  |
| Cybersecurity incident roles notification evidence preservation recovery and lessons learned are coordinated with department procedures. | ☐ | ☐ |  |
| Physical security tamper detection cabinet access and field maintenance practices are addressed. | ☐ | ☐ |  |
| Residual risks and exceptions have an identified owner and approval authority. | ☐ | ☐ |  |

| Security categorization or risk level |  |
| --- | --- |
| Cybersecurity plan reference |  |
| Responsible security reviewer | Name: ____________________ Date: __________ |
| Open risks and exceptions |  |

## D2 Data governance privacy and records

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| Data sources owners stewards users formats units timestamps and quality expectations are documented. | ☐ | ☐ |  |
| Authoritative source and system-of-record responsibilities are identified. | ☐ | ☐ |  |
| Data-sharing API publication and third-party use terms are documented. | ☐ | ☐ |  |
| Retention archival deletion public-record and legal-hold requirements are defined. | ☐ | ☐ |  |
| Personally identifiable sensitive security or precise-location data are identified and protected. | ☐ | ☐ |  |
| Metadata versioning provenance validation error correction and service-status indicators are defined. | ☐ | ☐ |  |
| Data portability and export prevent avoidable dependence on one vendor or platform. | ☐ | ☐ |  |
| Public information includes accessibility timeliness accuracy and outage considerations. | ☐ | ☐ |  |

## D3 Interfaces communications and infrastructure

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| A current context diagram identifies system boundaries external systems users and communications paths. | ☐ | ☐ |  |
| Interface-control information defines ownership data content protocols timing sequencing errors and version compatibility. | ☐ | ☐ |  |
| Bandwidth latency availability coverage and growth assumptions are documented and tested. | ☐ | ☐ |  |
| IP addressing naming time synchronization network management and device onboarding follow department practices. | ☐ | ☐ |  |
| Carrier service spectrum licensing permitting pole attachment utility and site-access requirements are resolved. | ☐ | ☐ |  |
| Power grounding surge protection uninterruptible power environmental enclosure and backup needs are addressed. | ☐ | ☐ |  |
| Single points of failure degraded operation fallback and recovery priorities are understood. | ☐ | ☐ |  |
| Communications and infrastructure capacity support planned expansion and maintenance access. | ☐ | ☐ |  |

Interface and communications summary

Identify the controlling diagrams interface documents communications design capacity calculations dependencies and unresolved external approvals.

## D4 Safety human factors and accessibility

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| Hazards associated with incorrect missing delayed or misunderstood system behavior are identified and controlled. | ☐ | ☐ |  |
| Failure modes place the system in a defined safe or operationally acceptable condition. | ☐ | ☐ |  |
| Operator displays alarms controls and procedures support workload situational awareness and timely decisions. | ☐ | ☐ |  |
| Traveler-facing information is clear consistent accessible and coordinated across channels. | ☐ | ☐ |  |
| Field installation maintenance and testing address worker traffic electrical climbing confined-space and environmental safety. | ☐ | ☐ |  |
| Automation and decision-support functions define human oversight operating limits and fallback behavior. | ☐ | ☐ |  |

## D5 Configuration change and asset management

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| The project identifies configuration items including hardware firmware software licenses settings databases models certificates documents and interfaces. | ☐ | ☐ |  |
| Approved baselines are established for requirements design test and as-built operation. | ☐ | ☐ |  |
| Changes are requested evaluated approved implemented verified documented and communicated through a defined process. | ☐ | ☐ |  |
| Asset identifiers locations ownership warranty condition support status and replacement information will enter the appropriate system of record. | ☐ | ☐ |  |
| Access to source files configurations credentials and vendor portals will transfer to the responsible owner. | ☐ | ☐ |  |
| Version compatibility rollback and recovery are addressed before production changes. | ☐ | ☐ |  |

## D6 Transition acceptance and post implementation

| Question | Yes | No | Notes reference or N/A basis |
| --- | --- | --- | --- |
| Operational and maintenance owners participate in design reviews testing and acceptance. | ☐ | ☐ |  |
| Training manuals standard operating procedures and emergency contacts are complete before service begins. | ☐ | ☐ |  |
| All critical defects are closed and accepted deviations have documented owners and expiration or disposition. | ☐ | ☐ |  |
| As-built drawings inventory configuration backups licenses warranties and test records are transferred. | ☐ | ☐ |  |
| A defined burn-in or reliability period demonstrates stable operation where appropriate. | ☐ | ☐ |  |
| The acceptance authority has objective evidence that requirements were verified and operational needs were validated. | ☐ | ☐ |  |
| A post-implementation review will compare outcomes with the original need and performance measures. | ☐ | ☐ |  |
| Lessons learned architecture changes standards updates and reusable requirements will be returned to the program. | ☐ | ☐ |  |

# Part E Deliverables and stage reviews

## E1 Project deliverables

Select the artifacts needed for this project. A Level 1 project may satisfy several rows through approved standard documents cited in this checklist. Level 2 and Level 3 projects should produce stand-alone artifacts where the subject requires review control or future use.

| Artifact | L1 | L2 | L3 | Project requirement | Document owner status or reference |
| --- | --- | --- | --- | --- | --- |
| ITS screening and completed checklist | R | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Systems engineering management plan | A | A | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Stakeholder and responsibility plan | A | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Concept of Operations | A | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Architecture mapping or project architecture | R | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Alternatives and lifecycle-cost analysis | A | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| System requirements specification | S | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Requirements traceability matrix | S | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| High-level and detailed design | S | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Interface-control documentation | A | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Cybersecurity plan and risk assessment | A | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Data management plan | A | A | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Procurement and contract strategy | S | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Verification and validation plan | S | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Test procedures and reports | S | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Operations and maintenance plan | S | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Training and transition plan | A | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| As-built configuration and asset records | R | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Acceptance report | R | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Post-implementation review | A | R | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |
| Replacement or decommissioning plan | A | A | R | ☐ Required ☐ Standard reference ☐ Not applicable |  |

Key: R means normally required. S means normally satisfied through approved standard requirements specifications procedures or plans. A means required when applicable to project scope risk or department direction.

## E2 Stage reviews and decision record

| Review | Minimum decision | Required evidence | Date | Disposition | Approver |
| --- | --- | --- | --- | --- | --- |
| 1 Need and scope | ITS determination funding and initial owner | Part A and initial stakeholder input |  | ☐ Proceed ☐ Conditional ☐ Revise ☐ N/A |  |
| 2 Concept and architecture | Operational concept interfaces level and artifacts | Parts B C1 C2 and concept documents |  | ☐ Proceed ☐ Conditional ☐ Revise ☐ N/A |  |
| 3 Requirements baseline | Needs and requirements approved before design commitment | C3 traceability and alternatives |  | ☐ Proceed ☐ Conditional ☐ Revise ☐ N/A |  |
| 4 Design and procurement readiness | Design contract standards security and test approach ready | C4 through C6 and applicable Part D |  | ☐ Proceed ☐ Conditional ☐ Revise ☐ N/A |  |
| 5 Deployment and test readiness | Sites environments staff procedures and evidence ready | Approved test plans procedures and transition plan |  | ☐ Proceed ☐ Conditional ☐ Revise ☐ N/A |  |
| 6 Acceptance and operations | Requirements verified service validated owners ready | Test reports O&M records training as-builts acceptance report |  | ☐ Proceed ☐ Conditional ☐ Revise ☐ N/A |  |
| 7 Post implementation | Benefits performance issues and updates documented | Performance review lessons learned architecture and standards updates |  | ☐ Proceed ☐ Conditional ☐ Revise ☐ N/A |  |

## E3 Open items and decision log

| ID | Issue decision or assumption | Owner | Due | Disposition | Closed |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |

# Part F Determination review and signatures

## F1 Final systems engineering determination

| ITS determination | ☐ Not ITS ☐ ITS element ☐ ITS project |
| --- | --- |
| 23 CFR 940.11 | ☐ Applies ☐ Does not apply ☐ FHWA determination attached |
| Documentation level | ☐ Level 1 Streamlined ☐ Level 2 Tailored ☐ Level 3 Full |
| Architecture status | ☐ Consistent ☐ Architecture update initiated ☐ Project architecture completed |
| Requirements status | ☐ Baseline approved ☐ Conditional ☐ Not ready |
| Operations readiness | ☐ Owner resources and procedures confirmed ☐ Conditional ☐ Not ready |
| Acceptance status | ☐ Accepted ☐ Conditionally accepted ☐ Not accepted ☐ Preconstruction review only |

Conditions exceptions and required follow up

List conditions of concurrence, approved exceptions, responsible owners, deadlines, and the project consequence if unresolved.

## F2 Review record

| Role | Name and title | Signature or concurrence record | Date |
| --- | --- | --- | --- |
| Project manager |  |  |  |
| Primary system owner |  |  |  |
| Operations owner |  |  |  |
| Maintenance owner |  |  |  |
| Regional Traffic and Safety |  |  |  |
| Information technology or cybersecurity |  |  |  |
| Statewide TSMO or ITS reviewer |  |  |  |
| FHWA reviewer when required |  |  |  |
| Other |  |  |  |

# Appendix A Completion guidance

## Use existing material without losing traceability

A project may rely on an approved statewide system document, standard specification, typical design, master test plan, or prior analysis when it truly applies. Record the document title, version, date, section, owner, and any project-specific differences. Do not cite a web page or shared folder without identifying the controlling document and version.

## Keep requirements separate from design

A requirement describes a necessary function, performance, interface, constraint, or quality. A design describes how the requirement will be met. For example, a requirement might state that an operator shall receive a device communication alarm within a defined time. Naming a particular modem, platform, or vendor is a design choice unless compatibility or policy makes it a justified constraint.

## Scale the work deliberately

A streamlined analysis can be a concise checklist supported by approved standard requirements, specifications, test procedures, and an established operations plan. A full analysis usually needs a Concept of Operations, controlled requirements, architecture and interface documentation, a systems-engineering management approach, traceability, staged verification and validation, and formal transition to operations. Project cost alone does not determine complexity.

## Update the checklist through the lifecycle

The initial checklist records what is known and what must be developed. Update it when the concept, architecture, requirements, procurement strategy, design, testing, or operational ownership changes. The final project record should show what was actually built, tested, accepted, and transferred to the operating organization.

## Suggested document references

| Reference | Version and date | Location or project section |
| --- | --- | --- |
| Design Study Report |  |  |
| Concept of Operations |  |  |
| ITS architecture mapping |  |  |
| Systems engineering management plan |  |  |
| System requirements specification |  |  |
| Requirements traceability matrix |  |  |
| Interface-control document |  |  |
| Cybersecurity plan and risk assessment |  |  |
| Verification and validation plan |  |  |
| Test procedures and reports |  |  |
| Operations and maintenance plan |  |  |
| Training and transition plan |  |  |
| As-built and configuration baseline |  |  |
| Acceptance report |  |  |

# Appendix B Definitions

| Term | Working definition |
| --- | --- |
| Architecture Reference for Cooperative and Intelligent Transportation | ARC IT is the national reference architecture used to support planning definition and integration of ITS. Regional and statewide architectures are tailored from it. |
| Concept of Operations | A user-oriented description of the problem operational environment stakeholders roles and how the proposed system will be used to meet needs. |
| Intelligent Transportation System | Electronics communications or information processing used singly or in combination to improve the efficiency or safety of a surface transportation system. |
| ITS architecture | A framework that identifies stakeholders systems services functions interfaces and information exchanges needed for institutional and technical integration. |
| ITS project | A project that in whole or in part funds technologies or systems of technologies that provide or significantly contribute to one or more ITS services. |
| System owner | The accountable organization or role that controls the service baseline investment priorities changes and lifecycle decisions. The system owner may be different from the day-to-day operator or maintainer. |
| Systems engineering analysis | A structured analysis scaled to project scope that addresses architecture roles requirements alternatives procurement standards testing and the resources needed for operations and management. |
| Validation | Objective evidence that the completed system fulfills stakeholder needs and supports the intended operational use. |
| Verification | Objective evidence that a requirement design or implementation satisfies its specified criteria. |

# Appendix C Authorities and resources

23 CFR 940.11 Project implementation

23 CFR Part 940 Intelligent Transportation System Architecture and Standards

FHWA Systems Engineering for ITS

ARC IT national reference architecture

Alaska Highway Preconstruction Manual Chapter 4

DOT&PF Preconstruction standards and manuals

Published Alaska Iways ITS architecture legacy page

2019 Alaska systems engineering checklist being replaced

Use the current version of each authority and resource. The Alaska Iways architecture and 2019 checklist links are included to maintain continuity with currently published material while DOT&PF updates its statewide TSMO and ITS program guidance.