## Complete Project
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category
574, 684, 1193 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | If project is selected, discuss with Regional Preconstruction Engineer and applicable Statewide resource heads to prioritize project for Statewide and Regional resources due to funding timeline requirements. Utilize consultant support if needed. | 2 | 3 | Medium | Other Risks | Categories from the NOFO
574, 684, 1193 | Legislative approval not granted. | Keep Commissioner apprised of grant application and status and utilize PIO as needed for messaging to Legislators if questions arise. | 1 | 5 | Medium | Funding Uncertainties | Procurement Delays
574, 684, 1193 | Material escalation due to tariffs or inflation. | Utilize appropriate contingency in programming estimates to ensure project cost does not exceed grant program allocation. Evaluate cost estimate for major cost components up front and monitor those elements for potential inflation as project design progresses. Communicate with Statewide Planning early on any project cost element that may require STIP funds to cover grant funding differences to ensure funds are available to obligate project on time. | 3 | 3 | Medium | Cost Uncertainties | Environmental Uncertainties
574, 684, 1193 | State funds not available for match. | Keep Commissioner apprised of grant application and status and utilize PIO as needed for messaging to Legislature on importance of capturing grant funding. | 1 | 5 | Medium | Funding Uncertainties | Cost Uncertainties
574, 684, 1193 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Utilize appropriate contingency in programming estimates (typically 15-20%) to ensure project cost does not exceed grant program allocation. | 2 | 2 | Low | Cost Uncertainties | Funding Uncertainties
574, 684, 1193 | Cost negotiations with design consultant delay NTP and subsequent advertise date. | Utilize in house resources, Northern Region has adequate staffing to support the current project. No project element requires special expertise outside Department capabilities. | 1 | 3 | Low | Cost Uncertainties | Natural Hazard Risks
574, 684, 1193 | Individual USACE permit or USCG permit required. | Monitor potential for changes in NWP requirements. Project is currently a FHWA CE so worst case under current NWP program is NWP 23. | 1 | 3 | Low | Environmental Uncertainties | Construction Risks
574, 684, 1193 | Material escalation due to limited suppliers and competing work. | Utilize appropriate contingency in programming estimates to ensure project cost does not exceed grant program allocation. Advertise project with sufficient time for material suppliers to balance workload (typically winter advertising ideal). | 1 | 3 | Low | Cost Uncertainties | Other Risks
574, 684, 1193 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Coordinate with Statewide Planning to ensure additional funds are available if needed, and communicate overall reduction in STIP impact as project is currently 100% STIP. Project is shown in NR funding plan for construction year 2021 using STIP funds currently. | 1 | 3 | Low | Funding Uncertainties
574, 684, 1193 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Refine design to remain within existing ROW if detailed design indicates some work falls outside the existing ROW. | 1 | 3 | Low | Environmental Uncertainties
574, 684, 1193 | Utility relocation required. | Identify utility relocation requirements early and coordinate with Delivery Team utility engineer to prioritize relocation schedule. | 1 | 3 | Low | Construction Risks
574, 684, 1193 | Insufficient material available (quality and/or quantity). | Evaluate existing materials site information and update permits as required. | 1 | 2 | Low | Construction Risks
574, 684, 1193 | Cost inflation due to real estate price increase. | N/A | 0 | 0 | None | Cost Uncertainties
574, 684, 1193 | Project environmental document not approved in time. | N/A | 0 | 0 | None | Environmental Uncertainties

## Bridge #574
Risk Register | [6 empty] | Bridge No. 1 - Gulkana River Bridge No. 574, Richardson Highway
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category | Remarks
574 | State funds not available for match. | Keep Commissioner apprised of grant application and status and utilize PIO as needed for messaging to Legislature on importance of capturing grant funding. | 1 | 5 | Medium | Funding Uncertainties |  | Categories from the NOFO
574 | Legislative approval not granted. | Keep Commissioner apprised of grant application and status and utilize PIO as needed for messaging to Legislators if questions arise. | 1 | 5 | Medium | Funding Uncertainties | Some potential for this to occur as these bridges are all in one legislative district, however rare that legislature would pass up 90/10 split funds. | Procurement Delays
574 | Material escalation due to limited suppliers and competing work. | Utilize appropriate contingency in programming estimates to ensure project cost does not exceed grant program allocation. Advertise project with sufficient time for material suppliers to balance workload (typically winter advertising ideal). | 2 | 3 | Medium | Cost Uncertainties | Polyester concrete overlay is specialty and typically requires subcontractor from Washington or East Coast to complete. | Environmental Uncertainties
574 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | If project is selected, discuss with Statewide Bridge Design to prioritize efforts to meet fixed timeline. | 1 | 3 | Low | Other Risks | Bridge Design is only support group resource needed for this project. | Cost Uncertainties
574 | Material escalation due to tariffs or inflation. | Utilize appropriate contingency in programming estimates to ensure project cost does not exceed grant program allocation. Evaluate cost estimate for major cost components up front and monitor those elements for potential inflation as project design progresses. Communicate with Statewide Planning early on any project cost element that may require STIP funds to cover grant funding differences to ensure funds are available to obligate project on time. | 1 | 3 | Low | Cost Uncertainties | Majority of work items are superstructure repairs, predominant cost item is polyester concrete overlay, low probably of inflation issues with this work. | Funding Uncertainties
574 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | N/A | 0 | 0 | None | Cost Uncertainties | Nature of work does not require information beyond what is available in routine inspection reports. | Natural Hazard Risks
574 | Cost inflation due to real estate price increase. | N/A | 0 | 0 | None | Cost Uncertainties | No ROW acquisition | Construction Risks
574 | Cost negotiations with design consultant delay NTP and subsequent advertise date. | N/A | 0 | 0 | None | Cost Uncertainties | In-house design | Other Risks
574 | Individual USACE permit or USCG permit required. | N/A | 0 | 0 | None | Environmental Uncertainties | No permits required.
574 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | N/A | 0 | 0 | None | Funding Uncertainties | Rehabilitation project (no non-bridge work), all work is eligible.
574 | Project environmental document not approved in time. | N/A | 0 | 0 | None | Environmental Uncertainties | Project environmental document complete.
574 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | N/A | 0 | 0 | None | Environmental Uncertainties | Rehabilitation work is all programmatic and no permits required. No adverse affect 106 finding.
574 | Utility relocation required. | N/A | 0 | 0 | None | Construction Risks | No utility work involved.
574 | Insufficient material available (quality and/or quantity). | N/A | 0 | 0 | None | Construction Risks | Current design would require specialized materials imported to project site (e.g. polyester concrete aggregate) eliminating risk that local materials wouldn't suffice.

## Bridge #684
Risk Register | [6 empty] | Bridge No. 2 - Rock Creek Bridge No. 684, MP 25 Denali Highway
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category | Remarks
684 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | If project is selected, discuss with Regional Preconstruction Engineer and applicable Statewide resource heads to prioritize project for Statewide and Regional resources due to funding timeline requirements. Utilize consultant support if needed. | 2 | 3 | Medium | Other Risks | Foundation drilling likely to be delayed until 2019 season, ROW needs unknown at this time. Bridge has foundation report from 1995 that can be used for making reasonable assumptions on foundation requirements. | Categories from the NOFO
684 | Legislative approval not granted. | Keep Commissioner apprised of grant application and status and utilize PIO as needed for messaging to Legislators if questions arise. | 1 | 5 | Medium | Funding Uncertainties | Some potential for this to occur as these bridges are all in one legislative district, however rare that legislature would pass up 90/10 split funds. | Procurement Delays
684 | Material escalation due to tariffs or inflation. | Utilize appropriate contingency in programming estimates to ensure project cost does not exceed grant program allocation. Evaluate cost estimate for major cost components up front and monitor those elements for potential inflation as project design progresses. Communicate with Statewide Planning early on any project cost element that may require STIP funds to cover grant funding differences to ensure funds are available to obligate project on time. | 3 | 3 | Medium | Cost Uncertainties | Potential for steel price to escalate significantly (piling, rebar). | Environmental Uncertainties
684 | State funds not available for match. | Keep Commissioner apprised of grant application and status and utilize PIO as needed for messaging to Legislature on importance of capturing grant funding. | 1 | 5 | Medium | Funding Uncertainties |  | Cost Uncertainties
684 | Utility relocation required. | Identify utility relocation requirements early and coordinate with Delivery Team utility engineer to prioritize relocation schedule. | 2 | 3 | Medium | Construction Risks | Utility relocation needs not known at this time. | Funding Uncertainties
684 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Utilize appropriate contingency in programming estimates (typically 15-20%) to ensure project cost does not exceed grant program allocation. Base estimates on recently constructed projects in the area (Seattle Creek Bridge 2016) and historical geotechnical information. | 2 | 2 | Low | Cost Uncertainties | Utility impacts unknown at this time | Natural Hazard Risks
684 | Cost negotiations with design consultant delay NTP and subsequent advertise date. | Utilize in house resources, Northern Region has adequate staffing to support the current project. No project element requires special expertise outside Department capabilities. | 1 | 3 | Low | Cost Uncertainties | Environmental document and permitting work done by consultant on a term agreement with limited funds. Use of in-house resources recommended if available. | Construction Risks
684 | Individual USACE permit or USCG permit required. | Monitor potential for changes in NWP requirements. Project is currently a FHWA CE so worst case under current NWP program is NWP 23. | 1 | 3 | Low | Environmental Uncertainties | USCG permit not required, NWP anticipated for USACE authorization. | Other Risks
684 | Material escalation due to limited suppliers and competing work. | Utilize appropriate contingency in programming estimates to ensure project cost does not exceed grant program allocation. Advertise project with sufficient time for material suppliers to balance workload (typically winter advertising ideal). | 1 | 3 | Low | Cost Uncertainties | Girders are manufactured by only 2 entities in state (and 1 has had quality issues).
684 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Coordinate with Statewide Planning to ensure additional funds are available if needed, and communicate overall reduction in STIP impact as project is currently 100% STIP. Project is shown in NR funding plan for construction year 2021 using STIP funds currently. | 1 | 3 | Low | Funding Uncertainties | At this time all project elements appear eligible for grant funding.
684 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Refine design to remain within existing ROW if detailed design indicates some work falls outside the existing ROW. | 1 | 3 | Low | Environmental Uncertainties | Project is adjacent to archaeological district and closest Materials Sites proposed have had environmental challenges historically. There are numerous materials sites along the Rich Hwy however.
684 | Insufficient material available (quality and/or quantity). | Evaluate existing materials site information and update permits as required. | 1 | 2 | Low | Construction Risks | All proposed material is from existing materials sites. Road is gravel surface, no paving aggregate required.
684 | Overrun of piling during construction resulting in the need for deeper piles and more time for construction | Add funds and include in contingency. | 2 | 1 | Low | Procurement Delays | In general, the uncertainty that accompanies most bridge construction projects is applicable to this bridge.
684 | Cost inflation due to real estate price increase. | N/A | 0 | 0 | None | Cost Uncertainties | Adjacent land interests in the project area are government (Alaska DNR or BLM), which are no cost land transfers.
684 | Project environmental document not approved in time. | N/A | 0 | 0 | None | Environmental Uncertainties | Environmental document complete.

## Bridge #1193
Risk Register | [6 empty] | Bridge No. 3 - Chokosna River Bridge No. 1193, MP 27 McCarthy Road
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category | Remarks
1193 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | If project is selected, discuss with Regional Preconstruction Engineer and applicable Statewide resource heads to prioritize project for Statewide and Regional resources due to funding timeline requirements. Utilize consultant support if needed. | 2 | 3 | Medium | Other Risks | Foundation drilling has not been completed and historical data for foundation information has not been found yet. Anticipate water aspect to be minimal (SW Hydraulic work could be handled by region if needed). ROW and utility support not needed. | Categories from the NOFO
1193 | Legislative approval not granted. | Keep Commissioner apprised of grant application and status and utilize PIO as needed for messaging to Legislators if questions arise. | 1 | 5 | Medium | Funding Uncertainties | Some potential for this to occur as these bridges are all in one legislative district, however rare that legislature would pass up 90/10 split funds. | Procurement Delays
1193 | Material escalation due to tariffs or inflation. | Utilize appropriate contingency in programming estimates to ensure project cost does not exceed grant program allocation. Evaluate cost estimate for major cost components up front and monitor those elements for potential inflation as project design progresses. Communicate with Statewide Planning early on any project cost element that may require STIP funds to cover grant funding differences to ensure funds are available to obligate project on time. | 3 | 3 | Medium | Cost Uncertainties | Potential for steel price to escalate significantly (piling, rebar). | Environmental Uncertainties
1193 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Coordinate with Statewide Planning to ensure additional funds are available if needed, and communicate overall reduction in STIP impact as project is currently 100% STIP. Project is shown in NR funding plan for construction year 2021 using STIP funds currently. | 2 | 3 | Medium | Funding Uncertainties | Potential for culvert replacement of Chokosna Tributary to be not eligible. Project is currently a STIP project so we would just be reducing the STIP impact with the bridge grant funding so not terribly concerned. | Cost Uncertainties
1193 | State funds not available for match. | Keep Commissioner apprised of grant application and status and utilize PIO as needed for messaging to Legislature on importance of capturing grant funding. | 1 | 5 | Medium | Funding Uncertainties |  | Funding Uncertainties
1193 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Utilize appropriate contingency in programming estimates (typically 15-20%) to ensure project cost does not exceed grant program allocation. Base estimates on recently constructed projects in the area (Lakina River Bridge 2015) and historical geotechnical information. | 2 | 2 | Low | Cost Uncertainties | Centerline investigation, M.S. investigation, and reconnaissance reporting available from 1968 and 1974 for project area. | Natural Hazard Risks
1193 | Individual USACE permit or USCG permit required. | Monitor potential for changes in NWP requirements. Project is currently a FHWA CE so worst case under current NWP program is NWP 23. | 1 | 3 | Low | Environmental Uncertainties | USCG permit not required, NWP anticipated for USACE authorization. | Construction Risks
1193 | Material escalation due to limited suppliers and competing work. | Utilize appropriate contingency in programming estimates to ensure project cost does not exceed grant program allocation. Advertise project with sufficient time for material suppliers to balance workload (typically winter advertising ideal). | 1 | 3 | Low | Cost Uncertainties | Girders are manufactured by only 2 entities in state (and 1 has had quality issues and other may be retiring). | Other Risks
1193 | Insufficient material available (quality and/or quantity). | Evaluate existing materials site information and update permits as required. | 1 | 2 | Low | Construction Risks | All proposed material is from existing materials sites. Road is gravel surface, no paving aggregate required.
1193 | Overrun of piling during construction resulting in the need for deeper piles and more time for construction | Add funds and include in contingency. | 2 | 1 | Low | Procurement Delays | In general, the uncertainty that accompanies most bridge construction projects is applicable to this bridge.
1193 | Cost inflation due to real estate price increase. | N/A | 0 | 0 | None | Cost Uncertainties | Not applicable, project does not propose ROW acquisition.
1193 | Cost negotiations with design consultant delay NTP and subsequent advertise date. | N/A | 0 | 0 | None | Cost Uncertainties | Project will be completed with in house resources.
1193 | Project environmental document not approved in time. | N/A | 0 | 0 | None | Environmental Uncertainties | Environmental document complete.
1193 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | N/A | 0 | 0 | None | Environmental Uncertainties | Environmental document documents this is a low scrutiny area.
1193 | Utility relocation required. | N/A | 0 | 0 | None | Construction Risks | No utilities present.