## Complete Project
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category
ALL | State funds not available for match. | Have Commissioner work with Legislature to understand importance of Grant deadlines. As a last resort, delay project | 1 | 5 | Medium | Funding Uncertainties | Categories from the NOFO
253 | Individual USACE permit or USCG permit delays | Increase consultation early. Avoid, minimize, mitigate. | 2 | 3 | Medium | Environmental Uncertainties | Procurement Delays
725 | Unanticipated Utility relocation required. | Develop construction phasing plan to account for unforeseen delays | 2 | 3 | Medium | Construction Risks | Environmental Uncertainties
253 | Unusually severe weather | Delay or add compensation | 3 | 3 | Medium | Construction Risks | Cost Uncertainties
ALL | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | conduct regular project meetings with support groups and track progress using MS Project | 1 | 3 | Low | Procurement Delays | Funding Uncertainties
ALL | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Include contingency. | 1 | 2 | Low | Cost Uncertainties | Natural Hazard Risks
725 | Cost inflation due to real estate price increase. | Seek additional funding or delay the project. | 2 | 2 | Low | Procurement Delays | Construction Risks
ALL | Legislative approval not granted. | Delay project | 1 | 2 | Low | Procurement Delays | Other Risks
ALL | Material escalation due to limited suppliers and competing work. | Add funds or delay project. | 1 | 2 | Low | Cost Uncertainties
ALL | Material escalation due to tariffs or inflation. | Add funds or delay project. | 1 | 2 | Low | Cost Uncertainties
ALL | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Other funds already identified. | 1 | 2 | Low | Funding Uncertainties
ALL | Project environmental document not approved in time. | conduct regular project meetings with EV groups and track progress using MS Project | 1 | 3 | Low | Environmental Uncertainties
253 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Increase consultation early | 1 | 3 | Low | Environmental Uncertainties

## Hoadly Ck 725
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category
725 | Existing large water line adjacent to bridge on upstream side. Current location creates a geometric constraint of bridge/construction footprint. | Coordinate with owner to determine where to locate proposed utility. | 5 | 3 | High | Other Risks | Categories from the NOFO
725 | Design/Construction with current ROW tightly constrained on all 4 corners of existing bridge. | Coordinate with land owners early for potential ROW acquisition. | 5 | 3 | High | Other Risks | Procurement Delays
725 | State funds not available for match. | Have Commissioner work with Legislature to understand importance of Grant deadlines. As a last resort, delay project | 1 | 5 | Medium | Funding Uncertainties | Environmental Uncertainties
725 | Unanticipated utility relocation required. | Develop construction phasing plan to account for unforeseen delays | 2 | 3 | Medium | Construction Risks | Funding Uncertainties
725 | Construction changing stream flow causing scour to downstream structures supported by piles in creek bed. | Leave existing bridge abutments in place and span over them with new structure so streamflow remain unaffected. Document condition of existing downstream foundations prior to construction. Coordinate with owners to create a scour protection plan. | 4 | 3 | Medium | Other Risks | Natural Hazard Risks
725 | Existing overhead powerline above bridge with foundations cast into approaching sidewalk. | Coordinate with power company to relocate lines prior to construction. | 5 | 2 | Medium | Other Risks | Construction Risks
725 | Construction during summer tourist season with heave traffic along Tongass Ave. | Plan detours or design phased construction accordingly to allow passage of traffic. | 5 | 2 | Medium | Other Risks | Other Risks
725 | Existing bridge continues to deteriorate and requires load restrictions (similar to what occurred at the nearby First Waterfall Creek Bridge) | Reduce width to signalized one-lane bridge or install modular truss bridge | 2 | 5 | Medium | Other Risks
725 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | Conduct regular project meetings with support groups and track progress using MS Project | 1 | 3 | Low | Procurement Delays
725 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Include contingency. | 1 | 2 | Low | Cost Uncertainties
725 | Cost inflation due to real estate price increase. | Seek additional funding or delay the project. | 2 | 2 | Low | Procurement Delays
725 | Individual USACE permit or USCG permit delays | Increase consultation early. Avoid, minimize, mitigate. | 1 | 3 | Low | Environmental Uncertainties
725 | Legislative approval not granted. | Delay project | 1 | 2 | Low | Funding Uncertainties
725 | Material escalation due to limited suppliers and competing work. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
725 | Material escalation due to tariffs or inflation. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
725 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Other funds already identified. | 1 | 2 | Low | Funding Uncertainties
725 | Project environmental document not approved in time. | Conduct regular project meetings with EV groups and track progress using MS Project | 1 | 3 | Low | Environmental Uncertainties
725 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Increase consultation early | 1 | 3 | Low | Environmental Uncertainties
725 | Unusually severe weather slows construction | Delay or add compensation | 1 | 1 | Low | Construction Risks
725 | Fish window creating construction delays | Plan construction event accordingly | 2 | 2 | Low | Construction Risks

## Herring Cove 253
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category
253 | State funds not available for match. | Have Commissioner work with Legislature to understand importance of Grant deadlines. As a last resort, delay project | 1 | 5 | Medium | Funding Uncertainties | Categories from the NOFO
253 | Individual USACE permit or USCG permit delays | Increase consultation early. Avoid, minimize, mitigate. | 2 | 3 | Medium | Environmental Uncertainties | Environmental Uncertainties
253 | Project environmental document not approved in time. | Conduct regular project meetings with EV groups and track progress using MS Project | 2 | 3 | Medium | Environmental Uncertainties | Cost Uncertainties
253 | Unusually severe weather delays construction | Delay or add compensation | 3 | 3 | Medium | Construction Risks | Funding Uncertainties
253 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | Conduct regular project meetings with support groups and track progress using MS Project | 1 | 3 | Low | Procurement Delays | Natural Hazard Risks
253 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Include contingency. | 1 | 2 | Low | Cost Uncertainties | Construction Risks
253 | Cost inflation due to real estate price increase. | Not necessary. Project has minor ROW costs. | 1 | 2 | Low | Cost Uncertainties | Other Risks
253 | Legislative approval not granted. | Delay project | 1 | 2 | Low | Funding Uncertainties
253 | Material escalation due to limited suppliers and competing work. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
253 | Material escalation due to tariffs or inflation. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
253 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Other funds already identified. | 1 | 2 | Low | Funding Uncertainties
253 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Increase consultation early | 1 | 3 | Low | Environmental Uncertainties
253 | Unanticipated Utility relocation required. | Develop construction phasing plan to account for unforeseen delays | 1 | 3 | Low | Construction Risks

## Ward Creek 747
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category
747 | State funds not available for match. | Have Commissioner work with Legislature to understand importance of Grant deadlines. As a last resort, delay project | 1 | 5 | Medium | Funding Uncertainties | Categories from the NOFO
747 | Pile overruns for abutment foundations | Locate foundation test hold as close to planned foundation locations as possible. | 2 | 4 | Medium | Construction Risks | Procurement Delays
747 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | Conduct regular project meetings with support groups and track progress using MS Project | 1 | 3 | Low | Procurement Delays | Environmental Uncertainties
747 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Include contingency. | 1 | 2 | Low | Cost Uncertainties | Cost Uncertainties
747 | Cost inflation due to real estate price increase. | Not necessary. Project has minor ROW costs. | 1 | 1 | Low | Cost Uncertainties | Funding Uncertainties
747 | Individual USACE permit or USCG permit delays | Increase consultation early. Avoid, minimize, mitigate. | 1 | 3 | Low | Environmental Uncertainties | Natural Hazard Risks
747 | Legislative approval not granted. | Delay project | 1 | 2 | Low | Funding Uncertainties | Construction Risks
747 | Material escalation due to limited suppliers and competing work. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties | Other Risks
747 | Material escalation due to tariffs or inflation. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
747 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Other funds already identified. | 1 | 2 | Low | Funding Uncertainties
747 | Project environmental document not approved in time. | Conduct regular project meetings with EV groups and track progress using MS Project | 1 | 2 | Low | Environmental Uncertainties
747 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Increase consultation early | 1 | 3 | Low | Environmental Uncertainties
747 | Unanticipated Utility relocation required. | Develop construction phasing plan to account for unforeseen delays | 1 | 3 | Low | Construction Risks
747 | Unusually severe weather | Delay or add compensation | 1 | 1 | Low | Construction Risks
747 | Construction staging doesn't allow overloads to use bridge | Alert MS&CVE for public outreach | 2 | 2 | Low | Construction Risks